## Sheet1
Report Date | Organisation | Business Area | Portfolio ID | Project ID | Risk ID | Risk Unique ID | Risk Type | Cont | Status | Criticality | PreMit_Criticality_Value | Main Risk Cat. | Risk | Owner | Start | Relief | Pre Prob | Pre Cost | Pre Factored Cost | Strategy | Post Prob | Post Cost | Post Factored Cost | PostMit_Criticality | PostMit_Criticality_Value | Trend | PreMit_Sched_Impact_Prob | PreMit_Sched_Impact_Min | PreMit_Sched_Impact_Most_Likely | PreMit_Sched_Impact_Max | PreMit_Sched_Impact | PreMit_Sched_Impact_Prob.1 | PostMit_Sched_Impact_Min | PostMit_Sched_Impact_Most_Likely | PostMit_Sched_Impact_Max | PostMit_Sched_Impact | Cost Reduction | Probability Reduction | Criticality Reduction | Mitigation Impact Score
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk004 | Project_002_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability of Test Equipment | Person_133 | 2014-03-26 | 2016-08-08 | 0.2 | 0.081443 | 0.016289 | Avoid | 0.2 | 0.081443 | 0.016289 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk006 | Project_002_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Additional Pressure Testing | Person_650 | 2014-06-14 | 2016-08-08 | 0.25 | 0.035539 | 0.0088847 | Avoid | 0.25 | 0.035539 | 0.0088847 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 01:00 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK007 | Project_004_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 01:00 | 2016-03-21 01:00 | 0.2 | 0.15317 | 0.030633 | Reduce | 0.2 | 0.10883 | 0.021765 | H3 | 3 | Stable | 0.9 | 114 | 138 | 143 | 134.8333 | 0.2 | 19 | 50 | 79 | 49.6667 | 28.9481 | 0 | 1 | 17.3689
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk011 | Project_002_Risk011 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Testing | Person_175 | 2014-06-29 | 2016-08-07 | 0.41 | 0.071669 | 0.029384 | Reduce | 0.1 | 0.0088847 | 0.00088847 | H3 | 3 | Stable | 0.8 | 105 | 140 | 156 | 136.8333 | 0.1 | 22 | 59 | 76 | 55.6667 | 87.6032 | 75.6098 | 1 | 54.8302
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 01:00 | 2016-10-19 01:00 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.5 | 104 | 123 | 143 | 123.1667 | 0.4 | 9 | 51 | 72 | 47.5 | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK004 | Project_004_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 0.2 | 0.14752 | 0.029504 | Avoid | 0.2 | 0.14752 | 0.029504 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK003 | Project_004_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-05-24 | 2016-03-21 01:00 | 0.2 | 0.060459 | 0.012092 | Avoid | 0.2 | 0.060459 | 0.012092 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK006 | Project_004_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2014-11-19 01:00 | 2016-03-21 01:00 | 0.1 | 0.049978 | 0.0049978 | Avoid | 0.1 | 0.049978 | 0.0049978 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk005 | Project_002_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2014-06-14 | 2016-08-08 | 0.3 | 0.035539 | 0.010662 | Avoid | 0.3 | 0.035539 | 0.010662 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 01:00 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK005 | Project_004_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk008 | Project_002_Risk008 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2014-08-20 | 2016-08-07 | 0.1 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | -100 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK002 | Project_004_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 0.5 | 0.15317 | 0.076583 | Avoid | 0.5 | 0.15317 | 0.076583 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk009 | Project_002_Risk009 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2014-06-14 | 2016-08-07 | 0.1 | 0.01925 | 0.001925 | Avoid | 0.1 | 0.01925 | 0.001925 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | RISK012 | Project_002_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Resourcing Suitably Qualified and experienced staff availability | Person_650 | 2015-11-21 | 2016-08-07 | 0.2 | 0.05627 | 0.011254 | Reduce | 0.2 | 0.05627 | 0.011254 | H3 | 3 | Stable | 0.9 | 91 | 134 | 156 | 130.5 | 0.4 | 3 | 58 | 73 | 51.3333 | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-010 | Project_005_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Risk that required resources (people and rigs) will not be available as required due to other projects/bids (Customer & Internal) | Person_470 | 2011-11-11 01:00 | 2016-07-20 | 0.25 | 3.9852 | 0.9963 | Reduce | 0.1 | 3.9852 | 0.39852 | H3 | 3 | Stable | 0.6 | 82 | 138 | 153 | 131.1667 | 0.1 | 31 | 54 | 68 | 52.5 | 0 | 60 | 1 | 1.8
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-034 | Project_005_Risk-034 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project delay causes cost impact to project | Person_470 | 2011-12-02 01:00 | 2016-08-18 01:00 | 0.5 | 16.3745 | 8.1873 | Reduce | 0.4 | 16.3745 | 6.5498 | H2 | 4 | Stable | 0.6 | 92 | 126 | 157 | 125.5 | 0.4 | 3 | 49 | 72 | 45.1667 | 0 | 20 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-060 | Project_005_Risk-060 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Technical Acceptance may be more difficult than anticipated | Person_470 | 2014-06-11 | 2016-07-20 | 0.5 | 1.6266 | 0.8133 | Reduce | 0.3 | 1.6266 | 0.48798 | H3 | 3 | Stable | 0.8 | 87 | 137 | 155 | 131.6667 | 0.1 | 7 | 40 | 73 | 40 | 0 | 40 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.9 | 99 | 124 | 155 | 125 | 0.1 | 27 | 46 | 79 | 48.3333 | 25.8065 | 20 | 0 | 15.4839
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_007 | R-057 | Project_007_R-057 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Interface cannot be fully proven until installation | Person_245 | 2015-05-24 | 2015-12-21 19:00 | 0.4 | 0.97576 | 0.3903 | Reduce | 0.1 | 0.48788 | 0.048788 | H3 | 3 | Improving | 0.7 | 111 | 134 | 153 | 133.3333 | 0.2 | 10 | 46 | 71 | 44.1667 | 50 | 75 | 1 | 32.25
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_007 | R-073 | Project_007_R-073 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Legacy System Issues | Person_386 | 2013-12-03 19:00 | 2016-02-19 19:00 | 0.7 | 0.55755 | 0.39029 | Reduce | 0.4 | 0.12197 | 0.048788 | H2 | 4 | Stable | 0.8 | 118 | 133 | 147 | 132.8333 | 0.4 | 6 | 41 | 63 | 38.8333 | 78.1239 | 42.8571 | 0 | 46.8743
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_007 | R-074 | Project_007_R-074 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | System INtegration Resources | Person_386 | 2013-12-03 19:00 | 2016-05-15 | 0.95 | 0.51354 | 0.48787 | Reduce | 0.95 | 0.51354 | 0.48787 | H1 | 5 | Stable | 0.8 | 91 | 139 | 160 | 134.5 | 0.3 | 3 | 43 | 65 | 40 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_007 | R-075 | Project_007_R-075 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Late Delivery | Person_386 | 2013-12-03 19:00 | 2015-12-20 19:00 | 0.6 | 0.48788 | 0.29273 | Reduce | 0.2 | 0.48788 | 0.097576 | H3 | 3 | Stable | 0.7 | 98 | 127 | 159 | 127.5 | 0.1 | 22 | 54 | 60 | 49.6667 | 0 | 66.6667 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_007 | R-076 | Project_007_R-076 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Contract Extension | Person_386 | 2013-12-03 19:00 | 2016-02-19 19:00 | 0.7 | 6.3425 | 4.4397 | Avoid | 0.05 | 0.97576 | 0.048788 | H3 | 3 | Stable | [10 empty] | 84.6154 | 92.8571 | 0 | 50.7692
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_007 | R-077 | Project_007_R-077 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Mech Counters | Person_386 | 2013-12-03 19:00 | 2016-03-21 19:00 | 0.5 | 0.3903 | 0.19515 | Avoid | 0.5 | 0.19515 | 0.097576 | H3 | 3 | Stable | [10 empty] | 50 | 0 | 0 | 30
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-043 | Project_008_Risk-043 | Opportunitity | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Joint courseware and tech pubs team | Person_280 | 2014-11-21 01:00 | 2016-11-19 01:00 | 0.5 | 28.2191 | 14.1096 | -- | 0.5 | 12.4997 | 6.2499 | H2 | 4 | Stable | [10 empty] | 55.7047 | 0 | 0 | 33.4228
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-063 | Project_008_Risk-063 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Annex | Person_639 | 2015-08-22 01:00 | 2018-05-21 | 1 | 13.6519 | 13.6519 | Reduce | 1 | 8.2858 | 8.2858 | H2 | 4 | Improving | 0.7 | 113 | 126 | 145 | 127 | 0.3 | 3 | 59 | 71 | 51.6667 | 39.3064 | 0 | 0 | 23.5838
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-059 | Project_008_Risk-059 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Project Resource Efficencies | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 0.4 | 50.3777 | 20.1511 | -- | 0.4 | 50.3777 | 20.1511 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-072 | Project_008_Risk-072 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply chain | Saving on budget for repairs | Person_565 | 2016-01-22 01:00 | 2018-08-21 | 0.5 | 13.8255 | 6.9127 | -- | 0.5 | 13.8255 | 6.9127 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK004 | Project_010_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Export License | Person_359 | 2015-02-18 01:00 | 2017-08-20 01:00 | 0.8 | 0.18482 | 0.14786 | Reduce | 0.8 | 0.18482 | 0.14786 | H1 | 5 | Worsening | 0.5 | 84 | 129 | 146 | 124.3333 | 0.1 | 35 | 48 | 79 | 51 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 01:00 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.8 | 103 | 136 | 153 | 133.3333 | 0.2 | 10 | 53 | 75 | 49.5 | 0 | 40 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.7 | 0.92411 | 0.64688 | Reduce | 0.3 | 0.36965 | 0.11089 | H2 | 4 | Worsening | 0.6 | 89 | 122 | 151 | 121.3333 | 0.4 | 25 | 45 | 69 | 45.6667 | 60 | 57.1429 | 0 | 36
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 01:00 | 2016-04-21 | 0.5 | 4.0661 | 2.033 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.8 | 99 | 140 | 153 | 135.3333 | 0.3 | 28 | 56 | 60 | 52 | 0 | 90 | 1 | 2.7
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.3 | 0.46206 | 0.13862 | H2 | 4 | Worsening | 0.8 | 105 | 135 | 155 | 133.3333 | 0.1 | 21 | 54 | 74 | 51.8333 | 58.3333 | 50 | 0 | 35
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 01:00 | 2017-08-20 01:00 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.8 | 91 | 132 | 152 | 128.5 | 0.4 | 33 | 58 | 72 | 56.1667 | 0 | 50 | 1 | 1.5
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.5 | 107 | 135 | 146 | 132.1667 | 0.2 | 39 | 55 | 75 | 55.6667 | 0 | 25 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Stable | 0.7 | 119 | 130 | 150 | 131.5 | 0.4 | 17 | 46 | 70 | 45.1667 | 0 | 40 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Worsening | [10 empty] | 0 | 37.5 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK84 | Project_010_RISK84 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality issues (for the future) | Person_359 | 2012-09-20 01:00 | 2017-08-20 01:00 | 0.6 | 2.033 | 1.2198 | Reduce | 0.25 | 0.92411 | 0.23103 | H2 | 4 | Stable | 0.6 | 119 | 133 | 153 | 134 | 0.3 | 36 | 40 | 79 | 45.8333 | 54.5455 | 58.3333 | 0 | 32.7273
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 0.3 | 1.8482 | 0.55447 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.6 | 95 | 138 | 148 | 132.5 | 0.3 | 35 | 49 | 75 | 51 | 0 | 33.3333 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 01:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.7 | 112 | 137 | 158 | 136.3333 | 0.2 | 36 | 47 | 72 | 49.3333 | 90 | 75 | 1 | 56.25
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | PRs per release cannot be absorbed within each WP and require a dedicated PR budget | Person_147 | 2013-08-21 01:00 | 2018-08-21 | 0.8 | 0.47334 | 0.37867 | Reduce | 0.8 | 0.47334 | 0.37867 | H1 | 5 | Stable | 0.7 | 86 | 139 | 145 | 131.1667 | 0.4 | 17 | 41 | 65 | 41 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-010 | Project_011_Risk-010 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Rework required following integration of Customer System | Person_140 | 2015-12-22 01:00 | 2016-08-19 01:00 | 0.5 | 1.3291 | 0.66455 | Reduce | 0.5 | 1.3291 | 0.66455 | H1 | 5 | Stable | 0.5 | 97 | 131 | 154 | 129.1667 | 0.2 | 36 | 49 | 62 | 49 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 0.4 | 0.68188 | 0.27275 | Reduce | 0.4 | 0.6137 | 0.24548 | H2 | 4 | Stable | 0.8 | 86 | 125 | 157 | 123.8333 | 0.2 | 9 | 57 | 77 | 52.3333 | 10 | 0 | 0 | 6
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK018 | Project_012_RISK018 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | No Additional material available due to attrition | Person_359 | 2015-04-04 | 2016-04-21 | 0.8 | 0.9915 | 0.7932 | Avoid | 0.7 | 0.84985 | 0.5949 | H2 | 4 | Stable | [10 empty] | 14.2857 | 12.5 | 0 | 8.5714
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK009 | Project_012_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Production Test equipment fails | Person_515 | 2015-04-04 | 2016-03-22 01:00 | 0.41 | 0.86402 | 0.35425 | Reduce | 0.25 | 0.14164 | 0.035411 | H2 | 4 | Stable | 0.5 | 106 | 123 | 143 | 123.5 | 0.3 | 39 | 45 | 75 | 49 | 83.6066 | 39.0244 | 0 | 50.1639
2016-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 0.3 | 8.7814 | 2.6344 | Reduce | 0.2 | 8.7832 | 1.7566 | H3 | 3 | Stable | 0.6 | 91 | 124 | 147 | 122.3333 | 0.2 | 28 | 51 | 63 | 49.1667 | -0.021119 | 33.3333 | 0 | -0.012672
2016-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 0.5 | 9.2728 | 4.6364 | Reduce | 0.3 | 9.2728 | 2.7819 | H2 | 4 | Stable | 0.8 | 99 | 128 | 156 | 127.8333 | 0.1 | 15 | 55 | 72 | 51.1667 | 0 | 40 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Obsolescence Monitoring Risk | Person_181 | 2016-12-03 01:00 | 2017-01-20 01:00 | 0.3 | 5.9458 | 1.7837 | Reduce | 0.15 | 0.9786 | 0.14679 | H3 | 3 | Stable | 0.7 | 93 | 133 | 158 | 130.5 | 0.1 | 11 | 43 | 78 | 43.5 | 83.5413 | 50 | 0 | 50.1248
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-21 01:00 | 2016-08-21 01:00 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.7 | 112 | 124 | 152 | 126.6667 | 0.1 | 7 | 43 | 65 | 40.6667 | 0 | 16.6667 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.8 | 106 | 122 | 151 | 124.1667 | 0.4 | 26 | 48 | 64 | 47 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 23:00 | 2019-08-20 23:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 23:00 | 2019-08-20 23:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 23:00 | 2019-08-20 23:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 23:00 | 2019-08-20 23:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 23:00 | 2019-08-20 23:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-21 23:00 | 2017-05-22 | 0.25 | 7.4225 | 1.8556 | Reduce | 0.1 | 3.7113 | 0.37113 | H3 | 3 | Stable | 0.5 | 115 | 132 | 152 | 132.5 | 0.1 | 10 | 41 | 69 | 40.5 | 50 | 60 | 0 | 30
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-18 23:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 2.6991 | 1.0796 | H2 | 4 | Stable | 0.5 | 87 | 129 | 141 | 124 | 0.1 | 20 | 54 | 75 | 51.8333 | 31.8182 | 20 | 0 | 19.0909
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk010 | Project_002_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability | Person_357 | 2014-06-14 | 2016-08-07 | 0.1 | 18.069 | 1.8069 | Accept | 0.1 | 18.069 | 1.8069 | H3 | 3 | Worsening | 0.9 | 84 | 123 | 148 | 120.6667 | 0.9 | 84 | 123 | 148 | 120.6667 | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_575 | 2015-05-24 | 2017-11-18 23:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 6.2979 | 0.94468 | H3 | 3 | Stable | 0.8 | 90 | 132 | 152 | 128.3333 | 0.1 | 13 | 59 | 72 | 53.5 | 0 | 70 | 1 | 2.1
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R012 | Project_021_Risk-R012 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Additional profiles required - in addition to those planned | Person_174 | 2016-02-06 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.5 | 83 | 138 | 159 | 132.3333 | 0.1 | 4 | 55 | 65 | 48.1667 |  | 60 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-13 | 2017-03-21 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.5 | 118 | 126 | 155 | 129.5 | 0.4 | 14 | 55 | 61 | 49.1667 | 80 | 66.6667 | 0 | 48
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk002 | Project_002_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Transducer Element Failures | Person_650 | 2014-06-04 | 2016-08-07 | 0.5 | 12.1398 | 8.4978 | Accept | 0.25 | 12.1398 | 8.4978 | H2 | 4 | Worsening | 0.8 | 88 | 128 | 149 | 124.8333 | 0.8 | 88 | 128 | 149 | 124.8333 | 0 | 50 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK004 | Project_021_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Delivery by Supplier late or requires correction that causes re-start of rig testing | Person_470 | 2016-02-13 | 2016-08-20 | 0.5 | 1.6113 | 0.80564 | Avoid | 0.5 | 1.6113 | 0.80564 | H1 | 5 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_470 | 2016-11-19 | 2017-11-19 | 0.4 | 0.48559 | 0.19424 | Reduce | 0.4 | 0.48559 | 0.19424 | H2 | 4 | Stable | 0.6 | 102 | 132 | 158 | 131.3333 | 0.1 | 31 | 43 | 73 | 46 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R026 | Project_021_Risk-R026 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Delay in readiness of System Equipment to commence Acceptance | Person_470 | 2016-02-28 | 2016-07-20 | 0.25 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H2 | 4 | Stable | 0.7 | 104 | 123 | 156 | 125.3333 | 0.2 | 5 | 52 | 73 | 47.6667 |  | 60 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_007 | R-072 | Project_007_R-072 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Software Issues | Person_245 | 2013-12-03 19:00 | 2016-03-23 | 0.5 | 0.33108 | 0.082771 | Accept | 0.5 | 0.33108 | 0.082771 | H2 | 4 | Stable | 0.5 | 84 | 137 | 153 | 130.8333 | 0.5 | 84 | 137 | 153 | 130.8333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Programme extension | Person_428 | 2009-06-23 | 2017-05-21 | 0.7 | 32.645 | 22.8515 | Reduce | 0.5 | 32.645 | 16.3225 | H1 | 5 | Stable | 0.5 | 120 | 131 | 148 | 132 | 0.1 | 4 | 57 | 74 | 51 | 0 | 28.5714 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Rejected concessions | Person_766 | 2016-02-11 | 2017-02-19 | 0.5 | 36.8056 | 18.4028 | Reduce | 0.15 | 33.5499 | 5.0325 | H2 | 4 | Worsening | 0.7 | 110 | 131 | 150 | 130.6667 | 0.3 | 22 | 44 | 66 | 44 | 8.8456 | 70 | 0 | 5.3073
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build ()/Decision Point concludes new release required | Person_428 | 2012-11-20 | 2017-05-21 | 0.1 | 165.5424 | 16.5542 | Reduce | 0.5 | 165.5424 | 82.7712 | H1 | 5 | Worsening | 0.5 | 100 | 139 | 152 | 134.6667 | 0.3 | 22 | 56 | 71 | 52.8333 | 0 | -400 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_470 | 2013-09-20 | 2017-01-20 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.5 | 12.6474 | 6.3237 | H1 | 5 | Stable | 0.5 | 98 | 136 | 144 | 131 | 0.3 | 11 | 57 | 63 | 50.3333 | 0 | 16.6667 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_470 | 2010-04-19 | 2017-01-19 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.6 | 113 | 122 | 155 | 126 | 0.3 | 27 | 44 | 60 | 43.8333 | 0 | 50 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safey Case Release is more complicated / delayed. | Person_470 | 2013-01-07 | 2017-02-19 | 0.5 | 4.7676 | 2.3838 | Reduce | 0.3 | 4.7676 | 1.4303 | H2 | 4 | Stable | 0.6 | 98 | 140 | 151 | 134.8333 | 0.1 | 26 | 40 | 77 | 43.8333 | 0 | 40 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_007 | R-078 | Project_007_R-078 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Environment Conditions | Person_356 | 2013-12-03 19:00 | 2016-03-21 19:00 | 0.2 | 1.9865 | 0.99325 | Accept | 0.2 | 1.9865 | 0.99325 | H3 | 3 | Stable | 0.6 | 83 | 129 | 156 | 125.8333 | 0.6 | 83 | 129 | 156 | 125.8333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_470 | 2013-01-07 | 2017-01-19 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.8 | 87 | 123 | 141 | 120 | 0.4 | 31 | 53 | 65 | 51.3333 | 0 | 33.3333 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 | 2017-06-21 | 0.7 | 10.8044 | 7.5631 | Reduce | 0.3 | 10.8044 | 3.2413 | H2 | 4 | Worsening | 0.6 | 118 | 130 | 159 | 132.8333 | 0.4 | 24 | 46 | 65 | 45.5 | 0 | 57.1429 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R013 | Project_021_Risk-R013 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials take longer to complete and delay the schedule | Person_470 | 2016-02-06 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.4 | 0 | 0 | H2 | 4 | Stable | 0.7 | 105 | 124 | 152 | 125.5 | 0.2 | 27 | 46 | 62 | 45.5 |  | 20 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 0.5 | 0.55886 | 0.27943 | Accept | 0.85 | 0.55886 | 0.11177 | H2 | 4 | Stable | 0.8 | 117 | 135 | 143 | 133.3333 | 0.8 | 117 | 135 | 143 | 133.3333 | 0 | -70 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-030 | Project_008_Risk-030 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Transition from old to new Standard causing additional unexpected work | Person_639 | 2013-09-20 01:00 | 2016-06-22 | 0.75 | 2.7943 | 0.55886 | Accept | 0.75 | 2.7943 | 0.55886 | H1 | 5 | Stable | 0.7 | 101 | 132 | 152 | 130.1667 | 0.7 | 101 | 132 | 152 | 130.1667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-09 | Project_022_RISK-09 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance - Issues arise | Person_393 | 2012-04-22 | 2016-09-19 01:00 | 0.7 | 24.8225 | 17.3758 | Reduce | 0.48 | 13.3846 | 6.4246 | H2 | 4 | Stable | 0.5 | 109 | 139 | 151 | 136 | 0.3 | 15 | 57 | 70 | 52.1667 | 46.0788 | 31.4286 | 0 | 27.6473
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-08 | Project_022_RISK-08 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Poor performance during acceptance phases | Person_248 | 2012-05-23 | 2016-09-19 01:00 | 0.65 | 5.6817 | 3.6931 | Reduce | 0.512 | 5.6817 | 2.909 | H1 | 5 | Stable | 0.7 | 89 | 137 | 149 | 131 | 0.2 | 15 | 45 | 79 | 45.6667 | 0 | 21.2308 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2016-09-19 01:00 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.347 | 2.9061 | 1.0084 | H2 | 4 | Worsening | 0.6 | 102 | 136 | 154 | 133.3333 | 0.4 | 11 | 47 | 63 | 43.6667 | 21.0126 | 56.625 | 0 | 12.6076
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation | Person_565 | 2018-05-22 | 2018-08-21 | 0.25 | 2.3975 | 2.3975 | Accept | 0.25 | 5.4295 | 5.4295 | H3 | 3 | Stable | 0.6 | 95 | 138 | 150 | 132.8333 | 0.6 | 95 | 138 | 150 | 132.8333 | -126.4653 | 0 | 0 | -75.8792
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-22 | Project_022_RISK-22 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Setting to work Issues - monitor may require changing | Person_393 | 2014-10-22 01:00 | 2016-09-19 01:00 | 0.6 | 11.6428 | 6.9857 | Reduce | 0.2 | 19.5167 | 3.9033 | H3 | 3 | Worsening | 0.8 | 109 | 135 | 150 | 133.1667 | 0.4 | 25 | 45 | 71 | 46 | -67.628 | 66.6667 | 0 | -40.5768
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-30 | Project_022_RISK-30 | Opportunitity | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Setting to work and acceptance issues | Person_703 | 2012-04-19 | 2016-08-20 01:00 | 0.8 | 8.6133 | 6.8907 | Exploit | 0.8 | 2.6904 | 2.1524 | H2 | 4 | Stable | [10 empty] | 68.7641 | 0 | 0 | 41.2585
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2016-08-20 01:00 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 3.3531 | 2.6825 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-074 | Project_008_Risk-074 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Re-design/Beyond Economic Repair costs | Person_565 | 2016-05-23 | 2016-11-19 01:00 | 1 | 5.4459 | 1.6338 | Accept | 1 | 0.18151 | 0.054453 | H1 | 5 | Stable | 0.7 | 118 | 126 | 151 | 128.8333 | 0.7 | 118 | 126 | 151 | 128.8333 | 96.667 | 0 | 0 | 58.0002
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2016-11-17 01:00 | 0.85 | 25.2325 | 21.4476 | Avoid | 0.08 | 20.8758 | 1.6701 | H2 | 4 | Improving | [10 empty] | 17.2662 | 90.5882 | 0 | 10.3597
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2016-11-17 01:00 | 0.7 | 24.1887 | 16.9321 | Reduce | 0.25 | 4.3567 | 1.0892 | H2 | 4 | Stable | 0.6 | 102 | 133 | 145 | 129.8333 | 0.1 | 32 | 55 | 74 | 54.3333 | 81.9887 | 64.2857 | 0 | 49.1932
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.05 | 5.9904 | 1.4976 | Accept | 0.05 | 0 | 0 | H2 | 4 | Stable | 0.6 | 103 | 131 | 149 | 129.3333 | 0.6 | 103 | 131 | 149 | 129.3333 | 100 | 0 | 0 | 60
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 0.8 | 30.7697 | 12.3079 | Accept | 0.6 | 30.7697 | 12.3079 | H1 | 5 | Stable | 0.6 | 114 | 138 | 146 | 135.3333 | 0.6 | 114 | 138 | 146 | 135.3333 | 0 | 25 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP068 | Project_024_OPP068 | Opportunitity | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Customer acceptance of iterative sell-off approach | Person_535 | 2016-07-21 | 2017-11-19 01:00 | 0.2 | 9.3045 | 1.8609 | -- | 0.3 | 9.3045 | 2.7913 | H2 | 4 | Stable | [10 empty] | 0 | -50 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 01:00 | 2016-08-20 01:00 | 0.1 | 14.541 | 5.8164 | Accept | 0.1 | 14.541 | 5.8164 | H2 | 4 | Stable | 0.5 | 101 | 130 | 145 | 127.6667 | 0.5 | 101 | 130 | 145 | 127.6667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK166 | Project_024_RISK166 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Requirements Acceptance Criteria | Person_288 | 2016-04-10 | 2017-03-06 01:00 | 0.4 | 3.843 | 1.5372 | Reduce | 0.2 | 1.2464 | 0.24927 | H2 | 4 | Improving | 0.7 | 97 | 139 | 154 | 134.5 | 0.4 | 2 | 56 | 68 | 49 | 67.5676 | 50 | 0 | 40.5405
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 0.2 | 1.3502 | 0.33756 | Accept | 0.2 | 1.3502 | 0.33756 | H3 | 3 | Improving | 0.9 | 90 | 135 | 149 | 129.8333 | 0.9 | 90 | 135 | 149 | 129.8333 | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK196 | Project_024_RISK196 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional Trials - Cost of Labour | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.3 | 0.95209 | 0.28563 | Reduce | 0.2 | 0.95209 | 0.19042 | H2 | 4 | Worsening | 0.5 | 96 | 139 | 153 | 134.1667 | 0.3 | 2 | 42 | 66 | 39.3333 | 0 | 33.3333 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK244 | Project_024_RISK244 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Blue Screen Of Death (BSOD) | Person_534 | 2016-04-22 | 2016-07-21 | 0.1 | 15.1468 | 1.5147 | Reduce | 0.1 | 15.1468 | 1.5147 | H3 | 3 | Stable | 0.7 | 113 | 121 | 142 | 123.1667 | 0.4 | 2 | 54 | 78 | 49.3333 | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK002 | Project_024_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | S/W Productivity | Person_331 | 2016-05-22 | 2016-11-19 01:00 | 0.43 | 90.8811 | 39.0789 | Reduce | 0.43 | 90.8811 | 39.0789 | H1 | 5 | Stable | 0.6 | 84 | 140 | 154 | 133 | 0.2 | 29 | 55 | 72 | 53.5 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK008 | Project_012_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Critical Resource leave the project | Person_359 | 2015-04-04 | 2016-03-22 01:00 | 0.25 | 19.9938 | 5.9981 | Accept | 0.25 | 19.9938 | 5.9981 | H2 | 4 | Stable | 0.7 | 85 | 133 | 144 | 126.8333 | 0.7 | 85 | 133 | 144 | 126.8333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK007 | Project_012_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Materials failure/shortages | Person_515 | 2015-04-04 | 2016-04-12 | 0.61 | 11.1654 | 2.2331 | Accept | 0.35 | 11.1654 | 2.2331 | H2 | 4 | Worsening | 0.9 | 102 | 128 | 148 | 127 | 0.9 | 102 | 128 | 148 | 127 | 0 | 42.623 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK023 | Project_012_RISK023 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional tests for final units | Person_359 | 2015-09-21 01:00 | 2016-04-12 | 0.8 | 9.2439 | 3.6976 | Accept | 0.4 | 9.2439 | 3.6976 | H3 | 3 | Stable | 0.5 | 99 | 131 | 146 | 128.1667 | 0.5 | 99 | 131 | 146 | 128.1667 | 0 | 50 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials - Increased Cost | Person_073 | 2016-05-23 | 2017-02-19 01:00 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.5 | 102 | 138 | 154 | 134.6667 | 0.1 | 32 | 59 | 66 | 55.6667 | 0 | 50 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | People unable to sustain the pace | Person_413 | 2015-11-21 01:00 | 2017-05-22 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.5 | 89 | 133 | 146 | 127.8333 | 0.4 | 5 | 51 | 66 | 45.8333 | 0 | 5 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Material/Labour Overspend | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 1.3502 | 0.27005 | Accept | 0.5 | 1.3502 | 0.27005 | H2 | 4 | Stable | 0.9 | 98 | 130 | 156 | 129 | 0.9 | 98 | 130 | 156 | 129 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 0.5 | 1.1685 | 0.23369 | Accept | 0.5 | 1.1685 | 0.23369 | H2 | 4 | Stable | 0.7 | 88 | 126 | 141 | 122.1667 | 0.7 | 88 | 126 | 141 | 122.1667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 0.5 | 1.3502 | 0.40507 | Accept | 0.5 | 1.3502 | 0.40507 | H2 | 4 | Stable | 0.6 | 99 | 137 | 142 | 131.5 | 0.6 | 99 | 137 | 142 | 131.5 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK153 | Project_024_RISK153 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Processor memory/performance Issue | Person_331 | 2016-06-23 | 2017-03-22 | 0.3 | 112.3463 | 33.7039 | Reduce | 0.2 | 112.3463 | 22.4693 | H2 | 4 | Stable | 0.7 | 82 | 138 | 149 | 130.5 | 0.1 | 15 | 50 | 77 | 48.6667 | 0 | 33.3333 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK155 | Project_024_RISK155 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Late availability of Parameters | Person_534 | 2016-03-23 | 2016-09-11 01:00 | 0.3 | 4.1113 | 1.2334 | Reduce | 0.3 | 4.1113 | 1.2334 | H1 | 5 | Stable | 0.8 | 86 | 121 | 142 | 118.6667 | 0.3 | 15 | 42 | 64 | 41.1667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 0.3 | 5.4096 | 0.54096 | Accept | 0.3 | 5.4096 | 0.54096 | H2 | 4 | Stable | 0.7 | 119 | 121 | 153 | 126 | 0.7 | 119 | 121 | 153 | 126 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Delay of processing | Person_306 | 2016-01-13 01:00 | 2019-08-21 01:00 | 0.15 | 25.966 | 7.7898 | Accept | 0.15 | 25.966 | 7.7898 | H3 | 3 | Stable | 0.5 | 96 | 128 | 142 | 125 | 0.5 | 96 | 128 | 142 | 125 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.35 | 62.3617 | 3.1181 | Accept | 0.35 | 62.3617 | 3.1181 | H3 | 3 | Stable | 0.9 | 107 | 140 | 160 | 137.8333 | 0.9 | 107 | 140 | 160 | 137.8333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.25 | 0.67512 | 0.13502 | Accept | 0.25 | 0.67512 | 0.13502 | H3 | 3 | Stable | 0.7 | 104 | 121 | 155 | 123.8333 | 0.7 | 104 | 121 | 155 | 123.8333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK201 | Project_024_RISK201 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Indication mode failure | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.25 | 1.6835 | 0.42087 | Reduce | 0.2 | 1.6835 | 0.33669 | H3 | 3 | Stable | 0.6 | 86 | 131 | 152 | 127 | 0.1 | 12 | 55 | 63 | 49.1667 | 0 | 20 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-21 01:00 | 2019-08-20 | 0.5 | 1.3502 | 0.54009 | Accept | 0.5 | 1.3502 | 0.54009 | H2 | 4 | Stable | 0.9 | 100 | 127 | 149 | 126.1667 | 0.9 | 100 | 127 | 149 | 126.1667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.2 | 1.9128 | 0.19128 | Accept | 0.2 | 1.9128 | 0.19128 | H3 | 3 | Stable | 0.9 | 105 | 126 | 154 | 127.1667 | 0.9 | 105 | 126 | 154 | 127.1667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK213 | Project_024_RISK213 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Rigs requireaccreditation as "Special to Type" Test equipment | Person_351 | 2016-05-23 | 2017-05-22 | 0.3 | 33.7558 | 10.1267 | Reduce | 0.2 | 23.3694 | 4.6739 | H2 | 4 | Stable | 0.8 | 116 | 135 | 155 | 135.1667 | 0.3 | 7 | 43 | 78 | 42.8333 | 30.7692 | 33.3333 | 0 | 18.4615
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK179 | Project_024_RISK179 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Testing Required | Person_289 | 2016-12-21 01:00 | 2017-05-22 | 0.5 | 3.5054 | 1.7527 | Reduce | 0.4 | 3.5054 | 1.4022 | H2 | 4 | Stable | 0.5 | 119 | 122 | 149 | 126 | 0.1 | 28 | 41 | 72 | 44 | 0 | 20 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK211 | Project_024_RISK211 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Customer drives scope change | Person_351 | 2017-01-21 01:00 | 2017-06-22 | 0.3 | 1.7657 | 0.52971 | Reduce | 0.2 | 1.7657 | 0.35314 | H3 | 3 | Stable | 0.9 | 81 | 123 | 148 | 120.1667 | 0.3 | 8 | 43 | 60 | 40 | 0 | 33.3333 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK218 | Project_024_RISK218 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | System issues general | Person_289 | 2016-08-21 01:00 | 2016-10-04 01:00 | 0.4 | 90.8811 | 36.3524 | Reduce | 0.3 | 90.8811 | 27.2643 | H1 | 5 | Stable | 0.8 | 95 | 121 | 147 | 121 | 0.2 | 7 | 52 | 67 | 47 | 0 | 25 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK180 | Project_024_RISK180 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | High Accelerated Life Testing (HALT) | Person_585 | 2016-12-21 01:00 | 2017-05-03 | 0.4 | 10.4903 | 4.1961 | Reduce | 0.2 | 10.4903 | 2.0981 | H2 | 4 | Stable | 0.8 | 101 | 125 | 159 | 126.6667 | 0.3 | 19 | 58 | 67 | 53 | 0 | 50 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R017 | Project_021_Risk-R017 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Effort to address Hexavalent Chromium issue is unknown at time of baseline | Person_470 | 2016-02-06 | 2016-11-19 | 0.7 | 35.885 | 14.354 | Accept | 0.7 | 35.885 | 14.354 | H1 | 5 | Stable | 0.9 | 118 | 125 | 143 | 126.8333 | 0.9 | 118 | 125 | 143 | 126.8333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R025 | Project_021_Risk-R025 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Analysis of Trials data may require further info or action to complete | Person_470 | 2016-02-18 | 2017-06-22 | 0.25 | 68.1262 | 6.8126 | Accept | 0.25 | 68.1262 | 6.8126 | H2 | 4 | Stable | 0.8 | 99 | 125 | 151 | 125 | 0.8 | 99 | 125 | 151 | 125 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R002 | Project_021_Risk-R002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Rig Unreliability | Person_470 | 2013-01-07 | 2016-07-20 | 0.5 | 90.8811 | 13.6322 | Accept | 0.5 | 90.8811 | 13.6322 | H1 | 5 | Stable | 0.8 | 113 | 127 | 144 | 127.5 | 0.8 | 113 | 127 | 144 | 127.5 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-47 | Project_022_RISK-47 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Software Issues | Person_245 | 2012-04-19 | 2016-09-19 01:00 | 0.5 | 0 | 0 | Accept | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.6 | 80 | 128 | 151 | 123.8333 | 0.6 | 80 | 128 | 151 | 123.8333 |  | 60 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-51 | Project_022_RISK-51 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Environment Conditions | Person_393 | 2012-04-19 | 2016-09-19 01:00 | 0.2 | 0 | 0 | Accept | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.8 | 120 | 135 | 154 | 135.6667 | 0.8 | 120 | 135 | 154 | 135.6667 |  | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 20:00 | 2019-08-20 20:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.6 | 116 | 136 | 151 | 135.1667 | 0.1 | 15 | 43 | 73 | 43.3333 | 83.3333 | 88.8889 | 1 | 52.6667
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 20:00 | 2019-08-20 20:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.9 | 88 | 124 | 144 | 121.3333 | 0.4 | 5 | 54 | 68 | 48.1667 | 72 | 0 | 0 | 43.2
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 20:00 | 2019-08-20 20:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.8 | 99 | 125 | 148 | 124.5 | 0.2 | 7 | 48 | 65 | 44 | 47.7391 | 0 | 0 | 28.6435
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 20:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.6 | 85 | 129 | 142 | 123.8333 | 0.3 | 17 | 48 | 77 | 47.6667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.7 | 94 | 123 | 150 | 122.6667 | 0.1 | 12 | 49 | 71 | 46.5 | 0 | 25 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-016 | Project_023_Risk-016 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Damage to equipment (Unable to replace due to obsolescence) | Person_703 | 2015-10-22 01:00 | 2016-06-22 | 0.3 | 6.7866 | 6.7866 | Accept | 0.3 | 6.7866 | 6.7866 | H2 | 4 | Stable | 0.5 | 103 | 127 | 154 | 127.5 | 0.5 | 103 | 127 | 154 | 127.5 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-007 | Project_026_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Additional requests for information and attendance at meetings | Person_264 | 2014-11-21 01:00 | 2018-12-27 01:00 | 0.5 | 10.5249 | 5.2625 | Reduce | 0.5 | 10.5249 | 5.2625 | H2 | 4 | Worsening | 0.9 | 97 | 128 | 153 | 127 | 0.4 | 14 | 53 | 65 | 48.5 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2016-12-08 01:00 | 0.41 | 3.4415 | 1.3766 | Accept | 0.41 | 3.4415 | 1.3766 | H2 | 4 | Stable | 0.6 | 82 | 122 | 149 | 119.8333 | 0.6 | 82 | 122 | 149 | 119.8333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-015 | Project_023_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Illness | Person_371 | 2015-04-09 | 2016-12-11 01:00 | 0.25 | 8.0582 | 2.4175 | Accept | 0.25 | 8.0582 | 2.4175 | H2 | 4 | Stable | 0.5 | 117 | 133 | 159 | 134.6667 | 0.5 | 117 | 133 | 159 | 134.6667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-035 | Project_026_Risk-035 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Interfacing between system elements more complex than anticipated | Person_385 | 2017-05-23 | 2018-08-04 | 0.5 | 16.1164 | 8.0582 | Reduce | 0.3 | 16.1164 | 4.8349 | H2 | 4 | Worsening | 0.5 | 96 | 139 | 146 | 133 | 0.2 | 32 | 47 | 79 | 49.8333 | 0 | 40 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK189 | Project_024_RISK189 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment integration - Audio and Video recording | Person_585 | 2016-08-20 01:00 | 2017-01-21 01:00 | 0.4 | 0.5596 | 0.05596 | Accept | 0.4 | 0.5596 | 0.05596 | H1 | 5 | Worsening | 0.7 | 111 | 137 | 147 | 134.3333 | 0.7 | 111 | 137 | 147 | 134.3333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_289 | 2016-05-23 | 2016-12-20 01:00 | 0.4 | 3.6174 | 1.8087 | Accept | 0.4 | 3.6172 | 1.8086 | H1 | 5 | Stable | 0.7 | 103 | 131 | 158 | 130.8333 | 0.7 | 103 | 131 | 158 | 130.8333 | 0.0051359 | 0 | 0 | 0.0030815
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK194 | Project_024_RISK194 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Performance Models require additional effort | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.25 | 2.3503 | 0.47006 | Accept | 0.25 | 2.3503 | 0.47006 | H2 | 4 | Stable | 0.9 | 98 | 138 | 141 | 131.8333 | 0.9 | 98 | 138 | 141 | 131.8333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK195 | Project_024_RISK195 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Perfomance Validation document not accepted | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.1 | 4.4768 | 2.2384 | Accept | 0.1 | 4.4768 | 2.2384 | H2 | 4 | Stable | 0.7 | 101 | 134 | 151 | 131.3333 | 0.7 | 101 | 134 | 151 | 131.3333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-019 | Project_026_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Customer interaction and reporting may be much greater than anticipated | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 0.3 | 16.3694 | 4.9108 | Reduce | 0.2 | 16.3683 | 3.2737 | H3 | 3 | Worsening | 0.6 | 93 | 140 | 141 | 132.3333 | 0.4 | 20 | 56 | 70 | 52.3333 | 0.0068371 | 33.3333 | 0 | 0.0041023
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-200 | Project_027_Risk-200 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Sucession Planning for key team members | Person_060 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.2 | 7.3175 | 1.4635 | Reduce | 0.05 | 7.3175 | 0.36588 | H2 | 4 | Stable | 0.7 | 119 | 133 | 154 | 134.1667 | 0.1 | 16 | 43 | 61 | 41.5 | 0 | 75 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-189 | Project_027_Risk-189 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Major Component obsolescence | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 8.3972 | 2.5191 | Reduce | 0.25 | 8.3972 | 2.0993 | H2 | 4 | Stable | 0.8 | 109 | 135 | 160 | 134.8333 | 0.1 | 30 | 58 | 72 | 55.6667 | 0 | 16.6667 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-201 | Project_027_Risk-201 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Transition into Support | Person_027 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0.5 | 68.3768 | 34.1884 | Reduce | 0.05 | 38.387 | 1.9193 | H2 | 4 | Stable | 0.7 | 93 | 136 | 156 | 132.1667 | 0.1 | 2 | 59 | 75 | 52.1667 | 43.8597 | 90 | 0 | 26.3158
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 0.3 | 20.0332 | 2.0033 | Accept | 0.3 | 20.0332 | 2.0033 | H1 | 5 | Improving | 0.8 | 87 | 133 | 154 | 128.8333 | 0.8 | 87 | 133 | 154 | 128.8333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-193 | Project_027_Risk-193 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | A greater number of arising technical queries | Person_110 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 13.7953 | 4.1386 | Reduce | 0.05 | 13.7953 | 0.68977 | H3 | 3 | Stable | 0.7 | 111 | 126 | 151 | 127.6667 | 0.2 | 2 | 55 | 66 | 48 | 0 | 83.3333 | 1 | 2.5
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_119 | 2016-10-21 01:00 | 2017-11-19 01:00 | 0.3 | 16.1945 | 2.4292 | Accept | 0.3 | 16.1945 | 2.4292 | H1 | 5 | Improving | 0.5 | 118 | 134 | 156 | 135 | 0.5 | 118 | 134 | 156 | 135 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK237 | Project_024_RISK237 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer coding standard Compliance | Person_534 | 2017-05-25 | 2017-10-27 01:00 | 0.2 | 35.9878 | 21.5927 | Accept | 0.2 | 15.5947 | 0.77974 | H2 | 4 | Stable | 0.7 | 95 | 134 | 147 | 129.6667 | 0.7 | 95 | 134 | 147 | 129.6667 | 56.6667 | 0 | 0 | 34
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK159 | Project_024_RISK159 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Extension of planned safety team work | Person_119 | 2016-10-21 01:00 | 2017-11-19 01:00 | 0.4 | 27.5907 | 2.7591 | Accept | 0.4 | 27.5907 | 2.7591 | H1 | 5 | Worsening | 0.7 | 117 | 136 | 159 | 136.6667 | 0.7 | 117 | 136 | 159 | 136.6667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK198 | Project_024_RISK198 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Spot Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 0.2 | 19.1935 | 2.879 | Accept | 0.2 | 19.1935 | 2.879 | H3 | 3 | Stable | 0.6 | 88 | 132 | 158 | 129 | 0.6 | 88 | 132 | 158 | 129 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK197 | Project_024_RISK197 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Fitness for purpose | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.2 | 8.3972 | 0.83972 | Accept | 0.2 | 8.3972 | 0.41986 | H2 | 4 | Stable | 0.7 | 91 | 123 | 141 | 120.6667 | 0.7 | 91 | 123 | 141 | 120.6667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK199 | Project_024_RISK199 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Strip Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 0.3 | 19.1935 | 1.9194 | Accept | 0.3 | 19.1935 | 1.9194 | H2 | 4 | Stable | 0.5 | 93 | 130 | 154 | 127.8333 | 0.5 | 93 | 130 | 154 | 127.8333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK152 | Project_024_RISK152 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Component Damage | Person_674 | 2016-04-06 | 2016-07-21 | 0.1 | 0.81199 | 0.081199 | Accept | 0.1 | 0.81199 | 0.0406 | H3 | 3 | Stable | 0.9 | 95 | 128 | 155 | 127 | 0.9 | 95 | 128 | 155 | 127 | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-022 | Project_028_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Accrediation Scope | Person_371 | 2014-01-21 | 2016-09-19 | 0.5 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 20 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment environmental failure | Person_585 | 2016-05-23 | 2016-12-02 01:00 | 0.3 | 12.1982 | 0.60991 | Accept | 0.3 | 12.1982 | 0.60991 | H1 | 5 | Improving | 0.9 | 109 | 128 | 155 | 129.3333 | 0.9 | 109 | 128 | 155 | 129.3333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Retained systems re-design or modification | Person_585 | 2016-08-20 01:00 | 2016-12-02 01:00 | 0.05 | 0 | 0 | Accept | 0.05 | 0 | 0 | H2 | 4 | Improving | 0.8 | 90 | 135 | 153 | 130.5 | 0.8 | 90 | 135 | 153 | 130.5 |  | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Mission System not compatible with platform systems | Person_585 | 2016-07-21 | 2017-02-19 01:00 | 0.1 | 0 | 0 | Accept | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.9 | 107 | 123 | 142 | 123.5 | 0.9 | 107 | 123 | 142 | 123.5 |  | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK202 | Project_024_RISK202 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Mode Specific | Person_448 | 2016-07-20 | 2017-02-19 01:00 | 0.2 | 4.4003 | 0.66004 | Accept | 0.2 | 4.4003 | 0.44003 | H3 | 3 | Stable | 0.7 | 82 | 139 | 154 | 132 | 0.7 | 82 | 139 | 154 | 132 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK204 | Project_024_RISK204 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Stabilisation | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.4 | 0 | 0 | Accept | 0.4 | 0 | 0 | H1 | 5 | Worsening | 0.7 | 81 | 136 | 156 | 130.1667 | 0.7 | 81 | 136 | 156 | 130.1667 |  | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK203 | Project_024_RISK203 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Detection/Tracking modifications | Person_448 | 2016-10-21 01:00 | 2017-02-19 01:00 | 0.1 | 2.2788 | 0.68363 | Accept | 0.1 | 2.2788 | 0.68363 | H3 | 3 | Stable | 0.6 | 81 | 133 | 160 | 128.8333 | 0.6 | 81 | 133 | 160 | 128.8333 | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK200 | Project_024_RISK200 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Height Finding | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.35 | 0.44449 | 0.088898 | Accept | 0.35 | 0.44449 | 0.044449 | H2 | 4 | Worsening | 0.6 | 92 | 121 | 158 | 122.3333 | 0.6 | 92 | 121 | 158 | 122.3333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-032 | Project_028_Risk-032 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software Development | Delays to Software Validation & Development | Person_542 | 2015-04-08 | 2016-09-18 21:00 | 0.5 | 0.52384 | 0.26192 | Reduce | 0.1 | 0.52384 | 0.052384 | H3 | 3 | Stable | 0.6 | 97 | 126 | 147 | 124.6667 | 0.1 | 12 | 42 | 66 | 41 | 0 | 80 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK209 | Project_024_RISK209 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Major Return to Service | Person_073 | 2016-11-20 01:00 | 2017-05-22 | 0.3 | 0.52384 | 0.26192 | Accept | 0.3 | 0.52384 | 0.26192 | H1 | 5 | Stable | 0.8 | 113 | 122 | 150 | 125.1667 | 0.8 | 113 | 122 | 150 | 125.1667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2016-11-19 | 0.2 | 0.90951 | 0.1819 | Reduce | 0.2 | 0.90951 | 0.1819 | H3 | 3 | Stable | 0.7 | 101 | 138 | 141 | 132.3333 | 0.3 | 12 | 49 | 67 | 45.8333 | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK206 | Project_024_RISK206 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Simulator Updates | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.1 | 0.681 | 0.2724 | Accept | 0.1 | 0.681 | 0.1362 | H3 | 3 | Stable | 0.6 | 89 | 137 | 147 | 130.6667 | 0.6 | 89 | 137 | 147 | 130.6667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Overland performance | Person_448 | 2016-06-23 | 2017-05-21 | 0.25 | 1.4532 | 0.072661 | Accept | 0.25 | 1.4532 | 0.072661 | H2 | 4 | Stable | 0.7 | 119 | 123 | 159 | 128.3333 | 0.7 | 119 | 123 | 159 | 128.3333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Qual failure | Person_585 | 2016-06-22 | 2016-11-20 01:00 | 0.4 | 11.0007 | 0.55004 | Accept | 0.4 | 11.0007 | 0.55004 | H1 | 5 | Improving | 0.7 | 117 | 135 | 155 | 135.3333 | 0.7 | 117 | 135 | 155 | 135.3333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2016-07-20 | 0.3 | 5.4553 | 1.6366 | Reduce | 0.2 | 5.252 | 1.0504 | H2 | 4 | Stable | 0.5 | 118 | 122 | 160 | 127.6667 | 0.1 | 12 | 48 | 75 | 46.5 | 3.7267 | 33.3333 | 0 | 2.236
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK210 | Project_024_RISK210 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Performance | Person_532 | 2016-06-22 | 2016-08-19 01:00 | 0.3 | 1.2572 | 0.37717 | Accept | 0.3 | 1.2572 | 0.37717 | H2 | 4 | Stable | 0.9 | 92 | 130 | 156 | 128 | 0.9 | 92 | 130 | 156 | 128 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-058 | Project_028_Risk-058 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | INterface Card | Person_253 | 2015-07-22 | 2016-08-20 | 0.2 | 2.8408 | 0.56817 | Reduce | 0.1 | 1.9314 | 0.19314 | H3 | 3 | Stable | 0.9 | 106 | 121 | 146 | 122.6667 | 0.4 | 28 | 49 | 61 | 47.5 | 32.0134 | 50 | 1 | 20.708
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Additional minor releases | Person_073 | 2016-05-23 | 2017-08-20 01:00 | 0.5 | 1.3215 | 0.39644 | Accept | 0.5 | 1.3215 | 0.39644 | H1 | 5 | Stable | 0.5 | 109 | 137 | 160 | 136.1667 | 0.5 | 109 | 137 | 160 | 136.1667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Digital Video Chainredesign | Person_289 | 2016-06-22 | 2016-12-17 01:00 | 0.4 | 12.1982 | 2.4396 | Accept | 0.4 | 10.8428 | 2.1686 | H1 | 5 | Worsening | 0.8 | 98 | 124 | 157 | 125.1667 | 0.8 | 98 | 124 | 157 | 125.1667 | 11.1111 | 0 | 0 | 6.6667
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK253 | Project_024_RISK253 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Insufficient parts to complete framework Warranty | Person_289 | 2016-05-23 | 2017-04-21 | 0.1 | 4.4727 | 0.44727 | Accept | 0.1 | 4.4727 | 0.22363 | H2 | 4 | Improving | 0.5 | 88 | 128 | 148 | 124.6667 | 0.5 | 88 | 128 | 148 | 124.6667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Cable and connectors | Person_050 | 2015-11-21 | 2017-08-09 | 0.45 | 0.41338 | 0.18602 | Reduce | 0.2 | 0.41338 | 0.082677 | H2 | 4 | Stable | 0.5 | 113 | 127 | 141 | 127 | 0.1 | 5 | 49 | 65 | 44.3333 | 0 | 55.5556 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Platform Acceptance | Person_500 | 2015-11-21 | 2017-01-20 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.2 | 4.2355 | 0.8471 | H3 | 3 | Stable | 0.6 | 117 | 121 | 155 | 126 | 0.2 | 2 | 40 | 60 | 37 | 0 | 42.8571 | 1 | 1.2857
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-001 | Project_028_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Porting software | Person_542 | 2014-03-23 | 2016-12-20 | 0.5 | 8.8098 | 4.4049 | Reduce | 0.08 | 7.4545 | 0.59636 | H2 | 4 | Stable | 0.6 | 110 | 140 | 154 | 137.3333 | 0.3 | 26 | 46 | 71 | 46.8333 | 15.3846 | 84 | 0 | 9.2308
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 20:00 | 2019-08-07 | 0.61 | 8.8098 | 3.0834 | Accept | 0.61 | 8.8098 | 1.762 | H1 | 5 | Stable | 0.5 | 102 | 137 | 158 | 134.6667 | 0.5 | 102 | 137 | 158 | 134.6667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Furnished Equipmnet Condition | Person_371 | 2015-04-27 | 2017-08-19 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.5 | 89 | 123 | 151 | 122 | 0.2 | 15 | 45 | 76 | 45.1667 |  | 62.5 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.41 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -2.5 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2016-07-20 | 0.61 | 0.25667 | 0.15657 | Reduce | 0.5 | 0.25667 | 0.12834 | H2 | 4 | Stable | 0.6 | 90 | 126 | 149 | 123.8333 | 0.3 | 8 | 44 | 71 | 42.5 | 0 | 18.0328 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2014-01-21 01:00 | 2017-11-20 01:00 | 0.4 | 1.078 | 0.43121 | Reduce | 0.2 | 1.078 | 0.2156 | H3 | 3 | Stable | 0.8 | 82 | 123 | 154 | 121.3333 | 0.1 | 39 | 58 | 77 | 58 | 0 | 50 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-118 | Project_029_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Acceptance Schedule is longer in duration/delayed | Person_102 | 2015-12-22 01:00 | 2016-08-21 01:00 | 0.55 | 0.56468 | 0.31057 | Reduce | 0.55 | 0.56468 | 0.31057 | H2 | 4 | Stable | 0.5 | 113 | 121 | 157 | 125.6667 | 0.3 | 25 | 43 | 69 | 44.3333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-038 | Project_029_Risk-038 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Integration and Reliability | Person_216 | 2014-03-23 | 2016-11-19 01:00 | 0.15 | 1.155 | 0.17325 | Reduce | 0.15 | 0.77001 | 0.1155 | H3 | 3 | Stable | 0.9 | 104 | 129 | 143 | 127.1667 | 0.4 | 7 | 48 | 66 | 44.1667 | 33.3333 | 0 | 1 | 20
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2017-11-19 01:00 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-113 | Project_029_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | SW Delivery to INtegration (including bug fixes post delivery) | Person_199 | 2014-07-22 | 2016-09-19 01:00 | 0.4 | 0.64168 | 0.25667 | Avoid | 0.4 | 0.64168 | 0.25667 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2016-06-21 | 0.6 | 0.89835 | 0.53901 | Transfer | 0.6 | 0.89835 | 0.53901 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2015-07-31 | 2017-05-15 | 0.35 | 0.85557 | 0.29945 | Reduce | 0.35 | 0.92402 | 0.32341 | H2 | 4 | Stable | 0.8 | 103 | 136 | 157 | 134 | 0.1 | 37 | 49 | 62 | 49.1667 | -8.0001 | 0 | 0 | -4.8001
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-106 | Project_029_Risk-106 | Opportunitity | Project Contingency | Open | H2 | 4 | 8. System Engineering | Opportunity to recover 50% of design effort | Person_438 | 2015-03-24 | 2017-05-08 | 0.8 | 1.0267 | 0.82135 | Exploit | 0.8 | 1.0267 | 0.82135 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-105 | Project_029_Risk-105 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Changes to CE markings | Person_692 | 2015-05-24 | 2020-11-19 01:00 | 0.8 | 0.51334 | 0.41067 | Reduce | 0.3 | 0.51334 | 0.154 | H3 | 3 | Stable | 0.8 | 98 | 128 | 147 | 126.1667 | 0.1 | 17 | 57 | 60 | 50.8333 | 0 | 62.5 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-028 | Project_029_Risk-028 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Assets (for system integration - repair of test assets) | Person_102 | 2015-02-21 01:00 | 2020-05-22 | 0.4 | 1.2834 | 0.51334 | Reduce | 0.2 | 1.2834 | 0.25667 | H3 | 3 | Stable | 0.7 | 98 | 140 | 155 | 135.5 | 0.1 | 36 | 53 | 67 | 52.5 | 0 | 50 | 1 | 1.5
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2016-05-23 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.9 | 91 | 136 | 160 | 132.5 | 0.3 | 15 | 42 | 73 | 42.6667 | 0 | 28.5714 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-104 | Project_029_Risk-104 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Assumed Synergies between Plan and Prospect | Person_692 | 2014-10-22 01:00 | 2021-05-22 | 0 | 0 | 0 | Reduce | 0 | 0 | 0 | H2 | 4 | Improving | 0.5 | 113 | 123 | 152 | 126.1667 | 0.2 | 10 | 49 | 67 | 45.5 |  |  | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2014-07-22 | 2017-11-19 01:00 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.8 | 118 | 137 | 152 | 136.3333 | 0.2 | 34 | 54 | 64 | 52.3333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2017-10-14 01:00 | 0.41 | 6.4168 | 2.6309 | Transfer | 0.41 | 0 | 0 | H1 | 5 | Stable | [10 empty] | 100 | 0 | 0 | 60
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-004 | Project_029_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Functionality shortfalls of sub-system Application Software Integration with the system | Person_199 | 2015-11-21 01:00 | 2016-09-19 01:00 | 0.2 | 0.53901 | 0.1078 | Reduce | 0.15 | 0.53901 | 0.080852 | H3 | 3 | Stable | 0.9 | 112 | 123 | 160 | 127.3333 | 0.4 | 29 | 52 | 79 | 52.6667 | 0 | 25 | 1 | 0.75
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 01:00 | 2016-05-21 | 0.5 | 4.3921 | 2.196 | Reduce | 0.3 | 4.3921 | 1.3176 | H1 | 5 | Stable | 0.8 | 89 | 134 | 151 | 129.3333 | 0.1 | 9 | 44 | 67 | 42 | 0 | 40 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.25 | 7.7469 | 1.9367 | Reduce | 0.25 | 7.7469 | 1.9367 | H3 | 3 | Stable | 0.8 | 113 | 126 | 153 | 128.3333 | 0.4 | 1 | 42 | 65 | 39 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-131 | Project_032_Risk-131 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 0.3 | 15.6782 | 4.7035 | Transfer | 0.3 | 15.6782 | 4.7035 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 01:00 | 0.05 | 11.3437 | 0.56718 | Reduce | 0.05 | 11.3437 | 0.56718 | H3 | 3 | Stable | 0.6 | 91 | 124 | 145 | 122 | 0.2 | 28 | 46 | 72 | 47.3333 | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 01:00 | 2017-03-22 | 0.05 | 87.6137 | 4.3807 | Reduce | 0.05 | 87.6137 | 4.3807 | H3 | 3 | Stable | 0.8 | 114 | 124 | 152 | 127 | 0.3 | 27 | 51 | 61 | 48.6667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.3 | 53.0293 | 15.9088 | Reduce | 0.3 | 53.0293 | 15.9088 | H3 | 3 | Worsening | 0.6 | 115 | 132 | 148 | 131.8333 | 0.3 | 29 | 52 | 61 | 49.6667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-187 | Project_027_Risk-187 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Loss of a major sub-contractor | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.12 | 16.7112 | 15.04 | Accept | 0.12 | 16.7112 | 15.04 | H3 | 3 | Stable | 0.8 | 111 | 140 | 160 | 138.5 | 0.8 | 111 | 140 | 160 | 138.5 | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Commercial aspects agreement | Person_480 | 2013-08-21 01:00 | 2016-05-22 | 0.02 | 4.8296 | 0.096593 | Transfer | 0.02 | 4.8296 | 0.096593 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 01:00 | 2017-08-20 01:00 | 0.1 | 34.363 | 3.4363 | Avoid | 0.1 | 34.363 | 3.4363 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.48 | 33.2985 | 15.9833 | Avoid | 0.48 | 33.2985 | 15.9833 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-126 | Project_032_Risk-126 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supply Chain - Delivery to Contract Requirement | Person_590 | 2012-08-21 01:00 | 2016-08-20 01:00 | 0.3 | 25.3619 | 7.6086 | Reduce | 0.3 | 25.3619 | 7.6086 | H2 | 4 | Stable | 0.5 | 113 | 140 | 153 | 137.6667 | 0.4 | 34 | 46 | 76 | 49 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-188 | Project_027_Risk-188 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Unidentified Technical Legacy Issue | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 0.20788 | 0.068599 | Accept | 0.1 | 0.20788 | 0.068599 | H3 | 3 | Stable | 0.9 | 118 | 135 | 146 | 134 | 0.9 | 118 | 135 | 146 | 134 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-196 | Project_027_Risk-196 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Aging equipment resulting in increasing failure rates | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.15 | 0.85811 | 0.42906 | Accept | 0.15 | 0.85811 | 0.42906 | H3 | 3 | Stable | 0.5 | 90 | 135 | 152 | 130.3333 | 0.5 | 90 | 135 | 152 | 130.3333 | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-185 | Project_027_Risk-185 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier manufacturing issues | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.6 | 0 | 0 | Accept | 0.05 | 0 | 0 | H3 | 3 | Stable | 0.9 | 110 | 134 | 145 | 131.8333 | 0.9 | 110 | 134 | 145 | 131.8333 |  | 91.6667 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK114 | Project_035_RISK114 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Qualification Facilities Availability. | Person_570 | 2015-09-21 01:00 | 2016-07-12 | 0.61 | 1.2358 | 0.75383 | Reduce | 0.3 | 1.2358 | 0.37073 | H2 | 4 | Stable | 0.7 | 87 | 127 | 154 | 124.8333 | 0.4 | 7 | 45 | 75 | 43.6667 | 0 | 50.8197 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-186 | Project_027_Risk-186 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Potential for composite suppliers going out of business | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 3.1633 | 0.63267 | Accept | 0.1 | 3.1633 | 0.63267 | H3 | 3 | Stable | 0.9 | 85 | 136 | 150 | 129.8333 | 0.9 | 85 | 136 | 150 | 129.8333 | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK003 | Project_035_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Environmental Qualification | Person_570 | 2015-05-24 | 2016-07-16 | 0.3 | 6.9524 | 2.0857 | Reduce | 0.23 | 3.6326 | 0.8355 | H2 | 4 | Worsening | 0.7 | 89 | 130 | 149 | 126.3333 | 0.3 | 9 | 51 | 68 | 46.8333 | 47.75 | 23.3333 | 0 | 28.65
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-194 | Project_027_Risk-194 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | The effect of specialist supplier obsolescence on complex assemblies | Person_074 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.15 | 6.3266 | 1.898 | Accept | 0.15 | 6.3266 | 1.898 | H3 | 3 | Stable | 0.5 | 115 | 138 | 154 | 136.8333 | 0.5 | 115 | 138 | 154 | 136.8333 | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK354 | Project_035_RISK354 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Product Team support for dependent projects | Person_151 | 2015-05-24 | 2016-08-13 | 0.5 | 0 | 0 | -- | 0.5 | 0 | 0 | H2 | 4 | Worsening | [11 empty] | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 | 0.1 | 1.2271 | 0.50311 | Accept | 0.05 | 1.2271 | 0.50311 | H3 | 3 | Stable | 0.6 | 108 | 135 | 156 | 134 | 0.6 | 108 | 135 | 156 | 134 | 0 | 50 | 1 | 1.5
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-015 | Project_028_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | STANDARDS Compliance | Person_499 | 2015-10-22 | 2016-11-19 | 0.05 | 3.65 | 0.365 | Accept | 0.05 | 3.65 | 0.365 | H3 | 3 | Stable | 0.9 | 90 | 131 | 154 | 128 | 0.9 | 90 | 131 | 154 | 128 | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK380 | Project_035_RISK380 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Data Throttling Algorithm | Person_699 | 2016-01-03 01:00 | 2016-11-20 01:00 | 0.2 | 2.6071 | 0.52143 | Reduce | 0.2 | 2.6071 | 0.52143 | H3 | 3 | Stable | 0.7 | 112 | 132 | 146 | 131 | 0.1 | 20 | 45 | 73 | 45.5 | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK394 | Project_035_RISK394 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Provision of supplier evidence | Person_631 | 2016-02-21 01:00 | 2016-08-20 01:00 | 0.5 | 2.4768 | 1.2384 | -- | 0.5 | 2.4768 | 1.2384 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK350 | Project_035_RISK350 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Sub-System Performance against Bid Scenario | Person_303 | 2015-06-24 | 2017-01-19 01:00 | 0.5 | 2.0423 | 1.0211 | -- | 0.3 | 1.0168 | 0.30503 | H2 | 4 | Stable | [10 empty] | 50.2128 | 40 | 0 | 30.1277
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-050 | Project_028_Risk-050 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Compatibility | Person_542 | 2015-10-22 | 2016-08-20 | 0.15 | 0 | 0 | Accept | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 92 | 128 | 148 | 125.3333 | 0.8 | 92 | 128 | 148 | 125.3333 |  | 33.3333 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK290 | Project_035_RISK290 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Face-to-Face Arbitration | Person_699 | 2015-01-22 01:00 | 2016-09-20 01:00 | 0.5 | 1.2445 | 0.62224 | -- | 0.2 | 1.2167 | 0.24333 | H3 | 3 | Improving | [10 empty] | 2.2349 | 60 | 0 | 1.3409
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK395 | Project_035_RISK395 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Test area Site Availability | Person_691 | 2016-05-23 | 2016-11-19 01:00 | 0.5 | 3.0417 | 1.5208 | -- | 0.5 | 3.0417 | 1.5208 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK324 | Project_037_RISK324 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Delay to integration | Person_330 | 2015-05-24 | 2016-05-15 | 0.5 | 1.4926 | 0.74629 | Reduce | 0.3 | 1.4926 | 0.44777 | H2 | 4 | Stable | 0.7 | 105 | 131 | 157 | 131 | 0.1 | 6 | 49 | 78 | 46.6667 | 0 | 40 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-10-21 01:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.6 | 108 | 128 | 157 | 129.5 | 0.3 | 37 | 53 | 63 | 52 | 47 | 0 | 0 | 28.2
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-11-20 01:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 4.7805 | 0.9561 | H3 | 3 | Stable | [10 empty] | 0 | 60 | 1 | 1.8
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-038 | Project_028_Risk-038 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Network Installation Features | Person_542 | 2015-04-08 | 2017-08-20 | 0.3 | 10.7826 | 4.3131 | Accept | 0.3 | 10.7826 | 4.3131 | H2 | 4 | Stable | 0.9 | 97 | 140 | 144 | 133.5 | 0.9 | 97 | 140 | 144 | 133.5 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK117 | Project_037_RISK117 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Data Comms Availability or Performance | Person_334 | 2015-05-24 | 2016-11-20 01:00 | 0.35 | 3.2401 | 1.134 | Transfer | 0.1 | 3.2401 | 0.32401 | H3 | 3 | Stable | [10 empty] | 0 | 71.4286 | 1 | 2.1429
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2016-08-19 01:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.4 | 3.187 | 1.2748 | H2 | 4 | Stable | 0.5 | 119 | 124 | 154 | 128.1667 | 0.3 | 39 | 53 | 68 | 53.1667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 0.4 | 9.139 | 3.6556 | Avoid | 0.2 | 9.139 | 1.8278 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK226 | Project_038_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Capacity to support enhancements or fixes post delivery | Person_330 | 2015-11-21 01:00 | 2017-05-22 | 0.5 | 13.9332 | 6.9666 | Avoid | 0.1 | 13.9332 | 1.3933 | H3 | 3 | Improving | [10 empty] | 0 | 80 | 1 | 2.4
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 0.5 | 13.7833 | 6.8917 | Avoid | 0.2 | 13.7833 | 2.7567 | H3 | 3 | Stable | [10 empty] | 0 | 60 | 1 | 1.8
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-037 | Project_028_Risk-037 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Migration to RedHat 7 | Person_542 | 2015-04-08 | 2016-08-20 | 0.2 | 5.6182 | 4.4946 | Accept | 0.1 | 5.6182 | 4.4946 | H3 | 3 | Stable | 0.9 | 96 | 127 | 158 | 127 | 0.9 | 96 | 127 | 158 | 127 | 0 | 50 | 1 | 1.5
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK187 | Project_038_RISK187 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Technical Publications | Person_671 | 2015-07-22 | 2016-06-22 | 0.5 | 4.6444 | 2.3222 | Avoid | 0.3 | 4.6444 | 1.3933 | H2 | 4 | Worsening | [10 empty] | 0 | 40 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK220 | Project_038_RISK220 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Lack of Resources needed to deliver the programme | Person_330 | 2013-09-20 01:00 | 2015-10-20 01:00 | 0.5 | 45.6947 | 22.8474 | Avoid | 0.1 | 18.1281 | 1.8128 | H2 | 4 | Stable | [10 empty] | 60.3279 | 80 | 0 | 36.1967
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-09-20 01:00 | 0.3 | 5.5433 | 1.663 | Reduce | 0.2 | 5.5433 | 1.1087 | H3 | 3 | Stable | 0.8 | 103 | 137 | 159 | 135 | 0.4 | 22 | 51 | 74 | 50 | 0 | 33.3333 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Stable | [10 empty] | 0 | 75 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK227 | Project_038_RISK227 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Verification and Acceptance of Customer Furnished Equipmnet Goods & Services | Person_330 | 2015-02-21 01:00 | 2016-05-22 | 0.6 | 6.4422 | 3.8653 | Avoid | 0.2 | 6.4422 | 1.2884 | H3 | 3 | Stable | [10 empty] | 0 | 66.6667 | 1 | 2
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-034 | Project_028_Risk-034 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Network Migration | Person_542 | 2015-04-08 | 2017-05-22 | 0.5 | 4.4946 | 1.1236 | Accept | 0.5 | 4.4946 | 1.1236 | H2 | 4 | Stable | 0.7 | 84 | 129 | 141 | 123.5 | 0.7 | 84 | 129 | 141 | 123.5 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-041 | Project_028_Risk-041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Role Test Equipment Team Deliver Late | Person_542 | 2015-04-08 | 2016-11-19 | 0.4 | 6.7418 | 1.6855 | Accept | 0.2 | 6.7418 | 1.6855 | H2 | 4 | Stable | 0.9 | 100 | 125 | 144 | 124 | 0.9 | 100 | 125 | 144 | 124 | 0 | 50 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-049 | Project_028_Risk-049 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | More integration required | Person_542 | 2015-04-08 | 2016-08-19 | 0.05 | 5.4834 | 1.0967 | Accept | 0.05 | 5.4834 | 0.43867 | H3 | 3 | Stable | 0.9 | 107 | 129 | 144 | 127.8333 | 0.9 | 107 | 129 | 144 | 127.8333 | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-048 | Project_028_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Compatibility | Person_542 | 2015-04-08 | 2016-08-20 | 0.05 | 5.3935 | 1.0787 | Accept | 0.05 | 5.3935 | 0.21574 | H2 | 4 | Stable | 0.8 | 97 | 140 | 157 | 135.6667 | 0.8 | 97 | 140 | 157 | 135.6667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK390 | Project_038_RISK390 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component shock failure | Person_531 | 2016-01-17 01:00 | 2016-06-23 | 0.2 | 17.1093 | 3.4219 | -- | 0.2 | 17.1093 | 3.4219 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 0.125 | 232.2192 | 29.0274 | -- | 0.125 | 156.8004 | 19.6 | H2 | 4 | Stable | [10 empty] | 32.4774 | 0 | 0 | 19.4865
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-045 | Project_028_Risk-045 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Subcontractor Delays to Software | Person_542 | 2015-11-21 | 2016-06-22 | 0.3 | 8.9142 | 2.6743 | Accept | 0.3 | 6.6669 | 2.0001 | H2 | 4 | Stable | 0.8 | 102 | 137 | 144 | 132.3333 | 0.8 | 102 | 137 | 144 | 132.3333 | 25.2101 | 0 | 0 | 15.126
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK232 | Project_038_RISK232 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Integration more complex than expected | Person_531 | 2015-11-21 01:00 | 2016-08-21 01:00 | 0.3 | 27.7165 | 8.3149 | Reduce | 0.185 | 27.7165 | 5.1275 | H2 | 4 | Improving | 0.7 | 114 | 135 | 157 | 135.1667 | 0.4 | 18 | 50 | 71 | 48.1667 | 0 | 38.3333 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 0.3 | 26.9674 | 8.0902 | Avoid | 0.3 | 14.9819 | 4.4946 | H2 | 4 | Stable | [10 empty] | 44.4444 | 0 | 0 | 26.6667
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-05-16 | 0.5 | 26.9674 | 13.4837 | Avoid | 0.0265 | 26.9674 | 0.71464 | H2 | 4 | Worsening | [10 empty] | 0 | 94.7 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence and missing info | Person_727 | 2015-11-25 | 2016-08-20 | 0.3 | 4.5695 | 0.45695 | Accept | 0.3 | 4.5695 | 0.45695 | H2 | 4 | Stable | 0.7 | 117 | 123 | 146 | 125.8333 | 0.7 | 117 | 123 | 146 | 125.8333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 | 2016-08-20 | 0.2 | 5.3935 | 1.3484 | Accept | 0.2 | 5.3935 | 1.3484 | H2 | 4 | Stable | 0.6 | 99 | 124 | 158 | 125.5 | 0.6 | 99 | 124 | 158 | 125.5 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-002 | Project_028_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Record / Replay feature | Person_499 | 2014-03-23 | 2016-08-20 | 0.1 | 17.9783 | 3.5957 | Accept | 0.05 | 17.9783 | 3.5957 | H2 | 4 | Stable | 0.6 | 100 | 129 | 141 | 126.1667 | 0.6 | 100 | 129 | 141 | 126.1667 | 0 | 50 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-108 | Project_039_Risk-108 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Product Redesign | Person_224 | 2015-06-24 | 2015-11-21 01:00 | 0.3 | 0.42929 | 0.12879 | Reduce | 0.1 | 0.51515 | 0.051515 | H3 | 3 | Stable | 0.6 | 115 | 125 | 149 | 127.3333 | 0.3 | 35 | 45 | 60 | 45.8333 | -20 | 66.6667 | 0 | -12
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-107 | Project_039_Risk-107 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact of the Component on performace | Person_224 | 2015-07-29 | 2016-07-20 | 0.5 | 0.29211 | 0.14605 | Reduce | 0.25 | 0.29211 | 0.073027 | H2 | 4 | Stable | 0.7 | 83 | 137 | 141 | 128.6667 | 0.4 | 21 | 51 | 67 | 48.6667 | 0 | 50 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-109 | Project_039_Risk-109 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Component Reselection | Person_224 | 2015-06-24 | 2016-05-15 | 0.3 | 2.218 | 0.6654 | Reduce | 0.2 | 2.3611 | 0.47222 | H3 | 3 | Stable | 0.5 | 97 | 133 | 151 | 130 | 0.2 | 8 | 59 | 66 | 51.6667 | -6.4515 | 33.3333 | 0 | -3.8709
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-104 | Project_039_Risk-104 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Not able to accurately measure past limits | Person_176 | 2015-08-06 | 2016-05-23 | 0.2 | 0.54026 | 0.10805 | Reduce | 0.05 | 0.54062 | 0.027031 | H3 | 3 | Stable | 0.7 | 94 | 130 | 148 | 127 | 0.3 | 20 | 44 | 63 | 43.1667 | -0.065952 | 75 | 0 | -0.039571
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-115 | Project_039_Risk-115 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Physical Integration of subsystem in to system | Person_343 | 2015-12-22 01:00 | 2016-05-15 | 0.5 | 2.4184 | 1.2092 | Reduce | 0.1 | 2.4184 | 0.24184 | H3 | 3 | Stable | 0.9 | 86 | 133 | 141 | 126.5 | 0.1 | 8 | 40 | 68 | 39.3333 | 0 | 80 | 1 | 2.4
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | EMC Testing | Person_070 | 2016-04-22 | 2016-08-20 | 0.35 | 0.68686 | 0.13737 | Accept | 0.2 | 0.68686 | 0.13737 | H2 | 4 | Stable | 0.7 | 85 | 132 | 147 | 126.6667 | 0.7 | 85 | 132 | 147 | 126.6667 | 0 | 42.8571 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-114 | Project_039_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Dual Cutoff | Person_343 | 2015-07-25 | 2016-06-23 | 0.5 | 19.8331 | 9.9165 | Reduce | 0.3 | 19.8331 | 5.9499 | H2 | 4 | Stable | 0.7 | 96 | 134 | 159 | 131.8333 | 0.2 | 15 | 54 | 62 | 48.8333 | 0 | 40 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-106 | Project_039_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Deliverables - Report Rework | Person_185 | 2014-12-22 01:00 | 2015-05-23 | 0.5 | 0.53661 | 0.2683 | Reduce | 0.25 | 0.53661 | 0.13415 | H2 | 4 | Stable | 0.9 | 101 | 140 | 143 | 134 | 0.4 | 30 | 54 | 69 | 52.5 | 0 | 50 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-117 | Project_039_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Filters | Person_380 | 2015-01-21 01:00 | 2016-07-20 | 0.4 | 3.005 | 1.202 | Reduce | 0.2 | 3.005 | 0.601 | H3 | 3 | Stable | 0.6 | 95 | 123 | 144 | 121.8333 | 0.3 | 18 | 49 | 78 | 48.6667 | 0 | 50 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-105 | Project_039_Risk-105 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | PMO Loading | Person_185 | 2014-12-22 01:00 | 2015-05-23 | 0.5 | 0.98021 | 0.4901 | Reduce | 0.15 | 0.98021 | 0.14703 | H3 | 3 | Stable | 0.6 | 92 | 123 | 146 | 121.6667 | 0.1 | 5 | 57 | 68 | 50.1667 | 0 | 70 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-017 | Project_039_Risk-017 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Component coupling causes unrecoverable impact | Person_596 | 2014-12-22 01:00 | 2016-08-20 01:00 | 0.6 | 8.1135 | 4.8681 | Avoid | 0.2 | 8.1135 | 1.6227 | H3 | 3 | Worsening | [10 empty] | 0 | 66.6667 | 1 | 2
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_542 | 2015-01-22 | 2017-08-20 | 0.35 | 0.48597 | 0.14579 | Accept | 0.2 | 0.48573 | 0.072859 | H2 | 4 | Stable | 0.8 | 88 | 132 | 154 | 128.3333 | 0.8 | 88 | 132 | 154 | 128.3333 | 0.050352 | 42.8571 | 0 | 0.030211
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-111 | Project_039_Risk-111 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Maturation results inconclusive | Person_297 | 2016-02-21 01:00 | 2016-05-15 | 0.5 | 0.35617 | 0.17808 | Reduce | 0.1 | 0.35617 | 0.035617 | H3 | 3 | Stable | 0.6 | 84 | 132 | 159 | 128.5 | 0.4 | 13 | 56 | 67 | 50.6667 | 0 | 80 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-102 | Project_039_Risk-102 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Component Structural Failure | Person_176 | 2015-11-21 01:00 | 2016-05-22 | 0.15 | 2.5686 | 0.38529 | Reduce | 0.05 | 2.5686 | 0.12843 | H3 | 3 | Stable | 0.5 | 80 | 122 | 155 | 120.5 | 0.1 | 26 | 48 | 78 | 49.3333 | 0 | 66.6667 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-113 | Project_039_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Integrated System Delay | Person_343 | 2015-07-24 | 2016-07-20 | 0.5 | 21.6218 | 10.8109 | Reduce | 0.3 | 14.6673 | 4.4002 | H2 | 4 | Stable | 0.7 | 83 | 123 | 147 | 120.3333 | 0.2 | 3 | 40 | 75 | 39.6667 | 32.1641 | 40 | 0 | 19.2985
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-098 | Project_039_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Supplier unable to provide compiant power source | Person_040 | 2015-07-24 | 2016-01-21 01:00 | 0.5 | 1.0875 | 0.54376 | Reduce | 0.1 | 1.0875 | 0.10875 | H3 | 3 | Stable | 0.7 | 96 | 130 | 141 | 126.1667 | 0.4 | 8 | 44 | 79 | 43.8333 | 0 | 80 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_070 | 2016-06-23 | 2016-08-21 | 0.4 | 2.3457 | 0.11728 | Accept | 0.2 | 2.3457 | 0.023457 | H2 | 4 | Stable | 0.8 | 117 | 140 | 141 | 136.3333 | 0.8 | 117 | 140 | 141 | 136.3333 | 0 | 50 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-117 | Project_029_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework costs | Person_216 | 2015-09-21 01:00 | 2016-12-19 01:00 | 0.33 | 2.3457 | 0.11728 | Accept | 0.33 | 2.3457 | 0.023457 | H3 | 3 | Stable | 0.5 | 108 | 129 | 157 | 130.1667 | 0.5 | 108 | 129 | 157 | 130.1667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK114 | Project_035_RISK114 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Qualification Facilities Availability. | Person_570 | 2015-09-21 01:00 | 2016-07-12 | 0.61 | 1.2358 | 0.75383 | Reduce | 0.3 | 1.2358 | 0.37073 | H2 | 4 | Stable | 0.6 | 95 | 138 | 156 | 133.8333 | 0.4 | 11 | 42 | 70 | 41.5 | 0 | 50.8197 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-017 | Project_029_Risk-017 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Additional Obsolescence - System | Person_102 | 2016-05-23 | 2017-10-21 01:00 | 0.5 | 3.1633 | 0.63267 | Accept | 0.1 | 3.1633 | 0.63267 | H3 | 3 | Stable | 0.9 | 89 | 128 | 157 | 126.3333 | 0.9 | 89 | 128 | 157 | 126.3333 | 0 | 80 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK003 | Project_035_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Environmental Qualification | Person_570 | 2015-05-24 | 2016-07-16 | 0.3 | 6.9524 | 2.0857 | Reduce | 0.23 | 3.6326 | 0.8355 | H2 | 4 | Worsening | 0.8 | 97 | 138 | 154 | 133.8333 | 0.2 | 8 | 46 | 78 | 45 | 47.75 | 23.3333 | 0 | 28.65
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-111 | Project_029_Risk-111 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Unplanned courier cost and T&S for any transportation of hardware during Integration phase | Person_692 | 2015-07-22 | 2016-06-23 | 0.8 | 6.3266 | 1.898 | Accept | 0.8 | 6.3266 | 1.898 | H2 | 4 | Stable | 0.6 | 83 | 130 | 156 | 126.5 | 0.6 | 83 | 130 | 156 | 126.5 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2016-05-23 | 2018-05-22 | 0.4 | 3.2155 | 0.96464 | Accept | 0.3 | 3.2155 | 0.48232 | H2 | 4 | Stable | 0.9 | 101 | 126 | 144 | 124.8333 | 0.9 | 101 | 126 | 144 | 124.8333 | 0 | 25 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2019-10-14 01:00 | 0.2 | 3.2155 | 0.96464 | Accept | 0.2 | 3.2155 | 0.96464 | H3 | 3 | Stable | 0.9 | 108 | 137 | 147 | 133.8333 | 0.9 | 108 | 137 | 147 | 133.8333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-026 | Project_029_Risk-026 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | platform Integration - SW support | Person_102 | 2016-09-02 01:00 | 2019-09-24 01:00 | 0.5 | 1.2271 | 0.50311 | Accept | 0.4 | 1.2271 | 0.50311 | H3 | 3 | Stable | 0.5 | 120 | 138 | 145 | 136.1667 | 0.5 | 120 | 138 | 145 | 136.1667 | 0 | 20 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK380 | Project_035_RISK380 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Data Throttling Algorithm | Person_699 | 2016-01-03 01:00 | 2016-11-20 01:00 | 0.2 | 2.6071 | 0.52143 | Reduce | 0.2 | 2.6071 | 0.52143 | H3 | 3 | Stable | 0.7 | 86 | 138 | 144 | 130.3333 | 0.2 | 25 | 43 | 67 | 44 | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK394 | Project_035_RISK394 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Provision of supplier evidence | Person_631 | 2016-02-21 01:00 | 2016-08-20 01:00 | 0.5 | 2.4768 | 1.2384 | -- | 0.5 | 1.2167 | 0.60833 | H2 | 4 | Stable | [10 empty] | 50.8773 | 0 | 0 | 30.5264
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK350 | Project_035_RISK350 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Sub-System Performance against Bid Scenario | Person_303 | 2015-06-24 | 2017-01-19 01:00 | 0.5 | 2.0423 | 1.0211 | -- | 0.3 | 1.0168 | 0.30503 | H2 | 4 | Stable | [10 empty] | 50.2128 | 40 | 0 | 30.1277
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2015-07-22 | 2017-11-19 01:00 | 0.3 | 8.4297 | 1.6859 | Accept | 0.2 | 4.745 | 0.949 | H3 | 3 | Stable | 0.6 | 105 | 125 | 152 | 126.1667 | 0.6 | 105 | 125 | 152 | 126.1667 | 43.7114 | 33.3333 | 1 | 27.2268
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2017-10-20 01:00 | 0.03 | 3.5631 | 0.53446 | Accept | 0.1 | 3.5631 | 0.53446 | H2 | 4 | Stable | 0.5 | 88 | 133 | 153 | 128.8333 | 0.5 | 88 | 133 | 153 | 128.8333 | 0 | -233.3333 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK290 | Project_035_RISK290 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Face-to-Face Arbitration | Person_699 | 2015-01-22 01:00 | 2016-09-20 01:00 | 0.5 | 1.2445 | 0.62224 | -- | 0.2 | 2.303 | 0.46059 | H3 | 3 | Improving | [10 empty] | -85.0557 | 60 | 0 | -51.0334
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK395 | Project_035_RISK395 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Test area Site Availability | Person_691 | 2016-05-23 | 2016-11-19 01:00 | 0.5 | 3.0417 | 1.5208 | -- | 0.5 | 3.0417 | 1.5208 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub-system FPGA | Person_216 | 2014-02-20 01:00 | 2017-05-22 | 0.3 | 32.3541 | 16.1771 | Accept | 0.2 | 33.1432 | 28.1718 | H3 | 3 | Stable | 0.6 | 83 | 130 | 148 | 125.1667 | 0.6 | 83 | 130 | 148 | 125.1667 | -2.439 | 33.3333 | 1 | -0.46341
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-043 | Project_008_Risk-043 | Opportunitity | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Joint courseware and tech pubs team | Person_280 | 2014-11-21 01:00 | 2016-11-19 01:00 | 0.5 | 28.2191 | 14.1096 | -- | 0.5 | 12.4997 | 6.2499 | H2 | 4 | Stable | [10 empty] | 55.7047 | 0 | 0 | 33.4228
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 0.1 | 9.3748 | 4.6874 | Accept | 0.1 | 9.3748 | 4.6874 | H2 | 4 | Stable | 0.6 | 93 | 129 | 156 | 127.5 | 0.6 | 93 | 129 | 156 | 127.5 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-059 | Project_008_Risk-059 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Project Resource Efficencies | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 0.2 | 21.6852 | 4.337 | -- | 0.2 | 21.6852 | 4.337 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-120 | Project_032_Risk-120 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | System STTE Equipment Roll Out | Person_768 | 2014-03-23 | 2017-03-23 | 0.9 | 17.2187 | 12.914 | Accept | 0.9 | 8.0017 | 6.0013 | H2 | 4 | Stable | 0.7 | 94 | 139 | 144 | 132.3333 | 0.7 | 94 | 139 | 144 | 132.3333 | 53.5289 | 0 | 0 | 32.1173
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-072 | Project_008_Risk-072 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply chain | Saving on budget for repairs | Person_565 | 2016-01-22 01:00 | 2018-08-21 | 0.5 | 13.8255 | 6.9127 | -- | 0.5 | 13.8255 | 6.9127 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK312 | Project_035_RISK312 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Audio Performance inadequate | Person_303 | 2015-06-24 | 2016-08-13 | 0.2 | 0.68188 | 0.27275 | Accept | 0.2 | 0.68188 | 0.27275 | H3 | 3 | Stable | 0.9 | 106 | 124 | 150 | 125.3333 | 0.9 | 106 | 124 | 150 | 125.3333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK313 | Project_035_RISK313 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Deployed Performance inadequate | Person_303 | 2015-05-24 | 2016-08-13 | 0.3 | 0.88815 | 0.62171 | Accept | 0.3 | 0.88815 | 0.62171 | H2 | 4 | Stable | 0.8 | 120 | 140 | 152 | 138.6667 | 0.8 | 120 | 140 | 152 | 138.6667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | PRs per release cannot be absorbed within each WP and require a dedicated PR budget | Person_147 | 2013-08-21 01:00 | 2018-08-21 | 0.8 | 0.47334 | 0.37867 | Reduce | 0.8 | 0.47334 | 0.37867 | H1 | 5 | Stable | 0.7 | 100 | 133 | 147 | 129.8333 | 0.4 | 5 | 46 | 73 | 43.6667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK309 | Project_035_RISK309 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Facility performance unacceptable during Scenario testing | Person_303 | 2015-03-24 | 2016-06-15 | 0.3 | 0.42493 | 0.25921 | Accept | 0.15 | 0.42493 | 0.25921 | H3 | 3 | Stable | 0.5 | 82 | 134 | 151 | 128.1667 | 0.5 | 82 | 134 | 151 | 128.1667 | 0 | 50 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK308 | Project_035_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Facility performance during Live trials | Person_303 | 2015-05-24 | 2016-12-21 01:00 | 0.3 | 0.45743 | 0.1601 | Accept | 0.3 | 0.45743 | 0.1601 | H2 | 4 | Stable | 0.7 | 90 | 126 | 156 | 125 | 0.7 | 90 | 126 | 156 | 125 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 0.3 | 8.7814 | 2.6344 | Reduce | 0.2 | 8.7832 | 1.7566 | H3 | 3 | Stable | 0.5 | 118 | 128 | 147 | 129.5 | 0.2 | 31 | 41 | 74 | 44.8333 | -0.021119 | 33.3333 | 0 | -0.012672
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK304 | Project_035_RISK304 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change at Elevation | Person_701 | 2016-09-20 01:00 | 2016-11-20 01:00 | 0.41 | 0.13638 | 0.054551 | Accept | 0.41 | 0.13638 | 0.054551 | H2 | 4 | Stable | 0.7 | 114 | 131 | 144 | 130.3333 | 0.7 | 114 | 131 | 144 | 130.3333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK317 | Project_035_RISK317 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_570 | 2014-10-22 01:00 | 2016-08-19 01:00 | 0.1 | 108.3186 | 32.4956 | Accept | 0.1 | 108.3186 | 32.4956 | H3 | 3 | Stable | 0.9 | 114 | 127 | 159 | 130.1667 | 0.9 | 114 | 127 | 159 | 130.1667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-010 | Project_011_Risk-010 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Rework required following integration of Customer System | Person_140 | 2015-12-22 01:00 | 2016-08-19 01:00 | 0.5 | 1.3291 | 0.66455 | Reduce | 0.5 | 1.3291 | 0.66455 | H1 | 5 | Stable | 0.7 | 83 | 134 | 159 | 129.6667 | 0.4 | 37 | 51 | 66 | 51.1667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Delay of processing | Person_306 | 2016-01-13 01:00 | 2019-08-21 01:00 | 0.15 | 26.3497 | 3.9525 | Reduce | 0.15 | 26.3497 | 3.9525 | H3 | 3 | Improving | 0.9 | 89 | 129 | 149 | 125.6667 | 0.1 | 11 | 52 | 74 | 48.8333 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK053 | Project_035_RISK053 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Assembly Use of Glass Reinforced Plastics | Person_570 | 2015-03-24 | 2016-07-16 | 0.2 | 0.41709 | 0.18769 | Accept | 0.2 | 0.41709 | 0.18769 | H3 | 3 | Stable | 0.7 | 94 | 137 | 142 | 130.6667 | 0.7 | 94 | 137 | 142 | 130.6667 | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 0.5 | 9.2728 | 4.6364 | Reduce | 0.3 | 9.2728 | 2.7819 | H2 | 4 | Stable | 0.9 | 113 | 132 | 153 | 132.3333 | 0.2 | 11 | 50 | 68 | 46.5 | 0 | 40 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 0.4 | 0.68188 | 0.27275 | Reduce | 0.4 | 0.6137 | 0.24548 | H2 | 4 | Stable | 0.8 | 81 | 136 | 142 | 127.8333 | 0.1 | 35 | 56 | 77 | 56 | 10 | 0 | 0 | 6
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Obsolescence Monitoring Risk | Person_181 | 2016-12-03 01:00 | 2017-01-20 01:00 | 0.3 | 5.9458 | 1.7837 | Reduce | 0.15 | 0.9786 | 0.14679 | H3 | 3 | Stable | 0.7 | 90 | 122 | 142 | 120 | 0.2 | 3 | 58 | 63 | 49.6667 | 83.5413 | 50 | 0 | 50.1248
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK096 | Project_035_RISK096 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Product Real World Performance | Person_699 | 2015-05-24 | 2016-10-20 01:00 | 0.15 | 3.0903 | 0.61807 | Accept | 0.15 | 3.0903 | 0.61807 | H3 | 3 | Stable | 0.7 | 94 | 133 | 158 | 130.6667 | 0.7 | 94 | 133 | 158 | 130.6667 | 0 | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK093 | Project_035_RISK093 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Sensitivity & Dynamic Range | Person_699 | 2015-01-22 01:00 | 2016-08-13 | 0 | 30.9033 | 7.7258 | Accept | 0 | 30.9033 | 7.7258 | H2 | 4 | Stable | 0.9 | 99 | 135 | 149 | 131.3333 | 0.9 | 99 | 135 | 149 | 131.3333 | 0 |  | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK118 | Project_037_RISK118 | Threat | Management Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Product does not deliver the inputs/depdencies required by the Project by the req'd dates | Person_330 | 2015-02-23 21:00 | 2015-12-19 21:00 | 0.4 | 15.0654 | 6.7794 | Accept | 0.4 | 15.0654 | 6.7794 | H2 | 4 | Worsening | 0.5 | 92 | 140 | 159 | 135.1667 | 0.5 | 92 | 140 | 159 | 135.1667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-200 | Project_027_Risk-200 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Sucession Planning for key team members | Person_060 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.2 | 7.3175 | 1.4635 | Reduce | 0.05 | 7.3175 | 0.36588 | H2 | 4 | Stable | 0.8 | 85 | 136 | 149 | 129.6667 | 0.2 | 21 | 41 | 65 | 41.6667 | 0 | 75 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-189 | Project_027_Risk-189 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Major Component obsolescence | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 8.3972 | 2.5191 | Reduce | 0.25 | 8.3972 | 2.0993 | H2 | 4 | Stable | 0.8 | 113 | 131 | 141 | 129.6667 | 0.2 | 25 | 58 | 72 | 54.8333 | 0 | 16.6667 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.7 | 88 | 135 | 160 | 131.3333 | 0.2 | 23 | 45 | 68 | 45.1667 | 0 | 25 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-201 | Project_027_Risk-201 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Transition into Support | Person_027 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0.5 | 68.3768 | 34.1884 | Reduce | 0.05 | 38.387 | 1.9193 | H2 | 4 | Stable | 0.7 | 93 | 125 | 156 | 124.8333 | 0.1 | 28 | 44 | 79 | 47.1667 | 43.8597 | 90 | 0 | 26.3158
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK269 | Project_038_RISK269 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software Development | Resource issue in card to provide real time data due to adding 2nd interface | Person_303 | 2015-07-22 | 2016-08-14 | 0.8 | 13.2195 | 1.5863 | Accept | 0.8 | 13.2195 | 1.5863 | H1 | 5 | Stable | 0.6 | 101 | 126 | 157 | 127 | 0.6 | 101 | 126 | 157 | 127 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance | Person_240 | 2015-12-22 01:00 | 2016-08-14 | 0.25 | 20.0332 | 2.0033 | Accept | 0.25 | 20.0332 | 2.0033 | H2 | 4 | Stable | 0.5 | 97 | 123 | 144 | 122.1667 | 0.5 | 97 | 123 | 144 | 122.1667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-193 | Project_027_Risk-193 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | A greater number of arising technical queries | Person_110 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 13.7953 | 4.1386 | Reduce | 0.05 | 13.7953 | 0.68977 | H3 | 3 | Stable | 0.5 | 89 | 122 | 149 | 121 | 0.1 | 7 | 55 | 60 | 47.8333 | 0 | 83.3333 | 1 | 2.5
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-09-20 01:00 | 0.25 | 16.1945 | 2.4292 | Accept | 0.25 | 16.1945 | 2.4292 | H2 | 4 | Stable | 0.6 | 105 | 131 | 157 | 131 | 0.6 | 105 | 131 | 157 | 131 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK152 | Project_038_RISK152 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Test Equipment Costs | Person_640 | 2015-06-24 | 2016-05-22 | 0.2 | 35.9878 | 21.5927 | Accept | 0.08 | 15.5947 | 0.77974 | H3 | 3 | Stable | 0.8 | 81 | 122 | 158 | 121.1667 | 0.8 | 81 | 122 | 158 | 121.1667 | 56.6667 | 60 | 0 | 34
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK154 | Project_038_RISK154 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production Tools and Jigs | Person_640 | 2015-06-24 | 2016-07-16 | 0.3 | 6.7866 | 6.7866 | Accept | 0.3 | 6.7866 | 6.7866 | H2 | 4 | Stable | 0.5 | 94 | 128 | 154 | 126.6667 | 0.5 | 94 | 128 | 154 | 126.6667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK160 | Project_038_RISK160 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Low noise Requirement | Person_017 | 2016-02-21 01:00 | 2016-07-21 | 0.1 | 19.1935 | 2.879 | Accept | 0.1 | 19.1935 | 2.879 | H3 | 3 | Stable | 0.8 | 117 | 135 | 145 | 133.6667 | 0.8 | 117 | 135 | 145 | 133.6667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-007 | Project_026_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Additional requests for information and attendance at meetings | Person_264 | 2014-11-21 01:00 | 2018-12-27 01:00 | 0.5 | 10.5249 | 5.2625 | Reduce | 0.5 | 10.5249 | 5.2625 | H2 | 4 | Worsening | 0.7 | 92 | 138 | 149 | 132.1667 | 0.2 | 2 | 57 | 74 | 50.6667 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK163 | Project_038_RISK163 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Additional Chamber trials | Person_531 | 2015-09-21 01:00 | 2016-09-20 01:00 | 0.25 | 8.3972 | 0.83972 | Accept | 0.25 | 8.3972 | 0.41986 | H2 | 4 | Stable | 0.5 | 117 | 137 | 145 | 135 | 0.5 | 117 | 137 | 145 | 135 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-103 | Project_039_Risk-103 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Performance when integrated not sufficient. | Person_176 | 2016-01-22 01:00 | 2016-06-20 | 0.2 | 3.4415 | 1.3766 | Accept | 0.2 | 3.4415 | 1.3766 | H3 | 3 | Stable | 0.9 | 116 | 135 | 151 | 134.5 | 0.9 | 116 | 135 | 151 | 134.5 | 0 | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-100 | Project_039_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Integration performance | Person_176 | 2016-01-22 01:00 | 2016-06-22 | 0.3 | 8.0582 | 2.4175 | Accept | 0.15 | 8.0582 | 2.4175 | H3 | 3 | Stable | 0.5 | 116 | 138 | 147 | 135.8333 | 0.5 | 116 | 138 | 147 | 135.8333 | 0 | 50 | 1 | 1.5
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_040 | RISK174 | Project_040_RISK174 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Supplier Power Supply quality | Person_687 | 2013-08-20 21:00 | 2014-07-22 | 0.05 | 0.5596 | 0.05596 | Accept | 0.01 | 0.5596 | 0.05596 | H2 | 4 | Stable | 0.7 | 101 | 121 | 149 | 122.3333 | 0.7 | 101 | 121 | 149 | 122.3333 | 0 | 80 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_040 | RISK174 | Project_040_RISK174 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Supplier Power Supply quality | Person_687 | 2013-08-20 21:00 | 2014-07-22 | 0.05 | 3.6174 | 1.8087 | Accept | 0.01 | 3.6172 | 1.8086 | H2 | 4 | Stable | 0.6 | 104 | 128 | 149 | 127.5 | 0.6 | 104 | 128 | 149 | 127.5 | 0.0051359 | 80 | 0 | 0.0030815
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK312 | Project_035_RISK312 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Audio Performance inadequate | Person_303 | 2015-06-24 | 2016-08-13 | 0.2 | 2.3503 | 0.47006 | Accept | 0.2 | 2.3503 | 0.47006 | H3 | 3 | Stable | 0.5 | 102 | 125 | 142 | 124 | 0.5 | 102 | 125 | 142 | 124 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK313 | Project_035_RISK313 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Deployed Performance inadequate | Person_303 | 2015-05-24 | 2016-08-13 | 0.3 | 4.4768 | 2.2384 | Accept | 0.3 | 4.4768 | 2.2384 | H2 | 4 | Stable | 0.6 | 113 | 127 | 142 | 127.1667 | 0.6 | 113 | 127 | 142 | 127.1667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK309 | Project_035_RISK309 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Facility performance unacceptable during Scenario testing | Person_303 | 2015-03-24 | 2016-10-13 01:00 | 0.3 | 0.85811 | 0.42906 | Accept | 0.15 | 0.85811 | 0.42906 | H3 | 3 | Stable | 0.8 | 113 | 134 | 144 | 132.1667 | 0.8 | 113 | 134 | 144 | 132.1667 | 0 | 50 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK308 | Project_035_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Facility performance during Live trials | Person_303 | 2015-05-24 | 2016-12-21 01:00 | 0.3 | 0 | 0 | Accept | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 93 | 121 | 156 | 122.1667 | 0.9 | 93 | 121 | 156 | 122.1667 |  | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK304 | Project_035_RISK304 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change at Elevation | Person_701 | 2016-09-20 01:00 | 2016-11-20 01:00 | 0.41 | 244.3581 | 12.2179 | Accept | 0.41 | 227.5702 | 11.3785 | H2 | 4 | Stable | 0.8 | 82 | 131 | 146 | 125.3333 | 0.8 | 82 | 131 | 146 | 125.3333 | 6.8702 | 0 | 0 | 4.1221
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-019 | Project_026_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Customer interaction and reporting may be much greater than anticipated | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 0.3 | 16.3694 | 4.9108 | Reduce | 0.2 | 16.3683 | 3.2737 | H3 | 3 | Worsening | 0.5 | 90 | 125 | 145 | 122.5 | 0.3 | 15 | 54 | 79 | 51.6667 | 0.0068371 | 33.3333 | 0 | 0.0041023
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK053 | Project_035_RISK053 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Assembly Use of Glass Reinforced Plastics | Person_570 | 2015-03-24 | 2016-07-16 | 0.2 | 27.1831 | 13.5915 | Accept | 0.2 | 27.1831 | 13.5915 | H3 | 3 | Stable | 0.9 | 82 | 140 | 155 | 132.8333 | 0.9 | 82 | 140 | 155 | 132.8333 | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 22:00 | 2019-08-20 22:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 22:00 | 2019-08-20 22:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 22:00 | 2019-08-20 22:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 22:00 | 2019-08-20 22:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 22:00 | 2019-08-20 22:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R012 | Project_021_Risk-R012 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Additional profiles required - in addition to those planned | Person_174 | 2016-02-05 23:00 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.9 | 117 | 133 | 156 | 134.1667 | 0.2 | 3 | 41 | 66 | 38.8333 |  | 60 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-12 23:00 | 2017-03-20 23:00 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.7 | 85 | 121 | 151 | 120 | 0.3 | 11 | 48 | 70 | 45.5 | 80 | 66.6667 | 0 | 48
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK096 | Project_035_RISK096 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Product Real World Performance | Person_699 | 2015-05-24 | 2016-10-20 01:00 | 0.15 | 12.1398 | 8.4978 | Accept | 0.15 | 12.1398 | 8.4978 | H3 | 3 | Stable | 0.5 | 120 | 125 | 151 | 128.5 | 0.5 | 120 | 125 | 151 | 128.5 | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK004 | Project_021_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Delivery by Supplier late or requires correction that causes re-start of rig testing | Person_470 | 2016-02-12 23:00 | 2016-08-19 23:00 | 0.5 | 1.6113 | 0.80564 | Avoid | 0.5 | 1.6113 | 0.80564 | H1 | 5 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_470 | 2016-11-18 23:00 | 2017-11-18 23:00 | 0.4 | 0.48559 | 0.19424 | Reduce | 0.4 | 0.48559 | 0.19424 | H2 | 4 | Stable | 0.6 | 83 | 122 | 146 | 119.5 | 0.3 | 4 | 59 | 60 | 50 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R026 | Project_021_Risk-R026 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Delay in readiness of System Equipment to commence Acceptance | Person_470 | 2016-02-27 23:00 | 2016-07-20 | 0.25 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H2 | 4 | Stable | 0.7 | 118 | 139 | 147 | 136.8333 | 0.1 | 20 | 58 | 78 | 55 |  | 60 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 0.5 | 0.33108 | 0.082771 | Accept | 0.85 | 0.33108 | 0.082771 | H2 | 4 | Stable | 0.6 | 85 | 139 | 143 | 130.6667 | 0.6 | 85 | 139 | 143 | 130.6667 | 0 | -70 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Programme extension | Person_428 | 2009-06-23 | 2017-05-21 | 0.7 | 32.645 | 22.8515 | Reduce | 0.5 | 32.645 | 16.3225 | H1 | 5 | Stable | 0.8 | 118 | 133 | 150 | 133.3333 | 0.1 | 1 | 43 | 63 | 39.3333 | 0 | 28.5714 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Rejected concessions | Person_766 | 2016-02-10 23:00 | 2017-02-18 23:00 | 0.5 | 36.8056 | 18.4028 | Reduce | 0.15 | 33.5499 | 5.0325 | H2 | 4 | Worsening | 0.5 | 84 | 135 | 149 | 128.8333 | 0.1 | 21 | 58 | 71 | 54 | 8.8456 | 70 | 0 | 5.3073
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build ()/Decision Point concludes new release required | Person_428 | 2012-11-19 23:00 | 2017-05-21 | 0.1 | 165.5424 | 16.5542 | Reduce | 0.5 | 165.5424 | 82.7712 | H1 | 5 | Worsening | 0.9 | 111 | 138 | 150 | 135.5 | 0.3 | 32 | 54 | 78 | 54.3333 | 0 | -400 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_470 | 2013-09-19 23:00 | 2017-01-19 23:00 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.5 | 12.6474 | 6.3237 | H1 | 5 | Stable | 0.9 | 102 | 128 | 141 | 125.8333 | 0.1 | 23 | 56 | 62 | 51.5 | 0 | 16.6667 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_470 | 2010-04-19 | 2017-01-18 23:00 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.5 | 85 | 123 | 157 | 122.3333 | 0.2 | 17 | 53 | 62 | 48.5 | 0 | 50 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safey Case Release is more complicated / delayed. | Person_470 | 2013-01-06 23:00 | 2017-02-18 23:00 | 0.5 | 4.7676 | 2.3838 | Reduce | 0.3 | 4.7676 | 1.4303 | H2 | 4 | Stable | 0.6 | 92 | 133 | 159 | 130.5 | 0.3 | 8 | 45 | 74 | 43.6667 | 0 | 40 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_470 | 2013-01-06 23:00 | 2017-01-18 23:00 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.7 | 83 | 129 | 154 | 125.5 | 0.1 | 21 | 48 | 67 | 46.6667 | 0 | 33.3333 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-20 23:00 | 2017-06-21 | 0.7 | 10.8044 | 7.5631 | Reduce | 0.3 | 10.8044 | 3.2413 | H2 | 4 | Worsening | 0.5 | 87 | 136 | 141 | 128.6667 | 0.1 | 10 | 57 | 69 | 51.1667 | 0 | 57.1429 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R013 | Project_021_Risk-R013 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials take longer to complete and delay the schedule | Person_470 | 2016-02-05 23:00 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.4 | 0 | 0 | H2 | 4 | Stable | 0.7 | 120 | 125 | 144 | 127.3333 | 0.2 | 35 | 49 | 71 | 50.3333 |  | 20 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-030 | Project_008_Risk-030 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Transition from old to new Standard causing additional unexpected work | Person_639 | 2013-09-20 01:00 | 2016-06-22 | 0.75 | 4.4985 | 1.3495 | Accept | 0.75 | 4.4985 | 1.3495 | H1 | 5 | Stable | 0.6 | 120 | 129 | 155 | 131.8333 | 0.6 | 120 | 129 | 155 | 131.8333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-21 22:00 | 2017-05-22 | 0.25 | 7.4225 | 1.8556 | Reduce | 0.1 | 3.7113 | 0.37113 | H3 | 3 | Stable | 0.9 | 85 | 126 | 158 | 124.5 | 0.3 | 20 | 59 | 63 | 53.1667 | 50 | 60 | 0 | 30
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-18 22:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 2.6991 | 1.0796 | H2 | 4 | Stable | 0.6 | 83 | 121 | 142 | 118.1667 | 0.2 | 24 | 53 | 66 | 50.3333 | 31.8182 | 20 | 0 | 19.0909
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation | Person_565 | 2018-05-22 | 2018-08-21 | 0.25 | 18.069 | 1.8069 | Accept | 0.25 | 18.069 | 1.8069 | H3 | 3 | Stable | 0.9 | 119 | 133 | 142 | 132.1667 | 0.9 | 119 | 133 | 142 | 132.1667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_575 | 2015-05-24 | 2017-11-18 22:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 6.2979 | 0.94468 | H3 | 3 | Stable | 0.7 | 116 | 122 | 145 | 124.8333 | 0.1 | 11 | 46 | 69 | 44 | 0 | 70 | 1 | 2.1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 | 2017-08-20 | 0.25 | 7.7469 | 1.9367 | Reduce | 0.25 | 7.7469 | 1.9367 | H3 | 3 | Stable | 0.6 | 83 | 136 | 149 | 129.3333 | 0.1 | 32 | 58 | 66 | 55 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-131 | Project_032_Risk-131 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Failure | Person_360 | 2012-08-21 | 2017-07-20 | 0.3 | 15.6782 | 4.7035 | Transfer | 0.3 | 15.6782 | 4.7035 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 | 0.05 | 11.3437 | 0.56718 | Reduce | 0.05 | 11.3437 | 0.56718 | H3 | 3 | Stable | 0.7 | 104 | 125 | 151 | 125.8333 | 0.3 | 25 | 58 | 63 | 53.3333 | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 | 2017-03-22 | 0.05 | 87.6137 | 4.3807 | Reduce | 0.05 | 87.6137 | 4.3807 | H3 | 3 | Stable | 0.5 | 85 | 131 | 143 | 125.3333 | 0.4 | 25 | 52 | 64 | 49.5 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 | 2017-08-20 | 0.3 | 53.0293 | 15.9088 | Reduce | 0.3 | 53.0293 | 15.9088 | H3 | 3 | Worsening | 0.5 | 116 | 140 | 150 | 137.6667 | 0.3 | 35 | 53 | 73 | 53.3333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-074 | Project_008_Risk-074 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Re-design/Beyond Economic Repair costs | Person_565 | 2016-05-23 | 2016-11-19 01:00 | 1 | 16.7112 | 15.04 | Accept | 1 | 16.7112 | 15.04 | H1 | 5 | Stable | 0.6 | 102 | 121 | 151 | 122.8333 | 0.6 | 102 | 121 | 151 | 122.8333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Commercial aspects agreement | Person_480 | 2013-08-21 | 2016-05-22 | 0.02 | 4.8296 | 0.096593 | Transfer | 0.02 | 4.8296 | 0.096593 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 | 2017-08-20 | 0.1 | 34.363 | 3.4363 | Avoid | 0.1 | 34.363 | 3.4363 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 | 2017-08-20 | 0.48 | 33.2985 | 15.9833 | Avoid | 0.48 | 33.2985 | 15.9833 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-126 | Project_032_Risk-126 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supply Chain - Delivery to Contract Requirement | Person_590 | 2012-08-21 | 2016-08-20 | 0.3 | 25.3619 | 7.6086 | Reduce | 0.3 | 25.3619 | 7.6086 | H2 | 4 | Stable | 0.8 | 119 | 128 | 157 | 131.3333 | 0.3 | 3 | 49 | 72 | 45.1667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-21 01:00 | 2016-08-21 01:00 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.7 | 95 | 130 | 147 | 127 | 0.4 | 17 | 51 | 67 | 48 | 0 | 16.6667 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 0.3 | 12.815 | 2.563 | Accept | 0.3 | 12.815 | 2.563 | H2 | 4 | Stable | 0.6 | 86 | 138 | 148 | 131 | 0.6 | 86 | 138 | 148 | 131 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.7 | 94 | 124 | 157 | 124.5 | 0.2 | 7 | 50 | 73 | 46.6667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK004 | Project_010_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Export License | Person_359 | 2015-02-18 01:00 | 2017-08-20 01:00 | 0.8 | 0.18482 | 0.14786 | Reduce | 0.8 | 0.18482 | 0.14786 | H1 | 5 | Worsening | 0.8 | 109 | 130 | 154 | 130.5 | 0.1 | 39 | 57 | 63 | 55 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 01:00 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.9 | 84 | 138 | 149 | 130.8333 | 0.4 | 10 | 47 | 77 | 45.8333 | 0 | 40 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.7 | 0.92411 | 0.64688 | Reduce | 0.3 | 0.36965 | 0.11089 | H2 | 4 | Stable | 0.8 | 91 | 140 | 149 | 133.3333 | 0.4 | 17 | 43 | 65 | 42.3333 | 60 | 57.1429 | 0 | 36
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 01:00 | 2016-04-21 | 0.5 | 4.0661 | 2.033 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.8 | 114 | 126 | 150 | 128 | 0.1 | 10 | 49 | 78 | 47.3333 | 0 | 90 | 1 | 2.7
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.3 | 0.46206 | 0.13862 | H2 | 4 | Improving | 0.9 | 111 | 140 | 152 | 137.1667 | 0.2 | 19 | 59 | 73 | 54.6667 | 58.3333 | 50 | 0 | 35
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 01:00 | 2017-08-20 01:00 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.6 | 93 | 129 | 142 | 125.1667 | 0.2 | 27 | 56 | 69 | 53.3333 | 0 | 50 | 1 | 1.5
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.5 | 106 | 138 | 150 | 134.6667 | 0.2 | 36 | 48 | 63 | 48.5 | 0 | 25 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Stable | 0.5 | 112 | 134 | 147 | 132.5 | 0.2 | 8 | 49 | 75 | 46.5 | 0 | 40 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Worsening | [10 empty] | 0 | 37.5 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK84 | Project_010_RISK84 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality issues (for the future) | Person_359 | 2012-09-20 01:00 | 2017-08-20 01:00 | 0.6 | 2.033 | 1.2198 | Reduce | 0.25 | 0.92411 | 0.23103 | H2 | 4 | Stable | 0.7 | 113 | 125 | 145 | 126.3333 | 0.4 | 10 | 53 | 67 | 48.1667 | 54.5455 | 58.3333 | 0 | 32.7273
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 0.3 | 1.8482 | 0.55447 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.9 | 92 | 122 | 146 | 121 | 0.4 | 34 | 51 | 68 | 51 | 0 | 33.3333 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 01:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.7 | 83 | 130 | 154 | 126.1667 | 0.4 | 12 | 41 | 74 | 41.6667 | 90 | 75 | 1 | 56.25
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP068 | Project_024_OPP068 | Opportunitity | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Customer acceptance of iterative sell-off approach | Person_535 | 2016-07-21 | 2017-11-19 01:00 | 0.2 | 9.3045 | 1.8609 | -- | 0.3 | 9.3045 | 2.7913 | H2 | 4 | Stable | [10 empty] | 0 | -50 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-187 | Project_027_Risk-187 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Loss of a major sub-contractor | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.12 | 14.541 | 5.8164 | Accept | 0.12 | 14.541 | 5.8164 | H3 | 3 | Stable | 0.7 | 95 | 127 | 150 | 125.5 | 0.7 | 95 | 127 | 150 | 125.5 | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK166 | Project_024_RISK166 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Requirements Acceptance Criteria | Person_288 | 2016-04-10 | 2017-03-06 01:00 | 0.4 | 3.843 | 1.5372 | Reduce | 0.2 | 1.2464 | 0.24927 | H2 | 4 | Improving | 0.6 | 94 | 132 | 157 | 129.8333 | 0.2 | 21 | 47 | 72 | 46.8333 | 67.5676 | 50 | 0 | 40.5405
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-188 | Project_027_Risk-188 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Unidentified Technical Legacy Issue | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 1.3502 | 0.33756 | Accept | 0.1 | 1.3502 | 0.33756 | H3 | 3 | Stable | 0.5 | 112 | 125 | 159 | 128.5 | 0.5 | 112 | 125 | 159 | 128.5 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK196 | Project_024_RISK196 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional Trials - Cost of Labour | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.3 | 0.95209 | 0.28563 | Reduce | 0.2 | 0.95209 | 0.19042 | H2 | 4 | Worsening | 0.5 | 82 | 138 | 148 | 130.3333 | 0.1 | 35 | 50 | 63 | 49.6667 | 0 | 33.3333 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-196 | Project_027_Risk-196 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Aging equipment resulting in increasing failure rates | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.15 | 2.0816 | 0.20816 | Accept | 0.15 | 2.0816 | 0.20816 | H3 | 3 | Stable | 0.8 | 97 | 128 | 142 | 125.1667 | 0.8 | 97 | 128 | 142 | 125.1667 | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-185 | Project_027_Risk-185 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier manufacturing issues | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.6 | 17.0765 | 1.7076 | Accept | 0.05 | 17.0765 | 1.7076 | H3 | 3 | Stable | 0.8 | 112 | 140 | 154 | 137.6667 | 0.8 | 112 | 140 | 154 | 137.6667 | 0 | 91.6667 | 1 | 2.75
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-186 | Project_027_Risk-186 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Potential for composite suppliers going out of business | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 22.8501 | 6.855 | Accept | 0.1 | 22.8501 | 6.855 | H3 | 3 | Stable | 0.7 | 109 | 131 | 152 | 130.8333 | 0.7 | 109 | 131 | 152 | 130.8333 | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK244 | Project_024_RISK244 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Blue Screen Of Death (BSOD) | Person_534 | 2016-04-22 | 2016-07-21 | 0.1 | 15.1468 | 1.5147 | Reduce | 0.1 | 15.1468 | 1.5147 | H3 | 3 | Stable | 0.8 | 113 | 130 | 145 | 129.6667 | 0.1 | 16 | 41 | 76 | 42.6667 | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-194 | Project_027_Risk-194 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | The effect of specialist supplier obsolescence on complex assemblies | Person_074 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.15 | 11.1654 | 2.2331 | Accept | 0.15 | 11.1654 | 2.2331 | H3 | 3 | Stable | 0.7 | 106 | 130 | 153 | 129.8333 | 0.7 | 106 | 130 | 153 | 129.8333 | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials - Increased Cost | Person_073 | 2016-05-23 | 2017-02-19 01:00 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.5 | 105 | 129 | 150 | 128.5 | 0.1 | 19 | 42 | 65 | 42 | 0 | 50 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | People unable to sustain the pace | Person_413 | 2015-11-21 01:00 | 2017-05-22 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.6 | 106 | 127 | 151 | 127.5 | 0.1 | 16 | 56 | 75 | 52.5 | 0 | 5 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK153 | Project_024_RISK153 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Processor memory/performance Issue | Person_331 | 2016-06-23 | 2017-03-22 | 0.3 | 112.3463 | 33.7039 | Reduce | 0.2 | 56.0866 | 11.2173 | H2 | 4 | Stable | 0.7 | 114 | 125 | 159 | 128.8333 | 0.4 | 22 | 51 | 77 | 50.5 | 50.077 | 33.3333 | 0 | 30.0462
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK155 | Project_024_RISK155 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Late availability of Parameters | Person_534 | 2016-03-23 | 2016-09-11 01:00 | 0.3 | 4.1113 | 1.2334 | Reduce | 0.3 | 19.0417 | 5.7125 | H1 | 5 | Stable | 0.6 | 100 | 139 | 142 | 133 | 0.3 | 3 | 46 | 62 | 41.5 | -363.158 | 0 | 0 | -217.8948
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK201 | Project_024_RISK201 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Indication mode failure | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.25 | 1.6835 | 0.42087 | Reduce | 0.2 | 1.6835 | 0.33669 | H3 | 3 | Stable | 0.5 | 88 | 136 | 153 | 130.8333 | 0.2 | 37 | 51 | 62 | 50.5 | 0 | 20 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R017 | Project_021_Risk-R017 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Effort to address Hexavalent Chromium issue is unknown at time of baseline | Person_470 | 2016-02-05 23:00 | 2016-11-18 23:00 | 0.7 | 0.35487 | 0.035487 | Accept | 0.7 | 0.35487 | 0.035487 | H1 | 5 | Stable | 0.6 | 90 | 132 | 156 | 129 | 0.6 | 90 | 132 | 156 | 129 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R025 | Project_021_Risk-R025 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Analysis of Trials data may require further info or action to complete | Person_470 | 2016-02-17 23:00 | 2017-06-22 | 0.25 | 1.6835 | 0.42087 | Accept | 0.25 | 1.6835 | 0.42087 | H2 | 4 | Stable | 0.5 | 90 | 135 | 148 | 129.6667 | 0.5 | 90 | 135 | 148 | 129.6667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK213 | Project_024_RISK213 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Rigs requireaccreditation as "Special to Type" Test equipment | Person_351 | 2016-10-21 01:00 | 2017-08-20 01:00 | 0.3 | 33.7558 | 10.1267 | Reduce | 0.2 | 23.3694 | 4.6739 | H2 | 4 | Stable | 0.6 | 89 | 140 | 145 | 132.3333 | 0.1 | 8 | 46 | 78 | 45 | 30.7692 | 33.3333 | 0 | 18.4615
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK179 | Project_024_RISK179 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Testing Required | Person_289 | 2016-12-21 01:00 | 2017-05-22 | 0.5 | 3.5054 | 1.7527 | Reduce | 0.4 | 3.5054 | 1.4022 | H2 | 4 | Stable | 0.7 | 109 | 133 | 141 | 130.3333 | 0.1 | 26 | 42 | 61 | 42.5 | 0 | 20 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R002 | Project_021_Risk-R002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Rig Unreliability | Person_470 | 2013-01-06 23:00 | 2016-07-20 | 0.5 | 30.2764 | 12.1106 | Accept | 0.5 | 30.2764 | 12.1106 | H1 | 5 | Stable | 0.7 | 85 | 138 | 160 | 132.8333 | 0.7 | 85 | 138 | 160 | 132.8333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK218 | Project_024_RISK218 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | System issues general | Person_289 | 2016-08-21 01:00 | 2016-10-04 01:00 | 0.4 | 90.8811 | 36.3524 | Reduce | 0.3 | 39.3904 | 11.8171 | H1 | 5 | Stable | 0.5 | 82 | 136 | 143 | 128.1667 | 0.2 | 1 | 41 | 66 | 38.5 | 56.6571 | 25 | 0 | 33.9943
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK180 | Project_024_RISK180 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | High Accelerated Life Testing (HALT) | Person_289 | 2016-12-21 01:00 | 2017-05-03 | 0.4 | 10.4903 | 4.1961 | Reduce | 0.2 | 10.4903 | 2.0981 | H2 | 4 | Stable | 0.7 | 85 | 134 | 160 | 130.1667 | 0.3 | 3 | 49 | 75 | 45.6667 | 0 | 50 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 | 2017-07-20 | 0.1 | 35.885 | 14.354 | Accept | 0.1 | 35.885 | 25.4784 | H2 | 4 | Stable | 0.5 | 94 | 138 | 159 | 134.1667 | 0.5 | 94 | 138 | 159 | 134.1667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-120 | Project_032_Risk-120 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | System STTE Equipment Roll Out | Person_768 | 2014-03-23 | 2017-03-23 | 0.9 | 68.1262 | 6.8126 | Accept | 0.9 | 68.1262 | 6.8126 | H2 | 4 | Stable | 0.5 | 93 | 124 | 150 | 123.1667 | 0.5 | 93 | 124 | 150 | 123.1667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.35 | 0.55886 | 0.27943 | Accept | 0.35 | 0.55886 | 0.11177 | H3 | 3 | Stable | 0.8 | 113 | 130 | 155 | 131.3333 | 0.8 | 113 | 130 | 155 | 131.3333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.25 | 2.7943 | 0.55886 | Accept | 0.25 | 2.7943 | 0.55886 | H3 | 3 | Stable | 0.6 | 95 | 135 | 142 | 129.5 | 0.6 | 95 | 135 | 142 | 129.5 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-09 | Project_022_RISK-09 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance - Issues arise | Person_393 | 2012-04-22 | 2016-10-19 01:00 | 0.7 | 24.8225 | 17.3758 | Reduce | 0.48 | 12.2576 | 5.8836 | H2 | 4 | Stable | 0.9 | 82 | 135 | 145 | 127.8333 | 0.4 | 34 | 53 | 77 | 53.8333 | 50.6191 | 31.4286 | 0 | 30.3715
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-08 | Project_022_RISK-08 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Poor performance during acceptance phases | Person_248 | 2012-05-23 | 2016-10-19 01:00 | 0.65 | 5.6817 | 3.6931 | Reduce | 0.512 | 5.6817 | 2.909 | H1 | 5 | Stable | 0.5 | 87 | 126 | 147 | 123 | 0.2 | 29 | 55 | 64 | 52.1667 | 0 | 21.2308 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2016-10-19 01:00 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.347 | 2.9061 | 1.0084 | H2 | 4 | Worsening | 0.8 | 97 | 126 | 145 | 124.3333 | 0.4 | 12 | 44 | 68 | 42.6667 | 21.0126 | 56.625 | 0 | 12.6076
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-21 01:00 | 2019-08-20 | 0.5 | 2.3975 | 2.3975 | Accept | 0.5 | 4.3118 | 4.3118 | H2 | 4 | Stable | 0.9 | 103 | 126 | 141 | 124.6667 | 0.9 | 103 | 126 | 141 | 124.6667 | -79.8462 | 0 | 0 | -47.9077
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-22 | Project_022_RISK-22 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Setting to work Issues - monitor may require changing | Person_393 | 2014-10-22 01:00 | 2016-10-19 01:00 | 0.6 | 11.6428 | 6.9857 | Reduce | 0.2 | 19.5167 | 3.9033 | H3 | 3 | Worsening | 0.6 | 104 | 124 | 159 | 126.5 | 0.4 | 38 | 49 | 60 | 49 | -67.628 | 66.6667 | 0 | -40.5768
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-30 | Project_022_RISK-30 | Opportunitity | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Setting to work and acceptance issues | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 0.8 | 8.6133 | 6.8907 | Exploit | 0.8 | 2.6904 | 2.1524 | H2 | 4 | Stable | [10 empty] | 68.7641 | 0 | 0 | 41.2585
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 3.3531 | 2.6825 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-114 | Project_039_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Dual Cutoff | Person_343 | 2015-07-25 | 2016-06-23 | 0.5 | 19.8331 | 9.9165 | Reduce | 0.3 | 19.8331 | 5.9499 | H2 | 4 | Stable | 0.6 | 80 | 130 | 150 | 125 | 0.1 | 10 | 53 | 68 | 48.3333 | 0 | 40 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-117 | Project_039_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Filters | Person_185 | 2015-01-21 01:00 | 2016-07-20 | 0.1 | 3.005 | 0.3005 | Reduce | 0.1 | 3.005 | 0.3005 | H3 | 3 | Stable | 0.9 | 82 | 138 | 147 | 130.1667 | 0.1 | 14 | 52 | 63 | 47.5 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-111 | Project_039_Risk-111 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Maturation results inconclusive | Person_297 | 2016-02-21 01:00 | 2016-05-15 | 0.5 | 0.35617 | 0.17808 | Reduce | 0.1 | 0.35617 | 0.035617 | H3 | 3 | Stable | 0.8 | 81 | 131 | 145 | 125 | 0.2 | 24 | 49 | 64 | 47.3333 | 0 | 80 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-113 | Project_039_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Integrated System Delay | Person_343 | 2015-07-24 | 2016-07-20 | 0.05 | 21.6218 | 1.0811 | Reduce | 0.05 | 14.6673 | 0.73337 | H2 | 4 | Improving | 0.5 | 105 | 137 | 146 | 133.1667 | 0.1 | 12 | 50 | 64 | 46 | 32.1641 | 0 | 0 | 19.2985
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.41 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -2.5 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.61 | 0.25667 | 0.15657 | Reduce | 0.5 | 0.25667 | 0.12834 | H2 | 4 | Stable | 0.7 | 119 | 140 | 141 | 136.6667 | 0.1 | 21 | 49 | 68 | 47.5 | 0 | 18.0328 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2014-01-21 01:00 | 2017-11-20 01:00 | 0.4 | 1.078 | 0.43121 | Reduce | 0.2 | 1.078 | 0.2156 | H3 | 3 | Stable | 0.9 | 113 | 126 | 155 | 128.6667 | 0.4 | 38 | 42 | 61 | 44.5 | 0 | 50 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-118 | Project_029_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Acceptance Schedule is longer in duration/delayed | Person_102 | 2015-12-22 01:00 | 2016-08-21 01:00 | 0.55 | 0.56468 | 0.31057 | Reduce | 0.55 | 0.56468 | 0.31057 | H2 | 4 | Stable | 0.8 | 92 | 125 | 159 | 125.1667 | 0.4 | 27 | 57 | 66 | 53.5 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.2 | 0.77001 | 0.2541 | Accept | 0.2 | 0.77001 | 0.2541 | H3 | 3 | Stable | 0.9 | 88 | 127 | 157 | 125.5 | 0.9 | 88 | 127 | 157 | 125.5 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.05 | 6.4168 | 3.2084 | Accept | 0.05 | 1.5614 | 0.15614 | H2 | 4 | Stable | 0.5 | 119 | 132 | 150 | 132.8333 | 0.5 | 119 | 132 | 150 | 132.8333 | 75.6667 | 0 | 0 | 45.4
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-038 | Project_029_Risk-038 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Integration and Reliability | Person_216 | 2014-03-23 | 2016-11-19 01:00 | 0.15 | 1.155 | 0.17325 | Reduce | 0.15 | 0.77001 | 0.1155 | H3 | 3 | Stable | 0.8 | 91 | 139 | 159 | 134.3333 | 0.4 | 9 | 46 | 64 | 42.8333 | 33.3333 | 0 | 1 | 20
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2017-11-19 01:00 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-113 | Project_029_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | SW Delivery to INtegration (including bug fixes post delivery) | Person_199 | 2014-07-22 | 2016-11-19 01:00 | 0.4 | 0.64168 | 0.25667 | Avoid | 0.4 | 0.64168 | 0.25667 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2016-09-19 01:00 | 0.6 | 0.89835 | 0.53901 | Transfer | 0.6 | 0.89835 | 0.53901 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 0.8 | 0.12834 | 0.10267 | Accept | 0.6 | 0.12834 | 0.10267 | H1 | 5 | Stable | 0.8 | 105 | 122 | 155 | 124.6667 | 0.8 | 105 | 122 | 155 | 124.6667 | 0 | 25 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2015-07-31 | 2017-05-15 | 0.35 | 0.85557 | 0.29945 | Reduce | 0.35 | 0.92402 | 0.32341 | H2 | 4 | Stable | 0.6 | 99 | 139 | 148 | 133.8333 | 0.4 | 31 | 49 | 72 | 49.8333 | -8.0001 | 0 | 0 | -4.8001
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 01:00 | 2016-08-20 01:00 | 0.1 | 0.77001 | 0.30801 | Accept | 0.1 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.9 | 92 | 136 | 152 | 131.3333 | 0.9 | 92 | 136 | 152 | 131.3333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-105 | Project_029_Risk-105 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Changes to CE markings | Person_692 | 2015-05-24 | 2020-11-19 01:00 | 0.8 | 0.51334 | 0.41067 | Reduce | 0.3 | 0.51334 | 0.154 | H3 | 3 | Stable | 0.9 | 82 | 126 | 151 | 122.8333 | 0.3 | 13 | 55 | 64 | 49.5 | 0 | 62.5 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-028 | Project_029_Risk-028 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Assets (for system integration - repair of test assets) | Person_102 | 2015-02-21 01:00 | 2020-05-22 | 0.4 | 1.2834 | 0.51334 | Reduce | 0.2 | 1.2834 | 0.25667 | H3 | 3 | Stable | 0.6 | 113 | 135 | 143 | 132.6667 | 0.3 | 3 | 47 | 72 | 43.8333 | 0 | 50 | 1 | 1.5
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2016-05-23 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.8 | 80 | 125 | 143 | 120.5 | 0.1 | 39 | 51 | 75 | 53 | 0 | 28.5714 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-104 | Project_029_Risk-104 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Assumed Synergies between Plan and Prospect | Person_692 | 2014-10-22 01:00 | 2021-05-22 | 0 | 0 | 0 | Reduce | 0 | 0 | 0 | H2 | 4 | Improving | 0.7 | 120 | 140 | 151 | 138.5 | 0.1 | 30 | 50 | 71 | 50.1667 |  |  | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 0.2 | 1.54 | 0.30801 | Accept | 0.2 | 0.77001 | 0.154 | H3 | 3 | Improving | 0.9 | 100 | 121 | 154 | 123 | 0.9 | 100 | 121 | 154 | 123 | 50 | 0 | 1 | 30
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK189 | Project_024_RISK189 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment integration - Audio and Video recording | Person_289 | 2016-08-20 01:00 | 2017-01-21 01:00 | 0.49 | 0.87268 | 0.43634 | Accept | 0.49 | 0.87268 | 0.34907 | H1 | 5 | Worsening | 0.7 | 110 | 124 | 149 | 125.8333 | 0.7 | 110 | 124 | 149 | 125.8333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_289 | 2016-05-23 | 2016-12-20 01:00 | 0.4 | 0.94968 | 0.28491 | Accept | 0.4 | 0.94968 | 0.18994 | H1 | 5 | Stable | 0.9 | 81 | 131 | 146 | 125.1667 | 0.9 | 81 | 131 | 146 | 125.1667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK194 | Project_024_RISK194 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Performance Models require additional effort | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.25 | 27.1644 | 0.81493 | Accept | 0.25 | 12.8336 | 1.2834 | H2 | 4 | Stable | 0.6 | 104 | 124 | 154 | 125.6667 | 0.6 | 104 | 124 | 154 | 125.6667 | 52.7559 | 0 | 0 | 31.6535
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2014-07-22 | 2017-11-19 01:00 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.8 | 96 | 138 | 152 | 133.3333 | 0.3 | 19 | 53 | 79 | 51.6667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2017-10-14 01:00 | 0.41 | 6.4168 | 2.6309 | Transfer | 0.41 | 0 | 0 | H1 | 5 | Stable | [10 empty] | 100 | 0 | 0 | 60
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-004 | Project_029_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Functionality shortfalls of sub-system Application Software Integration with the system | Person_199 | 2015-11-21 01:00 | 2016-09-19 01:00 | 0.2 | 0.53901 | 0.1078 | Reduce | 0.15 | 0.53901 | 0.080852 | H3 | 3 | Stable | 0.5 | 88 | 138 | 144 | 130.6667 | 0.3 | 24 | 51 | 70 | 49.6667 | 0 | 25 | 1 | 0.75
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK195 | Project_024_RISK195 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Perfomance Validation document not accepted | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.1 | 1.54 | 0.46201 | Accept | 0.1 | 1.155 | 0.231 | H2 | 4 | Stable | 0.8 | 101 | 132 | 141 | 128.3333 | 0.8 | 101 | 132 | 141 | 128.3333 | 25 | 0 | 0 | 15
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-022 | Project_028_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Accrediation Scope | Person_371 | 2014-01-21 01:00 | 2016-09-19 01:00 | 0.5 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 20 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 0.3 | 12.1982 | 0.60991 | Accept | 0.3 | 12.1982 | 0.60991 | H1 | 5 | Improving | 0.5 | 82 | 130 | 156 | 126.3333 | 0.5 | 82 | 130 | 156 | 126.3333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_119 | 2016-10-21 01:00 | 2017-11-19 01:00 | 0.3 | 0 | 0 | Accept | 0.3 | 0 | 0 | H1 | 5 | Improving | 0.9 | 120 | 130 | 147 | 131.1667 | 0.9 | 120 | 130 | 147 | 131.1667 |  | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK237 | Project_024_RISK237 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer coding standard Compliance | Person_534 | 2017-05-25 | 2017-10-27 01:00 | 0.2 | 0 | 0 | Accept | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.7 | 94 | 127 | 151 | 125.5 | 0.7 | 94 | 127 | 151 | 125.5 |  | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK198 | Project_024_RISK198 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Spot Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 0.2 | 4.4003 | 0.66004 | Accept | 0.2 | 4.4003 | 0.44003 | H3 | 3 | Stable | 0.9 | 118 | 126 | 141 | 127.1667 | 0.9 | 118 | 126 | 141 | 127.1667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2016-11-19 01:00 | 0.2 | 0.90951 | 0.1819 | Reduce | 0.2 | 0.90951 | 0.1819 | H3 | 3 | Stable | 0.7 | 93 | 126 | 141 | 123 | 0.3 | 26 | 51 | 71 | 50.1667 | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK197 | Project_024_RISK197 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Fitness for purpose | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.2 | 0.681 | 0.2724 | Accept | 0.2 | 0.681 | 0.1362 | H2 | 4 | Improving | 0.8 | 88 | 122 | 148 | 120.6667 | 0.8 | 88 | 122 | 148 | 120.6667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK199 | Project_024_RISK199 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Strip Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 0.3 | 1.4532 | 0.072661 | Accept | 0.3 | 1.4532 | 0.072661 | H2 | 4 | Stable | 0.5 | 86 | 135 | 154 | 130 | 0.5 | 86 | 135 | 154 | 130 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK152 | Project_024_RISK152 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Component Damage | Person_674 | 2016-04-06 | 2016-10-21 01:00 | 0.1 | 11.0007 | 0.55004 | Accept | 0.1 | 11.0007 | 0.55004 | H3 | 3 | Stable | 0.6 | 87 | 122 | 144 | 119.8333 | 0.6 | 87 | 122 | 144 | 119.8333 | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2016-09-19 01:00 | 0.3 | 5.4553 | 1.6366 | Reduce | 0.2 | 5.252 | 1.0504 | H2 | 4 | Stable | 0.9 | 84 | 134 | 157 | 129.5 | 0.1 | 37 | 48 | 75 | 50.6667 | 3.7267 | 33.3333 | 0 | 2.236
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-058 | Project_028_Risk-058 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | INterface Card | Person_253 | 2015-07-22 | 2016-09-19 01:00 | 0.2 | 2.8408 | 0.56817 | Reduce | 0.1 | 1.9314 | 0.19314 | H3 | 3 | Stable | 0.9 | 104 | 131 | 151 | 129.8333 | 0.2 | 33 | 45 | 76 | 48.1667 | 32.0134 | 50 | 1 | 20.708
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment environmental failure | Person_289 | 2016-05-23 | 2016-12-02 01:00 | 0.3 | 1.3215 | 0.39644 | Accept | 0.3 | 1.3215 | 0.39644 | H1 | 5 | Improving | 0.6 | 95 | 124 | 145 | 122.6667 | 0.6 | 95 | 124 | 145 | 122.6667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Retained systems re-design or modification | Person_289 | 2016-08-20 01:00 | 2016-12-02 01:00 | 0.05 | 12.1982 | 2.4396 | Accept | 0.05 | 10.8428 | 2.1686 | H2 | 4 | Improving | 0.6 | 82 | 133 | 150 | 127.3333 | 0.6 | 82 | 133 | 150 | 127.3333 | 11.1111 | 0 | 0 | 6.6667
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Mission System not compatible with platform systems | Person_289 | 2016-07-21 | 2017-02-19 01:00 | 0.1 | 4.4727 | 0.44727 | Accept | 0.1 | 4.4727 | 0.22363 | H3 | 3 | Stable | 0.5 | 115 | 121 | 150 | 124.8333 | 0.5 | 115 | 121 | 150 | 124.8333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK202 | Project_024_RISK202 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Mode Specific | Person_448 | 2015-09-04 01:00 | 2017-02-19 01:00 | 0.2 | 20.3303 | 7.1156 | Accept | 0.2 | 18.975 | 3.795 | H3 | 3 | Stable | 0.7 | 109 | 140 | 147 | 136 | 0.7 | 109 | 140 | 147 | 136 | 6.6667 | 0 | 0 | 4
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Cable and connectors | Person_050 | 2015-11-21 01:00 | 2017-08-09 | 0.45 | 0.41338 | 0.18602 | Reduce | 0.2 | 0.41338 | 0.082677 | H2 | 4 | Stable | 0.5 | 84 | 122 | 151 | 120.5 | 0.4 | 29 | 51 | 75 | 51.3333 | 0 | 55.5556 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Platform Acceptance | Person_500 | 2015-11-21 01:00 | 2017-01-20 01:00 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.2 | 4.2355 | 0.8471 | H3 | 3 | Stable | 0.8 | 105 | 126 | 142 | 125.1667 | 0.4 | 28 | 50 | 74 | 50.3333 | 0 | 42.8571 | 1 | 1.2857
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-001 | Project_028_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Porting software | Person_542 | 2014-03-23 | 2016-12-20 01:00 | 0.5 | 8.8098 | 4.4049 | Reduce | 0.08 | 7.4545 | 0.59636 | H2 | 4 | Stable | 0.6 | 84 | 128 | 154 | 125 | 0.1 | 6 | 43 | 67 | 40.8333 | 15.3846 | 84 | 0 | 9.2308
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK204 | Project_024_RISK204 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Stabilisation | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.4 | 8.8098 | 3.0834 | Accept | 0.4 | 8.8098 | 1.762 | H1 | 5 | Improving | 0.9 | 101 | 135 | 156 | 132.8333 | 0.9 | 101 | 135 | 156 | 132.8333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK203 | Project_024_RISK203 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Detection/Tracking modifications | Person_448 | 2016-10-21 01:00 | 2017-02-19 01:00 | 0.1 | 0.40661 | 0.16264 | Accept | 0.1 | 0.40661 | 0.081321 | H3 | 3 | Improving | 0.5 | 82 | 121 | 156 | 120.3333 | 0.5 | 82 | 121 | 156 | 120.3333 | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Furnished Equipmnet Condition | Person_371 | 2015-04-27 | 2017-08-19 01:00 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.8 | 111 | 127 | 157 | 129.3333 | 0.3 | 7 | 59 | 69 | 52 |  | 62.5 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK200 | Project_024_RISK200 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Height Finding | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.35 | 1.2105 | 1.2105 | Accept | 0.35 | 1.2105 | 1.2105 | H2 | 4 | Worsening | 0.8 | 111 | 127 | 156 | 129.1667 | 0.8 | 111 | 127 | 156 | 129.1667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 01:00 | 2016-05-21 | 0.5 | 4.3921 | 2.196 | Reduce | 0.3 | 4.3921 | 1.3176 | H1 | 5 | Stable | 0.7 | 85 | 136 | 143 | 128.6667 | 0.4 | 21 | 41 | 72 | 42.8333 | 0 | 40 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-58 | Project_022_RISK-58 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Handbook Update | Person_248 | 2012-04-19 | 2016-10-19 01:00 | 0.5 | 2.2354 | 1.1177 | Reduce | 0.5 | 2.2354 | 1.1177 | H3 | 3 | Stable | 0.7 | 111 | 133 | 151 | 132.3333 | 0.2 | 2 | 42 | 76 | 41 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK209 | Project_024_RISK209 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Major Return to Service | Person_073 | 2016-11-20 01:00 | 2017-05-22 | 0.3 | 7.2272 | 3.6136 | Accept | 0.3 | 7.2272 | 3.6136 | H1 | 5 | Stable | 0.7 | 108 | 133 | 143 | 130.5 | 0.7 | 108 | 133 | 143 | 130.5 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK206 | Project_024_RISK206 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Simulator Updates | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.1 | 4.4221 | 2.2111 | Accept | 0.1 | 4.4221 | 2.2111 | H3 | 3 | Stable | 0.8 | 81 | 129 | 142 | 123.1667 | 0.8 | 81 | 129 | 142 | 123.1667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Overland performance | Person_448 | 2016-06-23 | 2017-05-21 | 0.25 | 4.4778 | 2.2389 | Accept | 0.25 | 4.4778 | 2.2389 | H2 | 4 | Improving | 0.9 | 81 | 140 | 147 | 131.3333 | 0.9 | 81 | 140 | 147 | 131.3333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Qual failure | Person_289 | 2016-06-22 | 2016-11-20 01:00 | 0.4 | 3.8666 | 1.5853 | Accept | 0.4 | 1.3288 | 0.5448 | H1 | 5 | Improving | 0.8 | 81 | 140 | 154 | 132.5 | 0.8 | 81 | 140 | 154 | 132.5 | 65.6338 | 0 | 0 | 39.3803
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2016-11-17 01:00 | 0.85 | 25.2325 | 21.4476 | Avoid | 0.08 | 20.8758 | 1.6701 | H2 | 4 | Improving | [10 empty] | 17.2662 | 90.5882 | 0 | 10.3597
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-018 | Project_023_Risk-018 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Project Management | Person_703 | 2013-05-19 | 2017-05-22 | 0.8 | 0.10892 | 0.087134 | Exploit | 0.8 | 0.10892 | 0.087134 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK210 | Project_024_RISK210 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Performance | Person_532 | 2016-06-22 | 2017-02-19 01:00 | 0.3 | 5.9904 | 1.4976 | Accept | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 83 | 121 | 157 | 120.6667 | 0.6 | 83 | 121 | 157 | 120.6667 | 100 | 0 | 0 | 60
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Additional minor releases | Person_073 | 2016-05-23 | 2017-08-20 01:00 | 0.5 | 5.4459 | 1.6338 | Accept | 0.5 | 0.18151 | 0.054453 | H1 | 5 | Stable | 0.8 | 110 | 133 | 144 | 131 | 0.8 | 110 | 133 | 144 | 131 | 96.667 | 0 | 0 | 58.0002
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-019 | Project_023_Risk-019 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software | Person_253 | 2013-05-19 | 2017-05-22 | 0.8 | 0.38121 | 0.30497 | Exploit | 0.8 | 0.38121 | 0.30497 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2016-11-17 01:00 | 0.7 | 24.1887 | 16.9321 | Reduce | 0.25 | 4.3567 | 1.0892 | H2 | 4 | Stable | 0.6 | 113 | 123 | 157 | 127 | 0.4 | 32 | 59 | 78 | 57.6667 | 81.9887 | 64.2857 | 0 | 49.1932
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-020 | Project_023_Risk-020 | Opportunitity | Project Contingency | Open | H2 | 4 | 8. System Engineering | Installation & Acceptance - Preventative Maintenance | Person_253 | 2013-05-19 | 2017-05-22 | 0.8 | 0.81688 | 0.6535 | Exploit | 0.8 | 0.81688 | 0.6535 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-021 | Project_023_Risk-021 | Opportunitity | Project Contingency | Open | H2 | 4 | 8. System Engineering | Customer Services - Preventative Maintenance | Person_253 | 2013-05-19 | 2017-05-22 | 0.8 | 1.1981 | 0.95847 | Exploit | 0.8 | 1.1981 | 0.95847 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Digital Video Chainredesign | Person_289 | 2016-06-22 | 2016-12-17 01:00 | 0.4 | 60.4367 | 3.0218 | Accept | 0.71 | 60.4367 | 3.0218 | H1 | 5 | Worsening | 0.7 | 85 | 140 | 145 | 131.6667 | 0.7 | 85 | 140 | 145 | 131.6667 | 0 | -77.5 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-077 | Project_008_Risk-077 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply chain | product Spares | Person_565 | 2016-07-21 | 2017-01-19 01:00 | 1 | 14.2042 | 14.2042 | -- | 1 | 14.2042 | 14.2042 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK253 | Project_024_RISK253 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Insufficient parts to complete framework Warranty | Person_289 | 2016-05-23 | 2017-04-21 | 0.1 | 0.77172 | 0.30869 | Accept | 0.1 | 0.77172 | 0.30869 | H2 | 4 | Improving | 0.6 | 97 | 128 | 148 | 126.1667 | 0.6 | 97 | 128 | 148 | 126.1667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R43 | Project_041_R43 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Procurement - Component and Supplier Leadtime | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 0.25 | 10.9327 | 2.7332 | Reduce | 0.15 | 10.9327 | 1.6399 | H2 | 4 | Worsening | 0.9 | 87 | 124 | 158 | 123.5 | 0.3 | 14 | 42 | 70 | 42 | 0 | 40 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 0.45 | 10.7184 | 4.8233 | Reduce | 0.25 | 5.3592 | 1.3398 | H2 | 4 | Worsening | 0.7 | 92 | 137 | 160 | 133.3333 | 0.1 | 22 | 41 | 61 | 41.1667 | 50 | 44.4444 | 0 | 30
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R44 | Project_041_R44 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Procurement - Source Change | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 0.1 | 7.0313 | 0.70313 | Reduce | 0.01 | 7.0313 | 0.070313 | H2 | 4 | Improving | 0.6 | 98 | 121 | 160 | 123.6667 | 0.1 | 5 | 53 | 78 | 49.1667 | 0 | 90 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-47 | Project_022_RISK-47 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Software Issues | Person_245 | 2012-04-19 | 2016-10-19 01:00 | 0.5 | 1.2519 | 0.31298 | Accept | 0.2 | 1.2519 | 0.31298 | H3 | 3 | Stable | 0.8 | 99 | 130 | 159 | 129.6667 | 0.8 | 99 | 130 | 159 | 129.6667 | 0 | 60 | 1 | 1.8
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-51 | Project_022_RISK-51 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Environment Conditions | Person_393 | 2012-04-19 | 2016-10-19 01:00 | 0.2 | 3.7514 | 0.37514 | Accept | 0.2 | 3.7514 | 0.37514 | H3 | 3 | Stable | 0.5 | 96 | 122 | 143 | 121.1667 | 0.5 | 96 | 122 | 143 | 121.1667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-117 | Project_029_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework costs | Person_216 | 2015-09-21 01:00 | 2016-12-19 01:00 | 0.33 | 3.3227 | 0.83067 | Accept | 0.33 | 3.3227 | 0.83067 | H3 | 3 | Stable | 0.5 | 111 | 140 | 156 | 137.8333 | 0.5 | 111 | 140 | 156 | 137.8333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-017 | Project_029_Risk-017 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Additional Obsolescence - System | Person_102 | 2016-05-23 | 2017-10-21 01:00 | 0.5 | 13.3529 | 6.6765 | Accept | 0.1 | 13.3529 | 6.6765 | H3 | 3 | Stable | 0.7 | 90 | 132 | 159 | 129.5 | 0.7 | 90 | 132 | 159 | 129.5 | 0 | 80 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-111 | Project_029_Risk-111 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Unplanned courier cost and T&S for any transportation of hardware during Integration phase | Person_692 | 2015-07-22 | 2016-08-21 01:00 | 0.8 | 1.8788 | 0.28182 | Accept | 0.8 | 1.8788 | 0.28182 | H2 | 4 | Stable | 0.6 | 106 | 138 | 158 | 136 | 0.6 | 106 | 138 | 158 | 136 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2016-05-23 | 2018-05-22 | 0.4 | 9.3941 | 1.8788 | Accept | 0.3 | 9.3941 | 1.8788 | H2 | 4 | Stable | 0.9 | 117 | 131 | 145 | 131 | 0.9 | 117 | 131 | 145 | 131 | 0 | 25 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2019-10-14 01:00 | 0.2 | 1.8788 | 0.18788 | Accept | 0.2 | 1.8788 | 0.18788 | H3 | 3 | Stable | 0.7 | 117 | 136 | 160 | 136.8333 | 0.7 | 117 | 136 | 160 | 136.8333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-026 | Project_029_Risk-026 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | platform Integration - SW support | Person_102 | 2016-09-02 01:00 | 2019-09-24 01:00 | 0.5 | 29.4599 | 8.838 | Accept | 0.4 | 18.7882 | 5.6365 | H3 | 3 | Stable | 0.8 | 99 | 140 | 158 | 136.1667 | 0.8 | 99 | 140 | 158 | 136.1667 | 36.2245 | 20 | 0 | 21.7347
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2015-07-22 | 2017-11-19 01:00 | 0.3 | 1.1273 | 0.22546 | Accept | 0.2 | 1.1273 | 0.22546 | H3 | 3 | Stable | 0.5 | 105 | 135 | 146 | 131.8333 | 0.5 | 105 | 135 | 146 | 131.8333 | 0 | 33.3333 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2017-10-20 01:00 | 0.03 | 4.7948 | 0.95895 | Accept | 0.1 | 4.7948 | 0.95895 | H2 | 4 | Stable | 0.5 | 100 | 134 | 156 | 132 | 0.5 | 100 | 134 | 156 | 132 | 0 | -233.3333 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub-system FPGA | Person_216 | 2014-02-20 01:00 | 2017-05-22 | 0.3 | 0.65759 | 0.098638 | Accept | 0.2 | 0.65759 | 0.098638 | H3 | 3 | Stable | 0.5 | 110 | 121 | 147 | 123.5 | 0.5 | 110 | 121 | 147 | 123.5 | 0 | 33.3333 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 01:00 | 0.1 | 6.7638 | 1.3528 | Accept | 0.05 | 6.7638 | 1.3528 | H3 | 3 | Stable | 0.8 | 116 | 121 | 144 | 124 | 0.8 | 116 | 121 | 144 | 124 | 0 | 50 | 1 | 1.5
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-015 | Project_028_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | STANDARDS Compliance | Person_499 | 2015-10-22 01:00 | 2016-11-19 01:00 | 0.05 | 0.93941 | 0.14091 | Accept | 0.05 | 0.93941 | 0.14091 | H3 | 3 | Stable | 0.7 | 114 | 122 | 150 | 125.3333 | 0.7 | 114 | 122 | 150 | 125.3333 | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-050 | Project_028_Risk-050 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Compatibility | Person_542 | 2015-10-22 01:00 | 2016-09-19 01:00 | 0.15 | 2.5834 | 0.64585 | Accept | 0.1 | 2.5834 | 0.64585 | H3 | 3 | Stable | 0.9 | 101 | 130 | 152 | 128.8333 | 0.9 | 101 | 130 | 152 | 128.8333 | 0 | 33.3333 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-041 | Project_028_Risk-041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Role Test Equipment Team Deliver Late | Person_542 | 2015-04-08 | 2016-11-19 01:00 | 0.4 | 0.65759 | 0.065759 | Accept | 0.2 | 0.75153 | 0.075153 | H2 | 4 | Stable | 0.6 | 82 | 131 | 149 | 125.8333 | 0.6 | 82 | 131 | 149 | 125.8333 | -14.2857 | 50 | 0 | -8.5714
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-049 | Project_028_Risk-049 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | More integration required | Person_542 | 2015-04-08 | 2016-09-19 01:00 | 0.05 | 1.1273 | 0.45092 | Accept | 0.05 | 1.1273 | 0.45092 | H3 | 3 | Stable | 0.6 | 115 | 129 | 151 | 130.3333 | 0.6 | 115 | 129 | 151 | 130.3333 | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-048 | Project_028_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Compatibility | Person_542 | 2015-04-08 | 2016-09-19 01:00 | 0.05 | 9.3941 | 0.93941 | Accept | 0.05 | 9.3941 | 0.93941 | H2 | 4 | Stable | 0.5 | 109 | 125 | 146 | 125.8333 | 0.5 | 109 | 125 | 146 | 125.8333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Governance and Export Rules | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 0.93941 | 0.23485 | Transfer | 0.25 | 0.93941 | 0.23485 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence and missing info | Person_727 | 2015-11-25 01:00 | 2016-09-19 01:00 | 0.3 | 2.1606 | 0.43213 | Accept | 0.3 | 2.1606 | 0.43213 | H2 | 4 | Stable | 0.9 | 83 | 122 | 160 | 121.8333 | 0.9 | 83 | 122 | 160 | 121.8333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 01:00 | 2016-10-20 01:00 | 0.2 | 0.034059 | 0.0034059 | Accept | 0.2 | 0.034059 | 0.0034059 | H2 | 4 | Stable | 0.8 | 91 | 138 | 146 | 131.5 | 0.8 | 91 | 138 | 146 | 131.5 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-002 | Project_028_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Record / Replay feature | Person_499 | 2014-03-23 | 2016-09-19 01:00 | 0.1 | 0.35539 | 0.17769 | Accept | 0.05 | 0.35539 | 0.088847 | H2 | 4 | Stable | 0.6 | 85 | 130 | 149 | 125.6667 | 0.6 | 85 | 130 | 149 | 125.6667 | 0 | 50 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk005 | Project_002_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2014-06-14 | 2016-08-08 | 0.3 | 0.035539 | 0.010662 | Avoid | 0.3 | 0.035539 | 0.010662 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk008 | Project_002_Risk008 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2014-08-20 | 2016-08-07 | 0.1 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | -100 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk009 | Project_002_Risk009 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2014-06-14 | 2016-08-07 | 0.1 | 0.01925 | 0.001925 | Avoid | 0.1 | 0.01925 | 0.001925 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | RISK012 | Project_002_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Resourcing Suitably Qualified and experienced staff availability | Person_650 | 2015-11-21 | 2016-08-07 | 0.2 | 0.05627 | 0.011254 | Reduce | 0.2 | 0.05627 | 0.011254 | H3 | 3 | Stable | 0.7 | 94 | 135 | 157 | 131.8333 | 0.4 | 1 | 56 | 60 | 47.5 | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk004 | Project_002_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability of Test Equipment | Person_133 | 2014-03-26 | 2016-08-08 | 0.2 | 0.081443 | 0.016289 | Avoid | 0.2 | 0.081443 | 0.016289 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk006 | Project_002_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Additional Pressure Testing | Person_650 | 2014-06-14 | 2016-08-08 | 0.25 | 0.035539 | 0.0088847 | Avoid | 0.25 | 0.035539 | 0.0088847 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk011 | Project_002_Risk011 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Testing | Person_175 | 2014-06-29 | 2016-08-07 | 0.41 | 0.071669 | 0.029384 | Reduce | 0.1 | 0.0088847 | 0.00088847 | H3 | 3 | Stable | 0.6 | 118 | 136 | 144 | 134.3333 | 0.3 | 25 | 45 | 68 | 45.5 | 87.6032 | 75.6098 | 1 | 54.8302
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-010 | Project_005_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Risk that required resources (people and rigs) will not be available as required due to other projects/bids (Customer & Internal) | Person_470 | 2011-11-11 01:00 | 2016-07-20 | 0.25 | 3.9852 | 0.9963 | Reduce | 0.1 | 3.9852 | 0.39852 | H3 | 3 | Stable | 0.9 | 102 | 130 | 160 | 130.3333 | 0.4 | 3 | 42 | 62 | 38.8333 | 0 | 60 | 1 | 1.8
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-034 | Project_005_Risk-034 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project delay causes cost impact to project | Person_470 | 2011-12-02 01:00 | 2016-08-18 01:00 | 0.5 | 16.3745 | 8.1873 | Reduce | 0.4 | 16.3745 | 6.5498 | H2 | 4 | Stable | 0.9 | 98 | 130 | 142 | 126.6667 | 0.2 | 37 | 58 | 74 | 57.1667 | 0 | 20 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-060 | Project_005_Risk-060 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Technical Acceptance may be more difficult than anticipated | Person_470 | 2014-06-11 | 2016-07-20 | 0.5 | 1.6266 | 0.8133 | Reduce | 0.3 | 1.6266 | 0.48798 | H3 | 3 | Stable | 0.7 | 90 | 138 | 146 | 131.3333 | 0.1 | 36 | 58 | 78 | 57.6667 | 0 | 40 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK007 | Project_004_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 01:00 | 2016-03-21 01:00 | 0.2 | 0.15317 | 0.030633 | Reduce | 0.2 | 0.10883 | 0.021765 | H3 | 3 | Stable | 0.9 | 102 | 131 | 160 | 131 | 0.1 | 26 | 55 | 65 | 51.8333 | 28.9481 | 0 | 1 | 17.3689
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK004 | Project_004_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 0.2 | 0.14752 | 0.029504 | Avoid | 0.2 | 0.14752 | 0.029504 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK003 | Project_004_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-05-24 | 2016-03-21 01:00 | 0.2 | 0.060459 | 0.012092 | Avoid | 0.2 | 0.060459 | 0.012092 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK006 | Project_004_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2014-11-19 01:00 | 2016-03-21 01:00 | 0.1 | 0.049978 | 0.0049978 | Avoid | 0.1 | 0.049978 | 0.0049978 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK005 | Project_004_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK002 | Project_004_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 0.5 | 0.15317 | 0.076583 | Avoid | 0.5 | 0.15317 | 0.076583 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.5 | 104 | 129 | 158 | 129.6667 | 0.2 | 22 | 58 | 78 | 55.3333 | 25.8065 | 20 | 0 | 15.4839
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 01:00 | 2016-10-19 01:00 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.6 | 82 | 122 | 148 | 119.6667 | 0.1 | 15 | 51 | 76 | 49.1667 | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 01:00 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 01:00 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | EMC Testing | Person_070 | 2016-04-22 | 2016-09-19 01:00 | 0.35 | 0 | 0 | Accept | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.5 | 119 | 127 | 146 | 128.8333 | 0.5 | 119 | 127 | 146 | 128.8333 |  | 42.8571 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK324 | Project_037_RISK324 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Delay to integration | Person_330 | 2015-05-24 | 2016-05-15 | 0.5 | 1.4926 | 0.74629 | Reduce | 0.3 | 1.4926 | 0.44777 | H2 | 4 | Stable | 0.7 | 111 | 124 | 145 | 125.3333 | 0.1 | 36 | 46 | 68 | 48 | 0 | 40 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-10-21 01:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.8 | 118 | 121 | 159 | 126.8333 | 0.4 | 35 | 42 | 68 | 45.1667 | 47 | 0 | 0 | 28.2
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-11-20 01:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 4.7805 | 0.9561 | H3 | 3 | Stable | [10 empty] | 0 | 60 | 1 | 1.8
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_542 | 2015-01-22 01:00 | 2017-08-20 01:00 | 0.35 | 10.7826 | 4.3131 | Accept | 0.2 | 10.7826 | 4.3131 | H2 | 4 | Stable | 0.6 | 98 | 125 | 143 | 123.5 | 0.6 | 98 | 125 | 143 | 123.5 | 0 | 42.8571 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK117 | Project_037_RISK117 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Data Comms Availability or Performance | Person_334 | 2015-05-24 | 2016-11-20 01:00 | 0.35 | 3.2401 | 1.134 | Transfer | 0.1 | 3.2401 | 0.32401 | H3 | 3 | Stable | [10 empty] | 0 | 71.4286 | 1 | 2.1429
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2016-08-19 01:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.4 | 3.187 | 1.2748 | H2 | 4 | Stable | 0.8 | 94 | 131 | 150 | 128 | 0.2 | 8 | 53 | 60 | 46.6667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 0.4 | 9.139 | 3.6556 | Avoid | 0.2 | 9.139 | 1.8278 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK226 | Project_038_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Capacity to support enhancements or fixes post delivery | Person_330 | 2015-11-21 01:00 | 2017-05-22 | 0.5 | 13.9332 | 6.9666 | Avoid | 0.1 | 13.9332 | 1.3933 | H3 | 3 | Improving | [10 empty] | 0 | 80 | 1 | 2.4
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 0.5 | 13.7833 | 6.8917 | Avoid | 0.2 | 13.7833 | 2.7567 | H3 | 3 | Stable | [10 empty] | 0 | 60 | 1 | 1.8
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_070 | 2016-06-23 | 2016-08-21 01:00 | 0.4 | 5.6182 | 4.4946 | Accept | 0.2 | 5.6182 | 4.4946 | H2 | 4 | Stable | 0.8 | 114 | 140 | 146 | 136.6667 | 0.8 | 114 | 140 | 146 | 136.6667 | 0 | 50 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK187 | Project_038_RISK187 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Technical Publications | Person_671 | 2015-07-22 | 2016-06-22 | 0.5 | 4.6444 | 2.3222 | Avoid | 0.3 | 4.6444 | 1.3933 | H2 | 4 | Worsening | [10 empty] | 0 | 40 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK220 | Project_038_RISK220 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Lack of Resources needed to deliver the programme | Person_330 | 2013-09-20 01:00 | 2015-10-20 01:00 | 0.5 | 45.6947 | 22.8474 | Avoid | 0.1 | 18.1281 | 1.8128 | H2 | 4 | Stable | [10 empty] | 60.3279 | 80 | 0 | 36.1967
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-09-20 01:00 | 0.3 | 5.5433 | 1.663 | Reduce | 0.2 | 5.5433 | 1.1087 | H3 | 3 | Stable | 0.6 | 99 | 121 | 153 | 122.6667 | 0.3 | 24 | 41 | 65 | 42.1667 | 0 | 33.3333 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Stable | [10 empty] | 0 | 75 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK227 | Project_038_RISK227 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Verification and Acceptance of Customer Furnished Equipmnet Goods & Services | Person_330 | 2015-02-21 01:00 | 2016-05-22 | 0.6 | 6.4422 | 3.8653 | Avoid | 0.2 | 6.4422 | 1.2884 | H3 | 3 | Stable | [10 empty] | 0 | 66.6667 | 1 | 2
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Material/Labour Overspend | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 6.7418 | 1.6855 | Accept | 0.5 | 6.7418 | 1.6855 | H2 | 4 | Stable | 0.8 | 99 | 127 | 154 | 126.8333 | 0.8 | 99 | 127 | 154 | 126.8333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 0.5 | 5.4834 | 1.0967 | Accept | 0.5 | 5.4834 | 0.43867 | H2 | 4 | Stable | 0.7 | 90 | 126 | 147 | 123.5 | 0.7 | 90 | 126 | 147 | 123.5 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 | 2020-08-20 | 0.5 | 5.3935 | 1.0787 | Accept | 0.5 | 5.3935 | 0.21574 | H2 | 4 | Stable | 0.9 | 115 | 125 | 141 | 126 | 0.9 | 115 | 125 | 141 | 126 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK390 | Project_038_RISK390 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component shock failure | Person_531 | 2016-01-17 01:00 | 2016-06-23 | 0.2 | 17.1093 | 3.4219 | -- | 0.2 | 17.1093 | 3.4219 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 0.125 | 232.2192 | 29.0274 | -- | 0.125 | 156.8004 | 19.6 | H2 | 4 | Stable | [10 empty] | 32.4774 | 0 | 0 | 19.4865
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2016-12-08 01:00 | 0.41 | 8.9142 | 2.6743 | Accept | 0.41 | 6.6669 | 2.0001 | H2 | 4 | Stable | 0.8 | 104 | 138 | 151 | 134.5 | 0.8 | 104 | 138 | 151 | 134.5 | 25.2101 | 0 | 0 | 15.126
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK232 | Project_038_RISK232 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Integration more complex than expected | Person_531 | 2015-11-21 01:00 | 2016-08-21 01:00 | 0.3 | 27.7165 | 8.3149 | Reduce | 0.185 | 27.7165 | 5.1275 | H2 | 4 | Improving | 0.6 | 84 | 135 | 142 | 127.6667 | 0.4 | 18 | 46 | 66 | 44.6667 | 0 | 38.3333 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 0.3 | 26.9674 | 8.0902 | Avoid | 0.3 | 14.9819 | 4.4946 | H2 | 4 | Stable | [10 empty] | 44.4444 | 0 | 0 | 26.6667
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-05-16 | 0.5 | 26.9674 | 13.4837 | Avoid | 0.0265 | 26.9674 | 0.71464 | H2 | 4 | Worsening | [10 empty] | 0 | 94.7 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-015 | Project_023_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Illness | Person_371 | 2015-04-09 | 2016-12-11 01:00 | 0.25 | 4.5695 | 0.45695 | Accept | 0.25 | 4.5695 | 0.45695 | H2 | 4 | Stable | 0.8 | 120 | 135 | 155 | 135.8333 | 0.8 | 120 | 135 | 155 | 135.8333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-016 | Project_023_Risk-016 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Damage to equipment (Unable to replace due to obsolescence) | Person_703 | 2015-10-22 01:00 | 2016-06-22 | 0.3 | 5.3935 | 1.3484 | Accept | 0.3 | 5.3935 | 1.3484 | H2 | 4 | Stable | 0.7 | 96 | 124 | 157 | 124.8333 | 0.7 | 96 | 124 | 157 | 124.8333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 20:00 | 2019-08-20 20:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.7 | 90 | 139 | 160 | 134.3333 | 0.1 | 22 | 51 | 63 | 48.1667 | 83.3333 | 88.8889 | 1 | 52.6667
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 20:00 | 2019-08-20 20:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.9 | 120 | 133 | 154 | 134.3333 | 0.1 | 21 | 57 | 72 | 53.5 | 72 | 0 | 0 | 43.2
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 20:00 | 2019-08-20 20:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.8 | 111 | 129 | 141 | 128 | 0.2 | 6 | 45 | 64 | 41.6667 | 47.7391 | 0 | 0 | 28.6435
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 20:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.9 | 107 | 126 | 157 | 128 | 0.1 | 22 | 44 | 62 | 43.3333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 0.4 | 9.139 | 3.6556 | Avoid | 0.2 | 9.139 | 1.8278 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-10-21 01:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.6 | 101 | 140 | 142 | 133.8333 | 0.3 | 3 | 57 | 73 | 50.6667 | 47 | 0 | 0 | 28.2
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK226 | Project_038_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Capacity to support enhancements or fixes post delivery | Person_330 | 2015-11-21 01:00 | 2017-05-22 | 0.5 | 13.9332 | 6.9666 | Avoid | 0.1 | 13.9332 | 1.3933 | H3 | 3 | Improving | [10 empty] | 0 | 80 | 1 | 2.4
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-11-20 01:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 0.5 | 13.7833 | 6.8917 | Avoid | 0.2 | 13.7833 | 2.7567 | H3 | 3 | Stable | [10 empty] | 0 | 60 | 1 | 1.8
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK117 | Project_037_RISK117 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Data Comms Availability or Performance | Person_334 | 2015-05-24 | 2016-11-20 01:00 | 0.35 | 3.2401 | 1.134 | Transfer | 0.1 | 3.2401 | 0.32401 | H3 | 3 | Stable | [10 empty] | 0 | 71.4286 | 1 | 2.1429
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK187 | Project_038_RISK187 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Technical Publications | Person_671 | 2015-07-22 | 2016-08-20 01:00 | 0.5 | 4.6444 | 2.3222 | Avoid | 0.3 | 3.296 | 0.98881 | H2 | 4 | Worsening | [10 empty] | 29.0322 | 40 | 0 | 17.4193
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK220 | Project_038_RISK220 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Lack of Resources needed to deliver the programme | Person_330 | 2013-09-20 01:00 | 2015-10-20 01:00 | 0.5 | 45.6947 | 22.8474 | Avoid | 0.1 | 9.5884 | 0.95884 | H2 | 4 | Stable | [10 empty] | 79.0164 | 80 | 0 | 47.4098
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2016-08-19 01:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.3 | 3.187 | 0.9561 | H2 | 4 | Stable | 0.5 | 115 | 139 | 150 | 136.8333 | 0.2 | 2 | 53 | 75 | 48.1667 | 0 | 25 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-09-20 01:00 | 0.3 | 5.5433 | 1.663 | Reduce | 0.1 | 5.5433 | 0.55433 | H3 | 3 | Improving | 0.6 | 87 | 138 | 143 | 130.3333 | 0.2 | 33 | 41 | 79 | 46 | 0 | 66.6667 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Stable | [10 empty] | 0 | 75 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK227 | Project_038_RISK227 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Verification and Acceptance of Customer Furnished Equipmnet Goods & Services | Person_330 | 2015-02-21 01:00 | 2016-08-20 01:00 | 0.6 | 6.4422 | 3.8653 | Avoid | 0.2 | 6.4422 | 1.2884 | H3 | 3 | Stable | [10 empty] | 0 | 66.6667 | 1 | 2
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 0.5 | 4.4946 | 1.1236 | Accept | 0.5 | 4.4946 | 1.1236 | H2 | 4 | Improving | 0.6 | 81 | 139 | 151 | 131.3333 | 0.6 | 81 | 139 | 151 | 131.3333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Suppliers | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 6.7418 | 1.6855 | Accept | 0.15 | 6.7418 | 1.0113 | H2 | 4 | Stable | 0.8 | 95 | 128 | 153 | 126.6667 | 0.8 | 95 | 128 | 153 | 126.6667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 5.4834 | 1.0967 | Accept | 0.2 | 5.4834 | 0.82251 | H2 | 4 | Stable | 0.5 | 96 | 139 | 149 | 133.5 | 0.5 | 96 | 139 | 149 | 133.5 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 0.125 | 232.2192 | 29.0274 | -- | 0.4 | 36.9453 | 14.7781 | H2 | 4 | Stable | [10 empty] | 84.0903 | -220 | 0 | 50.4542
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Local customer Engineers in country | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 8.9142 | 2.6743 | Accept | 0.1 | 6.6669 | 2.0001 | H2 | 4 | Stable | 0.6 | 89 | 128 | 143 | 124 | 0.6 | 89 | 128 | 143 | 124 | 25.2101 | 0 | 0 | 15.126
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK232 | Project_038_RISK232 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Integration more complex than expected | Person_531 | 2015-11-21 01:00 | 2016-08-21 01:00 | 0.3 | 27.7165 | 8.3149 | Reduce | 0.185 | 13.1091 | 2.4252 | H3 | 3 | Improving | 0.6 | 96 | 129 | 144 | 126 | 0.1 | 32 | 54 | 62 | 51.6667 | 52.7027 | 38.3333 | 1 | 32.7716
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 0.3 | 26.9674 | 8.0902 | Avoid | 0.3 | 14.9819 | 4.4946 | H2 | 4 | Stable | [10 empty] | 44.4444 | 0 | 0 | 26.6667
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2016-10-20 01:00 | 0.5 | 26.9674 | 13.4837 | Avoid | 0.1 | 0 | 0 | H2 | 4 | Worsening | [10 empty] | 100 | 80 | 0 | 60
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence | Person_455 | 2016-05-23 | 2020-05-23 | 0.3 | 5.3935 | 1.3484 | Accept | 0.3 | 5.3935 | 1.3484 | H2 | 4 | Stable | 0.9 | 118 | 123 | 145 | 125.8333 | 0.9 | 118 | 123 | 145 | 125.8333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Consumables | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 17.9783 | 3.5957 | Accept | 0.2 | 17.9783 | 3.5957 | H2 | 4 | Stable | 0.5 | 119 | 121 | 160 | 127.1667 | 0.5 | 119 | 121 | 160 | 127.1667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 7. Finance | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 2.3457 | 0.11728 | Accept | 0.2 | 2.3457 | 0.023457 | H2 | 4 | Stable | 0.9 | 80 | 125 | 141 | 120.1667 | 0.9 | 80 | 125 | 141 | 120.1667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 23.6737 | 11.8369 | Accept | 0.15 | 52.0822 | 23.437 | H2 | 4 | Stable | 0.7 | 86 | 133 | 144 | 127 | 0.7 | 86 | 133 | 144 | 127 | -120 | 0 | 0 | -72
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-043 | Project_008_Risk-043 | Opportunitity | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Joint courseware and tech pubs team | Person_280 | 2014-11-21 01:00 | 2017-05-21 | 0.5 | 28.2191 | 14.1096 | -- | 0.8 | 13.2573 | 10.6058 | H1 | 5 | Stable | [10 empty] | 53.0201 | -60 | 0 | 31.8121
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 9.3748 | 4.6874 | Accept | 0.2 | 9.3748 | 3.7499 | H2 | 4 | Stable | 0.8 | 87 | 131 | 157 | 128 | 0.8 | 87 | 131 | 157 | 128 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-059 | Project_008_Risk-059 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Project Resource Efficencies | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 0.2 | 21.6852 | 4.337 | -- | 0.2 | 21.6852 | 4.337 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport Routes | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 15.8141 | 3.9535 | Accept | 0.15 | 15.8141 | 3.9535 | H2 | 4 | Stable | 0.8 | 116 | 129 | 152 | 130.6667 | 0.8 | 116 | 129 | 152 | 130.6667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Internal Quality Issues | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 1.2105 | 1.2105 | Accept | 0.2 | 1.2105 | 0.36316 | H2 | 4 | Stable | 0.9 | 97 | 123 | 153 | 123.6667 | 0.9 | 97 | 123 | 153 | 123.6667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk017 | Project_042_Risk017 | Threat | Financial Contingency | Open | H2 | 4 | 6. Contractual/Legal | Liquidated Damages | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 13.3529 | 6.6765 | Accept | 0.4 | 13.3529 | 6.6765 | H2 | 4 | Stable | 0.5 | 98 | 133 | 153 | 130.5 | 0.5 | 98 | 133 | 153 | 130.5 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK024 | Project_012_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component Repair & test costs | Person_359 | 2015-04-04 | 2016-04-12 | 0.7 | 0.84985 | 0.5949 | -- | 0.18 | 0.84985 | 0.15297 | H2 | 4 | Improving | [10 empty] | 0 | 74.2857 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 0.5 | 9.2728 | 4.6364 | Reduce | 0.3 | 9.2728 | 2.7819 | H2 | 4 | Stable | 0.9 | 96 | 136 | 142 | 130.3333 | 0.4 | 14 | 48 | 61 | 44.5 | 0 | 40 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 0.3 | 8.7814 | 2.6344 | Reduce | 0.2 | 8.7832 | 1.7566 | H3 | 3 | Stable | 0.7 | 106 | 140 | 151 | 136.1667 | 0.1 | 11 | 54 | 72 | 49.8333 | -0.021119 | 33.3333 | 0 | -0.012672
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Repairs | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 108.3186 | 32.4956 | Accept | 0.25 | 108.3186 | 32.4956 | H2 | 4 | Stable | 0.5 | 119 | 136 | 149 | 135.3333 | 0.5 | 119 | 136 | 149 | 135.3333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Delay of processing | Person_306 | 2016-01-13 01:00 | 2019-08-21 01:00 | 0.15 | 26.3497 | 3.9525 | Reduce | 0.15 | 26.3497 | 3.9525 | H3 | 3 | Improving | 0.9 | 103 | 139 | 151 | 135 | 0.4 | 12 | 58 | 76 | 53.3333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-200 | Project_027_Risk-200 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Sucession Planning for key team members | Person_060 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.2 | 7.3175 | 1.4635 | Reduce | 0.05 | 7.3175 | 0.36588 | H2 | 4 | Stable | 0.6 | 87 | 130 | 159 | 127.6667 | 0.2 | 26 | 47 | 69 | 47.1667 | 0 | 75 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-189 | Project_027_Risk-189 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Major Component obsolescence | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 8.3972 | 2.5191 | Reduce | 0.25 | 8.3972 | 2.0993 | H2 | 4 | Stable | 0.6 | 98 | 125 | 150 | 124.6667 | 0.2 | 34 | 49 | 79 | 51.5 | 0 | 16.6667 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-201 | Project_027_Risk-201 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Transition into Support | Person_027 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0.5 | 68.3768 | 34.1884 | Reduce | 0.05 | 38.387 | 1.9193 | H2 | 4 | Stable | 0.9 | 92 | 121 | 156 | 122 | 0.1 | 20 | 45 | 70 | 45 | 43.8597 | 90 | 0 | 26.3158
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk016 | Project_042_Risk016 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport/Delivery Speed | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 13.2195 | 1.5863 | Accept | 0.1 | 13.2195 | 1.5863 | H2 | 4 | Stable | 0.9 | 116 | 135 | 158 | 135.6667 | 0.9 | 116 | 135 | 158 | 135.6667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Country Stability | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 20.0332 | 2.0033 | Accept | 0.4 | 20.0332 | 2.0033 | H2 | 4 | Stable | 0.8 | 98 | 131 | 142 | 127.3333 | 0.8 | 98 | 131 | 142 | 127.3333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-193 | Project_027_Risk-193 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | A greater number of arising technical queries | Person_110 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 13.7953 | 4.1386 | Reduce | 0.05 | 13.7953 | 0.68977 | H3 | 3 | Stable | 0.8 | 94 | 129 | 149 | 126.5 | 0.4 | 23 | 49 | 69 | 48 | 0 | 83.3333 | 1 | 2.5
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 16.1945 | 2.4292 | Accept | 0.1 | 16.1945 | 2.4292 | H2 | 4 | Stable | 0.8 | 117 | 136 | 148 | 134.8333 | 0.8 | 117 | 136 | 148 | 134.8333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 35.9878 | 21.5927 | Accept | 0.2 | 15.5947 | 0.77974 | H2 | 4 | Stable | 0.8 | 101 | 122 | 146 | 122.5 | 0.8 | 101 | 122 | 146 | 122.5 | 56.6667 | 0 | 0 | 34
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk010 | Project_002_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability | Person_357 | 2014-06-14 | 2016-08-07 | 0.1 | 27.5907 | 2.7591 | Accept | 0.1 | 27.5907 | 2.7591 | H3 | 3 | Worsening | 0.8 | 96 | 126 | 157 | 126.1667 | 0.8 | 96 | 126 | 157 | 126.1667 | 0 | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk002 | Project_002_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Transducer Element Failures | Person_650 | 2014-06-04 | 2016-08-07 | 0.5 | 19.1935 | 2.879 | Accept | 0.25 | 19.1935 | 2.879 | H2 | 4 | Worsening | 0.6 | 103 | 138 | 142 | 132.8333 | 0.6 | 103 | 138 | 142 | 132.8333 | 0 | 50 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK118 | Project_037_RISK118 | Threat | Management Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Product does not deliver the inputs/depdencies required by the Project by the req'd dates | Person_330 | 2015-02-23 21:00 | 2015-12-19 21:00 | 0.4 | 19.1935 | 1.9194 | Accept | 0.4 | 19.1935 | 1.9194 | H2 | 4 | Worsening | 0.5 | 110 | 138 | 147 | 134.8333 | 0.5 | 110 | 138 | 147 | 134.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 | 2017-08-20 | 0.25 | 7.7469 | 1.9367 | Reduce | 0.25 | 7.7469 | 1.9367 | H3 | 3 | Stable | 0.5 | 87 | 137 | 159 | 132.3333 | 0.2 | 4 | 58 | 74 | 51.6667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-131 | Project_032_Risk-131 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Failure | Person_360 | 2012-08-21 | 2017-07-20 | 0.3 | 15.6782 | 4.7035 | Transfer | 0.3 | 15.6782 | 4.7035 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 | 0.05 | 11.3437 | 0.56718 | Reduce | 0.05 | 11.3437 | 0.56718 | H3 | 3 | Stable | 0.9 | 83 | 124 | 143 | 120.3333 | 0.1 | 35 | 59 | 61 | 55.3333 | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 | 2017-03-22 | 0.05 | 87.6137 | 4.3807 | Reduce | 0.05 | 87.6137 | 4.3807 | H3 | 3 | Stable | 0.5 | 92 | 138 | 144 | 131.3333 | 0.4 | 21 | 44 | 76 | 45.5 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK269 | Project_038_RISK269 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software Development | Resource issue in card to provide real time data due to adding 2nd interface | Person_303 | 2015-07-22 | 2016-08-14 | 0.8 | 5.8286 | 0.58286 | Accept | 0.8 | 5.8286 | 0.58286 | H1 | 5 | Stable | 0.6 | 116 | 136 | 158 | 136.3333 | 0.6 | 116 | 136 | 158 | 136.3333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 | 2017-08-20 | 0.3 | 53.0293 | 15.9088 | Reduce | 0.3 | 53.0293 | 15.9088 | H3 | 3 | Worsening | 0.6 | 81 | 133 | 160 | 128.8333 | 0.1 | 38 | 46 | 64 | 47.6667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance | Person_240 | 2015-12-22 01:00 | 2016-08-14 | 0.25 | 16.7112 | 15.04 | Accept | 0.25 | 16.7112 | 15.04 | H2 | 4 | Stable | 0.9 | 117 | 134 | 147 | 133.3333 | 0.9 | 117 | 134 | 147 | 133.3333 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-09-20 01:00 | 0.25 | 7.1867 | 3.5934 | Accept | 0.25 | 7.1867 | 3.5934 | H2 | 4 | Stable | 0.8 | 90 | 121 | 160 | 122.3333 | 0.8 | 90 | 121 | 160 | 122.3333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Commercial aspects agreement | Person_480 | 2013-08-21 | 2016-05-22 | 0.02 | 4.8296 | 0.096593 | Transfer | 0.02 | 4.8296 | 0.096593 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK004 | Project_010_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Export License | Person_359 | 2015-02-18 01:00 | 2017-08-20 01:00 | 0.8 | 0.18482 | 0.14786 | Reduce | 0.8 | 0.18482 | 0.14786 | H1 | 5 | Worsening | 0.7 | 102 | 140 | 149 | 135.1667 | 0.1 | 2 | 41 | 61 | 37.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 | 2017-08-20 | 0.1 | 34.363 | 3.4363 | Avoid | 0.1 | 34.363 | 3.4363 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 | 2017-08-20 | 0.48 | 33.2985 | 15.9833 | Avoid | 0.48 | 33.2985 | 15.9833 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 01:00 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.5 | 94 | 121 | 149 | 121.1667 | 0.4 | 37 | 58 | 70 | 56.5 | 0 | 40 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK152 | Project_038_RISK152 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Test Equipment Costs | Person_640 | 2015-06-24 | 2016-05-22 | 0.2 | 4.4221 | 2.2111 | Accept | 0.08 | 4.4221 | 2.2111 | H3 | 3 | Stable | 0.7 | 81 | 133 | 158 | 128.5 | 0.7 | 81 | 133 | 158 | 128.5 | 0 | 60 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-126 | Project_032_Risk-126 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supply Chain - Delivery to Contract Requirement | Person_590 | 2012-08-21 | 2016-08-20 | 0.3 | 25.3619 | 7.6086 | Reduce | 0.3 | 25.3619 | 7.6086 | H2 | 4 | Stable | 0.6 | 112 | 126 | 158 | 129 | 0.2 | 25 | 52 | 68 | 50.1667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.7 | 0.92411 | 0.64688 | Reduce | 0.3 | 0.36965 | 0.11089 | H2 | 4 | Stable | 0.7 | 97 | 133 | 160 | 131.5 | 0.3 | 15 | 59 | 71 | 53.6667 | 60 | 57.1429 | 0 | 36
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK154 | Project_038_RISK154 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production Tools and Jigs | Person_640 | 2015-06-24 | 2016-07-16 | 0.3 | 0.20788 | 0.068599 | Accept | 0.3 | 0.20788 | 0.068599 | H2 | 4 | Stable | 0.6 | 98 | 131 | 143 | 127.5 | 0.6 | 98 | 131 | 143 | 127.5 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 01:00 | 2016-04-21 | 0.5 | 4.0661 | 2.033 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.8 | 119 | 139 | 153 | 138 | 0.1 | 17 | 50 | 69 | 47.6667 | 0 | 90 | 1 | 2.7
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK160 | Project_038_RISK160 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Low noise Requirement | Person_017 | 2016-02-21 01:00 | 2016-07-21 | 0.1 | 3.1818 | 1.5909 | Accept | 0.1 | 3.1818 | 1.5909 | H3 | 3 | Stable | 0.5 | 119 | 130 | 152 | 131.8333 | 0.5 | 119 | 130 | 152 | 131.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.3 | 0.46206 | 0.13862 | H2 | 4 | Improving | 0.8 | 112 | 126 | 151 | 127.8333 | 0.2 | 1 | 41 | 61 | 37.6667 | 58.3333 | 50 | 0 | 35
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK163 | Project_038_RISK163 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Additional Chamber trials | Person_531 | 2015-09-21 01:00 | 2016-09-20 01:00 | 0.25 | 1.1089 | 0.88715 | Accept | 0.25 | 0.73929 | 0.44357 | H2 | 4 | Stable | 0.6 | 85 | 132 | 156 | 128.1667 | 0.6 | 85 | 132 | 156 | 128.1667 | 33.3333 | 0 | 0 | 20
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 01:00 | 2017-08-20 01:00 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.5 | 119 | 131 | 159 | 133.6667 | 0.1 | 2 | 47 | 71 | 43.5 | 0 | 50 | 1 | 1.5
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.6 | 94 | 136 | 147 | 130.8333 | 0.3 | 17 | 58 | 64 | 52.1667 | 0 | 25 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Stable | 0.7 | 92 | 138 | 158 | 133.6667 | 0.2 | 3 | 41 | 66 | 38.8333 | 0 | 40 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Worsening | [10 empty] | 0 | 37.5 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_468 | 2016-11-20 01:00 | 2018-11-20 01:00 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.1 | 6.431 | 0.6431 | H3 | 3 | Stable | 0.7 | 105 | 137 | 147 | 133.3333 | 0.2 | 30 | 54 | 74 | 53.3333 | -47.0588 | 33.3333 | 1 | -27.2353
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK84 | Project_010_RISK84 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality issues (for the future) | Person_359 | 2012-09-20 01:00 | 2017-08-20 01:00 | 0.6 | 2.033 | 1.2198 | Reduce | 0.25 | 0.92411 | 0.23103 | H2 | 4 | Stable | 0.8 | 82 | 123 | 160 | 122.3333 | 0.4 | 19 | 52 | 69 | 49.3333 | 54.5455 | 58.3333 | 0 | 32.7273
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R81 | Project_041_R81 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Re-imaging of PC's - additional material | Person_515 | 2016-11-20 01:00 | 2017-10-21 01:00 | 0.5 | 0.21008 | 0.10504 | Avoid | 0.5 | 0.21008 | 0.10504 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 0.3 | 1.8482 | 0.55447 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.5 | 105 | 121 | 159 | 124.6667 | 0.3 | 3 | 55 | 60 | 47.1667 | 0 | 33.3333 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 01:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.8 | 97 | 122 | 149 | 122.3333 | 0.2 | 36 | 50 | 67 | 50.5 | 90 | 75 | 1 | 56.25
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R85 | Project_041_R85 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Go to Offshore initiative | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 0.15 | 7.7172 | 1.1576 | -- | 0.15 | 7.7172 | 1.1576 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_368 | 2016-11-20 01:00 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.9 | 82 | 134 | 154 | 128.6667 | 0.3 | 28 | 42 | 62 | 43 | 0 | 50 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R43 | Project_041_R43 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Procurement - Component and Supplier Leadtime | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 0.25 | 10.9327 | 2.7332 | Reduce | 0.15 | 10.9327 | 1.6399 | H2 | 4 | Stable | 0.8 | 94 | 136 | 155 | 132.1667 | 0.4 | 16 | 51 | 71 | 48.5 | 0 | 40 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 0.75 | 10.7184 | 8.0388 | Reduce | 0.75 | 5.3592 | 4.0194 | H1 | 5 | Worsening | 0.7 | 94 | 133 | 142 | 128 | 0.4 | 27 | 49 | 66 | 48.1667 | 50 | 0 | 0 | 30
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R86 | Project_041_R86 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sharing Attrition Stock with Warranty Spares pool | Person_501 | 2016-11-20 01:00 | 2018-05-22 | 0.5 | 3.1083 | 1.5542 | Exploit | 0.5 | 3.1083 | 1.5542 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 20:00 | 2019-08-07 | 0.61 | 1.9722 | 0.98609 | Accept | 0.61 | 1.9722 | 0.98609 | H1 | 5 | Stable | 0.8 | 119 | 132 | 155 | 133.6667 | 0.8 | 119 | 132 | 155 | 133.6667 | 0 | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK219 | Project_024_RISK219 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | STTE additional work | Person_289 | 2016-09-20 01:00 | 2017-07-21 | 0.5 | 7.0313 | 3.5156 | Accept | 0.5 | 7.0313 | 3.5156 | H1 | 5 | Worsening | 0.8 | 102 | 132 | 153 | 130.5 | 0.8 | 102 | 132 | 153 | 130.5 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2016-11-20 01:00 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.05 | 0.68598 | 0.034299 | H3 | 3 | Stable | 0.7 | 89 | 133 | 156 | 129.5 | 0.2 | 35 | 43 | 64 | 45.1667 | 0 | 80 | 1 | 2.4
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK118 | Project_037_RISK118 | Threat | Management Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Product does not deliver the inputs/depdencies required by the Project by the req'd dates | Person_330 | 2015-02-23 20:00 | 2015-12-19 20:00 | 0.4 | 3.7514 | 0.37514 | Accept | 0.4 | 3.7514 | 0.37514 | H2 | 4 | Worsening | 0.7 | 99 | 126 | 151 | 125.6667 | 0.7 | 99 | 126 | 151 | 125.6667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R29 | Project_041_R29 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Attrition | Person_515 | 2016-11-20 01:00 | 2018-05-22 | 0.1 | 3.6014 | 0.36014 | Reduce | 0.05 | 3.6014 | 0.18007 | H3 | 3 | Stable | 0.5 | 84 | 135 | 160 | 130.6667 | 0.1 | 35 | 49 | 64 | 49.1667 | 0 | 50 | 1 | 1.5
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2016-11-20 01:00 | 2017-07-21 | 0.1 | 21.8655 | 2.1865 | Reduce | 0.05 | 21.8655 | 1.0933 | H2 | 4 | Stable | 0.6 | 110 | 127 | 148 | 127.6667 | 0.3 | 18 | 51 | 66 | 48 | 0 | 50 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Stable | 0.9 | 116 | 128 | 155 | 130.5 | 0.4 | 2 | 57 | 70 | 50 | 0 | 60 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 01:00 | 2016-10-19 01:00 | 0.25 | 0.6088 | 0.1522 | Accept | 0.25 | 0.6088 | 0.1522 | H2 | 4 | Stable | 0.8 | 90 | 135 | 156 | 131 | 0.8 | 90 | 135 | 156 | 131 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Unidentified Change Requests | Person_693 | 2016-11-20 01:00 | 2017-09-20 01:00 | 0.5 | 1.2005 | 0.60023 | Reduce | 0.1 | 0.51019 | 0.051019 | H3 | 3 | Stable | 0.5 | 93 | 133 | 159 | 130.6667 | 0.2 | 20 | 57 | 77 | 54.1667 | 57.5001 | 80 | 1 | 36.9001
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-09-20 01:00 | 0.25 | 3.3227 | 0.83067 | Accept | 0.15 | 3.3227 | 0.83067 | H3 | 3 | Stable | 0.8 | 84 | 136 | 146 | 129 | 0.8 | 84 | 136 | 146 | 129 | 0 | 40 | 1 | 1.2
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.1 | 0.77172 | 0.077172 | H3 | 3 | Stable | 0.5 | 88 | 140 | 148 | 132.6667 | 0.4 | 15 | 54 | 65 | 49.3333 | 0 | 60 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production or Engineering | Person_359 | 2016-11-20 01:00 | 2018-05-22 | 0.15 | 1.1576 | 0.17364 | Reduce | 0.1 | 1.1576 | 0.11576 | H3 | 3 | Stable | 0.6 | 117 | 123 | 142 | 125.1667 | 0.2 | 24 | 59 | 69 | 54.8333 | 0 | 33.3333 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R13 | Project_041_R13 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Loss of key personnel | Person_359 | 2016-11-20 01:00 | 2017-08-20 01:00 | 0.5 | 0.59165 | 0.29583 | Reduce | 0.1 | 0.59165 | 0.059165 | H3 | 3 | Stable | 0.9 | 100 | 139 | 144 | 133.3333 | 0.1 | 18 | 45 | 65 | 43.8333 | 0 | 80 | 1 | 2.4
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-13 01:00 | 2017-03-21 01:00 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.5 | 98 | 131 | 145 | 127.8333 | 0.3 | 25 | 56 | 66 | 52.5 | 80 | 66.6667 | 0 | 48
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK152 | Project_038_RISK152 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Test Equipment Costs | Person_640 | 2015-06-24 | 2016-08-20 01:00 | 0.2 | 12.1398 | 8.4978 | Accept | 0.15 | 12.1398 | 8.4978 | H3 | 3 | Stable | 0.6 | 91 | 132 | 160 | 129.8333 | 0.6 | 91 | 132 | 160 | 129.8333 | 0 | 25 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_174 | 2001-05-23 | 2018-02-19 01:00 | 0.4 | 0.48559 | 0.19424 | Reduce | 0.4 | 0.48559 | 0.19424 | H2 | 4 | Stable | 0.6 | 106 | 126 | 154 | 127.3333 | 0.3 | 22 | 55 | 60 | 50.3333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-05-21 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.5 | 82 | 123 | 153 | 121.1667 | 0.3 | 30 | 53 | 73 | 52.5 | 50 | 28.5714 | 0 | 30
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-02-19 01:00 | 0.5 | 17.2826 | 8.6413 | Reduce | 0.15 | 17.2826 | 2.5924 | H2 | 4 | Worsening | 0.6 | 109 | 135 | 148 | 132.8333 | 0.2 | 31 | 57 | 74 | 55.5 | 0 | 70 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build ()/Decision Point concludes new release required | Person_470 | 2012-11-20 01:00 | 2017-05-21 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.5 | 119 | 129 | 158 | 132.1667 | 0.4 | 3 | 51 | 72 | 46.5 | 0 | 50 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_207 | 2013-09-20 01:00 | 2017-01-20 01:00 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.4 | 12.6474 | 5.059 | H2 | 4 | Stable | 0.6 | 119 | 133 | 154 | 134.1667 | 0.2 | 26 | 43 | 78 | 46 | 0 | 33.3333 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_021 | 2010-04-19 | 2017-01-19 01:00 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.7 | 115 | 137 | 145 | 134.6667 | 0.3 | 2 | 47 | 60 | 41.6667 | 0 | 50 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Release is more complicated/ delayed. | Person_470 | 2013-01-07 01:00 | 2017-02-19 01:00 | 0.5 | 4.7676 | 2.3838 | Reduce | 0.3 | 4.7676 | 1.4303 | H2 | 4 | Stable | 0.9 | 115 | 122 | 154 | 126.1667 | 0.4 | 31 | 59 | 62 | 54.8333 | 0 | 40 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 01:00 | 2017-01-19 01:00 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.9 | 103 | 137 | 157 | 134.6667 | 0.2 | 16 | 48 | 61 | 44.8333 | 0 | 33.3333 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2017-05-21 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Worsening | 0.7 | 119 | 122 | 155 | 127 | 0.4 | 15 | 47 | 77 | 46.6667 | 0 | 57.1429 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 0.2 | 1.661 | 0.33219 | Reduce | 0.2 | 1.661 | 0.33219 | H2 | 4 | Stable | 0.9 | 100 | 138 | 151 | 133.8333 | 0.1 | 36 | 56 | 65 | 54.1667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2015-04-23 | 2018-08-21 | 0.4 | 1.2444 | 0.49778 | Reduce | 0.4 | 1.2444 | 0.49778 | H2 | 4 | Stable | 0.6 | 90 | 127 | 145 | 123.8333 | 0.4 | 28 | 51 | 74 | 51 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK154 | Project_038_RISK154 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production Tools and Jigs | Person_640 | 2015-06-24 | 2016-08-20 01:00 | 0.3 | 0.16195 | 0.072876 | Accept | 0.3 | 0.16195 | 0.072876 | H2 | 4 | Stable | 0.8 | 120 | 137 | 148 | 136 | 0.8 | 120 | 137 | 148 | 136 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 01:00 | 2018-08-21 | 0.45 | 0.83883 | 0.37747 | Reduce | 0.45 | 0.83883 | 0.37747 | H2 | 4 | Stable | 0.5 | 98 | 124 | 152 | 124.3333 | 0.4 | 20 | 42 | 73 | 43.5 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK163 | Project_038_RISK163 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Additional Chamber trials | Person_531 | 2015-09-21 01:00 | 2016-09-20 01:00 | 0.25 | 0.33412 | 0.15036 | Accept | 0.25 | 0.33412 | 0.15036 | H2 | 4 | Stable | 0.7 | 90 | 124 | 160 | 124.3333 | 0.7 | 90 | 124 | 160 | 124.3333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-010 | Project_011_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Rework required following integration of Customer System | Person_142 | 2013-08-21 01:00 | 2017-01-20 01:00 | 0.4 | 0.66881 | 0.26753 | Reduce | 0.4 | 0.66881 | 0.26753 | H2 | 4 | Stable | 0.8 | 111 | 130 | 149 | 130 | 0.4 | 20 | 46 | 64 | 44.6667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_040 | RISK174 | Project_040_RISK174 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Supplier Power Supply quality | Person_687 | 2013-08-20 21:00 | 2014-07-22 | 0.05 | 1.8788 | 0.28182 | Accept | 0.01 | 1.8788 | 0.28182 | H2 | 4 | Stable | 0.5 | 120 | 121 | 149 | 125.5 | 0.5 | 120 | 121 | 149 | 125.5 | 0 | 80 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 0.5 | 9.3941 | 1.8788 | Accept | 0.45 | 9.3941 | 1.8788 | H2 | 4 | Stable | 0.6 | 115 | 130 | 159 | 132.3333 | 0.6 | 115 | 130 | 159 | 132.3333 | 0 | 10 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation | Person_565 | 2018-05-22 | 2018-08-21 | 0.25 | 29.4599 | 8.838 | Accept | 0.25 | 18.7882 | 5.6365 | H3 | 3 | Stable | 0.7 | 103 | 136 | 146 | 132.1667 | 0.7 | 103 | 136 | 146 | 132.1667 | 36.2245 | 0 | 0 | 21.7347
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 0.5 | 4.7948 | 0.95895 | Accept | 0.5 | 4.7948 | 0.95895 | H2 | 4 | Improving | 0.5 | 119 | 124 | 160 | 129.1667 | 0.5 | 119 | 124 | 160 | 129.1667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 0.3 | 0.65759 | 0.098638 | Accept | 0.3 | 0.65759 | 0.098638 | H2 | 4 | Stable | 0.8 | 110 | 126 | 145 | 126.5 | 0.8 | 110 | 126 | 145 | 126.5 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-187 | Project_027_Risk-187 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Loss of a major sub-contractor | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.12 | 6.7638 | 1.3528 | Accept | 0.12 | 6.7638 | 1.3528 | H3 | 3 | Stable | 0.5 | 82 | 128 | 147 | 123.5 | 0.5 | 82 | 128 | 147 | 123.5 | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-188 | Project_027_Risk-188 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Unidentified Technical Legacy Issue | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 0.93941 | 0.14091 | Accept | 0.1 | 0.93941 | 0.14091 | H3 | 3 | Stable | 0.9 | 117 | 140 | 159 | 139.3333 | 0.9 | 117 | 140 | 159 | 139.3333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-196 | Project_027_Risk-196 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Aging equipment resulting in increasing failure rates | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.15 | 2.8182 | 0.56365 | Accept | 0.15 | 2.8182 | 0.56365 | H3 | 3 | Stable | 0.7 | 95 | 134 | 156 | 131.1667 | 0.7 | 95 | 134 | 156 | 131.1667 | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-185 | Project_027_Risk-185 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier manufacturing issues | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.6 | 0 | 0 | Accept | 0.05 | 0 | 0 | H3 | 3 | Stable | 0.9 | 89 | 131 | 151 | 127.3333 | 0.9 | 89 | 131 | 151 | 127.3333 |  | 91.6667 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-186 | Project_027_Risk-186 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Potential for composite suppliers going out of business | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 2.5834 | 0.64585 | Accept | 0.1 | 2.5834 | 0.64585 | H3 | 3 | Stable | 0.5 | 84 | 127 | 152 | 124 | 0.5 | 84 | 127 | 152 | 124 | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-194 | Project_027_Risk-194 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | The effect of specialist supplier obsolescence on complex assemblies | Person_074 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.15 | 0.65759 | 0.065759 | Accept | 0.15 | 0.75153 | 0.075153 | H3 | 3 | Stable | 0.8 | 80 | 131 | 156 | 126.6667 | 0.8 | 80 | 131 | 156 | 126.6667 | -14.2857 | 0 | 1 | -8.5714
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Governance and Export Rules | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 0.93941 | 0.23485 | Transfer | 0.25 | 0.93941 | 0.23485 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 | 2017-07-20 | 0.1 | 2.1606 | 0.43213 | Accept | 0.1 | 2.1606 | 0.43213 | H2 | 4 | Stable | 0.7 | 110 | 128 | 144 | 127.6667 | 0.7 | 110 | 128 | 144 | 127.6667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-120 | Project_032_Risk-120 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | System STTE Equipment Roll Out | Person_768 | 2014-03-23 | 2017-03-23 | 0.9 | 0.55886 | 0.27943 | Accept | 0.9 | 0.55886 | 0.11177 | H2 | 4 | Stable | 0.7 | 116 | 125 | 145 | 126.8333 | 0.7 | 116 | 125 | 145 | 126.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 2.7943 | 0.55886 | Accept | 0.5 | 2.7943 | 0.55886 | H2 | 4 | Stable | 0.5 | 101 | 131 | 156 | 130.1667 | 0.5 | 101 | 131 | 156 | 130.1667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-09 | Project_022_RISK-09 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance - Issues arise | Person_393 | 2012-04-22 | 2016-11-19 01:00 | 0.7 | 24.8225 | 17.3758 | Reduce | 0.48 | 8.951 | 4.2965 | H2 | 4 | Stable | 0.6 | 118 | 128 | 155 | 130.8333 | 0.2 | 27 | 59 | 61 | 54 | 63.94 | 31.4286 | 0 | 38.364
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-08 | Project_022_RISK-08 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Poor performance during acceptance phases | Person_248 | 2012-05-23 | 2016-11-19 01:00 | 0.65 | 5.6817 | 3.6931 | Reduce | 0.512 | 5.6817 | 2.909 | H1 | 5 | Stable | 0.9 | 88 | 136 | 143 | 129.1667 | 0.2 | 5 | 53 | 69 | 47.6667 | 0 | 21.2308 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.347 | 2.9061 | 1.0084 | H2 | 4 | Worsening | 0.5 | 93 | 139 | 154 | 133.8333 | 0.1 | 14 | 47 | 79 | 46.8333 | 21.0126 | 56.625 | 0 | 12.6076
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 0.5 | 2.3975 | 2.3975 | Accept | 0.5 | 4.3118 | 4.3118 | H2 | 4 | Stable | 0.6 | 115 | 133 | 159 | 134.3333 | 0.6 | 115 | 133 | 159 | 134.3333 | -79.8462 | 0 | 0 | -47.9077
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-22 | Project_022_RISK-22 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Setting to work Issues - monitor may require changing | Person_393 | 2014-10-22 01:00 | 2016-11-19 01:00 | 0.6 | 11.6428 | 6.9857 | Reduce | 0.2 | 19.5167 | 3.9033 | H3 | 3 | Worsening | 0.6 | 94 | 129 | 153 | 127.1667 | 0.2 | 14 | 44 | 78 | 44.6667 | -67.628 | 66.6667 | 0 | -40.5768
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.05 | 3.8666 | 1.5853 | Accept | 0.05 | 1.3288 | 0.5448 | H2 | 4 | Stable | 0.6 | 94 | 127 | 153 | 125.8333 | 0.6 | 94 | 127 | 153 | 125.8333 | 65.6338 | 0 | 0 | 39.3803
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-30 | Project_022_RISK-30 | Opportunitity | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Setting to work and acceptance issues | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 0.8 | 8.6133 | 6.8907 | Exploit | 0.8 | 2.6904 | 2.1524 | H2 | 4 | Stable | [10 empty] | 68.7641 | 0 | 0 | 41.2585
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2016-11-17 01:00 | 0.85 | 25.2325 | 21.4476 | Avoid | 0.08 | 20.8758 | 1.6701 | H2 | 4 | Improving | [10 empty] | 17.2662 | 90.5882 | 0 | 10.3597
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 3.3531 | 2.6825 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-018 | Project_023_Risk-018 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Project Management | Person_703 | 2013-05-19 | 2017-05-22 | 0.8 | 0.10892 | 0.087134 | Exploit | 0.8 | 0.10892 | 0.087134 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-58 | Project_022_RISK-58 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Handbook Update | Person_248 | 2012-04-19 | 2016-11-19 01:00 | 0.5 | 2.2354 | 1.1177 | Reduce | 0.5 | 2.2354 | 1.1177 | H3 | 3 | Stable | 0.8 | 110 | 136 | 159 | 135.5 | 0.3 | 17 | 43 | 63 | 42 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 0.5 | 5.4459 | 1.6338 | Accept | 0.5 | 0.18151 | 0.054453 | H2 | 4 | Stable | 0.6 | 95 | 131 | 144 | 127.1667 | 0.6 | 95 | 131 | 144 | 127.1667 | 96.667 | 0 | 0 | 58.0002
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-019 | Project_023_Risk-019 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software | Person_253 | 2013-05-19 | 2017-05-22 | 0.8 | 0.38121 | 0.30497 | Exploit | 0.8 | 0.38121 | 0.30497 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2016-11-17 01:00 | 0.7 | 24.1887 | 16.9321 | Reduce | 0.25 | 4.3567 | 1.0892 | H2 | 4 | Stable | 0.9 | 93 | 126 | 153 | 125 | 0.2 | 26 | 46 | 76 | 47.6667 | 81.9887 | 64.2857 | 0 | 49.1932
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-020 | Project_023_Risk-020 | Opportunitity | Project Contingency | Open | H2 | 4 | 8. System Engineering | Installation & Acceptance - Preventative Maintenance | Person_253 | 2013-05-19 | 2017-05-22 | 0.8 | 0.81688 | 0.6535 | Exploit | 0.8 | 0.81688 | 0.6535 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-021 | Project_023_Risk-021 | Opportunitity | Project Contingency | Open | H2 | 4 | 8. System Engineering | Customer Services - Preventative Maintenance | Person_253 | 2013-05-19 | 2017-05-22 | 0.8 | 1.1981 | 0.95847 | Exploit | 0.8 | 1.1981 | 0.95847 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 0.8 | 4.4985 | 1.3495 | Accept | 0.6 | 4.4985 | 1.3495 | H1 | 5 | Stable | 0.7 | 114 | 134 | 155 | 134.1667 | 0.7 | 114 | 134 | 155 | 134.1667 | 0 | 25 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-21 21:00 | 2017-05-22 | 0.25 | 7.4225 | 1.8556 | Reduce | 0.1 | 3.7113 | 0.37113 | H3 | 3 | Stable | 0.6 | 84 | 134 | 155 | 129.1667 | 0.4 | 39 | 41 | 79 | 47 | 50 | 60 | 0 | 30
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-18 21:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 2.6991 | 1.0796 | H2 | 4 | Stable | 0.5 | 108 | 135 | 144 | 132 | 0.2 | 38 | 52 | 77 | 53.8333 | 31.8182 | 20 | 0 | 19.0909
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 01:00 | 2016-08-20 01:00 | 0.1 | 18.069 | 1.8069 | Accept | 0.1 | 18.069 | 1.8069 | H2 | 4 | Stable | 0.6 | 88 | 137 | 160 | 132.6667 | 0.6 | 88 | 137 | 160 | 132.6667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_575 | 2015-05-24 | 2017-11-18 21:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 6.2979 | 0.94468 | H3 | 3 | Stable | 0.5 | 112 | 128 | 158 | 130.3333 | 0.2 | 26 | 55 | 73 | 53.1667 | 0 | 70 | 1 | 2.1
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.6 | 87 | 124 | 146 | 121.5 | 0.3 | 35 | 42 | 79 | 47 | 0 | 25 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 0.2 | 6.7866 | 6.7866 | Accept | 0.2 | 6.7866 | 6.7866 | H3 | 3 | Improving | 0.5 | 100 | 132 | 155 | 130.5 | 0.5 | 100 | 132 | 155 | 130.5 | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-007 | Project_026_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Additional requests for information and attendance at meetings | Person_264 | 2014-11-21 01:00 | 2018-12-27 01:00 | 0.5 | 10.5249 | 5.2625 | Reduce | 0.5 | 10.5249 | 5.2625 | H2 | 4 | Worsening | 0.9 | 95 | 122 | 154 | 122.8333 | 0.4 | 17 | 40 | 76 | 42.1667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Risk of repeat component Tests | Person_515 | 2017-12-21 01:00 | 2019-01-21 01:00 | 0.5 | 3.4415 | 1.3766 | Accept | 0.5 | 3.4415 | 1.3766 | H2 | 4 | Stable | 0.8 | 82 | 135 | 157 | 129.8333 | 0.8 | 82 | 135 | 157 | 129.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_515 | 2017-05-23 | 2019-01-21 01:00 | 0.5 | 8.0582 | 2.4175 | Accept | 0.5 | 8.0582 | 2.4175 | H2 | 4 | Stable | 0.7 | 114 | 134 | 154 | 134 | 0.7 | 114 | 134 | 154 | 134 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R44 | Project_041_R44 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Procurement - Source Change and cost change | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 0.5 | 0.5596 | 0.05596 | Accept | 0.5 | 0.5596 | 0.05596 | H1 | 5 | Worsening | 0.6 | 84 | 123 | 152 | 121.3333 | 0.6 | 84 | 123 | 152 | 121.3333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_368 | 2016-11-20 01:00 | 2017-09-19 01:00 | 0.25 | 3.6174 | 1.8087 | Accept | 0.25 | 3.6172 | 1.8086 | H3 | 3 | Stable | 0.6 | 117 | 135 | 156 | 135.5 | 0.6 | 117 | 135 | 156 | 135.5 | 0.0051359 | 0 | 0 | 0.0030815
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_515 | 2016-11-20 01:00 | 2018-05-22 | 0.1 | 2.3503 | 0.47006 | Accept | 0.1 | 2.3503 | 0.47006 | H3 | 3 | Stable | 0.8 | 82 | 131 | 158 | 127.3333 | 0.8 | 82 | 131 | 158 | 127.3333 | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R06 | Project_041_R06 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional PM time to support the supply chain | Person_359 | 2016-11-20 01:00 | 2017-09-19 01:00 | 0.25 | 4.4768 | 2.2384 | Accept | 0.25 | 4.4768 | 2.2384 | H3 | 3 | Stable | 0.7 | 86 | 140 | 156 | 133.6667 | 0.7 | 86 | 140 | 156 | 133.6667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_515 | 2016-11-20 01:00 | 2018-05-22 | 0.25 | 244.3581 | 12.2179 | Accept | 0.25 | 227.5702 | 11.3785 | H2 | 4 | Stable | 0.8 | 114 | 132 | 145 | 131.1667 | 0.8 | 114 | 132 | 145 | 131.1667 | 6.8702 | 0 | 0 | 4.1221
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-019 | Project_026_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Customer interaction and reporting may be much greater than anticipated | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 0.3 | 16.3694 | 4.9108 | Reduce | 0.2 | 16.3683 | 3.2737 | H3 | 3 | Worsening | 0.8 | 111 | 123 | 147 | 125 | 0.2 | 3 | 57 | 72 | 50.5 | 0.0068371 | 33.3333 | 0 | 0.0041023
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R017 | Project_021_Risk-R017 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Effort to address Hexavalent Chromium issue is unknown at time of baseline | Person_470 | 2016-02-06 01:00 | 2016-11-19 01:00 | 0.7 | 27.1831 | 13.5915 | Accept | 0.7 | 27.1831 | 13.5915 | H1 | 5 | Stable | 0.9 | 105 | 132 | 147 | 130 | 0.9 | 105 | 132 | 147 | 130 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Obsolescence Monitoring Risk | Person_181 | 2016-12-03 | 2017-01-20 | 0.3 | 5.9458 | 1.7837 | Reduce | 0.15 | 0.9786 | 0.14679 | H3 | 3 | Stable | 0.8 | 108 | 123 | 158 | 126.3333 | 0.2 | 12 | 52 | 71 | 48.5 | 83.5413 | 50 | 0 | 50.1248
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-21 | 2016-08-21 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.7 | 101 | 132 | 144 | 128.8333 | 0.2 | 6 | 54 | 74 | 49.3333 | 0 | 16.6667 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Suppliers | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 5.4336 | 1.3584 | Accept | 0.15 | 5.4336 | 1.3584 | H2 | 4 | Stable | 0.6 | 93 | 129 | 150 | 126.5 | 0.6 | 93 | 129 | 150 | 126.5 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 5.126 | 2.563 | Accept | 0.2 | 5.126 | 2.563 | H2 | 4 | Stable | 0.9 | 87 | 133 | 160 | 129.8333 | 0.9 | 87 | 133 | 160 | 129.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Local customer Engineers in country | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 12.815 | 2.563 | Accept | 0.1 | 12.815 | 2.563 | H2 | 4 | Stable | 0.8 | 109 | 130 | 156 | 130.8333 | 0.8 | 109 | 130 | 156 | 130.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence | Person_455 | 2016-05-23 | 2020-05-23 | 0.3 | 30.9033 | 7.7258 | Accept | 0.3 | 30.9033 | 7.7258 | H2 | 4 | Stable | 0.7 | 94 | 139 | 149 | 133.1667 | 0.7 | 94 | 139 | 149 | 133.1667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-21 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.9 | 91 | 125 | 147 | 123 | 0.2 | 25 | 44 | 63 | 44 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Consumables | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 35.0206 | 7.0041 | Accept | 0.2 | 35.0206 | 7.0041 | H2 | 4 | Stable | 0.9 | 102 | 130 | 151 | 128.8333 | 0.9 | 102 | 130 | 151 | 128.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 7. Finance | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 15.0654 | 6.7794 | Accept | 0.2 | 15.0654 | 6.7794 | H2 | 4 | Stable | 0.9 | 84 | 140 | 148 | 132 | 0.9 | 84 | 140 | 148 | 132 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-21 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.41 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -2.5 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.61 | 0.25667 | 0.15657 | Reduce | 0.5 | 0.25667 | 0.12834 | H2 | 4 | Stable | 0.5 | 96 | 136 | 151 | 131.8333 | 0.3 | 5 | 42 | 78 | 41.8333 | 0 | 18.0328 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2014-01-21 01:00 | 2017-11-20 01:00 | 0.4 | 1.078 | 0.43121 | Reduce | 0.2 | 1.078 | 0.2156 | H3 | 3 | Stable | 0.6 | 88 | 127 | 154 | 125 | 0.2 | 37 | 57 | 65 | 55 | 0 | 50 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-118 | Project_029_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Acceptance Schedule is longer in duration/delayed | Person_102 | 2015-12-22 01:00 | 2016-12-21 01:00 | 0.55 | 0.56468 | 0.31057 | Reduce | 0.55 | 0.56468 | 0.31057 | H2 | 4 | Stable | 0.8 | 107 | 131 | 155 | 131 | 0.1 | 20 | 51 | 72 | 49.3333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 0.77001 | 0.2541 | Accept | 0.15 | 0.77001 | 0.2541 | H2 | 4 | Stable | 0.5 | 114 | 121 | 146 | 124 | 0.5 | 114 | 121 | 146 | 124 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 6.4168 | 3.2084 | Accept | 0.2 | 1.5614 | 0.15614 | H2 | 4 | Stable | 0.6 | 80 | 130 | 147 | 124.5 | 0.6 | 80 | 130 | 147 | 124.5 | 75.6667 | 0 | 0 | 45.4
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-038 | Project_029_Risk-038 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Integration and Reliability | Person_216 | 2014-03-23 | 2016-11-19 01:00 | 0.15 | 1.155 | 0.17325 | Reduce | 0.15 | 0.77001 | 0.1155 | H3 | 3 | Stable | 0.7 | 119 | 126 | 145 | 128 | 0.2 | 38 | 55 | 77 | 55.8333 | 33.3333 | 0 | 1 | 20
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2017-11-19 01:00 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-113 | Project_029_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | SW Delivery to INtegration (including bug fixes post delivery) | Person_199 | 2014-07-22 | 2016-11-19 01:00 | 0.4 | 0.64168 | 0.25667 | Avoid | 0.4 | 0.84702 | 0.33881 | H2 | 4 | Worsening | [10 empty] | -32 | 0 | 0 | -19.2
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2016-10-21 01:00 | 0.6 | 0.89835 | 0.53901 | Transfer | 0.6 | 0.89835 | 0.53901 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport Routes | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 0.12834 | 0.10267 | Accept | 0.15 | 0.12834 | 0.10267 | H2 | 4 | Stable | 0.8 | 86 | 121 | 141 | 118.5 | 0.8 | 86 | 121 | 141 | 118.5 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2015-07-31 | 2017-05-15 | 0.35 | 0.85557 | 0.29945 | Reduce | 0.35 | 0.92402 | 0.32341 | H2 | 4 | Stable | 0.6 | 83 | 127 | 159 | 125 | 0.3 | 19 | 44 | 77 | 45.3333 | -8.0001 | 0 | 0 | -4.8001
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Internal Quality Issues | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 0.77001 | 0.30801 | Accept | 0.2 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.5 | 85 | 126 | 150 | 123.1667 | 0.5 | 85 | 126 | 150 | 123.1667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-105 | Project_029_Risk-105 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Changes to CE markings | Person_692 | 2015-05-24 | 2020-11-19 01:00 | 0.8 | 0.51334 | 0.41067 | Reduce | 0.3 | 0.51334 | 0.154 | H3 | 3 | Stable | 0.7 | 92 | 126 | 148 | 124 | 0.3 | 2 | 58 | 70 | 50.6667 | 0 | 62.5 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-028 | Project_029_Risk-028 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Assets (for system integration - repair of test assets) | Person_102 | 2015-02-21 01:00 | 2020-05-22 | 0.4 | 1.2834 | 0.51334 | Reduce | 0.2 | 1.2834 | 0.25667 | H3 | 3 | Stable | 0.7 | 103 | 121 | 160 | 124.5 | 0.1 | 15 | 46 | 79 | 46.3333 | 0 | 50 | 1 | 1.5
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2016-05-23 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.7 | 106 | 129 | 151 | 128.8333 | 0.4 | 12 | 56 | 69 | 50.8333 | 0 | 28.5714 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk017 | Project_042_Risk017 | Threat | Financial Contingency | Open | H2 | 4 | 6. Contractual/Legal | Liquidated Damages | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 1.54 | 0.30801 | Accept | 0.4 | 0.77001 | 0.154 | H2 | 4 | Stable | 0.9 | 117 | 140 | 151 | 138 | 0.9 | 117 | 140 | 151 | 138 | 50 | 0 | 0 | 30
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Repairs | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 0.87268 | 0.43634 | Accept | 0.25 | 0.87268 | 0.34907 | H2 | 4 | Stable | 0.7 | 96 | 130 | 157 | 128.8333 | 0.7 | 96 | 130 | 157 | 128.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk016 | Project_042_Risk016 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport/Delivery Speed | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 0.94968 | 0.28491 | Accept | 0.1 | 0.94968 | 0.18994 | H2 | 4 | Stable | 0.9 | 108 | 131 | 154 | 131 | 0.9 | 108 | 131 | 154 | 131 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Country Stability | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 27.1644 | 0.81493 | Accept | 0.4 | 12.8336 | 1.2834 | H2 | 4 | Stable | 0.5 | 104 | 132 | 159 | 131.8333 | 0.5 | 104 | 132 | 159 | 131.8333 | 52.7559 | 0 | 0 | 31.6535
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2014-07-22 | 2017-11-19 01:00 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.7 | 88 | 122 | 152 | 121.3333 | 0.2 | 39 | 55 | 64 | 53.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2017-10-14 01:00 | 0.41 | 6.4168 | 2.6309 | Transfer | 0.41 | 0 | 0 | H1 | 5 | Stable | [10 empty] | 100 | 0 | 0 | 60
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 1.54 | 0.46201 | Accept | 0.1 | 1.155 | 0.231 | H2 | 4 | Stable | 0.6 | 119 | 140 | 148 | 137.8333 | 0.6 | 119 | 140 | 148 | 137.8333 | 25 | 0 | 0 | 15
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK153 | Project_024_RISK153 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Processor memory/performance Issue | Person_331 | 2016-06-23 | 2017-03-22 | 0.3 | 112.3463 | 33.7039 | Reduce | 0.2 | 43.1036 | 8.6207 | H2 | 4 | Stable | 0.8 | 120 | 134 | 149 | 134.1667 | 0.1 | 20 | 51 | 70 | 49 | 61.6333 | 33.3333 | 0 | 36.98
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK155 | Project_024_RISK155 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Late availability of Parameters | Person_534 | 2016-03-23 | 2016-09-11 01:00 | 0.3 | 4.1113 | 1.2334 | Reduce | 0.3 | 4.1113 | 1.2334 | H1 | 5 | Stable | 0.6 | 110 | 136 | 147 | 133.5 | 0.3 | 27 | 41 | 66 | 42.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 5.4096 | 0.54096 | Accept | 0.2 | 5.4096 | 0.54096 | H2 | 4 | Stable | 0.8 | 117 | 122 | 144 | 124.8333 | 0.8 | 117 | 122 | 144 | 124.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-47 | Project_022_RISK-47 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Software Issues | Person_245 | 2012-04-19 | 2016-11-19 01:00 | 0.5 | 25.966 | 7.7898 | Accept | 0.2 | 25.966 | 7.7898 | H3 | 3 | Stable | 0.5 | 90 | 138 | 141 | 130.5 | 0.5 | 90 | 138 | 141 | 130.5 | 0 | 60 | 1 | 1.8
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-51 | Project_022_RISK-51 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Environmental Conditions | Person_393 | 2012-04-19 | 2016-11-19 01:00 | 0.2 | 62.3617 | 3.1181 | Accept | 0.2 | 62.3617 | 3.1181 | H3 | 3 | Stable | 0.8 | 111 | 129 | 143 | 128.3333 | 0.8 | 111 | 129 | 143 | 128.3333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2016-12-08 01:00 | 0.41 | 0.67512 | 0.13502 | Accept | 0.41 | 0.67512 | 0.13502 | H2 | 4 | Stable | 0.7 | 118 | 126 | 145 | 127.8333 | 0.7 | 118 | 126 | 145 | 127.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK201 | Project_024_RISK201 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Indication mode failure | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.25 | 1.6835 | 0.42087 | Reduce | 0.2 | 1.6835 | 0.33669 | H3 | 3 | Stable | 0.7 | 104 | 133 | 141 | 129.5 | 0.1 | 20 | 56 | 72 | 52.6667 | 0 | 20 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-015 | Project_023_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Illness | Person_371 | 2015-04-09 | 2016-12-11 01:00 | 0.25 | 1.3502 | 0.54009 | Accept | 0.25 | 1.3502 | 0.54009 | H2 | 4 | Stable | 0.6 | 118 | 121 | 154 | 126 | 0.6 | 118 | 121 | 154 | 126 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-016 | Project_023_Risk-016 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Damage to equipment (Unable to replace due to obsolescence) | Person_703 | 2015-10-22 01:00 | 2016-06-22 | 0.3 | 1.9128 | 0.19128 | Accept | 0.3 | 1.9128 | 0.19128 | H2 | 4 | Stable | 0.9 | 97 | 139 | 152 | 134.1667 | 0.9 | 97 | 139 | 152 | 134.1667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK213 | Project_024_RISK213 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Rigs requireaccreditation as "Special to Type" Test equipment | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.3 | 33.7558 | 10.1267 | Reduce | 0.2 | 23.3694 | 4.6739 | H2 | 4 | Stable | 0.6 | 91 | 128 | 146 | 124.8333 | 0.2 | 7 | 51 | 69 | 46.6667 | 30.7692 | 33.3333 | 0 | 18.4615
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK179 | Project_024_RISK179 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Testing Required | Person_289 | 2016-12-21 01:00 | 2017-05-22 | 0.5 | 3.5054 | 1.7527 | Reduce | 0.4 | 3.5054 | 1.4022 | H2 | 4 | Stable | 0.7 | 108 | 132 | 157 | 132.1667 | 0.4 | 14 | 52 | 71 | 48.8333 | 0 | 20 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK218 | Project_024_RISK218 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | System issues general | Person_289 | 2016-08-21 01:00 | 2016-10-04 01:00 | 0.4 | 90.8811 | 36.3524 | Reduce | 0.3 | 39.3904 | 11.8171 | H1 | 5 | Stable | 0.8 | 86 | 121 | 150 | 120 | 0.4 | 33 | 48 | 72 | 49.5 | 56.6571 | 25 | 0 | 33.9943
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK180 | Project_024_RISK180 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | High Accelerated Life Testing (HALT) | Person_289 | 2016-12-21 01:00 | 2017-05-03 | 0.4 | 10.4903 | 4.1961 | Reduce | 0.2 | 10.4903 | 2.0981 | H2 | 4 | Stable | 0.7 | 113 | 135 | 141 | 132.3333 | 0.1 | 20 | 43 | 75 | 44.5 | 0 | 50 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.7 | 81 | 131 | 143 | 124.6667 | 0.4 | 6 | 49 | 63 | 44.1667 | 0 | 60 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP068 | Project_024_OPP068 | Opportunitity | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Customer acceptance of iterative sell-off approach | Person_535 | 2016-07-21 | 2017-11-19 01:00 | 0.2 | 9.3045 | 1.8609 | -- | 0.3 | 9.3045 | 2.7913 | H2 | 4 | Stable | [10 empty] | 0 | -50 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-21 | 2019-08-20 | 0.35 | 14.541 | 5.8164 | Accept | 0.35 | 14.541 | 5.8164 | H3 | 3 | Stable | 0.6 | 101 | 134 | 148 | 130.8333 | 0.6 | 101 | 134 | 148 | 130.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK166 | Project_024_RISK166 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Requirements Acceptance Criteria | Person_288 | 2016-04-10 | 2017-03-06 01:00 | 0.4 | 3.843 | 1.5372 | Reduce | 0.2 | 1.2464 | 0.24927 | H2 | 4 | Improving | 0.8 | 93 | 122 | 155 | 122.6667 | 0.1 | 23 | 59 | 66 | 54.1667 | 67.5676 | 50 | 0 | 40.5405
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK196 | Project_024_RISK196 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional Trials - Cost of Labour | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.3 | 0.95209 | 0.28563 | Reduce | 0.2 | 0.95209 | 0.19042 | H2 | 4 | Worsening | 0.5 | 80 | 133 | 144 | 126 | 0.4 | 34 | 45 | 77 | 48.5 | 0 | 33.3333 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-21 | 2019-08-20 | 0.25 | 2.0816 | 0.20816 | Accept | 0.25 | 2.0816 | 0.20816 | H3 | 3 | Stable | 0.9 | 92 | 140 | 159 | 135.1667 | 0.9 | 92 | 140 | 159 | 135.1667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-21 | 2019-08-20 | 0.5 | 17.0765 | 1.7076 | Accept | 0.5 | 17.0765 | 1.7076 | H2 | 4 | Stable | 0.5 | 86 | 127 | 156 | 125 | 0.5 | 86 | 127 | 156 | 125 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-21 | 2019-08-20 | 0.2 | 22.8501 | 6.855 | Accept | 0.2 | 22.8501 | 6.855 | H3 | 3 | Stable | 0.5 | 92 | 139 | 148 | 132.6667 | 0.5 | 92 | 139 | 148 | 132.6667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK244 | Project_024_RISK244 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Blue Screen Of Death (BSOD) | Person_534 | 2016-04-22 | 2016-07-21 | 0.1 | 15.1468 | 1.5147 | Reduce | 0.1 | 15.1468 | 1.5147 | H3 | 3 | Stable | 0.6 | 88 | 138 | 151 | 131.8333 | 0.4 | 15 | 56 | 78 | 52.8333 | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.2 | 20.8767 | 4.1753 | H2 | 4 | Stable | 0.8 | 111 | 123 | 152 | 125.8333 | 0.4 | 28 | 52 | 70 | 51 | 50 | 50 | 0 | 30
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.49667 | 93.5036 | 46.4402 | Reduce | 0.29076 | 78.3005 | 22.767 | H1 | 5 | Worsening | 0.9 | 88 | 131 | 160 | 128.6667 | 0.2 | 36 | 42 | 65 | 44.8333 | 16.2594 | 41.457 | 0 | 9.7556
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials - Increased Cost | Person_073 | 2016-05-23 | 2017-02-19 01:00 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.5 | 101 | 126 | 144 | 124.8333 | 0.2 | 39 | 44 | 79 | 49 | 0 | 50 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | People unable to sustain the pace | Person_413 | 2015-11-21 01:00 | 2017-05-22 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.7 | 81 | 123 | 149 | 120.3333 | 0.4 | 28 | 57 | 67 | 53.8333 | 0 | 5 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-117 | Project_029_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework costs | Person_216 | 2015-09-21 01:00 | 2016-12-19 01:00 | 0.33 | 1.1685 | 0.23369 | Accept | 0.33 | 1.1685 | 0.23369 | H3 | 3 | Stable | 0.9 | 88 | 121 | 141 | 118.8333 | 0.9 | 88 | 121 | 141 | 118.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-017 | Project_029_Risk-017 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Additional Obsolescence - System | Person_102 | 2016-05-23 | 2017-10-21 01:00 | 0.5 | 1.3502 | 0.40507 | Accept | 0.1 | 1.3502 | 0.40507 | H3 | 3 | Stable | 0.6 | 108 | 122 | 147 | 123.8333 | 0.6 | 108 | 122 | 147 | 123.8333 | 0 | 80 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK286 | Project_024_RISK286 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Requirement sell off more difficult than expected | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.5 | 10.9057 | 5.4529 | Reduce | 0.4 | 7.7898 | 3.1159 | H1 | 5 | Worsening | 0.6 | 113 | 126 | 149 | 127.6667 | 0.3 | 12 | 47 | 68 | 44.6667 | 28.5714 | 20 | 0 | 17.1429
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK288 | Project_024_RISK288 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Unplanned obsolescence and/or repairs to rig assets. | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.6 | 5.8424 | 3.5054 | Reduce | 0.6 | 5.8424 | 3.5054 | H1 | 5 | Stable | 0.5 | 89 | 130 | 152 | 126.8333 | 0.3 | 25 | 44 | 68 | 44.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.4 | 25.4467 | 10.1787 | Reduce | 0.3 | 10.9057 | 3.2717 | H1 | 5 | Stable | 0.8 | 82 | 140 | 144 | 131 | 0.4 | 24 | 49 | 63 | 47.1667 | 57.1429 | 25 | 0 | 34.2857
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK291 | Project_024_RISK291 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | LoE Engineering support required post completion in addition to BCR | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 8.5688 | 4.2844 | Reduce | 0.4 | 8.5688 | 3.4275 | H1 | 5 | Worsening | 0.9 | 119 | 125 | 151 | 128.3333 | 0.1 | 4 | 50 | 78 | 47 | 0 | 20 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-111 | Project_029_Risk-111 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Unplanned courier cost and T&S for any transportation of hardware during Integration phase | Person_692 | 2015-07-22 | 2016-10-21 01:00 | 0.8 | 30.562 | 24.4496 | Accept | 0.8 | 30.562 | 24.4496 | H2 | 4 | Stable | 0.5 | 81 | 137 | 155 | 130.6667 | 0.5 | 81 | 137 | 155 | 130.6667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK290 | Project_024_RISK290 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance Strategy decisions being made too late | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.5 | 12.0742 | 6.0371 | Avoid | 0.1 | 12.0742 | 1.2074 | H3 | 3 | Stable | [10 empty] | 0 | 80 | 1 | 2.4
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2016-05-23 | 2018-05-22 | 0.4 | 15.0863 | 7.5431 | Accept | 0.3 | 15.0863 | 7.5431 | H2 | 4 | Stable | 0.8 | 92 | 136 | 151 | 131.1667 | 0.8 | 92 | 136 | 151 | 131.1667 | 0 | 25 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2019-10-14 01:00 | 0.2 | 29.1079 | 19.2112 | Accept | 0.2 | 29.1079 | 14.845 | H3 | 3 | Stable | 0.9 | 99 | 126 | 158 | 126.8333 | 0.9 | 99 | 126 | 158 | 126.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 01:00 | 2016-05-21 | 0.5 | 4.3921 | 2.196 | Reduce | 0.3 | 4.3921 | 1.3176 | H1 | 5 | Stable | 0.9 | 92 | 133 | 157 | 130.1667 | 0.1 | 27 | 56 | 73 | 54 | 0 | 40 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-117 | Project_039_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Filters | Person_185 | 2015-01-21 01:00 | 2017-02-19 01:00 | 0.1 | 3.005 | 0.3005 | Reduce | 0.1 | 3.005 | 0.3005 | H3 | 3 | Stable | 0.5 | 99 | 126 | 144 | 124.5 | 0.4 | 38 | 47 | 78 | 50.6667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-026 | Project_029_Risk-026 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | platform Integration - SW support | Person_102 | 2016-09-02 01:00 | 2019-09-24 01:00 | 0.5 | 0.35617 | 0.10685 | Accept | 0.4 | 0.35617 | 0.10685 | H3 | 3 | Stable | 0.9 | 103 | 139 | 147 | 134.3333 | 0.9 | 103 | 139 | 147 | 134.3333 | 0 | 20 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2015-07-22 | 2017-11-19 01:00 | 0.3 | 1.8602 | 0.55807 | Accept | 0.2 | 1.8602 | 0.55807 | H3 | 3 | Stable | 0.5 | 115 | 125 | 149 | 127.3333 | 0.5 | 115 | 125 | 149 | 127.3333 | 0 | 33.3333 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2017-10-20 01:00 | 0.03 | 1.4882 | 0.44646 | Accept | 0.1 | 1.4882 | 0.44646 | H2 | 4 | Stable | 0.9 | 84 | 137 | 143 | 129.1667 | 0.9 | 84 | 137 | 143 | 129.1667 | 0 | -233.3333 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub-system FPGA | Person_216 | 2014-02-20 01:00 | 2017-05-22 | 0.3 | 1.4882 | 0.44646 | Accept | 0.2 | 1.4882 | 0.44646 | H3 | 3 | Stable | 0.8 | 94 | 125 | 151 | 124.1667 | 0.8 | 94 | 125 | 151 | 124.1667 | 0 | 33.3333 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK152 | Project_024_RISK152 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Component Damage | Person_674 | 2016-04-06 | 2016-10-21 01:00 | 0.1 | 0.81199 | 0.081199 | Accept | 0.1 | 0.81199 | 0.0406 | H3 | 3 | Stable | 0.8 | 81 | 138 | 159 | 132 | 0.8 | 81 | 138 | 159 | 132 | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-022 | Project_028_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Accrediation Scope | Person_371 | 2014-01-21 01:00 | 2016-10-20 01:00 | 0.5 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 20 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment environmental failure | Person_289 | 2016-05-23 | 2016-12-02 01:00 | 0.3 | 12.1982 | 0.60991 | Accept | 0.3 | 12.1982 | 0.60991 | H1 | 5 | Improving | 0.7 | 107 | 124 | 152 | 125.8333 | 0.7 | 107 | 124 | 152 | 125.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Retained systems re-design or modification | Person_289 | 2016-08-20 01:00 | 2016-12-02 01:00 | 0.05 | 0 | 0 | Accept | 0.05 | 0 | 0 | H2 | 4 | Improving | 0.6 | 100 | 135 | 146 | 131 | 0.6 | 100 | 135 | 146 | 131 |  | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Mission System not compatible with platform systems | Person_289 | 2016-07-21 | 2017-02-19 01:00 | 0.1 | 0 | 0 | Accept | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 116 | 123 | 148 | 126 | 0.8 | 116 | 123 | 148 | 126 |  | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2016-11-19 01:00 | 0.2 | 0.90951 | 0.1819 | Reduce | 0.2 | 0.90951 | 0.1819 | H3 | 3 | Stable | 0.5 | 113 | 125 | 156 | 128.1667 | 0.3 | 3 | 45 | 63 | 41 | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK202 | Project_024_RISK202 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Mode Specific | Person_448 | 2015-09-04 01:00 | 2017-02-19 01:00 | 0.2 | 0.681 | 0.2724 | Accept | 0.2 | 0.681 | 0.1362 | H3 | 3 | Stable | 0.9 | 119 | 125 | 142 | 126.8333 | 0.9 | 119 | 125 | 142 | 126.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK204 | Project_024_RISK204 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Stabilisation | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.4 | 1.4532 | 0.072661 | Accept | 0.4 | 1.4532 | 0.072661 | H1 | 5 | Improving | 0.6 | 116 | 136 | 152 | 135.3333 | 0.6 | 116 | 136 | 152 | 135.3333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK203 | Project_024_RISK203 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Detection/Tracking modifications | Person_448 | 2016-10-21 01:00 | 2017-02-19 01:00 | 0.1 | 11.0007 | 0.55004 | Accept | 0.1 | 11.0007 | 0.55004 | H3 | 3 | Improving | 0.7 | 84 | 136 | 158 | 131 | 0.7 | 84 | 136 | 158 | 131 | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2017-01-20 01:00 | 0.3 | 5.4553 | 1.6366 | Reduce | 0.2 | 5.252 | 1.0504 | H2 | 4 | Stable | 0.5 | 91 | 127 | 151 | 125 | 0.3 | 11 | 42 | 60 | 39.8333 | 3.7267 | 33.3333 | 0 | 2.236
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-058 | Project_028_Risk-058 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | INterface Card | Person_253 | 2015-07-22 | 2016-10-20 01:00 | 0.2 | 2.8408 | 0.56817 | Reduce | 0.1 | 1.9314 | 0.19314 | H3 | 3 | Stable | 0.9 | 117 | 127 | 159 | 130.6667 | 0.1 | 28 | 45 | 62 | 45 | 32.0134 | 50 | 1 | 20.708
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK200 | Project_024_RISK200 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Height Finding | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.35 | 1.3215 | 0.39644 | Accept | 0.35 | 1.3215 | 0.39644 | H2 | 4 | Worsening | 0.6 | 80 | 136 | 154 | 129.6667 | 0.6 | 80 | 136 | 154 | 129.6667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK209 | Project_024_RISK209 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Major Return to Service | Person_073 | 2016-11-20 01:00 | 2017-05-22 | 0.3 | 12.1982 | 2.4396 | Accept | 0.3 | 10.8428 | 2.1686 | H1 | 5 | Stable | 0.5 | 85 | 136 | 155 | 130.6667 | 0.5 | 85 | 136 | 155 | 130.6667 | 11.1111 | 0 | 0 | 6.6667
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK206 | Project_024_RISK206 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Simulator Updates | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.1 | 4.4727 | 0.44727 | Accept | 0.1 | 4.4727 | 0.22363 | H3 | 3 | Stable | 0.5 | 106 | 137 | 152 | 134.3333 | 0.5 | 106 | 137 | 152 | 134.3333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Overland performance | Person_448 | 2016-06-23 | 2017-05-21 | 0.25 | 20.3303 | 7.1156 | Accept | 0.25 | 18.975 | 3.795 | H2 | 4 | Improving | 0.5 | 105 | 129 | 148 | 128.1667 | 0.5 | 105 | 129 | 148 | 128.1667 | 6.6667 | 0 | 0 | 4
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Cable and connectors | Person_050 | 2015-11-21 01:00 | 2017-08-09 | 0.45 | 0.41338 | 0.18602 | Reduce | 0.2 | 0.41338 | 0.082677 | H2 | 4 | Stable | 0.7 | 95 | 122 | 143 | 121 | 0.1 | 5 | 49 | 64 | 44.1667 | 0 | 55.5556 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Platform Acceptance | Person_500 | 2015-11-21 01:00 | 2017-04-21 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.2 | 4.2355 | 0.8471 | H3 | 3 | Stable | 0.9 | 106 | 137 | 155 | 134.8333 | 0.4 | 5 | 46 | 64 | 42.1667 | 0 | 42.8571 | 1 | 1.2857
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-001 | Project_028_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Porting software | Person_542 | 2014-03-23 | 2016-12-20 01:00 | 0.5 | 8.8098 | 4.4049 | Reduce | 0.08 | 7.4545 | 0.59636 | H2 | 4 | Stable | 0.8 | 90 | 133 | 155 | 129.5 | 0.3 | 11 | 41 | 76 | 41.8333 | 15.3846 | 84 | 0 | 9.2308
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Qual failure | Person_289 | 2016-06-22 | 2016-11-20 01:00 | 0.4 | 8.8098 | 3.0834 | Accept | 0.4 | 8.8098 | 1.762 | H1 | 5 | Improving | 0.9 | 120 | 138 | 155 | 137.8333 | 0.9 | 120 | 138 | 155 | 137.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK210 | Project_024_RISK210 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Performance | Person_532 | 2016-06-22 | 2017-02-19 01:00 | 0.3 | 0.40661 | 0.16264 | Accept | 0.3 | 0.40661 | 0.081321 | H2 | 4 | Stable | 0.7 | 81 | 121 | 143 | 118 | 0.7 | 81 | 121 | 143 | 118 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Furnished Equipmnet Condition | Person_371 | 2015-04-27 | 2017-08-19 01:00 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.5 | 120 | 134 | 160 | 136 | 0.2 | 3 | 46 | 74 | 43.5 |  | 62.5 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Additional minor releases | Person_073 | 2016-05-23 | 2017-08-20 01:00 | 0.5 | 71.0212 | 21.3064 | Accept | 0.5 | 71.0212 | 21.3064 | H1 | 5 | Stable | 0.8 | 119 | 129 | 141 | 129.3333 | 0.8 | 119 | 129 | 141 | 129.3333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-109 | Project_011_Risk-109 | Opportunitity | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Environment complexity | Person_187 | 2016-07-21 | 2018-08-21 | 0.25 | 0.14661 | 0.036651 | -- | 0.25 | 0.14661 | 0.036651 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-108 | Project_011_Risk-108 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Offer additional functionality to the customer | Person_147 | 2017-04-22 | 2018-08-21 | 0.1 | 0.34094 | 0.034094 | -- | 0.1 | 0.34094 | 0.034094 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 0.2 | 0.12388 | 0.024775 | Reduce | 0.2 | 0.12388 | 0.024775 | H2 | 4 | Stable | 0.9 | 94 | 133 | 158 | 130.6667 | 0.3 | 6 | 41 | 69 | 39.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 0.4 | 0.51141 | 0.20457 | Avoid | 0.4 | 0.51141 | 0.20457 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Digital Video Chainredesign | Person_289 | 2016-06-22 | 2016-12-17 01:00 | 0.4 | 0.49834 | 0.12459 | Accept | 0.71 | 0.49834 | 0.12459 | H1 | 5 | Worsening | 0.6 | 104 | 131 | 154 | 130.3333 | 0.6 | 104 | 131 | 154 | 130.3333 | 0 | -77.5 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.2 | 0.10171 | 0.020343 | -- | 0.2 | 0.10171 | 0.020343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 0.3 | 0.28639 | 0.085917 | Reduce | 0.3 | 0.28639 | 0.085917 | H2 | 4 | Stable | 0.7 | 112 | 128 | 160 | 130.6667 | 0.3 | 34 | 49 | 62 | 48.6667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 2. Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 0.25 | 0 | 0 | -- | 0.25 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2016-07-21 | 2018-05-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 0.3 | 0.10626 | 0.031878 | -- | 0.3 | 0.01932 | 0.005796 | H3 | 3 | Stable | [10 empty] | 81.8181 | 0 | 0 | 49.0909
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK253 | Project_024_RISK253 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Insufficient parts to complete framework Warranty | Person_289 | 2016-05-23 | 2017-04-21 | 0.1 | 1.0052 | 0.35182 | Accept | 0.1 | 1.0052 | 0.35182 | H2 | 4 | Improving | 0.7 | 91 | 128 | 158 | 126.8333 | 0.7 | 91 | 128 | 158 | 126.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-118 | Project_011_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer change environment | Person_187 | 2013-08-21 01:00 | 2018-08-21 | 0.1 | 0 | 0 | Avoid | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-116 | Project_011_Risk-116 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Delays to Qualification | Person_147 | 2017-04-22 | 2017-08-19 01:00 | 0.25 | 1.7297 | 0.43243 | -- | 0.25 | 1.7297 | 0.43243 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-104 | Project_011_Risk-104 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer delayed in providing Custeomr Furnished Equipment | Person_147 | 2016-06-23 | 2017-04-21 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.6 | 80 | 123 | 153 | 120.8333 | 0.4 | 32 | 47 | 72 | 48.6667 |  | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 0.3 | 0.51931 | 0.15579 | -- | 0.15 | 0.51931 | 0.077897 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 0.2 | 0.55005 | 0.11001 | Avoid | 0.2 | 0.55005 | 0.11001 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-123 | Project_011_Risk-123 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | No Requirement for Delta acceptance | Person_187 | 2017-06-23 | 2017-08-20 01:00 | 0.2 | 0.63074 | 0.12615 | -- | 0.2 | 0.63074 | 0.12615 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2016-07-21 | 2017-02-19 01:00 | 0.15 | 0.28639 | 0.042959 | -- | 0.15 | 0.28639 | 0.042959 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-04-21 | 0.4 | 0.24207 | 0.096828 | -- | 0.4 | 0.24207 | 0.096828 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK114 | Project_035_RISK114 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Qualification Facilities Availability. | Person_570 | 2015-09-21 01:00 | 2016-08-20 01:00 | 0.61 | 1.2358 | 0.75383 | Reduce | 0.3 | 1.2358 | 0.37073 | H2 | 4 | Stable | 0.5 | 110 | 130 | 142 | 128.6667 | 0.2 | 29 | 41 | 60 | 42.1667 | 0 | 50.8197 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK189 | Project_024_RISK189 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment integration - Audio and Video recording | Person_289 | 2016-08-20 01:00 | 2017-01-21 01:00 | 0.49 | 6.3266 | 1.898 | Accept | 0.49 | 6.3266 | 1.297 | H1 | 5 | Worsening | 0.7 | 105 | 132 | 158 | 131.8333 | 0.7 | 105 | 132 | 158 | 131.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_289 | 2016-05-23 | 2016-12-20 01:00 | 0.4 | 3.2155 | 0.96464 | Accept | 0.4 | 3.2155 | 0.48232 | H1 | 5 | Stable | 0.5 | 107 | 125 | 156 | 127.1667 | 0.5 | 107 | 125 | 156 | 127.1667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK194 | Project_024_RISK194 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Performance Models require additional effort | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.25 | 3.2155 | 0.96464 | Accept | 0.25 | 3.2155 | 0.96464 | H2 | 4 | Stable | 0.8 | 112 | 128 | 142 | 127.6667 | 0.8 | 112 | 128 | 142 | 127.6667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK195 | Project_024_RISK195 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Perfomance Validation document not accepted | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.1 | 1.2271 | 0.50311 | Accept | 0.1 | 1.2271 | 0.50311 | H2 | 4 | Stable | 0.6 | 113 | 136 | 143 | 133.3333 | 0.6 | 113 | 136 | 143 | 133.3333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK380 | Project_035_RISK380 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Data Throttling Algorithm | Person_699 | 2016-01-03 01:00 | 2016-11-20 01:00 | 0.2 | 2.6071 | 0.52143 | Reduce | 0.2 | 2.6071 | 0.52143 | H3 | 3 | Stable | 0.9 | 100 | 123 | 146 | 123 | 0.2 | 14 | 47 | 69 | 45.1667 | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK394 | Project_035_RISK394 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Provision of supplier evidence | Person_631 | 2016-02-21 01:00 | 2016-09-19 01:00 | 0.5 | 2.4768 | 1.2384 | -- | 0.5 | 1.2167 | 0.60833 | H2 | 4 | Improving | [10 empty] | 50.8773 | 0 | 0 | 30.5264
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK350 | Project_035_RISK350 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Sub-System Performance against Bid Scenario | Person_303 | 2015-06-24 | 2017-04-21 | 0.5 | 2.0423 | 1.0211 | -- | 0.3 | 1.0168 | 0.30503 | H2 | 4 | Stable | [10 empty] | 50.2128 | 40 | 0 | 30.1277
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2016-02-21 01:00 | 2018-05-22 | 0.1 | 8.4297 | 1.6859 | Accept | 0.1 | 4.745 | 0.4745 | H3 | 3 | Stable | 0.5 | 102 | 123 | 142 | 122.6667 | 0.5 | 102 | 123 | 142 | 122.6667 | 43.7114 | 0 | 1 | 26.2268
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 0.3 | 3.5631 | 0.53446 | Accept | 0.3 | 3.5631 | 0.42757 | H1 | 5 | Improving | 0.5 | 103 | 121 | 151 | 123 | 0.5 | 103 | 121 | 151 | 123 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK290 | Project_035_RISK290 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Face-to-Face Arbitration | Person_699 | 2015-01-22 01:00 | 2016-09-20 01:00 | 0.5 | 1.2445 | 0.62224 | -- | 0.2 | 2.303 | 0.46059 | H3 | 3 | Worsening | [10 empty] | -85.0557 | 60 | 0 | -51.0334
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK395 | Project_035_RISK395 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Test area Site Availability | Person_691 | 2016-05-23 | 2016-11-19 01:00 | 0.5 | 3.0417 | 1.5208 | -- | 0.5 | 3.0417 | 1.5208 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK399 | Project_038_RISK399 | Opportunitity | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Baseline Rationalisation | Person_151 | 2017-03-22 | 2017-05-15 | 0.4 | 1.3484 | 0.53935 | -- | 0.4 | 1.3484 | 0.53935 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_119 | 2016-10-21 01:00 | 2017-11-19 01:00 | 0.3 | 2.3457 | 0.11728 | Accept | 0.3 | 2.3457 | 0.023457 | H1 | 5 | Improving | 0.7 | 110 | 140 | 141 | 135.1667 | 0.7 | 110 | 140 | 141 | 135.1667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK237 | Project_024_RISK237 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer coding standard Compliance | Person_534 | 2017-05-25 | 2017-10-27 01:00 | 0.2 | 0.034059 | 0.0034059 | Accept | 0.2 | 0.034059 | 0.0034059 | H2 | 4 | Stable | 0.6 | 116 | 123 | 148 | 126 | 0.6 | 116 | 123 | 148 | 126 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK198 | Project_024_RISK198 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Spot Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 0.2 | 0.35539 | 0.17769 | Accept | 0.2 | 0.35539 | 0.088847 | H3 | 3 | Stable | 0.5 | 108 | 128 | 157 | 129.5 | 0.5 | 108 | 128 | 157 | 129.5 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk005 | Project_002_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2014-06-14 | 2016-08-08 | 0.3 | 0.035539 | 0.010662 | Avoid | 0.3 | 0.035539 | 0.010662 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk008 | Project_002_Risk008 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2014-08-20 | 2016-08-07 | 0.1 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | -100 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk009 | Project_002_Risk009 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2014-06-14 | 2016-08-07 | 0.1 | 0.01925 | 0.001925 | Avoid | 0.1 | 0.01925 | 0.001925 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | RISK012 | Project_002_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Resourcing Suitably Qualified and experienced staff availability | Person_650 | 2015-11-21 | 2016-08-07 | 0.2 | 0.05627 | 0.011254 | Reduce | 0.2 | 0.05627 | 0.011254 | H3 | 3 | Stable | 0.5 | 117 | 140 | 150 | 137.8333 | 0.1 | 38 | 40 | 79 | 46.1667 | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk004 | Project_002_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability of Test Equipment | Person_133 | 2014-03-26 | 2016-08-08 | 0.2 | 0.081443 | 0.016289 | Avoid | 0.2 | 0.081443 | 0.016289 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk006 | Project_002_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Additional Pressure Testing | Person_650 | 2014-06-14 | 2016-08-08 | 0.25 | 0.035539 | 0.0088847 | Avoid | 0.25 | 0.035539 | 0.0088847 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk011 | Project_002_Risk011 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Testing | Person_175 | 2014-06-29 | 2016-08-07 | 0.41 | 0.071669 | 0.029384 | Reduce | 0.1 | 0.0088847 | 0.00088847 | H3 | 3 | Stable | 0.5 | 94 | 128 | 152 | 126.3333 | 0.1 | 35 | 45 | 68 | 47.1667 | 87.6032 | 75.6098 | 1 | 54.8302
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-010 | Project_005_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Risk that required resources (people and rigs) will not be available as required due to other projects/bids (Customer & Internal) | Person_470 | 2011-11-11 01:00 | 2016-07-20 | 0.25 | 3.9852 | 0.9963 | Reduce | 0.1 | 3.9852 | 0.39852 | H3 | 3 | Stable | 0.7 | 94 | 131 | 145 | 127.1667 | 0.4 | 2 | 49 | 62 | 43.3333 | 0 | 60 | 1 | 1.8
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-034 | Project_005_Risk-034 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project delay causes cost impact to project | Person_470 | 2011-12-02 01:00 | 2016-08-18 01:00 | 0.5 | 16.3745 | 8.1873 | Reduce | 0.4 | 16.3745 | 6.5498 | H2 | 4 | Stable | 0.5 | 93 | 124 | 153 | 123.6667 | 0.2 | 10 | 50 | 65 | 45.8333 | 0 | 20 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-060 | Project_005_Risk-060 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Technical Acceptance may be more difficult than anticipated | Person_470 | 2014-06-11 | 2016-07-20 | 0.5 | 1.6266 | 0.8133 | Reduce | 0.3 | 1.6266 | 0.48798 | H3 | 3 | Stable | 0.9 | 99 | 140 | 145 | 134 | 0.4 | 11 | 47 | 60 | 43.1667 | 0 | 40 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK007 | Project_004_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 01:00 | 2016-03-21 01:00 | 0.2 | 0.15317 | 0.030633 | Reduce | 0.2 | 0.10883 | 0.021765 | H3 | 3 | Stable | 0.5 | 108 | 124 | 149 | 125.5 | 0.1 | 10 | 54 | 65 | 48.5 | 28.9481 | 0 | 1 | 17.3689
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK004 | Project_004_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 0.2 | 0.14752 | 0.029504 | Avoid | 0.2 | 0.14752 | 0.029504 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK003 | Project_004_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-05-24 | 2016-03-21 01:00 | 0.2 | 0.060459 | 0.012092 | Avoid | 0.2 | 0.060459 | 0.012092 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK006 | Project_004_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2014-11-19 01:00 | 2016-03-21 01:00 | 0.1 | 0.049978 | 0.0049978 | Avoid | 0.1 | 0.049978 | 0.0049978 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK005 | Project_004_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK002 | Project_004_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 0.5 | 0.15317 | 0.076583 | Avoid | 0.5 | 0.15317 | 0.076583 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.9 | 109 | 129 | 142 | 127.8333 | 0.2 | 12 | 53 | 71 | 49.1667 | 25.8065 | 20 | 0 | 15.4839
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 01:00 | 2016-10-19 01:00 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.9 | 115 | 137 | 145 | 134.6667 | 0.1 | 22 | 46 | 75 | 46.8333 | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 01:00 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 01:00 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK197 | Project_024_RISK197 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Fitness for purpose | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.2 | 0 | 0 | Accept | 0.2 | 0 | 0 | H2 | 4 | Improving | 0.8 | 116 | 121 | 148 | 124.6667 | 0.8 | 116 | 121 | 148 | 124.6667 |  | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK199 | Project_024_RISK199 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Strip Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 0.3 | 0.85811 | 0.42906 | Accept | 0.3 | 0.85811 | 0.42906 | H2 | 4 | Stable | 0.5 | 114 | 127 | 156 | 129.6667 | 0.5 | 114 | 127 | 156 | 129.6667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK219 | Project_024_RISK219 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | STTE additional work | Person_289 | 2016-09-20 01:00 | 2017-07-21 | 0.5 | 0 | 0 | Accept | 0.5 | 0 | 0 | H1 | 5 | Worsening | 0.5 | 86 | 140 | 143 | 131.5 | 0.5 | 86 | 140 | 143 | 131.5 |  | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 20:00 | 2019-08-20 20:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.9 | 108 | 136 | 153 | 134.1667 | 0.4 | 14 | 51 | 70 | 48 | 83.3333 | 88.8889 | 1 | 52.6667
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 20:00 | 2019-08-20 20:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.6 | 83 | 136 | 159 | 131 | 0.4 | 13 | 46 | 65 | 43.6667 | 72 | 0 | 0 | 43.2
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 20:00 | 2019-08-20 20:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.7 | 82 | 124 | 151 | 121.5 | 0.2 | 16 | 52 | 77 | 50.1667 | 47.7391 | 0 | 0 | 28.6435
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 20:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.6 | 97 | 127 | 153 | 126.3333 | 0.4 | 31 | 50 | 71 | 50.3333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H3 | 3 | Improving | 0.5 | 118 | 139 | 142 | 136 | 0.4 | 29 | 45 | 73 | 47 |  | 62.5 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.6 | 95 | 132 | 160 | 130.5 | 0.4 | 35 | 57 | 63 | 54.3333 |  | 50 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-005 | Project_021_Risk-005 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Opportunity to accelerate Component Approval through closer working efficiencies | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 0.1 | 0 | 0 | -- | 0.3 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -200 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2016-11-19 01:00 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.9 | 101 | 128 | 159 | 128.6667 | 0.3 | 38 | 45 | 79 | 49.5 |  | 50 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP006 | Project_021_OPP006 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Opportunity to accelerate Component Approval through closer working efficiencies | Person_721 | 2016-08-06 | 2016-11-19 01:00 | 0.1 | 0 | 0 | -- | 0.3 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -200 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2016-11-19 01:00 | 0.3 | 1.076 | 0.32281 | Reduce | 0.05 | 1.076 | 0.053801 | H2 | 4 | Improving | 0.9 | 117 | 125 | 143 | 126.6667 | 0.4 | 31 | 40 | 63 | 42.3333 | 0 | 83.3333 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-111 | Project_039_Risk-111 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Maturation results inconclusive | Person_297 | 2016-02-21 01:00 | 2017-01-20 01:00 | 0.3 | 2.5966 | 0.51932 | Accept | 0.3 | 2.5966 | 0.51932 | H2 | 4 | Stable | 0.7 | 80 | 123 | 151 | 120.5 | 0.7 | 80 | 123 | 151 | 120.5 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 01:00 | 0.1 | 9.8671 | 0.98671 | Accept | 0.05 | 9.8671 | 0.98671 | H3 | 3 | Stable | 0.8 | 95 | 122 | 153 | 122.6667 | 0.8 | 95 | 122 | 153 | 122.6667 | 0 | 50 | 1 | 1.5
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-015 | Project_028_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | STANDARDS Compliance | Person_499 | 2015-10-22 01:00 | 2016-11-19 01:00 | 0.05 | 4.6739 | 1.8696 | Accept | 0.05 | 4.6739 | 1.8696 | H3 | 3 | Stable | 0.8 | 114 | 130 | 160 | 132.3333 | 0.8 | 114 | 130 | 160 | 132.3333 | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-041 | Project_028_Risk-041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Role Test Equipment Team Deliver Late | Person_542 | 2015-04-08 | 2016-11-19 01:00 | 0.4 | 0.35539 | 0.17769 | Accept | 0.2 | 0.35539 | 0.088847 | H2 | 4 | Stable | 0.9 | 96 | 132 | 147 | 128.5 | 0.9 | 96 | 132 | 147 | 128.5 | 0 | 50 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk005 | Project_002_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2014-06-14 | 2016-08-08 | 0.3 | 0.035539 | 0.010662 | Avoid | 0.3 | 0.035539 | 0.010662 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk008 | Project_002_Risk008 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2014-08-20 | 2016-08-07 | 0.1 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | -100 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk009 | Project_002_Risk009 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2014-06-14 | 2016-08-07 | 0.1 | 0.01925 | 0.001925 | Avoid | 0.1 | 0.01925 | 0.001925 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | RISK012 | Project_002_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Resourcing Suitably Qualified and experienced staff availability | Person_650 | 2015-11-21 | 2016-08-07 | 0.2 | 0.05627 | 0.011254 | Reduce | 0.2 | 0.05627 | 0.011254 | H3 | 3 | Stable | 0.5 | 109 | 136 | 149 | 133.6667 | 0.2 | 25 | 58 | 79 | 56 | 0 | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-049 | Project_028_Risk-049 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | More integration required | Person_542 | 2015-04-08 | 2016-09-19 01:00 | 0.05 | 3.9852 | 0.9963 | Accept | 0.05 | 0 | 0 | H3 | 3 | Stable | 0.5 | 97 | 139 | 152 | 134.1667 | 0.5 | 97 | 139 | 152 | 134.1667 | 100 | 0 | 1 | 60
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk004 | Project_002_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability of Test Equipment | Person_133 | 2014-03-26 | 2016-08-08 | 0.2 | 0.081443 | 0.016289 | Avoid | 0.2 | 0.081443 | 0.016289 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-034 | Project_005_Risk-034 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project delay causes cost impact to project | Person_470 | 2011-12-02 01:00 | 2016-10-30 01:00 | 0.5 | 16.3745 | 8.1873 | Reduce | 0.1 | 2.5077 | 0.25077 | H3 | 3 | Stable | 0.7 | 98 | 127 | 153 | 126.5 | 0.4 | 19 | 59 | 69 | 54 | 84.6854 | 80 | 1 | 53.2113
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk006 | Project_002_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Additional Pressure Testing | Person_650 | 2014-06-14 | 2016-08-08 | 0.25 | 0.035539 | 0.0088847 | Avoid | 0.25 | 0.035539 | 0.0088847 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk011 | Project_002_Risk011 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Testing | Person_175 | 2014-06-29 | 2016-08-07 | 0.41 | 0.071669 | 0.029384 | Reduce | 0.1 | 0.0088847 | 0.00088847 | H3 | 3 | Stable | 0.9 | 81 | 130 | 154 | 125.8333 | 0.2 | 2 | 43 | 75 | 41.5 | 87.6032 | 75.6098 | 1 | 54.8302
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-048 | Project_028_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Compatibility | Person_542 | 2015-04-08 | 2016-09-19 01:00 | 0.05 | 1.6266 | 0.8133 | Accept | 0.05 | 1.6266 | 0.08133 | H2 | 4 | Stable | 0.9 | 113 | 137 | 148 | 134.8333 | 0.9 | 113 | 137 | 148 | 134.8333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.7 | 101 | 138 | 159 | 135.3333 | 0.1 | 32 | 57 | 77 | 56.1667 | 25.8065 | 20 | 0 | 15.4839
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence and missing info | Person_727 | 2015-11-25 01:00 | 2016-09-19 01:00 | 0.3 | 23.6737 | 11.8369 | Accept | 0.3 | 52.0822 | 23.437 | H2 | 4 | Stable | 0.9 | 105 | 128 | 147 | 127.3333 | 0.9 | 105 | 128 | 147 | 127.3333 | -120 | 0 | 0 | -72
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-043 | Project_008_Risk-043 | Opportunitity | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Joint courseware and tech pubs team | Person_280 | 2014-11-21 01:00 | 2017-05-21 | 0.5 | 28.2191 | 14.1096 | -- | 0.8 | 13.2573 | 10.6058 | H1 | 5 | Stable | [10 empty] | 53.0201 | -60 | 0 | 31.8121
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-059 | Project_008_Risk-059 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Project Resource Efficencies | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 0.2 | 21.6852 | 4.337 | -- | 0.2 | 21.6852 | 4.337 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 01:00 | 2016-10-20 01:00 | 0.2 | 15.8141 | 3.9535 | Accept | 0.2 | 15.8141 | 3.9535 | H2 | 4 | Stable | 0.7 | 92 | 132 | 144 | 127.3333 | 0.7 | 92 | 132 | 144 | 127.3333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-002 | Project_028_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Record / Replay feature | Person_499 | 2014-03-23 | 2016-10-20 01:00 | 0.1 | 71.0212 | 21.3064 | Accept | 0.05 | 71.0212 | 21.3064 | H2 | 4 | Stable | 0.7 | 93 | 121 | 148 | 120.8333 | 0.7 | 93 | 121 | 148 | 120.8333 | 0 | 50 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | EMC Testing | Person_070 | 2016-04-22 | 2016-10-15 01:00 | 0.35 | 13.3529 | 6.6765 | Accept | 0.2 | 13.3529 | 6.6765 | H2 | 4 | Stable | 0.9 | 92 | 123 | 142 | 121 | 0.9 | 92 | 123 | 142 | 121 | 0 | 42.8571 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 0.5 | 9.2728 | 4.6364 | Reduce | 0.3 | 9.2728 | 2.7819 | H2 | 4 | Stable | 0.7 | 101 | 136 | 152 | 132.8333 | 0.4 | 38 | 52 | 73 | 53.1667 | 0 | 40 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 0.3 | 8.7814 | 2.6344 | Reduce | 0.2 | 8.7832 | 1.7566 | H3 | 3 | Stable | 0.7 | 109 | 128 | 145 | 127.6667 | 0.3 | 38 | 55 | 62 | 53.3333 | -0.021119 | 33.3333 | 0 | -0.012672
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_542 | 2015-01-22 01:00 | 2017-08-20 01:00 | 0.35 | 108.3186 | 32.4956 | Accept | 0.2 | 108.3186 | 32.4956 | H2 | 4 | Stable | 0.5 | 99 | 135 | 142 | 130.1667 | 0.5 | 99 | 135 | 142 | 130.1667 | 0 | 42.8571 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Delay of processing | Person_306 | 2016-01-13 01:00 | 2019-08-21 01:00 | 0.15 | 26.3497 | 3.9525 | Reduce | 0.15 | 26.3497 | 3.9525 | H3 | 3 | Improving | 0.9 | 80 | 138 | 141 | 128.8333 | 0.4 | 10 | 51 | 63 | 46.1667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 | 2017-08-20 | 0.25 | 7.7469 | 1.9367 | Reduce | 0.25 | 7.7469 | 1.9367 | H3 | 3 | Stable | 0.5 | 114 | 127 | 154 | 129.3333 | 0.3 | 1 | 46 | 64 | 41.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-131 | Project_032_Risk-131 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Failure | Person_360 | 2012-08-21 | 2017-07-20 | 0.3 | 15.6782 | 4.7035 | Transfer | 0.3 | 15.6782 | 4.7035 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 | 0.05 | 11.3437 | 0.56718 | Reduce | 0.05 | 11.3437 | 0.56718 | H3 | 3 | Stable | 0.6 | 83 | 127 | 159 | 125 | 0.3 | 6 | 43 | 65 | 40.5 | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 | 2017-03-22 | 0.05 | 87.6137 | 4.3807 | Reduce | 0.05 | 87.6137 | 4.3807 | H3 | 3 | Stable | 0.7 | 96 | 131 | 144 | 127.3333 | 0.4 | 22 | 56 | 72 | 53 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_070 | 2016-06-23 | 2016-10-15 01:00 | 0.4 | 5.8286 | 0.58286 | Accept | 0.2 | 5.8286 | 0.58286 | H2 | 4 | Stable | 0.8 | 103 | 123 | 156 | 125.1667 | 0.8 | 103 | 123 | 156 | 125.1667 | 0 | 50 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 | 2017-08-20 | 0.3 | 53.0293 | 15.9088 | Reduce | 0.3 | 53.0293 | 15.9088 | H3 | 3 | Worsening | 0.5 | 106 | 135 | 157 | 133.8333 | 0.2 | 9 | 46 | 68 | 43.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Commercial aspects agreement | Person_480 | 2013-08-21 | 2016-05-22 | 0.02 | 4.8296 | 0.096593 | Transfer | 0.02 | 4.8296 | 0.096593 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 | 2017-08-20 | 0.1 | 34.363 | 3.4363 | Avoid | 0.1 | 34.363 | 3.4363 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 | 2017-08-20 | 0.48 | 33.2985 | 15.9833 | Avoid | 0.48 | 33.2985 | 15.9833 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-126 | Project_032_Risk-126 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supply Chain - Delivery to Contract Requirement | Person_590 | 2012-08-21 | 2016-08-20 | 0.3 | 25.3619 | 7.6086 | Reduce | 0.3 | 25.3619 | 7.6086 | H2 | 4 | Stable | 0.7 | 94 | 132 | 158 | 130 | 0.3 | 8 | 51 | 68 | 46.6667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 0.25 | 0.20788 | 0.068599 | Accept | 0.25 | 0.20788 | 0.068599 | H3 | 3 | Stable | 0.9 | 116 | 124 | 144 | 126 | 0.9 | 116 | 124 | 144 | 126 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | More issues than expected during Qualification | Person_147 | 2017-04-22 | 2017-11-04 01:00 | 0.35 | 1.8788 | 0.28182 | Accept | 0.35 | 1.8788 | 0.28182 | H1 | 5 | Stable | 0.9 | 120 | 123 | 154 | 127.6667 | 0.9 | 120 | 123 | 154 | 127.6667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 0.2 | 9.3941 | 1.8788 | Accept | 0.2 | 9.3941 | 1.8788 | H2 | 4 | Stable | 0.9 | 87 | 132 | 157 | 128.6667 | 0.9 | 87 | 132 | 157 | 128.6667 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK312 | Project_035_RISK312 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Audio Performance inadequate | Person_303 | 2015-06-24 | 2016-08-20 01:00 | 0.2 | 1.8788 | 0.18788 | Accept | 0.2 | 1.8788 | 0.18788 | H3 | 3 | Stable | 0.8 | 109 | 134 | 144 | 131.5 | 0.8 | 109 | 134 | 144 | 131.5 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK313 | Project_035_RISK313 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Deployed Performance inadequate | Person_303 | 2015-05-24 | 2016-09-13 01:00 | 0.3 | 29.4599 | 8.838 | Accept | 0.205 | 18.7882 | 5.6365 | H2 | 4 | Improving | 0.6 | 115 | 125 | 153 | 128 | 0.6 | 115 | 125 | 153 | 128 | 36.2245 | 31.6667 | 0 | 21.7347
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK309 | Project_035_RISK309 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Facility performance unacceptable during Scenario testing | Person_303 | 2015-03-24 | 2016-10-13 01:00 | 0.3 | 1.1273 | 0.22546 | Accept | 0.15 | 1.1273 | 0.22546 | H3 | 3 | Stable | 0.7 | 94 | 137 | 153 | 132.5 | 0.7 | 94 | 137 | 153 | 132.5 | 0 | 50 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK308 | Project_035_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Facility performance during Live trials | Person_303 | 2015-05-24 | 2016-12-21 01:00 | 0.3 | 4.7948 | 0.95895 | Accept | 0.3 | 4.7948 | 0.95895 | H2 | 4 | Stable | 0.6 | 92 | 137 | 157 | 132.8333 | 0.6 | 92 | 137 | 157 | 132.8333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK304 | Project_035_RISK304 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change at Elevation | Person_570 | 2016-09-20 01:00 | 2017-01-20 01:00 | 0.41 | 0.65759 | 0.098638 | Accept | 0.41 | 0.65759 | 0.098638 | H2 | 4 | Stable | 0.7 | 98 | 139 | 155 | 134.8333 | 0.7 | 98 | 139 | 155 | 134.8333 | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK053 | Project_035_RISK053 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Assembly Use of Glass Reinforced Plastics | Person_570 | 2015-03-24 | 2016-08-20 01:00 | 0.2 | 6.7638 | 1.3528 | Accept | 0.1 | 6.7638 | 1.3528 | H3 | 3 | Stable | 0.8 | 103 | 125 | 159 | 127 | 0.8 | 103 | 125 | 159 | 127 | 0 | 50 | 1 | 1.5
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK096 | Project_035_RISK096 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Product Real World Performance | Person_699 | 2015-05-24 | 2017-01-20 01:00 | 0.15 | 0.93941 | 0.14091 | Accept | 0.12 | 0.93941 | 0.14091 | H3 | 3 | Improving | 0.8 | 101 | 129 | 159 | 129.3333 | 0.8 | 101 | 129 | 159 | 129.3333 | 0 | 20 | 1 | 0.6
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_040 | RISK174 | Project_040_RISK174 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Supplier Power Supply quality | Person_687 | 2013-08-20 21:00 | 2014-07-22 | 0.05 | 2.8182 | 0.56365 | Accept | 0.01 | 2.8182 | 0.56365 | H2 | 4 | Stable | 0.6 | 116 | 136 | 158 | 136.3333 | 0.6 | 116 | 136 | 158 | 136.3333 | 0 | 80 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk010 | Project_002_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability | Person_357 | 2014-06-14 | 2016-08-07 | 0.1 | 0 | 0 | Accept | 0.1 | 0 | 0 | H3 | 3 | Worsening | 0.5 | 104 | 135 | 158 | 133.6667 | 0.5 | 104 | 135 | 158 | 133.6667 |  | 0 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk002 | Project_002_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Transducer Element Failures | Person_650 | 2014-06-04 | 2016-08-07 | 0.5 | 2.5834 | 0.64585 | Accept | 0.25 | 2.5834 | 0.64585 | H2 | 4 | Worsening | 0.9 | 112 | 132 | 144 | 130.6667 | 0.9 | 112 | 132 | 144 | 130.6667 | 0 | 50 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 20:00 | 2019-08-07 | 0.61 | 9.3941 | 0.93941 | Accept | 0.61 | 9.3941 | 0.93941 | H1 | 5 | Stable | 0.9 | 104 | 136 | 141 | 131.5 | 0.9 | 104 | 136 | 141 | 131.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Governance and Export Rules | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 0.93941 | 0.23485 | Transfer | 0.25 | 0.93941 | 0.23485 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-109 | Project_011_Risk-109 | Opportunitity | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Environment complexity | Person_187 | 2016-07-21 | 2018-08-21 | 0.25 | 0.14661 | 0.036651 | -- | 0.25 | 0.14661 | 0.036651 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-108 | Project_011_Risk-108 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Offer additional functionality to the customer | Person_147 | 2017-04-22 | 2018-08-21 | 0.1 | 0.34094 | 0.034094 | -- | 0.1 | 0.34094 | 0.034094 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 0.2 | 0.12388 | 0.024775 | Reduce | 0.2 | 0.12388 | 0.024775 | H2 | 4 | Stable | 0.6 | 92 | 128 | 152 | 126 | 0.1 | 10 | 50 | 63 | 45.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 0.4 | 0.51141 | 0.20457 | Avoid | 0.4 | 0.51141 | 0.20457 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.2 | 0.10171 | 0.020343 | -- | 0.2 | 0.10171 | 0.020343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 0.3 | 0.28639 | 0.085917 | Reduce | 0.3 | 0.28639 | 0.085917 | H2 | 4 | Stable | 0.6 | 117 | 140 | 155 | 138.6667 | 0.2 | 29 | 49 | 68 | 48.8333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 2. Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 0.25 | 0 | 0 | -- | 0.25 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2016-07-21 | 2018-05-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 0.3 | 0.10626 | 0.031878 | -- | 0.3 | 0.01932 | 0.005796 | H3 | 3 | Stable | [10 empty] | 81.8181 | 0 | 0 | 49.0909
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-118 | Project_011_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer change environment | Person_187 | 2013-08-21 | 2018-08-21 | 0.1 | 0 | 0 | Avoid | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-116 | Project_011_Risk-116 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Delays to Qualification | Person_147 | 2017-04-22 | 2017-08-19 | 0.25 | 1.7297 | 0.43243 | -- | 0.25 | 1.7297 | 0.43243 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-104 | Project_011_Risk-104 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer delayed in providing Custeomr Furnished Equipment | Person_147 | 2016-06-23 | 2017-04-21 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.9 | 105 | 121 | 150 | 123.1667 | 0.2 | 20 | 59 | 66 | 53.6667 |  | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK222 | Project_024_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Testing Extends beyond target completion | Person_351 | 2017-07-21 | 2018-08-21 | 0.2 | 0.30685 | 0.06137 | Accept | 0.2 | 0.30685 | 0.06137 | H2 | 4 | Stable | 0.9 | 95 | 132 | 146 | 128.1667 | 0.9 | 95 | 132 | 146 | 128.1667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 0.3 | 0.51931 | 0.15579 | -- | 0.15 | 0.51931 | 0.077897 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 0.2 | 0.55005 | 0.11001 | Avoid | 0.2 | 0.55005 | 0.11001 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-123 | Project_011_Risk-123 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | No Requirement for Delta acceptance | Person_187 | 2017-06-23 | 2017-08-20 | 0.2 | 0.63074 | 0.12615 | -- | 0.2 | 0.63074 | 0.12615 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2016-07-21 | 2017-02-19 | 0.15 | 0.28639 | 0.042959 | -- | 0.15 | 0.28639 | 0.042959 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-04-21 | 0.4 | 0.24207 | 0.096828 | -- | 0.4 | 0.24207 | 0.096828 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 | 2018-08-21 | 0.2 | 1.661 | 0.33219 | Reduce | 0.2 | 1.661 | 0.33219 | H2 | 4 | Stable | 0.8 | 106 | 133 | 154 | 132 | 0.2 | 20 | 49 | 64 | 46.6667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2015-04-23 | 2018-08-21 | 0.4 | 1.2444 | 0.49778 | Reduce | 0.4 | 1.2444 | 0.49778 | H2 | 4 | Stable | 0.8 | 100 | 122 | 150 | 123 | 0.4 | 10 | 55 | 66 | 49.3333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 | 2018-08-21 | 0.45 | 0.83883 | 0.37747 | Reduce | 0.45 | 0.83883 | 0.37747 | H2 | 4 | Stable | 0.6 | 88 | 135 | 146 | 129 | 0.4 | 6 | 48 | 66 | 44 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-010 | Project_011_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Rework required following integration of Customer System | Person_142 | 2013-08-21 | 2017-01-20 | 0.4 | 0.66881 | 0.26753 | Reduce | 0.4 | 0.66881 | 0.26753 | H2 | 4 | Stable | 0.9 | 95 | 122 | 149 | 122 | 0.1 | 19 | 57 | 74 | 53.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK024 | Project_012_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component Repair & test costs | Person_359 | 2015-04-04 | 2016-04-12 | 0.7 | 0.84985 | 0.5949 | -- | 0.18 | 0.84985 | 0.15297 | H2 | 4 | Improving | [10 empty] | 0 | 74.2857 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK004 | Project_010_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Export License | Person_359 | 2015-02-18 | 2017-08-20 | 0.8 | 0.18482 | 0.14786 | Reduce | 0.8 | 0.18482 | 0.14786 | H1 | 5 | Worsening | 0.9 | 92 | 122 | 153 | 122.1667 | 0.4 | 34 | 50 | 69 | 50.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.8 | 97 | 130 | 160 | 129.5 | 0.4 | 13 | 57 | 60 | 50.1667 | 0 | 40 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 | 0.7 | 0.92411 | 0.64688 | Reduce | 0.3 | 0.36965 | 0.11089 | H2 | 4 | Stable | 0.9 | 102 | 121 | 153 | 123.1667 | 0.4 | 12 | 48 | 60 | 44 | 60 | 57.1429 | 0 | 36
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 | 2016-04-21 | 0.5 | 4.0661 | 2.033 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.9 | 88 | 138 | 157 | 132.8333 | 0.1 | 33 | 53 | 75 | 53.3333 | 0 | 90 | 1 | 2.7
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.3 | 0.46206 | 0.13862 | H2 | 4 | Improving | 0.5 | 84 | 132 | 153 | 127.5 | 0.3 | 36 | 43 | 69 | 46.1667 | 58.3333 | 50 | 0 | 35
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 | 2017-08-20 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.6 | 92 | 123 | 150 | 122.3333 | 0.1 | 20 | 40 | 71 | 41.8333 | 0 | 50 | 1 | 1.5
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.5 | 80 | 124 | 148 | 120.6667 | 0.4 | 23 | 40 | 76 | 43.1667 | 0 | 25 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Stable | 0.7 | 90 | 131 | 148 | 127 | 0.3 | 34 | 51 | 65 | 50.5 | 0 | 40 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Worsening | [10 empty] | 0 | 37.5 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk010 | Project_002_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability | Person_357 | 2014-06-14 | 2016-08-07 | 0.1 | 3.6965 | 0.36965 | Accept | 0.1 | 3.6965 | 0.36965 | H3 | 3 | Worsening | 0.8 | 112 | 132 | 151 | 131.8333 | 0.8 | 112 | 132 | 151 | 131.8333 | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK84 | Project_010_RISK84 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality issues (for the future) | Person_359 | 2012-09-20 | 2017-08-20 | 0.6 | 2.033 | 1.2198 | Reduce | 0.25 | 0.92411 | 0.23103 | H2 | 4 | Stable | 0.9 | 102 | 139 | 142 | 133.3333 | 0.4 | 32 | 53 | 60 | 50.6667 | 54.5455 | 58.3333 | 0 | 32.7273
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk002 | Project_002_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Transducer Element Failures | Person_650 | 2014-06-04 | 2016-08-07 | 0.5 | 0.92411 | 0.18482 | Accept | 0.25 | 0.92411 | 0.18482 | H2 | 4 | Worsening | 0.7 | 82 | 124 | 159 | 122.8333 | 0.7 | 82 | 124 | 159 | 122.8333 | 0 | 50 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 0.3 | 1.8482 | 0.55447 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.5 | 112 | 140 | 151 | 137.1667 | 0.4 | 16 | 50 | 66 | 47 | 0 | 33.3333 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.9 | 96 | 130 | 146 | 127 | 0.1 | 30 | 48 | 75 | 49.5 | 90 | 75 | 1 | 56.25
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-200 | Project_027_Risk-200 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Sucession Planning for key team members | Person_060 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.2 | 7.3175 | 1.4635 | Reduce | 0.05 | 7.3175 | 0.36588 | H2 | 4 | Stable | 0.6 | 87 | 124 | 153 | 122.6667 | 0.3 | 39 | 53 | 71 | 53.6667 | 0 | 75 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-189 | Project_027_Risk-189 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Major Component obsolescence | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 8.3972 | 2.5191 | Reduce | 0.08 | 8.3972 | 0.67177 | H2 | 4 | Stable | 0.8 | 96 | 138 | 151 | 133.1667 | 0.1 | 30 | 42 | 61 | 43.1667 | 0 | 73.3333 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-201 | Project_027_Risk-201 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Transition into Support | Person_027 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0.5 | 68.3768 | 34.1884 | Reduce | 0.05 | 38.387 | 1.9193 | H2 | 4 | Stable | 0.6 | 82 | 128 | 141 | 122.5 | 0.1 | 33 | 57 | 60 | 53.5 | 43.8597 | 90 | 0 | 26.3158
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-010 | Project_005_Risk-010 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Risk that required resources (people and rigs) will not be available as required due to other projects/bids (Customer & Internal) | Person_470 | 2011-11-11 01:00 | 2016-11-18 01:00 | 0.25 | 13.2195 | 1.5863 | Accept | 0.1 | 13.2195 | 1.5863 | H3 | 3 | Stable | 0.5 | 83 | 138 | 151 | 131 | 0.5 | 83 | 138 | 151 | 131 | 0 | 60 | 1 | 1.8
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-188 | Project_027_Risk-188 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Unidentified Technical Legacy Issue | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 20.0332 | 2.0033 | Reduce | 0.05 | 20.0332 | 1.0017 | H3 | 3 | Stable | 0.6 | 83 | 135 | 151 | 129 | 0.2 | 15 | 59 | 66 | 52.8333 | 0 | 50 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-193 | Project_027_Risk-193 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | A greater number of arising technical queries | Person_110 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 13.7953 | 4.1386 | Reduce | 0.05 | 13.7953 | 0.68977 | H3 | 3 | Stable | 0.9 | 92 | 140 | 156 | 134.6667 | 0.2 | 16 | 42 | 63 | 41.1667 | 0 | 83.3333 | 1 | 2.5
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-060 | Project_005_Risk-060 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Technical Acceptance may be more difficult than anticipated | Person_470 | 2014-06-11 | 2016-10-18 01:00 | 0.5 | 16.1945 | 1.6195 | Accept | 0.05 | 16.1945 | 1.6195 | H3 | 3 | Stable | 0.8 | 86 | 126 | 153 | 123.8333 | 0.8 | 86 | 126 | 153 | 123.8333 | 0 | 90 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 0.5 | 35.9878 | 21.5927 | Accept | 0.45 | 15.5947 | 0.77974 | H2 | 4 | Stable | 0.6 | 91 | 136 | 149 | 130.6667 | 0.6 | 91 | 136 | 149 | 130.6667 | 56.6667 | 10 | 0 | 34
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation | Person_565 | 2018-05-22 | 2018-08-21 | 0.25 | 27.5907 | 2.7591 | Accept | 0.25 | 27.5907 | 2.7591 | H3 | 3 | Stable | 0.8 | 113 | 131 | 146 | 130.5 | 0.8 | 113 | 131 | 146 | 130.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 0.5 | 8.3972 | 0.83972 | Accept | 0.5 | 8.3972 | 0.41986 | H2 | 4 | Improving | 0.9 | 84 | 124 | 158 | 123 | 0.9 | 84 | 124 | 158 | 123 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 0.3 | 19.1935 | 0.95968 | Accept | 0.3 | 19.1935 | 0.95968 | H2 | 4 | Stable | 0.8 | 118 | 121 | 152 | 125.6667 | 0.8 | 118 | 121 | 152 | 125.6667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.41 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -2.5 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.61 | 0.25667 | 0.15657 | Reduce | 0.5 | 0.25667 | 0.12834 | H2 | 4 | Stable | 0.5 | 92 | 122 | 151 | 121.8333 | 0.4 | 36 | 46 | 76 | 49.3333 | 0 | 18.0328 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2014-01-21 01:00 | 2017-11-20 01:00 | 0.4 | 1.078 | 0.43121 | Reduce | 0.2 | 1.078 | 0.2156 | H3 | 3 | Stable | 0.9 | 83 | 136 | 146 | 128.8333 | 0.4 | 18 | 55 | 65 | 50.5 | 0 | 50 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-118 | Project_029_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Acceptance Schedule is longer in duration/delayed | Person_102 | 2015-12-22 01:00 | 2016-12-21 01:00 | 0.55 | 0.56468 | 0.31057 | Reduce | 0.55 | 0.56468 | 0.31057 | H2 | 4 | Stable | 0.6 | 112 | 132 | 151 | 131.8333 | 0.1 | 33 | 52 | 67 | 51.3333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 | 2017-07-20 | 0.1 | 6.4168 | 3.2084 | Accept | 0.1 | 1.5614 | 0.15614 | H2 | 4 | Stable | 0.7 | 119 | 128 | 151 | 130.3333 | 0.7 | 119 | 128 | 151 | 130.3333 | 75.6667 | 0 | 0 | 45.4
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-038 | Project_029_Risk-038 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Integration and Reliability | Person_216 | 2014-03-23 | 2016-11-19 01:00 | 0.15 | 1.155 | 0.17325 | Reduce | 0.15 | 0.77001 | 0.1155 | H3 | 3 | Stable | 0.7 | 98 | 138 | 141 | 131.8333 | 0.2 | 19 | 53 | 75 | 51 | 33.3333 | 0 | 1 | 20
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2017-11-19 01:00 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-113 | Project_029_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | SW Delivery to INtegration (including bug fixes post delivery) | Person_199 | 2014-07-22 | 2016-11-19 01:00 | 0.4 | 0.64168 | 0.25667 | Avoid | 0.4 | 0.84702 | 0.33881 | H2 | 4 | Worsening | [10 empty] | -32 | 0 | 0 | -19.2
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2016-10-21 01:00 | 0.6 | 0.89835 | 0.53901 | Transfer | 0.6 | 0.89835 | 0.53901 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-120 | Project_032_Risk-120 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | System STTE Equipment Roll Out | Person_768 | 2014-03-23 | 2017-03-23 | 0.9 | 0.12834 | 0.10267 | Accept | 0.9 | 0.12834 | 0.10267 | H2 | 4 | Stable | 0.7 | 104 | 129 | 141 | 126.8333 | 0.7 | 104 | 129 | 141 | 126.8333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2015-07-31 | 2017-05-15 | 0.35 | 0.85557 | 0.29945 | Reduce | 0.35 | 0.92402 | 0.32341 | H2 | 4 | Stable | 0.6 | 94 | 139 | 157 | 134.5 | 0.1 | 20 | 41 | 65 | 41.5 | -8.0001 | 0 | 0 | -4.8001
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-105 | Project_029_Risk-105 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Changes to CE markings | Person_692 | 2015-05-24 | 2020-11-19 01:00 | 0.8 | 0.51334 | 0.41067 | Reduce | 0.3 | 0.51334 | 0.154 | H3 | 3 | Stable | 0.9 | 87 | 138 | 159 | 133 | 0.2 | 28 | 58 | 62 | 53.6667 | 0 | 62.5 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-028 | Project_029_Risk-028 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Assets (for system integration - repair of test assets) | Person_102 | 2015-02-21 01:00 | 2020-05-22 | 0.4 | 1.2834 | 0.51334 | Reduce | 0.2 | 1.2834 | 0.25667 | H3 | 3 | Stable | 0.5 | 82 | 125 | 152 | 122.3333 | 0.4 | 19 | 59 | 74 | 54.8333 | 0 | 50 | 1 | 1.5
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2016-05-23 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.6 | 91 | 134 | 143 | 128.3333 | 0.1 | 11 | 55 | 78 | 51.5 | 0 | 28.5714 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Suppliers | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 1.54 | 0.30801 | Accept | 0.15 | 0.77001 | 0.154 | H2 | 4 | Stable | 0.7 | 114 | 137 | 151 | 135.5 | 0.7 | 114 | 137 | 151 | 135.5 | 50 | 0 | 0 | 30
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 0.87268 | 0.43634 | Accept | 0.2 | 0.87268 | 0.34907 | H2 | 4 | Stable | 0.5 | 97 | 138 | 148 | 132.8333 | 0.5 | 97 | 138 | 148 | 132.8333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Local customer Engineers in country | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 0.94968 | 0.28491 | Accept | 0.1 | 0.94968 | 0.18994 | H2 | 4 | Stable | 0.8 | 105 | 132 | 154 | 131.1667 | 0.8 | 105 | 132 | 154 | 131.1667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence | Person_455 | 2016-05-23 | 2020-05-23 | 0.3 | 27.1644 | 0.81493 | Accept | 0.3 | 12.8336 | 1.2834 | H2 | 4 | Stable | 0.9 | 95 | 127 | 152 | 125.8333 | 0.9 | 95 | 127 | 152 | 125.8333 | 52.7559 | 0 | 0 | 31.6535
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2014-07-22 | 2017-11-19 01:00 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.7 | 95 | 132 | 157 | 130 | 0.1 | 19 | 52 | 68 | 49.1667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2017-10-14 01:00 | 0.41 | 6.4168 | 2.6309 | Transfer | 0.41 | 0 | 0 | H1 | 5 | Stable | [10 empty] | 100 | 0 | 0 | 60
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub-system FPGA | Person_216 | 2014-02-20 01:00 | 2017-05-22 | 0.3 | 1.54 | 0.46201 | Reduce | 0.2 | 1.155 | 0.231 | H3 | 3 | Stable | 0.6 | 109 | 122 | 149 | 124.3333 | 0.4 | 22 | 56 | 72 | 53 | 25 | 33.3333 | 1 | 16
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK153 | Project_024_RISK153 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Processor memory/performance Issue | Person_331 | 2016-06-23 | 2017-03-22 | 0.3 | 112.3463 | 33.7039 | Reduce | 0.2 | 56.0866 | 11.2173 | H2 | 4 | Stable | 0.7 | 81 | 137 | 143 | 128.6667 | 0.3 | 23 | 46 | 77 | 47.3333 | 50.077 | 33.3333 | 0 | 30.0462
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK155 | Project_024_RISK155 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Late availability of Parameters | Person_534 | 2016-03-23 | 2016-09-11 01:00 | 0.3 | 4.1113 | 1.2334 | Reduce | 0.3 | 4.1113 | 1.2334 | H1 | 5 | Stable | 0.7 | 99 | 137 | 154 | 133.5 | 0.2 | 3 | 46 | 60 | 41.1667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Consumables | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 5.4096 | 0.54096 | Accept | 0.2 | 5.4096 | 0.54096 | H2 | 4 | Stable | 0.6 | 93 | 139 | 155 | 134 | 0.6 | 93 | 139 | 155 | 134 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 7. Finance | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 25.966 | 7.7898 | Accept | 0.2 | 25.966 | 7.7898 | H2 | 4 | Stable | 0.7 | 105 | 139 | 154 | 135.8333 | 0.7 | 105 | 139 | 154 | 135.8333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 62.3617 | 3.1181 | Accept | 0.15 | 62.3617 | 3.1181 | H2 | 4 | Stable | 0.7 | 89 | 129 | 160 | 127.5 | 0.7 | 89 | 129 | 160 | 127.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 4.5441 | 0.45441 | Accept | 0.2 | 4.5441 | 0.45441 | H2 | 4 | Stable | 0.6 | 80 | 127 | 155 | 123.8333 | 0.6 | 80 | 127 | 155 | 123.8333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport Routes | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 0.67512 | 0.13502 | Accept | 0.15 | 0.67512 | 0.13502 | H2 | 4 | Stable | 0.9 | 113 | 133 | 154 | 133.1667 | 0.9 | 113 | 133 | 154 | 133.1667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK201 | Project_024_RISK201 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Indication mode failure | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.25 | 1.6835 | 0.42087 | Reduce | 0.2 | 1.6835 | 0.33669 | H3 | 3 | Stable | 0.6 | 111 | 122 | 157 | 126 | 0.4 | 5 | 57 | 74 | 51.1667 | 0 | 20 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Internal Quality Issues | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 1.3502 | 0.54009 | Accept | 0.2 | 1.3502 | 0.54009 | H2 | 4 | Stable | 0.9 | 84 | 133 | 149 | 127.5 | 0.9 | 84 | 133 | 149 | 127.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk017 | Project_042_Risk017 | Threat | Financial Contingency | Open | H2 | 4 | 6. Contractual/Legal | Liquidated Damages | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 1.9128 | 0.19128 | Accept | 0.4 | 1.9128 | 0.19128 | H2 | 4 | Stable | 0.7 | 113 | 133 | 148 | 132.1667 | 0.7 | 113 | 133 | 148 | 132.1667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Repairs | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 1.3502 | 0.47258 | Accept | 0.25 | 1.3502 | 0.47258 | H2 | 4 | Stable | 0.9 | 83 | 130 | 157 | 126.6667 | 0.9 | 83 | 130 | 157 | 126.6667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk016 | Project_042_Risk016 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport/Delivery Speed | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 19.4745 | 5.8424 | Accept | 0.1 | 19.4745 | 5.8424 | H2 | 4 | Stable | 0.5 | 104 | 129 | 143 | 127.1667 | 0.5 | 104 | 129 | 143 | 127.1667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Country Stability | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 0.35487 | 0.035487 | Accept | 0.4 | 0.35487 | 0.035487 | H2 | 4 | Stable | 0.8 | 80 | 133 | 155 | 127.8333 | 0.8 | 80 | 133 | 155 | 127.8333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 1.6835 | 0.42087 | Accept | 0.1 | 1.6835 | 0.42087 | H2 | 4 | Stable | 0.5 | 114 | 136 | 146 | 134 | 0.5 | 114 | 136 | 146 | 134 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK213 | Project_024_RISK213 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Rigs requireaccreditation as "Special to Type" Test equipment | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.3 | 33.7558 | 10.1267 | Reduce | 0.2 | 23.3694 | 4.6739 | H2 | 4 | Stable | 0.6 | 102 | 129 | 155 | 128.8333 | 0.1 | 15 | 41 | 78 | 42.8333 | 30.7692 | 33.3333 | 0 | 18.4615
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK179 | Project_024_RISK179 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Testing Required | Person_289 | 2016-12-21 01:00 | 2017-05-22 | 0.5 | 3.5054 | 1.7527 | Reduce | 0.4 | 3.5054 | 1.4022 | H2 | 4 | Stable | 0.7 | 88 | 137 | 141 | 129.5 | 0.1 | 7 | 55 | 61 | 48 | 0 | 20 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 30.2764 | 12.1106 | Accept | 0.2 | 30.2764 | 12.1106 | H2 | 4 | Stable | 0.9 | 104 | 140 | 155 | 136.5 | 0.9 | 104 | 140 | 155 | 136.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 0.25 | 4.847 | 1.4541 | Accept | 0.25 | 4.847 | 1.4541 | H3 | 3 | Stable | 0.7 | 91 | 131 | 155 | 128.3333 | 0.7 | 91 | 131 | 155 | 128.3333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK218 | Project_024_RISK218 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | System issues general | Person_289 | 2016-08-21 01:00 | 2016-10-04 01:00 | 0.4 | 90.8811 | 36.3524 | Reduce | 0.3 | 39.3904 | 11.8171 | H1 | 5 | Stable | 0.9 | 104 | 138 | 150 | 134.3333 | 0.3 | 12 | 45 | 67 | 43.1667 | 56.6571 | 25 | 0 | 33.9943
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | More issues than expected during Qualification | Person_147 | 2017-04-22 | 2017-11-04 | 0.35 | 11.9444 | 5.9722 | Accept | 0.35 | 11.9444 | 5.9722 | H1 | 5 | Stable | 0.8 | 103 | 134 | 156 | 132.5 | 0.8 | 103 | 134 | 156 | 132.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK180 | Project_024_RISK180 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | High Accelerated Life Testing (HALT) | Person_289 | 2016-12-21 01:00 | 2017-05-03 | 0.4 | 10.4903 | 4.1961 | Reduce | 0.2 | 10.4903 | 2.0981 | H2 | 4 | Stable | 0.8 | 94 | 137 | 142 | 130.6667 | 0.2 | 25 | 56 | 79 | 54.6667 | 0 | 50 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 0.2 | 35.885 | 14.354 | Accept | 0.2 | 35.885 | 25.4784 | H2 | 4 | Stable | 0.9 | 116 | 130 | 155 | 131.8333 | 0.9 | 116 | 130 | 155 | 131.8333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.9 | 91 | 123 | 154 | 122.8333 | 0.1 | 5 | 43 | 60 | 39.5 | 0 | 60 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 | 0.05 | 30.7697 | 15.0772 | Accept | 0.05 | 30.7697 | 15.0772 | H2 | 4 | Stable | 0.8 | 117 | 135 | 159 | 136 | 0.8 | 117 | 135 | 159 | 136 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP068 | Project_024_OPP068 | Opportunitity | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Customer acceptance of iterative sell-off approach | Person_535 | 2016-07-21 | 2017-11-19 01:00 | 0.2 | 9.3045 | 1.8609 | -- | 0.3 | 9.3045 | 2.7913 | H2 | 4 | Stable | [10 empty] | 0 | -50 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 0.8 | 14.541 | 5.8164 | Accept | 0.6 | 14.541 | 5.8164 | H1 | 5 | Stable | 0.9 | 108 | 137 | 159 | 135.8333 | 0.9 | 108 | 137 | 159 | 135.8333 | 0 | 25 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK166 | Project_024_RISK166 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Requirements Acceptance Criteria | Person_288 | 2016-04-10 | 2017-03-06 01:00 | 0.4 | 3.843 | 1.5372 | Reduce | 0.2 | 1.2464 | 0.24927 | H2 | 4 | Improving | 0.8 | 112 | 127 | 142 | 127 | 0.3 | 19 | 54 | 74 | 51.5 | 67.5676 | 50 | 0 | 40.5405
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 | 2016-08-20 | 0.1 | 1.3502 | 0.33756 | Accept | 0.1 | 1.3502 | 0.33756 | H2 | 4 | Stable | 0.6 | 93 | 124 | 155 | 124 | 0.6 | 93 | 124 | 155 | 124 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK196 | Project_024_RISK196 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional Trials - Cost of Labour | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.3 | 0.95209 | 0.28563 | Reduce | 0.2 | 0.95209 | 0.19042 | H2 | 4 | Worsening | 0.7 | 117 | 126 | 155 | 129.3333 | 0.3 | 24 | 52 | 69 | 50.1667 | 0 | 33.3333 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 | 0.2 | 2.0816 | 0.20816 | Accept | 0.2 | 2.0816 | 0.20816 | H3 | 3 | Improving | 0.7 | 114 | 140 | 156 | 138.3333 | 0.7 | 114 | 140 | 156 | 138.3333 | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-187 | Project_027_Risk-187 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Loss of a major sub-contractor | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.12 | 17.0765 | 1.7076 | Accept | 0.12 | 17.0765 | 1.7076 | H3 | 3 | Stable | 0.9 | 113 | 139 | 142 | 135.1667 | 0.9 | 113 | 139 | 142 | 135.1667 | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-196 | Project_027_Risk-196 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Aging equipment resulting in increasing failure rates | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 22.8501 | 6.855 | Accept | 0.1 | 22.8501 | 6.855 | H3 | 3 | Stable | 0.8 | 117 | 137 | 146 | 135.1667 | 0.8 | 117 | 137 | 146 | 135.1667 | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK244 | Project_024_RISK244 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Blue Screen Of Death (BSOD) | Person_534 | 2016-04-22 | 2016-07-21 | 0.1 | 15.1468 | 1.5147 | Reduce | 0.1 | 15.1468 | 1.5147 | H3 | 3 | Stable | 0.8 | 101 | 133 | 156 | 131.5 | 0.4 | 21 | 56 | 74 | 53.1667 | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-185 | Project_027_Risk-185 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier manufacturing issues | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.6 | 19.9938 | 5.9981 | Accept | 0.05 | 19.9938 | 5.9981 | H3 | 3 | Stable | 0.7 | 119 | 135 | 158 | 136.1667 | 0.7 | 119 | 135 | 158 | 136.1667 | 0 | 91.6667 | 1 | 2.75
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-186 | Project_027_Risk-186 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Potential for composite suppliers going out of business | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 11.1654 | 2.2331 | Accept | 0.1 | 11.1654 | 2.2331 | H3 | 3 | Stable | 0.9 | 105 | 122 | 141 | 122.3333 | 0.9 | 105 | 122 | 141 | 122.3333 | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.2 | 20.8767 | 4.1753 | H2 | 4 | Stable | 0.9 | 80 | 135 | 157 | 129.5 | 0.4 | 17 | 43 | 68 | 42.8333 | 50 | 50 | 0 | 30
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.49667 | 93.5036 | 46.4402 | Reduce | 0.29076 | 78.3005 | 22.767 | H1 | 5 | Worsening | 0.7 | 101 | 133 | 145 | 129.6667 | 0.3 | 4 | 40 | 65 | 38.1667 | 16.2594 | 41.457 | 0 | 9.7556
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials - Increased Cost | Person_073 | 2016-05-23 | 2017-02-19 01:00 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.8 | 110 | 137 | 150 | 134.6667 | 0.1 | 1 | 53 | 74 | 47.8333 | 0 | 50 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | People unable to sustain the pace | Person_413 | 2015-11-21 01:00 | 2017-05-22 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.9 | 111 | 130 | 156 | 131.1667 | 0.3 | 30 | 44 | 78 | 47.3333 | 0 | 5 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-194 | Project_027_Risk-194 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | The effect of specialist supplier obsolescence on complex assemblies | Person_074 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.08 | 1.3502 | 0.27005 | Accept | 0.08 | 1.3502 | 0.27005 | H3 | 3 | Stable | 0.7 | 114 | 129 | 159 | 131.5 | 0.7 | 114 | 129 | 159 | 131.5 | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK286 | Project_024_RISK286 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Requirement sell off more difficult than expected | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.5 | 10.9057 | 5.4529 | Reduce | 0.4 | 7.7898 | 3.1159 | H1 | 5 | Worsening | 0.7 | 107 | 127 | 149 | 127.3333 | 0.2 | 29 | 47 | 76 | 48.8333 | 28.5714 | 20 | 0 | 17.1429
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK288 | Project_024_RISK288 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Unplanned obsolescence and/or repairs to rig assets. | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.6 | 5.8424 | 3.5054 | Reduce | 0.6 | 5.8424 | 3.5054 | H1 | 5 | Stable | 0.7 | 108 | 136 | 151 | 133.8333 | 0.4 | 38 | 59 | 76 | 58.3333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.4 | 25.4467 | 10.1787 | Reduce | 0.3 | 10.9057 | 3.2717 | H1 | 5 | Stable | 0.9 | 94 | 132 | 158 | 130 | 0.4 | 12 | 41 | 78 | 42.3333 | 57.1429 | 25 | 0 | 34.2857
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-017 | Project_029_Risk-017 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Additional Obsolescence - System | Person_102 | 2016-05-23 | 2017-10-21 01:00 | 0.5 | 2.5966 | 0.51932 | Accept | 0.1 | 2.5966 | 0.51932 | H3 | 3 | Stable | 0.7 | 99 | 134 | 142 | 129.5 | 0.7 | 99 | 134 | 142 | 129.5 | 0 | 80 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-111 | Project_029_Risk-111 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Unplanned courier cost and T&S for any transportation of hardware during Integration phase | Person_692 | 2015-07-22 | 2016-10-21 01:00 | 0.8 | 30.562 | 24.4496 | Accept | 0.8 | 30.562 | 24.4496 | H2 | 4 | Stable | 0.6 | 81 | 140 | 156 | 132.8333 | 0.6 | 81 | 140 | 156 | 132.8333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK290 | Project_024_RISK290 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance Strategy decisions being made too late | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.5 | 12.0742 | 6.0371 | Avoid | 0.1 | 12.0742 | 1.2074 | H3 | 3 | Stable | [10 empty] | 0 | 80 | 1 | 2.4
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2016-05-23 | 2018-05-22 | 0.4 | 15.0863 | 7.5431 | Accept | 0.3 | 15.0863 | 7.5431 | H2 | 4 | Stable | 0.5 | 94 | 125 | 153 | 124.5 | 0.5 | 94 | 125 | 153 | 124.5 | 0 | 25 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2019-10-14 01:00 | 0.2 | 29.1079 | 19.2112 | Accept | 0.2 | 29.1079 | 14.845 | H3 | 3 | Stable | 0.9 | 86 | 131 | 142 | 125.3333 | 0.9 | 86 | 131 | 142 | 125.3333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-026 | Project_029_Risk-026 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | platform Integration - SW support | Person_102 | 2016-09-02 01:00 | 2019-09-24 01:00 | 0.5 | 2.7146 | 2.7146 | Accept | 0.4 | 2.7146 | 2.7146 | H3 | 3 | Stable | 0.8 | 81 | 129 | 160 | 126.1667 | 0.8 | 81 | 129 | 160 | 126.1667 | 0 | 20 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2015-07-22 | 2017-11-19 01:00 | 0.3 | 9.8671 | 1.9734 | Accept | 0.2 | 9.8671 | 1.9734 | H3 | 3 | Stable | 0.6 | 111 | 140 | 150 | 136.8333 | 0.6 | 111 | 140 | 150 | 136.8333 | 0 | 33.3333 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2017-10-20 01:00 | 0.03 | 15.5796 | 6.2318 | Accept | 0.1 | 15.5796 | 6.2318 | H2 | 4 | Stable | 0.6 | 99 | 126 | 153 | 126 | 0.6 | 99 | 126 | 153 | 126 | 0 | -233.3333 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK152 | Project_024_RISK152 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Component Damage | Person_674 | 2016-04-06 | 2016-10-21 01:00 | 0.1 | 12.983 | 2.5966 | Accept | 0.1 | 12.983 | 2.5966 | H3 | 3 | Stable | 0.6 | 112 | 137 | 150 | 135 | 0.6 | 112 | 137 | 150 | 135 | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment environmental failure | Person_289 | 2016-05-23 | 2016-12-02 01:00 | 0.3 | 9.8671 | 0.98671 | Accept | 0.3 | 9.8671 | 0.98671 | H1 | 5 | Improving | 0.9 | 110 | 138 | 146 | 134.6667 | 0.9 | 110 | 138 | 146 | 134.6667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Retained systems re-design or modification | Person_289 | 2016-08-20 01:00 | 2016-12-02 01:00 | 0.05 | 4.6739 | 1.8696 | Accept | 0.05 | 4.6739 | 1.8696 | H2 | 4 | Improving | 0.7 | 94 | 137 | 150 | 132 | 0.7 | 94 | 137 | 150 | 132 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Mission System not compatible with platform systems | Person_289 | 2016-07-21 | 2017-02-19 01:00 | 0.1 | 32.4575 | 1.2983 | Accept | 0.1 | 32.4575 | 1.2983 | H3 | 3 | Stable | 0.7 | 116 | 128 | 152 | 130 | 0.7 | 116 | 128 | 152 | 130 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK202 | Project_024_RISK202 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Mode Specific | Person_448 | 2015-09-04 01:00 | 2017-02-19 01:00 | 0.2 | 7.1867 | 3.5934 | Accept | 0.2 | 7.1867 | 3.5934 | H3 | 3 | Stable | 0.9 | 92 | 127 | 143 | 123.8333 | 0.9 | 92 | 127 | 143 | 123.8333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK204 | Project_024_RISK204 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Stabilisation | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.4 | 4.4221 | 2.2111 | Accept | 0.4 | 4.4221 | 2.2111 | H1 | 5 | Improving | 0.6 | 101 | 127 | 156 | 127.5 | 0.6 | 101 | 127 | 156 | 127.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK203 | Project_024_RISK203 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Detection/Tracking modifications | Person_448 | 2016-10-21 01:00 | 2017-02-19 01:00 | 0.1 | 3.1818 | 1.5909 | Accept | 0.1 | 3.1818 | 1.5909 | H3 | 3 | Improving | 0.7 | 90 | 139 | 156 | 133.6667 | 0.7 | 90 | 139 | 156 | 133.6667 | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_468 | 2016-11-20 | 2018-11-20 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.1 | 6.431 | 0.6431 | H3 | 3 | Stable | 0.5 | 95 | 128 | 158 | 127.5 | 0.3 | 6 | 50 | 76 | 47 | -47.0588 | 33.3333 | 1 | -27.2353
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R81 | Project_041_R81 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Re-imaging of PC's - additional material | Person_515 | 2016-11-20 | 2017-10-21 | 0.5 | 0.21008 | 0.10504 | Avoid | 0.5 | 0.21008 | 0.10504 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R85 | Project_041_R85 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Go to Offshore initiative | Person_468 | 2016-11-20 | 2018-05-22 | 0.15 | 7.7172 | 1.1576 | -- | 0.15 | 7.7172 | 1.1576 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_368 | 2016-11-20 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.5 | 96 | 125 | 155 | 125.1667 | 0.1 | 32 | 56 | 70 | 54.3333 | 0 | 50 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R43 | Project_041_R43 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Procurement - Component and Supplier Leadtime | Person_468 | 2016-11-20 | 2018-05-22 | 0.25 | 10.9327 | 2.7332 | Reduce | 0.15 | 10.9327 | 1.6399 | H2 | 4 | Stable | 0.5 | 112 | 128 | 159 | 130.5 | 0.2 | 16 | 47 | 74 | 46.3333 | 0 | 40 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2016-11-20 | 2018-05-22 | 0.75 | 10.7184 | 8.0388 | Reduce | 0.75 | 5.3592 | 4.0194 | H1 | 5 | Worsening | 0.7 | 120 | 134 | 146 | 133.6667 | 0.1 | 14 | 58 | 67 | 52.1667 | 50 | 0 | 0 | 30
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R86 | Project_041_R86 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sharing Attrition Stock with Warranty Spares pool | Person_501 | 2016-11-20 | 2018-05-22 | 0.5 | 3.1083 | 1.5542 | Exploit | 0.5 | 3.1083 | 1.5542 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK200 | Project_024_RISK200 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Height Finding | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.35 | 1.9722 | 0.98609 | Accept | 0.35 | 1.9722 | 0.98609 | H2 | 4 | Worsening | 0.5 | 108 | 128 | 150 | 128.3333 | 0.5 | 108 | 128 | 150 | 128.3333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK209 | Project_024_RISK209 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Major Return to Service | Person_073 | 2016-11-20 01:00 | 2017-05-22 | 0.3 | 2.5081 | 1.2541 | Accept | 0.3 | 2.5081 | 1.2541 | H1 | 5 | Stable | 0.8 | 100 | 133 | 157 | 131.5 | 0.8 | 100 | 133 | 157 | 131.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK206 | Project_024_RISK206 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Simulator Updates | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.1 | 7.0313 | 3.5156 | Accept | 0.1 | 7.0313 | 3.5156 | H3 | 3 | Stable | 0.8 | 99 | 124 | 150 | 124.1667 | 0.8 | 99 | 124 | 150 | 124.1667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2016-11-20 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.05 | 0.68598 | 0.034299 | H3 | 3 | Stable | 0.9 | 81 | 125 | 160 | 123.5 | 0.2 | 7 | 56 | 72 | 50.5 | 0 | 80 | 1 | 2.4
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Overland performance | Person_448 | 2016-06-23 | 2017-05-21 | 0.25 | 1.2519 | 0.31298 | Accept | 0.25 | 1.2519 | 0.31298 | H2 | 4 | Improving | 0.6 | 117 | 121 | 148 | 124.8333 | 0.6 | 117 | 121 | 148 | 124.8333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Qual failure | Person_289 | 2016-06-22 | 2016-11-20 01:00 | 0.4 | 3.7514 | 0.37514 | Accept | 0.4 | 3.7514 | 0.37514 | H1 | 5 | Improving | 0.9 | 119 | 129 | 143 | 129.6667 | 0.9 | 119 | 129 | 143 | 129.6667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R29 | Project_041_R29 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Attrition | Person_515 | 2016-11-20 | 2018-05-22 | 0.1 | 3.6014 | 0.36014 | Reduce | 0.05 | 3.6014 | 0.18007 | H3 | 3 | Stable | 0.5 | 111 | 130 | 147 | 129.6667 | 0.3 | 23 | 53 | 69 | 50.6667 | 0 | 50 | 1 | 1.5
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2016-11-20 | 2017-07-21 | 0.1 | 21.8655 | 2.1865 | Reduce | 0.05 | 21.8655 | 1.0933 | H2 | 4 | Stable | 0.8 | 96 | 122 | 156 | 123.3333 | 0.3 | 2 | 44 | 71 | 41.5 | 0 | 50 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2016-11-20 | 2018-05-22 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Stable | 0.5 | 93 | 134 | 143 | 128.6667 | 0.3 | 16 | 47 | 63 | 44.5 | 0 | 60 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK210 | Project_024_RISK210 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Performance | Person_532 | 2016-06-22 | 2017-02-19 01:00 | 0.3 | 0.6088 | 0.1522 | Accept | 0.3 | 0.6088 | 0.1522 | H2 | 4 | Stable | 0.6 | 101 | 123 | 149 | 123.6667 | 0.6 | 101 | 123 | 149 | 123.6667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Unidentified Change Requests | Person_693 | 2016-11-20 | 2017-09-20 | 0.5 | 1.2005 | 0.60023 | Reduce | 0.1 | 0.51019 | 0.051019 | H3 | 3 | Stable | 0.7 | 88 | 139 | 160 | 134 | 0.1 | 7 | 41 | 66 | 39.5 | 57.5001 | 80 | 1 | 36.9001
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Additional minor releases | Person_073 | 2016-05-23 | 2017-08-20 01:00 | 0.5 | 3.3227 | 0.83067 | Accept | 0.5 | 3.3227 | 0.83067 | H1 | 5 | Stable | 0.5 | 115 | 123 | 150 | 126.1667 | 0.5 | 115 | 123 | 150 | 126.1667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_468 | 2016-11-20 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.1 | 0.77172 | 0.077172 | H3 | 3 | Stable | 0.5 | 109 | 139 | 151 | 136 | 0.4 | 23 | 52 | 72 | 50.5 | 0 | 60 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production or Engineering | Person_359 | 2016-11-20 | 2018-05-22 | 0.15 | 1.1576 | 0.17364 | Reduce | 0.1 | 1.1576 | 0.11576 | H3 | 3 | Stable | 0.5 | 82 | 139 | 160 | 133 | 0.3 | 26 | 55 | 62 | 51.3333 | 0 | 33.3333 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R13 | Project_041_R13 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Loss of key personnel | Person_359 | 2016-11-20 | 2017-08-20 | 0.5 | 0.59165 | 0.29583 | Reduce | 0.1 | 0.59165 | 0.059165 | H3 | 3 | Stable | 0.7 | 98 | 125 | 146 | 124 | 0.2 | 37 | 49 | 67 | 50 | 0 | 80 | 1 | 2.4
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs [technical scope] | Person_466 | 2016-05-23 | 2019-07-21 | 0.35 | 9.505 | 3.3267 | Reduce | 0.35 | 9.505 | 3.3267 | H2 | 4 | Stable | 0.6 | 100 | 131 | 156 | 130 | 0.3 | 21 | 45 | 78 | 46.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.5 | 3.5934 | 1.7967 | H2 | 4 | Stable | 0.9 | 99 | 128 | 157 | 128 | 0.1 | 2 | 46 | 75 | 43.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | HW - additional unplanned design effort | Person_216 | 2016-05-23 | 2019-10-21 01:00 | 0.4 | 3.3367 | 1.3347 | -- | 0.4 | 3.3367 | 1.3347 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Digital Video Chainredesign | Person_289 | 2016-06-22 | 2016-12-17 01:00 | 0.4 | 3.9356 | 0.98391 | Accept | 0.71 | 4.2779 | 1.0695 | H1 | 5 | Worsening | 0.6 | 108 | 138 | 154 | 135.6667 | 0.6 | 108 | 138 | 154 | 135.6667 | -8.6957 | -77.5 | 0 | -5.2174
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK253 | Project_024_RISK253 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Insufficient parts to complete framework Warranty | Person_289 | 2016-05-23 | 2017-04-21 | 0.1 | 2.5667 | 0.77001 | Accept | 0.1 | 2.5667 | 0.77001 | H2 | 4 | Improving | 0.5 | 105 | 135 | 145 | 131.6667 | 0.5 | 105 | 135 | 145 | 131.6667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design | Person_216 | 2016-05-23 | 2020-10-20 01:00 | 0.2 | 2.6951 | 0.53901 | Reduce | 0.2 | 2.6951 | 0.53901 | H3 | 3 | Stable | 0.8 | 94 | 122 | 150 | 122 | 0.1 | 34 | 46 | 76 | 49 | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-09 | Project_022_RISK-09 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance - Issues arise | Person_393 | 2012-04-22 | 2016-11-19 01:00 | 0.7 | 24.8225 | 17.3758 | Reduce | 0.48 | 8.951 | 4.2965 | H2 | 4 | Stable | 0.8 | 95 | 135 | 145 | 130 | 0.4 | 37 | 43 | 70 | 46.5 | 63.94 | 31.4286 | 0 | 38.364
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-08 | Project_022_RISK-08 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Poor performance during acceptance phases | Person_248 | 2012-05-23 | 2016-11-19 01:00 | 0.65 | 5.6817 | 3.6931 | Reduce | 0.512 | 5.6817 | 2.909 | H1 | 5 | Stable | 0.8 | 107 | 139 | 159 | 137 | 0.4 | 35 | 56 | 63 | 53.6667 | 0 | 21.2308 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.35 | 2.9061 | 1.0171 | H2 | 4 | Worsening | 0.9 | 117 | 121 | 141 | 123.6667 | 0.2 | 19 | 42 | 60 | 41.1667 | 21.0126 | 56.25 | 0 | 12.6076
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK189 | Project_024_RISK189 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment integration - Audio and Video recording | Person_289 | 2016-08-20 01:00 | 2017-01-21 01:00 | 0.49 | 2.3975 | 2.3975 | Accept | 0.49 | 0.66364 | 0.66364 | H1 | 5 | Worsening | 0.6 | 91 | 124 | 150 | 122.8333 | 0.6 | 91 | 124 | 150 | 122.8333 | 72.3193 | 0 | 0 | 43.3916
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-22 | Project_022_RISK-22 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Setting to work Issues - monitor may require changing | Person_393 | 2014-10-22 01:00 | 2016-11-19 01:00 | 0.6 | 11.6428 | 6.9857 | Reduce | 0.2 | 12.2515 | 2.4503 | H3 | 3 | Worsening | 0.7 | 114 | 135 | 142 | 132.6667 | 0.4 | 18 | 49 | 71 | 47.5 | -5.228 | 66.6667 | 0 | -3.1368
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-30 | Project_022_RISK-30 | Opportunitity | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Setting to work and acceptance issues | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 0.8 | 8.6133 | 6.8907 | Exploit | 0.8 | 2.6904 | 2.1524 | H2 | 4 | Stable | [10 empty] | 68.7641 | 0 | 0 | 41.2585
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 3.3531 | 2.6825 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-58 | Project_022_RISK-58 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Handbook Update | Person_248 | 2012-04-19 | 2016-11-19 01:00 | 0.5 | 2.2354 | 1.1177 | Reduce | 0.5 | 2.2354 | 1.1177 | H3 | 3 | Stable | 0.6 | 94 | 136 | 158 | 132.6667 | 0.1 | 39 | 54 | 68 | 53.8333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_289 | 2016-05-23 | 2016-12-20 01:00 | 0.4 | 4.4985 | 1.3495 | Accept | 0.4 | 4.4985 | 1.3495 | H1 | 5 | Stable | 0.6 | 101 | 131 | 145 | 128.3333 | 0.6 | 101 | 131 | 145 | 128.3333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-22 01:00 | 2017-05-22 | 0.25 | 7.4225 | 1.8556 | Reduce | 0.1 | 3.7113 | 0.37113 | H3 | 3 | Stable | 0.6 | 105 | 138 | 155 | 135.3333 | 0.2 | 24 | 45 | 78 | 47 | 50 | 60 | 0 | 30
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 2.6991 | 1.0796 | H2 | 4 | Stable | 0.8 | 86 | 121 | 146 | 119.3333 | 0.1 | 28 | 46 | 76 | 48 | 31.8182 | 20 | 0 | 19.0909
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK194 | Project_024_RISK194 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Performance Models require additional effort | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.25 | 18.069 | 1.8069 | Accept | 0.25 | 18.069 | 1.8069 | H2 | 4 | Stable | 0.8 | 82 | 139 | 154 | 132 | 0.8 | 82 | 139 | 154 | 132 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_575 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 6.2979 | 0.94468 | H3 | 3 | Stable | 0.9 | 84 | 132 | 157 | 128.1667 | 0.1 | 30 | 53 | 78 | 53.3333 | 0 | 70 | 1 | 2.1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 0.4 | 9.139 | 3.6556 | Avoid | 0.2 | 9.139 | 1.8278 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK226 | Project_038_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Capacity to support enhancements or fixes post delivery | Person_330 | 2015-11-21 01:00 | 2017-05-22 | 0.5 | 13.9332 | 6.9666 | Avoid | 0.1 | 13.9332 | 1.3933 | H3 | 3 | Improving | [10 empty] | 0 | 80 | 1 | 2.4
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 0.5 | 13.7833 | 6.8917 | Avoid | 0.2 | 6.8917 | 1.3783 | H3 | 3 | Stable | [10 empty] | 50 | 60 | 1 | 31.8
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK187 | Project_038_RISK187 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Technical Publications | Person_671 | 2015-07-22 | 2016-08-20 01:00 | 0.5 | 4.6444 | 2.3222 | Avoid | 0.3 | 1.648 | 0.4944 | H2 | 4 | Worsening | [10 empty] | 64.5162 | 40 | 0 | 38.7097
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-10-21 01:00 | 0.3 | 5.5433 | 1.663 | Reduce | 0.1 | 5.5433 | 0.55433 | H3 | 3 | Improving | 0.8 | 93 | 131 | 156 | 128.8333 | 0.4 | 28 | 57 | 64 | 53.3333 | 0 | 66.6667 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Stable | [10 empty] | 0 | 75 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK195 | Project_024_RISK195 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Perfomance Validation document not accepted | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.1 | 4.4946 | 1.1236 | Accept | 0.1 | 4.4946 | 0.44946 | H2 | 4 | Stable | 0.5 | 109 | 132 | 146 | 130.5 | 0.5 | 109 | 132 | 146 | 130.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2016-02-21 01:00 | 2018-05-22 | 0.1 | 6.7418 | 1.6855 | Accept | 0.1 | 6.7418 | 1.0113 | H3 | 3 | Stable | 0.8 | 103 | 128 | 159 | 129 | 0.8 | 103 | 128 | 159 | 129 | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 0.3 | 5.4834 | 1.0967 | Accept | 0.3 | 5.4834 | 0.82251 | H1 | 5 | Improving | 0.6 | 85 | 130 | 145 | 125 | 0.6 | 85 | 130 | 145 | 125 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 0.125 | 232.2192 | 29.0274 | -- | 0.4 | 29.6641 | 11.8657 | H2 | 4 | Stable | [10 empty] | 87.2258 | -220 | 0 | 52.3355
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK232 | Project_038_RISK232 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Integration more complex than expected | Person_531 | 2015-11-21 01:00 | 2016-11-20 01:00 | 0.3 | 27.7165 | 8.3149 | Reduce | 0.185 | 13.1091 | 2.4252 | H3 | 3 | Improving | 0.9 | 102 | 123 | 156 | 125 | 0.3 | 10 | 46 | 75 | 44.8333 | 52.7027 | 38.3333 | 1 | 32.7716
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 0.3 | 26.9674 | 8.0902 | Avoid | 0.3 | 14.9819 | 4.4946 | H2 | 4 | Stable | [10 empty] | 44.4444 | 0 | 0 | 26.6667
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-21 01:00 | 0.5 | 26.9674 | 13.4837 | Avoid | 0.1 | 12.7646 | 1.2765 | H2 | 4 | Worsening | [10 empty] | 52.6667 | 80 | 0 | 31.6
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_119 | 2016-10-21 01:00 | 2017-11-19 01:00 | 0.3 | 5.3935 | 1.3484 | Accept | 0.3 | 5.3935 | 1.3484 | H1 | 5 | Improving | 0.6 | 109 | 126 | 160 | 128.8333 | 0.6 | 109 | 126 | 160 | 128.8333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK237 | Project_024_RISK237 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer coding standard Compliance | Person_534 | 2017-05-25 | 2017-10-27 01:00 | 0.2 | 17.9783 | 3.5957 | Accept | 0.2 | 17.9783 | 3.5957 | H2 | 4 | Stable | 0.7 | 114 | 133 | 157 | 133.8333 | 0.7 | 114 | 133 | 157 | 133.8333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK198 | Project_024_RISK198 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Spot Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 0.2 | 0.81199 | 0.081199 | Accept | 0.2 | 0.81199 | 0.0406 | H3 | 3 | Stable | 0.5 | 81 | 140 | 149 | 131.6667 | 0.5 | 81 | 140 | 149 | 131.6667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-022 | Project_028_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Accrediation Scope | Person_371 | 2014-01-21 01:00 | 2016-11-19 01:00 | 0.5 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 20 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK197 | Project_024_RISK197 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Fitness for purpose | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.2 | 12.1982 | 0.60991 | Accept | 0.2 | 12.1982 | 0.60991 | H2 | 4 | Improving | 0.8 | 104 | 140 | 141 | 134.1667 | 0.8 | 104 | 140 | 141 | 134.1667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK199 | Project_024_RISK199 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Strip Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 0.3 | 0 | 0 | Accept | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 80 | 138 | 155 | 131.1667 | 0.9 | 80 | 138 | 155 | 131.1667 |  | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK291 | Project_024_RISK291 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Scope Increase | Person_318 | 2016-11-05 01:00 | 2017-04-22 | 0.2 | 0 | 0 | Accept | 0.2 | 0 | 0 | H2 | 4 | Worsening | 0.8 | 81 | 129 | 156 | 125.5 | 0.8 | 81 | 129 | 156 | 125.5 |  | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2016-11-19 01:00 | 0.2 | 0.90951 | 0.1819 | Reduce | 0.2 | 0.90951 | 0.1819 | H3 | 3 | Stable | 0.8 | 99 | 135 | 154 | 132.1667 | 0.4 | 5 | 57 | 67 | 50 | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK219 | Project_024_RISK219 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | STTE additional work | Person_289 | 2016-09-20 01:00 | 2017-07-21 | 0.5 | 1.4532 | 0.072661 | Accept | 0.5 | 1.4532 | 0.072661 | H1 | 5 | Worsening | 0.6 | 80 | 129 | 149 | 124.1667 | 0.6 | 80 | 129 | 149 | 124.1667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2017-01-20 01:00 | 0.3 | 5.4553 | 1.6366 | Reduce | 0.15 | 5.252 | 0.7878 | H2 | 4 | Stable | 0.8 | 87 | 132 | 147 | 127 | 0.2 | 26 | 48 | 68 | 47.6667 | 3.7267 | 50 | 0 | 2.236
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-058 | Project_028_Risk-058 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | INterface Card | Person_253 | 2015-07-22 | 2016-10-20 01:00 | 0.2 | 2.8408 | 0.56817 | Reduce | 0.1 | 1.9314 | 0.19314 | H3 | 3 | Stable | 0.8 | 93 | 121 | 156 | 122.1667 | 0.1 | 35 | 57 | 66 | 54.8333 | 32.0134 | 50 | 1 | 20.708
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK222 | Project_024_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Testing Extends beyond target completion | Person_351 | 2017-07-21 | 2018-08-21 | 0.2 | 4.4727 | 0.44727 | Accept | 0.2 | 4.4727 | 0.22363 | H2 | 4 | Stable | 0.6 | 85 | 138 | 152 | 131.5 | 0.6 | 85 | 138 | 152 | 131.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Cable and connectors | Person_050 | 2015-11-21 01:00 | 2017-08-09 | 0.45 | 0.41338 | 0.18602 | Reduce | 0.2 | 0.41338 | 0.082677 | H2 | 4 | Stable | 0.7 | 107 | 134 | 153 | 132.6667 | 0.2 | 28 | 44 | 73 | 46.1667 | 0 | 55.5556 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Platform Acceptance | Person_500 | 2015-11-21 01:00 | 2017-04-21 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.2 | 4.2355 | 0.8471 | H3 | 3 | Stable | 0.5 | 82 | 122 | 154 | 120.6667 | 0.1 | 13 | 52 | 61 | 47 | 0 | 42.8571 | 1 | 1.2857
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-001 | Project_028_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Porting software | Person_542 | 2014-03-23 | 2016-12-20 01:00 | 0.5 | 8.8098 | 4.4049 | Reduce | 0.08 | 7.4545 | 0.59636 | H2 | 4 | Stable | 0.6 | 112 | 129 | 145 | 128.8333 | 0.2 | 21 | 59 | 79 | 56 | 15.3846 | 84 | 0 | 9.2308
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Furnished Equipmnet Condition | Person_371 | 2015-04-27 | 2017-08-19 01:00 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.8 | 80 | 131 | 141 | 124.1667 | 0.2 | 10 | 57 | 71 | 51.5 |  | 62.5 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.5 | 90 | 129 | 160 | 127.6667 | 0.1 | 2 | 41 | 71 | 39.5 | 0 | 25 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-007 | Project_026_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Additional requests for information and attendance at meetings | Person_264 | 2014-11-21 01:00 | 2018-12-27 01:00 | 0.5 | 10.5249 | 5.2625 | Reduce | 0.5 | 10.5249 | 5.2625 | H2 | 4 | Stable | 0.9 | 84 | 136 | 144 | 128.6667 | 0.1 | 28 | 43 | 78 | 46.3333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 8.0582 | 2.4175 | Accept | 0.5 | 8.0582 | 2.4175 | H2 | 4 | Stable | 0.6 | 113 | 125 | 145 | 126.3333 | 0.6 | 113 | 125 | 145 | 126.3333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 0.5 | 0.5596 | 0.05596 | Accept | 0.5 | 0.5596 | 0.05596 | H2 | 4 | Stable | 0.5 | 87 | 126 | 141 | 122 | 0.5 | 87 | 126 | 141 | 122 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 0.5 | 3.6174 | 1.8087 | Accept | 0.5 | 3.6172 | 1.8086 | H2 | 4 | Stable | 0.6 | 90 | 124 | 154 | 123.3333 | 0.6 | 90 | 124 | 154 | 123.3333 | 0.0051359 | 0 | 0 | 0.0030815
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Risk of repeat component Tests | Person_515 | 2017-12-21 | 2019-01-21 | 0.5 | 2.3503 | 0.47006 | Accept | 0.5 | 2.3503 | 0.47006 | H2 | 4 | Stable | 0.8 | 86 | 128 | 148 | 124.3333 | 0.8 | 86 | 128 | 148 | 124.3333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_515 | 2017-05-23 | 2019-01-21 | 0.5 | 4.4768 | 2.2384 | Accept | 0.5 | 4.4768 | 2.2384 | H2 | 4 | Stable | 0.7 | 98 | 128 | 147 | 126.1667 | 0.7 | 98 | 128 | 147 | 126.1667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R44 | Project_041_R44 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Procurement - Source Change and cost change | Person_468 | 2016-11-20 | 2018-05-22 | 0.5 | 244.3581 | 12.2179 | Accept | 0.5 | 227.5702 | 11.3785 | H1 | 5 | Worsening | 0.5 | 93 | 127 | 155 | 126 | 0.5 | 93 | 127 | 155 | 126 | 6.8702 | 0 | 0 | 4.1221
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-019 | Project_026_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Customer interaction and reporting may be much greater than anticipated | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 0.3 | 16.3694 | 4.9108 | Reduce | 0.2 | 16.3683 | 3.2737 | H3 | 3 | Stable | 0.9 | 81 | 127 | 147 | 122.6667 | 0.2 | 25 | 43 | 71 | 44.6667 | 0.0068371 | 33.3333 | 0 | 0.0041023
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_368 | 2016-11-20 | 2017-09-19 | 0.25 | 24.8462 | 12.4231 | Accept | 0.25 | 27.1831 | 13.5915 | H3 | 3 | Stable | 0.9 | 103 | 127 | 144 | 125.8333 | 0.9 | 103 | 127 | 144 | 125.8333 | -9.4054 | 0 | 0 | -5.6432
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_515 | 2016-11-20 | 2018-05-22 | 0.1 | 60.4367 | 3.0218 | Accept | 0.1 | 60.4367 | 3.0218 | H3 | 3 | Stable | 0.9 | 85 | 139 | 148 | 131.5 | 0.9 | 85 | 139 | 148 | 131.5 | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R06 | Project_041_R06 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional PM time to support the supply chain | Person_359 | 2016-11-20 | 2017-09-19 | 0.25 | 3.8666 | 1.5853 | Accept | 0.25 | 1.3288 | 0.5448 | H3 | 3 | Stable | 0.5 | 90 | 132 | 159 | 129.5 | 0.5 | 90 | 132 | 159 | 129.5 | 65.6338 | 0 | 0 | 39.3803
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2016-11-17 01:00 | 0.85 | 25.2325 | 21.4476 | Avoid | 0.08 | 20.8758 | 1.6701 | H2 | 4 | Improving | [10 empty] | 17.2662 | 90.5882 | 0 | 10.3597
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-018 | Project_023_Risk-018 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Project Management | Person_703 | 2013-05-19 | 2017-05-22 | 0.8 | 0.10892 | 0.087134 | Exploit | 0.8 | 0.10892 | 0.087134 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_515 | 2016-11-20 | 2018-05-22 | 0.25 | 5.9904 | 1.4976 | Accept | 0.25 | 0 | 0 | H2 | 4 | Stable | 0.6 | 89 | 126 | 148 | 123.5 | 0.6 | 89 | 126 | 148 | 123.5 | 100 | 0 | 0 | 60
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-019 | Project_023_Risk-019 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software | Person_253 | 2013-05-19 | 2017-05-22 | 0.8 | 0.38121 | 0.30497 | Exploit | 0.8 | 0.38121 | 0.30497 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2016-11-17 01:00 | 0.7 | 24.1887 | 16.9321 | Reduce | 0.25 | 4.3567 | 1.0892 | H2 | 4 | Stable | 0.8 | 99 | 128 | 158 | 128.1667 | 0.3 | 25 | 46 | 70 | 46.5 | 81.9887 | 64.2857 | 0 | 49.1932
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-020 | Project_023_Risk-020 | Opportunitity | Project Contingency | Open | H2 | 4 | 8. System Engineering | Installation & Acceptance - Preventative Maintenance | Person_253 | 2013-05-19 | 2017-05-22 | 0.8 | 0.81688 | 0.6535 | Exploit | 0.8 | 0.81688 | 0.6535 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-021 | Project_023_Risk-021 | Opportunitity | Project Contingency | Open | H2 | 4 | 8. System Engineering | Customer Services - Preventative Maintenance | Person_253 | 2013-05-19 | 2017-05-22 | 0.8 | 1.1981 | 0.95847 | Exploit | 0.8 | 1.1981 | 0.95847 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-117 | Project_039_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Filters | Person_185 | 2015-01-21 01:00 | 2016-10-20 01:00 | 0.1 | 3.005 | 0.3005 | Reduce | 0.1 | 3.005 | 0.3005 | H3 | 3 | Stable | 0.5 | 117 | 123 | 160 | 128.1667 | 0.2 | 20 | 57 | 64 | 52 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of Batch 2 Re-Design | Person_199 | 2016-05-23 | 2019-10-21 01:00 | 0.3 | 0.35617 | 0.10685 | Accept | 0.3 | 0.35617 | 0.10685 | H2 | 4 | Stable | 0.8 | 92 | 128 | 155 | 126.5 | 0.8 | 92 | 128 | 155 | 126.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-47 | Project_022_RISK-47 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Software Issues | Person_245 | 2012-04-19 | 2016-11-19 01:00 | 0.5 | 1.8602 | 0.55807 | Accept | 0.2 | 1.8602 | 0.55807 | H3 | 3 | Stable | 0.7 | 102 | 139 | 147 | 134.1667 | 0.7 | 102 | 139 | 147 | 134.1667 | 0 | 60 | 1 | 1.8
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-51 | Project_022_RISK-51 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Environmental Conditions | Person_393 | 2012-04-19 | 2016-11-19 01:00 | 0.2 | 1.4882 | 0.44646 | Accept | 0.2 | 1.4882 | 0.44646 | H3 | 3 | Stable | 0.8 | 88 | 125 | 149 | 122.8333 | 0.8 | 88 | 125 | 149 | 122.8333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 | 2016-05-21 | 0.5 | 4.3921 | 2.196 | Reduce | 0.3 | 4.3921 | 1.3176 | H1 | 5 | Stable | 0.7 | 101 | 128 | 155 | 128 | 0.2 | 34 | 53 | 70 | 52.6667 | 0 | 40 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-12-21 01:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.9 | 105 | 137 | 154 | 134.5 | 0.2 | 34 | 54 | 60 | 51.6667 | 47 | 0 | 0 | 28.2
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-12-21 01:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK117 | Project_037_RISK117 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Data Comms Availability or Performance | Person_334 | 2015-05-24 | 2016-11-20 01:00 | 0.35 | 3.2401 | 1.134 | Transfer | 0.1 | 3.2401 | 0.32401 | H3 | 3 | Improving | [10 empty] | 0 | 71.4286 | 1 | 2.1429
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-19 01:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.3 | 3.187 | 0.9561 | H2 | 4 | Stable | 0.8 | 96 | 136 | 148 | 131.3333 | 0.1 | 22 | 54 | 67 | 50.8333 | 0 | 25 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK114 | Project_035_RISK114 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Qualification Facilities Availability. | Person_570 | 2015-09-21 01:00 | 2016-08-20 01:00 | 0.61 | 1.2358 | 0.75383 | Reduce | 0.3 | 1.2358 | 0.37073 | H2 | 4 | Stable | 0.9 | 80 | 123 | 160 | 122 | 0.3 | 24 | 56 | 65 | 52.1667 | 0 | 50.8197 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 01:00 | 2016-11-20 01:00 | 0.25 | 6.3266 | 1.898 | Accept | 0.1 | 6.3266 | 1.297 | H3 | 3 | Stable | 0.7 | 107 | 128 | 143 | 127 | 0.7 | 107 | 128 | 143 | 127 | 0 | 60 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-09-20 01:00 | 0.25 | 3.2155 | 0.96464 | Accept | 0.15 | 3.2155 | 0.96464 | H3 | 3 | Stable | 0.8 | 89 | 134 | 141 | 127.6667 | 0.8 | 89 | 134 | 141 | 127.6667 | 0 | 40 | 1 | 1.2
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK152 | Project_038_RISK152 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Test Equipment Costs | Person_640 | 2015-06-24 | 2016-08-20 01:00 | 0.2 | 1.2271 | 0.50311 | Accept | 0.15 | 1.2271 | 0.50311 | H3 | 3 | Stable | 0.8 | 117 | 131 | 160 | 133.5 | 0.8 | 117 | 131 | 160 | 133.5 | 0 | 25 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK380 | Project_035_RISK380 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Data Throttling Algorithm | Person_699 | 2016-01-03 01:00 | 2016-11-20 01:00 | 0.2 | 2.6071 | 0.52143 | Reduce | 0.2 | 2.6071 | 0.52143 | H3 | 3 | Stable | 0.5 | 94 | 139 | 152 | 133.6667 | 0.2 | 8 | 46 | 77 | 44.8333 | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK394 | Project_035_RISK394 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Provision of supplier evidence | Person_631 | 2016-02-21 01:00 | 2016-10-21 01:00 | 0.5 | 2.4768 | 1.2384 | -- | 0.5 | 1.2167 | 0.60833 | H2 | 4 | Improving | [10 empty] | 50.8773 | 0 | 0 | 30.5264
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK290 | Project_035_RISK290 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Face-to-Face Arbitration | Person_699 | 2015-01-22 01:00 | 2017-01-21 01:00 | 0.5 | 1.2445 | 0.62224 | -- | 0.2 | 2.303 | 0.46059 | H3 | 3 | Worsening | [10 empty] | -85.0557 | 60 | 0 | -51.0334
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK395 | Project_035_RISK395 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Test area Site Availability | Person_691 | 2016-05-23 | 2016-11-19 01:00 | 0.5 | 3.0417 | 1.5208 | -- | 0.5 | 3.0417 | 1.5208 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-148 | Project_020_Risk-148 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs non-available items | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.3 | 14.9935 | 4.498 | Reduce | 0.3 | 14.9935 | 4.498 | H2 | 4 | Stable | 0.5 | 80 | 122 | 158 | 121 | 0.4 | 29 | 54 | 78 | 53.8333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK163 | Project_038_RISK163 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Additional Chamber trials | Person_531 | 2015-09-21 01:00 | 2016-09-20 01:00 | 0.25 | 18.6688 | 3.7338 | Accept | 0.25 | 18.6688 | 3.7338 | H2 | 4 | Stable | 0.6 | 106 | 125 | 159 | 127.5 | 0.6 | 106 | 125 | 159 | 127.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-147 | Project_020_Risk-147 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component taking longer to refurbish in country | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.6 | 6.7477 | 4.0486 | Reduce | 0.6 | 6.7477 | 4.0486 | H2 | 4 | Stable | 0.7 | 98 | 138 | 144 | 132.3333 | 0.3 | 36 | 47 | 60 | 47.3333 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-150 | Project_020_Risk-150 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Power supply Test Environment | Person_248 | 2016-10-21 01:00 | 2017-05-22 | 0.6 | 6.7477 | 4.0486 | Reduce | 0.6 | 6.7477 | 4.0486 | H2 | 4 | Worsening | 0.7 | 87 | 124 | 155 | 123 | 0.2 | 34 | 59 | 69 | 56.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK007 | Project_004_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 01:00 | 2016-03-21 01:00 | 0.2 | 0.15317 | 0.030633 | Reduce | 0.2 | 0.10883 | 0.021765 | H3 | 3 | Stable | 0.5 | 117 | 139 | 152 | 137.5 | 0.3 | 28 | 41 | 63 | 42.5 | 28.9481 | 0 | 1 | 17.3689
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK004 | Project_004_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 0.2 | 0.14752 | 0.029504 | Avoid | 0.2 | 0.14752 | 0.029504 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK003 | Project_004_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-05-24 | 2016-03-21 01:00 | 0.2 | 0.060459 | 0.012092 | Avoid | 0.2 | 0.060459 | 0.012092 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK006 | Project_004_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2014-11-19 01:00 | 2016-03-21 01:00 | 0.1 | 0.049978 | 0.0049978 | Avoid | 0.1 | 0.049978 | 0.0049978 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK005 | Project_004_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK002 | Project_004_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 0.5 | 0.15317 | 0.076583 | Avoid | 0.5 | 0.15317 | 0.076583 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 01:00 | 2016-10-19 01:00 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.9 | 83 | 129 | 152 | 125.1667 | 0.3 | 30 | 52 | 77 | 52.5 | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 01:00 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 01:00 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 01:00 | 0.1 | 0 | 0 | Accept | 0.05 | 0 | 0 | H3 | 3 | Stable | 0.9 | 88 | 136 | 157 | 131.5 | 0.9 | 88 | 136 | 157 | 131.5 |  | 50 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-015 | Project_028_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | STANDARDS Compliance | Person_499 | 2015-10-22 01:00 | 2016-11-19 01:00 | 0.05 | 0.85811 | 0.42906 | Accept | 0.05 | 0.85811 | 0.42906 | H3 | 3 | Stable | 0.5 | 114 | 131 | 158 | 132.6667 | 0.5 | 114 | 131 | 158 | 132.6667 | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-21 01:00 | 2016-08-21 01:00 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.9 | 89 | 127 | 159 | 126 | 0.1 | 21 | 45 | 67 | 44.6667 | 0 | 16.6667 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-041 | Project_028_Risk-041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Role Test Equipment Team Deliver Late | Person_542 | 2015-04-08 | 2017-02-19 01:00 | 0.4 | 5.126 | 2.563 | Accept | 0.2 | 5.126 | 2.563 | H2 | 4 | Stable | 0.6 | 111 | 132 | 144 | 130.5 | 0.6 | 111 | 132 | 144 | 130.5 | 0 | 50 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-049 | Project_028_Risk-049 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | More integration required | Person_542 | 2015-04-08 | 2016-11-19 01:00 | 0.05 | 12.815 | 2.563 | Accept | 0.05 | 12.815 | 2.563 | H3 | 3 | Stable | 0.8 | 89 | 121 | 153 | 121 | 0.8 | 89 | 121 | 153 | 121 | 0 | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.5 | 88 | 130 | 152 | 126.6667 | 0.4 | 18 | 50 | 65 | 47.1667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence and missing info | Person_727 | 2015-11-25 01:00 | 2016-11-19 01:00 | 0.3 | 0 | 0 | Accept | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 104 | 121 | 150 | 123 | 0.6 | 104 | 121 | 150 | 123 |  | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 01:00 | 2016-11-19 01:00 | 0.2 | 0 | 0 | Accept | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.5 | 86 | 140 | 147 | 132.1667 | 0.5 | 86 | 140 | 147 | 132.1667 |  | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 20:00 | 2019-08-20 20:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.6 | 80 | 126 | 147 | 121.8333 | 0.4 | 29 | 46 | 60 | 45.5 | 83.3333 | 88.8889 | 1 | 52.6667
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 20:00 | 2019-08-20 20:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.6 | 117 | 134 | 147 | 133.3333 | 0.3 | 36 | 52 | 61 | 50.8333 | 72 | 0 | 0 | 43.2
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 20:00 | 2019-08-20 20:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.6 | 112 | 122 | 144 | 124 | 0.4 | 33 | 45 | 76 | 48.1667 | 47.7391 | 0 | 0 | 28.6435
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 20:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.7 | 94 | 136 | 155 | 132.1667 | 0.3 | 19 | 53 | 64 | 49.1667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Obsolescence Monitoring Risk | Person_181 | 2016-12-03 | 2017-01-20 | 0.3 | 5.9458 | 1.7837 | Reduce | 0.15 | 0.9786 | 0.14679 | H3 | 3 | Stable | 0.9 | 102 | 131 | 159 | 130.8333 | 0.4 | 36 | 50 | 74 | 51.6667 | 83.5413 | 50 | 0 | 50.1248
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-002 | Project_028_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Record / Replay feature | Person_499 | 2014-03-23 | 2016-11-19 01:00 | 0.1 | 3.0903 | 0.61807 | Accept | 0.05 | 3.0903 | 0.61807 | H2 | 4 | Stable | 0.7 | 105 | 136 | 141 | 131.6667 | 0.7 | 105 | 136 | 141 | 131.6667 | 0 | 50 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | EMC Testing | Person_070 | 2016-04-22 | 2016-11-19 01:00 | 0.35 | 30.9033 | 7.7258 | Accept | 0.2 | 30.9033 | 7.7258 | H2 | 4 | Stable | 0.9 | 110 | 133 | 145 | 131.1667 | 0.9 | 110 | 133 | 145 | 131.1667 | 0 | 42.8571 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_542 | 2015-01-22 01:00 | 2017-08-20 01:00 | 0.35 | 35.0206 | 7.0041 | Accept | 0.2 | 35.0206 | 7.0041 | H2 | 4 | Stable | 0.5 | 107 | 128 | 153 | 128.6667 | 0.5 | 107 | 128 | 153 | 128.6667 | 0 | 42.8571 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_070 | 2016-06-23 | 2017-03-22 | 0.4 | 15.0654 | 6.7794 | Accept | 0.2 | 15.0654 | 6.7794 | H2 | 4 | Stable | 0.6 | 83 | 126 | 158 | 124.1667 | 0.6 | 83 | 126 | 158 | 124.1667 | 0 | 50 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK293 | Project_024_RISK293 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | LoE Engineering support required post completion in addition to BCR | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 8.5688 | 4.2844 | Reduce | 0.4 | 8.5688 | 3.4275 | H1 | 5 | Worsening | 0.6 | 118 | 124 | 157 | 128.5 | 0.4 | 27 | 53 | 61 | 50 | 0 | 20 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-13 | 2016-11-19 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.9 | 102 | 128 | 148 | 127 | 0.1 | 32 | 51 | 72 | 51.3333 | 80 | 66.6667 | 0 | 48
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_174 | 2001-05-23 | 2018-02-19 | 0.4 | 0.48559 | 0.19424 | Reduce | 0.4 | 0.48559 | 0.19424 | H2 | 4 | Stable | 0.9 | 85 | 140 | 155 | 133.3333 | 0.2 | 22 | 49 | 71 | 48.1667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-05-21 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.8 | 100 | 137 | 149 | 132.8333 | 0.1 | 4 | 55 | 62 | 47.6667 | 50 | 28.5714 | 0 | 30
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2016-02-11 | 2017-02-19 | 0.5 | 17.2826 | 8.6413 | Reduce | 0.15 | 17.2826 | 2.5924 | H2 | 4 | Worsening | 0.6 | 117 | 121 | 159 | 126.6667 | 0.4 | 28 | 55 | 71 | 53.1667 | 0 | 70 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build ()/Decision Point concludes new release required | Person_470 | 2012-11-20 | 2017-05-21 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.7 | 101 | 124 | 141 | 123 | 0.3 | 19 | 44 | 78 | 45.5 | 0 | 50 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 | 2017-01-20 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.4 | 12.6474 | 5.059 | H2 | 4 | Stable | 0.9 | 117 | 135 | 142 | 133.1667 | 0.4 | 16 | 56 | 61 | 50.1667 | 0 | 33.3333 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_021 | 2010-04-19 | 2017-01-19 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.7 | 111 | 140 | 154 | 137.5 | 0.2 | 27 | 59 | 68 | 55.1667 | 0 | 50 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Release is more complicated/ delayed. | Person_482 | 2013-01-07 | 2017-02-19 | 0.5 | 4.7676 | 2.3838 | Reduce | 0.3 | 4.7676 | 1.4303 | H2 | 4 | Stable | 0.5 | 105 | 131 | 160 | 131.5 | 0.2 | 33 | 50 | 66 | 49.8333 | 0 | 40 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 | 2017-01-19 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.5 | 94 | 125 | 158 | 125.3333 | 0.1 | 18 | 55 | 66 | 50.6667 | 0 | 33.3333 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 | 2017-05-21 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Worsening | 0.5 | 119 | 134 | 156 | 135.1667 | 0.4 | 1 | 43 | 69 | 40.3333 | 0 | 57.1429 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 | 2017-04-21 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H3 | 3 | Improving | 0.9 | 103 | 131 | 155 | 130.3333 | 0.3 | 25 | 44 | 72 | 45.5 |  | 62.5 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-01-19 | 0.7 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Worsening | 0.7 | 89 | 133 | 149 | 128.3333 | 0.1 | 22 | 58 | 65 | 53.1667 |  | 28.5714 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-01-19 | 0.7 | 1.3243 | 0.92704 | Reduce | 0.5 | 1.3243 | 0.66217 | H1 | 5 | Stable | 0.8 | 82 | 133 | 159 | 128.8333 | 0.1 | 24 | 45 | 65 | 44.8333 | 0 | 28.5714 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-008 | Project_021_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Config Qualification delays due to equipment/ hardware unreliability | Person_207 | 2016-09-11 | 2016-12-19 | 0.5 | 1.3243 | 0.66217 | Reduce | 0.4 | 1.3243 | 0.52974 | H2 | 4 | Stable | 0.7 | 96 | 132 | 154 | 129.6667 | 0.3 | 37 | 58 | 70 | 56.5 | 0 | 20 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R030 | Project_021_Risk-R030 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Config Qualification delay due to Major PRs | Person_207 | 2016-08-03 | 2016-10-19 | 0.1 | 3.973 | 0.3973 | Reduce | 0.1 | 3.973 | 0.3973 | H2 | 4 | Improving | 0.7 | 84 | 137 | 144 | 129.3333 | 0.4 | 33 | 40 | 72 | 44.1667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-007 | Project_021_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Config Qualification delay due to Major PRs | Person_207 | 2016-09-11 | 2016-12-19 | 0.3 | 3.973 | 1.1919 | Reduce | 0.3 | 3.2005 | 0.96015 | H2 | 4 | Stable | 0.7 | 110 | 128 | 150 | 128.6667 | 0.1 | 36 | 59 | 68 | 56.6667 | 19.4445 | 0 | 0 | 11.6667
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 | 2017-04-21 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.6 | 114 | 135 | 157 | 135.1667 | 0.2 | 36 | 44 | 78 | 48.3333 |  | 50 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-005 | Project_021_Risk-005 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Opportunity to accelerate Component Approval through closer working efficiencies | Person_721 | 2016-09-11 | 2017-04-21 | 0.1 | 0 | 0 | -- | 0.3 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -200 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R033 | Project_021_Risk-R033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Config 1c Qualification delays due to equipment/ hardware unreliability | Person_207 | 2016-08-10 | 2016-11-19 | 0.5 | 1.3243 | 0.66217 | Reduce | 0.4 | 1.3243 | 0.52974 | H2 | 4 | Improving | 0.6 | 94 | 136 | 143 | 130.1667 | 0.4 | 1 | 50 | 77 | 46.3333 | 0 | 20 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2016-11-19 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.6 | 107 | 135 | 151 | 133 | 0.2 | 28 | 41 | 60 | 42 |  | 50 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R029 | Project_021_Risk-R029 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Config Qualification delay due to Major PRs | Person_207 | 2016-08-03 | 2016-10-19 | 0.3 | 3.973 | 1.1919 | Reduce | 0.3 | 3.2005 | 0.96015 | H2 | 4 | Improving | 0.6 | 99 | 138 | 147 | 133 | 0.2 | 14 | 48 | 72 | 46.3333 | 19.4445 | 0 | 0 | 11.6667
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP006 | Project_021_OPP006 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Opportunity to accelerate Component Approval through closer working efficiencies | Person_721 | 2016-08-06 | 2016-11-19 | 0.1 | 0 | 0 | -- | 0.3 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -200 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-011 | Project_021_Risk-011 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-09-11 | 2017-01-19 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.5 | 1.1257 | 0.56284 | H1 | 5 | Stable | 0.5 | 94 | 125 | 142 | 122.6667 | 0.2 | 35 | 51 | 61 | 50 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Config Qualification delays due to rig unavailability | Person_207 | 2016-09-11 | 2016-12-19 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.5 | 112 | 123 | 160 | 127.3333 | 0.4 | 10 | 49 | 60 | 44.3333 |  | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2016-11-19 | 0.3 | 1.076 | 0.32281 | Reduce | 0.05 | 1.076 | 0.053801 | H2 | 4 | Improving | 0.8 | 85 | 130 | 158 | 127.1667 | 0.3 | 29 | 50 | 62 | 48.5 | 0 | 83.3333 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Obsolescence Monitoring Risk | Person_181 | 2016-12-02 23:00 | 2017-01-19 23:00 | 0.3 | 5.9458 | 1.7837 | Reduce | 0.15 | 0.9786 | 0.14679 | H3 | 3 | Stable | 0.6 | 89 | 124 | 155 | 123.3333 | 0.1 | 29 | 43 | 70 | 45.1667 | 83.5413 | 50 | 0 | 50.1248
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-043 | Project_008_Risk-043 | Opportunitity | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Joint courseware and tech pubs team | Person_280 | 2014-11-21 01:00 | 2017-05-21 | 0.5 | 28.2191 | 14.1096 | -- | 0.8 | 13.2573 | 10.6058 | H1 | 5 | Stable | [10 empty] | 53.0201 | -60 | 0 | 31.8121
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-059 | Project_008_Risk-059 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Project Resource Efficencies | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 0.2 | 21.6852 | 4.337 | -- | 0.2 | 21.6852 | 4.337 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 0.5 | 9.2728 | 4.6364 | Reduce | 0.3 | 9.2728 | 2.7819 | H2 | 4 | Stable | 0.8 | 85 | 122 | 143 | 119.3333 | 0.1 | 28 | 48 | 76 | 49.3333 | 0 | 40 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 0.3 | 8.7814 | 2.6344 | Reduce | 0.2 | 8.7832 | 1.7566 | H3 | 3 | Stable | 0.7 | 114 | 138 | 158 | 137.3333 | 0.2 | 21 | 56 | 61 | 51 | -0.021119 | 33.3333 | 0 | -0.012672
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Delay of processing | Person_306 | 2016-01-13 01:00 | 2019-08-21 01:00 | 0.15 | 26.3497 | 3.9525 | Reduce | 0.15 | 26.3497 | 3.9525 | H3 | 3 | Improving | 0.9 | 103 | 123 | 145 | 123.3333 | 0.3 | 34 | 57 | 77 | 56.5 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 01:00 | 2017-03-22 | 0.05 | 87.6137 | 4.3807 | Reduce | 0.05 | 87.6137 | 4.3807 | H3 | 3 | Stable | 0.8 | 90 | 122 | 155 | 122.1667 | 0.1 | 38 | 45 | 73 | 48.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2016-12-08 01:00 | 0.41 | 5.8286 | 0.29143 | Accept | 0.41 | 5.8286 | 0.29143 | H2 | 4 | Stable | 0.5 | 94 | 135 | 144 | 129.6667 | 0.5 | 94 | 135 | 144 | 129.6667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.3 | 53.0293 | 15.9088 | Reduce | 0.3 | 53.0293 | 15.9088 | H3 | 3 | Worsening | 0.6 | 85 | 132 | 160 | 128.8333 | 0.3 | 10 | 54 | 75 | 50.1667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Commercial aspects agreement | Person_480 | 2013-08-21 01:00 | 2016-05-22 | 0.02 | 4.8296 | 0.096593 | Transfer | 0.02 | 4.8296 | 0.096593 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 01:00 | 2017-08-20 01:00 | 0.1 | 34.363 | 3.4363 | Avoid | 0.1 | 34.363 | 3.4363 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.48 | 33.2985 | 15.9833 | Avoid | 0.48 | 33.2985 | 15.9833 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-126 | Project_032_Risk-126 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supply Chain - Delivery to Contract Requirement | Person_590 | 2012-08-21 01:00 | 2016-08-20 01:00 | 0.3 | 25.3619 | 7.6086 | Reduce | 0.3 | 25.3619 | 7.6086 | H2 | 4 | Stable | 0.6 | 114 | 126 | 153 | 128.5 | 0.4 | 33 | 45 | 70 | 47.1667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-015 | Project_023_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Illness | Person_371 | 2015-04-09 | 2016-12-11 01:00 | 0.25 | 0.20788 | 0.068599 | Accept | 0.25 | 0.052336 | 0.0057569 | H2 | 4 | Stable | 0.6 | 105 | 137 | 145 | 133 | 0.6 | 105 | 137 | 145 | 133 | 74.8236 | 0 | 0 | 44.8942
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.25 | 7.7469 | 1.9367 | Reduce | 0.25 | 7.7469 | 1.9367 | H3 | 3 | Stable | 0.8 | 104 | 129 | 151 | 128.5 | 0.1 | 1 | 46 | 76 | 43.5 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-131 | Project_032_Risk-131 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 0.3 | 15.6782 | 4.7035 | Transfer | 0.3 | 15.6782 | 4.7035 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 01:00 | 0.05 | 11.3437 | 0.56718 | Reduce | 0.05 | 11.3437 | 0.56718 | H3 | 3 | Stable | 0.7 | 105 | 126 | 150 | 126.5 | 0.4 | 36 | 41 | 68 | 44.6667 | 0 | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-109 | Project_011_Risk-109 | Opportunitity | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Environment complexity | Person_187 | 2016-07-21 | 2018-08-21 | 0.25 | 0.14661 | 0.036651 | -- | 0.25 | 0.14661 | 0.036651 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-108 | Project_011_Risk-108 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Offer additional functionality to the customer | Person_147 | 2017-04-22 | 2018-08-21 | 0.1 | 0.34094 | 0.034094 | -- | 0.1 | 0.34094 | 0.034094 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 0.2 | 0.12388 | 0.024775 | Reduce | 0.2 | 0.12388 | 0.024775 | H2 | 4 | Stable | 0.7 | 102 | 137 | 152 | 133.6667 | 0.1 | 22 | 55 | 61 | 50.5 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 0.4 | 0.51141 | 0.20457 | Avoid | 0.4 | 0.51141 | 0.20457 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-016 | Project_023_Risk-016 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Damage to equipment (Unable to replace due to obsolescence) | Person_703 | 2015-10-22 01:00 | 2016-06-22 | 0.3 | 0.49834 | 0.12459 | Accept | 0.3 | 0.49834 | 0.12459 | H2 | 4 | Stable | 0.9 | 109 | 135 | 149 | 133 | 0.9 | 109 | 135 | 149 | 133 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.2 | 0.10171 | 0.020343 | -- | 0.2 | 0.10171 | 0.020343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 0.3 | 0.28639 | 0.085917 | Reduce | 0.3 | 0.28639 | 0.085917 | H2 | 4 | Stable | 0.5 | 110 | 135 | 157 | 134.5 | 0.4 | 19 | 40 | 71 | 41.6667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 2. Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 0.25 | 0 | 0 | -- | 0.25 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2016-07-21 | 2018-05-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 0.3 | 0.10626 | 0.031878 | -- | 0.3 | 0.01932 | 0.005796 | H3 | 3 | Stable | [10 empty] | 81.8181 | 0 | 0 | 49.0909
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-111 | Project_039_Risk-111 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Maturation results inconclusive | Person_297 | 2016-02-21 01:00 | 2017-01-20 01:00 | 0.3 | 1.0052 | 0.35182 | Accept | 0.3 | 1.0052 | 0.35182 | H2 | 4 | Stable | 0.6 | 87 | 128 | 154 | 125.5 | 0.6 | 87 | 128 | 154 | 125.5 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-118 | Project_011_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer change environment | Person_187 | 2013-08-21 | 2018-08-21 | 0.1 | 0 | 0 | Avoid | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-116 | Project_011_Risk-116 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Delays to Qualification | Person_147 | 2017-04-22 | 2017-08-19 | 0.25 | 1.7297 | 0.43243 | -- | 0.25 | 1.7297 | 0.43243 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-104 | Project_011_Risk-104 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer delayed in providing Custeomr Furnished Equipment | Person_147 | 2016-06-23 | 2017-04-21 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.8 | 91 | 126 | 160 | 125.8333 | 0.1 | 7 | 47 | 79 | 45.6667 |  | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-195 | Project_039_Risk-195 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Supply Chain Delays - System Comms, Component, and subsystem | Person_083 | 2016-08-21 01:00 | 2017-02-19 01:00 | 0.3 | 0.30685 | 0.06137 | Accept | 0.3 | 0.30685 | 0.06137 | H3 | 3 | Worsening | 0.9 | 107 | 123 | 141 | 123.3333 | 0.9 | 107 | 123 | 141 | 123.3333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 0.3 | 0.51931 | 0.15579 | -- | 0.15 | 0.51931 | 0.077897 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 0.2 | 0.55005 | 0.11001 | Avoid | 0.2 | 0.55005 | 0.11001 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-123 | Project_011_Risk-123 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | No Requirement for Delta acceptance | Person_187 | 2017-06-23 | 2017-08-20 | 0.2 | 0.63074 | 0.12615 | -- | 0.2 | 0.63074 | 0.12615 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2016-07-21 | 2017-02-19 | 0.15 | 0.28639 | 0.042959 | -- | 0.15 | 0.28639 | 0.042959 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-04-21 | 0.4 | 0.24207 | 0.096828 | -- | 0.4 | 0.24207 | 0.096828 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 | 2018-08-21 | 0.2 | 1.661 | 0.33219 | Reduce | 0.2 | 1.661 | 0.33219 | H2 | 4 | Stable | 0.9 | 110 | 122 | 157 | 125.8333 | 0.2 | 39 | 56 | 63 | 54.3333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-022 | Project_028_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Accrediation Scope | Person_371 | 2014-01-21 01:00 | 2016-12-20 01:00 | 0.5 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 20 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK118 | Project_037_RISK118 | Threat | Management Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Product does not deliver the inputs/depdencies required by the Project by the req'd dates | Person_330 | 2015-02-24 01:00 | 2016-06-23 | 0.4 | 0 | 0 | Accept | 0.4 | 0 | 0 | H2 | 4 | Worsening | 0.6 | 107 | 125 | 151 | 126.3333 | 0.6 | 107 | 125 | 151 | 126.3333 |  | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2015-04-23 | 2018-08-21 | 0.4 | 1.2444 | 0.49778 | Reduce | 0.4 | 1.2444 | 0.49778 | H2 | 4 | Stable | 0.7 | 113 | 137 | 148 | 134.8333 | 0.4 | 13 | 58 | 61 | 51 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK312 | Project_035_RISK312 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Audio Performance inadequate | Person_303 | 2015-06-24 | 2016-10-21 01:00 | 0.2 | 0 | 0 | Accept | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.5 | 101 | 123 | 152 | 124.1667 | 0.5 | 101 | 123 | 152 | 124.1667 |  | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK313 | Project_035_RISK313 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Deployed Performance inadequate | Person_303 | 2015-05-24 | 2016-10-21 01:00 | 0.3 | 0.16195 | 0.072876 | Accept | 0.205 | 0.16195 | 0.072876 | H2 | 4 | Improving | 0.8 | 96 | 137 | 157 | 133.5 | 0.8 | 96 | 137 | 157 | 133.5 | 0 | 31.6667 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2017-04-21 | 0.2 | 0.90951 | 0.1819 | Reduce | 0.2 | 0.90951 | 0.1819 | H3 | 3 | Stable | 0.7 | 115 | 132 | 157 | 133.3333 | 0.1 | 3 | 42 | 66 | 39.5 | 0 | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 | 2018-08-21 | 0.45 | 0.83883 | 0.37747 | Reduce | 0.45 | 0.83883 | 0.37747 | H2 | 4 | Stable | 0.5 | 105 | 124 | 157 | 126.3333 | 0.4 | 39 | 53 | 70 | 53.5 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK308 | Project_035_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Facility performance during Live trials | Person_303 | 2015-05-24 | 2016-10-21 01:00 | 0.3 | 1.4532 | 0.072661 | Accept | 0.3 | 1.4532 | 0.072661 | H2 | 4 | Improving | 0.5 | 104 | 139 | 160 | 136.6667 | 0.5 | 104 | 139 | 160 | 136.6667 | 0 | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK304 | Project_035_RISK304 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change at Elevation | Person_425 | 2016-09-20 01:00 | 2017-01-20 01:00 | 0.41 | 0.33412 | 0.15036 | Accept | 0.41 | 0.33412 | 0.15036 | H2 | 4 | Stable | 0.5 | 85 | 139 | 151 | 132 | 0.5 | 85 | 139 | 151 | 132 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2017-01-20 01:00 | 0.3 | 5.4553 | 1.6366 | Reduce | 0.15 | 5.252 | 0.7878 | H2 | 4 | Stable | 0.9 | 85 | 125 | 154 | 123.1667 | 0.2 | 6 | 55 | 64 | 48.3333 | 3.7267 | 50 | 0 | 2.236
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-010 | Project_011_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Rework required following integration of Customer System | Person_142 | 2013-08-21 | 2017-01-20 | 0.4 | 0.66881 | 0.26753 | Reduce | 0.4 | 0.66881 | 0.26753 | H2 | 4 | Stable | 0.9 | 120 | 133 | 153 | 134.1667 | 0.1 | 23 | 43 | 75 | 45 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-058 | Project_028_Risk-058 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | INterface Card | Person_253 | 2015-07-22 | 2016-12-18 01:00 | 0.2 | 2.8408 | 0.56817 | Reduce | 0.1 | 1.9314 | 0.19314 | H3 | 3 | Stable | 0.5 | 97 | 137 | 151 | 132.6667 | 0.1 | 35 | 45 | 75 | 48.3333 | 32.0134 | 50 | 1 | 20.708
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-149 | Project_020_Risk-149 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs to be returned to UK | Person_703 | 2016-12-21 01:00 | 2017-11-19 01:00 | 0.2 | 0.098873 | 0.0098873 | Accept | 0.2 | 0.098873 | 0.0098873 | H2 | 4 | Stable | 0.9 | 112 | 136 | 141 | 132.8333 | 0.9 | 112 | 136 | 141 | 132.8333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-05-21 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.6 | 97 | 135 | 146 | 130.5 | 0.4 | 25 | 56 | 77 | 54.3333 | 50 | 28.5714 | 0 | 30
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_040 | RISK174 | Project_040_RISK174 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Supplier Power Supply quality | Person_687 | 2013-08-20 21:00 | 2014-07-22 | 0.05 | 1.3215 | 0.39644 | Accept | 0.01 | 1.3215 | 0.39644 | H2 | 4 | Stable | 0.9 | 100 | 131 | 157 | 130.1667 | 0.9 | 100 | 131 | 157 | 130.1667 | 0 | 80 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-02-19 01:00 | 0.5 | 17.2826 | 8.6413 | Reduce | 0.15 | 17.2826 | 2.5924 | H2 | 4 | Worsening | 0.8 | 82 | 127 | 143 | 122.1667 | 0.4 | 6 | 42 | 60 | 39 | 0 | 70 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build ()/Decision Point concludes new release required | Person_470 | 2012-11-20 01:00 | 2017-05-21 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.6 | 109 | 137 | 156 | 135.5 | 0.2 | 38 | 43 | 72 | 47 | 0 | 50 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.35 | 20.3303 | 7.1156 | Accept | 0.35 | 18.975 | 3.795 | H3 | 3 | Stable | 0.8 | 112 | 127 | 147 | 127.8333 | 0.8 | 112 | 127 | 147 | 127.8333 | 6.6667 | 0 | 0 | 4
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-01-20 01:00 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.4 | 12.6474 | 5.059 | H2 | 4 | Stable | 0.8 | 109 | 140 | 143 | 135.3333 | 0.3 | 15 | 49 | 74 | 47.5 | 0 | 33.3333 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Cable and connectors | Person_050 | 2015-11-21 01:00 | 2017-08-09 | 0.45 | 0.41338 | 0.18602 | Reduce | 0.2 | 0.41338 | 0.082677 | H2 | 4 | Stable | 0.8 | 114 | 121 | 146 | 124 | 0.4 | 6 | 59 | 66 | 51.3333 | 0 | 55.5556 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_021 | 2010-04-19 | 2017-01-19 01:00 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.5 | 81 | 123 | 157 | 121.6667 | 0.1 | 15 | 42 | 79 | 43.6667 | 0 | 50 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Platform Acceptance | Person_500 | 2015-11-21 01:00 | 2017-04-21 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.2 | 4.2355 | 0.8471 | H3 | 3 | Stable | 0.8 | 106 | 129 | 150 | 128.6667 | 0.4 | 11 | 57 | 64 | 50.5 | 0 | 42.8571 | 1 | 1.2857
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Release is more complicated/ delayed. | Person_482 | 2013-01-07 01:00 | 2017-02-19 01:00 | 0.5 | 4.7676 | 2.3838 | Reduce | 0.3 | 4.7676 | 1.4303 | H2 | 4 | Stable | 0.8 | 97 | 127 | 154 | 126.5 | 0.3 | 35 | 44 | 70 | 46.8333 | 0 | 40 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 01:00 | 2017-01-19 01:00 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.5 | 97 | 133 | 159 | 131.3333 | 0.4 | 29 | 54 | 78 | 53.8333 | 0 | 33.3333 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.25 | 8.8098 | 3.0834 | Accept | 0.25 | 8.8098 | 1.762 | H3 | 3 | Stable | 0.8 | 89 | 140 | 153 | 133.6667 | 0.8 | 89 | 140 | 153 | 133.6667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2017-05-21 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Worsening | 0.9 | 106 | 128 | 155 | 128.8333 | 0.2 | 23 | 56 | 69 | 52.6667 | 0 | 57.1429 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-21 01:00 | 2019-08-20 | 0.5 | 0.40661 | 0.16264 | Accept | 0.5 | 0.40661 | 0.081321 | H2 | 4 | Stable | 0.8 | 108 | 122 | 148 | 124 | 0.8 | 108 | 122 | 148 | 124 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Furnished Equipmnet Condition | Person_371 | 2015-04-27 | 2017-08-19 01:00 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.6 | 84 | 138 | 153 | 131.5 | 0.1 | 24 | 50 | 77 | 50.1667 |  | 62.5 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H3 | 3 | Improving | 0.7 | 90 | 124 | 145 | 121.8333 | 0.4 | 34 | 47 | 69 | 48.5 |  | 62.5 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-01-19 01:00 | 0.7 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Worsening | 0.5 | 105 | 134 | 148 | 131.5 | 0.2 | 27 | 40 | 64 | 41.8333 |  | 28.5714 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-01-19 01:00 | 0.7 | 1.3243 | 0.92704 | Reduce | 0.5 | 1.3243 | 0.66217 | H1 | 5 | Stable | 0.8 | 95 | 123 | 141 | 121.3333 | 0.4 | 31 | 50 | 68 | 49.8333 | 0 | 28.5714 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-008 | Project_021_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Config Qualification delays due to equipment/ hardware unreliability | Person_207 | 2016-09-11 01:00 | 2016-12-19 01:00 | 0.5 | 1.3243 | 0.66217 | Reduce | 0.4 | 1.3243 | 0.52974 | H2 | 4 | Stable | 0.8 | 81 | 133 | 156 | 128.1667 | 0.4 | 6 | 57 | 73 | 51.1667 | 0 | 20 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-007 | Project_021_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Config Qualification delay due to Major PRs | Person_207 | 2016-09-11 01:00 | 2016-12-19 01:00 | 0.3 | 3.973 | 1.1919 | Reduce | 0.3 | 3.2005 | 0.96015 | H2 | 4 | Stable | 0.9 | 101 | 122 | 145 | 122.3333 | 0.2 | 20 | 48 | 73 | 47.5 | 19.4445 | 0 | 0 | 11.6667
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.8 | 82 | 131 | 141 | 124.5 | 0.2 | 39 | 59 | 74 | 58.1667 |  | 50 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-005 | Project_021_Risk-005 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Opportunity to accelerate Component Approval through closer working efficiencies | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 0.1 | 0 | 0 | -- | 0.3 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -200 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2016-11-19 01:00 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.9 | 81 | 126 | 150 | 122.5 | 0.3 | 3 | 51 | 64 | 45.1667 |  | 50 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP006 | Project_021_OPP006 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Opportunity to accelerate Component Approval through closer working efficiencies | Person_721 | 2016-08-06 | 2016-11-19 01:00 | 0.1 | 0 | 0 | -- | 0.3 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -200 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-011 | Project_021_Risk-011 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-09-11 01:00 | 2017-01-19 01:00 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.5 | 1.1257 | 0.56284 | H1 | 5 | Stable | 0.7 | 119 | 130 | 144 | 130.5 | 0.1 | 34 | 48 | 64 | 48.3333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Config Qualification delays due to rig unavailability | Person_207 | 2016-09-11 01:00 | 2016-12-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.9 | 100 | 139 | 149 | 134.1667 | 0.4 | 4 | 51 | 69 | 46.1667 |  | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-01-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.5 | 94 | 140 | 157 | 135.1667 | 0.2 | 30 | 58 | 73 | 55.8333 |  | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-05-21 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.5 | 1.1257 | 0.56284 | H1 | 5 | Stable | 0.5 | 120 | 124 | 152 | 128 | 0.4 | 10 | 55 | 72 | 50.3333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2016-11-19 01:00 | 0.3 | 1.076 | 0.32281 | Reduce | 0.05 | 1.076 | 0.053801 | H2 | 4 | Improving | 0.5 | 118 | 126 | 151 | 128.8333 | 0.3 | 2 | 42 | 79 | 41.5 | 0 | 83.3333 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-13 01:00 | 2016-11-19 01:00 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.9 | 117 | 137 | 154 | 136.5 | 0.1 | 24 | 41 | 63 | 41.8333 | 80 | 66.6667 | 0 | 48
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.2 | 12.1398 | 8.4978 | Accept | 0.2 | 12.1398 | 8.4978 | H3 | 3 | Stable | 0.8 | 116 | 126 | 142 | 127 | 0.8 | 116 | 126 | 142 | 127 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_174 | 2001-05-23 | 2018-02-19 01:00 | 0.4 | 0.48559 | 0.19424 | Reduce | 0.4 | 0.48559 | 0.19424 | H2 | 4 | Stable | 0.5 | 80 | 126 | 146 | 121.6667 | 0.2 | 38 | 54 | 73 | 54.5 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 0.4 | 9.139 | 3.6556 | Avoid | 0.2 | 9.139 | 1.8278 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK226 | Project_038_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Capacity to support enhancements or fixes post delivery | Person_330 | 2015-11-21 01:00 | 2017-05-22 | 0.5 | 13.9332 | 6.9666 | Avoid | 0.1 | 13.9332 | 1.3933 | H3 | 3 | Improving | [10 empty] | 0 | 80 | 1 | 2.4
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 0.5 | 13.7833 | 6.8917 | Avoid | 0.2 | 6.8917 | 1.3783 | H3 | 3 | Stable | [10 empty] | 50 | 60 | 1 | 31.8
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK187 | Project_038_RISK187 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Technical Publications | Person_671 | 2015-07-22 | 2016-12-20 01:00 | 0.5 | 4.6444 | 2.3222 | Avoid | 0.3 | 1.648 | 0.4944 | H2 | 4 | Worsening | [10 empty] | 64.5162 | 40 | 0 | 38.7097
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-20 01:00 | 0.3 | 5.5433 | 1.663 | Reduce | 0.1 | 5.5433 | 0.55433 | H3 | 3 | Improving | 0.5 | 104 | 129 | 159 | 129.8333 | 0.3 | 15 | 59 | 61 | 52 | 0 | 66.6667 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Stable | [10 empty] | 0 | 75 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 20:00 | 2019-08-07 | 0.61 | 4.4946 | 1.1236 | Accept | 0.61 | 4.4946 | 0.44946 | H1 | 5 | Stable | 0.9 | 115 | 123 | 156 | 127.1667 | 0.9 | 115 | 123 | 156 | 127.1667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 0.125 | 232.2192 | 29.0274 | -- | 0.327 | 27.8663 | 9.1123 | H2 | 4 | Stable | [10 empty] | 88 | -161.6 | 0 | 52.8
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 0.3 | 26.9674 | 8.0902 | Avoid | 0.3 | 14.9819 | 4.4946 | H2 | 4 | Stable | [10 empty] | 44.4444 | 0 | 0 | 26.6667
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-21 01:00 | 0.5 | 26.9674 | 13.4837 | Avoid | 0.1 | 12.7646 | 1.2765 | H2 | 4 | Worsening | [10 empty] | 52.6667 | 80 | 0 | 31.6
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 20:00 | 2019-08-20 20:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 20:00 | 2019-08-20 20:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 20:00 | 2019-08-20 20:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 20:00 | 2019-08-20 20:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 20:00 | 2019-08-20 20:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 01:00 | 2016-05-21 | 0.5 | 4.3921 | 2.196 | Reduce | 0.3 | 4.3921 | 1.3176 | H1 | 5 | Stable | 0.9 | 116 | 133 | 148 | 132.6667 | 0.4 | 17 | 49 | 74 | 47.8333 | 0 | 40 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.41 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -2.5 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.61 | 0.25667 | 0.15657 | Reduce | 0.5 | 0.25667 | 0.12834 | H2 | 4 | Stable | 0.5 | 111 | 134 | 150 | 132.8333 | 0.1 | 29 | 51 | 62 | 49.1667 | 0 | 18.0328 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2014-01-21 01:00 | 2017-11-20 01:00 | 0.4 | 1.078 | 0.43121 | Reduce | 0.4 | 1.4673 | 0.58692 | H2 | 4 | Stable | 0.8 | 93 | 129 | 145 | 125.6667 | 0.2 | 4 | 49 | 73 | 45.5 | -36.1112 | 0 | 0 | -21.6667
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-118 | Project_029_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Acceptance Schedule is longer in duration/delayed | Person_102 | 2015-12-22 01:00 | 2017-05-23 | 0.55 | 0.56468 | 0.31057 | Reduce | 0.55 | 0.56468 | 0.31057 | H2 | 4 | Stable | 0.6 | 99 | 127 | 159 | 127.6667 | 0.4 | 27 | 47 | 67 | 47 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2017-11-19 01:00 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2017-05-23 | 0.6 | 0.89835 | 0.53901 | Transfer | 0.6 | 0.89835 | 0.53901 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2015-07-31 | 2017-05-15 | 0.35 | 0.85557 | 0.29945 | Reduce | 0.35 | 0.92402 | 0.32341 | H2 | 4 | Stable | 0.6 | 108 | 126 | 156 | 128 | 0.2 | 28 | 44 | 71 | 45.8333 | -8.0001 | 0 | 0 | -4.8001
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R017 | Project_021_Risk-R017 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Effort to address Hexavalent Chromium issue is unknown at time of baseline | Person_470 | 2016-02-06 | 2016-11-19 | 0.7 | 0.77001 | 0.30801 | Accept | 0.7 | 0.77001 | 0.231 | H1 | 5 | Stable | 0.9 | 96 | 132 | 156 | 130 | 0.9 | 96 | 132 | 156 | 130 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2016-05-23 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.5 | 92 | 123 | 160 | 124 | 0.2 | 37 | 55 | 67 | 54 | 0 | 28.5714 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2014-07-22 | 2017-11-19 01:00 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.7 | 86 | 136 | 150 | 130 | 0.3 | 22 | 54 | 64 | 50.3333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2017-10-14 01:00 | 0.41 | 6.4168 | 2.6309 | Transfer | 0.41 | 0 | 0 | H1 | 5 | Stable | [10 empty] | 100 | 0 | 0 | 60
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub-system FPGA | Person_216 | 2014-02-20 01:00 | 2017-05-22 | 0.3 | 1.54 | 0.46201 | Reduce | 0.2 | 1.155 | 0.231 | H3 | 3 | Stable | 0.9 | 83 | 139 | 159 | 133 | 0.1 | 8 | 45 | 74 | 43.6667 | 25 | 33.3333 | 1 | 16
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SystemC HW/SW | Person_199 | 2016-05-23 | 2019-10-21 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.3 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.7 | 94 | 126 | 147 | 124.1667 | 0.3 | 26 | 56 | 69 | 53.1667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs [technical scope] | Person_466 | 2016-05-23 | 2019-07-21 | 0.35 | 9.505 | 3.3267 | Reduce | 0.35 | 9.505 | 3.3267 | H2 | 4 | Stable | 0.7 | 103 | 131 | 149 | 129.3333 | 0.4 | 9 | 54 | 64 | 48.1667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.5 | 3.5934 | 1.7967 | H2 | 4 | Stable | 0.9 | 99 | 139 | 141 | 132.6667 | 0.3 | 4 | 55 | 60 | 47.3333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | HW - additional unplanned design effort | Person_216 | 2016-05-23 | 2019-10-21 01:00 | 0.4 | 3.3367 | 1.3347 | -- | 0.4 | 3.3367 | 1.3347 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 0.5 | 3.9356 | 0.98391 | Accept | 0.45 | 4.2779 | 1.0695 | H2 | 4 | Stable | 0.6 | 81 | 131 | 145 | 125 | 0.6 | 81 | 131 | 145 | 125 | -8.6957 | 10 | 0 | -5.2174
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation | Person_565 | 2018-05-22 | 2018-08-21 | 0.25 | 2.5667 | 0.77001 | Accept | 0.25 | 2.5667 | 0.77001 | H3 | 3 | Stable | 0.6 | 101 | 139 | 155 | 135.3333 | 0.6 | 101 | 139 | 155 | 135.3333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design | Person_216 | 2016-05-23 | 2020-10-20 01:00 | 0.2 | 2.6951 | 0.53901 | Reduce | 0.2 | 2.6951 | 0.53901 | H3 | 3 | Stable | 0.5 | 115 | 129 | 145 | 129.3333 | 0.4 | 26 | 56 | 60 | 51.6667 | 0 | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 0.5 | 9.3941 | 1.8788 | Accept | 0.5 | 9.3941 | 1.8788 | H2 | 4 | Improving | 0.8 | 114 | 128 | 158 | 130.6667 | 0.8 | 114 | 128 | 158 | 130.6667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 0.3 | 1.8788 | 0.18788 | Accept | 0.3 | 1.8788 | 0.18788 | H2 | 4 | Stable | 0.9 | 82 | 123 | 142 | 119.3333 | 0.9 | 82 | 123 | 142 | 119.3333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 0.05 | 29.4599 | 8.838 | Accept | 0.05 | 18.7882 | 5.6365 | H2 | 4 | Stable | 0.5 | 107 | 128 | 156 | 129.1667 | 0.5 | 107 | 128 | 156 | 129.1667 | 36.2245 | 0 | 0 | 21.7347
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 0.25 | 4.7948 | 0.95895 | Accept | 0.25 | 4.7948 | 0.95895 | H3 | 3 | Stable | 0.7 | 89 | 134 | 146 | 128.5 | 0.7 | 89 | 134 | 146 | 128.5 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | More issues than expected during Qualification | Person_147 | 2017-04-22 | 2017-11-04 | 0.35 | 0.65759 | 0.098638 | Accept | 0.35 | 0.65759 | 0.098638 | H1 | 5 | Stable | 0.9 | 98 | 137 | 157 | 133.8333 | 0.9 | 98 | 137 | 157 | 133.8333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 0.2 | 6.7638 | 1.3528 | Accept | 0.2 | 6.7638 | 1.3528 | H2 | 4 | Stable | 0.5 | 108 | 122 | 157 | 125.5 | 0.5 | 108 | 122 | 157 | 125.5 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 01:00 | 0.1 | 0.93941 | 0.14091 | Accept | 0.05 | 0.93941 | 0.14091 | H3 | 3 | Stable | 0.9 | 114 | 140 | 159 | 138.8333 | 0.9 | 114 | 140 | 159 | 138.8333 | 0 | 50 | 1 | 1.5
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-015 | Project_028_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | STANDARDS Compliance | Person_499 | 2015-10-22 01:00 | 2016-11-19 01:00 | 0.05 | 2.8182 | 0.56365 | Accept | 0.05 | 2.8182 | 0.56365 | H3 | 3 | Stable | 0.5 | 99 | 136 | 148 | 131.8333 | 0.5 | 99 | 136 | 148 | 131.8333 | 0 | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-049 | Project_028_Risk-049 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | More integration required | Person_542 | 2015-04-08 | 2016-12-18 01:00 | 0.05 | 1.1273 | 0.45092 | Accept | 0.05 | 1.1273 | 0.45092 | H3 | 3 | Stable | 0.9 | 94 | 132 | 158 | 130 | 0.9 | 94 | 132 | 158 | 130 | 0 | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Governance and Export Rules | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 0.93941 | 0.23485 | Transfer | 0.25 | 0.93941 | 0.23485 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK004 | Project_010_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Export License | Person_359 | 2015-02-18 01:00 | 2017-08-20 01:00 | 0.8 | 0.18482 | 0.14786 | Reduce | 0.8 | 0.18482 | 0.14786 | H1 | 5 | Improving | 0.8 | 112 | 125 | 149 | 126.8333 | 0.1 | 2 | 55 | 65 | 47.8333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 01:00 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.6 | 90 | 140 | 145 | 132.5 | 0.2 | 30 | 47 | 77 | 49.1667 | 0 | 40 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence and missing info | Person_727 | 2015-11-25 01:00 | 2016-11-19 01:00 | 0.3 | 11.0894 | 0.55447 | Accept | 0.3 | 11.0894 | 0.55447 | H2 | 4 | Stable | 0.7 | 106 | 126 | 145 | 125.8333 | 0.7 | 106 | 126 | 145 | 125.8333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.7 | 0.92411 | 0.64688 | Reduce | 0.3 | 0.36965 | 0.11089 | H2 | 4 | Stable | 0.5 | 113 | 134 | 144 | 132.1667 | 0.4 | 29 | 49 | 64 | 48.1667 | 60 | 57.1429 | 0 | 36
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 01:00 | 2016-04-21 | 0.5 | 4.0661 | 2.033 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.5 | 117 | 129 | 153 | 131 | 0.4 | 24 | 54 | 78 | 53 | 0 | 90 | 1 | 2.7
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.3 | 0.46206 | 0.13862 | H2 | 4 | Improving | 0.9 | 84 | 126 | 142 | 121.6667 | 0.1 | 18 | 58 | 73 | 53.8333 | 58.3333 | 50 | 0 | 35
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 01:00 | 2017-03-22 | 0.2 | 1.1089 | 0.88715 | Accept | 0.2 | 0.73929 | 0.44357 | H2 | 4 | Stable | 0.7 | 111 | 134 | 143 | 131.6667 | 0.7 | 111 | 134 | 143 | 131.6667 | 33.3333 | 0 | 0 | 20
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 01:00 | 2017-08-20 01:00 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.9 | 120 | 127 | 160 | 131.3333 | 0.2 | 28 | 42 | 64 | 43.3333 | 0 | 50 | 1 | 1.5
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.5 | 109 | 129 | 144 | 128.1667 | 0.4 | 3 | 44 | 69 | 41.3333 | 0 | 25 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Stable | 0.6 | 99 | 134 | 158 | 132.1667 | 0.1 | 9 | 42 | 64 | 40.1667 | 0 | 40 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Worsening | [10 empty] | 0 | 37.5 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-002 | Project_028_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Record / Replay feature | Person_499 | 2014-03-23 | 2016-12-18 01:00 | 0.1 | 3.6965 | 0.36965 | Accept | 0.05 | 3.6965 | 0.36965 | H2 | 4 | Stable | 0.5 | 91 | 140 | 160 | 135.1667 | 0.5 | 91 | 140 | 160 | 135.1667 | 0 | 50 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | EMC Testing | Person_070 | 2016-04-22 | 2017-02-19 01:00 | 0.35 | 0.92411 | 0.18482 | Accept | 0.2 | 0.92411 | 0.18482 | H2 | 4 | Stable | 0.5 | 89 | 133 | 156 | 129.5 | 0.5 | 89 | 133 | 156 | 129.5 | 0 | 42.8571 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 0.3 | 1.8482 | 0.55447 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.7 | 92 | 127 | 159 | 126.5 | 0.2 | 23 | 43 | 70 | 44.1667 | 0 | 33.3333 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 01:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.8 | 91 | 127 | 143 | 123.6667 | 0.1 | 7 | 41 | 74 | 40.8333 | 90 | 75 | 1 | 56.25
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK024 | Project_012_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component Repair & test costs | Person_359 | 2015-04-04 | 2016-04-12 | 0.7 | 0.84985 | 0.5949 | -- | 0.18 | 0.84985 | 0.15297 | H2 | 4 | Improving | [10 empty] | 0 | 74.2857 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_468 | 2016-11-19 23:00 | 2018-11-19 23:00 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.1 | 6.431 | 0.6431 | H3 | 3 | Stable | 0.8 | 119 | 129 | 143 | 129.6667 | 0.2 | 8 | 44 | 60 | 40.6667 | -47.0588 | 33.3333 | 1 | -27.2353
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R81 | Project_041_R81 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Re-imaging of PC's - additional material | Person_515 | 2016-11-19 23:00 | 2017-10-20 23:00 | 0.5 | 0.21008 | 0.10504 | Avoid | 0.5 | 0.21008 | 0.10504 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R85 | Project_041_R85 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Go to Offshore initiative | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 0.15 | 7.7172 | 1.1576 | -- | 0.15 | 7.7172 | 1.1576 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_368 | 2016-11-19 23:00 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.7 | 112 | 134 | 159 | 134.5 | 0.1 | 16 | 53 | 79 | 51.1667 | 0 | 50 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R43 | Project_041_R43 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Procurement - Component and Supplier Leadtime | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 0.25 | 10.9327 | 2.7332 | Reduce | 0.15 | 10.9327 | 1.6399 | H2 | 4 | Stable | 0.9 | 81 | 137 | 148 | 129.5 | 0.3 | 8 | 44 | 78 | 43.6667 | 0 | 40 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 0.75 | 10.7184 | 8.0388 | Reduce | 0.75 | 5.3592 | 4.0194 | H1 | 5 | Worsening | 0.9 | 86 | 123 | 153 | 121.8333 | 0.1 | 21 | 57 | 74 | 53.8333 | 50 | 0 | 0 | 30
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R86 | Project_041_R86 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sharing Attrition Stock with Warranty Spares pool | Person_501 | 2016-11-19 23:00 | 2018-05-22 | 0.5 | 3.1083 | 1.5542 | Exploit | 0.5 | 3.1083 | 1.5542 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_542 | 2015-01-22 01:00 | 2017-08-20 01:00 | 0.35 | 1.9722 | 0.98609 | Accept | 0.2 | 1.9722 | 0.98609 | H2 | 4 | Stable | 0.7 | 80 | 131 | 145 | 124.8333 | 0.7 | 80 | 131 | 145 | 124.8333 | 0 | 42.8571 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_070 | 2016-06-23 | 2017-04-21 | 0.4 | 2.5081 | 1.2541 | Accept | 0.2 | 2.5081 | 1.2541 | H2 | 4 | Stable | 0.6 | 80 | 135 | 158 | 129.6667 | 0.6 | 80 | 135 | 158 | 129.6667 | 0 | 50 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R017 | Project_021_Risk-R017 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Effort to address Hexavalent Chromium issue is unknown at time of baseline | Person_470 | 2016-02-06 01:00 | 2016-11-19 01:00 | 0.7 | 7.0313 | 3.5156 | Accept | 0.7 | 7.0313 | 3.5156 | H1 | 5 | Stable | 0.7 | 115 | 131 | 149 | 131.3333 | 0.7 | 115 | 131 | 149 | 131.3333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.05 | 0.68598 | 0.034299 | H3 | 3 | Stable | 0.6 | 111 | 121 | 153 | 124.6667 | 0.1 | 13 | 51 | 71 | 48 | 0 | 80 | 1 | 2.4
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 01:00 | 2016-11-20 01:00 | 0.25 | 1.2519 | 0.31298 | Accept | 0.1 | 1.2519 | 0.31298 | H3 | 3 | Stable | 0.8 | 97 | 139 | 155 | 134.6667 | 0.8 | 97 | 139 | 155 | 134.6667 | 0 | 60 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-20 01:00 | 0.25 | 3.7514 | 0.37514 | Accept | 0.15 | 3.7514 | 0.37514 | H3 | 3 | Stable | 0.5 | 120 | 127 | 141 | 128.1667 | 0.5 | 120 | 127 | 141 | 128.1667 | 0 | 40 | 1 | 1.2
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R29 | Project_041_R29 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Attrition | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 0.1 | 3.6014 | 0.36014 | Reduce | 0.05 | 3.6014 | 0.18007 | H3 | 3 | Stable | 0.5 | 85 | 126 | 157 | 124.3333 | 0.3 | 13 | 57 | 68 | 51.5 | 0 | 50 | 1 | 1.5
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2016-11-19 23:00 | 2017-07-21 | 0.1 | 21.8655 | 2.1865 | Reduce | 0.05 | 21.8655 | 1.0933 | H2 | 4 | Stable | 0.7 | 91 | 140 | 148 | 133.1667 | 0.4 | 19 | 40 | 79 | 43 | 0 | 50 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Stable | 0.6 | 89 | 135 | 159 | 131.3333 | 0.4 | 39 | 56 | 70 | 55.5 | 0 | 60 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK163 | Project_038_RISK163 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Additional Chamber trials | Person_531 | 2015-09-21 01:00 | 2016-11-20 01:00 | 0.25 | 0.6088 | 0.1522 | Accept | 0.25 | 0.6088 | 0.1522 | H2 | 4 | Stable | 0.6 | 106 | 130 | 151 | 129.5 | 0.6 | 106 | 130 | 151 | 129.5 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Unidentified Change Requests | Person_693 | 2016-11-19 23:00 | 2017-09-19 23:00 | 0.5 | 1.2005 | 0.60023 | Reduce | 0.1 | 0.51019 | 0.051019 | H3 | 3 | Stable | 0.6 | 112 | 136 | 156 | 135.3333 | 0.4 | 15 | 59 | 62 | 52.1667 | 57.5001 | 80 | 1 | 36.9001
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.1 | 0.77172 | 0.077172 | H3 | 3 | Stable | 0.6 | 88 | 126 | 153 | 124.1667 | 0.3 | 39 | 55 | 62 | 53.5 | 0 | 60 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production or Engineering | Person_359 | 2016-11-19 23:00 | 2018-05-22 | 0.15 | 1.1576 | 0.17364 | Reduce | 0.1 | 1.1576 | 0.11576 | H3 | 3 | Stable | 0.9 | 116 | 126 | 149 | 128.1667 | 0.4 | 31 | 41 | 70 | 44.1667 | 0 | 33.3333 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R13 | Project_041_R13 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Loss of key personnel | Person_359 | 2016-11-19 23:00 | 2017-08-19 23:00 | 0.5 | 0.59165 | 0.29583 | Reduce | 0.1 | 0.59165 | 0.059165 | H3 | 3 | Stable | 0.7 | 93 | 131 | 157 | 129 | 0.2 | 10 | 53 | 77 | 49.8333 | 0 | 80 | 1 | 2.4
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-117 | Project_039_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Filters | Person_185 | 2015-01-21 01:00 | 2016-12-19 01:00 | 0.1 | 3.005 | 0.3005 | Reduce | 0.1 | 3.005 | 0.3005 | H3 | 3 | Stable | 0.5 | 113 | 128 | 151 | 129.3333 | 0.1 | 30 | 41 | 64 | 43 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-017 | Project_029_Risk-017 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Additional Obsolescence - System | Person_102 | 2016-05-23 | 2017-10-21 01:00 | 0.5 | 0.35617 | 0.10685 | Accept | 0.1 | 0.35617 | 0.10685 | H3 | 3 | Stable | 0.6 | 92 | 125 | 151 | 123.8333 | 0.6 | 92 | 125 | 151 | 123.8333 | 0 | 80 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-111 | Project_029_Risk-111 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Unplanned courier cost and T&S for any transportation of hardware during Integration phase | Person_692 | 2015-07-22 | 2017-04-22 | 0.8 | 1.8602 | 0.55807 | Accept | 0.8 | 1.8602 | 0.55807 | H2 | 4 | Stable | 0.8 | 97 | 128 | 159 | 128 | 0.8 | 97 | 128 | 159 | 128 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2016-05-23 | 2019-07-21 | 0.4 | 1.4882 | 0.44646 | Accept | 0.3 | 1.4882 | 0.44646 | H2 | 4 | Stable | 0.8 | 100 | 130 | 154 | 129 | 0.8 | 100 | 130 | 154 | 129 | 0 | 25 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2019-10-14 01:00 | 0.2 | 1.4882 | 0.44646 | Accept | 0.2 | 1.4882 | 0.44646 | H3 | 3 | Stable | 0.9 | 118 | 135 | 160 | 136.3333 | 0.9 | 118 | 135 | 160 | 136.3333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-026 | Project_029_Risk-026 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | platform Integration - SW support | Person_102 | 2016-09-02 01:00 | 2019-09-24 01:00 | 0.5 | 19.1935 | 1.5355 | Accept | 0.4 | 19.1935 | 1.5355 | H3 | 3 | Stable | 0.5 | 106 | 130 | 149 | 129.1667 | 0.5 | 106 | 130 | 149 | 129.1667 | 0 | 20 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2015-07-22 | 2019-07-21 | 0.3 | 8.3972 | 0.83972 | Accept | 0.2 | 8.3972 | 0.41986 | H3 | 3 | Stable | 0.5 | 107 | 122 | 143 | 123 | 0.5 | 107 | 122 | 143 | 123 | 0 | 33.3333 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2017-10-20 01:00 | 0.03 | 19.1935 | 0.95968 | Accept | 0.1 | 19.1935 | 0.95968 | H2 | 4 | Stable | 0.7 | 100 | 137 | 157 | 134.1667 | 0.7 | 100 | 137 | 157 | 134.1667 | 0 | -233.3333 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-200 | Project_027_Risk-200 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Sucession Planning for key team members | Person_060 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.2 | 7.3175 | 1.4635 | Reduce | 0.05 | 7.3175 | 0.36588 | H2 | 4 | Stable | 0.8 | 103 | 138 | 145 | 133.3333 | 0.2 | 22 | 52 | 62 | 48.6667 | 0 | 75 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-189 | Project_027_Risk-189 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Major Component obsolescence | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 8.3972 | 2.5191 | Reduce | 0.08 | 8.3972 | 0.67177 | H2 | 4 | Stable | 0.7 | 114 | 140 | 143 | 136.1667 | 0.4 | 11 | 53 | 71 | 49 | 0 | 73.3333 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-201 | Project_027_Risk-201 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Transition into Support | Person_027 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0.5 | 68.3768 | 34.1884 | Reduce | 0.05 | 38.387 | 1.9193 | H2 | 4 | Stable | 0.5 | 86 | 125 | 141 | 121.1667 | 0.1 | 37 | 50 | 72 | 51.5 | 43.8597 | 90 | 0 | 26.3158
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-05-23 | 2019-10-21 01:00 | 0.25 | 13.2195 | 1.5863 | Accept | 0.25 | 13.2195 | 1.5863 | H2 | 4 | Stable | 0.5 | 94 | 129 | 155 | 127.5 | 0.5 | 94 | 129 | 155 | 127.5 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-188 | Project_027_Risk-188 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Unidentified Technical Legacy Issue | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 20.0332 | 2.0033 | Reduce | 0.05 | 20.0332 | 1.0017 | H3 | 3 | Stable | 0.5 | 105 | 124 | 148 | 124.8333 | 0.2 | 24 | 45 | 70 | 45.6667 | 0 | 50 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-193 | Project_027_Risk-193 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | A greater number of arising technical queries | Person_110 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 13.7953 | 4.1386 | Reduce | 0.05 | 13.7953 | 0.68977 | H3 | 3 | Stable | 0.5 | 85 | 124 | 156 | 122.8333 | 0.3 | 21 | 59 | 62 | 53.1667 | 0 | 83.3333 | 1 | 2.5
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of Batch 2 Re-Design | Person_199 | 2016-05-23 | 2019-10-21 01:00 | 0.3 | 16.1945 | 1.6195 | Accept | 0.3 | 16.1945 | 1.6195 | H2 | 4 | Stable | 0.5 | 98 | 131 | 150 | 128.6667 | 0.5 | 98 | 131 | 150 | 128.6667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Suppliers | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 35.9878 | 21.5927 | Accept | 0.15 | 15.5947 | 0.77974 | H2 | 4 | Stable | 0.8 | 106 | 123 | 158 | 126 | 0.8 | 106 | 123 | 158 | 126 | 56.6667 | 0 | 0 | 34
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 27.5907 | 2.7591 | Accept | 0.2 | 27.5907 | 2.7591 | H2 | 4 | Stable | 0.5 | 115 | 130 | 154 | 131.5 | 0.5 | 115 | 130 | 154 | 131.5 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK153 | Project_024_RISK153 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Processor memory/performance Issue | Person_331 | 2016-06-23 | 2017-03-22 | 0.3 | 112.3463 | 33.7039 | Reduce | 0.2 | 38.196 | 7.6392 | H2 | 4 | Stable | 0.6 | 106 | 129 | 152 | 129 | 0.1 | 5 | 44 | 71 | 42 | 66.0015 | 33.3333 | 0 | 39.6009
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Local customer Engineers in country | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 25.966 | 7.7898 | Accept | 0.1 | 22.5039 | 6.7512 | H2 | 4 | Stable | 0.6 | 111 | 131 | 147 | 130.3333 | 0.6 | 111 | 131 | 147 | 130.3333 | 13.3333 | 0 | 0 | 8
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence | Person_455 | 2016-05-23 | 2020-05-23 | 0.3 | 62.3617 | 3.1181 | Accept | 0.3 | 62.3617 | 3.1181 | H2 | 4 | Stable | 0.7 | 94 | 130 | 144 | 126.3333 | 0.7 | 94 | 130 | 144 | 126.3333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Consumables | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 4.5441 | 0.45441 | Accept | 0.2 | 4.5441 | 0.45441 | H2 | 4 | Stable | 0.8 | 107 | 131 | 155 | 131 | 0.8 | 107 | 131 | 155 | 131 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK179 | Project_024_RISK179 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Testing Required | Person_289 | 2016-12-21 01:00 | 2017-05-22 | 0.5 | 3.5054 | 1.7527 | Reduce | 0.4 | 3.5054 | 1.4022 | H2 | 4 | Stable | 0.8 | 91 | 126 | 149 | 124 | 0.4 | 31 | 56 | 68 | 53.8333 | 0 | 20 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 7. Finance | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 30.2764 | 12.1106 | Accept | 0.2 | 30.2764 | 12.1106 | H2 | 4 | Stable | 0.7 | 83 | 124 | 148 | 121.1667 | 0.7 | 83 | 124 | 148 | 121.1667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 11.9444 | 5.9722 | Accept | 0.15 | 11.9444 | 5.9722 | H2 | 4 | Stable | 0.7 | 81 | 137 | 152 | 130.1667 | 0.7 | 81 | 137 | 152 | 130.1667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK180 | Project_024_RISK180 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | High Accelerated Life Testing (HALT) | Person_289 | 2016-12-21 01:00 | 2017-05-03 | 0.4 | 10.4903 | 4.1961 | Reduce | 0.2 | 10.4903 | 2.0981 | H2 | 4 | Stable | 0.9 | 110 | 130 | 147 | 129.5 | 0.3 | 3 | 50 | 74 | 46.1667 | 0 | 50 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 35.885 | 25.4784 | Accept | 0.2 | 27.0826 | 20.3119 | H2 | 4 | Stable | 0.5 | 110 | 122 | 150 | 124.6667 | 0.5 | 110 | 122 | 150 | 124.6667 | 24.5297 | 0 | 0 | 14.7178
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport Routes | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 30.7697 | 15.0772 | Accept | 0.15 | 24.3561 | 12.1781 | H2 | 4 | Stable | 0.8 | 105 | 126 | 160 | 128.1667 | 0.8 | 105 | 126 | 160 | 128.1667 | 20.8439 | 0 | 0 | 12.5063
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Internal Quality Issues | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 14.541 | 5.8164 | Accept | 0.2 | 14.541 | 5.8164 | H2 | 4 | Stable | 0.7 | 105 | 123 | 159 | 126 | 0.7 | 105 | 123 | 159 | 126 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk017 | Project_042_Risk017 | Threat | Financial Contingency | Open | H2 | 4 | 6. Contractual/Legal | Liquidated Damages | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 1.3502 | 0.33756 | Accept | 0.4 | 1.3502 | 0.33756 | H2 | 4 | Stable | 0.6 | 89 | 135 | 145 | 129 | 0.6 | 89 | 135 | 145 | 129 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK196 | Project_024_RISK196 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional Trials - Cost of Labour | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.3 | 0.95209 | 0.28563 | Reduce | 0.2 | 0.95209 | 0.19042 | H2 | 4 | Stable | 0.5 | 112 | 136 | 155 | 135.1667 | 0.3 | 3 | 51 | 73 | 46.6667 | 0 | 33.3333 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Repairs | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 2.0816 | 0.20816 | Accept | 0.25 | 2.0816 | 0.20816 | H2 | 4 | Stable | 0.8 | 98 | 131 | 150 | 128.6667 | 0.8 | 98 | 131 | 150 | 128.6667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials - Increased Cost | Person_073 | 2016-05-23 | 2017-02-19 01:00 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.5 | 96 | 125 | 149 | 124.1667 | 0.4 | 28 | 54 | 76 | 53.3333 | 0 | 50 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | People unable to sustain the pace | Person_413 | 2015-11-21 01:00 | 2017-05-22 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.8 | 107 | 138 | 153 | 135.3333 | 0.1 | 28 | 58 | 71 | 55.1667 | 0 | 5 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk016 | Project_042_Risk016 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport/Delivery Speed | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 1.1685 | 0.23369 | Accept | 0.1 | 1.1685 | 0.23369 | H2 | 4 | Stable | 0.8 | 86 | 121 | 160 | 121.6667 | 0.8 | 86 | 121 | 160 | 121.6667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Country Stability | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 0.5596 | 0.05596 | Accept | 0.4 | 0.5596 | 0.05596 | H2 | 4 | Stable | 0.6 | 80 | 123 | 141 | 118.8333 | 0.6 | 80 | 123 | 141 | 118.8333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 3.6174 | 1.8087 | Accept | 0.1 | 3.6172 | 0.72345 | H2 | 4 | Stable | 0.9 | 85 | 125 | 143 | 121.3333 | 0.9 | 85 | 125 | 143 | 121.3333 | 0.0051359 | 0 | 0 | 0.0030815
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 2.3503 | 0.47006 | Accept | 0.2 | 2.3503 | 0.47006 | H2 | 4 | Stable | 0.5 | 111 | 137 | 144 | 133.8333 | 0.5 | 111 | 137 | 144 | 133.8333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.05 | 4.4768 | 2.2384 | Accept | 0.05 | 4.4768 | 2.2384 | H2 | 4 | Stable | 0.6 | 107 | 127 | 153 | 128 | 0.6 | 107 | 127 | 153 | 128 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 0.8 | 244.3581 | 12.2179 | Accept | 0.6 | 227.5702 | 11.3785 | H1 | 5 | Stable | 0.5 | 102 | 139 | 144 | 133.6667 | 0.5 | 102 | 139 | 144 | 133.6667 | 6.8702 | 25 | 0 | 4.1221
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-019 | Project_026_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Customer interaction and reporting may be much greater than anticipated | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 0.3 | 16.3694 | 4.9108 | Reduce | 0.2 | 16.3683 | 3.2737 | H3 | 3 | Stable | 0.7 | 99 | 140 | 160 | 136.5 | 0.3 | 37 | 57 | 61 | 54.3333 | 0.0068371 | 33.3333 | 0 | 0.0041023
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 01:00 | 2016-08-20 01:00 | 0.1 | 24.8462 | 12.4231 | Accept | 0.1 | 24.8462 | 12.4231 | H2 | 4 | Stable | 0.7 | 106 | 129 | 154 | 129.3333 | 0.7 | 106 | 129 | 154 | 129.3333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 0.2 | 60.4367 | 3.0218 | Accept | 0.2 | 60.4367 | 3.0218 | H3 | 3 | Improving | 0.9 | 107 | 130 | 148 | 129.1667 | 0.9 | 107 | 130 | 148 | 129.1667 | 0 | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.5 | 117 | 123 | 154 | 127.1667 | 0.2 | 16 | 42 | 63 | 41.1667 | 0 | 25 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Risk of repeat component Tests | Person_515 | 2017-12-20 23:00 | 2019-01-20 23:00 | 0.5 | 6.7866 | 6.7866 | Accept | 0.5 | 6.7866 | 6.7866 | H2 | 4 | Stable | 0.7 | 97 | 129 | 152 | 127.5 | 0.7 | 97 | 129 | 152 | 127.5 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-007 | Project_026_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Additional requests for information and attendance at meetings | Person_264 | 2014-11-21 01:00 | 2018-12-27 01:00 | 0.5 | 10.5249 | 5.2625 | Reduce | 0.5 | 10.5249 | 5.2625 | H2 | 4 | Stable | 0.6 | 118 | 126 | 146 | 128 | 0.4 | 38 | 45 | 73 | 48.5 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_515 | 2017-05-23 | 2019-01-20 23:00 | 0.5 | 3.4415 | 1.3766 | Accept | 0.5 | 3.4415 | 1.3766 | H2 | 4 | Stable | 0.9 | 83 | 126 | 145 | 122 | 0.9 | 83 | 126 | 145 | 122 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R44 | Project_041_R44 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Procurement - Source Change and cost change | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 0.5 | 8.0582 | 2.4175 | Accept | 0.5 | 8.0582 | 2.4175 | H1 | 5 | Worsening | 0.8 | 109 | 124 | 147 | 125.3333 | 0.8 | 109 | 124 | 147 | 125.3333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_368 | 2016-11-19 23:00 | 2017-09-18 23:00 | 0.25 | 0.55886 | 0.27943 | Accept | 0.25 | 7.824 | 1.5648 | H3 | 3 | Stable | 0.6 | 120 | 133 | 143 | 132.5 | 0.6 | 120 | 133 | 143 | 132.5 | -1300 | 0 | 0 | -780
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 0.1 | 3.8666 | 1.5853 | Accept | 0.1 | 1.3288 | 0.5448 | H3 | 3 | Stable | 0.8 | 119 | 125 | 147 | 127.6667 | 0.8 | 119 | 125 | 147 | 127.6667 | 65.6338 | 0 | 1 | 39.3803
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2016-11-17 01:00 | 0.85 | 25.2325 | 21.4476 | Avoid | 0.08 | 20.8758 | 1.6701 | H2 | 4 | Improving | [10 empty] | 17.2662 | 90.5882 | 0 | 10.3597
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R06 | Project_041_R06 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional PM time to support the supply chain | Person_359 | 2016-11-19 23:00 | 2017-09-18 23:00 | 0.25 | 2.7943 | 0.55886 | Accept | 0.25 | 2.7943 | 0.55886 | H3 | 3 | Stable | 0.5 | 98 | 126 | 142 | 124 | 0.5 | 98 | 126 | 142 | 124 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-018 | Project_023_Risk-018 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Project Management | Person_703 | 2013-05-19 | 2017-05-22 | 0.8 | 0.10892 | 0.087134 | Exploit | 0.8 | 0.10892 | 0.087134 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-09 | Project_022_RISK-09 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance - Issues arise | Person_393 | 2012-04-22 | 2016-11-19 01:00 | 0.7 | 24.8225 | 17.3758 | Reduce | 0.48 | 8.951 | 4.2965 | H2 | 4 | Stable | 0.5 | 93 | 132 | 145 | 127.6667 | 0.4 | 22 | 47 | 76 | 47.6667 | 63.94 | 31.4286 | 0 | 38.364
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 0.25 | 5.9904 | 1.4976 | Accept | 0.25 | 0 | 0 | H2 | 4 | Stable | 0.5 | 108 | 133 | 149 | 131.5 | 0.5 | 108 | 133 | 149 | 131.5 | 100 | 0 | 0 | 60
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-08 | Project_022_RISK-08 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Poor performance during acceptance phases | Person_248 | 2012-05-23 | 2016-11-19 01:00 | 0.65 | 5.6817 | 3.6931 | Reduce | 0.512 | 5.6817 | 2.909 | H1 | 5 | Stable | 0.7 | 85 | 130 | 145 | 125 | 0.2 | 20 | 45 | 62 | 43.6667 | 0 | 21.2308 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-111 | Project_039_Risk-111 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Maturation results inconclusive | Person_297 | 2016-02-21 01:00 | 2017-01-20 01:00 | 0.3 | 5.4459 | 1.6338 | Accept | 0.3 | 0.18151 | 0.054453 | H2 | 4 | Stable | 0.7 | 105 | 132 | 151 | 130.6667 | 0.7 | 105 | 132 | 151 | 130.6667 | 96.667 | 0 | 0 | 58.0002
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.35 | 2.9061 | 1.0171 | H2 | 4 | Worsening | 0.8 | 84 | 136 | 145 | 128.8333 | 0.4 | 28 | 53 | 77 | 52.8333 | 21.0126 | 56.25 | 0 | 12.6076
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-019 | Project_023_Risk-019 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software | Person_253 | 2013-05-19 | 2017-05-22 | 0.8 | 0.38121 | 0.30497 | Exploit | 0.8 | 0.38121 | 0.30497 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-195 | Project_039_Risk-195 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Supply Chain Delays - System Comms, Component, and subsystem | Person_083 | 2016-08-21 01:00 | 2017-02-19 01:00 | 0.3 | 2.3975 | 2.3975 | Accept | 0.3 | 0.66364 | 0.66364 | H3 | 3 | Worsening | 0.6 | 103 | 131 | 157 | 130.6667 | 0.6 | 103 | 131 | 157 | 130.6667 | 72.3193 | 0 | 0 | 43.3916
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2016-11-17 01:00 | 0.7 | 24.1887 | 16.9321 | Reduce | 0.25 | 4.3567 | 1.0892 | H2 | 4 | Stable | 0.9 | 109 | 131 | 156 | 131.5 | 0.4 | 8 | 42 | 61 | 39.5 | 81.9887 | 64.2857 | 0 | 49.1932
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-22 | Project_022_RISK-22 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Setting to work Issues - monitor may require changing | Person_393 | 2014-10-22 01:00 | 2016-11-19 01:00 | 0.6 | 11.6428 | 6.9857 | Reduce | 0.2 | 12.2515 | 2.4503 | H3 | 3 | Worsening | 0.9 | 110 | 138 | 144 | 134.3333 | 0.2 | 6 | 59 | 77 | 53.1667 | -5.228 | 66.6667 | 0 | -3.1368
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-020 | Project_023_Risk-020 | Opportunitity | Project Contingency | Open | H2 | 4 | 8. System Engineering | Installation & Acceptance - Preventative Maintenance | Person_253 | 2013-05-19 | 2017-05-22 | 0.8 | 0.81688 | 0.6535 | Exploit | 0.8 | 0.81688 | 0.6535 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-30 | Project_022_RISK-30 | Opportunitity | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Setting to work and acceptance issues | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 0.8 | 8.6133 | 6.8907 | Exploit | 0.8 | 2.6904 | 2.1524 | H2 | 4 | Stable | [10 empty] | 68.7641 | 0 | 0 | 41.2585
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 3.3531 | 2.6825 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-58 | Project_022_RISK-58 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Handbook Update | Person_248 | 2012-04-19 | 2016-11-19 01:00 | 0.5 | 2.2354 | 1.1177 | Reduce | 0.5 | 2.2354 | 1.1177 | H3 | 3 | Stable | 0.9 | 88 | 121 | 155 | 121.1667 | 0.1 | 5 | 52 | 73 | 47.6667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-22 01:00 | 2017-05-22 | 0.25 | 7.4225 | 1.8556 | Reduce | 0.1 | 3.7113 | 0.37113 | H3 | 3 | Stable | 0.7 | 115 | 129 | 153 | 130.6667 | 0.3 | 16 | 52 | 76 | 50 | 50 | 60 | 0 | 30
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 2.6991 | 1.0796 | H2 | 4 | Stable | 0.7 | 116 | 126 | 147 | 127.8333 | 0.3 | 28 | 45 | 74 | 47 | 31.8182 | 20 | 0 | 19.0909
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_575 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 6.2979 | 0.94468 | H3 | 3 | Stable | 0.9 | 100 | 123 | 153 | 124.1667 | 0.2 | 5 | 50 | 62 | 44.5 | 0 | 70 | 1 | 2.1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-148 | Project_020_Risk-148 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs non-available items | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.3 | 14.9935 | 4.498 | Reduce | 0.3 | 14.9935 | 4.498 | H2 | 4 | Stable | 0.6 | 103 | 132 | 158 | 131.5 | 0.3 | 36 | 57 | 75 | 56.5 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-194 | Project_027_Risk-194 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | The effect of specialist supplier obsolescence on complex assemblies | Person_074 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.08 | 18.6688 | 3.7338 | Accept | 0.08 | 18.6688 | 3.7338 | H3 | 3 | Stable | 0.5 | 88 | 140 | 154 | 133.6667 | 0.5 | 88 | 140 | 154 | 133.6667 | 0 | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-147 | Project_020_Risk-147 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component taking longer to refurbish in country | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.6 | 6.7477 | 4.0486 | Reduce | 0.6 | 6.7477 | 4.0486 | H2 | 4 | Stable | 0.7 | 84 | 135 | 146 | 128.3333 | 0.1 | 22 | 53 | 61 | 49.1667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-150 | Project_020_Risk-150 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Power supply Test Environment | Person_248 | 2016-10-21 01:00 | 2017-05-22 | 0.6 | 6.7477 | 4.0486 | Reduce | 0.6 | 6.7477 | 4.0486 | H2 | 4 | Worsening | 0.8 | 95 | 126 | 158 | 126.1667 | 0.2 | 35 | 58 | 73 | 56.6667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-187 | Project_027_Risk-187 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Loss of a major sub-contractor | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.12 | 3.1818 | 1.5909 | Accept | 0.12 | 3.1818 | 1.5909 | H3 | 3 | Stable | 0.8 | 110 | 130 | 146 | 129.3333 | 0.8 | 110 | 130 | 146 | 129.3333 | 0 | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-12-21 01:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.6 | 82 | 137 | 141 | 128.5 | 0.4 | 10 | 44 | 68 | 42.3333 | 47 | 0 | 0 | 28.2
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-12-21 01:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-196 | Project_027_Risk-196 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Aging equipment resulting in increasing failure rates | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 10.7826 | 4.3131 | Accept | 0.1 | 10.7826 | 4.3131 | H3 | 3 | Stable | 0.9 | 88 | 136 | 156 | 131.3333 | 0.9 | 88 | 136 | 156 | 131.3333 | 0 | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK117 | Project_037_RISK117 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Data Comms Availability or Performance | Person_334 | 2015-05-24 | 2016-11-20 01:00 | 0.35 | 3.2401 | 1.134 | Transfer | 0.1 | 3.2401 | 0.32401 | H3 | 3 | Improving | [10 empty] | 0 | 71.4286 | 1 | 2.1429
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-19 01:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.3 | 3.187 | 0.9561 | H2 | 4 | Stable | 0.5 | 90 | 122 | 153 | 121.8333 | 0.4 | 4 | 59 | 72 | 52 | 0 | 25 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-185 | Project_027_Risk-185 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier manufacturing issues | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.6 | 2.3457 | 0.11728 | Accept | 0.05 | 2.3457 | 0.023457 | H3 | 3 | Stable | 0.9 | 86 | 124 | 145 | 121.1667 | 0.9 | 86 | 124 | 145 | 121.1667 | 0 | 91.6667 | 1 | 2.75
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-186 | Project_027_Risk-186 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Potential for composite suppliers going out of business | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 0.034059 | 0.0034059 | Accept | 0.1 | 0.034059 | 0.0034059 | H3 | 3 | Stable | 0.8 | 94 | 135 | 149 | 130.5 | 0.8 | 94 | 135 | 149 | 130.5 | 0 | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment environmental failure | Person_289 | 2016-05-23 | 2016-12-02 01:00 | 0.3 | 0.35539 | 0.17769 | Accept | 0.3 | 0.35539 | 0.088847 | H1 | 5 | Improving | 0.8 | 81 | 134 | 157 | 129 | 0.8 | 81 | 134 | 157 | 129 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk005 | Project_002_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2014-06-14 | 2016-08-08 | 0.3 | 0.035539 | 0.010662 | Avoid | 0.3 | 0.035539 | 0.010662 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk008 | Project_002_Risk008 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2014-08-20 | 2016-08-07 | 0.1 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | -100 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk009 | Project_002_Risk009 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2014-06-14 | 2016-08-07 | 0.1 | 0.01925 | 0.001925 | Avoid | 0.1 | 0.01925 | 0.001925 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | RISK012 | Project_002_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Resourcing Suitably Qualified and experienced staff availability | Person_650 | 2015-11-21 | 2016-08-07 | 0.2 | 0.05627 | 0.011254 | Reduce | 0.2 | 0.05627 | 0.011254 | H3 | 3 | Stable | 0.7 | 111 | 138 | 143 | 134.3333 | 0.4 | 3 | 49 | 79 | 46.3333 | 0 | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk004 | Project_002_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability of Test Equipment | Person_133 | 2014-03-26 | 2016-08-08 | 0.2 | 0.081443 | 0.016289 | Avoid | 0.2 | 0.081443 | 0.016289 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk006 | Project_002_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Additional Pressure Testing | Person_650 | 2014-06-14 | 2016-08-08 | 0.25 | 0.035539 | 0.0088847 | Avoid | 0.25 | 0.035539 | 0.0088847 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk011 | Project_002_Risk011 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Testing | Person_175 | 2014-06-29 | 2016-08-07 | 0.41 | 0.071669 | 0.029384 | Reduce | 0.1 | 0.0088847 | 0.00088847 | H3 | 3 | Stable | 0.9 | 94 | 128 | 149 | 125.8333 | 0.3 | 21 | 55 | 69 | 51.6667 | 87.6032 | 75.6098 | 1 | 54.8302
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Retained systems re-design or modification | Person_289 | 2016-08-20 01:00 | 2017-02-19 01:00 | 0.05 | 3.9852 | 0.9963 | Accept | 0.05 | 0 | 0 | H2 | 4 | Improving | 0.6 | 83 | 137 | 158 | 131.5 | 0.6 | 83 | 137 | 158 | 131.5 | 100 | 0 | 0 | 60
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-034 | Project_005_Risk-034 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project delay causes cost impact to project | Person_470 | 2011-12-02 01:00 | 2016-10-30 01:00 | 0.5 | 16.3745 | 8.1873 | Reduce | 0.1 | 2.5077 | 0.25077 | H3 | 3 | Stable | 0.5 | 119 | 126 | 145 | 128 | 0.1 | 9 | 57 | 71 | 51.3333 | 84.6854 | 80 | 1 | 53.2113
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Mission System not compatible with platform systems | Person_289 | 2016-07-21 | 2017-02-19 01:00 | 0.1 | 1.6266 | 0.8133 | Accept | 0.1 | 1.6266 | 0.08133 | H3 | 3 | Stable | 0.5 | 119 | 134 | 149 | 134 | 0.5 | 119 | 134 | 149 | 134 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Qual failure | Person_289 | 2016-06-22 | 2016-11-20 01:00 | 0.4 | 6.3266 | 1.898 | Accept | 0.4 | 6.3266 | 1.297 | H1 | 5 | Improving | 0.8 | 120 | 132 | 149 | 132.8333 | 0.8 | 120 | 132 | 149 | 132.8333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Additional minor releases | Person_073 | 2016-05-23 | 2017-08-20 01:00 | 0.5 | 3.2155 | 0.96464 | Accept | 0.5 | 3.2155 | 0.96464 | H1 | 5 | Stable | 0.6 | 95 | 126 | 153 | 125.3333 | 0.6 | 95 | 126 | 153 | 125.3333 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Digital Video Chainredesign | Person_289 | 2016-06-22 | 2016-12-17 01:00 | 0.71 | 1.2271 | 0.50311 | Accept | 0.75 | 1.2271 | 0.50311 | H1 | 5 | Worsening | 0.6 | 107 | 131 | 154 | 130.8333 | 0.6 | 107 | 131 | 154 | 130.8333 | 0 | -5.6338 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK380 | Project_035_RISK380 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Data Throttling Algorithm | Person_699 | 2016-01-03 01:00 | 2016-11-20 01:00 | 0.2 | 2.6071 | 0.52143 | Reduce | 0.2 | 2.6071 | 0.52143 | H3 | 3 | Stable | 0.7 | 107 | 128 | 148 | 127.8333 | 0.3 | 17 | 43 | 74 | 43.8333 | 0 | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK394 | Project_035_RISK394 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Provision of supplier evidence | Person_631 | 2016-02-21 01:00 | 2016-10-21 01:00 | 0.5 | 2.4768 | 1.2384 | -- | 0.5 | 1.2167 | 0.60833 | H2 | 4 | Improving | [10 empty] | 50.8773 | 0 | 0 | 30.5264
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK290 | Project_035_RISK290 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Face-to-Face Arbitration | Person_699 | 2015-01-22 01:00 | 2017-01-21 01:00 | 0.5 | 1.2445 | 0.62224 | -- | 0.2 | 2.303 | 0.46059 | H3 | 3 | Worsening | [10 empty] | -85.0557 | 60 | 0 | -51.0334
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK395 | Project_035_RISK395 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Test area Site Availability | Person_691 | 2016-05-23 | 2016-11-19 01:00 | 0.5 | 3.0417 | 1.5208 | -- | 0.5 | 3.0417 | 1.5208 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK114 | Project_035_RISK114 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Qualification Facilities Availability. | Person_570 | 2015-09-21 01:00 | 2016-08-20 01:00 | 0.61 | 1.2358 | 0.75383 | Reduce | 0.3 | 1.2358 | 0.37073 | H2 | 4 | Stable | 0.6 | 111 | 121 | 141 | 122.6667 | 0.3 | 21 | 48 | 77 | 48.3333 | 0 | 50.8197 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK189 | Project_024_RISK189 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment integration - Audio and Video recording | Person_289 | 2016-08-20 01:00 | 2017-01-21 01:00 | 0.49 | 3.1633 | 0.63267 | Accept | 0.5 | 3.1633 | 0.63267 | H1 | 5 | Worsening | 0.7 | 82 | 127 | 153 | 123.8333 | 0.7 | 82 | 127 | 153 | 123.8333 | 0 | -2.0408 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.7 | 106 | 132 | 158 | 132 | 0.1 | 24 | 43 | 64 | 43.3333 | 25.8065 | 20 | 0 | 15.4839
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK024 | Project_012_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component Repair & test costs | Person_359 | 2015-04-04 | 2016-04-12 | 0.7 | 0.84985 | 0.5949 | -- | 0.18 | 0.84985 | 0.15297 | H2 | 4 | Improving | [10 empty] | 0 | 74.2857 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-21 01:00 | 2016-08-21 01:00 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.5 | 119 | 133 | 147 | 133 | 0.1 | 20 | 51 | 63 | 47.8333 | 0 | 16.6667 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_289 | 2016-05-23 | 2016-12-20 01:00 | 0.4 | 7.689 | 2.6911 | Accept | 0.4 | 7.689 | 2.6911 | H1 | 5 | Stable | 0.7 | 97 | 125 | 141 | 123 | 0.7 | 97 | 125 | 141 | 123 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK194 | Project_024_RISK194 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Performance Models require additional effort | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.25 | 5.4336 | 1.3584 | Accept | 0.25 | 5.4336 | 1.3584 | H2 | 4 | Stable | 0.9 | 101 | 140 | 150 | 135.1667 | 0.9 | 101 | 140 | 150 | 135.1667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK195 | Project_024_RISK195 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Perfomance Validation document not accepted | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.1 | 5.126 | 2.563 | Accept | 0.1 | 5.126 | 2.563 | H2 | 4 | Stable | 0.5 | 114 | 126 | 160 | 129.6667 | 0.5 | 114 | 126 | 160 | 129.6667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK197 | Project_024_RISK197 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Fitness for purpose | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.2 | 12.815 | 2.563 | Accept | 0.2 | 12.815 | 2.563 | H2 | 4 | Improving | 0.7 | 112 | 131 | 160 | 132.6667 | 0.7 | 112 | 131 | 160 | 132.6667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.9 | 97 | 134 | 148 | 130.1667 | 0.1 | 12 | 54 | 79 | 51.1667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.6 | 91 | 135 | 143 | 129 | 0.3 | 12 | 59 | 66 | 52.3333 | 0 | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK007 | Project_004_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-03-21 | 0.2 | 0.15317 | 0.030633 | Reduce | 0.2 | 0.10883 | 0.021765 | H3 | 3 | Stable | 0.8 | 90 | 127 | 147 | 124.1667 | 0.1 | 29 | 48 | 74 | 49.1667 | 28.9481 | 0 | 1 | 17.3689
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK004 | Project_004_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2014-11-20 | 2016-03-21 | 0.2 | 0.14752 | 0.029504 | Avoid | 0.2 | 0.14752 | 0.029504 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK003 | Project_004_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-05-24 | 2016-03-21 | 0.2 | 0.060459 | 0.012092 | Avoid | 0.2 | 0.060459 | 0.012092 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK006 | Project_004_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2014-11-19 | 2016-03-21 | 0.1 | 0.049978 | 0.0049978 | Avoid | 0.1 | 0.049978 | 0.0049978 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK005 | Project_004_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2014-11-20 | 2016-03-21 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK002 | Project_004_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2014-11-20 | 2016-03-21 | 0.5 | 0.15317 | 0.076583 | Avoid | 0.5 | 0.15317 | 0.076583 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 19:00 | 2019-08-20 19:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.7 | 90 | 128 | 150 | 125.3333 | 0.2 | 38 | 44 | 73 | 47.8333 | 83.3333 | 88.8889 | 1 | 52.6667
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.7 | 80 | 126 | 149 | 122.1667 | 0.2 | 24 | 42 | 69 | 43.5 | 72 | 0 | 0 | 43.2
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.6 | 111 | 140 | 147 | 136.3333 | 0.2 | 2 | 48 | 68 | 43.6667 | 47.7391 | 0 | 0 | 28.6435
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 19:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.9 | 99 | 135 | 146 | 130.8333 | 0.1 | 23 | 46 | 69 | 46 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK004 | Project_004_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2014-11-20 | 2016-03-21 | 0.2 | 0.14752 | 0.029504 | Avoid | 0.2 | 0.14752 | 0.029504 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK003 | Project_004_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-05-24 | 2016-03-21 | 0.2 | 0.060459 | 0.012092 | Avoid | 0.2 | 0.060459 | 0.012092 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK006 | Project_004_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2014-11-19 | 2016-03-21 | 0.1 | 0.049978 | 0.0049978 | Avoid | 0.1 | 0.049978 | 0.0049978 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK005 | Project_004_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2014-11-20 | 2016-03-21 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK002 | Project_004_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2014-11-20 | 2016-03-21 | 0.5 | 0.15317 | 0.076583 | Avoid | 0.5 | 0.15317 | 0.076583 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK007 | Project_004_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-03-21 | 0.2 | 0.15317 | 0.030633 | Reduce | 0.2 | 0.10883 | 0.021765 | H3 | 3 | Stable | 0.8 | 114 | 133 | 150 | 132.6667 | 0.1 | 24 | 45 | 76 | 46.6667 | 28.9481 | 0 | 1 | 17.3689
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk005 | Project_002_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2014-06-14 | 2016-08-08 | 0.3 | 0.035539 | 0.010662 | Avoid | 0.3 | 0.035539 | 0.010662 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk008 | Project_002_Risk008 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2014-08-19 23:00 | 2016-08-07 | 0.1 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | -100 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk009 | Project_002_Risk009 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2014-06-14 | 2016-08-07 | 0.1 | 0.01925 | 0.001925 | Avoid | 0.1 | 0.01925 | 0.001925 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | RISK012 | Project_002_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Resourcing Suitably Qualified and experienced staff availability | Person_650 | 2015-11-20 23:00 | 2016-08-07 | 0.2 | 0.05627 | 0.011254 | Reduce | 0.2 | 0.05627 | 0.011254 | H3 | 3 | Stable | 0.7 | 100 | 125 | 144 | 124 | 0.1 | 23 | 51 | 69 | 49.3333 | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk004 | Project_002_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability of Test Equipment | Person_133 | 2014-03-26 | 2016-08-08 | 0.2 | 0.081443 | 0.016289 | Avoid | 0.2 | 0.081443 | 0.016289 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk006 | Project_002_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Additional Pressure Testing | Person_650 | 2014-06-14 | 2016-08-08 | 0.25 | 0.035539 | 0.0088847 | Avoid | 0.25 | 0.035539 | 0.0088847 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk011 | Project_002_Risk011 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Testing | Person_175 | 2014-06-29 | 2016-08-07 | 0.41 | 0.071669 | 0.029384 | Reduce | 0.1 | 0.0088847 | 0.00088847 | H3 | 3 | Stable | 0.9 | 91 | 127 | 158 | 126.1667 | 0.3 | 28 | 55 | 68 | 52.6667 | 87.6032 | 75.6098 | 1 | 54.8302
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK380 | Project_035_RISK380 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Data Throttling Algorithm | Person_699 | 2016-01-03 01:00 | 2016-11-20 01:00 | 0.2 | 2.6071 | 0.52143 | Reduce | 0.2 | 2.6071 | 0.52143 | H3 | 3 | Stable | 0.5 | 93 | 124 | 158 | 124.5 | 0.4 | 25 | 56 | 70 | 53.1667 | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK394 | Project_035_RISK394 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Provision of supplier evidence | Person_631 | 2016-02-21 01:00 | 2016-11-20 01:00 | 0.5 | 2.4768 | 1.2384 | -- | 0.4 | 1.2167 | 0.48666 | H3 | 3 | Improving | [10 empty] | 50.8773 | 20 | 0 | 30.5264
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK290 | Project_035_RISK290 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Face-to-Face Arbitration | Person_699 | 2015-01-22 01:00 | 2017-01-21 01:00 | 0.5 | 1.2445 | 0.62224 | -- | 0.15 | 2.303 | 0.34545 | H3 | 3 | Worsening | [10 empty] | -85.0557 | 70 | 0 | -51.0334
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK395 | Project_035_RISK395 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Test area Site Availability | Person_691 | 2016-05-23 | 2016-11-19 01:00 | 0.5 | 3.0417 | 1.5208 | -- | 0.5 | 3.0417 | 1.5208 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Obsolescence Monitoring Risk | Person_181 | 2016-12-02 23:00 | 2017-01-19 23:00 | 0.3 | 5.9458 | 1.7837 | Reduce | 0.15 | 0.9786 | 0.14679 | H3 | 3 | Stable | 0.6 | 82 | 125 | 146 | 121.3333 | 0.3 | 18 | 44 | 60 | 42.3333 | 83.5413 | 50 | 0 | 50.1248
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-47 | Project_022_RISK-47 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Software Issues | Person_245 | 2012-04-19 | 2016-11-19 01:00 | 0.5 | 35.0206 | 7.0041 | Accept | 0.2 | 35.0206 | 7.0041 | H3 | 3 | Stable | 0.8 | 113 | 140 | 154 | 137.8333 | 0.8 | 113 | 140 | 154 | 137.8333 | 0 | 60 | 1 | 1.8
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2016-12-08 01:00 | 0.41 | 15.0654 | 6.7794 | Accept | 0.41 | 15.0654 | 6.7794 | H2 | 4 | Stable | 0.5 | 113 | 129 | 155 | 130.6667 | 0.5 | 113 | 129 | 155 | 130.6667 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-51 | Project_022_RISK-51 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Environmental Conditions | Person_393 | 2012-04-19 | 2016-11-19 01:00 | 0.2 | 23.6737 | 11.8369 | Accept | 0.2 | 52.0822 | 23.437 | H3 | 3 | Stable | 0.7 | 88 | 127 | 141 | 122.8333 | 0.7 | 88 | 127 | 141 | 122.8333 | -120 | 0 | 0 | -72
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-043 | Project_008_Risk-043 | Opportunitity | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Joint courseware and tech pubs team | Person_280 | 2014-11-21 01:00 | 2017-05-21 | 0.5 | 28.2191 | 14.1096 | -- | 0.8 | 13.2573 | 10.6058 | H1 | 5 | Stable | [10 empty] | 53.0201 | -60 | 0 | 31.8121
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-059 | Project_008_Risk-059 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Project Resource Efficencies | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 0.2 | 21.6852 | 4.337 | -- | 0.2 | 21.6852 | 4.337 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-015 | Project_023_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Illness | Person_371 | 2015-04-09 | 2016-12-11 01:00 | 0.25 | 15.8141 | 3.9535 | Accept | 0.25 | 15.8141 | 3.9535 | H2 | 4 | Stable | 0.6 | 81 | 140 | 160 | 133.5 | 0.6 | 81 | 140 | 160 | 133.5 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-016 | Project_023_Risk-016 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Damage to equipment (Unable to replace due to obsolescence) | Person_703 | 2015-10-22 01:00 | 2016-06-22 | 0.3 | 71.0212 | 21.3064 | Accept | 0.3 | 71.0212 | 21.3064 | H2 | 4 | Stable | 0.9 | 105 | 124 | 152 | 125.5 | 0.9 | 105 | 124 | 152 | 125.5 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 01:00 | 2017-03-22 | 0.05 | 87.6137 | 4.3807 | Reduce | 0.05 | 87.6137 | 4.3807 | H3 | 3 | Stable | 0.9 | 105 | 136 | 145 | 132.3333 | 0.3 | 38 | 58 | 61 | 55.1667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.3 | 53.0293 | 15.9088 | Reduce | 0.3 | 53.0293 | 15.9088 | H3 | 3 | Worsening | 0.5 | 118 | 133 | 145 | 132.5 | 0.3 | 8 | 42 | 69 | 40.8333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Commercial aspects agreement | Person_480 | 2013-08-21 01:00 | 2016-05-22 | 0.02 | 4.8296 | 0.096593 | Transfer | 0.02 | 4.8296 | 0.096593 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 01:00 | 2017-08-20 01:00 | 0.1 | 34.363 | 3.4363 | Avoid | 0.1 | 34.363 | 3.4363 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.48 | 33.2985 | 15.9833 | Avoid | 0.48 | 33.2985 | 15.9833 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-126 | Project_032_Risk-126 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supply Chain - Delivery to Contract Requirement | Person_590 | 2012-08-21 01:00 | 2016-08-20 01:00 | 0.3 | 25.3619 | 7.6086 | Reduce | 0.3 | 25.3619 | 7.6086 | H2 | 4 | Stable | 0.9 | 120 | 137 | 154 | 137 | 0.4 | 26 | 44 | 68 | 45 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.25 | 7.7469 | 1.9367 | Reduce | 0.25 | 7.7469 | 1.9367 | H3 | 3 | Stable | 0.6 | 85 | 133 | 145 | 127 | 0.4 | 17 | 45 | 61 | 43 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-131 | Project_032_Risk-131 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 0.3 | 15.6782 | 4.7035 | Transfer | 0.3 | 15.6782 | 4.7035 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 01:00 | 0.05 | 11.3437 | 0.56718 | Reduce | 0.05 | 11.3437 | 0.56718 | H3 | 3 | Stable | 0.7 | 101 | 130 | 145 | 127.6667 | 0.3 | 31 | 58 | 64 | 54.5 | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-109 | Project_011_Risk-109 | Opportunitity | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Environment complexity | Person_187 | 2016-07-21 | 2018-08-21 | 0.25 | 0.14661 | 0.036651 | -- | 0.25 | 0.14661 | 0.036651 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-108 | Project_011_Risk-108 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Offer additional functionality to the customer | Person_147 | 2017-04-22 | 2018-08-21 | 0.1 | 0.34094 | 0.034094 | -- | 0.1 | 0.34094 | 0.034094 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 0.2 | 0.12388 | 0.024775 | Reduce | 0.2 | 0.12388 | 0.024775 | H2 | 4 | Stable | 0.9 | 114 | 134 | 158 | 134.6667 | 0.2 | 5 | 59 | 69 | 51.6667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 0.4 | 0.51141 | 0.20457 | Avoid | 0.4 | 0.51141 | 0.20457 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.2 | 0.10171 | 0.020343 | -- | 0.2 | 0.10171 | 0.020343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 0.3 | 0.28639 | 0.085917 | Reduce | 0.3 | 0.28639 | 0.085917 | H2 | 4 | Stable | 0.6 | 114 | 135 | 148 | 133.6667 | 0.2 | 11 | 46 | 63 | 43 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 2. Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 0.25 | 0 | 0 | -- | 0.25 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2017-10-21 01:00 | 2018-05-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 0.3 | 0.10626 | 0.031878 | -- | 0.3 | 0.01932 | 0.005796 | H3 | 3 | Stable | [10 empty] | 81.8181 | 0 | 0 | 49.0909
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-149 | Project_020_Risk-149 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs to be returned to UK | Person_703 | 2016-12-21 01:00 | 2017-11-19 01:00 | 0.2 | 1.0052 | 0.35182 | Accept | 0.2 | 1.0052 | 0.35182 | H2 | 4 | Stable | 0.8 | 85 | 139 | 144 | 130.8333 | 0.8 | 85 | 139 | 144 | 130.8333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-118 | Project_011_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer change environment | Person_187 | 2013-08-21 01:00 | 2018-08-21 | 0.1 | 0 | 0 | Avoid | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-116 | Project_011_Risk-116 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Delays to Qualification | Person_147 | 2017-04-22 | 2017-08-19 01:00 | 0.25 | 1.7297 | 0.43243 | -- | 0.25 | 1.7297 | 0.43243 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-104 | Project_011_Risk-104 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer delayed in providing Custeomr Furnished Equipment | Person_147 | 2016-06-23 | 2017-04-21 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.6 | 98 | 136 | 151 | 132.1667 | 0.1 | 39 | 46 | 74 | 49.5 |  | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 0.30685 | 0.06137 | Accept | 0.5 | 0.30685 | 0.06137 | H2 | 4 | Stable | 0.8 | 106 | 134 | 151 | 132.1667 | 0.8 | 106 | 134 | 151 | 132.1667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK004 | Project_010_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Export License | Person_359 | 2015-02-18 01:00 | 2017-08-20 01:00 | 0.8 | 0.18482 | 0.14786 | Reduce | 0.8 | 0.18482 | 0.14786 | H1 | 5 | Improving | 0.8 | 100 | 133 | 149 | 130.1667 | 0.1 | 11 | 54 | 60 | 47.8333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 0.3 | 0.51931 | 0.15579 | -- | 0.15 | 0.51931 | 0.077897 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 01:00 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.9 | 82 | 136 | 141 | 127.8333 | 0.1 | 2 | 56 | 73 | 49.8333 | 0 | 40 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 0.2 | 0.55005 | 0.11001 | Avoid | 0.2 | 0.55005 | 0.11001 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_468 | 2016-11-19 23:00 | 2018-11-19 23:00 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.1 | 6.431 | 0.6431 | H3 | 3 | Stable | 0.8 | 99 | 135 | 150 | 131.5 | 0.1 | 8 | 48 | 65 | 44.1667 | -47.0588 | 33.3333 | 1 | -27.2353
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 0.5 | 11.0894 | 0.55447 | Accept | 0.5 | 11.0894 | 0.55447 | H2 | 4 | Stable | 0.7 | 84 | 137 | 142 | 129 | 0.7 | 84 | 137 | 142 | 129 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R81 | Project_041_R81 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Re-imaging of PC's - additional material | Person_515 | 2016-11-19 23:00 | 2017-10-20 23:00 | 0.5 | 0.21008 | 0.10504 | Avoid | 0.5 | 0.21008 | 0.10504 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-123 | Project_011_Risk-123 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | No Requirement for Delta acceptance | Person_187 | 2017-06-23 | 2017-08-20 01:00 | 0.2 | 0.63074 | 0.12615 | -- | 0.2 | 0.63074 | 0.12615 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2016-07-21 | 2017-02-19 01:00 | 0.15 | 0.28639 | 0.042959 | -- | 0.15 | 0.28639 | 0.042959 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.7 | 0.92411 | 0.64688 | Reduce | 0.3 | 0.36965 | 0.11089 | H2 | 4 | Stable | 0.5 | 111 | 124 | 159 | 127.6667 | 0.2 | 35 | 53 | 62 | 51.5 | 60 | 57.1429 | 0 | 36
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R85 | Project_041_R85 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Go to Offshore initiative | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 0.15 | 7.7172 | 1.1576 | -- | 0.15 | 7.7172 | 1.1576 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-04-21 | 0.2 | 0.24207 | 0.048414 | -- | 0.2 | 0.24207 | 0.048414 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 01:00 | 2016-04-21 | 0.5 | 4.0661 | 2.033 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.7 | 112 | 121 | 148 | 124 | 0.3 | 8 | 56 | 74 | 51 | 0 | 90 | 1 | 2.7
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_368 | 2016-11-19 23:00 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.6 | 107 | 123 | 141 | 123.3333 | 0.2 | 13 | 50 | 63 | 46 | 0 | 50 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 0.2 | 1.661 | 0.33219 | Reduce | 0.2 | 1.661 | 0.33219 | H2 | 4 | Stable | 0.6 | 80 | 138 | 157 | 131.5 | 0.2 | 6 | 45 | 67 | 42.1667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.3 | 0.46206 | 0.13862 | H2 | 4 | Improving | 0.6 | 112 | 132 | 157 | 132.8333 | 0.2 | 9 | 49 | 73 | 46.3333 | 58.3333 | 50 | 0 | 35
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R43 | Project_041_R43 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Procurement - Component and Supplier Leadtime | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 0.25 | 10.9327 | 2.7332 | Reduce | 0.15 | 10.9327 | 1.6399 | H2 | 4 | Stable | 0.6 | 91 | 138 | 141 | 130.6667 | 0.2 | 13 | 52 | 71 | 48.6667 | 0 | 40 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 0.5 | 1.1089 | 0.88715 | Accept | 0.5 | 0.73929 | 0.44357 | H2 | 4 | Stable | 0.7 | 83 | 133 | 154 | 128.1667 | 0.7 | 83 | 133 | 154 | 128.1667 | 33.3333 | 0 | 0 | 20
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 0.75 | 10.7184 | 8.0388 | Reduce | 0.75 | 5.3592 | 4.0194 | H1 | 5 | Worsening | 0.8 | 92 | 133 | 145 | 128.1667 | 0.2 | 24 | 57 | 76 | 54.6667 | 50 | 0 | 0 | 30
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2017-10-21 01:00 | 2018-08-21 | 0.4 | 1.2444 | 0.49778 | Reduce | 0.4 | 1.2444 | 0.49778 | H2 | 4 | Stable | 0.8 | 118 | 137 | 150 | 136 | 0.2 | 3 | 44 | 75 | 42.3333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 01:00 | 2017-08-20 01:00 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.9 | 110 | 134 | 151 | 132.8333 | 0.1 | 30 | 50 | 74 | 50.6667 | 0 | 50 | 1 | 1.5
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK118 | Project_037_RISK118 | Threat | Management Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Product does not deliver the inputs/depdencies required by the Project by the req'd dates | Person_330 | 2015-02-24 | 2016-06-23 | 0.4 | 0.16195 | 0.072876 | Accept | 0.4 | 0.16195 | 0.072876 | H2 | 4 | Worsening | 0.7 | 114 | 121 | 157 | 125.8333 | 0.7 | 114 | 121 | 157 | 125.8333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R86 | Project_041_R86 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sharing Attrition Stock with Warranty Spares pool | Person_501 | 2016-11-19 23:00 | 2018-05-22 | 0.5 | 3.1083 | 1.5542 | Exploit | 0.5 | 3.1083 | 1.5542 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.8 | 87 | 122 | 160 | 122.5 | 0.3 | 6 | 44 | 71 | 42.1667 | 0 | 25 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_040 | RISK174 | Project_040_RISK174 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Supplier Power Supply quality | Person_687 | 2013-08-20 21:00 | 2014-07-22 | 0.05 | 1.9722 | 0.98609 | Accept | 0.01 | 1.9722 | 0.98609 | H2 | 4 | Stable | 0.8 | 104 | 125 | 149 | 125.5 | 0.8 | 104 | 125 | 149 | 125.5 | 0 | 80 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 01:00 | 2018-08-21 | 0.45 | 0.83883 | 0.37747 | Reduce | 0.45 | 0.83883 | 0.37747 | H2 | 4 | Stable | 0.7 | 104 | 123 | 149 | 124.1667 | 0.4 | 30 | 52 | 69 | 51.1667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Stable | 0.8 | 83 | 133 | 158 | 128.8333 | 0.2 | 9 | 46 | 75 | 44.6667 | 0 | 40 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk010 | Project_002_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability | Person_357 | 2014-06-14 | 2016-08-07 | 0.1 | 2.5081 | 1.2541 | Accept | 0.1 | 2.5081 | 1.2541 | H3 | 3 | Worsening | 0.7 | 92 | 139 | 141 | 131.5 | 0.7 | 92 | 139 | 141 | 131.5 | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Worsening | [10 empty] | 0 | 37.5 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk002 | Project_002_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Transducer Element Failures | Person_650 | 2014-06-04 | 2016-08-07 | 0.5 | 7.0313 | 3.5156 | Accept | 0.25 | 7.0313 | 3.5156 | H2 | 4 | Worsening | 0.5 | 99 | 124 | 149 | 124 | 0.5 | 99 | 124 | 149 | 124 | 0 | 50 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-010 | Project_005_Risk-010 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Risk that required resources (people and rigs) will not be available as required due to other projects/bids (Customer & Internal) | Person_470 | 2011-11-11 01:00 | 2016-11-18 01:00 | 0.25 | 3.6965 | 0.36965 | Accept | 0.1 | 3.6965 | 0.36965 | H3 | 3 | Stable | 0.5 | 119 | 123 | 154 | 127.5 | 0.5 | 119 | 123 | 154 | 127.5 | 0 | 60 | 1 | 1.8
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-060 | Project_005_Risk-060 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Technical Acceptance may be more difficult than anticipated | Person_470 | 2014-06-11 | 2016-10-18 01:00 | 0.5 | 0.33412 | 0.15036 | Accept | 0.05 | 0.33412 | 0.15036 | H3 | 3 | Stable | 0.9 | 114 | 130 | 141 | 129.1667 | 0.9 | 114 | 130 | 141 | 129.1667 | 0 | 90 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK313 | Project_035_RISK313 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Deployed Performance inadequate | Person_303 | 2015-05-24 | 2016-10-21 01:00 | 0.3 | 0.92411 | 0.18482 | Accept | 0.205 | 0.92411 | 0.18482 | H2 | 4 | Improving | 0.9 | 120 | 130 | 154 | 132.3333 | 0.9 | 120 | 130 | 154 | 132.3333 | 0 | 31.6667 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-010 | Project_011_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Rework required following integration of Customer System | Person_142 | 2013-08-21 01:00 | 2017-04-21 | 0.4 | 0.66881 | 0.26753 | Reduce | 0.4 | 0.66881 | 0.26753 | H2 | 4 | Stable | 0.6 | 95 | 122 | 156 | 123.1667 | 0.3 | 27 | 46 | 75 | 47.6667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.05 | 0.68598 | 0.034299 | H3 | 3 | Stable | 0.8 | 87 | 136 | 157 | 131.3333 | 0.3 | 4 | 48 | 74 | 45 | 0 | 80 | 1 | 2.4
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 0.3 | 1.8482 | 0.55447 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.5 | 84 | 122 | 144 | 119.3333 | 0.4 | 31 | 57 | 79 | 56.3333 | 0 | 33.3333 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK308 | Project_035_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Facility performance during Live trials | Person_303 | 2015-05-24 | 2016-10-21 01:00 | 0.3 | 1.2519 | 0.31298 | Accept | 0.3 | 1.2519 | 0.31298 | H2 | 4 | Improving | 0.6 | 107 | 135 | 142 | 131.5 | 0.6 | 107 | 135 | 142 | 131.5 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK304 | Project_035_RISK304 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change at Elevation | Person_425 | 2016-09-20 01:00 | 2017-01-20 01:00 | 0.41 | 0.098873 | 0.0098873 | Accept | 0.41 | 0.098873 | 0.0098873 | H2 | 4 | Stable | 0.5 | 103 | 131 | 156 | 130.5 | 0.5 | 103 | 131 | 156 | 130.5 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK312 | Project_035_RISK312 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Audio Performance inadequate | Person_303 | 2015-06-24 | 2016-10-21 01:00 | 0.2 | 3.7514 | 0.37514 | Accept | 0.2 | 3.7514 | 0.37514 | H3 | 3 | Stable | 0.7 | 92 | 131 | 159 | 129.1667 | 0.7 | 92 | 131 | 159 | 129.1667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 01:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.6 | 120 | 130 | 149 | 131.5 | 0.4 | 20 | 43 | 75 | 44.5 | 90 | 75 | 1 | 56.25
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R29 | Project_041_R29 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Attrition | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 0.1 | 3.6014 | 0.36014 | Reduce | 0.05 | 3.6014 | 0.18007 | H3 | 3 | Stable | 0.5 | 115 | 129 | 159 | 131.6667 | 0.3 | 27 | 54 | 69 | 52 | 0 | 50 | 1 | 1.5
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2016-11-19 23:00 | 2017-07-21 | 0.1 | 21.8655 | 2.1865 | Reduce | 0.05 | 21.8655 | 1.0933 | H2 | 4 | Stable | 0.7 | 97 | 134 | 141 | 129 | 0.3 | 25 | 54 | 64 | 50.8333 | 0 | 50 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Stable | 0.9 | 87 | 140 | 158 | 134.1667 | 0.1 | 24 | 40 | 77 | 43.5 | 0 | 60 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.35 | 0.6088 | 0.1522 | Accept | 0.35 | 0.6088 | 0.1522 | H3 | 3 | Stable | 0.7 | 85 | 138 | 145 | 130.3333 | 0.7 | 85 | 138 | 145 | 130.3333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Unidentified Change Requests | Person_693 | 2016-11-19 23:00 | 2017-09-19 23:00 | 0.5 | 1.2005 | 0.60023 | Reduce | 0.1 | 0.51019 | 0.051019 | H3 | 3 | Stable | 0.5 | 92 | 139 | 149 | 132.8333 | 0.3 | 8 | 47 | 77 | 45.5 | 57.5001 | 80 | 1 | 36.9001
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.25 | 3.3227 | 0.83067 | Accept | 0.25 | 3.3227 | 0.83067 | H3 | 3 | Stable | 0.9 | 111 | 140 | 151 | 137 | 0.9 | 111 | 140 | 151 | 137 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.1 | 0.77172 | 0.077172 | H3 | 3 | Stable | 0.5 | 116 | 125 | 145 | 126.8333 | 0.4 | 39 | 42 | 74 | 46.8333 | 0 | 60 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-117 | Project_039_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Filters | Person_185 | 2015-01-21 01:00 | 2016-12-19 01:00 | 0.1 | 3.005 | 0.3005 | Reduce | 0.1 | 3.005 | 0.3005 | H3 | 3 | Stable | 0.8 | 101 | 134 | 149 | 131 | 0.1 | 24 | 53 | 61 | 49.5 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production or Engineering | Person_359 | 2016-11-19 23:00 | 2018-05-22 | 0.15 | 1.1576 | 0.17364 | Reduce | 0.1 | 1.1576 | 0.11576 | H3 | 3 | Stable | 0.8 | 112 | 127 | 156 | 129.3333 | 0.4 | 1 | 42 | 65 | 39 | 0 | 33.3333 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-21 01:00 | 2019-08-20 | 0.5 | 0.35617 | 0.10685 | Accept | 0.5 | 0.35617 | 0.10685 | H2 | 4 | Stable | 0.6 | 98 | 138 | 146 | 132.6667 | 0.6 | 98 | 138 | 146 | 132.6667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R13 | Project_041_R13 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Loss of key personnel | Person_359 | 2016-11-19 23:00 | 2017-08-19 23:00 | 0.5 | 0.59165 | 0.29583 | Reduce | 0.1 | 0.59165 | 0.059165 | H3 | 3 | Stable | 0.5 | 90 | 128 | 147 | 124.8333 | 0.4 | 24 | 54 | 68 | 51.3333 | 0 | 80 | 1 | 2.4
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 0.2 | 1.8602 | 0.55807 | Accept | 0.2 | 1.8602 | 0.55807 | H3 | 3 | Stable | 0.8 | 119 | 127 | 144 | 128.5 | 0.8 | 119 | 127 | 144 | 128.5 | 0 | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 0.61 | 1.4882 | 0.44646 | Accept | 0.61 | 1.4882 | 0.44646 | H1 | 5 | Stable | 0.7 | 116 | 136 | 144 | 134 | 0.7 | 116 | 136 | 144 | 134 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 0.4 | 9.139 | 3.6556 | Avoid | 0.2 | 9.139 | 1.8278 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK226 | Project_038_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Capacity to support enhancements or fixes post delivery | Person_330 | 2015-11-21 01:00 | 2017-05-22 | 0.5 | 13.9332 | 6.9666 | Avoid | 0.1 | 13.9332 | 1.3933 | H3 | 3 | Improving | [10 empty] | 0 | 80 | 1 | 2.4
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 0.5 | 13.7833 | 6.8917 | Avoid | 0.2 | 6.8917 | 1.3783 | H3 | 3 | Stable | [10 empty] | 50 | 60 | 1 | 31.8
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK187 | Project_038_RISK187 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Technical Publications | Person_671 | 2015-07-22 | 2016-12-20 01:00 | 0.5 | 4.6444 | 2.3222 | Avoid | 0.3 | 1.648 | 0.4944 | H2 | 4 | Worsening | [10 empty] | 64.5162 | 40 | 0 | 38.7097
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-20 01:00 | 0.3 | 5.5433 | 1.663 | Reduce | 0.1 | 5.5433 | 0.55433 | H3 | 3 | Improving | 0.5 | 92 | 136 | 157 | 132.1667 | 0.1 | 35 | 50 | 68 | 50.5 | 0 | 66.6667 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Stable | [10 empty] | 0 | 75 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk010 | Project_002_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability | Person_357 | 2014-06-14 | 2016-08-07 | 0.1 | 4.4946 | 1.1236 | Accept | 0.1 | 4.4946 | 0.44946 | H3 | 3 | Worsening | 0.9 | 93 | 130 | 156 | 128.1667 | 0.9 | 93 | 130 | 156 | 128.1667 | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk002 | Project_002_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Transducer Element Failures | Person_650 | 2014-06-04 | 2016-08-07 | 0.5 | 6.7418 | 1.6855 | Accept | 0.25 | 6.7418 | 1.0113 | H2 | 4 | Worsening | 0.5 | 112 | 124 | 147 | 125.8333 | 0.5 | 112 | 124 | 147 | 125.8333 | 0 | 50 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 0.125 | 232.2192 | 29.0274 | -- | 0.297 | 27.8663 | 8.2763 | H2 | 4 | Stable | [10 empty] | 88 | -137.6 | 0 | 52.8
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 0.3 | 26.9674 | 8.0902 | Avoid | 0.3 | 14.9819 | 4.4946 | H2 | 4 | Stable | [10 empty] | 44.4444 | 0 | 0 | 26.6667
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-21 01:00 | 0.5 | 26.9674 | 13.4837 | Avoid | 0.1 | 12.7646 | 1.2765 | H2 | 4 | Worsening | [10 empty] | 52.6667 | 80 | 0 | 31.6
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK313 | Project_035_RISK313 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Deployed Performance inadequate | Person_303 | 2015-05-24 | 2016-11-20 01:00 | 0.3 | 5.3935 | 1.3484 | Accept | 0.15 | 5.3935 | 1.3484 | H3 | 3 | Improving | 0.9 | 108 | 137 | 148 | 134 | 0.9 | 108 | 137 | 148 | 134 | 0 | 50 | 1 | 1.5
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK308 | Project_035_RISK308 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Facility performance during Live trials | Person_303 | 2015-05-24 | 2016-11-20 01:00 | 0.3 | 17.9783 | 3.5957 | Accept | 0.15 | 17.9783 | 3.5957 | H3 | 3 | Improving | 0.6 | 118 | 126 | 141 | 127.1667 | 0.6 | 118 | 126 | 141 | 127.1667 | 0 | 50 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-12-21 01:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.8 | 108 | 137 | 152 | 134.6667 | 0.3 | 33 | 41 | 72 | 44.8333 | 47 | 0 | 0 | 28.2
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-12-21 01:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK304 | Project_035_RISK304 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change at Elevation | Person_425 | 2016-09-20 01:00 | 2017-01-20 01:00 | 0.41 | 10.7826 | 4.3131 | Accept | 0.41 | 10.7826 | 4.3131 | H2 | 4 | Stable | 0.7 | 90 | 123 | 146 | 121.3333 | 0.7 | 90 | 123 | 146 | 121.3333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK117 | Project_037_RISK117 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Data Comms Availability or Performance | Person_334 | 2015-05-24 | 2016-11-20 01:00 | 0.35 | 3.2401 | 1.134 | Transfer | 0.05 | 3.2401 | 0.16201 | H3 | 3 | Improving | [10 empty] | 0 | 85.7143 | 1 | 2.5714
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-19 01:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.2 | 3.187 | 0.6374 | H3 | 3 | Stable | 0.8 | 98 | 140 | 143 | 133.5 | 0.2 | 14 | 52 | 77 | 49.8333 | 0 | 50 | 1 | 1.5
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK312 | Project_035_RISK312 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Audio Performance inadequate | Person_303 | 2015-06-24 | 2016-11-20 01:00 | 0.2 | 19.1935 | 1.5355 | Accept | 0.15 | 19.1935 | 1.5355 | H3 | 3 | Stable | 0.9 | 118 | 129 | 159 | 132.1667 | 0.9 | 118 | 129 | 159 | 132.1667 | 0 | 25 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-200 | Project_027_Risk-200 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Sucession Planning for key team members | Person_060 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.2 | 7.3175 | 1.4635 | Reduce | 0.05 | 7.3175 | 0.36588 | H2 | 4 | Stable | 0.9 | 82 | 123 | 143 | 119.5 | 0.3 | 16 | 42 | 69 | 42.1667 | 0 | 75 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-189 | Project_027_Risk-189 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Major Component obsolescence | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 8.3972 | 2.5191 | Reduce | 0.08 | 8.3972 | 0.67177 | H2 | 4 | Stable | 0.9 | 85 | 130 | 146 | 125.1667 | 0.4 | 20 | 40 | 75 | 42.5 | 0 | 73.3333 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-201 | Project_027_Risk-201 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Transition into Support | Person_027 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0.5 | 68.3768 | 34.1884 | Reduce | 0.05 | 38.387 | 1.9193 | H2 | 4 | Stable | 0.5 | 103 | 136 | 151 | 133 | 0.2 | 11 | 45 | 64 | 42.5 | 43.8597 | 90 | 0 | 26.3158
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-188 | Project_027_Risk-188 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Unidentified Technical Legacy Issue | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 20.0332 | 2.0033 | Reduce | 0.05 | 20.0332 | 1.0017 | H3 | 3 | Stable | 0.9 | 117 | 134 | 143 | 132.6667 | 0.4 | 4 | 46 | 60 | 41.3333 | 0 | 50 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-193 | Project_027_Risk-193 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | A greater number of arising technical queries | Person_110 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 13.7953 | 4.1386 | Reduce | 0.05 | 13.7953 | 0.68977 | H3 | 3 | Stable | 0.6 | 87 | 130 | 157 | 127.3333 | 0.4 | 37 | 59 | 68 | 56.8333 | 0 | 83.3333 | 1 | 2.5
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 0.5 | 35.9878 | 21.5927 | Accept | 0.45 | 15.5947 | 0.77974 | H2 | 4 | Stable | 0.7 | 114 | 121 | 160 | 126.3333 | 0.7 | 114 | 121 | 160 | 126.3333 | 56.6667 | 10 | 0 | 34
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation | Person_565 | 2018-05-22 | 2018-08-21 | 0.25 | 27.5907 | 2.7591 | Accept | 0.25 | 27.5907 | 2.7591 | H3 | 3 | Stable | 0.7 | 100 | 131 | 144 | 128 | 0.7 | 100 | 131 | 144 | 128 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 0.05 | 3.6174 | 1.8087 | Accept | 0.05 | 3.6172 | 0.72345 | H2 | 4 | Stable | 0.6 | 87 | 136 | 154 | 130.8333 | 0.6 | 87 | 136 | 154 | 130.8333 | 0.0051359 | 0 | 0 | 0.0030815
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 0.25 | 4.4768 | 2.2384 | Accept | 0.25 | 4.4768 | 2.2384 | H3 | 3 | Stable | 0.8 | 95 | 126 | 144 | 123.8333 | 0.8 | 95 | 126 | 144 | 123.8333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | More issues than expected during Qualification | Person_147 | 2017-04-22 | 2017-11-04 01:00 | 0.35 | 244.3581 | 12.2179 | Accept | 0.35 | 227.5702 | 11.3785 | H1 | 5 | Stable | 0.7 | 117 | 127 | 143 | 128 | 0.7 | 117 | 127 | 143 | 128 | 6.8702 | 0 | 0 | 4.1221
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-019 | Project_026_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Customer interaction and reporting may be much greater than anticipated | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 0.3 | 16.3694 | 4.9108 | Reduce | 0.2 | 16.3683 | 3.2737 | H3 | 3 | Stable | 0.8 | 98 | 123 | 150 | 123.3333 | 0.4 | 8 | 54 | 77 | 50.1667 | 0.0068371 | 33.3333 | 0 | 0.0041023
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 0.2 | 24.8462 | 12.4231 | Accept | 0.2 | 24.8462 | 12.4231 | H2 | 4 | Stable | 0.6 | 86 | 136 | 150 | 130 | 0.6 | 86 | 136 | 150 | 130 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.05 | 60.4367 | 3.0218 | Accept | 0.05 | 60.4367 | 3.0218 | H2 | 4 | Stable | 0.5 | 119 | 137 | 142 | 134.8333 | 0.5 | 119 | 137 | 142 | 134.8333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.8 | 113 | 122 | 159 | 126.6667 | 0.2 | 7 | 42 | 61 | 39.3333 | 0 | 25 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 0.8 | 6.7866 | 6.7866 | Accept | 0.6 | 6.7866 | 6.7866 | H1 | 5 | Stable | 0.5 | 119 | 127 | 144 | 128.5 | 0.5 | 119 | 127 | 144 | 128.5 | 0 | 25 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-007 | Project_026_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Additional requests for information and attendance at meetings | Person_264 | 2014-11-21 01:00 | 2018-12-27 01:00 | 0.5 | 10.5249 | 5.2625 | Reduce | 0.5 | 10.5249 | 5.2625 | H2 | 4 | Stable | 0.8 | 98 | 134 | 154 | 131.3333 | 0.4 | 5 | 56 | 60 | 48.1667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Risk of repeat component Tests | Person_515 | 2017-12-20 23:00 | 2019-01-20 23:00 | 0.5 | 8.0582 | 2.4175 | Accept | 0.5 | 8.0582 | 2.4175 | H2 | 4 | Stable | 0.5 | 101 | 133 | 151 | 130.6667 | 0.5 | 101 | 133 | 151 | 130.6667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-08-20 01:00 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.6 | 118 | 127 | 155 | 130.1667 | 0.2 | 6 | 43 | 63 | 40.1667 | 50 | 28.5714 | 0 | 30
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-02-19 01:00 | 0.5 | 17.2826 | 8.6413 | Reduce | 0.15 | 17.2826 | 2.5924 | H2 | 4 | Improving | 0.7 | 92 | 136 | 146 | 130.3333 | 0.2 | 3 | 45 | 66 | 41.5 | 0 | 70 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_470 | 2012-11-20 01:00 | 2017-06-22 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.8 | 80 | 140 | 160 | 133.3333 | 0.2 | 19 | 46 | 63 | 44.3333 | 0 | 50 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-04-21 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.4 | 12.6474 | 5.059 | H2 | 4 | Stable | 0.8 | 105 | 130 | 156 | 130.1667 | 0.2 | 33 | 51 | 75 | 52 | 0 | 33.3333 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2017-08-19 01:00 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.9 | 101 | 129 | 150 | 127.8333 | 0.1 | 38 | 56 | 63 | 54.1667 | 0 | 50 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target. | Person_482 | 2013-01-07 01:00 | 2017-06-06 | 0.3 | 4.7676 | 1.4303 | Reduce | 0.15 | 4.7676 | 0.71514 | H2 | 4 | Stable | 0.7 | 86 | 134 | 142 | 127.3333 | 0.1 | 33 | 50 | 66 | 49.8333 | 0 | 50 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 01:00 | 2017-01-19 01:00 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.5 | 113 | 133 | 149 | 132.3333 | 0.2 | 4 | 52 | 64 | 46 | 0 | 33.3333 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2017-05-21 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Worsening | 0.5 | 108 | 137 | 145 | 133.5 | 0.4 | 38 | 56 | 66 | 54.6667 | 0 | 57.1429 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-002 | Project_021_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.5 | 97 | 139 | 151 | 134 | 0.1 | 18 | 42 | 68 | 42.3333 |  | 66.6667 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H3 | 3 | Stable | 0.7 | 87 | 136 | 156 | 131.1667 | 0.3 | 9 | 49 | 68 | 45.5 |  | 62.5 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-01-29 01:00 | 0.7 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Worsening | 0.6 | 117 | 129 | 155 | 131.3333 | 0.1 | 19 | 56 | 61 | 50.6667 |  | 28.5714 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-01-29 01:00 | 0.7 | 1.3243 | 0.92704 | Reduce | 0.5 | 1.3243 | 0.66217 | H1 | 5 | Stable | 0.9 | 117 | 127 | 157 | 130.3333 | 0.4 | 11 | 47 | 66 | 44.1667 | 0 | 28.5714 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-009 | Project_021_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Config Qualification delays due to insufficient resource | Person_207 | 2016-09-11 01:00 | 2017-01-19 01:00 | 0.2 | 0.41055 | 0.082109 | Reduce | 0.1 | 0.41055 | 0.041055 | H2 | 4 | Improving | 0.9 | 97 | 129 | 145 | 126.3333 | 0.4 | 6 | 52 | 67 | 46.8333 | 0 | 50 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-008 | Project_021_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Config Qualification delays due to equipment/ hardware unreliability | Person_207 | 2016-09-11 01:00 | 2017-01-22 01:00 | 0.5 | 1.3243 | 0.66217 | Reduce | 0.4 | 1.3243 | 0.52974 | H2 | 4 | Stable | 0.9 | 117 | 138 | 149 | 136.3333 | 0.2 | 13 | 45 | 62 | 42.5 | 0 | 20 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-007 | Project_021_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Config Qualification delay due to Major PRs | Person_207 | 2016-09-11 01:00 | 2017-01-22 01:00 | 0.3 | 3.973 | 1.1919 | Reduce | 0.3 | 3.2005 | 0.96015 | H2 | 4 | Stable | 0.5 | 84 | 127 | 158 | 125 | 0.2 | 15 | 41 | 60 | 39.8333 | 19.4445 | 0 | 0 | 11.6667
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.9 | 110 | 134 | 146 | 132 | 0.1 | 16 | 47 | 63 | 44.5 |  | 50 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-005 | Project_021_Risk-005 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Opportunity to accelerate Component Approval through closer working efficiencies | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 0.1 | 0 | 0 | -- | 0.3 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -200 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-004 | Project_021_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 119 | 140 | 146 | 137.5 | 0.4 | 7 | 58 | 71 | 51.6667 |  | 80 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2017-01-04 01:00 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.9 | 85 | 125 | 148 | 122.1667 | 0.2 | 26 | 47 | 70 | 47.3333 |  | 50 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-014 | Project_021_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.6 | 83 | 137 | 151 | 130.3333 | 0.1 | 37 | 48 | 65 | 49 |  | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-013 | Project_021_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-09-11 01:00 | 2017-06-29 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 104 | 130 | 141 | 127.5 | 0.3 | 11 | 59 | 66 | 52.1667 |  | 66.6667 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-011 | Project_021_Risk-011 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-09-11 01:00 | 2017-03-21 01:00 | 0.4 | 1.1257 | 0.45028 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Improving | 0.6 | 120 | 130 | 152 | 132 | 0.3 | 16 | 45 | 74 | 45 | 7.8429 | 25 | 0 | 4.7058
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Config Qualification delays due to rig unavailability | Person_207 | 2016-09-11 01:00 | 2017-01-22 01:00 | 0.4 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Improving | 0.6 | 114 | 130 | 156 | 131.6667 | 0.4 | 5 | 43 | 69 | 41 |  | 75 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-01-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.6 | 120 | 129 | 151 | 131.1667 | 0.4 | 31 | 50 | 74 | 50.8333 |  | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.7 | 92 | 139 | 151 | 133.1667 | 0.3 | 19 | 55 | 70 | 51.5 |  | 60 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-016 | Project_021_Risk-016 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.5 | 103 | 122 | 149 | 123.3333 | 0.2 | 32 | 57 | 79 | 56.5 |  | 66.6667 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-015 | Project_021_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to technical performance | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.3 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 91 | 126 | 153 | 124.6667 | 0.4 | 10 | 42 | 66 | 40.6667 |  | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-05-21 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.8 | 86 | 128 | 160 | 126.3333 | 0.1 | 12 | 58 | 75 | 53.1667 | 7.8429 | 40 | 0 | 4.7058
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R050 | Project_021_Risk-R050 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to failure of Customer modification Telemetry | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 0.2 | 2.5604 | 0.51208 | Reduce | 0.05 | 2.0527 | 0.10264 | H2 | 4 | Improving | 0.6 | 120 | 126 | 157 | 130.1667 | 0.1 | 19 | 43 | 76 | 44.5 | 19.8277 | 75 | 0 | 11.8966
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R053 | Project_021_Risk-R053 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-02-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.6 | 99 | 129 | 152 | 127.8333 | 0.1 | 10 | 59 | 66 | 52 |  | 60 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 0.02 | 0 | 0 | Reduce | 0.01 | 0 | 0 | H3 | 3 | Stable | 0.8 | 114 | 133 | 150 | 132.6667 | 0.4 | 39 | 56 | 67 | 55 |  | 50 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R051 | Project_021_Risk-R051 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-08-21 01:00 | 2017-01-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Worsening | 0.5 | 93 | 133 | 150 | 129.1667 | 0.1 | 18 | 46 | 62 | 44 |  | 66.6667 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R052 | Project_021_Risk-R052 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.6 | 86 | 122 | 153 | 121.1667 | 0.4 | 3 | 59 | 66 | 50.8333 |  | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R055 | Project_021_Risk-R055 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to lack of personnel resource | Person_174 | 2016-11-20 01:00 | 2017-02-19 01:00 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.9 | 114 | 122 | 143 | 124.1667 | 0.3 | 24 | 43 | 71 | 44.5 |  | 66.6667 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-01-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.5 | 88 | 130 | 155 | 127.1667 | 0.4 | 31 | 56 | 76 | 55.1667 |  | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Worsening | 0.6 | 93 | 128 | 153 | 126.3333 | 0.2 | 39 | 53 | 78 | 54.8333 |  | 66.6667 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-08-06 | 2017-01-04 01:00 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.9 | 99 | 140 | 159 | 136.3333 | 0.1 | 26 | 53 | 71 | 51.5 |  | 80 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2017-01-20 01:00 | 0.3 | 1.076 | 0.32281 | Reduce | 0.05 | 1.076 | 0.053801 | H2 | 4 | Improving | 0.7 | 106 | 131 | 141 | 128.5 | 0.1 | 35 | 51 | 66 | 50.8333 | 0 | 83.3333 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-13 01:00 | 2016-12-20 01:00 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.6 | 109 | 132 | 158 | 132.5 | 0.2 | 20 | 50 | 78 | 49.6667 | 80 | 66.6667 | 0 | 48
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_515 | 2017-05-23 | 2019-01-20 23:00 | 0.5 | 12.1398 | 8.4978 | Accept | 0.5 | 12.1398 | 8.4978 | H2 | 4 | Stable | 0.5 | 82 | 123 | 142 | 119.3333 | 0.5 | 82 | 123 | 142 | 119.3333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-07-21 | 2018-01-20 01:00 | 0.1 | 0.48559 | 0.048559 | Reduce | 0.1 | 0.48559 | 0.048559 | H2 | 4 | Stable | 0.6 | 95 | 137 | 141 | 130.6667 | 0.4 | 34 | 55 | 65 | 53.1667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 19:00 | 2019-08-20 19:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 19:00 | 2019-08-20 19:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 19:00 | 2019-08-20 19:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 19:00 | 2019-08-20 19:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 19:00 | 2019-08-20 19:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R44 | Project_041_R44 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Procurement - Source Change and cost change | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 0.5 | 4.4985 | 1.3495 | Accept | 0.5 | 2.999 | 0.8997 | H1 | 5 | Worsening | 0.9 | 104 | 134 | 152 | 132 | 0.9 | 104 | 134 | 152 | 132 | 33.333 | 0 | 0 | 19.9998
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-22 01:00 | 2017-05-22 | 0.25 | 7.4225 | 1.8556 | Reduce | 0.1 | 2.0081 | 0.20081 | H3 | 3 | Stable | 0.8 | 110 | 137 | 155 | 135.5 | 0.2 | 13 | 58 | 64 | 51.5 | 72.9455 | 60 | 0 | 43.7673
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 2.6991 | 1.0796 | H2 | 4 | Stable | 0.9 | 80 | 125 | 160 | 123.3333 | 0.3 | 17 | 55 | 62 | 49.8333 | 31.8182 | 20 | 0 | 19.0909
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 01:00 | 2016-08-20 01:00 | 0.1 | 18.069 | 1.8069 | Accept | 0.1 | 11.3212 | 1.1321 | H2 | 4 | Stable | 0.5 | 93 | 137 | 151 | 132 | 0.5 | 93 | 137 | 151 | 132 | 37.3444 | 0 | 0 | 22.4066
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_575 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 5.0983 | 0.76474 | H3 | 3 | Stable | 0.6 | 103 | 140 | 156 | 136.5 | 0.3 | 15 | 53 | 65 | 48.6667 | 19.0479 | 70 | 1 | 13.5287
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-148 | Project_020_Risk-148 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs non-available items | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.3 | 14.9935 | 4.498 | Reduce | 0.3 | 14.9935 | 4.498 | H2 | 4 | Stable | 0.5 | 105 | 135 | 146 | 131.8333 | 0.3 | 31 | 49 | 66 | 48.8333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-147 | Project_020_Risk-147 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component taking longer to refurbish in country | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.6 | 6.7477 | 4.0486 | Reduce | 0.6 | 6.7477 | 4.0486 | H2 | 4 | Stable | 0.6 | 106 | 136 | 160 | 135 | 0.1 | 34 | 40 | 79 | 45.5 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-150 | Project_020_Risk-150 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Power supply Test Environment | Person_248 | 2016-10-21 01:00 | 2017-05-22 | 0.6 | 6.7477 | 4.0486 | Reduce | 0.6 | 6.7477 | 4.0486 | H2 | 4 | Worsening | 0.5 | 87 | 132 | 151 | 127.6667 | 0.1 | 18 | 42 | 69 | 42.5 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.41 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -2.5 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.61 | 0.25667 | 0.15657 | Reduce | 0.5 | 0.25667 | 0.12834 | H2 | 4 | Stable | 0.9 | 81 | 126 | 141 | 121 | 0.3 | 35 | 40 | 77 | 45.3333 | 0 | 18.0328 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2014-01-21 01:00 | 2017-11-20 01:00 | 0.4 | 1.078 | 0.43121 | Reduce | 0.4 | 1.4673 | 0.58692 | H2 | 4 | Stable | 0.5 | 119 | 140 | 158 | 139.5 | 0.1 | 37 | 41 | 63 | 44 | -36.1112 | 0 | 0 | -21.6667
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-118 | Project_029_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Acceptance Schedule is longer in duration/delayed due to unplanned events. [Hardware availability] | Person_102 | 2015-12-22 01:00 | 2017-05-23 | 0.55 | 0.56468 | 0.31057 | Reduce | 0.55 | 0.56468 | 0.31057 | H2 | 4 | Stable | 0.6 | 105 | 121 | 148 | 122.8333 | 0.3 | 14 | 42 | 70 | 42 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2017-11-19 01:00 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2017-05-23 | 0.6 | 0.89835 | 0.53901 | Transfer | 0.6 | 0.89835 | 0.53901 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2015-07-31 | 2017-05-15 | 0.35 | 0.85557 | 0.29945 | Reduce | 0.35 | 1.9208 | 0.67227 | H2 | 4 | Stable | 0.5 | 86 | 128 | 141 | 123.1667 | 0.3 | 28 | 42 | 78 | 45.6667 | -124.5001 | 0 | 0 | -74.7001
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 0.2 | 0.77001 | 0.30801 | Accept | 0.2 | 0.77001 | 0.231 | H3 | 3 | Improving | 0.6 | 80 | 121 | 144 | 118 | 0.6 | 80 | 121 | 144 | 118 | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2016-05-23 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.7 | 119 | 139 | 145 | 136.6667 | 0.4 | 27 | 56 | 72 | 53.8333 | 0 | 28.5714 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_368 | 2016-11-19 23:00 | 2017-09-18 23:00 | 0.25 | 1.54 | 0.30801 | Accept | 0.25 | 0.77001 | 0.154 | H3 | 3 | Stable | 0.9 | 99 | 128 | 160 | 128.5 | 0.9 | 99 | 128 | 160 | 128.5 | 50 | 0 | 0 | 30
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 0.1 | 27.1644 | 0.81493 | Accept | 0.1 | 12.8336 | 1.2834 | H3 | 3 | Stable | 0.5 | 95 | 139 | 142 | 132.1667 | 0.5 | 95 | 139 | 142 | 132.1667 | 52.7559 | 0 | 1 | 31.6535
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2014-07-22 | 2017-11-19 01:00 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.5 | 101 | 132 | 155 | 130.6667 | 0.3 | 3 | 46 | 67 | 42.3333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2017-10-14 01:00 | 0.41 | 6.4168 | 2.6309 | Transfer | 0.41 | 0 | 0 | H1 | 5 | Stable | [10 empty] | 100 | 0 | 0 | 60
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub-system FPGA | Person_216 | 2014-02-20 01:00 | 2017-05-22 | 0.3 | 1.54 | 0.46201 | Reduce | 0.4 | 1.5914 | 0.63655 | H2 | 4 | Stable | 0.9 | 84 | 125 | 160 | 124 | 0.3 | 25 | 41 | 78 | 44.5 | -3.3333 | -33.3333 | 0 | -2
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SystemC HW/SW | Person_199 | 2016-05-23 | 2019-10-21 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.3 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.7 | 113 | 137 | 158 | 136.5 | 0.3 | 9 | 42 | 72 | 41.5 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs [technical scope] | Person_466 | 2016-05-23 | 2019-07-21 | 0.35 | 9.505 | 3.3267 | Reduce | 0.35 | 9.505 | 3.3267 | H2 | 4 | Stable | 0.6 | 102 | 133 | 149 | 130.5 | 0.2 | 28 | 50 | 62 | 48.3333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.5 | 3.5934 | 1.7967 | H2 | 4 | Stable | 0.8 | 94 | 123 | 151 | 122.8333 | 0.1 | 5 | 49 | 60 | 43.5 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | HW - additional unplanned design effort | Person_216 | 2016-05-23 | 2019-10-21 01:00 | 0.4 | 3.3367 | 1.3347 | -- | 0.4 | 3.3367 | 1.3347 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R06 | Project_041_R06 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional PM time to support the supply chain | Person_359 | 2016-11-19 23:00 | 2017-09-18 23:00 | 0.25 | 3.9356 | 0.98391 | Accept | 0.25 | 4.2779 | 1.0695 | H3 | 3 | Stable | 0.6 | 85 | 122 | 155 | 121.3333 | 0.6 | 85 | 122 | 155 | 121.3333 | -8.6957 | 0 | 0 | -5.2174
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 0.25 | 2.5667 | 0.77001 | Accept | 0.25 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.7 | 81 | 138 | 154 | 131.1667 | 0.7 | 81 | 138 | 154 | 131.1667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design | Person_216 | 2016-05-23 | 2020-10-20 01:00 | 0.2 | 2.6951 | 0.53901 | Reduce | 0.2 | 2.6951 | 0.53901 | H3 | 3 | Stable | 0.6 | 91 | 138 | 155 | 133 | 0.2 | 2 | 46 | 72 | 43 | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK153 | Project_024_RISK153 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Processor memory/performance Issue | Person_331 | 2016-06-23 | 2017-03-22 | 0.3 | 112.3463 | 33.7039 | Reduce | 0.2 | 38.196 | 7.6392 | H2 | 4 | Stable | 0.9 | 110 | 136 | 150 | 134 | 0.2 | 29 | 52 | 64 | 50.1667 | 66.0015 | 33.3333 | 0 | 39.6009
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-111 | Project_039_Risk-111 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Maturation results inconclusive | Person_297 | 2016-02-21 01:00 | 2017-01-20 01:00 | 0.3 | 25.966 | 7.7898 | Accept | 0.3 | 22.5039 | 6.7512 | H2 | 4 | Stable | 0.5 | 80 | 129 | 151 | 124.5 | 0.5 | 80 | 129 | 151 | 124.5 | 13.3333 | 0 | 0 | 8
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-195 | Project_039_Risk-195 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Supply Chain Delays - System Comms, Component, and subsystem | Person_083 | 2016-08-21 01:00 | 2017-02-19 01:00 | 0.3 | 62.3617 | 3.1181 | Accept | 0.3 | 62.3617 | 3.1181 | H3 | 3 | Worsening | 0.5 | 99 | 134 | 145 | 130 | 0.5 | 99 | 134 | 145 | 130 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK179 | Project_024_RISK179 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Testing Required | Person_289 | 2016-12-21 01:00 | 2017-05-22 | 0.5 | 3.5054 | 1.7527 | Reduce | 0.4 | 3.5054 | 1.4022 | H2 | 4 | Stable | 0.7 | 91 | 139 | 157 | 134 | 0.4 | 7 | 44 | 76 | 43.1667 | 0 | 20 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 01:00 | 2016-11-20 01:00 | 0.25 | 11.9444 | 5.9722 | Accept | 0.1 | 11.9444 | 5.9722 | H3 | 3 | Stable | 0.8 | 106 | 127 | 142 | 126 | 0.8 | 106 | 127 | 142 | 126 | 0 | 60 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK180 | Project_024_RISK180 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | High Accelerated Life Testing (HALT) | Person_289 | 2016-12-21 01:00 | 2017-05-03 | 0.4 | 10.4903 | 4.1961 | Reduce | 0.2 | 10.4903 | 2.0981 | H2 | 4 | Stable | 0.7 | 108 | 140 | 144 | 135.3333 | 0.3 | 4 | 40 | 62 | 37.6667 | 0 | 50 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-20 01:00 | 0.25 | 35.885 | 25.4784 | Accept | 0.15 | 27.0826 | 20.3119 | H3 | 3 | Stable | 0.7 | 101 | 131 | 150 | 129.1667 | 0.7 | 101 | 131 | 150 | 129.1667 | 24.5297 | 40 | 1 | 15.9178
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK163 | Project_038_RISK163 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Additional Chamber trials | Person_531 | 2015-09-21 01:00 | 2016-11-20 01:00 | 0.25 | 30.7697 | 15.0772 | Accept | 0.25 | 24.3561 | 12.1781 | H2 | 4 | Stable | 0.9 | 85 | 134 | 154 | 129.1667 | 0.9 | 85 | 134 | 154 | 129.1667 | 20.8439 | 0 | 0 | 12.5063
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK118 | Project_037_RISK118 | Threat | Management Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Product does not deliver the inputs/depdencies required by the Project by the req'd dates | Person_330 | 2015-02-23 23:00 | 2016-06-23 | 0.4 | 1.3502 | 0.33756 | Accept | 0.4 | 1.3502 | 0.33756 | H2 | 4 | Worsening | 0.7 | 92 | 132 | 148 | 128 | 0.7 | 92 | 132 | 148 | 128 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK196 | Project_024_RISK196 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional Trials - Cost of Labour | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.3 | 0.95209 | 0.28563 | Reduce | 0.2 | 0.95209 | 0.19042 | H2 | 4 | Stable | 0.5 | 104 | 137 | 150 | 133.6667 | 0.2 | 27 | 52 | 67 | 50.3333 | 0 | 33.3333 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-194 | Project_027_Risk-194 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | The effect of specialist supplier obsolescence on complex assemblies | Person_074 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.08 | 2.0816 | 0.20816 | Accept | 0.08 | 2.0816 | 0.20816 | H3 | 3 | Stable | 0.7 | 93 | 139 | 141 | 131.6667 | 0.7 | 93 | 139 | 141 | 131.6667 | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_073 | 2016-05-23 | 2017-02-19 01:00 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.7 | 99 | 129 | 155 | 128.3333 | 0.2 | 4 | 59 | 64 | 50.6667 | 0 | 50 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_413 | 2015-11-21 01:00 | 2017-05-22 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.7 | 113 | 122 | 145 | 124.3333 | 0.3 | 39 | 57 | 72 | 56.5 | 0 | 5 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-187 | Project_027_Risk-187 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Loss of a major sub-contractor | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.12 | 9.3941 | 1.8788 | Accept | 0.12 | 9.3941 | 1.8788 | H3 | 3 | Stable | 0.6 | 114 | 127 | 160 | 130.3333 | 0.6 | 114 | 127 | 160 | 130.3333 | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-196 | Project_027_Risk-196 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Aging equipment resulting in increasing failure rates | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 1.8788 | 0.18788 | Accept | 0.1 | 1.8788 | 0.18788 | H3 | 3 | Stable | 0.9 | 105 | 126 | 142 | 125.1667 | 0.9 | 105 | 126 | 142 | 125.1667 | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-185 | Project_027_Risk-185 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier manufacturing issues | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.6 | 29.4599 | 8.838 | Accept | 0.05 | 18.7882 | 5.6365 | H3 | 3 | Stable | 0.6 | 114 | 133 | 160 | 134.3333 | 0.6 | 114 | 133 | 160 | 134.3333 | 36.2245 | 91.6667 | 1 | 24.4847
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-186 | Project_027_Risk-186 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Potential for composite suppliers going out of business | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 1.1273 | 0.22546 | Accept | 0.1 | 1.1273 | 0.22546 | H3 | 3 | Stable | 0.8 | 81 | 130 | 150 | 125.1667 | 0.8 | 81 | 130 | 150 | 125.1667 | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Governance and Export Rules | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 0.93941 | 0.23485 | Transfer | 0.25 | 0.93941 | 0.23485 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R017 | Project_021_Risk-R017 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Effort to address Hexavalent Chromium issue is unknown at time of baseline | Person_470 | 2016-02-06 01:00 | 2016-12-20 01:00 | 0.7 | 2.1606 | 0.43213 | Accept | 0.7 | 2.1606 | 0.43213 | H1 | 5 | Stable | 0.7 | 87 | 125 | 156 | 123.8333 | 0.7 | 87 | 125 | 156 | 123.8333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-149 | Project_020_Risk-149 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs to be returned to UK | Person_703 | 2016-12-21 01:00 | 2017-11-19 01:00 | 0.2 | 7.3646 | 3.6823 | Accept | 0.2 | 7.3646 | 3.6823 | H2 | 4 | Stable | 0.6 | 92 | 138 | 160 | 134 | 0.6 | 92 | 138 | 160 | 134 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2016-05-23 | 2019-07-21 | 0.4 | 0.55886 | 0.27943 | Accept | 0.3 | 5.5886 | 1.1177 | H2 | 4 | Stable | 0.8 | 117 | 126 | 144 | 127.5 | 0.8 | 117 | 126 | 144 | 127.5 | -900 | 25 | 0 | -540
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2019-10-14 01:00 | 0.2 | 2.7943 | 0.55886 | Accept | 0.2 | 2.7943 | 0.55886 | H3 | 3 | Stable | 0.7 | 85 | 125 | 144 | 121.5 | 0.7 | 85 | 125 | 144 | 121.5 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-09 | Project_022_RISK-09 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance - Issues arise | Person_393 | 2012-04-22 | 2016-11-19 01:00 | 0.7 | 24.8225 | 17.3758 | Reduce | 0.48 | 8.951 | 4.2965 | H2 | 4 | Stable | 0.9 | 112 | 121 | 153 | 124.8333 | 0.1 | 27 | 58 | 76 | 55.8333 | 63.94 | 31.4286 | 0 | 38.364
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-08 | Project_022_RISK-08 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Poor performance during acceptance phases | Person_248 | 2012-05-23 | 2016-11-19 01:00 | 0.65 | 5.6817 | 3.6931 | Reduce | 0.512 | 5.6817 | 2.909 | H1 | 5 | Stable | 0.8 | 99 | 132 | 159 | 131 | 0.4 | 2 | 40 | 78 | 40 | 0 | 21.2308 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.35 | 2.9061 | 1.0171 | H2 | 4 | Worsening | 0.5 | 112 | 129 | 154 | 130.3333 | 0.3 | 27 | 53 | 79 | 53 | 21.0126 | 56.25 | 0 | 12.6076
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2015-07-22 | 2019-07-21 | 0.3 | 2.3975 | 2.3975 | Accept | 0.2 | 0.66364 | 0.66364 | H3 | 3 | Stable | 0.9 | 80 | 130 | 156 | 126 | 0.9 | 80 | 130 | 156 | 126 | 72.3193 | 33.3333 | 1 | 44.3916
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-22 | Project_022_RISK-22 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Setting to work Issues - monitor may require changing | Person_393 | 2014-10-22 01:00 | 2016-11-19 01:00 | 0.6 | 11.6428 | 6.9857 | Reduce | 0.2 | 12.2515 | 2.4503 | H3 | 3 | Worsening | 0.6 | 117 | 121 | 141 | 123.6667 | 0.3 | 28 | 50 | 61 | 48.1667 | -5.228 | 66.6667 | 0 | -3.1368
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 3.8666 | 1.5853 | Accept | 0.1 | 1.3288 | 0.5448 | H2 | 4 | Stable | 0.5 | 120 | 137 | 158 | 137.6667 | 0.5 | 120 | 137 | 158 | 137.6667 | 65.6338 | -233.3333 | 0 | 39.3803
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 1.0687 | 0.85496 | H2 | 4 | Stable | [10 empty] | 68.1283 | 0 | 0 | 40.877
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2016-11-17 01:00 | 0.85 | 25.2325 | 21.4476 | Avoid | 0.08 | 20.8758 | 1.6701 | H2 | 4 | Improving | [10 empty] | 17.2662 | 90.5882 | 0 | 10.3597
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-58 | Project_022_RISK-58 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Handbook Update | Person_248 | 2012-04-19 | 2016-11-19 01:00 | 0.5 | 2.2354 | 1.1177 | Reduce | 0.5 | 2.2354 | 1.1177 | H3 | 3 | Stable | 0.7 | 88 | 129 | 151 | 125.8333 | 0.1 | 15 | 53 | 63 | 48.3333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-018 | Project_023_Risk-018 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Project Management | Person_703 | 2013-05-19 | 2017-05-22 | 0.8 | 0.10892 | 0.087134 | Exploit | 0.8 | 0.13615 | 0.10892 | H2 | 4 | Stable | [10 empty] | -25 | 0 | 0 | -15
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 5.9904 | 1.4976 | Accept | 0.25 | 0 | 0 | H2 | 4 | Stable | 0.6 | 105 | 140 | 143 | 134.6667 | 0.6 | 105 | 140 | 143 | 134.6667 | 100 | 0 | 0 | 60
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of Batch 2 Re-Design | Person_199 | 2016-05-23 | 2019-10-21 01:00 | 0.3 | 5.4459 | 1.6338 | Accept | 0.3 | 0.18151 | 0.054453 | H2 | 4 | Stable | 0.8 | 101 | 135 | 144 | 130.8333 | 0.8 | 101 | 135 | 144 | 130.8333 | 96.667 | 0 | 0 | 58.0002
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-019 | Project_023_Risk-019 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software | Person_253 | 2013-05-19 | 2017-05-22 | 0.8 | 0.38121 | 0.30497 | Exploit | 0.8 | 0.47651 | 0.38121 | H2 | 4 | Stable | [10 empty] | -25 | 0 | 0 | -15
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2016-11-17 01:00 | 0.7 | 24.1887 | 16.9321 | Reduce | 0.25 | 4.3567 | 1.0892 | H2 | 4 | Stable | 0.8 | 82 | 140 | 152 | 132.3333 | 0.2 | 25 | 58 | 70 | 54.5 | 81.9887 | 64.2857 | 0 | 49.1932
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 01:00 | 2016-05-21 | 0.5 | 4.3921 | 2.196 | Reduce | 0.3 | 4.3921 | 1.3176 | H1 | 5 | Stable | 0.7 | 99 | 131 | 153 | 129.3333 | 0.2 | 35 | 41 | 66 | 44.1667 | 0 | 40 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-02-20 01:00 | 2018-08-21 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.8 | 101 | 122 | 157 | 124.3333 | 0.3 | 27 | 40 | 61 | 41.3333 |  | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Pick up and Drop off of Software Resource | Person_230 | 2017-04-21 | 2018-02-19 01:00 | 0.4 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment environmental failure | Person_289 | 2016-05-23 | 2017-08-18 01:00 | 0.3 | 0.034059 | 0.0034059 | Accept | 0.3 | 0.034059 | 0.0034059 | H1 | 5 | Improving | 0.6 | 111 | 133 | 142 | 130.8333 | 0.6 | 111 | 133 | 142 | 130.8333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Retained systems re-design or modification | Person_289 | 2016-08-20 01:00 | 2017-02-19 01:00 | 0.05 | 0.35539 | 0.17769 | Accept | 0.05 | 0.35539 | 0.088847 | H2 | 4 | Improving | 0.7 | 109 | 130 | 153 | 130.3333 | 0.7 | 109 | 130 | 153 | 130.3333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk005 | Project_002_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2014-06-14 | 2016-08-08 | 0.3 | 0.035539 | 0.010662 | Avoid | 0.3 | 0.035539 | 0.010662 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk008 | Project_002_Risk008 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2014-08-20 | 2016-08-07 | 0.1 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | -100 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk009 | Project_002_Risk009 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2014-06-14 | 2016-08-07 | 0.1 | 0.01925 | 0.001925 | Avoid | 0.1 | 0.01925 | 0.001925 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | RISK012 | Project_002_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Resourcing Suitably Qualified and experienced staff availability | Person_650 | 2015-11-21 | 2016-08-07 | 0.2 | 0.05627 | 0.011254 | Reduce | 0.2 | 0.05627 | 0.011254 | H3 | 3 | Stable | 0.7 | 101 | 130 | 152 | 128.8333 | 0.1 | 7 | 59 | 62 | 50.8333 | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk004 | Project_002_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability of Test Equipment | Person_133 | 2014-03-26 | 2016-08-08 | 0.2 | 0.081443 | 0.016289 | Avoid | 0.2 | 0.081443 | 0.016289 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk006 | Project_002_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Additional Pressure Testing | Person_650 | 2014-06-14 | 2016-08-08 | 0.25 | 0.035539 | 0.0088847 | Avoid | 0.25 | 0.035539 | 0.0088847 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk011 | Project_002_Risk011 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Testing | Person_175 | 2014-06-29 | 2016-08-07 | 0.41 | 0.071669 | 0.029384 | Reduce | 0.1 | 0.0088847 | 0.00088847 | H3 | 3 | Stable | 0.5 | 91 | 124 | 151 | 123 | 0.4 | 12 | 43 | 68 | 42 | 87.6032 | 75.6098 | 1 | 54.8302
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Mission System not compatible with platform systems | Person_289 | 2016-07-21 | 2017-02-19 01:00 | 0.1 | 3.9852 | 0.9963 | Accept | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 85 | 136 | 143 | 128.6667 | 0.8 | 85 | 136 | 143 | 128.6667 | 100 | 0 | 0 | 60
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-034 | Project_005_Risk-034 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project delay causes cost impact to project | Person_470 | 2011-12-02 01:00 | 2016-10-30 01:00 | 0.5 | 16.3745 | 8.1873 | Reduce | 0.1 | 2.5077 | 0.25077 | H3 | 3 | Stable | 0.7 | 119 | 133 | 149 | 133.3333 | 0.2 | 36 | 58 | 69 | 56.1667 | 84.6854 | 80 | 1 | 53.2113
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Qual failure | Person_289 | 2016-06-22 | 2017-08-12 | 0.4 | 1.6266 | 0.8133 | Accept | 0.4 | 1.6266 | 0.08133 | H1 | 5 | Improving | 0.7 | 87 | 137 | 158 | 132.1667 | 0.7 | 87 | 137 | 158 | 132.1667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Additional minor point releases | Person_073 | 2016-05-23 | 2017-08-20 01:00 | 0.5 | 6.3266 | 1.898 | Accept | 0.5 | 6.3266 | 1.297 | H1 | 5 | Stable | 0.8 | 89 | 137 | 157 | 132.3333 | 0.8 | 89 | 137 | 157 | 132.3333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Digital Video Chainredesign | Person_289 | 2016-06-22 | 2018-04-11 | 0.71 | 3.2155 | 0.96464 | Accept | 0.75 | 3.2155 | 0.96464 | H1 | 5 | Worsening | 0.7 | 98 | 125 | 145 | 123.8333 | 0.7 | 98 | 125 | 145 | 123.8333 | 0 | -5.6338 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK189 | Project_024_RISK189 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment integration - Audio and Video recording | Person_289 | 2016-08-20 01:00 | 2017-01-21 01:00 | 0.49 | 1.2271 | 0.50311 | Accept | 0.5 | 1.2271 | 0.50311 | H1 | 5 | Worsening | 0.6 | 112 | 123 | 159 | 127.1667 | 0.6 | 112 | 123 | 159 | 127.1667 | 0 | -2.0408 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK380 | Project_035_RISK380 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Data Throttling Algorithm | Person_699 | 2016-01-03 01:00 | 2016-11-20 01:00 | 0.2 | 2.6071 | 0.52143 | Reduce | 0.2 | 2.6071 | 0.52143 | H3 | 3 | Stable | 0.9 | 114 | 124 | 160 | 128.3333 | 0.1 | 33 | 49 | 63 | 48.6667 | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK394 | Project_035_RISK394 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Provision of supplier evidence | Person_631 | 2016-02-21 01:00 | 2016-10-21 01:00 | 0.5 | 2.4768 | 1.2384 | -- | 0.5 | 1.2167 | 0.60833 | H2 | 4 | Improving | [10 empty] | 50.8773 | 0 | 0 | 30.5264
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK290 | Project_035_RISK290 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Face-to-Face Arbitration | Person_699 | 2015-01-22 01:00 | 2017-01-21 01:00 | 0.5 | 1.2445 | 0.62224 | -- | 0.2 | 2.303 | 0.46059 | H3 | 3 | Worsening | [10 empty] | -85.0557 | 60 | 0 | -51.0334
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK395 | Project_035_RISK395 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Test area Site Availability | Person_691 | 2016-05-23 | 2016-11-19 01:00 | 0.5 | 3.0417 | 1.5208 | -- | 0.5 | 3.0417 | 1.5208 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK114 | Project_035_RISK114 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Qualification Facilities Availability. | Person_570 | 2015-09-21 01:00 | 2016-08-20 01:00 | 0.61 | 1.2358 | 0.75383 | Reduce | 0.3 | 1.2358 | 0.37073 | H2 | 4 | Stable | 0.7 | 87 | 138 | 150 | 131.5 | 0.2 | 11 | 41 | 60 | 39.1667 | 0 | 50.8197 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_289 | 2016-05-23 | 2017-08-20 01:00 | 0.4 | 3.1633 | 0.63267 | Accept | 0.4 | 3.1633 | 0.63267 | H1 | 5 | Stable | 0.6 | 95 | 127 | 157 | 126.6667 | 0.6 | 95 | 127 | 157 | 126.6667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.7 | 115 | 133 | 152 | 133.1667 | 0.1 | 6 | 54 | 69 | 48.5 | 25.8065 | 20 | 0 | 15.4839
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK024 | Project_012_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component Repair & test costs | Person_359 | 2015-04-04 | 2016-04-12 | 0.7 | 0.84985 | 0.5949 | -- | 0.18 | 0.84985 | 0.15297 | H2 | 4 | Improving | [10 empty] | 0 | 74.2857 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK194 | Project_024_RISK194 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Performance Models require additional effort | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.25 | 8.8098 | 3.0834 | Accept | 0.25 | 8.8098 | 1.762 | H2 | 4 | Stable | 0.9 | 114 | 136 | 151 | 134.8333 | 0.9 | 114 | 136 | 151 | 134.8333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK195 | Project_024_RISK195 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Perfomance Validation document not accepted | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.1 | 0.40661 | 0.16264 | Accept | 0.1 | 0.40661 | 0.081321 | H2 | 4 | Stable | 0.9 | 115 | 123 | 146 | 125.5 | 0.9 | 115 | 123 | 146 | 125.5 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Furnished Equipmnet Condition | Person_371 | 2015-04-27 | 2017-08-19 01:00 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.7 | 92 | 136 | 148 | 130.6667 | 0.3 | 32 | 50 | 65 | 49.5 |  | 62.5 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK197 | Project_024_RISK197 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Fitness for purpose | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.2 | 0.81199 | 0.081199 | Accept | 0.2 | 0.81199 | 0.0406 | H2 | 4 | Improving | 0.6 | 87 | 131 | 142 | 125.5 | 0.6 | 87 | 131 | 142 | 125.5 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-022 | Project_028_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Accrediation Scope | Person_371 | 2014-01-21 01:00 | 2016-12-20 01:00 | 0.5 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 20 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Suppliers | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 12.1982 | 0.60991 | Accept | 0.15 | 12.1982 | 0.60991 | H2 | 4 | Stable | 0.5 | 92 | 131 | 154 | 128.3333 | 0.5 | 92 | 131 | 154 | 128.3333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 0 | 0 | Accept | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.8 | 84 | 130 | 150 | 125.6667 | 0.8 | 84 | 130 | 150 | 125.6667 |  | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Local customer Engineers in country | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 0 | 0 | Accept | 0.1 | 0 | 0 | H2 | 4 | Stable | 0.9 | 108 | 139 | 144 | 134.6667 | 0.9 | 108 | 139 | 144 | 134.6667 |  | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2017-04-21 | 0.2 | 0.90951 | 0.1819 | Reduce | 0.2 | 0.90951 | 0.1819 | H3 | 3 | Stable | 0.7 | 114 | 137 | 158 | 136.6667 | 0.1 | 25 | 52 | 65 | 49.6667 | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence | Person_455 | 2016-05-23 | 2020-05-23 | 0.3 | 1.4532 | 0.072661 | Accept | 0.3 | 1.4532 | 0.072661 | H2 | 4 | Stable | 0.5 | 93 | 131 | 147 | 127.3333 | 0.5 | 93 | 131 | 147 | 127.3333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2017-01-20 01:00 | 0.3 | 5.4553 | 1.6366 | Reduce | 0.15 | 5.252 | 0.7878 | H2 | 4 | Stable | 0.9 | 90 | 137 | 155 | 132.1667 | 0.2 | 36 | 43 | 71 | 46.5 | 3.7267 | 50 | 0 | 2.236
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-058 | Project_028_Risk-058 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | INterface Card | Person_253 | 2015-07-22 | 2016-12-18 01:00 | 0.2 | 2.8408 | 0.56817 | Reduce | 0.1 | 1.9314 | 0.19314 | H3 | 3 | Stable | 0.7 | 96 | 127 | 154 | 126.3333 | 0.2 | 27 | 52 | 72 | 51.1667 | 32.0134 | 50 | 1 | 20.708
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Consumables | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 1.3215 | 0.39644 | Accept | 0.2 | 1.3215 | 0.39644 | H2 | 4 | Stable | 0.5 | 118 | 128 | 148 | 129.6667 | 0.5 | 118 | 128 | 148 | 129.6667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 7. Finance | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 12.1982 | 2.4396 | Accept | 0.2 | 10.8428 | 2.1686 | H2 | 4 | Stable | 0.8 | 98 | 125 | 153 | 125.1667 | 0.8 | 98 | 125 | 153 | 125.1667 | 11.1111 | 0 | 0 | 6.6667
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 4.4727 | 0.44727 | Accept | 0.15 | 4.4727 | 0.22363 | H2 | 4 | Stable | 0.9 | 113 | 140 | 146 | 136.5 | 0.9 | 113 | 140 | 146 | 136.5 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 20.3303 | 7.1156 | Accept | 0.2 | 18.975 | 3.795 | H2 | 4 | Stable | 0.7 | 93 | 127 | 145 | 124.3333 | 0.7 | 93 | 127 | 145 | 124.3333 | 6.6667 | 0 | 0 | 4
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Cable and connectors | Person_050 | 2015-11-21 01:00 | 2017-08-09 | 0.45 | 0.41338 | 0.18602 | Reduce | 0.2 | 0.41338 | 0.082677 | H2 | 4 | Stable | 0.5 | 99 | 129 | 154 | 128.1667 | 0.4 | 16 | 44 | 69 | 43.5 | 0 | 55.5556 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Platform Acceptance | Person_500 | 2015-11-21 01:00 | 2017-04-21 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.2 | 4.2355 | 0.8471 | H3 | 3 | Stable | 0.8 | 93 | 136 | 155 | 132 | 0.1 | 27 | 58 | 71 | 55 | 0 | 42.8571 | 1 | 1.2857
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport Routes | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 13.3529 | 6.6765 | Accept | 0.15 | 13.3529 | 6.6765 | H2 | 4 | Stable | 0.6 | 120 | 127 | 152 | 130 | 0.6 | 120 | 127 | 152 | 130 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 0.5 | 9.2728 | 4.6364 | Reduce | 0.3 | 9.2728 | 2.7819 | H2 | 4 | Stable | 0.7 | 109 | 124 | 150 | 125.8333 | 0.2 | 35 | 46 | 72 | 48.5 | 0 | 40 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 | 2017-08-20 | 0.3 | 8.7814 | 2.6344 | Reduce | 0.15 | 8.7832 | 1.3175 | H3 | 3 | Stable | 0.9 | 81 | 130 | 155 | 126 | 0.3 | 28 | 44 | 72 | 46 | -0.021119 | 50 | 0 | -0.012672
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Internal Quality Issues | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 108.3186 | 32.4956 | Accept | 0.2 | 108.3186 | 32.4956 | H2 | 4 | Stable | 0.8 | 83 | 122 | 153 | 120.6667 | 0.8 | 83 | 122 | 153 | 120.6667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Delay of processing | Person_306 | 2016-01-13 | 2019-08-21 | 0.15 | 26.3497 | 3.9525 | Reduce | 0.15 | 13.1767 | 1.9765 | H3 | 3 | Stable | 0.9 | 112 | 129 | 150 | 129.6667 | 0.2 | 32 | 55 | 61 | 52.1667 | 49.993 | 0 | 1 | 29.9958
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk017 | Project_042_Risk017 | Threat | Financial Contingency | Open | H2 | 4 | 6. Contractual/Legal | Liquidated Damages | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 12.0547 | 2.4109 | Accept | 0.4 | 12.0547 | 2.4109 | H2 | 4 | Stable | 0.9 | 86 | 127 | 142 | 122.6667 | 0.9 | 86 | 127 | 142 | 122.6667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Repairs | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 17.0765 | 1.7076 | Accept | 0.25 | 17.0765 | 1.7076 | H2 | 4 | Stable | 0.7 | 104 | 133 | 145 | 130.1667 | 0.7 | 104 | 133 | 145 | 130.1667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk016 | Project_042_Risk016 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport/Delivery Speed | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 0.67512 | 0.13502 | Accept | 0.1 | 0.67512 | 0.13502 | H2 | 4 | Stable | 0.6 | 113 | 121 | 146 | 123.8333 | 0.6 | 113 | 121 | 146 | 123.8333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.9 | 83 | 127 | 151 | 123.6667 | 0.2 | 28 | 42 | 73 | 44.8333 | 0 | 60 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Country Stability | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 50.7895 | 40.6316 | Accept | 0.4 | 50.7895 | 40.6316 | H2 | 4 | Stable | 0.7 | 108 | 121 | 142 | 122.3333 | 0.7 | 108 | 121 | 142 | 122.3333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK201 | Project_024_RISK201 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Indication mode failure | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.25 | 1.6835 | 0.42087 | Reduce | 0.2 | 1.6835 | 0.33669 | H3 | 3 | Stable | 0.5 | 103 | 132 | 159 | 131.6667 | 0.4 | 11 | 51 | 78 | 48.8333 | 0 | 20 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 1.3502 | 0.54009 | Accept | 0.1 | 1.3502 | 0.54009 | H2 | 4 | Stable | 0.9 | 112 | 125 | 155 | 127.8333 | 0.9 | 112 | 125 | 155 | 127.8333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 1.9128 | 0.19128 | Accept | 0.2 | 1.9128 | 0.19128 | H2 | 4 | Stable | 0.6 | 118 | 130 | 147 | 130.8333 | 0.6 | 118 | 130 | 147 | 130.8333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 0.5 | 22.8501 | 6.855 | Accept | 0.5 | 22.8501 | 6.855 | H2 | 4 | Stable | 0.5 | 97 | 126 | 154 | 125.8333 | 0.5 | 97 | 126 | 154 | 125.8333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK286 | Project_024_RISK286 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Requirement sell off more difficult than expected | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.5 | 10.1787 | 5.0893 | Reduce | 0.4 | 10.1787 | 4.0715 | H1 | 5 | Worsening | 0.9 | 101 | 125 | 151 | 125.3333 | 0.3 | 35 | 55 | 78 | 55.5 | 0 | 20 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK288 | Project_024_RISK288 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Unplanned obsolescence and/or repairs to rig assets. | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.6 | 5.8424 | 3.5054 | Reduce | 0.6 | 5.8424 | 3.5054 | H1 | 5 | Stable | 0.6 | 80 | 123 | 145 | 119.5 | 0.3 | 28 | 52 | 65 | 50.1667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 0.5 | 1.3502 | 0.47258 | Accept | 0.5 | 1.3502 | 0.47258 | H2 | 4 | Stable | 0.8 | 96 | 131 | 156 | 129.3333 | 0.8 | 96 | 131 | 156 | 129.3333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 19.9938 | 5.9981 | Accept | 0.5 | 19.9938 | 5.9981 | H2 | 4 | Stable | 0.6 | 89 | 124 | 153 | 123 | 0.6 | 89 | 124 | 153 | 123 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.4 | 25.4467 | 10.1787 | Reduce | 0.3 | 10.9057 | 3.2717 | H1 | 5 | Stable | 0.6 | 114 | 137 | 155 | 136.1667 | 0.4 | 18 | 42 | 64 | 41.6667 | 57.1429 | 25 | 0 | 34.2857
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-47 | Project_022_RISK-47 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Software Issues | Person_245 | 2012-04-19 | 2016-11-19 01:00 | 0.5 | 19.4745 | 5.8424 | Accept | 0.2 | 19.4745 | 5.8424 | H3 | 3 | Stable | 0.9 | 110 | 133 | 158 | 133.3333 | 0.9 | 110 | 133 | 158 | 133.3333 | 0 | 60 | 1 | 1.8
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-51 | Project_022_RISK-51 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Environmental Conditions | Person_393 | 2012-04-19 | 2016-11-19 01:00 | 0.2 | 0.35487 | 0.035487 | Accept | 0.2 | 0.35487 | 0.035487 | H3 | 3 | Stable | 0.7 | 97 | 126 | 146 | 124.5 | 0.7 | 97 | 126 | 146 | 124.5 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2016-12-08 01:00 | 0.41 | 2.7146 | 2.7146 | Accept | 0.41 | 2.7146 | 2.7146 | H2 | 4 | Stable | 0.6 | 84 | 124 | 159 | 123.1667 | 0.6 | 84 | 124 | 159 | 123.1667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-015 | Project_023_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Illness | Person_371 | 2015-04-09 | 2016-12-11 01:00 | 0.25 | 2.5966 | 0.51932 | Accept | 0.25 | 2.5966 | 0.51932 | H2 | 4 | Stable | 0.8 | 97 | 122 | 141 | 121 | 0.8 | 97 | 122 | 141 | 121 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-016 | Project_023_Risk-016 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Damage to equipment (Unable to replace due to obsolescence) | Person_703 | 2015-10-22 01:00 | 2016-06-22 | 0.3 | 30.562 | 24.4496 | Accept | 0.3 | 30.562 | 24.4496 | H2 | 4 | Stable | 0.5 | 98 | 132 | 154 | 130 | 0.5 | 98 | 132 | 154 | 130 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK290 | Project_024_RISK290 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance Strategy decisions being made too late | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.5 | 12.0742 | 6.0371 | Avoid | 0.1 | 12.0742 | 1.2074 | H3 | 3 | Stable | [10 empty] | 0 | 80 | 1 | 2.4
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK213 | Project_024_RISK213 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Rigs requireaccreditation as "Special to Type" Test equipment | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.3 | 33.7558 | 10.1267 | Reduce | 0.2 | 23.3694 | 4.6739 | H2 | 4 | Stable | 0.8 | 101 | 128 | 143 | 126 | 0.2 | 13 | 47 | 64 | 44.1667 | 30.7692 | 33.3333 | 0 | 18.4615
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk010 | Project_002_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability | Person_357 | 2014-06-14 | 2016-08-07 | 0.1 | 68.1262 | 6.8126 | Accept | 0.1 | 68.1262 | 6.8126 | H3 | 3 | Worsening | 0.6 | 108 | 136 | 149 | 133.5 | 0.6 | 108 | 136 | 149 | 133.5 | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk002 | Project_002_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Transducer Element Failures | Person_650 | 2014-06-04 | 2016-08-07 | 0.5 | 90.8811 | 13.6322 | Accept | 0.25 | 90.8811 | 13.6322 | H2 | 4 | Worsening | 0.7 | 114 | 122 | 147 | 124.8333 | 0.7 | 114 | 122 | 147 | 124.8333 | 0 | 50 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-010 | Project_005_Risk-010 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Risk that required resources (people and rigs) will not be available as required due to other projects/bids (Customer & Internal) | Person_470 | 2011-11-11 01:00 | 2016-11-18 01:00 | 0.25 | 8.5688 | 4.2844 | Accept | 0.1 | 8.5688 | 4.2844 | H3 | 3 | Stable | 0.8 | 98 | 121 | 157 | 123.1667 | 0.8 | 98 | 121 | 157 | 123.1667 | 0 | 60 | 1 | 1.8
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-060 | Project_005_Risk-060 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Technical Acceptance may be more difficult than anticipated | Person_470 | 2014-06-11 | 2016-10-18 01:00 | 0.5 | 4.847 | 1.4541 | Accept | 0.05 | 4.847 | 1.4541 | H3 | 3 | Stable | 0.5 | 107 | 126 | 144 | 125.8333 | 0.5 | 107 | 126 | 144 | 125.8333 | 0 | 90 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK219 | Project_024_RISK219 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | STTE additional work | Person_289 | 2016-09-20 01:00 | 2017-07-21 | 0.5 | 15.0863 | 7.5431 | Reduce | 0.5 | 15.0863 | 7.5431 | H1 | 5 | Worsening | 0.7 | 102 | 121 | 153 | 123.1667 | 0.4 | 38 | 44 | 67 | 46.8333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK218 | Project_024_RISK218 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | System issues general | Person_289 | 2016-08-21 01:00 | 2017-05-14 | 0.4 | 90.8811 | 36.3524 | Reduce | 0.3 | 39.3904 | 11.8171 | H1 | 5 | Stable | 0.7 | 103 | 131 | 148 | 129.1667 | 0.3 | 17 | 41 | 63 | 40.6667 | 56.6571 | 25 | 0 | 33.9943
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK313 | Project_035_RISK313 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Deployed Performance inadequate | Person_303 | 2015-05-24 | 2016-10-21 01:00 | 0.3 | 9.8671 | 1.9734 | Accept | 0.205 | 9.8671 | 1.9734 | H2 | 4 | Improving | 0.7 | 83 | 130 | 141 | 124 | 0.7 | 83 | 130 | 141 | 124 | 0 | 31.6667 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK308 | Project_035_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Facility performance during Live trials | Person_303 | 2015-05-24 | 2016-10-21 01:00 | 0.3 | 15.5796 | 6.2318 | Accept | 0.3 | 15.5796 | 6.2318 | H2 | 4 | Improving | 0.8 | 100 | 136 | 160 | 134 | 0.8 | 100 | 136 | 160 | 134 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK304 | Project_035_RISK304 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change at Elevation | Person_425 | 2016-09-20 01:00 | 2017-01-20 01:00 | 0.41 | 12.983 | 2.5966 | Accept | 0.41 | 12.983 | 2.5966 | H2 | 4 | Stable | 0.6 | 110 | 140 | 150 | 136.6667 | 0.6 | 110 | 140 | 150 | 136.6667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK312 | Project_035_RISK312 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Audio Performance inadequate | Person_303 | 2015-06-24 | 2016-10-21 01:00 | 0.2 | 11.1654 | 2.2331 | Accept | 0.2 | 11.1654 | 2.2331 | H3 | 3 | Stable | 0.9 | 107 | 133 | 143 | 130.3333 | 0.9 | 107 | 133 | 143 | 130.3333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_542 | 2015-01-22 01:00 | 2017-08-20 01:00 | 0.35 | 1.3502 | 0.27005 | Accept | 0.2 | 1.3502 | 0.27005 | H2 | 4 | Stable | 0.7 | 89 | 128 | 144 | 124.1667 | 0.7 | 89 | 128 | 144 | 124.1667 | 0 | 42.8571 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_070 | 2016-06-23 | 2017-04-21 | 0.4 | 1.3502 | 0.40507 | Accept | 0.2 | 1.3502 | 0.40507 | H2 | 4 | Stable | 0.8 | 93 | 122 | 145 | 121 | 0.8 | 93 | 122 | 145 | 121 | 0 | 50 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.2 | 20.8767 | 4.1753 | H2 | 4 | Stable | 0.6 | 102 | 130 | 151 | 128.8333 | 0.4 | 1 | 42 | 64 | 38.8333 | 50 | 50 | 0 | 30
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 01:00 | 0.1 | 29.1079 | 19.2112 | Accept | 0.05 | 29.1079 | 14.845 | H3 | 3 | Stable | 0.5 | 83 | 138 | 146 | 130.1667 | 0.5 | 83 | 138 | 146 | 130.1667 | 0 | 50 | 1 | 1.5
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-015 | Project_028_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | STANDARDS Compliance | Person_499 | 2015-10-22 01:00 | 2016-11-19 01:00 | 0.05 | 9.8671 | 0.98671 | Accept | 0.05 | 9.8671 | 0.98671 | H3 | 3 | Stable | 0.7 | 94 | 125 | 146 | 123.3333 | 0.7 | 94 | 125 | 146 | 123.3333 | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 0.49667 | 93.5036 | 46.4402 | Reduce | 0.30422 | 65.224 | 19.8425 | H1 | 5 | Worsening | 0.6 | 100 | 133 | 153 | 130.8333 | 0.4 | 4 | 48 | 64 | 43.3333 | 30.2444 | 38.7477 | 0 | 18.1466
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-20 23:00 | 2016-08-20 23:00 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.7 | 86 | 138 | 148 | 131 | 0.1 | 31 | 46 | 79 | 49 | 0 | 16.6667 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-049 | Project_028_Risk-049 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | More integration required | Person_542 | 2015-04-08 | 2016-12-18 01:00 | 0.05 | 7.689 | 2.6911 | Accept | 0.05 | 7.689 | 2.6911 | H3 | 3 | Stable | 0.9 | 83 | 136 | 151 | 129.6667 | 0.9 | 83 | 136 | 151 | 129.6667 | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence and missing info | Person_727 | 2015-11-25 01:00 | 2016-11-19 01:00 | 0.3 | 5.4336 | 1.3584 | Accept | 0.3 | 5.4336 | 1.3584 | H2 | 4 | Stable | 0.7 | 104 | 133 | 160 | 132.6667 | 0.7 | 104 | 133 | 160 | 132.6667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 01:00 | 2017-03-22 | 0.2 | 5.126 | 2.563 | Accept | 0.2 | 5.126 | 2.563 | H2 | 4 | Stable | 0.8 | 96 | 125 | 158 | 125.6667 | 0.8 | 96 | 125 | 158 | 125.6667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-002 | Project_028_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Record / Replay feature | Person_499 | 2014-03-23 | 2016-12-18 01:00 | 0.1 | 12.815 | 2.563 | Accept | 0.05 | 12.815 | 2.563 | H2 | 4 | Stable | 0.5 | 106 | 123 | 141 | 123.1667 | 0.5 | 106 | 123 | 141 | 123.1667 | 0 | 50 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.9 | 82 | 123 | 142 | 119.3333 | 0.1 | 18 | 41 | 74 | 42.6667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | EMC Testing | Person_070 | 2016-04-22 | 2017-02-19 01:00 | 0.35 | 0 | 0 | Accept | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.6 | 95 | 123 | 145 | 122 | 0.6 | 95 | 123 | 145 | 122 |  | 42.8571 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 0.5 | 0 | 0 | Accept | 0.5 | 0 | 0 | H2 | 4 | Improving | 0.7 | 82 | 139 | 155 | 132.1667 | 0.7 | 82 | 139 | 155 | 132.1667 |  | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 19:00 | 2019-08-20 19:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.8 | 96 | 124 | 146 | 123 | 0.2 | 31 | 49 | 75 | 50.3333 | 83.3333 | 88.8889 | 1 | 52.6667
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.7 | 96 | 134 | 155 | 131.1667 | 0.2 | 23 | 59 | 64 | 53.8333 | 72 | 0 | 0 | 43.2
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.9 | 88 | 125 | 143 | 121.8333 | 0.2 | 3 | 56 | 70 | 49.5 | 47.7391 | 0 | 0 | 28.6435
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 19:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.8 | 86 | 137 | 146 | 130 | 0.4 | 27 | 41 | 71 | 43.6667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.5 | 105 | 125 | 141 | 124.3333 | 0.1 | 5 | 43 | 71 | 41.3333 | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 | 0.3 | 16.3745 | 8.1873 | Accept | 0.3 | 2.5077 | 0.12538 | H2 | 4 | Stable | 0.6 | 81 | 139 | 154 | 131.8333 | 0.6 | 81 | 139 | 154 | 131.8333 | 84.6854 | 0 | 0 | 50.8113
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2017-02-20 01:00 | 2018-05-22 | 0.1 | 0.81199 | 0.081199 | Accept | 0.1 | 0.81199 | 0.0406 | H3 | 3 | Stable | 0.5 | 88 | 137 | 153 | 131.5 | 0.5 | 88 | 137 | 153 | 131.5 | 0 | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-022 | Project_028_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Accrediation Scope | Person_253 | 2014-01-21 01:00 | 2017-03-22 | 0.5 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 20 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK202 | Project_024_RISK202 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Mode Specific | Person_448 | 2015-09-04 01:00 | 2017-02-19 01:00 | 0.2 | 12.1982 | 0.60991 | Accept | 0.2 | 12.1982 | 0.60991 | H3 | 3 | Stable | 0.6 | 94 | 136 | 148 | 131 | 0.6 | 94 | 136 | 148 | 131 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK204 | Project_024_RISK204 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Stabilisation | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.4 | 0 | 0 | Accept | 0.4 | 0 | 0 | H1 | 5 | Improving | 0.5 | 81 | 126 | 160 | 124.1667 | 0.5 | 81 | 126 | 160 | 124.1667 |  | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2017-04-21 | 0.2 | 0.90951 | 0.1819 | Reduce | 0.2 | 0.90951 | 0.1819 | H3 | 3 | Stable | 0.8 | 117 | 123 | 151 | 126.6667 | 0.3 | 34 | 41 | 67 | 44.1667 | 0 | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2017-03-22 | 0.3 | 5.4553 | 1.6366 | Reduce | 0.15 | 5.252 | 0.7878 | H2 | 4 | Stable | 0.6 | 91 | 137 | 149 | 131.3333 | 0.4 | 14 | 57 | 79 | 53.5 | 3.7267 | 50 | 0 | 2.236
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK203 | Project_024_RISK203 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Detection/Tracking modifications | Person_448 | 2016-10-21 01:00 | 2017-02-19 01:00 | 0.1 | 1.3215 | 0.39644 | Accept | 0.1 | 1.3215 | 0.39644 | H3 | 3 | Stable | 0.5 | 91 | 132 | 152 | 128.5 | 0.5 | 91 | 132 | 152 | 128.5 | 0 | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 0.3 | 12.1982 | 2.4396 | Accept | 0.3 | 10.8428 | 1.0843 | H1 | 5 | Improving | 0.5 | 96 | 135 | 157 | 132.1667 | 0.5 | 96 | 135 | 157 | 132.1667 | 11.1111 | 0 | 0 | 6.6667
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK200 | Project_024_RISK200 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Height Finding | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.35 | 4.4727 | 0.44727 | Accept | 0.35 | 4.4727 | 0.22363 | H2 | 4 | Worsening | 0.5 | 112 | 134 | 155 | 133.8333 | 0.5 | 112 | 134 | 155 | 133.8333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_288 | 2017-02-22 01:00 | 2017-11-19 01:00 | 0.3 | 20.3303 | 7.1156 | Accept | 0.3 | 18.975 | 3.795 | H1 | 5 | Improving | 0.9 | 104 | 136 | 145 | 132.1667 | 0.9 | 104 | 136 | 145 | 132.1667 | 6.6667 | 0 | 0 | 4
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Cable and connectors | Person_499 | 2015-11-21 01:00 | 2017-08-09 | 0.45 | 0.41338 | 0.18602 | Reduce | 0.2 | 0.41338 | 0.082677 | H2 | 4 | Stable | 0.5 | 86 | 135 | 159 | 130.8333 | 0.2 | 11 | 45 | 64 | 42.5 | 0 | 55.5556 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Platform Acceptance | Person_500 | 2015-11-21 01:00 | 2017-05-22 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.3 | 8.471 | 2.5413 | H2 | 4 | Stable | 0.6 | 85 | 122 | 157 | 121.6667 | 0.2 | 23 | 40 | 71 | 42.3333 | -99.9999 | 14.2857 | 0 | -59.9999
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK209 | Project_024_RISK209 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Major Return to Service | Person_073 | 2016-11-20 01:00 | 2017-05-22 | 0.3 | 8.8098 | 3.0834 | Accept | 0.3 | 8.8098 | 1.762 | H1 | 5 | Stable | 0.9 | 85 | 122 | 144 | 119.5 | 0.9 | 85 | 122 | 144 | 119.5 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK206 | Project_024_RISK206 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Simulator Updates | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.1 | 0.40661 | 0.16264 | Accept | 0.1 | 0.40661 | 0.081321 | H3 | 3 | Stable | 0.7 | 90 | 138 | 151 | 132.1667 | 0.7 | 90 | 138 | 151 | 132.1667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Furnished Equipmnet Condition | Person_371 | 2015-04-27 | 2017-08-19 01:00 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.8 | 110 | 129 | 157 | 130.5 | 0.2 | 19 | 46 | 61 | 44 |  | 62.5 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Obsolescence Monitoring Risk | Person_181 | 2016-12-02 23:00 | 2017-01-19 23:00 | 0.3 | 5.9458 | 1.7837 | Reduce | 0.15 | 0.9786 | 0.14679 | H3 | 3 | Stable | 0.8 | 108 | 127 | 153 | 128.1667 | 0.1 | 2 | 57 | 62 | 48.6667 | 83.5413 | 50 | 0 | 50.1248
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Overland performance | Person_448 | 2016-06-23 | 2017-05-21 | 0.25 | 3.0903 | 0.61807 | Accept | 0.25 | 3.0903 | 0.61807 | H2 | 4 | Improving | 0.6 | 112 | 135 | 154 | 134.3333 | 0.6 | 112 | 135 | 154 | 134.3333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK253 | Project_024_RISK253 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Insufficient parts to complete framework Warranty | Person_289 | 2016-05-23 | 2017-04-21 | 0.1 | 23.6737 | 11.8369 | Accept | 0.1 | 52.0822 | 23.437 | H2 | 4 | Improving | 0.8 | 84 | 130 | 147 | 125.1667 | 0.8 | 84 | 130 | 147 | 125.1667 | -120 | 0 | 0 | -72
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-043 | Project_008_Risk-043 | Opportunitity | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Joint courseware and tech pubs team | Person_280 | 2014-11-21 01:00 | 2017-05-21 | 0.5 | 28.2191 | 14.1096 | -- | 0.8 | 13.2573 | 10.6058 | H1 | 5 | Stable | [10 empty] | 53.0201 | -60 | 0 | 31.8121
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-059 | Project_008_Risk-059 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Project Resource Efficencies | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 0.2 | 21.6852 | 4.337 | -- | 0.2 | 21.6852 | 4.337 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK296 | Project_024_RISK296 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | LoE Engineering support required post completion in addition to BCR | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 71.0212 | 21.3064 | Accept | 0.5 | 71.0212 | 21.3064 | H1 | 5 | Worsening | 0.5 | 98 | 133 | 153 | 130.5 | 0.5 | 98 | 133 | 153 | 130.5 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 01:00 | 2017-03-22 | 0.05 | 87.6137 | 4.3807 | Reduce | 0.05 | 87.6137 | 4.3807 | H3 | 3 | Stable | 0.8 | 99 | 137 | 152 | 133.1667 | 0.1 | 14 | 59 | 61 | 51.8333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK210 | Project_024_RISK210 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Performance impacts regualotory complaince | Person_534 | 2016-06-22 | 2017-02-19 01:00 | 0.3 | 5.8286 | 0.29143 | Accept | 0.3 | 5.8286 | 0.29143 | H2 | 4 | Stable | 0.6 | 108 | 134 | 154 | 133 | 0.6 | 108 | 134 | 154 | 133 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.3 | 53.0293 | 15.9088 | Reduce | 0.3 | 53.0293 | 15.9088 | H3 | 3 | Worsening | 0.7 | 114 | 133 | 151 | 132.8333 | 0.2 | 20 | 45 | 72 | 45.3333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Commercial aspects agreement | Person_480 | 2013-08-21 01:00 | 2016-05-22 | 0.02 | 4.8296 | 0.096593 | Transfer | 0.02 | 4.8296 | 0.096593 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 01:00 | 2017-08-20 01:00 | 0.1 | 34.363 | 3.4363 | Avoid | 0.1 | 34.363 | 3.4363 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.48 | 33.2985 | 15.9833 | Avoid | 0.48 | 33.2985 | 15.9833 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-126 | Project_032_Risk-126 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supply Chain - Delivery to Contract Requirement | Person_590 | 2012-08-21 01:00 | 2016-08-20 01:00 | 0.3 | 25.3619 | 7.6086 | Reduce | 0.3 | 25.3619 | 7.6086 | H2 | 4 | Stable | 0.5 | 105 | 138 | 159 | 136 | 0.4 | 35 | 52 | 67 | 51.6667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK222 | Project_024_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Testing Extends beyond target completion | Person_351 | 2017-07-21 | 2018-08-21 | 0.2 | 0.20788 | 0.068599 | Accept | 0.2 | 0.052336 | 0.0057569 | H2 | 4 | Stable | 0.8 | 112 | 124 | 146 | 125.6667 | 0.8 | 112 | 124 | 146 | 125.6667 | 74.8236 | 0 | 0 | 44.8942
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.25 | 7.7469 | 1.9367 | Reduce | 0.25 | 7.7469 | 1.9367 | H3 | 3 | Stable | 0.5 | 91 | 133 | 151 | 129 | 0.3 | 18 | 49 | 66 | 46.6667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-131 | Project_032_Risk-131 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 0.3 | 15.6782 | 4.7035 | Transfer | 0.3 | 15.6782 | 4.7035 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 01:00 | 0.05 | 11.3437 | 0.56718 | Reduce | 0.05 | 11.3437 | 0.56718 | H3 | 3 | Stable | 0.7 | 117 | 138 | 145 | 135.6667 | 0.2 | 35 | 42 | 72 | 45.8333 | 0 | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 0.3 | 0.51931 | 0.15579 | -- | 0.15 | 0.51931 | 0.077897 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 0.2 | 0.55005 | 0.11001 | Avoid | 0.2 | 0.55005 | 0.11001 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-123 | Project_011_Risk-123 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | No Requirement for Delta acceptance | Person_187 | 2017-06-23 | 2017-08-20 01:00 | 0.2 | 0.63074 | 0.12615 | -- | 0.2 | 0.63074 | 0.12615 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2016-07-21 | 2017-02-19 01:00 | 0.15 | 0.28639 | 0.042959 | -- | 0.15 | 0.28639 | 0.042959 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-04-21 | 0.2 | 0.24207 | 0.048414 | -- | 0.2 | 0.24207 | 0.048414 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 0.2 | 1.661 | 0.33219 | Reduce | 0.2 | 1.661 | 0.33219 | H2 | 4 | Stable | 0.8 | 97 | 137 | 150 | 132.5 | 0.1 | 37 | 59 | 70 | 57.1667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2017-10-21 01:00 | 2018-08-21 | 0.4 | 1.2444 | 0.49778 | Reduce | 0.4 | 1.2444 | 0.49778 | H2 | 4 | Stable | 0.9 | 85 | 126 | 159 | 124.6667 | 0.3 | 22 | 51 | 68 | 49 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 01:00 | 2018-08-21 | 0.45 | 0.83883 | 0.37747 | Reduce | 0.45 | 0.83883 | 0.37747 | H2 | 4 | Stable | 0.9 | 88 | 129 | 150 | 125.6667 | 0.1 | 9 | 53 | 67 | 48 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-010 | Project_011_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Rework required following integration of Customer System | Person_142 | 2013-08-21 01:00 | 2017-04-21 | 0.4 | 0.66881 | 0.26753 | Reduce | 0.4 | 0.66881 | 0.26753 | H2 | 4 | Stable | 0.5 | 105 | 122 | 142 | 122.5 | 0.3 | 38 | 51 | 71 | 52.1667 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK237 | Project_024_RISK237 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer coding standard Compliance | Person_534 | 2017-05-25 | 2017-10-27 01:00 | 0.2 | 0.098873 | 0.0098873 | Accept | 0.2 | 0.098873 | 0.0098873 | H2 | 4 | Stable | 0.7 | 111 | 122 | 153 | 125.3333 | 0.7 | 111 | 122 | 153 | 125.3333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-02-20 01:00 | 2018-08-21 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.5 | 83 | 123 | 151 | 121 | 0.4 | 35 | 46 | 78 | 49.5 |  | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Pick up and Drop off of Software Resource | Person_230 | 2017-04-21 | 2018-02-19 01:00 | 0.4 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-109 | Project_011_Risk-109 | Opportunitity | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Environment complexity | Person_187 | 2016-07-21 | 2018-08-21 | 0.25 | 0.14661 | 0.036651 | -- | 0.25 | 0.14661 | 0.036651 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-108 | Project_011_Risk-108 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Offer additional functionality to the customer | Person_147 | 2017-04-22 | 2018-08-21 | 0.1 | 0.34094 | 0.034094 | -- | 0.1 | 0.34094 | 0.034094 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 0.2 | 0.12388 | 0.024775 | Reduce | 0.2 | 0.12388 | 0.024775 | H2 | 4 | Stable | 0.9 | 112 | 140 | 150 | 137 | 0.1 | 21 | 46 | 75 | 46.6667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 0.4 | 0.51141 | 0.20457 | Avoid | 0.4 | 0.51141 | 0.20457 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK198 | Project_024_RISK198 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Spot Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 0.2 | 0.49834 | 0.12459 | Accept | 0.2 | 0.49834 | 0.12459 | H3 | 3 | Stable | 0.7 | 98 | 122 | 153 | 123.1667 | 0.7 | 98 | 122 | 153 | 123.1667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.2 | 0.10171 | 0.020343 | -- | 0.2 | 0.10171 | 0.020343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 0.3 | 0.28639 | 0.085917 | Reduce | 0.3 | 0.28639 | 0.085917 | H2 | 4 | Stable | 0.6 | 115 | 124 | 160 | 128.5 | 0.4 | 36 | 55 | 68 | 54 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 2. Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 0.25 | 0 | 0 | -- | 0.25 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2017-10-21 01:00 | 2018-05-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 0.3 | 0.10626 | 0.031878 | -- | 0.3 | 0.01932 | 0.005796 | H3 | 3 | Stable | [10 empty] | 81.8181 | 0 | 0 | 49.0909
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK199 | Project_024_RISK199 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Strip Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 0.3 | 1.0052 | 0.35182 | Accept | 0.3 | 1.0052 | 0.35182 | H2 | 4 | Stable | 0.8 | 117 | 128 | 147 | 129.3333 | 0.8 | 117 | 128 | 147 | 129.3333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_468 | 2016-11-19 23:00 | 2018-11-19 23:00 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.1 | 6.431 | 0.6431 | H3 | 3 | Stable | 0.7 | 114 | 134 | 160 | 135 | 0.1 | 35 | 48 | 68 | 49.1667 | -47.0588 | 33.3333 | 1 | -27.2353
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-118 | Project_011_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer change environment | Person_187 | 2013-08-21 01:00 | 2018-08-21 | 0.1 | 0 | 0 | Avoid | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R81 | Project_041_R81 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Re-imaging of PC's - additional material | Person_515 | 2016-11-19 23:00 | 2017-10-20 23:00 | 0.5 | 0.21008 | 0.10504 | Avoid | 0.5 | 0.21008 | 0.10504 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-116 | Project_011_Risk-116 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Delays to Qualification | Person_147 | 2017-04-22 | 2017-08-19 01:00 | 0.25 | 1.7297 | 0.43243 | -- | 0.25 | 1.7297 | 0.43243 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R85 | Project_041_R85 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Go to Offshore initiative | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 0.15 | 7.7172 | 1.1576 | -- | 0.15 | 7.7172 | 1.1576 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-104 | Project_011_Risk-104 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer delayed in providing Custeomr Furnished Equipment | Person_147 | 2016-06-23 | 2017-04-21 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.9 | 119 | 132 | 149 | 132.6667 | 0.4 | 26 | 47 | 72 | 47.6667 |  | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_368 | 2016-11-19 23:00 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.9 | 104 | 138 | 144 | 133.3333 | 0.1 | 34 | 50 | 76 | 51.6667 | 0 | 50 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK004 | Project_010_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Export License | Person_359 | 2015-02-18 01:00 | 2017-08-20 01:00 | 0.8 | 0.18482 | 0.14786 | Reduce | 0.8 | 0.18482 | 0.14786 | H1 | 5 | Improving | 0.5 | 86 | 123 | 141 | 119.8333 | 0.4 | 10 | 49 | 73 | 46.5 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R43 | Project_041_R43 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Procurement - Component and Supplier Leadtime | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 0.25 | 10.9327 | 2.7332 | Reduce | 0.15 | 10.9327 | 1.6399 | H2 | 4 | Stable | 0.9 | 117 | 137 | 147 | 135.3333 | 0.2 | 16 | 48 | 74 | 47 | 0 | 40 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 01:00 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.9 | 113 | 138 | 150 | 135.8333 | 0.3 | 16 | 47 | 69 | 45.5 | 0 | 40 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 0.75 | 10.7184 | 8.0388 | Reduce | 0.75 | 5.3592 | 4.0194 | H1 | 5 | Worsening | 0.8 | 87 | 136 | 157 | 131.3333 | 0.3 | 34 | 53 | 71 | 52.8333 | 50 | 0 | 0 | 30
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R86 | Project_041_R86 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sharing Attrition Stock with Warranty Spares pool | Person_501 | 2016-11-19 23:00 | 2018-05-22 | 0.5 | 3.1083 | 1.5542 | Exploit | 0.5 | 3.1083 | 1.5542 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.7 | 0.92411 | 0.64688 | Reduce | 0.3 | 0.36965 | 0.11089 | H2 | 4 | Stable | 0.5 | 119 | 136 | 150 | 135.5 | 0.4 | 17 | 52 | 75 | 50 | 60 | 57.1429 | 0 | 36
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 01:00 | 2016-04-21 | 0.5 | 4.0661 | 2.033 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.7 | 119 | 133 | 160 | 135.1667 | 0.1 | 28 | 58 | 65 | 54.1667 | 0 | 90 | 1 | 2.7
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.3 | 0.46206 | 0.13862 | H2 | 4 | Improving | 0.9 | 80 | 129 | 142 | 123 | 0.3 | 28 | 49 | 78 | 50.3333 | 58.3333 | 50 | 0 | 35
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.35 | 7.0313 | 3.5156 | Accept | 0.35 | 7.0313 | 3.5156 | H3 | 3 | Stable | 0.6 | 81 | 139 | 151 | 131.3333 | 0.6 | 81 | 139 | 151 | 131.3333 | 0 | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.25 | 1.1089 | 0.88715 | Accept | 0.25 | 0.73929 | 0.44357 | H3 | 3 | Stable | 0.9 | 98 | 131 | 148 | 128.3333 | 0.9 | 98 | 131 | 148 | 128.3333 | 33.3333 | 0 | 0 | 20
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.05 | 0.68598 | 0.034299 | H3 | 3 | Stable | 0.7 | 91 | 139 | 148 | 132.5 | 0.2 | 18 | 56 | 72 | 52.3333 | 0 | 80 | 1 | 2.4
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 01:00 | 2017-08-20 01:00 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.7 | 96 | 128 | 151 | 126.5 | 0.4 | 11 | 44 | 61 | 41.3333 | 0 | 50 | 1 | 1.5
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-20 23:00 | 2019-08-20 | 0.5 | 1.2519 | 0.31298 | Accept | 0.5 | 1.2519 | 0.31298 | H2 | 4 | Stable | 0.9 | 116 | 129 | 154 | 131 | 0.9 | 116 | 129 | 154 | 131 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.9 | 86 | 136 | 145 | 129.1667 | 0.1 | 19 | 57 | 72 | 53.1667 | 0 | 25 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.2 | 3.7514 | 0.37514 | Accept | 0.2 | 3.7514 | 0.37514 | H3 | 3 | Stable | 0.8 | 88 | 135 | 143 | 128.5 | 0.8 | 88 | 135 | 143 | 128.5 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Stable | 0.9 | 94 | 134 | 147 | 129.5 | 0.4 | 23 | 51 | 65 | 48.6667 | 0 | 40 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R29 | Project_041_R29 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Attrition | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 0.1 | 3.6014 | 0.36014 | Reduce | 0.05 | 3.6014 | 0.18007 | H3 | 3 | Stable | 0.7 | 100 | 137 | 158 | 134.3333 | 0.3 | 30 | 41 | 75 | 44.8333 | 0 | 50 | 1 | 1.5
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Worsening | [10 empty] | 0 | 37.5 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2016-11-19 23:00 | 2017-07-21 | 0.1 | 21.8655 | 2.1865 | Reduce | 0.05 | 21.8655 | 1.0933 | H2 | 4 | Stable | 0.9 | 107 | 133 | 160 | 133.1667 | 0.2 | 24 | 55 | 75 | 53.1667 | 0 | 50 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 0.61 | 3.6965 | 0.36965 | Accept | 0.61 | 3.6965 | 0.36965 | H1 | 5 | Stable | 0.7 | 83 | 136 | 154 | 130.1667 | 0.7 | 83 | 136 | 154 | 130.1667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Stable | 0.9 | 91 | 135 | 142 | 128.8333 | 0.1 | 14 | 59 | 70 | 53.3333 | 0 | 60 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-034 | Project_005_Risk-034 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project delay causes cost impact to project | Person_470 | 2011-12-02 01:00 | 2017-01-20 01:00 | 0.5 | 0.6088 | 0.1522 | Accept | 0.05 | 0.6088 | 0.1522 | H3 | 3 | Stable | 0.6 | 103 | 132 | 150 | 130.1667 | 0.6 | 103 | 132 | 150 | 130.1667 | 0 | 90 | 1 | 2.7
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 0.3 | 1.8482 | 0.55447 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.9 | 89 | 134 | 157 | 130.3333 | 0.2 | 34 | 41 | 65 | 43.8333 | 0 | 33.3333 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Unidentified Change Requests | Person_693 | 2016-11-19 23:00 | 2017-09-19 23:00 | 0.5 | 1.2005 | 0.60023 | Reduce | 0.1 | 0.51019 | 0.051019 | H3 | 3 | Stable | 0.5 | 116 | 130 | 147 | 130.5 | 0.2 | 29 | 46 | 65 | 46.3333 | 57.5001 | 80 | 1 | 36.9001
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 01:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.8 | 100 | 132 | 146 | 129 | 0.4 | 24 | 50 | 68 | 48.6667 | 90 | 75 | 1 | 56.25
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-060 | Project_005_Risk-060 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Technical Acceptance may be more difficult than anticipated | Person_470 | 2014-06-11 | 2017-01-20 01:00 | 0.5 | 3.3227 | 0.83067 | Accept | 0.05 | 3.3227 | 0.83067 | H3 | 3 | Stable | 0.5 | 89 | 130 | 150 | 126.5 | 0.5 | 89 | 130 | 150 | 126.5 | 0 | 90 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.1 | 0.77172 | 0.077172 | H3 | 3 | Stable | 0.5 | 117 | 135 | 146 | 133.8333 | 0.1 | 10 | 43 | 73 | 42.5 | 0 | 60 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production or Engineering | Person_359 | 2016-11-19 23:00 | 2018-05-22 | 0.15 | 1.1576 | 0.17364 | Reduce | 0.1 | 1.1576 | 0.11576 | H3 | 3 | Stable | 0.8 | 89 | 138 | 158 | 133.1667 | 0.2 | 31 | 56 | 70 | 54.1667 | 0 | 33.3333 | 1 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R13 | Project_041_R13 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Loss of key personnel | Person_359 | 2016-11-19 23:00 | 2017-08-19 23:00 | 0.5 | 0.59165 | 0.29583 | Reduce | 0.1 | 0.59165 | 0.059165 | H3 | 3 | Stable | 0.6 | 85 | 122 | 150 | 120.5 | 0.4 | 16 | 40 | 61 | 39.5 | 0 | 80 | 1 | 2.4
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 01:00 | 0.1 | 4.4985 | 1.3495 | Accept | 0.05 | 2.999 | 0.8997 | H3 | 3 | Stable | 0.9 | 83 | 138 | 158 | 132.1667 | 0.9 | 83 | 138 | 158 | 132.1667 | 33.333 | 50 | 1 | 21.4998
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-22 01:00 | 2017-05-22 | 0.25 | 7.4225 | 1.8556 | Reduce | 0.1 | 2.0081 | 0.20081 | H3 | 3 | Stable | 0.8 | 94 | 133 | 152 | 129.6667 | 0.3 | 21 | 43 | 62 | 42.5 | 72.9455 | 60 | 0 | 43.7673
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 2.6991 | 1.0796 | H2 | 4 | Stable | 0.8 | 96 | 131 | 150 | 128.3333 | 0.1 | 31 | 53 | 70 | 52.1667 | 31.8182 | 20 | 0 | 19.0909
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-015 | Project_028_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | STANDARDS Compliance | Person_499 | 2015-11-21 01:00 | 2017-03-21 01:00 | 0.05 | 18.069 | 1.8069 | Accept | 0.05 | 11.3212 | 1.1321 | H3 | 3 | Stable | 0.6 | 109 | 139 | 157 | 137 | 0.6 | 109 | 139 | 157 | 137 | 37.3444 | 0 | 1 | 22.4066
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_575 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 5.0983 | 0.76474 | H3 | 3 | Stable | 0.5 | 100 | 123 | 142 | 122.3333 | 0.4 | 2 | 50 | 73 | 45.8333 | 19.0479 | 70 | 1 | 13.5287
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-148 | Project_020_Risk-148 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs non-available items | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.3 | 14.9935 | 4.498 | Reduce | 0.3 | 14.9935 | 4.498 | H2 | 4 | Stable | 0.5 | 99 | 134 | 150 | 130.8333 | 0.1 | 12 | 44 | 66 | 42.3333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence and missing info | Person_727 | 2015-11-25 01:00 | 2017-02-19 01:00 | 0.3 | 1.8788 | 0.18788 | Accept | 0.3 | 1.8788 | 0.18788 | H2 | 4 | Stable | 0.7 | 99 | 133 | 150 | 130.1667 | 0.7 | 99 | 133 | 150 | 130.1667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 01:00 | 2017-03-22 | 0.2 | 18.6688 | 3.7338 | Accept | 0.1 | 18.6688 | 3.7338 | H2 | 4 | Stable | 0.6 | 115 | 133 | 158 | 134.1667 | 0.6 | 115 | 133 | 158 | 134.1667 | 0 | 50 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-002 | Project_028_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Record / Replay feature | Person_499 | 2014-03-23 | 2017-03-21 01:00 | 0.1 | 29.4599 | 8.838 | Accept | 0.05 | 18.7882 | 5.6365 | H2 | 4 | Stable | 0.7 | 83 | 123 | 152 | 121.1667 | 0.7 | 83 | 123 | 152 | 121.1667 | 36.2245 | 50 | 0 | 21.7347
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-147 | Project_020_Risk-147 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component taking longer to refurbish in country | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.6 | 6.7477 | 4.0486 | Reduce | 0.6 | 6.7477 | 4.0486 | H2 | 4 | Stable | 0.9 | 103 | 135 | 151 | 132.3333 | 0.4 | 11 | 44 | 73 | 43.3333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | EMC Testing | Person_070 | 2016-04-22 | 2017-04-21 | 0.35 | 1.1273 | 0.22546 | Accept | 0.2 | 1.1273 | 0.22546 | H2 | 4 | Stable | 0.9 | 87 | 129 | 142 | 124.1667 | 0.9 | 87 | 129 | 142 | 124.1667 | 0 | 42.8571 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_542 | 2015-01-22 01:00 | 2017-08-20 01:00 | 0.35 | 4.7948 | 0.95895 | Accept | 0.2 | 4.7948 | 0.95895 | H2 | 4 | Stable | 0.8 | 86 | 137 | 151 | 130.8333 | 0.8 | 86 | 137 | 151 | 130.8333 | 0 | 42.8571 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-150 | Project_020_Risk-150 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Power supply Test Environment | Person_248 | 2016-10-21 01:00 | 2017-05-22 | 0.6 | 6.7477 | 4.0486 | Reduce | 0.6 | 6.7477 | 4.0486 | H2 | 4 | Worsening | 0.9 | 99 | 136 | 154 | 132.8333 | 0.4 | 37 | 41 | 68 | 44.8333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_070 | 2016-06-23 | 2017-04-21 | 0.4 | 0.65759 | 0.098638 | Accept | 0.2 | 0.65759 | 0.098638 | H2 | 4 | Stable | 0.6 | 84 | 130 | 150 | 125.6667 | 0.6 | 84 | 130 | 150 | 125.6667 | 0 | 50 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 0.5 | 2.5834 | 0.64585 | Accept | 0.45 | 2.5834 | 0.64585 | H2 | 4 | Stable | 0.6 | 90 | 137 | 141 | 129.8333 | 0.6 | 90 | 137 | 141 | 129.8333 | 0 | 10 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation | Person_565 | 2018-05-22 | 2018-08-21 | 0.25 | 0.65759 | 0.065759 | Accept | 0.25 | 0.75153 | 0.075153 | H3 | 3 | Stable | 0.8 | 106 | 127 | 156 | 128.3333 | 0.8 | 106 | 127 | 156 | 128.3333 | -14.2857 | 0 | 0 | -8.5714
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 0.05 | 9.3941 | 0.93941 | Accept | 0.05 | 9.3941 | 0.93941 | H2 | 4 | Stable | 0.6 | 110 | 128 | 157 | 129.8333 | 0.6 | 110 | 128 | 157 | 129.8333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Governance and Export Rules | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 0.93941 | 0.23485 | Transfer | 0.25 | 0.93941 | 0.23485 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2017-03-22 | 0.85 | 25.2325 | 21.4476 | Avoid | 0.08 | 20.8758 | 1.6701 | H2 | 4 | Stable | [10 empty] | 17.2662 | 90.5882 | 0 | 10.3597
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-019 | Project_023_Risk-019 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software | Person_253 | 2013-05-19 | 2017-05-22 | 0.8 | 0.38121 | 0.30497 | Exploit | 0.8 | 0.47651 | 0.38121 | H2 | 4 | Stable | [10 empty] | -25 | 0 | 0 | -15
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2017-02-19 01:00 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.35 | 2.9061 | 1.0171 | H2 | 4 | Stable | 0.7 | 106 | 137 | 154 | 134.6667 | 0.1 | 3 | 53 | 63 | 46.3333 | 21.0126 | 56.25 | 0 | 12.6076
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2017-03-22 | 0.7 | 24.1887 | 16.9321 | Reduce | 0.25 | 4.3567 | 1.0892 | H2 | 4 | Stable | 0.5 | 111 | 137 | 158 | 136.1667 | 0.3 | 32 | 51 | 69 | 50.8333 | 81.9887 | 64.2857 | 0 | 49.1932
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 1.0687 | 0.85496 | H2 | 4 | Stable | [10 empty] | 68.1283 | 0 | 0 | 40.877
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 0.25 | 13.3529 | 6.6765 | Accept | 0.25 | 13.3529 | 6.6765 | H3 | 3 | Stable | 0.6 | 85 | 130 | 153 | 126.3333 | 0.6 | 85 | 130 | 153 | 126.3333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 0.5 | 9.2728 | 4.6364 | Reduce | 0.3 | 9.2728 | 2.7819 | H2 | 4 | Stable | 0.5 | 110 | 128 | 142 | 127.3333 | 0.3 | 21 | 49 | 73 | 48.3333 | 0 | 40 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 0.3 | 8.7814 | 2.6344 | Reduce | 0.15 | 8.7832 | 1.3175 | H3 | 3 | Stable | 0.5 | 82 | 132 | 142 | 125.3333 | 0.3 | 30 | 41 | 66 | 43.3333 | -0.021119 | 50 | 0 | -0.012672
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | More issues than expected during Qualification | Person_147 | 2017-04-22 | 2017-11-04 01:00 | 0.35 | 108.3186 | 32.4956 | Accept | 0.35 | 108.3186 | 32.4956 | H1 | 5 | Stable | 0.5 | 107 | 121 | 158 | 124.8333 | 0.5 | 107 | 121 | 158 | 124.8333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Delay of processing | Person_306 | 2016-01-13 01:00 | 2019-08-21 01:00 | 0.15 | 26.3497 | 3.9525 | Reduce | 0.15 | 13.1767 | 1.9765 | H3 | 3 | Stable | 0.8 | 110 | 140 | 152 | 137 | 0.3 | 20 | 56 | 78 | 53.6667 | 49.993 | 0 | 1 | 29.9958
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 0.2 | 12.0547 | 2.4109 | Accept | 0.2 | 12.0547 | 2.4109 | H2 | 4 | Stable | 0.8 | 120 | 133 | 159 | 135.1667 | 0.8 | 120 | 133 | 159 | 135.1667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 18:00 | 2019-08-20 18:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 18:00 | 2019-08-20 18:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 18:00 | 2019-08-20 18:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 18:00 | 2019-08-20 18:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 18:00 | 2019-08-20 18:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.41 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -2.5 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.61 | 0.25667 | 0.15657 | Reduce | 0.5 | 0.25667 | 0.12834 | H2 | 4 | Stable | 0.6 | 104 | 121 | 141 | 121.5 | 0.4 | 18 | 59 | 73 | 54.5 | 0 | 18.0328 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2014-01-21 01:00 | 2017-11-20 01:00 | 0.4 | 1.078 | 0.43121 | Reduce | 0.4 | 1.4673 | 0.58692 | H2 | 4 | Stable | 0.6 | 89 | 128 | 150 | 125.1667 | 0.2 | 4 | 48 | 68 | 44 | -36.1112 | 0 | 0 | -21.6667
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-118 | Project_029_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Acceptance Schedule is longer in duration/delayed due to unplanned events. [Hardware availability] | Person_102 | 2015-12-22 01:00 | 2017-05-23 | 0.55 | 1.3775 | 0.75761 | Reduce | 0.55 | 1.3775 | 0.75761 | H2 | 4 | Stable | 0.8 | 86 | 129 | 155 | 126.1667 | 0.3 | 12 | 50 | 76 | 48 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2017-11-19 01:00 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2017-05-23 | 0.6 | 0.89835 | 0.53901 | Transfer | 0.6 | 0.89835 | 0.53901 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 0.35 | 0.85557 | 0.29945 | Reduce | 0.35 | 1.9208 | 0.67227 | H2 | 4 | Stable | 0.9 | 113 | 134 | 147 | 132.6667 | 0.4 | 19 | 42 | 70 | 42.8333 | -124.5001 | 0 | 0 | -74.7001
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.05 | 0.77001 | 0.30801 | Accept | 0.05 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.8 | 98 | 130 | 146 | 127.3333 | 0.8 | 98 | 130 | 146 | 127.3333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2017-05-23 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.8 | 105 | 130 | 155 | 130 | 0.2 | 14 | 53 | 61 | 47.8333 | 0 | 28.5714 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Risk of repeat component Tests | Person_515 | 2017-12-20 23:00 | 2019-01-20 23:00 | 0.5 | 1.54 | 0.30801 | Accept | 0.5 | 0.77001 | 0.154 | H2 | 4 | Stable | 0.9 | 91 | 133 | 147 | 128.3333 | 0.9 | 91 | 133 | 147 | 128.3333 | 50 | 0 | 0 | 30
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_515 | 2017-05-23 | 2019-01-20 23:00 | 0.5 | 0.94968 | 0.28491 | Accept | 0.5 | 0.94968 | 0.18994 | H2 | 4 | Stable | 0.5 | 93 | 140 | 142 | 132.5 | 0.5 | 93 | 140 | 142 | 132.5 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R44 | Project_041_R44 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Procurement - Source Change and cost change | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 0.5 | 27.1644 | 0.81493 | Accept | 0.5 | 12.8336 | 1.2834 | H1 | 5 | Worsening | 0.5 | 107 | 129 | 141 | 127.3333 | 0.5 | 107 | 129 | 141 | 127.3333 | 52.7559 | 0 | 0 | 31.6535
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2014-07-22 | 2017-11-19 01:00 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.7 | 91 | 124 | 144 | 121.8333 | 0.2 | 14 | 54 | 74 | 50.6667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2017-10-14 01:00 | 0.41 | 6.4168 | 2.6309 | Transfer | 0.41 | 0 | 0 | H1 | 5 | Stable | [10 empty] | 100 | 0 | 0 | 60
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub-system FPGA | Person_216 | 2017-01-21 01:00 | 2018-05-22 | 0.3 | 1.54 | 0.46201 | Reduce | 0.4 | 1.5914 | 0.63655 | H2 | 4 | Stable | 0.9 | 106 | 131 | 149 | 129.8333 | 0.1 | 10 | 48 | 74 | 46 | -3.3333 | -33.3333 | 0 | -2
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SystemC HW/SW | Person_199 | 2016-05-23 | 2019-10-21 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.3 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.5 | 101 | 125 | 153 | 125.6667 | 0.1 | 23 | 43 | 75 | 45 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs [technical scope] | Person_466 | 2017-01-21 01:00 | 2019-07-21 | 0.35 | 9.505 | 3.3267 | Reduce | 0.35 | 9.505 | 3.3267 | H2 | 4 | Stable | 0.9 | 93 | 140 | 150 | 133.8333 | 0.2 | 23 | 55 | 75 | 53 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.5 | 3.5934 | 1.7967 | H2 | 4 | Stable | 0.8 | 102 | 122 | 148 | 123 | 0.2 | 31 | 40 | 64 | 42.5 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | HW - additional unplanned design effort | Person_216 | 2016-05-23 | 2019-10-21 01:00 | 0.4 | 3.3367 | 1.3347 | -- | 0.4 | 3.3367 | 1.3347 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 0.8 | 3.9356 | 0.98391 | Accept | 0.6 | 4.2779 | 1.0695 | H1 | 5 | Stable | 0.7 | 110 | 125 | 151 | 126.8333 | 0.7 | 110 | 125 | 151 | 126.8333 | -8.6957 | 25 | 0 | -5.2174
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_368 | 2016-11-19 23:00 | 2017-09-18 23:00 | 0.25 | 2.5667 | 0.77001 | Accept | 0.25 | 2.5667 | 0.77001 | H3 | 3 | Stable | 0.5 | 86 | 136 | 160 | 131.6667 | 0.5 | 86 | 136 | 160 | 131.6667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design | Person_216 | 2016-05-23 | 2020-10-20 01:00 | 0.2 | 2.6951 | 0.53901 | Reduce | 0.2 | 2.6951 | 0.53901 | H3 | 3 | Stable | 0.7 | 87 | 139 | 142 | 130.8333 | 0.2 | 24 | 58 | 70 | 54.3333 | 0 | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Non-Recurring Engineering higher than expected | Person_674 | 2016-06-01 | 2016-08-04 | 0.4 | 6.5968 | 2.6387 | Reduce | 0.2 | 6.5944 | 1.3189 | H3 | 3 | Improving | 0.7 | 102 | 125 | 145 | 124.5 | 0.2 | 2 | 44 | 67 | 40.8333 | 0.036395 | 50 | 0 | 0.021837
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 0.1 | 0.5596 | 0.05596 | Accept | 0.1 | 0.5596 | 0.05596 | H3 | 3 | Stable | 0.6 | 89 | 126 | 150 | 123.8333 | 0.6 | 89 | 126 | 150 | 123.8333 | 0 | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 01:00 | 2016-08-20 01:00 | 0.1 | 3.6174 | 1.8087 | Accept | 0.1 | 3.6172 | 0.72345 | H2 | 4 | Stable | 0.7 | 103 | 138 | 144 | 133.1667 | 0.7 | 103 | 138 | 144 | 133.1667 | 0.0051359 | 0 | 0 | 0.0030815
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 0.2 | 2.3503 | 0.47006 | Accept | 0.2 | 2.3503 | 0.47006 | H3 | 3 | Improving | 0.7 | 102 | 124 | 144 | 123.6667 | 0.7 | 102 | 124 | 144 | 123.6667 | 0 | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R06 | Project_041_R06 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional PM time to support the supply chain | Person_359 | 2016-11-19 23:00 | 2017-09-18 23:00 | 0.25 | 4.4768 | 2.2384 | Accept | 0.25 | 4.4768 | 2.2384 | H3 | 3 | Stable | 0.5 | 102 | 128 | 148 | 127 | 0.5 | 102 | 128 | 148 | 127 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 0.25 | 244.3581 | 12.2179 | Accept | 0.25 | 227.5702 | 11.3785 | H2 | 4 | Stable | 0.7 | 101 | 138 | 158 | 135.1667 | 0.7 | 101 | 138 | 158 | 135.1667 | 6.8702 | 0 | 0 | 4.1221
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.7 | 102 | 133 | 152 | 131 | 0.2 | 22 | 40 | 70 | 42 | 0 | 25 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Suppliers | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 6.2496 | 6.2496 | Accept | 0.15 | 6.2496 | 6.2496 | H2 | 4 | Stable | 0.7 | 113 | 132 | 143 | 130.6667 | 0.7 | 113 | 132 | 143 | 130.6667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 3.4415 | 1.3766 | Accept | 0.2 | 3.4415 | 1.3766 | H2 | 4 | Stable | 0.6 | 87 | 126 | 146 | 122.8333 | 0.6 | 87 | 126 | 146 | 122.8333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Local customer Engineers in country | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 8.0582 | 2.4175 | Accept | 0.1 | 8.0582 | 2.4175 | H2 | 4 | Stable | 0.8 | 83 | 128 | 146 | 123.5 | 0.8 | 83 | 128 | 146 | 123.5 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-149 | Project_020_Risk-149 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs to be returned to UK | Person_703 | 2016-12-21 01:00 | 2017-11-19 01:00 | 0.2 | 17.0765 | 1.7076 | Accept | 0.2 | 17.0765 | 1.7076 | H2 | 4 | Stable | 0.7 | 97 | 139 | 150 | 133.8333 | 0.7 | 97 | 139 | 150 | 133.8333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.8 | 100 | 130 | 144 | 127.3333 | 0.4 | 11 | 43 | 76 | 43.1667 | 0 | 60 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence | Person_455 | 2016-05-23 | 2020-05-23 | 0.3 | 50.7895 | 40.6316 | Accept | 0.3 | 50.7895 | 40.6316 | H2 | 4 | Stable | 0.9 | 81 | 140 | 153 | 132.3333 | 0.9 | 81 | 140 | 153 | 132.3333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK201 | Project_024_RISK201 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Indication mode failure | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.25 | 1.6835 | 0.42087 | Reduce | 0.2 | 1.6835 | 0.33669 | H3 | 3 | Stable | 0.9 | 111 | 124 | 150 | 126.1667 | 0.1 | 37 | 43 | 77 | 47.6667 | 0 | 20 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Consumables | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 1.3502 | 0.54009 | Accept | 0.2 | 1.9561 | 0.78244 | H2 | 4 | Stable | 0.7 | 104 | 131 | 150 | 129.6667 | 0.7 | 104 | 131 | 150 | 129.6667 | -44.8717 | 0 | 0 | -26.923
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 7. Finance | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 22.8501 | 6.855 | Accept | 0.2 | 22.8501 | 6.855 | H2 | 4 | Stable | 0.6 | 89 | 124 | 144 | 121.5 | 0.6 | 89 | 124 | 144 | 121.5 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK286 | Project_024_RISK286 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Requirement sell off more difficult than expected | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 10.1787 | 5.0893 | Reduce | 0.5 | 10.1787 | 5.0893 | H1 | 5 | Worsening | 0.8 | 81 | 121 | 159 | 120.6667 | 0.2 | 5 | 43 | 74 | 41.8333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK288 | Project_024_RISK288 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Unplanned obsolescence and/or repairs to rig assets. | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.6 | 5.8424 | 3.5054 | Reduce | 0.6 | 5.8424 | 3.5054 | H1 | 5 | Stable | 0.7 | 83 | 130 | 160 | 127.1667 | 0.1 | 34 | 52 | 79 | 53.5 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 1.3502 | 0.47258 | Accept | 0.15 | 2.2677 | 0.79369 | H2 | 4 | Stable | 0.8 | 92 | 125 | 149 | 123.5 | 0.8 | 92 | 125 | 149 | 123.5 | -67.9487 | 0 | 0 | -40.7692
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 19.9938 | 5.9981 | Accept | 0.2 | 19.9938 | 5.9981 | H2 | 4 | Stable | 0.9 | 102 | 126 | 155 | 126.8333 | 0.9 | 102 | 126 | 155 | 126.8333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.5 | 3.843 | 1.9215 | H1 | 5 | Stable | 0.8 | 99 | 128 | 151 | 127 | 0.1 | 33 | 53 | 71 | 52.6667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport Routes | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 19.4745 | 5.8424 | Accept | 0.15 | 19.4745 | 5.8424 | H2 | 4 | Stable | 0.7 | 100 | 140 | 141 | 133.5 | 0.7 | 100 | 140 | 141 | 133.5 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Overland performance | Person_448 | 2016-06-23 | 2017-05-21 | 0.1 | 1.6835 | 0.16835 | Reduce | 0.1 | 3.5011 | 0.35011 | H3 | 3 | Improving | 0.5 | 83 | 133 | 142 | 126.1667 | 0.2 | 37 | 44 | 64 | 46.1667 | -107.9692 | 0 | 1 | -64.7815
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Internal Quality Issues | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 2.7146 | 2.7146 | Accept | 0.2 | 2.7146 | 2.7146 | H2 | 4 | Stable | 0.6 | 108 | 124 | 154 | 126.3333 | 0.6 | 108 | 124 | 154 | 126.3333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk017 | Project_042_Risk017 | Threat | Financial Contingency | Open | H2 | 4 | 6. Contractual/Legal | Liquidated Damages | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 8.5688 | 4.2844 | Accept | 0.4 | 8.5688 | 4.2844 | H2 | 4 | Stable | 0.5 | 90 | 134 | 148 | 129 | 0.5 | 90 | 134 | 148 | 129 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Repairs | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 30.562 | 24.4496 | Accept | 0.25 | 30.562 | 24.4496 | H2 | 4 | Stable | 0.7 | 109 | 137 | 154 | 135.1667 | 0.7 | 109 | 137 | 154 | 135.1667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK213 | Project_024_RISK213 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Rigs requireaccreditation as "Special to Type" Test equipment | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.3 | 38.17 | 11.451 | Reduce | 0.25 | 19.4745 | 4.8686 | H2 | 4 | Stable | 0.5 | 86 | 140 | 157 | 133.8333 | 0.2 | 7 | 55 | 73 | 50 | 48.9796 | 16.6667 | 0 | 29.3878
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk016 | Project_042_Risk016 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport/Delivery Speed | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 68.1262 | 6.8126 | Accept | 0.1 | 68.1262 | 6.8126 | H2 | 4 | Stable | 0.6 | 96 | 136 | 148 | 131.3333 | 0.6 | 96 | 136 | 148 | 131.3333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Country Stability | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 90.8811 | 13.6322 | Accept | 0.4 | 90.8811 | 13.6322 | H2 | 4 | Stable | 0.9 | 100 | 125 | 150 | 125 | 0.9 | 100 | 125 | 150 | 125 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 4.847 | 1.4541 | Accept | 0.1 | 4.847 | 1.4541 | H2 | 4 | Stable | 0.5 | 117 | 121 | 159 | 126.6667 | 0.5 | 117 | 121 | 159 | 126.6667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK219 | Project_024_RISK219 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | STTE additional work | Person_289 | 2016-09-20 01:00 | 2017-07-21 | 0.5 | 15.0863 | 7.5431 | Reduce | 0.5 | 15.0863 | 7.5431 | H1 | 5 | Worsening | 0.5 | 96 | 128 | 156 | 127.3333 | 0.1 | 29 | 43 | 62 | 43.8333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK218 | Project_024_RISK218 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | System issues general | Person_289 | 2016-08-21 01:00 | 2017-05-14 | 0.4 | 90.8811 | 36.3524 | Reduce | 0.3 | 39.3904 | 11.8171 | H1 | 5 | Stable | 0.6 | 106 | 129 | 144 | 127.6667 | 0.1 | 37 | 52 | 67 | 52 | 56.6571 | 25 | 0 | 33.9943
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 9.8671 | 1.9734 | Accept | 0.2 | 9.8671 | 1.9734 | H2 | 4 | Stable | 0.9 | 118 | 121 | 160 | 127 | 0.9 | 118 | 121 | 160 | 127 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2017-03-22 | 0.41 | 15.5796 | 6.2318 | Accept | 0.41 | 15.5796 | 6.2318 | H2 | 4 | Stable | 0.5 | 90 | 122 | 148 | 121 | 0.5 | 90 | 122 | 148 | 121 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-016 | Project_023_Risk-016 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Damage to equipment (Unable to replace due to obsolescence) | Person_703 | 2015-10-22 01:00 | 2017-01-20 01:00 | 0.3 | 12.983 | 2.5966 | Accept | 0.3 | 16.8779 | 3.3756 | H2 | 4 | Stable | 0.6 | 115 | 129 | 152 | 130.5 | 0.6 | 115 | 129 | 152 | 130.5 | -30 | 0 | 0 | -18
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 0.5 | 1.3502 | 0.67512 | Accept | 0.5 | 3.0415 | 0.6083 | H2 | 4 | Improving | 0.6 | 110 | 136 | 152 | 134.3333 | 0.6 | 110 | 136 | 152 | 134.3333 | -125.2563 | 0 | 0 | -75.1538
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 0.3 | 1.3502 | 0.40507 | Accept | 0.3 | 2.2071 | 0.66213 | H2 | 4 | Stable | 0.7 | 110 | 129 | 148 | 129 | 0.7 | 110 | 129 | 148 | 129 | -63.4615 | 0 | 0 | -38.0769
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.2 | 20.8767 | 4.1753 | H2 | 4 | Stable | 0.5 | 115 | 123 | 160 | 127.8333 | 0.2 | 25 | 57 | 74 | 54.5 | 50 | 50 | 0 | 30
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.4769 | 79.0146 | 37.6821 | Reduce | 0.29469 | 62.617 | 18.4526 | H1 | 5 | Worsening | 0.8 | 97 | 140 | 155 | 135.3333 | 0.3 | 14 | 43 | 66 | 42 | 20.7525 | 38.2072 | 0 | 12.4515
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2016-05-23 | 2019-07-21 | 0.4 | 32.4575 | 1.2983 | Accept | 0.3 | 32.4575 | 1.2983 | H2 | 4 | Stable | 0.7 | 82 | 130 | 147 | 124.8333 | 0.7 | 82 | 130 | 147 | 124.8333 | 0 | 25 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK153 | Project_024_RISK153 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Processor memory/performance Issue | Person_331 | 2016-06-23 | 2017-03-22 | 0.3 | 112.3463 | 33.7039 | Reduce | 0.2 | 38.196 | 7.6392 | H2 | 4 | Stable | 0.5 | 119 | 124 | 144 | 126.5 | 0.4 | 18 | 41 | 66 | 41.3333 | 66.0015 | 33.3333 | 0 | 39.6009
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2019-10-14 01:00 | 0.2 | 25.966 | 7.7898 | Accept | 0.2 | 22.5039 | 6.7512 | H3 | 3 | Stable | 0.7 | 111 | 133 | 155 | 133 | 0.7 | 111 | 133 | 155 | 133 | 13.3333 | 0 | 0 | 8
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2015-07-22 | 2019-07-21 | 0.3 | 62.3617 | 3.1181 | Accept | 0.2 | 62.3617 | 3.1181 | H3 | 3 | Stable | 0.9 | 90 | 138 | 149 | 131.8333 | 0.9 | 90 | 138 | 149 | 131.8333 | 0 | 33.3333 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 4.5441 | 0.45441 | Accept | 0.1 | 4.5441 | 0.45441 | H2 | 4 | Stable | 0.6 | 110 | 137 | 149 | 134.5 | 0.6 | 110 | 137 | 149 | 134.5 | 0 | -233.3333 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK179 | Project_024_RISK179 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Testing Required | Person_289 | 2016-12-21 01:00 | 2017-05-22 | 0.5 | 3.5054 | 1.7527 | Reduce | 0.4 | 3.5054 | 1.4022 | H2 | 4 | Stable | 0.6 | 115 | 127 | 153 | 129.3333 | 0.1 | 10 | 57 | 72 | 51.6667 | 0 | 20 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 30.2764 | 12.1106 | Accept | 0.25 | 30.2764 | 12.1106 | H2 | 4 | Stable | 0.7 | 100 | 133 | 144 | 129.3333 | 0.7 | 100 | 133 | 144 | 129.3333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of Batch 2 Re-Design | Person_199 | 2016-05-23 | 2019-10-21 01:00 | 0.3 | 11.9444 | 5.9722 | Accept | 0.3 | 11.9444 | 5.9722 | H2 | 4 | Stable | 0.7 | 113 | 137 | 156 | 136.1667 | 0.7 | 113 | 137 | 156 | 136.1667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK180 | Project_024_RISK180 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | High Accelerated Life Testing (HALT) | Person_289 | 2016-12-21 01:00 | 2017-05-03 | 0.4 | 10.4903 | 4.1961 | Reduce | 0.2 | 10.4903 | 2.0981 | H2 | 4 | Stable | 0.5 | 107 | 128 | 146 | 127.5 | 0.1 | 17 | 44 | 64 | 42.8333 | 0 | 50 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_073 | 2016-05-23 | 2017-02-19 01:00 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.9 | 86 | 138 | 159 | 132.8333 | 0.1 | 6 | 40 | 73 | 39.8333 | 0 | 50 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_413 | 2015-11-21 01:00 | 2017-05-22 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.9 | 97 | 125 | 150 | 124.5 | 0.3 | 8 | 51 | 74 | 47.6667 | 0 | 5 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_692 | 2016-12-21 01:00 | 2017-12-19 01:00 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Stable | 0.6 | 85 | 126 | 152 | 123.5 | 0.4 | 26 | 55 | 73 | 53.1667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_692 | 2017-05-23 | 2019-07-21 | 0.333 | 11.5502 | 3.8462 | Reduce | 0.333 | 11.5502 | 3.8462 | H2 | 4 | Stable | 0.6 | 86 | 123 | 147 | 120.8333 | 0.2 | 7 | 44 | 64 | 41.1667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-117 | Project_039_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Filters | Person_185 | 2015-01-21 | 2016-12-19 | 0.1 | 3.005 | 0.3005 | Reduce | 0.1 | 3.005 | 0.3005 | H3 | 3 | Stable | 0.7 | 118 | 131 | 153 | 132.5 | 0.1 | 25 | 40 | 68 | 42.1667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2017-02-19 01:00 | 0.05 | 0.35617 | 0.10685 | Accept | 0.05 | 0.35617 | 0.10685 | H3 | 3 | Improving | 0.5 | 120 | 135 | 141 | 133.5 | 0.5 | 120 | 135 | 141 | 133.5 | 0 | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2017-02-20 01:00 | 2018-05-22 | 0.1 | 3.1818 | 1.5909 | Accept | 0.1 | 3.1818 | 1.5909 | H3 | 3 | Stable | 0.5 | 93 | 128 | 151 | 126 | 0.5 | 93 | 128 | 151 | 126 | 0 | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK204 | Project_024_RISK204 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Stabilisation | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.4 | 7.3646 | 3.6823 | Accept | 0.4 | 7.3646 | 3.6823 | H1 | 5 | Improving | 0.8 | 115 | 127 | 150 | 128.8333 | 0.8 | 115 | 127 | 150 | 128.8333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 0.3 | 0 | 0 | Accept | 0.3 | 0 | 0 | H1 | 5 | Improving | 0.9 | 117 | 123 | 155 | 127.3333 | 0.9 | 117 | 123 | 155 | 127.3333 |  | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 01:00 | 2016-05-21 | 0.5 | 4.3921 | 2.196 | Reduce | 0.3 | 4.3921 | 1.3176 | H1 | 5 | Stable | 0.5 | 97 | 137 | 158 | 133.8333 | 0.1 | 8 | 58 | 79 | 53.1667 | 0 | 40 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 0.4 | 9.139 | 3.6556 | Avoid | 0.2 | 9.139 | 1.8278 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 0.5 | 13.7833 | 6.8917 | Avoid | 0.2 | 6.8917 | 1.3783 | H3 | 3 | Stable | [10 empty] | 50 | 60 | 1 | 31.8
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-20 01:00 | 0.3 | 5.5433 | 1.663 | Reduce | 0.1 | 5.5433 | 0.55433 | H3 | 3 | Improving | 0.8 | 111 | 137 | 154 | 135.5 | 0.2 | 39 | 41 | 76 | 46.5 | 0 | 66.6667 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Stable | [10 empty] | 0 | 75 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK200 | Project_024_RISK200 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Height Finding | Person_448 | 2016-05-23 | 2017-03-21 01:00 | 0.35 | 4.4946 | 1.1236 | Accept | 0.35 | 4.4946 | 0.44946 | H2 | 4 | Worsening | 0.9 | 82 | 133 | 143 | 126.1667 | 0.9 | 82 | 133 | 143 | 126.1667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_288 | 2017-02-22 01:00 | 2017-11-19 01:00 | 0.3 | 6.7418 | 1.6855 | Accept | 0.3 | 6.7418 | 1.0113 | H1 | 5 | Improving | 0.5 | 107 | 136 | 154 | 134.1667 | 0.5 | 107 | 136 | 154 | 134.1667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 0.125 | 232.2192 | 29.0274 | -- | 0.215 | 27.8663 | 5.9913 | H2 | 4 | Stable | [10 empty] | 88 | -72 | 0 | 52.8
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 0.3 | 26.9674 | 8.0902 | Avoid | 0.3 | 14.9819 | 4.4946 | H2 | 4 | Stable | [10 empty] | 44.4444 | 0 | 0 | 26.6667
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-21 01:00 | 0.5 | 26.9674 | 13.4837 | Avoid | 0.1 | 12.7646 | 1.2765 | H2 | 4 | Worsening | [10 empty] | 52.6667 | 80 | 0 | 31.6
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK209 | Project_024_RISK209 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Major Return to Service | Person_073 | 2016-11-20 01:00 | 2017-05-22 | 0.3 | 17.9783 | 3.5957 | Accept | 0.3 | 17.9783 | 3.5957 | H1 | 5 | Stable | 0.7 | 81 | 133 | 157 | 128.3333 | 0.7 | 81 | 133 | 157 | 128.3333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-12-21 01:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.7 | 116 | 123 | 155 | 127.1667 | 0.4 | 38 | 50 | 69 | 51.1667 | 47 | 0 | 0 | 28.2
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-12-21 01:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK117 | Project_037_RISK117 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Data Comms Availability or Performance | Person_334 | 2015-05-24 | 2016-11-20 01:00 | 0.35 | 3.2401 | 1.134 | Transfer | 0.05 | 3.2401 | 0.16201 | H3 | 3 | Improving | [10 empty] | 0 | 85.7143 | 1 | 2.5714
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-19 01:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.2 | 1.5935 | 0.3187 | H3 | 3 | Stable | 0.7 | 110 | 138 | 147 | 134.8333 | 0.1 | 2 | 48 | 70 | 44 | 50 | 50 | 1 | 31.5
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK291 | Project_024_RISK291 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | LoE Engineering support required post completion in addition to BCR | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 0.034059 | 0.0034059 | Accept | 0.5 | 0.034059 | 0.0034059 | H1 | 5 | Worsening | 0.8 | 91 | 139 | 157 | 134 | 0.8 | 91 | 139 | 157 | 134 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk005 | Project_002_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2014-06-14 | 2016-08-08 | 0.3 | 0.035539 | 0.010662 | Avoid | 0.3 | 0.035539 | 0.010662 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk008 | Project_002_Risk008 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2014-08-20 | 2016-08-07 | 0.1 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | -100 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk009 | Project_002_Risk009 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2014-06-14 | 2016-08-07 | 0.1 | 0.01925 | 0.001925 | Avoid | 0.1 | 0.01925 | 0.001925 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | RISK012 | Project_002_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Resourcing Suitably Qualified and experienced staff availability | Person_650 | 2015-11-21 | 2016-08-07 | 0.2 | 0.05627 | 0.011254 | Reduce | 0.2 | 0.05627 | 0.011254 | H3 | 3 | Stable | 0.5 | 119 | 126 | 141 | 127.3333 | 0.1 | 35 | 57 | 67 | 55 | 0 | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk004 | Project_002_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability of Test Equipment | Person_133 | 2014-03-26 | 2016-08-08 | 0.2 | 0.081443 | 0.016289 | Avoid | 0.2 | 0.081443 | 0.016289 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk006 | Project_002_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Additional Pressure Testing | Person_650 | 2014-06-14 | 2016-08-08 | 0.25 | 0.035539 | 0.0088847 | Avoid | 0.25 | 0.035539 | 0.0088847 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk011 | Project_002_Risk011 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Testing | Person_175 | 2014-06-29 | 2016-08-07 | 0.41 | 0.071669 | 0.029384 | Reduce | 0.1 | 0.0088847 | 0.00088847 | H3 | 3 | Stable | 0.5 | 118 | 134 | 151 | 134.1667 | 0.3 | 29 | 50 | 73 | 50.3333 | 87.6032 | 75.6098 | 1 | 54.8302
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK253 | Project_024_RISK253 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Insufficient parts to complete framework Warranty | Person_289 | 2016-05-23 | 2017-04-21 | 0.1 | 6.3266 | 1.898 | Accept | 0.1 | 6.3266 | 1.297 | H2 | 4 | Improving | 0.6 | 118 | 137 | 142 | 134.6667 | 0.6 | 118 | 137 | 142 | 134.6667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK210 | Project_024_RISK210 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Performance impacts regualotory complaince | Person_534 | 2016-06-22 | 2017-02-19 01:00 | 0.3 | 1.2271 | 0.50311 | Accept | 0.3 | 1.2271 | 0.50311 | H2 | 4 | Stable | 0.7 | 95 | 133 | 156 | 130.5 | 0.7 | 95 | 133 | 156 | 130.5 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK380 | Project_035_RISK380 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Data Throttling Algorithm | Person_699 | 2016-01-03 01:00 | 2016-11-20 01:00 | 0.2 | 2.6071 | 0.52143 | Reduce | 0.2 | 2.6071 | 0.52143 | H3 | 3 | Stable | 0.9 | 91 | 136 | 151 | 131 | 0.4 | 6 | 57 | 70 | 50.6667 | 0 | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK394 | Project_035_RISK394 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Provision of supplier evidence | Person_631 | 2016-02-21 01:00 | 2016-10-21 01:00 | 0.5 | 2.4768 | 1.2384 | -- | 0.5 | 1.2167 | 0.60833 | H2 | 4 | Improving | [10 empty] | 50.8773 | 0 | 0 | 30.5264
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK290 | Project_035_RISK290 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Face-to-Face Arbitration | Person_699 | 2015-01-22 01:00 | 2017-01-21 01:00 | 0.5 | 1.2445 | 0.62224 | -- | 0.2 | 2.303 | 0.46059 | H3 | 3 | Worsening | [10 empty] | -85.0557 | 60 | 0 | -51.0334
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK395 | Project_035_RISK395 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Test area Site Availability | Person_691 | 2016-05-23 | 2016-11-19 01:00 | 0.5 | 3.0417 | 1.5208 | -- | 0.5 | 3.0417 | 1.5208 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK114 | Project_035_RISK114 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Qualification Facilities Availability. | Person_570 | 2015-09-21 01:00 | 2016-08-20 01:00 | 0.61 | 1.2358 | 0.75383 | Reduce | 0.3 | 1.2358 | 0.37073 | H2 | 4 | Stable | 0.8 | 88 | 122 | 151 | 121.1667 | 0.1 | 27 | 59 | 74 | 56.1667 | 0 | 50.8197 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK222 | Project_024_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Testing Extends beyond target completion | Person_351 | 2017-07-21 | 2018-08-21 | 0.2 | 3.1633 | 0.63267 | Accept | 0.2 | 3.1633 | 0.63267 | H2 | 4 | Stable | 0.9 | 116 | 126 | 147 | 127.8333 | 0.9 | 116 | 126 | 147 | 127.8333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.5 | 83 | 137 | 158 | 131.5 | 0.1 | 22 | 57 | 79 | 54.8333 | 25.8065 | 20 | 0 | 15.4839
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-117 | Project_039_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Filters | Person_185 | 2015-01-21 01:00 | 2016-12-19 01:00 | 0.1 | 3.005 | 0.3005 | Reduce | 0.1 | 3.005 | 0.3005 | H3 | 3 | Stable | 0.9 | 90 | 140 | 160 | 135 | 0.3 | 19 | 50 | 78 | 49.5 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK237 | Project_024_RISK237 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer coding standard Compliance | Person_534 | 2017-05-25 | 2017-10-27 01:00 | 0.2 | 1.4882 | 0.44646 | Accept | 0.2 | 1.4882 | 0.44646 | H2 | 4 | Stable | 0.8 | 107 | 139 | 142 | 134.1667 | 0.8 | 107 | 139 | 142 | 134.1667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK198 | Project_024_RISK198 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Spot Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 0.5 | 1.4882 | 0.44646 | Accept | 0.2 | 1.4882 | 0.44646 | H3 | 3 | Worsening | 0.8 | 91 | 125 | 150 | 123.5 | 0.8 | 91 | 125 | 150 | 123.5 | 0 | 60 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-08-20 01:00 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.9 | 106 | 128 | 156 | 129 | 0.3 | 29 | 45 | 60 | 44.8333 | 50 | 28.5714 | 0 | 30
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-02-19 01:00 | 0.5 | 17.2826 | 8.6413 | Reduce | 0.15 | 17.2826 | 2.5924 | H2 | 4 | Improving | 0.8 | 85 | 125 | 145 | 121.6667 | 0.4 | 16 | 41 | 70 | 41.6667 | 0 | 70 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_470 | 2012-11-20 01:00 | 2017-06-22 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.7 | 90 | 128 | 153 | 125.8333 | 0.1 | 15 | 46 | 65 | 44 | 0 | 50 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-04-21 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.4 | 12.6474 | 5.059 | H2 | 4 | Stable | 0.7 | 97 | 129 | 156 | 128.1667 | 0.3 | 18 | 44 | 60 | 42.3333 | 0 | 33.3333 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2017-08-19 01:00 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.7 | 104 | 127 | 146 | 126.3333 | 0.3 | 12 | 40 | 65 | 39.5 | 0 | 50 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target. | Person_482 | 2013-01-07 01:00 | 2017-06-06 | 0.3 | 4.7676 | 1.4303 | Reduce | 0.15 | 4.7676 | 0.71514 | H2 | 4 | Stable | 0.8 | 114 | 130 | 149 | 130.5 | 0.4 | 20 | 55 | 67 | 51.1667 | 0 | 50 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 01:00 | 2017-01-19 01:00 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.5 | 86 | 128 | 145 | 123.8333 | 0.4 | 8 | 59 | 76 | 53.3333 | 0 | 33.3333 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2017-05-21 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Worsening | 0.8 | 86 | 127 | 154 | 124.6667 | 0.1 | 39 | 50 | 68 | 51.1667 | 0 | 57.1429 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-002 | Project_021_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 96 | 137 | 142 | 131 | 0.3 | 19 | 51 | 66 | 48.1667 |  | 66.6667 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H3 | 3 | Stable | 0.6 | 119 | 133 | 160 | 135.1667 | 0.4 | 33 | 48 | 61 | 47.6667 |  | 62.5 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-01-29 01:00 | 0.7 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Worsening | 0.9 | 108 | 129 | 142 | 127.6667 | 0.4 | 7 | 50 | 62 | 44.8333 |  | 28.5714 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-01-29 01:00 | 0.7 | 1.3243 | 0.92704 | Reduce | 0.5 | 1.3243 | 0.66217 | H1 | 5 | Stable | 0.8 | 120 | 133 | 144 | 132.6667 | 0.4 | 36 | 45 | 69 | 47.5 | 0 | 28.5714 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-009 | Project_021_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Config Qualification delays due to insufficient resource | Person_207 | 2016-09-11 01:00 | 2017-01-19 01:00 | 0.2 | 0.41055 | 0.082109 | Reduce | 0.1 | 0.41055 | 0.041055 | H2 | 4 | Improving | 0.6 | 93 | 132 | 160 | 130.1667 | 0.1 | 7 | 58 | 69 | 51.3333 | 0 | 50 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-008 | Project_021_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Config Qualification delays due to equipment/ hardware unreliability | Person_207 | 2016-09-11 01:00 | 2017-01-22 01:00 | 0.5 | 1.3243 | 0.66217 | Reduce | 0.4 | 1.3243 | 0.52974 | H2 | 4 | Stable | 0.5 | 113 | 138 | 145 | 135 | 0.4 | 6 | 55 | 65 | 48.5 | 0 | 20 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-007 | Project_021_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Config Qualification delay due to Major PRs | Person_207 | 2016-09-11 01:00 | 2017-01-22 01:00 | 0.3 | 3.973 | 1.1919 | Reduce | 0.3 | 3.2005 | 0.96015 | H2 | 4 | Stable | 0.5 | 112 | 131 | 147 | 130.5 | 0.3 | 28 | 44 | 66 | 45 | 19.4445 | 0 | 0 | 11.6667
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.6 | 83 | 134 | 153 | 128.6667 | 0.4 | 14 | 52 | 77 | 49.8333 |  | 50 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-005 | Project_021_Risk-005 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Opportunity to accelerate Component Approval through closer working efficiencies | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 0.1 | 0 | 0 | -- | 0.3 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -200 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-004 | Project_021_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.9 | 99 | 134 | 154 | 131.5 | 0.1 | 39 | 56 | 68 | 55.1667 |  | 80 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2017-01-04 01:00 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.6 | 102 | 133 | 157 | 131.8333 | 0.3 | 22 | 54 | 65 | 50.5 |  | 50 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-014 | Project_021_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.9 | 82 | 139 | 145 | 130.5 | 0.2 | 33 | 58 | 65 | 55 |  | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-013 | Project_021_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-09-11 01:00 | 2017-06-29 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.5 | 104 | 130 | 145 | 128.1667 | 0.2 | 36 | 40 | 62 | 43 |  | 66.6667 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-011 | Project_021_Risk-011 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-09-11 01:00 | 2017-03-21 01:00 | 0.4 | 1.1257 | 0.45028 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Improving | 0.9 | 98 | 137 | 151 | 132.8333 | 0.4 | 6 | 54 | 64 | 47.6667 | 7.8429 | 25 | 0 | 4.7058
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Config Qualification delays due to rig unavailability | Person_207 | 2016-09-11 01:00 | 2017-01-22 01:00 | 0.4 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Improving | 0.5 | 103 | 121 | 152 | 123.1667 | 0.2 | 15 | 43 | 64 | 41.8333 |  | 75 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-01-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.5 | 99 | 125 | 159 | 126.3333 | 0.1 | 20 | 53 | 74 | 51 |  | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.8 | 111 | 137 | 152 | 135.1667 | 0.1 | 22 | 42 | 72 | 43.6667 |  | 60 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-016 | Project_021_Risk-016 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 88 | 128 | 153 | 125.5 | 0.2 | 17 | 53 | 67 | 49.3333 |  | 66.6667 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-015 | Project_021_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to technical performance | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.3 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 99 | 135 | 152 | 131.8333 | 0.1 | 37 | 45 | 69 | 47.6667 |  | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-05-21 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.8 | 111 | 128 | 154 | 129.5 | 0.1 | 21 | 54 | 79 | 52.6667 | 7.8429 | 40 | 0 | 4.7058
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R050 | Project_021_Risk-R050 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to failure of Customer modification Telemetry | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 0.2 | 2.5604 | 0.51208 | Reduce | 0.05 | 2.0527 | 0.10264 | H2 | 4 | Improving | 0.9 | 85 | 135 | 157 | 130.3333 | 0.3 | 4 | 45 | 70 | 42.3333 | 19.8277 | 75 | 0 | 11.8966
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R053 | Project_021_Risk-R053 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-02-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.9 | 109 | 131 | 160 | 132.1667 | 0.1 | 2 | 50 | 66 | 44.6667 |  | 60 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 0.02 | 0 | 0 | Reduce | 0.01 | 0 | 0 | H3 | 3 | Stable | 0.7 | 104 | 130 | 148 | 128.6667 | 0.3 | 17 | 55 | 70 | 51.1667 |  | 50 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R051 | Project_021_Risk-R051 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-08-21 01:00 | 2017-01-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Worsening | 0.9 | 80 | 140 | 153 | 132.1667 | 0.2 | 6 | 48 | 72 | 45 |  | 66.6667 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R052 | Project_021_Risk-R052 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.7 | 82 | 126 | 145 | 121.8333 | 0.1 | 9 | 59 | 62 | 51.1667 |  | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R055 | Project_021_Risk-R055 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to lack of personnel resource | Person_174 | 2016-11-20 01:00 | 2017-02-19 01:00 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.9 | 101 | 131 | 159 | 130.6667 | 0.2 | 19 | 49 | 61 | 46 |  | 66.6667 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-01-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 118 | 125 | 157 | 129.1667 | 0.2 | 14 | 56 | 69 | 51.1667 |  | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Worsening | 0.9 | 114 | 135 | 143 | 132.8333 | 0.2 | 21 | 45 | 68 | 44.8333 |  | 66.6667 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-08-06 | 2017-01-04 01:00 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 84 | 134 | 153 | 128.8333 | 0.2 | 1 | 40 | 77 | 39.6667 |  | 80 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2017-01-20 01:00 | 0.3 | 1.076 | 0.32281 | Reduce | 0.05 | 1.076 | 0.053801 | H2 | 4 | Improving | 0.9 | 94 | 137 | 152 | 132.3333 | 0.2 | 37 | 56 | 60 | 53.5 | 0 | 83.3333 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-13 01:00 | 2016-12-20 01:00 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.8 | 85 | 127 | 159 | 125.3333 | 0.2 | 1 | 48 | 64 | 42.8333 | 80 | 66.6667 | 0 | 48
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK199 | Project_024_RISK199 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Strip Mode | Person_448 | 2016-06-23 | 2017-01-19 01:00 | 0.3 | 12.1398 | 8.4978 | Accept | 0.3 | 12.1398 | 8.4978 | H2 | 4 | Stable | 0.8 | 109 | 131 | 144 | 129.5 | 0.8 | 109 | 131 | 144 | 129.5 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-07-21 | 2018-01-20 01:00 | 0.1 | 0.48559 | 0.048559 | Reduce | 0.1 | 0.48559 | 0.048559 | H2 | 4 | Stable | 0.6 | 118 | 125 | 151 | 128.1667 | 0.4 | 19 | 59 | 62 | 52.8333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment environmental failure | Person_289 | 2016-05-23 | 2016-12-02 01:00 | 0.3 | 19.1935 | 0.95968 | Accept | 0.3 | 19.1935 | 0.95968 | H1 | 5 | Improving | 0.6 | 105 | 126 | 145 | 125.6667 | 0.6 | 105 | 126 | 145 | 125.6667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-200 | Project_027_Risk-200 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Sucession Planning for key team members | Person_060 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.2 | 7.3175 | 1.4635 | Reduce | 0.05 | 7.3175 | 0.36588 | H2 | 4 | Stable | 0.8 | 110 | 124 | 148 | 125.6667 | 0.3 | 34 | 52 | 66 | 51.3333 | 0 | 75 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-189 | Project_027_Risk-189 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Major Component obsolescence | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 8.3972 | 2.5191 | Reduce | 0.08 | 8.3972 | 0.67177 | H2 | 4 | Stable | 0.6 | 102 | 134 | 153 | 131.8333 | 0.1 | 7 | 52 | 71 | 47.6667 | 0 | 73.3333 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-201 | Project_027_Risk-201 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Transition into Support | Person_027 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0.5 | 68.3768 | 34.1884 | Reduce | 0.05 | 38.387 | 1.9193 | H2 | 4 | Stable | 0.6 | 120 | 128 | 153 | 130.8333 | 0.4 | 37 | 45 | 63 | 46.6667 | 43.8597 | 90 | 0 | 26.3158
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Retained systems re-design or modification | Person_289 | 2016-08-20 01:00 | 2017-02-19 01:00 | 0.05 | 13.2195 | 1.5863 | Accept | 0.05 | 13.2195 | 1.5863 | H2 | 4 | Improving | 0.5 | 97 | 124 | 153 | 124.3333 | 0.5 | 97 | 124 | 153 | 124.3333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-188 | Project_027_Risk-188 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Unidentified Technical Legacy Issue | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 20.0332 | 2.0033 | Reduce | 0.05 | 20.0332 | 1.0017 | H3 | 3 | Stable | 0.6 | 94 | 134 | 146 | 129.3333 | 0.2 | 21 | 58 | 74 | 54.5 | 0 | 50 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-193 | Project_027_Risk-193 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | A greater number of arising technical queries | Person_110 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 13.7953 | 4.1386 | Reduce | 0.05 | 13.7953 | 0.68977 | H3 | 3 | Stable | 0.7 | 114 | 133 | 155 | 133.5 | 0.2 | 19 | 51 | 71 | 49 | 0 | 83.3333 | 1 | 2.5
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Mission System not compatible with platform systems | Person_289 | 2016-07-21 | 2017-02-19 01:00 | 0.1 | 16.1945 | 1.6195 | Accept | 0.1 | 16.1945 | 1.6195 | H3 | 3 | Stable | 0.5 | 109 | 140 | 152 | 136.8333 | 0.5 | 109 | 140 | 152 | 136.8333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Qual failure | Person_289 | 2016-06-22 | 2016-11-20 01:00 | 0.4 | 35.9878 | 21.5927 | Accept | 0.4 | 15.5947 | 0.77974 | H1 | 5 | Improving | 0.9 | 93 | 128 | 148 | 125.5 | 0.9 | 93 | 128 | 148 | 125.5 | 56.6667 | 0 | 0 | 34
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Additional minor point releases | Person_073 | 2016-05-23 | 2017-08-20 01:00 | 0.5 | 27.5907 | 2.7591 | Accept | 0.5 | 27.5907 | 2.7591 | H1 | 5 | Stable | 0.6 | 86 | 134 | 152 | 129 | 0.6 | 86 | 134 | 152 | 129 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.8 | 8.7765 | 7.0212 | Reduce | 0.45 | 8.7765 | 3.9494 | H1 | 5 | Stable | 0.8 | 100 | 122 | 149 | 122.8333 | 0.1 | 12 | 50 | 78 | 48.3333 | 0 | 43.75 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-20 23:00 | 2016-08-20 23:00 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.7 | 103 | 137 | 152 | 133.8333 | 0.4 | 19 | 43 | 62 | 42.1667 | 0 | 16.6667 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Digital Video Chainredesign | Person_289 | 2016-06-22 | 2016-12-17 01:00 | 0.71 | 7.689 | 2.6911 | Accept | 0.75 | 7.689 | 2.6911 | H1 | 5 | Worsening | 0.5 | 95 | 129 | 142 | 125.5 | 0.5 | 95 | 129 | 142 | 125.5 | 0 | -5.6338 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK189 | Project_024_RISK189 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment integration - Audio and Video recording | Person_289 | 2016-08-20 01:00 | 2017-01-21 01:00 | 0.49 | 5.4336 | 1.3584 | Accept | 0.5 | 5.4336 | 1.3584 | H1 | 5 | Worsening | 0.9 | 99 | 128 | 154 | 127.5 | 0.9 | 99 | 128 | 154 | 127.5 | 0 | -2.0408 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_289 | 2016-05-23 | 2016-12-20 01:00 | 0.4 | 5.126 | 2.563 | Accept | 0.4 | 5.126 | 2.563 | H1 | 5 | Stable | 0.9 | 109 | 136 | 143 | 132.6667 | 0.9 | 109 | 136 | 143 | 132.6667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK194 | Project_024_RISK194 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Performance Models require additional effort | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.25 | 12.815 | 2.563 | Accept | 0.25 | 12.815 | 2.563 | H2 | 4 | Stable | 0.8 | 97 | 127 | 159 | 127.3333 | 0.8 | 97 | 127 | 159 | 127.3333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.6 | 118 | 121 | 145 | 124.5 | 0.2 | 29 | 40 | 71 | 43.3333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK197 | Project_024_RISK197 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Fitness for purpose | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.2 | 0 | 0 | Accept | 0.2 | 0 | 0 | H2 | 4 | Improving | 0.5 | 115 | 125 | 160 | 129.1667 | 0.5 | 115 | 125 | 160 | 129.1667 |  | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 19:00 | 2019-08-20 19:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.9 | 80 | 132 | 144 | 125.3333 | 0.2 | 24 | 51 | 79 | 51.1667 | 83.3333 | 88.8889 | 1 | 52.6667
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.8 | 89 | 121 | 151 | 120.6667 | 0.1 | 20 | 40 | 62 | 40.3333 | 72 | 0 | 0 | 43.2
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.8 | 88 | 121 | 158 | 121.6667 | 0.3 | 17 | 40 | 79 | 42.6667 | 47.7391 | 0 | 0 | 28.6435
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 19:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.9 | 81 | 121 | 149 | 119 | 0.3 | 26 | 43 | 60 | 43 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.6 | 117 | 122 | 160 | 127.5 | 0.2 | 29 | 53 | 74 | 52.5 | 0 | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK004 | Project_004_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2014-11-19 23:00 | 2016-03-20 23:00 | 0.2 | 0.14752 | 0.029504 | Avoid | 0.2 | 0.14752 | 0.029504 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK003 | Project_004_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-05-24 | 2016-03-20 23:00 | 0.2 | 0.060459 | 0.012092 | Avoid | 0.2 | 0.060459 | 0.012092 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK006 | Project_004_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2014-11-18 23:00 | 2016-03-20 23:00 | 0.1 | 0.049978 | 0.0049978 | Avoid | 0.1 | 0.049978 | 0.0049978 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK005 | Project_004_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2014-11-19 23:00 | 2016-03-20 23:00 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK002 | Project_004_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2014-11-19 23:00 | 2016-03-20 23:00 | 0.5 | 0.15317 | 0.076583 | Avoid | 0.5 | 0.15317 | 0.076583 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK007 | Project_004_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-20 23:00 | 2016-03-20 23:00 | 0.2 | 0.15317 | 0.030633 | Reduce | 0.2 | 0.10883 | 0.021765 | H3 | 3 | Stable | 0.8 | 87 | 129 | 157 | 126.6667 | 0.2 | 35 | 50 | 63 | 49.6667 | 28.9481 | 0 | 1 | 17.3689
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-08-20 01:00 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.9 | 112 | 132 | 160 | 133.3333 | 0.2 | 13 | 43 | 74 | 43.1667 | 50 | 28.5714 | 0 | 30
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-02-19 01:00 | 0.5 | 17.2826 | 8.6413 | Reduce | 0.15 | 17.2826 | 2.5924 | H2 | 4 | Improving | 0.7 | 120 | 136 | 159 | 137.1667 | 0.4 | 3 | 40 | 79 | 40.3333 | 0 | 70 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_470 | 2012-11-20 01:00 | 2017-06-22 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.8 | 96 | 140 | 152 | 134.6667 | 0.1 | 34 | 55 | 61 | 52.5 | 0 | 50 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-04-21 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.4 | 12.6474 | 5.059 | H2 | 4 | Stable | 0.9 | 91 | 125 | 150 | 123.5 | 0.4 | 19 | 58 | 63 | 52.3333 | 0 | 33.3333 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2017-08-19 01:00 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.6 | 116 | 128 | 160 | 131.3333 | 0.2 | 23 | 58 | 65 | 53.3333 | 0 | 50 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target. | Person_482 | 2013-01-07 01:00 | 2017-06-06 | 0.3 | 4.7676 | 1.4303 | Reduce | 0.15 | 4.7676 | 0.71514 | H2 | 4 | Stable | 0.9 | 86 | 123 | 157 | 122.5 | 0.1 | 2 | 44 | 63 | 40.1667 | 0 | 50 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 01:00 | 2017-01-19 01:00 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.9 | 116 | 139 | 152 | 137.3333 | 0.4 | 32 | 58 | 63 | 54.5 | 0 | 33.3333 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2017-05-21 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Worsening | 0.7 | 89 | 139 | 147 | 132 | 0.1 | 29 | 56 | 62 | 52.5 | 0 | 57.1429 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-002 | Project_021_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.6 | 118 | 123 | 145 | 125.8333 | 0.4 | 5 | 50 | 74 | 46.5 |  | 66.6667 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H3 | 3 | Stable | 0.5 | 80 | 130 | 148 | 124.6667 | 0.2 | 1 | 56 | 72 | 49.5 |  | 62.5 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-01-29 01:00 | 0.7 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Worsening | 0.6 | 82 | 132 | 154 | 127.3333 | 0.2 | 19 | 41 | 66 | 41.5 |  | 57.1429 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-01-29 01:00 | 0.7 | 1.3243 | 0.92704 | Reduce | 0.3 | 1.3243 | 0.3973 | H2 | 4 | Stable | 0.7 | 115 | 133 | 151 | 133 | 0.1 | 39 | 41 | 72 | 45.8333 | 0 | 57.1429 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-009 | Project_021_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Config Qualification delays due to insufficient resource | Person_207 | 2016-09-11 01:00 | 2017-01-19 01:00 | 0.2 | 0.41055 | 0.082109 | Reduce | 0.1 | 0.41055 | 0.041055 | H2 | 4 | Improving | 0.6 | 97 | 134 | 150 | 130.5 | 0.2 | 35 | 47 | 64 | 47.8333 | 0 | 50 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.8 | 89 | 136 | 145 | 129.6667 | 0.3 | 39 | 52 | 78 | 54.1667 |  | 50 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-005 | Project_021_Risk-005 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Opportunity to accelerate Component Approval through closer working efficiencies | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 0.1 | 0 | 0 | -- | 0.3 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -200 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-004 | Project_021_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 102 | 123 | 151 | 124.1667 | 0.1 | 23 | 49 | 62 | 46.8333 |  | 80 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2017-01-04 01:00 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.6 | 113 | 131 | 150 | 131.1667 | 0.1 | 24 | 48 | 77 | 48.8333 |  | 50 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-014 | Project_021_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.6 | 84 | 126 | 152 | 123.3333 | 0.4 | 16 | 59 | 60 | 52 |  | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-013 | Project_021_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-09-11 01:00 | 2017-06-29 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.9 | 90 | 126 | 141 | 122.5 | 0.4 | 34 | 42 | 75 | 46.1667 |  | 66.6667 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-011 | Project_021_Risk-011 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-09-11 01:00 | 2017-03-21 01:00 | 0.4 | 1.1257 | 0.45028 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Improving | 0.9 | 109 | 123 | 150 | 125.1667 | 0.4 | 21 | 59 | 68 | 54.1667 | 7.8429 | 25 | 0 | 4.7058
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Config Qualification delays due to rig unavailability | Person_207 | 2016-09-11 01:00 | 2017-01-22 01:00 | 0.4 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Improving | 0.9 | 99 | 139 | 144 | 133.1667 | 0.2 | 17 | 46 | 77 | 46.3333 |  | 75 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-01-20 01:00 | 0.5 | 0 | 0 | Reduce | 1 | 0 | 0 | H1 | 5 | Stable | 0.6 | 106 | 122 | 145 | 123.1667 | 0.3 | 7 | 55 | 73 | 50 |  | -100 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.8 | 96 | 126 | 160 | 126.6667 | 0.4 | 14 | 50 | 64 | 46.3333 |  | 60 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-016 | Project_021_Risk-016 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 109 | 139 | 160 | 137.5 | 0.2 | 13 | 53 | 66 | 48.5 |  | 66.6667 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-015 | Project_021_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to technical performance | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.3 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 110 | 122 | 142 | 123.3333 | 0.1 | 6 | 58 | 68 | 51 |  | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-05-21 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.8 | 119 | 133 | 150 | 133.5 | 0.2 | 22 | 44 | 69 | 44.5 | 7.8429 | 40 | 0 | 4.7058
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R050 | Project_021_Risk-R050 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to failure of Customer modification Telemetry | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 0.2 | 2.5604 | 0.51208 | Reduce | 0.05 | 2.0527 | 0.10264 | H2 | 4 | Improving | 0.6 | 83 | 125 | 141 | 120.6667 | 0.4 | 5 | 47 | 78 | 45.1667 | 19.8277 | 75 | 0 | 11.8966
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R053 | Project_021_Risk-R053 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-02-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.6 | 117 | 140 | 150 | 137.8333 | 0.2 | 13 | 41 | 79 | 42.6667 |  | 60 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 0.02 | 0 | 0 | Reduce | 0.01 | 0 | 0 | H3 | 3 | Stable | 0.8 | 87 | 137 | 151 | 131 | 0.2 | 20 | 57 | 70 | 53 |  | 50 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R051 | Project_021_Risk-R051 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-08-21 01:00 | 2017-01-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Worsening | 0.6 | 108 | 130 | 145 | 128.8333 | 0.1 | 25 | 53 | 72 | 51.5 |  | 66.6667 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R052 | Project_021_Risk-R052 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.6 | 0 | 0 | H1 | 5 | Stable | 0.8 | 107 | 134 | 141 | 130.6667 | 0.2 | 17 | 41 | 72 | 42.1667 |  | -20 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R055 | Project_021_Risk-R055 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to lack of personnel resource | Person_174 | 2016-11-20 01:00 | 2017-02-19 01:00 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.6 | 84 | 137 | 147 | 129.8333 | 0.4 | 25 | 46 | 65 | 45.6667 |  | 66.6667 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-01-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.7 | 97 | 137 | 155 | 133.3333 | 0.2 | 32 | 53 | 78 | 53.6667 |  | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Worsening | 0.9 | 90 | 130 | 151 | 126.8333 | 0.4 | 20 | 46 | 74 | 46.3333 |  | 66.6667 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-08-06 | 2017-01-04 01:00 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.9 | 97 | 121 | 159 | 123.3333 | 0.2 | 15 | 52 | 68 | 48.5 |  | 80 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2017-03-22 | 0.3 | 1.076 | 0.32281 | Reduce | 0.05 | 1.076 | 0.053801 | H2 | 4 | Improving | 0.9 | 103 | 122 | 147 | 123 | 0.4 | 24 | 42 | 63 | 42.5 | 0 | 83.3333 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-13 01:00 | 2017-03-21 01:00 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.5 | 114 | 125 | 150 | 127.3333 | 0.3 | 10 | 52 | 68 | 47.6667 | 80 | 66.6667 | 0 | 48
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-111 | Project_039_Risk-111 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Maturation results inconclusive | Person_297 | 2016-02-21 | 2017-01-20 | 0.3 | 12.1398 | 8.4978 | Accept | 0.3 | 12.1398 | 8.4978 | H2 | 4 | Stable | 0.5 | 102 | 133 | 143 | 129.5 | 0.5 | 102 | 133 | 143 | 129.5 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-07-21 | 2018-01-20 01:00 | 0.1 | 0.48559 | 0.048559 | Reduce | 0.1 | 0.48559 | 0.048559 | H2 | 4 | Stable | 0.5 | 97 | 131 | 142 | 127.1667 | 0.1 | 39 | 55 | 65 | 54 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-195 | Project_039_Risk-195 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Supply Chain Delays - System Comms, Component, and subsystem | Person_083 | 2016-08-21 | 2017-02-19 | 0.3 | 16.3745 | 8.1873 | Accept | 0.3 | 2.5077 | 0.12538 | H3 | 3 | Worsening | 0.6 | 106 | 132 | 160 | 132.3333 | 0.6 | 106 | 132 | 160 | 132.3333 | 84.6854 | 0 | 0 | 50.8113
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-043 | Project_008_Risk-043 | Opportunitity | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Joint courseware and tech pubs team | Person_280 | 2014-11-21 01:00 | 2017-05-21 | 0.5 | 28.2191 | 14.1096 | -- | 0.8 | 13.2573 | 10.6058 | H1 | 5 | Stable | [10 empty] | 53.0201 | -60 | 0 | 31.8121
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-059 | Project_008_Risk-059 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Project Resource Efficencies | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 0.2 | 21.6852 | 4.337 | -- | 0.2 | 21.6852 | 4.337 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 0.5 | 15.8141 | 3.9535 | Accept | 0.5 | 15.8141 | 3.9535 | H2 | 4 | Stable | 0.5 | 109 | 136 | 158 | 135.1667 | 0.5 | 109 | 136 | 158 | 135.1667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 0.5 | 71.0212 | 21.3064 | Accept | 0.5 | 71.0212 | 21.3064 | H2 | 4 | Stable | 0.8 | 108 | 136 | 142 | 132.3333 | 0.8 | 108 | 136 | 142 | 132.3333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-116 | Project_011_Risk-116 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Delays to Qualification | Person_147 | 2017-04-22 | 2017-08-19 01:00 | 0.25 | 1.7297 | 0.43243 | -- | 0.25 | 1.7297 | 0.43243 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-104 | Project_011_Risk-104 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer delayed in providing Custeomr Furnished Equipment | Person_147 | 2016-06-23 | 2017-04-21 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.6 | 118 | 131 | 146 | 131.3333 | 0.4 | 31 | 57 | 63 | 53.6667 |  | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 0.30685 | 0.06137 | Accept | 0.5 | 0.30685 | 0.06137 | H2 | 4 | Stable | 0.7 | 81 | 124 | 148 | 120.8333 | 0.7 | 81 | 124 | 148 | 120.8333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 0.3 | 0.51931 | 0.15579 | -- | 0.15 | 0.51931 | 0.077897 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 0.2 | 0.55005 | 0.11001 | Avoid | 0.2 | 0.55005 | 0.11001 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-123 | Project_011_Risk-123 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | No Requirement for Delta acceptance | Person_187 | 2017-06-23 | 2017-08-20 01:00 | 0.2 | 0.63074 | 0.12615 | -- | 0.2 | 0.63074 | 0.12615 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2016-07-21 | 2017-02-19 01:00 | 0.15 | 0.28639 | 0.042959 | -- | 0.15 | 0.28639 | 0.042959 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-04-21 | 0.2 | 0.24207 | 0.048414 | -- | 0.2 | 0.24207 | 0.048414 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 0.2 | 1.661 | 0.33219 | Reduce | 0.2 | 1.661 | 0.33219 | H2 | 4 | Stable | 0.7 | 99 | 127 | 153 | 126.6667 | 0.4 | 2 | 45 | 70 | 42 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2017-10-21 01:00 | 2018-08-21 | 0.4 | 1.2444 | 0.49778 | Reduce | 0.4 | 1.2444 | 0.49778 | H2 | 4 | Stable | 0.5 | 106 | 132 | 157 | 131.8333 | 0.4 | 3 | 47 | 62 | 42.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 01:00 | 2018-08-21 | 0.45 | 0.83883 | 0.37747 | Reduce | 0.45 | 0.83883 | 0.37747 | H2 | 4 | Stable | 0.8 | 109 | 132 | 155 | 132 | 0.4 | 17 | 40 | 75 | 42 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 01:00 | 2016-11-20 01:00 | 0.25 | 0.33412 | 0.15036 | Accept | 0.1 | 0.33412 | 0.15036 | H3 | 3 | Stable | 0.8 | 106 | 125 | 154 | 126.6667 | 0.8 | 106 | 125 | 154 | 126.6667 | 0 | 60 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-010 | Project_011_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Rework required following integration of Customer System | Person_142 | 2013-08-21 01:00 | 2017-04-21 | 0.4 | 0.66881 | 0.26753 | Reduce | 0.4 | 0.66881 | 0.26753 | H2 | 4 | Stable | 0.8 | 96 | 131 | 158 | 129.6667 | 0.4 | 32 | 54 | 64 | 52 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-20 01:00 | 0.25 | 0.098873 | 0.0098873 | Accept | 0.15 | 0.098873 | 0.0098873 | H3 | 3 | Stable | 0.6 | 94 | 133 | 152 | 129.6667 | 0.6 | 94 | 133 | 152 | 129.6667 | 0 | 40 | 1 | 1.2
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-02-20 01:00 | 2018-08-21 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.7 | 94 | 129 | 146 | 126 | 0.3 | 21 | 43 | 67 | 43.3333 |  | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Pick up and Drop off of Software Resource | Person_230 | 2017-04-21 | 2018-02-19 01:00 | 0.4 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-109 | Project_011_Risk-109 | Opportunitity | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Environment complexity | Person_187 | 2016-07-21 | 2018-08-21 | 0.25 | 0.14661 | 0.036651 | -- | 0.25 | 0.14661 | 0.036651 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-108 | Project_011_Risk-108 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Offer additional functionality to the customer | Person_147 | 2017-04-22 | 2018-08-21 | 0.1 | 0.34094 | 0.034094 | -- | 0.1 | 0.34094 | 0.034094 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 0.2 | 0.12388 | 0.024775 | Reduce | 0.2 | 0.12388 | 0.024775 | H2 | 4 | Stable | 0.8 | 107 | 129 | 151 | 129 | 0.4 | 34 | 54 | 78 | 54.6667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 0.4 | 0.51141 | 0.20457 | Avoid | 0.4 | 0.51141 | 0.20457 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.2 | 0.10171 | 0.020343 | -- | 0.2 | 0.10171 | 0.020343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 0.3 | 0.28639 | 0.085917 | Reduce | 0.3 | 0.28639 | 0.085917 | H2 | 4 | Stable | 0.7 | 112 | 132 | 145 | 130.8333 | 0.2 | 12 | 53 | 70 | 49 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 2. Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 0.25 | 0 | 0 | -- | 0.25 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2017-10-21 01:00 | 2018-05-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 0.3 | 0.10626 | 0.031878 | -- | 0.3 | 0.01932 | 0.005796 | H3 | 3 | Stable | [10 empty] | 81.8181 | 0 | 0 | 49.0909
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK118 | Project_037_RISK118 | Threat | Management Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Product does not deliver the inputs/depdencies required by the Project by the req'd dates | Person_330 | 2015-02-23 22:00 | 2016-06-23 | 0.4 | 1.0052 | 0.35182 | Accept | 0.4 | 1.0052 | 0.35182 | H2 | 4 | Worsening | 0.7 | 95 | 140 | 145 | 133.3333 | 0.7 | 95 | 140 | 145 | 133.3333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-118 | Project_011_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer change environment | Person_187 | 2013-08-21 01:00 | 2018-08-21 | 0.1 | 0 | 0 | Avoid | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk010 | Project_002_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability | Person_357 | 2014-06-14 | 2016-08-07 | 0.1 | 1.8788 | 0.28182 | Accept | 0.1 | 1.8788 | 0.28182 | H3 | 3 | Worsening | 0.5 | 97 | 138 | 159 | 134.6667 | 0.5 | 97 | 138 | 159 | 134.6667 | 0 | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk002 | Project_002_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Transducer Element Failures | Person_650 | 2014-06-04 | 2016-08-07 | 0.5 | 9.3941 | 1.8788 | Accept | 0.25 | 9.3941 | 1.8788 | H2 | 4 | Worsening | 0.6 | 85 | 129 | 154 | 125.8333 | 0.6 | 85 | 129 | 154 | 125.8333 | 0 | 50 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK313 | Project_035_RISK313 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Deployed Performance inadequate | Person_303 | 2015-05-24 | 2016-10-21 01:00 | 0.3 | 1.8788 | 0.18788 | Accept | 0.205 | 1.8788 | 0.18788 | H2 | 4 | Improving | 0.5 | 111 | 140 | 151 | 137 | 0.5 | 111 | 140 | 151 | 137 | 0 | 31.6667 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK308 | Project_035_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Facility performance during Live trials | Person_303 | 2015-05-24 | 2016-10-21 01:00 | 0.3 | 29.4599 | 8.838 | Accept | 0.3 | 18.7882 | 5.6365 | H2 | 4 | Improving | 0.7 | 108 | 129 | 146 | 128.3333 | 0.7 | 108 | 129 | 146 | 128.3333 | 36.2245 | 0 | 0 | 21.7347
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK304 | Project_035_RISK304 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change at Elevation | Person_425 | 2016-09-20 01:00 | 2017-01-20 01:00 | 0.41 | 1.1273 | 0.22546 | Accept | 0.41 | 1.1273 | 0.22546 | H2 | 4 | Stable | 0.8 | 106 | 132 | 155 | 131.5 | 0.8 | 106 | 132 | 155 | 131.5 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK312 | Project_035_RISK312 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Audio Performance inadequate | Person_303 | 2015-06-24 | 2016-10-21 01:00 | 0.2 | 4.7948 | 0.95895 | Accept | 0.2 | 4.7948 | 0.95895 | H3 | 3 | Stable | 0.5 | 86 | 125 | 150 | 122.6667 | 0.5 | 86 | 125 | 150 | 122.6667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-111 | Project_039_Risk-111 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Maturation results inconclusive | Person_297 | 2016-02-21 01:00 | 2017-01-20 01:00 | 0.3 | 0.65759 | 0.098638 | Accept | 0.3 | 0.65759 | 0.098638 | H2 | 4 | Stable | 0.9 | 110 | 140 | 159 | 138.1667 | 0.9 | 110 | 140 | 159 | 138.1667 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-195 | Project_039_Risk-195 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Supply Chain Delays - System Comms, Component, and subsystem | Person_083 | 2016-08-21 01:00 | 2017-02-19 01:00 | 0.3 | 6.7638 | 1.3528 | Accept | 0.3 | 6.7638 | 1.3528 | H3 | 3 | Worsening | 0.6 | 111 | 134 | 150 | 132.8333 | 0.6 | 111 | 134 | 150 | 132.8333 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R017 | Project_021_Risk-R017 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Effort to address Hexavalent Chromium issue is unknown at time of baseline | Person_470 | 2016-02-06 01:00 | 2016-12-20 01:00 | 0.7 | 0 | 0 | Accept | 0.7 | 0 | 0 | H1 | 5 | Stable | 0.7 | 86 | 126 | 149 | 123.1667 | 0.7 | 86 | 126 | 149 | 123.1667 |  | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-194 | Project_027_Risk-194 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | The effect of specialist supplier obsolescence on complex assemblies | Person_074 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.08 | 2.5834 | 0.64585 | Accept | 0.08 | 2.5834 | 0.64585 | H3 | 3 | Stable | 0.9 | 112 | 133 | 149 | 132.1667 | 0.9 | 112 | 133 | 149 | 132.1667 | 0 | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-187 | Project_027_Risk-187 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Loss of a major sub-contractor | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.12 | 9.3941 | 0.93941 | Accept | 0.12 | 9.3941 | 0.93941 | H3 | 3 | Stable | 0.6 | 80 | 124 | 154 | 121.6667 | 0.6 | 80 | 124 | 154 | 121.6667 | 0 | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Governance and Export Rules | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 0.93941 | 0.23485 | Transfer | 0.25 | 0.93941 | 0.23485 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-196 | Project_027_Risk-196 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Aging equipment resulting in increasing failure rates | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 2.1606 | 0.43213 | Accept | 0.1 | 2.1606 | 0.43213 | H3 | 3 | Stable | 0.9 | 113 | 132 | 147 | 131.3333 | 0.9 | 113 | 132 | 147 | 131.3333 | 0 | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R85 | Project_041_R85 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Go to Offshore initiative | Person_468 | 2016-11-19 22:00 | 2018-05-22 | 0.15 | 7.7172 | 1.1576 | -- | 0.15 | 7.7172 | 1.1576 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_368 | 2016-11-19 22:00 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.7 | 118 | 131 | 158 | 133.3333 | 0.3 | 26 | 52 | 63 | 49.5 | 0 | 50 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R43 | Project_041_R43 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Procurement - Component and Supplier Leadtime | Person_468 | 2016-11-19 22:00 | 2018-05-22 | 0.25 | 10.9327 | 2.7332 | Reduce | 0.15 | 10.9327 | 1.6399 | H2 | 4 | Stable | 0.6 | 119 | 127 | 153 | 130 | 0.3 | 9 | 40 | 64 | 38.8333 | 0 | 40 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2016-11-19 22:00 | 2018-05-22 | 0.75 | 10.7184 | 8.0388 | Reduce | 0.75 | 5.3592 | 4.0194 | H1 | 5 | Worsening | 0.5 | 84 | 136 | 158 | 131 | 0.1 | 1 | 59 | 65 | 50.3333 | 50 | 0 | 0 | 30
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R86 | Project_041_R86 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sharing Attrition Stock with Warranty Spares pool | Person_501 | 2016-11-19 22:00 | 2018-05-22 | 0.5 | 3.1083 | 1.5542 | Exploit | 0.5 | 3.1083 | 1.5542 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-185 | Project_027_Risk-185 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier manufacturing issues | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.6 | 1.9722 | 0.98609 | Accept | 0.05 | 1.9722 | 0.98609 | H3 | 3 | Stable | 0.7 | 92 | 121 | 158 | 122.3333 | 0.7 | 92 | 121 | 158 | 122.3333 | 0 | 91.6667 | 1 | 2.75
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-186 | Project_027_Risk-186 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Potential for composite suppliers going out of business | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 2.5081 | 1.2541 | Accept | 0.1 | 2.5081 | 1.2541 | H3 | 3 | Stable | 0.6 | 88 | 129 | 160 | 127.3333 | 0.6 | 88 | 129 | 160 | 127.3333 | 0 | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.35 | 7.0313 | 3.5156 | Accept | 0.35 | 7.0313 | 3.5156 | H3 | 3 | Stable | 0.8 | 95 | 132 | 159 | 130.3333 | 0.8 | 95 | 132 | 159 | 130.3333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2016-11-19 22:00 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.05 | 0.68598 | 0.034299 | H3 | 3 | Stable | 0.8 | 102 | 131 | 159 | 130.8333 | 0.1 | 2 | 54 | 75 | 48.8333 | 0 | 80 | 1 | 2.4
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.25 | 1.2519 | 0.31298 | Accept | 0.25 | 1.2519 | 0.31298 | H3 | 3 | Stable | 0.7 | 81 | 128 | 142 | 122.5 | 0.7 | 81 | 128 | 142 | 122.5 | 0 | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-20 23:00 | 2019-08-20 | 0.5 | 3.7514 | 0.37514 | Accept | 0.5 | 3.7514 | 0.37514 | H2 | 4 | Stable | 0.8 | 85 | 123 | 155 | 122 | 0.8 | 85 | 123 | 155 | 122 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R29 | Project_041_R29 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Attrition | Person_515 | 2016-11-19 22:00 | 2018-05-22 | 0.1 | 3.6014 | 0.36014 | Reduce | 0.05 | 3.6014 | 0.18007 | H3 | 3 | Stable | 0.9 | 109 | 133 | 159 | 133.3333 | 0.4 | 27 | 42 | 69 | 44 | 0 | 50 | 1 | 1.5
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2016-11-19 22:00 | 2017-07-21 | 0.1 | 21.8655 | 2.1865 | Reduce | 0.05 | 21.8655 | 1.0933 | H2 | 4 | Stable | 0.6 | 96 | 127 | 143 | 124.5 | 0.4 | 10 | 50 | 68 | 46.3333 | 0 | 50 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2016-11-19 22:00 | 2018-05-22 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Stable | 0.8 | 89 | 139 | 154 | 133.1667 | 0.3 | 19 | 43 | 75 | 44.3333 | 0 | 60 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.2 | 0.6088 | 0.1522 | Accept | 0.2 | 0.6088 | 0.1522 | H3 | 3 | Stable | 0.5 | 117 | 121 | 159 | 126.6667 | 0.5 | 117 | 121 | 159 | 126.6667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Unidentified Change Requests | Person_693 | 2016-11-19 22:00 | 2017-09-19 22:00 | 0.5 | 1.2005 | 0.60023 | Reduce | 0.1 | 0.51019 | 0.051019 | H3 | 3 | Stable | 0.8 | 85 | 121 | 150 | 119.8333 | 0.2 | 28 | 47 | 73 | 48.1667 | 57.5001 | 80 | 1 | 36.9001
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 0.61 | 3.3227 | 0.83067 | Accept | 0.61 | 3.3227 | 0.83067 | H1 | 5 | Stable | 0.6 | 92 | 128 | 153 | 126.1667 | 0.6 | 92 | 128 | 153 | 126.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_468 | 2016-11-19 22:00 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.1 | 0.77172 | 0.077172 | H3 | 3 | Stable | 0.6 | 117 | 138 | 153 | 137 | 0.4 | 30 | 57 | 70 | 54.6667 | 0 | 60 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production or Engineering | Person_359 | 2016-11-19 22:00 | 2018-05-22 | 0.15 | 1.1576 | 0.17364 | Reduce | 0.1 | 1.1576 | 0.11576 | H3 | 3 | Stable | 0.5 | 114 | 129 | 157 | 131.1667 | 0.2 | 23 | 57 | 60 | 51.8333 | 0 | 33.3333 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R13 | Project_041_R13 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Loss of key personnel | Person_359 | 2016-11-19 22:00 | 2017-08-19 22:00 | 0.5 | 0.59165 | 0.29583 | Reduce | 0.1 | 0.59165 | 0.059165 | H3 | 3 | Stable | 0.9 | 99 | 127 | 152 | 126.5 | 0.2 | 14 | 45 | 70 | 44 | 0 | 80 | 1 | 2.4
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_468 | 2016-11-19 22:00 | 2018-11-19 22:00 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.1 | 6.431 | 0.6431 | H3 | 3 | Stable | 0.7 | 112 | 126 | 148 | 127.3333 | 0.4 | 22 | 47 | 73 | 47.1667 | -47.0588 | 33.3333 | 1 | -27.2353
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R81 | Project_041_R81 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Re-imaging of PC's - additional material | Person_515 | 2016-11-19 22:00 | 2017-10-20 22:00 | 0.5 | 0.21008 | 0.10504 | Avoid | 0.5 | 0.21008 | 0.10504 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK004 | Project_010_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Export License | Person_359 | 2015-02-18 | 2017-08-20 | 0.8 | 0.18482 | 0.14786 | Reduce | 0.8 | 0.18482 | 0.14786 | H1 | 5 | Improving | 0.7 | 103 | 126 | 143 | 125 | 0.4 | 30 | 57 | 79 | 56.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.6 | 96 | 135 | 148 | 130.6667 | 0.4 | 12 | 52 | 60 | 46.6667 | 0 | 40 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 | 0.7 | 0.92411 | 0.64688 | Reduce | 0.3 | 0.36965 | 0.11089 | H2 | 4 | Stable | 0.8 | 95 | 133 | 156 | 130.5 | 0.4 | 32 | 55 | 70 | 53.6667 | 60 | 57.1429 | 0 | 36
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 | 2016-04-21 | 0.5 | 4.0661 | 2.033 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.6 | 84 | 128 | 150 | 124.3333 | 0.3 | 3 | 58 | 60 | 49.1667 | 0 | 90 | 1 | 2.7
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.3 | 0.46206 | 0.13862 | H2 | 4 | Improving | 0.8 | 80 | 135 | 159 | 129.8333 | 0.4 | 34 | 43 | 77 | 47.1667 | 58.3333 | 50 | 0 | 35
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R017 | Project_021_Risk-R017 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Effort to address Hexavalent Chromium issue is unknown at time of baseline | Person_470 | 2016-02-06 01:00 | 2016-12-20 01:00 | 0.7 | 1.1089 | 0.88715 | Accept | 0.7 | 0.73929 | 0.44357 | H1 | 5 | Stable | 0.9 | 120 | 123 | 160 | 128.6667 | 0.9 | 120 | 123 | 160 | 128.6667 | 33.3333 | 0 | 0 | 20
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 | 2017-08-20 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.6 | 104 | 129 | 152 | 128.6667 | 0.1 | 32 | 54 | 64 | 52 | 0 | 50 | 1 | 1.5
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.9 | 91 | 134 | 156 | 130.5 | 0.3 | 9 | 50 | 76 | 47.5 | 0 | 25 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Stable | 0.6 | 107 | 121 | 147 | 123 | 0.1 | 27 | 40 | 66 | 42.1667 | 0 | 40 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Worsening | [10 empty] | 0 | 37.5 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-034 | Project_005_Risk-034 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project delay causes cost impact to project | Person_470 | 2011-12-02 01:00 | 2017-01-20 01:00 | 0.5 | 3.6965 | 0.36965 | Accept | 0.05 | 3.6965 | 0.36965 | H3 | 3 | Stable | 0.9 | 116 | 121 | 143 | 123.8333 | 0.9 | 116 | 121 | 143 | 123.8333 | 0 | 90 | 1 | 2.7
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 0.45 | 0.92411 | 0.18482 | Accept | 0.45 | 0.92411 | 0.18482 | H2 | 4 | Stable | 0.9 | 109 | 128 | 143 | 127.3333 | 0.9 | 109 | 128 | 143 | 127.3333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 0.3 | 1.8482 | 0.55447 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.8 | 91 | 127 | 144 | 123.8333 | 0.2 | 30 | 51 | 67 | 50.1667 | 0 | 33.3333 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.5 | 119 | 124 | 154 | 128.1667 | 0.3 | 32 | 52 | 64 | 50.6667 | 90 | 75 | 1 | 56.25
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.41 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -2.5 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.61 | 0.25667 | 0.15657 | Reduce | 0.5 | 0.25667 | 0.12834 | H2 | 4 | Stable | 0.8 | 106 | 140 | 147 | 135.5 | 0.3 | 30 | 58 | 74 | 56 | 0 | 18.0328 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2014-01-21 01:00 | 2017-11-20 01:00 | 0.4 | 1.078 | 0.43121 | Reduce | 0.4 | 1.4673 | 0.58692 | H2 | 4 | Improving | 0.6 | 116 | 140 | 154 | 138.3333 | 0.1 | 13 | 50 | 76 | 48.1667 | -36.1112 | 0 | 0 | -21.6667
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-118 | Project_029_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Acceptance Schedule is longer in duration/delayed due to unplanned events. [Hardware availability] | Person_102 | 2017-01-21 01:00 | 2017-05-23 | 0.55 | 1.3775 | 0.75761 | Reduce | 0.55 | 1.3775 | 0.75761 | H2 | 4 | Stable | 0.9 | 111 | 123 | 153 | 126 | 0.4 | 5 | 46 | 69 | 43 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2017-11-19 01:00 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2017-05-23 | 0.6 | 0.89835 | 0.53901 | Transfer | 0.6 | 0.89835 | 0.53901 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 0.35 | 0.85557 | 0.29945 | Reduce | 0.35 | 1.9208 | 0.67227 | H2 | 4 | Stable | 0.9 | 102 | 135 | 154 | 132.6667 | 0.2 | 26 | 57 | 78 | 55.3333 | -124.5001 | 0 | 0 | -74.7001
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-060 | Project_005_Risk-060 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Technical Acceptance may be more difficult than anticipated | Person_470 | 2014-06-11 | 2017-01-20 01:00 | 0.5 | 0.77001 | 0.30801 | Accept | 0.05 | 0.77001 | 0.231 | H3 | 3 | Stable | 0.8 | 105 | 133 | 142 | 129.8333 | 0.8 | 105 | 133 | 142 | 129.8333 | 0 | 90 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2018-02-20 01:00 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.7 | 116 | 138 | 145 | 135.5 | 0.1 | 18 | 52 | 73 | 49.8333 | 0 | 28.5714 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation | Person_565 | 2018-05-22 | 2018-08-21 | 0.25 | 1.54 | 0.30801 | Accept | 0.25 | 0.77001 | 0.154 | H3 | 3 | Stable | 0.9 | 107 | 130 | 148 | 129.1667 | 0.9 | 107 | 130 | 148 | 129.1667 | 50 | 0 | 0 | 30
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 0.2 | 27.1644 | 0.81493 | Accept | 0.2 | 12.8336 | 1.2834 | H2 | 4 | Stable | 0.5 | 98 | 128 | 156 | 127.6667 | 0.5 | 98 | 128 | 156 | 127.6667 | 52.7559 | 0 | 0 | 31.6535
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2014-07-22 | 2017-11-19 01:00 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.6 | 89 | 138 | 153 | 132.3333 | 0.1 | 29 | 45 | 62 | 45.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2017-10-14 01:00 | 0.41 | 6.4168 | 2.6309 | Transfer | 0.41 | 0 | 0 | H1 | 5 | Stable | [10 empty] | 100 | 0 | 0 | 60
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub-system FPGA | Person_216 | 2017-01-21 01:00 | 2017-08-20 01:00 | 0.3 | 1.54 | 0.46201 | Reduce | 0.4 | 1.5914 | 0.63655 | H2 | 4 | Stable | 0.9 | 94 | 136 | 160 | 133 | 0.3 | 37 | 47 | 72 | 49.5 | -3.3333 | -33.3333 | 0 | -2
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SystemC HW/SW | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.3 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.8 | 94 | 139 | 149 | 133.1667 | 0.2 | 21 | 47 | 70 | 46.5 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs [technical scope] | Person_466 | 2017-01-21 01:00 | 2019-07-21 | 0.35 | 9.505 | 3.3267 | Reduce | 0.35 | 9.505 | 3.3267 | H2 | 4 | Stable | 0.5 | 98 | 121 | 156 | 123 | 0.3 | 38 | 52 | 60 | 51 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.5 | 3.5934 | 1.7967 | H2 | 4 | Stable | 0.7 | 91 | 122 | 153 | 122 | 0.1 | 25 | 49 | 77 | 49.6667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | HW - additional unplanned design effort | Person_216 | 2016-05-23 | 2019-10-21 01:00 | 0.4 | 3.3367 | 1.3347 | Reduce | 0.4 | 3.3367 | 1.3347 | H2 | 4 | Stable | 0.9 | 110 | 122 | 143 | 123.5 | 0.3 | 23 | 49 | 72 | 48.5 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design | Person_216 | 2016-05-23 | 2017-07-20 | 0.2 | 2.6951 | 0.53901 | Reduce | 0.2 | 2.6951 | 0.53901 | H3 | 3 | Improving | 0.8 | 116 | 133 | 146 | 132.3333 | 0.4 | 7 | 40 | 74 | 40.1667 | 0 | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_692 | 2016-12-21 01:00 | 2017-12-19 01:00 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Stable | 0.9 | 88 | 134 | 153 | 129.5 | 0.4 | 10 | 40 | 74 | 40.6667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_692 | 2017-05-23 | 2019-07-21 | 0.333 | 11.5502 | 3.8462 | Reduce | 0.333 | 11.5502 | 3.8462 | H2 | 4 | Stable | 0.9 | 80 | 130 | 159 | 126.5 | 0.3 | 2 | 45 | 60 | 40.3333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-22 01:00 | 2017-05-22 | 0.25 | 7.4225 | 1.8556 | Reduce | 0.1 | 2.0081 | 0.20081 | H3 | 3 | Stable | 0.7 | 85 | 131 | 157 | 127.6667 | 0.4 | 19 | 46 | 72 | 45.8333 | 72.9455 | 60 | 0 | 43.7673
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 2.6991 | 1.0796 | H2 | 4 | Stable | 0.9 | 98 | 133 | 145 | 129.1667 | 0.4 | 7 | 40 | 77 | 40.6667 | 31.8182 | 20 | 0 | 19.0909
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 0.25 | 18.069 | 1.8069 | Accept | 0.25 | 11.3212 | 1.1321 | H3 | 3 | Stable | 0.8 | 89 | 127 | 149 | 124.3333 | 0.8 | 89 | 127 | 149 | 124.3333 | 37.3444 | 0 | 0 | 22.4066
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_575 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 5.0983 | 0.76474 | H3 | 3 | Stable | 0.7 | 109 | 129 | 150 | 129.1667 | 0.4 | 8 | 57 | 62 | 49.6667 | 19.0479 | 70 | 1 | 13.5287
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-148 | Project_020_Risk-148 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs non-available items | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.3 | 14.9935 | 4.498 | Reduce | 0.3 | 14.9935 | 4.498 | H2 | 4 | Stable | 0.7 | 116 | 124 | 149 | 126.8333 | 0.1 | 24 | 50 | 78 | 50.3333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | More issues than expected during Qualification | Person_147 | 2017-04-22 | 2017-11-04 01:00 | 0.35 | 18.6688 | 3.7338 | Accept | 0.35 | 18.6688 | 3.7338 | H1 | 5 | Stable | 0.7 | 96 | 121 | 147 | 121.1667 | 0.7 | 96 | 121 | 147 | 121.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-147 | Project_020_Risk-147 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component taking longer to refurbish in country | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.6 | 6.7477 | 4.0486 | Reduce | 0.6 | 6.7477 | 4.0486 | H2 | 4 | Stable | 0.9 | 81 | 139 | 150 | 131.1667 | 0.1 | 12 | 58 | 60 | 50.6667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-150 | Project_020_Risk-150 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Power supply Test Environment | Person_248 | 2016-10-21 01:00 | 2017-05-22 | 0.6 | 6.7477 | 4.0486 | Reduce | 0.6 | 6.7477 | 4.0486 | H2 | 4 | Worsening | 0.8 | 88 | 135 | 149 | 129.5 | 0.2 | 38 | 50 | 62 | 50 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2017-04-21 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.35 | 2.9061 | 1.0171 | H2 | 4 | Stable | 0.5 | 113 | 137 | 159 | 136.6667 | 0.4 | 37 | 47 | 64 | 48.1667 | 21.0126 | 56.25 | 0 | 12.6076
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Suppliers | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 2.3975 | 2.3975 | Accept | 0.15 | 14.8583 | 14.8583 | H2 | 4 | Stable | 0.6 | 102 | 129 | 151 | 128.1667 | 0.6 | 102 | 129 | 151 | 128.1667 | -519.7413 | 0 | 0 | -311.8448
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2017-04-21 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 0.65554 | 0.52443 | H2 | 4 | Stable | [10 empty] | 80.45 | 0 | 0 | 48.27
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 3.8666 | 1.5853 | Accept | 0.2 | 1.3288 | 0.5448 | H2 | 4 | Stable | 0.5 | 113 | 135 | 155 | 134.6667 | 0.5 | 113 | 135 | 155 | 134.6667 | 65.6338 | 0 | 0 | 39.3803
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2017-03-22 | 0.85 | 25.2325 | 21.4476 | Avoid | 0.08 | 20.8758 | 1.6701 | H2 | 4 | Stable | [10 empty] | 17.2662 | 90.5882 | 0 | 10.3597
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Local customer Engineers in country | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 5.4459 | 1.6338 | Accept | 0.1 | 0.18151 | 0.054453 | H2 | 4 | Stable | 0.9 | 120 | 137 | 160 | 138 | 0.9 | 120 | 137 | 160 | 138 | 96.667 | 0 | 0 | 58.0002
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2017-03-22 | 0.7 | 24.1887 | 16.9321 | Reduce | 0.25 | 4.3567 | 1.0892 | H2 | 4 | Stable | 0.7 | 114 | 132 | 157 | 133.1667 | 0.1 | 3 | 45 | 72 | 42.5 | 81.9887 | 64.2857 | 0 | 49.1932
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence | Person_455 | 2016-05-23 | 2020-05-23 | 0.3 | 13.3529 | 6.6765 | Accept | 0.3 | 13.3529 | 6.6765 | H2 | 4 | Stable | 0.9 | 119 | 125 | 156 | 129.1667 | 0.9 | 119 | 125 | 156 | 129.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 0.5 | 9.2728 | 4.6364 | Reduce | 0.3 | 9.2728 | 2.7819 | H2 | 4 | Stable | 0.5 | 83 | 122 | 159 | 121.6667 | 0.1 | 37 | 55 | 67 | 54 | 0 | 40 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 0.3 | 8.7814 | 2.6344 | Reduce | 0.15 | 8.7832 | 1.3175 | H3 | 3 | Stable | 0.5 | 102 | 140 | 143 | 134.1667 | 0.4 | 28 | 48 | 73 | 48.8333 | -0.021119 | 50 | 0 | -0.012672
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Consumables | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 108.3186 | 32.4956 | Accept | 0.2 | 108.3186 | 32.4956 | H2 | 4 | Stable | 0.6 | 89 | 135 | 153 | 130.3333 | 0.6 | 89 | 135 | 153 | 130.3333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Delay of processing | Person_306 | 2016-01-13 01:00 | 2019-08-21 01:00 | 0.15 | 26.3497 | 3.9525 | Reduce | 0.15 | 13.1767 | 1.9765 | H3 | 3 | Stable | 0.6 | 91 | 126 | 156 | 125.1667 | 0.1 | 29 | 59 | 68 | 55.5 | 49.993 | 0 | 1 | 29.9958
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 7. Finance | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 12.0547 | 2.4109 | Accept | 0.2 | 12.0547 | 2.4109 | H2 | 4 | Stable | 0.7 | 114 | 140 | 145 | 136.5 | 0.7 | 114 | 140 | 145 | 136.5 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 17.0765 | 1.7076 | Accept | 0.15 | 17.0765 | 1.7076 | H2 | 4 | Stable | 0.6 | 96 | 140 | 147 | 133.8333 | 0.6 | 96 | 140 | 147 | 133.8333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.7 | 105 | 127 | 147 | 126.6667 | 0.2 | 17 | 49 | 61 | 45.6667 | 0 | 60 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 50.7895 | 40.6316 | Accept | 0.2 | 50.7895 | 40.6316 | H2 | 4 | Stable | 0.6 | 120 | 139 | 145 | 136.8333 | 0.6 | 120 | 139 | 145 | 136.8333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK201 | Project_024_RISK201 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Indication mode failure | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.25 | 1.6835 | 0.42087 | Reduce | 0.2 | 1.6835 | 0.33669 | H3 | 3 | Stable | 0.8 | 94 | 125 | 155 | 124.8333 | 0.3 | 28 | 51 | 70 | 50.3333 | 0 | 20 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport Routes | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 22.8501 | 6.855 | Accept | 0.15 | 22.8501 | 6.855 | H2 | 4 | Stable | 0.5 | 106 | 127 | 152 | 127.6667 | 0.5 | 106 | 127 | 152 | 127.6667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK286 | Project_024_RISK286 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Requirement sell off more difficult than expected | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 10.1787 | 5.0893 | Reduce | 0.5 | 10.1787 | 5.0893 | H1 | 5 | Worsening | 0.7 | 110 | 128 | 141 | 127.1667 | 0.2 | 26 | 52 | 75 | 51.5 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK288 | Project_024_RISK288 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Unplanned obsolescence and/or repairs to rig assets. | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.6 | 5.8424 | 3.5054 | Reduce | 0.6 | 4.9768 | 2.9861 | H1 | 5 | Stable | 0.8 | 99 | 122 | 147 | 122.3333 | 0.2 | 15 | 49 | 71 | 47 | 14.8148 | 0 | 0 | 8.8889
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Internal Quality Issues | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 1.3502 | 0.47258 | Accept | 0.2 | 2.2677 | 0.79369 | H2 | 4 | Stable | 0.7 | 82 | 130 | 143 | 124.1667 | 0.7 | 82 | 130 | 143 | 124.1667 | -67.9487 | 0 | 0 | -40.7692
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk017 | Project_042_Risk017 | Threat | Financial Contingency | Open | H2 | 4 | 6. Contractual/Legal | Liquidated Damages | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 19.9938 | 5.9981 | Accept | 0.4 | 19.9938 | 5.9981 | H2 | 4 | Stable | 0.8 | 118 | 124 | 148 | 127 | 0.8 | 118 | 124 | 148 | 127 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.5 | 3.843 | 1.9215 | H1 | 5 | Stable | 0.6 | 84 | 128 | 153 | 124.8333 | 0.1 | 1 | 59 | 65 | 50.3333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Repairs | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 19.4745 | 5.8424 | Accept | 0.25 | 19.4745 | 5.8424 | H2 | 4 | Stable | 0.5 | 93 | 140 | 155 | 134.6667 | 0.5 | 93 | 140 | 155 | 134.6667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Overland performance | Person_448 | 2016-06-23 | 2017-05-21 | 0.1 | 1.6835 | 0.16835 | Reduce | 0.1 | 3.5011 | 0.35011 | H3 | 3 | Improving | 0.6 | 91 | 130 | 156 | 127.8333 | 0.2 | 16 | 42 | 75 | 43.1667 | -107.9692 | 0 | 1 | -64.7815
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk016 | Project_042_Risk016 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport/Delivery Speed | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 2.7146 | 2.7146 | Accept | 0.1 | 2.7146 | 2.7146 | H2 | 4 | Stable | 0.7 | 102 | 127 | 159 | 128.1667 | 0.7 | 102 | 127 | 159 | 128.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Country Stability | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 8.5688 | 4.2844 | Accept | 0.4 | 8.5688 | 4.2844 | H2 | 4 | Stable | 0.9 | 93 | 140 | 154 | 134.5 | 0.9 | 93 | 140 | 154 | 134.5 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 30.562 | 24.4496 | Accept | 0.1 | 30.562 | 24.4496 | H2 | 4 | Stable | 0.8 | 99 | 131 | 141 | 127.3333 | 0.8 | 99 | 131 | 141 | 127.3333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK213 | Project_024_RISK213 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Rigs requireaccreditation as "Special to Type" Test equipment | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.3 | 38.17 | 11.451 | Reduce | 0.25 | 19.4745 | 4.8686 | H2 | 4 | Stable | 0.5 | 104 | 122 | 143 | 122.5 | 0.1 | 12 | 44 | 73 | 43.5 | 48.9796 | 16.6667 | 0 | 29.3878
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 68.1262 | 6.8126 | Accept | 0.2 | 68.1262 | 6.8126 | H2 | 4 | Stable | 0.9 | 80 | 127 | 158 | 124.3333 | 0.9 | 80 | 127 | 158 | 124.3333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Risk of repeat component Tests | Person_515 | 2017-12-20 22:00 | 2019-01-20 22:00 | 0.5 | 90.8811 | 13.6322 | Accept | 0.5 | 90.8811 | 13.6322 | H2 | 4 | Stable | 0.9 | 90 | 123 | 151 | 122.1667 | 0.9 | 90 | 123 | 151 | 122.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_515 | 2017-05-23 | 2019-01-20 22:00 | 0.5 | 4.847 | 1.4541 | Accept | 0.5 | 4.847 | 1.4541 | H2 | 4 | Stable | 0.8 | 111 | 137 | 160 | 136.5 | 0.8 | 111 | 137 | 160 | 136.5 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK219 | Project_024_RISK219 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | STTE additional work | Person_289 | 2016-09-20 01:00 | 2017-07-21 | 0.5 | 15.0863 | 7.5431 | Reduce | 0.5 | 15.0863 | 7.5431 | H1 | 5 | Worsening | 0.7 | 98 | 135 | 157 | 132.5 | 0.1 | 7 | 59 | 79 | 53.6667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK218 | Project_024_RISK218 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | System issues general | Person_388 | 2016-08-21 01:00 | 2017-05-14 | 0.4 | 90.8811 | 36.3524 | Reduce | 0.3 | 39.3904 | 11.8171 | H1 | 5 | Stable | 0.9 | 83 | 137 | 150 | 130.1667 | 0.3 | 5 | 57 | 65 | 49.6667 | 56.6571 | 25 | 0 | 33.9943
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R44 | Project_041_R44 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Procurement - Source Change and cost change | Person_468 | 2016-11-19 22:00 | 2018-05-22 | 0.5 | 9.8671 | 1.9734 | Accept | 0.5 | 9.8671 | 1.9734 | H1 | 5 | Worsening | 0.8 | 90 | 126 | 145 | 123.1667 | 0.8 | 90 | 126 | 145 | 123.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_368 | 2016-11-19 22:00 | 2017-09-18 22:00 | 0.25 | 15.5796 | 6.2318 | Accept | 0.25 | 15.5796 | 6.2318 | H3 | 3 | Stable | 0.6 | 107 | 121 | 154 | 124.1667 | 0.6 | 107 | 121 | 154 | 124.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_515 | 2016-11-19 22:00 | 2018-05-22 | 0.1 | 11.1654 | 2.2331 | Accept | 0.1 | 12.4637 | 2.4927 | H3 | 3 | Stable | 0.9 | 114 | 123 | 154 | 126.6667 | 0.9 | 114 | 123 | 154 | 126.6667 | -11.6279 | 0 | 1 | -6.9767
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.2 | 20.8767 | 4.1753 | H2 | 4 | Stable | 0.5 | 110 | 134 | 150 | 132.6667 | 0.2 | 38 | 59 | 69 | 57.1667 | 50 | 50 | 0 | 30
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R06 | Project_041_R06 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional PM time to support the supply chain | Person_359 | 2016-11-19 22:00 | 2017-09-18 22:00 | 0.25 | 29.1079 | 19.2112 | Accept | 0.25 | 29.1079 | 14.845 | H3 | 3 | Stable | 0.5 | 83 | 134 | 149 | 128 | 0.5 | 83 | 134 | 149 | 128 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.48165 | 78.4174 | 37.7697 | Reduce | 0.2967 | 59.2155 | 17.5692 | H1 | 5 | Worsening | 0.9 | 106 | 137 | 158 | 135.3333 | 0.2 | 16 | 47 | 63 | 44.5 | 24.4868 | 38.3993 | 0 | 14.6921
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_515 | 2016-11-19 22:00 | 2018-05-22 | 0.25 | 32.4575 | 1.2983 | Accept | 0.25 | 32.4575 | 1.2983 | H2 | 4 | Stable | 0.6 | 119 | 122 | 144 | 125.1667 | 0.6 | 119 | 122 | 144 | 125.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 | 0.05 | 25.966 | 7.7898 | Accept | 0.05 | 22.5039 | 6.7512 | H2 | 4 | Stable | 0.6 | 82 | 131 | 158 | 127.3333 | 0.6 | 82 | 131 | 158 | 127.3333 | 13.3333 | 0 | 0 | 8
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 0.8 | 62.3617 | 3.1181 | Accept | 0.6 | 62.3617 | 3.1181 | H1 | 5 | Stable | 0.8 | 80 | 127 | 148 | 122.6667 | 0.8 | 80 | 127 | 148 | 122.6667 | 0 | 25 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 | 2016-08-20 | 0.1 | 4.5441 | 0.45441 | Accept | 0.1 | 4.5441 | 0.45441 | H2 | 4 | Stable | 0.7 | 97 | 131 | 156 | 129.5 | 0.7 | 97 | 131 | 156 | 129.5 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK179 | Project_024_RISK179 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Testing Required | Person_710 | 2016-12-21 01:00 | 2017-05-22 | 0.5 | 3.5054 | 1.7527 | Reduce | 0.4 | 3.5054 | 1.4022 | H2 | 4 | Stable | 0.7 | 108 | 125 | 152 | 126.6667 | 0.4 | 27 | 44 | 62 | 44.1667 | 0 | 20 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 | 0.2 | 30.2764 | 12.1106 | Accept | 0.2 | 30.2764 | 12.1106 | H3 | 3 | Improving | 0.9 | 82 | 127 | 156 | 124.3333 | 0.9 | 82 | 127 | 156 | 124.3333 | 0 | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2017-02-20 01:00 | 2019-07-21 | 0.4 | 11.9444 | 5.9722 | Accept | 0.3 | 11.9444 | 5.9722 | H2 | 4 | Stable | 0.5 | 115 | 127 | 145 | 128 | 0.5 | 115 | 127 | 145 | 128 | 0 | 25 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK180 | Project_024_RISK180 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | High Accelerated Life Testing (HALT) | Person_289 | 2016-12-21 01:00 | 2017-05-03 | 0.4 | 10.4903 | 4.1961 | Reduce | 0.2 | 10.4903 | 2.0981 | H2 | 4 | Stable | 0.9 | 87 | 130 | 159 | 127.6667 | 0.1 | 17 | 48 | 68 | 46.1667 | 0 | 50 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2019-10-14 01:00 | 0.2 | 35.885 | 25.4784 | Accept | 0.2 | 27.0826 | 20.3119 | H3 | 3 | Stable | 0.6 | 118 | 124 | 152 | 127.6667 | 0.6 | 118 | 124 | 152 | 127.6667 | 24.5297 | 0 | 0 | 14.7178
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-02-20 01:00 | 2019-07-21 | 0.3 | 30.7697 | 15.0772 | Accept | 0.2 | 24.3561 | 12.1781 | H3 | 3 | Stable | 0.7 | 105 | 138 | 148 | 134.1667 | 0.7 | 105 | 138 | 148 | 134.1667 | 20.8439 | 33.3333 | 1 | 13.5063
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 14.541 | 5.8164 | Accept | 0.1 | 14.541 | 5.8164 | H2 | 4 | Stable | 0.6 | 86 | 140 | 160 | 134.3333 | 0.6 | 86 | 140 | 160 | 134.3333 | 0 | -233.3333 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 1.3502 | 0.33756 | Accept | 0.25 | 1.3502 | 0.33756 | H2 | 4 | Stable | 0.6 | 117 | 133 | 149 | 133 | 0.6 | 117 | 133 | 149 | 133 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_073 | 2016-05-23 | 2017-02-19 01:00 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.6 | 90 | 122 | 159 | 122.8333 | 0.3 | 20 | 45 | 74 | 45.6667 | 0 | 50 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_413 | 2015-11-21 01:00 | 2017-05-22 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.6 | 97 | 122 | 142 | 121.1667 | 0.1 | 39 | 47 | 69 | 49.3333 | 0 | 5 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of Batch 2 Re-Design | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 1.1685 | 0.23369 | Accept | 0.3 | 1.1685 | 0.23369 | H2 | 4 | Stable | 0.6 | 83 | 121 | 149 | 119.3333 | 0.6 | 83 | 121 | 149 | 119.3333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.8 | 8.7765 | 7.0212 | Reduce | 0.45 | 8.7765 | 3.9494 | H1 | 5 | Stable | 0.5 | 98 | 122 | 158 | 124 | 0.2 | 24 | 40 | 61 | 40.8333 | 0 | 43.75 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.5 | 107 | 136 | 155 | 134.3333 | 0.2 | 24 | 51 | 78 | 51 | 0 | 25 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-149 | Project_020_Risk-149 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs to be returned to UK | Person_703 | 2016-12-21 01:00 | 2017-11-19 01:00 | 0.2 | 0 | 0 | Accept | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.9 | 89 | 138 | 147 | 131.3333 | 0.9 | 89 | 138 | 147 | 131.3333 |  | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2017-03-22 | 0.41 | 3.6174 | 1.8087 | Accept | 0.41 | 3.6172 | 0.72345 | H2 | 4 | Stable | 0.7 | 117 | 134 | 156 | 134.8333 | 0.7 | 117 | 134 | 156 | 134.8333 | 0.0051359 | 0 | 0 | 0.0030815
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-016 | Project_023_Risk-016 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Damage to equipment (Unable to replace due to obsolescence) | Person_703 | 2015-10-22 01:00 | 2017-01-20 01:00 | 0.3 | 2.3503 | 0.47006 | Accept | 0.3 | 2.3503 | 0.47006 | H2 | 4 | Stable | 0.6 | 107 | 129 | 144 | 127.8333 | 0.6 | 107 | 129 | 144 | 127.8333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 0.5 | 4.4768 | 2.2384 | Accept | 0.5 | 4.4768 | 2.2384 | H2 | 4 | Improving | 0.9 | 82 | 137 | 160 | 131.6667 | 0.9 | 82 | 137 | 160 | 131.6667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 0.3 | 244.3581 | 12.2179 | Accept | 0.3 | 227.5702 | 11.3785 | H2 | 4 | Stable | 0.9 | 87 | 135 | 150 | 129.5 | 0.9 | 87 | 135 | 150 | 129.5 | 6.8702 | 0 | 0 | 4.1221
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2017-02-20 01:00 | 2018-05-22 | 0.1 | 60.4367 | 3.0218 | Accept | 0.1 | 60.4367 | 3.0218 | H3 | 3 | Stable | 0.6 | 112 | 140 | 151 | 137.1667 | 0.6 | 112 | 140 | 151 | 137.1667 | 0 | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 17:00 | 2019-08-20 17:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 17:00 | 2019-08-20 17:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 17:00 | 2019-08-20 17:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 17:00 | 2019-08-20 17:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 17:00 | 2019-08-20 17:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 0.3 | 4.0228 | 2.0114 | Accept | 0.3 | 4.0228 | 2.0114 | H2 | 4 | Improving | 0.8 | 110 | 123 | 143 | 124.1667 | 0.8 | 110 | 123 | 143 | 124.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK200 | Project_024_RISK200 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Height Finding | Person_448 | 2016-05-23 | 2017-03-21 01:00 | 0.35 | 7.3646 | 3.6823 | Accept | 0.35 | 7.3646 | 3.6823 | H2 | 4 | Worsening | 0.8 | 99 | 127 | 156 | 127.1667 | 0.8 | 99 | 127 | 156 | 127.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 | 2016-05-21 | 0.5 | 4.3921 | 2.196 | Reduce | 0.3 | 4.3921 | 1.3176 | H1 | 5 | Stable | 0.7 | 117 | 121 | 156 | 126.1667 | 0.3 | 24 | 59 | 79 | 56.5 | 0 | 40 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 01:00 | 2017-03-22 | 0.05 | 87.6137 | 4.3807 | Reduce | 0.05 | 87.6137 | 4.3807 | H3 | 3 | Stable | 0.8 | 85 | 130 | 149 | 125.6667 | 0.3 | 34 | 41 | 62 | 43.3333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_288 | 2017-02-22 01:00 | 2017-11-19 01:00 | 0.3 | 5.8286 | 0.29143 | Accept | 0.3 | 5.8286 | 0.29143 | H2 | 4 | Improving | 0.9 | 92 | 124 | 144 | 122 | 0.9 | 92 | 124 | 144 | 122 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.3 | 53.0293 | 15.9088 | Reduce | 0.3 | 53.0293 | 15.9088 | H3 | 3 | Worsening | 0.9 | 102 | 134 | 149 | 131.1667 | 0.1 | 30 | 56 | 76 | 55 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Commercial aspects agreement | Person_480 | 2013-08-21 01:00 | 2017-05-22 | 0.02 | 4.8296 | 0.096593 | Transfer | 0.02 | 4.8296 | 0.096593 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 01:00 | 2017-08-20 01:00 | 0.1 | 34.363 | 3.4363 | Avoid | 0.1 | 34.363 | 3.4363 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.26 | 16.2047 | 4.2132 | Avoid | 0.26 | 16.2047 | 4.2132 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK209 | Project_024_RISK209 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Major Return to Service | Person_073 | 2016-11-20 01:00 | 2017-05-22 | 0.3 | 0.20788 | 0.068599 | Accept | 0.3 | 0.052336 | 0.0057569 | H2 | 4 | Stable | 0.5 | 99 | 130 | 142 | 126.8333 | 0.5 | 99 | 130 | 142 | 126.8333 | 74.8236 | 0 | 0 | 44.8942
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.25 | 7.7469 | 1.9367 | Reduce | 0.25 | 7.7469 | 1.9367 | H3 | 3 | Stable | 0.8 | 87 | 130 | 159 | 127.6667 | 0.3 | 36 | 49 | 64 | 49.3333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 01:00 | 0.05 | 11.3437 | 0.56718 | Reduce | 0.05 | 11.3437 | 0.56718 | H3 | 3 | Stable | 0.5 | 82 | 138 | 141 | 129.1667 | 0.2 | 27 | 57 | 72 | 54.5 | 0 | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-117 | Project_039_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Filters | Person_185 | 2015-01-21 01:00 | 2016-12-19 01:00 | 0.1 | 3.005 | 0.3005 | Reduce | 0.1 | 3.005 | 0.3005 | H3 | 3 | Stable | 0.6 | 114 | 134 | 146 | 132.6667 | 0.1 | 37 | 42 | 62 | 44.5 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK291 | Project_024_RISK291 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | LoE Engineering support required post completion in addition to BCR | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 1.8602 | 0.55807 | Accept | 0.5 | 1.8602 | 0.55807 | H1 | 5 | Worsening | 0.8 | 85 | 121 | 146 | 119.1667 | 0.8 | 85 | 121 | 146 | 119.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK253 | Project_024_RISK253 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Insufficient parts to complete framework Warranty | Person_289 | 2016-05-23 | 2017-04-21 | 0.1 | 1.4882 | 0.44646 | Accept | 0.1 | 1.4882 | 0.44646 | H2 | 4 | Improving | 0.8 | 115 | 136 | 150 | 134.8333 | 0.8 | 115 | 136 | 150 | 134.8333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Non-Recurring Engineering higher than expected | Person_674 | 2016-06-01 | 2016-08-04 | 0.4 | 6.5968 | 2.6387 | Reduce | 0.2 | 6.5944 | 1.3189 | H3 | 3 | Improving | 0.9 | 94 | 140 | 146 | 133.3333 | 0.1 | 6 | 43 | 67 | 40.8333 | 0.036395 | 50 | 0 | 0.021837
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK210 | Project_024_RISK210 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Performance impacts regualotory complaince | Person_534 | 2016-06-22 | 2017-02-19 01:00 | 0.3 | 19.1935 | 1.5355 | Accept | 0.3 | 19.1935 | 1.5355 | H2 | 4 | Stable | 0.6 | 87 | 140 | 156 | 133.8333 | 0.6 | 87 | 140 | 156 | 133.8333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK222 | Project_024_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Testing Extends beyond target completion | Person_351 | 2017-07-21 | 2018-08-21 | 0.2 | 8.3972 | 0.83972 | Accept | 0.2 | 8.3972 | 0.41986 | H2 | 4 | Stable | 0.9 | 92 | 125 | 141 | 122.1667 | 0.9 | 92 | 125 | 141 | 122.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-200 | Project_027_Risk-200 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Sucession Planning for key team members | Person_060 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.2 | 7.3175 | 1.4635 | Reduce | 0.05 | 7.3175 | 0.36588 | H2 | 4 | Stable | 0.5 | 103 | 133 | 150 | 130.8333 | 0.4 | 13 | 59 | 68 | 52.8333 | 0 | 75 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-189 | Project_027_Risk-189 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Major Component obsolescence | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 8.3972 | 2.5191 | Reduce | 0.08 | 8.3972 | 0.67177 | H2 | 4 | Stable | 0.6 | 84 | 129 | 152 | 125.3333 | 0.3 | 18 | 52 | 70 | 49.3333 | 0 | 73.3333 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-201 | Project_027_Risk-201 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Transition into Support | Person_027 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0.5 | 68.3768 | 34.1884 | Reduce | 0.05 | 38.387 | 1.9193 | H2 | 4 | Stable | 0.6 | 99 | 131 | 143 | 127.6667 | 0.2 | 13 | 55 | 79 | 52 | 43.8597 | 90 | 0 | 26.3158
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK237 | Project_024_RISK237 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer coding standard Compliance | Person_534 | 2017-05-25 | 2017-10-27 01:00 | 0.2 | 13.2195 | 1.5863 | Accept | 0.2 | 13.2195 | 1.5863 | H2 | 4 | Stable | 0.6 | 91 | 121 | 142 | 119.5 | 0.6 | 91 | 121 | 142 | 119.5 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-188 | Project_027_Risk-188 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Unidentified Technical Legacy Issue | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 20.0332 | 2.0033 | Reduce | 0.05 | 20.0332 | 1.0017 | H3 | 3 | Stable | 0.7 | 87 | 139 | 153 | 132.6667 | 0.1 | 10 | 51 | 71 | 47.5 | 0 | 50 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-193 | Project_027_Risk-193 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | A greater number of arising technical queries | Person_110 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 13.7953 | 4.1386 | Reduce | 0.05 | 13.7953 | 0.68977 | H3 | 3 | Stable | 0.8 | 86 | 131 | 159 | 128.1667 | 0.4 | 39 | 59 | 63 | 56.3333 | 0 | 83.3333 | 1 | 2.5
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Equipment environmental failure | Person_710 | 2016-05-23 | 2017-05-22 | 0.3 | 27.5907 | 2.7591 | Accept | 0.3 | 27.5907 | 2.7591 | H2 | 4 | Improving | 0.5 | 102 | 129 | 150 | 128 | 0.5 | 102 | 129 | 150 | 128 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-20 01:00 | 0.3 | 5.5433 | 1.663 | Reduce | 0.1 | 5.5433 | 0.55433 | H3 | 3 | Improving | 0.9 | 97 | 131 | 146 | 127.8333 | 0.4 | 35 | 49 | 64 | 49.1667 | 0 | 66.6667 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Stable | [10 empty] | 0 | 75 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Retained systems re-design or modification | Person_710 | 2016-08-20 01:00 | 2017-02-19 01:00 | 0.05 | 4.4946 | 1.1236 | Accept | 0.05 | 4.4946 | 0.44946 | H2 | 4 | Improving | 0.6 | 86 | 128 | 150 | 124.6667 | 0.6 | 86 | 128 | 150 | 124.6667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Mission System not compatible with platform systems | Person_710 | 2016-07-21 | 2017-04-21 | 0.1 | 6.7418 | 1.6855 | Accept | 0.1 | 6.7418 | 1.0113 | H3 | 3 | Stable | 0.9 | 96 | 126 | 141 | 123.5 | 0.9 | 96 | 126 | 141 | 123.5 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Qual failure | Person_710 | 2016-06-22 | 2017-05-22 | 0.4 | 17.9783 | 3.5957 | Accept | 0.4 | 17.9783 | 3.5957 | H1 | 5 | Improving | 0.9 | 117 | 140 | 141 | 136.3333 | 0.9 | 117 | 140 | 141 | 136.3333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Additional minor point releases | Person_073 | 2016-05-23 | 2017-08-20 01:00 | 0.5 | 0.81199 | 0.081199 | Accept | 0.5 | 0.81199 | 0.0406 | H1 | 5 | Stable | 0.9 | 102 | 139 | 159 | 136.1667 | 0.9 | 102 | 139 | 159 | 136.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-022 | Project_028_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Accrediation Scope | Person_253 | 2014-01-21 01:00 | 2017-03-22 | 0.5 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 20 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Digital Video Chainredesign | Person_289 | 2016-06-22 | 2017-05-22 | 0.71 | 12.1982 | 0.60991 | Accept | 0.75 | 12.1982 | 0.60991 | H1 | 5 | Worsening | 0.9 | 89 | 138 | 157 | 133 | 0.9 | 89 | 138 | 157 | 133 | 0 | -5.6338 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK189 | Project_024_RISK189 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment integration - Audio and Video recording | Person_289 | 2016-08-20 01:00 | 2017-03-22 | 0.49 | 0 | 0 | Accept | 0.5 | 0 | 0 | H1 | 5 | Worsening | 0.6 | 85 | 130 | 148 | 125.5 | 0.6 | 85 | 130 | 148 | 125.5 |  | -2.0408 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_641 | 2016-05-23 | 2017-08-20 01:00 | 0.4 | 0 | 0 | Accept | 0.4 | 0 | 0 | H1 | 5 | Stable | 0.5 | 105 | 127 | 141 | 125.6667 | 0.5 | 105 | 127 | 141 | 125.6667 |  | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2017-04-21 | 0.2 | 0.90951 | 0.1819 | Reduce | 0.2 | 0.90951 | 0.1819 | H3 | 3 | Stable | 0.6 | 112 | 139 | 145 | 135.5 | 0.4 | 25 | 55 | 64 | 51.5 | 0 | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2017-03-22 | 0.3 | 5.4553 | 1.6366 | Reduce | 0.15 | 5.252 | 0.7878 | H2 | 4 | Stable | 0.9 | 108 | 136 | 145 | 132.8333 | 0.1 | 1 | 41 | 73 | 39.6667 | 3.7267 | 50 | 0 | 2.236
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK194 | Project_024_RISK194 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Performance Models require additional effort | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.25 | 1.3215 | 0.39644 | Accept | 0.25 | 1.3215 | 0.39644 | H2 | 4 | Stable | 0.6 | 98 | 131 | 160 | 130.3333 | 0.6 | 98 | 131 | 160 | 130.3333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK197 | Project_024_RISK197 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Fitness for purpose | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 0.2 | 12.1982 | 2.4396 | Accept | 0.2 | 10.8428 | 1.0843 | H2 | 4 | Improving | 0.9 | 90 | 126 | 144 | 123 | 0.9 | 90 | 126 | 144 | 123 | 11.1111 | 0 | 0 | 6.6667
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Cable and connectors | Person_499 | 2015-11-21 01:00 | 2017-08-09 | 0.45 | 0.41338 | 0.18602 | Reduce | 0.2 | 0.41338 | 0.082677 | H2 | 4 | Stable | 0.6 | 88 | 136 | 149 | 130.1667 | 0.2 | 28 | 50 | 66 | 49 | 0 | 55.5556 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Platform Acceptance | Person_500 | 2015-11-21 01:00 | 2017-05-22 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.3 | 8.471 | 2.5413 | H2 | 4 | Stable | 0.8 | 100 | 122 | 147 | 122.5 | 0.1 | 35 | 41 | 67 | 44.3333 | -99.9999 | 14.2857 | 0 | -59.9999
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Furnished Equipmnet Condition | Person_371 | 2015-04-27 | 2017-08-19 01:00 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.8 | 94 | 131 | 151 | 128.1667 | 0.4 | 37 | 43 | 77 | 47.6667 |  | 62.5 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK225 | Project_024_RISK225 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | SW verification against SRSs required | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 5.6866 | 2.8433 | Reduce | 0.5 | 5.6866 | 2.8433 | H1 | 5 | Stable | 0.8 | 116 | 133 | 159 | 134.5 | 0.4 | 6 | 42 | 75 | 41.5 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-12-21 01:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.5 | 92 | 136 | 142 | 129.6667 | 0.1 | 15 | 54 | 70 | 50.1667 | 47 | 0 | 0 | 28.2
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-12-21 01:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 0.4 | 9.139 | 3.6556 | Avoid | 0.2 | 9.139 | 1.8278 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 0.5 | 13.7833 | 6.8917 | Avoid | 0.2 | 6.8917 | 1.3783 | H3 | 3 | Stable | [10 empty] | 50 | 60 | 1 | 31.8
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK117 | Project_037_RISK117 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Data Comms Availability or Performance | Person_334 | 2015-05-24 | 2016-11-20 01:00 | 0.35 | 3.2401 | 1.134 | Transfer | 0.05 | 3.2401 | 0.16201 | H3 | 3 | Improving | [10 empty] | 0 | 85.7143 | 1 | 2.5714
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-20 01:00 | 0.3 | 5.5433 | 1.663 | Reduce | 0.35 | 5.5433 | 1.9402 | H2 | 4 | Worsening | 0.5 | 94 | 130 | 149 | 127.1667 | 0.2 | 1 | 50 | 62 | 43.8333 | 0 | -16.6667 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-19 01:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.2 | 1.5935 | 0.3187 | H3 | 3 | Stable | 0.9 | 99 | 128 | 148 | 126.5 | 0.4 | 26 | 56 | 76 | 54.3333 | 50 | 50 | 1 | 31.5
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Stable | [10 empty] | 0 | 75 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 0.125 | 232.2192 | 29.0274 | -- | 0.215 | 27.8663 | 5.9913 | H2 | 4 | Stable | [10 empty] | 88 | -72 | 0 | 52.8
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 0.3 | 26.9674 | 8.0902 | Avoid | 0.3 | 14.9819 | 4.4946 | H2 | 4 | Stable | [10 empty] | 44.4444 | 0 | 0 | 26.6667
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-21 01:00 | 0.5 | 26.9674 | 13.4837 | Avoid | 0.1 | 12.7646 | 1.2765 | H2 | 4 | Worsening | [10 empty] | 52.6667 | 80 | 0 | 31.6
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Obsolescence Monitoring Risk | Person_181 | 2016-12-02 21:00 | 2017-01-19 21:00 | 0.3 | 5.9458 | 1.7837 | Reduce | 0.15 | 0.9786 | 0.14679 | H3 | 3 | Stable | 0.6 | 101 | 124 | 154 | 125.1667 | 0.3 | 27 | 50 | 71 | 49.6667 | 83.5413 | 50 | 0 | 50.1248
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2017-02-19 01:00 | 0.05 | 3.0903 | 0.61807 | Accept | 0.05 | 3.0903 | 0.61807 | H3 | 3 | Improving | 0.9 | 98 | 123 | 141 | 121.8333 | 0.9 | 98 | 123 | 141 | 121.8333 | 0 | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 0.5 | 30.9033 | 7.7258 | Accept | 0.5 | 30.9033 | 7.7258 | H2 | 4 | Stable | 0.5 | 106 | 123 | 150 | 124.6667 | 0.5 | 106 | 123 | 150 | 124.6667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 0.5 | 35.0206 | 7.0041 | Accept | 0.5 | 35.0206 | 7.0041 | H2 | 4 | Stable | 0.7 | 86 | 133 | 145 | 127.1667 | 0.7 | 86 | 133 | 145 | 127.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 15.0654 | 6.7794 | Accept | 0.5 | 15.0654 | 6.7794 | H2 | 4 | Stable | 0.6 | 100 | 138 | 145 | 132.8333 | 0.6 | 100 | 138 | 145 | 132.8333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.5 | 90 | 130 | 150 | 126.6667 | 0.2 | 22 | 53 | 61 | 49.1667 | 25.8065 | 20 | 0 | 15.4839
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-20 23:00 | 2016-08-20 23:00 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.5 | 111 | 134 | 148 | 132.5 | 0.4 | 16 | 52 | 77 | 50.1667 | 0 | 16.6667 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 0.05 | 7.689 | 2.6911 | Accept | 0.05 | 7.689 | 2.6911 | H2 | 4 | Stable | 0.9 | 101 | 123 | 148 | 123.5 | 0.9 | 101 | 123 | 148 | 123.5 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-111 | Project_039_Risk-111 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Maturation results inconclusive | Person_297 | 2016-02-21 01:00 | 2017-01-20 01:00 | 0.3 | 5.126 | 2.563 | Accept | 0.3 | 5.126 | 2.563 | H2 | 4 | Stable | 0.5 | 114 | 132 | 152 | 132.3333 | 0.5 | 114 | 132 | 152 | 132.3333 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-195 | Project_039_Risk-195 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Supply Chain Delays - System Comms, Component, and subsystem | Person_083 | 2016-08-21 01:00 | 2017-02-19 01:00 | 0.3 | 12.815 | 2.563 | Accept | 0.3 | 12.815 | 2.563 | H3 | 3 | Worsening | 0.5 | 95 | 127 | 148 | 125.1667 | 0.5 | 95 | 127 | 148 | 125.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.5 | 84 | 129 | 151 | 125.1667 | 0.3 | 34 | 55 | 71 | 54.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 19:00 | 2019-08-20 19:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.5 | 104 | 130 | 160 | 130.6667 | 0.4 | 31 | 49 | 67 | 49 | 83.3333 | 88.8889 | 1 | 52.6667
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.7 | 96 | 138 | 155 | 133.8333 | 0.2 | 14 | 51 | 76 | 49 | 72 | 0 | 0 | 43.2
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.6 | 119 | 126 | 142 | 127.5 | 0.2 | 23 | 55 | 70 | 52.1667 | 47.7391 | 0 | 0 | 28.6435
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 19:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.5 | 100 | 121 | 146 | 121.6667 | 0.4 | 27 | 46 | 65 | 46 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.8 | 109 | 130 | 142 | 128.5 | 0.3 | 28 | 59 | 76 | 56.6667 | 0 | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.8 | 84 | 140 | 142 | 131 | 0.1 | 4 | 49 | 67 | 44.5 | 25.8065 | 20 | 0 | 15.4839
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-189 | Project_027_Risk-189 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Major Component obsolescence | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 8.3972 | 2.5191 | Reduce | 0.08 | 8.3972 | 0.67177 | H2 | 4 | Stable | 0.7 | 112 | 125 | 153 | 127.5 | 0.2 | 25 | 57 | 77 | 55 | 0 | 73.3333 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-201 | Project_027_Risk-201 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Transition into Support | Person_027 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0.5 | 68.3768 | 34.1884 | Reduce | 0.05 | 38.387 | 1.9193 | H2 | 4 | Stable | 0.7 | 101 | 132 | 154 | 130.5 | 0.4 | 28 | 57 | 66 | 53.6667 | 43.8597 | 90 | 0 | 26.3158
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-188 | Project_027_Risk-188 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Unidentified Technical Legacy Issue | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 20.0332 | 2.0033 | Reduce | 0.05 | 20.0332 | 1.0017 | H3 | 3 | Stable | 0.5 | 102 | 121 | 158 | 124 | 0.4 | 6 | 47 | 78 | 45.3333 | 0 | 50 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-193 | Project_027_Risk-193 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | A greater number of arising technical queries | Person_110 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 13.7953 | 4.1386 | Reduce | 0.05 | 13.7953 | 0.68977 | H3 | 3 | Stable | 0.5 | 100 | 139 | 150 | 134.3333 | 0.1 | 14 | 47 | 75 | 46.1667 | 0 | 83.3333 | 1 | 2.5
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-194 | Project_027_Risk-194 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | The effect of specialist supplier obsolescence on complex assemblies | Person_074 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.08 | 35.9878 | 21.5927 | Accept | 0.08 | 15.5947 | 0.77974 | H3 | 3 | Stable | 0.6 | 84 | 129 | 147 | 124.5 | 0.6 | 84 | 129 | 147 | 124.5 | 56.6667 | 0 | 1 | 34
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-022 | Project_028_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Accrediation Scope | Person_253 | 2014-01-21 01:00 | 2017-06-22 | 0.5 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 20 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-187 | Project_027_Risk-187 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Loss of a major sub-contractor | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.12 | 12.1982 | 0.60991 | Accept | 0.12 | 12.1982 | 0.60991 | H3 | 3 | Stable | 0.7 | 117 | 122 | 157 | 127 | 0.7 | 117 | 122 | 157 | 127 | 0 | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-196 | Project_027_Risk-196 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Aging equipment resulting in increasing failure rates | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 0 | 0 | Accept | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 94 | 136 | 155 | 132.1667 | 0.7 | 94 | 136 | 155 | 132.1667 |  | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-185 | Project_027_Risk-185 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier manufacturing issues | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.6 | 0 | 0 | Accept | 0.05 | 0 | 0 | H3 | 3 | Stable | 0.8 | 83 | 126 | 156 | 123.8333 | 0.8 | 83 | 126 | 156 | 123.8333 |  | 91.6667 | 1
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2017-04-21 | 0.2 | 0.90951 | 0.1819 | Reduce | 0.1 | 0.90951 | 0.090951 | H3 | 3 | Stable | 0.5 | 112 | 140 | 155 | 137.8333 | 0.2 | 26 | 40 | 75 | 43.5 | 0 | 50 | 1 | 1.5
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2017-06-22 | 0.3 | 5.4553 | 1.6366 | Reduce | 0.15 | 5.252 | 0.7878 | H2 | 4 | Stable | 0.9 | 117 | 138 | 150 | 136.5 | 0.1 | 11 | 54 | 66 | 48.8333 | 3.7267 | 50 | 0 | 2.236
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-186 | Project_027_Risk-186 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Potential for composite suppliers going out of business | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 1.3215 | 0.39644 | Accept | 0.1 | 1.3215 | 0.39644 | H3 | 3 | Stable | 0.7 | 120 | 123 | 154 | 127.6667 | 0.7 | 120 | 123 | 154 | 127.6667 | 0 | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 01:00 | 2016-11-20 01:00 | 0.25 | 12.1982 | 2.4396 | Accept | 0.1 | 10.8428 | 1.0843 | H3 | 3 | Stable | 0.7 | 83 | 135 | 159 | 130.3333 | 0.7 | 83 | 135 | 159 | 130.3333 | 11.1111 | 60 | 0 | 6.6667
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-20 01:00 | 0.25 | 4.4727 | 0.22363 | Accept | 0.15 | 4.4727 | 0.22363 | H3 | 3 | Stable | 0.5 | 89 | 131 | 152 | 127.5 | 0.5 | 89 | 131 | 152 | 127.5 | 0 | 40 | 1 | 1.2
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Cable and connectors | Person_499 | 2015-11-21 01:00 | 2017-08-09 | 0.45 | 0.41338 | 0.18602 | Reduce | 0.2 | 0.41338 | 0.082677 | H2 | 4 | Stable | 0.8 | 97 | 127 | 155 | 126.6667 | 0.3 | 30 | 58 | 60 | 53.6667 | 0 | 55.5556 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Platform Acceptance | Person_500 | 2015-11-21 01:00 | 2017-05-22 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.3 | 8.471 | 2.5413 | H2 | 4 | Stable | 0.7 | 94 | 132 | 146 | 128 | 0.1 | 28 | 42 | 77 | 45.5 | -99.9999 | 14.2857 | 0 | -59.9999
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 01:00 | 0.1 | 8.8098 | 3.0834 | Accept | 0.05 | 8.8098 | 1.762 | H3 | 3 | Stable | 0.9 | 114 | 133 | 158 | 134 | 0.9 | 114 | 133 | 158 | 134 | 0 | 50 | 1 | 1.5
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-015 | Project_028_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | STANDARDS Compliance | Person_499 | 2015-11-21 01:00 | 2017-03-21 01:00 | 0.05 | 0.40661 | 0.16264 | Accept | 0.05 | 0.40661 | 0.081321 | H3 | 3 | Stable | 0.5 | 101 | 129 | 146 | 127.1667 | 0.5 | 101 | 129 | 146 | 127.1667 | 0 | 0 | 1 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Furnished Equipmnet Condition | Person_371 | 2015-04-27 | 2017-08-19 01:00 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.6 | 101 | 133 | 155 | 131.3333 | 0.4 | 34 | 54 | 67 | 52.8333 |  | 62.5 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-080 | Project_008_Risk-080 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Recovery of Costs | Person_565 | 2016-08-21 01:00 | 2017-05-21 | 0.5 | 23.6737 | 11.8369 | -- | 0.5 | 23.6737 | 11.8369 | H3 | 3 | Worsening | [10 empty] | 0 | 0 | 1 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-059 | Project_008_Risk-059 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Project Resource Efficencies | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 0.2 | 21.6852 | 4.337 | -- | 0.15 | 21.6852 | 3.2528 | H3 | 3 | Worsening | [10 empty] | 0 | 25 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Survey costs | Person_618 | 2016-04-22 | 2017-08-20 01:00 | 1 | 13.2573 | 13.2573 | Avoid | 0.5 | 13.2573 | 6.6286 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-079 | Project_008_Risk-079 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Regulations Phase 3 and 4 | Person_565 | 2016-10-21 01:00 | 2018-08-21 | 0.25 | 71.9682 | 17.992 | -- | 0.25 | 71.9682 | 17.992 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence and missing info | Person_727 | 2015-11-25 01:00 | 2017-02-19 01:00 | 0.3 | 71.0212 | 21.3064 | Accept | 0.3 | 71.0212 | 21.3064 | H2 | 4 | Stable | 0.8 | 106 | 126 | 152 | 127 | 0.8 | 106 | 126 | 152 | 127 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 01:00 | 2017-03-22 | 0.2 | 1.8788 | 0.28182 | Accept | 0.1 | 1.8788 | 0.28182 | H2 | 4 | Stable | 0.6 | 120 | 128 | 156 | 131.3333 | 0.6 | 120 | 128 | 156 | 131.3333 | 0 | 50 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-002 | Project_028_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Record / Replay feature | Person_499 | 2014-03-23 | 2017-03-21 01:00 | 0.1 | 9.3941 | 1.8788 | Accept | 0.05 | 9.3941 | 1.8788 | H2 | 4 | Stable | 0.5 | 118 | 139 | 148 | 137 | 0.5 | 118 | 139 | 148 | 137 | 0 | 50 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | EMC Testing | Person_070 | 2016-04-22 | 2017-04-21 | 0.35 | 1.8788 | 0.18788 | Accept | 0.2 | 1.8788 | 0.18788 | H2 | 4 | Stable | 0.6 | 103 | 136 | 147 | 132.3333 | 0.6 | 103 | 136 | 147 | 132.3333 | 0 | 42.8571 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_542 | 2015-01-22 01:00 | 2017-08-20 01:00 | 0.35 | 29.4599 | 8.838 | Accept | 0.2 | 18.7882 | 5.6365 | H2 | 4 | Stable | 0.5 | 110 | 138 | 155 | 136.1667 | 0.5 | 110 | 138 | 155 | 136.1667 | 36.2245 | 42.8571 | 0 | 21.7347
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_070 | 2016-06-23 | 2017-04-21 | 0.4 | 1.1273 | 0.22546 | Accept | 0.2 | 1.1273 | 0.22546 | H2 | 4 | Stable | 0.8 | 83 | 121 | 157 | 120.6667 | 0.8 | 83 | 121 | 157 | 120.6667 | 0 | 50 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK118 | Project_037_RISK118 | Threat | Management Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Product does not deliver the inputs/depdencies required by the Project by the req'd dates | Person_330 | 2015-02-23 21:00 | 2016-06-23 | 0.4 | 4.7948 | 0.95895 | Accept | 0.4 | 4.7948 | 0.95895 | H2 | 4 | Worsening | 0.6 | 88 | 122 | 151 | 121.1667 | 0.6 | 88 | 122 | 151 | 121.1667 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 01:00 | 2016-11-20 01:00 | 0.25 | 0.65759 | 0.098638 | Accept | 0.1 | 0.65759 | 0.098638 | H3 | 3 | Stable | 0.8 | 92 | 134 | 141 | 128.1667 | 0.8 | 92 | 134 | 141 | 128.1667 | 0 | 60 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-20 01:00 | 0.25 | 6.7638 | 1.3528 | Accept | 0.15 | 6.7638 | 1.3528 | H3 | 3 | Stable | 0.6 | 105 | 131 | 156 | 130.8333 | 0.6 | 105 | 131 | 156 | 130.8333 | 0 | 40 | 1 | 1.2
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.35 | 9.3941 | 0.93941 | Accept | 0.35 | 9.3941 | 0.93941 | H3 | 3 | Stable | 0.5 | 113 | 126 | 149 | 127.6667 | 0.5 | 113 | 126 | 149 | 127.6667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Governance and Export Rules | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 0.93941 | 0.23485 | Transfer | 0.25 | 0.93941 | 0.23485 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.25 | 2.1606 | 0.43213 | Accept | 0.25 | 2.1606 | 0.43213 | H3 | 3 | Stable | 0.5 | 89 | 134 | 155 | 130 | 0.5 | 89 | 134 | 155 | 130 | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-20 23:00 | 2019-08-20 | 0.5 | 13.3529 | 6.6765 | Accept | 0.5 | 23.5716 | 11.7858 | H2 | 4 | Stable | 0.7 | 104 | 132 | 159 | 131.8333 | 0.7 | 104 | 132 | 159 | 131.8333 | -76.5278 | 0 | 0 | -45.9167
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 0.5 | 9.2728 | 4.6364 | Reduce | 0.15 | 9.2728 | 1.3909 | H2 | 4 | Stable | 0.8 | 111 | 140 | 149 | 136.6667 | 0.4 | 32 | 44 | 64 | 45.3333 | 0 | 70 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R008 | Project_016_Risk--R008 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Additional Travel & Subsistence | Person_574 | 2016-01-13 01:00 | 2019-05-23 | 0.4 | 8.9019 | 3.5608 | Reduce | 0.25 | 8.9019 | 2.2255 | H3 | 3 | Stable | 0.5 | 94 | 139 | 150 | 133.3333 | 0.3 | 37 | 48 | 70 | 49.8333 | 0 | 37.5 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 0.3 | 8.7814 | 2.6344 | Reduce | 0.15 | 8.7832 | 1.3175 | H3 | 3 | Stable | 0.8 | 116 | 133 | 153 | 133.5 | 0.1 | 12 | 49 | 67 | 45.8333 | -0.021119 | 50 | 1 | 1.4873
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 17:00 | 2019-08-20 17:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R009 | Project_016_Risk--R009 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer maybe difficult to work with | Person_697 | 2016-04-02 | 2019-08-01 | 0.6 | 23.9549 | 14.3729 | Reduce | 0.43864 | 23.8312 | 10.4533 | H2 | 4 | Stable | 0.6 | 107 | 131 | 153 | 130.6667 | 0.1 | 34 | 46 | 69 | 47.8333 | 0.51612 | 26.8938 | 0 | 0.30967
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 17:00 | 2019-08-20 17:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.2 | 108.3186 | 32.4956 | Accept | 0.2 | 108.3186 | 32.4956 | H3 | 3 | Stable | 0.6 | 89 | 136 | 154 | 131.1667 | 0.6 | 89 | 136 | 154 | 131.1667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 17:00 | 2019-08-20 17:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Delay of processing | Person_306 | 2016-04-02 | 2017-03-21 01:00 | 0.15 | 26.3497 | 3.9525 | Reduce | 0.15 | 13.1767 | 1.9765 | H3 | 3 | Stable | 0.8 | 87 | 134 | 145 | 128 | 0.4 | 16 | 41 | 61 | 40.1667 | 49.993 | 0 | 1 | 29.9958
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 17:00 | 2019-08-20 17:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 17:00 | 2019-08-20 17:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 0.61 | 12.0547 | 2.4109 | Accept | 0.61 | 12.0547 | 2.4109 | H1 | 5 | Stable | 0.6 | 120 | 128 | 151 | 130.5 | 0.6 | 120 | 128 | 151 | 130.5 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 01:00 | 2017-03-22 | 0.05 | 87.6137 | 4.3807 | Reduce | 0.05 | 87.6137 | 4.3807 | H3 | 3 | Stable | 0.7 | 119 | 128 | 145 | 129.3333 | 0.3 | 7 | 50 | 60 | 44.5 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.3 | 53.0293 | 15.9088 | Reduce | 0.3 | 53.0293 | 15.9088 | H3 | 3 | Worsening | 0.8 | 92 | 127 | 143 | 123.8333 | 0.3 | 34 | 54 | 78 | 54.6667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Commercial aspects agreement | Person_480 | 2013-08-21 01:00 | 2017-05-22 | 0.02 | 4.8296 | 0.096593 | Transfer | 0.02 | 4.8296 | 0.096593 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 01:00 | 2017-08-20 01:00 | 0.1 | 34.363 | 3.4363 | Avoid | 0.1 | 34.363 | 3.4363 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.26 | 16.2047 | 4.2132 | Avoid | 0.26 | 16.2047 | 4.2132 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-194 | Project_027_Risk-194 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | The effect of specialist supplier obsolescence on complex assemblies | Person_074 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.08 | 0.20788 | 0.068599 | Accept | 0.08 | 0.052336 | 0.0057569 | H3 | 3 | Stable | 0.9 | 81 | 140 | 142 | 130.5 | 0.9 | 81 | 140 | 142 | 130.5 | 74.8236 | 0 | 1 | 44.8942
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.25 | 7.7469 | 1.9367 | Reduce | 0.25 | 7.7469 | 1.9367 | H3 | 3 | Stable | 0.6 | 117 | 134 | 149 | 133.6667 | 0.1 | 12 | 43 | 76 | 43.3333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 01:00 | 0.05 | 11.3437 | 0.56718 | Reduce | 0.05 | 11.3437 | 0.56718 | H3 | 3 | Stable | 0.8 | 117 | 127 | 155 | 130 | 0.1 | 20 | 49 | 78 | 49 | 0 | 0 | 1 | 0
2017-01-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.8 | 95 | 130 | 155 | 128.3333 | 0.2 | 3 | 40 | 67 | 38.3333 | 0 | 25 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-185 | Project_027_Risk-185 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier manufacturing issues | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.6 | 3.4415 | 1.3766 | Accept | 0.05 | 3.4415 | 1.3766 | H3 | 3 | Stable | 0.6 | 115 | 121 | 156 | 125.8333 | 0.6 | 115 | 121 | 156 | 125.8333 | 0 | 91.6667 | 1 | 2.75
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-186 | Project_027_Risk-186 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Potential for composite suppliers going out of business | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 8.0582 | 2.4175 | Accept | 0.1 | 8.0582 | 2.4175 | H3 | 3 | Stable | 0.7 | 119 | 139 | 157 | 138.6667 | 0.7 | 119 | 139 | 157 | 138.6667 | 0 | 0 | 1 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 01:00 | 0.1 | 0 | 0 | Accept | 0.05 | 0 | 0 | H3 | 3 | Stable | 0.7 | 106 | 125 | 143 | 124.8333 | 0.7 | 106 | 125 | 143 | 124.8333 |  | 50 | 1
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-015 | Project_028_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | STANDARDS Compliance | Person_499 | 2015-11-21 01:00 | 2017-05-21 | 0.05 | 0.5596 | 0.05596 | Accept | 0.05 | 0.5596 | 0.05596 | H3 | 3 | Stable | 0.5 | 115 | 138 | 157 | 137.3333 | 0.5 | 115 | 138 | 157 | 137.3333 | 0 | 0 | 1 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence and missing info | Person_727 | 2015-11-25 01:00 | 2017-06-21 | 0.3 | 4.4768 | 2.2384 | Accept | 0.3 | 4.4768 | 2.2384 | H2 | 4 | Stable | 0.9 | 101 | 134 | 152 | 131.5 | 0.9 | 101 | 134 | 152 | 131.5 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 01:00 | 2017-03-22 | 0.2 | 244.3581 | 12.2179 | Accept | 0.1 | 227.5702 | 11.3785 | H2 | 4 | Stable | 0.9 | 90 | 126 | 151 | 124.1667 | 0.9 | 90 | 126 | 151 | 124.1667 | 6.8702 | 50 | 0 | 4.1221
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-002 | Project_028_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Record / Replay feature | Person_499 | 2014-03-23 | 2017-04-21 | 0.05 | 24.8462 | 12.4231 | Accept | 0.05 | 24.8462 | 12.4231 | H2 | 4 | Stable | 0.9 | 106 | 133 | 147 | 130.8333 | 0.9 | 106 | 133 | 147 | 130.8333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | EMC Testing | Person_070 | 2016-04-22 | 2017-04-21 | 0.35 | 60.4367 | 3.0218 | Accept | 0.2 | 60.4367 | 3.0218 | H2 | 4 | Stable | 0.6 | 96 | 123 | 142 | 121.6667 | 0.6 | 96 | 123 | 142 | 121.6667 | 0 | 42.8571 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK004 | Project_010_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Export License | Person_359 | 2015-02-18 01:00 | 2017-08-20 01:00 | 0.8 | 0.18482 | 0.14786 | Reduce | 0.8 | 0.18482 | 0.14786 | H1 | 5 | Improving | 0.7 | 116 | 123 | 149 | 126.1667 | 0.4 | 37 | 45 | 64 | 46.8333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 01:00 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.5 | 81 | 123 | 148 | 120.1667 | 0.3 | 38 | 54 | 76 | 55 | 0 | 40 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_542 | 2015-01-22 01:00 | 2017-08-20 01:00 | 0.35 | 11.0894 | 0.55447 | Accept | 0.2 | 11.0894 | 0.55447 | H2 | 4 | Stable | 0.7 | 117 | 125 | 152 | 128.1667 | 0.7 | 117 | 125 | 152 | 128.1667 | 0 | 42.8571 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.7 | 0.92411 | 0.64688 | Reduce | 0.3 | 0.36965 | 0.11089 | H2 | 4 | Stable | 0.8 | 87 | 122 | 141 | 119.3333 | 0.2 | 11 | 56 | 73 | 51.3333 | 60 | 57.1429 | 0 | 36
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 01:00 | 2016-04-21 | 0.5 | 4.0661 | 2.033 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.6 | 81 | 125 | 154 | 122.5 | 0.2 | 9 | 44 | 60 | 40.8333 | 0 | 90 | 1 | 2.7
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.3 | 0.46206 | 0.13862 | H2 | 4 | Improving | 0.6 | 111 | 134 | 147 | 132.3333 | 0.2 | 19 | 56 | 64 | 51.1667 | 58.3333 | 50 | 0 | 35
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_070 | 2016-06-23 | 2017-06-21 | 0.4 | 1.1089 | 0.88715 | Accept | 0.2 | 0.73929 | 0.44357 | H2 | 4 | Stable | 0.5 | 84 | 121 | 146 | 119 | 0.5 | 84 | 121 | 146 | 119 | 33.3333 | 50 | 0 | 20
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 01:00 | 2017-08-20 01:00 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.7 | 115 | 126 | 151 | 128.3333 | 0.4 | 38 | 53 | 69 | 53.1667 | 0 | 50 | 1 | 1.5
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.5 | 119 | 138 | 144 | 135.8333 | 0.4 | 1 | 58 | 69 | 50.3333 | 0 | 25 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Stable | 0.6 | 102 | 125 | 158 | 126.6667 | 0.3 | 17 | 51 | 71 | 48.6667 | 0 | 40 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Worsening | [10 empty] | 0 | 37.5 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 0.45 | 3.6965 | 0.36965 | Accept | 0.45 | 3.6965 | 0.36965 | H2 | 4 | Stable | 0.9 | 108 | 124 | 147 | 125.1667 | 0.9 | 108 | 124 | 147 | 125.1667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_565 | 2018-05-22 | 2018-08-21 | 0.25 | 0.92411 | 0.18482 | Accept | 0.25 | 0.92411 | 0.18482 | H3 | 3 | Stable | 0.7 | 115 | 127 | 150 | 128.8333 | 0.7 | 115 | 127 | 150 | 128.8333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 0.3 | 1.8482 | 0.55447 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.9 | 100 | 130 | 151 | 128.5 | 0.1 | 3 | 54 | 77 | 49.3333 | 0 | 33.3333 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 01:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.5 | 120 | 135 | 147 | 134.5 | 0.2 | 18 | 52 | 71 | 49.5 | 90 | 75 | 1 | 56.25
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_693 | 2017-03-23 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Worsening | 0.7 | 99 | 134 | 141 | 129.3333 | 0.2 | 26 | 47 | 78 | 48.6667 | 0 | 50 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2017-03-23 | 2018-05-22 | 0.75 | 10.7184 | 8.0388 | Reduce | 0.1 | 5.3592 | 0.53592 | H3 | 3 | Worsening | 0.6 | 100 | 124 | 145 | 123.5 | 0.2 | 22 | 42 | 69 | 43.1667 | 50 | 86.6667 | 1 | 32.6
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Lack of Spares Availability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 0.3 | 1.9722 | 0.98609 | Accept | 0.3 | 1.9722 | 0.98609 | H2 | 4 | Stable | 0.6 | 85 | 125 | 141 | 121 | 0.6 | 85 | 125 | 141 | 121 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Suppliers | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 2.5081 | 1.2541 | Accept | 0.15 | 2.5081 | 1.2541 | H2 | 4 | Stable | 0.6 | 116 | 135 | 159 | 135.8333 | 0.6 | 116 | 135 | 159 | 135.8333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment | Person_238 | 2017-04-01 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.05 | 1.2219 | 0.061095 | H3 | 3 | Stable | 0.9 | 84 | 140 | 150 | 132.3333 | 0.4 | 37 | 46 | 78 | 49.8333 | -78.1248 | 80 | 1 | -44.4749
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 0.45017 | 0.2701 | Accept | 0.2 | 0.45017 | 0.2701 | H2 | 4 | Stable | 0.7 | 80 | 124 | 152 | 121.3333 | 0.7 | 80 | 124 | 152 | 121.3333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Local customer Engineers in country | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 3.7514 | 0.37514 | Accept | 0.1 | 3.7514 | 0.37514 | H2 | 4 | Stable | 0.7 | 107 | 122 | 146 | 123.5 | 0.7 | 107 | 122 | 146 | 123.5 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2017-03-23 | 2017-07-21 | 0.1 | 21.8655 | 2.1865 | Reduce | 0.01 | 21.8655 | 0.21865 | H2 | 4 | Stable | 0.7 | 93 | 131 | 152 | 128.1667 | 0.4 | 17 | 49 | 66 | 46.5 | 0 | 90 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2017-03-23 | 2018-05-22 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Stable | 0.5 | 93 | 139 | 159 | 134.6667 | 0.3 | 12 | 40 | 74 | 41 | 0 | 60 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence | Person_455 | 2016-05-23 | 2020-05-23 | 0.3 | 0.6088 | 0.3044 | Accept | 0.3 | 0.6088 | 0.3044 | H2 | 4 | Stable | 0.6 | 92 | 122 | 146 | 121 | 0.6 | 92 | 122 | 146 | 121 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Unidentified CRs and concessions | Person_693 | 2017-03-23 | 2017-09-20 01:00 | 0.5 | 1.2005 | 0.60023 | Reduce | 0.15 | 0.51019 | 0.076529 | H3 | 3 | Stable | 0.6 | 113 | 129 | 152 | 130.1667 | 0.4 | 32 | 52 | 72 | 52 | 57.5001 | 70 | 1 | 36.6001
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_238 | 2017-03-23 | 2018-05-22 | 0.25 | 3.3227 | 0.83067 | Reduce | 0.05 | 3.3227 | 0.16613 | H3 | 3 | Stable | 0.6 | 112 | 126 | 154 | 128.3333 | 0.3 | 13 | 49 | 73 | 47 | 0 | 80 | 1 | 2.4
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_693 | 2017-03-23 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.1 | 0.77172 | 0.077172 | H3 | 3 | Stable | 0.9 | 113 | 125 | 155 | 128 | 0.1 | 25 | 56 | 72 | 53.5 | 0 | 60 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production or Engineering | Person_058 | 2017-03-23 | 2018-05-22 | 0.3 | 1.7492 | 0.52477 | Reduce | 0.1 | 1.7492 | 0.17492 | H3 | 3 | Stable | 0.6 | 96 | 124 | 146 | 123 | 0.4 | 29 | 42 | 60 | 42.8333 | 0 | 66.6667 | 1 | 2
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_693 | 2017-03-23 | 2018-11-20 01:00 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.1 | 6.431 | 0.6431 | H3 | 3 | Improving | 0.8 | 84 | 123 | 155 | 121.8333 | 0.4 | 32 | 43 | 72 | 46 | -47.0588 | 33.3333 | 1 | -27.2353
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Consumables | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 0.21008 | 0.10504 | Accept | 0.2 | 0.21008 | 0.05252 | H2 | 4 | Stable | 0.7 | 93 | 121 | 141 | 119.6667 | 0.7 | 93 | 121 | 141 | 119.6667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Reduce touch labour if Production readiness programme successful | Person_238 | 2017-03-23 | 2017-10-21 01:00 | 0.3 | 1.5606 | 0.46818 | Exploit | 0.5 | 1.5606 | 0.7803 | H2 | 4 | Stable | [10 empty] | 0 | -66.6667 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-116 | Project_011_Risk-116 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Delays to Qualification | Person_147 | 2017-04-22 | 2017-08-19 01:00 | 0.5 | 0.86486 | 0.43243 | Reduce | 0.5 | 0.86486 | 0.43243 | H1 | 5 | Stable | 0.5 | 104 | 124 | 153 | 125.5 | 0.2 | 23 | 50 | 63 | 47.6667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-104 | Project_011_Risk-104 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer delayed in providing Custeomr Furnished Equipment | Person_147 | 2016-06-23 | 2017-04-21 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.9 | 81 | 126 | 145 | 121.6667 | 0.2 | 33 | 43 | 63 | 44.6667 |  | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 7. Finance | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 0.30685 | 0.06137 | Accept | 0.2 | 0.30685 | 0.06137 | H2 | 4 | Stable | 0.9 | 112 | 139 | 153 | 136.8333 | 0.9 | 112 | 139 | 153 | 136.8333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 0.3 | 0.51931 | 0.15579 | -- | 0.15 | 0.51931 | 0.077897 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 0.2 | 0.55005 | 0.11001 | Avoid | 0.2 | 0.55005 | 0.11001 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-123 | Project_011_Risk-123 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | No Requirement for Delta acceptance | Person_187 | 2017-06-23 | 2017-08-20 01:00 | 0.2 | 0.63074 | 0.12615 | -- | 0.2 | 0.63074 | 0.12615 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2016-07-21 | 2017-02-19 01:00 | 0.15 | 0.28639 | 0.042959 | -- | 0.15 | 0.28639 | 0.042959 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-04-21 | 0.2 | 0.24207 | 0.048414 | -- | 0.2 | 0.24207 | 0.048414 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 0.2 | 1.661 | 0.33219 | Reduce | 0.2 | 1.661 | 0.33219 | H2 | 4 | Stable | 0.9 | 84 | 139 | 158 | 133 | 0.2 | 5 | 59 | 77 | 53 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2017-10-21 01:00 | 2018-08-21 | 0.4 | 1.2444 | 0.49778 | Reduce | 0.4 | 1.2444 | 0.49778 | H2 | 4 | Stable | 0.5 | 106 | 136 | 150 | 133.3333 | 0.1 | 25 | 45 | 77 | 47 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 0.16195 | 0.072876 | Accept | 0.15 | 0.16195 | 0.072876 | H2 | 4 | Stable | 0.8 | 100 | 121 | 160 | 124 | 0.8 | 100 | 121 | 160 | 124 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 01:00 | 2018-08-21 | 0.45 | 0.83883 | 0.37747 | Reduce | 0.45 | 0.83883 | 0.37747 | H2 | 4 | Stable | 0.6 | 112 | 122 | 160 | 126.6667 | 0.4 | 36 | 56 | 75 | 55.8333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-010 | Project_011_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Rework required following integration of Customer System | Person_142 | 2013-08-21 01:00 | 2017-05-21 | 0.4 | 0.66881 | 0.26753 | Reduce | 0.4 | 0.66881 | 0.26753 | H2 | 4 | Stable | 0.6 | 101 | 127 | 145 | 125.6667 | 0.3 | 15 | 41 | 60 | 39.8333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 0.098873 | 0.0098873 | Accept | 0.2 | 0.098873 | 0.0098873 | H2 | 4 | Stable | 0.7 | 117 | 132 | 158 | 133.8333 | 0.7 | 117 | 132 | 158 | 133.8333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-02-20 01:00 | 2018-08-21 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.5 | 107 | 133 | 142 | 130.1667 | 0.2 | 21 | 54 | 76 | 52.1667 |  | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Pick up and Drop off of Software Resource | Person_230 | 2017-04-21 | 2018-02-19 01:00 | 0.4 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-109 | Project_011_Risk-109 | Opportunitity | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Environment complexity | Person_187 | 2016-07-21 | 2018-08-21 | 0.25 | 0.14661 | 0.036651 | -- | 0.25 | 0.14661 | 0.036651 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-108 | Project_011_Risk-108 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Offer additional functionality to the customer | Person_147 | 2017-04-22 | 2018-08-21 | 0.1 | 0.34094 | 0.034094 | -- | 0.1 | 0.34094 | 0.034094 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 0.2 | 0.12388 | 0.024775 | Reduce | 0.2 | 0.12388 | 0.024775 | H2 | 4 | Stable | 0.6 | 94 | 131 | 148 | 127.6667 | 0.4 | 32 | 56 | 74 | 55 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 0.4 | 0.51141 | 0.20457 | Avoid | 0.4 | 0.51141 | 0.20457 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport Routes | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 0.49834 | 0.12459 | Accept | 0.15 | 0.49834 | 0.12459 | H2 | 4 | Stable | 0.6 | 82 | 132 | 149 | 126.5 | 0.6 | 82 | 132 | 149 | 126.5 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.2 | 0.10171 | 0.020343 | -- | 0.2 | 0.10171 | 0.020343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 0.3 | 0.28639 | 0.085917 | Reduce | 0.3 | 0.28639 | 0.085917 | H2 | 4 | Stable | 0.5 | 96 | 140 | 157 | 135.5 | 0.1 | 14 | 43 | 63 | 41.5 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 2. Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 0.25 | 0 | 0 | -- | 0.25 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2017-10-21 01:00 | 2018-05-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 0.3 | 0.10626 | 0.031878 | -- | 0.3 | 0.01932 | 0.005796 | H3 | 3 | Stable | [10 empty] | 81.8181 | 0 | 0 | 49.0909
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Internal Quality Issues | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 1.0052 | 0.35182 | Accept | 0.2 | 1.0052 | 0.35182 | H2 | 4 | Stable | 0.7 | 100 | 138 | 160 | 135.3333 | 0.7 | 100 | 138 | 160 | 135.3333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-118 | Project_011_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer change environment | Person_187 | 2013-08-21 01:00 | 2018-08-21 | 0.1 | 0 | 0 | Avoid | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Obsolescence Monitoring Risk | Person_181 | 2016-12-02 21:00 | 2017-01-19 21:00 | 0.3 | 5.9458 | 1.7837 | Reduce | 0.15 | 0.9786 | 0.14679 | H3 | 3 | Stable | 0.9 | 119 | 128 | 159 | 131.6667 | 0.3 | 2 | 43 | 72 | 41 | 83.5413 | 50 | 0 | 50.1248
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk017 | Project_042_Risk017 | Threat | Financial Contingency | Open | H2 | 4 | 6. Contractual/Legal | Liquidated Damages | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 3.0903 | 0.61807 | Accept | 0.4 | 3.0903 | 0.61807 | H2 | 4 | Stable | 0.8 | 101 | 121 | 157 | 123.6667 | 0.8 | 101 | 121 | 157 | 123.6667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Repairs | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 30.9033 | 7.7258 | Accept | 0.25 | 30.9033 | 7.7258 | H2 | 4 | Stable | 0.8 | 93 | 140 | 141 | 132.3333 | 0.8 | 93 | 140 | 141 | 132.3333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk016 | Project_042_Risk016 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport/Delivery Speed | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 35.0206 | 7.0041 | Accept | 0.1 | 35.0206 | 7.0041 | H2 | 4 | Stable | 0.9 | 106 | 128 | 155 | 128.8333 | 0.9 | 106 | 128 | 155 | 128.8333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Country Stability | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 15.0654 | 6.7794 | Accept | 0.4 | 15.0654 | 6.7794 | H2 | 4 | Stable | 0.6 | 117 | 123 | 147 | 126 | 0.6 | 117 | 123 | 147 | 126 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-08-20 01:00 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.6 | 114 | 133 | 155 | 133.5 | 0.3 | 17 | 40 | 78 | 42.5 | 50 | 28.5714 | 0 | 30
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-02-19 01:00 | 0.5 | 17.2826 | 8.6413 | Reduce | 0.15 | 17.2826 | 2.5924 | H2 | 4 | Improving | 0.9 | 84 | 140 | 147 | 131.8333 | 0.3 | 9 | 45 | 66 | 42.5 | 0 | 70 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_427 | 2012-11-20 01:00 | 2017-06-22 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.7 | 108 | 138 | 149 | 134.8333 | 0.3 | 22 | 40 | 64 | 41 | 0 | 50 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2016-07-20 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.4 | 12.6474 | 5.059 | H2 | 4 | Stable | 0.7 | 119 | 128 | 148 | 129.8333 | 0.4 | 38 | 48 | 64 | 49 | 0 | 33.3333 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2017-08-19 01:00 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.9 | 119 | 123 | 148 | 126.5 | 0.1 | 5 | 49 | 71 | 45.3333 | 0 | 50 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target. | Person_482 | 2013-01-07 01:00 | 2017-06-06 | 0.3 | 4.7676 | 1.4303 | Reduce | 0.15 | 4.7676 | 0.71514 | H2 | 4 | Stable | 0.8 | 118 | 135 | 143 | 133.5 | 0.2 | 5 | 54 | 72 | 48.8333 | 0 | 50 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 01:00 | 2017-08-20 01:00 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.7 | 118 | 122 | 147 | 125.5 | 0.1 | 17 | 56 | 67 | 51.3333 | 0 | 33.3333 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2017-05-21 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Worsening | 0.9 | 99 | 121 | 151 | 122.3333 | 0.3 | 5 | 54 | 73 | 49 | 0 | 57.1429 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-05-21 | 0.8 | 0 | 0 | Reduce | 0.6 | 0 | 0 | H1 | 5 | Worsening | 0.7 | 104 | 139 | 160 | 136.6667 | 0.1 | 24 | 44 | 63 | 43.8333 |  | 25 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-05-21 | 0.8 | 1.3243 | 1.0595 | Reduce | 0.6 | 1.3243 | 0.7946 | H1 | 5 | Worsening | 0.6 | 91 | 133 | 155 | 129.6667 | 0.3 | 2 | 44 | 63 | 40.1667 | 0 | 25 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2017-06-22 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.8 | 112 | 131 | 147 | 130.5 | 0.2 | 30 | 53 | 79 | 53.5 |  | 50 | 1
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 1 | 0 | 0 | H1 | 5 | Stable | 0.5 | 103 | 123 | 148 | 123.8333 | 0.3 | 21 | 59 | 67 | 54 |  | -100 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.5 | 94 | 139 | 144 | 132.3333 | 0.4 | 38 | 58 | 70 | 56.6667 |  | 60 | 1
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-08-20 01:00 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.5 | 117 | 128 | 154 | 130.5 | 0.2 | 8 | 58 | 63 | 50.5 | 7.8429 | 40 | 0 | 4.7058
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R050 | Project_021_Risk-R050 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to failure of Customer modification Telemetry | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 0.2 | 2.5604 | 0.51208 | Reduce | 0.02 | 2.0527 | 0.041055 | H2 | 4 | Improving | 0.5 | 86 | 132 | 141 | 125.8333 | 0.1 | 31 | 50 | 63 | 49 | 19.8277 | 90 | 0 | 11.8966
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R053 | Project_021_Risk-R053 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.9 | 104 | 138 | 159 | 135.8333 | 0.4 | 20 | 53 | 61 | 48.8333 |  | 60 | 1
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 0.02 | 0 | 0 | Reduce | 0.01 | 0 | 0 | H3 | 3 | Stable | 0.6 | 110 | 140 | 148 | 136.3333 | 0.4 | 5 | 49 | 70 | 45.1667 |  | 50 | 1
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R052 | Project_021_Risk-R052 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.6 | 0 | 0 | H1 | 5 | Stable | 0.9 | 103 | 140 | 150 | 135.5 | 0.4 | 35 | 46 | 69 | 48 |  | -20 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R055 | Project_021_Risk-R055 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to lack of personnel resource | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 110 | 128 | 160 | 130.3333 | 0.1 | 28 | 44 | 63 | 44.5 |  | 66.6667 | 1
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 0.3 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 94 | 133 | 156 | 130.3333 | 0.1 | 7 | 57 | 75 | 51.6667 |  | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 85 | 124 | 150 | 121.8333 | 0.2 | 26 | 46 | 77 | 47.8333 |  | 66.6667 | 1
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-08-06 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.6 | 90 | 127 | 156 | 125.6667 | 0.4 | 34 | 55 | 61 | 52.5 |  | 80 | 1
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2017-06-22 | 0.3 | 1.076 | 0.32281 | Reduce | 0.05 | 1.076 | 0.053801 | H2 | 4 | Improving | 0.5 | 83 | 131 | 154 | 126.8333 | 0.1 | 9 | 49 | 68 | 45.5 | 0 | 83.3333 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-13 01:00 | 2017-05-07 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.8 | 98 | 125 | 156 | 125.6667 | 0.2 | 27 | 50 | 67 | 49 | 80 | 66.6667 | 0 | 48
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-07-21 | 2018-01-20 01:00 | 0.1 | 0.48559 | 0.048559 | Reduce | 0.1 | 0.48559 | 0.048559 | H2 | 4 | Stable | 0.7 | 105 | 129 | 143 | 127.3333 | 0.4 | 9 | 41 | 78 | 41.8333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.41 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -2.5 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.61 | 0.25667 | 0.15657 | Reduce | 0.5 | 0.25667 | 0.12834 | H2 | 4 | Stable | 0.7 | 88 | 132 | 159 | 129.1667 | 0.3 | 38 | 44 | 65 | 46.5 | 0 | 18.0328 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2014-01-21 01:00 | 2017-11-20 01:00 | 0.4 | 1.078 | 0.43121 | Reduce | 0.4 | 1.4673 | 0.58692 | H2 | 4 | Improving | 0.7 | 113 | 127 | 155 | 129.3333 | 0.3 | 29 | 51 | 71 | 50.6667 | -36.1112 | 0 | 0 | -21.6667
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-118 | Project_029_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Acceptance Schedule is longer in duration/delayed due to unplanned events. [Hardware availability] | Person_102 | 2017-01-21 01:00 | 2017-05-23 | 0.55 | 1.3775 | 0.75761 | Reduce | 0.55 | 1.3775 | 0.75761 | H2 | 4 | Stable | 0.7 | 94 | 121 | 146 | 120.6667 | 0.2 | 33 | 40 | 71 | 44 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2017-11-19 01:00 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2017-09-20 01:00 | 0.6 | 0.89835 | 0.53901 | Transfer | 0.6 | 0.89835 | 0.53901 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 0.35 | 0.85557 | 0.29945 | Reduce | 0.35 | 1.9208 | 0.67227 | H2 | 4 | Stable | 0.6 | 91 | 122 | 159 | 123 | 0.1 | 30 | 52 | 75 | 52.1667 | -124.5001 | 0 | 0 | -74.7001
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 0.77001 | 0.30801 | Accept | 0.1 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.6 | 103 | 129 | 147 | 127.6667 | 0.6 | 103 | 129 | 147 | 127.6667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2018-02-20 01:00 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.6 | 89 | 122 | 150 | 121.1667 | 0.4 | 4 | 59 | 72 | 52 | 0 | 28.5714 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 1.54 | 0.30801 | Accept | 0.2 | 0.77001 | 0.154 | H2 | 4 | Stable | 0.8 | 112 | 130 | 141 | 128.8333 | 0.8 | 112 | 130 | 141 | 128.8333 | 50 | 0 | 0 | 30
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 0.5 | 0.94968 | 0.28491 | Accept | 0.5 | 0.94968 | 0.18994 | H2 | 4 | Improving | 0.8 | 111 | 124 | 160 | 127.8333 | 0.8 | 111 | 124 | 160 | 127.8333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 0.3 | 27.1644 | 0.81493 | Accept | 0.3 | 12.8336 | 1.2834 | H2 | 4 | Stable | 0.5 | 88 | 129 | 159 | 127.1667 | 0.5 | 88 | 129 | 159 | 127.1667 | 52.7559 | 0 | 0 | 31.6535
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2014-07-22 | 2017-11-19 01:00 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.9 | 115 | 138 | 150 | 136.1667 | 0.4 | 14 | 59 | 64 | 52.3333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2017-10-14 01:00 | 0.41 | 6.4168 | 2.6309 | Transfer | 0.41 | 0 | 0 | H1 | 5 | Stable | [10 empty] | 100 | 0 | 0 | 60
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub-system FPGA | Person_216 | 2017-01-21 01:00 | 2017-08-20 01:00 | 0.3 | 1.54 | 0.46201 | Reduce | 0.4 | 1.5914 | 0.63655 | H2 | 4 | Stable | 0.7 | 89 | 133 | 160 | 130.1667 | 0.3 | 10 | 58 | 74 | 52.6667 | -3.3333 | -33.3333 | 0 | -2
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SystemC HW/SW | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.3 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.9 | 113 | 138 | 158 | 137.1667 | 0.3 | 16 | 50 | 61 | 46.1667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs [technical scope] | Person_466 | 2017-01-21 01:00 | 2019-07-21 | 0.35 | 9.505 | 3.3267 | Reduce | 0.35 | 9.505 | 3.3267 | H2 | 4 | Stable | 0.8 | 118 | 138 | 146 | 136 | 0.4 | 8 | 49 | 60 | 44 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.5 | 3.5934 | 1.7967 | H2 | 4 | Stable | 0.6 | 106 | 124 | 146 | 124.6667 | 0.1 | 10 | 42 | 60 | 39.6667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | HW - additional unplanned design effort | Person_216 | 2016-05-23 | 2019-10-21 01:00 | 0.4 | 3.3367 | 1.3347 | Reduce | 0.4 | 3.3367 | 1.3347 | H2 | 4 | Stable | 0.6 | 92 | 127 | 160 | 126.6667 | 0.3 | 5 | 49 | 62 | 43.8333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R013 | Project_016_Risk--R013 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Resource Availability (Threat) | Person_697 | 2016-04-02 | 2019-08-01 | 0.2 | 3.9356 | 0.98391 | Accept | 0.2 | 4.2779 | 1.0695 | H2 | 4 | Worsening | 0.9 | 119 | 123 | 151 | 127 | 0.9 | 119 | 123 | 151 | 127 | -8.6957 | 0 | 0 | -5.2174
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 0.05 | 2.5667 | 0.77001 | Accept | 0.05 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.5 | 92 | 126 | 148 | 124 | 0.5 | 92 | 126 | 148 | 124 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design | Person_216 | 2016-05-23 | 2017-07-20 | 0.2 | 2.6951 | 0.53901 | Reduce | 0.2 | 2.6951 | 0.53901 | H3 | 3 | Improving | 0.7 | 91 | 124 | 158 | 124.1667 | 0.4 | 31 | 55 | 69 | 53.3333 | 0 | 0 | 1 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_692 | 2016-12-21 01:00 | 2017-12-19 01:00 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Stable | 0.9 | 95 | 128 | 154 | 126.8333 | 0.1 | 17 | 59 | 70 | 53.8333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_692 | 2017-05-23 | 2019-07-21 | 0.333 | 11.5502 | 3.8462 | Reduce | 0.333 | 11.5502 | 3.8462 | H2 | 4 | Stable | 0.7 | 91 | 136 | 147 | 130.3333 | 0.1 | 32 | 50 | 70 | 50.3333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK225 | Project_024_RISK225 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | More testing required as a result compliance to Platform Risk | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 5.6866 | 2.8433 | Reduce | 0.5 | 5.6866 | 2.8433 | H1 | 5 | Stable | 0.8 | 81 | 140 | 147 | 131.3333 | 0.2 | 7 | 54 | 68 | 48.5 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.5 | 98 | 128 | 157 | 127.8333 | 0.2 | 37 | 48 | 60 | 48.1667 | 0 | 60 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK286 | Project_024_RISK286 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Requirement sell off more difficult than expected | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 10.1787 | 5.0893 | Reduce | 0.5 | 10.1787 | 5.0893 | H1 | 5 | Worsening | 0.5 | 83 | 134 | 153 | 128.6667 | 0.4 | 38 | 46 | 65 | 47.8333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK288 | Project_024_RISK288 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Unplanned obsolescence and/or repairs to rig assets. | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.6 | 5.8424 | 3.5054 | Reduce | 0.6 | 4.9768 | 2.9861 | H1 | 5 | Stable | 0.7 | 116 | 134 | 145 | 132.8333 | 0.2 | 18 | 46 | 60 | 43.6667 | 14.8148 | 0 | 0 | 8.8889
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.5 | 3.843 | 1.9215 | H1 | 5 | Stable | 0.7 | 98 | 133 | 157 | 131.1667 | 0.3 | 21 | 54 | 71 | 51.3333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Overland performance | Person_448 | 2016-06-23 | 2017-05-21 | 0.1 | 1.6835 | 0.16835 | Reduce | 0.1 | 3.5011 | 0.35011 | H3 | 3 | Improving | 0.9 | 118 | 135 | 152 | 135 | 0.2 | 26 | 56 | 78 | 54.6667 | -107.9692 | 0 | 1 | -64.7815
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK213 | Project_024_RISK213 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Rigs requireaccreditation as "Special to Type" Test equipment | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.3 | 38.17 | 11.451 | Reduce | 0.25 | 19.4745 | 4.8686 | H2 | 4 | Stable | 0.9 | 116 | 123 | 160 | 128 | 0.2 | 22 | 45 | 70 | 45.3333 | 48.9796 | 16.6667 | 0 | 29.3878
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK256 | Project_024_RISK256 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unable to meet spare capacity requirement | Person_318 | 2016-07-21 | 2018-01-21 01:00 | 0.8 | 0.12983 | 0.10386 | Reduce | 0.05 | 0.12983 | 0.0064915 | H3 | 3 | Stable | 0.6 | 94 | 126 | 153 | 125.1667 | 0.1 | 1 | 44 | 71 | 41.3333 | 0 | 93.75 | 1 | 2.8125
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK219 | Project_024_RISK219 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | STTE additional work | Person_710 | 2016-09-20 01:00 | 2017-07-21 | 0.5 | 15.0863 | 7.5431 | Reduce | 0.5 | 15.0863 | 7.5431 | H1 | 5 | Worsening | 0.7 | 82 | 126 | 145 | 121.8333 | 0.2 | 13 | 40 | 78 | 41.8333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK218 | Project_024_RISK218 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | System issues general | Person_388 | 2016-08-21 01:00 | 2017-05-14 | 0.4 | 90.8811 | 36.3524 | Reduce | 0.3 | 39.3904 | 11.8171 | H1 | 5 | Stable | 0.8 | 112 | 122 | 144 | 124 | 0.3 | 7 | 40 | 62 | 38.1667 | 56.6571 | 25 | 0 | 33.9943
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK261 | Project_024_RISK261 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Viewer may not work | Person_318 | 2016-05-23 | 2017-04-21 | 0.5 | 3.9382 | 1.9691 | Reduce | 0.1 | 3.9382 | 0.39382 | H3 | 3 | Improving | 0.5 | 98 | 135 | 157 | 132.5 | 0.2 | 23 | 49 | 60 | 46.5 | 0 | 80 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.2 | 20.8767 | 4.1753 | H2 | 4 | Stable | 0.9 | 88 | 126 | 159 | 125.1667 | 0.3 | 37 | 43 | 78 | 47.8333 | 50 | 50 | 0 | 30
2017-01-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2017-02-19 01:00 | 0.05 | 29.1079 | 19.2112 | Accept | 0.05 | 14.1671 | 7.2252 | H3 | 3 | Improving | 0.6 | 99 | 124 | 154 | 124.8333 | 0.6 | 99 | 124 | 154 | 124.8333 | 51.3292 | 0 | 1 | 30.7975
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.48 | 76.3401 | 36.6432 | Reduce | 0.2858 | 57.5537 | 16.4488 | H1 | 5 | Worsening | 0.7 | 107 | 137 | 157 | 135.3333 | 0.4 | 24 | 45 | 65 | 44.8333 | 24.6088 | 40.4583 | 0 | 14.7653
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.05 | 32.4575 | 1.2983 | Accept | 0.05 | 32.4575 | 1.2983 | H2 | 4 | Stable | 0.9 | 106 | 126 | 153 | 127.1667 | 0.9 | 106 | 126 | 153 | 127.1667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 0.8 | 25.966 | 7.7898 | Accept | 0.6 | 10.3864 | 3.1159 | H1 | 5 | Stable | 0.8 | 101 | 130 | 158 | 129.8333 | 0.8 | 101 | 130 | 158 | 129.8333 | 60 | 25 | 0 | 36
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 01:00 | 2016-08-20 01:00 | 0.1 | 62.3617 | 3.1181 | Accept | 0.1 | 62.3617 | 3.1181 | H2 | 4 | Stable | 0.9 | 87 | 122 | 157 | 122 | 0.9 | 87 | 122 | 157 | 122 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 0.2 | 4.5441 | 0.45441 | Accept | 0.2 | 4.5441 | 0.45441 | H3 | 3 | Improving | 0.5 | 111 | 132 | 145 | 130.6667 | 0.5 | 111 | 132 | 145 | 130.6667 | 0 | 0 | 1 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK179 | Project_024_RISK179 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Testing Required | Person_710 | 2016-12-21 01:00 | 2017-05-22 | 0.5 | 3.5054 | 1.7527 | Avoid | 0.4 | 3.5054 | 1.4022 | H2 | 4 | Stable | [10 empty] | 0 | 20 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Risk of not being able to perform Tests | Person_238 | 2017-12-21 01:00 | 2019-01-21 01:00 | 0.5 | 30.2764 | 12.1106 | Accept | 0.5 | 30.2764 | 12.1106 | H2 | 4 | Stable | 0.5 | 119 | 124 | 142 | 126.1667 | 0.5 | 119 | 124 | 142 | 126.1667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_238 | 2017-05-23 | 2019-01-21 01:00 | 0.5 | 11.9444 | 5.9722 | Accept | 0.5 | 11.9444 | 5.9722 | H2 | 4 | Stable | 0.6 | 87 | 134 | 157 | 130 | 0.6 | 87 | 134 | 157 | 130 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK180 | Project_024_RISK180 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | High Accelerated Life Testing (HALT) | Person_710 | 2014-12-22 01:00 | 2019-05-23 | 0.4 | 10.4903 | 4.1961 | Avoid | 0.2 | 10.4903 | 2.0981 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_693 | 2017-03-23 | 2017-09-19 01:00 | 0.6 | 35.885 | 25.4784 | Accept | 0.6 | 15.3199 | 4.596 | H2 | 4 | Stable | 0.5 | 81 | 140 | 159 | 133.3333 | 0.5 | 81 | 140 | 159 | 133.3333 | 57.3082 | 0 | 0 | 34.3849
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_058 | 2017-03-23 | 2018-05-22 | 0.1 | 30.7697 | 15.0772 | Accept | 0.1 | 13.0349 | 3.9105 | H3 | 3 | Stable | 0.8 | 106 | 121 | 147 | 122.8333 | 0.8 | 106 | 121 | 147 | 122.8333 | 57.6371 | 0 | 1 | 34.5823
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R06 | Project_041_R06 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Additional PM time to support the supply chain | Person_058 | 2017-03-23 | 2017-09-19 01:00 | 0.5 | 14.541 | 5.8164 | Accept | 0.5 | 14.541 | 5.8164 | H2 | 4 | Stable | 0.6 | 120 | 135 | 144 | 134 | 0.6 | 120 | 135 | 144 | 134 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_073 | 2016-05-23 | 2017-02-19 01:00 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.6 | 81 | 136 | 156 | 130.1667 | 0.1 | 3 | 40 | 61 | 37.3333 | 0 | 50 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_413 | 2015-11-21 01:00 | 2017-05-22 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.6 | 114 | 134 | 144 | 132.3333 | 0.3 | 27 | 41 | 60 | 41.8333 | 0 | 5 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.8 | 8.7765 | 7.0212 | Reduce | 0.45 | 8.7765 | 3.9494 | H1 | 5 | Stable | 0.9 | 85 | 136 | 148 | 129.5 | 0.3 | 18 | 44 | 72 | 44.3333 | 0 | 43.75 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2017-04-21 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.35 | 2.8688 | 1.0041 | H2 | 4 | Stable | 0.8 | 118 | 133 | 142 | 132 | 0.2 | 4 | 46 | 62 | 41.6667 | 22.0253 | 56.25 | 0 | 13.2152
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R81 | Project_041_R81 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Re-imaging of PC's - additional material | Person_515 | 2017-03-23 | 2017-10-21 01:00 | 0.5 | 2.3975 | 2.3975 | Accept | 0.25 | 14.5644 | 14.5644 | H2 | 4 | Improving | 0.7 | 89 | 132 | 153 | 128.3333 | 0.7 | 89 | 132 | 153 | 128.3333 | -507.4848 | 50 | 0 | -304.4909
2017-01-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2017-04-21 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 0.65554 | 0.52443 | H2 | 4 | Stable | [10 empty] | 80.45 | 0 | 0 | 48.27
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 0.2 | 3.1818 | 1.5909 | Accept | 0.2 | 3.1818 | 1.5909 | H2 | 4 | Stable | 0.7 | 104 | 125 | 141 | 124.1667 | 0.7 | 104 | 125 | 141 | 124.1667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 0.25 | 3.8666 | 1.5853 | Accept | 0.25 | 1.3288 | 0.5448 | H3 | 3 | Stable | 0.9 | 101 | 140 | 153 | 135.6667 | 0.9 | 101 | 140 | 153 | 135.6667 | 65.6338 | 0 | 0 | 39.3803
2017-01-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2017-03-22 | 0.85 | 25.2325 | 21.4476 | Avoid | 0.08 | 20.8758 | 1.6701 | H2 | 4 | Stable | [10 empty] | 17.2662 | 90.5882 | 0 | 10.3597
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | More issues than expected during Qualification | Person_147 | 2017-04-22 | 2017-11-04 01:00 | 0.35 | 5.4459 | 1.6338 | Accept | 0.35 | 0.18151 | 0.054453 | H1 | 5 | Stable | 0.9 | 98 | 125 | 146 | 124 | 0.9 | 98 | 125 | 146 | 124 | 96.667 | 0 | 0 | 58.0002
2017-01-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2017-03-22 | 0.7 | 24.1887 | 16.9321 | Reduce | 0.25 | 4.3567 | 1.0892 | H2 | 4 | Stable | 0.9 | 92 | 138 | 143 | 131.1667 | 0.3 | 36 | 56 | 60 | 53.3333 | 81.9887 | 64.2857 | 0 | 49.1932
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-148 | Project_020_Risk-148 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs non-available items | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.3 | 14.9935 | 4.498 | Reduce | 0.3 | 14.9935 | 4.498 | H2 | 4 | Stable | 0.8 | 120 | 130 | 148 | 131.3333 | 0.2 | 8 | 58 | 63 | 50.5 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-22 01:00 | 2017-05-22 | 0.25 | 7.4225 | 1.8556 | Reduce | 0.1 | 2.0081 | 0.20081 | H3 | 3 | Stable | 0.8 | 108 | 125 | 150 | 126.3333 | 0.2 | 38 | 55 | 77 | 55.8333 | 72.9455 | 60 | 0 | 43.7673
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 2.6991 | 1.0796 | H2 | 4 | Stable | 0.7 | 105 | 127 | 149 | 127 | 0.4 | 6 | 41 | 74 | 40.6667 | 31.8182 | 20 | 0 | 19.0909
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-147 | Project_020_Risk-147 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component taking longer to refurbish in country | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.6 | 6.7477 | 4.0486 | Reduce | 0.6 | 6.7477 | 4.0486 | H2 | 4 | Stable | 0.8 | 101 | 127 | 159 | 128 | 0.2 | 17 | 55 | 73 | 51.6667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-150 | Project_020_Risk-150 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Power supply Test Environment | Person_248 | 2016-10-21 01:00 | 2017-05-22 | 0.6 | 6.7477 | 4.0486 | Reduce | 0.6 | 6.7477 | 4.0486 | H2 | 4 | Worsening | 0.8 | 84 | 138 | 149 | 130.8333 | 0.4 | 39 | 40 | 77 | 46 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_575 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 5.0983 | 0.76474 | H3 | 3 | Stable | 0.6 | 107 | 131 | 141 | 128.6667 | 0.1 | 26 | 56 | 79 | 54.8333 | 19.0479 | 70 | 1 | 13.5287
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-12-21 01:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.6 | 91 | 137 | 141 | 130 | 0.2 | 11 | 57 | 61 | 50 | 47 | 0 | 0 | 28.2
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-12-21 01:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-19 01:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.2 | 1.5935 | 0.3187 | H3 | 3 | Stable | 0.5 | 116 | 139 | 159 | 138.5 | 0.3 | 8 | 43 | 67 | 41.1667 | 50 | 50 | 1 | 31.5
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 0.4 | 9.139 | 3.6556 | Avoid | 0.2 | 9.139 | 1.8278 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 0.125 | 232.2192 | 29.0274 | -- | 0.215 | 27.8663 | 5.9913 | H2 | 4 | Stable | [10 empty] | 88 | -72 | 0 | 52.8
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 0.5 | 13.7833 | 6.8917 | Avoid | 0.2 | 6.8917 | 1.3783 | H3 | 3 | Stable | [10 empty] | 50 | 60 | 1 | 31.8
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-20 01:00 | 0.3 | 5.5433 | 1.663 | Reduce | 0.35 | 5.5433 | 1.9402 | H2 | 4 | Worsening | 0.8 | 106 | 123 | 145 | 123.8333 | 0.3 | 7 | 52 | 66 | 46.8333 | 0 | -16.6667 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Worsening | [10 empty] | 0 | 75 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2017-02-20 01:00 | 2019-07-21 | 0.4 | 4.4946 | 1.1236 | Accept | 0.3 | 4.4946 | 0.44946 | H2 | 4 | Stable | 0.7 | 114 | 131 | 157 | 132.5 | 0.7 | 114 | 131 | 157 | 132.5 | 0 | 25 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2019-10-14 01:00 | 0.2 | 6.7418 | 1.6855 | Accept | 0.2 | 6.7418 | 1.0113 | H3 | 3 | Stable | 0.7 | 117 | 125 | 144 | 126.8333 | 0.7 | 117 | 125 | 144 | 126.8333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 0.3 | 26.9674 | 8.0902 | Avoid | 0.3 | 14.9819 | 4.4946 | H2 | 4 | Stable | [10 empty] | 44.4444 | 0 | 0 | 26.6667
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-21 01:00 | 0.5 | 26.9674 | 13.4837 | Avoid | 0.1 | 12.7646 | 1.2765 | H2 | 4 | Worsening | [10 empty] | 52.6667 | 80 | 0 | 31.6
2017-01-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 01:00 | 2016-05-21 | 0.5 | 4.3921 | 2.196 | Reduce | 0.3 | 4.3921 | 1.3176 | H1 | 5 | Stable | 0.9 | 111 | 128 | 151 | 129 | 0.2 | 7 | 41 | 73 | 40.6667 | 0 | 40 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Non-Recurring Engineering higher than expected | Person_674 | 2016-06-01 | 2016-08-04 | 0.4 | 6.5968 | 2.6387 | Reduce | 0.2 | 6.5944 | 1.3189 | H3 | 3 | Improving | 0.9 | 105 | 137 | 144 | 132.8333 | 0.3 | 5 | 48 | 70 | 44.5 | 0.036395 | 50 | 0 | 0.021837
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2019-07-21 | 0.3 | 1.2004 | 0.24009 | Accept | 0.2 | 1.2004 | 0.24009 | H3 | 3 | Stable | 0.6 | 98 | 129 | 150 | 127.3333 | 0.6 | 98 | 129 | 150 | 127.3333 | 0 | 33.3333 | 1 | 1
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-117 | Project_039_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Filters | Person_185 | 2015-01-21 01:00 | 2016-12-19 01:00 | 0.1 | 3.005 | 0.3005 | Reduce | 0.1 | 3.005 | 0.3005 | H3 | 3 | Stable | 0.8 | 118 | 138 | 154 | 137.3333 | 0.2 | 18 | 55 | 73 | 51.8333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 0.35617 | 0.10685 | Accept | 0.1 | 0.35617 | 0.10685 | H2 | 4 | Stable | 0.5 | 104 | 127 | 160 | 128.6667 | 0.5 | 104 | 127 | 160 | 128.6667 | 0 | -233.3333 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 1.8602 | 0.55807 | Accept | 0.25 | 1.8602 | 0.55807 | H2 | 4 | Stable | 0.5 | 88 | 122 | 142 | 119.6667 | 0.5 | 88 | 122 | 142 | 119.6667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of Batch 2 Re-Design | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 1.4882 | 0.44646 | Accept | 0.3 | 1.4882 | 0.44646 | H2 | 4 | Stable | 0.7 | 119 | 124 | 148 | 127.1667 | 0.7 | 119 | 124 | 148 | 127.1667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2017-02-20 01:00 | 2018-05-22 | 0.1 | 1.4882 | 0.44646 | Accept | 0.1 | 1.4882 | 0.44646 | H3 | 3 | Stable | 0.9 | 94 | 129 | 150 | 126.6667 | 0.9 | 94 | 129 | 150 | 126.6667 | 0 | 0 | 1 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK306(028) | Project_024_RISK306(028) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | HW repairs required on units | Person_119 | 2016-11-19 01:00 | 2018-11-20 01:00 | 0.3 | 2.813 | 0.8439 | Reduce | 0.2 | 2.813 | 0.5626 | H2 | 4 | Stable | 0.9 | 113 | 140 | 147 | 136.6667 | 0.2 | 12 | 53 | 73 | 49.5 | 0 | 33.3333 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 0.3 | 0.5626 | 0.14065 | Accept | 0.3 | 0.5626 | 0.14065 | H2 | 4 | Improving | 0.8 | 120 | 122 | 143 | 125.1667 | 0.8 | 120 | 122 | 143 | 125.1667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_288 | 2017-02-22 01:00 | 2017-11-19 01:00 | 0.3 | 5.1932 | 2.0773 | Accept | 0.3 | 5.1716 | 2.0686 | H2 | 4 | Improving | 0.8 | 87 | 138 | 141 | 130 | 0.8 | 87 | 138 | 141 | 130 | 0.41665 | 0 | 0 | 0.24999
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK209 | Project_024_RISK209 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Major Return to Service | Person_073 | 2016-11-20 01:00 | 2017-05-22 | 0.3 | 5.1932 | 1.2983 | Accept | 0.3 | 5.1932 | 1.2983 | H2 | 4 | Stable | 0.9 | 90 | 137 | 152 | 131.6667 | 0.9 | 90 | 137 | 152 | 131.6667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK291 | Project_024_RISK291 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | LoE Engineering support required post completion in addition to BCR | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 5.3577 | 1.3394 | Accept | 0.5 | 5.3577 | 1.3394 | H1 | 5 | Worsening | 0.7 | 98 | 138 | 156 | 134.3333 | 0.7 | 98 | 138 | 156 | 134.3333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK302(024) | Project_024_RISK302(024) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | On time provision of platform units | Person_119 | 2016-11-19 01:00 | 2019-05-23 | 0.25 | 2.3889 | 0.59722 | Reduce | 0.15 | 2.3889 | 0.35833 | H2 | 4 | Stable | 0.8 | 97 | 122 | 157 | 123.6667 | 0.4 | 28 | 52 | 78 | 52.3333 | 0 | 40 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK210 | Project_024_RISK210 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Performance impacts regualotory complaince | Person_534 | 2016-06-22 | 2017-02-19 01:00 | 0.3 | 4.8297 | 1.6904 | Accept | 0.3 | 4.8297 | 1.6904 | H2 | 4 | Stable | 0.6 | 118 | 126 | 150 | 128.6667 | 0.6 | 118 | 126 | 150 | 128.6667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK222 | Project_024_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Testing Extends beyond target completion | Person_351 | 2017-07-21 | 2018-08-21 | 0.2 | 5.1067 | 1.0213 | Accept | 0.2 | 5.1067 | 1.0213 | H2 | 4 | Stable | 0.8 | 84 | 130 | 144 | 124.6667 | 0.8 | 84 | 130 | 144 | 124.6667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK237 | Project_024_RISK237 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer coding standard Compliance | Person_534 | 2017-05-25 | 2018-01-27 01:00 | 0.2 | 0.5626 | 0.19691 | Accept | 0.2 | 0.5626 | 0.19691 | H2 | 4 | Stable | 0.5 | 107 | 132 | 156 | 131.8333 | 0.5 | 107 | 132 | 156 | 131.8333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-20 23:00 | 2016-08-20 23:00 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.8 | 110 | 128 | 151 | 128.8333 | 0.3 | 37 | 47 | 77 | 50.3333 | 0 | 16.6667 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Equipment environmental failure | Person_710 | 2016-05-23 | 2017-05-22 | 0.3 | 5.126 | 2.563 | Accept | 0.3 | 5.126 | 2.563 | H2 | 4 | Improving | 0.7 | 101 | 123 | 157 | 125 | 0.7 | 101 | 123 | 157 | 125 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Retained systems re-design or modification | Person_710 | 2016-08-20 01:00 | 2017-08-19 01:00 | 0.05 | 12.815 | 2.563 | Accept | 0.05 | 12.815 | 2.563 | H2 | 4 | Improving | 0.7 | 87 | 126 | 147 | 123 | 0.7 | 87 | 126 | 147 | 123 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.8 | 113 | 125 | 152 | 127.5 | 0.2 | 9 | 41 | 60 | 38.8333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Mission System not compatible with platform systems | Person_710 | 2016-07-21 | 2017-04-21 | 0.1 | 0 | 0 | Accept | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.5 | 85 | 132 | 146 | 126.5 | 0.5 | 85 | 132 | 146 | 126.5 |  | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Qual failure | Person_710 | 2016-06-22 | 2017-05-22 | 0.4 | 0 | 0 | Accept | 0.4 | 0 | 0 | H1 | 5 | Improving | 0.7 | 94 | 139 | 156 | 134.3333 | 0.7 | 94 | 139 | 156 | 134.3333 |  | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 19:00 | 2019-08-20 19:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.6 | 85 | 140 | 146 | 131.8333 | 0.4 | 22 | 51 | 67 | 48.8333 | 83.3333 | 88.8889 | 1 | 52.6667
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.8 | 92 | 132 | 145 | 127.5 | 0.2 | 32 | 47 | 68 | 48 | 72 | 0 | 0 | 43.2
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.6 | 86 | 140 | 147 | 132.1667 | 0.4 | 18 | 45 | 76 | 45.6667 | 47.7391 | 0 | 0 | 28.6435
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 19:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.5 | 96 | 135 | 148 | 130.6667 | 0.2 | 19 | 47 | 76 | 47.1667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.9 | 112 | 130 | 152 | 130.6667 | 0.4 | 8 | 53 | 60 | 46.6667 | 0 | 0 | 1 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-20 23:00 | 2016-08-20 23:00 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.5 | 87 | 124 | 152 | 122.5 | 0.1 | 24 | 58 | 79 | 55.8333 | 0 | 16.6667 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Additional minor point releases | Person_073 | 2016-05-23 | 2017-08-20 01:00 | 0.5 | 7.689 | 2.6911 | Accept | 0.5 | 7.689 | 2.6911 | H1 | 5 | Stable | 0.5 | 83 | 132 | 153 | 127.3333 | 0.5 | 83 | 132 | 153 | 127.3333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digital Video Chainredesign | Person_710 | 2016-06-22 | 2017-05-22 | 0.71 | 5.4336 | 1.3584 | Accept | 0.3 | 5.4336 | 1.3584 | H2 | 4 | Worsening | 0.5 | 109 | 140 | 148 | 136.1667 | 0.5 | 109 | 140 | 148 | 136.1667 | 0 | 57.7465 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK189 | Project_024_RISK189 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment integration - Audio and Video recording | Person_710 | 2016-08-20 01:00 | 2017-03-22 | 0.49 | 5.126 | 2.563 | Accept | 0.3 | 5.126 | 2.563 | H1 | 5 | Worsening | 0.8 | 107 | 134 | 143 | 131 | 0.8 | 107 | 134 | 143 | 131 | 0 | 38.7755 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_641 | 2016-05-23 | 2017-08-19 01:00 | 0.4 | 12.815 | 2.563 | Accept | 0.4 | 12.815 | 2.563 | H1 | 5 | Stable | 0.7 | 87 | 127 | 153 | 124.6667 | 0.7 | 87 | 127 | 153 | 124.6667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.8 | 100 | 140 | 157 | 136.1667 | 0.1 | 33 | 51 | 63 | 50 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 0.5 | 19.1935 | 1.5355 | Accept | 0.5 | 19.1935 | 1.5355 | H2 | 4 | Stable | 0.8 | 119 | 140 | 160 | 139.8333 | 0.8 | 119 | 140 | 160 | 139.8333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-189 | Project_027_Risk-189 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Major Component obsolescence | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 8.3972 | 2.5191 | Reduce | 0.08 | 8.3972 | 0.67177 | H2 | 4 | Stable | 0.5 | 92 | 135 | 150 | 130.3333 | 0.2 | 14 | 54 | 78 | 51.3333 | 0 | 73.3333 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 0.5 | 0 | 0 | Accept | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.9 | 116 | 127 | 159 | 130.5 | 0.9 | 116 | 127 | 159 | 130.5 |  | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-201 | Project_027_Risk-201 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Transition into Support | Person_027 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0.5 | 68.3768 | 34.1884 | Reduce | 0.05 | 38.387 | 1.9193 | H2 | 4 | Stable | 0.6 | 108 | 129 | 146 | 128.3333 | 0.2 | 8 | 42 | 65 | 40.1667 | 43.8597 | 90 | 0 | 26.3158
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-188 | Project_027_Risk-188 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Unidentified Technical Legacy Issue | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 20.0332 | 2.0033 | Reduce | 0.05 | 20.0332 | 1.0017 | H3 | 3 | Stable | 0.5 | 118 | 135 | 160 | 136.3333 | 0.3 | 18 | 53 | 73 | 50.5 | 0 | 50 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2017-08-19 01:00 | 0.2 | 0.90951 | 0.1819 | Reduce | 0.1 | 0.90951 | 0.090951 | H3 | 3 | Stable | 0.7 | 115 | 137 | 159 | 137 | 0.4 | 10 | 44 | 72 | 43 | 0 | 50 | 1 | 1.5
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-193 | Project_027_Risk-193 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | A greater number of arising technical queries | Person_110 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.3 | 13.7953 | 4.1386 | Reduce | 0.05 | 13.7953 | 0.68977 | H3 | 3 | Stable | 0.6 | 104 | 132 | 147 | 129.8333 | 0.2 | 17 | 43 | 74 | 43.8333 | 0 | 83.3333 | 1 | 2.5
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2017-06-22 | 0.3 | 5.4553 | 1.6366 | Reduce | 0.15 | 5.252 | 0.7878 | H2 | 4 | Stable | 0.7 | 98 | 132 | 144 | 128.3333 | 0.2 | 2 | 51 | 68 | 45.6667 | 3.7267 | 50 | 0 | 2.236
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 1.3215 | 0.39644 | Accept | 0.5 | 1.3215 | 0.13215 | H2 | 4 | Stable | 0.8 | 110 | 136 | 151 | 134.1667 | 0.8 | 110 | 136 | 151 | 134.1667 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2017-03-22 | 0.41 | 35.9878 | 21.5927 | Accept | 0.41 | 15.5947 | 0.77974 | H2 | 4 | Stable | 0.6 | 90 | 131 | 144 | 126.3333 | 0.6 | 90 | 131 | 144 | 126.3333 | 56.6667 | 0 | 0 | 34
2017-01-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-016 | Project_023_Risk-016 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Damage to equipment (Unable to replace due to obsolescence) | Person_703 | 2015-10-22 01:00 | 2017-01-20 01:00 | 0.3 | 27.5907 | 2.7591 | Accept | 0.3 | 27.5907 | 2.7591 | H2 | 4 | Stable | 0.9 | 93 | 127 | 143 | 124 | 0.9 | 93 | 127 | 143 | 124 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-149 | Project_020_Risk-149 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs to be returned to UK | Person_703 | 2016-12-21 01:00 | 2017-11-19 01:00 | 0.2 | 12.1982 | 2.4396 | Accept | 0.2 | 10.8428 | 1.0843 | H2 | 4 | Stable | 0.9 | 85 | 129 | 147 | 124.6667 | 0.9 | 85 | 129 | 147 | 124.6667 | 11.1111 | 0 | 0 | 6.6667
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Cable and connectors | Person_499 | 2015-11-21 01:00 | 2017-08-09 | 0.45 | 0.41338 | 0.18602 | Reduce | 0.2 | 0.41338 | 0.082677 | H2 | 4 | Stable | 0.6 | 85 | 138 | 150 | 131.1667 | 0.3 | 32 | 47 | 61 | 46.8333 | 0 | 55.5556 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | FOC Acceptance | Person_500 | 2015-11-21 01:00 | 2017-08-19 01:00 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.3 | 8.471 | 2.5413 | H2 | 4 | Stable | 0.8 | 86 | 127 | 155 | 124.8333 | 0.3 | 22 | 49 | 69 | 47.8333 | -99.9999 | 14.2857 | 0 | -59.9999
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 01:00 | 2016-11-20 01:00 | 0.25 | 0.40661 | 0.16264 | Accept | 0.1 | 0.40661 | 0.081321 | H3 | 3 | Stable | 0.7 | 116 | 133 | 158 | 134.3333 | 0.7 | 116 | 133 | 158 | 134.3333 | 0 | 60 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Furnished Equipmnet Condition | Person_371 | 2015-04-27 | 2017-08-19 01:00 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.7 | 108 | 140 | 152 | 136.6667 | 0.4 | 24 | 43 | 77 | 45.5 |  | 62.5 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-080 | Project_008_Risk-080 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Recovery of Costs | Person_565 | 2016-08-21 01:00 | 2017-05-21 | 0.5 | 23.6737 | 11.8369 | -- | 0.5 | 23.6737 | 11.8369 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-20 01:00 | 0.25 | 52.0822 | 23.437 | Accept | 0.15 | 52.0822 | 23.437 | H3 | 3 | Stable | 0.5 | 116 | 137 | 143 | 134.5 | 0.5 | 116 | 137 | 143 | 134.5 | 0 | 40 | 1 | 1.2
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-059 | Project_008_Risk-059 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Project Resource Efficencies | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 0.2 | 21.6852 | 4.337 | -- | 0.15 | 21.6852 | 3.2528 | H3 | 3 | Worsening | [10 empty] | 0 | 25 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Survey costs | Person_618 | 2016-04-22 | 2017-08-20 01:00 | 1 | 13.2573 | 13.2573 | Reduce | 0.3 | 13.2573 | 3.9772 | H3 | 3 | Improving | 0.9 | 82 | 136 | 141 | 127.8333 | 0.4 | 19 | 55 | 74 | 52.1667 | 0 | 70 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-079 | Project_008_Risk-079 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Regulations Phase 3 and 4 | Person_565 | 2016-10-21 01:00 | 2018-08-21 | 0.25 | 71.9682 | 17.992 | -- | 0.25 | 71.9682 | 17.992 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-111 | Project_039_Risk-111 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Maturation results inconclusive | Person_297 | 2016-02-21 01:00 | 2017-01-20 01:00 | 0.3 | 71.0212 | 21.3064 | Accept | 0.3 | 71.0212 | 21.3064 | H2 | 4 | Stable | 0.8 | 98 | 131 | 142 | 127.3333 | 0.8 | 98 | 131 | 142 | 127.3333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-195 | Project_039_Risk-195 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Supply Chain Delays - System Comms, Component, and subsystem | Person_083 | 2016-08-21 01:00 | 2017-02-19 01:00 | 0.3 | 13.3529 | 6.6765 | Accept | 0.3 | 23.5716 | 11.7858 | H3 | 3 | Worsening | 0.5 | 114 | 131 | 142 | 130 | 0.5 | 114 | 131 | 142 | 130 | -76.5278 | 0 | 0 | -45.9167
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 0.5 | 9.2728 | 4.6364 | Reduce | 0.15 | 9.2728 | 1.3909 | H2 | 4 | Stable | 0.9 | 96 | 139 | 160 | 135.3333 | 0.1 | 8 | 49 | 61 | 44.1667 | 0 | 70 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R008 | Project_016_Risk--R008 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Additional Travel & Subsistence | Person_574 | 2016-01-13 01:00 | 2019-05-23 | 0.4 | 8.9019 | 3.5608 | Reduce | 0.25 | 8.9019 | 2.2255 | H3 | 3 | Stable | 0.6 | 86 | 140 | 153 | 133.1667 | 0.2 | 19 | 59 | 77 | 55.3333 | 0 | 37.5 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 0.3 | 8.7814 | 2.6344 | Reduce | 0.15 | 8.7832 | 1.3175 | H3 | 3 | Stable | 0.9 | 109 | 128 | 150 | 128.5 | 0.4 | 7 | 49 | 79 | 47 | -0.021119 | 50 | 1 | 1.4873
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R009 | Project_016_Risk--R009 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer maybe difficult to work with | Person_697 | 2016-04-02 | 2019-08-01 | 0.6 | 23.9549 | 14.3729 | Reduce | 0.43864 | 23.8312 | 10.4533 | H2 | 4 | Stable | 0.5 | 119 | 123 | 149 | 126.6667 | 0.3 | 13 | 42 | 72 | 42.1667 | 0.51612 | 26.8938 | 0 | 0.30967
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Delay of processing | Person_306 | 2016-04-02 | 2017-03-21 01:00 | 0.15 | 26.3497 | 3.9525 | Reduce | 0.15 | 13.1767 | 1.9765 | H3 | 3 | Stable | 0.7 | 114 | 139 | 149 | 136.5 | 0.4 | 16 | 51 | 68 | 48 | 49.993 | 0 | 1 | 29.9958
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK300(020) | Project_024_RISK300(020) | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Travel and onsite support | Person_119 | 2017-01-20 01:00 | 2017-07-20 | 0.25 | 87.6137 | 4.3807 | Accept | 0.25 | 87.6137 | 4.3807 | H3 | 3 | Stable | 0.6 | 109 | 121 | 147 | 123.3333 | 0.6 | 109 | 121 | 147 | 123.3333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK304(026) | Project_024_RISK304(026) | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | complex integration | Person_119 | 2016-10-20 01:00 | 2017-07-20 | 0.4 | 5.8286 | 0.29143 | Accept | 0.4 | 5.8286 | 0.29143 | H1 | 5 | Worsening | 0.9 | 98 | 138 | 157 | 134.5 | 0.9 | 98 | 138 | 157 | 134.5 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK303(025) | Project_024_RISK303(025) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in contract value from our supplier | Person_119 | 2016-10-20 01:00 | 2019-05-23 | 0.25 | 31.83 | 23.8725 | Accept | 0.25 | 31.83 | 23.8725 | H2 | 4 | Stable | 0.9 | 89 | 127 | 144 | 123.5 | 0.9 | 89 | 127 | 144 | 123.5 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.2 | 53.0293 | 10.6059 | Reduce | 0.2 | 53.0293 | 10.6059 | H3 | 3 | Worsening | 0.6 | 100 | 123 | 159 | 125.1667 | 0.2 | 39 | 46 | 77 | 50 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Commercial aspects agreement | Person_439 | 2013-08-21 01:00 | 2017-05-22 | 0.02 | 4.8296 | 0.096593 | Transfer | 0.02 | 4.8296 | 0.096593 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 01:00 | 2017-08-20 01:00 | 0.1 | 34.363 | 3.4363 | Avoid | 0.1 | 34.363 | 3.4363 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_693 | 2017-04-22 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Worsening | 0.7 | 90 | 135 | 148 | 129.6667 | 0.4 | 3 | 55 | 63 | 47.6667 | 0 | 50 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.26 | 16.2047 | 4.2132 | Avoid | 0.26 | 16.2047 | 4.2132 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.6 | 118 | 128 | 152 | 130.3333 | 0.4 | 4 | 42 | 72 | 40.6667 | 0 | 25 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2017-04-22 | 2018-05-22 | 0.75 | 10.7184 | 8.0388 | Reduce | 0.15 | 5.3592 | 0.80388 | H3 | 3 | Worsening | 0.7 | 94 | 129 | 156 | 127.6667 | 0.2 | 24 | 57 | 72 | 54 | 50 | 80 | 1 | 32.4
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK305(027) | Project_024_RISK305(027) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment not available on time | Person_119 | 2016-11-19 01:00 | 2019-05-23 | 0.3 | 0.20788 | 0.068599 | Accept | 0.3 | 0.052336 | 0.0057569 | H2 | 4 | Stable | 0.5 | 112 | 136 | 144 | 133.3333 | 0.5 | 112 | 136 | 144 | 133.3333 | 74.8236 | 0 | 0 | 44.8942
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK296(013) | Project_024_RISK296(013) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Qualification/Certification Requirements flowdown | Person_119 | 2016-10-20 01:00 | 2017-05-22 | 0.25 | 1.9722 | 0.98609 | Accept | 0.25 | 1.9722 | 0.98609 | H2 | 4 | Worsening | 0.6 | 90 | 128 | 159 | 126.8333 | 0.6 | 90 | 128 | 159 | 126.8333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK004 | Project_010_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Export License | Person_359 | 2015-02-18 01:00 | 2017-08-20 01:00 | 0.8 | 0.18482 | 0.14786 | Reduce | 0.8 | 0.18482 | 0.14786 | H1 | 5 | Improving | 0.7 | 97 | 130 | 153 | 128.3333 | 0.4 | 24 | 40 | 78 | 43.6667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.25 | 7.7469 | 1.9367 | Reduce | 0.25 | 7.7469 | 1.9367 | H3 | 3 | Stable | 0.6 | 85 | 135 | 155 | 130 | 0.1 | 3 | 44 | 63 | 40.3333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before part b finished | Person_119 | 2016-10-20 01:00 | 2017-07-20 | 0.35 | 2.5081 | 1.2541 | Accept | 0.35 | 2.5081 | 1.2541 | H2 | 4 | Worsening | 0.9 | 91 | 131 | 151 | 127.6667 | 0.9 | 91 | 131 | 151 | 127.6667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 01:00 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.7 | 104 | 136 | 144 | 132 | 0.3 | 8 | 46 | 69 | 43.5 | 0 | 40 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK298(016) | Project_024_RISK298(016) | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Environmental testing required | Person_119 | 2016-10-20 01:00 | 2017-05-22 | 0.2 | 11.3437 | 0.56718 | Accept | 0.2 | 11.3437 | 0.56718 | H2 | 4 | Stable | 0.5 | 89 | 139 | 148 | 132.1667 | 0.5 | 89 | 139 | 148 | 132.1667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment | Person_238 | 2017-05-01 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.05 | 1.2219 | 0.061095 | H3 | 3 | Stable | 0.6 | 91 | 132 | 146 | 127.5 | 0.2 | 37 | 46 | 75 | 49.3333 | -78.1248 | 80 | 1 | -44.4749
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK301(022) | Project_024_RISK301(022) | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Interface delays | Person_119 | 2016-10-20 01:00 | 2017-01-20 01:00 | 0.1 | 11.0894 | 0.55447 | Accept | 0.1 | 11.0894 | 0.55447 | H3 | 3 | Stable | 0.6 | 89 | 135 | 152 | 130.1667 | 0.6 | 89 | 135 | 152 | 130.1667 | 0 | 0 | 1 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK299(018) | Project_024_RISK299(018) | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Additional support hours | Person_119 | 2017-01-20 01:00 | 2017-07-20 | 0.35 | 0.45017 | 0.2701 | Accept | 0.35 | 0.45017 | 0.2701 | H3 | 3 | Stable | 0.8 | 88 | 136 | 150 | 130.3333 | 0.8 | 88 | 136 | 150 | 130.3333 | 0 | 0 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.7 | 0.92411 | 0.64688 | Reduce | 0.3 | 0.36965 | 0.11089 | H2 | 4 | Stable | 0.9 | 90 | 129 | 147 | 125.5 | 0.4 | 12 | 58 | 79 | 53.8333 | 60 | 57.1429 | 0 | 36
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.35 | 3.7514 | 0.37514 | Accept | 0.35 | 3.7514 | 0.37514 | H3 | 3 | Stable | 0.9 | 106 | 139 | 158 | 136.6667 | 0.9 | 106 | 139 | 158 | 136.6667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 01:00 | 2016-04-21 | 0.5 | 4.0661 | 2.033 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.8 | 114 | 133 | 146 | 132 | 0.1 | 5 | 55 | 60 | 47.5 | 0 | 90 | 1 | 2.7
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2017-04-22 | 2017-07-21 | 0.1 | 21.8655 | 2.1865 | Reduce | 0.01 | 21.8655 | 0.21865 | H2 | 4 | Stable | 0.5 | 118 | 128 | 146 | 129.3333 | 0.4 | 24 | 41 | 79 | 44.5 | 0 | 90 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.3 | 0.46206 | 0.13862 | H2 | 4 | Improving | 0.7 | 82 | 122 | 144 | 119 | 0.1 | 24 | 51 | 72 | 50 | 58.3333 | 50 | 0 | 35
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2017-04-22 | 2018-05-22 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Stable | 0.9 | 113 | 121 | 150 | 124.5 | 0.3 | 38 | 44 | 66 | 46.6667 | 0 | 60 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.25 | 1.1089 | 0.88715 | Accept | 0.25 | 0.73929 | 0.44357 | H3 | 3 | Stable | 0.6 | 114 | 123 | 148 | 125.6667 | 0.6 | 114 | 123 | 148 | 125.6667 | 33.3333 | 0 | 0 | 20
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Unidentified CRs and concessions | Person_693 | 2017-04-22 | 2017-09-20 01:00 | 0.5 | 1.2005 | 0.60023 | Reduce | 0.15 | 0.51019 | 0.076529 | H3 | 3 | Stable | 0.8 | 111 | 121 | 144 | 123.1667 | 0.1 | 27 | 53 | 75 | 52.3333 | 57.5001 | 70 | 1 | 36.6001
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 01:00 | 2017-08-20 01:00 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.7 | 93 | 128 | 156 | 126.8333 | 0.3 | 6 | 43 | 77 | 42.5 | 0 | 50 | 1 | 1.5
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_238 | 2017-04-22 | 2018-05-22 | 0.25 | 3.3227 | 0.83067 | Reduce | 0.05 | 3.3227 | 0.16613 | H3 | 3 | Stable | 0.5 | 84 | 138 | 152 | 131.3333 | 0.2 | 7 | 54 | 67 | 48.3333 | 0 | 80 | 1 | 2.4
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.8 | 81 | 140 | 157 | 133 | 0.4 | 7 | 51 | 77 | 48 | 0 | 25 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_693 | 2017-04-22 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.1 | 0.77172 | 0.077172 | H3 | 3 | Stable | 0.7 | 92 | 121 | 158 | 122.3333 | 0.4 | 20 | 53 | 76 | 51.3333 | 0 | 60 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Stable | 0.8 | 103 | 127 | 152 | 127.1667 | 0.1 | 12 | 54 | 66 | 49 | 0 | 40 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Worsening | [10 empty] | 0 | 37.5 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production or Engineering | Person_725 | 2018-01-21 01:00 | 2019-06-24 | 0.3 | 1.7492 | 0.52477 | Reduce | 0.1 | 1.7492 | 0.17492 | H3 | 3 | Stable | 0.8 | 84 | 134 | 143 | 127.1667 | 0.2 | 39 | 43 | 63 | 45.6667 | 0 | 66.6667 | 1 | 2
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-20 23:00 | 2019-08-20 | 0.5 | 3.6965 | 0.36965 | Accept | 0.5 | 3.6965 | 0.36965 | H2 | 4 | Stable | 0.7 | 103 | 128 | 156 | 128.5 | 0.7 | 103 | 128 | 156 | 128.5 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_693 | 2017-04-22 | 2018-11-20 01:00 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.08 | 6.431 | 0.51448 | H3 | 3 | Improving | 0.8 | 105 | 131 | 148 | 129.5 | 0.2 | 10 | 47 | 70 | 44.6667 | -47.0588 | 46.6667 | 1 | -26.8353
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.2 | 0.92411 | 0.18482 | Accept | 0.2 | 0.92411 | 0.18482 | H3 | 3 | Stable | 0.6 | 80 | 127 | 152 | 123.3333 | 0.6 | 80 | 127 | 152 | 123.3333 | 0 | 0 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 0.61 | 0.21008 | 0.10504 | Accept | 0.61 | 0.21008 | 0.05252 | H1 | 5 | Stable | 0.7 | 116 | 138 | 155 | 137.1667 | 0.7 | 116 | 138 | 155 | 137.1667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 0.3 | 1.8482 | 0.55447 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.9 | 91 | 140 | 158 | 134.8333 | 0.1 | 39 | 57 | 73 | 56.6667 | 0 | 33.3333 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Reduce touch labour if Production readiness programme successful | Person_238 | 2017-04-22 | 2017-10-21 01:00 | 0.3 | 1.5606 | 0.46818 | Exploit | 0.5 | 1.5606 | 0.7803 | H2 | 4 | Stable | [10 empty] | 0 | -66.6667 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.35 | 8.0582 | 2.4175 | Accept | 0.35 | 8.0582 | 2.4175 | H3 | 3 | Stable | 0.8 | 107 | 140 | 145 | 135.3333 | 0.8 | 107 | 140 | 145 | 135.3333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 01:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.6 | 87 | 135 | 143 | 128.3333 | 0.4 | 31 | 59 | 70 | 56.1667 | 90 | 75 | 1 | 56.25
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.25 | 0 | 0 | Accept | 0.25 | 0 | 0 | H3 | 3 | Stable | 0.8 | 106 | 126 | 145 | 125.8333 | 0.8 | 106 | 126 | 145 | 125.8333 |  | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-20 23:00 | 2019-08-20 | 0.5 | 0.5596 | 0.05596 | Accept | 0.5 | 0.5596 | 0.05596 | H2 | 4 | Stable | 0.8 | 95 | 131 | 148 | 127.8333 | 0.8 | 95 | 131 | 148 | 127.8333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 0.2 | 3.6174 | 1.8087 | Accept | 0.2 | 3.6172 | 0.72345 | H3 | 3 | Stable | 0.8 | 95 | 122 | 148 | 121.8333 | 0.8 | 95 | 122 | 148 | 121.8333 | 0.0051359 | 0 | 0 | 0.0030815
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 01:00 | 0.1 | 2.3503 | 0.47006 | Accept | 0.05 | 2.3503 | 0.47006 | H3 | 3 | Stable | 0.8 | 81 | 127 | 151 | 123.3333 | 0.8 | 81 | 127 | 151 | 123.3333 | 0 | 50 | 1 | 1.5
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-194 | Project_027_Risk-194 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | The effect of specialist supplier obsolescence on complex assemblies | Person_074 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.08 | 4.4768 | 2.2384 | Accept | 0.08 | 4.4768 | 2.2384 | H3 | 3 | Stable | 0.5 | 109 | 134 | 151 | 132.6667 | 0.5 | 109 | 134 | 151 | 132.6667 | 0 | 0 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-116 | Project_011_Risk-116 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Delays to Qualification | Person_147 | 2017-04-22 | 2017-08-19 01:00 | 0.5 | 0.86486 | 0.43243 | Reduce | 0.5 | 0.86486 | 0.43243 | H1 | 5 | Stable | 0.7 | 112 | 135 | 151 | 133.8333 | 0.3 | 19 | 43 | 61 | 42 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-104 | Project_011_Risk-104 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer delayed in providing Custeomr Furnished Equipment | Person_147 | 2016-06-23 | 2017-04-21 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.8 | 114 | 123 | 156 | 127 | 0.1 | 7 | 51 | 69 | 46.6667 |  | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence and missing info | Person_727 | 2015-11-25 01:00 | 2017-06-21 | 0.3 | 0.30685 | 0.06137 | Accept | 0.1 | 0.30685 | 0.06137 | H3 | 3 | Stable | 0.5 | 98 | 136 | 144 | 131 | 0.5 | 98 | 136 | 144 | 131 | 0 | 66.6667 | 1 | 2
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 0.3 | 0.51931 | 0.15579 | -- | 0.15 | 0.51931 | 0.077897 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Obsolescence Monitoring Risk | Person_181 | 2016-12-02 21:00 | 2017-01-19 21:00 | 0.3 | 5.9458 | 1.7837 | Reduce | 0.15 | 0.9786 | 0.14679 | H3 | 3 | Stable | 0.6 | 98 | 135 | 158 | 132.6667 | 0.4 | 15 | 40 | 72 | 41.1667 | 83.5413 | 50 | 0 | 50.1248
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 0.2 | 0.55005 | 0.11001 | Avoid | 0.2 | 0.55005 | 0.11001 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-185 | Project_027_Risk-185 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier manufacturing issues | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.6 | 3.0903 | 0.61807 | Accept | 0.05 | 3.0903 | 0.61807 | H3 | 3 | Stable | 0.5 | 82 | 128 | 155 | 124.8333 | 0.5 | 82 | 128 | 155 | 124.8333 | 0 | 91.6667 | 1 | 2.75
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-123 | Project_011_Risk-123 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | No Requirement for Delta acceptance | Person_187 | 2017-06-23 | 2017-08-20 01:00 | 0.2 | 0.63074 | 0.12615 | -- | 0.2 | 0.63074 | 0.12615 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2016-07-21 | 2017-02-19 01:00 | 0.15 | 0.28639 | 0.042959 | -- | 0.15 | 0.28639 | 0.042959 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-04-21 | 0.2 | 0.24207 | 0.048414 | -- | 0.2 | 0.24207 | 0.048414 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-186 | Project_027_Risk-186 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Potential for composite suppliers going out of business | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 0.1 | 24.8462 | 12.4231 | Accept | 0.1 | 24.8462 | 12.4231 | H3 | 3 | Stable | 0.5 | 94 | 138 | 154 | 133.3333 | 0.5 | 94 | 138 | 154 | 133.3333 | 0 | 0 | 1 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 01:00 | 2017-03-22 | 0.2 | 30.9033 | 7.7258 | Accept | 0.1 | 30.9033 | 7.7258 | H2 | 4 | Stable | 0.5 | 84 | 136 | 153 | 130.1667 | 0.5 | 84 | 136 | 153 | 130.1667 | 0 | 50 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 0.2 | 1.661 | 0.33219 | Reduce | 0.2 | 1.661 | 0.33219 | H2 | 4 | Stable | 0.6 | 114 | 139 | 154 | 137.3333 | 0.2 | 15 | 59 | 63 | 52.3333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-002 | Project_028_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Record / Replay feature | Person_499 | 2014-03-23 | 2017-04-21 | 0.05 | 35.0206 | 7.0041 | Accept | 0.05 | 35.0206 | 7.0041 | H2 | 4 | Stable | 0.7 | 88 | 123 | 151 | 121.8333 | 0.7 | 88 | 123 | 151 | 121.8333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | EMC Testing | Person_070 | 2016-04-22 | 2017-04-21 | 0.35 | 60.4367 | 3.0218 | Accept | 0.2 | 60.4367 | 3.0218 | H2 | 4 | Stable | 0.6 | 86 | 135 | 145 | 128.5 | 0.6 | 86 | 135 | 145 | 128.5 | 0 | 42.8571 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_542 | 2015-01-22 01:00 | 2017-08-20 01:00 | 0.35 | 15.0654 | 6.7794 | Accept | 0.2 | 15.0654 | 6.7794 | H2 | 4 | Stable | 0.5 | 84 | 131 | 160 | 128 | 0.5 | 84 | 131 | 160 | 128 | 0 | 42.8571 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2017-10-21 01:00 | 2018-08-21 | 0.4 | 1.2444 | 0.49778 | Reduce | 0.4 | 1.2444 | 0.49778 | H2 | 4 | Stable | 0.5 | 101 | 138 | 149 | 133.6667 | 0.2 | 16 | 57 | 79 | 53.8333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_070 | 2016-06-23 | 2017-08-20 01:00 | 0.4 | 0.16195 | 0.072876 | Accept | 0.2 | 0.16195 | 0.072876 | H2 | 4 | Stable | 0.7 | 90 | 137 | 152 | 131.6667 | 0.7 | 90 | 137 | 152 | 131.6667 | 0 | 50 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 01:00 | 2018-08-21 | 0.45 | 0.83883 | 0.37747 | Reduce | 0.45 | 0.83883 | 0.37747 | H2 | 4 | Stable | 0.5 | 119 | 125 | 151 | 128.3333 | 0.3 | 27 | 58 | 76 | 55.8333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-010 | Project_011_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Rework required following integration of Customer System | Person_142 | 2013-08-21 01:00 | 2017-05-21 | 0.4 | 0.66881 | 0.26753 | Reduce | 0.4 | 0.66881 | 0.26753 | H2 | 4 | Stable | 0.7 | 108 | 128 | 150 | 128.3333 | 0.4 | 31 | 53 | 77 | 53.3333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 0.45 | 0.098873 | 0.0098873 | Accept | 0.45 | 0.098873 | 0.0098873 | H2 | 4 | Stable | 0.7 | 104 | 137 | 148 | 133.3333 | 0.7 | 104 | 137 | 148 | 133.3333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-02-20 01:00 | 2018-08-21 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.5 | 88 | 126 | 141 | 122.1667 | 0.4 | 30 | 59 | 77 | 57.1667 |  | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Pick up and Drop off of Software Resource | Person_230 | 2017-04-21 | 2018-02-19 01:00 | 0.4 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-109 | Project_011_Risk-109 | Opportunitity | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Environment complexity | Person_187 | 2016-07-21 | 2018-08-21 | 0.25 | 0.14661 | 0.036651 | -- | 0.25 | 0.14661 | 0.036651 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-108 | Project_011_Risk-108 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Offer additional functionality to the customer | Person_147 | 2017-04-22 | 2018-08-21 | 0.1 | 0.34094 | 0.034094 | -- | 0.1 | 0.34094 | 0.034094 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 0.2 | 0.12388 | 0.024775 | Reduce | 0.2 | 0.12388 | 0.024775 | H2 | 4 | Stable | 0.6 | 83 | 139 | 142 | 130.1667 | 0.2 | 10 | 55 | 63 | 48.8333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 0.4 | 0.51141 | 0.20457 | Avoid | 0.4 | 0.51141 | 0.20457 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_565 | 2018-05-22 | 2018-08-21 | 0.25 | 0.49834 | 0.12459 | Accept | 0.25 | 0.49834 | 0.12459 | H3 | 3 | Stable | 0.7 | 110 | 125 | 149 | 126.5 | 0.7 | 110 | 125 | 149 | 126.5 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.2 | 0.10171 | 0.020343 | -- | 0.2 | 0.10171 | 0.020343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 0.3 | 0.28639 | 0.085917 | Reduce | 0.3 | 0.28639 | 0.085917 | H2 | 4 | Stable | 0.9 | 104 | 132 | 150 | 130.3333 | 0.2 | 39 | 47 | 79 | 51 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 2. Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 0.25 | 0 | 0 | -- | 0.25 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2017-10-21 01:00 | 2018-05-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 0.3 | 0.10626 | 0.031878 | -- | 0.3 | 0.01932 | 0.005796 | H3 | 3 | Stable | [10 empty] | 81.8181 | 0 | 0 | 49.0909
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Lack of Spares Availability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 0.3 | 1.0052 | 0.35182 | Accept | 0.3 | 1.0052 | 0.35182 | H2 | 4 | Stable | 0.8 | 111 | 137 | 143 | 133.6667 | 0.8 | 111 | 137 | 143 | 133.6667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-118 | Project_011_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer change environment | Person_187 | 2013-08-21 01:00 | 2018-08-21 | 0.1 | 0 | 0 | Avoid | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 | 2016-12-21 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.9 | 101 | 133 | 150 | 130.5 | 0.3 | 33 | 49 | 60 | 48.1667 | 47 | 0 | 0 | 28.2
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 | 2016-12-21 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-19 | 0.4 | 3.187 | 1.2748 | Reduce | 0.2 | 1.5935 | 0.3187 | H3 | 3 | Stable | 0.9 | 92 | 130 | 147 | 126.5 | 0.3 | 27 | 58 | 61 | 53.3333 | 50 | 50 | 1 | 31.5
2017-02-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 01:00 | 2016-05-21 | 0.5 | 4.3921 | 2.196 | Reduce | 0.3 | 0 | 0 | H1 | 5 | Stable | 0.9 | 94 | 130 | 154 | 128 | 0.1 | 16 | 53 | 66 | 49 | 100 | 40 | 0 | 60
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-08-20 01:00 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.5 | 112 | 140 | 153 | 137.5 | 0.4 | 39 | 52 | 73 | 53.3333 | 50 | 28.5714 | 0 | 30
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-11-19 01:00 | 0.5 | 17.2826 | 8.6413 | Reduce | 0.15 | 17.2826 | 2.5924 | H2 | 4 | Worsening | 0.9 | 99 | 127 | 146 | 125.5 | 0.1 | 14 | 58 | 71 | 52.8333 | 0 | 70 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_427 | 2012-11-20 01:00 | 2017-06-22 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.7 | 102 | 126 | 152 | 126.3333 | 0.2 | 25 | 49 | 65 | 47.6667 | 0 | 50 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2016-07-20 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.4 | 12.6474 | 5.059 | H2 | 4 | Stable | 0.8 | 87 | 127 | 160 | 125.8333 | 0.3 | 18 | 55 | 74 | 52 | 0 | 33.3333 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.9 | 99 | 133 | 157 | 131.3333 | 0.2 | 15 | 52 | 68 | 48.5 | 0 | 50 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target. | Person_482 | 2013-01-07 01:00 | 2017-06-06 | 0.3 | 4.7676 | 1.4303 | Reduce | 0.15 | 4.7676 | 0.71514 | H2 | 4 | Stable | 0.9 | 109 | 127 | 150 | 127.8333 | 0.3 | 2 | 49 | 74 | 45.3333 | 0 | 50 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 01:00 | 2017-08-20 01:00 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.6 | 93 | 125 | 150 | 123.8333 | 0.2 | 9 | 45 | 72 | 43.5 | 0 | 33.3333 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2016-12-20 01:00 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Improving | 0.8 | 102 | 135 | 159 | 133.5 | 0.1 | 25 | 48 | 79 | 49.3333 | 0 | 57.1429 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-05-21 | 0.8 | 0 | 0 | Reduce | 0.6 | 0 | 0 | H1 | 5 | Worsening | 0.8 | 120 | 131 | 147 | 131.8333 | 0.4 | 39 | 48 | 64 | 49.1667 |  | 25 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-05-21 | 0.8 | 1.3243 | 1.0595 | Reduce | 0.6 | 1.3243 | 0.7946 | H1 | 5 | Worsening | 0.7 | 107 | 139 | 157 | 136.6667 | 0.2 | 35 | 57 | 74 | 56.1667 | 0 | 25 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2017-06-22 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.6 | 84 | 135 | 155 | 129.8333 | 0.4 | 8 | 59 | 72 | 52.6667 |  | 50 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trial delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 119 | 128 | 156 | 131.1667 | 0.1 | 36 | 55 | 68 | 54 |  | 40 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trial delay due to equip[ment availability | Person_174 | 2016-10-21 01:00 | 2017-08-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.7 | 87 | 137 | 157 | 132 | 0.4 | 36 | 46 | 79 | 49.8333 |  | 60 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-08-20 01:00 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.5 | 117 | 137 | 152 | 136.1667 | 0.3 | 12 | 48 | 73 | 46.1667 | 7.8429 | 40 | 0 | 4.7058
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 0.2 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 82 | 138 | 153 | 131.1667 | 0.4 | 27 | 47 | 71 | 47.6667 |  | 50 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 0.3 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.7 | 106 | 136 | 141 | 131.8333 | 0.2 | 5 | 48 | 66 | 43.8333 |  | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.9 | 113 | 121 | 142 | 123.1667 | 0.3 | 9 | 48 | 68 | 44.8333 |  | 66.6667 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-08-06 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.6 | 82 | 138 | 156 | 131.6667 | 0.2 | 1 | 45 | 71 | 42 |  | 80 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2017-06-22 | 0.3 | 1.076 | 0.32281 | Reduce | 0.05 | 1.076 | 0.053801 | H2 | 4 | Improving | 0.5 | 120 | 123 | 147 | 126.5 | 0.4 | 16 | 58 | 69 | 52.8333 | 0 | 83.3333 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2017-05-07 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.5 | 93 | 121 | 150 | 121.1667 | 0.1 | 21 | 46 | 67 | 45.3333 | 80 | 66.6667 | 0 | 48
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-05-23 | 2018-01-20 01:00 | 0.1 | 0.48559 | 0.048559 | Reduce | 0.1 | 0.48559 | 0.048559 | H2 | 4 | Stable | 0.6 | 90 | 139 | 154 | 133.3333 | 0.2 | 24 | 56 | 69 | 52.8333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 0.5 | 3.8666 | 1.5853 | Accept | 0.5 | 1.3288 | 0.5448 | H2 | 4 | Improving | 0.5 | 114 | 140 | 158 | 138.6667 | 0.5 | 114 | 140 | 158 | 138.6667 | 65.6338 | 0 | 0 | 39.3803
2017-02-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2017-05-22 | 0.85 | 25.2325 | 21.4476 | Avoid | 0.08 | 13.7962 | 1.1037 | H2 | 4 | Stable | [10 empty] | 45.3237 | 90.5882 | 0 | 27.1942
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 0.3 | 5.4459 | 1.6338 | Accept | 0.3 | 0.18151 | 0.054453 | H2 | 4 | Stable | 0.9 | 112 | 127 | 151 | 128.5 | 0.9 | 112 | 127 | 151 | 128.5 | 96.667 | 0 | 0 | 58.0002
2017-02-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2017-04-21 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.35 | 2.8688 | 1.0041 | H2 | 4 | Stable | 0.6 | 91 | 139 | 144 | 131.8333 | 0.1 | 27 | 54 | 72 | 52.5 | 22.0253 | 56.25 | 0 | 13.2152
2017-02-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2017-05-22 | 0.7 | 24.1887 | 16.9321 | Reduce | 0.25 | 2.6322 | 0.65804 | H2 | 4 | Stable | 0.7 | 86 | 132 | 150 | 127.3333 | 0.4 | 33 | 52 | 69 | 51.6667 | 89.1182 | 64.2857 | 0 | 53.4709
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R013 | Project_016_Risk--R013 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Resource Availability (Threat) | Person_697 | 2016-04-02 | 2019-08-01 | 0.2 | 2.3975 | 2.3975 | Accept | 0.2 | 11.8183 | 11.8183 | H2 | 4 | Worsening | 0.8 | 119 | 131 | 144 | 131.1667 | 0.8 | 119 | 131 | 144 | 131.1667 | -392.9441 | 0 | 0 | -235.7664
2017-02-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2017-04-21 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 0.65554 | 0.52443 | H2 | 4 | Stable | [10 empty] | 80.45 | 0 | 0 | 48.27
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-148 | Project_020_Risk-148 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs non-available items | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.3 | 14.9935 | 4.498 | Reduce | 0.3 | 4.1112 | 1.2334 | H2 | 4 | Stable | 0.8 | 119 | 138 | 144 | 135.8333 | 0.3 | 38 | 55 | 64 | 53.6667 | 72.5803 | 0 | 0 | 43.5482
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-22 01:00 | 2017-05-22 | 0.25 | 7.4225 | 1.8556 | Reduce | 0.1 | 2.0081 | 0.20081 | H3 | 3 | Stable | 0.5 | 99 | 140 | 156 | 135.8333 | 0.2 | 27 | 45 | 76 | 47.1667 | 72.9455 | 60 | 0 | 43.7673
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 2.6991 | 1.0796 | H2 | 4 | Stable | 0.6 | 81 | 123 | 148 | 120.1667 | 0.3 | 8 | 55 | 63 | 48.5 | 31.8182 | 20 | 0 | 19.0909
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.05 | 18.6688 | 3.7338 | Accept | 0.05 | 18.6688 | 3.7338 | H3 | 3 | Stable | 0.5 | 119 | 127 | 157 | 130.6667 | 0.5 | 119 | 127 | 157 | 130.6667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-147 | Project_020_Risk-147 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component taking longer to refurbish in country | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.6 | 6.7477 | 4.0486 | Reduce | 0.6 | 3.3739 | 2.0243 | H2 | 4 | Stable | 0.8 | 99 | 121 | 152 | 122.5 | 0.2 | 11 | 50 | 75 | 47.6667 | 50 | 0 | 0 | 30
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 0.05 | 18.069 | 1.8069 | Accept | 0.05 | 11.3212 | 1.1321 | H2 | 4 | Stable | 0.9 | 91 | 122 | 147 | 121 | 0.9 | 91 | 122 | 147 | 121 | 37.3444 | 0 | 0 | 22.4066
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_575 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 5.0983 | 0.76474 | H3 | 3 | Stable | 0.9 | 83 | 138 | 148 | 130.5 | 0.1 | 4 | 54 | 71 | 48.5 | 19.0479 | 70 | 1 | 13.5287
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Risk of not being able to perform Tests | Person_238 | 2017-12-21 01:00 | 2019-01-21 01:00 | 0.5 | 4.0228 | 2.0114 | Accept | 0.5 | 4.0228 | 2.0114 | H2 | 4 | Stable | 0.7 | 96 | 134 | 144 | 129.3333 | 0.7 | 96 | 134 | 144 | 129.3333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_238 | 2017-05-23 | 2019-01-21 01:00 | 0.5 | 7.3646 | 3.6823 | Accept | 0.5 | 7.3646 | 3.6823 | H2 | 4 | Stable | 0.8 | 102 | 131 | 153 | 129.8333 | 0.8 | 102 | 131 | 153 | 129.8333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.41 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -2.5 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.61 | 0.25667 | 0.15657 | Reduce | 0.5 | 0.25667 | 0.12834 | H2 | 4 | Stable | 0.6 | 120 | 123 | 155 | 127.8333 | 0.3 | 17 | 47 | 77 | 47 | 0 | 18.0328 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2014-01-21 01:00 | 2017-11-20 01:00 | 0.4 | 1.078 | 0.43121 | Reduce | 0.4 | 1.4673 | 0.58692 | H2 | 4 | Improving | 0.6 | 113 | 127 | 159 | 130 | 0.4 | 12 | 50 | 61 | 45.5 | -36.1112 | 0 | 0 | -21.6667
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-118 | Project_029_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Acceptance Schedule is longer in duration/delayed due to unplanned events. [Hardware availability] | Person_102 | 2017-01-21 01:00 | 2017-05-23 | 0.55 | 1.3775 | 0.75761 | Reduce | 0.55 | 1.3775 | 0.75761 | H2 | 4 | Stable | 0.9 | 83 | 139 | 152 | 131.8333 | 0.3 | 36 | 53 | 72 | 53.3333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2017-11-19 01:00 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2017-09-20 01:00 | 0.6 | 0.89835 | 0.53901 | Transfer | 0.6 | 0.89835 | 0.53901 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 0.35 | 0.85557 | 0.29945 | Reduce | 0.35 | 1.9208 | 0.67227 | H2 | 4 | Stable | 0.9 | 103 | 123 | 148 | 123.8333 | 0.2 | 15 | 54 | 75 | 51 | -124.5001 | 0 | 0 | -74.7001
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 01:00 | 0.05 | 0.77001 | 0.30801 | Accept | 0.05 | 0.77001 | 0.231 | H3 | 3 | Stable | 0.7 | 95 | 136 | 142 | 130.1667 | 0.7 | 95 | 136 | 142 | 130.1667 | 0 | 0 | 1 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2018-02-20 01:00 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.8 | 81 | 131 | 156 | 126.8333 | 0.1 | 15 | 45 | 79 | 45.6667 | 0 | 28.5714 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.05 | 1.54 | 0.30801 | Accept | 0.05 | 0.77001 | 0.154 | H2 | 4 | Stable | 0.9 | 91 | 124 | 148 | 122.5 | 0.9 | 91 | 124 | 148 | 122.5 | 50 | 0 | 0 | 30
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_693 | 2017-04-22 | 2017-09-19 01:00 | 0.6 | 0.94968 | 0.28491 | Accept | 0.6 | 0.94968 | 0.18994 | H2 | 4 | Stable | 0.6 | 109 | 136 | 154 | 134.5 | 0.6 | 109 | 136 | 154 | 134.5 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_547 | 2017-04-22 | 2018-05-22 | 0.1 | 27.1644 | 0.81493 | Accept | 0.1 | 12.8336 | 1.2834 | H3 | 3 | Stable | 0.5 | 101 | 139 | 160 | 136.1667 | 0.5 | 101 | 139 | 160 | 136.1667 | 52.7559 | 0 | 1 | 31.6535
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2014-07-22 | 2017-11-19 01:00 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.9 | 90 | 127 | 149 | 124.5 | 0.3 | 32 | 48 | 76 | 50 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2017-10-14 01:00 | 0.41 | 6.4168 | 2.6309 | Transfer | 0.41 | 0 | 0 | H1 | 5 | Stable | [10 empty] | 100 | 0 | 0 | 60
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub-system FPGA | Person_216 | 2017-01-21 01:00 | 2017-08-20 01:00 | 0.3 | 1.54 | 0.46201 | Reduce | 0.4 | 1.5914 | 0.63655 | H2 | 4 | Stable | 0.5 | 103 | 125 | 153 | 126 | 0.1 | 28 | 50 | 66 | 49 | -3.3333 | -33.3333 | 0 | -2
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SystemC HW/SW | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.3 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.5 | 95 | 127 | 148 | 125.1667 | 0.2 | 20 | 51 | 79 | 50.5 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs [technical scope] | Person_372 | 2017-01-21 01:00 | 2019-07-21 | 0.35 | 9.505 | 3.3267 | Reduce | 0.35 | 9.505 | 3.3267 | H2 | 4 | Stable | 0.8 | 81 | 122 | 152 | 120.1667 | 0.4 | 24 | 49 | 75 | 49.1667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.5 | 3.5934 | 1.7967 | H2 | 4 | Stable | 0.9 | 98 | 132 | 156 | 130.3333 | 0.2 | 19 | 52 | 73 | 50 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | HW - additional unplanned design effort | Person_216 | 2016-05-23 | 2019-10-21 01:00 | 0.4 | 3.3367 | 1.3347 | Reduce | 0.4 | 3.3367 | 1.3347 | H2 | 4 | Stable | 0.9 | 104 | 136 | 153 | 133.5 | 0.4 | 5 | 50 | 62 | 44.5 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 0.8 | 3.9356 | 0.98391 | Accept | 0.6 | 4.2779 | 1.0695 | H1 | 5 | Stable | 0.7 | 92 | 127 | 160 | 126.6667 | 0.7 | 92 | 127 | 160 | 126.6667 | -8.6957 | 25 | 0 | -5.2174
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 01:00 | 2016-08-20 01:00 | 0.1 | 2.5667 | 0.77001 | Accept | 0.1 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.7 | 109 | 123 | 153 | 125.6667 | 0.7 | 109 | 123 | 153 | 125.6667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design | Person_216 | 2016-05-23 | 2017-07-20 | 0.2 | 2.6951 | 0.53901 | Reduce | 0.2 | 2.6951 | 0.53901 | H3 | 3 | Improving | 0.9 | 86 | 130 | 153 | 126.5 | 0.4 | 24 | 50 | 77 | 50.1667 | 0 | 0 | 1 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_692 | 2016-12-21 01:00 | 2017-12-19 01:00 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Stable | 0.9 | 95 | 136 | 150 | 131.5 | 0.4 | 20 | 50 | 79 | 49.8333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_692 | 2017-05-23 | 2019-07-21 | 0.333 | 11.5502 | 3.8462 | Reduce | 0.333 | 11.5502 | 3.8462 | H2 | 4 | Stable | 0.7 | 101 | 130 | 151 | 128.6667 | 0.1 | 14 | 56 | 62 | 50 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 0.2 | 1.8788 | 0.28182 | Accept | 0.2 | 1.8788 | 0.28182 | H3 | 3 | Improving | 0.5 | 107 | 124 | 145 | 124.6667 | 0.5 | 107 | 124 | 145 | 124.6667 | 0 | 0 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R81 | Project_041_R81 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Re-imaging of PC's - additional material | Person_515 | 2017-04-22 | 2017-10-21 01:00 | 0.5 | 9.3941 | 1.8788 | Accept | 0.25 | 9.3941 | 1.8788 | H2 | 4 | Worsening | 0.9 | 97 | 132 | 144 | 128.1667 | 0.9 | 97 | 132 | 144 | 128.1667 | 0 | 50 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 0.2 | 0 | 0 | Accept | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.7 | 87 | 128 | 152 | 125.1667 | 0.7 | 87 | 128 | 152 | 125.1667 |  | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Governance and Export Rules | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 0.93941 | 0.23485 | Transfer | 0.25 | 0.93941 | 0.23485 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2017-05-21 | 0.05 | 2.1606 | 0.43213 | Accept | 0.05 | 2.1606 | 0.43213 | H3 | 3 | Improving | 0.5 | 93 | 140 | 154 | 134.5 | 0.5 | 93 | 140 | 154 | 134.5 | 0 | 0 | 1 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 16:00 | 2019-08-20 16:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 16:00 | 2019-08-20 16:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 16:00 | 2019-08-20 16:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 16:00 | 2019-08-20 16:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 16:00 | 2019-08-20 16:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-020 | Project_028_Risk-020 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | (Project Management WP) Availability of Customer Furnished Equipmnet for modification | Person_253 | 2015-05-24 | 2019-02-20 01:00 | 0.25 | 0 | 0 | Avoid | 0.05 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 80 | 1
2017-02-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-62 | Project_022_RISK-62 | Threat | Project Contingency | Open | H3 | 3 | 8. Operations & Maintenance | Additional Costs from Integration Cost Centre | Person_703 | 2017-03-23 | 2017-05-14 | 0.5 | 7.1754 | 3.5877 | Avoid | 0.5 | 7.1754 | 3.5877 | H3 | 3 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unforseen and substantial increase in Repairs workload during new build production period. | Person_547 | 2017-10-23 01:00 | 2017-11-19 01:00 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.03 | 1.5434 | 0.046303 | H3 | 3 | Stable | 0.8 | 112 | 130 | 143 | 129.1667 | 0.4 | 26 | 57 | 70 | 54 | 0 | 90 | 1 | 2.7
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK225 | Project_024_RISK225 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | More testing required as a result compliance to Platform Risk | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 5.6866 | 2.8433 | Reduce | 0.5 | 5.6866 | 2.8433 | H1 | 5 | Stable | 0.8 | 116 | 131 | 146 | 131 | 0.4 | 9 | 46 | 60 | 42.1667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.8 | 91 | 127 | 150 | 124.8333 | 0.1 | 21 | 59 | 62 | 53.1667 | 0 | 60 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK286 | Project_024_RISK286 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Requirement sell off more difficult than expected | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 10.1787 | 5.0893 | Reduce | 0.5 | 10.1787 | 5.0893 | H1 | 5 | Worsening | 0.8 | 108 | 124 | 157 | 126.8333 | 0.2 | 19 | 59 | 67 | 53.6667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK288 | Project_024_RISK288 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Unplanned obsolescence and/or repairs to rig assets. | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.6 | 5.8424 | 3.5054 | Reduce | 0.6 | 4.9768 | 2.9861 | H1 | 5 | Stable | 0.5 | 118 | 128 | 153 | 130.5 | 0.2 | 21 | 44 | 69 | 44.3333 | 14.8148 | 0 | 0 | 8.8889
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 0.25 | 19.9938 | 5.9981 | Accept | 0.25 | 19.9938 | 5.9981 | H3 | 3 | Stable | 0.6 | 110 | 125 | 148 | 126.3333 | 0.6 | 110 | 125 | 148 | 126.3333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.5 | 3.843 | 1.9215 | H1 | 5 | Stable | 0.6 | 91 | 124 | 148 | 122.5 | 0.4 | 16 | 41 | 79 | 43.1667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | More issues than expected during Qualification | Person_147 | 2017-04-22 | 2017-11-04 01:00 | 0.35 | 19.4745 | 5.8424 | Accept | 0.35 | 19.4745 | 5.8424 | H1 | 5 | Stable | 0.9 | 112 | 139 | 156 | 137.3333 | 0.9 | 112 | 139 | 156 | 137.3333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Overland performance | Person_448 | 2016-06-23 | 2017-11-19 01:00 | 0.1 | 1.6835 | 0.16835 | Reduce | 0.1 | 3.5011 | 0.35011 | H3 | 3 | Improving | 0.8 | 101 | 132 | 154 | 130.5 | 0.2 | 10 | 44 | 65 | 41.8333 | -107.9692 | 0 | 1 | -64.7815
2017-02-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2017-05-22 | 0.41 | 2.7146 | 2.7146 | Accept | 0.41 | 2.7146 | 2.7146 | H2 | 4 | Stable | 0.5 | 114 | 130 | 148 | 130.3333 | 0.5 | 114 | 130 | 148 | 130.3333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-016 | Project_023_Risk-016 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Damage to equipment (Unable to replace due to obsolescence) | Person_703 | 2015-10-22 01:00 | 2017-05-22 | 0.3 | 8.5688 | 4.2844 | Accept | 0.3 | 8.5688 | 4.2844 | H2 | 4 | Stable | 0.7 | 82 | 122 | 157 | 121.1667 | 0.7 | 82 | 122 | 157 | 121.1667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK213 | Project_024_RISK213 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Rigs requireaccreditation as "Special to Type" Test equipment | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.3 | 38.17 | 11.451 | Avoid | 0.25 | 19.4745 | 4.8686 | H2 | 4 | Stable | [10 empty] | 48.9796 | 16.6667 | 0 | 29.3878
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK256 | Project_024_RISK256 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unable to meet spare capacity requirement | Person_318 | 2016-07-21 | 2018-01-21 01:00 | 0.8 | 0.12983 | 0.10386 | Reduce | 0.05 | 0.12983 | 0.0064915 | H3 | 3 | Stable | 0.7 | 98 | 139 | 156 | 135 | 0.1 | 20 | 40 | 64 | 40.6667 | 0 | 93.75 | 1 | 2.8125
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK219 | Project_024_RISK219 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | STTE additional work | Person_710 | 2016-09-20 01:00 | 2017-07-21 | 0.5 | 15.0863 | 7.5431 | Reduce | 0.5 | 15.0863 | 7.5431 | H1 | 5 | Worsening | 0.6 | 97 | 136 | 157 | 133 | 0.4 | 10 | 56 | 70 | 50.6667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK218 | Project_024_RISK218 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | System issues general | Person_388 | 2016-08-21 01:00 | 2017-06-22 | 0.4 | 90.8811 | 36.3524 | Reduce | 0.3 | 39.3904 | 11.8171 | H1 | 5 | Stable | 0.8 | 92 | 140 | 141 | 132.1667 | 0.1 | 19 | 53 | 71 | 50.3333 | 56.6571 | 25 | 0 | 33.9943
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK261 | Project_024_RISK261 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Viewer may not work | Person_318 | 2016-05-23 | 2017-04-21 | 0.5 | 3.9382 | 1.9691 | Reduce | 0.1 | 3.9382 | 0.39382 | H3 | 3 | Improving | 0.7 | 109 | 128 | 149 | 128.3333 | 0.2 | 34 | 49 | 66 | 49.3333 | 0 | 80 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK222 | Project_024_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Testing Extends beyond target completion | Person_351 | 2017-07-21 | 2018-08-21 | 0.2 | 9.8671 | 1.9734 | Reduce | 0.2 | 9.8671 | 1.9734 | H2 | 4 | Stable | 0.8 | 119 | 127 | 153 | 130 | 0.2 | 10 | 56 | 79 | 52.1667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-149 | Project_020_Risk-149 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs to be returned to UK | Person_703 | 2016-12-21 01:00 | 2017-11-19 01:00 | 0.2 | 15.5796 | 6.2318 | Accept | 0.2 | 15.5796 | 6.2318 | H2 | 4 | Stable | 0.9 | 91 | 126 | 141 | 122.6667 | 0.9 | 91 | 126 | 141 | 122.6667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.2 | 20.8767 | 4.1753 | H2 | 4 | Stable | 0.7 | 120 | 132 | 159 | 134.5 | 0.3 | 15 | 41 | 73 | 42 | 50 | 50 | 0 | 30
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.48 | 76.3401 | 36.6432 | Reduce | 0.2858 | 57.5537 | 16.4488 | H1 | 5 | Worsening | 0.6 | 98 | 130 | 145 | 127.1667 | 0.3 | 10 | 45 | 65 | 42.5 | 24.6088 | 40.4583 | 0 | 14.7653
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 0.5 | 32.4575 | 1.2983 | Accept | 0.5 | 32.4575 | 1.2983 | H2 | 4 | Stable | 0.5 | 107 | 122 | 153 | 124.6667 | 0.5 | 107 | 122 | 153 | 124.6667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 0.5 | 25.966 | 7.7898 | Accept | 0.5 | 10.3864 | 3.1159 | H2 | 4 | Stable | 0.7 | 94 | 123 | 141 | 121.1667 | 0.7 | 94 | 123 | 141 | 121.1667 | 60 | 0 | 0 | 36
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 62.3617 | 3.1181 | Accept | 0.5 | 62.3617 | 3.1181 | H2 | 4 | Stable | 0.5 | 97 | 137 | 152 | 132.8333 | 0.5 | 97 | 137 | 152 | 132.8333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2017-02-20 01:00 | 2019-07-21 | 0.4 | 4.5441 | 0.45441 | Accept | 0.3 | 4.5441 | 0.45441 | H2 | 4 | Stable | 0.5 | 104 | 132 | 141 | 128.8333 | 0.5 | 104 | 132 | 141 | 128.8333 | 0 | 25 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK179 | Project_024_RISK179 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Testing Required | Person_710 | 2016-12-21 01:00 | 2017-06-22 | 0.5 | 3.5054 | 1.7527 | Avoid | 0.4 | 3.5054 | 1.4022 | H2 | 4 | Stable | [10 empty] | 0 | 20 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2019-10-14 01:00 | 0.2 | 30.2764 | 12.1106 | Accept | 0.2 | 30.2764 | 12.1106 | H3 | 3 | Stable | 0.7 | 101 | 138 | 145 | 133 | 0.7 | 101 | 138 | 145 | 133 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2019-07-21 | 0.3 | 11.9444 | 5.9722 | Accept | 0.2 | 11.9444 | 5.9722 | H3 | 3 | Stable | 0.8 | 95 | 123 | 146 | 122.1667 | 0.8 | 95 | 123 | 146 | 122.1667 | 0 | 33.3333 | 1 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK180 | Project_024_RISK180 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | High Accelerated Life Testing (HALT) | Person_710 | 2014-12-22 01:00 | 2017-06-22 | 0.4 | 10.4903 | 4.1961 | Avoid | 0.2 | 10.4903 | 2.0981 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 35.885 | 25.4784 | Accept | 0.1 | 15.3199 | 4.596 | H2 | 4 | Stable | 0.6 | 116 | 135 | 154 | 135 | 0.6 | 116 | 135 | 154 | 135 | 57.3082 | -233.3333 | 0 | 34.3849
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 30.7697 | 15.0772 | Accept | 0.25 | 13.0349 | 3.9105 | H2 | 4 | Stable | 0.5 | 111 | 121 | 141 | 122.6667 | 0.5 | 111 | 121 | 141 | 122.6667 | 57.6371 | 0 | 0 | 34.5823
2017-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of Batch 2 Re-Design | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 14.541 | 5.8164 | Accept | 0.3 | 14.541 | 5.8164 | H2 | 4 | Stable | 0.9 | 84 | 139 | 157 | 132.8333 | 0.9 | 84 | 139 | 157 | 132.8333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_073 | 2016-05-23 | 2017-02-19 01:00 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.8 | 88 | 128 | 147 | 124.5 | 0.2 | 33 | 54 | 76 | 54.1667 | 0 | 50 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_413 | 2015-11-21 01:00 | 2017-05-22 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.9 | 86 | 131 | 141 | 125.1667 | 0.3 | 30 | 47 | 77 | 49.1667 | 0 | 5 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.8 | 8.7765 | 7.0212 | Reduce | 0.45 | 8.7765 | 3.9494 | H1 | 5 | Stable | 0.5 | 84 | 124 | 142 | 120.3333 | 0.1 | 7 | 45 | 73 | 43.3333 | 0 | 43.75 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK306(028) | Project_024_RISK306(028) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | HW repairs required on units | Person_119 | 2016-11-19 01:00 | 2018-11-20 01:00 | 0.3 | 2.813 | 0.8439 | Reduce | 0.2 | 2.813 | 0.5626 | H2 | 4 | Stable | 0.5 | 89 | 126 | 142 | 122.5 | 0.2 | 21 | 57 | 71 | 53.3333 | 0 | 33.3333 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Suppliers | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 0.5626 | 0.14065 | Accept | 0.15 | 0.5626 | 0.14065 | H2 | 4 | Stable | 0.7 | 91 | 129 | 142 | 124.8333 | 0.7 | 91 | 129 | 142 | 124.8333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 5.1932 | 2.0773 | Accept | 0.2 | 5.1716 | 2.0686 | H2 | 4 | Stable | 0.6 | 95 | 132 | 155 | 129.6667 | 0.6 | 95 | 132 | 155 | 129.6667 | 0.41665 | 0 | 0 | 0.24999
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Local customer Engineers in country | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 5.1932 | 1.2983 | Accept | 0.1 | 5.1932 | 1.2983 | H2 | 4 | Stable | 0.6 | 120 | 125 | 150 | 128.3333 | 0.6 | 120 | 125 | 150 | 128.3333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence | Person_455 | 2016-05-23 | 2020-05-23 | 0.3 | 5.1932 | 1.558 | Accept | 0.3 | 5.1932 | 1.558 | H2 | 4 | Stable | 0.8 | 87 | 139 | 142 | 130.8333 | 0.8 | 87 | 139 | 142 | 130.8333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Consumables | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 5.3577 | 1.3394 | Accept | 0.2 | 5.3577 | 1.3394 | H2 | 4 | Stable | 0.9 | 93 | 137 | 141 | 130.3333 | 0.9 | 93 | 137 | 141 | 130.3333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK302(024) | Project_024_RISK302(024) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | On time provision of platform units | Person_119 | 2016-11-19 01:00 | 2019-05-23 | 0.25 | 2.3889 | 0.59722 | Reduce | 0.15 | 2.3889 | 0.35833 | H2 | 4 | Stable | 0.5 | 103 | 133 | 157 | 132 | 0.2 | 11 | 49 | 62 | 44.8333 | 0 | 40 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 7. Finance | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 4.8297 | 1.6904 | Accept | 0.2 | 4.8297 | 1.6904 | H2 | 4 | Stable | 0.9 | 101 | 130 | 155 | 129.3333 | 0.9 | 101 | 130 | 155 | 129.3333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 5.1067 | 1.0213 | Accept | 0.15 | 5.1067 | 1.0213 | H2 | 4 | Stable | 0.5 | 114 | 140 | 147 | 136.8333 | 0.5 | 114 | 140 | 147 | 136.8333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 4.1546 | 0.41546 | Accept | 0.2 | 4.1546 | 0.41546 | H2 | 4 | Stable | 0.9 | 93 | 122 | 145 | 121 | 0.9 | 93 | 122 | 145 | 121 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport Routes | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 0.5626 | 0.19691 | Accept | 0.15 | 0.5626 | 0.19691 | H2 | 4 | Stable | 0.6 | 84 | 121 | 146 | 119 | 0.6 | 84 | 121 | 146 | 119 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 0.4 | 9.139 | 3.6556 | Avoid | 0.2 | 9.139 | 1.8278 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 0.125 | 232.2192 | 29.0274 | -- | 0.215 | 27.8663 | 5.9913 | H2 | 4 | Stable | [10 empty] | 88 | -72 | 0 | 52.8
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 0.5 | 13.7833 | 6.8917 | Avoid | 0.2 | 6.8917 | 1.3783 | H3 | 3 | Stable | [10 empty] | 50 | 60 | 1 | 31.8
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-20 01:00 | 0.3 | 5.5433 | 1.663 | Reduce | 0.35 | 5.5433 | 1.9402 | H2 | 4 | Worsening | 0.7 | 107 | 131 | 157 | 131.3333 | 0.4 | 32 | 57 | 71 | 55.1667 | 0 | -16.6667 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Worsening | [10 empty] | 0 | 75 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Internal Quality Issues | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 4.4946 | 1.1236 | Accept | 0.2 | 4.4946 | 0.44946 | H2 | 4 | Stable | 0.9 | 119 | 122 | 145 | 125.3333 | 0.9 | 119 | 122 | 145 | 125.3333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk017 | Project_042_Risk017 | Threat | Financial Contingency | Open | H2 | 4 | 6. Contractual/Legal | Liquidated Damages | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 6.7418 | 1.6855 | Accept | 0.4 | 6.7418 | 1.0113 | H2 | 4 | Stable | 0.5 | 100 | 140 | 150 | 135 | 0.5 | 100 | 140 | 150 | 135 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 0.3 | 26.9674 | 8.0902 | Avoid | 0.3 | 14.9819 | 4.4946 | H2 | 4 | Stable | [10 empty] | 44.4444 | 0 | 0 | 26.6667
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-21 01:00 | 0.5 | 26.9674 | 13.4837 | Avoid | 0.1 | 12.7646 | 1.2765 | H2 | 4 | Worsening | [10 empty] | 52.6667 | 80 | 0 | 31.6
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Non-Recurring Engineering higher than expected | Person_674 | 2016-06-01 | 2016-08-04 | 0.4 | 6.5968 | 2.6387 | Reduce | 0.2 | 6.5944 | 1.3189 | H3 | 3 | Improving | 0.5 | 111 | 127 | 158 | 129.5 | 0.3 | 30 | 57 | 68 | 54.3333 | 0.036395 | 50 | 0 | 0.021837
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Repairs | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 1.2004 | 0.24009 | Accept | 0.25 | 1.2004 | 0.24009 | H2 | 4 | Stable | 0.8 | 105 | 133 | 147 | 130.6667 | 0.8 | 105 | 133 | 147 | 130.6667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-08-20 01:00 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.6 | 116 | 133 | 157 | 134.1667 | 0.3 | 10 | 52 | 67 | 47.5 | 50 | 28.5714 | 0 | 30
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-02-19 01:00 | 0.5 | 17.2826 | 8.6413 | Reduce | 0.15 | 17.2826 | 2.5924 | H2 | 4 | Improving | 0.5 | 91 | 127 | 160 | 126.5 | 0.4 | 17 | 44 | 76 | 44.8333 | 0 | 70 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_427 | 2012-11-20 01:00 | 2017-06-22 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.9 | 108 | 131 | 152 | 130.6667 | 0.2 | 22 | 47 | 71 | 46.8333 | 0 | 50 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2016-07-20 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.4 | 12.6474 | 5.059 | H2 | 4 | Stable | 0.9 | 81 | 140 | 150 | 131.8333 | 0.2 | 22 | 52 | 63 | 48.8333 | 0 | 33.3333 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2017-08-19 01:00 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.8 | 104 | 128 | 148 | 127.3333 | 0.2 | 36 | 56 | 61 | 53.5 | 0 | 50 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target. | Person_482 | 2013-01-07 01:00 | 2017-06-06 | 0.3 | 4.7676 | 1.4303 | Reduce | 0.15 | 4.7676 | 0.71514 | H2 | 4 | Stable | 0.8 | 94 | 126 | 160 | 126.3333 | 0.2 | 28 | 52 | 71 | 51.1667 | 0 | 50 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 01:00 | 2017-08-20 01:00 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.6 | 87 | 122 | 156 | 121.8333 | 0.2 | 12 | 57 | 79 | 53.1667 | 0 | 33.3333 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2017-05-21 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Worsening | 0.8 | 91 | 139 | 156 | 133.8333 | 0.1 | 39 | 44 | 69 | 47.3333 | 0 | 57.1429 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-05-21 | 0.8 | 0 | 0 | Reduce | 0.6 | 0 | 0 | H1 | 5 | Worsening | 0.8 | 103 | 122 | 151 | 123.6667 | 0.4 | 30 | 44 | 77 | 47.1667 |  | 25 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-05-21 | 0.8 | 1.3243 | 1.0595 | Reduce | 0.6 | 1.3243 | 0.7946 | H1 | 5 | Worsening | 0.8 | 98 | 134 | 146 | 130 | 0.2 | 21 | 52 | 77 | 51 | 0 | 25 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2017-06-22 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.8 | 100 | 121 | 144 | 121.3333 | 0.1 | 21 | 52 | 60 | 48.1667 |  | 50 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 1 | 0 | 0 | H1 | 5 | Stable | 0.9 | 89 | 129 | 154 | 126.5 | 0.3 | 35 | 41 | 61 | 43.3333 |  | -100 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.5 | 107 | 125 | 148 | 125.8333 | 0.3 | 11 | 59 | 62 | 51.5 |  | 60 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-08-20 01:00 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.8 | 103 | 124 | 146 | 124.1667 | 0.4 | 27 | 51 | 62 | 48.8333 | 7.8429 | 40 | 0 | 4.7058
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R050 | Project_021_Risk-R050 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to failure of Customer modification Telemetry | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 0.2 | 2.5604 | 0.51208 | Reduce | 0.02 | 2.0527 | 0.041055 | H2 | 4 | Improving | 0.5 | 118 | 133 | 142 | 132 | 0.3 | 15 | 54 | 79 | 51.6667 | 19.8277 | 90 | 0 | 11.8966
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R053 | Project_021_Risk-R053 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.9 | 85 | 129 | 148 | 124.8333 | 0.3 | 36 | 48 | 66 | 49 |  | 60 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 0.02 | 0 | 0 | Reduce | 0.01 | 0 | 0 | H3 | 3 | Stable | 0.6 | 115 | 140 | 157 | 138.6667 | 0.2 | 23 | 40 | 67 | 41.6667 |  | 50 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R052 | Project_021_Risk-R052 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.6 | 0 | 0 | H1 | 5 | Stable | 0.9 | 118 | 127 | 158 | 130.6667 | 0.3 | 4 | 46 | 73 | 43.5 |  | -20 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R055 | Project_021_Risk-R055 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to lack of personnel resource | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.6 | 99 | 136 | 155 | 133 | 0.2 | 6 | 55 | 61 | 47.8333 |  | 66.6667 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 0.3 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 84 | 129 | 157 | 126.1667 | 0.2 | 2 | 55 | 73 | 49.1667 |  | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 114 | 133 | 153 | 133.1667 | 0.1 | 27 | 44 | 66 | 44.8333 |  | 66.6667 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-08-06 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 99 | 137 | 147 | 132.3333 | 0.3 | 21 | 53 | 61 | 49 |  | 80 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2017-06-22 | 0.3 | 1.076 | 0.32281 | Reduce | 0.05 | 1.076 | 0.053801 | H2 | 4 | Improving | 0.7 | 110 | 131 | 144 | 129.6667 | 0.3 | 19 | 49 | 76 | 48.5 | 0 | 83.3333 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-13 01:00 | 2017-05-07 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.6 | 116 | 140 | 150 | 137.6667 | 0.3 | 4 | 44 | 79 | 43.1667 | 80 | 66.6667 | 0 | 48
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-07-21 | 2018-01-20 01:00 | 0.1 | 0.48559 | 0.048559 | Reduce | 0.1 | 0.48559 | 0.048559 | H2 | 4 | Stable | 0.6 | 97 | 124 | 155 | 124.6667 | 0.2 | 31 | 52 | 67 | 51 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 01:00 | 2016-05-21 | 0.5 | 4.3921 | 2.196 | Reduce | 0.3 | 4.3921 | 1.3176 | H1 | 5 | Stable | 0.5 | 84 | 139 | 142 | 130.3333 | 0.1 | 8 | 55 | 64 | 48.6667 | 0 | 40 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk016 | Project_042_Risk016 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport/Delivery Speed | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 0.79975 | 0.79975 | Accept | 0.1 | 0.79934 | 0.79934 | H2 | 4 | Stable | 0.5 | 97 | 138 | 151 | 133.3333 | 0.5 | 97 | 138 | 151 | 133.3333 | 0.051948 | 0 | 0 | 0.031169
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Country Stability | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 0.80702 | 0.80702 | Accept | 0.4 | 0.80702 | 0.80702 | H2 | 4 | Stable | 0.8 | 116 | 126 | 144 | 127.3333 | 0.8 | 116 | 126 | 144 | 127.3333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 0 | 0 | Accept | 0.1 | 0 | 0 | H2 | 4 | Stable | 0.8 | 97 | 132 | 149 | 129 | 0.8 | 97 | 132 | 149 | 129 |  | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 0 | 0 | Accept | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.9 | 90 | 128 | 142 | 124 | 0.9 | 90 | 128 | 142 | 124 |  | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 19:00 | 2019-08-20 19:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.7 | 120 | 140 | 149 | 138.1667 | 0.3 | 21 | 55 | 76 | 52.8333 | 83.3333 | 88.8889 | 1 | 52.6667
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.6 | 109 | 125 | 159 | 128 | 0.1 | 20 | 51 | 61 | 47.5 | 72 | 0 | 0 | 43.2
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.9 | 80 | 129 | 148 | 124 | 0.3 | 31 | 52 | 71 | 51.6667 | 47.7391 | 0 | 0 | 28.6435
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 19:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.5 | 96 | 136 | 154 | 132.3333 | 0.2 | 12 | 59 | 66 | 52.3333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.7 | 97 | 139 | 149 | 133.6667 | 0.1 | 32 | 45 | 75 | 47.8333 | 25.8065 | 20 | 0 | 15.4839
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.7 | 91 | 129 | 146 | 125.5 | 0.2 | 21 | 59 | 63 | 53.3333 | 0 | 0 | 1 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-080 | Project_008_Risk-080 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Recovery of Costs | Person_565 | 2016-08-21 01:00 | 2017-05-21 | 0.5 | 23.6737 | 11.8369 | -- | 0.5 | 23.6737 | 11.8369 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-059 | Project_008_Risk-059 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Project Resource Efficencies | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 0.2 | 21.6852 | 4.337 | -- | 0.15 | 21.6852 | 3.2528 | H3 | 3 | Worsening | [10 empty] | 0 | 25 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2017-02-20 01:00 | 2018-05-22 | 0.1 | 15.8141 | 3.9535 | Accept | 0.1 | 15.8141 | 3.9535 | H3 | 3 | Stable | 0.7 | 104 | 133 | 158 | 132.3333 | 0.7 | 104 | 133 | 158 | 132.3333 | 0 | 0 | 1 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Survey costs | Person_618 | 2016-04-22 | 2017-08-20 01:00 | 0.3 | 13.2573 | 3.9772 | Reduce | 0.3 | 13.2573 | 3.9772 | H3 | 3 | Improving | 0.6 | 120 | 137 | 141 | 134.8333 | 0.3 | 38 | 44 | 70 | 47.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-079 | Project_008_Risk-079 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Regulations Phase 3 and 4 | Person_565 | 2016-10-21 01:00 | 2018-08-21 | 0.25 | 71.9682 | 17.992 | -- | 0.25 | 71.9682 | 17.992 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 0.3 | 71.0212 | 21.3064 | Accept | 0.3 | 71.0212 | 21.3064 | H2 | 4 | Improving | 0.7 | 103 | 139 | 141 | 133.3333 | 0.7 | 103 | 139 | 141 | 133.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Obsolescence Monitoring Risk | Person_181 | 2016-12-02 21:00 | 2017-01-19 21:00 | 0.3 | 5.9458 | 1.7837 | Reduce | 0.15 | 0.9786 | 0.14679 | H3 | 3 | Stable | 0.6 | 107 | 121 | 156 | 124.5 | 0.1 | 26 | 52 | 68 | 50.3333 | 83.5413 | 50 | 0 | 50.1248
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_288 | 2017-02-22 01:00 | 2017-11-19 01:00 | 0.3 | 3.0903 | 0.61807 | Accept | 0.3 | 3.0903 | 0.61807 | H2 | 4 | Improving | 0.5 | 90 | 136 | 141 | 129.1667 | 0.5 | 90 | 136 | 141 | 129.1667 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK209 | Project_024_RISK209 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Major Return to Service | Person_073 | 2016-11-20 01:00 | 2017-05-22 | 0.3 | 30.9033 | 7.7258 | Accept | 0.3 | 30.9033 | 7.7258 | H2 | 4 | Stable | 0.8 | 118 | 123 | 143 | 125.5 | 0.8 | 118 | 123 | 143 | 125.5 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK291 | Project_024_RISK291 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | LoE Engineering support required post completion in addition to BCR | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 15.0654 | 6.7794 | Accept | 0.5 | 15.0654 | 6.7794 | H1 | 5 | Worsening | 0.5 | 108 | 131 | 147 | 129.8333 | 0.5 | 108 | 131 | 147 | 129.8333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unforseen and substantial increase in Repairs workload during new build production period. | Person_515 | 2017-10-23 01:00 | 2017-11-19 01:00 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.03 | 1.5434 | 0.046303 | H3 | 3 | Stable | 0.6 | 88 | 125 | 145 | 122.1667 | 0.2 | 17 | 59 | 68 | 53.5 | 0 | 90 | 1 | 2.7
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 01:00 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.8 | 96 | 132 | 160 | 130.6667 | 0.3 | 27 | 44 | 79 | 47 | 0 | 40 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_693 | 2017-05-23 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Worsening | 0.7 | 83 | 138 | 155 | 131.6667 | 0.2 | 38 | 41 | 78 | 46.6667 | 0 | 50 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK210 | Project_024_RISK210 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Performance impacts regualotory complaince | Person_534 | 2016-06-22 | 2017-02-19 01:00 | 0.3 | 11.0894 | 0.55447 | Accept | 0.3 | 11.0894 | 0.55447 | H2 | 4 | Stable | 0.6 | 91 | 132 | 148 | 127.8333 | 0.6 | 91 | 132 | 148 | 127.8333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2017-04-22 | 2018-05-22 | 0.75 | 10.7184 | 8.0388 | Reduce | 0.15 | 5.3592 | 0.80388 | H3 | 3 | Worsening | 0.7 | 88 | 121 | 154 | 121 | 0.2 | 22 | 50 | 66 | 48 | 50 | 80 | 1 | 32.4
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.7 | 0.92411 | 0.64688 | Reduce | 0.3 | 0.36965 | 0.11089 | H2 | 4 | Stable | 0.9 | 111 | 132 | 148 | 131.1667 | 0.2 | 12 | 59 | 62 | 51.6667 | 60 | 57.1429 | 0 | 36
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 01:00 | 2016-04-21 | 0.5 | 4.0661 | 2.033 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.7 | 85 | 128 | 152 | 124.8333 | 0.2 | 13 | 42 | 76 | 42.8333 | 0 | 90 | 1 | 2.7
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK237 | Project_024_RISK237 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer coding standard Compliance | Person_534 | 2017-05-25 | 2018-01-27 01:00 | 0.2 | 2.5081 | 1.2541 | Accept | 0.2 | 2.5081 | 1.2541 | H2 | 4 | Stable | 0.8 | 89 | 133 | 154 | 129.1667 | 0.8 | 89 | 133 | 154 | 129.1667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.5 | 0.46206 | 0.23103 | H1 | 5 | Improving | 0.9 | 83 | 135 | 148 | 128.5 | 0.3 | 12 | 50 | 79 | 48.5 | 58.3333 | 16.6667 | 0 | 35
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2017-05-23 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.05 | 1.2219 | 0.061095 | H3 | 3 | Stable | 0.6 | 87 | 138 | 156 | 132.5 | 0.3 | 3 | 57 | 70 | 50.1667 | -78.1248 | 80 | 1 | -44.4749
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 01:00 | 2017-08-20 01:00 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.5 | 113 | 133 | 147 | 132 | 0.3 | 15 | 51 | 65 | 47.3333 | 0 | 50 | 1 | 1.5
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Equipment environmental failure | Person_710 | 2016-05-23 | 2017-09-19 01:00 | 0.3 | 3.7514 | 0.37514 | Accept | 0.3 | 3.7514 | 0.37514 | H2 | 4 | Improving | 0.9 | 93 | 122 | 144 | 120.8333 | 0.9 | 93 | 122 | 144 | 120.8333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.9 | 118 | 131 | 153 | 132.5 | 0.3 | 38 | 51 | 64 | 51 | 0 | 25 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2017-05-23 | 2017-07-21 | 0.1 | 21.8655 | 2.1865 | Reduce | 0.01 | 21.8655 | 0.21865 | H2 | 4 | Stable | 0.7 | 103 | 129 | 142 | 126.8333 | 0.4 | 20 | 45 | 72 | 45.3333 | 0 | 90 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Stable | 0.7 | 82 | 139 | 154 | 132 | 0.1 | 1 | 47 | 71 | 43.3333 | 0 | 40 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2017-05-23 | 2018-05-22 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Stable | 0.9 | 85 | 137 | 155 | 131.3333 | 0.3 | 8 | 55 | 66 | 49 | 0 | 60 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Worsening | [10 empty] | 0 | 37.5 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Unidentified CRs and concessions | Person_693 | 2017-04-22 | 2017-09-20 01:00 | 0.5 | 1.2005 | 0.60023 | Reduce | 0.15 | 0.51019 | 0.076529 | H3 | 3 | Stable | 0.9 | 80 | 125 | 156 | 122.6667 | 0.2 | 37 | 49 | 61 | 49 | 57.5001 | 70 | 1 | 36.6001
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Retained systems re-design or modification | Person_710 | 2016-08-20 01:00 | 2017-08-19 01:00 | 0.05 | 3.6965 | 0.36965 | Accept | 0.05 | 3.6965 | 0.36965 | H2 | 4 | Improving | 0.5 | 115 | 126 | 151 | 128.3333 | 0.5 | 115 | 126 | 151 | 128.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_238 | 2017-04-22 | 2018-05-22 | 0.25 | 3.3227 | 0.83067 | Reduce | 0.05 | 3.3227 | 0.16613 | H3 | 3 | Stable | 0.6 | 108 | 136 | 160 | 135.3333 | 0.3 | 5 | 41 | 70 | 39.8333 | 0 | 80 | 1 | 2.4
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Mission System not compatible with platform systems | Person_710 | 2016-07-21 | 2017-08-20 01:00 | 0.1 | 0.92411 | 0.18482 | Accept | 0.1 | 0.92411 | 0.18482 | H3 | 3 | Stable | 0.9 | 86 | 123 | 146 | 120.6667 | 0.9 | 86 | 123 | 146 | 120.6667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_693 | 2017-05-23 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.1 | 0.77172 | 0.077172 | H3 | 3 | Stable | 0.6 | 81 | 131 | 150 | 125.8333 | 0.3 | 35 | 44 | 61 | 45.3333 | 0 | 60 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Qual failure | Person_710 | 2016-06-22 | 2017-06-22 | 0.4 | 1.8482 | 0.55447 | Accept | 0.4 | 1.8482 | 0.73929 | H1 | 5 | Improving | 0.8 | 81 | 137 | 144 | 128.8333 | 0.8 | 81 | 137 | 144 | 128.8333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production or Engineering | Person_725 | 2018-01-21 01:00 | 2019-06-24 | 0.3 | 1.7492 | 0.52477 | Reduce | 0.1 | 1.7492 | 0.17492 | H3 | 3 | Stable | 0.6 | 115 | 138 | 154 | 136.8333 | 0.2 | 27 | 46 | 61 | 45.3333 | 0 | 66.6667 | 1 | 2
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 01:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.7 | 107 | 137 | 160 | 135.8333 | 0.1 | 19 | 47 | 66 | 45.5 | 90 | 75 | 1 | 56.25
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_693 | 2017-05-23 | 2018-11-20 01:00 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.08 | 6.431 | 0.51448 | H3 | 3 | Improving | 0.9 | 83 | 139 | 143 | 130.3333 | 0.1 | 1 | 48 | 66 | 43.1667 | -47.0588 | 46.6667 | 1 | -26.8353
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Additional minor point releases | Person_073 | 2016-05-23 | 2017-08-20 01:00 | 0.5 | 0.21008 | 0.10504 | Accept | 0.5 | 0.21008 | 0.05252 | H1 | 5 | Stable | 0.8 | 107 | 134 | 143 | 131 | 0.8 | 107 | 134 | 143 | 131 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Reduce touch labour if Production readiness programme successful | Person_238 | 2017-05-23 | 2017-10-21 01:00 | 0.3 | 1.5606 | 0.46818 | Exploit | 0.5 | 1.5606 | 0.7803 | H2 | 4 | Stable | [10 empty] | 0 | -66.6667 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.41 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -2.5 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.61 | 0.25667 | 0.15657 | Reduce | 0.5 | 0.25667 | 0.12834 | H2 | 4 | Stable | 0.5 | 89 | 123 | 157 | 123 | 0.1 | 7 | 51 | 69 | 46.6667 | 0 | 18.0328 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 1.078 | 0.43121 | Reduce | 0.4 | 1.4673 | 0.58692 | H2 | 4 | Improving | 0.8 | 120 | 129 | 143 | 129.8333 | 0.4 | 36 | 54 | 74 | 54.3333 | -36.1112 | 0 | 0 | -21.6667
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-118 | Project_029_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Acceptance Schedule is longer in duration/delayed due to unplanned events. [Hardware availability] | Person_102 | 2017-01-21 01:00 | 2017-05-23 | 0.55 | 1.3775 | 0.75761 | Reduce | 0.55 | 1.3775 | 0.75761 | H2 | 4 | Stable | 0.8 | 95 | 121 | 147 | 121 | 0.2 | 38 | 42 | 78 | 47.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2017-11-19 01:00 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2017-09-20 01:00 | 0.6 | 0.89835 | 0.53901 | Transfer | 0.6 | 0.89835 | 0.53901 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 0.35 | 0.85557 | 0.29945 | Reduce | 0.35 | 1.9208 | 0.67227 | H2 | 4 | Stable | 0.5 | 80 | 135 | 146 | 127.6667 | 0.4 | 3 | 41 | 76 | 40.5 | -124.5001 | 0 | 0 | -74.7001
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 0.77001 | 0.30801 | Reduce | 0.3 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.7 | 82 | 140 | 157 | 133.1667 | 0.3 | 29 | 46 | 69 | 47 | 0 | 25 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2018-02-20 01:00 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.8 | 107 | 127 | 152 | 127.8333 | 0.3 | 37 | 54 | 68 | 53.5 | 0 | 28.5714 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digital Video Chainredesign | Person_710 | 2016-06-22 | 2017-05-22 | 0.71 | 1.54 | 0.30801 | Accept | 0.3 | 0.77001 | 0.154 | H2 | 4 | Worsening | 0.5 | 104 | 137 | 144 | 132.6667 | 0.5 | 104 | 137 | 144 | 132.6667 | 50 | 57.7465 | 0 | 30
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK189 | Project_024_RISK189 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment integration - Audio and Video recording | Person_710 | 2016-08-20 01:00 | 2017-09-19 01:00 | 0.49 | 0.94968 | 0.28491 | Accept | 0.3 | 0.94968 | 0.18994 | H1 | 5 | Worsening | 0.6 | 118 | 137 | 156 | 137 | 0.6 | 118 | 137 | 156 | 137 | 0 | 38.7755 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_641 | 2016-05-23 | 2017-08-19 01:00 | 0.4 | 27.1644 | 0.81493 | Accept | 0.4 | 12.8336 | 1.2834 | H1 | 5 | Stable | 0.5 | 88 | 123 | 153 | 122.1667 | 0.5 | 88 | 123 | 153 | 122.1667 | 52.7559 | 0 | 0 | 31.6535
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2018-03-22 | 2019-07-21 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.6 | 108 | 131 | 147 | 129.8333 | 0.2 | 27 | 57 | 65 | 53.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2017-10-14 01:00 | 0.41 | 6.4168 | 2.6309 | Transfer | 0.41 | 0 | 0 | H1 | 5 | Stable | [10 empty] | 100 | 0 | 0 | 60
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub-system FPGA | Person_216 | 2017-01-21 01:00 | 2017-08-20 01:00 | 0.3 | 1.54 | 0.46201 | Reduce | 0.4 | 1.5914 | 0.63655 | H2 | 4 | Stable | 0.9 | 118 | 132 | 154 | 133.3333 | 0.4 | 21 | 46 | 76 | 46.8333 | -3.3333 | -33.3333 | 0 | -2
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort for System HW/SW- System upgrade | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.3 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.9 | 96 | 130 | 142 | 126.3333 | 0.2 | 15 | 53 | 75 | 50.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs [technical scope] | Person_372 | 2017-06-23 | 2018-05-22 | 0.35 | 9.505 | 3.3267 | Reduce | 0.35 | 9.505 | 3.3267 | H2 | 4 | Stable | 0.7 | 82 | 133 | 152 | 127.6667 | 0.2 | 15 | 42 | 69 | 42 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.5 | 3.5934 | 1.7967 | H2 | 4 | Stable | 0.5 | 80 | 126 | 142 | 121 | 0.2 | 34 | 49 | 70 | 50 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | HW - additional unplanned design effort | Person_216 | 2016-05-23 | 2019-10-21 01:00 | 0.4 | 3.3367 | 1.3347 | Reduce | 0.4 | 3.3367 | 1.3347 | H2 | 4 | Stable | 0.7 | 91 | 127 | 157 | 126 | 0.2 | 18 | 47 | 73 | 46.5 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK300(020) | Project_024_RISK300(020) | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Travel and onsite support | Person_119 | 2017-01-20 01:00 | 2017-07-20 | 0.25 | 3.9356 | 0.98391 | Accept | 0.25 | 4.2779 | 1.0695 | H3 | 3 | Stable | 0.6 | 82 | 128 | 145 | 123.1667 | 0.6 | 82 | 128 | 145 | 123.1667 | -8.6957 | 0 | 0 | -5.2174
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK304(026) | Project_024_RISK304(026) | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | complex integration | Person_119 | 2016-10-20 01:00 | 2017-07-20 | 0.4 | 2.5667 | 0.77001 | Accept | 0.4 | 2.5667 | 0.77001 | H1 | 5 | Worsening | 0.6 | 92 | 136 | 145 | 130.1667 | 0.6 | 92 | 136 | 145 | 130.1667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design [in addition to costed effort] | Person_216 | 2017-05-28 | 2017-10-17 01:00 | 0.2 | 2.6951 | 0.53901 | Reduce | 0.2 | 2.6951 | 0.53901 | H3 | 3 | Improving | 0.7 | 86 | 125 | 148 | 122.3333 | 0.4 | 18 | 58 | 70 | 53.3333 | 0 | 0 | 1 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_692 | 2016-12-21 01:00 | 2017-12-19 01:00 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Stable | 0.7 | 93 | 124 | 152 | 123.5 | 0.3 | 10 | 59 | 60 | 51 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_692 | 2017-05-23 | 2019-07-21 | 0.333 | 11.5502 | 3.8462 | Reduce | 0.333 | 11.5502 | 3.8462 | H2 | 4 | Stable | 0.7 | 89 | 127 | 151 | 124.6667 | 0.1 | 34 | 57 | 68 | 55 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK225 | Project_024_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | More testing required as a result compliance to Platform Risk | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 5.6866 | 2.8433 | Reduce | 0.3 | 5.6866 | 1.706 | H2 | 4 | Stable | 0.5 | 83 | 123 | 142 | 119.5 | 0.1 | 13 | 52 | 69 | 48.3333 | 0 | 40 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK303(025) | Project_024_RISK303(025) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in contract value from our supplier | Person_119 | 2016-10-20 01:00 | 2019-05-23 | 0.25 | 17.0765 | 1.7076 | Accept | 0.25 | 17.0765 | 1.7076 | H2 | 4 | Stable | 0.5 | 103 | 131 | 147 | 129 | 0.5 | 103 | 131 | 147 | 129 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.8 | 112 | 134 | 157 | 134.1667 | 0.1 | 31 | 44 | 72 | 46.5 | 0 | 60 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK286 | Project_024_RISK286 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Requirement sell off more difficult than expected | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 10.1787 | 5.0893 | Reduce | 0.5 | 10.1787 | 5.0893 | H1 | 5 | Worsening | 0.8 | 98 | 131 | 143 | 127.5 | 0.3 | 24 | 56 | 62 | 51.6667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK288 | Project_024_RISK288 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Unplanned obsolescence and/or repairs to rig assets. | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.6 | 5.8424 | 3.5054 | Reduce | 0.6 | 4.9768 | 2.9861 | H1 | 5 | Stable | 0.8 | 92 | 128 | 142 | 124.3333 | 0.4 | 35 | 53 | 71 | 53 | 14.8148 | 0 | 0 | 8.8889
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK305(027) | Project_024_RISK305(027) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment not available on time | Person_119 | 2016-11-19 01:00 | 2019-05-23 | 0.3 | 19.9938 | 5.9981 | Accept | 0.3 | 19.9938 | 5.9981 | H2 | 4 | Stable | 0.5 | 82 | 131 | 145 | 125.1667 | 0.5 | 82 | 131 | 145 | 125.1667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.5 | 3.843 | 1.9215 | H1 | 5 | Stable | 0.5 | 95 | 127 | 158 | 126.8333 | 0.4 | 6 | 56 | 60 | 48.3333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK296(013) | Project_024_RISK296(013) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Qualification/Certification Requirements flowdown | Person_119 | 2016-10-20 01:00 | 2017-05-22 | 0.25 | 19.4745 | 5.8424 | Accept | 0.25 | 19.4745 | 5.8424 | H2 | 4 | Worsening | 0.9 | 104 | 138 | 147 | 133.8333 | 0.9 | 104 | 138 | 147 | 133.8333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Overland performance | Person_075 | 2016-06-23 | 2017-11-19 01:00 | 0.1 | 1.6835 | 0.16835 | Reduce | 0.1 | 3.5011 | 0.35011 | H3 | 3 | Improving | 0.7 | 110 | 123 | 151 | 125.5 | 0.3 | 5 | 49 | 63 | 44 | -107.9692 | 0 | 1 | -64.7815
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before part b finished | Person_119 | 2016-10-20 01:00 | 2017-07-20 | 0.35 | 2.7146 | 2.7146 | Accept | 0.35 | 2.7146 | 2.7146 | H2 | 4 | Worsening | 0.5 | 81 | 135 | 149 | 128.3333 | 0.5 | 81 | 135 | 149 | 128.3333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK298(016) | Project_024_RISK298(016) | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Environmental testing required | Person_119 | 2016-10-20 01:00 | 2017-05-22 | 0.2 | 8.5688 | 4.2844 | Accept | 0.2 | 8.5688 | 4.2844 | H2 | 4 | Stable | 0.8 | 103 | 129 | 145 | 127.3333 | 0.8 | 103 | 129 | 145 | 127.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK213 | Project_024_RISK213 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Rigs requireaccreditation as "Special to Type" Test equipment | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.3 | 38.17 | 11.451 | Avoid | 0.25 | 19.4745 | 4.8686 | H2 | 4 | Stable | [10 empty] | 48.9796 | 16.6667 | 0 | 29.3878
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK256 | Project_024_RISK256 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unable to meet spare capacity requirement | Person_318 | 2016-07-21 | 2018-01-21 01:00 | 0.8 | 0.12983 | 0.10386 | Reduce | 0.05 | 0.12983 | 0.0064915 | H3 | 3 | Stable | 0.5 | 112 | 135 | 148 | 133.3333 | 0.3 | 8 | 45 | 67 | 42.5 | 0 | 93.75 | 1 | 2.8125
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK301(022) | Project_024_RISK301(022) | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Interface delays | Person_119 | 2016-10-20 01:00 | 2017-01-20 01:00 | 0.1 | 4.847 | 1.4541 | Accept | 0.1 | 4.847 | 1.4541 | H3 | 3 | Stable | 0.9 | 90 | 125 | 156 | 124.3333 | 0.9 | 90 | 125 | 156 | 124.3333 | 0 | 0 | 1 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK218 | Project_024_RISK218 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | System issues general | Person_388 | 2016-08-21 01:00 | 2017-06-22 | 0.4 | 90.8811 | 36.3524 | Reduce | 0.3 | 0 | 0 | H1 | 5 | Stable | 0.8 | 97 | 132 | 150 | 129.1667 | 0.3 | 1 | 50 | 70 | 45.1667 | 100 | 25 | 0 | 60
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK261 | Project_024_RISK261 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Viewer may not work | Person_318 | 2016-05-23 | 2017-04-21 | 0.5 | 3.9382 | 1.9691 | Reduce | 0.1 | 3.9382 | 0.39382 | H3 | 3 | Improving | 0.6 | 119 | 135 | 157 | 136 | 0.2 | 2 | 42 | 71 | 40.1667 | 0 | 80 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK222 | Project_024_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Testing Extends beyond target completion | Person_351 | 2017-07-21 | 2018-08-21 | 0.2 | 9.8671 | 1.9734 | Reduce | 0.2 | 9.8671 | 1.9734 | H2 | 4 | Stable | 0.6 | 93 | 139 | 157 | 134.3333 | 0.4 | 13 | 53 | 62 | 47.8333 | 0 | 0 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK299(018) | Project_024_RISK299(018) | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Additional support hours | Person_119 | 2017-01-20 01:00 | 2017-07-20 | 0.35 | 15.5796 | 6.2318 | Accept | 0.35 | 15.5796 | 6.2318 | H3 | 3 | Stable | 0.5 | 104 | 132 | 145 | 129.5 | 0.5 | 104 | 132 | 145 | 129.5 | 0 | 0 | 1 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Performance (collector opportunity) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.284 | 10.8798 | 3.0899 | -- | 0.361 | 10.8798 | 3.9276 | H2 | 4 | Stable | [10 empty] | 0 | -27.1127 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 01:00 | 2016-11-20 01:00 | 0.25 | 12.4637 | 2.4927 | Accept | 0.1 | 12.4637 | 1.2464 | H3 | 3 | Stable | 0.7 | 85 | 138 | 144 | 130.1667 | 0.7 | 85 | 138 | 144 | 130.1667 | 0 | 60 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.2 | 20.8767 | 4.1753 | H2 | 4 | Stable | 0.7 | 81 | 139 | 144 | 130.1667 | 0.4 | 13 | 55 | 67 | 50 | 50 | 50 | 0 | 30
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-20 01:00 | 0.25 | 29.1079 | 19.2112 | Accept | 0.15 | 14.1671 | 7.2252 | H3 | 3 | Stable | 0.5 | 89 | 136 | 152 | 130.8333 | 0.5 | 89 | 136 | 152 | 130.8333 | 51.3292 | 40 | 1 | 31.9975
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.48 | 76.3401 | 36.6432 | Reduce | 0.2858 | 57.5537 | 16.4488 | H1 | 5 | Worsening | 0.6 | 115 | 128 | 152 | 129.8333 | 0.3 | 25 | 55 | 66 | 51.8333 | 24.6088 | 40.4583 | 0 | 14.7653
2017-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK294 | Project_024_RISK294 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | product improvement - Extractor | Person_075 | 2017-03-19 01:00 | 2018-01-21 01:00 | 1 | 25.966 | 7.7898 | Accept | 1 | 10.3864 | 3.1159 | H2 | 4 | Stable | 0.6 | 120 | 134 | 146 | 133.6667 | 0.6 | 120 | 134 | 146 | 133.6667 | 60 | 0 | 0 | 36
2017-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 0.61 | 4.5441 | 0.45441 | Accept | 0.61 | 4.5441 | 0.45441 | H1 | 5 | Stable | 0.9 | 90 | 133 | 149 | 128.5 | 0.9 | 90 | 133 | 149 | 128.5 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 0.45 | 11.9444 | 5.9722 | Accept | 0.45 | 11.9444 | 5.9722 | H2 | 4 | Stable | 0.7 | 82 | 121 | 144 | 118.3333 | 0.7 | 82 | 121 | 144 | 118.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_565 | 2018-05-22 | 2018-08-21 | 0.25 | 35.885 | 25.4784 | Accept | 0.25 | 2.5966 | 0.51932 | H3 | 3 | Stable | 0.5 | 93 | 140 | 152 | 134.1667 | 0.5 | 93 | 140 | 152 | 134.1667 | 92.7641 | 0 | 0 | 55.6585
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Lack of Spares Availability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 0.3 | 14.541 | 5.8164 | Accept | 0.3 | 14.541 | 5.8164 | H2 | 4 | Stable | 0.9 | 81 | 130 | 141 | 123.6667 | 0.9 | 81 | 130 | 141 | 123.6667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_073 | 2016-05-23 | 2017-02-19 01:00 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.5 | 90 | 131 | 150 | 127.3333 | 0.4 | 16 | 50 | 65 | 46.8333 | 0 | 50 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_413 | 2015-11-21 01:00 | 2017-05-22 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.6 | 101 | 125 | 143 | 124 | 0.3 | 8 | 51 | 60 | 45.3333 | 0 | 5 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.8 | 2.8043 | 2.2435 | Reduce | 0.45 | 2.8043 | 1.2619 | H1 | 5 | Stable | 0.6 | 112 | 133 | 152 | 132.6667 | 0.4 | 37 | 45 | 66 | 47.1667 | 0 | 43.75 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK306(028) | Project_024_RISK306(028) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | HW repairs required on units | Person_119 | 2016-11-19 01:00 | 2018-11-20 01:00 | 0.3 | 2.813 | 0.8439 | Reduce | 0.2 | 2.813 | 0.5626 | H2 | 4 | Stable | 0.5 | 95 | 136 | 160 | 133.1667 | 0.4 | 1 | 41 | 76 | 40.1667 | 0 | 33.3333 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.05 | 5.3577 | 1.3394 | Accept | 0.05 | 5.3577 | 1.3394 | H2 | 4 | Stable | 0.9 | 93 | 133 | 144 | 128.1667 | 0.9 | 93 | 133 | 144 | 128.1667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK302(024) | Project_024_RISK302(024) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | On time provision of platform units | Person_119 | 2016-11-19 01:00 | 2019-05-23 | 0.25 | 2.3889 | 0.59722 | Reduce | 0.15 | 2.3889 | 0.35833 | H2 | 4 | Stable | 0.6 | 80 | 133 | 151 | 127.1667 | 0.4 | 31 | 40 | 66 | 42.8333 | 0 | 40 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Risk of not being able to perform Tests | Person_238 | 2017-12-21 01:00 | 2019-01-21 01:00 | 0.5 | 4.8297 | 1.6904 | Accept | 0.5 | 4.8297 | 1.6904 | H2 | 4 | Stable | 0.9 | 85 | 128 | 153 | 125 | 0.9 | 85 | 128 | 153 | 125 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_238 | 2017-05-23 | 2019-01-21 01:00 | 0.5 | 5.1067 | 1.0213 | Accept | 0.5 | 5.1067 | 1.0213 | H2 | 4 | Stable | 0.8 | 95 | 132 | 154 | 129.5 | 0.8 | 95 | 132 | 154 | 129.5 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 0.8 | 4.1546 | 0.41546 | Accept | 0.6 | 4.1546 | 0.41546 | H1 | 5 | Stable | 0.8 | 118 | 125 | 143 | 126.8333 | 0.8 | 118 | 125 | 143 | 126.8333 | 0 | 25 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_693 | 2017-04-22 | 2017-09-19 01:00 | 0.6 | 0.5626 | 0.19691 | Accept | 0.6 | 0.5626 | 0.19691 | H2 | 4 | Stable | 0.7 | 86 | 134 | 142 | 127.3333 | 0.7 | 86 | 134 | 142 | 127.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-116 | Project_011_Risk-116 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Delays to Qualification | Person_147 | 2017-04-22 | 2017-08-19 | 0.5 | 0.86486 | 0.43243 | Reduce | 0.5 | 0.86486 | 0.43243 | H1 | 5 | Stable | 0.6 | 85 | 136 | 142 | 128.5 | 0.2 | 14 | 53 | 64 | 48.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-104 | Project_011_Risk-104 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer delayed in providing Custeomr Furnished Equipment | Person_147 | 2016-06-23 | 2017-04-21 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.6 | 101 | 136 | 160 | 134.1667 | 0.2 | 37 | 54 | 62 | 52.5 |  | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_547 | 2017-05-23 | 2018-05-22 | 0.1 | 0.30685 | 0.06137 | Accept | 0.1 | 0.30685 | 0.06137 | H3 | 3 | Stable | 0.5 | 84 | 122 | 150 | 120.3333 | 0.5 | 84 | 122 | 150 | 120.3333 | 0 | 0 | 1 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 0.3 | 0.51931 | 0.15579 | -- | 0.15 | 0.51931 | 0.077897 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 0.2 | 0.55005 | 0.11001 | Avoid | 0.2 | 0.55005 | 0.11001 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-123 | Project_011_Risk-123 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | No Requirement for Delta acceptance | Person_187 | 2017-06-23 | 2017-08-20 | 0.2 | 0.63074 | 0.12615 | -- | 0.2 | 0.63074 | 0.12615 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2016-07-21 | 2017-02-19 | 0.15 | 0.28639 | 0.042959 | -- | 0.15 | 0.28639 | 0.042959 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-04-21 | 0.2 | 0.24207 | 0.048414 | -- | 0.2 | 0.24207 | 0.048414 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 | 2018-08-21 | 0.2 | 1.661 | 0.33219 | Reduce | 0.2 | 1.661 | 0.33219 | H2 | 4 | Stable | 0.6 | 91 | 122 | 152 | 121.8333 | 0.1 | 24 | 54 | 73 | 52.1667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2017-10-21 | 2018-08-21 | 0.4 | 1.2444 | 0.49778 | Reduce | 0.4 | 1.2444 | 0.49778 | H2 | 4 | Stable | 0.6 | 86 | 124 | 142 | 120.6667 | 0.2 | 33 | 45 | 71 | 47.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 01:00 | 2016-08-20 01:00 | 0.1 | 0.16195 | 0.072876 | Accept | 0.1 | 0.16195 | 0.072876 | H2 | 4 | Stable | 0.5 | 112 | 138 | 143 | 134.5 | 0.5 | 112 | 138 | 143 | 134.5 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 | 2018-08-21 | 0.45 | 0.83883 | 0.37747 | Reduce | 0.45 | 0.83883 | 0.37747 | H2 | 4 | Stable | 0.5 | 109 | 140 | 150 | 136.5 | 0.1 | 31 | 57 | 73 | 55.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-010 | Project_011_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Rework required following integration of Customer System | Person_142 | 2013-08-21 | 2017-05-21 | 0.4 | 0.66881 | 0.26753 | Reduce | 0.4 | 0.66881 | 0.26753 | H2 | 4 | Stable | 0.9 | 114 | 131 | 142 | 130 | 0.4 | 10 | 53 | 76 | 49.6667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 0.2 | 0.098873 | 0.0098873 | Accept | 0.2 | 0.098873 | 0.0098873 | H3 | 3 | Improving | 0.6 | 111 | 121 | 143 | 123 | 0.6 | 111 | 121 | 143 | 123 | 0 | 0 | 1 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-02-20 | 2018-08-21 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.7 | 89 | 130 | 153 | 127 | 0.2 | 28 | 58 | 62 | 53.6667 |  | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Pick up and Drop off of Software Resource | Person_230 | 2017-04-21 | 2018-02-19 | 0.4 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-109 | Project_011_Risk-109 | Opportunitity | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Environment complexity | Person_187 | 2016-07-21 | 2018-08-21 | 0.25 | 0.14661 | 0.036651 | -- | 0.25 | 0.14661 | 0.036651 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-108 | Project_011_Risk-108 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Offer additional functionality to the customer | Person_147 | 2017-04-22 | 2018-08-21 | 0.1 | 0.34094 | 0.034094 | -- | 0.1 | 0.34094 | 0.034094 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 0.2 | 0.12388 | 0.024775 | Reduce | 0.2 | 0.12388 | 0.024775 | H2 | 4 | Stable | 0.6 | 120 | 135 | 157 | 136.1667 | 0.2 | 12 | 45 | 62 | 42.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 0.4 | 0.51141 | 0.20457 | Avoid | 0.4 | 0.51141 | 0.20457 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 0.3 | 0.49834 | 0.12459 | Accept | 0.4 | 0.49834 | 0.12459 | H3 | 3 | Stable | 0.5 | 113 | 140 | 144 | 136.1667 | 0.5 | 113 | 140 | 144 | 136.1667 | 0 | -33.3333 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.2 | 0.10171 | 0.020343 | -- | 0.2 | 0.10171 | 0.020343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 0.3 | 0.28639 | 0.085917 | Reduce | 0.3 | 0.28639 | 0.085917 | H2 | 4 | Stable | 0.8 | 105 | 125 | 143 | 124.6667 | 0.2 | 1 | 55 | 78 | 49.8333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 2. Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 0.25 | 0 | 0 | -- | 0.25 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2017-10-21 | 2018-05-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 0.3 | 0.10626 | 0.031878 | -- | 0.3 | 0.01932 | 0.005796 | H3 | 3 | Stable | [10 empty] | 81.8181 | 0 | 0 | 49.0909
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R81 | Project_041_R81 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Re-imaging of PC's - additional material | Person_515 | 2017-05-23 | 2017-10-21 01:00 | 0.5 | 1.0052 | 0.35182 | Accept | 0.25 | 1.0052 | 0.35182 | H2 | 4 | Worsening | 0.8 | 101 | 121 | 152 | 122.8333 | 0.8 | 101 | 121 | 152 | 122.8333 | 0 | 50 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-118 | Project_011_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer change environment | Person_187 | 2013-08-21 | 2018-08-21 | 0.1 | 0 | 0 | Avoid | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2019-10-14 01:00 | 0.2 | 1.8788 | 0.28182 | Accept | 0.2 | 1.8788 | 0.28182 | H3 | 3 | Stable | 0.7 | 119 | 126 | 152 | 129.1667 | 0.7 | 119 | 126 | 152 | 129.1667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2019-07-21 | 0.3 | 9.3941 | 1.8788 | Accept | 0.2 | 9.3941 | 1.8788 | H3 | 3 | Stable | 0.8 | 116 | 133 | 146 | 132.3333 | 0.8 | 116 | 133 | 146 | 132.3333 | 0 | 33.3333 | 1 | 1
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 1.8788 | 0.18788 | Accept | 0.1 | 1.8788 | 0.18788 | H3 | 3 | Stable | 0.9 | 113 | 133 | 146 | 131.8333 | 0.9 | 113 | 133 | 146 | 131.8333 | 0 | -233.3333 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 29.4599 | 8.838 | Accept | 0.25 | 18.7882 | 5.6365 | H2 | 4 | Stable | 0.6 | 106 | 126 | 154 | 127.3333 | 0.6 | 106 | 126 | 154 | 127.3333 | 36.2245 | 0 | 0 | 21.7347
2017-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 1.1273 | 0.22546 | Accept | 0.3 | 1.1273 | 0.22546 | H2 | 4 | Stable | 0.5 | 80 | 125 | 147 | 121.1667 | 0.5 | 80 | 125 | 147 | 121.1667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2017-02-20 01:00 | 2018-05-22 | 0.1 | 4.7948 | 0.95895 | Accept | 0.1 | 4.7948 | 0.95895 | H3 | 3 | Stable | 0.9 | 112 | 133 | 155 | 133.1667 | 0.9 | 112 | 133 | 155 | 133.1667 | 0 | 0 | 1 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_288 | 2017-02-22 01:00 | 2017-11-19 01:00 | 0.3 | 0.65759 | 0.098638 | Accept | 0.3 | 0.65759 | 0.098638 | H2 | 4 | Improving | 0.9 | 82 | 137 | 157 | 131.1667 | 0.9 | 82 | 137 | 157 | 131.1667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK209 | Project_024_RISK209 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Major Return to Service | Person_228 | 2016-11-20 01:00 | 2017-05-22 | 0.3 | 6.7638 | 1.3528 | Accept | 0.3 | 6.7638 | 1.3528 | H2 | 4 | Stable | 0.8 | 97 | 122 | 143 | 121.3333 | 0.8 | 97 | 122 | 143 | 121.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK291 | Project_024_RISK291 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | LoE Engineering support required post completion in addition to BCR | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 2.8182 | 0.56365 | Accept | 0.5 | 2.8182 | 0.56365 | H1 | 5 | Worsening | 0.5 | 80 | 127 | 146 | 122.3333 | 0.5 | 80 | 127 | 146 | 122.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK210 | Project_024_RISK210 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Performance impacts regualotory complaince | Person_534 | 2016-06-22 | 2017-02-19 01:00 | 0.3 | 0 | 0 | Accept | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.7 | 86 | 121 | 154 | 120.6667 | 0.7 | 86 | 121 | 154 | 120.6667 |  | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK237 | Project_024_RISK237 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer coding standard Compliance | Person_534 | 2017-05-25 | 2018-01-27 01:00 | 0.2 | 0.65759 | 0.065759 | Accept | 0.1 | 0.75153 | 0.075153 | H3 | 3 | Stable | 0.5 | 91 | 134 | 147 | 129 | 0.5 | 91 | 134 | 147 | 129 | -14.2857 | 50 | 1 | -7.0714
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Governance and Export Rules | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 0.93941 | 0.23485 | Transfer | 0.25 | 0.93941 | 0.23485 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Equipment environmental failure | Person_710 | 2016-05-23 | 2017-09-19 01:00 | 0.3 | 2.1606 | 0.43213 | Accept | 0.3 | 2.1606 | 0.43213 | H2 | 4 | Improving | 0.8 | 91 | 133 | 141 | 127.3333 | 0.8 | 91 | 133 | 141 | 127.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Retained systems re-design or modification | Person_710 | 2016-08-20 01:00 | 2018-02-19 01:00 | 0.05 | 3.8666 | 1.5853 | Accept | 0.05 | 1.3288 | 0.5448 | H2 | 4 | Improving | 0.9 | 96 | 137 | 150 | 132.3333 | 0.9 | 96 | 137 | 150 | 132.3333 | 65.6338 | 0 | 0 | 39.3803
2017-03-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2017-05-22 | 0.85 | 25.2325 | 21.4476 | Avoid | 0.08 | 10.2019 | 0.81615 | H2 | 4 | Stable | [10 empty] | 59.5683 | 90.5882 | 0 | 35.741
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Mission System not compatible with platform systems | Person_710 | 2016-07-21 | 2017-08-20 01:00 | 0.1 | 5.4459 | 1.6338 | Accept | 0.1 | 0.18151 | 0.054453 | H3 | 3 | Stable | 0.5 | 85 | 138 | 144 | 130.1667 | 0.5 | 85 | 138 | 144 | 130.1667 | 96.667 | 0 | 0 | 58.0002
2017-03-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2017-05-22 | 0.7 | 24.1887 | 16.9321 | Reduce | 0.25 | 2.6322 | 0.65804 | H2 | 4 | Stable | 0.7 | 85 | 139 | 142 | 130.5 | 0.2 | 26 | 40 | 60 | 41 | 89.1182 | 64.2857 | 0 | 53.4709
2017-03-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-62 | Project_022_RISK-62 | Threat | Project Contingency | Open | H3 | 3 | 8. Operations & Maintenance | Additional Costs from Integration Cost Centre | Person_703 | 2017-03-23 | 2017-05-14 | 0.5 | 7.1754 | 3.5877 | Avoid | 0.292 | 3.5877 | 1.0476 | H3 | 3 | Worsening | [10 empty] | 50 | 41.6 | 0 | 30
2017-03-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2017-06-21 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.35 | 2.8688 | 1.0041 | H2 | 4 | Stable | 0.8 | 119 | 127 | 150 | 129.5 | 0.1 | 1 | 50 | 77 | 46.3333 | 22.0253 | 56.25 | 0 | 13.2152
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Qual failure | Person_710 | 2016-06-22 | 2017-06-22 | 0.4 | 2.3975 | 2.3975 | Accept | 0.4 | 0 | 0 | H1 | 5 | Improving | 0.8 | 90 | 121 | 144 | 119.6667 | 0.8 | 90 | 121 | 144 | 119.6667 | 100 | 0 | 0 | 60
2017-03-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2017-04-21 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 0.65554 | 0.52443 | H2 | 4 | Stable | [10 empty] | 80.45 | 0 | 0 | 48.27
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-148 | Project_020_Risk-148 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs non-available items | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.3 | 14.9935 | 4.498 | Reduce | 0.3 | 2.6369 | 0.79106 | H2 | 4 | Stable | 0.5 | 102 | 127 | 158 | 128 | 0.1 | 10 | 43 | 62 | 40.6667 | 82.4131 | 0 | 0 | 49.4479
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-22 01:00 | 2017-05-22 | 0.25 | 7.4225 | 1.8556 | Reduce | 0.1 | 2.0081 | 0.20081 | H3 | 3 | Stable | 0.8 | 120 | 130 | 146 | 131 | 0.4 | 25 | 52 | 72 | 50.8333 | 72.9455 | 60 | 0 | 43.7673
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 2.6991 | 1.0796 | H2 | 4 | Stable | 0.5 | 117 | 128 | 146 | 129.1667 | 0.1 | 18 | 47 | 74 | 46.6667 | 31.8182 | 20 | 0 | 19.0909
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Additional minor point releases | Person_228 | 2016-05-23 | 2017-08-20 01:00 | 0.5 | 18.6688 | 3.7338 | Accept | 0.5 | 18.6688 | 3.7338 | H1 | 5 | Stable | 0.8 | 91 | 140 | 149 | 133.3333 | 0.8 | 91 | 140 | 149 | 133.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-147 | Project_020_Risk-147 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component taking longer to refurbish in country | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.6 | 6.7477 | 4.0486 | Reduce | 0.6 | 1.8743 | 1.1246 | H2 | 4 | Stable | 0.9 | 116 | 125 | 156 | 128.6667 | 0.3 | 35 | 49 | 79 | 51.6667 | 72.2227 | 0 | 0 | 43.3336
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digital Video Chainredesign | Person_710 | 2016-06-22 | 2017-05-22 | 0.71 | 18.069 | 1.8069 | Accept | 0.2 | 11.3212 | 1.1321 | H2 | 4 | Worsening | 0.7 | 118 | 124 | 157 | 128.5 | 0.7 | 118 | 124 | 157 | 128.5 | 37.3444 | 71.831 | 0 | 22.4066
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_641 | 2016-05-23 | 2017-08-19 01:00 | 0.4 | 4.4985 | 1.3495 | Accept | 0.4 | 2.999 | 0.8997 | H1 | 5 | Stable | 0.8 | 113 | 122 | 149 | 125 | 0.8 | 113 | 122 | 149 | 125 | 33.333 | 0 | 0 | 19.9998
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_703 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 5.0983 | 0.76474 | H3 | 3 | Stable | 0.7 | 87 | 138 | 153 | 132 | 0.1 | 17 | 49 | 70 | 47.1667 | 19.0479 | 70 | 1 | 13.5287
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK300(020) | Project_024_RISK300(020) | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Travel and onsite support | Person_119 | 2017-01-20 01:00 | 2017-07-20 | 0.25 | 31.83 | 23.8725 | Accept | 0.25 | 31.83 | 23.8725 | H3 | 3 | Stable | 0.6 | 118 | 134 | 151 | 134.1667 | 0.6 | 118 | 134 | 151 | 134.1667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.6 | 100 | 138 | 153 | 134.1667 | 0.3 | 29 | 52 | 78 | 52.5 | 0 | 25 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK304(026) | Project_024_RISK304(026) | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | complex integration | Person_119 | 2016-10-20 01:00 | 2017-07-20 | 0.4 | 3.4415 | 1.3766 | Accept | 0.4 | 3.4415 | 1.3766 | H1 | 5 | Worsening | 0.7 | 101 | 126 | 147 | 125.3333 | 0.7 | 101 | 126 | 147 | 125.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK303(025) | Project_024_RISK303(025) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in contract value from our supplier | Person_119 | 2016-10-20 01:00 | 2019-05-23 | 0.25 | 8.0582 | 2.4175 | Accept | 0.25 | 8.0582 | 2.4175 | H2 | 4 | Stable | 0.8 | 116 | 133 | 148 | 132.6667 | 0.8 | 116 | 133 | 148 | 132.6667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK305(027) | Project_024_RISK305(027) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment not available on time | Person_119 | 2016-11-19 01:00 | 2019-05-23 | 0.3 | 0 | 0 | Accept | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 95 | 139 | 142 | 132.1667 | 0.6 | 95 | 139 | 142 | 132.1667 |  | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK296(013) | Project_024_RISK296(013) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Qualification/Certification Requirements flowdown | Person_119 | 2016-10-20 01:00 | 2017-05-22 | 0.25 | 0.5596 | 0.05596 | Accept | 0.25 | 0.5596 | 0.05596 | H2 | 4 | Worsening | 0.5 | 98 | 133 | 146 | 129.3333 | 0.5 | 98 | 133 | 146 | 129.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before part b finished | Person_119 | 2016-10-20 01:00 | 2017-07-20 | 0.35 | 3.6174 | 1.8087 | Accept | 0.35 | 3.6172 | 0.72345 | H2 | 4 | Worsening | 0.9 | 110 | 126 | 144 | 126.3333 | 0.9 | 110 | 126 | 144 | 126.3333 | 0.0051359 | 0 | 0 | 0.0030815
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK298(016) | Project_024_RISK298(016) | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Environmental testing required | Person_119 | 2016-10-20 01:00 | 2017-05-22 | 0.2 | 2.3503 | 0.47006 | Accept | 0.2 | 2.3503 | 0.47006 | H2 | 4 | Stable | 0.5 | 105 | 125 | 148 | 125.5 | 0.5 | 105 | 125 | 148 | 125.5 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK301(022) | Project_024_RISK301(022) | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Interface delays | Person_119 | 2016-10-20 01:00 | 2017-05-22 | 0.1 | 4.4768 | 2.2384 | Accept | 0.1 | 4.4768 | 2.2384 | H3 | 3 | Stable | 0.6 | 92 | 136 | 143 | 129.8333 | 0.6 | 92 | 136 | 143 | 129.8333 | 0 | 0 | 1 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK299(018) | Project_024_RISK299(018) | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Additional support hours | Person_119 | 2017-01-20 01:00 | 2017-07-20 | 0.35 | 244.3581 | 12.2179 | Accept | 0.35 | 227.5702 | 11.3785 | H3 | 3 | Stable | 0.5 | 118 | 139 | 152 | 137.6667 | 0.5 | 118 | 139 | 152 | 137.6667 | 6.8702 | 0 | 1 | 4.1221
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 0.2 | 24.8462 | 12.4231 | Accept | 0.2 | 24.8462 | 12.4231 | H2 | 4 | Stable | 0.9 | 80 | 127 | 145 | 122.1667 | 0.9 | 80 | 127 | 145 | 122.1667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 0.4 | 9.139 | 3.6556 | Avoid | 0.2 | 9.139 | 1.8278 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 0.125 | 232.2192 | 29.0274 | -- | 0.215 | 27.8663 | 5.9913 | H2 | 4 | Stable | [10 empty] | 88 | -72 | 0 | 52.8
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 0.5 | 13.7833 | 6.8917 | Avoid | 0.2 | 6.8917 | 1.3783 | H3 | 3 | Stable | [10 empty] | 50 | 60 | 1 | 31.8
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-20 01:00 | 0.3 | 5.5433 | 1.663 | Reduce | 0.35 | 5.5433 | 1.9402 | H2 | 4 | Worsening | 0.8 | 109 | 138 | 158 | 136.5 | 0.1 | 15 | 51 | 61 | 46.6667 | 0 | -16.6667 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Worsening | [10 empty] | 0 | 75 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 0.25 | 6.7418 | 1.6855 | Accept | 0.25 | 6.7418 | 1.0113 | H3 | 3 | Stable | 0.6 | 105 | 130 | 144 | 128.1667 | 0.6 | 105 | 130 | 144 | 128.1667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 0.3 | 26.9674 | 8.0902 | Avoid | 0.3 | 14.9819 | 4.4946 | H2 | 4 | Stable | [10 empty] | 44.4444 | 0 | 0 | 26.6667
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-21 01:00 | 0.5 | 26.9674 | 13.4837 | Avoid | 0.1 | 12.7646 | 1.2765 | H2 | 4 | Worsening | [10 empty] | 52.6667 | 80 | 0 | 31.6
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | More issues than expected during Qualification | Person_147 | 2017-04-22 | 2017-11-04 | 0.35 | 13.3529 | 6.6765 | Accept | 0.35 | 23.5716 | 11.7858 | H1 | 5 | Stable | 0.6 | 107 | 138 | 147 | 134.3333 | 0.6 | 107 | 138 | 147 | 134.3333 | -76.5278 | 0 | 0 | -45.9167
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 0.5 | 9.2728 | 4.6364 | Reduce | 0.15 | 9.2728 | 1.3909 | H2 | 4 | Stable | 0.6 | 120 | 126 | 155 | 129.8333 | 0.1 | 28 | 57 | 69 | 54.1667 | 0 | 70 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R008 | Project_016_Risk--R008 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Additional Travel & Subsistence | Person_574 | 2016-01-13 01:00 | 2019-05-23 | 0.4 | 8.9019 | 3.5608 | Reduce | 0.25 | 8.9019 | 2.2255 | H3 | 3 | Stable | 0.7 | 85 | 138 | 143 | 130 | 0.3 | 29 | 43 | 65 | 44.3333 | 0 | 37.5 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 0.3 | 8.7814 | 2.6344 | Reduce | 0.15 | 8.7832 | 1.3175 | H3 | 3 | Stable | 0.9 | 120 | 130 | 145 | 130.8333 | 0.2 | 17 | 50 | 65 | 47 | -0.021119 | 50 | 1 | 1.4873
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R009 | Project_016_Risk--R009 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer maybe difficult to work with | Person_697 | 2016-04-02 | 2019-08-01 | 0.6 | 23.9549 | 14.3729 | Reduce | 0.43864 | 23.8312 | 10.4533 | H2 | 4 | Stable | 0.8 | 114 | 131 | 156 | 132.3333 | 0.2 | 30 | 58 | 65 | 54.5 | 0.51612 | 26.8938 | 0 | 0.30967
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Suppliers | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 108.3186 | 32.4956 | Accept | 0.15 | 108.3186 | 32.4956 | H2 | 4 | Stable | 0.5 | 103 | 123 | 152 | 124.5 | 0.5 | 103 | 123 | 152 | 124.5 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Delay of processing | Person_306 | 2016-04-02 | 2017-03-21 01:00 | 0.15 | 26.3497 | 3.9525 | Reduce | 0.15 | 13.1767 | 1.9765 | H3 | 3 | Stable | 0.9 | 111 | 131 | 159 | 132.3333 | 0.3 | 16 | 48 | 62 | 45 | 49.993 | 0 | 1 | 29.9958
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 12.0547 | 2.4109 | Accept | 0.2 | 12.0547 | 2.4109 | H2 | 4 | Stable | 0.6 | 110 | 126 | 157 | 128.5 | 0.6 | 110 | 126 | 157 | 128.5 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 15:00 | 2019-08-20 15:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 15:00 | 2019-08-20 15:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 15:00 | 2019-08-20 15:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 15:00 | 2019-08-20 15:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 15:00 | 2019-08-20 15:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-21 23:00 | 2016-12-20 23:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.9 | 111 | 122 | 158 | 126.1667 | 0.4 | 8 | 47 | 77 | 45.5 | 47 | 0 | 0 | 28.2
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-21 23:00 | 2016-12-20 23:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-18 23:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.2 | 1.5935 | 0.3187 | H3 | 3 | Stable | 0.9 | 107 | 132 | 157 | 132 | 0.3 | 28 | 47 | 73 | 48.1667 | 50 | 50 | 1 | 31.5
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-20 22:00 | 2016-08-20 22:00 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.7 | 86 | 123 | 149 | 121.1667 | 0.1 | 38 | 50 | 66 | 50.6667 | 0 | 16.6667 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Local customer Engineers in country | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 7.689 | 2.6911 | Accept | 0.1 | 7.689 | 2.6911 | H2 | 4 | Stable | 0.7 | 105 | 126 | 159 | 128 | 0.7 | 105 | 126 | 159 | 128 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence | Person_455 | 2016-05-23 | 2020-05-23 | 0.3 | 5.4336 | 1.3584 | Accept | 0.3 | 5.4336 | 1.3584 | H2 | 4 | Stable | 0.8 | 106 | 121 | 158 | 124.6667 | 0.8 | 106 | 121 | 158 | 124.6667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Consumables | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 5.126 | 2.563 | Accept | 0.2 | 5.126 | 2.563 | H2 | 4 | Stable | 0.9 | 82 | 129 | 144 | 123.6667 | 0.9 | 82 | 129 | 144 | 123.6667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 7. Finance | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 12.815 | 2.563 | Accept | 0.2 | 12.815 | 2.563 | H2 | 4 | Stable | 0.7 | 101 | 121 | 158 | 123.8333 | 0.7 | 101 | 121 | 158 | 123.8333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.7 | 115 | 124 | 152 | 127.1667 | 0.2 | 11 | 55 | 75 | 51 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-08-20 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.5 | 94 | 138 | 142 | 131.3333 | 0.4 | 5 | 46 | 75 | 44 | 50 | 28.5714 | 0 | 30
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2016-02-11 | 2017-11-19 | 0.5 | 17.2826 | 8.6413 | Reduce | 0.15 | 17.2826 | 2.5924 | H2 | 4 | Worsening | 0.6 | 93 | 131 | 142 | 126.5 | 0.1 | 37 | 40 | 63 | 43.3333 | 0 | 70 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_427 | 2012-11-20 | 2017-06-22 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.8 | 108 | 125 | 158 | 127.6667 | 0.3 | 35 | 58 | 75 | 57 | 0 | 50 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 | 2016-07-20 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.4 | 12.6474 | 5.059 | H2 | 4 | Stable | 0.7 | 92 | 124 | 150 | 123 | 0.2 | 14 | 42 | 66 | 41.3333 | 0 | 33.3333 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.5 | 93 | 126 | 155 | 125.3333 | 0.1 | 25 | 40 | 78 | 43.8333 | 0 | 50 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target. | Person_482 | 2013-01-07 | 2017-06-06 | 0.3 | 4.7676 | 1.4303 | Reduce | 0.15 | 4.7676 | 0.71514 | H2 | 4 | Stable | 0.6 | 86 | 123 | 141 | 119.8333 | 0.4 | 26 | 50 | 75 | 50.1667 | 0 | 50 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 | 2017-08-20 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.6 | 81 | 130 | 144 | 124.1667 | 0.3 | 14 | 52 | 76 | 49.6667 | 0 | 33.3333 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 | 2016-12-20 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Improving | 0.6 | 120 | 124 | 160 | 129.3333 | 0.1 | 39 | 45 | 61 | 46.6667 | 0 | 57.1429 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-05-21 | 0.8 | 0 | 0 | Reduce | 0.6 | 0 | 0 | H1 | 5 | Worsening | 0.9 | 119 | 128 | 160 | 131.8333 | 0.1 | 4 | 59 | 68 | 51.3333 |  | 25 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-05-21 | 0.8 | 1.3243 | 1.0595 | Reduce | 0.6 | 1.3243 | 0.7946 | H1 | 5 | Worsening | 0.9 | 106 | 130 | 156 | 130.3333 | 0.3 | 12 | 57 | 73 | 52.1667 | 0 | 25 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2017-06-22 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.6 | 84 | 126 | 156 | 124 | 0.3 | 2 | 44 | 62 | 40 |  | 50 | 1
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trial delay due to weather | Person_174 | 2016-11-18 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 112 | 122 | 145 | 124.1667 | 0.2 | 7 | 51 | 71 | 47 |  | 40 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trial delay due to equip[ment availability | Person_174 | 2016-10-21 | 2017-08-20 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.6 | 115 | 128 | 155 | 130.3333 | 0.4 | 21 | 44 | 71 | 44.6667 |  | 60 | 1
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-08-20 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.9 | 83 | 138 | 151 | 131 | 0.4 | 31 | 52 | 67 | 51 | 7.8429 | 40 | 0 | 4.7058
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 | 2017-06-22 | 0.2 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 101 | 129 | 152 | 128.1667 | 0.3 | 5 | 47 | 78 | 45.1667 |  | 50 | 1
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 | 2017-06-22 | 0.3 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.7 | 96 | 124 | 153 | 124.1667 | 0.3 | 13 | 57 | 68 | 51.5 |  | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 | 2017-06-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 89 | 140 | 147 | 132.6667 | 0.1 | 15 | 51 | 69 | 48 |  | 66.6667 | 1
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-08-06 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 113 | 137 | 154 | 135.8333 | 0.2 | 14 | 41 | 68 | 41 |  | 80 | 1
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2017-06-22 | 0.3 | 1.076 | 0.32281 | Reduce | 0.05 | 1.076 | 0.053801 | H2 | 4 | Improving | 0.9 | 120 | 126 | 146 | 128.3333 | 0.2 | 10 | 43 | 71 | 42.1667 | 0 | 83.3333 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 | 2017-05-07 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.6 | 84 | 121 | 141 | 118.1667 | 0.4 | 18 | 55 | 60 | 49.6667 | 80 | 66.6667 | 0 | 48
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-05-23 | 2018-01-20 | 0.1 | 0.48559 | 0.048559 | Reduce | 0.1 | 0.48559 | 0.048559 | H2 | 4 | Stable | 0.6 | 90 | 125 | 145 | 122.5 | 0.2 | 19 | 43 | 77 | 44.6667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 87.6137 | 4.3807 | Accept | 0.15 | 87.6137 | 4.3807 | H2 | 4 | Stable | 0.8 | 86 | 128 | 155 | 125.5 | 0.8 | 86 | 128 | 155 | 125.5 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 5.8286 | 0.29143 | Accept | 0.2 | 5.8286 | 0.29143 | H2 | 4 | Stable | 0.6 | 91 | 128 | 158 | 126.8333 | 0.6 | 91 | 128 | 158 | 126.8333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 | 2017-08-20 | 0.2 | 53.0293 | 10.6059 | Reduce | 0.2 | 53.0293 | 10.6059 | H3 | 3 | Worsening | 0.8 | 110 | 133 | 152 | 132.3333 | 0.4 | 32 | 53 | 66 | 51.6667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Commercial aspects agreement | Person_439 | 2013-08-21 | 2017-05-22 | 0.02 | 4.8296 | 0.096593 | Transfer | 0.02 | 4.8296 | 0.096593 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 | 2017-08-20 | 0.1 | 34.363 | 3.4363 | Avoid | 0.1 | 34.363 | 3.4363 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 | 2017-08-20 | 0.26 | 16.2047 | 4.2132 | Avoid | 0.26 | 16.2047 | 4.2132 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport Routes | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 0.20788 | 0.068599 | Accept | 0.15 | 0.052336 | 0.0057569 | H2 | 4 | Stable | 0.9 | 93 | 126 | 153 | 125 | 0.9 | 93 | 126 | 153 | 125 | 74.8236 | 0 | 0 | 44.8942
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 | 2017-08-20 | 0.25 | 7.7469 | 1.9367 | Reduce | 0.25 | 7.7469 | 1.9367 | H3 | 3 | Stable | 0.5 | 93 | 134 | 151 | 130 | 0.1 | 10 | 56 | 65 | 49.8333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Internal Quality Issues | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 11.3437 | 0.56718 | Accept | 0.2 | 11.3437 | 0.56718 | H2 | 4 | Stable | 0.7 | 102 | 121 | 144 | 121.6667 | 0.7 | 102 | 121 | 144 | 121.6667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk017 | Project_042_Risk017 | Threat | Financial Contingency | Open | H2 | 4 | 6. Contractual/Legal | Liquidated Damages | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 21.1629 | 21.1629 | Accept | 0.4 | 21.1629 | 21.1629 | H2 | 4 | Stable | 0.7 | 100 | 130 | 152 | 128.6667 | 0.7 | 100 | 130 | 152 | 128.6667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Repairs | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 3.9728 | 1.3905 | Accept | 0.25 | 3.9728 | 1.3905 | H2 | 4 | Stable | 0.6 | 119 | 140 | 143 | 137 | 0.6 | 119 | 140 | 143 | 137 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk016 | Project_042_Risk016 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport/Delivery Speed | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 4.0228 | 2.0114 | Accept | 0.1 | 4.0228 | 2.0114 | H2 | 4 | Stable | 0.9 | 81 | 128 | 154 | 124.5 | 0.9 | 81 | 128 | 154 | 124.5 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Country Stability | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 0.81199 | 0.081199 | Accept | 0.4 | 0.81199 | 0.0406 | H2 | 4 | Stable | 0.8 | 105 | 130 | 155 | 130 | 0.8 | 105 | 130 | 155 | 130 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 0 | 0 | Accept | 0.1 | 0 | 0 | H2 | 4 | Stable | 0.6 | 81 | 125 | 155 | 122.6667 | 0.6 | 81 | 125 | 155 | 122.6667 |  | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2017-08-19 01:00 | 0.2 | 0.90951 | 0.1819 | Reduce | 0.1 | 0.90951 | 0.090951 | H3 | 3 | Stable | 0.8 | 115 | 126 | 152 | 128.5 | 0.3 | 20 | 55 | 62 | 50.3333 | 0 | 50 | 1 | 1.5
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2017-06-22 | 0.3 | 5.4553 | 1.6366 | Reduce | 0.15 | 5.252 | 0.7878 | H2 | 4 | Stable | 0.7 | 100 | 123 | 148 | 123.3333 | 0.4 | 19 | 52 | 65 | 48.6667 | 3.7267 | 50 | 0 | 2.236
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 1.3215 | 0.39644 | Accept | 0.2 | 1.3215 | 0.13215 | H2 | 4 | Stable | 0.6 | 108 | 139 | 160 | 137.3333 | 0.6 | 108 | 139 | 160 | 137.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2017-05-22 | 0.41 | 12.1982 | 2.4396 | Accept | 0.41 | 10.8428 | 1.0843 | H2 | 4 | Stable | 0.6 | 115 | 124 | 151 | 127 | 0.6 | 115 | 124 | 151 | 127 | 11.1111 | 0 | 0 | 6.6667
2017-03-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-016 | Project_023_Risk-016 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Damage to equipment (Unable to replace due to obsolescence) | Person_703 | 2015-10-22 01:00 | 2017-05-22 | 0.3 | 4.4727 | 0.22363 | Accept | 0.3 | 4.4727 | 0.22363 | H2 | 4 | Stable | 0.6 | 99 | 129 | 159 | 129 | 0.6 | 99 | 129 | 159 | 129 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Cable and connectors | Person_499 | 2015-11-21 01:00 | 2017-08-09 | 0.45 | 0.41338 | 0.18602 | Reduce | 0.2 | 0.41338 | 0.082677 | H2 | 4 | Stable | 0.8 | 117 | 132 | 145 | 131.6667 | 0.3 | 25 | 59 | 68 | 54.8333 | 0 | 55.5556 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | FOC Acceptance | Person_500 | 2015-11-21 01:00 | 2017-08-19 01:00 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.3 | 8.471 | 2.5413 | H2 | 4 | Stable | 0.9 | 88 | 128 | 154 | 125.6667 | 0.4 | 17 | 52 | 68 | 48.8333 | -99.9999 | 14.2857 | 0 | -59.9999
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-149 | Project_020_Risk-149 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs to be returned to UK | Person_703 | 2016-12-21 01:00 | 2017-11-19 01:00 | 0.2 | 8.8098 | 3.0834 | Accept | 0.2 | 8.8098 | 1.762 | H2 | 4 | Stable | 0.9 | 107 | 130 | 148 | 129.1667 | 0.9 | 107 | 130 | 148 | 129.1667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Furnished Equipmnet Condition | Person_371 | 2015-04-27 | 2017-08-19 01:00 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.5 | 99 | 131 | 160 | 130.5 | 0.4 | 37 | 44 | 72 | 47.5 |  | 62.5 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-020 | Project_028_Risk-020 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | (Project Management WP) Availability of Customer Furnished Equipmnet for modification | Person_253 | 2015-05-24 | 2019-02-20 01:00 | 0.25 | 0 | 0 | Avoid | 0.05 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 80 | 1
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.8 | 102 | 138 | 151 | 134.1667 | 0.3 | 34 | 54 | 69 | 53.1667 | 25.8065 | 20 | 0 | 15.4839
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 19:00 | 2019-08-20 19:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.7 | 119 | 130 | 143 | 130.3333 | 0.4 | 21 | 49 | 69 | 47.6667 | 83.3333 | 88.8889 | 1 | 52.6667
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.7 | 103 | 136 | 153 | 133.3333 | 0.4 | 12 | 52 | 64 | 47.3333 | 72 | 0 | 0 | 43.2
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.6 | 111 | 132 | 157 | 132.6667 | 0.3 | 38 | 51 | 77 | 53.1667 | 47.7391 | 0 | 0 | 28.6435
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 19:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.6 | 97 | 121 | 141 | 120.3333 | 0.2 | 19 | 55 | 72 | 51.8333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Non-Recurring Engineering higher than expected | Person_674 | 2016-06-01 | 2016-08-04 | 0.4 | 6.5968 | 2.6387 | Reduce | 0.2 | 6.5944 | 1.3189 | H3 | 3 | Improving | 0.7 | 103 | 125 | 151 | 125.6667 | 0.1 | 4 | 53 | 76 | 48.6667 | 0.036395 | 50 | 0 | 0.021837
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.9 | 89 | 138 | 146 | 131.1667 | 0.3 | 35 | 40 | 79 | 45.6667 | 0 | 0 | 1 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-026 | Project_043_Risk-026 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Equipment Delivery | Person_693 | 2017-04-19 | 2017-07-20 | 0.25 | 1.1976 | 0.29941 | -- | 0.25 | 1.1976 | 0.29941 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 | 2016-05-21 | 0.5 | 4.3921 | 2.196 | Reduce | 0.3 | 0 | 0 | H1 | 5 | Stable | 0.8 | 89 | 133 | 145 | 127.6667 | 0.2 | 4 | 44 | 69 | 41.5 | 100 | 40 | 0 | 60
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2017-06-22 | 0.2 | 0.90951 | 0.1819 | Reduce | 0.1 | 0.90951 | 0.090951 | H3 | 3 | Stable | 0.5 | 101 | 138 | 154 | 134.5 | 0.3 | 16 | 49 | 67 | 46.5 | 0 | 50 | 1 | 1.5
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2017-06-22 | 0.3 | 5.4553 | 1.6366 | Reduce | 0.15 | 5.252 | 0.7878 | H2 | 4 | Stable | 0.8 | 120 | 136 | 150 | 135.6667 | 0.3 | 38 | 42 | 68 | 45.6667 | 3.7267 | 50 | 0 | 2.236
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Cable and connectors | Person_499 | 2015-11-21 01:00 | 2017-08-09 | 0.45 | 0.41338 | 0.18602 | Reduce | 0.2 | 0.41338 | 0.082677 | H2 | 4 | Stable | 0.5 | 81 | 137 | 155 | 130.6667 | 0.3 | 9 | 50 | 70 | 46.5 | 0 | 55.5556 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | FOC Acceptance | Person_500 | 2015-11-21 01:00 | 2017-08-19 01:00 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.3 | 8.471 | 2.5413 | H2 | 4 | Stable | 0.9 | 82 | 137 | 153 | 130.5 | 0.1 | 1 | 41 | 72 | 39.5 | -99.9999 | 14.2857 | 0 | -59.9999
2017-03-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2017-05-21 | 0.05 | 8.8098 | 3.0834 | Accept | 0.05 | 8.8098 | 1.762 | H3 | 3 | Improving | 0.6 | 99 | 137 | 141 | 131.3333 | 0.6 | 99 | 137 | 141 | 131.3333 | 0 | 0 | 1 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 01:00 | 2016-11-20 01:00 | 0.25 | 0.40661 | 0.16264 | Accept | 0.1 | 0.40661 | 0.081321 | H3 | 3 | Stable | 0.8 | 96 | 132 | 146 | 128.3333 | 0.8 | 96 | 132 | 146 | 128.3333 | 0 | 60 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Furnished Equipmnet Condition | Person_132 | 2015-04-27 | 2017-08-19 01:00 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.6 | 94 | 139 | 155 | 134.1667 | 0.4 | 1 | 53 | 73 | 47.6667 |  | 62.5 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-20 01:00 | 0.25 | 65.2604 | 58.7343 | Accept | 0.15 | 65.2604 | 13.0521 | H3 | 3 | Stable | 0.5 | 91 | 135 | 149 | 130 | 0.5 | 91 | 135 | 149 | 130 | 0 | 40 | 1 | 1.2
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 0.5 | 0 | 0 | Accept | 0.5 | 0 | 0 | H2 | 4 | Improving | 0.5 | 120 | 137 | 141 | 134.8333 | 0.5 | 120 | 137 | 141 | 134.8333 |  | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-020 | Project_028_Risk-020 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | (Project Management WP) Availability of Customer Furnished Equipmnet for modification | Person_253 | 2015-05-24 | 2019-02-20 01:00 | 0.25 | 0 | 0 | Avoid | 0.05 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 80 | 1
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 0.3 | 54.7292 | 43.7834 | Accept | 0.3 | 54.7292 | 43.7834 | H2 | 4 | Stable | 0.8 | 105 | 128 | 160 | 129.5 | 0.8 | 105 | 128 | 160 | 129.5 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Obsolescence Monitoring Risk | Person_181 | 2016-12-02 21:00 | 2017-01-19 21:00 | 0.3 | 5.9458 | 1.7837 | Reduce | 0.15 | 0.9786 | 0.14679 | H3 | 3 | Stable | 0.9 | 82 | 140 | 142 | 130.6667 | 0.3 | 34 | 44 | 76 | 47.6667 | 83.5413 | 50 | 0 | 50.1248
2017-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R013 | Project_016_Risk--R013 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Resource Availability (Threat) | Person_697 | 2016-04-02 | 2019-08-01 | 0.2 | 3.0903 | 0.61807 | Accept | 0.2 | 3.0903 | 0.61807 | H2 | 4 | Worsening | 0.7 | 109 | 122 | 155 | 125.3333 | 0.7 | 109 | 122 | 155 | 125.3333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 30.9033 | 7.7258 | Accept | 0.35 | 30.9033 | 7.7258 | H3 | 3 | Stable | 0.6 | 98 | 132 | 146 | 128.6667 | 0.6 | 98 | 132 | 146 | 128.6667 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.25 | 35.0206 | 7.0041 | Accept | 0.25 | 35.0206 | 7.0041 | H3 | 3 | Stable | 0.9 | 110 | 123 | 153 | 125.8333 | 0.9 | 110 | 123 | 153 | 125.8333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-20 22:00 | 2019-08-20 | 0.5 | 15.0654 | 6.7794 | Accept | 0.5 | 15.0654 | 6.7794 | H2 | 4 | Stable | 0.8 | 92 | 123 | 157 | 123.5 | 0.8 | 92 | 123 | 157 | 123.5 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unforseen and substantial increase in Repairs workload during new build production period. | Person_515 | 2017-10-23 01:00 | 2017-11-19 01:00 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.03 | 1.5434 | 0.046303 | H3 | 3 | Worsening | 0.9 | 86 | 124 | 141 | 120.5 | 0.3 | 8 | 48 | 67 | 44.5 | 0 | 90 | 1 | 2.7
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_693 | 2017-05-23 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Worsening | 0.8 | 113 | 140 | 147 | 136.6667 | 0.3 | 11 | 47 | 69 | 44.6667 | 0 | 50 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2017-04-22 | 2018-05-22 | 0.75 | 10.7184 | 8.0388 | Reduce | 0.15 | 5.3592 | 0.80388 | H3 | 3 | Stable | 0.9 | 99 | 129 | 148 | 127.1667 | 0.3 | 27 | 40 | 66 | 42.1667 | 50 | 80 | 1 | 32.4
2017-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.2 | 1.9722 | 0.98609 | Accept | 0.2 | 1.9722 | 0.98609 | H3 | 3 | Stable | 0.5 | 120 | 135 | 143 | 133.8333 | 0.5 | 120 | 135 | 143 | 133.8333 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 | 2017-08-20 | 0.05 | 2.5081 | 1.2541 | Accept | 0.05 | 2.5081 | 1.2541 | H3 | 3 | Stable | 0.6 | 114 | 129 | 147 | 129.5 | 0.6 | 114 | 129 | 147 | 129.5 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2017-05-23 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.05 | 0.68598 | 0.034299 | H3 | 3 | Stable | 0.9 | 85 | 139 | 146 | 131.1667 | 0.1 | 15 | 48 | 66 | 45.5 | 0 | 80 | 1 | 2.4
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 | 2017-07-20 | 0.05 | 0.45017 | 0.2701 | Accept | 0.05 | 0.45017 | 0.13505 | H2 | 4 | Stable | 0.6 | 98 | 132 | 154 | 130 | 0.6 | 98 | 132 | 154 | 130 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2017-05-23 | 2017-07-21 | 0.1 | 21.8655 | 2.1865 | Reduce | 0.01 | 21.8655 | 0.21865 | H2 | 4 | Stable | 0.9 | 97 | 130 | 154 | 128.5 | 0.3 | 38 | 51 | 79 | 53.5 | 0 | 90 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2017-05-23 | 2018-05-22 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Stable | 0.8 | 92 | 137 | 154 | 132.3333 | 0.2 | 7 | 51 | 74 | 47.5 | 0 | 60 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Unidentified CRs and concessions | Person_693 | 2017-04-22 | 2017-09-20 01:00 | 0.5 | 1.2005 | 0.60023 | Reduce | 0.15 | 0.51019 | 0.076529 | H3 | 3 | Stable | 0.6 | 118 | 136 | 156 | 136.3333 | 0.2 | 12 | 48 | 60 | 44 | 57.5001 | 70 | 1 | 36.6001
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_238 | 2017-04-22 | 2018-05-22 | 0.25 | 3.3227 | 0.83067 | Reduce | 0.05 | 3.3227 | 0.16613 | H3 | 3 | Stable | 0.8 | 98 | 125 | 160 | 126.3333 | 0.3 | 1 | 59 | 69 | 51 | 0 | 80 | 1 | 2.4
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_693 | 2017-05-23 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.1 | 0.77172 | 0.077172 | H3 | 3 | Worsening | 0.7 | 87 | 130 | 153 | 126.6667 | 0.3 | 4 | 54 | 66 | 47.6667 | 0 | 60 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 | 0.05 | 1.7492 | 0.17492 | Accept | 0.05 | 1.7492 | 0.17492 | H3 | 3 | Stable | 0.7 | 119 | 122 | 144 | 125.1667 | 0.7 | 119 | 122 | 144 | 125.1667 | 0 | 0 | 1 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_693 | 2017-05-23 | 2018-11-20 01:00 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.08 | 6.431 | 0.51448 | H3 | 3 | Improving | 0.7 | 109 | 136 | 151 | 134 | 0.2 | 24 | 50 | 63 | 47.8333 | -47.0588 | 46.6667 | 1 | -26.8353
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Reduce touch labour if Production readiness programme successful | Person_238 | 2017-05-23 | 2017-10-21 01:00 | 0.3 | 1.5606 | 0.46818 | Exploit | 0.5 | 1.5606 | 0.7803 | H2 | 4 | Stable | [10 empty] | 0 | -66.6667 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 0.5 | 9.2728 | 4.6364 | Reduce | 0.15 | 9.2728 | 1.3909 | H2 | 4 | Stable | 0.6 | 90 | 135 | 149 | 129.8333 | 0.4 | 35 | 46 | 68 | 47.8333 | 0 | 70 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R008 | Project_016_Risk--R008 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Additional Travel & Subsistence | Person_574 | 2016-01-13 01:00 | 2019-05-23 | 0.4 | 8.9019 | 3.5608 | Reduce | 0.25 | 8.9019 | 2.2255 | H3 | 3 | Stable | 0.7 | 84 | 135 | 141 | 127.5 | 0.4 | 21 | 42 | 69 | 43 | 0 | 37.5 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 0.3 | 8.7814 | 2.6344 | Reduce | 0.15 | 8.7832 | 1.3175 | H3 | 3 | Stable | 0.6 | 101 | 135 | 146 | 131.1667 | 0.4 | 1 | 44 | 66 | 40.5 | -0.021119 | 50 | 1 | 1.4873
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R009 | Project_016_Risk--R009 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer maybe difficult to work with | Person_697 | 2016-04-02 | 2019-08-01 | 0.6 | 23.9549 | 14.3729 | Reduce | 0.43864 | 23.8312 | 10.4533 | H2 | 4 | Stable | 0.8 | 104 | 124 | 146 | 124.3333 | 0.4 | 26 | 49 | 60 | 47 | 0.51612 | 26.8938 | 0 | 0.30967
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 0.5 | 108.3186 | 32.4956 | Accept | 0.5 | 108.3186 | 32.4956 | H2 | 4 | Stable | 0.8 | 89 | 122 | 144 | 120.1667 | 0.8 | 89 | 122 | 144 | 120.1667 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Delay of processing | Person_306 | 2016-04-02 | 2017-03-21 01:00 | 0.15 | 26.3497 | 3.9525 | Reduce | 0.15 | 13.1767 | 1.9765 | H3 | 3 | Stable | 0.7 | 83 | 131 | 159 | 127.6667 | 0.1 | 10 | 53 | 67 | 48.1667 | 49.993 | 0 | 1 | 29.9958
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 01:00 | 0.1 | 12.0547 | 2.4109 | Accept | 0.05 | 12.0547 | 2.4109 | H3 | 3 | Stable | 0.8 | 98 | 127 | 151 | 126.1667 | 0.8 | 98 | 127 | 151 | 126.1667 | 0 | 50 | 1 | 1.5
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-20 22:00 | 2016-08-20 22:00 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.5 | 108 | 129 | 155 | 129.8333 | 0.4 | 16 | 46 | 78 | 46.3333 | 0 | 16.6667 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence and missing info | Person_727 | 2015-11-25 01:00 | 2017-06-21 | 0.3 | 5.4336 | 1.3584 | Accept | 0.1 | 5.4336 | 1.3584 | H3 | 3 | Stable | 0.7 | 98 | 134 | 143 | 129.5 | 0.7 | 98 | 134 | 143 | 129.5 | 0 | 66.6667 | 1 | 2
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 01:00 | 2017-03-22 | 0.2 | 5.126 | 2.563 | Accept | 0.1 | 5.126 | 2.563 | H2 | 4 | Stable | 0.9 | 101 | 130 | 146 | 127.8333 | 0.9 | 101 | 130 | 146 | 127.8333 | 0 | 50 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-002 | Project_028_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Record / Replay feature | Person_499 | 2014-03-23 | 2017-04-21 | 0.05 | 12.815 | 2.563 | Accept | 0.05 | 12.815 | 2.563 | H2 | 4 | Stable | 0.7 | 83 | 129 | 154 | 125.5 | 0.7 | 83 | 129 | 154 | 125.5 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.5 | 100 | 128 | 157 | 128.1667 | 0.3 | 20 | 51 | 67 | 48.5 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | EMC Testing | Person_070 | 2016-04-22 | 2017-04-21 | 0.35 | 87.6137 | 4.3807 | Accept | 0.2 | 87.6137 | 4.3807 | H2 | 4 | Stable | 0.8 | 118 | 127 | 154 | 130 | 0.8 | 118 | 127 | 154 | 130 | 0 | 42.8571 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_542 | 2015-01-22 01:00 | 2017-08-20 01:00 | 0.35 | 5.8286 | 0.29143 | Accept | 0.2 | 5.8286 | 0.29143 | H2 | 4 | Stable | 0.7 | 82 | 140 | 153 | 132.5 | 0.7 | 82 | 140 | 153 | 132.5 | 0 | 42.8571 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 | 2017-08-20 | 0.2 | 53.0293 | 10.6059 | Reduce | 0.2 | 53.0293 | 10.6059 | H3 | 3 | Worsening | 0.6 | 93 | 126 | 142 | 123.1667 | 0.4 | 18 | 58 | 69 | 53.1667 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Commercial aspects agreement | Person_439 | 2013-08-21 | 2017-05-22 | 0.02 | 4.8296 | 0.096593 | Transfer | 0.02 | 4.8296 | 0.096593 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 | 2017-08-20 | 0.1 | 34.363 | 3.4363 | Avoid | 0.1 | 34.363 | 3.4363 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 | 2017-08-20 | 0.26 | 16.2047 | 4.2132 | Avoid | 0.26 | 16.2047 | 4.2132 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_070 | 2016-06-23 | 2017-08-20 01:00 | 0.4 | 0.20788 | 0.068599 | Accept | 0.2 | 0.052336 | 0.0057569 | H2 | 4 | Stable | 0.9 | 116 | 140 | 142 | 136.3333 | 0.9 | 116 | 140 | 142 | 136.3333 | 74.8236 | 50 | 0 | 44.8942
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 | 2017-08-20 | 0.25 | 7.7469 | 1.9367 | Reduce | 0.25 | 7.7469 | 1.9367 | H3 | 3 | Stable | 0.6 | 88 | 140 | 145 | 132.1667 | 0.4 | 33 | 51 | 63 | 50 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 21.1629 | 21.1629 | Accept | 0.5 | 21.1629 | 21.1629 | H2 | 4 | Stable | 0.8 | 110 | 123 | 154 | 126 | 0.8 | 110 | 123 | 154 | 126 | 0 | 0 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 0.5 | 3.9728 | 1.3905 | Accept | 0.5 | 3.9728 | 1.3905 | H2 | 4 | Stable | 0.8 | 86 | 131 | 157 | 127.8333 | 0.8 | 86 | 131 | 157 | 127.8333 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK225 | Project_024_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | More testing required as a result compliance to Platform Risk | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 5.6866 | 2.8433 | Reduce | 0.3 | 5.6866 | 1.706 | H2 | 4 | Stable | 0.5 | 117 | 133 | 157 | 134.3333 | 0.1 | 20 | 47 | 65 | 45.5 | 0 | 40 | 0 | 0
2017-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 0.61 | 17.0765 | 1.7076 | Accept | 0.61 | 17.0765 | 1.7076 | H1 | 5 | Stable | 0.9 | 87 | 138 | 141 | 130 | 0.9 | 87 | 138 | 141 | 130 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.8 | 103 | 131 | 153 | 130 | 0.1 | 31 | 43 | 78 | 46.8333 | 0 | 60 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK286 | Project_024_RISK286 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Requirement sell off more difficult than expected | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 10.1787 | 5.0893 | Reduce | 0.5 | 10.1787 | 5.0893 | H1 | 5 | Worsening | 0.6 | 82 | 129 | 150 | 124.6667 | 0.2 | 8 | 51 | 78 | 48.3333 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK288 | Project_024_RISK288 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Unplanned obsolescence and/or repairs to rig assets. | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.6 | 5.8424 | 3.5054 | Reduce | 0.6 | 4.9768 | 2.9861 | H1 | 5 | Stable | 0.7 | 102 | 135 | 155 | 132.8333 | 0.1 | 14 | 56 | 70 | 51.3333 | 14.8148 | 0 | 0 | 8.8889
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_288 | 2017-02-22 01:00 | 2017-11-19 01:00 | 0.3 | 19.9938 | 5.9981 | Reduce | 0.1 | 19.9938 | 1.9994 | H3 | 3 | Improving | 0.7 | 106 | 124 | 155 | 126.1667 | 0.2 | 1 | 48 | 61 | 42.3333 | 0 | 66.6667 | 1 | 2
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.5 | 3.843 | 1.9215 | H1 | 5 | Stable | 0.9 | 111 | 122 | 142 | 123.5 | 0.3 | 17 | 52 | 76 | 50.1667 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Overland performance | Person_075 | 2016-06-23 | 2017-11-19 01:00 | 0.1 | 1.6835 | 0.16835 | Reduce | 0.1 | 3.5011 | 0.35011 | H3 | 3 | Improving | 0.7 | 98 | 138 | 146 | 132.6667 | 0.2 | 29 | 41 | 67 | 43.3333 | -107.9692 | 0 | 1 | -64.7815
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK213 | Project_024_RISK213 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Rigs requireaccreditation as "Special to Type" Test equipment | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.3 | 38.17 | 11.451 | Avoid | 0.25 | 19.4745 | 4.8686 | H2 | 4 | Stable | [10 empty] | 48.9796 | 16.6667 | 0 | 29.3878
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK256 | Project_024_RISK256 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unable to meet spare capacity requirement | Person_119 | 2016-07-21 | 2018-01-21 01:00 | 0.8 | 0.12983 | 0.10386 | Reduce | 0.05 | 0.12983 | 0.0064915 | H3 | 3 | Stable | 0.5 | 82 | 127 | 158 | 124.6667 | 0.3 | 34 | 54 | 78 | 54.6667 | 0 | 93.75 | 1 | 2.8125
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK218 | Project_024_RISK218 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | System issues general | Person_388 | 2015-09-04 01:00 | 2019-05-23 | 0.4 | 90.8811 | 36.3524 | Reduce | 0.3 | 0 | 0 | H1 | 5 | Stable | 0.7 | 82 | 121 | 142 | 118 | 0.3 | 3 | 46 | 67 | 42.3333 | 100 | 25 | 0 | 60
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK222 | Project_024_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Testing Extends beyond target completion | Person_351 | 2017-07-21 | 2018-08-21 | 0.2 | 9.8671 | 1.9734 | Reduce | 0.2 | 9.8671 | 1.9734 | H2 | 4 | Stable | 0.8 | 109 | 137 | 156 | 135.5 | 0.3 | 2 | 44 | 62 | 40 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 01:00 | 0.1 | 15.5796 | 6.2318 | Accept | 0.05 | 15.5796 | 6.2318 | H3 | 3 | Stable | 0.7 | 81 | 123 | 146 | 119.8333 | 0.7 | 81 | 123 | 146 | 119.8333 | 0 | 50 | 1 | 1.5
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Performance (collector opportunity) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.3814 | 26.127 | 9.9648 | -- | 0.4132 | 26.127 | 10.7957 | H1 | 5 | Stable | [10 empty] | 0 | -8.3377 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.3 | 20.8767 | 6.263 | H2 | 4 | Stable | 0.5 | 118 | 137 | 155 | 136.8333 | 0.2 | 5 | 58 | 77 | 52.3333 | 50 | 25 | 0 | 30
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.47368 | 82.8835 | 39.2603 | Reduce | 0.27765 | 63.9673 | 17.7605 | H1 | 5 | Worsening | 0.8 | 87 | 124 | 150 | 122.1667 | 0.3 | 8 | 53 | 74 | 49 | 22.8227 | 41.3845 | 0 | 13.6936
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence and missing info | Person_727 | 2015-11-25 01:00 | 2017-06-21 | 0.3 | 25.966 | 7.7898 | Accept | 0.1 | 10.3864 | 3.1159 | H3 | 3 | Stable | 0.8 | 83 | 135 | 150 | 128.8333 | 0.8 | 83 | 135 | 150 | 128.8333 | 60 | 66.6667 | 1 | 38
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 01:00 | 2017-08-20 01:00 | 0.2 | 62.3617 | 3.1181 | Accept | 0.1 | 62.3617 | 3.1181 | H2 | 4 | Stable | 0.9 | 120 | 129 | 142 | 129.6667 | 0.9 | 120 | 129 | 142 | 129.6667 | 0 | 50 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | EMC Testing | Person_332 | 2016-04-22 | 2017-06-22 | 0.35 | 4.5441 | 0.45441 | Accept | 0.2 | 4.5441 | 0.45441 | H2 | 4 | Stable | 0.7 | 88 | 123 | 149 | 121.5 | 0.7 | 88 | 123 | 149 | 121.5 | 0 | 42.8571 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_542 | 2015-01-22 01:00 | 2017-08-20 01:00 | 0.35 | 30.2764 | 12.1106 | Accept | 0.2 | 30.2764 | 12.1106 | H2 | 4 | Stable | 0.9 | 84 | 132 | 159 | 128.5 | 0.9 | 84 | 132 | 159 | 128.5 | 0 | 42.8571 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Additional minor point releases | Person_228 | 2016-05-23 | 2017-10-19 01:00 | 0.5 | 11.9444 | 5.9722 | Reduce | 0.25 | 11.9444 | 2.9861 | H2 | 4 | Stable | 0.6 | 109 | 129 | 156 | 130.1667 | 0.2 | 33 | 56 | 65 | 53.6667 | 0 | 50 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_332 | 2016-06-23 | 2017-08-20 01:00 | 0.4 | 35.885 | 25.4784 | Accept | 0.2 | 2.5966 | 0.51932 | H2 | 4 | Stable | 0.7 | 102 | 131 | 156 | 130.3333 | 0.7 | 102 | 131 | 156 | 130.3333 | 92.7641 | 50 | 0 | 55.6585
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_228 | 2016-05-23 | 2017-02-19 01:00 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.9 | 120 | 130 | 157 | 132.8333 | 0.4 | 35 | 45 | 75 | 48.3333 | 0 | 50 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_413 | 2015-11-21 01:00 | 2018-11-20 01:00 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.9 | 90 | 136 | 152 | 131 | 0.2 | 10 | 55 | 79 | 51.5 | 0 | 5 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.8 | 2.8043 | 2.2435 | Reduce | 0.45 | 2.8043 | 1.2619 | H1 | 5 | Stable | 0.7 | 114 | 131 | 147 | 130.8333 | 0.2 | 23 | 49 | 75 | 49 | 0 | 43.75 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK306(028) | Project_024_RISK306(028) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | HW repairs required on units | Person_119 | 2016-11-19 01:00 | 2018-11-20 01:00 | 0.3 | 2.813 | 0.8439 | Reduce | 0.2 | 2.813 | 0.5626 | H2 | 4 | Stable | 0.6 | 85 | 122 | 150 | 120.5 | 0.1 | 17 | 58 | 64 | 52.1667 | 0 | 33.3333 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | RISK004 | Project_028_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Engineering Changes to be embodied on the Rig | Person_253 | 2017-04-29 | 2019-02-20 01:00 | 0.8 | 5.1932 | 2.0773 | Accept | 0.8 | 5.1716 | 2.0686 | H1 | 5 | Stable | 0.6 | 103 | 133 | 153 | 131.3333 | 0.6 | 103 | 133 | 153 | 131.3333 | 0.41665 | 0 | 0 | 0.24999
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK302(024) | Project_024_RISK302(024) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | On time provision of platform units | Person_119 | 2016-11-19 01:00 | 2019-05-23 | 0.25 | 2.3889 | 0.59722 | Reduce | 0.15 | 2.3889 | 0.35833 | H2 | 4 | Stable | 0.6 | 109 | 138 | 142 | 133.8333 | 0.2 | 6 | 52 | 64 | 46.3333 | 0 | 40 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Risk of not being able to perform Tests | Person_238 | 2017-12-21 01:00 | 2019-01-21 01:00 | 0.5 | 5.1067 | 1.0213 | Accept | 0.5 | 5.1067 | 1.0213 | H2 | 4 | Stable | 0.9 | 105 | 137 | 147 | 133.3333 | 0.9 | 105 | 137 | 147 | 133.3333 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_238 | 2017-05-23 | 2019-01-21 01:00 | 0.5 | 4.1546 | 0.41546 | Accept | 0.5 | 4.1546 | 0.41546 | H2 | 4 | Stable | 0.8 | 84 | 125 | 157 | 123.5 | 0.8 | 84 | 125 | 157 | 123.5 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_693 | 2017-04-22 | 2017-09-19 01:00 | 0.6 | 0.5626 | 0.19691 | Accept | 0.3 | 0.5626 | 0.19691 | H3 | 3 | Stable | 0.6 | 102 | 126 | 150 | 126 | 0.6 | 102 | 126 | 150 | 126 | 0 | 50 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-116 | Project_011_Risk-116 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Delays to Qualification | Person_147 | 2017-04-22 | 2017-08-19 01:00 | 0.5 | 0.43243 | 0.21621 | Reduce | 0.5 | 0.43243 | 0.21621 | H1 | 5 | Stable | 0.9 | 97 | 136 | 145 | 131 | 0.1 | 35 | 57 | 76 | 56.5 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-104 | Project_011_Risk-104 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer delayed in providing Custeomr Furnished Equipment | Person_147 | 2016-06-23 | 2017-04-21 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.6 | 107 | 138 | 149 | 134.6667 | 0.2 | 27 | 41 | 63 | 42.3333 |  | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_547 | 2017-05-23 | 2018-05-22 | 0.1 | 0.30685 | 0.06137 | Accept | 0.1 | 0.30685 | 0.06137 | H3 | 3 | Stable | 0.6 | 85 | 122 | 158 | 121.8333 | 0.6 | 85 | 122 | 158 | 121.8333 | 0 | 0 | 1 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 0.3 | 0.51931 | 0.15579 | -- | 0.15 | 0.51931 | 0.077897 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 0.2 | 0.55005 | 0.11001 | Avoid | 0.2 | 0.55005 | 0.11001 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-123 | Project_011_Risk-123 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | No Requirement for Delta acceptance | Person_187 | 2017-06-23 | 2017-08-20 01:00 | 0.2 | 0.63074 | 0.12615 | -- | 0.2 | 0.63074 | 0.12615 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2016-07-21 | 2017-02-19 01:00 | 0.15 | 0.28639 | 0.042959 | -- | 0.15 | 0.28639 | 0.042959 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-08-20 01:00 | 0.2 | 0.24207 | 0.048414 | -- | 0.2 | 0.24207 | 0.048414 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 0.2 | 1.661 | 0.33219 | Reduce | 0.2 | 1.661 | 0.33219 | H2 | 4 | Stable | 0.8 | 103 | 128 | 158 | 128.8333 | 0.1 | 23 | 59 | 63 | 53.6667 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2017-10-21 01:00 | 2018-08-21 | 0.4 | 1.2444 | 0.49778 | Reduce | 0.4 | 1.2444 | 0.49778 | H2 | 4 | Stable | 0.7 | 90 | 134 | 150 | 129.3333 | 0.3 | 3 | 42 | 66 | 39.5 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production, Procurement or Engineering | Person_725 | 2018-01-21 01:00 | 2019-05-23 | 0.1 | 0.16195 | 0.072876 | Accept | 0.1 | 0.16195 | 0.072876 | H3 | 3 | Stable | 0.8 | 82 | 122 | 155 | 120.8333 | 0.8 | 82 | 122 | 155 | 120.8333 | 0 | 0 | 1 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 01:00 | 2017-07-20 | 0.45 | 0.41947 | 0.18876 | Reduce | 0.45 | 0.41944 | 0.18875 | H2 | 4 | Stable | 0.5 | 93 | 128 | 143 | 124.6667 | 0.4 | 34 | 49 | 63 | 48.8333 | 0.0067461 | 0 | 0 | 0.0040477
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R81 | Project_041_R81 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Re-imaging of PC's - additional material/Labour effort | Person_515 | 2017-05-23 | 2017-10-21 01:00 | 0.5 | 0.098873 | 0.0098873 | Accept | 0.25 | 0.098873 | 0.0098873 | H2 | 4 | Stable | 0.9 | 118 | 130 | 156 | 132.3333 | 0.9 | 118 | 130 | 156 | 132.3333 | 0 | 50 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-02-20 01:00 | 2018-08-21 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.5 | 115 | 136 | 159 | 136.3333 | 0.1 | 17 | 46 | 63 | 44 |  | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Pick up and Drop off of Software Resource | Person_230 | 2017-04-21 | 2018-02-19 01:00 | 0.4 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-109 | Project_011_Risk-109 | Opportunitity | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Environment complexity | Person_187 | 2016-07-21 | 2018-08-21 | 0.25 | 0.14661 | 0.036651 | -- | 0.25 | 0.14661 | 0.036651 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-108 | Project_011_Risk-108 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Offer additional functionality to the customer | Person_147 | 2017-04-22 | 2018-08-21 | 0.1 | 0.34094 | 0.034094 | -- | 0.1 | 0.34094 | 0.034094 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 0.2 | 0.12388 | 0.024775 | Reduce | 0.2 | 0.12388 | 0.024775 | H2 | 4 | Stable | 0.7 | 111 | 122 | 146 | 124.1667 | 0.1 | 22 | 57 | 75 | 54.1667 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 0.4 | 0.51141 | 0.20457 | Avoid | 0.4 | 0.51141 | 0.20457 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 0.5 | 0.49834 | 0.12459 | Accept | 0.5 | 0.49834 | 0.12459 | H2 | 4 | Improving | 0.8 | 110 | 129 | 155 | 130.1667 | 0.8 | 110 | 129 | 155 | 130.1667 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.2 | 0.10171 | 0.020343 | -- | 0.2 | 0.10171 | 0.020343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 0.3 | 0.28639 | 0.085917 | Reduce | 0.3 | 0.28639 | 0.085917 | H2 | 4 | Stable | 0.8 | 87 | 133 | 141 | 126.6667 | 0.2 | 29 | 46 | 62 | 45.8333 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 2. Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 0.25 | 0 | 0 | -- | 0.25 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2017-10-21 01:00 | 2018-05-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 0.3 | 0.10626 | 0.031878 | -- | 0.3 | 0.01932 | 0.005796 | H3 | 3 | Stable | [10 empty] | 81.8181 | 0 | 0 | 49.0909
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 0.3 | 1.0052 | 0.35182 | Accept | 0.3 | 1.0052 | 0.35182 | H2 | 4 | Stable | 0.9 | 118 | 136 | 143 | 134.1667 | 0.9 | 118 | 136 | 143 | 134.1667 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-118 | Project_011_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer change environment | Person_187 | 2013-08-21 01:00 | 2018-08-21 | 0.1 | 0 | 0 | Avoid | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R013 | Project_016_Risk--R013 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Resource Availability (Threat) | Person_697 | 2016-04-02 | 2019-08-01 | 0.2 | 1.8788 | 0.28182 | Accept | 0.2 | 1.8788 | 0.28182 | H2 | 4 | Worsening | 0.7 | 86 | 135 | 155 | 130.1667 | 0.7 | 86 | 135 | 155 | 130.1667 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 9.3941 | 1.8788 | Accept | 0.35 | 9.3941 | 1.8788 | H3 | 3 | Stable | 0.8 | 99 | 136 | 142 | 130.8333 | 0.8 | 99 | 136 | 142 | 130.8333 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.25 | 1.8788 | 0.18788 | Accept | 0.25 | 1.8788 | 0.18788 | H3 | 3 | Stable | 0.7 | 83 | 133 | 141 | 126 | 0.7 | 83 | 133 | 141 | 126 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-20 22:00 | 2019-08-20 | 0.5 | 29.4599 | 8.838 | Accept | 0.5 | 18.7882 | 5.6365 | H2 | 4 | Stable | 0.9 | 97 | 124 | 147 | 123.3333 | 0.9 | 97 | 124 | 147 | 123.3333 | 36.2245 | 0 | 0 | 21.7347
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.2 | 1.1273 | 0.22546 | Accept | 0.2 | 1.1273 | 0.22546 | H3 | 3 | Stable | 0.8 | 88 | 136 | 148 | 130 | 0.8 | 88 | 136 | 148 | 130 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 | 2017-08-20 | 0.05 | 4.7948 | 0.95895 | Accept | 0.05 | 4.7948 | 0.95895 | H3 | 3 | Stable | 0.8 | 88 | 122 | 160 | 122.6667 | 0.8 | 88 | 122 | 160 | 122.6667 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 | 2017-07-20 | 0.05 | 0.65759 | 0.098638 | Accept | 0.05 | 0.65759 | 0.098638 | H2 | 4 | Stable | 0.6 | 99 | 130 | 152 | 128.5 | 0.6 | 99 | 130 | 152 | 128.5 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 | 0.05 | 0.93941 | 0.14091 | Accept | 0.05 | 0.93941 | 0.14091 | H3 | 3 | Stable | 0.7 | 113 | 126 | 141 | 126.3333 | 0.7 | 113 | 126 | 141 | 126.3333 | 0 | 0 | 1 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2017-02-20 01:00 | 2018-05-22 | 0.1 | 2.5834 | 0.64585 | Accept | 0.1 | 2.5834 | 0.64585 | H3 | 3 | Stable | 0.6 | 93 | 133 | 155 | 130 | 0.6 | 93 | 133 | 155 | 130 | 0 | 0 | 1 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK291 | Project_024_RISK291 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | LoE Engineering support required post completion in addition to BCR | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 1.1273 | 0.45092 | Accept | 0.5 | 1.1273 | 0.45092 | H1 | 5 | Worsening | 0.8 | 90 | 131 | 150 | 127.3333 | 0.8 | 90 | 131 | 150 | 127.3333 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Governance and Export Rules | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 0.93941 | 0.23485 | Transfer | 0.25 | 0.93941 | 0.23485 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.8 | 113 | 126 | 147 | 127.3333 | 0.3 | 33 | 59 | 73 | 57 | 0 | 40 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Equipment environmental failure | Person_710 | 2016-05-23 | 2017-09-19 01:00 | 0.3 | 11.0894 | 0.55447 | Accept | 0.3 | 11.0894 | 0.55447 | H2 | 4 | Improving | 0.9 | 105 | 131 | 157 | 131 | 0.9 | 105 | 131 | 157 | 131 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 | 0.7 | 0.92411 | 0.64688 | Reduce | 0.3 | 0.36965 | 0.11089 | H2 | 4 | Stable | 0.8 | 80 | 125 | 148 | 121.3333 | 0.3 | 15 | 44 | 78 | 44.8333 | 60 | 57.1429 | 0 | 36
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 | 2016-04-21 | 0.5 | 4.0661 | 2.033 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.9 | 101 | 128 | 151 | 127.3333 | 0.1 | 19 | 58 | 69 | 53.3333 | 0 | 90 | 1 | 2.7
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.5 | 0.46206 | 0.23103 | H1 | 5 | Improving | 0.9 | 89 | 138 | 157 | 133 | 0.4 | 36 | 56 | 68 | 54.6667 | 58.3333 | 16.6667 | 0 | 35
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Retained systems re-design or modification | Person_710 | 2016-08-20 01:00 | 2018-02-19 01:00 | 0.05 | 1.1089 | 0.88715 | Accept | 0.05 | 0.73929 | 0.44357 | H2 | 4 | Improving | 0.5 | 110 | 139 | 157 | 137.1667 | 0.5 | 110 | 139 | 157 | 137.1667 | 33.3333 | 0 | 0 | 20
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 | 2017-08-20 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.8 | 118 | 127 | 152 | 129.6667 | 0.2 | 20 | 47 | 65 | 45.5 | 0 | 50 | 1 | 1.5
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.5 | 115 | 137 | 152 | 135.8333 | 0.4 | 23 | 51 | 62 | 48.1667 | 0 | 25 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Stable | 0.7 | 108 | 122 | 146 | 123.6667 | 0.1 | 12 | 43 | 76 | 43.3333 | 0 | 40 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Worsening | [10 empty] | 0 | 37.5 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Mission System not compatible with platform systems | Person_710 | 2016-07-21 | 2017-08-20 01:00 | 0.1 | 3.6965 | 0.36965 | Accept | 0.1 | 3.6965 | 0.36965 | H3 | 3 | Stable | 0.7 | 117 | 134 | 158 | 135.1667 | 0.7 | 117 | 134 | 158 | 135.1667 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Qual failure | Person_710 | 2016-06-22 | 2017-06-22 | 0.4 | 0.92411 | 0.18482 | Accept | 0.4 | 0.92411 | 0.18482 | H1 | 5 | Improving | 0.9 | 85 | 139 | 145 | 131 | 0.9 | 85 | 139 | 145 | 131 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digital Video Chainredesign | Person_710 | 2016-06-22 | 2017-05-22 | 0.71 | 1.8482 | 0.55447 | Accept | 0.2 | 1.8482 | 0.73929 | H2 | 4 | Worsening | 0.6 | 91 | 134 | 144 | 128.5 | 0.6 | 91 | 134 | 144 | 128.5 | 0 | 71.831 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.7 | 105 | 124 | 155 | 126 | 0.2 | 15 | 52 | 78 | 50.1667 | 90 | 75 | 1 | 56.25
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.41 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -2.5 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.61 | 0.25667 | 0.15657 | Reduce | 0.5 | 0.25667 | 0.12834 | H2 | 4 | Stable | 0.5 | 99 | 137 | 143 | 131.6667 | 0.2 | 12 | 56 | 76 | 52 | 0 | 18.0328 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 1.078 | 0.43121 | Reduce | 0.4 | 1.4673 | 0.58692 | H2 | 4 | Improving | 0.9 | 83 | 134 | 146 | 127.5 | 0.2 | 15 | 55 | 78 | 52.1667 | -36.1112 | 0 | 0 | -21.6667
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2018-03-21 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2017-11-20 01:00 | 0.6 | 0.89835 | 0.53901 | Transfer | 0.6 | 0.89835 | 0.53901 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 0.35 | 0.85557 | 0.29945 | Reduce | 0.35 | 1.9208 | 0.67227 | H2 | 4 | Stable | 0.9 | 94 | 140 | 150 | 134 | 0.2 | 24 | 40 | 73 | 42.8333 | -124.5001 | 0 | 0 | -74.7001
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 0.77001 | 0.30801 | Reduce | 0.3 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.8 | 114 | 125 | 151 | 127.5 | 0.4 | 29 | 55 | 79 | 54.6667 | 0 | 25 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2018-02-20 01:00 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.8 | 102 | 140 | 156 | 136.3333 | 0.2 | 13 | 47 | 79 | 46.6667 | 0 | 28.5714 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_641 | 2016-05-23 | 2017-08-19 01:00 | 0.4 | 1.54 | 0.30801 | Accept | 0.4 | 0.77001 | 0.154 | H1 | 5 | Stable | 0.6 | 109 | 131 | 141 | 129 | 0.6 | 109 | 131 | 141 | 129 | 50 | 0 | 0 | 30
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK300(020) | Project_024_RISK300(020) | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Travel and onsite support | Person_119 | 2017-01-20 01:00 | 2017-07-20 | 0.25 | 0.94968 | 0.28491 | Accept | 0.25 | 0.94968 | 0.18994 | H3 | 3 | Stable | 0.5 | 81 | 129 | 150 | 124.5 | 0.5 | 81 | 129 | 150 | 124.5 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK304(026) | Project_024_RISK304(026) | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | complex integration | Person_119 | 2016-10-20 01:00 | 2017-07-20 | 0.4 | 27.1644 | 0.81493 | Accept | 0.4 | 12.8336 | 1.2834 | H1 | 5 | Worsening | 0.9 | 89 | 128 | 148 | 124.8333 | 0.9 | 89 | 128 | 148 | 124.8333 | 52.7559 | 0 | 0 | 31.6535
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2018-03-22 | 2019-07-21 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.6 | 114 | 135 | 149 | 133.8333 | 0.2 | 9 | 44 | 65 | 41.6667 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2018-03-16 01:00 | 0.41 | 6.4168 | 2.6309 | Transfer | 0.41 | 0 | 0 | H1 | 5 | Stable | [10 empty] | 100 | 0 | 0 | 60
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub-system FPGA | Person_216 | 2017-01-21 01:00 | 2018-02-20 01:00 | 0.3 | 1.54 | 0.46201 | Reduce | 0.4 | 1.5914 | 0.63655 | H2 | 4 | Stable | 0.6 | 107 | 123 | 144 | 123.8333 | 0.4 | 34 | 44 | 71 | 46.8333 | -3.3333 | -33.3333 | 0 | -2
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort for System HW/SW- System upgrade | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.3 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.6 | 98 | 129 | 147 | 126.8333 | 0.2 | 10 | 48 | 70 | 45.3333 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs [technical scope] | Person_372 | 2017-06-23 | 2018-08-22 01:00 | 0.35 | 9.505 | 3.3267 | Reduce | 0.35 | 9.505 | 3.3267 | H2 | 4 | Stable | 0.6 | 97 | 133 | 145 | 129 | 0.2 | 28 | 41 | 71 | 43.8333 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.5 | 3.5934 | 1.7967 | H2 | 4 | Stable | 0.9 | 80 | 122 | 147 | 119.1667 | 0.2 | 26 | 57 | 70 | 54 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | HW - additional unplanned design effort | Person_216 | 2016-05-23 | 2019-10-21 01:00 | 0.4 | 3.3367 | 1.3347 | Reduce | 0.4 | 3.3367 | 1.3347 | H2 | 4 | Stable | 0.7 | 93 | 124 | 154 | 123.8333 | 0.2 | 6 | 58 | 69 | 51.1667 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK303(025) | Project_024_RISK303(025) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in contract value from our supplier | Person_119 | 2016-10-20 01:00 | 2019-05-23 | 0.25 | 4.2779 | 1.0695 | Accept | 0.25 | 4.2779 | 1.0695 | H2 | 4 | Stable | 0.9 | 84 | 123 | 160 | 122.6667 | 0.9 | 84 | 123 | 160 | 122.6667 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK305(027) | Project_024_RISK305(027) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment not available on time | Person_119 | 2016-11-19 01:00 | 2019-05-23 | 0.3 | 2.5667 | 0.77001 | Accept | 0.3 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.9 | 91 | 124 | 153 | 123.3333 | 0.9 | 91 | 124 | 153 | 123.3333 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design [in addition to costed effort] | Person_216 | 2017-05-28 | 2017-10-17 01:00 | 0.2 | 2.6951 | 0.53901 | Reduce | 0.2 | 2.6951 | 0.53901 | H3 | 3 | Improving | 0.5 | 94 | 134 | 144 | 129 | 0.4 | 39 | 57 | 73 | 56.6667 | 0 | 0 | 1 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_692 | 2016-12-21 01:00 | 2017-12-19 01:00 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Stable | 0.5 | 85 | 134 | 146 | 127.8333 | 0.2 | 14 | 42 | 71 | 42.1667 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_692 | 2017-05-23 | 2019-07-21 | 0.333 | 11.5502 | 3.8462 | Reduce | 0.333 | 11.5502 | 3.8462 | H2 | 4 | Stable | 0.9 | 102 | 137 | 155 | 134.1667 | 0.4 | 32 | 52 | 68 | 51.3333 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-080 | Project_008_Risk-080 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Recovery of Costs | Person_565 | 2016-08-21 01:00 | 2017-08-20 01:00 | 0.5 | 23.6737 | 11.8369 | -- | 0.5 | 23.6737 | 11.8369 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK296(013) | Project_024_RISK296(013) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Qualification/Certification Requirements flowdown | Person_119 | 2016-10-20 01:00 | 2017-05-22 | 0.25 | 52.0822 | 23.437 | Accept | 0.25 | 52.0822 | 23.437 | H2 | 4 | Worsening | 0.6 | 109 | 131 | 150 | 130.5 | 0.6 | 109 | 131 | 150 | 130.5 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before part b finished | Person_119 | 2016-10-20 01:00 | 2017-07-20 | 0.35 | 15.8141 | 3.9535 | Accept | 0.35 | 15.8141 | 3.9535 | H2 | 4 | Worsening | 0.8 | 84 | 138 | 158 | 132.3333 | 0.8 | 84 | 138 | 158 | 132.3333 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Survey costs | Person_618 | 2016-04-22 | 2017-08-20 01:00 | 0.2 | 13.2573 | 2.6515 | Avoid | 0.2 | 13.2573 | 2.6515 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-079 | Project_008_Risk-079 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Regulations Phase 3 and 4 | Person_565 | 2016-10-21 01:00 | 2018-08-21 | 0.25 | 71.9682 | 17.992 | -- | 0.25 | 71.9682 | 17.992 | H3 | 3 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK298(016) | Project_024_RISK298(016) | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Environmental testing required | Person_119 | 2016-10-20 01:00 | 2017-05-22 | 0.2 | 33.9324 | 10.1797 | Accept | 0.2 | 33.9324 | 10.1797 | H2 | 4 | Stable | 0.5 | 84 | 137 | 154 | 131 | 0.5 | 84 | 137 | 154 | 131 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK301(022) | Project_024_RISK301(022) | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Interface delays | Person_119 | 2016-10-20 01:00 | 2017-01-20 01:00 | 0.1 | 3.1818 | 1.5909 | Accept | 0.1 | 3.1818 | 1.5909 | H3 | 3 | Stable | 0.7 | 93 | 136 | 160 | 132.8333 | 0.7 | 93 | 136 | 160 | 132.8333 | 0 | 0 | 1 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK299(018) | Project_024_RISK299(018) | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Additional support hours | Person_119 | 2017-01-20 01:00 | 2017-07-20 | 0.35 | 3.046 | 1.523 | Accept | 0.35 | 3.046 | 1.523 | H3 | 3 | Stable | 0.8 | 97 | 132 | 154 | 129.8333 | 0.8 | 97 | 132 | 154 | 129.8333 | 0 | 0 | 1 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 0.2 | 7.2932 | 3.6466 | Accept | 0.2 | 7.2932 | 3.6466 | H2 | 4 | Stable | 0.5 | 114 | 134 | 148 | 133 | 0.5 | 114 | 134 | 148 | 133 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.7 | 103 | 123 | 158 | 125.5 | 0.3 | 27 | 50 | 66 | 48.8333 | 0 | 25 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 0.25 | 8.0582 | 2.4175 | Accept | 0.25 | 8.0582 | 2.4175 | H3 | 3 | Stable | 0.7 | 95 | 129 | 158 | 128.1667 | 0.7 | 95 | 129 | 158 | 128.1667 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | More issues during Qualification including additional PRs | Person_147 | 2017-04-22 | 2017-11-04 01:00 | 0.35 | 0 | 0 | Accept | 0.35 | 0 | 0 | H1 | 5 | Stable | 0.9 | 118 | 125 | 160 | 129.6667 | 0.9 | 118 | 125 | 160 | 129.6667 |  | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Suppliers | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 0.5596 | 0.05596 | Accept | 0.15 | 0.5596 | 0.05596 | H2 | 4 | Stable | 0.6 | 101 | 139 | 144 | 133.5 | 0.6 | 101 | 139 | 144 | 133.5 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 3.6174 | 1.8087 | Accept | 0.2 | 3.6172 | 0.72345 | H2 | 4 | Stable | 0.6 | 109 | 123 | 155 | 126 | 0.6 | 109 | 123 | 155 | 126 | 0.0051359 | 0 | 0 | 0.0030815
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Local customer Engineers in country | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 2.3503 | 0.47006 | Accept | 0.1 | 2.3503 | 0.47006 | H2 | 4 | Stable | 0.7 | 112 | 134 | 153 | 133.5 | 0.7 | 112 | 134 | 153 | 133.5 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence | Person_455 | 2016-05-23 | 2020-05-23 | 0.3 | 4.4768 | 2.2384 | Accept | 0.3 | 4.4768 | 2.2384 | H2 | 4 | Stable | 0.9 | 94 | 131 | 146 | 127.3333 | 0.9 | 94 | 131 | 146 | 127.3333 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Consumables | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 76.7807 | 3.839 | Accept | 0.2 | 76.7807 | 3.839 | H2 | 4 | Stable | 0.7 | 113 | 127 | 154 | 129.1667 | 0.7 | 113 | 127 | 154 | 129.1667 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 7. Finance | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 23.5255 | 11.7628 | Accept | 0.2 | 23.5255 | 11.7628 | H2 | 4 | Stable | 0.8 | 101 | 126 | 151 | 126 | 0.8 | 101 | 126 | 151 | 126 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 60.4367 | 3.0218 | Accept | 0.15 | 60.4367 | 3.0218 | H2 | 4 | Stable | 0.9 | 113 | 140 | 142 | 135.8333 | 0.9 | 113 | 140 | 142 | 135.8333 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-148 | Project_020_Risk-148 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs non-available items | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.3 | 14.9935 | 4.498 | Reduce | 0.3 | 2.6369 | 0.79106 | H2 | 4 | Stable | 0.8 | 108 | 136 | 158 | 135 | 0.2 | 14 | 40 | 72 | 41 | 82.4131 | 0 | 0 | 49.4479
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-22 01:00 | 2017-05-22 | 0.25 | 7.4225 | 1.8556 | Reduce | 0.1 | 2.0081 | 0.20081 | H3 | 3 | Stable | 0.8 | 113 | 132 | 157 | 133 | 0.2 | 15 | 57 | 73 | 52.6667 | 72.9455 | 60 | 0 | 43.7673
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 2.6991 | 1.0796 | H2 | 4 | Stable | 0.9 | 107 | 126 | 146 | 126.1667 | 0.2 | 10 | 48 | 77 | 46.5 | 31.8182 | 20 | 0 | 19.0909
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 18.6688 | 3.7338 | Accept | 0.2 | 18.6688 | 1.9191 | H2 | 4 | Stable | 0.9 | 105 | 130 | 148 | 128.8333 | 0.9 | 105 | 130 | 148 | 128.8333 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-147 | Project_020_Risk-147 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component taking longer to refurbish in country | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.6 | 6.7477 | 4.0486 | Reduce | 0.6 | 1.8743 | 1.1246 | H2 | 4 | Stable | 0.9 | 99 | 137 | 153 | 133.3333 | 0.4 | 7 | 42 | 62 | 39.5 | 72.2227 | 0 | 0 | 43.3336
2017-04-22 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-62 | Project_022_RISK-62 | Threat | Project Contingency | Open | H3 | 3 | 8. Operations & Maintenance | Additional Costs from Integration Cost Centre | Person_703 | 2017-03-23 | 2017-05-14 | 0.5 | 7.1754 | 3.5877 | Avoid | 0.292 | 3.5877 | 1.0476 | H3 | 3 | Worsening | [10 empty] | 50 | 41.6 | 0 | 30
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport Routes | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 3.8666 | 1.5853 | Accept | 0.15 | 1.3288 | 0.5448 | H2 | 4 | Stable | 0.9 | 89 | 131 | 150 | 127.1667 | 0.9 | 89 | 131 | 150 | 127.1667 | 65.6338 | 0 | 0 | 39.3803
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Internal Quality Issues | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 18.069 | 1.8069 | Accept | 0.2 | 11.3212 | 1.1321 | H2 | 4 | Stable | 0.8 | 115 | 138 | 154 | 136.8333 | 0.8 | 115 | 138 | 154 | 136.8333 | 37.3444 | 0 | 0 | 22.4066
2017-04-22 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2017-06-21 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.35 | 2.8688 | 1.0041 | H2 | 4 | Stable | 0.5 | 81 | 140 | 152 | 132.1667 | 0.2 | 27 | 57 | 74 | 54.8333 | 22.0253 | 56.25 | 0 | 13.2152
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk017 | Project_042_Risk017 | Threat | Financial Contingency | Open | H2 | 4 | 6. Contractual/Legal | Liquidated Damages | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 4.4985 | 1.3495 | Accept | 0.4 | 2.999 | 0.8997 | H2 | 4 | Stable | 0.9 | 80 | 134 | 160 | 129.3333 | 0.9 | 80 | 134 | 160 | 129.3333 | 33.333 | 0 | 0 | 19.9998
2017-04-22 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2017-05-22 | 0.85 | 25.2325 | 21.4476 | Avoid | 0.08 | 8.5319 | 0.68255 | H2 | 4 | Stable | [10 empty] | 66.187 | 90.5882 | 0 | 39.7122
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Repairs | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 2.3975 | 2.3975 | Accept | 0.25 | 0 | 0 | H2 | 4 | Stable | 0.7 | 114 | 128 | 152 | 129.6667 | 0.7 | 114 | 128 | 152 | 129.6667 | 100 | 0 | 0 | 60
2017-04-22 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2017-08-20 01:00 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 0.65554 | 0.52443 | H2 | 4 | Stable | [10 empty] | 80.45 | 0 | 0 | 48.27
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_703 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 5.0983 | 0.76474 | H3 | 3 | Stable | 0.9 | 100 | 140 | 145 | 134.1667 | 0.3 | 39 | 44 | 67 | 47 | 19.0479 | 70 | 1 | 13.5287
2017-04-22 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2017-05-22 | 0.7 | 24.1887 | 16.9321 | Reduce | 0.25 | 2.1783 | 0.54459 | H2 | 4 | Stable | 0.9 | 84 | 138 | 157 | 132.1667 | 0.1 | 27 | 42 | 66 | 43.5 | 90.9944 | 64.2857 | 0 | 54.5966
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_174 | 2009-06-23 | 2017-08-20 01:00 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.5 | 103 | 125 | 143 | 124.3333 | 0.3 | 5 | 41 | 71 | 40 | 50 | 28.5714 | 0 | 30
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-12-20 01:00 | 0.5 | 17.2826 | 8.6413 | Reduce | 0.15 | 17.2826 | 2.5924 | H2 | 4 | Worsening | 0.5 | 113 | 127 | 145 | 127.6667 | 0.1 | 33 | 47 | 72 | 48.8333 | 0 | 70 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_174 | 2012-11-20 01:00 | 2017-08-20 01:00 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.7 | 117 | 133 | 147 | 132.6667 | 0.4 | 15 | 55 | 67 | 50.3333 | 0 | 50 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-12-17 01:00 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.4 | 12.6474 | 5.059 | H2 | 4 | Stable | 0.6 | 98 | 127 | 146 | 125.3333 | 0.1 | 10 | 43 | 78 | 43.3333 | 0 | 33.3333 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.8 | 115 | 125 | 156 | 128.5 | 0.2 | 25 | 59 | 75 | 56 | 0 | 50 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond (revised) target. | Person_482 | 2013-01-07 01:00 | 2018-02-04 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.8 | 105 | 134 | 141 | 130.3333 | 0.3 | 23 | 58 | 60 | 52.5 | 0 | 33.3333 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 01:00 | 2017-11-19 01:00 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.5 | 99 | 126 | 142 | 124.1667 | 0.2 | 2 | 57 | 61 | 48.5 | 0 | 33.3333 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2018-02-19 01:00 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Improving | 0.6 | 108 | 121 | 156 | 124.6667 | 0.4 | 24 | 55 | 77 | 53.5 | 0 | 57.1429 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 0.8 | 0.55181 | 0.44144 | Reduce | 0.6 | 0.55181 | 0.33108 | H1 | 5 | Worsening | 0.7 | 93 | 127 | 149 | 125 | 0.2 | 22 | 49 | 79 | 49.5 | 0 | 25 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 0.8 | 1.3243 | 1.0595 | Reduce | 0.6 | 1.3243 | 0.7946 | H1 | 5 | Worsening | 0.6 | 83 | 135 | 144 | 127.8333 | 0.2 | 28 | 43 | 78 | 46.3333 | 0 | 25 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_482 | 2016-08-06 | 2017-06-22 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.8 | 85 | 135 | 158 | 130.5 | 0.4 | 12 | 54 | 70 | 49.6667 |  | 50 | 1
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trial delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.7 | 91 | 123 | 144 | 121.1667 | 0.3 | 4 | 55 | 73 | 49.5 |  | 40 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trial delay due to equip[ment availability | Person_174 | 2016-10-21 01:00 | 2017-08-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.9 | 101 | 121 | 159 | 124 | 0.2 | 10 | 44 | 73 | 43.1667 |  | 60 | 1
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-09-19 01:00 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.8 | 86 | 135 | 152 | 129.6667 | 0.3 | 38 | 55 | 78 | 56 | 7.8429 | 40 | 0 | 4.7058
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 0.2 | 0 | 0 | Reduce | 0.05 | 0 | 0 | H3 | 3 | Stable | 0.5 | 84 | 135 | 148 | 128.6667 | 0.3 | 9 | 44 | 68 | 42.1667 |  | 75 | 1
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 0.3 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 83 | 129 | 157 | 126 | 0.2 | 32 | 42 | 71 | 45.1667 |  | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 91 | 123 | 143 | 121 | 0.2 | 21 | 45 | 69 | 45 |  | 66.6667 | 1
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_482 | 2016-08-06 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 88 | 123 | 145 | 120.8333 | 0.1 | 24 | 59 | 63 | 53.8333 |  | 80 | 1
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2017-05-07 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.9 | 92 | 122 | 154 | 122.3333 | 0.1 | 25 | 56 | 79 | 54.6667 | 80 | 66.6667 | 0 | 48
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-05-23 | 2018-01-20 01:00 | 0.1 | 0.48559 | 0.048559 | Reduce | 0.1 | 0.48559 | 0.048559 | H2 | 4 | Stable | 0.8 | 95 | 132 | 160 | 130.5 | 0.2 | 22 | 52 | 74 | 50.6667 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 14:00 | 2019-08-20 14:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 14:00 | 2019-08-20 14:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 14:00 | 2019-08-20 14:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 14:00 | 2019-08-20 14:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 14:00 | 2019-08-20 14:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-63 | Project_022_RISK-63 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Levy | Person_703 | 2012-04-19 | 2017-08-20 01:00 | 0.8 | 3.5298 | 2.8239 | Exploit | 0.8 | 3.5298 | 2.8239 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-095 | Project_008_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Repair of interface units from the Programme | Person_567 | 2017-05-23 | 2018-08-21 | 0.2 | 9.4695 | 1.8939 | Avoid | 0.2 | 9.4695 | 1.8939 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk016 | Project_042_Risk016 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport/Delivery Speed | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 4.8452 | 1.9381 | Accept | 0.1 | 4.8452 | 1.9381 | H2 | 4 | Stable | 0.8 | 109 | 126 | 152 | 127.5 | 0.8 | 109 | 126 | 152 | 127.5 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Country Stability | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 3.7878 | 1.1363 | Accept | 0.4 | 3.7878 | 1.1363 | H2 | 4 | Stable | 0.8 | 87 | 136 | 148 | 129.8333 | 0.8 | 87 | 136 | 148 | 129.8333 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK021 | Project_021_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | ERP implementation | Person_174 | 2017-06-23 | 2017-09-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.9 | 83 | 137 | 150 | 130.1667 | 0.4 | 15 | 57 | 60 | 50.5 |  | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK024 | Project_021_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_482 | 2017-05-23 | 2017-11-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 110 | 124 | 158 | 127.3333 | 0.4 | 2 | 57 | 74 | 50.6667 |  | 40 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 | 0.4 | 9.139 | 3.6556 | Avoid | 0.2 | 9.139 | 1.8278 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Product Baseline delivery is late | Person_151 | 2015-09-21 | 2017-02-13 | 0.125 | 232.2192 | 29.0274 | -- | 0.215 | 27.8663 | 5.9913 | H2 | 4 | Stable | [10 empty] | 88 | -72 | 0 | 52.8
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 0.5 | 13.7833 | 6.8917 | Avoid | 0.2 | 6.8917 | 1.3783 | H3 | 3 | Stable | [10 empty] | 50 | 60 | 1 | 31.8
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-20 | 0.3 | 5.5433 | 1.663 | Reduce | 0.35 | 5.5433 | 1.9402 | H2 | 4 | Worsening | 0.5 | 93 | 129 | 150 | 126.5 | 0.3 | 26 | 53 | 66 | 50.6667 | 0 | -16.6667 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 | 2016-11-20 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Worsening | [10 empty] | 0 | 75 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 4.4946 | 1.1236 | Accept | 0.1 | 4.4946 | 0.44946 | H2 | 4 | Stable | 0.5 | 110 | 125 | 146 | 126 | 0.5 | 110 | 125 | 146 | 126 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 6.7418 | 1.6855 | Accept | 0.2 | 6.7418 | 1.0113 | H2 | 4 | Stable | 0.6 | 93 | 127 | 158 | 126.5 | 0.6 | 93 | 127 | 158 | 126.5 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 0.3 | 26.9674 | 8.0902 | Avoid | 0.3 | 14.9819 | 4.4946 | H2 | 4 | Stable | [10 empty] | 44.4444 | 0 | 0 | 26.6667
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-21 | 0.5 | 26.9674 | 13.4837 | Avoid | 0.1 | 12.7646 | 1.2765 | H2 | 4 | Worsening | [10 empty] | 52.6667 | 80 | 0 | 31.6
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-21 22:00 | 2016-12-20 22:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.7 | 96 | 135 | 158 | 132.3333 | 0.3 | 6 | 51 | 66 | 46 | 47 | 0 | 0 | 28.2
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-21 22:00 | 2016-12-20 22:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-18 22:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.2 | 1.5935 | 0.3187 | H3 | 3 | Stable | 0.9 | 100 | 131 | 149 | 128.8333 | 0.4 | 34 | 51 | 69 | 51.1667 | 50 | 50 | 1 | 31.5
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.9 | 100 | 138 | 143 | 132.5 | 0.4 | 13 | 51 | 69 | 47.6667 | 25.8065 | 20 | 0 | 15.4839
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 | 0.05 | 0.59882 | 0.059882 | Accept | 0.05 | 0.59882 | 0.059882 | H2 | 4 | Stable | 0.6 | 99 | 122 | 154 | 123.5 | 0.6 | 99 | 122 | 154 | 123.5 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-125 | Project_043_Risk-125 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | IOC Delayed due to a number of factors (Marching Customer Risk) | Person_084 | 2014-09-13 01:00 | 2018-03-21 | 0.5 | 1.9362 | 0.96809 | -- | 0.3 | 1.9362 | 0.58086 | H2 | 4 | Stable | [10 empty] | 0 | 40 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 0.8 | 22.8501 | 6.855 | Accept | 0.6 | 22.8501 | 6.855 | H1 | 5 | Stable | 0.6 | 98 | 136 | 156 | 133 | 0.6 | 98 | 136 | 156 | 133 | 0 | 25 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 | 2016-08-20 | 0.1 | 0 | 0 | Accept | 0.1 | 0 | 0 | H2 | 4 | Stable | 0.9 | 113 | 130 | 155 | 131.3333 | 0.9 | 113 | 130 | 155 | 131.3333 |  | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 | 0.2 | 0 | 0 | Accept | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.9 | 117 | 125 | 147 | 127.3333 | 0.9 | 117 | 125 | 147 | 127.3333 |  | 0 | 1
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 19:00 | 2019-08-20 19:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.5 | 120 | 135 | 149 | 134.8333 | 0.3 | 33 | 41 | 78 | 45.8333 | 83.3333 | 88.8889 | 1 | 52.6667
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.6 | 101 | 139 | 143 | 133.3333 | 0.1 | 8 | 56 | 60 | 48.6667 | 72 | 0 | 0 | 43.2
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.6 | 86 | 128 | 160 | 126.3333 | 0.2 | 32 | 46 | 68 | 47.3333 | 47.7391 | 0 | 0 | 28.6435
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 19:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.5 | 94 | 136 | 148 | 131 | 0.3 | 23 | 53 | 75 | 51.6667 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Non-Recurring Engineering higher than expected | Person_674 | 2016-06-01 | 2016-08-04 | 0.4 | 6.5968 | 2.6387 | Reduce | 0.2 | 6.5944 | 1.3189 | H3 | 3 | Improving | 0.6 | 118 | 139 | 147 | 136.8333 | 0.3 | 1 | 53 | 62 | 45.8333 | 0.036395 | 50 | 0 | 0.021837
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 0.3 | 1.2004 | 0.24009 | Accept | 0.4 | 1.2004 | 0.24009 | H3 | 3 | Stable | 0.6 | 82 | 127 | 144 | 122.3333 | 0.6 | 82 | 127 | 144 | 122.3333 | 0 | -33.3333 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.6 | 118 | 138 | 148 | 136.3333 | 0.4 | 5 | 42 | 78 | 41.8333 | 0 | 0 | 1 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.8 | 113 | 135 | 148 | 133.5 | 0.4 | 37 | 55 | 65 | 53.6667 | 25.8065 | 20 | 0 | 15.4839
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unforseen and substantial increase in Repairs workload during new build production period. | Person_515 | 2017-10-23 01:00 | 2017-11-19 01:00 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.03 | 1.5434 | 0.046303 | H3 | 3 | Stable | 0.5 | 85 | 138 | 149 | 131 | 0.4 | 8 | 45 | 67 | 42.5 | 0 | 90 | 1 | 2.7
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK007 | Project_041_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Advanced production of products using a Qual. standard component rather than a Prod. standard | Person_547 | 2017-10-21 01:00 | 2019-05-23 | 0.49 | 1.2862 | 0.63024 | Reduce | 0.2 | 1.2862 | 0.25724 | H3 | 3 | Stable | 0.5 | 115 | 136 | 148 | 134.5 | 0.4 | 24 | 44 | 77 | 46.1667 | 0 | 59.1837 | 1 | 1.7755
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_693 | 2017-05-23 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.6 | 114 | 128 | 153 | 129.8333 | 0.4 | 26 | 42 | 76 | 45 | 0 | 50 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2017-04-22 | 2018-05-22 | 0.75 | 10.7184 | 8.0388 | Reduce | 0.15 | 5.3592 | 0.80388 | H3 | 3 | Stable | 0.6 | 82 | 124 | 150 | 121.3333 | 0.2 | 1 | 42 | 60 | 38.1667 | 50 | 80 | 1 | 32.4
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2020-09-19 01:00 | 0.2 | 1.9722 | 0.98609 | Accept | 0.2 | 1.9722 | 0.98609 | H3 | 3 | Stable | 0.8 | 120 | 135 | 157 | 136.1667 | 0.8 | 120 | 135 | 157 | 136.1667 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2019-07-21 | 0.3 | 2.5081 | 1.2541 | Accept | 0.2 | 2.5081 | 1.2541 | H3 | 3 | Stable | 0.6 | 88 | 130 | 153 | 126.8333 | 0.6 | 88 | 130 | 153 | 126.8333 | 0 | 33.3333 | 1 | 1
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2017-05-23 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.05 | 0.68598 | 0.034299 | H3 | 3 | Stable | 0.6 | 110 | 128 | 151 | 128.8333 | 0.4 | 6 | 47 | 67 | 43.5 | 0 | 80 | 1 | 2.4
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 0.45017 | 0.2701 | Accept | 0.1 | 0.45017 | 0.13505 | H3 | 3 | Stable | 0.5 | 92 | 124 | 158 | 124.3333 | 0.5 | 92 | 124 | 158 | 124.3333 | 0 | -233.3333 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 3.7514 | 0.37514 | Accept | 0.25 | 3.7514 | 0.37514 | H2 | 4 | Stable | 0.5 | 114 | 139 | 155 | 137.5 | 0.5 | 114 | 139 | 155 | 137.5 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2017-05-23 | 2017-12-21 01:00 | 0.1 | 21.8655 | 2.1865 | Reduce | 0.01 | 21.8655 | 0.21865 | H2 | 4 | Stable | 0.5 | 80 | 137 | 160 | 131.3333 | 0.1 | 19 | 45 | 70 | 44.8333 | 0 | 90 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2017-05-23 | 2018-11-20 01:00 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Stable | 0.8 | 82 | 138 | 144 | 129.6667 | 0.4 | 33 | 55 | 67 | 53.3333 | 0 | 60 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Unidentified CRs and concessions | Person_693 | 2017-04-22 | 2017-09-20 01:00 | 0.5 | 1.2005 | 0.60023 | Reduce | 0.15 | 0.51019 | 0.076529 | H3 | 3 | Stable | 0.9 | 103 | 138 | 141 | 132.6667 | 0.1 | 3 | 42 | 65 | 39.3333 | 57.5001 | 70 | 1 | 36.6001
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_238 | 2017-04-22 | 2018-05-22 | 0.25 | 3.3227 | 0.83067 | Reduce | 0.05 | 3.3227 | 0.16613 | H3 | 3 | Stable | 0.6 | 83 | 138 | 153 | 131.3333 | 0.1 | 39 | 48 | 63 | 49 | 0 | 80 | 1 | 2.4
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_693 | 2017-05-23 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.1 | 0.77172 | 0.077172 | H3 | 3 | Worsening | 0.6 | 107 | 125 | 148 | 125.8333 | 0.1 | 10 | 47 | 68 | 44.3333 | 0 | 60 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 1.7492 | 0.17492 | Accept | 0.3 | 1.7492 | 0.17492 | H2 | 4 | Stable | 0.8 | 101 | 122 | 154 | 123.8333 | 0.8 | 101 | 122 | 154 | 123.8333 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_693 | 2017-05-23 | 2018-11-20 01:00 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.08 | 6.431 | 0.51448 | H3 | 3 | Improving | 0.8 | 99 | 140 | 153 | 135.3333 | 0.2 | 33 | 59 | 62 | 55.1667 | -47.0588 | 46.6667 | 1 | -26.8353
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 0.45 | 0.21008 | 0.10504 | Accept | 0.45 | 0.21008 | 0.05252 | H2 | 4 | Stable | 0.6 | 100 | 131 | 141 | 127.5 | 0.6 | 100 | 131 | 141 | 127.5 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Reduce touch labour if Production readiness programme successful | Person_238 | 2017-05-23 | 2017-10-21 01:00 | 0.3 | 1.5606 | 0.46818 | Exploit | 0.5 | 1.5606 | 0.7803 | H2 | 4 | Stable | [10 empty] | 0 | -66.6667 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_565 | 2018-05-22 | 2018-08-21 | 0.25 | 13.3529 | 6.6765 | Accept | 0.25 | 23.5716 | 11.7858 | H3 | 3 | Stable | 0.6 | 111 | 123 | 156 | 126.5 | 0.6 | 111 | 123 | 156 | 126.5 | -76.5278 | 0 | 0 | -45.9167
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 0.5 | 9.2728 | 4.6364 | Reduce | 0.15 | 9.2728 | 1.3909 | H2 | 4 | Stable | 0.5 | 101 | 122 | 155 | 124 | 0.4 | 8 | 43 | 62 | 40.3333 | 0 | 70 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R008 | Project_016_Risk--R008 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Additional Travel & Subsistence | Person_574 | 2016-01-13 01:00 | 2019-05-23 | 0.4 | 8.9019 | 3.5608 | Reduce | 0.25 | 8.9019 | 2.2255 | H3 | 3 | Stable | 0.8 | 87 | 132 | 147 | 127 | 0.3 | 14 | 44 | 67 | 42.8333 | 0 | 37.5 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 0.3 | 8.7814 | 2.6344 | Reduce | 0.15 | 8.7832 | 1.3175 | H3 | 3 | Stable | 0.9 | 96 | 130 | 156 | 128.6667 | 0.4 | 20 | 40 | 77 | 42.8333 | -0.021119 | 50 | 1 | 1.4873
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R009 | Project_016_Risk--R009 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer maybe difficult to work with | Person_697 | 2016-04-02 | 2019-08-01 | 0.6 | 23.9549 | 14.3729 | Reduce | 0.43864 | 23.8312 | 10.4533 | H2 | 4 | Stable | 0.5 | 86 | 130 | 147 | 125.5 | 0.4 | 15 | 54 | 64 | 49.1667 | 0.51612 | 26.8938 | 0 | 0.30967
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Lack of Spares Availability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 0.3 | 108.3186 | 32.4956 | Accept | 0.3 | 108.3186 | 32.4956 | H3 | 3 | Improving | 0.9 | 118 | 137 | 141 | 134.5 | 0.9 | 118 | 137 | 141 | 134.5 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 0.5 | 5.126 | 2.563 | Accept | 0.5 | 5.126 | 2.563 | H2 | 4 | Stable | 0.6 | 82 | 127 | 150 | 123.3333 | 0.6 | 82 | 127 | 150 | 123.3333 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Delay of processing | Person_306 | 2016-04-02 | 2017-03-21 01:00 | 0.15 | 26.3497 | 3.9525 | Reduce | 0.15 | 13.1767 | 1.9765 | H3 | 3 | Stable | 0.6 | 81 | 129 | 160 | 126.1667 | 0.3 | 2 | 59 | 70 | 51.3333 | 49.993 | 0 | 1 | 29.9958
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 0.5 | 12.815 | 2.563 | Accept | 0.5 | 12.815 | 2.563 | H2 | 4 | Stable | 0.7 | 119 | 130 | 149 | 131.3333 | 0.7 | 119 | 130 | 149 | 131.3333 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 12.0547 | 2.4109 | Accept | 0.5 | 12.0547 | 2.4109 | H1 | 5 | Stable | 0.5 | 103 | 130 | 152 | 129.1667 | 0.5 | 103 | 130 | 152 | 129.1667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.8 | 93 | 127 | 151 | 125.3333 | 0.2 | 13 | 46 | 65 | 43.6667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-20 22:00 | 2016-08-20 22:00 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.6 | 89 | 126 | 158 | 125.1667 | 0.1 | 1 | 51 | 67 | 45.3333 | 0 | 16.6667 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 | 2017-08-20 | 0.2 | 53.0293 | 10.6059 | Reduce | 0.2 | 53.0293 | 10.6059 | H3 | 3 | Worsening | 0.9 | 115 | 127 | 146 | 128.1667 | 0.3 | 23 | 55 | 65 | 51.3333 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Commercial aspects agreement | Person_439 | 2013-08-21 | 2017-05-22 | 0.02 | 4.8296 | 0.096593 | Transfer | 0.02 | 4.8296 | 0.096593 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 | 2017-08-20 | 0.1 | 34.363 | 3.4363 | Avoid | 0.1 | 34.363 | 3.4363 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 | 2017-08-20 | 0.26 | 16.2047 | 4.2132 | Avoid | 0.26 | 16.2047 | 4.2132 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 | 2017-08-20 | 0.25 | 7.7469 | 1.9367 | Reduce | 0.25 | 7.7469 | 1.9367 | H3 | 3 | Stable | 0.6 | 82 | 126 | 142 | 121.3333 | 0.2 | 21 | 41 | 76 | 43.5 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-116 | Project_011_Risk-116 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Delays to Qualification | Person_147 | 2017-04-22 | 2017-08-19 01:00 | 0.5 | 0.43243 | 0.21621 | Reduce | 0.5 | 0.43243 | 0.21621 | H1 | 5 | Stable | 0.7 | 86 | 123 | 145 | 120.5 | 0.4 | 21 | 45 | 79 | 46.6667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-104 | Project_011_Risk-104 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer delayed in providing Custeomr Furnished Equipment | Person_147 | 2016-06-23 | 2017-04-21 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.7 | 84 | 122 | 153 | 120.8333 | 0.3 | 34 | 47 | 77 | 49.8333 |  | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 0.3 | 0.51931 | 0.15579 | -- | 0.15 | 0.51931 | 0.077897 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-095 | Project_008_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Repair of interface units from the Programme | Person_567 | 2017-05-23 | 2018-08-21 | 0.2 | 9.4695 | 1.8939 | Avoid | 0.2 | 9.4695 | 1.8939 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 0.2 | 0.55005 | 0.11001 | Avoid | 0.2 | 0.55005 | 0.11001 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2017-09-20 01:00 | 2018-04-21 | 0.15 | 0.28639 | 0.042959 | -- | 0.15 | 0.28639 | 0.042959 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-080 | Project_008_Risk-080 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Recovery of Costs | Person_565 | 2016-08-21 01:00 | 2017-08-20 01:00 | 0.5 | 23.6737 | 11.8369 | -- | 0.5 | 23.6737 | 11.8369 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-08-20 01:00 | 0.2 | 0.24207 | 0.048414 | -- | 0.2 | 0.24207 | 0.048414 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 0.2 | 1.661 | 0.33219 | Reduce | 0.2 | 1.661 | 0.33219 | H2 | 4 | Stable | 0.5 | 93 | 124 | 160 | 124.8333 | 0.1 | 19 | 52 | 72 | 49.8333 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2017-11-19 01:00 | 0.05 | 15.8141 | 3.9535 | Accept | 0.05 | 15.8141 | 3.9535 | H3 | 3 | Improving | 0.9 | 111 | 126 | 156 | 128.5 | 0.9 | 111 | 126 | 156 | 128.5 | 0 | 0 | 1 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Survey costs | Person_618 | 2016-04-22 | 2017-08-20 01:00 | 0.2 | 13.2573 | 2.6515 | Avoid | 0.2 | 13.2573 | 2.6515 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2017-10-21 01:00 | 2018-08-21 | 0.4 | 1.2444 | 0.49778 | Reduce | 0.4 | 1.2444 | 0.49778 | H2 | 4 | Stable | 0.5 | 88 | 128 | 143 | 123.8333 | 0.4 | 28 | 44 | 79 | 47.1667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-079 | Project_008_Risk-079 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Regulations Phase 3 and 4 | Person_565 | 2016-10-21 01:00 | 2018-08-21 | 0.25 | 71.9682 | 17.992 | -- | 0.25 | 71.9682 | 17.992 | H3 | 3 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-149 | Project_020_Risk-149 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs to be returned to UK | Person_703 | 2016-12-21 01:00 | 2017-11-19 01:00 | 0.2 | 0.16195 | 0.072876 | Accept | 0.1028 | 0.16195 | 0.072876 | H2 | 4 | Stable | 0.5 | 100 | 134 | 154 | 131.6667 | 0.5 | 100 | 134 | 154 | 131.6667 | 0 | 48.6 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2017-05-22 | 0.41 | 33.9324 | 10.1797 | Accept | 0.41 | 33.9324 | 10.1797 | H2 | 4 | Stable | 0.9 | 99 | 124 | 146 | 123.5 | 0.9 | 99 | 124 | 146 | 123.5 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 01:00 | 2017-07-20 | 0.45 | 0.41947 | 0.18876 | Reduce | 0.45 | 0.41944 | 0.18875 | H2 | 4 | Stable | 0.6 | 113 | 133 | 149 | 132.3333 | 0.4 | 12 | 57 | 78 | 53 | 0.0067461 | 0 | 0 | 0.0040477
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-10-19 01:00 | 2018-08-21 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.8 | 90 | 126 | 145 | 123.1667 | 0.4 | 18 | 53 | 76 | 51 |  | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Pick up and Drop off of Software Resource | Person_230 | 2017-12-19 01:00 | 2018-02-19 01:00 | 0.4 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-109 | Project_011_Risk-109 | Opportunitity | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Environment complexity | Person_187 | 2016-07-21 | 2018-08-21 | 0.25 | 0.14661 | 0.036651 | -- | 0.25 | 0.14661 | 0.036651 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-108 | Project_011_Risk-108 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Offer additional functionality to the customer | Person_147 | 2017-04-22 | 2018-08-21 | 0.1 | 0.34094 | 0.034094 | -- | 0.1 | 0.34094 | 0.034094 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 0.2 | 0.12388 | 0.024775 | Reduce | 0.2 | 0.12388 | 0.024775 | H2 | 4 | Stable | 0.6 | 102 | 132 | 151 | 130.1667 | 0.4 | 38 | 50 | 60 | 49.6667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 0.4 | 0.51141 | 0.20457 | Avoid | 0.4 | 0.51141 | 0.20457 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.2 | 0.10171 | 0.020343 | -- | 0.2 | 0.10171 | 0.020343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 0.3 | 0.28639 | 0.085917 | Reduce | 0.3 | 0.28639 | 0.085917 | H2 | 4 | Stable | 0.6 | 119 | 126 | 146 | 128.1667 | 0.3 | 5 | 52 | 72 | 47.5 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 2. Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 0.25 | 0 | 0 | -- | 0.25 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2017-10-21 01:00 | 2018-05-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 0.3 | 0.10626 | 0.031878 | -- | 0.3 | 0.01932 | 0.005796 | H3 | 3 | Stable | [10 empty] | 81.8181 | 0 | 0 | 49.0909
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_174 | 2009-06-23 | 2018-08-21 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.7 | 117 | 138 | 157 | 137.6667 | 0.3 | 28 | 54 | 76 | 53.3333 | 50 | 28.5714 | 0 | 30
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-12-20 01:00 | 0.6 | 17.2826 | 10.3696 | Reduce | 0.3 | 17.2826 | 5.1848 | H2 | 4 | Worsening | 0.5 | 106 | 137 | 146 | 133.3333 | 0.1 | 31 | 44 | 79 | 47.6667 | 0 | 50 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_174 | 2012-11-20 01:00 | 2018-08-21 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.9 | 102 | 133 | 157 | 131.8333 | 0.3 | 10 | 50 | 79 | 48.1667 | 0 | 50 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-12-17 01:00 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.4 | 12.6474 | 5.059 | H2 | 4 | Stable | 0.9 | 115 | 140 | 146 | 136.8333 | 0.4 | 32 | 45 | 68 | 46.6667 | 0 | 33.3333 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.6 | 97 | 132 | 152 | 129.5 | 0.3 | 38 | 44 | 66 | 46.6667 | 0 | 50 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond (revised) target. | Person_482 | 2013-01-07 01:00 | 2018-02-04 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.5 | 84 | 133 | 155 | 128.5 | 0.1 | 33 | 44 | 62 | 45.1667 | 0 | 33.3333 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2013-01-07 01:00 | 2017-11-19 01:00 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.9 | 98 | 123 | 158 | 124.6667 | 0.3 | 13 | 41 | 66 | 40.5 | 0 | 33.3333 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2018-02-19 01:00 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Stable | 0.6 | 97 | 134 | 159 | 132 | 0.4 | 12 | 41 | 71 | 41.1667 | 0 | 57.1429 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 0.8 | 4.6352 | 3.7081 | Reduce | 0.6 | 4.6352 | 2.7811 | H1 | 5 | Worsening | 0.5 | 92 | 124 | 154 | 123.6667 | 0.4 | 29 | 57 | 75 | 55.3333 | 0 | 25 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 0.8 | 1.3243 | 1.0595 | Reduce | 0.6 | 1.3243 | 0.7946 | H1 | 5 | Worsening | 0.7 | 109 | 124 | 150 | 125.8333 | 0.4 | 3 | 56 | 72 | 49.8333 | 0 | 25 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_482 | 2016-08-06 | 2017-06-22 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.9 | 112 | 131 | 154 | 131.6667 | 0.4 | 11 | 53 | 76 | 49.8333 |  | 50 | 1
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trial delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 89 | 130 | 145 | 125.6667 | 0.3 | 10 | 53 | 68 | 48.3333 |  | 40 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trial delay due to equip[ment availability | Person_174 | 2016-10-21 01:00 | 2017-08-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.9 | 111 | 140 | 144 | 135.8333 | 0.4 | 3 | 59 | 77 | 52.6667 |  | 60 | 1
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-09-19 01:00 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.7 | 113 | 130 | 144 | 129.5 | 0.4 | 14 | 42 | 66 | 41.3333 | 7.8429 | 40 | 0 | 4.7058
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 0.2 | 0 | 0 | Reduce | 0.05 | 0 | 0 | H3 | 3 | Stable | 0.7 | 84 | 125 | 159 | 123.8333 | 0.4 | 34 | 49 | 65 | 49.1667 |  | 75 | 1
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 0.3 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 98 | 125 | 144 | 123.6667 | 0.3 | 28 | 58 | 74 | 55.6667 |  | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 94 | 121 | 150 | 121.3333 | 0.1 | 10 | 53 | 71 | 48.8333 |  | 66.6667 | 1
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_482 | 2016-08-06 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 120 | 125 | 143 | 127.1667 | 0.3 | 17 | 44 | 77 | 45 |  | 80 | 1
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2018-01-19 01:00 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H3 | 3 | Stable | 0.6 | 109 | 123 | 151 | 125.3333 | 0.4 | 33 | 49 | 69 | 49.6667 | 80 | 66.6667 | 0 | 48
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-05-23 | 2018-01-20 01:00 | 0.1 | 0.48559 | 0.048559 | Reduce | 0.1 | 0.48559 | 0.048559 | H3 | 3 | Stable | 0.8 | 111 | 131 | 144 | 129.8333 | 0.3 | 13 | 53 | 74 | 49.8333 | 0 | 0 | 1 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK021 | Project_021_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | ERP implementation | Person_174 | 2017-06-23 | 2017-09-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.25 | 0 | 0 | H2 | 4 | Stable | 0.9 | 81 | 138 | 156 | 131.5 | 0.1 | 36 | 50 | 68 | 50.6667 |  | 50 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK024 | Project_021_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_482 | 2017-05-23 | 2017-11-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.5 | 105 | 126 | 152 | 126.8333 | 0.2 | 8 | 41 | 78 | 41.6667 |  | 40 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-085 | Project_008_SER-085 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Insufficient LOE to manage the supply chain with reducing number of spares | Person_639 | 2017-04-22 | 2018-08-21 | 0.4 | 1.8788 | 0.28182 | Accept | 0.4 | 1.8788 | 0.28182 | H3 | 3 | Stable | 0.5 | 109 | 136 | 159 | 135.3333 | 0.5 | 109 | 136 | 159 | 135.3333 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 | 2016-11-20 | 0.25 | 1.8788 | 0.18788 | Accept | 0.1 | 1.8788 | 0.18788 | H3 | 3 | Stable | 0.8 | 98 | 123 | 151 | 123.5 | 0.8 | 98 | 123 | 151 | 123.5 | 0 | 60 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-20 | 0.25 | 29.4599 | 8.838 | Accept | 0.15 | 18.7882 | 5.6365 | H3 | 3 | Stable | 0.9 | 93 | 126 | 157 | 125.6667 | 0.9 | 93 | 126 | 157 | 125.6667 | 36.2245 | 40 | 1 | 22.9347
2017-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 0.3 | 4.7948 | 0.95895 | Accept | 0.3 | 4.7948 | 0.95895 | H2 | 4 | Improving | 0.5 | 101 | 130 | 146 | 127.8333 | 0.5 | 101 | 130 | 146 | 127.8333 | 0 | 0 | 0 | 0
2017-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 0.61 | 0.65759 | 0.098638 | Accept | 0.61 | 0.65759 | 0.098638 | H1 | 5 | Stable | 0.5 | 114 | 139 | 151 | 136.8333 | 0.5 | 114 | 139 | 151 | 136.8333 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Risk of not being able to perform Tests | Person_238 | 2017-12-21 01:00 | 2019-01-21 01:00 | 0.5 | 2.8182 | 0.56365 | Accept | 0.5 | 2.8182 | 0.56365 | H2 | 4 | Stable | 0.8 | 119 | 123 | 141 | 125.3333 | 0.8 | 119 | 123 | 141 | 125.3333 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_238 | 2017-05-23 | 2019-01-21 01:00 | 0.5 | 0 | 0 | Accept | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.7 | 99 | 132 | 148 | 129.1667 | 0.7 | 99 | 132 | 148 | 129.1667 |  | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_693 | 2017-04-22 | 2017-09-19 01:00 | 0.6 | 2.5834 | 0.64585 | Accept | 0.3 | 2.5834 | 0.64585 | H3 | 3 | Worsening | 0.8 | 93 | 127 | 159 | 126.6667 | 0.8 | 93 | 127 | 159 | 126.6667 | 0 | 50 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_547 | 2017-05-23 | 2018-05-22 | 0.1 | 0.65759 | 0.065759 | Accept | 0.1 | 0.75153 | 0.075153 | H3 | 3 | Stable | 0.6 | 107 | 122 | 155 | 125 | 0.6 | 107 | 122 | 155 | 125 | -14.2857 | 0 | 1 | -8.5714
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production, Procurement or Engineering | Person_725 | 2018-01-21 01:00 | 2019-05-23 | 0.1 | 1.1273 | 0.45092 | Accept | 0.1 | 1.1273 | 0.45092 | H3 | 3 | Worsening | 0.6 | 97 | 134 | 150 | 130.5 | 0.6 | 97 | 134 | 150 | 130.5 | 0 | 0 | 1 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R81 | Project_041_R81 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Re-imaging of PC's - additional material/Labour effort | Person_515 | 2017-05-23 | 2017-10-21 01:00 | 0.5 | 9.3941 | 0.93941 | Accept | 0.25 | 9.3941 | 0.93941 | H2 | 4 | Stable | 0.8 | 118 | 128 | 156 | 131 | 0.8 | 118 | 128 | 156 | 131 | 0 | 50 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Governance and Export Rules | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 0.93941 | 0.23485 | Transfer | 0.25 | 0.93941 | 0.23485 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 0.5 | 2.1606 | 0.43213 | Accept | 0.5 | 2.1606 | 0.43213 | H2 | 4 | Improving | 0.8 | 93 | 125 | 154 | 124.5 | 0.8 | 93 | 125 | 154 | 124.5 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-148 | Project_020_Risk-148 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs non-available items | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.3 | 14.9935 | 4.498 | Reduce | 0.3 | 2.6369 | 0.79106 | H2 | 4 | Stable | 0.7 | 106 | 138 | 142 | 133.3333 | 0.4 | 38 | 47 | 74 | 50 | 82.4131 | 0 | 0 | 49.4479
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-22 01:00 | 2017-05-22 | 0.25 | 7.4225 | 1.8556 | Reduce | 0.1 | 2.0081 | 0.20081 | H3 | 3 | Stable | 0.7 | 80 | 127 | 142 | 121.6667 | 0.2 | 7 | 45 | 67 | 42.3333 | 72.9455 | 60 | 0 | 43.7673
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 2.6991 | 1.0796 | H2 | 4 | Stable | 0.9 | 82 | 140 | 143 | 130.8333 | 0.2 | 33 | 55 | 68 | 53.5 | 31.8182 | 20 | 0 | 19.0909
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 0.3 | 18.6688 | 3.7338 | Accept | 0.3 | 18.6688 | 1.4338 | H2 | 4 | Stable | 0.7 | 108 | 139 | 157 | 136.8333 | 0.7 | 108 | 139 | 157 | 136.8333 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-147 | Project_020_Risk-147 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component taking longer to refurbish in country | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.6 | 6.7477 | 4.0486 | Reduce | 0.6 | 1.8743 | 1.1246 | H2 | 4 | Stable | 0.5 | 101 | 126 | 151 | 126 | 0.2 | 23 | 53 | 72 | 51.1667 | 72.2227 | 0 | 0 | 43.3336
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-20 22:00 | 2019-08-20 | 0.5 | 18.069 | 1.8069 | Accept | 0.5 | 11.3212 | 1.1321 | H2 | 4 | Stable | 0.8 | 113 | 136 | 152 | 134.8333 | 0.8 | 113 | 136 | 152 | 134.8333 | 37.3444 | 0 | 0 | 22.4066
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.2 | 4.4985 | 1.3495 | Accept | 0.2 | 2.999 | 0.8997 | H3 | 3 | Stable | 0.5 | 120 | 131 | 158 | 133.6667 | 0.5 | 120 | 131 | 158 | 133.6667 | 33.333 | 0 | 0 | 19.9998
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_703 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 5.0983 | 0.76474 | H3 | 3 | Stable | 0.7 | 116 | 135 | 145 | 133.5 | 0.2 | 17 | 56 | 73 | 52.3333 | 19.0479 | 70 | 1 | 13.5287
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R013 | Project_016_Risk--R013 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Resource Availability (Threat) | Person_697 | 2016-04-02 | 2019-08-01 | 0.2 | 25.966 | 7.7898 | Accept | 0.2 | 10.3864 | 3.1159 | H2 | 4 | Worsening | 0.9 | 97 | 138 | 159 | 134.6667 | 0.9 | 97 | 138 | 159 | 134.6667 | 60 | 0 | 0 | 36
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 | 2017-08-20 | 0.05 | 30.2764 | 12.1106 | Accept | 0.05 | 30.2764 | 12.1106 | H3 | 3 | Stable | 0.7 | 113 | 135 | 152 | 134.1667 | 0.7 | 113 | 135 | 152 | 134.1667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Additional minor point releases | Person_228 | 2016-05-23 | 2017-10-19 01:00 | 0.5 | 11.9444 | 5.9722 | Reduce | 0.25 | 11.9444 | 2.9861 | H2 | 4 | Stable | 0.6 | 101 | 131 | 159 | 130.6667 | 0.2 | 20 | 44 | 71 | 44.5 | 0 | 50 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_228 | 2016-05-23 | 2017-07-23 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.5 | 115 | 124 | 145 | 126 | 0.2 | 31 | 45 | 60 | 45.1667 | 0 | 50 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_413 | 2015-11-21 01:00 | 2018-11-20 01:00 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.8 | 117 | 122 | 143 | 124.6667 | 0.3 | 22 | 42 | 63 | 42.1667 | 0 | 5 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.8 | 2.8043 | 2.2435 | Reduce | 0.45 | 2.8043 | 1.2619 | H1 | 5 | Stable | 0.6 | 100 | 128 | 148 | 126.6667 | 0.4 | 15 | 54 | 68 | 49.8333 | 0 | 43.75 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK167 | Project_024_RISK167 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer not providing the information needed | Person_710 | 2016-08-21 01:00 | 2018-02-19 01:00 | 0.5 | 9.971 | 4.9855 | Reduce | 0.3 | 9.971 | 2.9913 | H2 | 4 | Worsening | 0.6 | 93 | 122 | 146 | 121.1667 | 0.1 | 16 | 56 | 64 | 50.6667 | 0 | 40 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK306(028) | Project_024_RISK306(028) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | HW repairs required on units | Person_119 | 2016-11-19 01:00 | 2018-11-20 01:00 | 0.3 | 2.813 | 0.8439 | Reduce | 0.2 | 2.813 | 0.5626 | H2 | 4 | Stable | 0.5 | 113 | 131 | 151 | 131.3333 | 0.3 | 5 | 42 | 61 | 39 | 0 | 33.3333 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 0.5626 | 0.14065 | Accept | 0.35 | 0.5626 | 0.14065 | H3 | 3 | Stable | 0.8 | 83 | 128 | 155 | 125 | 0.8 | 83 | 128 | 155 | 125 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 | 2017-07-20 | 0.05 | 5.1932 | 2.0773 | Accept | 0.05 | 5.1716 | 2.0686 | H2 | 4 | Stable | 0.9 | 80 | 131 | 145 | 124.8333 | 0.9 | 80 | 131 | 145 | 124.8333 | 0.41665 | 0 | 0 | 0.24999
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.25 | 5.1932 | 1.2983 | Accept | 0.25 | 5.1932 | 1.2983 | H3 | 3 | Stable | 0.7 | 102 | 135 | 142 | 130.6667 | 0.7 | 102 | 135 | 142 | 130.6667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 | 0.05 | 5.3577 | 1.3394 | Accept | 0.05 | 5.3577 | 1.3394 | H3 | 3 | Stable | 0.7 | 90 | 128 | 143 | 124.1667 | 0.7 | 90 | 128 | 143 | 124.1667 | 0 | 0 | 1 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK226 | Project_024_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Late Evidences delay Certification delivery | Person_710 | 2017-04-30 | 2017-12-21 01:00 | 0.4 | 3.9468 | 1.5787 | Reduce | 0.2 | 3.9468 | 0.78937 | H2 | 4 | Worsening | 0.6 | 80 | 136 | 147 | 128.5 | 0.2 | 11 | 40 | 69 | 40 | 0 | 50 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK302(024) | Project_024_RISK302(024) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | On time provision of platform units | Person_119 | 2016-11-19 01:00 | 2019-05-23 | 0.25 | 2.3889 | 0.59722 | Reduce | 0.15 | 2.3889 | 0.35833 | H2 | 4 | Stable | 0.9 | 105 | 128 | 153 | 128.3333 | 0.4 | 13 | 58 | 65 | 51.6667 | 0 | 40 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK227 | Project_024_RISK227 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Data Bunching | Person_710 | 2017-03-23 | 2017-09-19 01:00 | 0.4 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 95 | 127 | 160 | 127.1667 | 0.1 | 30 | 56 | 65 | 53.1667 |  | 25 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 0.2 | 4.8297 | 1.6904 | Accept | 0.2 | 4.8297 | 1.6904 | H2 | 4 | Stable | 0.9 | 118 | 129 | 143 | 129.5 | 0.9 | 118 | 129 | 143 | 129.5 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-085 | Project_008_SER-085 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Insufficient LOE to manage the supply chain with reducing number of spares | Person_639 | 2017-04-22 | 2018-08-21 | 0.4 | 5.1067 | 1.0213 | Accept | 0.4 | 5.1067 | 1.0213 | H3 | 3 | Stable | 0.8 | 80 | 136 | 150 | 129 | 0.8 | 80 | 136 | 150 | 129 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 0.45 | 0.5626 | 0.19691 | Accept | 0.45 | 0.5626 | 0.19691 | H2 | 4 | Stable | 0.8 | 101 | 125 | 160 | 126.8333 | 0.8 | 101 | 125 | 160 | 126.8333 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_565 | 2018-05-22 | 2018-08-21 | 0.25 | 21.1629 | 21.1629 | Accept | 0.25 | 21.1629 | 21.1629 | H3 | 3 | Stable | 0.9 | 83 | 126 | 152 | 123.1667 | 0.9 | 83 | 126 | 152 | 123.1667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK225 | Project_024_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | More testing required as a result compliance to Platform Risk | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 5.6866 | 2.8433 | Reduce | 0.3 | 5.6866 | 1.706 | H2 | 4 | Stable | 0.7 | 87 | 132 | 157 | 128.6667 | 0.2 | 39 | 53 | 70 | 53.5 | 0 | 40 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.5 | 101 | 136 | 159 | 134 | 0.4 | 10 | 54 | 72 | 49.6667 | 0 | 60 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_288 | 2017-02-22 01:00 | 2017-11-19 01:00 | 0.3 | 19.9938 | 5.9981 | Reduce | 0.1 | 19.9938 | 1.9994 | H3 | 3 | Improving | 0.5 | 86 | 130 | 159 | 127.5 | 0.1 | 3 | 57 | 65 | 49.3333 | 0 | 66.6667 | 1 | 2
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.5 | 3.843 | 1.9215 | H1 | 5 | Stable | 0.6 | 94 | 133 | 148 | 129 | 0.3 | 19 | 53 | 78 | 51.5 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Overland performance | Person_075 | 2016-06-23 | 2017-11-19 01:00 | 0.1 | 1.6835 | 0.16835 | Reduce | 0.1 | 3.5011 | 0.35011 | H3 | 3 | Improving | 0.8 | 91 | 131 | 146 | 126.8333 | 0.3 | 16 | 56 | 70 | 51.6667 | -107.9692 | 0 | 1 | -64.7815
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Lack of Spares Availability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 0.3 | 2.7146 | 2.7146 | Accept | 0.3 | 2.7146 | 2.7146 | H3 | 3 | Stable | 0.5 | 93 | 132 | 153 | 129 | 0.5 | 93 | 132 | 153 | 129 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK256 | Project_024_RISK256 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unable to meet spare capacity requirement | Person_119 | 2016-07-21 | 2018-01-21 01:00 | 0.8 | 0.12983 | 0.10386 | Reduce | 0.05 | 0.12983 | 0.0064915 | H3 | 3 | Stable | 0.5 | 97 | 132 | 158 | 130.5 | 0.2 | 19 | 47 | 78 | 47.5 | 0 | 93.75 | 1 | 2.8125
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Performance (collector opportunity) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.3814 | 26.127 | 9.9648 | -- | 0.4132 | 26.127 | 10.7957 | H1 | 5 | Stable | [10 empty] | 0 | -8.3377 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.3 | 20.8767 | 6.263 | H2 | 4 | Stable | 0.9 | 94 | 127 | 149 | 125.1667 | 0.2 | 20 | 56 | 65 | 51.5 | 50 | 25 | 0 | 30
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.493 | 58.1898 | 28.6876 | Reduce | 0.32035 | 40.4161 | 12.9473 | H1 | 5 | Worsening | 0.8 | 110 | 124 | 149 | 125.8333 | 0.1 | 11 | 48 | 62 | 44.1667 | 30.5444 | 35.0203 | 0 | 18.3266
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK308 | Project_024_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System robustness and resilience | Person_774 | 2017-04-06 | 2018-06-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.1 | 2.5966 | 0.25966 | H3 | 3 | Stable | 0.7 | 98 | 122 | 152 | 123 | 0.4 | 34 | 56 | 67 | 54.1667 | 58.3333 | 66.6667 | 1 | 37
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK312 | Project_024_RISK312 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Built-in Test not fit for purpose | Person_774 | 2017-02-25 01:00 | 2018-05-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.2 | 9.8671 | 1.9734 | H2 | 4 | Stable | 0.8 | 102 | 127 | 154 | 127.3333 | 0.3 | 2 | 54 | 79 | 49.5 | -58.3333 | 33.3333 | 0 | -35
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) at the System level on product platform - performed by 3rd parties | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.41 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -2.5 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.61 | 0.25667 | 0.15657 | Reduce | 0.5 | 0.25667 | 0.12834 | H2 | 4 | Stable | 0.7 | 101 | 128 | 158 | 128.5 | 0.4 | 19 | 43 | 75 | 44.3333 | 0 | 18.0328 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 1.078 | 0.43121 | Reduce | 0.4 | 1.4673 | 0.58692 | H2 | 4 | Improving | 0.7 | 96 | 122 | 153 | 122.8333 | 0.1 | 3 | 56 | 78 | 50.8333 | -36.1112 | 0 | 0 | -21.6667
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2018-03-21 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2017-11-20 01:00 | 0.6 | 0.89835 | 0.53901 | Transfer | 0.6 | 0.89835 | 0.53901 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 0.35 | 0.85557 | 0.29945 | Reduce | 0.35 | 1.9208 | 0.67227 | H2 | 4 | Stable | 0.6 | 86 | 125 | 153 | 123.1667 | 0.1 | 6 | 45 | 79 | 44.1667 | -124.5001 | 0 | 0 | -74.7001
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 0.77001 | 0.30801 | Reduce | 0.3 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.5 | 111 | 131 | 153 | 131.3333 | 0.3 | 4 | 54 | 60 | 46.6667 | 0 | 25 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2018-02-20 01:00 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.5 | 93 | 126 | 151 | 124.6667 | 0.4 | 30 | 50 | 76 | 51 | 0 | 28.5714 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 0.25 | 1.54 | 0.30801 | Accept | 0.25 | 0.77001 | 0.154 | H3 | 3 | Stable | 0.7 | 97 | 135 | 154 | 131.8333 | 0.7 | 97 | 135 | 154 | 131.8333 | 50 | 0 | 0 | 30
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | More issues during Qualification including additional PRs | Person_147 | 2017-07-26 | 2017-11-04 01:00 | 0.35 | 0.94968 | 0.28491 | Accept | 0.35 | 0.94968 | 0.18994 | H1 | 5 | Stable | 0.6 | 114 | 130 | 153 | 131.1667 | 0.6 | 114 | 130 | 153 | 131.1667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Suppliers | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 27.1644 | 0.81493 | Accept | 0.15 | 12.8336 | 1.2834 | H2 | 4 | Stable | 0.9 | 96 | 124 | 141 | 122.1667 | 0.9 | 96 | 124 | 141 | 122.1667 | 52.7559 | 0 | 0 | 31.6535
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2018-03-22 | 2019-07-21 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.8 | 106 | 128 | 160 | 129.6667 | 0.4 | 16 | 42 | 74 | 43 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2018-03-16 01:00 | 0.41 | 6.4168 | 2.6309 | Transfer | 0.41 | 0 | 0 | H1 | 5 | Stable | [10 empty] | 100 | 0 | 0 | 60
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sub-system FPGA | Person_216 | 2017-01-21 01:00 | 2018-02-20 01:00 | 0.3 | 1.54 | 0.46201 | Reduce | 0.4 | 1.5914 | 0.63655 | H2 | 4 | Stable | 0.7 | 107 | 127 | 153 | 128 | 0.2 | 13 | 44 | 73 | 43.6667 | -3.3333 | -33.3333 | 0 | -2
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort for System HW/SW- System upgrade | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.3 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.8 | 93 | 123 | 156 | 123.5 | 0.4 | 31 | 51 | 72 | 51.1667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs [technical scope] | Person_372 | 2017-06-23 | 2018-08-22 01:00 | 0.35 | 9.505 | 3.3267 | Reduce | 0.35 | 9.505 | 3.3267 | H2 | 4 | Stable | 0.8 | 82 | 135 | 154 | 129.3333 | 0.4 | 29 | 57 | 73 | 55 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.5 | 3.5934 | 1.7967 | H2 | 4 | Stable | 0.9 | 83 | 136 | 157 | 130.6667 | 0.1 | 31 | 42 | 64 | 43.8333 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | HW - additional unplanned design effort | Person_216 | 2016-05-23 | 2019-10-21 01:00 | 0.4 | 3.3367 | 1.3347 | Reduce | 0.4 | 3.3367 | 1.3347 | H2 | 4 | Stable | 0.6 | 101 | 126 | 154 | 126.5 | 0.2 | 31 | 46 | 73 | 48 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 4.2779 | 1.0695 | Accept | 0.2 | 4.2779 | 1.0695 | H2 | 4 | Stable | 0.7 | 100 | 127 | 149 | 126.1667 | 0.7 | 100 | 127 | 149 | 126.1667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Local customer Engineers in country | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 2.5667 | 0.77001 | Accept | 0.1 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.9 | 103 | 134 | 142 | 130.1667 | 0.9 | 103 | 134 | 142 | 130.1667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design [in addition to costed effort] | Person_216 | 2017-05-28 | 2017-10-17 01:00 | 0.2 | 2.6951 | 0.53901 | Reduce | 0.2 | 2.6951 | 0.53901 | H3 | 3 | Improving | 0.7 | 92 | 136 | 141 | 129.5 | 0.4 | 22 | 57 | 79 | 54.8333 | 0 | 0 | 1 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_372 | 2016-12-21 01:00 | 2017-12-19 01:00 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Stable | 0.5 | 101 | 133 | 152 | 130.8333 | 0.1 | 33 | 58 | 76 | 56.8333 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_585 | 2017-10-21 01:00 | 2019-07-21 | 0.333 | 11.5502 | 3.8462 | Reduce | 0.333 | 11.5502 | 3.8462 | H2 | 4 | Stable | 0.5 | 82 | 140 | 147 | 131.5 | 0.4 | 14 | 45 | 73 | 44.5 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence | Person_455 | 2016-05-23 | 2020-05-23 | 0.3 | 31.83 | 23.8725 | Accept | 0.3 | 31.83 | 23.8725 | H2 | 4 | Stable | 0.5 | 117 | 124 | 143 | 126 | 0.5 | 117 | 124 | 143 | 126 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.7 | 118 | 129 | 152 | 131 | 0.4 | 15 | 50 | 79 | 49 | 0 | 25 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Consumables | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 3.4415 | 1.3766 | Accept | 0.2 | 3.4415 | 1.3766 | H2 | 4 | Stable | 0.6 | 100 | 124 | 144 | 123.3333 | 0.6 | 100 | 124 | 144 | 123.3333 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 7. Finance | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 8.0582 | 2.4175 | Accept | 0.2 | 8.0582 | 2.4175 | H2 | 4 | Stable | 0.8 | 105 | 140 | 155 | 136.6667 | 0.8 | 105 | 140 | 155 | 136.6667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 0 | 0 | Accept | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.5 | 97 | 138 | 151 | 133.3333 | 0.5 | 97 | 138 | 151 | 133.3333 |  | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 0.5596 | 0.05596 | Accept | 0.2 | 0.5596 | 0.05596 | H2 | 4 | Stable | 0.9 | 116 | 139 | 151 | 137.1667 | 0.9 | 116 | 139 | 151 | 137.1667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport Routes | Person_455 | 2016-05-23 | 2020-05-23 | 0.15 | 3.6174 | 1.8087 | Accept | 0.15 | 3.6172 | 0.72345 | H2 | 4 | Stable | 0.7 | 111 | 132 | 158 | 132.8333 | 0.7 | 111 | 132 | 158 | 132.8333 | 0.0051359 | 0 | 0 | 0.0030815
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Internal Quality Issues | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 2.3503 | 0.47006 | Accept | 0.2 | 2.3503 | 0.47006 | H2 | 4 | Stable | 0.5 | 115 | 123 | 149 | 126 | 0.5 | 115 | 123 | 149 | 126 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk017 | Project_042_Risk017 | Threat | Financial Contingency | Open | H2 | 4 | 6. Contractual/Legal | Liquidated Damages | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 4.4768 | 2.2384 | Accept | 0.4 | 4.4768 | 2.2384 | H2 | 4 | Stable | 0.8 | 82 | 133 | 154 | 128 | 0.8 | 82 | 133 | 154 | 128 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Repairs | Person_455 | 2016-05-23 | 2020-05-23 | 0.25 | 76.7807 | 3.839 | Accept | 0.25 | 76.7807 | 3.839 | H2 | 4 | Stable | 0.7 | 81 | 134 | 156 | 128.8333 | 0.7 | 81 | 134 | 156 | 128.8333 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk016 | Project_042_Risk016 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and Offsets | Transport/Delivery Speed | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 23.5255 | 11.7628 | Accept | 0.1 | 23.5255 | 11.7628 | H2 | 4 | Stable | 0.8 | 112 | 139 | 152 | 136.6667 | 0.8 | 112 | 139 | 152 | 136.6667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Country Stability | Person_455 | 2016-05-23 | 2020-05-23 | 0.4 | 60.4367 | 3.0218 | Accept | 0.4 | 60.4367 | 3.0218 | H2 | 4 | Stable | 0.5 | 118 | 137 | 154 | 136.6667 | 0.5 | 118 | 137 | 154 | 136.6667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2020-05-23 | 0.1 | 0 | 0 | Accept | 0.1 | 0 | 0 | H2 | 4 | Stable | 0.6 | 84 | 140 | 144 | 131.3333 | 0.6 | 84 | 140 | 144 | 131.3333 |  | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2020-05-23 | 0.2 | 0.81199 | 0.081199 | Accept | 0.2 | 0.81199 | 0.0406 | H2 | 4 | Stable | 0.8 | 81 | 134 | 143 | 126.6667 | 0.8 | 81 | 134 | 143 | 126.6667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-149 | Project_020_Risk-149 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs to be returned to UK | Person_703 | 2016-12-21 01:00 | 2017-11-19 01:00 | 0.2 | 0 | 0 | Accept | 0.0768 | 0 | 0 | H2 | 4 | Stable | 0.5 | 108 | 124 | 151 | 125.8333 | 0.5 | 108 | 124 | 151 | 125.8333 |  | 61.6 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PEN Testing Security Features | Person_604 | 2015-04-11 | 2017-08-20 01:00 | 0.3 | 5.4553 | 1.6366 | Reduce | 0.15 | 5.252 | 0.7878 | H2 | 4 | Stable | 0.7 | 97 | 135 | 141 | 129.6667 | 0.1 | 15 | 51 | 79 | 49.6667 | 3.7267 | 50 | 0 | 2.236
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Equipment environmental failure | Person_710 | 2016-05-23 | 2017-09-19 01:00 | 0.3 | 20.3303 | 7.1156 | Accept | 0.3 | 18.975 | 3.795 | H2 | 4 | Improving | 0.7 | 88 | 130 | 156 | 127.3333 | 0.7 | 88 | 130 | 156 | 127.3333 | 6.6667 | 0 | 0 | 4
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Cable and connectors | Person_499 | 2015-11-21 01:00 | 2019-04-10 | 0.45 | 0.41338 | 0.18602 | Reduce | 0.2 | 0.41338 | 0.082677 | H2 | 4 | Stable | 0.7 | 106 | 128 | 146 | 127.3333 | 0.2 | 9 | 49 | 75 | 46.6667 | 0 | 55.5556 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | FOC Acceptance | Person_500 | 2015-11-21 01:00 | 2017-12-20 01:00 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.3 | 8.471 | 2.5413 | H2 | 4 | Stable | 0.6 | 120 | 128 | 144 | 129.3333 | 0.3 | 28 | 59 | 76 | 56.6667 | -99.9999 | 14.2857 | 0 | -59.9999
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Qual failure | Person_710 | 2016-06-22 | 2017-07-20 | 0.4 | 8.8098 | 3.0834 | Accept | 0.4 | 8.8098 | 1.762 | H1 | 5 | Improving | 0.5 | 102 | 140 | 144 | 134.3333 | 0.5 | 102 | 140 | 144 | 134.3333 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK300(020) | Project_024_RISK300(020) | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Travel and onsite support | Person_119 | 2017-01-20 01:00 | 2017-07-20 | 0.25 | 0.40661 | 0.16264 | Accept | 0.25 | 0.40661 | 0.081321 | H3 | 3 | Stable | 0.9 | 81 | 132 | 153 | 127 | 0.9 | 81 | 132 | 153 | 127 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Furnished Equipmnet Condition | Person_132 | 2015-04-27 | 2017-08-19 01:00 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.7 | 86 | 126 | 156 | 124.3333 | 0.2 | 19 | 51 | 67 | 48.3333 |  | 62.5 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK304(026) | Project_024_RISK304(026) | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | complex integration | Person_119 | 2016-10-20 01:00 | 2017-07-20 | 0.4 | 65.2604 | 58.7343 | Accept | 0.4 | 65.2604 | 32.6302 | H1 | 5 | Worsening | 0.6 | 88 | 121 | 160 | 122 | 0.6 | 88 | 121 | 160 | 122 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK303(025) | Project_024_RISK303(025) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in contract value from our supplier | Person_119 | 2016-10-20 01:00 | 2019-05-23 | 0.25 | 0 | 0 | Accept | 0.25 | 0 | 0 | H2 | 4 | Stable | 0.6 | 100 | 122 | 142 | 121.6667 | 0.6 | 100 | 122 | 142 | 121.6667 |  | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-020 | Project_028_Risk-020 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | (Project Management WP) Availability of Customer Furnished Equipmnet for modification | Person_604 | 2015-05-24 | 2019-02-20 01:00 | 0.25 | 0 | 0 | Avoid | 0.05 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 80 | 1
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK305(027) | Project_024_RISK305(027) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment not available on time | Person_119 | 2016-11-19 01:00 | 2019-05-23 | 0.3 | 54.7292 | 43.7834 | Accept | 0.3 | 54.7292 | 43.7834 | H2 | 4 | Stable | 0.8 | 93 | 123 | 158 | 123.8333 | 0.8 | 93 | 123 | 158 | 123.8333 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-20 23:00 | 2016-05-21 | 0.5 | 4.3921 | 2.196 | Reduce | 0.3 | 0 | 0 | H1 | 5 | Stable | 0.8 | 103 | 138 | 152 | 134.5 | 0.1 | 5 | 45 | 63 | 41.3333 | 100 | 40 | 0 | 60
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK296(013) | Project_024_RISK296(013) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Qualification/Certification Requirements flowdown | Person_119 | 2016-10-20 01:00 | 2017-08-20 01:00 | 0.25 | 3.1818 | 1.5909 | Accept | 0.25 | 3.1818 | 1.5909 | H2 | 4 | Worsening | 0.9 | 102 | 126 | 147 | 125.5 | 0.9 | 102 | 126 | 147 | 125.5 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before part b finished | Person_119 | 2016-10-20 01:00 | 2017-07-20 | 0.35 | 3.046 | 1.523 | Accept | 0.35 | 3.046 | 1.523 | H2 | 4 | Worsening | 0.7 | 118 | 126 | 149 | 128.5 | 0.7 | 118 | 126 | 149 | 128.5 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK298(016) | Project_024_RISK298(016) | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Environmental testing required | Person_119 | 2016-10-20 01:00 | 2017-08-20 01:00 | 0.2 | 7.2932 | 3.6466 | Accept | 0.2 | 7.2932 | 3.6466 | H2 | 4 | Stable | 0.7 | 120 | 126 | 141 | 127.5 | 0.7 | 120 | 126 | 141 | 127.5 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK301(022) | Project_024_RISK301(022) | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Interface delays | Person_119 | 2016-10-20 01:00 | 2017-09-19 01:00 | 0.1 | 0.59882 | 0.14971 | Accept | 0.1 | 0.59882 | 0.14971 | H3 | 3 | Stable | 0.6 | 117 | 121 | 154 | 125.8333 | 0.6 | 117 | 121 | 154 | 125.8333 | 0 | 0 | 1 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK001 | Project_043_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Mission System Laptops | Person_135 | 2017-04-19 | 2017-07-30 | 0.33 | 0 | 0 | Reduce | 0.33 | 0 | 0 | H2 | 4 | Improving | 0.5 | 80 | 124 | 150 | 121 | 0.2 | 5 | 51 | 74 | 47.1667 |  | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK299(018) | Project_024_RISK299(018) | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Additional support hours | Person_119 | 2017-01-20 01:00 | 2017-07-20 | 0.35 | 0.11976 | 0.0059882 | Accept | 0.35 | 0.11976 | 0.0059882 | H3 | 3 | Stable | 0.6 | 118 | 128 | 149 | 129.8333 | 0.6 | 118 | 128 | 149 | 129.8333 | 0 | 0 | 1 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-125 | Project_043_Risk-125 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | IOC Delayed due to a number of factors (Marching Customer Risk) | Person_084 | 2014-09-13 01:00 | 2018-03-21 | 0.5 | 1.9362 | 0.96809 | -- | 0.3 | 1.9362 | 0.58086 | H2 | 4 | Stable | [10 empty] | 0 | 40 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2020-09-19 01:00 | 0.2 | 35.0206 | 7.0041 | Accept | 0.2 | 35.0206 | 7.0041 | H3 | 3 | Stable | 0.6 | 88 | 132 | 157 | 128.8333 | 0.6 | 88 | 132 | 157 | 128.8333 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2019-07-21 | 0.3 | 0.77172 | 0.30869 | Accept | 0.2 | 1.9293 | 0.77172 | H3 | 3 | Stable | 0.5 | 106 | 129 | 156 | 129.6667 | 0.5 | 106 | 129 | 156 | 129.6667 | -150 | 33.3333 | 1 | -89
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 13:00 | 2019-08-20 13:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 13:00 | 2019-08-20 13:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 13:00 | 2019-08-20 13:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 13:00 | 2019-08-20 13:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 13:00 | 2019-08-20 13:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-62 | Project_022_RISK-62 | Threat | Project Contingency | Open | H3 | 3 | 8. Operations & Maintenance | Additional Costs from Integration Cost Centre | Person_703 | 2017-03-23 | 2017-05-14 | 0.5 | 7.1754 | 3.5877 | Avoid | 0.292 | 3.5877 | 1.0476 | H3 | 3 | Worsening | [10 empty] | 50 | 41.6 | 0 | 30
2017-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2017-06-21 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.35 | 2.8688 | 1.0041 | H2 | 4 | Stable | 0.8 | 116 | 135 | 142 | 133 | 0.2 | 18 | 56 | 61 | 50.5 | 22.0253 | 56.25 | 0 | 13.2152
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 2.3975 | 2.3975 | Accept | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 111 | 133 | 148 | 131.8333 | 0.8 | 111 | 133 | 148 | 131.8333 | 100 | -233.3333 | 0 | 60
2017-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2017-08-20 01:00 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 0.65554 | 0.52443 | H2 | 4 | Stable | [10 empty] | 80.45 | 0 | 0 | 48.27
2017-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-63 | Project_022_RISK-63 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Levy | Person_703 | 2012-04-19 | 2017-08-20 01:00 | 0.8 | 3.5298 | 2.8239 | Exploit | 0.8 | 3.5298 | 2.8239 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 3.8666 | 1.5853 | Accept | 0.25 | 1.3288 | 0.5448 | H2 | 4 | Stable | 0.8 | 117 | 138 | 156 | 137.5 | 0.8 | 117 | 138 | 156 | 137.5 | 65.6338 | 0 | 0 | 39.3803
2017-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2017-05-22 | 0.85 | 25.2325 | 21.4476 | Avoid | 0.08 | 8.5319 | 0.68255 | H2 | 4 | Stable | [10 empty] | 66.187 | 90.5882 | 0 | 39.7122
2017-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2017-05-22 | 0.7 | 24.1887 | 16.9321 | Reduce | 0.25 | 2.1783 | 0.54459 | H2 | 4 | Stable | 0.7 | 88 | 123 | 156 | 122.6667 | 0.4 | 20 | 46 | 63 | 44.5 | 90.9944 | 64.2857 | 0 | 54.5966
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 0.3 | 0.51931 | 0.15579 | -- | 0.15 | 0.51931 | 0.077897 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 0.2 | 0.55005 | 0.11001 | Avoid | 0.2 | 0.55005 | 0.11001 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-123 | Project_011_Risk-123 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | No Requirement for Delta acceptance | Person_187 | 2017-06-23 | 2017-08-20 01:00 | 0.2 | 0.63074 | 0.12615 | -- | 0.2 | 0.63074 | 0.12615 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2016-07-21 | 2017-02-19 01:00 | 0.15 | 0.28639 | 0.042959 | -- | 0.15 | 0.28639 | 0.042959 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-08-20 01:00 | 0.2 | 0.24207 | 0.048414 | -- | 0.2 | 0.24207 | 0.048414 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 0.2 | 1.661 | 0.33219 | Reduce | 0.2 | 1.661 | 0.33219 | H2 | 4 | Stable | 0.8 | 104 | 132 | 152 | 130.6667 | 0.3 | 18 | 56 | 72 | 52.3333 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2017-10-21 01:00 | 2018-08-21 | 0.4 | 1.2444 | 0.49778 | Reduce | 0.4 | 1.2444 | 0.49778 | H2 | 4 | Stable | 0.5 | 114 | 123 | 141 | 124.5 | 0.2 | 8 | 49 | 69 | 45.5 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 0.16195 | 0.072876 | Accept | 0.3 | 0.16195 | 0.072876 | H2 | 4 | Stable | 0.9 | 93 | 122 | 148 | 121.5 | 0.9 | 93 | 122 | 148 | 121.5 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 01:00 | 2017-07-20 | 0.45 | 0.41947 | 0.18876 | Reduce | 0.45 | 0.41944 | 0.18875 | H2 | 4 | Stable | 0.6 | 100 | 121 | 145 | 121.5 | 0.2 | 24 | 45 | 77 | 46.8333 | 0.0067461 | 0 | 0 | 0.0040477
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-02-20 01:00 | 2018-08-21 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.8 | 118 | 128 | 156 | 131 | 0.3 | 20 | 53 | 72 | 50.6667 |  | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Pick up and Drop off of Software Resource | Person_230 | 2017-04-21 | 2018-02-19 01:00 | 0.4 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-109 | Project_011_Risk-109 | Opportunitity | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Environment complexity | Person_187 | 2016-07-21 | 2018-08-21 | 0.25 | 0.14661 | 0.036651 | -- | 0.25 | 0.14661 | 0.036651 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-108 | Project_011_Risk-108 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Offer additional functionality to the customer | Person_147 | 2017-04-22 | 2018-08-21 | 0.1 | 0.34094 | 0.034094 | -- | 0.1 | 0.34094 | 0.034094 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 0.2 | 0.12388 | 0.024775 | Reduce | 0.2 | 0.12388 | 0.024775 | H2 | 4 | Stable | 0.8 | 89 | 127 | 159 | 126 | 0.4 | 37 | 53 | 61 | 51.6667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 0.4 | 0.51141 | 0.20457 | Avoid | 0.4 | 0.51141 | 0.20457 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.2 | 0.10171 | 0.020343 | -- | 0.2 | 0.10171 | 0.020343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 0.3 | 0.28639 | 0.085917 | Reduce | 0.3 | 0.28639 | 0.085917 | H2 | 4 | Stable | 0.9 | 103 | 124 | 152 | 125.1667 | 0.2 | 33 | 48 | 76 | 50.1667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 2. Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 0.25 | 0 | 0 | -- | 0.25 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2017-10-21 01:00 | 2018-05-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 0.3 | 0.10626 | 0.031878 | -- | 0.3 | 0.01932 | 0.005796 | H3 | 3 | Stable | [10 empty] | 81.8181 | 0 | 0 | 49.0909
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-118 | Project_011_Risk-118 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer change environment | Person_187 | 2013-08-21 01:00 | 2018-08-21 | 0.1 | 0 | 0 | Avoid | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Non-Recurring Engineering higher than expected | Person_674 | 2016-06-01 | 2016-08-04 | 0.4 | 6.5968 | 2.6387 | Reduce | 0.2 | 6.5944 | 1.3189 | H3 | 3 | Improving | 0.5 | 90 | 136 | 158 | 132 | 0.4 | 15 | 42 | 69 | 42 | 0.036395 | 50 | 0 | 0.021837
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 19:00 | 2019-08-20 19:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.6 | 109 | 127 | 154 | 128.5 | 0.1 | 4 | 52 | 67 | 46.5 | 83.3333 | 88.8889 | 1 | 52.6667
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.7 | 85 | 131 | 153 | 127 | 0.1 | 15 | 44 | 68 | 43.1667 | 72 | 0 | 0 | 43.2
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.8 | 102 | 137 | 158 | 134.6667 | 0.3 | 14 | 58 | 75 | 53.5 | 47.7391 | 0 | 0 | 28.6435
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 19:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.8 | 90 | 128 | 158 | 126.6667 | 0.3 | 36 | 48 | 74 | 50.3333 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-19 23:00 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.6 | 98 | 136 | 159 | 133.5 | 0.1 | 14 | 51 | 65 | 47.1667 | 0 | 40 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-19 23:00 | 0.7 | 0.92411 | 0.64688 | Reduce | 0.3 | 0.36965 | 0.11089 | H2 | 4 | Stable | 0.7 | 83 | 130 | 151 | 125.6667 | 0.4 | 22 | 41 | 79 | 44.1667 | 60 | 57.1429 | 0 | 36
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-03 23:00 | 2016-04-21 | 0.5 | 4.0661 | 2.033 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.5 | 85 | 133 | 152 | 128.1667 | 0.2 | 2 | 45 | 73 | 42.5 | 0 | 90 | 1 | 2.7
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-19 23:00 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.5 | 0.46206 | 0.23103 | H1 | 5 | Improving | 0.6 | 88 | 132 | 145 | 126.8333 | 0.3 | 24 | 53 | 67 | 50.5 | 58.3333 | 16.6667 | 0 | 35
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-28 23:00 | 2017-08-19 23:00 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.6 | 92 | 131 | 149 | 127.5 | 0.1 | 39 | 52 | 68 | 52.5 | 0 | 50 | 1 | 1.5
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-19 23:00 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.6 | 117 | 132 | 158 | 133.8333 | 0.3 | 23 | 47 | 66 | 46.1667 | 0 | 25 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Stable | 0.8 | 107 | 126 | 159 | 128.3333 | 0.1 | 29 | 49 | 69 | 49 | 0 | 40 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-18 23:00 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Worsening | [10 empty] | 0 | 37.5 | 0 | 0
2017-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2017-11-19 01:00 | 0.05 | 0.92411 | 0.18482 | Accept | 0.05 | 0.92411 | 0.18482 | H3 | 3 | Improving | 0.8 | 113 | 136 | 152 | 134.8333 | 0.8 | 113 | 136 | 152 | 134.8333 | 0 | 0 | 1 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-19 23:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.7 | 93 | 137 | 153 | 132.3333 | 0.1 | 32 | 40 | 64 | 42.6667 | 90 | 75 | 1 | 56.25
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-19 23:00 | 0.4 | 9.139 | 3.6556 | Avoid | 0.2 | 9.139 | 1.8278 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Product Baseline delivery is late | Person_151 | 2015-09-20 23:00 | 2017-02-12 23:00 | 0.125 | 232.2192 | 29.0274 | -- | 0.215 | 27.8663 | 5.9913 | H2 | 4 | Stable | [10 empty] | 88 | -72 | 0 | 52.8
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 0.5 | 13.7833 | 6.8917 | Avoid | 0.2 | 6.8917 | 1.3783 | H3 | 3 | Stable | [10 empty] | 50 | 60 | 1 | 31.8
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-19 23:00 | 0.3 | 5.5433 | 1.663 | Reduce | 0.35 | 5.5433 | 1.9402 | H2 | 4 | Worsening | 0.5 | 86 | 130 | 145 | 125.1667 | 0.4 | 24 | 46 | 62 | 45 | 0 | -16.6667 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-20 23:00 | 2016-11-19 23:00 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Worsening | [10 empty] | 0 | 75 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Further Software Development | Person_523 | 2015-05-24 | 2017-08-19 01:00 | 0.1 | 4.4946 | 1.1236 | Accept | 0.05 | 4.4946 | 0.44946 | H3 | 3 | Stable | 0.8 | 105 | 132 | 146 | 129.8333 | 0.8 | 105 | 132 | 146 | 129.8333 | 0 | 50 | 1 | 1.5
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 0.3 | 26.9674 | 8.0902 | Avoid | 0.3 | 14.9819 | 4.4946 | H2 | 4 | Stable | [10 empty] | 44.4444 | 0 | 0 | 26.6667
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-20 23:00 | 0.5 | 26.9674 | 13.4837 | Avoid | 0.1 | 12.7646 | 1.2765 | H2 | 4 | Worsening | [10 empty] | 52.6667 | 80 | 0 | 31.6
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-12-21 01:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.6 | 81 | 134 | 147 | 127.3333 | 0.3 | 10 | 48 | 70 | 45.3333 | 47 | 0 | 0 | 28.2
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-12-21 01:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-19 01:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.2 | 1.5935 | 0.3187 | H3 | 3 | Stable | 0.7 | 110 | 127 | 147 | 127.5 | 0.3 | 11 | 40 | 63 | 39 | 50 | 50 | 1 | 31.5
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.9 | 87 | 135 | 142 | 128.1667 | 0.4 | 6 | 49 | 62 | 44 | 0 | 0 | 1 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence and missing info | Person_382 | 2015-11-25 01:00 | 2017-07-20 | 0.3 | 0 | 0 | Accept | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 113 | 131 | 153 | 131.6667 | 0.8 | 113 | 131 | 153 | 131.6667 |  | 66.6667 | 1
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Recorder unavailability | Person_604 | 2015-02-21 01:00 | 2017-08-20 01:00 | 0.2 | 0 | 0 | Accept | 0.1 | 0 | 0 | H2 | 4 | Stable | 0.6 | 112 | 123 | 144 | 124.6667 | 0.6 | 112 | 123 | 144 | 124.6667 |  | 50 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 19:00 | 2019-08-20 19:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.5 | 87 | 126 | 160 | 125.1667 | 0.2 | 22 | 48 | 63 | 46.1667 | 83.3333 | 88.8889 | 1 | 52.6667
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.6 | 100 | 121 | 158 | 123.6667 | 0.4 | 13 | 44 | 78 | 44.5 | 72 | 0 | 0 | 43.2
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.7 | 87 | 136 | 148 | 129.8333 | 0.2 | 28 | 53 | 61 | 50.1667 | 47.7391 | 0 | 0 | 28.6435
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 19:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.9 | 102 | 137 | 149 | 133.1667 | 0.2 | 18 | 47 | 63 | 44.8333 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Non-Recurring Engineering higher than expected | Person_510 | 2016-06-01 | 2016-08-20 01:00 | 0.5 | 13.3382 | 6.6691 | Reduce | 0.5 | 13.3382 | 6.6691 | H2 | 4 | Improving | 0.7 | 107 | 126 | 146 | 126.1667 | 0.2 | 17 | 51 | 67 | 48 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | EMC Testing | Person_332 | 2016-04-22 | 2017-08-20 01:00 | 0.35 | 4.8729 | 3.8983 | Accept | 0.2 | 4.8729 | 3.8983 | H2 | 4 | Stable | 0.9 | 99 | 126 | 151 | 125.6667 | 0.9 | 99 | 126 | 151 | 125.6667 | 0 | 42.8571 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_523 | 2015-01-22 01:00 | 2017-08-20 01:00 | 0.35 | 5.3353 | 1.0671 | Accept | 0.2 | 5.3353 | 1.0671 | H2 | 4 | Stable | 0.5 | 119 | 123 | 153 | 127.3333 | 0.5 | 119 | 123 | 153 | 127.3333 | 0 | 42.8571 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-63 | Project_022_RISK-63 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Levy | Person_703 | 2012-04-19 | 2017-08-20 01:00 | 0.8 | 3.5298 | 2.8239 | Exploit | 0.8 | 3.5298 | 2.8239 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-62 | Project_022_RISK-62 | Threat | Project Contingency | Open | H3 | 3 | 8. Operations & Maintenance | Additional Costs from Integration Cost Centre | Person_703 | 2017-03-23 | 2017-05-14 | 0.5 | 7.1754 | 3.5877 | Avoid | 0.292 | 3.5877 | 1.0476 | H3 | 3 | Worsening | [10 empty] | 50 | 41.6 | 0 | 30
2017-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2017-06-21 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.35 | 2.8688 | 1.0041 | H2 | 4 | Stable | 0.9 | 93 | 135 | 158 | 131.8333 | 0.1 | 14 | 45 | 68 | 43.6667 | 22.0253 | 56.25 | 0 | 13.2152
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_332 | 2016-06-23 | 2017-11-19 01:00 | 0.4 | 2.3975 | 2.3975 | Accept | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.7 | 115 | 127 | 144 | 127.8333 | 0.7 | 115 | 127 | 144 | 127.8333 | 100 | 50 | 0 | 60
2017-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2017-08-20 01:00 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 0.65554 | 0.52443 | H2 | 4 | Stable | [10 empty] | 80.45 | 0 | 0 | 48.27
2017-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2017-10-20 01:00 | 0.85 | 25.2325 | 21.4476 | Avoid | 0.08 | 8.5319 | 0.68255 | H2 | 4 | Stable | [10 empty] | 66.187 | 90.5882 | 0 | 39.7122
2017-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2017-10-20 01:00 | 0.7 | 24.1887 | 16.9321 | Reduce | 0.25 | 2.1783 | 0.54459 | H2 | 4 | Stable | 0.8 | 106 | 131 | 150 | 130 | 0.1 | 17 | 43 | 61 | 41.6667 | 90.9944 | 64.2857 | 0 | 54.5966
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | RISK004 | Project_028_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Engineering Changes to be embodied on the Rig | Person_604 | 2017-04-29 | 2019-02-20 01:00 | 0.8 | 12.815 | 2.563 | Accept | 0.8 | 12.815 | 2.563 | H1 | 5 | Stable | 0.5 | 83 | 134 | 159 | 129.6667 | 0.5 | 83 | 134 | 159 | 129.6667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.5 | 89 | 128 | 160 | 126.8333 | 0.2 | 17 | 40 | 67 | 40.6667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-20 22:00 | 2016-08-20 22:00 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.9 | 91 | 140 | 156 | 134.5 | 0.1 | 27 | 59 | 64 | 54.5 | 0 | 16.6667 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 | 2020-08-20 | 0.5 | 7.689 | 2.6911 | Accept | 0.5 | 7.689 | 2.6911 | H2 | 4 | Stable | 0.8 | 104 | 125 | 156 | 126.6667 | 0.8 | 104 | 125 | 156 | 126.6667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Generic Labour Risk Provision | Person_662 | 2015-11-02 | 2018-01-20 | 0.5 | 5.4336 | 1.3584 | Accept | 0.5 | 5.4336 | 1.3584 | H2 | 4 | Stable | 0.9 | 96 | 124 | 151 | 123.8333 | 0.9 | 96 | 124 | 151 | 123.8333 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-095 | Project_008_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Repair of interface units from the Programme | Person_567 | 2017-05-23 | 2018-08-21 | 0.2 | 9.4695 | 1.8939 | Avoid | 0.2 | 9.4695 | 1.8939 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 4.8452 | 1.2113 | Accept | 0.5 | 4.8452 | 1.2113 | H1 | 5 | Stable | 0.8 | 117 | 121 | 159 | 126.6667 | 0.8 | 117 | 121 | 159 | 126.6667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-026 | Project_043_Risk-026 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Equipment Delivery | Person_693 | 2017-04-19 | 2017-07-20 | 0.25 | 3.7878 | 1.1363 | Accept | 0.25 | 3.7878 | 1.1363 | H2 | 4 | Improving | 0.7 | 114 | 138 | 151 | 136.1667 | 0.7 | 114 | 138 | 151 | 136.1667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-080 | Project_008_Risk-080 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Recovery of Costs | Person_565 | 2016-08-21 01:00 | 2017-08-20 01:00 | 0.5 | 23.6737 | 11.8369 | -- | 0.5 | 23.6737 | 11.8369 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Survey costs | Person_618 | 2016-04-22 | 2017-08-20 01:00 | 0.2 | 13.2573 | 2.6515 | Avoid | 0.2 | 13.2573 | 2.6515 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-079 | Project_008_Risk-079 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Regulations Phase 3 and 4 | Person_565 | 2016-10-21 01:00 | 2018-08-21 | 0.25 | 71.9682 | 17.992 | -- | 0.25 | 71.9682 | 17.992 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software issue input | Person_084 | 2016-11-23 01:00 | 2023-02-20 01:00 | 0.4 | 33.9324 | 10.1797 | Accept | 0.2 | 33.9324 | 10.1797 | H2 | 4 | Stable | 0.6 | 105 | 128 | 147 | 127.3333 | 0.6 | 105 | 128 | 147 | 127.3333 | 0 | 50 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-116 | Project_011_Risk-116 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Delays to Qualification | Person_147 | 2017-04-22 | 2017-08-31 01:00 | 0.5 | 0.43243 | 0.21621 | Reduce | 0.5 | 0.43243 | 0.21621 | H1 | 5 | Stable | 0.9 | 116 | 122 | 150 | 125.6667 | 0.3 | 15 | 45 | 70 | 44.1667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-104 | Project_011_Risk-104 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer delayed in providing Custeomr Furnished Equipment | Person_147 | 2016-06-23 | 2017-08-25 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.8 | 113 | 130 | 144 | 129.5 | 0.2 | 36 | 56 | 74 | 55.6667 |  | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Volume of production tools and Jigs | Person_084 | 2016-11-23 01:00 | 2021-11-23 01:00 | 0.35 | 0.30685 | 0.06137 | Accept | 0.2 | 0.30685 | 0.06137 | H2 | 4 | Stable | 0.5 | 82 | 134 | 151 | 128.1667 | 0.5 | 82 | 134 | 151 | 128.1667 | 0 | 42.8571 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 0.3 | 0.51931 | 0.15579 | -- | 0.15 | 0.51931 | 0.077897 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 0.2 | 0.55005 | 0.11001 | Avoid | 0.2 | 0.55005 | 0.11001 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2017-09-20 01:00 | 2018-04-21 | 0.15 | 0.28639 | 0.042959 | -- | 0.15 | 0.28639 | 0.042959 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-08-20 01:00 | 0.2 | 0.24207 | 0.048414 | -- | 0.2 | 0.24207 | 0.048414 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 0.2 | 1.661 | 0.33219 | Reduce | 0.2 | 1.661 | 0.33219 | H2 | 4 | Stable | 0.6 | 99 | 125 | 157 | 126 | 0.2 | 20 | 51 | 68 | 48.6667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2017-10-21 01:00 | 2018-08-21 | 0.4 | 1.2444 | 0.49778 | Reduce | 0.4 | 1.2444 | 0.49778 | H2 | 4 | Stable | 0.7 | 111 | 136 | 151 | 134.3333 | 0.4 | 19 | 43 | 67 | 43 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK040 | Project_017_RISK040 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Upgrades | Person_084 | 2016-09-30 01:00 | 2016-12-18 01:00 | 0.35 | 0.16195 | 0.072876 | Accept | 0.35 | 0.16195 | 0.072876 | H2 | 4 | Stable | 0.9 | 96 | 130 | 158 | 129 | 0.9 | 96 | 130 | 158 | 129 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 01:00 | 2017-08-23 01:00 | 0.45 | 0.41947 | 0.18876 | Reduce | 0.45 | 0.41944 | 0.18875 | H2 | 4 | Stable | 0.5 | 114 | 137 | 145 | 134.5 | 0.1 | 10 | 57 | 74 | 52 | 0.0067461 | 0 | 0 | 0.0040477
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-10-19 01:00 | 2018-08-21 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.5 | 91 | 136 | 142 | 129.5 | 0.3 | 12 | 43 | 77 | 43.5 |  | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Pick up and Drop off of Software Resource | Person_230 | 2017-12-19 01:00 | 2018-02-19 01:00 | 0.4 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 0.2 | 0.12388 | 0.024775 | Reduce | 0.2 | 0.12388 | 0.024775 | H2 | 4 | Stable | 0.9 | 85 | 129 | 157 | 126.3333 | 0.4 | 32 | 51 | 65 | 50.1667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 0.4 | 0.51141 | 0.20457 | Avoid | 0.4 | 0.51141 | 0.20457 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK006 | Project_041_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Change of Component material | Person_468 | 2016-11-20 01:00 | 2018-11-20 01:00 | 0.4 | 0.49834 | 0.12459 | Accept | 0.4 | 0.49834 | 0.12459 | H2 | 4 | Worsening | 0.5 | 109 | 126 | 145 | 126.3333 | 0.5 | 109 | 126 | 145 | 126.3333 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.2 | 0.10171 | 0.020343 | -- | 0.2 | 0.10171 | 0.020343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 0.3 | 0.28639 | 0.085917 | Reduce | 0.3 | 0.28639 | 0.085917 | H2 | 4 | Stable | 0.8 | 116 | 133 | 152 | 133.3333 | 0.1 | 4 | 52 | 71 | 47.1667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 2. Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 0.25 | 0 | 0 | -- | 0.25 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2017-10-21 01:00 | 2018-05-21 | 0.4 | 0.1699 | 0.067961 | -- | 0.4 | 0.1699 | 0.067961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 0.3 | 0.10626 | 0.031878 | -- | 0.3 | 0.01932 | 0.005796 | H3 | 3 | Stable | [10 empty] | 81.8181 | 0 | 0 | 49.0909
2017-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2017-05-22 | 0.41 | 3.1344 | 1.5672 | Accept | 0.41 | 3.1344 | 1.5672 | H2 | 4 | Stable | 0.8 | 90 | 131 | 158 | 128.6667 | 0.8 | 90 | 131 | 158 | 128.6667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 01:00 | 2019-05-14 | 0.5 | 4.3921 | 2.196 | Reduce | 0.3 | 4.3921 | 1.3176 | H1 | 5 | Stable | 0.6 | 119 | 125 | 156 | 129.1667 | 0.4 | 29 | 40 | 77 | 44.3333 | 0 | 40 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK019 | Project_042_RISK019 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2016-05-23 | 2021-05-22 | 0.3 | 7.5153 | 2.2546 | -- | 0.3 | 7.5153 | 2.2546 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 0.25 | 1.8788 | 0.28182 | Accept | 0.25 | 1.8788 | 0.28182 | H3 | 3 | Stable | 0.9 | 104 | 140 | 158 | 137 | 0.9 | 104 | 140 | 158 | 137 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | More issues during Qualification including additional PRs | Person_147 | 2017-04-22 | 2017-11-04 01:00 | 0.35 | 9.3941 | 1.8788 | Accept | 0.35 | 9.3941 | 1.8788 | H1 | 5 | Stable | 0.8 | 87 | 134 | 158 | 130.1667 | 0.8 | 87 | 134 | 158 | 130.1667 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 0.61 | 1.1273 | 0.22546 | Accept | 0.61 | 1.1273 | 0.22546 | H1 | 5 | Stable | 0.5 | 98 | 128 | 152 | 127 | 0.5 | 98 | 128 | 152 | 127 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-19 23:00 | 0.05 | 0.65759 | 0.098638 | Accept | 0.05 | 0.65759 | 0.098638 | H2 | 4 | Stable | 0.9 | 111 | 130 | 146 | 129.5 | 0.9 | 111 | 130 | 146 | 129.5 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 0.8 | 6.7638 | 1.3528 | Accept | 0.6 | 6.7638 | 1.3528 | H1 | 5 | Stable | 0.8 | 88 | 134 | 145 | 128.1667 | 0.8 | 88 | 134 | 145 | 128.1667 | 0 | 25 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-26 23:00 | 2016-08-19 23:00 | 0.1 | 0.93941 | 0.14091 | Accept | 0.1 | 0.93941 | 0.14091 | H2 | 4 | Stable | 0.8 | 105 | 129 | 153 | 129 | 0.8 | 105 | 129 | 153 | 129 | 0 | 0 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-18 23:00 | 0.2 | 2.8182 | 0.56365 | Accept | 0.2 | 2.8182 | 0.56365 | H3 | 3 | Improving | 0.9 | 97 | 122 | 158 | 123.8333 | 0.9 | 97 | 122 | 158 | 123.8333 | 0 | 0 | 1 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 0.3 | 2.5834 | 0.64585 | Accept | 0.4 | 2.5834 | 0.64585 | H3 | 3 | Stable | 0.9 | 101 | 138 | 149 | 133.6667 | 0.9 | 101 | 138 | 149 | 133.6667 | 0 | -33.3333 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-21 23:00 | 2016-11-19 23:00 | 0.25 | 1.1273 | 0.45092 | Accept | 0.1 | 1.1273 | 0.45092 | H3 | 3 | Stable | 0.5 | 85 | 137 | 142 | 129.1667 | 0.5 | 85 | 137 | 142 | 129.1667 | 0 | 60 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-19 23:00 | 0.25 | 9.3941 | 0.93941 | Accept | 0.15 | 9.3941 | 0.93941 | H3 | 3 | Stable | 0.9 | 97 | 136 | 150 | 131.8333 | 0.9 | 97 | 136 | 150 | 131.8333 | 0 | 40 | 1 | 1.2
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Governance and Export Rules | Person_455 | 2016-05-23 | 2021-05-22 | 0.25 | 0.93941 | 0.23485 | Transfer | 0.25 | 0.93941 | 0.23485 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 0.61 | 2.1606 | 0.43213 | Accept | 0.61 | 2.1606 | 0.43213 | H1 | 5 | Stable | 0.7 | 87 | 123 | 141 | 120 | 0.7 | 87 | 123 | 141 | 120 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Additional minor point releases | Person_228 | 2016-05-23 | 2017-10-19 01:00 | 0.5 | 11.9444 | 5.9722 | Reduce | 0.25 | 11.9444 | 2.9861 | H2 | 4 | Stable | 0.7 | 89 | 140 | 156 | 134.1667 | 0.4 | 13 | 59 | 74 | 53.8333 | 0 | 50 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_228 | 2016-05-23 | 2017-02-19 01:00 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.9 | 80 | 137 | 151 | 129.8333 | 0.2 | 14 | 42 | 67 | 41.5 | 0 | 50 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_413 | 2015-11-21 01:00 | 2018-11-20 01:00 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.7 | 111 | 135 | 155 | 134.3333 | 0.3 | 11 | 54 | 67 | 49 | 0 | 5 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.8 | 2.8043 | 2.2435 | Reduce | 0.45 | 2.8043 | 1.2619 | H1 | 5 | Stable | 0.7 | 89 | 131 | 147 | 126.6667 | 0.2 | 30 | 57 | 75 | 55.5 | 0 | 43.75 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK167 | Project_024_RISK167 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Customer not providing the information needed | Person_710 | 2016-08-21 01:00 | 2018-02-19 01:00 | 0.5 | 9.971 | 4.9855 | Reduce | 0.3 | 9.971 | 2.9913 | H1 | 5 | Worsening | 0.5 | 96 | 140 | 148 | 134 | 0.1 | 9 | 48 | 74 | 45.8333 | 0 | 40 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK306(028) | Project_024_RISK306(028) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | HW repairs required on units | Person_119 | 2016-11-19 01:00 | 2018-11-20 01:00 | 0.3 | 2.813 | 0.8439 | Reduce | 0.2 | 2.813 | 0.5626 | H2 | 4 | Stable | 0.5 | 97 | 128 | 142 | 125.1667 | 0.1 | 18 | 40 | 74 | 42 | 0 | 33.3333 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2017-05-22 | 0.41 | 5.1932 | 1.2983 | Accept | 0.41 | 5.1932 | 1.2983 | H2 | 4 | Stable | 0.8 | 120 | 126 | 145 | 128.1667 | 0.8 | 120 | 126 | 145 | 128.1667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-20 22:00 | 2019-08-20 | 0.5 | 5.1932 | 1.558 | Accept | 0.5 | 5.1932 | 1.558 | H2 | 4 | Stable | 0.8 | 82 | 122 | 153 | 120.5 | 0.8 | 82 | 122 | 153 | 120.5 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.2 | 5.3577 | 1.3394 | Accept | 0.2 | 5.3577 | 1.3394 | H3 | 3 | Stable | 0.6 | 95 | 132 | 145 | 128 | 0.6 | 95 | 132 | 145 | 128 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK226 | Project_024_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Late Evidences delay Certification delivery | Person_710 | 2017-04-30 | 2017-12-21 01:00 | 0.4 | 3.9468 | 1.5787 | Reduce | 0.2 | 3.9468 | 0.78937 | H2 | 4 | Worsening | 0.9 | 98 | 136 | 144 | 131 | 0.1 | 14 | 40 | 68 | 40.3333 | 0 | 50 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK302(024) | Project_024_RISK302(024) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | On time provision of platform units | Person_119 | 2016-11-19 01:00 | 2019-05-23 | 0.25 | 2.3889 | 0.59722 | Reduce | 0.15 | 2.3889 | 0.35833 | H2 | 4 | Stable | 0.7 | 94 | 128 | 144 | 125 | 0.1 | 8 | 54 | 69 | 48.8333 | 0 | 40 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK227 | Project_024_RISK227 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Data Bunching | Person_710 | 2017-03-23 | 2017-09-19 01:00 | 0.4 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H1 | 5 | Stable | 0.7 | 119 | 139 | 147 | 137 | 0.4 | 35 | 42 | 77 | 46.6667 |  | 25 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 4.8297 | 1.6904 | Accept | 0.35 | 4.8297 | 1.6904 | H3 | 3 | Stable | 0.8 | 100 | 125 | 154 | 125.6667 | 0.8 | 100 | 125 | 154 | 125.6667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.25 | 5.1067 | 1.0213 | Accept | 0.25 | 5.1067 | 1.0213 | H3 | 3 | Stable | 0.7 | 87 | 128 | 157 | 126 | 0.7 | 87 | 128 | 157 | 126 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-085 | Project_008_SER-085 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Insufficient LOE to manage the supply chain with reducing number of spares | Person_639 | 2017-04-22 | 2018-08-21 | 0.25 | 0.5626 | 0.19691 | Accept | 0.25 | 0.5626 | 0.19691 | H3 | 3 | Improving | 0.5 | 119 | 140 | 141 | 136.6667 | 0.5 | 119 | 140 | 141 | 136.6667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-090 | Project_008_Risk-090 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Demands but not provisioned | Person_639 | 2017-04-22 | 2018-08-21 | 0.3 | 4.1546 | 4.1546 | Accept | 0.3 | 21.1623 | 21.1623 | H3 | 3 | Stable | 0.8 | 102 | 125 | 158 | 126.6667 | 0.8 | 102 | 125 | 158 | 126.6667 | -409.375 | 0 | 0 | -245.625
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 0.45 | 3.9728 | 1.3905 | Accept | 0.45 | 3.9728 | 1.3905 | H2 | 4 | Stable | 0.6 | 109 | 139 | 154 | 136.5 | 0.6 | 109 | 139 | 154 | 136.5 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK225 | Project_024_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | More testing required as a result compliance to Platform Risk | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 5.6866 | 2.8433 | Reduce | 0.3 | 5.6866 | 1.706 | H2 | 4 | Stable | 0.8 | 81 | 125 | 145 | 121 | 0.2 | 23 | 40 | 64 | 41.1667 | 0 | 40 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.7 | 93 | 126 | 144 | 123.5 | 0.2 | 37 | 53 | 70 | 53.1667 | 0 | 60 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_288 | 2017-02-22 01:00 | 2017-11-19 01:00 | 0.3 | 19.9938 | 5.9981 | Reduce | 0.1 | 19.9938 | 1.9994 | H3 | 3 | Improving | 0.5 | 98 | 124 | 145 | 123.1667 | 0.4 | 13 | 47 | 73 | 45.6667 | 0 | 66.6667 | 1 | 2
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.5 | 3.843 | 1.9215 | H1 | 5 | Stable | 0.9 | 93 | 136 | 159 | 132.6667 | 0.4 | 10 | 57 | 68 | 51 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Overland performance | Person_075 | 2016-06-23 | 2017-11-19 01:00 | 0.1 | 1.6835 | 0.16835 | Reduce | 0.1 | 3.5011 | 0.35011 | H3 | 3 | Improving | 0.7 | 86 | 124 | 152 | 122.3333 | 0.2 | 17 | 52 | 64 | 48.1667 | -107.9692 | 0 | 1 | -64.7815
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_565 | 2018-05-22 | 2018-08-21 | 0.25 | 2.7146 | 2.7146 | Accept | 0.25 | 2.7146 | 2.7146 | H3 | 3 | Stable | 0.9 | 80 | 136 | 148 | 128.6667 | 0.9 | 80 | 136 | 148 | 128.6667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK256 | Project_024_RISK256 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unable to meet spare capacity requirement | Person_119 | 2016-07-21 | 2018-01-21 01:00 | 0.8 | 0.12983 | 0.10386 | Reduce | 0.05 | 0.12983 | 0.0064915 | H3 | 3 | Stable | 0.9 | 117 | 136 | 159 | 136.6667 | 0.4 | 9 | 56 | 77 | 51.6667 | 0 | 93.75 | 1 | 2.8125
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Lack of Spares Availability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 0.3 | 15.5796 | 6.2318 | Accept | 0.3 | 15.5796 | 6.2318 | H3 | 3 | Stable | 0.5 | 89 | 129 | 154 | 126.5 | 0.5 | 89 | 129 | 154 | 126.5 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Performance (collector opportunity) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.3814 | 26.127 | 9.9648 | -- | 0.4132 | 26.127 | 10.7957 | H1 | 5 | Stable | [10 empty] | 0 | -8.3377 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.3 | 20.8767 | 6.263 | H1 | 5 | Stable | 0.6 | 87 | 122 | 142 | 119.5 | 0.1 | 35 | 41 | 75 | 45.6667 | 50 | 25 | 0 | 30
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.493 | 58.1898 | 28.6876 | Reduce | 0.32036 | 40.4161 | 12.9477 | H1 | 5 | Worsening | 0.5 | 105 | 125 | 145 | 125 | 0.1 | 19 | 49 | 69 | 47.3333 | 30.5444 | 35.0183 | 0 | 18.3266
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK308 | Project_024_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System robustness and resilience | Person_774 | 2017-04-06 | 2018-06-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.1 | 2.5966 | 0.25966 | H3 | 3 | Stable | 0.9 | 112 | 122 | 150 | 125 | 0.1 | 15 | 47 | 72 | 45.8333 | 58.3333 | 66.6667 | 1 | 37
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK312 | Project_024_RISK312 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Built-in Test not fit for purpose | Person_774 | 2017-02-25 01:00 | 2018-05-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.2 | 9.8671 | 1.9734 | H2 | 4 | Stable | 0.5 | 108 | 136 | 144 | 132.6667 | 0.2 | 29 | 48 | 66 | 47.8333 | -58.3333 | 33.3333 | 0 | -35
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-148 | Project_020_Risk-148 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs non-available items | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.3 | 14.9935 | 4.498 | Reduce | 0.3 | 1.1374 | 0.34121 | H2 | 4 | Stable | 0.9 | 109 | 130 | 158 | 131.1667 | 0.3 | 9 | 55 | 78 | 51.1667 | 92.4143 | 0 | 0 | 55.4486
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-22 01:00 | 2017-05-22 | 0.25 | 7.4225 | 1.8556 | Reduce | 0.1 | 2.0081 | 0.20081 | H3 | 3 | Stable | 0.5 | 101 | 121 | 147 | 122 | 0.2 | 18 | 47 | 68 | 45.6667 | 72.9455 | 60 | 0 | 43.7673
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 2.2492 | 0.8997 | H2 | 4 | Stable | 0.5 | 113 | 130 | 159 | 132 | 0.4 | 14 | 46 | 61 | 43.1667 | 43.1818 | 20 | 0 | 25.9091
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 0.2 | 18.6688 | 3.7338 | Accept | 0.2 | 14.6039 | 0.7302 | H2 | 4 | Stable | 0.7 | 83 | 136 | 144 | 128.5 | 0.7 | 83 | 136 | 144 | 128.5 | 21.7735 | 0 | 0 | 13.0641
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-147 | Project_020_Risk-147 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component taking longer to refurbish in country | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.6 | 6.7477 | 4.0486 | Reduce | 0.6 | 0.74972 | 0.44983 | H2 | 4 | Stable | 0.6 | 104 | 128 | 160 | 129.3333 | 0.3 | 39 | 49 | 77 | 52 | 88.8893 | 0 | 0 | 53.3336
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_703 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 5.0983 | 0.76474 | H3 | 3 | Stable | 0.6 | 84 | 128 | 143 | 123.1667 | 0.3 | 24 | 52 | 75 | 51.1667 | 19.0479 | 70 | 1 | 13.5287
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.1 | 53.0293 | 5.3029 | Reduce | 0.1 | 53.0293 | 5.3029 | H3 | 3 | Worsening | 0.5 | 114 | 136 | 150 | 134.6667 | 0.2 | 36 | 44 | 65 | 46.1667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 0.25 | 0.20788 | 0.068599 | Accept | 0.25 | 0.052336 | 0.0057569 | H3 | 3 | Stable | 0.8 | 116 | 130 | 145 | 130.1667 | 0.8 | 116 | 130 | 145 | 130.1667 | 74.8236 | 0 | 0 | 44.8942
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.1 | 7.7469 | 0.77469 | Reduce | 0.1 | 7.7469 | 0.77469 | H3 | 3 | Stable | 0.9 | 104 | 138 | 158 | 135.6667 | 0.3 | 3 | 43 | 65 | 40 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | More issues during Qualification including additional PRs | Person_147 | 2017-07-26 | 2017-11-04 01:00 | 0.35 | 11.3437 | 0.56718 | Accept | 0.35 | 11.3437 | 0.56718 | H1 | 5 | Stable | 0.7 | 103 | 136 | 141 | 131.3333 | 0.7 | 103 | 136 | 141 | 131.3333 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 0.5 | 0.11976 | 0.0059882 | Accept | 0.5 | 0.11976 | 0.0059882 | H2 | 4 | Stable | 0.9 | 107 | 126 | 155 | 127.6667 | 0.9 | 107 | 126 | 155 | 127.6667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 0.5 | 0.59882 | 0.059882 | Accept | 0.5 | 0.59882 | 0.059882 | H2 | 4 | Stable | 0.8 | 107 | 132 | 144 | 129.8333 | 0.8 | 107 | 132 | 144 | 129.8333 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-125 | Project_043_Risk-125 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | IOC Delayed due to a number of factors (Marching Customer Risk) | Person_084 | 2014-09-13 01:00 | 2018-03-21 | 0.5 | 1.9362 | 0.96809 | -- | 0.3 | 1.9362 | 0.58086 | H2 | 4 | Stable | [10 empty] | 0 | 40 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 0.59882 | 0.14971 | Accept | 0.5 | 0.59882 | 0.14971 | H2 | 4 | Stable | 0.8 | 92 | 135 | 142 | 129 | 0.8 | 92 | 135 | 142 | 129 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suppliers | Person_455 | 2016-05-23 | 2021-05-22 | 0.15 | 0.81199 | 0.081199 | Accept | 0.15 | 0.81199 | 0.0406 | H2 | 4 | Stable | 0.7 | 81 | 124 | 142 | 119.8333 | 0.7 | 81 | 124 | 142 | 119.8333 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares | Person_455 | 2016-05-23 | 2021-05-22 | 0.2 | 0 | 0 | Accept | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.8 | 118 | 128 | 156 | 131 | 0.8 | 118 | 128 | 156 | 131 |  | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PEN Testing Security Features | Person_604 | 2015-04-11 | 2017-10-20 01:00 | 0.3 | 5.4553 | 1.6366 | Reduce | 0.15 | 5.252 | 0.7878 | H2 | 4 | Stable | 0.5 | 113 | 129 | 144 | 128.8333 | 0.4 | 21 | 42 | 74 | 43.8333 | 3.7267 | 50 | 0 | 2.236
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Local customer Engineers in country | Person_455 | 2016-05-23 | 2021-05-22 | 0.1 | 20.3303 | 7.1156 | Accept | 0.1 | 18.975 | 1.8975 | H2 | 4 | Stable | 0.8 | 108 | 126 | 141 | 125.5 | 0.8 | 108 | 126 | 141 | 125.5 | 6.6667 | 0 | 0 | 4
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Cable and connectors | Person_499 | 2015-11-21 01:00 | 2019-04-10 | 0.45 | 0.41338 | 0.18602 | Reduce | 0.2 | 0.41338 | 0.082677 | H2 | 4 | Stable | 0.6 | 107 | 140 | 148 | 135.8333 | 0.3 | 20 | 48 | 60 | 45.3333 | 0 | 55.5556 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | FOC Acceptance | Person_500 | 2015-11-21 01:00 | 2017-12-20 01:00 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.3 | 8.471 | 2.5413 | H2 | 4 | Stable | 0.8 | 102 | 133 | 146 | 130 | 0.1 | 9 | 41 | 74 | 41.1667 | -99.9999 | 14.2857 | 0 | -59.9999
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence | Person_455 | 2016-05-23 | 2021-05-22 | 0.3 | 8.8098 | 3.0834 | Accept | 0.3 | 8.8098 | 1.762 | H2 | 4 | Stable | 0.6 | 94 | 121 | 144 | 120.3333 | 0.6 | 94 | 121 | 144 | 120.3333 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables | Person_455 | 2016-05-23 | 2021-05-22 | 0.2 | 0.40661 | 0.16264 | Accept | 0.2 | 0.40661 | 0.081321 | H2 | 4 | Stable | 0.8 | 119 | 130 | 152 | 131.8333 | 0.8 | 119 | 130 | 152 | 131.8333 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Furnished Equipmnet Condition | Person_132 | 2015-04-27 | 2019-04-10 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.6 | 90 | 138 | 147 | 131.5 | 0.2 | 12 | 49 | 63 | 45.1667 |  | 62.5 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2021-05-22 | 0.2 | 6.6751 | 6.0076 | Accept | 0.2 | 16.2643 | 8.1321 | H2 | 4 | Stable | 0.5 | 87 | 131 | 156 | 127.8333 | 0.5 | 87 | 131 | 156 | 127.8333 | -143.6548 | 0 | 0 | -86.1929
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2021-05-22 | 0.15 | 0 | 0 | Accept | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.5 | 86 | 121 | 141 | 118.5 | 0.5 | 86 | 121 | 141 | 118.5 |  | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-020 | Project_028_Risk-020 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | (Project Management WP) Availability of Customer Furnished Equipmnet for modification | Person_604 | 2015-05-24 | 2019-02-20 01:00 | 0.25 | 0 | 0 | Avoid | 0.05 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 80 | 1
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2021-05-22 | 0.2 | 5.4729 | 4.3783 | Accept | 0.2 | 4.6191 | 3.6952 | H2 | 4 | Stable | 0.7 | 100 | 132 | 153 | 130.1667 | 0.7 | 100 | 132 | 153 | 130.1667 | 15.6018 | 0 | 0 | 9.3611
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unforseen and substantial increase in Repairs workload during new build production period. | Person_515 | 2017-10-23 01:00 | 2017-11-19 01:00 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.03 | 1.5434 | 0.046303 | H3 | 3 | Stable | 0.9 | 98 | 139 | 149 | 133.8333 | 0.3 | 28 | 59 | 69 | 55.5 | 0 | 90 | 1 | 2.7
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK007 | Project_041_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Advanced production of products using a Qual. standard component rather than a Prod. standard | Person_547 | 2017-10-21 01:00 | 2019-05-23 | 0.49 | 1.2862 | 0.63024 | Reduce | 0.2 | 1.2862 | 0.25724 | H3 | 3 | Stable | 0.7 | 119 | 122 | 142 | 124.8333 | 0.1 | 17 | 42 | 62 | 41.1667 | 0 | 59.1837 | 1 | 1.7755
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_693 | 2017-05-23 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.9 | 85 | 140 | 143 | 131.3333 | 0.3 | 1 | 40 | 60 | 36.8333 | 0 | 50 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2017-04-22 | 2018-05-22 | 0.75 | 10.7184 | 8.0388 | Reduce | 0.15 | 5.3592 | 0.80388 | H3 | 3 | Stable | 0.7 | 115 | 138 | 155 | 137 | 0.3 | 37 | 50 | 70 | 51.1667 | 50 | 80 | 1 | 32.4
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Transport Routes | Person_455 | 2016-05-23 | 2021-05-22 | 0.15 | 1.9722 | 0.98609 | Accept | 0.15 | 1.9722 | 0.98609 | H2 | 4 | Stable | 0.5 | 87 | 125 | 145 | 122 | 0.5 | 87 | 125 | 145 | 122 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Internal Quality Issues | Person_251 | 2016-05-23 | 2021-05-22 | 0.2 | 2.5081 | 1.2541 | Accept | 0.2 | 2.5081 | 1.2541 | H2 | 4 | Stable | 0.6 | 114 | 126 | 154 | 128.6667 | 0.6 | 114 | 126 | 154 | 128.6667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2017-05-23 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.05 | 0.68598 | 0.034299 | H3 | 3 | Stable | 0.7 | 117 | 138 | 147 | 136 | 0.2 | 24 | 47 | 75 | 47.8333 | 0 | 80 | 1 | 2.4
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs | Person_455 | 2016-05-23 | 2021-05-22 | 0.25 | 0.45017 | 0.2701 | Accept | 0.25 | 0.45017 | 0.13505 | H2 | 4 | Stable | 0.5 | 97 | 121 | 147 | 121.3333 | 0.5 | 97 | 121 | 147 | 121.3333 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Country Stability | Person_455 | 2016-05-23 | 2021-05-22 | 0.4 | 3.7514 | 0.37514 | Accept | 0.4 | 3.7514 | 0.37514 | H2 | 4 | Stable | 0.5 | 104 | 125 | 148 | 125.3333 | 0.5 | 104 | 125 | 148 | 125.3333 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2017-05-23 | 2017-12-21 01:00 | 0.1 | 21.8655 | 2.1865 | Reduce | 0.01 | 21.8655 | 0.21865 | H2 | 4 | Stable | 0.7 | 90 | 126 | 149 | 123.8333 | 0.2 | 30 | 44 | 63 | 44.8333 | 0 | 90 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2017-05-23 | 2018-11-20 01:00 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Stable | 0.8 | 106 | 124 | 144 | 124.3333 | 0.3 | 1 | 48 | 62 | 42.5 | 0 | 60 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Unidentified CRs and concessions | Person_693 | 2017-04-22 | 2017-09-20 01:00 | 0.5 | 1.2005 | 0.60023 | Reduce | 0.15 | 0.51019 | 0.076529 | H3 | 3 | Stable | 0.5 | 101 | 121 | 159 | 124 | 0.2 | 6 | 48 | 63 | 43.5 | 57.5001 | 70 | 1 | 36.6001
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_238 | 2017-04-22 | 2018-05-22 | 0.25 | 3.3227 | 0.83067 | Reduce | 0.05 | 3.3227 | 0.16613 | H3 | 3 | Stable | 0.9 | 95 | 138 | 147 | 132.3333 | 0.3 | 20 | 46 | 79 | 47.1667 | 0 | 80 | 1 | 2.4
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_693 | 2017-05-23 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.1 | 0.77172 | 0.077172 | H3 | 3 | Worsening | 0.7 | 84 | 127 | 145 | 122.8333 | 0.1 | 25 | 43 | 73 | 45 | 0 | 60 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2021-05-22 | 0.1 | 1.7492 | 0.17492 | Accept | 0.1 | 1.7492 | 0.17492 | H2 | 4 | Stable | 0.9 | 102 | 138 | 154 | 134.6667 | 0.9 | 102 | 138 | 154 | 134.6667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_693 | 2017-05-23 | 2018-11-20 01:00 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.08 | 6.431 | 0.51448 | H3 | 3 | Improving | 0.7 | 111 | 139 | 146 | 135.5 | 0.1 | 16 | 51 | 76 | 49.3333 | -47.0588 | 46.6667 | 1 | -26.8353
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2021-05-22 | 0.2 | 0.21008 | 0.10504 | Accept | 0.2 | 0.21008 | 0.05252 | H2 | 4 | Stable | 0.6 | 96 | 124 | 147 | 123.1667 | 0.6 | 96 | 124 | 147 | 123.1667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Reduce touch labour if Production readiness programme successful | Person_238 | 2017-05-23 | 2017-10-21 01:00 | 0.3 | 1.5606 | 0.46818 | Exploit | 0.5 | 1.5606 | 0.7803 | H2 | 4 | Stable | [10 empty] | 0 | -66.6667 | 0 | 0
2017-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-03-22 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.5 | 89 | 136 | 150 | 130.5 | 0.2 | 25 | 57 | 71 | 54 | 0 | 25 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment environmental failure | Person_710 | 2016-05-23 | 2017-09-19 01:00 | 0.3 | 3.4415 | 1.3766 | Accept | 0.3 | 3.4415 | 1.3766 | H1 | 5 | Improving | 0.6 | 117 | 129 | 155 | 131.3333 | 0.6 | 117 | 129 | 155 | 131.3333 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Qual failure | Person_710 | 2016-06-22 | 2017-06-22 | 0.4 | 8.0582 | 2.4175 | Accept | 0.4 | 8.0582 | 2.4175 | H1 | 5 | Improving | 0.7 | 106 | 128 | 144 | 127 | 0.7 | 106 | 128 | 144 | 127 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK300(020) | Project_024_RISK300(020) | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Travel and onsite support | Person_119 | 2017-01-20 01:00 | 2018-04-21 | 0.25 | 0 | 0 | Accept | 0.25 | 0 | 0 | H3 | 3 | Stable | 0.6 | 113 | 124 | 153 | 127 | 0.6 | 113 | 124 | 153 | 127 |  | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK304(026) | Project_024_RISK304(026) | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | complex integration | Person_119 | 2016-10-20 01:00 | 2018-01-20 01:00 | 0.4 | 0.5596 | 0.05596 | Accept | 0.4 | 0.5596 | 0.05596 | H1 | 5 | Worsening | 0.5 | 109 | 122 | 151 | 124.6667 | 0.5 | 109 | 122 | 151 | 124.6667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK303(025) | Project_024_RISK303(025) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in contract value from our supplier | Person_119 | 2016-10-20 01:00 | 2019-05-23 | 0.25 | 3.6174 | 1.8087 | Accept | 0.25 | 3.6172 | 0.72345 | H2 | 4 | Stable | 0.9 | 89 | 134 | 158 | 130.5 | 0.9 | 89 | 134 | 158 | 130.5 | 0.0051359 | 0 | 0 | 0.0030815
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK305(027) | Project_024_RISK305(027) | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Customer Furnished Equipment not available on time | Person_119 | 2016-11-19 01:00 | 2019-05-23 | 0.3 | 2.3503 | 0.47006 | Accept | 0.3 | 2.3503 | 0.47006 | H1 | 5 | Stable | 0.8 | 95 | 125 | 144 | 123.1667 | 0.8 | 95 | 125 | 144 | 123.1667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK296(013) | Project_024_RISK296(013) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Qualification/Certification Requirements flowdown | Person_119 | 2016-10-20 01:00 | 2017-08-20 01:00 | 0.25 | 4.4768 | 2.2384 | Accept | 0.25 | 4.4768 | 2.2384 | H2 | 4 | Worsening | 0.8 | 93 | 135 | 143 | 129.3333 | 0.8 | 93 | 135 | 143 | 129.3333 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before part b finished | Person_119 | 2016-10-20 01:00 | 2018-04-21 | 0.35 | 76.7807 | 3.839 | Accept | 0.35 | 76.7807 | 3.839 | H2 | 4 | Worsening | 0.9 | 102 | 122 | 145 | 122.5 | 0.9 | 102 | 122 | 145 | 122.5 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK298(016) | Project_024_RISK298(016) | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Environmental testing required | Person_119 | 2016-10-20 01:00 | 2017-10-20 01:00 | 0.2 | 23.5255 | 11.7628 | Accept | 0.2 | 23.5255 | 11.7628 | H2 | 4 | Stable | 0.6 | 93 | 130 | 153 | 127.6667 | 0.6 | 93 | 130 | 153 | 127.6667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK299(018) | Project_024_RISK299(018) | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Additional support hours | Person_119 | 2017-01-20 01:00 | 2018-04-21 | 0.35 | 60.4367 | 3.0218 | Accept | 0.35 | 60.4367 | 3.0218 | H3 | 3 | Stable | 0.9 | 101 | 125 | 155 | 126 | 0.9 | 101 | 125 | 155 | 126 | 0 | 0 | 1 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.8 | 114 | 131 | 154 | 132 | 0.4 | 11 | 57 | 70 | 51.5 | 25.8065 | 20 | 0 | 15.4839
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 12:00 | 2019-08-20 12:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 12:00 | 2019-08-20 12:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 12:00 | 2019-08-20 12:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 12:00 | 2019-08-20 12:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 12:00 | 2019-08-20 12:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 0.5 | 9.2728 | 4.6364 | Reduce | 0.15 | 9.2728 | 1.3909 | H2 | 4 | Stable | 0.7 | 98 | 126 | 157 | 126.5 | 0.1 | 12 | 42 | 78 | 43 | 0 | 70 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R008 | Project_016_Risk--R008 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Additional Travel & Subsistence | Person_574 | 2016-01-13 | 2019-05-23 | 0.4 | 8.9019 | 3.5608 | Reduce | 0.25 | 8.9019 | 2.2255 | H3 | 3 | Stable | 0.9 | 110 | 135 | 157 | 134.5 | 0.4 | 33 | 41 | 78 | 45.8333 | 0 | 37.5 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 | 2017-08-20 | 0.3 | 8.7814 | 2.6344 | Reduce | 0.15 | 8.7832 | 1.3175 | H3 | 3 | Stable | 0.5 | 83 | 127 | 158 | 124.8333 | 0.3 | 5 | 50 | 69 | 45.6667 | -0.021119 | 50 | 1 | 1.4873
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R009 | Project_016_Risk--R009 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer maybe difficult to work with | Person_697 | 2016-04-02 | 2019-08-01 | 0.6 | 23.9549 | 14.3729 | Reduce | 0.43864 | 23.8312 | 10.4533 | H2 | 4 | Stable | 0.9 | 110 | 125 | 153 | 127.1667 | 0.3 | 19 | 43 | 77 | 44.6667 | 0.51612 | 26.8938 | 0 | 0.30967
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Delay of processing | Person_306 | 2016-04-02 | 2017-03-21 | 0.15 | 26.3497 | 3.9525 | Reduce | 0.15 | 13.1767 | 1.9765 | H3 | 3 | Stable | 0.9 | 102 | 127 | 156 | 127.6667 | 0.3 | 27 | 40 | 61 | 41.3333 | 49.993 | 0 | 1 | 29.9958
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) at the System level on product platform - performed by 3rd parties | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.41 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -2.5 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Sub-system / product system accreditation hindered by Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.1 | 0.25667 | 0.025667 | Transfer | 0.1 | 0.25667 | 0.025667 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 1.078 | 0.43121 | Reduce | 0.4 | 1.4673 | 0.58692 | H2 | 4 | Improving | 0.6 | 100 | 138 | 154 | 134.3333 | 0.4 | 38 | 57 | 76 | 57 | -36.1112 | 0 | 0 | -21.6667
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2018-03-21 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2017-11-20 01:00 | 0.6 | 0.89835 | 0.53901 | Transfer | 0.6 | 0.89835 | 0.53901 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 0.35 | 0.85557 | 0.29945 | Reduce | 0.35 | 1.9208 | 0.67227 | H2 | 4 | Stable | 0.9 | 80 | 127 | 150 | 123 | 0.3 | 11 | 42 | 74 | 42.1667 | -124.5001 | 0 | 0 | -74.7001
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 0.77001 | 0.30801 | Reduce | 0.3 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.6 | 101 | 128 | 150 | 127.1667 | 0.1 | 33 | 58 | 69 | 55.6667 | 0 | 25 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2018-02-20 01:00 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.6 | 103 | 128 | 158 | 128.8333 | 0.2 | 39 | 46 | 68 | 48.5 | 0 | 28.5714 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-149 | Project_020_Risk-149 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs to be returned to UK | Person_703 | 2016-12-21 01:00 | 2017-11-19 01:00 | 0.2 | 0.94968 | 0.28491 | Accept | 0.05 | 0.94968 | 0.18994 | H2 | 4 | Stable | 0.9 | 87 | 139 | 141 | 130.6667 | 0.9 | 87 | 139 | 141 | 130.6667 | 0 | 75 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2018-03-22 | 2019-07-21 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.9 | 110 | 123 | 155 | 126.1667 | 0.3 | 15 | 50 | 74 | 48.1667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2018-03-16 01:00 | 0.1 | 6.4168 | 0.64168 | Transfer | 0.1 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sub-system FPGA | Person_216 | 2017-01-21 01:00 | 2018-02-20 01:00 | 0.3 | 1.54 | 0.46201 | Reduce | 0.4 | 1.5914 | 0.63655 | H2 | 4 | Stable | 0.6 | 104 | 128 | 157 | 128.8333 | 0.2 | 11 | 51 | 72 | 47.8333 | -3.3333 | -33.3333 | 0 | -2
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort for System HW/SW- System upgrade | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.3 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.8 | 85 | 134 | 159 | 130 | 0.4 | 21 | 55 | 72 | 52.1667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs | Person_372 | 2017-06-23 | 2018-08-22 01:00 | 0.5 | 6.6521 | 3.326 | Reduce | 0.5 | 6.6521 | 3.326 | H2 | 4 | Stable | 0.7 | 101 | 124 | 157 | 125.6667 | 0.4 | 28 | 55 | 62 | 51.6667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.5 | 3.5934 | 1.7967 | H2 | 4 | Stable | 0.9 | 91 | 128 | 153 | 126 | 0.3 | 11 | 53 | 69 | 48.6667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | HW - additional unplanned design effort | Person_216 | 2016-05-23 | 2019-10-21 01:00 | 0.4 | 3.3367 | 1.3347 | Reduce | 0.4 | 3.3367 | 1.3347 | H2 | 4 | Stable | 0.8 | 111 | 140 | 157 | 138 | 0.3 | 4 | 45 | 61 | 40.8333 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design [in addition to costed effort] | Person_216 | 2017-05-28 | 2017-10-17 01:00 | 0.2 | 2.6951 | 0.53901 | Reduce | 0.2 | 2.6951 | 0.53901 | H3 | 3 | Improving | 0.6 | 95 | 124 | 150 | 123.5 | 0.3 | 32 | 40 | 79 | 45.1667 | 0 | 0 | 1 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Minimum Order Quantities | Person_372 | 2017-05-23 | 2019-05-16 | 0.2 | 1.925 | 0.38501 | -- | 0.2 | 1.925 | 0.38501 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_372 | 2016-12-21 01:00 | 2017-12-19 01:00 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Worsening | 0.7 | 93 | 124 | 149 | 123 | 0.2 | 30 | 48 | 61 | 47.1667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_585 | 2017-10-21 01:00 | 2019-07-21 | 0.333 | 11.5502 | 3.8462 | Reduce | 0.333 | 11.5502 | 3.8462 | H2 | 4 | Stable | 0.8 | 83 | 122 | 160 | 121.8333 | 0.2 | 31 | 47 | 74 | 48.8333 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK021 | Project_021_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | ERP implementation | Person_174 | 2017-06-23 | 2017-09-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.25 | 0 | 0 | H2 | 4 | Stable | 0.6 | 97 | 129 | 146 | 126.5 | 0.4 | 3 | 40 | 77 | 40 |  | 50 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_174 | 2012-11-20 01:00 | 2018-08-21 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.9 | 86 | 135 | 148 | 129 | 0.1 | 2 | 58 | 78 | 52 | 0 | 50 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK024 | Project_021_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_482 | 2017-05-23 | 2017-11-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 97 | 128 | 156 | 127.5 | 0.3 | 4 | 50 | 61 | 44.1667 |  | 40 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2018-02-19 01:00 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Stable | 0.5 | 108 | 128 | 143 | 127.1667 | 0.3 | 14 | 52 | 65 | 47.8333 | 0 | 57.1429 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 0.8 | 4.6352 | 3.7081 | Reduce | 0.6 | 4.6352 | 2.7811 | H1 | 5 | Worsening | 0.8 | 96 | 140 | 155 | 135.1667 | 0.3 | 6 | 48 | 60 | 43 | 0 | 25 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-12-20 01:00 | 0.6 | 17.2826 | 10.3696 | Reduce | 0.3 | 17.2826 | 5.1848 | H2 | 4 | Worsening | 0.8 | 87 | 132 | 141 | 126 | 0.3 | 10 | 51 | 70 | 47.3333 | 0 | 50 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 0.8 | 1.3243 | 1.0595 | Reduce | 0.6 | 1.3243 | 0.7946 | H1 | 5 | Worsening | 0.5 | 98 | 126 | 145 | 124.5 | 0.3 | 9 | 58 | 65 | 51 | 0 | 25 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 0.2 | 0 | 0 | Reduce | 0.05 | 0 | 0 | H3 | 3 | Stable | 0.7 | 84 | 134 | 148 | 128 | 0.3 | 10 | 51 | 78 | 48.6667 |  | 75 | 1
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2018-01-19 01:00 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.8 | 81 | 121 | 151 | 119.3333 | 0.1 | 36 | 48 | 77 | 50.8333 | 80 | 66.6667 | 0 | 48
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_482 | 2016-08-06 | 2017-06-22 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.8 | 91 | 124 | 151 | 123 | 0.2 | 25 | 53 | 62 | 49.8333 |  | 50 | 1
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 0.3 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 99 | 122 | 151 | 123 | 0.4 | 20 | 42 | 79 | 44.5 |  | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 103 | 133 | 146 | 130.1667 | 0.3 | 18 | 58 | 69 | 53.1667 |  | 66.6667 | 1
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond (revised) target. | Person_482 | 2013-01-07 01:00 | 2018-02-04 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.8 | 82 | 137 | 151 | 130.1667 | 0.3 | 21 | 59 | 65 | 53.6667 | 0 | 33.3333 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_482 | 2016-08-06 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.6 | 105 | 134 | 147 | 131.3333 | 0.4 | 17 | 58 | 62 | 51.8333 |  | 80 | 1
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trial delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.5 | 85 | 135 | 160 | 130.8333 | 0.2 | 36 | 43 | 66 | 45.6667 |  | 40 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2013-01-07 01:00 | 2017-11-19 01:00 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.8 | 117 | 124 | 160 | 128.8333 | 0.2 | 23 | 53 | 65 | 50 | 0 | 33.3333 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Trial delay due to equip[ment availability | Person_174 | 2016-10-21 01:00 | 2017-08-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.8 | 102 | 139 | 152 | 135 | 0.1 | 4 | 46 | 60 | 41.3333 |  | 60 | 1
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_174 | 2009-06-23 | 2018-08-21 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.6 | 103 | 140 | 147 | 135 | 0.4 | 39 | 55 | 79 | 56.3333 | 50 | 28.5714 | 0 | 30
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-09-19 01:00 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.8 | 116 | 123 | 145 | 125.5 | 0.4 | 26 | 55 | 66 | 52 | 7.8429 | 40 | 0 | 4.7058
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-12-17 01:00 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.4 | 12.6474 | 5.059 | H2 | 4 | Stable | 0.5 | 88 | 131 | 145 | 126.1667 | 0.1 | 28 | 49 | 63 | 47.8333 | 0 | 33.3333 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.9 | 99 | 128 | 156 | 127.8333 | 0.3 | 31 | 45 | 70 | 46.8333 | 0 | 50 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 0.4 | 9.139 | 3.6556 | Avoid | 0.2 | 9.139 | 1.8278 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 0.125 | 232.2192 | 29.0274 | -- | 0.215 | 27.8663 | 5.9913 | H2 | 4 | Stable | [10 empty] | 88 | -72 | 0 | 52.8
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 0.5 | 13.7833 | 6.8917 | Avoid | 0.2 | 6.8917 | 1.3783 | H3 | 3 | Stable | [10 empty] | 50 | 60 | 1 | 31.8
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-20 01:00 | 0.3 | 5.5433 | 1.663 | Reduce | 0.35 | 5.5433 | 1.9402 | H2 | 4 | Worsening | 0.9 | 101 | 122 | 149 | 123 | 0.2 | 15 | 40 | 69 | 40.6667 | 0 | -16.6667 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Worsening | [10 empty] | 0 | 75 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 01:00 | 0.05 | 4.4946 | 1.1236 | Accept | 0.05 | 4.4946 | 0.44946 | H3 | 3 | Stable | 0.6 | 94 | 121 | 149 | 121.1667 | 0.6 | 94 | 121 | 149 | 121.1667 | 0 | 0 | 1 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 0.3 | 26.9674 | 8.0902 | Avoid | 0.3 | 14.9819 | 4.4946 | H2 | 4 | Stable | [10 empty] | 44.4444 | 0 | 0 | 26.6667
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-21 01:00 | 0.5 | 26.9674 | 13.4837 | Avoid | 0.1 | 12.7646 | 1.2765 | H2 | 4 | Worsening | [10 empty] | 52.6667 | 80 | 0 | 31.6
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-12-21 01:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.7 | 93 | 133 | 149 | 129 | 0.2 | 23 | 42 | 71 | 43.6667 | 47 | 0 | 0 | 28.2
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-12-21 01:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-19 01:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.2 | 1.5935 | 0.3187 | H3 | 3 | Stable | 0.5 | 107 | 123 | 157 | 126 | 0.2 | 15 | 46 | 62 | 43.5 | 50 | 50 | 1 | 31.5
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-026 | Project_043_Risk-026 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Equipment Delivery | Person_693 | 2017-04-19 | 2017-07-20 | 0.25 | 186.9553 | 59.2026 | Accept | 0.25 | 186.9553 | 1.3939 | H2 | 4 | Improving | 0.9 | 118 | 124 | 144 | 126.3333 | 0.9 | 118 | 124 | 144 | 126.3333 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Further Software Development | Person_523 | 2015-05-24 | 2018-02-19 01:00 | 0.1 | 22.8501 | 6.855 | Accept | 0.05 | 22.8501 | 6.855 | H3 | 3 | Stable | 0.8 | 92 | 128 | 156 | 126.6667 | 0.8 | 92 | 128 | 156 | 126.6667 | 0 | 50 | 1 | 1.5
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK225 | Project_024_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | More testing required as a result compliance to Platform Risk | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 5.6866 | 2.8433 | Reduce | 0.3 | 5.6866 | 1.706 | H2 | 4 | Stable | 0.8 | 97 | 128 | 142 | 125.1667 | 0.1 | 12 | 46 | 68 | 44 | 0 | 40 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.7 | 80 | 128 | 157 | 124.8333 | 0.4 | 6 | 51 | 74 | 47.3333 | 0 | 60 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_288 | 2017-02-22 01:00 | 2017-11-19 01:00 | 0.3 | 19.9938 | 5.9981 | Reduce | 0.1 | 19.9938 | 1.9994 | H3 | 3 | Improving | 0.9 | 102 | 138 | 148 | 133.6667 | 0.1 | 14 | 51 | 66 | 47.3333 | 0 | 66.6667 | 1 | 2
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK256 | Project_024_RISK256 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unable to meet spare capacity requirement | Person_119 | 2016-07-21 | 2018-01-21 01:00 | 0.8 | 0.12983 | 0.10386 | Reduce | 0.05 | 0.12983 | 0.0064915 | H3 | 3 | Stable | 0.7 | 87 | 122 | 154 | 121.5 | 0.3 | 39 | 43 | 67 | 46.3333 | 0 | 93.75 | 1 | 2.8125
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Performance (collector opportunity) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.3814 | 26.127 | 9.9648 | -- | 0.4132 | 26.127 | 10.7957 | H1 | 5 | Stable | [10 empty] | 0 | -8.3377 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.3 | 20.8767 | 6.263 | H2 | 4 | Stable | 0.9 | 104 | 138 | 156 | 135.3333 | 0.1 | 35 | 46 | 74 | 48.8333 | 50 | 25 | 0 | 30
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.493 | 58.1898 | 28.6876 | Reduce | 0.32035 | 40.4161 | 12.9473 | H1 | 5 | Worsening | 0.5 | 104 | 140 | 146 | 135 | 0.1 | 34 | 40 | 72 | 44.3333 | 30.5444 | 35.0203 | 0 | 18.3266
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK308 | Project_024_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System robustness and resilience | Person_774 | 2017-04-06 | 2018-06-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.1 | 2.5966 | 0.25966 | H3 | 3 | Stable | 0.7 | 116 | 125 | 152 | 128 | 0.2 | 8 | 54 | 66 | 48.3333 | 58.3333 | 66.6667 | 1 | 37
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK312 | Project_024_RISK312 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Built-in Test not fit for purpose | Person_774 | 2017-02-25 01:00 | 2018-05-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.2 | 9.8671 | 1.9734 | H2 | 4 | Stable | 0.7 | 81 | 133 | 154 | 127.8333 | 0.2 | 23 | 58 | 75 | 55 | -58.3333 | 33.3333 | 0 | -35
2017-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-62 | Project_022_RISK-62 | Threat | Project Contingency | Open | H3 | 3 | 8. Operations & Maintenance | Additional Costs from Integration Cost Centre | Person_703 | 2017-03-23 | 2017-05-14 | 0.5 | 7.1754 | 3.5877 | Avoid | 0.292 | 3.5877 | 1.0476 | H3 | 3 | Worsening | [10 empty] | 50 | 41.6 | 0 | 30
2017-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2017-06-21 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.35 | 2.8688 | 1.0041 | H2 | 4 | Stable | 0.8 | 97 | 139 | 141 | 132.3333 | 0.1 | 26 | 40 | 73 | 43.1667 | 22.0253 | 56.25 | 0 | 13.2152
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | EMC Testing | Person_332 | 2016-04-22 | 2017-10-20 01:00 | 0.35 | 2.3975 | 2.3975 | Accept | 0.1 | 0 | 0 | H2 | 4 | Stable | 0.8 | 91 | 134 | 148 | 129.1667 | 0.8 | 91 | 134 | 148 | 129.1667 | 100 | 71.4286 | 0 | 60
2017-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2017-08-20 01:00 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 0.65554 | 0.52443 | H2 | 4 | Stable | [10 empty] | 80.45 | 0 | 0 | 48.27
2017-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-63 | Project_022_RISK-63 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Levy | Person_703 | 2012-04-19 | 2017-08-20 01:00 | 0.8 | 3.5298 | 2.8239 | Exploit | 0.8 | 3.5298 | 2.8239 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-19 22:00 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.7 | 115 | 126 | 150 | 128.1667 | 0.3 | 37 | 56 | 73 | 55.6667 | 0 | 40 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_523 | 2015-01-22 01:00 | 2018-02-19 01:00 | 0.35 | 11.0894 | 0.55447 | Accept | 0.2 | 11.0894 | 0.55447 | H2 | 4 | Stable | 0.9 | 102 | 137 | 152 | 133.6667 | 0.9 | 102 | 137 | 152 | 133.6667 | 0 | 42.8571 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-19 22:00 | 0.7 | 0.92411 | 0.64688 | Reduce | 0.3 | 0.36965 | 0.11089 | H2 | 4 | Stable | 0.9 | 96 | 125 | 146 | 123.6667 | 0.1 | 18 | 59 | 76 | 55 | 60 | 57.1429 | 0 | 36
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-03 22:00 | 2016-04-21 | 0.5 | 4.0661 | 2.033 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.7 | 99 | 125 | 146 | 124.1667 | 0.2 | 14 | 50 | 71 | 47.5 | 0 | 90 | 1 | 2.7
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-19 22:00 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.5 | 0.46206 | 0.23103 | H1 | 5 | Improving | 0.9 | 116 | 125 | 157 | 128.8333 | 0.1 | 28 | 55 | 61 | 51.5 | 58.3333 | 16.6667 | 0 | 35
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_332 | 2016-06-23 | 2017-11-19 01:00 | 0.4 | 1.1089 | 0.88715 | Accept | 0.2 | 0.73929 | 0.44357 | H2 | 4 | Stable | 0.5 | 91 | 133 | 159 | 130.3333 | 0.5 | 91 | 133 | 159 | 130.3333 | 33.3333 | 50 | 0 | 20
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-28 22:00 | 2017-08-19 22:00 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.5 | 112 | 136 | 155 | 135.1667 | 0.1 | 7 | 50 | 69 | 46 | 0 | 50 | 1 | 1.5
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-19 22:00 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.8 | 84 | 124 | 145 | 120.8333 | 0.3 | 5 | 59 | 70 | 51.8333 | 0 | 25 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Stable | 0.6 | 99 | 134 | 151 | 131 | 0.2 | 29 | 40 | 77 | 44.3333 | 0 | 40 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-18 22:00 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Worsening | [10 empty] | 0 | 37.5 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | RISK004 | Project_028_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Engineering Changes to be embodied on the Rig | Person_604 | 2017-04-29 | 2019-02-20 01:00 | 0.8 | 1.8482 | 0.55447 | Accept | 0.8 | 1.8482 | 0.73929 | H1 | 5 | Stable | 0.8 | 109 | 121 | 151 | 124 | 0.8 | 109 | 121 | 151 | 124 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-19 22:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.5 | 84 | 122 | 146 | 119.6667 | 0.3 | 27 | 59 | 74 | 56.1667 | 90 | 75 | 1 | 56.25
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Risk of not being able to perform Tests | Person_238 | 2017-12-21 01:00 | 2019-01-21 01:00 | 0.5 | 49.4398 | 19.7759 | Accept | 0.5 | 49.4398 | 9.888 | H2 | 4 | Stable | 0.6 | 97 | 137 | 145 | 131.6667 | 0.6 | 97 | 137 | 145 | 131.6667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_238 | 2017-05-23 | 2019-01-21 01:00 | 0.5 | 6.4382 | 2.2534 | Accept | 0.5 | 6.4382 | 1.2876 | H2 | 4 | Stable | 0.7 | 97 | 136 | 153 | 132.3333 | 0.7 | 97 | 136 | 153 | 132.3333 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_693 | 2017-04-22 | 2017-09-19 01:00 | 0.6 | 6.6957 | 2.3435 | Accept | 0.3 | 6.6957 | 2.3435 | H3 | 3 | Worsening | 0.5 | 109 | 133 | 144 | 130.8333 | 0.5 | 109 | 133 | 144 | 130.8333 | 0 | 50 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_547 | 2017-05-23 | 2018-05-22 | 0.1 | 35.0206 | 7.0041 | Accept | 0.1 | 35.0206 | 7.0041 | H3 | 3 | Stable | 0.9 | 102 | 122 | 144 | 122.3333 | 0.9 | 102 | 122 | 144 | 122.3333 | 0 | 0 | 1 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.9 | 106 | 121 | 146 | 122.6667 | 0.1 | 22 | 45 | 69 | 45.1667 | 0 | 0 | 1 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-095 | Project_008_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Repair of interface units from the Programme | Person_639 | 2017-05-23 | 2018-08-21 | 0.2 | 9.4695 | 1.8939 | Avoid | 0.2 | 9.4695 | 1.8939 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production, Procurement or Engineering | Person_725 | 2018-01-21 01:00 | 2019-05-23 | 0.1 | 4.8452 | 1.2113 | Accept | 0.1 | 4.8452 | 1.2113 | H3 | 3 | Worsening | 0.8 | 120 | 126 | 151 | 129.1667 | 0.8 | 120 | 126 | 151 | 129.1667 | 0 | 0 | 1 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R81 | Project_041_R81 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Re-imaging of PC's - additional material/Labour effort | Person_515 | 2017-05-23 | 2017-10-21 01:00 | 0.5 | 3.7878 | 1.1363 | Accept | 0.25 | 3.7878 | 1.1363 | H2 | 4 | Stable | 0.8 | 111 | 131 | 154 | 131.5 | 0.8 | 111 | 131 | 154 | 131.5 | 0 | 50 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-080 | Project_008_Risk-080 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Recovery of Costs | Person_565 | 2016-08-21 01:00 | 2017-08-20 01:00 | 0.5 | 23.6737 | 11.8369 | -- | 0.5 | 23.6737 | 11.8369 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Survey costs | Person_618 | 2016-04-22 | 2017-08-20 01:00 | 0.2 | 13.2573 | 2.6515 | Avoid | 0.2 | 13.2573 | 2.6515 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-079 | Project_008_Risk-079 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Regulations Phase 3 and 4 | Person_565 | 2016-10-21 01:00 | 2018-08-21 | 0.25 | 71.9682 | 17.992 | -- | 0.25 | 71.9682 | 17.992 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK021 | Project_021_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | ERP implementation | Person_174 | 2017-06-23 | 2017-09-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.25 | 0 | 0 | H2 | 4 | Stable | 0.5 | 117 | 121 | 149 | 125 | 0.3 | 14 | 42 | 76 | 43 |  | 50 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_174 | 2012-11-20 01:00 | 2018-08-21 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.7 | 100 | 135 | 155 | 132.5 | 0.2 | 24 | 45 | 63 | 44.5 | 0 | 50 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK024 | Project_021_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_482 | 2017-05-23 | 2017-11-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 82 | 135 | 159 | 130.1667 | 0.2 | 12 | 49 | 78 | 47.6667 |  | 40 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2018-02-19 01:00 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Stable | 0.9 | 113 | 123 | 149 | 125.6667 | 0.2 | 23 | 43 | 64 | 43.1667 | 0 | 57.1429 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 0.8 | 4.6352 | 3.7081 | Reduce | 0.6 | 4.6352 | 2.7811 | H1 | 5 | Worsening | 0.6 | 112 | 135 | 160 | 135.3333 | 0.3 | 11 | 49 | 65 | 45.3333 | 0 | 25 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-12-20 01:00 | 0.6 | 17.2826 | 10.3696 | Reduce | 0.3 | 17.2826 | 5.1848 | H2 | 4 | Worsening | 0.7 | 93 | 124 | 141 | 121.6667 | 0.1 | 4 | 50 | 75 | 46.5 | 0 | 50 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Additional tasks required with mode certification | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 0.8 | 1.3243 | 1.0595 | Reduce | 0.6 | 1.3243 | 0.7946 | H1 | 5 | Worsening | 0.9 | 94 | 136 | 156 | 132.3333 | 0.3 | 24 | 47 | 74 | 47.6667 | 0 | 25 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to build standard issue relating to the modification of product | Person_174 | 2016-11-20 01:00 | 2017-10-19 01:00 | 0.2 | 0 | 0 | Reduce | 0.05 | 0 | 0 | H3 | 3 | Stable | 0.9 | 82 | 138 | 142 | 129.3333 | 0.4 | 33 | 46 | 63 | 46.6667 |  | 75 | 1
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2018-01-19 01:00 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.9 | 117 | 130 | 145 | 130.3333 | 0.4 | 18 | 42 | 60 | 41 | 80 | 66.6667 | 0 | 48
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond (revised) target. | Person_482 | 2013-01-07 01:00 | 2018-02-04 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.9 | 95 | 129 | 151 | 127 | 0.4 | 36 | 52 | 79 | 53.8333 | 0 | 33.3333 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2013-01-07 01:00 | 2017-11-19 01:00 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.7 | 101 | 129 | 147 | 127.3333 | 0.2 | 37 | 54 | 66 | 53.1667 | 0 | 33.3333 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_174 | 2009-06-23 | 2018-08-21 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.9 | 92 | 129 | 154 | 127 | 0.2 | 6 | 44 | 66 | 41.3333 | 50 | 28.5714 | 0 | 30
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-09-19 01:00 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.5 | 91 | 140 | 156 | 134.5 | 0.1 | 9 | 50 | 65 | 45.6667 | 7.8429 | 40 | 0 | 4.7058
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-12-17 01:00 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.4 | 12.6474 | 5.059 | H2 | 4 | Stable | 0.6 | 119 | 137 | 151 | 136.3333 | 0.2 | 8 | 46 | 77 | 44.8333 | 0 | 33.3333 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.6 | 114 | 136 | 153 | 135.1667 | 0.2 | 34 | 48 | 76 | 50.3333 | 0 | 50 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK019 | Project_042_RISK019 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2016-05-23 | 2021-05-22 | 0.3 | 7.5153 | 2.2546 | -- | 0.3 | 7.5153 | 2.2546 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2017-11-19 01:00 | 0.05 | 0.65759 | 0.098638 | Accept | 0.05 | 0.65759 | 0.098638 | H3 | 3 | Improving | 0.8 | 110 | 128 | 153 | 129.1667 | 0.8 | 110 | 128 | 153 | 129.1667 | 0 | 0 | 1 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 0.5 | 6.7638 | 1.3528 | Accept | 0.5 | 6.7638 | 1.3528 | H2 | 4 | Improving | 0.6 | 93 | 129 | 141 | 125 | 0.6 | 93 | 129 | 141 | 125 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 | 0.3 | 0.93941 | 0.14091 | Accept | 0.3 | 0.93941 | 0.14091 | H2 | 4 | Stable | 0.6 | 120 | 140 | 145 | 137.5 | 0.6 | 120 | 140 | 145 | 137.5 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R013 | Project_016_Risk--R013 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Resource Availability (Threat) | Person_697 | 2016-04-02 | 2019-08-01 | 0.2 | 2.8182 | 0.56365 | Accept | 0.2 | 2.8182 | 0.56365 | H2 | 4 | Worsening | 0.7 | 115 | 127 | 157 | 130 | 0.7 | 115 | 127 | 157 | 130 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2020-09-19 01:00 | 0.2 | 2.5834 | 0.64585 | Accept | 0.2 | 2.5834 | 0.64585 | H3 | 3 | Stable | 0.9 | 116 | 133 | 151 | 133.1667 | 0.9 | 116 | 133 | 151 | 133.1667 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2019-07-21 | 0.3 | 1.1273 | 0.45092 | Accept | 0.2 | 1.1273 | 0.45092 | H3 | 3 | Stable | 0.6 | 86 | 137 | 148 | 130.3333 | 0.6 | 86 | 137 | 148 | 130.3333 | 0 | 33.3333 | 1 | 1
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 9.3941 | 0.93941 | Accept | 0.1 | 9.3941 | 0.93941 | H3 | 3 | Stable | 0.5 | 108 | 123 | 147 | 124.5 | 0.5 | 108 | 123 | 147 | 124.5 | 0 | -233.3333 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Governance and Export Rules | Person_455 | 2016-05-23 | 2021-05-22 | 0.25 | 0.93941 | 0.23485 | Transfer | 0.25 | 0.93941 | 0.23485 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 2.1606 | 0.43213 | Accept | 0.25 | 2.1606 | 0.43213 | H2 | 4 | Stable | 0.6 | 100 | 129 | 156 | 128.6667 | 0.6 | 100 | 129 | 156 | 128.6667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.1 | 53.0293 | 5.3029 | Reduce | 0.1 | 53.0293 | 5.3029 | H3 | 3 | Worsening | 0.9 | 87 | 130 | 149 | 126 | 0.4 | 16 | 44 | 77 | 44.8333 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 0.20788 | 0.068599 | Accept | 0.3 | 0.052336 | 0.0057569 | H2 | 4 | Stable | 0.8 | 86 | 133 | 158 | 129.3333 | 0.8 | 86 | 133 | 158 | 129.3333 | 74.8236 | 0 | 0 | 44.8942
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 01:00 | 2017-08-20 01:00 | 0.1 | 7.7469 | 0.77469 | Reduce | 0.1 | 7.7469 | 0.77469 | H3 | 3 | Stable | 0.9 | 82 | 134 | 141 | 126.5 | 0.4 | 10 | 58 | 61 | 50.5 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 01:00 | 2016-11-20 01:00 | 0.25 | 11.3437 | 0.56718 | Accept | 0.1 | 11.3437 | 0.56718 | H3 | 3 | Stable | 0.5 | 98 | 123 | 143 | 122.1667 | 0.5 | 98 | 123 | 143 | 122.1667 | 0 | 60 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-20 01:00 | 0.25 | 17.0765 | 1.7076 | Accept | 0.15 | 17.0765 | 1.7076 | H3 | 3 | Stable | 0.6 | 110 | 127 | 145 | 127.1667 | 0.6 | 110 | 127 | 145 | 127.1667 | 0 | 40 | 1 | 1.2
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2017-02-20 01:00 | 2018-05-22 | 0.1 | 186.9553 | 59.2026 | Accept | 0.1 | 186.9553 | 1.3939 | H3 | 3 | Stable | 0.6 | 95 | 121 | 157 | 122.6667 | 0.6 | 95 | 121 | 157 | 122.6667 | 0 | 0 | 1 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK003 | Project_024_RISK003 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance | Person_288 | 2017-12-21 01:00 | 2018-08-21 | 0.31667 | 22.8501 | 6.855 | Accept | 0.007456 | 22.8501 | 6.855 | H2 | 4 | Stable | 0.9 | 93 | 136 | 160 | 132.8333 | 0.9 | 93 | 136 | 160 | 132.8333 | 0 | 97.6455 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Management Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 0.3 | 25.966 | 7.7898 | Accept | 0.3 | 10.3864 | 3.1159 | H1 | 5 | Improving | 0.7 | 85 | 137 | 147 | 130 | 0.7 | 85 | 137 | 147 | 130 | 60 | 0 | 0 | 36
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Additional minor point releases | Person_228 | 2016-05-23 | 2017-10-19 01:00 | 0.5 | 11.9444 | 5.9722 | Reduce | 0.25 | 11.9444 | 2.9861 | H2 | 4 | Stable | 0.7 | 118 | 129 | 150 | 130.6667 | 0.4 | 33 | 50 | 69 | 50.3333 | 0 | 50 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_228 | 2016-05-23 | 2018-04-21 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.7 | 105 | 134 | 160 | 133.5 | 0.1 | 1 | 49 | 73 | 45 | 0 | 50 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_413 | 2015-11-21 01:00 | 2018-11-20 01:00 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.8 | 115 | 129 | 145 | 129.3333 | 0.2 | 34 | 45 | 76 | 48.3333 | 0 | 5 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.8 | 2.8043 | 2.2435 | Reduce | 0.45 | 2.8043 | 1.2619 | H1 | 5 | Stable | 0.5 | 115 | 135 | 155 | 135 | 0.1 | 2 | 59 | 68 | 51 | 0 | 43.75 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK167 | Project_024_RISK167 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Customer not providing the information needed | Person_710 | 2016-08-21 01:00 | 2018-02-19 01:00 | 0.5 | 9.971 | 4.9855 | Reduce | 0.3 | 9.971 | 2.9913 | H1 | 5 | Worsening | 0.6 | 85 | 123 | 150 | 121.1667 | 0.4 | 23 | 52 | 75 | 51 | 0 | 40 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK306(028) | Project_024_RISK306(028) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | HW repairs required on units | Person_119 | 2016-11-19 01:00 | 2018-11-20 01:00 | 0.3 | 2.813 | 0.8439 | Reduce | 0.2 | 2.813 | 0.5626 | H2 | 4 | Stable | 0.7 | 94 | 122 | 160 | 123.6667 | 0.1 | 2 | 49 | 60 | 43 | 0 | 33.3333 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-19 22:00 | 0.05 | 5.1932 | 1.2983 | Accept | 0.05 | 5.1932 | 1.2983 | H2 | 4 | Stable | 0.6 | 119 | 125 | 143 | 127 | 0.6 | 119 | 125 | 143 | 127 | 0 | 0 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 0.8 | 5.1932 | 1.558 | Accept | 0.6 | 5.1932 | 1.558 | H1 | 5 | Stable | 0.7 | 87 | 128 | 156 | 125.8333 | 0.7 | 87 | 128 | 156 | 125.8333 | 0 | 25 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-26 22:00 | 2016-08-19 22:00 | 0.1 | 5.3577 | 1.3394 | Accept | 0.1 | 5.3577 | 1.3394 | H2 | 4 | Stable | 0.9 | 99 | 133 | 154 | 130.8333 | 0.9 | 99 | 133 | 154 | 130.8333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK226 | Project_024_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Late Evidences delay Certification delivery | Person_710 | 2017-04-30 | 2017-12-21 01:00 | 0.4 | 3.9468 | 1.5787 | Reduce | 0.2 | 3.9468 | 0.78937 | H2 | 4 | Worsening | 0.7 | 91 | 136 | 159 | 132.3333 | 0.1 | 17 | 48 | 64 | 45.5 | 0 | 50 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK302(024) | Project_024_RISK302(024) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | On time provision of platform units | Person_119 | 2016-11-19 01:00 | 2019-05-23 | 0.25 | 2.3889 | 0.59722 | Reduce | 0.15 | 2.3889 | 0.35833 | H2 | 4 | Stable | 0.5 | 107 | 138 | 159 | 136.3333 | 0.1 | 30 | 41 | 77 | 45.1667 | 0 | 40 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK227 | Project_024_RISK227 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Data Bunching | Person_710 | 2017-03-23 | 2017-09-19 01:00 | 0.4 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H1 | 5 | Stable | 0.9 | 100 | 133 | 160 | 132 | 0.4 | 30 | 55 | 64 | 52.3333 |  | 25 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-18 22:00 | 0.2 | 4.8297 | 1.6904 | Accept | 0.2 | 4.8297 | 1.6904 | H3 | 3 | Improving | 0.8 | 111 | 138 | 156 | 136.5 | 0.8 | 111 | 138 | 156 | 136.5 | 0 | 0 | 1 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 0.3 | 5.1067 | 1.0213 | Accept | 0.4 | 5.1067 | 1.0213 | H3 | 3 | Stable | 0.7 | 103 | 133 | 152 | 131.1667 | 0.7 | 103 | 133 | 152 | 131.1667 | 0 | -33.3333 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software issue input | Person_084 | 2016-11-23 | 2023-02-20 | 0.4 | 0.5626 | 0.19691 | Accept | 0.2 | 0.5626 | 0.19691 | H2 | 4 | Stable | 0.5 | 91 | 140 | 160 | 135.1667 | 0.5 | 91 | 140 | 160 | 135.1667 | 0 | 50 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Volume of production tools and Jigs | Person_084 | 2016-11-23 | 2021-11-23 | 0.35 | 21.1623 | 21.1623 | Accept | 0.2 | 21.1623 | 21.1623 | H2 | 4 | Stable | 0.6 | 81 | 125 | 141 | 120.3333 | 0.6 | 81 | 125 | 141 | 120.3333 | 0 | 42.8571 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK040 | Project_017_RISK040 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Upgrades | Person_084 | 2016-09-30 | 2016-12-18 | 0.35 | 3.9728 | 1.3905 | Accept | 0.35 | 3.9728 | 1.3905 | H2 | 4 | Stable | 0.8 | 87 | 136 | 152 | 130.5 | 0.8 | 87 | 136 | 152 | 130.5 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK225 | Project_024_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | More testing required as a result compliance to Platform Risk | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 5.6866 | 2.8433 | Reduce | 0.3 | 5.6866 | 1.706 | H2 | 4 | Stable | 0.7 | 87 | 129 | 159 | 127 | 0.2 | 30 | 41 | 70 | 44 | 0 | 40 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.8 | 80 | 139 | 160 | 132.6667 | 0.4 | 22 | 49 | 76 | 49 | 0 | 60 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_288 | 2017-02-22 01:00 | 2017-11-19 01:00 | 0.3 | 19.9938 | 5.9981 | Reduce | 0.1 | 19.9938 | 1.9994 | H3 | 3 | Improving | 0.5 | 92 | 131 | 159 | 129.1667 | 0.3 | 27 | 53 | 71 | 51.6667 | 0 | 66.6667 | 1 | 2
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.2 | 3.843 | 0.76859 | H2 | 4 | Stable | 0.5 | 90 | 125 | 149 | 123.1667 | 0.1 | 3 | 56 | 69 | 49.3333 | 0 | 60 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK256 | Project_024_RISK256 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unable to meet spare capacity requirement | Person_119 | 2016-07-21 | 2018-01-21 01:00 | 0.8 | 0.12983 | 0.10386 | Reduce | 0.05 | 0.12983 | 0.0064915 | H3 | 3 | Stable | 0.5 | 116 | 132 | 159 | 133.8333 | 0.4 | 37 | 48 | 66 | 49.1667 | 0 | 93.75 | 1 | 2.8125
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Performance (collector opportunity) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.3814 | 26.127 | 9.9648 | -- | 0.4132 | 26.127 | 10.7957 | H1 | 5 | Stable | [10 empty] | 0 | -8.3377 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.3 | 20.8767 | 6.263 | H1 | 5 | Stable | 0.9 | 93 | 135 | 146 | 129.8333 | 0.2 | 18 | 40 | 76 | 42.3333 | 50 | 25 | 0 | 30
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.50325 | 71.5182 | 35.9915 | Reduce | 0.3172 | 51.9268 | 16.4712 | H1 | 5 | Worsening | 0.7 | 110 | 121 | 143 | 122.8333 | 0.4 | 9 | 45 | 79 | 44.6667 | 27.3935 | 36.9697 | 0 | 16.4361
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK308 | Project_024_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System robustness and resilience | Person_774 | 2017-04-06 | 2018-06-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.1 | 2.5966 | 0.25966 | H3 | 3 | Stable | 0.7 | 100 | 121 | 145 | 121.5 | 0.1 | 15 | 40 | 67 | 40.3333 | 58.3333 | 66.6667 | 1 | 37
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-085 | Project_008_SER-085 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Insufficient LOE to manage the supply chain with reducing number of spares | Person_639 | 2017-04-22 | 2018-08-21 | 0.25 | 3.1344 | 1.5672 | Accept | 0.25 | 3.1344 | 1.5672 | H3 | 3 | Stable | 0.8 | 92 | 137 | 142 | 130.3333 | 0.8 | 92 | 137 | 142 | 130.3333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-090 | Project_008_Risk-090 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Demands but not provisioned | Person_639 | 2017-04-22 | 2018-08-21 | 0.3 | 0.97678 | 0.48839 | Accept | 0.3 | 0.97678 | 0.48839 | H3 | 3 | Stable | 0.8 | 110 | 135 | 144 | 132.3333 | 0.8 | 110 | 135 | 144 | 132.3333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 0.45 | 7.3848 | 3.6924 | Accept | 0.45 | 7.3848 | 3.6924 | H2 | 4 | Stable | 0.8 | 90 | 127 | 154 | 125.3333 | 0.8 | 90 | 127 | 154 | 125.3333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-116 | Project_011_Risk-116 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Delays to Qualification | Person_147 | 2017-04-22 | 2017-08-31 01:00 | 0.5 | 0.48868 | 0.24434 | Reduce | 0.5 | 0.48868 | 0.24434 | H1 | 5 | Stable | 0.5 | 103 | 138 | 153 | 134.6667 | 0.4 | 32 | 54 | 72 | 53.3333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-104 | Project_011_Risk-104 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer delayed in providing Custeomr Furnished Equipment | Person_147 | 2016-06-23 | 2017-08-25 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.7 | 109 | 138 | 149 | 135 | 0.1 | 19 | 57 | 79 | 54.3333 |  | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_565 | 2018-05-22 | 2018-08-21 | 0.25 | 0.34776 | 0.069552 | Accept | 0.25 | 0.34776 | 0.069552 | H3 | 3 | Stable | 0.5 | 91 | 129 | 141 | 124.6667 | 0.5 | 91 | 129 | 141 | 124.6667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 0.3 | 0.58983 | 0.17695 | -- | 0.15 | 0.58983 | 0.088474 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 0.2 | 0.62279 | 0.12456 | Avoid | 0.2 | 0.62279 | 0.12456 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2017-09-20 01:00 | 2018-04-21 | 0.15 | 0.28639 | 0.042959 | -- | 0.15 | 0.28639 | 0.042959 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-08-20 01:00 | 0.2 | 0.27503 | 0.055005 | -- | 0.2 | 0.27503 | 0.055005 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 0.2 | 1.8854 | 0.37708 | Reduce | 0.2 | 1.8854 | 0.37708 | H2 | 4 | Stable | 0.5 | 119 | 122 | 160 | 127.8333 | 0.1 | 5 | 42 | 61 | 39 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2017-10-21 01:00 | 2018-08-21 | 0.4 | 1.4138 | 0.56551 | Reduce | 0.4 | 1.4138 | 0.56551 | H2 | 4 | Stable | 0.5 | 108 | 124 | 143 | 124.5 | 0.1 | 33 | 45 | 74 | 47.8333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Lack of Spares Availability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 0.3 | 0.18354 | 0.082593 | Accept | 0.3 | 0.18354 | 0.082593 | H3 | 3 | Stable | 0.7 | 115 | 128 | 143 | 128.3333 | 0.7 | 115 | 128 | 143 | 128.3333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 01:00 | 2017-08-23 01:00 | 0.45 | 0.47448 | 0.21351 | Reduce | 0.45 | 0.47448 | 0.21351 | H2 | 4 | Stable | 0.9 | 118 | 127 | 147 | 128.8333 | 0.1 | 38 | 49 | 75 | 51.5 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suppliers | Person_455 | 2016-05-23 | 2021-05-22 | 0.15 | 0.11081 | 0.011081 | Accept | 0.15 | 0.11081 | 0.011081 | H2 | 4 | Stable | 0.9 | 113 | 131 | 143 | 130 | 0.9 | 113 | 131 | 143 | 130 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-10-19 01:00 | 2018-08-21 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.7 | 93 | 130 | 160 | 128.8333 | 0.4 | 15 | 44 | 61 | 42 |  | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Pick up and Drop off of Software Resource | Person_230 | 2017-12-19 01:00 | 2018-02-19 01:00 | 0.4 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 0.4 | 0.19206 | 0.076826 | -- | 0.4 | 0.19206 | 0.076826 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 0.2 | 0.14035 | 0.028071 | Reduce | 0.2 | 0.14035 | 0.028071 | H2 | 4 | Stable | 0.7 | 80 | 135 | 157 | 129.5 | 0.1 | 8 | 44 | 76 | 43.3333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 0.4 | 0.58017 | 0.23207 | Avoid | 0.4 | 0.58017 | 0.23207 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares | Person_455 | 2016-05-23 | 2021-05-22 | 0.2 | 0.49834 | 0.12459 | Accept | 0.2 | 0.49834 | 0.12459 | H2 | 4 | Stable | 0.9 | 93 | 121 | 146 | 120.5 | 0.9 | 93 | 121 | 146 | 120.5 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.2 | 0.11365 | 0.022729 | -- | 0.2 | 0.11365 | 0.022729 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 0.3 | 0.32389 | 0.097168 | Reduce | 0.3 | 0.32389 | 0.097168 | H2 | 4 | Stable | 0.5 | 96 | 132 | 152 | 129.3333 | 0.1 | 3 | 56 | 77 | 50.6667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 2. Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 0.25 | 0 | 0 | -- | 0.25 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2017-10-21 01:00 | 2018-05-21 | 0.4 | 0.19206 | 0.076826 | -- | 0.4 | 0.19206 | 0.076826 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 0.3 | 0.11933 | 0.035799 | -- | 0.3 | 0.022161 | 0.0066484 | H3 | 3 | Stable | [10 empty] | 81.4286 | 0 | 0 | 48.8571
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Local customer Engineers in country | Person_455 | 2016-05-23 | 2021-05-22 | 0.1 | 1.1416 | 0.39956 | Accept | 0.1 | 1.1416 | 0.39956 | H2 | 4 | Stable | 0.7 | 112 | 140 | 149 | 136.8333 | 0.7 | 112 | 140 | 149 | 136.8333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) at the System level on product platform - performed by 3rd parties | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.41 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -2.5 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Sub-system / product system accreditation hindered by Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.1 | 0.25667 | 0.025667 | Transfer | 0.1 | 0.25667 | 0.025667 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 1.078 | 0.43121 | Reduce | 0.4 | 1.4673 | 0.58692 | H2 | 4 | Improving | 0.9 | 115 | 136 | 152 | 135.1667 | 0.3 | 31 | 53 | 64 | 51.1667 | -36.1112 | 0 | 0 | -21.6667
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2018-03-21 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2017-11-20 01:00 | 0.6 | 0.89835 | 0.53901 | Transfer | 0.6 | 0.89835 | 0.53901 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 0.35 | 0.85557 | 0.29945 | Reduce | 0.35 | 1.9208 | 0.67227 | H2 | 4 | Stable | 0.9 | 119 | 130 | 158 | 132.8333 | 0.1 | 30 | 57 | 78 | 56 | -124.5001 | 0 | 0 | -74.7001
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 0.77001 | 0.30801 | Reduce | 0.3 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.9 | 86 | 124 | 146 | 121.3333 | 0.1 | 37 | 55 | 63 | 53.3333 | 0 | 25 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2018-02-20 01:00 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.8 | 85 | 125 | 155 | 123.3333 | 0.3 | 3 | 51 | 72 | 46.5 | 0 | 28.5714 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence | Person_455 | 2016-05-23 | 2021-05-22 | 0.3 | 1.54 | 0.30801 | Accept | 0.3 | 0.77001 | 0.154 | H2 | 4 | Stable | 0.6 | 91 | 131 | 160 | 129.1667 | 0.6 | 91 | 131 | 160 | 129.1667 | 50 | 0 | 0 | 30
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables | Person_455 | 2016-05-23 | 2021-05-22 | 0.2 | 0.94968 | 0.28491 | Accept | 0.2 | 0.94968 | 0.18994 | H2 | 4 | Stable | 0.5 | 82 | 139 | 151 | 131.5 | 0.5 | 82 | 139 | 151 | 131.5 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2021-05-22 | 0.2 | 27.1644 | 0.81493 | Accept | 0.2 | 12.8336 | 1.2834 | H2 | 4 | Stable | 0.6 | 105 | 138 | 145 | 133.6667 | 0.6 | 105 | 138 | 145 | 133.6667 | 52.7559 | 0 | 0 | 31.6535
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2018-03-22 | 2019-07-21 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.5 | 91 | 140 | 157 | 134.6667 | 0.4 | 9 | 58 | 60 | 50.1667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2018-03-16 01:00 | 0.1 | 6.4168 | 0.64168 | Transfer | 0.1 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sub-system FPGA | Person_216 | 2017-01-21 01:00 | 2018-02-20 01:00 | 0.4 | 1.5914 | 0.63655 | Reduce | 0.4 | 1.5914 | 0.63655 | H2 | 4 | Stable | 0.5 | 81 | 122 | 152 | 120.1667 | 0.1 | 22 | 58 | 61 | 52.5 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort for System HW/SW- System upgrade | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.3 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.7 | 106 | 140 | 149 | 135.8333 | 0.4 | 19 | 59 | 60 | 52.5 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs | Person_372 | 2017-06-23 | 2018-08-22 01:00 | 0.5 | 6.6521 | 3.326 | Reduce | 0.5 | 6.6521 | 3.326 | H2 | 4 | Stable | 0.7 | 120 | 131 | 145 | 131.5 | 0.1 | 35 | 40 | 74 | 44.8333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.5 | 3.5934 | 1.7967 | H2 | 4 | Stable | 0.9 | 84 | 121 | 153 | 120.1667 | 0.2 | 27 | 54 | 72 | 52.5 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | HW - additional unplanned design effort | Person_332 | 2016-05-23 | 2018-02-20 01:00 | 0.4 | 3.3367 | 1.3347 | Reduce | 0.4 | 3.3367 | 1.3347 | H2 | 4 | Stable | 0.6 | 94 | 134 | 145 | 129.1667 | 0.4 | 15 | 49 | 76 | 47.8333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2021-05-22 | 0.15 | 4.2779 | 1.0695 | Accept | 0.15 | 4.2779 | 1.0695 | H2 | 4 | Stable | 0.5 | 118 | 137 | 148 | 135.6667 | 0.5 | 118 | 137 | 148 | 135.6667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2021-05-22 | 0.2 | 2.5667 | 0.77001 | Accept | 0.2 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.6 | 81 | 127 | 156 | 124.1667 | 0.6 | 81 | 127 | 156 | 124.1667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design [in addition to costed effort] | Person_332 | 2017-05-28 | 2018-08-18 | 0.2 | 2.6951 | 0.53901 | Reduce | 0.2 | 2.6951 | 0.53901 | H3 | 3 | Improving | 0.6 | 101 | 140 | 148 | 134.8333 | 0.2 | 34 | 58 | 79 | 57.5 | 0 | 0 | 1 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Minimum Order Quantities | Person_372 | 2017-05-23 | 2019-05-16 | 0.2 | 1.925 | 0.38501 | -- | 0.2 | 1.925 | 0.38501 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_372 | 2016-12-21 01:00 | 2017-12-19 01:00 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Worsening | 0.9 | 88 | 124 | 152 | 122.6667 | 0.4 | 5 | 45 | 74 | 43.1667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_585 | 2017-10-21 01:00 | 2019-07-21 | 0.333 | 11.5502 | 3.8462 | Reduce | 0.333 | 11.5502 | 3.8462 | H2 | 4 | Stable | 0.9 | 103 | 131 | 149 | 129.3333 | 0.3 | 21 | 46 | 72 | 46.1667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Transport Routes | Person_455 | 2016-05-23 | 2021-05-22 | 0.15 | 0.81199 | 0.081199 | Accept | 0.15 | 0.81199 | 0.0406 | H2 | 4 | Stable | 0.5 | 108 | 133 | 148 | 131.3333 | 0.5 | 108 | 133 | 148 | 131.3333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Internal Quality Issues | Person_251 | 2016-05-23 | 2021-05-22 | 0.2 | 1.2198 | 0.60991 | Accept | 0.2 | 1.2198 | 0.60991 | H2 | 4 | Stable | 0.5 | 96 | 122 | 147 | 121.8333 | 0.5 | 96 | 122 | 147 | 121.8333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs | Person_455 | 2016-05-23 | 2021-05-22 | 0.25 | 0 | 0 | Accept | 0.25 | 0 | 0 | H2 | 4 | Stable | 0.8 | 120 | 129 | 156 | 132 | 0.8 | 120 | 129 | 156 | 132 |  | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PEN Testing Security Features | Person_604 | 2015-04-11 | 2017-10-20 01:00 | 0.3 | 5.4553 | 1.6366 | Reduce | 0.15 | 5.252 | 0.7878 | H2 | 4 | Stable | 0.5 | 98 | 138 | 160 | 135 | 0.3 | 17 | 58 | 64 | 52.1667 | 3.7267 | 50 | 0 | 2.236
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Platforms Cable and connectors | Person_499 | 2015-11-21 01:00 | 2019-04-10 | 0.45 | 0.41338 | 0.18602 | Reduce | 0.05 | 0.41338 | 0.020669 | H2 | 4 | Stable | 0.5 | 92 | 124 | 147 | 122.5 | 0.2 | 6 | 52 | 65 | 46.5 | 0 | 88.8889 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | FOC Acceptance | Person_499 | 2015-11-21 01:00 | 2018-02-18 01:00 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.3 | 8.471 | 2.5413 | H2 | 4 | Stable | 0.9 | 80 | 123 | 144 | 119.3333 | 0.4 | 14 | 58 | 67 | 52.1667 | -99.9999 | 14.2857 | 0 | -59.9999
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Country Stability | Person_455 | 2016-05-23 | 2021-05-22 | 0.4 | 8.8098 | 3.0834 | Accept | 0.4 | 8.8098 | 1.762 | H2 | 4 | Stable | 0.6 | 112 | 123 | 147 | 125.1667 | 0.6 | 112 | 123 | 147 | 125.1667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2021-05-22 | 0.1 | 0.40661 | 0.16264 | Accept | 0.1 | 0.40661 | 0.081321 | H2 | 4 | Stable | 0.7 | 101 | 130 | 157 | 129.6667 | 0.7 | 101 | 130 | 157 | 129.6667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Furnished Equipmnet Condition | Person_496 | 2015-04-27 | 2019-04-10 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.8 | 91 | 124 | 145 | 122 | 0.4 | 1 | 43 | 62 | 39.1667 |  | 62.5 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2021-05-22 | 0.2 | 0.76103 | 0.60883 | Accept | 0.2 | 0.76103 | 0.60883 | H2 | 4 | Stable | 0.9 | 95 | 126 | 158 | 126.1667 | 0.9 | 95 | 126 | 158 | 126.1667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 01:00 | 0.05 | 5.4729 | 4.3783 | Accept | 0.05 | 4.6191 | 1.3857 | H3 | 3 | Stable | 0.5 | 115 | 127 | 142 | 127.5 | 0.5 | 115 | 127 | 142 | 127.5 | 15.6018 | 0 | 1 | 9.3611
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-148 | Project_020_Risk-148 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs non-available items | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.3 | 14.9935 | 4.498 | Reduce | 0.3 | 1.1374 | 0.34121 | H2 | 4 | Stable | 0.5 | 91 | 132 | 153 | 128.6667 | 0.1 | 28 | 46 | 76 | 48 | 92.4143 | 0 | 0 | 55.4486
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 2.2492 | 0.8997 | H2 | 4 | Stable | 0.8 | 95 | 126 | 142 | 123.5 | 0.3 | 35 | 52 | 75 | 53 | 43.1818 | 20 | 0 | 25.9091
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2017-02-20 01:00 | 2018-05-22 | 0.1 | 18.6688 | 3.7338 | Accept | 0.1 | 14.6039 | 0.7302 | H3 | 3 | Stable | 0.5 | 102 | 134 | 148 | 131 | 0.5 | 102 | 134 | 148 | 131 | 21.7735 | 0 | 1 | 13.0641
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-147 | Project_020_Risk-147 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component taking longer to refurbish in country | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.6 | 6.7477 | 4.0486 | Reduce | 0.6 | 0.74972 | 0.44983 | H2 | 4 | Stable | 0.7 | 115 | 134 | 159 | 135 | 0.2 | 12 | 49 | 73 | 46.8333 | 88.8893 | 0 | 0 | 53.3336
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_703 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 5.0983 | 0.76474 | H3 | 3 | Stable | 0.7 | 103 | 134 | 143 | 130.3333 | 0.2 | 34 | 44 | 60 | 45 | 19.0479 | 70 | 1 | 13.5287
2017-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-63 | Project_022_RISK-63 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Levy | Person_703 | 2012-04-19 | 2017-08-20 01:00 | 0.8 | 3.5298 | 2.8239 | Exploit | 0.8 | 3.5298 | 2.8239 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-62 | Project_022_RISK-62 | Threat | Project Contingency | Open | H3 | 3 | 8. Operations & Maintenance | Additional Costs from Integration Cost Centre | Person_703 | 2017-03-23 | 2017-05-14 | 0.5 | 7.1754 | 3.5877 | Avoid | 0.292 | 3.5877 | 1.0476 | H3 | 3 | Worsening | [10 empty] | 50 | 41.6 | 0 | 30
2017-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2017-06-21 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.35 | 2.8688 | 1.0041 | H2 | 4 | Stable | 0.7 | 89 | 128 | 143 | 124 | 0.4 | 12 | 40 | 65 | 39.5 | 22.0253 | 56.25 | 0 | 13.2152
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK003 | Project_024_RISK003 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance | Person_288 | 2017-12-21 01:00 | 2018-08-21 | 0.31667 | 2.3975 | 2.3975 | Accept | 0.007456 | 0 | 0 | H2 | 4 | Stable | 0.6 | 97 | 125 | 159 | 126 | 0.6 | 97 | 125 | 159 | 126 | 100 | 97.6455 | 0 | 60
2017-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2017-08-20 01:00 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 0.65554 | 0.52443 | H2 | 4 | Stable | [10 empty] | 80.45 | 0 | 0 | 48.27
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Management Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 0.3 | 3.8666 | 1.5853 | Accept | 0.3 | 1.3288 | 0.5448 | H1 | 5 | Improving | 0.6 | 103 | 135 | 146 | 131.5 | 0.6 | 103 | 135 | 146 | 131.5 | 65.6338 | 0 | 0 | 39.3803
2017-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2017-10-20 01:00 | 0.85 | 25.2325 | 21.4476 | Avoid | 0.08 | 8.5319 | 0.68255 | H2 | 4 | Stable | [10 empty] | 66.187 | 90.5882 | 0 | 39.7122
2017-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2017-10-20 01:00 | 0.7 | 24.1887 | 16.9321 | Reduce | 0.25 | 2.1783 | 0.54459 | H2 | 4 | Stable | 0.9 | 91 | 135 | 143 | 129 | 0.2 | 13 | 40 | 79 | 42 | 90.9944 | 64.2857 | 0 | 54.5966
2017-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-04-20 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.8 | 80 | 134 | 141 | 126.1667 | 0.1 | 24 | 54 | 65 | 50.8333 | 0 | 25 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment environmental failure | Person_710 | 2016-05-23 | 2017-09-19 01:00 | 0.3 | 3.4415 | 1.3766 | Accept | 0.3 | 3.4415 | 1.3766 | H1 | 5 | Improving | 0.6 | 102 | 129 | 145 | 127.1667 | 0.6 | 102 | 129 | 145 | 127.1667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK300(020) | Project_024_RISK300(020) | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Travel and onsite support | Person_119 | 2017-01-20 01:00 | 2018-04-21 | 0.25 | 8.0582 | 2.4175 | Accept | 0.25 | 8.0582 | 2.4175 | H3 | 3 | Stable | 0.9 | 99 | 124 | 158 | 125.5 | 0.9 | 99 | 124 | 158 | 125.5 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK304(026) | Project_024_RISK304(026) | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | complex integration | Person_119 | 2016-10-20 01:00 | 2018-01-20 01:00 | 0.4 | 0 | 0 | Accept | 0.4 | 0 | 0 | H1 | 5 | Worsening | 0.7 | 88 | 124 | 151 | 122.5 | 0.7 | 88 | 124 | 151 | 122.5 |  | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK303(025) | Project_024_RISK303(025) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in contract value from our supplier | Person_119 | 2016-10-20 01:00 | 2019-05-23 | 0.25 | 0.5596 | 0.05596 | Accept | 0.25 | 0.5596 | 0.05596 | H2 | 4 | Stable | 0.5 | 114 | 130 | 147 | 130.1667 | 0.5 | 114 | 130 | 147 | 130.1667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK305(027) | Project_024_RISK305(027) | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Customer Furnished Equipment not available on time | Person_119 | 2016-11-19 01:00 | 2019-05-23 | 0.3 | 3.6174 | 1.8087 | Accept | 0.3 | 3.6172 | 0.72345 | H1 | 5 | Stable | 0.5 | 80 | 131 | 155 | 126.5 | 0.5 | 80 | 131 | 155 | 126.5 | 0.0051359 | 0 | 0 | 0.0030815
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK296(013) | Project_024_RISK296(013) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Qualification/Certification Requirements flowdown | Person_119 | 2016-10-20 01:00 | 2017-08-20 01:00 | 0.25 | 2.3503 | 0.47006 | Accept | 0.25 | 2.3503 | 0.47006 | H2 | 4 | Worsening | 0.5 | 111 | 121 | 157 | 125.3333 | 0.5 | 111 | 121 | 157 | 125.3333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before part b finished | Person_119 | 2016-10-20 01:00 | 2018-04-21 | 0.35 | 4.4768 | 2.2384 | Accept | 0.35 | 4.4768 | 2.2384 | H2 | 4 | Worsening | 0.8 | 105 | 122 | 146 | 123.1667 | 0.8 | 105 | 122 | 146 | 123.1667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK298(016) | Project_024_RISK298(016) | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Environmental testing required | Person_119 | 2016-10-20 01:00 | 2017-10-20 01:00 | 0.2 | 76.7807 | 3.839 | Accept | 0.2 | 76.7807 | 3.839 | H2 | 4 | Stable | 0.6 | 91 | 138 | 142 | 130.8333 | 0.6 | 91 | 138 | 142 | 130.8333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK299(018) | Project_024_RISK299(018) | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Additional support hours | Person_119 | 2017-01-20 01:00 | 2018-04-21 | 0.35 | 23.5255 | 11.7628 | Accept | 0.35 | 23.5255 | 11.7628 | H3 | 3 | Stable | 0.6 | 101 | 121 | 141 | 121 | 0.6 | 101 | 121 | 141 | 121 | 0 | 0 | 1 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-19 21:00 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.5 | 111 | 138 | 142 | 134.1667 | 0.3 | 32 | 53 | 62 | 51 | 0 | 40 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-19 21:00 | 0.7 | 0.92411 | 0.64688 | Reduce | 0.3 | 0.36965 | 0.11089 | H2 | 4 | Stable | 0.5 | 109 | 130 | 143 | 128.6667 | 0.2 | 15 | 44 | 60 | 41.8333 | 60 | 57.1429 | 0 | 36
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-03 21:00 | 2016-04-21 | 0.5 | 4.0661 | 2.033 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.5 | 102 | 124 | 142 | 123.3333 | 0.1 | 6 | 51 | 67 | 46.1667 | 0 | 90 | 1 | 2.7
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-19 21:00 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.5 | 0.46206 | 0.23103 | H1 | 5 | Improving | 0.7 | 109 | 134 | 154 | 133.1667 | 0.4 | 34 | 51 | 64 | 50.3333 | 58.3333 | 16.6667 | 0 | 35
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-28 21:00 | 2017-08-19 21:00 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.6 | 100 | 135 | 148 | 131.3333 | 0.1 | 25 | 41 | 66 | 42.5 | 0 | 50 | 1 | 1.5
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-19 21:00 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.9 | 84 | 134 | 142 | 127 | 0.3 | 24 | 47 | 79 | 48.5 | 0 | 25 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Stable | 0.9 | 98 | 128 | 146 | 126 | 0.1 | 13 | 41 | 60 | 39.5 | 0 | 40 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-18 21:00 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Worsening | [10 empty] | 0 | 37.5 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 0.5 | 3.6965 | 0.36965 | Accept | 0.5 | 3.6965 | 0.36965 | H2 | 4 | Stable | 0.8 | 92 | 129 | 159 | 127.8333 | 0.8 | 92 | 129 | 159 | 127.8333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 0.5 | 0.92411 | 0.18482 | Accept | 0.5 | 0.92411 | 0.18482 | H2 | 4 | Stable | 0.6 | 103 | 138 | 149 | 134 | 0.6 | 103 | 138 | 149 | 134 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 1.8482 | 0.55447 | Accept | 0.5 | 1.8482 | 0.73929 | H2 | 4 | Stable | 0.6 | 116 | 132 | 145 | 131.5 | 0.6 | 116 | 132 | 145 | 131.5 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-19 21:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.5 | 80 | 126 | 151 | 122.5 | 0.2 | 8 | 43 | 64 | 40.6667 | 90 | 75 | 1 | 56.25
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unforseen and substantial increase in Repairs workload during new build production period. | Person_515 | 2017-10-23 01:00 | 2017-11-19 01:00 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.03 | 1.5434 | 0.046303 | H3 | 3 | Stable | 0.5 | 109 | 129 | 146 | 128.5 | 0.1 | 5 | 49 | 65 | 44.3333 | 0 | 90 | 1 | 2.7
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK007 | Project_041_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Advanced production of products using a Qual. standard component rather than a Prod. standard | Person_547 | 2017-10-21 01:00 | 2019-05-23 | 0.49 | 1.2862 | 0.63024 | Reduce | 0.2 | 1.2862 | 0.25724 | H3 | 3 | Stable | 0.5 | 96 | 121 | 142 | 120.3333 | 0.2 | 15 | 44 | 79 | 45 | 0 | 59.1837 | 1 | 1.7755
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_693 | 2017-05-23 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.9 | 101 | 136 | 146 | 131.8333 | 0.1 | 12 | 54 | 78 | 51 | 0 | 50 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2017-04-22 | 2018-05-22 | 0.75 | 10.7184 | 8.0388 | Reduce | 0.15 | 5.3592 | 0.80388 | H3 | 3 | Stable | 0.5 | 117 | 132 | 154 | 133.1667 | 0.3 | 33 | 49 | 72 | 50.1667 | 50 | 80 | 1 | 32.4
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 0.2 | 1.9722 | 0.98609 | Accept | 0.2 | 1.9722 | 0.98609 | H2 | 4 | Stable | 0.8 | 104 | 133 | 152 | 131.3333 | 0.8 | 104 | 133 | 152 | 131.3333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2017-05-23 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.05 | 0.68598 | 0.034299 | H3 | 3 | Stable | 0.5 | 117 | 130 | 151 | 131.3333 | 0.4 | 22 | 52 | 79 | 51.5 | 0 | 80 | 1 | 2.4
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 0.25 | 3.7514 | 0.37514 | Accept | 0.25 | 3.7514 | 0.37514 | H3 | 3 | Stable | 0.5 | 101 | 137 | 151 | 133.3333 | 0.5 | 101 | 137 | 151 | 133.3333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2017-05-23 | 2017-12-21 01:00 | 0.1 | 21.8655 | 2.1865 | Reduce | 0.01 | 21.8655 | 0.21865 | H2 | 4 | Stable | 0.8 | 85 | 122 | 142 | 119.1667 | 0.1 | 17 | 48 | 60 | 44.8333 | 0 | 90 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2017-05-23 | 2018-11-20 01:00 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Stable | 0.7 | 93 | 124 | 152 | 123.5 | 0.1 | 5 | 56 | 69 | 49.6667 | 0 | 60 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Unidentified CRs and concessions | Person_693 | 2017-04-22 | 2017-09-20 01:00 | 0.5 | 1.2005 | 0.60023 | Reduce | 0.15 | 0.51019 | 0.076529 | H3 | 3 | Stable | 0.8 | 107 | 127 | 146 | 126.8333 | 0.1 | 39 | 52 | 65 | 52 | 57.5001 | 70 | 1 | 36.6001
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_238 | 2017-04-22 | 2018-05-22 | 0.25 | 3.3227 | 0.83067 | Reduce | 0.05 | 3.3227 | 0.16613 | H3 | 3 | Stable | 0.6 | 93 | 128 | 154 | 126.5 | 0.2 | 11 | 41 | 78 | 42.1667 | 0 | 80 | 1 | 2.4
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_693 | 2017-05-23 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.1 | 0.77172 | 0.077172 | H3 | 3 | Worsening | 0.6 | 81 | 137 | 155 | 130.6667 | 0.1 | 5 | 45 | 70 | 42.5 | 0 | 60 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | More issues during Qualification including additional PRs | Person_147 | 2017-07-26 | 2017-11-04 01:00 | 0.35 | 1.7492 | 0.17492 | Accept | 0.35 | 1.7492 | 0.17492 | H1 | 5 | Stable | 0.7 | 111 | 130 | 145 | 129.3333 | 0.7 | 111 | 130 | 145 | 129.3333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_693 | 2017-05-23 | 2018-11-20 01:00 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.08 | 6.431 | 0.51448 | H3 | 3 | Improving | 0.7 | 88 | 139 | 152 | 132.6667 | 0.3 | 24 | 48 | 61 | 46.1667 | -47.0588 | 46.6667 | 1 | -26.8353
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Reduce touch labour if Production readiness programme successful | Person_238 | 2017-05-23 | 2017-10-21 01:00 | 0.3 | 1.5606 | 0.46818 | Exploit | 0.5 | 1.5606 | 0.7803 | H2 | 4 | Stable | [10 empty] | 0 | -66.6667 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2020-09-19 01:00 | 0.2 | 11.5901 | 5.795 | Accept | 0.2 | 11.5901 | 5.795 | H3 | 3 | Stable | 0.6 | 87 | 127 | 143 | 123 | 0.6 | 87 | 127 | 143 | 123 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2019-07-21 | 0.3 | 5.795 | 2.8975 | Accept | 0.2 | 5.795 | 2.8975 | H3 | 3 | Stable | 0.6 | 84 | 129 | 149 | 124.8333 | 0.6 | 84 | 129 | 149 | 124.8333 | 0 | 33.3333 | 1 | 1
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 1.4488 | 0.43463 | Accept | 0.1 | 1.4488 | 0.43463 | H3 | 3 | Stable | 0.9 | 94 | 127 | 150 | 125.3333 | 0.9 | 94 | 127 | 150 | 125.3333 | 0 | -233.3333 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 1.8765 | 0.93824 | Accept | 0.25 | 1.8765 | 0.93824 | H2 | 4 | Stable | 0.9 | 83 | 133 | 157 | 128.6667 | 0.9 | 83 | 133 | 157 | 128.6667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.5 | 108 | 130 | 154 | 130.3333 | 0.4 | 19 | 40 | 68 | 41.1667 | 25.8065 | 20 | 0 | 15.4839
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2017-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 22.384 | 11.192 | Accept | 0.3 | 22.384 | 11.192 | H2 | 4 | Stable | 0.5 | 86 | 140 | 150 | 132.6667 | 0.5 | 86 | 140 | 150 | 132.6667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Further Software Development | Person_523 | 2015-05-24 | 2018-02-18 01:00 | 0.1 | 3.772 | 2.6404 | Accept | 0.05 | 3.772 | 2.6404 | H3 | 3 | Stable | 0.9 | 106 | 140 | 149 | 135.8333 | 0.9 | 106 | 140 | 149 | 135.8333 | 0 | 50 | 1 | 1.5
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Interface implementation | Person_496 | 2014-01-21 01:00 | 2017-10-20 01:00 | 0.5 | 5.8198 | 4.0739 | Accept | 0.5 | 5.8198 | 4.0739 | H2 | 4 | Stable | 0.7 | 86 | 130 | 149 | 125.8333 | 0.7 | 86 | 130 | 149 | 125.8333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_523 | 2015-01-22 01:00 | 2018-02-18 01:00 | 0.35 | 0.11976 | 0.0059882 | Accept | 0.2 | 0.11976 | 0.0059882 | H2 | 4 | Stable | 0.8 | 100 | 130 | 148 | 128 | 0.8 | 100 | 130 | 148 | 128 | 0 | 42.8571 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_332 | 2016-06-23 | 2017-11-19 01:00 | 0.4 | 0.59882 | 0.059882 | Accept | 0.2 | 0.59882 | 0.059882 | H2 | 4 | Stable | 0.9 | 95 | 130 | 147 | 127 | 0.9 | 95 | 130 | 147 | 127 | 0 | 50 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-125 | Project_043_Risk-125 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | IOC Delayed due to a number of factors (Marching Customer Risk) | Person_084 | 2014-09-13 01:00 | 2019-01-21 01:00 | 0.5 | 1.9362 | 0.96809 | Reduce | 0.3 | 1.9362 | 0.58086 | H2 | 4 | Stable | 0.8 | 97 | 136 | 150 | 131.8333 | 0.4 | 3 | 52 | 68 | 46.5 | 0 | 40 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | RISK004 | Project_028_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Changes to be embodied on the Rig | Person_604 | 2017-04-29 | 2019-02-20 01:00 | 0.8 | 5.2705 | 1.5811 | Accept | 0.3 | 4.3921 | 0.87842 | H2 | 4 | Stable | 0.6 | 99 | 130 | 153 | 128.6667 | 0.6 | 99 | 130 | 153 | 128.6667 | 16.6667 | 62.5 | 0 | 10
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 11:00 | 2019-08-20 11:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 11:00 | 2019-08-20 11:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 11:00 | 2019-08-20 11:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 11:00 | 2019-08-20 11:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 11:00 | 2019-08-20 11:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_002 | BA_004 | Portfolio_010 | Project_046 | PRO004 | Project_046_PRO004 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | High Material Atrition Level | Person_025 | 2016-06-14 | 2017-11-20 01:00 | 0.5 | 1.618 | 0.80901 | Reduce | 0.5 | 1.618 | 0.80901 | H1 | 5 | Stable | 0.8 | 110 | 126 | 160 | 129 | 0.3 | 4 | 58 | 68 | 50.6667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-128 | Project_011_Risk-128 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Incorrect Maps used during Qualification | Person_147 | 2017-04-22 | 2018-01-21 01:00 | 0.5 | 0.05688 | 0.02844 | Transfer | 0.5 | 0.05688 | 0.02844 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-129 | Project_011_Risk-129 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Signature of Work Authorisation documents | Person_140 | 2017-05-24 | 2018-01-21 01:00 | 0.4 | 0 | 0 | -- | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-130 | Project_011_Risk-130 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer does not accept Voice Pronounciation | Person_187 | 2017-05-24 | 2018-02-19 01:00 | 0.2 | 0.090918 | 0.018184 | Avoid | 0.2 | 0.090918 | 0.018184 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_002 | BA_005 | Portfolio_011 | Project_047 | RISK006 | Project_047_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer find issues with delivered parts | Person_454 | 2017-05-23 | 2017-08-19 01:00 | 0.8 | 1.2591 | 1.0073 | Reduce | 0.4 | 1.2591 | 0.50365 | H3 | 3 | Improving | 0.7 | 95 | 127 | 146 | 124.8333 | 0.2 | 9 | 53 | 79 | 50 | 0 | 50 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-149 | Project_020_Risk-149 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs to be returned to UK | Person_703 | 2016-12-21 01:00 | 2017-11-19 01:00 | 0.2 | 8.8959 | 4.448 | Accept | 0.05 | 8.8959 | 4.448 | H2 | 4 | Stable | 0.5 | 98 | 140 | 142 | 133.3333 | 0.5 | 98 | 140 | 142 | 133.3333 | 0 | 75 | 0 | 0
2017-07-21 | ORG_002 | BA_005 | Portfolio_011 | Project_047 | RISK009 | Project_047_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Open PR's | Person_647 | 2017-04-22 | 2018-11-20 01:00 | 0.5 | 0.51323 | 0.25661 | Reduce | 0.3 | 0.51323 | 0.15397 | H2 | 4 | Improving | 0.5 | 84 | 123 | 160 | 122.6667 | 0.4 | 16 | 46 | 61 | 43.5 | 0 | 40 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Non-Recurring Engineering higher than expected | Person_510 | 2016-06-01 | 2016-08-20 01:00 | 0.5 | 13.3382 | 6.6691 | Reduce | 0.5 | 13.3382 | 6.6691 | H2 | 4 | Improving | 0.5 | 108 | 140 | 150 | 136.3333 | 0.3 | 25 | 54 | 60 | 50.1667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2017-05-22 | 0.41 | 5.3353 | 1.0671 | Accept | 0.41 | 5.3353 | 1.0671 | H2 | 4 | Stable | 0.9 | 82 | 122 | 150 | 120 | 0.9 | 82 | 122 | 150 | 120 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-12-21 01:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.8 | 107 | 133 | 147 | 131 | 0.4 | 38 | 49 | 69 | 50.5 | 47 | 0 | 0 | 28.2
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-12-21 01:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-19 01:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.2 | 1.5935 | 0.3187 | H3 | 3 | Stable | 0.6 | 93 | 130 | 150 | 127.1667 | 0.2 | 29 | 40 | 65 | 42.3333 | 50 | 50 | 1 | 31.5
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 0.4 | 9.139 | 3.6556 | Avoid | 0.2 | 9.139 | 1.8278 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 0.125 | 232.2192 | 29.0274 | -- | 0.215 | 27.8663 | 5.9913 | H2 | 4 | Stable | [10 empty] | 88 | -72 | 0 | 52.8
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 0.5 | 13.7833 | 6.8917 | Avoid | 0.2 | 6.8917 | 1.3783 | H3 | 3 | Stable | [10 empty] | 50 | 60 | 1 | 31.8
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-20 01:00 | 0.3 | 5.5433 | 1.663 | Reduce | 0.35 | 5.5433 | 1.9402 | H2 | 4 | Worsening | 0.6 | 86 | 134 | 154 | 129.3333 | 0.2 | 39 | 50 | 62 | 50.1667 | 0 | -16.6667 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Worsening | [10 empty] | 0 | 75 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 0.3 | 26.9674 | 8.0902 | Avoid | 0.3 | 14.9819 | 4.4946 | H2 | 4 | Stable | [10 empty] | 44.4444 | 0 | 0 | 26.6667
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-21 01:00 | 0.5 | 26.9674 | 13.4837 | Avoid | 0.1 | 12.7646 | 1.2765 | H2 | 4 | Worsening | [10 empty] | 52.6667 | 80 | 0 | 31.6
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.9 | 93 | 136 | 160 | 132.8333 | 0.3 | 2 | 58 | 79 | 52.1667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-20 22:00 | 2016-08-20 22:00 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.5 | 86 | 133 | 158 | 129.3333 | 0.2 | 24 | 57 | 67 | 53.1667 | 0 | 16.6667 | 0 | 0
2017-07-21 | ORG_002 | BA_005 | Portfolio_011 | Project_047 | RISK078 | Project_047_RISK078 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer find issues with delivered parts. | Person_236 | 2017-04-22 | 2018-10-20 01:00 | 0.9 | 20.2553 | 18.2298 | Reduce | 0.35 | 10.1277 | 3.5447 | H3 | 3 | Improving | 0.6 | 114 | 131 | 153 | 131.8333 | 0.4 | 3 | 48 | 66 | 43.5 | 50 | 61.1111 | 0 | 30
2017-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2017-11-19 01:00 | 0.05 | 35.0206 | 7.0041 | Accept | 0.05 | 35.0206 | 7.0041 | H3 | 3 | Improving | 0.9 | 117 | 131 | 158 | 133.1667 | 0.9 | 117 | 131 | 158 | 133.1667 | 0 | 0 | 1 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-19 21:00 | 0.05 | 0 | 0 | Accept | 0.05 | 0 | 0 | H2 | 4 | Stable | 0.8 | 100 | 126 | 158 | 127 | 0.8 | 100 | 126 | 158 | 127 |  | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 0.8 | 0 | 0 | Accept | 0.6 | 0 | 0 | H1 | 5 | Stable | 0.7 | 96 | 130 | 158 | 129 | 0.7 | 96 | 130 | 158 | 129 |  | 25 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 19:00 | 2019-08-20 19:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.9 | 85 | 130 | 151 | 126 | 0.1 | 10 | 49 | 62 | 44.6667 | 83.3333 | 88.8889 | 1 | 52.6667
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.6 | 107 | 139 | 155 | 136.3333 | 0.3 | 20 | 58 | 74 | 54.3333 | 72 | 0 | 0 | 43.2
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.9 | 96 | 123 | 152 | 123.3333 | 0.4 | 27 | 55 | 78 | 54.1667 | 47.7391 | 0 | 0 | 28.6435
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 19:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.8 | 113 | 136 | 142 | 133.1667 | 0.1 | 17 | 44 | 60 | 42.1667 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.8 | 96 | 139 | 150 | 133.6667 | 0.3 | 32 | 44 | 77 | 47.5 | 0 | 0 | 1 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-26 21:00 | 2016-08-19 21:00 | 0.1 | 13.3529 | 6.6765 | Accept | 0.1 | 23.5716 | 11.7858 | H2 | 4 | Stable | 0.9 | 91 | 133 | 145 | 128 | 0.9 | 91 | 133 | 145 | 128 | -76.5278 | 0 | 0 | -45.9167
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 0.5 | 9.2728 | 4.6364 | Reduce | 0.15 | 9.2728 | 1.3909 | H2 | 4 | Stable | 0.9 | 80 | 138 | 159 | 131.8333 | 0.2 | 21 | 40 | 67 | 41.3333 | 0 | 70 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R008 | Project_016_Risk--R008 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Additional Travel & Subsistence | Person_574 | 2016-01-12 23:00 | 2019-05-23 | 0.4 | 8.9019 | 3.5608 | Reduce | 0.25 | 8.9019 | 2.2255 | H3 | 3 | Stable | 0.9 | 107 | 140 | 156 | 137.1667 | 0.1 | 28 | 42 | 64 | 43.3333 | 0 | 37.5 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-12 23:00 | 2017-08-19 23:00 | 0.3 | 8.7814 | 2.6344 | Reduce | 0.15 | 8.7832 | 1.3175 | H3 | 3 | Stable | 0.7 | 117 | 137 | 150 | 135.8333 | 0.2 | 26 | 57 | 79 | 55.5 | -0.021119 | 50 | 1 | 1.4873
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R009 | Project_016_Risk--R009 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer maybe difficult to work with | Person_697 | 2016-04-02 | 2019-08-01 | 0.6 | 23.9549 | 14.3729 | Reduce | 0.43864 | 23.8312 | 10.4533 | H2 | 4 | Stable | 0.8 | 106 | 136 | 153 | 133.8333 | 0.2 | 15 | 49 | 64 | 45.8333 | 0.51612 | 26.8938 | 0 | 0.30967
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-18 21:00 | 0.2 | 108.3186 | 32.4956 | Accept | 0.2 | 108.3186 | 32.4956 | H3 | 3 | Improving | 0.5 | 100 | 136 | 142 | 131 | 0.5 | 100 | 136 | 142 | 131 | 0 | 0 | 1 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Delay of processing | Person_306 | 2016-04-02 | 2017-03-20 23:00 | 0.15 | 26.3497 | 3.9525 | Reduce | 0.15 | 13.1767 | 1.9765 | H3 | 3 | Stable | 0.9 | 93 | 131 | 144 | 126.8333 | 0.1 | 20 | 47 | 73 | 46.8333 | 49.993 | 0 | 1 | 29.9958
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 0.3 | 12.0547 | 2.4109 | Accept | 0.4 | 12.0547 | 2.4109 | H3 | 3 | Stable | 0.7 | 80 | 122 | 157 | 120.8333 | 0.7 | 80 | 122 | 157 | 120.8333 | 0 | -33.3333 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Non-Recurring Engineering higher than expected | Person_510 | 2016-06-01 | 2016-08-20 | 0.5 | 13.3382 | 6.6691 | Reduce | 0.5 | 13.3382 | 6.6691 | H2 | 4 | Improving | 0.8 | 82 | 129 | 145 | 123.8333 | 0.3 | 4 | 44 | 74 | 42.3333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Risk of not being able to perform Tests | Person_238 | 2017-12-21 01:00 | 2019-01-21 01:00 | 0.5 | 4.8729 | 3.8983 | Accept | 0.5 | 4.8729 | 3.8983 | H2 | 4 | Stable | 0.6 | 95 | 135 | 142 | 129.5 | 0.6 | 95 | 135 | 142 | 129.5 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_238 | 2017-05-23 | 2019-01-21 01:00 | 0.5 | 5.3353 | 1.0671 | Accept | 0.5 | 5.3353 | 1.0671 | H2 | 4 | Stable | 0.7 | 109 | 127 | 152 | 128.1667 | 0.7 | 109 | 127 | 152 | 128.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 | 0.4 | 9.139 | 3.6556 | Avoid | 0.2 | 9.139 | 1.8278 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 | 2016-12-21 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.7 | 108 | 140 | 157 | 137.5 | 0.2 | 22 | 55 | 72 | 52.3333 | 47 | 0 | 0 | 28.2
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Product Baseline delivery is late | Person_151 | 2015-09-21 | 2017-02-13 | 0.125 | 232.2192 | 29.0274 | -- | 0.215 | 27.8663 | 5.9913 | H2 | 4 | Stable | [10 empty] | 88 | -72 | 0 | 52.8
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 | 2016-12-21 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 0.5 | 13.7833 | 6.8917 | Avoid | 0.2 | 6.8917 | 1.3783 | H3 | 3 | Stable | [10 empty] | 50 | 60 | 1 | 31.8
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-19 | 0.4 | 3.187 | 1.2748 | Reduce | 0.2 | 1.5935 | 0.3187 | H3 | 3 | Stable | 0.8 | 95 | 130 | 148 | 127.1667 | 0.4 | 28 | 45 | 69 | 46.1667 | 50 | 50 | 1 | 31.5
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-20 | 0.3 | 5.5433 | 1.663 | Reduce | 0.35 | 5.5433 | 1.9402 | H2 | 4 | Worsening | 0.5 | 103 | 121 | 146 | 122.1667 | 0.1 | 26 | 41 | 66 | 42.6667 | 0 | -16.6667 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 | 2016-11-20 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Worsening | [10 empty] | 0 | 75 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_693 | 2017-04-22 | 2017-09-19 01:00 | 0.6 | 4.4946 | 1.1236 | Accept | 0.3 | 4.4946 | 0.44946 | H3 | 3 | Worsening | 0.8 | 94 | 126 | 157 | 125.8333 | 0.8 | 94 | 126 | 157 | 125.8333 | 0 | 50 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_547 | 2017-05-23 | 2018-05-22 | 0.1 | 6.7418 | 1.6855 | Accept | 0.1 | 6.7418 | 1.0113 | H3 | 3 | Stable | 0.5 | 88 | 123 | 142 | 120.3333 | 0.5 | 88 | 123 | 142 | 120.3333 | 0 | 0 | 1 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 0.3 | 26.9674 | 8.0902 | Avoid | 0.3 | 14.9819 | 4.4946 | H2 | 4 | Stable | [10 empty] | 44.4444 | 0 | 0 | 26.6667
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-21 | 0.5 | 26.9674 | 13.4837 | Avoid | 0.1 | 12.7646 | 1.2765 | H2 | 4 | Worsening | [10 empty] | 52.6667 | 80 | 0 | 31.6
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK021 | Project_021_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | ERP implementation | Person_174 | 2017-06-23 | 2017-09-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.25 | 0 | 0 | H2 | 4 | Stable | 0.7 | 97 | 134 | 159 | 132 | 0.1 | 4 | 51 | 77 | 47.5 |  | 50 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_174 | 2012-11-20 01:00 | 2018-08-21 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.8 | 81 | 138 | 144 | 129.5 | 0.2 | 18 | 55 | 75 | 52.1667 | 0 | 50 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK024 | Project_021_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_482 | 2017-05-23 | 2017-11-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 107 | 122 | 143 | 123 | 0.4 | 12 | 46 | 61 | 42.8333 |  | 40 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2018-02-19 01:00 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Stable | 0.5 | 88 | 137 | 158 | 132.3333 | 0.3 | 16 | 47 | 74 | 46.3333 | 0 | 57.1429 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 0.8 | 4.6352 | 3.7081 | Reduce | 0.6 | 4.6352 | 2.7811 | H1 | 5 | Worsening | 0.8 | 107 | 133 | 142 | 130.1667 | 0.1 | 35 | 42 | 72 | 45.8333 | 0 | 25 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-12-20 01:00 | 0.6 | 17.2826 | 10.3696 | Reduce | 0.3 | 17.2826 | 5.1848 | H2 | 4 | Worsening | 0.5 | 112 | 124 | 156 | 127.3333 | 0.3 | 14 | 57 | 67 | 51.5 | 0 | 50 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Additional tasks required with mode certification | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 0.8 | 1.3243 | 1.0595 | Reduce | 0.6 | 1.3243 | 0.7946 | H1 | 5 | Worsening | 0.7 | 102 | 124 | 160 | 126.3333 | 0.1 | 25 | 41 | 69 | 43 | 0 | 25 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2018-01-19 01:00 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.8 | 110 | 137 | 147 | 134.1667 | 0.4 | 11 | 49 | 75 | 47 | 80 | 66.6667 | 0 | 48
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond (revised) target. | Person_482 | 2013-01-07 01:00 | 2018-02-04 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.9 | 102 | 128 | 142 | 126 | 0.4 | 30 | 44 | 75 | 46.8333 | 0 | 33.3333 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2013-01-07 01:00 | 2017-11-19 01:00 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.8 | 88 | 128 | 153 | 125.5 | 0.3 | 32 | 48 | 65 | 48.1667 | 0 | 33.3333 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_174 | 2009-06-23 | 2018-08-21 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.6 | 104 | 139 | 145 | 134.1667 | 0.3 | 20 | 51 | 65 | 48.1667 | 50 | 28.5714 | 0 | 30
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-09-19 01:00 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.7 | 107 | 128 | 152 | 128.5 | 0.3 | 9 | 50 | 67 | 46 | 7.8429 | 40 | 0 | 4.7058
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-12-17 01:00 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.4 | 12.6474 | 5.059 | H2 | 4 | Stable | 0.8 | 87 | 131 | 151 | 127 | 0.3 | 15 | 51 | 60 | 46.5 | 0 | 33.3333 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.8 | 118 | 140 | 160 | 139.6667 | 0.2 | 21 | 41 | 77 | 43.6667 | 0 | 50 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unforseen and substantial increase in Repairs workload during new build production period. | Person_515 | 2017-10-23 01:00 | 2017-11-19 01:00 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.03 | 1.5434 | 0.046303 | H3 | 3 | Stable | 0.6 | 107 | 124 | 156 | 126.5 | 0.2 | 4 | 55 | 65 | 48.1667 | 0 | 90 | 1 | 2.7
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK007 | Project_041_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Advanced production of products using a Qual. standard component rather than a Prod. standard | Person_547 | 2017-10-21 01:00 | 2019-05-23 | 0.49 | 1.2862 | 0.63024 | Reduce | 0.2 | 1.2862 | 0.25724 | H3 | 3 | Stable | 0.6 | 90 | 131 | 159 | 128.8333 | 0.1 | 25 | 47 | 75 | 48 | 0 | 59.1837 | 1 | 1.7755
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_693 | 2017-05-23 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.6 | 84 | 126 | 149 | 122.8333 | 0.3 | 29 | 55 | 70 | 53.1667 | 0 | 50 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2017-04-22 | 2018-05-22 | 0.75 | 10.7184 | 8.0388 | Reduce | 0.15 | 5.3592 | 0.80388 | H3 | 3 | Stable | 0.9 | 90 | 131 | 145 | 126.5 | 0.1 | 22 | 45 | 62 | 44 | 50 | 80 | 1 | 32.4
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production, Procurement or Engineering | Person_725 | 2018-01-21 01:00 | 2019-05-23 | 0.1 | 1.9722 | 0.98609 | Accept | 0.1 | 1.9722 | 0.98609 | H3 | 3 | Worsening | 0.6 | 93 | 129 | 152 | 126.8333 | 0.6 | 93 | 129 | 152 | 126.8333 | 0 | 0 | 1 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2017-05-23 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.05 | 0.68598 | 0.034299 | H3 | 3 | Stable | 0.9 | 93 | 140 | 156 | 134.8333 | 0.3 | 1 | 55 | 68 | 48.1667 | 0 | 80 | 1 | 2.4
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2017-05-23 | 2017-12-21 01:00 | 0.1 | 21.8655 | 2.1865 | Reduce | 0.01 | 21.8655 | 0.21865 | H2 | 4 | Stable | 0.9 | 91 | 139 | 148 | 132.5 | 0.1 | 18 | 55 | 68 | 51 | 0 | 90 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2017-05-23 | 2018-11-20 01:00 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Stable | 0.6 | 104 | 122 | 157 | 124.8333 | 0.3 | 26 | 44 | 66 | 44.6667 | 0 | 60 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Unidentified CRs and concessions | Person_693 | 2017-04-22 | 2017-09-20 01:00 | 0.5 | 1.2005 | 0.60023 | Reduce | 0.15 | 0.51019 | 0.076529 | H3 | 3 | Stable | 0.9 | 103 | 128 | 156 | 128.5 | 0.1 | 18 | 57 | 66 | 52 | 57.5001 | 70 | 1 | 36.6001
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_238 | 2017-04-22 | 2018-05-22 | 0.25 | 3.3227 | 0.83067 | Reduce | 0.05 | 3.3227 | 0.16613 | H3 | 3 | Stable | 0.5 | 90 | 128 | 148 | 125 | 0.3 | 5 | 59 | 79 | 53.3333 | 0 | 80 | 1 | 2.4
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_693 | 2017-05-23 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.1 | 0.77172 | 0.077172 | H3 | 3 | Worsening | 0.9 | 100 | 123 | 154 | 124.3333 | 0.4 | 38 | 51 | 72 | 52.3333 | 0 | 60 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_009 | Project_045 | RISK001 | Project_045_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Generic Labour or Expense overspend | Person_662 | 2017-10-21 01:00 | 2019-05-23 | 0.5 | 1.7492 | 0.17492 | Accept | 0.5 | 1.7492 | 0.17492 | H2 | 4 | Stable | 0.5 | 106 | 131 | 156 | 131 | 0.5 | 106 | 131 | 156 | 131 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_693 | 2017-05-23 | 2018-11-20 01:00 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.08 | 6.431 | 0.51448 | H3 | 3 | Improving | 0.9 | 100 | 140 | 151 | 135.1667 | 0.2 | 9 | 44 | 64 | 41.5 | -47.0588 | 46.6667 | 1 | -26.8353
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Reduce touch labour if Production readiness programme successful | Person_238 | 2017-05-23 | 2017-10-21 01:00 | 0.3 | 1.5606 | 0.46818 | Exploit | 0.5 | 1.5606 | 0.7803 | H2 | 4 | Stable | [10 empty] | 0 | -66.6667 | 0 | 0
2017-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-04-20 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.5 | 100 | 130 | 150 | 128.3333 | 0.4 | 5 | 50 | 63 | 44.6667 | 0 | 25 | 0 | 0
2017-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_077 | 2016-01-22 01:00 | 2018-02-17 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H1 | 5 | Improving | 0.5 | 118 | 121 | 153 | 125.8333 | 0.2 | 7 | 42 | 66 | 40.1667 |  | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-026 | Project_043_Risk-026 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Equipment Delivery | Person_693 | 2017-04-19 | 2017-10-19 01:00 | 0.25 | 60.4367 | 3.0218 | Accept | 0.25 | 60.4367 | 3.0218 | H2 | 4 | Improving | 0.8 | 104 | 133 | 152 | 131.3333 | 0.8 | 104 | 133 | 152 | 131.3333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2018-04-21 | 0.15 | 0.58983 | 0.088474 | -- | 0.15 | 0.58983 | 0.088474 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 0.2 | 0.62279 | 0.12456 | Avoid | 0.2 | 0.62279 | 0.12456 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2017-09-20 01:00 | 2018-04-21 | 0.15 | 0.28639 | 0.042959 | -- | 0.15 | 0.28639 | 0.042959 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-11-19 01:00 | 0.1 | 0.27503 | 0.027503 | -- | 0.1 | 0.27503 | 0.027503 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 0.2 | 1.8854 | 0.37708 | Reduce | 0.2 | 1.8854 | 0.37708 | H2 | 4 | Stable | 0.7 | 108 | 140 | 147 | 135.8333 | 0.1 | 24 | 56 | 73 | 53.5 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2017-10-21 01:00 | 2018-08-21 | 0.4 | 1.4138 | 0.56551 | Reduce | 0.4 | 1.4138 | 0.56551 | H2 | 4 | Stable | 0.9 | 110 | 126 | 154 | 128 | 0.1 | 22 | 55 | 61 | 50.5 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 01:00 | 2016-11-20 01:00 | 0.25 | 0.18354 | 0.045885 | Accept | 0.1 | 0.18354 | 0.045885 | H3 | 3 | Stable | 0.8 | 109 | 137 | 151 | 134.6667 | 0.8 | 109 | 137 | 151 | 134.6667 | 0 | 60 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-20 01:00 | 0.25 | 0.11081 | 0.011081 | Accept | 0.15 | 0.11081 | 0.011081 | H3 | 3 | Stable | 0.9 | 107 | 121 | 156 | 124.5 | 0.9 | 107 | 121 | 156 | 124.5 | 0 | 40 | 1 | 1.2
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-10-19 01:00 | 2018-08-21 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.7 | 85 | 137 | 144 | 129.5 | 0.1 | 4 | 45 | 63 | 41.1667 |  | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Pick up and Drop off of Software Resource | Person_230 | 2017-12-19 01:00 | 2018-02-19 01:00 | 0.4 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 0.4 | 0.19206 | 0.076826 | -- | 0.4 | 0.19206 | 0.076826 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 0.4 | 0.58017 | 0.23207 | Avoid | 0.4 | 0.58017 | 0.23207 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-20 22:00 | 2019-08-20 | 0.5 | 0.49834 | 0.12459 | Accept | 0.5 | 0.49834 | 0.12459 | H2 | 4 | Stable | 0.5 | 82 | 135 | 160 | 130.3333 | 0.5 | 82 | 135 | 160 | 130.3333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.2 | 0.11365 | 0.022729 | -- | 0.2 | 0.11365 | 0.022729 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 0.55 | 0.32389 | 0.17814 | Reduce | 0.55 | 0.32389 | 0.17814 | H1 | 5 | Stable | 0.6 | 115 | 126 | 148 | 127.8333 | 0.2 | 31 | 52 | 78 | 52.8333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2017-10-21 01:00 | 2018-05-21 | 0.4 | 0.19206 | 0.076826 | -- | 0.4 | 0.19206 | 0.076826 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 0.3 | 0.11933 | 0.035799 | -- | 0.3 | 0.022161 | 0.0066484 | H3 | 3 | Stable | [10 empty] | 81.4286 | 0 | 0 | 48.8571
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.2 | 1.1416 | 0.68495 | Accept | 0.2 | 1.1416 | 0.68495 | H3 | 3 | Stable | 0.6 | 81 | 123 | 157 | 121.6667 | 0.6 | 81 | 123 | 157 | 121.6667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-117 | Project_011_Risk-117 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Avaliability for testing/reviews | Person_147 | 2016-07-21 | 2018-08-21 | 0.35 | 0 | 0 | Avoid | 0.35 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-128 | Project_011_Risk-128 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Incorrect Maps used during Qualification | Person_147 | 2017-04-22 | 2018-01-21 01:00 | 0.5 | 0.05688 | 0.02844 | Transfer | 0.5 | 0.05688 | 0.02844 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-129 | Project_011_Risk-129 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Signature of Work Authorisation documents | Person_140 | 2017-05-24 | 2018-01-21 01:00 | 0.2 | 0.12643 | 0.025287 | -- | 0.2 | 0.12643 | 0.025287 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-130 | Project_011_Risk-130 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer does not accept Voice Pronounciation | Person_187 | 2017-05-24 | 2018-02-19 01:00 | 0.4 | 0.090918 | 0.036367 | Avoid | 0.4 | 0.090918 | 0.036367 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 1.8788 | 0.18788 | Accept | 0.35 | 1.8788 | 0.18788 | H3 | 3 | Stable | 0.8 | 111 | 124 | 146 | 125.5 | 0.8 | 111 | 124 | 146 | 125.5 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 | 2017-08-20 | 0.1 | 53.0293 | 5.3029 | Reduce | 0.1 | 53.0293 | 5.3029 | H3 | 3 | Worsening | 0.5 | 111 | 122 | 145 | 124 | 0.3 | 15 | 40 | 61 | 39.3333 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.25 | 0.20788 | 0.068599 | Accept | 0.25 | 0.052336 | 0.0057569 | H3 | 3 | Stable | 0.7 | 103 | 140 | 142 | 134.1667 | 0.7 | 103 | 140 | 142 | 134.1667 | 74.8236 | 0 | 0 | 44.8942
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 | 2017-08-20 | 0.1 | 7.7469 | 0.77469 | Reduce | 0.1 | 7.7469 | 0.77469 | H3 | 3 | Stable | 0.8 | 95 | 134 | 156 | 131.1667 | 0.3 | 12 | 59 | 76 | 54 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software issue input | Person_084 | 2016-11-22 23:00 | 2023-02-19 23:00 | 0.4 | 11.3437 | 0.56718 | Accept | 0.2 | 11.3437 | 0.56718 | H2 | 4 | Stable | 0.5 | 102 | 140 | 143 | 134.1667 | 0.5 | 102 | 140 | 143 | 134.1667 | 0 | 50 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-148 | Project_020_Risk-148 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs non-available items | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.3 | 14.9935 | 4.498 | Reduce | 0.3 | 1.1374 | 0.34121 | H2 | 4 | Stable | 0.8 | 82 | 128 | 154 | 124.6667 | 0.4 | 6 | 58 | 76 | 52.3333 | 92.4143 | 0 | 0 | 55.4486
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 2.2492 | 0.8997 | H2 | 4 | Stable | 0.5 | 93 | 135 | 158 | 131.8333 | 0.3 | 5 | 43 | 68 | 40.8333 | 43.1818 | 20 | 0 | 25.9091
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Volume of production tools and Jigs | Person_084 | 2016-11-22 23:00 | 2021-11-22 23:00 | 0.35 | 18.6688 | 3.7338 | Accept | 0.2 | 13.7328 | 0.54931 | H2 | 4 | Stable | 0.5 | 115 | 124 | 143 | 125.6667 | 0.5 | 115 | 124 | 143 | 125.6667 | 26.4398 | 42.8571 | 0 | 15.8639
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-147 | Project_020_Risk-147 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component taking longer to refurbish in country | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 0.6 | 6.7477 | 4.0486 | Reduce | 0.6 | 0.74972 | 0.44983 | H2 | 4 | Stable | 0.9 | 119 | 129 | 160 | 132.5 | 0.1 | 7 | 43 | 77 | 42.6667 | 88.8893 | 0 | 0 | 53.3336
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_703 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 5.0983 | 0.76474 | H3 | 3 | Stable | 0.8 | 117 | 132 | 144 | 131.5 | 0.1 | 28 | 54 | 72 | 52.6667 | 19.0479 | 70 | 1 | 13.5287
2017-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-63 | Project_022_RISK-63 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Levy | Person_703 | 2012-04-19 | 2017-08-20 | 0.8 | 3.5298 | 2.8239 | Exploit | 0.8 | 3.5298 | 2.8239 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-62 | Project_022_RISK-62 | Threat | Project Contingency | Open | H3 | 3 | 8. Operations & Maintenance | Additional Costs from Integration Cost Centre | Person_703 | 2017-03-23 | 2017-05-14 | 0.5 | 7.1754 | 3.5877 | Avoid | 0.292 | 3.5877 | 1.0476 | H3 | 3 | Worsening | [10 empty] | 50 | 41.6 | 0 | 30
2017-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2017-06-21 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.35 | 2.8688 | 1.0041 | H2 | 4 | Stable | 0.7 | 115 | 127 | 146 | 128.1667 | 0.4 | 20 | 45 | 75 | 45.8333 | 22.0253 | 56.25 | 0 | 13.2152
2017-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK040 | Project_017_RISK040 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Upgrades | Person_084 | 2016-09-29 23:00 | 2016-12-17 23:00 | 0.35 | 2.3975 | 2.3975 | Accept | 0.35 | 0 | 0 | H2 | 4 | Stable | 0.9 | 107 | 124 | 154 | 126.1667 | 0.9 | 107 | 124 | 154 | 126.1667 | 100 | 0 | 0 | 60
2017-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2017-08-20 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 0.65554 | 0.52443 | H2 | 4 | Stable | [10 empty] | 80.45 | 0 | 0 | 48.27
2017-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test & Acceptance | Person_277 | 2013-09-28 | 2017-10-20 | 0.7 | 24.1887 | 16.9321 | Reduce | 0.25 | 2.1783 | 0.54459 | H2 | 4 | Stable | 0.7 | 119 | 126 | 146 | 128.1667 | 0.4 | 9 | 54 | 67 | 48.6667 | 90.9944 | 64.2857 | 0 | 54.5966
2017-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2017-10-20 | 0.85 | 25.2325 | 21.4476 | Avoid | 0.08 | 8.5319 | 0.68255 | H2 | 4 | Stable | [10 empty] | 66.187 | 90.5882 | 0 | 39.7122
2017-08-21 | ORG_002 | BA_005 | Portfolio_011 | Project_047 | RISK006 | Project_047_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer find issues with delivered parts | Person_454 | 2017-05-23 | 2017-08-19 | 0.8 | 1.2591 | 1.0073 | Reduce | 0.4 | 1.2591 | 0.50365 | H3 | 3 | Improving | 0.7 | 101 | 139 | 148 | 134.1667 | 0.2 | 23 | 53 | 61 | 49.3333 | 0 | 50 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 0.61 | 8.8959 | 4.448 | Accept | 0.61 | 8.8959 | 4.448 | H1 | 5 | Stable | 0.9 | 100 | 137 | 147 | 132.5 | 0.9 | 100 | 137 | 147 | 132.5 | 0 | 0 | 0 | 0
2017-08-21 | ORG_002 | BA_005 | Portfolio_011 | Project_047 | RISK009 | Project_047_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Open PR's | Person_647 | 2017-04-22 | 2018-11-20 | 0.5 | 0.51323 | 0.25661 | Reduce | 0.3 | 0.51323 | 0.15397 | H2 | 4 | Improving | 0.9 | 107 | 121 | 156 | 124.5 | 0.4 | 31 | 41 | 70 | 44.1667 | 0 | 40 | 0 | 0
2017-08-21 | ORG_002 | BA_005 | Portfolio_011 | Project_047 | RISK078 | Project_047_RISK078 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer find issues with delivered parts. | Person_236 | 2017-04-22 | 2018-10-20 | 0.9 | 20.2553 | 18.2298 | Reduce | 0.35 | 10.1277 | 3.5447 | H3 | 3 | Improving | 0.6 | 110 | 135 | 152 | 133.6667 | 0.1 | 35 | 54 | 71 | 53.6667 | 50 | 61.1111 | 0 | 30
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 0.5 | 1.2198 | 0.60991 | Accept | 0.5 | 1.2198 | 0.60991 | H2 | 4 | Improving | 0.6 | 83 | 133 | 159 | 129 | 0.6 | 83 | 133 | 159 | 129 | 0 | 0 | 0 | 0
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-20 23:00 | 0.3 | 6.0991 | 0 | Accept | 0.3 | 6.0991 | 4.0864 | H2 | 4 | Stable | 0.7 | 114 | 140 | 159 | 138.8333 | 0.7 | 114 | 140 | 159 | 138.8333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PEN Testing Security Features | Person_604 | 2015-04-11 | 2018-01-20 01:00 | 0.3 | 5.4553 | 1.6366 | Reduce | 0.2 | 5.252 | 1.0504 | H2 | 4 | Stable | 0.8 | 92 | 127 | 155 | 125.8333 | 0.1 | 34 | 59 | 78 | 58 | 3.7267 | 33.3333 | 0 | 2.236
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Platforms Cable and connectors | Person_499 | 2015-11-21 01:00 | 2019-04-10 | 0.45 | 0.41338 | 0.18602 | Reduce | 0.05 | 0.41338 | 0.020669 | H2 | 4 | Stable | 0.9 | 80 | 121 | 149 | 118.8333 | 0.4 | 23 | 40 | 79 | 43.6667 | 0 | 88.8889 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | FOC Acceptance | Person_499 | 2015-11-21 01:00 | 2018-02-18 01:00 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.3 | 8.471 | 2.5413 | H2 | 4 | Stable | 0.9 | 103 | 124 | 155 | 125.6667 | 0.1 | 30 | 49 | 75 | 50.1667 | -99.9999 | 14.2857 | 0 | -59.9999
2017-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R013 | Project_016_Risk--R013 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Resource Availability (Threat) | Person_697 | 2016-04-02 | 2019-08-01 | 0.2 | 8.8098 | 3.0834 | Accept | 0.2 | 8.8098 | 1.762 | H2 | 4 | Worsening | 0.6 | 120 | 132 | 158 | 134.3333 | 0.6 | 120 | 132 | 158 | 134.3333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Furnished Equipmnet Condition | Person_496 | 2015-04-27 | 2019-04-10 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.7 | 107 | 140 | 149 | 136 | 0.4 | 21 | 41 | 67 | 42 |  | 62.5 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 | 2016-11-20 | 0.25 | 6.6751 | 6.0076 | Accept | 0.1 | 16.2643 | 8.1321 | H3 | 3 | Stable | 0.9 | 116 | 126 | 142 | 127 | 0.9 | 116 | 126 | 142 | 127 | -143.6548 | 60 | 0 | -86.1929
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-20 | 0.25 | 5.4729 | 4.3783 | Accept | 0.15 | 4.6191 | 1.3857 | H3 | 3 | Stable | 0.6 | 102 | 126 | 147 | 125.5 | 0.6 | 102 | 126 | 147 | 125.5 | 15.6018 | 40 | 1 | 10.5611
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Risk of not being able to perform Tests | Person_238 | 2017-12-21 01:00 | 2019-01-21 01:00 | 0.5 | 5.2705 | 1.5811 | Accept | 0.5 | 4.3921 | 0.87842 | H2 | 4 | Stable | 0.7 | 90 | 125 | 154 | 124 | 0.7 | 90 | 125 | 154 | 124 | 16.6667 | 0 | 0 | 10
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2018-05-22 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.7 | 115 | 137 | 149 | 135.3333 | 0.2 | 27 | 43 | 70 | 44.8333 | 0 | 40 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_238 | 2017-05-23 | 2019-01-21 01:00 | 0.5 | 11.0894 | 0.55447 | Accept | 0.5 | 11.0894 | 0.55447 | H2 | 4 | Stable | 0.8 | 113 | 135 | 156 | 134.8333 | 0.8 | 113 | 135 | 156 | 134.8333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.7 | 0.92411 | 0.64688 | Reduce | 0.3 | 0.36965 | 0.11089 | H2 | 4 | Stable | 0.9 | 103 | 122 | 145 | 122.6667 | 0.1 | 12 | 58 | 63 | 51.1667 | 60 | 57.1429 | 0 | 36
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 01:00 | 2018-04-21 | 0.5 | 4.0661 | 2.033 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.6 | 114 | 127 | 158 | 130 | 0.1 | 11 | 48 | 61 | 44 | 0 | 90 | 1 | 2.7
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.5 | 0.46206 | 0.23103 | H1 | 5 | Improving | 0.8 | 111 | 131 | 141 | 129.3333 | 0.1 | 18 | 41 | 78 | 43.3333 | 58.3333 | 16.6667 | 0 | 35
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_693 | 2017-04-22 | 2017-09-19 01:00 | 0.6 | 1.1089 | 0.88715 | Accept | 0.3 | 0.73929 | 0.44357 | H3 | 3 | Worsening | 0.7 | 98 | 135 | 155 | 132.1667 | 0.7 | 98 | 135 | 155 | 132.1667 | 33.3333 | 50 | 0 | 20
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 01:00 | 2018-05-22 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.8 | 120 | 133 | 146 | 133 | 0.3 | 3 | 49 | 67 | 44.3333 | 0 | 50 | 1 | 1.5
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2018-05-22 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.5 | 118 | 125 | 149 | 127.8333 | 0.2 | 35 | 51 | 68 | 51.1667 | 0 | 25 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_693 | 2012-06-01 | 2018-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Improving | 0.6 | 118 | 122 | 148 | 125.6667 | 0.4 | 6 | 59 | 75 | 52.8333 | 0 | 40 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2018-05-21 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Stable | [10 empty] | 0 | 37.5 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_547 | 2017-05-23 | 2018-05-22 | 0.1 | 3.6965 | 0.36965 | Accept | 0.1 | 3.6965 | 0.36965 | H3 | 3 | Stable | 0.8 | 83 | 128 | 155 | 125 | 0.8 | 83 | 128 | 155 | 125 | 0 | 0 | 1 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production, Procurement or Engineering | Person_725 | 2018-01-21 01:00 | 2019-05-23 | 0.1 | 0.92411 | 0.18482 | Accept | 0.1 | 0.92411 | 0.18482 | H3 | 3 | Worsening | 0.5 | 82 | 136 | 152 | 129.6667 | 0.5 | 82 | 136 | 152 | 129.6667 | 0 | 0 | 1 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2018-02-19 01:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.5 | 105 | 136 | 143 | 132 | 0.4 | 14 | 57 | 71 | 52.1667 | 90 | 75 | 1 | 56.25
2017-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2017-11-19 01:00 | 0.05 | 4.6971 | 0.93941 | Accept | 0.05 | 4.6971 | 0.93941 | H3 | 3 | Improving | 0.8 | 114 | 135 | 158 | 135.3333 | 0.8 | 114 | 135 | 158 | 135.3333 | 0 | 0 | 1 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK044 | Project_042_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2018-02-20 01:00 | 2018-12-21 01:00 | 0.32 | 6.5759 | 2.1043 | -- | 0.32 | 6.5759 | 2.1043 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 0.2 | 4.6971 | 0.93941 | Accept | 0.2 | 4.6971 | 0.93941 | H2 | 4 | Stable | 0.6 | 102 | 137 | 149 | 133.1667 | 0.6 | 102 | 137 | 149 | 133.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK045 | Project_042_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2019-01-22 01:00 | 2019-05-23 | 0.25 | 3.908 | 0.97699 | -- | 0.25 | 3.908 | 0.97699 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 0.25 | 3.7576 | 0.75153 | Accept | 0.25 | 3.7576 | 0.75153 | H3 | 3 | Stable | 0.7 | 105 | 123 | 153 | 125 | 0.7 | 105 | 123 | 153 | 125 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | More issues during Qualification including additional PRs | Person_147 | 2017-07-26 | 2017-11-04 01:00 | 0.6 | 2.2828 | 0.31959 | Accept | 0.6 | 2.2828 | 0.31959 | H1 | 5 | Stable | 0.9 | 107 | 138 | 142 | 133.5 | 0.9 | 107 | 138 | 142 | 133.5 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Local customer Engineers in country | Person_455 | 2019-03-22 | 2019-05-23 | 0.1 | 2.1419 | 0.53546 | Accept | 0.1 | 2.1419 | 0.53546 | H2 | 4 | Stable | 0.5 | 90 | 129 | 153 | 126.5 | 0.5 | 90 | 129 | 153 | 126.5 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 | 0.05 | 2.8182 | 0.28182 | Accept | 0.05 | 2.8182 | 0.28182 | H3 | 3 | Stable | 0.6 | 81 | 127 | 156 | 124.1667 | 0.6 | 81 | 127 | 156 | 124.1667 | 0 | 0 | 1 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-149 | Project_020_Risk-149 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Component needs to be returned to UK | Person_703 | 2016-12-21 01:00 | 2017-11-19 01:00 | 0.2 | 1.8788 | 0.37576 | Accept | 0.04 | 1.8788 | 0.37576 | H3 | 3 | Stable | 0.7 | 88 | 134 | 148 | 128.6667 | 0.7 | 88 | 134 | 148 | 128.6667 | 0 | 80 | 1 | 2.4
2017-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2017-05-22 | 0.41 | 1.8788 | 0.37576 | Accept | 0.41 | 1.8788 | 0.37576 | H2 | 4 | Stable | 0.8 | 110 | 130 | 145 | 129.1667 | 0.8 | 110 | 130 | 145 | 129.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Further Software Development | Person_523 | 2015-05-24 | 2018-04-21 | 0.1 | 1.8788 | 0.18788 | Accept | 0.05 | 1.8788 | 0.18788 | H3 | 3 | Stable | 0.7 | 93 | 132 | 153 | 129 | 0.7 | 93 | 132 | 153 | 129 | 0 | 50 | 1 | 1.5
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Interface implementation | Person_496 | 2014-01-21 01:00 | 2017-10-20 01:00 | 0.5 | 1.8788 | 0.18788 | Accept | 0.5 | 1.8788 | 0.18788 | H2 | 4 | Stable | 0.7 | 95 | 136 | 144 | 130.5 | 0.7 | 95 | 136 | 144 | 130.5 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of the platforms for modification | Person_496 | 2014-01-21 01:00 | 2018-02-18 01:00 | 0 | 1.8788 | 0.18788 | Accept | 0.67 | 1.8788 | 0.18788 | H3 | 3 | Stable | 0.5 | 100 | 138 | 158 | 135 | 0.5 | 100 | 138 | 158 | 135 | 0 | -inf | 1 | -inf
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-095 | Project_008_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Repair of interface units from the Programme | Person_639 | 2017-05-23 | 2018-08-21 | 0.2 | 9.4695 | 1.8939 | Avoid | 0.2 | 9.4695 | 1.8939 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_523 | 2015-01-22 01:00 | 2018-04-21 | 0.35 | 4.8452 | 1.2113 | Accept | 0.2 | 4.8452 | 1.2113 | H2 | 4 | Stable | 0.6 | 103 | 126 | 158 | 127.5 | 0.6 | 103 | 126 | 158 | 127.5 | 0 | 42.8571 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_332 | 2016-06-23 | 2018-02-19 01:00 | 0.4 | 3.7878 | 1.1363 | Accept | 0.2 | 3.7878 | 1.1363 | H2 | 4 | Stable | 0.5 | 116 | 125 | 156 | 128.6667 | 0.5 | 116 | 125 | 156 | 128.6667 | 0 | 50 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-080 | Project_008_Risk-080 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Recovery of Costs | Person_565 | 2016-08-21 01:00 | 2017-08-20 01:00 | 0.5 | 23.6737 | 11.8369 | -- | 0.5 | 23.6737 | 11.8369 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Survey costs | Person_618 | 2016-04-22 | 2017-08-20 01:00 | 0.2 | 13.2573 | 2.6515 | Avoid | 0.2 | 13.2573 | 2.6515 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-079 | Project_008_Risk-079 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Regulations Phase 3 and 4 | Person_565 | 2016-10-21 01:00 | 2018-08-21 | 0.25 | 71.9682 | 17.992 | -- | 0.25 | 71.9682 | 17.992 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | RISK004 | Project_028_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Changes to be embodied on the Rig | Person_604 | 2017-04-29 | 2019-02-20 01:00 | 0.8 | 33.9324 | 10.1797 | Accept | 0.3 | 33.9324 | 10.1797 | H2 | 4 | Stable | 0.7 | 102 | 135 | 146 | 131.3333 | 0.7 | 102 | 135 | 146 | 131.3333 | 0 | 62.5 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.05 | 6.6957 | 2.3435 | Accept | 0.05 | 6.6957 | 2.3435 | H2 | 4 | Stable | 0.6 | 120 | 131 | 147 | 131.8333 | 0.6 | 120 | 131 | 147 | 131.8333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2018-04-22 | 0.8 | 35.0206 | 7.0041 | Accept | 0.6 | 35.0206 | 7.0041 | H1 | 5 | Stable | 0.6 | 92 | 133 | 147 | 128.5 | 0.6 | 92 | 133 | 147 | 128.5 | 0 | 25 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 01:00 | 2018-05-22 | 0.1 | 49.4398 | 19.7759 | Accept | 0.1 | 49.4398 | 9.888 | H2 | 4 | Stable | 0.9 | 91 | 140 | 160 | 135.1667 | 0.9 | 91 | 140 | 160 | 135.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) at the System level on product platform - performed by 3rd parties | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.41 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -2.5 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Sub-system / product system accreditation hindered by Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.1 | 0.25667 | 0.025667 | Transfer | 0.1 | 0.25667 | 0.025667 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 1.4673 | 0.58692 | Reduce | 0.4 | 1.4673 | 0.58692 | H2 | 4 | Improving | 0.7 | 112 | 132 | 146 | 131 | 0.3 | 18 | 57 | 66 | 52 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2018-03-21 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2018-01-19 01:00 | 0.3 | 0.89835 | 0.26951 | Transfer | 0.3 | 0.89835 | 0.26951 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 0.35 | 0.85557 | 0.29945 | Reduce | 0.35 | 1.9208 | 0.67227 | H2 | 4 | Stable | 0.6 | 84 | 137 | 146 | 129.6667 | 0.1 | 26 | 46 | 72 | 47 | -124.5001 | 0 | 0 | -74.7001
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 0.77001 | 0.30801 | Reduce | 0.3 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.9 | 92 | 131 | 160 | 129.3333 | 0.1 | 11 | 50 | 64 | 45.8333 | 0 | 25 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2018-02-20 01:00 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.8 | 85 | 133 | 147 | 127.3333 | 0.3 | 34 | 50 | 68 | 50.3333 | 0 | 28.5714 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2018-05-21 | 0.2 | 1.54 | 0.30801 | Accept | 0.2 | 0.77001 | 0.154 | H3 | 3 | Improving | 0.9 | 93 | 138 | 154 | 133.1667 | 0.9 | 93 | 138 | 154 | 133.1667 | 50 | 0 | 1 | 30
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2018-04-22 | 0.3 | 0.94968 | 0.28491 | Accept | 0.4 | 0.94968 | 0.18994 | H3 | 3 | Stable | 0.7 | 89 | 138 | 141 | 130.3333 | 0.7 | 89 | 138 | 141 | 130.3333 | 0 | -33.3333 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_009 | Project_045 | RISK001 | Project_045_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Generic Labour or Expense overspend | Person_662 | 2017-10-21 01:00 | 2019-05-23 | 0.5 | 27.1644 | 0.81493 | Accept | 0.5 | 12.8336 | 1.2834 | H2 | 4 | Stable | 0.6 | 101 | 121 | 153 | 123 | 0.6 | 101 | 121 | 153 | 123 | 52.7559 | 0 | 0 | 31.6535
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2018-03-22 | 2019-07-21 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.8 | 85 | 123 | 150 | 121.1667 | 0.3 | 23 | 45 | 62 | 44.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2018-03-16 01:00 | 0.1 | 6.4168 | 0.64168 | Transfer | 0.1 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sub-system FPGA | Person_332 | 2017-01-21 01:00 | 2018-02-20 01:00 | 0.4 | 1.5914 | 0.63655 | Reduce | 0.4 | 1.5914 | 0.63655 | H2 | 4 | Stable | 0.8 | 84 | 134 | 148 | 128 | 0.1 | 26 | 59 | 74 | 56 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort for System HW/SW- System upgrade | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.3 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.5 | 94 | 133 | 159 | 130.8333 | 0.2 | 23 | 58 | 68 | 53.8333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs | Person_372 | 2018-04-22 | 2018-08-22 01:00 | 0.5 | 6.6521 | 3.326 | Reduce | 0.5 | 6.6521 | 3.326 | H2 | 4 | Stable | 0.6 | 104 | 138 | 145 | 133.5 | 0.2 | 11 | 45 | 62 | 42.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.5 | 3.5934 | 1.7967 | H2 | 4 | Stable | 0.6 | 93 | 138 | 157 | 133.6667 | 0.1 | 6 | 42 | 78 | 42 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | HW - additional unplanned design effort | Person_332 | 2016-05-23 | 2018-02-20 01:00 | 0.4 | 3.3367 | 1.3347 | Reduce | 0.4 | 3.3367 | 1.3347 | H2 | 4 | Stable | 0.7 | 106 | 126 | 145 | 125.8333 | 0.2 | 27 | 58 | 70 | 54.8333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 0.5 | 4.2779 | 1.0695 | Accept | 0.5 | 4.2779 | 1.0695 | H2 | 4 | Stable | 0.5 | 119 | 131 | 160 | 133.8333 | 0.5 | 119 | 131 | 160 | 133.8333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK026 | Project_042_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st Jan to 31st March | Person_455 | 2020-05-23 | 2020-08-20 01:00 | 0.25 | 2.5667 | 0.77001 | Accept | 0.25 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.7 | 85 | 131 | 152 | 126.8333 | 0.7 | 85 | 131 | 152 | 126.8333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design [in addition to costed effort] | Person_332 | 2017-05-28 | 2018-08-18 | 0.2 | 2.6951 | 0.53901 | Reduce | 0.2 | 2.6951 | 0.53901 | H3 | 3 | Improving | 0.5 | 91 | 136 | 143 | 129.6667 | 0.1 | 22 | 53 | 60 | 49 | 0 | 0 | 1 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Minimum Order Quantities | Person_372 | 2017-11-20 01:00 | 2018-05-15 | 0.2 | 1.925 | 0.38501 | -- | 0.2 | 1.925 | 0.38501 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_372 | 2018-04-22 | 2018-08-22 01:00 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Worsening | 0.9 | 99 | 124 | 147 | 123.6667 | 0.2 | 37 | 44 | 70 | 47.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_585 | 2017-10-21 01:00 | 2019-07-21 | 0.333 | 11.5502 | 3.8462 | Reduce | 0.333 | 11.5502 | 3.8462 | H2 | 4 | Stable | 0.7 | 116 | 121 | 145 | 124.1667 | 0.1 | 7 | 57 | 60 | 49.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK047 | Project_042_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables | Person_455 | 2020-11-20 01:00 | 2021-05-22 | 0.2 | 0.82576 | 0.16515 | Accept | 0.2 | 0.82576 | 0.082576 | H2 | 4 | Stable | 0.7 | 113 | 131 | 151 | 131.3333 | 0.7 | 113 | 131 | 151 | 131.3333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK014 | Project_048_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Line Qualification | Person_551 | 2017-02-20 01:00 | 2019-05-23 | 0.2 | 1.4864 | 0.29728 | Reduce | 0.1 | 1.4864 | 0.14864 | H3 | 3 | Stable | 0.5 | 109 | 137 | 155 | 135.3333 | 0.3 | 33 | 50 | 66 | 49.8333 | 0 | 50 | 0 | 0
2017-08-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK006 | Project_048_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Lead Times | Person_261 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0.82576 | 0.16515 | Avoid | 0.1 | 0.82576 | 0.082576 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-08-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK005 | Project_048_RISK005 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2020-05-22 | 0.15 | 0.30966 | 0.046449 | Avoid | 0.1 | 0.30966 | 0.030966 | H3 | 3 | Stable | [10 empty] | 0 | 33.3333 | 0 | 0
2017-08-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK011 | Project_048_RISK011 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Oracle | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0.20644 | 0.041288 | Avoid | 0.1 | 0.20644 | 0.020644 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-08-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK010 | Project_048_RISK010 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Staff Availability | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0.61932 | 0.12386 | Avoid | 0.1 | 0.61932 | 0.061932 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-08-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK013 | Project_048_RISK013 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Material | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.25 | 5.161 | 1.2903 | Avoid | 0.1 | 5.161 | 0.5161 | H3 | 3 | Stable | [10 empty] | 0 | 60 | 0 | 0
2017-08-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK001 | Project_048_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Procurement | Person_261 | 2017-02-20 01:00 | 2019-05-23 | 0.2 | 10.1828 | 2.0366 | Reduce | 0.1 | 10.1827 | 1.0183 | H3 | 3 | Stable | 0.6 | 90 | 132 | 158 | 129.3333 | 0.1 | 11 | 47 | 63 | 43.6667 | 0.00070957 | 50 | 1 | 1.5004
2017-08-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK012 | Project_048_RISK012 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Supplier Performance | Person_261 | 2017-02-20 01:00 | 2020-05-22 | 0.3 | 0.72254 | 0.21676 | Reduce | 0.15 | 0.72254 | 0.10838 | H3 | 3 | Stable | 0.9 | 120 | 130 | 144 | 130.6667 | 0.1 | 6 | 50 | 78 | 47.3333 | 0 | 50 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK028 | Project_042_RISK028 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st July to 30th September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 0.25 | 0.61932 | 0.37159 | Accept | 0.25 | 0.61932 | 0.1858 | H2 | 4 | Stable | 0.9 | 103 | 132 | 145 | 129.3333 | 0.9 | 103 | 132 | 145 | 129.3333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK007 | Project_048_RISK007 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 1.4451 | 0.28902 | Reduce | 0.1 | 1.4451 | 0.14451 | H3 | 3 | Stable | 0.5 | 102 | 130 | 158 | 130 | 0.2 | 39 | 55 | 74 | 55.5 | 0 | 50 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK027 | Project_042_RISK027 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st April to 30th June | Person_455 | 2020-08-21 01:00 | 2020-09-19 01:00 | 0.25 | 11.5901 | 5.795 | Accept | 0.25 | 11.5901 | 5.795 | H2 | 4 | Stable | 0.8 | 93 | 139 | 144 | 132.1667 | 0.8 | 93 | 139 | 144 | 132.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK022 | Project_042_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2017-09-20 01:00 | 2018-09-20 01:00 | 0.2 | 5.795 | 2.8975 | Accept | 0.2 | 5.795 | 2.8975 | H2 | 4 | Stable | 0.8 | 100 | 130 | 146 | 127.6667 | 0.8 | 100 | 130 | 146 | 127.6667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK043 | Project_042_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st December | Person_455 | 2021-03-23 | 2021-05-22 | 0.1 | 1.4488 | 0.43463 | Accept | 0.1 | 1.4488 | 0.43463 | H2 | 4 | Stable | 0.9 | 116 | 140 | 156 | 138.6667 | 0.9 | 116 | 140 | 156 | 138.6667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK024 | Project_042_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2019-09-21 01:00 | 2020-09-19 01:00 | 0.33 | 0.3553 | 0.14212 | Accept | 0.33 | 0.3553 | 0.14212 | H2 | 4 | Stable | 0.8 | 85 | 134 | 148 | 128.1667 | 0.8 | 85 | 134 | 148 | 128.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK046 | Project_042_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables - June | Person_455 | 2018-11-21 01:00 | 2020-11-19 01:00 | 0.2 | 0.11976 | 0.0059882 | Accept | 0.2 | 0.11976 | 0.0059882 | H2 | 4 | Stable | 0.5 | 105 | 127 | 150 | 127.1667 | 0.5 | 105 | 127 | 150 | 127.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK023 | Project_042_RISK023 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2018-09-21 01:00 | 2019-09-20 01:00 | 0.2 | 0.59882 | 0.059882 | Accept | 0.2 | 0.59882 | 0.059882 | H2 | 4 | Stable | 0.5 | 110 | 134 | 141 | 131.1667 | 0.5 | 110 | 134 | 141 | 131.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK029 | Project_042_RISK029 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st October to 31st December | Person_455 | 2021-02-20 01:00 | 2021-05-22 | 0.25 | 0.95811 | 0.23953 | Accept | 0.25 | 0.95811 | 0.23953 | H2 | 4 | Stable | 0.5 | 111 | 134 | 143 | 131.6667 | 0.5 | 111 | 134 | 143 | 131.6667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-125 | Project_043_Risk-125 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | IOC Delayed due to a number of factors (Marching Customer Risk) | Person_084 | 2014-09-13 01:00 | 2019-01-21 01:00 | 0.5 | 1.9362 | 0.96809 | Reduce | 0.3 | 1.9362 | 0.58086 | H2 | 4 | Stable | 0.6 | 87 | 140 | 143 | 131.6667 | 0.1 | 9 | 41 | 77 | 41.6667 | 0 | 40 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK031 | Project_042_RISK031 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours 30th June to 30th September | Person_455 | 2020-08-20 01:00 | 2021-02-19 01:00 | 0.2 | 0.59882 | 0.14971 | Accept | 0.2 | 0.59882 | 0.14971 | H2 | 4 | Stable | 0.6 | 112 | 140 | 152 | 137.3333 | 0.6 | 112 | 140 | 152 | 137.3333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK030 | Project_042_RISK030 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours 31st March to 29 Jun | Person_455 | 2020-08-20 01:00 | 2020-11-18 01:00 | 0.2 | 2.2586 | 0.90343 | Accept | 0.2 | 2.2586 | 0.90343 | H2 | 4 | Stable | 0.5 | 98 | 125 | 144 | 123.6667 | 0.5 | 98 | 125 | 144 | 123.6667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK037 | Project_042_RISK037 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 1 | Person_455 | 2020-05-23 | 2021-05-22 | 0.14 | 2.9272 | 1.4636 | Accept | 0.14 | 2.9272 | 1.4636 | H2 | 4 | Stable | 0.7 | 108 | 125 | 146 | 125.6667 | 0.7 | 108 | 125 | 146 | 125.6667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK036 | Project_042_RISK036 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 2 | Person_455 | 2019-05-24 | 2020-05-22 | 0.25 | 4.4984 | 2.2492 | Accept | 0.25 | 4.4984 | 2.2492 | H2 | 4 | Stable | 0.5 | 98 | 140 | 152 | 135 | 0.5 | 98 | 140 | 152 | 135 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK039 | Project_042_RISK039 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality Issues 16th August to 15th August | Person_251 | 2020-01-06 01:00 | 2021-01-04 01:00 | 0.1 | 1.6962 | 0.33923 | Accept | 0.1 | 1.6962 | 0.33923 | H2 | 4 | Stable | 0.7 | 104 | 137 | 145 | 132.8333 | 0.7 | 104 | 137 | 145 | 132.8333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK038 | Project_042_RISK038 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality Issues 16th August to 15th August | Person_251 | 2019-01-06 01:00 | 2020-01-05 01:00 | 0.1 | 3.0513 | 0.61026 | Accept | 0.1 | 3.0513 | 0.61026 | H2 | 4 | Stable | 0.6 | 93 | 122 | 148 | 121.5 | 0.6 | 93 | 122 | 148 | 121.5 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK033 | Project_042_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st April to 30 June | Person_455 | 2019-08-22 01:00 | 2019-11-20 01:00 | 0.2 | 18.9062 | 9.4531 | Accept | 0.2 | 18.9062 | 9.4531 | H2 | 4 | Stable | 0.6 | 100 | 122 | 159 | 124.5 | 0.6 | 100 | 122 | 159 | 124.5 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK032 | Project_042_RISK032 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours 30th June to 30th September | Person_455 | 2020-08-20 01:00 | 2021-02-19 01:00 | 0.2 | 3.7214 | 0.93035 | Accept | 0.2 | 3.7214 | 0.93035 | H2 | 4 | Stable | 0.8 | 92 | 128 | 148 | 125.3333 | 0.8 | 92 | 128 | 148 | 125.3333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK035 | Project_042_RISK035 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st October to 31st December | Person_455 | 2021-02-20 01:00 | 2021-05-22 | 0.2 | 3.7207 | 0.93016 | Accept | 0.2 | 3.7207 | 0.93016 | H2 | 4 | Stable | 0.6 | 98 | 127 | 146 | 125.3333 | 0.6 | 98 | 127 | 146 | 125.3333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK034 | Project_042_RISK034 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st July to 30 September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 0.2 | 8.2789 | 2.4837 | Accept | 0.2 | 8.2789 | 2.4837 | H2 | 4 | Stable | 0.6 | 88 | 135 | 159 | 131.1667 | 0.6 | 88 | 135 | 159 | 131.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK040 | Project_042_RISK040 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st May to 30 Oct | Person_455 | 2019-09-21 01:00 | 2020-03-21 | 0.1 | 10.4822 | 4.717 | Accept | 0.1 | 10.4822 | 4.717 | H2 | 4 | Stable | 0.9 | 103 | 125 | 155 | 126.3333 | 0.9 | 103 | 125 | 155 | 126.3333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-002 | Project_021_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.9 | 91 | 122 | 157 | 122.6667 | 0.3 | 34 | 54 | 61 | 51.8333 |  | 66.6667 | 1
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H3 | 3 | Stable | 0.8 | 94 | 126 | 148 | 124.3333 | 0.4 | 2 | 50 | 73 | 45.8333 |  | 62.5 | 1
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK028 | Project_021_RISK028 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | trials delay due to lack of equipment | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 93 | 124 | 155 | 124 | 0.4 | 2 | 45 | 67 | 41.5 |  | 66.6667 | 1
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-009 | Project_021_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification Report delays due to insufficient resource in supply chain | Person_207 | 2017-09-20 01:00 | 2017-12-20 01:00 | 0.2 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.5 | 98 | 132 | 153 | 129.8333 | 0.4 | 7 | 46 | 63 | 42.3333 |  | 50 | 1
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK029 | Project_021_RISK029 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | trials delay due to lack of supporting resources | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 85 | 138 | 157 | 132.3333 | 0.3 | 30 | 55 | 69 | 53.1667 |  | 66.6667 | 1
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-004 | Project_021_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 107 | 124 | 147 | 125 | 0.2 | 18 | 41 | 62 | 40.6667 |  | 80 | 1
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-014 | Project_021_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.9 | 106 | 128 | 158 | 129.3333 | 0.1 | 32 | 57 | 69 | 54.8333 |  | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-013 | Project_021_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to late Trials Approval | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.6 | 84 | 122 | 158 | 121.6667 | 0.3 | 3 | 42 | 78 | 41.5 |  | 66.6667 | 1
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification delays | Person_207 | 2017-09-20 01:00 | 2017-11-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Worsening | 0.6 | 111 | 129 | 142 | 128.1667 | 0.1 | 2 | 57 | 76 | 51 |  | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-018 | Project_021_Risk-018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2017-05-23 | 2017-11-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 88 | 136 | 144 | 129.3333 | 0.1 | 19 | 53 | 71 | 50.3333 |  | 40 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-017 | Project_021_Risk-017 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target. | Person_061 | 2013-01-07 01:00 | 2018-02-04 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.9 | 101 | 137 | 147 | 132.6667 | 0.3 | 5 | 48 | 69 | 44.3333 | 0 | 33.3333 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-015 | Project_021_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to technical performance | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.3 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.9 | 97 | 136 | 151 | 132 | 0.4 | 33 | 46 | 65 | 47 |  | 33.3333 | 1
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK042 | Project_042_RISK042 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st February to 14th July | Person_455 | 2020-06-23 | 2020-12-03 01:00 | 0.1 | 15.5796 | 6.2318 | Accept | 0.1 | 15.5796 | 6.2318 | H2 | 4 | Stable | 0.7 | 95 | 121 | 150 | 121.5 | 0.7 | 95 | 121 | 150 | 121.5 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Performance (collector opportunity) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.3814 | 26.127 | 9.9648 | -- | 0.4132 | 26.127 | 10.7957 | H1 | 5 | Stable | [10 empty] | 0 | -8.3377 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.3 | 20.8767 | 6.263 | H1 | 5 | Stable | 0.6 | 107 | 137 | 156 | 135.1667 | 0.3 | 23 | 40 | 60 | 40.5 | 50 | 25 | 0 | 30
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.493 | 58.1898 | 28.6876 | Reduce | 0.32036 | 40.4161 | 12.9477 | H1 | 5 | Worsening | 0.5 | 100 | 125 | 142 | 123.6667 | 0.4 | 32 | 41 | 69 | 44.1667 | 30.5444 | 35.0183 | 0 | 18.3266
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK308 | Project_024_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System robustness and resilience | Person_774 | 2017-04-06 | 2018-06-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.1 | 2.5966 | 0.25966 | H3 | 3 | Stable | 0.8 | 113 | 121 | 158 | 125.8333 | 0.4 | 33 | 48 | 71 | 49.3333 | 58.3333 | 66.6667 | 1 | 37
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK312 | Project_024_RISK312 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Built-in Test not fit for purpose | Person_774 | 2017-02-25 01:00 | 2018-05-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.2 | 9.8671 | 1.9734 | H2 | 4 | Stable | 0.6 | 106 | 121 | 160 | 125 | 0.1 | 31 | 53 | 78 | 53.5 | -58.3333 | 33.3333 | 0 | -35
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.8 | 106 | 137 | 152 | 134.3333 | 0.4 | 12 | 58 | 79 | 53.8333 | 25.8065 | 20 | 0 | 15.4839
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK041 | Project_042_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st Jan | Person_455 | 2020-03-23 | 2020-06-22 | 0.1 | 7.3848 | 3.6924 | Accept | 0.1 | 7.3848 | 3.6924 | H2 | 4 | Stable | 0.6 | 82 | 137 | 156 | 131 | 0.6 | 82 | 137 | 156 | 131 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-085 | Project_008_SER-085 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Insufficient LOE to manage the supply chain with reducing number of spares | Person_639 | 2017-04-22 | 2018-08-21 | 0.25 | 5.126 | 2.563 | Accept | 0.25 | 5.126 | 2.563 | H3 | 3 | Stable | 0.5 | 99 | 137 | 145 | 132 | 0.5 | 99 | 137 | 145 | 132 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-090 | Project_008_Risk-090 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Demands but not provisioned | Person_639 | 2017-04-22 | 2018-08-21 | 0.3 | 12.815 | 2.563 | Accept | 0.3 | 12.815 | 2.563 | H3 | 3 | Stable | 0.6 | 105 | 139 | 144 | 134.1667 | 0.6 | 105 | 139 | 144 | 134.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.6 | 103 | 122 | 148 | 123.1667 | 0.4 | 6 | 42 | 67 | 40.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-20 22:00 | 2016-08-20 22:00 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.6 | 114 | 133 | 148 | 132.3333 | 0.1 | 24 | 59 | 64 | 54 | 0 | 16.6667 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 0.45 | 7.689 | 2.6911 | Accept | 0.45 | 7.689 | 2.6911 | H2 | 4 | Stable | 0.6 | 84 | 136 | 151 | 129.8333 | 0.6 | 84 | 136 | 151 | 129.8333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_565 | 2018-05-22 | 2018-08-21 | 0.25 | 5.4336 | 1.3584 | Accept | 0.25 | 5.4336 | 1.3584 | H3 | 3 | Stable | 0.8 | 80 | 125 | 149 | 121.5 | 0.8 | 80 | 125 | 149 | 121.5 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Lack of Spares Availability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 0.3 | 13.3529 | 6.6765 | Accept | 0.3 | 23.5716 | 11.7858 | H3 | 3 | Stable | 0.9 | 90 | 126 | 145 | 123.1667 | 0.9 | 90 | 126 | 145 | 123.1667 | -76.5278 | 0 | 0 | -45.9167
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 0.5 | 9.2728 | 4.6364 | Reduce | 0.15 | 9.2728 | 1.3909 | H2 | 4 | Stable | 0.8 | 93 | 134 | 150 | 129.8333 | 0.4 | 5 | 46 | 68 | 42.8333 | 0 | 70 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R008 | Project_016_Risk--R008 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Additional Travel & Subsistence | Person_574 | 2016-01-13 01:00 | 2019-05-23 | 0.4 | 8.9019 | 3.5608 | Reduce | 0.25 | 8.9019 | 2.2255 | H3 | 3 | Stable | 0.6 | 108 | 122 | 154 | 125 | 0.1 | 28 | 50 | 66 | 49 | 0 | 37.5 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 0.3 | 8.7814 | 2.6344 | Reduce | 0.15 | 8.7832 | 1.3175 | H3 | 3 | Stable | 0.8 | 115 | 122 | 141 | 124 | 0.3 | 12 | 49 | 68 | 46 | -0.021119 | 50 | 1 | 1.4873
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R009 | Project_016_Risk--R009 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer maybe difficult to work with | Person_697 | 2016-04-02 | 2019-08-01 | 0.6 | 23.9549 | 14.3729 | Reduce | 0.43864 | 23.8312 | 10.4533 | H2 | 4 | Stable | 0.7 | 86 | 137 | 156 | 131.6667 | 0.4 | 19 | 45 | 67 | 44.3333 | 0.51612 | 26.8938 | 0 | 0.30967
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Volume of production tools and Jigs | Person_084 | 2016-11-22 22:00 | 2021-11-22 22:00 | 0.35 | 108.3186 | 32.4956 | Accept | 0.2 | 108.3186 | 32.4956 | H2 | 4 | Stable | 0.7 | 88 | 125 | 142 | 121.6667 | 0.7 | 88 | 125 | 142 | 121.6667 | 0 | 42.8571 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Delay of processing | Person_306 | 2016-04-02 | 2017-03-21 01:00 | 0.15 | 26.3497 | 3.9525 | Reduce | 0.15 | 13.1767 | 1.9765 | H3 | 3 | Stable | 0.9 | 113 | 140 | 151 | 137.3333 | 0.3 | 16 | 51 | 61 | 46.8333 | 49.993 | 0 | 1 | 29.9958
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK040 | Project_017_RISK040 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Upgrades | Person_084 | 2016-09-29 22:00 | 2016-12-17 22:00 | 0.35 | 12.0547 | 2.4109 | Accept | 0.35 | 12.0547 | 2.4109 | H2 | 4 | Stable | 0.8 | 112 | 126 | 159 | 129.1667 | 0.8 | 112 | 126 | 159 | 129.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software issue input | Person_084 | 2016-11-22 22:00 | 2023-02-19 22:00 | 0.4 | 0 | 0 | Accept | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.5 | 80 | 126 | 142 | 121 | 0.5 | 80 | 126 | 142 | 121 |  | 50 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 19:00 | 2019-08-20 19:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.9 | 103 | 128 | 144 | 126.5 | 0.1 | 32 | 53 | 74 | 53 | 83.3333 | 88.8889 | 1 | 52.6667
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.5 | 85 | 131 | 158 | 127.8333 | 0.1 | 2 | 40 | 74 | 39.3333 | 72 | 0 | 0 | 43.2
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.8 | 108 | 121 | 146 | 123 | 0.1 | 20 | 50 | 71 | 48.5 | 47.7391 | 0 | 0 | 28.6435
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 19:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.5 | 110 | 136 | 158 | 135.3333 | 0.1 | 10 | 51 | 77 | 48.5 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2018-03-16 01:00 | 0.1 | 6.4168 | 0.64168 | Transfer | 0.1 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sub-system FPGA | Person_216 | 2017-01-21 01:00 | 2018-02-20 01:00 | 0.4 | 1.5914 | 0.63655 | Reduce | 0.4 | 1.5914 | 0.63655 | H2 | 4 | Stable | 0.5 | 98 | 132 | 153 | 129.8333 | 0.3 | 11 | 54 | 68 | 49.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2020-09-19 01:00 | 0.2 | 4.2779 | 1.0695 | Accept | 0.2 | 4.2779 | 1.0695 | H3 | 3 | Stable | 0.6 | 82 | 131 | 151 | 126.1667 | 0.6 | 82 | 131 | 151 | 126.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2019-07-21 | 0.3 | 2.5667 | 0.77001 | Accept | 0.2 | 2.5667 | 0.77001 | H3 | 3 | Stable | 0.5 | 113 | 128 | 156 | 130.1667 | 0.5 | 113 | 128 | 156 | 130.1667 | 0 | 33.3333 | 1 | 1
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design [in addition to costed effort] | Person_332 | 2017-05-28 | 2018-08-18 | 0.2 | 2.6951 | 0.53901 | Reduce | 0.2 | 2.6951 | 0.53901 | H3 | 3 | Improving | 0.6 | 87 | 134 | 141 | 127.3333 | 0.4 | 36 | 58 | 78 | 57.6667 | 0 | 0 | 1 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Minimum Order Quantities | Person_372 | 2017-05-23 | 2019-05-16 | 0.2 | 1.925 | 0.38501 | -- | 0.2 | 1.925 | 0.38501 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_372 | 2016-12-21 01:00 | 2017-12-19 01:00 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Worsening | 0.5 | 100 | 138 | 143 | 132.5 | 0.3 | 17 | 41 | 66 | 41.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_585 | 2017-10-21 01:00 | 2019-07-21 | 0.333 | 11.5502 | 3.8462 | Reduce | 0.333 | 11.5502 | 3.8462 | H2 | 4 | Stable | 0.8 | 87 | 122 | 153 | 121.3333 | 0.1 | 16 | 56 | 71 | 51.8333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 3.1344 | 1.5672 | Accept | 0.1 | 3.1344 | 1.5672 | H3 | 3 | Stable | 0.7 | 92 | 130 | 141 | 125.5 | 0.7 | 92 | 130 | 141 | 125.5 | 0 | -233.3333 | 0 | 0
2017-08-21 | ORG_002 | BA_004 | Portfolio_010 | Project_046 | PRO004 | Project_046_PRO004 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | High Material Atrition Level | Person_025 | 2016-06-14 | 2017-11-20 01:00 | 0.5 | 1.618 | 0.80901 | Reduce | 0.5 | 1.618 | 0.80901 | H1 | 5 | Stable | 0.7 | 97 | 123 | 143 | 122 | 0.2 | 7 | 51 | 60 | 45.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 17.0765 | 1.7076 | Accept | 0.25 | 17.0765 | 1.7076 | H2 | 4 | Stable | 0.7 | 82 | 121 | 157 | 120.5 | 0.7 | 82 | 121 | 157 | 120.5 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 186.9553 | 59.2026 | Accept | 0.3 | 186.9553 | 1.3939 | H2 | 4 | Stable | 0.5 | 115 | 137 | 153 | 136 | 0.5 | 115 | 137 | 153 | 136 | 0 | 0 | 0 | 0
2017-08-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK015 | Project_048_RISK015 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Customer requires additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 22.8501 | 6.855 | Accept | 0.1 | 22.8501 | 6.855 | H3 | 3 | Stable | 0.5 | 94 | 126 | 152 | 125 | 0.5 | 94 | 126 | 152 | 125 | 0 | 50 | 0 | 0
2017-08-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK008 | Project_048_RISK008 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 25.966 | 7.7898 | Accept | 0.3 | 10.3864 | 3.1159 | H3 | 3 | Stable | 0.8 | 80 | 128 | 149 | 123.5 | 0.8 | 80 | 128 | 149 | 123.5 | 60 | 50 | 0 | 36
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Additional minor point releases | Person_228 | 2016-05-23 | 2017-10-19 | 0.5 | 11.9444 | 5.9722 | Reduce | 0.25 | 11.9444 | 2.9861 | H2 | 4 | Stable | 0.7 | 117 | 137 | 160 | 137.5 | 0.1 | 16 | 47 | 73 | 46.1667 | 0 | 50 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_228 | 2016-05-23 | 2018-04-21 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.9 | 96 | 124 | 159 | 125.1667 | 0.4 | 19 | 52 | 60 | 47.8333 | 0 | 50 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_413 | 2015-11-21 | 2018-11-20 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.9 | 103 | 133 | 156 | 131.8333 | 0.2 | 1 | 56 | 74 | 49.8333 | 0 | 5 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Acceptance team experience | Person_351 | 2017-09-21 | 2018-07-25 | 0.8 | 2.8043 | 2.2435 | Reduce | 0.45 | 2.8043 | 1.2619 | H1 | 5 | Stable | 0.9 | 112 | 122 | 149 | 124.8333 | 0.4 | 12 | 43 | 68 | 42 | 0 | 43.75 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK167 | Project_024_RISK167 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Customer not providing the information needed | Person_710 | 2016-08-21 | 2018-02-19 | 0.5 | 9.971 | 4.9855 | Reduce | 0.3 | 9.971 | 2.9913 | H1 | 5 | Worsening | 0.5 | 114 | 128 | 151 | 129.5 | 0.3 | 27 | 41 | 65 | 42.6667 | 0 | 40 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK306(028) | Project_024_RISK306(028) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | HW repairs required on units | Person_119 | 2016-11-19 | 2018-11-20 | 0.3 | 2.813 | 0.8439 | Reduce | 0.2 | 2.813 | 0.5626 | H2 | 4 | Stable | 0.7 | 95 | 140 | 147 | 133.6667 | 0.2 | 25 | 43 | 70 | 44.5 | 0 | 33.3333 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK226 | Project_024_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Late Evidences delay Certification delivery | Person_710 | 2017-04-30 | 2017-12-21 | 0.4 | 3.9468 | 1.5787 | Reduce | 0.2 | 3.9468 | 0.78937 | H2 | 4 | Worsening | 0.8 | 92 | 125 | 147 | 123.1667 | 0.1 | 28 | 43 | 69 | 44.8333 | 0 | 50 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK302(024) | Project_024_RISK302(024) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | On time provision of platform units | Person_119 | 2016-11-19 | 2019-05-23 | 0.25 | 2.3889 | 0.59722 | Reduce | 0.15 | 2.3889 | 0.35833 | H2 | 4 | Stable | 0.5 | 110 | 129 | 151 | 129.5 | 0.1 | 5 | 51 | 62 | 45.1667 | 0 | 40 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK227 | Project_024_RISK227 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Data Bunching | Person_710 | 2017-03-23 | 2017-09-19 | 0.4 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H1 | 5 | Stable | 0.7 | 118 | 140 | 159 | 139.5 | 0.1 | 6 | 46 | 73 | 43.8333 |  | 25 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-026 | Project_043_Risk-026 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Equipment Delivery & Certification Risk | Person_693 | 2017-04-19 | 2017-10-19 01:00 | 0.25 | 0.5626 | 0.19691 | Accept | 0.25 | 0.5626 | 0.19691 | H2 | 4 | Improving | 0.7 | 108 | 136 | 156 | 134.6667 | 0.7 | 108 | 136 | 156 | 134.6667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK225 | Project_024_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | More testing required as a result compliance to Platform Risk | Person_351 | 2017-09-21 | 2018-07-25 | 0.5 | 5.6866 | 2.8433 | Reduce | 0.3 | 5.6866 | 1.706 | H2 | 4 | Stable | 0.8 | 115 | 128 | 157 | 130.6667 | 0.2 | 39 | 42 | 74 | 46.8333 | 0 | 40 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.8 | 112 | 121 | 160 | 126 | 0.1 | 33 | 59 | 70 | 56.5 | 0 | 60 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_288 | 2017-02-22 | 2017-11-19 | 0.3 | 19.9938 | 5.9981 | Reduce | 0.1 | 19.9938 | 1.9994 | H3 | 3 | Improving | 0.7 | 115 | 126 | 151 | 128.3333 | 0.2 | 6 | 41 | 74 | 40.6667 | 0 | 66.6667 | 1 | 2
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.2 | 3.843 | 0.76859 | H2 | 4 | Stable | 0.9 | 102 | 122 | 152 | 123.6667 | 0.1 | 15 | 51 | 71 | 48.3333 | 0 | 60 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK256 | Project_024_RISK256 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unable to meet spare capacity requirement | Person_119 | 2016-07-21 | 2018-01-21 | 0.8 | 0.12983 | 0.10386 | Reduce | 0.05 | 0.12983 | 0.0064915 | H3 | 3 | Stable | 0.7 | 81 | 131 | 147 | 125.3333 | 0.3 | 37 | 45 | 63 | 46.6667 | 0 | 93.75 | 1 | 2.8125
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Performance (collector opportunity) | Person_351 | 2017-01-21 | 2018-07-25 | 0.3814 | 26.127 | 9.9648 | -- | 0.4132 | 26.127 | 10.7957 | H1 | 5 | Stable | [10 empty] | 0 | -8.3377 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-09-21 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.3 | 20.8767 | 6.263 | H1 | 5 | Stable | 0.8 | 115 | 127 | 145 | 128 | 0.1 | 8 | 48 | 79 | 46.5 | 50 | 25 | 0 | 30
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 | 2018-07-25 | 0.50325 | 71.5182 | 35.9915 | Reduce | 0.3172 | 51.9268 | 16.4712 | H1 | 5 | Worsening | 0.9 | 114 | 134 | 149 | 133.1667 | 0.4 | 11 | 49 | 78 | 47.5 | 27.3935 | 36.9697 | 0 | 16.4361
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK308 | Project_024_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System robustness and resilience | Person_774 | 2017-04-06 | 2018-06-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.1 | 2.5966 | 0.25966 | H3 | 3 | Stable | 0.9 | 82 | 137 | 155 | 130.8333 | 0.3 | 19 | 42 | 67 | 42.3333 | 58.3333 | 66.6667 | 1 | 37
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.8 | 112 | 125 | 157 | 128.1667 | 0.2 | 36 | 55 | 60 | 52.6667 | 0 | 0 | 1 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 10:00 | 2019-08-20 10:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 10:00 | 2019-08-20 10:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 10:00 | 2019-08-20 10:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 10:00 | 2019-08-20 10:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 10:00 | 2019-08-20 10:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 0.5 | 9.2728 | 4.6364 | Reduce | 0.15 | 9.2728 | 1.3909 | H2 | 4 | Stable | 0.6 | 103 | 135 | 157 | 133.3333 | 0.4 | 16 | 50 | 78 | 49 | 0 | 70 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R008 | Project_016_Risk--R008 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Additional Travel & Subsistence | Person_574 | 2016-01-12 22:00 | 2019-05-23 | 0.4 | 8.9019 | 3.5608 | Reduce | 0.25 | 8.9019 | 2.2255 | H3 | 3 | Stable | 0.6 | 118 | 133 | 141 | 131.8333 | 0.3 | 12 | 52 | 72 | 48.6667 | 0 | 37.5 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-12 22:00 | 2017-08-19 22:00 | 0.3 | 8.7814 | 2.6344 | Reduce | 0.15 | 8.7832 | 1.3175 | H3 | 3 | Stable | 0.9 | 113 | 132 | 141 | 130.3333 | 0.4 | 29 | 56 | 72 | 54.1667 | -0.021119 | 50 | 1 | 1.4873
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R009 | Project_016_Risk--R009 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer maybe difficult to work with | Person_697 | 2016-04-02 | 2019-08-01 | 0.6 | 23.9549 | 14.3729 | Reduce | 0.43864 | 23.8312 | 10.4533 | H2 | 4 | Stable | 0.5 | 98 | 133 | 146 | 129.3333 | 0.3 | 18 | 54 | 79 | 52.1667 | 0.51612 | 26.8938 | 0 | 0.30967
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Delay of processing | Person_306 | 2016-04-02 | 2017-03-20 22:00 | 0.15 | 26.3497 | 3.9525 | Reduce | 0.15 | 13.1767 | 1.9765 | H3 | 3 | Stable | 0.7 | 86 | 124 | 153 | 122.5 | 0.2 | 19 | 42 | 76 | 43.8333 | 49.993 | 0 | 1 | 29.9958
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.6 | 83 | 121 | 147 | 119 | 0.3 | 32 | 44 | 75 | 47.1667 | 0 | 0 | 1 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 19:00 | 2019-08-20 19:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.8 | 100 | 127 | 147 | 125.8333 | 0.3 | 7 | 44 | 72 | 42.5 | 83.3333 | 88.8889 | 1 | 52.6667
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.6 | 108 | 126 | 151 | 127.1667 | 0.1 | 17 | 57 | 66 | 51.8333 | 72 | 0 | 0 | 43.2
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.9 | 120 | 124 | 149 | 127.5 | 0.4 | 25 | 41 | 72 | 43.5 | 47.7391 | 0 | 0 | 28.6435
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 19:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.6 | 80 | 133 | 159 | 128.5 | 0.1 | 17 | 47 | 67 | 45.3333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.7 | 116 | 124 | 144 | 126 | 0.2 | 37 | 54 | 75 | 54.6667 | 25.8065 | 20 | 0 | 15.4839
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 | 2016-12-21 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.5 | 109 | 135 | 158 | 134.5 | 0.3 | 30 | 50 | 69 | 49.8333 | 47 | 0 | 0 | 28.2
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 | 0.4 | 9.139 | 3.6556 | Avoid | 0.2 | 9.139 | 1.8278 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Product Baseline delivery is late | Person_151 | 2015-09-21 | 2017-02-13 | 0.125 | 232.2192 | 29.0274 | -- | 0.215 | 27.8663 | 5.9913 | H2 | 4 | Stable | [10 empty] | 88 | -72 | 0 | 52.8
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 | 2016-12-21 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-19 | 0.4 | 3.187 | 1.2748 | Reduce | 0.2 | 1.5935 | 0.3187 | H3 | 3 | Stable | 0.5 | 118 | 124 | 149 | 127.1667 | 0.1 | 6 | 40 | 76 | 40.3333 | 50 | 50 | 1 | 31.5
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 0.5 | 13.7833 | 6.8917 | Avoid | 0.2 | 6.8917 | 1.3783 | H3 | 3 | Stable | [10 empty] | 50 | 60 | 1 | 31.8
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-20 | 0.3 | 5.5433 | 1.663 | Reduce | 0.35 | 5.5433 | 1.9402 | H2 | 4 | Worsening | 0.6 | 91 | 121 | 149 | 120.6667 | 0.4 | 3 | 45 | 60 | 40.5 | 0 | -16.6667 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 | 2016-11-20 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Worsening | [10 empty] | 0 | 75 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 6.7418 | 1.6855 | Accept | 0.5 | 6.7418 | 1.0113 | H2 | 4 | Stable | 0.5 | 93 | 140 | 148 | 133.5 | 0.5 | 93 | 140 | 148 | 133.5 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 0.3 | 26.9674 | 8.0902 | Avoid | 0.3 | 14.9819 | 4.4946 | H2 | 4 | Stable | [10 empty] | 44.4444 | 0 | 0 | 26.6667
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-21 | 0.5 | 26.9674 | 13.4837 | Avoid | 0.1 | 12.7646 | 1.2765 | H2 | 4 | Worsening | [10 empty] | 52.6667 | 80 | 0 | 31.6
2017-09-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK004 | Project_048_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 3.1534 | 0.63068 | Reduce | 0.15 | 3.1534 | 0.47301 | H3 | 3 | Stable | 0.8 | 98 | 133 | 141 | 128.5 | 0.1 | 22 | 57 | 71 | 53.5 | 0 | 25 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-20 22:00 | 2019-08-20 | 0.5 | 0 | 0 | Accept | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.9 | 80 | 133 | 142 | 125.6667 | 0.9 | 80 | 133 | 142 | 125.6667 |  | 0 | 0
2017-09-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK003 | Project_048_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Lead Times | Person_261 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 1.1285 | 0.22571 | Avoid | 0.2 | 1.1285 | 0.22571 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-09-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK014 | Project_048_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2020-05-22 | 0.2 | 0.61932 | 0.12386 | Reduce | 0.2 | 0.61932 | 0.12386 | H3 | 3 | Stable | 0.9 | 89 | 123 | 145 | 121 | 0.3 | 18 | 43 | 69 | 43.1667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK006 | Project_048_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Customer | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0.20644 | 0.041288 | Reduce | 0.15 | 0.20644 | 0.030966 | H3 | 3 | Stable | 0.6 | 108 | 124 | 159 | 127.1667 | 0.1 | 14 | 41 | 71 | 41.5 | 0 | 25 | 0 | 0
2017-09-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK005 | Project_048_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 3.3031 | 1.9818 | Avoid | 0.5 | 3.3031 | 1.6515 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2017-09-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK011 | Project_048_RISK011 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Line Qualification | Person_551 | 2017-02-20 01:00 | 2019-05-23 | 0.2 | 0.61932 | 0.12386 | Reduce | 0.2 | 0.61932 | 0.12386 | H3 | 3 | Stable | 0.6 | 105 | 139 | 143 | 134 | 0.4 | 19 | 59 | 64 | 53.1667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK010 | Project_048_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Material | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.25 | 0 | 0 | Avoid | 0.25 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-09-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK002 | Project_048_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2020-05-22 | 0.15 | 0.30966 | 0.046449 | Avoid | 0.15 | 0.30966 | 0.046449 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-09-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK001 | Project_048_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Procurement | Person_261 | 2017-02-20 01:00 | 2019-05-23 | 0.2 | 5.5679 | 1.1136 | Reduce | 0.1 | 10.1827 | 1.0183 | H3 | 3 | Stable | 0.6 | 101 | 137 | 154 | 133.8333 | 0.2 | 11 | 49 | 67 | 45.6667 | -82.8827 | 50 | 1 | -48.2296
2017-09-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK012 | Project_048_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Customer requires additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 1.0666 | 0.21332 | Avoid | 0.2 | 1.0666 | 0.21332 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-09-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK008 | Project_048_RISK008 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Oracle | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0.20644 | 0.041288 | Avoid | 0.2 | 0.20644 | 0.041288 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK007 | Project_048_RISK007 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Staff Availability | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0.61932 | 0.12386 | Avoid | 0.2 | 0.61932 | 0.12386 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK009 | Project_048_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Supplier Performance | Person_261 | 2017-02-20 01:00 | 2020-05-22 | 0.3 | 0.72254 | 0.21676 | Reduce | 0.3 | 0.72254 | 0.21676 | H2 | 4 | Stable | 0.8 | 97 | 129 | 158 | 128.5 | 0.4 | 39 | 48 | 76 | 51.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.2 | 0 | 0 | Accept | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.7 | 120 | 125 | 150 | 128.3333 | 0.7 | 120 | 125 | 150 | 128.3333 |  | 0 | 0
2017-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-04-20 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.5 | 85 | 129 | 154 | 125.8333 | 0.3 | 14 | 46 | 67 | 44.1667 | 0 | 25 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 1.8788 | 0.46971 | Accept | 0.35 | 1.5031 | 0.22546 | H3 | 3 | Stable | 0.7 | 120 | 122 | 146 | 125.6667 | 0.7 | 120 | 122 | 146 | 125.6667 | 20 | 0 | 0 | 12
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.25 | 5.596 | 0.2798 | Accept | 0.25 | 5.596 | 0.2798 | H3 | 3 | Stable | 0.5 | 83 | 134 | 141 | 126.6667 | 0.5 | 83 | 134 | 141 | 126.6667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 0.5 | 0.56365 | 0.11273 | Accept | 0.5 | 0.56365 | 0.11273 | H2 | 4 | Improving | 0.7 | 114 | 125 | 143 | 126.1667 | 0.7 | 114 | 125 | 143 | 126.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 0.3 | 1.8788 | 0.46971 | Accept | 0.3 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.7 | 107 | 129 | 146 | 128.1667 | 0.7 | 107 | 129 | 146 | 128.1667 | 20 | 0 | 0 | 12
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R013 | Project_016_Risk--R013 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Resource Availability (Threat) | Person_697 | 2016-04-02 | 2019-08-01 | 0.2 | 1.8788 | 0.46971 | Accept | 0.2 | 1.5031 | 0.22546 | H2 | 4 | Worsening | 0.6 | 104 | 127 | 152 | 127.3333 | 0.6 | 104 | 127 | 152 | 127.3333 | 20 | 0 | 0 | 12
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 | 2017-08-20 | 0.1 | 53.0293 | 5.3029 | Reduce | 0.1 | 53.0293 | 5.3029 | H3 | 3 | Worsening | 0.8 | 85 | 125 | 147 | 122 | 0.3 | 18 | 51 | 73 | 49.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 0.61 | 4.6971 | 0.93941 | Accept | 0.61 | 3.7576 | 0.67638 | H1 | 5 | Stable | 0.8 | 82 | 133 | 151 | 127.5 | 0.8 | 82 | 133 | 151 | 127.5 | 20 | 0 | 0 | 12
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK044 | Project_042_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2018-02-20 01:00 | 2018-12-21 01:00 | 0.32 | 6.5759 | 2.1043 | -- | 0.32 | 6.5759 | 2.1043 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 | 2017-08-20 | 0.1 | 7.7469 | 0.77469 | Reduce | 0.1 | 7.7469 | 0.77469 | H3 | 3 | Stable | 0.8 | 102 | 137 | 155 | 134.1667 | 0.1 | 33 | 51 | 76 | 52.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 1.8788 | 0.18788 | Accept | 0.25 | 1.8788 | 0.18788 | H2 | 4 | Stable | 0.9 | 81 | 131 | 146 | 125.1667 | 0.9 | 81 | 131 | 146 | 125.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 11.3437 | 0.56718 | Accept | 0.3 | 11.3437 | 0.56718 | H2 | 4 | Stable | 0.7 | 81 | 139 | 152 | 131.5 | 0.7 | 81 | 139 | 152 | 131.5 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 0.5 | 9.3941 | 3.1001 | Accept | 0.5 | 7.5153 | 2.2546 | H2 | 4 | Stable | 0.9 | 120 | 123 | 145 | 126.1667 | 0.9 | 120 | 123 | 145 | 126.1667 | 20 | 0 | 0 | 12
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2017-02-20 | 2018-05-22 | 0.1 | 0.56365 | 0.11273 | Accept | 0.1 | 0.56365 | 0.11273 | H3 | 3 | Stable | 0.9 | 95 | 140 | 148 | 133.8333 | 0.9 | 95 | 140 | 148 | 133.8333 | 0 | 0 | 1 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK003 | Project_024_RISK003 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance | Person_288 | 2017-12-21 | 2018-08-21 | 0.31667 | 4.6971 | 0.93941 | Accept | 0.007456 | 3.7576 | 0.67638 | H2 | 4 | Stable | 0.5 | 118 | 134 | 142 | 132.6667 | 0.5 | 118 | 134 | 142 | 132.6667 | 20 | 97.6455 | 0 | 12
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK045 | Project_042_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2019-01-22 01:00 | 2019-05-23 | 0.25 | 3.908 | 0.97699 | -- | 0.25 | 3.908 | 0.97699 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Management Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 | 2018-05-21 | 0.3 | 1.8788 | 0.46971 | Accept | 0.3 | 1.1273 | 0.11273 | H1 | 5 | Improving | 0.8 | 111 | 124 | 153 | 126.6667 | 0.8 | 111 | 124 | 153 | 126.6667 | 40 | 0 | 0 | 24
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Equipment environmental failure | Person_710 | 2016-05-23 | 2017-09-19 | 0.3 | 0 | 0 | Accept | 0.3 | 0 | 0 | H1 | 5 | Improving | 0.5 | 87 | 132 | 141 | 126 | 0.5 | 87 | 132 | 141 | 126 |  | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK300(020) | Project_024_RISK300(020) | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Travel and onsite support | Person_119 | 2017-01-20 | 2018-04-21 | 0.25 | 1.8788 | 0.37576 | Accept | 0.25 | 1.4091 | 0.21137 | H3 | 3 | Stable | 0.8 | 113 | 131 | 151 | 131.3333 | 0.8 | 113 | 131 | 151 | 131.3333 | 25 | 0 | 0 | 15
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK304(026) | Project_024_RISK304(026) | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | complex integration | Person_119 | 2016-10-20 | 2018-01-20 | 0.4 | 0.81199 | 0.081199 | Accept | 0.4 | 0.81199 | 0.0406 | H1 | 5 | Worsening | 0.7 | 118 | 124 | 153 | 127.8333 | 0.7 | 118 | 124 | 153 | 127.8333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK303(025) | Project_024_RISK303(025) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in contract value from our supplier | Person_119 | 2016-10-20 | 2019-05-23 | 0.25 | 3.7576 | 0.75153 | Accept | 0.25 | 2.8182 | 0.42274 | H2 | 4 | Stable | 0.5 | 119 | 139 | 146 | 136.8333 | 0.5 | 119 | 139 | 146 | 136.8333 | 25 | 0 | 0 | 15
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK305(027) | Project_024_RISK305(027) | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Customer Furnished Equipment not available on time | Person_119 | 2016-11-19 | 2019-05-23 | 0.3 | 1.2198 | 0.60991 | Accept | 0.3 | 1.2198 | 0.60991 | H1 | 5 | Stable | 0.9 | 104 | 127 | 151 | 127.1667 | 0.9 | 104 | 127 | 151 | 127.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK296(013) | Project_024_RISK296(013) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Qualification/Certification Requirements flowdown | Person_119 | 2016-10-20 | 2017-08-20 | 0.25 | 2.2828 | 0.31959 | Accept | 0.25 | 2.2828 | 0.31959 | H2 | 4 | Worsening | 0.9 | 119 | 138 | 156 | 137.8333 | 0.9 | 119 | 138 | 156 | 137.8333 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before part b finished | Person_119 | 2016-10-20 | 2018-04-21 | 0.35 | 6.0991 | 0 | Accept | 0.35 | 6.0991 | 4.0864 | H2 | 4 | Worsening | 0.6 | 90 | 124 | 147 | 122.1667 | 0.6 | 90 | 124 | 147 | 122.1667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK298(016) | Project_024_RISK298(016) | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Environmental testing required | Person_119 | 2016-10-20 | 2017-10-20 | 0.2 | 2.1419 | 0.53546 | Accept | 0.2 | 2.1419 | 0.53546 | H2 | 4 | Stable | 0.6 | 92 | 121 | 145 | 120.1667 | 0.6 | 92 | 121 | 145 | 120.1667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PEN Testing Security Features | Person_604 | 2015-04-11 | 2018-01-20 01:00 | 0.3 | 5.4553 | 1.6366 | Reduce | 0.2 | 5.252 | 1.0504 | H2 | 4 | Stable | 0.9 | 81 | 130 | 156 | 126.1667 | 0.4 | 34 | 57 | 73 | 55.8333 | 3.7267 | 33.3333 | 0 | 2.236
2017-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK299(018) | Project_024_RISK299(018) | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Additional support hours | Person_119 | 2017-01-20 | 2018-04-21 | 0.35 | 0.5596 | 0.05596 | Accept | 0.35 | 0.5596 | 0.05596 | H3 | 3 | Stable | 0.7 | 89 | 125 | 141 | 121.6667 | 0.7 | 89 | 125 | 141 | 121.6667 | 0 | 0 | 1 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Platforms Cable and connectors | Person_499 | 2015-11-21 01:00 | 2019-04-10 | 0.45 | 0.41338 | 0.18602 | Reduce | 0.05 | 0.41338 | 0.020669 | H2 | 4 | Stable | 0.9 | 92 | 133 | 143 | 127.8333 | 0.4 | 21 | 42 | 69 | 43 | 0 | 88.8889 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | FOC Acceptance | Person_499 | 2015-11-21 01:00 | 2018-02-18 01:00 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.3 | 8.471 | 2.5413 | H2 | 4 | Stable | 0.5 | 90 | 129 | 141 | 124.5 | 0.4 | 6 | 45 | 64 | 41.6667 | -99.9999 | 14.2857 | 0 | -59.9999
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2018-05-22 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.7 | 102 | 130 | 143 | 127.5 | 0.3 | 4 | 56 | 64 | 48.6667 | 0 | 40 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 0.5 | 1.8788 | 0.37576 | Accept | 0.5 | 1.5031 | 0.22546 | H2 | 4 | Improving | 0.8 | 83 | 126 | 152 | 123.1667 | 0.8 | 83 | 126 | 152 | 123.1667 | 20 | 0 | 0 | 12
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-20 22:00 | 0.3 | 8.8098 | 3.0834 | Accept | 0.3 | 8.8098 | 1.762 | H2 | 4 | Stable | 0.5 | 99 | 138 | 145 | 132.6667 | 0.5 | 99 | 138 | 145 | 132.6667 | 0 | 0 | 0 | 0
2017-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R013 | Project_016_Risk--R013 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Resource Availability (Threat) | Person_697 | 2016-04-02 | 2019-08-01 | 0.2 | 11.0894 | 0.55447 | Accept | 0.2 | 11.0894 | 0.55447 | H2 | 4 | Worsening | 0.6 | 80 | 131 | 147 | 125.1667 | 0.6 | 80 | 131 | 147 | 125.1667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 0.61 | 2.3503 | 0.47006 | Accept | 0.61 | 2.3503 | 0.47006 | H1 | 5 | Stable | 0.5 | 96 | 132 | 145 | 128.1667 | 0.5 | 96 | 132 | 145 | 128.1667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 | 2020-08-20 | 0.5 | 1.1273 | 0.22546 | Accept | 0.5 | 0.93941 | 0.14091 | H2 | 4 | Stable | 0.8 | 81 | 138 | 152 | 130.8333 | 0.8 | 81 | 138 | 152 | 130.8333 | 16.6667 | 0 | 0 | 10
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.7 | 0.92411 | 0.64688 | Reduce | 0.3 | 0.36965 | 0.11089 | H2 | 4 | Stable | 0.8 | 113 | 132 | 143 | 130.6667 | 0.2 | 11 | 42 | 67 | 41 | 60 | 57.1429 | 0 | 36
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 4.4768 | 2.2384 | Accept | 0.5 | 4.4768 | 2.2384 | H2 | 4 | Stable | 0.8 | 97 | 130 | 147 | 127.3333 | 0.8 | 97 | 130 | 147 | 127.3333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Furnished Equipmnet Condition | Person_496 | 2015-04-27 | 2019-04-10 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.9 | 119 | 127 | 144 | 128.5 | 0.2 | 23 | 48 | 78 | 48.8333 |  | 62.5 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 | 2016-11-20 | 0.25 | 1.8788 | 0.37576 | Accept | 0.1 | 1.8788 | 0.37576 | H3 | 3 | Stable | 0.5 | 81 | 133 | 158 | 128.5 | 0.5 | 81 | 133 | 158 | 128.5 | 0 | 60 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 01:00 | 2018-04-21 | 0.5 | 4.0661 | 2.033 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.7 | 105 | 140 | 146 | 135.1667 | 0.1 | 38 | 51 | 62 | 50.6667 | 0 | 90 | 1 | 2.7
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-20 | 0.25 | 1.7281 | 1.3825 | Accept | 0.15 | 1.7281 | 1.3825 | H3 | 3 | Stable | 0.6 | 81 | 133 | 141 | 125.6667 | 0.6 | 81 | 133 | 141 | 125.6667 | 0 | 40 | 1 | 1.2
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.5 | 0.46206 | 0.23103 | H1 | 5 | Improving | 0.8 | 91 | 136 | 147 | 130.3333 | 0.4 | 18 | 51 | 60 | 47 | 58.3333 | 16.6667 | 0 | 35
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK026 | Project_042_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st Jan to 31st March | Person_455 | 2020-05-23 | 2020-08-20 01:00 | 0.25 | 1.1089 | 0.88715 | Accept | 0.15 | 0.73929 | 0.44357 | H2 | 4 | Stable | 0.9 | 103 | 125 | 144 | 124.5 | 0.9 | 103 | 125 | 144 | 124.5 | 33.3333 | 40 | 0 | 20
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK047 | Project_042_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables | Person_455 | 2020-11-20 01:00 | 2021-05-22 | 0.2 | 1.8788 | 0.18788 | Accept | 0.2 | 1.8788 | 0.18788 | H2 | 4 | Stable | 0.5 | 88 | 138 | 157 | 132.8333 | 0.5 | 88 | 138 | 157 | 132.8333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 01:00 | 2018-05-22 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.6 | 105 | 123 | 141 | 123 | 0.3 | 19 | 50 | 61 | 46.6667 | 0 | 50 | 1 | 1.5
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK028 | Project_042_RISK028 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st July to 30th September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 0.25 | 6.4382 | 2.2534 | Accept | 0.15 | 6.4382 | 1.2876 | H2 | 4 | Stable | 0.9 | 88 | 138 | 144 | 130.6667 | 0.9 | 88 | 138 | 144 | 130.6667 | 0 | 40 | 0 | 0
2017-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_077 | 2016-01-22 01:00 | 2018-02-17 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H1 | 5 | Improving | 0.7 | 92 | 137 | 157 | 132.8333 | 0.1 | 25 | 49 | 60 | 46.8333 |  | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2018-05-22 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.6 | 116 | 122 | 156 | 126.6667 | 0.4 | 5 | 40 | 73 | 39.6667 | 0 | 25 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK027 | Project_042_RISK027 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st April to 30th June | Person_455 | 2020-08-21 01:00 | 2020-09-19 01:00 | 0.25 | 1.8788 | 0.18788 | Accept | 0.15 | 1.8788 | 0.18788 | H2 | 4 | Stable | 0.8 | 91 | 138 | 156 | 133.1667 | 0.8 | 91 | 138 | 156 | 133.1667 | 0 | 40 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK022 | Project_042_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2017-09-20 01:00 | 2018-09-20 01:00 | 0.2 | 5.4729 | 4.3783 | Accept | 0.18 | 4.6191 | 1.3857 | H2 | 4 | Stable | 0.7 | 92 | 124 | 146 | 122.3333 | 0.7 | 92 | 124 | 146 | 122.3333 | 15.6018 | 10 | 0 | 9.3611
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK043 | Project_042_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st December | Person_455 | 2021-03-23 | 2021-05-22 | 0.1 | 1.8788 | 0.18788 | Accept | 0.1 | 0.79775 | 0.039887 | H2 | 4 | Stable | 0.8 | 118 | 129 | 155 | 131.5 | 0.8 | 118 | 129 | 155 | 131.5 | 57.54 | 0 | 0 | 34.524
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_693 | 2012-06-01 | 2018-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Improving | 0.6 | 80 | 122 | 149 | 119.5 | 0.1 | 26 | 47 | 67 | 46.8333 | 0 | 40 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 | 0.05 | 3.922 | 0.98049 | Accept | 0.05 | 3.922 | 0.98049 | H3 | 3 | Stable | 0.6 | 86 | 129 | 141 | 123.8333 | 0.6 | 86 | 129 | 141 | 123.8333 | 0 | 0 | 1 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK024 | Project_042_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2019-09-21 01:00 | 2020-09-19 01:00 | 0.33 | 35.0206 | 7.0041 | Accept | 0.3 | 35.0206 | 7.0041 | H2 | 4 | Stable | 0.5 | 94 | 140 | 149 | 133.8333 | 0.5 | 94 | 140 | 149 | 133.8333 | 0 | 9.0909 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-090 | Project_008_Risk-090 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Demands but not provisioned | Person_639 | 2017-04-22 | 2018-08-21 | 0.3 | 3.7878 | 1.1363 | Reduce | 0.3 | 3.7878 | 1.1363 | H3 | 3 | Stable | 0.6 | 101 | 124 | 157 | 125.6667 | 0.4 | 8 | 40 | 69 | 39.5 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2018-05-21 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Stable | [10 empty] | 0 | 37.5 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK046 | Project_042_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables - June | Person_455 | 2018-11-21 01:00 | 2020-11-19 01:00 | 0.2 | 49.4398 | 19.7759 | Accept | 0.2 | 49.4398 | 9.888 | H2 | 4 | Stable | 0.9 | 102 | 138 | 159 | 135.5 | 0.9 | 102 | 138 | 159 | 135.5 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-080 | Project_008_Risk-080 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Recovery of Costs | Person_567 | 2016-08-21 01:00 | 2017-08-20 01:00 | 0.5 | 23.6737 | 11.8369 | -- | 0.5 | 23.6737 | 11.8369 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK023 | Project_042_RISK023 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2018-09-21 01:00 | 2019-09-20 01:00 | 0.2 | 3.6965 | 0.36965 | Accept | 0.18 | 3.6965 | 0.36965 | H2 | 4 | Stable | 0.9 | 117 | 128 | 156 | 130.8333 | 0.9 | 117 | 128 | 156 | 130.8333 | 0 | 10 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK029 | Project_042_RISK029 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st October to 31st December | Person_455 | 2021-02-20 01:00 | 2021-05-22 | 0.25 | 46.5584 | 20.9513 | Accept | 0.1 | 46.5584 | 20.9513 | H2 | 4 | Stable | 0.7 | 86 | 128 | 155 | 125.5 | 0.7 | 86 | 128 | 155 | 125.5 | 0 | 60 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK031 | Project_042_RISK031 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours 30th June to 30th September | Person_455 | 2020-08-20 01:00 | 2021-02-19 01:00 | 0.2 | 15.8141 | 3.9535 | Accept | 0.15 | 15.8141 | 3.9535 | H2 | 4 | Stable | 0.7 | 114 | 121 | 152 | 125 | 0.7 | 114 | 121 | 152 | 125 | 0 | 25 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Further Software Development | Person_523 | 2015-05-24 | 2018-04-21 | 0.1 | 1.8482 | 0.55447 | Accept | 0.05 | 1.8482 | 0.73929 | H3 | 3 | Stable | 0.8 | 110 | 140 | 148 | 136.3333 | 0.8 | 110 | 140 | 148 | 136.3333 | 0 | 50 | 1 | 1.5
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Survey costs | Person_618 | 2016-04-22 | 2017-12-20 01:00 | 0.2 | 13.2573 | 2.6515 | Avoid | 0.2 | 13.2573 | 2.6515 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2018-02-19 01:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.9 | 101 | 130 | 151 | 128.6667 | 0.3 | 16 | 58 | 70 | 53 | 90 | 75 | 1 | 56.25
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-079 | Project_008_Risk-079 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Regulations Phase 3 and 4 | Person_567 | 2016-10-21 01:00 | 2018-08-21 | 0.25 | 71.9682 | 17.992 | -- | 0.25 | 71.9682 | 17.992 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK030 | Project_042_RISK030 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours 31st March to 29 June | Person_455 | 2020-08-20 01:00 | 2020-11-18 01:00 | 0.2 | 6.3794 | 1.2759 | Accept | 0.15 | 6.3794 | 1.2759 | H2 | 4 | Stable | 0.9 | 82 | 132 | 157 | 127.8333 | 0.9 | 82 | 132 | 157 | 127.8333 | 0 | 25 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Interface implementation | Person_496 | 2014-01-21 01:00 | 2017-10-20 01:00 | 0.5 | 33.9324 | 10.1797 | Accept | 0.5 | 33.9324 | 10.1797 | H2 | 4 | Stable | 0.8 | 97 | 123 | 153 | 123.6667 | 0.8 | 97 | 123 | 153 | 123.6667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK037 | Project_042_RISK037 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 1 | Person_455 | 2020-05-23 | 2021-05-22 | 0.14 | 23.5255 | 11.7628 | Accept | 0.14 | 23.5255 | 11.7628 | H2 | 4 | Stable | 0.7 | 119 | 133 | 146 | 132.8333 | 0.7 | 119 | 133 | 146 | 132.8333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of the platforms for modification | Person_496 | 2014-01-21 01:00 | 2018-02-18 01:00 | 0 | 60.4367 | 3.0218 | Accept | 0.67 | 60.4367 | 3.0218 | H3 | 3 | Stable | 0.7 | 119 | 138 | 143 | 135.6667 | 0.7 | 119 | 138 | 143 | 135.6667 | 0 | -inf | 1 | -inf
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK036 | Project_042_RISK036 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 2 | Person_455 | 2019-05-24 | 2020-05-22 | 0.25 | 22.384 | 11.192 | Accept | 0.25 | 22.384 | 11.192 | H2 | 4 | Stable | 0.6 | 92 | 137 | 147 | 131.1667 | 0.6 | 92 | 137 | 147 | 131.1667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK039 | Project_042_RISK039 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality Issues 16th August to 15th August | Person_251 | 2020-01-06 01:00 | 2021-01-04 01:00 | 0.1 | 5.8198 | 4.0739 | Accept | 0.1 | 5.8198 | 4.0739 | H2 | 4 | Stable | 0.9 | 117 | 122 | 147 | 125.3333 | 0.9 | 117 | 122 | 147 | 125.3333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2018-04-21 | 0.15 | 0.58983 | 0.088474 | -- | 0.15 | 0.58983 | 0.088474 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 0.2 | 0.62279 | 0.12456 | Avoid | 0.2 | 0.62279 | 0.12456 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-12-06 01:00 | 0.1 | 0.27503 | 0.027503 | -- | 0.1 | 0.27503 | 0.027503 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 0.2 | 1.8854 | 0.37708 | Reduce | 0.2 | 1.8854 | 0.37708 | H2 | 4 | Stable | 0.8 | 112 | 135 | 142 | 132.3333 | 0.2 | 11 | 42 | 66 | 40.8333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2017-10-21 01:00 | 2018-08-21 | 0.4 | 1.4138 | 0.56551 | Reduce | 0.4 | 1.4138 | 0.56551 | H2 | 4 | Stable | 0.5 | 87 | 124 | 159 | 123.6667 | 0.2 | 27 | 56 | 61 | 52 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK038 | Project_042_RISK038 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality Issues 16th August to 15th August | Person_251 | 2019-01-06 01:00 | 2020-01-05 01:00 | 0.1 | 0.18354 | 0.045885 | Accept | 0.1 | 0.18354 | 0.045885 | H2 | 4 | Stable | 0.9 | 105 | 121 | 149 | 123 | 0.9 | 105 | 121 | 149 | 123 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK033 | Project_042_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st April to 30 June | Person_455 | 2019-08-22 01:00 | 2019-11-20 01:00 | 0.2 | 0.11081 | 0.011081 | Accept | 0.15 | 0.11081 | 0.011081 | H2 | 4 | Stable | 0.8 | 110 | 137 | 154 | 135.3333 | 0.8 | 110 | 137 | 154 | 135.3333 | 0 | 25 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-10-19 01:00 | 2018-08-21 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.5 | 103 | 121 | 155 | 123.6667 | 0.1 | 12 | 40 | 78 | 41.6667 |  | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Pick up and Drop off of Software Resource | Person_230 | 2017-12-19 01:00 | 2018-02-19 01:00 | 0.4 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 0.4 | 0.19206 | 0.076826 | -- | 0.4 | 0.19206 | 0.076826 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 0.4 | 0.58017 | 0.23207 | Avoid | 0.4 | 0.58017 | 0.23207 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_523 | 2015-01-22 01:00 | 2018-04-21 | 0.35 | 0.49834 | 0.12459 | Accept | 0.2 | 0.49834 | 0.12459 | H2 | 4 | Stable | 0.9 | 118 | 134 | 146 | 133.3333 | 0.9 | 118 | 134 | 146 | 133.3333 | 0 | 42.8571 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.2 | 0.11365 | 0.022729 | -- | 0.2 | 0.11365 | 0.022729 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 0.55 | 0.32389 | 0.17814 | Reduce | 0.55 | 0.32389 | 0.17814 | H1 | 5 | Stable | 0.6 | 105 | 132 | 148 | 130.1667 | 0.4 | 6 | 48 | 69 | 44.5 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2017-10-21 01:00 | 2018-05-21 | 0.4 | 0.19206 | 0.076826 | -- | 0.4 | 0.19206 | 0.076826 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 0.3 | 0.11933 | 0.035799 | -- | 0.3 | 0.022161 | 0.0066484 | H3 | 3 | Stable | [10 empty] | 81.4286 | 0 | 0 | 48.8571
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.05 | 1.1416 | 0.68495 | Accept | 0.05 | 1.1416 | 0.68495 | H2 | 4 | Stable | 0.8 | 110 | 124 | 148 | 125.6667 | 0.8 | 110 | 124 | 148 | 125.6667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-117 | Project_011_Risk-117 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Avaliability for testing/reviews | Person_147 | 2016-07-21 | 2018-08-21 | 0.35 | 0 | 0 | Avoid | 0.35 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-128 | Project_011_Risk-128 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Incorrect Maps used during Qualification | Person_147 | 2017-04-22 | 2018-01-21 01:00 | 0.5 | 0.05688 | 0.02844 | Transfer | 0.5 | 0.05688 | 0.02844 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-129 | Project_011_Risk-129 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Signature of Work Authorisation documents | Person_140 | 2017-05-24 | 2018-01-21 01:00 | 0.2 | 0.12643 | 0.025287 | -- | 0.2 | 0.12643 | 0.025287 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-130 | Project_011_Risk-130 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer does not accept Voice Pronounciation | Person_187 | 2017-05-24 | 2018-02-19 01:00 | 0.4 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 1.3834 | 0.55336 | H2 | 4 | Stable | 0.5 | 85 | 123 | 146 | 120.5 | 0.1 | 15 | 47 | 66 | 44.8333 | 65.054 | 20 | 0 | 39.0324
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_703 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 5.0983 | 0.76474 | H3 | 3 | Stable | 0.9 | 92 | 140 | 149 | 133.5 | 0.4 | 6 | 57 | 61 | 49.1667 | 19.0479 | 70 | 1 | 13.5287
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_332 | 2016-06-23 | 2018-02-19 01:00 | 0.4 | 11.2729 | 2.2546 | Accept | 0.2 | 11.2729 | 2.2546 | H2 | 4 | Stable | 0.6 | 102 | 132 | 142 | 128.6667 | 0.6 | 102 | 132 | 142 | 128.6667 | 0 | 50 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK032 | Project_042_RISK032 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours 30th June to 30th September | Person_455 | 2020-08-20 01:00 | 2021-02-19 01:00 | 0.2 | 3.7576 | 0.18788 | Accept | 0.15 | 3.7576 | 0.56365 | H2 | 4 | Stable | 0.5 | 92 | 125 | 143 | 122.5 | 0.5 | 92 | 125 | 143 | 122.5 | 0 | 25 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK035 | Project_042_RISK035 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st October to 31st December | Person_455 | 2021-02-20 01:00 | 2021-05-22 | 0.2 | 1.0618 | 0.53089 | Accept | 0.2 | 1.0618 | 0.53089 | H2 | 4 | Stable | 0.6 | 110 | 122 | 154 | 125.3333 | 0.6 | 110 | 122 | 154 | 125.3333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-002 | Project_021_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.6 | 116 | 138 | 142 | 135 | 0.3 | 13 | 44 | 69 | 43 |  | 66.6667 | 1
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H3 | 3 | Stable | 0.5 | 118 | 134 | 148 | 133.6667 | 0.3 | 20 | 50 | 60 | 46.6667 |  | 62.5 | 1
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-009 | Project_021_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification Report delays due to insufficient resource in supply chain | Person_207 | 2017-09-20 01:00 | 2017-12-20 01:00 | 0.2 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.6 | 103 | 122 | 158 | 124.8333 | 0.3 | 16 | 47 | 72 | 46 |  | 50 | 1
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-004 | Project_021_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 82 | 135 | 148 | 128.3333 | 0.2 | 39 | 58 | 65 | 56 |  | 80 | 1
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-014 | Project_021_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.5 | 91 | 131 | 159 | 129 | 0.1 | 5 | 40 | 70 | 39.1667 |  | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-013 | Project_021_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to late Trials Approval | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.5 | 101 | 139 | 147 | 134 | 0.1 | 15 | 53 | 72 | 49.8333 |  | 66.6667 | 1
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification delays | Person_207 | 2017-09-20 01:00 | 2017-11-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Worsening | 0.8 | 82 | 126 | 149 | 122.5 | 0.3 | 19 | 49 | 68 | 47.1667 |  | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-018 | Project_021_Risk-018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2017-05-23 | 2017-11-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 91 | 135 | 143 | 129 | 0.2 | 35 | 59 | 72 | 57.1667 |  | 40 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-017 | Project_021_Risk-017 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target. | Person_061 | 2013-01-07 01:00 | 2018-02-04 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.5 | 109 | 137 | 148 | 134.1667 | 0.1 | 24 | 59 | 70 | 55 | 0 | 33.3333 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-015 | Project_021_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to technical performance | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.3 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.5 | 114 | 128 | 150 | 129.3333 | 0.3 | 28 | 44 | 61 | 44.1667 |  | 33.3333 | 1
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK021 | Project_021_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | ERP implementation | Person_174 | 2017-06-23 | 2017-09-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.25 | 0 | 0 | H2 | 4 | Stable | 0.6 | 116 | 138 | 152 | 136.6667 | 0.1 | 27 | 53 | 72 | 51.8333 |  | 50 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_174 | 2012-11-20 01:00 | 2018-08-21 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.8 | 87 | 122 | 159 | 122.3333 | 0.4 | 16 | 52 | 64 | 48 | 0 | 50 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK024 | Project_021_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_482 | 2017-05-23 | 2017-11-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 91 | 122 | 141 | 120 | 0.2 | 34 | 53 | 72 | 53 |  | 40 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2018-02-19 01:00 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Stable | 0.6 | 85 | 133 | 145 | 127 | 0.1 | 33 | 54 | 75 | 54 | 0 | 57.1429 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 0.8 | 4.6352 | 3.7081 | Reduce | 0.6 | 4.6352 | 2.7811 | H1 | 5 | Worsening | 0.9 | 105 | 130 | 152 | 129.5 | 0.2 | 18 | 40 | 67 | 40.8333 | 0 | 25 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-12-20 01:00 | 0.6 | 17.2826 | 10.3696 | Reduce | 0.3 | 17.2826 | 5.1848 | H2 | 4 | Worsening | 0.9 | 106 | 134 | 142 | 130.6667 | 0.1 | 8 | 41 | 64 | 39.3333 | 0 | 50 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Additional tasks required with mode certification | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 0.8 | 1.3243 | 1.0595 | Reduce | 0.6 | 1.3243 | 0.7946 | H1 | 5 | Worsening | 0.5 | 110 | 130 | 157 | 131.1667 | 0.2 | 29 | 41 | 66 | 43.1667 | 0 | 25 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2018-01-19 01:00 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.5 | 86 | 126 | 157 | 124.5 | 0.2 | 26 | 41 | 69 | 43.1667 | 80 | 66.6667 | 0 | 48
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond (revised) target. | Person_482 | 2013-01-07 01:00 | 2018-02-04 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.8 | 117 | 128 | 143 | 128.6667 | 0.3 | 21 | 55 | 74 | 52.5 | 0 | 33.3333 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2013-01-07 01:00 | 2017-11-19 01:00 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.9 | 81 | 129 | 149 | 124.3333 | 0.2 | 39 | 59 | 71 | 57.6667 | 0 | 33.3333 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_174 | 2009-06-23 | 2018-08-21 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.9 | 91 | 138 | 146 | 131.5 | 0.1 | 2 | 59 | 77 | 52.5 | 50 | 28.5714 | 0 | 30
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-09-19 01:00 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.7 | 98 | 138 | 152 | 133.6667 | 0.1 | 10 | 52 | 72 | 48.3333 | 7.8429 | 40 | 0 | 4.7058
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-12-17 01:00 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.4 | 12.6474 | 5.059 | H2 | 4 | Stable | 0.8 | 107 | 122 | 160 | 125.8333 | 0.2 | 12 | 47 | 64 | 44 | 0 | 33.3333 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.6 | 109 | 135 | 146 | 132.5 | 0.3 | 31 | 50 | 76 | 51.1667 | 0 | 50 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK034 | Project_042_RISK034 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st July to 30 September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 0.2 | 186.9553 | 59.2026 | Accept | 0.2 | 186.9553 | 1.3939 | H2 | 4 | Stable | 0.5 | 83 | 124 | 148 | 121.1667 | 0.5 | 83 | 124 | 148 | 121.1667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Additional minor point releases | Person_228 | 2016-05-23 | 2017-10-19 01:00 | 0.5 | 11.9444 | 5.9722 | Reduce | 0.25 | 11.9444 | 2.9861 | H2 | 4 | Stable | 0.5 | 95 | 122 | 149 | 122 | 0.3 | 30 | 42 | 65 | 43.8333 | 0 | 50 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_228 | 2016-05-23 | 2018-04-21 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.5 | 115 | 129 | 147 | 129.6667 | 0.4 | 20 | 56 | 73 | 52.8333 | 0 | 50 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_004 | 2015-11-21 01:00 | 2018-11-20 01:00 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.9 | 80 | 138 | 159 | 131.8333 | 0.3 | 5 | 48 | 69 | 44.3333 | 0 | 5 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.8 | 2.8043 | 2.2435 | Reduce | 0.45 | 2.8043 | 1.2619 | H1 | 5 | Stable | 0.8 | 106 | 125 | 158 | 127.3333 | 0.4 | 12 | 52 | 71 | 48.5 | 0 | 43.75 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK167 | Project_024_RISK167 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Customer not providing the information needed | Person_710 | 2016-08-21 01:00 | 2018-02-19 01:00 | 0.5 | 9.971 | 4.9855 | Reduce | 0.3 | 9.971 | 2.9913 | H1 | 5 | Worsening | 0.9 | 120 | 127 | 155 | 130.5 | 0.2 | 15 | 46 | 64 | 43.8333 | 0 | 40 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK306(028) | Project_024_RISK306(028) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | HW repairs required on units | Person_119 | 2016-11-19 01:00 | 2018-11-20 01:00 | 0.3 | 2.813 | 0.8439 | Reduce | 0.2 | 2.813 | 0.5626 | H2 | 4 | Stable | 0.6 | 108 | 128 | 154 | 129 | 0.1 | 33 | 59 | 71 | 56.6667 | 0 | 33.3333 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2018-04-22 | 0.8 | 0.5626 | 0.14065 | Accept | 0.6 | 0.5626 | 0.14065 | H1 | 5 | Stable | 0.9 | 110 | 140 | 144 | 135.6667 | 0.9 | 110 | 140 | 144 | 135.6667 | 0 | 25 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK040 | Project_042_RISK040 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st May to 30 Oct | Person_455 | 2019-09-21 01:00 | 2020-03-21 | 0.1 | 5.1932 | 2.0773 | Accept | 0.1 | 5.1716 | 2.0686 | H2 | 4 | Stable | 0.5 | 110 | 138 | 148 | 135 | 0.5 | 110 | 138 | 148 | 135 | 0.41665 | 0 | 0 | 0.24999
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK042 | Project_042_RISK042 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st February to 14th July | Person_455 | 2020-06-23 | 2020-12-03 01:00 | 0.1 | 5.1932 | 1.2983 | Accept | 0.1 | 5.1932 | 1.2983 | H2 | 4 | Stable | 0.9 | 109 | 130 | 149 | 129.6667 | 0.9 | 109 | 130 | 149 | 129.6667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Closed | H2 | 4 | 13. Logistic support and Services | Volume of production tools and Jigs | Person_084 | 2016-11-22 22:00 | 2021-11-22 22:00 | 0.35 | 5.1932 | 1.558 | Accept | 0.2 | 5.1932 | 1.558 | H2 | 4 | Stable | 0.9 | 85 | 133 | 152 | 128.1667 | 0.9 | 85 | 133 | 152 | 128.1667 | 0 | 42.8571 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK041 | Project_042_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st Jan | Person_455 | 2020-03-23 | 2020-06-22 | 0.1 | 5.3577 | 1.3394 | Accept | 0.1 | 5.3577 | 1.3394 | H2 | 4 | Stable | 0.9 | 95 | 139 | 141 | 132 | 0.9 | 95 | 139 | 141 | 132 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK226 | Project_024_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Late Evidences delay Certification delivery | Person_710 | 2017-04-30 | 2017-12-21 01:00 | 0.4 | 3.9468 | 1.5787 | Reduce | 0.2 | 3.9468 | 0.78937 | H2 | 4 | Worsening | 0.6 | 91 | 140 | 160 | 135.1667 | 0.2 | 17 | 43 | 65 | 42.3333 | 0 | 50 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK302(024) | Project_024_RISK302(024) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | On time provision of platform units | Person_119 | 2016-11-19 01:00 | 2019-05-23 | 0.25 | 2.3889 | 0.59722 | Reduce | 0.15 | 2.3889 | 0.35833 | H2 | 4 | Stable | 0.6 | 95 | 124 | 153 | 124 | 0.1 | 20 | 43 | 79 | 45.1667 | 0 | 40 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK227 | Project_024_RISK227 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Data Bunching | Person_710 | 2017-03-23 | 2018-01-19 01:00 | 0.4 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H1 | 5 | Stable | 0.6 | 111 | 130 | 146 | 129.5 | 0.2 | 29 | 53 | 76 | 52.8333 |  | 25 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | RISK004 | Project_028_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Changes to be embodied on the Rig | Person_604 | 2017-04-29 | 2019-02-20 01:00 | 0.8 | 4.8297 | 1.6904 | Accept | 0.3 | 4.8297 | 1.6904 | H2 | 4 | Stable | 0.7 | 83 | 136 | 145 | 128.6667 | 0.7 | 83 | 136 | 145 | 128.6667 | 0 | 62.5 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK040 | Project_017_RISK040 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Upgrades | Person_084 | 2016-09-29 22:00 | 2016-12-17 22:00 | 0.35 | 5.1067 | 1.0213 | Accept | 0.35 | 5.1067 | 1.0213 | H2 | 4 | Stable | 0.6 | 112 | 128 | 149 | 128.8333 | 0.6 | 112 | 128 | 149 | 128.8333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Local customer Engineers in country | Person_455 | 2019-03-22 | 2019-05-23 | 0.1 | 0.5626 | 0.19691 | Accept | 0.05 | 0.5626 | 0.19691 | H2 | 4 | Stable | 0.8 | 118 | 126 | 159 | 130.1667 | 0.8 | 118 | 126 | 159 | 130.1667 | 0 | 50 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-085 | Project_008_SER-085 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Insufficient LOE to manage the supply chain with reducing number of spares | Person_639 | 2017-04-22 | 2018-08-21 | 0.25 | 21.1623 | 21.1623 | Accept | 0.25 | 10.0488 | 10.0488 | H3 | 3 | Stable | 0.7 | 118 | 133 | 144 | 132.3333 | 0.7 | 118 | 133 | 144 | 132.3333 | 52.5153 | 0 | 0 | 31.5092
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.5 | 115 | 139 | 148 | 136.5 | 0.1 | 9 | 48 | 73 | 45.6667 | 0 | 60 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis and Security | Person_288 | 2017-02-22 01:00 | 2017-11-19 01:00 | 0.3 | 19.9938 | 5.9981 | Reduce | 0.1 | 19.9938 | 1.9994 | H3 | 3 | Improving | 0.7 | 112 | 131 | 158 | 132.3333 | 0.3 | 17 | 40 | 76 | 42.1667 | 0 | 66.6667 | 1 | 2
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.2 | 3.843 | 0.76859 | H2 | 4 | Stable | 0.6 | 113 | 132 | 141 | 130.3333 | 0.1 | 14 | 46 | 79 | 46.1667 | 0 | 60 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software issue input | Person_084 | 2016-11-22 22:00 | 2023-02-19 22:00 | 0.4 | 15.5796 | 6.2318 | Accept | 0.2 | 15.5796 | 6.2318 | H2 | 4 | Stable | 0.7 | 84 | 129 | 145 | 124.1667 | 0.7 | 84 | 129 | 145 | 124.1667 | 0 | 50 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Performance (collector opportunity) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.3814 | 26.127 | 9.9648 | -- | 0.4132 | 26.127 | 10.7957 | H1 | 5 | Stable | [10 empty] | 0 | -8.3377 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.3 | 20.8767 | 6.263 | H1 | 5 | Stable | 0.9 | 94 | 136 | 157 | 132.5 | 0.3 | 5 | 58 | 65 | 50.3333 | 50 | 25 | 0 | 30
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5094 | 70.0901 | 35.7039 | Reduce | 0.29635 | 50.4987 | 14.9653 | H2 | 4 | Worsening | 0.6 | 113 | 128 | 153 | 129.6667 | 0.3 | 11 | 57 | 74 | 52.1667 | 27.9517 | 41.8237 | 0 | 16.771
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK308 | Project_024_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System robustness and resilience | Person_774 | 2017-04-06 | 2018-06-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.1 | 2.5966 | 0.25966 | H3 | 3 | Stable | 0.5 | 115 | 127 | 141 | 127.3333 | 0.2 | 25 | 53 | 72 | 51.5 | 58.3333 | 66.6667 | 1 | 37
2017-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-63 | Project_022_RISK-63 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Levy | Person_703 | 2012-04-19 | 2017-08-20 01:00 | 0.8 | 3.5298 | 2.8239 | Exploit | 0.8 | 3.5298 | 2.8239 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-62 | Project_022_RISK-62 | Threat | Project Contingency | Open | H3 | 3 | 8. Operations & Maintenance | Additional Costs from Integration Cost Centre | Person_703 | 2017-03-23 | 2017-05-14 | 0.5 | 7.1754 | 3.5877 | Avoid | 0.292 | 3.5877 | 1.0476 | H3 | 3 | Worsening | [10 empty] | 50 | 41.6 | 0 | 30
2017-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2017-06-21 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.35 | 2.8688 | 1.0041 | H2 | 4 | Stable | 0.5 | 103 | 140 | 158 | 136.8333 | 0.3 | 17 | 42 | 64 | 41.5 | 22.0253 | 56.25 | 0 | 13.2152
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 01:00 | 2018-05-22 | 0.1 | 2.3975 | 2.3975 | Accept | 0.1 | 0 | 0 | H2 | 4 | Stable | 0.9 | 83 | 128 | 143 | 123 | 0.9 | 83 | 128 | 143 | 123 | 100 | 0 | 0 | 60
2017-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2017-08-20 01:00 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 0.65554 | 0.52443 | H2 | 4 | Stable | [10 empty] | 80.45 | 0 | 0 | 48.27
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_567 | 2015-08-22 01:00 | 2018-08-21 | 0.45 | 2.2586 | 0.90343 | Accept | 0.45 | 2.2586 | 0.90343 | H3 | 3 | Worsening | 0.7 | 101 | 137 | 149 | 133 | 0.7 | 101 | 137 | 149 | 133 | 0 | 0 | 1 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2018-05-21 | 0.2 | 2.9272 | 1.4636 | Accept | 0.2 | 2.9272 | 1.4636 | H3 | 3 | Improving | 0.8 | 102 | 134 | 151 | 131.5 | 0.8 | 102 | 134 | 151 | 131.5 | 0 | 0 | 1 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_567 | 2018-05-22 | 2018-08-21 | 0.25 | 4.4984 | 2.2492 | Accept | 0.25 | 4.4984 | 2.2492 | H3 | 3 | Stable | 0.6 | 106 | 126 | 148 | 126.3333 | 0.6 | 106 | 126 | 148 | 126.3333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2018-04-22 | 0.3 | 1.6962 | 0.33923 | Accept | 0.4 | 1.6962 | 0.33923 | H3 | 3 | Stable | 0.6 | 104 | 127 | 157 | 128.1667 | 0.6 | 104 | 127 | 157 | 128.1667 | 0 | -33.3333 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Lack of Spares Availability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 0.3 | 18.9062 | 9.4531 | Accept | 0.3 | 18.9062 | 9.4531 | H3 | 3 | Stable | 0.7 | 81 | 126 | 143 | 121.3333 | 0.7 | 81 | 126 | 143 | 121.3333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2017-11-19 01:00 | 0.05 | 3.7207 | 0.93016 | Accept | 0.05 | 3.7207 | 0.93016 | H3 | 3 | Improving | 0.9 | 108 | 123 | 158 | 126.3333 | 0.9 | 108 | 123 | 158 | 126.3333 | 0 | 0 | 1 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) at the System level on product platform - performed by 3rd parties | Person_102 | 2015-01-22 | 2020-10-21 | 0.4 | 0 | 0 | Transfer | 0.41 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -2.5 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Sub-system / product system accreditation hindered by Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 | 2020-07-20 | 0.1 | 0.25667 | 0.025667 | Transfer | 0.1 | 0.25667 | 0.025667 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 1.4673 | 0.58692 | Reduce | 0.4 | 1.4673 | 0.58692 | H2 | 4 | Improving | 0.5 | 81 | 127 | 143 | 122 | 0.2 | 28 | 52 | 71 | 51.1667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2018-03-21 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 | 2018-01-19 | 0.3 | 0.89835 | 0.26951 | Transfer | 0.3 | 0.89835 | 0.26951 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 0.35 | 0.85557 | 0.29945 | Reduce | 0.35 | 1.9208 | 0.67227 | H2 | 4 | Stable | 0.8 | 120 | 127 | 143 | 128.5 | 0.1 | 25 | 54 | 78 | 53.1667 | -124.5001 | 0 | 0 | -74.7001
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 0.77001 | 0.30801 | Reduce | 0.3 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.7 | 100 | 123 | 151 | 123.8333 | 0.1 | 25 | 40 | 71 | 42.6667 | 0 | 25 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2018-02-20 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.7 | 108 | 124 | 155 | 126.5 | 0.3 | 10 | 45 | 79 | 44.8333 | 0 | 28.5714 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 0.2 | 0.94968 | 0.28491 | Accept | 0.2 | 0.94968 | 0.18994 | H2 | 4 | Stable | 0.8 | 82 | 122 | 141 | 118.5 | 0.8 | 82 | 122 | 141 | 118.5 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2018-03-22 | 2019-07-21 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.5 | 119 | 125 | 155 | 129 | 0.3 | 33 | 45 | 71 | 47.3333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 | 2018-03-16 | 0.1 | 6.4168 | 0.64168 | Transfer | 0.1 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sub-system FPGA | Person_332 | 2017-01-21 | 2018-02-20 | 0.4 | 1.5914 | 0.63655 | Reduce | 0.4 | 1.5914 | 0.63655 | H2 | 4 | Stable | 0.5 | 111 | 128 | 159 | 130.3333 | 0.3 | 34 | 53 | 74 | 53.3333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort for System HW/SW- System upgrade | Person_199 | 2017-05-23 | 2019-10-21 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.3 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.6 | 100 | 126 | 150 | 125.6667 | 0.1 | 27 | 55 | 65 | 52 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs | Person_372 | 2018-04-22 | 2018-08-22 | 0.5 | 6.6521 | 3.326 | Reduce | 0.5 | 6.6521 | 3.326 | H2 | 4 | Stable | 0.7 | 104 | 139 | 157 | 136.1667 | 0.3 | 34 | 46 | 69 | 47.8333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.5 | 3.5934 | 1.7967 | H2 | 4 | Stable | 0.9 | 83 | 122 | 152 | 120.5 | 0.2 | 14 | 58 | 63 | 51.5 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | HW - additional unplanned design effort | Person_332 | 2016-05-23 | 2018-02-20 | 0.4 | 3.3367 | 1.3347 | Reduce | 0.4 | 3.3367 | 1.3347 | H2 | 4 | Stable | 0.5 | 91 | 126 | 159 | 125.6667 | 0.2 | 12 | 45 | 65 | 42.8333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 0.25 | 2.5667 | 0.77001 | Accept | 0.25 | 2.5667 | 0.77001 | H3 | 3 | Stable | 0.9 | 94 | 135 | 155 | 131.5 | 0.9 | 94 | 135 | 155 | 131.5 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design [in addition to costed effort] | Person_332 | 2017-05-28 | 2018-08-18 | 0.2 | 2.6951 | 0.53901 | Reduce | 0.2 | 2.6951 | 0.53901 | H3 | 3 | Improving | 0.5 | 88 | 136 | 159 | 131.8333 | 0.1 | 27 | 50 | 65 | 48.6667 | 0 | 0 | 1 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Minimum Order Quantities | Person_372 | 2017-11-20 | 2018-05-15 | 0.2 | 1.925 | 0.38501 | -- | 0.2 | 1.925 | 0.38501 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_372 | 2018-04-22 | 2018-08-22 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Worsening | 0.5 | 115 | 138 | 146 | 135.5 | 0.1 | 31 | 40 | 78 | 44.8333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_585 | 2017-10-21 | 2019-07-21 | 0.333 | 11.5502 | 3.8462 | Reduce | 0.333 | 11.5502 | 3.8462 | H2 | 4 | Stable | 0.6 | 112 | 134 | 155 | 133.8333 | 0.4 | 29 | 53 | 71 | 52 | 0 | 0 | 0 | 0
2017-09-20 | ORG_002 | BA_005 | Portfolio_011 | Project_047 | RISK006 | Project_047_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer find issues with delivered parts | Person_454 | 2017-05-23 | 2017-08-18 23:00 | 0.8 | 1.2591 | 1.0073 | Reduce | 0.4 | 1.2591 | 0.50365 | H3 | 3 | Improving | 0.6 | 101 | 140 | 157 | 136.3333 | 0.2 | 38 | 45 | 74 | 48.6667 | 0 | 50 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | More issues during Qualification including additional PRs | Person_147 | 2017-07-26 | 2017-12-17 01:00 | 0.6 | 8.8959 | 4.448 | Accept | 0.6 | 8.8959 | 4.448 | H1 | 5 | Stable | 0.7 | 102 | 137 | 152 | 133.6667 | 0.7 | 102 | 137 | 152 | 133.6667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_002 | BA_005 | Portfolio_011 | Project_047 | RISK009 | Project_047_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Open PR's | Person_647 | 2017-04-22 | 2018-11-19 23:00 | 0.5 | 0.51323 | 0.25661 | Reduce | 0.3 | 0.51323 | 0.15397 | H2 | 4 | Improving | 0.8 | 104 | 135 | 159 | 133.8333 | 0.3 | 30 | 56 | 66 | 53.3333 | 0 | 40 | 0 | 0
2017-09-20 | ORG_002 | BA_005 | Portfolio_011 | Project_047 | RISK078 | Project_047_RISK078 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer find issues with delivered parts. | Person_236 | 2017-04-22 | 2018-10-19 23:00 | 0.9 | 20.2553 | 18.2298 | Reduce | 0.35 | 10.1277 | 3.5447 | H3 | 3 | Improving | 0.5 | 91 | 124 | 153 | 123.3333 | 0.3 | 14 | 59 | 60 | 51.6667 | 50 | 61.1111 | 0 | 30
2017-09-20 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK003 | Project_044_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Mono vs stereo Component | Person_358 | 2016-03-23 | 2018-10-22 01:00 | 0.7 | 14.4876 | 10.1413 | Reduce | 0.5 | 14.4876 | 7.2438 | H2 | 4 | Improving | 0.9 | 105 | 138 | 149 | 134.3333 | 0.4 | 19 | 50 | 76 | 49.1667 | 0 | 28.5714 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Labour/Material Risk | Person_662 | 2015-05-24 | 2019-05-23 | 0.5 | 11.5901 | 3.477 | Accept | 0.5 | 11.5901 | 5.795 | H2 | 4 | Stable | 0.5 | 86 | 133 | 142 | 126.6667 | 0.5 | 86 | 133 | 142 | 126.6667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_009 | Project_045 | RISK001 | Project_045_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour/T&S Overspend | Person_662 | 2017-01-21 01:00 | 2020-05-22 | 0.5 | 5.795 | 2.8975 | Accept | 0.5 | 5.795 | 2.8975 | H2 | 4 | Stable | 0.8 | 98 | 125 | 150 | 124.6667 | 0.8 | 98 | 125 | 150 | 124.6667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2017-02-20 01:00 | 2018-05-22 | 0.1 | 1.5695 | 0.47085 | Accept | 0.1 | 1.4488 | 0.43463 | H3 | 3 | Stable | 0.8 | 101 | 128 | 147 | 126.6667 | 0.8 | 101 | 128 | 147 | 126.6667 | 7.6924 | 0 | 1 | 4.6155
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unforseen and substantial increase in Repairs workload during new build production period. | Person_515 | 2017-10-23 01:00 | 2017-11-19 01:00 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.03 | 1.5434 | 0.046303 | H3 | 3 | Stable | 0.7 | 86 | 129 | 149 | 125.1667 | 0.2 | 1 | 54 | 62 | 46.5 | 0 | 90 | 1 | 2.7
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK007 | Project_041_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Advanced production of products using a Qual. standard component rather than a Prod. standard | Person_547 | 2017-10-21 01:00 | 2019-05-23 | 0.49 | 1.2862 | 0.63024 | Reduce | 0.2 | 1.2862 | 0.25724 | H3 | 3 | Stable | 0.9 | 87 | 132 | 148 | 127.1667 | 0.4 | 5 | 56 | 70 | 49.8333 | 0 | 59.1837 | 1 | 1.7755
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_693 | 2017-05-23 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.9 | 110 | 122 | 154 | 125.3333 | 0.4 | 26 | 50 | 61 | 47.8333 | 0 | 50 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2017-04-22 | 2018-05-22 | 0.75 | 10.7184 | 8.0388 | Reduce | 0.25 | 5.3592 | 1.3398 | H2 | 4 | Worsening | 0.8 | 116 | 140 | 158 | 139 | 0.4 | 21 | 48 | 67 | 46.6667 | 50 | 66.6667 | 0 | 30
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK003 | Project_024_RISK003 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance | Person_288 | 2017-12-21 01:00 | 2018-08-21 | 0.31667 | 1.9722 | 0.98609 | Accept | 0.007456 | 1.9722 | 0.98609 | H2 | 4 | Stable | 0.8 | 109 | 137 | 149 | 134.3333 | 0.8 | 109 | 137 | 149 | 134.3333 | 0 | 97.6455 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Management Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 0.3 | 2.5081 | 1.2541 | Accept | 0.3 | 2.5081 | 1.2541 | H1 | 5 | Improving | 0.6 | 93 | 129 | 148 | 126.1667 | 0.6 | 93 | 129 | 148 | 126.1667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2017-05-23 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.05 | 0.68598 | 0.034299 | H3 | 3 | Improving | 0.7 | 107 | 138 | 157 | 136 | 0.4 | 24 | 47 | 79 | 48.5 | 0 | 80 | 1 | 2.4
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK300(020) | Project_024_RISK300(020) | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Travel and onsite support | Person_119 | 2017-01-20 01:00 | 2018-04-21 | 0.25 | 0.45017 | 0.2701 | Accept | 0.25 | 0.45017 | 0.13505 | H3 | 3 | Stable | 0.9 | 86 | 138 | 158 | 132.6667 | 0.9 | 86 | 138 | 158 | 132.6667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK304(026) | Project_024_RISK304(026) | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | complex integration | Person_119 | 2016-10-20 01:00 | 2018-01-20 01:00 | 0.4 | 3.7514 | 0.37514 | Accept | 0.4 | 3.7514 | 0.37514 | H1 | 5 | Worsening | 0.9 | 106 | 140 | 152 | 136.3333 | 0.9 | 106 | 140 | 152 | 136.3333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2017-05-23 | 2019-04-23 | 0.1 | 21.8655 | 2.1865 | Reduce | 0.01 | 21.8655 | 0.21865 | H2 | 4 | Improving | 0.9 | 102 | 123 | 159 | 125.5 | 0.2 | 35 | 55 | 78 | 55.5 | 0 | 90 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2017-05-23 | 2019-08-20 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Stable | 0.6 | 96 | 138 | 152 | 133.3333 | 0.4 | 13 | 51 | 68 | 47.5 | 0 | 60 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Unidentified CRs and concessions | Person_693 | 2017-04-22 | 2019-07-22 | 0.5 | 1.2005 | 0.60023 | Reduce | 0.15 | 0.51019 | 0.076529 | H3 | 3 | Stable | 0.9 | 82 | 132 | 156 | 127.6667 | 0.4 | 5 | 52 | 75 | 48 | 57.5001 | 70 | 1 | 36.6001
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_238 | 2017-04-22 | 2018-05-22 | 0.25 | 3.3227 | 0.83067 | Reduce | 0.05 | 3.3227 | 0.16613 | H3 | 3 | Stable | 0.5 | 88 | 140 | 152 | 133.3333 | 0.3 | 4 | 52 | 65 | 46.1667 | 0 | 80 | 1 | 2.4
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_693 | 2017-05-23 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.1 | 0.77172 | 0.077172 | H3 | 3 | Stable | 0.6 | 111 | 140 | 159 | 138.3333 | 0.2 | 5 | 40 | 79 | 40.6667 | 0 | 60 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK303(025) | Project_024_RISK303(025) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in contract value from our supplier | Person_119 | 2016-10-20 01:00 | 2019-05-23 | 0.25 | 1.7492 | 0.17492 | Accept | 0.25 | 1.7492 | 0.17492 | H2 | 4 | Stable | 0.9 | 92 | 122 | 158 | 123 | 0.9 | 92 | 122 | 158 | 123 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_693 | 2017-05-23 | 2017-12-01 01:00 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.08 | 6.431 | 0.51448 | H3 | 3 | Improving | 0.7 | 80 | 136 | 148 | 128.6667 | 0.4 | 22 | 55 | 65 | 51.1667 | -47.0588 | 46.6667 | 1 | -26.8353
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Reduce touch labour if Production readiness programme successful | Person_238 | 2017-05-23 | 2017-10-21 01:00 | 0.3 | 1.5606 | 0.46818 | Exploit | 0.5 | 1.5606 | 0.7803 | H2 | 4 | Stable | [10 empty] | 0 | -66.6667 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK305(027) | Project_024_RISK305(027) | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Customer Furnished Equipment not available on time | Person_119 | 2016-11-19 01:00 | 2019-05-23 | 0.3 | 0.11976 | 0.0059882 | Accept | 0.3 | 0.11976 | 0.0059882 | H1 | 5 | Stable | 0.5 | 93 | 139 | 144 | 132.1667 | 0.5 | 93 | 139 | 144 | 132.1667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK296(013) | Project_024_RISK296(013) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Qualification/Certification Requirements flowdown | Person_119 | 2016-10-20 01:00 | 2017-12-19 01:00 | 0.25 | 0.95811 | 0.23953 | Accept | 0.25 | 0.95811 | 0.23953 | H2 | 4 | Worsening | 0.9 | 105 | 130 | 152 | 129.5 | 0.9 | 105 | 130 | 152 | 129.5 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before part b finished | Person_119 | 2016-10-20 01:00 | 2018-04-21 | 0.35 | 0.59882 | 0.14971 | Accept | 0.35 | 0.59882 | 0.14971 | H2 | 4 | Worsening | 0.5 | 98 | 138 | 148 | 133 | 0.5 | 98 | 138 | 148 | 133 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK298(016) | Project_024_RISK298(016) | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Environmental testing required | Person_119 | 2016-10-20 01:00 | 2017-12-20 01:00 | 0.2 | 0.78901 | 0.3945 | Accept | 0.2 | 0.78901 | 0.3945 | H2 | 4 | Stable | 0.8 | 91 | 130 | 151 | 127 | 0.8 | 91 | 130 | 151 | 127 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK299(018) | Project_024_RISK299(018) | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Additional support hours | Person_119 | 2017-01-20 01:00 | 2018-04-21 | 0.35 | 2.0712 | 2.0712 | Accept | 0.35 | 2.0694 | 2.0694 | H3 | 3 | Stable | 0.9 | 108 | 136 | 151 | 133.8333 | 0.9 | 108 | 136 | 151 | 133.8333 | 0.084402 | 0 | 1 | 0.050641
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 09:00 | 2019-08-20 09:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 09:00 | 2019-08-20 09:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 09:00 | 2019-08-20 09:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 09:00 | 2019-08-20 09:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 09:00 | 2019-08-20 09:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-022 | Project_021_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | trials delay due to lack of supporting resources | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 118 | 130 | 151 | 131.5 | 0.1 | 32 | 59 | 74 | 57 |  | 66.6667 | 1
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-021 | Project_021_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | trials delay due to lack of equipment | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.5 | 119 | 139 | 150 | 137.5 | 0.3 | 34 | 58 | 69 | 55.8333 |  | 66.6667 | 1
2017-09-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK016 | Project_048_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.3 | 0.22605 | 0.067816 | -- | 0.2 | 0.22605 | 0.045211 | H3 | 3 | Stable | [10 empty] | 0 | 33.3333 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Non-Recurring Engineering higher than expected | Person_510 | 2016-06-01 | 2016-08-20 | 0.5 | 13.3382 | 6.6691 | Reduce | 0.5 | 13.3382 | 6.6691 | H2 | 4 | Improving | 0.9 | 93 | 135 | 157 | 131.6667 | 0.4 | 7 | 45 | 67 | 42.3333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.8 | 90 | 135 | 148 | 129.6667 | 0.1 | 4 | 57 | 74 | 51 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-20 22:00 | 2016-08-20 22:00 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.6 | 88 | 124 | 160 | 124 | 0.4 | 21 | 50 | 67 | 48 | 0 | 16.6667 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 0.5 | 9.2728 | 4.6364 | Reduce | 0.15 | 9.2728 | 1.3909 | H2 | 4 | Stable | 0.7 | 85 | 131 | 160 | 128.1667 | 0.1 | 39 | 58 | 61 | 55.3333 | 0 | 70 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R008 | Project_016_Risk--R008 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Additional Travel & Subsistence | Person_574 | 2016-01-13 01:00 | 2019-05-23 | 0.4 | 8.9019 | 3.5608 | Reduce | 0.25 | 8.9019 | 2.2255 | H3 | 3 | Stable | 0.5 | 109 | 128 | 151 | 128.6667 | 0.2 | 37 | 59 | 65 | 56.3333 | 0 | 37.5 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 0.3 | 8.7814 | 2.6344 | Reduce | 0.15 | 8.7832 | 1.3175 | H3 | 3 | Stable | 0.9 | 105 | 137 | 148 | 133.5 | 0.4 | 13 | 42 | 77 | 43 | -0.021119 | 50 | 1 | 1.4873
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R009 | Project_016_Risk--R009 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer maybe difficult to work with | Person_697 | 2016-04-02 | 2019-08-01 | 0.6 | 23.9549 | 14.3729 | Reduce | 0.43864 | 23.8312 | 10.4533 | H2 | 4 | Stable | 0.6 | 101 | 133 | 147 | 130 | 0.4 | 9 | 44 | 65 | 41.6667 | 0.51612 | 26.8938 | 0 | 0.30967
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Delay of processing | Person_306 | 2016-04-02 | 2017-03-21 01:00 | 0.15 | 26.3497 | 3.9525 | Reduce | 0.15 | 13.1767 | 1.9765 | H3 | 3 | Stable | 0.8 | 107 | 124 | 156 | 126.5 | 0.3 | 19 | 41 | 74 | 42.8333 | 49.993 | 0 | 1 | 29.9958
2017-09-20 | ORG_002 | BA_004 | Portfolio_010 | Project_046 | PRO004 | Project_046_PRO004 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | High Material Atrition Level | Person_025 | 2016-06-14 | 2017-11-20 01:00 | 0.5 | 1.618 | 0.80901 | Reduce | 0.5 | 1.618 | 0.80901 | H1 | 5 | Stable | 0.9 | 91 | 132 | 141 | 126.6667 | 0.4 | 24 | 48 | 76 | 48.6667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-002 | Project_052_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Schedule slippage due to infeed of critical hardware | Person_376 | 2017-08-19 01:00 | 2018-02-19 01:00 | 0.5 | 3.2555 | 1.6277 | Reduce | 0.5 | 3.2555 | 1.6277 | H3 | 3 | Stable | 0.6 | 90 | 123 | 147 | 121.5 | 0.3 | 23 | 48 | 68 | 47.1667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-016 | Project_052_Risk-016 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Environmental conditions | Person_651 | 2017-08-19 01:00 | 2018-02-19 01:00 | 0.2 | 13.8182 | 2.7636 | Transfer | 0.2 | 13.8182 | 2.7636 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-010 | Project_052_Risk-010 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Potential update of software / hardware required during the 3 year support period (RESOURCE) | Person_376 | 2017-08-19 01:00 | 2018-02-19 01:00 | 0.3 | 3.1214 | 0.93642 | Transfer | 0.3 | 3.1184 | 0.93551 | H3 | 3 | Stable | [10 empty] | 0.09816 | 0 | 0 | 0.058896
2017-09-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-012 | Project_052_Risk-012 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Issues from Supplier affect product | Person_651 | 2017-08-19 01:00 | 2020-08-19 01:00 | 0.3 | 5.1992 | 1.5598 | -- | 0.3 | 5.1972 | 1.5591 | H3 | 3 | Stable | [10 empty] | 0.038674 | 0 | 0 | 0.023204
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 | 2020-09-19 | 0.2 | 7.1379 | 2.1414 | Accept | 0.2 | 7.1379 | 2.1414 | H3 | 3 | Stable | 0.6 | 102 | 130 | 158 | 130 | 0.6 | 102 | 130 | 158 | 130 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2019-07-21 | 0.3 | 8.4929 | 2.5479 | Accept | 0.2 | 8.4929 | 2.5479 | H3 | 3 | Stable | 0.5 | 118 | 127 | 155 | 130.1667 | 0.5 | 118 | 127 | 155 | 130.1667 | 0 | 33.3333 | 1 | 1
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 | 2019-08-21 | 0.03 | 10.2724 | 2.0545 | Accept | 0.1 | 10.2724 | 2.0545 | H3 | 3 | Stable | 0.5 | 85 | 122 | 156 | 121.5 | 0.5 | 85 | 122 | 156 | 121.5 | 0 | -233.3333 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 | 2019-10-21 | 0.25 | 15.8357 | 3.1671 | Accept | 0.25 | 15.8357 | 3.1671 | H2 | 4 | Stable | 0.5 | 88 | 134 | 153 | 129.5 | 0.5 | 88 | 134 | 153 | 129.5 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 | 0.3 | 8.5887 | 2.5766 | Accept | 0.3 | 8.5887 | 2.5766 | H2 | 4 | Stable | 0.5 | 86 | 134 | 149 | 128.5 | 0.5 | 86 | 134 | 149 | 128.5 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK008 | Project_044_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Skills | Person_505 | 2017-10-21 01:00 | 2018-10-22 01:00 | 0.3 | 1.0661 | 0.21322 | Accept | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 94 | 127 | 154 | 126 | 0.8 | 94 | 127 | 154 | 126 | 100 | 0 | 0 | 60
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Risk of not being able to perform Tests | Person_238 | 2017-12-21 01:00 | 2019-01-21 01:00 | 0.5 | 5.126 | 2.563 | Accept | 0.5 | 5.126 | 2.563 | H2 | 4 | Stable | 0.9 | 96 | 139 | 148 | 133.3333 | 0.9 | 96 | 139 | 148 | 133.3333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_238 | 2017-05-23 | 2019-01-21 01:00 | 0.5 | 12.815 | 2.563 | Accept | 0.5 | 12.815 | 2.563 | H2 | 4 | Stable | 0.7 | 106 | 126 | 152 | 127 | 0.7 | 106 | 126 | 152 | 127 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.8 | 109 | 123 | 156 | 126.1667 | 0.4 | 22 | 45 | 65 | 44.5 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-20 22:00 | 2016-08-20 22:00 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.5 | 82 | 137 | 159 | 131.5 | 0.4 | 23 | 53 | 68 | 50.5 | 0 | 16.6667 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_693 | 2017-04-22 | 2017-09-19 01:00 | 0.6 | 7.689 | 2.6911 | Accept | 0.3 | 7.689 | 2.6911 | H3 | 3 | Stable | 0.6 | 119 | 125 | 155 | 129 | 0.6 | 119 | 125 | 155 | 129 | 0 | 50 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_547 | 2017-05-23 | 2018-05-22 | 0.1 | 5.4336 | 1.3584 | Accept | 0.1 | 5.4336 | 1.3584 | H3 | 3 | Stable | 0.5 | 106 | 125 | 152 | 126.3333 | 0.5 | 106 | 125 | 152 | 126.3333 | 0 | 0 | 1 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Non-Recurring Engineering higher than expected | Person_510 | 2016-06-01 | 2016-08-20 01:00 | 0.5 | 13.3382 | 6.6691 | Reduce | 0.5 | 13.3382 | 6.6691 | H2 | 4 | Improving | 0.5 | 107 | 133 | 144 | 130.5 | 0.3 | 12 | 57 | 68 | 51.3333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production, Procurement or Engineering | Person_725 | 2018-01-21 01:00 | 2019-05-23 | 0.1 | 4.8729 | 3.8983 | Accept | 0.1 | 4.8729 | 3.8983 | H3 | 3 | Worsening | 0.8 | 119 | 122 | 144 | 125.1667 | 0.8 | 119 | 122 | 144 | 125.1667 | 0 | 0 | 1 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-026 | Project_043_Risk-026 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Equipment Delivery & Certification Risk | Person_693 | 2017-04-19 | 2017-10-19 01:00 | 0.25 | 7.3848 | 3.6924 | Accept | 0.25 | 7.3848 | 3.6924 | H2 | 4 | Improving | 0.8 | 111 | 121 | 150 | 124.1667 | 0.8 | 111 | 121 | 150 | 124.1667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_002 | Portfolio_009 | Project_051 | RISK001 | Project_051_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Generic Labour or Material Overspend | Person_577 | 2012-05-23 | 2021-05-22 | 0.5 | 3.1344 | 1.5672 | Accept | 0.5 | 3.1344 | 1.5672 | H3 | 3 | Stable | 0.8 | 113 | 129 | 152 | 130.1667 | 0.8 | 113 | 129 | 152 | 130.1667 | 0 | 0 | 0 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK004 | Project_048_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 1.0253 | 0.20506 | Reduce | 0.15 | 1.0253 | 0.1538 | H3 | 3 | Stable | 0.8 | 117 | 127 | 146 | 128.5 | 0.3 | 15 | 57 | 62 | 50.8333 | 0 | 25 | 0 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK003 | Project_048_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Lead Times | Person_261 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 1.1285 | 0.22571 | Avoid | 0.2 | 1.1285 | 0.22571 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK014 | Project_048_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2020-05-22 | 0.1 | 2.5117 | 0.25117 | Reduce | 0.05 | 2.5117 | 0.12558 | H3 | 3 | Stable | 0.9 | 99 | 132 | 148 | 129.1667 | 0.4 | 11 | 56 | 61 | 49.3333 | 0 | 50 | 0 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK006 | Project_048_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Customer | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0.20644 | 0.041288 | Reduce | 0.15 | 0.20644 | 0.030966 | H3 | 3 | Stable | 0.6 | 82 | 124 | 148 | 121 | 0.3 | 19 | 57 | 75 | 53.6667 | 0 | 25 | 0 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK005 | Project_048_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 0.43506 | 0.26104 | Avoid | 0.5 | 0.43506 | 0.21753 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK011 | Project_048_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Line Qualification | Person_270 | 2017-02-20 01:00 | 2019-05-23 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.5 | 101 | 136 | 153 | 133 | 0.4 | 34 | 43 | 75 | 46.8333 |  | 0 | 1
2017-10-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK010 | Project_048_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Material | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.5 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Worsening | [11 empty] | 20 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK002 | Project_048_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2020-05-22 | 0.15 | 0.30966 | 0.046449 | Avoid | 0.15 | 0.30966 | 0.046449 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK001 | Project_048_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Procurement | Person_261 | 2017-02-20 01:00 | 2019-05-23 | 0.2 | 5.5679 | 1.1136 | Reduce | 0.1 | 5.5679 | 0.55679 | H3 | 3 | Stable | 0.6 | 103 | 126 | 153 | 126.6667 | 0.1 | 23 | 53 | 73 | 51.3333 | 0 | 50 | 1 | 1.5
2017-10-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK012 | Project_048_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Customer requires additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-10-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK008 | Project_048_RISK008 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Oracle | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0.20644 | 0.041288 | Avoid | 0.1 | 0.20644 | 0.020644 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK007 | Project_048_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Staff Availability | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0.067093 | 0.013419 | Avoid | 0.1 | 0.067093 | 0.0067093 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2017-10-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK009 | Project_048_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Supplier Performance | Person_261 | 2017-02-20 01:00 | 2020-05-22 | 0.3 | 0.72254 | 0.21676 | Reduce | 0.3 | 0.72254 | 0.21676 | H2 | 4 | Stable | 0.5 | 108 | 122 | 153 | 124.8333 | 0.3 | 10 | 47 | 62 | 43.3333 | 0 | 0 | 0 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK017 | Project_048_RISK017 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Increased build rate | Person_683 | 2017-11-12 01:00 | 2019-08-21 01:00 | 0.5 | 7.7433 | 3.8716 | -- | 0.5 | 7.7433 | 3.8716 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK016 | Project_048_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.2 | 0.22605 | 0.045211 | -- | 0.1 | 0.22605 | 0.022605 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK018 | Project_048_RISK018 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Line Closure | Person_683 | 2019-08-21 01:00 | 2019-11-20 01:00 | 0.5 | 0.68298 | 0.34149 | -- | 0.5 | 1.5483 | 0.77415 | H2 | 4 | Improving | [10 empty] | -126.7001 | 0 | 0 | -76.0201
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-20 22:00 | 2019-08-20 | 0.5 | 1.8788 | 0.46971 | Accept | 0.5 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.6 | 118 | 125 | 151 | 128.1667 | 0.6 | 118 | 125 | 151 | 128.1667 | 20 | 0 | 0 | 12
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.2 | 1.8788 | 0.46971 | Accept | 0.2 | 1.5031 | 0.22546 | H3 | 3 | Stable | 0.8 | 113 | 131 | 141 | 129.6667 | 0.8 | 113 | 131 | 141 | 129.6667 | 20 | 0 | 0 | 12
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 4.6971 | 0.93941 | Accept | 0.35 | 3.7576 | 0.67638 | H3 | 3 | Stable | 0.6 | 81 | 125 | 153 | 122.3333 | 0.6 | 81 | 125 | 153 | 122.3333 | 20 | 0 | 0 | 12
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK044 | Project_042_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2018-02-20 01:00 | 2018-12-21 01:00 | 0.32 | 6.5759 | 2.1043 | -- | 0.32 | 6.5759 | 2.1043 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.25 | 1.8788 | 0.18788 | Accept | 0.25 | 1.5031 | 0.12024 | H3 | 3 | Stable | 0.8 | 111 | 127 | 156 | 129.1667 | 0.8 | 111 | 127 | 156 | 129.1667 | 20 | 0 | 0 | 12
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 0.5 | 9.3941 | 3.1001 | Accept | 0.5 | 7.5153 | 2.2546 | H2 | 4 | Improving | 0.6 | 113 | 127 | 157 | 129.6667 | 0.6 | 113 | 127 | 157 | 129.6667 | 20 | 0 | 0 | 12
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 0.3 | 0.56365 | 0.11273 | Accept | 0.3 | 0.28182 | 0.028182 | H2 | 4 | Stable | 0.6 | 98 | 127 | 151 | 126.1667 | 0.6 | 98 | 127 | 151 | 126.1667 | 50 | 0 | 0 | 30
2017-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R013 | Project_016_Risk--R013 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Resource Availability (Threat) | Person_697 | 2016-04-02 | 2019-08-01 | 0.2 | 0.81199 | 0.081199 | Accept | 0.2 | 0.81199 | 0.0406 | H2 | 4 | Worsening | 0.7 | 104 | 134 | 151 | 131.8333 | 0.7 | 104 | 134 | 151 | 131.8333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-013 | Project_052_Risk-013 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Additional material and effort required to support the delta equipment | Person_376 | 2017-08-19 01:00 | 2018-02-19 01:00 | 0.3 | 1.2198 | 0.60991 | Accept | 0.3 | 1.2198 | 0.60991 | H3 | 3 | Stable | 0.5 | 96 | 131 | 144 | 127.3333 | 0.5 | 96 | 131 | 144 | 127.3333 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK045 | Project_042_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2019-01-22 01:00 | 2019-05-23 | 0.25 | 3.908 | 0.97699 | -- | 0.25 | 3.908 | 0.97699 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 | 2017-08-20 | 0.1 | 53.0293 | 5.3029 | Reduce | 0.1 | 53.0293 | 5.3029 | H3 | 3 | Worsening | 0.5 | 109 | 131 | 146 | 129.8333 | 0.1 | 38 | 44 | 73 | 47.8333 | 0 | 0 | 0 | 0
2017-09-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-004 | Project_052_Risk-004 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Installation Risk for Phase 1a and 1b | Person_488 | 2017-08-19 01:00 | 2018-02-19 01:00 | 0.2 | 6.0991 | 0 | Accept | 0.2 | 6.0991 | 4.0864 | H3 | 3 | Stable | 0.6 | 94 | 134 | 157 | 131.1667 | 0.6 | 94 | 134 | 157 | 131.1667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-005 | Project_052_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Potential update of software / hardware required during the 3 year support period | Person_488 | 2017-08-19 01:00 | 2018-02-19 01:00 | 0.3 | 1.8788 | 0.46971 | Accept | 0.3 | 1.1273 | 0.11273 | H3 | 3 | Stable | 0.7 | 91 | 138 | 150 | 132.1667 | 0.7 | 91 | 138 | 150 | 132.1667 | 40 | 0 | 0 | 24
2017-09-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-020 | Project_052_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Material escalation - | Person_376 | 2017-08-19 01:00 | 2018-02-19 01:00 | 0.3 | 0.20788 | 0.068599 | Accept | 0.3 | 0.052336 | 0.0057569 | H3 | 3 | Stable | 0.7 | 113 | 134 | 151 | 133.3333 | 0.7 | 113 | 134 | 151 | 133.3333 | 74.8236 | 0 | 0 | 44.8942
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PEN Testing Security Features | Person_604 | 2015-04-11 | 2018-01-20 01:00 | 0.3 | 5.4553 | 1.6366 | Reduce | 0.2 | 5.252 | 1.0504 | H2 | 4 | Stable | 0.8 | 105 | 122 | 145 | 123 | 0.1 | 26 | 48 | 66 | 47.3333 | 3.7267 | 33.3333 | 0 | 2.236
2017-09-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-001 | Project_052_Risk-001 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Greater modification than expected for system uplift | Person_376 | 2017-08-19 01:00 | 2018-02-19 01:00 | 0.3 | 1.8788 | 0.37576 | Accept | 0.3 | 1.4091 | 0.21137 | H3 | 3 | Stable | 0.9 | 109 | 128 | 150 | 128.5 | 0.9 | 109 | 128 | 150 | 128.5 | 25 | 0 | 0 | 15
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 | 2017-08-20 | 0.1 | 7.7469 | 0.77469 | Reduce | 0.1 | 7.7469 | 0.77469 | H3 | 3 | Stable | 0.7 | 85 | 123 | 146 | 120.5 | 0.2 | 32 | 58 | 71 | 55.8333 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Platforms Cable and connectors | Person_499 | 2015-11-21 01:00 | 2019-04-10 | 0.45 | 0.41338 | 0.18602 | Reduce | 0.05 | 0.41338 | 0.020669 | H2 | 4 | Stable | 0.7 | 80 | 127 | 152 | 123.3333 | 0.3 | 18 | 53 | 74 | 50.6667 | 0 | 88.8889 | 0 | 0
2017-09-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-006 | Project_052_Risk-006 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Acceptance failures | Person_488 | 2017-08-19 01:00 | 2018-02-19 01:00 | 0.3 | 11.3437 | 0.56718 | Accept | 0.3 | 11.3437 | 0.56718 | H3 | 3 | Stable | 0.9 | 91 | 140 | 142 | 132.1667 | 0.9 | 91 | 140 | 142 | 132.1667 | 0 | 0 | 0 | 0
2017-09-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-018 | Project_052_Risk-018 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Support - spares availability | Person_156 | 2017-08-19 01:00 | 2018-02-19 01:00 | 0.2 | 3.7576 | 0.75153 | Accept | 0.2 | 2.8182 | 0.42274 | H3 | 3 | Stable | 0.5 | 92 | 129 | 157 | 127.5 | 0.5 | 92 | 129 | 157 | 127.5 | 25 | 0 | 0 | 15
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | FOC Acceptance | Person_499 | 2015-11-21 01:00 | 2018-02-18 01:00 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.3 | 8.471 | 2.5413 | H2 | 4 | Stable | 0.8 | 109 | 124 | 158 | 127.1667 | 0.1 | 25 | 56 | 64 | 52.1667 | -99.9999 | 14.2857 | 0 | -59.9999
2017-09-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-019 | Project_052_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Additional Design effort required | Person_488 | 2017-08-19 01:00 | 2018-02-19 01:00 | 0.2 | 2.2828 | 0.31959 | Accept | 0.2 | 2.217 | 0.24387 | H3 | 3 | Stable | 0.7 | 96 | 121 | 151 | 121.8333 | 0.7 | 96 | 121 | 151 | 121.8333 | 2.8807 | 0 | 0 | 1.7284
2017-09-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-009 | Project_052_Risk-009 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | System acceptance not costed in line with Customer expectations | Person_651 | 2017-08-19 01:00 | 2020-08-19 01:00 | 0.3 | 8.8098 | 3.0834 | Accept | 0.3 | 8.8098 | 1.762 | H3 | 3 | Stable | 0.7 | 85 | 121 | 144 | 118.8333 | 0.7 | 85 | 121 | 144 | 118.8333 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Furnished Equipmnet Condition | Person_496 | 2015-04-27 | 2019-04-10 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.9 | 120 | 126 | 146 | 128.3333 | 0.1 | 8 | 53 | 78 | 49.6667 |  | 62.5 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-20 22:00 | 2019-08-20 | 0.5 | 2.8182 | 0.28182 | Accept | 0.5 | 2.7619 | 0.22095 | H2 | 4 | Stable | 0.5 | 112 | 124 | 149 | 126.1667 | 0.5 | 112 | 124 | 149 | 126.1667 | 2 | 0 | 0 | 1.2
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.2 | 1.7281 | 1.3825 | Accept | 0.2 | 1.7281 | 1.3825 | H3 | 3 | Stable | 0.5 | 108 | 139 | 160 | 137.3333 | 0.5 | 108 | 139 | 160 | 137.3333 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 1.8788 | 0.37576 | Accept | 0.35 | 1.5031 | 0.22546 | H3 | 3 | Stable | 0.8 | 85 | 140 | 143 | 131.3333 | 0.8 | 85 | 140 | 143 | 131.3333 | 20 | 0 | 0 | 12
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.25 | 6.6751 | 6.0076 | Accept | 0.25 | 16.2643 | 8.1321 | H3 | 3 | Stable | 0.6 | 96 | 136 | 154 | 132.3333 | 0.6 | 96 | 136 | 154 | 132.3333 | -143.6548 | 0 | 0 | -86.1929
2017-10-21 | ORG_001 | BA_002 | Portfolio_009 | Project_051 | RISK001 | Project_051_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Generic Labour or Material Overspend | Person_577 | 2012-05-23 | 2021-05-22 | 0.5 | 1.8788 | 0.37576 | Accept | 0.5 | 1.5031 | 0.22546 | H3 | 3 | Stable | 0.7 | 98 | 126 | 150 | 125.3333 | 0.7 | 98 | 126 | 150 | 125.3333 | 20 | 0 | 0 | 12
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 5.4729 | 4.3783 | Accept | 0.5 | 4.6191 | 1.3857 | H2 | 4 | Stable | 0.5 | 112 | 128 | 145 | 128.1667 | 0.5 | 112 | 128 | 145 | 128.1667 | 15.6018 | 0 | 0 | 9.3611
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 | 2020-08-20 | 0.5 | 1.0334 | 0.20667 | Accept | 0.5 | 0.80789 | 0.12118 | H2 | 4 | Stable | 0.6 | 94 | 135 | 160 | 132.3333 | 0.6 | 94 | 135 | 160 | 132.3333 | 21.8182 | 0 | 0 | 13.0909
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-080 | Project_008_Risk-080 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Recovery of Costs | Person_567 | 2016-08-21 01:00 | 2017-12-20 01:00 | 0.5 | 23.6737 | 11.8369 | -- | 0.5 | 23.6737 | 11.8369 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK026 | Project_042_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st Jan to 31st March | Person_455 | 2020-05-23 | 2020-08-20 01:00 | 0.25 | 49.7149 | 22.3717 | Accept | 0.15 | 49.7149 | 22.3717 | H2 | 4 | Stable | 0.5 | 108 | 139 | 144 | 134.6667 | 0.5 | 108 | 139 | 144 | 134.6667 | 0 | 40 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK047 | Project_042_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables | Person_455 | 2020-11-20 01:00 | 2021-05-22 | 0.2 | 1.8788 | 0.18788 | Accept | 0.1 | 1.5031 | 0.12024 | H2 | 4 | Stable | 0.5 | 83 | 128 | 160 | 125.8333 | 0.5 | 83 | 128 | 160 | 125.8333 | 20 | 50 | 0 | 12
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK028 | Project_042_RISK028 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st July to 30th September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 0.25 | 1.8788 | 0.18788 | Accept | 0.15 | 1.5031 | 0.12024 | H2 | 4 | Stable | 0.5 | 88 | 122 | 142 | 119.6667 | 0.5 | 88 | 122 | 142 | 119.6667 | 20 | 40 | 0 | 12
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Survey costs | Person_618 | 2016-04-22 | 2017-12-20 01:00 | 0.2 | 13.2573 | 2.6515 | Avoid | 0.2 | 13.2573 | 2.6515 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK027 | Project_042_RISK027 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st April to 30th June | Person_455 | 2020-08-21 01:00 | 2020-09-19 01:00 | 0.25 | 1.8788 | 0.18788 | Accept | 0.15 | 0.79775 | 0.039887 | H2 | 4 | Stable | 0.7 | 93 | 136 | 149 | 131 | 0.7 | 93 | 136 | 149 | 131 | 57.54 | 40 | 0 | 34.524
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-079 | Project_008_Risk-079 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Regulations Phase 3 and 4 | Person_567 | 2016-10-21 01:00 | 2018-08-21 | 0.25 | 71.9682 | 17.992 | -- | 0.25 | 71.9682 | 17.992 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK022 | Project_042_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2017-09-20 01:00 | 2018-09-20 01:00 | 0.2 | 10.3335 | 1.0334 | Accept | 0.18 | 10.3335 | 1.0334 | H2 | 4 | Stable | 0.5 | 88 | 139 | 160 | 134 | 0.5 | 88 | 139 | 160 | 134 | 0 | 10 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK043 | Project_042_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st December | Person_455 | 2021-03-23 | 2021-05-22 | 0.1 | 33.9324 | 10.1797 | Accept | 0.08 | 33.9324 | 10.1797 | H3 | 3 | Stable | 0.9 | 86 | 125 | 159 | 124.1667 | 0.9 | 86 | 125 | 159 | 124.1667 | 0 | 20 | 1 | 0.6
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK024 | Project_042_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2019-09-21 01:00 | 2020-09-19 01:00 | 0.33 | 11.2729 | 2.2546 | Accept | 0.3 | 11.2729 | 2.2546 | H2 | 4 | Stable | 0.7 | 95 | 137 | 147 | 131.6667 | 0.7 | 95 | 137 | 147 | 131.6667 | 0 | 9.0909 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK046 | Project_042_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables - June | Person_455 | 2018-11-21 01:00 | 2020-11-19 01:00 | 0.2 | 3.7576 | 0.18788 | Accept | 0.1 | 3.7576 | 0.56365 | H2 | 4 | Stable | 0.7 | 117 | 135 | 155 | 135.3333 | 0.7 | 117 | 135 | 155 | 135.3333 | 0 | 50 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Further Software Development | Person_523 | 2015-05-24 | 2018-04-21 | 0.1 | 6.4382 | 2.2534 | Accept | 0.05 | 6.4382 | 1.2876 | H3 | 3 | Stable | 0.9 | 88 | 125 | 150 | 123 | 0.9 | 88 | 125 | 150 | 123 | 0 | 50 | 1 | 1.5
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK023 | Project_042_RISK023 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2018-09-21 01:00 | 2019-09-20 01:00 | 0.2 | 35.0206 | 7.0041 | Accept | 0.18 | 35.0206 | 7.0041 | H2 | 4 | Stable | 0.8 | 89 | 140 | 144 | 132.1667 | 0.8 | 89 | 140 | 144 | 132.1667 | 0 | 10 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software issue input | Person_279 | 2016-11-23 01:00 | 2023-02-20 01:00 | 0.4 | 49.4398 | 19.7759 | Reduce | 0.2 | 49.4398 | 9.888 | H2 | 4 | Stable | 0.9 | 105 | 136 | 143 | 132 | 0.1 | 37 | 50 | 78 | 52.5 | 0 | 50 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Interface implementation | Person_496 | 2014-01-21 01:00 | 2017-10-20 01:00 | 0.5 | 0.78457 | 0.39228 | Accept | 0.5 | 0.78457 | 0.39228 | H2 | 4 | Stable | 0.8 | 82 | 131 | 149 | 125.8333 | 0.8 | 82 | 131 | 149 | 125.8333 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of the platforms for modification | Person_496 | 2014-01-21 01:00 | 2018-02-18 01:00 | 0 | 1.6721 | 0.66883 | Accept | 0.67 | 1.6721 | 0.66883 | H3 | 3 | Stable | 0.5 | 94 | 131 | 154 | 128.6667 | 0.5 | 94 | 131 | 154 | 128.6667 | 0 | -inf | 1 | -inf
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unforseen and substantial increase in Repairs workload during new build production period. | Person_238 | 2017-10-23 01:00 | 2017-12-20 01:00 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.03 | 1.5434 | 0.046303 | H3 | 3 | Stable | 0.8 | 88 | 140 | 142 | 131.6667 | 0.3 | 7 | 50 | 64 | 45.1667 | 0 | 90 | 1 | 2.7
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK007 | Project_041_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Advanced production of products using a Qual. standard component rather than a Prod. standard | Person_547 | 2017-10-21 01:00 | 2017-12-20 01:00 | 0.49 | 1.2862 | 0.63024 | Reduce | 0.2 | 1.2862 | 0.25724 | H3 | 3 | Stable | 0.8 | 117 | 129 | 156 | 131.5 | 0.3 | 6 | 59 | 63 | 50.8333 | 0 | 59.1837 | 1 | 1.7755
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 09:00 | 2019-08-20 09:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_693 | 2017-05-23 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.8 | 100 | 125 | 158 | 126.3333 | 0.3 | 19 | 53 | 60 | 48.5 | 0 | 50 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 09:00 | 2019-08-20 09:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2017-04-22 | 2018-05-22 | 0.75 | 10.7184 | 8.0388 | Reduce | 0.2 | 2.4052 | 0.48104 | H3 | 3 | Worsening | 0.7 | 106 | 125 | 157 | 127.1667 | 0.4 | 14 | 51 | 63 | 46.8333 | 77.56 | 73.3333 | 0 | 46.536
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 09:00 | 2019-08-20 09:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK029 | Project_042_RISK029 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st October to 31st December | Person_455 | 2021-02-20 01:00 | 2021-05-22 | 0.25 | 1.9722 | 0.98609 | Accept | 0.1 | 1.9722 | 0.98609 | H2 | 4 | Stable | 0.5 | 112 | 127 | 145 | 127.5 | 0.5 | 112 | 127 | 145 | 127.5 | 0 | 60 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 09:00 | 2019-08-20 09:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 09:00 | 2019-08-20 09:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment (Second Test Set) | Person_238 | 2017-05-23 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.05 | 0.68598 | 0.034299 | H3 | 3 | Improving | 0.5 | 120 | 135 | 149 | 134.8333 | 0.4 | 38 | 44 | 74 | 48 | 0 | 80 | 1 | 2.4
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK031 | Project_042_RISK031 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours 1st July to 30th September | Person_455 | 2020-11-19 01:00 | 2021-02-19 01:00 | 0.2 | 0.45017 | 0.13505 | Accept | 0.15 | 0.45017 | 0.13505 | H2 | 4 | Stable | 0.5 | 85 | 138 | 152 | 131.5 | 0.5 | 85 | 138 | 152 | 131.5 | 0 | 25 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 | 0.05 | 3.7514 | 0.37514 | Accept | 0.05 | 3.7514 | 0.37514 | H3 | 3 | Stable | 0.7 | 116 | 128 | 142 | 128.3333 | 0.7 | 116 | 128 | 142 | 128.3333 | 0 | 0 | 1 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2017-05-23 | 2019-04-23 | 0.1 | 21.8655 | 2.1865 | Reduce | 0.01 | 21.8655 | 0.21865 | H2 | 4 | Improving | 0.5 | 81 | 135 | 143 | 127.3333 | 0.4 | 13 | 42 | 63 | 40.6667 | 0 | 90 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2017-05-23 | 2019-08-20 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Stable | 0.6 | 92 | 136 | 155 | 131.8333 | 0.2 | 20 | 41 | 60 | 40.6667 | 0 | 60 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Unidentified CRs and concessions | Person_693 | 2017-04-22 | 2019-07-22 | 0.5 | 1.2005 | 0.60023 | Reduce | 0.15 | 0.51019 | 0.076529 | H3 | 3 | Stable | 0.5 | 105 | 127 | 145 | 126.3333 | 0.2 | 23 | 57 | 76 | 54.5 | 57.5001 | 70 | 1 | 36.6001
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_238 | 2017-04-22 | 2018-05-22 | 0.25 | 3.3227 | 0.83067 | Reduce | 0.05 | 3.3227 | 0.16613 | H3 | 3 | Stable | 0.8 | 117 | 140 | 142 | 136.5 | 0.4 | 16 | 58 | 67 | 52.5 | 0 | 80 | 1 | 2.4
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_693 | 2017-05-23 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.1 | 0.77172 | 0.077172 | H3 | 3 | Stable | 0.9 | 97 | 134 | 160 | 132.1667 | 0.4 | 14 | 42 | 72 | 42.3333 | 0 | 60 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK030 | Project_042_RISK030 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours 31st March to 29 June | Person_455 | 2020-08-20 01:00 | 2020-11-18 01:00 | 0.2 | 1.7492 | 0.17492 | Accept | 0.15 | 1.7492 | 0.17492 | H2 | 4 | Stable | 0.5 | 89 | 135 | 154 | 130.5 | 0.5 | 89 | 135 | 154 | 130.5 | 0 | 25 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_693 | 2017-05-23 | 2018-01-20 01:00 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.08 | 6.431 | 0.51448 | H3 | 3 | Improving | 0.7 | 98 | 130 | 153 | 128.5 | 0.2 | 32 | 46 | 72 | 48 | -47.0588 | 46.6667 | 1 | -26.8353
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Reduce touch labour if Production readiness programme successful | Person_238 | 2017-05-23 | 2018-02-20 01:00 | 0.3 | 1.5606 | 0.46818 | Exploit | 0.5 | 1.5606 | 0.7803 | H2 | 4 | Stable | [10 empty] | 0 | -66.6667 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-002 | Project_021_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 117 | 132 | 160 | 134.1667 | 0.4 | 14 | 42 | 68 | 41.6667 |  | 66.6667 | 1
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H3 | 3 | Stable | 0.5 | 97 | 137 | 143 | 131.3333 | 0.1 | 1 | 46 | 72 | 42.8333 |  | 62.5 | 1
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-009 | Project_021_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification Report delays due to insufficient resource in supply chain | Person_207 | 2017-09-20 01:00 | 2017-12-20 01:00 | 0.2 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 108 | 126 | 148 | 126.6667 | 0.2 | 18 | 51 | 62 | 47.3333 |  | 50 | 1
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-004 | Project_021_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.6 | 101 | 131 | 151 | 129.3333 | 0.1 | 36 | 50 | 73 | 51.5 |  | 80 | 1
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-014 | Project_021_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.9 | 112 | 127 | 151 | 128.5 | 0.3 | 14 | 48 | 71 | 46.1667 |  | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-013 | Project_021_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to late Trials Approval | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 86 | 132 | 155 | 128.1667 | 0.2 | 36 | 50 | 79 | 52.5 |  | 66.6667 | 1
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification delays | Person_207 | 2017-09-20 01:00 | 2017-11-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Worsening | 0.8 | 117 | 136 | 143 | 134 | 0.4 | 22 | 53 | 69 | 50.5 |  | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-018 | Project_021_Risk-018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2017-05-23 | 2017-11-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.5 | 92 | 126 | 151 | 124.5 | 0.3 | 7 | 49 | 77 | 46.6667 |  | 40 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-017 | Project_021_Risk-017 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target. | Person_061 | 2013-01-07 01:00 | 2018-02-04 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.7 | 113 | 135 | 156 | 134.8333 | 0.2 | 17 | 51 | 79 | 50 | 0 | 33.3333 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-015 | Project_021_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to technical performance | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.3 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.5 | 107 | 136 | 148 | 133.1667 | 0.1 | 31 | 58 | 78 | 56.8333 |  | 33.3333 | 1
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK021 | Project_021_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | ERP implementation | Person_174 | 2017-06-23 | 2017-09-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.25 | 0 | 0 | H2 | 4 | Stable | 0.5 | 120 | 121 | 153 | 126.1667 | 0.1 | 17 | 49 | 75 | 48 |  | 50 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_174 | 2012-11-20 01:00 | 2018-08-21 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.6 | 119 | 136 | 151 | 135.6667 | 0.3 | 7 | 48 | 79 | 46.3333 | 0 | 50 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK024 | Project_021_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_482 | 2017-05-23 | 2017-11-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 96 | 123 | 141 | 121.5 | 0.4 | 29 | 44 | 77 | 47 |  | 40 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2018-02-19 01:00 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Stable | 0.9 | 104 | 133 | 147 | 130.5 | 0.1 | 18 | 50 | 72 | 48.3333 | 0 | 57.1429 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 0.8 | 4.6352 | 3.7081 | Reduce | 0.6 | 4.6352 | 2.7811 | H1 | 5 | Worsening | 0.6 | 97 | 127 | 145 | 125 | 0.2 | 37 | 41 | 62 | 43.8333 | 0 | 25 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-12-20 01:00 | 0.6 | 17.2826 | 10.3696 | Reduce | 0.3 | 17.2826 | 5.1848 | H2 | 4 | Worsening | 0.8 | 120 | 137 | 146 | 135.6667 | 0.3 | 7 | 52 | 78 | 48.8333 | 0 | 50 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Additional tasks required with mode certification | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 0.8 | 1.3243 | 1.0595 | Reduce | 0.6 | 1.3243 | 0.7946 | H1 | 5 | Worsening | 0.5 | 106 | 135 | 144 | 131.6667 | 0.4 | 33 | 54 | 68 | 52.8333 | 0 | 25 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2018-01-19 01:00 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.9 | 86 | 140 | 148 | 132.3333 | 0.1 | 10 | 57 | 65 | 50.5 | 80 | 66.6667 | 0 | 48
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond (revised) target. | Person_482 | 2013-01-07 01:00 | 2018-02-04 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.7 | 119 | 139 | 147 | 137 | 0.2 | 8 | 48 | 75 | 45.8333 | 0 | 33.3333 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2013-01-07 01:00 | 2017-11-19 01:00 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.9 | 92 | 132 | 154 | 129 | 0.4 | 31 | 57 | 64 | 53.8333 | 0 | 33.3333 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_174 | 2009-06-23 | 2018-08-21 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.7 | 91 | 127 | 152 | 125.1667 | 0.3 | 23 | 45 | 73 | 46 | 50 | 28.5714 | 0 | 30
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-09-19 01:00 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.5 | 120 | 125 | 145 | 127.5 | 0.3 | 10 | 50 | 63 | 45.5 | 7.8429 | 40 | 0 | 4.7058
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-12-17 01:00 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.4 | 12.6474 | 5.059 | H2 | 4 | Stable | 0.8 | 108 | 136 | 146 | 133 | 0.1 | 32 | 46 | 77 | 48.8333 | 0 | 33.3333 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.5 | 99 | 122 | 151 | 123 | 0.3 | 3 | 46 | 74 | 43.5 | 0 | 50 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-022 | Project_021_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | trials delay due to lack of supporting resources | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 100 | 132 | 160 | 131.3333 | 0.1 | 28 | 57 | 72 | 54.6667 |  | 66.6667 | 1
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-021 | Project_021_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | trials delay due to lack of equipment | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.9 | 91 | 132 | 155 | 129 | 0.1 | 33 | 58 | 69 | 55.6667 |  | 66.6667 | 1
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2018-05-22 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.6 | 93 | 135 | 151 | 130.6667 | 0.2 | 18 | 41 | 70 | 42 | 0 | 40 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK037 | Project_042_RISK037 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 1 | Person_455 | 2020-05-23 | 2021-05-22 | 0.14 | 11.0894 | 0.55447 | Accept | 0.11 | 11.0894 | 0.55447 | H2 | 4 | Stable | 0.5 | 113 | 128 | 154 | 129.8333 | 0.5 | 113 | 128 | 154 | 129.8333 | 0 | 21.4286 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.7 | 0.92411 | 0.64688 | Reduce | 0.3 | 0.36965 | 0.11089 | H2 | 4 | Stable | 0.5 | 108 | 137 | 145 | 133.5 | 0.2 | 34 | 41 | 72 | 45 | 60 | 57.1429 | 0 | 36
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 | 2018-04-21 | 0.5 | 4.0661 | 2.033 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.9 | 110 | 132 | 160 | 133 | 0.4 | 6 | 42 | 68 | 40.3333 | 0 | 90 | 1 | 2.7
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.5 | 0.46206 | 0.23103 | H1 | 5 | Improving | 0.8 | 94 | 122 | 154 | 122.6667 | 0.2 | 24 | 44 | 77 | 46.1667 | 58.3333 | 16.6667 | 0 | 35
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_523 | 2015-01-22 01:00 | 2018-04-21 | 0.35 | 1.1089 | 0.88715 | Accept | 0.2 | 0.73929 | 0.44357 | H2 | 4 | Stable | 0.9 | 88 | 140 | 150 | 133 | 0.9 | 88 | 140 | 150 | 133 | 33.3333 | 42.8571 | 0 | 20
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 | 2018-05-22 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.8 | 83 | 135 | 147 | 128.3333 | 0.3 | 25 | 42 | 64 | 42.8333 | 0 | 50 | 1 | 1.5
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2018-05-22 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.6 | 101 | 125 | 150 | 125.1667 | 0.3 | 9 | 50 | 77 | 47.6667 | 0 | 25 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_693 | 2012-06-01 | 2018-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Improving | 0.6 | 104 | 131 | 150 | 129.6667 | 0.2 | 21 | 54 | 69 | 51 | 0 | 40 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2018-05-21 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Stable | [10 empty] | 0 | 37.5 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK036 | Project_042_RISK036 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 2 | Person_455 | 2019-05-24 | 2020-05-22 | 0.25 | 3.6965 | 0.36965 | Accept | 0.2 | 3.6965 | 0.36965 | H2 | 4 | Stable | 0.8 | 95 | 125 | 152 | 124.5 | 0.8 | 95 | 125 | 152 | 124.5 | 0 | 20 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_332 | 2016-06-23 | 2018-02-19 01:00 | 0.4 | 1.8482 | 0.55447 | Accept | 0.2 | 1.8482 | 0.73929 | H2 | 4 | Stable | 0.9 | 91 | 138 | 146 | 131.5 | 0.9 | 91 | 138 | 146 | 131.5 | 0 | 50 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2018-02-19 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.8 | 111 | 132 | 153 | 132 | 0.1 | 20 | 41 | 63 | 41.1667 | 90 | 75 | 1 | 56.25
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-19 23:00 | 0.4 | 9.139 | 3.6556 | Avoid | 0.2 | 9.139 | 1.8278 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Product Baseline delivery is late | Person_151 | 2015-09-20 23:00 | 2017-02-12 23:00 | 0.125 | 232.2192 | 29.0274 | -- | 0.215 | 27.8663 | 5.9913 | H2 | 4 | Stable | [10 empty] | 88 | -72 | 0 | 52.8
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 0.5 | 13.7833 | 6.8917 | Avoid | 0.2 | 6.8917 | 1.3783 | H3 | 3 | Stable | [10 empty] | 50 | 60 | 1 | 31.8
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-19 23:00 | 0.3 | 5.5433 | 1.663 | Reduce | 0.35 | 5.5433 | 1.9402 | H2 | 4 | Worsening | 0.7 | 97 | 127 | 149 | 125.6667 | 0.3 | 34 | 58 | 66 | 55.3333 | 0 | -16.6667 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-20 23:00 | 2016-11-19 23:00 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Worsening | [10 empty] | 0 | 75 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK039 | Project_042_RISK039 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality Issues 16th August to 15th August | Person_540 | 2020-01-06 01:00 | 2021-01-04 01:00 | 0.1 | 4.4946 | 1.1236 | Accept | 0.08 | 4.4946 | 0.44946 | H2 | 4 | Stable | 0.6 | 88 | 131 | 159 | 128.5 | 0.6 | 88 | 131 | 159 | 128.5 | 0 | 20 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK038 | Project_042_RISK038 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality Issues 16th August to 15th August | Person_540 | 2019-01-06 01:00 | 2020-01-05 01:00 | 0.1 | 6.7418 | 1.6855 | Accept | 0.08 | 6.7418 | 1.0113 | H2 | 4 | Stable | 0.7 | 81 | 136 | 144 | 128.1667 | 0.7 | 81 | 136 | 144 | 128.1667 | 0 | 20 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 0.3 | 26.9674 | 8.0902 | Avoid | 0.3 | 14.9819 | 4.4946 | H2 | 4 | Stable | [10 empty] | 44.4444 | 0 | 0 | 26.6667
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-20 23:00 | 0.5 | 26.9674 | 13.4837 | Avoid | 0.1 | 12.7646 | 1.2765 | H2 | 4 | Worsening | [10 empty] | 52.6667 | 80 | 0 | 31.6
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-21 23:00 | 2016-12-20 23:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.7 | 86 | 123 | 145 | 120.5 | 0.3 | 39 | 58 | 73 | 57.3333 | 47 | 0 | 0 | 28.2
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-21 23:00 | 2016-12-20 23:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-18 23:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.2 | 1.5935 | 0.3187 | H3 | 3 | Stable | 0.5 | 96 | 133 | 156 | 130.6667 | 0.3 | 15 | 46 | 62 | 43.5 | 50 | 50 | 1 | 31.5
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.8 | 106 | 121 | 141 | 121.8333 | 0.4 | 38 | 54 | 63 | 52.8333 | 25.8065 | 20 | 0 | 15.4839
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK033 | Project_042_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st April to 30 June | Person_455 | 2019-08-22 01:00 | 2019-11-20 01:00 | 0.2 | 0.95811 | 0.23953 | Accept | 0.15 | 0.95811 | 0.23953 | H2 | 4 | Stable | 0.6 | 83 | 126 | 145 | 122 | 0.6 | 83 | 126 | 145 | 122 | 0 | 25 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-085 | Project_008_SER-085 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Insufficient LOE to manage the supply chain with reducing number of spares | Person_639 | 2017-04-22 | 2018-08-21 | 0.25 | 3.8949 | 1.9475 | Accept | 0.25 | 3.8949 | 0.19669 | H3 | 3 | Stable | 0.5 | 97 | 129 | 148 | 126.8333 | 0.5 | 97 | 129 | 148 | 126.8333 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK032 | Project_042_RISK032 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours 1st October to 31st December | Person_455 | 2021-02-20 01:00 | 2021-05-22 | 0.2 | 17.0765 | 1.7076 | Accept | 0.15 | 17.0765 | 1.7076 | H2 | 4 | Stable | 0.6 | 117 | 122 | 159 | 127.3333 | 0.6 | 117 | 122 | 159 | 127.3333 | 0 | 25 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK035 | Project_042_RISK035 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st October to 31st December | Person_455 | 2021-02-20 01:00 | 2021-05-22 | 0.2 | 186.9553 | 59.2026 | Accept | 0.15 | 186.9553 | 1.3939 | H2 | 4 | Stable | 0.7 | 97 | 125 | 143 | 123.3333 | 0.7 | 97 | 125 | 143 | 123.3333 | 0 | 25 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | RISK004 | Project_028_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Changes to be embodied on the Rig | Person_604 | 2017-04-29 | 2019-02-20 01:00 | 0.8 | 22.8501 | 6.855 | Accept | 0.3 | 22.8501 | 6.855 | H2 | 4 | Stable | 0.5 | 93 | 137 | 147 | 131.3333 | 0.5 | 93 | 137 | 147 | 131.3333 | 0 | 62.5 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Additional minor point releases | Person_228 | 2016-05-23 | 2017-10-19 01:00 | 0.5 | 11.9444 | 5.9722 | Reduce | 0.25 | 11.9444 | 2.9861 | H2 | 4 | Stable | 0.7 | 112 | 123 | 158 | 127 | 0.4 | 5 | 54 | 67 | 48 | 0 | 50 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_228 | 2016-05-23 | 2018-04-21 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.5 | 96 | 121 | 157 | 122.8333 | 0.2 | 2 | 50 | 61 | 43.8333 | 0 | 50 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_004 | 2015-11-21 01:00 | 2018-11-20 01:00 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.7 | 90 | 122 | 144 | 120.3333 | 0.4 | 32 | 55 | 77 | 54.8333 | 0 | 5 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.8 | 2.8043 | 2.2435 | Reduce | 0.45 | 2.8043 | 1.2619 | H1 | 5 | Stable | 0.9 | 84 | 124 | 143 | 120.5 | 0.3 | 13 | 54 | 65 | 49 | 0 | 43.75 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK167 | Project_024_RISK167 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Customer not providing the information needed or Customer not accepting the Customer documentation resulting in rewor. | Person_710 | 2016-08-21 01:00 | 2018-02-19 01:00 | 0.5 | 9.971 | 4.9855 | Reduce | 0.3 | 9.971 | 2.9913 | H1 | 5 | Worsening | 0.5 | 114 | 130 | 147 | 130.1667 | 0.1 | 19 | 50 | 70 | 48.1667 | 0 | 40 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK226 | Project_024_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Late Evidences Certification delivery | Person_710 | 2017-04-30 | 2017-12-21 01:00 | 0.4 | 3.9468 | 1.5787 | Reduce | 0.2 | 3.9468 | 0.78937 | H2 | 4 | Worsening | 0.5 | 89 | 132 | 147 | 127.3333 | 0.3 | 30 | 51 | 64 | 49.6667 | 0 | 50 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK034 | Project_042_RISK034 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st July to 30 September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 0.2 | 35.9673 | 10.7902 | Accept | 0.15 | 35.9673 | 9.773 | H2 | 4 | Stable | 0.7 | 81 | 134 | 147 | 127.3333 | 0.7 | 81 | 134 | 147 | 127.3333 | 0 | 25 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK040 | Project_042_RISK040 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st May to 30 Oct | Person_455 | 2019-09-21 01:00 | 2020-03-21 | 0.1 | 3.9728 | 1.3905 | Accept | 0.07 | 3.9728 | 1.3905 | H2 | 4 | Stable | 0.5 | 98 | 132 | 141 | 127.8333 | 0.5 | 98 | 132 | 141 | 127.8333 | 0 | 30 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.9 | 93 | 125 | 142 | 122.5 | 0.1 | 6 | 41 | 69 | 39.8333 | 0 | 60 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis and Security | Person_288 | 2017-02-22 01:00 | 2017-11-19 01:00 | 0.3 | 19.9938 | 5.9981 | Reduce | 0.04675 | 19.9938 | 0.93471 | H3 | 3 | Improving | 0.7 | 104 | 139 | 141 | 133.5 | 0.3 | 37 | 43 | 66 | 45.8333 | 0 | 84.4167 | 1 | 2.5325
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.2 | 3.843 | 0.76859 | H2 | 4 | Stable | 0.8 | 103 | 135 | 150 | 132.1667 | 0.4 | 16 | 49 | 77 | 48.1667 | 0 | 60 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Performance (collector opportunity) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.3814 | 26.127 | 9.9648 | -- | 0.4132 | 26.127 | 10.7957 | H1 | 5 | Stable | [10 empty] | 0 | -8.3377 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.3 | 20.8767 | 6.263 | H1 | 5 | Stable | 0.6 | 80 | 139 | 156 | 132 | 0.3 | 22 | 56 | 74 | 53.3333 | 50 | 25 | 0 | 30
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5094 | 70.0901 | 35.7039 | Reduce | 0.29635 | 50.4987 | 14.9653 | H2 | 4 | Worsening | 0.5 | 94 | 126 | 148 | 124.3333 | 0.4 | 10 | 50 | 60 | 45 | 27.9517 | 41.8237 | 0 | 16.771
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK308 | Project_024_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System robustness and resilience | Person_774 | 2017-04-06 | 2018-06-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.1 | 2.5966 | 0.25966 | H3 | 3 | Stable | 0.5 | 102 | 133 | 141 | 129.1667 | 0.2 | 7 | 44 | 69 | 42 | 58.3333 | 66.6667 | 1 | 37
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_567 | 2015-08-22 01:00 | 2018-08-21 | 0.45 | 0 | 0 | Accept | 0.45 | 0 | 0 | H2 | 4 | Worsening | 0.9 | 110 | 129 | 153 | 129.8333 | 0.9 | 110 | 129 | 153 | 129.8333 |  | 0 | 0
2017-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-04-20 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.7 | 95 | 135 | 146 | 130.1667 | 0.2 | 6 | 43 | 78 | 42.6667 | 0 | 25 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK042 | Project_042_RISK042 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st February to 14th July | Person_455 | 2020-06-23 | 2020-12-03 01:00 | 0.1 | 5.596 | 0.2798 | Accept | 0.08 | 5.596 | 0.2798 | H2 | 4 | Stable | 0.5 | 105 | 125 | 156 | 126.8333 | 0.5 | 105 | 125 | 156 | 126.8333 | 0 | 20 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK041 | Project_042_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st Jan | Person_455 | 2020-03-23 | 2020-06-22 | 0.1 | 0 | 0 | Accept | 0.08 | 0 | 0 | H2 | 4 | Stable | 0.9 | 106 | 133 | 153 | 131.8333 | 0.9 | 106 | 133 | 153 | 131.8333 |  | 20 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Local customer Engineers in country | Person_455 | 2019-03-22 | 2019-05-23 | 0.1 | 0.5596 | 0.05596 | Accept | 0.05 | 0.5596 | 0.05596 | H2 | 4 | Stable | 0.6 | 88 | 125 | 144 | 122 | 0.6 | 88 | 125 | 144 | 122 | 0 | 50 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Lack of Spares Availability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 0.3 | 2.3503 | 0.47006 | Accept | 0.3 | 2.3503 | 0.47006 | H3 | 3 | Stable | 0.6 | 89 | 127 | 152 | 124.8333 | 0.6 | 89 | 127 | 152 | 124.8333 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Volume of production tools and Jigs | Person_279 | 2016-11-23 01:00 | 2021-11-23 01:00 | 0.35 | 4.4768 | 2.2384 | Accept | 0.2 | 4.4768 | 2.2384 | H2 | 4 | Stable | 0.6 | 94 | 136 | 155 | 132.1667 | 0.6 | 94 | 136 | 155 | 132.1667 | 0 | 42.8571 | 0 | 0
2017-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_077 | 2016-01-22 01:00 | 2018-02-17 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H1 | 5 | Improving | 0.5 | 94 | 124 | 143 | 122.1667 | 0.4 | 39 | 57 | 75 | 57 |  | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Labour/Material Risk | Person_662 | 2015-05-24 | 2019-05-23 | 0.5 | 23.5255 | 11.7628 | Accept | 0.5 | 23.5255 | 11.7628 | H2 | 4 | Stable | 0.5 | 94 | 134 | 154 | 130.6667 | 0.5 | 94 | 134 | 154 | 130.6667 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Risk of not being able to perform Tests | Person_238 | 2017-12-21 01:00 | 2019-01-21 01:00 | 0.5 | 22.384 | 11.192 | Accept | 0.5 | 22.384 | 11.192 | H2 | 4 | Stable | 0.6 | 111 | 131 | 157 | 132 | 0.6 | 111 | 131 | 157 | 132 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_238 | 2017-05-23 | 2019-01-21 01:00 | 0.5 | 3.772 | 2.6404 | Accept | 0.5 | 3.772 | 2.6404 | H2 | 4 | Stable | 0.8 | 113 | 132 | 142 | 130.5 | 0.8 | 113 | 132 | 142 | 130.5 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_693 | 2017-04-22 | 2018-05-13 | 0.3 | 5.8198 | 4.0739 | Accept | 0.3 | 5.8198 | 4.0739 | H3 | 3 | Stable | 0.9 | 92 | 136 | 155 | 131.8333 | 0.9 | 92 | 136 | 155 | 131.8333 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_547 | 2017-05-23 | 2018-05-22 | 0.1 | 1.0618 | 0.53089 | Accept | 0.1 | 1.0618 | 0.53089 | H3 | 3 | Stable | 0.8 | 116 | 137 | 151 | 135.8333 | 0.8 | 116 | 137 | 151 | 135.8333 | 0 | 0 | 1 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production, Procurement or Engineering | Person_725 | 2018-01-21 01:00 | 2019-05-23 | 0.1 | 2.2586 | 0.90343 | Accept | 0.1 | 2.2586 | 0.90343 | H3 | 3 | Stable | 0.5 | 109 | 131 | 156 | 131.5 | 0.5 | 109 | 131 | 156 | 131.5 | 0 | 0 | 1 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 | 0.05 | 2.9272 | 1.4636 | Accept | 0.05 | 2.9272 | 1.4636 | H2 | 4 | Stable | 0.8 | 90 | 125 | 155 | 124.1667 | 0.8 | 90 | 125 | 155 | 124.1667 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2018-04-22 | 0.8 | 4.4984 | 2.2492 | Accept | 0.6 | 4.4984 | 2.2492 | H1 | 5 | Stable | 0.7 | 88 | 128 | 142 | 123.6667 | 0.7 | 88 | 128 | 142 | 123.6667 | 0 | 25 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 | 2018-05-22 | 0.1 | 1.6962 | 0.33923 | Accept | 0.1 | 1.6962 | 0.33923 | H2 | 4 | Stable | 0.9 | 96 | 134 | 142 | 129 | 0.9 | 96 | 134 | 142 | 129 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2018-05-21 | 0.2 | 3.0513 | 0.61026 | Accept | 0.2 | 3.0513 | 0.61026 | H3 | 3 | Improving | 0.7 | 98 | 136 | 150 | 132 | 0.7 | 98 | 136 | 150 | 132 | 0 | 0 | 1 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2018-04-22 | 0.3 | 18.9062 | 9.4531 | Accept | 0.4 | 18.9062 | 9.4531 | H3 | 3 | Stable | 0.6 | 106 | 122 | 149 | 123.8333 | 0.6 | 106 | 122 | 149 | 123.8333 | 0 | -33.3333 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-21 23:00 | 2016-11-19 23:00 | 0.25 | 3.7214 | 0.93035 | Accept | 0.1 | 3.7214 | 0.93035 | H3 | 3 | Stable | 0.8 | 87 | 126 | 157 | 124.6667 | 0.8 | 87 | 126 | 157 | 124.6667 | 0 | 60 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-19 23:00 | 0.25 | 3.7207 | 0.93016 | Accept | 0.15 | 3.7207 | 0.93016 | H3 | 3 | Stable | 0.6 | 85 | 126 | 142 | 121.8333 | 0.6 | 85 | 126 | 142 | 121.8333 | 0 | 40 | 1 | 1.2
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 1.3834 | 0.55336 | H2 | 4 | Stable | 0.9 | 97 | 130 | 141 | 126.3333 | 0.4 | 27 | 57 | 68 | 53.8333 | 65.054 | 20 | 0 | 39.0324
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_703 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 5.0983 | 0.76474 | H3 | 3 | Stable | 0.8 | 86 | 138 | 142 | 130 | 0.4 | 29 | 47 | 68 | 47.5 | 19.0479 | 70 | 1 | 13.5287
2017-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-63 | Project_022_RISK-63 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Levy | Person_703 | 2012-04-19 | 2017-08-20 01:00 | 0.8 | 3.5298 | 2.8239 | Exploit | 0.8 | 3.5298 | 2.8239 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-62 | Project_022_RISK-62 | Threat | Project Contingency | Open | H3 | 3 | 8. Operations & Maintenance | Additional Costs from Integration Cost Centre | Person_703 | 2017-03-23 | 2017-05-14 | 0.5 | 7.1754 | 3.5877 | Avoid | 0.292 | 3.5877 | 1.0476 | H3 | 3 | Worsening | [10 empty] | 50 | 41.6 | 0 | 30
2017-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2017-06-21 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.35 | 2.8688 | 1.0041 | H2 | 4 | Stable | 0.9 | 119 | 122 | 150 | 126.1667 | 0.4 | 28 | 41 | 75 | 44.5 | 22.0253 | 56.25 | 0 | 13.2152
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-026 | Project_043_Risk-026 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Equipment Delivery & Certification Risk | Person_693 | 2017-04-19 | 2017-10-19 | 0.25 | 2.3975 | 2.3975 | Accept | 0.25 | 0 | 0 | H2 | 4 | Improving | 0.6 | 100 | 124 | 153 | 124.8333 | 0.6 | 100 | 124 | 153 | 124.8333 | 100 | 0 | 0 | 60
2017-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2017-08-20 01:00 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 0.65554 | 0.52443 | H2 | 4 | Stable | [10 empty] | 80.45 | 0 | 0 | 48.27
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2017-02-20 01:00 | 2018-05-22 | 0.1 | 27.1644 | 0.81493 | Accept | 0.1 | 12.8336 | 1.2834 | H3 | 3 | Stable | 0.7 | 103 | 133 | 148 | 130.5 | 0.7 | 103 | 133 | 148 | 130.5 | 52.7559 | 0 | 1 | 31.6535
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2018-03-22 | 2019-07-21 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.7 | 105 | 135 | 141 | 131 | 0.4 | 22 | 46 | 72 | 46.3333 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2018-03-16 01:00 | 0.1 | 6.4168 | 0.64168 | Transfer | 0.1 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sub-system FPGA | Person_332 | 2017-01-21 01:00 | 2018-02-20 01:00 | 0.4 | 1.5914 | 0.63655 | Reduce | 0.4 | 1.5914 | 0.63655 | H2 | 4 | Stable | 0.9 | 112 | 131 | 154 | 131.6667 | 0.3 | 11 | 55 | 73 | 50.6667 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort for System HW/SW- System upgrade | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.3 | 2.5667 | 0.77001 | H2 | 4 | Stable | 0.6 | 100 | 125 | 145 | 124.1667 | 0.1 | 21 | 58 | 65 | 53 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs | Person_372 | 2018-04-22 | 2018-08-22 01:00 | 0.5 | 6.6521 | 3.326 | Reduce | 0.5 | 6.6521 | 3.326 | H2 | 4 | Stable | 0.9 | 83 | 133 | 150 | 127.5 | 0.1 | 11 | 49 | 69 | 46 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.5 | 3.5934 | 1.7967 | H2 | 4 | Stable | 0.8 | 81 | 129 | 146 | 123.8333 | 0.1 | 13 | 49 | 64 | 45.5 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | HW - additional unplanned design effort | Person_332 | 2016-05-23 | 2018-02-20 01:00 | 0.4 | 3.3367 | 1.3347 | Reduce | 0.4 | 3.3367 | 1.3347 | H2 | 4 | Stable | 0.5 | 98 | 140 | 155 | 135.5 | 0.2 | 21 | 40 | 71 | 42 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK003 | Project_024_RISK003 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance | Person_288 | 2017-12-21 01:00 | 2018-08-21 | 0.31667 | 4.2779 | 1.0695 | Accept | 0.007456 | 4.2779 | 1.0695 | H2 | 4 | Stable | 0.9 | 95 | 137 | 144 | 131.1667 | 0.9 | 95 | 137 | 144 | 131.1667 | 0 | 97.6455 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Management Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 0.3 | 2.5667 | 0.77001 | Accept | 0.3 | 2.5667 | 0.77001 | H1 | 5 | Improving | 0.6 | 120 | 125 | 153 | 128.8333 | 0.6 | 120 | 125 | 153 | 128.8333 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design [in addition to costed effort] | Person_332 | 2017-05-28 | 2018-08-18 | 0.2 | 2.6951 | 0.53901 | Reduce | 0.2 | 2.6951 | 0.53901 | H3 | 3 | Improving | 0.9 | 117 | 136 | 149 | 135 | 0.4 | 39 | 49 | 61 | 49.3333 | 0 | 0 | 1 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Minimum Order Quantities | Person_372 | 2017-11-20 01:00 | 2018-05-15 | 0.2 | 1.925 | 0.38501 | -- | 0.2 | 1.925 | 0.38501 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_372 | 2018-04-22 | 2018-08-22 01:00 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Worsening | 0.6 | 85 | 137 | 155 | 131.3333 | 0.3 | 3 | 47 | 74 | 44.1667 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_585 | 2017-10-21 01:00 | 2019-07-21 | 0.333 | 11.5502 | 3.8462 | Reduce | 0.333 | 11.5502 | 3.8462 | H2 | 4 | Stable | 0.7 | 83 | 124 | 146 | 120.8333 | 0.4 | 31 | 59 | 69 | 56 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) at the System level on product platform - performed by 3rd parties | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.41 | 0 | 0 | H2 | 4 | Stable | [11 empty] | -2.5 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Sub-system / product system accreditation hindered by Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.1 | 0.25667 | 0.025667 | Transfer | 0.1 | 0.25667 | 0.025667 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 1.4673 | 0.58692 | Reduce | 0.4 | 1.4673 | 0.58692 | H2 | 4 | Improving | 0.5 | 90 | 139 | 142 | 131.3333 | 0.2 | 30 | 56 | 60 | 52.3333 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2018-03-21 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2018-01-19 01:00 | 0.3 | 0.89835 | 0.26951 | Transfer | 0.3 | 0.89835 | 0.26951 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 0.35 | 0.85557 | 0.29945 | Reduce | 0.35 | 1.9208 | 0.67227 | H2 | 4 | Stable | 0.6 | 100 | 137 | 146 | 132.3333 | 0.3 | 12 | 56 | 78 | 52.3333 | -124.5001 | 0 | 0 | -74.7001
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 0.77001 | 0.30801 | Reduce | 0.3 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.7 | 99 | 129 | 151 | 127.6667 | 0.4 | 27 | 59 | 74 | 56.1667 | 0 | 25 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2018-02-20 01:00 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.5 | 80 | 128 | 157 | 124.8333 | 0.1 | 8 | 57 | 68 | 50.6667 | 0 | 28.5714 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before Part B finished (Collector Risk) | Person_119 | 2016-10-20 01:00 | 2018-04-21 | 0.3 | 1.54 | 0.30801 | Accept | 0.27172 | 0.77001 | 0.154 | H2 | 4 | Worsening | 0.8 | 99 | 132 | 160 | 131.1667 | 0.8 | 99 | 132 | 160 | 131.1667 | 50 | 9.4267 | 0 | 30
2017-10-21 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK003 | Project_044_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Mono vs stereo Component | Person_358 | 2016-03-23 | 2018-10-22 01:00 | 0.7 | 14.4876 | 10.1413 | Reduce | 0.5 | 14.4876 | 7.2438 | H2 | 4 | Improving | 0.9 | 85 | 122 | 150 | 120.5 | 0.2 | 4 | 49 | 65 | 44.1667 | 0 | 28.5714 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-18 23:00 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-20 23:00 | 2016-10-18 23:00 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.6 | 82 | 137 | 156 | 131 | 0.1 | 7 | 59 | 77 | 53.3333 | 0 | 0 | 1 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-18 23:00 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-18 23:00 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-18 23:00 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-18 23:00 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-10-21 | ORG_001 | BA_002 | Portfolio_008 | Project_057 | Risk-01 | Project_057_Risk-01 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Cable | Person_464 | 2015-08-22 01:00 | 2016-12-21 01:00 | 0.4 | 12.6408 | 5.0563 | Reduce | 0.1 | 0.23232 | 0.023232 | H2 | 4 | Improving | 0.6 | 119 | 129 | 159 | 132.3333 | 0.2 | 24 | 42 | 79 | 45.1667 | 98.1622 | 75 | 0 | 58.8973
2017-10-21 | ORG_002 | BA_005 | Portfolio_011 | Project_047 | RISK006 | Project_047_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer find issues with delivered parts | Person_454 | 2017-05-23 | 2017-08-18 22:00 | 0.8 | 1.2591 | 1.0073 | Reduce | 0.4 | 1.2591 | 0.50365 | H3 | 3 | Improving | 0.8 | 88 | 124 | 157 | 123.5 | 0.2 | 5 | 50 | 75 | 46.6667 | 0 | 50 | 0 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_011 | Project_047 | RISK009 | Project_047_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Open PR's | Person_647 | 2017-04-22 | 2018-11-19 22:00 | 0.5 | 0.51323 | 0.25661 | Reduce | 0.3 | 0.51323 | 0.15397 | H2 | 4 | Improving | 0.7 | 96 | 137 | 150 | 132.3333 | 0.3 | 37 | 42 | 65 | 45 | 0 | 40 | 0 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_011 | Project_047 | RISK078 | Project_047_RISK078 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer find issues with delivered parts. | Person_236 | 2017-04-22 | 2018-10-19 22:00 | 0.9 | 20.2553 | 18.2298 | Reduce | 0.35 | 10.1277 | 3.5447 | H3 | 3 | Improving | 0.5 | 113 | 140 | 145 | 136.3333 | 0.4 | 5 | 41 | 62 | 38.5 | 50 | 61.1111 | 0 | 30
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2018-04-21 | 0.15 | 0.58983 | 0.088474 | -- | 0.15 | 0.58983 | 0.088474 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 0.2 | 0.62279 | 0.12456 | Avoid | 0.2 | 0.62279 | 0.12456 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2018-03-21 | 0.1 | 0.27503 | 0.027503 | -- | 0.1 | 0.27503 | 0.027503 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 0.2 | 1.8854 | 0.37708 | Reduce | 0.2 | 1.8854 | 0.37708 | H2 | 4 | Stable | 0.5 | 113 | 135 | 143 | 132.6667 | 0.1 | 19 | 59 | 62 | 52.8333 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2017-10-21 01:00 | 2018-08-21 | 0.4 | 1.4138 | 0.56551 | Reduce | 0.4 | 1.4138 | 0.56551 | H2 | 4 | Stable | 0.6 | 81 | 123 | 148 | 120.1667 | 0.2 | 8 | 45 | 75 | 43.8333 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-10-19 01:00 | 2018-08-21 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.8 | 95 | 122 | 145 | 121.3333 | 0.3 | 15 | 46 | 60 | 43.1667 |  | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Pick up and Drop off of Software Resource | Person_230 | 2018-04-21 | 2018-07-18 | 0.4 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 0.4 | 0.19206 | 0.076826 | -- | 0.4 | 0.19206 | 0.076826 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 0.4 | 0.58017 | 0.23207 | Avoid | 0.4 | 0.58017 | 0.23207 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.2 | 0.11365 | 0.022729 | -- | 0.2 | 0.11365 | 0.022729 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 0.55 | 0.32389 | 0.17814 | Reduce | 0.55 | 0.32389 | 0.17814 | H1 | 5 | Stable | 0.9 | 80 | 139 | 147 | 130.5 | 0.2 | 19 | 56 | 64 | 51.1667 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test/SAT | Person_182 | 2017-10-21 01:00 | 2018-05-21 | 0.4 | 0.19206 | 0.076826 | -- | 0.4 | 0.19206 | 0.076826 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 0.3 | 0.11933 | 0.035799 | -- | 0.3 | 0.022161 | 0.0066484 | H3 | 3 | Stable | [10 empty] | 81.4286 | 0 | 0 | 48.8571
2017-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2017-11-19 01:00 | 0.05 | 1.1416 | 0.68495 | Accept | 0.05 | 1.1416 | 0.68495 | H3 | 3 | Improving | 0.5 | 108 | 132 | 145 | 130.1667 | 0.5 | 108 | 132 | 145 | 130.1667 | 0 | 0 | 1 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-117 | Project_011_Risk-117 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Avaliability for testing/reviews | Person_147 | 2016-07-21 | 2018-08-21 | 0.35 | 0 | 0 | Avoid | 0.35 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-128 | Project_011_Risk-128 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Different maps needed post Qualification baseline | Person_147 | 2017-04-22 | 2018-01-21 01:00 | 0.5 | 0.05688 | 0.02844 | Transfer | 0.5 | 0.05688 | 0.02844 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-129 | Project_011_Risk-129 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Signature of Work Authorisation documents | Person_182 | 2017-05-24 | 2018-01-21 01:00 | 0.2 | 0.12643 | 0.025287 | -- | 0.2 | 0.12643 | 0.025287 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-130 | Project_011_Risk-130 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer does not accept Voice Pronounciation | Person_187 | 2017-05-24 | 2018-02-19 01:00 | 0.4 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.5 | 91 | 138 | 141 | 130.6667 | 0.4 | 15 | 57 | 62 | 50.8333 | 0 | 0 | 1 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-10-21 | ORG_002 | BA_005 | Portfolio_011 | Project_047 | RISK006 | Project_047_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer find issues with delivered parts | Person_454 | 2017-05-23 | 2017-08-18 23:00 | 0.8 | 1.2591 | 1.0073 | Reduce | 0.4 | 1.2591 | 0.50365 | H3 | 3 | Improving | 0.7 | 94 | 137 | 153 | 132.5 | 0.4 | 5 | 58 | 73 | 51.6667 | 0 | 50 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_009 | Project_045 | RISK001 | Project_045_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour/T&S Overspend | Person_662 | 2017-01-21 01:00 | 2020-05-22 | 0.5 | 8.8959 | 4.448 | Accept | 0.5 | 8.8959 | 4.448 | H2 | 4 | Stable | 0.6 | 115 | 134 | 156 | 134.5 | 0.6 | 115 | 134 | 156 | 134.5 | 0 | 0 | 0 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_011 | Project_047 | RISK009 | Project_047_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Open PR's | Person_647 | 2017-04-22 | 2018-11-19 23:00 | 0.5 | 0.51323 | 0.25661 | Reduce | 0.3 | 0.51323 | 0.15397 | H2 | 4 | Improving | 0.5 | 98 | 140 | 157 | 135.8333 | 0.4 | 16 | 44 | 77 | 44.8333 | 0 | 40 | 0 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_011 | Project_047 | RISK078 | Project_047_RISK078 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer find issues with delivered parts. | Person_236 | 2017-04-22 | 2018-10-19 23:00 | 0.9 | 20.2553 | 18.2298 | Reduce | 0.35 | 10.1277 | 3.5447 | H3 | 3 | Improving | 0.7 | 115 | 131 | 142 | 130.1667 | 0.1 | 21 | 49 | 64 | 46.8333 | 50 | 61.1111 | 0 | 30
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 19:00 | 2019-08-20 19:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.8 | 93 | 122 | 148 | 121.5 | 0.4 | 10 | 53 | 64 | 47.6667 | 83.3333 | 88.8889 | 1 | 52.6667
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.5 | 100 | 135 | 149 | 131.5 | 0.1 | 14 | 51 | 74 | 48.6667 | 72 | 0 | 0 | 43.2
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 19:00 | 2019-08-20 19:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.6 | 111 | 125 | 148 | 126.5 | 0.4 | 1 | 51 | 79 | 47.3333 | 47.7391 | 0 | 0 | 28.6435
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 19:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.6 | 111 | 124 | 147 | 125.6667 | 0.2 | 33 | 57 | 69 | 55 | 0 | 0 | 0 | 0
2017-10-21 | ORG_002 | BA_004 | Portfolio_010 | Project_046 | PRO004 | Project_046_PRO004 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | High Material Atrition Level | Person_025 | 2016-06-14 | 2017-11-20 01:00 | 0.5 | 1.618 | 0.80901 | Reduce | 0.5 | 1.618 | 0.80901 | H1 | 5 | Stable | 0.9 | 99 | 134 | 151 | 131 | 0.3 | 18 | 40 | 64 | 40.3333 | 0 | 0 | 0 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer find issues with delivered parts | Person_387 | 2016-05-23 | 2019-08-20 | 0.8 | 9.0039 | 7.2032 | Reduce | 0.25 | 9.0039 | 2.251 | H2 | 4 | Improving | 0.6 | 86 | 131 | 157 | 127.8333 | 0.2 | 31 | 45 | 76 | 47.8333 | 0 | 68.75 | 0 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Open PR's | Person_319 | 2017-04-22 | 2018-11-20 01:00 | 0.5 | 0.29361 | 0.1468 | Reduce | 0.15 | 0.29361 | 0.044041 | H3 | 3 | Improving | 0.5 | 97 | 140 | 157 | 135.6667 | 0.4 | 22 | 53 | 63 | 49.5 | 0 | 70 | 1 | 2.1
2017-10-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-002 | Project_052_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Schedule slippage due to infeed of critical hardware | Person_376 | 2017-08-19 | 2018-02-19 | 0.5 | 3.2555 | 1.6277 | Reduce | 0.5 | 3.2555 | 1.6277 | H3 | 3 | Stable | 0.7 | 84 | 125 | 145 | 121.5 | 0.2 | 15 | 52 | 71 | 49 | 0 | 0 | 0 | 0
2017-10-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-016 | Project_052_Risk-016 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Environmental conditions | Person_651 | 2017-08-19 | 2018-02-19 | 0.2 | 13.8182 | 2.7636 | Transfer | 0.2 | 13.8182 | 2.7636 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-10-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-010 | Project_052_Risk-010 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Potential update of software / hardware required during the 3 year support period (RESOURCE) | Person_376 | 2017-08-19 | 2018-02-19 | 0.3 | 3.1214 | 0.93642 | Transfer | 0.3 | 3.1184 | 0.93551 | H3 | 3 | Stable | [10 empty] | 0.09816 | 0 | 0 | 0.058896
2017-10-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-012 | Project_052_Risk-012 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Issues from Supplier affect product | Person_651 | 2017-08-19 | 2020-08-19 | 0.3 | 5.1992 | 1.5598 | -- | 0.3 | 5.1972 | 1.5591 | H3 | 3 | Stable | [10 empty] | 0.038674 | 0 | 0 | 0.023204
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 1.2124 | 0.12124 | Accept | 0.1 | 1.2124 | 0.060622 | H3 | 3 | Stable | 0.7 | 104 | 140 | 151 | 135.8333 | 0.7 | 104 | 140 | 151 | 135.8333 | 0 | -233.3333 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 0.80829 | 0.32332 | Accept | 0.25 | 0.80829 | 0.32332 | H2 | 4 | Stable | 0.8 | 108 | 125 | 152 | 126.6667 | 0.8 | 108 | 125 | 152 | 126.6667 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 0.80829 | 0.32332 | Accept | 0.3 | 0.80829 | 0.32332 | H2 | 4 | Stable | 0.5 | 98 | 130 | 147 | 127.5 | 0.5 | 98 | 130 | 147 | 127.5 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2020-09-19 01:00 | 0.2 | 0.64663 | 0.32332 | Accept | 0.2 | 0.64663 | 0.32332 | H3 | 3 | Stable | 0.9 | 118 | 124 | 150 | 127.3333 | 0.9 | 118 | 124 | 150 | 127.3333 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2019-07-21 | 0.3 | 0.80829 | 0.16166 | Accept | 0.2 | 0.80829 | 0.16166 | H3 | 3 | Stable | 0.7 | 109 | 126 | 160 | 128.8333 | 0.7 | 109 | 126 | 160 | 128.8333 | 0 | 33.3333 | 1 | 1
2017-10-21 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK008 | Project_044_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Skills | Person_505 | 2017-10-21 01:00 | 2018-10-22 01:00 | 0.3 | 1.6166 | 0.64663 | Accept | 0.3 | 1.6166 | 0.64663 | H2 | 4 | Stable | 0.6 | 114 | 123 | 154 | 126.6667 | 0.6 | 114 | 123 | 154 | 126.6667 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 0.2 | 2.0207 | 0.20207 | Accept | 0.2 | 2.0207 | 0.20207 | H2 | 4 | Stable | 0.7 | 105 | 136 | 145 | 132.3333 | 0.7 | 105 | 136 | 145 | 132.3333 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 0.25 | 0.5769 | 0.28845 | Accept | 0.25 | 0 | 0 | H3 | 3 | Stable | 0.6 | 101 | 128 | 152 | 127.5 | 0.6 | 101 | 128 | 152 | 127.5 | 100 | 0 | 0 | 60
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | More issues during Qualification including additional PRs | Person_147 | 2017-07-26 | 2017-12-17 01:00 | 0.6 | 0 | 0 | Accept | 0.6 | 0 | 0 | H1 | 5 | Stable | 0.5 | 107 | 126 | 153 | 127.3333 | 0.5 | 107 | 126 | 153 | 127.3333 |  | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-148 | Project_008_SER-148 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Demands but not provisioned | Person_639 | 2018-08-22 01:00 | 2020-08-20 01:00 | 0.3 | 1.4422 | 1.0096 | Accept | 0.3 | 1.4422 | 1.0096 | H3 | 3 | Stable | 0.5 | 93 | 126 | 157 | 125.6667 | 0.5 | 93 | 126 | 157 | 125.6667 | 0 | 0 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-094 | Project_008_Risk-094 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Consumable Stock Levels | Person_567 | 2017-04-22 | 2018-08-21 | 0.5 | 1.4007 | 0.49026 | Accept | 0.5 | 1.4007 | 0.49026 | H3 | 3 | Stable | 0.9 | 83 | 134 | 141 | 126.6667 | 0.9 | 83 | 134 | 141 | 126.6667 | 0 | 0 | 1 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-000 | Project_008_SER-000 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_567 | 2018-05-22 | 2018-08-21 | 0.25 | 1.0661 | 0.21322 | Accept | 0.25 | 0 | 0 | H3 | 3 | Stable | 0.6 | 88 | 123 | 142 | 120.3333 | 0.6 | 88 | 123 | 142 | 120.3333 | 100 | 0 | 0 | 60
2017-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 0.61 | 1.0661 | 0.21322 | Accept | 0.61 | 0 | 0 | H1 | 5 | Stable | 0.8 | 96 | 140 | 143 | 133.1667 | 0.8 | 96 | 140 | 143 | 133.1667 | 100 | 0 | 0 | 60
2017-11-20 | ORG_002 | BA_004 | Portfolio_010 | Project_046 | PRO004 | Project_046_PRO004 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | High Material Atrition Level | Person_025 | 2016-06-14 | 2017-11-20 | 0.5 | 1.618 | 0.80901 | Reduce | 0.5 | 1.618 | 0.80901 | H1 | 5 | Stable | 0.6 | 91 | 126 | 149 | 124 | 0.2 | 9 | 52 | 65 | 47 | 0 | 0 | 0 | 0
2017-10-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-013 | Project_052_Risk-013 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Additional material and effort required to support the delta equipment | Person_376 | 2017-08-19 | 2018-02-19 | 0.3 | 0 | 0 | Accept | 0.3 | 0 | 0 | H3 | 3 | Stable | 0.9 | 117 | 125 | 148 | 127.5 | 0.9 | 117 | 125 | 148 | 127.5 |  | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 18:00 | 2019-08-20 18:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.9 | 82 | 131 | 150 | 126 | 0.2 | 17 | 50 | 61 | 46.3333 | 83.3333 | 88.8889 | 1 | 52.6667
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 18:00 | 2019-08-20 18:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.9 | 111 | 121 | 150 | 124.1667 | 0.4 | 1 | 52 | 62 | 45.1667 | 72 | 0 | 0 | 43.2
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 18:00 | 2019-08-20 18:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.8 | 117 | 130 | 144 | 130.1667 | 0.2 | 26 | 55 | 79 | 54.1667 | 47.7391 | 0 | 0 | 28.6435
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 18:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.8 | 89 | 126 | 146 | 123.1667 | 0.2 | 37 | 45 | 76 | 48.8333 | 0 | 0 | 0 | 0
2017-10-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-004 | Project_052_Risk-004 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Installation Risk for Phase 1a and 1b | Person_488 | 2017-08-19 | 2018-02-19 | 0.2 | 0.78901 | 0.3945 | Accept | 0.2 | 0.78901 | 0.3945 | H3 | 3 | Stable | 0.8 | 92 | 134 | 153 | 130.1667 | 0.8 | 92 | 134 | 153 | 130.1667 | 0 | 0 | 0 | 0
2017-10-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-005 | Project_052_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Potential update of software / hardware required during the 3 year support period | Person_488 | 2017-08-19 | 2018-02-19 | 0.3 | 5.126 | 2.563 | Accept | 0.3 | 5.126 | 2.563 | H3 | 3 | Stable | 0.9 | 117 | 132 | 141 | 131 | 0.9 | 117 | 132 | 141 | 131 | 0 | 0 | 0 | 0
2017-10-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-020 | Project_052_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Material escalation - | Person_376 | 2017-08-19 | 2018-02-19 | 0.3 | 7.3848 | 3.6924 | Accept | 0.3 | 7.3848 | 3.6924 | H3 | 3 | Stable | 0.5 | 104 | 136 | 145 | 132.1667 | 0.5 | 104 | 136 | 145 | 132.1667 | 0 | 0 | 0 | 0
2017-10-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-001 | Project_052_Risk-001 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Greater modification than expected for system uplift | Person_376 | 2017-08-19 | 2018-02-19 | 0.3 | 3.1344 | 1.5672 | Accept | 0.3 | 3.1344 | 1.5672 | H3 | 3 | Stable | 0.9 | 110 | 132 | 151 | 131.5 | 0.9 | 110 | 132 | 151 | 131.5 | 0 | 0 | 0 | 0
2017-10-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-006 | Project_052_Risk-006 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Acceptance failures | Person_488 | 2017-08-19 | 2018-02-19 | 0.3 | 12.815 | 2.563 | Accept | 0.3 | 12.815 | 2.563 | H3 | 3 | Stable | 0.8 | 84 | 132 | 148 | 126.6667 | 0.8 | 84 | 132 | 148 | 126.6667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.5 | 96 | 138 | 154 | 133.6667 | 0.1 | 27 | 54 | 71 | 52.3333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-20 22:00 | 2016-08-20 22:00 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.7 | 100 | 132 | 147 | 129.1667 | 0.4 | 7 | 43 | 72 | 41.8333 | 0 | 16.6667 | 0 | 0
2017-10-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-018 | Project_052_Risk-018 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Support - spares availability | Person_156 | 2017-08-19 | 2018-02-19 | 0.2 | 7.689 | 2.6911 | Accept | 0.2 | 7.689 | 2.6911 | H3 | 3 | Stable | 0.7 | 110 | 130 | 143 | 128.8333 | 0.7 | 110 | 130 | 143 | 128.8333 | 0 | 0 | 0 | 0
2017-10-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-019 | Project_052_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Additional Design effort required | Person_488 | 2017-08-19 | 2018-02-19 | 0.2 | 5.4336 | 1.3584 | Accept | 0.2 | 5.4336 | 1.3584 | H3 | 3 | Stable | 0.9 | 93 | 129 | 144 | 125.5 | 0.9 | 93 | 129 | 144 | 125.5 | 0 | 0 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK004 | Project_048_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 1.0253 | 0.20506 | Reduce | 0.15 | 1.0253 | 0.1538 | H3 | 3 | Stable | 0.6 | 110 | 129 | 158 | 130.6667 | 0.3 | 36 | 45 | 75 | 48.5 | 0 | 25 | 0 | 0
2017-10-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-009 | Project_052_Risk-009 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | System acceptance not costed in line with Customer expectations | Person_651 | 2017-08-19 | 2020-08-19 | 0.3 | 0 | 0 | Accept | 0.3 | 0 | 0 | H3 | 3 | Stable | 0.7 | 82 | 127 | 149 | 123.1667 | 0.7 | 82 | 127 | 149 | 123.1667 |  | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK003 | Project_048_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Lead Times | Person_261 | 2017-02-20 01:00 | 2020-05-22 | 0.3 | 1.1285 | 0.33856 | Avoid | 0.2 | 1.1285 | 0.22571 | H3 | 3 | Worsening | [10 empty] | 0 | 33.3333 | 1 | 1
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK014 | Project_048_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2020-05-22 | 0.1 | 2.5117 | 0.25117 | Reduce | 0.05 | 2.5117 | 0.12558 | H3 | 3 | Worsening | 0.9 | 120 | 126 | 151 | 129.1667 | 0.4 | 28 | 40 | 72 | 43.3333 | 0 | 50 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK006 | Project_048_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Customer | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0.20644 | 0.041288 | Reduce | 0.15 | 0.20644 | 0.030966 | H3 | 3 | Stable | 0.5 | 95 | 140 | 148 | 133.8333 | 0.1 | 1 | 47 | 70 | 43.1667 | 0 | 25 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK005 | Project_048_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 0.43506 | 0.26104 | Avoid | 0.5 | 0.43506 | 0.21753 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK011 | Project_048_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Line Qualification | Person_270 | 2017-02-20 01:00 | 2019-05-23 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.5 | 115 | 124 | 149 | 126.6667 | 0.1 | 24 | 46 | 78 | 47.6667 |  | 0 | 1
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK002 | Project_048_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2020-05-22 | 0.15 | 0.30966 | 0.046449 | Avoid | 0.15 | 0.30966 | 0.046449 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK001 | Project_048_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Procurement | Person_261 | 2017-02-20 01:00 | 2019-05-23 | 0.3 | 5.5679 | 1.6704 | Reduce | 0.2 | 5.5679 | 1.1136 | H3 | 3 | Stable | 0.6 | 115 | 128 | 159 | 131 | 0.4 | 37 | 47 | 60 | 47.5 | 0 | 33.3333 | 1 | 1
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK012 | Project_048_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Customer requires additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 | 2017-08-20 | 0.1 | 53.0293 | 5.3029 | Reduce | 0.1 | 53.0293 | 5.3029 | H3 | 3 | Worsening | 0.9 | 91 | 134 | 154 | 130.1667 | 0.3 | 6 | 57 | 62 | 49.3333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK008 | Project_048_RISK008 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Oracle | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0.20644 | 0.041288 | Avoid | 0.1 | 0.20644 | 0.020644 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK007 | Project_048_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Staff Availability | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0.067093 | 0.013419 | Avoid | 0.1 | 0.067093 | 0.0067093 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 | 2017-08-20 | 0.1 | 7.7469 | 0.77469 | Reduce | 0.1 | 7.7469 | 0.77469 | H3 | 3 | Stable | 0.8 | 82 | 126 | 153 | 123.1667 | 0.1 | 15 | 46 | 65 | 44 | 0 | 0 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK009 | Project_048_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Supplier Performance | Person_261 | 2017-02-20 01:00 | 2020-05-22 | 0.3 | 0.20644 | 0.061932 | Reduce | 0.3 | 0.72254 | 0.21676 | H2 | 4 | Stable | 0.9 | 106 | 123 | 144 | 123.6667 | 0.1 | 35 | 55 | 67 | 53.6667 | -250 | 0 | 0 | -150
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK017 | Project_048_RISK017 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Increased build rate | Person_683 | 2017-11-12 01:00 | 2019-08-21 01:00 | 0.5 | 7.7433 | 3.8716 | -- | 0.5 | 7.7433 | 3.8716 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK016 | Project_048_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.2 | 0.22605 | 0.045211 | -- | 0.1 | 0.22605 | 0.022605 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK018 | Project_048_RISK018 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Line Closure | Person_683 | 2019-08-21 01:00 | 2019-11-20 01:00 | 0.5 | 0.68298 | 0.34149 | -- | 0.5 | 1.5483 | 0.77415 | H2 | 4 | Improving | [10 empty] | -126.7001 | 0 | 0 | -76.0201
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | FOC Acceptance | Person_499 | 2015-11-21 01:00 | 2018-02-18 01:00 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.15 | 8.471 | 1.2706 | H3 | 3 | Stable | 0.9 | 105 | 125 | 145 | 125 | 0.3 | 34 | 41 | 77 | 45.8333 | -99.9999 | 57.1429 | 1 | -58.2857
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software issue input | Person_279 | 2016-11-23 01:00 | 2023-02-20 01:00 | 0.4 | 49.4398 | 19.7759 | Reduce | 0.2 | 49.4398 | 9.888 | H2 | 4 | Stable | 0.8 | 108 | 122 | 144 | 123.3333 | 0.2 | 20 | 59 | 76 | 55.3333 | 0 | 50 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-117 | Project_043_Risk-117 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Supplier Technical Publications maturity not at the level required | Person_769 | 2017-04-19 | 2018-05-13 | 0.2 | 0.21458 | 0.042916 | Reduce | 0.2 | 0.21458 | 0.042916 | H2 | 4 | Improving | 0.8 | 118 | 140 | 154 | 138.6667 | 0.3 | 36 | 41 | 71 | 45.1667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-111 | Project_043_Risk-111 | Opportunitity | Project Contingency | Open | H1 | 5 | 7. Finance | Decrease the cost of obsolescence sweeps | Person_769 | 2018-01-11 01:00 | 2020-12-21 01:00 | 0.5 | 0.038325 | 0.019162 | Exploit | 0.5 | 0.038325 | 0.019162 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-113 | Project_043_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | No Gen 1 products available, transition cost to Gen 2 | Person_769 | 2017-04-19 | 2020-12-21 01:00 | 0.2 | 0.59882 | 0.11976 | Reduce | 0.2 | 0.59882 | 0.11976 | H2 | 4 | Stable | 0.7 | 87 | 135 | 144 | 128.5 | 0.3 | 30 | 44 | 62 | 44.6667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-121 | Project_043_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | More Tech Pubs Update than estimated | Person_769 | 2019-01-21 01:00 | 2020-10-20 01:00 | 0.25 | 0.32576 | 0.08144 | Reduce | 0.2 | 0.32576 | 0.065152 | H2 | 4 | Stable | 0.6 | 86 | 134 | 155 | 129.5 | 0.4 | 22 | 43 | 72 | 44.3333 | 0 | 20 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-084 | Project_043_Risk-084 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | complex repair ( over and above the forecast average) | Person_368 | 2017-12-21 01:00 | 2020-12-21 01:00 | 0.2 | 0.51898 | 0.1038 | Reduce | 0.2 | 0.51898 | 0.1038 | H2 | 4 | Stable | 0.6 | 85 | 136 | 148 | 129.5 | 0.2 | 1 | 53 | 60 | 45.5 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-128 | Project_043_Risk-128 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Reliance of Customer Avaliability | Person_135 | 2017-04-19 | 2018-08-21 | 0.5 | 0.83036 | 0.41518 | Reduce | 0.25 | 0.41418 | 0.10355 | H2 | 4 | Stable | 0.8 | 84 | 123 | 142 | 119.6667 | 0.2 | 37 | 43 | 65 | 45.6667 | 50.1202 | 50 | 0 | 30.0721
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-089 | Project_043_Risk-089 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares pool is limited | Person_307 | 2018-12-22 01:00 | 2020-12-21 01:00 | 0.25 | 1.018 | 0.2545 | Reduce | 0.25 | 0.57886 | 0.14472 | H2 | 4 | Stable | 0.6 | 86 | 130 | 152 | 126.3333 | 0.3 | 31 | 50 | 61 | 48.6667 | 43.1373 | 0 | 0 | 25.8824
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-001 | Project_043_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Training Programme capacity | Person_336 | 2017-04-28 | 2018-11-20 01:00 | 0.15 | 0 | 0 | Reduce | 0.05 | 0 | 0 | H3 | 3 | Improving | 0.6 | 98 | 132 | 156 | 130.3333 | 0.4 | 31 | 57 | 79 | 56.3333 |  | 66.6667 | 1
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-039 | Project_043_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System fails to achieve required performance | Person_051 | 2017-04-19 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H2 | 4 | Stable | 0.5 | 93 | 124 | 147 | 122.6667 | 0.1 | 28 | 59 | 70 | 55.6667 |  | 66.6667 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK003 | Project_044_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Mono vs stereo Component | Person_358 | 2016-03-23 | 2018-10-22 01:00 | 0.7 | 14.4876 | 10.1413 | Reduce | 0.5 | 14.4876 | 7.2438 | H2 | 4 | Improving | 0.8 | 82 | 133 | 154 | 128 | 0.4 | 13 | 59 | 65 | 52.3333 | 0 | 28.5714 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK008 | Project_044_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Skills | Person_505 | 2017-10-21 01:00 | 2018-10-22 01:00 | 0.3 | 1.5695 | 0.47085 | Reduce | 0.3 | 1.4488 | 0.43463 | H2 | 4 | Stable | 0.9 | 99 | 130 | 153 | 128.6667 | 0.2 | 7 | 45 | 78 | 44.1667 | 7.6924 | 0 | 0 | 4.6155
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 18:00 | 2019-08-07 | 0.61 | 8.2789 | 2.4837 | Accept | 0.61 | 8.2789 | 2.4837 | H1 | 5 | Stable | 0.7 | 96 | 129 | 148 | 126.6667 | 0.7 | 96 | 129 | 148 | 126.6667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_009 | Project_051 | RISK001 | Project_051_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Generic Labour or Material Overspend | Person_577 | 2012-05-23 | 2021-05-22 | 0.5 | 27.1644 | 0.81493 | Accept | 0.5 | 12.8336 | 0.38501 | H3 | 3 | Stable | 0.6 | 114 | 124 | 142 | 125.3333 | 0.6 | 114 | 124 | 142 | 125.3333 | 52.7559 | 0 | 0 | 31.6535
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2018-03-22 | 2019-07-21 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.9 | 111 | 139 | 145 | 135.3333 | 0.2 | 25 | 54 | 62 | 50.5 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2018-03-16 01:00 | 0.1 | 6.4168 | 0.64168 | Transfer | 0.1 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sub-system FPGA | Person_332 | 2017-01-21 01:00 | 2018-09-20 01:00 | 0.4 | 1.5914 | 0.63655 | Reduce | 0.2 | 1.5914 | 0.31827 | H3 | 3 | Stable | 0.9 | 84 | 128 | 147 | 123.8333 | 0.3 | 10 | 52 | 71 | 48.1667 | 0 | 50 | 1 | 1.5
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort for System HW/SW- System upgrade. | Person_199 | 2017-05-23 | 2019-09-18 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.2 | 2.5667 | 0.51334 | H3 | 3 | Stable | 0.7 | 84 | 136 | 153 | 130.1667 | 0.2 | 4 | 56 | 71 | 49.8333 | 0 | 33.3333 | 1 | 1
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs | Person_372 | 2018-04-22 | 2018-08-22 01:00 | 0.5 | 6.6521 | 3.326 | Reduce | 0.5 | 6.6521 | 3.326 | H2 | 4 | Stable | 0.8 | 89 | 123 | 141 | 120.3333 | 0.3 | 1 | 53 | 78 | 48.5 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.5 | 3.5934 | 1.7967 | H2 | 4 | Stable | 0.5 | 101 | 124 | 155 | 125.3333 | 0.3 | 37 | 57 | 72 | 56.1667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-20 22:00 | 2019-08-20 | 0.5 | 3.3367 | 1.3347 | Accept | 0.5 | 3.3367 | 1.3347 | H2 | 4 | Stable | 0.5 | 82 | 139 | 154 | 132 | 0.5 | 82 | 139 | 154 | 132 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 4.2779 | 1.0695 | Accept | 0.5 | 4.2779 | 1.0695 | H2 | 4 | Stable | 0.5 | 117 | 127 | 141 | 127.6667 | 0.5 | 117 | 127 | 141 | 127.6667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 | 2020-08-20 | 0.5 | 2.5667 | 0.77001 | Accept | 0.5 | 2.5667 | 0.51334 | H2 | 4 | Stable | 0.6 | 98 | 123 | 142 | 122 | 0.6 | 98 | 123 | 142 | 122 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.2 | 2.6951 | 0.53901 | Accept | 0.2 | 2.6951 | 0.53901 | H3 | 3 | Stable | 0.8 | 105 | 121 | 159 | 124.6667 | 0.8 | 105 | 121 | 159 | 124.6667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Minimum Order Quantities | Person_372 | 2017-11-20 01:00 | 2018-05-15 | 0.2 | 1.925 | 0.38501 | Exploit | 0.2 | 1.925 | 0.38501 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_372 | 2018-04-22 | 2018-08-22 01:00 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Worsening | 0.6 | 111 | 138 | 157 | 136.6667 | 0.1 | 16 | 58 | 66 | 52.3333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_585 | 2017-10-21 01:00 | 2019-07-21 | 0.333 | 11.5502 | 3.8462 | Reduce | 0.333 | 11.5502 | 3.8462 | H2 | 4 | Stable | 0.5 | 100 | 132 | 158 | 131 | 0.1 | 27 | 50 | 65 | 48.6667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) at the System level on product platform - performed by 3rd parties | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Sub-system / product system accreditation hindered by Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.1 | 0.25667 | 0.025667 | Transfer | 0.1 | 0.25667 | 0.025667 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 1.4673 | 0.58692 | Reduce | 0.3 | 1.4673 | 0.44019 | H2 | 4 | Improving | 0.9 | 91 | 140 | 155 | 134.3333 | 0.2 | 23 | 56 | 65 | 52 | 0 | 25 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2018-03-21 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2018-01-19 01:00 | 0.3 | 0.89835 | 0.26951 | Transfer | 0.3 | 0.89835 | 0.26951 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 0.35 | 1.9208 | 0.67227 | Reduce | 0.25 | 1.9208 | 0.48019 | H2 | 4 | Stable | 0.5 | 99 | 122 | 144 | 121.8333 | 0.4 | 18 | 44 | 71 | 44.1667 | 0 | 28.5714 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2018-03-22 | 2018-10-18 01:00 | 0.4 | 0.77001 | 0.30801 | Reduce | 0.3 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.6 | 109 | 125 | 146 | 125.8333 | 0.1 | 21 | 57 | 74 | 53.8333 | 0 | 25 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2018-02-20 01:00 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.9 | 120 | 131 | 148 | 132 | 0.4 | 8 | 40 | 69 | 39.5 | 0 | 28.5714 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 1.54 | 0.30801 | Accept | 0.35 | 0.77001 | 0.154 | H3 | 3 | Stable | 0.8 | 103 | 138 | 142 | 132.8333 | 0.8 | 103 | 138 | 142 | 132.8333 | 50 | 0 | 0 | 30
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.25 | 0.94968 | 0.28491 | Accept | 0.25 | 0.94968 | 0.18994 | H3 | 3 | Stable | 0.7 | 81 | 140 | 144 | 130.8333 | 0.7 | 81 | 140 | 144 | 130.8333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 | 0.05 | 1.8788 | 0.46971 | Accept | 0.05 | 1.5031 | 0.22546 | H3 | 3 | Stable | 0.5 | 100 | 127 | 150 | 126.3333 | 0.5 | 100 | 127 | 150 | 126.3333 | 20 | 0 | 1 | 12
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of the platforms for modification | Person_496 | 2014-01-21 01:00 | 2018-02-18 01:00 | 0.67 | 1.8788 | 0.46971 | Accept | 0.67 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.8 | 107 | 139 | 146 | 134.8333 | 0.8 | 107 | 139 | 146 | 134.8333 | 20 | 0 | 0 | 12
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Volume of production tools and Jigs | Person_279 | 2016-11-23 01:00 | 2021-11-23 01:00 | 0.35 | 4.6971 | 0.93941 | Accept | 0.2 | 3.7576 | 0.67638 | H2 | 4 | Stable | 0.6 | 83 | 133 | 141 | 126 | 0.6 | 83 | 133 | 141 | 126 | 20 | 42.8571 | 0 | 12
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK044 | Project_042_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2018-02-20 | 2018-12-21 | 0.32 | 6.5759 | 2.1043 | -- | 0.32 | 6.5759 | 2.1043 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_523 | 2015-01-22 01:00 | 2018-04-21 | 0.35 | 0.56365 | 0.11273 | Accept | 0.2 | 0.28182 | 0.028182 | H2 | 4 | Stable | 0.5 | 120 | 130 | 154 | 132.3333 | 0.5 | 120 | 130 | 154 | 132.3333 | 50 | 42.8571 | 0 | 30
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_332 | 2016-06-23 | 2018-02-02 01:00 | 0.4 | 4.6971 | 0.93941 | Accept | 0.2 | 3.7576 | 0.67638 | H2 | 4 | Stable | 0.5 | 90 | 123 | 159 | 123.5 | 0.5 | 90 | 123 | 159 | 123.5 | 20 | 50 | 0 | 12
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK045 | Project_042_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2019-01-22 | 2019-05-23 | 0.25 | 3.908 | 0.97699 | -- | 0.25 | 3.908 | 0.97699 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-085 | Project_043_Risk-085 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Failure of a product pre delivery | Person_359 | 2017-04-19 | 2018-04-21 | 0.05 | 1.8788 | 0.37576 | Accept | 0.05 | 1.4091 | 0.21137 | H2 | 4 | Improving | 0.7 | 84 | 140 | 151 | 132.5 | 0.7 | 84 | 140 | 151 | 132.5 | 25 | 0 | 0 | 15
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 1.8788 | 0.18788 | Accept | 0.03 | 0.79775 | 0.039887 | H3 | 3 | Stable | 0.8 | 119 | 139 | 141 | 136 | 0.8 | 119 | 139 | 141 | 136 | 57.54 | 0 | 0 | 34.524
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | HW - additional unplanned design effort | Person_332 | 2016-05-23 | 2018-03-23 | 0.4 | 10.3335 | 1.0334 | Accept | 0.4 | 10.3335 | 1.0334 | H2 | 4 | Stable | 0.8 | 118 | 122 | 141 | 124.5 | 0.8 | 118 | 122 | 141 | 124.5 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 11.2729 | 2.2546 | Accept | 0.25 | 11.2729 | 2.2546 | H2 | 4 | Stable | 0.5 | 99 | 135 | 151 | 131.6667 | 0.5 | 99 | 135 | 151 | 131.6667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 3.7576 | 0.18788 | Accept | 0.2 | 3.7576 | 0.56365 | H3 | 3 | Stable | 0.5 | 84 | 130 | 154 | 126.3333 | 0.5 | 84 | 130 | 154 | 126.3333 | 0 | 33.3333 | 1 | 1
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design [in addition to costed effort] | Person_332 | 2017-05-28 | 2018-11-30 01:00 | 0.2 | 7.2784 | 2.1835 | Accept | 0.2 | 7.2784 | 2.1835 | H3 | 3 | Improving | 0.5 | 93 | 131 | 150 | 127.8333 | 0.5 | 93 | 131 | 150 | 127.8333 | 0 | 0 | 1 | 0
2017-11-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-002 | Project_052_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Schedule slippage due to infeed of critical hardware | Person_376 | 2017-08-19 | 2018-02-19 | 0.5 | 3.2555 | 1.6277 | Reduce | 0.5 | 3.2555 | 1.6277 | H3 | 3 | Stable | 0.7 | 119 | 125 | 146 | 127.5 | 0.4 | 9 | 50 | 62 | 45.1667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2020-09-19 01:00 | 0.2 | 3.0869 | 0.61737 | Accept | 0.2 | 3.0869 | 0.61737 | H3 | 3 | Stable | 0.9 | 94 | 124 | 148 | 123 | 0.9 | 94 | 124 | 148 | 123 | 0 | 0 | 0 | 0
2017-11-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-016 | Project_052_Risk-016 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Environmental conditions | Person_651 | 2017-08-19 | 2018-02-19 | 0.2 | 13.8182 | 2.7636 | Transfer | 0.2 | 13.8182 | 2.7636 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2019-07-21 | 0.3 | 4.6565 | 1.3969 | Accept | 0.2 | 4.6565 | 1.3969 | H3 | 3 | Stable | 0.9 | 89 | 126 | 145 | 123 | 0.9 | 89 | 126 | 145 | 123 | 0 | 33.3333 | 1 | 1
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK026 | Project_042_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st Jan to 31st March | Person_455 | 2020-05-23 | 2020-08-20 | 0.25 | 9.5749 | 2.8725 | Accept | 0.15 | 9.5749 | 2.8725 | H2 | 4 | Stable | 0.7 | 90 | 136 | 148 | 130.3333 | 0.7 | 90 | 136 | 148 | 130.3333 | 0 | 40 | 0 | 0
2017-11-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-010 | Project_052_Risk-010 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Potential update of software / hardware required during the 3 year support period (RESOURCE) | Person_376 | 2017-08-19 | 2018-02-19 | 0.3 | 3.1214 | 0.93642 | Transfer | 0.3 | 3.1184 | 0.93551 | H3 | 3 | Stable | [10 empty] | 0.09816 | 0 | 0 | 0.058896
2017-11-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-012 | Project_052_Risk-012 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Issues from Supplier affect product | Person_651 | 2017-08-19 | 2020-08-19 | 0.3 | 5.1992 | 1.5598 | -- | 0.3 | 5.1972 | 1.5591 | H3 | 3 | Stable | [10 empty] | 0.038674 | 0 | 0 | 0.023204
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK047 | Project_042_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables | Person_455 | 2020-11-20 | 2021-05-22 | 0.2 | 7.1379 | 2.1414 | Accept | 0.1 | 7.1379 | 2.1414 | H2 | 4 | Stable | 0.6 | 112 | 138 | 159 | 137.1667 | 0.6 | 112 | 138 | 159 | 137.1667 | 0 | 50 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK028 | Project_042_RISK028 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st July to 30th September | Person_455 | 2020-11-20 | 2021-02-19 | 0.25 | 8.4929 | 2.5479 | Accept | 0.15 | 8.4929 | 2.5479 | H2 | 4 | Stable | 0.7 | 92 | 135 | 148 | 130 | 0.7 | 92 | 135 | 148 | 130 | 0 | 40 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK027 | Project_042_RISK027 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st April to 30th June | Person_455 | 2020-08-21 | 2020-09-19 | 0.25 | 10.2724 | 2.0545 | Accept | 0.15 | 10.2724 | 2.0545 | H2 | 4 | Stable | 0.5 | 85 | 136 | 157 | 131 | 0.5 | 85 | 136 | 157 | 131 | 0 | 40 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK022 | Project_042_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2017-09-20 | 2018-09-20 | 0.2 | 15.8357 | 3.1671 | Accept | 0.18 | 15.8357 | 3.1671 | H2 | 4 | Stable | 0.9 | 104 | 130 | 152 | 129.3333 | 0.9 | 104 | 130 | 152 | 129.3333 | 0 | 10 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK043 | Project_042_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st December | Person_455 | 2021-03-23 | 2021-05-22 | 0.1 | 8.5887 | 2.5766 | Accept | 0.08 | 8.5887 | 2.5766 | H3 | 3 | Stable | 0.8 | 102 | 126 | 151 | 126.1667 | 0.8 | 102 | 126 | 151 | 126.1667 | 0 | 20 | 1 | 0.6
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2018-05-22 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.9 | 87 | 126 | 143 | 122.3333 | 0.1 | 7 | 42 | 68 | 40.5 | 0 | 40 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK024 | Project_042_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2019-09-21 | 2020-09-19 | 0.33 | 11.0894 | 0.55447 | Accept | 0.3 | 11.0894 | 0.55447 | H2 | 4 | Stable | 0.9 | 86 | 139 | 157 | 133.1667 | 0.9 | 86 | 139 | 157 | 133.1667 | 0 | 9.0909 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 0.92411 | 0.55447 | Reduce | 0.5 | 0.36965 | 0.18482 | H2 | 4 | Stable | 0.6 | 103 | 129 | 152 | 128.5 | 0.1 | 1 | 42 | 66 | 39.1667 | 60 | 16.6667 | 0 | 36
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 01:00 | 2018-04-21 | 0.2 | 4.0661 | 0.81322 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.9 | 117 | 126 | 157 | 129.6667 | 0.4 | 31 | 44 | 73 | 46.6667 | 0 | 75 | 1 | 2.25
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.5 | 0.46206 | 0.23103 | H1 | 5 | Stable | 0.8 | 93 | 121 | 149 | 121 | 0.4 | 29 | 48 | 76 | 49.5 | 58.3333 | 16.6667 | 0 | 35
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK046 | Project_042_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables - June | Person_455 | 2018-11-21 | 2020-11-19 | 0.2 | 1.1089 | 0.88715 | Accept | 0.1 | 0.73929 | 0.44357 | H2 | 4 | Stable | 0.9 | 109 | 122 | 160 | 126.1667 | 0.9 | 109 | 122 | 160 | 126.1667 | 33.3333 | 50 | 0 | 20
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 01:00 | 2018-05-22 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.9 | 119 | 129 | 159 | 132.3333 | 0.4 | 30 | 41 | 73 | 44.5 | 0 | 50 | 1 | 1.5
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2018-05-22 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.5 | 114 | 124 | 154 | 127.3333 | 0.3 | 18 | 49 | 66 | 46.6667 | 0 | 25 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_693 | 2012-06-01 | 2018-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Improving | 0.7 | 94 | 126 | 143 | 123.5 | 0.2 | 37 | 41 | 70 | 45.1667 | 0 | 40 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2018-05-21 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Stable | [10 empty] | 0 | 37.5 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK023 | Project_042_RISK023 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2018-09-21 | 2019-09-20 | 0.2 | 3.6965 | 0.36965 | Accept | 0.18 | 3.6965 | 0.36965 | H2 | 4 | Stable | 0.7 | 92 | 137 | 148 | 131.3333 | 0.7 | 92 | 137 | 148 | 131.3333 | 0 | 10 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK029 | Project_042_RISK029 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st October to 31st December | Person_455 | 2021-02-20 | 2021-05-22 | 0.25 | 0.92411 | 0.18482 | Accept | 0.1 | 0.92411 | 0.18482 | H2 | 4 | Stable | 0.6 | 93 | 127 | 147 | 124.6667 | 0.6 | 93 | 127 | 147 | 124.6667 | 0 | 60 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK031 | Project_042_RISK031 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours 1st July to 30th September | Person_455 | 2020-11-19 | 2021-02-19 | 0.2 | 1.8482 | 0.55447 | Accept | 0.15 | 1.8482 | 0.36965 | H2 | 4 | Stable | 0.5 | 84 | 126 | 147 | 122.5 | 0.5 | 84 | 126 | 147 | 122.5 | 0 | 25 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2018-02-19 01:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.5 | 103 | 131 | 150 | 129.5 | 0.2 | 21 | 53 | 68 | 50.1667 | 90 | 75 | 1 | 56.25
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK030 | Project_042_RISK030 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours 31st March to 29 June | Person_455 | 2020-08-20 | 2020-11-18 | 0.2 | 17.0765 | 1.7076 | Accept | 0.15 | 17.0765 | 1.7076 | H2 | 4 | Stable | 0.7 | 99 | 132 | 141 | 128 | 0.7 | 99 | 132 | 141 | 128 | 0 | 25 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK037 | Project_042_RISK037 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 1 | Person_455 | 2020-05-23 | 2021-05-22 | 0.14 | 186.9553 | 59.2026 | Accept | 0.11 | 186.9553 | 1.3939 | H2 | 4 | Stable | 0.6 | 111 | 136 | 153 | 134.6667 | 0.6 | 111 | 136 | 153 | 134.6667 | 0 | 21.4286 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK036 | Project_042_RISK036 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 2 | Person_455 | 2019-05-24 | 2020-05-22 | 0.25 | 22.8501 | 6.855 | Accept | 0.2 | 22.8501 | 6.855 | H2 | 4 | Stable | 0.6 | 92 | 135 | 149 | 130.1667 | 0.6 | 92 | 135 | 149 | 130.1667 | 0 | 20 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Additional minor point releases | Person_228 | 2016-05-23 | 2018-05-21 | 0.5 | 11.9444 | 5.9722 | Reduce | 0.25 | 11.9444 | 2.9861 | H2 | 4 | Stable | 0.8 | 101 | 133 | 143 | 129.3333 | 0.4 | 6 | 47 | 60 | 42.3333 | 0 | 50 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_228 | 2016-05-23 | 2018-04-21 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.8 | 113 | 140 | 153 | 137.6667 | 0.4 | 35 | 43 | 75 | 47 | 0 | 50 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_004 | 2015-11-21 01:00 | 2018-11-20 01:00 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.9 | 93 | 140 | 157 | 135 | 0.1 | 25 | 47 | 69 | 47 | 0 | 5 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.8 | 2.8043 | 2.2435 | Reduce | 0.45 | 2.8043 | 1.2619 | H1 | 5 | Stable | 0.7 | 98 | 129 | 141 | 125.8333 | 0.2 | 31 | 47 | 64 | 47.1667 | 0 | 43.75 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK167 | Project_024_RISK167 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Customer not providing the information needed or Customer not accepting the Customer documentation resulting in rewor. | Person_710 | 2016-08-21 01:00 | 2018-02-19 01:00 | 0.5 | 9.971 | 4.9855 | Reduce | 0.3 | 9.971 | 2.9913 | H1 | 5 | Worsening | 0.6 | 112 | 136 | 154 | 135 | 0.2 | 1 | 45 | 69 | 41.6667 | 0 | 40 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK226 | Project_024_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Late Evidences Certification delivery | Person_710 | 2017-04-30 | 2018-04-22 | 0.4 | 3.9468 | 1.5787 | Reduce | 0.2 | 3.9468 | 0.78937 | H2 | 4 | Worsening | 0.6 | 113 | 130 | 144 | 129.5 | 0.4 | 16 | 44 | 61 | 42.1667 | 0 | 50 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK039 | Project_042_RISK039 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality Issues 16th August to 15th August | Person_540 | 2020-01-06 | 2021-01-04 | 0.1 | 35.9673 | 10.7902 | Accept | 0.08 | 35.9673 | 9.7651 | H2 | 4 | Stable | 0.9 | 116 | 130 | 141 | 129.5 | 0.9 | 116 | 130 | 141 | 129.5 | 0 | 20 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK038 | Project_042_RISK038 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality Issues 16th August to 15th August | Person_540 | 2019-01-06 | 2020-01-05 | 0.1 | 3.9728 | 1.3905 | Accept | 0.08 | 3.9728 | 1.3905 | H2 | 4 | Stable | 0.8 | 119 | 126 | 142 | 127.5 | 0.8 | 119 | 126 | 142 | 127.5 | 0 | 20 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.7 | 104 | 136 | 153 | 133.5 | 0.4 | 38 | 57 | 63 | 54.8333 | 0 | 60 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis and Security | Person_288 | 2017-02-22 01:00 | 2018-05-21 | 0.3 | 19.9938 | 5.9981 | Reduce | 0.04675 | 19.9938 | 0.93471 | H3 | 3 | Improving | 0.8 | 92 | 122 | 159 | 123.1667 | 0.2 | 24 | 42 | 65 | 42.8333 | 0 | 84.4167 | 1 | 2.5325
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.2 | 3.843 | 0.76859 | H2 | 4 | Stable | 0.8 | 88 | 124 | 155 | 123.1667 | 0.4 | 31 | 47 | 64 | 47.1667 | 0 | 60 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Performance (collector opportunity) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.3814 | 26.127 | 9.9648 | -- | 0.4132 | 26.127 | 10.7957 | H1 | 5 | Stable | [10 empty] | 0 | -8.3377 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.3 | 20.8767 | 6.263 | H1 | 5 | Stable | 0.9 | 118 | 128 | 146 | 129.3333 | 0.1 | 34 | 50 | 74 | 51.3333 | 50 | 25 | 0 | 30
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.51 | 70.438 | 35.9234 | Reduce | 0.29565 | 50.8467 | 15.0328 | H2 | 4 | Worsening | 0.7 | 115 | 139 | 152 | 137.1667 | 0.4 | 8 | 46 | 64 | 42.6667 | 27.8136 | 42.0294 | 0 | 16.6882
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK308 | Project_024_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System robustness and resilience | Person_774 | 2017-04-06 | 2018-06-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.1 | 2.5966 | 0.25966 | H3 | 3 | Stable | 0.8 | 114 | 132 | 152 | 132.3333 | 0.2 | 19 | 47 | 64 | 45.1667 | 58.3333 | 66.6667 | 1 | 37
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK033 | Project_042_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st April to 30 June | Person_455 | 2019-08-22 | 2019-11-20 | 0.2 | 3.922 | 0.98049 | Accept | 0.15 | 3.922 | 0.98049 | H2 | 4 | Stable | 0.7 | 88 | 121 | 147 | 119.8333 | 0.7 | 88 | 121 | 147 | 119.8333 | 0 | 25 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-080 | Project_008_Risk-080 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Recovery of Costs | Person_567 | 2016-08-21 01:00 | 2018-01-20 01:00 | 0.5 | 23.6737 | 11.8369 | -- | 0.5 | 23.6737 | 11.8369 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK032 | Project_042_RISK032 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours 1st October to 31st December | Person_455 | 2021-02-20 | 2021-05-22 | 0.2 | 49.7149 | 22.3717 | Accept | 0.15 | 49.7149 | 22.3717 | H2 | 4 | Stable | 0.5 | 89 | 139 | 149 | 132.3333 | 0.5 | 89 | 139 | 149 | 132.3333 | 0 | 25 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Survey costs | Person_618 | 2016-04-22 | 2018-01-20 01:00 | 0.2 | 13.2573 | 2.6515 | Avoid | 0.2 | 13.2573 | 2.6515 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-079 | Project_008_Risk-079 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Regulations Phase 3 and 4 | Person_567 | 2016-10-21 01:00 | 2018-08-21 | 0.25 | 71.9682 | 17.992 | -- | 0.25 | 71.9682 | 17.992 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK035 | Project_042_RISK035 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st October to 31st December | Person_455 | 2021-02-20 | 2021-05-22 | 0.2 | 33.9324 | 10.1797 | Accept | 0.15 | 33.9324 | 10.1797 | H2 | 4 | Stable | 0.6 | 98 | 136 | 150 | 132 | 0.6 | 98 | 136 | 150 | 132 | 0 | 25 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK034 | Project_042_RISK034 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st July to 30 September | Person_455 | 2020-11-20 | 2021-02-19 | 0.2 | 14.0464 | 4.2139 | Accept | 0.15 | 14.0464 | 4.2139 | H2 | 4 | Stable | 0.7 | 112 | 124 | 151 | 126.5 | 0.7 | 112 | 124 | 151 | 126.5 | 0 | 25 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK040 | Project_042_RISK040 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st May to 30 Oct | Person_455 | 2019-09-21 | 2020-03-21 | 0.1 | 9.4695 | 4.7347 | Accept | 0.07 | 9.4695 | 4.7347 | H2 | 4 | Stable | 0.9 | 100 | 123 | 146 | 123 | 0.9 | 100 | 123 | 146 | 123 | 0 | 30 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK042 | Project_042_RISK042 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st February to 14th July | Person_455 | 2020-06-23 | 2020-12-03 | 0.1 | 15.8141 | 3.9535 | Accept | 0.08 | 15.8141 | 3.9535 | H2 | 4 | Stable | 0.5 | 98 | 128 | 155 | 127.5 | 0.5 | 98 | 128 | 155 | 127.5 | 0 | 20 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK041 | Project_042_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st Jan | Person_455 | 2020-03-23 | 2020-06-22 | 0.1 | 0.34776 | 0.069552 | Accept | 0.08 | 0.34776 | 0.069552 | H2 | 4 | Stable | 0.8 | 81 | 138 | 150 | 130.5 | 0.8 | 81 | 138 | 150 | 130.5 | 0 | 20 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2018-04-21 | 0.15 | 0.58983 | 0.088474 | -- | 0.15 | 0.58983 | 0.088474 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 0.2 | 0.62279 | 0.12456 | Avoid | 0.2 | 0.62279 | 0.12456 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2018-03-21 | 0.1 | 0.27503 | 0.027503 | -- | 0.1 | 0.27503 | 0.027503 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 | 2018-08-21 | 0.2 | 1.8854 | 0.37708 | Reduce | 0.2 | 1.8854 | 0.37708 | H2 | 4 | Stable | 0.9 | 106 | 130 | 152 | 129.6667 | 0.3 | 19 | 56 | 76 | 53.1667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2017-10-21 | 2018-08-21 | 0.4 | 1.4138 | 0.56551 | Reduce | 0.4 | 1.4138 | 0.56551 | H2 | 4 | Stable | 0.9 | 88 | 132 | 156 | 128.6667 | 0.2 | 34 | 43 | 60 | 44.3333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Local customer Engineers in country | Person_455 | 2019-03-22 | 2019-05-23 | 0.1 | 0.18354 | 0.045885 | Accept | 0.05 | 0.18354 | 0.045885 | H2 | 4 | Stable | 0.5 | 114 | 135 | 141 | 132.5 | 0.5 | 114 | 135 | 141 | 132.5 | 0 | 50 | 0 | 0
2017-11-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-013 | Project_052_Risk-013 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Additional material and effort required to support the delta equipment | Person_376 | 2017-08-19 | 2018-02-19 | 0.3 | 0.11081 | 0.011081 | Accept | 0.3 | 0.11081 | 0.011081 | H3 | 3 | Stable | 0.9 | 100 | 138 | 159 | 135.1667 | 0.9 | 100 | 138 | 159 | 135.1667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-10-19 | 2018-08-21 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.5 | 110 | 129 | 146 | 128.6667 | 0.2 | 2 | 49 | 69 | 44.5 |  | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Pick up and Drop off of Software Resource | Person_230 | 2018-04-21 | 2018-07-18 | 0.4 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 0.4 | 0.19206 | 0.076826 | -- | 0.4 | 0.19206 | 0.076826 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 0.4 | 0.58017 | 0.23207 | Avoid | 0.4 | 0.58017 | 0.23207 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-004 | Project_052_Risk-004 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Installation Risk for Phase 1a and 1b | Person_488 | 2017-08-19 | 2018-02-19 | 0.2 | 0.49834 | 0.12459 | Accept | 0.2 | 0.49834 | 0.12459 | H3 | 3 | Stable | 0.6 | 112 | 129 | 159 | 131.1667 | 0.6 | 112 | 129 | 159 | 131.1667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.2 | 0.11365 | 0.022729 | -- | 0.2 | 0.11365 | 0.022729 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 0.55 | 0.32389 | 0.17814 | Reduce | 0.55 | 0.32389 | 0.17814 | H1 | 5 | Stable | 0.9 | 80 | 140 | 151 | 131.8333 | 0.1 | 39 | 55 | 61 | 53.3333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test/SAT | Person_182 | 2017-10-21 | 2018-05-21 | 0.4 | 0.19206 | 0.076826 | -- | 0.4 | 0.19206 | 0.076826 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 0.3 | 0.11933 | 0.035799 | -- | 0.3 | 0.022161 | 0.0066484 | H3 | 3 | Stable | [10 empty] | 81.4286 | 0 | 0 | 48.8571
2017-11-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-005 | Project_052_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Potential update of software / hardware required during the 3 year support period | Person_488 | 2017-08-19 | 2018-02-19 | 0.3 | 1.1416 | 0.68495 | Accept | 0.3 | 1.1416 | 0.68495 | H3 | 3 | Stable | 0.8 | 89 | 121 | 150 | 120.5 | 0.8 | 89 | 121 | 150 | 120.5 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-117 | Project_011_Risk-117 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Avaliability for testing/reviews | Person_147 | 2016-07-21 | 2018-08-21 | 0.35 | 0 | 0 | Avoid | 0.35 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-128 | Project_011_Risk-128 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Different maps needed post Qualification baseline | Person_147 | 2017-04-22 | 2018-01-21 | 0.5 | 0.05688 | 0.02844 | Transfer | 0.5 | 0.05688 | 0.02844 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-129 | Project_011_Risk-129 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Signature of Work Authorisation documents | Person_182 | 2017-05-24 | 2018-01-21 | 0.2 | 0.12643 | 0.025287 | -- | 0.2 | 0.12643 | 0.025287 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-130 | Project_011_Risk-130 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer does not accept Voice Pronounciation | Person_187 | 2017-05-24 | 2018-02-19 | 0.4 | 0 | 0 | Avoid | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_016 | Project_061 | RISK003 | Project_061_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Test equipment reliability | Person_104 | 2017-05-23 | 2020-11-19 01:00 | 0.4 | 0.11013 | 0.044051 | Reduce | 0.3 | 0.11013 | 0.033038 | H2 | 4 | Stable | 0.8 | 85 | 127 | 149 | 123.6667 | 0.2 | 33 | 46 | 74 | 48.5 | 0 | 25 | 0 | 0
2017-11-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-020 | Project_052_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Material escalation - | Person_376 | 2017-08-19 | 2018-02-19 | 0.3 | 0 | 0 | Accept | 0.3 | 0 | 0 | H3 | 3 | Stable | 0.9 | 87 | 137 | 157 | 132 | 0.9 | 87 | 137 | 157 | 132 |  | 0 | 0
2017-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-04-20 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.8 | 109 | 135 | 141 | 131.6667 | 0.2 | 27 | 46 | 74 | 47.5 | 0 | 25 | 0 | 0
2017-11-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-001 | Project_052_Risk-001 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Greater modification than expected for system uplift | Person_376 | 2017-08-19 | 2018-02-19 | 0.3 | 5.596 | 0.2798 | Accept | 0.3 | 5.596 | 0.2798 | H3 | 3 | Stable | 0.9 | 91 | 138 | 146 | 131.5 | 0.9 | 91 | 138 | 146 | 131.5 | 0 | 0 | 0 | 0
2017-11-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-006 | Project_052_Risk-006 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Acceptance failures | Person_488 | 2017-08-19 | 2018-02-19 | 0.3 | 0 | 0 | Accept | 0.3 | 0 | 0 | H3 | 3 | Stable | 0.6 | 107 | 124 | 158 | 126.8333 | 0.6 | 107 | 124 | 158 | 126.8333 |  | 0 | 0
2017-11-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-018 | Project_052_Risk-018 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Support - spares availability | Person_156 | 2017-08-19 | 2018-02-19 | 0.2 | 0.5596 | 0.05596 | Accept | 0.2 | 0.5596 | 0.05596 | H3 | 3 | Stable | 0.8 | 101 | 137 | 157 | 134.3333 | 0.8 | 101 | 137 | 157 | 134.3333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-019 | Project_052_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Additional Design effort required | Person_488 | 2017-08-19 | 2018-02-19 | 0.2 | 2.3503 | 0.47006 | Accept | 0.2 | 2.3503 | 0.47006 | H3 | 3 | Stable | 0.5 | 87 | 128 | 144 | 123.8333 | 0.5 | 87 | 128 | 144 | 123.8333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-009 | Project_052_Risk-009 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | System acceptance not costed in line with Customer expectations | Person_651 | 2017-08-19 | 2020-08-19 | 0.3 | 4.4768 | 2.2384 | Accept | 0.3 | 4.4768 | 2.2384 | H3 | 3 | Stable | 0.6 | 116 | 122 | 154 | 126.3333 | 0.6 | 116 | 122 | 154 | 126.3333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_077 | 2016-01-22 01:00 | 2018-02-17 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H1 | 5 | Improving | 0.8 | 82 | 128 | 142 | 122.6667 | 0.4 | 14 | 50 | 69 | 47.1667 |  | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.05 | 6.3794 | 1.2759 | Accept | 0.05 | 6.3794 | 1.2759 | H2 | 4 | Stable | 0.8 | 102 | 140 | 159 | 136.8333 | 0.8 | 102 | 140 | 159 | 136.8333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2018-04-22 | 0.8 | 23.5255 | 11.7628 | Accept | 0.6 | 23.5255 | 11.7628 | H1 | 5 | Stable | 0.5 | 104 | 130 | 158 | 130.3333 | 0.5 | 104 | 130 | 158 | 130.3333 | 0 | 25 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 01:00 | 2018-05-22 | 0.1 | 60.4367 | 3.0218 | Accept | 0.1 | 60.4367 | 3.0218 | H2 | 4 | Stable | 0.5 | 89 | 123 | 142 | 120.5 | 0.5 | 89 | 123 | 142 | 120.5 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2018-05-21 | 0.2 | 22.384 | 11.192 | Accept | 0.2 | 22.384 | 11.192 | H3 | 3 | Improving | 0.6 | 109 | 137 | 146 | 133.8333 | 0.6 | 109 | 137 | 146 | 133.8333 | 0 | 0 | 1 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2018-04-22 | 0.3 | 3.772 | 2.6404 | Accept | 0.2 | 3.772 | 2.6404 | H3 | 3 | Stable | 0.9 | 110 | 134 | 145 | 131.8333 | 0.9 | 110 | 134 | 145 | 131.8333 | 0 | 33.3333 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2017-02-20 01:00 | 2018-05-22 | 0.1 | 5.8198 | 4.0739 | Accept | 0.1 | 5.8198 | 4.0739 | H3 | 3 | Stable | 0.6 | 86 | 124 | 150 | 122 | 0.6 | 86 | 124 | 150 | 122 | 0 | 0 | 1 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK003 | Project_024_RISK003 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance | Person_288 | 2017-12-21 01:00 | 2018-08-21 | 0.31667 | 1.2549 | 0.12549 | Accept | 0.007456 | 1.2549 | 0.12549 | H2 | 4 | Stable | 0.7 | 98 | 128 | 142 | 125.3333 | 0.7 | 98 | 128 | 142 | 125.3333 | 0 | 97.6455 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-054 | Project_062_Risk-054 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | sub-system rework to reviised standard | Person_277 | 2017-07-21 | 2018-11-21 01:00 | 0.4 | 0.62744 | 0.25098 | Transfer | 0.4 | 0.62744 | 0.25098 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Management Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 0.3 | 4.183 | 1.2549 | Accept | 0.3 | 4.183 | 1.2549 | H1 | 5 | Improving | 0.8 | 80 | 126 | 159 | 123.8333 | 0.8 | 80 | 126 | 159 | 123.8333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-013 | Project_062_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Unavailability of Network | Person_479 | 2017-07-21 | 2018-05-22 | 0.25 | 3.5555 | 0.88888 | Reduce | 0.2 | 3.5555 | 0.7111 | H3 | 3 | Stable | 0.7 | 119 | 124 | 156 | 128.5 | 0.1 | 17 | 57 | 68 | 52.1667 | 0 | 20 | 1 | 0.6
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-055 | Project_062_Risk-055 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Supplier integration and Apps | Person_245 | 2017-07-21 | 2018-11-21 01:00 | 0.5 | 0.83659 | 0.4183 | Reduce | 0.5 | 0.83659 | 0.4183 | H2 | 4 | Stable | 0.7 | 89 | 133 | 147 | 128 | 0.1 | 2 | 42 | 74 | 40.6667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-011 | Project_062_Risk-011 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Variant deviations between SW | Person_479 | 2017-07-21 | 2018-02-17 01:00 | 0.4 | 0.71808 | 0.28723 | Reduce | 0.3 | 0.71808 | 0.21542 | H2 | 4 | Stable | 0.9 | 85 | 125 | 146 | 121.8333 | 0.4 | 16 | 41 | 65 | 40.8333 | 0 | 25 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before part b finished | Person_119 | 2016-10-20 01:00 | 2018-04-21 | 0.3 | 10.4574 | 2.6144 | Accept | 0.2715 | 10.4574 | 2.6144 | H2 | 4 | Worsening | 0.6 | 81 | 122 | 150 | 119.8333 | 0.6 | 81 | 122 | 150 | 119.8333 | 0 | 9.5 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-056 | Project_062_Risk-056 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Supplier integration acceptance by end Customer | Person_031 | 2017-07-21 | 2018-11-21 01:00 | 0.3 | 1.8823 | 0.5647 | Reduce | 0.3 | 1.8823 | 0.5647 | H3 | 3 | Stable | 0.7 | 115 | 123 | 155 | 127 | 0.3 | 21 | 59 | 66 | 53.8333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-039 | Project_062_Risk-039 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Delay of tasks from our / Customer | Person_459 | 2017-07-21 | 2018-04-22 | 0.25 | 0.83659 | 0.20915 | Avoid | 0.15 | 0.83659 | 0.12549 | H3 | 3 | Stable | [10 empty] | 0 | 40 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-017 | Project_062_Risk-017 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer platform Schedule Unknown | Person_459 | 2017-07-21 | 2018-10-22 01:00 | 0.2 | 2.5098 | 0.50196 | Avoid | 0.1 | 2.5098 | 0.25098 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-037 | Project_062_Risk-037 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Server availability | Person_459 | 2017-07-21 | 2018-04-22 | 0.35 | 4.183 | 1.464 | Avoid | 0.1 | 4.183 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 71.4286 | 1 | 2.1429
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-038 | Project_062_Risk-038 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Delay in start of Phase 2 | Person_459 | 2017-07-21 | 2018-02-20 01:00 | 0.2 | 2.0915 | 0.4183 | Avoid | 0.2 | 2.0915 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-016 | Project_062_Risk-016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Supplier Component Unavailability | Person_664 | 2017-07-21 | 2018-05-15 | 0.3 | 2.0927 | 0.62782 | Reduce | 0.2 | 2.0915 | 0.4183 | H3 | 3 | Stable | 0.7 | 88 | 129 | 150 | 125.6667 | 0.1 | 28 | 43 | 73 | 45.5 | 0.059964 | 33.3333 | 0 | 0.035978
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-085 | Project_008_SER-085 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Insufficient LOE to manage the supply chain with reducing number of spares | Person_639 | 2017-04-22 | 2018-08-21 | 0.25 | 1.5477 | 0.15477 | Accept | 0.25 | 1.5477 | 0.15167 | H3 | 3 | Stable | 0.8 | 91 | 125 | 149 | 123.3333 | 0.8 | 91 | 125 | 149 | 123.3333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-050 | Project_062_Risk-050 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SW v1.2 in use on some Hardware | Person_245 | 2017-07-21 | 2018-11-21 01:00 | 0.1 | 4.183 | 0.4183 | Avoid | 0.1 | 4.183 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-020 | Project_062_Risk-020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Security Encryption Solution | Person_245 | 2017-07-21 | 2018-09-20 01:00 | 0.25 | 4.183 | 1.0457 | Reduce | 0.2 | 4.183 | 0.83659 | H2 | 4 | Stable | 0.6 | 115 | 123 | 160 | 127.8333 | 0.2 | 24 | 55 | 79 | 53.8333 | 0 | 20 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-042 | Project_062_Risk-042 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Open source software packages | Person_664 | 2017-07-21 | 2018-04-22 | 0.3 | 1.0457 | 0.31372 | Avoid | 0.2 | 1.0457 | 0.20915 | H3 | 3 | Stable | [10 empty] | 0 | 33.3333 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_567 | 2015-08-22 01:00 | 2018-08-21 | 0.45 | 6.2744 | 1.8823 | Accept | 0.45 | 6.2744 | 1.5686 | H2 | 4 | Worsening | 0.5 | 86 | 123 | 142 | 120 | 0.5 | 86 | 123 | 142 | 120 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-043 | Project_062_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | User response | Person_664 | 2017-07-21 | 2019-02-21 01:00 | 0.35 | 3.3464 | 1.1712 | Avoid | 0.25 | 3.3464 | 0.83659 | H2 | 4 | Stable | [10 empty] | 0 | 28.5714 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-040 | Project_062_Risk-040 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Custom code or open source software | Person_664 | 2017-07-21 | 2018-04-22 | 0.25 | 0.83659 | 0.20915 | Avoid | 0.15 | 0.83659 | 0.12549 | H3 | 3 | Stable | [10 empty] | 0 | 40 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-041 | Project_062_Risk-041 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Incompatible software package versions | Person_664 | 2017-07-21 | 2018-04-22 | 0.3 | 1.0457 | 0.31372 | Avoid | 0.2 | 1.0457 | 0.20915 | H3 | 3 | Stable | [10 empty] | 0 | 33.3333 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-046 | Project_062_Risk-046 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Additional Java licences | Person_245 | 2017-07-21 | 2018-10-22 01:00 | 0.1 | 0.84775 | 0.084775 | Avoid | 0.1 | 0.84775 | 0.084775 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-047 | Project_062_Risk-047 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Redhat6 on PCI shelf | Person_245 | 2017-07-21 | 2018-07-22 | 0.3 | 7.1808 | 2.1542 | Avoid | 0.3 | 7.1808 | 2.1542 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-025 | Project_062_Risk-025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | System Obsolescence Risk | Person_543 | 2017-07-21 | 2018-04-22 | 0.3 | 2.0915 | 0.62744 | Avoid | 0.2 | 2.0915 | 0.4183 | H2 | 4 | Stable | [10 empty] | 0 | 33.3333 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-022 | Project_062_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Registers Might Be Unstable | Person_479 | 2017-07-21 | 2018-04-22 | 0.1 | 0.8589 | 0.08589 | Reduce | 0.1 | 0.8589 | 0.08589 | H3 | 3 | Stable | 0.9 | 114 | 128 | 144 | 128.3333 | 0.2 | 22 | 57 | 75 | 54.1667 | 0 | 0 | 1 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-001 | Project_062_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Supplier servers | Person_664 | 2017-10-21 01:00 | 2018-05-23 | 0.5 | 1.2549 | 0.62744 | Reduce | 0.5 | 1.2549 | 0.62744 | H2 | 4 | Stable | 0.8 | 83 | 133 | 148 | 127.1667 | 0.2 | 2 | 44 | 74 | 42 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-023 | Project_062_Risk-023 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Change In Security Boundary | Person_031 | 2017-07-21 | 2019-02-21 01:00 | 0.3 | 4.6013 | 1.3804 | Reduce | 0.2 | 4.6013 | 0.92025 | H3 | 3 | Stable | 0.6 | 103 | 139 | 148 | 134.5 | 0.2 | 20 | 58 | 74 | 54.3333 | 0 | 33.3333 | 1 | 1
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-026 | Project_062_Risk-026 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Lack of Suitably Qualified and experienced staff availability ILS resource | Person_543 | 2017-07-21 | 2019-02-21 01:00 | 0.3 | 2.0915 | 0.62744 | Reduce | 0.2 | 2.0915 | 0.4183 | H2 | 4 | Stable | 0.5 | 80 | 127 | 156 | 124 | 0.2 | 5 | 57 | 74 | 51.1667 | 0 | 33.3333 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-048 | Project_062_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software lockdown features | Person_245 | 2017-07-21 | 2018-11-21 01:00 | 0.5 | 0.71808 | 0.35904 | Reduce | 0.5 | 0.71808 | 0.35904 | H2 | 4 | Stable | 0.7 | 119 | 135 | 154 | 135.5 | 0.2 | 27 | 58 | 76 | 55.8333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Lack of Spares Availability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 0.3 | 1.9325 | 1.2561 | Accept | 0.3 | 1.9325 | 1.2561 | H3 | 3 | Stable | 0.7 | 81 | 124 | 156 | 122.1667 | 0.7 | 81 | 124 | 156 | 122.1667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-148 | Project_008_SER-148 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Demands but not provisioned | Person_639 | 2018-08-22 01:00 | 2020-08-20 01:00 | 0.3 | 0.5769 | 0.28845 | Accept | 0.3 | 0 | 0 | H3 | 3 | Stable | 0.8 | 94 | 137 | 151 | 132.1667 | 0.8 | 94 | 137 | 151 | 132.1667 | 100 | 0 | 0 | 60
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-094 | Project_008_Risk-094 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Consumable Stock Levels | Person_567 | 2017-04-22 | 2018-08-21 | 0.5 | 0 | 0 | Accept | 0.5 | 0 | 0 | H3 | 3 | Stable | 0.9 | 106 | 132 | 160 | 132.3333 | 0.9 | 106 | 132 | 160 | 132.3333 |  | 0 | 1
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-000 | Project_008_SER-000 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_567 | 2018-05-22 | 2018-08-21 | 0.25 | 1.4422 | 1.0096 | Accept | 0.25 | 1.4422 | 1.0096 | H3 | 3 | Stable | 0.5 | 113 | 125 | 153 | 127.6667 | 0.5 | 113 | 125 | 153 | 127.6667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 0.2 | 0.78457 | 0.39228 | Accept | 0.2 | 0.78457 | 0.39228 | H2 | 4 | Stable | 0.7 | 95 | 139 | 158 | 134.8333 | 0.7 | 95 | 139 | 158 | 134.8333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK004 | Project_063_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 2.861 | 0.57221 | Reduce | 0.15 | 2.861 | 0.42915 | H3 | 3 | Stable | 0.5 | 82 | 133 | 142 | 126 | 0.3 | 38 | 41 | 63 | 44.1667 | 0 | 25 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK003 | Project_063_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Lead Times | Person_261 | 2017-02-20 01:00 | 2020-05-22 | 0.3 | 3.1491 | 0.94472 | Avoid | 0.2 | 3.1491 | 0.62981 | H3 | 3 | Worsening | [10 empty] | 0 | 33.3333 | 1 | 1
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK014 | Project_063_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2020-05-22 | 0.1 | 7.0086 | 0.70086 | -- | 0.05 | 7.0086 | 0.35043 | H3 | 3 | Worsening | [10 empty] | 0 | 50 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK006 | Project_063_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Customer | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0.57605 | 0.11521 | Reduce | 0.15 | 0.57605 | 0.086407 | H3 | 3 | Stable | 0.6 | 100 | 136 | 159 | 133.8333 | 0.4 | 16 | 55 | 74 | 51.6667 | 0 | 25 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK017 | Project_063_RISK017 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Increased build rate | Person_683 | 2017-11-12 01:00 | 2019-08-21 01:00 | 0.5 | 21.6065 | 10.8033 | -- | 0.5 | 21.6065 | 10.8033 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK005 | Project_063_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 1.214 | 0.72839 | -- | 0.5 | 1.214 | 0.60699 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK016 | Project_063_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.2 | 0.63077 | 0.12615 | -- | 0.1 | 0.63077 | 0.063077 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK011 | Project_063_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Line Qualification | Person_270 | 2017-02-20 01:00 | 2019-05-23 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.6 | 84 | 137 | 149 | 130.1667 | 0.4 | 38 | 43 | 78 | 48 |  | 0 | 1
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK002 | Project_063_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2020-05-22 | 0.15 | 0.86407 | 0.12961 | Avoid | 0.15 | 0.86407 | 0.12961 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK001 | Project_063_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Procurement | Person_261 | 2017-02-20 01:00 | 2019-05-23 | 0.3 | 15.5365 | 4.6609 | Reduce | 0.2 | 15.5365 | 3.1073 | H3 | 3 | Stable | 0.7 | 88 | 127 | 141 | 122.8333 | 0.4 | 3 | 44 | 69 | 41.3333 | 0 | 33.3333 | 1 | 1
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK012 | Project_063_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Customer requires additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK008 | Project_063_RISK008 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Oracle | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0.57605 | 0.11521 | Avoid | 0.1 | 0.57605 | 0.057605 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK007 | Project_063_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Staff Availability | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0.18722 | 0.037443 | Avoid | 0.1 | 0.18722 | 0.018722 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK018 | Project_063_RISK018 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Line Closure | Person_683 | 2019-08-21 01:00 | 2019-11-20 01:00 | 0.5 | 1.9058 | 0.95288 | -- | 0.5 | 4.3203 | 2.1602 | H2 | 4 | Improving | [10 empty] | -126.7001 | 0 | 0 | -76.0201
2017-11-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK009 | Project_063_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Supplier Performance | Person_261 | 2017-02-20 01:00 | 2020-05-22 | 0.3 | 0.57605 | 0.17281 | Reduce | 0.3 | 2.0162 | 0.60485 | H2 | 4 | Stable | 0.8 | 105 | 123 | 154 | 125.1667 | 0.2 | 7 | 48 | 72 | 45.1667 | -250 | 0 | 0 | -150
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unforseen and substantial increase in Repairs workload during new build production period. | Person_238 | 2017-10-23 01:00 | 2019-08-21 01:00 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.03 | 1.5434 | 0.046303 | H3 | 3 | Stable | 0.8 | 81 | 130 | 153 | 125.6667 | 0.1 | 15 | 47 | 72 | 45.8333 | 0 | 90 | 1 | 2.7
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK007 | Project_041_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Advanced production of products using a Qual. standard component rather than a Prod. standard | Person_547 | 2017-10-21 01:00 | 2017-12-20 01:00 | 0.49 | 1.2862 | 0.63024 | Reduce | 0.2 | 1.2862 | 0.25724 | H3 | 3 | Stable | 0.6 | 108 | 138 | 144 | 134 | 0.1 | 16 | 58 | 74 | 53.6667 | 0 | 59.1837 | 1 | 1.7755
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_693 | 2017-07-21 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.6 | 112 | 131 | 146 | 130.3333 | 0.4 | 12 | 43 | 65 | 41.5 | 0 | 50 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2017-04-22 | 2018-05-22 | 0.75 | 10.7184 | 8.0388 | Reduce | 0.05 | 2.4052 | 0.12026 | H3 | 3 | Stable | 0.8 | 114 | 139 | 153 | 137.1667 | 0.3 | 35 | 57 | 71 | 55.6667 | 77.56 | 93.3333 | 0 | 46.536
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 0.25 | 1.9722 | 0.98609 | Accept | 0.25 | 1.9722 | 0.98609 | H3 | 3 | Stable | 0.8 | 83 | 134 | 156 | 129.1667 | 0.8 | 83 | 134 | 156 | 129.1667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | More issues during Qualification including additional PRs | Person_147 | 2017-07-26 | 2017-12-17 | 0.6 | 2.5081 | 1.2541 | Accept | 0.6 | 2.5081 | 1.2541 | H1 | 5 | Stable | 0.5 | 105 | 123 | 143 | 123.3333 | 0.5 | 105 | 123 | 143 | 123.3333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment (Second Test Set) | Person_238 | 2017-05-23 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.05 | 0.68598 | 0.034299 | H3 | 3 | Improving | 0.6 | 87 | 127 | 141 | 122.6667 | 0.4 | 8 | 41 | 70 | 40.3333 | 0 | 80 | 1 | 2.4
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2017-05-23 | 2019-08-20 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Stable | 0.5 | 115 | 139 | 151 | 137 | 0.4 | 34 | 48 | 61 | 47.8333 | 0 | 60 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_238 | 2017-04-22 | 2018-05-22 | 0.25 | 3.3227 | 0.83067 | Reduce | 0.012 | 3.3055 | 0.039667 | H3 | 3 | Stable | 0.9 | 116 | 123 | 160 | 128 | 0.2 | 5 | 52 | 67 | 46.6667 | 0.51615 | 95.2 | 1 | 3.1657
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_693 | 2017-05-23 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.1 | 0.77172 | 0.077172 | H3 | 3 | Stable | 0.5 | 97 | 135 | 156 | 132.1667 | 0.1 | 23 | 53 | 76 | 51.8333 | 0 | 60 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_693 | 2017-05-23 | 2018-01-20 01:00 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.02 | 6.431 | 0.12862 | H3 | 3 | Improving | 0.6 | 91 | 137 | 144 | 130.5 | 0.3 | 6 | 44 | 78 | 43.3333 | -47.0588 | 86.6667 | 1 | -25.6353
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Reduce touch labour if Production readiness programme successful | Person_238 | 2017-05-23 | 2018-03-23 | 0.3 | 1.5606 | 0.46818 | Exploit | 0.5 | 1.5606 | 0.7803 | H2 | 4 | Stable | [10 empty] | 0 | -66.6667 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_008 | Project_057 | Risk-01 | Project_057_Risk-01 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Cable | Person_464 | 2015-08-22 01:00 | 2016-12-21 01:00 | 0.1 | 12.6408 | 1.2641 | Avoid | 0.1 | 0.23232 | 0.023232 | H2 | 4 | Improving | [10 empty] | 98.1622 | 0 | 0 | 58.8973
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 1.3834 | 0.55336 | H2 | 4 | Stable | 0.5 | 84 | 134 | 146 | 127.6667 | 0.3 | 12 | 53 | 70 | 49 | 65.054 | 20 | 0 | 39.0324
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_703 | 2015-05-24 | 2017-11-19 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 5.0983 | 0.76474 | H3 | 3 | Stable | 0.5 | 108 | 135 | 148 | 132.6667 | 0.3 | 3 | 49 | 79 | 46.3333 | 19.0479 | 70 | 1 | 13.5287
2017-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-63 | Project_022_RISK-63 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Levy | Person_703 | 2012-04-19 | 2017-08-20 | 0.8 | 3.5298 | 2.8239 | Exploit | 0.8 | 3.5298 | 2.8239 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-62 | Project_022_RISK-62 | Threat | Project Contingency | Open | H3 | 3 | 8. Operations & Maintenance | Additional Costs from Integration Cost Centre | Person_703 | 2017-03-23 | 2017-05-14 | 0.5 | 7.1754 | 3.5877 | Avoid | 0.292 | 3.5877 | 1.0476 | H3 | 3 | Worsening | [10 empty] | 50 | 41.6 | 0 | 30
2017-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2017-06-21 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.35 | 2.8688 | 1.0041 | H2 | 4 | Stable | 0.7 | 99 | 135 | 147 | 131 | 0.4 | 11 | 43 | 67 | 41.6667 | 22.0253 | 56.25 | 0 | 13.2152
2017-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2017-08-20 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 0.65554 | 0.52443 | H2 | 4 | Stable | [10 empty] | 80.45 | 0 | 0 | 48.27
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.5 | 94 | 130 | 149 | 127.1667 | 0.2 | 29 | 42 | 72 | 44.8333 | 25.8065 | 20 | 0 | 15.4839
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-002 | Project_021_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 93 | 137 | 154 | 132.5 | 0.4 | 19 | 44 | 75 | 45 |  | 66.6667 | 1
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H3 | 3 | Stable | 0.6 | 88 | 138 | 150 | 131.6667 | 0.3 | 28 | 47 | 65 | 46.8333 |  | 62.5 | 1
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-009 | Project_021_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification Report delays due to insufficient resource in supply chain | Person_207 | 2017-09-20 01:00 | 2017-12-20 01:00 | 0.2 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.6 | 111 | 128 | 141 | 127.3333 | 0.3 | 31 | 41 | 72 | 44.5 |  | 50 | 1
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-004 | Project_021_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 80 | 132 | 152 | 126.6667 | 0.4 | 34 | 53 | 72 | 53 |  | 80 | 1
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-014 | Project_021_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.8 | 89 | 140 | 144 | 132.1667 | 0.1 | 20 | 49 | 70 | 47.6667 |  | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-013 | Project_021_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to late Trials Approval | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 119 | 125 | 150 | 128.1667 | 0.3 | 35 | 41 | 68 | 44.5 |  | 66.6667 | 1
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification delays | Person_207 | 2017-09-20 01:00 | 2017-11-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Worsening | 0.9 | 117 | 128 | 156 | 130.8333 | 0.2 | 3 | 52 | 64 | 45.8333 |  | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-018 | Project_021_Risk-018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2017-05-23 | 2017-11-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 91 | 132 | 156 | 129.1667 | 0.3 | 24 | 44 | 72 | 45.3333 |  | 40 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-017 | Project_021_Risk-017 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target. | Person_061 | 2013-01-07 01:00 | 2018-02-04 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.8 | 111 | 128 | 145 | 128 | 0.1 | 10 | 56 | 60 | 49 | 0 | 33.3333 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-015 | Project_021_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to technical performance | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.3 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.5 | 86 | 132 | 144 | 126.3333 | 0.4 | 37 | 51 | 79 | 53.3333 |  | 33.3333 | 1
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK021 | Project_021_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | ERP implementation | Person_174 | 2017-06-23 | 2017-09-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.25 | 0 | 0 | H2 | 4 | Stable | 0.5 | 118 | 134 | 147 | 133.5 | 0.1 | 15 | 57 | 60 | 50.5 |  | 50 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_174 | 2012-11-20 01:00 | 2018-08-21 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.6 | 83 | 139 | 142 | 130.1667 | 0.4 | 17 | 55 | 61 | 49.6667 | 0 | 50 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK024 | Project_021_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_482 | 2017-05-23 | 2017-11-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.7 | 106 | 124 | 153 | 125.8333 | 0.4 | 23 | 58 | 64 | 53.1667 |  | 40 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2018-02-19 01:00 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Stable | 0.8 | 81 | 138 | 156 | 131.5 | 0.3 | 16 | 49 | 72 | 47.3333 | 0 | 57.1429 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 0.8 | 4.6352 | 3.7081 | Reduce | 0.6 | 4.6352 | 2.7811 | H1 | 5 | Worsening | 0.8 | 106 | 127 | 156 | 128.3333 | 0.1 | 39 | 51 | 69 | 52 | 0 | 25 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-12-20 01:00 | 0.6 | 17.2826 | 10.3696 | Reduce | 0.3 | 17.2826 | 5.1848 | H2 | 4 | Worsening | 0.7 | 91 | 135 | 156 | 131.1667 | 0.4 | 16 | 53 | 60 | 48 | 0 | 50 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Additional tasks required with mode certification | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 0.8 | 1.3243 | 1.0595 | Reduce | 0.6 | 1.3243 | 0.7946 | H1 | 5 | Worsening | 0.5 | 90 | 139 | 144 | 131.6667 | 0.2 | 15 | 45 | 77 | 45.3333 | 0 | 25 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2018-01-19 01:00 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.7 | 118 | 137 | 152 | 136.3333 | 0.3 | 8 | 44 | 73 | 42.8333 | 80 | 66.6667 | 0 | 48
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond (revised) target. | Person_482 | 2013-01-07 01:00 | 2018-02-04 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.8 | 111 | 139 | 151 | 136.3333 | 0.1 | 24 | 41 | 74 | 43.6667 | 0 | 33.3333 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2013-01-07 01:00 | 2017-11-19 01:00 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.7 | 119 | 128 | 148 | 129.8333 | 0.1 | 38 | 49 | 73 | 51.1667 | 0 | 33.3333 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_174 | 2009-06-23 | 2018-08-21 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.5 | 97 | 125 | 158 | 125.8333 | 0.4 | 34 | 56 | 74 | 55.3333 | 50 | 28.5714 | 0 | 30
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-09-19 01:00 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.5 | 102 | 138 | 148 | 133.6667 | 0.1 | 32 | 48 | 62 | 47.6667 | 7.8429 | 40 | 0 | 4.7058
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-12-17 01:00 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.4 | 12.6474 | 5.059 | H2 | 4 | Stable | 0.6 | 85 | 123 | 141 | 119.6667 | 0.4 | 2 | 56 | 67 | 48.8333 | 0 | 33.3333 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.5 | 102 | 126 | 147 | 125.5 | 0.1 | 10 | 54 | 67 | 48.8333 | 0 | 50 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-022 | Project_021_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | trials delay due to lack of supporting resources | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.5 | 105 | 124 | 154 | 125.8333 | 0.3 | 27 | 57 | 67 | 53.6667 |  | 66.6667 | 1
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-021 | Project_021_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | trials delay due to lack of equipment | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.5 | 97 | 127 | 152 | 126.1667 | 0.1 | 34 | 55 | 68 | 53.6667 |  | 66.6667 | 1
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Non-Recurring Engineering higher than expected | Person_510 | 2016-06-01 | 2016-08-20 | 0.5 | 13.3382 | 6.6691 | Reduce | 0.5 | 13.3382 | 6.6691 | H2 | 4 | Improving | 0.5 | 111 | 129 | 153 | 130 | 0.1 | 30 | 40 | 63 | 42.1667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-19 22:00 | 0.4 | 9.139 | 3.6556 | Avoid | 0.2 | 9.139 | 1.8278 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Product Baseline delivery is late | Person_151 | 2015-09-20 22:00 | 2017-02-12 22:00 | 0.125 | 232.2192 | 29.0274 | -- | 0.215 | 27.8663 | 5.9913 | H2 | 4 | Stable | [10 empty] | 88 | -72 | 0 | 52.8
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 0.5 | 13.7833 | 6.8917 | Avoid | 0.2 | 6.8917 | 1.3783 | H3 | 3 | Stable | [10 empty] | 50 | 60 | 1 | 31.8
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-19 22:00 | 0.3 | 5.5433 | 1.663 | Reduce | 0.35 | 5.5433 | 1.9402 | H2 | 4 | Worsening | 0.5 | 80 | 136 | 159 | 130.5 | 0.1 | 30 | 57 | 60 | 53 | 0 | -16.6667 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-20 22:00 | 2016-11-19 22:00 | 0.6 | 22.9223 | 13.7534 | Avoid | 0.15 | 22.9223 | 3.4383 | H2 | 4 | Worsening | [10 empty] | 0 | 75 | 0 | 0
2017-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2017-11-19 01:00 | 0.05 | 6.7418 | 1.6855 | Accept | 0.05 | 6.7418 | 1.0113 | H3 | 3 | Improving | 0.8 | 89 | 126 | 145 | 123 | 0.8 | 89 | 126 | 145 | 123 | 0 | 0 | 1 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 0.3 | 26.9674 | 8.0902 | Avoid | 0.3 | 14.9819 | 4.4946 | H2 | 4 | Stable | [10 empty] | 44.4444 | 0 | 0 | 26.6667
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-20 22:00 | 0.5 | 26.9674 | 13.4837 | Avoid | 0.1 | 12.7646 | 1.2765 | H2 | 4 | Worsening | [10 empty] | 52.6667 | 80 | 0 | 31.6
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-21 22:00 | 2016-12-20 22:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.5 | 87 | 128 | 151 | 125 | 0.3 | 30 | 55 | 61 | 51.8333 | 47 | 0 | 0 | 28.2
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-21 22:00 | 2016-12-20 22:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-18 22:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.2 | 1.5935 | 0.3187 | H3 | 3 | Stable | 0.8 | 95 | 139 | 144 | 132.5 | 0.4 | 34 | 54 | 66 | 52.6667 | 50 | 50 | 1 | 31.5
2017-11-20 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK003 | Project_053_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier procured Equipment lead times | Person_546 | 2017-10-21 01:00 | 2018-03-21 | 0.5 | 4.3099 | 2.155 | Reduce | 0.1 | 4.3099 | 0.43099 | H3 | 3 | Improving | 0.6 | 118 | 130 | 155 | 132.1667 | 0.2 | 38 | 45 | 63 | 46.8333 | 0 | 80 | 1 | 2.4
2017-11-20 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK006 | Project_053_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional UK integration of the System product | Person_719 | 2018-01-21 01:00 | 2018-03-22 | 0.2 | 6.3212 | 1.2642 | Avoid | 0.2 | 6.3212 | 1.2642 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-11-20 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK005 | Project_053_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier Deiivery Schedule | Person_252 | 2018-01-21 01:00 | 2018-09-20 01:00 | 0.5 | 5.3299 | 2.665 | Reduce | 0.25 | 5.3299 | 1.3325 | H2 | 4 | Stable | 0.9 | 99 | 139 | 159 | 135.6667 | 0.4 | 18 | 56 | 60 | 50.3333 | 0 | 50 | 0 | 0
2017-11-20 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK010 | Project_053_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Immaturity of the core product | Person_719 | 2018-08-22 01:00 | 2018-11-20 01:00 | 0.5 | 6.4649 | 3.2325 | Transfer | 0.2 | 6.4649 | 1.293 | H2 | 4 | Stable | [10 empty] | 0 | 60 | 0 | 0
2017-11-20 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK007 | Project_053_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Resources Uavailable | Person_252 | 2017-11-20 01:00 | 2019-08-21 01:00 | 0.5 | 10.3438 | 5.1719 | Reduce | 0.2 | 7.9015 | 1.5803 | H3 | 3 | Stable | 0.7 | 104 | 126 | 160 | 128 | 0.4 | 28 | 45 | 78 | 47.6667 | 23.6111 | 60 | 1 | 15.9666
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.6 | 109 | 122 | 160 | 126.1667 | 0.4 | 1 | 43 | 72 | 40.8333 | 0 | 0 | 1 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-11-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer find issues with delivered parts | Person_387 | 2016-05-23 | 2019-08-20 | 0.8 | 9.0039 | 7.2032 | Reduce | 0.25 | 9.0039 | 2.251 | H2 | 4 | Improving | 0.6 | 108 | 125 | 155 | 127.1667 | 0.4 | 20 | 50 | 79 | 49.8333 | 0 | 68.75 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Open PR's | Person_319 | 2017-04-22 | 2018-11-20 01:00 | 0.5 | 0.29361 | 0.1468 | Reduce | 0.15 | 0.29361 | 0.044041 | H3 | 3 | Improving | 0.8 | 114 | 131 | 155 | 132.1667 | 0.4 | 23 | 50 | 70 | 48.8333 | 0 | 70 | 1 | 2.1
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-034 | Project_062_Risk-034 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Long lead Procurement price increases | Person_664 | 2017-07-21 | 2018-04-22 | 0.25 | 1.6962 | 0.33923 | Accept | 0.25 | 1.6962 | 0.33923 | H2 | 4 | Stable | 0.8 | 113 | 135 | 143 | 132.6667 | 0.8 | 113 | 135 | 143 | 132.6667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-018 | Project_062_Risk-018 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Prioritisation - new or less experienced staff | Person_459 | 2017-07-21 | 2018-11-20 01:00 | 0.35 | 3.0513 | 0.61026 | Accept | 0.25 | 3.0513 | 0.61026 | H2 | 4 | Improving | 0.6 | 84 | 139 | 156 | 132.6667 | 0.6 | 84 | 139 | 156 | 132.6667 | 0 | 28.5714 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-019 | Project_062_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Obsolescence | Person_543 | 2017-07-21 | 2018-05-15 | 0.1 | 18.9062 | 9.4531 | Accept | 0.098 | 18.9062 | 9.4531 | H3 | 3 | Stable | 0.5 | 116 | 124 | 155 | 127.8333 | 0.5 | 116 | 124 | 155 | 127.8333 | 0 | 2 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-021 | Project_062_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Hardware CoSupplierng | Person_664 | 2017-07-21 | 2018-07-20 | 0.3 | 3.7214 | 0.93035 | Accept | 0.25 | 3.7214 | 0.93035 | H2 | 4 | Stable | 0.8 | 106 | 126 | 148 | 126.3333 | 0.8 | 106 | 126 | 148 | 126.3333 | 0 | 16.6667 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-060 | Project_062_Risk-060 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Software Port between networks | Person_479 | 2017-09-20 01:00 | 2017-12-21 01:00 | 0.65 | 3.7207 | 0.93016 | Accept | 0.65 | 3.7207 | 0.93016 | H1 | 5 | Stable | 0.8 | 94 | 140 | 155 | 134.8333 | 0.8 | 94 | 140 | 155 | 134.8333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 08:00 | 2019-08-20 08:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 08:00 | 2019-08-20 08:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 08:00 | 2019-08-20 08:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 08:00 | 2019-08-20 08:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 08:00 | 2019-08-20 08:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Labour/Material Risk | Person_662 | 2015-05-24 | 2019-05-23 | 0.5 | 1.2124 | 0.12124 | Accept | 0.5 | 1.2124 | 0.060622 | H2 | 4 | Stable | 0.8 | 84 | 125 | 150 | 122.3333 | 0.8 | 84 | 125 | 150 | 122.3333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_002 | Portfolio_009 | Project_045 | RISK001 | Project_045_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour/T&S Overspend | Person_662 | 2017-01-21 | 2020-05-22 | 0.5 | 0.80829 | 0.32332 | Accept | 0.5 | 0.80829 | 0.32332 | H2 | 4 | Stable | 0.5 | 90 | 127 | 160 | 126.3333 | 0.5 | 90 | 127 | 160 | 126.3333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK013 | Project_041_RISK013 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional components validation | Person_693 | 2017-07-15 | 2018-04-22 | 0.4 | 0.80829 | 0.32332 | Accept | 0.4 | 0.80829 | 0.32332 | H2 | 4 | Stable | 0.5 | 85 | 134 | 157 | 129.6667 | 0.5 | 85 | 134 | 157 | 129.6667 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Risk of not being able to perform Tests | Person_238 | 2017-12-21 01:00 | 2019-01-21 01:00 | 0.5 | 0.64663 | 0.32332 | Accept | 0.5 | 0.64663 | 0.32332 | H2 | 4 | Stable | 0.8 | 110 | 128 | 143 | 127.5 | 0.8 | 110 | 128 | 143 | 127.5 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_238 | 2017-05-23 | 2019-01-21 01:00 | 0.5 | 0.80829 | 0.16166 | Accept | 0.5 | 0.80829 | 0.16166 | H2 | 4 | Stable | 0.7 | 83 | 127 | 144 | 122.5 | 0.7 | 83 | 127 | 144 | 122.5 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_547 | 2017-05-23 | 2018-05-22 | 0.1 | 0.80829 | 0.16166 | Accept | 0.1 | 0.80829 | 0.16166 | H3 | 3 | Stable | 0.6 | 96 | 133 | 148 | 129.3333 | 0.6 | 96 | 133 | 148 | 129.3333 | 0 | 0 | 1 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production, Procurement or Engineering | Person_725 | 2018-01-21 01:00 | 2019-05-23 | 0.1 | 1.6166 | 0.48497 | Accept | 0.1 | 1.6166 | 0.48497 | H3 | 3 | Worsening | 0.8 | 119 | 135 | 157 | 136 | 0.8 | 119 | 135 | 157 | 136 | 0 | 0 | 1 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK002 | Project_041_RISK002 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Component Technical risk using new material | Person_653 | 2017-09-20 01:00 | 2018-05-22 | 0.4 | 2.0207 | 0.20207 | Accept | 0.4 | 2.0207 | 0.20207 | H3 | 3 | Stable | 0.7 | 92 | 126 | 159 | 125.8333 | 0.7 | 92 | 126 | 159 | 125.8333 | 0 | 0 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-21 22:00 | 2016-11-19 22:00 | 0.25 | 0 | 0 | Accept | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 84 | 126 | 150 | 123 | 0.8 | 84 | 126 | 150 | 123 |  | 60 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-19 22:00 | 0.25 | 1.0661 | 0.21322 | Accept | 0.15 | 0 | 0 | H3 | 3 | Stable | 0.5 | 91 | 125 | 152 | 123.8333 | 0.5 | 91 | 125 | 152 | 123.8333 | 100 | 40 | 1 | 61.2
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer find issues with delivered parts or documentation | Person_387 | 2016-05-23 | 2019-08-20 | 0.4 | 9.0039 | 3.6016 | Reduce | 0.25 | 9.0039 | 2.251 | H2 | 4 | Improving | 0.6 | 88 | 135 | 146 | 129 | 0.3 | 7 | 59 | 66 | 51.5 | 0 | 37.5 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Open PR's | Person_319 | 2017-04-22 | 2018-11-20 01:00 | 0.5 | 0.29361 | 0.1468 | Reduce | 0.15 | 0.29361 | 0.044041 | H3 | 3 | Improving | 0.9 | 99 | 134 | 155 | 131.6667 | 0.1 | 5 | 55 | 78 | 50.5 | 0 | 70 | 1 | 2.1
2017-11-20 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK021 | Project_053_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Product documentation | Person_719 | 2018-08-22 01:00 | 2019-07-26 | 0.35 | 0 | 0 | Accept | 0.35 | 0 | 0 | H2 | 4 | Stable | 0.6 | 113 | 122 | 141 | 123.6667 | 0.6 | 113 | 122 | 141 | 123.6667 |  | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_016 | Project_061 | RISK003 | Project_061_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Test equipment reliability | Person_104 | 2017-05-23 | 2020-11-19 01:00 | 0.4 | 0.11013 | 0.044051 | Reduce | 0.3 | 0.11013 | 0.033038 | H2 | 4 | Stable | 0.9 | 119 | 135 | 154 | 135.5 | 0.2 | 33 | 40 | 76 | 44.8333 | 0 | 25 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Rotatory System | Person_403 | 2013-03-14 18:00 | 2019-08-20 18:00 | 0.9 | 9.9244 | 8.932 | Reduce | 0.1 | 1.6541 | 0.16541 | H3 | 3 | Stable | 0.6 | 81 | 121 | 149 | 119 | 0.2 | 16 | 41 | 75 | 42.5 | 83.3333 | 88.8889 | 1 | 52.6667
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.7 | 90 | 138 | 150 | 132 | 0.1 | 30 | 47 | 71 | 48.1667 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 18:00 | 2019-08-20 18:00 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 0.61752 | 0.37669 | H1 | 5 | Stable | 0.6 | 83 | 139 | 157 | 132.6667 | 0.1 | 34 | 58 | 65 | 55.1667 | 72 | 0 | 0 | 43.2
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 4.6134 | 1.6147 | -- | 0.35 | 4.6134 | 1.6147 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Workshop ability | Person_039 | 2012-08-20 18:00 | 2019-08-20 18:00 | 0.41 | 2.5362 | 1.0399 | Reduce | 0.41 | 1.3255 | 0.54344 | H3 | 3 | Stable | 0.5 | 99 | 134 | 159 | 132.3333 | 0.1 | 7 | 58 | 65 | 50.6667 | 47.7391 | 0 | 0 | 28.6435
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-20 22:00 | 2016-08-20 22:00 | 0.3 | 37.5906 | 11.2772 | Reduce | 0.25 | 37.5906 | 9.3977 | H2 | 4 | Stable | 0.9 | 102 | 129 | 160 | 129.6667 | 0.4 | 37 | 42 | 67 | 45.3333 | 0 | 16.6667 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 18:00 | 0.7 | 2.8891 | 2.0224 | Reduce | 0.7 | 2.8891 | 2.0224 | H1 | 5 | Worsening | 0.7 | 100 | 131 | 154 | 129.6667 | 0.2 | 13 | 51 | 74 | 48.5 | 0 | 0 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK007 | Project_048_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Staff Availability | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.4 | 0.067093 | 0.026837 | Avoid | 0.1 | 0.067093 | 0.0067093 | H3 | 3 | Stable | [10 empty] | 0 | 75 | 1 | 2.25
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK017 | Project_048_RISK017 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Increased build rate | Person_683 | 2017-11-12 01:00 | 2019-08-21 01:00 | 0.5 | 7.7433 | 3.8716 | -- | 0.5 | 7.7433 | 3.8716 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK016 | Project_048_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.2 | 0.22605 | 0.045211 | -- | 0.1 | 0.22605 | 0.022605 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK018 | Project_048_RISK018 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Line Closure | Person_683 | 2019-08-21 01:00 | 2019-11-20 01:00 | 0.5 | 0.68298 | 0.34149 | -- | 0.5 | 1.5483 | 0.77415 | H2 | 4 | Improving | [10 empty] | -126.7001 | 0 | 0 | -76.0201
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK004 | Project_048_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 1.0253 | 0.20506 | Reduce | 0.15 | 1.0253 | 0.1538 | H3 | 3 | Stable | 0.6 | 115 | 127 | 158 | 130.1667 | 0.4 | 33 | 41 | 66 | 43.8333 | 0 | 25 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK014 | Project_048_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 0.1 | 2.5117 | 0.25117 | Avoid | 0.05 | 2.5117 | 0.12558 | H3 | 3 | Worsening | [10 empty] | 0 | 50 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK006 | Project_048_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Customer | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0.20644 | 0.041288 | Reduce | 0.15 | 0.20644 | 0.030966 | H3 | 3 | Stable | 0.8 | 88 | 134 | 142 | 127.6667 | 0.2 | 1 | 48 | 77 | 45 | 0 | 25 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK005 | Project_048_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 0.43506 | 0.26104 | Avoid | 0.5 | 0.43506 | 0.21753 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK011 | Project_048_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Line Qualification | Person_270 | 2017-02-20 01:00 | 2019-05-23 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.5 | 117 | 126 | 141 | 127 | 0.2 | 23 | 53 | 60 | 49.1667 |  | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK002 | Project_048_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2020-05-22 | 0.15 | 0.30966 | 0.046449 | Avoid | 0.15 | 0.30966 | 0.046449 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK012 | Project_048_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Customer require additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK008 | Project_048_RISK008 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Oracle | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.1 | 0.20644 | 0.020644 | Avoid | 0.05 | 0.20644 | 0.010322 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK004 | Project_063_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 2.861 | 0.57221 | Reduce | 0.15 | 2.861 | 0.42915 | H3 | 3 | Stable | 0.5 | 83 | 127 | 142 | 122.1667 | 0.2 | 38 | 44 | 69 | 47.1667 | 0 | 25 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK014 | Project_063_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 0.1 | 7.0086 | 0.70086 | Avoid | 0.05 | 7.0086 | 0.35043 | H3 | 3 | Worsening | [10 empty] | 0 | 50 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK006 | Project_063_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Customer | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0.57605 | 0.11521 | Reduce | 0.15 | 0.57605 | 0.086407 | H3 | 3 | Stable | 0.7 | 108 | 140 | 159 | 137.8333 | 0.4 | 32 | 43 | 77 | 46.8333 | 0 | 25 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK017 | Project_063_RISK017 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Increased build rate | Person_683 | 2017-11-12 01:00 | 2019-08-21 01:00 | 0.5 | 21.6065 | 10.8033 | -- | 0.5 | 21.6065 | 10.8033 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK005 | Project_063_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 1.214 | 0.72839 | -- | 0.5 | 1.214 | 0.60699 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK016 | Project_063_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.2 | 0.63077 | 0.12615 | -- | 0.1 | 0.63077 | 0.063077 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK011 | Project_063_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Line Qualification | Person_270 | 2017-02-20 01:00 | 2019-05-23 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.9 | 80 | 137 | 148 | 129.3333 | 0.2 | 36 | 51 | 76 | 52.6667 |  | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK002 | Project_063_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2020-05-22 | 0.15 | 0.86407 | 0.12961 | Avoid | 0.15 | 0.86407 | 0.12961 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK012 | Project_063_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Customer require additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK008 | Project_063_RISK008 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Oracle | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.1 | 0.57605 | 0.057605 | Avoid | 0.05 | 0.57605 | 0.028802 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK007 | Project_063_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Staff Availability | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.4 | 0.18722 | 0.074886 | Avoid | 0.1 | 0.18722 | 0.018722 | H3 | 3 | Stable | [10 empty] | 0 | 75 | 1 | 2.25
2017-12-21 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK003 | Project_044_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Mono vs stereo Component | Person_358 | 2016-03-23 | 2018-10-22 01:00 | 0.7 | 14.4876 | 10.1413 | Reduce | 0.5 | 14.4876 | 7.2438 | H2 | 4 | Improving | 0.7 | 107 | 140 | 144 | 135.1667 | 0.1 | 38 | 46 | 79 | 50.1667 | 0 | 28.5714 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK018 | Project_063_RISK018 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Line Closure | Person_683 | 2019-08-21 01:00 | 2019-11-20 01:00 | 0.5 | 1.9058 | 0.95288 | -- | 0.5 | 4.3203 | 2.1602 | H2 | 4 | Improving | [10 empty] | -126.7001 | 0 | 0 | -76.0201
2017-12-21 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK008 | Project_044_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Skills | Person_505 | 2017-10-21 01:00 | 2018-10-22 01:00 | 0.3 | 1.5695 | 0.47085 | Reduce | 0.3 | 1.4488 | 0.43463 | H2 | 4 | Stable | 0.7 | 117 | 138 | 142 | 135.1667 | 0.3 | 33 | 41 | 68 | 44.1667 | 7.6924 | 0 | 0 | 4.6155
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK004 | Project_060_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Cross-functional Estimates | Person_729 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.2 | 1.0961 | 0.21922 | Reduce | 0.1 | 0.28845 | 0.028845 | H3 | 3 | Stable | 0.8 | 80 | 132 | 150 | 126.3333 | 0.3 | 21 | 58 | 79 | 55.3333 | 73.6842 | 50 | 0 | 44.2105
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK006 | Project_060_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Secure material Handling | Person_033 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.5 | 1.1538 | 0.5769 | Reduce | 0.2 | 1.1538 | 0.23076 | H3 | 3 | Stable | 0.9 | 105 | 133 | 152 | 131.5 | 0.3 | 24 | 57 | 62 | 52.3333 | 0 | 60 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK002 | Project_060_RISK002 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Requirements Misalignment | Person_729 | 2017-11-19 01:00 | 2018-11-08 01:00 | 0.5 | 0.5769 | 0.28845 | Reduce | 0.1 | 0.5769 | 0.05769 | H3 | 3 | Stable | 0.5 | 101 | 131 | 148 | 128.8333 | 0.2 | 33 | 59 | 78 | 57.8333 | 0 | 80 | 0 | 0
2017-12-21 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK003 | Project_053_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier procured Equipment lead times | Person_546 | 2017-10-21 01:00 | 2018-03-21 | 0.5 | 4.3099 | 2.155 | Reduce | 0.1 | 4.3099 | 0.43099 | H3 | 3 | Improving | 0.8 | 96 | 125 | 148 | 124 | 0.3 | 15 | 44 | 69 | 43.3333 | 0 | 80 | 1 | 2.4
2017-12-21 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK006 | Project_053_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional UK integration of the System product | Person_719 | 2018-01-21 01:00 | 2018-03-22 | 0.2 | 6.3212 | 1.2642 | Avoid | 0.2 | 6.3212 | 1.2642 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-12-21 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK005 | Project_053_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier Deiivery Schedule | Person_252 | 2018-01-21 01:00 | 2018-09-20 01:00 | 0.5 | 5.3299 | 2.665 | Reduce | 0.25 | 5.3299 | 1.3325 | H2 | 4 | Stable | 0.6 | 83 | 132 | 160 | 128.5 | 0.1 | 20 | 59 | 64 | 53.3333 | 0 | 50 | 0 | 0
2017-12-21 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK010 | Project_053_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Immaturity of the core product | Person_719 | 2018-08-22 01:00 | 2018-11-20 01:00 | 0.5 | 6.4649 | 3.2325 | Transfer | 0.2 | 6.4649 | 1.293 | H2 | 4 | Stable | [10 empty] | 0 | 60 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-002 | Project_021_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.9 | 80 | 132 | 158 | 127.6667 | 0.4 | 2 | 40 | 67 | 38.1667 |  | 66.6667 | 1
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H3 | 3 | Stable | 0.5 | 105 | 124 | 160 | 126.8333 | 0.4 | 11 | 45 | 62 | 42.1667 |  | 62.5 | 1
2017-12-21 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK007 | Project_053_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Resources Uavailable | Person_252 | 2017-11-20 01:00 | 2019-08-21 01:00 | 0.5 | 10.3438 | 5.1719 | Reduce | 0.2 | 7.9015 | 1.5803 | H3 | 3 | Stable | 0.5 | 111 | 139 | 148 | 135.8333 | 0.2 | 8 | 40 | 71 | 39.8333 | 23.6111 | 60 | 1 | 15.9666
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-009 | Project_021_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification Report delays due to insufficient resource in supply chain | Person_207 | 2017-09-20 01:00 | 2017-12-20 01:00 | 0.2 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.6 | 95 | 135 | 144 | 129.8333 | 0.2 | 27 | 58 | 61 | 53.3333 |  | 50 | 1
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-004 | Project_021_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.9 | 82 | 122 | 159 | 121.5 | 0.4 | 4 | 49 | 70 | 45 |  | 80 | 1
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-014 | Project_021_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.9 | 119 | 139 | 146 | 136.8333 | 0.1 | 32 | 49 | 62 | 48.3333 |  | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-013 | Project_021_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to late Trials Approval | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.5 | 99 | 132 | 159 | 131 | 0.3 | 1 | 52 | 61 | 45 |  | 66.6667 | 1
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification delays | Person_207 | 2017-09-20 01:00 | 2017-11-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Worsening | 0.5 | 109 | 133 | 142 | 130.5 | 0.1 | 24 | 52 | 71 | 50.5 |  | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-018 | Project_021_Risk-018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2017-05-23 | 2017-11-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 106 | 122 | 143 | 122.8333 | 0.4 | 17 | 59 | 66 | 53.1667 |  | 40 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-017 | Project_021_Risk-017 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target. | Person_061 | 2013-01-07 01:00 | 2018-02-04 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.6 | 108 | 121 | 152 | 124 | 0.1 | 31 | 56 | 70 | 54.1667 | 0 | 33.3333 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-015 | Project_021_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to technical performance | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 0.3 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.5 | 87 | 125 | 151 | 123 | 0.4 | 36 | 57 | 63 | 54.5 |  | 33.3333 | 1
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK021 | Project_021_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | ERP implementation | Person_174 | 2017-06-23 | 2017-09-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.25 | 0 | 0 | H2 | 4 | Stable | 0.5 | 117 | 140 | 153 | 138.3333 | 0.2 | 5 | 50 | 63 | 44.6667 |  | 50 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_174 | 2012-11-20 01:00 | 2018-08-21 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.8 | 98 | 135 | 152 | 131.6667 | 0.1 | 28 | 46 | 72 | 47.3333 | 0 | 50 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK024 | Project_021_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_482 | 2017-05-23 | 2017-11-19 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 111 | 130 | 157 | 131.3333 | 0.2 | 10 | 45 | 65 | 42.5 |  | 40 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2018-02-19 01:00 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Stable | 0.9 | 119 | 122 | 153 | 126.6667 | 0.3 | 25 | 49 | 64 | 47.5 | 0 | 57.1429 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 0.8 | 4.6352 | 3.7081 | Reduce | 0.6 | 4.6352 | 2.7811 | H1 | 5 | Worsening | 0.7 | 97 | 137 | 149 | 132.3333 | 0.1 | 28 | 52 | 76 | 52 | 0 | 25 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-12-20 01:00 | 0.6 | 17.2826 | 10.3696 | Reduce | 0.3 | 17.2826 | 5.1848 | H2 | 4 | Worsening | 0.7 | 114 | 130 | 148 | 130.3333 | 0.3 | 17 | 59 | 68 | 53.5 | 0 | 50 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Additional tasks required with mode certification | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 0.8 | 1.3243 | 1.0595 | Reduce | 0.6 | 1.3243 | 0.7946 | H1 | 5 | Worsening | 0.8 | 112 | 123 | 141 | 124.1667 | 0.3 | 7 | 42 | 76 | 41.8333 | 0 | 25 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2018-01-19 01:00 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.7 | 102 | 134 | 146 | 130.6667 | 0.3 | 25 | 40 | 64 | 41.5 | 80 | 66.6667 | 0 | 48
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond (revised) target. | Person_482 | 2013-01-07 01:00 | 2018-02-04 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.6 | 100 | 125 | 146 | 124.3333 | 0.2 | 32 | 41 | 65 | 43.5 | 0 | 33.3333 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2013-01-07 01:00 | 2017-11-19 01:00 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.7 | 100 | 121 | 155 | 123.1667 | 0.2 | 36 | 46 | 66 | 47.6667 | 0 | 33.3333 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_174 | 2009-06-23 | 2018-08-21 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.7 | 96 | 122 | 153 | 122.8333 | 0.2 | 26 | 46 | 77 | 47.8333 | 50 | 28.5714 | 0 | 30
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-09-19 01:00 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.5 | 117 | 127 | 142 | 127.8333 | 0.2 | 29 | 54 | 60 | 50.8333 | 7.8429 | 40 | 0 | 4.7058
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-12-17 01:00 | 0.6 | 12.6474 | 7.5885 | Reduce | 0.4 | 12.6474 | 5.059 | H2 | 4 | Stable | 0.9 | 107 | 136 | 155 | 134.3333 | 0.4 | 8 | 57 | 69 | 50.8333 | 0 | 33.3333 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 0.4 | 19.1897 | 7.6759 | Reduce | 0.2 | 19.1897 | 3.8379 | H2 | 4 | Stable | 0.9 | 97 | 131 | 145 | 127.6667 | 0.4 | 24 | 42 | 73 | 44.1667 | 0 | 50 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-022 | Project_021_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | trials delay due to lack of supporting resources | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.9 | 83 | 139 | 157 | 132.6667 | 0.4 | 4 | 55 | 66 | 48.3333 |  | 66.6667 | 1
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-021 | Project_021_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | trials delay due to lack of equipment | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 107 | 134 | 153 | 132.6667 | 0.4 | 8 | 50 | 74 | 47 |  | 66.6667 | 1
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-117 | Project_043_Risk-117 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Supplier Technical Publications maturity not at the level required | Person_769 | 2017-04-19 | 2018-05-13 | 0.2 | 0.21458 | 0.042916 | Reduce | 0.2 | 0.21458 | 0.042916 | H2 | 4 | Improving | 0.9 | 117 | 126 | 150 | 128.5 | 0.1 | 22 | 55 | 75 | 52.8333 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-111 | Project_043_Risk-111 | Opportunitity | Project Contingency | Open | H1 | 5 | 7. Finance | Decrease the cost of obsolescence sweeps | Person_769 | 2018-01-11 | 2020-12-21 | 0.5 | 0.038325 | 0.019162 | Exploit | 0.5 | 0.038325 | 0.019162 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-113 | Project_043_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | No Gen 1 products available, transition cost to Gen 2 | Person_769 | 2017-04-19 | 2020-12-21 | 0.2 | 0.59882 | 0.11976 | Reduce | 0.2 | 0.59882 | 0.11976 | H2 | 4 | Stable | 0.5 | 114 | 136 | 147 | 134.1667 | 0.1 | 9 | 40 | 73 | 40.3333 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-121 | Project_043_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | More Tech Pubs Update than estimated | Person_769 | 2019-01-21 | 2020-10-20 | 0.25 | 0.32576 | 0.08144 | Reduce | 0.2 | 0.32576 | 0.065152 | H2 | 4 | Stable | 0.8 | 98 | 133 | 150 | 130 | 0.1 | 20 | 47 | 70 | 46.3333 | 0 | 20 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-084 | Project_043_Risk-084 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | complex repair ( over and above the forecast average) | Person_368 | 2017-12-21 | 2020-12-21 | 0.2 | 0.51898 | 0.1038 | Reduce | 0.2 | 0.51898 | 0.1038 | H2 | 4 | Stable | 0.8 | 80 | 135 | 141 | 126.8333 | 0.3 | 38 | 51 | 68 | 51.6667 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-128 | Project_043_Risk-128 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Reliance of Customer Avaliability | Person_135 | 2017-04-19 | 2018-08-21 | 0.5 | 0.83036 | 0.41518 | Reduce | 0.25 | 0.41418 | 0.10355 | H2 | 4 | Stable | 0.6 | 110 | 122 | 155 | 125.5 | 0.4 | 22 | 40 | 62 | 40.6667 | 50.1202 | 50 | 0 | 30.0721
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-089 | Project_043_Risk-089 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares pool is limited | Person_307 | 2018-12-22 | 2020-12-21 | 0.25 | 1.018 | 0.2545 | Reduce | 0.25 | 0.57886 | 0.14472 | H2 | 4 | Stable | 0.5 | 119 | 125 | 145 | 127.3333 | 0.1 | 24 | 53 | 62 | 49.6667 | 43.1373 | 0 | 0 | 25.8824
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-001 | Project_043_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Training Programme capacity | Person_336 | 2017-04-28 | 2018-11-20 | 0.15 | 0 | 0 | Reduce | 0.05 | 0 | 0 | H3 | 3 | Improving | 0.9 | 90 | 136 | 143 | 129.5 | 0.2 | 17 | 57 | 77 | 53.6667 |  | 66.6667 | 1
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-039 | Project_043_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System fails to achieve required performance | Person_051 | 2017-04-19 | 2018-11-20 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H2 | 4 | Stable | 0.6 | 101 | 137 | 150 | 133.1667 | 0.3 | 24 | 43 | 65 | 43.5 |  | 66.6667 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2018-03-22 | 2019-07-21 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.8 | 85 | 135 | 141 | 127.6667 | 0.4 | 31 | 45 | 60 | 45.1667 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_585 | 2017-09-02 01:00 | 2018-03-16 01:00 | 0.1 | 6.4168 | 0.64168 | Transfer | 0.1 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sub-system FPGA | Person_332 | 2017-01-21 01:00 | 2018-09-20 01:00 | 0.4 | 1.5914 | 0.63655 | Reduce | 0.2 | 1.5914 | 0.31827 | H3 | 3 | Stable | 0.9 | 114 | 135 | 160 | 135.6667 | 0.3 | 14 | 43 | 77 | 43.8333 | 0 | 50 | 1 | 1.5
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort for System HW/SW- System upgrade. | Person_199 | 2017-05-23 | 2019-09-18 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.2 | 2.5667 | 0.51334 | H3 | 3 | Stable | 0.8 | 110 | 123 | 153 | 125.8333 | 0.4 | 4 | 48 | 61 | 42.8333 | 0 | 33.3333 | 1 | 1
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs | Person_372 | 2018-04-22 | 2018-08-22 01:00 | 0.5 | 6.6521 | 3.326 | Reduce | 0.5 | 6.6521 | 3.326 | H2 | 4 | Stable | 0.9 | 116 | 128 | 148 | 129.3333 | 0.2 | 7 | 52 | 77 | 48.6667 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.25 | 3.5934 | 0.89835 | H2 | 4 | Stable | 0.9 | 112 | 122 | 141 | 123.5 | 0.1 | 31 | 44 | 61 | 44.6667 | 0 | 50 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Minimum Order Quantities | Person_372 | 2017-11-20 01:00 | 2018-05-15 | 0.2 | 1.925 | 0.38501 | Exploit | 0.2 | 1.925 | 0.38501 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_372 | 2018-04-22 | 2018-08-22 01:00 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Worsening | 0.5 | 113 | 137 | 155 | 136 | 0.1 | 22 | 55 | 70 | 52 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) at the System level on product platform - performed by 3rd parties | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Sub-system / product system accreditation hindered by Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.1 | 0.25667 | 0.025667 | Transfer | 0.1 | 0.25667 | 0.025667 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_585 | 2017-05-23 | 2018-04-21 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2018-01-19 01:00 | 0.3 | 0.89835 | 0.26951 | Transfer | 0.3 | 0.89835 | 0.26951 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 0.35 | 1.9208 | 0.67227 | Reduce | 0.25 | 1.9208 | 0.48019 | H2 | 4 | Stable | 0.7 | 101 | 136 | 153 | 133 | 0.1 | 18 | 58 | 68 | 53 | 0 | 28.5714 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2018-03-22 | 2018-10-18 01:00 | 0.4 | 0.77001 | 0.30801 | Reduce | 0.3 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.6 | 108 | 128 | 155 | 129.1667 | 0.1 | 23 | 48 | 72 | 47.8333 | 0 | 25 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2018-02-20 01:00 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.7 | 98 | 124 | 157 | 125.1667 | 0.1 | 3 | 47 | 77 | 44.6667 | 0 | 28.5714 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 07:00 | 2019-08-20 07:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 07:00 | 2019-08-20 07:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 07:00 | 2019-08-20 07:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 07:00 | 2019-08-20 07:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 07:00 | 2019-08-20 07:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Succession Planning | Person_403 | 2012-08-20 18:00 | 2019-08-07 | 0.61 | 1.8788 | 0.46971 | Accept | 0.61 | 1.5031 | 0.22546 | H1 | 5 | Stable | 0.6 | 99 | 134 | 149 | 130.6667 | 0.6 | 99 | 134 | 149 | 130.6667 | 20 | 0 | 0 | 12
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-20 22:00 | 2019-08-20 | 0.5 | 1.8788 | 0.46971 | Accept | 0.5 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.7 | 95 | 122 | 150 | 122.1667 | 0.7 | 95 | 122 | 150 | 122.1667 | 20 | 0 | 0 | 12
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK044 | Project_042_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2018-02-20 01:00 | 2018-12-21 01:00 | 0.32 | 6.5759 | 2.1043 | -- | 0.32 | 6.5759 | 2.1043 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.2 | 1.8788 | 0.18788 | Accept | 0.2 | 1.5031 | 0.12024 | H3 | 3 | Stable | 0.8 | 120 | 132 | 147 | 132.5 | 0.8 | 120 | 132 | 147 | 132.5 | 20 | 0 | 0 | 12
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.35 | 9.3941 | 3.1001 | Accept | 0.35 | 7.5153 | 2.2546 | H3 | 3 | Stable | 0.5 | 110 | 140 | 158 | 138 | 0.5 | 110 | 140 | 158 | 138 | 20 | 0 | 0 | 12
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-20 22:00 | 2019-08-20 | 0.25 | 0.56365 | 0.11273 | Accept | 0.25 | 0.28182 | 0.028182 | H3 | 3 | Stable | 0.6 | 105 | 125 | 147 | 125.3333 | 0.6 | 105 | 125 | 147 | 125.3333 | 50 | 0 | 0 | 30
2017-12-21 | ORG_001 | BA_002 | Portfolio_009 | Project_051 | RISK001 | Project_051_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Generic Labour or Material Overspend | Person_577 | 2012-05-23 | 2021-05-22 | 0.5 | 4.6971 | 0.93941 | Accept | 0.5 | 3.7576 | 0.67638 | H3 | 3 | Stable | 0.9 | 115 | 128 | 143 | 128.3333 | 0.9 | 115 | 128 | 143 | 128.3333 | 20 | 0 | 0 | 12
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK045 | Project_042_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2019-01-22 01:00 | 2019-05-23 | 0.25 | 3.908 | 0.97699 | -- | 0.25 | 3.908 | 0.97699 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 | 2020-08-20 | 0.5 | 1.8788 | 0.46971 | Accept | 0.5 | 1.1273 | 0.11273 | H2 | 4 | Stable | 0.9 | 92 | 126 | 154 | 125 | 0.9 | 92 | 126 | 154 | 125 | 40 | 0 | 0 | 24
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 1.8788 | 0.37576 | Accept | 0.5 | 1.4091 | 0.21137 | H2 | 4 | Stable | 0.6 | 90 | 126 | 156 | 125 | 0.6 | 90 | 126 | 156 | 125 | 25 | 0 | 0 | 15
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK001 | Project_060_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Porcurement Prices | Person_033 | 2017-11-02 01:00 | 2018-08-20 | 0.7 | 2.1419 | 0.53546 | Accept | 0.7 | 2.0479 | 0.40958 | H2 | 4 | Stable | 0.9 | 117 | 132 | 154 | 133.1667 | 0.9 | 117 | 132 | 154 | 133.1667 | 4.386 | 0 | 0 | 2.6316
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Labour/Material Risk | Person_662 | 2015-05-24 | 2019-05-23 | 0.5 | 2.8182 | 0.28182 | Accept | 0.5 | 2.7619 | 0.22095 | H2 | 4 | Stable | 0.7 | 108 | 136 | 159 | 135.1667 | 0.7 | 108 | 136 | 159 | 135.1667 | 2 | 0 | 0 | 1.2
2017-12-21 | ORG_001 | BA_002 | Portfolio_009 | Project_045 | RISK001 | Project_045_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour/T&S Overspend | Person_662 | 2017-01-21 01:00 | 2020-05-22 | 0.5 | 2.8182 | 0.28182 | Accept | 0.5 | 2.7619 | 0.22095 | H2 | 4 | Stable | 0.9 | 85 | 131 | 143 | 125.3333 | 0.9 | 85 | 131 | 143 | 125.3333 | 2 | 0 | 0 | 1.2
2017-12-21 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK021 | Project_053_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Product documentation | Person_719 | 2018-08-22 01:00 | 2019-07-26 | 0.35 | 1.8788 | 0.37576 | Accept | 0.35 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.8 | 115 | 133 | 150 | 132.8333 | 0.8 | 115 | 133 | 150 | 132.8333 | 20 | 0 | 0 | 12
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-085 | Project_043_Risk-085 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Failure of a product pre delivery | Person_359 | 2017-04-19 | 2018-04-21 | 0.05 | 1.1273 | 0.22546 | Accept | 0.05 | 0.93941 | 0.14091 | H2 | 4 | Improving | 0.9 | 108 | 129 | 159 | 130.5 | 0.9 | 108 | 129 | 159 | 130.5 | 16.6667 | 0 | 0 | 10
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_585 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 1.8788 | 0.37576 | Accept | 0.03 | 1.5031 | 0.22546 | H3 | 3 | Stable | 0.8 | 109 | 123 | 150 | 125.1667 | 0.8 | 109 | 123 | 150 | 125.1667 | 20 | 0 | 0 | 12
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | HW - additional unplanned design effort | Person_332 | 2016-05-23 | 2018-03-23 | 0.4 | 1.0334 | 0.20667 | Accept | 0.4 | 0.80789 | 0.12118 | H2 | 4 | Stable | 0.7 | 104 | 138 | 144 | 133.3333 | 0.7 | 104 | 138 | 144 | 133.3333 | 21.8182 | 0 | 0 | 13.0909
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 1.8788 | 0.18788 | Accept | 0.25 | 1.8225 | 0.12757 | H2 | 4 | Stable | 0.9 | 100 | 123 | 159 | 125.1667 | 0.9 | 100 | 123 | 159 | 125.1667 | 3 | 0 | 0 | 1.8
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 1.8788 | 0.18788 | Accept | 0.2 | 1.5031 | 0.12024 | H3 | 3 | Stable | 0.5 | 83 | 122 | 149 | 120 | 0.5 | 83 | 122 | 149 | 120 | 20 | 33.3333 | 1 | 13
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design [in addition to costed effort] | Person_332 | 2017-05-28 | 2018-11-30 01:00 | 0.2 | 1.8788 | 0.18788 | Accept | 0.2 | 1.5031 | 0.12024 | H3 | 3 | Improving | 0.6 | 84 | 134 | 150 | 128.3333 | 0.6 | 84 | 134 | 150 | 128.3333 | 20 | 0 | 1 | 12
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_585 | 2017-10-21 01:00 | 2019-07-21 | 0.333 | 1.8788 | 0.18788 | Accept | 0.333 | 0.79775 | 0.039887 | H2 | 4 | Stable | 0.7 | 88 | 139 | 151 | 132.5 | 0.7 | 88 | 139 | 151 | 132.5 | 57.54 | 0 | 0 | 34.524
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 10.3335 | 1.0334 | Accept | 0.3 | 10.3335 | 1.0334 | H2 | 4 | Improving | 0.7 | 116 | 128 | 154 | 130.3333 | 0.7 | 116 | 128 | 154 | 130.3333 | 0 | 25 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2020-09-19 01:00 | 0.2 | 11.2729 | 2.2546 | Accept | 0.2 | 11.2729 | 2.2546 | H3 | 3 | Stable | 0.9 | 87 | 137 | 142 | 129.5 | 0.9 | 87 | 137 | 142 | 129.5 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2019-07-21 | 0.3 | 3.7576 | 0.18788 | Accept | 0.2 | 3.7576 | 0.56365 | H3 | 3 | Stable | 0.6 | 105 | 137 | 151 | 134 | 0.6 | 105 | 137 | 151 | 134 | 0 | 33.3333 | 1 | 1
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK026 | Project_042_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st Jan to 31st March | Person_455 | 2020-05-23 | 2020-08-20 01:00 | 0.25 | 6.4382 | 2.2534 | Accept | 0.15 | 6.4382 | 1.2876 | H2 | 4 | Stable | 0.6 | 104 | 136 | 142 | 131.6667 | 0.6 | 104 | 136 | 142 | 131.6667 | 0 | 40 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK047 | Project_042_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables | Person_455 | 2020-11-20 01:00 | 2021-05-22 | 0.2 | 35.0206 | 7.0041 | Accept | 0.1 | 35.0206 | 7.0041 | H2 | 4 | Stable | 0.6 | 111 | 128 | 153 | 129.3333 | 0.6 | 111 | 128 | 153 | 129.3333 | 0 | 50 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software issue input | Person_279 | 2016-11-23 | 2023-02-20 | 0.4 | 49.4398 | 19.7759 | Reduce | 0.2 | 49.4398 | 9.888 | H2 | 4 | Stable | 0.8 | 91 | 131 | 158 | 128.8333 | 0.3 | 1 | 42 | 64 | 38.8333 | 0 | 50 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK028 | Project_042_RISK028 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st July to 30th September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 0.25 | 17.0765 | 1.7076 | Accept | 0.15 | 17.0765 | 1.7076 | H2 | 4 | Stable | 0.8 | 82 | 130 | 144 | 124.3333 | 0.8 | 82 | 130 | 144 | 124.3333 | 0 | 40 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK027 | Project_042_RISK027 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st April to 30th June | Person_455 | 2020-08-21 01:00 | 2020-09-19 01:00 | 0.25 | 186.9553 | 59.2026 | Accept | 0.15 | 186.9553 | 1.3939 | H2 | 4 | Stable | 0.7 | 86 | 132 | 155 | 128.1667 | 0.7 | 86 | 132 | 155 | 128.1667 | 0 | 40 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK022 | Project_042_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2017-09-20 01:00 | 2018-09-20 01:00 | 0.2 | 22.8501 | 6.855 | Accept | 0.18 | 22.8501 | 6.855 | H2 | 4 | Stable | 0.5 | 87 | 122 | 158 | 122.1667 | 0.5 | 87 | 122 | 158 | 122.1667 | 0 | 10 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Additional minor point releases | Person_228 | 2016-05-23 | 2017-10-19 01:00 | 0.5 | 11.9444 | 5.9722 | Reduce | 0.45 | 11.9444 | 5.375 | H1 | 5 | Stable | 0.6 | 86 | 125 | 158 | 124 | 0.4 | 15 | 54 | 74 | 50.8333 | 0 | 10 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_228 | 2016-05-23 | 2018-04-21 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.6 | 117 | 127 | 150 | 129.1667 | 0.4 | 21 | 47 | 65 | 45.6667 | 0 | 50 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_004 | 2015-11-21 01:00 | 2018-11-20 01:00 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.5 | 115 | 122 | 155 | 126.3333 | 0.4 | 18 | 40 | 61 | 39.8333 | 0 | 5 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.8 | 2.8043 | 2.2435 | Reduce | 0.45 | 2.8043 | 1.2619 | H1 | 5 | Stable | 0.7 | 104 | 130 | 150 | 129 | 0.4 | 29 | 48 | 76 | 49.5 | 0 | 43.75 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK167 | Project_024_RISK167 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Customer not providing the information needed or Customer not accepting the Customer documentation resulting in rewor. | Person_710 | 2016-08-21 01:00 | 2018-05-21 | 0.5 | 9.971 | 4.9855 | Reduce | 0.3 | 9.971 | 2.9913 | H1 | 5 | Worsening | 0.5 | 103 | 134 | 157 | 132.6667 | 0.3 | 12 | 40 | 76 | 41.3333 | 0 | 40 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK226 | Project_024_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Late Evidences Certification delivery | Person_642 | 2017-04-30 | 2018-05-21 | 0.4 | 3.9468 | 1.5787 | Reduce | 0.2 | 3.9468 | 0.78937 | H2 | 4 | Worsening | 0.7 | 99 | 139 | 156 | 135.1667 | 0.2 | 19 | 59 | 76 | 55.1667 | 0 | 50 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK043 | Project_042_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st December | Person_455 | 2021-03-23 | 2021-05-22 | 0.1 | 35.9673 | 10.7902 | Accept | 0.08 | 35.9673 | 9.7112 | H3 | 3 | Stable | 0.6 | 81 | 137 | 159 | 131.3333 | 0.6 | 81 | 137 | 159 | 131.3333 | 0 | 20 | 1 | 0.6
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK024 | Project_042_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2019-09-21 01:00 | 2020-09-19 01:00 | 0.33 | 3.9728 | 1.3905 | Accept | 0.3 | 3.9728 | 1.3905 | H2 | 4 | Stable | 0.6 | 108 | 140 | 149 | 136.1667 | 0.6 | 108 | 140 | 149 | 136.1667 | 0 | 9.0909 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.7 | 89 | 134 | 160 | 130.8333 | 0.2 | 8 | 45 | 64 | 42 | 0 | 60 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis and Security | Person_288 | 2017-02-22 01:00 | 2017-11-19 01:00 | 0.3 | 19.9938 | 5.9981 | Reduce | 0.04675 | 19.9938 | 0.93471 | H3 | 3 | Improving | 0.6 | 109 | 135 | 149 | 133 | 0.1 | 19 | 41 | 71 | 42.3333 | 0 | 84.4167 | 1 | 2.5325
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.2 | 3.843 | 0.76859 | H2 | 4 | Stable | 0.6 | 117 | 138 | 147 | 136 | 0.3 | 33 | 57 | 74 | 55.8333 | 0 | 60 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Performance (collector opportunity) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.373 | 19.5316 | 7.2853 | -- | 0.4158 | 19.5316 | 8.1213 | H1 | 5 | Stable | [10 empty] | 0 | -11.4745 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.3 | 20.8767 | 6.263 | H1 | 5 | Stable | 0.5 | 113 | 138 | 159 | 137.3333 | 0.1 | 15 | 56 | 64 | 50.5 | 50 | 25 | 0 | 30
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.504 | 73.3644 | 36.9756 | Reduce | 0.2975 | 53.773 | 15.9975 | H1 | 5 | Worsening | 0.6 | 110 | 132 | 152 | 131.6667 | 0.1 | 32 | 55 | 71 | 53.8333 | 26.7042 | 40.9722 | 0 | 16.0225
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK308 | Project_024_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System robustness and resilience | Person_774 | 2017-04-06 | 2018-06-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.1 | 2.5966 | 0.25966 | H3 | 3 | Stable | 0.9 | 120 | 125 | 151 | 128.5 | 0.4 | 25 | 59 | 76 | 56.1667 | 58.3333 | 66.6667 | 1 | 37
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK046 | Project_042_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables - June | Person_455 | 2018-11-21 01:00 | 2020-11-19 01:00 | 0.2 | 1.2549 | 0.12549 | Accept | 0.1 | 1.2549 | 0.12549 | H2 | 4 | Stable | 0.9 | 114 | 136 | 151 | 134.8333 | 0.9 | 114 | 136 | 151 | 134.8333 | 0 | 50 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-054 | Project_062_Risk-054 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | sub-system rework to reviised standard | Person_277 | 2017-07-21 | 2018-11-21 | 0.4 | 0.62744 | 0.25098 | Transfer | 0.4 | 0.62744 | 0.25098 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK023 | Project_042_RISK023 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2018-09-21 01:00 | 2019-09-20 01:00 | 0.2 | 4.183 | 1.2549 | Accept | 0.18 | 4.183 | 1.2549 | H2 | 4 | Stable | 0.7 | 86 | 121 | 150 | 120 | 0.7 | 86 | 121 | 150 | 120 | 0 | 10 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-013 | Project_062_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Unavailability of Network | Person_479 | 2017-07-21 | 2018-05-22 | 0.25 | 3.5555 | 0.88888 | Reduce | 0.2 | 3.5555 | 0.7111 | H3 | 3 | Stable | 0.7 | 97 | 121 | 154 | 122.5 | 0.4 | 39 | 48 | 68 | 49.8333 | 0 | 20 | 1 | 0.6
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-055 | Project_062_Risk-055 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Supplier integration and Apps | Person_245 | 2017-07-21 | 2018-11-21 | 0.5 | 0.83659 | 0.4183 | Reduce | 0.5 | 0.83659 | 0.4183 | H2 | 4 | Stable | 0.7 | 101 | 139 | 156 | 135.5 | 0.2 | 26 | 54 | 63 | 50.8333 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-011 | Project_062_Risk-011 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Variant deviations between SW | Person_479 | 2017-07-21 | 2018-02-17 | 0.4 | 0.71808 | 0.28723 | Reduce | 0.3 | 0.71808 | 0.21542 | H2 | 4 | Stable | 0.6 | 117 | 128 | 156 | 130.8333 | 0.3 | 5 | 51 | 77 | 47.6667 | 0 | 25 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK029 | Project_042_RISK029 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st October to 31st December | Person_455 | 2021-02-20 01:00 | 2021-05-22 | 0.25 | 10.4574 | 2.6144 | Accept | 0.1 | 10.4574 | 2.6144 | H2 | 4 | Stable | 0.5 | 113 | 138 | 152 | 136.1667 | 0.5 | 113 | 138 | 152 | 136.1667 | 0 | 60 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-056 | Project_062_Risk-056 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Supplier integration acceptance by end Customer | Person_031 | 2017-07-21 | 2018-11-21 | 0.3 | 1.8823 | 0.5647 | Reduce | 0.3 | 1.8823 | 0.5647 | H3 | 3 | Stable | 0.8 | 86 | 139 | 148 | 131.6667 | 0.2 | 9 | 57 | 65 | 50.3333 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-039 | Project_062_Risk-039 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Delay of tasks from our / Customer | Person_459 | 2017-07-21 | 2018-04-22 | 0.25 | 0.83659 | 0.20915 | Avoid | 0.15 | 0.83659 | 0.12549 | H3 | 3 | Stable | [10 empty] | 0 | 40 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-017 | Project_062_Risk-017 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer platform Schedule Unknown | Person_459 | 2017-07-21 | 2018-10-22 | 0.2 | 2.5098 | 0.50196 | Avoid | 0.1 | 2.5098 | 0.25098 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK031 | Project_042_RISK031 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours 1st July to 30th September | Person_455 | 2020-11-19 01:00 | 2021-02-19 01:00 | 0.2 | 12.6326 | 4.4214 | Accept | 0.15 | 12.6326 | 3.1581 | H2 | 4 | Stable | 0.8 | 115 | 136 | 151 | 135 | 0.8 | 115 | 136 | 151 | 135 | 0 | 25 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-037 | Project_062_Risk-037 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Server availability | Person_459 | 2017-07-21 | 2018-04-22 | 0.35 | 4.183 | 1.464 | Avoid | 0.1 | 4.183 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 71.4286 | 1 | 2.1429
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-038 | Project_062_Risk-038 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Delay in start of Phase 2 | Person_459 | 2017-07-21 | 2018-02-20 | 0.2 | 2.0915 | 0.4183 | Avoid | 0.2 | 2.0915 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-016 | Project_062_Risk-016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Supplier Component Unavailability | Person_664 | 2017-07-21 | 2018-05-15 | 0.3 | 2.0927 | 0.62782 | Reduce | 0.2 | 2.0915 | 0.4183 | H3 | 3 | Stable | 0.8 | 116 | 121 | 145 | 124.1667 | 0.4 | 22 | 49 | 62 | 46.6667 | 0.059964 | 33.3333 | 0 | 0.035978
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK030 | Project_042_RISK030 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours 31st March to 29 June | Person_455 | 2020-08-20 01:00 | 2020-11-18 01:00 | 0.2 | 1.5477 | 0.15477 | Accept | 0.15 | 1.5477 | 0.15167 | H2 | 4 | Stable | 0.8 | 85 | 138 | 157 | 132.3333 | 0.8 | 85 | 138 | 157 | 132.3333 | 0 | 25 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-050 | Project_062_Risk-050 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SW v1.2 in use on some Hardware | Person_245 | 2017-07-21 | 2018-11-21 | 0.1 | 4.183 | 0.4183 | Avoid | 0.1 | 4.183 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-020 | Project_062_Risk-020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Security Encryption Solution | Person_245 | 2017-07-21 | 2018-09-20 | 0.25 | 4.183 | 1.0457 | Reduce | 0.2 | 4.183 | 0.83659 | H2 | 4 | Stable | 0.5 | 111 | 138 | 142 | 134.1667 | 0.3 | 9 | 50 | 67 | 46 | 0 | 20 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-042 | Project_062_Risk-042 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Open source software packages | Person_664 | 2017-07-21 | 2018-04-22 | 0.3 | 1.0457 | 0.31372 | Avoid | 0.2 | 1.0457 | 0.20915 | H3 | 3 | Stable | [10 empty] | 0 | 33.3333 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK037 | Project_042_RISK037 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 1 | Person_455 | 2020-05-23 | 2021-05-22 | 0.14 | 6.2744 | 1.8823 | Accept | 0.11 | 6.2744 | 1.5686 | H2 | 4 | Stable | 0.7 | 82 | 132 | 143 | 125.5 | 0.7 | 82 | 132 | 143 | 125.5 | 0 | 21.4286 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-043 | Project_062_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | User response | Person_664 | 2017-07-21 | 2019-02-21 | 0.35 | 3.3464 | 1.1712 | Avoid | 0.25 | 3.3464 | 0.83659 | H2 | 4 | Stable | [10 empty] | 0 | 28.5714 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-040 | Project_062_Risk-040 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Custom code or open source software | Person_664 | 2017-07-21 | 2018-04-22 | 0.25 | 0.83659 | 0.20915 | Avoid | 0.15 | 0.83659 | 0.12549 | H3 | 3 | Stable | [10 empty] | 0 | 40 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-041 | Project_062_Risk-041 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Incompatible software package versions | Person_664 | 2017-07-21 | 2018-04-22 | 0.3 | 1.0457 | 0.31372 | Avoid | 0.2 | 1.0457 | 0.20915 | H3 | 3 | Stable | [10 empty] | 0 | 33.3333 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-046 | Project_062_Risk-046 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Additional Java licences | Person_245 | 2017-07-21 | 2018-10-22 | 0.1 | 0.84775 | 0.084775 | Avoid | 0.1 | 0.84775 | 0.084775 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-047 | Project_062_Risk-047 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Redhat6 on PCI shelf | Person_245 | 2017-07-21 | 2018-07-22 | 0.3 | 7.1808 | 2.1542 | Avoid | 0.3 | 7.1808 | 2.1542 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-025 | Project_062_Risk-025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | System Obsolescence Risk | Person_543 | 2017-07-21 | 2018-04-22 | 0.3 | 2.0915 | 0.62744 | Avoid | 0.2 | 2.0915 | 0.4183 | H2 | 4 | Stable | [10 empty] | 0 | 33.3333 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-022 | Project_062_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Registers Might Be Unstable | Person_479 | 2017-07-21 | 2018-04-22 | 0.1 | 0.8589 | 0.08589 | Reduce | 0.1 | 0.8589 | 0.08589 | H3 | 3 | Stable | 0.7 | 119 | 140 | 152 | 138.5 | 0.2 | 32 | 46 | 61 | 46.1667 | 0 | 0 | 1 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-001 | Project_062_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Supplier servers | Person_664 | 2017-10-21 | 2018-05-23 | 0.5 | 1.2549 | 0.62744 | Reduce | 0.5 | 1.2549 | 0.62744 | H2 | 4 | Stable | 0.5 | 116 | 126 | 143 | 127.1667 | 0.3 | 2 | 41 | 64 | 38.3333 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-023 | Project_062_Risk-023 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Change In Security Boundary | Person_031 | 2017-07-21 | 2019-02-21 | 0.3 | 4.6013 | 1.3804 | Reduce | 0.2 | 4.6013 | 0.92025 | H3 | 3 | Stable | 0.7 | 115 | 133 | 157 | 134 | 0.2 | 7 | 47 | 75 | 45 | 0 | 33.3333 | 1 | 1
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-026 | Project_062_Risk-026 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Lack of Suitably Qualified and experienced staff availability ILS resource | Person_543 | 2017-07-21 | 2019-02-21 | 0.3 | 2.0915 | 0.62744 | Reduce | 0.2 | 2.0915 | 0.4183 | H2 | 4 | Stable | 0.9 | 93 | 134 | 157 | 131 | 0.1 | 17 | 48 | 63 | 45.3333 | 0 | 33.3333 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-048 | Project_062_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software lockdown features | Person_245 | 2017-07-21 | 2018-11-21 | 0.5 | 0.71808 | 0.35904 | Reduce | 0.5 | 0.71808 | 0.35904 | H2 | 4 | Stable | 0.8 | 84 | 126 | 155 | 123.8333 | 0.2 | 25 | 54 | 77 | 53 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK036 | Project_042_RISK036 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 2 | Person_455 | 2019-05-24 | 2020-05-22 | 0.25 | 1.9325 | 1.2561 | Accept | 0.2 | 1.9325 | 1.2561 | H2 | 4 | Stable | 0.8 | 112 | 139 | 148 | 136 | 0.8 | 112 | 139 | 148 | 136 | 0 | 20 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK039 | Project_042_RISK039 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality Issues 16th August to 15th August | Person_540 | 2020-01-06 01:00 | 2021-01-04 01:00 | 0.1 | 1.2124 | 0.24249 | Accept | 0.08 | 1.2124 | 0.24249 | H2 | 4 | Stable | 0.6 | 111 | 128 | 159 | 130.3333 | 0.6 | 111 | 128 | 159 | 130.3333 | 0 | 20 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK038 | Project_042_RISK038 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality Issues 16th August to 15th August | Person_540 | 2019-01-06 01:00 | 2020-01-05 01:00 | 0.1 | 1.6166 | 0.32332 | Accept | 0.08 | 1.6166 | 0.32332 | H2 | 4 | Stable | 0.5 | 113 | 127 | 147 | 128 | 0.5 | 113 | 127 | 147 | 128 | 0 | 20 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK033 | Project_042_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st April to 30 June | Person_455 | 2019-08-22 01:00 | 2019-11-20 01:00 | 0.2 | 2.0207 | 0.20207 | Accept | 0.15 | 2.0207 | 0.20207 | H2 | 4 | Stable | 0.7 | 112 | 121 | 154 | 125 | 0.7 | 112 | 121 | 154 | 125 | 0 | 25 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK032 | Project_042_RISK032 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Level of Effort Hours 1st October to 31st December | Person_455 | 2021-02-20 01:00 | 2021-05-22 | 0.2 | 2.0207 | 0.20207 | Accept | 0.15 | 2.0207 | 0.20207 | H2 | 4 | Stable | 0.6 | 90 | 136 | 148 | 130.3333 | 0.6 | 90 | 136 | 148 | 130.3333 | 0 | 25 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK035 | Project_042_RISK035 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st October to 31st December | Person_455 | 2021-02-20 01:00 | 2021-05-22 | 0.2 | 2.0207 | 0.20207 | Accept | 0.15 | 2.0207 | 0.20207 | H2 | 4 | Stable | 0.9 | 118 | 124 | 157 | 128.5 | 0.9 | 118 | 124 | 157 | 128.5 | 0 | 25 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK034 | Project_042_RISK034 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st July to 30 September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 0.2 | 1.2124 | 0.12124 | Accept | 0.15 | 1.2124 | 0.12124 | H2 | 4 | Stable | 0.5 | 103 | 127 | 158 | 128.1667 | 0.5 | 103 | 127 | 158 | 128.1667 | 0 | 25 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK040 | Project_042_RISK040 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st May to 30 Oct | Person_455 | 2019-09-21 01:00 | 2020-03-21 | 0.1 | 0.60622 | 0.18186 | Accept | 0.07 | 0.60622 | 0.18186 | H2 | 4 | Stable | 0.9 | 113 | 122 | 155 | 126 | 0.9 | 113 | 122 | 155 | 126 | 0 | 30 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK042 | Project_042_RISK042 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st February to 14th July | Person_455 | 2020-06-23 | 2020-12-03 01:00 | 0.1 | 0.64865 | 0.32433 | Accept | 0.08 | 0.64865 | 0.32433 | H2 | 4 | Stable | 0.6 | 95 | 130 | 158 | 128.8333 | 0.6 | 95 | 130 | 158 | 128.8333 | 0 | 20 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK041 | Project_042_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st Jan | Person_455 | 2020-03-23 | 2020-06-22 | 0.1 | 0.80829 | 0.16166 | Accept | 0.08 | 0.80829 | 0.16166 | H2 | 4 | Stable | 0.5 | 114 | 132 | 148 | 131.6667 | 0.5 | 114 | 132 | 148 | 131.6667 | 0 | 20 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-20 23:00 | 2017-08-19 23:00 | 0.1 | 53.0293 | 5.3029 | Reduce | 0.1 | 53.0293 | 5.3029 | H3 | 3 | Worsening | 0.6 | 81 | 139 | 142 | 129.8333 | 0.2 | 34 | 55 | 75 | 54.8333 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Local customer Engineers in country | Person_455 | 2019-03-22 | 2019-05-23 | 0.1 | 0.20788 | 0.068599 | Accept | 0.05 | 0.052336 | 0.0057569 | H2 | 4 | Stable | 0.6 | 104 | 132 | 158 | 131.6667 | 0.6 | 104 | 132 | 158 | 131.6667 | 74.8236 | 50 | 0 | 44.8942
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-20 23:00 | 2017-08-19 23:00 | 0.1 | 7.7469 | 0.77469 | Reduce | 0.1 | 7.7469 | 0.77469 | H3 | 3 | Stable | 0.7 | 109 | 125 | 151 | 126.6667 | 0.3 | 1 | 48 | 76 | 44.8333 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Volume of production tools and Jigs | Person_279 | 2016-11-23 | 2021-11-23 | 0.35 | 11.3437 | 0.56718 | Accept | 0.2 | 11.3437 | 0.56718 | H2 | 4 | Stable | 0.8 | 100 | 125 | 147 | 124.5 | 0.8 | 100 | 125 | 147 | 124.5 | 0 | 42.8571 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2017-02-20 01:00 | 2018-05-22 | 0.1 | 1.6721 | 0.66883 | Accept | 0.1 | 1.6721 | 0.66883 | H3 | 3 | Stable | 0.6 | 90 | 134 | 150 | 129.3333 | 0.6 | 90 | 134 | 150 | 129.3333 | 0 | 0 | 1 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unforseen and substantial increase in Repairs workload during new build production period. | Person_238 | 2017-10-23 01:00 | 2019-08-21 01:00 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.03 | 1.5434 | 0.046303 | H3 | 3 | Stable | 0.6 | 81 | 140 | 152 | 132.1667 | 0.2 | 18 | 50 | 61 | 46.5 | 0 | 90 | 1 | 2.7
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK007 | Project_041_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Advanced production of products using a Qual. standard component rather than a Prod. standard | Person_547 | 2017-10-21 01:00 | 2018-07-06 | 0.49 | 1.2862 | 0.63024 | Reduce | 0.2 | 1.2862 | 0.25724 | H3 | 3 | Stable | 0.6 | 107 | 127 | 151 | 127.6667 | 0.1 | 37 | 58 | 78 | 57.8333 | 0 | 59.1837 | 1 | 1.7755
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_693 | 2017-07-21 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.5 | 91 | 130 | 146 | 126.1667 | 0.3 | 33 | 46 | 67 | 47.3333 | 0 | 50 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2017-04-22 | 2018-05-22 | 0.75 | 10.7184 | 8.0388 | Reduce | 0.05 | 2.4052 | 0.12026 | H3 | 3 | Stable | 0.8 | 89 | 140 | 155 | 134 | 0.3 | 21 | 54 | 78 | 52.5 | 77.56 | 93.3333 | 0 | 46.536
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK003 | Project_024_RISK003 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance | Person_288 | 2017-12-21 01:00 | 2018-08-21 | 0.31667 | 1.9722 | 0.98609 | Accept | 0.007456 | 1.9722 | 0.98609 | H2 | 4 | Stable | 0.7 | 104 | 137 | 154 | 134.3333 | 0.7 | 104 | 137 | 154 | 134.3333 | 0 | 97.6455 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Management Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 0.3 | 2.5081 | 1.2541 | Accept | 0.3 | 2.5081 | 1.2541 | H1 | 5 | Improving | 0.7 | 112 | 122 | 150 | 125 | 0.7 | 112 | 122 | 150 | 125 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment (Second Test Set) | Person_238 | 2017-05-23 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.05 | 0.68598 | 0.034299 | H3 | 3 | Improving | 0.6 | 97 | 140 | 146 | 133.8333 | 0.4 | 9 | 45 | 62 | 41.8333 | 0 | 80 | 1 | 2.4
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before part b finished | Person_119 | 2016-10-20 01:00 | 2018-04-21 | 0.3 | 3.7514 | 0.37514 | Accept | 0.27 | 3.7514 | 0.37514 | H2 | 4 | Worsening | 0.6 | 89 | 131 | 157 | 128.3333 | 0.6 | 89 | 131 | 157 | 128.3333 | 0 | 10 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2017-05-23 | 2019-08-20 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Stable | 0.8 | 100 | 128 | 155 | 127.8333 | 0.2 | 25 | 58 | 70 | 54.5 | 0 | 60 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_238 | 2017-04-22 | 2018-05-22 | 0.25 | 3.3227 | 0.83067 | Reduce | 0.012 | 3.3055 | 0.039667 | H3 | 3 | Stable | 0.8 | 114 | 137 | 160 | 137 | 0.4 | 12 | 59 | 66 | 52.3333 | 0.51615 | 95.2 | 1 | 3.1657
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_693 | 2017-05-23 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.1 | 0.77172 | 0.077172 | H3 | 3 | Stable | 0.9 | 114 | 139 | 142 | 135.3333 | 0.2 | 8 | 48 | 64 | 44 | 0 | 60 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_693 | 2017-05-23 | 2018-04-21 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.02 | 6.431 | 0.12862 | H3 | 3 | Improving | 0.8 | 98 | 122 | 158 | 124 | 0.2 | 22 | 57 | 65 | 52.5 | -47.0588 | 86.6667 | 1 | -25.6353
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Reduce touch labour if Production readiness programme successful | Person_238 | 2017-05-23 | 2018-03-23 | 0.3 | 1.5606 | 0.46818 | Exploit | 0.5 | 1.5606 | 0.7803 | H2 | 4 | Stable | [10 empty] | 0 | -66.6667 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Survey costs | Person_618 | 2016-04-22 | 2018-08-21 | 0.2 | 13.2573 | 2.6515 | Avoid | 0.2 | 13.2573 | 2.6515 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-034 | Project_062_Risk-034 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Long lead Procurement price increases | Person_664 | 2017-07-21 | 2018-04-22 | 0.25 | 33.9324 | 10.1797 | Accept | 0.25 | 33.9324 | 10.1797 | H2 | 4 | Stable | 0.7 | 94 | 124 | 148 | 123 | 0.7 | 94 | 124 | 148 | 123 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-099 | Project_008_Risk-099 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Risk on Consumables Exposure | Person_639 | 2017-08-04 | 2018-08-21 | 0.5 | 5.6817 | 2.8408 | Reduce | 0.5 | 5.6817 | 2.8408 | H3 | 3 | Stable | 0.6 | 82 | 136 | 157 | 130.5 | 0.3 | 28 | 40 | 71 | 43.1667 | 0 | 0 | 1 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-018 | Project_062_Risk-018 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Prioritisation - new or less experienced staff | Person_459 | 2017-07-21 | 2018-11-20 | 0.35 | 14.0464 | 4.2139 | Accept | 0.25 | 14.0464 | 4.2139 | H2 | 4 | Improving | 0.9 | 97 | 138 | 150 | 133.1667 | 0.9 | 97 | 138 | 150 | 133.1667 | 0 | 28.5714 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-019 | Project_062_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Obsolescence | Person_543 | 2017-07-21 | 2018-05-15 | 0.1 | 9.4695 | 4.7347 | Accept | 0.098 | 9.4695 | 4.7347 | H3 | 3 | Stable | 0.9 | 111 | 139 | 146 | 135.5 | 0.9 | 111 | 139 | 146 | 135.5 | 0 | 2 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-021 | Project_062_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Hardware CoSupplierng | Person_664 | 2017-07-21 | 2018-07-20 | 0.3 | 15.8141 | 3.9535 | Accept | 0.25 | 15.8141 | 3.9535 | H2 | 4 | Stable | 0.7 | 84 | 134 | 147 | 127.8333 | 0.7 | 84 | 134 | 147 | 127.8333 | 0 | 16.6667 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-060 | Project_062_Risk-060 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Software Port between networks | Person_479 | 2017-09-20 | 2017-12-21 | 0.65 | 7.2784 | 2.1835 | Accept | 0.65 | 7.2784 | 2.1835 | H1 | 5 | Stable | 0.9 | 111 | 123 | 147 | 125 | 0.9 | 111 | 123 | 147 | 125 | 0 | 0 | 0 | 0
2017-12-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-010 | Project_052_Risk-010 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Potential update of software / hardware required during the 3 year support period (RESOURCE) | Person_376 | 2017-08-19 01:00 | 2018-02-19 01:00 | 0.25 | 3.1214 | 0.78035 | Transfer | 0.25 | 3.1214 | 0.78035 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-04-20 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.5 | 87 | 131 | 151 | 127 | 0.1 | 14 | 42 | 63 | 40.8333 | 0 | 25 | 0 | 0
2017-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_077 | 2016-01-22 01:00 | 2018-02-17 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H1 | 5 | Improving | 0.8 | 109 | 129 | 159 | 130.6667 | 0.1 | 5 | 56 | 69 | 49.6667 |  | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-19 23:00 | 0.05 | 6.3794 | 1.2759 | Accept | 0.05 | 6.3794 | 1.2759 | H3 | 3 | Stable | 0.8 | 92 | 140 | 153 | 134.1667 | 0.8 | 92 | 140 | 153 | 134.1667 | 0 | 0 | 1 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK002 | Project_041_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Component Technical risk using new material | Person_653 | 2017-09-20 01:00 | 2018-07-20 | 0.5 | 23.5255 | 11.7628 | Accept | 0.4 | 23.5255 | 11.7628 | H2 | 4 | Stable | 0.5 | 105 | 138 | 156 | 135.5 | 0.5 | 105 | 138 | 156 | 135.5 | 0 | 20 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK013 | Project_041_RISK013 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional components validation | Person_693 | 2017-07-15 | 2018-04-22 | 0.4 | 60.4367 | 3.0218 | Accept | 0.4 | 60.4367 | 3.0218 | H2 | 4 | Stable | 0.5 | 93 | 127 | 148 | 124.8333 | 0.5 | 93 | 127 | 148 | 124.8333 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Risk of not being able to perform Tests | Person_238 | 2017-12-21 01:00 | 2019-01-21 01:00 | 0.5 | 22.384 | 11.192 | Accept | 0.5 | 22.384 | 11.192 | H2 | 4 | Stable | 0.7 | 105 | 126 | 151 | 126.6667 | 0.7 | 105 | 126 | 151 | 126.6667 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_238 | 2017-05-23 | 2019-01-21 01:00 | 0.5 | 3.772 | 2.6404 | Accept | 0.5 | 3.772 | 2.6404 | H2 | 4 | Stable | 0.8 | 80 | 121 | 160 | 120.6667 | 0.8 | 80 | 121 | 160 | 120.6667 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_547 | 2017-05-23 | 2018-05-22 | 0.1 | 5.8198 | 4.0739 | Accept | 0.1 | 5.8198 | 4.0739 | H3 | 3 | Stable | 0.9 | 107 | 135 | 152 | 133.1667 | 0.9 | 107 | 135 | 152 | 133.1667 | 0 | 0 | 1 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 1.3834 | 0.55336 | H2 | 4 | Stable | 0.5 | 104 | 139 | 156 | 136 | 0.2 | 28 | 46 | 68 | 46.6667 | 65.054 | 20 | 0 | 39.0324
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_703 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 6.3069 | 0.94603 | H3 | 3 | Stable | 0.5 | 83 | 127 | 151 | 123.6667 | 0.4 | 12 | 44 | 73 | 43.5 | -0.14286 | 70 | 1 | 2.0143
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production, Procurement or Engineering | Person_725 | 2018-01-21 01:00 | 2019-05-23 | 0.1 | 2.2586 | 0.90343 | Accept | 0.1 | 2.2586 | 0.90343 | H3 | 3 | Stable | 0.5 | 87 | 138 | 149 | 131.3333 | 0.5 | 87 | 138 | 149 | 131.3333 | 0 | 0 | 1 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-085 | Project_008_SER-085 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Insufficient LOE to manage the supply chain with reducing number of spares | Person_639 | 2017-04-22 | 2018-08-21 | 0.25 | 2.9272 | 1.4636 | Accept | 0.25 | 2.9272 | 1.4636 | H3 | 3 | Stable | 0.5 | 81 | 137 | 142 | 128.5 | 0.5 | 81 | 137 | 142 | 128.5 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_567 | 2017-08-21 01:00 | 2018-08-21 | 0.45 | 4.4984 | 2.2492 | Accept | 0.45 | 4.4984 | 2.2492 | H2 | 4 | Stable | 0.6 | 100 | 121 | 142 | 121 | 0.6 | 100 | 121 | 142 | 121 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Lack of Spares Availability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 0.3 | 1.6962 | 0.33923 | Accept | 0.3 | 1.6962 | 0.33923 | H3 | 3 | Stable | 0.6 | 94 | 137 | 156 | 133 | 0.6 | 94 | 137 | 156 | 133 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-148 | Project_008_SER-148 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Demands but not provisioned | Person_639 | 2017-08-21 01:00 | 2018-08-21 | 0.3 | 3.0513 | 0.61026 | Accept | 0.3 | 3.0513 | 0.61026 | H3 | 3 | Stable | 0.7 | 95 | 126 | 151 | 125 | 0.7 | 95 | 126 | 151 | 125 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-094 | Project_008_Risk-094 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Consumable Stock Levels | Person_567 | 2017-04-22 | 2018-08-21 | 0.5 | 18.9062 | 9.4531 | Accept | 0.5 | 18.9062 | 9.4531 | H3 | 3 | Stable | 0.9 | 111 | 124 | 144 | 125.1667 | 0.9 | 111 | 124 | 144 | 125.1667 | 0 | 0 | 1 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-000 | Project_008_SER-000 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_567 | 2018-05-22 | 2018-08-21 | 0.25 | 3.7214 | 0.93035 | Accept | 0.25 | 3.7214 | 0.93035 | H3 | 3 | Stable | 0.9 | 88 | 122 | 148 | 120.6667 | 0.9 | 88 | 122 | 148 | 120.6667 | 0 | 0 | 0 | 0
2017-12-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-013 | Project_052_Risk-013 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional material and effort required to support the delta equipment | Person_376 | 2017-08-19 01:00 | 2018-03-22 | 0.3 | 3.7207 | 0.93016 | Accept | 0.3 | 3.7207 | 0.93016 | H3 | 3 | Stable | 0.8 | 94 | 126 | 153 | 125.1667 | 0.8 | 94 | 126 | 153 | 125.1667 | 0 | 0 | 0 | 0
2017-12-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-004 | Project_052_Risk-004 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | IOC Risk for Phase 1b | Person_488 | 2017-08-19 01:00 | 2018-03-22 | 0.1 | 9.9467 | 7.9574 | Accept | 0.1 | 9.9467 | 7.9574 | H3 | 3 | Stable | 0.9 | 90 | 139 | 157 | 133.8333 | 0.9 | 90 | 139 | 157 | 133.8333 | 0 | 0 | 0 | 0
2017-12-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-001 | Project_052_Risk-001 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Greater modification than expected for system uplift | Person_376 | 2017-08-19 01:00 | 2018-03-22 | 0.1 | 8.2789 | 2.4837 | Accept | 0.1 | 8.2789 | 2.4837 | H3 | 3 | Stable | 0.5 | 101 | 130 | 146 | 127.8333 | 0.5 | 101 | 130 | 146 | 127.8333 | 0 | 0 | 0 | 0
2017-12-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-009 | Project_052_Risk-009 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | System acceptance not costed in line with Customer expectations | Person_651 | 2017-08-19 01:00 | 2018-03-22 | 0.1 | 10.4822 | 2.6205 | Accept | 0.1 | 10.4822 | 2.6205 | H3 | 3 | Stable | 0.6 | 97 | 129 | 150 | 127.1667 | 0.6 | 97 | 129 | 150 | 127.1667 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | FOC Acceptance | Person_499 | 2015-11-21 01:00 | 2018-06-23 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.15 | 8.471 | 1.2706 | H3 | 3 | Stable | 0.5 | 100 | 134 | 159 | 132.5 | 0.3 | 7 | 40 | 64 | 38.5 | -99.9999 | 57.1429 | 1 | -58.2857
2017-12-21 | ORG_001 | BA_002 | Portfolio_008 | Project_057 | Risk-01 | Project_057_Risk-01 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Cable | Person_464 | 2015-08-22 | 2016-12-21 | 0.1 | 12.6408 | 1.2641 | Avoid | 0.1 | 0.23232 | 0.023232 | H2 | 4 | Improving | [10 empty] | 98.1622 | 0 | 0 | 58.8973
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2018-08-21 | 0.15 | 0.58983 | 0.088474 | -- | 0.15 | 0.58983 | 0.088474 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2018-04-22 | 2018-09-20 01:00 | 0.2 | 0.62279 | 0.12456 | Avoid | 0.2 | 0.62279 | 0.12456 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-09-20 01:00 | 0.2 | 1.8854 | 0.37708 | Reduce | 0.2 | 1.8854 | 0.37708 | H2 | 4 | Stable | 0.7 | 112 | 137 | 159 | 136.5 | 0.3 | 17 | 57 | 74 | 53.1667 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2018-06-23 | 2018-10-21 01:00 | 0.4 | 1.4138 | 0.56551 | Reduce | 0.4 | 1.4138 | 0.56551 | H2 | 4 | Stable | 0.6 | 99 | 127 | 145 | 125.3333 | 0.2 | 1 | 49 | 67 | 44 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-126 | Project_011_Risk-126 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Increase in regression testing | Person_140 | 2017-11-20 01:00 | 2018-05-21 | 0.25 | 0.12558 | 0.031395 | -- | 0.25 | 0.12558 | 0.031395 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-10-19 01:00 | 2018-08-21 | 0.2 | 0.081826 | 0.016365 | Reduce | 0.2 | 0.081826 | 0.016365 | H2 | 4 | Stable | 0.8 | 91 | 125 | 141 | 122 | 0.3 | 15 | 58 | 63 | 51.6667 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Pick up and Drop off of Software Resource | Person_230 | 2017-12-19 01:00 | 2018-07-20 | 0.6 | 0.36106 | 0.21663 | Avoid | 0.6 | 0.36106 | 0.21663 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-09-20 01:00 | 0.4 | 0.19206 | 0.076826 | -- | 0.4 | 0.19206 | 0.076826 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-08-22 01:00 | 2018-11-20 01:00 | 0.4 | 0.58017 | 0.23207 | Avoid | 0.4 | 0.58017 | 0.23207 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.4 | 0.11365 | 0.045459 | -- | 0.4 | 0.11365 | 0.045459 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-11-20 01:00 | 0.55 | 0.32389 | 0.17814 | Reduce | 0.55 | 0.32389 | 0.17814 | H1 | 5 | Stable | 0.7 | 100 | 124 | 152 | 124.6667 | 0.2 | 30 | 57 | 77 | 55.8333 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_182 | 2018-06-23 | 2018-10-21 01:00 | 0.4 | 0.19206 | 0.076826 | -- | 0.4 | 0.19206 | 0.076826 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 0.3 | 0.11933 | 0.035799 | -- | 0.3 | 0.022161 | 0.0066484 | H3 | 3 | Stable | [10 empty] | 81.4286 | 0 | 0 | 48.8571
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-117 | Project_011_Risk-117 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Avaliability for testing/reviews | Person_147 | 2018-04-06 | 2018-09-20 01:00 | 0.35 | 0 | 0 | Avoid | 0.35 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-128 | Project_011_Risk-128 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Incorrect Maps used during Qualification | Person_147 | 2017-04-22 | 2018-04-22 | 0.5 | 0.05688 | 0.02844 | Transfer | 0.5 | 0.05688 | 0.02844 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-129 | Project_011_Risk-129 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Signature of Work Authorisation documents | Person_140 | 2017-05-24 | 2018-04-21 | 0.4 | 0.12643 | 0.050573 | -- | 0.4 | 0.12643 | 0.050573 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-130 | Project_011_Risk-130 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer does not accept Voice Pronounciation | Person_187 | 2017-05-24 | 2018-02-19 01:00 | 0.4 | 0.090918 | 0.036367 | Avoid | 0.4 | 0.090918 | 0.036367 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-21 21:00 | 2016-12-20 21:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.6 | 114 | 137 | 156 | 136.3333 | 0.4 | 32 | 59 | 75 | 57.1667 | 47 | 0 | 0 | 28.2
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-21 21:00 | 2016-12-20 21:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-18 21:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.2 | 1.5935 | 0.3187 | H3 | 3 | Stable | 0.9 | 112 | 132 | 147 | 131.1667 | 0.4 | 25 | 45 | 69 | 45.6667 | 50 | 50 | 1 | 31.5
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK003 | Project_060_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Misalignment of Critical Resource | Person_312 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.7 | 0.5769 | 0.40383 | Reduce | 0.5 | 0.5769 | 0.28845 | H2 | 4 | Stable | 0.5 | 87 | 135 | 148 | 129.1667 | 0.4 | 16 | 53 | 62 | 48.3333 | 0 | 28.5714 | 0 | 0
2017-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2018-02-19 01:00 | 0.05 | 1.029 | 0.30869 | Accept | 0.05 | 1.029 | 0.30869 | H3 | 3 | Improving | 0.8 | 107 | 134 | 144 | 131.1667 | 0.8 | 107 | 134 | 144 | 131.1667 | 0 | 0 | 1 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK010 | Project_041_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Assembly - Testing | Person_547 | 2018-01-28 01:00 | 2018-03-30 | 0.3 | 0.51448 | 0.15434 | -- | 0.3 | 0.51448 | 0.15434 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK021 | Project_048_RISK021 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Late Delivery | Person_261 | 2018-01-14 01:00 | 2018-11-20 01:00 | 0.7 | 0 | 0 | Reduce | 0.7 | 0 | 0 | H1 | 5 | Stable | 0.7 | 105 | 139 | 150 | 135.1667 | 0.3 | 5 | 54 | 71 | 48.6667 |  | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK003 | Project_001_RISK003 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Non-Recurring Engineering higher than expected | Person_674 | 2017-12-21 01:00 | 2018-08-21 | 0.5 | 16.0059 | 8.0029 | Reduce | 0.2 | 8.0029 | 1.6006 | H3 | 3 | Improving | 0.9 | 116 | 139 | 157 | 138.1667 | 0.2 | 7 | 55 | 76 | 50.5 | 50 | 60 | 0 | 30
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-01-12 01:00 | 0.8 | 18.0459 | 14.4367 | Reduce | 0.2 | 3.0076 | 0.60153 | H3 | 3 | Stable | 0.9 | 92 | 125 | 159 | 125.1667 | 0.3 | 39 | 59 | 73 | 58 | 83.3335 | 75 | 1 | 52.2501
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 0.4 | 5.1004 | 2.0402 | Reduce | 0.2 | 2.5506 | 0.51013 | H3 | 3 | Stable | 0.8 | 115 | 126 | 156 | 129.1667 | 0.3 | 26 | 53 | 69 | 51.1667 | 49.9917 | 50 | 0 | 29.995
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-21 01:00 | 2018-04-22 | 0.5 | 28.0275 | 14.0137 | Reduce | 0.1 | 28.0275 | 2.8027 | H3 | 3 | Stable | 0.6 | 88 | 121 | 155 | 121.1667 | 0.4 | 9 | 54 | 71 | 49.3333 | 0 | 80 | 1 | 2.4
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | R054 | Project_066_R054 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | System Cybersecurity shortfalls | Person_689 | 2017-01-21 01:00 | 2024-05-23 | 0.8 | 15.7936 | 12.6349 | Reduce | 0.5 | 15.7936 | 7.8968 | H1 | 5 | Stable | 0.9 | 114 | 129 | 153 | 130.5 | 0.3 | 4 | 41 | 75 | 40.5 | 0 | 37.5 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | R181 | Project_066_R181 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | USB Hub start up issues | Person_365 | 2017-01-21 01:00 | 2024-05-23 | 0.8 | 12.1204 | 9.6963 | Reduce | 0.2 | 12.1204 | 2.4241 | H2 | 4 | Stable | 0.9 | 96 | 138 | 160 | 134.6667 | 0.2 | 24 | 53 | 67 | 50.5 | 0 | 75 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK021 | Project_063_RISK021 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Late Delivery | Person_261 | 2018-01-14 01:00 | 2018-11-20 01:00 | 0.7 | 0 | 0 | Reduce | 0.7 | 0 | 0 | H1 | 5 | Stable | 0.7 | 81 | 130 | 156 | 126.1667 | 0.1 | 28 | 59 | 76 | 56.6667 |  | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-115 | Project_011_Risk-115 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | SMEs are unavailable to support project activites | Person_230 | 2016-07-21 | 2018-08-21 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-058 | Project_011_Risk-058 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Programme delays | Person_147 | 2013-11-20 01:00 | 2018-11-20 01:00 | 0.25 | 1.5013 | 0.37532 | Reduce | 0.25 | 1.5013 | 0.37532 | H2 | 4 | Stable | 0.9 | 109 | 126 | 145 | 126.3333 | 0.1 | 4 | 58 | 78 | 52.3333 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-131 | Project_011_Risk-131 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Support team have not covered all obligations in support contract | Person_147 | 2016-05-24 | 2018-08-17 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-137 | Project_011_Risk-137 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Subsystem will not match Fidelity of Customer - does not accept | Person_147 | 2018-02-16 01:00 | 2018-09-20 01:00 | 0.4 | 0.11876 | 0.047505 | Avoid | 0.2 | 0.11876 | 0.023752 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2017-09-20 01:00 | 2018-04-21 | 0.15 | 0.28639 | 0.042959 | -- | 0.15 | 0.28639 | 0.042959 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2018-05-22 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.8 | 85 | 135 | 154 | 129.8333 | 0.4 | 39 | 42 | 75 | 47 | 0 | 40 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 0.92411 | 0.55447 | Reduce | 0.5 | 0.36965 | 0.18482 | H2 | 4 | Stable | 0.6 | 98 | 130 | 145 | 127.1667 | 0.4 | 22 | 40 | 74 | 42.6667 | 60 | 16.6667 | 0 | 36
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 01:00 | 2018-04-21 | 0.2 | 4.0661 | 0.81322 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.9 | 109 | 137 | 144 | 133.5 | 0.3 | 7 | 48 | 77 | 46 | 0 | 75 | 1 | 2.25
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.5 | 0.46206 | 0.23103 | H1 | 5 | Stable | 0.5 | 85 | 135 | 142 | 127.8333 | 0.4 | 13 | 56 | 73 | 51.6667 | 58.3333 | 16.6667 | 0 | 35
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 01:00 | 2018-05-22 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.6 | 105 | 135 | 156 | 133.5 | 0.2 | 23 | 59 | 65 | 54 | 0 | 50 | 1 | 1.5
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2018-05-22 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.6 | 88 | 134 | 147 | 128.5 | 0.1 | 7 | 48 | 68 | 44.5 | 0 | 25 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_693 | 2012-06-01 | 2018-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Improving | 0.9 | 104 | 137 | 145 | 132.8333 | 0.4 | 18 | 53 | 78 | 51.3333 | 0 | 40 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2018-05-21 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Stable | [10 empty] | 0 | 37.5 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of the platforms for modification | Person_496 | 2014-01-21 01:00 | 2019-04-10 | 0.67 | 1.8482 | 0.55447 | Accept | 0.67 | 1.8482 | 0.36965 | H2 | 4 | Stable | 0.9 | 85 | 123 | 146 | 120.5 | 0.9 | 85 | 123 | 146 | 120.5 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2018-02-19 01:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.8 | 115 | 122 | 158 | 126.8333 | 0.4 | 11 | 41 | 65 | 40 | 90 | 75 | 1 | 56.25
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_523 | 2015-01-22 01:00 | 2018-06-23 | 0.35 | 0.36965 | 0.25875 | Accept | 0.2 | 0.36965 | 0.25875 | H2 | 4 | Stable | 0.6 | 101 | 122 | 154 | 123.8333 | 0.6 | 101 | 122 | 154 | 123.8333 | 0 | 42.8571 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK010 | Project_010_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Use of Lead components | Person_359 | 2012-05-23 | 2025-04-22 | 0.05 | 1.8482 | 0.092411 | Reduce | 0.05 | 1.8482 | 0.092411 | H3 | 3 | Stable | 0.6 | 116 | 135 | 147 | 133.8333 | 0.1 | 1 | 41 | 77 | 40.3333 | 0 | 0 | 1 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK016 | Project_038_RISK016 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Supplier Quality Issues | Person_397 | 2012-11-20 01:00 | 2018-10-21 01:00 | 0.5 | 5.0339 | 2.517 | Avoid | 0.5 | 5.0339 | 2.517 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK018 | Project_038_RISK018 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Last System Syndrome | Person_060 | 2012-11-20 01:00 | 2018-10-21 01:00 | 0.15 | 31.462 | 4.7193 | -- | 0.15 | 31.462 | 4.7193 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK002 | Project_065_RISK002 | Opportunitity | Project Contingency | Open | H1 | 5 | 12. Acquisition and offsets | New supplier for enclosure | Person_598 | 2015-01-07 01:00 | 2017-10-19 01:00 | 0.05 | 9.6346 | 0.48173 | Exploit | 0.7 | 9.6346 | 6.7442 | H1 | 5 | Stable | [10 empty] | 0 | -1300 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_332 | 2016-06-23 | 2018-02-02 01:00 | 0.4 | 1.7748 | 0.4437 | Accept | 0.2 | 1.7748 | 0.4437 | H2 | 4 | Stable | 0.9 | 103 | 126 | 142 | 124.8333 | 0.9 | 103 | 126 | 142 | 124.8333 | 0 | 50 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier Selection Process | Person_379 | 2017-10-19 01:00 | 2019-04-23 | 0.4 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.7 | 115 | 135 | 158 | 135.5 | 0.2 | 7 | 40 | 66 | 38.8333 |  | 25 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Colour Representation in Video Image Distortion | Person_305 | 2017-09-22 01:00 | 2017-12-19 01:00 | 0.5 | 5.5323 | 2.7662 | Reduce | 0.1 | 5.5323 | 0.55323 | H3 | 3 | Stable | 0.9 | 99 | 137 | 142 | 131.5 | 0.3 | 26 | 49 | 74 | 49.3333 | 0 | 80 | 1 | 2.4
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-21 01:00 | 0.8 | 35.2369 | 28.1895 | Reduce | 0.3 | 18.4979 | 5.5494 | H2 | 4 | Stable | 0.6 | 97 | 137 | 156 | 133.5 | 0.2 | 33 | 46 | 67 | 47.3333 | 47.5042 | 62.5 | 0 | 28.5025
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 4 | 9. Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-21 01:00 | 0.7 | 20.6835 | 14.4785 | Reduce | 0.3 | 20.6835 | 6.2051 | H2 | 4 | Stable | 0.5 | 120 | 125 | 145 | 127.5 | 0.3 | 35 | 42 | 70 | 45.5 | 0 | 57.1429 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 4 | 8. System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 0.6 | 5.2585 | 3.1551 | Reduce | 0.15 | 5.2585 | 0.78877 | H2 | 4 | Stable | 0.5 | 99 | 124 | 145 | 123.3333 | 0.4 | 27 | 41 | 71 | 43.6667 | 0 | 75 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 0.2 | 7.7077 | 2.6977 | Accept | 0.2 | 7.7077 | 2.6977 | H2 | 4 | Stable | 0.7 | 119 | 129 | 160 | 132.5 | 0.7 | 119 | 129 | 160 | 132.5 | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 0.25 | 1.0497 | 0.3149 | Accept | 0.25 | 1.0497 | 0.3149 | H3 | 3 | Stable | 0.6 | 87 | 128 | 144 | 123.8333 | 0.6 | 87 | 128 | 144 | 123.8333 | 0 | 0 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-04-21 | 0.3 | 2.723 | 0.81691 | Reduce | 0.1 | 2.723 | 0.2723 | H3 | 3 | Improving | 0.7 | 114 | 129 | 148 | 129.6667 | 0.3 | 20 | 45 | 78 | 46.3333 | 0 | 66.6667 | 1 | 2
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.6 | 115 | 130 | 150 | 130.8333 | 0.1 | 21 | 49 | 68 | 47.5 | 60.3671 | 58.3333 | 0 | 36.2202
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK011 | Project_041_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier Development support | Person_693 | 2018-01-25 01:00 | 2018-04-06 | 0.3 | 5.0032 | 3.5023 | Accept | 0.3 | 5.0032 | 3.5023 | H2 | 4 | Stable | 0.5 | 103 | 140 | 154 | 136.1667 | 0.5 | 103 | 140 | 154 | 136.1667 | 0 | 0 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 0.2 | 4.8444 | 0.96888 | Reduce | 0.2 | 4.8444 | 0.96888 | H3 | 3 | Stable | 0.6 | 93 | 138 | 143 | 131.3333 | 0.3 | 24 | 52 | 68 | 50 | 0 | 0 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_038 | 2020-05-23 | 2023-10-26 01:00 | 0.2 | 7.4599 | 1.492 | Reduce | 0.05 | 7.4599 | 0.37299 | H2 | 4 | Stable | 0.6 | 100 | 128 | 145 | 126.1667 | 0.3 | 19 | 44 | 69 | 44 | 0 | 75 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-29 01:00 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.7 | 80 | 132 | 145 | 125.5 | 0.2 | 39 | 49 | 74 | 51.5 | 60.3671 | 58.3333 | 0 | 36.2202
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-20 01:00 | 0.4 | 2.8643 | 1.1457 | Reduce | 0.1 | 2.8643 | 0.28643 | H3 | 3 | Stable | 0.7 | 119 | 122 | 159 | 127.6667 | 0.4 | 24 | 42 | 67 | 43.1667 | 0.0015933 | 75 | 1 | 2.251
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power Supply - Motor Controller Interface | Person_047 | 2016-05-23 | 2018-04-21 | 0.5 | 25.3543 | 12.6771 | Reduce | 0.2 | 25.3543 | 5.0709 | H3 | 3 | Stable | 0.8 | 85 | 124 | 144 | 120.8333 | 0.1 | 22 | 41 | 69 | 42.5 | 0 | 60 | 1 | 1.8
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 0.1 | 12.7232 | 1.2723 | Reduce | 0.1 | 12.7232 | 1.2723 | H3 | 3 | Stable | 0.7 | 105 | 123 | 160 | 126.1667 | 0.3 | 1 | 44 | 79 | 42.6667 | 0 | 0 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | EMC non compliance | Person_047 | 2016-06-23 | 2019-12-27 01:00 | 0.7 | 3.935 | 2.7545 | Reduce | 0.5 | 3.935 | 1.9675 | H2 | 4 | Stable | 0.7 | 94 | 123 | 146 | 122 | 0.3 | 23 | 54 | 63 | 50.3333 | 0 | 28.5714 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SubSystem System Design | Person_038 | 2017-10-01 01:00 | 2019-11-20 01:00 | 0.2 | 1.5213 | 0.30425 | Reduce | 0.1 | 1.5213 | 0.15213 | H3 | 3 | Stable | 0.6 | 118 | 130 | 155 | 132.1667 | 0.2 | 25 | 52 | 68 | 50.1667 | 0 | 50 | 1 | 1.5
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 0.05 | 1.2677 | 0.12677 | Accept | 0.03 | 1.2677 | 0.12677 | H2 | 4 | Stable | 0.8 | 116 | 128 | 155 | 130.5 | 0.8 | 116 | 128 | 155 | 130.5 | 0 | 40 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2018-04-22 | 0.8 | 67.8016 | 27.1206 | Accept | 0.6 | 67.8016 | 27.1206 | H1 | 5 | Stable | 0.9 | 102 | 135 | 159 | 133.5 | 0.9 | 102 | 135 | 159 | 133.5 | 0 | 25 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 01:00 | 2018-05-22 | 0.1 | 65.469 | 26.1876 | Accept | 0.05 | 65.469 | 26.1876 | H2 | 4 | Stable | 0.5 | 89 | 139 | 146 | 131.8333 | 0.5 | 89 | 139 | 146 | 131.8333 | 0 | 50 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2018-05-21 | 0.2 | 7.7077 | 1.5415 | Accept | 0.2 | 7.7077 | 1.5415 | H3 | 3 | Worsening | 0.8 | 95 | 126 | 150 | 124.8333 | 0.8 | 95 | 126 | 150 | 124.8333 | 0 | 0 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-21 01:00 | 2023-12-22 01:00 | 0.4 | 30.1969 | 12.0788 | Reduce | 0.25 | 30.1969 | 7.5492 | H2 | 4 | Stable | 0.9 | 92 | 138 | 151 | 132.5 | 0.1 | 23 | 52 | 66 | 49.5 | 0 | 37.5 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2018-04-22 | 0.3 | 25.1514 | 12.5757 | Accept | 0.2 | 25.1514 | 12.5757 | H3 | 3 | Stable | 0.7 | 107 | 128 | 160 | 129.8333 | 0.7 | 107 | 128 | 160 | 129.8333 | 0 | 33.3333 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | In-house development of sub-system estimate is low | Person_594 | 2016-03-23 | 2018-03-22 | 0.5 | 6.5118 | 3.2559 | Reduce | 0.2 | 1.506 | 0.30121 | H3 | 3 | Stable | 0.8 | 80 | 139 | 158 | 132.3333 | 0.3 | 4 | 52 | 72 | 47.3333 | 76.8722 | 60 | 0 | 46.1233
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2017-12-19 01:00 | 0.3 | 1.0142 | 0.30425 | Reduce | 0.2 | 1.0142 | 0.20283 | H3 | 3 | Stable | 0.5 | 96 | 124 | 143 | 122.5 | 0.2 | 10 | 52 | 67 | 47.5 | 0 | 33.3333 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | 9. Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 0.8 | 19.1678 | 15.3343 | Reduce | 0.2 | 2.8752 | 0.57503 | H3 | 3 | Stable | 0.8 | 115 | 128 | 152 | 129.8333 | 0.3 | 14 | 48 | 74 | 46.6667 | 85 | 75 | 0 | 51
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 0.25 | 0.63626 | 0.15906 | Reduce | 0.05 | 0.63626 | 0.031813 | H3 | 3 | Stable | 0.6 | 105 | 129 | 146 | 127.8333 | 0.2 | 31 | 53 | 78 | 53.5 | 0 | 80 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Component Shock test failure | Person_661 | 2016-09-08 01:00 | 2019-11-15 01:00 | 0.4 | 0.8467 | 0.33868 | Reduce | 0.2 | 0.8467 | 0.16934 | H3 | 3 | Stable | 0.7 | 88 | 135 | 154 | 130.3333 | 0.1 | 14 | 41 | 60 | 39.6667 | 0 | 50 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-06 01:00 | 2019-09-13 01:00 | 0.8 | 8.0322 | 6.4258 | Reduce | 0.5 | 4.006 | 2.003 | H2 | 4 | Stable | 0.8 | 89 | 132 | 144 | 126.8333 | 0.3 | 33 | 46 | 64 | 46.8333 | 50.1263 | 37.5 | 0 | 30.0758
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.8 | 95 | 121 | 157 | 122.6667 | 0.3 | 19 | 55 | 63 | 50.3333 | 25.8065 | 20 | 0 | 15.4839
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2017-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-63 | Project_022_RISK-63 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer Levy | Person_703 | 2012-04-19 | 2017-08-20 | 0.8 | 3.5298 | 2.8239 | Exploit | 0.8 | 3.5298 | 2.8239 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-62 | Project_022_RISK-62 | Threat | Project Contingency | Open | H3 | 3 | 8. Operations & Maintenance | Additional Costs from Integration Cost Centre | Person_703 | 2017-03-23 | 2017-05-14 | 0.5 | 7.1754 | 3.5877 | Avoid | 0.292 | 3.5877 | 1.0476 | H3 | 3 | Worsening | [10 empty] | 50 | 41.6 | 0 | 30
2017-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2017-06-21 | 0.8 | 3.6791 | 2.9433 | Reduce | 0.35 | 2.8688 | 1.0041 | H2 | 4 | Stable | 0.6 | 111 | 122 | 141 | 123.3333 | 0.2 | 20 | 41 | 60 | 40.6667 | 22.0253 | 56.25 | 0 | 13.2152
2017-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Bank Guarantees | Person_703 | 2012-04-19 | 2017-08-20 | 0.8 | 3.3531 | 2.6825 | Exploit | 0.8 | 0.65554 | 0.52443 | H2 | 4 | Stable | [10 empty] | 80.45 | 0 | 0 | 48.27
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 0.5 | 0.014395 | 0.0071976 | Avoid | 0.5 | 0.014395 | 0.0071976 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 0.2 | 0.014395 | 0.002879 | Reduce | 0.2 | 0.014395 | 0.002879 | H3 | 3 | Stable | 0.9 | 100 | 125 | 150 | 125 | 0.1 | 8 | 40 | 60 | 38 | 0 | 0 | 1 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.013865 | 0.0027729 | Avoid | 0.2 | 0.013865 | 0.0027729 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0.0056822 | 0.0011364 | Avoid | 0.2 | 0.0056822 | 0.0011364 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 0.1 | 0.0046972 | 0.00046972 | Avoid | 0.1 | 0.0046972 | 0.00046972 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2017-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.9 | 83 | 136 | 150 | 129.5 | 0.1 | 27 | 43 | 66 | 44.1667 | 25.8065 | 20 | 0 | 15.4839
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer find issues with delivered parts or documentation | Person_294 | 2016-05-23 | 2019-08-20 | 0.4 | 9.0039 | 3.6016 | Reduce | 0.25 | 9.0039 | 2.251 | H2 | 4 | Improving | 0.5 | 113 | 140 | 155 | 138 | 0.2 | 33 | 54 | 67 | 52.6667 | 0 | 37.5 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Open PR's | Person_319 | 2017-04-22 | 2018-11-20 01:00 | 0.5 | 0.29361 | 0.1468 | Reduce | 0.15 | 0.29361 | 0.044041 | H3 | 3 | Improving | 0.8 | 109 | 125 | 152 | 126.8333 | 0.3 | 32 | 57 | 72 | 55.3333 | 0 | 70 | 1 | 2.1
2018-01-21 | ORG_002 | BA_005 | Portfolio_016 | Project_061 | RISK003 | Project_061_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Test equipment reliability | Person_104 | 2017-05-23 | 2020-11-19 01:00 | 0.4 | 0.11013 | 0.044051 | Reduce | 0.3 | 0.11013 | 0.033038 | H2 | 4 | Stable | 0.5 | 114 | 131 | 158 | 132.6667 | 0.3 | 4 | 50 | 68 | 45.3333 | 0 | 25 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.5 | 103 | 125 | 156 | 126.5 | 0.3 | 32 | 47 | 61 | 46.8333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_676 | 2016-08-21 01:00 | 2017-08-21 01:00 | 0.5 | 37.5906 | 18.7953 | Reduce | 0.15 | 37.5906 | 5.6386 | H3 | 3 | Stable | 0.8 | 100 | 130 | 147 | 127.8333 | 0.2 | 37 | 41 | 75 | 46 | 0 | 70 | 1 | 2.1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System Performance | Person_305 | 2016-09-08 01:00 | 2020-09-21 01:00 | 0.15 | 7.689 | 2.6911 | Accept | 0.05 | 7.689 | 2.6911 | H2 | 4 | Stable | 0.9 | 116 | 125 | 153 | 128.1667 | 0.9 | 116 | 125 | 153 | 128.1667 | 0 | 66.6667 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK007 | Project_048_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Staff Availability | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.4 | 0.067093 | 0.026837 | Avoid | 0.1 | 0.067093 | 0.0067093 | H3 | 3 | Stable | [10 empty] | 0 | 75 | 1 | 2.25
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK017 | Project_048_RISK017 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Increased build rate | Person_683 | 2017-11-12 01:00 | 2019-08-21 01:00 | 0.5 | 7.7433 | 3.8716 | -- | 0.5 | 7.7433 | 3.8716 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK016 | Project_048_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.2 | 0.22605 | 0.045211 | -- | 0.1 | 0.22605 | 0.022605 | H3 | 3 | Worsening | [10 empty] | 0 | 50 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK018 | Project_048_RISK018 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Line Closure | Person_683 | 2019-08-21 01:00 | 2019-11-20 01:00 | 0.5 | 0.68298 | 0.34149 | -- | 0.5 | 1.5483 | 0.77415 | H2 | 4 | Improving | [10 empty] | -126.7001 | 0 | 0 | -76.0201
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK004 | Project_048_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 1.0253 | 0.20506 | Reduce | 0.15 | 1.0253 | 0.1538 | H3 | 3 | Stable | 0.9 | 88 | 129 | 144 | 124.6667 | 0.2 | 17 | 48 | 71 | 46.6667 | 0 | 25 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK014 | Project_048_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 0.1 | 2.5117 | 0.25117 | Avoid | 0.05 | 2.5117 | 0.12558 | H3 | 3 | Worsening | [10 empty] | 0 | 50 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK006 | Project_048_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Customer | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0.20644 | 0.041288 | Reduce | 0.15 | 0.20644 | 0.030966 | H3 | 3 | Stable | 0.7 | 82 | 130 | 142 | 124 | 0.1 | 28 | 53 | 65 | 50.8333 | 0 | 25 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK005 | Project_048_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 0.43506 | 0.26104 | Avoid | 0.5 | 0.43506 | 0.21753 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK011 | Project_048_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Line Qualification | Person_665 | 2017-02-20 01:00 | 2019-05-23 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.8 | 114 | 138 | 146 | 135.3333 | 0.1 | 25 | 50 | 67 | 48.6667 |  | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK002 | Project_048_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2020-05-22 | 0.15 | 0.30966 | 0.046449 | Avoid | 0.15 | 0.30966 | 0.046449 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK012 | Project_048_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Customer require additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK008 | Project_048_RISK008 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Oracle | Person_683 | 2017-02-20 01:00 | 2018-11-05 01:00 | 0.1 | 0.20644 | 0.020644 | Avoid | 0.05 | 0.20644 | 0.010322 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK021 | Project_048_RISK021 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Late Delivery | Person_261 | 2018-01-14 01:00 | 2018-11-20 01:00 | 0.7 | 0 | 0 | Reduce | 0.7 | 0 | 0 | H1 | 5 | Stable | 0.9 | 108 | 135 | 154 | 133.6667 | 0.1 | 37 | 50 | 66 | 50.5 |  | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK021 | Project_063_RISK021 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Late Delivery | Person_261 | 2018-01-14 01:00 | 2018-11-20 01:00 | 0.7 | 0 | 0 | Reduce | 0.7 | 0 | 0 | H1 | 5 | Stable | 0.6 | 96 | 125 | 146 | 123.6667 | 0.2 | 20 | 53 | 64 | 49.3333 |  | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK004 | Project_063_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 2.861 | 0.57221 | Reduce | 0.15 | 2.861 | 0.42915 | H3 | 3 | Stable | 0.5 | 82 | 129 | 158 | 126 | 0.2 | 5 | 53 | 65 | 47 | 0 | 25 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK014 | Project_063_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 0.1 | 7.0086 | 0.70086 | Avoid | 0.05 | 7.0086 | 0.35043 | H3 | 3 | Worsening | [10 empty] | 0 | 50 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK006 | Project_063_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Customer | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0.57605 | 0.11521 | Reduce | 0.15 | 0.57605 | 0.086407 | H3 | 3 | Stable | 0.5 | 94 | 137 | 146 | 131.3333 | 0.2 | 32 | 51 | 66 | 50.3333 | 0 | 25 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK017 | Project_063_RISK017 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Increased build rate | Person_683 | 2017-11-12 01:00 | 2019-08-21 01:00 | 0.5 | 21.6065 | 10.8033 | -- | 0.5 | 21.6065 | 10.8033 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK005 | Project_063_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 1.214 | 0.72839 | -- | 0.5 | 1.214 | 0.60699 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK016 | Project_063_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.2 | 0.63077 | 0.12615 | -- | 0.1 | 0.63077 | 0.063077 | H3 | 3 | Worsening | [10 empty] | 0 | 50 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK011 | Project_063_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Line Qualification | Person_665 | 2017-02-20 01:00 | 2019-05-23 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.6 | 93 | 131 | 153 | 128.3333 | 0.3 | 32 | 48 | 71 | 49.1667 |  | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK002 | Project_063_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2020-05-22 | 0.15 | 0.86407 | 0.12961 | Avoid | 0.15 | 0.86407 | 0.12961 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK012 | Project_063_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Customer require additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK003 | Project_060_RISK003 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Misalignment of Critical Resource | Person_312 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.7 | 11.7303 | 8.2112 | Reduce | 0.5 | 11.7303 | 5.8651 | H1 | 5 | Improving | 0.9 | 85 | 139 | 157 | 133 | 0.4 | 15 | 46 | 63 | 43.6667 | 0 | 28.5714 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK008 | Project_063_RISK008 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Oracle | Person_683 | 2017-02-20 01:00 | 2018-11-05 01:00 | 0.1 | 0.57605 | 0.057605 | Avoid | 0.05 | 0.57605 | 0.028802 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK004 | Project_060_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Cross-functional Estimates | Person_729 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.7 | 2.8845 | 2.0191 | Reduce | 0.5 | 2.8845 | 1.4422 | H2 | 4 | Stable | 0.8 | 118 | 126 | 151 | 128.8333 | 0.3 | 20 | 45 | 68 | 44.6667 | 0 | 28.5714 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK007 | Project_063_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Staff Availability | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.4 | 0.18722 | 0.074886 | Avoid | 0.1 | 0.18722 | 0.018722 | H3 | 3 | Stable | [10 empty] | 0 | 75 | 1 | 2.25
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK006 | Project_060_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Secure material Handling | Person_033 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.5 | 1.1538 | 0.5769 | Reduce | 0.2 | 1.1538 | 0.23076 | H3 | 3 | Stable | 0.8 | 116 | 134 | 154 | 134.3333 | 0.3 | 23 | 59 | 65 | 54 | 0 | 60 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK018 | Project_063_RISK018 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Line Closure | Person_683 | 2019-08-21 01:00 | 2019-11-20 01:00 | 0.5 | 1.9058 | 0.95288 | -- | 0.5 | 4.3203 | 2.1602 | H2 | 4 | Improving | [10 empty] | -126.7001 | 0 | 0 | -76.0201
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK001 | Project_060_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Procurement Prices | Person_033 | 2017-11-02 01:00 | 2018-08-20 | 0.7 | 1.4422 | 1.0096 | Transfer | 0.7 | 1.4422 | 1.0096 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK015 | Project_053_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Equipment export licences | Person_252 | 2018-06-23 | 2019-07-22 | 0.3 | 2.586 | 0.77579 | Avoid | 0.1 | 2.586 | 0.2586 | H3 | 3 | Improving | [10 empty] | 0 | 66.6667 | 1 | 2
2018-01-21 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK006 | Project_053_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional UK integration of the System product | Person_719 | 2018-10-22 01:00 | 2019-01-21 01:00 | 0.2 | 6.3212 | 1.2642 | Avoid | 0.2 | 6.3212 | 1.2642 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 1 | 0
2018-01-21 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK005 | Project_053_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier Deiivery Schedule | Person_252 | 2018-01-21 01:00 | 2018-11-20 01:00 | 0.5 | 5.3299 | 2.665 | Reduce | 0.25 | 5.3299 | 1.3325 | H2 | 4 | Stable | 0.5 | 96 | 134 | 141 | 128.8333 | 0.1 | 21 | 54 | 75 | 52 | 0 | 50 | 0 | 0
2018-01-21 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK010 | Project_053_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Immaturity of the core product | Person_719 | 2018-08-22 01:00 | 2018-11-20 01:00 | 0.5 | 6.4649 | 3.2325 | Avoid | 0.2 | 6.4649 | 1.293 | H2 | 4 | Stable | [10 empty] | 0 | 60 | 0 | 0
2018-01-21 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK007 | Project_053_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Resources Uavailable | Person_252 | 2017-11-20 01:00 | 2019-08-21 01:00 | 0.5 | 10.3438 | 5.1719 | Reduce | 0.2 | 7.9015 | 1.5803 | H3 | 3 | Stable | 0.6 | 110 | 138 | 154 | 136 | 0.4 | 28 | 43 | 78 | 46.3333 | 23.6111 | 60 | 1 | 15.9666
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2018-03-22 | 2019-07-21 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.5 | 101 | 140 | 149 | 135 | 0.2 | 12 | 44 | 66 | 42.3333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_585 | 2017-09-02 01:00 | 2018-03-16 01:00 | 0.1 | 6.4168 | 0.64168 | Transfer | 0.1 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sub-system FPGA | Person_332 | 2017-01-21 01:00 | 2018-09-20 01:00 | 0.4 | 1.5914 | 0.63655 | Reduce | 0.2 | 1.5914 | 0.31827 | H3 | 3 | Stable | 0.6 | 110 | 128 | 151 | 128.8333 | 0.3 | 24 | 48 | 61 | 46.1667 | 0 | 50 | 1 | 1.5
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort for System HW/SW- System upgrade. | Person_199 | 2017-05-23 | 2019-09-18 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.2 | 2.5667 | 0.51334 | H3 | 3 | Stable | 0.9 | 98 | 128 | 153 | 127.1667 | 0.3 | 24 | 48 | 77 | 48.8333 | 0 | 33.3333 | 1 | 1
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs | Person_372 | 2018-04-22 | 2018-08-22 01:00 | 0.5 | 6.6521 | 3.326 | Reduce | 0.5 | 6.6521 | 3.326 | H2 | 4 | Stable | 0.9 | 97 | 123 | 157 | 124.3333 | 0.3 | 13 | 51 | 63 | 46.6667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.25 | 3.5934 | 0.89835 | H2 | 4 | Stable | 0.8 | 107 | 137 | 154 | 134.8333 | 0.1 | 35 | 46 | 69 | 48 | 0 | 50 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-23 | 2024-05-22 | 0.1 | 2.6951 | 0.53901 | Accept | 0.1 | 2.6951 | 0.53901 | H3 | 3 | Improving | 0.8 | 81 | 122 | 154 | 120.5 | 0.8 | 81 | 122 | 154 | 120.5 | 0 | 0 | 1 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Minimum Order Quantities | Person_372 | 2017-11-20 01:00 | 2018-05-15 | 0.2 | 1.925 | 0.38501 | Exploit | 0.2 | 1.925 | 0.38501 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_372 | 2018-04-22 | 2018-08-22 01:00 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Worsening | 0.9 | 83 | 139 | 145 | 130.6667 | 0.1 | 33 | 51 | 67 | 50.6667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK044 | Project_042_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2018-02-20 01:00 | 2018-12-21 01:00 | 0.32 | 6.5759 | 2.1043 | Reduce | 0.17 | 6.5759 | 1.1179 | H2 | 4 | Stable | 0.9 | 113 | 127 | 143 | 127.3333 | 0.3 | 2 | 45 | 75 | 42.8333 | 0 | 46.875 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 0.3 | 1.8788 | 0.18788 | Accept | 0.3 | 1.5031 | 0.12024 | H3 | 3 | Stable | 0.7 | 80 | 136 | 141 | 127.5 | 0.7 | 80 | 136 | 141 | 127.5 | 20 | 0 | 0 | 12
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK024 | Project_042_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2019-09-21 01:00 | 2020-09-19 01:00 | 0.33 | 9.3941 | 3.1001 | Reduce | 0.15 | 7.5153 | 1.1273 | H2 | 4 | Stable | 0.9 | 113 | 132 | 143 | 130.6667 | 0.3 | 37 | 42 | 61 | 44.3333 | 20 | 54.5455 | 0 | 12
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) at the System level on product platform - performed by 3rd parties | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Sub-system / product system accreditation hindered by Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.1 | 0.25667 | 0.025667 | Transfer | 0.1 | 0.25667 | 0.025667 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK045 | Project_042_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2019-01-22 01:00 | 2019-05-23 | 0.25 | 3.908 | 0.97699 | Reduce | 0.25 | 3.908 | 0.97699 | H2 | 4 | Stable | 0.9 | 115 | 132 | 147 | 131.6667 | 0.3 | 10 | 53 | 64 | 47.6667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_585 | 2017-05-23 | 2018-04-21 | 0.3 | 2.0534 | 0.61601 | Transfer | 0.1 | 1.54 | 0.154 | H3 | 3 | Stable | [10 empty] | 25 | 66.6667 | 0 | 15
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2018-05-15 | 0.3 | 0.89835 | 0.26951 | Transfer | 0.3 | 0.89835 | 0.26951 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 0.35 | 1.9208 | 0.67227 | Reduce | 0.25 | 1.9208 | 0.48019 | H2 | 4 | Stable | 0.6 | 83 | 134 | 157 | 129.3333 | 0.2 | 19 | 53 | 64 | 49.1667 | 0 | 28.5714 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2018-03-22 | 2018-10-18 01:00 | 0.4 | 0.77001 | 0.30801 | Reduce | 0.3 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.9 | 93 | 128 | 151 | 126 | 0.2 | 33 | 58 | 75 | 56.6667 | 0 | 25 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_676 | 2016-10-21 01:00 | 2019-08-20 | 0.5 | 35.0206 | 7.0041 | Accept | 0.5 | 35.0206 | 7.0041 | H2 | 4 | Stable | 0.7 | 96 | 121 | 154 | 122.3333 | 0.7 | 96 | 121 | 154 | 122.3333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_102 | 2018-02-20 01:00 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.5 | 89 | 125 | 148 | 122.8333 | 0.2 | 15 | 52 | 76 | 49.8333 | 0 | 28.5714 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.2 | 2.8182 | 0.28182 | Accept | 0.2 | 2.7619 | 0.22095 | H3 | 3 | Stable | 0.9 | 91 | 139 | 159 | 134.3333 | 0.9 | 91 | 139 | 159 | 134.3333 | 2 | 0 | 0 | 1.2
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software issue input | Person_279 | 2016-11-23 | 2023-02-20 | 0.4 | 49.4398 | 19.7759 | Reduce | 0.2 | 49.4398 | 9.888 | H2 | 4 | Stable | 0.6 | 95 | 134 | 144 | 129.1667 | 0.1 | 11 | 43 | 77 | 43.3333 | 0 | 50 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.35 | 1.54 | 0.30801 | Accept | 0.35 | 0.77001 | 0.154 | H3 | 3 | Stable | 0.6 | 102 | 127 | 145 | 125.8333 | 0.6 | 102 | 127 | 145 | 125.8333 | 50 | 0 | 0 | 30
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-20 23:00 | 2017-08-19 23:00 | 0.1 | 53.0293 | 5.3029 | Reduce | 0.1 | 53.0293 | 5.3029 | H3 | 3 | Stable | 0.8 | 110 | 121 | 146 | 123.3333 | 0.4 | 25 | 45 | 64 | 44.8333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.25 | 1.6166 | 0.32332 | Accept | 0.25 | 1.6166 | 0.32332 | H3 | 3 | Stable | 0.9 | 82 | 121 | 151 | 119.5 | 0.9 | 82 | 121 | 151 | 119.5 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_009 | Project_051 | RISK001 | Project_051_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Generic Labour or Material Overspend | Person_577 | 2012-05-23 | 2021-05-22 | 0.5 | 0.94968 | 0.28491 | Accept | 0.5 | 0.94968 | 0.18994 | H3 | 3 | Stable | 0.5 | 109 | 139 | 154 | 136.5 | 0.5 | 109 | 139 | 154 | 136.5 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 | 2020-08-20 | 0.5 | 0.20788 | 0.068599 | Accept | 0.5 | 31.0429 | 15.5215 | H2 | 4 | Stable | 0.8 | 82 | 137 | 150 | 130 | 0.8 | 82 | 137 | 150 | 130 | -14833.3191 | 0 | 0 | -8899.9915
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 1.8788 | 0.37576 | Accept | 0.5 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.8 | 98 | 131 | 158 | 130 | 0.8 | 98 | 131 | 158 | 130 | 20 | 0 | 0 | 12
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-20 23:00 | 2017-08-19 23:00 | 0.1 | 7.7469 | 0.77469 | Reduce | 0.1 | 7.7469 | 0.77469 | H3 | 3 | Stable | 0.7 | 116 | 131 | 155 | 132.5 | 0.1 | 4 | 41 | 78 | 41 | 0 | 0 | 0 | 0
2018-01-21 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK021 | Project_053_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Product documentation | Person_719 | 2018-08-22 01:00 | 2019-07-26 | 0.35 | 2.0207 | 0.20207 | Accept | 0.35 | 2.0207 | 0.20207 | H2 | 4 | Stable | 0.6 | 99 | 130 | 157 | 129.3333 | 0.6 | 99 | 130 | 157 | 129.3333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_585 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 1.8788 | 0.37576 | Accept | 0.03 | 1.5031 | 0.22546 | H3 | 3 | Stable | 0.9 | 97 | 128 | 156 | 127.5 | 0.9 | 97 | 128 | 156 | 127.5 | 20 | 0 | 0 | 12
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | HW - additional unplanned design effort | Person_332 | 2016-05-23 | 2018-03-23 | 0.4 | 2.0207 | 0.20207 | Accept | 0.4 | 2.0207 | 0.20207 | H2 | 4 | Stable | 0.7 | 80 | 126 | 153 | 122.8333 | 0.7 | 80 | 126 | 153 | 122.8333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 1.0334 | 0.20667 | Accept | 0.25 | 0.80789 | 0.12118 | H2 | 4 | Stable | 0.9 | 94 | 140 | 155 | 134.8333 | 0.9 | 94 | 140 | 155 | 134.8333 | 21.8182 | 0 | 0 | 13.0909
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK047 | Project_042_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables | Person_455 | 2020-11-20 01:00 | 2021-05-22 | 0.2 | 1.8788 | 0.18788 | Accept | 0.1 | 1.8225 | 0.12757 | H2 | 4 | Stable | 0.8 | 83 | 125 | 156 | 123.1667 | 0.8 | 83 | 125 | 156 | 123.1667 | 3 | 50 | 0 | 1.8
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 2.0207 | 0.20207 | Accept | 0.2 | 2.0207 | 0.20207 | H3 | 3 | Stable | 0.8 | 101 | 136 | 152 | 132.8333 | 0.8 | 101 | 136 | 152 | 132.8333 | 0 | 33.3333 | 1 | 1
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design [in addition to costed effort] | Person_332 | 2017-05-28 | 2018-11-30 01:00 | 0.2 | 1.8788 | 0.18788 | Accept | 0.2 | 1.5031 | 0.12024 | H3 | 3 | Improving | 0.7 | 93 | 139 | 148 | 132.8333 | 0.7 | 93 | 139 | 148 | 132.8333 | 20 | 0 | 1 | 12
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK022 | Project_042_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2017-09-20 01:00 | 2018-09-20 01:00 | 0.2 | 1.8788 | 0.18788 | Accept | 0.18 | 1.5031 | 0.12024 | H2 | 4 | Stable | 0.8 | 103 | 122 | 150 | 123.5 | 0.8 | 103 | 122 | 150 | 123.5 | 20 | 10 | 0 | 12
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_585 | 2017-10-21 01:00 | 2019-07-21 | 0.333 | 1.2124 | 0.12124 | Accept | 0.333 | 1.2124 | 0.12124 | H2 | 4 | Stable | 0.8 | 91 | 135 | 145 | 129.3333 | 0.8 | 91 | 135 | 145 | 129.3333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK043 | Project_042_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st December | Person_455 | 2021-03-23 | 2021-05-22 | 0.1 | 0.79775 | 0.039887 | Accept | 0.08 | 0.79775 | 0.039887 | H3 | 3 | Stable | 0.7 | 81 | 130 | 150 | 125.1667 | 0.7 | 81 | 130 | 150 | 125.1667 | 0 | 20 | 1 | 0.6
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK046 | Project_042_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables - June | Person_455 | 2018-11-21 01:00 | 2020-11-19 01:00 | 0.2 | 10.3335 | 1.0334 | Accept | 0.1 | 10.3335 | 1.0334 | H2 | 4 | Stable | 0.6 | 86 | 124 | 146 | 121.3333 | 0.6 | 86 | 124 | 146 | 121.3333 | 0 | 50 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK023 | Project_042_RISK023 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2018-09-21 01:00 | 2019-09-20 01:00 | 0.2 | 11.2729 | 2.2546 | Accept | 0.1 | 11.2729 | 2.2546 | H2 | 4 | Stable | 0.9 | 116 | 139 | 148 | 136.6667 | 0.9 | 116 | 139 | 148 | 136.6667 | 0 | 50 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 0.60622 | 0.18186 | Accept | 0.3 | 0.60622 | 0.18186 | H2 | 4 | Improving | 0.6 | 84 | 129 | 149 | 124.8333 | 0.6 | 84 | 129 | 149 | 124.8333 | 0 | 25 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK029 | Project_042_RISK029 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st October to 31st December | Person_455 | 2020-11-20 01:00 | 2021-05-22 | 0.25 | 3.7576 | 0.18788 | Accept | 0.1 | 3.7576 | 0.56365 | H2 | 4 | Stable | 0.9 | 81 | 134 | 159 | 129.3333 | 0.9 | 81 | 134 | 159 | 129.3333 | 0 | 60 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Volume of production tools and Jigs | Person_279 | 2016-11-23 | 2021-11-23 | 0.35 | 0.64865 | 0.32433 | Accept | 0.2 | 0.64865 | 0.32433 | H2 | 4 | Stable | 0.9 | 102 | 134 | 148 | 131 | 0.9 | 102 | 134 | 148 | 131 | 0 | 42.8571 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK036 | Project_042_RISK036 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 2 | Person_455 | 2019-05-24 | 2020-05-22 | 0.25 | 0.80829 | 0.16166 | Accept | 0.2 | 0.80829 | 0.16166 | H2 | 4 | Stable | 0.5 | 98 | 125 | 144 | 123.6667 | 0.5 | 98 | 125 | 144 | 123.6667 | 0 | 20 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_431 | 2016-07-21 | 2018-08-21 | 0.15 | 0.58983 | 0.088474 | -- | 0.15 | 0.58983 | 0.088474 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2018-04-22 | 2018-09-20 01:00 | 0.2 | 0.62279 | 0.12456 | Avoid | 0.2 | 0.62279 | 0.12456 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK039 | Project_042_RISK039 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality Issues 16th August to 15th August | Person_540 | 2020-01-06 01:00 | 2021-01-04 01:00 | 0.1 | 13.4066 | 5.3626 | Accept | 0.08 | 13.4066 | 5.3626 | H2 | 4 | Stable | 0.9 | 87 | 127 | 160 | 125.8333 | 0.9 | 87 | 127 | 160 | 125.8333 | 0 | 20 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-09-20 01:00 | 0.2 | 1.8854 | 0.37708 | Reduce | 0.2 | 1.8854 | 0.37708 | H2 | 4 | Stable | 0.5 | 87 | 126 | 143 | 122.3333 | 0.2 | 8 | 47 | 72 | 44.6667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2018-06-23 | 2018-10-21 01:00 | 0.4 | 1.4138 | 0.56551 | Reduce | 0.4 | 1.4138 | 0.56551 | H2 | 4 | Stable | 0.9 | 120 | 127 | 159 | 131.1667 | 0.4 | 37 | 47 | 64 | 48.1667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-126 | Project_011_Risk-126 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Increase in regression testing | Person_182 | 2017-11-20 01:00 | 2018-05-21 | 0.25 | 0.12558 | 0.031395 | -- | 0.25 | 0.12558 | 0.031395 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-10-19 01:00 | 2018-08-21 | 0.2 | 0.081826 | 0.016365 | Reduce | 0.2 | 0.081826 | 0.016365 | H2 | 4 | Stable | 0.6 | 85 | 122 | 144 | 119.5 | 0.2 | 11 | 41 | 73 | 41.3333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Pick up and Drop off of Software Resource | Person_431 | 2017-12-19 01:00 | 2018-07-20 | 0.6 | 0.36106 | 0.21663 | Avoid | 0.6 | 0.36106 | 0.21663 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-09-20 01:00 | 0.4 | 0.19206 | 0.076826 | -- | 0.4 | 0.19206 | 0.076826 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-08-22 01:00 | 2018-11-20 01:00 | 0.4 | 0.58017 | 0.23207 | Avoid | 0.4 | 0.58017 | 0.23207 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2020-09-19 01:00 | 0.2 | 0.49834 | 0.12459 | Accept | 0.2 | 0.49834 | 0.12459 | H3 | 3 | Stable | 0.9 | 118 | 129 | 143 | 129.5 | 0.9 | 118 | 129 | 143 | 129.5 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.4 | 0.11365 | 0.045459 | -- | 0.4 | 0.11365 | 0.045459 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-11-20 01:00 | 0.55 | 0.32389 | 0.17814 | Reduce | 0.55 | 0.32389 | 0.17814 | H1 | 5 | Stable | 0.9 | 99 | 129 | 153 | 128 | 0.2 | 14 | 46 | 67 | 44.1667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | R054 | Project_066_R054 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | System Cybersecurity shortfalls | Person_689 | 2017-01-21 01:00 | 2024-05-23 | 0.8 | 15.7936 | 12.6349 | Reduce | 0.5 | 15.7936 | 7.8968 | H1 | 5 | Stable | 0.7 | 95 | 130 | 159 | 129 | 0.1 | 24 | 50 | 63 | 47.8333 | 0 | 37.5 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_182 | 2018-06-23 | 2018-10-21 01:00 | 0.4 | 0.19206 | 0.076826 | -- | 0.4 | 0.19206 | 0.076826 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_431 | 2017-05-24 | 2018-08-19 | 0.3 | 0.11933 | 0.035799 | -- | 0.3 | 0.022161 | 0.0066484 | H3 | 3 | Stable | [10 empty] | 81.4286 | 0 | 0 | 48.8571
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-117 | Project_011_Risk-117 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Avaliability for testing/reviews | Person_147 | 2018-04-06 | 2018-09-20 01:00 | 0.35 | 0 | 0 | Avoid | 0.35 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-128 | Project_011_Risk-128 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Incorrect Maps used during Qualification | Person_147 | 2017-04-22 | 2018-04-22 | 0.5 | 0.05688 | 0.02844 | Transfer | 0.5 | 0.05688 | 0.02844 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-129 | Project_011_Risk-129 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Signature of Work Authorisation documents | Person_422 | 2017-05-24 | 2018-04-21 | 0.4 | 0.12643 | 0.050573 | -- | 0.4 | 0.12643 | 0.050573 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-130 | Project_011_Risk-130 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer does not accept Voice Pronounciation | Person_187 | 2017-05-24 | 2018-06-21 | 0.4 | 0.090918 | 0.036367 | Avoid | 0.4 | 0.090918 | 0.036367 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-115 | Project_011_Risk-115 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | SMEs are unavailable to support project activites | Person_230 | 2016-07-21 | 2018-08-21 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-058 | Project_011_Risk-058 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Programme delays | Person_147 | 2013-11-20 01:00 | 2018-11-20 01:00 | 0.25 | 1.5013 | 0.37532 | Reduce | 0.25 | 1.5013 | 0.37532 | H2 | 4 | Stable | 0.7 | 84 | 124 | 155 | 122.5 | 0.4 | 20 | 43 | 77 | 44.8333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2019-07-21 | 0.3 | 8.8305 | 2.6492 | Accept | 0.2 | 8.8305 | 2.6492 | H3 | 3 | Stable | 0.9 | 112 | 139 | 146 | 135.6667 | 0.9 | 112 | 139 | 146 | 135.6667 | 0 | 33.3333 | 1 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-131 | Project_011_Risk-131 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Support team have not covered all obligations in support contract | Person_147 | 2016-05-24 | 2018-08-17 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-137 | Project_011_Risk-137 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Subsystem will not match Fidelity of Customer - does not accept | Person_147 | 2018-02-16 01:00 | 2018-09-20 01:00 | 0.4 | 0.11876 | 0.047505 | Avoid | 0.2 | 0.11876 | 0.023752 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-184 | Project_032_Risk-184 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Manufacture of new Sub-systems | Person_629 | 2016-04-08 | 2018-02-18 23:00 | 0.33 | 28.5076 | 7.1269 | Accept | 0.5 | 28.5076 | 2.8508 | H1 | 5 | Stable | 0.5 | 103 | 138 | 147 | 133.6667 | 0.5 | 103 | 138 | 147 | 133.6667 | 0 | -51.5152 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK033 | Project_042_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st April to 30 June | Person_455 | 2019-08-22 01:00 | 2019-11-20 01:00 | 0.2 | 1.4099 | 0.42298 | Accept | 0.15 | 1.4099 | 0.42298 | H2 | 4 | Stable | 0.8 | 86 | 139 | 147 | 131.5 | 0.8 | 86 | 139 | 147 | 131.5 | 0 | 25 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-19 23:00 | 0.05 | 105.645 | 105.645 | Accept | 0.05 | 105.645 | 105.645 | H3 | 3 | Stable | 0.8 | 86 | 128 | 159 | 126.1667 | 0.8 | 86 | 128 | 159 | 126.1667 | 0 | 0 | 1 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | R181 | Project_066_R181 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | USB Hub start up issues | Person_365 | 2017-01-21 01:00 | 2024-05-23 | 1 | 12.1204 | 12.1204 | Reduce | 1 | 12.1204 | 12.1204 | H1 | 5 | Stable | 0.8 | 113 | 122 | 157 | 126.3333 | 0.3 | 12 | 45 | 71 | 43.8333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK008 | Project_044_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Skills | Person_505 | 2017-10-21 01:00 | 2018-10-22 01:00 | 0.3 | 1.5695 | 0.47085 | Reduce | 0.3 | 1.4488 | 0.43463 | H2 | 4 | Stable | 0.5 | 115 | 122 | 155 | 126.3333 | 0.2 | 13 | 54 | 74 | 50.5 | 7.6924 | 0 | 0 | 4.6155
2018-01-21 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK003 | Project_044_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Mono vs stereo Component | Person_358 | 2016-03-23 | 2018-10-22 01:00 | 0.7 | 14.4876 | 10.1413 | Reduce | 0.5 | 14.4876 | 7.2438 | H2 | 4 | Stable | 0.7 | 102 | 139 | 155 | 135.5 | 0.4 | 11 | 58 | 73 | 52.6667 | 0 | 28.5714 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK035 | Project_042_RISK035 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st October to 31st December | Person_455 | 2021-02-20 01:00 | 2021-05-22 | 0.2 | 14.5313 | 2.9063 | Accept | 0.15 | 14.5313 | 2.9063 | H2 | 4 | Stable | 0.7 | 107 | 140 | 156 | 137.1667 | 0.7 | 107 | 140 | 156 | 137.1667 | 0 | 25 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Additional minor point release | Person_228 | 2016-05-23 | 2018-10-21 01:00 | 0.5 | 11.9444 | 5.9722 | Reduce | 0.25 | 11.9444 | 2.9861 | H2 | 4 | Stable | 0.6 | 114 | 125 | 157 | 128.5 | 0.1 | 14 | 48 | 68 | 45.6667 | 0 | 50 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_228 | 2016-05-23 | 2018-08-20 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.8 | 103 | 136 | 145 | 132 | 0.4 | 9 | 56 | 77 | 51.6667 | 0 | 50 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_004 | 2015-11-21 01:00 | 2018-11-20 01:00 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.6 | 104 | 128 | 156 | 128.6667 | 0.3 | 16 | 59 | 69 | 53.5 | 0 | 5 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.8 | 2.8043 | 2.2435 | Reduce | 0.45 | 2.8043 | 1.2619 | H1 | 5 | Stable | 0.9 | 113 | 133 | 148 | 132.1667 | 0.1 | 3 | 54 | 70 | 48.1667 | 0 | 43.75 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK167 | Project_024_RISK167 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Customer not providing the information needed or Customer not accepting the Customer documentation resulting in rewor. | Person_710 | 2016-08-21 01:00 | 2018-05-21 | 0.5 | 9.971 | 4.9855 | Reduce | 0.3 | 9.971 | 2.9913 | H1 | 5 | Worsening | 0.8 | 116 | 134 | 160 | 135.3333 | 0.1 | 28 | 49 | 62 | 47.6667 | 0 | 40 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK226 | Project_024_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Late Evidences Certification delivery | Person_642 | 2017-04-30 | 2018-05-21 | 0.4 | 3.9468 | 1.5787 | Reduce | 0.2 | 3.9468 | 0.78937 | H2 | 4 | Worsening | 0.6 | 80 | 137 | 157 | 130.8333 | 0.1 | 21 | 41 | 62 | 41.1667 | 0 | 50 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK034 | Project_042_RISK034 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st July to 30 September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 0.2 | 35.9673 | 10.7902 | Accept | 0.15 | 35.9673 | 9.7112 | H2 | 4 | Stable | 0.7 | 89 | 129 | 160 | 127.5 | 0.7 | 89 | 129 | 160 | 127.5 | 0 | 25 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK040 | Project_042_RISK040 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st May to 30 Oct | Person_455 | 2019-09-21 01:00 | 2020-03-21 | 0.1 | 3.9728 | 1.3905 | Accept | 0.07 | 3.9728 | 1.3905 | H2 | 4 | Stable | 0.6 | 100 | 126 | 148 | 125.3333 | 0.6 | 100 | 126 | 148 | 125.3333 | 0 | 30 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.6 | 118 | 123 | 143 | 125.5 | 0.4 | 24 | 49 | 72 | 48.6667 | 0 | 60 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis and Security | Person_288 | 2017-02-22 01:00 | 2018-08-20 | 0.3 | 19.9938 | 5.9981 | Reduce | 0.04675 | 19.9938 | 0.93471 | H3 | 3 | Improving | 0.9 | 114 | 124 | 156 | 127.6667 | 0.1 | 21 | 55 | 74 | 52.5 | 0 | 84.4167 | 1 | 2.5325
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.2 | 3.843 | 0.76859 | H2 | 4 | Stable | 0.6 | 81 | 127 | 159 | 124.6667 | 0.3 | 29 | 40 | 65 | 42.3333 | 0 | 60 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Performance (collector opportunity) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.373 | 19.5316 | 7.2853 | -- | 0.4158 | 19.5316 | 8.1213 | H1 | 5 | Stable | [10 empty] | 0 | -11.4745 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.3 | 20.8767 | 6.263 | H1 | 5 | Stable | 0.5 | 85 | 134 | 154 | 129.1667 | 0.4 | 3 | 55 | 69 | 48.6667 | 50 | 25 | 0 | 30
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.504 | 73.3644 | 36.9756 | Reduce | 0.0852 | 53.773 | 4.5815 | H2 | 4 | Worsening | 0.8 | 91 | 137 | 144 | 130.5 | 0.1 | 36 | 43 | 63 | 45.1667 | 26.7042 | 83.0952 | 0 | 16.0225
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK308 | Project_024_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System robustness and resilience | Person_774 | 2017-04-06 | 2018-06-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.1 | 2.5966 | 0.25966 | H3 | 3 | Stable | 0.9 | 106 | 122 | 153 | 124.5 | 0.4 | 14 | 52 | 60 | 47 | 58.3333 | 66.6667 | 1 | 37
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK042 | Project_042_RISK042 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st February to 14th July | Person_455 | 2020-06-23 | 2020-12-03 01:00 | 0.1 | 1.0618 | 0.53089 | Accept | 0.08 | 1.0618 | 0.53089 | H2 | 4 | Stable | 0.6 | 109 | 122 | 152 | 124.8333 | 0.6 | 109 | 122 | 152 | 124.8333 | 0 | 20 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 1.3834 | 0.55336 | H2 | 4 | Stable | 0.7 | 88 | 125 | 154 | 123.6667 | 0.4 | 14 | 40 | 69 | 40.5 | 65.054 | 20 | 0 | 39.0324
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_703 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 5.0983 | 0.76474 | H3 | 3 | Stable | 0.5 | 82 | 129 | 141 | 123.1667 | 0.1 | 13 | 52 | 62 | 47.1667 | 19.0479 | 70 | 1 | 13.5287
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-054 | Project_062_Risk-054 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | sub-system rework to reviised standard | Person_031 | 2017-07-21 | 2018-11-21 01:00 | 0.4 | 0.62744 | 0.25098 | Transfer | 0.4 | 0.62744 | 0.25098 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-010 | Project_062_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Resource | Person_479 | 2017-07-21 | 2019-02-21 01:00 | 0.25 | 17.6033 | 4.4008 | Reduce | 0.25 | 17.6033 | 4.4008 | H2 | 4 | Stable | 0.5 | 84 | 128 | 155 | 125.1667 | 0.2 | 17 | 54 | 74 | 51.1667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK041 | Project_042_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st Jan | Person_455 | 2020-03-23 | 2020-06-22 | 0.1 | 4.183 | 1.2549 | Accept | 0.08 | 4.183 | 1.2549 | H2 | 4 | Stable | 0.8 | 84 | 134 | 144 | 127.3333 | 0.8 | 84 | 134 | 144 | 127.3333 | 0 | 20 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-013 | Project_062_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Unavailability of Network | Person_479 | 2017-07-21 | 2018-05-22 | 0.25 | 3.5555 | 0.88888 | Reduce | 0.2 | 3.5555 | 0.7111 | H3 | 3 | Stable | 0.9 | 118 | 128 | 154 | 130.6667 | 0.3 | 5 | 40 | 66 | 38.5 | 0 | 20 | 1 | 0.6
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-055 | Project_062_Risk-055 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Supplier integration and Apps | Person_245 | 2017-07-21 | 2018-11-21 01:00 | 0.5 | 0.83659 | 0.4183 | Reduce | 0.5 | 0.83659 | 0.4183 | H2 | 4 | Stable | 0.9 | 112 | 139 | 151 | 136.5 | 0.2 | 36 | 45 | 78 | 49 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-011 | Project_062_Risk-011 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Variant deviations between SW | Person_479 | 2017-07-21 | 2018-02-17 01:00 | 0.4 | 0.71808 | 0.28723 | Reduce | 0.3 | 0.71808 | 0.21542 | H2 | 4 | Stable | 0.9 | 82 | 133 | 156 | 128.3333 | 0.3 | 11 | 43 | 71 | 42.3333 | 0 | 25 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-056 | Project_062_Risk-056 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Supplier integration acceptance by end Customer | Person_031 | 2017-07-21 | 2018-11-21 01:00 | 0.3 | 1.8823 | 0.5647 | Reduce | 0.3 | 1.8823 | 0.5647 | H3 | 3 | Stable | 0.5 | 108 | 133 | 146 | 131 | 0.3 | 14 | 51 | 67 | 47.5 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-017 | Project_062_Risk-017 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer platform Schedule Unknown | Person_459 | 2017-07-21 | 2018-10-22 01:00 | 0.2 | 2.5098 | 0.50196 | Avoid | 0.1 | 2.5098 | 0.25098 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Local customer Engineers in country | Person_455 | 2018-12-20 01:00 | 2021-05-22 | 0.05 | 12.7037 | 4.4463 | Accept | 0.05 | 12.7037 | 3.8111 | H2 | 4 | Stable | 0.9 | 94 | 137 | 154 | 132.6667 | 0.9 | 94 | 137 | 154 | 132.6667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-037 | Project_062_Risk-037 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Server availability | Person_459 | 2017-07-21 | 2018-04-22 | 0.35 | 4.183 | 1.464 | Avoid | 0.1 | 4.183 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 71.4286 | 1 | 2.1429
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-038 | Project_062_Risk-038 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Delay in start of Phase 2 | Person_459 | 2017-07-21 | 2018-02-20 01:00 | 0.2 | 2.0915 | 0.4183 | Avoid | 0.2 | 2.0915 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-016 | Project_062_Risk-016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Supplier Component Unavailability | Person_664 | 2017-07-21 | 2018-05-15 | 0.3 | 2.0927 | 0.62782 | Reduce | 0.2 | 2.0915 | 0.4183 | H3 | 3 | Stable | 0.5 | 96 | 138 | 158 | 134.3333 | 0.2 | 9 | 52 | 73 | 48.3333 | 0.059964 | 33.3333 | 0 | 0.035978
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-050 | Project_062_Risk-050 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SW v1.2 in use on some Hardware | Person_245 | 2017-07-21 | 2018-11-21 01:00 | 0.1 | 4.183 | 0.4183 | Avoid | 0.1 | 4.183 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-020 | Project_062_Risk-020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Security Encryption Solution | Person_245 | 2017-07-21 | 2018-09-20 01:00 | 0.25 | 4.183 | 1.0457 | Reduce | 0.2 | 4.183 | 0.83659 | H2 | 4 | Stable | 0.9 | 100 | 139 | 149 | 134.1667 | 0.2 | 10 | 53 | 61 | 47.1667 | 0 | 20 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-021 | Project_062_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Hardware CoSupplierng | Person_664 | 2017-07-21 | 2018-07-20 | 0.3 | 6.2744 | 1.8823 | Reduce | 0.25 | 6.2744 | 1.5686 | H2 | 4 | Stable | 0.6 | 96 | 123 | 151 | 123.1667 | 0.4 | 10 | 47 | 66 | 44 | 0 | 16.6667 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-043 | Project_062_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | User response | Person_459 | 2017-07-21 | 2019-02-21 01:00 | 0.35 | 3.3464 | 1.1712 | Avoid | 0.25 | 3.3464 | 0.83659 | H2 | 4 | Stable | [10 empty] | 0 | 28.5714 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-002 | Project_062_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | SDLC Card Obsolescence | Person_253 | 2017-07-21 | 2019-03-22 | 0.5 | 2.0915 | 1.0457 | Transfer | 0.2 | 2.0915 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 60 | 1 | 1.8
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-047 | Project_062_Risk-047 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Redhat6 on PCI shelf | Person_245 | 2017-07-21 | 2018-07-22 | 0.3 | 7.1808 | 2.1542 | Avoid | 0.3 | 7.1808 | 2.1542 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-025 | Project_062_Risk-025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | System Obsolescence Risk | Person_543 | 2017-07-21 | 2019-03-22 | 0.3 | 2.0915 | 0.62744 | Avoid | 0.2 | 2.0915 | 0.4183 | H2 | 4 | Stable | [10 empty] | 0 | 33.3333 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-022 | Project_062_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Registers Might Be Unstable | Person_479 | 2017-07-21 | 2018-04-22 | 0.1 | 0.8589 | 0.08589 | Reduce | 0.1 | 0.8589 | 0.08589 | H3 | 3 | Stable | 0.7 | 107 | 125 | 160 | 127.8333 | 0.1 | 9 | 44 | 77 | 43.6667 | 0 | 0 | 1 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-001 | Project_062_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier servers | Person_459 | 2017-10-21 01:00 | 2018-05-23 | 0.5 | 1.2549 | 0.62744 | Reduce | 0.5 | 1.2549 | 0.62744 | H2 | 4 | Stable | 0.8 | 111 | 135 | 159 | 135 | 0.4 | 30 | 50 | 68 | 49.6667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-023 | Project_062_Risk-023 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Change In Security Boundary | Person_031 | 2017-07-21 | 2019-02-21 01:00 | 0.3 | 4.6013 | 1.3804 | Reduce | 0.2 | 4.6013 | 0.92025 | H3 | 3 | Stable | 0.9 | 112 | 134 | 148 | 132.6667 | 0.1 | 5 | 45 | 67 | 42 | 0 | 33.3333 | 1 | 1
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-006 | Project_062_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unavailability of Hardware | Person_253 | 2017-07-21 | 2019-03-22 | 0.5 | 2.5098 | 1.2549 | Reduce | 0.25 | 2.5098 | 0.62744 | H2 | 4 | Stable | 0.7 | 105 | 140 | 143 | 134.6667 | 0.3 | 30 | 41 | 60 | 42.3333 | 0 | 50 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-048 | Project_062_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software lockdown features | Person_245 | 2017-07-21 | 2018-11-21 01:00 | 0.5 | 0.71808 | 0.35904 | Reduce | 0.5 | 0.71808 | 0.35904 | H2 | 4 | Stable | 0.7 | 104 | 128 | 150 | 127.6667 | 0.4 | 39 | 52 | 72 | 53.1667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-005 | Project_062_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Security Solution Integration | Person_245 | 2017-07-21 | 2018-11-14 01:00 | 0.3 | 4.6013 | 1.3804 | Avoid | 0.25 | 4.6013 | 1.1503 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Survey costs | Person_618 | 2016-04-22 | 2018-08-21 | 0.2 | 13.2573 | 2.6515 | Avoid | 0.2 | 13.2573 | 2.6515 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_431 | 2016-06-23 | 2018-08-21 | 0.2 | 33.9324 | 10.1797 | Accept | 0.2 | 33.9324 | 10.1797 | H2 | 4 | Stable | 0.7 | 102 | 140 | 153 | 135.8333 | 0.7 | 102 | 140 | 153 | 135.8333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-099 | Project_008_Risk-099 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Risk on Consumables Exposure | Person_639 | 2017-08-04 | 2018-08-21 | 0.5 | 5.6817 | 2.8408 | Reduce | 0.5 | 5.6817 | 2.8408 | H3 | 3 | Stable | 0.6 | 88 | 130 | 156 | 127.3333 | 0.2 | 16 | 50 | 68 | 47.3333 | 0 | 0 | 1 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_147 | 2016-04-21 | 2018-08-21 | 0.25 | 9.4695 | 4.7347 | Accept | 0.25 | 9.4695 | 4.7347 | H3 | 3 | Stable | 0.8 | 111 | 124 | 150 | 126.1667 | 0.8 | 111 | 124 | 150 | 126.1667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Succession Planning | Person_619 | 2012-08-21 01:00 | 2019-08-07 | 0.61 | 5.9546 | 3.6323 | Reduce | 0.3 | 5.9546 | 1.7864 | H2 | 4 | Improving | 0.5 | 103 | 125 | 153 | 126 | 0.1 | 32 | 44 | 77 | 47.5 | 0 | 50.8197 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_373 | 2012-08-21 01:00 | 2019-08-07 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 2.2054 | 1.3453 | H1 | 5 | Stable | 0.8 | 107 | 129 | 149 | 128.6667 | 0.2 | 1 | 42 | 75 | 40.6667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-07 | 0.2 | 2.8891 | 0.57782 | Reduce | 0.2 | 2.8891 | 0.57782 | H3 | 3 | Stable | 0.8 | 104 | 134 | 143 | 130.5 | 0.3 | 15 | 57 | 79 | 53.6667 | 0 | 0 | 1 | 0
2018-01-21 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK044 | Project_053_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Product Hardening | Person_719 | 2018-03-23 | 2019-01-20 01:00 | 0.3 | 7.9015 | 2.3705 | Avoid | 0.3 | 7.9015 | 2.3705 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK048 | Project_042_RISK048 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | On the Job Training. | Person_371 | 2018-03-02 01:00 | 2019-02-05 01:00 | 0.85 | 2.1043 | 1.7886 | Reduce | 0.5 | 2.1043 | 1.0521 | H1 | 5 | Stable | 0.7 | 114 | 136 | 158 | 136 | 0.3 | 32 | 47 | 75 | 49.1667 | 0 | 41.1765 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK003 | Project_024_RISK003 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance | Person_288 | 2017-12-21 01:00 | 2018-08-21 | 0.31667 | 1.8788 | 0.46971 | Accept | 0.04388 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.9 | 92 | 126 | 149 | 124.1667 | 0.9 | 92 | 126 | 149 | 124.1667 | 20 | 86.1432 | 0 | 12
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK049 | Project_042_RISK049 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Industry STTE Upkeep. | Person_371 | 2018-03-02 01:00 | 2019-02-05 01:00 | 0.85 | 1.3152 | 1.1179 | Reduce | 0.5 | 1.3152 | 0.65759 | H2 | 4 | Stable | 0.5 | 86 | 122 | 146 | 120 | 0.3 | 29 | 42 | 68 | 44.1667 | 0 | 41.1765 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before part b finished | Person_119 | 2016-10-20 01:00 | 2018-05-21 | 0.3 | 1.8788 | 0.46971 | Accept | 0.27 | 1.5031 | 0.22546 | H2 | 4 | Worsening | 0.8 | 100 | 131 | 147 | 128.5 | 0.8 | 100 | 131 | 147 | 128.5 | 20 | 10 | 0 | 12
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Labour/Material Risk | Person_662 | 2015-05-24 | 2019-05-23 | 0.5 | 3.6256 | 1.4502 | Accept | 0.5 | 3.6256 | 1.4502 | H2 | 4 | Stable | 0.8 | 94 | 139 | 154 | 134 | 0.8 | 94 | 139 | 154 | 134 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_009 | Project_045 | RISK001 | Project_045_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour/T&S Overspend | Person_662 | 2017-01-21 01:00 | 2020-05-22 | 0.5 | 6.0991 | 4.0864 | Accept | 0.5 | 6.0991 | 4.0864 | H2 | 4 | Stable | 0.6 | 110 | 138 | 159 | 136.8333 | 0.6 | 110 | 138 | 159 | 136.8333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | FOC Acceptance | Person_499 | 2018-05-23 | 2018-07-21 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.15 | 8.471 | 1.2706 | H3 | 3 | Stable | 0.8 | 102 | 128 | 154 | 128 | 0.3 | 2 | 57 | 61 | 48.5 | -99.9999 | 57.1429 | 1 | -58.2857
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-057 | Project_062_Risk-057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Supplier Application Encryption / Protection | Person_253 | 2017-07-21 | 2019-02-21 01:00 | 0.3 | 8.8098 | 3.0834 | Accept | 0.3 | 8.8098 | 1.762 | H2 | 4 | Stable | 0.9 | 84 | 124 | 154 | 122.3333 | 0.9 | 84 | 124 | 154 | 122.3333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK024 | Project_048_RISK024 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Procurement/ Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 0.8 | 0 | 0 | -- | 0.8 | 0 | 0 | H1 | 5 | Worsening | [11 empty] | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK024 | Project_063_RISK024 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Procurement/ Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 0.8 | 0 | 0 | -- | 0.8 | 0 | 0 | H1 | 5 | Worsening | [11 empty] | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_008 | Project_057 | Risk-01 | Project_057_Risk-01 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Cable | Person_464 | 2015-08-22 01:00 | 2016-12-21 01:00 | 0.1 | 12.6408 | 1.2641 | Avoid | 0.1 | 0.23232 | 0.023232 | H2 | 4 | Improving | [10 empty] | 98.1622 | 0 | 0 | 58.8973
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE-01 | Project_067_SE-01 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Procurement of Cables for Rig (Procurement Process) | Person_327 | 2015-08-22 01:00 | 2018-08-21 | 0.4 | 0.63006 | 0.25202 | Reduce | 0.2 | 0.31503 | 0.063006 | H3 | 3 | Stable | 0.6 | 112 | 127 | 141 | 126.8333 | 0.2 | 2 | 59 | 73 | 51.8333 | 50 | 50 | 1 | 31.5
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-R1 | Project_067_Risk-R1 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Rhapsody modification to manual to System interface | Person_327 | 2017-03-23 | 2018-08-13 | 0.3 | 7.8758 | 2.3627 | Reduce | 0.2 | 2.2502 | 0.45004 | H3 | 3 | Stable | 0.6 | 91 | 125 | 155 | 124.3333 | 0.3 | 25 | 52 | 71 | 50.6667 | 71.4286 | 33.3333 | 1 | 43.8571
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE-10 | Project_067_SE-10 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Configuration baseline unstable for Platform | Person_327 | 2017-10-26 01:00 | 2018-08-18 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.5 | 104 | 134 | 143 | 130.5 | 0.3 | 14 | 40 | 62 | 39.3333 |  | 60 | 1
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE-08 | Project_067_SE-08 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Ageing Test Infrastructure | Person_327 | 2015-10-01 01:00 | 2018-08-21 | 0.6 | 0 | 0 | Transfer | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 33.3333 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-R4 | Project_067_Risk-R4 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Resource Availability | Person_011 | 2015-08-22 01:00 | 2018-08-21 | 0.45 | 2.579 | 1.1606 | Reduce | 0.6 | 1.2857 | 0.77145 | H1 | 5 | Improving | 0.8 | 105 | 137 | 141 | 132.3333 | 0.1 | 38 | 43 | 77 | 47.8333 | 50.1455 | -33.3333 | 0 | 30.0873
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-R2 | Project_067_Risk-R2 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Sub-Contractor Performance - Manufacturing | Person_011 | 2015-08-22 01:00 | 2018-08-20 | 0.3 | 0.23127 | 0.069382 | Reduce | 0.1 | 0.040628 | 0.0040628 | H3 | 3 | Improving | 0.6 | 101 | 128 | 156 | 128.1667 | 0.2 | 36 | 44 | 60 | 45.3333 | 82.4331 | 66.6667 | 1 | 51.4598
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-R6 | Project_067_Risk-R6 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub-Contractor Performance - Support Services | Person_011 | 2017-08-21 01:00 | 2018-08-21 | 0.5 | 2.2502 | 1.1251 | Reduce | 0.5 | 2.2502 | 1.1251 | H2 | 4 | Stable | 0.9 | 119 | 127 | 143 | 128.3333 | 0.1 | 31 | 44 | 66 | 45.5 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-034 | Project_062_Risk-034 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Long lead Procurement price increases | Person_664 | 2017-07-21 | 2018-04-22 | 0.25 | 5.2705 | 1.5811 | Accept | 0.25 | 4.3921 | 0.87842 | H2 | 4 | Stable | 0.6 | 87 | 128 | 141 | 123.3333 | 0.6 | 87 | 128 | 141 | 123.3333 | 16.6667 | 0 | 0 | 10
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-018 | Project_062_Risk-018 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Prioritisation - new or less experienced staff | Person_459 | 2017-07-21 | 2018-11-20 01:00 | 0.35 | 0 | 0 | Accept | 0.3 | 0 | 0 | H2 | 4 | Improving | 0.8 | 106 | 133 | 143 | 130.1667 | 0.8 | 106 | 133 | 143 | 130.1667 |  | 14.2857 | 0
2018-01-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-04-20 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.6 | 112 | 124 | 146 | 125.6667 | 0.2 | 4 | 53 | 78 | 49 | 0 | 25 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-009 | Project_062_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Unresolved technical debt (excluding ILS) | Person_253 | 2017-07-21 | 2018-05-22 | 0.5 | 5.596 | 0.2798 | Accept | 0.5 | 5.596 | 0.2798 | H2 | 4 | Stable | 0.8 | 118 | 139 | 160 | 139 | 0.8 | 118 | 139 | 160 | 139 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-085 | Project_008_SER-085 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Insufficient LOE to manage the supply chain with reducing number of spares | Person_639 | 2017-04-22 | 2018-08-21 | 0.25 | 0 | 0 | Accept | 0.25 | 0 | 0 | H3 | 3 | Stable | 0.5 | 108 | 121 | 154 | 124.3333 | 0.5 | 108 | 121 | 154 | 124.3333 |  | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_567 | 2017-08-21 01:00 | 2018-08-21 | 0.3 | 0.5596 | 0.05596 | Accept | 0.3 | 0.5596 | 0.05596 | H2 | 4 | Stable | 0.9 | 117 | 125 | 148 | 127.5 | 0.9 | 117 | 125 | 148 | 127.5 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Lack of Spares Availability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 0.3 | 2.3503 | 0.47006 | Accept | 0.3 | 2.3503 | 0.47006 | H3 | 3 | Stable | 0.6 | 84 | 127 | 145 | 122.8333 | 0.6 | 84 | 127 | 145 | 122.8333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-148 | Project_008_SER-148 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Demands but not provisioned | Person_639 | 2017-08-21 01:00 | 2018-08-21 | 0.3 | 4.4768 | 2.2384 | Accept | 0.3 | 4.4768 | 2.2384 | H3 | 3 | Stable | 0.8 | 118 | 123 | 150 | 126.6667 | 0.8 | 118 | 123 | 150 | 126.6667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_077 | 2016-01-22 01:00 | 2018-02-17 01:00 | 0.15 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Improving | 0.6 | 93 | 124 | 155 | 124 | 0.4 | 33 | 44 | 67 | 46 |  | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-094 | Project_008_Risk-094 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Consumable Stock Levels | Person_567 | 2017-04-22 | 2018-08-21 | 0.5 | 6.3794 | 1.2759 | Accept | 0.5 | 6.3794 | 1.2759 | H3 | 3 | Stable | 0.9 | 98 | 124 | 144 | 123 | 0.9 | 98 | 124 | 144 | 123 | 0 | 0 | 1 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-000 | Project_008_SER-000 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_567 | 2018-05-22 | 2018-08-21 | 0.25 | 23.5255 | 11.7628 | Accept | 0.25 | 23.5255 | 11.7628 | H3 | 3 | Stable | 0.9 | 114 | 125 | 158 | 128.6667 | 0.9 | 114 | 125 | 158 | 128.6667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-004 | Project_062_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Undefined risks | Person_459 | 2017-07-21 | 2019-03-24 | 0.35 | 60.4367 | 3.0218 | Accept | 0.35 | 60.4367 | 3.0218 | H2 | 4 | Stable | 0.6 | 82 | 136 | 154 | 130 | 0.6 | 82 | 136 | 154 | 130 | 0 | 0 | 0 | 0
2018-01-21 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK047 | Project_053_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Lab Availability | Person_252 | 2017-10-21 01:00 | 2020-01-22 01:00 | 0.5 | 3.772 | 2.6404 | Accept | 0.2 | 3.772 | 2.6404 | H3 | 3 | Improving | 0.8 | 80 | 140 | 150 | 131.6667 | 0.8 | 80 | 140 | 150 | 131.6667 | 0 | 60 | 1 | 1.8
2018-01-21 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK043 | Project_053_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Change in REACH/RoSH Legislation | Person_302 | 2017-11-20 01:00 | 2018-09-20 01:00 | 0.1 | 5.8198 | 4.0739 | Accept | 0.1 | 5.8198 | 4.0739 | H2 | 4 | Stable | 0.5 | 102 | 138 | 150 | 134 | 0.5 | 102 | 138 | 150 | 134 | 0 | 0 | 0 | 0
2018-01-21 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK046 | Project_053_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Un-Planned Production Activities | Person_252 | 2019-07-22 | 2020-01-22 01:00 | 0.5 | 2.2586 | 0.90343 | Accept | 0.2 | 2.2586 | 0.90343 | H3 | 3 | Stable | 0.7 | 116 | 137 | 142 | 134.3333 | 0.7 | 116 | 137 | 142 | 134.3333 | 0 | 60 | 1 | 1.8
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK026 | Project_042_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st Jan to 31st March | Person_455 | 2020-05-23 | 2020-08-20 01:00 | 0.25 | 2.9272 | 1.4636 | Accept | 0.15 | 2.9272 | 1.4636 | H2 | 4 | Stable | 0.7 | 99 | 125 | 149 | 124.6667 | 0.7 | 99 | 125 | 149 | 124.6667 | 0 | 40 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK025 | Project_042_RISK025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to 31 Dec | Person_455 | 2020-09-20 01:00 | 2021-05-22 | 0.2 | 4.4984 | 2.2492 | Accept | 0.15 | 4.4984 | 2.2492 | H2 | 4 | Stable | 0.9 | 116 | 133 | 155 | 133.8333 | 0.9 | 116 | 133 | 155 | 133.8333 | 0 | 25 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK028 | Project_042_RISK028 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st July to 30th September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 0.25 | 1.6962 | 0.33923 | Accept | 0.15 | 1.6962 | 0.33923 | H2 | 4 | Stable | 0.9 | 101 | 128 | 141 | 125.6667 | 0.9 | 101 | 128 | 141 | 125.6667 | 0 | 40 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK027 | Project_042_RISK027 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st April to 30th June | Person_455 | 2020-08-21 01:00 | 2020-09-19 01:00 | 0.25 | 18.9062 | 9.4531 | Accept | 0.15 | 18.9062 | 9.4531 | H2 | 4 | Stable | 0.7 | 105 | 140 | 151 | 136 | 0.7 | 105 | 140 | 151 | 136 | 0 | 40 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK037 | Project_042_RISK037 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 1 | Person_455 | 2020-05-23 | 2021-05-22 | 0.14 | 3.7214 | 0.93035 | Accept | 0.14 | 3.7214 | 0.93035 | H2 | 4 | Stable | 0.7 | 120 | 139 | 156 | 138.6667 | 0.7 | 120 | 139 | 156 | 138.6667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of the platforms for modification | Person_496 | 2014-01-21 01:00 | 2019-04-10 | 0.67 | 3.7207 | 0.93016 | Accept | 0.67 | 3.7207 | 0.93016 | H2 | 4 | Stable | 0.6 | 88 | 135 | 147 | 129.1667 | 0.6 | 88 | 135 | 147 | 129.1667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_523 | 2018-05-23 | 2018-07-21 | 0.35 | 8.2789 | 2.4837 | Accept | 0.2 | 8.2789 | 2.4837 | H2 | 4 | Stable | 0.7 | 90 | 138 | 144 | 131 | 0.7 | 90 | 138 | 144 | 131 | 0 | 42.8571 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK003 | Project_001_RISK003 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Non-Recurring Engineering higher than expected | Person_674 | 2017-12-21 | 2018-08-21 | 0.5 | 16.0059 | 8.0029 | Reduce | 0.2 | 8.0029 | 1.6006 | H3 | 3 | Improving | 0.5 | 98 | 121 | 159 | 123.5 | 0.1 | 30 | 44 | 61 | 44.5 | 50 | 60 | 0 | 30
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK010 | Project_041_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Assembly - Testing | Person_547 | 2016-11-20 01:00 | 2019-08-21 01:00 | 0.1 | 0.51448 | 0.051448 | -- | 0.1 | 0.51448 | 0.051448 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unforseen and substantial increase in Repairs workload during new build production period. | Person_238 | 2017-10-23 01:00 | 2019-08-21 01:00 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.25 | 1.5434 | 0.38586 | H2 | 4 | Stable | 0.9 | 108 | 130 | 150 | 129.6667 | 0.2 | 32 | 43 | 75 | 46.5 | 0 | 16.6667 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK007 | Project_041_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Advanced production of products using a Qual. standard component rather than a Prod. standard | Person_547 | 2017-10-21 01:00 | 2018-06-22 | 0.49 | 1.2862 | 0.63024 | Reduce | 0.2 | 1.2862 | 0.25724 | H3 | 3 | Stable | 0.9 | 102 | 134 | 155 | 132.1667 | 0.3 | 31 | 50 | 69 | 50 | 0 | 59.1837 | 1 | 1.7755
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_693 | 2017-07-21 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.7 | 94 | 131 | 144 | 127 | 0.1 | 39 | 41 | 72 | 45.8333 | 0 | 50 | 0 | 0
2018-01-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2018-10-21 01:00 | 0.05 | 1.9722 | 0.98609 | Accept | 0.05 | 1.9722 | 0.98609 | H3 | 3 | Improving | 0.7 | 108 | 122 | 155 | 125.1667 | 0.7 | 108 | 122 | 155 | 125.1667 | 0 | 0 | 1 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment (Second Test Set) | Person_238 | 2017-05-23 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.05 | 0.68598 | 0.034299 | H3 | 3 | Improving | 0.5 | 90 | 126 | 158 | 125.3333 | 0.1 | 10 | 43 | 60 | 40.3333 | 0 | 80 | 1 | 2.4
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2017-05-23 | 2019-08-20 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Stable | 0.5 | 115 | 121 | 150 | 124.8333 | 0.3 | 39 | 57 | 77 | 57.3333 | 0 | 60 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_238 | 2017-04-22 | 2018-05-22 | 0.25 | 3.3227 | 0.83067 | Reduce | 0.012 | 3.3055 | 0.039667 | H3 | 3 | Stable | 0.9 | 104 | 133 | 160 | 132.6667 | 0.2 | 4 | 53 | 71 | 47.8333 | 0.51615 | 95.2 | 1 | 3.1657
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Outstanding CRs | Person_693 | 2017-05-23 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.5 | 0.77172 | 0.38586 | H2 | 4 | Stable | 0.9 | 106 | 123 | 156 | 125.6667 | 0.2 | 24 | 51 | 62 | 48.3333 | 0 | -100 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_693 | 2017-05-23 | 2018-01-20 01:00 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.02 | 6.431 | 0.12862 | H3 | 3 | Improving | 0.8 | 101 | 131 | 155 | 130 | 0.4 | 30 | 53 | 60 | 50.3333 | -47.0588 | 86.6667 | 1 | -25.6353
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Reduce touch labour if Production readiness programme successful | Person_238 | 2017-05-23 | 2018-03-23 | 0.3 | 1.5606 | 0.46818 | Exploit | 0.5 | 1.5606 | 0.7803 | H2 | 4 | Stable | [10 empty] | 0 | -66.6667 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 06:00 | 2019-08-20 06:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 06:00 | 2019-08-20 06:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 06:00 | 2019-08-20 06:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 06:00 | 2019-08-20 06:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 06:00 | 2019-08-20 06:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2018-05-22 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.5 | 84 | 134 | 144 | 127.3333 | 0.1 | 18 | 50 | 61 | 46.5 | 0 | 40 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 0.92411 | 0.55447 | Reduce | 0.5 | 0.36965 | 0.18482 | H2 | 4 | Stable | 0.9 | 86 | 134 | 154 | 129.3333 | 0.3 | 8 | 47 | 72 | 44.6667 | 60 | 16.6667 | 0 | 36
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 | 2018-04-21 | 0.2 | 4.0661 | 0.81322 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.5 | 107 | 124 | 149 | 125.3333 | 0.1 | 20 | 59 | 79 | 55.8333 | 0 | 75 | 1 | 2.25
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.5 | 0.46206 | 0.23103 | H1 | 5 | Stable | 0.5 | 83 | 129 | 141 | 123.3333 | 0.4 | 1 | 51 | 74 | 46.5 | 58.3333 | 16.6667 | 0 | 35
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 | 2018-05-22 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.5 | 97 | 123 | 149 | 123 | 0.2 | 6 | 41 | 70 | 40 | 0 | 50 | 1 | 1.5
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2018-05-22 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.9 | 110 | 136 | 155 | 134.8333 | 0.3 | 33 | 48 | 74 | 49.8333 | 0 | 25 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_693 | 2012-06-01 | 2018-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Improving | 0.6 | 95 | 140 | 158 | 135.5 | 0.3 | 21 | 43 | 66 | 43.1667 | 0 | 40 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2018-05-21 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Stable | [10 empty] | 0 | 37.5 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2018-02-19 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.9 | 101 | 126 | 143 | 124.6667 | 0.1 | 20 | 56 | 71 | 52.5 | 90 | 75 | 1 | 56.25
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK010 | Project_010_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Use of Lead components | Person_359 | 2012-05-23 | 2025-04-22 | 0.05 | 1.8482 | 0.092411 | Reduce | 0.05 | 1.8482 | 0.092411 | H3 | 3 | Stable | 0.7 | 120 | 131 | 157 | 133.5 | 0.1 | 18 | 42 | 79 | 44.1667 | 0 | 0 | 1 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-117 | Project_043_Risk-117 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Supplier Technical Publications maturity not at the level required | Person_769 | 2017-04-19 | 2018-05-13 | 0.45 | 1.7366 | 0.78146 | Reduce | 0.45 | 1.7366 | 0.78146 | H1 | 5 | Improving | 0.6 | 107 | 137 | 154 | 134.8333 | 0.2 | 9 | 58 | 73 | 52.3333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-111 | Project_043_Risk-111 | Opportunitity | Project Contingency | Open | H1 | 5 | 7. Finance | Decrease the cost of obsolescence sweeps | Person_769 | 2018-01-11 01:00 | 2020-12-21 01:00 | 0.5 | 0.038325 | 0.019162 | Exploit | 0.5 | 0.038325 | 0.019162 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-113 | Project_043_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | No Gen 1 products available, transition cost to Gen 2 | Person_769 | 2017-04-19 | 2020-12-21 01:00 | 0.3 | 1.4971 | 0.44912 | Reduce | 0.3 | 1.4971 | 0.44912 | H2 | 4 | Stable | 0.9 | 110 | 133 | 149 | 131.8333 | 0.1 | 21 | 52 | 69 | 49.6667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-121 | Project_043_Risk-121 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | More Tech Pubs Update than estimated | Person_769 | 2019-01-21 01:00 | 2020-10-20 01:00 | 0.45 | 1.7366 | 0.78146 | Reduce | 0.45 | 1.7366 | 0.78146 | H1 | 5 | Stable | 0.7 | 98 | 122 | 154 | 123.3333 | 0.2 | 26 | 55 | 73 | 53.1667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-084 | Project_043_Risk-084 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | complex repair ( over and above the forecast average) | Person_368 | 2017-12-21 01:00 | 2020-12-21 01:00 | 0.2 | 0.71859 | 0.14372 | Reduce | 0.2 | 0.71859 | 0.14372 | H2 | 4 | Stable | 0.7 | 85 | 140 | 150 | 132.5 | 0.4 | 5 | 53 | 66 | 47.1667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-128 | Project_043_Risk-128 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Reliance of Customer Avaliability | Person_135 | 2017-04-19 | 2018-08-21 | 0.5 | 1.7665 | 0.88326 | Reduce | 0.5 | 1.7665 | 0.88326 | H1 | 5 | Stable | 0.6 | 118 | 124 | 150 | 127.3333 | 0.3 | 35 | 43 | 66 | 45.5 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-089 | Project_043_Risk-089 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares pool is limited | Person_307 | 2018-12-22 01:00 | 2020-12-21 01:00 | 0.25 | 1.5969 | 0.39921 | Reduce | 0.25 | 1.2775 | 0.31937 | H2 | 4 | Stable | 0.9 | 95 | 125 | 157 | 125.3333 | 0.2 | 19 | 43 | 78 | 44.8333 | 20 | 0 | 0 | 12
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-001 | Project_043_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Training Programme capacity | Person_336 | 2017-04-28 | 2018-11-20 01:00 | 0.15 | 0 | 0 | Reduce | 0.05 | 0 | 0 | H3 | 3 | Improving | 0.5 | 105 | 123 | 147 | 124 | 0.1 | 34 | 53 | 72 | 53 |  | 66.6667 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-039 | Project_043_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System fails to achieve required performance | Person_051 | 2017-04-19 | 2018-11-20 01:00 | 0.3 | 4.7906 | 1.4372 | Reduce | 0.3 | 4.7906 | 1.4372 | H2 | 4 | Stable | 0.9 | 104 | 133 | 159 | 132.5 | 0.3 | 1 | 41 | 64 | 38.1667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK016 | Project_038_RISK016 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Supplier Quality Issues | Person_397 | 2012-11-20 01:00 | 2018-10-21 01:00 | 0.5 | 5.0339 | 2.517 | Avoid | 0.5 | 5.0339 | 2.517 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK018 | Project_038_RISK018 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Last System Syndrome | Person_060 | 2012-11-20 01:00 | 2018-10-21 01:00 | 0.15 | 43.4175 | 6.5126 | -- | 0.15 | 43.4175 | 6.5126 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-21 20:00 | 2016-12-20 20:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.5 | 82 | 137 | 160 | 131.6667 | 0.2 | 33 | 47 | 65 | 47.6667 | 47 | 0 | 0 | 28.2
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-21 20:00 | 2016-12-20 20:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-18 20:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.2 | 1.5935 | 0.3187 | H3 | 3 | Stable | 0.9 | 95 | 125 | 144 | 123.1667 | 0.1 | 11 | 54 | 60 | 47.8333 | 50 | 50 | 1 | 31.5
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS020 | Project_025_RS020 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Plant Machinery failure | Person_619 | 2017-03-23 | 2019-08-05 | 0.3 | 0.026907 | 0.0080721 | Reduce | 0.3 | 0.026907 | 0.0080721 | H2 | 4 | Stable | 0.7 | 104 | 124 | 149 | 124.8333 | 0.3 | 15 | 50 | 68 | 47.1667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS019 | Project_025_RS019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Product Component Failure | Person_619 | 2017-03-23 | 2019-08-07 | 0.7 | 0.82924 | 0.58047 | Reduce | 0.1 | 0.82924 | 0.082924 | H3 | 3 | Stable | 0.5 | 106 | 131 | 160 | 131.6667 | 0.1 | 18 | 41 | 76 | 43 | 0 | 85.7143 | 1 | 2.5714
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--28 | Project_021_Risk--28 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort required to agree protocl for Client Server | Person_766 | 2018-03-23 | 2019-03-23 | 0.8 | 1.1522 | 0.92174 | Reduce | 0.4 | 1.1522 | 0.46087 | H2 | 4 | Stable | 0.9 | 106 | 130 | 155 | 130.1667 | 0.4 | 26 | 53 | 76 | 52.3333 | 0 | 50 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--05 | Project_021_Risk--05 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification delays | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Worsening | 0.9 | 103 | 139 | 141 | 133.3333 | 0.1 | 9 | 40 | 66 | 39.1667 |  | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--04 | Project_021_Risk--04 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Final Qual test report delayed due to insufficient supply chain resource | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 0.2 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 97 | 121 | 154 | 122.5 | 0.2 | 13 | 41 | 70 | 41.1667 |  | 50 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--03 | Project_021_Risk--03 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.9 | 103 | 135 | 152 | 132.5 | 0.4 | 5 | 57 | 76 | 51.5 | 0 | 33.3333 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--25 | Project_021_Risk--25 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of supporting resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 93 | 126 | 152 | 124.8333 | 0.4 | 36 | 45 | 75 | 48.5 |  | 40 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--02 | Project_021_Risk--02 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_061 | 2018-02-20 01:00 | 2019-03-23 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.8 | 104 | 140 | 160 | 137.3333 | 0.2 | 36 | 42 | 68 | 45.3333 | 80 | 66.6667 | 0 | 48
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--24 | Project_021_Risk--24 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of equipment | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 98 | 128 | 153 | 127.1667 | 0.4 | 5 | 50 | 62 | 44.5 |  | 40 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--01 | Project_021_Risk--01 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification/ delay due to build standard issue | Person_615 | 2018-02-20 01:00 | 2018-06-22 | 0.1 | 2.2183 | 0.22183 | Reduce | 0.05 | 2.2183 | 0.11091 | H2 | 4 | Stable | 0.7 | 80 | 140 | 143 | 130.5 | 0.1 | 1 | 52 | 75 | 47.3333 | 0 | 50 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--21 | Project_021_Risk--21 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.7 | 87 | 129 | 145 | 124.6667 | 0.2 | 22 | 52 | 63 | 48.8333 |  | 40 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--09 | Project_021_Risk--09 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 111 | 126 | 153 | 128 | 0.4 | 15 | 42 | 70 | 42.1667 |  | 40 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--08 | Project_021_Risk--08 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H3 | 3 | Stable | 0.8 | 103 | 139 | 147 | 134.3333 | 0.4 | 2 | 59 | 71 | 51.5 |  | 62.5 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--07 | Project_021_Risk--07 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 0.6 | 17.2826 | 10.3696 | Reduce | 0.3 | 17.2826 | 5.1848 | H2 | 4 | Worsening | 0.7 | 115 | 122 | 143 | 124.3333 | 0.1 | 17 | 45 | 61 | 43 | 0 | 50 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--20 | Project_021_Risk--20 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | ERP implementation | Person_061 | 2018-01-21 01:00 | 2018-07-20 | 0.5 | 0 | 0 | Reduce | 0.25 | 0 | 0 | H2 | 4 | Stable | 0.7 | 92 | 129 | 150 | 126.3333 | 0.2 | 35 | 57 | 78 | 56.8333 |  | 50 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--17 | Project_021_Risk--17 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to technical performance | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.8 | 81 | 129 | 155 | 125.3333 | 0.2 | 1 | 58 | 79 | 52 |  | 33.3333 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--39 | Project_021_Risk--39 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Delay to completion of product upgrade | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.7 | 91 | 131 | 153 | 128 | 0.4 | 38 | 51 | 72 | 52.3333 |  | 40 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--16 | Project_021_Risk--16 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of weather | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.6 | 91 | 122 | 151 | 121.6667 | 0.2 | 2 | 58 | 75 | 51.5 |  | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--15 | Project_021_Risk--15 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to lack of personnel resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.8 | 117 | 130 | 159 | 132.6667 | 0.4 | 36 | 50 | 77 | 52.1667 |  | 33.3333 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--14 | Project_021_Risk--14 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to late Trials Approval | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 87 | 135 | 144 | 128.5 | 0.1 | 38 | 51 | 78 | 53.3333 |  | 66.6667 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--13 | Project_021_Risk--13 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Critical or Safety PR arises in Final build /Decision Point concludes new release req | Person_174 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.5 | 113 | 130 | 152 | 130.8333 | 0.2 | 27 | 48 | 76 | 49.1667 | 0 | 50 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--12 | Project_021_Risk--12 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.6 | 81 | 129 | 151 | 124.6667 | 0.3 | 26 | 55 | 77 | 53.8333 | 0 | 33.3333 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--11 | Project_021_Risk--11 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.5 | 85 | 130 | 149 | 125.6667 | 0.1 | 27 | 48 | 66 | 47.5 | 7.8429 | 40 | 0 | 4.7058
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--10 | Project_021_Risk--10 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Stable | 0.6 | 84 | 131 | 154 | 127 | 0.2 | 30 | 53 | 64 | 51 | 0 | 57.1429 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--32 | Project_021_Risk--32 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Lack of Customer resource to provide timely to Acceptance and Closure activities | Person_766 | 2018-10-22 01:00 | 2019-04-23 | 0.8 | 0 | 0 | Reduce | 0.4 | 0 | 0 | H2 | 4 | Stable | 0.8 | 116 | 122 | 155 | 126.5 | 0.2 | 35 | 48 | 63 | 48.3333 |  | 50 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--18 | Project_021_Risk--18 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.6 | 91 | 124 | 143 | 121.6667 | 0.1 | 5 | 51 | 65 | 45.6667 | 50 | 28.5714 | 0 | 30
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK011 | Project_041_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier Development support | Person_693 | 2016-11-20 01:00 | 2019-08-21 01:00 | 0.3 | 1.1744 | 0.46977 | Accept | 0.3 | 1.1744 | 0.46977 | H2 | 4 | Stable | 0.6 | 91 | 135 | 151 | 130.3333 | 0.6 | 91 | 135 | 151 | 130.3333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK002 | Project_041_RISK002 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Component Technical risk using new material | Person_653 | 2017-09-20 01:00 | 2018-05-22 | 0.4 | 2.9361 | 0.58721 | Accept | 0.4 | 2.9361 | 0.58721 | H3 | 3 | Stable | 0.5 | 111 | 133 | 152 | 132.5 | 0.5 | 111 | 133 | 152 | 132.5 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-21 21:00 | 2016-12-20 21:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.9 | 110 | 135 | 144 | 132.3333 | 0.4 | 31 | 46 | 67 | 47 | 47 | 0 | 0 | 28.2
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-21 21:00 | 2016-12-20 21:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-18 21:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.2 | 1.5935 | 0.3187 | H3 | 3 | Stable | 0.8 | 85 | 132 | 154 | 127.8333 | 0.2 | 34 | 55 | 62 | 52.6667 | 50 | 50 | 1 | 31.5
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK013 | Project_041_RISK013 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional components validation | Person_693 | 2017-07-15 | 2018-05-23 | 0.4 | 1.029 | 0.30869 | Accept | 0.4 | 1.029 | 0.30869 | H2 | 4 | Stable | 0.9 | 114 | 131 | 149 | 131.1667 | 0.9 | 114 | 131 | 149 | 131.1667 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK010 | Project_041_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Assembly - Testing | Person_547 | 2018-01-28 01:00 | 2018-03-30 | 0.3 | 0.51448 | 0.15434 | -- | 0.3 | 0.51448 | 0.15434 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Risk of not being able to perform Tests | Person_238 | 2017-12-21 01:00 | 2019-01-21 01:00 | 0.5 | 0.38586 | 0.11576 | Accept | 0.5 | 0.38586 | 0.11576 | H2 | 4 | Stable | 0.7 | 89 | 133 | 146 | 127.8333 | 0.7 | 89 | 133 | 146 | 127.8333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.8 | 90 | 130 | 152 | 127 | 0.1 | 35 | 40 | 71 | 44.3333 | 60.3671 | 58.3333 | 0 | 36.2202
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_238 | 2017-05-23 | 2019-01-21 01:00 | 0.5 | 1.9438 | 0.77753 | Accept | 0.5 | 1.9438 | 0.77753 | H2 | 4 | Stable | 0.9 | 119 | 124 | 150 | 127.5 | 0.9 | 119 | 124 | 150 | 127.5 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_547 | 2017-05-23 | 2018-06-22 | 0.1 | 8.0289 | 1.6058 | Accept | 0.1 | 2.5354 | 0.50709 | H3 | 3 | Stable | 0.5 | 80 | 124 | 157 | 122.1667 | 0.5 | 80 | 124 | 157 | 122.1667 | 68.421 | 0 | 1 | 41.0526
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production, Procurement or Engineering | Person_725 | 2018-01-21 01:00 | 2019-05-23 | 0.1 | 11.5024 | 4.601 | Accept | 0.1 | 11.5024 | 4.601 | H3 | 3 | Worsening | 0.6 | 91 | 122 | 155 | 122.3333 | 0.6 | 91 | 122 | 155 | 122.3333 | 0 | 0 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 0.1 | 12.7232 | 1.2723 | Reduce | 0.1 | 12.7232 | 1.2723 | H3 | 3 | Stable | 0.7 | 114 | 132 | 159 | 133.5 | 0.3 | 20 | 50 | 61 | 46.8333 | 0 | 0 | 1 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Interface implementation | Person_496 | 2018-05-23 | 2018-07-21 | 0.5 | 1.2677 | 0.12677 | Accept | 0.25 | 1.2677 | 0.12677 | H2 | 4 | Stable | 0.7 | 116 | 122 | 151 | 125.8333 | 0.7 | 116 | 122 | 151 | 125.8333 | 0 | 50 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-21 01:00 | 2023-12-22 01:00 | 0.4 | 30.1969 | 12.0788 | Reduce | 0.25 | 30.1969 | 7.5492 | H2 | 4 | Stable | 0.5 | 99 | 127 | 152 | 126.5 | 0.1 | 35 | 52 | 73 | 52.6667 | 0 | 37.5 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | In-house development of sub-system estimate is low | Person_594 | 2016-03-23 | 2018-03-22 | 0.5 | 6.5118 | 3.2559 | Reduce | 0.2 | 1.506 | 0.30121 | H3 | 3 | Stable | 0.7 | 101 | 128 | 154 | 127.8333 | 0.2 | 10 | 42 | 68 | 41 | 76.8722 | 60 | 0 | 46.1233
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 0.25 | 0.63626 | 0.15906 | Reduce | 0.05 | 0.63626 | 0.031813 | H3 | 3 | Stable | 0.7 | 117 | 127 | 143 | 128 | 0.3 | 26 | 47 | 73 | 47.8333 | 0 | 80 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Component Shock test failure | Person_661 | 2016-09-08 01:00 | 2019-11-15 01:00 | 0.4 | 0.8467 | 0.33868 | Reduce | 0.2 | 0.8467 | 0.16934 | H3 | 3 | Stable | 0.6 | 80 | 135 | 149 | 128.1667 | 0.4 | 23 | 41 | 64 | 41.8333 | 0 | 50 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-01-12 01:00 | 0.8 | 18.0459 | 14.4367 | Reduce | 0.2 | 3.0076 | 0.60153 | H3 | 3 | Stable | 0.6 | 119 | 136 | 155 | 136.3333 | 0.3 | 24 | 56 | 75 | 53.8333 | 83.3335 | 75 | 1 | 52.2501
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 | 0.05 | 2.4509 | 0.73527 | Accept | 0.03 | 2.4509 | 0.73527 | H2 | 4 | Stable | 0.6 | 98 | 140 | 155 | 135.5 | 0.6 | 98 | 140 | 155 | 135.5 | 0 | 40 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 0.4 | 5.1004 | 2.0402 | Reduce | 0.2 | 2.5506 | 0.51013 | H3 | 3 | Stable | 0.9 | 100 | 123 | 156 | 124.6667 | 0.1 | 30 | 47 | 68 | 47.6667 | 49.9917 | 50 | 0 | 29.995
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-21 01:00 | 2018-04-22 | 0.5 | 28.0275 | 14.0137 | Reduce | 0.1 | 28.0275 | 2.8027 | H3 | 3 | Stable | 0.5 | 103 | 130 | 145 | 128 | 0.3 | 26 | 43 | 79 | 46.1667 | 0 | 80 | 1 | 2.4
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2018-04-22 | 0.8 | 2.216 | 0.2216 | Accept | 0.6 | 2.216 | 0.2216 | H1 | 5 | Stable | 0.9 | 120 | 133 | 144 | 132.6667 | 0.9 | 120 | 133 | 144 | 132.6667 | 0 | 25 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 | 2018-05-22 | 0.1 | 5.0032 | 3.5023 | Accept | 0.05 | 5.0032 | 3.5023 | H2 | 4 | Stable | 0.8 | 103 | 140 | 149 | 135.3333 | 0.8 | 103 | 140 | 149 | 135.3333 | 0 | 50 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2018-05-21 | 0.2 | 18.4072 | 5.5222 | Accept | 0.2 | 18.4072 | 5.5222 | H3 | 3 | Worsening | 0.8 | 111 | 130 | 148 | 129.8333 | 0.8 | 111 | 130 | 148 | 129.8333 | 0 | 0 | 1 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2018-04-22 | 0.3 | 3.4651 | 1.0395 | Accept | 0.2 | 3.4651 | 1.0395 | H3 | 3 | Stable | 0.5 | 116 | 121 | 153 | 125.5 | 0.5 | 116 | 121 | 153 | 125.5 | 0 | 33.3333 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | EMC non compliance | Person_047 | 2016-06-23 | 2019-12-27 01:00 | 0.7 | 3.935 | 2.7545 | Reduce | 0.5 | 3.935 | 1.9675 | H2 | 4 | Stable | 0.9 | 109 | 135 | 156 | 134.1667 | 0.4 | 4 | 45 | 65 | 41.5 | 0 | 28.5714 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SubSystem System Design | Person_038 | 2017-10-01 01:00 | 2019-11-20 01:00 | 0.2 | 1.5213 | 0.30425 | Reduce | 0.1 | 1.5213 | 0.15213 | H3 | 3 | Stable | 0.5 | 97 | 127 | 158 | 127.1667 | 0.3 | 1 | 41 | 67 | 38.6667 | 0 | 50 | 1 | 1.5
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-085 | Project_043_Risk-085 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Failure of a product pre delivery | Person_359 | 2017-04-19 | 2018-04-21 | 0.25 | 67.8016 | 27.1206 | Accept | 0.25 | 67.8016 | 27.1206 | H2 | 4 | Improving | 0.5 | 92 | 127 | 159 | 126.5 | 0.5 | 92 | 127 | 159 | 126.5 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--27 | Project_021_Risk--27 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PR rectification | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 0.1 | 65.469 | 26.1876 | Accept | 0.1 | 65.469 | 26.1876 | H2 | 4 | Stable | 0.9 | 112 | 136 | 145 | 133.5 | 0.9 | 112 | 136 | 145 | 133.5 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--26 | Project_021_Risk--26 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional design effort required to satisfy SME feedback/input | Person_615 | 2018-01-21 01:00 | 2018-05-21 | 0.2 | 7.7077 | 1.5415 | Accept | 0.2 | 7.7077 | 1.5415 | H2 | 4 | Improving | 0.6 | 105 | 129 | 141 | 127 | 0.6 | 105 | 129 | 141 | 127 | 0 | 0 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--35 | Project_021_Risk--35 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Delay to sub-system releases due to supply chain dependencies | Person_615 | 2018-01-21 01:00 | 2018-03-22 | 0.4 | 25.1514 | 12.5757 | Accept | 0.4 | 25.1514 | 12.5757 | H2 | 4 | Stable | 0.6 | 99 | 133 | 160 | 131.8333 | 0.6 | 99 | 133 | 160 | 131.8333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-06-06 | 0.4 | 1.0142 | 0.40567 | Reduce | 0.1 | 1.0142 | 0.10142 | H3 | 3 | Stable | 0.9 | 114 | 137 | 158 | 136.6667 | 0.1 | 29 | 44 | 68 | 45.5 | 0 | 75 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | 9. Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 0.8 | 19.1678 | 15.3343 | Reduce | 0.2 | 2.8752 | 0.57503 | H3 | 3 | Stable | 0.7 | 104 | 127 | 153 | 127.5 | 0.4 | 36 | 40 | 74 | 45 | 85 | 75 | 0 | 51
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--34 | Project_021_Risk--34 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Delay due to poor weather | Person_615 | 2018-03-23 | 2018-06-22 | 0.5 | 2.0043 | 1.0022 | Accept | 0.5 | 2.0043 | 1.0022 | H2 | 4 | Stable | 0.9 | 90 | 139 | 158 | 134 | 0.9 | 90 | 139 | 158 | 134 | 0 | 0 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-06 01:00 | 2019-09-13 01:00 | 0.8 | 8.0322 | 6.4258 | Reduce | 0.5 | 4.006 | 2.003 | H2 | 4 | Stable | 0.8 | 96 | 134 | 146 | 129.6667 | 0.3 | 21 | 41 | 76 | 43.5 | 50.1263 | 37.5 | 0 | 30.0758
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK002 | Project_065_RISK002 | Opportunitity | Project Contingency | Open | H1 | 5 | 12. Acquisition and offsets | New supplier for enclosure | Person_598 | 2015-01-07 01:00 | 2017-10-19 01:00 | 0.05 | 9.6346 | 0.48173 | Exploit | 0.7 | 9.6346 | 6.7442 | H1 | 5 | Stable | [10 empty] | 0 | -1300 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK011 | Project_041_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier Development support | Person_693 | 2018-01-25 01:00 | 2018-04-06 | 0.3 | 1.7748 | 0.4437 | Accept | 0.3 | 1.7748 | 0.4437 | H2 | 4 | Stable | 0.6 | 90 | 125 | 144 | 122.3333 | 0.6 | 90 | 125 | 144 | 122.3333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier Selection Process | Person_379 | 2017-10-19 01:00 | 2019-04-23 | 0.4 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 94 | 122 | 148 | 121.6667 | 0.4 | 13 | 41 | 78 | 42.5 |  | 25 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Colour Representation in Video Image Distortion | Person_305 | 2017-09-22 01:00 | 2020-03-21 | 0.5 | 5.5323 | 2.7662 | Reduce | 0.1 | 5.5323 | 0.55323 | H3 | 3 | Stable | 0.8 | 109 | 130 | 152 | 130.1667 | 0.3 | 9 | 56 | 74 | 51.1667 | 0 | 80 | 1 | 2.4
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-21 01:00 | 0.8 | 35.2369 | 28.1895 | Reduce | 0.3 | 18.4979 | 5.5494 | H2 | 4 | Stable | 0.8 | 82 | 126 | 160 | 124.3333 | 0.1 | 29 | 46 | 65 | 46.3333 | 47.5042 | 62.5 | 0 | 28.5025
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 4 | 9. Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-21 01:00 | 0.7 | 20.6835 | 14.4785 | Reduce | 0.3 | 20.6835 | 6.2051 | H2 | 4 | Stable | 0.7 | 106 | 130 | 157 | 130.5 | 0.2 | 30 | 48 | 65 | 47.8333 | 0 | 57.1429 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 4 | 8. System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 0.6 | 5.2585 | 3.1551 | Reduce | 0.15 | 5.2585 | 0.78877 | H2 | 4 | Stable | 0.6 | 102 | 133 | 146 | 130 | 0.2 | 39 | 48 | 61 | 48.6667 | 0 | 75 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-04-21 | 0.3 | 2.723 | 0.81691 | Reduce | 0.1 | 2.723 | 0.2723 | H3 | 3 | Improving | 0.6 | 106 | 130 | 148 | 129 | 0.2 | 4 | 49 | 74 | 45.6667 | 0 | 66.6667 | 1 | 2
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 0.2 | 4.8444 | 0.96888 | Reduce | 0.2 | 4.8444 | 0.96888 | H3 | 3 | Stable | 0.9 | 115 | 131 | 154 | 132.1667 | 0.3 | 13 | 58 | 65 | 51.6667 | 0 | 0 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System Performance | Person_305 | 2016-09-08 01:00 | 2020-09-21 01:00 | 0.15 | 5.8725 | 0.88088 | Reduce | 0.05 | 5.8725 | 0.29363 | H2 | 4 | Stable | 0.9 | 118 | 137 | 152 | 136.3333 | 0.1 | 5 | 53 | 65 | 47 | 0 | 66.6667 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 0.3 | 4.8596 | 1.4579 | Accept | 0.3 | 4.8596 | 1.4579 | H3 | 3 | Stable | 0.6 | 86 | 138 | 156 | 132.3333 | 0.6 | 86 | 138 | 156 | 132.3333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_038 | 2020-05-23 | 2023-10-26 01:00 | 0.2 | 7.4599 | 1.492 | Reduce | 0.05 | 7.4599 | 0.37299 | H2 | 4 | Stable | 0.8 | 102 | 124 | 158 | 126 | 0.2 | 39 | 55 | 76 | 55.8333 | 0 | 75 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-29 01:00 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.5 | 89 | 136 | 154 | 131.1667 | 0.2 | 27 | 57 | 73 | 54.6667 | 60.3671 | 58.3333 | 0 | 36.2202
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-20 01:00 | 0.4 | 2.8643 | 1.1457 | Reduce | 0.1 | 2.8643 | 0.28643 | H3 | 3 | Stable | 0.8 | 107 | 134 | 147 | 131.6667 | 0.4 | 6 | 45 | 69 | 42.5 | 0.0015933 | 75 | 1 | 2.251
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power Supply - Motor Controller Interface | Person_047 | 2016-05-23 | 2018-04-21 | 0.5 | 25.3543 | 12.6771 | Reduce | 0.2 | 25.3543 | 5.0709 | H3 | 3 | Stable | 0.5 | 82 | 124 | 147 | 120.8333 | 0.4 | 17 | 41 | 64 | 40.8333 | 0 | 60 | 1 | 1.8
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-1 | Project_067_Risk-1 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Schedule Overrun | Person_002 | 2018-02-20 01:00 | 2019-10-20 01:00 | 0.7 | 0 | 0 | Reduce | 0.7 | 0 | 0 | H1 | 5 | Stable | 0.8 | 92 | 138 | 157 | 133.5 | 0.1 | 27 | 55 | 75 | 53.6667 |  | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-2 | Project_067_Risk-2 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System Performance | Person_765 | 2018-02-20 01:00 | 2019-10-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.8 | 120 | 126 | 152 | 129.3333 | 0.3 | 29 | 48 | 70 | 48.5 |  | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-5 | Project_067_Risk-5 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System performance levels | Person_327 | 2018-02-20 01:00 | 2019-10-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.5 | 114 | 133 | 143 | 131.5 | 0.1 | 6 | 52 | 79 | 48.8333 |  | 0 | 0
2018-01-21 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-6 | Project_067_Risk-6 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | System Resources | Person_002 | 2018-03-02 01:00 | 2019-10-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 100 | 125 | 146 | 124.3333 | 0.4 | 4 | 54 | 71 | 48.5 |  | 0 | 0
2018-01-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-010 | Project_052_Risk-010 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Potential update of software / hardware required during the 3 year support period (RESOURCE) | Person_376 | 2017-08-19 | 2018-02-19 | 0.25 | 3.1214 | 0.78035 | Transfer | 0.25 | 3.1214 | 0.78035 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.8 | 107 | 130 | 151 | 129.6667 | 0.4 | 26 | 51 | 70 | 50 | 25.8065 | 20 | 0 | 15.4839
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-23 | 2024-05-22 | 0.1 | 0.93298 | 0.13995 | Accept | 0.1 | 0.93298 | 0.13995 | H3 | 3 | Improving | 0.9 | 92 | 121 | 152 | 121.3333 | 0.9 | 92 | 121 | 152 | 121.3333 | 0 | 0 | 1 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK024 | Project_063_RISK024 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Procurement/ Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 0.8 | 0 | 0 | -- | 0.8 | 0 | 0 | H1 | 5 | Worsening | [11 empty] | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK022 | Project_063_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Equipment | Person_104 | 2018-01-14 01:00 | 2019-08-20 | 0.15 | 0.45604 | 0.068405 | -- | 0.15 | 0.45604 | 0.068405 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK021 | Project_063_RISK021 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Late Delivery | Person_261 | 2018-01-14 01:00 | 2018-11-20 01:00 | 0.7 | 10.3688 | 7.2582 | Reduce | 0.7 | 10.3688 | 7.2582 | H1 | 5 | Stable | 0.6 | 93 | 121 | 143 | 120 | 0.3 | 11 | 51 | 60 | 45.8333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK003 | Project_060_RISK003 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Misalignment of Critical Resource | Person_312 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.7 | 11.7303 | 8.2112 | Reduce | 0.5 | 11.7303 | 5.8651 | H1 | 5 | Improving | 0.6 | 80 | 136 | 142 | 127.6667 | 0.1 | 6 | 56 | 65 | 49.1667 | 0 | 28.5714 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK004 | Project_063_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 2.861 | 0.57221 | Reduce | 0.15 | 2.861 | 0.42915 | H3 | 3 | Stable | 0.9 | 117 | 139 | 145 | 136.3333 | 0.3 | 17 | 45 | 65 | 43.6667 | 0 | 25 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK004 | Project_060_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Cross-functional Estimates | Person_729 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.7 | 2.8845 | 2.0191 | Reduce | 0.5 | 2.8845 | 1.4422 | H2 | 4 | Stable | 0.8 | 109 | 139 | 160 | 137.5 | 0.1 | 38 | 41 | 64 | 44.3333 | 0 | 28.5714 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK006 | Project_060_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Secure material Handling | Person_033 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.5 | 1.1538 | 0.5769 | Reduce | 0.2 | 1.1538 | 0.23076 | H3 | 3 | Stable | 0.8 | 119 | 127 | 144 | 128.5 | 0.2 | 26 | 40 | 79 | 44.1667 | 0 | 60 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK014 | Project_063_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 0.1 | 8.3527 | 0.83527 | Avoid | 0.05 | 7.0086 | 0.35043 | H3 | 3 | Worsening | [10 empty] | 16.092 | 50 | 0 | 9.6552
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK001 | Project_060_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Procurement Prices | Person_033 | 2017-11-02 01:00 | 2018-08-20 | 0.7 | 1.4422 | 1.0096 | Transfer | 0.7 | 1.4422 | 1.0096 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK017 | Project_063_RISK017 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Increased build rate | Person_683 | 2017-11-12 01:00 | 2019-08-21 01:00 | 0.5 | 21.6065 | 10.8033 | -- | 0.5 | 21.6065 | 10.8033 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK005 | Project_063_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 1.214 | 0.72839 | -- | 0.5 | 1.214 | 0.60699 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-02-20 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK044 | Project_053_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Product Hardening | Person_719 | 2018-03-23 | 2019-01-20 01:00 | 0.3 | 7.9015 | 2.3705 | Avoid | 0.3 | 7.9015 | 2.3705 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK016 | Project_063_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.2 | 0.63077 | 0.12615 | -- | 0.2 | 0.63077 | 0.12615 | H3 | 3 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK002 | Project_063_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2020-05-22 | 0.15 | 8.6407 | 1.2961 | Avoid | 0.15 | 8.6407 | 1.2961 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-02-20 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK015 | Project_053_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Equipment export licences | Person_252 | 2018-06-23 | 2019-07-22 | 0.3 | 2.586 | 0.77579 | Avoid | 0.1 | 2.586 | 0.2586 | H3 | 3 | Improving | [10 empty] | 0 | 66.6667 | 1 | 2
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK012 | Project_063_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Customer require additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 6.0485 | 1.2097 | Avoid | 0.2 | 6.0485 | 1.2097 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-02-20 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK006 | Project_053_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional UK integration of the System product | Person_719 | 2018-10-22 01:00 | 2019-01-21 01:00 | 0.2 | 6.3212 | 1.2642 | Avoid | 0.2 | 6.3212 | 1.2642 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 1 | 0
2018-02-20 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK005 | Project_053_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier Deiivery Schedule | Person_252 | 2018-01-21 01:00 | 2018-11-20 01:00 | 0.5 | 5.3299 | 2.665 | Reduce | 0.25 | 5.3299 | 1.3325 | H2 | 4 | Stable | 0.6 | 117 | 137 | 150 | 135.8333 | 0.4 | 21 | 59 | 60 | 52.8333 | 0 | 50 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK018 | Project_063_RISK018 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Line Closure | Person_683 | 2019-08-21 01:00 | 2019-11-20 01:00 | 0.5 | 1.9058 | 0.95288 | -- | 0.5 | 4.3203 | 2.1602 | H2 | 4 | Improving | [10 empty] | -126.7001 | 0 | 0 | -76.0201
2018-02-20 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK010 | Project_053_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Immaturity of the core product | Person_719 | 2018-08-22 01:00 | 2018-11-20 01:00 | 0.5 | 6.4649 | 3.2325 | Avoid | 0.2 | 6.4649 | 1.293 | H2 | 4 | Stable | [10 empty] | 0 | 60 | 0 | 0
2018-02-20 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK007 | Project_053_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Resources Uavailable | Person_252 | 2017-11-20 01:00 | 2019-08-21 01:00 | 0.5 | 10.3438 | 5.1719 | Reduce | 0.2 | 7.9015 | 1.5803 | H3 | 3 | Stable | 0.6 | 106 | 122 | 143 | 122.8333 | 0.1 | 8 | 50 | 63 | 45.1667 | 23.6111 | 60 | 1 | 15.9666
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Volume of production tools and Jigs | Person_279 | 2016-11-23 01:00 | 2021-11-23 01:00 | 0.35 | 6.4382 | 2.2534 | Reduce | 0.15 | 6.4382 | 0.96573 | H2 | 4 | Stable | 0.9 | 109 | 130 | 151 | 130 | 0.4 | 1 | 47 | 60 | 41.5 | 0 | 57.1429 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software issue input | Person_279 | 2016-11-23 01:00 | 2023-02-20 01:00 | 0.4 | 49.4398 | 19.7759 | Reduce | 0.2 | 49.4398 | 9.888 | H2 | 4 | Stable | 0.6 | 111 | 138 | 157 | 136.6667 | 0.2 | 19 | 46 | 66 | 44.8333 | 0 | 50 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-115 | Project_011_Risk-115 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | SMEs are unavailable to support project activites | Person_230 | 2016-07-21 | 2018-08-21 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-058 | Project_011_Risk-058 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Programme delays | Person_147 | 2013-11-20 01:00 | 2018-11-20 01:00 | 0.25 | 1.5013 | 0.37532 | Reduce | 0.25 | 1.5013 | 0.37532 | H2 | 4 | Stable | 0.7 | 111 | 123 | 148 | 125.1667 | 0.4 | 18 | 41 | 65 | 41.1667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-131 | Project_011_Risk-131 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Support team have not covered all obligations in support contract | Person_147 | 2016-05-24 | 2018-08-17 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-137 | Project_011_Risk-137 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Subsystem will not match Fidelity of Customer - does not accept | Person_147 | 2018-02-16 01:00 | 2018-09-20 01:00 | 0.4 | 0.11876 | 0.047505 | Avoid | 0.2 | 0.11876 | 0.023752 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Gold Rig is unavailable when required | Person_431 | 2016-07-21 | 2018-08-21 | 0.15 | 0.58983 | 0.088474 | -- | 0.15 | 0.58983 | 0.088474 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2018-04-22 | 2018-09-20 01:00 | 0.2 | 0.62279 | 0.12456 | Avoid | 0.2 | 0.62279 | 0.12456 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-09-20 01:00 | 0.2 | 1.8854 | 0.37708 | Reduce | 0.2 | 1.8854 | 0.37708 | H2 | 4 | Stable | 0.8 | 80 | 125 | 156 | 122.6667 | 0.4 | 34 | 52 | 65 | 51.1667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2018-06-23 | 2018-10-21 01:00 | 0.4 | 1.4138 | 0.56551 | Reduce | 0.4 | 1.4138 | 0.56551 | H2 | 4 | Stable | 0.5 | 115 | 134 | 156 | 134.5 | 0.1 | 22 | 49 | 61 | 46.5 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-126 | Project_011_Risk-126 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Increase in regression testing | Person_182 | 2017-11-20 01:00 | 2018-05-21 | 0.25 | 0.12558 | 0.031395 | -- | 0.25 | 0.12558 | 0.031395 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-10-19 01:00 | 2018-08-21 | 0.2 | 0.081826 | 0.016365 | Reduce | 0.2 | 0.081826 | 0.016365 | H2 | 4 | Stable | 0.9 | 101 | 136 | 142 | 131.1667 | 0.4 | 13 | 57 | 65 | 51 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Pick up and Drop off of Software Resource | Person_431 | 2017-12-19 01:00 | 2018-07-20 | 0.6 | 0.36106 | 0.21663 | Avoid | 0.6 | 0.36106 | 0.21663 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-09-20 01:00 | 0.4 | 0.19206 | 0.076826 | -- | 0.4 | 0.19206 | 0.076826 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-08-22 01:00 | 2018-11-20 01:00 | 0.4 | 0.58017 | 0.23207 | Avoid | 0.4 | 0.58017 | 0.23207 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 0.4 | 0.11365 | 0.045459 | -- | 0.4 | 0.11365 | 0.045459 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-11-20 01:00 | 0.55 | 0.32389 | 0.17814 | Reduce | 0.55 | 0.32389 | 0.17814 | H1 | 5 | Stable | 0.8 | 108 | 140 | 152 | 136.6667 | 0.4 | 2 | 48 | 74 | 44.6667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_182 | 2018-06-23 | 2018-10-21 01:00 | 0.4 | 0.19206 | 0.076826 | -- | 0.4 | 0.19206 | 0.076826 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_431 | 2017-05-24 | 2018-08-19 | 0.3 | 0.11933 | 0.035799 | -- | 0.3 | 0.022161 | 0.0066484 | H3 | 3 | Stable | [10 empty] | 81.4286 | 0 | 0 | 48.8571
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-117 | Project_011_Risk-117 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Avaliability for testing/reviews | Person_147 | 2018-04-06 | 2018-09-20 01:00 | 0.35 | 0 | 0 | Avoid | 0.35 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-01-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-013 | Project_052_Risk-013 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional material and effort required to support the delta equipment | Person_376 | 2017-08-19 | 2018-03-22 | 0.3 | 3.6256 | 1.4502 | Accept | 0.3 | 3.6256 | 1.4502 | H3 | 3 | Stable | 0.5 | 86 | 127 | 154 | 124.6667 | 0.5 | 86 | 127 | 154 | 124.6667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-128 | Project_011_Risk-128 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Incorrect Maps used during Qualification | Person_147 | 2017-04-22 | 2018-04-22 | 0.5 | 0.05688 | 0.02844 | Transfer | 0.5 | 0.05688 | 0.02844 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-129 | Project_011_Risk-129 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Signature of Work Authorisation documents | Person_422 | 2017-05-24 | 2018-04-21 | 0.4 | 0.12643 | 0.050573 | -- | 0.4 | 0.12643 | 0.050573 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-01-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-004 | Project_052_Risk-004 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | IOC Risk for Phase 1b | Person_488 | 2017-08-19 | 2018-03-22 | 0.1 | 6.0991 | 4.0864 | Accept | 0.1 | 6.0991 | 4.0864 | H3 | 3 | Stable | 0.7 | 97 | 122 | 159 | 124 | 0.7 | 97 | 122 | 159 | 124 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-130 | Project_011_Risk-130 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer does not accept Voice Pronounciation | Person_187 | 2017-05-24 | 2018-06-21 | 0.4 | 0.090918 | 0.036367 | Avoid | 0.4 | 0.090918 | 0.036367 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | FOC Acceptance | Person_499 | 2018-05-23 | 2018-07-21 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.15 | 8.471 | 1.2706 | H3 | 3 | Stable | 0.8 | 93 | 125 | 144 | 122.8333 | 0.1 | 4 | 57 | 63 | 49.1667 | -99.9999 | 57.1429 | 1 | -58.2857
2018-01-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-001 | Project_052_Risk-001 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Greater modification than expected for system uplift | Person_376 | 2017-08-19 | 2018-03-22 | 0.1 | 8.8098 | 3.0834 | Accept | 0.1 | 8.8098 | 1.762 | H3 | 3 | Stable | 0.7 | 109 | 136 | 159 | 135.3333 | 0.7 | 109 | 136 | 159 | 135.3333 | 0 | 0 | 0 | 0
2018-01-21 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-009 | Project_052_Risk-009 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | System acceptance not costed in line with Customer expectations | Person_651 | 2017-08-19 | 2018-03-22 | 0.1 | 5.2705 | 1.5811 | Accept | 0.1 | 4.3921 | 0.87842 | H3 | 3 | Stable | 0.5 | 98 | 138 | 148 | 133 | 0.5 | 98 | 138 | 148 | 133 | 16.6667 | 0 | 0 | 10
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 05:00 | 2019-08-20 05:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 05:00 | 2019-08-20 05:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 05:00 | 2019-08-20 05:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 05:00 | 2019-08-20 05:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 05:00 | 2019-08-20 05:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK008 | Project_044_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Skills | Person_505 | 2017-10-21 01:00 | 2018-10-22 01:00 | 0.3 | 1.5695 | 0.47085 | Reduce | 0.3 | 1.4488 | 0.43463 | H2 | 4 | Stable | 0.6 | 94 | 123 | 150 | 122.6667 | 0.1 | 35 | 42 | 61 | 44 | 7.6924 | 0 | 0 | 4.6155
2018-02-20 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK003 | Project_044_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Mono vs stereo Component | Person_358 | 2016-03-23 | 2018-10-22 01:00 | 0.7 | 14.4876 | 10.1413 | Reduce | 0.5 | 14.4876 | 7.2438 | H2 | 4 | Stable | 0.6 | 92 | 129 | 159 | 127.8333 | 0.2 | 29 | 47 | 63 | 46.6667 | 0 | 28.5714 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK044 | Project_042_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2018-02-20 | 2018-12-21 | 0.32 | 6.5759 | 2.1043 | Reduce | 0.17 | 6.5759 | 1.1179 | H2 | 4 | Stable | 0.6 | 81 | 129 | 150 | 124.5 | 0.1 | 21 | 50 | 66 | 47.8333 | 0 | 46.875 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK024 | Project_042_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2019-09-21 | 2020-09-19 | 0.33 | 9.3941 | 3.1001 | Reduce | 0.15 | 7.5153 | 1.1273 | H2 | 4 | Stable | 0.5 | 96 | 138 | 150 | 133 | 0.4 | 26 | 59 | 74 | 56 | 20 | 54.5455 | 0 | 12
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK045 | Project_042_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2019-01-22 | 2019-05-23 | 0.25 | 3.908 | 0.97699 | Reduce | 0.25 | 3.908 | 0.97699 | H2 | 4 | Stable | 0.6 | 102 | 125 | 152 | 125.6667 | 0.3 | 13 | 40 | 73 | 41 | 0 | 0 | 0 | 0
2018-02-20 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK047 | Project_053_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Lab Availability | Person_252 | 2017-10-21 01:00 | 2020-01-22 01:00 | 0.5 | 1.8788 | 0.37576 | Accept | 0.2 | 1.5031 | 0.22546 | H3 | 3 | Improving | 0.5 | 98 | 131 | 150 | 128.6667 | 0.5 | 98 | 131 | 150 | 128.6667 | 20 | 60 | 1 | 13.8
2018-02-20 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK043 | Project_053_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Change in REACH/RoSH Legislation | Person_302 | 2017-11-20 01:00 | 2018-09-20 01:00 | 0.1 | 1.0334 | 0.20667 | Accept | 0.1 | 0.80789 | 0.12118 | H2 | 4 | Stable | 0.6 | 89 | 132 | 160 | 129.5 | 0.6 | 89 | 132 | 160 | 129.5 | 21.8182 | 0 | 0 | 13.0909
2018-02-20 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK046 | Project_053_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Un-Planned Production Activities | Person_252 | 2019-07-22 | 2020-01-22 01:00 | 0.5 | 1.8788 | 0.18788 | Accept | 0.2 | 1.8225 | 0.12757 | H3 | 3 | Stable | 0.9 | 108 | 126 | 153 | 127.5 | 0.9 | 108 | 126 | 153 | 127.5 | 3 | 60 | 1 | 3.6
2018-02-20 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK021 | Project_053_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Product documentation | Person_719 | 2018-08-22 01:00 | 2019-07-26 | 0.35 | 1.8788 | 0.18788 | Accept | 0.35 | 1.5031 | 0.12024 | H2 | 4 | Stable | 0.8 | 98 | 130 | 148 | 127.6667 | 0.8 | 98 | 130 | 148 | 127.6667 | 20 | 0 | 0 | 12
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unreliability of Hardware | Person_431 | 2016-06-23 | 2018-08-21 | 0.2 | 1.8788 | 0.18788 | Accept | 0.2 | 1.5031 | 0.12024 | H2 | 4 | Stable | 0.5 | 85 | 122 | 152 | 120.8333 | 0.5 | 85 | 122 | 152 | 120.8333 | 20 | 0 | 0 | 12
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_147 | 2016-04-21 | 2018-08-21 | 0.25 | 0.79775 | 0.039887 | Accept | 0.25 | 0.79775 | 0.039887 | H3 | 3 | Stable | 0.9 | 85 | 135 | 155 | 130 | 0.9 | 85 | 135 | 155 | 130 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Interface implementation | Person_496 | 2018-05-23 | 2018-07-21 | 0.5 | 10.3335 | 1.0334 | Accept | 0.25 | 10.3335 | 1.0334 | H2 | 4 | Stable | 0.9 | 112 | 140 | 146 | 136.3333 | 0.9 | 112 | 140 | 146 | 136.3333 | 0 | 50 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of the platforms for modification | Person_496 | 2014-01-21 01:00 | 2019-04-10 | 0.67 | 3.7576 | 0.18788 | Accept | 0.67 | 3.7576 | 0.56365 | H2 | 4 | Stable | 0.6 | 117 | 130 | 144 | 130.1667 | 0.6 | 117 | 130 | 144 | 130.1667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_523 | 2018-05-23 | 2018-07-21 | 0.35 | 1.8788 | 0.46971 | Accept | 0.2 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.7 | 101 | 131 | 156 | 130.1667 | 0.7 | 101 | 131 | 156 | 130.1667 | 20 | 42.8571 | 0 | 12
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK048 | Project_042_RISK048 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | On the Job Training. | Person_371 | 2018-03-02 | 2019-02-05 | 0.85 | 2.1043 | 1.7886 | Reduce | 0.5 | 2.1043 | 1.0521 | H1 | 5 | Stable | 0.7 | 108 | 129 | 145 | 128.1667 | 0.2 | 16 | 56 | 69 | 51.5 | 0 | 41.1765 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK049 | Project_042_RISK049 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Industry STTE Upkeep. | Person_371 | 2018-03-02 | 2019-02-05 | 0.85 | 1.3152 | 1.1179 | Reduce | 0.5 | 1.3152 | 0.65759 | H2 | 4 | Stable | 0.8 | 118 | 121 | 150 | 125.3333 | 0.3 | 22 | 49 | 61 | 46.5 | 0 | 41.1765 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK047 | Project_042_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables | Person_455 | 2020-11-20 | 2021-05-22 | 0.2 | 1.8788 | 0.46971 | Accept | 0.1 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.6 | 111 | 131 | 147 | 130.3333 | 0.6 | 111 | 131 | 147 | 130.3333 | 20 | 50 | 0 | 12
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK022 | Project_042_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2017-09-20 | 2018-09-20 | 0.2 | 2.2828 | 0.31959 | Accept | 0.18 | 2.2828 | 0.31959 | H2 | 4 | Stable | 0.9 | 114 | 128 | 142 | 128 | 0.9 | 114 | 128 | 142 | 128 | 0 | 10 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-20 22:00 | 2017-08-19 22:00 | 0.1 | 53.0293 | 5.3029 | Reduce | 0.1 | 53.0293 | 5.3029 | H3 | 3 | Stable | 0.5 | 111 | 130 | 144 | 129.1667 | 0.1 | 14 | 46 | 76 | 45.6667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK043 | Project_042_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st December | Person_455 | 2021-03-23 | 2021-05-22 | 0.1 | 0.20788 | 0.068599 | Accept | 0.08 | 31.0429 | 15.5215 | H3 | 3 | Stable | 0.5 | 117 | 128 | 160 | 131.5 | 0.5 | 117 | 128 | 160 | 131.5 | -14833.3191 | 20 | 1 | -8899.3915
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-20 22:00 | 2017-08-19 22:00 | 0.1 | 7.7469 | 0.77469 | Reduce | 0.1 | 7.7469 | 0.77469 | H3 | 3 | Stable | 0.7 | 81 | 133 | 160 | 128.8333 | 0.4 | 30 | 42 | 75 | 45.5 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK046 | Project_042_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables - June | Person_455 | 2018-11-21 | 2020-11-19 | 0.2 | 11.3437 | 0.56718 | Accept | 0.1 | 11.3437 | 0.56718 | H2 | 4 | Stable | 0.8 | 95 | 121 | 160 | 123.1667 | 0.8 | 95 | 121 | 160 | 123.1667 | 0 | 50 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK023 | Project_042_RISK023 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2018-09-21 | 2019-09-20 | 0.2 | 1.1744 | 0.46977 | Accept | 0.1 | 1.1744 | 0.46977 | H2 | 4 | Stable | 0.5 | 106 | 125 | 156 | 127 | 0.5 | 106 | 125 | 156 | 127 | 0 | 50 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK029 | Project_042_RISK029 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st October to 31st December | Person_455 | 2020-11-20 | 2021-05-22 | 0.25 | 1.1744 | 0.23489 | Accept | 0.1 | 1.1744 | 0.23489 | H2 | 4 | Stable | 0.8 | 109 | 134 | 155 | 133.3333 | 0.8 | 109 | 134 | 155 | 133.3333 | 0 | 60 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK036 | Project_042_RISK036 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 2 | Person_455 | 2019-05-24 | 2020-05-22 | 0.25 | 2.9361 | 0.58721 | Accept | 0.2 | 2.9361 | 0.58721 | H2 | 4 | Stable | 0.9 | 110 | 131 | 141 | 129.1667 | 0.9 | 110 | 131 | 141 | 129.1667 | 0 | 20 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer find issues with delivered parts or documentation | Person_294 | 2017-05-23 | 2019-08-20 | 0.4 | 9.0039 | 3.6016 | Reduce | 0.25 | 9.0039 | 2.251 | H2 | 4 | Improving | 0.8 | 117 | 139 | 160 | 138.8333 | 0.4 | 33 | 46 | 74 | 48.5 | 0 | 37.5 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK002 | Project_058_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence of key parts | Person_236 | 2017-05-23 | 2018-05-22 | 0.5 | 6.7334 | 3.3667 | Reduce | 0.25 | 6.7334 | 1.6833 | H2 | 4 | Stable | 0.5 | 83 | 131 | 148 | 125.8333 | 0.1 | 17 | 45 | 79 | 46 | 0 | 50 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK052 | Project_058_RISK052 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | sub-System Cleanliness | Person_324 | 2017-05-23 | 2018-09-20 01:00 | 0.75 | 13.3102 | 9.9826 | Reduce | 0.2 | 13.3102 | 2.662 | H3 | 3 | Stable | 0.9 | 83 | 134 | 155 | 129 | 0.2 | 4 | 58 | 70 | 51 | 0 | 73.3333 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Open PR's | Person_319 | 2018-04-22 | 2018-11-20 01:00 | 0.5 | 7.6338 | 3.8169 | Reduce | 0.3 | 7.6338 | 2.2901 | H3 | 3 | Improving | 0.8 | 102 | 130 | 157 | 129.8333 | 0.1 | 28 | 58 | 62 | 53.6667 | 0 | 40 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK039 | Project_042_RISK039 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality Issues 16th August to 15th August | Person_540 | 2020-01-06 | 2021-01-04 | 0.1 | 3.1344 | 1.5672 | Accept | 0.08 | 3.1344 | 1.5672 | H2 | 4 | Stable | 0.5 | 84 | 139 | 157 | 132.8333 | 0.5 | 84 | 139 | 157 | 132.8333 | 0 | 20 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK033 | Project_042_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st April to 30 June | Person_455 | 2019-08-22 | 2019-11-20 | 0.2 | 7.3848 | 3.6924 | Accept | 0.15 | 7.3848 | 3.6924 | H2 | 4 | Stable | 0.6 | 119 | 126 | 148 | 128.5 | 0.6 | 119 | 126 | 148 | 128.5 | 0 | 25 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK035 | Project_042_RISK035 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st October to 31st December | Person_455 | 2021-02-20 | 2021-05-22 | 0.2 | 0.78901 | 0.3945 | Accept | 0.15 | 0.78901 | 0.3945 | H2 | 4 | Stable | 0.5 | 119 | 128 | 148 | 129.8333 | 0.5 | 119 | 128 | 148 | 129.8333 | 0 | 25 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK024 | Project_048_RISK024 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Procurement/ Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 0.8 | 0 | 0 | -- | 0.8 | 0 | 0 | H1 | 5 | Worsening | [11 empty] | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK017 | Project_048_RISK017 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Increased build rate | Person_683 | 2017-11-12 01:00 | 2019-08-21 01:00 | 0.5 | 7.7433 | 3.8716 | -- | 0.5 | 7.7433 | 3.8716 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK016 | Project_048_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.2 | 0.22605 | 0.045211 | -- | 0.2 | 0.22605 | 0.045211 | H3 | 3 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK018 | Project_048_RISK018 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Line Closure | Person_683 | 2019-08-21 01:00 | 2019-11-20 01:00 | 0.5 | 0.68298 | 0.34149 | -- | 0.5 | 1.5483 | 0.77415 | H2 | 4 | Improving | [10 empty] | -126.7001 | 0 | 0 | -76.0201
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK004 | Project_048_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 1.0253 | 0.20506 | Reduce | 0.15 | 1.0253 | 0.1538 | H3 | 3 | Stable | 0.5 | 108 | 124 | 156 | 126.6667 | 0.4 | 4 | 54 | 74 | 49 | 0 | 25 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK034 | Project_042_RISK034 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st July to 30 September | Person_455 | 2020-11-20 | 2021-02-19 | 0.2 | 0 | 0 | Accept | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.8 | 89 | 127 | 147 | 124 | 0.8 | 89 | 127 | 147 | 124 |  | 25 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK014 | Project_048_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 0.1 | 2.9934 | 0.29934 | Avoid | 0.05 | 2.5117 | 0.12558 | H3 | 3 | Worsening | [10 empty] | 16.092 | 50 | 0 | 9.6552
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK005 | Project_048_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 0.43506 | 0.26104 | Avoid | 0.5 | 0.43506 | 0.21753 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK002 | Project_048_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2020-05-22 | 0.15 | 3.0966 | 0.46449 | Avoid | 0.15 | 3.0966 | 0.46449 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK012 | Project_048_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Customer require additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 2.1676 | 0.43353 | Avoid | 0.2 | 2.1676 | 0.43353 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK022 | Project_048_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Equipment | Person_104 | 2018-01-14 01:00 | 2019-08-20 | 0.15 | 0.16343 | 0.024515 | -- | 0.15 | 0.16343 | 0.024515 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK021 | Project_048_RISK021 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Late Delivery | Person_261 | 2018-01-14 01:00 | 2018-11-20 01:00 | 0.7 | 3.7159 | 2.6012 | Reduce | 0.7 | 3.7159 | 2.6012 | H1 | 5 | Stable | 0.5 | 90 | 137 | 154 | 132 | 0.3 | 30 | 40 | 65 | 42.5 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK040 | Project_042_RISK040 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st May to 30 Oct | Person_455 | 2019-09-21 | 2020-03-21 | 0.1 | 2.9272 | 1.4636 | Accept | 0.07 | 2.9272 | 1.4636 | H2 | 4 | Stable | 0.7 | 87 | 133 | 147 | 127.6667 | 0.7 | 87 | 133 | 147 | 127.6667 | 0 | 30 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK042 | Project_042_RISK042 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st February to 14th July | Person_455 | 2020-06-23 | 2020-12-03 | 0.1 | 1.6962 | 0.33923 | Accept | 0.08 | 1.6962 | 0.33923 | H2 | 4 | Stable | 0.7 | 110 | 136 | 145 | 133.1667 | 0.7 | 110 | 136 | 145 | 133.1667 | 0 | 20 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK041 | Project_042_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st Jan | Person_455 | 2020-03-23 | 2020-06-22 | 0.1 | 42.7783 | 32.0837 | Accept | 0.08 | 42.7783 | 32.0837 | H2 | 4 | Stable | 0.7 | 117 | 124 | 148 | 126.8333 | 0.7 | 117 | 124 | 148 | 126.8333 | 0 | 20 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Local customer Engineers in country | Person_455 | 2018-12-20 | 2021-05-22 | 0.05 | 8.2789 | 2.4837 | Accept | 0.05 | 8.2789 | 2.4837 | H2 | 4 | Stable | 0.6 | 84 | 130 | 144 | 124.6667 | 0.6 | 84 | 130 | 144 | 124.6667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK026 | Project_042_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st Jan to 31st March | Person_455 | 2020-05-23 | 2020-08-20 | 0.25 | 10.4822 | 2.6205 | Accept | 0.15 | 10.4822 | 2.6205 | H2 | 4 | Stable | 0.8 | 109 | 124 | 155 | 126.6667 | 0.8 | 109 | 124 | 155 | 126.6667 | 0 | 40 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK025 | Project_042_RISK025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to 31 Dec | Person_455 | 2020-09-20 | 2021-05-22 | 0.2 | 94.501 | 47.2505 | Accept | 0.15 | 94.501 | 47.2505 | H2 | 4 | Stable | 0.9 | 119 | 127 | 150 | 129.5 | 0.9 | 119 | 127 | 150 | 129.5 | 0 | 25 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK028 | Project_042_RISK028 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st July to 30th September | Person_455 | 2020-11-20 | 2021-02-19 | 0.25 | 31.4106 | 15.7053 | Accept | 0.15 | 31.4106 | 15.7053 | H2 | 4 | Stable | 0.9 | 84 | 130 | 155 | 126.5 | 0.9 | 84 | 130 | 155 | 126.5 | 0 | 40 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK027 | Project_042_RISK027 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st April to 30th June | Person_455 | 2020-08-21 | 2020-09-19 | 0.25 | 14.5313 | 2.9063 | Accept | 0.15 | 14.5313 | 2.9063 | H2 | 4 | Stable | 0.9 | 83 | 128 | 151 | 124.3333 | 0.9 | 83 | 128 | 151 | 124.3333 | 0 | 40 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.9 | 87 | 131 | 159 | 128.3333 | 0.2 | 22 | 55 | 74 | 52.6667 | 60.3671 | 58.3333 | 0 | 36.2202
2018-02-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK037 | Project_042_RISK037 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 1 | Person_455 | 2020-05-23 | 2021-05-22 | 0.14 | 1.9438 | 0.77753 | Accept | 0.14 | 1.9438 | 0.77753 | H2 | 4 | Stable | 0.5 | 100 | 137 | 148 | 132.6667 | 0.5 | 100 | 137 | 148 | 132.6667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-184 | Project_032_Risk-184 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Manufacture of new Sub-systems | Person_629 | 2016-04-08 | 2018-02-18 22:00 | 0.33 | 8.0289 | 1.6058 | Accept | 0.5 | 2.5354 | 0.50709 | H1 | 5 | Stable | 0.6 | 81 | 135 | 141 | 127 | 0.6 | 81 | 135 | 141 | 127 | 68.421 | -51.5152 | 0 | 41.0526
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-19 22:00 | 0.05 | 11.5024 | 4.601 | Accept | 0.05 | 11.5024 | 4.601 | H3 | 3 | Stable | 0.7 | 113 | 139 | 146 | 135.8333 | 0.7 | 113 | 139 | 146 | 135.8333 | 0 | 0 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-08 | 2020-09-21 | 0.1 | 12.7232 | 1.2723 | Reduce | 0.1 | 12.7232 | 1.2723 | H3 | 3 | Stable | 0.7 | 105 | 123 | 142 | 123.1667 | 0.3 | 7 | 49 | 63 | 44.3333 | 0 | 0 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-21 | 2023-12-22 | 0.4 | 30.1969 | 12.0788 | Reduce | 0.25 | 30.1969 | 7.5492 | H2 | 4 | Stable | 0.6 | 99 | 126 | 148 | 125.1667 | 0.2 | 14 | 47 | 67 | 44.8333 | 0 | 37.5 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | In-house development of sub-system estimate is low | Person_594 | 2016-03-23 | 2018-03-22 | 0.5 | 6.5118 | 3.2559 | Reduce | 0.2 | 1.506 | 0.30121 | H3 | 3 | Stable | 0.9 | 94 | 139 | 142 | 132 | 0.1 | 8 | 44 | 63 | 41.1667 | 76.8722 | 60 | 0 | 46.1233
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 0.25 | 0.63626 | 0.15906 | Reduce | 0.05 | 0.63626 | 0.031813 | H3 | 3 | Stable | 0.6 | 91 | 127 | 147 | 124.3333 | 0.4 | 38 | 56 | 67 | 54.8333 | 0 | 80 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Component Shock test failure | Person_661 | 2016-09-08 | 2019-11-15 | 0.4 | 0.8467 | 0.33868 | Reduce | 0.2 | 0.8467 | 0.16934 | H3 | 3 | Stable | 0.5 | 108 | 133 | 153 | 132.1667 | 0.4 | 25 | 57 | 66 | 53.1667 | 0 | 50 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-01-12 | 0.8 | 18.0459 | 14.4367 | Reduce | 0.2 | 3.0076 | 0.60153 | H3 | 3 | Stable | 0.9 | 109 | 129 | 156 | 130.1667 | 0.2 | 5 | 53 | 63 | 46.6667 | 83.3335 | 75 | 1 | 52.2501
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 0.4 | 5.1004 | 2.0402 | Reduce | 0.2 | 2.5506 | 0.51013 | H3 | 3 | Stable | 0.6 | 100 | 126 | 143 | 124.5 | 0.4 | 20 | 55 | 68 | 51.3333 | 49.9917 | 50 | 0 | 29.995
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-21 | 2018-04-22 | 0.5 | 28.0275 | 14.0137 | Reduce | 0.1 | 28.0275 | 2.8027 | H3 | 3 | Stable | 0.5 | 89 | 122 | 148 | 120.8333 | 0.3 | 17 | 42 | 78 | 43.8333 | 0 | 80 | 1 | 2.4
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-20 23:00 | 2020-08-19 23:00 | 0.5 | 2.216 | 0.2216 | Accept | 0.5 | 2.216 | 0.2216 | H2 | 4 | Stable | 0.9 | 95 | 132 | 149 | 128.6667 | 0.9 | 95 | 132 | 149 | 128.6667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 5.0032 | 3.5023 | Accept | 0.5 | 5.0032 | 3.5023 | H2 | 4 | Stable | 0.5 | 110 | 124 | 152 | 126.3333 | 0.5 | 110 | 124 | 152 | 126.3333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_009 | Project_051 | RISK001 | Project_051_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Generic Labour or Material Overspend | Person_577 | 2012-05-23 | 2021-05-22 | 0.5 | 18.4072 | 5.5222 | Accept | 0.5 | 18.4072 | 5.5222 | H3 | 3 | Stable | 0.9 | 89 | 140 | 145 | 132.3333 | 0.9 | 89 | 140 | 145 | 132.3333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | EMC non compliance | Person_047 | 2016-06-23 | 2019-12-27 | 0.7 | 3.935 | 2.7545 | Reduce | 0.5 | 3.935 | 1.9675 | H2 | 4 | Stable | 0.6 | 109 | 137 | 151 | 134.6667 | 0.3 | 30 | 54 | 62 | 51.3333 | 0 | 28.5714 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SubSystem System Design | Person_038 | 2017-10-01 | 2019-11-20 | 0.2 | 1.5213 | 0.30425 | Reduce | 0.1 | 1.5213 | 0.15213 | H3 | 3 | Stable | 0.9 | 83 | 134 | 145 | 127.3333 | 0.2 | 12 | 51 | 60 | 46 | 0 | 50 | 1 | 1.5
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-06-06 | 0.4 | 1.0142 | 0.40567 | Reduce | 0.1 | 1.0142 | 0.10142 | H3 | 3 | Stable | 0.8 | 114 | 129 | 143 | 128.8333 | 0.2 | 28 | 56 | 77 | 54.8333 | 0 | 75 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | 9. Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 0.8 | 19.1678 | 15.3343 | Reduce | 0.2 | 2.8752 | 0.57503 | H3 | 3 | Stable | 0.8 | 108 | 123 | 158 | 126.3333 | 0.1 | 24 | 47 | 76 | 48 | 85 | 75 | 0 | 51
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-06 | 2019-09-13 | 0.8 | 8.0322 | 6.4258 | Reduce | 0.5 | 4.006 | 2.003 | H2 | 4 | Stable | 0.8 | 117 | 127 | 150 | 129.1667 | 0.1 | 18 | 46 | 74 | 46 | 50.1263 | 37.5 | 0 | 30.0758
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK002 | Project_065_RISK002 | Opportunitity | Project Contingency | Open | H1 | 5 | 12. Acquisition and offsets | New supplier for enclosure | Person_598 | 2015-01-07 | 2017-10-19 | 0.05 | 9.6346 | 0.48173 | Exploit | 0.7 | 9.6346 | 6.7442 | H1 | 5 | Stable | [10 empty] | 0 | -1300 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier Selection Process | Person_379 | 2017-10-19 | 2019-04-23 | 0.4 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 109 | 130 | 158 | 131.1667 | 0.1 | 31 | 53 | 63 | 51 |  | 25 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Colour Representation in Video Image Distortion | Person_305 | 2017-09-22 | 2020-03-21 | 0.5 | 5.5323 | 2.7662 | Reduce | 0.1 | 5.5323 | 0.55323 | H3 | 3 | Stable | 0.6 | 91 | 121 | 141 | 119.3333 | 0.1 | 3 | 42 | 71 | 40.3333 | 0 | 80 | 1 | 2.4
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-21 | 0.8 | 35.2369 | 28.1895 | Reduce | 0.3 | 18.4979 | 5.5494 | H2 | 4 | Stable | 0.8 | 105 | 138 | 143 | 133.3333 | 0.3 | 17 | 58 | 79 | 54.6667 | 47.5042 | 62.5 | 0 | 28.5025
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 4 | 9. Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-21 | 0.7 | 20.6835 | 14.4785 | Reduce | 0.3 | 20.6835 | 6.2051 | H2 | 4 | Stable | 0.7 | 98 | 130 | 143 | 126.8333 | 0.3 | 1 | 59 | 61 | 49.6667 | 0 | 57.1429 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 4 | 8. System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 0.6 | 5.2585 | 3.1551 | Reduce | 0.15 | 5.2585 | 0.78877 | H2 | 4 | Stable | 0.9 | 106 | 131 | 153 | 130.5 | 0.1 | 33 | 45 | 78 | 48.5 | 0 | 75 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 0.3 | 7.7077 | 2.6977 | Accept | 0.3 | 7.7077 | 2.6977 | H3 | 3 | Stable | 0.5 | 81 | 122 | 149 | 119.6667 | 0.5 | 81 | 122 | 149 | 119.6667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-04-21 | 0.3 | 2.723 | 0.81691 | Reduce | 0.1 | 2.723 | 0.2723 | H3 | 3 | Improving | 0.5 | 92 | 137 | 160 | 133.3333 | 0.3 | 26 | 59 | 66 | 54.6667 | 0 | 66.6667 | 1 | 2
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-08 | 2020-09-21 | 0.2 | 4.8444 | 0.96888 | Reduce | 0.2 | 4.8444 | 0.96888 | H3 | 3 | Stable | 0.9 | 86 | 134 | 145 | 127.8333 | 0.2 | 23 | 56 | 62 | 51.5 | 0 | 0 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System Performance | Person_305 | 2016-09-08 | 2020-09-21 | 0.15 | 5.8725 | 0.88088 | Reduce | 0.05 | 5.8725 | 0.29363 | H2 | 4 | Stable | 0.9 | 112 | 128 | 157 | 130.1667 | 0.2 | 37 | 47 | 63 | 48 | 0 | 66.6667 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_038 | 2020-05-23 | 2023-10-26 | 0.2 | 7.4599 | 1.492 | Reduce | 0.05 | 7.4599 | 0.37299 | H2 | 4 | Stable | 0.6 | 98 | 136 | 160 | 133.6667 | 0.1 | 35 | 57 | 72 | 55.8333 | 0 | 75 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-29 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.9 | 88 | 121 | 143 | 119.1667 | 0.4 | 38 | 52 | 74 | 53.3333 | 60.3671 | 58.3333 | 0 | 36.2202
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-20 | 0.4 | 2.8643 | 1.1457 | Reduce | 0.1 | 2.8643 | 0.28643 | H3 | 3 | Stable | 0.5 | 95 | 139 | 149 | 133.3333 | 0.4 | 6 | 51 | 73 | 47.1667 | 0.0015933 | 75 | 1 | 2.251
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power Supply - Motor Controller Interface | Person_047 | 2016-05-23 | 2018-04-21 | 0.5 | 25.3543 | 12.6771 | Reduce | 0.2 | 25.3543 | 5.0709 | H3 | 3 | Stable | 0.6 | 109 | 132 | 144 | 130.1667 | 0.1 | 38 | 47 | 75 | 50.1667 | 0 | 60 | 1 | 1.8
2018-02-20 | ORG_002 | BA_005 | Portfolio_016 | Project_061 | RISK003 | Project_061_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Test equipment reliability | Person_104 | 2017-05-23 | 2020-11-19 | 0.4 | 0.11013 | 0.044051 | Reduce | 0.3 | 0.11013 | 0.033038 | H2 | 4 | Stable | 0.5 | 92 | 134 | 155 | 130.5 | 0.4 | 7 | 54 | 74 | 49.5 | 0 | 25 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-23 | 2024-05-22 | 0.1 | 0.64865 | 0.32433 | Accept | 0.1 | 0.64865 | 0.32433 | H3 | 3 | Improving | 0.6 | 91 | 127 | 149 | 124.6667 | 0.6 | 91 | 127 | 149 | 124.6667 | 0 | 0 | 1 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 0.70865 | 0.28346 | H2 | 4 | Stable | 0.5 | 85 | 136 | 158 | 131.1667 | 0.1 | 37 | 52 | 78 | 53.8333 | 82.0989 | 20 | 0 | 49.2593
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_703 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 1.7994 | 0.26991 | H3 | 3 | Stable | 0.5 | 111 | 139 | 149 | 136 | 0.3 | 25 | 48 | 72 | 48.1667 | 71.4286 | 70 | 1 | 44.9571
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_676 | 2016-08-21 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.5 | 117 | 131 | 150 | 131.8333 | 0.1 | 18 | 44 | 70 | 44 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_676 | 2016-08-21 | 2017-08-21 | 0.5 | 37.5906 | 18.7953 | Reduce | 0.15 | 37.5906 | 5.6386 | H3 | 3 | Stable | 0.5 | 87 | 138 | 153 | 132 | 0.2 | 2 | 56 | 74 | 50 | 0 | 70 | 1 | 2.1
2018-02-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-04-20 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.9 | 102 | 129 | 159 | 129.5 | 0.4 | 32 | 52 | 75 | 52.5 | 0 | 25 | 0 | 0
2018-02-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_077 | 2016-01-22 01:00 | 2018-04-18 | 0.15 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Improving | 0.7 | 90 | 125 | 157 | 124.5 | 0.4 | 28 | 43 | 76 | 46 |  | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Labour/Material Risk | Person_662 | 2015-05-24 | 2019-05-23 | 0.5 | 49.7149 | 14.9145 | Accept | 0.5 | 49.7149 | 14.9145 | H2 | 4 | Stable | 0.7 | 82 | 123 | 157 | 121.8333 | 0.7 | 82 | 123 | 157 | 121.8333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Survey costs | Person_618 | 2016-04-22 | 2018-08-21 | 0.2 | 13.2573 | 2.6515 | Avoid | 0.2 | 13.2573 | 2.6515 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_009 | Project_045 | RISK001 | Project_045_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour/T&S Overspend | Person_662 | 2017-01-21 01:00 | 2020-05-22 | 0.5 | 33.9324 | 6.7865 | Accept | 0.5 | 33.9324 | 6.7865 | H2 | 4 | Stable | 0.7 | 109 | 136 | 154 | 134.5 | 0.7 | 109 | 136 | 154 | 134.5 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-099 | Project_008_Risk-099 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Risk on Consumables Exposure | Person_639 | 2017-08-04 | 2018-08-21 | 0.5 | 5.6817 | 2.8408 | Reduce | 0.5 | 5.6817 | 2.8408 | H3 | 3 | Stable | 0.8 | 104 | 124 | 147 | 124.5 | 0.1 | 17 | 53 | 75 | 50.6667 | 0 | 0 | 1 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_676 | 2016-10-21 | 2019-08-20 | 0.5 | 14.0464 | 4.2139 | Accept | 0.5 | 14.0464 | 4.2139 | H2 | 4 | Stable | 0.8 | 97 | 122 | 141 | 121 | 0.8 | 97 | 122 | 141 | 121 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_676 | 2016-08-21 | 2019-08-20 | 0.2 | 9.4695 | 4.7347 | Accept | 0.2 | 9.4695 | 4.7347 | H3 | 3 | Stable | 0.9 | 95 | 134 | 152 | 130.5 | 0.9 | 95 | 134 | 152 | 130.5 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_676 | 2016-08-21 | 2019-08-20 | 0.35 | 27.1644 | 0.81493 | Accept | 0.35 | 12.8336 | 0.38501 | H3 | 3 | Stable | 0.8 | 103 | 134 | 146 | 130.8333 | 0.8 | 103 | 134 | 146 | 130.8333 | 52.7559 | 0 | 0 | 31.6535
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2018-03-22 | 2019-07-21 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.5 | 109 | 129 | 159 | 130.6667 | 0.1 | 30 | 52 | 67 | 50.8333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_585 | 2017-09-02 01:00 | 2018-10-31 01:00 | 0.1 | 6.4168 | 0.64168 | Transfer | 0.1 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sub-system FPGA | Person_332 | 2017-01-21 01:00 | 2018-09-20 01:00 | 0.4 | 1.5914 | 0.63655 | Reduce | 0.2 | 1.5914 | 0.31827 | H3 | 3 | Stable | 0.9 | 101 | 132 | 147 | 129.3333 | 0.1 | 11 | 49 | 60 | 44.5 | 0 | 50 | 1 | 1.5
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort for System HW/SW- System upgrade. | Person_199 | 2017-05-23 | 2019-09-18 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.2 | 2.5667 | 0.51334 | H3 | 3 | Stable | 0.9 | 107 | 121 | 158 | 124.8333 | 0.4 | 15 | 51 | 62 | 46.8333 | 0 | 33.3333 | 1 | 1
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs | Person_403 | 2018-04-22 | 2018-08-22 01:00 | 0.5 | 6.6521 | 3.326 | Reduce | 0.5 | 6.6521 | 3.326 | H2 | 4 | Stable | 0.5 | 120 | 128 | 146 | 129.6667 | 0.3 | 1 | 52 | 60 | 44.8333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.25 | 3.5934 | 0.89835 | H2 | 4 | Stable | 0.9 | 103 | 122 | 159 | 125 | 0.2 | 13 | 46 | 77 | 45.6667 | 0 | 50 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_676 | 2016-08-21 | 2019-08-20 | 0.25 | 4.2779 | 1.0695 | Accept | 0.25 | 4.2779 | 1.0695 | H3 | 3 | Stable | 0.6 | 99 | 135 | 145 | 130.6667 | 0.6 | 99 | 135 | 145 | 130.6667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Minimum Order Quantities | Person_403 | 2017-11-20 01:00 | 2018-06-21 | 0.2 | 1.925 | 0.38501 | Exploit | 0.2 | 1.925 | 0.38501 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_403 | 2018-04-22 | 2018-08-22 01:00 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Worsening | 0.8 | 102 | 137 | 144 | 132.3333 | 0.3 | 21 | 58 | 65 | 53 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2018-10-21 01:00 | 0.05 | 11.5502 | 3.8462 | Accept | 0.05 | 11.5502 | 3.8462 | H3 | 3 | Improving | 0.7 | 113 | 135 | 151 | 134 | 0.7 | 113 | 135 | 151 | 134 | 0 | 0 | 1 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) at the System level on product platform - performed by 3rd parties | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Sub-system / product system accreditation hindered by Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.1 | 0.25667 | 0.025667 | Transfer | 0.1 | 0.25667 | 0.025667 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_694 | 2017-05-23 | 2018-10-07 01:00 | 0.3 | 0 | 0 | Transfer | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 66.6667 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2018-05-15 | 0.3 | 0.89835 | 0.26951 | Transfer | 0.3 | 0.89835 | 0.26951 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 0.35 | 1.9208 | 0.67227 | Reduce | 0.25 | 1.9208 | 0.48019 | H2 | 4 | Stable | 0.9 | 82 | 127 | 155 | 124.1667 | 0.1 | 26 | 55 | 70 | 52.6667 | 0 | 28.5714 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2018-03-22 | 2018-10-18 01:00 | 0.4 | 0.77001 | 0.30801 | Reduce | 0.3 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.7 | 100 | 134 | 152 | 131.3333 | 0.4 | 24 | 47 | 71 | 47.1667 | 0 | 25 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_694 | 2018-02-20 01:00 | 2018-04-22 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.8 | 120 | 138 | 143 | 135.8333 | 0.1 | 26 | 57 | 67 | 53.5 | 0 | 28.5714 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS020 | Project_025_RS020 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Plant Machinery failure | Person_619 | 2017-03-23 | 2019-08-07 | 0.3 | 0.05293 | 0.015879 | Reduce | 0.3 | 0.05293 | 0.015879 | H2 | 4 | Stable | 0.9 | 112 | 139 | 148 | 136 | 0.4 | 38 | 59 | 70 | 57.3333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS019 | Project_025_RS019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Product Component Failure | Person_619 | 2017-03-23 | 2019-08-07 | 0.7 | 0.82924 | 0.58047 | Reduce | 0.3 | 0.82924 | 0.24877 | H2 | 4 | Stable | 0.6 | 90 | 131 | 153 | 127.8333 | 0.2 | 5 | 57 | 68 | 50.1667 | 0 | 57.1429 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_373 | 2012-08-21 01:00 | 2019-08-07 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 2.2054 | 1.3453 | H1 | 5 | Stable | 0.6 | 85 | 138 | 159 | 132.6667 | 0.2 | 14 | 43 | 69 | 42.5 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-054 | Project_062_Risk-054 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | sub-system rework to reviised standard | Person_031 | 2017-07-21 | 2018-11-21 01:00 | 0.4 | 0.62744 | 0.25098 | Transfer | 0.4 | 0.62744 | 0.25098 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-010 | Project_062_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Resource | Person_479 | 2017-07-21 | 2019-02-21 01:00 | 0.4 | 7.5293 | 3.0117 | Reduce | 0.3 | 7.5293 | 2.2588 | H2 | 4 | Stable | 0.9 | 99 | 132 | 160 | 131.1667 | 0.2 | 6 | 59 | 62 | 50.6667 | 0 | 25 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-013 | Project_062_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Unavailability of Network | Person_479 | 2017-07-21 | 2018-05-22 | 0.25 | 3.5555 | 0.88888 | Reduce | 0.2 | 3.5555 | 0.7111 | H3 | 3 | Stable | 0.7 | 83 | 124 | 152 | 121.8333 | 0.1 | 3 | 47 | 75 | 44.3333 | 0 | 20 | 1 | 0.6
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-055 | Project_062_Risk-055 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Supplier integration and Apps | Person_245 | 2017-07-21 | 2018-11-21 01:00 | 0.5 | 0.83659 | 0.4183 | Reduce | 0.5 | 0.83659 | 0.4183 | H2 | 4 | Stable | 0.5 | 95 | 122 | 155 | 123 | 0.3 | 34 | 55 | 62 | 52.6667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-011 | Project_062_Risk-011 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Variant deviations between SW | Person_479 | 2017-07-21 | 2018-05-13 | 0.4 | 0.71808 | 0.28723 | Reduce | 0.3 | 0.71808 | 0.21542 | H2 | 4 | Stable | 0.8 | 114 | 127 | 160 | 130.3333 | 0.2 | 22 | 58 | 62 | 52.6667 | 0 | 25 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-056 | Project_062_Risk-056 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Supplier integration acceptance by end Customer | Person_031 | 2017-07-21 | 2018-11-21 01:00 | 0.3 | 1.8823 | 0.5647 | Reduce | 0.3 | 1.8823 | 0.5647 | H3 | 3 | Stable | 0.9 | 80 | 121 | 160 | 120.6667 | 0.1 | 3 | 49 | 79 | 46.3333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-017 | Project_062_Risk-017 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer platform Schedule Unknown | Person_459 | 2017-07-21 | 2018-10-22 01:00 | 0.2 | 2.5098 | 0.50196 | Avoid | 0.1 | 2.5098 | 0.25098 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-037 | Project_062_Risk-037 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Server availability | Person_459 | 2017-07-21 | 2018-04-22 | 0.35 | 4.183 | 1.464 | Avoid | 0.1 | 4.183 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 71.4286 | 1 | 2.1429
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-038 | Project_062_Risk-038 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Delay in start of Phase 2 | Person_459 | 2017-07-21 | 2018-02-20 01:00 | 0.2 | 2.0915 | 0.4183 | Avoid | 0.2 | 2.0915 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-016 | Project_062_Risk-016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Supplier Component Unavailability | Person_664 | 2017-07-21 | 2018-05-15 | 0.3 | 2.0927 | 0.62782 | Reduce | 0.2 | 2.0915 | 0.4183 | H3 | 3 | Stable | 0.6 | 119 | 140 | 159 | 139.6667 | 0.3 | 13 | 53 | 78 | 50.5 | 0.059964 | 33.3333 | 0 | 0.035978
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-020 | Project_062_Risk-020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Security Encryption Solution | Person_245 | 2017-07-21 | 2018-09-20 01:00 | 0.25 | 4.183 | 1.0457 | Reduce | 0.2 | 4.183 | 0.83659 | H2 | 4 | Stable | 0.9 | 94 | 134 | 155 | 130.8333 | 0.1 | 24 | 47 | 74 | 47.6667 | 0 | 20 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-021 | Project_062_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Hardware CoSupplierng | Person_664 | 2017-07-21 | 2018-07-20 | 0.3 | 6.2744 | 1.8823 | Reduce | 0.25 | 6.2744 | 1.5686 | H2 | 4 | Stable | 0.9 | 115 | 128 | 156 | 130.5 | 0.1 | 29 | 44 | 61 | 44.3333 | 0 | 16.6667 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-043 | Project_062_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | User response | Person_459 | 2017-07-21 | 2019-02-21 01:00 | 0.35 | 3.3464 | 1.1712 | Avoid | 0.25 | 3.3464 | 0.83659 | H2 | 4 | Stable | [10 empty] | 0 | 28.5714 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-002 | Project_062_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | SDLC Card Obsolescence | Person_253 | 2017-07-21 | 2019-03-22 | 0.5 | 2.0915 | 1.0457 | Transfer | 0.2 | 2.0915 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 60 | 1 | 1.8
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-047 | Project_062_Risk-047 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Redhat6 on PCI shelf | Person_245 | 2017-07-21 | 2019-03-24 | 0.3 | 7.1808 | 2.1542 | Avoid | 0.3 | 7.1808 | 2.1542 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-025 | Project_062_Risk-025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | System Obsolescence Risk | Person_543 | 2017-07-21 | 2019-03-22 | 0.3 | 2.0915 | 0.62744 | Avoid | 0.2 | 2.0915 | 0.4183 | H2 | 4 | Stable | [10 empty] | 0 | 33.3333 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-022 | Project_062_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Registers Might Be Unstable | Person_479 | 2017-07-21 | 2018-06-22 | 0.25 | 1.3385 | 0.33464 | Reduce | 0.2 | 1.3385 | 0.26771 | H3 | 3 | Stable | 0.7 | 111 | 133 | 143 | 131 | 0.2 | 11 | 52 | 63 | 47 | 0 | 20 | 1 | 0.6
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-001 | Project_062_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier servers | Person_459 | 2017-10-21 01:00 | 2018-05-23 | 0.5 | 1.2549 | 0.62744 | Reduce | 0.5 | 1.2549 | 0.62744 | H2 | 4 | Stable | 0.8 | 86 | 129 | 142 | 124 | 0.4 | 22 | 40 | 66 | 41.3333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-023 | Project_062_Risk-023 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Change In Security Boundary | Person_031 | 2017-07-21 | 2019-02-21 01:00 | 0.3 | 4.6013 | 1.3804 | Reduce | 0.2 | 4.6013 | 0.92025 | H3 | 3 | Stable | 0.8 | 95 | 135 | 145 | 130 | 0.2 | 36 | 50 | 67 | 50.5 | 0 | 33.3333 | 1 | 1
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-006 | Project_062_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unavailability of Hardware | Person_253 | 2017-07-21 | 2019-03-22 | 0.5 | 2.5098 | 1.2549 | Reduce | 0.25 | 2.5098 | 0.62744 | H2 | 4 | Stable | 0.6 | 83 | 128 | 159 | 125.6667 | 0.4 | 26 | 49 | 72 | 49 | 0 | 50 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-048 | Project_062_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software lockdown features | Person_245 | 2017-07-21 | 2018-11-21 01:00 | 0.5 | 0.71808 | 0.35904 | Reduce | 0.5 | 0.71808 | 0.35904 | H2 | 4 | Stable | 0.6 | 99 | 138 | 150 | 133.5 | 0.4 | 12 | 44 | 72 | 43.3333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-005 | Project_062_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Security Solution Integration | Person_245 | 2017-07-21 | 2018-11-14 01:00 | 0.3 | 4.6013 | 1.3804 | Avoid | 0.25 | 4.6013 | 1.1503 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE-01 | Project_067_SE-01 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Procurement of Cables for Rig (Procurement Process) | Person_327 | 2015-08-22 | 2018-08-21 | 0.4 | 0.63006 | 0.25202 | Reduce | 0.2 | 0.31503 | 0.063006 | H3 | 3 | Stable | 0.6 | 96 | 128 | 143 | 125.1667 | 0.4 | 22 | 44 | 67 | 44.1667 | 50 | 50 | 1 | 31.5
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-R1 | Project_067_Risk-R1 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Rhapsody modification to manual to System interface | Person_327 | 2017-03-23 | 2018-08-13 | 0.3 | 7.8758 | 2.3627 | Reduce | 0.2 | 2.2502 | 0.45004 | H3 | 3 | Stable | 0.8 | 98 | 135 | 146 | 130.6667 | 0.3 | 24 | 49 | 79 | 49.8333 | 71.4286 | 33.3333 | 1 | 43.8571
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE-10 | Project_067_SE-10 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Configuration baseline unstable for Platform | Person_327 | 2017-10-26 | 2018-08-18 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.8 | 118 | 128 | 153 | 130.5 | 0.3 | 15 | 41 | 77 | 42.6667 |  | 60 | 1
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE-08 | Project_067_SE-08 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Ageing Test Infrastructure | Person_327 | 2015-10-01 | 2018-08-21 | 0.6 | 0 | 0 | Transfer | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 33.3333 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-R4 | Project_067_Risk-R4 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Resource Availability | Person_011 | 2015-08-22 | 2018-08-21 | 0.45 | 2.579 | 1.1606 | Reduce | 0.6 | 1.2857 | 0.77145 | H1 | 5 | Improving | 0.5 | 109 | 132 | 148 | 130.8333 | 0.2 | 4 | 44 | 66 | 41 | 50.1455 | -33.3333 | 0 | 30.0873
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-R2 | Project_067_Risk-R2 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Sub-Contractor Performance - Manufacturing | Person_011 | 2015-08-22 | 2018-08-20 | 0.3 | 0.23127 | 0.069382 | Reduce | 0.1 | 0.040628 | 0.0040628 | H3 | 3 | Improving | 0.9 | 80 | 136 | 143 | 127.8333 | 0.1 | 3 | 48 | 66 | 43.5 | 82.4331 | 66.6667 | 1 | 51.4598
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-R6 | Project_067_Risk-R6 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub-Contractor Performance - Support Services | Person_011 | 2017-08-21 | 2018-08-21 | 0.5 | 2.2502 | 1.1251 | Reduce | 0.5 | 2.2502 | 1.1251 | H2 | 4 | Stable | 0.7 | 88 | 124 | 160 | 124 | 0.3 | 3 | 59 | 74 | 52.1667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-1 | Project_067_Risk-1 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Schedule Overrun | Person_002 | 2018-02-20 | 2019-10-20 | 0.7 | 0 | 0 | Reduce | 0.7 | 0 | 0 | H1 | 5 | Stable | 0.5 | 90 | 125 | 149 | 123.1667 | 0.4 | 6 | 40 | 67 | 38.8333 |  | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-2 | Project_067_Risk-2 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System Performance | Person_765 | 2018-02-20 | 2019-10-20 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.7 | 109 | 127 | 147 | 127.3333 | 0.2 | 13 | 46 | 66 | 43.8333 |  | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-5 | Project_067_Risk-5 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System performance levels | Person_327 | 2018-02-20 | 2019-10-20 | 0.3 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.5 | 99 | 131 | 143 | 127.6667 | 0.3 | 13 | 45 | 60 | 42.1667 |  | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-6 | Project_067_Risk-6 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | System Resources | Person_002 | 2018-03-02 | 2019-10-20 | 0.3 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.5 | 91 | 135 | 157 | 131.3333 | 0.2 | 1 | 42 | 73 | 40.3333 |  | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-085 | Project_008_SER-085 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Insufficient LOE to manage the supply chain with reducing number of spares | Person_639 | 2017-04-22 | 2018-08-21 | 0.25 | 13.4066 | 5.3626 | Accept | 0.25 | 13.4066 | 5.3626 | H3 | 3 | Stable | 0.5 | 98 | 131 | 147 | 128.1667 | 0.5 | 98 | 131 | 147 | 128.1667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | R054 | Project_066_R054 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | System Cybersecurity shortfalls | Person_507 | 2017-01-21 01:00 | 2024-05-23 | 0.8 | 15.7936 | 12.6349 | Reduce | 0.5 | 15.7936 | 7.8968 | H1 | 5 | Stable | 0.6 | 108 | 138 | 148 | 134.6667 | 0.4 | 32 | 56 | 69 | 54.1667 | 0 | 37.5 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_567 | 2017-08-21 01:00 | 2018-08-21 | 0.3 | 18.5516 | 12.9861 | Accept | 0.3 | 18.5516 | 12.9861 | H2 | 4 | Stable | 0.8 | 115 | 124 | 160 | 128.5 | 0.8 | 115 | 124 | 160 | 128.5 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Lack of Spares Availability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 0.2 | 8.8305 | 2.6492 | Accept | 0.2 | 8.8305 | 2.6492 | H3 | 3 | Stable | 0.7 | 115 | 133 | 153 | 133.3333 | 0.7 | 115 | 133 | 153 | 133.3333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-148 | Project_008_SER-148 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Demands but not provisioned | Person_639 | 2017-08-21 01:00 | 2018-08-21 | 0.3 | 28.5076 | 7.1269 | Accept | 0.3 | 28.5076 | 2.8508 | H3 | 3 | Stable | 0.5 | 91 | 130 | 150 | 126.8333 | 0.5 | 91 | 130 | 150 | 126.8333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-094 | Project_008_Risk-094 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Consumable Stock Levels | Person_567 | 2017-04-22 | 2018-08-21 | 0.5 | 1.4099 | 0.42298 | Accept | 0.5 | 1.4099 | 0.42298 | H3 | 3 | Stable | 0.7 | 108 | 124 | 148 | 125.3333 | 0.7 | 108 | 124 | 148 | 125.3333 | 0 | 0 | 1 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_585 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 105.645 | 105.645 | Accept | 0.03 | 105.645 | 105.645 | H3 | 3 | Stable | 0.6 | 81 | 123 | 158 | 121.8333 | 0.6 | 81 | 123 | 158 | 121.8333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 12.1204 | 12.1204 | Accept | 0.25 | 12.1204 | 12.1204 | H2 | 4 | Stable | 0.9 | 113 | 122 | 144 | 124.1667 | 0.9 | 113 | 122 | 144 | 124.1667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2018-05-22 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.7 | 84 | 123 | 148 | 120.6667 | 0.1 | 17 | 45 | 63 | 43.3333 | 0 | 40 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 11.0894 | 0.55447 | Accept | 0.2 | 11.0894 | 0.33268 | H3 | 3 | Stable | 0.7 | 112 | 127 | 159 | 129.8333 | 0.7 | 112 | 127 | 159 | 129.8333 | 0 | 33.3333 | 1 | 1
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 0.92411 | 0.55447 | Reduce | 0.5 | 0.36965 | 0.18482 | H2 | 4 | Stable | 0.5 | 101 | 123 | 148 | 123.5 | 0.4 | 29 | 52 | 75 | 52 | 60 | 16.6667 | 0 | 36
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-03 23:00 | 2018-04-21 | 0.2 | 4.0661 | 0.81322 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.9 | 95 | 134 | 154 | 130.8333 | 0.1 | 33 | 52 | 72 | 52.1667 | 0 | 75 | 1 | 2.25
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.5 | 0.46206 | 0.23103 | H1 | 5 | Stable | 0.6 | 86 | 136 | 148 | 129.6667 | 0.2 | 38 | 47 | 64 | 48.3333 | 58.3333 | 16.6667 | 0 | 35
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design [in addition to costed effort] | Person_332 | 2017-05-28 | 2018-11-30 01:00 | 0.2 | 1.1089 | 0.88715 | Accept | 0.2 | 0.73929 | 0.44357 | H3 | 3 | Improving | 0.5 | 102 | 132 | 142 | 128.6667 | 0.5 | 102 | 132 | 142 | 128.6667 | 33.3333 | 0 | 1 | 20
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-28 23:00 | 2018-05-22 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.8 | 95 | 128 | 141 | 124.6667 | 0.2 | 5 | 49 | 72 | 45.5 | 0 | 50 | 1 | 1.5
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2018-05-22 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.6 | 91 | 135 | 154 | 130.8333 | 0.4 | 25 | 57 | 74 | 54.5 | 0 | 25 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_693 | 2012-06-01 | 2018-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Improving | 0.6 | 103 | 133 | 150 | 130.8333 | 0.4 | 38 | 41 | 79 | 46.8333 | 0 | 40 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2018-05-21 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Stable | [10 empty] | 0 | 37.5 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_585 | 2017-10-21 01:00 | 2019-07-21 | 0.333 | 3.6965 | 0.36965 | Accept | 0.333 | 3.6965 | 0.18482 | H2 | 4 | Stable | 0.9 | 105 | 140 | 151 | 136 | 0.9 | 105 | 140 | 151 | 136 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 0.92411 | 0.18482 | Accept | 0.3 | 0.92411 | 0.18482 | H2 | 4 | Improving | 0.6 | 106 | 123 | 145 | 123.8333 | 0.6 | 106 | 123 | 145 | 123.8333 | 0 | 25 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2020-09-19 01:00 | 0.2 | 1.8482 | 0.55447 | Accept | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.9 | 102 | 123 | 154 | 124.6667 | 0.9 | 102 | 123 | 154 | 124.6667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2018-02-18 23:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.6 | 114 | 129 | 143 | 128.8333 | 0.2 | 5 | 56 | 64 | 48.8333 | 90 | 75 | 1 | 56.25
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2019-07-21 | 0.3 | 0.36965 | 0.25875 | Accept | 0.2 | 0.36965 | 0.25875 | H3 | 3 | Stable | 0.6 | 104 | 131 | 154 | 130.3333 | 0.6 | 104 | 131 | 154 | 130.3333 | 0 | 33.3333 | 1 | 1
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK010 | Project_010_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Use of Lead components | Person_359 | 2012-05-23 | 2025-04-22 | 0.05 | 1.8482 | 0.092411 | Reduce | 0.05 | 1.8482 | 0.092411 | H3 | 3 | Stable | 0.7 | 91 | 126 | 150 | 124.1667 | 0.3 | 31 | 53 | 69 | 52 | 0 | 0 | 1 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-057 | Project_062_Risk-057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Supplier Application Encryption / Protection | Person_253 | 2017-07-21 | 2019-02-21 01:00 | 0.3 | 15.8141 | 3.9535 | Accept | 0.3 | 15.8141 | 3.9535 | H2 | 4 | Stable | 0.6 | 80 | 132 | 151 | 126.5 | 0.6 | 80 | 132 | 151 | 126.5 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-119 | Project_029_Risk-119 | Opportunitity | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Not required to support on load & offload of Customer Furnished Equipmnet | Person_585 | 2017-05-23 | 2020-04-16 | 0.8 | 5.1334 | 4.1067 | Exploit | 0.8 | 3.4137 | 2.731 | H2 | 4 | Stable | [10 empty] | 33.5 | 0 | 0 | 20.1
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-034 | Project_062_Risk-034 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Long lead Procurement price increases | Person_664 | 2017-07-21 | 2018-04-22 | 0.25 | 2.6585 | 0.66463 | Accept | 0.25 | 2.6585 | 0.66463 | H2 | 4 | Stable | 0.5 | 96 | 133 | 142 | 128.3333 | 0.5 | 96 | 133 | 142 | 128.3333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK003 | Project_001_RISK003 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Non-Recurring Engineering higher than expected | Person_674 | 2017-12-20 23:00 | 2018-08-21 | 0.5 | 16.0059 | 8.0029 | Reduce | 0.2 | 8.0029 | 1.6006 | H3 | 3 | Improving | 0.7 | 108 | 127 | 145 | 126.8333 | 0.1 | 15 | 58 | 76 | 53.8333 | 50 | 60 | 0 | 30
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-018 | Project_062_Risk-018 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Prioritisation - new or less experienced staff | Person_459 | 2017-07-21 | 2018-11-20 01:00 | 0.35 | 4.8729 | 3.8983 | Accept | 0.3 | 4.8729 | 3.8983 | H2 | 4 | Improving | 0.7 | 118 | 127 | 157 | 130.5 | 0.7 | 118 | 127 | 157 | 130.5 | 0 | 14.2857 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-009 | Project_062_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Unresolved technical debt (excluding ILS) | Person_253 | 2017-07-21 | 2018-05-22 | 0.5 | 2.6676 | 0.53353 | Accept | 0.5 | 2.6676 | 0.53353 | H2 | 4 | Stable | 0.8 | 100 | 125 | 150 | 125 | 0.8 | 100 | 125 | 150 | 125 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-004 | Project_062_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Undefined risks | Person_459 | 2017-07-21 | 2019-03-24 | 0.35 | 2.7703 | 1.3852 | Accept | 0.35 | 2.7703 | 1.3852 | H2 | 4 | Stable | 0.6 | 104 | 138 | 149 | 134.1667 | 0.6 | 104 | 138 | 149 | 134.1667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--17 | Project_021_Risk--17 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to technical performance | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.5 | 93 | 122 | 154 | 122.5 | 0.1 | 31 | 43 | 69 | 45.3333 |  | 33.3333 | 1
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--39 | Project_021_Risk--39 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Delay to completion of product upgrade | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.7 | 96 | 136 | 145 | 130.8333 | 0.3 | 34 | 40 | 77 | 45.1667 |  | 40 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--16 | Project_021_Risk--16 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of weather | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.5 | 106 | 135 | 147 | 132.1667 | 0.3 | 18 | 45 | 68 | 44.3333 |  | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--15 | Project_021_Risk--15 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to lack of personnel resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.9 | 87 | 132 | 155 | 128.3333 | 0.2 | 25 | 50 | 65 | 48.3333 |  | 33.3333 | 1
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--14 | Project_021_Risk--14 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to late Trials Approval | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.5 | 88 | 128 | 154 | 125.6667 | 0.1 | 37 | 40 | 73 | 45 |  | 66.6667 | 1
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--13 | Project_021_Risk--13 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Critical or Safety PR arises in Final build /Decision Point concludes new release req | Person_174 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.8 | 99 | 123 | 148 | 123.1667 | 0.2 | 6 | 55 | 78 | 50.6667 | 0 | 50 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--12 | Project_021_Risk--12 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.8 | 102 | 126 | 142 | 124.6667 | 0.2 | 33 | 54 | 62 | 51.8333 | 0 | 33.3333 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--11 | Project_021_Risk--11 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.8 | 111 | 132 | 152 | 131.8333 | 0.1 | 22 | 43 | 60 | 42.3333 | 7.8429 | 40 | 0 | 4.7058
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--10 | Project_021_Risk--10 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Stable | 0.6 | 94 | 123 | 155 | 123.5 | 0.2 | 23 | 49 | 65 | 47.3333 | 0 | 57.1429 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--32 | Project_021_Risk--32 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Lack of Customer resource to provide timely to Acceptance and Closure activities | Person_766 | 2018-10-22 01:00 | 2019-04-23 | 0.8 | 0 | 0 | Reduce | 0.4 | 0 | 0 | H2 | 4 | Stable | 0.9 | 117 | 130 | 150 | 131.1667 | 0.4 | 11 | 45 | 71 | 43.6667 |  | 50 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--18 | Project_021_Risk--18 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.5 | 114 | 130 | 146 | 130 | 0.2 | 38 | 59 | 69 | 57.1667 | 50 | 28.5714 | 0 | 30
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--28 | Project_021_Risk--28 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort required to agree protocl for Client Server | Person_766 | 2018-03-23 | 2019-03-23 | 0.8 | 1.1522 | 0.92174 | Reduce | 0.4 | 1.1522 | 0.46087 | H2 | 4 | Stable | 0.7 | 115 | 121 | 149 | 124.6667 | 0.4 | 4 | 50 | 72 | 46 | 0 | 50 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--05 | Project_021_Risk--05 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification delays | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Worsening | 0.8 | 111 | 127 | 149 | 128 | 0.1 | 32 | 45 | 72 | 47.3333 |  | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--04 | Project_021_Risk--04 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Final Qual test report delayed due to insufficient supply chain resource | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 0.2 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 89 | 136 | 153 | 131 | 0.4 | 31 | 45 | 67 | 46.3333 |  | 50 | 1
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--03 | Project_021_Risk--03 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.5 | 105 | 122 | 148 | 123.5 | 0.1 | 35 | 46 | 71 | 48.3333 | 0 | 33.3333 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--25 | Project_021_Risk--25 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of supporting resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 112 | 130 | 153 | 130.8333 | 0.4 | 36 | 57 | 60 | 54 |  | 40 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--02 | Project_021_Risk--02 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_061 | 2018-02-20 01:00 | 2019-03-23 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.8 | 106 | 123 | 142 | 123.3333 | 0.2 | 31 | 44 | 71 | 46.3333 | 80 | 66.6667 | 0 | 48
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--24 | Project_021_Risk--24 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of equipment | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 82 | 123 | 157 | 121.8333 | 0.1 | 1 | 50 | 60 | 43.5 |  | 40 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--01 | Project_021_Risk--01 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification/ delay due to build standard issue | Person_615 | 2018-02-20 01:00 | 2018-06-22 | 0.1 | 2.2183 | 0.22183 | Reduce | 0.05 | 2.2183 | 0.11091 | H2 | 4 | Stable | 0.8 | 111 | 132 | 154 | 132.1667 | 0.1 | 5 | 52 | 60 | 45.5 | 0 | 50 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--21 | Project_021_Risk--21 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.7 | 117 | 125 | 144 | 126.8333 | 0.2 | 13 | 40 | 61 | 39 |  | 40 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--09 | Project_021_Risk--09 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 85 | 129 | 141 | 123.6667 | 0.2 | 27 | 48 | 60 | 46.5 |  | 40 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--08 | Project_021_Risk--08 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H3 | 3 | Stable | 0.7 | 88 | 135 | 159 | 131.1667 | 0.2 | 11 | 44 | 64 | 41.8333 |  | 62.5 | 1
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--07 | Project_021_Risk--07 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 0.6 | 17.2826 | 10.3696 | Reduce | 0.3 | 17.2826 | 5.1848 | H2 | 4 | Worsening | 0.9 | 91 | 132 | 141 | 126.6667 | 0.4 | 20 | 44 | 63 | 43.1667 | 0 | 50 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--20 | Project_021_Risk--20 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | ERP implementation | Person_061 | 2018-01-21 01:00 | 2018-07-20 | 0.5 | 0 | 0 | Reduce | 0.25 | 0 | 0 | H2 | 4 | Stable | 0.7 | 102 | 123 | 141 | 122.5 | 0.3 | 2 | 48 | 64 | 43 |  | 50 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier revert to original component (Supplier NRE) | Person_693 | 2017-05-23 | 2018-01-20 01:00 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.02 | 6.431 | 0.12862 | H3 | 3 | Improving | 0.6 | 114 | 134 | 148 | 133 | 0.4 | 27 | 47 | 68 | 47.1667 | -47.0588 | 86.6667 | 1 | -25.6353
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK011 | Project_041_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier Development support | Person_693 | 2016-11-20 01:00 | 2019-08-21 01:00 | 0.3 | 0.77172 | 0.23152 | -- | 0.3 | 0.77172 | 0.23152 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_238 | 2017-04-22 | 2018-05-22 | 0.25 | 3.3227 | 0.83067 | Reduce | 0.012 | 3.3055 | 0.039667 | H3 | 3 | Stable | 0.5 | 96 | 121 | 145 | 120.8333 | 0.4 | 9 | 55 | 66 | 49.1667 | 0.51615 | 95.2 | 1 | 3.1657
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unforseen and substantial increase in Repairs workload during new build production period. | Person_238 | 2017-10-23 01:00 | 2019-08-21 01:00 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.25 | 1.5434 | 0.38586 | H2 | 4 | Stable | 0.9 | 95 | 133 | 145 | 128.6667 | 0.2 | 26 | 52 | 64 | 49.6667 | 0 | 16.6667 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK007 | Project_041_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Advanced production of products using a Qual. standard component rather than a Prod. standard | Person_547 | 2017-10-21 01:00 | 2018-06-22 | 0.49 | 1.2862 | 0.63024 | Reduce | 0.2 | 1.2862 | 0.25724 | H3 | 3 | Stable | 0.7 | 101 | 123 | 145 | 123 | 0.4 | 21 | 55 | 68 | 51.5 | 0 | 59.1837 | 1 | 1.7755
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 4 | 7. Finance | Reduce touch labour if Production readiness programme successful | Person_238 | 2017-05-23 | 2018-03-23 | 0.3 | 1.5606 | 0.46818 | Exploit | 0.5 | 1.5606 | 0.7803 | H2 | 4 | Stable | [10 empty] | 0 | -66.6667 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Outstanding CRs | Person_693 | 2017-05-23 | 2018-05-22 | 0.25 | 0.77172 | 0.19293 | Reduce | 0.5 | 0.77172 | 0.38586 | H2 | 4 | Stable | 0.7 | 94 | 134 | 156 | 131 | 0.1 | 19 | 59 | 63 | 53 | 0 | -100 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_693 | 2018-03-23 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.8 | 116 | 123 | 159 | 127.8333 | 0.1 | 2 | 46 | 74 | 43.3333 | 0 | 50 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | R181 | Project_066_R181 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | USB Hub start up issues | Person_247 | 2017-01-21 01:00 | 2024-05-23 | 1 | 1.9722 | 0.98609 | Accept | 1 | 1.9722 | 0.98609 | H2 | 4 | Stable | 0.9 | 115 | 127 | 160 | 130.5 | 0.9 | 115 | 127 | 160 | 130.5 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-19 23:00 | 0.05 | 1.7492 | 0.17492 | Accept | 0.03 | 1.7492 | 0.12944 | H2 | 4 | Stable | 0.8 | 107 | 123 | 151 | 125 | 0.8 | 107 | 123 | 151 | 125 | 0 | 40 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2018-04-22 | 0.8 | 2.5081 | 1.2541 | Accept | 0.6 | 2.5081 | 1.2541 | H1 | 5 | Stable | 0.6 | 96 | 127 | 148 | 125.3333 | 0.6 | 96 | 127 | 148 | 125.3333 | 0 | 25 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment (Second Test Set) | Person_238 | 2017-05-23 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.15 | 0.68598 | 0.1029 | H3 | 3 | Stable | 0.7 | 116 | 134 | 142 | 132.3333 | 0.3 | 11 | 46 | 64 | 43.1667 | 0 | 40 | 1 | 1.2
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-26 23:00 | 2018-05-22 | 0.1 | 3.7514 | 0.37514 | Accept | 0.05 | 3.7514 | 0.37514 | H2 | 4 | Stable | 0.7 | 88 | 139 | 153 | 132.8333 | 0.7 | 88 | 139 | 153 | 132.8333 | 0 | 50 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2017-05-23 | 2019-08-20 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Improving | 0.7 | 116 | 131 | 154 | 132.3333 | 0.4 | 9 | 46 | 62 | 42.5 | 0 | 60 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2018-05-21 | 0.2 | 7.2784 | 2.1835 | Accept | 0.2 | 7.2784 | 2.1835 | H3 | 3 | Worsening | 0.9 | 111 | 139 | 145 | 135.3333 | 0.9 | 111 | 139 | 145 | 135.3333 | 0 | 0 | 1 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2018-04-22 | 0.3 | 3.0869 | 0.30869 | Accept | 0.2 | 3.0869 | 0.30869 | H3 | 3 | Stable | 0.6 | 118 | 125 | 154 | 128.6667 | 0.6 | 118 | 125 | 154 | 128.6667 | 0 | 33.3333 | 0 | 0
2018-02-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-010 | Project_052_Risk-010 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Potential update of software / hardware required during the 3 year support period (RESOURCE) | Person_376 | 2017-08-19 01:00 | 2020-08-19 01:00 | 0.25 | 3.1214 | 0.78035 | Transfer | 0.25 | 3.1214 | 0.78035 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-034 | Project_008_SER-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_567 | 2018-05-22 | 2018-08-21 | 0.25 | 8.5887 | 0.85887 | Accept | 0.25 | 8.5887 | 0.85887 | H3 | 3 | Stable | 0.9 | 106 | 133 | 151 | 131.5 | 0.9 | 106 | 133 | 151 | 131.5 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK016 | Project_038_RISK016 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Supplier Quality Issues | Person_397 | 2012-11-20 01:00 | 2018-08-22 01:00 | 0.5 | 5.0339 | 2.517 | Avoid | 0.5 | 5.0339 | 2.517 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK018 | Project_038_RISK018 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Last System Syndrome | Person_329 | 2012-11-20 01:00 | 2018-10-21 01:00 | 0.15 | 43.4175 | 6.5126 | -- | 0.1288 | 43.4175 | 5.5922 | H2 | 4 | Worsening | [10 empty] | 0 | 14.1333 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-21 21:00 | 2016-12-20 21:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.5 | 81 | 126 | 154 | 123.1667 | 0.2 | 1 | 48 | 79 | 45.3333 | 47 | 0 | 0 | 28.2
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-21 21:00 | 2016-12-20 21:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-18 21:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.2 | 1.5935 | 0.3187 | H3 | 3 | Stable | 0.7 | 110 | 133 | 145 | 131.1667 | 0.4 | 25 | 46 | 78 | 47.8333 | 50 | 50 | 1 | 31.5
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK003 | Project_001_RISK003 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Non-Recurring Engineering higher than expected | Person_674 | 2017-12-21 | 2018-08-21 | 0.5 | 16.0059 | 8.0029 | Reduce | 0.2 | 8.0029 | 1.6006 | H3 | 3 | Improving | 0.6 | 80 | 123 | 149 | 120.1667 | 0.3 | 30 | 55 | 77 | 54.5 | 50 | 60 | 0 | 30
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-117 | Project_043_Risk-117 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Supplier Technical Publications maturity not at the level required | Person_769 | 2017-04-19 | 2018-05-13 | 0.45 | 1.7366 | 0.78146 | Reduce | 0.45 | 1.7366 | 0.78146 | H1 | 5 | Improving | 0.8 | 110 | 132 | 148 | 131 | 0.4 | 14 | 44 | 67 | 42.8333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-111 | Project_043_Risk-111 | Opportunitity | Project Contingency | Open | H1 | 5 | 7. Finance | Decrease the cost of obsolescence sweeps | Person_769 | 2018-01-11 01:00 | 2020-12-21 01:00 | 0.5 | 0.038325 | 0.019162 | Exploit | 0.5 | 0.038325 | 0.019162 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-113 | Project_043_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | No Gen 1 products available, transition cost to Gen 2 | Person_769 | 2017-04-19 | 2020-12-21 01:00 | 0.3 | 1.4971 | 0.44912 | Reduce | 0.3 | 1.4971 | 0.44912 | H2 | 4 | Stable | 0.5 | 94 | 139 | 148 | 133 | 0.3 | 2 | 45 | 67 | 41.5 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-121 | Project_043_Risk-121 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | More Tech Pubs Update than estimated | Person_769 | 2019-01-21 01:00 | 2020-10-20 01:00 | 0.45 | 1.7366 | 0.78146 | Reduce | 0.45 | 1.7366 | 0.78146 | H1 | 5 | Stable | 0.5 | 119 | 122 | 141 | 124.6667 | 0.4 | 39 | 54 | 77 | 55.3333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-084 | Project_043_Risk-084 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | complex repair ( over and above the forecast average) | Person_368 | 2017-12-21 01:00 | 2020-12-21 01:00 | 0.2 | 0.71859 | 0.14372 | Reduce | 0.2 | 0.71859 | 0.14372 | H2 | 4 | Stable | 0.7 | 115 | 122 | 160 | 127.1667 | 0.3 | 6 | 43 | 60 | 39.6667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-128 | Project_043_Risk-128 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Reliance of Customer Avaliability | Person_135 | 2017-04-19 | 2018-08-21 | 0.5 | 1.7665 | 0.88326 | Reduce | 0.5 | 1.7665 | 0.88326 | H1 | 5 | Stable | 0.7 | 103 | 140 | 149 | 135.3333 | 0.3 | 30 | 54 | 68 | 52.3333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-089 | Project_043_Risk-089 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares pool is limited | Person_307 | 2018-12-22 01:00 | 2020-12-21 01:00 | 0.25 | 1.5969 | 0.39921 | Reduce | 0.25 | 1.2775 | 0.31937 | H2 | 4 | Stable | 0.5 | 118 | 122 | 151 | 126.1667 | 0.4 | 29 | 50 | 79 | 51.3333 | 20 | 0 | 0 | 12
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-001 | Project_043_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Training Programme capacity | Person_336 | 2017-04-28 | 2018-11-20 01:00 | 0.15 | 0 | 0 | Reduce | 0.05 | 0 | 0 | H3 | 3 | Improving | 0.7 | 89 | 124 | 159 | 124 | 0.2 | 33 | 44 | 62 | 45.1667 |  | 66.6667 | 1
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-039 | Project_043_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System fails to achieve required performance | Person_051 | 2017-04-19 | 2018-11-20 01:00 | 0.3 | 4.7906 | 1.4372 | Reduce | 0.3 | 4.7906 | 1.4372 | H2 | 4 | Stable | 0.7 | 98 | 138 | 144 | 132.3333 | 0.1 | 12 | 57 | 73 | 52.1667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-21 01:00 | 2018-04-22 | 0.5 | 28.0275 | 14.0137 | Reduce | 0.1 | 28.0275 | 2.8027 | H3 | 3 | Stable | 0.6 | 86 | 137 | 156 | 131.6667 | 0.3 | 20 | 56 | 73 | 52.8333 | 0 | 80 | 1 | 2.4
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--35 | Project_021_Risk--35 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Delay to sub-system releases due to supply chain dependencies | Person_615 | 2018-01-21 01:00 | 2018-03-22 | 0.4 | 5.0032 | 3.5023 | Accept | 0.4 | 5.0032 | 3.5023 | H2 | 4 | Stable | 0.6 | 80 | 136 | 145 | 128.1667 | 0.6 | 80 | 136 | 145 | 128.1667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--34 | Project_021_Risk--34 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Delay due to poor weather | Person_615 | 2018-03-23 | 2018-06-22 | 0.5 | 18.4072 | 5.5222 | Accept | 0.5 | 18.4072 | 5.5222 | H2 | 4 | Stable | 0.8 | 94 | 140 | 158 | 135.3333 | 0.8 | 94 | 140 | 158 | 135.3333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--27 | Project_021_Risk--27 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PR rectification | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 0.1 | 3.4651 | 1.0395 | Accept | 0.1 | 3.4651 | 1.0395 | H2 | 4 | Stable | 0.7 | 107 | 123 | 153 | 125.3333 | 0.7 | 107 | 123 | 153 | 125.3333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--26 | Project_021_Risk--26 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional design effort required to satisfy SME feedback/input | Person_615 | 2018-01-21 01:00 | 2018-05-21 | 0.2 | 3.4651 | 1.0395 | Accept | 0.2 | 3.4651 | 1.0395 | H2 | 4 | Improving | 0.5 | 103 | 125 | 148 | 125.1667 | 0.5 | 103 | 125 | 148 | 125.1667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | EMC non compliance | Person_047 | 2016-06-23 | 2019-12-27 01:00 | 0.7 | 3.935 | 2.7545 | Reduce | 0.5 | 3.935 | 1.9675 | H2 | 4 | Stable | 0.5 | 103 | 125 | 142 | 124.1667 | 0.4 | 18 | 55 | 71 | 51.5 | 0 | 28.5714 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SubSystem System Design | Person_038 | 2017-10-01 01:00 | 2019-11-20 01:00 | 0.2 | 1.5213 | 0.30425 | Reduce | 0.1 | 1.5213 | 0.15213 | H3 | 3 | Stable | 0.7 | 85 | 126 | 153 | 123.6667 | 0.3 | 28 | 50 | 60 | 48 | 0 | 50 | 1 | 1.5
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK002 | Project_041_RISK002 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Component Technical risk using new material | Person_653 | 2017-09-20 01:00 | 2018-05-22 | 0.4 | 67.8016 | 27.1206 | Accept | 0.3 | 67.8016 | 27.1206 | H3 | 3 | Stable | 0.9 | 116 | 134 | 160 | 135.3333 | 0.9 | 116 | 134 | 160 | 135.3333 | 0 | 25 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK013 | Project_041_RISK013 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional components validation | Person_693 | 2017-07-15 | 2018-05-23 | 0.4 | 65.469 | 26.1876 | Accept | 0.3 | 65.469 | 26.1876 | H2 | 4 | Stable | 0.9 | 109 | 131 | 152 | 130.8333 | 0.9 | 109 | 131 | 152 | 130.8333 | 0 | 25 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Risk of not being able to perform Tests | Person_238 | 2017-12-21 01:00 | 2019-01-21 01:00 | 0.5 | 7.7077 | 1.5415 | Accept | 0.5 | 7.7077 | 1.5415 | H2 | 4 | Stable | 0.8 | 83 | 121 | 156 | 120.5 | 0.8 | 83 | 121 | 156 | 120.5 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production, Procurement or Engineering | Person_725 | 2018-01-21 01:00 | 2019-05-23 | 0.1 | 25.1514 | 12.5757 | Accept | 0.074 | 25.1514 | 12.5757 | H3 | 3 | Stable | 0.5 | 113 | 124 | 159 | 128 | 0.5 | 113 | 124 | 159 | 128 | 0 | 26 | 1 | 0.78
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-06-06 | 0.4 | 1.0142 | 0.40567 | Reduce | 0.1 | 1.0142 | 0.10142 | H3 | 3 | Stable | 0.7 | 103 | 123 | 153 | 124.6667 | 0.4 | 35 | 41 | 64 | 43.8333 | 0 | 75 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | 9. Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 0.8 | 19.1678 | 15.3343 | Reduce | 0.2 | 2.8752 | 0.57503 | H3 | 3 | Stable | 0.7 | 88 | 121 | 151 | 120.5 | 0.1 | 7 | 57 | 65 | 50 | 85 | 75 | 0 | 51
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_238 | 2017-05-23 | 2019-01-21 01:00 | 0.5 | 2.0043 | 1.0022 | Accept | 0.5 | 2.0043 | 1.0022 | H2 | 4 | Stable | 0.5 | 93 | 129 | 152 | 126.8333 | 0.5 | 93 | 129 | 152 | 126.8333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_547 | 2017-05-23 | 2018-06-22 | 0.1 | 0 | 0 | Accept | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.6 | 103 | 132 | 152 | 130.5 | 0.6 | 103 | 132 | 152 | 130.5 |  | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-06 01:00 | 2019-09-13 01:00 | 0.8 | 8.0322 | 6.4258 | Reduce | 0.5 | 4.006 | 2.003 | H2 | 4 | Stable | 0.5 | 94 | 122 | 160 | 123.6667 | 0.1 | 8 | 53 | 60 | 46.6667 | 50.1263 | 37.5 | 0 | 30.0758
2018-02-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-013 | Project_052_Risk-013 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional material and effort required to support the delta equipment | Person_376 | 2017-08-19 01:00 | 2020-08-20 01:00 | 0.3 | 1.2677 | 0.12677 | Accept | 0.3 | 1.2677 | 0.12677 | H3 | 3 | Stable | 0.8 | 103 | 125 | 160 | 127.1667 | 0.8 | 103 | 125 | 160 | 127.1667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-004 | Project_052_Risk-004 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | IOC Risk for Phase 1b | Person_488 | 2017-08-19 01:00 | 2018-04-21 | 0.1 | 5.5176 | 2.7588 | Accept | 0.1 | 5.5176 | 2.7588 | H3 | 3 | Stable | 0.9 | 96 | 130 | 144 | 126.6667 | 0.9 | 96 | 130 | 144 | 126.6667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK002 | Project_065_RISK002 | Opportunitity | Project Contingency | Open | H1 | 5 | 12. Acquisition and offsets | New supplier for enclosure | Person_598 | 2015-01-07 01:00 | 2017-10-19 01:00 | 0.05 | 9.6346 | 0.48173 | Exploit | 0.7 | 9.6346 | 6.7442 | H1 | 5 | Stable | [10 empty] | 0 | -1300 | 0 | 0
2018-02-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-001 | Project_052_Risk-001 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Greater modification than expected for system uplift | Person_376 | 2017-08-19 01:00 | 2018-03-22 | 0.1 | 1.7748 | 0.4437 | Accept | 0.1 | 1.7748 | 0.4437 | H3 | 3 | Stable | 0.7 | 113 | 137 | 145 | 134.3333 | 0.7 | 113 | 137 | 145 | 134.3333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier Selection Process | Person_379 | 2017-10-19 01:00 | 2019-04-23 | 0.4 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 100 | 133 | 153 | 130.8333 | 0.3 | 3 | 44 | 66 | 40.8333 |  | 25 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Colour Representation in Video Image Distortion | Person_305 | 2017-09-22 01:00 | 2020-03-21 | 0.5 | 5.5323 | 2.7662 | Reduce | 0.1 | 5.5323 | 0.55323 | H3 | 3 | Stable | 0.8 | 97 | 121 | 147 | 121.3333 | 0.4 | 8 | 47 | 60 | 42.6667 | 0 | 80 | 1 | 2.4
2018-02-20 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-009 | Project_052_Risk-009 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | System acceptance not costed in line with Customer expectations | Person_651 | 2017-08-19 01:00 | 2018-06-22 | 0.1 | 3.2479 | 0.64958 | Accept | 0.1 | 3.2479 | 0.64958 | H3 | 3 | Stable | 0.7 | 90 | 131 | 155 | 128.1667 | 0.7 | 90 | 131 | 155 | 128.1667 | 0 | 0 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-21 01:00 | 0.8 | 35.2369 | 28.1895 | Reduce | 0.3 | 18.4979 | 5.5494 | H2 | 4 | Stable | 0.8 | 92 | 123 | 149 | 122.1667 | 0.3 | 37 | 50 | 61 | 49.6667 | 47.5042 | 62.5 | 0 | 28.5025
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 4 | 9. Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-21 01:00 | 0.7 | 20.6835 | 14.4785 | Reduce | 0.3 | 20.6835 | 6.2051 | H2 | 4 | Stable | 0.9 | 95 | 130 | 154 | 128.1667 | 0.4 | 22 | 54 | 69 | 51.1667 | 0 | 57.1429 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 4 | 8. System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 0.6 | 5.2585 | 3.1551 | Reduce | 0.15 | 5.2585 | 0.78877 | H2 | 4 | Stable | 0.5 | 105 | 133 | 156 | 132.1667 | 0.1 | 32 | 53 | 71 | 52.5 | 0 | 75 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-085 | Project_043_Risk-085 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Failure of a product pre delivery | Person_359 | 2017-04-19 | 2018-04-21 | 0.25 | 7.7077 | 2.6977 | Accept | 0.25 | 7.7077 | 2.6977 | H2 | 4 | Improving | 0.6 | 112 | 129 | 157 | 130.8333 | 0.6 | 112 | 129 | 157 | 130.8333 | 0 | 0 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-04-21 | 0.3 | 2.723 | 0.81691 | Reduce | 0.1 | 2.723 | 0.2723 | H3 | 3 | Improving | 0.9 | 109 | 132 | 153 | 131.6667 | 0.2 | 12 | 58 | 61 | 50.8333 | 0 | 66.6667 | 1 | 2
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 0.2 | 4.8444 | 0.96888 | Reduce | 0.2 | 4.8444 | 0.96888 | H3 | 3 | Stable | 0.5 | 105 | 127 | 159 | 128.6667 | 0.2 | 39 | 43 | 69 | 46.6667 | 0 | 0 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System Performance | Person_305 | 2016-09-08 01:00 | 2020-09-21 01:00 | 0.15 | 5.8725 | 0.88088 | Reduce | 0.05 | 5.8725 | 0.29363 | H2 | 4 | Stable | 0.5 | 92 | 137 | 143 | 130.5 | 0.1 | 11 | 58 | 60 | 50.5 | 0 | 66.6667 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_038 | 2020-05-23 | 2023-10-26 01:00 | 0.2 | 7.4599 | 1.492 | Reduce | 0.05 | 7.4599 | 0.37299 | H2 | 4 | Stable | 0.7 | 98 | 121 | 153 | 122.5 | 0.1 | 6 | 45 | 62 | 41.3333 | 0 | 75 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-29 01:00 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.5 | 100 | 132 | 153 | 130.1667 | 0.3 | 24 | 53 | 68 | 50.6667 | 60.3671 | 58.3333 | 0 | 36.2202
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-20 01:00 | 0.4 | 2.8643 | 1.1457 | Reduce | 0.1 | 2.8643 | 0.28643 | H3 | 3 | Stable | 0.5 | 84 | 129 | 159 | 126.5 | 0.4 | 37 | 50 | 62 | 49.8333 | 0.0015933 | 75 | 1 | 2.251
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power Supply - Motor Controller Interface | Person_047 | 2016-05-23 | 2018-04-21 | 0.5 | 25.3543 | 12.6771 | Reduce | 0.2 | 25.3543 | 5.0709 | H3 | 3 | Stable | 0.8 | 80 | 136 | 143 | 127.8333 | 0.2 | 19 | 42 | 69 | 42.6667 | 0 | 60 | 1 | 1.8
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-23 | 2024-05-22 | 0.1 | 2.5488 | 0.89207 | Accept | 0.1 | 0 | 0 | H3 | 3 | Improving | 0.6 | 102 | 121 | 157 | 123.8333 | 0.6 | 102 | 121 | 157 | 123.8333 | 100 | 0 | 1 | 60
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Additional minor point release | Person_228 | 2016-05-23 | 2018-10-21 01:00 | 0.5 | 11.9444 | 5.9722 | Reduce | 0.25 | 11.9444 | 2.9861 | H2 | 4 | Stable | 0.5 | 92 | 124 | 148 | 122.6667 | 0.4 | 36 | 47 | 69 | 48.8333 | 0 | 50 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_228 | 2016-05-23 | 2018-08-20 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.6 | 92 | 121 | 147 | 120.5 | 0.1 | 28 | 45 | 65 | 45.5 | 0 | 50 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_004 | 2015-11-21 01:00 | 2018-11-20 01:00 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.8 | 89 | 125 | 160 | 124.8333 | 0.1 | 21 | 41 | 64 | 41.5 | 0 | 5 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.8 | 2.8043 | 2.2435 | Reduce | 0.45 | 2.8043 | 1.2619 | H1 | 5 | Stable | 0.5 | 116 | 136 | 142 | 133.6667 | 0.2 | 15 | 43 | 73 | 43.3333 | 0 | 43.75 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK167 | Project_024_RISK167 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Customer not providing the information needed or Customer not accepting the Customer documentation resulting in rewor. | Person_710 | 2016-08-21 01:00 | 2018-05-21 | 0.5 | 9.971 | 4.9855 | Reduce | 0.3 | 9.971 | 2.9913 | H1 | 5 | Worsening | 0.7 | 109 | 127 | 153 | 128.3333 | 0.3 | 12 | 55 | 63 | 49.1667 | 0 | 40 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK226 | Project_024_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Late Evidences Certification delivery | Person_642 | 2017-04-30 | 2018-05-21 | 0.4 | 3.9468 | 1.5787 | Reduce | 0.2 | 3.9468 | 0.78937 | H2 | 4 | Worsening | 0.5 | 83 | 137 | 150 | 130.1667 | 0.1 | 1 | 42 | 77 | 41 | 0 | 50 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.8 | 83 | 131 | 155 | 127 | 0.4 | 12 | 55 | 70 | 50.3333 | 0 | 60 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis and Security | Person_288 | 2017-02-22 01:00 | 2018-08-20 | 0.3 | 19.9938 | 5.9981 | Reduce | 0.04675 | 19.9938 | 0.93471 | H3 | 3 | Improving | 0.7 | 96 | 136 | 160 | 133.3333 | 0.4 | 22 | 55 | 71 | 52.1667 | 0 | 84.4167 | 1 | 2.5325
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.2 | 3.843 | 0.76859 | H2 | 4 | Stable | 0.6 | 92 | 137 | 143 | 130.5 | 0.1 | 31 | 42 | 72 | 45.1667 | 0 | 60 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Performance (collector opportunity) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.373 | 19.5316 | 7.2853 | -- | 0.4158 | 19.5316 | 8.1213 | H1 | 5 | Stable | [10 empty] | 0 | -11.4745 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.3 | 20.8767 | 6.263 | H1 | 5 | Stable | 0.6 | 106 | 140 | 155 | 136.8333 | 0.3 | 19 | 42 | 64 | 41.8333 | 50 | 25 | 0 | 30
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.504 | 73.3644 | 36.9756 | Reduce | 0.0852 | 53.773 | 4.5815 | H2 | 4 | Worsening | 0.8 | 95 | 128 | 145 | 125.3333 | 0.2 | 5 | 41 | 79 | 41.3333 | 26.7042 | 83.0952 | 0 | 16.0225
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK308 | Project_024_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System robustness and resilience | Person_774 | 2017-04-06 | 2018-06-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.1 | 2.5966 | 0.25966 | H3 | 3 | Stable | 0.8 | 107 | 132 | 151 | 131 | 0.4 | 39 | 40 | 72 | 45.1667 | 58.3333 | 66.6667 | 1 | 37
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-117 | Project_043_Risk-117 | Threat | Project Contingency | Open | H1 | 5 | 6. Contractual/Legal | Supplier Technical Publications maturity not at the level required | Person_769 | 2017-04-19 | 2018-05-13 | 0.45 | 1.7366 | 0.78146 | Reduce | 0.45 | 1.7366 | 0.78146 | H1 | 5 | Improving | 0.9 | 109 | 137 | 156 | 135.5 | 0.4 | 32 | 56 | 61 | 52.8333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-111 | Project_043_Risk-111 | Opportunitity | Project Contingency | Open | H1 | 5 | 7. Finance | Decrease the cost of obsolescence sweeps | Person_769 | 2018-01-11 | 2020-12-21 | 0.5 | 0.038325 | 0.019162 | Exploit | 0.5 | 0.038325 | 0.019162 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-113 | Project_043_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | No Gen 1 products available, transition cost to Gen 2 | Person_769 | 2017-04-19 | 2020-12-21 | 0.3 | 1.4971 | 0.44912 | Reduce | 0.3 | 1.4971 | 0.44912 | H2 | 4 | Stable | 0.6 | 108 | 125 | 143 | 125.1667 | 0.4 | 13 | 42 | 61 | 40.3333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-121 | Project_043_Risk-121 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | More Tech Pubs Update than estimated | Person_769 | 2019-01-21 | 2020-10-20 | 0.45 | 1.7366 | 0.78146 | Reduce | 0.45 | 1.7366 | 0.78146 | H1 | 5 | Stable | 0.7 | 81 | 132 | 160 | 128.1667 | 0.2 | 16 | 43 | 69 | 42.8333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-084 | Project_043_Risk-084 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | complex repair ( over and above the forecast average) | Person_368 | 2017-12-21 | 2020-12-21 | 0.2 | 0.71859 | 0.14372 | Reduce | 0.2 | 0.71859 | 0.14372 | H2 | 4 | Stable | 0.9 | 108 | 136 | 144 | 132.6667 | 0.3 | 20 | 59 | 69 | 54.1667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-128 | Project_043_Risk-128 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Reliance of Customer Avaliability | Person_135 | 2017-04-19 | 2018-08-21 | 0.5 | 1.7665 | 0.88326 | Reduce | 0.5 | 1.7665 | 0.88326 | H1 | 5 | Stable | 0.7 | 120 | 131 | 152 | 132.6667 | 0.4 | 6 | 41 | 75 | 40.8333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-089 | Project_043_Risk-089 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares pool is limited | Person_307 | 2018-12-22 | 2020-12-21 | 0.25 | 1.5969 | 0.39921 | Reduce | 0.25 | 1.2775 | 0.31937 | H2 | 4 | Stable | 0.5 | 111 | 138 | 143 | 134.3333 | 0.4 | 29 | 55 | 65 | 52.3333 | 20 | 0 | 0 | 12
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-001 | Project_043_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Training Programme capacity | Person_336 | 2017-04-28 | 2018-11-20 | 0.15 | 0 | 0 | Reduce | 0.05 | 0 | 0 | H3 | 3 | Improving | 0.5 | 114 | 126 | 146 | 127.3333 | 0.3 | 1 | 41 | 66 | 38.5 |  | 66.6667 | 1
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-039 | Project_043_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System fails to achieve required performance | Person_051 | 2017-04-19 | 2018-11-20 | 0.3 | 4.7906 | 1.4372 | Reduce | 0.3 | 4.7906 | 1.4372 | H2 | 4 | Stable | 0.7 | 89 | 123 | 156 | 122.8333 | 0.4 | 25 | 59 | 71 | 55.3333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK024 | Project_063_RISK024 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Procurement/Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 0.8 | 0 | 0 | -- | 0.8 | 0 | 0 | H1 | 5 | Worsening | [11 empty] | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK022 | Project_063_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Equipment | Person_104 | 2018-01-14 01:00 | 2019-08-20 | 0.15 | 2.3618 | 0.35427 | -- | 0.15 | 2.3618 | 0.35427 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK004 | Project_063_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 2.861 | 0.57221 | Reduce | 0.15 | 2.861 | 0.42915 | H3 | 3 | Stable | 0.9 | 81 | 138 | 153 | 131 | 0.3 | 26 | 40 | 64 | 41.6667 | 0 | 25 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK014 | Project_063_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 0.1 | 8.3527 | 0.83527 | Avoid | 0.05 | 7.0086 | 0.35043 | H3 | 3 | Stable | [10 empty] | 16.092 | 50 | 0 | 9.6552
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK003 | Project_060_RISK003 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Misalignment of Critical Resource | Person_312 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.7 | 11.7303 | 8.2112 | Reduce | 0.5 | 11.7303 | 5.8651 | H1 | 5 | Stable | 0.5 | 83 | 126 | 159 | 124.3333 | 0.3 | 37 | 44 | 77 | 48.3333 | 0 | 28.5714 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK017 | Project_063_RISK017 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Increased build rate | Person_683 | 2017-11-12 01:00 | 2019-08-21 01:00 | 0.5 | 21.6065 | 10.8033 | -- | 0.5 | 21.6065 | 10.8033 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK004 | Project_060_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Cross-functional Estimates | Person_729 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.7 | 2.8845 | 2.0191 | Reduce | 0.5 | 2.8845 | 1.4422 | H2 | 4 | Worsening | 0.9 | 94 | 130 | 153 | 127.8333 | 0.3 | 10 | 52 | 65 | 47.1667 | 0 | 28.5714 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK005 | Project_063_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 1.214 | 0.72839 | -- | 0.5 | 1.214 | 0.60699 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK016 | Project_063_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.2 | 0.63077 | 0.12615 | -- | 0.2 | 0.63077 | 0.12615 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK001 | Project_060_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Procurement Prices | Person_033 | 2017-11-02 01:00 | 2018-08-20 | 0.7 | 1.4422 | 1.0096 | Transfer | 0.7 | 1.4422 | 1.0096 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK002 | Project_063_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2020-05-22 | 0.15 | 8.6407 | 1.2961 | Avoid | 0.15 | 8.6407 | 1.2961 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK012 | Project_063_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Customer require additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.1 | 6.0485 | 0.60485 | Avoid | 0.1 | 6.0485 | 0.60485 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK018 | Project_063_RISK018 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Line Closure | Person_683 | 2019-08-21 01:00 | 2019-11-20 01:00 | 0.5 | 1.9058 | 0.95288 | -- | 0.5 | 4.3203 | 2.1602 | H2 | 4 | Improving | [10 empty] | -126.7001 | 0 | 0 | -76.0201
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | R054 | Project_066_R054 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | System Cybersecurity shortfalls | Person_549 | 2016-05-23 | 2024-05-23 | 0.8 | 15.7936 | 12.6349 | Reduce | 0.5 | 15.7936 | 7.8968 | H1 | 5 | Stable | 0.7 | 108 | 139 | 144 | 134.6667 | 0.1 | 15 | 57 | 76 | 53.1667 | 0 | 37.5 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | FOC Acceptance | Person_499 | 2018-05-23 | 2018-07-21 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.15 | 8.471 | 1.2706 | H3 | 3 | Stable | 0.7 | 113 | 129 | 157 | 131 | 0.2 | 35 | 43 | 79 | 47.6667 | -99.9999 | 57.1429 | 1 | -58.2857
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK003 | Project_024_RISK003 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance | Person_288 | 2017-12-21 01:00 | 2018-08-21 | 0.31667 | 2.7703 | 1.3852 | Accept | 0.04388 | 2.7703 | 1.3852 | H2 | 4 | Stable | 0.8 | 93 | 132 | 155 | 129.3333 | 0.8 | 93 | 132 | 155 | 129.3333 | 0 | 86.1432 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before part b finished | Person_119 | 2016-10-20 01:00 | 2018-05-21 | 0.3 | 8.8305 | 2.6492 | Accept | 0.27 | 8.8305 | 2.6492 | H2 | 4 | Worsening | 0.6 | 86 | 127 | 143 | 122.8333 | 0.6 | 86 | 127 | 143 | 122.8333 | 0 | 10 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-085 | Project_043_Risk-085 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Failure of a product pre delivery | Person_359 | 2017-04-19 | 2018-04-21 | 0.25 | 1.4099 | 0.42298 | Accept | 0.25 | 1.4099 | 0.42298 | H2 | 4 | Improving | 0.5 | 106 | 127 | 150 | 127.3333 | 0.5 | 106 | 127 | 150 | 127.3333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-20 22:00 | 2017-08-19 22:00 | 0.1 | 53.0293 | 5.3029 | Reduce | 0.1 | 53.0293 | 5.3029 | H3 | 3 | Stable | 0.6 | 97 | 133 | 159 | 131.3333 | 0.4 | 33 | 56 | 70 | 54.5 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-20 22:00 | 2017-08-19 22:00 | 0.1 | 7.7469 | 0.77469 | Reduce | 0.1 | 7.7469 | 0.77469 | H3 | 3 | Stable | 0.6 | 96 | 126 | 158 | 126.3333 | 0.2 | 27 | 52 | 73 | 51.3333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK006 | Project_060_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Secure material Handling | Person_033 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.5 | 12.1204 | 12.1204 | Accept | 0.5 | 12.1204 | 12.1204 | H2 | 4 | Stable | 0.5 | 103 | 139 | 141 | 133.3333 | 0.5 | 103 | 139 | 141 | 133.3333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK024 | Project_048_RISK024 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Procurement/Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 0.8 | 0 | 0 | -- | 0.8 | 0 | 0 | H1 | 5 | Worsening | [11 empty] | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK017 | Project_048_RISK017 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Increased build rate | Person_683 | 2017-11-12 01:00 | 2019-08-21 01:00 | 0.5 | 7.7433 | 3.8716 | -- | 0.5 | 7.7433 | 3.8716 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Interface implementation | Person_496 | 2018-05-23 | 2018-07-21 | 0.5 | 5.126 | 2.563 | Accept | 0.25 | 5.126 | 2.563 | H2 | 4 | Stable | 0.8 | 120 | 140 | 151 | 138.5 | 0.8 | 120 | 140 | 151 | 138.5 | 0 | 50 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK016 | Project_048_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.2 | 0.22605 | 0.045211 | -- | 0.2 | 0.22605 | 0.045211 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of the platforms for modification | Person_496 | 2014-01-21 01:00 | 2019-04-10 | 0.67 | 6.3794 | 1.2759 | Accept | 0.67 | 6.3794 | 1.2759 | H2 | 4 | Stable | 0.6 | 86 | 137 | 155 | 131.5 | 0.6 | 86 | 137 | 155 | 131.5 | 0 | 0 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK018 | Project_048_RISK018 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Line Closure | Person_683 | 2019-08-21 01:00 | 2019-11-20 01:00 | 0.5 | 0.68298 | 0.34149 | -- | 0.5 | 1.5483 | 0.77415 | H2 | 4 | Improving | [10 empty] | -126.7001 | 0 | 0 | -76.0201
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_676 | 2016-08-21 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.7 | 81 | 124 | 155 | 122 | 0.1 | 19 | 52 | 74 | 50.1667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_523 | 2018-05-23 | 2018-07-21 | 0.35 | 0.60622 | 0.18186 | Accept | 0.2 | 0.60622 | 0.18186 | H2 | 4 | Stable | 0.8 | 96 | 139 | 146 | 133 | 0.8 | 96 | 139 | 146 | 133 | 0 | 42.8571 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_676 | 2016-08-21 | 2017-08-21 | 0.5 | 37.5906 | 18.7953 | Reduce | 0.15 | 37.5906 | 5.6386 | H3 | 3 | Stable | 0.6 | 116 | 122 | 145 | 124.8333 | 0.1 | 11 | 49 | 66 | 45.5 | 0 | 70 | 1 | 2.1
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK004 | Project_048_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 1.0253 | 0.20506 | Reduce | 0.15 | 1.0253 | 0.1538 | H3 | 3 | Stable | 0.9 | 113 | 125 | 144 | 126.1667 | 0.1 | 32 | 56 | 79 | 55.8333 | 0 | 25 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK014 | Project_048_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 0.1 | 2.9934 | 0.29934 | Avoid | 0.05 | 2.5117 | 0.12558 | H3 | 3 | Stable | [10 empty] | 16.092 | 50 | 0 | 9.6552
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-184 | Project_032_Risk-184 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Manufacture of new Sub-systems | Person_629 | 2016-04-08 | 2018-02-18 22:00 | 0.33 | 5.4336 | 1.3584 | Accept | 0.5 | 5.4336 | 1.3584 | H1 | 5 | Stable | 0.6 | 96 | 136 | 143 | 130.5 | 0.6 | 96 | 136 | 143 | 130.5 | 0 | -51.5152 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK005 | Project_048_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 0.43506 | 0.26104 | Avoid | 0.5 | 0.43506 | 0.21753 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK002 | Project_048_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2020-05-22 | 0.15 | 3.0966 | 0.46449 | Avoid | 0.15 | 3.0966 | 0.46449 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-20 23:00 | 2020-08-19 23:00 | 0.5 | 1.7836 | 0.53509 | Accept | 0.5 | 1.7836 | 0.53509 | H2 | 4 | Stable | 0.9 | 105 | 127 | 143 | 126 | 0.9 | 105 | 127 | 143 | 126 | 0 | 0 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK012 | Project_048_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Customer require additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.1 | 2.1676 | 0.21676 | Avoid | 0.1 | 2.1676 | 0.21676 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK022 | Project_048_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Equipment | Person_104 | 2018-01-14 01:00 | 2019-08-20 | 0.15 | 0.84641 | 0.12696 | -- | 0.15 | 0.84641 | 0.12696 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-19 22:00 | 0.05 | 3.7727 | 2.6409 | Accept | 0.05 | 3.772 | 2.6404 | H3 | 3 | Stable | 0.5 | 82 | 136 | 142 | 128 | 0.5 | 82 | 136 | 142 | 128 | 0.019757 | 0 | 1 | 0.011854
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 5.8198 | 4.0739 | Accept | 0.5 | 5.8198 | 4.0739 | H2 | 4 | Stable | 0.7 | 86 | 130 | 154 | 126.6667 | 0.7 | 86 | 130 | 154 | 126.6667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_009 | Project_051 | RISK001 | Project_051_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Generic Labour or Material Overspend | Person_577 | 2012-05-23 | 2021-05-22 | 0.5 | 1.6166 | 0.32332 | Accept | 0.5 | 1.6166 | 0.32332 | H3 | 3 | Stable | 0.8 | 83 | 137 | 146 | 129.5 | 0.8 | 83 | 137 | 146 | 129.5 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | R181 | Project_066_R181 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | USB Hub start up issues | Person_247 | 2016-05-23 | 2024-05-23 | 1 | 2.0207 | 0.40414 | Accept | 1 | 2.0207 | 0.40414 | H2 | 4 | Stable | 0.8 | 117 | 124 | 152 | 127.5 | 0.8 | 117 | 124 | 152 | 127.5 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-04-20 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.7 | 93 | 135 | 147 | 130 | 0.2 | 38 | 49 | 61 | 49.1667 | 0 | 25 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS020 | Project_025_RS020 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Plant Machinery failure | Person_619 | 2017-03-23 | 2019-08-07 | 0.3 | 0.05293 | 0.015879 | Reduce | 0.3 | 0.05293 | 0.015879 | H2 | 4 | Stable | 0.9 | 101 | 128 | 155 | 128 | 0.2 | 2 | 46 | 73 | 43.1667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS019 | Project_025_RS019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Product Component Failure | Person_619 | 2017-03-23 | 2019-08-07 | 0.7 | 0.82924 | 0.58047 | Reduce | 0.3 | 0.82924 | 0.24877 | H2 | 4 | Stable | 0.6 | 90 | 126 | 146 | 123.3333 | 0.4 | 25 | 58 | 77 | 55.6667 | 0 | 57.1429 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_373 | 2012-08-21 01:00 | 2019-08-07 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 2.2054 | 1.3453 | H1 | 5 | Stable | 0.8 | 111 | 135 | 141 | 132 | 0.3 | 11 | 44 | 78 | 44.1667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_676 | 2016-10-21 | 2019-08-20 | 0.5 | 0 | 0 | Accept | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.6 | 94 | 129 | 149 | 126.5 | 0.6 | 94 | 129 | 149 | 126.5 |  | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_676 | 2016-08-21 | 2019-08-20 | 0.2 | 0 | 0 | Accept | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.8 | 105 | 135 | 143 | 131.3333 | 0.8 | 105 | 135 | 143 | 131.3333 |  | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--17 | Project_021_Risk--17 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to technical performance | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.8 | 100 | 139 | 157 | 135.5 | 0.2 | 19 | 40 | 67 | 41 |  | 33.3333 | 1
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--39 | Project_021_Risk--39 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Delay to completion of product upgrade | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 107 | 134 | 149 | 132 | 0.4 | 25 | 47 | 63 | 46 |  | 40 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--16 | Project_021_Risk--16 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of weather | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.8 | 113 | 122 | 156 | 126.1667 | 0.4 | 15 | 48 | 70 | 46.1667 |  | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--15 | Project_021_Risk--15 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to lack of personnel resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.6 | 102 | 133 | 141 | 129.1667 | 0.1 | 12 | 43 | 79 | 43.8333 |  | 33.3333 | 1
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--14 | Project_021_Risk--14 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to late Trials Approval | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 106 | 129 | 148 | 128.3333 | 0.2 | 2 | 40 | 68 | 38.3333 |  | 66.6667 | 1
2018-03-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_077 | 2016-01-22 01:00 | 2018-04-18 | 0.15 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Improving | 0.8 | 110 | 139 | 151 | 136.1667 | 0.3 | 10 | 51 | 61 | 45.8333 |  | 0 | 0
2018-03-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2018-10-21 01:00 | 0.05 | 0 | 0 | Accept | 0.05 | 0 | 0 | H3 | 3 | Improving | 0.6 | 94 | 134 | 147 | 129.5 | 0.6 | 94 | 134 | 147 | 129.5 |  | 0 | 1
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--13 | Project_021_Risk--13 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Critical or Safety PR arises in Final build /Decision Point concludes new release req | Person_174 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.9 | 90 | 125 | 152 | 123.6667 | 0.1 | 17 | 51 | 64 | 47.5 | 0 | 50 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--12 | Project_021_Risk--12 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.5 | 94 | 131 | 142 | 126.6667 | 0.4 | 16 | 53 | 78 | 51 | 0 | 33.3333 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_676 | 2016-08-21 | 2019-08-20 | 0.35 | 0 | 0 | Accept | 0.35 | 0 | 0 | H3 | 3 | Stable | 0.7 | 115 | 140 | 145 | 136.6667 | 0.7 | 115 | 140 | 145 | 136.6667 |  | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--11 | Project_021_Risk--11 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.7 | 106 | 138 | 150 | 134.6667 | 0.4 | 10 | 40 | 68 | 39.6667 | 7.8429 | 40 | 0 | 4.7058
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--10 | Project_021_Risk--10 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Stable | 0.8 | 90 | 137 | 158 | 132.6667 | 0.2 | 8 | 44 | 65 | 41.5 | 0 | 57.1429 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--32 | Project_021_Risk--32 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Lack of Customer resource to provide timely to Acceptance and Closure activities | Person_766 | 2018-10-22 01:00 | 2019-04-23 | 0.8 | 0 | 0 | Reduce | 0.4 | 0 | 0 | H2 | 4 | Stable | 0.9 | 98 | 130 | 143 | 126.8333 | 0.2 | 30 | 41 | 77 | 45.1667 |  | 50 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--18 | Project_021_Risk--18 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.6 | 120 | 138 | 154 | 137.6667 | 0.4 | 8 | 45 | 64 | 42 | 50 | 28.5714 | 0 | 30
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--28 | Project_021_Risk--28 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort required to agree protocl for Client Server | Person_766 | 2018-03-23 | 2019-03-23 | 0.8 | 1.1522 | 0.92174 | Reduce | 0.4 | 1.1522 | 0.46087 | H2 | 4 | Stable | 0.5 | 103 | 131 | 142 | 128.1667 | 0.1 | 23 | 44 | 62 | 43.5 | 0 | 50 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--05 | Project_021_Risk--05 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification delays | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Worsening | 0.7 | 118 | 132 | 157 | 133.8333 | 0.1 | 5 | 51 | 69 | 46.3333 |  | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--04 | Project_021_Risk--04 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Final Qual test report delayed due to insufficient supply chain resource | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 0.2 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.9 | 94 | 121 | 141 | 119.8333 | 0.1 | 16 | 54 | 63 | 49.1667 |  | 50 | 1
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--03 | Project_021_Risk--03 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.7 | 104 | 132 | 142 | 129 | 0.4 | 29 | 50 | 63 | 48.6667 | 0 | 33.3333 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--25 | Project_021_Risk--25 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of supporting resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.5 | 98 | 127 | 150 | 126 | 0.2 | 20 | 47 | 77 | 47.5 |  | 40 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--02 | Project_021_Risk--02 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_061 | 2018-02-20 01:00 | 2019-03-23 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.7 | 99 | 140 | 157 | 136 | 0.4 | 2 | 45 | 79 | 43.5 | 80 | 66.6667 | 0 | 48
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--24 | Project_021_Risk--24 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of equipment | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 113 | 140 | 155 | 138 | 0.2 | 34 | 41 | 79 | 46.1667 |  | 40 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--01 | Project_021_Risk--01 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification/ delay due to build standard issue | Person_615 | 2018-02-20 01:00 | 2018-06-22 | 0.1 | 2.2183 | 0.22183 | Reduce | 0.05 | 2.2183 | 0.11091 | H2 | 4 | Stable | 0.8 | 114 | 138 | 146 | 135.3333 | 0.1 | 12 | 40 | 61 | 38.8333 | 0 | 50 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--21 | Project_021_Risk--21 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 105 | 137 | 155 | 134.6667 | 0.2 | 17 | 43 | 63 | 42 |  | 40 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--09 | Project_021_Risk--09 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 98 | 130 | 157 | 129.1667 | 0.4 | 19 | 59 | 77 | 55.3333 |  | 40 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--08 | Project_021_Risk--08 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H3 | 3 | Stable | 0.9 | 92 | 124 | 157 | 124.1667 | 0.4 | 28 | 54 | 69 | 52.1667 |  | 62.5 | 1
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--07 | Project_021_Risk--07 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 0.6 | 17.2826 | 10.3696 | Reduce | 0.3 | 17.2826 | 5.1848 | H2 | 4 | Worsening | 0.5 | 97 | 140 | 151 | 134.6667 | 0.3 | 29 | 52 | 63 | 50 | 0 | 50 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--20 | Project_021_Risk--20 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | ERP implementation | Person_061 | 2018-01-21 01:00 | 2018-07-20 | 0.5 | 0 | 0 | Reduce | 0.25 | 0 | 0 | H2 | 4 | Stable | 0.7 | 95 | 127 | 156 | 126.5 | 0.3 | 21 | 52 | 62 | 48.5 |  | 50 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_676 | 2016-08-21 | 2019-08-20 | 0.25 | 0.56365 | 0.11273 | Accept | 0.25 | 0.28182 | 0.028182 | H3 | 3 | Stable | 0.6 | 83 | 130 | 160 | 127.1667 | 0.6 | 83 | 130 | 160 | 127.1667 | 50 | 0 | 0 | 30
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK044 | Project_042_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2018-02-20 01:00 | 2018-12-21 01:00 | 0.32 | 6.5759 | 2.1043 | Reduce | 0.17 | 6.5759 | 1.1179 | H2 | 4 | Stable | 0.8 | 118 | 122 | 145 | 125.1667 | 0.3 | 19 | 46 | 63 | 44.3333 | 0 | 46.875 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK024 | Project_042_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2019-09-21 01:00 | 2020-09-19 01:00 | 0.33 | 9.3941 | 3.1001 | Reduce | 0.15 | 7.5153 | 1.1273 | H2 | 4 | Stable | 0.8 | 84 | 140 | 150 | 132.3333 | 0.1 | 33 | 54 | 78 | 54.5 | 20 | 54.5455 | 0 | 12
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK045 | Project_042_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2019-01-22 01:00 | 2019-05-23 | 0.25 | 3.908 | 0.97699 | Reduce | 0.25 | 3.908 | 0.97699 | H2 | 4 | Stable | 0.5 | 104 | 133 | 150 | 131 | 0.4 | 1 | 43 | 67 | 40 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--35 | Project_021_Risk--35 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Delay to sub-system releases due to supply chain dependencies | Person_615 | 2018-01-21 01:00 | 2018-03-22 | 0.4 | 0.79775 | 0.039887 | Accept | 0.4 | 0.79775 | 0.039887 | H2 | 4 | Stable | 0.8 | 110 | 136 | 142 | 132.6667 | 0.8 | 110 | 136 | 142 | 132.6667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--34 | Project_021_Risk--34 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Delay due to poor weather | Person_615 | 2018-03-23 | 2018-06-22 | 0.5 | 10.3335 | 1.0334 | Accept | 0.5 | 10.3335 | 1.0334 | H2 | 4 | Stable | 0.7 | 80 | 140 | 145 | 130.8333 | 0.7 | 80 | 140 | 145 | 130.8333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--27 | Project_021_Risk--27 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PR rectification | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 0.1 | 11.2729 | 2.2546 | Accept | 0.1 | 11.2729 | 2.2546 | H2 | 4 | Stable | 0.5 | 119 | 138 | 153 | 137.3333 | 0.5 | 119 | 138 | 153 | 137.3333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--26 | Project_021_Risk--26 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional design effort required to satisfy SME feedback/input | Person_615 | 2018-01-21 01:00 | 2018-05-21 | 0.2 | 3.7576 | 0.18788 | Accept | 0.2 | 3.7576 | 0.56365 | H2 | 4 | Improving | 0.9 | 113 | 133 | 141 | 131 | 0.9 | 113 | 133 | 141 | 131 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK047 | Project_042_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables | Person_455 | 2020-11-20 01:00 | 2021-05-22 | 0.2 | 1.8788 | 0.46971 | Accept | 0.1 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.5 | 93 | 130 | 151 | 127.3333 | 0.5 | 93 | 130 | 151 | 127.3333 | 20 | 50 | 0 | 12
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK048 | Project_042_RISK048 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | On the Job Training. | Person_371 | 2018-03-02 01:00 | 2019-02-05 01:00 | 0.85 | 2.1043 | 1.7886 | Reduce | 0.5 | 2.1043 | 1.0521 | H1 | 5 | Stable | 0.7 | 119 | 139 | 143 | 136.3333 | 0.3 | 38 | 42 | 61 | 44.5 | 0 | 41.1765 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK022 | Project_042_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2017-09-20 01:00 | 2018-09-20 01:00 | 0.2 | 4.6971 | 0.93941 | Accept | 0.18 | 3.7576 | 0.56365 | H2 | 4 | Stable | 0.5 | 120 | 121 | 144 | 124.6667 | 0.5 | 120 | 121 | 144 | 124.6667 | 20 | 10 | 0 | 12
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK043 | Project_042_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st December | Person_455 | 2021-03-23 | 2021-05-22 | 0.1 | 1.8788 | 0.46971 | Accept | 0.08 | 1.5031 | 0.22546 | H3 | 3 | Stable | 0.5 | 114 | 134 | 160 | 135 | 0.5 | 114 | 134 | 160 | 135 | 20 | 20 | 1 | 12.6
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK049 | Project_042_RISK049 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Industry STTE Upkeep. | Person_371 | 2018-03-02 01:00 | 2019-02-05 01:00 | 0.85 | 1.3152 | 1.1179 | Reduce | 0.5 | 1.3152 | 0.65759 | H2 | 4 | Stable | 0.6 | 88 | 136 | 147 | 129.8333 | 0.1 | 18 | 44 | 71 | 44.1667 | 0 | 41.1765 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK046 | Project_042_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables - June | Person_455 | 2018-11-21 01:00 | 2020-11-19 01:00 | 0.2 | 1.8788 | 0.46971 | Accept | 0.1 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.6 | 103 | 140 | 154 | 136.1667 | 0.6 | 103 | 140 | 154 | 136.1667 | 20 | 50 | 0 | 12
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK023 | Project_042_RISK023 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2018-09-21 01:00 | 2019-09-20 01:00 | 0.2 | 2.2828 | 0.31959 | Accept | 0.1 | 2.2828 | 0.31959 | H2 | 4 | Stable | 0.6 | 106 | 133 | 149 | 131.1667 | 0.6 | 106 | 133 | 149 | 131.1667 | 0 | 50 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK029 | Project_042_RISK029 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st October to 31st December | Person_455 | 2020-11-20 01:00 | 2021-05-22 | 0.25 | 2.6585 | 0.66463 | Accept | 0.1 | 2.6585 | 0.66463 | H2 | 4 | Stable | 0.8 | 80 | 121 | 159 | 120.5 | 0.8 | 80 | 121 | 159 | 120.5 | 0 | 60 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK036 | Project_042_RISK036 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 2 | Person_455 | 2019-05-24 | 2020-05-22 | 0.25 | 1.593 | 0.79649 | Accept | 0.2 | 0 | 0 | H2 | 4 | Stable | 0.8 | 100 | 138 | 155 | 134.5 | 0.8 | 100 | 138 | 155 | 134.5 | 100 | 20 | 0 | 60
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK039 | Project_042_RISK039 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality Issues 16th August to 15th August | Person_540 | 2020-01-06 01:00 | 2021-01-04 01:00 | 0.1 | 3.186 | 1.593 | Accept | 0.08 | 0 | 0 | H2 | 4 | Stable | 0.8 | 85 | 136 | 157 | 131 | 0.8 | 85 | 136 | 157 | 131 | 100 | 20 | 0 | 60
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK033 | Project_042_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st April to 30 June | Person_455 | 2019-08-22 01:00 | 2019-11-20 01:00 | 0.2 | 0.19116 | 0.038232 | Accept | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.5 | 96 | 135 | 155 | 131.8333 | 0.5 | 96 | 135 | 155 | 131.8333 | 100 | 25 | 0 | 60
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK035 | Project_042_RISK035 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st October to 31st December | Person_455 | 2021-02-20 01:00 | 2021-05-22 | 0.2 | 3.1541 | 1.2616 | Accept | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.5 | 89 | 123 | 151 | 122 | 0.5 | 89 | 123 | 151 | 122 | 100 | 25 | 0 | 60
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK034 | Project_042_RISK034 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st July to 30 September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 0.2 | 3.8232 | 1.3381 | Accept | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.9 | 92 | 129 | 158 | 127.6667 | 0.9 | 92 | 129 | 158 | 127.6667 | 100 | 25 | 0 | 60
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK040 | Project_042_RISK040 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st May to 30 Oct | Person_455 | 2019-09-21 01:00 | 2020-03-21 | 0.1 | 1.2744 | 0.63719 | Accept | 0.07 | 0 | 0 | H2 | 4 | Stable | 0.8 | 107 | 125 | 142 | 124.8333 | 0.8 | 107 | 125 | 142 | 124.8333 | 100 | 30 | 0 | 60
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK042 | Project_042_RISK042 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st February to 14th July | Person_455 | 2020-06-23 | 2020-12-03 01:00 | 0.1 | 2.5488 | 0.89207 | Accept | 0.08 | 0 | 0 | H2 | 4 | Stable | 0.8 | 85 | 139 | 149 | 131.6667 | 0.8 | 85 | 139 | 149 | 131.6667 | 100 | 20 | 0 | 60
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK041 | Project_042_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st Jan | Person_455 | 2020-03-23 | 2020-06-22 | 0.1 | 0.82835 | 0.49701 | Accept | 0.08 | 0 | 0 | H2 | 4 | Stable | 0.6 | 95 | 121 | 145 | 120.6667 | 0.6 | 95 | 121 | 145 | 120.6667 | 100 | 20 | 0 | 60
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Local customer Engineers in country | Person_455 | 2018-12-20 01:00 | 2021-05-22 | 0.05 | 0 | 0 | Accept | 0.05 | 0 | 0 | H2 | 4 | Stable | 0.9 | 92 | 123 | 154 | 123 | 0.9 | 92 | 123 | 154 | 123 |  | 0 | 0
2018-03-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK044 | Project_053_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Product Hardening | Person_719 | 2018-03-23 | 2019-01-20 01:00 | 0.3 | 7.9015 | 2.3705 | Avoid | 0.3 | 7.9015 | 2.3705 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK026 | Project_042_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st Jan to 31st March | Person_455 | 2020-05-23 | 2020-08-20 01:00 | 0.25 | 4.4955 | 0.44955 | Accept | 0.15 | 4.4955 | 0.44955 | H2 | 4 | Stable | 0.7 | 91 | 137 | 148 | 131.1667 | 0.7 | 91 | 137 | 148 | 131.1667 | 0 | 40 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK025 | Project_042_RISK025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to 31 Dec | Person_455 | 2020-09-20 01:00 | 2021-05-22 | 0.2 | 2.2986 | 1.1493 | Accept | 0.15 | 2.2986 | 0.45973 | H2 | 4 | Stable | 0.5 | 90 | 127 | 154 | 125.3333 | 0.5 | 90 | 127 | 154 | 125.3333 | 0 | 25 | 0 | 0
2018-03-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK015 | Project_053_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Equipment export licences | Person_252 | 2018-06-23 | 2019-07-22 | 0.3 | 2.586 | 0.77579 | Avoid | 0.1 | 2.586 | 0.2586 | H3 | 3 | Improving | [10 empty] | 0 | 66.6667 | 1 | 2
2018-03-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK006 | Project_053_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional UK integration of the System product | Person_719 | 2018-10-22 01:00 | 2019-01-21 01:00 | 0.2 | 6.3212 | 1.2642 | Avoid | 0.2 | 6.3212 | 1.2642 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 1 | 0
2018-03-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK005 | Project_053_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier Deiivery Schedule | Person_252 | 2018-01-21 01:00 | 2018-11-20 01:00 | 0.5 | 5.3299 | 2.665 | Reduce | 0.25 | 5.3299 | 1.3325 | H2 | 4 | Stable | 0.8 | 103 | 134 | 156 | 132.5 | 0.4 | 12 | 49 | 60 | 44.6667 | 0 | 50 | 0 | 0
2018-03-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK010 | Project_053_RISK010 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Immaturity of the core product | Person_719 | 2018-08-22 01:00 | 2018-11-20 01:00 | 0.5 | 6.4649 | 3.2325 | Avoid | 0.7 | 6.4649 | 4.5254 | H1 | 5 | Worsening | [10 empty] | 0 | -40 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK028 | Project_042_RISK028 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st July to 30th September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 0.25 | 1.4007 | 0.49026 | Accept | 0.15 | 1.4007 | 0.49026 | H2 | 4 | Stable | 0.7 | 102 | 134 | 145 | 130.5 | 0.7 | 102 | 134 | 145 | 130.5 | 0 | 40 | 0 | 0
2018-03-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK007 | Project_053_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Resources Uavailable | Person_252 | 2017-11-20 01:00 | 2019-08-21 01:00 | 0.5 | 10.3438 | 5.1719 | Reduce | 0.2 | 7.9015 | 1.5803 | H3 | 3 | Stable | 0.9 | 82 | 135 | 155 | 129.5 | 0.1 | 22 | 57 | 67 | 52.8333 | 23.6111 | 60 | 1 | 15.9666
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-119 | Project_029_Risk-119 | Opportunitity | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Not required to support on load & offload of Customer Furnished Equipmnet | Person_585 | 2017-05-23 | 2020-04-16 | 0.8 | 5.1334 | 4.1067 | Exploit | 0.8 | 3.4137 | 2.731 | H2 | 4 | Stable | [10 empty] | 33.5 | 0 | 0 | 20.1
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK027 | Project_042_RISK027 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st April to 30th June | Person_455 | 2020-08-21 01:00 | 2020-09-19 01:00 | 0.25 | 27.1644 | 0.81493 | Accept | 0.15 | 12.8336 | 0.38501 | H2 | 4 | Stable | 0.9 | 86 | 138 | 155 | 132.1667 | 0.9 | 86 | 138 | 155 | 132.1667 | 52.7559 | 40 | 0 | 31.6535
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2018-03-22 | 2019-07-21 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.7 | 120 | 133 | 144 | 132.6667 | 0.2 | 37 | 59 | 74 | 57.8333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_585 | 2017-09-02 01:00 | 2018-10-31 01:00 | 0.1 | 6.4168 | 0.64168 | Transfer | 0.1 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sub-system FPGA | Person_332 | 2017-01-21 01:00 | 2019-05-16 | 0.4 | 1.5914 | 0.63655 | Reduce | 0.2 | 1.5914 | 0.31827 | H3 | 3 | Stable | 0.8 | 100 | 137 | 155 | 133.8333 | 0.2 | 14 | 59 | 69 | 53.1667 | 0 | 50 | 1 | 1.5
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort for System HW/SW- System upgrade. | Person_199 | 2017-05-23 | 2019-09-18 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.2 | 2.5667 | 0.51334 | H3 | 3 | Stable | 0.9 | 89 | 135 | 157 | 131 | 0.3 | 18 | 53 | 62 | 48.6667 | 0 | 33.3333 | 1 | 1
2018-03-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK037 | Project_042_RISK037 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 1 | Person_455 | 2020-05-23 | 2021-05-22 | 0.14 | 6.6521 | 3.326 | Accept | 0.14 | 6.6521 | 3.326 | H2 | 4 | Stable | 0.6 | 90 | 127 | 141 | 123.1667 | 0.6 | 90 | 127 | 141 | 123.1667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.25 | 3.5934 | 0.89835 | H2 | 4 | Stable | 0.7 | 89 | 130 | 154 | 127.1667 | 0.3 | 28 | 47 | 75 | 48.5 | 0 | 50 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Minimum Order Quantities | Person_403 | 2017-11-20 01:00 | 2018-06-21 | 0.2 | 1.925 | 0.38501 | Exploit | 0.2 | 1.925 | 0.38501 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_403 | 2018-04-22 | 2018-08-22 01:00 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Worsening | 0.5 | 82 | 131 | 159 | 127.5 | 0.1 | 39 | 58 | 70 | 56.8333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) at the System level on product platform - performed by 3rd parties | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Sub-system / product system accreditation hindered by Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.1 | 0.25667 | 0.025667 | Transfer | 0.1 | 0.25667 | 0.025667 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_694 | 2017-05-23 | 2018-10-07 01:00 | 0.3 | 0 | 0 | Transfer | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 66.6667 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2018-05-15 | 0.3 | 0.89835 | 0.26951 | Transfer | 0.3 | 0.89835 | 0.26951 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 0.35 | 1.9208 | 0.67227 | Reduce | 0.25 | 1.9208 | 0.48019 | H2 | 4 | Stable | 0.6 | 95 | 126 | 157 | 126 | 0.3 | 30 | 50 | 74 | 50.6667 | 0 | 28.5714 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2018-03-22 | 2018-10-18 01:00 | 0.4 | 0.77001 | 0.30801 | Reduce | 0.3 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.9 | 96 | 139 | 154 | 134.3333 | 0.1 | 11 | 42 | 69 | 41.3333 | 0 | 25 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_694 | 2018-02-20 01:00 | 2018-09-20 01:00 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.6 | 115 | 136 | 149 | 134.6667 | 0.3 | 1 | 50 | 62 | 43.8333 | 0 | 28.5714 | 0 | 0
2018-03-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK047 | Project_053_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Lab Availability | Person_252 | 2017-10-21 01:00 | 2020-01-22 01:00 | 0.5 | 1.1744 | 0.23489 | Accept | 0.2 | 1.1744 | 0.23489 | H3 | 3 | Improving | 0.8 | 97 | 137 | 154 | 133.1667 | 0.8 | 97 | 137 | 154 | 133.1667 | 0 | 60 | 1 | 1.8
2018-03-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK043 | Project_053_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Change in REACH/RoSH Legislation | Person_302 | 2017-11-20 01:00 | 2018-09-20 01:00 | 0.1 | 2.9361 | 0.58721 | Accept | 0.1 | 2.9361 | 0.58721 | H2 | 4 | Stable | 0.8 | 120 | 121 | 141 | 124.1667 | 0.8 | 120 | 121 | 141 | 124.1667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer find issues with delivered parts or documentation | Person_294 | 2017-05-23 | 2019-08-20 | 0.4 | 9.0039 | 3.6016 | Reduce | 0.25 | 9.0039 | 2.251 | H2 | 4 | Improving | 0.8 | 114 | 137 | 150 | 135.3333 | 0.4 | 11 | 54 | 63 | 48.3333 | 0 | 37.5 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK002 | Project_058_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence of key parts | Person_236 | 2017-05-23 | 2018-05-22 | 0.5 | 6.7334 | 3.3667 | Reduce | 0.25 | 6.7334 | 1.6833 | H2 | 4 | Stable | 0.6 | 105 | 137 | 148 | 133.5 | 0.3 | 35 | 58 | 74 | 56.8333 | 0 | 50 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK052 | Project_058_RISK052 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | sub-System Cleanliness | Person_324 | 2017-05-23 | 2018-09-20 01:00 | 0.75 | 13.3102 | 9.9826 | Reduce | 0.2 | 13.3102 | 2.662 | H3 | 3 | Stable | 0.8 | 102 | 136 | 146 | 132 | 0.4 | 29 | 44 | 68 | 45.5 | 0 | 73.3333 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Open PR's | Person_319 | 2018-04-22 | 2018-11-20 01:00 | 0.5 | 7.6338 | 3.8169 | Reduce | 0.3 | 7.6338 | 2.2901 | H3 | 3 | Improving | 0.8 | 96 | 136 | 152 | 132 | 0.1 | 23 | 59 | 76 | 55.8333 | 0 | 40 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-054 | Project_062_Risk-054 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | sub-system rework to reviised standard | Person_031 | 2017-07-21 | 2018-11-21 01:00 | 0.4 | 0.62744 | 0.25098 | Transfer | 0.4 | 0.62744 | 0.25098 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-010 | Project_062_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Resource | Person_479 | 2017-07-21 | 2019-02-21 01:00 | 0.4 | 7.5293 | 3.0117 | Reduce | 0.3 | 7.5293 | 2.2588 | H2 | 4 | Stable | 0.8 | 108 | 140 | 148 | 136 | 0.3 | 21 | 55 | 60 | 50.1667 | 0 | 25 | 0 | 0
2018-03-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK046 | Project_053_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Un-Planned Production Activities | Person_252 | 2019-07-22 | 2020-01-22 01:00 | 0.5 | 4.183 | 1.2549 | Accept | 0.2 | 4.183 | 1.2549 | H3 | 3 | Stable | 0.7 | 85 | 129 | 153 | 125.6667 | 0.7 | 85 | 129 | 153 | 125.6667 | 0 | 60 | 1 | 1.8
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-013 | Project_062_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Unavailability of Network | Person_479 | 2017-07-21 | 2018-05-22 | 0.25 | 3.5555 | 0.88888 | Reduce | 0.2 | 3.5555 | 0.7111 | H3 | 3 | Stable | 0.9 | 87 | 129 | 143 | 124.3333 | 0.4 | 4 | 42 | 74 | 41 | 0 | 20 | 1 | 0.6
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-055 | Project_062_Risk-055 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Supplier integration and Apps | Person_245 | 2017-07-21 | 2018-11-21 01:00 | 0.5 | 0.83659 | 0.4183 | Reduce | 0.5 | 0.83659 | 0.4183 | H2 | 4 | Stable | 0.9 | 85 | 123 | 144 | 120.1667 | 0.2 | 16 | 50 | 71 | 47.8333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-011 | Project_062_Risk-011 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Variant deviations between SW | Person_479 | 2017-07-21 | 2018-05-13 | 0.4 | 0.71808 | 0.28723 | Reduce | 0.3 | 0.71808 | 0.21542 | H2 | 4 | Stable | 0.8 | 107 | 124 | 144 | 124.5 | 0.2 | 32 | 40 | 76 | 44.6667 | 0 | 25 | 0 | 0
2018-03-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK021 | Project_053_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Product documentation | Person_719 | 2018-08-22 01:00 | 2019-07-26 | 0.35 | 10.4574 | 2.6144 | Accept | 0.35 | 10.4574 | 2.6144 | H2 | 4 | Worsening | 0.8 | 91 | 132 | 156 | 129.1667 | 0.8 | 91 | 132 | 156 | 129.1667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-056 | Project_062_Risk-056 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Supplier integration acceptance by end Customer | Person_031 | 2017-07-21 | 2018-11-21 01:00 | 0.3 | 1.8823 | 0.5647 | Reduce | 0.3 | 1.8823 | 0.5647 | H3 | 3 | Stable | 0.6 | 107 | 131 | 144 | 129.1667 | 0.4 | 19 | 55 | 76 | 52.5 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-017 | Project_062_Risk-017 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer platform Schedule Unknown | Person_459 | 2017-07-21 | 2018-10-22 01:00 | 0.2 | 2.5098 | 0.50196 | Avoid | 0.1 | 2.5098 | 0.25098 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_585 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 12.7037 | 4.4463 | Accept | 0.03 | 12.7037 | 3.8111 | H3 | 3 | Stable | 0.5 | 103 | 135 | 153 | 132.6667 | 0.5 | 103 | 135 | 153 | 132.6667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-037 | Project_062_Risk-037 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Server availability | Person_459 | 2017-07-21 | 2018-04-22 | 0.35 | 4.183 | 1.464 | Avoid | 0.1 | 4.183 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 71.4286 | 1 | 2.1429
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-038 | Project_062_Risk-038 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Delay in start of Phase 2 | Person_459 | 2017-07-21 | 2018-02-20 01:00 | 0.2 | 2.0915 | 0.4183 | Avoid | 0.2 | 2.0915 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-016 | Project_062_Risk-016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Supplier Component Unavailability | Person_664 | 2017-07-21 | 2018-05-15 | 0.3 | 2.0927 | 0.62782 | Reduce | 0.2 | 2.0915 | 0.4183 | H3 | 3 | Stable | 0.8 | 92 | 131 | 141 | 126.1667 | 0.4 | 26 | 43 | 65 | 43.8333 | 0.059964 | 33.3333 | 0 | 0.035978
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-020 | Project_062_Risk-020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Security Encryption Solution | Person_245 | 2017-07-21 | 2018-09-20 01:00 | 0.25 | 4.183 | 1.0457 | Reduce | 0.2 | 4.183 | 0.83659 | H2 | 4 | Stable | 0.6 | 93 | 124 | 159 | 124.6667 | 0.3 | 11 | 56 | 70 | 50.8333 | 0 | 20 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-021 | Project_062_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Hardware CoSupplierng | Person_664 | 2017-07-21 | 2018-07-20 | 0.3 | 6.2744 | 1.8823 | Reduce | 0.25 | 6.2744 | 1.5686 | H2 | 4 | Stable | 0.7 | 102 | 128 | 143 | 126.1667 | 0.1 | 19 | 43 | 61 | 42 | 0 | 16.6667 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-043 | Project_062_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | User response | Person_459 | 2017-07-21 | 2019-02-21 01:00 | 0.35 | 3.3464 | 1.1712 | Avoid | 0.25 | 3.3464 | 0.83659 | H2 | 4 | Stable | [10 empty] | 0 | 28.5714 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-002 | Project_062_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | SDLC Card Obsolescence | Person_253 | 2017-07-21 | 2019-03-22 | 0.5 | 2.0915 | 1.0457 | Transfer | 0.2 | 2.0915 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 60 | 1 | 1.8
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-047 | Project_062_Risk-047 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Redhat6 on PCI shelf | Person_245 | 2017-07-21 | 2019-03-24 | 0.3 | 7.1808 | 2.1542 | Avoid | 0.3 | 7.1808 | 2.1542 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-025 | Project_062_Risk-025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | System Obsolescence Risk | Person_543 | 2017-07-21 | 2019-03-22 | 0.3 | 2.0915 | 0.62744 | Avoid | 0.2 | 2.0915 | 0.4183 | H2 | 4 | Stable | [10 empty] | 0 | 33.3333 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-022 | Project_062_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Registers Might Be Unstable | Person_479 | 2017-07-21 | 2018-06-22 | 0.25 | 1.3385 | 0.33464 | Reduce | 0.2 | 1.3385 | 0.26771 | H3 | 3 | Stable | 0.6 | 101 | 129 | 145 | 127 | 0.4 | 21 | 50 | 66 | 47.8333 | 0 | 20 | 1 | 0.6
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-001 | Project_062_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier servers | Person_459 | 2017-10-21 01:00 | 2018-05-23 | 0.5 | 1.2549 | 0.62744 | Reduce | 0.5 | 1.2549 | 0.62744 | H2 | 4 | Stable | 0.5 | 116 | 135 | 153 | 134.8333 | 0.4 | 19 | 57 | 77 | 54 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-023 | Project_062_Risk-023 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Change In Security Boundary | Person_031 | 2017-07-21 | 2019-02-21 01:00 | 0.3 | 4.6013 | 1.3804 | Reduce | 0.2 | 4.6013 | 0.92025 | H3 | 3 | Stable | 0.7 | 81 | 139 | 145 | 130.3333 | 0.3 | 8 | 43 | 76 | 42.6667 | 0 | 33.3333 | 1 | 1
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-006 | Project_062_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unavailability of Hardware | Person_253 | 2017-07-21 | 2019-03-22 | 0.5 | 2.5098 | 1.2549 | Reduce | 0.25 | 2.5098 | 0.62744 | H2 | 4 | Stable | 0.5 | 111 | 124 | 153 | 126.6667 | 0.3 | 31 | 56 | 67 | 53.6667 | 0 | 50 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-048 | Project_062_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software lockdown features | Person_245 | 2017-07-21 | 2018-11-21 01:00 | 0.5 | 0.71808 | 0.35904 | Reduce | 0.5 | 0.71808 | 0.35904 | H2 | 4 | Stable | 0.7 | 108 | 139 | 153 | 136.1667 | 0.3 | 31 | 48 | 77 | 50 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-005 | Project_062_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Security Solution Integration | Person_245 | 2017-07-21 | 2018-11-14 01:00 | 0.3 | 4.6013 | 1.3804 | Avoid | 0.25 | 4.6013 | 1.1503 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs | Person_403 | 2018-04-22 | 2018-08-22 01:00 | 0.5 | 2.5098 | 1.2549 | Accept | 0.5 | 2.5098 | 1.2549 | H2 | 4 | Stable | 0.5 | 93 | 134 | 147 | 129.3333 | 0.5 | 93 | 134 | 147 | 129.3333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 5.5717 | 1.9501 | Accept | 0.25 | 5.5717 | 1.9501 | H2 | 4 | Stable | 0.5 | 105 | 132 | 150 | 130.5 | 0.5 | 105 | 132 | 150 | 130.5 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Volume of production tools and Jigs | Person_279 | 2016-11-23 | 2021-11-23 | 0.35 | 6.4382 | 2.2534 | Reduce | 0.15 | 6.4382 | 0.96573 | H2 | 4 | Stable | 0.9 | 95 | 133 | 157 | 130.6667 | 0.3 | 31 | 55 | 70 | 53.5 | 0 | 57.1429 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software issue input | Person_279 | 2016-11-23 | 2023-02-20 | 0.4 | 49.4398 | 19.7759 | Reduce | 0.2 | 49.4398 | 9.888 | H2 | 4 | Stable | 0.7 | 103 | 134 | 152 | 131.8333 | 0.2 | 28 | 44 | 70 | 45.6667 | 0 | 50 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 15.8141 | 3.9535 | Accept | 0.2 | 15.8141 | 3.9535 | H3 | 3 | Stable | 0.7 | 102 | 135 | 152 | 132.3333 | 0.7 | 102 | 135 | 152 | 132.3333 | 0 | 33.3333 | 1 | 1
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design [in addition to costed effort] | Person_332 | 2017-05-28 | 2018-11-30 01:00 | 0.2 | 2.1133 | 0.52832 | Accept | 0.2 | 2.1133 | 0.52832 | H3 | 3 | Improving | 0.5 | 114 | 139 | 152 | 137 | 0.5 | 114 | 139 | 152 | 137 | 0 | 0 | 1 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_585 | 2017-10-21 01:00 | 2019-07-21 | 0.333 | 49.7149 | 14.9145 | Accept | 0.333 | 49.7149 | 14.9145 | H2 | 4 | Stable | 0.8 | 93 | 125 | 158 | 125.1667 | 0.8 | 93 | 125 | 158 | 125.1667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Survey costs | Person_618 | 2016-04-22 | 2018-08-21 | 0.2 | 13.2573 | 2.6515 | Avoid | 0.2 | 13.2573 | 2.6515 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 33.9324 | 6.7865 | Accept | 0.3 | 33.9324 | 6.7865 | H2 | 4 | Improving | 0.8 | 83 | 128 | 143 | 123 | 0.8 | 83 | 128 | 143 | 123 | 0 | 25 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-099 | Project_008_Risk-099 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Risk on Consumables Exposure | Person_639 | 2017-08-04 | 2018-08-21 | 0.5 | 5.6817 | 2.8408 | Reduce | 0.5 | 5.6817 | 2.8408 | H3 | 3 | Stable | 0.8 | 88 | 137 | 148 | 130.6667 | 0.1 | 11 | 50 | 79 | 48.3333 | 0 | 0 | 1 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2020-09-19 01:00 | 0.2 | 14.0464 | 4.2139 | Accept | 0.2 | 14.0464 | 4.2139 | H3 | 3 | Stable | 0.9 | 92 | 132 | 152 | 128.6667 | 0.9 | 92 | 132 | 152 | 128.6667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2019-07-21 | 0.3 | 9.4695 | 4.7347 | Accept | 0.2 | 9.4695 | 4.7347 | H3 | 3 | Stable | 0.5 | 80 | 137 | 141 | 128.1667 | 0.5 | 80 | 137 | 141 | 128.1667 | 0 | 33.3333 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_016 | Project_061 | RISK003 | Project_061_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Test equipment reliability | Person_104 | 2017-05-23 | 2020-11-18 23:00 | 0.4 | 0.11013 | 0.044051 | Reduce | 0.3 | 0.11013 | 0.033038 | H2 | 4 | Stable | 0.8 | 96 | 124 | 157 | 124.8333 | 0.1 | 25 | 55 | 72 | 52.8333 | 0 | 25 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.6 | 101 | 140 | 144 | 134.1667 | 0.4 | 33 | 52 | 75 | 52.6667 | 60.3671 | 58.3333 | 0 | 36.2202
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-07 23:00 | 2020-09-20 23:00 | 0.1 | 12.7232 | 1.2723 | Reduce | 0.1 | 12.7232 | 1.2723 | H3 | 3 | Stable | 0.8 | 107 | 122 | 142 | 122.8333 | 0.1 | 31 | 51 | 70 | 50.8333 | 0 | 0 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-20 23:00 | 2023-12-21 23:00 | 0.4 | 30.1969 | 12.0788 | Reduce | 0.25 | 30.1969 | 7.5492 | H2 | 4 | Stable | 0.5 | 97 | 131 | 154 | 129.1667 | 0.3 | 1 | 44 | 63 | 40 | 0 | 37.5 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | In-house development of sub-system estimate is low | Person_594 | 2016-03-23 | 2018-03-22 | 0.5 | 6.5118 | 3.2559 | Reduce | 0.2 | 1.506 | 0.30121 | H3 | 3 | Stable | 0.7 | 92 | 133 | 145 | 128.1667 | 0.2 | 16 | 48 | 71 | 46.5 | 76.8722 | 60 | 0 | 46.1233
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 0.25 | 0.63626 | 0.15906 | Reduce | 0.05 | 0.63626 | 0.031813 | H3 | 3 | Stable | 0.6 | 80 | 124 | 148 | 120.6667 | 0.4 | 4 | 48 | 72 | 44.6667 | 0 | 80 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Component Shock test failure | Person_661 | 2016-09-07 23:00 | 2019-11-14 23:00 | 0.4 | 0.8467 | 0.33868 | Reduce | 0.2 | 0.8467 | 0.16934 | H3 | 3 | Stable | 0.9 | 119 | 132 | 143 | 131.6667 | 0.3 | 38 | 52 | 64 | 51.6667 | 0 | 50 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-01-11 23:00 | 0.8 | 18.0459 | 14.4367 | Reduce | 0.2 | 3.0076 | 0.60153 | H3 | 3 | Stable | 0.5 | 103 | 129 | 146 | 127.5 | 0.1 | 37 | 42 | 62 | 44.5 | 83.3335 | 75 | 1 | 52.2501
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-057 | Project_062_Risk-057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Supplier Application Encryption / Protection | Person_253 | 2017-07-21 | 2019-02-21 01:00 | 0.3 | 18.4072 | 5.5222 | Accept | 0.3 | 18.4072 | 5.5222 | H2 | 4 | Stable | 0.9 | 112 | 127 | 153 | 128.8333 | 0.9 | 112 | 127 | 153 | 128.8333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-034 | Project_062_Risk-034 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Long lead Procurement price increases | Person_664 | 2017-07-21 | 2018-04-22 | 0.25 | 2.4509 | 0.73527 | Accept | 0.25 | 2.4509 | 0.73527 | H2 | 4 | Stable | 0.5 | 82 | 135 | 148 | 128.3333 | 0.5 | 82 | 135 | 148 | 128.3333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 0.4 | 5.1004 | 2.0402 | Reduce | 0.2 | 2.5506 | 0.51013 | H3 | 3 | Stable | 0.9 | 103 | 134 | 158 | 132.8333 | 0.2 | 29 | 57 | 73 | 55 | 49.9917 | 50 | 0 | 29.995
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-20 23:00 | 2018-04-22 | 0.5 | 28.0275 | 14.0137 | Reduce | 0.1 | 28.0275 | 2.8027 | H3 | 3 | Stable | 0.5 | 80 | 122 | 156 | 120.6667 | 0.3 | 36 | 47 | 60 | 47.3333 | 0 | 80 | 1 | 2.4
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-018 | Project_062_Risk-018 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Prioritisation - new or less experienced staff | Person_459 | 2017-07-21 | 2018-11-20 01:00 | 0.35 | 2.216 | 0.2216 | Accept | 0.3 | 2.216 | 0.2216 | H2 | 4 | Improving | 0.8 | 119 | 132 | 160 | 134.5 | 0.8 | 119 | 132 | 160 | 134.5 | 0 | 14.2857 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-009 | Project_062_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Unresolved technical debt (excluding ILS) | Person_253 | 2017-07-21 | 2018-05-22 | 0.5 | 5.0032 | 3.5023 | Accept | 0.5 | 5.0032 | 3.5023 | H2 | 4 | Stable | 0.6 | 84 | 128 | 156 | 125.3333 | 0.6 | 84 | 128 | 156 | 125.3333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-004 | Project_062_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Undefined risks | Person_459 | 2017-07-21 | 2019-03-24 | 0.35 | 18.4072 | 5.5222 | Accept | 0.35 | 18.4072 | 5.5222 | H2 | 4 | Stable | 0.8 | 100 | 130 | 145 | 127.5 | 0.8 | 100 | 130 | 145 | 127.5 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-034 | Project_008_SER-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_567 | 2018-05-22 | 2018-08-21 | 0.25 | 3.4651 | 1.0395 | Accept | 0.25 | 3.4651 | 1.0395 | H3 | 3 | Stable | 0.7 | 103 | 132 | 151 | 130.3333 | 0.7 | 103 | 132 | 151 | 130.3333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-085 | Project_008_SER-085 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Insufficient LOE to manage the supply chain with reducing number of spares | Person_639 | 2017-04-22 | 2018-08-21 | 0.25 | 3.4651 | 1.0395 | Accept | 0.25 | 3.4651 | 1.0395 | H3 | 3 | Stable | 0.7 | 120 | 124 | 141 | 126.1667 | 0.7 | 120 | 124 | 141 | 126.1667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | EMC non compliance | Person_047 | 2016-06-23 | 2019-12-26 23:00 | 0.7 | 3.935 | 2.7545 | Reduce | 0.5 | 3.935 | 1.9675 | H2 | 4 | Stable | 0.6 | 117 | 132 | 158 | 133.8333 | 0.3 | 18 | 46 | 78 | 46.6667 | 0 | 28.5714 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SubSystem System Design | Person_038 | 2017-09-30 23:00 | 2019-11-19 23:00 | 0.2 | 1.5213 | 0.30425 | Reduce | 0.1 | 1.5213 | 0.15213 | H3 | 3 | Stable | 0.8 | 99 | 125 | 148 | 124.5 | 0.3 | 37 | 57 | 61 | 54.3333 | 0 | 50 | 1 | 1.5
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_567 | 2017-08-21 01:00 | 2018-08-21 | 0.3 | 67.8016 | 27.1206 | Accept | 0.3 | 67.8016 | 27.1206 | H2 | 4 | Stable | 0.6 | 104 | 131 | 144 | 128.6667 | 0.6 | 104 | 131 | 144 | 128.6667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Lack of Spares Availability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 0.2 | 65.469 | 26.1876 | Accept | 0.2 | 65.469 | 26.1876 | H3 | 3 | Stable | 0.8 | 88 | 123 | 148 | 121.3333 | 0.8 | 88 | 123 | 148 | 121.3333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-148 | Project_008_SER-148 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Demands but not provisioned | Person_639 | 2017-08-21 01:00 | 2018-08-21 | 0.3 | 7.7077 | 1.5415 | Accept | 0.3 | 7.7077 | 1.5415 | H3 | 3 | Stable | 0.9 | 84 | 130 | 142 | 124.3333 | 0.9 | 84 | 130 | 142 | 124.3333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-094 | Project_008_Risk-094 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Consumable Stock Levels | Person_567 | 2017-04-22 | 2018-08-21 | 0.5 | 25.1514 | 12.5757 | Accept | 0.5 | 25.1514 | 12.5757 | H3 | 3 | Stable | 0.9 | 101 | 137 | 144 | 132.1667 | 0.9 | 101 | 137 | 144 | 132.1667 | 0 | 0 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-06-06 | 0.4 | 1.0142 | 0.40567 | Reduce | 0.1 | 1.0142 | 0.10142 | H3 | 3 | Stable | 0.8 | 93 | 121 | 146 | 120.5 | 0.4 | 34 | 57 | 77 | 56.5 | 0 | 75 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | 9. Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 0.8 | 19.1678 | 15.3343 | Reduce | 0.2 | 2.8752 | 0.57503 | H3 | 3 | Stable | 0.5 | 109 | 129 | 153 | 129.6667 | 0.4 | 16 | 40 | 62 | 39.6667 | 85 | 75 | 0 | 51
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-05 23:00 | 2019-09-12 23:00 | 0.8 | 8.0322 | 6.4258 | Reduce | 0.5 | 4.006 | 2.003 | H2 | 4 | Stable | 0.9 | 112 | 124 | 145 | 125.5 | 0.1 | 27 | 54 | 70 | 52.1667 | 50.1263 | 37.5 | 0 | 30.0758
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK002 | Project_065_RISK002 | Opportunitity | Project Contingency | Open | H1 | 5 | 12. Acquisition and offsets | New supplier for enclosure | Person_598 | 2015-01-06 23:00 | 2017-10-18 23:00 | 0.05 | 9.6346 | 0.48173 | Exploit | 0.7 | 9.6346 | 6.7442 | H1 | 5 | Stable | [10 empty] | 0 | -1300 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier Selection Process | Person_379 | 2017-10-18 23:00 | 2019-04-23 | 0.4 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 81 | 125 | 143 | 120.6667 | 0.1 | 34 | 55 | 73 | 54.5 |  | 25 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Colour Representation in Video Image Distortion | Person_305 | 2017-09-21 23:00 | 2020-03-21 | 0.5 | 5.5323 | 2.7662 | Reduce | 0.1 | 5.5323 | 0.55323 | H3 | 3 | Stable | 0.6 | 84 | 137 | 154 | 131 | 0.4 | 7 | 41 | 61 | 38.6667 | 0 | 80 | 1 | 2.4
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 0.3 | 3.2479 | 0.64958 | Accept | 0.3 | 3.2479 | 0.64958 | H3 | 3 | Stable | 0.8 | 119 | 130 | 150 | 131.5 | 0.8 | 119 | 130 | 150 | 131.5 | 0 | 0 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-20 23:00 | 0.8 | 35.2369 | 28.1895 | Reduce | 0.3 | 18.4979 | 5.5494 | H2 | 4 | Stable | 0.8 | 117 | 132 | 149 | 132.3333 | 0.3 | 10 | 56 | 67 | 50.1667 | 47.5042 | 62.5 | 0 | 28.5025
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 4 | 9. Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-20 23:00 | 0.7 | 20.6835 | 14.4785 | Reduce | 0.3 | 20.6835 | 6.2051 | H2 | 4 | Stable | 0.5 | 111 | 134 | 147 | 132.3333 | 0.3 | 15 | 56 | 63 | 50.3333 | 0 | 57.1429 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 4 | 8. System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 0.6 | 5.2585 | 3.1551 | Reduce | 0.15 | 5.2585 | 0.78877 | H2 | 4 | Stable | 0.7 | 96 | 131 | 148 | 128 | 0.1 | 21 | 57 | 61 | 51.6667 | 0 | 75 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-04-21 | 0.3 | 2.723 | 0.81691 | Reduce | 0.1 | 2.723 | 0.2723 | H3 | 3 | Improving | 0.9 | 82 | 135 | 152 | 129 | 0.4 | 25 | 43 | 68 | 44.1667 | 0 | 66.6667 | 1 | 2
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-07 23:00 | 2020-09-20 23:00 | 0.2 | 4.8444 | 0.96888 | Reduce | 0.2 | 4.8444 | 0.96888 | H3 | 3 | Stable | 0.7 | 120 | 123 | 146 | 126.3333 | 0.1 | 6 | 46 | 73 | 43.8333 | 0 | 0 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System Performance | Person_305 | 2016-09-07 23:00 | 2020-09-20 23:00 | 0.15 | 5.8725 | 0.88088 | Reduce | 0.05 | 5.8725 | 0.29363 | H2 | 4 | Stable | 0.8 | 118 | 125 | 159 | 129.5 | 0.2 | 38 | 57 | 60 | 54.3333 | 0 | 66.6667 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_038 | 2020-05-23 | 2023-10-25 23:00 | 0.2 | 7.4599 | 1.492 | Reduce | 0.05 | 7.4599 | 0.37299 | H2 | 4 | Stable | 0.5 | 113 | 129 | 153 | 130.3333 | 0.1 | 39 | 46 | 68 | 48.5 | 0 | 75 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-28 23:00 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.7 | 104 | 127 | 159 | 128.5 | 0.2 | 14 | 49 | 73 | 47.1667 | 60.3671 | 58.3333 | 0 | 36.2202
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-19 23:00 | 0.4 | 2.8643 | 1.1457 | Reduce | 0.1 | 2.8643 | 0.28643 | H3 | 3 | Stable | 0.9 | 99 | 122 | 151 | 123 | 0.1 | 32 | 47 | 78 | 49.6667 | 0.0015933 | 75 | 1 | 2.251
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power Supply - Motor Controller Interface | Person_047 | 2016-05-23 | 2018-04-21 | 0.5 | 25.3543 | 12.6771 | Reduce | 0.2 | 25.3543 | 5.0709 | H3 | 3 | Stable | 0.7 | 105 | 126 | 156 | 127.5 | 0.1 | 32 | 48 | 70 | 49 | 0 | 60 | 1 | 1.8
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-23 | 2024-05-22 | 0.1 | 2.9272 | 1.4636 | Accept | 0.1 | 2.9272 | 1.4636 | H3 | 3 | Improving | 0.6 | 116 | 134 | 147 | 133.1667 | 0.6 | 116 | 134 | 147 | 133.1667 | 0 | 0 | 1 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 0.70865 | 0.28346 | H2 | 4 | Stable | 0.6 | 102 | 128 | 145 | 126.5 | 0.4 | 21 | 52 | 76 | 50.8333 | 82.0989 | 20 | 0 | 49.2593
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_703 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 1.7994 | 0.26991 | H3 | 3 | Stable | 0.6 | 92 | 137 | 153 | 132.1667 | 0.4 | 2 | 47 | 78 | 44.6667 | 71.4286 | 70 | 1 | 44.9571
2018-03-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK008 | Project_044_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Skills | Person_505 | 2017-10-21 01:00 | 2018-10-22 01:00 | 0.3 | 1.5695 | 0.47085 | Reduce | 0.3 | 1.4488 | 0.43463 | H2 | 4 | Stable | 0.7 | 109 | 121 | 158 | 125.1667 | 0.3 | 2 | 53 | 74 | 48 | 7.6924 | 0 | 0 | 4.6155
2018-03-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK003 | Project_044_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Mono vs stereo Component | Person_358 | 2016-03-23 | 2018-10-22 01:00 | 0.7 | 14.4876 | 10.1413 | Reduce | 0.5 | 14.4876 | 7.2438 | H2 | 4 | Stable | 0.5 | 92 | 122 | 146 | 121 | 0.1 | 25 | 57 | 63 | 52.6667 | 0 | 28.5714 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE-01 | Project_067_SE-01 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Procurement of Cables for Rig (Procurement Process) | Person_327 | 2015-08-22 01:00 | 2018-08-21 | 0.4 | 0.63006 | 0.25202 | Reduce | 0.2 | 0.31503 | 0.063006 | H3 | 3 | Stable | 0.6 | 96 | 140 | 150 | 134.3333 | 0.4 | 37 | 55 | 68 | 54.1667 | 50 | 50 | 1 | 31.5
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-R1 | Project_067_Risk-R1 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Rhapsody modification to manual to System interface | Person_327 | 2017-03-23 | 2018-08-13 | 0.3 | 7.8758 | 2.3627 | Reduce | 0.2 | 2.2502 | 0.45004 | H3 | 3 | Stable | 0.7 | 105 | 128 | 151 | 128 | 0.2 | 23 | 59 | 71 | 55 | 71.4286 | 33.3333 | 1 | 43.8571
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE-10 | Project_067_SE-10 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Configuration baseline unstable for Platform | Person_327 | 2017-10-26 01:00 | 2018-08-18 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.9 | 104 | 134 | 160 | 133.3333 | 0.2 | 3 | 44 | 78 | 42.8333 |  | 60 | 1
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE-08 | Project_067_SE-08 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Ageing Test Infrastructure | Person_327 | 2015-10-01 01:00 | 2018-08-21 | 0.6 | 0 | 0 | Transfer | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 33.3333 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-R4 | Project_067_Risk-R4 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Resource Availability | Person_325 | 2015-08-22 01:00 | 2018-08-21 | 0.45 | 2.579 | 1.1606 | Reduce | 0.6 | 1.2857 | 0.77145 | H1 | 5 | Improving | 0.5 | 97 | 134 | 156 | 131.5 | 0.4 | 4 | 58 | 71 | 51.1667 | 50.1455 | -33.3333 | 0 | 30.0873
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-R2 | Project_067_Risk-R2 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Sub-Contractor Performance - Manufacturing | Person_325 | 2015-08-22 01:00 | 2018-08-20 | 0.3 | 0.23127 | 0.069382 | Reduce | 0.1 | 0.040628 | 0.0040628 | H3 | 3 | Stable | 0.6 | 109 | 128 | 148 | 128.1667 | 0.1 | 35 | 48 | 79 | 51 | 82.4331 | 66.6667 | 1 | 51.4598
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-R6 | Project_067_Risk-R6 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub-Contractor Performance - Support Services | Person_713 | 2017-08-21 01:00 | 2018-08-21 | 0.5 | 2.2502 | 1.1251 | Reduce | 0.5 | 2.2502 | 1.1251 | H2 | 4 | Stable | 0.7 | 112 | 124 | 158 | 127.6667 | 0.1 | 10 | 59 | 65 | 51.8333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-1 | Project_067_Risk-1 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Schedule Overrun | Person_325 | 2018-02-20 01:00 | 2019-10-20 01:00 | 0.7 | 0 | 0 | Reduce | 0.7 | 0 | 0 | H1 | 5 | Stable | 0.5 | 118 | 122 | 160 | 127.6667 | 0.2 | 26 | 50 | 76 | 50.3333 |  | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-2 | Project_067_Risk-2 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System Performance | Person_765 | 2018-02-20 01:00 | 2019-10-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.8 | 114 | 122 | 152 | 125.6667 | 0.3 | 23 | 57 | 78 | 54.8333 |  | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-5 | Project_067_Risk-5 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System performance levels | Person_327 | 2018-02-20 01:00 | 2019-10-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 85 | 133 | 155 | 128.6667 | 0.2 | 26 | 47 | 60 | 45.6667 |  | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-6 | Project_067_Risk-6 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | System Resources | Person_325 | 2018-03-02 01:00 | 2019-10-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.7 | 90 | 136 | 141 | 129.1667 | 0.4 | 25 | 51 | 65 | 49 |  | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-7 | Project_067_Risk-7 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Unexpected bugs found in release candidate of Software | Person_327 | 2019-06-13 | 2019-08-15 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 92 | 125 | 143 | 122.5 | 0.2 | 11 | 52 | 66 | 47.5 |  | 40 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-012 | Project_062_Risk-012 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Integration Rig Move | Person_253 | 2018-05-23 | 2019-05-23 | 0.3 | 0.4183 | 0.12549 | Avoid | 0.3 | 0.4183 | 0.12549 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-024 | Project_062_Risk-024 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional SW Build post-Factory Acceptance Test | Person_253 | 2019-01-22 01:00 | 2019-04-22 | 0.3 | 1.7778 | 0.53333 | Avoid | 0.3 | 1.7778 | 0.53333 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-027 | Project_062_Risk-027 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Facility to Test modifications | Person_253 | 2018-08-22 01:00 | 2020-04-21 | 0.5 | 2.3703 | 1.1852 | Reduce | 0.4 | 2.3703 | 0.94814 | H2 | 4 | Stable | 0.9 | 107 | 134 | 145 | 131.3333 | 0.3 | 27 | 50 | 69 | 49.3333 | 0 | 20 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-008 | Project_062_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Paperwork for Legacy Items | Person_459 | 2018-03-23 | 2019-03-24 | 0.3 | 0.83659 | 0.25098 | Avoid | 0.3 | 0.83659 | 0.25098 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.6 | 95 | 136 | 159 | 133 | 0.3 | 38 | 41 | 64 | 44.3333 | 25.8065 | 20 | 0 | 15.4839
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-115 | Project_011_Risk-115 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | SMEs are unavailable to support project activites | Person_230 | 2016-07-21 | 2018-08-21 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-058 | Project_011_Risk-058 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Programme delays | Person_147 | 2013-11-20 01:00 | 2018-11-20 01:00 | 0.25 | 1.5013 | 0.37532 | Reduce | 0.25 | 1.5013 | 0.37532 | H2 | 4 | Stable | 0.8 | 92 | 137 | 152 | 132 | 0.1 | 5 | 49 | 66 | 44.5 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-131 | Project_011_Risk-131 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Support team have not covered all obligations in support contract | Person_147 | 2016-05-24 | 2018-08-17 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-137 | Project_011_Risk-137 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Subsystem will not match Fidelity of Customer - does not accept | Person_147 | 2018-02-16 01:00 | 2018-09-20 01:00 | 0.4 | 0.11876 | 0.047505 | Avoid | 0.2 | 0.11876 | 0.023752 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Labour/Material Risk | Person_662 | 2015-05-24 | 2019-05-23 | 0.5 | 0.34776 | 0.034776 | Accept | 0.5 | 0.34776 | 0.034776 | H2 | 4 | Stable | 0.9 | 99 | 138 | 158 | 134.8333 | 0.9 | 99 | 138 | 158 | 134.8333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2018-04-22 | 2018-09-20 01:00 | 0.2 | 0.62279 | 0.12456 | Avoid | 0.2 | 0.62279 | 0.12456 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-09-20 01:00 | 0.2 | 1.8854 | 0.37708 | Reduce | 0.2 | 1.8854 | 0.37708 | H2 | 4 | Stable | 0.9 | 82 | 132 | 160 | 128.3333 | 0.2 | 2 | 40 | 64 | 37.6667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2018-06-23 | 2018-10-21 01:00 | 0.4 | 1.4138 | 0.56551 | Reduce | 0.4 | 1.4138 | 0.56551 | H2 | 4 | Stable | 0.8 | 100 | 128 | 153 | 127.5 | 0.1 | 33 | 48 | 73 | 49.6667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-09-20 01:00 | 0.4 | 0.19206 | 0.076826 | -- | 0.4 | 0.19206 | 0.076826 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-08-22 01:00 | 2018-11-20 01:00 | 0.4 | 0.58017 | 0.23207 | Avoid | 0.4 | 0.58017 | 0.23207 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_009 | Project_045 | RISK001 | Project_045_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour/T&S Overspend | Person_662 | 2017-01-21 01:00 | 2020-05-22 | 0.5 | 0.49834 | 0.12459 | Accept | 0.5 | 0.49834 | 0.12459 | H2 | 4 | Stable | 0.6 | 101 | 134 | 156 | 132.1667 | 0.6 | 101 | 134 | 156 | 132.1667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-11-20 01:00 | 0.3 | 0.32389 | 0.097168 | Reduce | 0.3 | 0.32389 | 0.097168 | H2 | 4 | Stable | 0.5 | 93 | 138 | 149 | 132.3333 | 0.1 | 28 | 50 | 60 | 48 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_182 | 2018-06-23 | 2018-10-21 01:00 | 0.2 | 0.19206 | 0.038413 | -- | 0.2 | 0.19206 | 0.038413 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_431 | 2017-05-24 | 2018-08-19 | 0.3 | 0.11933 | 0.035799 | -- | 0.3 | 0.022161 | 0.0066484 | H3 | 3 | Stable | [10 empty] | 81.4286 | 0 | 0 | 48.8571
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-117 | Project_011_Risk-117 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Avaliability for testing/reviews | Person_147 | 2018-04-06 | 2018-09-20 01:00 | 0.35 | 0 | 0 | Avoid | 0.35 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-129 | Project_011_Risk-129 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Signature of Work Authorisation documents | Person_422 | 2017-05-24 | 2018-06-21 | 0.4 | 0.12643 | 0.050573 | -- | 0.4 | 0.12643 | 0.050573 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-130 | Project_011_Risk-130 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer does not accept Voice Pronounciation | Person_187 | 2017-05-24 | 2018-06-21 | 0.4 | 0.090918 | 0.036367 | Avoid | 0.4 | 0.090918 | 0.036367 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure | Person_299 | 2014-08-21 04:00 | 2019-08-20 04:00 | 0.5 | 15.0856 | 7.5428 | Avoid | 0.5 | 15.0856 | 7.5428 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repair costs | Person_299 | 2014-08-21 04:00 | 2019-08-20 04:00 | 0.1 | 25.1176 | 2.5118 | Avoid | 0.1 | 25.1176 | 2.5118 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 04:00 | 2019-08-20 04:00 | 0.5 | 17.0468 | 8.5234 | Avoid | 0.5 | 17.0468 | 8.5234 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 04:00 | 2019-08-20 04:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 04:00 | 2019-08-20 04:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Supplier revert to original component (Supplier NRE) | Person_693 | 2017-05-23 | 2018-06-22 | 0.15 | 4.3731 | 0.65596 | Reduce | 0.02 | 6.431 | 0.12862 | H3 | 3 | Improving | 0.9 | 112 | 125 | 158 | 128.3333 | 0.1 | 20 | 43 | 72 | 44 | -47.0588 | 86.6667 | 1 | -25.6353
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_238 | 2017-04-22 | 2018-05-22 | 0.25 | 3.3227 | 0.83067 | Reduce | 0.012 | 3.3055 | 0.039667 | H3 | 3 | Stable | 0.6 | 108 | 138 | 143 | 133.8333 | 0.1 | 4 | 53 | 73 | 48.1667 | 0.51615 | 95.2 | 1 | 3.1657
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Unforseen and substantial increase in Repairs workload during new build production period. | Person_238 | 2017-10-23 01:00 | 2019-08-21 01:00 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.25 | 1.5434 | 0.38586 | H2 | 4 | Stable | 0.9 | 119 | 138 | 151 | 137 | 0.4 | 2 | 44 | 73 | 41.8333 | 0 | 16.6667 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK007 | Project_041_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Advanced production of products using a Qual. standard component rather than a Prod. standard | Person_547 | 2017-10-21 01:00 | 2018-10-21 01:00 | 0.49 | 1.2862 | 0.63024 | Reduce | 0.2 | 1.2862 | 0.25724 | H3 | 3 | Stable | 0.6 | 93 | 124 | 141 | 121.6667 | 0.4 | 27 | 40 | 74 | 43.5 | 0 | 59.1837 | 1 | 1.7755
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Reduce touch labour if Production readiness programme successful | Person_238 | 2017-05-23 | 2018-12-21 01:00 | 0.3 | 1.5606 | 0.46818 | Exploit | 0.05 | 1.5606 | 0.07803 | H3 | 3 | Stable | [10 empty] | 0 | 83.3333 | 1 | 2.5
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Regulatory standards changes misunderstood | Person_693 | 2018-03-23 | 2018-06-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.7 | 83 | 135 | 144 | 127.8333 | 0.4 | 35 | 49 | 71 | 50.3333 | 0 | 50 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Production - Test Equipment (Second Test Set) | Person_238 | 2017-05-23 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.15 | 0.68598 | 0.1029 | H3 | 3 | Stable | 0.7 | 83 | 133 | 145 | 126.6667 | 0.4 | 26 | 58 | 70 | 54.6667 | 0 | 40 | 1 | 1.2
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK026 | Project_063_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Clause on Joint Proposal | Person_261 | 2018-05-04 | 2019-05-23 | 0.5 | 9.8888 | 4.9444 | -- | 0.5 | 9.8888 | 4.9444 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK026 | Project_048_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Clause on Joint Proposal | Person_261 | 2018-05-04 | 2019-05-23 | 0.5 | 3.5439 | 1.772 | -- | 0.5 | 3.5439 | 1.772 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2018-05-22 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.8 | 116 | 134 | 159 | 135.1667 | 0.3 | 13 | 59 | 72 | 53.5 | 0 | 40 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 0.92411 | 0.55447 | Reduce | 0.5 | 0.36965 | 0.18482 | H2 | 4 | Stable | 0.5 | 97 | 133 | 154 | 130.5 | 0.1 | 36 | 42 | 73 | 46.1667 | 60 | 16.6667 | 0 | 36
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-03 22:00 | 2018-04-21 | 0.2 | 4.0661 | 0.81322 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.8 | 86 | 122 | 158 | 122 | 0.3 | 10 | 50 | 74 | 47.3333 | 0 | 75 | 1 | 2.25
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.5 | 0.46206 | 0.23103 | H1 | 5 | Stable | 0.6 | 115 | 131 | 141 | 130 | 0.3 | 15 | 51 | 70 | 48.1667 | 58.3333 | 16.6667 | 0 | 35
2018-03-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-015 | Project_062_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Re-work | Person_253 | 2018-03-01 01:00 | 2019-05-22 | 0.5 | 1.1089 | 0.88715 | Accept | 0.5 | 0.73929 | 0.44357 | H2 | 4 | Stable | 0.6 | 91 | 127 | 150 | 124.8333 | 0.6 | 91 | 127 | 150 | 124.8333 | 33.3333 | 0 | 0 | 20
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-28 22:00 | 2018-05-22 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.8 | 87 | 127 | 150 | 124.1667 | 0.3 | 5 | 54 | 65 | 47.6667 | 0 | 50 | 1 | 1.5
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2018-05-22 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.7 | 80 | 135 | 152 | 128.6667 | 0.2 | 34 | 54 | 69 | 53.1667 | 0 | 25 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_693 | 2012-06-01 | 2018-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Improving | 0.8 | 119 | 124 | 160 | 129.1667 | 0.4 | 22 | 59 | 70 | 54.6667 | 0 | 40 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2018-05-21 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Stable | [10 empty] | 0 | 37.5 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Unreliability of Hardware | Person_431 | 2016-06-23 | 2018-08-21 | 0.1 | 3.6965 | 0.36965 | Accept | 0.1 | 3.6965 | 0.18482 | H3 | 3 | Stable | 0.5 | 117 | 129 | 145 | 129.6667 | 0.5 | 117 | 129 | 145 | 129.6667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_147 | 2016-04-21 | 2018-08-21 | 0.25 | 0.92411 | 0.18482 | Accept | 0.25 | 0.92411 | 0.18482 | H3 | 3 | Stable | 0.9 | 92 | 125 | 149 | 123.5 | 0.9 | 92 | 125 | 149 | 123.5 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | RISK008 | Project_029_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Impact of sub-system Design Changes [product dependency] | Person_332 | 2016-09-20 01:00 | 2019-08-15 | 0.7 | 1.8482 | 0.55447 | Accept | 0.7 | 1.8482 | 0.36965 | H2 | 4 | Stable | 0.8 | 96 | 138 | 149 | 132.8333 | 0.8 | 96 | 138 | 149 | 132.8333 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2018-02-18 22:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.8 | 95 | 133 | 141 | 128 | 0.4 | 19 | 49 | 77 | 48.6667 | 90 | 75 | 1 | 56.25
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK011 | Project_041_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Supplier Development support | Person_693 | 2018-04-11 | 2018-06-22 | 0.3 | 0.36965 | 0.25875 | Accept | 0.3 | 0.36965 | 0.25875 | H2 | 4 | Stable | 0.6 | 102 | 136 | 147 | 132.1667 | 0.6 | 102 | 136 | 147 | 132.1667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK010 | Project_010_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Use of Lead components | Person_359 | 2012-05-23 | 2025-04-22 | 0.05 | 1.8482 | 0.092411 | Reduce | 0.05 | 1.8482 | 0.092411 | H3 | 3 | Stable | 0.6 | 80 | 136 | 145 | 128.1667 | 0.1 | 9 | 53 | 66 | 47.8333 | 0 | 0 | 1 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK010 | Project_041_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Digital Assembly - Testing | Person_547 | 2018-04-11 | 2018-11-20 01:00 | 0.1 | 17.0765 | 1.7076 | Accept | 0.15 | 17.0765 | 1.7076 | H3 | 3 | Improving | 0.6 | 90 | 132 | 157 | 129.1667 | 0.6 | 90 | 132 | 157 | 129.1667 | 0 | -50 | 1 | -1.5
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK002 | Project_041_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Component Technical risk using new material | Person_653 | 2017-09-20 01:00 | 2018-06-22 | 0.4 | 186.9553 | 59.2026 | Accept | 0.9 | 186.9553 | 1.3939 | H2 | 4 | Stable | 0.6 | 120 | 134 | 143 | 133.1667 | 0.6 | 120 | 134 | 143 | 133.1667 | 0 | -125 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK013 | Project_041_RISK013 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional components validation | Person_693 | 2017-07-15 | 2018-05-23 | 0.4 | 22.8501 | 6.855 | Accept | 0.3 | 22.8501 | 6.855 | H2 | 4 | Stable | 0.7 | 82 | 139 | 156 | 132.3333 | 0.7 | 82 | 139 | 156 | 132.3333 | 0 | 25 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Additional minor point releases | Person_228 | 2016-05-23 | 2017-10-19 01:00 | 0.5 | 11.9444 | 5.9722 | Reduce | 0.45 | 11.9444 | 5.375 | H1 | 5 | Stable | 0.8 | 84 | 130 | 155 | 126.5 | 0.4 | 34 | 56 | 79 | 56.1667 | 0 | 10 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_228 | 2016-05-23 | 2018-04-21 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.6 | 119 | 138 | 156 | 137.8333 | 0.4 | 29 | 43 | 78 | 46.5 | 0 | 50 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_004 | 2015-11-21 01:00 | 2018-11-20 01:00 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.5 | 102 | 140 | 142 | 134 | 0.1 | 17 | 46 | 61 | 43.6667 | 0 | 5 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.8 | 2.8043 | 2.2435 | Reduce | 0.45 | 2.8043 | 1.2619 | H1 | 5 | Stable | 0.9 | 84 | 132 | 149 | 126.8333 | 0.4 | 13 | 45 | 74 | 44.5 | 0 | 43.75 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK167 | Project_024_RISK167 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Customer not providing the information needed or Customer not accepting the Customer documentation resulting in rewor. | Person_710 | 2016-08-21 01:00 | 2018-05-21 | 0.5 | 9.971 | 4.9855 | Reduce | 0.3 | 9.971 | 2.9913 | H1 | 5 | Worsening | 0.7 | 119 | 122 | 151 | 126.3333 | 0.2 | 17 | 41 | 77 | 43 | 0 | 40 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK226 | Project_024_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Late Evidences Certification delivery | Person_642 | 2017-04-30 | 2018-05-21 | 0.4 | 3.9468 | 1.5787 | Reduce | 0.2 | 3.9468 | 0.78937 | H2 | 4 | Worsening | 0.7 | 94 | 129 | 149 | 126.5 | 0.3 | 1 | 50 | 72 | 45.5 | 0 | 50 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Outstanding CRs | Person_693 | 2017-05-23 | 2018-12-21 01:00 | 0.25 | 35.9673 | 10.7902 | Accept | 0.5 | 35.9673 | 9.7112 | H2 | 4 | Stable | 0.7 | 92 | 138 | 160 | 134 | 0.7 | 92 | 138 | 160 | 134 | 0 | -100 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of not being able to perform Tests | Person_238 | 2017-12-21 01:00 | 2019-01-21 01:00 | 0.5 | 3.9728 | 1.3905 | Accept | 0.5 | 3.9728 | 1.3905 | H2 | 4 | Stable | 0.8 | 95 | 124 | 154 | 124.1667 | 0.8 | 95 | 124 | 154 | 124.1667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.6 | 83 | 132 | 160 | 128.5 | 0.3 | 19 | 45 | 69 | 44.6667 | 0 | 60 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis and Security | Person_288 | 2017-02-22 01:00 | 2017-11-19 01:00 | 0.3 | 19.9938 | 5.9981 | Reduce | 0.04675 | 19.9938 | 0.93471 | H3 | 3 | Improving | 0.7 | 95 | 124 | 145 | 122.6667 | 0.2 | 21 | 43 | 79 | 45.3333 | 0 | 84.4167 | 1 | 2.5325
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.2 | 3.843 | 0.76859 | H2 | 4 | Stable | 0.9 | 86 | 128 | 159 | 126.1667 | 0.3 | 31 | 40 | 74 | 44.1667 | 0 | 60 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Performance (collector opportunity) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.373 | 19.5316 | 7.2853 | -- | 0.4158 | 19.5316 | 8.1213 | H1 | 5 | Stable | [10 empty] | 0 | -11.4745 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.3 | 20.8767 | 6.263 | H1 | 5 | Stable | 0.9 | 120 | 132 | 145 | 132.1667 | 0.1 | 3 | 53 | 75 | 48.3333 | 50 | 25 | 0 | 30
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.504 | 73.3644 | 36.9756 | Reduce | 0.2975 | 53.773 | 15.9975 | H1 | 5 | Worsening | 0.7 | 104 | 137 | 146 | 133 | 0.2 | 26 | 44 | 69 | 45.1667 | 26.7042 | 40.9722 | 0 | 16.0225
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK308 | Project_024_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System robustness and resilience | Person_774 | 2017-04-06 | 2018-06-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.1 | 2.5966 | 0.25966 | H3 | 3 | Stable | 0.7 | 119 | 140 | 143 | 137 | 0.1 | 22 | 54 | 75 | 52.1667 | 58.3333 | 66.6667 | 1 | 37
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-21 21:00 | 2016-12-20 21:00 | 0.3 | 1.5935 | 0.47805 | Reduce | 0.3 | 0.84455 | 0.25337 | H2 | 4 | Stable | 0.7 | 119 | 126 | 153 | 129.3333 | 0.2 | 25 | 45 | 76 | 46.8333 | 47 | 0 | 0 | 28.2
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-21 21:00 | 2016-12-20 21:00 | 0.5 | 4.7805 | 2.3902 | Avoid | 0.2 | 1.3279 | 0.26558 | H3 | 3 | Stable | [10 empty] | 72.2222 | 60 | 1 | 45.1333
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-18 21:00 | 0.4 | 3.187 | 1.2748 | Reduce | 0.2 | 1.5935 | 0.3187 | H3 | 3 | Stable | 0.5 | 85 | 133 | 159 | 129.3333 | 0.3 | 37 | 52 | 60 | 50.8333 | 50 | 50 | 1 | 31.5
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK003 | Project_001_RISK003 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Non-Recurring Engineering higher than expected | Person_674 | 2017-12-21 | 2018-08-21 | 0.5 | 16.0059 | 8.0029 | Reduce | 0.2 | 8.0029 | 1.6006 | H3 | 3 | Improving | 0.9 | 88 | 134 | 157 | 130.1667 | 0.4 | 7 | 45 | 63 | 41.6667 | 50 | 60 | 0 | 30
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Availability of key resource within Engineering | Person_693 | 2018-01-21 01:00 | 2019-05-23 | 0.1 | 4.8729 | 3.8983 | Accept | 0.2 | 4.8729 | 3.8983 | H3 | 3 | Stable | 0.6 | 104 | 132 | 159 | 131.8333 | 0.6 | 104 | 132 | 159 | 131.8333 | 0 | -100 | 1 | -3
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_238 | 2017-05-23 | 2019-01-21 01:00 | 0.5 | 2.6676 | 0.53353 | Accept | 0.5 | 2.6676 | 0.53353 | H2 | 4 | Stable | 0.5 | 117 | 123 | 150 | 126.5 | 0.5 | 117 | 123 | 150 | 126.5 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Production - Design Changes | Person_547 | 2017-05-23 | 2018-06-22 | 0.1 | 1.6721 | 0.66883 | Accept | 0.1 | 1.6721 | 0.50162 | H3 | 3 | Stable | 0.7 | 99 | 132 | 152 | 129.8333 | 0.7 | 99 | 132 | 152 | 129.8333 | 0 | 0 | 1 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_238 | 2017-04-22 | 2018-05-22 | 0.25 | 3.3227 | 0.83067 | Reduce | 0.012 | 3.3055 | 0.039667 | H3 | 3 | Stable | 0.5 | 106 | 133 | 144 | 130.3333 | 0.2 | 2 | 46 | 77 | 43.8333 | 0.51615 | 95.2 | 1 | 3.1657
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unforseen and substantial increase in Repairs workload during new build production period. | Person_238 | 2017-10-23 01:00 | 2019-08-21 01:00 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.25 | 1.5434 | 0.38586 | H2 | 4 | Stable | 0.8 | 97 | 136 | 144 | 130.8333 | 0.3 | 24 | 48 | 65 | 46.8333 | 0 | 16.6667 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK007 | Project_041_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Advanced production of products using a Qual. standard component rather than a Prod. standard | Person_547 | 2017-10-21 01:00 | 2018-06-22 | 0.49 | 1.2862 | 0.63024 | Reduce | 0.2 | 1.2862 | 0.25724 | H3 | 3 | Stable | 0.9 | 94 | 128 | 154 | 126.6667 | 0.1 | 19 | 49 | 76 | 48.5 | 0 | 59.1837 | 1 | 1.7755
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_693 | 2018-03-23 | 2018-05-22 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.7 | 117 | 136 | 153 | 135.6667 | 0.3 | 26 | 49 | 66 | 48 | 0 | 50 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Production - Supplier Quality | Person_468 | 2017-05-23 | 2019-08-20 | 0.25 | 1.9722 | 0.98609 | Accept | 0.1 | 1.9722 | 0.98609 | H3 | 3 | Improving | 0.8 | 103 | 139 | 156 | 135.8333 | 0.8 | 103 | 139 | 156 | 135.8333 | 0 | 60 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-19 22:00 | 0.05 | 1.7492 | 0.17492 | Accept | 0.03 | 1.7492 | 0.12944 | H2 | 4 | Stable | 0.5 | 119 | 128 | 156 | 131.1667 | 0.5 | 119 | 128 | 156 | 131.1667 | 0 | 40 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2018-04-22 | 0.8 | 2.5081 | 1.2541 | Accept | 0.6 | 2.5081 | 1.2541 | H1 | 5 | Stable | 0.7 | 111 | 138 | 156 | 136.5 | 0.7 | 111 | 138 | 156 | 136.5 | 0 | 25 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Test Equipment (Second Test Set) | Person_238 | 2017-05-23 | 2018-05-22 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.15 | 0.68598 | 0.1029 | H3 | 3 | Stable | 0.7 | 106 | 121 | 157 | 124.5 | 0.3 | 32 | 49 | 69 | 49.5 | 0 | 40 | 1 | 1.2
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-26 22:00 | 2018-05-22 | 0.1 | 3.7514 | 0.37514 | Accept | 0.05 | 3.7514 | 0.37514 | H2 | 4 | Stable | 0.6 | 98 | 135 | 159 | 132.8333 | 0.6 | 98 | 135 | 159 | 132.8333 | 0 | 50 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2017-05-23 | 2019-08-20 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Improving | 0.8 | 113 | 139 | 156 | 137.5 | 0.1 | 33 | 48 | 69 | 49 | 0 | 60 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2018-05-21 | 0.2 | 7.2784 | 2.1835 | Accept | 0.2 | 7.2784 | 2.1835 | H3 | 3 | Worsening | 0.6 | 86 | 137 | 157 | 131.8333 | 0.6 | 86 | 137 | 157 | 131.8333 | 0 | 0 | 1 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2018-04-22 | 0.3 | 3.0869 | 0.30869 | Accept | 0.2 | 3.0869 | 0.30869 | H3 | 3 | Stable | 0.6 | 111 | 132 | 159 | 133 | 0.6 | 111 | 132 | 159 | 133 | 0 | 33.3333 | 0 | 0
2018-03-23 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-010 | Project_052_Risk-010 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Potential update of software / hardware required during the 3 year support period (RESOURCE) | Person_376 | 2017-08-19 | 2018-02-19 | 0.25 | 3.1214 | 0.78035 | Transfer | 0.25 | 3.1214 | 0.78035 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2017-02-20 01:00 | 2018-05-22 | 0.1 | 8.5887 | 0.85887 | Accept | 0.1 | 8.5887 | 0.85887 | H3 | 3 | Stable | 0.6 | 86 | 136 | 147 | 129.5 | 0.6 | 86 | 136 | 147 | 129.5 | 0 | 0 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_038 | 2020-05-23 | 2023-10-26 | 0.2 | 7.4599 | 1.492 | Reduce | 0.05 | 7.4599 | 0.37299 | H2 | 4 | Stable | 0.7 | 96 | 135 | 143 | 129.8333 | 0.4 | 27 | 52 | 62 | 49.5 | 0 | 75 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK003 | Project_024_RISK003 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance | Person_288 | 2017-12-21 01:00 | 2018-08-21 | 0.31667 | 2.1974 | 0.21974 | Accept | 0.007456 | 2.1974 | 0.21974 | H2 | 4 | Stable | 0.5 | 99 | 138 | 146 | 132.8333 | 0.5 | 99 | 138 | 146 | 132.8333 | 0 | 97.6455 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Management Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 0.3 | 8.7429 | 1.7486 | Accept | 0.3 | 8.7429 | 1.7486 | H1 | 5 | Improving | 0.6 | 103 | 129 | 141 | 126.6667 | 0.6 | 103 | 129 | 141 | 126.6667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before part b finished | Person_119 | 2016-10-20 01:00 | 2018-04-21 | 0.3 | 0 | 0 | Accept | 0.27 | 0 | 0 | H2 | 4 | Worsening | 0.6 | 119 | 122 | 143 | 125 | 0.6 | 119 | 122 | 143 | 125 |  | 10 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK016 | Project_038_RISK016 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Supplier Quality Issues | Person_397 | 2012-11-20 | 2018-08-22 | 0.5 | 5.0339 | 2.517 | Avoid | 0.5 | 5.0339 | 2.517 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK018 | Project_038_RISK018 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Last System Syndrome | Person_329 | 2012-11-20 | 2018-10-21 | 0.15 | 43.4175 | 6.5126 | -- | 0.1288 | 43.4175 | 5.5922 | H2 | 4 | Worsening | [10 empty] | 0 | 14.1333 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK003 | Project_060_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Misalignment of Critical Resource | Person_312 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.7 | 10.7688 | 7.5381 | Reduce | 0.5 | 10.7688 | 5.3844 | H2 | 4 | Stable | 0.8 | 83 | 135 | 153 | 129.3333 | 0.1 | 15 | 40 | 62 | 39.5 | 0 | 28.5714 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK024 | Project_063_RISK024 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Procurement/Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 0.8 | 0 | 0 | -- | 0.8 | 0 | 0 | H1 | 5 | Worsening | [11 empty] | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK004 | Project_060_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Cross-functional Estimates | Person_729 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.7 | 2.8845 | 2.0191 | Reduce | 0.5 | 2.8845 | 1.4422 | H2 | 4 | Improving | 0.6 | 91 | 130 | 142 | 125.5 | 0.2 | 15 | 45 | 61 | 42.6667 | 0 | 28.5714 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK022 | Project_063_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Equipment | Person_104 | 2018-01-14 01:00 | 2019-08-20 | 0.15 | 2.3618 | 0.35427 | -- | 0.15 | 2.3618 | 0.35427 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK013 | Project_041_RISK013 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional components validation | Person_693 | 2017-07-15 | 2018-05-23 | 0.4 | 1.1538 | 0.5769 | Accept | 0.3 | 1.1538 | 0.5769 | H2 | 4 | Stable | 0.8 | 91 | 126 | 148 | 123.8333 | 0.8 | 91 | 126 | 148 | 123.8333 | 0 | 25 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK004 | Project_063_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 2.861 | 0.57221 | Reduce | 0.15 | 2.861 | 0.42915 | H3 | 3 | Stable | 0.6 | 88 | 132 | 158 | 129 | 0.1 | 34 | 58 | 72 | 56.3333 | 0 | 25 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK001 | Project_060_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Procurement Prices | Person_033 | 2017-11-02 01:00 | 2018-08-20 | 0.7 | 1.4422 | 1.0096 | Reduce | 0.3 | 1.4422 | 0.43267 | H3 | 3 | Stable | 0.5 | 93 | 126 | 152 | 124.8333 | 0.3 | 4 | 46 | 60 | 41.3333 | 0 | 57.1429 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK014 | Project_063_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 0.1 | 8.3527 | 0.83527 | Avoid | 0.05 | 7.0086 | 0.35043 | H3 | 3 | Stable | [10 empty] | 16.092 | 50 | 0 | 9.6552
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK017 | Project_063_RISK017 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Increased build rate | Person_683 | 2017-11-12 01:00 | 2019-08-21 01:00 | 0.5 | 21.6065 | 10.8033 | -- | 0.5 | 21.6065 | 10.8033 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK005 | Project_063_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 1.214 | 0.72839 | -- | 0.5 | 1.214 | 0.60699 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK016 | Project_063_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.2 | 0.63077 | 0.12615 | -- | 0.2 | 0.63077 | 0.12615 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK002 | Project_063_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2020-05-22 | 0.15 | 8.6407 | 1.2961 | Avoid | 0.15 | 8.6407 | 1.2961 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK012 | Project_063_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Customer require additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.1 | 6.0485 | 0.60485 | Avoid | 0.1 | 6.0485 | 0.60485 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK018 | Project_063_RISK018 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Line Closure | Person_683 | 2019-08-21 01:00 | 2019-11-20 01:00 | 0.5 | 1.9058 | 0.95288 | -- | 0.5 | 4.3203 | 2.1602 | H2 | 4 | Improving | [10 empty] | -126.7001 | 0 | 0 | -76.0201
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK026 | Project_063_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Clause on Joint Proposal | Person_261 | 2018-05-04 | 2019-05-23 | 0.5 | 9.8888 | 4.9444 | -- | 0.5 | 9.8888 | 4.9444 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Risk of not being able to perform Tests | Person_238 | 2017-12-21 01:00 | 2019-01-21 01:00 | 0.5 | 13.4066 | 5.3626 | Accept | 0.5 | 13.4066 | 5.3626 | H2 | 4 | Stable | 0.7 | 111 | 135 | 158 | 134.8333 | 0.7 | 111 | 135 | 158 | 134.8333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-20 22:00 | 2017-08-19 22:00 | 0.1 | 53.0293 | 5.3029 | Reduce | 0.1 | 53.0293 | 5.3029 | H3 | 3 | Stable | 0.5 | 85 | 137 | 150 | 130.5 | 0.3 | 26 | 49 | 70 | 48.6667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of key resource within production, Procurement or Engineering | Person_725 | 2018-01-21 01:00 | 2019-05-23 | 0.1 | 0.20788 | 0.068599 | Accept | 0.074 | 31.0429 | 15.5215 | H3 | 3 | Stable | 0.5 | 105 | 130 | 160 | 130.8333 | 0.5 | 105 | 130 | 160 | 130.8333 | -14833.3191 | 26 | 1 | -8899.2115
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-20 22:00 | 2017-08-19 22:00 | 0.1 | 7.7469 | 0.77469 | Reduce | 0.1 | 7.7469 | 0.77469 | H3 | 3 | Stable | 0.8 | 85 | 128 | 146 | 123.8333 | 0.3 | 4 | 43 | 71 | 41.1667 | 0 | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_238 | 2017-05-23 | 2019-01-21 01:00 | 0.5 | 11.3437 | 0.56718 | Accept | 0.5 | 11.3437 | 0.56718 | H2 | 4 | Stable | 0.5 | 95 | 136 | 144 | 130.5 | 0.5 | 95 | 136 | 144 | 130.5 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | R054 | Project_066_R054 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | System Cybersecurity shortfalls | Person_549 | 2017-01-21 01:00 | 2024-05-23 | 0.8 | 15.7936 | 12.6349 | Reduce | 0.5 | 15.7936 | 7.8968 | H1 | 5 | Stable | 0.6 | 104 | 123 | 141 | 122.8333 | 0.3 | 20 | 44 | 71 | 44.5 | 0 | 37.5 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Production - Design Changes | Person_547 | 2017-05-23 | 2018-06-22 | 0.1 | 18.5516 | 12.9861 | Accept | 0.1 | 18.5516 | 12.9861 | H3 | 3 | Stable | 0.5 | 90 | 127 | 152 | 125 | 0.5 | 90 | 127 | 152 | 125 | 0 | 0 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK024 | Project_048_RISK024 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Procurement/Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 0.8 | 0 | 0 | -- | 0.8 | 0 | 0 | H1 | 5 | Worsening | [11 empty] | 0 | 0
2018-03-23 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-013 | Project_052_Risk-013 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional material and effort required to support the delta equipment | Person_376 | 2017-08-19 | 2018-03-22 | 0.3 | 8.8305 | 2.6492 | Accept | 0.3 | 8.8305 | 2.6492 | H3 | 3 | Stable | 0.7 | 108 | 132 | 151 | 131.1667 | 0.7 | 108 | 132 | 151 | 131.1667 | 0 | 0 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK017 | Project_048_RISK017 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Increased build rate | Person_683 | 2017-11-12 01:00 | 2019-08-21 01:00 | 0.5 | 7.7433 | 3.8716 | -- | 0.5 | 7.7433 | 3.8716 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK016 | Project_048_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.2 | 0.22605 | 0.045211 | -- | 0.2 | 0.22605 | 0.045211 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK018 | Project_048_RISK018 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Line Closure | Person_683 | 2019-08-21 01:00 | 2019-11-20 01:00 | 0.5 | 0.68298 | 0.34149 | -- | 0.5 | 1.5483 | 0.77415 | H2 | 4 | Improving | [10 empty] | -126.7001 | 0 | 0 | -76.0201
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK004 | Project_048_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 1.0253 | 0.20506 | Reduce | 0.15 | 1.0253 | 0.1538 | H3 | 3 | Stable | 0.7 | 88 | 137 | 147 | 130.5 | 0.4 | 3 | 40 | 75 | 39.6667 | 0 | 25 | 0 | 0
2018-03-23 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-004 | Project_052_Risk-004 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | IOC Risk for Phase 1b | Person_488 | 2017-08-19 | 2018-03-22 | 0.1 | 0 | 0 | Accept | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.6 | 91 | 132 | 141 | 126.6667 | 0.6 | 91 | 132 | 141 | 126.6667 |  | 0 | 0
2018-03-23 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-001 | Project_052_Risk-001 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Greater modification than expected for system uplift | Person_376 | 2017-08-19 | 2018-03-22 | 0.1 | 28.5076 | 7.1269 | Accept | 0.1 | 28.5076 | 2.8508 | H3 | 3 | Stable | 0.9 | 110 | 123 | 149 | 125.1667 | 0.9 | 110 | 123 | 149 | 125.1667 | 0 | 0 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK014 | Project_048_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 0.1 | 2.9934 | 0.29934 | Avoid | 0.05 | 2.5117 | 0.12558 | H3 | 3 | Stable | [10 empty] | 16.092 | 50 | 0 | 9.6552
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK005 | Project_048_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 0.43506 | 0.26104 | Avoid | 0.5 | 0.43506 | 0.21753 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK002 | Project_048_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2020-05-22 | 0.15 | 3.0966 | 0.46449 | Avoid | 0.15 | 3.0966 | 0.46449 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-03-23 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-009 | Project_052_Risk-009 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | System acceptance not costed in line with Customer expectations | Person_651 | 2017-08-19 | 2018-03-22 | 0.1 | 1.4099 | 0.42298 | Accept | 0.1 | 1.4099 | 0.42298 | H3 | 3 | Stable | 0.7 | 120 | 124 | 143 | 126.5 | 0.7 | 120 | 124 | 143 | 126.5 | 0 | 0 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK012 | Project_048_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Customer require additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.1 | 2.1676 | 0.21676 | Avoid | 0.1 | 2.1676 | 0.21676 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK022 | Project_048_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Equipment | Person_104 | 2018-01-14 01:00 | 2019-08-20 | 0.15 | 0.84641 | 0.12696 | -- | 0.15 | 0.84641 | 0.12696 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK026 | Project_048_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Clause on Joint Proposal | Person_261 | 2018-05-04 | 2019-05-23 | 0.5 | 3.5439 | 1.772 | -- | 0.5 | 3.5439 | 1.772 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS020 | Project_025_RS020 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Plant Machinery failure | Person_619 | 2017-03-23 | 2019-08-07 | 0.3 | 0.05293 | 0.015879 | Reduce | 0.3 | 0.05293 | 0.015879 | H2 | 4 | Stable | 0.6 | 106 | 134 | 148 | 131.6667 | 0.1 | 23 | 45 | 76 | 46.5 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS019 | Project_025_RS019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Product Component Failure | Person_619 | 2017-03-23 | 2019-08-07 | 0.7 | 0.82924 | 0.58047 | Reduce | 0.3 | 0.82924 | 0.24877 | H2 | 4 | Stable | 0.8 | 116 | 139 | 144 | 136 | 0.4 | 34 | 51 | 65 | 50.5 | 0 | 57.1429 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_373 | 2012-08-21 01:00 | 2019-08-07 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 2.2054 | 1.3453 | H1 | 5 | Stable | 0.7 | 89 | 125 | 141 | 121.6667 | 0.2 | 4 | 53 | 77 | 48.8333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK044 | Project_042_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2018-02-20 01:00 | 2018-12-21 01:00 | 0.32 | 6.5759 | 2.1043 | Reduce | 0.17 | 6.5759 | 1.1179 | H2 | 4 | Stable | 0.7 | 102 | 132 | 145 | 129.1667 | 0.4 | 29 | 43 | 61 | 43.6667 | 0 | 46.875 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK024 | Project_042_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2019-09-21 01:00 | 2020-09-19 01:00 | 0.33 | 9.3941 | 3.1001 | Reduce | 0.15 | 7.5153 | 1.1273 | H2 | 4 | Stable | 0.5 | 94 | 140 | 145 | 133.1667 | 0.2 | 17 | 41 | 65 | 41 | 20 | 54.5455 | 0 | 12
2018-04-22 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK006 | Project_060_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Secure material Handling | Person_033 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.5 | 4.6971 | 0.93941 | Accept | 0.5 | 3.7576 | 0.37576 | H2 | 4 | Stable | 0.5 | 85 | 121 | 151 | 120 | 0.5 | 85 | 121 | 151 | 120 | 20 | 0 | 0 | 12
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK045 | Project_042_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2019-01-22 01:00 | 2019-05-23 | 0.25 | 3.908 | 0.97699 | Reduce | 0.25 | 3.908 | 0.97699 | H2 | 4 | Stable | 0.8 | 92 | 136 | 151 | 131.1667 | 0.3 | 37 | 40 | 76 | 45.5 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--17 | Project_021_Risk--17 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to technical performance | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.5 | 113 | 127 | 145 | 127.6667 | 0.4 | 13 | 57 | 74 | 52.5 |  | 33.3333 | 1
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--39 | Project_021_Risk--39 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Delay to completion of product upgrade | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.7 | 90 | 125 | 149 | 123.1667 | 0.3 | 22 | 42 | 70 | 43.3333 |  | 40 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-184 | Project_032_Risk-184 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Manufacture of new Sub-systems | Person_629 | 2016-04-08 | 2018-02-18 22:00 | 0.33 | 2.6585 | 0.66463 | Accept | 0.5 | 2.6585 | 0.66463 | H1 | 5 | Stable | 0.7 | 84 | 121 | 150 | 119.6667 | 0.7 | 84 | 121 | 150 | 119.6667 | 0 | -51.5152 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--16 | Project_021_Risk--16 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of weather | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.8 | 104 | 129 | 154 | 129 | 0.4 | 39 | 56 | 76 | 56.5 |  | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-19 22:00 | 0.05 | 2.1419 | 0.53546 | Accept | 0.05 | 2.0479 | 0.40958 | H3 | 3 | Stable | 0.5 | 88 | 140 | 145 | 132.1667 | 0.5 | 88 | 140 | 145 | 132.1667 | 4.386 | 0 | 1 | 2.6316
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--15 | Project_021_Risk--15 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to lack of personnel resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.6 | 111 | 125 | 146 | 126.1667 | 0.2 | 31 | 44 | 77 | 47.3333 |  | 33.3333 | 1
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--14 | Project_021_Risk--14 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to late Trials Approval | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.6 | 115 | 127 | 154 | 129.5 | 0.2 | 23 | 51 | 76 | 50.5 |  | 66.6667 | 1
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK047 | Project_042_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables | Person_455 | 2020-11-20 01:00 | 2021-05-22 | 0.2 | 1.8788 | 0.18788 | Accept | 0.1 | 1.5031 | 0.12024 | H2 | 4 | Stable | 0.6 | 94 | 140 | 153 | 134.5 | 0.6 | 94 | 140 | 153 | 134.5 | 20 | 50 | 0 | 12
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--13 | Project_021_Risk--13 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Critical or Safety PR arises in Final build /Decision Point concludes new release req | Person_174 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.8 | 86 | 134 | 145 | 127.8333 | 0.3 | 27 | 46 | 67 | 46.3333 | 0 | 50 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK022 | Project_042_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2017-09-20 01:00 | 2018-09-20 01:00 | 0.2 | 1.8788 | 0.18788 | Accept | 0.18 | 1.5031 | 0.12024 | H2 | 4 | Stable | 0.5 | 101 | 139 | 151 | 134.6667 | 0.5 | 101 | 139 | 151 | 134.6667 | 20 | 10 | 0 | 12
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--12 | Project_021_Risk--12 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.7 | 102 | 129 | 158 | 129.3333 | 0.3 | 12 | 49 | 66 | 45.6667 | 0 | 33.3333 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK043 | Project_042_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st December | Person_455 | 2021-03-23 | 2021-05-22 | 0.1 | 0 | 0 | Accept | 0.08 | 0 | 0 | H3 | 3 | Stable | 0.9 | 86 | 125 | 154 | 123.3333 | 0.9 | 86 | 125 | 154 | 123.3333 |  | 20 | 1
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | R181 | Project_066_R181 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | USB Hub start up issues | Person_247 | 2017-01-21 01:00 | 2024-05-23 | 1 | 0.79775 | 0.039887 | Accept | 1 | 0.79775 | 0.039887 | H1 | 5 | Stable | 0.6 | 110 | 128 | 148 | 128.3333 | 0.6 | 110 | 128 | 148 | 128.3333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--11 | Project_021_Risk--11 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.5 | 106 | 134 | 141 | 130.5 | 0.3 | 2 | 40 | 75 | 39.5 | 7.8429 | 40 | 0 | 4.7058
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK046 | Project_042_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables - June | Person_455 | 2018-11-21 01:00 | 2020-11-19 01:00 | 0.2 | 10.3335 | 1.0334 | Accept | 0.1 | 10.3335 | 1.0334 | H2 | 4 | Stable | 0.8 | 106 | 124 | 160 | 127 | 0.8 | 106 | 124 | 160 | 127 | 0 | 50 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK023 | Project_042_RISK023 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2018-09-21 01:00 | 2019-09-20 01:00 | 0.2 | 11.2729 | 2.2546 | Accept | 0.1 | 11.2729 | 2.2546 | H2 | 4 | Stable | 0.6 | 112 | 137 | 146 | 134.3333 | 0.6 | 112 | 137 | 146 | 134.3333 | 0 | 50 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--10 | Project_021_Risk--10 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Stable | 0.5 | 80 | 124 | 150 | 121 | 0.2 | 7 | 59 | 60 | 50.5 | 0 | 57.1429 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK029 | Project_042_RISK029 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st October to 31st December | Person_455 | 2020-11-20 01:00 | 2021-05-22 | 0.25 | 3.7576 | 0.18788 | Accept | 0.1 | 3.7576 | 0.56365 | H2 | 4 | Stable | 0.7 | 92 | 123 | 142 | 121 | 0.7 | 92 | 123 | 142 | 121 | 0 | 60 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--32 | Project_021_Risk--32 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Lack of Customer resource to provide timely to Acceptance and Closure activities | Person_766 | 2018-10-22 01:00 | 2019-04-23 | 0.8 | 0 | 0 | Reduce | 0.4 | 0 | 0 | H2 | 4 | Stable | 0.7 | 95 | 138 | 147 | 132.3333 | 0.1 | 33 | 42 | 79 | 46.6667 |  | 50 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK048 | Project_042_RISK048 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | On the Job Training. | Person_371 | 2018-03-02 01:00 | 2019-02-05 01:00 | 0.85 | 2.1043 | 1.7886 | Reduce | 0.5 | 2.1043 | 1.0521 | H1 | 5 | Stable | 0.6 | 113 | 128 | 153 | 129.6667 | 0.4 | 16 | 42 | 75 | 43.1667 | 0 | 41.1765 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--18 | Project_021_Risk--18 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.5 | 86 | 139 | 152 | 132.3333 | 0.3 | 10 | 44 | 61 | 41.1667 | 50 | 28.5714 | 0 | 30
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK036 | Project_042_RISK036 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 2 | Person_455 | 2019-05-24 | 2020-05-22 | 0.25 | 4.6971 | 0.93941 | Accept | 0.2 | 3.7576 | 0.56365 | H2 | 4 | Stable | 0.8 | 110 | 134 | 154 | 133.3333 | 0.8 | 110 | 134 | 154 | 133.3333 | 20 | 20 | 0 | 12
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK039 | Project_042_RISK039 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality Issues 16th August to 15th August | Person_540 | 2020-01-06 01:00 | 2021-01-04 01:00 | 0.1 | 1.8788 | 0.46971 | Accept | 0.08 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.7 | 89 | 137 | 157 | 132.3333 | 0.7 | 89 | 137 | 157 | 132.3333 | 20 | 20 | 0 | 12
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--28 | Project_021_Risk--28 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort required to agree protocl for Client Server | Person_766 | 2018-03-23 | 2019-03-23 | 0.8 | 1.1522 | 0.92174 | Reduce | 0.4 | 1.1522 | 0.46087 | H2 | 4 | Stable | 0.6 | 116 | 121 | 144 | 124 | 0.4 | 21 | 46 | 79 | 47.3333 | 0 | 50 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK049 | Project_042_RISK049 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Industry STTE Upkeep. | Person_371 | 2018-03-02 01:00 | 2019-02-05 01:00 | 0.85 | 1.3152 | 1.1179 | Reduce | 0.5 | 1.3152 | 0.65759 | H2 | 4 | Stable | 0.8 | 96 | 129 | 157 | 128.1667 | 0.3 | 18 | 50 | 67 | 47.5 | 0 | 41.1765 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--05 | Project_021_Risk--05 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification delays | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Worsening | 0.5 | 81 | 123 | 142 | 119.1667 | 0.1 | 18 | 46 | 77 | 46.5 |  | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK033 | Project_042_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st April to 30 June | Person_455 | 2019-08-22 01:00 | 2019-11-20 01:00 | 0.2 | 1.8788 | 0.46971 | Accept | 0.15 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.7 | 109 | 125 | 146 | 125.8333 | 0.7 | 109 | 125 | 146 | 125.8333 | 20 | 25 | 0 | 12
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK035 | Project_042_RISK035 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st October to 31st December | Person_455 | 2021-02-20 01:00 | 2021-05-22 | 0.2 | 2.1388 | 0.21388 | Accept | 0.15 | 2.1388 | 0.21388 | H2 | 4 | Stable | 0.9 | 88 | 124 | 145 | 121.5 | 0.9 | 88 | 124 | 145 | 121.5 | 0 | 25 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK034 | Project_042_RISK034 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st July to 30 September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 0.2 | 2.2828 | 0.31959 | Accept | 0.15 | 2.2828 | 0.31959 | H2 | 4 | Stable | 0.8 | 101 | 125 | 147 | 124.6667 | 0.8 | 101 | 125 | 147 | 124.6667 | 0 | 25 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--04 | Project_021_Risk--04 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Final Qual test report delayed due to insufficient supply chain resource | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 0.2 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 120 | 122 | 144 | 125.3333 | 0.4 | 6 | 50 | 77 | 47.1667 |  | 50 | 1
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK040 | Project_042_RISK040 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st May to 30 Oct | Person_455 | 2019-09-21 01:00 | 2020-03-21 | 0.1 | 1.9998 | 0.39995 | Accept | 0.07 | 1.9998 | 0.39995 | H2 | 4 | Stable | 0.6 | 84 | 139 | 151 | 131.8333 | 0.6 | 84 | 139 | 151 | 131.8333 | 0 | 30 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--03 | Project_021_Risk--03 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.8 | 101 | 128 | 146 | 126.5 | 0.2 | 13 | 59 | 74 | 53.8333 | 0 | 33.3333 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--25 | Project_021_Risk--25 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of supporting resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.7 | 104 | 133 | 147 | 130.5 | 0.3 | 18 | 51 | 75 | 49.5 |  | 40 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--02 | Project_021_Risk--02 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_061 | 2018-02-20 01:00 | 2019-03-23 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.9 | 101 | 136 | 144 | 131.5 | 0.4 | 15 | 59 | 64 | 52.5 | 80 | 66.6667 | 0 | 48
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--24 | Project_021_Risk--24 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of equipment | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 97 | 129 | 159 | 128.6667 | 0.4 | 26 | 41 | 76 | 44.3333 |  | 40 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--01 | Project_021_Risk--01 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification/ delay due to build standard issue | Person_615 | 2018-02-20 01:00 | 2018-06-22 | 0.1 | 2.2183 | 0.22183 | Reduce | 0.05 | 2.2183 | 0.11091 | H2 | 4 | Stable | 0.7 | 115 | 122 | 152 | 125.8333 | 0.1 | 39 | 44 | 75 | 48.3333 | 0 | 50 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--21 | Project_021_Risk--21 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 95 | 140 | 158 | 135.5 | 0.2 | 27 | 48 | 70 | 48.1667 |  | 40 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--09 | Project_021_Risk--09 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 112 | 140 | 154 | 137.6667 | 0.2 | 13 | 44 | 60 | 41.5 |  | 40 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--35 | Project_021_Risk--35 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Delay to sub-system releases due to supply chain dependencies | Person_615 | 2018-01-21 01:00 | 2018-03-22 | 0.4 | 1.1744 | 0.46977 | Accept | 0.4 | 1.1744 | 0.46977 | H2 | 4 | Stable | 0.7 | 90 | 140 | 150 | 133.3333 | 0.7 | 90 | 140 | 150 | 133.3333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--08 | Project_021_Risk--08 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 0.4 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H3 | 3 | Stable | 0.8 | 85 | 130 | 142 | 124.5 | 0.1 | 29 | 53 | 74 | 52.5 |  | 62.5 | 1
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--07 | Project_021_Risk--07 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 0.6 | 17.2826 | 10.3696 | Reduce | 0.3 | 17.2826 | 5.1848 | H2 | 4 | Worsening | 0.6 | 99 | 125 | 159 | 126.3333 | 0.1 | 25 | 50 | 71 | 49.3333 | 0 | 50 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--20 | Project_021_Risk--20 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | ERP implementation | Person_061 | 2018-01-21 01:00 | 2018-07-20 | 0.5 | 0 | 0 | Reduce | 0.25 | 0 | 0 | H2 | 4 | Stable | 0.7 | 109 | 123 | 148 | 124.8333 | 0.1 | 4 | 40 | 62 | 37.6667 |  | 50 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK042 | Project_042_RISK042 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st February to 14th July | Person_455 | 2020-06-23 | 2020-12-03 01:00 | 0.1 | 0.78457 | 0.39228 | Accept | 0.08 | 0.78457 | 0.39228 | H2 | 4 | Stable | 0.8 | 98 | 125 | 155 | 125.5 | 0.8 | 98 | 125 | 155 | 125.5 | 0 | 20 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK041 | Project_042_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st Jan | Person_455 | 2020-03-23 | 2020-06-22 | 0.1 | 1.1744 | 0.23489 | Accept | 0.08 | 1.1744 | 0.23489 | H2 | 4 | Stable | 0.8 | 87 | 130 | 153 | 126.6667 | 0.8 | 87 | 130 | 153 | 126.6667 | 0 | 20 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--34 | Project_021_Risk--34 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Delay due to poor weather | Person_615 | 2018-03-23 | 2018-06-22 | 0.5 | 2.9361 | 0.58721 | Accept | 0.5 | 2.9361 | 0.58721 | H2 | 4 | Stable | 0.9 | 109 | 125 | 145 | 125.6667 | 0.9 | 109 | 125 | 145 | 125.6667 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Local customer Engineers in country | Person_455 | 2018-12-20 01:00 | 2021-05-22 | 0.05 | 1.0475 | 0.52377 | Accept | 0.05 | 1.0485 | 0.52426 | H2 | 4 | Stable | 0.8 | 86 | 121 | 155 | 120.8333 | 0.8 | 86 | 121 | 155 | 120.8333 | -0.092391 | 0 | 0 | -0.055435
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK026 | Project_042_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st Jan to 31st March | Person_455 | 2020-05-23 | 2020-08-20 01:00 | 0.25 | 1.0661 | 0.21322 | Accept | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.9 | 113 | 129 | 154 | 130.5 | 0.9 | 113 | 129 | 154 | 130.5 | 100 | 40 | 0 | 60
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer find issues with delivered parts or documentation | Person_294 | 2017-05-23 | 2019-08-20 | 0.4 | 9.0039 | 3.6016 | Reduce | 0.25 | 9.0039 | 2.251 | H2 | 4 | Improving | 0.5 | 86 | 122 | 151 | 120.8333 | 0.4 | 1 | 40 | 75 | 39.3333 | 0 | 37.5 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK025 | Project_042_RISK025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to 31 Dec | Person_455 | 2020-09-20 01:00 | 2021-05-22 | 0.2 | 0 | 0 | Accept | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.9 | 103 | 123 | 144 | 123.1667 | 0.9 | 103 | 123 | 144 | 123.1667 |  | 25 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK028 | Project_042_RISK028 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st July to 30th September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 0.25 | 1.0661 | 0.21322 | Accept | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.9 | 84 | 135 | 142 | 127.6667 | 0.9 | 84 | 135 | 142 | 127.6667 | 100 | 40 | 0 | 60
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK002 | Project_058_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence of key parts | Person_236 | 2017-05-23 | 2019-08-07 | 0.5 | 6.7334 | 3.3667 | Reduce | 0.25 | 6.7334 | 1.6833 | H2 | 4 | Stable | 0.9 | 83 | 131 | 153 | 126.6667 | 0.1 | 12 | 42 | 69 | 41.5 | 0 | 50 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 0.45943 | 0.18377 | H2 | 4 | Stable | 0.9 | 91 | 121 | 160 | 122.5 | 0.2 | 33 | 56 | 73 | 55 | 88.3943 | 20 | 0 | 53.0366
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_703 | 2015-05-24 | 2017-11-19 01:00 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 1.1996 | 0.17994 | H3 | 3 | Stable | 0.5 | 84 | 122 | 153 | 120.8333 | 0.1 | 30 | 52 | 61 | 49.8333 | 80.9521 | 70 | 1 | 50.6713
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK052 | Project_058_RISK052 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | sub-System Cleanliness | Person_294 | 2017-05-23 | 2018-09-20 01:00 | 0.75 | 13.3102 | 9.9826 | Reduce | 0.2 | 13.3102 | 2.662 | H3 | 3 | Stable | 0.6 | 89 | 126 | 151 | 124 | 0.1 | 19 | 50 | 71 | 48.3333 | 0 | 73.3333 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Open PR's | Person_319 | 2018-04-22 | 2018-11-20 01:00 | 0.5 | 7.6338 | 3.8169 | Reduce | 0.3 | 7.6338 | 2.2901 | H3 | 3 | Improving | 0.8 | 113 | 127 | 141 | 127 | 0.4 | 1 | 58 | 73 | 51 | 0 | 40 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK027 | Project_042_RISK027 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st April to 30th June | Person_455 | 2020-08-21 01:00 | 2020-09-19 01:00 | 0.25 | 2.3975 | 2.3975 | Accept | 0.15 | 0.2811 | 0.2811 | H2 | 4 | Stable | 0.9 | 80 | 131 | 148 | 125.3333 | 0.9 | 80 | 131 | 148 | 125.3333 | 88.2751 | 40 | 0 | 52.965
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-115 | Project_011_Risk-115 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | SMEs are unavailable to support project activites | Person_431 | 2016-07-21 | 2018-08-21 | 0.2 | 0 | 0 | Avoid | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 50 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-058 | Project_011_Risk-058 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Programme delays | Person_147 | 2013-11-20 01:00 | 2018-11-20 01:00 | 0.25 | 1.5013 | 0.37532 | Reduce | 0.25 | 1.5013 | 0.37532 | H2 | 4 | Stable | 0.6 | 118 | 138 | 158 | 138 | 0.2 | 31 | 53 | 71 | 52.3333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-131 | Project_011_Risk-131 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Support team have not covered all obligations in support contract | Person_147 | 2016-05-24 | 2018-08-17 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-137 | Project_011_Risk-137 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Subsystem will not match Fidelity of Customer - does not accept | Person_147 | 2018-02-16 01:00 | 2018-09-20 01:00 | 0.4 | 0.11876 | 0.047505 | Avoid | 0.2 | 0.11876 | 0.023752 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--27 | Project_021_Risk--27 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PR rectification | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 0.1 | 0.34776 | 0.034776 | Accept | 0.1 | 0.34776 | 0.034776 | H2 | 4 | Stable | 0.8 | 96 | 128 | 158 | 127.6667 | 0.8 | 96 | 128 | 158 | 127.6667 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2018-04-22 | 2018-09-20 01:00 | 0.2 | 0.62279 | 0.12456 | Avoid | 0.2 | 0.62279 | 0.12456 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-09-20 01:00 | 0.2 | 1.8854 | 0.37708 | Reduce | 0.2 | 1.8854 | 0.37708 | H2 | 4 | Stable | 0.8 | 100 | 126 | 160 | 127.3333 | 0.1 | 36 | 41 | 64 | 44 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2018-06-23 | 2018-10-21 01:00 | 0.4 | 1.4138 | 0.56551 | Reduce | 0.4 | 1.4138 | 0.56551 | H2 | 4 | Stable | 0.5 | 87 | 131 | 142 | 125.5 | 0.1 | 24 | 55 | 68 | 52 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-09-20 01:00 | 0.4 | 0.19206 | 0.076826 | -- | 0.4 | 0.19206 | 0.076826 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-08-22 01:00 | 2018-11-20 01:00 | 0.4 | 0.58017 | 0.23207 | Avoid | 0.4 | 0.58017 | 0.23207 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK037 | Project_042_RISK037 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 1 | Person_455 | 2020-05-23 | 2021-05-22 | 0.14 | 0.49834 | 0.12459 | Accept | 0.14 | 0.49834 | 0.12459 | H2 | 4 | Stable | 0.9 | 80 | 131 | 145 | 124.8333 | 0.9 | 80 | 131 | 145 | 124.8333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-11-20 01:00 | 0.3 | 0.32389 | 0.097168 | Reduce | 0.3 | 0.32389 | 0.097168 | H2 | 4 | Stable | 0.7 | 100 | 131 | 141 | 127.5 | 0.4 | 16 | 57 | 68 | 52 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures during SAT | Person_182 | 2018-06-23 | 2018-10-21 01:00 | 0.2 | 0.19206 | 0.038413 | -- | 0.2 | 0.19206 | 0.038413 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_431 | 2017-05-24 | 2018-08-19 | 0.3 | 0.11933 | 0.035799 | -- | 0.3 | 0.022161 | 0.0066484 | H3 | 3 | Stable | [10 empty] | 81.4286 | 0 | 0 | 48.8571
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-117 | Project_011_Risk-117 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Avaliability for testing/reviews | Person_147 | 2018-04-06 | 2018-09-20 01:00 | 0.35 | 0 | 0 | Avoid | 0.35 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-129 | Project_011_Risk-129 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Signature of Work Authorisation documents | Person_422 | 2017-05-24 | 2018-06-21 | 0.4 | 0.12643 | 0.050573 | -- | 0.4 | 0.12643 | 0.050573 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-130 | Project_011_Risk-130 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer does not accept Voice Pronounciation | Person_187 | 2017-05-24 | 2018-07-20 | 0.25 | 0.090918 | 0.022729 | Avoid | 0.25 | 0.090918 | 0.022729 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--26 | Project_021_Risk--26 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional design effort required to satisfy SME feedback/input | Person_615 | 2018-01-21 01:00 | 2018-05-21 | 0.2 | 3.1344 | 1.5672 | Accept | 0.2 | 3.1344 | 1.5672 | H2 | 4 | Improving | 0.9 | 82 | 129 | 158 | 126 | 0.9 | 82 | 129 | 158 | 126 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Labour/Material Risk | Person_662 | 2015-05-24 | 2019-05-23 | 0.5 | 0.78901 | 0.3945 | Accept | 0.5 | 0.78901 | 0.3945 | H2 | 4 | Stable | 0.8 | 83 | 139 | 150 | 131.5 | 0.8 | 83 | 139 | 150 | 131.5 | 0 | 0 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.8 | 84 | 135 | 154 | 129.6667 | 0.1 | 4 | 57 | 64 | 49.3333 | 60.3671 | 58.3333 | 0 | 36.2202
2018-04-22 | ORG_001 | BA_002 | Portfolio_009 | Project_045 | RISK001 | Project_045_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour/T&S Overspend | Person_662 | 2017-01-21 01:00 | 2020-05-22 | 0.5 | 11.5024 | 4.601 | Accept | 0.5 | 11.5024 | 4.601 | H2 | 4 | Stable | 0.7 | 93 | 137 | 148 | 131.5 | 0.7 | 93 | 137 | 148 | 131.5 | 0 | 0 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-07 22:00 | 2020-09-20 22:00 | 0.1 | 12.7232 | 1.2723 | Reduce | 0.1 | 12.7232 | 1.2723 | H3 | 3 | Stable | 0.5 | 116 | 124 | 145 | 126.1667 | 0.1 | 10 | 46 | 64 | 43 | 0 | 0 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-20 22:00 | 2023-12-21 22:00 | 0.4 | 30.1969 | 12.0788 | Reduce | 0.25 | 30.1969 | 7.5492 | H2 | 4 | Stable | 0.6 | 118 | 133 | 160 | 135 | 0.4 | 23 | 40 | 71 | 42.3333 | 0 | 37.5 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | In-house development of sub-system estimate is low | Person_594 | 2016-03-23 | 2018-03-22 | 0.5 | 6.5118 | 3.2559 | Reduce | 0.2 | 1.506 | 0.30121 | H3 | 3 | Stable | 0.7 | 88 | 122 | 143 | 119.8333 | 0.1 | 6 | 42 | 74 | 41.3333 | 76.8722 | 60 | 0 | 46.1233
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 0.25 | 0.63626 | 0.15906 | Reduce | 0.05 | 0.63626 | 0.031813 | H3 | 3 | Stable | 0.5 | 107 | 135 | 150 | 132.8333 | 0.4 | 9 | 54 | 75 | 50 | 0 | 80 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Component Shock test failure | Person_661 | 2016-09-07 22:00 | 2019-11-14 22:00 | 0.4 | 0.8467 | 0.33868 | Reduce | 0.2 | 0.8467 | 0.16934 | H3 | 3 | Stable | 0.8 | 86 | 123 | 149 | 121.1667 | 0.4 | 36 | 46 | 64 | 47.3333 | 0 | 50 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-01-11 22:00 | 0.8 | 18.0459 | 14.4367 | Reduce | 0.2 | 3.0076 | 0.60153 | H3 | 3 | Stable | 0.6 | 118 | 135 | 144 | 133.6667 | 0.1 | 11 | 52 | 75 | 49 | 83.3335 | 75 | 1 | 52.2501
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 0.4 | 5.1004 | 2.0402 | Reduce | 0.2 | 2.5506 | 0.51013 | H3 | 3 | Stable | 0.6 | 97 | 123 | 143 | 122 | 0.2 | 26 | 40 | 73 | 43.1667 | 49.9917 | 50 | 0 | 29.995
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-20 22:00 | 2018-04-22 | 0.5 | 28.0275 | 14.0137 | Reduce | 0.1 | 28.0275 | 2.8027 | H3 | 3 | Stable | 0.8 | 112 | 123 | 156 | 126.6667 | 0.3 | 24 | 49 | 78 | 49.6667 | 0 | 80 | 1 | 2.4
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Unreliability of Hardware | Person_431 | 2016-06-23 | 2018-08-21 | 0.1 | 5.0032 | 3.5023 | Accept | 0.1 | 5.0032 | 3.5023 | H3 | 3 | Stable | 0.7 | 105 | 139 | 148 | 134.8333 | 0.7 | 105 | 139 | 148 | 134.8333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_147 | 2016-04-21 | 2018-08-21 | 0.25 | 18.4072 | 5.5222 | Accept | 0.25 | 18.4072 | 5.5222 | H3 | 3 | Stable | 0.6 | 110 | 132 | 147 | 130.8333 | 0.6 | 110 | 132 | 147 | 130.8333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-20 22:00 | 2020-08-19 22:00 | 0.5 | 3.4651 | 1.0395 | Accept | 0.5 | 3.4651 | 1.0395 | H2 | 4 | Stable | 0.9 | 85 | 124 | 160 | 123.5 | 0.9 | 85 | 124 | 160 | 123.5 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 3.4651 | 1.0395 | Accept | 0.5 | 3.4651 | 1.0395 | H2 | 4 | Stable | 0.8 | 95 | 136 | 155 | 132.3333 | 0.8 | 95 | 136 | 155 | 132.3333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | EMC non compliance | Person_047 | 2016-06-23 | 2019-12-26 22:00 | 0.7 | 3.935 | 2.7545 | Reduce | 0.5 | 3.935 | 1.9675 | H2 | 4 | Stable | 0.6 | 101 | 131 | 142 | 127.8333 | 0.3 | 30 | 54 | 65 | 51.8333 | 0 | 28.5714 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SubSystem System Design | Person_038 | 2017-09-30 22:00 | 2019-11-19 22:00 | 0.2 | 1.5213 | 0.30425 | Reduce | 0.1 | 1.5213 | 0.15213 | H3 | 3 | Stable | 0.8 | 114 | 138 | 155 | 136.8333 | 0.3 | 34 | 47 | 66 | 48 | 0 | 50 | 1 | 1.5
2018-04-22 | ORG_001 | BA_002 | Portfolio_009 | Project_051 | RISK001 | Project_051_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Generic Labour or Material Overspend | Person_577 | 2012-05-23 | 2021-05-22 | 0.5 | 67.8016 | 27.1206 | Accept | 0.5 | 67.8016 | 27.1206 | H3 | 3 | Stable | 0.7 | 105 | 135 | 151 | 132.6667 | 0.7 | 105 | 135 | 151 | 132.6667 | 0 | 0 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-06-06 | 0.4 | 1.0142 | 0.40567 | Reduce | 0.1 | 1.0142 | 0.10142 | H3 | 3 | Stable | 0.9 | 96 | 126 | 142 | 123.6667 | 0.1 | 27 | 45 | 60 | 44.5 | 0 | 75 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | 9. Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 0.8 | 19.1678 | 15.3343 | Reduce | 0.2 | 2.8752 | 0.57503 | H3 | 3 | Stable | 0.7 | 115 | 132 | 153 | 132.6667 | 0.4 | 27 | 55 | 73 | 53.3333 | 85 | 75 | 0 | 51
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-05 22:00 | 2019-09-12 22:00 | 0.8 | 8.0322 | 6.4258 | Reduce | 0.5 | 4.006 | 2.003 | H2 | 4 | Stable | 0.5 | 116 | 127 | 145 | 128.1667 | 0.1 | 23 | 47 | 71 | 47 | 50.1263 | 37.5 | 0 | 30.0758
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 0.3 | 1.2677 | 0.12677 | Accept | 0.3 | 1.2677 | 0.12677 | H3 | 3 | Stable | 0.8 | 98 | 131 | 156 | 129.6667 | 0.8 | 98 | 131 | 156 | 129.6667 | 0 | 0 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK002 | Project_065_RISK002 | Opportunitity | Project Contingency | Open | H1 | 5 | 12. Acquisition and offsets | New supplier for enclosure | Person_598 | 2015-01-06 22:00 | 2017-10-18 22:00 | 0.05 | 9.6346 | 0.48173 | Exploit | 0.7 | 9.6346 | 6.7442 | H1 | 5 | Stable | [10 empty] | 0 | -1300 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier Selection Process | Person_379 | 2017-10-18 22:00 | 2019-04-23 | 0.4 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 110 | 129 | 153 | 129.8333 | 0.4 | 1 | 56 | 67 | 48.6667 |  | 25 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Colour Representation in Video Image Distortion | Person_305 | 2017-09-21 22:00 | 2020-03-21 | 0.5 | 5.5323 | 2.7662 | Reduce | 0.1 | 5.5323 | 0.55323 | H3 | 3 | Stable | 0.6 | 119 | 124 | 148 | 127.1667 | 0.1 | 35 | 52 | 64 | 51.1667 | 0 | 80 | 1 | 2.4
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-20 22:00 | 0.8 | 35.2369 | 28.1895 | Reduce | 0.3 | 18.4979 | 5.5494 | H2 | 4 | Stable | 0.8 | 107 | 135 | 157 | 134 | 0.3 | 19 | 41 | 66 | 41.5 | 47.5042 | 62.5 | 0 | 28.5025
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 4 | 9. Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-20 22:00 | 0.7 | 20.6835 | 14.4785 | Reduce | 0.3 | 20.6835 | 6.2051 | H2 | 4 | Stable | 0.5 | 89 | 125 | 142 | 121.8333 | 0.4 | 13 | 45 | 67 | 43.3333 | 0 | 57.1429 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 4 | 8. System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 0.6 | 5.2585 | 3.1551 | Reduce | 0.15 | 5.2585 | 0.78877 | H2 | 4 | Stable | 0.7 | 97 | 132 | 160 | 130.8333 | 0.4 | 26 | 59 | 62 | 54 | 0 | 75 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-04-21 | 0.3 | 2.723 | 0.81691 | Reduce | 0.1 | 2.723 | 0.2723 | H3 | 3 | Improving | 0.5 | 106 | 125 | 143 | 124.8333 | 0.4 | 32 | 48 | 61 | 47.5 | 0 | 66.6667 | 1 | 2
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-07 22:00 | 2020-09-20 22:00 | 0.2 | 4.8444 | 0.96888 | Reduce | 0.2 | 4.8444 | 0.96888 | H3 | 3 | Stable | 0.7 | 113 | 135 | 148 | 133.5 | 0.2 | 33 | 50 | 68 | 50.1667 | 0 | 0 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System Performance | Person_305 | 2016-09-07 22:00 | 2020-09-20 22:00 | 0.15 | 5.8725 | 0.88088 | Reduce | 0.05 | 5.8725 | 0.29363 | H2 | 4 | Stable | 0.7 | 101 | 126 | 158 | 127.1667 | 0.1 | 35 | 46 | 78 | 49.5 | 0 | 66.6667 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_038 | 2020-05-23 | 2023-10-25 22:00 | 0.2 | 7.4599 | 1.492 | Reduce | 0.05 | 7.4599 | 0.37299 | H2 | 4 | Stable | 0.9 | 84 | 139 | 152 | 132 | 0.1 | 1 | 59 | 64 | 50.1667 | 0 | 75 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-28 22:00 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.7 | 119 | 123 | 152 | 127.1667 | 0.2 | 16 | 58 | 67 | 52.5 | 60.3671 | 58.3333 | 0 | 36.2202
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-19 22:00 | 0.4 | 2.8643 | 1.1457 | Reduce | 0.1 | 2.8643 | 0.28643 | H3 | 3 | Stable | 0.5 | 87 | 126 | 143 | 122.3333 | 0.2 | 9 | 52 | 76 | 48.8333 | 0.0015933 | 75 | 1 | 2.251
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power Supply - Motor Controller Interface | Person_047 | 2016-05-23 | 2018-04-21 | 0.5 | 25.3543 | 12.6771 | Reduce | 0.2 | 25.3543 | 5.0709 | H3 | 3 | Stable | 0.8 | 115 | 134 | 144 | 132.5 | 0.4 | 21 | 44 | 79 | 46 | 0 | 60 | 1 | 1.8
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_061 | RISK003 | Project_061_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Test equipment reliability | Person_104 | 2017-05-23 | 2020-11-18 22:00 | 0.4 | 0.11013 | 0.044051 | Reduce | 0.3 | 0.11013 | 0.033038 | H2 | 4 | Stable | 0.9 | 95 | 123 | 160 | 124.5 | 0.4 | 32 | 49 | 73 | 50.1667 | 0 | 25 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-119 | Project_029_Risk-119 | Opportunitity | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Not required to support on load & offload of Customer Furnished Equipmnet | Person_585 | 2017-05-23 | 2020-04-16 | 0.8 | 5.1334 | 4.1067 | Exploit | 0.8 | 3.4137 | 2.731 | H2 | 4 | Stable | [10 empty] | 33.5 | 0 | 0 | 20.1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-23 | 2024-05-22 | 0.1 | 27.1644 | 0.81493 | Accept | 0.1 | 12.8336 | 0.38501 | H3 | 3 | Improving | 0.5 | 104 | 124 | 155 | 125.8333 | 0.5 | 104 | 124 | 155 | 125.8333 | 52.7559 | 0 | 1 | 31.6535
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2018-03-22 | 2019-07-21 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.6 | 99 | 127 | 146 | 125.5 | 0.3 | 37 | 49 | 75 | 51.3333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_585 | 2017-09-02 | 2018-10-31 | 0.1 | 6.4168 | 0.64168 | Transfer | 0.1 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sub-system FPGA | Person_332 | 2017-01-21 | 2019-05-16 | 0.4 | 1.5914 | 0.63655 | Reduce | 0.2 | 1.5914 | 0.31827 | H3 | 3 | Stable | 0.7 | 104 | 131 | 147 | 129.1667 | 0.2 | 1 | 51 | 70 | 45.8333 | 0 | 50 | 1 | 1.5
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort for System HW/SW- System upgrade. | Person_199 | 2017-05-23 | 2019-09-18 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.2 | 2.5667 | 0.51334 | H3 | 3 | Stable | 0.6 | 95 | 137 | 145 | 131.3333 | 0.3 | 35 | 44 | 63 | 45.6667 | 0 | 33.3333 | 1 | 1
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.25 | 3.5934 | 0.89835 | H2 | 4 | Stable | 0.8 | 94 | 121 | 155 | 122.1667 | 0.1 | 29 | 58 | 69 | 55 | 0 | 50 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Minimum Order Quantities | Person_403 | 2017-11-20 | 2018-06-21 | 0.2 | 1.925 | 0.38501 | Exploit | 0.2 | 1.925 | 0.38501 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_403 | 2018-04-22 | 2018-08-22 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Worsening | 0.8 | 120 | 127 | 150 | 129.6667 | 0.1 | 39 | 56 | 66 | 54.8333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) at the System level on product platform - performed by 3rd parties | Person_102 | 2015-01-22 | 2020-10-21 | 0.4 | 0 | 0 | Transfer | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Sub-system / product system accreditation hindered by Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 | 2020-07-20 | 0.1 | 0.25667 | 0.025667 | Transfer | 0.1 | 0.25667 | 0.025667 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_694 | 2017-05-23 | 2018-10-07 | 0.3 | 0 | 0 | Transfer | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 66.6667 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 | 2018-05-15 | 0.3 | 0.89835 | 0.26951 | Transfer | 0.3 | 0.89835 | 0.26951 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 0.35 | 1.9208 | 0.67227 | Reduce | 0.25 | 1.9208 | 0.48019 | H2 | 4 | Stable | 0.6 | 99 | 125 | 160 | 126.5 | 0.2 | 30 | 42 | 64 | 43.6667 | 0 | 28.5714 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2018-03-22 | 2018-10-18 | 0.4 | 0.77001 | 0.30801 | Reduce | 0.3 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.7 | 112 | 127 | 156 | 129.3333 | 0.3 | 11 | 46 | 65 | 43.3333 | 0 | 25 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_694 | 2018-02-20 | 2018-09-20 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.6 | 106 | 122 | 145 | 123.1667 | 0.3 | 26 | 54 | 78 | 53.3333 | 0 | 28.5714 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_585 | 2017-09-22 | 2019-08-21 | 0.03 | 0 | 0 | Accept | 0.03 | 0 | 0 | H3 | 3 | Stable | 0.9 | 108 | 134 | 151 | 132.5 | 0.9 | 108 | 134 | 151 | 132.5 |  | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs | Person_403 | 2018-04-22 | 2018-08-22 | 0.5 | 0.5596 | 0.05596 | Accept | 0.5 | 0.5596 | 0.05596 | H2 | 4 | Stable | 0.5 | 87 | 135 | 144 | 128.5 | 0.5 | 87 | 135 | 144 | 128.5 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 | 2019-10-21 | 0.25 | 2.3503 | 0.47006 | Accept | 0.25 | 2.3503 | 0.47006 | H2 | 4 | Stable | 0.6 | 110 | 121 | 157 | 125.1667 | 0.6 | 110 | 121 | 157 | 125.1667 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 | 0.3 | 4.4768 | 2.2384 | Accept | 0.2 | 4.4768 | 2.2384 | H3 | 3 | Stable | 0.7 | 80 | 134 | 160 | 129.3333 | 0.7 | 80 | 134 | 160 | 129.3333 | 0 | 33.3333 | 1 | 1
2018-04-22 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_077 | 2016-01-22 01:00 | 2018-04-18 | 0.15 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Improving | 0.9 | 86 | 121 | 141 | 118.5 | 0.3 | 39 | 55 | 74 | 55.5 |  | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design [in addition to costed effort] | Person_332 | 2017-05-28 | 2018-11-30 | 0.2 | 6.3794 | 1.2759 | Accept | 0.2 | 6.3794 | 1.2759 | H3 | 3 | Improving | 0.7 | 104 | 124 | 145 | 124.1667 | 0.7 | 104 | 124 | 145 | 124.1667 | 0 | 0 | 1 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_585 | 2017-10-21 | 2019-07-21 | 0.333 | 23.5255 | 11.7628 | Accept | 0.333 | 23.5255 | 11.7628 | H2 | 4 | Stable | 0.7 | 98 | 128 | 149 | 126.5 | 0.7 | 98 | 128 | 149 | 126.5 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 60.4367 | 3.0218 | Accept | 0.3 | 60.4367 | 3.0218 | H2 | 4 | Improving | 0.8 | 93 | 134 | 156 | 130.8333 | 0.8 | 93 | 134 | 156 | 130.8333 | 0 | 25 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 | 2020-09-19 | 0.2 | 3.7727 | 2.6409 | Accept | 0.2 | 3.772 | 2.6404 | H3 | 3 | Stable | 0.8 | 95 | 135 | 154 | 131.5 | 0.8 | 95 | 135 | 154 | 131.5 | 0.019757 | 0 | 0 | 0.011854
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2019-07-21 | 0.3 | 5.8198 | 4.0739 | Accept | 0.2 | 5.8198 | 4.0739 | H3 | 3 | Stable | 0.5 | 94 | 129 | 158 | 128 | 0.5 | 94 | 129 | 158 | 128 | 0 | 33.3333 | 1 | 1
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | RISK008 | Project_029_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Impact of sub-system Design Changes [product dependency] | Person_332 | 2016-09-20 | 2019-08-15 | 0.7 | 0 | 0 | Accept | 0.7 | 0 | 0 | H2 | 4 | Stable | 0.6 | 119 | 125 | 150 | 128.1667 | 0.6 | 119 | 125 | 150 | 128.1667 |  | 0 | 0
2018-04-22 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-07-21 | 0.2 | 4.0291 | 0.80582 | Reduce | 0.15 | 4.0291 | 0.60437 | H2 | 4 | Improving | 0.7 | 106 | 121 | 143 | 122.1667 | 0.1 | 37 | 41 | 60 | 43.5 | 0 | 25 | 0 | 0
2018-04-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK044 | Project_053_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Product Hardening | Person_719 | 2018-03-23 | 2019-01-20 | 0.3 | 7.9015 | 2.3705 | Avoid | 0.3 | 7.9015 | 2.3705 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK015 | Project_053_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Equipment export licences | Person_252 | 2018-06-23 | 2019-07-22 | 0.3 | 2.586 | 0.77579 | Avoid | 0.1 | 2.586 | 0.2586 | H3 | 3 | Improving | [10 empty] | 0 | 66.6667 | 1 | 2
2018-04-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK006 | Project_053_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional UK integration of the System product | Person_719 | 2018-10-22 | 2019-01-21 | 0.2 | 6.3212 | 1.2642 | Avoid | 0.2 | 6.3212 | 1.2642 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 1 | 0
2018-04-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK005 | Project_053_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier Deiivery Schedule | Person_252 | 2018-01-21 | 2018-11-20 | 0.5 | 5.3299 | 2.665 | Reduce | 0.25 | 5.3299 | 1.3325 | H2 | 4 | Stable | 0.5 | 93 | 126 | 154 | 125.1667 | 0.3 | 29 | 47 | 66 | 47.1667 | 0 | 50 | 0 | 0
2018-04-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK010 | Project_053_RISK010 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Immaturity of the core product | Person_719 | 2018-08-22 | 2018-11-20 | 0.5 | 6.4649 | 3.2325 | Avoid | 0.7 | 6.4649 | 4.5254 | H1 | 5 | Worsening | [10 empty] | 0 | -40 | 0 | 0
2018-04-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK007 | Project_053_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Resources Uavailable | Person_252 | 2017-11-20 | 2019-08-21 | 0.5 | 10.3438 | 5.1719 | Reduce | 0.2 | 7.9015 | 1.5803 | H3 | 3 | Stable | 0.9 | 98 | 136 | 153 | 132.5 | 0.4 | 27 | 57 | 66 | 53.5 | 23.6111 | 60 | 1 | 15.9666
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Survey costs | Person_618 | 2016-04-22 | 2018-08-21 | 0.2 | 13.2573 | 2.6515 | Avoid | 0.2 | 13.2573 | 2.6515 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2018-10-21 01:00 | 0.05 | 33.9324 | 6.7865 | Accept | 0.05 | 33.9324 | 6.7865 | H3 | 3 | Improving | 0.6 | 103 | 133 | 145 | 130 | 0.6 | 103 | 133 | 145 | 130 | 0 | 0 | 1 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-099 | Project_008_Risk-099 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Risk on Consumables Exposure | Person_639 | 2017-08-04 | 2018-08-21 | 0.5 | 5.6817 | 2.8408 | Reduce | 0.5 | 5.6817 | 2.8408 | H3 | 3 | Stable | 0.8 | 111 | 135 | 141 | 132 | 0.4 | 27 | 59 | 61 | 54 | 0 | 0 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK004 | Project_059_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Cyber Security Obligations | Person_592 | 2017-10-21 01:00 | 2019-08-04 | 0.4 | 0.80829 | 0.32332 | Reduce | 0.2 | 0.80829 | 0.16166 | H3 | 3 | Stable | 0.5 | 98 | 138 | 145 | 132.5 | 0.3 | 4 | 49 | 68 | 44.6667 | 0 | 50 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK003 | Project_059_RISK003 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Catalyst Requirements | Person_278 | 2017-10-21 01:00 | 2019-02-20 01:00 | 0.4 | 0.80829 | 0.32332 | Reduce | 0.2 | 0.80829 | 0.16166 | H3 | 3 | Stable | 0.8 | 93 | 127 | 151 | 125.3333 | 0.3 | 4 | 42 | 62 | 39 | 0 | 50 | 0 | 0
2018-04-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK047 | Project_053_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Lab Availability | Person_252 | 2017-10-21 | 2020-01-22 | 0.5 | 0.60622 | 0.18186 | Accept | 0.2 | 0.60622 | 0.18186 | H3 | 3 | Improving | 0.5 | 87 | 124 | 143 | 121 | 0.5 | 87 | 124 | 143 | 121 | 0 | 60 | 1 | 1.8
2018-04-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK043 | Project_053_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Change in REACH/RoSH Legislation | Person_302 | 2017-11-20 | 2018-09-20 | 0.1 | 0.64865 | 0.32433 | Accept | 0.1 | 0.64865 | 0.32433 | H2 | 4 | Stable | 0.5 | 116 | 134 | 159 | 135.1667 | 0.5 | 116 | 134 | 159 | 135.1667 | 0 | 0 | 0 | 0
2018-04-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK046 | Project_053_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Un-Planned Production Activities | Person_252 | 2019-07-22 | 2020-01-22 | 0.5 | 1.7836 | 0.53509 | Accept | 0.2 | 1.7836 | 0.53509 | H3 | 3 | Stable | 0.5 | 108 | 131 | 151 | 130.5 | 0.5 | 108 | 131 | 151 | 130.5 | 0 | 60 | 1 | 1.8
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK002 | Project_059_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SW Compatibility | Person_517 | 2017-11-20 01:00 | 2018-10-22 01:00 | 0.3 | 1.6166 | 0.48497 | Reduce | 0.1 | 1.6166 | 0.16166 | H3 | 3 | Stable | 0.8 | 81 | 126 | 155 | 123.3333 | 0.3 | 22 | 50 | 79 | 50.1667 | 0 | 66.6667 | 1 | 2
2018-04-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK021 | Project_053_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Product documentation | Person_719 | 2018-08-22 | 2019-07-26 | 0.35 | 1.6166 | 0.32332 | Accept | 0.35 | 1.6166 | 0.32332 | H2 | 4 | Worsening | 0.5 | 88 | 125 | 159 | 124.5 | 0.5 | 88 | 125 | 159 | 124.5 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-034 | Project_008_SER-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_567 | 2018-05-22 | 2018-08-21 | 0.25 | 2.0207 | 0.40414 | Accept | 0.25 | 2.0207 | 0.40414 | H3 | 3 | Stable | 0.6 | 118 | 132 | 147 | 132.1667 | 0.6 | 118 | 132 | 147 | 132.1667 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-085 | Project_008_SER-085 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Insufficient LOE to manage the supply chain with reducing number of spares | Person_639 | 2017-04-22 | 2018-08-21 | 0.25 | 2.0207 | 0.20207 | Accept | 0.25 | 2.0207 | 0.20207 | H3 | 3 | Stable | 0.5 | 97 | 127 | 159 | 127.3333 | 0.5 | 97 | 127 | 159 | 127.3333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Repairs at Supplier | Person_567 | 2017-08-21 01:00 | 2018-08-21 | 0.3 | 8.7429 | 1.7486 | Accept | 0.3 | 8.7429 | 1.7486 | H2 | 4 | Stable | 0.8 | 88 | 140 | 154 | 133.6667 | 0.8 | 88 | 140 | 154 | 133.6667 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Lack of Spares Availability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 0.2 | 0 | 0 | Accept | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.6 | 117 | 126 | 148 | 128.1667 | 0.6 | 117 | 126 | 148 | 128.1667 |  | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-148 | Project_008_SER-148 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Demands but not provisioned | Person_639 | 2017-08-21 01:00 | 2018-08-21 | 0.3 | 6.1106 | 0.61106 | Accept | 0.3 | 6.1106 | 0.61106 | H3 | 3 | Stable | 0.5 | 92 | 138 | 141 | 130.8333 | 0.5 | 92 | 138 | 141 | 130.8333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-094 | Project_008_Risk-094 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Consumable Stock Levels | Person_567 | 2017-04-22 | 2018-08-21 | 0.5 | 6.1106 | 0.61106 | Accept | 0.5 | 6.1106 | 0.61106 | H3 | 3 | Stable | 0.7 | 104 | 121 | 144 | 122 | 0.7 | 104 | 121 | 144 | 122 | 0 | 0 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK009 | Project_059_RISK009 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Safety risk mitigations - UNCERTAINTY | Person_592 | 2017-10-21 01:00 | 2019-08-20 | 0.1 | 3.0553 | 0.61106 | Accept | 0.1 | 3.0553 | 0.61106 | H3 | 3 | Stable | 0.6 | 106 | 124 | 143 | 124.1667 | 0.6 | 106 | 124 | 143 | 124.1667 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.9 | 94 | 129 | 144 | 125.6667 | 0.2 | 1 | 46 | 73 | 43 | 25.8065 | 20 | 0 | 15.4839
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | FOC Acceptance | Person_499 | 2018-07-25 | 2018-08-19 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.15 | 8.471 | 1.2706 | H3 | 3 | Stable | 0.8 | 106 | 131 | 142 | 128.6667 | 0.3 | 10 | 55 | 71 | 50.1667 | -99.9999 | 57.1429 | 1 | -58.2857
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK001 | Project_059_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Critical Personnel | Person_162 | 2017-10-21 01:00 | 2019-08-04 | 0.2 | 0.50826 | 0.40661 | Accept | 0.2 | 0.50826 | 0.40661 | H3 | 3 | Stable | 0.8 | 87 | 123 | 141 | 120 | 0.8 | 87 | 123 | 141 | 120 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE-10 | Project_067_SE-10 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Configuration baseline unstable for Platform | Person_327 | 2017-10-26 01:00 | 2018-08-18 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.5 | 98 | 123 | 146 | 122.6667 | 0.2 | 2 | 40 | 71 | 38.8333 |  | 60 | 1
2018-04-22 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-R6 | Project_067_Risk-R6 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub-Contractor Performance - Support Services | Person_713 | 2017-08-21 01:00 | 2018-08-21 | 0.5 | 2.2502 | 1.1251 | Reduce | 0.5 | 2.2502 | 1.1251 | H2 | 4 | Stable | 0.9 | 120 | 133 | 160 | 135.3333 | 0.2 | 13 | 49 | 78 | 47.8333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-054 | Project_062_Risk-054 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | sub-system rework to reviised standard | Person_031 | 2017-07-21 | 2018-11-21 01:00 | 0.4 | 0.62744 | 0.25098 | Transfer | 0.4 | 0.62744 | 0.25098 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-010 | Project_062_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Resource | Person_479 | 2017-07-21 | 2019-02-21 01:00 | 0.4 | 7.5293 | 3.0117 | Reduce | 0.3 | 7.5293 | 2.2588 | H2 | 4 | Stable | 0.5 | 88 | 129 | 152 | 126 | 0.2 | 33 | 52 | 68 | 51.5 | 0 | 25 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-013 | Project_062_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Unavailability of Network | Person_479 | 2017-07-21 | 2018-07-08 | 0.25 | 3.5555 | 0.88888 | Reduce | 0.2 | 3.5555 | 0.7111 | H3 | 3 | Stable | 0.6 | 104 | 123 | 146 | 123.6667 | 0.1 | 19 | 42 | 67 | 42.3333 | 0 | 20 | 1 | 0.6
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-055 | Project_062_Risk-055 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Supplier integration and Apps | Person_245 | 2017-07-21 | 2018-11-21 01:00 | 0.75 | 2.0915 | 1.5686 | Reduce | 0.75 | 2.0915 | 1.5686 | H2 | 4 | Stable | 0.5 | 85 | 133 | 144 | 126.8333 | 0.1 | 3 | 55 | 60 | 47.1667 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-011 | Project_062_Risk-011 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Variant deviations between SW | Person_479 | 2017-07-21 | 2018-06-22 | 0.4 | 0.71808 | 0.28723 | Reduce | 0.3 | 0.71808 | 0.21542 | H2 | 4 | Stable | 0.9 | 105 | 136 | 155 | 134 | 0.4 | 20 | 45 | 67 | 44.5 | 0 | 25 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-056 | Project_062_Risk-056 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Supplier integration acceptance by end Customer | Person_031 | 2017-07-21 | 2018-11-21 01:00 | 0.3 | 1.8823 | 0.5647 | Reduce | 0.3 | 1.8823 | 0.5647 | H3 | 3 | Stable | 0.7 | 103 | 122 | 148 | 123.1667 | 0.1 | 8 | 47 | 67 | 43.8333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-017 | Project_062_Risk-017 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer platform Schedule Unknown | Person_459 | 2017-07-21 | 2018-10-22 01:00 | 0.2 | 2.5098 | 0.50196 | Avoid | 0.1 | 2.5098 | 0.25098 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-037 | Project_062_Risk-037 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Server availability | Person_459 | 2017-07-21 | 2018-09-20 01:00 | 0.35 | 4.183 | 1.464 | Avoid | 0.1 | 4.183 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 71.4286 | 1 | 2.1429
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-016 | Project_062_Risk-016 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier Component Unavailability | Person_664 | 2017-07-21 | 2018-09-20 01:00 | 0.3 | 4.183 | 1.2549 | Reduce | 0.2 | 4.183 | 0.83659 | H3 | 3 | Stable | 0.8 | 113 | 127 | 154 | 129.1667 | 0.2 | 22 | 57 | 62 | 52 | 0 | 33.3333 | 1 | 1
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-020 | Project_062_Risk-020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Security Encryption Solution | Person_245 | 2017-07-21 | 2018-09-20 01:00 | 0.25 | 4.183 | 1.0457 | Reduce | 0.2 | 4.183 | 0.83659 | H2 | 4 | Improving | 0.6 | 105 | 128 | 149 | 127.6667 | 0.2 | 29 | 50 | 72 | 50.1667 | 0 | 20 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-021 | Project_062_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Hardware CoSupplierng | Person_664 | 2017-07-21 | 2018-09-20 01:00 | 0.3 | 7.5293 | 2.2588 | Reduce | 0.25 | 7.5293 | 1.8823 | H2 | 4 | Stable | 0.7 | 112 | 136 | 146 | 133.6667 | 0.4 | 25 | 57 | 61 | 52.3333 | 0 | 16.6667 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-043 | Project_062_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | User response | Person_459 | 2017-07-21 | 2019-02-21 01:00 | 0.35 | 3.3464 | 1.1712 | Avoid | 0.25 | 3.3464 | 0.83659 | H2 | 4 | Stable | [10 empty] | 0 | 28.5714 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-002 | Project_062_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | SDLC Card Obsolescence | Person_253 | 2017-07-21 | 2019-03-22 | 0.5 | 2.0915 | 1.0457 | Transfer | 0.2 | 2.0915 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 60 | 1 | 1.8
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-047 | Project_062_Risk-047 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Redhat6 on PCI shelf | Person_245 | 2017-07-21 | 2019-03-24 | 0.3 | 7.1808 | 2.1542 | Avoid | 0.3 | 7.1808 | 2.1542 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-025 | Project_062_Risk-025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | System Obsolescence Risk | Person_543 | 2017-07-21 | 2019-03-22 | 0.3 | 2.0915 | 0.62744 | Avoid | 0.2 | 2.0915 | 0.4183 | H2 | 4 | Stable | [10 empty] | 0 | 33.3333 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-022 | Project_062_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Registers Might Be Unstable | Person_479 | 2017-07-21 | 2018-08-19 | 0.25 | 1.3385 | 0.33464 | Reduce | 0.2 | 1.3385 | 0.26771 | H3 | 3 | Stable | 0.8 | 91 | 126 | 142 | 122.8333 | 0.3 | 1 | 40 | 60 | 36.8333 | 0 | 20 | 1 | 0.6
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-023 | Project_062_Risk-023 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Change In Security Boundary | Person_031 | 2017-07-21 | 2019-02-21 01:00 | 0.3 | 4.6013 | 1.3804 | Reduce | 0.2 | 4.6013 | 0.92025 | H3 | 3 | Stable | 0.8 | 84 | 129 | 146 | 124.3333 | 0.4 | 3 | 52 | 63 | 45.6667 | 0 | 33.3333 | 1 | 1
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-006 | Project_062_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unavailability of Hardware | Person_253 | 2017-07-21 | 2019-03-22 | 0.5 | 2.5098 | 1.2549 | Reduce | 0.25 | 2.5098 | 0.62744 | H2 | 4 | Stable | 0.7 | 106 | 140 | 147 | 135.5 | 0.1 | 33 | 47 | 61 | 47 | 0 | 50 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-048 | Project_062_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software lockdown features | Person_245 | 2017-07-21 | 2018-11-21 01:00 | 0.5 | 0.71808 | 0.35904 | Reduce | 0.5 | 0.71808 | 0.35904 | H2 | 4 | Stable | 0.8 | 105 | 130 | 156 | 130.1667 | 0.1 | 9 | 45 | 61 | 41.6667 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-005 | Project_062_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Security Solution Integration | Person_245 | 2017-07-21 | 2018-11-14 01:00 | 0.3 | 4.6013 | 1.3804 | Avoid | 0.25 | 4.6013 | 1.1503 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-012 | Project_062_Risk-012 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Integration Rig Move | Person_253 | 2018-05-23 | 2019-05-23 | 0.3 | 0.4183 | 0.12549 | Avoid | 0.3 | 0.4183 | 0.12549 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-024 | Project_062_Risk-024 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional SW Build post-Factory Acceptance Test | Person_253 | 2019-01-22 01:00 | 2019-04-22 | 0.3 | 1.7778 | 0.53333 | Avoid | 0.3 | 1.7778 | 0.53333 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-027 | Project_062_Risk-027 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Facility to Test modifications | Person_253 | 2018-08-22 01:00 | 2020-04-21 | 0.5 | 2.3703 | 1.1852 | Reduce | 0.4 | 2.3703 | 0.94814 | H2 | 4 | Stable | 0.8 | 98 | 137 | 147 | 132.1667 | 0.1 | 4 | 44 | 64 | 40.6667 | 0 | 20 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-008 | Project_062_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Paperwork for Legacy Items | Person_459 | 2018-03-23 | 2019-03-24 | 0.3 | 0.83659 | 0.25098 | Avoid | 0.3 | 0.83659 | 0.25098 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R008 | Project_044_Risk-R008 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Engineering Skills | Person_505 | 2017-10-21 01:00 | 2018-10-22 01:00 | 0.3 | 1.5695 | 0.47085 | Reduce | 0.3 | 1.4488 | 0.43463 | H2 | 4 | Stable | 0.6 | 94 | 136 | 159 | 132.8333 | 0.4 | 2 | 43 | 79 | 42.1667 | 7.6924 | 0 | 0 | 4.6155
2018-04-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R003 | Project_044_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Mono vs stereo Component | Person_358 | 2016-03-23 | 2018-10-22 01:00 | 0.7 | 14.4876 | 10.1413 | Reduce | 0.5 | 14.4876 | 7.2438 | H2 | 4 | Stable | 0.9 | 107 | 128 | 143 | 127 | 0.2 | 12 | 48 | 61 | 44.1667 | 0 | 28.5714 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-007 | Project_062_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Hardware Encryption / Protection | Person_253 | 2018-02-10 01:00 | 2019-03-22 | 0.3 | 4.183 | 1.2549 | Reduce | 0.3 | 4.183 | 1.2549 | H2 | 4 | Stable | 0.5 | 92 | 128 | 150 | 125.6667 | 0.4 | 23 | 54 | 79 | 53 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Interface implementation | Person_496 | 2018-07-25 | 2018-08-19 | 0.5 | 94.501 | 47.2505 | Accept | 0.25 | 94.501 | 47.2505 | H2 | 4 | Stable | 0.7 | 107 | 140 | 155 | 137 | 0.7 | 107 | 140 | 155 | 137 | 0 | 50 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of the platforms for modification | Person_496 | 2014-01-21 01:00 | 2019-04-10 | 0.67 | 1.6962 | 0.33923 | Accept | 0.67 | 1.6962 | 0.33923 | H2 | 4 | Stable | 0.7 | 118 | 122 | 151 | 126.1667 | 0.7 | 118 | 122 | 151 | 126.1667 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_523 | 2018-07-25 | 2018-08-19 | 0.35 | 42.7783 | 32.0837 | Accept | 0.2 | 42.7783 | 32.0837 | H2 | 4 | Stable | 0.9 | 82 | 136 | 143 | 128.1667 | 0.9 | 82 | 136 | 143 | 128.1667 | 0 | 42.8571 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2018-05-22 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.6 | 116 | 121 | 153 | 125.5 | 0.2 | 14 | 46 | 66 | 44 | 0 | 40 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-057 | Project_062_Risk-057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Supplier Application Encryption / Protection | Person_253 | 2017-07-21 | 2019-02-21 01:00 | 0.3 | 11.0894 | 0.55447 | Accept | 0.3 | 11.0894 | 0.33268 | H2 | 4 | Stable | 0.8 | 116 | 123 | 155 | 127.1667 | 0.8 | 116 | 123 | 155 | 127.1667 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 0.92411 | 0.55447 | Reduce | 0.5 | 0.36965 | 0.18482 | H2 | 4 | Stable | 0.9 | 120 | 125 | 159 | 129.8333 | 0.4 | 23 | 47 | 75 | 47.6667 | 60 | 16.6667 | 0 | 36
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-03 21:00 | 2018-04-21 | 0.2 | 4.0661 | 0.81322 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.7 | 112 | 121 | 142 | 123 | 0.4 | 18 | 55 | 69 | 51.1667 | 0 | 75 | 1 | 2.25
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.5 | 0.46206 | 0.23103 | H1 | 5 | Stable | 0.9 | 83 | 131 | 155 | 127 | 0.4 | 27 | 41 | 61 | 42 | 58.3333 | 16.6667 | 0 | 35
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-018 | Project_062_Risk-018 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Prioritisation - new or less experienced staff | Person_459 | 2017-07-21 | 2018-11-20 01:00 | 0.35 | 1.1089 | 0.88715 | Accept | 0.25 | 0.73929 | 0.44357 | H2 | 4 | Improving | 0.8 | 91 | 126 | 142 | 122.8333 | 0.8 | 91 | 126 | 142 | 122.8333 | 33.3333 | 28.5714 | 0 | 20
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-28 21:00 | 2018-05-22 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.7 | 100 | 131 | 153 | 129.5 | 0.2 | 2 | 56 | 63 | 48.1667 | 0 | 50 | 1 | 1.5
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2018-05-22 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.6 | 96 | 122 | 159 | 123.8333 | 0.1 | 21 | 46 | 65 | 45 | 0 | 25 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_693 | 2012-06-01 | 2018-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Improving | 0.8 | 85 | 127 | 158 | 125.1667 | 0.1 | 11 | 43 | 71 | 42.3333 | 0 | 40 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2018-05-21 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Stable | [10 empty] | 0 | 37.5 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-009 | Project_062_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Unresolved technical debt (excluding ILS) | Person_253 | 2017-07-21 | 2018-05-22 | 0.5 | 3.6965 | 0.36965 | Accept | 0.5 | 3.6965 | 0.18482 | H2 | 4 | Stable | 0.6 | 83 | 134 | 158 | 129.5 | 0.6 | 83 | 134 | 158 | 129.5 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-015 | Project_062_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Re-work | Person_253 | 2018-03-01 01:00 | 2019-05-22 | 0.5 | 0.92411 | 0.18482 | Accept | 0.5 | 0.92411 | 0.18482 | H2 | 4 | Stable | 0.8 | 113 | 137 | 151 | 135.3333 | 0.8 | 113 | 137 | 151 | 135.3333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2018-02-18 21:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.8 | 96 | 121 | 159 | 123.1667 | 0.3 | 35 | 40 | 70 | 44.1667 | 90 | 75 | 1 | 56.25
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK010 | Project_010_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Use of Lead components | Person_359 | 2012-05-23 | 2025-04-22 | 0.05 | 1.8482 | 0.092411 | Reduce | 0.05 | 1.8482 | 0.092411 | H3 | 3 | Stable | 0.9 | 114 | 121 | 150 | 124.6667 | 0.2 | 31 | 53 | 62 | 50.8333 | 0 | 0 | 1 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-22 01:00 | 2019-08-21 01:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-22 01:00 | 2019-08-21 01:00 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Volume of production tools and Jigs | Person_279 | 2016-11-22 23:00 | 2021-11-22 23:00 | 0.35 | 6.4382 | 2.2534 | Reduce | 0.15 | 6.4382 | 0.96573 | H2 | 4 | Stable | 0.9 | 80 | 129 | 145 | 123.5 | 0.3 | 14 | 40 | 60 | 39 | 0 | 57.1429 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software issue input | Person_279 | 2016-11-22 23:00 | 2023-02-19 23:00 | 0.4 | 49.4398 | 19.7759 | Reduce | 0.2 | 49.4398 | 9.888 | H2 | 4 | Stable | 0.5 | 92 | 132 | 159 | 129.8333 | 0.4 | 3 | 46 | 60 | 41.1667 | 0 | 50 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_547 | 2017-04-22 | 2018-08-21 | 0.25 | 3.3227 | 0.83067 | Reduce | 0.012 | 3.3055 | 0.039667 | H3 | 3 | Stable | 0.7 | 112 | 139 | 158 | 137.6667 | 0.4 | 37 | 52 | 69 | 52.3333 | 0.51615 | 95.2 | 1 | 3.1657
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Unforseen and substantial increase in Repairs workload during new build production period. | Person_547 | 2017-10-23 01:00 | 2019-08-21 01:00 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.25 | 1.5434 | 0.38586 | H2 | 4 | Stable | 0.8 | 81 | 137 | 141 | 128.3333 | 0.3 | 4 | 59 | 63 | 50.5 | 0 | 16.6667 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK007 | Project_041_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Advanced production of products using a Qual. standard component rather than a Prod. standard | Person_547 | 2017-10-21 01:00 | 2018-10-21 01:00 | 0.49 | 1.2862 | 0.63024 | Reduce | 0.2 | 1.2862 | 0.25724 | H3 | 3 | Stable | 0.8 | 88 | 126 | 149 | 123.5 | 0.3 | 27 | 44 | 74 | 46.1667 | 0 | 59.1837 | 1 | 1.7755
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-19 21:00 | 0.05 | 0.77172 | 0.54021 | Accept | 0.03 | 0.77172 | 0.38586 | H2 | 4 | Stable | 0.7 | 113 | 125 | 150 | 127.1667 | 0.7 | 113 | 125 | 150 | 127.1667 | 0 | 40 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Regulatory standards changes misunderstood | Person_693 | 2018-03-23 | 2018-07-21 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.8 | 116 | 137 | 141 | 134.1667 | 0.4 | 39 | 43 | 67 | 46.3333 | 0 | 50 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2018-04-22 | 0.8 | 1.9722 | 0.98609 | Accept | 0.6 | 1.9722 | 0.98609 | H1 | 5 | Stable | 0.5 | 118 | 122 | 155 | 126.8333 | 0.5 | 118 | 122 | 155 | 126.8333 | 0 | 25 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-26 21:00 | 2018-05-22 | 0.1 | 1.7492 | 0.17492 | Accept | 0.05 | 1.7492 | 0.17492 | H2 | 4 | Stable | 0.7 | 106 | 126 | 147 | 126.1667 | 0.7 | 106 | 126 | 147 | 126.1667 | 0 | 50 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2018-05-21 | 0.2 | 2.5081 | 1.2541 | Accept | 0.2 | 2.5081 | 1.2541 | H3 | 3 | Worsening | 0.7 | 102 | 136 | 145 | 131.8333 | 0.7 | 102 | 136 | 145 | 131.8333 | 0 | 0 | 1 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Production - Test Equipment (Second Test Set) | Person_686 | 2017-05-23 | 2018-09-20 01:00 | 0.25 | 0.68598 | 0.17149 | Reduce | 0.15 | 0.68598 | 0.1029 | H3 | 3 | Stable | 0.7 | 114 | 136 | 160 | 136.3333 | 0.1 | 21 | 56 | 63 | 51.3333 | 0 | 40 | 1 | 1.2
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2018-04-22 | 0.3 | 3.7514 | 0.37514 | Accept | 0.2 | 3.7514 | 0.37514 | H3 | 3 | Stable | 0.9 | 112 | 126 | 151 | 127.8333 | 0.9 | 112 | 126 | 151 | 127.8333 | 0 | 33.3333 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK004 | Project_075_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional Material required for investigations | Person_627 | 2017-07-21 | 2018-11-20 01:00 | 0.4 | 3.3748 | 1.3499 | Reduce | 0.1 | 3.3748 | 0.33748 | H3 | 3 | Stable | 0.5 | 118 | 139 | 155 | 138.1667 | 0.4 | 27 | 58 | 67 | 54.3333 | 0 | 75 | 1 | 2.25
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK024 | Project_075_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Failure to meet promised delivery dates | Person_627 | 2017-09-20 01:00 | 2019-01-21 01:00 | 0.5 | 2.5311 | 1.2656 | Reduce | 0.4 | 2.5311 | 1.0124 | H2 | 4 | Stable | 0.8 | 102 | 132 | 152 | 130.3333 | 0.4 | 21 | 55 | 71 | 52 | 0 | 20 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK011 | Project_041_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Supplier Development support | Person_693 | 2018-04-11 | 2018-07-21 | 0.5 | 5.9059 | 1.7718 | Accept | 0.332 | 5.9059 | 1.7718 | H2 | 4 | Stable | 0.6 | 112 | 129 | 155 | 130.5 | 0.6 | 112 | 129 | 155 | 130.5 | 0 | 33.6 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK010 | Project_041_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Digital Assembly - Testing | Person_547 | 2018-04-11 | 2018-11-20 01:00 | 0.15 | 2.0249 | 0.20249 | Accept | 0.1 | 2.0249 | 0.20249 | H3 | 3 | Improving | 0.7 | 120 | 130 | 145 | 130.8333 | 0.7 | 120 | 130 | 145 | 130.8333 | 0 | 33.3333 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK009 | Project_075_RISK009 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Suppliers can't meet timescales. | Person_627 | 2016-12-20 01:00 | 2018-11-20 01:00 | 0.7 | 22.2176 | 15.5523 | Reduce | 0.6 | 6.7497 | 4.0498 | H1 | 5 | Stable | 0.5 | 91 | 140 | 141 | 132 | 0.1 | 30 | 59 | 64 | 55 | 69.6202 | 14.2857 | 0 | 41.7721
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK017 | Project_075_RISK017 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | New Materials not tested for Out Gassing | Person_451 | 2017-07-21 | 2018-06-22 | 0.35 | 12.3041 | 4.3064 | Reduce | 0.2 | 12.3041 | 2.4608 | H2 | 4 | Stable | 0.6 | 120 | 133 | 142 | 132.3333 | 0.2 | 32 | 49 | 72 | 50 | 0 | 42.8571 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK002 | Project_041_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Component Technical risk using new material | Person_653 | 2017-09-20 01:00 | 2018-07-21 | 0.4 | 26.0143 | 13.0071 | Accept | 0.5 | 26.0143 | 13.0071 | H2 | 4 | Stable | 0.6 | 112 | 124 | 154 | 127 | 0.6 | 112 | 124 | 154 | 127 | 0 | -25 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK013 | Project_041_RISK013 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional components validation | Person_693 | 2017-07-15 | 2018-09-20 01:00 | 0.4 | 2.5311 | 1.2656 | Accept | 0.3 | 2.5311 | 1.2656 | H2 | 4 | Stable | 0.9 | 120 | 133 | 145 | 132.8333 | 0.9 | 120 | 133 | 145 | 132.8333 | 0 | 25 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Outstanding CRs | Person_693 | 2017-05-23 | 2018-12-21 01:00 | 0.7 | 0.98433 | 0.78746 | Accept | 0.5 | 0.98433 | 0.78746 | H2 | 4 | Stable | 0.5 | 103 | 138 | 156 | 135.1667 | 0.5 | 103 | 138 | 156 | 135.1667 | 0 | 28.5714 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-111 | Project_043_Risk-111 | Opportunitity | Project Contingency | Open | H1 | 5 | 7. Finance | Decrease the cost of obsolescence sweeps | Person_769 | 2018-01-11 01:00 | 2020-12-21 01:00 | 0.5 | 0.038325 | 0.019162 | Exploit | 0.5 | 0.038325 | 0.019162 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-113 | Project_043_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | No Gen 1 products available, transition cost to Gen 2 | Person_769 | 2017-04-19 | 2020-12-21 01:00 | 0.3 | 1.4971 | 0.44912 | Reduce | 0.3 | 1.4971 | 0.44912 | H2 | 4 | Stable | 0.5 | 103 | 135 | 146 | 131.5 | 0.1 | 39 | 46 | 74 | 49.5 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-121 | Project_043_Risk-121 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | More Tech Pubs Update than estimated | Person_769 | 2019-01-21 01:00 | 2020-10-20 01:00 | 0.45 | 1.7366 | 0.78146 | Reduce | 0.45 | 1.7366 | 0.78146 | H1 | 5 | Stable | 0.8 | 96 | 135 | 148 | 130.6667 | 0.2 | 2 | 57 | 60 | 48.3333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-084 | Project_043_Risk-084 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | complex repair ( over and above the forecast average) | Person_368 | 2017-12-21 01:00 | 2020-12-21 01:00 | 0.2 | 0.71859 | 0.14372 | Reduce | 0.2 | 0.71859 | 0.14372 | H2 | 4 | Stable | 0.6 | 97 | 128 | 156 | 127.5 | 0.2 | 10 | 45 | 64 | 42.3333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-128 | Project_043_Risk-128 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Reliance of Customer Avaliability | Person_135 | 2017-04-19 | 2018-08-21 | 0.5 | 1.7665 | 0.88326 | Reduce | 0.1 | 1.7665 | 0.17665 | H2 | 4 | Stable | 0.7 | 94 | 130 | 145 | 126.5 | 0.3 | 21 | 46 | 72 | 46.1667 | 0 | 80 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-089 | Project_043_Risk-089 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares pool is limited | Person_307 | 2018-12-22 01:00 | 2020-12-21 01:00 | 0.25 | 1.5969 | 0.39921 | Reduce | 0.25 | 1.2775 | 0.31937 | H2 | 4 | Stable | 0.8 | 100 | 131 | 145 | 128.1667 | 0.3 | 24 | 57 | 76 | 54.6667 | 20 | 0 | 0 | 12
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-039 | Project_043_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System fails to achieve required performance | Person_051 | 2017-04-19 | 2018-11-20 01:00 | 0.3 | 4.7906 | 1.4372 | Reduce | 0.3 | 4.7906 | 1.4372 | H2 | 4 | Stable | 0.9 | 107 | 133 | 151 | 131.6667 | 0.1 | 35 | 56 | 78 | 56.1667 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of not being able to perform Tests | Person_547 | 2017-12-21 01:00 | 2019-01-21 01:00 | 0.5 | 9.6742 | 0.96742 | Accept | 0.5 | 9.6742 | 0.96742 | H2 | 4 | Stable | 0.6 | 100 | 138 | 154 | 134.3333 | 0.6 | 100 | 138 | 154 | 134.3333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Availability of key resource within Engineering | Person_693 | 2018-01-21 01:00 | 2019-05-23 | 0.1 | 0.89832 | 0.17966 | Accept | 0.1 | 0.89832 | 0.17966 | H3 | 3 | Improving | 0.7 | 108 | 137 | 155 | 135.1667 | 0.7 | 108 | 137 | 155 | 135.1667 | 0 | 0 | 1 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_547 | 2017-05-23 | 2019-01-21 01:00 | 0.5 | 1.6584 | 0.82922 | Accept | 0.5 | 1.6584 | 0.82922 | H2 | 4 | Stable | 0.8 | 97 | 132 | 154 | 129.8333 | 0.8 | 97 | 132 | 154 | 129.8333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Production - Design Changes | Person_547 | 2017-05-23 | 2018-08-19 | 0.1 | 4.3949 | 3.5159 | Accept | 0.1 | 4.3949 | 3.5159 | H3 | 3 | Stable | 0.7 | 92 | 127 | 149 | 124.8333 | 0.7 | 92 | 127 | 149 | 124.8333 | 0 | 0 | 1 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Production - Supplier Quality | Person_468 | 2017-05-23 | 2019-08-20 | 0.25 | 0.41461 | 0.10365 | Accept | 0.192 | 0.41461 | 0.10365 | H3 | 3 | Improving | 0.8 | 107 | 138 | 154 | 135.5 | 0.8 | 107 | 138 | 154 | 135.5 | 0 | 23.2 | 0 | 0
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.8 | 90 | 134 | 143 | 128.1667 | 0.2 | 1 | 51 | 79 | 47.3333 | 25.8065 | 20 | 0 | 15.4839
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2018-04-22 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK003 | Project_001_RISK003 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Non-Recurring Engineering higher than expected | Person_674 | 2017-12-21 | 2018-08-21 | 0.5 | 16.0059 | 8.0029 | Reduce | 0.2 | 8.0029 | 1.6006 | H3 | 3 | Improving | 0.5 | 90 | 126 | 156 | 125 | 0.1 | 11 | 44 | 65 | 42 | 50 | 60 | 0 | 30
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK008 | Project_075_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Failures at Acceptance stage | Person_627 | 2017-07-21 | 2018-09-20 01:00 | 0.3 | 2.6676 | 0.53353 | Accept | 0.3 | 2.6676 | 0.53353 | H2 | 4 | Stable | 0.7 | 119 | 130 | 160 | 133.1667 | 0.7 | 119 | 130 | 160 | 133.1667 | 0 | 0 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK007 | Project_075_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Range performance does not meet requirement. | Person_003 | 2017-07-21 | 2018-09-20 01:00 | 0.1 | 0.82635 | 0.20659 | Accept | 0.1 | 0.82635 | 0.20659 | H3 | 3 | Stable | 0.5 | 105 | 139 | 148 | 134.8333 | 0.5 | 105 | 139 | 148 | 134.8333 | 0 | 0 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK010 | Project_075_RISK010 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | We do not achieve Standard compliant energy over temperature | Person_449 | 2017-07-21 | 2018-09-20 01:00 | 0.5 | 0.93298 | 0.13995 | Accept | 0.5 | 0.93298 | 0.13995 | H1 | 5 | Stable | 0.5 | 97 | 132 | 145 | 128.3333 | 0.5 | 97 | 132 | 145 | 128.3333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK018 | Project_075_RISK018 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Crystal switch | Person_627 | 2017-03-21 01:00 | 2018-09-20 01:00 | 0.5 | 0.95964 | 0.28789 | Accept | 0.5 | 0.95964 | 0.28789 | H2 | 4 | Stable | 0.9 | 89 | 134 | 148 | 128.8333 | 0.9 | 89 | 134 | 148 | 128.8333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_676 | 2016-08-21 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.7 | 105 | 129 | 159 | 130 | 0.1 | 11 | 48 | 67 | 45 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_676 | 2016-08-21 | 2017-08-21 | 0.5 | 37.5906 | 18.7953 | Reduce | 0.15 | 37.5906 | 5.6386 | H3 | 3 | Stable | 0.9 | 89 | 139 | 157 | 133.6667 | 0.3 | 5 | 42 | 63 | 39.3333 | 0 | 70 | 1 | 2.1
2018-04-22 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-010 | Project_052_Risk-010 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Potential update of software / hardware required during the 3 year support period (RESOURCE) | Person_376 | 2017-08-19 | 2018-02-19 | 0.25 | 3.1214 | 0.78035 | Transfer | 0.25 | 3.1214 | 0.78035 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_676 | 2016-10-21 | 2019-08-20 | 0.5 | 3.8232 | 1.3381 | Accept | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.6 | 89 | 131 | 141 | 125.6667 | 0.6 | 89 | 131 | 141 | 125.6667 | 100 | 0 | 0 | 60
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_676 | 2016-08-21 | 2019-08-20 | 0.2 | 1.2744 | 0.63719 | Accept | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.9 | 119 | 124 | 154 | 128.1667 | 0.9 | 119 | 124 | 154 | 128.1667 | 100 | 0 | 0 | 60
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_676 | 2016-08-21 | 2019-08-20 | 0.35 | 2.5488 | 0.89207 | Accept | 0.35 | 0 | 0 | H3 | 3 | Stable | 0.8 | 92 | 139 | 156 | 134 | 0.8 | 92 | 139 | 156 | 134 | 100 | 0 | 0 | 60
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_676 | 2016-08-21 | 2019-08-20 | 0.25 | 0.82835 | 0.49701 | Accept | 0.25 | 0 | 0 | H3 | 3 | Stable | 0.7 | 91 | 123 | 148 | 121.8333 | 0.7 | 91 | 123 | 148 | 121.8333 | 100 | 0 | 0 | 60
2018-04-22 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-013 | Project_052_Risk-013 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional material and effort required to support the delta equipment | Person_376 | 2017-08-19 | 2018-03-22 | 0.3 | 67.8016 | 27.1206 | Accept | 0.3 | 67.8016 | 27.1206 | H3 | 3 | Stable | 0.5 | 108 | 140 | 145 | 135.5 | 0.5 | 108 | 140 | 145 | 135.5 | 0 | 0 | 0 | 0
2018-04-22 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-004 | Project_052_Risk-004 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | IOC Risk for Phase 1b | Person_488 | 2017-08-19 | 2018-03-22 | 0.1 | 65.469 | 26.1876 | Accept | 0.1 | 65.469 | 26.1876 | H3 | 3 | Stable | 0.6 | 117 | 128 | 144 | 128.8333 | 0.6 | 117 | 128 | 144 | 128.8333 | 0 | 0 | 0 | 0
2018-04-22 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-001 | Project_052_Risk-001 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Greater modification than expected for system uplift | Person_376 | 2017-08-19 | 2018-03-22 | 0.1 | 7.7077 | 1.5415 | Accept | 0.1 | 7.7077 | 1.5415 | H3 | 3 | Stable | 0.6 | 102 | 138 | 156 | 135 | 0.6 | 102 | 138 | 156 | 135 | 0 | 0 | 0 | 0
2018-04-22 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-009 | Project_052_Risk-009 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | System acceptance not costed in line with Customer expectations | Person_651 | 2017-08-19 | 2018-03-22 | 0.1 | 25.1514 | 12.5757 | Accept | 0.1 | 25.1514 | 12.5757 | H3 | 3 | Stable | 0.8 | 102 | 135 | 156 | 133 | 0.8 | 102 | 135 | 156 | 133 | 0 | 0 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-06-06 | 0.4 | 1.0142 | 0.40567 | Reduce | 0.1 | 1.0142 | 0.10142 | H3 | 3 | Stable | 0.7 | 111 | 133 | 148 | 131.8333 | 0.1 | 14 | 57 | 71 | 52.1667 | 0 | 75 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | 9. Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 0.8 | 19.1678 | 15.3343 | Reduce | 0.2 | 2.8752 | 0.57503 | H3 | 3 | Stable | 0.7 | 95 | 137 | 154 | 132.8333 | 0.2 | 13 | 48 | 65 | 45 | 85 | 75 | 0 | 51
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-05 23:00 | 2019-09-12 23:00 | 0.8 | 8.0322 | 6.4258 | Reduce | 0.5 | 4.006 | 2.003 | H2 | 4 | Stable | 0.5 | 83 | 126 | 159 | 124.3333 | 0.4 | 9 | 55 | 64 | 48.8333 | 50.1263 | 37.5 | 0 | 30.0758
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK002 | Project_065_RISK002 | Opportunitity | Project Contingency | Open | H1 | 5 | 12. Acquisition and offsets | New supplier for enclosure | Person_598 | 2015-01-06 23:00 | 2017-10-18 23:00 | 0.05 | 9.6346 | 0.48173 | Exploit | 0.7 | 9.6346 | 6.7442 | H1 | 5 | Stable | [10 empty] | 0 | -1300 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier Selection Process | Person_379 | 2017-10-18 23:00 | 2019-04-23 | 0.4 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.5 | 111 | 138 | 141 | 134 | 0.1 | 14 | 51 | 63 | 46.8333 |  | 25 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Colour Representation in Video Image Distortion | Person_305 | 2017-09-21 23:00 | 2020-03-21 | 0.5 | 5.5323 | 2.7662 | Reduce | 0.1 | 5.5323 | 0.55323 | H3 | 3 | Stable | 0.9 | 94 | 137 | 141 | 130.5 | 0.1 | 39 | 43 | 62 | 45.5 | 0 | 80 | 1 | 2.4
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-20 23:00 | 0.8 | 35.2369 | 28.1895 | Reduce | 0.3 | 18.4979 | 5.5494 | H2 | 4 | Stable | 0.7 | 104 | 125 | 150 | 125.6667 | 0.2 | 10 | 40 | 63 | 38.8333 | 47.5042 | 62.5 | 0 | 28.5025
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 4 | 9. Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-20 23:00 | 0.7 | 20.6835 | 14.4785 | Reduce | 0.3 | 20.6835 | 6.2051 | H2 | 4 | Stable | 0.9 | 103 | 122 | 146 | 122.8333 | 0.4 | 27 | 42 | 65 | 43.3333 | 0 | 57.1429 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 4 | 8. System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 0.6 | 5.2585 | 3.1551 | Reduce | 0.15 | 5.2585 | 0.78877 | H2 | 4 | Stable | 0.8 | 93 | 137 | 146 | 131.1667 | 0.2 | 16 | 42 | 69 | 42.1667 | 0 | 75 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-04-21 | 0.3 | 2.723 | 0.81691 | Reduce | 0.1 | 2.723 | 0.2723 | H3 | 3 | Improving | 0.7 | 86 | 133 | 144 | 127 | 0.3 | 24 | 56 | 71 | 53.1667 | 0 | 66.6667 | 1 | 2
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-07 23:00 | 2020-09-20 23:00 | 0.2 | 4.8444 | 0.96888 | Reduce | 0.2 | 4.8444 | 0.96888 | H3 | 3 | Stable | 0.8 | 96 | 126 | 159 | 126.5 | 0.1 | 7 | 41 | 78 | 41.5 | 0 | 0 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System Performance | Person_305 | 2016-09-07 23:00 | 2020-09-20 23:00 | 0.15 | 5.8725 | 0.88088 | Reduce | 0.05 | 5.8725 | 0.29363 | H2 | 4 | Stable | 0.7 | 100 | 137 | 154 | 133.6667 | 0.1 | 28 | 41 | 77 | 44.8333 | 0 | 66.6667 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_038 | 2020-05-23 | 2023-10-25 23:00 | 0.2 | 7.4599 | 1.492 | Reduce | 0.05 | 7.4599 | 0.37299 | H2 | 4 | Stable | 0.6 | 86 | 127 | 144 | 123 | 0.2 | 6 | 40 | 64 | 38.3333 | 0 | 75 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-28 23:00 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.5 | 94 | 121 | 153 | 121.8333 | 0.2 | 37 | 43 | 68 | 46.1667 | 60.3671 | 58.3333 | 0 | 36.2202
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-19 23:00 | 0.4 | 2.8643 | 1.1457 | Reduce | 0.1 | 2.8643 | 0.28643 | H3 | 3 | Stable | 0.8 | 116 | 136 | 151 | 135.1667 | 0.3 | 30 | 56 | 74 | 54.6667 | 0.0015933 | 75 | 1 | 2.251
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power Supply - Motor Controller Interface | Person_047 | 2016-05-23 | 2018-04-21 | 0.5 | 25.3543 | 12.6771 | Reduce | 0.2 | 25.3543 | 5.0709 | H3 | 3 | Stable | 0.5 | 95 | 126 | 149 | 124.6667 | 0.3 | 18 | 54 | 70 | 50.6667 | 0 | 60 | 1 | 1.8
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.7 | 102 | 123 | 159 | 125.5 | 0.1 | 24 | 59 | 77 | 56.1667 | 60.3671 | 58.3333 | 0 | 36.2202
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-23 | 2024-05-22 | 0.1 | 1.9438 | 0.77753 | Accept | 0.1 | 1.9438 | 0.77753 | H3 | 3 | Improving | 0.6 | 95 | 130 | 142 | 126.1667 | 0.6 | 95 | 130 | 142 | 126.1667 | 0 | 0 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-07 23:00 | 2020-09-20 23:00 | 0.1 | 12.7232 | 1.2723 | Reduce | 0.1 | 12.7232 | 1.2723 | H3 | 3 | Stable | 0.9 | 96 | 133 | 151 | 129.8333 | 0.3 | 20 | 47 | 71 | 46.5 | 0 | 0 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-20 23:00 | 2023-12-21 23:00 | 0.4 | 30.1969 | 12.0788 | Reduce | 0.25 | 30.1969 | 7.5492 | H2 | 4 | Stable | 0.5 | 108 | 128 | 148 | 128 | 0.4 | 10 | 40 | 68 | 39.6667 | 0 | 37.5 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | In-house development of sub-system estimate is low | Person_594 | 2016-03-23 | 2018-03-22 | 0.5 | 6.5118 | 3.2559 | Reduce | 0.2 | 1.506 | 0.30121 | H3 | 3 | Stable | 0.7 | 93 | 128 | 144 | 124.8333 | 0.3 | 11 | 55 | 63 | 49 | 76.8722 | 60 | 0 | 46.1233
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 0.25 | 0.63626 | 0.15906 | Reduce | 0.05 | 0.63626 | 0.031813 | H3 | 3 | Stable | 0.7 | 97 | 128 | 156 | 127.5 | 0.4 | 10 | 48 | 76 | 46.3333 | 0 | 80 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Component Shock test failure | Person_661 | 2016-09-07 23:00 | 2019-11-14 23:00 | 0.4 | 0.8467 | 0.33868 | Reduce | 0.2 | 0.8467 | 0.16934 | H3 | 3 | Stable | 0.8 | 96 | 130 | 141 | 126.1667 | 0.2 | 27 | 51 | 79 | 51.6667 | 0 | 50 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-01-11 23:00 | 0.8 | 18.0459 | 14.4367 | Reduce | 0.2 | 3.0076 | 0.60153 | H3 | 3 | Stable | 0.9 | 104 | 125 | 158 | 127 | 0.4 | 23 | 54 | 65 | 50.6667 | 83.3335 | 75 | 1 | 52.2501
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 0.4 | 5.1004 | 2.0402 | Reduce | 0.2 | 2.5506 | 0.51013 | H3 | 3 | Stable | 0.8 | 80 | 140 | 154 | 132.3333 | 0.1 | 30 | 44 | 76 | 47 | 49.9917 | 50 | 0 | 29.995
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK016 | Project_038_RISK016 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Supplier Quality Issues | Person_397 | 2012-11-19 23:00 | 2018-08-21 23:00 | 0.5 | 5.0339 | 2.517 | Avoid | 0.5 | 5.0339 | 2.517 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK018 | Project_038_RISK018 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Last System Syndrome | Person_329 | 2012-11-19 23:00 | 2018-10-20 23:00 | 0.15 | 43.4175 | 6.5126 | -- | 0.1288 | 43.4175 | 5.5922 | H2 | 4 | Worsening | [10 empty] | 0 | 14.1333 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Additional minor point release | Person_228 | 2016-05-23 | 2019-06-23 | 0.5 | 11.9444 | 5.9722 | Reduce | 0.25 | 11.9444 | 2.9861 | H2 | 4 | Stable | 0.9 | 118 | 137 | 155 | 136.8333 | 0.4 | 2 | 58 | 61 | 49.1667 | 0 | 50 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_228 | 2016-05-23 | 2018-12-21 01:00 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.9 | 113 | 123 | 147 | 125.3333 | 0.2 | 2 | 41 | 77 | 40.5 | 0 | 50 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_004 | 2015-11-21 01:00 | 2018-11-20 01:00 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.8 | 88 | 136 | 148 | 130 | 0.1 | 16 | 47 | 73 | 46.1667 | 0 | 5 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.8 | 2.8043 | 2.2435 | Reduce | 0.45 | 2.8043 | 1.2619 | H1 | 5 | Stable | 0.7 | 80 | 133 | 144 | 126 | 0.2 | 5 | 53 | 78 | 49.1667 | 0 | 43.75 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK167 | Project_024_RISK167 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Customer not providing the information needed or Customer not accepting the Customer documentation resulting in rewor. | Person_052 | 2016-08-21 01:00 | 2018-06-21 | 0.5 | 9.971 | 4.9855 | Reduce | 0.3 | 9.971 | 2.9913 | H1 | 5 | Improving | 0.7 | 107 | 121 | 146 | 122.8333 | 0.2 | 5 | 55 | 67 | 48.6667 | 0 | 40 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.8 | 82 | 123 | 156 | 121.6667 | 0.4 | 18 | 40 | 78 | 42.6667 | 0 | 60 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis and Security | Person_119 | 2017-02-22 01:00 | 2019-05-22 | 0.3 | 19.9938 | 5.9981 | Reduce | 0.04675 | 19.9938 | 0.93471 | H3 | 3 | Improving | 0.6 | 89 | 139 | 142 | 131.1667 | 0.3 | 8 | 58 | 60 | 50 | 0 | 84.4167 | 1 | 2.5325
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.2 | 3.843 | 0.76859 | H2 | 4 | Stable | 0.8 | 91 | 124 | 147 | 122.3333 | 0.1 | 29 | 45 | 66 | 45.8333 | 0 | 60 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Performance (collector opportunity) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.373 | 19.5316 | 7.2853 | -- | 0.4158 | 19.5316 | 8.1213 | H1 | 5 | Stable | [10 empty] | 0 | -11.4745 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.3 | 20.8767 | 6.263 | H1 | 5 | Stable | 0.5 | 110 | 140 | 159 | 138.1667 | 0.1 | 30 | 59 | 63 | 54.8333 | 50 | 25 | 0 | 30
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.504 | 73.3644 | 36.9756 | Reduce | 0.0852 | 53.773 | 4.5815 | H2 | 4 | Worsening | 0.7 | 117 | 133 | 145 | 132.3333 | 0.3 | 26 | 58 | 70 | 54.6667 | 26.7042 | 83.0952 | 0 | 16.0225
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK308 | Project_024_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System robustness and resilience | Person_774 | 2017-04-06 | 2018-06-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.1 | 2.5966 | 0.25966 | H3 | 3 | Stable | 0.7 | 81 | 124 | 152 | 121.5 | 0.3 | 8 | 57 | 63 | 49.8333 | 58.3333 | 66.6667 | 1 | 37
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-020 | Project_077_T-020 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Cybersecurity | Person_560 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.1 | 1.3478 | 0.13478 | Reduce | 0.1 | 1.3478 | 0.13478 | H3 | 3 | Stable | 0.9 | 95 | 138 | 145 | 132 | 0.2 | 10 | 59 | 65 | 51.8333 | 0 | 0 | 1 | 0
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-005 | Project_077_T-005 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | SSTP/SSTR overspend | Person_667 | 2018-10-22 01:00 | 2020-02-21 01:00 | 0.3 | 10.5469 | 3.1641 | Reduce | 0.3 | 10.5469 | 3.1641 | H2 | 4 | Stable | 0.5 | 114 | 135 | 143 | 132.8333 | 0.4 | 1 | 52 | 79 | 48 | 0 | 0 | 0 | 0
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-006 | Project_077_T-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Functionality | Person_667 | 2018-05-23 | 2020-02-21 01:00 | 0.2 | 3.774 | 0.7548 | -- | 0.2 | 3.774 | 0.7548 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-007 | Project_077_T-007 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Rig Failure or Damage | Person_574 | 2018-07-22 | 2020-02-21 01:00 | 0.3 | 2.033 | 0.6099 | Reduce | 0.3 | 2.033 | 0.6099 | H2 | 4 | Stable | 0.6 | 92 | 132 | 160 | 130 | 0.4 | 6 | 42 | 65 | 39.8333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-023 | Project_077_T-023 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Legacy abilities | Person_706 | 2018-10-22 01:00 | 2020-02-21 01:00 | 0.1 | 1.0019 | 0.10019 | Avoid | 0.1 | 1.0019 | 0.10019 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-001 | Project_077_T-001 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Increased Interface changes | Person_538 | 2018-07-22 | 2020-02-21 01:00 | 0.5 | 2.1566 | 1.0783 | Transfer | 0.3 | 2.1566 | 0.64697 | H2 | 4 | Stable | [10 empty] | 0 | 40 | 0 | 0
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-025 | Project_077_T-025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Delayed Config File delivery | Person_163 | 2019-05-24 | 2020-02-21 01:00 | 0.5 | 3.3696 | 1.6848 | Avoid | 0.5 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-003 | Project_077_T-003 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | SW Resource availability | Person_508 | 2018-05-23 | 2020-02-21 01:00 | 0.5 | 25.1598 | 12.5799 | Reduce | 0.5 | 25.1598 | 12.5799 | H1 | 5 | Worsening | 0.5 | 91 | 123 | 146 | 121.5 | 0.2 | 3 | 57 | 65 | 49.3333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-026 | Project_077_T-026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Insufficient Config Option capacity | Person_706 | 2018-04-22 | 2020-02-21 01:00 | 0.2 | 1.0019 | 0.20038 | Avoid | 0.05 | 1.0019 | 0.050095 | H3 | 3 | Stable | [10 empty] | 0 | 75 | 1 | 2.25
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-004 | Project_077_T-004 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Debt | Person_667 | 2018-06-23 | 2020-02-21 01:00 | 0.2 | 2.1566 | 0.43131 | Reduce | 0.2 | 2.1566 | 0.43131 | H3 | 3 | Stable | 0.9 | 115 | 131 | 148 | 131.1667 | 0.4 | 33 | 46 | 68 | 47.5 | 0 | 0 | 1 | 0
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | OPRisk-001 | Project_077_OPRisk-001 | Opportunitity | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Opportunity that fewer than expected customer problem reports are raised. | Person_706 | 2019-03-24 | 2020-02-21 01:00 | 0.5 | 1.0221 | 0.51106 | -- | 0.5 | 0.14602 | 0.07301 | H2 | 4 | Stable | [10 empty] | 85.7141 | 0 | 0 | 51.4285
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-010 | Project_077_T-010 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Technical Directorate changes to software/data artefacts - Internal Requirement | Person_574 | 2018-11-21 01:00 | 2020-02-21 01:00 | 0.4 | 1.887 | 0.7548 | Reduce | 0.4 | 1.887 | 0.7548 | H2 | 4 | Stable | 0.6 | 80 | 137 | 158 | 131 | 0.3 | 16 | 54 | 64 | 49.3333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-032 | Project_077_T-032 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Requirement Updated from Issue 4 to 6 | Person_574 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.5 | 3.3696 | 1.6848 | Avoid | 0.1 | 3.3696 | 0.33696 | H3 | 3 | Stable | [10 empty] | 0 | 80 | 1 | 2.4
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-011 | Project_077_T-011 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Bus Scheduling table changes affecting proven interface | Person_706 | 2019-05-24 | 2020-02-21 01:00 | 0.2 | 0.92103 | 0.18421 | Reduce | 0.2 | 0.92103 | 0.18421 | H3 | 3 | Stable | 0.8 | 114 | 127 | 141 | 127.1667 | 0.3 | 2 | 56 | 73 | 49.8333 | 0 | 0 | 1 | 0
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-033 | Project_077_T-033 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | PDA availability | Person_574 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.4 | 3.0327 | 1.2131 | Avoid | 0.4 | 3.0327 | 1.2131 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-016 | Project_077_T-016 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Autotest | Person_574 | 2018-09-09 01:00 | 2020-02-21 01:00 | 0.5 | 2.1341 | 1.067 | Reduce | 0.5 | 2.1341 | 1.067 | H2 | 4 | Stable | 0.9 | 104 | 127 | 141 | 125.5 | 0.1 | 29 | 51 | 76 | 51.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-012 | Project_077_T-012 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Managment cost increases for BMN | Person_667 | 2018-03-01 01:00 | 2020-02-21 01:00 | 0.21 | 1.5725 | 0.33022 | Avoid | 0.21 | 1.5725 | 0.33022 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-034 | Project_077_T-034 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Simulator update not viable if needed | Person_707 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.5 | 0.74806 | 0.37403 | Avoid | 0.5 | 0.74806 | 0.37403 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-013 | Project_077_T-013 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | More customer failures than anticipated | Person_706 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.2 | 3.3809 | 0.67617 | Reduce | 0.2 | 3.3809 | 0.67617 | H3 | 3 | Stable | 0.8 | 94 | 130 | 141 | 125.8333 | 0.4 | 22 | 59 | 65 | 53.8333 | 0 | 0 | 1 | 0
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-014 | Project_077_T-014 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Extra Release | Person_667 | 2020-06-23 | 2020-11-20 01:00 | 0.1 | 13.4785 | 1.3478 | Avoid | 0.1 | 13.4785 | 1.3478 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK003 | Project_060_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Misalignment of Critical Resource | Person_312 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.7 | 1.0769 | 0.75381 | Reduce | 0.5 | 1.0769 | 0.53844 | H2 | 4 | Stable | 0.9 | 86 | 125 | 145 | 121.8333 | 0.4 | 7 | 44 | 78 | 43.5 | 0 | 28.5714 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK004 | Project_060_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Cross-functional Estimates | Person_729 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.7 | 2.8845 | 2.0191 | Reduce | 0.5 | 1.4422 | 0.72112 | H2 | 4 | Improving | 0.8 | 95 | 137 | 145 | 131.3333 | 0.1 | 24 | 56 | 67 | 52.5 | 50 | 28.5714 | 0 | 30
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK024 | Project_063_RISK024 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Procurement/Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 0.8 | 0 | 0 | -- | 0.8 | 0 | 0 | H1 | 5 | Worsening | [11 empty] | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK022 | Project_063_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Equipment | Person_104 | 2018-01-14 01:00 | 2019-08-20 | 0.15 | 2.3618 | 0.35427 | -- | 0.15 | 2.3618 | 0.35427 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK001 | Project_060_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Procurement Prices | Person_033 | 2017-11-02 01:00 | 2018-08-20 | 0.7 | 1.4422 | 1.0096 | Reduce | 0.3 | 1.4422 | 0.43267 | H3 | 3 | Stable | 0.9 | 117 | 121 | 151 | 125.3333 | 0.4 | 31 | 42 | 69 | 44.6667 | 0 | 57.1429 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK004 | Project_063_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 2.861 | 0.57221 | Reduce | 0.15 | 2.861 | 0.42915 | H3 | 3 | Stable | 0.5 | 97 | 137 | 146 | 131.8333 | 0.1 | 34 | 57 | 66 | 54.6667 | 0 | 25 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK014 | Project_063_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 0.1 | 8.3527 | 0.83527 | Avoid | 0.05 | 7.0086 | 0.35043 | H3 | 3 | Stable | [10 empty] | 16.092 | 50 | 0 | 9.6552
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK017 | Project_063_RISK017 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Increased build rate | Person_683 | 2017-11-12 01:00 | 2019-08-21 01:00 | 0.5 | 21.6065 | 10.8033 | -- | 0.5 | 21.6065 | 10.8033 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK005 | Project_063_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 1.214 | 0.72839 | -- | 0.5 | 1.214 | 0.60699 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK016 | Project_063_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.2 | 0.63077 | 0.12615 | -- | 0.2 | 0.63077 | 0.12615 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK002 | Project_063_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2020-05-22 | 0.15 | 8.6407 | 1.2961 | Avoid | 0.15 | 8.6407 | 1.2961 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK012 | Project_063_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Customer require additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.1 | 6.0485 | 0.60485 | Avoid | 0.1 | 6.0485 | 0.60485 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK018 | Project_063_RISK018 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Line Closure | Person_683 | 2019-08-21 01:00 | 2019-11-20 01:00 | 0.5 | 1.9058 | 0.95288 | -- | 0.5 | 4.3203 | 2.1602 | H2 | 4 | Improving | [10 empty] | -126.7001 | 0 | 0 | -76.0201
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK026 | Project_063_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Clause on Joint Proposal | Person_261 | 2018-05-04 | 2019-05-23 | 0.5 | 9.8888 | 4.9444 | -- | 0.5 | 9.8888 | 4.9444 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-20 22:00 | 2017-08-19 22:00 | 0.1 | 53.0293 | 5.3029 | Reduce | 0.1 | 53.0293 | 5.3029 | H3 | 3 | Stable | 0.6 | 112 | 124 | 157 | 127.5 | 0.3 | 18 | 55 | 69 | 51.1667 | 0 | 0 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 0.3 | 0.20788 | 0.068599 | Accept | 0.3 | 31.0429 | 15.5215 | H3 | 3 | Stable | 0.8 | 93 | 135 | 155 | 131.3333 | 0.8 | 93 | 135 | 155 | 131.3333 | -14833.3191 | 0 | 0 | -8899.9915
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-20 22:00 | 2017-08-19 22:00 | 0.1 | 7.7469 | 0.77469 | Reduce | 0.1 | 7.7469 | 0.77469 | H3 | 3 | Stable | 0.7 | 112 | 122 | 155 | 125.8333 | 0.3 | 22 | 55 | 70 | 52 | 0 | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK003 | Project_024_RISK003 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance | Person_119 | 2017-12-21 01:00 | 2019-02-20 01:00 | 0.31667 | 11.3437 | 0.56718 | Accept | 0.04388 | 11.3437 | 0.56718 | H2 | 4 | Stable | 0.6 | 107 | 134 | 141 | 130.6667 | 0.6 | 107 | 134 | 141 | 130.6667 | 0 | 86.1432 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK024 | Project_048_RISK024 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Procurement/Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 0.8 | 0 | 0 | -- | 0.8 | 0 | 0 | H1 | 5 | Worsening | [11 empty] | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before part b finished | Person_119 | 2016-10-20 01:00 | 2018-04-21 | 0.3 | 0.05293 | 0.015879 | Accept | 0.27 | 0.05293 | 0.015879 | H2 | 4 | Worsening | 0.6 | 81 | 131 | 155 | 126.6667 | 0.6 | 81 | 131 | 155 | 126.6667 | 0 | 10 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK017 | Project_048_RISK017 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Increased build rate | Person_683 | 2017-11-12 01:00 | 2019-08-21 01:00 | 0.5 | 7.7433 | 3.8716 | -- | 0.5 | 7.7433 | 3.8716 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS019 | Project_025_RS019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Product Component Failure | Person_619 | 2017-03-23 | 2019-08-07 | 0.7 | 0.82924 | 0.58047 | Reduce | 0.3 | 0.82924 | 0.24877 | H2 | 4 | Stable | 0.7 | 105 | 122 | 145 | 123 | 0.3 | 39 | 55 | 70 | 54.8333 | 0 | 57.1429 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK016 | Project_048_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.2 | 0.22605 | 0.045211 | -- | 0.2 | 0.22605 | 0.045211 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_373 | 2012-08-21 01:00 | 2019-08-07 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 2.2054 | 1.3453 | H1 | 5 | Stable | 0.9 | 115 | 136 | 151 | 135 | 0.2 | 7 | 44 | 72 | 42.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK018 | Project_048_RISK018 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Line Closure | Person_683 | 2019-08-21 01:00 | 2019-11-20 01:00 | 0.5 | 0.68298 | 0.34149 | -- | 0.5 | 1.5483 | 0.77415 | H2 | 4 | Improving | [10 empty] | -126.7001 | 0 | 0 | -76.0201
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK004 | Project_048_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 1.0253 | 0.20506 | Reduce | 0.15 | 1.0253 | 0.1538 | H3 | 3 | Stable | 0.8 | 107 | 130 | 151 | 129.6667 | 0.3 | 26 | 59 | 61 | 53.8333 | 0 | 25 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK014 | Project_048_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 0.1 | 2.9934 | 0.29934 | Avoid | 0.05 | 2.5117 | 0.12558 | H3 | 3 | Stable | [10 empty] | 16.092 | 50 | 0 | 9.6552
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK005 | Project_048_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 0.43506 | 0.26104 | Avoid | 0.5 | 0.43506 | 0.21753 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK002 | Project_048_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2020-05-22 | 0.15 | 3.0966 | 0.46449 | Avoid | 0.15 | 3.0966 | 0.46449 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK012 | Project_048_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Customer require additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.1 | 2.1676 | 0.21676 | Avoid | 0.1 | 2.1676 | 0.21676 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK022 | Project_048_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Equipment | Person_104 | 2018-01-14 01:00 | 2019-08-20 | 0.15 | 0.84641 | 0.12696 | -- | 0.15 | 0.84641 | 0.12696 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK026 | Project_048_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Clause on Joint Proposal | Person_261 | 2018-05-04 | 2019-05-23 | 0.5 | 3.5439 | 1.772 | -- | 0.5 | 3.5439 | 1.772 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--16 | Project_021_Risk--16 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of weather | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.8 | 114 | 137 | 160 | 137 | 0.1 | 35 | 59 | 68 | 56.5 |  | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--15 | Project_021_Risk--15 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to lack of personnel resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.4 | 0 | 0 | H2 | 4 | Stable | 0.8 | 106 | 122 | 151 | 124.1667 | 0.4 | 7 | 40 | 68 | 39.1667 |  | 20 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--14 | Project_021_Risk--14 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to late Trials Approval | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 116 | 134 | 158 | 135 | 0.1 | 13 | 59 | 68 | 52.8333 |  | 66.6667 | 1
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--13 | Project_021_Risk--13 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Critical or Safety PR arises in Final build /Decision Point concludes new release req | Person_174 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.9 | 92 | 122 | 156 | 122.6667 | 0.3 | 30 | 56 | 70 | 54 | 0 | 50 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--12 | Project_021_Risk--12 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.6 | 117 | 130 | 153 | 131.6667 | 0.2 | 17 | 47 | 75 | 46.6667 | 0 | 33.3333 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--11 | Project_021_Risk--11 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional documentation required for final build certification | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.5 | 1.1257 | 0.56284 | Reduce | 0.3 | 1.0374 | 0.31122 | H2 | 4 | Stable | 0.7 | 98 | 131 | 141 | 127.1667 | 0.2 | 22 | 42 | 64 | 42.3333 | 7.8429 | 40 | 0 | 4.7058
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--10 | Project_021_Risk--10 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Stable | 0.6 | 110 | 125 | 146 | 126 | 0.4 | 26 | 49 | 71 | 48.8333 | 0 | 57.1429 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--32 | Project_021_Risk--32 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Lack of Customer resource to provide timely input to Acceptance and Closure activities | Person_766 | 2018-10-22 01:00 | 2019-04-23 | 0.8 | 0 | 0 | Reduce | 0.4 | 0 | 0 | H2 | 4 | Stable | 0.7 | 93 | 122 | 144 | 120.8333 | 0.3 | 35 | 42 | 70 | 45.5 |  | 50 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--18 | Project_021_Risk--18 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.7 | 93 | 131 | 158 | 129.1667 | 0.3 | 29 | 42 | 72 | 44.8333 | 50 | 28.5714 | 0 | 30
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--28 | Project_021_Risk--28 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort required to agree protocl for Client Server | Person_766 | 2018-03-23 | 2019-03-23 | 0.8 | 1.1522 | 0.92174 | Reduce | 0.4 | 1.1522 | 0.46087 | H2 | 4 | Stable | 0.9 | 101 | 129 | 150 | 127.8333 | 0.3 | 14 | 45 | 71 | 44.1667 | 0 | 50 | 0 | 0
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-002 | Project_077_T-002 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Legacy testing Repeatability | Person_708 | 2018-10-22 01:00 | 2019-05-11 | 0.3 | 3.1344 | 1.5672 | Accept | 0.3 | 3.1344 | 1.5672 | H2 | 4 | Stable | 0.6 | 90 | 126 | 155 | 124.8333 | 0.6 | 90 | 126 | 155 | 124.8333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--05 | Project_021_Risk--05 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification delays | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Worsening | 0.9 | 88 | 129 | 146 | 125 | 0.4 | 9 | 52 | 66 | 47.1667 |  | 60 | 1
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-018 | Project_077_T-018 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Config system changes | Person_574 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.15 | 2.1388 | 0.21388 | Accept | 0.15 | 2.1388 | 0.21388 | H3 | 3 | Stable | 0.8 | 120 | 130 | 158 | 133 | 0.8 | 120 | 130 | 158 | 133 | 0 | 0 | 1 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--04 | Project_021_Risk--04 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Final Qual test report delayed due to insufficient supply chain resource | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 0.2 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.9 | 120 | 138 | 147 | 136.5 | 0.1 | 39 | 47 | 65 | 48.6667 |  | 50 | 1
2018-05-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-019 | Project_077_T-019 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | New stakeholders/Changeovers | Person_667 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.3 | 1.9998 | 0.39995 | Accept | 0.3 | 1.9998 | 0.39995 | H2 | 4 | Stable | 0.9 | 103 | 134 | 155 | 132.3333 | 0.9 | 103 | 134 | 155 | 132.3333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--03 | Project_021_Risk--03 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.7 | 107 | 135 | 144 | 131.8333 | 0.2 | 38 | 46 | 73 | 49.1667 | 0 | 33.3333 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK006 | Project_060_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Secure material Handling | Person_033 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.5 | 0.78901 | 0.3945 | Accept | 0.5 | 0.78901 | 0.3945 | H2 | 4 | Stable | 0.7 | 109 | 121 | 146 | 123.1667 | 0.7 | 109 | 121 | 146 | 123.1667 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--25 | Project_021_Risk--25 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of supporting resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.5 | 106 | 133 | 149 | 131.1667 | 0.1 | 9 | 57 | 79 | 52.6667 |  | 40 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-184 | Project_032_Risk-184 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Manufacture of new Sub-systems | Person_629 | 2016-04-08 | 2018-02-18 22:00 | 0.33 | 7.3848 | 3.6924 | Accept | 0.5 | 7.3848 | 3.6924 | H1 | 5 | Stable | 0.5 | 83 | 122 | 141 | 118.6667 | 0.5 | 83 | 122 | 141 | 118.6667 | 0 | -51.5152 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--02 | Project_021_Risk--02 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_061 | 2018-02-20 01:00 | 2019-03-23 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.6 | 87 | 131 | 156 | 127.8333 | 0.2 | 5 | 54 | 76 | 49.5 | 80 | 66.6667 | 0 | 48
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--24 | Project_021_Risk--24 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of equipment | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 109 | 121 | 158 | 125.1667 | 0.4 | 10 | 57 | 61 | 49.8333 |  | 40 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-19 22:00 | 0.05 | 1.1744 | 0.23489 | Accept | 0.05 | 1.1744 | 0.23489 | H3 | 3 | Stable | 0.9 | 112 | 128 | 149 | 128.8333 | 0.9 | 112 | 128 | 149 | 128.8333 | 0 | 0 | 1 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--01 | Project_021_Risk--01 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification/ delay due to build standard issue | Person_615 | 2018-02-20 01:00 | 2018-06-22 | 0.1 | 2.2183 | 0.22183 | Reduce | 0.05 | 2.2183 | 0.11091 | H2 | 4 | Stable | 0.7 | 96 | 139 | 147 | 133.1667 | 0.3 | 32 | 42 | 60 | 43.3333 | 0 | 50 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_061 | RISK003 | Project_061_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Test equipment reliability | Person_104 | 2017-05-23 | 2020-11-18 22:00 | 0.4 | 0.11013 | 0.044051 | Reduce | 0.3 | 0.11013 | 0.033038 | H2 | 4 | Stable | 0.5 | 115 | 136 | 158 | 136.1667 | 0.3 | 17 | 51 | 66 | 47.8333 | 0 | 25 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS020 | Project_025_RS020 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Plant Machinery failure | Person_619 | 2017-03-23 | 2019-08-07 | 0.3 | 2.9361 | 0.58721 | Accept | 0.3 | 2.9361 | 0.58721 | H2 | 4 | Stable | 0.8 | 109 | 137 | 158 | 135.8333 | 0.8 | 109 | 137 | 158 | 135.8333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--21 | Project_021_Risk--21 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 88 | 129 | 157 | 126.8333 | 0.1 | 27 | 53 | 74 | 52.1667 |  | 40 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--09 | Project_021_Risk--09 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 90 | 132 | 145 | 127.1667 | 0.1 | 31 | 43 | 77 | 46.6667 |  | 40 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--08 | Project_021_Risk--08 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 0.5 | 0 | 0 | Reduce | 0.4 | 0 | 0 | H2 | 4 | Stable | 0.6 | 110 | 137 | 142 | 133.3333 | 0.1 | 6 | 43 | 79 | 42.8333 |  | 20 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--07 | Project_021_Risk--07 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 0.6 | 17.2826 | 10.3696 | Reduce | 0.3 | 17.2826 | 5.1848 | H2 | 4 | Worsening | 0.9 | 102 | 130 | 149 | 128.5 | 0.1 | 37 | 46 | 75 | 49.3333 | 0 | 50 | 0 | 0
2018-05-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK044 | Project_053_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Product Hardening | Person_719 | 2018-03-23 | 2019-01-20 | 0.3 | 7.9015 | 2.3705 | Avoid | 0.3 | 7.9015 | 2.3705 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer find issues with delivered parts or documentation | Person_294 | 2017-05-23 | 2019-08-20 | 0.4 | 9.0039 | 3.6016 | Reduce | 0.25 | 9.0039 | 2.251 | H2 | 4 | Improving | 0.8 | 98 | 122 | 157 | 123.8333 | 0.2 | 3 | 41 | 64 | 38.5 | 0 | 37.5 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--20 | Project_021_Risk--20 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | ERP implementation | Person_061 | 2018-01-21 01:00 | 2018-07-20 | 0.5 | 0 | 0 | Reduce | 0.25 | 0 | 0 | H2 | 4 | Stable | 0.8 | 97 | 133 | 141 | 128.3333 | 0.2 | 30 | 56 | 72 | 54.3333 |  | 50 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--35 | Project_021_Risk--35 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Delay to sub-system ATRs and other Component dependencies due to supply chain dependencies | Person_615 | 2018-01-21 01:00 | 2018-03-22 | 0.4 | 2.2986 | 1.1493 | Accept | 0.4 | 2.2986 | 0.45973 | H2 | 4 | Stable | 0.7 | 100 | 122 | 146 | 122.3333 | 0.7 | 100 | 122 | 146 | 122.3333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK002 | Project_058_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence of key parts | Person_236 | 2017-05-23 | 2019-08-07 | 0.5 | 6.7334 | 3.3667 | Reduce | 0.25 | 6.7334 | 1.6833 | H2 | 4 | Stable | 0.8 | 102 | 138 | 145 | 133.1667 | 0.1 | 16 | 50 | 63 | 46.5 | 0 | 50 | 0 | 0
2018-05-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK015 | Project_053_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Equipment export licences | Person_252 | 2018-06-23 | 2019-07-22 | 0.3 | 2.586 | 0.77579 | Avoid | 0.1 | 2.586 | 0.2586 | H3 | 3 | Improving | [10 empty] | 0 | 66.6667 | 1 | 2
2018-05-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK006 | Project_053_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional UK integration of the System product | Person_719 | 2018-10-22 | 2019-01-21 | 0.2 | 6.3212 | 1.2642 | Avoid | 0.2 | 6.3212 | 1.2642 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 1 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--17 | Project_021_Risk--17 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delays due to technical performacne | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.7 | 117 | 132 | 144 | 131.5 | 0.1 | 13 | 42 | 66 | 41.1667 |  | 33.3333 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK052 | Project_058_RISK052 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | sub-System Cleanliness | Person_294 | 2017-05-23 | 2018-09-20 01:00 | 0.75 | 13.3102 | 9.9826 | Reduce | 0.2 | 13.3102 | 2.662 | H3 | 3 | Stable | 0.7 | 117 | 140 | 152 | 138.1667 | 0.1 | 5 | 50 | 62 | 44.5 | 0 | 73.3333 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--39 | Project_021_Risk--39 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Delay to completion of product upgrade | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 99 | 139 | 159 | 135.6667 | 0.1 | 27 | 42 | 68 | 43.8333 |  | 40 | 0
2018-05-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK005 | Project_053_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier Deiivery Schedule | Person_252 | 2018-01-21 | 2018-11-20 | 0.5 | 5.3299 | 2.665 | Reduce | 0.25 | 5.3299 | 1.3325 | H2 | 4 | Stable | 0.5 | 106 | 127 | 153 | 127.8333 | 0.1 | 2 | 40 | 78 | 40 | 0 | 50 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Open PR's | Person_319 | 2018-04-22 | 2018-11-20 01:00 | 0.5 | 7.6338 | 3.8169 | Reduce | 0.3 | 7.6338 | 2.2901 | H3 | 3 | Improving | 0.8 | 87 | 136 | 143 | 129 | 0.1 | 34 | 48 | 63 | 48.1667 | 0 | 40 | 0 | 0
2018-05-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK010 | Project_053_RISK010 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Immaturity of the core product | Person_719 | 2018-08-22 | 2018-11-20 | 0.5 | 6.4649 | 3.2325 | Avoid | 0.7 | 6.4649 | 4.5254 | H1 | 5 | Worsening | [10 empty] | 0 | -40 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--34 | Project_021_Risk--34 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Delay due to poor weather | Person_615 | 2018-03-23 | 2018-06-22 | 0.5 | 1.4007 | 0.49026 | Accept | 0.5 | 1.4007 | 0.49026 | H2 | 4 | Stable | 0.8 | 108 | 134 | 142 | 131 | 0.8 | 108 | 134 | 142 | 131 | 0 | 0 | 0 | 0
2018-05-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK007 | Project_053_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Resources Uavailable | Person_252 | 2017-11-20 | 2019-08-21 | 0.5 | 10.3438 | 5.1719 | Reduce | 0.2 | 7.9015 | 1.5803 | H3 | 3 | Stable | 0.5 | 100 | 138 | 143 | 132.5 | 0.4 | 39 | 51 | 62 | 50.8333 | 23.6111 | 60 | 1 | 15.9666
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK030 | Project_059_RISK030 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | PC Delay - Supplier | Person_517 | 2018-05-23 | 2018-06-22 | 0.15 | 0.48497 | 0.072746 | Reduce | 0.1 | 0.48497 | 0.048497 | H3 | 3 | Stable | 0.8 | 99 | 125 | 160 | 126.5 | 0.2 | 8 | 48 | 72 | 45.3333 | 0 | 33.3333 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-20 22:00 | 2020-08-19 22:00 | 0.5 | 2.1306 | 0.53266 | Accept | 0.5 | 2.1306 | 0.53266 | H2 | 4 | Stable | 0.6 | 119 | 125 | 155 | 129 | 0.6 | 119 | 125 | 155 | 129 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--27 | Project_021_Risk--27 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PR rectification | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 0.1 | 3.6256 | 1.4502 | Accept | 0.1 | 3.6256 | 1.4502 | H2 | 4 | Stable | 0.5 | 101 | 132 | 158 | 131.1667 | 0.5 | 101 | 132 | 158 | 131.1667 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE-10 | Project_067_SE-10 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Configuration baseline unstable for Platform | Person_327 | 2017-10-26 01:00 | 2018-08-18 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.6 | 92 | 128 | 145 | 124.8333 | 0.4 | 37 | 45 | 76 | 48.8333 |  | 60 | 1
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--26 | Project_021_Risk--26 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional design effort required to satisfy SME feedback/input | Person_615 | 2018-01-21 01:00 | 2018-05-21 | 0.2 | 6.0991 | 4.0864 | Accept | 0.2 | 6.0991 | 3.3759 | H2 | 4 | Improving | 0.5 | 112 | 127 | 142 | 127 | 0.5 | 112 | 127 | 142 | 127 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-R6 | Project_067_Risk-R6 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Sub-Contractor Performance - Support Services | Person_713 | 2017-08-21 01:00 | 2018-08-21 | 0.5 | 2.2502 | 1.1251 | Reduce | 0.5 | 2.2502 | 1.1251 | H2 | 4 | Worsening | 0.6 | 94 | 135 | 144 | 129.6667 | 0.3 | 38 | 45 | 79 | 49.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_009 | Project_051 | RISK001 | Project_051_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Generic Labour or Material Overspend | Person_577 | 2012-05-23 | 2021-05-22 | 0.5 | 49.7149 | 7.4572 | Accept | 0.5 | 49.7149 | 7.4572 | H3 | 3 | Stable | 0.6 | 81 | 140 | 148 | 131.5 | 0.6 | 81 | 140 | 148 | 131.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | FOC Acceptance | Person_499 | 2018-07-25 | 2018-08-19 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.15 | 8.471 | 1.2706 | H3 | 3 | Stable | 0.9 | 119 | 139 | 154 | 138.1667 | 0.4 | 4 | 57 | 69 | 50.1667 | -99.9999 | 57.1429 | 1 | -58.2857
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 8.8098 | 3.0834 | Accept | 0.5 | 8.8098 | 1.762 | H2 | 4 | Stable | 0.8 | 85 | 134 | 149 | 128.3333 | 0.8 | 85 | 134 | 149 | 128.3333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK047 | Project_053_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Lab Availability | Person_252 | 2017-10-21 | 2020-01-22 | 0.5 | 0.50826 | 0.40661 | Accept | 0.2 | 0.50826 | 0.40661 | H3 | 3 | Improving | 0.5 | 120 | 127 | 160 | 131.3333 | 0.5 | 120 | 127 | 160 | 131.3333 | 0 | 60 | 1 | 1.8
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-099 | Project_008_Risk-099 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Risk on Consumables Exposure | Person_639 | 2017-08-04 | 2018-08-21 | 0.5 | 5.6817 | 2.8408 | Reduce | 0.5 | 5.6817 | 2.8408 | H3 | 3 | Stable | 0.7 | 93 | 133 | 151 | 129.3333 | 0.4 | 33 | 50 | 78 | 51.8333 | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK004 | Project_059_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Cyber Security Obligations | Person_592 | 2017-10-21 01:00 | 2019-08-04 | 0.4 | 0.80829 | 0.32332 | Reduce | 0.2 | 0.80829 | 0.16166 | H3 | 3 | Stable | 0.8 | 92 | 132 | 158 | 129.6667 | 0.4 | 22 | 54 | 74 | 52 | 0 | 50 | 0 | 0
2018-05-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK043 | Project_053_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Change in REACH/RoSH Legislation | Person_302 | 2017-11-20 | 2018-09-20 | 0.1 | 14.0464 | 4.2139 | Accept | 0.1 | 14.0464 | 4.2139 | H2 | 4 | Stable | 0.5 | 118 | 123 | 146 | 126 | 0.5 | 118 | 123 | 146 | 126 | 0 | 0 | 0 | 0
2018-05-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK046 | Project_053_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Un-Planned Production Activities | Person_252 | 2019-07-22 | 2020-01-22 | 0.5 | 1.2124 | 0.12124 | Accept | 0.2 | 1.2124 | 0.12124 | H3 | 3 | Stable | 0.6 | 90 | 128 | 157 | 126.5 | 0.6 | 90 | 128 | 157 | 126.5 | 0 | 60 | 1 | 1.8
2018-05-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK021 | Project_053_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Product documentation | Person_719 | 2018-08-22 | 2019-07-26 | 0.35 | 2.7703 | 1.3852 | Accept | 0.35 | 2.7703 | 1.3852 | H2 | 4 | Worsening | 0.7 | 99 | 133 | 151 | 130.3333 | 0.7 | 99 | 133 | 151 | 130.3333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Interface implementation | Person_496 | 2018-07-25 | 2018-08-19 | 0.5 | 9.4695 | 4.7347 | Accept | 0.25 | 9.4695 | 4.7347 | H2 | 4 | Stable | 0.5 | 117 | 131 | 154 | 132.5 | 0.5 | 117 | 131 | 154 | 132.5 | 0 | 50 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-034 | Project_008_SER-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_567 | 2018-05-22 | 2018-08-21 | 0.25 | 0.80829 | 0.16166 | Accept | 0.25 | 0.80829 | 0.16166 | H3 | 3 | Stable | 0.7 | 83 | 123 | 157 | 122 | 0.7 | 83 | 123 | 157 | 122 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of the platforms for modification | Person_496 | 2014-01-21 01:00 | 2019-04-10 | 0.67 | 0.64865 | 0.32433 | Accept | 0.5535 | 0.64865 | 0.32433 | H2 | 4 | Stable | 0.5 | 107 | 138 | 155 | 135.6667 | 0.5 | 107 | 138 | 155 | 135.6667 | 0 | 17.3881 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Repairs at Supplier | Person_567 | 2017-08-21 01:00 | 2018-08-21 | 0.15 | 1.7836 | 0.53509 | Accept | 0.15 | 1.7836 | 0.53509 | H3 | 3 | Stable | 0.5 | 106 | 123 | 160 | 126.3333 | 0.5 | 106 | 123 | 160 | 126.3333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_523 | 2018-07-25 | 2018-08-19 | 0.35 | 1.6166 | 0.16166 | Accept | 0.2 | 1.6166 | 0.16166 | H2 | 4 | Stable | 0.8 | 112 | 125 | 152 | 127.3333 | 0.8 | 112 | 125 | 152 | 127.3333 | 0 | 42.8571 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK013 | Project_059_RISK013 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | ICD Errors - Uncertainty | Person_278 | 2017-10-21 01:00 | 2019-03-23 | 0.2 | 1.2124 | 0.24249 | Reduce | 0.15 | 1.2124 | 0.18186 | H3 | 3 | Stable | 0.6 | 101 | 137 | 144 | 132.1667 | 0.4 | 37 | 44 | 63 | 46 | 0 | 25 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK009 | Project_059_RISK009 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Safety risk mitigations - UNCERTAINTY | Person_592 | 2017-10-21 01:00 | 2019-08-20 | 0.1 | 1.6166 | 0.32332 | Accept | 0.1 | 1.6166 | 0.32332 | H3 | 3 | Stable | 0.7 | 101 | 136 | 148 | 132.1667 | 0.7 | 101 | 136 | 148 | 132.1667 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK012 | Project_059_RISK012 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Failures at Acceptance stage - UNCERTAINTY | Person_278 | 2018-02-18 01:00 | 2019-08-04 | 0.3 | 2.0207 | 0.60622 | Reduce | 0.1 | 2.0207 | 0.20207 | H3 | 3 | Stable | 0.5 | 115 | 138 | 142 | 134.8333 | 0.2 | 34 | 46 | 68 | 47.6667 | 0 | 66.6667 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Lack of Spares Availability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 0.2 | 2.0207 | 0.40414 | Accept | 0.2 | 2.0207 | 0.40414 | H3 | 3 | Stable | 0.8 | 117 | 127 | 144 | 128.1667 | 0.8 | 117 | 127 | 144 | 128.1667 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-148 | Project_008_SER-148 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Demands but not provisioned | Person_639 | 2017-08-21 01:00 | 2018-08-21 | 0.3 | 1.2124 | 0.24249 | Accept | 0.3 | 1.2124 | 0.24249 | H3 | 3 | Stable | 0.6 | 83 | 138 | 144 | 129.8333 | 0.6 | 83 | 138 | 144 | 129.8333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-094 | Project_008_Risk-094 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Consumable Stock Levels | Person_567 | 2017-04-22 | 2018-08-21 | 0.5 | 0 | 0 | Accept | 0.5 | 0 | 0 | H3 | 3 | Stable | 0.7 | 91 | 135 | 152 | 130.5 | 0.7 | 91 | 135 | 152 | 130.5 |  | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK003 | Project_059_RISK003 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Catalyst Requirements | Person_278 | 2017-10-21 01:00 | 2019-02-20 01:00 | 0.2 | 0.5596 | 0.05596 | Accept | 0.2 | 0.5596 | 0.05596 | H3 | 3 | Stable | 0.6 | 82 | 129 | 146 | 124 | 0.6 | 82 | 129 | 146 | 124 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_077 | 2016-01-22 01:00 | 2018-11-17 01:00 | 0.15 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Improving | 0.8 | 85 | 138 | 144 | 130.1667 | 0.3 | 7 | 47 | 79 | 45.6667 |  | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK002 | Project_059_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SW Compatibility | Person_517 | 2017-11-20 01:00 | 2018-10-22 01:00 | 0.1 | 6.3794 | 1.2759 | Accept | 0.1 | 6.3794 | 1.2759 | H3 | 3 | Stable | 0.9 | 110 | 124 | 152 | 126.3333 | 0.9 | 110 | 124 | 152 | 126.3333 | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK001 | Project_059_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Critical Personnel | Person_162 | 2017-10-21 01:00 | 2019-08-04 | 0.2 | 23.5255 | 11.7628 | Accept | 0.2 | 23.5255 | 11.7628 | H3 | 3 | Stable | 0.7 | 103 | 136 | 142 | 131.5 | 0.7 | 103 | 136 | 142 | 131.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-07-21 | 0.1 | 4.0291 | 0.40291 | Reduce | 0.1 | 4.0291 | 0.40291 | H2 | 4 | Improving | 0.8 | 91 | 128 | 153 | 126 | 0.1 | 28 | 55 | 61 | 51.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK036 | Project_042_RISK036 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 2 | Person_455 | 2019-05-24 | 2020-05-22 | 0.25 | 1.8788 | 0.46971 | Accept | 0.2 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.6 | 101 | 135 | 157 | 133 | 0.6 | 101 | 135 | 157 | 133 | 20 | 20 | 0 | 12
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK048 | Project_042_RISK048 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | On the Job Training. | Person_371 | 2018-03-02 01:00 | 2019-02-05 01:00 | 0.85 | 2.1043 | 1.7886 | Reduce | 0.5 | 2.1043 | 1.0521 | H1 | 5 | Stable | 0.5 | 109 | 123 | 147 | 124.6667 | 0.2 | 1 | 41 | 78 | 40.5 | 0 | 41.1765 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK039 | Project_042_RISK039 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality Issues 16th August to 15th August | Person_540 | 2020-01-06 01:00 | 2021-01-04 01:00 | 0.1 | 4.6971 | 0.93941 | Accept | 0.08 | 3.7576 | 0.56365 | H2 | 4 | Stable | 0.5 | 108 | 137 | 144 | 133.3333 | 0.5 | 108 | 137 | 144 | 133.3333 | 20 | 20 | 0 | 12
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK033 | Project_042_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st April to 30 June | Person_455 | 2019-08-22 01:00 | 2019-11-20 01:00 | 0.2 | 1.8788 | 0.46971 | Accept | 0.15 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.7 | 114 | 140 | 155 | 138.1667 | 0.7 | 114 | 140 | 155 | 138.1667 | 20 | 25 | 0 | 12
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK049 | Project_042_RISK049 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Industry STTE Upkeep. | Person_371 | 2018-03-02 01:00 | 2019-02-05 01:00 | 0.85 | 1.3152 | 1.1179 | Reduce | 0.5 | 1.3152 | 0.65759 | H2 | 4 | Stable | 0.5 | 115 | 123 | 152 | 126.5 | 0.1 | 26 | 49 | 68 | 48.3333 | 0 | 41.1765 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK035 | Project_042_RISK035 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st October to 31st December | Person_455 | 2021-02-20 01:00 | 2021-05-22 | 0.2 | 1.8788 | 0.46971 | Accept | 0.15 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.9 | 117 | 131 | 160 | 133.5 | 0.9 | 117 | 131 | 160 | 133.5 | 20 | 25 | 0 | 12
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK034 | Project_042_RISK034 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st July to 30 September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 0.2 | 2.2828 | 0.31959 | Accept | 0.15 | 2.2828 | 0.31959 | H2 | 4 | Stable | 0.5 | 115 | 138 | 160 | 137.8333 | 0.5 | 115 | 138 | 160 | 137.8333 | 0 | 25 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK040 | Project_042_RISK040 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st May to 30 Oct | Person_455 | 2019-09-21 01:00 | 2020-03-21 | 0.1 | 0.56365 | 0.11273 | Accept | 0.07 | 0.28182 | 0.028182 | H2 | 4 | Stable | 0.6 | 80 | 122 | 160 | 121.3333 | 0.6 | 80 | 122 | 160 | 121.3333 | 50 | 30 | 0 | 30
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK042 | Project_042_RISK042 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st February to 14th July | Person_455 | 2020-06-23 | 2020-12-03 01:00 | 0.1 | 4.6971 | 0.93941 | Accept | 0.08 | 3.7576 | 0.67638 | H2 | 4 | Stable | 0.5 | 89 | 137 | 153 | 131.6667 | 0.5 | 89 | 137 | 153 | 131.6667 | 20 | 20 | 0 | 12
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK044 | Project_042_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2018-02-20 01:00 | 2018-12-21 01:00 | 0.32 | 6.5759 | 2.1043 | Reduce | 0.17 | 6.5759 | 1.1179 | H2 | 4 | Stable | 0.6 | 86 | 138 | 158 | 132.6667 | 0.1 | 19 | 41 | 71 | 42.3333 | 0 | 46.875 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK041 | Project_042_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st Jan | Person_455 | 2020-03-23 | 2020-06-22 | 0.1 | 1.8788 | 0.18788 | Accept | 0.08 | 1.5031 | 0.12024 | H2 | 4 | Stable | 0.8 | 86 | 135 | 153 | 129.8333 | 0.8 | 86 | 135 | 153 | 129.8333 | 20 | 20 | 0 | 12
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK024 | Project_042_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2019-09-21 01:00 | 2020-09-19 01:00 | 0.33 | 9.3941 | 3.1001 | Reduce | 0.15 | 7.5153 | 1.1273 | H2 | 4 | Stable | 0.5 | 113 | 140 | 148 | 136.8333 | 0.4 | 2 | 51 | 73 | 46.5 | 20 | 54.5455 | 0 | 12
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Local customer Engineers in country | Person_455 | 2018-12-20 01:00 | 2021-05-22 | 0.05 | 0.56365 | 0.11273 | Accept | 0.05 | 0.28182 | 0.028182 | H2 | 4 | Stable | 0.7 | 84 | 121 | 143 | 118.5 | 0.7 | 84 | 121 | 143 | 118.5 | 50 | 0 | 0 | 30
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK026 | Project_042_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st Jan to 31st March | Person_455 | 2020-05-23 | 2020-08-20 01:00 | 0.25 | 4.6971 | 0.93941 | Accept | 0.15 | 3.7576 | 0.37576 | H2 | 4 | Stable | 0.7 | 120 | 131 | 159 | 133.8333 | 0.7 | 120 | 131 | 159 | 133.8333 | 20 | 40 | 0 | 12
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK045 | Project_042_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2019-01-22 01:00 | 2019-05-23 | 0.25 | 3.908 | 0.97699 | Reduce | 0.25 | 3.908 | 0.97699 | H2 | 4 | Stable | 0.8 | 86 | 131 | 144 | 125.6667 | 0.3 | 16 | 50 | 69 | 47.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK025 | Project_042_RISK025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to 31 Dec | Person_455 | 2020-09-20 01:00 | 2021-05-22 | 0.2 | 1.8788 | 0.46971 | Accept | 0.15 | 1.1273 | 0.11273 | H2 | 4 | Stable | 0.8 | 109 | 135 | 142 | 131.8333 | 0.8 | 109 | 135 | 142 | 131.8333 | 40 | 25 | 0 | 24
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK028 | Project_042_RISK028 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st July to 30th September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 0.25 | 0 | 0 | Accept | 0.15 | 0 | 0 | H2 | 4 | Stable | 0.5 | 87 | 121 | 151 | 120.3333 | 0.5 | 87 | 121 | 151 | 120.3333 |  | 40 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK027 | Project_042_RISK027 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st April to 30th June | Person_455 | 2020-08-21 01:00 | 2020-09-19 01:00 | 0.25 | 6.1106 | 0.61106 | Accept | 0.15 | 6.1106 | 0.61106 | H2 | 4 | Stable | 0.9 | 115 | 134 | 154 | 134.1667 | 0.9 | 115 | 134 | 154 | 134.1667 | 0 | 40 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK004 | Project_075_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional Material required for investigations | Person_627 | 2017-07-21 | 2018-11-20 01:00 | 0.4 | 3.3748 | 1.3499 | Reduce | 0.1 | 3.3748 | 0.33748 | H3 | 3 | Stable | 0.6 | 86 | 136 | 149 | 129.8333 | 0.1 | 34 | 41 | 72 | 45 | 0 | 75 | 1 | 2.25
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK037 | Project_042_RISK037 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 1 | Person_455 | 2020-05-23 | 2021-05-22 | 0.14 | 0 | 0 | Accept | 0.14 | 0 | 0 | H2 | 4 | Stable | 0.7 | 80 | 123 | 142 | 119 | 0.7 | 80 | 123 | 142 | 119 |  | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK047 | Project_042_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables | Person_455 | 2020-11-20 01:00 | 2021-05-22 | 0.2 | 4.0498 | 2.8349 | Accept | 0.1 | 4.0498 | 2.8349 | H2 | 4 | Stable | 0.7 | 84 | 136 | 159 | 131.1667 | 0.7 | 84 | 136 | 159 | 131.1667 | 0 | 50 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK024 | Project_075_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Failure to meet promised delivery dates | Person_627 | 2017-09-20 01:00 | 2019-01-21 01:00 | 0.5 | 2.5311 | 1.2656 | Reduce | 0.4 | 2.5311 | 1.0124 | H2 | 4 | Stable | 0.8 | 105 | 133 | 144 | 130.1667 | 0.3 | 2 | 49 | 67 | 44.1667 | 0 | 20 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK022 | Project_042_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2017-09-20 01:00 | 2018-09-20 01:00 | 0.2 | 5.9059 | 1.7718 | Accept | 0.18 | 5.9059 | 1.7718 | H2 | 4 | Stable | 0.6 | 95 | 127 | 156 | 126.5 | 0.6 | 95 | 127 | 156 | 126.5 | 0 | 10 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK043 | Project_042_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st December | Person_455 | 2021-03-23 | 2021-05-22 | 0.1 | 2.0249 | 0.20249 | Accept | 0.08 | 2.0249 | 0.20249 | H3 | 3 | Stable | 0.8 | 85 | 121 | 156 | 120.8333 | 0.8 | 85 | 121 | 156 | 120.8333 | 0 | 20 | 1 | 0.6
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK009 | Project_075_RISK009 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Suppliers can't meet timescales. | Person_627 | 2016-12-20 01:00 | 2018-11-20 01:00 | 0.7 | 22.2176 | 15.5523 | Reduce | 0.6 | 6.7497 | 4.0498 | H1 | 5 | Stable | 0.5 | 91 | 125 | 154 | 124.1667 | 0.2 | 6 | 55 | 73 | 49.8333 | 69.6202 | 14.2857 | 0 | 41.7721
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK017 | Project_075_RISK017 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | New Materials not tested for Out Gassing | Person_451 | 2017-07-21 | 2018-08-20 | 0.35 | 12.3041 | 4.3064 | Reduce | 0.2 | 12.3041 | 2.4608 | H2 | 4 | Stable | 0.5 | 82 | 124 | 149 | 121.1667 | 0.1 | 3 | 46 | 66 | 42.1667 | 0 | 42.8571 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK046 | Project_042_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables - June | Person_455 | 2018-11-21 01:00 | 2020-11-19 01:00 | 0.2 | 26.0143 | 13.0071 | Accept | 0.1 | 26.0143 | 13.0071 | H2 | 4 | Stable | 0.9 | 120 | 136 | 144 | 134.6667 | 0.9 | 120 | 136 | 144 | 134.6667 | 0 | 50 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK023 | Project_042_RISK023 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2018-09-21 01:00 | 2019-09-20 01:00 | 0.2 | 2.5311 | 1.2656 | Accept | 0.1 | 2.5311 | 1.2656 | H2 | 4 | Stable | 0.6 | 116 | 124 | 149 | 126.8333 | 0.6 | 116 | 124 | 149 | 126.8333 | 0 | 50 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK029 | Project_042_RISK029 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st October to 31st December | Person_455 | 2020-11-20 01:00 | 2021-05-22 | 0.25 | 0.98433 | 0.78746 | Accept | 0.1 | 0.98433 | 0.78746 | H2 | 4 | Stable | 0.9 | 116 | 128 | 155 | 130.5 | 0.9 | 116 | 128 | 155 | 130.5 | 0 | 60 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK008 | Project_075_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Failures at Acceptance stage | Person_449 | 2017-07-21 | 2019-04-22 | 0.3 | 31.4106 | 15.7053 | Accept | 0.3 | 31.4106 | 15.7053 | H2 | 4 | Stable | 0.8 | 119 | 137 | 147 | 135.6667 | 0.8 | 119 | 137 | 147 | 135.6667 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK007 | Project_075_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Range performance does not meet requirement. | Person_003 | 2017-07-21 | 2018-09-20 01:00 | 0.1 | 8.2789 | 2.4837 | Accept | 0.1 | 8.2789 | 2.4837 | H3 | 3 | Stable | 0.5 | 89 | 132 | 157 | 129 | 0.5 | 89 | 132 | 157 | 129 | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK010 | Project_075_RISK010 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | We do not achieve Standard compliant energy over temperature | Person_449 | 2017-07-21 | 2018-09-20 01:00 | 0.5 | 9.6742 | 0.96742 | Accept | 0.5 | 9.6742 | 0.96742 | H1 | 5 | Stable | 0.6 | 118 | 135 | 144 | 133.6667 | 0.6 | 118 | 135 | 144 | 133.6667 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK018 | Project_075_RISK018 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Crystal switch | Person_627 | 2017-03-21 01:00 | 2018-09-20 01:00 | 0.5 | 0.89832 | 0.17966 | Accept | 0.5 | 0.89832 | 0.17966 | H2 | 4 | Stable | 0.5 | 109 | 138 | 146 | 134.5 | 0.5 | 109 | 138 | 146 | 134.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2018-10-20 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 0.45943 | 0.18377 | H2 | 4 | Stable | 0.8 | 110 | 123 | 157 | 126.5 | 0.4 | 37 | 42 | 70 | 45.8333 | 88.3943 | 20 | 0 | 53.0366
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_703 | 2015-05-24 | 2019-05-22 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 1.1996 | 0.17994 | H3 | 3 | Stable | 0.5 | 88 | 125 | 151 | 123.1667 | 0.2 | 19 | 44 | 63 | 43 | 80.9521 | 70 | 1 | 50.6713
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-119 | Project_029_Risk-119 | Opportunitity | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Not required to support on load & offload of Customer Furnished Equipmnet | Person_585 | 2017-05-23 | 2020-04-16 | 0.8 | 5.1334 | 4.1067 | Exploit | 0.8 | 3.4137 | 2.731 | H2 | 4 | Stable | [10 empty] | 33.5 | 0 | 0 | 20.1
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2018-03-22 | 2019-07-21 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.7 | 80 | 132 | 147 | 125.8333 | 0.2 | 5 | 56 | 69 | 49.6667 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_585 | 2017-09-02 01:00 | 2018-10-31 01:00 | 0.1 | 6.4168 | 0.64168 | Transfer | 0.1 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sub-system FPGA | Person_332 | 2017-01-21 01:00 | 2019-05-16 | 0.4 | 1.5914 | 0.63655 | Reduce | 0.2 | 1.5914 | 0.31827 | H3 | 3 | Stable | 0.6 | 109 | 137 | 143 | 133.3333 | 0.4 | 33 | 42 | 66 | 44.5 | 0 | 50 | 1 | 1.5
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort for System HW/SW- System upgrade. | Person_199 | 2017-05-23 | 2019-09-18 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.2 | 2.5667 | 0.51334 | H3 | 3 | Stable | 0.8 | 106 | 136 | 142 | 132 | 0.1 | 2 | 51 | 74 | 46.6667 | 0 | 33.3333 | 1 | 1
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.25 | 3.5934 | 0.89835 | H2 | 4 | Stable | 0.7 | 103 | 127 | 151 | 127 | 0.1 | 2 | 44 | 60 | 39.6667 | 0 | 50 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Minimum Order Quantities | Person_403 | 2017-11-20 01:00 | 2018-06-21 | 0.2 | 1.925 | 0.38501 | Exploit | 0.2 | 1.925 | 0.38501 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_403 | 2018-04-22 | 2018-08-22 01:00 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Worsening | 0.7 | 106 | 137 | 149 | 133.8333 | 0.4 | 33 | 48 | 72 | 49.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) at the System level on product platform - performed by 3rd parties | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Sub-system / product system accreditation hindered by Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.1 | 0.25667 | 0.025667 | Transfer | 0.1 | 0.25667 | 0.025667 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_694 | 2017-05-23 | 2018-10-07 01:00 | 0.3 | 0 | 0 | Transfer | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 66.6667 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2018-05-15 | 0.3 | 0.89835 | 0.26951 | Transfer | 0.3 | 0.89835 | 0.26951 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 0.35 | 1.9208 | 0.67227 | Reduce | 0.25 | 1.9208 | 0.48019 | H2 | 4 | Stable | 0.8 | 101 | 128 | 145 | 126.3333 | 0.1 | 36 | 57 | 60 | 54 | 0 | 28.5714 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2018-03-22 | 2018-10-18 01:00 | 0.4 | 0.77001 | 0.30801 | Reduce | 0.3 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.5 | 80 | 125 | 158 | 123 | 0.4 | 36 | 58 | 78 | 57.6667 | 0 | 25 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_694 | 2018-02-20 01:00 | 2018-09-20 01:00 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.8 | 87 | 131 | 160 | 128.5 | 0.2 | 4 | 50 | 63 | 44.5 | 0 | 28.5714 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_585 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 1.0695 | 0.74863 | Accept | 0.03 | 1.0695 | 0.74863 | H3 | 3 | Stable | 0.5 | 96 | 123 | 144 | 122 | 0.5 | 96 | 123 | 144 | 122 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-054 | Project_062_Risk-054 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | sub-system rework to reviised standard | Person_031 | 2017-07-21 | 2018-11-21 01:00 | 0.4 | 0.62744 | 0.25098 | Transfer | 0.4 | 0.62744 | 0.25098 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-010 | Project_062_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Resource | Person_479 | 2017-07-21 | 2019-02-21 01:00 | 0.4 | 7.5293 | 3.0117 | Reduce | 0.3 | 7.5293 | 2.2588 | H2 | 4 | Stable | 0.6 | 114 | 122 | 143 | 124.1667 | 0.3 | 39 | 59 | 70 | 57.5 | 0 | 25 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs | Person_403 | 2018-04-22 | 2018-08-22 01:00 | 0.5 | 4.183 | 1.2549 | Accept | 0.5 | 4.183 | 1.2549 | H2 | 4 | Stable | 0.7 | 119 | 134 | 152 | 134.5 | 0.7 | 119 | 134 | 152 | 134.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-013 | Project_062_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Unavailability of Network | Person_479 | 2017-07-21 | 2018-07-08 | 0.25 | 3.5555 | 0.88888 | Reduce | 0.2 | 3.5555 | 0.7111 | H3 | 3 | Stable | 0.6 | 103 | 122 | 160 | 125.1667 | 0.4 | 12 | 47 | 69 | 44.8333 | 0 | 20 | 1 | 0.6
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-011 | Project_062_Risk-011 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Variant deviations between SW | Person_479 | 2017-07-21 | 2018-06-22 | 0.4 | 0.71808 | 0.28723 | Reduce | 0.3 | 0.71808 | 0.21542 | H2 | 4 | Stable | 0.9 | 104 | 129 | 156 | 129.3333 | 0.4 | 32 | 54 | 60 | 51.3333 | 0 | 25 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-056 | Project_062_Risk-056 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Supplier integration acceptance by end Customer | Person_031 | 2017-07-21 | 2018-11-21 01:00 | 0.3 | 1.8823 | 0.5647 | Reduce | 0.3 | 1.8823 | 0.5647 | H3 | 3 | Stable | 0.6 | 111 | 138 | 145 | 134.6667 | 0.3 | 9 | 54 | 75 | 50 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-017 | Project_062_Risk-017 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer platform Schedule Unknown | Person_459 | 2017-07-21 | 2018-10-22 01:00 | 0.2 | 2.5098 | 0.50196 | Avoid | 0.1 | 2.5098 | 0.25098 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 12.7037 | 4.4463 | Accept | 0.25 | 12.7037 | 3.1759 | H2 | 4 | Stable | 0.7 | 110 | 121 | 155 | 124.8333 | 0.7 | 110 | 121 | 155 | 124.8333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-037 | Project_062_Risk-037 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Server availability | Person_479 | 2017-07-21 | 2018-09-20 01:00 | 0.35 | 4.183 | 1.464 | Avoid | 0.1 | 4.183 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 71.4286 | 1 | 2.1429
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-016 | Project_062_Risk-016 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier Component Unavailability | Person_664 | 2017-07-21 | 2018-09-20 01:00 | 0.3 | 4.183 | 1.2549 | Reduce | 0.2 | 4.183 | 0.83659 | H3 | 3 | Stable | 0.8 | 120 | 133 | 143 | 132.5 | 0.4 | 21 | 57 | 78 | 54.5 | 0 | 33.3333 | 1 | 1
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-020 | Project_062_Risk-020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Security Encryption Solution | Person_245 | 2017-07-21 | 2018-09-20 01:00 | 0.25 | 4.183 | 1.0457 | Reduce | 0.2 | 4.183 | 0.83659 | H2 | 4 | Improving | 0.9 | 118 | 135 | 158 | 136 | 0.2 | 36 | 49 | 64 | 49.3333 | 0 | 20 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-021 | Project_062_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Hardware CoSupplierng | Person_664 | 2017-07-21 | 2018-09-20 01:00 | 0.3 | 7.5293 | 2.2588 | Reduce | 0.25 | 7.5293 | 1.8823 | H2 | 4 | Stable | 0.7 | 110 | 125 | 142 | 125.3333 | 0.1 | 5 | 49 | 70 | 45.1667 | 0 | 16.6667 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-043 | Project_062_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | User response | Person_479 | 2017-07-21 | 2019-02-21 01:00 | 0.35 | 3.3464 | 1.1712 | Avoid | 0.25 | 3.3464 | 0.83659 | H2 | 4 | Stable | [10 empty] | 0 | 28.5714 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-047 | Project_062_Risk-047 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Redhat6 on PCI shelf | Person_245 | 2017-07-21 | 2019-03-24 | 0.3 | 7.1808 | 2.1542 | Avoid | 0.3 | 7.1808 | 2.1542 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-025 | Project_062_Risk-025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | System Obsolescence Risk | Person_543 | 2017-07-21 | 2019-03-22 | 0.3 | 2.0915 | 0.62744 | Avoid | 0.2 | 2.0915 | 0.4183 | H2 | 4 | Stable | [10 empty] | 0 | 33.3333 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-022 | Project_062_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Registers Might Be Unstable | Person_479 | 2017-07-21 | 2018-08-19 | 0.25 | 1.3385 | 0.33464 | Reduce | 0.2 | 1.3385 | 0.26771 | H3 | 3 | Stable | 0.8 | 84 | 128 | 145 | 123.5 | 0.2 | 22 | 53 | 61 | 49.1667 | 0 | 20 | 1 | 0.6
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-023 | Project_062_Risk-023 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Change In Security Boundary | Person_031 | 2017-07-21 | 2019-02-21 01:00 | 0.3 | 4.6013 | 1.3804 | Reduce | 0.15 | 4.6013 | 0.69019 | H3 | 3 | Stable | 0.6 | 89 | 127 | 148 | 124.1667 | 0.1 | 4 | 50 | 63 | 44.5 | 0 | 50 | 1 | 1.5
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-006 | Project_062_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unavailability of Test Hardware | Person_253 | 2017-07-21 | 2019-03-22 | 0.5 | 2.5098 | 1.2549 | Reduce | 0.25 | 2.5098 | 0.62744 | H2 | 4 | Stable | 0.5 | 114 | 133 | 160 | 134.3333 | 0.3 | 1 | 56 | 75 | 50 | 0 | 50 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-048 | Project_062_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software lockdown features | Person_245 | 2017-07-21 | 2018-11-21 01:00 | 0.5 | 0.71808 | 0.35904 | Reduce | 0.5 | 0.71808 | 0.35904 | H2 | 4 | Stable | 0.9 | 94 | 124 | 150 | 123.3333 | 0.2 | 39 | 48 | 78 | 51.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-005 | Project_062_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Security Solution Integration | Person_245 | 2017-07-21 | 2018-11-14 01:00 | 0.3 | 4.6013 | 1.3804 | Avoid | 0.25 | 4.6013 | 1.1503 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 2.5098 | 1.2549 | Accept | 0.2 | 2.5098 | 0.75293 | H3 | 3 | Stable | 0.5 | 89 | 134 | 142 | 127.8333 | 0.5 | 89 | 134 | 142 | 127.8333 | 0 | 33.3333 | 1 | 1
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-012 | Project_062_Risk-012 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Integration Rig Move | Person_253 | 2018-05-23 | 2019-05-23 | 0.3 | 0.4183 | 0.12549 | Avoid | 0.3 | 0.4183 | 0.12549 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen Component Rack Re-Design [in addition to costed effort] | Person_332 | 2017-05-28 | 2018-11-30 01:00 | 0.2 | 1.0457 | 0.52287 | Accept | 0.2 | 1.0457 | 0.52287 | H3 | 3 | Improving | 0.5 | 104 | 140 | 157 | 136.8333 | 0.5 | 104 | 140 | 157 | 136.8333 | 0 | 0 | 1 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-024 | Project_062_Risk-024 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional SW Build post-Factory Acceptance Test | Person_253 | 2019-01-22 01:00 | 2019-04-22 | 0.3 | 1.7778 | 0.53333 | Avoid | 0.3 | 1.7778 | 0.53333 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-027 | Project_062_Risk-027 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Facility to Test modifications | Person_253 | 2018-08-22 01:00 | 2020-04-21 | 0.5 | 2.3703 | 1.1852 | Reduce | 0.4 | 2.3703 | 0.94814 | H2 | 4 | Stable | 0.5 | 103 | 121 | 143 | 121.6667 | 0.4 | 1 | 57 | 69 | 49.6667 | 0 | 20 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-008 | Project_062_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Paperwork for Legacy Items | Person_459 | 2018-03-23 | 2019-03-24 | 0.3 | 0.83659 | 0.25098 | Avoid | 0.3 | 0.83659 | 0.25098 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-007 | Project_062_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Hardware Encryption / Protection | Person_479 | 2018-02-10 01:00 | 2019-03-22 | 0.3 | 4.183 | 1.2549 | Reduce | 0.2 | 4.183 | 0.83659 | H3 | 3 | Stable | 0.8 | 87 | 138 | 142 | 130.1667 | 0.1 | 1 | 54 | 60 | 46.1667 | 0 | 33.3333 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK004 | Project_079_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 8.8685 | 1.7737 | Reduce | 0.15 | 8.8685 | 1.3303 | H3 | 3 | Stable | 0.5 | 111 | 134 | 141 | 131.3333 | 0.3 | 24 | 57 | 60 | 52 | 0 | 25 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK026 | Project_079_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Clause on Joint Proposal | Person_261 | 2018-05-04 | 2019-05-23 | 0.4 | 30.653 | 12.2612 | -- | 0.4 | 30.653 | 12.2612 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK014 | Project_079_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 0.05 | 21.725 | 1.0862 | Reduce | 0.05 | 21.725 | 1.0862 | H3 | 3 | Improving | 0.7 | 90 | 132 | 152 | 128.3333 | 0.3 | 4 | 59 | 63 | 50.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK025 | Project_079_RISK025 | Opportunitity | Project Contingency | Open | H3 | 3 | 4. Customers | Reclaim pellet delivery delays from Customer | Person_002 | 2018-02-02 01:00 | 2020-04-22 | 0.1 | 33.9266 | 3.3927 | -- | 0.1 | 33.9266 | 3.3927 | H3 | 3 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK005 | Project_079_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 3.7631 | 2.2578 | -- | 0.5 | 3.7631 | 1.8815 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK016 | Project_079_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.8 | 1.9552 | 1.5642 | Avoid | 0.2 | 1.9552 | 0.39105 | H3 | 3 | Worsening | [10 empty] | 0 | 75 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK022 | Project_079_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Equipment | Person_104 | 2018-01-14 01:00 | 2019-08-20 | 0.15 | 7.321 | 1.0982 | Reduce | 0.15 | 7.321 | 1.0982 | H3 | 3 | Stable | 0.7 | 114 | 140 | 146 | 136.6667 | 0.2 | 39 | 59 | 62 | 56.1667 | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK002 | Project_079_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2022-05-22 | 0.15 | 26.7842 | 4.0176 | Avoid | 0.15 | 26.7842 | 4.0176 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK024 | Project_079_RISK024 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Procurement/Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 0.8 | 14.4992 | 11.5993 | -- | 0.8 | 0 | 0 | H1 | 5 | Worsening | [10 empty] | 100 | 0 | 0 | 60
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK012 | Project_079_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Customer require additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.05 | 13.6897 | 0.68448 | Avoid | 0.05 | 13.6897 | 0.68448 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK004 | Project_081_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Greater number of failures/ investigations | Person_260 | 2017-09-27 01:00 | 2021-09-27 01:00 | 0.6 | 2.685 | 1.611 | Reduce | 0.6 | 2.685 | 1.611 | H3 | 3 | Worsening | 0.8 | 84 | 133 | 158 | 129 | 0.2 | 30 | 54 | 70 | 52.6667 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK006 | Project_081_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Large volume of repairs loaded to clear backlog | Person_260 | 2017-09-27 01:00 | 2021-09-27 01:00 | 0.25 | 3.1854 | 0.79634 | Reduce | 0.25 | 3.1854 | 0.79634 | H3 | 3 | Stable | 0.5 | 95 | 135 | 158 | 132.1667 | 0.4 | 9 | 46 | 70 | 43.8333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK005 | Project_081_RISK005 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Marching army Customer costs for duration of contract | Person_260 | 2021-05-23 | 2021-09-27 01:00 | 0.2 | 1.6598 | 0.33196 | Reduce | 0.2 | 1.6598 | 0.33196 | H3 | 3 | Stable | 0.7 | 108 | 134 | 142 | 131 | 0.2 | 9 | 43 | 73 | 42.3333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK021 | Project_081_RISK021 | Threat | Financial Contingency | Open | H3 | 3 | 7. Finance | Increase of bank fees and other direct costs | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.15 | 2.27 | 0.3405 | Avoid | 0.15 | 2.27 | 0.3405 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK024 | Project_081_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer- Training | Person_115 | 2017-09-27 01:00 | 2021-11-27 01:00 | 0.7 | 1.1532 | 0.80724 | Reduce | 0.7 | 1.1532 | 0.80724 | H3 | 3 | Stable | 0.5 | 84 | 121 | 154 | 120.3333 | 0.4 | 33 | 53 | 72 | 52.8333 | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK002 | Project_081_RISK002 | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Supplier costs to be covered by us | Person_260 | 2017-09-27 01:00 | 2021-09-20 01:00 | 0.2 | 2.0381 | 0.40763 | Reduce | 0.2 | 2.0381 | 0.40763 | H3 | 3 | Stable | 0.9 | 94 | 136 | 157 | 132.5 | 0.3 | 13 | 58 | 64 | 51.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK023 | Project_081_RISK023 | Threat | Project Contingency | Open | H2 | 4 | 7. Finance | Risk of funding requirement | Person_115 | 2017-09-27 01:00 | 2021-09-27 01:00 | 0.7 | 1.5207 | 1.0645 | Reduce | 0.7 | 1.5202 | 1.0641 | H3 | 3 | Stable | 0.6 | 88 | 127 | 157 | 125.5 | 0.1 | 20 | 45 | 73 | 45.5 | 0.032103 | 0 | 1 | 0.019262
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK008 | Project_081_RISK008 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Failure to meet repair turnaround time | Person_260 | 2017-09-27 01:00 | 2021-09-20 01:00 | 0.1 | 1.5866 | 0.15866 | Reduce | 0.1 | 1.5866 | 0.15866 | H3 | 3 | Stable | 0.8 | 115 | 133 | 154 | 133.5 | 0.4 | 29 | 52 | 65 | 50.3333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK007 | Project_081_RISK007 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | High value supplier repair/replacements required | Person_260 | 2017-09-27 01:00 | 2021-09-20 01:00 | 0.4 | 3.7834 | 1.5133 | Reduce | 0.4 | 3.7834 | 1.5133 | H3 | 3 | Stable | 0.7 | 104 | 132 | 152 | 130.6667 | 0.1 | 18 | 56 | 62 | 50.6667 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK009 | Project_081_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 7. Finance | Increase of Spares UPCs | Person_260 | 2017-09-27 01:00 | 2019-09-28 01:00 | 0.2 | 17.5011 | 3.5002 | Reduce | 0.2 | 17.5011 | 3.5002 | H3 | 3 | Stable | 0.7 | 98 | 121 | 157 | 123.1667 | 0.2 | 35 | 48 | 61 | 48 | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP002 | Project_081_OPP002 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Core Management team shared across other programmes | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.3 | 0.91533 | 0.2746 | -- | 0.3 | 0.91533 | 0.2746 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP001 | Project_081_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 7. Finance | Reduction in Spares UPC | Person_260 | 2017-07-21 | 2021-07-21 | 0.2 | 6.1022 | 1.2204 | -- | 0.2 | 6.1022 | 1.2204 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP004 | Project_081_OPP004 | Opportunitity | Project Contingency | Open | H3 | 3 | 7. Finance | Less repairs than planned in base costs | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.2 | 1.2204 | 0.24409 | -- | 0.2 | 1.2204 | 0.24409 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP003 | Project_081_OPP003 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Supplier abilities mature exponentially throughout contract requiring less FSE support | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.25 | 1.8307 | 0.45767 | -- | 0.25 | 1.8307 | 0.45767 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK015 | Project_081_RISK015 | Threat | Project Contingency | Open | H3 | 3 | 7. Finance | Our being liable for freight costs. | Person_260 | 2018-03-23 | 2021-09-20 01:00 | 0.3 | 3.0511 | 0.91533 | Reduce | 0.3 | 3.0511 | 0.91533 | H3 | 3 | Stable | 0.6 | 111 | 123 | 156 | 126.5 | 0.2 | 13 | 52 | 72 | 48.8333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK014 | Project_081_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 7. Finance | Supplier request financial support for Training admin. | Person_260 | 2018-02-20 01:00 | 2021-09-20 01:00 | 0.1 | 0.50038 | 0.050038 | Reduce | 0.1 | 0.50038 | 0.050038 | H3 | 3 | Stable | 0.6 | 98 | 136 | 153 | 132.5 | 0.4 | 33 | 59 | 60 | 54.8333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK017 | Project_081_RISK017 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Extended working hours during site visits | Person_419 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.3 | 1.1716 | 0.35149 | Reduce | 0.3 | 1.1716 | 0.35149 | H3 | 3 | Stable | 0.5 | 118 | 125 | 150 | 128 | 0.1 | 29 | 55 | 78 | 54.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK016 | Project_081_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Additional visit support requested by Customer/Supplier | Person_260 | 2017-10-21 01:00 | 2021-09-20 01:00 | 0.4 | 2.331 | 0.93242 | Reduce | 0.4 | 2.331 | 0.93242 | H3 | 3 | Stable | 0.7 | 95 | 137 | 158 | 133.5 | 0.4 | 26 | 44 | 75 | 46.1667 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK011 | Project_081_RISK011 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Additional quantities of spares/material/STTE requested by customer | Person_260 | 2017-07-21 | 2019-07-22 | 0.1 | 6.3707 | 0.63707 | Reduce | 0.1 | 6.3707 | 0.63707 | H3 | 3 | Stable | 0.7 | 109 | 136 | 148 | 133.5 | 0.3 | 2 | 49 | 67 | 44.1667 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK010 | Project_081_RISK010 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Increased material lead times for Spares | Person_649 | 2017-09-27 01:00 | 2019-09-28 01:00 | 0.1 | 6.3707 | 0.63707 | Reduce | 0.1 | 6.3707 | 0.63707 | H3 | 3 | Stable | 0.5 | 119 | 122 | 156 | 127.1667 | 0.1 | 31 | 57 | 60 | 53.1667 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK013 | Project_081_RISK013 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Additional training requested by customer. | Person_419 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.15 | 0.50038 | 0.075057 | Reduce | 0.15 | 0.50038 | 0.075057 | H3 | 3 | Stable | 0.7 | 82 | 124 | 153 | 121.8333 | 0.3 | 2 | 57 | 61 | 48.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK012 | Project_081_RISK012 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Supplier unable to deliver course without our input | Person_260 | 2017-09-27 01:00 | 2021-09-27 01:00 | 0.5 | 0.50038 | 0.25019 | Reduce | 0.5 | 0.50038 | 0.25019 | H3 | 3 | Stable | 0.5 | 85 | 127 | 157 | 125 | 0.3 | 23 | 41 | 77 | 44 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK019 | Project_081_RISK019 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Misc costs incurred at trials | Person_260 | 2018-05-23 | 2021-09-20 01:00 | 0.2 | 1.3425 | 0.2685 | Avoid | 0.2 | 1.3425 | 0.2685 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK018 | Project_081_RISK018 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Additional trials support requested (+3) | Person_260 | 2018-05-23 | 2021-07-21 | 0.2 | 2.0259 | 0.40519 | Reduce | 0.2 | 2.0259 | 0.40519 | H3 | 3 | Stable | 0.9 | 85 | 133 | 159 | 129.3333 | 0.1 | 24 | 50 | 67 | 48.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK020 | Project_081_RISK020 | Threat | Project Contingency | Open | H3 | 3 | 7. Finance | Travel Cost Increases | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.3 | 1.8307 | 0.5492 | Reduce | 0.3 | 1.8307 | 0.5492 | H3 | 3 | Stable | 0.8 | 108 | 138 | 144 | 134 | 0.3 | 15 | 48 | 75 | 47 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_585 | 2017-10-21 01:00 | 2019-07-21 | 0.333 | 3.3378 | 3.3378 | Accept | 0.333 | 3.3378 | 3.3378 | H2 | 4 | Stable | 0.5 | 118 | 128 | 146 | 129.3333 | 0.5 | 118 | 128 | 146 | 129.3333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_676 | 2016-08-21 01:00 | 2017-08-21 01:00 | 0.5 | 37.5906 | 18.7953 | Reduce | 0.15 | 37.5906 | 5.6386 | H3 | 3 | Stable | 0.5 | 93 | 124 | 156 | 124.1667 | 0.2 | 16 | 59 | 79 | 55.1667 | 0 | 70 | 1 | 2.1
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 7.689 | 2.6911 | Accept | 0.3 | 7.689 | 2.6911 | H2 | 4 | Improving | 0.5 | 81 | 126 | 153 | 123 | 0.5 | 81 | 126 | 153 | 123 | 0 | 25 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2020-09-19 01:00 | 0.2 | 5.4336 | 1.3584 | Accept | 0.2 | 5.4336 | 1.3584 | H3 | 3 | Stable | 0.8 | 90 | 140 | 156 | 134.3333 | 0.8 | 90 | 140 | 156 | 134.3333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2019-07-21 | 0.3 | 5.126 | 2.563 | Accept | 0.2 | 5.126 | 2.563 | H3 | 3 | Stable | 0.5 | 113 | 134 | 144 | 132.1667 | 0.5 | 113 | 134 | 144 | 132.1667 | 0 | 33.3333 | 1 | 1
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | RISK008 | Project_029_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Impact of sub-system Design Changes [product dependency] | Person_332 | 2016-09-20 01:00 | 2019-08-15 | 0.7 | 12.815 | 2.563 | Accept | 0.7 | 12.815 | 2.563 | H2 | 4 | Stable | 0.5 | 91 | 121 | 160 | 122.5 | 0.5 | 91 | 121 | 160 | 122.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.4 | 2.3067 | 0.92268 | Reduce | 0.4 | 2.3067 | 0.92268 | H3 | 3 | Stable | 0.5 | 120 | 124 | 150 | 127.6667 | 0.3 | 11 | 55 | 67 | 49.6667 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-057 | Project_062_Risk-057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Supplier Application Encryption / Protection | Person_479 | 2017-07-21 | 2019-02-21 01:00 | 0.3 | 5.2705 | 1.5811 | Accept | 0.3 | 4.3921 | 0.87842 | H2 | 4 | Stable | 0.7 | 112 | 123 | 147 | 125.1667 | 0.7 | 112 | 123 | 147 | 125.1667 | 16.6667 | 0 | 0 | 10
2018-05-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-O09 | Project_044_Risk-O09 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Lower System housing space | Person_763 | 2018-11-21 01:00 | 2019-11-21 01:00 | 0.3 | 4.2255 | 1.2677 | Exploit | 0.2 | 4.2255 | 0.84511 | H3 | 3 | Stable | [10 empty] | 0 | 33.3333 | 1 | 1
2018-05-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R008 | Project_044_Risk-R008 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Engineering Skills | Person_505 | 2017-10-21 01:00 | 2018-10-22 01:00 | 0.2 | 1.5695 | 0.3139 | Reduce | 0.1 | 1.2073 | 0.12073 | H3 | 3 | Stable | 0.6 | 107 | 134 | 146 | 131.5 | 0.3 | 22 | 51 | 76 | 50.3333 | 23.0769 | 50 | 1 | 15.3461
2018-05-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R018 | Project_044_Risk-R018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | EMC (susceptibility) | Person_763 | 2016-03-23 | 2019-05-23 | 0.5 | 5.795 | 2.8975 | Reduce | 0.1 | 5.795 | 0.5795 | H3 | 3 | Stable | 0.6 | 96 | 139 | 141 | 132.1667 | 0.1 | 2 | 48 | 70 | 44 | 0 | 80 | 1 | 2.4
2018-05-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R001 | Project_044_Risk-R001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | subsystem1 development | Person_358 | 2017-12-22 01:00 | 2019-11-20 01:00 | 0.2 | 20.8621 | 4.1724 | Reduce | 0.15 | 20.8621 | 3.1293 | H2 | 4 | Stable | 0.7 | 117 | 128 | 158 | 131.1667 | 0.4 | 26 | 43 | 60 | 43 | 0 | 25 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R023 | Project_044_Risk-R023 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Integrated performance | Person_358 | 2017-12-15 01:00 | 2020-10-21 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.7 | 107 | 129 | 153 | 129.3333 | 0.4 | 38 | 45 | 72 | 48.3333 |  | 40 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-018 | Project_062_Risk-018 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Prioritisation - new or less experienced staff | Person_459 | 2017-07-21 | 2018-11-20 01:00 | 0.35 | 6.0365 | 0.60365 | Accept | 0.25 | 6.0365 | 0.60365 | H2 | 4 | Improving | 0.8 | 97 | 137 | 153 | 133 | 0.8 | 97 | 137 | 153 | 133 | 0 | 28.5714 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R010 | Project_044_Risk-R010 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Line of sight | Person_763 | 2017-11-20 01:00 | 2018-06-22 | 0.7 | 4.2255 | 2.9579 | -- | 0.2 | 4.2255 | 0.84511 | H3 | 3 | Stable | [10 empty] | 0 | 71.4286 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R026 | Project_044_Risk-R026 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Component position | Person_763 | 2017-11-20 01:00 | 2018-11-20 01:00 | 0.2 | 4.2255 | 0.84511 | Reduce | 0.1 | 4.2255 | 0.42255 | H3 | 3 | Stable | 0.6 | 94 | 131 | 147 | 127.5 | 0.3 | 27 | 53 | 78 | 52.8333 | 0 | 50 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R003 | Project_044_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Mono vs stereo Component | Person_358 | 2018-01-19 01:00 | 2018-10-22 01:00 | 0.4 | 20.8621 | 8.3448 | Reduce | 0.2 | 20.8621 | 4.1724 | H3 | 3 | Stable | 0.5 | 93 | 131 | 154 | 128.5 | 0.4 | 19 | 52 | 69 | 49.3333 | 0 | 50 | 1 | 1.5
2018-05-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R025 | Project_044_Risk-R025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence | Person_763 | 2017-11-20 01:00 | 2019-05-22 | 0.3 | 3.0182 | 0.90547 | Reduce | 0.1 | 1.2073 | 0.12073 | H3 | 3 | Stable | 0.5 | 114 | 128 | 149 | 129.1667 | 0.4 | 6 | 43 | 71 | 41.5 | 60 | 66.6667 | 1 | 38
2018-05-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R002 | Project_044_Risk-R002 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Parts changing post ordering | Person_310 | 2018-01-20 01:00 | 2019-05-22 | 0.9 | 0 | 0 | -- | 0.9 | 0 | 0 | H1 | 5 | Stable | [11 empty] | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-009 | Project_062_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Unresolved technical debt (excluding ILS) | Person_253 | 2017-07-21 | 2019-03-23 | 0.5 | 4.8292 | 0.96584 | Accept | 0.3 | 4.8292 | 0.96584 | H2 | 4 | Stable | 0.8 | 86 | 132 | 155 | 128.1667 | 0.8 | 86 | 132 | 155 | 128.1667 | 0 | 40 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R092 | Project_044_Risk-R092 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Downstream Integration changes | Person_358 | 2018-11-21 01:00 | 2019-11-21 01:00 | 0.3 | 0 | 0 | -- | 0.2 | 4.2255 | 0.84511 | H3 | 3 | Stable | [10 empty] | -inf | 33.3333 | 1 | -inf
2018-05-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R091 | Project_044_Risk-R091 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Receive System Performance | Person_763 | 2017-11-20 01:00 | 2018-11-21 01:00 | 0.5 | 4.2255 | 2.1128 | Reduce | 0.2 | 4.2255 | 0.84511 | H3 | 3 | Stable | 0.6 | 88 | 137 | 159 | 132.5 | 0.4 | 3 | 52 | 72 | 47.1667 | 0 | 60 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R090 | Project_044_Risk-R090 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Gain and noise measurements | Person_763 | 2017-11-20 01:00 | 2019-05-23 | 0.5 | 4.2255 | 2.1128 | -- | 0.2 | 4.2255 | 0.84511 | H3 | 3 | Stable | [10 empty] | 0 | 60 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R005 | Project_044_Risk-R005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | CE Marking | Person_763 | 2018-01-20 01:00 | 2018-11-05 01:00 | 0.3 | 2.1128 | 0.63383 | Reduce | 0.1 | 1.2073 | 0.12073 | H3 | 3 | Stable | 0.8 | 110 | 138 | 143 | 134.1667 | 0.1 | 27 | 44 | 63 | 44.3333 | 42.8571 | 66.6667 | 1 | 27.7143
2018-05-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-015 | Project_062_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Re-work | Person_253 | 2018-03-01 01:00 | 2019-05-22 | 0.5 | 0.82922 | 0.7463 | Accept | 0.5 | 0.82922 | 0.7463 | H2 | 4 | Stable | 0.9 | 118 | 140 | 160 | 139.6667 | 0.9 | 118 | 140 | 160 | 139.6667 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK075 | Project_076_RISK075 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Delay in SW completion completion - Safety issues | Person_152 | 2018-07-05 | 2019-05-16 | 0.5 | 1.6723 | 0.83613 | Reduce | 0.1 | 1.6723 | 0.16723 | H3 | 3 | Stable | 0.8 | 101 | 137 | 143 | 132 | 0.2 | 21 | 59 | 61 | 53 | 0 | 80 | 1 | 2.4
2018-05-23 | ORG_001 | BA_002 | Portfolio_008 | Project_082 | RISK007 | Project_082_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Task 30 - Pylon Procurement | Person_619 | 2017-04-13 | 2018-07-21 | 1 | 0.78457 | 0.39228 | Accept | 1 | 0.78457 | 0.39228 | H2 | 4 | Stable | 0.9 | 103 | 130 | 159 | 130.3333 | 0.9 | 103 | 130 | 159 | 130.3333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.35 | 1.0475 | 0.52377 | Accept | 0.35 | 1.0485 | 0.52426 | H3 | 3 | Stable | 0.8 | 102 | 136 | 143 | 131.5 | 0.8 | 102 | 136 | 143 | 131.5 | -0.092391 | 0 | 0 | -0.055435
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-22 | 2019-08-21 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-22 | 2019-08-21 | 0.5 | 3.7714 | 1.8857 | Avoid | 0.5 | 3.7714 | 1.8857 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-113 | Project_043_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | No Gen 1 products available, transition cost to Gen 2 | Person_769 | 2017-04-19 | 2020-12-21 01:00 | 0.3 | 1.4971 | 0.44912 | Reduce | 0.3 | 1.4971 | 0.44912 | H2 | 4 | Stable | 0.6 | 80 | 134 | 150 | 127.6667 | 0.3 | 36 | 50 | 73 | 51.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-121 | Project_043_Risk-121 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | More Tech Pubs Update than estimated | Person_769 | 2019-01-21 01:00 | 2020-10-20 01:00 | 0.45 | 1.7366 | 0.78146 | Reduce | 0.45 | 1.7366 | 0.78146 | H1 | 5 | Stable | 0.6 | 113 | 139 | 151 | 136.6667 | 0.4 | 22 | 53 | 75 | 51.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-084 | Project_043_Risk-084 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | complex repair ( over and above the forecast average) | Person_693 | 2017-12-21 01:00 | 2020-12-21 01:00 | 0.2 | 0.71859 | 0.14372 | Reduce | 0.2 | 0.71859 | 0.14372 | H2 | 4 | Stable | 0.7 | 120 | 135 | 152 | 135.3333 | 0.3 | 24 | 44 | 63 | 43.8333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-128 | Project_043_Risk-128 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Reliance of Customer Avaliability | Person_135 | 2017-04-19 | 2018-08-21 | 0.5 | 1.7665 | 0.88326 | Reduce | 0.1 | 1.7665 | 0.17665 | H2 | 4 | Stable | 0.9 | 87 | 138 | 146 | 130.8333 | 0.4 | 27 | 52 | 61 | 49.3333 | 0 | 80 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-089 | Project_043_Risk-089 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares pool is limited | Person_307 | 2018-12-22 01:00 | 2020-12-21 01:00 | 0.25 | 1.5969 | 0.39921 | Reduce | 0.25 | 1.2775 | 0.31937 | H2 | 4 | Stable | 0.5 | 104 | 138 | 142 | 133 | 0.2 | 35 | 54 | 61 | 52 | 20 | 0 | 0 | 12
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-039 | Project_043_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System fails to achieve required performance | Person_051 | 2017-04-19 | 2018-11-20 01:00 | 0.3 | 4.7906 | 1.4372 | Reduce | 0.3 | 4.7906 | 1.4372 | H2 | 4 | Stable | 0.9 | 85 | 127 | 145 | 123 | 0.4 | 11 | 55 | 79 | 51.6667 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-115 | Project_011_Risk-115 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | SMEs are unavailable to support project activites | Person_431 | 2016-07-21 | 2018-08-21 | 0.2 | 0 | 0 | Avoid | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 50 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-058 | Project_011_Risk-058 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme delays | Person_147 | 2013-11-20 01:00 | 2018-11-20 01:00 | 0.25 | 1.5013 | 0.37532 | Reduce | 0.4 | 1.5013 | 0.60051 | H1 | 5 | Stable | 0.5 | 86 | 137 | 154 | 131.3333 | 0.4 | 31 | 47 | 63 | 47 | 0 | -60 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-131 | Project_011_Risk-131 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Support team have not covered all obligations in support contract | Person_147 | 2016-05-24 | 2018-08-17 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-137 | Project_011_Risk-137 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Subsystem will not match Fidelity of Customer - does not accept | Person_147 | 2018-02-16 01:00 | 2018-09-20 01:00 | 0.4 | 0.11876 | 0.047505 | Avoid | 0.2 | 0.11876 | 0.023752 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.25 | 0.34776 | 0.034776 | Accept | 0.25 | 0.34776 | 0.034776 | H3 | 3 | Stable | 0.9 | 99 | 134 | 151 | 131 | 0.9 | 99 | 134 | 151 | 131 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2018-04-22 | 2018-09-20 01:00 | 0.2 | 0.62279 | 0.12456 | Avoid | 0.2 | 0.62279 | 0.12456 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-09-20 01:00 | 0.2 | 1.8854 | 0.37708 | Reduce | 0.2 | 1.8854 | 0.37708 | H2 | 4 | Stable | 0.9 | 104 | 125 | 149 | 125.5 | 0.3 | 39 | 52 | 67 | 52.3333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2018-06-23 | 2018-10-21 01:00 | 0.4 | 1.4138 | 0.56551 | Reduce | 0.5 | 1.4138 | 0.70689 | H1 | 5 | Stable | 0.5 | 84 | 136 | 152 | 130 | 0.2 | 29 | 47 | 76 | 48.8333 | 0 | -25 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-09-20 01:00 | 0.4 | 0.19206 | 0.076826 | -- | 0.4 | 0.19206 | 0.076826 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-08-22 01:00 | 2018-11-20 01:00 | 0.4 | 0.58017 | 0.23207 | Avoid | 0.4 | 0.58017 | 0.23207 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_676 | 2016-10-21 01:00 | 2019-08-20 | 0.5 | 0.49834 | 0.12459 | Accept | 0.5 | 0.49834 | 0.12459 | H2 | 4 | Stable | 0.5 | 113 | 129 | 149 | 129.6667 | 0.5 | 113 | 129 | 149 | 129.6667 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-11-20 01:00 | 0.3 | 0.32389 | 0.097168 | Reduce | 0.3 | 0.32389 | 0.097168 | H2 | 4 | Stable | 0.7 | 117 | 138 | 143 | 135.3333 | 0.1 | 6 | 53 | 72 | 48.3333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures during SAT | Person_182 | 2018-06-23 | 2018-10-21 01:00 | 0.2 | 0.19206 | 0.038413 | -- | 0.2 | 0.19206 | 0.038413 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_431 | 2017-05-24 | 2018-09-19 01:00 | 0.3 | 0.11933 | 0.035799 | -- | 0.3 | 0.022161 | 0.0066484 | H3 | 3 | Stable | [10 empty] | 81.4286 | 0 | 0 | 48.8571
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-117 | Project_011_Risk-117 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Avaliability for testing/reviews | Person_147 | 2018-04-06 | 2018-09-20 01:00 | 0.35 | 0 | 0 | Avoid | 0.35 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-129 | Project_011_Risk-129 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Signature of Work Authorisation documents | Person_422 | 2017-05-24 | 2018-08-05 | 0.4 | 0.12643 | 0.050573 | -- | 0.4 | 0.12643 | 0.050573 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-130 | Project_011_Risk-130 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Customer does not accept Voice Pronounciation | Person_187 | 2017-05-24 | 2018-07-20 | 0.25 | 0.090918 | 0.022729 | Avoid | 0.1 | 0.090918 | 0.0090918 | H3 | 3 | Stable | [10 empty] | 0 | 60 | 1 | 1.8
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.2 | 2.033 | 1.0165 | Accept | 0.2 | 1.4231 | 0.71156 | H3 | 3 | Stable | 0.7 | 115 | 121 | 152 | 125.1667 | 0.7 | 115 | 121 | 152 | 125.1667 | 30 | 0 | 0 | 18
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Volume of production tools and Jigs | Person_279 | 2016-11-22 22:00 | 2021-11-22 22:00 | 0.35 | 6.4382 | 2.2534 | Reduce | 0.15 | 6.4382 | 0.96573 | H2 | 4 | Stable | 0.8 | 83 | 125 | 151 | 122.3333 | 0.4 | 12 | 50 | 77 | 48.1667 | 0 | 57.1429 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software issue input | Person_279 | 2016-11-22 22:00 | 2023-02-19 22:00 | 0.4 | 49.4398 | 19.7759 | Reduce | 0.2 | 49.4398 | 9.888 | H2 | 4 | Stable | 0.7 | 85 | 129 | 144 | 124.1667 | 0.4 | 37 | 41 | 70 | 45.1667 | 0 | 50 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK014 | Project_083_RISK014 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System SW hosting Enrionment | Person_712 | 2018-02-20 01:00 | 2019-05-22 | 0.3 | 4.8313 | 1.4494 | Reduce | 0.25 | 4.8313 | 1.2078 | H2 | 4 | Stable | 0.5 | 93 | 135 | 150 | 130.5 | 0.4 | 31 | 44 | 68 | 45.8333 | 0 | 16.6667 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK003 | Project_083_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supply Chain late delivery against Baseline Plan | Person_391 | 2018-02-20 01:00 | 2019-05-16 | 0.6 | 2.3988 | 1.4393 | Reduce | 0.4 | 2.3988 | 0.95952 | H2 | 4 | Stable | 0.8 | 115 | 130 | 154 | 131.5 | 0.1 | 31 | 44 | 76 | 47.1667 | 0 | 33.3333 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK017 | Project_083_RISK017 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Modules Obsolescence Resolution - Domestic Programmes | Person_712 | 2018-03-17 01:00 | 2019-01-20 01:00 | 0.15 | 10.3732 | 1.556 | Reduce | 0.15 | 10.3732 | 1.556 | H3 | 3 | Stable | 0.5 | 102 | 132 | 154 | 130.6667 | 0.4 | 3 | 46 | 60 | 41.1667 | 0 | 0 | 1 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK016 | Project_083_RISK016 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Dependencies on product | Person_465 | 2018-03-17 01:00 | 2019-01-20 01:00 | 0.3 | 12.3182 | 3.6955 | Avoid | 0.15 | 12.3182 | 1.8477 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK022 | Project_083_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Availability of Engineering Resource | Person_712 | 2018-03-17 01:00 | 2019-01-20 01:00 | 0.4 | 0 | 0 | Reduce | 0.2 | 5.4459 | 1.0892 | H3 | 3 | Stable | 0.8 | 82 | 133 | 160 | 129 | 0.2 | 16 | 52 | 63 | 47.8333 | -inf | 50 | 1 | -inf
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK002 | Project_083_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supply Chain Cost Increase - post Engineering design until completion of Procurement Phase | Person_391 | 2018-02-20 01:00 | 2019-01-20 01:00 | 0.65 | 5.8349 | 3.7927 | Reduce | 0.25 | 4.8385 | 1.2096 | H2 | 4 | Stable | 0.5 | 88 | 127 | 153 | 124.8333 | 0.3 | 31 | 48 | 70 | 48.8333 | 17.0777 | 61.5385 | 0 | 10.2466
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK024 | Project_083_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability of Data to support Customer Deliverable updates aligned to Customer Deliverable delivery dates | Person_712 | 2018-03-17 01:00 | 2019-01-20 01:00 | 0.4 | 9.2062 | 3.6825 | Reduce | 0.35 | 7.754 | 2.7139 | H2 | 4 | Stable | 0.9 | 120 | 129 | 148 | 130.6667 | 0.4 | 26 | 41 | 70 | 43.3333 | 15.7746 | 12.5 | 0 | 9.4648
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK023 | Project_083_RISK023 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Customer Deliverables - Read Across from product | Person_712 | 2018-03-17 01:00 | 2019-01-20 01:00 | 0.6 | 4.279 | 2.5674 | Reduce | 0.4 | 2.8267 | 1.1307 | H3 | 3 | Stable | 0.7 | 114 | 131 | 144 | 130.3333 | 0.4 | 35 | 53 | 69 | 52.6667 | 33.9395 | 33.3333 | 0 | 20.3637
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | OP001 | Project_083_OP001 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply chain | Cross Project Procurement | Person_391 | 2018-02-20 01:00 | 2019-01-20 01:00 | 0.2 | 4.2141 | 0.84283 | Exploit | 0.7 | 4.2141 | 2.9499 | H3 | 3 | Stable | [10 empty] | 0 | -250 | 1 | -7.5
2018-05-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R022 | Project_044_Risk-R022 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Shock Requirement | Person_763 | 2018-11-20 01:00 | 2019-05-23 | 0.1 | 20.4694 | 10.2347 | Accept | 0.1 | 20.4694 | 10.2347 | H3 | 3 | Stable | 0.6 | 102 | 124 | 143 | 123.5 | 0.6 | 102 | 124 | 143 | 123.5 | 0 | 0 | 1 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Regulatory standards changes misunderstood | Person_693 | 2018-03-23 | 2018-07-21 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.7 | 100 | 138 | 141 | 132.1667 | 0.4 | 13 | 45 | 70 | 43.8333 | 0 | 50 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R024 | Project_044_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Receiver System Performance | Person_763 | 2017-11-20 01:00 | 2019-11-21 01:00 | 0.2 | 1.7748 | 0.4437 | Accept | 0.2 | 1.7748 | 0.4437 | H3 | 3 | Stable | 0.9 | 112 | 139 | 149 | 136.1667 | 0.9 | 112 | 139 | 149 | 136.1667 | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier Selection Process | Person_379 | 2017-10-19 01:00 | 2019-04-23 | 0.4 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 83 | 131 | 145 | 125.3333 | 0.2 | 7 | 45 | 66 | 42.1667 |  | 25 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Colour Representation in Video Image Distortion | Person_305 | 2017-09-22 01:00 | 2019-11-28 01:00 | 0.5 | 5.5323 | 2.7662 | Reduce | 0.1 | 5.5323 | 0.55323 | H3 | 3 | Stable | 0.7 | 112 | 136 | 155 | 135.1667 | 0.2 | 25 | 58 | 72 | 54.8333 | 0 | 80 | 1 | 2.4
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-21 01:00 | 2018-07-20 | 0.5 | 28.0275 | 14.0137 | Reduce | 0.1 | 28.0275 | 2.8027 | H3 | 3 | Stable | 0.5 | 111 | 125 | 153 | 127.3333 | 0.2 | 6 | 45 | 71 | 42.8333 | 0 | 80 | 1 | 2.4
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Labour/Material Risk | Person_662 | 2015-05-24 | 2019-05-23 | 0.5 | 3.2479 | 0.64958 | Accept | 0.5 | 3.2479 | 0.64958 | H2 | 4 | Stable | 0.9 | 110 | 127 | 152 | 128.3333 | 0.9 | 110 | 127 | 152 | 128.3333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-21 01:00 | 0.8 | 35.2369 | 28.1895 | Reduce | 0.3 | 18.4979 | 5.5494 | H2 | 4 | Stable | 0.5 | 117 | 125 | 146 | 127.1667 | 0.1 | 10 | 54 | 69 | 49.1667 | 47.5042 | 62.5 | 0 | 28.5025
2018-05-23 | ORG_001 | BA_002 | Portfolio_009 | Project_045 | RISK001 | Project_045_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour/T&S Overspend | Person_662 | 2017-01-21 | 2020-05-22 | 0.5 | 3.5496 | 1.0649 | Accept | 0.5 | 3.5496 | 1.0649 | H2 | 4 | Stable | 0.6 | 84 | 126 | 160 | 124.6667 | 0.6 | 84 | 126 | 160 | 124.6667 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 4 | 9. Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-21 01:00 | 0.7 | 20.6835 | 14.4785 | Reduce | 0.3 | 20.6835 | 6.2051 | H2 | 4 | Stable | 0.5 | 101 | 124 | 157 | 125.6667 | 0.2 | 35 | 50 | 72 | 51.1667 | 0 | 57.1429 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Unreliability of Hardware | Person_431 | 2016-06-23 | 2018-08-21 | 0.1 | 8.0289 | 0.80289 | Accept | 0.1 | 2.5354 | 0.25354 | H3 | 3 | Stable | 0.8 | 88 | 134 | 145 | 128.1667 | 0.8 | 88 | 134 | 145 | 128.1667 | 68.421 | 0 | 0 | 41.0526
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 4 | 8. System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 0.6 | 5.2585 | 3.1551 | Reduce | 0.15 | 5.2585 | 0.78877 | H2 | 4 | Stable | 0.6 | 103 | 121 | 149 | 122.6667 | 0.2 | 23 | 56 | 67 | 52.3333 | 0 | 75 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_147 | 2016-04-21 | 2018-08-21 | 0.25 | 2.1974 | 0.87895 | Accept | 0.25 | 2.1974 | 0.87895 | H3 | 3 | Stable | 0.5 | 94 | 122 | 159 | 123.5 | 0.5 | 94 | 122 | 159 | 123.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | RISK015 | Project_028_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Engineering Change | Person_496 | 2018-07-22 | 2018-09-20 01:00 | 0.5 | 7.7077 | 2.6977 | Accept | 0.5 | 7.7077 | 2.6977 | H2 | 4 | Stable | 0.8 | 87 | 136 | 160 | 131.8333 | 0.8 | 87 | 136 | 160 | 131.8333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK030 | Project_083_RISK030 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Additional (unknown) support as result of sub-system learning within supply and customer | Person_644 | 2017-11-20 01:00 | 2020-11-19 01:00 | 0.4 | 1.0497 | 0.3149 | Accept | 0.4 | 1.0497 | 0.3149 | H3 | 3 | Stable | 0.7 | 98 | 124 | 159 | 125.5 | 0.7 | 98 | 124 | 159 | 125.5 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-07-21 | 0.3 | 2.723 | 0.81691 | Reduce | 0.1 | 2.723 | 0.2723 | H3 | 3 | Improving | 0.9 | 80 | 133 | 142 | 125.6667 | 0.2 | 15 | 59 | 61 | 52 | 0 | 66.6667 | 1 | 2
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.8 | 97 | 124 | 142 | 122.5 | 0.1 | 29 | 49 | 78 | 50.5 | 60.3671 | 58.3333 | 0 | 36.2202
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 0.3 | 4.8444 | 1.4533 | Reduce | 0.2 | 4.8444 | 0.96888 | H3 | 3 | Stable | 0.5 | 120 | 122 | 145 | 125.5 | 0.1 | 29 | 58 | 65 | 54.3333 | 0 | 33.3333 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System Performance | Person_305 | 2016-09-08 01:00 | 2020-09-21 01:00 | 0.3 | 5.8725 | 1.7618 | Reduce | 0.1 | 5.8725 | 0.58725 | H2 | 4 | Stable | 0.5 | 112 | 132 | 151 | 131.8333 | 0.4 | 25 | 58 | 65 | 53.6667 | 0 | 66.6667 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_572 | 2020-05-23 | 2023-10-26 01:00 | 0.2 | 7.4599 | 1.492 | Reduce | 0.05 | 7.4599 | 0.37299 | H2 | 4 | Stable | 0.7 | 110 | 136 | 159 | 135.5 | 0.2 | 8 | 41 | 62 | 39 | 0 | 75 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-29 01:00 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.7 | 90 | 127 | 158 | 126 | 0.2 | 25 | 41 | 60 | 41.5 | 60.3671 | 58.3333 | 0 | 36.2202
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-20 01:00 | 0.4 | 2.8643 | 1.1457 | Reduce | 0.1 | 2.8643 | 0.28643 | H3 | 3 | Stable | 0.5 | 119 | 139 | 157 | 138.6667 | 0.4 | 23 | 55 | 74 | 52.8333 | 0.0015933 | 75 | 1 | 2.251
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power Supply - Motor Controller Interface | Person_179 | 2016-05-23 | 2018-09-19 01:00 | 0.5 | 25.3543 | 12.6771 | Reduce | 0.2 | 25.3543 | 5.0709 | H3 | 3 | Stable | 0.6 | 111 | 127 | 141 | 126.6667 | 0.2 | 29 | 43 | 76 | 46.1667 | 0 | 60 | 1 | 1.8
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 0.1 | 12.7232 | 1.2723 | Reduce | 0.1 | 12.7232 | 1.2723 | H3 | 3 | Stable | 0.9 | 104 | 126 | 153 | 126.8333 | 0.2 | 9 | 41 | 68 | 40.1667 | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | EMC non compliance | Person_047 | 2023-05-24 | 2023-12-01 01:00 | 0.7 | 3.935 | 2.7545 | Reduce | 0.5 | 3.935 | 1.9675 | H2 | 4 | Stable | 0.9 | 93 | 121 | 155 | 122 | 0.3 | 22 | 51 | 73 | 49.8333 | 0 | 28.5714 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SubSystem System Design | Person_038 | 2017-10-01 01:00 | 2019-11-20 01:00 | 0.2 | 1.5213 | 0.30425 | Reduce | 0.1 | 1.5213 | 0.15213 | H3 | 3 | Stable | 0.9 | 119 | 134 | 153 | 134.6667 | 0.3 | 22 | 57 | 61 | 51.8333 | 0 | 50 | 1 | 1.5
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-21 01:00 | 2023-12-22 01:00 | 0.4 | 30.1969 | 12.0788 | Reduce | 0.25 | 30.1969 | 7.5492 | H2 | 4 | Stable | 0.7 | 99 | 140 | 144 | 133.8333 | 0.3 | 7 | 59 | 79 | 53.6667 | 0 | 37.5 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | In-house development of sub-system estimate is low | Person_418 | 2016-03-23 | 2018-06-06 | 0.5 | 6.5118 | 3.2559 | Reduce | 0.2 | 1.506 | 0.30121 | H3 | 3 | Stable | 0.6 | 110 | 125 | 146 | 126 | 0.3 | 10 | 47 | 60 | 43 | 76.8722 | 60 | 0 | 46.1233
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-10-20 01:00 | 0.4 | 1.0142 | 0.40567 | Reduce | 0.1 | 1.0142 | 0.10142 | H3 | 3 | Stable | 0.7 | 101 | 126 | 148 | 125.5 | 0.1 | 5 | 47 | 76 | 44.8333 | 0 | 75 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | 9. Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 0.8 | 19.1678 | 15.3343 | Reduce | 0.2 | 2.8752 | 0.57503 | H3 | 3 | Stable | 0.6 | 102 | 134 | 154 | 132 | 0.3 | 1 | 56 | 64 | 48.1667 | 85 | 75 | 0 | 51
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 0.25 | 0.63626 | 0.15906 | Reduce | 0.05 | 0.63626 | 0.031813 | H3 | 3 | Stable | 0.9 | 95 | 126 | 159 | 126.3333 | 0.4 | 34 | 52 | 71 | 52.1667 | 0 | 80 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Component Shock test failure | Person_020 | 2016-09-08 01:00 | 2019-11-15 01:00 | 0.4 | 0.8467 | 0.33868 | Reduce | 0.2 | 0.8467 | 0.16934 | H3 | 3 | Stable | 0.5 | 104 | 124 | 145 | 124.1667 | 0.3 | 26 | 58 | 73 | 55.1667 | 0 | 50 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-06 01:00 | 2019-09-13 01:00 | 0.8 | 8.0322 | 6.4258 | Reduce | 0.5 | 4.006 | 2.003 | H2 | 4 | Stable | 0.9 | 114 | 122 | 154 | 126 | 0.2 | 2 | 54 | 61 | 46.5 | 50.1263 | 37.5 | 0 | 30.0758
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-04-22 | 0.8 | 18.0459 | 14.4367 | Reduce | 0.2 | 3.0076 | 0.60153 | H3 | 3 | Stable | 0.5 | 85 | 135 | 160 | 130.8333 | 0.1 | 20 | 55 | 66 | 51 | 83.3335 | 75 | 1 | 52.2501
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 0.4 | 5.1004 | 2.0402 | Reduce | 0.2 | 2.5506 | 0.51013 | H3 | 3 | Stable | 0.8 | 114 | 140 | 158 | 138.6667 | 0.4 | 31 | 45 | 72 | 47.1667 | 49.9917 | 50 | 0 | 29.995
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK024 | Project_048_RISK024 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Procurement/Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 0.8 | 0 | 0 | -- | 0.8 | 0 | 0 | H1 | 5 | Worsening | [11 empty] | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK017 | Project_048_RISK017 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Increased build rate | Person_683 | 2017-11-12 01:00 | 2019-08-21 01:00 | 0.5 | 7.7433 | 3.8716 | -- | 0.5 | 7.7433 | 3.8716 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK016 | Project_048_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.2 | 0.22605 | 0.045211 | -- | 0.2 | 0.22605 | 0.045211 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK018 | Project_048_RISK018 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Line Closure | Person_683 | 2019-08-21 01:00 | 2019-11-20 01:00 | 0.5 | 0.68298 | 0.34149 | -- | 0.5 | 1.5483 | 0.77415 | H2 | 4 | Improving | [10 empty] | -126.7001 | 0 | 0 | -76.0201
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK004 | Project_048_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 1.0253 | 0.20506 | Reduce | 0.15 | 1.0253 | 0.1538 | H3 | 3 | Stable | 0.5 | 119 | 125 | 147 | 127.6667 | 0.3 | 2 | 43 | 66 | 40 | 0 | 25 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK014 | Project_048_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 0.1 | 2.9934 | 0.29934 | Avoid | 0.05 | 2.5117 | 0.12558 | H3 | 3 | Stable | [10 empty] | 16.092 | 50 | 0 | 9.6552
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK005 | Project_048_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 0.43506 | 0.26104 | Avoid | 0.5 | 0.43506 | 0.21753 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK002 | Project_048_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2020-05-22 | 0.15 | 3.0966 | 0.46449 | Avoid | 0.15 | 3.0966 | 0.46449 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK012 | Project_048_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Customer require additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.1 | 2.1676 | 0.21676 | Avoid | 0.1 | 2.1676 | 0.21676 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK022 | Project_048_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Equipment | Person_104 | 2018-01-14 01:00 | 2019-08-20 | 0.15 | 0.84641 | 0.12696 | -- | 0.15 | 0.84641 | 0.12696 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_048 | RISK026 | Project_048_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Clause on Joint Proposal | Person_261 | 2018-05-04 | 2019-05-23 | 0.5 | 3.5439 | 1.772 | -- | 0.5 | 3.5439 | 1.772 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.7 | 110 | 135 | 150 | 133.3333 | 0.1 | 39 | 47 | 63 | 48.3333 | 25.8065 | 20 | 0 | 15.4839
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2018-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | R054 | Project_066_R054 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | System Cybersecurity shortfalls | Person_549 | 2017-01-21 01:00 | 2024-05-23 | 0.8 | 15.7936 | 12.6349 | Reduce | 0.5 | 15.7936 | 7.8968 | H1 | 5 | Stable | 0.9 | 93 | 127 | 155 | 126 | 0.1 | 9 | 55 | 79 | 51.3333 | 0 | 37.5 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 0.3 | 1.0661 | 0.21322 | Accept | 0.3 | 0 | 0 | H3 | 3 | Stable | 0.9 | 100 | 131 | 148 | 128.6667 | 0.9 | 100 | 131 | 148 | 128.6667 | 100 | 0 | 0 | 60
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-010 | Project_052_Risk-010 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Potential update of software / hardware required during the 3 year support period (RESOURCE) | Person_376 | 2017-08-19 | 2018-02-19 | 0.25 | 3.1214 | 0.78035 | Transfer | 0.25 | 3.1214 | 0.78035 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK024 | Project_063_RISK024 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Procurement/Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 0.8 | 0 | 0 | -- | 0.8 | 0 | 0 | H1 | 5 | Worsening | [11 empty] | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK022 | Project_063_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Equipment | Person_104 | 2018-01-14 01:00 | 2019-08-20 | 0.15 | 2.3618 | 0.35427 | -- | 0.15 | 2.3618 | 0.35427 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK004 | Project_063_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 2.861 | 0.57221 | Reduce | 0.15 | 2.861 | 0.42915 | H3 | 3 | Stable | 0.9 | 119 | 138 | 143 | 135.6667 | 0.4 | 18 | 54 | 76 | 51.6667 | 0 | 25 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK014 | Project_063_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 0.1 | 8.3527 | 0.83527 | Avoid | 0.05 | 7.0086 | 0.35043 | H3 | 3 | Stable | [10 empty] | 16.092 | 50 | 0 | 9.6552
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK017 | Project_063_RISK017 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Increased build rate | Person_683 | 2017-11-12 01:00 | 2019-08-21 01:00 | 0.5 | 21.6065 | 10.8033 | -- | 0.5 | 21.6065 | 10.8033 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK005 | Project_063_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 1.214 | 0.72839 | -- | 0.5 | 1.214 | 0.60699 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK016 | Project_063_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.2 | 0.63077 | 0.12615 | -- | 0.2 | 0.63077 | 0.12615 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK002 | Project_063_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2020-05-22 | 0.15 | 8.6407 | 1.2961 | Avoid | 0.15 | 8.6407 | 1.2961 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK012 | Project_063_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Customer require additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 0.1 | 6.0485 | 0.60485 | Avoid | 0.1 | 6.0485 | 0.60485 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK018 | Project_063_RISK018 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Line Closure | Person_683 | 2019-08-21 01:00 | 2019-11-20 01:00 | 0.5 | 1.9058 | 0.95288 | -- | 0.5 | 4.3203 | 2.1602 | H2 | 4 | Improving | [10 empty] | -126.7001 | 0 | 0 | -76.0201
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_063 | RISK026 | Project_063_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Clause on Joint Proposal | Person_261 | 2018-05-04 | 2019-05-23 | 0.5 | 9.8888 | 4.9444 | -- | 0.5 | 9.8888 | 4.9444 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | R181 | Project_066_R181 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | USB Hub start up issues | Person_247 | 2017-01-21 01:00 | 2024-05-23 | 1 | 3.186 | 1.593 | Accept | 1 | 0 | 0 | H1 | 5 | Stable | 0.8 | 116 | 133 | 143 | 131.8333 | 0.8 | 116 | 133 | 143 | 131.8333 | 100 | 0 | 0 | 60
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-013 | Project_052_Risk-013 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional material and effort required to support the delta equipment | Person_376 | 2017-08-19 | 2018-03-22 | 0.3 | 1.2744 | 0.63719 | Accept | 0.3 | 0 | 0 | H3 | 3 | Stable | 0.9 | 103 | 123 | 146 | 123.5 | 0.9 | 103 | 123 | 146 | 123.5 | 100 | 0 | 0 | 60
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-004 | Project_052_Risk-004 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | IOC Risk for Phase 1b | Person_488 | 2017-08-19 | 2018-03-22 | 0.1 | 2.5488 | 0.89207 | Accept | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 81 | 131 | 152 | 126.1667 | 0.7 | 81 | 131 | 152 | 126.1667 | 100 | 0 | 0 | 60
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-001 | Project_052_Risk-001 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Greater modification than expected for system uplift | Person_376 | 2017-08-19 | 2018-03-22 | 0.1 | 0.82835 | 0.49701 | Accept | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 116 | 127 | 152 | 129.3333 | 0.8 | 116 | 127 | 152 | 129.3333 | 100 | 0 | 0 | 60
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-20 22:00 | 2023-12-21 22:00 | 0.4 | 30.1969 | 12.0788 | Reduce | 0.25 | 30.1969 | 7.5492 | H2 | 4 | Stable | 0.8 | 110 | 123 | 141 | 123.8333 | 0.3 | 5 | 55 | 70 | 49.1667 | 0 | 37.5 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Component Shock test failure | Person_661 | 2016-09-07 22:00 | 2019-11-14 22:00 | 0.4 | 0.8467 | 0.33868 | Reduce | 0.2 | 0.8467 | 0.16934 | H3 | 3 | Stable | 0.5 | 103 | 121 | 154 | 123.5 | 0.1 | 34 | 58 | 60 | 54.3333 | 0 | 50 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-01-11 22:00 | 0.8 | 18.0459 | 14.4367 | Reduce | 0.2 | 3.0076 | 0.60153 | H3 | 3 | Stable | 0.7 | 105 | 138 | 142 | 133.1667 | 0.3 | 8 | 42 | 69 | 40.8333 | 83.3335 | 75 | 1 | 52.2501
2018-05-23 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-009 | Project_052_Risk-009 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | System acceptance not costed in line with Customer expectations | Person_651 | 2017-08-19 | 2018-03-22 | 0.1 | 18.4072 | 5.5222 | Accept | 0.1 | 18.4072 | 5.5222 | H3 | 3 | Stable | 0.5 | 112 | 138 | 152 | 136 | 0.5 | 112 | 138 | 152 | 136 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 0.4 | 5.1004 | 2.0402 | Reduce | 0.2 | 2.5506 | 0.51013 | H3 | 3 | Stable | 0.6 | 116 | 138 | 147 | 135.8333 | 0.1 | 24 | 54 | 76 | 52.6667 | 49.9917 | 50 | 0 | 29.995
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-20 22:00 | 2018-04-22 | 0.5 | 28.0275 | 14.0137 | Reduce | 0.1 | 28.0275 | 2.8027 | H3 | 3 | Stable | 0.6 | 85 | 137 | 150 | 130.5 | 0.4 | 36 | 58 | 76 | 57.3333 | 0 | 80 | 1 | 2.4
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | EMC non compliance | Person_047 | 2016-06-23 | 2019-12-26 22:00 | 0.7 | 3.935 | 2.7545 | Reduce | 0.5 | 3.935 | 1.9675 | H2 | 4 | Stable | 0.5 | 84 | 127 | 150 | 123.6667 | 0.1 | 11 | 46 | 71 | 44.3333 | 0 | 28.5714 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SubSystem System Design | Person_038 | 2017-09-30 22:00 | 2019-11-19 22:00 | 0.2 | 1.5213 | 0.30425 | Reduce | 0.1 | 1.5213 | 0.15213 | H3 | 3 | Stable | 0.6 | 107 | 134 | 158 | 133.5 | 0.4 | 22 | 59 | 79 | 56.1667 | 0 | 50 | 1 | 1.5
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 0.3 | 25.1514 | 12.5757 | Accept | 0.3 | 25.1514 | 12.5757 | H3 | 3 | Stable | 0.5 | 90 | 122 | 141 | 119.8333 | 0.5 | 90 | 122 | 141 | 119.8333 | 0 | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-06-06 | 0.4 | 1.0142 | 0.40567 | Reduce | 0.1 | 1.0142 | 0.10142 | H3 | 3 | Stable | 0.6 | 84 | 130 | 158 | 127 | 0.4 | 26 | 56 | 69 | 53.1667 | 0 | 75 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | 9. Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 0.8 | 19.1678 | 15.3343 | Reduce | 0.2 | 2.8752 | 0.57503 | H3 | 3 | Stable | 0.8 | 97 | 133 | 146 | 129.1667 | 0.3 | 32 | 51 | 71 | 51.1667 | 85 | 75 | 0 | 51
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-05 22:00 | 2019-09-12 22:00 | 0.8 | 8.0322 | 6.4258 | Reduce | 0.5 | 4.006 | 2.003 | H2 | 4 | Stable | 0.7 | 114 | 138 | 155 | 136.8333 | 0.4 | 8 | 44 | 68 | 42 | 50.1263 | 37.5 | 0 | 30.0758
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK002 | Project_065_RISK002 | Opportunitity | Project Contingency | Open | H1 | 5 | 12. Acquisition and offsets | New supplier for enclosure | Person_598 | 2015-01-06 22:00 | 2017-10-18 22:00 | 0.05 | 9.6346 | 0.48173 | Exploit | 0.7 | 9.6346 | 6.7442 | H1 | 5 | Stable | [10 empty] | 0 | -1300 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier Selection Process | Person_379 | 2017-10-18 22:00 | 2019-04-23 | 0.4 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 104 | 129 | 141 | 126.8333 | 0.4 | 5 | 51 | 71 | 46.6667 |  | 25 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Colour Representation in Video Image Distortion | Person_305 | 2017-09-21 22:00 | 2020-03-21 | 0.5 | 5.5323 | 2.7662 | Reduce | 0.1 | 5.5323 | 0.55323 | H3 | 3 | Stable | 0.7 | 88 | 134 | 159 | 130.5 | 0.2 | 32 | 58 | 68 | 55.3333 | 0 | 80 | 1 | 2.4
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-20 22:00 | 0.8 | 35.2369 | 28.1895 | Reduce | 0.3 | 18.4979 | 5.5494 | H2 | 4 | Stable | 0.7 | 87 | 123 | 150 | 121.5 | 0.2 | 28 | 54 | 76 | 53.3333 | 47.5042 | 62.5 | 0 | 28.5025
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 4 | 9. Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-20 22:00 | 0.7 | 20.6835 | 14.4785 | Reduce | 0.3 | 20.6835 | 6.2051 | H2 | 4 | Stable | 0.6 | 92 | 133 | 151 | 129.1667 | 0.2 | 11 | 56 | 76 | 51.8333 | 0 | 57.1429 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 4 | 8. System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 0.6 | 5.2585 | 3.1551 | Reduce | 0.15 | 5.2585 | 0.78877 | H2 | 4 | Stable | 0.7 | 111 | 139 | 145 | 135.3333 | 0.3 | 1 | 52 | 69 | 46.3333 | 0 | 75 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-04-21 | 0.3 | 2.723 | 0.81691 | Reduce | 0.1 | 2.723 | 0.2723 | H3 | 3 | Improving | 0.7 | 118 | 136 | 141 | 133.8333 | 0.4 | 27 | 43 | 70 | 44.8333 | 0 | 66.6667 | 1 | 2
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-07 22:00 | 2020-09-20 22:00 | 0.2 | 4.8444 | 0.96888 | Reduce | 0.2 | 4.8444 | 0.96888 | H3 | 3 | Stable | 0.8 | 85 | 131 | 153 | 127 | 0.4 | 6 | 41 | 77 | 41.1667 | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System Performance | Person_305 | 2016-09-07 22:00 | 2020-09-20 22:00 | 0.15 | 5.8725 | 0.88088 | Reduce | 0.05 | 5.8725 | 0.29363 | H2 | 4 | Stable | 0.7 | 117 | 140 | 159 | 139.3333 | 0.1 | 34 | 49 | 79 | 51.5 | 0 | 66.6667 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-23 | 2024-05-22 | 0.1 | 4.8596 | 1.4579 | Accept | 0.1 | 4.8596 | 1.4579 | H3 | 3 | Improving | 0.5 | 81 | 124 | 157 | 122.3333 | 0.5 | 81 | 124 | 157 | 122.3333 | 0 | 0 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_038 | 2020-05-23 | 2023-10-25 22:00 | 0.2 | 7.4599 | 1.492 | Reduce | 0.05 | 7.4599 | 0.37299 | H2 | 4 | Stable | 0.7 | 109 | 132 | 160 | 132.8333 | 0.1 | 10 | 48 | 73 | 45.8333 | 0 | 75 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-28 22:00 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.6 | 96 | 122 | 146 | 121.6667 | 0.1 | 11 | 48 | 74 | 46.1667 | 60.3671 | 58.3333 | 0 | 36.2202
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-19 22:00 | 0.4 | 2.8643 | 1.1457 | Reduce | 0.1 | 2.8643 | 0.28643 | H3 | 3 | Stable | 0.9 | 103 | 139 | 148 | 134.5 | 0.3 | 10 | 42 | 79 | 42.8333 | 0.0015933 | 75 | 1 | 2.251
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power Supply - Motor Controller Interface | Person_047 | 2016-05-23 | 2018-04-21 | 0.5 | 25.3543 | 12.6771 | Reduce | 0.2 | 25.3543 | 5.0709 | H3 | 3 | Stable | 0.5 | 96 | 130 | 158 | 129 | 0.3 | 17 | 50 | 62 | 46.5 | 0 | 60 | 1 | 1.8
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Unforseen and substantial increase in Repairs workload during new build production period. | Person_547 | 2017-10-23 01:00 | 2019-08-21 01:00 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.25 | 1.5434 | 0.38586 | H2 | 4 | Stable | 0.6 | 100 | 123 | 142 | 122.3333 | 0.2 | 26 | 52 | 74 | 51.3333 | 0 | 16.6667 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK007 | Project_041_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Advanced production of products using a Qual. standard component rather than a Prod. standard | Person_547 | 2017-10-21 01:00 | 2019-02-20 01:00 | 0.49 | 1.2862 | 0.63024 | Reduce | 0.2 | 1.2862 | 0.25724 | H3 | 3 | Stable | 0.9 | 117 | 130 | 160 | 132.8333 | 0.3 | 22 | 55 | 75 | 52.8333 | 0 | 59.1837 | 1 | 1.7755
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK011 | Project_041_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Supplier Development support | Person_693 | 2018-04-11 | 2018-07-21 | 0.5 | 10.5437 | 2.1087 | Accept | 0.332 | 10.5437 | 2.1087 | H2 | 4 | Stable | 0.9 | 89 | 126 | 147 | 123.3333 | 0.9 | 89 | 126 | 147 | 123.3333 | 0 | 33.6 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK010 | Project_041_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Digital Assembly - Testing | Person_547 | 2018-04-11 | 2018-08-20 | 0.15 | 5.9234 | 1.1847 | Accept | 0.1 | 5.9234 | 0.59234 | H3 | 3 | Improving | 0.7 | 116 | 128 | 157 | 130.8333 | 0.7 | 116 | 128 | 157 | 130.8333 | 0 | 33.3333 | 1 | 1
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK013 | Project_041_RISK013 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional components validation | Person_693 | 2017-07-15 | 2018-09-20 01:00 | 0.4 | 0.60436 | 0.48349 | Accept | 0.3 | 0.60436 | 0.48349 | H2 | 4 | Stable | 0.5 | 88 | 131 | 159 | 128.5 | 0.5 | 88 | 131 | 159 | 128.5 | 0 | 25 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Outstanding CRs | Person_693 | 2017-05-23 | 2018-12-21 01:00 | 0.7 | 0 | 0 | Accept | 0.3 | 0 | 0 | H3 | 3 | Stable | 0.7 | 95 | 128 | 143 | 125 | 0.7 | 95 | 128 | 143 | 125 |  | 57.1429 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of not being able to perform Tests | Person_547 | 2018-08-20 | 2019-01-21 01:00 | 0.5 | 0.60436 | 0.18131 | Accept | 0.5 | 0.60436 | 0.18131 | H2 | 4 | Stable | 0.8 | 108 | 128 | 146 | 127.6667 | 0.8 | 108 | 128 | 146 | 127.6667 | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Availability of key resource within Engineering | Person_693 | 2018-01-21 01:00 | 2019-05-23 | 0.1 | 0.33844 | 0.10153 | Accept | 0.1 | 0.33844 | 0.10153 | H3 | 3 | Improving | 0.7 | 114 | 132 | 154 | 132.6667 | 0.7 | 114 | 132 | 154 | 132.6667 | 0 | 0 | 1 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_547 | 2017-05-23 | 2019-01-21 01:00 | 0.5 | 0 | 0 | Accept | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.5 | 119 | 133 | 155 | 134.3333 | 0.5 | 119 | 133 | 155 | 134.3333 |  | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_693 | 2017-04-22 | 2018-08-19 | 0.15 | 4.0901 | 1.227 | Accept | 0.1 | 12.6747 | 3.8024 | H3 | 3 | Stable | 0.9 | 83 | 129 | 160 | 126.5 | 0.9 | 83 | 129 | 160 | 126.5 | -209.8901 | 33.3333 | 0 | -125.9341
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK016 | Project_038_RISK016 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Supplier Quality Issues | Person_397 | 2012-11-20 01:00 | 2018-08-22 01:00 | 0.5 | 5.0339 | 2.517 | Avoid | 0.5 | 5.0339 | 2.517 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Production - Supplier Quality | Person_468 | 2017-05-23 | 2019-08-20 | 0.25 | 2.4645 | 0.4929 | Accept | 0.192 | 2.4645 | 0.4929 | H3 | 3 | Improving | 0.6 | 85 | 126 | 158 | 124.5 | 0.6 | 85 | 126 | 158 | 124.5 | 0 | 23.2 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK018 | Project_038_RISK018 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Last System Syndrome | Person_329 | 2012-11-20 01:00 | 2018-10-21 01:00 | 0.15 | 43.4175 | 6.5126 | Reduce | 0.13 | 43.4175 | 5.6443 | H2 | 4 | Worsening | 0.5 | 98 | 126 | 142 | 124 | 0.2 | 6 | 55 | 60 | 47.6667 | 0 | 13.3333 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Additional minor point release | Person_228 | 2016-05-23 | 2019-06-23 | 0.5 | 11.9444 | 5.9722 | Reduce | 0.25 | 11.9444 | 2.9861 | H2 | 4 | Stable | 0.8 | 85 | 139 | 150 | 131.8333 | 0.2 | 37 | 54 | 77 | 55 | 0 | 50 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_228 | 2016-05-23 | 2018-12-21 01:00 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.8 | 82 | 136 | 141 | 127.8333 | 0.4 | 27 | 45 | 73 | 46.6667 | 0 | 50 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_004 | 2015-11-21 01:00 | 2018-11-20 01:00 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.8 | 120 | 126 | 141 | 127.5 | 0.4 | 16 | 45 | 77 | 45.5 | 0 | 5 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.8 | 2.8043 | 2.2435 | Reduce | 0.45 | 2.8043 | 1.2619 | H1 | 5 | Stable | 0.7 | 110 | 131 | 159 | 132.1667 | 0.4 | 8 | 55 | 75 | 50.5 | 0 | 43.75 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK167 | Project_024_RISK167 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Customer not providing the information needed or Customer not accepting the Customer documentation resulting in rewor. | Person_052 | 2016-08-21 01:00 | 2018-06-21 | 0.5 | 9.971 | 4.9855 | Reduce | 0.3 | 9.971 | 2.9913 | H1 | 5 | Improving | 0.9 | 120 | 131 | 155 | 133.1667 | 0.3 | 34 | 57 | 65 | 54.5 | 0 | 40 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.8 | 86 | 136 | 157 | 131.1667 | 0.3 | 19 | 55 | 63 | 50.3333 | 0 | 60 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis and Security | Person_119 | 2017-02-22 01:00 | 2019-05-22 | 0.3 | 19.9938 | 5.9981 | Reduce | 0.04675 | 19.9938 | 0.93471 | H3 | 3 | Improving | 0.9 | 91 | 132 | 146 | 127.5 | 0.2 | 37 | 46 | 68 | 48.1667 | 0 | 84.4167 | 1 | 2.5325
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.2 | 3.843 | 0.76859 | H2 | 4 | Stable | 0.9 | 117 | 126 | 153 | 129 | 0.4 | 25 | 56 | 75 | 54 | 0 | 60 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Performance (collector opportunity) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.373 | 19.5316 | 7.2853 | -- | 0.4158 | 19.5316 | 8.1213 | H1 | 5 | Stable | [10 empty] | 0 | -11.4745 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.3 | 20.8767 | 6.263 | H1 | 5 | Stable | 0.5 | 95 | 124 | 153 | 124 | 0.1 | 8 | 57 | 79 | 52.5 | 50 | 25 | 0 | 30
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.504 | 73.3644 | 36.9756 | Reduce | 0.0852 | 53.773 | 4.5815 | H2 | 4 | Worsening | 0.9 | 112 | 125 | 150 | 127 | 0.1 | 36 | 45 | 63 | 46.5 | 26.7042 | 83.0952 | 0 | 16.0225
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK308 | Project_024_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System robustness and resilience | Person_774 | 2017-04-06 | 2018-06-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.1 | 2.5966 | 0.25966 | H3 | 3 | Stable | 0.9 | 117 | 134 | 143 | 132.6667 | 0.4 | 24 | 57 | 79 | 55.1667 | 58.3333 | 66.6667 | 1 | 37
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2018-05-22 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.7 | 113 | 125 | 160 | 128.8333 | 0.3 | 21 | 48 | 69 | 47 | 0 | 40 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 0.92411 | 0.55447 | Reduce | 0.5 | 0.36965 | 0.18482 | H2 | 4 | Stable | 0.6 | 84 | 126 | 154 | 123.6667 | 0.2 | 20 | 45 | 76 | 46 | 60 | 16.6667 | 0 | 36
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-03 20:00 | 2018-04-21 | 0.2 | 4.0661 | 0.81322 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.5 | 106 | 124 | 151 | 125.5 | 0.3 | 37 | 44 | 63 | 46 | 0 | 75 | 1 | 2.25
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.5 | 0.46206 | 0.23103 | H1 | 5 | Stable | 0.5 | 86 | 122 | 150 | 120.6667 | 0.1 | 24 | 58 | 73 | 54.8333 | 58.3333 | 16.6667 | 0 | 35
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-28 20:00 | 2018-05-22 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.9 | 109 | 140 | 156 | 137.5 | 0.1 | 4 | 56 | 60 | 48 | 0 | 50 | 1 | 1.5
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2018-05-22 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.9 | 118 | 127 | 160 | 131 | 0.3 | 18 | 42 | 66 | 42 | 0 | 25 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_693 | 2012-06-01 | 2018-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Improving | 0.9 | 120 | 133 | 144 | 132.6667 | 0.3 | 8 | 50 | 67 | 45.8333 | 0 | 40 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2018-05-21 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Stable | [10 empty] | 0 | 37.5 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2018-02-18 20:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.7 | 89 | 128 | 150 | 125.1667 | 0.2 | 37 | 40 | 73 | 45 | 90 | 75 | 1 | 56.25
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK003 | Project_024_RISK003 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance | Person_119 | 2017-12-21 01:00 | 2019-02-20 01:00 | 0.31667 | 0.36965 | 0.25875 | Accept | 0.04388 | 0.36965 | 0.25875 | H2 | 4 | Stable | 0.6 | 94 | 123 | 147 | 122.1667 | 0.6 | 94 | 123 | 147 | 122.1667 | 0 | 86.1432 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK010 | Project_010_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Use of Lead components | Person_359 | 2012-05-23 | 2025-04-22 | 0.05 | 1.8482 | 0.092411 | Reduce | 0.05 | 1.8482 | 0.092411 | H3 | 3 | Stable | 0.7 | 94 | 126 | 145 | 123.8333 | 0.4 | 21 | 58 | 73 | 54.3333 | 0 | 0 | 1 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before part b finished | Person_119 | 2016-10-20 01:00 | 2018-04-21 | 0.3 | 1.593 | 0.39825 | Accept | 0.27 | 1.593 | 0.39825 | H2 | 4 | Worsening | 0.9 | 119 | 122 | 156 | 127.1667 | 0.9 | 119 | 122 | 156 | 127.1667 | 0 | 10 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-19 20:00 | 0.05 | 1.2744 | 0.63719 | Accept | 0.03 | 1.2744 | 0.63719 | H2 | 4 | Stable | 0.6 | 93 | 124 | 157 | 124.3333 | 0.6 | 93 | 124 | 157 | 124.3333 | 0 | 40 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2018-04-22 | 0.8 | 2.5488 | 0.89207 | Accept | 0.6 | 2.5488 | 0.89207 | H1 | 5 | Stable | 0.5 | 97 | 123 | 148 | 122.8333 | 0.5 | 97 | 123 | 148 | 122.8333 | 0 | 25 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-26 20:00 | 2018-05-22 | 0.1 | 0.63719 | 0.50975 | Accept | 0.05 | 1.4974 | 1.1979 | H2 | 4 | Stable | 0.5 | 117 | 138 | 147 | 136 | 0.5 | 117 | 138 | 147 | 136 | -135 | 50 | 0 | -81
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2018-05-21 | 0.2 | 0.82835 | 0.49701 | Accept | 0.2 | 0.82835 | 0.49701 | H3 | 3 | Worsening | 0.6 | 111 | 124 | 141 | 124.6667 | 0.6 | 111 | 124 | 141 | 124.6667 | 0 | 0 | 1 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2018-04-22 | 0.3 | 9.5749 | 4.3087 | Accept | 0.2 | 9.5749 | 4.3087 | H3 | 3 | Stable | 0.9 | 111 | 124 | 145 | 125.3333 | 0.9 | 111 | 124 | 145 | 125.3333 | 0 | 33.3333 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK026 | Project_069_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional Representative HW | Person_257 | 2018-03-16 01:00 | 2021-07-16 | 0.25 | 8.5887 | 0.85887 | Accept | 0.25 | 8.5887 | 0.85887 | H2 | 4 | Stable | 0.6 | 90 | 125 | 144 | 122.3333 | 0.6 | 90 | 125 | 144 | 122.3333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK025 | Project_069_RISK025 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Additional in-country presence (all WP's) | Person_257 | 2018-03-16 01:00 | 2021-07-16 | 0.5 | 0 | 0 | Accept | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.5 | 110 | 126 | 147 | 126.8333 | 0.5 | 110 | 126 | 147 | 126.8333 |  | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-054 | Project_062_Risk-054 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | sub-system rework to reviised standard | Person_031 | 2017-07-21 | 2018-11-21 01:00 | 0.4 | 0.62744 | 0.25098 | Transfer | 0.4 | 0.62744 | 0.25098 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK044 | Project_053_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Product Hardening | Person_719 | 2018-03-23 | 2019-01-20 | 0.3 | 7.9015 | 2.3705 | Avoid | 0.3 | 7.9015 | 2.3705 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-010 | Project_062_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Resource | Person_479 | 2017-07-21 | 2019-02-21 01:00 | 0.4 | 7.5293 | 3.0117 | Reduce | 0.3 | 7.5293 | 2.2588 | H2 | 4 | Stable | 0.8 | 88 | 133 | 151 | 128.5 | 0.1 | 27 | 49 | 70 | 48.8333 | 0 | 25 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK022 | Project_069_RISK022 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Handbooks - Level of SW Change may increase (Not increase in scope). | Person_056 | 2018-03-16 01:00 | 2021-07-16 | 0.4 | 4.4955 | 0.44955 | Accept | 0.4 | 4.4955 | 0.44955 | H3 | 3 | Stable | 0.5 | 91 | 125 | 156 | 124.5 | 0.5 | 91 | 125 | 156 | 124.5 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK024 | Project_069_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Training | Person_479 | 2018-03-16 01:00 | 2021-07-16 | 0.5 | 4.183 | 1.2549 | Accept | 0.5 | 4.183 | 1.2549 | H2 | 4 | Stable | 0.7 | 94 | 135 | 160 | 132.3333 | 0.7 | 94 | 135 | 160 | 132.3333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK020 | Project_069_RISK020 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Directives may have a wider impact and requires additional work. | Person_530 | 2018-03-16 01:00 | 2021-07-16 | 0.35 | 2.2986 | 1.1493 | Accept | 0.35 | 2.2986 | 0.45973 | H2 | 4 | Stable | 0.7 | 113 | 122 | 159 | 126.6667 | 0.7 | 113 | 122 | 159 | 126.6667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-013 | Project_062_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Unavailability of Network | Person_479 | 2017-07-21 | 2018-07-08 | 0.25 | 3.5555 | 0.88888 | Reduce | 0.2 | 3.5555 | 0.7111 | H3 | 3 | Stable | 0.7 | 81 | 139 | 146 | 130.5 | 0.3 | 1 | 56 | 70 | 49.1667 | 0 | 20 | 1 | 0.6
2018-06-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK015 | Project_053_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Equipment export licences | Person_252 | 2018-06-23 | 2019-07-22 | 0.3 | 2.586 | 0.77579 | Avoid | 0.1 | 2.586 | 0.2586 | H3 | 3 | Improving | [10 empty] | 0 | 66.6667 | 1 | 2
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-011 | Project_062_Risk-011 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Variant deviations between SW | Person_479 | 2017-07-21 | 2018-06-22 | 0.4 | 0.71808 | 0.28723 | Reduce | 0.3 | 0.71808 | 0.21542 | H2 | 4 | Stable | 0.5 | 97 | 129 | 149 | 127 | 0.3 | 30 | 43 | 72 | 45.6667 | 0 | 25 | 0 | 0
2018-06-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK006 | Project_053_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional UK integration of the System product | Person_719 | 2018-10-22 | 2019-01-21 | 0.2 | 6.3212 | 1.2642 | Avoid | 0.2 | 6.3212 | 1.2642 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 1 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK007 | Project_069_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Without dedicated Datastore hardware, lots of re-work is required | Person_479 | 2018-05-24 | 2018-10-20 01:00 | 0.8 | 5.2705 | 1.5811 | Accept | 0.8 | 4.3921 | 0.87842 | H2 | 4 | Stable | 0.6 | 120 | 132 | 153 | 133.5 | 0.6 | 120 | 132 | 153 | 133.5 | 16.6667 | 0 | 0 | 10
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-056 | Project_062_Risk-056 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Supplier integration acceptance by end Customer | Person_031 | 2017-07-21 | 2018-11-21 01:00 | 0.3 | 1.8823 | 0.5647 | Reduce | 0.3 | 1.8823 | 0.5647 | H3 | 3 | Stable | 0.7 | 83 | 134 | 147 | 127.6667 | 0.4 | 7 | 40 | 67 | 39 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-017 | Project_062_Risk-017 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Customer platform Schedule Unknown | Person_459 | 2017-07-21 | 2018-10-22 01:00 | 0.2 | 2.5098 | 0.50196 | Avoid | 0.1 | 2.5098 | 0.25098 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 1 | 1.5
2018-06-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK005 | Project_053_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier Deiivery Schedule | Person_252 | 2018-01-21 | 2018-11-20 | 0.5 | 5.3299 | 2.665 | Reduce | 0.25 | 5.3299 | 1.3325 | H2 | 4 | Stable | 0.5 | 107 | 125 | 157 | 127.3333 | 0.2 | 10 | 44 | 72 | 43 | 0 | 50 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK009 | Project_069_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sizings assume that at least 1 software engineer on the project has at least 2 years experience | Person_479 | 2018-03-16 01:00 | 2021-07-16 | 0.6 | 12.7037 | 4.4463 | Accept | 0.6 | 12.7037 | 3.1759 | H2 | 4 | Stable | 0.8 | 113 | 131 | 148 | 130.8333 | 0.8 | 113 | 131 | 148 | 130.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK010 | Project_053_RISK010 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Immaturity of the core product | Person_719 | 2018-08-22 | 2018-11-20 | 0.5 | 6.4649 | 3.2325 | Avoid | 0.7 | 6.4649 | 4.5254 | H1 | 5 | Worsening | [10 empty] | 0 | -40 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-037 | Project_062_Risk-037 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Server availability | Person_479 | 2017-07-21 | 2018-09-20 01:00 | 0.35 | 4.183 | 1.464 | Avoid | 0.1 | 4.183 | 0.4183 | H3 | 3 | Stable | [10 empty] | 0 | 71.4286 | 1 | 2.1429
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-013 | Project_052_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Additional material and effort required to support the delta equipment | Person_271 | 2017-08-19 01:00 | 2020-08-20 01:00 | 0.45 | 1.4007 | 0.49026 | Accept | 0.45 | 1.4007 | 0.49026 | H2 | 4 | Stable | 0.7 | 91 | 128 | 151 | 125.6667 | 0.7 | 91 | 128 | 151 | 125.6667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-016 | Project_062_Risk-016 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier Component Unavailability | Person_664 | 2017-07-21 | 2018-09-20 01:00 | 0.3 | 4.183 | 1.2549 | Reduce | 0.2 | 4.183 | 0.83659 | H3 | 3 | Stable | 0.9 | 107 | 137 | 141 | 132.6667 | 0.3 | 22 | 46 | 63 | 44.8333 | 0 | 33.3333 | 1 | 1
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-020 | Project_062_Risk-020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Security Encryption Solution | Person_245 | 2017-07-21 | 2018-09-20 01:00 | 0.25 | 4.183 | 1.0457 | Reduce | 0.2 | 4.183 | 0.83659 | H2 | 4 | Improving | 0.7 | 97 | 129 | 148 | 126.8333 | 0.3 | 8 | 47 | 77 | 45.5 | 0 | 20 | 0 | 0
2018-06-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK007 | Project_053_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Resources Uavailable | Person_252 | 2017-11-20 | 2019-08-21 | 0.5 | 10.3438 | 5.1719 | Reduce | 0.2 | 7.9015 | 1.5803 | H3 | 3 | Stable | 0.6 | 87 | 127 | 149 | 124 | 0.2 | 21 | 54 | 69 | 51 | 23.6111 | 60 | 1 | 15.9666
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-021 | Project_062_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Hardware CoSupplierng | Person_664 | 2017-07-21 | 2018-09-20 01:00 | 0.3 | 7.5293 | 2.2588 | Reduce | 0.25 | 7.5293 | 1.8823 | H2 | 4 | Stable | 0.9 | 99 | 129 | 153 | 128 | 0.1 | 37 | 56 | 70 | 55.1667 | 0 | 16.6667 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-043 | Project_062_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | User response | Person_479 | 2017-07-21 | 2019-02-21 01:00 | 0.35 | 3.3464 | 1.1712 | Avoid | 0.25 | 3.3464 | 0.83659 | H2 | 4 | Stable | [10 empty] | 0 | 28.5714 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-047 | Project_062_Risk-047 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Redhat6 on PCI shelf | Person_245 | 2017-07-21 | 2019-03-24 | 0.3 | 7.1808 | 2.1542 | Avoid | 0.3 | 7.1808 | 2.1542 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-025 | Project_062_Risk-025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | System Obsolescence Risk | Person_543 | 2017-07-21 | 2019-03-22 | 0.3 | 2.0915 | 0.62744 | Avoid | 0.2 | 2.0915 | 0.4183 | H2 | 4 | Stable | [10 empty] | 0 | 33.3333 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-022 | Project_062_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Registers Might Be Unstable | Person_479 | 2017-07-21 | 2018-08-19 | 0.25 | 1.3385 | 0.33464 | Reduce | 0.2 | 1.3385 | 0.26771 | H3 | 3 | Stable | 0.7 | 98 | 127 | 153 | 126.5 | 0.4 | 15 | 41 | 76 | 42.5 | 0 | 20 | 1 | 0.6
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-023 | Project_062_Risk-023 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Change In Security Boundary | Person_031 | 2017-07-21 | 2019-02-21 01:00 | 0.3 | 4.6013 | 1.3804 | Reduce | 0.15 | 4.6013 | 0.69019 | H3 | 3 | Stable | 0.9 | 82 | 139 | 156 | 132.3333 | 0.2 | 2 | 45 | 76 | 43 | 0 | 50 | 1 | 1.5
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-006 | Project_062_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unavailability of Test Hardware | Person_253 | 2017-07-21 | 2019-03-22 | 0.5 | 2.5098 | 1.2549 | Reduce | 0.25 | 2.5098 | 0.62744 | H2 | 4 | Stable | 0.9 | 117 | 136 | 157 | 136.3333 | 0.4 | 20 | 45 | 66 | 44.3333 | 0 | 50 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-048 | Project_062_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software lockdown features | Person_245 | 2017-07-21 | 2018-11-21 01:00 | 0.5 | 0.71808 | 0.35904 | Reduce | 0.5 | 0.71808 | 0.35904 | H2 | 4 | Stable | 0.7 | 100 | 132 | 155 | 130.5 | 0.3 | 39 | 56 | 78 | 56.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-005 | Project_062_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Security Solution Integration | Person_245 | 2017-07-21 | 2018-11-14 01:00 | 0.3 | 4.6013 | 1.3804 | Avoid | 0.25 | 4.6013 | 1.1503 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-010 | Project_052_Risk-010 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Potential update of software / hardware required during the 3 year support period (RESOURCE) | Person_376 | 2017-08-19 01:00 | 2020-08-19 01:00 | 0.25 | 2.5098 | 1.2549 | Accept | 0.25 | 2.5098 | 0.75293 | H3 | 3 | Stable | 0.5 | 107 | 138 | 145 | 134 | 0.5 | 107 | 138 | 145 | 134 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-012 | Project_062_Risk-012 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Integration Rig Move | Person_253 | 2018-05-23 | 2019-05-23 | 0.3 | 0.4183 | 0.12549 | Avoid | 0.3 | 0.4183 | 0.12549 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-009 | Project_052_Risk-009 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | System acceptance not costed in line with Customer expectations | Person_651 | 2017-08-19 01:00 | 2018-06-22 | 0.1 | 2.0207 | 0.20207 | Accept | 0.1 | 2.0207 | 0.20207 | H3 | 3 | Stable | 0.9 | 85 | 124 | 152 | 122.1667 | 0.9 | 85 | 124 | 152 | 122.1667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK047 | Project_053_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Lab Availability | Person_252 | 2017-10-21 | 2020-01-22 | 0.5 | 1.0457 | 0.52287 | Accept | 0.2 | 1.0457 | 0.52287 | H3 | 3 | Improving | 0.7 | 88 | 122 | 151 | 121.1667 | 0.7 | 88 | 122 | 151 | 121.1667 | 0 | 60 | 1 | 1.8
2018-06-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK043 | Project_053_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Change in REACH/RoSH Legislation | Person_302 | 2017-11-20 | 2018-09-20 | 0.1 | 0.50826 | 0.40661 | Accept | 0.1 | 0.50826 | 0.40661 | H2 | 4 | Stable | 0.5 | 83 | 131 | 143 | 125 | 0.5 | 83 | 131 | 143 | 125 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-024 | Project_062_Risk-024 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional SW Build post-Factory Acceptance Test | Person_253 | 2019-01-22 01:00 | 2019-04-22 | 0.3 | 1.7778 | 0.53333 | Avoid | 0.3 | 1.7778 | 0.53333 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE-10 | Project_067_SE-10 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Configuration baseline unstable for Platform | Person_327 | 2017-10-26 01:00 | 2018-08-18 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.5 | 83 | 130 | 159 | 127 | 0.2 | 16 | 58 | 74 | 53.6667 |  | 60 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK004 | Project_059_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Cyber Security Obligations | Person_592 | 2017-10-21 01:00 | 2019-08-04 | 0.4 | 0.80829 | 0.32332 | Reduce | 0.2 | 0.80829 | 0.16166 | H3 | 3 | Stable | 0.7 | 86 | 122 | 158 | 122 | 0.3 | 2 | 59 | 79 | 52.8333 | 0 | 50 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-027 | Project_062_Risk-027 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Facility to Test modifications | Person_253 | 2018-08-22 01:00 | 2020-04-21 | 0.5 | 2.3703 | 1.1852 | Reduce | 0.4 | 2.3703 | 0.94814 | H2 | 4 | Stable | 0.8 | 98 | 140 | 143 | 133.5 | 0.4 | 21 | 46 | 77 | 47 | 0 | 20 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-057 | Project_062_Risk-057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Supplier Application Encryption / Protection | Person_479 | 2017-07-21 | 2019-02-21 01:00 | 0.3 | 2.7703 | 1.3852 | Accept | 0.3 | 2.7703 | 1.3852 | H2 | 4 | Stable | 0.7 | 91 | 134 | 156 | 130.5 | 0.7 | 91 | 134 | 156 | 130.5 | 0 | 0 | 0 | 0
2018-06-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK046 | Project_053_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Un-Planned Production Activities | Person_252 | 2019-07-22 | 2020-01-22 | 0.5 | 1.2124 | 0.12124 | Accept | 0.2 | 1.2124 | 0.12124 | H3 | 3 | Stable | 0.5 | 109 | 133 | 148 | 131.5 | 0.5 | 109 | 133 | 148 | 131.5 | 0 | 60 | 1 | 1.8
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-008 | Project_062_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Paperwork for Legacy Items | Person_459 | 2018-03-23 | 2019-03-24 | 0.3 | 0.83659 | 0.25098 | Avoid | 0.3 | 0.83659 | 0.25098 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-018 | Project_062_Risk-018 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Prioritisation - new or less experienced staff | Person_459 | 2017-07-21 | 2018-11-20 01:00 | 0.35 | 0.80829 | 0.16166 | Accept | 0.25 | 0.80829 | 0.16166 | H2 | 4 | Improving | 0.9 | 84 | 130 | 149 | 125.5 | 0.9 | 84 | 130 | 149 | 125.5 | 0 | 28.5714 | 0 | 0
2018-06-23 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK021 | Project_053_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Product documentation | Person_719 | 2018-08-22 | 2019-07-26 | 0.35 | 0.60622 | 0.18186 | Accept | 0.35 | 0.60622 | 0.18186 | H2 | 4 | Worsening | 0.8 | 113 | 131 | 155 | 132 | 0.8 | 113 | 131 | 155 | 132 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-009 | Project_062_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Unresolved technical debt (excluding ILS) | Person_253 | 2017-07-21 | 2019-03-23 | 0.5 | 1.2198 | 0.60991 | Accept | 0.3 | 1.2198 | 0.30495 | H2 | 4 | Stable | 0.6 | 81 | 129 | 152 | 124.8333 | 0.6 | 81 | 129 | 152 | 124.8333 | 0 | 40 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-007 | Project_062_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Hardware Encryption / Protection | Person_479 | 2018-02-10 01:00 | 2019-03-22 | 0.3 | 4.183 | 1.2549 | Reduce | 0.2 | 4.183 | 0.83659 | H3 | 3 | Stable | 0.5 | 105 | 124 | 145 | 124.3333 | 0.1 | 17 | 53 | 61 | 48.3333 | 0 | 33.3333 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK009 | Project_059_RISK009 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Safety risk mitigations - UNCERTAINTY | Person_592 | 2017-10-21 01:00 | 2019-08-20 | 0.1 | 3.6256 | 1.4502 | Accept | 0.1 | 3.6256 | 1.4502 | H3 | 3 | Stable | 0.7 | 113 | 127 | 158 | 129.8333 | 0.7 | 113 | 127 | 158 | 129.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-015 | Project_062_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Re-work | Person_253 | 2018-03-01 01:00 | 2019-05-22 | 0.5 | 0.64865 | 0.32433 | Accept | 0.5 | 0.64865 | 0.32433 | H2 | 4 | Stable | 0.5 | 82 | 132 | 148 | 126.3333 | 0.5 | 82 | 132 | 148 | 126.3333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK075 | Project_076_RISK075 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Delay in SW completion - Safety issues | Person_152 | 2018-07-05 | 2019-05-16 | 0.5 | 1.6723 | 0.83613 | Reduce | 0.1 | 1.6723 | 0.16723 | H3 | 3 | Stable | 0.5 | 100 | 122 | 148 | 122.6667 | 0.2 | 29 | 53 | 76 | 52.8333 | 0 | 80 | 1 | 2.4
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | FOC Acceptance | Person_499 | 2018-07-25 | 2018-08-19 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.15 | 8.471 | 1.2706 | H3 | 3 | Stable | 0.7 | 113 | 128 | 142 | 127.8333 | 0.2 | 37 | 58 | 74 | 57.1667 | -99.9999 | 57.1429 | 1 | -58.2857
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | RISK015 | Project_028_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Engineering Change | Person_496 | 2018-07-22 | 2018-09-20 01:00 | 0.5 | 8.8098 | 3.0834 | Accept | 0.5 | 8.8098 | 1.762 | H2 | 4 | Stable | 0.5 | 99 | 128 | 159 | 128.3333 | 0.5 | 99 | 128 | 159 | 128.3333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK003 | Project_059_RISK003 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Catalyst Requirements | Person_278 | 2017-10-21 01:00 | 2019-02-20 01:00 | 0.2 | 1.6166 | 0.16166 | Accept | 0.2 | 1.6166 | 0.16166 | H3 | 3 | Stable | 0.5 | 113 | 121 | 150 | 124.5 | 0.5 | 113 | 121 | 150 | 124.5 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK013 | Project_059_RISK013 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | ICD Errors - Uncertainty | Person_278 | 2017-10-21 01:00 | 2019-03-23 | 0.15 | 1.2124 | 0.18186 | Reduce | 0.15 | 1.2124 | 0.18186 | H3 | 3 | Stable | 0.9 | 104 | 134 | 142 | 130.3333 | 0.4 | 13 | 54 | 73 | 50.3333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK014 | Project_059_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Integration Materials - UNCERTAINTY | Person_278 | 2017-10-21 01:00 | 2019-08-04 | 0.3 | 1.6166 | 0.32332 | Accept | 0.3 | 1.6166 | 0.32332 | H3 | 3 | Stable | 0.9 | 116 | 127 | 156 | 130 | 0.9 | 116 | 127 | 156 | 130 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Interface implementation | Person_496 | 2018-07-25 | 2018-08-19 | 0.5 | 9.6742 | 0.96742 | Accept | 0.25 | 9.6742 | 0.96742 | H2 | 4 | Stable | 0.6 | 98 | 131 | 146 | 128 | 0.6 | 98 | 131 | 146 | 128 | 0 | 50 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK012 | Project_059_RISK012 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Failures at Acceptance stage - UNCERTAINTY | Person_278 | 2018-02-18 01:00 | 2019-08-04 | 0.3 | 2.0207 | 0.60622 | Reduce | 0.1 | 2.0207 | 0.20207 | H3 | 3 | Stable | 0.6 | 111 | 135 | 150 | 133.5 | 0.2 | 17 | 44 | 64 | 42.8333 | 0 | 66.6667 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of the platforms for modification | Person_496 | 2014-01-21 01:00 | 2019-04-10 | 0.67 | 4.3949 | 3.5159 | Accept | 0.55 | 4.3949 | 3.5159 | H2 | 4 | Stable | 0.8 | 119 | 134 | 156 | 135.1667 | 0.8 | 119 | 134 | 156 | 135.1667 | 0 | 17.9104 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_523 | 2018-07-25 | 2018-08-19 | 0.35 | 0.41461 | 0.10365 | Accept | 0.2 | 0.41461 | 0.10365 | H2 | 4 | Stable | 0.9 | 91 | 133 | 155 | 129.6667 | 0.9 | 91 | 133 | 155 | 129.6667 | 0 | 42.8571 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK071 | Project_076_RISK071 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | System development of components | Person_474 | 2018-03-23 | 2018-11-20 01:00 | 0.8 | 6.6337 | 5.307 | Reduce | 0.1 | 6.6337 | 0.66337 | H3 | 3 | Stable | 0.8 | 84 | 123 | 148 | 120.6667 | 0.3 | 15 | 53 | 67 | 49 | 0 | 87.5 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK002 | Project_059_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SW Compatibility | Person_517 | 2017-11-20 01:00 | 2018-10-22 01:00 | 0.1 | 1.6584 | 0.33169 | Accept | 0.1 | 1.6584 | 0.33169 | H3 | 3 | Stable | 0.8 | 85 | 131 | 143 | 125.3333 | 0.8 | 85 | 131 | 143 | 125.3333 | 0 | 0 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK003 | Project_060_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Misalignment of Critical Resource | Person_312 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.7 | 1.0769 | 0.75381 | Reduce | 0.5 | 1.0769 | 0.53844 | H2 | 4 | Stable | 0.6 | 118 | 130 | 156 | 132.3333 | 0.1 | 26 | 53 | 66 | 50.6667 | 0 | 28.5714 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK004 | Project_060_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Cross-functional Estimates | Person_729 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.7 | 2.8845 | 2.0191 | Reduce | 0.5 | 1.4422 | 0.72112 | H2 | 4 | Improving | 0.7 | 117 | 124 | 158 | 128.5 | 0.1 | 3 | 44 | 79 | 43 | 50 | 28.5714 | 0 | 30
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK001 | Project_059_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Critical Personnel | Person_162 | 2017-10-21 01:00 | 2019-08-04 | 0.2 | 1.1538 | 0.5769 | Accept | 0.2 | 1.1538 | 0.5769 | H3 | 3 | Stable | 0.9 | 97 | 121 | 150 | 121.8333 | 0.9 | 97 | 121 | 150 | 121.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK001 | Project_060_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Procurement Prices | Person_033 | 2017-11-02 01:00 | 2018-08-20 | 0.7 | 1.4422 | 1.0096 | Reduce | 0.3 | 1.4422 | 0.43267 | H3 | 3 | Stable | 0.7 | 96 | 122 | 150 | 122.3333 | 0.3 | 28 | 41 | 70 | 43.6667 | 0 | 57.1429 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK006 | Project_060_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Secure material Handling | Person_033 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.5 | 4.4768 | 2.2384 | Accept | 0.5 | 4.4768 | 2.2384 | H2 | 4 | Stable | 0.5 | 97 | 132 | 160 | 130.8333 | 0.5 | 97 | 132 | 160 | 130.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_077 | 2016-01-22 01:00 | 2018-11-17 01:00 | 0.15 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Improving | 0.9 | 109 | 123 | 149 | 125 | 0.4 | 19 | 50 | 76 | 49.1667 |  | 0 | 0
2018-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-07-21 | 0.1 | 4.0291 | 0.40291 | Reduce | 0.1 | 4.0291 | 0.40291 | H2 | 4 | Improving | 0.6 | 91 | 135 | 150 | 130.1667 | 0.3 | 8 | 58 | 70 | 51.6667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_676 | 2016-08-21 01:00 | 2017-08-21 01:00 | 0.5 | 37.5906 | 18.7953 | Reduce | 0.15 | 37.5906 | 5.6386 | H3 | 3 | Stable | 0.9 | 100 | 131 | 152 | 129.3333 | 0.4 | 13 | 41 | 64 | 40.1667 | 0 | 70 | 1 | 2.1
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.4 | 2.563 | 1.0252 | Reduce | 0.4 | 2.563 | 1.0252 | H3 | 3 | Stable | 0.8 | 92 | 136 | 147 | 130.5 | 0.1 | 34 | 50 | 73 | 51.1667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.35 | 1.8788 | 0.18788 | Accept | 0.35 | 1.8225 | 0.12757 | H3 | 3 | Stable | 0.6 | 114 | 126 | 147 | 127.5 | 0.6 | 114 | 126 | 147 | 127.5 | 3 | 0 | 0 | 1.8
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.25 | 1.8788 | 0.18788 | Accept | 0.25 | 1.5031 | 0.12024 | H3 | 3 | Stable | 0.8 | 84 | 137 | 150 | 130.3333 | 0.8 | 84 | 137 | 150 | 130.3333 | 20 | 0 | 0 | 12
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_676 | 2016-10-21 01:00 | 2019-08-20 | 0.5 | 1.8788 | 0.18788 | Accept | 0.5 | 1.5031 | 0.12024 | H2 | 4 | Stable | 0.7 | 111 | 130 | 141 | 128.6667 | 0.7 | 111 | 130 | 141 | 128.6667 | 20 | 0 | 0 | 12
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.2 | 0.79775 | 0.039887 | Accept | 0.2 | 0.79775 | 0.039887 | H3 | 3 | Stable | 0.6 | 110 | 127 | 143 | 126.8333 | 0.6 | 110 | 127 | 143 | 126.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK036 | Project_042_RISK036 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 2 | Person_455 | 2019-05-24 | 2020-05-22 | 0.25 | 10.3335 | 1.0334 | Accept | 0.2 | 10.3335 | 1.0334 | H2 | 4 | Stable | 0.6 | 96 | 121 | 153 | 122.1667 | 0.6 | 96 | 121 | 153 | 122.1667 | 0 | 20 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK039 | Project_042_RISK039 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality Issues 16th August to 15th August | Person_540 | 2020-01-06 | 2021-01-04 | 0.1 | 11.2729 | 2.2546 | Accept | 0.08 | 11.2729 | 2.2546 | H2 | 4 | Stable | 0.7 | 105 | 136 | 157 | 134.3333 | 0.7 | 105 | 136 | 157 | 134.3333 | 0 | 20 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK033 | Project_042_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st April to 30 June | Person_455 | 2019-08-22 | 2019-11-20 | 0.2 | 3.7576 | 0.18788 | Accept | 0.15 | 3.7576 | 0.56365 | H2 | 4 | Stable | 0.8 | 85 | 129 | 158 | 126.5 | 0.8 | 85 | 129 | 158 | 126.5 | 0 | 25 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK035 | Project_042_RISK035 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st October to 31st December | Person_455 | 2021-02-20 | 2021-05-22 | 0.2 | 1.8788 | 0.46971 | Accept | 0.15 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.6 | 115 | 134 | 155 | 134.3333 | 0.6 | 115 | 134 | 155 | 134.3333 | 20 | 25 | 0 | 12
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK048 | Project_042_RISK048 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | On the Job Training. | Person_371 | 2018-03-02 | 2019-02-05 | 0.85 | 2.1043 | 1.7886 | Reduce | 0.5 | 2.1043 | 1.0521 | H1 | 5 | Stable | 0.5 | 119 | 136 | 158 | 136.8333 | 0.2 | 21 | 51 | 74 | 49.8333 | 0 | 41.1765 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK034 | Project_042_RISK034 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st July to 30 September | Person_455 | 2020-11-20 | 2021-02-19 | 0.2 | 4.6971 | 0.93941 | Accept | 0.15 | 3.7576 | 0.56365 | H2 | 4 | Stable | 0.7 | 99 | 138 | 150 | 133.5 | 0.7 | 99 | 138 | 150 | 133.5 | 20 | 25 | 0 | 12
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK040 | Project_042_RISK040 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st May to 30 Oct | Person_455 | 2019-09-21 | 2020-03-21 | 0.1 | 1.8788 | 0.46971 | Accept | 0.07 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.8 | 84 | 128 | 159 | 125.8333 | 0.8 | 84 | 128 | 159 | 125.8333 | 20 | 30 | 0 | 12
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK049 | Project_042_RISK049 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Industry STTE Upkeep. | Person_371 | 2018-03-02 | 2019-02-05 | 0.85 | 1.3152 | 1.1179 | Reduce | 0.5 | 1.3152 | 0.65759 | H2 | 4 | Stable | 0.8 | 89 | 130 | 145 | 125.6667 | 0.3 | 37 | 51 | 73 | 52.3333 | 0 | 41.1765 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK042 | Project_042_RISK042 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st February to 14th July | Person_455 | 2020-06-23 | 2020-12-03 | 0.1 | 1.8788 | 0.46971 | Accept | 0.08 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.7 | 103 | 139 | 148 | 134.5 | 0.7 | 103 | 139 | 148 | 134.5 | 20 | 20 | 0 | 12
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK041 | Project_042_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st Jan | Person_455 | 2020-03-23 | 2020-06-22 | 0.1 | 2.2828 | 0.31959 | Accept | 0.08 | 2.2828 | 0.31959 | H2 | 4 | Stable | 0.7 | 108 | 134 | 146 | 131.6667 | 0.7 | 108 | 134 | 146 | 131.6667 | 0 | 20 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Local customer Engineers in country | Person_455 | 2018-12-20 | 2021-05-22 | 0.05 | 0.56365 | 0.11273 | Accept | 0.05 | 0.28182 | 0.028182 | H2 | 4 | Stable | 0.7 | 85 | 125 | 149 | 122.3333 | 0.7 | 85 | 125 | 149 | 122.3333 | 50 | 0 | 0 | 30
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK026 | Project_042_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st Jan to 31st March | Person_455 | 2020-05-23 | 2020-08-20 | 0.25 | 4.6971 | 0.93941 | Accept | 0.15 | 3.7576 | 0.67638 | H2 | 4 | Stable | 0.6 | 88 | 138 | 148 | 131.3333 | 0.6 | 88 | 138 | 148 | 131.3333 | 20 | 40 | 0 | 12
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK044 | Project_042_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2018-02-20 | 2018-12-21 | 0.32 | 6.5759 | 2.1043 | Reduce | 0.17 | 6.5759 | 1.1179 | H2 | 4 | Stable | 0.9 | 91 | 126 | 145 | 123.3333 | 0.4 | 28 | 46 | 77 | 48.1667 | 0 | 46.875 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK025 | Project_042_RISK025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to 31 Dec | Person_455 | 2020-09-20 | 2021-05-22 | 0.2 | 1.8788 | 0.18788 | Accept | 0.15 | 1.5031 | 0.12024 | H2 | 4 | Stable | 0.5 | 109 | 134 | 159 | 134 | 0.5 | 109 | 134 | 159 | 134 | 20 | 25 | 0 | 12
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK024 | Project_042_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2019-09-21 | 2020-09-19 | 0.33 | 9.3941 | 3.1001 | Reduce | 0.15 | 7.5153 | 1.1273 | H2 | 4 | Stable | 0.9 | 85 | 123 | 150 | 121.1667 | 0.3 | 20 | 43 | 72 | 44 | 20 | 54.5455 | 0 | 12
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK028 | Project_042_RISK028 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st July to 30th September | Person_455 | 2020-11-20 | 2021-02-19 | 0.25 | 0.56365 | 0.11273 | Accept | 0.15 | 0.28182 | 0.028182 | H2 | 4 | Stable | 0.9 | 91 | 138 | 148 | 131.8333 | 0.9 | 91 | 138 | 148 | 131.8333 | 50 | 40 | 0 | 30
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK027 | Project_042_RISK027 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st April to 30th June | Person_455 | 2020-08-21 | 2020-09-19 | 0.25 | 4.6971 | 0.93941 | Accept | 0.15 | 3.7576 | 0.37576 | H2 | 4 | Stable | 0.8 | 91 | 126 | 156 | 125.1667 | 0.8 | 91 | 126 | 156 | 125.1667 | 20 | 40 | 0 | 12
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK045 | Project_042_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2019-01-22 | 2019-05-23 | 0.25 | 3.908 | 0.97699 | Reduce | 0.25 | 3.908 | 0.97699 | H2 | 4 | Stable | 0.8 | 108 | 128 | 145 | 127.5 | 0.3 | 21 | 54 | 77 | 52.3333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK037 | Project_042_RISK037 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 1 | Person_455 | 2020-05-23 | 2021-05-22 | 0.14 | 1.8788 | 0.46971 | Accept | 0.14 | 1.1273 | 0.11273 | H2 | 4 | Stable | 0.5 | 111 | 123 | 159 | 127 | 0.5 | 111 | 123 | 159 | 127 | 40 | 0 | 0 | 24
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-099 | Project_008_Risk-099 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Risk on Consumables Exposure | Person_639 | 2017-08-04 | 2018-08-21 | 0.5 | 5.6817 | 2.8408 | Reduce | 0.5 | 5.6817 | 2.8408 | H3 | 3 | Stable | 0.6 | 89 | 121 | 157 | 121.6667 | 0.3 | 33 | 45 | 77 | 48.3333 | 0 | 0 | 1 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK047 | Project_042_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables | Person_455 | 2020-11-20 | 2021-05-22 | 0.2 | 14.0464 | 4.2139 | Accept | 0.1 | 14.0464 | 4.2139 | H2 | 4 | Stable | 0.5 | 114 | 130 | 144 | 129.6667 | 0.5 | 114 | 130 | 144 | 129.6667 | 0 | 50 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK022 | Project_042_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2017-09-20 | 2018-09-20 | 0.2 | 9.4695 | 4.7347 | Accept | 0.18 | 9.4695 | 4.7347 | H2 | 4 | Stable | 0.5 | 107 | 122 | 141 | 122.6667 | 0.5 | 107 | 122 | 141 | 122.6667 | 0 | 10 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK043 | Project_042_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st December | Person_455 | 2021-03-23 | 2021-05-22 | 0.1 | 2.1306 | 0.53266 | Accept | 0.08 | 2.1306 | 0.53266 | H3 | 3 | Stable | 0.9 | 82 | 139 | 147 | 130.8333 | 0.9 | 82 | 139 | 147 | 130.8333 | 0 | 20 | 1 | 0.6
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK046 | Project_042_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables - June | Person_455 | 2018-11-21 | 2020-11-19 | 0.2 | 49.7149 | 7.4572 | Accept | 0.1 | 49.7149 | 7.4572 | H2 | 4 | Stable | 0.5 | 102 | 127 | 160 | 128.3333 | 0.5 | 102 | 127 | 160 | 128.3333 | 0 | 50 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK023 | Project_042_RISK023 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2018-09-21 | 2019-09-20 | 0.2 | 33.9324 | 6.7865 | Accept | 0.1 | 33.9324 | 6.7865 | H2 | 4 | Stable | 0.9 | 105 | 133 | 141 | 129.6667 | 0.9 | 105 | 133 | 141 | 129.6667 | 0 | 50 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK029 | Project_042_RISK029 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st October to 31st December | Person_455 | 2020-11-20 | 2021-05-22 | 0.25 | 2.2589 | 0.22589 | Accept | 0.1 | 2.2589 | 0.22589 | H2 | 4 | Stable | 0.9 | 111 | 128 | 143 | 127.6667 | 0.9 | 111 | 128 | 143 | 127.6667 | 0 | 60 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK004 | Project_075_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional Material required for investigations | Person_627 | 2017-07-21 | 2018-11-20 01:00 | 0.4 | 3.3748 | 1.3499 | Reduce | 0.1 | 3.3748 | 0.33748 | H3 | 3 | Stable | 0.6 | 80 | 124 | 155 | 121.8333 | 0.2 | 4 | 40 | 77 | 40.1667 | 0 | 75 | 1 | 2.25
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-148 | Project_008_SER-148 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Demands but not provisioned | Person_639 | 2017-08-21 01:00 | 2018-08-21 | 0.3 | 0 | 0 | Accept | 0.3 | 0 | 0 | H3 | 3 | Stable | 0.5 | 98 | 138 | 141 | 131.8333 | 0.5 | 98 | 138 | 141 | 131.8333 |  | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-094 | Project_008_Risk-094 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Consumable Stock Levels | Person_567 | 2017-04-22 | 2018-08-21 | 0.5 | 4.0498 | 2.8349 | Accept | 0.5 | 4.0498 | 2.8349 | H3 | 3 | Stable | 0.5 | 87 | 139 | 144 | 131.1667 | 0.5 | 87 | 139 | 144 | 131.1667 | 0 | 0 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK024 | Project_075_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Failure to meet promised delivery dates | Person_627 | 2017-09-20 01:00 | 2019-01-21 01:00 | 0.5 | 2.5311 | 1.2656 | Reduce | 0.4 | 2.5311 | 1.0124 | H2 | 4 | Stable | 0.7 | 98 | 133 | 159 | 131.5 | 0.1 | 3 | 40 | 75 | 39.6667 | 0 | 20 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-034 | Project_008_SER-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_567 | 2018-05-22 | 2018-08-21 | 0.25 | 5.9059 | 1.7718 | Accept | 0.25 | 5.9059 | 1.7718 | H3 | 3 | Stable | 0.6 | 93 | 126 | 150 | 124.5 | 0.6 | 93 | 126 | 150 | 124.5 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Repairs at Supplier | Person_567 | 2017-08-21 01:00 | 2018-08-21 | 0.15 | 2.0249 | 0.20249 | Accept | 0.15 | 2.0249 | 0.20249 | H3 | 3 | Stable | 0.9 | 118 | 131 | 154 | 132.6667 | 0.9 | 118 | 131 | 154 | 132.6667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK009 | Project_075_RISK009 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Suppliers can't meet timescales. | Person_627 | 2016-12-20 01:00 | 2018-11-20 01:00 | 0.7 | 22.2176 | 15.5523 | Reduce | 0.6 | 6.7497 | 4.0498 | H1 | 5 | Stable | 0.8 | 98 | 138 | 151 | 133.5 | 0.4 | 22 | 43 | 76 | 45 | 69.6202 | 14.2857 | 0 | 41.7721
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK017 | Project_075_RISK017 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | New Materials not tested for Out Gassing | Person_451 | 2017-07-21 | 2018-08-20 | 0.35 | 12.3041 | 4.3064 | Reduce | 0.2 | 12.3041 | 2.4608 | H2 | 4 | Stable | 0.6 | 80 | 134 | 143 | 126.5 | 0.2 | 20 | 43 | 62 | 42.3333 | 0 | 42.8571 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Lack of Spares Availability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 0.2 | 26.0143 | 13.0071 | Accept | 0.2 | 26.0143 | 13.0071 | H3 | 3 | Stable | 0.9 | 88 | 130 | 149 | 126.1667 | 0.9 | 88 | 130 | 149 | 126.1667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK008 | Project_075_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Failures at Acceptance stage | Person_449 | 2017-07-21 | 2019-04-22 | 0.3 | 0.69417 | 0.13883 | Accept | 0.3 | 0.69417 | 0.13883 | H2 | 4 | Stable | 0.5 | 107 | 123 | 150 | 124.8333 | 0.5 | 107 | 123 | 150 | 124.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK007 | Project_075_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Range performance does not meet requirement. | Person_003 | 2017-07-21 | 2018-09-20 01:00 | 0.1 | 0.39514 | 0.079029 | Accept | 0.1 | 0.39514 | 0.079029 | H3 | 3 | Stable | 0.6 | 101 | 130 | 144 | 127.5 | 0.6 | 101 | 130 | 144 | 127.5 | 0 | 0 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK010 | Project_075_RISK010 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | We do not achieve Standard compliant energy over temperature | Person_449 | 2017-07-21 | 2018-09-20 01:00 | 0.5 | 1.1744 | 0.46977 | Accept | 0.5 | 1.1744 | 0.46977 | H1 | 5 | Stable | 0.6 | 112 | 129 | 145 | 128.8333 | 0.6 | 112 | 129 | 145 | 128.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK018 | Project_075_RISK018 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Crystal switch | Person_627 | 2017-03-21 01:00 | 2018-09-20 01:00 | 0.5 | 1.1744 | 0.23489 | Accept | 0.5 | 1.1744 | 0.23489 | H2 | 4 | Stable | 0.8 | 107 | 124 | 147 | 125 | 0.8 | 107 | 124 | 147 | 125 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer find issues with delivered parts or documentation | Person_294 | 2017-05-23 | 2019-08-20 | 0.4 | 19.8087 | 7.9235 | Reduce | 0.25 | 19.8087 | 4.9522 | H2 | 4 | Improving | 0.6 | 114 | 121 | 150 | 124.6667 | 0.3 | 11 | 48 | 61 | 44 | 0 | 37.5 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK002 | Project_058_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence of key parts | Person_236 | 2017-05-23 | 2019-08-07 | 0.5 | 6.7334 | 3.3667 | Reduce | 0.25 | 6.7334 | 1.6833 | H2 | 4 | Stable | 0.9 | 118 | 130 | 157 | 132.5 | 0.1 | 30 | 48 | 77 | 49.8333 | 0 | 50 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK052 | Project_058_RISK052 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | sub-System Cleanliness | Person_294 | 2017-05-23 | 2019-05-23 | 0.75 | 15.9918 | 11.9938 | Reduce | 0.2 | 15.9918 | 3.1984 | H3 | 3 | Stable | 0.5 | 101 | 126 | 143 | 124.6667 | 0.4 | 13 | 50 | 64 | 46.1667 | 0 | 73.3333 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Open PR's | Person_294 | 2018-04-22 | 2018-11-20 01:00 | 0.5 | 7.6338 | 3.8169 | Reduce | 0.3 | 7.6338 | 2.2901 | H3 | 3 | Improving | 0.8 | 90 | 135 | 159 | 131.5 | 0.4 | 14 | 57 | 62 | 50.6667 | 0 | 40 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-O09 | Project_044_Risk-O09 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Lower System housing space | Person_763 | 2018-11-21 | 2019-11-21 | 0.3 | 4.2255 | 1.2677 | Exploit | 0.2 | 4.2255 | 0.84511 | H3 | 3 | Stable | [10 empty] | 0 | 33.3333 | 1 | 1
2018-06-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R008 | Project_044_Risk-R008 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Engineering Skills | Person_505 | 2017-10-21 | 2018-10-22 | 0.2 | 1.5695 | 0.3139 | Reduce | 0.1 | 1.2073 | 0.12073 | H3 | 3 | Stable | 0.6 | 92 | 139 | 159 | 134.5 | 0.3 | 19 | 46 | 79 | 47 | 23.0769 | 50 | 1 | 15.3461
2018-06-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R018 | Project_044_Risk-R018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | EMC (susceptibility) | Person_763 | 2016-03-23 | 2019-05-23 | 0.5 | 5.795 | 2.8975 | Reduce | 0.1 | 5.795 | 0.5795 | H3 | 3 | Stable | 0.7 | 82 | 130 | 143 | 124.1667 | 0.1 | 31 | 51 | 72 | 51.1667 | 0 | 80 | 1 | 2.4
2018-06-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R001 | Project_044_Risk-R001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | subsystem1 development | Person_358 | 2017-12-22 | 2019-11-20 | 0.2 | 20.8621 | 4.1724 | Reduce | 0.15 | 20.8621 | 3.1293 | H2 | 4 | Stable | 0.8 | 94 | 131 | 160 | 129.6667 | 0.1 | 8 | 43 | 75 | 42.5 | 0 | 25 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R023 | Project_044_Risk-R023 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Integrated performance | Person_358 | 2017-12-15 | 2020-10-21 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 107 | 137 | 153 | 134.6667 | 0.4 | 10 | 40 | 79 | 41.5 |  | 40 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R010 | Project_044_Risk-R010 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Line of sight | Person_763 | 2017-11-20 | 2018-06-22 | 0.7 | 4.2255 | 2.9579 | -- | 0.2 | 4.2255 | 0.84511 | H3 | 3 | Stable | [10 empty] | 0 | 71.4286 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R026 | Project_044_Risk-R026 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Component position | Person_763 | 2017-11-20 | 2018-11-20 | 0.2 | 4.2255 | 0.84511 | Reduce | 0.1 | 4.2255 | 0.42255 | H3 | 3 | Stable | 0.7 | 89 | 138 | 141 | 130.3333 | 0.1 | 25 | 48 | 64 | 46.8333 | 0 | 50 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R003 | Project_044_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Mono vs stereo Component | Person_358 | 2018-01-19 | 2018-10-22 | 0.4 | 20.8621 | 8.3448 | Reduce | 0.2 | 20.8621 | 4.1724 | H3 | 3 | Stable | 0.6 | 110 | 123 | 154 | 126 | 0.3 | 13 | 53 | 73 | 49.6667 | 0 | 50 | 1 | 1.5
2018-06-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R025 | Project_044_Risk-R025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence | Person_763 | 2017-11-20 | 2019-05-22 | 0.3 | 3.0182 | 0.90547 | Reduce | 0.1 | 1.2073 | 0.12073 | H3 | 3 | Stable | 0.5 | 115 | 135 | 155 | 135 | 0.3 | 34 | 44 | 61 | 45.1667 | 60 | 66.6667 | 1 | 38
2018-06-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R002 | Project_044_Risk-R002 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Parts changing post ordering | Person_310 | 2018-01-20 | 2019-05-22 | 0.9 | 0 | 0 | -- | 0.9 | 0 | 0 | H1 | 5 | Stable | [11 empty] | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R092 | Project_044_Risk-R092 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Downstream Integration changes | Person_358 | 2018-11-21 | 2019-11-21 | 0.3 | 0 | 0 | -- | 0.2 | 4.2255 | 0.84511 | H3 | 3 | Stable | [10 empty] | -inf | 33.3333 | 1 | -inf
2018-06-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R091 | Project_044_Risk-R091 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Receive System Performance | Person_763 | 2017-11-20 | 2018-11-21 | 0.5 | 4.2255 | 2.1128 | Reduce | 0.2 | 4.2255 | 0.84511 | H3 | 3 | Stable | 0.8 | 112 | 135 | 149 | 133.5 | 0.4 | 32 | 50 | 78 | 51.6667 | 0 | 60 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R090 | Project_044_Risk-R090 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Gain and noise measurements | Person_763 | 2017-11-20 | 2019-05-23 | 0.5 | 4.2255 | 2.1128 | -- | 0.2 | 4.2255 | 0.84511 | H3 | 3 | Stable | [10 empty] | 0 | 60 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R005 | Project_044_Risk-R005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | CE Marking | Person_763 | 2018-01-20 | 2018-11-05 | 0.3 | 2.1128 | 0.63383 | Reduce | 0.1 | 1.2073 | 0.12073 | H3 | 3 | Stable | 0.7 | 105 | 138 | 150 | 134.5 | 0.2 | 18 | 54 | 76 | 51.6667 | 42.8571 | 66.6667 | 1 | 27.7143
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--16 | Project_021_Risk--16 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of weather | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.6 | 97 | 131 | 151 | 128.6667 | 0.1 | 2 | 54 | 77 | 49.1667 |  | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--15 | Project_021_Risk--15 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to lack of personnel resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.4 | 0 | 0 | H2 | 4 | Stable | 0.8 | 89 | 136 | 153 | 131 | 0.3 | 4 | 55 | 68 | 48.6667 |  | 20 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--14 | Project_021_Risk--14 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to late Trials Approval | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.9 | 109 | 129 | 158 | 130.5 | 0.1 | 37 | 55 | 76 | 55.5 |  | 66.6667 | 1
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--13 | Project_021_Risk--13 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Critical or Safety PR arises in Final build /Decision Point concludes new release req | Person_174 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.9 | 90 | 130 | 156 | 127.6667 | 0.3 | 19 | 41 | 68 | 41.8333 | 0 | 50 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--12 | Project_021_Risk--12 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.5 | 81 | 125 | 154 | 122.5 | 0.1 | 9 | 58 | 66 | 51.1667 | 0 | 33.3333 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--10 | Project_021_Risk--10 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Stable | 0.5 | 105 | 130 | 143 | 128 | 0.1 | 30 | 49 | 78 | 50.6667 | 0 | 57.1429 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--32 | Project_021_Risk--32 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Lack of Customer resource to provide timely input to Acceptance and Closure activities | Person_766 | 2018-10-22 01:00 | 2019-04-23 | 0.8 | 0 | 0 | Reduce | 0.4 | 0 | 0 | H2 | 4 | Stable | 0.9 | 112 | 123 | 148 | 125.3333 | 0.3 | 10 | 54 | 63 | 48.1667 |  | 50 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--18 | Project_021_Risk--18 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.6 | 110 | 123 | 157 | 126.5 | 0.3 | 10 | 54 | 64 | 48.3333 | 50 | 28.5714 | 0 | 30
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--28 | Project_021_Risk--28 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort required to agree protocl for Client Server | Person_766 | 2018-03-23 | 2019-03-23 | 0.8 | 1.1522 | 0.92174 | Reduce | 0.4 | 1.1522 | 0.46087 | H2 | 4 | Stable | 0.9 | 81 | 130 | 158 | 126.5 | 0.4 | 19 | 45 | 61 | 43.3333 | 0 | 50 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--05 | Project_021_Risk--05 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification delays | Person_207 | 2018-02-20 01:00 | 2018-10-05 01:00 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.6 | 117 | 128 | 156 | 130.8333 | 0.3 | 34 | 53 | 60 | 51 |  | 50 | 1
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--04 | Project_021_Risk--04 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Final Qual test report delayed due to insufficient supply chain resource | Person_615 | 2018-09-20 01:00 | 2018-10-21 01:00 | 0.2 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.6 | 100 | 132 | 153 | 130.1667 | 0.1 | 30 | 53 | 61 | 50.5 |  | 50 | 1
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--03 | Project_021_Risk--03 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.9 | 91 | 134 | 159 | 131 | 0.4 | 7 | 51 | 70 | 46.8333 | 0 | 33.3333 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--25 | Project_021_Risk--25 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of supporting resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.7 | 115 | 123 | 156 | 127.1667 | 0.3 | 3 | 54 | 63 | 47 |  | 40 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--02 | Project_021_Risk--02 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_061 | 2018-02-20 01:00 | 2019-03-23 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.9 | 96 | 136 | 147 | 131.1667 | 0.2 | 37 | 44 | 76 | 48.1667 | 80 | 66.6667 | 0 | 48
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--24 | Project_021_Risk--24 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of equipment | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 103 | 121 | 150 | 122.8333 | 0.3 | 10 | 41 | 61 | 39.1667 |  | 40 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--21 | Project_021_Risk--21 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 94 | 126 | 145 | 123.8333 | 0.2 | 21 | 53 | 70 | 50.5 |  | 40 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--09 | Project_021_Risk--09 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_470 | 2018-02-20 01:00 | 2018-08-21 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 97 | 132 | 154 | 129.8333 | 0.1 | 33 | 59 | 65 | 55.6667 |  | 40 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--08 | Project_021_Risk--08 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-02-20 01:00 | 2018-10-05 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 97 | 137 | 145 | 131.6667 | 0.3 | 14 | 59 | 79 | 54.8333 |  | 40 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--07 | Project_021_Risk--07 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 0.6 | 17.2826 | 10.3696 | Reduce | 0.3 | 17.2826 | 5.1848 | H2 | 4 | Worsening | 0.9 | 114 | 130 | 159 | 132.1667 | 0.1 | 36 | 41 | 70 | 45 | 0 | 50 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--17 | Project_021_Risk--17 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delays due to technical performacne | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.9 | 89 | 129 | 154 | 126.5 | 0.4 | 2 | 50 | 76 | 46.3333 |  | 33.3333 | 1
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--39 | Project_021_Risk--39 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Delay to completion of product upgrade | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.7 | 109 | 140 | 145 | 135.6667 | 0.1 | 23 | 53 | 66 | 50.1667 |  | 40 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R022 | Project_044_Risk-R022 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Shock Requirement | Person_763 | 2018-11-20 | 2019-05-23 | 0.1 | 1.7748 | 0.4437 | Accept | 0.1 | 1.7748 | 0.4437 | H3 | 3 | Stable | 0.8 | 86 | 134 | 151 | 128.8333 | 0.8 | 86 | 134 | 151 | 128.8333 | 0 | 0 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier Selection Process | Person_379 | 2017-10-19 | 2019-04-23 | 0.4 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 106 | 128 | 149 | 127.8333 | 0.4 | 24 | 57 | 71 | 53.8333 |  | 25 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Colour Representation in Video Image Distortion | Person_305 | 2017-09-22 | 2019-11-28 | 0.5 | 5.5323 | 2.7662 | Reduce | 0.1 | 5.5323 | 0.55323 | H3 | 3 | Stable | 0.6 | 87 | 138 | 152 | 131.8333 | 0.1 | 19 | 48 | 64 | 45.8333 | 0 | 80 | 1 | 2.4
2018-06-23 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R024 | Project_044_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Receiver System Performance | Person_763 | 2017-11-20 | 2019-11-21 | 0.2 | 3.4651 | 1.0395 | Accept | 0.2 | 3.4651 | 1.0395 | H3 | 3 | Stable | 0.9 | 113 | 132 | 149 | 131.6667 | 0.9 | 113 | 132 | 149 | 131.6667 | 0 | 0 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-21 | 2018-07-20 | 0.5 | 28.0275 | 14.0137 | Reduce | 0.1 | 28.0275 | 2.8027 | H3 | 3 | Stable | 0.5 | 91 | 125 | 154 | 124.1667 | 0.3 | 10 | 45 | 72 | 43.6667 | 0 | 80 | 1 | 2.4
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--35 | Project_021_Risk--35 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Delay to sub-system and other Components - dependencies due to supply chain dependencies | Person_615 | 2018-01-21 01:00 | 2018-03-22 | 0.4 | 3.2479 | 0.64958 | Accept | 0.4 | 3.2479 | 0.64958 | H2 | 4 | Stable | 0.9 | 116 | 135 | 156 | 135.3333 | 0.9 | 116 | 135 | 156 | 135.3333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-21 | 0.8 | 35.2369 | 28.1895 | Reduce | 0.3 | 18.4979 | 5.5494 | H2 | 4 | Stable | 0.8 | 85 | 121 | 158 | 121.1667 | 0.2 | 11 | 45 | 78 | 44.8333 | 47.5042 | 62.5 | 0 | 28.5025
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--34 | Project_021_Risk--34 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Delay due to poor weather | Person_615 | 2018-03-23 | 2018-10-21 01:00 | 0.5 | 3.5496 | 1.0649 | Accept | 0.5 | 3.5496 | 1.0649 | H2 | 4 | Stable | 0.8 | 90 | 126 | 160 | 125.6667 | 0.8 | 90 | 126 | 160 | 125.6667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 4 | 9. Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-21 | 0.7 | 20.6835 | 14.4785 | Reduce | 0.3 | 20.6835 | 6.2051 | H2 | 4 | Stable | 0.5 | 102 | 139 | 149 | 134.5 | 0.3 | 25 | 58 | 64 | 53.5 | 0 | 57.1429 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--27 | Project_021_Risk--27 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PR rectification | Person_207 | 2018-02-20 01:00 | 2018-11-05 01:00 | 0.1 | 8.0289 | 0.80289 | Accept | 0.1 | 2.5354 | 0.25354 | H2 | 4 | Stable | 0.5 | 85 | 139 | 144 | 130.8333 | 0.5 | 85 | 139 | 144 | 130.8333 | 68.421 | 0 | 0 | 41.0526
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 4 | 8. System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 0.6 | 5.2585 | 3.1551 | Reduce | 0.15 | 5.2585 | 0.78877 | H2 | 4 | Stable | 0.7 | 120 | 130 | 147 | 131.1667 | 0.4 | 10 | 41 | 78 | 42 | 0 | 75 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-07-21 | 0.3 | 2.723 | 0.81691 | Reduce | 0.1 | 2.723 | 0.2723 | H3 | 3 | Improving | 0.5 | 81 | 131 | 144 | 124.8333 | 0.4 | 39 | 59 | 63 | 56.3333 | 0 | 66.6667 | 1 | 2
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.9 | 85 | 137 | 149 | 130.3333 | 0.4 | 29 | 40 | 62 | 41.8333 | 60.3671 | 58.3333 | 0 | 36.2202
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-08 | 2020-09-21 | 0.3 | 4.8444 | 1.4533 | Reduce | 0.2 | 4.8444 | 0.96888 | H3 | 3 | Stable | 0.7 | 102 | 136 | 158 | 134 | 0.2 | 9 | 57 | 70 | 51.1667 | 0 | 33.3333 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System Performance | Person_305 | 2016-09-08 | 2020-09-21 | 0.3 | 5.8725 | 1.7618 | Reduce | 0.1 | 5.8725 | 0.58725 | H2 | 4 | Stable | 0.5 | 113 | 121 | 149 | 124.3333 | 0.4 | 1 | 42 | 67 | 39.3333 | 0 | 66.6667 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_572 | 2020-05-23 | 2023-10-26 | 0.2 | 7.4599 | 1.492 | Reduce | 0.05 | 7.4599 | 0.37299 | H2 | 4 | Stable | 0.9 | 105 | 132 | 154 | 131.1667 | 0.4 | 20 | 53 | 65 | 49.5 | 0 | 75 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-29 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.7 | 89 | 135 | 143 | 128.6667 | 0.4 | 24 | 47 | 64 | 46 | 60.3671 | 58.3333 | 0 | 36.2202
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-20 | 0.4 | 2.8643 | 1.1457 | Reduce | 0.1 | 2.8643 | 0.28643 | H3 | 3 | Stable | 0.8 | 99 | 133 | 152 | 130.5 | 0.1 | 21 | 56 | 66 | 51.8333 | 0.0015933 | 75 | 1 | 2.251
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power Supply - Motor Controller Interface | Person_179 | 2016-05-23 | 2018-09-19 | 0.5 | 25.3543 | 12.6771 | Reduce | 0.2 | 25.3543 | 5.0709 | H3 | 3 | Stable | 0.7 | 82 | 136 | 156 | 130.3333 | 0.1 | 37 | 44 | 67 | 46.6667 | 0 | 60 | 1 | 1.8
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-08 | 2020-09-21 | 0.1 | 12.7232 | 1.2723 | Reduce | 0.1 | 12.7232 | 1.2723 | H3 | 3 | Stable | 0.8 | 86 | 134 | 149 | 128.5 | 0.1 | 30 | 56 | 61 | 52.5 | 0 | 0 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | EMC non compliance | Person_047 | 2023-05-24 | 2023-12-01 | 0.7 | 3.935 | 2.7545 | Reduce | 0.5 | 3.935 | 1.9675 | H2 | 4 | Stable | 0.7 | 86 | 134 | 141 | 127.1667 | 0.1 | 8 | 55 | 66 | 49 | 0 | 28.5714 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SubSystem System Design | Person_038 | 2017-10-01 | 2019-11-20 | 0.2 | 1.5213 | 0.30425 | Reduce | 0.1 | 1.5213 | 0.15213 | H3 | 3 | Stable | 0.6 | 99 | 137 | 157 | 134 | 0.4 | 16 | 50 | 74 | 48.3333 | 0 | 50 | 1 | 1.5
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-21 | 2023-12-22 | 0.4 | 30.1969 | 12.0788 | Reduce | 0.25 | 30.1969 | 7.5492 | H2 | 4 | Stable | 0.5 | 88 | 138 | 151 | 131.8333 | 0.4 | 9 | 53 | 62 | 47.1667 | 0 | 37.5 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | In-house development of sub-system estimate is low | Person_418 | 2016-03-23 | 2018-06-06 | 0.5 | 6.5118 | 3.2559 | Reduce | 0.2 | 1.506 | 0.30121 | H3 | 3 | Stable | 0.8 | 95 | 137 | 143 | 131 | 0.2 | 21 | 57 | 75 | 54 | 76.8722 | 60 | 0 | 46.1233
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-10-20 | 0.4 | 1.0142 | 0.40567 | Reduce | 0.1 | 1.0142 | 0.10142 | H3 | 3 | Stable | 0.9 | 105 | 127 | 142 | 125.8333 | 0.2 | 14 | 51 | 75 | 48.8333 | 0 | 75 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | 9. Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 0.8 | 19.1678 | 15.3343 | Reduce | 0.2 | 2.8752 | 0.57503 | H3 | 3 | Stable | 0.6 | 90 | 127 | 158 | 126 | 0.3 | 16 | 45 | 69 | 44.1667 | 85 | 75 | 0 | 51
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 0.25 | 0.63626 | 0.15906 | Reduce | 0.05 | 0.63626 | 0.031813 | H3 | 3 | Stable | 0.7 | 94 | 121 | 148 | 121 | 0.3 | 25 | 48 | 79 | 49.3333 | 0 | 80 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Component Shock test failure | Person_020 | 2016-09-08 | 2019-11-15 | 0.4 | 0.8467 | 0.33868 | Reduce | 0.2 | 0.8467 | 0.16934 | H3 | 3 | Stable | 0.5 | 105 | 131 | 141 | 128.3333 | 0.1 | 31 | 59 | 74 | 56.8333 | 0 | 50 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-06 | 2019-09-13 | 0.8 | 8.0322 | 6.4258 | Reduce | 0.5 | 4.006 | 2.003 | H2 | 4 | Stable | 0.7 | 113 | 124 | 143 | 125.3333 | 0.1 | 29 | 55 | 72 | 53.5 | 50.1263 | 37.5 | 0 | 30.0758
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-04-22 | 0.8 | 18.0459 | 14.4367 | Reduce | 0.2 | 3.0076 | 0.60153 | H3 | 3 | Stable | 0.9 | 89 | 134 | 157 | 130.3333 | 0.3 | 13 | 57 | 72 | 52.1667 | 83.3335 | 75 | 1 | 52.2501
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 0.4 | 5.1004 | 2.0402 | Reduce | 0.2 | 2.5506 | 0.51013 | H3 | 3 | Stable | 0.6 | 90 | 129 | 158 | 127.3333 | 0.1 | 12 | 51 | 74 | 48.3333 | 49.9917 | 50 | 0 | 29.995
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-22 01:00 | 2019-08-21 01:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-22 01:00 | 2019-08-21 01:00 | 0.5 | 3.3188 | 1.6594 | Avoid | 0.5 | 3.3188 | 1.6594 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK004 | Project_079_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 8.8685 | 1.7737 | Reduce | 0.15 | 8.8685 | 1.3303 | H3 | 3 | Stable | 0.6 | 104 | 139 | 154 | 135.6667 | 0.3 | 12 | 51 | 65 | 46.8333 | 0 | 25 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK026 | Project_079_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Clause on Joint Proposal | Person_261 | 2018-05-04 | 2019-05-23 | 0.4 | 30.653 | 12.2612 | -- | 0.4 | 30.653 | 12.2612 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK014 | Project_079_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 0.05 | 21.725 | 1.0862 | Reduce | 0.05 | 21.725 | 1.0862 | H3 | 3 | Stable | 0.5 | 83 | 128 | 151 | 124.3333 | 0.1 | 34 | 45 | 67 | 46.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK005 | Project_079_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 3.7631 | 2.2578 | -- | 0.5 | 3.7631 | 1.8815 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK016 | Project_079_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 0.8 | 1.9552 | 1.5642 | Avoid | 0.2 | 1.9552 | 0.39105 | H3 | 3 | Stable | [10 empty] | 0 | 75 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK022 | Project_079_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Equipment | Person_104 | 2018-01-14 01:00 | 2019-08-20 | 0.15 | 7.321 | 1.0982 | Reduce | 0.15 | 7.321 | 1.0982 | H3 | 3 | Stable | 0.6 | 106 | 130 | 153 | 129.8333 | 0.4 | 3 | 59 | 64 | 50.5 | 0 | 0 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK002 | Project_079_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2022-05-22 | 0.15 | 26.7842 | 4.0176 | Avoid | 0.15 | 26.7842 | 4.0176 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK024 | Project_079_RISK024 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Procurement/Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 0.5 | 14.4992 | 7.2496 | -- | 0.8 | 0 | 0 | H1 | 5 | Stable | [10 empty] | 100 | -60 | 0 | 60
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 0.3 | 31.4106 | 15.7053 | Accept | 0.3 | 31.4106 | 15.7053 | H3 | 3 | Stable | 0.8 | 116 | 132 | 154 | 133 | 0.8 | 116 | 132 | 154 | 133 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-115 | Project_011_Risk-115 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | SMEs are unavailable to support project activites | Person_431 | 2016-07-21 | 2018-10-21 01:00 | 0.2 | 0 | 0 | Avoid | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 50 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-058 | Project_011_Risk-058 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme delays | Person_147 | 2013-11-20 01:00 | 2019-01-20 01:00 | 0.25 | 1.5013 | 0.37532 | Reduce | 0.4 | 1.5013 | 0.60051 | H1 | 5 | Stable | 0.7 | 82 | 139 | 159 | 132.8333 | 0.1 | 14 | 51 | 71 | 48.1667 | 0 | -60 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-131 | Project_011_Risk-131 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Support team have not covered all obligations in support contract | Person_147 | 2016-05-24 | 2018-10-21 01:00 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-137 | Project_011_Risk-137 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Subsystem will not match Fidelity of Customer - does not accept | Person_147 | 2018-02-16 01:00 | 2018-09-20 01:00 | 0.4 | 0.11876 | 0.047505 | Avoid | 0.2 | 0.11876 | 0.023752 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2018-04-22 | 2019-01-20 01:00 | 0.2 | 0.62279 | 0.12456 | Avoid | 0.2 | 0.62279 | 0.12456 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-09-20 01:00 | 0.1 | 1.8854 | 0.18854 | Reduce | 0.1 | 1.8854 | 0.18854 | H3 | 3 | Stable | 0.6 | 98 | 125 | 153 | 125.1667 | 0.1 | 18 | 42 | 77 | 43.8333 | 0 | 0 | 1 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2018-06-23 | 2019-01-20 01:00 | 0.4 | 1.4138 | 0.56551 | Reduce | 0.5 | 1.4138 | 0.70689 | H1 | 5 | Stable | 0.6 | 105 | 137 | 160 | 135.5 | 0.4 | 31 | 43 | 67 | 45 | 0 | -25 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-10-21 01:00 | 0.2 | 0.19206 | 0.038413 | -- | 0.2 | 0.19206 | 0.038413 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-08-22 01:00 | 2018-11-20 01:00 | 0.4 | 0.58017 | 0.23207 | Avoid | 0.4 | 0.58017 | 0.23207 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-11-20 01:00 | 0.3 | 0.32389 | 0.097168 | Reduce | 0.3 | 0.32389 | 0.097168 | H2 | 4 | Stable | 0.5 | 118 | 134 | 159 | 135.5 | 0.4 | 12 | 44 | 68 | 42.6667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures during SAT | Person_182 | 2018-06-23 | 2018-10-21 01:00 | 0.2 | 0.19206 | 0.038413 | -- | 0.2 | 0.19206 | 0.038413 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_431 | 2017-05-24 | 2018-09-19 01:00 | 0.3 | 0.11933 | 0.035799 | -- | 0.3 | 0.022161 | 0.0066484 | H3 | 3 | Stable | [10 empty] | 81.4286 | 0 | 0 | 48.8571
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-117 | Project_011_Risk-117 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Avaliability for testing/reviews | Person_147 | 2018-04-06 | 2018-10-21 01:00 | 0.35 | 0 | 0 | Avoid | 0.35 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-129 | Project_011_Risk-129 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Signature of Work Authorisation documents | Person_422 | 2017-05-24 | 2018-09-18 01:00 | 0.4 | 0.12643 | 0.050573 | -- | 0.4 | 0.12643 | 0.050573 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Regulatory standards changes misunderstood | Person_693 | 2018-03-23 | 2018-07-21 | 0.5 | 1.3377 | 0.66883 | Reduce | 0.25 | 1.3377 | 0.33441 | H2 | 4 | Stable | 0.6 | 93 | 132 | 147 | 128 | 0.3 | 32 | 46 | 79 | 49.1667 | 0 | 50 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Unforseen and substantial increase in Repairs workload during new build production period. | Person_547 | 2017-10-23 | 2019-08-21 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.25 | 1.5434 | 0.38586 | H2 | 4 | Stable | 0.6 | 97 | 135 | 153 | 131.6667 | 0.3 | 25 | 40 | 71 | 42.6667 | 0 | 16.6667 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK007 | Project_041_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Advanced production of products using a Qual. standard component rather than a Prod. standard | Person_547 | 2017-10-21 | 2019-02-20 | 0.49 | 1.2862 | 0.63024 | Reduce | 0.2 | 1.2862 | 0.25724 | H3 | 3 | Stable | 0.6 | 112 | 129 | 145 | 128.8333 | 0.4 | 12 | 58 | 77 | 53.5 | 0 | 59.1837 | 1 | 1.7755
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Unreliability of Hardware | Person_431 | 2016-06-23 | 2018-10-21 01:00 | 0.1 | 1.9722 | 0.98609 | Accept | 0.1 | 1.9722 | 0.98609 | H3 | 3 | Stable | 0.7 | 108 | 139 | 160 | 137.3333 | 0.7 | 108 | 139 | 160 | 137.3333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_147 | 2016-04-21 | 2018-10-21 01:00 | 0.25 | 1.7492 | 0.17492 | Accept | 0.25 | 1.7492 | 0.17492 | H3 | 3 | Stable | 0.5 | 96 | 128 | 154 | 127 | 0.5 | 96 | 128 | 154 | 127 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK011 | Project_041_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Supplier Development support | Person_693 | 2018-04-11 | 2018-07-21 | 0.5 | 2.5081 | 1.2541 | Accept | 0.332 | 2.5081 | 1.2541 | H2 | 4 | Stable | 0.9 | 117 | 132 | 144 | 131.5 | 0.9 | 117 | 132 | 144 | 131.5 | 0 | 33.6 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK010 | Project_041_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Digital Assembly - Testing | Person_547 | 2018-04-11 | 2018-08-20 | 0.15 | 0.55736 | 0.083603 | Accept | 0.1 | 0.55736 | 0.055736 | H3 | 3 | Improving | 0.9 | 82 | 133 | 149 | 127.1667 | 0.9 | 82 | 133 | 149 | 127.1667 | 0 | 33.3333 | 1 | 1
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK013 | Project_041_RISK013 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional components validation | Person_693 | 2017-07-15 | 2018-09-20 | 0.4 | 2.358 | 0.58951 | Accept | 0.3 | 2.358 | 0.45274 | H2 | 4 | Stable | 0.8 | 118 | 135 | 148 | 134.3333 | 0.8 | 118 | 135 | 148 | 134.3333 | 0 | 25 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK004 | Project_081_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Greater number of failures/ investigations | Person_260 | 2017-09-27 01:00 | 2021-09-27 01:00 | 0.6 | 2.685 | 1.611 | Reduce | 0.6 | 2.685 | 1.611 | H3 | 3 | Worsening | 0.8 | 81 | 125 | 148 | 121.5 | 0.4 | 24 | 43 | 79 | 45.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK003 | Project_081_RISK003 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Export control issues taking longer to resolve | Person_260 | 2017-09-27 01:00 | 2021-09-27 01:00 | 0.2 | 1.5256 | 0.30511 | Reduce | 0.2 | 1.5256 | 0.30511 | H3 | 3 | Stable | 0.7 | 103 | 139 | 156 | 135.8333 | 0.4 | 6 | 51 | 70 | 46.6667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK006 | Project_081_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Large volume of repairs loaded to clear backlog | Person_260 | 2017-09-27 01:00 | 2021-09-27 01:00 | 0.25 | 3.1854 | 0.79634 | Reduce | 0.25 | 3.1854 | 0.79634 | H3 | 3 | Worsening | 0.7 | 83 | 125 | 159 | 123.6667 | 0.3 | 5 | 59 | 79 | 53.3333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK005 | Project_081_RISK005 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Marching army Customer costs for duration of contract | Person_260 | 2021-05-23 | 2021-09-27 01:00 | 0.2 | 1.6598 | 0.33196 | Reduce | 0.2 | 1.6598 | 0.33196 | H3 | 3 | Stable | 0.8 | 92 | 133 | 145 | 128.1667 | 0.2 | 12 | 47 | 71 | 45.1667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK021 | Project_081_RISK021 | Threat | Financial Contingency | Open | H3 | 3 | 7. Finance | Increase of bank fees and other direct costs | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.15 | 2.27 | 0.3405 | Avoid | 0.15 | 2.27 | 0.3405 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK024 | Project_081_RISK024 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer- Training | Person_115 | 2017-09-27 01:00 | 2021-11-27 01:00 | 0.6 | 1.3425 | 0.80549 | Reduce | 0.6 | 1.3425 | 0.80549 | H3 | 3 | Stable | 0.7 | 118 | 134 | 146 | 133.3333 | 0.1 | 21 | 43 | 64 | 42.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK002 | Project_081_RISK002 | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Supplier costs to be covered by us | Person_260 | 2017-09-27 01:00 | 2021-09-20 01:00 | 0.2 | 2.0381 | 0.40763 | Reduce | 0.2 | 2.0381 | 0.40763 | H3 | 3 | Stable | 0.9 | 87 | 138 | 158 | 132.8333 | 0.4 | 13 | 57 | 66 | 51.1667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK023 | Project_081_RISK023 | Threat | Project Contingency | Open | H3 | 3 | 7. Finance | Risk of funding requirement | Person_115 | 2017-09-27 01:00 | 2021-09-27 01:00 | 0.6 | 1.7696 | 1.0618 | Reduce | 0.6 | 1.7696 | 1.0618 | H3 | 3 | Stable | 0.7 | 97 | 122 | 146 | 121.8333 | 0.2 | 13 | 56 | 71 | 51.3333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK001 | Project_081_RISK001 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | Increase in Support Management | Person_260 | 2017-07-21 | 2021-07-21 | 0.4 | 2.0381 | 0.81526 | Reduce | 0.4 | 2.0381 | 0.81526 | H3 | 3 | Stable | 0.5 | 81 | 132 | 145 | 125.6667 | 0.1 | 14 | 51 | 68 | 47.6667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK008 | Project_081_RISK008 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Failure to meet repair turnaround time | Person_260 | 2017-09-27 01:00 | 2021-09-20 01:00 | 0.1 | 1.5866 | 0.15866 | Reduce | 0.1 | 1.5866 | 0.15866 | H3 | 3 | Stable | 0.8 | 100 | 134 | 152 | 131.3333 | 0.3 | 5 | 56 | 72 | 50.1667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK007 | Project_081_RISK007 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | High value supplier repair/replacements required | Person_260 | 2017-09-27 01:00 | 2021-09-20 01:00 | 0.4 | 3.7834 | 1.5133 | Reduce | 0.4 | 3.7834 | 1.5133 | H3 | 3 | Stable | 0.6 | 105 | 122 | 146 | 123.1667 | 0.4 | 39 | 59 | 63 | 56.3333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK009 | Project_081_RISK009 | Threat | Management Contingency | Open | H2 | 4 | 7. Finance | Increase of Spares UPCs | Person_260 | 2017-09-27 01:00 | 2019-09-28 01:00 | 0.2 | 17.5011 | 3.5002 | Reduce | 0.2 | 17.5011 | 3.5002 | H3 | 3 | Stable | 0.5 | 111 | 138 | 142 | 134.1667 | 0.1 | 4 | 52 | 73 | 47.5 | 0 | 0 | 1 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP002 | Project_081_OPP002 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Core Management team shared across other programmes | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.3 | 0.91533 | 0.2746 | -- | 0.3 | 0.91533 | 0.2746 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP001 | Project_081_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 7. Finance | Reduction in Spares UPC | Person_260 | 2017-07-21 | 2021-07-21 | 0.2 | 6.1022 | 1.2204 | -- | 0.2 | 6.1022 | 1.2204 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP004 | Project_081_OPP004 | Opportunitity | Project Contingency | Open | H3 | 3 | 7. Finance | Less repairs than planned in base costs | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.2 | 1.2204 | 0.24409 | -- | 0.2 | 1.2204 | 0.24409 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP003 | Project_081_OPP003 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Supplier abilities mature exponentially throughout contract requiring less FSE support | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.25 | 1.8307 | 0.45767 | -- | 0.25 | 1.8307 | 0.45767 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK015 | Project_081_RISK015 | Threat | Management Contingency | Open | H3 | 3 | 7. Finance | Our being liable for freight costs. | Person_260 | 2018-03-23 | 2021-09-20 01:00 | 0.3 | 3.0511 | 0.91533 | Reduce | 0.3 | 3.0511 | 0.91533 | H3 | 3 | Stable | 0.8 | 116 | 129 | 147 | 129.8333 | 0.1 | 39 | 54 | 67 | 53.6667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK014 | Project_081_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 7. Finance | Supplier request financial support for Training admin. | Person_260 | 2018-02-20 01:00 | 2021-09-20 01:00 | 0.1 | 0.50038 | 0.050038 | Reduce | 0.1 | 0.50038 | 0.050038 | H3 | 3 | Stable | 0.5 | 103 | 132 | 152 | 130.5 | 0.2 | 5 | 56 | 76 | 50.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK017 | Project_081_RISK017 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Extended working hours during site visits | Person_419 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.3 | 1.1716 | 0.35149 | Reduce | 0.3 | 1.1716 | 0.35149 | H3 | 3 | Stable | 0.5 | 116 | 135 | 157 | 135.5 | 0.3 | 10 | 58 | 69 | 51.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK016 | Project_081_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Additional visit support requested by Customer/Supplier | Person_260 | 2017-10-21 01:00 | 2021-09-20 01:00 | 0.4 | 2.331 | 0.93242 | Reduce | 0.4 | 2.331 | 0.93242 | H3 | 3 | Stable | 0.8 | 90 | 129 | 147 | 125.5 | 0.1 | 8 | 53 | 70 | 48.3333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK011 | Project_081_RISK011 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Additional quantities of spares/material/STTE requested by customer | Person_260 | 2017-07-21 | 2019-07-22 | 0.1 | 6.3707 | 0.63707 | Reduce | 0.1 | 6.3707 | 0.63707 | H3 | 3 | Stable | 0.7 | 87 | 126 | 144 | 122.5 | 0.2 | 18 | 54 | 65 | 49.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK010 | Project_081_RISK010 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Increased material lead times for Spares | Person_649 | 2017-09-27 01:00 | 2019-09-28 01:00 | 0.1 | 6.3707 | 0.63707 | Reduce | 0.1 | 6.3707 | 0.63707 | H3 | 3 | Worsening | 0.8 | 117 | 126 | 154 | 129.1667 | 0.3 | 32 | 46 | 79 | 49.1667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK013 | Project_081_RISK013 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Additional training requested by customer. | Person_419 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.15 | 0.50038 | 0.075057 | Reduce | 0.15 | 0.50038 | 0.075057 | H3 | 3 | Stable | 0.5 | 115 | 125 | 156 | 128.5 | 0.2 | 24 | 44 | 67 | 44.5 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK012 | Project_081_RISK012 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Supplier unable to deliver course without our input | Person_260 | 2017-09-27 01:00 | 2021-09-27 01:00 | 0.5 | 0.50038 | 0.25019 | Reduce | 0.5 | 0.50038 | 0.25019 | H3 | 3 | Stable | 0.5 | 109 | 126 | 147 | 126.6667 | 0.3 | 3 | 53 | 60 | 45.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK019 | Project_081_RISK019 | Threat | Management Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Misc costs incurred at trials | Person_260 | 2018-05-23 | 2021-09-20 01:00 | 0.2 | 1.3425 | 0.2685 | Avoid | 0.2 | 1.3425 | 0.2685 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK018 | Project_081_RISK018 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Additional trials support requested (+3) | Person_260 | 2018-05-23 | 2021-07-21 | 0.2 | 2.0259 | 0.40519 | Reduce | 0.2 | 2.0259 | 0.40519 | H3 | 3 | Stable | 0.6 | 115 | 123 | 157 | 127.3333 | 0.2 | 37 | 54 | 62 | 52.5 | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK020 | Project_081_RISK020 | Threat | Project Contingency | Open | H3 | 3 | 7. Finance | Travel Cost Increases | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.3 | 1.8307 | 0.5492 | Reduce | 0.3 | 1.8307 | 0.5492 | H3 | 3 | Stable | 0.6 | 87 | 121 | 153 | 120.6667 | 0.1 | 7 | 52 | 66 | 46.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-001 | Project_067_Risk-001 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Lack of Technical Control plan | Person_327 | 2017-07-21 | 2018-09-20 01:00 | 1 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.5 | 97 | 123 | 147 | 122.6667 | 0.1 | 25 | 50 | 79 | 50.6667 |  | 80 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | P006 | Project_067_P006 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Complete SDRL deliverables in Schedule | Person_325 | 2018-07-07 | 2018-08-05 | 0.3 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.7 | 118 | 136 | 142 | 134 | 0.4 | 22 | 47 | 67 | 46.1667 |  | -66.6667 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-004 | Project_067_Risk-004 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Creation of Serial Number for formal Software Releases | Person_327 | 2018-07-07 | 2018-10-21 01:00 | 1 | 0 | 0 | Reduce | 1 | 0 | 0 | H1 | 5 | Stable | 0.7 | 113 | 124 | 150 | 126.5 | 0.3 | 35 | 54 | 74 | 54.1667 |  | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE005 | Project_067_SE005 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Change in Delivery Approach | Person_327 | 2018-07-07 | 2018-08-05 | 0.8 | 0 | 0 | -- | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 75 | 1
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-20 21:00 | 2017-08-19 21:00 | 0.1 | 53.0293 | 5.3029 | Reduce | 0.1 | 53.0293 | 5.3029 | H3 | 3 | Stable | 0.6 | 104 | 127 | 150 | 127 | 0.1 | 26 | 44 | 61 | 43.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Outstanding CRs | Person_693 | 2017-05-23 | 2018-12-21 | 0.7 | 0.20788 | 0.068599 | Accept | 0.3 | 31.0429 | 15.5215 | H3 | 3 | Stable | 0.7 | 113 | 138 | 146 | 135.1667 | 0.7 | 113 | 138 | 146 | 135.1667 | -14833.3191 | 57.1429 | 0 | -8899.9915
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-20 21:00 | 2017-08-19 21:00 | 0.1 | 7.7469 | 0.77469 | Reduce | 0.1 | 7.7469 | 0.77469 | H3 | 3 | Stable | 0.6 | 120 | 124 | 144 | 126.6667 | 0.2 | 9 | 52 | 71 | 48 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of not being able to perform Tests | Person_547 | 2018-08-20 | 2019-01-21 | 0.5 | 11.3437 | 0.56718 | Accept | 0.5 | 11.3437 | 0.56718 | H2 | 4 | Stable | 0.6 | 112 | 136 | 157 | 135.5 | 0.6 | 112 | 136 | 157 | 135.5 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Availability of key resource within Engineering | Person_693 | 2018-01-21 | 2019-05-23 | 0.1 | 3.1344 | 1.5672 | Accept | 0.1 | 3.1344 | 1.5672 | H3 | 3 | Improving | 0.9 | 103 | 131 | 157 | 130.6667 | 0.9 | 103 | 131 | 157 | 130.6667 | 0 | 0 | 1 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_547 | 2017-05-23 | 2019-01-21 | 0.5 | 7.3848 | 3.6924 | Accept | 0.5 | 7.3848 | 3.6924 | H2 | 4 | Stable | 0.9 | 89 | 138 | 144 | 130.8333 | 0.9 | 89 | 138 | 144 | 130.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_693 | 2017-04-22 | 2018-08-19 | 0.15 | 0.78901 | 0.3945 | Accept | 0.1 | 0.78901 | 0.3945 | H3 | 3 | Stable | 0.8 | 86 | 123 | 146 | 120.6667 | 0.8 | 86 | 123 | 146 | 120.6667 | 0 | 33.3333 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK014 | Project_083_RISK014 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System SW hosting Enrionment | Person_712 | 2018-02-20 | 2019-05-22 | 0.3 | 4.8313 | 1.4494 | Reduce | 0.25 | 4.8313 | 1.2078 | H2 | 4 | Stable | 0.9 | 81 | 127 | 147 | 122.6667 | 0.4 | 31 | 48 | 78 | 50.1667 | 0 | 16.6667 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK003 | Project_083_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supply Chain late delivery against Baseline Plan | Person_391 | 2018-02-20 | 2019-05-16 | 0.6 | 2.3988 | 1.4393 | Reduce | 0.4 | 2.3988 | 0.95952 | H2 | 4 | Stable | 0.5 | 93 | 126 | 157 | 125.6667 | 0.1 | 14 | 59 | 63 | 52.1667 | 0 | 33.3333 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK017 | Project_083_RISK017 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Modules Obsolescence Resolution - Domestic Programmes | Person_712 | 2018-03-17 | 2019-01-20 | 0.15 | 10.3732 | 1.556 | Reduce | 0.15 | 10.3732 | 1.556 | H3 | 3 | Stable | 0.7 | 104 | 129 | 151 | 128.5 | 0.3 | 15 | 52 | 61 | 47.3333 | 0 | 0 | 1 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK016 | Project_083_RISK016 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Dependencies on product | Person_465 | 2018-03-17 | 2019-01-20 | 0.3 | 12.3182 | 3.6955 | Avoid | 0.15 | 12.3182 | 1.8477 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK022 | Project_083_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Availability of Engineering Resource | Person_712 | 2018-03-17 | 2019-01-20 | 0.4 | 0 | 0 | Reduce | 0.2 | 5.4459 | 1.0892 | H3 | 3 | Stable | 0.8 | 105 | 132 | 144 | 129.5 | 0.1 | 5 | 51 | 67 | 46 | -inf | 50 | 1 | -inf
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK002 | Project_083_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supply Chain Cost Increase - post Engineering design until completion of Procurement Phase | Person_391 | 2018-02-20 | 2019-01-20 | 0.65 | 5.8349 | 3.7927 | Reduce | 0.25 | 4.8385 | 1.2096 | H2 | 4 | Stable | 0.6 | 96 | 137 | 141 | 130.8333 | 0.3 | 5 | 53 | 72 | 48.1667 | 17.0777 | 61.5385 | 0 | 10.2466
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK024 | Project_083_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability of Data to support Customer Deliverable updates aligned to Customer Deliverable delivery dates | Person_712 | 2018-03-17 | 2019-01-20 | 0.4 | 9.2062 | 3.6825 | Reduce | 0.35 | 7.754 | 2.7139 | H2 | 4 | Stable | 0.9 | 99 | 123 | 147 | 123 | 0.3 | 30 | 55 | 74 | 54 | 15.7746 | 12.5 | 0 | 9.4648
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK023 | Project_083_RISK023 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Customer Deliverables - Read Across from product | Person_712 | 2018-03-17 | 2019-01-20 | 0.6 | 4.279 | 2.5674 | Reduce | 0.4 | 2.8267 | 1.1307 | H3 | 3 | Stable | 0.7 | 101 | 121 | 144 | 121.5 | 0.3 | 9 | 48 | 66 | 44.5 | 33.9395 | 33.3333 | 0 | 20.3637
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Production - Supplier Quality | Person_468 | 2017-05-23 | 2019-08-20 | 0.25 | 6.7219 | 2.6887 | Accept | 0.192 | 6.7219 | 2.6887 | H3 | 3 | Improving | 0.6 | 89 | 122 | 145 | 120.3333 | 0.6 | 89 | 122 | 145 | 120.3333 | 0 | 23.2 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | OP001 | Project_083_OP001 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply chain | Cross Project Procurement | Person_391 | 2018-02-20 | 2019-01-20 | 0.2 | 4.2141 | 0.84283 | Exploit | 0.7 | 4.2141 | 2.9499 | H3 | 3 | Stable | [10 empty] | 0 | -250 | 1 | -7.5
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-184 | Project_032_Risk-184 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Manufacture of new Sub-systems | Person_629 | 2016-04-08 | 2018-02-18 21:00 | 0.33 | 0.05293 | 0.015879 | Accept | 0.5 | 0.05293 | 0.015879 | H1 | 5 | Stable | 0.9 | 101 | 124 | 142 | 123.1667 | 0.9 | 101 | 124 | 142 | 123.1667 | 0 | -51.5152 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS019 | Project_025_RS019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Product Component Failure | Person_619 | 2017-03-23 | 2019-08-07 | 0.7 | 0.82924 | 0.58047 | Reduce | 0.3 | 0.82924 | 0.24877 | H2 | 4 | Stable | 0.9 | 100 | 135 | 142 | 130.3333 | 0.1 | 39 | 51 | 60 | 50.5 | 0 | 57.1429 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_373 | 2012-08-21 | 2019-08-07 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 2.2054 | 1.3453 | H1 | 5 | Stable | 0.7 | 96 | 138 | 148 | 132.6667 | 0.3 | 32 | 58 | 72 | 56 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2018-10-20 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 0.45943 | 0.18377 | H2 | 4 | Stable | 0.5 | 89 | 134 | 143 | 128 | 0.3 | 38 | 54 | 79 | 55.5 | 88.3943 | 20 | 0 | 53.0366
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_703 | 2015-05-24 | 2019-05-22 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 1.1996 | 0.17994 | H3 | 3 | Stable | 0.6 | 95 | 136 | 142 | 130.1667 | 0.2 | 25 | 59 | 68 | 54.8333 | 80.9521 | 70 | 1 | 50.6713
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-19 21:00 | 0.05 | 2.3975 | 2.3975 | Accept | 0.05 | 0.2811 | 0.2811 | H3 | 3 | Stable | 0.6 | 118 | 134 | 149 | 133.8333 | 0.6 | 118 | 134 | 149 | 133.8333 | 88.2751 | 0 | 1 | 52.965
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-20 21:00 | 2020-08-19 21:00 | 0.5 | 0.98068 | 0.2942 | Accept | 0.5 | 0.98068 | 0.2942 | H2 | 4 | Stable | 0.9 | 90 | 126 | 147 | 123.5 | 0.9 | 90 | 126 | 147 | 123.5 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 1.126 | 0.22519 | Accept | 0.5 | 1.126 | 0.22519 | H2 | 4 | Stable | 0.7 | 115 | 126 | 157 | 129.3333 | 0.7 | 115 | 126 | 157 | 129.3333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_009 | Project_051 | RISK001 | Project_051_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Generic Labour or Material Overspend | Person_577 | 2012-05-23 | 2021-05-22 | 0.5 | 0.5993 | 0.23972 | Accept | 0.5 | 0.5993 | 0.23972 | H3 | 3 | Stable | 0.5 | 110 | 132 | 141 | 129.8333 | 0.5 | 110 | 132 | 141 | 129.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-020 | Project_077_T-020 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Cybersecurity | Person_560 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.1 | 1.3478 | 0.13478 | Reduce | 0.1 | 1.3478 | 0.13478 | H3 | 3 | Stable | 0.7 | 87 | 137 | 150 | 130.8333 | 0.4 | 3 | 46 | 63 | 41.6667 | 0 | 0 | 1 | 0
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-005 | Project_077_T-005 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | SSTP/SSTR overspend | Person_667 | 2018-10-22 01:00 | 2020-02-21 01:00 | 0.3 | 10.5469 | 3.1641 | Reduce | 0.3 | 10.5469 | 3.1641 | H2 | 4 | Stable | 0.6 | 90 | 121 | 157 | 121.8333 | 0.4 | 26 | 55 | 68 | 52.3333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-006 | Project_077_T-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Functionality | Person_667 | 2018-08-22 01:00 | 2020-02-21 01:00 | 0.2 | 3.774 | 0.7548 | -- | 0.2 | 3.774 | 0.7548 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-007 | Project_077_T-007 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Rig Failure or Damage | Person_574 | 2018-09-21 01:00 | 2020-12-08 01:00 | 0.3 | 2.033 | 0.6099 | Reduce | 0.3 | 2.033 | 0.6099 | H2 | 4 | Stable | 0.8 | 109 | 137 | 150 | 134.5 | 0.4 | 1 | 48 | 70 | 43.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-023 | Project_077_T-023 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Legacy abilities | Person_706 | 2018-10-22 01:00 | 2020-02-21 01:00 | 0.1 | 1.0019 | 0.10019 | Avoid | 0.1 | 1.0019 | 0.10019 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-001 | Project_077_T-001 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Increased Interface changes | Person_544 | 2018-07-22 | 2018-09-04 01:00 | 0.5 | 2.1566 | 1.0783 | Transfer | 0.3 | 2.1566 | 0.64697 | H2 | 4 | Stable | [10 empty] | 0 | 40 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK030 | Project_083_RISK030 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Additional (unknown) support as result of sub-system learning within supply and customer | Person_644 | 2017-11-20 | 2020-11-19 | 0.4 | 2.4261 | 0.72784 | Accept | 0.4 | 2.4261 | 0.72784 | H3 | 3 | Stable | 0.9 | 91 | 135 | 151 | 130.3333 | 0.9 | 91 | 135 | 151 | 130.3333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-025 | Project_077_T-025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Delayed Config File delivery | Person_163 | 2019-05-24 | 2020-02-21 01:00 | 0.5 | 3.3696 | 1.6848 | Avoid | 0.5 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-003 | Project_077_T-003 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | SW Resource availability | Person_508 | 2018-05-23 | 2020-02-21 01:00 | 0.5 | 25.1598 | 12.5799 | Reduce | 0.5 | 25.1598 | 12.5799 | H1 | 5 | Worsening | 0.5 | 93 | 123 | 141 | 121 | 0.2 | 34 | 53 | 77 | 53.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-026 | Project_077_T-026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Insufficient Config Option capacity | Person_706 | 2018-04-22 | 2020-02-21 01:00 | 0.2 | 1.0019 | 0.20038 | Avoid | 0.05 | 1.0019 | 0.050095 | H3 | 3 | Stable | [10 empty] | 0 | 75 | 1 | 2.25
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-004 | Project_077_T-004 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Debt | Person_667 | 2018-08-22 01:00 | 2020-02-21 01:00 | 0.2 | 2.1566 | 0.43131 | Reduce | 0.2 | 2.1566 | 0.43131 | H3 | 3 | Stable | 0.8 | 98 | 140 | 145 | 133.8333 | 0.4 | 33 | 57 | 64 | 54.1667 | 0 | 0 | 1 | 0
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | OPRisk-001 | Project_077_OPRisk-001 | Opportunitity | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Opportunity that fewer than expected customer problem reports are raised. | Person_706 | 2019-03-24 | 2020-02-21 01:00 | 0.5 | 1.0221 | 0.51106 | -- | 0.5 | 0.14602 | 0.07301 | H2 | 4 | Stable | [10 empty] | 85.7141 | 0 | 0 | 51.4285
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-010 | Project_077_T-010 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Technical Directorate changes to software/data artefacts - Internal Requirement | Person_574 | 2018-11-21 01:00 | 2020-02-21 01:00 | 0.4 | 1.887 | 0.7548 | Reduce | 0.4 | 1.887 | 0.7548 | H2 | 4 | Stable | 0.8 | 105 | 124 | 149 | 125 | 0.3 | 23 | 41 | 69 | 42.6667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-032 | Project_077_T-032 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Requirement Updated from Issue 4 to 6 | Person_574 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.5 | 3.3696 | 1.6848 | Avoid | 0.1 | 3.3696 | 0.33696 | H3 | 3 | Stable | [10 empty] | 0 | 80 | 1 | 2.4
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-011 | Project_077_T-011 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Bus Scheduling table changes affecting proven interface | Person_706 | 2019-05-24 | 2020-02-21 01:00 | 0.2 | 0.92103 | 0.18421 | Reduce | 0.2 | 0.92103 | 0.18421 | H3 | 3 | Stable | 0.5 | 95 | 130 | 153 | 128 | 0.4 | 39 | 57 | 67 | 55.6667 | 0 | 0 | 1 | 0
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-033 | Project_077_T-033 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | PDA availability | Person_574 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.4 | 3.0327 | 1.2131 | Avoid | 0.4 | 3.0327 | 1.2131 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-016 | Project_077_T-016 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Autotest | Person_574 | 2018-09-09 01:00 | 2020-02-21 01:00 | 0.5 | 2.1341 | 1.067 | Reduce | 0.5 | 2.1341 | 1.067 | H2 | 4 | Stable | 0.7 | 101 | 140 | 141 | 133.6667 | 0.3 | 26 | 43 | 74 | 45.3333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS020 | Project_025_RS020 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Plant Machinery failure | Person_619 | 2017-03-23 | 2019-08-07 | 0.3 | 2.4711 | 0.37066 | Accept | 0.3 | 2.4711 | 0.37066 | H2 | 4 | Stable | 0.9 | 88 | 134 | 152 | 129.3333 | 0.9 | 88 | 134 | 152 | 129.3333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-012 | Project_077_T-012 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Managment cost increases for BMN | Person_667 | 2018-03-01 01:00 | 2020-02-21 01:00 | 0.21 | 1.5725 | 0.33022 | Avoid | 0.21 | 1.5725 | 0.33022 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-034 | Project_077_T-034 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Simulator update not viable if needed | Person_707 | 2018-10-22 01:00 | 2020-02-21 01:00 | 0.5 | 0.74806 | 0.37403 | Avoid | 0.5 | 0.74806 | 0.37403 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-013 | Project_077_T-013 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | More customer failures than anticipated | Person_706 | 2019-02-21 01:00 | 2020-02-21 01:00 | 0.2 | 3.3809 | 0.67617 | Reduce | 0.2 | 3.3809 | 0.67617 | H3 | 3 | Stable | 0.8 | 115 | 136 | 147 | 134.3333 | 0.4 | 6 | 43 | 67 | 40.8333 | 0 | 0 | 1 | 0
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-014 | Project_077_T-014 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Extra Release | Person_667 | 2020-06-23 | 2020-11-20 01:00 | 0.1 | 13.4785 | 1.3478 | Avoid | 0.1 | 13.4785 | 1.3478 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-119 | Project_029_Risk-119 | Opportunitity | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Not required to support on load & offload of Customer Furnished Equipmnet | Person_585 | 2017-05-23 | 2020-04-16 | 0.8 | 5.1334 | 4.1067 | Exploit | 0.8 | 3.4137 | 2.731 | H2 | 4 | Stable | [10 empty] | 33.5 | 0 | 0 | 20.1
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_089 | RISK011 | Project_089_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Critical Resources / Skills | Person_503 | 2018-02-20 01:00 | 2020-05-23 | 0.3 | 27.1644 | 0.81493 | Accept | 0.3 | 12.8336 | 0.38501 | H2 | 4 | Stable | 0.6 | 101 | 136 | 144 | 131.5 | 0.6 | 101 | 136 | 144 | 131.5 | 52.7559 | 0 | 0 | 31.6535
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2018-03-22 | 2019-07-21 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.6 | 117 | 135 | 145 | 133.6667 | 0.4 | 32 | 49 | 71 | 49.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_585 | 2017-09-02 01:00 | 2020-04-26 | 0.1 | 6.4168 | 0.64168 | Transfer | 0.1 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sub-system FPGA | Person_332 | 2017-01-21 01:00 | 2019-05-16 | 0.4 | 1.5914 | 0.63655 | Reduce | 0.2 | 1.5914 | 0.31827 | H3 | 3 | Stable | 0.5 | 108 | 126 | 148 | 126.6667 | 0.3 | 23 | 50 | 77 | 50 | 0 | 50 | 1 | 1.5
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort for System HW/SW- System upgrade. | Person_199 | 2017-05-23 | 2019-09-18 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.2 | 2.5667 | 0.51334 | H3 | 3 | Stable | 0.6 | 88 | 128 | 146 | 124.3333 | 0.3 | 34 | 42 | 60 | 43.6667 | 0 | 33.3333 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_089 | RISK013 | Project_089_RISK013 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Software incompatibility issue | Person_503 | 2018-10-22 01:00 | 2018-12-22 01:00 | 0.2 | 6.6521 | 3.326 | Accept | 0.2 | 6.6521 | 3.326 | H3 | 3 | Stable | 0.7 | 118 | 134 | 149 | 133.8333 | 0.7 | 118 | 134 | 149 | 133.8333 | 0 | 0 | 1 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.25 | 3.5934 | 0.89835 | H2 | 4 | Stable | 0.7 | 108 | 125 | 142 | 125 | 0.2 | 21 | 41 | 73 | 43 | 0 | 50 | 0 | 0
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-002 | Project_077_T-002 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Legacy testing Repeatability | Person_708 | 2018-10-22 01:00 | 2019-05-11 | 0.3 | 2.5667 | 0.77001 | Accept | 0.3 | 2.5667 | 0.51334 | H2 | 4 | Stable | 0.8 | 82 | 135 | 157 | 129.8333 | 0.8 | 82 | 135 | 157 | 129.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Minimum Order Quantities | Person_403 | 2017-11-20 01:00 | 2019-05-16 | 0.2 | 1.925 | 0.38501 | Exploit | 0.2 | 1.925 | 0.38501 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_403 | 2018-04-22 | 2019-05-16 | 0.33 | 5.7323 | 1.8917 | Reduce | 0.33 | 5.7323 | 1.8917 | H2 | 4 | Worsening | 0.5 | 110 | 126 | 142 | 126 | 0.1 | 28 | 51 | 67 | 49.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-018 | Project_077_T-018 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Config system changes | Person_574 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.15 | 11.5502 | 3.8462 | Accept | 0.15 | 11.5502 | 3.8462 | H3 | 3 | Stable | 0.7 | 116 | 131 | 146 | 131 | 0.7 | 116 | 131 | 146 | 131 | 0 | 0 | 1 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) at the System level on product platform - performed by 3rd parties | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Sub-system / product system accreditation hindered by Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.1 | 0.25667 | 0.025667 | Transfer | 0.1 | 0.25667 | 0.025667 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-06-23 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-019 | Project_077_T-019 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | New stakeholders/Changeovers | Person_667 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.3 | 1.4673 | 0.58692 | Accept | 0.3 | 1.4673 | 0.44019 | H2 | 4 | Stable | 0.9 | 120 | 131 | 142 | 131 | 0.9 | 120 | 131 | 142 | 131 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_694 | 2017-05-23 | 2019-08-04 | 0.3 | 0 | 0 | Transfer | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 66.6667 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_585 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 1.9208 | 0.67227 | Accept | 0.03 | 1.9208 | 0.48019 | H3 | 3 | Stable | 0.6 | 99 | 124 | 155 | 125 | 0.6 | 99 | 124 | 155 | 125 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2018-03-22 | 2020-04-26 | 0.4 | 0.77001 | 0.30801 | Reduce | 0.3 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.9 | 118 | 121 | 149 | 125.1667 | 0.2 | 33 | 59 | 70 | 56.5 | 0 | 25 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_694 | 2018-02-20 01:00 | 2019-08-04 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.7 | 80 | 140 | 152 | 132 | 0.1 | 8 | 40 | 64 | 38.6667 | 0 | 28.5714 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs | Person_403 | 2018-04-22 | 2019-05-16 | 0.5 | 1.54 | 0.30801 | Accept | 0.5 | 0.77001 | 0.154 | H2 | 4 | Stable | 0.9 | 91 | 129 | 146 | 125.5 | 0.9 | 91 | 129 | 146 | 125.5 | 50 | 0 | 0 | 30
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 0.94968 | 0.28491 | Accept | 0.25 | 0.94968 | 0.18994 | H2 | 4 | Stable | 0.9 | 85 | 128 | 159 | 126 | 0.9 | 85 | 128 | 159 | 126 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 1.0695 | 0.74863 | Accept | 0.2 | 1.0695 | 0.74863 | H3 | 3 | Stable | 0.5 | 88 | 123 | 151 | 121.8333 | 0.5 | 88 | 123 | 151 | 121.8333 | 0 | 33.3333 | 1 | 1
2018-06-23 | ORG_002 | BA_004 | Portfolio_021 | Project_086 | RISK003 | Project_086_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Qualification | Person_528 | 2017-11-22 01:00 | 2018-10-21 01:00 | 0.3 | 0.33844 | 0.10153 | Reduce | 0.2 | 0.33844 | 0.067689 | H2 | 4 | Worsening | 0.5 | 111 | 121 | 151 | 124.3333 | 0.2 | 22 | 56 | 76 | 53.6667 | 0 | 33.3333 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_585 | 2017-10-21 01:00 | 2019-07-21 | 0.333 | 0.60436 | 0.48349 | Accept | 0.333 | 0.60436 | 0.48349 | H2 | 4 | Stable | 0.9 | 109 | 136 | 152 | 134.1667 | 0.9 | 109 | 136 | 152 | 134.1667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 0 | 0 | Accept | 0.3 | 0 | 0 | H2 | 4 | Improving | 0.8 | 81 | 132 | 147 | 126 | 0.8 | 81 | 132 | 147 | 126 |  | 25 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2020-04-26 | 0.35 | 0.60436 | 0.18131 | Accept | 0.25 | 0.60436 | 0.18131 | H2 | 4 | Stable | 0.7 | 96 | 122 | 154 | 123 | 0.7 | 96 | 122 | 154 | 123 | 0 | 28.5714 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2020-09-19 01:00 | 0.2 | 0.33844 | 0.10153 | Accept | 0.2 | 0.33844 | 0.10153 | H3 | 3 | Stable | 0.8 | 92 | 132 | 143 | 127.1667 | 0.8 | 92 | 132 | 143 | 127.1667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2019-07-21 | 0.3 | 0 | 0 | Accept | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.5 | 108 | 127 | 141 | 126.1667 | 0.5 | 108 | 127 | 141 | 126.1667 |  | 33.3333 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK031 | Project_079_RISK031 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Line Closure Savings | Person_683 | 2020-12-21 01:00 | 2021-04-22 | 0.8 | 2.3927 | 1.9142 | -- | 0.8 | 2.3927 | 1.9142 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK030 | Project_079_RISK030 | Opportunitity | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Production Build / Touch Labour | Person_683 | 2018-11-21 01:00 | 2020-04-22 | 0.8 | 46.4619 | 37.1695 | -- | 0.8 | 46.4619 | 37.1695 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-082 | Project_008_Risk-082 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Insufficient spares to maintain the Training availability | Person_639 | 2017-05-23 | 2018-08-21 | 0.15 | 6.6286 | 0.9943 | Reduce | 0.15 | 6.6286 | 0.9943 | H2 | 4 | Stable | 0.9 | 89 | 140 | 149 | 133 | 0.2 | 12 | 40 | 72 | 40.6667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_070 | Risk-003 | Project_070_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_676 | 2016-08-21 01:00 | 2017-08-21 01:00 | 0.5 | 23.4578 | 11.7289 | Reduce | 0.15 | 23.4578 | 3.5187 | H3 | 3 | Stable | 0.9 | 119 | 130 | 146 | 130.8333 | 0.3 | 7 | 46 | 76 | 44.5 | 0 | 70 | 1 | 2.1
2018-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | RISK008 | Project_029_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Impact of sub-system Design Changes [product dependency] | Person_332 | 2016-09-20 01:00 | 2019-08-15 | 0.7 | 4.7982 | 1.6794 | Accept | 0.7 | 4.7982 | 1.6794 | H2 | 4 | Stable | 0.7 | 96 | 127 | 155 | 126.5 | 0.7 | 96 | 127 | 155 | 126.5 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_070 | Risk-021 | Project_070_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.4 | 1.5994 | 0.63976 | Reduce | 0.4 | 1.5994 | 0.63976 | H3 | 3 | Stable | 0.6 | 116 | 128 | 148 | 129.3333 | 0.3 | 35 | 48 | 76 | 50.5 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-113 | Project_043_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | No Gen 1 products available, transition cost to Gen 2 | Person_769 | 2017-04-19 | 2020-12-21 | 0.3 | 1.4971 | 0.44912 | Reduce | 0.3 | 1.4971 | 0.44912 | H2 | 4 | Stable | 0.6 | 109 | 132 | 155 | 132 | 0.1 | 9 | 51 | 64 | 46.1667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-121 | Project_043_Risk-121 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | More Tech Pubs Update than estimated | Person_769 | 2019-01-21 | 2020-10-20 | 0.45 | 1.7366 | 0.78146 | Reduce | 0.45 | 1.7366 | 0.78146 | H1 | 5 | Stable | 0.5 | 99 | 128 | 147 | 126.3333 | 0.4 | 38 | 48 | 73 | 50.5 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-084 | Project_043_Risk-084 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | complex repair ( over and above the forecast average) | Person_693 | 2017-12-21 | 2020-12-21 | 0.2 | 0.71859 | 0.14372 | Reduce | 0.2 | 0.71859 | 0.14372 | H2 | 4 | Stable | 0.9 | 98 | 136 | 156 | 133 | 0.4 | 2 | 57 | 70 | 50 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-128 | Project_043_Risk-128 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Reliance of Customer Avaliability | Person_135 | 2017-04-19 | 2018-08-21 | 0.5 | 1.7665 | 0.88326 | Reduce | 0.1 | 1.7665 | 0.17665 | H2 | 4 | Stable | 0.6 | 101 | 137 | 144 | 132.1667 | 0.3 | 36 | 50 | 73 | 51.5 | 0 | 80 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-089 | Project_043_Risk-089 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares pool is limited | Person_307 | 2018-12-22 | 2020-12-21 | 0.25 | 1.5969 | 0.39921 | Reduce | 0.25 | 1.2775 | 0.31937 | H2 | 4 | Stable | 0.9 | 111 | 127 | 158 | 129.5 | 0.4 | 33 | 49 | 63 | 48.6667 | 20 | 0 | 0 | 12
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-039 | Project_043_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System fails to achieve required performance | Person_051 | 2017-04-19 | 2018-11-20 | 0.3 | 4.7906 | 1.4372 | Reduce | 0.3 | 4.7906 | 1.4372 | H2 | 4 | Stable | 0.8 | 97 | 135 | 149 | 131 | 0.4 | 37 | 55 | 62 | 53.1667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_070 | Risk-019 | Project_070_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.35 | 10.5437 | 2.1087 | Accept | 0.35 | 10.5437 | 2.1087 | H3 | 3 | Stable | 0.9 | 111 | 140 | 156 | 137.8333 | 0.9 | 111 | 140 | 156 | 137.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 0.2 | 23.521 | 4.7042 | Avoid | 0.15 | 20.0321 | 3.0048 | H2 | 4 | Stable | [10 empty] | 14.8333 | 25 | 0 | 8.9
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 0.25 | 9.1144 | 2.2786 | Reduce | 0.2 | 6.7623 | 1.3525 | H2 | 4 | Improving | 0.5 | 103 | 137 | 155 | 134.3333 | 0.4 | 32 | 53 | 72 | 52.6667 | 25.8065 | 20 | 0 | 15.4839
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 0.15 | 21.3649 | 3.2047 | Avoid | 0.1 | 17.6408 | 1.7641 | H2 | 4 | Stable | [10 empty] | 17.4312 | 33.3333 | 0 | 10.4587
2018-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 0.15 | 14.8966 | 2.2345 | Avoid | 0.1 | 8.8204 | 0.88204 | H2 | 4 | Stable | [10 empty] | 40.7895 | 33.3333 | 0 | 24.4737
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_070 | Risk-020 | Project_070_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.25 | 13.4066 | 5.3626 | Accept | 0.25 | 13.4066 | 5.3626 | H3 | 3 | Stable | 0.8 | 89 | 136 | 155 | 131.3333 | 0.8 | 89 | 136 | 155 | 131.3333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | R054 | Project_066_R054 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | System Cybersecurity shortfalls | Person_549 | 2017-01-21 01:00 | 2024-05-23 | 0.8 | 15.7936 | 12.6349 | Reduce | 0.5 | 15.7936 | 7.8968 | H1 | 5 | Stable | 0.6 | 81 | 128 | 147 | 123.3333 | 0.3 | 13 | 56 | 71 | 51.3333 | 0 | 37.5 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_070 | Risk-001 | Project_070_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_676 | 2016-10-21 01:00 | 2019-08-20 | 0.5 | 18.5516 | 12.9861 | Accept | 0.5 | 18.5516 | 12.9861 | H2 | 4 | Stable | 0.7 | 119 | 133 | 148 | 133.1667 | 0.7 | 119 | 133 | 148 | 133.1667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_070 | Risk-002 | Project_070_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.2 | 8.8305 | 2.6492 | Accept | 0.2 | 8.8305 | 2.6492 | H3 | 3 | Stable | 0.8 | 102 | 140 | 143 | 134.1667 | 0.8 | 102 | 140 | 143 | 134.1667 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Volume of production tools and Jigs | Person_279 | 2016-11-22 23:00 | 2021-11-22 23:00 | 0.35 | 6.4382 | 2.2534 | Reduce | 0.15 | 6.4382 | 0.96573 | H2 | 4 | Stable | 0.5 | 111 | 132 | 160 | 133.1667 | 0.1 | 33 | 49 | 71 | 50 | 0 | 57.1429 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software issue input | Person_279 | 2016-11-22 23:00 | 2023-02-19 23:00 | 0.4 | 49.4398 | 19.7759 | Reduce | 0.2 | 49.4398 | 9.888 | H2 | 4 | Stable | 0.7 | 100 | 127 | 154 | 127 | 0.4 | 2 | 43 | 60 | 39 | 0 | 50 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2018-05-22 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.6 | 108 | 125 | 153 | 126.8333 | 0.2 | 13 | 58 | 60 | 50.8333 | 0 | 40 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 0.92411 | 0.55447 | Reduce | 0.5 | 0.36965 | 0.18482 | H2 | 4 | Stable | 0.6 | 89 | 131 | 148 | 126.8333 | 0.2 | 1 | 59 | 76 | 52.1667 | 60 | 16.6667 | 0 | 36
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-03 19:00 | 2018-04-21 | 0.2 | 4.0661 | 0.81322 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.7 | 120 | 138 | 153 | 137.5 | 0.2 | 36 | 55 | 70 | 54.3333 | 0 | 75 | 1 | 2.25
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.5 | 0.46206 | 0.23103 | H1 | 5 | Stable | 0.5 | 92 | 133 | 154 | 129.6667 | 0.1 | 35 | 51 | 66 | 50.8333 | 58.3333 | 16.6667 | 0 | 35
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | R181 | Project_066_R181 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | USB Hub start up issues | Person_247 | 2017-01-21 01:00 | 2024-05-23 | 1 | 1.1089 | 0.88715 | Accept | 1 | 0.73929 | 0.44357 | H1 | 5 | Stable | 0.8 | 96 | 128 | 144 | 125.3333 | 0.8 | 96 | 128 | 144 | 125.3333 | 33.3333 | 0 | 0 | 20
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-28 19:00 | 2018-05-22 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.8 | 101 | 123 | 159 | 125.3333 | 0.3 | 25 | 48 | 77 | 49 | 0 | 50 | 1 | 1.5
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2018-05-22 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.5 | 96 | 127 | 155 | 126.5 | 0.4 | 28 | 49 | 79 | 50.5 | 0 | 25 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_693 | 2012-06-01 | 2018-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Improving | 0.9 | 80 | 139 | 141 | 129.5 | 0.2 | 27 | 46 | 64 | 45.8333 | 0 | 40 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2018-05-21 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Stable | [10 empty] | 0 | 37.5 | 0 | 0
2018-06-23 | ORG_001 | BA_002 | Portfolio_008 | Project_082 | RISK007 | Project_082_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Task 30 - Pylon Procurement | Person_619 | 2017-04-13 | 2018-07-21 | 1 | 3.6965 | 0.36965 | Accept | 1 | 3.6965 | 0.18482 | H2 | 4 | Stable | 0.5 | 120 | 121 | 148 | 125.3333 | 0.5 | 120 | 121 | 148 | 125.3333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2018-02-18 19:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.5 | 94 | 130 | 157 | 128.5 | 0.4 | 25 | 48 | 71 | 48 | 90 | 75 | 1 | 56.25
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK010 | Project_010_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Use of Lead components | Person_359 | 2012-05-23 | 2025-04-22 | 0.05 | 1.8482 | 0.092411 | Reduce | 0.05 | 1.8482 | 0.092411 | H3 | 3 | Stable | 0.7 | 94 | 123 | 147 | 122.1667 | 0.4 | 30 | 48 | 78 | 50 | 0 | 0 | 1 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-19 19:00 | 0.05 | 226.8807 | 71.8456 | Accept | 0.03 | 226.8807 | 9.9555 | H2 | 4 | Stable | 0.8 | 114 | 131 | 153 | 131.8333 | 0.8 | 114 | 131 | 153 | 131.8333 | 0 | 40 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Additional minor point release | Person_228 | 2016-05-23 | 2019-06-23 | 0.5 | 11.9444 | 5.9722 | Reduce | 0.25 | 11.9444 | 2.9861 | H2 | 4 | Stable | 0.7 | 104 | 129 | 152 | 128.6667 | 0.4 | 27 | 55 | 71 | 53 | 0 | 50 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_004 | 2015-11-21 01:00 | 2019-07-21 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.9 | 89 | 134 | 157 | 130.3333 | 0.1 | 15 | 43 | 78 | 44.1667 | 0 | 5 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-09-24 01:00 | 0.8 | 2.8043 | 2.2435 | Reduce | 0.45 | 2.8043 | 1.2619 | H1 | 5 | Stable | 0.6 | 80 | 139 | 142 | 129.6667 | 0.3 | 26 | 50 | 65 | 48.5 | 0 | 43.75 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2018-04-22 | 0.8 | 35.9673 | 10.7902 | Accept | 0.6 | 35.9673 | 9.7112 | H1 | 5 | Stable | 0.5 | 94 | 138 | 148 | 132.3333 | 0.5 | 94 | 138 | 148 | 132.3333 | 0 | 25 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-26 19:00 | 2018-05-22 | 0.1 | 3.9728 | 1.3905 | Accept | 0.05 | 3.9728 | 1.3905 | H2 | 4 | Stable | 0.5 | 119 | 121 | 146 | 124.8333 | 0.5 | 119 | 121 | 146 | 124.8333 | 0 | 50 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_610 | 2017-09-21 01:00 | 2018-09-24 01:00 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.7 | 109 | 124 | 148 | 125.5 | 0.2 | 12 | 48 | 77 | 46.8333 | 0 | 60 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2019-04-22 | 0.5 | 3.843 | 1.9215 | Reduce | 0.2 | 3.843 | 0.76859 | H2 | 4 | Stable | 0.9 | 98 | 133 | 160 | 131.6667 | 0.3 | 11 | 42 | 74 | 42.1667 | 0 | 60 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Performance (collector opportunity) | Person_351 | 2017-01-21 01:00 | 2019-07-25 | 0.373 | 19.5316 | 7.2853 | -- | 0.4158 | 19.5316 | 8.1213 | H1 | 5 | Stable | [10 empty] | 0 | -11.4745 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK308 | Project_024_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System robustness and resilience | Person_774 | 2017-04-06 | 2019-02-10 01:00 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.1 | 2.5966 | 0.25966 | H3 | 3 | Stable | 0.6 | 94 | 128 | 145 | 125.1667 | 0.4 | 27 | 52 | 76 | 51.8333 | 58.3333 | 66.6667 | 1 | 37
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2018-05-21 | 0.2 | 5.6606 | 5.6606 | Accept | 0.2 | 5.6606 | 5.6606 | H3 | 3 | Worsening | 0.9 | 91 | 140 | 156 | 134.5 | 0.9 | 91 | 140 | 156 | 134.5 | 0 | 0 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_061 | RISK003 | Project_061_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Test equipment reliability | Person_104 | 2017-05-23 | 2020-11-18 21:00 | 0.4 | 0.11013 | 0.044051 | Reduce | 0.3 | 0.11013 | 0.033038 | H2 | 4 | Stable | 0.6 | 100 | 136 | 156 | 133.3333 | 0.2 | 31 | 42 | 69 | 44.6667 | 0 | 25 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK018 | Project_038_RISK018 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Last System Syndrome | Person_329 | 2012-11-20 | 2018-10-21 | 0.15 | 43.4175 | 6.5126 | Reduce | 0.13 | 43.4175 | 5.6443 | H2 | 4 | Worsening | 0.9 | 91 | 131 | 159 | 129 | 0.1 | 35 | 53 | 68 | 52.5 | 0 | 13.3333 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2018-04-22 | 0.3 | 6.8093 | 1.7023 | Accept | 0.2 | 6.8093 | 1.7023 | H3 | 3 | Stable | 0.7 | 113 | 134 | 146 | 132.5 | 0.7 | 113 | 134 | 146 | 132.5 | 0 | 33.3333 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK016 | Project_038_RISK016 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Supplier Quality Issues | Person_397 | 2012-11-20 | 2018-08-22 | 0.5 | 5.0339 | 2.517 | Avoid | 0.5 | 5.0339 | 2.517 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK003 | Project_024_RISK003 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance | Person_119 | 2017-12-21 01:00 | 2019-07-21 | 0.31667 | 2.4645 | 0.4929 | Accept | 0.04388 | 2.4645 | 0.4929 | H2 | 4 | Stable | 0.9 | 105 | 130 | 152 | 129.5 | 0.9 | 105 | 130 | 152 | 129.5 | 0 | 86.1432 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before part b finished | Person_119 | 2016-10-20 01:00 | 2018-09-20 01:00 | 0.3 | 1.8757 | 0.56272 | Accept | 0.27 | 1.8757 | 0.56272 | H2 | 4 | Worsening | 0.7 | 111 | 123 | 152 | 125.8333 | 0.7 | 111 | 123 | 152 | 125.8333 | 0 | 10 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK389 | Project_024_RISK389 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Further Problem Report Growth | Person_186 | 2018-06-27 | 2018-10-20 01:00 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.3 | 20.8767 | 6.263 | H1 | 5 | Stable | 0.9 | 87 | 133 | 152 | 128.5 | 0.4 | 32 | 56 | 74 | 55 | 50 | 25 | 0 | 30
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK341 | Project_024_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Latent Technical Debt impacts acceptance | Person_610 | 2018-06-27 | 2018-10-25 01:00 | 0.6 | 2.4668 | 1.4801 | Reduce | 0.1 | 1.6878 | 0.16878 | H3 | 3 | Stable | 0.7 | 117 | 129 | 150 | 130.5 | 0.2 | 39 | 51 | 67 | 51.6667 | 31.5789 | 83.3333 | 1 | 21.4474
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK340 | Project_024_RISK340 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Subsystemup dates for Trade Items do not occur as needed | Person_610 | 2018-06-27 | 2018-10-25 01:00 | 0.4 | 1.268 | 0.5072 | Reduce | 0.2 | 1.268 | 0.2536 | H2 | 4 | Stable | 0.9 | 91 | 129 | 160 | 127.8333 | 0.1 | 2 | 49 | 71 | 44.8333 | 0 | 50 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK342 | Project_024_RISK342 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Unable to release updates to the software | Person_124 | 2017-01-21 01:00 | 2018-10-25 01:00 | 0.2 | 0.34751 | 0.069502 | Reduce | 0.2 | 0.34751 | 0.069502 | H3 | 3 | Stable | 0.7 | 90 | 129 | 158 | 127.3333 | 0.3 | 8 | 47 | 67 | 43.8333 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK390 | Project_024_RISK390 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Customer drives scope change | Person_233 | 2018-01-21 01:00 | 2019-02-21 01:00 | 0.5 | 2.1292 | 1.0646 | Reduce | 0.3 | 1.6878 | 0.50634 | H1 | 5 | Stable | 0.5 | 85 | 137 | 142 | 129.1667 | 0.1 | 26 | 51 | 77 | 51.1667 | 20.7317 | 40 | 0 | 12.439
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK399 | Project_024_RISK399 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Contract change items scope poorly defined | Person_610 | 2018-06-27 | 2018-10-25 01:00 | 0.2 | 3.289 | 0.65781 | Reduce | 0.2 | 3.289 | 0.65781 | H2 | 4 | Improving | 0.8 | 80 | 134 | 158 | 129 | 0.4 | 17 | 59 | 74 | 54.5 | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK398 | Project_024_RISK398 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Non compliance against SSS drives minor design change. | Person_610 | 2017-01-21 01:00 | 2018-10-25 01:00 | 0.25 | 3.0121 | 0.75301 | Reduce | 0.2 | 1.6359 | 0.32717 | H3 | 3 | Stable | 0.8 | 99 | 123 | 147 | 123 | 0.4 | 1 | 54 | 79 | 49.3333 | 45.6897 | 20 | 0 | 27.4138
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK397 | Project_024_RISK397 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Capability for each System release does not remain stable | Person_016 | 2017-01-21 01:00 | 2018-10-25 01:00 | 0.5 | 2.4408 | 1.2204 | Reduce | 0.45 | 1.2204 | 0.54918 | H1 | 5 | Improving | 0.5 | 91 | 127 | 157 | 126 | 0.2 | 22 | 44 | 75 | 45.5 | 50 | 10 | 0 | 30
2018-07-22 | ORG_005 | BA_008 | Portfolio_020 | Project_090 | RISK004 | Project_090_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 2. Bid Management | Test equipment out of calibration or not available | Person_304 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.2 | 0.074606 | 0.014921 | Reduce | 0.1 | 0.074606 | 0.0074606 | H3 | 3 | Stable | 0.7 | 85 | 129 | 144 | 124.1667 | 0.4 | 10 | 40 | 63 | 38.8333 | 0 | 50 | 1 | 1.5
2018-07-22 | ORG_005 | BA_008 | Portfolio_020 | Project_090 | RISK006 | Project_090_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | No on site transport | Person_304 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.21 | 0.098542 | 0.020694 | Avoid | 0.21 | 0.098542 | 0.020694 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_005 | BA_008 | Portfolio_020 | Project_090 | RISK002 | Project_090_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Risk of delays | Person_304 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.41 | 0.10558 | 0.043287 | Reduce | 0.41 | 0.10558 | 0.043287 | H2 | 4 | Stable | 0.9 | 93 | 128 | 150 | 125.8333 | 0.4 | 11 | 44 | 67 | 42.3333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_005 | BA_008 | Portfolio_020 | Project_090 | RISK008 | Project_090_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | System failure | Person_304 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.21 | 0.098542 | 0.020694 | Reduce | 0.15 | 0.098542 | 0.014781 | H3 | 3 | Stable | 0.5 | 96 | 121 | 141 | 120.1667 | 0.1 | 32 | 51 | 66 | 50.3333 | 0 | 28.5714 | 1 | 0.85714
2018-07-22 | ORG_005 | BA_008 | Portfolio_020 | Project_090 | RISK007 | Project_090_RISK007 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Weather | Person_304 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.2 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.5 | 80 | 134 | 156 | 128.6667 | 0.3 | 13 | 57 | 67 | 51.3333 |  | 0 | 0
2018-07-22 | ORG_005 | BA_008 | Portfolio_020 | Project_090 | RISK009 | Project_090_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Transition to different geo-political environment | Person_304 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.1 | 0.12669 | 0.012669 | Transfer | 0.1 | 0.12669 | 0.012669 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK343 | Project_024_RISK343 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Product technical debt requiring project resolution | Person_610 | 2017-01-21 01:00 | 2018-10-25 01:00 | 0.3 | 3.3378 | 3.3378 | Accept | 0.3 | 3.3378 | 3.3378 | H3 | 3 | Improving | 0.7 | 120 | 124 | 156 | 128.6667 | 0.7 | 120 | 124 | 156 | 128.6667 | 0 | 0 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK003 | Project_060_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Misalignment of Critical Resource | Person_312 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.7 | 1.0769 | 0.75381 | Reduce | 0.5 | 1.0769 | 0.53844 | H2 | 4 | Stable | 0.6 | 117 | 127 | 141 | 127.6667 | 0.3 | 22 | 56 | 72 | 53 | 0 | 28.5714 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK004 | Project_060_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Cross-functional Estimates | Person_729 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.7 | 2.8845 | 2.0191 | Reduce | 0.5 | 1.4422 | 0.72112 | H2 | 4 | Improving | 0.7 | 107 | 127 | 141 | 126 | 0.1 | 24 | 44 | 62 | 43.6667 | 50 | 28.5714 | 0 | 30
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK392 | Project_024_RISK392 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Rig maintenance is not adequate | Person_016 | 2017-01-21 01:00 | 2018-10-25 01:00 | 0.2 | 1.1538 | 0.5769 | Accept | 0.2 | 1.1538 | 0.5769 | H2 | 4 | Stable | 0.9 | 118 | 138 | 157 | 137.8333 | 0.9 | 118 | 138 | 157 | 137.8333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK001 | Project_060_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Procurement Prices | Person_033 | 2017-11-02 01:00 | 2018-08-20 | 0.7 | 1.4422 | 1.0096 | Reduce | 0.3 | 1.4422 | 0.43267 | H3 | 3 | Stable | 0.5 | 97 | 136 | 148 | 131.5 | 0.1 | 27 | 48 | 78 | 49.5 | 0 | 57.1429 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK393 | Project_024_RISK393 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Insufficient Systems to support Trainer project needs. | Person_348 | 2016-08-21 01:00 | 2018-10-25 01:00 | 0.4 | 0 | 0 | Accept | 0.4 | 0 | 0 | H1 | 5 | Worsening | 0.7 | 80 | 123 | 157 | 121.5 | 0.7 | 80 | 123 | 157 | 121.5 |  | 0 | 0
2018-07-22 | ORG_005 | BA_008 | Portfolio_020 | Project_090 | RISK003 | Project_090_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Illness | Person_304 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.2 | 6.1106 | 0.61106 | Accept | 0.2 | 6.1106 | 0.61106 | H3 | 3 | Stable | 0.6 | 106 | 136 | 146 | 132.6667 | 0.6 | 106 | 136 | 146 | 132.6667 | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_676 | 2016-08-21 01:00 | 2017-08-21 01:00 | 0.5 | 37.5906 | 18.7953 | Reduce | 0.15 | 37.5906 | 5.6386 | H3 | 3 | Stable | 0.8 | 87 | 121 | 143 | 119 | 0.4 | 23 | 45 | 63 | 44.3333 | 0 | 70 | 1 | 2.1
2018-07-22 | ORG_005 | BA_008 | Portfolio_020 | Project_090 | RISK001 | Project_090_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Resource reduction in personnel | Person_304 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.5 | 7.689 | 2.6911 | Accept | 0.5 | 7.689 | 2.6911 | H2 | 4 | Stable | 0.7 | 104 | 139 | 155 | 135.8333 | 0.7 | 104 | 139 | 155 | 135.8333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_008 | Project_082 | RISK007 | Project_082_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Task 30 - Pylon Procurement | Person_619 | 2017-04-13 | 2018-07-21 | 1 | 5.5361 | 1.384 | Accept | 1 | 5.5361 | 1.384 | H2 | 4 | Stable | 0.9 | 86 | 125 | 145 | 121.8333 | 0.9 | 86 | 125 | 145 | 121.8333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK006 | Project_060_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Secure material Handling | Person_033 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.5 | 5.126 | 2.563 | Accept | 0.5 | 5.126 | 1.5378 | H2 | 4 | Stable | 0.8 | 113 | 134 | 149 | 133 | 0.8 | 113 | 134 | 149 | 133 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.4 | 2.563 | 1.0252 | Reduce | 0.4 | 2.563 | 1.0252 | H3 | 3 | Stable | 0.7 | 93 | 121 | 146 | 120.5 | 0.1 | 14 | 45 | 64 | 43 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.35 | 1.8788 | 0.37576 | Accept | 0.35 | 1.5031 | 0.22546 | H3 | 3 | Stable | 0.8 | 109 | 130 | 155 | 130.6667 | 0.8 | 109 | 130 | 155 | 130.6667 | 20 | 0 | 0 | 12
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.25 | 1.8788 | 0.37576 | Accept | 0.25 | 1.5031 | 0.22546 | H3 | 3 | Stable | 0.5 | 84 | 130 | 156 | 126.6667 | 0.5 | 84 | 130 | 156 | 126.6667 | 20 | 0 | 0 | 12
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_676 | 2016-10-21 01:00 | 2019-08-20 | 0.5 | 1.0334 | 0.20667 | Accept | 0.3 | 0.80789 | 0.12118 | H3 | 3 | Stable | 0.7 | 89 | 136 | 157 | 131.6667 | 0.7 | 89 | 136 | 157 | 131.6667 | 21.8182 | 40 | 0 | 13.0909
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK036 | Project_042_RISK036 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 2 | Person_455 | 2019-05-24 | 2020-05-22 | 0.25 | 1.8788 | 0.18788 | Accept | 0.2 | 1.8225 | 0.12757 | H2 | 4 | Stable | 0.8 | 118 | 139 | 147 | 136.8333 | 0.8 | 118 | 139 | 147 | 136.8333 | 3 | 20 | 0 | 1.8
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.2 | 1.8788 | 0.18788 | Accept | 0.2 | 1.5031 | 0.12024 | H3 | 3 | Stable | 0.7 | 115 | 134 | 159 | 135 | 0.7 | 115 | 134 | 159 | 135 | 20 | 0 | 0 | 12
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK039 | Project_042_RISK039 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality Issues 16th August to 15th August | Person_540 | 2020-01-06 | 2021-01-04 | 0.1 | 1.8788 | 0.18788 | Accept | 0.08 | 1.5031 | 0.12024 | H2 | 4 | Stable | 0.8 | 110 | 121 | 150 | 124 | 0.8 | 110 | 121 | 150 | 124 | 20 | 20 | 0 | 12
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK033 | Project_042_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st April to 30 June | Person_455 | 2019-08-22 | 2019-11-20 | 0.2 | 0.79775 | 0.039887 | Accept | 0.15 | 0.79775 | 0.039887 | H2 | 4 | Stable | 0.7 | 99 | 139 | 144 | 133.1667 | 0.7 | 99 | 139 | 144 | 133.1667 | 0 | 25 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK035 | Project_042_RISK035 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st October to 31st December | Person_455 | 2021-02-20 | 2021-05-22 | 0.2 | 10.3335 | 1.0334 | Accept | 0.15 | 10.3335 | 1.0334 | H2 | 4 | Stable | 0.7 | 80 | 121 | 142 | 117.6667 | 0.7 | 80 | 121 | 142 | 117.6667 | 0 | 25 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK034 | Project_042_RISK034 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st July to 30 September | Person_455 | 2020-11-20 | 2021-02-19 | 0.2 | 11.2729 | 2.2546 | Accept | 0.15 | 11.2729 | 2.2546 | H2 | 4 | Stable | 0.8 | 112 | 121 | 144 | 123.3333 | 0.8 | 112 | 121 | 144 | 123.3333 | 0 | 25 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK040 | Project_042_RISK040 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st May to 30 Oct | Person_455 | 2019-09-21 | 2020-03-21 | 0.1 | 3.7576 | 0.18788 | Accept | 0.07 | 3.7576 | 0.56365 | H2 | 4 | Stable | 0.8 | 105 | 125 | 157 | 127 | 0.8 | 105 | 125 | 157 | 127 | 0 | 30 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK042 | Project_042_RISK042 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st February to 14th July | Person_455 | 2020-06-23 | 2020-12-03 | 0.1 | 1.8788 | 0.46971 | Accept | 0.08 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.9 | 107 | 136 | 160 | 135.1667 | 0.9 | 107 | 136 | 160 | 135.1667 | 20 | 20 | 0 | 12
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK048 | Project_042_RISK048 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | On the Job Training. | Person_371 | 2018-03-02 | 2019-02-05 | 0.85 | 2.1043 | 1.7886 | Reduce | 0.5 | 2.1043 | 1.0521 | H1 | 5 | Stable | 0.6 | 116 | 129 | 145 | 129.5 | 0.1 | 9 | 59 | 63 | 51.3333 | 0 | 41.1765 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK041 | Project_042_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st Jan | Person_455 | 2020-03-23 | 2020-06-22 | 0.1 | 4.6971 | 0.93941 | Accept | 0.08 | 3.7576 | 0.56365 | H2 | 4 | Stable | 0.6 | 114 | 125 | 156 | 128.3333 | 0.6 | 114 | 125 | 156 | 128.3333 | 20 | 20 | 0 | 12
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Local customer Engineers in country | Person_455 | 2018-12-20 | 2021-05-22 | 0.05 | 1.8788 | 0.46971 | Accept | 0.05 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.7 | 107 | 127 | 141 | 126 | 0.7 | 107 | 127 | 141 | 126 | 20 | 0 | 0 | 12
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK049 | Project_042_RISK049 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Industry STTE Upkeep. | Person_371 | 2018-03-02 | 2019-02-05 | 0.85 | 1.3152 | 1.1179 | Reduce | 0.5 | 1.3152 | 0.65759 | H2 | 4 | Stable | 0.6 | 89 | 136 | 143 | 129.3333 | 0.4 | 23 | 52 | 66 | 49.5 | 0 | 41.1765 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK026 | Project_042_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st Jan to 31st March | Person_455 | 2020-05-23 | 2020-08-20 | 0.25 | 1.8788 | 0.46971 | Accept | 0.15 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.9 | 87 | 121 | 159 | 121.6667 | 0.9 | 87 | 121 | 159 | 121.6667 | 20 | 40 | 0 | 12
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK025 | Project_042_RISK025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to 31 Dec | Person_455 | 2020-09-20 | 2021-05-22 | 0.2 | 2.2828 | 0.31959 | Accept | 0.15 | 2.2828 | 0.31959 | H2 | 4 | Stable | 0.5 | 107 | 128 | 147 | 127.6667 | 0.5 | 107 | 128 | 147 | 127.6667 | 0 | 25 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK028 | Project_042_RISK028 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st July to 30th September | Person_455 | 2020-11-20 | 2021-02-19 | 0.25 | 0.56365 | 0.11273 | Accept | 0.15 | 0.28182 | 0.028182 | H2 | 4 | Stable | 0.7 | 103 | 124 | 143 | 123.6667 | 0.7 | 103 | 124 | 143 | 123.6667 | 50 | 40 | 0 | 30
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK027 | Project_042_RISK027 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st April to 30th June | Person_455 | 2020-08-21 | 2020-09-19 | 0.25 | 4.6971 | 0.93941 | Accept | 0.15 | 3.7576 | 0.67638 | H2 | 4 | Stable | 0.8 | 119 | 139 | 156 | 138.5 | 0.8 | 119 | 139 | 156 | 138.5 | 20 | 40 | 0 | 12
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK044 | Project_042_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2018-02-20 | 2018-12-21 | 0.32 | 6.5759 | 2.1043 | Reduce | 0.17 | 6.5759 | 1.1179 | H2 | 4 | Stable | 0.9 | 113 | 135 | 144 | 132.8333 | 0.1 | 4 | 59 | 62 | 50.3333 | 0 | 46.875 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK037 | Project_042_RISK037 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 1 | Person_455 | 2020-05-23 | 2021-05-22 | 0.14 | 1.8788 | 0.18788 | Accept | 0.14 | 1.5031 | 0.12024 | H2 | 4 | Stable | 0.8 | 94 | 126 | 142 | 123.3333 | 0.8 | 94 | 126 | 142 | 123.3333 | 20 | 0 | 0 | 12
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK047 | Project_042_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables | Person_455 | 2020-11-20 | 2021-05-22 | 0.2 | 2.484 | 1.242 | Accept | 0.1 | 0 | 0 | H2 | 4 | Stable | 0.7 | 87 | 137 | 141 | 129.3333 | 0.7 | 87 | 137 | 141 | 129.3333 | 100 | 50 | 0 | 60
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK024 | Project_042_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2019-09-21 | 2020-09-19 | 0.33 | 9.3941 | 3.1001 | Reduce | 0.15 | 7.5153 | 1.1273 | H2 | 4 | Stable | 0.8 | 106 | 121 | 160 | 125 | 0.2 | 17 | 46 | 64 | 44.1667 | 20 | 54.5455 | 0 | 12
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK022 | Project_042_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2017-09-20 | 2018-09-20 | 0.2 | 2.2589 | 0.22589 | Accept | 0.18 | 2.2589 | 0.22589 | H2 | 4 | Stable | 0.7 | 84 | 128 | 145 | 123.5 | 0.7 | 84 | 128 | 145 | 123.5 | 0 | 10 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK043 | Project_042_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st December | Person_455 | 2021-03-23 | 2021-05-22 | 0.1 | 0.56365 | 0.11273 | Accept | 0.08 | 0.28182 | 0.028182 | H3 | 3 | Stable | 0.7 | 108 | 131 | 160 | 132 | 0.7 | 108 | 131 | 160 | 132 | 50 | 20 | 1 | 30.6
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-20 21:00 | 2017-08-19 21:00 | 0.1 | 53.0293 | 5.3029 | Reduce | 0.1 | 53.0293 | 5.3029 | H3 | 3 | Stable | 0.9 | 97 | 121 | 155 | 122.6667 | 0.2 | 4 | 46 | 74 | 43.6667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK045 | Project_042_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2019-01-22 | 2019-05-23 | 0.25 | 3.908 | 0.97699 | Reduce | 0.25 | 3.908 | 0.97699 | H2 | 4 | Stable | 0.6 | 101 | 140 | 155 | 136 | 0.4 | 10 | 41 | 65 | 39.8333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK046 | Project_042_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables - June | Person_455 | 2018-11-21 | 2020-11-19 | 0.2 | 1.8788 | 0.46971 | Accept | 0.1 | 1.1273 | 0.11273 | H2 | 4 | Stable | 0.6 | 92 | 122 | 142 | 120.3333 | 0.6 | 92 | 122 | 142 | 120.3333 | 40 | 50 | 0 | 24
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-20 21:00 | 2017-08-19 21:00 | 0.1 | 7.7469 | 0.77469 | Reduce | 0.1 | 7.7469 | 0.77469 | H3 | 3 | Stable | 0.8 | 117 | 124 | 151 | 127.3333 | 0.1 | 10 | 54 | 70 | 49.3333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK023 | Project_042_RISK023 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2018-09-21 | 2019-09-20 | 0.2 | 11.3437 | 0.56718 | Accept | 0.1 | 11.3437 | 0.56718 | H2 | 4 | Stable | 0.5 | 95 | 136 | 146 | 130.8333 | 0.5 | 95 | 136 | 146 | 130.8333 | 0 | 50 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-184 | Project_032_Risk-184 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Manufacture of new Sub-systems | Person_629 | 2016-04-08 | 2018-02-18 21:00 | 0.33 | 0.05293 | 0.015879 | Accept | 0.5 | 0.05293 | 0.015879 | H1 | 5 | Stable | 0.8 | 105 | 135 | 149 | 132.3333 | 0.8 | 105 | 135 | 149 | 132.3333 | 0 | -51.5152 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS019 | Project_025_RS019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Product Component Failure | Person_619 | 2017-03-23 | 2019-08-07 | 0.7 | 0.82924 | 0.58047 | Reduce | 0.3 | 0.82924 | 0.24877 | H2 | 4 | Stable | 0.5 | 112 | 135 | 145 | 132.8333 | 0.1 | 34 | 57 | 76 | 56.3333 | 0 | 57.1429 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_373 | 2012-08-21 | 2019-08-07 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 2.2054 | 1.3453 | H1 | 5 | Stable | 0.5 | 110 | 124 | 153 | 126.5 | 0.2 | 14 | 57 | 79 | 53.5 | 0 | 0 | 0 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-020 | Project_077_T-020 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Cybersecurity | Person_560 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.1 | 1.3478 | 0.13478 | Reduce | 0.1 | 1.3478 | 0.13478 | H3 | 3 | Stable | 0.5 | 115 | 140 | 158 | 138.8333 | 0.1 | 22 | 47 | 79 | 48.1667 | 0 | 0 | 1 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-005 | Project_077_T-005 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | SSTP/SSTR overspend | Person_667 | 2018-10-22 01:00 | 2020-02-21 01:00 | 0.3 | 10.5469 | 3.1641 | Reduce | 0.3 | 10.5469 | 3.1641 | H2 | 4 | Stable | 0.6 | 119 | 133 | 145 | 132.6667 | 0.4 | 33 | 48 | 62 | 47.8333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-006 | Project_077_T-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Functionality | Person_667 | 2018-08-22 01:00 | 2020-02-21 01:00 | 0.2 | 3.774 | 0.7548 | -- | 0.2 | 3.774 | 0.7548 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-007 | Project_077_T-007 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Rig Failure or Damage | Person_574 | 2018-09-21 01:00 | 2020-12-08 01:00 | 0.3 | 2.033 | 0.6099 | Reduce | 0.3 | 2.033 | 0.6099 | H2 | 4 | Stable | 0.5 | 103 | 128 | 148 | 127.1667 | 0.3 | 13 | 57 | 60 | 50.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK029 | Project_042_RISK029 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st October to 31st December | Person_455 | 2020-11-20 | 2021-05-22 | 0.25 | 1.2744 | 0.63719 | Accept | 0.1 | 1.2744 | 0.63719 | H2 | 4 | Stable | 0.9 | 102 | 133 | 146 | 130 | 0.9 | 102 | 133 | 146 | 130 | 0 | 60 | 0 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-023 | Project_077_T-023 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Legacy abilities | Person_706 | 2018-10-22 01:00 | 2020-02-21 01:00 | 0.1 | 1.0019 | 0.10019 | Avoid | 0.1 | 1.0019 | 0.10019 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-19 21:00 | 0.05 | 2.5488 | 0.89207 | Accept | 0.05 | 2.5488 | 0.89207 | H3 | 3 | Stable | 0.8 | 100 | 124 | 160 | 126 | 0.8 | 100 | 124 | 160 | 126 | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS020 | Project_025_RS020 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Plant Machinery failure | Person_619 | 2017-03-23 | 2019-08-07 | 0.3 | 0.98068 | 0.2942 | Accept | 0.3 | 0.98068 | 0.2942 | H2 | 4 | Stable | 0.9 | 81 | 126 | 150 | 122.5 | 0.9 | 81 | 126 | 150 | 122.5 | 0 | 0 | 0 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-001 | Project_077_T-001 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Increased Interface changes | Person_544 | 2018-07-22 | 2018-10-20 01:00 | 0.5 | 2.1566 | 1.0783 | Transfer | 0.3 | 2.1566 | 0.64697 | H2 | 4 | Stable | [10 empty] | 0 | 40 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK024 | Project_069_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Training | Person_479 | 2018-03-16 01:00 | 2021-07-16 | 0.5 | 0.63719 | 0.50975 | Accept | 0.5 | 1.4974 | 1.1979 | H2 | 4 | Stable | 0.5 | 104 | 129 | 154 | 129 | 0.5 | 104 | 129 | 154 | 129 | -135 | 0 | 0 | -81
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK020 | Project_069_RISK020 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Directives may have a wider impact and requires additional work. | Person_530 | 2018-03-16 01:00 | 2021-07-16 | 0.35 | 1.126 | 0.22519 | Accept | 0.35 | 1.126 | 0.22519 | H2 | 4 | Stable | 0.8 | 114 | 126 | 153 | 128.5 | 0.8 | 114 | 126 | 153 | 128.5 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_089 | RISK011 | Project_089_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Critical Resources / Skills | Person_503 | 2018-02-20 01:00 | 2020-05-23 | 0.3 | 0.82835 | 0.49701 | Accept | 0.3 | 0.82835 | 0.49701 | H2 | 4 | Stable | 0.6 | 97 | 135 | 141 | 129.6667 | 0.6 | 97 | 135 | 141 | 129.6667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK007 | Project_069_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Without dedicated Datastore hardware, lots of re-work is required | Person_479 | 2018-05-24 | 2018-10-20 01:00 | 0.8 | 2.4261 | 0.72784 | Accept | 0.8 | 2.4261 | 0.72784 | H2 | 4 | Stable | 0.5 | 86 | 131 | 146 | 126 | 0.5 | 86 | 131 | 146 | 126 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_089 | RISK013 | Project_089_RISK013 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Software incompatibility issue | Person_503 | 2018-10-22 01:00 | 2018-12-22 01:00 | 0.2 | 1.593 | 0.39825 | Accept | 0.2 | 1.593 | 0.39825 | H3 | 3 | Stable | 0.6 | 119 | 132 | 155 | 133.6667 | 0.6 | 119 | 132 | 155 | 133.6667 | 0 | 0 | 1 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-025 | Project_077_T-025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Delayed Config File delivery | Person_163 | 2019-05-24 | 2020-02-21 01:00 | 0.5 | 3.3696 | 1.6848 | Avoid | 0.5 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK009 | Project_069_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sizings assume that at least 1 software engineer on the project has at least 2 years experience | Person_479 | 2018-03-16 01:00 | 2021-07-16 | 0.6 | 0.5993 | 0.23972 | Accept | 0.6 | 0.5993 | 0.23972 | H2 | 4 | Stable | 0.5 | 108 | 129 | 150 | 129 | 0.5 | 108 | 129 | 150 | 129 | 0 | 0 | 0 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-002 | Project_077_T-002 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Legacy testing Repeatability | Person_708 | 2018-10-22 01:00 | 2019-05-11 | 0.3 | 3.186 | 1.593 | Accept | 0.3 | 3.186 | 1.593 | H2 | 4 | Stable | 0.9 | 120 | 129 | 156 | 132 | 0.9 | 120 | 129 | 156 | 132 | 0 | 0 | 0 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-003 | Project_077_T-003 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | SW Resource availability | Person_508 | 2018-05-23 | 2020-02-21 01:00 | 0.5 | 25.1598 | 12.5799 | Reduce | 0.5 | 25.1598 | 12.5799 | H1 | 5 | Worsening | 0.7 | 100 | 132 | 142 | 128.3333 | 0.1 | 12 | 59 | 76 | 54 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK026 | Project_069_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional Representative HW | Person_257 | 2018-03-16 01:00 | 2021-07-16 | 0.25 | 3.1541 | 1.2616 | Accept | 0.25 | 3.1541 | 1.2616 | H2 | 4 | Stable | 0.9 | 106 | 124 | 155 | 126.1667 | 0.9 | 106 | 124 | 155 | 126.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-026 | Project_077_T-026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Insufficient Config Option capacity | Person_706 | 2018-04-22 | 2020-02-21 01:00 | 0.2 | 1.0019 | 0.20038 | Avoid | 0.05 | 1.0019 | 0.050095 | H3 | 3 | Stable | [10 empty] | 0 | 75 | 1 | 2.25
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-004 | Project_077_T-004 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Debt | Person_667 | 2018-10-20 01:00 | 2020-02-21 01:00 | 0.2 | 2.1566 | 0.43131 | Reduce | 0.2 | 2.1566 | 0.43131 | H3 | 3 | Stable | 0.9 | 114 | 137 | 142 | 134 | 0.3 | 13 | 58 | 63 | 51.3333 | 0 | 0 | 1 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | OPRisk-001 | Project_077_OPRisk-001 | Opportunitity | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Opportunity that fewer than expected customer problem reports are raised. | Person_706 | 2019-03-24 | 2020-02-21 01:00 | 0.5 | 3.3642 | 1.6821 | -- | 0.5 | 3364.2293 | 1682.1146 | H1 | 5 | Stable | [10 empty] | -99900 | 0 | 0 | -59940
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-010 | Project_077_T-010 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Technical Directorate changes to SW/data artefacts - Internal Requirement | Person_574 | 2018-11-21 01:00 | 2020-02-21 01:00 | 0.4 | 1.887 | 0.7548 | Reduce | 0.4 | 1.887 | 0.7548 | H2 | 4 | Stable | 0.6 | 119 | 135 | 143 | 133.6667 | 0.2 | 25 | 41 | 67 | 42.6667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--16 | Project_021_Risk--16 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of weather | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.4 | 0 | 0 | H2 | 4 | Stable | 0.7 | 101 | 133 | 147 | 130 | 0.1 | 15 | 51 | 71 | 48.3333 |  | 20 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-032 | Project_077_T-032 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Requirement Updated from Issue 4 to 6 | Person_574 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.5 | 3.3696 | 1.6848 | Avoid | 0.1 | 3.3696 | 0.33696 | H3 | 3 | Stable | [10 empty] | 0 | 80 | 1 | 2.4
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--15 | Project_021_Risk--15 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to lack of personnel resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 102 | 123 | 153 | 124.5 | 0.2 | 33 | 52 | 77 | 53 |  | 40 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-011 | Project_077_T-011 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Bus Scheduling table changes affecting proven interface | Person_706 | 2019-05-24 | 2020-02-21 01:00 | 0.2 | 0.92103 | 0.18421 | Reduce | 0.2 | 0.92103 | 0.18421 | H3 | 3 | Stable | 0.9 | 104 | 124 | 144 | 124 | 0.1 | 3 | 56 | 74 | 50.1667 | 0 | 0 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK004 | Project_079_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 8.8685 | 1.7737 | Reduce | 0.1 | 8.8685 | 0.88685 | H3 | 3 | Stable | 0.6 | 88 | 129 | 159 | 127.1667 | 0.3 | 20 | 48 | 66 | 46.3333 | 0 | 50 | 0 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-033 | Project_077_T-033 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | PDA availability | Person_574 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.4 | 3.0327 | 1.2131 | Avoid | 0.4 | 3.0327 | 1.2131 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--14 | Project_021_Risk--14 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to late Trials Approval | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.6 | 108 | 137 | 155 | 135.1667 | 0.2 | 30 | 52 | 61 | 49.8333 |  | 66.6667 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK026 | Project_079_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Clause on Joint Proposal | Person_261 | 2018-05-04 | 2019-05-23 | 0.3 | 30.653 | 9.1959 | -- | 0.3 | 30.653 | 9.1959 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-016 | Project_077_T-016 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Autotest | Person_574 | 2018-09-09 01:00 | 2020-02-21 01:00 | 0.5 | 2.1341 | 1.067 | Reduce | 0.5 | 2.1341 | 1.067 | H2 | 4 | Stable | 0.6 | 119 | 136 | 158 | 136.8333 | 0.2 | 32 | 55 | 62 | 52.3333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK014 | Project_079_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 0.05 | 21.725 | 1.0862 | Reduce | 0.05 | 21.725 | 1.0862 | H3 | 3 | Stable | 0.9 | 105 | 139 | 154 | 135.8333 | 0.2 | 35 | 41 | 76 | 45.8333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK025 | Project_069_RISK025 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Additional in-country presence (all WP's) | Person_257 | 2018-03-16 01:00 | 2021-07-16 | 0.5 | 0 | 0 | Accept | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.5 | 106 | 122 | 147 | 123.5 | 0.5 | 106 | 122 | 147 | 123.5 |  | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK022 | Project_069_RISK022 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Handbooks - Level of SW Change may increase (Not increase in scope). | Person_056 | 2018-03-16 01:00 | 2021-07-16 | 0.4 | 2.6957 | 0.80871 | Accept | 0.4 | 2.6957 | 0.80871 | H3 | 3 | Stable | 0.6 | 89 | 121 | 143 | 119.3333 | 0.6 | 89 | 121 | 143 | 119.3333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--13 | Project_021_Risk--13 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Critical or Safety PR arises in Final build /Decision Point concludes new release req | Person_174 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.5 | 80 | 135 | 144 | 127.3333 | 0.3 | 9 | 49 | 71 | 46 | 0 | 50 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK005 | Project_079_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 3.7631 | 2.2578 | -- | 0.5 | 3.7631 | 1.8815 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-012 | Project_077_T-012 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Management cost increases for BMN | Person_667 | 2018-03-01 01:00 | 2020-02-21 01:00 | 0.21 | 1.5725 | 0.33022 | Avoid | 0.21 | 1.5725 | 0.33022 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--12 | Project_021_Risk--12 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.6 | 6.6769 | 4.0061 | Reduce | 0.4 | 6.6769 | 2.6707 | H2 | 4 | Stable | 0.6 | 91 | 136 | 152 | 131.1667 | 0.3 | 18 | 49 | 72 | 47.6667 | 0 | 33.3333 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK016 | Project_079_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_104 | 2017-09-29 01:00 | 2019-05-23 | 0.8 | 1.9552 | 1.5642 | Avoid | 0.3 | 1.9552 | 0.58657 | H3 | 3 | Stable | [10 empty] | 0 | 62.5 | 0 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-034 | Project_077_T-034 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Simulator update not viable if needed | Person_707 | 2018-10-22 01:00 | 2020-02-21 01:00 | 0.5 | 0.74806 | 0.37403 | Avoid | 0.5 | 0.74806 | 0.37403 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-018 | Project_077_T-018 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Config system changes | Person_574 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.15 | 0 | 0 | Accept | 0.15 | 0 | 0 | H3 | 3 | Stable | 0.8 | 103 | 123 | 150 | 124.1667 | 0.8 | 103 | 123 | 150 | 124.1667 |  | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK022 | Project_079_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Equipment | Person_104 | 2018-01-14 01:00 | 2019-08-20 | 0.15 | 7.321 | 1.0982 | Reduce | 0.15 | 7.321 | 1.0982 | H3 | 3 | Stable | 0.7 | 85 | 129 | 148 | 124.8333 | 0.2 | 16 | 43 | 77 | 44.1667 | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--10 | Project_021_Risk--10 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Stable | 0.5 | 109 | 140 | 160 | 138.1667 | 0.2 | 31 | 46 | 69 | 47.3333 | 0 | 57.1429 | 0 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-013 | Project_077_T-013 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | More customer failures than anticipated | Person_706 | 2019-02-21 01:00 | 2020-02-21 01:00 | 0.2 | 3.3809 | 0.67617 | Reduce | 0.2 | 3.3809 | 0.67617 | H3 | 3 | Stable | 0.6 | 82 | 132 | 150 | 126.6667 | 0.1 | 1 | 50 | 67 | 44.6667 | 0 | 0 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK002 | Project_079_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2022-05-22 | 0.15 | 26.7842 | 4.0176 | Avoid | 0.15 | 26.7842 | 4.0176 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--32 | Project_021_Risk--32 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Lack of Customer resource to provide timely input to Acceptance and Closure activities | Person_766 | 2018-10-22 01:00 | 2019-04-23 | 0.8 | 0 | 0 | Reduce | 0.4 | 0 | 0 | H2 | 4 | Stable | 0.9 | 111 | 134 | 146 | 132.1667 | 0.1 | 27 | 57 | 76 | 55.1667 |  | 50 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK024 | Project_079_RISK024 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Procurement/Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 0.5 | 14.4992 | 7.2496 | Reduce | 0.5 | 14.4992 | 7.2496 | H1 | 5 | Stable | 0.9 | 93 | 128 | 143 | 124.6667 | 0.4 | 12 | 48 | 69 | 45.5 | 0 | 0 | 0 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-014 | Project_077_T-014 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Extra Release | Person_667 | 2020-06-23 | 2020-11-20 01:00 | 0.1 | 13.4785 | 1.3478 | Avoid | 0.1 | 13.4785 | 1.3478 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--18 | Project_021_Risk--18 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.6 | 98 | 127 | 154 | 126.6667 | 0.3 | 25 | 54 | 66 | 51.1667 | 50 | 28.5714 | 0 | 30
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK031 | Project_079_RISK031 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Line Closure Savings | Person_683 | 2020-12-21 01:00 | 2021-04-22 | 0.8 | 2.3927 | 1.9142 | -- | 0.8 | 2.3927 | 1.9142 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--28 | Project_021_Risk--28 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort required to agree protocl for Client Server | Person_766 | 2018-03-23 | 2019-03-23 | 0.8 | 1.1522 | 0.92174 | Reduce | 0.4 | 1.1522 | 0.46087 | H2 | 4 | Stable | 0.9 | 102 | 135 | 148 | 131.6667 | 0.1 | 18 | 43 | 68 | 43 | 0 | 50 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-115 | Project_011_Risk-115 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | SMEs are unavailable to support project activites | Person_431 | 2016-07-21 | 2018-10-21 01:00 | 0.2 | 0 | 0 | Avoid | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 50 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK030 | Project_079_RISK030 | Opportunitity | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Production Build / Touch Labour | Person_683 | 2018-11-21 01:00 | 2020-04-22 | 0.8 | 46.4619 | 37.1695 | -- | 0.8 | 46.4619 | 37.1695 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--05 | Project_021_Risk--05 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification delays | Person_207 | 2018-02-20 01:00 | 2018-10-05 01:00 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.7 | 107 | 139 | 157 | 136.6667 | 0.2 | 13 | 59 | 69 | 53 |  | 50 | 1
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-058 | Project_011_Risk-058 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme delays | Person_147 | 2013-11-20 01:00 | 2019-01-20 01:00 | 0.25 | 1.5013 | 0.37532 | Reduce | 0.4 | 1.5013 | 0.60051 | H1 | 5 | Stable | 0.7 | 112 | 128 | 157 | 130.1667 | 0.3 | 39 | 41 | 72 | 45.8333 | 0 | -60 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--35 | Project_021_Risk--35 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Delay to sub-system and other Components - dependencies due to supply chain dependencies | Person_615 | 2018-01-21 01:00 | 2018-03-22 | 0.4 | 2.1388 | 0.21388 | Accept | 0.2 | 2.1388 | 0.21388 | H3 | 3 | Stable | 0.9 | 85 | 139 | 145 | 131 | 0.9 | 85 | 139 | 145 | 131 | 0 | 50 | 1 | 1.5
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-131 | Project_011_Risk-131 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Support team have not covered all obligations in support contract | Person_147 | 2016-05-24 | 2018-10-21 01:00 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--04 | Project_021_Risk--04 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Final Qual test report delayed due to insufficient supply chain resource | Person_615 | 2018-09-20 01:00 | 2018-10-21 01:00 | 0.2 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.5 | 110 | 140 | 150 | 136.6667 | 0.1 | 16 | 50 | 70 | 47.6667 |  | 50 | 1
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-137 | Project_011_Risk-137 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Subsystem will not match Fidelity of Customer - does not accept | Person_147 | 2018-02-16 01:00 | 2018-09-20 01:00 | 0.4 | 0.11876 | 0.047505 | Avoid | 0.2 | 0.11876 | 0.023752 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--03 | Project_021_Risk--03 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.8 | 80 | 130 | 150 | 125 | 0.2 | 15 | 44 | 72 | 43.8333 | 0 | 33.3333 | 0 | 0
2018-07-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-019 | Project_077_T-019 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | New stakeholders/Changeovers | Person_667 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.3 | 0.34776 | 0.034776 | Accept | 0.3 | 0.34776 | 0.034776 | H2 | 4 | Stable | 0.5 | 117 | 133 | 150 | 133.1667 | 0.5 | 117 | 133 | 150 | 133.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--25 | Project_021_Risk--25 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of supporting resource | Person_080 | 2018-06-22 | 2019-02-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.7 | 85 | 134 | 146 | 127.8333 | 0.1 | 24 | 57 | 67 | 53.1667 |  | 60 | 1
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2018-04-22 | 2019-01-20 01:00 | 0.2 | 0.62279 | 0.12456 | Avoid | 0.2 | 0.62279 | 0.12456 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--02 | Project_021_Risk--02 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_061 | 2018-02-20 01:00 | 2019-03-23 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.9 | 102 | 130 | 154 | 129.3333 | 0.2 | 36 | 54 | 70 | 53.6667 | 80 | 66.6667 | 0 | 48
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-11-20 01:00 | 0.1 | 1.8854 | 0.18854 | Reduce | 0.1 | 1.8854 | 0.18854 | H3 | 3 | Stable | 0.5 | 87 | 122 | 153 | 121.3333 | 0.4 | 34 | 41 | 66 | 44 | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--24 | Project_021_Risk--24 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of equipment | Person_080 | 2018-06-22 | 2019-02-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.9 | 98 | 122 | 150 | 122.6667 | 0.3 | 11 | 58 | 68 | 51.8333 |  | 60 | 1
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2018-06-23 | 2019-01-20 01:00 | 0.4 | 1.4138 | 0.56551 | Reduce | 0.5 | 1.4138 | 0.70689 | H1 | 5 | Stable | 0.8 | 91 | 131 | 148 | 127.1667 | 0.4 | 38 | 42 | 74 | 46.6667 | 0 | -25 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-12-16 01:00 | 0.2 | 0.19206 | 0.038413 | -- | 0.2 | 0.19206 | 0.038413 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--21 | Project_021_Risk--21 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 115 | 126 | 159 | 129.6667 | 0.1 | 27 | 56 | 67 | 53 |  | 40 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-08-22 01:00 | 2019-01-20 01:00 | 0.4 | 0.58017 | 0.23207 | Avoid | 0.4 | 0.58017 | 0.23207 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--09 | Project_021_Risk--09 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_470 | 2018-02-20 01:00 | 2018-08-21 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.5 | 113 | 136 | 142 | 133.1667 | 0.2 | 16 | 47 | 65 | 44.8333 |  | 40 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--34 | Project_021_Risk--34 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Delay due to poor weather | Person_615 | 2018-03-23 | 2018-10-21 01:00 | 0.5 | 0.49834 | 0.12459 | Accept | 0.5 | 0.49834 | 0.12459 | H2 | 4 | Stable | 0.9 | 106 | 134 | 141 | 130.5 | 0.9 | 106 | 134 | 141 | 130.5 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-11-20 01:00 | 0.3 | 0.32389 | 0.097168 | Reduce | 0.3 | 0.32389 | 0.097168 | H2 | 4 | Stable | 0.5 | 110 | 128 | 142 | 127.3333 | 0.4 | 17 | 53 | 72 | 50.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--08 | Project_021_Risk--08 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-02-20 01:00 | 2018-10-05 01:00 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 81 | 140 | 160 | 133.5 | 0.2 | 28 | 56 | 77 | 54.8333 |  | 80 | 1
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--07 | Project_021_Risk--07 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 0.6 | 17.2826 | 10.3696 | Reduce | 0.3 | 17.2826 | 5.1848 | H2 | 4 | Worsening | 0.5 | 103 | 135 | 143 | 131 | 0.4 | 11 | 47 | 70 | 44.8333 | 0 | 50 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures during SAT | Person_182 | 2018-06-23 | 2019-01-20 01:00 | 0.2 | 0.19206 | 0.038413 | -- | 0.2 | 0.19206 | 0.038413 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_431 | 2017-05-24 | 2018-10-19 01:00 | 0.3 | 0.11933 | 0.035799 | -- | 0.3 | 0.022161 | 0.0066484 | H3 | 3 | Stable | [10 empty] | 81.4286 | 0 | 0 | 48.8571
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-117 | Project_011_Risk-117 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Avaliability for testing/reviews | Person_147 | 2018-04-06 | 2018-10-21 01:00 | 0.35 | 0 | 0 | Avoid | 0.35 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--17 | Project_021_Risk--17 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delays due to technical performacne | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.9 | 120 | 130 | 153 | 132.1667 | 0.1 | 38 | 47 | 61 | 47.8333 |  | 33.3333 | 1
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-129 | Project_011_Risk-129 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Signature of Work Authorisation documents | Person_422 | 2017-05-24 | 2018-09-18 01:00 | 0.4 | 0.12643 | 0.050573 | -- | 0.4 | 0.12643 | 0.050573 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--39 | Project_021_Risk--39 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Delay to completion of product upgrade | Person_080 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.6 | 84 | 140 | 155 | 133.1667 | 0.3 | 26 | 55 | 74 | 53.3333 |  | 80 | 1
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--27 | Project_021_Risk--27 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PR rectification | Person_207 | 2018-02-20 01:00 | 2018-11-05 01:00 | 0.1 | 1.6166 | 0.16166 | Accept | 0.1 | 1.6166 | 0.16166 | H2 | 4 | Stable | 0.8 | 101 | 130 | 144 | 127.5 | 0.8 | 101 | 130 | 144 | 127.5 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Unreliability of Hardware | Person_431 | 2016-06-23 | 2018-11-18 01:00 | 0.1 | 1.2124 | 0.18186 | Accept | 0.1 | 1.2124 | 0.18186 | H3 | 3 | Stable | 0.8 | 101 | 131 | 147 | 128.6667 | 0.8 | 101 | 131 | 147 | 128.6667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_147 | 2016-04-21 | 2018-10-21 01:00 | 0.25 | 1.6166 | 0.32332 | Accept | 0.25 | 1.6166 | 0.32332 | H3 | 3 | Stable | 0.5 | 106 | 137 | 146 | 133.3333 | 0.5 | 106 | 137 | 146 | 133.3333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK002 | Project_059_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SW Compatibility | Person_517 | 2017-11-20 01:00 | 2018-10-22 01:00 | 0.1 | 8.8098 | 3.0834 | Accept | 0.1 | 8.8098 | 1.762 | H3 | 3 | Stable | 0.8 | 103 | 126 | 155 | 127 | 0.8 | 103 | 126 | 155 | 127 | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE-10 | Project_067_SE-10 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Configuration baseline unstable for Platform | Person_327 | 2017-10-26 01:00 | 2018-08-18 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.9 | 102 | 128 | 145 | 126.5 | 0.2 | 28 | 54 | 68 | 52 |  | 60 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK012 | Project_059_RISK012 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Failures at Acceptance stage - UNCERTAINTY | Person_278 | 2018-02-18 01:00 | 2019-08-04 | 0.3 | 2.0207 | 0.60622 | Reduce | 0.1 | 2.0207 | 0.20207 | H3 | 3 | Stable | 0.6 | 86 | 126 | 151 | 123.5 | 0.2 | 8 | 56 | 60 | 48.6667 | 0 | 66.6667 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK013 | Project_059_RISK013 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | ICD Errors - Uncertainty | Person_278 | 2017-10-21 01:00 | 2019-06-23 | 0.15 | 0.50826 | 0.40661 | Accept | 0.15 | 0.50826 | 0.40661 | H3 | 3 | Stable | 0.7 | 89 | 127 | 155 | 125.3333 | 0.7 | 89 | 127 | 155 | 125.3333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-001 | Project_067_Risk-001 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Lack of Technical Control plan | Person_327 | 2017-07-21 | 2018-09-20 01:00 | 1 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.5 | 97 | 123 | 158 | 124.5 | 0.3 | 32 | 43 | 72 | 46 |  | 80 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK001 | Project_059_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Critical Personnel | Person_162 | 2017-10-21 01:00 | 2019-08-04 | 0.2 | 2.0207 | 0.40414 | Accept | 0.2 | 2.0207 | 0.40414 | H3 | 3 | Stable | 0.5 | 88 | 138 | 159 | 133.1667 | 0.5 | 88 | 138 | 159 | 133.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_523 | 2018-07-25 | 2018-10-19 01:00 | 0.35 | 2.0207 | 0.20207 | Accept | 0.2 | 2.0207 | 0.20207 | H2 | 4 | Stable | 0.5 | 120 | 129 | 147 | 130.5 | 0.5 | 120 | 129 | 147 | 130.5 | 0 | 42.8571 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | P006 | Project_067_P006 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Complete SDRL deliverables in Schedule | Person_325 | 2018-07-07 | 2018-08-05 | 0.3 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.6 | 92 | 137 | 146 | 131 | 0.3 | 36 | 46 | 74 | 49 |  | -66.6667 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK007 | Project_059_RISK007 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Code Re-Use | Person_517 | 2017-11-29 01:00 | 2019-02-20 01:00 | 0.1 | 2.0207 | 0.20207 | Accept | 0.1 | 2.0207 | 0.20207 | H3 | 3 | Stable | 0.5 | 82 | 122 | 159 | 121.5 | 0.5 | 82 | 122 | 159 | 121.5 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-004 | Project_067_Risk-004 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Creation of Serial Number for formal Software Releases | Person_327 | 2018-07-07 | 2018-10-21 01:00 | 1 | 0 | 0 | Reduce | 1 | 0 | 0 | H1 | 5 | Stable | 0.6 | 101 | 129 | 159 | 129.3333 | 0.1 | 1 | 45 | 61 | 40.3333 |  | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE005 | Project_067_SE005 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Change in Delivery Approach | Person_327 | 2018-07-07 | 2018-08-05 | 0.8 | 0 | 0 | -- | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 75 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK004 | Project_059_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Cyber Security Obligations | Person_592 | 2017-10-21 01:00 | 2019-08-04 | 0.4 | 0.80829 | 0.32332 | Reduce | 0.2 | 0.80829 | 0.16166 | H3 | 3 | Stable | 0.7 | 81 | 134 | 141 | 126.3333 | 0.2 | 24 | 42 | 64 | 42.6667 | 0 | 50 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK009 | Project_059_RISK009 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Safety risk mitigations - UNCERTAINTY | Person_592 | 2017-10-21 01:00 | 2019-08-20 | 0.1 | 3.6256 | 1.4502 | Accept | 0.1 | 3.6256 | 1.4502 | H3 | 3 | Stable | 0.6 | 118 | 123 | 160 | 128.3333 | 0.6 | 118 | 123 | 160 | 128.3333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | RISK015 | Project_028_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Engineering Change | Person_496 | 2018-07-22 | 2018-09-20 01:00 | 0.5 | 6.0991 | 4.0864 | Accept | 0.5 | 6.0991 | 3.3545 | H2 | 4 | Stable | 0.5 | 117 | 135 | 141 | 133 | 0.5 | 117 | 135 | 141 | 133 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Interface implementation | Person_496 | 2018-07-25 | 2018-10-19 01:00 | 0.5 | 1.2124 | 0.12124 | Accept | 0.25 | 1.2124 | 0.12124 | H2 | 4 | Stable | 0.9 | 103 | 126 | 156 | 127.1667 | 0.9 | 103 | 126 | 156 | 127.1667 | 0 | 50 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | FOC Acceptance | Person_499 | 2018-07-25 | 2018-10-19 01:00 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.15 | 8.471 | 1.2706 | H3 | 3 | Stable | 0.6 | 103 | 123 | 155 | 125 | 0.2 | 21 | 42 | 64 | 42.1667 | -99.9999 | 57.1429 | 1 | -58.2857
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of the platforms for modification | Person_496 | 2014-01-21 01:00 | 2019-04-10 | 0.67 | 0.80829 | 0.16166 | Accept | 0.55 | 0.80829 | 0.16166 | H2 | 4 | Stable | 0.6 | 117 | 139 | 145 | 136.3333 | 0.6 | 117 | 139 | 145 | 136.3333 | 0 | 17.9104 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK057 | Project_076_RISK057 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | SubSystem measures not in place and work to implement not in the budget | Person_484 | 2018-02-20 01:00 | 2018-08-21 | 0.1 | 0.60622 | 0.18186 | Accept | 0.1 | 0.60622 | 0.18186 | H3 | 3 | Stable | 0.5 | 94 | 137 | 151 | 132.1667 | 0.5 | 94 | 137 | 151 | 132.1667 | 0 | 0 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK003 | Project_059_RISK003 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Catalyst Requirements | Person_278 | 2017-10-21 01:00 | 2019-02-20 01:00 | 0.2 | 4.3949 | 3.5159 | Accept | 0.2 | 4.3949 | 3.5159 | H3 | 3 | Stable | 0.9 | 92 | 135 | 160 | 132 | 0.9 | 92 | 135 | 160 | 132 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK056 | Project_076_RISK056 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Peer Review Failures | Person_484 | 2018-02-20 01:00 | 2019-11-20 01:00 | 0.2 | 0.64865 | 0.32433 | Accept | 0.2 | 0.64865 | 0.32433 | H3 | 3 | Stable | 0.9 | 98 | 138 | 145 | 132.5 | 0.9 | 98 | 138 | 145 | 132.5 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK014 | Project_059_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Integration Materials - UNCERTAINTY | Person_278 | 2017-10-21 01:00 | 2019-08-04 | 0.3 | 1.7836 | 0.53509 | Accept | 0.3 | 1.7836 | 0.53509 | H3 | 3 | Stable | 0.5 | 116 | 129 | 157 | 131.5 | 0.5 | 116 | 129 | 157 | 131.5 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK071 | Project_076_RISK071 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | System development of components | Person_474 | 2018-03-23 | 2018-11-20 01:00 | 0.8 | 6.6337 | 5.307 | Reduce | 0.1 | 6.6337 | 0.66337 | H3 | 3 | Stable | 0.9 | 94 | 123 | 158 | 124 | 0.2 | 13 | 43 | 76 | 43.5 | 0 | 87.5 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK075 | Project_076_RISK075 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Delay in SW completion due to safety workload | Person_152 | 2018-07-05 | 2019-05-16 | 0.5 | 1.6723 | 0.83613 | Reduce | 0.1 | 1.6723 | 0.16723 | H3 | 3 | Stable | 0.6 | 96 | 137 | 155 | 133.1667 | 0.4 | 21 | 57 | 78 | 54.5 | 0 | 80 | 1 | 2.4
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK070 | Project_076_RISK070 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Component needs to be refigured | Person_484 | 2018-05-23 | 2019-09-26 01:00 | 0.2 | 2.9361 | 2.3489 | Accept | 0.2 | 2.9361 | 2.3489 | H3 | 3 | Stable | 0.7 | 80 | 122 | 151 | 119.8333 | 0.7 | 80 | 122 | 151 | 119.8333 | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-O09 | Project_044_Risk-O09 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Lower System housing space | Person_763 | 2018-11-21 01:00 | 2019-11-21 01:00 | 0.3 | 4.2255 | 1.2677 | Exploit | 0.2 | 4.2255 | 0.84511 | H3 | 3 | Stable | [10 empty] | 0 | 33.3333 | 1 | 1
2018-07-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R008 | Project_044_Risk-R008 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Engineering Skills | Person_505 | 2017-10-21 01:00 | 2018-10-22 01:00 | 0.2 | 1.5695 | 0.3139 | Reduce | 0.1 | 1.2073 | 0.12073 | H3 | 3 | Stable | 0.6 | 83 | 128 | 155 | 125 | 0.2 | 10 | 50 | 66 | 46 | 23.0769 | 50 | 1 | 15.3461
2018-07-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R018 | Project_044_Risk-R018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | EMC (susceptibility) | Person_763 | 2016-03-23 | 2019-11-20 01:00 | 0.5 | 5.795 | 2.8975 | Reduce | 0.1 | 5.795 | 0.5795 | H3 | 3 | Stable | 0.6 | 81 | 126 | 151 | 122.6667 | 0.4 | 35 | 41 | 60 | 43.1667 | 0 | 80 | 1 | 2.4
2018-07-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R001 | Project_044_Risk-R001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | subsystem1 development | Person_358 | 2017-12-22 01:00 | 2019-11-20 01:00 | 0.2 | 17.3851 | 3.477 | Reduce | 0.15 | 17.3851 | 2.6078 | H2 | 4 | Stable | 0.9 | 100 | 123 | 153 | 124.1667 | 0.1 | 3 | 43 | 70 | 40.8333 | 0 | 25 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK020 | Project_058_RISK020 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier Delay | Person_511 | 2018-03-22 | 2018-10-22 01:00 | 0.8 | 3.9148 | 3.1318 | Reduce | 0.4 | 3.9148 | 1.5659 | H2 | 4 | Improving | 0.7 | 88 | 131 | 157 | 128.1667 | 0.2 | 5 | 46 | 68 | 42.8333 | 0 | 50 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R023 | Project_044_Risk-R023 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Integrated performance | Person_358 | 2017-12-15 01:00 | 2020-10-21 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 100 | 126 | 149 | 125.5 | 0.2 | 33 | 48 | 69 | 49 |  | 40 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer find issues with delivered parts or documentation | Person_294 | 2017-05-23 | 2019-08-20 | 0.4 | 19.8087 | 7.9235 | Reduce | 0.25 | 19.8087 | 4.9522 | H2 | 4 | Improving | 0.7 | 85 | 138 | 152 | 131.5 | 0.4 | 39 | 46 | 79 | 50.3333 | 0 | 37.5 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R010 | Project_044_Risk-R010 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Line of sight | Person_763 | 2017-11-20 01:00 | 2019-06-23 | 0.5 | 4.2255 | 2.1128 | Reduce | 0.2 | 4.2255 | 0.84511 | H3 | 3 | Stable | 0.9 | 91 | 129 | 158 | 127.5 | 0.4 | 16 | 41 | 65 | 40.8333 | 0 | 60 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK002 | Project_058_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Obsolescence of key parts | Person_236 | 2017-05-23 | 2019-08-07 | 0.5 | 6.7334 | 3.3667 | Reduce | 0.25 | 6.7334 | 1.6833 | H2 | 4 | Stable | 0.9 | 105 | 131 | 157 | 131 | 0.3 | 8 | 48 | 63 | 43.8333 | 0 | 50 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R003 | Project_044_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Mono vs stereo Component | Person_358 | 2018-01-19 01:00 | 2018-10-22 01:00 | 0.4 | 17.3851 | 6.954 | Reduce | 0.2 | 17.3851 | 3.477 | H3 | 3 | Stable | 0.7 | 99 | 136 | 150 | 132.1667 | 0.1 | 5 | 53 | 64 | 46.8333 | 0 | 50 | 1 | 1.5
2018-07-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R025 | Project_044_Risk-R025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence | Person_763 | 2017-11-20 01:00 | 2019-02-10 01:00 | 0.3 | 3.0182 | 0.90547 | Reduce | 0.1 | 1.2073 | 0.12073 | H3 | 3 | Stable | 0.6 | 99 | 123 | 152 | 123.8333 | 0.4 | 21 | 51 | 64 | 48.1667 | 60 | 66.6667 | 1 | 38
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK052 | Project_058_RISK052 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | sub-System Cleanliness | Person_294 | 2017-05-23 | 2019-05-23 | 0.75 | 15.9918 | 11.9938 | Reduce | 0.2 | 15.9918 | 3.1984 | H3 | 3 | Stable | 0.7 | 108 | 135 | 154 | 133.6667 | 0.3 | 37 | 59 | 67 | 56.6667 | 0 | 73.3333 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R002 | Project_044_Risk-R002 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Parts changing post ordering | Person_310 | 2018-01-20 01:00 | 2019-05-22 | 0.9 | 0 | 0 | -- | 0.9 | 0 | 0 | H1 | 5 | Stable | [11 empty] | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R022 | Project_044_Risk-R022 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Shock Requirement | Person_763 | 2018-11-20 01:00 | 2020-01-20 01:00 | 0.1 | 4.8292 | 0.96584 | Accept | 0.1 | 4.8292 | 0.72438 | H3 | 3 | Stable | 0.9 | 97 | 128 | 157 | 127.6667 | 0.9 | 97 | 128 | 157 | 127.6667 | 0 | 0 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Open PR's | Person_294 | 2018-04-22 | 2018-11-20 01:00 | 0.5 | 7.6338 | 3.8169 | Reduce | 0.3 | 7.6338 | 2.2901 | H3 | 3 | Improving | 0.7 | 85 | 135 | 159 | 130.6667 | 0.4 | 21 | 57 | 77 | 54.3333 | 0 | 40 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R091 | Project_044_Risk-R091 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Receive System Performance | Person_763 | 2017-11-20 01:00 | 2018-11-21 01:00 | 0.2 | 4.2255 | 0.84511 | Reduce | 0.1 | 4.2255 | 0.42255 | H3 | 3 | Stable | 0.8 | 99 | 125 | 153 | 125.3333 | 0.1 | 25 | 50 | 66 | 48.5 | 0 | 50 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R090 | Project_044_Risk-R090 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Gain and noise measurements | Person_763 | 2017-11-20 01:00 | 2019-05-23 | 0.2 | 4.2255 | 0.84511 | -- | 0.1 | 4.2255 | 0.42255 | H3 | 3 | Stable | [10 empty] | 0 | 50 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R005 | Project_044_Risk-R005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | CE Marking | Person_763 | 2018-01-20 01:00 | 2018-11-05 01:00 | 0.3 | 2.1128 | 0.63383 | Reduce | 0.1 | 1.2073 | 0.12073 | H3 | 3 | Stable | 0.7 | 109 | 133 | 144 | 130.8333 | 0.2 | 36 | 54 | 77 | 54.8333 | 42.8571 | 66.6667 | 1 | 27.7143
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Volume of production tools and Jigs | Person_279 | 2016-11-22 21:00 | 2021-11-22 21:00 | 0.35 | 6.4382 | 2.2534 | Reduce | 0.15 | 6.4382 | 0.96573 | H2 | 4 | Stable | 0.7 | 112 | 131 | 147 | 130.5 | 0.2 | 26 | 54 | 77 | 53.1667 | 0 | 57.1429 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software issue input | Person_279 | 2016-11-22 21:00 | 2023-02-19 21:00 | 0.4 | 49.4398 | 19.7759 | Reduce | 0.2 | 49.4398 | 9.888 | H2 | 4 | Stable | 0.8 | 100 | 125 | 145 | 124.1667 | 0.1 | 36 | 47 | 70 | 49 | 0 | 50 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-119 | Project_029_Risk-119 | Opportunitity | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Not required to support on load & offload of Customer Furnished Equipmnet | Person_585 | 2017-05-23 | 2020-04-16 | 0.8 | 5.1334 | 4.1067 | Exploit | 0.8 | 3.4137 | 2.731 | H2 | 4 | Stable | [10 empty] | 33.5 | 0 | 0 | 20.1
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2018-03-22 | 2019-07-21 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.5 | 115 | 135 | 158 | 135.5 | 0.2 | 34 | 59 | 71 | 56.8333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_585 | 2017-09-02 01:00 | 2020-04-26 | 0.1 | 6.4168 | 0.64168 | Transfer | 0.1 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sub-system FPGA | Person_332 | 2017-01-21 01:00 | 2019-05-16 | 0.4 | 1.5914 | 0.63655 | Reduce | 0.2 | 1.5914 | 0.31827 | H3 | 3 | Stable | 0.8 | 89 | 127 | 156 | 125.5 | 0.1 | 38 | 43 | 73 | 47.1667 | 0 | 50 | 1 | 1.5
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort for System HW/SW- System upgrade. | Person_199 | 2017-05-23 | 2019-09-18 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.2 | 2.5667 | 0.51334 | H3 | 3 | Stable | 0.8 | 103 | 134 | 153 | 132 | 0.4 | 15 | 52 | 72 | 49.1667 | 0 | 33.3333 | 1 | 1
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.25 | 3.5934 | 0.89835 | H2 | 4 | Stable | 0.6 | 118 | 126 | 146 | 128 | 0.2 | 37 | 43 | 62 | 45.1667 | 0 | 50 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R024 | Project_044_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Receiver System Performance | Person_763 | 2017-11-20 01:00 | 2019-11-21 01:00 | 0.2 | 4.2779 | 1.0695 | Accept | 0.15 | 4.2779 | 1.0695 | H3 | 3 | Stable | 0.8 | 90 | 139 | 141 | 131.1667 | 0.8 | 90 | 139 | 141 | 131.1667 | 0 | 25 | 1 | 0.75
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_585 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 2.5667 | 0.77001 | Accept | 0.03 | 2.5667 | 0.51334 | H3 | 3 | Stable | 0.9 | 80 | 127 | 142 | 121.6667 | 0.9 | 80 | 127 | 142 | 121.6667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Minimum Order Quantities | Person_403 | 2017-11-20 01:00 | 2019-05-16 | 0.2 | 1.925 | 0.38501 | Exploit | 0.2 | 1.925 | 0.38501 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs | Person_403 | 2018-04-22 | 2019-05-16 | 0.5 | 11.5502 | 3.8462 | Accept | 0.5 | 11.5502 | 3.8462 | H2 | 4 | Stable | 0.7 | 119 | 138 | 149 | 136.6667 | 0.7 | 119 | 138 | 149 | 136.6667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) at the System level on product platform - performed by 3rd parties | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Sub-system / product system accreditation hindered by Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.1 | 0.25667 | 0.025667 | Transfer | 0.1 | 0.25667 | 0.025667 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 0.25 | 1.4673 | 0.58692 | Accept | 0.25 | 1.4673 | 0.44019 | H2 | 4 | Stable | 0.5 | 102 | 126 | 145 | 125.1667 | 0.5 | 102 | 126 | 145 | 125.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_694 | 2017-05-23 | 2019-08-04 | 0.3 | 0 | 0 | Transfer | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 66.6667 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 1.9208 | 0.67227 | Accept | 0.2 | 1.9208 | 0.48019 | H3 | 3 | Stable | 0.7 | 90 | 127 | 147 | 124.1667 | 0.7 | 90 | 127 | 147 | 124.1667 | 0 | 33.3333 | 1 | 1
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2018-03-22 | 2020-04-26 | 0.4 | 0.77001 | 0.30801 | Reduce | 0.3 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.5 | 84 | 138 | 145 | 130.1667 | 0.2 | 37 | 49 | 69 | 50.3333 | 0 | 25 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_694 | 2018-02-20 01:00 | 2019-08-04 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.8 | 106 | 127 | 143 | 126.1667 | 0.3 | 26 | 47 | 62 | 46 | 0 | 28.5714 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_585 | 2017-10-21 01:00 | 2019-07-21 | 0.333 | 1.54 | 0.30801 | Accept | 0.333 | 0.77001 | 0.154 | H2 | 4 | Stable | 0.8 | 112 | 131 | 158 | 132.3333 | 0.8 | 112 | 131 | 158 | 132.3333 | 50 | 0 | 0 | 30
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2018-03-22 | 2019-07-21 | 0.4 | 0.94968 | 0.28491 | Accept | 0.3 | 0.94968 | 0.18994 | H2 | 4 | Improving | 0.9 | 117 | 121 | 150 | 125.1667 | 0.9 | 117 | 121 | 150 | 125.1667 | 0 | 25 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2020-04-26 | 0.35 | 1.0695 | 0.74863 | Accept | 0.25 | 1.0695 | 0.74863 | H2 | 4 | Stable | 0.7 | 106 | 134 | 155 | 132.8333 | 0.7 | 106 | 134 | 155 | 132.8333 | 0 | 28.5714 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2020-09-19 01:00 | 0.2 | 10.5437 | 2.1087 | Accept | 0.2 | 10.5437 | 2.1087 | H3 | 3 | Stable | 0.9 | 94 | 139 | 152 | 133.6667 | 0.9 | 94 | 139 | 152 | 133.6667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK004 | Project_075_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional Material required for investigations | Person_627 | 2017-07-21 | 2018-11-20 01:00 | 0.4 | 3.3748 | 1.3499 | Reduce | 0.1 | 3.3748 | 0.33748 | H3 | 3 | Stable | 0.7 | 112 | 134 | 145 | 132.1667 | 0.2 | 8 | 51 | 76 | 48 | 0 | 75 | 1 | 2.25
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2019-07-21 | 0.3 | 0 | 0 | Accept | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.8 | 80 | 129 | 160 | 126 | 0.8 | 80 | 129 | 160 | 126 |  | 33.3333 | 1
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | RISK008 | Project_029_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Impact of sub-system Design Changes [product dependency] | Person_332 | 2016-09-20 01:00 | 2019-08-15 | 0.7 | 4.0498 | 2.8349 | Accept | 0.7 | 4.0498 | 2.8349 | H2 | 4 | Stable | 0.7 | 85 | 128 | 158 | 125.8333 | 0.7 | 85 | 128 | 158 | 125.8333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK024 | Project_075_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Failure to meet promised delivery dates | Person_627 | 2017-09-20 01:00 | 2019-01-21 01:00 | 0.5 | 2.5311 | 1.2656 | Reduce | 0.4 | 2.5311 | 1.0124 | H2 | 4 | Stable | 0.9 | 109 | 124 | 149 | 125.6667 | 0.1 | 14 | 40 | 75 | 41.5 | 0 | 20 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK009 | Project_075_RISK009 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Suppliers can't meet timescales. | Person_627 | 2016-12-20 01:00 | 2018-11-20 01:00 | 0.7 | 22.2176 | 15.5523 | Reduce | 0.6 | 6.7497 | 4.0498 | H1 | 5 | Stable | 0.7 | 88 | 130 | 147 | 125.8333 | 0.2 | 31 | 47 | 77 | 49.3333 | 69.6202 | 14.2857 | 0 | 41.7721
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK017 | Project_075_RISK017 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | New Materials not tested for Out Gassing | Person_451 | 2017-07-21 | 2018-08-20 | 0.35 | 12.3041 | 4.3064 | Reduce | 0.2 | 12.3041 | 2.4608 | H2 | 4 | Stable | 0.8 | 85 | 126 | 158 | 124.5 | 0.1 | 7 | 49 | 71 | 45.6667 | 0 | 42.8571 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK008 | Project_075_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Failures at Acceptance stage | Person_449 | 2017-07-21 | 2019-04-22 | 0.3 | 2.5311 | 1.2656 | Accept | 0.3 | 2.5311 | 1.2656 | H2 | 4 | Stable | 0.5 | 101 | 128 | 155 | 128 | 0.5 | 101 | 128 | 155 | 128 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK007 | Project_075_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Range performance does not meet requirement. | Person_003 | 2017-07-21 | 2018-09-20 01:00 | 0.1 | 0.98433 | 0.78746 | Accept | 0.1 | 0.98433 | 0.78746 | H3 | 3 | Stable | 0.8 | 105 | 127 | 142 | 125.8333 | 0.8 | 105 | 127 | 142 | 125.8333 | 0 | 0 | 1 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_021 | Project_086 | RISK003 | Project_086_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Qualification | Person_528 | 2017-11-22 01:00 | 2018-10-21 01:00 | 0.3 | 0.33844 | 0.10153 | Reduce | 0.2 | 0.33844 | 0.067689 | H2 | 4 | Worsening | 0.7 | 83 | 130 | 147 | 125 | 0.2 | 2 | 47 | 64 | 42.3333 | 0 | 33.3333 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK010 | Project_075_RISK010 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | We do not achieve Standard compliant energy over temperature | Person_449 | 2017-07-21 | 2018-09-20 01:00 | 0.5 | 0.60436 | 0.48349 | Accept | 0.5 | 0.60436 | 0.48349 | H1 | 5 | Stable | 0.6 | 88 | 127 | 150 | 124.3333 | 0.6 | 88 | 127 | 150 | 124.3333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK018 | Project_075_RISK018 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Crystal switch | Person_627 | 2017-03-21 01:00 | 2018-09-20 01:00 | 0.5 | 0 | 0 | Accept | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.8 | 81 | 136 | 152 | 129.5 | 0.8 | 81 | 136 | 152 | 129.5 |  | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-054 | Project_062_Risk-054 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | sub-system rework to reviised standard | Person_031 | 2017-07-21 | 2018-11-21 01:00 | 0.4 | 0.62744 | 0.25098 | Transfer | 0.4 | 0.62744 | 0.25098 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-010 | Project_062_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Resource | Person_479 | 2017-07-21 | 2019-02-21 01:00 | 0.4 | 7.5293 | 3.0117 | Reduce | 0.25 | 7.5293 | 1.8823 | H2 | 4 | Stable | 0.6 | 103 | 133 | 143 | 129.6667 | 0.2 | 33 | 49 | 64 | 48.8333 | 0 | 37.5 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-057 | Project_062_Risk-057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Supplier Application Encryption / Protection | Person_479 | 2017-07-21 | 2019-02-21 01:00 | 0.3 | 4.183 | 1.2549 | Reduce | 0.1 | 4.183 | 0.4183 | H3 | 3 | Stable | 0.5 | 114 | 137 | 141 | 133.8333 | 0.4 | 20 | 42 | 72 | 43.3333 | 0 | 66.6667 | 1 | 2
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-013 | Project_062_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Unavailability of Network | Person_479 | 2017-07-21 | 2018-11-20 01:00 | 0.25 | 3.5555 | 0.88888 | Reduce | 0.15 | 3.5555 | 0.53333 | H3 | 3 | Improving | 0.6 | 114 | 130 | 148 | 130.3333 | 0.4 | 26 | 53 | 71 | 51.5 | 0 | 40 | 1 | 1.2
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-011 | Project_062_Risk-011 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Variant deviations between SW | Person_479 | 2017-07-21 | 2018-09-20 01:00 | 0.4 | 0.71808 | 0.28723 | Reduce | 0.3 | 0.71808 | 0.21542 | H2 | 4 | Stable | 0.6 | 112 | 135 | 160 | 135.3333 | 0.2 | 11 | 40 | 74 | 40.8333 | 0 | 25 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-056 | Project_062_Risk-056 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Supplier integration acceptance by end Customer | Person_031 | 2017-07-21 | 2018-11-21 01:00 | 0.3 | 1.8823 | 0.5647 | Reduce | 0.3 | 1.8823 | 0.5647 | H3 | 3 | Stable | 0.6 | 91 | 135 | 152 | 130.5 | 0.2 | 18 | 49 | 63 | 46.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-018 | Project_062_Risk-018 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Prioritisation - new or less experienced staff | Person_459 | 2017-07-21 | 2019-02-20 01:00 | 0.35 | 12.7044 | 4.4465 | Reduce | 0.15 | 12.7044 | 1.9057 | H2 | 4 | Improving | 0.5 | 82 | 129 | 142 | 123.3333 | 0.2 | 26 | 42 | 76 | 45 | 0 | 57.1429 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-016 | Project_062_Risk-016 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier Component Unavailability | Person_664 | 2017-07-21 | 2018-12-22 01:00 | 0.3 | 4.183 | 1.2549 | Reduce | 0.2 | 4.183 | 0.83659 | H3 | 3 | Stable | 0.6 | 97 | 128 | 152 | 126.8333 | 0.1 | 34 | 45 | 60 | 45.6667 | 0 | 33.3333 | 1 | 1
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-020 | Project_062_Risk-020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Security Encryption Solution | Person_245 | 2017-07-21 | 2018-10-22 01:00 | 0.25 | 4.183 | 1.0457 | Reduce | 0.2 | 4.183 | 0.83659 | H2 | 4 | Improving | 0.7 | 103 | 126 | 151 | 126.3333 | 0.1 | 13 | 52 | 69 | 48.3333 | 0 | 20 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-021 | Project_062_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Hardware CoSupplierng | Person_664 | 2017-07-21 | 2018-09-20 01:00 | 0.3 | 7.5293 | 2.2588 | Reduce | 0.25 | 7.5293 | 1.8823 | H2 | 4 | Stable | 0.9 | 91 | 133 | 160 | 130.5 | 0.3 | 13 | 41 | 74 | 41.8333 | 0 | 16.6667 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-043 | Project_062_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | User response | Person_479 | 2017-07-21 | 2019-02-21 01:00 | 0.35 | 3.3464 | 1.1712 | Avoid | 0.25 | 3.3464 | 0.83659 | H2 | 4 | Stable | [10 empty] | 0 | 28.5714 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-047 | Project_062_Risk-047 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Redhat6 on PCI shelf | Person_253 | 2017-07-21 | 2019-03-24 | 0.3 | 7.1808 | 2.1542 | Avoid | 0.3 | 7.1808 | 2.1542 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-025 | Project_062_Risk-025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | System Obsolescence Risk | Person_543 | 2017-07-21 | 2019-03-22 | 0.3 | 2.0915 | 0.62744 | Avoid | 0.1 | 2.0915 | 0.20915 | H2 | 4 | Stable | [10 empty] | 0 | 66.6667 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-022 | Project_062_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Registers Might Be Unstable | Person_479 | 2017-07-21 | 2018-10-21 01:00 | 0.25 | 1.3385 | 0.33464 | Reduce | 0.2 | 1.3385 | 0.26771 | H3 | 3 | Stable | 0.6 | 102 | 125 | 152 | 125.6667 | 0.3 | 31 | 44 | 61 | 44.6667 | 0 | 20 | 1 | 0.6
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-023 | Project_062_Risk-023 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Change In Security Boundary | Person_031 | 2017-07-21 | 2019-02-21 01:00 | 0.3 | 4.6013 | 1.3804 | Reduce | 0.15 | 4.6013 | 0.69019 | H3 | 3 | Stable | 0.7 | 120 | 129 | 156 | 132 | 0.4 | 16 | 45 | 67 | 43.8333 | 0 | 50 | 1 | 1.5
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-006 | Project_062_Risk-006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Unavailability of Test Hardware | Person_253 | 2017-07-21 | 2019-03-22 | 0.5 | 2.5098 | 1.2549 | Reduce | 0.25 | 2.5098 | 0.62744 | H2 | 4 | Stable | 0.7 | 109 | 126 | 155 | 128 | 0.1 | 23 | 46 | 73 | 46.6667 | 0 | 50 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-048 | Project_062_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software lockdown features | Person_245 | 2017-07-21 | 2018-11-21 01:00 | 0.5 | 0.71808 | 0.35904 | Reduce | 0.5 | 0.71808 | 0.35904 | H2 | 4 | Stable | 0.6 | 87 | 125 | 147 | 122.3333 | 0.2 | 21 | 59 | 76 | 55.5 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-005 | Project_062_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Security Solution Integration | Person_245 | 2017-07-21 | 2018-11-14 01:00 | 0.3 | 4.6013 | 1.3804 | Avoid | 0.25 | 4.6013 | 1.1503 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-009 | Project_062_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Unresolved technical debt (excluding ILS) | Person_253 | 2017-07-21 | 2019-03-23 | 0.5 | 2.5098 | 1.2549 | Reduce | 0.3 | 2.5098 | 0.75293 | H2 | 4 | Stable | 0.7 | 90 | 123 | 156 | 123 | 0.4 | 20 | 50 | 66 | 47.6667 | 0 | 40 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-012 | Project_062_Risk-012 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Integration Rig Move | Person_253 | 2018-05-23 | 2019-05-23 | 0.3 | 0.4183 | 0.12549 | Avoid | 0.3 | 0.4183 | 0.12549 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-015 | Project_062_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Re-work | Person_253 | 2018-03-01 01:00 | 2019-05-22 | 0.5 | 1.0457 | 0.52287 | Avoid | 0.5 | 1.0457 | 0.52287 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-024 | Project_062_Risk-024 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional SW Build post-Factory Acceptance Test | Person_253 | 2018-08-22 01:00 | 2019-04-22 | 0.3 | 1.7778 | 0.53333 | Avoid | 0.3 | 1.7778 | 0.53333 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-027 | Project_062_Risk-027 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Facility to Test modifications | Person_253 | 2018-03-23 | 2019-04-22 | 0.5 | 2.3703 | 1.1852 | Reduce | 0.4 | 2.3703 | 0.94814 | H2 | 4 | Stable | 0.7 | 102 | 125 | 150 | 125.3333 | 0.3 | 29 | 42 | 67 | 44 | 0 | 20 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-008 | Project_062_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Paperwork for Legacy Items | Person_459 | 2018-03-23 | 2019-03-24 | 0.3 | 0.83659 | 0.25098 | Avoid | 0.3 | 0.83659 | 0.25098 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-028 | Project_062_Risk-028 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Hardware Engineering Team | Person_116 | 2018-05-23 | 2019-03-23 | 0.25 | 0.62744 | 0.15686 | Avoid | 0.25 | 0.62744 | 0.15686 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-007 | Project_062_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Hardware Encryption / Protection | Person_479 | 2018-02-10 01:00 | 2019-03-22 | 0.3 | 4.183 | 1.2549 | Reduce | 0.2 | 4.183 | 0.83659 | H3 | 3 | Stable | 0.6 | 113 | 123 | 157 | 127 | 0.4 | 6 | 56 | 62 | 48.6667 | 0 | 33.3333 | 1 | 1
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | RISK004 | Project_062_RISK004 | Opportunitity | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Carry out Console & Cabinet mod kit reviews in parallel | Person_019 | 2017-10-21 01:00 | 2019-02-21 01:00 | 0.5 | 0.33464 | 0.16732 | Exploit | 0.5 | 0.33464 | 0.16732 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | RISK006 | Project_062_RISK006 | Opportunitity | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Acceptance Management post Factory Acceptance Test | Person_253 | 2018-10-22 01:00 | 2019-03-24 | 0.2 | 0.12549 | 0.025098 | Exploit | 0.2 | 0.12549 | 0.025098 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | RISK007 | Project_062_RISK007 | Opportunitity | Project Contingency | Open | H3 | 3 | 8. System Engineering | Installation of mod kits | Person_253 | 2017-10-21 01:00 | 2019-03-24 | 0.5 | 0.1464 | 0.073202 | Exploit | 0.5 | 0.1464 | 0.073202 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | RISK013 | Project_062_RISK013 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | System modifications and technical debt. | Person_401 | 2018-08-22 01:00 | 2019-03-11 01:00 | 0.6 | 3.5555 | 2.1333 | Reduce | 0.4 | 3.5555 | 1.4222 | H2 | 4 | Stable | 0.7 | 95 | 136 | 160 | 133.1667 | 0.1 | 18 | 56 | 60 | 50.3333 | 0 | 33.3333 | 0 | 0
2018-07-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK044 | Project_053_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Product Hardening | Person_719 | 2018-03-23 | 2019-01-19 23:00 | 0.3 | 7.9015 | 2.3705 | Avoid | 0.3 | 7.9015 | 2.3705 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK015 | Project_053_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Equipment export licences | Person_252 | 2018-06-23 | 2019-07-22 | 0.3 | 2.586 | 0.77579 | Avoid | 0.1 | 2.586 | 0.2586 | H3 | 3 | Improving | [10 empty] | 0 | 66.6667 | 1 | 2
2018-07-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK006 | Project_053_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional UK integration of the System product | Person_719 | 2018-10-21 23:00 | 2019-01-20 23:00 | 0.2 | 6.3212 | 1.2642 | Avoid | 0.2 | 6.3212 | 1.2642 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 1 | 0
2018-07-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK005 | Project_053_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier Deiivery Schedule | Person_252 | 2018-01-20 23:00 | 2018-11-19 23:00 | 0.5 | 5.3299 | 2.665 | Reduce | 0.25 | 5.3299 | 1.3325 | H2 | 4 | Stable | 0.7 | 114 | 130 | 145 | 129.8333 | 0.4 | 3 | 44 | 64 | 40.5 | 0 | 50 | 0 | 0
2018-07-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK010 | Project_053_RISK010 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Immaturity of the core product | Person_719 | 2018-08-21 23:00 | 2018-11-19 23:00 | 0.5 | 6.4649 | 3.2325 | Avoid | 0.7 | 6.4649 | 4.5254 | H1 | 5 | Worsening | [10 empty] | 0 | -40 | 0 | 0
2018-07-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK047 | Project_053_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Lab Availability | Person_252 | 2017-10-20 23:00 | 2020-01-21 23:00 | 0.5 | 1.4007 | 0.49026 | Accept | 0.2 | 1.4007 | 0.49026 | H3 | 3 | Improving | 0.9 | 92 | 131 | 143 | 126.5 | 0.9 | 92 | 131 | 143 | 126.5 | 0 | 60 | 1 | 1.8
2018-07-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK007 | Project_053_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Resources Uavailable | Person_252 | 2017-11-19 23:00 | 2019-08-20 23:00 | 0.5 | 10.3438 | 5.1719 | Reduce | 0.2 | 7.9015 | 1.5803 | H3 | 3 | Stable | 0.6 | 83 | 135 | 158 | 130.1667 | 0.4 | 6 | 47 | 66 | 43.3333 | 23.6111 | 60 | 1 | 15.9666
2018-07-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK043 | Project_053_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Change in REACH/RoSH Legislation | Person_302 | 2017-11-19 23:00 | 2018-09-19 23:00 | 0.1 | 0.041801 | 0.0083602 | Accept | 0.1 | 0.041801 | 0.0083602 | H2 | 4 | Stable | 0.6 | 108 | 127 | 154 | 128.3333 | 0.6 | 108 | 127 | 154 | 128.3333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK046 | Project_053_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Un-Planned Production Activities | Person_252 | 2019-07-22 | 2020-01-21 23:00 | 0.5 | 0.039983 | 0.0079966 | Accept | 0.2 | 0.039983 | 0.0079966 | H3 | 3 | Stable | 0.6 | 95 | 139 | 143 | 132.3333 | 0.6 | 95 | 139 | 143 | 132.3333 | 0 | 60 | 1 | 1.8
2018-07-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK021 | Project_053_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Product documentation | Person_719 | 2018-08-21 23:00 | 2019-07-26 | 0.35 | 0.39983 | 0.19991 | Accept | 0.35 | 0.39983 | 0.19991 | H2 | 4 | Worsening | 0.6 | 105 | 126 | 159 | 128 | 0.6 | 105 | 126 | 159 | 128 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_077 | 2016-01-22 01:00 | 2018-11-17 01:00 | 0.15 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Improving | 0.9 | 115 | 131 | 142 | 130.1667 | 0.1 | 17 | 56 | 71 | 52 |  | 0 | 0
2018-07-22 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-07-21 | 0.1 | 4.0291 | 0.40291 | Reduce | 0.1 | 4.0291 | 0.40291 | H2 | 4 | Improving | 0.9 | 104 | 125 | 142 | 124.3333 | 0.1 | 5 | 58 | 65 | 50.3333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-148 | Project_008_SER-148 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Demands but not provisioned | Person_639 | 2017-08-21 01:00 | 2018-08-21 | 0.3 | 0.68561 | 0.20568 | Accept | 0.3 | 0.68561 | 0.20568 | H3 | 3 | Stable | 0.6 | 108 | 129 | 152 | 129.3333 | 0.6 | 108 | 129 | 152 | 129.3333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-094 | Project_008_Risk-094 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Consumable Stock Levels | Person_567 | 2017-04-22 | 2018-08-21 | 0.5 | 0.95964 | 0.57578 | Accept | 0.5 | 0.95964 | 0.57578 | H3 | 3 | Stable | 0.9 | 87 | 126 | 152 | 123.8333 | 0.9 | 87 | 126 | 152 | 123.8333 | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-034 | Project_008_SER-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_567 | 2018-05-22 | 2018-08-21 | 0.25 | 8.2016 | 0.82016 | Accept | 0.25 | 8.2016 | 0 | H3 | 3 | Stable | 0.6 | 82 | 126 | 145 | 121.8333 | 0.6 | 82 | 126 | 145 | 121.8333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-023 | Project_018_Risk-023 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Head Repairs | Person_676 | 2017-07-21 | 2019-08-20 | 0.3 | 2.563 | 0.7689 | Reduce | 0.3 | 2.563 | 0.7689 | H3 | 3 | Stable | 0.7 | 83 | 128 | 152 | 124.5 | 0.1 | 5 | 40 | 65 | 38.3333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 1.0726 | 0.42903 | Accept | 0.5 | 1.0726 | 0.42903 | H2 | 4 | Stable | 0.6 | 101 | 128 | 144 | 126.1667 | 0.6 | 101 | 128 | 144 | 126.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2018-11-20 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 0.45943 | 0.18377 | H2 | 4 | Stable | 0.5 | 81 | 138 | 152 | 130.8333 | 0.2 | 8 | 52 | 67 | 47.1667 | 88.3943 | 20 | 0 | 53.0366
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_703 | 2015-05-24 | 2019-05-22 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 1.1996 | 0.17994 | H3 | 3 | Stable | 0.5 | 86 | 123 | 157 | 122.5 | 0.2 | 25 | 57 | 70 | 53.8333 | 80.9521 | 70 | 1 | 50.6713
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK004 | Project_081_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Greater number of failures/ investigations | Person_260 | 2017-09-27 01:00 | 2021-09-27 01:00 | 0.6 | 2.685 | 1.611 | Reduce | 0.6 | 2.685 | 1.611 | H3 | 3 | Worsening | 0.7 | 83 | 128 | 155 | 125 | 0.3 | 18 | 45 | 70 | 44.6667 | 0 | 0 | 1 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK003 | Project_081_RISK003 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Export control issues taking longer to resolve | Person_260 | 2017-09-27 01:00 | 2021-09-27 01:00 | 0.2 | 1.5256 | 0.30511 | Reduce | 0.2 | 1.5256 | 0.30511 | H3 | 3 | Stable | 0.6 | 91 | 138 | 145 | 131.3333 | 0.3 | 31 | 44 | 77 | 47.3333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK006 | Project_081_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Large volume of repairs loaded to clear backlog | Person_260 | 2017-09-27 01:00 | 2021-09-27 01:00 | 0.25 | 3.1854 | 0.79634 | Reduce | 0.25 | 3.1854 | 0.79634 | H3 | 3 | Worsening | 0.8 | 103 | 133 | 142 | 129.5 | 0.4 | 26 | 50 | 73 | 49.8333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK005 | Project_081_RISK005 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Marching army Customer costs for duration of contract | Person_260 | 2021-05-23 | 2021-09-27 01:00 | 0.2 | 1.6598 | 0.33196 | Reduce | 0.2 | 1.6598 | 0.33196 | H3 | 3 | Stable | 0.7 | 108 | 123 | 143 | 123.8333 | 0.4 | 39 | 51 | 73 | 52.6667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK021 | Project_081_RISK021 | Threat | Financial Contingency | Open | H3 | 3 | 7. Finance | Increase of bank fees and other direct costs | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.15 | 2.27 | 0.3405 | Avoid | 0.15 | 2.27 | 0.3405 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK024 | Project_081_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer- Training | Person_115 | 2017-09-27 01:00 | 2021-11-27 01:00 | 0.6 | 1.3425 | 0.80549 | Reduce | 0.6 | 1.3425 | 0.80549 | H3 | 3 | Stable | 0.9 | 117 | 125 | 152 | 128.1667 | 0.4 | 8 | 49 | 69 | 45.5 | 0 | 0 | 1 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK002 | Project_081_RISK002 | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Supplier costs to be covered by us | Person_260 | 2017-09-27 01:00 | 2021-09-20 01:00 | 0.2 | 2.0381 | 0.40763 | Reduce | 0.2 | 2.0381 | 0.40763 | H3 | 3 | Stable | 0.7 | 109 | 127 | 152 | 128.1667 | 0.4 | 25 | 52 | 60 | 48.8333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK023 | Project_081_RISK023 | Threat | Project Contingency | Open | H2 | 4 | 7. Finance | Risk of funding requirement | Person_115 | 2017-09-27 01:00 | 2021-09-27 01:00 | 0.6 | 1.7696 | 1.0618 | Reduce | 0.6 | 1.7696 | 1.0618 | H3 | 3 | Stable | 0.5 | 80 | 129 | 148 | 124 | 0.4 | 37 | 59 | 65 | 56.3333 | 0 | 0 | 1 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK001 | Project_081_RISK001 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | Increase in Support Management | Person_260 | 2017-07-21 | 2021-07-21 | 0.4 | 2.0381 | 0.81526 | Reduce | 0.4 | 2.0381 | 0.81526 | H3 | 3 | Stable | 0.5 | 119 | 128 | 146 | 129.5 | 0.4 | 20 | 48 | 77 | 48.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK008 | Project_081_RISK008 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Failure to meet repair turnaround time | Person_260 | 2017-09-27 01:00 | 2021-09-20 01:00 | 0.1 | 1.5866 | 0.15866 | Reduce | 0.1 | 1.5866 | 0.15866 | H3 | 3 | Stable | 0.9 | 95 | 137 | 143 | 131 | 0.4 | 1 | 48 | 63 | 42.6667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK007 | Project_081_RISK007 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | High value supplier repair/replacements required | Person_260 | 2017-09-27 01:00 | 2021-09-20 01:00 | 0.4 | 3.7834 | 1.5133 | Reduce | 0.4 | 3.7834 | 1.5133 | H3 | 3 | Stable | 0.8 | 103 | 137 | 142 | 132.1667 | 0.2 | 13 | 55 | 61 | 49 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK009 | Project_081_RISK009 | Threat | Management Contingency | Open | H2 | 4 | 7. Finance | Increase of Spares UPCs | Person_260 | 2017-09-27 01:00 | 2019-05-16 | 0.2 | 17.5011 | 3.5002 | Reduce | 0.2 | 17.5011 | 3.5002 | H3 | 3 | Stable | 0.5 | 108 | 122 | 156 | 125.3333 | 0.3 | 6 | 43 | 73 | 41.8333 | 0 | 0 | 1 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP002 | Project_081_OPP002 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Core Management team shared across other programmes | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.3 | 0.91533 | 0.2746 | -- | 0.3 | 0.91533 | 0.2746 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP001 | Project_081_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 7. Finance | Reduction in Spares UPC | Person_260 | 2017-07-21 | 2019-05-16 | 0.2 | 6.1022 | 1.2204 | -- | 0.2 | 6.1022 | 1.2204 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP004 | Project_081_OPP004 | Opportunitity | Project Contingency | Open | H3 | 3 | 7. Finance | Less repairs than planned in base costs | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.2 | 1.2204 | 0.24409 | -- | 0.2 | 1.2204 | 0.24409 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP003 | Project_081_OPP003 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Supplier abilities mature exponentially throughout contract requiring less FSE support | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.25 | 1.8307 | 0.45767 | -- | 0.25 | 1.8307 | 0.45767 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK015 | Project_081_RISK015 | Threat | Management Contingency | Open | H3 | 3 | 7. Finance | Our being liable for freight costs. | Person_260 | 2018-03-23 | 2021-09-20 01:00 | 0.3 | 3.0511 | 0.91533 | Reduce | 0.3 | 3.0511 | 0.91533 | H3 | 3 | Stable | 0.7 | 120 | 140 | 159 | 139.8333 | 0.2 | 31 | 45 | 78 | 48.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK014 | Project_081_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 7. Finance | Supplier request financial support for Training admin. | Person_260 | 2018-02-20 01:00 | 2021-09-20 01:00 | 0.1 | 0.50038 | 0.050038 | Reduce | 0.1 | 0.50038 | 0.050038 | H3 | 3 | Stable | 0.8 | 120 | 124 | 154 | 128.3333 | 0.3 | 31 | 59 | 70 | 56.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK017 | Project_081_RISK017 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Extended working hours during site visits | Person_419 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.3 | 1.1716 | 0.35149 | Reduce | 0.3 | 1.1716 | 0.35149 | H3 | 3 | Stable | 0.8 | 82 | 126 | 143 | 121.5 | 0.4 | 36 | 42 | 64 | 44.6667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK016 | Project_081_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Additional visit support requested by Customer/Supplier | Person_260 | 2017-10-21 01:00 | 2021-09-20 01:00 | 0.4 | 2.331 | 0.93242 | Reduce | 0.4 | 2.331 | 0.93242 | H3 | 3 | Stable | 0.9 | 100 | 138 | 150 | 133.6667 | 0.3 | 9 | 49 | 65 | 45 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK011 | Project_081_RISK011 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Additional quantities of spares/material/STTE requested by customer | Person_260 | 2017-07-21 | 2019-07-22 | 0.1 | 6.3707 | 0.63707 | Reduce | 0.1 | 6.3707 | 0.63707 | H3 | 3 | Stable | 0.7 | 120 | 139 | 147 | 137.1667 | 0.3 | 18 | 53 | 70 | 50 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK010 | Project_081_RISK010 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Increased material lead times for Spares | Person_649 | 2017-09-27 01:00 | 2019-05-16 | 0.1 | 6.3707 | 0.63707 | Reduce | 0.1 | 6.3707 | 0.63707 | H3 | 3 | Stable | 0.8 | 97 | 129 | 146 | 126.5 | 0.2 | 1 | 57 | 64 | 48.8333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK013 | Project_081_RISK013 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Additional training requested by customer. | Person_419 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.15 | 0.50038 | 0.075057 | Reduce | 0.15 | 0.50038 | 0.075057 | H3 | 3 | Stable | 0.6 | 99 | 128 | 160 | 128.5 | 0.1 | 34 | 42 | 76 | 46.3333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK012 | Project_081_RISK012 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Supplier unable to deliver course without our input | Person_419 | 2017-09-27 01:00 | 2021-09-27 01:00 | 0.5 | 0.50038 | 0.25019 | Reduce | 0.5 | 0.50038 | 0.25019 | H3 | 3 | Stable | 0.9 | 91 | 137 | 143 | 130.3333 | 0.4 | 26 | 44 | 68 | 45 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK019 | Project_081_RISK019 | Threat | Management Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Misc costs incurred at trials | Person_260 | 2018-05-23 | 2021-09-20 01:00 | 0.2 | 1.3425 | 0.2685 | Avoid | 0.2 | 1.3425 | 0.2685 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK018 | Project_081_RISK018 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Additional trials support requested (+3) | Person_260 | 2018-05-23 | 2021-07-21 | 0.2 | 2.0259 | 0.40519 | Reduce | 0.2 | 2.0259 | 0.40519 | H3 | 3 | Stable | 0.8 | 81 | 126 | 149 | 122.3333 | 0.2 | 36 | 46 | 66 | 47.6667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK020 | Project_081_RISK020 | Threat | Project Contingency | Open | H3 | 3 | 7. Finance | Travel Cost Increases | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.3 | 1.8307 | 0.5492 | Reduce | 0.3 | 1.8307 | 0.5492 | H3 | 3 | Stable | 0.8 | 81 | 126 | 148 | 122.1667 | 0.3 | 33 | 42 | 75 | 46 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_009 | Project_051 | RISK001 | Project_051_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Generic Labour or Material Overspend | Person_577 | 2012-05-23 | 2021-05-22 | 0.5 | 2.2129 | 1.549 | Accept | 0.5 | 2.2129 | 1.549 | H3 | 3 | Stable | 0.5 | 97 | 133 | 154 | 130.5 | 0.5 | 97 | 133 | 154 | 130.5 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-20 20:00 | 2020-08-19 20:00 | 0.5 | 6.0949 | 1.219 | Accept | 0.5 | 6.0949 | 1.219 | H2 | 4 | Stable | 0.6 | 108 | 129 | 151 | 129.1667 | 0.6 | 108 | 129 | 151 | 129.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Regulatory standards changes misunderstood | Person_693 | 2018-03-23 | 2018-10-21 01:00 | 0.3 | 1.3377 | 0.4013 | Reduce | 0.15 | 1.3377 | 0.20065 | H3 | 3 | Stable | 0.9 | 102 | 136 | 159 | 134.1667 | 0.3 | 8 | 58 | 69 | 51.5 | 0 | 50 | 1 | 1.5
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Availability of key resource within Engineering | Person_693 | 2018-01-21 01:00 | 2019-05-23 | 0.1 | 0.57879 | 0.086819 | Accept | 0.1 | 0.57879 | 0.057879 | H3 | 3 | Improving | 0.8 | 83 | 127 | 145 | 122.6667 | 0.8 | 83 | 127 | 145 | 122.6667 | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_547 | 2018-08-22 01:00 | 2019-01-21 01:00 | 0.5 | 1.6721 | 0.66883 | Accept | 0.3 | 1.6721 | 0.50162 | H2 | 4 | Stable | 0.9 | 98 | 138 | 142 | 132 | 0.9 | 98 | 138 | 142 | 132 | 0 | 40 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK011 | Project_041_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Supplier Development support | Person_693 | 2018-04-11 | 2019-01-19 01:00 | 0.5 | 0.55736 | 0.083603 | Accept | 0.332 | 0.55736 | 0.027868 | H2 | 4 | Stable | 0.9 | 88 | 135 | 149 | 129.5 | 0.9 | 88 | 135 | 149 | 129.5 | 0 | 33.6 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Production - Supplier Quality | Person_468 | 2017-05-23 | 2018-11-20 01:00 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Improving | 0.9 | 93 | 138 | 146 | 131.8333 | 0.2 | 23 | 51 | 77 | 50.6667 | 0 | 60 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Unforseen and substantial increase in Repairs workload during new build production period. | Person_547 | 2017-10-23 01:00 | 2019-08-21 01:00 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.1 | 1.5434 | 0.15434 | H3 | 3 | Stable | 0.7 | 94 | 138 | 152 | 133 | 0.4 | 21 | 51 | 77 | 50.3333 | 0 | 66.6667 | 1 | 2
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK007 | Project_041_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Advanced production of products using a Qual. standard component rather than a Prod. standard | Person_547 | 2018-10-22 01:00 | 2019-02-20 01:00 | 0.49 | 1.2862 | 0.63024 | Reduce | 0.25 | 1.5434 | 0.38586 | H2 | 4 | Stable | 0.8 | 109 | 123 | 155 | 126 | 0.2 | 20 | 46 | 62 | 44.3333 | -20 | 48.9796 | 0 | -12
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK010 | Project_041_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Digital Assembly - Testing | Person_547 | 2018-04-11 | 2018-08-20 | 0.15 | 0.77172 | 0.54021 | Accept | 0.1 | 0.77172 | 0.23152 | H3 | 3 | Improving | 0.8 | 120 | 125 | 150 | 128.3333 | 0.8 | 120 | 125 | 150 | 128.3333 | 0 | 33.3333 | 1 | 1
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK013 | Project_041_RISK013 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional components validation | Person_693 | 2017-07-15 | 2018-09-20 01:00 | 0.4 | 1.2798 | 0.95984 | Accept | 0.3 | 1.2798 | 0.95984 | H2 | 4 | Stable | 0.7 | 87 | 139 | 158 | 133.5 | 0.7 | 87 | 139 | 158 | 133.5 | 0 | 25 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_693 | 2017-04-22 | 2018-11-19 01:00 | 0.15 | 0.81362 | 0.40681 | Accept | 0.05 | 0.81362 | 0.40681 | H3 | 3 | Stable | 0.8 | 116 | 131 | 148 | 131.3333 | 0.8 | 116 | 131 | 148 | 131.3333 | 0 | 66.6667 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Outstanding CRs | Person_693 | 2017-05-23 | 2018-12-21 01:00 | 0.7 | 0.39054 | 0.15622 | Accept | 0.3 | 0.39054 | 0.15622 | H3 | 3 | Stable | 0.8 | 116 | 126 | 143 | 127.1667 | 0.8 | 116 | 126 | 143 | 127.1667 | 0 | 57.1429 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK004 | Project_094_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Acceptance trial success criteria not achieved | Person_419 | 2019-11-21 01:00 | 2020-02-21 01:00 | 0.2 | 19.9676 | 3.9935 | Reduce | 0.2 | 19.9676 | 3.9935 | H3 | 3 | Stable | 0.9 | 116 | 125 | 159 | 129.1667 | 0.3 | 6 | 57 | 78 | 52 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK003 | Project_094_RISK003 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Issues experienced during system integration | Person_198 | 2019-08-22 01:00 | 2020-11-20 01:00 | 0.3 | 15.974 | 4.7922 | Reduce | 0.3 | 15.974 | 4.7922 | H3 | 3 | Stable | 0.5 | 91 | 134 | 159 | 131 | 0.1 | 7 | 46 | 74 | 44.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK006 | Project_094_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Additional freight costs | Person_198 | 2020-08-21 01:00 | 2022-05-22 | 0.3 | 11.9805 | 3.5942 | Reduce | 0.3 | 11.9805 | 3.5942 | H3 | 3 | Stable | 0.7 | 106 | 136 | 153 | 133.8333 | 0.4 | 36 | 59 | 60 | 55.3333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK005 | Project_094_RISK005 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Project extension due to schedule slippage | Person_198 | 2021-04-22 | 2022-05-22 | 0.2 | 11.9805 | 2.3961 | Reduce | 0.2 | 11.9805 | 2.3961 | H3 | 3 | Stable | 0.5 | 92 | 121 | 145 | 120.1667 | 0.4 | 6 | 40 | 74 | 40 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK011 | Project_094_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unplanned redesign activity | Person_198 | 2018-08-22 01:00 | 2020-05-22 | 0.4 | 21.4052 | 8.5621 | Reduce | 0.4 | 21.4052 | 8.5621 | H2 | 4 | Stable | 0.7 | 84 | 134 | 144 | 127.3333 | 0.4 | 21 | 47 | 70 | 46.5 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK010 | Project_094_RISK010 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Increased cost of manufacture | Person_193 | 2019-04-23 | 2020-05-22 | 0.4 | 19.1689 | 7.6675 | Reduce | 0.4 | 19.1689 | 7.6675 | H3 | 3 | Stable | 0.9 | 112 | 140 | 147 | 136.5 | 0.2 | 15 | 54 | 77 | 51.3333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK002 | Project_094_RISK002 | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Facilities or equipment for training not available | Person_198 | 2020-12-21 01:00 | 2021-05-22 | 0.2 | 15.974 | 3.1948 | Reduce | 0.2 | 15.974 | 3.1948 | H3 | 3 | Stable | 0.9 | 87 | 129 | 147 | 125 | 0.4 | 16 | 43 | 77 | 44.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK013 | Project_094_RISK013 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Other risks | Person_198 | 2018-08-22 01:00 | 2022-05-22 | 0.1 | 49.1298 | 4.913 | Reduce | 0.1 | 49.1298 | 4.913 | H3 | 3 | Stable | 0.5 | 81 | 136 | 144 | 128.1667 | 0.2 | 15 | 42 | 65 | 41.3333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK001 | Project_094_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Immature Prime not qualified to deliver SoW | Person_198 | 2018-08-22 01:00 | 2021-08-21 01:00 | 0.4 | 27.9546 | 11.1818 | Reduce | 0.4 | 27.9546 | 11.1818 | H2 | 4 | Stable | 0.5 | 94 | 138 | 144 | 131.6667 | 0.2 | 37 | 59 | 72 | 57.5 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK012 | Project_094_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Insufficient resources to meet the demand of the programme | Person_198 | 2018-08-22 01:00 | 2021-07-20 | 0.35 | 4.6804 | 1.6381 | Reduce | 0.35 | 4.6804 | 1.6381 | H2 | 4 | Stable | 0.5 | 119 | 124 | 147 | 127 | 0.1 | 4 | 46 | 61 | 41.5 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK008 | Project_094_RISK008 | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Increased warranty costs | Person_260 | 2020-11-20 01:00 | 2023-05-23 | 0.1 | 11.9805 | 1.1981 | Avoid | 0.1 | 11.9805 | 1.1981 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK007 | Project_094_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Additional training requested | Person_620 | 2020-12-21 01:00 | 2021-07-20 | 0.3 | 5.9903 | 1.7971 | Avoid | 0.3 | 5.9903 | 1.7971 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK009 | Project_094_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Financial instability/loss of quality/abilities of suppliers for batch 2 | Person_281 | 2020-08-21 01:00 | 2021-05-22 | 0.3 | 28.1143 | 8.4343 | Reduce | 0.3 | 28.1143 | 8.4343 | H2 | 4 | Stable | 0.9 | 113 | 137 | 152 | 135.5 | 0.2 | 5 | 42 | 67 | 40 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | OPP002 | Project_094_OPP002 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Integration schedule improved | Person_198 | 2018-08-22 01:00 | 2021-03-22 | 0.3 | 7.987 | 2.3961 | -- | 0.3 | 7.987 | 2.3961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | OPP001 | Project_094_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 11. Supply chain | UPC savings | Person_198 | 2018-08-22 01:00 | 2019-09-20 01:00 | 0.2 | 19.9676 | 3.9935 | -- | 0.2 | 19.9676 | 3.9935 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK014 | Project_083_RISK014 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System SW hosting Environment | Person_712 | 2018-02-20 01:00 | 2019-05-22 | 0.3 | 4.8313 | 1.4494 | Reduce | 0.25 | 4.8313 | 1.2078 | H2 | 4 | Stable | 0.7 | 104 | 136 | 146 | 132.3333 | 0.2 | 10 | 53 | 67 | 48.1667 | 0 | 16.6667 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK003 | Project_083_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supply Chain late delivery against Baseline Plan (Internal and External) | Person_391 | 2018-02-20 01:00 | 2019-05-16 | 0.6 | 2.3988 | 1.4393 | Reduce | 0.4 | 2.3988 | 0.95952 | H2 | 4 | Stable | 0.8 | 87 | 130 | 152 | 126.5 | 0.4 | 37 | 40 | 65 | 43.6667 | 0 | 33.3333 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK017 | Project_083_RISK017 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Modules Obsolescence Resolution - Domestic Programmes | Person_712 | 2018-03-17 01:00 | 2019-01-20 01:00 | 0.15 | 10.3732 | 1.556 | Reduce | 0.15 | 10.3732 | 1.556 | H3 | 3 | Stable | 0.8 | 105 | 138 | 159 | 136 | 0.2 | 2 | 58 | 72 | 51 | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK016 | Project_083_RISK016 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Dependencies on product | Person_465 | 2018-03-17 01:00 | 2019-01-20 01:00 | 0.3 | 12.3182 | 3.6955 | Avoid | 0.15 | 12.3182 | 1.8477 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK022 | Project_083_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Availability of Engineering Resource | Person_712 | 2018-03-17 01:00 | 2019-01-20 01:00 | 0.4 | 0 | 0 | Reduce | 0.2 | 5.4459 | 1.0892 | H3 | 3 | Stable | 0.6 | 91 | 125 | 152 | 123.8333 | 0.1 | 22 | 50 | 67 | 48.1667 | -inf | 50 | 1 | -inf
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK002 | Project_083_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supply Chain Cost Increase - post Engineering design until completion of Procurement Phase | Person_391 | 2018-02-20 01:00 | 2019-01-20 01:00 | 0.65 | 5.8349 | 3.7927 | Reduce | 0.25 | 4.8385 | 1.2096 | H2 | 4 | Stable | 0.5 | 87 | 122 | 157 | 122 | 0.4 | 35 | 41 | 61 | 43.3333 | 17.0777 | 61.5385 | 0 | 10.2466
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK024 | Project_083_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability of Data to support Customer Deliverable updates aligned to Customer Deliverable delivery dates | Person_712 | 2018-03-17 01:00 | 2019-01-20 01:00 | 0.4 | 9.2062 | 3.6825 | Reduce | 0.35 | 7.754 | 2.7139 | H2 | 4 | Stable | 0.9 | 101 | 125 | 151 | 125.3333 | 0.4 | 9 | 58 | 67 | 51.3333 | 15.7746 | 12.5 | 0 | 9.4648
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK023 | Project_083_RISK023 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Customer Deliverables - Read Across from product | Person_712 | 2018-03-17 01:00 | 2019-01-20 01:00 | 0.6 | 4.279 | 2.5674 | Reduce | 0.4 | 2.8267 | 1.1307 | H3 | 3 | Stable | 0.9 | 86 | 126 | 158 | 124.6667 | 0.2 | 18 | 42 | 65 | 41.8333 | 33.9395 | 33.3333 | 0 | 20.3637
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_093 | Risk010 | Project_093_Risk010 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Solution for Video Combination | Person_516 | 2018-07-08 | 2018-08-21 | 0.4 | 6.7219 | 2.6887 | Accept | 0.4 | 6.7219 | 2.6887 | H3 | 3 | Stable | 0.5 | 81 | 138 | 145 | 129.6667 | 0.5 | 81 | 138 | 145 | 129.6667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | OP001 | Project_083_OP001 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply chain | Cross Project Procurement | Person_391 | 2018-02-20 01:00 | 2019-01-20 01:00 | 0.2 | 4.2141 | 0.84283 | Exploit | 0.7 | 4.2141 | 2.9499 | H3 | 3 | Stable | [10 empty] | 0 | -250 | 1 | -7.5
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2018-05-22 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.7 | 84 | 134 | 156 | 129.3333 | 0.4 | 23 | 41 | 77 | 44 | 0 | 40 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_093 | Risk008 | Project_093_Risk008 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Legacy Code aand documentation | Person_342 | 2018-07-08 | 2018-08-21 | 0.3 | 11.0894 | 0.55447 | Accept | 0.3 | 11.0894 | 0.33268 | H3 | 3 | Stable | 0.9 | 107 | 127 | 153 | 128 | 0.9 | 107 | 127 | 153 | 128 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 0.92411 | 0.55447 | Reduce | 0.5 | 0.36965 | 0.18482 | H2 | 4 | Stable | 0.6 | 106 | 125 | 145 | 125.1667 | 0.2 | 37 | 59 | 63 | 56 | 60 | 16.6667 | 0 | 36
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-03 18:00 | 2018-04-21 | 0.2 | 4.0661 | 0.81322 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.6 | 112 | 137 | 149 | 134.8333 | 0.2 | 4 | 58 | 78 | 52.3333 | 0 | 75 | 1 | 2.25
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.5 | 0.46206 | 0.23103 | H1 | 5 | Stable | 0.6 | 99 | 133 | 154 | 130.8333 | 0.3 | 27 | 40 | 60 | 41.1667 | 58.3333 | 16.6667 | 0 | 35
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_093 | Risk009 | Project_093_Risk009 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Tracker Algorithm performace | Person_342 | 2018-07-08 | 2018-07-22 | 0.25 | 1.1089 | 0.88715 | Accept | 0.25 | 0.73929 | 0.44357 | H2 | 4 | Stable | 0.9 | 119 | 130 | 151 | 131.6667 | 0.9 | 119 | 130 | 151 | 131.6667 | 33.3333 | 0 | 0 | 20
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-28 18:00 | 2018-05-22 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.7 | 103 | 126 | 151 | 126.3333 | 0.2 | 7 | 56 | 77 | 51.3333 | 0 | 50 | 1 | 1.5
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2018-05-22 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.9 | 97 | 131 | 148 | 128.1667 | 0.2 | 39 | 43 | 65 | 46 | 0 | 25 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_693 | 2012-06-01 | 2018-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Improving | 0.8 | 112 | 138 | 156 | 136.6667 | 0.1 | 23 | 49 | 69 | 48 | 0 | 40 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2018-05-21 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Stable | [10 empty] | 0 | 37.5 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK030 | Project_083_RISK030 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Additional (unknown) support as result of sub-system learning within supply and customer | Person_644 | 2017-11-20 01:00 | 2020-11-19 01:00 | 0.4 | 3.6965 | 0.36965 | Accept | 0.4 | 3.6965 | 0.18482 | H3 | 3 | Stable | 0.6 | 88 | 123 | 153 | 122.1667 | 0.6 | 88 | 123 | 153 | 122.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-19 18:00 | 0.05 | 0.92411 | 0.18482 | Accept | 0.03 | 0.92411 | 0.18482 | H2 | 4 | Stable | 0.6 | 80 | 132 | 147 | 125.8333 | 0.6 | 80 | 132 | 147 | 125.8333 | 0 | 40 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2018-04-22 | 0.8 | 1.8482 | 0.55447 | Accept | 0.6 | 1.8482 | 0.36965 | H1 | 5 | Stable | 0.5 | 80 | 123 | 141 | 118.8333 | 0.5 | 80 | 123 | 141 | 118.8333 | 0 | 25 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2018-02-18 18:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.6 | 110 | 132 | 149 | 131.1667 | 0.4 | 33 | 51 | 69 | 51 | 90 | 75 | 1 | 56.25
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-26 18:00 | 2018-05-22 | 0.1 | 0.36965 | 0.25875 | Accept | 0.05 | 0.36965 | 0.25875 | H2 | 4 | Stable | 0.8 | 82 | 129 | 156 | 125.6667 | 0.8 | 82 | 129 | 156 | 125.6667 | 0 | 50 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK010 | Project_010_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Use of Lead components | Person_359 | 2012-05-23 | 2025-04-22 | 0.05 | 1.8482 | 0.092411 | Reduce | 0.05 | 1.8482 | 0.092411 | H3 | 3 | Stable | 0.5 | 113 | 126 | 160 | 129.5 | 0.2 | 23 | 48 | 71 | 47.6667 | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK003 | Project_044_RISK003 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Unavailability / failure of Range | Person_763 | 2018-06-15 | 2019-10-21 01:00 | 0.7 | 21.7314 | 15.212 | Reduce | 0.2 | 2.5957 | 0.51914 | H3 | 3 | Stable | 0.8 | 104 | 130 | 158 | 130.3333 | 0.1 | 25 | 47 | 78 | 48.5 | 88.0556 | 71.4286 | 0 | 52.8333
2018-07-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK001 | Project_044_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Non-compliance with regs | Person_763 | 2018-07-14 | 2019-02-10 01:00 | 0.5 | 10.262 | 5.131 | Reduce | 0.3 | 2.5957 | 0.77871 | H3 | 3 | Stable | 0.6 | 102 | 137 | 145 | 132.5 | 0.4 | 21 | 50 | 69 | 48.3333 | 74.7059 | 40 | 0 | 44.8235
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2018-05-21 | 0.2 | 5.2705 | 2.1082 | Accept | 0.2 | 5.2705 | 2.1082 | H3 | 3 | Worsening | 0.8 | 118 | 128 | 150 | 130 | 0.8 | 118 | 128 | 150 | 130 | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-113 | Project_043_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | No Gen 1 products available, transition cost to Gen 2 | Person_769 | 2017-04-19 | 2020-12-20 23:00 | 0.3 | 1.4971 | 0.44912 | Reduce | 0.3 | 1.4971 | 0.44912 | H2 | 4 | Stable | 0.8 | 102 | 131 | 145 | 128.5 | 0.4 | 26 | 46 | 66 | 46 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-121 | Project_043_Risk-121 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | More Tech Pubs Update than estimated | Person_769 | 2019-01-20 23:00 | 2020-10-19 23:00 | 0.45 | 1.7366 | 0.78146 | Reduce | 0.45 | 1.7366 | 0.78146 | H1 | 5 | Stable | 0.7 | 109 | 136 | 158 | 135.1667 | 0.3 | 12 | 57 | 63 | 50.5 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-084 | Project_043_Risk-084 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | complex repair ( over and above the forecast average) | Person_693 | 2017-12-20 23:00 | 2020-12-20 23:00 | 0.2 | 0.71859 | 0.14372 | Reduce | 0.2 | 0.71859 | 0.14372 | H2 | 4 | Stable | 0.5 | 120 | 125 | 143 | 127.1667 | 0.3 | 20 | 48 | 61 | 45.5 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-128 | Project_043_Risk-128 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Reliance of Customer Avaliability | Person_135 | 2017-04-19 | 2018-08-21 | 0.5 | 1.7665 | 0.88326 | Reduce | 0.1 | 1.7665 | 0.17665 | H2 | 4 | Stable | 0.6 | 115 | 134 | 152 | 133.8333 | 0.1 | 16 | 42 | 62 | 41 | 0 | 80 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-089 | Project_043_Risk-089 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares pool is limited | Person_307 | 2018-12-21 23:00 | 2020-12-20 23:00 | 0.25 | 1.5969 | 0.39921 | Reduce | 0.25 | 1.2775 | 0.31937 | H2 | 4 | Stable | 0.9 | 111 | 131 | 157 | 132 | 0.3 | 31 | 57 | 63 | 53.6667 | 20 | 0 | 0 | 12
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-039 | Project_043_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System fails to achieve required performance | Person_051 | 2017-04-19 | 2018-11-19 23:00 | 0.3 | 4.7906 | 1.4372 | Reduce | 0.3 | 4.7906 | 1.4372 | H2 | 4 | Stable | 0.6 | 80 | 129 | 157 | 125.5 | 0.4 | 6 | 44 | 75 | 42.8333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2018-04-22 | 0.3 | 0.038035 | 0.036134 | Accept | 0.2 | 0.038035 | 0.036134 | H3 | 3 | Stable | 0.6 | 87 | 131 | 158 | 128.1667 | 0.6 | 87 | 131 | 158 | 128.1667 | 0 | 33.3333 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-22 | 2019-08-21 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-22 | 2019-08-21 | 0.5 | 3.3188 | 1.6594 | Avoid | 0.5 | 3.3188 | 1.6594 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--46 | Project_021_Risk--46 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-08-08 | 2018-11-05 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.6 | 104 | 131 | 143 | 128.5 | 0.4 | 18 | 56 | 61 | 50.5 |  | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--45 | Project_021_Risk--45 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Additional work of deliverables may be required from Customer - Customer to complete System CoD | Person_470 | 2018-05-23 | 2018-11-20 01:00 | 0.5 | 6.0147 | 3.0074 | Reduce | 0.3 | 6.0147 | 1.8044 | H2 | 4 | Stable | 0.6 | 109 | 122 | 144 | 123.5 | 0.4 | 18 | 40 | 68 | 41 | 0 | 40 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK018 | Project_038_RISK018 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Last System Syndrome | Person_329 | 2012-11-20 01:00 | 2019-01-21 01:00 | 0.15 | 43.4175 | 6.5126 | Reduce | 0.13 | 43.4175 | 5.6443 | H2 | 4 | Worsening | 0.6 | 101 | 123 | 148 | 123.5 | 0.1 | 34 | 52 | 77 | 53.1667 | 0 | 13.3333 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK016 | Project_038_RISK016 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Supplier Quality Issues | Person_770 | 2012-11-20 01:00 | 2018-08-22 01:00 | 0.5 | 5.0339 | 2.517 | Reduce | 0.5 | 5.0339 | 2.517 | H2 | 4 | Worsening | 0.7 | 112 | 127 | 148 | 128 | 0.4 | 28 | 43 | 79 | 46.5 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--47 | Project_021_Risk--47 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Delay to sub-system and other Component dependencies due to supply chain dependencies | Person_615 | 2018-08-09 | 2018-12-21 01:00 | 0.4 | 2.4645 | 0.4929 | Accept | 0.4 | 2.4645 | 0.4929 | H2 | 4 | Stable | 0.8 | 82 | 137 | 159 | 131.5 | 0.8 | 82 | 137 | 159 | 131.5 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK018 | Project_038_RISK018 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Last System Syndrome | Person_329 | 2012-11-20 | 2018-10-21 | 0.15 | 43.4175 | 6.5126 | Reduce | 0.13 | 43.4175 | 5.6443 | H2 | 4 | Worsening | 0.6 | 81 | 140 | 142 | 130.5 | 0.4 | 34 | 48 | 71 | 49.5 | 0 | 13.3333 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK016 | Project_038_RISK016 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Supplier Quality Issues | Person_397 | 2012-11-20 | 2018-08-22 | 0.5 | 5.0339 | 2.517 | Avoid | 0.5 | 5.0339 | 2.517 | H2 | 4 | Worsening | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-099 | Project_008_Risk-099 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Risk on Consumables Exposure | Person_639 | 2017-08-04 | 2018-08-21 | 0.5 | 5.6817 | 2.8408 | Reduce | 0.5 | 5.6817 | 2.8408 | H3 | 3 | Stable | 0.5 | 111 | 134 | 160 | 134.5 | 0.1 | 29 | 48 | 78 | 49.8333 | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-148 | Project_008_SER-148 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Demands but not provisioned | Person_639 | 2017-08-21 01:00 | 2018-08-21 | 0.3 | 49.7149 | 7.4572 | Accept | 0.3 | 49.7149 | 7.4572 | H3 | 3 | Stable | 0.6 | 106 | 123 | 141 | 123.1667 | 0.6 | 106 | 123 | 141 | 123.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-094 | Project_008_Risk-094 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Consumable Stock Levels | Person_567 | 2017-04-22 | 2018-08-21 | 0.5 | 33.9324 | 6.7865 | Accept | 0.5 | 33.9324 | 6.7865 | H3 | 3 | Stable | 0.6 | 112 | 134 | 154 | 133.6667 | 0.6 | 112 | 134 | 154 | 133.6667 | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-082 | Project_008_Risk-082 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Insufficient spares to maintain the Training availability | Person_639 | 2017-05-23 | 2018-08-21 | 0.15 | 6.6286 | 0.9943 | Reduce | 0.15 | 6.6286 | 0.9943 | H2 | 4 | Stable | 0.7 | 107 | 140 | 142 | 134.8333 | 0.2 | 35 | 49 | 76 | 51.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | SER-034 | Project_008_SER-034 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_567 | 2018-05-22 | 2018-08-21 | 0.25 | 13.4066 | 5.3626 | Accept | 0.25 | 13.4066 | 5.3626 | H3 | 3 | Stable | 0.7 | 120 | 133 | 151 | 133.8333 | 0.7 | 120 | 133 | 151 | 133.8333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | R054 | Project_066_R054 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | System Cybersecurity shortfalls | Person_549 | 2017-01-21 01:00 | 2024-05-23 | 0.8 | 15.7936 | 12.6349 | Reduce | 0.5 | 15.7936 | 7.8968 | H1 | 5 | Stable | 0.9 | 94 | 122 | 152 | 122.3333 | 0.2 | 27 | 54 | 70 | 52.1667 | 0 | 37.5 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Repairs at Supplier | Person_567 | 2017-08-21 01:00 | 2018-08-21 | 0.15 | 18.5516 | 12.9861 | Accept | 0.15 | 18.5516 | 12.9861 | H3 | 3 | Stable | 0.9 | 91 | 122 | 154 | 122.1667 | 0.9 | 91 | 122 | 154 | 122.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Lack of Spares Availability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 0.2 | 8.8305 | 2.6492 | Accept | 0.2 | 8.8305 | 2.6492 | H3 | 3 | Stable | 0.7 | 84 | 140 | 143 | 131.1667 | 0.7 | 84 | 140 | 143 | 131.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | R181 | Project_066_R181 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | USB Hub start up issues | Person_247 | 2017-01-21 01:00 | 2024-05-23 | 1 | 186.9553 | 59.2026 | Accept | 1 | 186.9553 | 1.3939 | H1 | 5 | Stable | 0.9 | 112 | 122 | 144 | 124 | 0.9 | 112 | 122 | 144 | 124 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-20 21:00 | 2020-08-19 21:00 | 0.5 | 22.8501 | 6.855 | Accept | 0.5 | 22.8501 | 6.855 | H2 | 4 | Stable | 0.5 | 120 | 125 | 147 | 127.8333 | 0.5 | 120 | 125 | 147 | 127.8333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Additional minor point releases | Person_228 | 2016-05-23 | 2017-10-19 01:00 | 0.5 | 11.9444 | 5.9722 | Reduce | 0.45 | 11.9444 | 5.375 | H1 | 5 | Stable | 0.5 | 116 | 128 | 152 | 130 | 0.1 | 24 | 47 | 68 | 46.6667 | 0 | 10 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Additional Trials e.g. product - Cost | Person_228 | 2016-05-23 | 2018-04-21 | 0.4 | 16.2288 | 6.4915 | Reduce | 0.2 | 16.2288 | 3.2458 | H2 | 4 | Stable | 0.6 | 105 | 124 | 156 | 126.1667 | 0.1 | 29 | 49 | 69 | 49 | 0 | 50 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_004 | 2015-11-21 01:00 | 2018-11-20 01:00 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.6 | 110 | 134 | 150 | 132.6667 | 0.2 | 21 | 56 | 62 | 51.1667 | 0 | 5 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.8 | 2.8043 | 2.2435 | Reduce | 0.45 | 2.8043 | 1.2619 | H1 | 5 | Stable | 0.6 | 119 | 129 | 146 | 130.1667 | 0.4 | 2 | 48 | 78 | 45.3333 | 0 | 43.75 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK167 | Project_024_RISK167 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Customer not providing the information needed or Customer not accepting the Customer documentation resulting in rewor. | Person_710 | 2016-08-21 01:00 | 2018-05-21 | 0.5 | 9.971 | 4.9855 | Reduce | 0.3 | 9.971 | 2.9913 | H1 | 5 | Worsening | 0.8 | 111 | 123 | 152 | 125.8333 | 0.2 | 32 | 56 | 74 | 55 | 0 | 40 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK226 | Project_024_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Late Evidences Certification delivery | Person_642 | 2017-04-30 | 2018-05-21 | 0.4 | 3.9468 | 1.5787 | Reduce | 0.2 | 3.9468 | 0.78937 | H2 | 4 | Worsening | 0.9 | 83 | 136 | 153 | 130 | 0.3 | 38 | 42 | 67 | 45.5 | 0 | 50 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2017-02-20 01:00 | 2018-05-22 | 0.1 | 35.9673 | 10.7902 | Accept | 0.1 | 35.9673 | 9.7112 | H3 | 3 | Stable | 0.8 | 116 | 124 | 157 | 128.1667 | 0.8 | 116 | 124 | 157 | 128.1667 | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK003 | Project_024_RISK003 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance | Person_288 | 2017-12-21 01:00 | 2018-08-21 | 0.31667 | 3.9728 | 1.3905 | Accept | 0.007456 | 3.9728 | 1.3905 | H2 | 4 | Stable | 0.8 | 89 | 139 | 153 | 133 | 0.8 | 89 | 139 | 153 | 133 | 0 | 97.6455 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.5 | 9.2179 | 4.609 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.5 | 90 | 131 | 156 | 128.3333 | 0.3 | 3 | 54 | 67 | 47.6667 | 0 | 60 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis and Security | Person_288 | 2017-02-22 01:00 | 2017-11-19 01:00 | 0.3 | 19.9938 | 5.9981 | Reduce | 0.04675 | 19.9938 | 0.93471 | H3 | 3 | Improving | 0.8 | 86 | 134 | 150 | 128.6667 | 0.3 | 33 | 45 | 62 | 45.8333 | 0 | 84.4167 | 1 | 2.5325
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.5 | 3.843 | 1.9215 | Reduce | 0.2 | 3.843 | 0.76859 | H2 | 4 | Stable | 0.9 | 113 | 124 | 150 | 126.5 | 0.2 | 16 | 41 | 65 | 40.8333 | 0 | 60 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Performance (collector opportunity) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.373 | 19.5316 | 7.2853 | -- | 0.4158 | 19.5316 | 8.1213 | H1 | 5 | Stable | [10 empty] | 0 | -11.4745 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.3 | 20.8767 | 6.263 | H1 | 5 | Stable | 0.6 | 98 | 135 | 159 | 132.8333 | 0.4 | 14 | 49 | 72 | 47 | 50 | 25 | 0 | 30
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 0.504 | 73.3644 | 36.9756 | Reduce | 0.2975 | 53.773 | 15.9975 | H1 | 5 | Worsening | 0.8 | 82 | 121 | 150 | 119.3333 | 0.4 | 32 | 40 | 62 | 42.3333 | 26.7042 | 40.9722 | 0 | 16.0225
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK308 | Project_024_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System robustness and resilience | Person_774 | 2017-04-06 | 2018-06-11 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.1 | 2.5966 | 0.25966 | H3 | 3 | Stable | 0.9 | 117 | 129 | 141 | 129 | 0.3 | 3 | 46 | 68 | 42.5 | 58.3333 | 66.6667 | 1 | 37
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-22 01:00 | 2019-08-21 01:00 | 0.2 | 30.1713 | 6.0343 | Avoid | 0.2 | 30.1713 | 6.0343 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-22 01:00 | 2019-08-21 01:00 | 0.5 | 3.3188 | 1.6594 | Avoid | 0.5 | 3.3188 | 1.6594 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Management Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 0.3 | 5.5452 | 1.6635 | Accept | 0.3 | 5.5452 | 1.6635 | H1 | 5 | Improving | 0.7 | 111 | 121 | 157 | 125.3333 | 0.7 | 111 | 121 | 157 | 125.3333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before part b finished | Person_119 | 2016-10-20 01:00 | 2018-04-21 | 0.3 | 0.69417 | 0.13883 | Accept | 0.27 | 0.69417 | 0.13883 | H2 | 4 | Worsening | 0.7 | 85 | 126 | 154 | 123.8333 | 0.7 | 85 | 126 | 154 | 123.8333 | 0 | 10 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-013 | Project_052_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Additional material and effort required to support the delta equipment | Person_271 | 2017-08-19 01:00 | 2020-08-20 01:00 | 0.45 | 20.4694 | 10.2347 | Accept | 0.45 | 20.4694 | 10.2347 | H2 | 4 | Stable | 0.5 | 102 | 139 | 144 | 133.6667 | 0.5 | 102 | 139 | 144 | 133.6667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-010 | Project_052_Risk-010 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Potential update of software / hardware required during the 3 year support period (RESOURCE) | Person_376 | 2017-08-19 01:00 | 2020-08-19 01:00 | 0.25 | 1.7748 | 0.4437 | Accept | 0.25 | 1.7748 | 0.4437 | H3 | 3 | Stable | 0.7 | 90 | 129 | 153 | 126.5 | 0.7 | 90 | 129 | 153 | 126.5 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier Selection Process | Person_379 | 2017-10-19 01:00 | 2019-04-23 | 0.4 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 114 | 136 | 149 | 134.5 | 0.2 | 1 | 49 | 75 | 45.3333 |  | 25 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Colour Representation in Video Image Distortion | Person_305 | 2017-09-22 01:00 | 2019-11-28 01:00 | 0.5 | 5.5323 | 2.7662 | Reduce | 0.1 | 5.5323 | 0.55323 | H3 | 3 | Stable | 0.8 | 107 | 138 | 154 | 135.5 | 0.1 | 13 | 48 | 61 | 44.3333 | 0 | 80 | 1 | 2.4
2018-07-22 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-009 | Project_052_Risk-009 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | System acceptance not costed in line with Customer expectations | Person_651 | 2017-08-19 01:00 | 2018-06-22 | 0.1 | 3.4651 | 1.0395 | Accept | 0.1 | 3.4651 | 1.0395 | H3 | 3 | Stable | 0.9 | 110 | 135 | 155 | 134.1667 | 0.9 | 110 | 135 | 155 | 134.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-21 01:00 | 2018-07-20 | 0.5 | 28.0275 | 14.0137 | Reduce | 0.1 | 28.0275 | 2.8027 | H3 | 3 | Stable | 0.6 | 105 | 133 | 150 | 131.1667 | 0.1 | 16 | 53 | 70 | 49.6667 | 0 | 80 | 1 | 2.4
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-21 01:00 | 0.8 | 35.2369 | 28.1895 | Reduce | 0.3 | 18.4979 | 5.5494 | H2 | 4 | Stable | 0.6 | 114 | 129 | 156 | 131 | 0.4 | 12 | 53 | 63 | 47.8333 | 47.5042 | 62.5 | 0 | 28.5025
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 4 | 9. Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-21 01:00 | 0.7 | 20.6835 | 14.4785 | Reduce | 0.3 | 20.6835 | 6.2051 | H2 | 4 | Stable | 0.7 | 99 | 129 | 160 | 129.1667 | 0.4 | 16 | 41 | 69 | 41.5 | 0 | 57.1429 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 4 | 8. System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 0.6 | 5.2585 | 3.1551 | Reduce | 0.15 | 5.2585 | 0.78877 | H2 | 4 | Stable | 0.9 | 98 | 130 | 144 | 127 | 0.2 | 31 | 56 | 75 | 55 | 0 | 75 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-07-21 | 0.3 | 2.723 | 0.81691 | Reduce | 0.1 | 2.723 | 0.2723 | H3 | 3 | Improving | 0.6 | 91 | 139 | 157 | 134 | 0.3 | 27 | 40 | 76 | 43.8333 | 0 | 66.6667 | 1 | 2
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.6 | 86 | 121 | 145 | 119.1667 | 0.3 | 31 | 44 | 72 | 46.5 | 60.3671 | 58.3333 | 0 | 36.2202
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 0.3 | 4.8444 | 1.4533 | Reduce | 0.2 | 4.8444 | 0.96888 | H3 | 3 | Stable | 0.9 | 101 | 131 | 151 | 129.3333 | 0.2 | 13 | 56 | 62 | 49.8333 | 0 | 33.3333 | 1 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System Performance | Person_305 | 2016-09-08 01:00 | 2020-09-21 01:00 | 0.3 | 5.8725 | 1.7618 | Reduce | 0.1 | 5.8725 | 0.58725 | H2 | 4 | Stable | 0.7 | 87 | 124 | 148 | 121.8333 | 0.3 | 31 | 59 | 76 | 57.1667 | 0 | 66.6667 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_572 | 2020-05-23 | 2023-10-26 01:00 | 0.2 | 7.4599 | 1.492 | Reduce | 0.05 | 7.4599 | 0.37299 | H2 | 4 | Stable | 0.7 | 80 | 128 | 141 | 122.1667 | 0.1 | 23 | 46 | 69 | 46 | 0 | 75 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-29 01:00 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.9 | 116 | 133 | 152 | 133.3333 | 0.4 | 1 | 45 | 63 | 40.6667 | 60.3671 | 58.3333 | 0 | 36.2202
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-20 01:00 | 0.4 | 2.8643 | 1.1457 | Reduce | 0.1 | 2.8643 | 0.28643 | H3 | 3 | Stable | 0.8 | 111 | 124 | 149 | 126 | 0.2 | 29 | 49 | 77 | 50.3333 | 0.0015933 | 75 | 1 | 2.251
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power Supply - Motor Controller Interface | Person_179 | 2016-05-23 | 2018-09-19 01:00 | 0.5 | 25.3543 | 12.6771 | Reduce | 0.2 | 25.3543 | 5.0709 | H3 | 3 | Stable | 0.8 | 99 | 128 | 159 | 128.3333 | 0.4 | 31 | 56 | 69 | 54 | 0 | 60 | 1 | 1.8
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 0.1 | 12.7232 | 1.2723 | Reduce | 0.1 | 12.7232 | 1.2723 | H3 | 3 | Stable | 0.8 | 118 | 123 | 154 | 127.3333 | 0.2 | 34 | 41 | 65 | 43.8333 | 0 | 0 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | EMC non compliance | Person_047 | 2023-05-24 | 2023-12-01 01:00 | 0.7 | 3.935 | 2.7545 | Reduce | 0.5 | 3.935 | 1.9675 | H2 | 4 | Stable | 0.5 | 86 | 130 | 147 | 125.5 | 0.2 | 30 | 56 | 64 | 53 | 0 | 28.5714 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SubSystem System Design | Person_038 | 2017-10-01 01:00 | 2019-11-20 01:00 | 0.2 | 1.5213 | 0.30425 | Reduce | 0.1 | 1.5213 | 0.15213 | H3 | 3 | Stable | 0.9 | 118 | 131 | 142 | 130.6667 | 0.1 | 3 | 57 | 78 | 51.5 | 0 | 50 | 1 | 1.5
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-21 01:00 | 2023-12-22 01:00 | 0.4 | 30.1969 | 12.0788 | Reduce | 0.25 | 30.1969 | 7.5492 | H2 | 4 | Stable | 0.5 | 96 | 121 | 145 | 120.8333 | 0.4 | 13 | 46 | 75 | 45.3333 | 0 | 37.5 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | In-house development of sub-system estimate is low | Person_418 | 2016-03-23 | 2018-06-06 | 0.5 | 6.5118 | 3.2559 | Reduce | 0.2 | 1.506 | 0.30121 | H3 | 3 | Stable | 0.8 | 98 | 123 | 153 | 123.8333 | 0.4 | 7 | 52 | 68 | 47.1667 | 76.8722 | 60 | 0 | 46.1233
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-10-20 01:00 | 0.4 | 1.0142 | 0.40567 | Reduce | 0.1 | 1.0142 | 0.10142 | H3 | 3 | Stable | 0.6 | 107 | 127 | 160 | 129.1667 | 0.4 | 2 | 51 | 71 | 46.1667 | 0 | 75 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | 9. Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 0.8 | 19.1678 | 15.3343 | Reduce | 0.2 | 2.8752 | 0.57503 | H3 | 3 | Stable | 0.5 | 88 | 126 | 157 | 124.8333 | 0.2 | 28 | 50 | 67 | 49.1667 | 85 | 75 | 0 | 51
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 0.25 | 0.63626 | 0.15906 | Reduce | 0.05 | 0.63626 | 0.031813 | H3 | 3 | Stable | 0.6 | 86 | 130 | 153 | 126.5 | 0.1 | 27 | 41 | 66 | 42.8333 | 0 | 80 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Component Shock test failure | Person_020 | 2016-09-08 01:00 | 2019-11-15 01:00 | 0.4 | 0.8467 | 0.33868 | Reduce | 0.2 | 0.8467 | 0.16934 | H3 | 3 | Stable | 0.9 | 100 | 125 | 145 | 124.1667 | 0.1 | 3 | 56 | 61 | 48 | 0 | 50 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-06 01:00 | 2019-09-13 01:00 | 0.8 | 8.0322 | 6.4258 | Reduce | 0.5 | 4.006 | 2.003 | H2 | 4 | Stable | 0.5 | 113 | 133 | 143 | 131.3333 | 0.1 | 37 | 59 | 79 | 58.6667 | 50.1263 | 37.5 | 0 | 30.0758
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-04-22 | 0.8 | 18.0459 | 14.4367 | Reduce | 0.2 | 3.0076 | 0.60153 | H3 | 3 | Stable | 0.6 | 100 | 132 | 157 | 130.8333 | 0.3 | 2 | 54 | 65 | 47.1667 | 83.3335 | 75 | 1 | 52.2501
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 0.4 | 5.1004 | 2.0402 | Reduce | 0.2 | 2.5506 | 0.51013 | H3 | 3 | Stable | 0.5 | 116 | 135 | 146 | 133.6667 | 0.3 | 17 | 42 | 74 | 43.1667 | 49.9917 | 50 | 0 | 29.995
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Additional minor point release | Person_228 | 2016-05-23 | 2019-06-23 | 0.5 | 11.9444 | 5.9722 | Reduce | 0.25 | 11.9444 | 2.9861 | H2 | 4 | Stable | 0.9 | 92 | 136 | 157 | 132.1667 | 0.4 | 27 | 54 | 66 | 51.5 | 0 | 50 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 5 | 14. Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_004 | 2015-11-21 01:00 | 2019-07-21 | 0.4 | 15.5623 | 6.2249 | Reduce | 0.38 | 15.5623 | 5.9137 | H1 | 5 | Stable | 0.9 | 108 | 123 | 154 | 125.6667 | 0.3 | 16 | 58 | 67 | 52.5 | 0 | 5 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 0.3 | 3.9728 | 1.3905 | Accept | 0.3 | 3.9728 | 1.3905 | H3 | 3 | Stable | 0.6 | 95 | 121 | 154 | 122.1667 | 0.6 | 95 | 121 | 154 | 122.1667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System architecture not adequate to meet performance requirements. | Person_067 | 2017-09-21 01:00 | 2018-11-08 01:00 | 0.3 | 9.2179 | 2.7654 | Reduce | 0.2 | 9.2179 | 1.8436 | H2 | 4 | Improving | 0.8 | 105 | 122 | 157 | 125 | 0.4 | 13 | 50 | 67 | 46.6667 | 0 | 33.3333 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Subsystem does not meet requirements | Person_233 | 2017-01-21 01:00 | 2019-02-28 01:00 | 0.5 | 1.2464 | 0.62318 | Reduce | 0.2 | 1.2464 | 0.24927 | H2 | 4 | Stable | 0.9 | 91 | 139 | 149 | 132.6667 | 0.2 | 4 | 40 | 77 | 40.1667 | 0 | 60 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Performance (collector opportunity) | Person_233 | 2017-01-21 01:00 | 2018-07-25 | 0.373 | 19.5316 | 7.2853 | -- | 0.4158 | 19.5316 | 8.1213 | H1 | 5 | Stable | [10 empty] | 0 | -11.4745 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK308 | Project_024_RISK308 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System robustness and resilience | Person_774 | 2018-10-22 01:00 | 2018-08-23 01:00 | 0.3 | 6.2318 | 1.8696 | Reduce | 0.1 | 2.5966 | 0.25966 | H3 | 3 | Stable | 0.9 | 109 | 137 | 143 | 133.3333 | 0.1 | 10 | 40 | 72 | 40.3333 | 58.3333 | 66.6667 | 1 | 37
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK003 | Project_024_RISK003 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance | Person_119 | 2017-12-21 01:00 | 2020-01-18 01:00 | 0.31667 | 5.6606 | 5.6606 | Accept | 0.04388 | 5.6606 | 5.6606 | H2 | 4 | Stable | 0.8 | 115 | 127 | 145 | 128 | 0.8 | 115 | 127 | 145 | 128 | 0 | 86.1432 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK341 | Project_024_RISK341 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Latent Technical Debt impacts acceptance | Person_067 | 2018-06-27 | 2019-02-28 01:00 | 0.6 | 2.4668 | 1.4801 | Reduce | 0.1 | 1.6878 | 0.16878 | H3 | 3 | Stable | 0.9 | 108 | 126 | 148 | 126.6667 | 0.2 | 4 | 43 | 65 | 40.1667 | 31.5789 | 83.3333 | 1 | 21.4474
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK297(015) | Project_024_RISK297(015) | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Issues not identified before part b finished | Person_119 | 2016-10-20 01:00 | 2018-09-20 01:00 | 0.3 | 0.77898 | 0.23369 | Accept | 0.27 | 0.77898 | 0.23369 | H2 | 4 | Worsening | 0.5 | 107 | 138 | 150 | 134.8333 | 0.5 | 107 | 138 | 150 | 134.8333 | 0 | 10 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK342 | Project_024_RISK342 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Unable to release updates to the software | Person_124 | 2017-10-26 01:00 | 2019-02-10 01:00 | 0.2 | 0.34751 | 0.069502 | Reduce | 0.2 | 0.34751 | 0.069502 | H3 | 3 | Stable | 0.7 | 102 | 135 | 141 | 130.5 | 0.3 | 7 | 45 | 67 | 42.3333 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK390 | Project_024_RISK390 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Customer drives scope change | Person_233 | 2018-01-21 01:00 | 2019-08-03 | 0.5 | 2.1292 | 1.0646 | Reduce | 0.3 | 1.6878 | 0.50634 | H1 | 5 | Stable | 0.5 | 119 | 130 | 157 | 132.6667 | 0.4 | 23 | 54 | 79 | 53 | 20.7317 | 40 | 0 | 12.439
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK399 | Project_024_RISK399 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Contract change items scope poorly defined | Person_067 | 2017-05-27 | 2018-11-08 01:00 | 0.2 | 3.289 | 0.65781 | Reduce | 0.2 | 3.289 | 0.65781 | H2 | 4 | Improving | 0.5 | 94 | 131 | 141 | 126.5 | 0.3 | 31 | 47 | 69 | 48 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK398 | Project_024_RISK398 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Non compliance against SSS drives minor design change. | Person_067 | 2017-01-21 01:00 | 2019-08-03 | 0.25 | 3.0121 | 0.75301 | Reduce | 0.2 | 1.6359 | 0.32717 | H3 | 3 | Stable | 0.8 | 93 | 134 | 156 | 130.8333 | 0.1 | 28 | 42 | 67 | 43.8333 | 45.6897 | 20 | 0 | 27.4138
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK397 | Project_024_RISK397 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Capability for each System release does not remain stable | Person_016 | 2017-01-21 01:00 | 2019-08-03 | 0.5 | 2.4408 | 1.2204 | Reduce | 0.45 | 1.2204 | 0.54918 | H1 | 5 | Improving | 0.9 | 99 | 136 | 150 | 132.1667 | 0.2 | 18 | 56 | 74 | 52.6667 | 50 | 10 | 0 | 30
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_061 | RISK003 | Project_061_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Test equipment reliability | Person_104 | 2017-05-23 | 2020-11-18 20:00 | 0.4 | 0.11013 | 0.044051 | Reduce | 0.3 | 0.11013 | 0.033038 | H2 | 4 | Stable | 0.7 | 84 | 125 | 141 | 120.8333 | 0.3 | 5 | 43 | 69 | 41 | 0 | 25 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Number of Problem Reports greater than planned | Person_186 | 2018-07-25 | 2019-02-28 01:00 | 0.4 | 41.7534 | 16.7013 | Reduce | 0.3 | 20.8767 | 6.263 | H1 | 5 | Stable | 0.5 | 80 | 132 | 160 | 128 | 0.4 | 27 | 56 | 79 | 55 | 50 | 25 | 0 | 30
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-015 | Project_096_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Ssub-system Accreditation | Person_623 | 2018-11-21 01:00 | 2019-04-23 | 0.15 | 7.6685 | 1.1503 | Transfer | 0.15 | 7.6685 | 1.1503 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-004 | Project_096_Risk-004 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Acceptance | Person_099 | 2019-01-22 01:00 | 2019-05-12 | 0.3 | 3.8342 | 1.1503 | Reduce | 0.1 | 3.8342 | 0.38342 | H3 | 3 | Improving | 0.5 | 87 | 129 | 147 | 125 | 0.4 | 5 | 40 | 67 | 38.6667 | 0 | 66.6667 | 1 | 2
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-005 | Project_096_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Availability of test site and Customer Furnished Equipment dependencies | Person_639 | 2019-03-02 01:00 | 2019-04-23 | 0.1 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.8 | 117 | 130 | 144 | 130.1667 | 0.3 | 21 | 52 | 68 | 49.5 |  | 0 | 1
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-007 | Project_096_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Dependency | Person_623 | 2018-03-23 | 2018-09-07 01:00 | 0.25 | 0.95856 | 0.23964 | Reduce | 0.4 | 0.95856 | 0.38342 | H2 | 4 | Worsening | 0.6 | 119 | 124 | 147 | 127 | 0.3 | 11 | 58 | 66 | 51.5 | 0 | -60 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-008 | Project_096_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Spiral Software update | Person_259 | 2018-02-20 01:00 | 2018-12-16 01:00 | 0.3 | 3.8342 | 1.1503 | Reduce | 0.2 | 3.8342 | 0.76685 | H2 | 4 | Stable | 0.9 | 83 | 136 | 145 | 128.6667 | 0.4 | 37 | 48 | 71 | 50 | 0 | 33.3333 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-009 | Project_096_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Assurance | Person_083 | 2018-10-05 01:00 | 2019-03-22 | 0.3 | 3.8342 | 1.1503 | Transfer | 0.25 | 3.8342 | 0.95856 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-001 | Project_096_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Suitably Qualified and experienced staff availability Resource availability | Person_083 | 2018-05-23 | 2018-12-22 01:00 | 0.3 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H2 | 4 | Improving | 0.9 | 116 | 137 | 158 | 137 | 0.2 | 33 | 55 | 68 | 53.5 |  | 33.3333 | 0
2018-07-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-014 | Project_096_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Hosting issues | Person_259 | 2018-06-23 | 2018-12-07 01:00 | 0.15 | 3.0354 | 0.45532 | Reduce | 0.15 | 3.0354 | 0.45532 | H3 | 3 | Stable | 0.8 | 110 | 121 | 148 | 123.6667 | 0.3 | 5 | 59 | 75 | 52.6667 | 0 | 0 | 1 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK343 | Project_024_RISK343 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Product technical debt requiring project resolution | Person_610 | 2017-01-21 01:00 | 2019-02-10 01:00 | 0.3 | 13.4066 | 5.3626 | Accept | 0.3 | 13.4066 | 5.3626 | H3 | 3 | Improving | 0.5 | 99 | 121 | 154 | 122.8333 | 0.5 | 99 | 121 | 154 | 122.8333 | 0 | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | R055 | Project_066_R055 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Shortfall in availability of system Testing/Development Assets | Person_549 | 2017-07-21 | 2018-10-21 01:00 | 0.7 | 13.3571 | 9.35 | Reduce | 0.3 | 6.6786 | 2.0036 | H1 | 5 | Stable | 0.5 | 109 | 138 | 150 | 135.1667 | 0.1 | 30 | 54 | 60 | 51 | 50 | 57.1429 | 0 | 30
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | R054 | Project_066_R054 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | System Cybersecurity shortfalls | Person_549 | 2017-07-21 | 2018-10-21 01:00 | 0.8 | 15.7936 | 12.6349 | Reduce | 0.5 | 15.7936 | 7.8968 | H1 | 5 | Stable | 0.5 | 100 | 131 | 148 | 128.6667 | 0.1 | 38 | 42 | 74 | 46.6667 | 0 | 37.5 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK392 | Project_024_RISK392 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Rig maintenance is not adequate | Person_016 | 2017-01-21 01:00 | 2019-08-03 | 0.2 | 19.6523 | 9.8261 | Accept | 0.2 | 19.6523 | 9.8261 | H2 | 4 | Stable | 0.9 | 96 | 131 | 146 | 127.6667 | 0.9 | 96 | 131 | 146 | 127.6667 | 0 | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK395 | Project_024_RISK395 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Latent Defects | Person_348 | 2017-09-21 01:00 | 2018-12-15 01:00 | 0.2 | 17.6858 | 5.3057 | Accept | 0.2 | 17.6858 | 5.3057 | H2 | 4 | Improving | 0.8 | 104 | 132 | 146 | 129.6667 | 0.8 | 104 | 132 | 146 | 129.6667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | R151 | Project_066_R151 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | system Pulse recording degradation | Person_507 | 2017-08-21 01:00 | 2019-08-21 01:00 | 0.4 | 4.2991 | 1.0748 | Accept | 0.4 | 4.2991 | 1.0748 | H3 | 3 | Stable | 0.8 | 116 | 132 | 157 | 133.5 | 0.8 | 116 | 132 | 157 | 133.5 | 0 | 0 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-013 | Project_052_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Additional material and effort required to support the delta equipment | Person_271 | 2017-08-19 01:00 | 2020-08-20 01:00 | 0.45 | 5.5452 | 1.6635 | Accept | 0.45 | 5.5452 | 1.6635 | H2 | 4 | Stable | 0.9 | 94 | 128 | 156 | 127 | 0.9 | 94 | 128 | 156 | 127 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-010 | Project_052_Risk-010 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Potential update of software / hardware required during the 3 year support period (RESOURCE) | Person_376 | 2017-08-19 01:00 | 2020-08-19 01:00 | 0.25 | 0.69417 | 0.13883 | Accept | 0.25 | 0.69417 | 0.13883 | H3 | 3 | Stable | 0.9 | 103 | 128 | 150 | 127.5 | 0.9 | 103 | 128 | 150 | 127.5 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_052 | Risk-009 | Project_052_Risk-009 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | System acceptance not costed in line with Customer expectations | Person_651 | 2017-08-19 01:00 | 2018-06-22 | 0.1 | 0.39514 | 0.079029 | Accept | 0.1 | 0.39514 | 0.079029 | H3 | 3 | Stable | 0.6 | 94 | 136 | 151 | 131.5 | 0.6 | 94 | 136 | 151 | 131.5 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK004 | Project_075_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional Material required for investigations | Person_627 | 2017-07-21 | 2018-11-20 01:00 | 0.4 | 3.3748 | 1.3499 | Reduce | 0.1 | 3.3748 | 0.33748 | H3 | 3 | Stable | 0.8 | 90 | 123 | 160 | 123.6667 | 0.3 | 30 | 40 | 75 | 44.1667 | 0 | 75 | 1 | 2.25
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK024 | Project_075_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Failure to meet promised delivery dates | Person_627 | 2017-09-20 01:00 | 2019-01-21 01:00 | 0.5 | 2.5311 | 1.2656 | Reduce | 0.4 | 2.5311 | 1.0124 | H2 | 4 | Stable | 0.7 | 106 | 130 | 159 | 130.8333 | 0.1 | 18 | 53 | 75 | 50.8333 | 0 | 20 | 0 | 0
2018-08-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK044 | Project_053_RISK044 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Product Hardening | Person_719 | 2018-03-23 | 2019-01-19 23:00 | 0.3 | 7.9015 | 2.3705 | Avoid | 0.3 | 7.9015 | 2.3705 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK047 | Project_053_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Lab Availability | Person_252 | 2017-10-20 23:00 | 2020-01-21 23:00 | 0.5 | 2.2986 | 1.1493 | Accept | 0.2 | 2.2986 | 0.45973 | H3 | 3 | Improving | 0.7 | 95 | 132 | 143 | 127.6667 | 0.7 | 95 | 132 | 143 | 127.6667 | 0 | 60 | 1 | 1.8
2018-08-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK043 | Project_053_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Change in REACH/RoSH Legislation | Person_302 | 2017-11-19 23:00 | 2018-09-19 23:00 | 0.1 | 2.0249 | 0.20249 | Accept | 0.1 | 2.0249 | 0.20249 | H2 | 4 | Stable | 0.6 | 80 | 131 | 154 | 126.3333 | 0.6 | 80 | 131 | 154 | 126.3333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK015 | Project_053_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Equipment export licences | Person_252 | 2018-06-23 | 2019-07-22 | 0.3 | 2.586 | 0.77579 | Avoid | 0.1 | 2.586 | 0.2586 | H3 | 3 | Improving | [10 empty] | 0 | 66.6667 | 1 | 2
2018-08-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK006 | Project_053_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Additional UK integration of the System product | Person_719 | 2018-10-21 23:00 | 2019-01-20 23:00 | 0.2 | 6.3212 | 1.2642 | Avoid | 0.2 | 6.3212 | 1.2642 | H3 | 3 | Improving | [10 empty] | 0 | 0 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK008 | Project_075_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Failures at Acceptance stage | Person_449 | 2017-07-21 | 2019-04-22 | 0.3 | 0 | 0 | Accept | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 90 | 123 | 144 | 121 | 0.6 | 90 | 123 | 144 | 121 |  | 0 | 0
2018-08-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK005 | Project_053_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier Deiivery Schedule | Person_252 | 2018-01-20 23:00 | 2018-11-19 23:00 | 0.5 | 5.3299 | 2.665 | Reduce | 0.25 | 5.3299 | 1.3325 | H2 | 4 | Stable | 0.7 | 108 | 138 | 157 | 136.1667 | 0.2 | 18 | 42 | 75 | 43.5 | 0 | 50 | 0 | 0
2018-08-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK046 | Project_053_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Un-Planned Production Activities | Person_252 | 2019-07-22 | 2020-01-21 23:00 | 0.5 | 3.3378 | 3.3378 | Accept | 0.2 | 3.3378 | 3.3378 | H3 | 3 | Stable | 0.5 | 118 | 133 | 141 | 131.8333 | 0.5 | 118 | 133 | 141 | 131.8333 | 0 | 60 | 1 | 1.8
2018-08-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK010 | Project_053_RISK010 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Immaturity of the core product | Person_719 | 2018-08-21 23:00 | 2018-11-19 23:00 | 0.5 | 6.4649 | 3.2325 | Avoid | 0.7 | 6.4649 | 4.5254 | H1 | 5 | Worsening | [10 empty] | 0 | -40 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK007 | Project_075_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Range performance does not meet requirement. | Person_003 | 2017-07-21 | 2018-09-20 01:00 | 0.1 | 1.4007 | 0.49026 | Accept | 0.1 | 1.4007 | 0.49026 | H3 | 3 | Stable | 0.9 | 100 | 137 | 147 | 132.5 | 0.9 | 100 | 137 | 147 | 132.5 | 0 | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_082 | RISK007 | Project_082_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Task 30 - Pylon Procurement | Person_619 | 2017-04-13 | 2018-07-21 | 1 | 0 | 0 | Accept | 1 | 0 | 0 | H2 | 4 | Stable | 0.7 | 85 | 128 | 142 | 123.1667 | 0.7 | 85 | 128 | 142 | 123.1667 |  | 0 | 0
2018-08-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK007 | Project_053_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Resources Uavailable | Person_252 | 2017-11-19 23:00 | 2019-08-20 23:00 | 0.5 | 10.3438 | 5.1719 | Reduce | 0.2 | 7.9015 | 1.5803 | H3 | 3 | Stable | 0.5 | 86 | 132 | 157 | 128.5 | 0.3 | 22 | 49 | 79 | 49.5 | 23.6111 | 60 | 1 | 15.9666
2018-08-22 | ORG_003 | BA_006 | Portfolio_014 | Project_053 | RISK021 | Project_053_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Product documentation | Person_719 | 2018-08-21 23:00 | 2019-07-26 | 0.35 | 0.5596 | 0.05596 | Accept | 0.35 | 0.5596 | 0.05596 | H2 | 4 | Worsening | 0.8 | 109 | 124 | 146 | 125.1667 | 0.8 | 109 | 124 | 146 | 125.1667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK004 | Project_079_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.2 | 8.8685 | 1.7737 | Reduce | 0.1 | 8.8685 | 0.88685 | H3 | 3 | Stable | 0.9 | 107 | 138 | 150 | 134.8333 | 0.3 | 7 | 41 | 76 | 41.1667 | 0 | 50 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK026 | Project_079_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Clause on Joint Proposal | Person_261 | 2018-05-04 | 2019-05-23 | 0.3 | 30.653 | 9.1959 | -- | 0.3 | 30.653 | 9.1959 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK014 | Project_079_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 0.05 | 21.725 | 1.0862 | Reduce | 0.05 | 21.725 | 1.0862 | H3 | 3 | Stable | 0.6 | 83 | 131 | 150 | 126.1667 | 0.1 | 16 | 54 | 63 | 49.1667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK018 | Project_075_RISK018 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Crystal switch | Person_627 | 2017-03-21 01:00 | 2018-09-20 01:00 | 0.5 | 4.4768 | 2.2384 | Accept | 0.5 | 4.4768 | 2.2384 | H2 | 4 | Stable | 0.8 | 85 | 133 | 146 | 127.1667 | 0.8 | 85 | 133 | 146 | 127.1667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK005 | Project_079_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 0.6 | 3.7631 | 2.2578 | -- | 0.5 | 3.7631 | 1.8815 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK016 | Project_079_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Test Equipment | Person_104 | 2017-09-29 01:00 | 2019-05-23 | 0.8 | 1.9552 | 1.5642 | Avoid | 0.3 | 1.9552 | 0.58657 | H3 | 3 | Worsening | [10 empty] | 0 | 62.5 | 0 | 0
2018-08-22 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_077 | 2016-01-22 01:00 | 2018-11-17 01:00 | 0.15 | 0 | 0 | Reduce | 0.15 | 0 | 0 | H2 | 4 | Improving | 0.5 | 88 | 129 | 149 | 125.5 | 0.2 | 21 | 55 | 64 | 50.8333 |  | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK027 | Project_079_RISK027 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Trials | Person_002 | 2018-07-22 | 2018-08-21 | 0.5 | 0.88388 | 0.44194 | -- | 0.5 | 0.88388 | 0.44194 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK022 | Project_079_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Test Equipment | Person_104 | 2018-01-14 01:00 | 2019-08-20 | 0.15 | 7.321 | 1.0982 | Reduce | 0.15 | 7.321 | 1.0982 | H3 | 3 | Stable | 0.6 | 93 | 140 | 156 | 134.8333 | 0.3 | 23 | 51 | 67 | 49 | 0 | 0 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK002 | Project_079_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2022-05-22 | 0.15 | 26.7842 | 4.0176 | Avoid | 0.15 | 26.7842 | 4.0176 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK024 | Project_079_RISK024 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Procurement/Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 0.5 | 14.4992 | 7.2496 | Reduce | 0.5 | 14.4992 | 7.2496 | H1 | 5 | Stable | 0.9 | 96 | 135 | 154 | 131.6667 | 0.2 | 2 | 54 | 79 | 49.5 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK031 | Project_079_RISK031 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Line Closure Savings | Person_683 | 2020-12-21 01:00 | 2021-04-22 | 0.8 | 2.3927 | 1.9142 | -- | 0.8 | 2.3927 | 1.9142 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK030 | Project_079_RISK030 | Opportunitity | Project Contingency | Open | H1 | 5 | 11. Supply Chain | Production Build / Touch Labour | Person_683 | 2018-11-21 01:00 | 2020-04-22 | 0.8 | 46.4619 | 37.1695 | -- | 0.8 | 46.4619 | 37.1695 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-07-21 | 0.1 | 4.0291 | 0.40291 | Reduce | 0.1 | 4.0291 | 0.40291 | H2 | 4 | Improving | 0.7 | 106 | 123 | 149 | 124.5 | 0.3 | 18 | 45 | 79 | 46.1667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Retests | Person_523 | 2018-07-25 | 2018-10-19 01:00 | 0.35 | 1.2124 | 0.18186 | Accept | 0.2 | 1.2124 | 0.18186 | H2 | 4 | Stable | 0.8 | 85 | 133 | 148 | 127.5 | 0.8 | 85 | 133 | 148 | 127.5 | 0 | 42.8571 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK002 | Project_059_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SW Compatibility | Person_517 | 2017-11-20 01:00 | 2018-10-22 01:00 | 0.1 | 1.6166 | 0.32332 | Accept | 0.1 | 1.6166 | 0.32332 | H3 | 3 | Stable | 0.7 | 108 | 134 | 159 | 133.8333 | 0.7 | 108 | 134 | 159 | 133.8333 | 0 | 0 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK012 | Project_059_RISK012 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Failures at Acceptance stage - UNCERTAINTY | Person_278 | 2018-02-18 01:00 | 2019-08-04 | 0.3 | 2.0207 | 0.60622 | Reduce | 0.1 | 2.0207 | 0.20207 | H3 | 3 | Stable | 0.6 | 80 | 139 | 160 | 132.6667 | 0.3 | 38 | 56 | 77 | 56.5 | 0 | 66.6667 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK013 | Project_059_RISK013 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | ICD Errors - Uncertainty | Person_278 | 2017-10-21 01:00 | 2019-06-23 | 0.15 | 2.033 | 1.0165 | Accept | 0.15 | 1.4231 | 0.71156 | H3 | 3 | Stable | 0.9 | 114 | 124 | 147 | 126.1667 | 0.9 | 114 | 124 | 147 | 126.1667 | 30 | 0 | 0 | 18
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK001 | Project_059_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Critical Personnel | Person_162 | 2017-10-21 01:00 | 2019-08-04 | 0.2 | 2.0207 | 0.40414 | Accept | 0.2 | 2.0207 | 0.40414 | H3 | 3 | Stable | 0.5 | 84 | 137 | 141 | 128.8333 | 0.5 | 84 | 137 | 141 | 128.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | RISK015 | Project_028_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Engineering Change | Person_496 | 2018-07-22 | 2018-09-20 01:00 | 0.5 | 1.2198 | 0.60991 | Accept | 0.5 | 1.2198 | 0.30495 | H2 | 4 | Stable | 0.9 | 115 | 125 | 153 | 128 | 0.9 | 115 | 125 | 153 | 128 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK007 | Project_059_RISK007 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Code Re-Use | Person_517 | 2017-11-29 01:00 | 2019-02-20 01:00 | 0.1 | 1.2124 | 0.24249 | Accept | 0.1 | 1.2124 | 0.24249 | H3 | 3 | Stable | 0.5 | 96 | 121 | 141 | 120.1667 | 0.5 | 96 | 121 | 141 | 120.1667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Interface implementation | Person_496 | 2018-07-25 | 2018-10-19 01:00 | 0.5 | 3.6256 | 1.4502 | Accept | 0.25 | 3.6256 | 1.4502 | H2 | 4 | Stable | 0.8 | 108 | 135 | 154 | 133.6667 | 0.8 | 108 | 135 | 154 | 133.6667 | 0 | 50 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | FOC Acceptance | Person_499 | 2018-07-25 | 2018-10-19 01:00 | 0.35 | 4.2355 | 1.4824 | Reduce | 0.15 | 8.471 | 1.2706 | H3 | 3 | Stable | 0.5 | 120 | 133 | 147 | 133.1667 | 0.4 | 39 | 50 | 68 | 51.1667 | -99.9999 | 57.1429 | 1 | -58.2857
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK004 | Project_059_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Cyber Security Obligations | Person_592 | 2017-10-21 01:00 | 2019-08-04 | 0.4 | 0.80829 | 0.32332 | Reduce | 0.2 | 0.80829 | 0.16166 | H3 | 3 | Stable | 0.5 | 80 | 130 | 152 | 125.3333 | 0.4 | 23 | 45 | 63 | 44.3333 | 0 | 50 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK009 | Project_059_RISK009 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Safety risk mitigations - UNCERTAINTY | Person_592 | 2017-10-21 01:00 | 2019-08-20 | 0.1 | 1.2124 | 0.12124 | Accept | 0.1 | 1.2124 | 0.12124 | H3 | 3 | Stable | 0.6 | 84 | 135 | 148 | 128.6667 | 0.6 | 84 | 135 | 148 | 128.6667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Availability of the platforms for modification | Person_496 | 2014-01-21 01:00 | 2019-04-10 | 0.67 | 0.80829 | 0.16166 | Accept | 0.48 | 0.80829 | 0.16166 | H2 | 4 | Stable | 0.6 | 93 | 140 | 149 | 133.6667 | 0.6 | 93 | 140 | 149 | 133.6667 | 0 | 28.3582 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK003 | Project_059_RISK003 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Catalyst Requirements | Person_278 | 2017-10-21 01:00 | 2019-02-20 01:00 | 0.2 | 1.7836 | 0.53509 | Accept | 0.2 | 1.7836 | 0.53509 | H3 | 3 | Stable | 0.6 | 117 | 124 | 148 | 126.8333 | 0.6 | 117 | 124 | 148 | 126.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_059 | RISK014 | Project_059_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Integration Materials - UNCERTAINTY | Person_178 | 2017-10-21 01:00 | 2019-08-04 | 0.3 | 1.2798 | 0.95984 | Accept | 0.3 | 1.2798 | 0.95984 | H3 | 3 | Stable | 0.5 | 82 | 128 | 155 | 124.8333 | 0.5 | 82 | 128 | 155 | 124.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-023 | Project_018_Risk-023 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Head Repairs | Person_676 | 2017-07-21 | 2019-08-20 | 0.3 | 2.563 | 0.7689 | Reduce | 0.3 | 2.563 | 0.7689 | H3 | 3 | Stable | 0.7 | 82 | 129 | 142 | 123.3333 | 0.1 | 8 | 47 | 61 | 42.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-20 21:00 | 2017-08-19 21:00 | 0.1 | 53.0293 | 5.3029 | Reduce | 0.1 | 53.0293 | 5.3029 | H3 | 3 | Stable | 0.7 | 103 | 125 | 145 | 124.6667 | 0.1 | 11 | 41 | 74 | 41.5 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Test Equipment Failure | Person_676 | 2016-08-21 01:00 | 2017-08-21 01:00 | 0.5 | 37.5906 | 18.7953 | Reduce | 0.15 | 37.5906 | 5.6386 | H3 | 3 | Stable | 0.8 | 113 | 128 | 146 | 128.5 | 0.2 | 26 | 58 | 75 | 55.5 | 0 | 70 | 1 | 2.1
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-20 21:00 | 2017-08-19 21:00 | 0.1 | 7.7469 | 0.77469 | Reduce | 0.1 | 7.7469 | 0.77469 | H3 | 3 | Stable | 0.5 | 107 | 134 | 147 | 131.6667 | 0.2 | 8 | 53 | 60 | 46.6667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-184 | Project_032_Risk-184 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Manufacture of new Sub-systems | Person_629 | 2016-04-08 | 2018-02-18 21:00 | 0.33 | 5.5361 | 1.384 | Accept | 0.5 | 5.5361 | 1.384 | H1 | 5 | Stable | 0.8 | 120 | 129 | 148 | 130.6667 | 0.8 | 120 | 129 | 148 | 130.6667 | 0 | -51.5152 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | External SME Repairs | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.35 | 0.05293 | 0.015879 | Accept | 0.35 | 0.05293 | 0.015879 | H3 | 3 | Stable | 0.7 | 84 | 140 | 144 | 131.3333 | 0.7 | 84 | 140 | 144 | 131.3333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS019 | Project_025_RS019 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Product Component Failure | Person_619 | 2017-03-23 | 2019-08-07 | 0.7 | 0.82924 | 0.58047 | Reduce | 0.3 | 0.82924 | 0.24877 | H2 | 4 | Stable | 0.9 | 109 | 130 | 157 | 131 | 0.2 | 31 | 43 | 64 | 44.5 | 0 | 57.1429 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Repair Model | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.25 | 5.126 | 2.563 | Accept | 0.25 | 5.126 | 1.5378 | H3 | 3 | Stable | 0.9 | 113 | 137 | 143 | 134 | 0.9 | 113 | 137 | 143 | 134 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS020 | Project_025_RS020 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Plant Machinery failure | Person_619 | 2017-03-23 | 2019-08-07 | 0.3 | 12.815 | 2.563 | Accept | 0.3 | 12.815 | 2.563 | H2 | 4 | Stable | 0.6 | 92 | 129 | 147 | 125.8333 | 0.6 | 92 | 129 | 147 | 125.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Unsupported Software | Person_373 | 2012-08-21 01:00 | 2019-08-07 | 0.61 | 2.2054 | 1.3453 | Reduce | 0.61 | 2.2054 | 1.3453 | H1 | 5 | Stable | 0.5 | 110 | 137 | 149 | 134.5 | 0.1 | 12 | 45 | 64 | 42.6667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Loss of Key Resources | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.4 | 2.563 | 1.0252 | Reduce | 0.4 | 2.563 | 1.0252 | H3 | 3 | Stable | 0.8 | 99 | 136 | 156 | 133.1667 | 0.2 | 38 | 53 | 74 | 54 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-19 21:00 | 0.05 | 1.2744 | 0.63719 | Accept | 0.05 | 1.2744 | 0.63719 | H3 | 3 | Stable | 0.6 | 107 | 139 | 141 | 134 | 0.6 | 107 | 139 | 141 | 134 | 0 | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Increase in Repair costs | Person_676 | 2016-10-21 01:00 | 2019-08-20 | 0.5 | 2.5488 | 0.89207 | Accept | 0.3 | 2.5488 | 0.89207 | H3 | 3 | Stable | 0.8 | 91 | 125 | 142 | 122.1667 | 0.8 | 91 | 125 | 142 | 122.1667 | 0 | 40 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Volume of Repairs | Person_676 | 2016-08-21 01:00 | 2019-08-20 | 0.2 | 2.484 | 1.242 | Accept | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.7 | 101 | 125 | 148 | 124.8333 | 0.7 | 101 | 125 | 148 | 124.8333 | 100 | 0 | 0 | 60
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK024 | Project_069_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Training | Person_479 | 2018-03-16 01:00 | 2021-07-16 | 0.5 | 0.63719 | 0.50975 | Accept | 0.5 | 1.4974 | 1.1979 | H2 | 4 | Stable | 0.5 | 96 | 134 | 157 | 131.5 | 0.5 | 96 | 134 | 157 | 131.5 | -135 | 0 | 0 | -81
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK020 | Project_069_RISK020 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Directives may have a wider impact and requires additional work. | Person_530 | 2018-03-16 01:00 | 2021-07-16 | 0.35 | 2.2589 | 0.22589 | Accept | 0.35 | 2.2589 | 0.22589 | H2 | 4 | Stable | 0.5 | 103 | 126 | 143 | 125 | 0.5 | 103 | 126 | 143 | 125 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK007 | Project_069_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Without dedicated Datastore hardware, lots of re-work is required | Person_479 | 2018-05-24 | 2018-10-20 01:00 | 0.8 | 1.593 | 0.39825 | Accept | 0.8 | 1.593 | 0.39825 | H2 | 4 | Stable | 0.8 | 83 | 122 | 155 | 121 | 0.8 | 83 | 122 | 155 | 121 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK009 | Project_069_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sizings assume that at least 1 software engineer on the project has at least 2 years experience | Person_479 | 2018-03-16 01:00 | 2021-07-16 | 0.6 | 3.1541 | 1.2616 | Accept | 0.6 | 3.1541 | 1.2616 | H2 | 4 | Stable | 0.6 | 111 | 139 | 149 | 136 | 0.6 | 111 | 139 | 149 | 136 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-115 | Project_011_Risk-115 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | SMEs are unavailable to support project activites | Person_431 | 2016-07-21 | 2018-10-21 | 0.2 | 0 | 0 | Avoid | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 50 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-058 | Project_011_Risk-058 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme delays | Person_147 | 2013-11-20 | 2019-01-20 | 0.25 | 1.5013 | 0.37532 | Reduce | 0.4 | 1.5013 | 0.60051 | H1 | 5 | Stable | 0.6 | 89 | 124 | 153 | 123 | 0.1 | 12 | 50 | 70 | 47 | 0 | -60 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-131 | Project_011_Risk-131 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Support team have not covered all obligations in support contract | Person_147 | 2016-05-24 | 2018-10-21 | 0.2 | 0 | 0 | Avoid | 0.2 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-137 | Project_011_Risk-137 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Subsystem will not match Fidelity of Customer - does not accept | Person_147 | 2018-02-16 | 2018-09-20 | 0.4 | 0.11876 | 0.047505 | Avoid | 0.2 | 0.11876 | 0.023752 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK026 | Project_069_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional Representative HW | Person_257 | 2018-03-16 01:00 | 2021-07-16 | 0.25 | 0.34776 | 0.034776 | Accept | 0.25 | 0.34776 | 0.034776 | H2 | 4 | Stable | 0.7 | 87 | 139 | 144 | 131.1667 | 0.7 | 87 | 139 | 144 | 131.1667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Acceptance of the System | Person_147 | 2018-04-22 | 2019-01-20 | 0.2 | 0.62279 | 0.12456 | Avoid | 0.2 | 0.62279 | 0.12456 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 | 2018-11-20 | 0.1 | 1.8854 | 0.18854 | Reduce | 0.1 | 1.8854 | 0.18854 | H3 | 3 | Stable | 0.9 | 115 | 138 | 153 | 136.6667 | 0.3 | 25 | 56 | 75 | 54 | 0 | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2018-06-23 | 2019-01-20 | 0.4 | 1.4138 | 0.56551 | Reduce | 0.5 | 1.4138 | 0.70689 | H1 | 5 | Stable | 0.8 | 91 | 139 | 143 | 131.6667 | 0.3 | 38 | 41 | 75 | 46.1667 | 0 | -25 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-12-16 | 0.2 | 0.19206 | 0.038413 | -- | 0.2 | 0.19206 | 0.038413 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-08-22 | 2019-01-20 | 0.4 | 0.58017 | 0.23207 | Avoid | 0.4 | 0.58017 | 0.23207 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK025 | Project_069_RISK025 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Additional in-country presence (all WP's) | Person_257 | 2018-03-16 01:00 | 2021-07-16 | 0.5 | 0.49834 | 0.12459 | Accept | 0.5 | 0.49834 | 0.12459 | H2 | 4 | Stable | 0.8 | 80 | 132 | 159 | 127.8333 | 0.8 | 80 | 132 | 159 | 127.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-11-20 | 0.3 | 0.32389 | 0.097168 | Reduce | 0.3 | 0.32389 | 0.097168 | H2 | 4 | Stable | 0.8 | 81 | 121 | 148 | 118.8333 | 0.1 | 2 | 57 | 72 | 50.3333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Fidelity of Failures during SAT | Person_182 | 2018-06-23 | 2019-01-20 | 0.2 | 0.19206 | 0.038413 | -- | 0.2 | 0.19206 | 0.038413 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Required to produce a more comprehensive data pack than originally expected | Person_431 | 2017-05-24 | 2018-10-19 | 0.3 | 0.11933 | 0.035799 | -- | 0.3 | 0.022161 | 0.0066484 | H3 | 3 | Stable | [10 empty] | 81.4286 | 0 | 0 | 48.8571
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-117 | Project_011_Risk-117 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer Avaliability for testing/reviews | Person_147 | 2018-04-06 | 2018-10-21 | 0.35 | 0 | 0 | Avoid | 0.35 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-129 | Project_011_Risk-129 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Signature of Work Authorisation documents | Person_422 | 2017-05-24 | 2018-09-18 | 0.4 | 0.12643 | 0.050573 | -- | 0.4 | 0.12643 | 0.050573 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_069 | RISK022 | Project_069_RISK022 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Handbooks - Level of SW Change may increase (Not increase in scope). | Person_056 | 2018-03-16 01:00 | 2021-07-16 | 0.4 | 20.4694 | 10.2347 | Accept | 0.4 | 20.4694 | 10.2347 | H3 | 3 | Stable | 0.6 | 86 | 129 | 147 | 124.8333 | 0.6 | 86 | 129 | 147 | 124.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Unreliability of Hardware | Person_431 | 2016-06-23 | 2018-11-18 | 0.1 | 1.7748 | 0.4437 | Accept | 0.1 | 1.7748 | 0.4437 | H3 | 3 | Stable | 0.5 | 118 | 125 | 156 | 129 | 0.5 | 118 | 125 | 156 | 129 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier Selection Process | Person_379 | 2017-10-18 23:00 | 2019-04-23 | 0.4 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 110 | 130 | 141 | 128.5 | 0.4 | 33 | 50 | 78 | 51.8333 |  | 25 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Colour Representation in Video Image Distortion | Person_305 | 2017-09-21 23:00 | 2019-11-27 23:00 | 0.5 | 5.5323 | 2.7662 | Reduce | 0.1 | 5.5323 | 0.55323 | H3 | 3 | Stable | 0.9 | 114 | 122 | 143 | 124.1667 | 0.4 | 22 | 48 | 68 | 47 | 0 | 80 | 1 | 2.4
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_147 | 2016-04-21 | 2018-10-21 | 0.25 | 3.4651 | 1.0395 | Accept | 0.25 | 3.4651 | 1.0395 | H3 | 3 | Stable | 0.5 | 82 | 133 | 152 | 127.6667 | 0.5 | 82 | 133 | 152 | 127.6667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-20 23:00 | 2018-07-20 | 0.5 | 28.0275 | 14.0137 | Reduce | 0.1 | 28.0275 | 2.8027 | H3 | 3 | Stable | 0.9 | 83 | 135 | 147 | 128.3333 | 0.4 | 27 | 42 | 74 | 44.8333 | 0 | 80 | 1 | 2.4
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 4 | 5. Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-20 23:00 | 0.8 | 35.2369 | 28.1895 | Reduce | 0.3 | 18.4979 | 5.5494 | H2 | 4 | Stable | 0.7 | 120 | 130 | 148 | 131.3333 | 0.3 | 15 | 55 | 75 | 51.6667 | 47.5042 | 62.5 | 0 | 28.5025
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 4 | 9. Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-20 23:00 | 0.7 | 20.6835 | 14.4785 | Reduce | 0.3 | 20.6835 | 6.2051 | H2 | 4 | Stable | 0.5 | 96 | 124 | 142 | 122.3333 | 0.1 | 12 | 47 | 79 | 46.5 | 0 | 57.1429 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 4 | 8. System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 0.6 | 5.2585 | 3.1551 | Reduce | 0.15 | 5.2585 | 0.78877 | H2 | 4 | Stable | 0.8 | 102 | 130 | 159 | 130.1667 | 0.4 | 4 | 50 | 63 | 44.5 | 0 | 75 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-07-21 | 0.3 | 2.723 | 0.81691 | Reduce | 0.1 | 2.723 | 0.2723 | H3 | 3 | Improving | 0.5 | 115 | 121 | 149 | 124.6667 | 0.4 | 32 | 57 | 78 | 56.3333 | 0 | 66.6667 | 1 | 2
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.7 | 80 | 128 | 146 | 123 | 0.2 | 38 | 41 | 74 | 46 | 60.3671 | 58.3333 | 0 | 36.2202
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-07 23:00 | 2020-09-20 23:00 | 0.3 | 4.8444 | 1.4533 | Reduce | 0.2 | 4.8444 | 0.96888 | H3 | 3 | Stable | 0.6 | 120 | 135 | 148 | 134.6667 | 0.2 | 6 | 48 | 77 | 45.8333 | 0 | 33.3333 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | System Performance | Person_305 | 2016-09-07 23:00 | 2020-09-20 23:00 | 0.3 | 5.8725 | 1.7618 | Reduce | 0.1 | 5.8725 | 0.58725 | H2 | 4 | Stable | 0.8 | 89 | 134 | 148 | 128.8333 | 0.4 | 24 | 44 | 64 | 44 | 0 | 66.6667 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_572 | 2020-05-23 | 2023-10-25 23:00 | 0.2 | 7.4599 | 1.492 | Reduce | 0.05 | 7.4599 | 0.37299 | H2 | 4 | Stable | 0.5 | 93 | 135 | 149 | 130.3333 | 0.3 | 25 | 53 | 77 | 52.3333 | 0 | 75 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-28 23:00 | 0.6 | 5.7098 | 3.4259 | Reduce | 0.25 | 2.263 | 0.56574 | H2 | 4 | Stable | 0.5 | 86 | 128 | 146 | 124 | 0.2 | 34 | 55 | 60 | 52.3333 | 60.3671 | 58.3333 | 0 | 36.2202
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-19 23:00 | 0.4 | 2.8643 | 1.1457 | Reduce | 0.1 | 2.8643 | 0.28643 | H3 | 3 | Stable | 0.6 | 85 | 138 | 142 | 129.8333 | 0.4 | 36 | 56 | 75 | 55.8333 | 0.0015933 | 75 | 1 | 2.251
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power Supply - Motor Controller Interface | Person_179 | 2016-05-23 | 2018-09-18 23:00 | 0.5 | 25.3543 | 12.6771 | Reduce | 0.2 | 25.3543 | 5.0709 | H3 | 3 | Stable | 0.8 | 91 | 136 | 144 | 129.8333 | 0.3 | 32 | 57 | 64 | 54 | 0 | 60 | 1 | 1.8
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-07 23:00 | 2020-09-20 23:00 | 0.1 | 12.7232 | 1.2723 | Reduce | 0.1 | 12.7232 | 1.2723 | H3 | 3 | Stable | 0.9 | 104 | 129 | 148 | 128 | 0.3 | 8 | 49 | 67 | 45.1667 | 0 | 0 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | EMC non compliance | Person_047 | 2023-05-24 | 2023-11-30 23:00 | 0.7 | 3.935 | 2.7545 | Reduce | 0.5 | 3.935 | 1.9675 | H2 | 4 | Stable | 0.6 | 85 | 122 | 148 | 120.1667 | 0.4 | 21 | 52 | 63 | 48.6667 | 0 | 28.5714 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SubSystem System Design | Person_038 | 2017-09-30 23:00 | 2019-11-19 23:00 | 0.2 | 1.5213 | 0.30425 | Reduce | 0.1 | 1.5213 | 0.15213 | H3 | 3 | Stable | 0.8 | 97 | 128 | 144 | 125.5 | 0.1 | 10 | 59 | 62 | 51.3333 | 0 | 50 | 1 | 1.5
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-20 23:00 | 2023-12-21 23:00 | 0.4 | 30.1969 | 12.0788 | Reduce | 0.25 | 30.1969 | 7.5492 | H2 | 4 | Stable | 0.5 | 80 | 139 | 149 | 130.8333 | 0.4 | 16 | 54 | 69 | 50.1667 | 0 | 37.5 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | In-house development of sub-system estimate is low | Person_418 | 2016-03-23 | 2018-06-06 | 0.5 | 6.5118 | 3.2559 | Reduce | 0.2 | 1.506 | 0.30121 | H3 | 3 | Stable | 0.7 | 119 | 139 | 159 | 139 | 0.1 | 35 | 48 | 77 | 50.6667 | 76.8722 | 60 | 0 | 46.1233
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-10-19 23:00 | 0.4 | 1.0142 | 0.40567 | Reduce | 0.1 | 1.0142 | 0.10142 | H3 | 3 | Stable | 0.8 | 95 | 127 | 157 | 126.6667 | 0.2 | 2 | 50 | 73 | 45.8333 | 0 | 75 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | 9. Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 0.8 | 19.1678 | 15.3343 | Reduce | 0.2 | 2.8752 | 0.57503 | H3 | 3 | Stable | 0.5 | 95 | 133 | 152 | 129.8333 | 0.1 | 13 | 43 | 65 | 41.6667 | 85 | 75 | 0 | 51
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 0.25 | 0.63626 | 0.15906 | Reduce | 0.05 | 0.63626 | 0.031813 | H3 | 3 | Stable | 0.5 | 88 | 134 | 149 | 128.8333 | 0.3 | 16 | 47 | 77 | 46.8333 | 0 | 80 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Component Shock test failure | Person_020 | 2016-09-07 23:00 | 2019-11-14 23:00 | 0.4 | 0.8467 | 0.33868 | Reduce | 0.2 | 0.8467 | 0.16934 | H3 | 3 | Stable | 0.5 | 94 | 130 | 142 | 126 | 0.2 | 34 | 59 | 65 | 55.8333 | 0 | 50 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-05 23:00 | 2019-09-12 23:00 | 0.8 | 8.0322 | 6.4258 | Reduce | 0.5 | 4.006 | 2.003 | H2 | 4 | Stable | 0.7 | 116 | 131 | 147 | 131.1667 | 0.2 | 35 | 54 | 70 | 53.5 | 50.1263 | 37.5 | 0 | 30.0758
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-04-22 | 0.8 | 18.0459 | 14.4367 | Reduce | 0.2 | 3.0076 | 0.60153 | H3 | 3 | Stable | 0.9 | 93 | 126 | 148 | 124.1667 | 0.1 | 25 | 47 | 70 | 47.1667 | 83.3335 | 75 | 1 | 52.2501
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | 8. System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 0.4 | 5.1004 | 2.0402 | Reduce | 0.2 | 2.5506 | 0.51013 | H3 | 3 | Stable | 0.7 | 114 | 138 | 148 | 135.6667 | 0.4 | 12 | 45 | 60 | 42 | 49.9917 | 50 | 0 | 29.995
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK075 | Project_076_RISK075 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Delay in SW completion due to safety workload | Person_152 | 2018-07-05 | 2019-05-16 | 0.5 | 16.5844 | 8.2922 | Reduce | 0.25 | 16.5844 | 4.1461 | H2 | 4 | Stable | 0.6 | 118 | 131 | 141 | 130.5 | 0.3 | 19 | 55 | 67 | 51 | 0 | 50 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--16 | Project_021_Risk--16 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of weather | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.4 | 0 | 0 | H2 | 4 | Stable | 0.8 | 104 | 139 | 153 | 135.5 | 0.2 | 6 | 45 | 64 | 41.6667 |  | 20 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--15 | Project_021_Risk--15 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to lack of personnel resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 81 | 140 | 146 | 131.1667 | 0.3 | 8 | 43 | 64 | 40.6667 |  | 40 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--14 | Project_021_Risk--14 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Trials delay due to late Trials Approval | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.9 | 80 | 132 | 144 | 125.3333 | 0.4 | 33 | 44 | 72 | 46.8333 |  | 66.6667 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--12 | Project_021_Risk--12 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Safety Case Delayed Completion beyond target | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.4 | 6.6769 | 2.6707 | Reduce | 0.2 | 6.6769 | 1.3354 | H2 | 4 | Stable | 0.8 | 107 | 135 | 142 | 131.5 | 0.3 | 10 | 59 | 78 | 54 | 0 | 50 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 0.3 | 0 | 0 | Accept | 0.3 | 0 | 0 | H3 | 3 | Stable | 0.9 | 114 | 135 | 144 | 133 | 0.9 | 114 | 135 | 144 | 133 |  | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--10 | Project_021_Risk--10 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Development Closure | Person_652 | 2018-08-22 01:00 | 2019-03-23 | 0.7 | 10.4954 | 7.3468 | Reduce | 0.3 | 10.4954 | 3.1486 | H2 | 4 | Improving | 0.8 | 89 | 124 | 147 | 122 | 0.3 | 9 | 47 | 79 | 46 | 0 | 57.1429 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--32 | Project_021_Risk--32 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Lack of Customer resource to provide timely input to Acceptance and Closure activities | Person_615 | 2018-10-22 01:00 | 2019-04-23 | 0.8 | 0 | 0 | Reduce | 0.4 | 0 | 0 | H2 | 4 | Stable | 0.6 | 99 | 132 | 146 | 128.8333 | 0.1 | 6 | 42 | 64 | 39.6667 |  | 50 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--18 | Project_021_Risk--18 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Programme extends beyond 50% SRA date | Person_174 | 2018-01-21 01:00 | 2019-10-21 01:00 | 0.7 | 20.3948 | 14.2764 | Reduce | 0.5 | 10.1974 | 5.0987 | H1 | 5 | Stable | 0.5 | 83 | 123 | 144 | 119.8333 | 0.1 | 11 | 41 | 78 | 42.1667 | 50 | 28.5714 | 0 | 30
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--28 | Project_021_Risk--28 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort required to agree protocl for Client Server | Person_615 | 2018-03-23 | 2019-02-20 01:00 | 0.8 | 1.1522 | 0.92174 | Reduce | 0.4 | 1.1522 | 0.46087 | H2 | 4 | Stable | 0.9 | 81 | 138 | 146 | 129.8333 | 0.4 | 14 | 49 | 63 | 45.5 | 0 | 50 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--05 | Project_021_Risk--05 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Qualification delays | Person_207 | 2018-02-20 01:00 | 2018-10-05 01:00 | 0.4 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.9 | 83 | 122 | 150 | 120.1667 | 0.2 | 21 | 43 | 63 | 42.6667 |  | 50 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK073 | Project_076_RISK073 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Competence Centre Level of effort | Person_152 | 2018-05-23 | 2018-12-22 01:00 | 0.7 | 2.1388 | 0.21388 | Accept | 0.7 | 2.1388 | 0.21388 | H1 | 5 | Stable | 0.7 | 87 | 138 | 154 | 132.1667 | 0.7 | 87 | 138 | 154 | 132.1667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--04 | Project_021_Risk--04 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Final Qual test report delayed due to insufficient supply chain resource | Person_207 | 2018-09-20 01:00 | 2018-10-21 01:00 | 0.2 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 81 | 137 | 154 | 130.5 | 0.3 | 5 | 54 | 78 | 49.8333 |  | 50 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--03 | Project_021_Risk--03 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 0.6 | 2.2624 | 1.3574 | Reduce | 0.4 | 2.2624 | 0.90497 | H2 | 4 | Stable | 0.8 | 95 | 122 | 151 | 122.3333 | 0.2 | 25 | 42 | 69 | 43.6667 | 0 | 33.3333 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--25 | Project_021_Risk--25 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of supporting resource | Person_080 | 2018-06-22 | 2019-02-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.9 | 107 | 135 | 151 | 133 | 0.2 | 29 | 42 | 62 | 43.1667 |  | 60 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--02 | Project_021_Risk--02 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Impact from Regulations | Person_061 | 2018-02-20 01:00 | 2019-03-23 | 0.3 | 2.6487 | 0.7946 | Reduce | 0.1 | 0.52974 | 0.052974 | H2 | 4 | Stable | 0.5 | 94 | 130 | 144 | 126.3333 | 0.1 | 6 | 47 | 79 | 45.5 | 80 | 66.6667 | 0 | 48
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--24 | Project_021_Risk--24 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delay due to lack of equipment | Person_080 | 2018-06-22 | 2019-02-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.6 | 89 | 121 | 152 | 120.8333 | 0.1 | 7 | 46 | 68 | 43.1667 |  | 60 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--21 | Project_021_Risk--21 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.9 | 107 | 134 | 153 | 132.6667 | 0.3 | 37 | 56 | 75 | 56 |  | 40 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--09 | Project_021_Risk--09 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_470 | 2018-02-20 01:00 | 2019-04-22 | 0.6 | 0 | 0 | Reduce | 0.4 | 0 | 0 | H2 | 4 | Stable | 0.5 | 82 | 127 | 141 | 121.8333 | 0.4 | 20 | 59 | 75 | 55.1667 |  | 33.3333 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--08 | Project_021_Risk--08 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-02-20 01:00 | 2018-11-20 01:00 | 0.7 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.9 | 118 | 132 | 149 | 132.5 | 0.3 | 9 | 51 | 64 | 46.1667 |  | 28.5714 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--07 | Project_021_Risk--07 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Rejected concessions | Person_615 | 2018-08-22 01:00 | 2019-03-23 | 0.6 | 17.2826 | 10.3696 | Reduce | 0.3 | 17.2826 | 5.1848 | H2 | 4 | Improving | 0.9 | 95 | 134 | 141 | 128.6667 | 0.2 | 27 | 46 | 60 | 45.1667 | 0 | 50 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--17 | Project_021_Risk--17 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Trials delays due to technical performacne | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.6 | 100 | 139 | 143 | 133.1667 | 0.1 | 11 | 57 | 67 | 51 |  | 33.3333 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--39 | Project_021_Risk--39 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Delay to completion of product upgrade | Person_080 | 2018-02-20 01:00 | 2019-02-20 01:00 | 0.5 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.5 | 104 | 126 | 159 | 127.8333 | 0.4 | 1 | 52 | 74 | 47.1667 |  | 80 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--46 | Project_021_Risk--46 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-08-08 | 2018-11-05 01:00 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.9 | 81 | 133 | 157 | 128.3333 | 0.2 | 34 | 48 | 65 | 48.5 |  | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--45 | Project_021_Risk--45 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Additional work on deliverables may be required from Customer | Person_470 | 2018-05-23 | 2018-11-20 01:00 | 0.5 | 6.0147 | 3.0074 | Reduce | 0.3 | 6.0147 | 1.8044 | H2 | 4 | Stable | 0.5 | 93 | 123 | 158 | 123.8333 | 0.3 | 32 | 53 | 63 | 51.1667 | 0 | 40 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R008 | Project_044_Risk-R008 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Engineering Skills | Person_505 | 2017-10-21 01:00 | 2018-10-22 01:00 | 0.2 | 1.5695 | 0.3139 | Reduce | 0.1 | 1.2073 | 0.12073 | H3 | 3 | Stable | 0.5 | 97 | 139 | 141 | 132.3333 | 0.3 | 24 | 49 | 73 | 48.8333 | 23.0769 | 50 | 1 | 15.3461
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R018 | Project_044_Risk-R018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | EMC (susceptibility) | Person_763 | 2016-03-23 | 2019-11-20 01:00 | 0.5 | 5.795 | 2.8975 | Reduce | 0.1 | 5.795 | 0.5795 | H3 | 3 | Stable | 0.5 | 117 | 139 | 151 | 137.3333 | 0.1 | 19 | 46 | 68 | 45.1667 | 0 | 80 | 1 | 2.4
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R001 | Project_044_Risk-R001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | subsystem1 development | Person_358 | 2017-12-22 01:00 | 2019-11-20 01:00 | 0.2 | 17.3851 | 3.477 | Reduce | 0.15 | 17.3851 | 2.6078 | H2 | 4 | Stable | 0.6 | 113 | 135 | 157 | 135 | 0.1 | 12 | 43 | 60 | 40.6667 | 0 | 25 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--35 | Project_021_Risk--35 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Delay to sub-system and other Components - dependencies due to supply chain dependencies | Person_615 | 2018-01-21 01:00 | 2019-03-23 | 0.4 | 6.0365 | 0.60365 | Accept | 0.2 | 6.0365 | 0.60365 | H3 | 3 | Stable | 0.6 | 114 | 126 | 157 | 129.1667 | 0.6 | 114 | 126 | 157 | 129.1667 | 0 | 50 | 1 | 1.5
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R010 | Project_044_Risk-R010 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Line of sight | Person_044 | 2017-11-20 01:00 | 2019-06-23 | 0.15 | 1.0503 | 0.15755 | Reduce | 0.05 | 1.0503 | 0.052517 | H3 | 3 | Stable | 0.9 | 112 | 140 | 154 | 137.6667 | 0.1 | 7 | 41 | 68 | 39.8333 | 0 | 66.6667 | 1 | 2
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R003 | Project_044_Risk-R003 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Mono vs stereo Component | Person_358 | 2018-01-19 01:00 | 2018-10-22 01:00 | 0.4 | 17.3851 | 6.954 | Reduce | 0.2 | 17.3851 | 3.477 | H3 | 3 | Stable | 0.7 | 93 | 123 | 159 | 124 | 0.3 | 28 | 56 | 62 | 52.3333 | 0 | 50 | 1 | 1.5
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R025 | Project_044_Risk-R025 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Obsolescence | Person_044 | 2017-11-20 01:00 | 2019-02-10 01:00 | 0.2 | 1.1831 | 0.23663 | Reduce | 0.05 | 1.1831 | 0.059157 | H3 | 3 | Stable | 0.7 | 81 | 128 | 142 | 122.5 | 0.3 | 30 | 42 | 63 | 43.5 | 0 | 75 | 1 | 2.25
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--34 | Project_021_Risk--34 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Delay due to poor weather | Person_207 | 2018-03-23 | 2018-10-21 01:00 | 0.5 | 0 | 0 | Accept | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.5 | 93 | 137 | 160 | 133.5 | 0.5 | 93 | 137 | 160 | 133.5 |  | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--27 | Project_021_Risk--27 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | PR rectification | Person_207 | 2018-02-20 01:00 | 2018-11-05 01:00 | 0.1 | 4.8292 | 0.96584 | Accept | 0.1 | 4.8292 | 0.72438 | H2 | 4 | Stable | 0.7 | 116 | 133 | 147 | 132.5 | 0.7 | 116 | 133 | 147 | 132.5 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R022 | Project_044_Risk-R022 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Shock Requirement | Person_763 | 2018-11-20 01:00 | 2020-01-20 01:00 | 0.1 | 2.318 | 0.1159 | Accept | 0.1 | 2.318 | 0.1159 | H3 | 3 | Stable | 0.7 | 118 | 132 | 151 | 132.8333 | 0.7 | 118 | 132 | 151 | 132.8333 | 0 | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK003 | Project_044_RISK003 | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Unavailability / failure of Range | Person_553 | 2018-08-14 | 2019-10-21 01:00 | 0.7 | 21.7314 | 15.212 | Reduce | 0.2 | 2.5957 | 0.51914 | H3 | 3 | Worsening | 0.7 | 114 | 133 | 160 | 134.3333 | 0.3 | 34 | 53 | 76 | 53.6667 | 88.0556 | 71.4286 | 0 | 52.8333
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK001 | Project_044_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Non-compliance with regs | Person_044 | 2018-07-14 | 2019-02-10 01:00 | 0.5 | 2.0403 | 1.0202 | Reduce | 0.2 | 1.992 | 0.39841 | H3 | 3 | Stable | 0.5 | 87 | 134 | 160 | 130.5 | 0.4 | 23 | 56 | 69 | 52.6667 | 2.367 | 60 | 1 | 3.2202
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK004 | Project_094_RISK004 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Acceptance trial success criteria not achieved | Person_419 | 2019-11-21 | 2020-02-21 | 0.2 | 19.9676 | 3.9935 | Reduce | 0.2 | 19.9676 | 3.9935 | H3 | 3 | Stable | 0.8 | 93 | 137 | 145 | 131 | 0.3 | 29 | 48 | 71 | 48.6667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK003 | Project_094_RISK003 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Issues experienced during system integration | Person_198 | 2019-08-22 | 2020-11-20 | 0.3 | 15.974 | 4.7922 | Reduce | 0.3 | 15.974 | 4.7922 | H3 | 3 | Stable | 0.8 | 113 | 122 | 149 | 125 | 0.2 | 21 | 49 | 63 | 46.6667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK006 | Project_094_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Additional freight costs | Person_198 | 2020-08-21 | 2022-05-22 | 0.3 | 11.9805 | 3.5942 | Reduce | 0.3 | 11.9805 | 3.5942 | H3 | 3 | Stable | 0.6 | 106 | 127 | 153 | 127.8333 | 0.4 | 10 | 40 | 62 | 38.6667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK005 | Project_094_RISK005 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Project extension due to schedule slippage | Person_198 | 2021-04-22 | 2022-05-22 | 0.2 | 11.9805 | 2.3961 | Reduce | 0.2 | 11.9805 | 2.3961 | H3 | 3 | Stable | 0.6 | 84 | 121 | 147 | 119.1667 | 0.3 | 5 | 53 | 65 | 47 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK011 | Project_094_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unplanned redesign activity | Person_198 | 2018-08-22 | 2020-05-22 | 0.4 | 21.4052 | 8.5621 | Reduce | 0.4 | 21.4052 | 8.5621 | H2 | 4 | Stable | 0.9 | 99 | 133 | 143 | 129 | 0.1 | 14 | 51 | 73 | 48.5 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK010 | Project_094_RISK010 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Increased cost of manufacture | Person_193 | 2019-04-23 | 2020-05-22 | 0.4 | 19.1689 | 7.6675 | Reduce | 0.4 | 19.1689 | 7.6675 | H3 | 3 | Stable | 0.9 | 112 | 133 | 158 | 133.6667 | 0.3 | 4 | 46 | 67 | 42.5 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK002 | Project_094_RISK002 | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Facilities or equipment for training not available | Person_198 | 2020-12-21 | 2021-05-22 | 0.2 | 15.974 | 3.1948 | Reduce | 0.2 | 15.974 | 3.1948 | H3 | 3 | Stable | 0.7 | 108 | 123 | 159 | 126.5 | 0.1 | 18 | 47 | 66 | 45.3333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK013 | Project_094_RISK013 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Other risks | Person_198 | 2018-08-22 | 2022-05-22 | 0.1 | 49.1298 | 4.913 | Reduce | 0.1 | 49.1298 | 4.913 | H3 | 3 | Stable | 0.7 | 117 | 130 | 142 | 129.8333 | 0.3 | 21 | 51 | 61 | 47.6667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK001 | Project_094_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Immature Prime not qualified to deliver SoW | Person_198 | 2018-08-22 | 2021-08-21 | 0.4 | 27.9546 | 11.1818 | Reduce | 0.4 | 27.9546 | 11.1818 | H2 | 4 | Stable | 0.9 | 104 | 131 | 147 | 129.1667 | 0.1 | 10 | 52 | 61 | 46.5 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK012 | Project_094_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Insufficient resources to meet the demand of the programme | Person_198 | 2018-08-22 | 2021-07-20 | 0.35 | 4.6804 | 1.6381 | Reduce | 0.35 | 4.6804 | 1.6381 | H2 | 4 | Stable | 0.9 | 101 | 136 | 157 | 133.6667 | 0.4 | 17 | 41 | 65 | 41 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK008 | Project_094_RISK008 | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Increased warranty costs | Person_260 | 2020-11-20 | 2023-05-23 | 0.1 | 11.9805 | 1.1981 | Avoid | 0.1 | 11.9805 | 1.1981 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK007 | Project_094_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Additional training requested | Person_620 | 2020-12-21 | 2021-07-20 | 0.3 | 5.9903 | 1.7971 | Avoid | 0.3 | 5.9903 | 1.7971 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK009 | Project_094_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Financial instability/loss of quality/abilities of suppliers for batch 2 | Person_281 | 2020-08-21 | 2021-05-22 | 0.3 | 28.1143 | 8.4343 | Reduce | 0.3 | 28.1143 | 8.4343 | H2 | 4 | Stable | 0.9 | 94 | 123 | 157 | 123.8333 | 0.1 | 39 | 49 | 75 | 51.6667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | OPP002 | Project_094_OPP002 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | Integration schedule improved | Person_198 | 2018-08-22 | 2021-03-22 | 0.3 | 7.987 | 2.3961 | -- | 0.3 | 7.987 | 2.3961 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | OPP001 | Project_094_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 11. Supply chain | UPC savings | Person_198 | 2018-08-22 | 2019-09-20 | 0.2 | 19.9676 | 3.9935 | -- | 0.2 | 19.9676 | 3.9935 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK003 | Project_060_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Misalignment of Critical Resource | Person_312 | 2017-12-19 01:00 | 2018-11-06 01:00 | 0.7 | 1.0769 | 0.75381 | Reduce | 0.5 | 1.0769 | 0.53844 | H2 | 4 | Improving | 0.9 | 90 | 121 | 149 | 120.5 | 0.2 | 9 | 56 | 69 | 50.3333 | 0 | 28.5714 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK004 | Project_060_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Cross-functional Estimates | Person_729 | 2017-11-19 01:00 | 2018-11-06 01:00 | 0.7 | 2.8845 | 2.0191 | Reduce | 0.5 | 1.4422 | 0.72112 | H2 | 4 | Improving | 0.5 | 80 | 131 | 148 | 125.3333 | 0.1 | 29 | 48 | 69 | 48.3333 | 50 | 28.5714 | 0 | 30
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK001 | Project_060_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Procurement Prices | Person_033 | 2017-11-02 01:00 | 2018-11-20 01:00 | 0.7 | 5.769 | 4.0383 | Reduce | 0.3 | 5.769 | 1.7307 | H2 | 4 | Stable | 0.9 | 97 | 127 | 144 | 124.8333 | 0.3 | 7 | 52 | 75 | 48.3333 | 0 | 57.1429 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R002 | Project_044_Risk-R002 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | Parts changing post ordering | Person_310 | 2018-01-20 01:00 | 2019-05-22 | 0.9 | 0.5476 | 0.16428 | Accept | 0.9 | 0.5476 | 0.16428 | H1 | 5 | Stable | 0.7 | 107 | 133 | 159 | 133 | 0.7 | 107 | 133 | 159 | 133 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R024 | Project_044_Risk-R024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Receiver System Performance | Person_763 | 2017-11-20 01:00 | 2019-11-21 01:00 | 0.2 | 8.3115 | 4.1558 | Accept | 0.15 | 8.3115 | 1.6623 | H3 | 3 | Stable | 0.7 | 89 | 131 | 155 | 128 | 0.7 | 89 | 131 | 155 | 128 | 0 | 25 | 1 | 0.75
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R091 | Project_044_Risk-R091 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Receive System Performance | Person_044 | 2017-11-20 01:00 | 2018-11-21 01:00 | 0.05 | 0.060012 | 0.0030006 | Accept | 0.05 | 0.060012 | 0.0030006 | H3 | 3 | Stable | 0.8 | 100 | 125 | 156 | 126 | 0.8 | 100 | 125 | 156 | 126 | 0 | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK036 | Project_042_RISK036 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 2 | Person_455 | 2019-05-24 | 2020-05-22 | 0.25 | 1.8788 | 0.37576 | Accept | 0.2 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.9 | 80 | 136 | 160 | 130.6667 | 0.9 | 80 | 136 | 160 | 130.6667 | 20 | 20 | 0 | 12
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK039 | Project_042_RISK039 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Quality Issues 16th August to 15th August | Person_540 | 2020-01-06 01:00 | 2021-01-04 01:00 | 0.1 | 1.0334 | 0.20667 | Accept | 0.08 | 0.80789 | 0.12118 | H2 | 4 | Stable | 0.8 | 86 | 131 | 156 | 127.6667 | 0.8 | 86 | 131 | 156 | 127.6667 | 21.8182 | 20 | 0 | 13.0909
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK033 | Project_042_RISK033 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st April to 30 June | Person_455 | 2019-08-22 01:00 | 2019-11-20 01:00 | 0.2 | 1.8788 | 0.18788 | Accept | 0.15 | 1.8225 | 0.12757 | H2 | 4 | Stable | 0.8 | 108 | 139 | 142 | 134.3333 | 0.8 | 108 | 139 | 142 | 134.3333 | 3 | 25 | 0 | 1.8
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK035 | Project_042_RISK035 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st October to 31st December | Person_455 | 2021-02-20 01:00 | 2021-05-22 | 0.2 | 1.8788 | 0.18788 | Accept | 0.15 | 1.5031 | 0.12024 | H2 | 4 | Stable | 0.5 | 108 | 121 | 148 | 123.3333 | 0.5 | 108 | 121 | 148 | 123.3333 | 20 | 25 | 0 | 12
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK034 | Project_042_RISK034 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | T&S (Travel and Subsistence) 1st July to 30 September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 0.2 | 1.8788 | 0.18788 | Accept | 0.15 | 1.5031 | 0.12024 | H2 | 4 | Stable | 0.6 | 119 | 127 | 146 | 128.8333 | 0.6 | 119 | 127 | 146 | 128.8333 | 20 | 25 | 0 | 12
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK040 | Project_042_RISK040 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st May to 30 Oct | Person_455 | 2019-09-21 01:00 | 2020-03-21 | 0.1 | 0.79775 | 0.039887 | Accept | 0.07 | 0.79775 | 0.039887 | H2 | 4 | Stable | 0.6 | 114 | 137 | 154 | 136 | 0.6 | 114 | 137 | 154 | 136 | 0 | 30 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK042 | Project_042_RISK042 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st February to 14th July | Person_455 | 2020-06-23 | 2020-12-03 01:00 | 0.1 | 10.3335 | 1.0334 | Accept | 0.08 | 10.3335 | 1.0334 | H2 | 4 | Stable | 0.9 | 106 | 131 | 150 | 130 | 0.9 | 106 | 131 | 150 | 130 | 0 | 20 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK041 | Project_042_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st Jan | Person_455 | 2020-03-23 | 2020-06-22 | 0.1 | 11.2729 | 2.2546 | Accept | 0.08 | 11.2729 | 2.2546 | H2 | 4 | Stable | 0.5 | 99 | 133 | 146 | 129.5 | 0.5 | 99 | 133 | 146 | 129.5 | 0 | 20 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Local customer Engineers in country | Person_455 | 2018-12-20 01:00 | 2021-05-22 | 0.05 | 3.7576 | 0.18788 | Accept | 0.05 | 3.7576 | 0.56365 | H2 | 4 | Stable | 0.9 | 88 | 124 | 142 | 121 | 0.9 | 88 | 124 | 142 | 121 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK026 | Project_042_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st Jan to 31st March | Person_455 | 2020-05-23 | 2020-08-20 01:00 | 0.25 | 1.8788 | 0.46971 | Accept | 0.15 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.8 | 110 | 137 | 149 | 134.5 | 0.8 | 110 | 137 | 149 | 134.5 | 20 | 40 | 0 | 12
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK025 | Project_042_RISK025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to 31 Dec | Person_455 | 2020-09-20 01:00 | 2021-05-22 | 0.2 | 4.6971 | 0.93941 | Accept | 0.15 | 3.7576 | 0.56365 | H2 | 4 | Stable | 0.6 | 102 | 123 | 159 | 125.5 | 0.6 | 102 | 123 | 159 | 125.5 | 20 | 25 | 0 | 12
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK028 | Project_042_RISK028 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st July to 30th September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 0.25 | 1.8788 | 0.46971 | Accept | 0.15 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.8 | 107 | 124 | 157 | 126.6667 | 0.8 | 107 | 124 | 157 | 126.6667 | 20 | 40 | 0 | 12
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK027 | Project_042_RISK027 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares1st April to 30th June | Person_455 | 2020-08-21 01:00 | 2020-09-19 01:00 | 0.25 | 1.8788 | 0.46971 | Accept | 0.15 | 1.5031 | 0.22546 | H2 | 4 | Stable | 0.9 | 86 | 127 | 149 | 123.8333 | 0.9 | 86 | 127 | 149 | 123.8333 | 20 | 40 | 0 | 12
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK037 | Project_042_RISK037 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Repairs 1st Jan to 31 December Year 1 | Person_455 | 2020-05-23 | 2021-05-22 | 0.14 | 2.2828 | 0.31959 | Accept | 0.14 | 2.2828 | 0.31959 | H2 | 4 | Stable | 0.9 | 110 | 126 | 157 | 128.5 | 0.9 | 110 | 126 | 157 | 128.5 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK047 | Project_042_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables | Person_455 | 2020-11-20 01:00 | 2021-05-22 | 0.2 | 0.56365 | 0.11273 | Accept | 0.1 | 0.28182 | 0.028182 | H2 | 4 | Stable | 0.6 | 110 | 135 | 153 | 133.8333 | 0.6 | 110 | 135 | 153 | 133.8333 | 50 | 50 | 0 | 30
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK022 | Project_042_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2017-09-20 01:00 | 2018-09-20 01:00 | 0.2 | 4.6971 | 0.93941 | Accept | 0.18 | 3.7576 | 0.67638 | H2 | 4 | Stable | 0.9 | 111 | 123 | 160 | 127.1667 | 0.9 | 111 | 123 | 160 | 127.1667 | 20 | 10 | 0 | 12
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK043 | Project_042_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | STTE 1st November to 31st December | Person_455 | 2021-03-23 | 2021-05-22 | 0.1 | 1.8788 | 0.18788 | Accept | 0.08 | 1.5031 | 0.12024 | H3 | 3 | Stable | 0.6 | 92 | 125 | 157 | 124.8333 | 0.6 | 92 | 125 | 157 | 124.8333 | 20 | 20 | 1 | 12.6
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK024 | Project_042_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2019-09-21 01:00 | 2020-09-19 01:00 | 0.33 | 9.3941 | 3.1001 | Reduce | 0.15 | 7.5153 | 1.1273 | H2 | 4 | Stable | 0.6 | 94 | 122 | 147 | 121.5 | 0.1 | 18 | 51 | 76 | 49.6667 | 20 | 54.5455 | 0 | 12
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK046 | Project_042_RISK046 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Consumables - June | Person_455 | 2018-11-21 01:00 | 2020-11-19 01:00 | 0.2 | 0.56365 | 0.11273 | Accept | 0.1 | 0.28182 | 0.028182 | H2 | 4 | Stable | 0.7 | 117 | 138 | 159 | 138 | 0.7 | 117 | 138 | 159 | 138 | 50 | 50 | 0 | 30
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK023 | Project_042_RISK023 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence May to April | Person_455 | 2018-09-21 01:00 | 2019-09-20 01:00 | 0.2 | 4.6971 | 0.93941 | Accept | 0.1 | 3.7576 | 0.37576 | H2 | 4 | Stable | 0.9 | 95 | 135 | 146 | 130.1667 | 0.9 | 95 | 135 | 146 | 130.1667 | 20 | 50 | 0 | 12
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK029 | Project_042_RISK029 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Spares 1st October to 31st December | Person_455 | 2020-11-20 01:00 | 2021-05-22 | 0.25 | 1.8788 | 0.46971 | Accept | 0.1 | 1.1273 | 0.11273 | H2 | 4 | Stable | 0.9 | 111 | 127 | 154 | 128.8333 | 0.9 | 111 | 127 | 154 | 128.8333 | 40 | 60 | 0 | 24
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_061 | RISK003 | Project_061_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Test equipment reliability | Person_104 | 2017-05-23 | 2020-11-18 19:00 | 0.4 | 0.11013 | 0.044051 | Reduce | 0.3 | 0.11013 | 0.033038 | H2 | 4 | Stable | 0.9 | 90 | 124 | 148 | 122.3333 | 0.1 | 32 | 52 | 69 | 51.5 | 0 | 25 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 0.5 | 7.3848 | 3.6924 | Accept | 0.5 | 7.3848 | 3.6924 | H2 | 4 | Stable | 0.9 | 120 | 137 | 151 | 136.5 | 0.9 | 120 | 137 | 151 | 136.5 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1010 | Project_091_RISK1010 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Supplier may not be approved for Dip Brazed Manufacture | Person_675 | 2018-09-27 01:00 | 2018-12-21 01:00 | 0.05 | 0.59721 | 0.02986 | Accept | 0.05 | 0.59721 | 0.02986 | H2 | 4 | Stable | 0.5 | 89 | 126 | 144 | 122.8333 | 0.5 | 89 | 126 | 144 | 122.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1011 | Project_091_RISK1011 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier stud nut rework takes too long | Person_261 | 2018-09-27 01:00 | 2018-10-28 01:00 | 0.7 | 0 | 0 | Reduce | 0.4 | 0 | 0 | H2 | 4 | Stable | 0.8 | 103 | 124 | 150 | 124.8333 | 0.3 | 1 | 58 | 66 | 49.8333 |  | 42.8571 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK004 | Project_081_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Greater number of failures/ investigations | Person_260 | 2017-09-27 01:00 | 2021-09-27 01:00 | 0.6 | 2.685 | 1.611 | Reduce | 0.6 | 2.685 | 1.611 | H3 | 3 | Worsening | 0.9 | 90 | 135 | 150 | 130 | 0.3 | 21 | 58 | 71 | 54 | 0 | 0 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK003 | Project_081_RISK003 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Export control issues taking longer to resolve | Person_260 | 2017-09-27 01:00 | 2021-09-27 01:00 | 0.2 | 1.5256 | 0.30511 | Reduce | 0.2 | 1.5256 | 0.30511 | H3 | 3 | Stable | 0.7 | 102 | 126 | 159 | 127.5 | 0.4 | 32 | 47 | 63 | 47.1667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK006 | Project_081_RISK006 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Large volume of repairs loaded to clear backlog | Person_260 | 2017-09-27 01:00 | 2021-09-27 01:00 | 0.25 | 3.1854 | 0.79634 | Reduce | 0.25 | 3.1854 | 0.79634 | H3 | 3 | Worsening | 0.9 | 111 | 129 | 146 | 128.8333 | 0.4 | 37 | 53 | 74 | 53.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK005 | Project_081_RISK005 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Marching army Customer costs for duration of contract | Person_260 | 2021-05-23 | 2021-09-27 01:00 | 0.2 | 1.6598 | 0.33196 | Reduce | 0.2 | 1.6598 | 0.33196 | H3 | 3 | Stable | 0.9 | 109 | 122 | 151 | 124.6667 | 0.4 | 4 | 46 | 65 | 42.1667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK021 | Project_081_RISK021 | Threat | Financial Contingency | Open | H3 | 3 | 7. Finance | Increase of bank fees and other direct costs | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.15 | 2.27 | 0.3405 | Avoid | 0.15 | 2.27 | 0.3405 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK024 | Project_081_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer- Training | Person_115 | 2017-09-27 01:00 | 2021-11-27 01:00 | 0.6 | 1.3425 | 0.80549 | Reduce | 0.6 | 1.3425 | 0.80549 | H3 | 3 | Stable | 0.9 | 97 | 140 | 154 | 135.1667 | 0.4 | 6 | 51 | 64 | 45.6667 | 0 | 0 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK002 | Project_081_RISK002 | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Supplier costs to be covered by us | Person_260 | 2017-09-27 01:00 | 2021-09-20 01:00 | 0.2 | 2.0381 | 0.40763 | Reduce | 0.2 | 2.0381 | 0.40763 | H3 | 3 | Stable | 0.9 | 85 | 134 | 151 | 128.6667 | 0.3 | 23 | 40 | 76 | 43.1667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK023 | Project_081_RISK023 | Threat | Project Contingency | Open | H2 | 4 | 7. Finance | Risk of funding requirement | Person_115 | 2017-09-27 01:00 | 2021-09-27 01:00 | 0.6 | 1.7696 | 1.0618 | Reduce | 0.6 | 1.7696 | 1.0618 | H3 | 3 | Stable | 0.8 | 82 | 134 | 154 | 128.6667 | 0.4 | 38 | 51 | 61 | 50.5 | 0 | 0 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK001 | Project_081_RISK001 | Threat | Management Contingency | Open | H3 | 3 | 5. Project Management | Increase in Support Management | Person_260 | 2017-07-21 | 2021-07-21 | 0.4 | 2.0381 | 0.81526 | Reduce | 0.4 | 2.0381 | 0.81526 | H3 | 3 | Worsening | 0.9 | 117 | 123 | 148 | 126.1667 | 0.3 | 30 | 53 | 77 | 53.1667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK008 | Project_081_RISK008 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | Failure to meet repair turnaround time | Person_260 | 2017-09-27 01:00 | 2021-09-20 01:00 | 0.1 | 1.5866 | 0.15866 | Reduce | 0.1 | 1.5866 | 0.15866 | H3 | 3 | Stable | 0.9 | 107 | 136 | 154 | 134.1667 | 0.3 | 31 | 45 | 65 | 46 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK007 | Project_081_RISK007 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | High value supplier repair/replacements required | Person_260 | 2017-09-27 01:00 | 2021-09-20 01:00 | 0.4 | 3.7834 | 1.5133 | Reduce | 0.4 | 3.7834 | 1.5133 | H3 | 3 | Stable | 0.9 | 116 | 133 | 156 | 134 | 0.2 | 1 | 56 | 71 | 49.3333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK009 | Project_081_RISK009 | Threat | Management Contingency | Open | H2 | 4 | 7. Finance | Increase of Spares UPCs | Person_260 | 2017-09-27 01:00 | 2019-05-16 | 0.2 | 17.5011 | 3.5002 | Reduce | 0.2 | 17.5011 | 3.5002 | H3 | 3 | Stable | 0.9 | 112 | 132 | 147 | 131.1667 | 0.1 | 22 | 40 | 79 | 43.5 | 0 | 0 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP002 | Project_081_OPP002 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Core Management team shared across other programmes | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.3 | 0.91533 | 0.2746 | Exploit | 0.3 | 0.91533 | 0.2746 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP001 | Project_081_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | 7. Finance | Reduction in Spares UPC | Person_260 | 2017-07-21 | 2019-05-16 | 0.2 | 6.1022 | 1.2204 | -- | 0.2 | 6.1022 | 1.2204 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP004 | Project_081_OPP004 | Opportunitity | Project Contingency | Open | H3 | 3 | 7. Finance | Less repairs than planned in base costs | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.2 | 1.2204 | 0.24409 | -- | 0.2 | 1.2204 | 0.24409 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP003 | Project_081_OPP003 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Supplier abilities mature exponentially throughout contract requiring less FSE support | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.25 | 1.8307 | 0.45767 | -- | 0.25 | 1.8307 | 0.45767 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK015 | Project_081_RISK015 | Threat | Management Contingency | Open | H3 | 3 | 7. Finance | Our being liable for freight costs. | Person_260 | 2018-03-23 | 2021-09-20 01:00 | 0.3 | 3.0511 | 0.91533 | Reduce | 0.3 | 3.0511 | 0.91533 | H3 | 3 | Stable | 0.7 | 88 | 129 | 157 | 126.8333 | 0.4 | 3 | 52 | 70 | 46.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK014 | Project_081_RISK014 | Threat | Project Contingency | Open | H3 | 3 | 7. Finance | Supplier request financial support for Training admin. | Person_260 | 2018-02-20 01:00 | 2021-09-20 01:00 | 0.1 | 0.50038 | 0.050038 | Reduce | 0.1 | 0.50038 | 0.050038 | H3 | 3 | Stable | 0.6 | 110 | 139 | 142 | 134.6667 | 0.2 | 2 | 52 | 70 | 46.6667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK017 | Project_081_RISK017 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Extended working hours during site visits | Person_419 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.3 | 1.1716 | 0.35149 | Reduce | 0.3 | 1.1716 | 0.35149 | H3 | 3 | Stable | 0.9 | 106 | 121 | 141 | 121.8333 | 0.1 | 22 | 59 | 70 | 54.6667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK016 | Project_081_RISK016 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Additional visit support requested by Customer/Supplier | Person_260 | 2017-10-21 01:00 | 2021-09-20 01:00 | 0.4 | 2.331 | 0.93242 | Reduce | 0.4 | 2.331 | 0.93242 | H3 | 3 | Stable | 0.9 | 115 | 131 | 160 | 133.1667 | 0.2 | 25 | 41 | 77 | 44.3333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK011 | Project_081_RISK011 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Additional quantities of spares/material/STTE requested by customer | Person_260 | 2017-07-21 | 2019-07-22 | 0.1 | 6.3707 | 0.63707 | Reduce | 0.1 | 6.3707 | 0.63707 | H3 | 3 | Stable | 0.9 | 116 | 131 | 152 | 132 | 0.2 | 22 | 57 | 76 | 54.3333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK010 | Project_081_RISK010 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Increased material lead times for Spares | Person_649 | 2017-09-27 01:00 | 2019-05-16 | 0.1 | 6.3707 | 0.63707 | Reduce | 0.1 | 6.3707 | 0.63707 | H3 | 3 | Stable | 0.5 | 100 | 134 | 159 | 132.5 | 0.3 | 1 | 56 | 60 | 47.5 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK013 | Project_081_RISK013 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Additional training requested by customer. | Person_419 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.15 | 0.50038 | 0.075057 | Reduce | 0.15 | 0.50038 | 0.075057 | H3 | 3 | Stable | 0.8 | 111 | 136 | 159 | 135.6667 | 0.2 | 24 | 47 | 64 | 46 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK012 | Project_081_RISK012 | Threat | Project Contingency | Open | H3 | 3 | 12. Acquisition and offsets | Supplier unable to deliver course without our input | Person_419 | 2017-09-27 01:00 | 2021-09-27 01:00 | 0.5 | 0.50038 | 0.25019 | Reduce | 0.5 | 0.50038 | 0.25019 | H3 | 3 | Stable | 0.7 | 110 | 132 | 147 | 130.8333 | 0.2 | 25 | 54 | 66 | 51.1667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK019 | Project_081_RISK019 | Threat | Management Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Misc costs incurred at trials | Person_260 | 2018-05-23 | 2021-09-20 01:00 | 0.2 | 1.3425 | 0.2685 | Avoid | 0.2 | 1.3425 | 0.2685 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK018 | Project_081_RISK018 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Additional trials support requested (+3) | Person_260 | 2018-05-23 | 2021-07-21 | 0.2 | 2.0259 | 0.40519 | Reduce | 0.2 | 2.0259 | 0.40519 | H3 | 3 | Stable | 0.8 | 89 | 139 | 143 | 131.3333 | 0.1 | 7 | 56 | 72 | 50.5 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK020 | Project_081_RISK020 | Threat | Project Contingency | Open | H3 | 3 | 7. Finance | Travel Cost Increases | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 0.3 | 1.8307 | 0.5492 | Reduce | 0.3 | 1.8307 | 0.5492 | H3 | 3 | Stable | 0.6 | 117 | 140 | 153 | 138.3333 | 0.3 | 18 | 48 | 73 | 47.1667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-020 | Project_077_T-020 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Cybersecurity | Person_544 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.1 | 1.3478 | 0.13478 | Reduce | 0.1 | 1.3478 | 0.13478 | H3 | 3 | Stable | 0.6 | 107 | 123 | 141 | 123.3333 | 0.4 | 30 | 40 | 73 | 43.8333 | 0 | 0 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-005 | Project_077_T-005 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | SSTP/SSTR overspend | Person_202 | 2018-10-22 01:00 | 2020-02-21 01:00 | 0.3 | 10.5469 | 3.1641 | Reduce | 0.3 | 10.5469 | 3.1641 | H2 | 4 | Stable | 0.6 | 111 | 122 | 142 | 123.5 | 0.4 | 24 | 42 | 70 | 43.6667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-006 | Project_077_T-006 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Functionality | Person_202 | 2018-08-22 01:00 | 2020-02-21 01:00 | 0.2 | 3.774 | 0.7548 | -- | 0.2 | 3.774 | 0.7548 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-007 | Project_077_T-007 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Rig Failure or Damage | Person_092 | 2018-09-21 01:00 | 2020-12-08 01:00 | 0.3 | 2.033 | 0.6099 | Reduce | 0.3 | 2.033 | 0.6099 | H2 | 4 | Stable | 0.9 | 98 | 123 | 156 | 124.3333 | 0.4 | 27 | 42 | 76 | 45.1667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-023 | Project_077_T-023 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Sub-system legacy abilities | Person_544 | 2018-10-22 01:00 | 2020-02-21 01:00 | 0.1 | 1.0019 | 0.10019 | Avoid | 0.1 | 1.0019 | 0.10019 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-001 | Project_077_T-001 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Increased Interface changes | Person_544 | 2018-07-22 | 2018-10-20 01:00 | 0.5 | 2.1566 | 1.0783 | Transfer | 0.3 | 2.1566 | 0.64697 | H2 | 4 | Stable | [10 empty] | 0 | 40 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-002 | Project_077_T-002 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Legacy testing Repeatability | Person_202 | 2018-10-22 01:00 | 2019-05-11 | 0.3 | 2.4261 | 0.72784 | Accept | 0.3 | 2.4261 | 0.72784 | H2 | 4 | Stable | 0.9 | 100 | 133 | 147 | 129.8333 | 0.9 | 100 | 133 | 147 | 129.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-025 | Project_077_T-025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Delayed Config File delivery | Person_426 | 2019-05-24 | 2020-02-21 01:00 | 0.5 | 3.3696 | 1.6848 | Avoid | 0.5 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-003 | Project_077_T-003 | Threat | Project Contingency | Open | H1 | 5 | 9. Hardware/Software development | SW Resource availability | Person_509 | 2018-05-23 | 2020-02-21 01:00 | 0.5 | 25.1598 | 12.5799 | Reduce | 0.5 | 25.1598 | 12.5799 | H1 | 5 | Worsening | 0.9 | 83 | 124 | 150 | 121.5 | 0.1 | 5 | 43 | 63 | 40 | 0 | 0 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-026 | Project_077_T-026 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Insufficient Config Option capacity | Person_544 | 2018-04-22 | 2020-02-21 01:00 | 0.2 | 1.0019 | 0.20038 | Avoid | 0.05 | 1.0019 | 0.050095 | H3 | 3 | Stable | [10 empty] | 0 | 75 | 1 | 2.25
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-004 | Project_077_T-004 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Technical Debt | Person_202 | 2018-10-20 01:00 | 2020-02-21 01:00 | 0.2 | 2.1566 | 0.43131 | Reduce | 0.2 | 2.1566 | 0.43131 | H3 | 3 | Stable | 0.7 | 120 | 133 | 144 | 132.6667 | 0.3 | 26 | 45 | 68 | 45.6667 | 0 | 0 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | OPRisk-001 | Project_077_OPRisk-001 | Opportunitity | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Opportunity that fewer than expected customer problem reports are raised. | Person_544 | 2019-07-22 | 2020-02-21 01:00 | 0.5 | 3.3642 | 1.6821 | -- | 0.5 | 3364.2293 | 1682.1146 | H1 | 5 | Stable | [10 empty] | -99900 | 0 | 0 | -59940
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-010 | Project_077_T-010 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Technical Directorate changes to SW/data artefacts - Internal Requirement | Person_092 | 2018-11-21 01:00 | 2020-02-21 01:00 | 0.4 | 1.887 | 0.7548 | Reduce | 0.4 | 1.887 | 0.7548 | H2 | 4 | Stable | 0.6 | 117 | 127 | 158 | 130.5 | 0.1 | 28 | 44 | 68 | 45.3333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-032 | Project_077_T-032 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Requirement Updated from Issue 4 to 6 | Person_092 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.5 | 3.3696 | 1.6848 | Avoid | 0.1 | 3.3696 | 0.33696 | H3 | 3 | Stable | [10 empty] | 0 | 80 | 1 | 2.4
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-011 | Project_077_T-011 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Bus Scheduling table changes affecting proven interface | Person_544 | 2019-05-24 | 2020-02-21 01:00 | 0.2 | 0.92103 | 0.18421 | Reduce | 0.2 | 0.92103 | 0.18421 | H3 | 3 | Stable | 0.7 | 106 | 140 | 148 | 135.6667 | 0.3 | 16 | 47 | 63 | 44.5 | 0 | 0 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-033 | Project_077_T-033 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | PDA availability | Person_092 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.4 | 3.0327 | 1.2131 | Avoid | 0.4 | 3.0327 | 1.2131 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-016 | Project_077_T-016 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Autotest | Person_092 | 2018-12-09 01:00 | 2020-02-21 01:00 | 0.5 | 2.1341 | 1.067 | Reduce | 0.5 | 2.1341 | 1.067 | H2 | 4 | Stable | 0.5 | 107 | 126 | 158 | 128.1667 | 0.4 | 10 | 56 | 79 | 52.1667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-018 | Project_077_T-018 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Config system changes | Person_092 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.15 | 2.4711 | 0.37066 | Accept | 0.15 | 2.4711 | 0.37066 | H3 | 3 | Stable | 0.9 | 88 | 131 | 149 | 126.8333 | 0.9 | 88 | 131 | 149 | 126.8333 | 0 | 0 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-019 | Project_077_T-019 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | New stakeholders/Changeovers | Person_203 | 2018-02-20 01:00 | 2020-02-21 01:00 | 0.3 | 2.6957 | 0.80871 | Accept | 0.3 | 2.6957 | 0.80871 | H2 | 4 | Stable | 0.6 | 119 | 135 | 155 | 135.6667 | 0.6 | 119 | 135 | 155 | 135.6667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-012 | Project_077_T-012 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Management cost increases for BMN | Person_202 | 2018-03-01 01:00 | 2020-02-21 01:00 | 0.21 | 1.5725 | 0.33022 | Avoid | 0.21 | 1.5725 | 0.33022 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-034 | Project_077_T-034 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Simulator update not viable if needed | Person_203 | 2018-10-22 01:00 | 2020-02-21 01:00 | 0.5 | 0.74806 | 0.37403 | Avoid | 0.5 | 0.74806 | 0.37403 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-035 | Project_077_T-035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Cost of succession planning | Person_545 | 2018-04-22 | 2021-04-22 | 0.5 | 6.7392 | 3.3696 | -- | 0.5 | 11.2545 | 5.6273 | H2 | 4 | Stable | [10 empty] | -67 | 0 | 0 | -40.2
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-013 | Project_077_T-013 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | More customer failures than anticipated | Person_544 | 2019-07-22 | 2020-02-21 01:00 | 0.2 | 3.3809 | 0.67617 | Reduce | 0.2 | 3.3809 | 0.67617 | H3 | 3 | Stable | 0.8 | 109 | 123 | 154 | 125.8333 | 0.3 | 23 | 43 | 73 | 44.6667 | 0 | 0 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-014 | Project_077_T-014 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Extra Release | Person_203 | 2020-06-23 | 2020-11-20 01:00 | 0.1 | 13.4785 | 1.3478 | Avoid | 0.1 | 13.4785 | 1.3478 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_072 | RISK099 | Project_072_RISK099 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Multiplex Development Delay | Person_285 | 2018-07-21 | 2021-08-20 01:00 | 0.1 | 0.80789 | 0.080789 | Accept | 0.1 | 0.80789 | 0.080789 | H3 | 3 | Improving | 0.6 | 100 | 130 | 150 | 128.3333 | 0.6 | 100 | 130 | 150 | 128.3333 | 0 | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_072 | RISK101 | Project_072_RISK101 | Opportunitity | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SW Scope Update | Person_195 | 2018-07-21 | 2018-08-01 | 0.9 | 12.4856 | 11.237 | -- | 0.9 | 12.4856 | 11.237 | H2 | 4 | Improving | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_068 | RISK008 | Project_068_RISK008 | Threat | Project Contingency | Open | H1 | 5 | 1. Business Strategy and Objectives | Sub-system Suitably Qualified and experienced staff availability | Person_407 | 2017-07-21 | 2018-11-04 01:00 | 0 | 0 | 0 | Transfer | 0 | 0 | 0 | H1 | 5 | Worsening | [12 empty] | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_068 | RISK007 | Project_068_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Equipment Scheduling | Person_407 | 2017-07-21 | 2018-11-04 01:00 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Stable | 0.7 | 102 | 128 | 152 | 127.6667 | 0.4 | 27 | 48 | 75 | 49 |  | 60 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-054 | Project_062_Risk-054 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | sub-system rework to reviised standard | Person_031 | 2017-07-21 | 2018-11-21 01:00 | 0.4 | 0.62744 | 0.25098 | Transfer | 0.4 | 0.62744 | 0.25098 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-010 | Project_062_Risk-010 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software Resource | Person_479 | 2017-07-21 | 2019-02-21 01:00 | 0.4 | 7.5293 | 3.0117 | Reduce | 0.25 | 7.5293 | 1.8823 | H2 | 4 | Stable | 0.7 | 92 | 135 | 160 | 132 | 0.4 | 34 | 49 | 72 | 50.3333 | 0 | 37.5 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-057 | Project_062_Risk-057 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Supplier Application Encryption / Protection | Person_479 | 2017-07-21 | 2019-02-21 01:00 | 0.3 | 4.183 | 1.2549 | Reduce | 0.1 | 4.183 | 0.4183 | H3 | 3 | Stable | 0.9 | 111 | 124 | 159 | 127.6667 | 0.1 | 30 | 42 | 69 | 44.5 | 0 | 66.6667 | 1 | 2
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-013 | Project_062_Risk-013 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Unavailability of Network | Person_479 | 2017-07-21 | 2018-11-20 01:00 | 0.25 | 3.5555 | 0.88888 | Reduce | 0.15 | 3.5555 | 0.53333 | H3 | 3 | Improving | 0.8 | 120 | 135 | 145 | 134.1667 | 0.1 | 20 | 54 | 64 | 50 | 0 | 40 | 1 | 1.2
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-011 | Project_062_Risk-011 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Variant deviations between SW | Person_479 | 2017-07-21 | 2018-11-20 01:00 | 0.4 | 0.71808 | 0.28723 | Reduce | 0.3 | 0.71808 | 0.21542 | H2 | 4 | Stable | 0.8 | 96 | 140 | 156 | 135.3333 | 0.2 | 1 | 59 | 71 | 51.3333 | 0 | 25 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-056 | Project_062_Risk-056 | Threat | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Supplier integration acceptance by end Customer | Person_031 | 2017-07-21 | 2018-11-21 01:00 | 0.3 | 1.8823 | 0.5647 | Reduce | 0.3 | 1.8823 | 0.5647 | H3 | 3 | Stable | 0.5 | 91 | 129 | 146 | 125.5 | 0.2 | 14 | 45 | 70 | 44 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-018 | Project_062_Risk-018 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Prioritisation - new or less experienced staff | Person_459 | 2017-09-20 01:00 | 2019-02-20 01:00 | 0.35 | 12.7044 | 4.4465 | Reduce | 0.1 | 12.7044 | 1.2704 | H2 | 4 | Improving | 0.5 | 116 | 128 | 158 | 131 | 0.1 | 4 | 44 | 75 | 42.5 | 0 | 71.4286 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-016 | Project_062_Risk-016 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supplier Component Unavailability | Person_664 | 2017-07-21 | 2018-12-22 01:00 | 0.3 | 4.183 | 1.2549 | Reduce | 0.15 | 4.183 | 0.62744 | H3 | 3 | Stable | 0.8 | 114 | 132 | 144 | 131 | 0.4 | 18 | 47 | 75 | 46.8333 | 0 | 50 | 1 | 1.5
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-020 | Project_062_Risk-020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Security Encryption Solution | Person_245 | 2017-07-21 | 2018-10-22 01:00 | 0.25 | 4.183 | 1.0457 | Reduce | 0.2 | 4.183 | 0.83659 | H2 | 4 | Improving | 0.8 | 118 | 139 | 141 | 135.8333 | 0.1 | 20 | 51 | 73 | 49.5 | 0 | 20 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-021 | Project_062_Risk-021 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Hardware CoSupplierng | Person_664 | 2017-07-21 | 2018-11-20 01:00 | 0.3 | 7.5293 | 2.2588 | Reduce | 0.2 | 7.5293 | 1.5059 | H2 | 4 | Stable | 0.7 | 88 | 132 | 144 | 126.6667 | 0.3 | 26 | 59 | 66 | 54.6667 | 0 | 33.3333 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-043 | Project_062_Risk-043 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | User response | Person_479 | 2017-07-21 | 2019-02-21 01:00 | 0.35 | 3.3464 | 1.1712 | Avoid | 0.25 | 3.3464 | 0.83659 | H2 | 4 | Stable | [10 empty] | 0 | 28.5714 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-047 | Project_062_Risk-047 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Redhat6 on PCI shelf | Person_253 | 2017-07-21 | 2019-03-24 | 0.3 | 7.1808 | 2.1542 | Avoid | 0.15 | 7.1808 | 1.0771 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-025 | Project_062_Risk-025 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | System Obsolescence Risk | Person_543 | 2017-07-21 | 2019-03-22 | 0.3 | 2.0915 | 0.62744 | Avoid | 0.1 | 2.0915 | 0.20915 | H2 | 4 | Stable | [10 empty] | 0 | 66.6667 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-022 | Project_062_Risk-022 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Registers Might Be Unstable | Person_479 | 2017-07-21 | 2018-10-21 01:00 | 0.25 | 1.3385 | 0.33464 | Reduce | 0.2 | 1.3385 | 0.26771 | H3 | 3 | Stable | 0.8 | 102 | 122 | 153 | 123.8333 | 0.4 | 25 | 57 | 65 | 53 | 0 | 20 | 1 | 0.6
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-023 | Project_062_Risk-023 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Change In Security Boundary | Person_031 | 2017-07-21 | 2019-02-21 01:00 | 0.3 | 4.6013 | 1.3804 | Reduce | 0.15 | 4.6013 | 0.69019 | H3 | 3 | Stable | 0.6 | 99 | 132 | 157 | 130.6667 | 0.3 | 36 | 47 | 69 | 48.8333 | 0 | 50 | 1 | 1.5
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-048 | Project_062_Risk-048 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software lockdown features | Person_245 | 2017-07-21 | 2018-11-21 01:00 | 0.5 | 0.71808 | 0.35904 | Reduce | 0.5 | 0.71808 | 0.35904 | H2 | 4 | Stable | 0.6 | 115 | 127 | 142 | 127.5 | 0.3 | 19 | 58 | 65 | 52.6667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-005 | Project_062_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Security Solution Integration | Person_245 | 2017-07-21 | 2018-11-14 01:00 | 0.3 | 4.6013 | 1.3804 | Avoid | 0.25 | 4.6013 | 1.1503 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-009 | Project_062_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Unresolved technical debt (excluding ILS) | Person_253 | 2017-07-21 | 2019-03-23 | 0.5 | 2.5098 | 1.2549 | Reduce | 0.3 | 2.5098 | 0.75293 | H2 | 4 | Stable | 0.7 | 96 | 131 | 142 | 127 | 0.3 | 24 | 48 | 72 | 48 | 0 | 40 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-012 | Project_062_Risk-012 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Integration Rig Move | Person_253 | 2018-05-23 | 2019-05-23 | 0.3 | 0.4183 | 0.12549 | Avoid | 0.3 | 0.4183 | 0.12549 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-015 | Project_062_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Re-work | Person_253 | 2018-03-01 01:00 | 2019-05-22 | 0.5 | 1.0457 | 0.52287 | Avoid | 0.5 | 1.0457 | 0.52287 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-024 | Project_062_Risk-024 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional SW Build post-Factory Acceptance Test | Person_479 | 2018-08-22 01:00 | 2019-04-22 | 0.3 | 1.7778 | 0.53333 | Avoid | 0.3 | 1.7778 | 0.53333 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-027 | Project_062_Risk-027 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Facility to Test modifications | Person_253 | 2018-03-23 | 2019-04-22 | 0.5 | 2.3703 | 1.1852 | Reduce | 0.4 | 2.3703 | 0.94814 | H2 | 4 | Stable | 0.5 | 87 | 134 | 142 | 127.5 | 0.4 | 11 | 59 | 62 | 51.5 | 0 | 20 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-008 | Project_062_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Paperwork for Legacy & New Items | Person_459 | 2018-09-21 01:00 | 2019-04-23 | 0.3 | 0.83659 | 0.25098 | Avoid | 0.3 | 0.83659 | 0.25098 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-007 | Project_062_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Hardware Encryption / Protection | Person_479 | 2018-02-10 01:00 | 2019-03-22 | 0.3 | 4.183 | 1.2549 | Reduce | 0.2 | 4.183 | 0.83659 | H3 | 3 | Stable | 0.8 | 84 | 132 | 142 | 125.6667 | 0.4 | 11 | 41 | 77 | 42 | 0 | 33.3333 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | RISK004 | Project_062_RISK004 | Opportunitity | Project Contingency | Open | H3 | 3 | 9. Hardware/Software development | Carry out Console & Cabinet mod kit reviews in parallel | Person_019 | 2017-10-21 01:00 | 2019-02-21 01:00 | 0.5 | 0.33464 | 0.16732 | Exploit | 0.5 | 0.33464 | 0.16732 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | RISK013 | Project_062_RISK013 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | System modifications and technical debt. | Person_401 | 2018-12-22 01:00 | 2019-03-11 01:00 | 0.6 | 3.5555 | 2.1333 | Reduce | 0.4 | 3.5555 | 1.4222 | H2 | 4 | Stable | 0.5 | 96 | 125 | 156 | 125.3333 | 0.2 | 3 | 59 | 72 | 51.8333 | 0 | 33.3333 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK020 | Project_058_RISK020 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Supplier Delay | Person_511 | 2018-03-22 | 2018-10-22 01:00 | 0.8 | 3.9148 | 3.1318 | Reduce | 0.4 | 3.9148 | 1.5659 | H2 | 4 | Improving | 0.7 | 120 | 134 | 147 | 133.8333 | 0.4 | 11 | 47 | 62 | 43.5 | 0 | 50 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Customer find issues with delivered parts or documentation | Person_294 | 2017-05-23 | 2019-08-20 | 0.4 | 19.8087 | 7.9235 | Reduce | 0.25 | 19.8087 | 4.9522 | H2 | 4 | Improving | 0.7 | 104 | 136 | 152 | 133.3333 | 0.2 | 30 | 48 | 60 | 47 | 0 | 37.5 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK002 | Project_058_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Obsolescence of key parts | Person_236 | 2017-05-23 | 2019-08-07 | 0.5 | 6.7334 | 3.3667 | Reduce | 0.25 | 6.7334 | 1.6833 | H2 | 4 | Stable | 0.8 | 117 | 130 | 154 | 131.8333 | 0.2 | 29 | 49 | 78 | 50.5 | 0 | 50 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK052 | Project_058_RISK052 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply Chain | sub-System Cleanliness | Person_294 | 2017-05-23 | 2019-05-23 | 0.75 | 15.9918 | 11.9938 | Reduce | 0.2 | 15.9918 | 3.1984 | H3 | 3 | Stable | 0.7 | 111 | 135 | 147 | 133 | 0.2 | 22 | 58 | 79 | 55.5 | 0 | 73.3333 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Open PR's | Person_294 | 2018-04-22 | 2018-11-20 01:00 | 0.5 | 7.6338 | 3.8169 | Reduce | 0.3 | 7.6338 | 2.2901 | H3 | 3 | Improving | 0.6 | 90 | 139 | 156 | 133.6667 | 0.2 | 16 | 52 | 62 | 47.6667 | 0 | 40 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-113 | Project_043_Risk-113 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | No Gen 1 products available, transition cost to Gen 2 | Person_769 | 2017-04-19 | 2020-12-20 22:00 | 0.3 | 1.4971 | 0.44912 | Reduce | 0.3 | 1.4971 | 0.44912 | H2 | 4 | Stable | 0.9 | 101 | 128 | 141 | 125.6667 | 0.2 | 7 | 47 | 74 | 44.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-121 | Project_043_Risk-121 | Threat | Project Contingency | Open | H1 | 5 | 13. Logistic support and Services | More Tech Pubs Update than estimated | Person_769 | 2019-01-20 22:00 | 2020-10-19 22:00 | 0.45 | 1.7366 | 0.78146 | Reduce | 0.45 | 1.7366 | 0.78146 | H1 | 5 | Stable | 0.5 | 81 | 134 | 145 | 127 | 0.1 | 16 | 53 | 74 | 50.3333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-084 | Project_043_Risk-084 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | complex repair ( over and above the forecast average) | Person_693 | 2017-12-20 22:00 | 2020-12-20 22:00 | 0.2 | 0.71859 | 0.14372 | Reduce | 0.2 | 0.71859 | 0.14372 | H2 | 4 | Stable | 0.9 | 99 | 123 | 143 | 122.3333 | 0.2 | 24 | 51 | 73 | 50.1667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-128 | Project_043_Risk-128 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Reliance of Customer Avaliability | Person_135 | 2017-04-19 | 2018-08-21 | 0.5 | 1.7665 | 0.88326 | Reduce | 0.1 | 1.7665 | 0.17665 | H2 | 4 | Stable | 0.6 | 95 | 128 | 155 | 127 | 0.4 | 31 | 49 | 63 | 48.3333 | 0 | 80 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-089 | Project_043_Risk-089 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Spares pool is limited | Person_307 | 2018-12-21 22:00 | 2020-12-20 22:00 | 0.25 | 1.5969 | 0.39921 | Reduce | 0.25 | 1.2775 | 0.31937 | H2 | 4 | Stable | 0.8 | 104 | 131 | 156 | 130.6667 | 0.2 | 36 | 59 | 73 | 57.5 | 20 | 0 | 0 | 12
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-039 | Project_043_Risk-039 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System fails to achieve required performance | Person_051 | 2017-04-19 | 2018-11-19 22:00 | 0.3 | 4.7906 | 1.4372 | Reduce | 0.3 | 4.7906 | 1.4372 | H2 | 4 | Stable | 0.7 | 90 | 126 | 148 | 123.6667 | 0.3 | 23 | 47 | 73 | 47.3333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK026 | Project_097_RISK026 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | SW Uplift - Estimating Bias | Person_667 | 2018-09-21 01:00 | 2019-09-21 01:00 | 0.3 | 0.6529 | 0.19587 | Reduce | 0.15 | 0.6529 | 0.097935 | H2 | 4 | Stable | 0.5 | 104 | 132 | 152 | 130.6667 | 0.3 | 12 | 57 | 68 | 51.3333 | 0 | 50 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK048 | Project_097_RISK048 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Obsolescence - Data Migration takes longer than expected | Person_574 | 2019-05-24 | 2020-01-22 01:00 | 0.3 | 0.12886 | 0.038659 | Accept | 0.3 | 0.12886 | 0.038659 | H2 | 4 | Stable | 0.6 | 108 | 124 | 155 | 126.5 | 0.6 | 108 | 124 | 155 | 126.5 | 0 | 0 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK004 | Project_097_RISK004 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | SW Uplift Core - Core Software Engineer Resource Availability | Person_667 | 2018-09-15 01:00 | 2019-01-20 01:00 | 0.4 | 0.19866 | 0.079465 | Reduce | 0.1 | 0.19866 | 0.019866 | H2 | 4 | Worsening | 0.9 | 91 | 128 | 143 | 124.3333 | 0.3 | 17 | 43 | 66 | 42.5 | 0 | 75 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK047 | Project_097_RISK047 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Obsolescence - Desktops no longer available for purchase | Person_560 | 2018-09-21 01:00 | 2019-01-22 01:00 | 0.3 | 0.38659 | 0.11598 | Reduce | 0.25 | 0.38659 | 0.096647 | H2 | 4 | Stable | 0.6 | 85 | 122 | 158 | 121.8333 | 0.3 | 5 | 55 | 62 | 47.8333 | 0 | 16.6667 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK003 | Project_097_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | SW Uplift - Additional Software Release | Person_667 | 2018-09-22 01:00 | 2019-06-29 | 0.35 | 0.80539 | 0.28189 | Avoid | 0.15 | 0.80539 | 0.12081 | H2 | 4 | Stable | [10 empty] | 0 | 57.1429 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK006 | Project_097_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | SW Uplift - Compliance | Person_667 | 2019-05-24 | 2019-10-06 01:00 | 0.4 | 0.21477 | 0.085908 | Reduce | 0.1 | 0.21477 | 0.021477 | H2 | 4 | Stable | 0.5 | 110 | 138 | 153 | 135.8333 | 0.1 | 8 | 58 | 63 | 50.5 | 0 | 75 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK049 | Project_097_RISK049 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence - Hardware Failure | Person_659 | 2018-09-21 01:00 | 2019-10-20 01:00 | 0.2 | 0.1396 | 0.02792 | Reduce | 0.05 | 0.1396 | 0.0069801 | H2 | 4 | Stable | 0.6 | 108 | 122 | 143 | 123.1667 | 0.3 | 7 | 44 | 74 | 42.8333 | 0 | 75 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK027 | Project_097_RISK027 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SW Uplift - Must-Fix Defects are identified during roll-out period. | Person_667 | 2019-10-22 01:00 | 2020-01-22 01:00 | 0.1 | 0.90204 | 0.090204 | Reduce | 0.05 | 0.90204 | 0.045102 | H2 | 4 | Stable | 0.6 | 104 | 126 | 141 | 124.8333 | 0.4 | 36 | 40 | 75 | 45.1667 | 0 | 50 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK021 | Project_097_RISK021 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | SW Uplift - Late Delivery of our Dependencies | Person_574 | 2018-09-21 01:00 | 2019-01-21 01:00 | 0.3 | 0.20403 | 0.06121 | Reduce | 0.05 | 0.20403 | 0.010202 | H2 | 4 | Stable | 0.9 | 103 | 126 | 149 | 126 | 0.3 | 36 | 41 | 79 | 46.5 | 0 | 83.3333 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK043 | Project_097_RISK043 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence - Suppliers unable to provide extended validity on prices | Person_659 | 2018-09-21 01:00 | 2019-01-22 01:00 | 0.4 | 0.88593 | 0.35437 | Reduce | 0.2 | 0.84566 | 0.16913 | H2 | 4 | Stable | 0.8 | 87 | 134 | 144 | 127.8333 | 0.3 | 2 | 53 | 72 | 47.6667 | 4.5455 | 50 | 0 | 2.7273
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK024 | Project_097_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SW Uplift - regression testing not sufficient | Person_560 | 2018-09-21 01:00 | 2018-11-21 01:00 | 0.4 | 0.95358 | 0.38143 | Reduce | 0.05 | 0.54122 | 0.027061 | H2 | 4 | Stable | 0.8 | 80 | 138 | 147 | 129.8333 | 0.2 | 15 | 48 | 64 | 45.1667 | 43.2432 | 87.5 | 0 | 25.9459
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK002 | Project_097_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | SW Uplift - Additional Software Release | Person_667 | 2018-10-06 01:00 | 2018-10-27 01:00 | 0.1 | 0.080539 | 0.0080539 | Reduce | 0.05 | 0.080539 | 0.004027 | H2 | 4 | Stable | 0.7 | 97 | 131 | 145 | 127.6667 | 0.3 | 7 | 40 | 69 | 39.3333 | 0 | 50 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK045 | Project_097_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Obsolescence - solution more expensive than previously thought | Person_560 | 2018-08-22 01:00 | 2019-03-23 | 0.3 | 0.51545 | 0.15463 | Reduce | 0.05 | 0.51545 | 0.025772 | H2 | 4 | Stable | 0.6 | 87 | 140 | 146 | 132.1667 | 0.1 | 2 | 46 | 71 | 42.8333 | 0 | 83.3333 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK001 | Project_097_RISK001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SW Uplift - Additional Software Release | Person_667 | 2018-09-15 01:00 | 2018-10-20 01:00 | 0.25 | 0.15463 | 0.038659 | Reduce | 0.05 | 0.15463 | 0.0077317 | H2 | 4 | Stable | 0.5 | 84 | 139 | 155 | 132.5 | 0.1 | 12 | 58 | 67 | 51.8333 | 0 | 80 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK008 | Project_097_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | SW Uplift - implementation of New Scope | Person_560 | 2019-09-04 01:00 | 2019-10-06 01:00 | 0.3 | 0.1745 | 0.05235 | Reduce | 0.05 | 0.1745 | 0.008725 | H2 | 4 | Stable | 0.5 | 103 | 134 | 155 | 132.3333 | 0.3 | 34 | 42 | 72 | 45.6667 | 0 | 83.3333 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK029 | Project_097_RISK029 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | SW Uplift - Test period extended | Person_574 | 2019-08-22 01:00 | 2019-09-21 01:00 | 0.3 | 0.12886 | 0.038659 | Reduce | 0.2 | 0.12886 | 0.025772 | H2 | 4 | Stable | 0.7 | 97 | 121 | 145 | 121 | 0.3 | 15 | 56 | 73 | 52 | 0 | 33.3333 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK009 | Project_097_RISK009 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | SW Uplift - Customer Trial | Person_560 | 2019-08-22 01:00 | 2019-09-20 01:00 | 0.4 | 0.34712 | 0.13885 | Reduce | 0.1 | 0.34712 | 0.034712 | H2 | 4 | Stable | 0.7 | 117 | 135 | 147 | 134 | 0.3 | 11 | 50 | 79 | 48.3333 | 0 | 75 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK051 | Project_097_RISK051 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Obsolescence - SME Resource Availability during rollout | Person_667 | 2019-10-22 01:00 | 2020-01-20 01:00 | 0.4 | 0.070874 | 0.02835 | Reduce | 0.05 | 0.070874 | 0.0035437 | H2 | 4 | Stable | 0.8 | 102 | 135 | 149 | 131.8333 | 0.4 | 8 | 49 | 70 | 45.6667 | 0 | 87.5 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK050 | Project_097_RISK050 | Threat | Management Contingency | Open | H2 | 4 | 13. Logistic support and Services | Obsolescence - FSE Availability during rollout | Person_234 | 2019-10-22 01:00 | 2019-12-22 01:00 | 0.25 | 0.070874 | 0.017719 | Reduce | 0.15 | 0.070874 | 0.010631 | H2 | 4 | Stable | 0.6 | 108 | 129 | 144 | 128 | 0.4 | 12 | 56 | 69 | 50.8333 | 0 | 40 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK031 | Project_097_RISK031 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | SW Uplift - Additional support | Person_659 | 2019-10-22 01:00 | 2019-12-22 01:00 | 0.2 | 0.18792 | 0.037585 | Reduce | 0.1 | 0.18792 | 0.018792 | H2 | 4 | Improving | 0.8 | 118 | 138 | 143 | 135.5 | 0.4 | 39 | 50 | 60 | 49.8333 | 0 | 50 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK052 | Project_097_RISK052 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | SW Uplift - Penetration Test identifies critical vulnerabilities | Person_667 | 2018-11-21 01:00 | 2019-10-22 01:00 | 0.4 | 0.40806 | 0.16323 | Reduce | 0.25 | 0.40806 | 0.10202 | H2 | 4 | Stable | 0.5 | 91 | 134 | 144 | 128.5 | 0.3 | 21 | 57 | 69 | 53 | 0 | 37.5 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK015 | Project_097_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SW Uplift - Failure of test environment | Person_667 | 2018-11-21 01:00 | 2019-09-21 01:00 | 0.2 | 0.065773 | 0.013155 | Reduce | 0.1 | 0.065773 | 0.0065773 | H2 | 4 | Stable | 0.8 | 101 | 137 | 149 | 133 | 0.4 | 1 | 51 | 74 | 46.5 | 0 | 50 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK037 | Project_097_RISK037 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Migration - may have a detrimental effect | Person_648 | 2018-11-21 01:00 | 2019-09-21 01:00 | 0.25 | 0.068727 | 0.017182 | Reduce | 0.15 | 0.068727 | 0.010309 | H2 | 4 | Stable | 0.6 | 102 | 121 | 155 | 123.5 | 0.2 | 11 | 41 | 68 | 40.5 | 0 | 40 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK036 | Project_097_RISK036 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Migration - Software defect identified during formal Testing | Person_667 | 2018-11-21 01:00 | 2019-09-21 01:00 | 0.2 | 0.31142 | 0.062283 | Reduce | 0.1 | 0.31142 | 0.031142 | H2 | 4 | Stable | 0.6 | 106 | 137 | 141 | 132.5 | 0.1 | 34 | 46 | 66 | 47.3333 | 0 | 50 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK039 | Project_097_RISK039 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Obsolescence - Encrypted Hardware Approval to purchase | Person_574 | 2018-10-22 01:00 | 2019-04-23 | 0.3 | 0.048323 | 0.014497 | Reduce | 0.2 | 0.048323 | 0.0096647 | H2 | 4 | Stable | 0.7 | 104 | 122 | 145 | 122.8333 | 0.2 | 17 | 46 | 76 | 46.1667 | 0 | 33.3333 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK011 | Project_097_RISK011 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | SW Uplift Core - Price Reduction | Person_667 | 2018-09-15 01:00 | 2019-01-21 01:00 | 0.05 | 0.46981 | 0.023491 | Exploit | 0.5 | 0.46981 | 0.23491 | H1 | 5 | Stable | [10 empty] | 0 | -900 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK055 | Project_097_RISK055 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | SW Uplift - Additional technical impact | Person_560 | 2019-05-24 | 2019-10-22 01:00 | 0.3 | 0.31142 | 0.093425 | Accept | 0.3 | 0.31142 | 0.093425 | H2 | 4 | Stable | 0.8 | 95 | 123 | 150 | 122.8333 | 0.8 | 95 | 123 | 150 | 122.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK010 | Project_097_RISK010 | Opportunitity | Project Contingency | Open | H2 | 4 | 5. Project Management | SW Uplift - Test Report Efficiencies | Person_667 | 2019-08-22 01:00 | 2019-10-22 01:00 | 0.05 | 0.077317 | 0.0038659 | Exploit | 0.25 | 0.077317 | 0.019329 | H2 | 4 | Stable | [10 empty] | 0 | -400 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK054 | Project_097_RISK054 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Obsolescence - Picture of obsolescence changes between estimation and realisation | Person_574 | 2018-08-22 01:00 | 2019-10-22 01:00 | 0.3 | 0.17182 | 0.051545 | Reduce | 0.25 | 0.17182 | 0.042954 | H2 | 4 | Stable | 0.8 | 116 | 136 | 145 | 134.1667 | 0.2 | 10 | 49 | 77 | 47.1667 | 0 | 16.6667 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK032 | Project_097_RISK032 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | SW Uplift - Bugs | Person_659 | 2018-12-22 01:00 | 2019-09-21 01:00 | 0.2 | 0.64431 | 0.12886 | Reduce | 0.05 | 0.64431 | 0.032216 | H2 | 4 | Stable | 0.9 | 109 | 123 | 145 | 124.3333 | 0.3 | 12 | 59 | 79 | 54.5 | 0 | 75 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK056 | Project_097_RISK056 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Obsolescence - Additional testing required following review of VCRM | Person_667 | 2019-07-22 | 2019-12-22 01:00 | 0.4 | 0.32323 | 0.12929 | Reduce | 0.05 | 0.32323 | 0.016162 | H2 | 4 | Stable | 0.5 | 87 | 136 | 155 | 131 | 0.1 | 5 | 54 | 69 | 48.3333 | 0 | 87.5 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK012 | Project_097_RISK012 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | SW Uplift - Scan | Person_667 | 2018-12-01 01:00 | 2019-02-09 01:00 | 0.3 | 0.21209 | 0.063626 | Reduce | 0.1 | 0.21209 | 0.021209 | H2 | 4 | Stable | 0.6 | 104 | 131 | 147 | 129.1667 | 0.3 | 27 | 40 | 64 | 41.8333 | 0 | 66.6667 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK018 | Project_097_RISK018 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | SW Uplift - Loss of Key resource | Person_668 | 2018-09-21 01:00 | 2020-05-22 | 0.25 | 0.78391 | 0.19598 | Reduce | 0.1 | 0.78391 | 0.078391 | H2 | 4 | Stable | 0.6 | 103 | 134 | 149 | 131.3333 | 0.4 | 31 | 58 | 70 | 55.5 | 0 | 60 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK040 | Project_097_RISK040 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Data is inconsistent with the Data Specification | Person_560 | 2018-11-21 01:00 | 2019-09-21 01:00 | 0.2 | 0.040806 | 0.0081612 | Transfer | 0.05 | 0.040806 | 0.0020403 | H2 | 4 | Stable | [10 empty] | 0 | 75 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK020 | Project_097_RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | SW Uplift - Late Delivery of Software Sub-Systems | Person_574 | 2018-09-21 01:00 | 2019-01-21 01:00 | 0.2 | 0.12886 | 0.025772 | Reduce | 0.05 | 0.12886 | 0.0064431 | H2 | 4 | Stable | 0.7 | 119 | 139 | 153 | 138 | 0.4 | 27 | 51 | 78 | 51.5 | 0 | 75 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK042 | Project_097_RISK042 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Obsolescence - Supplier lead times | Person_659 | 2018-10-22 01:00 | 2019-01-22 01:00 | 0.3 | 0.034363 | 0.010309 | Reduce | 0.15 | 0.034363 | 0.0051544 | H2 | 4 | Stable | 0.9 | 118 | 138 | 159 | 138.1667 | 0.1 | 14 | 53 | 70 | 49.3333 | 0 | 50 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK041 | Project_097_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Obsolescence - System instalations | Person_667 | 2019-08-22 01:00 | 2019-11-21 01:00 | 0.25 | 0.068727 | 0.017182 | Reduce | 0.05 | 0.068727 | 0.0034364 | H2 | 4 | Stable | 0.8 | 114 | 133 | 145 | 131.8333 | 0.3 | 12 | 42 | 76 | 42.6667 | 0 | 80 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK033 | Project_079_RISK033 | Opportunitity | Project Contingency | Open | H3 | 3 | 5. Project Management | Completion of Build in year 4 or 5 | Person_683 | 2018-09-30 01:00 | 2020-08-21 01:00 | 0.5 | 0.98209 | 0.49104 | -- | 0.5 | 0.98209 | 0.49104 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-003 | Project_098_Risk-003 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Continuation of in service support | Person_464 | 2018-05-24 | 2027-05-16 | 0.5 | 51.6624 | 25.8312 | Reduce | 0.1 | 2.5831 | 0.25831 | H2 | 4 | Stable | 0.7 | 109 | 134 | 159 | 134 | 0.1 | 1 | 44 | 73 | 41.6667 | 95 | 80 | 0 | 57
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-005 | Project_098_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | SubSystem Failure | Person_360 | 2018-05-24 | 2019-11-20 01:00 | 0.2 | 3.8747 | 0.77494 | Reduce | 0.1 | 3.8747 | 0.38747 | H2 | 4 | Stable | 0.9 | 119 | 131 | 153 | 132.6667 | 0.1 | 14 | 45 | 77 | 45.1667 | 0 | 50 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-007 | Project_098_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Operational Damage Not Allowed | Person_439 | 2018-05-24 | 2027-05-23 | 0.3 | 5.1662 | 1.5499 | Accept | 0.3 | 5.1662 | 1.5499 | H2 | 4 | Stable | 0.8 | 108 | 125 | 146 | 125.6667 | 0.8 | 108 | 125 | 146 | 125.6667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-008 | Project_098_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Efficiency Targets Not realised | Person_360 | 2018-05-24 | 2027-05-23 | 0.3 | 0 | 0 | Accept | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.6 | 120 | 126 | 149 | 128.8333 | 0.6 | 120 | 126 | 149 | 128.8333 |  | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-005 | Project_098_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | POOR SUPPLIER QUALITY | Person_660 | 2018-05-23 | 2033-05-22 | 0.3 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.6 | 112 | 123 | 142 | 124.3333 | 0.4 | 4 | 56 | 72 | 50 |  | 66.6667 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-002 | Project_098_Risk-002 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | External Sub-system DESIGN | Person_660 | 2018-05-23 | 2033-05-22 | 0.5 | 3.6379 | 1.8189 | Reduce | 0.3 | 2.7984 | 0.83951 | H2 | 4 | Stable | 0.9 | 106 | 122 | 159 | 125.5 | 0.3 | 31 | 57 | 72 | 55.1667 | 23.0769 | 40 | 0 | 13.8462
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-001 | Project_098_Risk-001 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | UNIT PRODUCTION COSTS | Person_660 | 2018-05-23 | 2033-05-22 | 0.8 | 276.8242 | 221.4594 | Reduce | 0.5 | 135.6137 | 67.8069 | H1 | 5 | Stable | 0.7 | 80 | 137 | 155 | 130.5 | 0.2 | 22 | 57 | 61 | 51.8333 | 51.0109 | 37.5 | 0 | 30.6065
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-003 | Project_098_Risk-003 | Threat | Project Contingency | Open | H1 | 5 | 11. Supply chain | External Sub-system CAPACITY | Person_660 | 2018-05-23 | 2033-05-22 | 0.5 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H1 | 5 | Stable | 0.9 | 94 | 126 | 159 | 126.1667 | 0.1 | 1 | 41 | 79 | 40.6667 |  | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK088 | Project_076_RISK088 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Change to decision on aggregation | Person_628 | 2018-09-21 01:00 | 2019-05-16 | 0.1 | 12.4383 | 1.2438 | Reject | 0.1 | 12.4383 | 1.2438 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK079 | Project_076_RISK079 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Resources required to finish project | Person_152 | 2019-03-24 | 2019-05-16 | 0.6996 | 26.535 | 18.5639 | Accept | 0.6996 | 26.535 | 18.5639 | H1 | 5 | Stable | 0.5 | 115 | 126 | 160 | 129.8333 | 0.5 | 115 | 126 | 160 | 129.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK078 | Project_076_RISK078 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Schedule Slippage due to change in resource allocation | Person_152 | 2018-08-25 01:00 | 2019-09-20 01:00 | 0.75 | 8.2922 | 6.2191 | Accept | 0.75 | 8.2922 | 6.2191 | H1 | 5 | Stable | 0.8 | 87 | 125 | 154 | 123.5 | 0.8 | 87 | 125 | 154 | 123.5 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK089 | Project_076_RISK089 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Travel cost savings | Person_152 | 2018-09-21 01:00 | 2019-05-16 | 0.5 | 2.7364 | 1.3682 | Reject | 0.5 | 2.7364 | 1.3682 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK084 | Project_076_RISK084 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Safety assessment creates the need for additional development activities | Person_484 | 2018-09-21 01:00 | 2019-05-23 | 0.39 | 8.2922 | 3.234 | Accept | 0.39 | 8.2922 | 3.234 | H2 | 4 | Stable | 0.7 | 107 | 140 | 157 | 137.3333 | 0.7 | 107 | 140 | 157 | 137.3333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK083 | Project_076_RISK083 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Higher than expected level of bug fixing required | Person_152 | 2018-09-21 01:00 | 2019-09-20 01:00 | 0.5 | 16.5844 | 8.2922 | Accept | 0.5 | 16.5844 | 8.2922 | H2 | 4 | Stable | 0.9 | 85 | 140 | 148 | 132.1667 | 0.9 | 85 | 140 | 148 | 132.1667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK086 | Project_076_RISK086 | Opportunitity | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Reduction in modules that require full safety process | Person_771 | 2018-09-21 01:00 | 2019-05-23 | 0.5 | 13.5163 | 6.7581 | Reject | 0.5 | 13.5163 | 6.7581 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK085 | Project_076_RISK085 | Opportunitity | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | E2 Cloud - Shared Cloud License | Person_152 | 2019-02-21 01:00 | 2019-05-23 | 0.2 | 4.8095 | 0.96189 | Reject | 0.2 | 4.8095 | 0.96189 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK091 | Project_076_RISK091 | Threat | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Peer review teams unavailable for the required project timescales | Person_484 | 2018-09-21 01:00 | 2019-05-16 | 0.3 | 0 | 0 | Accept | 0.3 | 0 | 0 | H2 | 4 | Stable | 0.8 | 101 | 131 | 158 | 130.5 | 0.8 | 101 | 131 | 158 | 130.5 |  | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK080 | Project_076_RISK080 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional technical support required to supplier | Person_621 | 2018-09-21 01:00 | 2019-05-23 | 0.5 | 10.7798 | 5.3899 | Accept | 0.5 | 10.7798 | 5.3899 | H2 | 4 | Stable | 0.9 | 116 | 122 | 154 | 126.3333 | 0.9 | 116 | 122 | 154 | 126.3333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK090 | Project_076_RISK090 | Opportunitity | Project Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Reduction in LoE as project tapers off during final year | Person_628 | 2018-09-21 01:00 | 2019-05-16 | 0.5 | 9.9506 | 4.9753 | Reject | 0.5 | 9.9506 | 4.9753 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK082 | Project_076_RISK082 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Additional project integration support is required | Person_152 | 2018-09-21 01:00 | 2019-09-20 01:00 | 0.4 | 20.7305 | 8.2922 | Accept | 0.4 | 20.7305 | 8.2922 | H2 | 4 | Stable | 0.9 | 84 | 135 | 156 | 130 | 0.9 | 84 | 135 | 156 | 130 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK092 | Project_076_RISK092 | Threat | Management Contingency | Open | H2 | 4 | 1. Business Strategy and Objectives | Labour Rate Change | Person_628 | 2019-05-24 | 2019-08-22 01:00 | 0.5 | 19.3622 | 9.6811 | Accept | 0.5 | 19.3626 | 9.6813 | H2 | 4 | Stable | 0.6 | 84 | 128 | 152 | 124.6667 | 0.6 | 84 | 128 | 152 | 124.6667 | -0.0017131 | 0 | 0 | -0.0010278
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK081 | Project_076_RISK081 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | New Safety tagged requirements are defined, increasing safety workload | Person_771 | 2018-09-21 01:00 | 2019-05-23 | 0.4 | 13.5163 | 5.4065 | Accept | 0.4 | 13.5163 | 5.4065 | H2 | 4 | Stable | 0.9 | 109 | 128 | 155 | 129.3333 | 0.9 | 109 | 128 | 155 | 129.3333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 4 | 4. Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2018-11-20 01:00 | 0.5 | 3.9587 | 1.9793 | Reduce | 0.4 | 0.45943 | 0.18377 | H2 | 4 | Stable | 0.9 | 112 | 138 | 154 | 136.3333 | 0.2 | 19 | 49 | 63 | 46.3333 | 88.3943 | 20 | 0 | 53.0366
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_703 | 2015-05-24 | 2019-05-22 | 0.5 | 6.2979 | 3.1489 | Reduce | 0.15 | 1.1996 | 0.17994 | H3 | 3 | Stable | 0.5 | 117 | 123 | 160 | 128.1667 | 0.4 | 28 | 54 | 63 | 51.1667 | 80.9521 | 70 | 1 | 50.6713
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--108 | Project_100_Risk--108 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Insufficient LOE to manage the supply chain with reducing number of spares | Person_639 | 2018-08-22 01:00 | 2021-08-20 01:00 | 0.4 | 0.6385 | 0.2554 | Accept | 0.4 | 0.6385 | 0.2554 | H3 | 3 | Stable | 0.7 | 87 | 126 | 144 | 122.5 | 0.7 | 87 | 126 | 144 | 122.5 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--107 | Project_100_Risk--107 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Supplier Costs higher than expected | Person_639 | 2018-08-22 01:00 | 2021-08-20 01:00 | 0.4 | 1.6239 | 0.64955 | -- | 0.4 | 1.6239 | 0.64955 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--109 | Project_100_Risk--109 | Threat | Project Contingency | Open | H3 | 3 | 13. Logistic support and Services | Increased repairs and spares | Person_639 | 2018-08-22 01:00 | 2021-08-20 01:00 | 0.2 | 2.1583 | 0.43166 | Accept | 0.2 | 2.1583 | 0.43166 | H3 | 3 | Stable | 0.6 | 120 | 133 | 159 | 135.1667 | 0.6 | 120 | 133 | 159 | 135.1667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--103 | Project_100_Risk--103 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Consumable Stock Levels | Person_639 | 2018-08-22 01:00 | 2021-08-20 01:00 | 0.5 | 1.5417 | 0.77083 | Accept | 0.5 | 1.5417 | 0.77083 | H3 | 3 | Stable | 0.5 | 115 | 131 | 151 | 131.6667 | 0.5 | 115 | 131 | 151 | 131.6667 | 0 | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--105 | Project_100_Risk--105 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | FFF replacement costs | Person_433 | 2018-08-22 01:00 | 2021-08-20 01:00 | 0.4 | 1.1049 | 0.44194 | -- | 0.4 | 1.1049 | 0.44194 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--100 | Project_100_Risk--100 | Threat | Project Contingency | Open | H3 | 3 | 6. Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_567 | 2018-08-22 01:00 | 2021-08-20 01:00 | 0.25 | 0.34687 | 0.086718 | Accept | 0.25 | 0.34687 | 0.086718 | H3 | 3 | Stable | 0.7 | 115 | 139 | 156 | 137.8333 | 0.7 | 115 | 139 | 156 | 137.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--111 | Project_100_Risk--111 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Failure to achieve KPIs | Person_567 | 2018-08-22 01:00 | 2021-08-20 01:00 | 0.1 | 3.7 | 0.37 | -- | 0.1 | 3.7 | 0.37 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--102 | Project_100_Risk--102 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Demands but not provisioned | Person_639 | 2018-08-22 01:00 | 2021-08-20 01:00 | 0.3 | 2.2868 | 0.68604 | Accept | 0.3 | 2.2868 | 0.68604 | H3 | 3 | Stable | 0.9 | 103 | 125 | 143 | 124.3333 | 0.9 | 103 | 125 | 143 | 124.3333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | RISK015 | Project_062_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Absence of evidence underpinning the supporting CoDs and thus the Safety Case. | Person_253 | 2018-09-21 01:00 | 2019-02-21 01:00 | 0.8 | 0.62744 | 0.50196 | Avoid | 0.2 | 0.62744 | 0.12549 | H3 | 3 | Stable | [10 empty] | 0 | 75 | 1 | 2.25
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | RISK014 | Project_062_RISK014 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Rework to kits following Factory Acceptance Test | Person_253 | 2018-11-21 01:00 | 2019-04-22 | 0.2 | 0.62744 | 0.12549 | Avoid | 0.2 | 0.62744 | 0.12549 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2018-04-22 | 0.8 | 1.1089 | 0.88715 | Accept | 0.6 | 0.73929 | 0.44357 | H1 | 5 | Stable | 0.6 | 82 | 131 | 149 | 125.8333 | 0.6 | 82 | 131 | 149 | 125.8333 | 33.3333 | 25 | 0 | 20
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-28 17:00 | 2018-05-22 | 0.1 | 0.55447 | 0.055447 | Reduce | 0.05 | 0.55447 | 0.027723 | H3 | 3 | Stable | 0.5 | 115 | 124 | 152 | 127.1667 | 0.4 | 15 | 53 | 69 | 49.3333 | 0 | 50 | 1 | 1.5
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2018-05-22 | 0.2 | 0.92411 | 0.18482 | Reduce | 0.15 | 0.92411 | 0.13862 | H3 | 3 | Stable | 0.9 | 118 | 132 | 159 | 134.1667 | 0.2 | 10 | 54 | 75 | 50.1667 | 0 | 25 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_693 | 2012-06-01 | 2018-04-22 | 0.5 | 0.27723 | 0.13862 | Reduce | 0.3 | 0.27723 | 0.08317 | H2 | 4 | Improving | 0.8 | 109 | 140 | 144 | 135.5 | 0.2 | 16 | 56 | 67 | 51.1667 | 0 | 40 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2018-05-21 | 0.8 | 0.18482 | 0.14786 | Avoid | 0.5 | 0.18482 | 0.092411 | H1 | 5 | Stable | [10 empty] | 0 | 37.5 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-26 17:00 | 2018-05-22 | 0.1 | 3.6965 | 0.36965 | Accept | 0.05 | 3.6965 | 0.18482 | H2 | 4 | Stable | 0.9 | 116 | 137 | 145 | 134.8333 | 0.9 | 116 | 137 | 145 | 134.8333 | 0 | 50 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2018-05-21 | 0.2 | 0.92411 | 0.18482 | Accept | 0.2 | 0.92411 | 0.18482 | H3 | 3 | Worsening | 0.5 | 117 | 130 | 154 | 131.8333 | 0.5 | 117 | 130 | 154 | 131.8333 | 0 | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2018-04-22 | 0.3 | 1.8482 | 0.55447 | Accept | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.9 | 106 | 128 | 157 | 129.1667 | 0.9 | 106 | 128 | 157 | 129.1667 | 0 | 33.3333 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2018-02-18 17:00 | 0.8 | 18.4823 | 14.7858 | Reduce | 0.2 | 1.8482 | 0.36965 | H3 | 3 | Stable | 0.8 | 111 | 133 | 146 | 131.5 | 0.2 | 31 | 58 | 70 | 55.5 | 90 | 75 | 1 | 56.25
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK010 | Project_010_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Use of Lead components | Person_359 | 2012-05-23 | 2025-04-22 | 0.05 | 1.8482 | 0.092411 | Reduce | 0.05 | 1.8482 | 0.092411 | H3 | 3 | Stable | 0.6 | 95 | 137 | 146 | 131.5 | 0.1 | 27 | 49 | 71 | 49 | 0 | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2018-05-22 | 0.5 | 3.6965 | 1.8482 | Reduce | 0.3 | 3.6965 | 1.1089 | H2 | 4 | Stable | 0.8 | 116 | 140 | 160 | 139.3333 | 0.4 | 22 | 54 | 61 | 49.8333 | 0 | 40 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-19 17:00 | 0.05 | 11.0894 | 0.55447 | Accept | 0.03 | 11.0894 | 0.33268 | H2 | 4 | Stable | 0.8 | 92 | 130 | 151 | 127.1667 | 0.8 | 92 | 130 | 151 | 127.1667 | 0 | 40 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 0.92411 | 0.55447 | Reduce | 0.5 | 0.36965 | 0.18482 | H2 | 4 | Stable | 0.6 | 81 | 139 | 143 | 130 | 0.3 | 16 | 48 | 65 | 45.5 | 60 | 16.6667 | 0 | 36
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software Development | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-03 17:00 | 2018-04-21 | 0.2 | 4.0661 | 0.81322 | Reduce | 0.05 | 4.0661 | 0.2033 | H3 | 3 | Stable | 0.5 | 115 | 140 | 159 | 139 | 0.1 | 8 | 50 | 72 | 46.6667 | 0 | 75 | 1 | 2.25
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 0.6 | 1.1089 | 0.66536 | Reduce | 0.5 | 0.46206 | 0.23103 | H1 | 5 | Stable | 0.7 | 117 | 131 | 152 | 132.1667 | 0.3 | 25 | 52 | 61 | 49 | 58.3333 | 16.6667 | 0 | 35
2018-08-22 | ORG_001 | BA_002 | Portfolio_009 | Project_051 | RISK001 | Project_051_RISK001 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Generic Labour or Material Overspend | Person_577 | 2012-05-23 | 2021-05-22 | 0.5 | 0.78901 | 0.3945 | Accept | 0.5 | 0.78901 | 0.3945 | H3 | 3 | Stable | 0.5 | 118 | 130 | 158 | 132.6667 | 0.5 | 118 | 130 | 158 | 132.6667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Volume of production tools and Jigs | Person_279 | 2016-11-22 20:00 | 2021-11-22 20:00 | 0.35 | 6.4382 | 2.2534 | Reduce | 0.15 | 6.4382 | 0.96573 | H2 | 4 | Stable | 0.7 | 95 | 129 | 143 | 125.6667 | 0.4 | 31 | 51 | 74 | 51.5 | 0 | 57.1429 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software issue input | Person_279 | 2016-11-22 20:00 | 2023-02-19 20:00 | 0.4 | 49.4398 | 19.7759 | Reduce | 0.2 | 49.4398 | 9.888 | H2 | 4 | Stable | 0.6 | 116 | 123 | 158 | 127.6667 | 0.2 | 3 | 55 | 77 | 50 | 0 | 50 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_068 | RISK040 | Project_068_RISK040 | Threat | Project Contingency | Open | H1 | 5 | 4. Customers | Risk that the relationship with the customer breaks down | Person_407 | 2017-02-20 01:00 | 2018-11-04 01:00 | 0.7 | 0 | 0 | -- | 0.7 | 0 | 0 | H1 | 5 | Stable | [11 empty] | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK015 | Project_041_RISK015 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Conponent on product #1 having to be returned to Supplier (qualification temperature failure) | Person_693 | 2018-10-22 01:00 | 2018-12-22 01:00 | 0.5 | 1.029 | 0.51448 | -- | 0.5 | 1.029 | 0.51448 | H2 | 4 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK011 | Project_041_RISK011 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Supplier Development support | Person_693 | 2018-04-11 | 2019-01-19 01:00 | 0.5 | 0.77172 | 0.38586 | Accept | 0.332 | 0.77172 | 0.25621 | H2 | 4 | Stable | 0.9 | 87 | 134 | 156 | 129.8333 | 0.9 | 87 | 134 | 156 | 129.8333 | 0 | 33.6 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK010 | Project_041_RISK010 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Digital Assembly - Testing | Person_547 | 2018-04-11 | 2019-05-16 | 0.15 | 0.57879 | 0.086819 | Accept | 0.1 | 0.57879 | 0.057879 | H3 | 3 | Improving | 0.5 | 102 | 128 | 147 | 126.8333 | 0.5 | 102 | 128 | 147 | 126.8333 | 0 | 33.3333 | 1 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK013 | Project_041_RISK013 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional components validation | Person_693 | 2017-07-15 | 2018-10-21 01:00 | 0.4 | 1.6721 | 0.66883 | Accept | 0.139 | 1.6721 | 0.23242 | H3 | 3 | Stable | 0.8 | 102 | 126 | 157 | 127.1667 | 0.8 | 102 | 126 | 157 | 127.1667 | 0 | 65.25 | 1 | 1.9575
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Unforseen and substantial increase in Repairs workload during new build production period. | Person_547 | 2017-10-23 01:00 | 2019-08-21 01:00 | 0.3 | 1.5434 | 0.46303 | Reduce | 0.1 | 1.5434 | 0.15434 | H3 | 3 | Stable | 0.9 | 119 | 135 | 156 | 135.8333 | 0.1 | 33 | 57 | 65 | 54.3333 | 0 | 66.6667 | 1 | 2
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK007 | Project_041_RISK007 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Advanced production of products using a Qual. standard component rather than a Prod. standard | Person_547 | 2018-09-21 01:00 | 2019-02-20 01:00 | 0.49 | 1.2862 | 0.63024 | Reduce | 0.25 | 1.5434 | 0.38586 | H2 | 4 | Stable | 0.5 | 101 | 140 | 152 | 135.5 | 0.4 | 31 | 53 | 74 | 52.8333 | -20 | 48.9796 | 0 | -12
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Outstanding CRs | Person_693 | 2017-05-23 | 2019-02-21 01:00 | 0.7 | 0.77172 | 0.54021 | Accept | 0.3 | 0.77172 | 0.23152 | H3 | 3 | Stable | 0.9 | 107 | 139 | 146 | 134.8333 | 0.9 | 107 | 139 | 146 | 134.8333 | 0 | 57.1429 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Regulatory standards changes misunderstood | Person_693 | 2018-03-23 | 2018-11-18 01:00 | 0.3 | 1.3377 | 0.4013 | Reduce | 0.15 | 1.3377 | 0.20065 | H3 | 3 | Stable | 0.9 | 106 | 138 | 155 | 135.5 | 0.3 | 2 | 47 | 77 | 44.5 | 0 | 50 | 1 | 1.5
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Availability of key resource within Engineering | Person_693 | 2018-01-21 01:00 | 2019-05-23 | 0.1 | 1.7492 | 0.17492 | Accept | 0.1 | 1.7492 | 0.17492 | H3 | 3 | Improving | 0.5 | 101 | 124 | 141 | 123 | 0.5 | 101 | 124 | 141 | 123 | 0 | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 4 | 14. Other Risks and Contingencies | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_547 | 2018-09-19 01:00 | 2019-03-17 01:00 | 0.5 | 2.5081 | 1.2541 | Accept | 0.3 | 2.5081 | 0.75243 | H2 | 4 | Stable | 0.5 | 114 | 139 | 149 | 136.5 | 0.5 | 114 | 139 | 149 | 136.5 | 0 | 40 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | 1. Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_693 | 2017-04-22 | 2019-05-16 | 0.15 | 0.55736 | 0.083603 | Accept | 0.05 | 0.55736 | 0.027868 | H3 | 3 | Stable | 0.5 | 104 | 122 | 160 | 125.3333 | 0.5 | 104 | 122 | 160 | 125.3333 | 0 | 66.6667 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | 11. Supply chain | Production - Supplier Quality | Person_468 | 2017-05-23 | 2019-02-17 01:00 | 0.25 | 2.358 | 0.58951 | Reduce | 0.1 | 2.358 | 0.2358 | H3 | 3 | Improving | 0.9 | 118 | 138 | 159 | 138.1667 | 0.2 | 32 | 54 | 60 | 51.3333 | 0 | 60 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-015 | Project_096_Risk-015 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Ssub-system Accreditation | Person_623 | 2018-11-21 01:00 | 2019-03-22 | 0.15 | 7.6685 | 1.1503 | Reduce | 0.05 | 7.6685 | 0.38342 | H3 | 3 | Stable | 0.6 | 89 | 122 | 154 | 121.8333 | 0.3 | 8 | 51 | 72 | 47.3333 | 0 | 66.6667 | 1 | 2
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-005 | Project_096_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 13. Logistic support and Services | Availability of test site and Customer Furnished Equipment dependencies | Person_639 | 2019-03-02 01:00 | 2019-04-23 | 0.1 | 0 | 0 | Reduce | 0.1 | 0 | 0 | H3 | 3 | Stable | 0.7 | 109 | 135 | 154 | 133.8333 | 0.1 | 1 | 56 | 74 | 49.8333 |  | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-007 | Project_096_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Dependency | Person_623 | 2018-03-23 | 2018-11-07 01:00 | 0.4 | 0.95856 | 0.38342 | Reduce | 0.4 | 0.95856 | 0.38342 | H2 | 4 | Worsening | 0.6 | 83 | 130 | 158 | 126.8333 | 0.2 | 25 | 52 | 79 | 52 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-008 | Project_096_Risk-008 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Spiral Software update | Person_259 | 2018-02-20 01:00 | 2018-11-16 01:00 | 0.3 | 3.8342 | 1.1503 | Reduce | 0.2 | 3.8342 | 0.76685 | H2 | 4 | Stable | 0.5 | 120 | 121 | 150 | 125.6667 | 0.4 | 27 | 59 | 70 | 55.5 | 0 | 33.3333 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-009 | Project_096_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Assurance | Person_083 | 2018-10-05 01:00 | 2019-03-22 | 0.3 | 3.8342 | 1.1503 | Transfer | 0.25 | 3.8342 | 0.95856 | H2 | 4 | Stable | [10 empty] | 0 | 16.6667 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-001 | Project_096_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Suitably Qualified and experienced staff availability Resource availability | Person_083 | 2018-05-23 | 2018-12-22 01:00 | 0.3 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H2 | 4 | Improving | 0.7 | 100 | 128 | 145 | 126.1667 | 0.4 | 8 | 46 | 74 | 44.3333 |  | 33.3333 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-014 | Project_096_Risk-014 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Hosting issues | Person_259 | 2018-06-23 | 2018-12-16 01:00 | 0.15 | 3.0354 | 0.45532 | Reduce | 0.1 | 3.0354 | 0.30354 | H3 | 3 | Stable | 0.7 | 83 | 132 | 156 | 127.8333 | 0.1 | 35 | 42 | 75 | 46.3333 | 0 | 33.3333 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-119 | Project_029_Risk-119 | Opportunitity | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Not required to support on load & offload of Customer Furnished Equipmnet | Person_585 | 2017-05-23 | 2020-04-16 | 0.8 | 5.1334 | 4.1067 | Exploit | 0.8 | 3.4137 | 2.731 | H2 | 4 | Stable | [10 empty] | 33.5 | 0 | 0 | 20.1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H3 | 3 | 4. Customers | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_585 | 2017-09-22 01:00 | 2019-08-21 01:00 | 0.03 | 27.1644 | 0.81493 | Accept | 0.03 | 12.8336 | 0.38501 | H3 | 3 | Stable | 0.9 | 90 | 123 | 154 | 122.6667 | 0.9 | 90 | 123 | 154 | 122.6667 | 52.7559 | 0 | 0 | 31.6535
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2018-03-22 | 2019-07-21 | 0.25 | 0.7914 | 0.19785 | Reduce | 0.25 | 0.7914 | 0.19785 | H2 | 4 | Improving | 0.9 | 120 | 128 | 156 | 131.3333 | 0.3 | 29 | 49 | 74 | 49.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_585 | 2017-09-02 01:00 | 2020-04-26 | 0.1 | 6.4168 | 0.64168 | Transfer | 0.1 | 0 | 0 | H2 | 4 | Stable | [10 empty] | 100 | 0 | 0 | 60
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Sub-system FPGA | Person_332 | 2017-01-21 01:00 | 2019-05-16 | 0.4 | 1.5914 | 0.63655 | Reduce | 0.2 | 1.5914 | 0.31827 | H3 | 3 | Stable | 0.5 | 84 | 129 | 144 | 124 | 0.4 | 21 | 47 | 65 | 45.6667 | 0 | 50 | 1 | 1.5
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Additional effort for System HW/SW- System upgrade. | Person_199 | 2017-05-23 | 2019-09-18 01:00 | 0.3 | 2.5667 | 0.77001 | Reduce | 0.2 | 2.5667 | 0.51334 | H3 | 3 | Stable | 0.9 | 87 | 124 | 146 | 121.5 | 0.3 | 15 | 40 | 72 | 41.1667 | 0 | 33.3333 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Increase in Supply Chain Material Costs and Lead Times | Person_403 | 2018-04-22 | 2019-05-16 | 0.5 | 6.6521 | 3.326 | Accept | 0.5 | 6.6521 | 3.326 | H2 | 4 | Stable | 0.7 | 100 | 140 | 155 | 135.8333 | 0.7 | 100 | 140 | 155 | 135.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 0.5 | 3.5934 | 1.7967 | Reduce | 0.25 | 3.5934 | 0.89835 | H2 | 4 | Stable | 0.7 | 91 | 130 | 148 | 126.5 | 0.1 | 39 | 54 | 67 | 53.6667 | 0 | 50 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-08-14 | 0.25 | 4.2779 | 1.0695 | Accept | 0.25 | 4.2779 | 1.0695 | H2 | 4 | Stable | 0.7 | 109 | 134 | 147 | 132 | 0.7 | 109 | 134 | 147 | 132 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 0.3 | 2.5667 | 0.77001 | Accept | 0.2 | 2.5667 | 0.51334 | H3 | 3 | Stable | 0.5 | 111 | 136 | 151 | 134.3333 | 0.5 | 111 | 136 | 151 | 134.3333 | 0 | 33.3333 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Open | H2 | 4 | 12. Acquisition and offsets | Minimum Order Quantities | Person_403 | 2017-11-20 01:00 | 2019-05-16 | 0.2 | 1.925 | 0.38501 | Exploit | 0.2 | 1.925 | 0.38501 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 4 | 9. Hardware/Software development | Software delays Impacting schedule | Person_585 | 2017-10-21 01:00 | 2019-07-21 | 0.333 | 11.5502 | 3.8462 | Accept | 0.333 | 11.5502 | 3.8462 | H2 | 4 | Stable | 0.6 | 89 | 137 | 154 | 131.8333 | 0.6 | 89 | 137 | 154 | 131.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Penetration testing (of our SW) at the System level on product platform - performed by 3rd parties | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 0.4 | 0 | 0 | Transfer | 0.4 | 0 | 0 | H2 | 4 | Stable | [11 empty] | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Sub-system / product system accreditation hindered by Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 0.1 | 0.25667 | 0.025667 | Transfer | 0.1 | 0.25667 | 0.025667 | H3 | 3 | Stable | [10 empty] | 0 | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2018-03-22 | 2020-11-25 01:00 | 0.4 | 1.4673 | 0.58692 | Accept | 0.3 | 1.4673 | 0.44019 | H2 | 4 | Improving | 0.8 | 113 | 122 | 158 | 126.5 | 0.8 | 113 | 122 | 158 | 126.5 | 0 | 25 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_694 | 2017-05-23 | 2019-08-04 | 0.3 | 0 | 0 | Transfer | 0.1 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 66.6667 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2020-04-26 | 0.35 | 1.9208 | 0.67227 | Accept | 0.25 | 1.9208 | 0.48019 | H2 | 4 | Stable | 0.8 | 106 | 136 | 154 | 134 | 0.8 | 106 | 136 | 154 | 134 | 0 | 28.5714 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Functionality Test of system with a Test Box | Person_102 | 2018-03-22 | 2020-04-26 | 0.4 | 0.77001 | 0.30801 | Reduce | 0.3 | 0.77001 | 0.231 | H2 | 4 | Stable | 0.5 | 81 | 131 | 152 | 126.1667 | 0.1 | 11 | 50 | 76 | 47.8333 | 0 | 25 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | system - Integration - platform Installation Activities | Person_694 | 2018-02-20 01:00 | 2019-08-04 | 0.35 | 1.0267 | 0.35934 | Reduce | 0.25 | 1.0267 | 0.25667 | H2 | 4 | Stable | 0.8 | 87 | 127 | 148 | 123.8333 | 0.1 | 34 | 44 | 62 | 45.3333 | 0 | 28.5714 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 | 10. System Integration, Verification & Validation | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2020-09-19 01:00 | 0.2 | 1.54 | 0.30801 | Accept | 0.2 | 0.77001 | 0.154 | H3 | 3 | Stable | 0.8 | 85 | 131 | 141 | 125 | 0.8 | 85 | 131 | 141 | 125 | 50 | 0 | 0 | 30
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 4 | 6. Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2020-10-26 01:00 | 0.3 | 0.94968 | 0.28491 | Accept | 0.2 | 0.94968 | 0.18994 | H3 | 3 | Stable | 0.6 | 112 | 138 | 145 | 134.8333 | 0.6 | 112 | 138 | 145 | 134.8333 | 0 | 33.3333 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | RISK008 | Project_029_RISK008 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | Impact of sub-system Design Changes [product dependency] | Person_332 | 2016-09-20 01:00 | 2019-08-15 | 0.7 | 1.0695 | 0.74863 | Accept | 0.7 | 1.0695 | 0.74863 | H2 | 4 | Stable | 0.7 | 94 | 121 | 153 | 121.8333 | 0.7 | 94 | 121 | 153 | 121.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK051 | Project_042_RISK051 | Opportunitity | Project Contingency | Open | H1 | 5 | 5. Project Management | Main external component Refurbishment Savings | Person_455 | 2019-05-24 | 2020-09-20 01:00 | 0.8 | 9.3941 | 7.5153 | -- | 0.8 | 9.3941 | 7.5153 | H1 | 5 | Stable | [10 empty] | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK052 | Project_042_RISK052 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Additional Engineering Support to Industry | Person_134 | 2018-09-23 01:00 | 2019-10-22 01:00 | 0.5 | 1.1011 | 0.55057 | Accept | 0.5 | 1.1011 | 0.55057 | H2 | 4 | Stable | 0.7 | 111 | 126 | 143 | 126.3333 | 0.7 | 111 | 126 | 143 | 126.3333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK059 | Project_042_RISK059 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Additional Material Requirements. | Person_664 | 2018-09-23 01:00 | 2019-10-22 01:00 | 0.4 | 3.7576 | 1.5031 | Accept | 0.4 | 3.7576 | 1.5031 | H2 | 4 | Stable | 0.5 | 80 | 135 | 155 | 129.1667 | 0.5 | 80 | 135 | 155 | 129.1667 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK058 | Project_042_RISK058 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Special to type Test Equipment availability | Person_129 | 2018-09-23 01:00 | 2019-10-22 01:00 | 0.1 | 1.8788 | 0.18788 | Accept | 0.1 | 1.8788 | 0.18788 | H3 | 3 | Stable | 0.5 | 102 | 128 | 153 | 127.8333 | 0.5 | 102 | 128 | 153 | 127.8333 | 0 | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK054 | Project_042_RISK054 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Staff Retention/Business Priorities | Person_134 | 2018-09-23 01:00 | 2019-10-22 01:00 | 0.33 | 2.8421 | 0.93789 | Accept | 0.33 | 2.8421 | 0.93789 | H2 | 4 | Stable | 0.7 | 92 | 132 | 160 | 130 | 0.7 | 92 | 132 | 160 | 130 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK057 | Project_042_RISK057 | Threat | Project Contingency | Open | H1 | 5 | 8. System Engineering | Supplier Unplanned failures. | Person_129 | 2018-09-23 01:00 | 2019-10-22 01:00 | 0.6 | 2.4425 | 1.4655 | Accept | 0.6 | 2.4425 | 1.4655 | H1 | 5 | Stable | 0.8 | 107 | 132 | 150 | 130.8333 | 0.8 | 107 | 132 | 150 | 130.8333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK056 | Project_042_RISK056 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Long Lead times for supplier items | Person_134 | 2018-09-23 01:00 | 2019-10-22 01:00 | 0.3 | 4.2461 | 1.2738 | Accept | 0.3 | 4.2461 | 1.2738 | H2 | 4 | Stable | 0.5 | 91 | 124 | 145 | 122 | 0.5 | 91 | 124 | 145 | 122 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK014 | Project_083_RISK014 | Threat | Project Contingency | Open | H2 | 4 | 10. System Integration, Verification & Validation | System SW hosting Environment | Person_712 | 2018-02-20 01:00 | 2019-05-22 | 0.3 | 4.8313 | 1.4494 | Reduce | 0.25 | 4.8313 | 1.2078 | H2 | 4 | Stable | 0.9 | 92 | 128 | 159 | 127.1667 | 0.4 | 36 | 50 | 63 | 49.8333 | 0 | 16.6667 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK003 | Project_083_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supply Chain late delivery against Baseline Plan (Internal and External) | Person_391 | 2018-02-20 01:00 | 2019-05-16 | 0.6 | 2.3988 | 1.4393 | Reduce | 0.4 | 2.3988 | 0.95952 | H2 | 4 | Stable | 0.7 | 99 | 134 | 144 | 129.8333 | 0.1 | 16 | 42 | 65 | 41.5 | 0 | 33.3333 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK017 | Project_083_RISK017 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply Chain | Modules Obsolescence Resolution - Domestic Programmes | Person_712 | 2018-03-17 01:00 | 2019-01-20 01:00 | 0.15 | 10.3732 | 1.556 | Reduce | 0.15 | 10.3732 | 1.556 | H3 | 3 | Stable | 0.9 | 118 | 125 | 146 | 127.3333 | 0.3 | 6 | 41 | 66 | 39.3333 | 0 | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK016 | Project_083_RISK016 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Dependencies on product | Person_465 | 2018-03-17 01:00 | 2019-01-20 01:00 | 0.3 | 12.3182 | 3.6955 | Avoid | 0.15 | 12.3182 | 1.8477 | H2 | 4 | Stable | [10 empty] | 0 | 50 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK022 | Project_083_RISK022 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Availability of Engineering Resource | Person_712 | 2018-03-17 01:00 | 2019-01-20 01:00 | 0.3 | 0 | 0 | Reduce | 0.2 | 5.4459 | 1.0892 | H3 | 3 | Stable | 0.6 | 87 | 125 | 157 | 124 | 0.2 | 22 | 59 | 75 | 55.5 | -inf | 33.3333 | 1 | -inf
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK002 | Project_083_RISK002 | Threat | Project Contingency | Open | H2 | 4 | 11. Supply chain | Supply Chain Cost Increase - post Engineering design until completion of Procurement Phase | Person_391 | 2018-02-20 01:00 | 2019-01-20 01:00 | 0.65 | 5.8349 | 3.7927 | Reduce | 0.4 | 4.8385 | 1.9354 | H2 | 4 | Worsening | 0.7 | 97 | 122 | 141 | 121 | 0.2 | 33 | 53 | 78 | 53.8333 | 17.0777 | 38.4615 | 0 | 10.2466
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK024 | Project_083_RISK024 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Availability of Data to support Customer Deliverable updates aligned to Customer Deliverable delivery dates | Person_712 | 2018-03-17 01:00 | 2019-01-20 01:00 | 0.35 | 9.2062 | 3.2222 | Reduce | 0.25 | 7.754 | 1.9385 | H2 | 4 | Improving | 0.7 | 116 | 125 | 157 | 128.8333 | 0.2 | 1 | 53 | 78 | 48.5 | 15.7746 | 28.5714 | 0 | 9.4648
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK023 | Project_083_RISK023 | Threat | Project Contingency | Open | H3 | 3 | 8. System Engineering | Customer Deliverables - Read Across from product | Person_712 | 2018-03-17 01:00 | 2019-01-20 01:00 | 0.25 | 4.279 | 1.0697 | Reduce | 0.15 | 2.8267 | 0.42401 | H3 | 3 | Improving | 0.6 | 80 | 121 | 147 | 118.5 | 0.2 | 12 | 56 | 70 | 51 | 33.9395 | 40 | 0 | 20.3637
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK030 | Project_083_RISK030 | Threat | Project Contingency | Open | H3 | 3 | 14. Other Risks and Contingencies | Additional (unknown) support as result of sub-system learning within supply and customer | Person_644 | 2017-11-20 01:00 | 2020-11-19 01:00 | 0.4 | 6.7219 | 2.6887 | Accept | 0.4 | 6.7219 | 2.6887 | H3 | 3 | Stable | 0.6 | 80 | 126 | 145 | 121.5 | 0.6 | 80 | 126 | 145 | 121.5 | 0 | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | OP001 | Project_083_OP001 | Opportunitity | Project Contingency | Open | H2 | 4 | 11. Supply chain | Cross Project Procurement | Person_391 | 2018-02-20 01:00 | 2018-12-20 01:00 | 0.2 | 4.2141 | 0.84283 | Exploit | 0.7 | 4.2141 | 2.9499 | H3 | 3 | Stable | [10 empty] | 0 | -250 | 1 | -7.5
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE-10 | Project_067_SE-10 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Configuration baseline unstable for Platform | Person_327 | 2017-10-26 | 2018-08-18 | 0.5 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.5 | 118 | 126 | 143 | 127.5 | 0.1 | 6 | 43 | 71 | 41.5 |  | 60 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-001 | Project_067_Risk-001 | Threat | Project Contingency | Open | H3 | 3 | 5. Project Management | Lack of Technical Control plan | Person_327 | 2017-07-21 | 2018-09-20 | 1 | 0 | 0 | Reduce | 0.2 | 0 | 0 | H3 | 3 | Improving | 0.8 | 111 | 135 | 144 | 132.5 | 0.2 | 34 | 44 | 62 | 45.3333 |  | 80 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | P006 | Project_067_P006 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Complete SDRL deliverables in Schedule | Person_325 | 2018-07-07 | 2018-08-05 | 0.3 | 0 | 0 | Reduce | 0.5 | 0 | 0 | H2 | 4 | Stable | 0.8 | 84 | 136 | 151 | 129.8333 | 0.2 | 32 | 42 | 73 | 45.5 |  | -66.6667 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-004 | Project_067_Risk-004 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Creation of Serial Number for formal Software Releases | Person_327 | 2018-07-07 | 2018-10-21 | 1 | 0 | 0 | Reduce | 1 | 0 | 0 | H1 | 5 | Stable | 0.5 | 107 | 130 | 141 | 128 | 0.2 | 27 | 41 | 75 | 44.3333 |  | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE005 | Project_067_SE005 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Change in Delivery Approach | Person_327 | 2018-07-07 | 2018-08-05 | 0.8 | 0 | 0 | -- | 0.2 | 0 | 0 | H3 | 3 | Stable | [11 empty] | 75 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_021 | Project_086 | RISK003 | Project_086_RISK003 | Threat | Project Contingency | Open | H2 | 4 | 8. System Engineering | Qualification | Person_528 | 2017-11-22 01:00 | 2018-10-21 01:00 | 0.3 | 0.33844 | 0.10153 | Reduce | 0.2 | 0.33844 | 0.067689 | H2 | 4 | Worsening | 0.9 | 97 | 133 | 149 | 129.6667 | 0.4 | 4 | 55 | 63 | 47.8333 | 0 | 33.3333 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_021 | Project_086 | RISK006 | Project_086_RISK006 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Delivery Risk from Lack of Tool and Process Knowledge | Person_048 | 2018-09-21 01:00 | 2018-11-20 01:00 | 0.3 | 0.60436 | 0.18131 | Accept | 0.3 | 0.60436 | 0.18131 | H2 | 4 | Improving | 0.5 | 115 | 127 | 141 | 127.3333 | 0.5 | 115 | 127 | 141 | 127.3333 | 0 | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_021 | Project_086 | RISK008 | Project_086_RISK008 | Threat | Project Contingency | Open | H1 | 5 | 5. Project Management | Resource Deployment in Supplier | Person_048 | 2017-11-22 01:00 | 2018-11-22 01:00 | 0.5 | 0 | 0 | Accept | 0.5 | 0 | 0 | H1 | 5 | Improving | 0.6 | 97 | 128 | 160 | 128.1667 | 0.6 | 97 | 128 | 160 | 128.1667 |  | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--13 | Project_021_Risk--13 | Threat | Project Contingency | Open | H2 | 4 | 5. Project Management | Critical or Safety PR arises in Final build /Decision Point concludes new release req | Person_174 | 2018-02-20 01:00 | 2019-08-21 01:00 | 0.2 | 165.5424 | 33.1085 | Reduce | 0.1 | 165.5424 | 16.5542 | H2 | 4 | Stable | 0.9 | 111 | 128 | 146 | 128.1667 | 0.3 | 31 | 54 | 71 | 53 | 0 | 50 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | RISK018 | Project_029_RISK018 | Threat | Project Contingency | Open | H1 | 5 | 10. System Integration, Verification & Validation | Delays to platform Build Programme | Person_694 | 2018-10-22 01:00 | 2021-07-20 | 0.6 | 1.1122 | 0.66735 | Accept | 0.6 | 1.1122 | 0.66735 | H1 | 5 | Worsening | 0.9 | 108 | 133 | 155 | 132.5 | 0.9 | 108 | 133 | 155 | 132.5 | 0 | 0 | 0 | 0