%R | 504033 | 6359 | 125353 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ACRF4630 | Installation of Refrigerant Pipes | 8178 | 272 | 248 | 200 | 0 | 512 | 512 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-12 08:00 | 2014-11-09 17:00 |  | 2014-08-31 08:00 | 2014-09-28 17:00 | 2014-08-31 08:00 | 2014-09-28 17:00 | 2014-08-31 08:00 | 2014-09-28 17:00 | 2014-10-12 08:00 | 2014-11-09 17:00 |  | PT_Normal |  |  |  |  | XP/WM/6XRVWXebPeprJM7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33160 | N | N | 20 | ROOF |  | 125351 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 512 | LABOR- SUBCONTRACTOR
%R | 504034 | 6359 | 125353 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ACRF4635 | Installation of Condensing Unit | 8178 | 24 | 24 | 200 | 0 | 710 | 710 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-10-14 08:00 | 2014-11-11 17:00 | 2014-10-14 08:00 | 2014-11-11 17:00 | 2014-10-14 08:00 | 2014-11-11 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | QRbU/bBRTPSeizaBLCdV+A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33160 | N | N | 20 | ROOF |  | 125351 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 710 | LABOR- SUBCONTRACTOR
%R | 504035 | 6359 | 125354 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ACFF4615 | Installation AC Pipes | 8178 | 216 | 168 | 160 | 0 | 1222 | 1222 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-21 17:00 |  | 2014-07-26 08:00 | 2014-08-20 17:00 | 2014-07-26 08:00 | 2014-08-20 17:00 | 2014-07-26 08:00 | 2014-08-20 17:00 | 2014-08-30 08:00 | 2014-09-21 17:00 |  | PT_Normal |  |  |  |  | 2YGbfbwvQVSXhz4FdR1T7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33150 | N | N | 15 | FIRST FLOORS |  | 125351 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1222 | LABOR- SUBCONTRACTOR
%R | 504036 | 6359 | 125354 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ACFF4620 | Fixing of Ventilation Equipments | 8178 | 16 | 0 | 200 | 0 | 142 | 142 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-17 08:00 | 2014-10-18 17:00 |  | 2014-09-15 08:00 | 2014-10-15 17:00 | 2014-09-15 08:00 | 2014-10-15 17:00 | 2014-09-15 08:00 | 2014-10-15 17:00 | 2014-09-17 08:00 | 2014-10-18 17:00 |  | PT_Normal |  |  |  |  | IATrb7TvSzqKFj/VaaacAQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33150 | N | N | 15 | FIRST FLOORS |  | 125351 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 71 | LABOR- SUBCONTRACTOR
%R | 504037 | 6359 | 125354 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ACFF4625 | Fixing of Split AC | 8178 | 16 | 0 | 160 | 0 | 370 | 370 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-08 08:00 | 2014-11-02 17:00 |  | 2014-10-06 08:00 | 2014-10-30 17:00 | 2014-10-06 08:00 | 2014-10-30 17:00 | 2014-10-06 08:00 | 2014-10-30 17:00 | 2014-10-08 08:00 | 2014-11-02 17:00 |  | PT_Normal |  |  |  |  | pDwptm9XQQGsS66WJ2apeA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33150 | N | N | 15 | FIRST FLOORS |  | 125351 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 370 | LABOR- SUBCONTRACTOR
%R | 504038 | 6359 | 125357 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9AREL3665 | External Plastering | 8169 | 376 | 0 | 200 | 0 | 17843.75 | 17843.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-20 08:00 | 2014-10-20 17:00 |  | 2014-07-23 08:00 | 2014-08-24 17:00 | 2014-07-23 08:00 | 2014-08-24 17:00 | 2014-07-23 08:00 | 2014-08-24 17:00 | 2014-09-20 08:00 | 2014-10-20 17:00 |  | PT_Normal |  |  |  |  | OyrgRi2QRCaI5iEfZt96rA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33030 | N | N | 15 | ELEVATION |  | 125356 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 8921.875 | PLASTER MASON SK
%R | 504039 | 6359 | 125357 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9AREL3670 | External stone cladding works | 8170 | 392 | 0 | 160 | 0 | 1237.5 | 1237.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-12 08:00 | 2014-11-03 17:00 |  | 2014-08-13 08:00 | 2014-09-04 17:00 | 2014-08-13 08:00 | 2014-09-04 17:00 | 2014-08-13 08:00 | 2014-09-04 17:00 | 2014-10-12 08:00 | 2014-11-03 17:00 |  | PT_Normal |  |  |  |  | 85E8W7zpTsmXlS3fvs+XZg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33030 | N | N | 15 | ELEVATION |  | 125356 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1237.5 | TILE MASON SK
%R | 504040 | 6359 | 125357 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9AREL3680 | External Painting | 8178 | 392 | 392 | 160 | 0 | 4730 | 4730 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-23 08:00 | 2014-11-15 17:00 |  | 2014-08-25 08:00 | 2014-09-16 17:00 | 2014-08-25 08:00 | 2014-09-16 17:00 | 2014-08-25 08:00 | 2014-09-16 17:00 | 2014-10-23 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | 0fZ5l4YsRYSsJcinp+JNSw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33030 | N | N | 15 | ELEVATION |  | 125356 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 4730 | LABOR- SUBCONTRACTOR
%R | 504041 | 6359 | 125358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARRF3635 | Laying of Waterproofing Membrane | 8178 | 168 | 0 | 200 | 0 | 1423.5 | 1423.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-07 08:00 | 2014-10-05 17:00 |  | 2014-08-13 08:00 | 2014-09-10 17:00 | 2014-08-13 08:00 | 2014-09-10 17:00 | 2014-08-13 08:00 | 2014-09-10 17:00 | 2014-09-07 08:00 | 2014-10-05 17:00 |  | PT_Normal |  |  |  |  | OxuI+ykDSvWp++U12XAQQA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33020 | N | N | 10 | ROOF |  | 125356 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1423.5 | LABOR- SUBCONTRACTOR
%R | 504042 | 6359 | 125358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARRF3640 | Installation of Insulation & Protection | 8178 | 168 | 0 | 200 | 0 | 1760 | 1760 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-11 08:00 | 2014-10-12 17:00 |  | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-09-11 08:00 | 2014-10-12 17:00 |  | PT_Normal |  |  |  |  | na/LpHJhT6CSwTOJZvwfBA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33020 | N | N | 10 | ROOF |  | 125356 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1760 | LABOR- SUBCONTRACTOR
%R | 504043 | 6359 | 125358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 168 | 0 | 200 | 0 | 858 | 858 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-08-23 08:00 | 2014-09-20 17:00 | 2014-08-23 08:00 | 2014-09-20 17:00 | 2014-08-23 08:00 | 2014-09-20 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | PtBeBEEmQQ2lXHo/7t/8Ig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33020 | N | N | 10 | ROOF |  | 125356 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 858 | TILE MASON SK
%R | 504044 | 6359 | 125358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 168 | 0 | 160 | 0 | 770 | 770 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-12 08:00 | 2014-11-03 17:00 |  | 2014-09-15 08:00 | 2014-10-07 17:00 | 2014-09-15 08:00 | 2014-10-07 17:00 | 2014-09-15 08:00 | 2014-10-07 17:00 | 2014-10-12 08:00 | 2014-11-03 17:00 |  | PT_Normal |  |  |  |  | mllFZqabTjiNKrh9KuHiFA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33020 | N | N | 10 | ROOF |  | 125356 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 770 | LABOR- SUBCONTRACTOR
%R | 504045 | 6359 | 125358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 168 | 0 | 200 | 0 | 1307.25 | 1307.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-24 08:00 | 2014-10-25 17:00 |  | 2014-08-31 08:00 | 2014-09-28 17:00 | 2014-08-31 08:00 | 2014-09-28 17:00 | 2014-08-31 08:00 | 2014-09-28 17:00 | 2014-09-24 08:00 | 2014-10-25 17:00 |  | PT_Normal |  |  |  |  | YFC6c2I1Tj6lsuu9ND5ZUw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33020 | N | N | 10 | ROOF |  | 125356 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1307.25 | LABOR- SUBCONTRACTOR
%R | 504046 | 6359 | 125358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARRF3660 | Installation of Access Ladder | 8178 | 208 | 208 | 120 | 0 | 220 | 220 | 120 | 0 | 0 | 0 |  |  |  | 2014-10-29 08:00 | 2014-11-15 17:00 |  | 2014-09-27 08:00 | 2014-10-15 17:00 | 2014-09-27 08:00 | 2014-10-15 17:00 | 2014-09-27 08:00 | 2014-10-15 17:00 | 2014-10-29 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | N8yz9DfASIOPj1ELjwjxSg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33020 | N | N | 10 | ROOF |  | 125356 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 220 | LABOR- SUBCONTRACTOR
%R | 504047 | 6359 | 125358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARRF3630 | Leveling Screed for Waterproofing | 8164 | 168 | 0 | 200 | 0 | 1000 | 1000 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-03 08:00 | 2014-10-01 17:00 |  | 2014-08-10 08:00 | 2014-09-07 17:00 | 2014-08-10 08:00 | 2014-09-07 17:00 | 2014-08-10 08:00 | 2014-09-07 17:00 | 2014-09-03 08:00 | 2014-10-01 17:00 |  | PT_Normal |  |  |  |  | lSLrtpUIRTi8RN3t3G8OOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33020 | N | N | 10 | ROOF |  | 125356 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1000 | SCREED MASON SK
%R | 504048 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3000 | Block work | 8168 | 144 | 0 | 200 | 0 | 12172.25 | 12172.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-27 08:00 | 2014-06-24 17:00 |  | 2014-05-06 08:00 | 2014-06-03 17:00 | 2014-05-06 08:00 | 2014-06-03 17:00 | 2014-05-06 08:00 | 2014-06-03 17:00 | 2014-05-27 08:00 | 2014-06-24 17:00 |  | PT_Normal |  |  |  |  | Y988BpTgTwCeeXKiHdvU+A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 12172.25 | BLOCK MASON SK
%R | 504049 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3005 | Plastering work | 8169 | 144 | 0 | 200 | 0 | 17049 | 17049 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-18 08:00 | 2014-07-16 17:00 |  | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-06-18 08:00 | 2014-07-16 17:00 |  | PT_Normal |  |  |  |  | esIsjy03Sv+BaN/LyAIdQA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 17049 | PLASTER MASON SK
%R | 504050 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3010 | Flooring screed | 8164 | 208 | 64 | 168 | 0 | 1974.5 | 1974.5 | 168 | 0 | 0 | 0 |  |  |  | 2014-07-06 08:00 | 2014-07-29 17:00 |  | 2014-06-05 08:00 | 2014-06-29 17:00 | 2014-06-05 08:00 | 2014-06-29 17:00 | 2014-06-05 08:00 | 2014-06-29 17:00 | 2014-07-06 08:00 | 2014-07-29 17:00 |  | PT_Normal |  |  |  |  | VMFXEnnCR+SyIjRCO699Vw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1974.5 | SCREED MASON SK
%R | 504051 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 144 | 0 | 120 | 0 | 308 | 308 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-06 08:00 | 2014-07-22 17:00 |  | 2014-06-15 08:00 | 2014-07-01 17:00 | 2014-06-15 08:00 | 2014-07-01 17:00 | 2014-06-15 08:00 | 2014-07-01 17:00 | 2014-07-06 08:00 | 2014-07-22 17:00 |  | PT_Normal |  |  |  |  | gFRHKXksTFuiODGx8/CpBQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 308 | LABOR- SUBCONTRACTOR
%R | 504052 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3030 | Paint First coat | 8178 | 256 | 112 | 200 | 0 | 6781.5 | 6781.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-21 08:00 | 2014-08-21 17:00 |  | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-07-21 08:00 | 2014-08-21 17:00 |  | PT_Normal |  |  |  |  | mV9PDfO+SaGP8CvprA7Gww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 6781.5 | LABOR- SUBCONTRACTOR
%R | 504053 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3020 | Ceramic Wall Tiling | 8170 | 144 | 0 | 200 | 0 | 5534.75 | 5534.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-12 08:00 | 2014-08-12 17:00 |  | 2014-06-21 08:00 | 2014-07-19 17:00 | 2014-06-21 08:00 | 2014-07-19 17:00 | 2014-06-21 08:00 | 2014-07-19 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 |  | PT_Normal |  |  |  |  | Z+kmFIkzSk6P70D/+sPByA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 5534.75 | TILE MASON SK
%R | 504054 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3025 | Porcelain Tile flooring | 8170 | 144 | 0 | 200 | 0 | 2180.25 | 2180.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-17 08:00 | 2014-08-18 17:00 |  | 2014-06-26 08:00 | 2014-07-24 17:00 | 2014-06-26 08:00 | 2014-07-24 17:00 | 2014-06-26 08:00 | 2014-07-24 17:00 | 2014-07-17 08:00 | 2014-08-18 17:00 |  | PT_Normal |  |  |  |  | EmebZFTxSlay1l80bxa4AQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 2180.25 | TILE MASON SK
%R | 504055 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3040 | Cobble Tile flooring | 8170 | 168 | 0 | 120 | 0 | 925 | 925 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-20 08:00 | 2014-09-06 17:00 |  | 2014-07-23 08:00 | 2014-08-12 17:00 | 2014-07-23 08:00 | 2014-08-12 17:00 | 2014-07-23 08:00 | 2014-08-12 17:00 | 2014-08-20 08:00 | 2014-09-06 17:00 |  | PT_Normal |  |  |  |  | auq2gUqyT3eTe07hhKsm1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 925 | TILE MASON SK
%R | 504056 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 184 | 16 | 120 | 0 | 950 | 950 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-16 08:00 | 2014-09-01 17:00 |  | 2014-07-16 08:00 | 2014-08-05 17:00 | 2014-07-16 08:00 | 2014-08-05 17:00 | 2014-07-16 08:00 | 2014-08-05 17:00 | 2014-08-16 08:00 | 2014-09-01 17:00 |  | PT_Normal |  |  |  |  | xFmestIGQuC3sfcipLTUDA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 950 | TILE MASON SK
%R | 504057 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 168 | 0 | 160 | 0 | 1093.75 | 1093.75 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-28 08:00 | 2014-09-20 17:00 |  | 2014-07-31 08:00 | 2014-08-26 17:00 | 2014-07-31 08:00 | 2014-08-26 17:00 | 2014-07-31 08:00 | 2014-08-26 17:00 | 2014-08-28 08:00 | 2014-09-20 17:00 |  | PT_Normal |  |  |  |  | IJfP65BaSVO62CkwtOGMDA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1093.75 | GRANITE MASON SK
%R | 504058 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3045 | Fixing of Suspension systems | 8178 | 144 | 0 | 160 | 0 | 1818.81 | 1818.81 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-07 08:00 | 2014-08-30 17:00 |  | 2014-07-14 08:00 | 2014-08-09 17:00 | 2014-07-14 08:00 | 2014-08-09 17:00 | 2014-07-14 08:00 | 2014-08-09 17:00 | 2014-08-07 08:00 | 2014-08-30 17:00 |  | PT_Normal |  |  |  |  | fy4CnzzsQbubu+svVxU/Vg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1818.81 | LABOR- SUBCONTRACTOR
%R | 504059 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3055 | Aluminum tile false ceiling | 8178 | 168 | 24 | 200 | 0 | 187.5 | 187.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-19 08:00 | 2014-09-16 17:00 |  | 2014-07-22 08:00 | 2014-08-23 17:00 | 2014-07-22 08:00 | 2014-08-23 17:00 | 2014-07-22 08:00 | 2014-08-23 17:00 | 2014-08-19 08:00 | 2014-09-16 17:00 |  | PT_Normal |  |  |  |  | eJJfpG++T4KKk49Ti45hXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 93.75 | LABOR- SUBCONTRACTOR
%R | 504060 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3060 | Gypsum board false ceiling | 8178 | 144 | 0 | 200 | 0 | 1668.81 | 1668.81 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-19 08:00 | 2014-09-16 17:00 |  | 2014-07-26 08:00 | 2014-08-26 17:00 | 2014-07-26 08:00 | 2014-08-26 17:00 | 2014-07-26 08:00 | 2014-08-26 17:00 | 2014-08-19 08:00 | 2014-09-16 17:00 |  | PT_Normal |  |  |  |  | NLhTn3I+QsOZgUOwi+5r4A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 834.405 | LABOR- SUBCONTRACTOR
%R | 504061 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3065 | Wooden door & PVC Door | 8178 | 168 | 0 | 120 | 0 | 385 | 385 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-11 08:00 | 2014-09-28 17:00 |  | 2014-08-18 08:00 | 2014-09-03 17:00 | 2014-08-18 08:00 | 2014-09-03 17:00 | 2014-08-18 08:00 | 2014-09-03 17:00 | 2014-09-11 08:00 | 2014-09-28 17:00 |  | PT_Normal |  |  |  |  | AdMrTKf/SG+V5vyTKRBCuQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 385 | LABOR- SUBCONTRACTOR
%R | 504062 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3070 | Aluminum doors | 8178 | 168 | 0 | 120 | 0 | 220 | 220 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-17 08:00 | 2014-10-04 17:00 |  | 2014-08-24 08:00 | 2014-09-09 17:00 | 2014-08-24 08:00 | 2014-09-09 17:00 | 2014-08-24 08:00 | 2014-09-09 17:00 | 2014-09-17 08:00 | 2014-10-04 17:00 |  | PT_Normal |  |  |  |  | fZrZN3CNSZKksSFmZ3VM8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 220 | LABOR- SUBCONTRACTOR
%R | 504063 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3080 | Aluminum windows | 8178 | 248 | 80 | 160 | 0 | 202.5 | 202.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-06 08:00 | 2014-10-30 17:00 |  | 2014-08-31 08:00 | 2014-09-22 17:00 | 2014-08-31 08:00 | 2014-09-22 17:00 | 2014-08-31 08:00 | 2014-09-22 17:00 | 2014-10-06 08:00 | 2014-10-30 17:00 |  | PT_Normal |  |  |  |  | Nntu1wfhRsWzQDPHgzAAEA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 202.5 | LABOR- SUBCONTRACTOR
%R | 504064 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3075 | Carpentry & Joinery Works | 8178 | 168 | 0 | 160 | 0 | 715 | 715 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-23 08:00 | 2014-10-18 17:00 |  | 2014-08-30 08:00 | 2014-09-21 17:00 | 2014-08-30 08:00 | 2014-09-21 17:00 | 2014-08-30 08:00 | 2014-09-21 17:00 | 2014-09-23 08:00 | 2014-10-18 17:00 |  | PT_Normal |  |  |  |  | lQRQzEdpQ/+BKhEMZgAIyw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 715 | LABOR- SUBCONTRACTOR
%R | 504065 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3090 | Installation of Granite Counter Top | 8171 | 168 | 0 | 120 | 0 | 220 | 220 | 120 | 0 | 0 | 0 |  |  |  | 2014-10-06 08:00 | 2014-10-25 17:00 |  | 2014-09-11 08:00 | 2014-09-28 17:00 | 2014-09-11 08:00 | 2014-09-28 17:00 | 2014-09-11 08:00 | 2014-09-28 17:00 | 2014-10-06 08:00 | 2014-10-25 17:00 |  | PT_Normal |  |  |  |  | XepbsXcBSYaQj5DzdwVjtQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 220 | GRANITE MASON SK
%R | 504066 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3085 | S.S.Balustrade | 8178 | 208 | 40 | 160 | 0 | 328.5 | 328.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-07 08:00 | 2014-11-01 17:00 |  | 2014-09-07 08:00 | 2014-09-29 17:00 | 2014-09-07 08:00 | 2014-09-29 17:00 | 2014-09-07 08:00 | 2014-09-29 17:00 | 2014-10-07 08:00 | 2014-11-01 17:00 |  | PT_Normal |  |  |  |  | TpdCWl2bTnaqtz+ZR4UoCQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 328.5 | LABOR- SUBCONTRACTOR
%R | 504067 | 6359 | 125360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARGF3095 | Final Painting | 8178 | 168 | 168 | 200 | 0 | 6781.5 | 6781.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-09-21 08:00 | 2014-10-21 17:00 | 2014-09-21 08:00 | 2014-10-21 17:00 | 2014-09-21 08:00 | 2014-10-21 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | 0RM2vI35RWCTxiCNT6ON3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32980 | N | N | 10 | GROUND FLOOR |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 3390.75 | LABOR- SUBCONTRACTOR
%R | 504068 | 6359 | 125361 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARRF3600 | Block work | 8168 | 384 | 0 | 160 | 0 | 875 | 875 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-03 08:00 | 2014-09-25 17:00 |  | 2014-07-06 08:00 | 2014-07-28 17:00 | 2014-07-06 08:00 | 2014-07-28 17:00 | 2014-07-06 08:00 | 2014-07-28 17:00 | 2014-09-03 08:00 | 2014-09-25 17:00 |  | PT_Normal |  |  |  |  | 1M7YB5ArQ7+HklOjWYdLvA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33000 | N | N | 20 | ROOF |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 875 | BLOCK MASON SK
%R | 504069 | 6359 | 125361 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARRF3605 | Plastering work | 8169 | 384 | 0 | 160 | 0 | 2231.25 | 2231.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-11 08:00 | 2014-10-04 17:00 |  | 2014-07-14 08:00 | 2014-08-09 17:00 | 2014-07-14 08:00 | 2014-08-09 17:00 | 2014-07-14 08:00 | 2014-08-09 17:00 | 2014-09-11 08:00 | 2014-10-04 17:00 |  | PT_Normal |  |  |  |  | imWYgBqsSXyabTNVL4sjDA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33000 | N | N | 20 | ROOF |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 2231.25 | PLASTER MASON SK
%R | 504070 | 6359 | 125361 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARRF3610 | Flooring screed | 8164 | 424 | 0 | 120 | 0 | 170.5 | 170.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-10-01 08:00 | 2014-10-20 17:00 |  | 2014-07-28 08:00 | 2014-08-17 17:00 | 2014-07-28 08:00 | 2014-08-17 17:00 | 2014-07-28 08:00 | 2014-08-17 17:00 | 2014-10-01 08:00 | 2014-10-20 17:00 |  | PT_Normal |  |  |  |  | HmWLhy5YRrC8vsNPmMzNCw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33000 | N | N | 20 | ROOF |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 170.5 | SCREED MASON SK
%R | 504071 | 6359 | 125361 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARRF3695 | Painting -Storage area | 8178 | 424 | 0 | 160 | 0 | 2050 | 2050 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-12 08:00 | 2014-11-03 17:00 |  | 2014-08-09 08:00 | 2014-08-31 17:00 | 2014-08-09 08:00 | 2014-08-31 17:00 | 2014-08-09 08:00 | 2014-08-31 17:00 | 2014-10-12 08:00 | 2014-11-03 17:00 |  | PT_Normal |  |  |  |  | mzw0qAP8RoyGuYPBpjMs5Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33000 | N | N | 20 | ROOF |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 2050 | LABOR- SUBCONTRACTOR
%R | 504072 | 6359 | 125361 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARRF3620 | Epoxy Painting -Storage area | 8178 | 424 | 424 | 120 | 0 | 59.5 | 59.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-10-29 08:00 | 2014-11-15 17:00 |  | 2014-08-26 08:00 | 2014-09-11 17:00 | 2014-08-26 08:00 | 2014-09-11 17:00 | 2014-08-26 08:00 | 2014-09-11 17:00 | 2014-10-29 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | 9cks8qidQtqnkxBr1PEmfg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33000 | N | N | 20 | ROOF |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 59.5 | LABOR- SUBCONTRACTOR
%R | 504073 | 6359 | 125362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARFF3345 | Fixing of Suspension systems | 8178 | 0 | 0 | 160 | 0 | 1631.25 | 1631.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-31 08:00 | 2014-09-22 17:00 |  | 2014-08-31 08:00 | 2014-09-22 17:00 | 2014-08-31 08:00 | 2014-09-22 17:00 | 2014-08-31 08:00 | 2014-09-22 17:00 | 2014-08-31 08:00 | 2014-09-22 17:00 |  | PT_Normal |  |  |  |  | krRezLcsRNKmWpDm9tYSCw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32990 | N | N | 15 | FIRST FLOORS |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1631.25 | LABOR- SUBCONTRACTOR
%R | 504074 | 6359 | 125362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARFF3360 | Gypsum board false ceiling | 8178 | 0 | 0 | 200 | 0 | 1631.25 | 1631.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-07 08:00 | 2014-10-05 17:00 |  | 2014-09-07 08:00 | 2014-10-05 17:00 | 2014-09-07 08:00 | 2014-10-05 17:00 | 2014-09-07 08:00 | 2014-10-05 17:00 | 2014-09-07 08:00 | 2014-10-05 17:00 |  | PT_Normal |  |  |  |  | d9MtHR8nQGmB0CDiJbXFuA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32990 | N | N | 15 | FIRST FLOORS |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 1631.25 | LABOR- SUBCONTRACTOR
%R | 504075 | 6359 | 125362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARFF3365 | Wooden door | 8178 | 0 | 0 | 120 | 0 | 385 | 385 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-22 08:00 | 2014-10-08 17:00 |  | 2014-09-22 08:00 | 2014-10-08 17:00 | 2014-09-22 08:00 | 2014-10-08 17:00 | 2014-09-22 08:00 | 2014-10-08 17:00 | 2014-09-22 08:00 | 2014-10-08 17:00 |  | PT_Normal |  |  |  |  | lEdGnlW9RnipyKLWG18uZg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32990 | N | N | 15 | FIRST FLOORS |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 385 | LABOR- SUBCONTRACTOR
%R | 504076 | 6359 | 125362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARFF3370 | Aluminum Door | 8178 | 0 | 0 | 160 | 0 | 275 | 275 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-22 08:00 | 2014-10-16 17:00 |  | 2014-09-22 08:00 | 2014-10-16 17:00 | 2014-09-22 08:00 | 2014-10-16 17:00 | 2014-09-22 08:00 | 2014-10-16 17:00 | 2014-09-22 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | kbBycXN+TMyI7jhlPUTswA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32990 | N | N | 15 | FIRST FLOORS |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 275 | LABOR- SUBCONTRACTOR
%R | 504077 | 6359 | 125362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARFF3380 | Aluminum windows | 8178 | 32 | 32 | 160 | 0 | 202.5 | 202.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-04 08:00 | 2014-10-28 17:00 |  | 2014-09-29 08:00 | 2014-10-23 17:00 | 2014-09-29 08:00 | 2014-10-23 17:00 | 2014-09-29 08:00 | 2014-10-23 17:00 | 2014-10-04 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | 5UCOLe0KTOe2NYOqEllCCQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32990 | N | N | 15 | FIRST FLOORS |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 202.5 | LABOR- SUBCONTRACTOR
%R | 504078 | 6359 | 125362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARFF3375 | Carpentry & Joinery Works | 8178 | 0 | 0 | 200 | 0 | 1375 | 1375 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-28 08:00 | 2014-10-28 17:00 |  | 2014-09-28 08:00 | 2014-10-28 17:00 | 2014-09-28 08:00 | 2014-10-28 17:00 | 2014-09-28 08:00 | 2014-10-28 17:00 | 2014-09-28 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | u6YZq7oISAukNgAW1uDE5A |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32990 | N | N | 15 | FIRST FLOORS |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 687.5 | LABOR- SUBCONTRACTOR
%R | 504079 | 6359 | 125362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARFF3390 | Installation of Granite Counter Top | 8171 | 8 | 8 | 160 | 0 | 110 | 110 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-13 08:00 | 2014-11-04 17:00 |  | 2014-10-12 08:00 | 2014-11-03 17:00 | 2014-10-12 08:00 | 2014-11-03 17:00 | 2014-10-12 08:00 | 2014-11-03 17:00 | 2014-10-13 08:00 | 2014-11-04 17:00 |  | PT_Normal |  |  |  |  | USvVoopWTXOmWSn26fnldw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32990 | N | N | 15 | FIRST FLOORS |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 110 | GRANITE MASON SK
%R | 504080 | 6359 | 125362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARFF3385 | Handrail & Balustrade | 8178 | 0 | 0 | 160 | 0 | 984.75 | 984.75 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-12 08:00 | 2014-11-03 17:00 |  | 2014-10-12 08:00 | 2014-11-03 17:00 | 2014-10-12 08:00 | 2014-11-03 17:00 | 2014-10-12 08:00 | 2014-11-03 17:00 | 2014-10-12 08:00 | 2014-11-03 17:00 |  | PT_Normal |  |  |  |  | DCGAxFxmSq+LFjSMR7VX6A |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32990 | N | N | 15 | FIRST FLOORS |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 984.75 | LABOR- SUBCONTRACTOR
%R | 504081 | 6359 | 125362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARFF3395 | Final Painting | 8178 | 0 | 0 | 200 | 0 | 5928.18 | 5928.18 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-10-18 08:00 | 2014-11-15 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | Z25LA+pLRs6aFIq6kK5w9Q |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32990 | N | N | 15 | FIRST FLOORS |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 5928.18 | LABOR- SUBCONTRACTOR
%R | 504082 | 6359 | 125362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARFF3300 | Block work | 8168 | 0 | 0 | 200 | 0 | 7984.75 | 7984.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | PQlOtgtnSXSopkwmZZJKWw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32990 | N | N | 15 | FIRST FLOORS |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 7984.75 | BLOCK MASON SK
%R | 504083 | 6359 | 125362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARFF3305 | Plastering work | 8169 | 0 | 0 | 200 | 0 | 11124 | 11124 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-12 08:00 | 2014-08-12 17:00 |  | 2014-07-12 08:00 | 2014-08-12 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 |  | PT_Normal |  |  |  |  | VE20ydFvTiCcEUd12MYJfg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32990 | N | N | 15 | FIRST FLOORS |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 5562 | PLASTER MASON SK
%R | 504084 | 6359 | 125362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARFF3310 | Flooring screed | 8164 | 96 | 96 | 168 | 0 | 1520.75 | 1520.75 | 168 | 0 | 0 | 0 |  |  |  | 2014-08-06 08:00 | 2014-08-30 17:00 |  | 2014-07-20 08:00 | 2014-08-16 17:00 | 2014-07-20 08:00 | 2014-08-16 17:00 | 2014-07-20 08:00 | 2014-08-16 17:00 | 2014-08-06 08:00 | 2014-08-30 17:00 |  | PT_Normal |  |  |  |  | 8Vs4OIh3TTqsXlDIWr5NeQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32990 | N | N | 15 | FIRST FLOORS |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1520.75 | SCREED MASON SK
%R | 504085 | 6359 | 125362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARFF3315 | Wet area waterproofing | 8178 | 0 | 0 | 120 | 0 | 1518 | 1518 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-31 08:00 | 2014-08-20 17:00 |  | 2014-07-31 08:00 | 2014-08-20 17:00 | 2014-07-31 08:00 | 2014-08-20 17:00 | 2014-07-31 08:00 | 2014-08-20 17:00 | 2014-07-31 08:00 | 2014-08-20 17:00 |  | PT_Normal |  |  |  |  | bONMjO8cSEywkGqALcs3og |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32990 | N | N | 15 | FIRST FLOORS |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1518 | LABOR- SUBCONTRACTOR
%R | 504086 | 6359 | 125362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARFF3330 | Paint First coat | 8178 | 112 | 112 | 200 | 0 | 5928.18 | 5928.18 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-17 08:00 | 2014-09-14 17:00 |  | 2014-07-28 08:00 | 2014-08-28 17:00 | 2014-07-28 08:00 | 2014-08-28 17:00 | 2014-07-28 08:00 | 2014-08-28 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 |  | PT_Normal |  |  |  |  | 4wiVzD3XRXaByXkpmDeUaQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32990 | N | N | 15 | FIRST FLOORS |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 2964.09 | LABOR- SUBCONTRACTOR
%R | 504087 | 6359 | 125362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARFF3320 | Ceramic Wall Tiling | 8170 | 0 | 0 | 200 | 0 | 2372.25 | 2372.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-11 08:00 | 2014-09-08 17:00 |  | 2014-08-11 08:00 | 2014-09-08 17:00 | 2014-08-11 08:00 | 2014-09-08 17:00 | 2014-08-11 08:00 | 2014-09-08 17:00 | 2014-08-11 08:00 | 2014-09-08 17:00 |  | PT_Normal |  |  |  |  | Z8AfkQy0TL6OQduoP1k8vQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32990 | N | N | 15 | FIRST FLOORS |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 2372.25 | TILE MASON SK
%R | 504088 | 6359 | 125362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARFF3325 | Porcelain Tile flooring | 8170 | 0 | 0 | 200 | 0 | 2180.25 | 2180.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | 33KISCFuScOqUar0SDPbwg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32990 | N | N | 15 | FIRST FLOORS |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 2180.25 | TILE MASON SK
%R | 504089 | 6359 | 125362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARFF3335 | Slate Tile Flooring & Skirting | 8170 | 64 | 64 | 120 | 0 | 325 | 325 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-14 08:00 | 2014-09-30 17:00 |  | 2014-09-04 08:00 | 2014-09-21 17:00 | 2014-09-04 08:00 | 2014-09-21 17:00 | 2014-09-04 08:00 | 2014-09-21 17:00 | 2014-09-14 08:00 | 2014-09-30 17:00 |  | PT_Normal |  |  |  |  | Y7SL6aAEQpSegC/4hBwiIA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32990 | N | N | 15 | FIRST FLOORS |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 325 | TILE MASON SK
%R | 504090 | 6359 | 125362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ARFF3350 | Granite - Stair case flooring & Skirting | 8171 | 16 | 16 | 160 | 0 | 1093.75 | 1093.75 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-10-02 17:00 |  | 2014-09-08 08:00 | 2014-09-30 17:00 | 2014-09-08 08:00 | 2014-09-30 17:00 | 2014-09-08 08:00 | 2014-09-30 17:00 | 2014-09-10 08:00 | 2014-10-02 17:00 |  | PT_Normal |  |  |  |  | gBHFbHPZRcGQ46Ze85Eylg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32990 | N | N | 15 | FIRST FLOORS |  | 125359 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 1093.75 | GRANITE MASON SK
%R | 504091 | 6359 | 125365 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STFF2020 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 4476.5 | 4476.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-10 08:00 | 2014-05-08 17:00 |  | 2014-04-10 08:00 | 2014-05-08 17:00 | 2014-04-10 08:00 | 2014-05-08 17:00 | 2014-04-10 08:00 | 2014-05-08 17:00 | 2014-04-10 08:00 | 2014-05-08 17:00 |  | PT_Normal |  |  |  |  | v5nVaFh3Tkuba3/X7659Mw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32940 | N | N | 15 | FIRST FLOORS |  | 125364 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 4476.5 | STEEL FIXERS SK
%R | 504092 | 6359 | 125365 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STFF2025 | Column-Concrete | 8167 | 0 | 0 | 192 | 0 | 280 | 280 | 192 | 0 | 0 | 0 |  |  |  | 2014-04-22 08:00 | 2014-05-19 17:00 |  | 2014-04-22 08:00 | 2014-05-19 17:00 | 2014-04-22 08:00 | 2014-05-19 17:00 | 2014-04-22 08:00 | 2014-05-19 17:00 | 2014-04-22 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | 5sihZ6XSQVmVJQgDtIEqag |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32940 | N | N | 15 | FIRST FLOORS |  | 125364 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 280 | CONCRETE MASON SK
%R | 504093 | 6359 | 125365 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 20147.75 | 20147.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-07 08:00 | 2014-06-04 17:00 |  | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 |  | PT_Normal |  |  |  |  | 3043YnFhR3GdfmIUbs2g9w |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32940 | N | N | 15 | FIRST FLOORS |  | 125364 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 20147.75 | STEEL FIXERS SK
%R | 504094 | 6359 | 125365 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 0 | 0 | 112 | 0 | 1428 | 1428 | 112 | 0 | 0 | 0 |  |  |  | 2014-05-24 08:00 | 2014-06-08 17:00 |  | 2014-05-24 08:00 | 2014-06-08 17:00 | 2014-05-24 08:00 | 2014-06-08 17:00 | 2014-05-24 08:00 | 2014-06-08 17:00 | 2014-05-24 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | BUUb6esXS+ej47/XA3RFlA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32940 | N | N | 15 | FIRST FLOORS |  | 125364 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1428 | CONCRETE MASON SK
%R | 504095 | 6359 | 125366 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STRF2040 | Column-Rebar & Formwork | 8165 | 72 | 0 | 144 | 0 | 1506.75 | 1506.75 | 144 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-06-25 17:00 |  | 2014-05-26 08:00 | 2014-06-15 17:00 | 2014-05-26 08:00 | 2014-06-15 17:00 | 2014-05-26 08:00 | 2014-06-15 17:00 | 2014-06-05 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | whFwgYhZRreC0ljpjsWkUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32950 | N | N | 20 | ROOF |  | 125364 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1506.75 | STEEL FIXERS SK
%R | 504096 | 6359 | 125366 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STRF2045 | Column-Concrete | 8167 | 72 | 0 | 136 | 0 | 66.5 | 66.5 | 136 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-06-28 17:00 |  | 2014-05-29 08:00 | 2014-06-17 17:00 | 2014-05-29 08:00 | 2014-06-17 17:00 | 2014-05-29 08:00 | 2014-06-17 17:00 | 2014-06-09 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | SITPdw0rRayH0oxbkQDYMA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32950 | N | N | 20 | ROOF |  | 125364 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 66.5 | CONCRETE MASON SK
%R | 504097 | 6359 | 125366 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STRF2050 | Slab-Rebar & Formwork - Head Room | 8165 | 72 | 0 | 160 | 0 | 3416 | 3416 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-07-03 17:00 |  | 2014-06-01 08:00 | 2014-06-23 17:00 | 2014-06-01 08:00 | 2014-06-23 17:00 | 2014-06-01 08:00 | 2014-06-23 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 |  | PT_Normal |  |  |  |  | nPfax2qDTASdOFr+v0ND2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32950 | N | N | 20 | ROOF |  | 125364 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 3416 | STEEL FIXERS SK
%R | 504098 | 6359 | 125366 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STRF2055 | Slab-Concrete-Head room | 8167 | 72 | 0 | 104 | 0 | 315 | 315 | 104 | 0 | 0 | 0 |  |  |  | 2014-06-22 08:00 | 2014-07-06 17:00 |  | 2014-06-11 08:00 | 2014-06-25 17:00 | 2014-06-11 08:00 | 2014-06-25 17:00 | 2014-06-11 08:00 | 2014-06-25 17:00 | 2014-06-22 08:00 | 2014-07-06 17:00 |  | PT_Normal |  |  |  |  | NCXDOVeZT0Ca8m/f3nvNWA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32950 | N | N | 20 | ROOF |  | 125364 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 315 | CONCRETE MASON SK
%R | 504099 | 6359 | 125366 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STRF2060 | Construction of Parapets | 8168 | 416 | 0 | 200 | 0 | 2750 | 2750 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-17 08:00 | 2014-09-14 17:00 |  | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 |  | PT_Normal |  |  |  |  | 6QvvQm9fRcaJs1io+llWeA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32950 | N | N | 20 | ROOF |  | 125364 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 2750 | BLOCK MASON SK
%R | 504100 | 6359 | 125366 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STRF2065 | Construction of up stands/Plinth | 8165 | 416 | 176 | 200 | 0 | 693 | 693 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-23 08:00 | 2014-09-20 17:00 |  | 2014-06-19 08:00 | 2014-07-17 17:00 | 2014-06-19 08:00 | 2014-07-17 17:00 | 2014-06-19 08:00 | 2014-07-17 17:00 | 2014-08-23 08:00 | 2014-09-20 17:00 |  | PT_Normal |  |  |  |  | wfx6tmY6RYu0gu0ouysNdA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32950 | N | N | 20 | ROOF |  | 125364 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 693 | STEEL FIXERS SK
%R | 504101 | 6359 | 125367 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STGF2000 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 5057.5 | 5057.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-25 08:00 | 2014-03-25 17:00 |  | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 |  | PT_Normal |  |  |  |  | b/qL5hs6TRCvk/hwDjyVbQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32930 | N | N | 10 | GROUND FLOOR |  | 125364 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 2528.75 | STEEL FIXERS SK
%R | 504102 | 6359 | 125367 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STGF2005 | Column-Concrete | 8167 | 0 | 0 | 192 | 0 | 318.5 | 318.5 | 192 | 0 | 0 | 0 |  |  |  | 2014-03-06 08:00 | 2014-04-02 17:00 |  | 2014-03-06 08:00 | 2014-04-02 17:00 | 2014-03-06 08:00 | 2014-04-02 17:00 | 2014-03-06 08:00 | 2014-04-02 17:00 | 2014-03-06 08:00 | 2014-04-02 17:00 |  | PT_Normal |  |  |  |  | VXV1N2kPQFaMNRk8yjVDGg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32930 | N | N | 10 | GROUND FLOOR |  | 125364 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 318.5 | CONCRETE MASON SK
%R | 504103 | 6359 | 125367 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 21035 | 21035 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-19 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | f4FUiy8XRo+sfTPUOVACJw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32930 | N | N | 10 | GROUND FLOOR |  | 125364 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 21035 | STEEL FIXERS SK
%R | 504104 | 6359 | 125367 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 0 | 0 | 112 | 0 | 1617 | 1617 | 112 | 0 | 0 | 0 |  |  |  | 2014-04-07 08:00 | 2014-04-22 17:00 |  | 2014-04-07 08:00 | 2014-04-22 17:00 | 2014-04-07 08:00 | 2014-04-22 17:00 | 2014-04-07 08:00 | 2014-04-22 17:00 | 2014-04-07 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | mOtm1q8lQlWTNhGb0Csm5A |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32930 | N | N | 10 | GROUND FLOOR |  | 125364 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1617 | CONCRETE MASON SK
%R | 504105 | 6359 | 125369 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STUG1015 | Footing Waterproofing & Screed | 8164 | 0 | 0 | 200 | 0 | 719.5 | 719.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-02 08:00 | 2013-11-30 17:00 |  | 2013-11-02 08:00 | 2013-11-30 17:00 | 2013-11-02 08:00 | 2013-11-30 17:00 | 2013-11-02 08:00 | 2013-11-30 17:00 | 2013-11-02 08:00 | 2013-11-30 17:00 |  | PT_Normal |  |  |  |  | rF42Q3BZSLuomFLcJ2wD0Q |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32910 | N | N | 10 | UPTO GRADE SLAB |  | 125368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 719.5 | SCREED MASON SK
%R | 504106 | 6359 | 125369 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STUG1020 | Construction of foundations | 8165 | 0 | 0 | 160 | 0 | 9721.25 | 9721.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-17 08:00 | 2013-12-09 17:00 |  | 2013-11-17 08:00 | 2013-12-09 17:00 | 2013-11-17 08:00 | 2013-12-09 17:00 | 2013-11-17 08:00 | 2013-12-09 17:00 | 2013-11-17 08:00 | 2013-12-09 17:00 |  | PT_Normal |  |  |  |  | vuiD4bYFQau6ZmWK1KDkDA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32910 | N | N | 10 | UPTO GRADE SLAB |  | 125368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 9721.25 | STEEL FIXERS SK
%R | 504107 | 6359 | 125369 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STUG1030 | Waterproofing Footing & Neck Column | 8178 | 0 | 0 | 200 | 0 | 643.5 | 643.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-05 08:00 | 2014-01-04 17:00 |  | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 |  | PT_Normal |  |  |  |  | 38TZvIWaRamkrNPGdRkrcA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32910 | N | N | 10 | UPTO GRADE SLAB |  | 125368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 643.5 | LABOR- SUBCONTRACTOR
%R | 504108 | 6359 | 125369 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 0 | 0 | 200 | 0 | 1095 | 1095 | 200 | 825 | 0 | 825 |  |  |  | 2013-12-21 08:00 | 2014-01-18 17:00 |  | 2013-12-21 08:00 | 2014-01-18 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | 6TCG4T72Tc6WGoMCH8KBwg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32910 | N | N | 10 | UPTO GRADE SLAB |  | 125368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1095 | LABOR - CIVIL
%R | 504109 | 6359 | 125369 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STUG1040 | Construction of Grade Beams | 8163 | 0 | 0 | 200 | 0 | 9462.25 | 9462.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-06 08:00 | 2014-02-03 17:00 |  | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 |  | PT_Normal |  |  |  |  | nQqvmypPT+6WJBP1x318wQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32910 | N | N | 10 | UPTO GRADE SLAB |  | 125368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 9462.25 | BLINDING MASON SK
%R | 504110 | 6359 | 125369 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STUG1045 | Construction of slab on grade | 8163 | 0 | 0 | 200 | 0 | 5529 | 5529 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-08 08:00 | 2014-03-09 17:00 |  | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 |  | PT_Normal |  |  |  |  | 7wlbu3LRQAuMfJ3u8NWkNA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32910 | N | N | 10 | UPTO GRADE SLAB |  | 125368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 2764.5 | BLINDING MASON SK
%R | 504111 | 6359 | 125369 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STUG1025 | Construction of neck of columns | 8165 | 0 | 0 | 200 | 0 | 2007.25 | 2007.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-26 08:00 | 2013-12-25 17:00 |  | 2013-11-26 08:00 | 2013-12-25 17:00 | 2013-11-26 08:00 | 2013-12-25 17:00 | 2013-11-26 08:00 | 2013-12-25 17:00 | 2013-11-26 08:00 | 2013-12-25 17:00 |  | PT_Normal |  |  |  |  | VdHqIcp1SqKuD6WLpKKshg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32910 | N | N | 10 | UPTO GRADE SLAB |  | 125368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 2007.25 | STEEL FIXERS SK
%R | 504112 | 6359 | 125369 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STUG1000 | Footing Excavation | 8177 | 0 | 0 | 200 | 0 | 1394 | 1394 | 200 | 656 | 0 | 656 |  |  |  | 2013-10-09 08:00 | 2013-11-09 17:00 |  | 2013-10-09 08:00 | 2013-11-09 17:00 | 2013-10-09 08:00 | 2013-11-09 17:00 | 2013-10-09 08:00 | 2013-11-09 17:00 | 2013-10-09 08:00 | 2013-11-09 17:00 |  | PT_Normal |  |  |  |  | d4YdjpulSyquhbFWYANqzg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32910 | N | N | 10 | UPTO GRADE SLAB |  | 125368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 697 | LABOR - CIVIL
%R | 504113 | 6359 | 125369 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STUG1005 | Footing Antitermite | 8178 | 0 | 0 | 184 | 0 | 1980 | 1980 | 184 | 0 | 0 | 0 |  |  |  | 2013-10-23 08:00 | 2013-11-18 17:00 |  | 2013-10-23 08:00 | 2013-11-18 17:00 | 2013-10-23 08:00 | 2013-11-18 17:00 | 2013-10-23 08:00 | 2013-11-18 17:00 | 2013-10-23 08:00 | 2013-11-18 17:00 |  | PT_Normal |  |  |  |  | pJ9REf5IQ1ydmgXMCAJ7mg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32910 | N | N | 10 | UPTO GRADE SLAB |  | 125368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1980 | LABOR- SUBCONTRACTOR
%R | 504114 | 6359 | 125369 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9STUG1010 | Footing Blinding | 8163 | 0 | 0 | 184 | 0 | 994 | 994 | 184 | 0 | 0 | 0 |  |  |  | 2013-10-27 08:00 | 2013-11-21 17:00 |  | 2013-10-27 08:00 | 2013-11-21 17:00 | 2013-10-27 08:00 | 2013-11-21 17:00 | 2013-10-27 08:00 | 2013-11-21 17:00 | 2013-10-27 08:00 | 2013-11-21 17:00 |  | PT_Normal |  |  |  |  | Mofso5rOST6h219Y+TtuKg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32910 | N | N | 10 | UPTO GRADE SLAB |  | 125368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 994 | BLINDING MASON SK
%R | 504115 | 6359 | 125373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STUG1000 | Footing Excavation | 8177 | 0 | 0 | 200 | 0 | 1114 | 1114 | 200 | 524 | 0 | 524 |  |  |  | 2013-07-10 08:00 | 2013-08-07 17:00 |  | 2013-07-10 08:00 | 2013-08-07 17:00 | 2013-07-10 08:00 | 2013-08-07 17:00 | 2013-07-10 08:00 | 2013-08-07 17:00 | 2013-07-10 08:00 | 2013-08-07 17:00 |  | PT_Normal |  |  |  |  | EODDAwNvRvOmb4VHlnPaig |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31830 | N | N | 10 | UPTO GRADE SLAB |  | 125372 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 1114 | LABOR - CIVIL
%R | 504116 | 6359 | 125373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STUG1005 | Footing Antitermite | 8178 | 0 | 0 | 184 | 0 | 1584 | 1584 | 184 | 0 | 0 | 0 |  |  |  | 2013-07-22 08:00 | 2013-08-20 17:00 |  | 2013-07-22 08:00 | 2013-08-20 17:00 | 2013-07-22 08:00 | 2013-08-20 17:00 | 2013-07-22 08:00 | 2013-08-20 17:00 | 2013-07-22 08:00 | 2013-08-20 17:00 |  | PT_Normal |  |  |  |  | i4Xa2ETASRWXtc0qUko2ew |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31830 | N | N | 10 | UPTO GRADE SLAB |  | 125372 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 1584 | LABOR- SUBCONTRACTOR
%R | 504117 | 6359 | 125373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STUG1010 | Footing Blinding | 8163 | 0 | 0 | 184 | 0 | 794.5 | 794.5 | 184 | 0 | 0 | 0 |  |  |  | 2013-07-25 08:00 | 2013-08-24 17:00 |  | 2013-07-25 08:00 | 2013-08-24 17:00 | 2013-07-25 08:00 | 2013-08-24 17:00 | 2013-07-25 08:00 | 2013-08-24 17:00 | 2013-07-25 08:00 | 2013-08-24 17:00 |  | PT_Normal |  |  |  |  | 7M+DmV5uQAeVtlzr6sra9A |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31830 | N | N | 10 | UPTO GRADE SLAB |  | 125372 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 794.5 | BLINDING MASON SK
%R | 504118 | 6359 | 125373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STUG1015 | Footing Waterproofing & Screed | 8164 | 0 | 0 | 200 | 0 | 574.75 | 574.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-31 08:00 | 2013-09-01 17:00 |  | 2013-07-31 08:00 | 2013-09-01 17:00 | 2013-07-31 08:00 | 2013-09-01 17:00 | 2013-07-31 08:00 | 2013-09-01 17:00 | 2013-07-31 08:00 | 2013-09-01 17:00 |  | PT_Normal |  |  |  |  | 4OSagSOBTRyvFH/DeswHvw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31830 | N | N | 10 | UPTO GRADE SLAB |  | 125372 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 287.375 | SCREED MASON SK
%R | 504119 | 6359 | 125373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STUG1020 | Construction of foundations | 8165 | 0 | 0 | 160 | 0 | 7778.75 | 7778.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-08-19 08:00 | 2013-09-10 17:00 |  | 2013-08-19 08:00 | 2013-09-10 17:00 | 2013-08-19 08:00 | 2013-09-10 17:00 | 2013-08-19 08:00 | 2013-09-10 17:00 | 2013-08-19 08:00 | 2013-09-10 17:00 |  | PT_Normal |  |  |  |  | xEAfFp68RTK0jyiK6ECm3Q |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31830 | N | N | 10 | UPTO GRADE SLAB |  | 125372 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 7778.75 | STEEL FIXERS SK
%R | 504120 | 6359 | 125373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STUG1025 | Construction of neck of columns | 8165 | 0 | 0 | 200 | 0 | 1606.5 | 1606.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-28 08:00 | 2013-09-25 17:00 |  | 2013-08-28 08:00 | 2013-09-25 17:00 | 2013-08-28 08:00 | 2013-09-25 17:00 | 2013-08-28 08:00 | 2013-09-25 17:00 | 2013-08-28 08:00 | 2013-09-25 17:00 |  | PT_Normal |  |  |  |  | TO4YeJw8QEiz+GcWIIJe+Q |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31830 | N | N | 10 | UPTO GRADE SLAB |  | 125372 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 1606.5 | STEEL FIXERS SK
%R | 504121 | 6359 | 125373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STUG1030 | Waterproofing Footing & Neck Column | 8178 | 0 | 0 | 200 | 0 | 516 | 516 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-07 08:00 | 2013-10-05 17:00 |  | 2013-09-07 08:00 | 2013-10-05 17:00 | 2013-09-07 08:00 | 2013-10-05 17:00 | 2013-09-07 08:00 | 2013-10-05 17:00 | 2013-09-07 08:00 | 2013-10-05 17:00 |  | PT_Normal |  |  |  |  | DGbhEloiRbOSgW5KuOA/zg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31830 | N | N | 10 | UPTO GRADE SLAB |  | 125372 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 516 | LABOR- SUBCONTRACTOR
%R | 504122 | 6359 | 125373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 0 | 0 | 200 | 0 | 1041 | 1041 | 200 | 825 | 0 | 825 |  |  |  | 2013-09-21 08:00 | 2013-10-21 17:00 |  | 2013-09-21 08:00 | 2013-10-21 17:00 | 2013-09-21 08:00 | 2013-10-21 17:00 | 2013-09-21 08:00 | 2013-10-21 17:00 | 2013-09-21 08:00 | 2013-10-21 17:00 |  | PT_Normal |  |  |  |  | uRT9cBm/R+OxuvJFQXiXrQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31830 | N | N | 10 | UPTO GRADE SLAB |  | 125372 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 520.5 | LABOR - CIVIL
%R | 504123 | 6359 | 125373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STUG1040 | Construction of Grade Beams | 8163 | 0 | 0 | 200 | 0 | 7568.75 | 7568.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-07 08:00 | 2013-11-06 17:00 |  | 2013-10-07 08:00 | 2013-11-06 17:00 | 2013-10-07 08:00 | 2013-11-06 17:00 | 2013-10-07 08:00 | 2013-11-06 17:00 | 2013-10-07 08:00 | 2013-11-06 17:00 |  | PT_Normal |  |  |  |  | u0mqIas0QZqYp3mWEvo4bQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31830 | N | N | 10 | UPTO GRADE SLAB |  | 125372 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 7568.75 | BLINDING MASON SK
%R | 504124 | 6359 | 125373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STUG1045 | Construction of slab on grade | 8163 | 0 | 0 | 200 | 0 | 4422 | 4422 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-11 08:00 | 2013-12-09 17:00 |  | 2013-11-11 08:00 | 2013-12-09 17:00 | 2013-11-11 08:00 | 2013-12-09 17:00 | 2013-11-11 08:00 | 2013-12-09 17:00 | 2013-11-11 08:00 | 2013-12-09 17:00 |  | PT_Normal |  |  |  |  | C0EWmawaQMuqNF4g++6EnA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31830 | N | N | 10 | UPTO GRADE SLAB |  | 125372 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 4422 | BLINDING MASON SK
%R | 504125 | 6359 | 125375 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STRF2040 | Column-Rebar & Formwork | 8165 | 64 | 0 | 144 | 0 | 1205.75 | 1205.75 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-04 08:00 | 2014-03-24 17:00 |  | 2014-02-23 08:00 | 2014-03-15 17:00 | 2014-02-23 08:00 | 2014-03-15 17:00 | 2014-02-23 08:00 | 2014-03-15 17:00 | 2014-03-04 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | vWjqct22TpqCWs5pmWQkGw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31870 | N | N | 20 | ROOF |  | 125374 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1205.75 | STEEL FIXERS SK
%R | 504126 | 6359 | 125375 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STRF2045 | Column-Concrete | 8167 | 64 | 0 | 136 | 0 | 52.5 | 52.5 | 136 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-26 17:00 |  | 2014-02-26 08:00 | 2014-03-17 17:00 | 2014-02-26 08:00 | 2014-03-17 17:00 | 2014-02-26 08:00 | 2014-03-17 17:00 | 2014-03-08 08:00 | 2014-03-26 17:00 |  | PT_Normal |  |  |  |  | DOHozTGKQMW4dxeLJIti5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31870 | N | N | 20 | ROOF |  | 125374 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 52.5 | CONCRETE MASON SK
%R | 504127 | 6359 | 125375 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STRF2050 | Slab-Rebar & Formwork - Head Room | 8165 | 64 | 0 | 160 | 0 | 2735.25 | 2735.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-10 08:00 | 2014-04-01 17:00 |  | 2014-03-01 08:00 | 2014-03-23 17:00 | 2014-03-01 08:00 | 2014-03-23 17:00 | 2014-03-01 08:00 | 2014-03-23 17:00 | 2014-03-10 08:00 | 2014-04-01 17:00 |  | PT_Normal |  |  |  |  | AMWIyHK8QUCnIHdZH6M3Ww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31870 | N | N | 20 | ROOF |  | 125374 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 2735.25 | STEEL FIXERS SK
%R | 504128 | 6359 | 125375 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STRF2055 | Slab-Concrete-Head room | 8167 | 64 | 0 | 104 | 0 | 252 | 252 | 104 | 0 | 0 | 0 |  |  |  | 2014-03-20 08:00 | 2014-04-03 17:00 |  | 2014-03-11 08:00 | 2014-03-25 17:00 | 2014-03-11 08:00 | 2014-03-25 17:00 | 2014-03-11 08:00 | 2014-03-25 17:00 | 2014-03-20 08:00 | 2014-04-03 17:00 |  | PT_Normal |  |  |  |  | JnjoEeBCTg+PQPhYGkKm5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31870 | N | N | 20 | ROOF |  | 125374 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 252 | CONCRETE MASON SK
%R | 504129 | 6359 | 125375 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STRF2060 | Construction of Parapets | 8168 | 448 | 32 | 200 | 0 | 2200 | 2200 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-18 08:00 | 2014-06-15 17:00 |  | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-05-18 08:00 | 2014-06-15 17:00 |  | PT_Normal |  |  |  |  | CjC1W1rGRjemyp/sX70G4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31870 | N | N | 20 | ROOF |  | 125374 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 2200 | BLOCK MASON SK
%R | 504130 | 6359 | 125375 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STRF2065 | Construction of up stands/Plinth | 8165 | 416 | 0 | 200 | 0 | 554.75 | 554.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-24 08:00 | 2014-06-21 17:00 |  | 2014-03-24 08:00 | 2014-04-21 17:00 | 2014-03-24 08:00 | 2014-04-21 17:00 | 2014-03-24 08:00 | 2014-04-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 |  | PT_Normal |  |  |  |  | ww349yC1TgqYb3QOIsb1gQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31870 | N | N | 20 | ROOF |  | 125374 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 554.75 | STEEL FIXERS SK
%R | 504131 | 6359 | 125376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 16 | 0 | 112 | 0 | 1295 | 1295 | 112 | 0 | 0 | 0 |  |  |  | 2014-01-09 08:00 | 2014-01-25 17:00 |  | 2014-01-07 08:00 | 2014-01-22 17:00 | 2014-01-07 08:00 | 2014-01-22 17:00 | 2014-01-07 08:00 | 2014-01-22 17:00 | 2014-01-09 08:00 | 2014-01-25 17:00 |  | PT_Normal |  |  |  |  | jhAIDYkaTI2nITEfa7osEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31850 | N | N | 10 | GROUND FLOOR |  | 125374 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1295 | CONCRETE MASON SK
%R | 504132 | 6359 | 125376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STGF2000 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 4046 | 4046 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-27 08:00 | 2013-12-26 17:00 |  | 2013-11-27 08:00 | 2013-12-26 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 |  | PT_Normal |  |  |  |  | HiFV7O9NTZ+527HvGUtNIw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31850 | N | N | 10 | GROUND FLOOR |  | 125374 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 4046 | STEEL FIXERS SK
%R | 504133 | 6359 | 125376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STGF2005 | Column-Concrete | 8167 | 16 | 0 | 192 | 0 | 255.5 | 255.5 | 192 | 0 | 0 | 0 |  |  |  | 2013-12-08 08:00 | 2014-01-05 17:00 |  | 2013-12-05 08:00 | 2014-01-02 17:00 | 2013-12-05 08:00 | 2014-01-02 17:00 | 2013-12-05 08:00 | 2014-01-02 17:00 | 2013-12-08 08:00 | 2014-01-05 17:00 |  | PT_Normal |  |  |  |  | 7s4rmbD6QCyho+kgQ50oyA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31850 | N | N | 10 | GROUND FLOOR |  | 125374 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 255.5 | CONCRETE MASON SK
%R | 504134 | 6359 | 125376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 16 | 0 | 200 | 0 | 16829.75 | 16829.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-24 08:00 | 2014-01-21 17:00 |  | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 |  | PT_Normal |  |  |  |  | 9CaLrmvyS6KTLtT4mnz/mA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31850 | N | N | 10 | GROUND FLOOR |  | 125374 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 16829.75 | STEEL FIXERS SK
%R | 504135 | 6359 | 125377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STFF2020 | Column-Rebar & Formwork | 8165 | 16 | 0 | 200 | 0 | 3580.5 | 3580.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-12 08:00 | 2014-02-09 17:00 |  | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-01-12 08:00 | 2014-02-09 17:00 |  | PT_Normal |  |  |  |  | Wvlg9pCsTkisk0zEeEQ5uw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31860 | N | N | 15 | FIRST FLOORS |  | 125374 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 3580.5 | STEEL FIXERS SK
%R | 504136 | 6359 | 125377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STFF2025 | Column-Concrete | 8167 | 32 | 0 | 192 | 0 | 224 | 224 | 192 | 0 | 0 | 0 |  |  |  | 2014-01-23 08:00 | 2014-02-20 17:00 |  | 2014-01-19 08:00 | 2014-02-16 17:00 | 2014-01-19 08:00 | 2014-02-16 17:00 | 2014-01-19 08:00 | 2014-02-16 17:00 | 2014-01-23 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | ZxKMNEWdRrqSQ4HuuG/APw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31860 | N | N | 15 | FIRST FLOORS |  | 125374 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 224 | CONCRETE MASON SK
%R | 504137 | 6359 | 125377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 32 | 0 | 200 | 0 | 16119.25 | 16119.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-08 08:00 | 2014-03-09 17:00 |  | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 |  | PT_Normal |  |  |  |  | LmL3GPXOQkapj2nqsendUQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31860 | N | N | 15 | FIRST FLOORS |  | 125374 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 8059.625 | STEEL FIXERS SK
%R | 504138 | 6359 | 125377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 32 | 0 | 112 | 0 | 1141 | 1141 | 112 | 0 | 0 | 0 |  |  |  | 2014-02-25 08:00 | 2014-03-12 17:00 |  | 2014-02-20 08:00 | 2014-03-08 17:00 | 2014-02-20 08:00 | 2014-03-08 17:00 | 2014-02-20 08:00 | 2014-03-08 17:00 | 2014-02-25 08:00 | 2014-03-12 17:00 |  | PT_Normal |  |  |  |  | i7kOFepvQliApsirTG8P9A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31860 | N | N | 15 | FIRST FLOORS |  | 125374 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1141 | CONCRETE MASON SK
%R | 504139 | 6359 | 125378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 0 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | D0Ef6cslTLqlYJzLpwZL9Q |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32150 | N | N | 30 | TESTING AND COMMISSIONING |  | 125370 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 504140 | 6359 | 125378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | uw+e0t1yQHqiJTuzuAKepw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32150 | N | N | 30 | TESTING AND COMMISSIONING |  | 125370 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 504141 | 6359 | 125378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | D0PyQZajQP2UGSjAFrgW9Q |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32150 | N | N | 30 | TESTING AND COMMISSIONING |  | 125370 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 504142 | 6359 | 125380 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6WEEX5030 | Excavation | 8177 | 264 | 0 | 160 | 0 | 64 | 64 | 160 | 40 | 0 | 40 |  |  |  | 2014-05-29 08:00 | 2014-06-21 17:00 |  | 2014-04-21 08:00 | 2014-05-13 17:00 | 2014-04-21 08:00 | 2014-05-13 17:00 | 2014-04-21 08:00 | 2014-05-13 17:00 | 2014-05-29 08:00 | 2014-06-21 17:00 |  | PT_Normal |  |  |  |  | BACBy+1YTNCxDSX2O4ELPA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32120 | N | N | 15 | WATER TANK ENCLOSURE |  | 125379 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 64 | LABOR - CIVIL
%R | 504143 | 6359 | 125380 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6WEEX5035 | Construction of Raft | 8165 | 264 | 0 | 200 | 0 | 840 | 840 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-04 08:00 | 2014-07-02 17:00 |  | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-06-04 08:00 | 2014-07-02 17:00 |  | PT_Normal |  |  |  |  | Kqd97/5rR+Wje4IGevb4GQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32120 | N | N | 15 | WATER TANK ENCLOSURE |  | 125379 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 840 | STEEL FIXERS SK
%R | 504144 | 6359 | 125380 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6WEEX5040 | Block works & Plastering | 8168 | 264 | 0 | 200 | 0 | 512 | 512 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-14 08:00 | 2014-07-12 17:00 |  | 2014-05-06 08:00 | 2014-06-03 17:00 | 2014-05-06 08:00 | 2014-06-03 17:00 | 2014-05-06 08:00 | 2014-06-03 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 |  | PT_Normal |  |  |  |  | PCpsR42lS1Cfg+h2YbAX1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32120 | N | N | 15 | WATER TANK ENCLOSURE |  | 125379 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 512 | BLOCK MASON SK
%R | 504145 | 6359 | 125380 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6WEEX5045 | Flooring & Painting | 8178 | 264 | 112 | 200 | 0 | 232 | 232 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-21 08:00 | 2014-07-19 17:00 |  | 2014-05-13 08:00 | 2014-06-10 17:00 | 2014-05-13 08:00 | 2014-06-10 17:00 | 2014-05-13 08:00 | 2014-06-10 17:00 | 2014-06-21 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | RNVSF7+kTeugKLbx9QOIRQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32120 | N | N | 15 | WATER TANK ENCLOSURE |  | 125379 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 232 | LABOR- SUBCONTRACTOR
%R | 504146 | 6359 | 125380 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6WEEX5050 | Installation of Steel Gate | 8178 | 152 | 72 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-03 08:00 | 2014-07-26 17:00 |  | 2014-06-11 08:00 | 2014-07-03 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 | 2014-07-03 08:00 | 2014-07-26 17:00 |  | PT_Normal |  |  |  |  | HQT1x/k9TfmfUOhZV6CdTg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32120 | N | N | 15 | WATER TANK ENCLOSURE |  | 125379 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 56 | LABOR- SUBCONTRACTOR
%R | 504147 | 6359 | 125380 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 80 | 0 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-09 08:00 | 2014-08-10 17:00 |  | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-07-09 08:00 | 2014-08-10 17:00 |  | PT_Normal |  |  |  |  | eVfzO2KzSGKQ6Bcysjjw5w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32120 | N | N | 15 | WATER TANK ENCLOSURE |  | 125379 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 336 | LABOR- SUBCONTRACTOR
%R | 504148 | 6359 | 125380 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 72 | 0 | 200 | 0 | 203.2 | 203.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-07-06 08:00 | 2014-08-06 17:00 | 2014-07-06 08:00 | 2014-08-06 17:00 | 2014-07-06 08:00 | 2014-08-06 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | c00MAxW6SD6zBc3o+skjmQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32120 | N | N | 15 | WATER TANK ENCLOSURE |  | 125379 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 101.6 | LABOR- SUBCONTRACTOR
%R | 504149 | 6359 | 125381 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 672 | 168 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-22 08:00 | 2014-11-19 17:00 |  | 2014-07-10 08:00 | 2014-08-11 17:00 | 2014-07-10 08:00 | 2014-08-11 17:00 | 2014-07-10 08:00 | 2014-08-11 17:00 | 2014-10-22 08:00 | 2014-11-19 17:00 |  | PT_Normal |  |  |  |  | GT5EecZHRNGWpCbnISo7YA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32110 | N | N | 10 | MISCELLANEOUS |  | 125379 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 200 | LABOR- SUBCONTRACTOR
%R | 504150 | 6359 | 125381 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6MSEX5020 | Construction Entrance Ramp | 8164 | 128 | 0 | 200 | 0 | 656 | 656 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-01 08:00 | 2014-06-29 17:00 |  | 2014-05-13 08:00 | 2014-06-10 17:00 | 2014-05-13 08:00 | 2014-06-10 17:00 | 2014-05-13 08:00 | 2014-06-10 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 |  | PT_Normal |  |  |  |  | ViAIsVVUQrq7CDsPyPRaXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32110 | N | N | 10 | MISCELLANEOUS |  | 125379 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 656 | SCREED MASON SK
%R | 504151 | 6359 | 125381 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6MSEX5025 | SS.Handrails and Balustrades | 8178 | 152 | 0 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-22 08:00 | 2014-07-14 17:00 |  | 2014-05-31 08:00 | 2014-06-22 17:00 | 2014-05-31 08:00 | 2014-06-22 17:00 | 2014-05-31 08:00 | 2014-06-22 17:00 | 2014-06-22 08:00 | 2014-07-14 17:00 |  | PT_Normal |  |  |  |  | IJIf/Y4iR42D8GJi8wHEXw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32110 | N | N | 10 | MISCELLANEOUS |  | 125379 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 56 | LABOR- SUBCONTRACTOR
%R | 504152 | 6359 | 125381 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6MSEX5015 | Construction of grease Trap | 8178 | 64 | 0 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-05 08:00 | 2014-05-27 17:00 |  | 2014-04-26 08:00 | 2014-05-18 17:00 | 2014-04-26 08:00 | 2014-05-18 17:00 | 2014-04-26 08:00 | 2014-05-18 17:00 | 2014-05-05 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | Rwe9nvwgTPmXuKj/CmYAKA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32110 | N | N | 10 | MISCELLANEOUS |  | 125379 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 56 | LABOR- SUBCONTRACTOR
%R | 504153 | 6359 | 125381 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6MSEX5000 | Construction of Manholes | 8172 | 64 | 0 | 200 | 0 | 528 | 528 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-01 08:00 | 2014-04-29 17:00 |  | 2014-03-23 08:00 | 2014-04-20 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 |  | PT_Normal |  |  |  |  | OlPZwLTdS+Kew1QzX80rEw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32110 | N | N | 10 | MISCELLANEOUS |  | 125379 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 528 | MANHOLES SK
%R | 504154 | 6359 | 125381 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6MSEX5005 | Construction of Soak pit, Chambers | 8172 | 64 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-13 17:00 |  | 2014-04-06 08:00 | 2014-05-04 17:00 | 2014-04-06 08:00 | 2014-05-04 17:00 | 2014-04-06 08:00 | 2014-05-04 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 |  | PT_Normal |  |  |  |  | StsgxflfQH+PfbkHYxFG5Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32110 | N | N | 10 | MISCELLANEOUS |  | 125379 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 176 | MANHOLES SK
%R | 504155 | 6359 | 125381 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6MSEX5010 | Telephone cable laying | 8177 | 64 | 0 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-25 17:00 |  | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | tN6h2oVuS2yJrkGa5iUFrg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32110 | N | N | 10 | MISCELLANEOUS |  | 125379 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 500 | LABOR - CIVIL
%R | 504156 | 6359 | 125382 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6HDEX5090 | kerb works | 8173 | 128 | 0 | 160 | 0 | 344 | 344 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-07 17:00 |  | 2014-05-27 08:00 | 2014-06-18 17:00 | 2014-05-27 08:00 | 2014-06-18 17:00 | 2014-05-27 08:00 | 2014-06-18 17:00 | 2014-06-15 08:00 | 2014-07-07 17:00 |  | PT_Normal |  |  |  |  | eln2AMj9Qh6qNHFqz4Vbow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32130 | N | N | 20 | HARD LANDSCAPING |  | 125379 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 344 | KERBSTONE MASON SK
%R | 504157 | 6359 | 125382 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6HDEX5095 | Cobble Stone Works | 8170 | 128 | 0 | 160 | 0 | 200 | 200 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-26 08:00 | 2014-07-19 17:00 |  | 2014-06-08 08:00 | 2014-06-30 17:00 | 2014-06-08 08:00 | 2014-06-30 17:00 | 2014-06-08 08:00 | 2014-06-30 17:00 | 2014-06-26 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | WJvS+sJhQ52MakQK13Se4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32130 | N | N | 20 | HARD LANDSCAPING |  | 125379 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 200 | TILE MASON SK
%R | 504158 | 6359 | 125382 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6HDEX5100 | Interlock works | 8174 | 128 | 0 | 160 | 0 | 232 | 232 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-03 08:00 | 2014-07-26 17:00 |  | 2014-06-15 08:00 | 2014-07-07 17:00 | 2014-06-15 08:00 | 2014-07-07 17:00 | 2014-06-15 08:00 | 2014-07-07 17:00 | 2014-07-03 08:00 | 2014-07-26 17:00 |  | PT_Normal |  |  |  |  | Hsg5aX4bSeucmSC8Uv5zKw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32130 | N | N | 20 | HARD LANDSCAPING |  | 125379 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 232 | INTERLOCK MASON SK
%R | 504159 | 6359 | 125383 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6SLEX5105 | Laying of Grass/ green area | 8178 | 128 | 0 | 200 | 0 | 2744 | 2744 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-09 08:00 | 2014-08-10 17:00 |  | 2014-06-21 08:00 | 2014-07-19 17:00 | 2014-06-21 08:00 | 2014-07-19 17:00 | 2014-06-21 08:00 | 2014-07-19 17:00 | 2014-07-09 08:00 | 2014-08-10 17:00 |  | PT_Normal |  |  |  |  | gp2+4pupS0KdUT+EKYumuA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32140 | N | N | 25 | SOFT LANDSCAPING |  | 125379 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 2744 | LABOR- SUBCONTRACTOR
%R | 504160 | 6359 | 125383 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6SLEX5110 | Laying of Palm tree | 8178 | 128 | 128 | 200 | 0 | 168 | 168 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | f5xB5TEHTOGUpd+awfL9Ww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32140 | N | N | 25 | SOFT LANDSCAPING |  | 125379 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 168 | LABOR- SUBCONTRACTOR
%R | 504161 | 6359 | 125386 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ELRF4070 | Installation of Isolator | 8178 | 8 | 0 | 144 | 0 | 412.8 | 412.8 | 144 | 0 | 0 | 0 |  |  |  | 2014-07-13 08:00 | 2014-08-05 17:00 |  | 2014-07-12 08:00 | 2014-07-31 17:00 | 2014-07-12 08:00 | 2014-07-31 17:00 | 2014-07-12 08:00 | 2014-07-31 17:00 | 2014-07-13 08:00 | 2014-08-05 17:00 |  | PT_Normal |  |  |  |  | wdePEWFeRgCWuW8hfiq2PA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32000 | N | N | 20 | ROOF |  | 125385 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 412.8 | LABOR- SUBCONTRACTOR
%R | 504162 | 6359 | 125386 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ELRF4075 | Installation of TV Dish Antenna | 8178 | 8 | 8 | 184 | 0 | 732.8 | 732.8 | 184 | 0 | 0 | 0 |  |  |  | 2014-07-19 08:00 | 2014-08-17 17:00 |  | 2014-07-17 08:00 | 2014-08-16 17:00 | 2014-07-17 08:00 | 2014-08-16 17:00 | 2014-07-17 08:00 | 2014-08-16 17:00 | 2014-07-19 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | ReOl9NxJTn2vKmj5UOYt7Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32000 | N | N | 20 | ROOF |  | 125385 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 732.8 | LABOR- SUBCONTRACTOR
%R | 504163 | 6359 | 125387 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 88 | 0 | 200 | 0 | 1222.4 | 1222.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-09 08:00 | 2014-05-07 17:00 |  | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 |  | PT_Normal |  |  |  |  | XIJ4HcDRRqijbV/MLLX1zg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31990 | N | N | 15 | FIRST FLOORS |  | 125385 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1222.4 | LABOR- SUBCONTRACTOR
%R | 504164 | 6359 | 125387 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ELFF4040 | Cable tray & trunking installation | 8178 | 232 | 16 | 160 | 0 | 1318.4 | 1318.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-12 08:00 | 2014-06-03 17:00 |  | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-05-12 08:00 | 2014-06-03 17:00 |  | PT_Normal |  |  |  |  | SilZTSMFR2udG0kMCXuw7Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31990 | N | N | 15 | FIRST FLOORS |  | 125385 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1318.4 | LABOR- SUBCONTRACTOR
%R | 504165 | 6359 | 125387 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ELFF4045 | Installation of wiring & Main Cabling | 8178 | 216 | 0 | 200 | 0 | 296 | 296 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-20 08:00 | 2014-06-17 17:00 |  | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | 2kwct4ncSXSsuOx1BhhEaQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31990 | N | N | 15 | FIRST FLOORS |  | 125385 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 296 | LABOR- SUBCONTRACTOR
%R | 504166 | 6359 | 125387 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 24 | 16 | 160 | 0 | 227.2 | 227.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-23 08:00 | 2014-07-15 17:00 |  | 2014-06-19 08:00 | 2014-07-12 17:00 | 2014-06-19 08:00 | 2014-07-12 17:00 | 2014-06-19 08:00 | 2014-07-12 17:00 | 2014-06-23 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | rH2cWYWzS5qV0FJWaASASw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31990 | N | N | 15 | FIRST FLOORS |  | 125385 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 227.2 | LABOR- SUBCONTRACTOR
%R | 504167 | 6359 | 125387 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 8 | 0 | 200 | 0 | 1651.2 | 1651.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-27 17:00 |  | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | /04oSBZZRn2MZ18Dru4h6g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31990 | N | N | 15 | FIRST FLOORS |  | 125385 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1651.2 | LABOR- SUBCONTRACTOR
%R | 504168 | 6359 | 125387 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 8 | 0 | 200 | 0 | 1008 | 1008 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | 1H/oYkI0Rxay53trjL/Zmw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31990 | N | N | 15 | FIRST FLOORS |  | 125385 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1008 | LABOR- SUBCONTRACTOR
%R | 504169 | 6359 | 125387 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ELFF4050 | Installation of Telephone System | 8178 | 64 | 56 | 200 | 0 | 451.2 | 451.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-26 08:00 | 2014-07-24 17:00 |  | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-26 08:00 | 2014-07-24 17:00 |  | PT_Normal |  |  |  |  | MyUKV5lAS16czVQdpgtfjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31990 | N | N | 15 | FIRST FLOORS |  | 125385 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 451.2 | LABOR- SUBCONTRACTOR
%R | 504170 | 6359 | 125388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 216 | 0 | 200 | 0 | 1222.4 | 1222.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-14 17:00 |  | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 |  | PT_Normal |  |  |  |  | eYL6yZaeS2iRvMq8xeWY8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31980 | N | N | 10 | GROUND FLOOR |  | 125385 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 611.2 | LABOR- SUBCONTRACTOR
%R | 504171 | 6359 | 125388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ELGF4005 | Cable tray & trunking installation | 8178 | 360 | 0 | 160 | 0 | 1318.4 | 1318.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-19 08:00 | 2014-05-11 17:00 |  | 2014-02-25 08:00 | 2014-03-19 17:00 | 2014-02-25 08:00 | 2014-03-19 17:00 | 2014-02-25 08:00 | 2014-03-19 17:00 | 2014-04-19 08:00 | 2014-05-11 17:00 |  | PT_Normal |  |  |  |  | PfNjz+j6SP2+tvXI3l8rXQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31980 | N | N | 10 | GROUND FLOOR |  | 125385 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1318.4 | LABOR- SUBCONTRACTOR
%R | 504172 | 6359 | 125388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ELGF4010 | Installation of wiring & Main Cabling | 8178 | 360 | 216 | 200 | 0 | 296 | 296 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-27 08:00 | 2014-05-25 17:00 |  | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 |  | PT_Normal |  |  |  |  | fAPFwNkIS72LKfUUBlnuww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31980 | N | N | 10 | GROUND FLOOR |  | 125385 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 296 | LABOR- SUBCONTRACTOR
%R | 504173 | 6359 | 125388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 144 | 0 | 160 | 0 | 227.2 | 227.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-03 08:00 | 2014-06-25 17:00 |  | 2014-05-13 08:00 | 2014-06-04 17:00 | 2014-05-13 08:00 | 2014-06-04 17:00 | 2014-05-13 08:00 | 2014-06-04 17:00 | 2014-06-03 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | kqM91GVMQAiqDPFKoObT0w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31980 | N | N | 10 | GROUND FLOOR |  | 125385 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 227.2 | LABOR- SUBCONTRACTOR
%R | 504174 | 6359 | 125388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 200 | 0 | 200 | 0 | 1651.2 | 1651.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-23 08:00 | 2014-07-21 17:00 |  | 2014-05-25 08:00 | 2014-06-22 17:00 | 2014-05-25 08:00 | 2014-06-22 17:00 | 2014-05-25 08:00 | 2014-06-22 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 |  | PT_Normal |  |  |  |  | 1TE7SE0/RtuBVE42twN6EQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31980 | N | N | 10 | GROUND FLOOR |  | 125385 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1651.2 | LABOR- SUBCONTRACTOR
%R | 504175 | 6359 | 125388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 240 | 0 | 200 | 0 | 1075.2 | 1075.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-07-09 17:00 |  | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-06-11 08:00 | 2014-07-09 17:00 |  | PT_Normal |  |  |  |  | S4lock3ISjKSE3S9vMRLOg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31980 | N | N | 10 | GROUND FLOOR |  | 125385 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1075.2 | LABOR- SUBCONTRACTOR
%R | 504176 | 6359 | 125388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ELGF4030 | Installation of Telephone System | 8178 | 144 | 40 | 160 | 0 | 520 | 520 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-07 17:00 |  | 2014-05-25 08:00 | 2014-06-16 17:00 | 2014-05-25 08:00 | 2014-06-16 17:00 | 2014-05-25 08:00 | 2014-06-16 17:00 | 2014-06-15 08:00 | 2014-07-07 17:00 |  | PT_Normal |  |  |  |  | Txvm4SRtS4+XxPssDOnokA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31980 | N | N | 10 | GROUND FLOOR |  | 125385 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 520 | LABOR- SUBCONTRACTOR
%R | 504177 | 6359 | 125390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 144 | 0 | 144 | 0 | 441.6 | 441.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-06 17:00 |  | 2014-02-24 08:00 | 2014-03-16 17:00 | 2014-02-24 08:00 | 2014-03-16 17:00 | 2014-02-24 08:00 | 2014-03-16 17:00 | 2014-03-17 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | vyt5c+KsTGGb5bfZwj3o9Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32020 | N | N | 10 | GROUND FLOOR |  | 125389 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 441.6 | LABOR- SUBCONTRACTOR
%R | 504178 | 6359 | 125390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6PLGF4310 | Installation of Drainage pipes &testing | 8178 | 168 | 104 | 144 | 0 | 177.6 | 177.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-20 08:00 | 2014-04-09 17:00 |  | 2014-02-24 08:00 | 2014-03-16 17:00 | 2014-02-24 08:00 | 2014-03-16 17:00 | 2014-02-24 08:00 | 2014-03-16 17:00 | 2014-03-20 08:00 | 2014-04-09 17:00 |  | PT_Normal |  |  |  |  | Ilg5DgOBQw+2CV1ZPlpTXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32020 | N | N | 10 | GROUND FLOOR |  | 125389 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 177.6 | LABOR- SUBCONTRACTOR
%R | 504179 | 6359 | 125390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6PLGF4315 | Sanitary Fittings & Accessories | 8178 | 360 | 0 | 160 | 0 | 134.4 | 134.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-11 17:00 |  | 2014-05-25 08:00 | 2014-06-16 17:00 | 2014-05-25 08:00 | 2014-06-16 17:00 | 2014-05-25 08:00 | 2014-06-16 17:00 | 2014-07-16 08:00 | 2014-08-11 17:00 |  | PT_Normal |  |  |  |  | N3JwQ1UjSV+F2n1GusQQlQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32020 | N | N | 10 | GROUND FLOOR |  | 125389 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 504180 | 6359 | 125390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6PLGF4320 | Installation of Water Heater | 8178 | 360 | 80 | 120 | 0 | 134.4 | 134.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-28 08:00 | 2014-08-17 17:00 |  | 2014-06-05 08:00 | 2014-06-22 17:00 | 2014-06-05 08:00 | 2014-06-22 17:00 | 2014-06-05 08:00 | 2014-06-22 17:00 | 2014-07-28 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | vzpXuF9DSLWFyOQVkfj/vw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32020 | N | N | 10 | GROUND FLOOR |  | 125389 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 504181 | 6359 | 125390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 0 | 0 | 128 | 0 | 67.2 | 67.2 | 128 | 0 | 0 | 0 |  |  |  | 2013-11-02 08:00 | 2013-11-19 17:00 |  | 2013-11-02 08:00 | 2013-11-19 17:00 | 2013-11-02 08:00 | 2013-11-19 17:00 | 2013-11-02 08:00 | 2013-11-19 17:00 | 2013-11-02 08:00 | 2013-11-19 17:00 |  | PT_Normal |  |  |  |  | iaUpoZUyS8+TzFPbFdGRhQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32020 | N | N | 10 | GROUND FLOOR |  | 125389 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504182 | 6359 | 125391 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 448 | 240 | 120 | 0 | 110.4 | 110.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-01 08:00 | 2014-07-17 17:00 |  | 2014-04-27 08:00 | 2014-05-13 17:00 | 2014-04-27 08:00 | 2014-05-13 17:00 | 2014-04-27 08:00 | 2014-05-13 17:00 | 2014-07-01 08:00 | 2014-07-17 17:00 |  | PT_Normal |  |  |  |  | 678uVZ+pTNaNP4vaRdXiew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32040 | N | N | 20 | ROOF |  | 125389 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 110.4 | LABOR- SUBCONTRACTOR
%R | 504183 | 6359 | 125391 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6PLRF4350 | Installation of Rain water Pipes | 8178 | 208 | 80 | 120 | 0 | 67.2 | 67.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-10 08:00 | 2014-07-27 17:00 |  | 2014-06-10 08:00 | 2014-06-26 17:00 | 2014-06-10 08:00 | 2014-06-26 17:00 | 2014-06-10 08:00 | 2014-06-26 17:00 | 2014-07-10 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | 82q6a2KCSAOZMemnVWyQvQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32040 | N | N | 20 | ROOF |  | 125389 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504184 | 6359 | 125391 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 8 | 0 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-07-15 08:00 | 2014-08-16 17:00 | 2014-07-15 08:00 | 2014-08-16 17:00 | 2014-07-15 08:00 | 2014-08-16 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | gryjN7HBTqq3pp0sXbW9XA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32040 | N | N | 20 | ROOF |  | 125389 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 168 | LABOR- SUBCONTRACTOR
%R | 504185 | 6359 | 125392 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 0 | 0 | 144 | 0 | 441.6 | 441.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-08 08:00 | 2014-04-28 17:00 |  | 2014-04-08 08:00 | 2014-04-28 17:00 | 2014-04-08 08:00 | 2014-04-28 17:00 | 2014-04-08 08:00 | 2014-04-28 17:00 | 2014-04-08 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | L1LQNQhiRrG16f/2GCsWJQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32030 | N | N | 15 | FIRST FLOORS |  | 125389 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 441.6 | LABOR- SUBCONTRACTOR
%R | 504186 | 6359 | 125392 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6PLFF4330 | Installation of Drainage pipes & testing | 8178 | 176 | 56 | 144 | 0 | 177.6 | 177.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-05-04 08:00 | 2014-05-24 17:00 |  | 2014-04-08 08:00 | 2014-04-28 17:00 | 2014-04-08 08:00 | 2014-04-28 17:00 | 2014-04-08 08:00 | 2014-04-28 17:00 | 2014-05-04 08:00 | 2014-05-24 17:00 |  | PT_Normal |  |  |  |  | WDAZzNzFTxaXaXS8hbxg4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32030 | N | N | 15 | FIRST FLOORS |  | 125389 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 177.6 | LABOR- SUBCONTRACTOR
%R | 504187 | 6359 | 125392 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6PLFF4335 | Sanitary Fittings & Accessories | 8178 | 40 | 0 | 160 | 0 | 67.2 | 67.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-21 17:00 |  | 2014-06-23 08:00 | 2014-07-15 17:00 | 2014-06-23 08:00 | 2014-07-15 17:00 | 2014-06-23 08:00 | 2014-07-15 17:00 | 2014-06-29 08:00 | 2014-07-21 17:00 |  | PT_Normal |  |  |  |  | EfZl9AA7SMKR9GWoDmAzjA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32030 | N | N | 15 | FIRST FLOORS |  | 125389 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504188 | 6359 | 125392 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6PLFF4340 | Installation of Water Heater | 8178 | 40 | 32 | 120 | 0 | 67.2 | 67.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-10 08:00 | 2014-07-27 17:00 |  | 2014-07-05 08:00 | 2014-07-21 17:00 | 2014-07-05 08:00 | 2014-07-21 17:00 | 2014-07-05 08:00 | 2014-07-21 17:00 | 2014-07-10 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | 2jb/+UFDQ7iJNkpfo/iF8w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32030 | N | N | 15 | FIRST FLOORS |  | 125389 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504189 | 6359 | 125394 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ACFF4615 | Installation AC Pipes | 8178 | 216 | 40 | 160 | 0 | 977.6 | 977.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-31 08:00 | 2014-06-22 17:00 |  | 2014-04-29 08:00 | 2014-05-21 17:00 | 2014-04-29 08:00 | 2014-05-21 17:00 | 2014-04-29 08:00 | 2014-05-21 17:00 | 2014-05-31 08:00 | 2014-06-22 17:00 |  | PT_Normal |  |  |  |  | WUvLBT5xR+2CNwNgm7VNuQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32070 | N | N | 15 | FIRST FLOORS |  | 125393 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 977.6 | LABOR- SUBCONTRACTOR
%R | 504190 | 6359 | 125394 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ACFF4620 | Fixing of Ventilation Equipments | 8178 | 16 | 0 | 200 | 0 | 113.6 | 113.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-18 08:00 | 2014-07-16 17:00 |  | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-18 08:00 | 2014-07-16 17:00 |  | PT_Normal |  |  |  |  | tN+2KqAqQvuV2bnRBEyFxg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32070 | N | N | 15 | FIRST FLOORS |  | 125393 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 113.6 | LABOR- SUBCONTRACTOR
%R | 504191 | 6359 | 125394 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ACFF4625 | Fixing of Split AC | 8178 | 16 | 0 | 160 | 0 | 296 | 296 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-09 08:00 | 2014-07-31 17:00 |  | 2014-07-07 08:00 | 2014-07-29 17:00 | 2014-07-07 08:00 | 2014-07-29 17:00 | 2014-07-07 08:00 | 2014-07-29 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 |  | PT_Normal |  |  |  |  | BEUhwdorTXq/K8nkfnUdcw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32070 | N | N | 15 | FIRST FLOORS |  | 125393 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 296 | LABOR- SUBCONTRACTOR
%R | 504192 | 6359 | 125395 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ACGF4600 | Installation AC Pipes | 8178 | 392 | 40 | 160 | 0 | 977.6 | 977.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-12 08:00 | 2014-06-03 17:00 |  | 2014-03-16 08:00 | 2014-04-07 17:00 | 2014-03-16 08:00 | 2014-04-07 17:00 | 2014-03-16 08:00 | 2014-04-07 17:00 | 2014-05-12 08:00 | 2014-06-03 17:00 |  | PT_Normal |  |  |  |  | 4KlnqpdjTyOShKQJ0dAF4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32060 | N | N | 10 | GROUND FLOOR |  | 125393 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 977.6 | LABOR- SUBCONTRACTOR
%R | 504193 | 6359 | 125395 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ACGF4605 | Fixing of Ventilation Equipments | 8178 | 256 | 0 | 200 | 0 | 182.4 | 182.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-14 08:00 | 2014-07-12 17:00 |  | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 |  | PT_Normal |  |  |  |  | UEk5bVTuShOvuumece1vhw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32060 | N | N | 10 | GROUND FLOOR |  | 125393 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 182.4 | LABOR- SUBCONTRACTOR
%R | 504194 | 6359 | 125395 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ACGF4610 | Fixing of Split AC | 8178 | 256 | 40 | 160 | 0 | 296 | 296 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-05 08:00 | 2014-07-27 17:00 |  | 2014-05-28 08:00 | 2014-06-19 17:00 | 2014-05-28 08:00 | 2014-06-19 17:00 | 2014-05-28 08:00 | 2014-06-19 17:00 | 2014-07-05 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | 5wy0gWZdSqmwMrIjb0a3aQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32060 | N | N | 10 | GROUND FLOOR |  | 125393 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 296 | LABOR- SUBCONTRACTOR
%R | 504195 | 6359 | 125396 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ACRF4630 | Installation of Refrigerant Pipes | 8178 | 272 | 0 | 200 | 0 | 409.6 | 409.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-10 08:00 | 2014-08-11 17:00 |  | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-07-10 08:00 | 2014-08-11 17:00 |  | PT_Normal |  |  |  |  | adkLDPRrRkSVmzdJLI0s3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32080 | N | N | 20 | ROOF |  | 125393 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 409.6 | LABOR- SUBCONTRACTOR
%R | 504196 | 6359 | 125396 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ACRF4635 | Installation of Condensing Unit | 8178 | 24 | 0 | 200 | 0 | 568 | 568 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | G35X+7QAToa2uVukn6WMSQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32080 | N | N | 20 | ROOF |  | 125393 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 284 | LABOR- SUBCONTRACTOR
%R | 504197 | 6359 | 125399 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARRF3600 | Block work | 8168 | 416 | 0 | 160 | 0 | 700 | 700 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-04 08:00 | 2014-06-26 17:00 |  | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-06-04 08:00 | 2014-06-26 17:00 |  | PT_Normal |  |  |  |  | arZWKGmYRru8Uep7wVl1YA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31920 | N | N | 20 | ROOF |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 700 | BLOCK MASON SK
%R | 504198 | 6359 | 125399 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARRF3605 | Plastering work | 8169 | 416 | 0 | 160 | 0 | 1786.5 | 1786.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-07-05 17:00 |  | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-06-12 08:00 | 2014-07-05 17:00 |  | PT_Normal |  |  |  |  | WUXDtfSNQ0mZ9fJJs3y3Hw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31920 | N | N | 20 | ROOF |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1786.5 | PLASTER MASON SK
%R | 504199 | 6359 | 125399 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARRF3610 | Flooring screed | 8164 | 456 | 0 | 120 | 0 | 136.5 | 136.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-02 08:00 | 2014-07-19 17:00 |  | 2014-04-27 08:00 | 2014-05-13 17:00 | 2014-04-27 08:00 | 2014-05-13 17:00 | 2014-04-27 08:00 | 2014-05-13 17:00 | 2014-07-02 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | IOlkUUeqTMmyIKR+FoOgQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31920 | N | N | 20 | ROOF |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 136.5 | SCREED MASON SK
%R | 504200 | 6359 | 125399 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARRF3695 | Painting -Storage area | 8178 | 456 | 0 | 160 | 0 | 1640 | 1640 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-10 08:00 | 2014-08-05 17:00 |  | 2014-05-05 08:00 | 2014-05-27 17:00 | 2014-05-05 08:00 | 2014-05-27 17:00 | 2014-05-05 08:00 | 2014-05-27 17:00 | 2014-07-10 08:00 | 2014-08-05 17:00 |  | PT_Normal |  |  |  |  | jWhgKExkQJGruzN/o1KzDQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31920 | N | N | 20 | ROOF |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1640 | LABOR- SUBCONTRACTOR
%R | 504201 | 6359 | 125399 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARRF3620 | Epoxy Painting -Storage area | 8178 | 456 | 456 | 120 | 0 | 48.5 | 48.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-28 08:00 | 2014-08-17 17:00 |  | 2014-05-22 08:00 | 2014-06-08 17:00 | 2014-05-22 08:00 | 2014-06-08 17:00 | 2014-05-22 08:00 | 2014-06-08 17:00 | 2014-07-28 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | CbK6l+KvQICQQ2acQ/aU0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31920 | N | N | 20 | ROOF |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 48.5 | LABOR- SUBCONTRACTOR
%R | 504202 | 6359 | 125400 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARFF3300 | Block work | 8168 | 0 | 0 | 200 | 0 | 6387.5 | 6387.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-19 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | 62pNKGVBRDO1unZdc+2fuA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31910 | N | N | 15 | FIRST FLOORS |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 6387.5 | BLOCK MASON SK
%R | 504203 | 6359 | 125400 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARFF3305 | Plastering work | 8169 | 0 | 0 | 200 | 0 | 8899 | 8899 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-13 17:00 |  | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 |  | PT_Normal |  |  |  |  | E+aGl+5iSROy97Qvd6NReA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31910 | N | N | 15 | FIRST FLOORS |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 8899 | PLASTER MASON SK
%R | 504204 | 6359 | 125400 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARFF3310 | Flooring screed | 8164 | 96 | 96 | 168 | 0 | 1215.5 | 1215.5 | 168 | 0 | 0 | 0 |  |  |  | 2014-05-07 08:00 | 2014-05-31 17:00 |  | 2014-04-23 08:00 | 2014-05-17 17:00 | 2014-04-23 08:00 | 2014-05-17 17:00 | 2014-04-23 08:00 | 2014-05-17 17:00 | 2014-05-07 08:00 | 2014-05-31 17:00 |  | PT_Normal |  |  |  |  | fu9howYDQeuZrTNaKzr4Qw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31910 | N | N | 15 | FIRST FLOORS |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1215.5 | SCREED MASON SK
%R | 504205 | 6359 | 125400 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARFF3315 | Wet area waterproofing | 8178 | 0 | 0 | 120 | 0 | 1215.5 | 1215.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-05 08:00 | 2014-05-21 17:00 |  | 2014-05-05 08:00 | 2014-05-21 17:00 | 2014-05-05 08:00 | 2014-05-21 17:00 | 2014-05-05 08:00 | 2014-05-21 17:00 | 2014-05-05 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | wMDbaLbzS9aZHd+l0H2ShQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31910 | N | N | 15 | FIRST FLOORS |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1215.5 | LABOR- SUBCONTRACTOR
%R | 504206 | 6359 | 125400 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARFF3330 | Paint First coat | 8178 | 112 | 112 | 200 | 0 | 4742.75 | 4742.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-18 08:00 | 2014-06-15 17:00 |  | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-05-18 08:00 | 2014-06-15 17:00 |  | PT_Normal |  |  |  |  | FLyASuPLREKFM7nC+5JmAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31910 | N | N | 15 | FIRST FLOORS |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 4742.75 | LABOR- SUBCONTRACTOR
%R | 504207 | 6359 | 125400 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARFF3320 | Ceramic Wall Tiling | 8170 | 0 | 0 | 200 | 0 | 1897.25 | 1897.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-12 08:00 | 2014-06-09 17:00 |  | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 |  | PT_Normal |  |  |  |  | CB6pz+ELS0iNGvmHj/weFg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31910 | N | N | 15 | FIRST FLOORS |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1897.25 | TILE MASON SK
%R | 504208 | 6359 | 125400 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARFF3325 | Porcelain Tile flooring | 8170 | 0 | 0 | 200 | 0 | 1743.75 | 1743.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | Enz84yL2Tyir4lER7qe5QQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31910 | N | N | 15 | FIRST FLOORS |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1743.75 | TILE MASON SK
%R | 504209 | 6359 | 125400 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARFF3335 | Slate Tile Flooring & Skirting | 8170 | 64 | 64 | 120 | 0 | 261.5 | 261.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-01 17:00 |  | 2014-06-05 08:00 | 2014-06-22 17:00 | 2014-06-05 08:00 | 2014-06-22 17:00 | 2014-06-05 08:00 | 2014-06-22 17:00 | 2014-06-15 08:00 | 2014-07-01 17:00 |  | PT_Normal |  |  |  |  | kKvGTzq6S7aIpkb5T/GhvQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31910 | N | N | 15 | FIRST FLOORS |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 261.5 | TILE MASON SK
%R | 504210 | 6359 | 125400 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARFF3350 | Granite - Stair case flooring & Skirting | 8171 | 16 | 16 | 160 | 0 | 875 | 875 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-07-03 17:00 |  | 2014-06-09 08:00 | 2014-07-01 17:00 | 2014-06-09 08:00 | 2014-07-01 17:00 | 2014-06-09 08:00 | 2014-07-01 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 |  | PT_Normal |  |  |  |  | 4xN1CMLRRWWVd2+2MI0TXQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31910 | N | N | 15 | FIRST FLOORS |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 875 | GRANITE MASON SK
%R | 504211 | 6359 | 125400 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARFF3345 | Fixing of Suspension systems | 8178 | 0 | 0 | 160 | 0 | 1305 | 1305 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-01 08:00 | 2014-06-23 17:00 |  | 2014-06-01 08:00 | 2014-06-23 17:00 | 2014-06-01 08:00 | 2014-06-23 17:00 | 2014-06-01 08:00 | 2014-06-23 17:00 | 2014-06-01 08:00 | 2014-06-23 17:00 |  | PT_Normal |  |  |  |  | FnZkOiFpQ/WGyhVbqG1moQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31910 | N | N | 15 | FIRST FLOORS |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1305 | LABOR- SUBCONTRACTOR
%R | 504212 | 6359 | 125400 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARFF3360 | Gypsum board false ceiling | 8178 | 0 | 0 | 200 | 0 | 1305 | 1305 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-08 08:00 | 2014-07-06 17:00 |  | 2014-06-08 08:00 | 2014-07-06 17:00 | 2014-06-08 08:00 | 2014-07-06 17:00 | 2014-06-08 08:00 | 2014-07-06 17:00 | 2014-06-08 08:00 | 2014-07-06 17:00 |  | PT_Normal |  |  |  |  | N5gORMlQRKmYWI7RxcJeLw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31910 | N | N | 15 | FIRST FLOORS |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1305 | LABOR- SUBCONTRACTOR
%R | 504213 | 6359 | 125400 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARFF3365 | Wooden door | 8178 | 0 | 0 | 120 | 0 | 308 | 308 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-23 08:00 | 2014-07-09 17:00 |  | 2014-06-23 08:00 | 2014-07-09 17:00 | 2014-06-23 08:00 | 2014-07-09 17:00 | 2014-06-23 08:00 | 2014-07-09 17:00 | 2014-06-23 08:00 | 2014-07-09 17:00 |  | PT_Normal |  |  |  |  | yGZuccv5RpW5tfM3bOd0hA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31910 | N | N | 15 | FIRST FLOORS |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 308 | LABOR- SUBCONTRACTOR
%R | 504214 | 6359 | 125400 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARFF3370 | Aluminum Door | 8178 | 0 | 0 | 160 | 0 | 220 | 220 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-23 08:00 | 2014-07-15 17:00 |  | 2014-06-23 08:00 | 2014-07-15 17:00 | 2014-06-23 08:00 | 2014-07-15 17:00 | 2014-06-23 08:00 | 2014-07-15 17:00 | 2014-06-23 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | hd3DyXxjTR2VvtUKzL6j0g |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31910 | N | N | 15 | FIRST FLOORS |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 220 | LABOR- SUBCONTRACTOR
%R | 504215 | 6359 | 125400 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARFF3380 | Aluminum windows | 8178 | 32 | 32 | 160 | 0 | 162.25 | 162.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-05 08:00 | 2014-07-27 17:00 |  | 2014-06-30 08:00 | 2014-07-22 17:00 | 2014-06-30 08:00 | 2014-07-22 17:00 | 2014-06-30 08:00 | 2014-07-22 17:00 | 2014-07-05 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | eKJfdURoReKjEyswvlxBLg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31910 | N | N | 15 | FIRST FLOORS |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 162.25 | LABOR- SUBCONTRACTOR
%R | 504216 | 6359 | 125400 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARFF3375 | Carpentry & Joinery Works | 8178 | 0 | 0 | 200 | 0 | 1100 | 1100 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-27 17:00 |  | 2014-06-29 08:00 | 2014-07-27 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | 1czqykfOQVe9VaScJmi3PQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31910 | N | N | 15 | FIRST FLOORS |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1100 | LABOR- SUBCONTRACTOR
%R | 504217 | 6359 | 125400 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARFF3390 | Installation of Granite Counter Top | 8171 | 8 | 8 | 160 | 0 | 88 | 88 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-12 08:00 | 2014-08-06 17:00 |  | 2014-07-10 08:00 | 2014-08-05 17:00 | 2014-07-10 08:00 | 2014-08-05 17:00 | 2014-07-10 08:00 | 2014-08-05 17:00 | 2014-07-12 08:00 | 2014-08-06 17:00 |  | PT_Normal |  |  |  |  | J8zuDofZRLC1O7e6+HFeig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31910 | N | N | 15 | FIRST FLOORS |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 88 | GRANITE MASON SK
%R | 504218 | 6359 | 125400 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARFF3385 | Handrail & Balustrade | 8178 | 0 | 0 | 160 | 0 | 787.5 | 787.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-10 08:00 | 2014-08-05 17:00 |  | 2014-07-10 08:00 | 2014-08-05 17:00 | 2014-07-10 08:00 | 2014-08-05 17:00 | 2014-07-10 08:00 | 2014-08-05 17:00 | 2014-07-10 08:00 | 2014-08-05 17:00 |  | PT_Normal |  |  |  |  | XePTzig+QdOrVCLFXqNX9A |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31910 | N | N | 15 | FIRST FLOORS |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 787.5 | LABOR- SUBCONTRACTOR
%R | 504219 | 6359 | 125400 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARFF3395 | Final Painting | 8178 | 0 | 0 | 200 | 0 | 4742.75 | 4742.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | boCGybT0RsyBgFwr3cvRfw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31910 | N | N | 15 | FIRST FLOORS |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 2371.375 | LABOR- SUBCONTRACTOR
%R | 504220 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3000 | Block work | 8168 | 144 | 0 | 200 | 0 | 9737.5 | 9737.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-01 08:00 | 2014-03-29 17:00 |  | 2014-02-06 08:00 | 2014-03-08 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 | 2014-03-01 08:00 | 2014-03-29 17:00 |  | PT_Normal |  |  |  |  | sun3j7ivRdCvpY++mKJaDw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 4868.75 | BLOCK MASON SK
%R | 504221 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3005 | Plastering work | 8169 | 144 | 0 | 200 | 0 | 13637.5 | 13637.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-23 08:00 | 2014-04-20 17:00 |  | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | vMMZIxHBSWO46ng0ilKYfw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 13637.5 | PLASTER MASON SK
%R | 504222 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3010 | Flooring screed | 8164 | 208 | 64 | 168 | 0 | 1580.25 | 1580.25 | 168 | 0 | 0 | 0 |  |  |  | 2014-04-09 08:00 | 2014-05-03 17:00 |  | 2014-03-10 08:00 | 2014-04-02 17:00 | 2014-03-10 08:00 | 2014-04-02 17:00 | 2014-03-10 08:00 | 2014-04-02 17:00 | 2014-04-09 08:00 | 2014-05-03 17:00 |  | PT_Normal |  |  |  |  | ZQUcbdU1TpaeIyrijfXK6g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1580.25 | SCREED MASON SK
%R | 504223 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 144 | 0 | 120 | 0 | 247.5 | 247.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-09 08:00 | 2014-04-26 17:00 |  | 2014-03-19 08:00 | 2014-04-05 17:00 | 2014-03-19 08:00 | 2014-04-05 17:00 | 2014-03-19 08:00 | 2014-04-05 17:00 | 2014-04-09 08:00 | 2014-04-26 17:00 |  | PT_Normal |  |  |  |  | mPH3QHE2T9OdT53U3p4ZUQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 247.5 | LABOR- SUBCONTRACTOR
%R | 504224 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3030 | Paint First coat | 8178 | 256 | 0 | 200 | 0 | 5425.75 | 5425.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-24 08:00 | 2014-05-22 17:00 |  | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 |  | PT_Normal |  |  |  |  | xLz8FM4KQz2hhBMfE7+K6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 5425.75 | LABOR- SUBCONTRACTOR
%R | 504225 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3020 | Ceramic Wall Tiling | 8170 | 144 | 0 | 200 | 0 | 4428.5 | 4428.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-13 17:00 |  | 2014-03-25 08:00 | 2014-04-22 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 |  | PT_Normal |  |  |  |  | UXjuOlrnRIe4B33c5Q4Z2Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 4428.5 | TILE MASON SK
%R | 504226 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3025 | Porcelain Tile flooring | 8170 | 144 | 0 | 200 | 0 | 1743.75 | 1743.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-21 08:00 | 2014-05-19 17:00 |  | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | 1HhiDQuoSyaGm6bZRF2s1w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1743.75 | TILE MASON SK
%R | 504227 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3040 | Cobble Tile flooring | 8170 | 168 | 0 | 120 | 0 | 741 | 741 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-21 08:00 | 2014-06-07 17:00 |  | 2014-04-27 08:00 | 2014-05-13 17:00 | 2014-04-27 08:00 | 2014-05-13 17:00 | 2014-04-27 08:00 | 2014-05-13 17:00 | 2014-05-21 08:00 | 2014-06-07 17:00 |  | PT_Normal |  |  |  |  | q2IChTPKRiK9euBMC/ygsg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 741 | TILE MASON SK
%R | 504228 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 184 | 16 | 120 | 0 | 761.5 | 761.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-02 17:00 |  | 2014-04-20 08:00 | 2014-05-06 17:00 | 2014-04-20 08:00 | 2014-05-06 17:00 | 2014-04-20 08:00 | 2014-05-06 17:00 | 2014-05-17 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | 90F6HefTQAycJSt03+yFhA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 761.5 | TILE MASON SK
%R | 504229 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 168 | 0 | 160 | 0 | 875 | 875 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-29 08:00 | 2014-06-21 17:00 |  | 2014-05-05 08:00 | 2014-05-27 17:00 | 2014-05-05 08:00 | 2014-05-27 17:00 | 2014-05-05 08:00 | 2014-05-27 17:00 | 2014-05-29 08:00 | 2014-06-21 17:00 |  | PT_Normal |  |  |  |  | RgyySe5fSNa0/s7aTviQVA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 875 | GRANITE MASON SK
%R | 504230 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3045 | Fixing of Suspension systems | 8178 | 144 | 0 | 160 | 0 | 1455.05 | 1455.05 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-08 08:00 | 2014-05-31 17:00 |  | 2014-04-17 08:00 | 2014-05-10 17:00 | 2014-04-17 08:00 | 2014-05-10 17:00 | 2014-04-17 08:00 | 2014-05-10 17:00 | 2014-05-08 08:00 | 2014-05-31 17:00 |  | PT_Normal |  |  |  |  | CqiR+oPZTLGe6aATscSTpw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1455.05 | LABOR- SUBCONTRACTOR
%R | 504231 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3055 | Aluminum tile false ceiling | 8178 | 168 | 24 | 200 | 0 | 150 | 150 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-20 08:00 | 2014-06-17 17:00 |  | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | /s1ZZvHcSOOeve7EtkcSjw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 150 | LABOR- SUBCONTRACTOR
%R | 504232 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3060 | Gypsum board false ceiling | 8178 | 144 | 0 | 200 | 0 | 1335.15 | 1335.15 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-20 08:00 | 2014-06-17 17:00 |  | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | E7sfggprQZuwpNi4rf7lgQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1335.15 | LABOR- SUBCONTRACTOR
%R | 504233 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3065 | Wooden door & PVC Door | 8178 | 168 | 0 | 120 | 0 | 308 | 308 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-06-29 17:00 |  | 2014-05-19 08:00 | 2014-06-04 17:00 | 2014-05-19 08:00 | 2014-06-04 17:00 | 2014-05-19 08:00 | 2014-06-04 17:00 | 2014-06-12 08:00 | 2014-06-29 17:00 |  | PT_Normal |  |  |  |  | oB5ioImJTrSYYkajcrK2MQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 308 | LABOR- SUBCONTRACTOR
%R | 504234 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3070 | Aluminum doors | 8178 | 168 | 0 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-18 08:00 | 2014-07-05 17:00 |  | 2014-05-25 08:00 | 2014-06-10 17:00 | 2014-05-25 08:00 | 2014-06-10 17:00 | 2014-05-25 08:00 | 2014-06-10 17:00 | 2014-06-18 08:00 | 2014-07-05 17:00 |  | PT_Normal |  |  |  |  | pRCDXwfARg6acE9UMJdRuA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 176 | LABOR- SUBCONTRACTOR
%R | 504235 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3080 | Aluminum windows | 8178 | 248 | 40 | 160 | 0 | 162.25 | 162.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-07 08:00 | 2014-07-29 17:00 |  | 2014-06-01 08:00 | 2014-06-23 17:00 | 2014-06-01 08:00 | 2014-06-23 17:00 | 2014-06-01 08:00 | 2014-06-23 17:00 | 2014-07-07 08:00 | 2014-07-29 17:00 |  | PT_Normal |  |  |  |  | /5gmoXvnQoODfcrQSb+L7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 162.25 | LABOR- SUBCONTRACTOR
%R | 504236 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3075 | Carpentry & Joinery Works | 8178 | 168 | 0 | 160 | 0 | 572 | 572 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-24 08:00 | 2014-07-16 17:00 |  | 2014-05-31 08:00 | 2014-06-22 17:00 | 2014-05-31 08:00 | 2014-06-22 17:00 | 2014-05-31 08:00 | 2014-06-22 17:00 | 2014-06-24 08:00 | 2014-07-16 17:00 |  | PT_Normal |  |  |  |  | WN4slLYJTDuW2muTrgVYyA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 572 | LABOR- SUBCONTRACTOR
%R | 504237 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3090 | Installation of Granite Counter Top | 8171 | 168 | 0 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-07 08:00 | 2014-07-23 17:00 |  | 2014-06-12 08:00 | 2014-06-29 17:00 | 2014-06-12 08:00 | 2014-06-29 17:00 | 2014-06-12 08:00 | 2014-06-29 17:00 | 2014-07-07 08:00 | 2014-07-23 17:00 |  | PT_Normal |  |  |  |  | uasYcjinTQu5l9YnDQ+b4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 176 | GRANITE MASON SK
%R | 504238 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3085 | S.S.Balustrade | 8178 | 208 | 40 | 160 | 0 | 262.5 | 262.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-08 08:00 | 2014-07-30 17:00 |  | 2014-06-08 08:00 | 2014-06-30 17:00 | 2014-06-08 08:00 | 2014-06-30 17:00 | 2014-06-08 08:00 | 2014-06-30 17:00 | 2014-07-08 08:00 | 2014-07-30 17:00 |  | PT_Normal |  |  |  |  | tGTwrGF9RFKo2QuqIK0P+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 262.5 | LABOR- SUBCONTRACTOR
%R | 504239 | 6359 | 125401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARGF3095 | Final Painting | 8178 | 168 | 0 | 200 | 0 | 5425.75 | 5425.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | Arw96XWrQVyma+He488UWg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31900 | N | N | 10 | GROUND FLOOR |  | 125398 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 5425.75 | LABOR- SUBCONTRACTOR
%R | 504240 | 6359 | 125403 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARRF3630 | Leveling Screed for Waterproofing | 8164 | 168 | 0 | 200 | 0 | 800 | 800 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-04 08:00 | 2014-07-02 17:00 |  | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-06-04 08:00 | 2014-07-02 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31940 | N | N | 10 | ROOF |  | 125402 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 800 | SCREED MASON SK
%R | 504241 | 6359 | 125403 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARRF3635 | Laying of Waterproofing Membrane | 8178 | 168 | 0 | 200 | 0 | 1138.5 | 1138.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-08 08:00 | 2014-07-06 17:00 |  | 2014-05-14 08:00 | 2014-06-11 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 | 2014-06-08 08:00 | 2014-07-06 17:00 |  | PT_Normal |  |  |  |  | Lu6ZRFyOR9SIG82D/U8+3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31940 | N | N | 10 | ROOF |  | 125402 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1138.5 | LABOR- SUBCONTRACTOR
%R | 504242 | 6359 | 125403 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARRF3640 | Installation of Insulation & Protection | 8178 | 168 | 0 | 200 | 0 | 1408 | 1408 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-07-10 17:00 |  | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 |  | PT_Normal |  |  |  |  | CTpcrlz6T0y20EBvyj6gYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31940 | N | N | 10 | ROOF |  | 125402 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1408 | LABOR- SUBCONTRACTOR
%R | 504243 | 6359 | 125403 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 168 | 0 | 200 | 0 | 688.25 | 688.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | U5D37KqJRv28H6RptK6UaA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31940 | N | N | 10 | ROOF |  | 125402 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 688.25 | TILE MASON SK
%R | 504244 | 6359 | 125403 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 168 | 0 | 160 | 0 | 616 | 616 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-10 08:00 | 2014-08-05 17:00 |  | 2014-06-16 08:00 | 2014-07-08 17:00 | 2014-06-16 08:00 | 2014-07-08 17:00 | 2014-06-16 08:00 | 2014-07-08 17:00 | 2014-07-10 08:00 | 2014-08-05 17:00 |  | PT_Normal |  |  |  |  | 3X1SZCbKTy+jljyJ37SOmw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31940 | N | N | 10 | ROOF |  | 125402 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 616 | LABOR- SUBCONTRACTOR
%R | 504245 | 6359 | 125403 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 168 | 0 | 200 | 0 | 1046.5 | 1046.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-25 08:00 | 2014-07-23 17:00 |  | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-25 08:00 | 2014-07-23 17:00 |  | PT_Normal |  |  |  |  | aj5CFRXxTM20lZJZuWRTDw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31940 | N | N | 10 | ROOF |  | 125402 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1046.5 | LABOR- SUBCONTRACTOR
%R | 504246 | 6359 | 125403 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6ARRF3660 | Installation of Access Ladder | 8178 | 208 | 208 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-28 08:00 | 2014-08-17 17:00 |  | 2014-06-28 08:00 | 2014-07-14 17:00 | 2014-06-28 08:00 | 2014-07-14 17:00 | 2014-06-28 08:00 | 2014-07-14 17:00 | 2014-07-28 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | pZcH50okR1OtUp8ySs6eyg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31940 | N | N | 10 | ROOF |  | 125402 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 176 | LABOR- SUBCONTRACTOR
%R | 504247 | 6359 | 125404 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6AREL3665 | External Plastering | 8169 | 376 | 0 | 200 | 0 | 14275 | 14275 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-21 08:00 | 2014-07-19 17:00 |  | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-06-21 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | n8dr3dvhTEOnzvWveiLt/w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31950 | N | N | 15 | ELEVATION |  | 125402 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 14275 | PLASTER MASON SK
%R | 504248 | 6359 | 125404 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6AREL3670 | External stone cladding works | 8170 | 392 | 0 | 160 | 0 | 990 | 990 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-10 08:00 | 2014-08-05 17:00 |  | 2014-05-14 08:00 | 2014-06-05 17:00 | 2014-05-14 08:00 | 2014-06-05 17:00 | 2014-05-14 08:00 | 2014-06-05 17:00 | 2014-07-10 08:00 | 2014-08-05 17:00 |  | PT_Normal |  |  |  |  | U9YJ9WUEQOSm5oZ6MvBuIw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31950 | N | N | 15 | ELEVATION |  | 125402 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 990 | TILE MASON SK
%R | 504249 | 6359 | 125404 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ6AREL3680 | External Painting | 8178 | 392 | 40 | 160 | 0 | 3784 | 3784 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-22 08:00 | 2014-08-17 17:00 |  | 2014-05-26 08:00 | 2014-06-17 17:00 | 2014-05-26 08:00 | 2014-06-17 17:00 | 2014-05-26 08:00 | 2014-06-17 17:00 | 2014-07-22 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | Uh+BuAdjT4KFadIXm0B4Gg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31950 | N | N | 15 | ELEVATION |  | 125402 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 3784 | LABOR- SUBCONTRACTOR
%R | 504250 | 6359 | 125406 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-10-18 08:00 | 2014-11-15 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | aiIbJMZeTg2GomDfukewFw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32870 | N | N | 30 | TESTING AND COMMISSIONING |  | 125405 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 504251 | 6359 | 125406 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-10-18 08:00 | 2014-11-15 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | JPdBqdKVQkGe6wWDP/Knew |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32870 | N | N | 30 | TESTING AND COMMISSIONING |  | 125405 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 504252 | 6359 | 125406 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 0 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-10-18 08:00 | 2014-11-15 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | t7ZSegHrTPWujvpO526wLQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32870 | N | N | 30 | TESTING AND COMMISSIONING |  | 125405 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 504253 | 6359 | 125408 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8HDEX5090 | kerb works | 8173 | 128 | 0 | 160 | 0 | 344 | 344 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-16 08:00 | 2014-09-07 17:00 |  | 2014-07-24 08:00 | 2014-08-19 17:00 | 2014-07-24 08:00 | 2014-08-19 17:00 | 2014-07-24 08:00 | 2014-08-19 17:00 | 2014-08-16 08:00 | 2014-09-07 17:00 |  | PT_Normal |  |  |  |  | FO4t4h7sSHGC7JBy6Wx0ZQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32850 | N | N | 20 | HARD LANDSCAPING |  | 125407 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 344 | KERBSTONE MASON SK
%R | 504254 | 6359 | 125408 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8HDEX5095 | Cobble Stone Works | 8170 | 128 | 0 | 160 | 0 | 200 | 200 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-27 08:00 | 2014-09-18 17:00 |  | 2014-08-09 08:00 | 2014-08-31 17:00 | 2014-08-09 08:00 | 2014-08-31 17:00 | 2014-08-09 08:00 | 2014-08-31 17:00 | 2014-08-27 08:00 | 2014-09-18 17:00 |  | PT_Normal |  |  |  |  | 6sxH0gV8Sbikqpc8DkXmXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32850 | N | N | 20 | HARD LANDSCAPING |  | 125407 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 200 | TILE MASON SK
%R | 504255 | 6359 | 125408 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8HDEX5100 | Interlock works | 8174 | 128 | 0 | 160 | 0 | 232 | 232 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-03 08:00 | 2014-09-25 17:00 |  | 2014-08-16 08:00 | 2014-09-07 17:00 | 2014-08-16 08:00 | 2014-09-07 17:00 | 2014-08-16 08:00 | 2014-09-07 17:00 | 2014-09-03 08:00 | 2014-09-25 17:00 |  | PT_Normal |  |  |  |  | 5PWg2UXISlmDq0un1jmWJw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32850 | N | N | 20 | HARD LANDSCAPING |  | 125407 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 232 | INTERLOCK MASON SK
%R | 504256 | 6359 | 125409 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 440 | 168 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-08 08:00 | 2014-12-06 17:00 |  | 2014-09-02 08:00 | 2014-09-30 17:00 | 2014-09-02 08:00 | 2014-09-30 17:00 | 2014-09-02 08:00 | 2014-09-30 17:00 | 2014-11-08 08:00 | 2014-12-06 17:00 |  | PT_Normal |  |  |  |  | i1+ySOIbTSqEBCqgHikRig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32830 | N | N | 10 | MISCELLANEOUS |  | 125407 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 400 | LABOR- SUBCONTRACTOR
%R | 504257 | 6359 | 125409 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8MSEX5020 | Construction Entrance Ramp | 8164 | 128 | 0 | 200 | 0 | 656 | 656 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-29 08:00 | 2014-08-30 17:00 |  | 2014-07-10 08:00 | 2014-08-11 17:00 | 2014-07-10 08:00 | 2014-08-11 17:00 | 2014-07-10 08:00 | 2014-08-11 17:00 | 2014-07-29 08:00 | 2014-08-30 17:00 |  | PT_Normal |  |  |  |  | bq3jXblWR/+7S197F6SpyA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32830 | N | N | 10 | MISCELLANEOUS |  | 125407 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 328 | SCREED MASON SK
%R | 504258 | 6359 | 125409 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8MSEX5025 | SS.Handrails and Balustrades | 8178 | 152 | 0 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-23 08:00 | 2014-09-14 17:00 |  | 2014-07-28 08:00 | 2014-08-23 17:00 | 2014-07-28 08:00 | 2014-08-23 17:00 | 2014-07-28 08:00 | 2014-08-23 17:00 | 2014-08-23 08:00 | 2014-09-14 17:00 |  | PT_Normal |  |  |  |  | nRrU3peySROYnrw8BlQ7yA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32830 | N | N | 10 | MISCELLANEOUS |  | 125407 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 56 | LABOR- SUBCONTRACTOR
%R | 504259 | 6359 | 125409 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8MSEX5015 | Construction of grease Trap | 8178 | 64 | 0 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-02 08:00 | 2014-07-24 17:00 |  | 2014-06-23 08:00 | 2014-07-15 17:00 | 2014-06-23 08:00 | 2014-07-15 17:00 | 2014-06-23 08:00 | 2014-07-15 17:00 | 2014-07-02 08:00 | 2014-07-24 17:00 |  | PT_Normal |  |  |  |  | ++1xX90gQ7CFzrDSK8K/dg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32830 | N | N | 10 | MISCELLANEOUS |  | 125407 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 56 | LABOR- SUBCONTRACTOR
%R | 504260 | 6359 | 125409 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8MSEX5000 | Construction of Manholes | 8172 | 64 | 0 | 200 | 0 | 528 | 528 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-29 08:00 | 2014-06-26 17:00 |  | 2014-05-20 08:00 | 2014-06-17 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 |  | PT_Normal |  |  |  |  | bys5ywvDSee8O8XULsottA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32830 | N | N | 10 | MISCELLANEOUS |  | 125407 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 528 | MANHOLES SK
%R | 504261 | 6359 | 125409 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8MSEX5005 | Construction of Soak pit, Chambers | 8172 | 64 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-07-10 17:00 |  | 2014-06-03 08:00 | 2014-07-01 17:00 | 2014-06-03 08:00 | 2014-07-01 17:00 | 2014-06-03 08:00 | 2014-07-01 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 |  | PT_Normal |  |  |  |  | 5ptPo+GGTXunjd0J9WsKgA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32830 | N | N | 10 | MISCELLANEOUS |  | 125407 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 176 | MANHOLES SK
%R | 504262 | 6359 | 125409 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8MSEX5010 | Telephone cable laying | 8177 | 64 | 0 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-26 08:00 | 2014-08-26 17:00 |  | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-26 08:00 | 2014-08-26 17:00 |  | PT_Normal |  |  |  |  | jYMwF/l2RwKnE19axZ31Zw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32830 | N | N | 10 | MISCELLANEOUS |  | 125407 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 250 | LABOR - CIVIL
%R | 504263 | 6359 | 125410 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8SLEX5105 | Laying of Grass/ green area | 8178 | 128 | 0 | 200 | 0 | 2744 | 2744 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-09 08:00 | 2014-10-07 17:00 |  | 2014-08-21 08:00 | 2014-09-18 17:00 | 2014-08-21 08:00 | 2014-09-18 17:00 | 2014-08-21 08:00 | 2014-09-18 17:00 | 2014-09-09 08:00 | 2014-10-07 17:00 |  | PT_Normal |  |  |  |  | QURRtM7/R4C1dCGEwm99rQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32860 | N | N | 25 | SOFT LANDSCAPING |  | 125407 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 2744 | LABOR- SUBCONTRACTOR
%R | 504264 | 6359 | 125410 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8SLEX5110 | Laying of Palm tree | 8178 | 128 | 128 | 200 | 0 | 168 | 168 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | CrBXSZF4ShCO5p7dBH24RQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32860 | N | N | 25 | SOFT LANDSCAPING |  | 125407 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 168 | LABOR- SUBCONTRACTOR
%R | 504265 | 6359 | 125411 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8WEEX5030 | Excavation | 8177 | 344 | 0 | 160 | 0 | 64 | 64 | 160 | 40 | 0 | 40 |  |  |  | 2014-07-27 08:00 | 2014-08-21 17:00 |  | 2014-06-07 08:00 | 2014-06-29 17:00 | 2014-06-07 08:00 | 2014-06-29 17:00 | 2014-06-07 08:00 | 2014-06-29 17:00 | 2014-07-27 08:00 | 2014-08-21 17:00 |  | PT_Normal |  |  |  |  | S/lVMDLHQ3m/XigjKV9O6g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32840 | N | N | 15 | WATER TANK ENCLOSURE |  | 125407 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 64 | LABOR - CIVIL
%R | 504266 | 6359 | 125411 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8WEEX5035 | Construction of Raft | 8165 | 344 | 0 | 200 | 0 | 840 | 840 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-05 08:00 | 2014-09-02 17:00 |  | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-08-05 08:00 | 2014-09-02 17:00 |  | PT_Normal |  |  |  |  | VhnxPXxoTt+VvqXIpyBtgQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32840 | N | N | 15 | WATER TANK ENCLOSURE |  | 125407 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 840 | STEEL FIXERS SK
%R | 504267 | 6359 | 125411 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8WEEX5040 | Block works & Plastering | 8168 | 344 | 0 | 200 | 0 | 512 | 512 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-14 08:00 | 2014-09-11 17:00 |  | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-08-14 08:00 | 2014-09-11 17:00 |  | PT_Normal |  |  |  |  | eWUnOAgwRiSl+wSxLhOXDA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32840 | N | N | 15 | WATER TANK ENCLOSURE |  | 125407 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 512 | BLOCK MASON SK
%R | 504268 | 6359 | 125411 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8WEEX5045 | Flooring & Painting | 8178 | 344 | 192 | 200 | 0 | 232 | 232 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-21 08:00 | 2014-09-18 17:00 |  | 2014-06-29 08:00 | 2014-07-27 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 | 2014-08-21 08:00 | 2014-09-18 17:00 |  | PT_Normal |  |  |  |  | cFN0Op5+SsSljJ81AQV5Kw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32840 | N | N | 15 | WATER TANK ENCLOSURE |  | 125407 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 232 | LABOR- SUBCONTRACTOR
%R | 504269 | 6359 | 125411 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8WEEX5050 | Installation of Steel Gate | 8178 | 152 | 72 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-03 08:00 | 2014-09-25 17:00 |  | 2014-08-12 08:00 | 2014-09-03 17:00 | 2014-08-12 08:00 | 2014-09-03 17:00 | 2014-08-12 08:00 | 2014-09-03 17:00 | 2014-09-03 08:00 | 2014-09-25 17:00 |  | PT_Normal |  |  |  |  | u+UcWAe9TZKxLauksVDOZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32840 | N | N | 15 | WATER TANK ENCLOSURE |  | 125407 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 56 | LABOR- SUBCONTRACTOR
%R | 504270 | 6359 | 125411 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 80 | 0 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-09 08:00 | 2014-10-07 17:00 |  | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-09-09 08:00 | 2014-10-07 17:00 |  | PT_Normal |  |  |  |  | RIg225RFRjWSvYNfRd8XkA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32840 | N | N | 15 | WATER TANK ENCLOSURE |  | 125407 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 336 | LABOR- SUBCONTRACTOR
%R | 504271 | 6359 | 125411 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 72 | 0 | 200 | 0 | 203.2 | 203.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-09-06 08:00 | 2014-10-04 17:00 | 2014-09-06 08:00 | 2014-10-04 17:00 | 2014-09-06 08:00 | 2014-10-04 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | 82SnrJMhQt2OGVYBUVnUeA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32840 | N | N | 15 | WATER TANK ENCLOSURE |  | 125407 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 203.2 | LABOR- SUBCONTRACTOR
%R | 504272 | 6359 | 125414 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 32 | 0 | 200 | 0 | 16119.25 | 16119.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-08 08:00 | 2014-05-06 17:00 |  | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 |  | PT_Normal |  |  |  |  | 6AjlTL9xQZes67WQY4atTw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32580 | N | N | 15 | FIRST FLOORS |  | 125413 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 16119.25 | STEEL FIXERS SK
%R | 504273 | 6359 | 125414 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 32 | 0 | 112 | 0 | 1141 | 1141 | 112 | 0 | 0 | 0 |  |  |  | 2014-04-24 08:00 | 2014-05-10 17:00 |  | 2014-04-20 08:00 | 2014-05-05 17:00 | 2014-04-20 08:00 | 2014-05-05 17:00 | 2014-04-20 08:00 | 2014-05-05 17:00 | 2014-04-24 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | NxVoqER5RXOyVQjB88NnTA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32580 | N | N | 15 | FIRST FLOORS |  | 125413 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1141 | CONCRETE MASON SK
%R | 504274 | 6359 | 125414 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STFF2020 | Column-Rebar & Formwork | 8165 | 16 | 0 | 200 | 0 | 3580.5 | 3580.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-12 08:00 | 2014-04-09 17:00 |  | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-12 08:00 | 2014-04-09 17:00 |  | PT_Normal |  |  |  |  | lUD8weHHTZqgb+mIPfsmIQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32580 | N | N | 15 | FIRST FLOORS |  | 125413 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 3580.5 | STEEL FIXERS SK
%R | 504275 | 6359 | 125414 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STFF2025 | Column-Concrete | 8167 | 32 | 0 | 192 | 0 | 224 | 224 | 192 | 0 | 0 | 0 |  |  |  | 2014-03-24 08:00 | 2014-04-20 17:00 |  | 2014-03-19 08:00 | 2014-04-15 17:00 | 2014-03-19 08:00 | 2014-04-15 17:00 | 2014-03-19 08:00 | 2014-04-15 17:00 | 2014-03-24 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | qqyG04P7SDqhj+71bN7x9w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32580 | N | N | 15 | FIRST FLOORS |  | 125413 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 224 | CONCRETE MASON SK
%R | 504276 | 6359 | 125415 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STGF2000 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 4046 | 4046 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-26 08:00 | 2014-02-24 17:00 |  | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 |  | PT_Normal |  |  |  |  | x4eotDLGTIeM6fXOW3h9cw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32570 | N | N | 10 | GROUND FLOOR |  | 125413 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 4046 | STEEL FIXERS SK
%R | 504277 | 6359 | 125415 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STGF2005 | Column-Concrete | 8167 | 16 | 0 | 192 | 0 | 255.5 | 255.5 | 192 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-03-05 17:00 |  | 2014-02-03 08:00 | 2014-03-03 17:00 | 2014-02-03 08:00 | 2014-03-03 17:00 | 2014-02-03 08:00 | 2014-03-03 17:00 | 2014-02-05 08:00 | 2014-03-05 17:00 |  | PT_Normal |  |  |  |  | vKZs2Z+1T6OEIjzMOhUI3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32570 | N | N | 10 | GROUND FLOOR |  | 125413 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 127.75 | CONCRETE MASON SK
%R | 504278 | 6359 | 125415 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 16 | 0 | 200 | 0 | 16829.75 | 16829.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-22 17:00 |  | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | h4VBXaf3SP6YE97OZMZ7/Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32570 | N | N | 10 | GROUND FLOOR |  | 125413 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 8414.875 | STEEL FIXERS SK
%R | 504279 | 6359 | 125415 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 16 | 0 | 112 | 0 | 1295 | 1295 | 112 | 0 | 0 | 0 |  |  |  | 2014-03-10 08:00 | 2014-03-25 17:00 |  | 2014-03-08 08:00 | 2014-03-23 17:00 | 2014-03-08 08:00 | 2014-03-23 17:00 | 2014-03-08 08:00 | 2014-03-23 17:00 | 2014-03-10 08:00 | 2014-03-25 17:00 |  | PT_Normal |  |  |  |  | lGthWsHLTHiWMhCc9dfsWA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32570 | N | N | 10 | GROUND FLOOR |  | 125413 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1295 | CONCRETE MASON SK
%R | 504280 | 6359 | 125416 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STRF2040 | Column-Rebar & Formwork | 8165 | 64 | 0 | 144 | 0 | 1205.75 | 1205.75 | 144 | 0 | 0 | 0 |  |  |  | 2014-05-01 08:00 | 2014-05-21 17:00 |  | 2014-04-22 08:00 | 2014-05-12 17:00 | 2014-04-22 08:00 | 2014-05-12 17:00 | 2014-04-22 08:00 | 2014-05-12 17:00 | 2014-05-01 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | bJHAzTRCTwav89zPsm2iuQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32590 | N | N | 20 | ROOF |  | 125413 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1205.75 | STEEL FIXERS SK
%R | 504281 | 6359 | 125416 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STRF2045 | Column-Concrete | 8167 | 64 | 0 | 136 | 0 | 52.5 | 52.5 | 136 | 0 | 0 | 0 |  |  |  | 2014-05-05 08:00 | 2014-05-24 17:00 |  | 2014-04-26 08:00 | 2014-05-14 17:00 | 2014-04-26 08:00 | 2014-05-14 17:00 | 2014-04-26 08:00 | 2014-05-14 17:00 | 2014-05-05 08:00 | 2014-05-24 17:00 |  | PT_Normal |  |  |  |  | d38H8lbmScCLaDCeiG5ZTQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32590 | N | N | 20 | ROOF |  | 125413 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 52.5 | CONCRETE MASON SK
%R | 504282 | 6359 | 125416 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STRF2050 | Slab-Rebar & Formwork - Head Room | 8165 | 64 | 0 | 160 | 0 | 2735.25 | 2735.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-07 08:00 | 2014-05-29 17:00 |  | 2014-04-28 08:00 | 2014-05-20 17:00 | 2014-04-28 08:00 | 2014-05-20 17:00 | 2014-04-28 08:00 | 2014-05-20 17:00 | 2014-05-07 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | fFWUykmSRBudxK1TXhD6SA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32590 | N | N | 20 | ROOF |  | 125413 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 2735.25 | STEEL FIXERS SK
%R | 504283 | 6359 | 125416 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STRF2055 | Slab-Concrete-Head room | 8167 | 64 | 0 | 104 | 0 | 252 | 252 | 104 | 0 | 0 | 0 |  |  |  | 2014-05-18 08:00 | 2014-06-01 17:00 |  | 2014-05-08 08:00 | 2014-05-22 17:00 | 2014-05-08 08:00 | 2014-05-22 17:00 | 2014-05-08 08:00 | 2014-05-22 17:00 | 2014-05-18 08:00 | 2014-06-01 17:00 |  | PT_Normal |  |  |  |  | zwD5p08+Rx+BcQG3oYWqvQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32590 | N | N | 20 | ROOF |  | 125413 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 252 | CONCRETE MASON SK
%R | 504284 | 6359 | 125416 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STRF2060 | Construction of Parapets | 8168 | 448 | 32 | 200 | 0 | 2200 | 2200 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-15 08:00 | 2014-08-16 17:00 |  | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-07-15 08:00 | 2014-08-16 17:00 |  | PT_Normal |  |  |  |  | cZ74FfNyQ7+bUpd53TTwRw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32590 | N | N | 20 | ROOF |  | 125413 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 2200 | BLOCK MASON SK
%R | 504285 | 6359 | 125416 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STRF2065 | Construction of up stands/Plinth | 8165 | 416 | 0 | 200 | 0 | 554.75 | 554.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-21 08:00 | 2014-08-21 17:00 |  | 2014-05-21 08:00 | 2014-06-18 17:00 | 2014-05-21 08:00 | 2014-06-18 17:00 | 2014-05-21 08:00 | 2014-06-18 17:00 | 2014-07-21 08:00 | 2014-08-21 17:00 |  | PT_Normal |  |  |  |  | ecifZK+cSS6wTHqsBOj7yg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32590 | N | N | 20 | ROOF |  | 125413 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 554.75 | STEEL FIXERS SK
%R | 504286 | 6359 | 125418 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STUG1005 | Footing Antitermite | 8178 | 0 | 0 | 184 | 0 | 1584 | 1584 | 184 | 0 | 0 | 0 |  |  |  | 2013-09-22 08:00 | 2013-10-20 17:00 |  | 2013-09-22 08:00 | 2013-10-20 17:00 | 2013-09-22 08:00 | 2013-10-20 17:00 | 2013-09-22 08:00 | 2013-10-20 17:00 | 2013-09-22 08:00 | 2013-10-20 17:00 |  | PT_Normal |  |  |  |  | 2vP+qCJjRniqhgYaTz3yQA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32550 | N | N | 10 | UPTO GRADE SLAB |  | 125417 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1584 | LABOR- SUBCONTRACTOR
%R | 504287 | 6359 | 125418 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STUG1010 | Footing Blinding | 8163 | 0 | 0 | 184 | 0 | 794.5 | 794.5 | 184 | 0 | 0 | 0 |  |  |  | 2013-09-25 08:00 | 2013-10-23 17:00 |  | 2013-09-25 08:00 | 2013-10-23 17:00 | 2013-09-25 08:00 | 2013-10-23 17:00 | 2013-09-25 08:00 | 2013-10-23 17:00 | 2013-09-25 08:00 | 2013-10-23 17:00 |  | PT_Normal |  |  |  |  | l9JvoRtCRLO28sLxrMtzeA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32550 | N | N | 10 | UPTO GRADE SLAB |  | 125417 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 794.5 | BLINDING MASON SK
%R | 504288 | 6359 | 125418 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STUG1015 | Footing Waterproofing & Screed | 8164 | 0 | 0 | 200 | 0 | 574.75 | 574.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-01 08:00 | 2013-10-31 17:00 |  | 2013-10-01 08:00 | 2013-10-31 17:00 | 2013-10-01 08:00 | 2013-10-31 17:00 | 2013-10-01 08:00 | 2013-10-31 17:00 | 2013-10-01 08:00 | 2013-10-31 17:00 |  | PT_Normal |  |  |  |  | gJi9ltTdQ6yLNEpUYFL6JQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32550 | N | N | 10 | UPTO GRADE SLAB |  | 125417 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 574.75 | SCREED MASON SK
%R | 504289 | 6359 | 125418 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STUG1020 | Construction of foundations | 8165 | 0 | 0 | 160 | 0 | 7778.75 | 7778.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-10-16 08:00 | 2013-11-10 17:00 |  | 2013-10-16 08:00 | 2013-11-10 17:00 | 2013-10-16 08:00 | 2013-11-10 17:00 | 2013-10-16 08:00 | 2013-11-10 17:00 | 2013-10-16 08:00 | 2013-11-10 17:00 |  | PT_Normal |  |  |  |  | i/HJvJSETNyuRgWRD62vSg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32550 | N | N | 10 | UPTO GRADE SLAB |  | 125417 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 7778.75 | STEEL FIXERS SK
%R | 504290 | 6359 | 125418 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STUG1025 | Construction of neck of columns | 8165 | 0 | 0 | 200 | 0 | 1606.5 | 1606.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-28 08:00 | 2013-11-25 17:00 |  | 2013-10-28 08:00 | 2013-11-25 17:00 | 2013-10-28 08:00 | 2013-11-25 17:00 | 2013-10-28 08:00 | 2013-11-25 17:00 | 2013-10-28 08:00 | 2013-11-25 17:00 |  | PT_Normal |  |  |  |  | 5JHTLtXDRQyZdCk8jg8r7Q |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32550 | N | N | 10 | UPTO GRADE SLAB |  | 125417 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1606.5 | STEEL FIXERS SK
%R | 504291 | 6359 | 125418 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STUG1030 | Waterproofing Footing & Neck Column | 8178 | 0 | 0 | 200 | 0 | 516 | 516 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-06 08:00 | 2013-12-04 17:00 |  | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-11-06 08:00 | 2013-12-04 17:00 |  | PT_Normal |  |  |  |  | jTouisvHTuuWQJuI3rz2KQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32550 | N | N | 10 | UPTO GRADE SLAB |  | 125417 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 516 | LABOR- SUBCONTRACTOR
%R | 504292 | 6359 | 125418 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 0 | 0 | 200 | 0 | 1041 | 1041 | 200 | 825 | 0 | 825 |  |  |  | 2013-11-20 08:00 | 2013-12-19 17:00 |  | 2013-11-20 08:00 | 2013-12-19 17:00 | 2013-11-20 08:00 | 2013-12-19 17:00 | 2013-11-20 08:00 | 2013-12-19 17:00 | 2013-11-20 08:00 | 2013-12-19 17:00 |  | PT_Normal |  |  |  |  | lLk7/hTBS6STLwdaDznAnQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32550 | N | N | 10 | UPTO GRADE SLAB |  | 125417 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1041 | LABOR - CIVIL
%R | 504293 | 6359 | 125418 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STUG1040 | Construction of Grade Beams | 8163 | 0 | 0 | 200 | 0 | 7568.75 | 7568.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-07 08:00 | 2014-01-05 17:00 |  | 2013-12-07 08:00 | 2014-01-05 17:00 | 2013-12-07 08:00 | 2014-01-05 17:00 | 2013-12-07 08:00 | 2014-01-05 17:00 | 2013-12-07 08:00 | 2014-01-05 17:00 |  | PT_Normal |  |  |  |  | HTt0OhMMRkKFrk+fkqRPfw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32550 | N | N | 10 | UPTO GRADE SLAB |  | 125417 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 7568.75 | BLINDING MASON SK
%R | 504294 | 6359 | 125418 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STUG1045 | Construction of slab on grade | 8163 | 0 | 0 | 200 | 0 | 4422 | 4422 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-09 08:00 | 2014-02-06 17:00 |  | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-01-09 08:00 | 2014-02-06 17:00 |  | PT_Normal |  |  |  |  | xacrUYbhQZ+4xuGI0VQ/vQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32550 | N | N | 10 | UPTO GRADE SLAB |  | 125417 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 4422 | BLINDING MASON SK
%R | 504295 | 6359 | 125418 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8STUG1000 | Footing Excavation | 8177 | 0 | 0 | 200 | 0 | 1114 | 1114 | 200 | 524 | 0 | 524 |  |  |  | 2013-09-10 08:00 | 2013-10-08 17:00 |  | 2013-09-10 08:00 | 2013-10-08 17:00 | 2013-09-10 08:00 | 2013-10-08 17:00 | 2013-09-10 08:00 | 2013-10-08 17:00 | 2013-09-10 08:00 | 2013-10-08 17:00 |  | PT_Normal |  |  |  |  | GY12/8PGT8ejIpdSNgt1FA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32550 | N | N | 10 | UPTO GRADE SLAB |  | 125417 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1114 | LABOR - CIVIL
%R | 504296 | 6359 | 125421 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 448 | 240 | 120 | 0 | 110.4 | 110.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-01 08:00 | 2014-09-17 17:00 |  | 2014-06-24 08:00 | 2014-07-10 17:00 | 2014-06-24 08:00 | 2014-07-10 17:00 | 2014-06-24 08:00 | 2014-07-10 17:00 | 2014-09-01 08:00 | 2014-09-17 17:00 |  | PT_Normal |  |  |  |  | jxiDGErbRsyZUKxNbYYJoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32760 | N | N | 20 | ROOF |  | 125420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 110.4 | LABOR- SUBCONTRACTOR
%R | 504297 | 6359 | 125421 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8PLRF4350 | Installation of Rain water Pipes | 8178 | 208 | 80 | 120 | 0 | 67.2 | 67.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-09-27 17:00 |  | 2014-08-11 08:00 | 2014-08-27 17:00 | 2014-08-11 08:00 | 2014-08-27 17:00 | 2014-08-11 08:00 | 2014-08-27 17:00 | 2014-09-10 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | gPMI3cupSeWA61K/7r0b7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32760 | N | N | 20 | ROOF |  | 125420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504298 | 6359 | 125421 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 8 | 0 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-09-15 08:00 | 2014-10-15 17:00 | 2014-09-15 08:00 | 2014-10-15 17:00 | 2014-09-15 08:00 | 2014-10-15 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | GKm8uuEVTB+AX4o5IYtg/Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32760 | N | N | 20 | ROOF |  | 125420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 168 | LABOR- SUBCONTRACTOR
%R | 504299 | 6359 | 125422 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 0 | 0 | 144 | 0 | 441.6 | 441.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-06-25 17:00 |  | 2014-06-05 08:00 | 2014-06-25 17:00 | 2014-06-05 08:00 | 2014-06-25 17:00 | 2014-06-05 08:00 | 2014-06-25 17:00 | 2014-06-05 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | wAnSIG94TAOZK0UPR1x2Zw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32750 | N | N | 15 | FIRST FLOORS |  | 125420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 441.6 | LABOR- SUBCONTRACTOR
%R | 504300 | 6359 | 125422 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8PLFF4330 | Installation of Drainage pipes & testing | 8178 | 176 | 56 | 144 | 0 | 177.6 | 177.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-07-01 08:00 | 2014-07-21 17:00 |  | 2014-06-05 08:00 | 2014-06-25 17:00 | 2014-06-05 08:00 | 2014-06-25 17:00 | 2014-06-05 08:00 | 2014-06-25 17:00 | 2014-07-01 08:00 | 2014-07-21 17:00 |  | PT_Normal |  |  |  |  | u48JE/VnRRu/L/0SlW2xzw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32750 | N | N | 15 | FIRST FLOORS |  | 125420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 177.6 | LABOR- SUBCONTRACTOR
%R | 504301 | 6359 | 125422 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8PLFF4335 | Sanitary Fittings & Accessories | 8178 | 40 | 0 | 160 | 0 | 67.2 | 67.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-21 17:00 |  | 2014-08-24 08:00 | 2014-09-15 17:00 | 2014-08-24 08:00 | 2014-09-15 17:00 | 2014-08-24 08:00 | 2014-09-15 17:00 | 2014-08-30 08:00 | 2014-09-21 17:00 |  | PT_Normal |  |  |  |  | 1SzKp+3AT6SW+sVIlZ/XoA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32750 | N | N | 15 | FIRST FLOORS |  | 125420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504302 | 6359 | 125422 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8PLFF4340 | Installation of Water Heater | 8178 | 40 | 32 | 120 | 0 | 67.2 | 67.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-09-27 17:00 |  | 2014-09-04 08:00 | 2014-09-21 17:00 | 2014-09-04 08:00 | 2014-09-21 17:00 | 2014-09-04 08:00 | 2014-09-21 17:00 | 2014-09-10 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | ri9ZtvwlQt+zCSDi5eZ7RA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32750 | N | N | 15 | FIRST FLOORS |  | 125420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504303 | 6359 | 125423 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 144 | 0 | 144 | 0 | 441.6 | 441.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-05-14 08:00 | 2014-06-03 17:00 |  | 2014-04-23 08:00 | 2014-05-13 17:00 | 2014-04-23 08:00 | 2014-05-13 17:00 | 2014-04-23 08:00 | 2014-05-13 17:00 | 2014-05-14 08:00 | 2014-06-03 17:00 |  | PT_Normal |  |  |  |  | 7datScGlR4qItF7ND7Cgag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32740 | N | N | 10 | GROUND FLOOR |  | 125420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 441.6 | LABOR- SUBCONTRACTOR
%R | 504304 | 6359 | 125423 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8PLGF4310 | Installation of Drainage pipes &testing | 8178 | 168 | 104 | 144 | 0 | 177.6 | 177.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-05-18 08:00 | 2014-06-07 17:00 |  | 2014-04-23 08:00 | 2014-05-13 17:00 | 2014-04-23 08:00 | 2014-05-13 17:00 | 2014-04-23 08:00 | 2014-05-13 17:00 | 2014-05-18 08:00 | 2014-06-07 17:00 |  | PT_Normal |  |  |  |  | BnmdSBaGT6+P5WsKR9l29A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32740 | N | N | 10 | GROUND FLOOR |  | 125420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 177.6 | LABOR- SUBCONTRACTOR
%R | 504305 | 6359 | 125423 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8PLGF4315 | Sanitary Fittings & Accessories | 8178 | 360 | 0 | 160 | 0 | 134.4 | 134.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-08 17:00 |  | 2014-07-22 08:00 | 2014-08-17 17:00 | 2014-07-22 08:00 | 2014-08-17 17:00 | 2014-07-22 08:00 | 2014-08-17 17:00 | 2014-09-16 08:00 | 2014-10-08 17:00 |  | PT_Normal |  |  |  |  | 3XJwgU6ZSlSUsh0FgjSQOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32740 | N | N | 10 | GROUND FLOOR |  | 125420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 504306 | 6359 | 125423 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8PLGF4320 | Installation of Water Heater | 8178 | 360 | 80 | 120 | 0 | 134.4 | 134.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-28 08:00 | 2014-10-16 17:00 |  | 2014-08-06 08:00 | 2014-08-23 17:00 | 2014-08-06 08:00 | 2014-08-23 17:00 | 2014-08-06 08:00 | 2014-08-23 17:00 | 2014-09-28 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | As6gCMSEQvKijujeuZxDOg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32740 | N | N | 10 | GROUND FLOOR |  | 125420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 504307 | 6359 | 125423 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 0 | 0 | 128 | 0 | 67.2 | 67.2 | 128 | 0 | 0 | 0 |  |  |  | 2013-12-31 08:00 | 2014-01-18 17:00 |  | 2013-12-31 08:00 | 2014-01-18 17:00 | 2013-12-31 08:00 | 2014-01-18 17:00 | 2013-12-31 08:00 | 2014-01-18 17:00 | 2013-12-31 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | WT/8neU9SjOUN2U1KcdN0g |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32740 | N | N | 10 | GROUND FLOOR |  | 125420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504308 | 6359 | 125425 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ACFF4615 | Installation AC Pipes | 8178 | 216 | 40 | 160 | 0 | 977.6 | 977.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-28 08:00 | 2014-08-23 17:00 |  | 2014-06-26 08:00 | 2014-07-19 17:00 | 2014-06-26 08:00 | 2014-07-19 17:00 | 2014-06-26 08:00 | 2014-07-19 17:00 | 2014-07-28 08:00 | 2014-08-23 17:00 |  | PT_Normal |  |  |  |  | sgYeaV28Rb+7MHXirhbUHg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32790 | N | N | 15 | FIRST FLOORS |  | 125424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 977.6 | LABOR- SUBCONTRACTOR
%R | 504309 | 6359 | 125425 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ACFF4620 | Fixing of Ventilation Equipments | 8178 | 16 | 0 | 200 | 0 | 113.6 | 113.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-19 08:00 | 2014-09-16 17:00 |  | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-19 08:00 | 2014-09-16 17:00 |  | PT_Normal |  |  |  |  | /pbvJmv4SYeWjSA2YVk3KQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32790 | N | N | 15 | FIRST FLOORS |  | 125424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 113.6 | LABOR- SUBCONTRACTOR
%R | 504310 | 6359 | 125425 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ACFF4625 | Fixing of Split AC | 8178 | 16 | 0 | 160 | 0 | 296 | 296 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-09 08:00 | 2014-10-01 17:00 |  | 2014-09-07 08:00 | 2014-09-29 17:00 | 2014-09-07 08:00 | 2014-09-29 17:00 | 2014-09-07 08:00 | 2014-09-29 17:00 | 2014-09-09 08:00 | 2014-10-01 17:00 |  | PT_Normal |  |  |  |  | lju983JGToisWopOaAqp9A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32790 | N | N | 15 | FIRST FLOORS |  | 125424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 296 | LABOR- SUBCONTRACTOR
%R | 504311 | 6359 | 125426 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ACGF4600 | Installation AC Pipes | 8178 | 392 | 40 | 160 | 0 | 977.6 | 977.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-09 08:00 | 2014-07-31 17:00 |  | 2014-05-13 08:00 | 2014-06-04 17:00 | 2014-05-13 08:00 | 2014-06-04 17:00 | 2014-05-13 08:00 | 2014-06-04 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 |  | PT_Normal |  |  |  |  | OFKbYILeSD+jQod5WppcQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32780 | N | N | 10 | GROUND FLOOR |  | 125424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 977.6 | LABOR- SUBCONTRACTOR
%R | 504312 | 6359 | 125426 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ACGF4605 | Fixing of Ventilation Equipments | 8178 | 256 | 0 | 200 | 0 | 182.4 | 182.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-14 08:00 | 2014-09-11 17:00 |  | 2014-07-05 08:00 | 2014-08-05 17:00 | 2014-07-05 08:00 | 2014-08-05 17:00 | 2014-07-05 08:00 | 2014-08-05 17:00 | 2014-08-14 08:00 | 2014-09-11 17:00 |  | PT_Normal |  |  |  |  | /OFSYGB9TNSWvziz32ylrQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32780 | N | N | 10 | GROUND FLOOR |  | 125424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 91.2 | LABOR- SUBCONTRACTOR
%R | 504313 | 6359 | 125426 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ACGF4610 | Fixing of Split AC | 8178 | 256 | 40 | 160 | 0 | 296 | 296 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-04 08:00 | 2014-09-27 17:00 |  | 2014-07-26 08:00 | 2014-08-20 17:00 | 2014-07-26 08:00 | 2014-08-20 17:00 | 2014-07-26 08:00 | 2014-08-20 17:00 | 2014-09-04 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | MvKU7xN6QeimBjkuE4Jw2w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32780 | N | N | 10 | GROUND FLOOR |  | 125424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 296 | LABOR- SUBCONTRACTOR
%R | 504314 | 6359 | 125427 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ACRF4630 | Installation of Refrigerant Pipes | 8178 | 272 | 0 | 200 | 0 | 409.6 | 409.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-10-08 17:00 |  | 2014-07-29 08:00 | 2014-08-30 17:00 | 2014-07-29 08:00 | 2014-08-30 17:00 | 2014-07-29 08:00 | 2014-08-30 17:00 | 2014-09-10 08:00 | 2014-10-08 17:00 |  | PT_Normal |  |  |  |  | K6YrPrtHSIeWALYBzMdCGQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32800 | N | N | 20 | ROOF |  | 125424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 204.8 | LABOR- SUBCONTRACTOR
%R | 504315 | 6359 | 125427 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ACRF4635 | Installation of Condensing Unit | 8178 | 24 | 0 | 200 | 0 | 568 | 568 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-09-13 08:00 | 2014-10-13 17:00 | 2014-09-13 08:00 | 2014-10-13 17:00 | 2014-09-13 08:00 | 2014-10-13 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | 7qaCBP4CSw+2zJ4tK8DooA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32800 | N | N | 20 | ROOF |  | 125424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 284 | LABOR- SUBCONTRACTOR
%R | 504316 | 6359 | 125429 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 88 | 0 | 200 | 0 | 1222.4 | 1222.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-07 08:00 | 2014-07-05 17:00 |  | 2014-05-25 08:00 | 2014-06-22 17:00 | 2014-05-25 08:00 | 2014-06-22 17:00 | 2014-05-25 08:00 | 2014-06-22 17:00 | 2014-06-07 08:00 | 2014-07-05 17:00 |  | PT_Normal |  |  |  |  | bnvIYRLxSmmJXuzed2YYcg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32710 | N | N | 15 | FIRST FLOORS |  | 125428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1222.4 | LABOR- SUBCONTRACTOR
%R | 504317 | 6359 | 125429 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ELFF4040 | Cable tray & trunking installation | 8178 | 232 | 16 | 160 | 0 | 1318.4 | 1318.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-09 08:00 | 2014-07-31 17:00 |  | 2014-06-05 08:00 | 2014-06-28 17:00 | 2014-06-05 08:00 | 2014-06-28 17:00 | 2014-06-05 08:00 | 2014-06-28 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 |  | PT_Normal |  |  |  |  | TJbBaVvqRZWiCbqNOTzcsw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32710 | N | N | 15 | FIRST FLOORS |  | 125428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1318.4 | LABOR- SUBCONTRACTOR
%R | 504318 | 6359 | 125429 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ELFF4045 | Installation of wiring & Main Cabling | 8178 | 216 | 0 | 200 | 0 | 296 | 296 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-17 08:00 | 2014-08-18 17:00 |  | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-07-17 08:00 | 2014-08-18 17:00 |  | PT_Normal |  |  |  |  | auShZ20fQNSccyQJ5lCkFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32710 | N | N | 15 | FIRST FLOORS |  | 125428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 296 | LABOR- SUBCONTRACTOR
%R | 504319 | 6359 | 125429 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 24 | 16 | 160 | 0 | 227.2 | 227.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-24 08:00 | 2014-09-15 17:00 |  | 2014-08-20 08:00 | 2014-09-11 17:00 | 2014-08-20 08:00 | 2014-09-11 17:00 | 2014-08-20 08:00 | 2014-09-11 17:00 | 2014-08-24 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | yKYEV3grTXqJY2ziQb3CIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32710 | N | N | 15 | FIRST FLOORS |  | 125428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 227.2 | LABOR- SUBCONTRACTOR
%R | 504320 | 6359 | 125429 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 8 | 0 | 200 | 0 | 1651.2 | 1651.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-27 17:00 |  | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-30 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | MvXMiGuPSHWmRTz+uNcZHw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32710 | N | N | 15 | FIRST FLOORS |  | 125428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1651.2 | LABOR- SUBCONTRACTOR
%R | 504321 | 6359 | 125429 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 8 | 0 | 200 | 0 | 1008 | 1008 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | Smu5yxIESxCDSZMmlkRusA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32710 | N | N | 15 | FIRST FLOORS |  | 125428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1008 | LABOR- SUBCONTRACTOR
%R | 504322 | 6359 | 125429 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ELFF4050 | Installation of Telephone System | 8178 | 64 | 56 | 200 | 0 | 451.2 | 451.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-27 08:00 | 2014-09-24 17:00 |  | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-27 08:00 | 2014-09-24 17:00 |  | PT_Normal |  |  |  |  | dFLfszmCQD+fAm6HyY/9dw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32710 | N | N | 15 | FIRST FLOORS |  | 125428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 451.2 | LABOR- SUBCONTRACTOR
%R | 504323 | 6359 | 125430 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 216 | 0 | 200 | 0 | 1222.4 | 1222.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-14 08:00 | 2014-06-11 17:00 |  | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 |  | PT_Normal |  |  |  |  | grQFadBYSUSlxluvAsmpJA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32700 | N | N | 10 | GROUND FLOOR |  | 125428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1222.4 | LABOR- SUBCONTRACTOR
%R | 504324 | 6359 | 125430 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ELGF4005 | Cable tray & trunking installation | 8178 | 360 | 0 | 160 | 0 | 1318.4 | 1318.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-16 08:00 | 2014-07-08 17:00 |  | 2014-04-24 08:00 | 2014-05-17 17:00 | 2014-04-24 08:00 | 2014-05-17 17:00 | 2014-04-24 08:00 | 2014-05-17 17:00 | 2014-06-16 08:00 | 2014-07-08 17:00 |  | PT_Normal |  |  |  |  | gXndLZ5wR+66OA3SQXKvbg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32700 | N | N | 10 | GROUND FLOOR |  | 125428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1318.4 | LABOR- SUBCONTRACTOR
%R | 504325 | 6359 | 125430 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ELGF4010 | Installation of wiring & Main Cabling | 8178 | 360 | 216 | 200 | 0 | 296 | 296 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-24 08:00 | 2014-07-22 17:00 |  | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-06-24 08:00 | 2014-07-22 17:00 |  | PT_Normal |  |  |  |  | zsq/Vl6vQ7Cf5op3FSPiOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32700 | N | N | 10 | GROUND FLOOR |  | 125428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 296 | LABOR- SUBCONTRACTOR
%R | 504326 | 6359 | 125430 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 144 | 0 | 160 | 0 | 227.2 | 227.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-31 08:00 | 2014-08-26 17:00 |  | 2014-07-10 08:00 | 2014-08-05 17:00 | 2014-07-10 08:00 | 2014-08-05 17:00 | 2014-07-10 08:00 | 2014-08-05 17:00 | 2014-07-31 08:00 | 2014-08-26 17:00 |  | PT_Normal |  |  |  |  | u8tqvn4lTfGFLAoPvhfALQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32700 | N | N | 10 | GROUND FLOOR |  | 125428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 227.2 | LABOR- SUBCONTRACTOR
%R | 504327 | 6359 | 125430 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 200 | 0 | 200 | 0 | 1651.2 | 1651.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-24 08:00 | 2014-09-21 17:00 |  | 2014-07-22 08:00 | 2014-08-23 17:00 | 2014-07-22 08:00 | 2014-08-23 17:00 | 2014-07-22 08:00 | 2014-08-23 17:00 | 2014-08-24 08:00 | 2014-09-21 17:00 |  | PT_Normal |  |  |  |  | GhCoROoqTNqYtA4mAI2jwQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32700 | N | N | 10 | GROUND FLOOR |  | 125428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 825.6 | LABOR- SUBCONTRACTOR
%R | 504328 | 6359 | 125430 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 240 | 0 | 200 | 0 | 1075.2 | 1075.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-09-09 17:00 |  | 2014-07-05 08:00 | 2014-08-05 17:00 | 2014-07-05 08:00 | 2014-08-05 17:00 | 2014-07-05 08:00 | 2014-08-05 17:00 | 2014-08-12 08:00 | 2014-09-09 17:00 |  | PT_Normal |  |  |  |  | DW4wsTttSuSTeLuuXnaXCw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32700 | N | N | 10 | GROUND FLOOR |  | 125428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 537.6 | LABOR- SUBCONTRACTOR
%R | 504329 | 6359 | 125430 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ELGF4030 | Installation of Telephone System | 8178 | 144 | 40 | 160 | 0 | 520 | 520 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-16 08:00 | 2014-09-07 17:00 |  | 2014-07-22 08:00 | 2014-08-17 17:00 | 2014-07-22 08:00 | 2014-08-17 17:00 | 2014-07-22 08:00 | 2014-08-17 17:00 | 2014-08-16 08:00 | 2014-09-07 17:00 |  | PT_Normal |  |  |  |  | 8ulfDqGlQLONe6klXND+sQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32700 | N | N | 10 | GROUND FLOOR |  | 125428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 520 | LABOR- SUBCONTRACTOR
%R | 504330 | 6359 | 125431 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ELRF4070 | Installation of Isolator | 8178 | 8 | 0 | 144 | 0 | 412.8 | 412.8 | 144 | 0 | 0 | 0 |  |  |  | 2014-09-13 08:00 | 2014-10-02 17:00 |  | 2014-09-11 08:00 | 2014-10-01 17:00 | 2014-09-11 08:00 | 2014-10-01 17:00 | 2014-09-11 08:00 | 2014-10-01 17:00 | 2014-09-13 08:00 | 2014-10-02 17:00 |  | PT_Normal |  |  |  |  | yG5/m4uwRP2nZcCjfKS1Pw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32720 | N | N | 20 | ROOF |  | 125428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 412.8 | LABOR- SUBCONTRACTOR
%R | 504331 | 6359 | 125431 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ELRF4075 | Installation of TV Dish Antenna | 8178 | 8 | 8 | 184 | 0 | 732.8 | 732.8 | 184 | 0 | 0 | 0 |  |  |  | 2014-09-18 08:00 | 2014-10-16 17:00 |  | 2014-09-17 08:00 | 2014-10-15 17:00 | 2014-09-17 08:00 | 2014-10-15 17:00 | 2014-09-17 08:00 | 2014-10-15 17:00 | 2014-09-18 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | QRLrVPPSR4iJy79DhABc0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32720 | N | N | 20 | ROOF |  | 125428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 732.8 | LABOR- SUBCONTRACTOR
%R | 504332 | 6359 | 125434 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARRF3630 | Leveling Screed for Waterproofing | 8164 | 168 | 0 | 200 | 0 | 800 | 800 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-05 08:00 | 2014-09-02 17:00 |  | 2014-07-08 08:00 | 2014-08-09 17:00 | 2014-07-08 08:00 | 2014-08-09 17:00 | 2014-07-08 08:00 | 2014-08-09 17:00 | 2014-08-05 08:00 | 2014-09-02 17:00 |  | PT_Normal |  |  |  |  | t7xjFFEBRAWLJNMMglLn8A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32660 | N | N | 10 | ROOF |  | 125433 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 400 | SCREED MASON SK
%R | 504333 | 6359 | 125434 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARRF3635 | Laying of Waterproofing Membrane | 8178 | 168 | 0 | 200 | 0 | 1138.5 | 1138.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-09 08:00 | 2014-09-06 17:00 |  | 2014-07-12 08:00 | 2014-08-12 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 | 2014-08-09 08:00 | 2014-09-06 17:00 |  | PT_Normal |  |  |  |  | 5OLBJGR0QBOfu5f4U48oOw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32660 | N | N | 10 | ROOF |  | 125433 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 569.25 | LABOR- SUBCONTRACTOR
%R | 504334 | 6359 | 125434 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARRF3640 | Installation of Insulation & Protection | 8178 | 168 | 0 | 200 | 0 | 1408 | 1408 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-13 08:00 | 2014-09-10 17:00 |  | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-08-13 08:00 | 2014-09-10 17:00 |  | PT_Normal |  |  |  |  | R/UGRmBkQtSGpEHeWaPkqg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32660 | N | N | 10 | ROOF |  | 125433 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 704 | LABOR- SUBCONTRACTOR
%R | 504335 | 6359 | 125434 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 168 | 0 | 200 | 0 | 688.25 | 688.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-07-21 08:00 | 2014-08-21 17:00 | 2014-07-21 08:00 | 2014-08-21 17:00 | 2014-07-21 08:00 | 2014-08-21 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | R1PcCG1rQsyQYBBGOyzS0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32660 | N | N | 10 | ROOF |  | 125433 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 344.125 | TILE MASON SK
%R | 504336 | 6359 | 125434 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 168 | 0 | 160 | 0 | 616 | 616 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-10-02 17:00 |  | 2014-08-17 08:00 | 2014-09-08 17:00 | 2014-08-17 08:00 | 2014-09-08 17:00 | 2014-08-17 08:00 | 2014-09-08 17:00 | 2014-09-10 08:00 | 2014-10-02 17:00 |  | PT_Normal |  |  |  |  | oQCTLavCQNGMDRupo1poEA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32660 | N | N | 10 | ROOF |  | 125433 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 616 | LABOR- SUBCONTRACTOR
%R | 504337 | 6359 | 125434 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 168 | 0 | 200 | 0 | 1046.5 | 1046.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-26 08:00 | 2014-09-23 17:00 |  | 2014-07-29 08:00 | 2014-08-30 17:00 | 2014-07-29 08:00 | 2014-08-30 17:00 | 2014-07-29 08:00 | 2014-08-30 17:00 | 2014-08-26 08:00 | 2014-09-23 17:00 |  | PT_Normal |  |  |  |  | cEQTeWgHQHWDmtJRPtpx9Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32660 | N | N | 10 | ROOF |  | 125433 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 523.25 | LABOR- SUBCONTRACTOR
%R | 504338 | 6359 | 125434 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARRF3660 | Installation of Access Ladder | 8178 | 208 | 208 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-28 08:00 | 2014-10-16 17:00 |  | 2014-08-28 08:00 | 2014-09-14 17:00 | 2014-08-28 08:00 | 2014-09-14 17:00 | 2014-08-28 08:00 | 2014-09-14 17:00 | 2014-09-28 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | /uqv0EdeSomgwsDaX8gzvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32660 | N | N | 10 | ROOF |  | 125433 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 176 | LABOR- SUBCONTRACTOR
%R | 504339 | 6359 | 125435 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8AREL3665 | External Plastering | 8169 | 376 | 0 | 200 | 0 | 14275 | 14275 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-21 08:00 | 2014-09-18 17:00 |  | 2014-06-24 08:00 | 2014-07-22 17:00 | 2014-06-24 08:00 | 2014-07-22 17:00 | 2014-06-24 08:00 | 2014-07-22 17:00 | 2014-08-21 08:00 | 2014-09-18 17:00 |  | PT_Normal |  |  |  |  | 3WMPo4inR3q/Jl6nSSSWLg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32670 | N | N | 15 | ELEVATION |  | 125433 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 14275 | PLASTER MASON SK
%R | 504340 | 6359 | 125435 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8AREL3670 | External stone cladding works | 8170 | 392 | 0 | 160 | 0 | 990 | 990 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-10-02 17:00 |  | 2014-07-12 08:00 | 2014-08-06 17:00 | 2014-07-12 08:00 | 2014-08-06 17:00 | 2014-07-12 08:00 | 2014-08-06 17:00 | 2014-09-10 08:00 | 2014-10-02 17:00 |  | PT_Normal |  |  |  |  | S+rerYJtR+O49lFV9LkA1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32670 | N | N | 15 | ELEVATION |  | 125433 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 990 | TILE MASON SK
%R | 504341 | 6359 | 125435 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8AREL3680 | External Painting | 8178 | 392 | 40 | 160 | 0 | 3784 | 3784 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-22 08:00 | 2014-10-16 17:00 |  | 2014-07-23 08:00 | 2014-08-18 17:00 | 2014-07-23 08:00 | 2014-08-18 17:00 | 2014-07-23 08:00 | 2014-08-18 17:00 | 2014-09-22 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | 4HTAW+hBR4eJn4SWAz6O/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32670 | N | N | 15 | ELEVATION |  | 125433 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 3784 | LABOR- SUBCONTRACTOR
%R | 504342 | 6359 | 125437 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARRF3600 | Block work | 8168 | 416 | 0 | 160 | 0 | 700 | 700 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-05 08:00 | 2014-08-27 17:00 |  | 2014-06-02 08:00 | 2014-06-24 17:00 | 2014-06-02 08:00 | 2014-06-24 17:00 | 2014-06-02 08:00 | 2014-06-24 17:00 | 2014-08-05 08:00 | 2014-08-27 17:00 |  | PT_Normal |  |  |  |  | KLWkfRG4TP69yIhU8vtkdQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32640 | N | N | 20 | ROOF |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 700 | BLOCK MASON SK
%R | 504343 | 6359 | 125437 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARRF3605 | Plastering work | 8169 | 416 | 0 | 160 | 0 | 1786.5 | 1786.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-13 08:00 | 2014-09-04 17:00 |  | 2014-06-10 08:00 | 2014-07-02 17:00 | 2014-06-10 08:00 | 2014-07-02 17:00 | 2014-06-10 08:00 | 2014-07-02 17:00 | 2014-08-13 08:00 | 2014-09-04 17:00 |  | PT_Normal |  |  |  |  | VK9zAEBOQc6JZ3bP3T0MdQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32640 | N | N | 20 | ROOF |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1786.5 | PLASTER MASON SK
%R | 504344 | 6359 | 125437 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARRF3610 | Flooring screed | 8164 | 456 | 0 | 120 | 0 | 136.5 | 136.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-02 08:00 | 2014-09-18 17:00 |  | 2014-06-24 08:00 | 2014-07-10 17:00 | 2014-06-24 08:00 | 2014-07-10 17:00 | 2014-06-24 08:00 | 2014-07-10 17:00 | 2014-09-02 08:00 | 2014-09-18 17:00 |  | PT_Normal |  |  |  |  | zb/KjzO9Tryh1Fj/K2uOZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32640 | N | N | 20 | ROOF |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 136.5 | SCREED MASON SK
%R | 504345 | 6359 | 125437 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARRF3695 | Painting -Storage area | 8178 | 456 | 0 | 160 | 0 | 1640 | 1640 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-10-02 17:00 |  | 2014-07-02 08:00 | 2014-07-24 17:00 | 2014-07-02 08:00 | 2014-07-24 17:00 | 2014-07-02 08:00 | 2014-07-24 17:00 | 2014-09-10 08:00 | 2014-10-02 17:00 |  | PT_Normal |  |  |  |  | ME53LcIqTbS0N+cfhZRxqg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32640 | N | N | 20 | ROOF |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1640 | LABOR- SUBCONTRACTOR
%R | 504346 | 6359 | 125437 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARRF3620 | Epoxy Painting -Storage area | 8178 | 456 | 456 | 120 | 0 | 48.5 | 48.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-28 08:00 | 2014-10-16 17:00 |  | 2014-07-20 08:00 | 2014-08-09 17:00 | 2014-07-20 08:00 | 2014-08-09 17:00 | 2014-07-20 08:00 | 2014-08-09 17:00 | 2014-09-28 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | M5VjZvhURKCXPrQexTY/pQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32640 | N | N | 20 | ROOF |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 48.5 | LABOR- SUBCONTRACTOR
%R | 504347 | 6359 | 125438 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARFF3300 | Block work | 8168 | 0 | 0 | 200 | 0 | 6387.5 | 6387.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | ZyYqTtC3Tg6FFRhS80T8nw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32630 | N | N | 15 | FIRST FLOORS |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 6387.5 | BLOCK MASON SK
%R | 504348 | 6359 | 125438 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARFF3305 | Plastering work | 8169 | 0 | 0 | 200 | 0 | 8899 | 8899 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-07-10 17:00 |  | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 |  | PT_Normal |  |  |  |  | v0xT9NmtRFqKwdxvuLy1pA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32630 | N | N | 15 | FIRST FLOORS |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 8899 | PLASTER MASON SK
%R | 504349 | 6359 | 125438 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARFF3310 | Flooring screed | 8164 | 96 | 96 | 168 | 0 | 1215.5 | 1215.5 | 168 | 0 | 0 | 0 |  |  |  | 2014-07-05 08:00 | 2014-07-28 17:00 |  | 2014-06-21 08:00 | 2014-07-14 17:00 | 2014-06-21 08:00 | 2014-07-14 17:00 | 2014-06-21 08:00 | 2014-07-14 17:00 | 2014-07-05 08:00 | 2014-07-28 17:00 |  | PT_Normal |  |  |  |  | FY8FUf6dTA+7ZxTuW5DobA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32630 | N | N | 15 | FIRST FLOORS |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1215.5 | SCREED MASON SK
%R | 504350 | 6359 | 125438 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARFF3315 | Wet area waterproofing | 8178 | 0 | 0 | 120 | 0 | 1215.5 | 1215.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-02 08:00 | 2014-07-19 17:00 |  | 2014-07-02 08:00 | 2014-07-19 17:00 | 2014-07-02 08:00 | 2014-07-19 17:00 | 2014-07-02 08:00 | 2014-07-19 17:00 | 2014-07-02 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | 4wgMbvEQQneECnE8isP3yA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32630 | N | N | 15 | FIRST FLOORS |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1215.5 | LABOR- SUBCONTRACTOR
%R | 504351 | 6359 | 125438 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARFF3330 | Paint First coat | 8178 | 112 | 112 | 200 | 0 | 4742.75 | 4742.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-15 08:00 | 2014-08-16 17:00 |  | 2014-06-29 08:00 | 2014-07-27 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 | 2014-07-15 08:00 | 2014-08-16 17:00 |  | PT_Normal |  |  |  |  | Xu4WV+IBSTCKJ1Uf6TS5Mw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32630 | N | N | 15 | FIRST FLOORS |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 4742.75 | LABOR- SUBCONTRACTOR
%R | 504352 | 6359 | 125438 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARFF3320 | Ceramic Wall Tiling | 8170 | 0 | 0 | 200 | 0 | 1897.25 | 1897.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-09 08:00 | 2014-08-10 17:00 |  | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-07-09 08:00 | 2014-08-10 17:00 |  | PT_Normal |  |  |  |  | 5/VIKWksTF+/c121j5PWPw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32630 | N | N | 15 | FIRST FLOORS |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 948.625 | TILE MASON SK
%R | 504353 | 6359 | 125438 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARFF3325 | Porcelain Tile flooring | 8170 | 0 | 0 | 200 | 0 | 1743.75 | 1743.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | 7Ge0usl6Txy/uMUHzJz1AQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32630 | N | N | 15 | FIRST FLOORS |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 871.875 | TILE MASON SK
%R | 504354 | 6359 | 125438 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARFF3335 | Slate Tile Flooring & Skirting | 8170 | 64 | 64 | 120 | 0 | 261.5 | 261.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-16 08:00 | 2014-09-01 17:00 |  | 2014-08-06 08:00 | 2014-08-23 17:00 | 2014-08-06 08:00 | 2014-08-23 17:00 | 2014-08-06 08:00 | 2014-08-23 17:00 | 2014-08-16 08:00 | 2014-09-01 17:00 |  | PT_Normal |  |  |  |  | bc0TxfViS+Skgi6KLeqYpQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32630 | N | N | 15 | FIRST FLOORS |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 261.5 | TILE MASON SK
%R | 504355 | 6359 | 125438 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARFF3350 | Granite - Stair case flooring & Skirting | 8171 | 16 | 16 | 160 | 0 | 875 | 875 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-09-03 17:00 |  | 2014-08-10 08:00 | 2014-09-01 17:00 | 2014-08-10 08:00 | 2014-09-01 17:00 | 2014-08-10 08:00 | 2014-09-01 17:00 | 2014-08-12 08:00 | 2014-09-03 17:00 |  | PT_Normal |  |  |  |  | EG4Yydg/SJGIr3L101d/1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32630 | N | N | 15 | FIRST FLOORS |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 875 | GRANITE MASON SK
%R | 504356 | 6359 | 125438 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARFF3345 | Fixing of Suspension systems | 8178 | 0 | 0 | 160 | 0 | 1305 | 1305 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-29 08:00 | 2014-08-24 17:00 |  | 2014-07-29 08:00 | 2014-08-24 17:00 | 2014-07-29 08:00 | 2014-08-24 17:00 | 2014-07-29 08:00 | 2014-08-24 17:00 | 2014-07-29 08:00 | 2014-08-24 17:00 |  | PT_Normal |  |  |  |  | BaZGeeh0T8CZfyvYExqtLQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32630 | N | N | 15 | FIRST FLOORS |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1305 | LABOR- SUBCONTRACTOR
%R | 504357 | 6359 | 125438 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARFF3360 | Gypsum board false ceiling | 8178 | 0 | 0 | 200 | 0 | 1305 | 1305 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-09 08:00 | 2014-09-06 17:00 |  | 2014-08-09 08:00 | 2014-09-06 17:00 | 2014-08-09 08:00 | 2014-09-06 17:00 | 2014-08-09 08:00 | 2014-09-06 17:00 | 2014-08-09 08:00 | 2014-09-06 17:00 |  | PT_Normal |  |  |  |  | hxCa2d+oQAeeEFVQVQdwTA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32630 | N | N | 15 | FIRST FLOORS |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1305 | LABOR- SUBCONTRACTOR
%R | 504358 | 6359 | 125438 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARFF3365 | Wooden door | 8178 | 0 | 0 | 120 | 0 | 308 | 308 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-24 08:00 | 2014-09-09 17:00 |  | 2014-08-24 08:00 | 2014-09-09 17:00 | 2014-08-24 08:00 | 2014-09-09 17:00 | 2014-08-24 08:00 | 2014-09-09 17:00 | 2014-08-24 08:00 | 2014-09-09 17:00 |  | PT_Normal |  |  |  |  | RO5kUqpfTb6rHCfcbAV1GQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32630 | N | N | 15 | FIRST FLOORS |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 308 | LABOR- SUBCONTRACTOR
%R | 504359 | 6359 | 125438 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARFF3370 | Aluminum Door | 8178 | 0 | 0 | 160 | 0 | 220 | 220 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-24 08:00 | 2014-09-15 17:00 |  | 2014-08-24 08:00 | 2014-09-15 17:00 | 2014-08-24 08:00 | 2014-09-15 17:00 | 2014-08-24 08:00 | 2014-09-15 17:00 | 2014-08-24 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | wQUQoMFhQheuxLEXy+oE0w |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32630 | N | N | 15 | FIRST FLOORS |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 220 | LABOR- SUBCONTRACTOR
%R | 504360 | 6359 | 125438 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARFF3380 | Aluminum windows | 8178 | 32 | 32 | 160 | 0 | 162.25 | 162.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-04 08:00 | 2014-09-27 17:00 |  | 2014-08-31 08:00 | 2014-09-22 17:00 | 2014-08-31 08:00 | 2014-09-22 17:00 | 2014-08-31 08:00 | 2014-09-22 17:00 | 2014-09-04 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | D7vCt+viRmK0ROTsQQkImQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32630 | N | N | 15 | FIRST FLOORS |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 162.25 | LABOR- SUBCONTRACTOR
%R | 504361 | 6359 | 125438 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARFF3375 | Carpentry & Joinery Works | 8178 | 0 | 0 | 200 | 0 | 1100 | 1100 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-27 17:00 |  | 2014-08-30 08:00 | 2014-09-27 17:00 | 2014-08-30 08:00 | 2014-09-27 17:00 | 2014-08-30 08:00 | 2014-09-27 17:00 | 2014-08-30 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | 9O51ugnkTaeEpTCHs0dnjA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32630 | N | N | 15 | FIRST FLOORS |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1100 | LABOR- SUBCONTRACTOR
%R | 504362 | 6359 | 125438 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARFF3390 | Installation of Granite Counter Top | 8171 | 8 | 8 | 160 | 0 | 88 | 88 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-11 08:00 | 2014-10-04 17:00 |  | 2014-09-10 08:00 | 2014-10-02 17:00 | 2014-09-10 08:00 | 2014-10-02 17:00 | 2014-09-10 08:00 | 2014-10-02 17:00 | 2014-09-11 08:00 | 2014-10-04 17:00 |  | PT_Normal |  |  |  |  | Bu6z2UXdRAGyDO9DSFMZsw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32630 | N | N | 15 | FIRST FLOORS |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 88 | GRANITE MASON SK
%R | 504363 | 6359 | 125438 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARFF3385 | Handrail & Balustrade | 8178 | 0 | 0 | 160 | 0 | 787.5 | 787.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-10-02 17:00 |  | 2014-09-10 08:00 | 2014-10-02 17:00 | 2014-09-10 08:00 | 2014-10-02 17:00 | 2014-09-10 08:00 | 2014-10-02 17:00 | 2014-09-10 08:00 | 2014-10-02 17:00 |  | PT_Normal |  |  |  |  | uiOUlOU/TZe9TrCOyp7nyg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32630 | N | N | 15 | FIRST FLOORS |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 787.5 | LABOR- SUBCONTRACTOR
%R | 504364 | 6359 | 125438 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARFF3395 | Final Painting | 8178 | 0 | 0 | 200 | 0 | 4742.75 | 4742.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-09-16 08:00 | 2014-10-16 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | ULjSPQ6OQBOIADQ3CIzEnQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32630 | N | N | 15 | FIRST FLOORS |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 2371.375 | LABOR- SUBCONTRACTOR
%R | 504365 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3000 | Block work | 8168 | 144 | 0 | 200 | 0 | 9737.5 | 9737.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-28 08:00 | 2014-05-26 17:00 |  | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-28 08:00 | 2014-05-26 17:00 |  | PT_Normal |  |  |  |  | XjUX7Cc+Rya51PgSeJTDIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 9737.5 | BLOCK MASON SK
%R | 504366 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3005 | Plastering work | 8169 | 144 | 0 | 200 | 0 | 13637.5 | 13637.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-20 08:00 | 2014-06-17 17:00 |  | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | sXI2veHWSMaPTiftlc8MNg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 13637.5 | PLASTER MASON SK
%R | 504367 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3010 | Flooring screed | 8164 | 208 | 64 | 168 | 0 | 1580.25 | 1580.25 | 168 | 0 | 0 | 0 |  |  |  | 2014-06-07 08:00 | 2014-06-30 17:00 |  | 2014-05-07 08:00 | 2014-05-31 17:00 | 2014-05-07 08:00 | 2014-05-31 17:00 | 2014-05-07 08:00 | 2014-05-31 17:00 | 2014-06-07 08:00 | 2014-06-30 17:00 |  | PT_Normal |  |  |  |  | 1zSU/vZiSJa+fax7g/uOMw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1580.25 | SCREED MASON SK
%R | 504368 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 144 | 0 | 120 | 0 | 247.5 | 247.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-07 08:00 | 2014-06-23 17:00 |  | 2014-05-17 08:00 | 2014-06-02 17:00 | 2014-05-17 08:00 | 2014-06-02 17:00 | 2014-05-17 08:00 | 2014-06-02 17:00 | 2014-06-07 08:00 | 2014-06-23 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 247.5 | LABOR- SUBCONTRACTOR
%R | 504369 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3030 | Paint First coat | 8178 | 256 | 0 | 200 | 0 | 5425.75 | 5425.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-22 08:00 | 2014-07-20 17:00 |  | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 |  | PT_Normal |  |  |  |  | GnT5Ak/WRVymjIYt3vVyvA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 5425.75 | LABOR- SUBCONTRACTOR
%R | 504370 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3020 | Ceramic Wall Tiling | 8170 | 144 | 0 | 200 | 0 | 4428.5 | 4428.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-07-10 17:00 |  | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 4428.5 | TILE MASON SK
%R | 504371 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3025 | Porcelain Tile flooring | 8170 | 144 | 0 | 200 | 0 | 1743.75 | 1743.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-18 08:00 | 2014-07-16 17:00 |  | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-06-18 08:00 | 2014-07-16 17:00 |  | PT_Normal |  |  |  |  | xQxsW57ARUaZ+szY3h0VWw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1743.75 | TILE MASON SK
%R | 504372 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3040 | Cobble Tile flooring | 8170 | 168 | 0 | 120 | 0 | 741 | 741 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-19 08:00 | 2014-08-07 17:00 |  | 2014-06-24 08:00 | 2014-07-10 17:00 | 2014-06-24 08:00 | 2014-07-10 17:00 | 2014-06-24 08:00 | 2014-07-10 17:00 | 2014-07-19 08:00 | 2014-08-07 17:00 |  | PT_Normal |  |  |  |  | 72IEVzZPT46kkNtVDxeQ1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 741 | TILE MASON SK
%R | 504373 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 184 | 16 | 120 | 0 | 761.5 | 761.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-14 08:00 | 2014-07-30 17:00 |  | 2014-06-17 08:00 | 2014-07-03 17:00 | 2014-06-17 08:00 | 2014-07-03 17:00 | 2014-06-17 08:00 | 2014-07-03 17:00 | 2014-07-14 08:00 | 2014-07-30 17:00 |  | PT_Normal |  |  |  |  | Gf9J6oKdRwOiwz6yb8n0fA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 761.5 | TILE MASON SK
%R | 504374 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 168 | 0 | 160 | 0 | 875 | 875 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-27 08:00 | 2014-08-21 17:00 |  | 2014-07-02 08:00 | 2014-07-24 17:00 | 2014-07-02 08:00 | 2014-07-24 17:00 | 2014-07-02 08:00 | 2014-07-24 17:00 | 2014-07-27 08:00 | 2014-08-21 17:00 |  | PT_Normal |  |  |  |  | mCnoOA2LSnqL9tRi4/d6VA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 875 | GRANITE MASON SK
%R | 504375 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3045 | Fixing of Suspension systems | 8178 | 144 | 0 | 160 | 0 | 1455.05 | 1455.05 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-06 08:00 | 2014-07-28 17:00 |  | 2014-06-15 08:00 | 2014-07-07 17:00 | 2014-06-15 08:00 | 2014-07-07 17:00 | 2014-06-15 08:00 | 2014-07-07 17:00 | 2014-07-06 08:00 | 2014-07-28 17:00 |  | PT_Normal |  |  |  |  | Oid4/9JWTdukiyYq0cHKbQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1455.05 | LABOR- SUBCONTRACTOR
%R | 504376 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3055 | Aluminum tile false ceiling | 8178 | 168 | 24 | 200 | 0 | 150 | 150 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-17 08:00 | 2014-08-18 17:00 |  | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-07-17 08:00 | 2014-08-18 17:00 |  | PT_Normal |  |  |  |  | q46Li7fQTdubfWcU7LXZqQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 150 | LABOR- SUBCONTRACTOR
%R | 504377 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3060 | Gypsum board false ceiling | 8178 | 144 | 0 | 200 | 0 | 1335.15 | 1335.15 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-17 08:00 | 2014-08-18 17:00 |  | 2014-06-26 08:00 | 2014-07-24 17:00 | 2014-06-26 08:00 | 2014-07-24 17:00 | 2014-06-26 08:00 | 2014-07-24 17:00 | 2014-07-17 08:00 | 2014-08-18 17:00 |  | PT_Normal |  |  |  |  | ZspaneKITPKMeiVHfw7ohg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1335.15 | LABOR- SUBCONTRACTOR
%R | 504378 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3065 | Wooden door & PVC Door | 8178 | 168 | 0 | 120 | 0 | 308 | 308 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-13 08:00 | 2014-08-30 17:00 |  | 2014-07-16 08:00 | 2014-08-05 17:00 | 2014-07-16 08:00 | 2014-08-05 17:00 | 2014-07-16 08:00 | 2014-08-05 17:00 | 2014-08-13 08:00 | 2014-08-30 17:00 |  | PT_Normal |  |  |  |  | /7yDzuCuSZahs2bON64Bvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 308 | LABOR- SUBCONTRACTOR
%R | 504379 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3070 | Aluminum doors | 8178 | 168 | 0 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-19 08:00 | 2014-09-04 17:00 |  | 2014-07-22 08:00 | 2014-08-11 17:00 | 2014-07-22 08:00 | 2014-08-11 17:00 | 2014-07-22 08:00 | 2014-08-11 17:00 | 2014-08-19 08:00 | 2014-09-04 17:00 |  | PT_Normal |  |  |  |  | EVPQ67DhQOWNoPiDlXa5bA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 176 | LABOR- SUBCONTRACTOR
%R | 504380 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3080 | Aluminum windows | 8178 | 248 | 40 | 160 | 0 | 162.25 | 162.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-07 08:00 | 2014-09-29 17:00 |  | 2014-07-29 08:00 | 2014-08-24 17:00 | 2014-07-29 08:00 | 2014-08-24 17:00 | 2014-07-29 08:00 | 2014-08-24 17:00 | 2014-09-07 08:00 | 2014-09-29 17:00 |  | PT_Normal |  |  |  |  | boNy0w3iTgG048tDxYoDtg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 162.25 | LABOR- SUBCONTRACTOR
%R | 504381 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3075 | Carpentry & Joinery Works | 8178 | 168 | 0 | 160 | 0 | 572 | 572 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-25 08:00 | 2014-09-16 17:00 |  | 2014-07-28 08:00 | 2014-08-23 17:00 | 2014-07-28 08:00 | 2014-08-23 17:00 | 2014-07-28 08:00 | 2014-08-23 17:00 | 2014-08-25 08:00 | 2014-09-16 17:00 |  | PT_Normal |  |  |  |  | Kgm1n5Q5RYGpu+y07GVajQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 572 | LABOR- SUBCONTRACTOR
%R | 504382 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3090 | Installation of Granite Counter Top | 8171 | 168 | 0 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-07 08:00 | 2014-09-23 17:00 |  | 2014-08-13 08:00 | 2014-08-30 17:00 | 2014-08-13 08:00 | 2014-08-30 17:00 | 2014-08-13 08:00 | 2014-08-30 17:00 | 2014-09-07 08:00 | 2014-09-23 17:00 |  | PT_Normal |  |  |  |  | DbD5dhFwQh6hxp5U9JKklQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 176 | GRANITE MASON SK
%R | 504383 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3085 | S.S.Balustrade | 8178 | 208 | 40 | 160 | 0 | 262.5 | 262.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-08 08:00 | 2014-09-30 17:00 |  | 2014-08-09 08:00 | 2014-08-31 17:00 | 2014-08-09 08:00 | 2014-08-31 17:00 | 2014-08-09 08:00 | 2014-08-31 17:00 | 2014-09-08 08:00 | 2014-09-30 17:00 |  | PT_Normal |  |  |  |  | KOqi3XNESCGqwzPCVRfqrg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 262.5 | LABOR- SUBCONTRACTOR
%R | 504384 | 6359 | 125439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ8ARGF3095 | Final Painting | 8178 | 168 | 0 | 200 | 0 | 5425.75 | 5425.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-08-23 08:00 | 2014-09-20 17:00 | 2014-08-23 08:00 | 2014-09-20 17:00 | 2014-08-23 08:00 | 2014-09-20 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | sp4SXhnLSqqdx+fO+48RNQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32620 | N | N | 10 | GROUND FLOOR |  | 125436 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 5425.75 | LABOR- SUBCONTRACTOR
%R | 504385 | 6359 | 125441 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-09-16 08:00 | 2014-10-16 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | 2mhuI+1fQH+ik5++o0ly7w |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32510 | N | N | 30 | TESTING AND COMMISSIONING |  | 125440 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 504386 | 6359 | 125441 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 0 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-09-16 08:00 | 2014-10-16 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | HOI8pNKQQr6FHLJdyJRckA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32510 | N | N | 30 | TESTING AND COMMISSIONING |  | 125440 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 750 | LABOR- SUBCONTRACTOR
%R | 504387 | 6359 | 125441 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-09-16 08:00 | 2014-10-16 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | UnjU2Cx/R5C0bn5/4IAHmQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32510 | N | N | 30 | TESTING AND COMMISSIONING |  | 125440 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 504388 | 6359 | 125444 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STUG1000 | Footing Excavation | 8177 | 0 | 0 | 200 | 0 | 1114 | 1114 | 200 | 524 | 0 | 524 |  |  |  | 2013-08-08 08:00 | 2013-09-09 17:00 |  | 2013-08-08 08:00 | 2013-09-09 17:00 | 2013-08-08 08:00 | 2013-09-09 17:00 | 2013-08-08 08:00 | 2013-09-09 17:00 | 2013-08-08 08:00 | 2013-09-09 17:00 |  | PT_Normal |  |  |  |  | ZZC+m0HLTTGjxfHvM/6E+A |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32190 | N | N | 10 | UPTO GRADE SLAB |  | 125443 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 557 | LABOR - CIVIL
%R | 504389 | 6359 | 125444 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STUG1005 | Footing Antitermite | 8178 | 0 | 0 | 184 | 0 | 1584 | 1584 | 184 | 0 | 0 | 0 |  |  |  | 2013-08-24 08:00 | 2013-09-18 17:00 |  | 2013-08-24 08:00 | 2013-09-18 17:00 | 2013-08-24 08:00 | 2013-09-18 17:00 | 2013-08-24 08:00 | 2013-09-18 17:00 | 2013-08-24 08:00 | 2013-09-18 17:00 |  | PT_Normal |  |  |  |  | hdHHlSbaQvWn1wbDw/t0vg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32190 | N | N | 10 | UPTO GRADE SLAB |  | 125443 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 1584 | LABOR- SUBCONTRACTOR
%R | 504390 | 6359 | 125444 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STUG1010 | Footing Blinding | 8163 | 0 | 0 | 184 | 0 | 794.5 | 794.5 | 184 | 0 | 0 | 0 |  |  |  | 2013-08-27 08:00 | 2013-09-22 17:00 |  | 2013-08-27 08:00 | 2013-09-22 17:00 | 2013-08-27 08:00 | 2013-09-22 17:00 | 2013-08-27 08:00 | 2013-09-22 17:00 | 2013-08-27 08:00 | 2013-09-22 17:00 |  | PT_Normal |  |  |  |  | b0NtYw3WSEKgqRUpmrZ8nQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32190 | N | N | 10 | UPTO GRADE SLAB |  | 125443 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 794.5 | BLINDING MASON SK
%R | 504391 | 6359 | 125444 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STUG1015 | Footing Waterproofing & Screed | 8164 | 0 | 0 | 200 | 0 | 574.75 | 574.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-02 08:00 | 2013-09-30 17:00 |  | 2013-09-02 08:00 | 2013-09-30 17:00 | 2013-09-02 08:00 | 2013-09-30 17:00 | 2013-09-02 08:00 | 2013-09-30 17:00 | 2013-09-02 08:00 | 2013-09-30 17:00 |  | PT_Normal |  |  |  |  | hWuPtN2ySDO25P0dFUskWg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32190 | N | N | 10 | UPTO GRADE SLAB |  | 125443 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 574.75 | SCREED MASON SK
%R | 504392 | 6359 | 125444 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STUG1020 | Construction of foundations | 8165 | 0 | 0 | 160 | 0 | 7778.75 | 7778.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-09-17 08:00 | 2013-10-09 17:00 |  | 2013-09-17 08:00 | 2013-10-09 17:00 | 2013-09-17 08:00 | 2013-10-09 17:00 | 2013-09-17 08:00 | 2013-10-09 17:00 | 2013-09-17 08:00 | 2013-10-09 17:00 |  | PT_Normal |  |  |  |  | whTiZ1bbRAib7xhJomoujA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32190 | N | N | 10 | UPTO GRADE SLAB |  | 125443 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 7778.75 | STEEL FIXERS SK
%R | 504393 | 6359 | 125444 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STUG1025 | Construction of neck of columns | 8165 | 0 | 0 | 200 | 0 | 1606.5 | 1606.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-26 08:00 | 2013-10-27 17:00 |  | 2013-09-26 08:00 | 2013-10-27 17:00 | 2013-09-26 08:00 | 2013-10-27 17:00 | 2013-09-26 08:00 | 2013-10-27 17:00 | 2013-09-26 08:00 | 2013-10-27 17:00 |  | PT_Normal |  |  |  |  | DKrZtxlXTpGL4Kv5cCrrtA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32190 | N | N | 10 | UPTO GRADE SLAB |  | 125443 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 803.25 | STEEL FIXERS SK
%R | 504394 | 6359 | 125444 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STUG1030 | Waterproofing Footing & Neck Column | 8178 | 0 | 0 | 200 | 0 | 516 | 516 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-06 08:00 | 2013-11-05 17:00 |  | 2013-10-06 08:00 | 2013-11-05 17:00 | 2013-10-06 08:00 | 2013-11-05 17:00 | 2013-10-06 08:00 | 2013-11-05 17:00 | 2013-10-06 08:00 | 2013-11-05 17:00 |  | PT_Normal |  |  |  |  | /+YdQ4iAR6WIWHLI1xV8TQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32190 | N | N | 10 | UPTO GRADE SLAB |  | 125443 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 516 | LABOR- SUBCONTRACTOR
%R | 504395 | 6359 | 125444 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 0 | 0 | 200 | 0 | 1041 | 1041 | 200 | 825 | 0 | 825 |  |  |  | 2013-10-22 08:00 | 2013-11-19 17:00 |  | 2013-10-22 08:00 | 2013-11-19 17:00 | 2013-10-22 08:00 | 2013-11-19 17:00 | 2013-10-22 08:00 | 2013-11-19 17:00 | 2013-10-22 08:00 | 2013-11-19 17:00 |  | PT_Normal |  |  |  |  | FaC+45k3TLuarjppTzV26g |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32190 | N | N | 10 | UPTO GRADE SLAB |  | 125443 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1041 | LABOR - CIVIL
%R | 504396 | 6359 | 125444 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STUG1040 | Construction of Grade Beams | 8163 | 0 | 0 | 200 | 0 | 7568.75 | 7568.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-07 08:00 | 2013-12-05 17:00 |  | 2013-11-07 08:00 | 2013-12-05 17:00 | 2013-11-07 08:00 | 2013-12-05 17:00 | 2013-11-07 08:00 | 2013-12-05 17:00 | 2013-11-07 08:00 | 2013-12-05 17:00 |  | PT_Normal |  |  |  |  | 7vh71M49TwSP7RpCncJxcw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32190 | N | N | 10 | UPTO GRADE SLAB |  | 125443 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 7568.75 | BLINDING MASON SK
%R | 504397 | 6359 | 125444 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STUG1045 | Construction of slab on grade | 8163 | 0 | 0 | 200 | 0 | 4422 | 4422 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-10 08:00 | 2014-01-08 17:00 |  | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 |  | PT_Normal |  |  |  |  | 5ltkSYZXSxuxnmXmYCXxlA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32190 | N | N | 10 | UPTO GRADE SLAB |  | 125443 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 4422 | BLINDING MASON SK
%R | 504398 | 6359 | 125446 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STFF2025 | Column-Concrete | 8167 | 32 | 0 | 192 | 0 | 224 | 224 | 192 | 0 | 0 | 0 |  |  |  | 2014-02-23 08:00 | 2014-03-22 17:00 |  | 2014-02-18 08:00 | 2014-03-17 17:00 | 2014-02-18 08:00 | 2014-03-17 17:00 | 2014-02-18 08:00 | 2014-03-17 17:00 | 2014-02-23 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | TPEqFx7DQbGqckXiOvNQpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32220 | N | N | 15 | FIRST FLOORS |  | 125445 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 224 | CONCRETE MASON SK
%R | 504399 | 6359 | 125446 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 32 | 0 | 200 | 0 | 16119.25 | 16119.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-10 08:00 | 2014-04-07 17:00 |  | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 |  | PT_Normal |  |  |  |  | juJqyk8MS+qqsg7nmwBzbg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32220 | N | N | 15 | FIRST FLOORS |  | 125445 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 16119.25 | STEEL FIXERS SK
%R | 504400 | 6359 | 125446 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 32 | 0 | 112 | 0 | 1141 | 1141 | 112 | 0 | 0 | 0 |  |  |  | 2014-03-26 08:00 | 2014-04-10 17:00 |  | 2014-03-22 08:00 | 2014-04-06 17:00 | 2014-03-22 08:00 | 2014-04-06 17:00 | 2014-03-22 08:00 | 2014-04-06 17:00 | 2014-03-26 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | yDsaRnIQRA2KEcmm0fl1uQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32220 | N | N | 15 | FIRST FLOORS |  | 125445 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1141 | CONCRETE MASON SK
%R | 504401 | 6359 | 125446 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STFF2020 | Column-Rebar & Formwork | 8165 | 16 | 0 | 200 | 0 | 3580.5 | 3580.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-10 08:00 | 2014-03-11 17:00 |  | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-10 08:00 | 2014-03-11 17:00 |  | PT_Normal |  |  |  |  | Mih/nBrrQJ+NJ4sA3OwwUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32220 | N | N | 15 | FIRST FLOORS |  | 125445 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 1790.25 | STEEL FIXERS SK
%R | 504402 | 6359 | 125447 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STGF2000 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 4046 | 4046 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-28 08:00 | 2014-01-25 17:00 |  | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 |  | PT_Normal |  |  |  |  | OtL63Tp/T62xEivz/E7xVA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32210 | N | N | 10 | GROUND FLOOR |  | 125445 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 4046 | STEEL FIXERS SK
%R | 504403 | 6359 | 125447 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STGF2005 | Column-Concrete | 8167 | 16 | 0 | 192 | 0 | 255.5 | 255.5 | 192 | 0 | 0 | 0 |  |  |  | 2014-01-07 08:00 | 2014-02-03 17:00 |  | 2014-01-05 08:00 | 2014-02-01 17:00 | 2014-01-05 08:00 | 2014-02-01 17:00 | 2014-01-05 08:00 | 2014-02-01 17:00 | 2014-01-07 08:00 | 2014-02-03 17:00 |  | PT_Normal |  |  |  |  | nOdB01/aTAeUNmLKl7azDw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32210 | N | N | 10 | GROUND FLOOR |  | 125445 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 255.5 | CONCRETE MASON SK
%R | 504404 | 6359 | 125447 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 16 | 0 | 200 | 0 | 16829.75 | 16829.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-20 17:00 |  | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | GaLP4qJTSDGmnYski3YR/Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32210 | N | N | 10 | GROUND FLOOR |  | 125445 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 16829.75 | STEEL FIXERS SK
%R | 504405 | 6359 | 125447 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 16 | 0 | 112 | 0 | 1295 | 1295 | 112 | 0 | 0 | 0 |  |  |  | 2014-02-08 08:00 | 2014-02-24 17:00 |  | 2014-02-05 08:00 | 2014-02-22 17:00 | 2014-02-05 08:00 | 2014-02-22 17:00 | 2014-02-05 08:00 | 2014-02-22 17:00 | 2014-02-08 08:00 | 2014-02-24 17:00 |  | PT_Normal |  |  |  |  | JUMpGsSMTiGbvy9s9KpFIQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32210 | N | N | 10 | GROUND FLOOR |  | 125445 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1295 | CONCRETE MASON SK
%R | 504406 | 6359 | 125448 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STRF2040 | Column-Rebar & Formwork | 8165 | 64 | 0 | 144 | 0 | 1205.75 | 1205.75 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-02 08:00 | 2014-04-22 17:00 |  | 2014-03-24 08:00 | 2014-04-13 17:00 | 2014-03-24 08:00 | 2014-04-13 17:00 | 2014-03-24 08:00 | 2014-04-13 17:00 | 2014-04-02 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | GvW3JL7USlSZwuaIT0VeCw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32230 | N | N | 20 | ROOF |  | 125445 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1205.75 | STEEL FIXERS SK
%R | 504407 | 6359 | 125448 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STRF2045 | Column-Concrete | 8167 | 64 | 0 | 136 | 0 | 52.5 | 52.5 | 136 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-04-24 17:00 |  | 2014-03-27 08:00 | 2014-04-15 17:00 | 2014-03-27 08:00 | 2014-04-15 17:00 | 2014-03-27 08:00 | 2014-04-15 17:00 | 2014-04-06 08:00 | 2014-04-24 17:00 |  | PT_Normal |  |  |  |  | RHlam2anRri2pcy1uTLcMw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32230 | N | N | 20 | ROOF |  | 125445 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 52.5 | CONCRETE MASON SK
%R | 504408 | 6359 | 125448 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STRF2050 | Slab-Rebar & Formwork - Head Room | 8165 | 64 | 0 | 160 | 0 | 2735.25 | 2735.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-08 08:00 | 2014-04-30 17:00 |  | 2014-03-30 08:00 | 2014-04-21 17:00 | 2014-03-30 08:00 | 2014-04-21 17:00 | 2014-03-30 08:00 | 2014-04-21 17:00 | 2014-04-08 08:00 | 2014-04-30 17:00 |  | PT_Normal |  |  |  |  | 8zxYmN39QHK9+xtEBQwK/A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32230 | N | N | 20 | ROOF |  | 125445 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 2735.25 | STEEL FIXERS SK
%R | 504409 | 6359 | 125448 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STRF2055 | Slab-Concrete-Head room | 8167 | 64 | 0 | 104 | 0 | 252 | 252 | 104 | 0 | 0 | 0 |  |  |  | 2014-04-19 08:00 | 2014-05-03 17:00 |  | 2014-04-09 08:00 | 2014-04-23 17:00 | 2014-04-09 08:00 | 2014-04-23 17:00 | 2014-04-09 08:00 | 2014-04-23 17:00 | 2014-04-19 08:00 | 2014-05-03 17:00 |  | PT_Normal |  |  |  |  | 1kL9Cc21Q3SYE43FtyahEw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32230 | N | N | 20 | ROOF |  | 125445 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 252 | CONCRETE MASON SK
%R | 504410 | 6359 | 125448 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STRF2060 | Construction of Parapets | 8168 | 448 | 32 | 200 | 0 | 2200 | 2200 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-16 08:00 | 2014-07-14 17:00 |  | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 |  | PT_Normal |  |  |  |  | 5W0ugGPSRAe7neTURcS7sQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32230 | N | N | 20 | ROOF |  | 125445 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 2200 | BLOCK MASON SK
%R | 504411 | 6359 | 125448 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7STRF2065 | Construction of up stands/Plinth | 8165 | 416 | 0 | 200 | 0 | 554.75 | 554.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-22 08:00 | 2014-07-20 17:00 |  | 2014-04-22 08:00 | 2014-05-20 17:00 | 2014-04-22 08:00 | 2014-05-20 17:00 | 2014-04-22 08:00 | 2014-05-20 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 |  | PT_Normal |  |  |  |  | T91SQFF/SBGaFLiQAO11kA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32230 | N | N | 20 | ROOF |  | 125445 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 554.75 | STEEL FIXERS SK
%R | 504412 | 6359 | 125450 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7HDEX5090 | kerb works | 8173 | 128 | 0 | 160 | 0 | 344 | 344 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-14 08:00 | 2014-08-09 17:00 |  | 2014-06-25 08:00 | 2014-07-17 17:00 | 2014-06-25 08:00 | 2014-07-17 17:00 | 2014-06-25 08:00 | 2014-07-17 17:00 | 2014-07-14 08:00 | 2014-08-09 17:00 |  | PT_Normal |  |  |  |  | NWm4OP7yRjKqVp7bP5kmqA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32490 | N | N | 20 | HARD LANDSCAPING |  | 125449 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 344 | KERBSTONE MASON SK
%R | 504413 | 6359 | 125450 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7HDEX5095 | Cobble Stone Works | 8170 | 128 | 0 | 160 | 0 | 200 | 200 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-26 08:00 | 2014-08-20 17:00 |  | 2014-07-07 08:00 | 2014-07-29 17:00 | 2014-07-07 08:00 | 2014-07-29 17:00 | 2014-07-07 08:00 | 2014-07-29 17:00 | 2014-07-26 08:00 | 2014-08-20 17:00 |  | PT_Normal |  |  |  |  | rLzyGevnQDeyPIysP7e16A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32490 | N | N | 20 | HARD LANDSCAPING |  | 125449 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 200 | TILE MASON SK
%R | 504414 | 6359 | 125450 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7HDEX5100 | Interlock works | 8174 | 128 | 0 | 160 | 0 | 232 | 232 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-05 08:00 | 2014-08-27 17:00 |  | 2014-07-14 08:00 | 2014-08-09 17:00 | 2014-07-14 08:00 | 2014-08-09 17:00 | 2014-07-14 08:00 | 2014-08-09 17:00 | 2014-08-05 08:00 | 2014-08-27 17:00 |  | PT_Normal |  |  |  |  | Dj1hRW/mR3GK7bJzbH6i/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32490 | N | N | 20 | HARD LANDSCAPING |  | 125449 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 232 | INTERLOCK MASON SK
%R | 504415 | 6359 | 125451 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7WEEX5030 | Excavation | 8177 | 304 | 0 | 160 | 0 | 64 | 64 | 160 | 40 | 0 | 40 |  |  |  | 2014-06-28 08:00 | 2014-07-20 17:00 |  | 2014-05-14 08:00 | 2014-06-05 17:00 | 2014-05-14 08:00 | 2014-06-05 17:00 | 2014-05-14 08:00 | 2014-06-05 17:00 | 2014-06-28 08:00 | 2014-07-20 17:00 |  | PT_Normal |  |  |  |  | YETkWluJQMOEZW+D99P8Rg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32480 | N | N | 15 | WATER TANK ENCLOSURE |  | 125449 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 64 | LABOR - CIVIL
%R | 504416 | 6359 | 125451 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7WEEX5035 | Construction of Raft | 8165 | 304 | 0 | 200 | 0 | 840 | 840 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-03 08:00 | 2014-07-31 17:00 |  | 2014-05-20 08:00 | 2014-06-17 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 | 2014-07-03 08:00 | 2014-07-31 17:00 |  | PT_Normal |  |  |  |  | CqVElic/S/S07ukGDSVr/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32480 | N | N | 15 | WATER TANK ENCLOSURE |  | 125449 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 840 | STEEL FIXERS SK
%R | 504417 | 6359 | 125451 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7WEEX5040 | Block works & Plastering | 8168 | 304 | 0 | 200 | 0 | 512 | 512 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-13 08:00 | 2014-08-13 17:00 |  | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 |  | PT_Normal |  |  |  |  | T0aEqewuRPOwVL0oKUzOow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32480 | N | N | 15 | WATER TANK ENCLOSURE |  | 125449 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 512 | BLOCK MASON SK
%R | 504418 | 6359 | 125451 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7WEEX5045 | Flooring & Painting | 8178 | 304 | 152 | 200 | 0 | 232 | 232 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-20 08:00 | 2014-08-20 17:00 |  | 2014-06-05 08:00 | 2014-07-03 17:00 | 2014-06-05 08:00 | 2014-07-03 17:00 | 2014-06-05 08:00 | 2014-07-03 17:00 | 2014-07-20 08:00 | 2014-08-20 17:00 |  | PT_Normal |  |  |  |  | Uu9dkVRgSQKXKRWv05Hdpw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32480 | N | N | 15 | WATER TANK ENCLOSURE |  | 125449 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 232 | LABOR- SUBCONTRACTOR
%R | 504419 | 6359 | 125451 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7WEEX5050 | Installation of Steel Gate | 8178 | 152 | 72 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-05 08:00 | 2014-08-27 17:00 |  | 2014-07-10 08:00 | 2014-08-05 17:00 | 2014-07-10 08:00 | 2014-08-05 17:00 | 2014-07-10 08:00 | 2014-08-05 17:00 | 2014-08-05 08:00 | 2014-08-27 17:00 |  | PT_Normal |  |  |  |  | tTLJG4F4Rj6znRRRcffneA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32480 | N | N | 15 | WATER TANK ENCLOSURE |  | 125449 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 56 | LABOR- SUBCONTRACTOR
%R | 504420 | 6359 | 125451 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 80 | 0 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-11 08:00 | 2014-09-08 17:00 |  | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-08-11 08:00 | 2014-09-08 17:00 |  | PT_Normal |  |  |  |  | yPeTqcxMSdm9rswRggYAQA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32480 | N | N | 15 | WATER TANK ENCLOSURE |  | 125449 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 168 | LABOR- SUBCONTRACTOR
%R | 504421 | 6359 | 125451 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 72 | 0 | 200 | 0 | 203.2 | 203.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-08-07 08:00 | 2014-09-04 17:00 | 2014-08-07 08:00 | 2014-09-04 17:00 | 2014-08-07 08:00 | 2014-09-04 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | d77VK0eVRmac3vfQblSK2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32480 | N | N | 15 | WATER TANK ENCLOSURE |  | 125449 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 203.2 | LABOR- SUBCONTRACTOR
%R | 504422 | 6359 | 125452 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 504 | 64 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-30 08:00 | 2014-11-27 17:00 |  | 2014-08-16 08:00 | 2014-09-13 17:00 | 2014-08-16 08:00 | 2014-09-13 17:00 | 2014-08-16 08:00 | 2014-09-13 17:00 | 2014-10-30 08:00 | 2014-11-27 17:00 |  | PT_Normal |  |  |  |  | zjylguJGT0KUPavM3sAiaA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32470 | N | N | 10 | MISCELLANEOUS |  | 125449 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 400 | LABOR- SUBCONTRACTOR
%R | 504423 | 6359 | 125452 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7MSEX5020 | Construction Entrance Ramp | 8164 | 128 | 0 | 200 | 0 | 656 | 656 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-30 08:00 | 2014-07-28 17:00 |  | 2014-06-11 08:00 | 2014-07-09 17:00 | 2014-06-11 08:00 | 2014-07-09 17:00 | 2014-06-11 08:00 | 2014-07-09 17:00 | 2014-06-30 08:00 | 2014-07-28 17:00 |  | PT_Normal |  |  |  |  | C0+3M8y1T0ecrQZDPhQ9lw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32470 | N | N | 10 | MISCELLANEOUS |  | 125449 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 656 | SCREED MASON SK
%R | 504424 | 6359 | 125452 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7MSEX5025 | SS.Handrails and Balustrades | 8178 | 152 | 0 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-21 08:00 | 2014-08-16 17:00 |  | 2014-06-29 08:00 | 2014-07-21 17:00 | 2014-06-29 08:00 | 2014-07-21 17:00 | 2014-06-29 08:00 | 2014-07-21 17:00 | 2014-07-21 08:00 | 2014-08-16 17:00 |  | PT_Normal |  |  |  |  | xfn+mY3CRMONned0u/pe3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32470 | N | N | 10 | MISCELLANEOUS |  | 125449 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 56 | LABOR- SUBCONTRACTOR
%R | 504425 | 6359 | 125452 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7MSEX5015 | Construction of grease Trap | 8178 | 64 | 0 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-03 08:00 | 2014-06-25 17:00 |  | 2014-05-25 08:00 | 2014-06-16 17:00 | 2014-05-25 08:00 | 2014-06-16 17:00 | 2014-05-25 08:00 | 2014-06-16 17:00 | 2014-06-03 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | tCZKYH1NRgOMa92+MdSvsA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32470 | N | N | 10 | MISCELLANEOUS |  | 125449 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 56 | LABOR- SUBCONTRACTOR
%R | 504426 | 6359 | 125452 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7MSEX5000 | Construction of Manholes | 8172 | 64 | 0 | 200 | 0 | 528 | 528 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-30 08:00 | 2014-05-28 17:00 |  | 2014-04-21 08:00 | 2014-05-19 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 |  | PT_Normal |  |  |  |  | Lp6AZ+GNQnqAtt67bMW4/w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32470 | N | N | 10 | MISCELLANEOUS |  | 125449 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 528 | MANHOLES SK
%R | 504427 | 6359 | 125452 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7MSEX5005 | Construction of Soak pit, Chambers | 8172 | 64 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-14 08:00 | 2014-06-11 17:00 |  | 2014-05-05 08:00 | 2014-06-02 17:00 | 2014-05-05 08:00 | 2014-06-02 17:00 | 2014-05-05 08:00 | 2014-06-02 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 |  | PT_Normal |  |  |  |  | J0cFK38WSV6bGFU4T+hfgQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32470 | N | N | 10 | MISCELLANEOUS |  | 125449 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 176 | MANHOLES SK
%R | 504428 | 6359 | 125452 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7MSEX5010 | Telephone cable laying | 8177 | 64 | 0 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-26 08:00 | 2014-07-24 17:00 |  | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-26 08:00 | 2014-07-24 17:00 |  | PT_Normal |  |  |  |  | Oi3Gx2uLQ5CGqTrl+vHKIA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32470 | N | N | 10 | MISCELLANEOUS |  | 125449 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 500 | LABOR - CIVIL
%R | 504429 | 6359 | 125453 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7SLEX5105 | Laying of Grass/ green area | 8178 | 128 | 0 | 200 | 0 | 2744 | 2744 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-11 08:00 | 2014-09-08 17:00 |  | 2014-07-20 08:00 | 2014-08-20 17:00 | 2014-07-20 08:00 | 2014-08-20 17:00 | 2014-07-20 08:00 | 2014-08-20 17:00 | 2014-08-11 08:00 | 2014-09-08 17:00 |  | PT_Normal |  |  |  |  | Yz49jIgCRzm+79i2NA88iA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32500 | N | N | 25 | SOFT LANDSCAPING |  | 125449 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 1372 | LABOR- SUBCONTRACTOR
%R | 504430 | 6359 | 125453 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7SLEX5110 | Laying of Palm tree | 8178 | 128 | 128 | 200 | 0 | 168 | 168 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | aaDybtglTNSROXfZVdQm8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32500 | N | N | 25 | SOFT LANDSCAPING |  | 125449 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 84 | LABOR- SUBCONTRACTOR
%R | 504431 | 6359 | 125456 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARRF3630 | Leveling Screed for Waterproofing | 8164 | 168 | 0 | 200 | 0 | 800 | 800 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-03 08:00 | 2014-07-31 17:00 |  | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-07-03 08:00 | 2014-07-31 17:00 |  | PT_Normal |  |  |  |  | J06t1rJ+RlaOIhAc98N2/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32300 | N | N | 10 | ROOF |  | 125455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 800 | SCREED MASON SK
%R | 504432 | 6359 | 125456 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARRF3635 | Laying of Waterproofing Membrane | 8178 | 168 | 0 | 200 | 0 | 1138.5 | 1138.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-07 08:00 | 2014-08-07 17:00 |  | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-07-07 08:00 | 2014-08-07 17:00 |  | PT_Normal |  |  |  |  | HRLSTDlIRK6ubWf+csz0fQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32300 | N | N | 10 | ROOF |  | 125455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1138.5 | LABOR- SUBCONTRACTOR
%R | 504433 | 6359 | 125456 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARRF3640 | Installation of Insulation & Protection | 8178 | 168 | 0 | 200 | 0 | 1408 | 1408 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-12 08:00 | 2014-08-12 17:00 |  | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 |  | PT_Normal |  |  |  |  | KKCyVLqqQ8WRCxSbe1+tSQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32300 | N | N | 10 | ROOF |  | 125455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1408 | LABOR- SUBCONTRACTOR
%R | 504434 | 6359 | 125456 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 168 | 0 | 200 | 0 | 688.25 | 688.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | N68KErbSR4qcQx4ksq3HFg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32300 | N | N | 10 | ROOF |  | 125455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 688.25 | TILE MASON SK
%R | 504435 | 6359 | 125456 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 168 | 0 | 160 | 0 | 616 | 616 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-09-03 17:00 |  | 2014-07-15 08:00 | 2014-08-10 17:00 | 2014-07-15 08:00 | 2014-08-10 17:00 | 2014-07-15 08:00 | 2014-08-10 17:00 | 2014-08-12 08:00 | 2014-09-03 17:00 |  | PT_Normal |  |  |  |  | 0/SlnlqSRH+Rhf0hbEdw4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32300 | N | N | 10 | ROOF |  | 125455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 616 | LABOR- SUBCONTRACTOR
%R | 504436 | 6359 | 125456 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 168 | 0 | 200 | 0 | 1046.5 | 1046.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-24 08:00 | 2014-08-25 17:00 |  | 2014-06-30 08:00 | 2014-07-28 17:00 | 2014-06-30 08:00 | 2014-07-28 17:00 | 2014-06-30 08:00 | 2014-07-28 17:00 | 2014-07-24 08:00 | 2014-08-25 17:00 |  | PT_Normal |  |  |  |  | xb+MXp52QwqCNcRjUZtP3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32300 | N | N | 10 | ROOF |  | 125455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1046.5 | LABOR- SUBCONTRACTOR
%R | 504437 | 6359 | 125456 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARRF3660 | Installation of Access Ladder | 8178 | 208 | 208 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-15 17:00 |  | 2014-07-27 08:00 | 2014-08-16 17:00 | 2014-07-27 08:00 | 2014-08-16 17:00 | 2014-07-27 08:00 | 2014-08-16 17:00 | 2014-08-30 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | BjITlB7xSVarnyBt01JQPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32300 | N | N | 10 | ROOF |  | 125455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 176 | LABOR- SUBCONTRACTOR
%R | 504438 | 6359 | 125457 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7AREL3665 | External Plastering | 8169 | 376 | 0 | 200 | 0 | 14275 | 14275 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-20 08:00 | 2014-08-20 17:00 |  | 2014-05-26 08:00 | 2014-06-23 17:00 | 2014-05-26 08:00 | 2014-06-23 17:00 | 2014-05-26 08:00 | 2014-06-23 17:00 | 2014-07-20 08:00 | 2014-08-20 17:00 |  | PT_Normal |  |  |  |  | 8U5tErdeSVyMXy6iH1Ae3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32310 | N | N | 15 | ELEVATION |  | 125455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 14275 | PLASTER MASON SK
%R | 504439 | 6359 | 125457 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7AREL3670 | External stone cladding works | 8170 | 392 | 0 | 160 | 0 | 990 | 990 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-09-03 17:00 |  | 2014-06-12 08:00 | 2014-07-05 17:00 | 2014-06-12 08:00 | 2014-07-05 17:00 | 2014-06-12 08:00 | 2014-07-05 17:00 | 2014-08-12 08:00 | 2014-09-03 17:00 |  | PT_Normal |  |  |  |  | 8Rrhg1vZTMa05WGXtCjzKA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32310 | N | N | 15 | ELEVATION |  | 125455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 990 | TILE MASON SK
%R | 504440 | 6359 | 125457 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7AREL3680 | External Painting | 8178 | 392 | 40 | 160 | 0 | 3784 | 3784 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-24 08:00 | 2014-09-15 17:00 |  | 2014-06-24 08:00 | 2014-07-16 17:00 | 2014-06-24 08:00 | 2014-07-16 17:00 | 2014-06-24 08:00 | 2014-07-16 17:00 | 2014-08-24 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | cYj0xXAEQM6GpNNLyUe26g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32310 | N | N | 15 | ELEVATION |  | 125455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 3784 | LABOR- SUBCONTRACTOR
%R | 504441 | 6359 | 125459 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARRF3600 | Block work | 8168 | 416 | 0 | 160 | 0 | 700 | 700 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-03 08:00 | 2014-07-26 17:00 |  | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-07-03 08:00 | 2014-07-26 17:00 |  | PT_Normal |  |  |  |  | uFWQ0t4fRQeXVAuHFxoaRw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32280 | N | N | 20 | ROOF |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 700 | BLOCK MASON SK
%R | 504442 | 6359 | 125459 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARRF3605 | Plastering work | 8169 | 416 | 0 | 160 | 0 | 1786.5 | 1786.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-12 08:00 | 2014-08-06 17:00 |  | 2014-05-12 08:00 | 2014-06-03 17:00 | 2014-05-12 08:00 | 2014-06-03 17:00 | 2014-05-12 08:00 | 2014-06-03 17:00 | 2014-07-12 08:00 | 2014-08-06 17:00 |  | PT_Normal |  |  |  |  | BaE8a/mMSQOWeWqIOBLhZg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32280 | N | N | 20 | ROOF |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1786.5 | PLASTER MASON SK
%R | 504443 | 6359 | 125459 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARRF3610 | Flooring screed | 8164 | 456 | 0 | 120 | 0 | 136.5 | 136.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-31 08:00 | 2014-08-20 17:00 |  | 2014-05-26 08:00 | 2014-06-11 17:00 | 2014-05-26 08:00 | 2014-06-11 17:00 | 2014-05-26 08:00 | 2014-06-11 17:00 | 2014-07-31 08:00 | 2014-08-20 17:00 |  | PT_Normal |  |  |  |  | 00B5guiJS6WzApH2GwEreA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32280 | N | N | 20 | ROOF |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 136.5 | SCREED MASON SK
%R | 504444 | 6359 | 125459 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARRF3695 | Painting -Storage area | 8178 | 456 | 0 | 160 | 0 | 1640 | 1640 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-09-03 17:00 |  | 2014-06-03 08:00 | 2014-06-25 17:00 | 2014-06-03 08:00 | 2014-06-25 17:00 | 2014-06-03 08:00 | 2014-06-25 17:00 | 2014-08-12 08:00 | 2014-09-03 17:00 |  | PT_Normal |  |  |  |  | /qc1lOkjQMCmWFRSWQU0Bg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32280 | N | N | 20 | ROOF |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1640 | LABOR- SUBCONTRACTOR
%R | 504445 | 6359 | 125459 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARRF3620 | Epoxy Painting -Storage area | 8178 | 456 | 456 | 120 | 0 | 48.5 | 48.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-15 17:00 |  | 2014-06-21 08:00 | 2014-07-07 17:00 | 2014-06-21 08:00 | 2014-07-07 17:00 | 2014-06-21 08:00 | 2014-07-07 17:00 | 2014-08-30 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | QhCB/z2kQCGYl1mUAnckIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32280 | N | N | 20 | ROOF |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 48.5 | LABOR- SUBCONTRACTOR
%R | 504446 | 6359 | 125460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARFF3310 | Flooring screed | 8164 | 96 | 96 | 168 | 0 | 1215.5 | 1215.5 | 168 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-06-29 17:00 |  | 2014-05-22 08:00 | 2014-06-15 17:00 | 2014-05-22 08:00 | 2014-06-15 17:00 | 2014-05-22 08:00 | 2014-06-15 17:00 | 2014-06-05 08:00 | 2014-06-29 17:00 |  | PT_Normal |  |  |  |  | UZlG7BjsRmSegs7BVF3I0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32270 | N | N | 15 | FIRST FLOORS |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1215.5 | SCREED MASON SK
%R | 504447 | 6359 | 125460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARFF3315 | Wet area waterproofing | 8178 | 0 | 0 | 120 | 0 | 1215.5 | 1215.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-03 08:00 | 2014-06-19 17:00 |  | 2014-06-03 08:00 | 2014-06-19 17:00 | 2014-06-03 08:00 | 2014-06-19 17:00 | 2014-06-03 08:00 | 2014-06-19 17:00 | 2014-06-03 08:00 | 2014-06-19 17:00 |  | PT_Normal |  |  |  |  | YpwpwNbERIWlczQtruHFzQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32270 | N | N | 15 | FIRST FLOORS |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1215.5 | LABOR- SUBCONTRACTOR
%R | 504448 | 6359 | 125460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARFF3330 | Paint First coat | 8178 | 112 | 112 | 200 | 0 | 4742.75 | 4742.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-16 08:00 | 2014-07-14 17:00 |  | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 |  | PT_Normal |  |  |  |  | PS0LkYhcQraAQT9ZhkCrRA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32270 | N | N | 15 | FIRST FLOORS |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 4742.75 | LABOR- SUBCONTRACTOR
%R | 504449 | 6359 | 125460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARFF3320 | Ceramic Wall Tiling | 8170 | 0 | 0 | 200 | 0 | 1897.25 | 1897.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-10 08:00 | 2014-07-08 17:00 |  | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 |  | PT_Normal |  |  |  |  | qrPwnIvGRty7W/JxSUpG2Q |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32270 | N | N | 15 | FIRST FLOORS |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1897.25 | TILE MASON SK
%R | 504450 | 6359 | 125460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARFF3325 | Porcelain Tile flooring | 8170 | 0 | 0 | 200 | 0 | 1743.75 | 1743.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | 9o3hSbvwRyuK92kfeIShFA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32270 | N | N | 15 | FIRST FLOORS |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1743.75 | TILE MASON SK
%R | 504451 | 6359 | 125460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARFF3335 | Slate Tile Flooring & Skirting | 8170 | 64 | 64 | 120 | 0 | 261.5 | 261.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-14 08:00 | 2014-07-30 17:00 |  | 2014-07-05 08:00 | 2014-07-21 17:00 | 2014-07-05 08:00 | 2014-07-21 17:00 | 2014-07-05 08:00 | 2014-07-21 17:00 | 2014-07-14 08:00 | 2014-07-30 17:00 |  | PT_Normal |  |  |  |  | PLw+6434SfSggMHWhZ/6lA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32270 | N | N | 15 | FIRST FLOORS |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 261.5 | TILE MASON SK
%R | 504452 | 6359 | 125460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARFF3350 | Granite - Stair case flooring & Skirting | 8171 | 16 | 16 | 160 | 0 | 875 | 875 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-10 08:00 | 2014-08-05 17:00 |  | 2014-07-08 08:00 | 2014-07-30 17:00 | 2014-07-08 08:00 | 2014-07-30 17:00 | 2014-07-08 08:00 | 2014-07-30 17:00 | 2014-07-10 08:00 | 2014-08-05 17:00 |  | PT_Normal |  |  |  |  | 9E4kwK17REmS54DrDhqgew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32270 | N | N | 15 | FIRST FLOORS |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 875 | GRANITE MASON SK
%R | 504453 | 6359 | 125460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARFF3345 | Fixing of Suspension systems | 8178 | 0 | 0 | 160 | 0 | 1305 | 1305 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-30 08:00 | 2014-07-22 17:00 |  | 2014-06-30 08:00 | 2014-07-22 17:00 | 2014-06-30 08:00 | 2014-07-22 17:00 | 2014-06-30 08:00 | 2014-07-22 17:00 | 2014-06-30 08:00 | 2014-07-22 17:00 |  | PT_Normal |  |  |  |  | 6uh2i1hnSPSLenjQWTZnJQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32270 | N | N | 15 | FIRST FLOORS |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1305 | LABOR- SUBCONTRACTOR
%R | 504454 | 6359 | 125460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARFF3360 | Gypsum board false ceiling | 8178 | 0 | 0 | 200 | 0 | 1305 | 1305 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-07 08:00 | 2014-08-07 17:00 |  | 2014-07-07 08:00 | 2014-08-07 17:00 | 2014-07-07 08:00 | 2014-08-07 17:00 | 2014-07-07 08:00 | 2014-08-07 17:00 | 2014-07-07 08:00 | 2014-08-07 17:00 |  | PT_Normal |  |  |  |  | coJMaNpyQjKGJo0GvpFisA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32270 | N | N | 15 | FIRST FLOORS |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 652.5 | LABOR- SUBCONTRACTOR
%R | 504455 | 6359 | 125460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARFF3365 | Wooden door | 8178 | 0 | 0 | 120 | 0 | 308 | 308 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-22 08:00 | 2014-08-11 17:00 |  | 2014-07-22 08:00 | 2014-08-11 17:00 | 2014-07-22 08:00 | 2014-08-11 17:00 | 2014-07-22 08:00 | 2014-08-11 17:00 | 2014-07-22 08:00 | 2014-08-11 17:00 |  | PT_Normal |  |  |  |  | UI52/wp9QkCgWBXje79rWg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32270 | N | N | 15 | FIRST FLOORS |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 308 | LABOR- SUBCONTRACTOR
%R | 504456 | 6359 | 125460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARFF3370 | Aluminum Door | 8178 | 0 | 0 | 160 | 0 | 220 | 220 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-22 08:00 | 2014-08-17 17:00 |  | 2014-07-22 08:00 | 2014-08-17 17:00 | 2014-07-22 08:00 | 2014-08-17 17:00 | 2014-07-22 08:00 | 2014-08-17 17:00 | 2014-07-22 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | aggVDvgaS56wC6T/DVsHAw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32270 | N | N | 15 | FIRST FLOORS |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 220 | LABOR- SUBCONTRACTOR
%R | 504457 | 6359 | 125460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARFF3380 | Aluminum windows | 8178 | 32 | 32 | 160 | 0 | 162.25 | 162.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-06 08:00 | 2014-08-28 17:00 |  | 2014-07-29 08:00 | 2014-08-24 17:00 | 2014-07-29 08:00 | 2014-08-24 17:00 | 2014-07-29 08:00 | 2014-08-24 17:00 | 2014-08-06 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | ZCFwbkDSQYKkSC8I+c2dDQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32270 | N | N | 15 | FIRST FLOORS |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 162.25 | LABOR- SUBCONTRACTOR
%R | 504458 | 6359 | 125460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARFF3375 | Carpentry & Joinery Works | 8178 | 0 | 0 | 200 | 0 | 1100 | 1100 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-28 08:00 | 2014-08-28 17:00 |  | 2014-07-28 08:00 | 2014-08-28 17:00 | 2014-07-28 08:00 | 2014-08-28 17:00 | 2014-07-28 08:00 | 2014-08-28 17:00 | 2014-07-28 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | HEUah5A5Q1OkxFmF5QU3BQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32270 | N | N | 15 | FIRST FLOORS |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 550 | LABOR- SUBCONTRACTOR
%R | 504459 | 6359 | 125460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARFF3390 | Installation of Granite Counter Top | 8171 | 8 | 8 | 160 | 0 | 88 | 88 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-13 08:00 | 2014-09-04 17:00 |  | 2014-08-12 08:00 | 2014-09-03 17:00 | 2014-08-12 08:00 | 2014-09-03 17:00 | 2014-08-12 08:00 | 2014-09-03 17:00 | 2014-08-13 08:00 | 2014-09-04 17:00 |  | PT_Normal |  |  |  |  | PJ9knusWTF2U5XZNPScDKw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32270 | N | N | 15 | FIRST FLOORS |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 88 | GRANITE MASON SK
%R | 504460 | 6359 | 125460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARFF3385 | Handrail & Balustrade | 8178 | 0 | 0 | 160 | 0 | 787.5 | 787.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-09-03 17:00 |  | 2014-08-12 08:00 | 2014-09-03 17:00 | 2014-08-12 08:00 | 2014-09-03 17:00 | 2014-08-12 08:00 | 2014-09-03 17:00 | 2014-08-12 08:00 | 2014-09-03 17:00 |  | PT_Normal |  |  |  |  | KIZecZFCTcajG5SlxVgHSA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32270 | N | N | 15 | FIRST FLOORS |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 787.5 | LABOR- SUBCONTRACTOR
%R | 504461 | 6359 | 125460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARFF3395 | Final Painting | 8178 | 0 | 0 | 200 | 0 | 4742.75 | 4742.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | WYaqUXSQTAWVjFkNdA6wGw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32270 | N | N | 15 | FIRST FLOORS |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 4742.75 | LABOR- SUBCONTRACTOR
%R | 504462 | 6359 | 125460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARFF3300 | Block work | 8168 | 0 | 0 | 200 | 0 | 6387.5 | 6387.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | +1CayyNkTR6KkQNDemQz/w |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32270 | N | N | 15 | FIRST FLOORS |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 6387.5 | BLOCK MASON SK
%R | 504463 | 6359 | 125460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARFF3305 | Plastering work | 8169 | 0 | 0 | 200 | 0 | 8899 | 8899 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-14 08:00 | 2014-06-11 17:00 |  | 2014-05-14 08:00 | 2014-06-11 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 |  | PT_Normal |  |  |  |  | OWNKdi8MT5iYE9fRZXBWyQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32270 | N | N | 15 | FIRST FLOORS |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 8899 | PLASTER MASON SK
%R | 504464 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3000 | Block work | 8168 | 144 | 0 | 200 | 0 | 9737.5 | 9737.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-30 08:00 | 2014-04-27 17:00 |  | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-30 08:00 | 2014-04-27 17:00 |  | PT_Normal |  |  |  |  | ft8aEp5USQqNLF9sfrZ7KQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 9737.5 | BLOCK MASON SK
%R | 504465 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3005 | Plastering work | 8169 | 144 | 0 | 200 | 0 | 13637.5 | 13637.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-21 08:00 | 2014-05-19 17:00 |  | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | /ZYny5pIQe+BjPgyluZ2Qw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 13637.5 | PLASTER MASON SK
%R | 504466 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3010 | Flooring screed | 8164 | 208 | 64 | 168 | 0 | 1580.25 | 1580.25 | 168 | 0 | 0 | 0 |  |  |  | 2014-05-08 08:00 | 2014-06-01 17:00 |  | 2014-04-08 08:00 | 2014-05-01 17:00 | 2014-04-08 08:00 | 2014-05-01 17:00 | 2014-04-08 08:00 | 2014-05-01 17:00 | 2014-05-08 08:00 | 2014-06-01 17:00 |  | PT_Normal |  |  |  |  | QZo1c3dsSRCoFhjDE5bOiw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1580.25 | SCREED MASON SK
%R | 504467 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 144 | 0 | 120 | 0 | 247.5 | 247.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-08 08:00 | 2014-05-25 17:00 |  | 2014-04-17 08:00 | 2014-05-04 17:00 | 2014-04-17 08:00 | 2014-05-04 17:00 | 2014-04-17 08:00 | 2014-05-04 17:00 | 2014-05-08 08:00 | 2014-05-25 17:00 |  | PT_Normal |  |  |  |  | oOcE/YEtTUyfuDKo3RAFvg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 247.5 | LABOR- SUBCONTRACTOR
%R | 504468 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3030 | Paint First coat | 8178 | 256 | 0 | 200 | 0 | 5425.75 | 5425.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-24 08:00 | 2014-06-21 17:00 |  | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 |  | PT_Normal |  |  |  |  | RomZZGSdST23krpq1kmYeg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 5425.75 | LABOR- SUBCONTRACTOR
%R | 504469 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3020 | Ceramic Wall Tiling | 8170 | 144 | 0 | 200 | 0 | 4428.5 | 4428.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-14 08:00 | 2014-06-11 17:00 |  | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 |  | PT_Normal |  |  |  |  | ozvS4IJVR9C8e40l7OZ57A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 4428.5 | TILE MASON SK
%R | 504470 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3025 | Porcelain Tile flooring | 8170 | 144 | 0 | 200 | 0 | 1743.75 | 1743.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-20 08:00 | 2014-06-17 17:00 |  | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | PoZGXMQVTXKuuWAhORG2FQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1743.75 | TILE MASON SK
%R | 504471 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3040 | Cobble Tile flooring | 8170 | 168 | 0 | 120 | 0 | 741 | 741 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-19 08:00 | 2014-07-06 17:00 |  | 2014-05-26 08:00 | 2014-06-11 17:00 | 2014-05-26 08:00 | 2014-06-11 17:00 | 2014-05-26 08:00 | 2014-06-11 17:00 | 2014-06-19 08:00 | 2014-07-06 17:00 |  | PT_Normal |  |  |  |  | AvnJtCq0QoyY5avBcXoRBA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 741 | TILE MASON SK
%R | 504472 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 184 | 16 | 120 | 0 | 761.5 | 761.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-01 17:00 |  | 2014-05-19 08:00 | 2014-06-04 17:00 | 2014-05-19 08:00 | 2014-06-04 17:00 | 2014-05-19 08:00 | 2014-06-04 17:00 | 2014-06-15 08:00 | 2014-07-01 17:00 |  | PT_Normal |  |  |  |  | ZzZ2nKctQVerrN/8ObQe8A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 761.5 | TILE MASON SK
%R | 504473 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 168 | 0 | 160 | 0 | 875 | 875 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-28 08:00 | 2014-07-20 17:00 |  | 2014-06-03 08:00 | 2014-06-25 17:00 | 2014-06-03 08:00 | 2014-06-25 17:00 | 2014-06-03 08:00 | 2014-06-25 17:00 | 2014-06-28 08:00 | 2014-07-20 17:00 |  | PT_Normal |  |  |  |  | KxinKKupRIamH9RpWqVseA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 875 | GRANITE MASON SK
%R | 504474 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3045 | Fixing of Suspension systems | 8178 | 144 | 0 | 160 | 0 | 1455.05 | 1455.05 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-07 08:00 | 2014-06-29 17:00 |  | 2014-05-17 08:00 | 2014-06-08 17:00 | 2014-05-17 08:00 | 2014-06-08 17:00 | 2014-05-17 08:00 | 2014-06-08 17:00 | 2014-06-07 08:00 | 2014-06-29 17:00 |  | PT_Normal |  |  |  |  | 84O3h6EkQOeroMFs6UV08A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1455.05 | LABOR- SUBCONTRACTOR
%R | 504475 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3055 | Aluminum tile false ceiling | 8178 | 168 | 24 | 200 | 0 | 150 | 150 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-18 08:00 | 2014-07-16 17:00 |  | 2014-05-25 08:00 | 2014-06-22 17:00 | 2014-05-25 08:00 | 2014-06-22 17:00 | 2014-05-25 08:00 | 2014-06-22 17:00 | 2014-06-18 08:00 | 2014-07-16 17:00 |  | PT_Normal |  |  |  |  | NHj2Olc/Tg2fihAOuj1tgQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 150 | LABOR- SUBCONTRACTOR
%R | 504476 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3060 | Gypsum board false ceiling | 8178 | 144 | 0 | 200 | 0 | 1335.15 | 1335.15 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-18 08:00 | 2014-07-16 17:00 |  | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-06-18 08:00 | 2014-07-16 17:00 |  | PT_Normal |  |  |  |  | j1Ykc1uMQuWBsxU/Laoq6w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1335.15 | LABOR- SUBCONTRACTOR
%R | 504477 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3065 | Wooden door & PVC Door | 8178 | 168 | 0 | 120 | 0 | 308 | 308 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-12 08:00 | 2014-07-28 17:00 |  | 2014-06-17 08:00 | 2014-07-03 17:00 | 2014-06-17 08:00 | 2014-07-03 17:00 | 2014-06-17 08:00 | 2014-07-03 17:00 | 2014-07-12 08:00 | 2014-07-28 17:00 |  | PT_Normal |  |  |  |  | mzslrVSFSWiGVTv6FyRmbQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 308 | LABOR- SUBCONTRACTOR
%R | 504478 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3070 | Aluminum doors | 8178 | 168 | 0 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-17 08:00 | 2014-08-06 17:00 |  | 2014-06-23 08:00 | 2014-07-09 17:00 | 2014-06-23 08:00 | 2014-07-09 17:00 | 2014-06-23 08:00 | 2014-07-09 17:00 | 2014-07-17 08:00 | 2014-08-06 17:00 |  | PT_Normal |  |  |  |  | N+yjZTDLQCeRD4UlBp5GiA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 176 | LABOR- SUBCONTRACTOR
%R | 504479 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3080 | Aluminum windows | 8178 | 248 | 40 | 160 | 0 | 162.25 | 162.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-09 08:00 | 2014-08-31 17:00 |  | 2014-06-30 08:00 | 2014-07-22 17:00 | 2014-06-30 08:00 | 2014-07-22 17:00 | 2014-06-30 08:00 | 2014-07-22 17:00 | 2014-08-09 08:00 | 2014-08-31 17:00 |  | PT_Normal |  |  |  |  | AhE37puWRFC4tAKHabhlHg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 162.25 | LABOR- SUBCONTRACTOR
%R | 504480 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3075 | Carpentry & Joinery Works | 8178 | 168 | 0 | 160 | 0 | 572 | 572 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-23 08:00 | 2014-08-18 17:00 |  | 2014-06-29 08:00 | 2014-07-21 17:00 | 2014-06-29 08:00 | 2014-07-21 17:00 | 2014-06-29 08:00 | 2014-07-21 17:00 | 2014-07-23 08:00 | 2014-08-18 17:00 |  | PT_Normal |  |  |  |  | TVFRhc2nR5WSfspiFTPjvA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 572 | LABOR- SUBCONTRACTOR
%R | 504481 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3090 | Installation of Granite Counter Top | 8171 | 168 | 0 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-09 08:00 | 2014-08-25 17:00 |  | 2014-07-12 08:00 | 2014-07-28 17:00 | 2014-07-12 08:00 | 2014-07-28 17:00 | 2014-07-12 08:00 | 2014-07-28 17:00 | 2014-08-09 08:00 | 2014-08-25 17:00 |  | PT_Normal |  |  |  |  | CLecDlbuSc+jVUn1USdryg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 176 | GRANITE MASON SK
%R | 504482 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3085 | S.S.Balustrade | 8178 | 208 | 40 | 160 | 0 | 262.5 | 262.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-10 08:00 | 2014-09-01 17:00 |  | 2014-07-07 08:00 | 2014-07-29 17:00 | 2014-07-07 08:00 | 2014-07-29 17:00 | 2014-07-07 08:00 | 2014-07-29 17:00 | 2014-08-10 08:00 | 2014-09-01 17:00 |  | PT_Normal |  |  |  |  | 82dASGhaSc2fCX0xRyJiig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 262.5 | LABOR- SUBCONTRACTOR
%R | 504483 | 6359 | 125461 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ARGF3095 | Final Painting | 8178 | 168 | 0 | 200 | 0 | 5425.75 | 5425.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-07-21 08:00 | 2014-08-21 17:00 | 2014-07-21 08:00 | 2014-08-21 17:00 | 2014-07-21 08:00 | 2014-08-21 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | rFi/oqLmQ8ihIqvifj065g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32260 | N | N | 10 | GROUND FLOOR |  | 125458 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 2712.875 | LABOR- SUBCONTRACTOR
%R | 504484 | 6359 | 125464 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7PLFF4330 | Installation of Drainage pipes & testing | 8178 | 176 | 56 | 144 | 0 | 177.6 | 177.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-06-02 08:00 | 2014-06-22 17:00 |  | 2014-05-07 08:00 | 2014-05-27 17:00 | 2014-05-07 08:00 | 2014-05-27 17:00 | 2014-05-07 08:00 | 2014-05-27 17:00 | 2014-06-02 08:00 | 2014-06-22 17:00 |  | PT_Normal |  |  |  |  | /QArbT4LSu6G6NFJgnM1Jw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32390 | N | N | 15 | FIRST FLOORS |  | 125463 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 177.6 | LABOR- SUBCONTRACTOR
%R | 504485 | 6359 | 125464 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7PLFF4335 | Sanitary Fittings & Accessories | 8178 | 40 | 0 | 160 | 0 | 67.2 | 67.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-28 08:00 | 2014-08-23 17:00 |  | 2014-07-22 08:00 | 2014-08-17 17:00 | 2014-07-22 08:00 | 2014-08-17 17:00 | 2014-07-22 08:00 | 2014-08-17 17:00 | 2014-07-28 08:00 | 2014-08-23 17:00 |  | PT_Normal |  |  |  |  | d/vSbUX4QhCuf1Jf0RrNwA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32390 | N | N | 15 | FIRST FLOORS |  | 125463 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504486 | 6359 | 125464 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7PLFF4340 | Installation of Water Heater | 8178 | 40 | 32 | 120 | 0 | 67.2 | 67.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-08-28 17:00 |  | 2014-08-06 08:00 | 2014-08-23 17:00 | 2014-08-06 08:00 | 2014-08-23 17:00 | 2014-08-06 08:00 | 2014-08-23 17:00 | 2014-08-12 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | byoChGt7Q1OjzG/4T0MjHQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32390 | N | N | 15 | FIRST FLOORS |  | 125463 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504487 | 6359 | 125464 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 0 | 0 | 144 | 0 | 441.6 | 441.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-05-07 08:00 | 2014-05-27 17:00 |  | 2014-05-07 08:00 | 2014-05-27 17:00 | 2014-05-07 08:00 | 2014-05-27 17:00 | 2014-05-07 08:00 | 2014-05-27 17:00 | 2014-05-07 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | 8J/Y6QUmQW2oVOoIe12Dpg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32390 | N | N | 15 | FIRST FLOORS |  | 125463 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 441.6 | LABOR- SUBCONTRACTOR
%R | 504488 | 6359 | 125465 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 448 | 240 | 120 | 0 | 110.4 | 110.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-30 08:00 | 2014-08-19 17:00 |  | 2014-05-26 08:00 | 2014-06-11 17:00 | 2014-05-26 08:00 | 2014-06-11 17:00 | 2014-05-26 08:00 | 2014-06-11 17:00 | 2014-07-30 08:00 | 2014-08-19 17:00 |  | PT_Normal |  |  |  |  | MDLzBoqmTiao7Z6r5IxUkw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32400 | N | N | 20 | ROOF |  | 125463 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 110.4 | LABOR- SUBCONTRACTOR
%R | 504489 | 6359 | 125465 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7PLRF4350 | Installation of Rain water Pipes | 8178 | 208 | 80 | 120 | 0 | 67.2 | 67.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-08-28 17:00 |  | 2014-07-09 08:00 | 2014-07-26 17:00 | 2014-07-09 08:00 | 2014-07-26 17:00 | 2014-07-09 08:00 | 2014-07-26 17:00 | 2014-08-12 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | HjDt+6iNS+aXN+1pN8qHnw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32400 | N | N | 20 | ROOF |  | 125463 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504490 | 6359 | 125465 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 8 | 0 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | nRPaXxtWQe+/dPjhraVP2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32400 | N | N | 20 | ROOF |  | 125463 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 336 | LABOR- SUBCONTRACTOR
%R | 504491 | 6359 | 125466 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7PLGF4315 | Sanitary Fittings & Accessories | 8178 | 360 | 0 | 160 | 0 | 134.4 | 134.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-09 17:00 |  | 2014-06-23 08:00 | 2014-07-15 17:00 | 2014-06-23 08:00 | 2014-07-15 17:00 | 2014-06-23 08:00 | 2014-07-15 17:00 | 2014-08-18 08:00 | 2014-09-09 17:00 |  | PT_Normal |  |  |  |  | AO5/udcLQbiQ5a1SVE0Cuw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32380 | N | N | 10 | GROUND FLOOR |  | 125463 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 504492 | 6359 | 125466 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7PLGF4320 | Installation of Water Heater | 8178 | 360 | 80 | 120 | 0 | 134.4 | 134.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-15 17:00 |  | 2014-07-05 08:00 | 2014-07-21 17:00 | 2014-07-05 08:00 | 2014-07-21 17:00 | 2014-07-05 08:00 | 2014-07-21 17:00 | 2014-08-30 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | o9IIr/aXRaWS0ZiKDTs9PQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32380 | N | N | 10 | GROUND FLOOR |  | 125463 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 504493 | 6359 | 125466 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 0 | 0 | 128 | 0 | 67.2 | 67.2 | 128 | 0 | 0 | 0 |  |  |  | 2013-12-01 08:00 | 2013-12-19 17:00 |  | 2013-12-01 08:00 | 2013-12-19 17:00 | 2013-12-01 08:00 | 2013-12-19 17:00 | 2013-12-01 08:00 | 2013-12-19 17:00 | 2013-12-01 08:00 | 2013-12-19 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32380 | N | N | 10 | GROUND FLOOR |  | 125463 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504494 | 6359 | 125466 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 144 | 0 | 144 | 0 | 441.6 | 441.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-05 17:00 |  | 2014-03-25 08:00 | 2014-04-14 17:00 | 2014-03-25 08:00 | 2014-04-14 17:00 | 2014-03-25 08:00 | 2014-04-14 17:00 | 2014-04-15 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | gbIPEN3JTg++3w4AHdHLPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32380 | N | N | 10 | GROUND FLOOR |  | 125463 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 441.6 | LABOR- SUBCONTRACTOR
%R | 504495 | 6359 | 125466 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7PLGF4310 | Installation of Drainage pipes &testing | 8178 | 168 | 104 | 144 | 0 | 177.6 | 177.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-19 08:00 | 2014-05-08 17:00 |  | 2014-03-25 08:00 | 2014-04-14 17:00 | 2014-03-25 08:00 | 2014-04-14 17:00 | 2014-03-25 08:00 | 2014-04-14 17:00 | 2014-04-19 08:00 | 2014-05-08 17:00 |  | PT_Normal |  |  |  |  | b7rmQeqIRqiekphmXHWdBw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32380 | N | N | 10 | GROUND FLOOR |  | 125463 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 177.6 | LABOR- SUBCONTRACTOR
%R | 504496 | 6359 | 125468 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ELRF4070 | Installation of Isolator | 8178 | 8 | 0 | 144 | 0 | 412.8 | 412.8 | 144 | 0 | 0 | 0 |  |  |  | 2014-08-14 08:00 | 2014-09-03 17:00 |  | 2014-08-13 08:00 | 2014-09-02 17:00 | 2014-08-13 08:00 | 2014-09-02 17:00 | 2014-08-13 08:00 | 2014-09-02 17:00 | 2014-08-14 08:00 | 2014-09-03 17:00 |  | PT_Normal |  |  |  |  | zBBuJaQSS/a+FbFEJePcaA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32360 | N | N | 20 | ROOF |  | 125467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 412.8 | LABOR- SUBCONTRACTOR
%R | 504497 | 6359 | 125468 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ELRF4075 | Installation of TV Dish Antenna | 8178 | 8 | 8 | 184 | 0 | 732.8 | 732.8 | 184 | 0 | 0 | 0 |  |  |  | 2014-08-20 08:00 | 2014-09-15 17:00 |  | 2014-08-19 08:00 | 2014-09-14 17:00 | 2014-08-19 08:00 | 2014-09-14 17:00 | 2014-08-19 08:00 | 2014-09-14 17:00 | 2014-08-20 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | fQHzVNJQToSOucvxYJfXLg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32360 | N | N | 20 | ROOF |  | 125467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 732.8 | LABOR- SUBCONTRACTOR
%R | 504498 | 6359 | 125469 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 88 | 0 | 200 | 0 | 1222.4 | 1222.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-08 08:00 | 2014-06-05 17:00 |  | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-05-08 08:00 | 2014-06-05 17:00 |  | PT_Normal |  |  |  |  | K/jyP5p9TfeUyk3reqD73Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32350 | N | N | 15 | FIRST FLOORS |  | 125467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1222.4 | LABOR- SUBCONTRACTOR
%R | 504499 | 6359 | 125469 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ELFF4040 | Cable tray & trunking installation | 8178 | 232 | 16 | 160 | 0 | 1318.4 | 1318.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-10 08:00 | 2014-07-02 17:00 |  | 2014-05-07 08:00 | 2014-05-29 17:00 | 2014-05-07 08:00 | 2014-05-29 17:00 | 2014-05-07 08:00 | 2014-05-29 17:00 | 2014-06-10 08:00 | 2014-07-02 17:00 |  | PT_Normal |  |  |  |  | hXI6dwrlSQKoSsEAgkTnIQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32350 | N | N | 15 | FIRST FLOORS |  | 125467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1318.4 | LABOR- SUBCONTRACTOR
%R | 504500 | 6359 | 125469 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ELFF4045 | Installation of wiring & Main Cabling | 8178 | 216 | 0 | 200 | 0 | 296 | 296 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-18 08:00 | 2014-07-16 17:00 |  | 2014-05-18 08:00 | 2014-06-15 17:00 | 2014-05-18 08:00 | 2014-06-15 17:00 | 2014-05-18 08:00 | 2014-06-15 17:00 | 2014-06-18 08:00 | 2014-07-16 17:00 |  | PT_Normal |  |  |  |  | Egdfq2MzRS6gO8rdOda/TA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32350 | N | N | 15 | FIRST FLOORS |  | 125467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 296 | LABOR- SUBCONTRACTOR
%R | 504501 | 6359 | 125469 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 24 | 16 | 160 | 0 | 227.2 | 227.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-22 08:00 | 2014-08-17 17:00 |  | 2014-07-19 08:00 | 2014-08-13 17:00 | 2014-07-19 08:00 | 2014-08-13 17:00 | 2014-07-19 08:00 | 2014-08-13 17:00 | 2014-07-22 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | Td/SXTpdTOeZ+swyOxjGAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32350 | N | N | 15 | FIRST FLOORS |  | 125467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 227.2 | LABOR- SUBCONTRACTOR
%R | 504502 | 6359 | 125469 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 8 | 0 | 200 | 0 | 1651.2 | 1651.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-28 08:00 | 2014-08-28 17:00 |  | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-07-28 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | MStqPkkoT9y5Ph8eyHP2jw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32350 | N | N | 15 | FIRST FLOORS |  | 125467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 825.6 | LABOR- SUBCONTRACTOR
%R | 504503 | 6359 | 125469 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 8 | 0 | 200 | 0 | 1008 | 1008 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-07-15 08:00 | 2014-08-16 17:00 | 2014-07-15 08:00 | 2014-08-16 17:00 | 2014-07-15 08:00 | 2014-08-16 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | V2T3lgEdSEWeMlVgsUEAhA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32350 | N | N | 15 | FIRST FLOORS |  | 125467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 504 | LABOR- SUBCONTRACTOR
%R | 504504 | 6359 | 125469 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ELFF4050 | Installation of Telephone System | 8178 | 64 | 56 | 200 | 0 | 451.2 | 451.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-26 08:00 | 2014-08-26 17:00 |  | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-26 08:00 | 2014-08-26 17:00 |  | PT_Normal |  |  |  |  | bto4A2IPTgm1jXw/n6/LQw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32350 | N | N | 15 | FIRST FLOORS |  | 125467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 225.6 | LABOR- SUBCONTRACTOR
%R | 504505 | 6359 | 125470 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 216 | 0 | 200 | 0 | 1222.4 | 1222.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-13 17:00 |  | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 |  | PT_Normal |  |  |  |  | XtRgscVzSOSY0L1SNA1qIw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32340 | N | N | 10 | GROUND FLOOR |  | 125467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1222.4 | LABOR- SUBCONTRACTOR
%R | 504506 | 6359 | 125470 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ELGF4005 | Cable tray & trunking installation | 8178 | 360 | 0 | 160 | 0 | 1318.4 | 1318.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-18 08:00 | 2014-06-09 17:00 |  | 2014-03-26 08:00 | 2014-04-17 17:00 | 2014-03-26 08:00 | 2014-04-17 17:00 | 2014-03-26 08:00 | 2014-04-17 17:00 | 2014-05-18 08:00 | 2014-06-09 17:00 |  | PT_Normal |  |  |  |  | ZNn3fQ9qQdubUbkx+Cdllw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32340 | N | N | 10 | GROUND FLOOR |  | 125467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1318.4 | LABOR- SUBCONTRACTOR
%R | 504507 | 6359 | 125470 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ELGF4010 | Installation of wiring & Main Cabling | 8178 | 360 | 216 | 200 | 0 | 296 | 296 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-26 08:00 | 2014-06-23 17:00 |  | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-05-26 08:00 | 2014-06-23 17:00 |  | PT_Normal |  |  |  |  | EaCT7YpgRxGYaqIQGo3lmw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32340 | N | N | 10 | GROUND FLOOR |  | 125467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 296 | LABOR- SUBCONTRACTOR
%R | 504508 | 6359 | 125470 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 144 | 0 | 160 | 0 | 227.2 | 227.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-02 08:00 | 2014-07-24 17:00 |  | 2014-06-11 08:00 | 2014-07-03 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 | 2014-07-02 08:00 | 2014-07-24 17:00 |  | PT_Normal |  |  |  |  | g42ptd4xSGCa8t1ife+pEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32340 | N | N | 10 | GROUND FLOOR |  | 125467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 227.2 | LABOR- SUBCONTRACTOR
%R | 504509 | 6359 | 125470 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 200 | 0 | 200 | 0 | 1651.2 | 1651.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-22 08:00 | 2014-08-23 17:00 |  | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-07-22 08:00 | 2014-08-23 17:00 |  | PT_Normal |  |  |  |  | Ulr9bst4Rfiq1TyKaU6O6w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32340 | N | N | 10 | GROUND FLOOR |  | 125467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1651.2 | LABOR- SUBCONTRACTOR
%R | 504510 | 6359 | 125470 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 240 | 0 | 200 | 0 | 1075.2 | 1075.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-10 08:00 | 2014-08-11 17:00 |  | 2014-06-05 08:00 | 2014-07-03 17:00 | 2014-06-05 08:00 | 2014-07-03 17:00 | 2014-06-05 08:00 | 2014-07-03 17:00 | 2014-07-10 08:00 | 2014-08-11 17:00 |  | PT_Normal |  |  |  |  | NC17emfaQ4WoFoeK+HmghA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32340 | N | N | 10 | GROUND FLOOR |  | 125467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1075.2 | LABOR- SUBCONTRACTOR
%R | 504511 | 6359 | 125470 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ELGF4030 | Installation of Telephone System | 8178 | 144 | 40 | 160 | 0 | 520 | 520 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-14 08:00 | 2014-08-09 17:00 |  | 2014-06-23 08:00 | 2014-07-15 17:00 | 2014-06-23 08:00 | 2014-07-15 17:00 | 2014-06-23 08:00 | 2014-07-15 17:00 | 2014-07-14 08:00 | 2014-08-09 17:00 |  | PT_Normal |  |  |  |  | XAMopIC4S6eQhBPyaMV/eQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32340 | N | N | 10 | GROUND FLOOR |  | 125467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 520 | LABOR- SUBCONTRACTOR
%R | 504512 | 6359 | 125472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ACFF4615 | Installation AC Pipes | 8178 | 216 | 40 | 160 | 0 | 977.6 | 977.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-21 17:00 |  | 2014-05-28 08:00 | 2014-06-19 17:00 | 2014-05-28 08:00 | 2014-06-19 17:00 | 2014-05-28 08:00 | 2014-06-19 17:00 | 2014-06-29 08:00 | 2014-07-21 17:00 |  | PT_Normal |  |  |  |  | 781qziYbTyWbFZGRjlqOjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32430 | N | N | 15 | FIRST FLOORS |  | 125471 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 977.6 | LABOR- SUBCONTRACTOR
%R | 504513 | 6359 | 125472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ACFF4620 | Fixing of Ventilation Equipments | 8178 | 16 | 0 | 200 | 0 | 113.6 | 113.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-17 08:00 | 2014-08-18 17:00 |  | 2014-07-15 08:00 | 2014-08-16 17:00 | 2014-07-15 08:00 | 2014-08-16 17:00 | 2014-07-15 08:00 | 2014-08-16 17:00 | 2014-07-17 08:00 | 2014-08-18 17:00 |  | PT_Normal |  |  |  |  | dOGYT+juRJ6wD7UUZuJlkw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32430 | N | N | 15 | FIRST FLOORS |  | 125471 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 56.8 | LABOR- SUBCONTRACTOR
%R | 504514 | 6359 | 125472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ACFF4625 | Fixing of Split AC | 8178 | 16 | 0 | 160 | 0 | 296 | 296 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-11 08:00 | 2014-09-02 17:00 |  | 2014-08-09 08:00 | 2014-08-31 17:00 | 2014-08-09 08:00 | 2014-08-31 17:00 | 2014-08-09 08:00 | 2014-08-31 17:00 | 2014-08-11 08:00 | 2014-09-02 17:00 |  | PT_Normal |  |  |  |  | +53ZBZ8ATMePDPksYxR/Fw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32430 | N | N | 15 | FIRST FLOORS |  | 125471 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 296 | LABOR- SUBCONTRACTOR
%R | 504515 | 6359 | 125473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ACRF4630 | Installation of Refrigerant Pipes | 8178 | 272 | 0 | 200 | 0 | 409.6 | 409.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-09-09 17:00 |  | 2014-06-30 08:00 | 2014-07-28 17:00 | 2014-06-30 08:00 | 2014-07-28 17:00 | 2014-06-30 08:00 | 2014-07-28 17:00 | 2014-08-12 08:00 | 2014-09-09 17:00 |  | PT_Normal |  |  |  |  | Kds4YoyjQpWsZy/3DlTVUw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32440 | N | N | 20 | ROOF |  | 125471 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 409.6 | LABOR- SUBCONTRACTOR
%R | 504516 | 6359 | 125473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ACRF4635 | Installation of Condensing Unit | 8178 | 24 | 0 | 200 | 0 | 568 | 568 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-08-14 08:00 | 2014-09-11 17:00 | 2014-08-14 08:00 | 2014-09-11 17:00 | 2014-08-14 08:00 | 2014-09-11 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | YBIv/RCRQKWARNpixNpHgw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32440 | N | N | 20 | ROOF |  | 125471 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 568 | LABOR- SUBCONTRACTOR
%R | 504517 | 6359 | 125474 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ACGF4600 | Installation AC Pipes | 8178 | 392 | 40 | 160 | 0 | 977.6 | 977.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-10 08:00 | 2014-07-02 17:00 |  | 2014-04-14 08:00 | 2014-05-06 17:00 | 2014-04-14 08:00 | 2014-05-06 17:00 | 2014-04-14 08:00 | 2014-05-06 17:00 | 2014-06-10 08:00 | 2014-07-02 17:00 |  | PT_Normal |  |  |  |  | pTqkpC/cTiW0/apytbGC3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32420 | N | N | 10 | GROUND FLOOR |  | 125471 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 977.6 | LABOR- SUBCONTRACTOR
%R | 504518 | 6359 | 125474 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ACGF4605 | Fixing of Ventilation Equipments | 8178 | 256 | 0 | 200 | 0 | 182.4 | 182.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-13 08:00 | 2014-08-13 17:00 |  | 2014-06-05 08:00 | 2014-07-03 17:00 | 2014-06-05 08:00 | 2014-07-03 17:00 | 2014-06-05 08:00 | 2014-07-03 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 |  | PT_Normal |  |  |  |  | qwpYO5WkSymuNHYnAa4ykw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32420 | N | N | 10 | GROUND FLOOR |  | 125471 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 182.4 | LABOR- SUBCONTRACTOR
%R | 504519 | 6359 | 125474 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ7ACGF4610 | Fixing of Split AC | 8178 | 256 | 40 | 160 | 0 | 296 | 296 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-06 08:00 | 2014-08-28 17:00 |  | 2014-06-26 08:00 | 2014-07-19 17:00 | 2014-06-26 08:00 | 2014-07-19 17:00 | 2014-06-26 08:00 | 2014-07-19 17:00 | 2014-08-06 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | lB/Zf+0LRWuE1L2PZFGE7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 32420 | N | N | 10 | GROUND FLOOR |  | 125471 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 296 | LABOR- SUBCONTRACTOR
%R | 504520 | 6359 | 125477 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKMSEX5020 | Construction Entrance Ramp | 8164 | 128 | 0 | 56 | 0 | 86 | 86 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-28 08:00 | 2014-01-04 17:00 |  | 2013-12-08 08:00 | 2013-12-15 17:00 | 2013-12-08 08:00 | 2013-12-15 17:00 | 2013-12-08 08:00 | 2013-12-15 17:00 | 2013-12-28 08:00 | 2014-01-04 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29940 | N | N | 10 | MISCELLANEOUS |  | 125476 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 86 | SCREED MASON SK
%R | 504521 | 6359 | 125477 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKMSEX5025 | SS.Handrails and Balustrades | 8178 | 144 | 0 | 40 | 0 | 14 | 14 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-07 08:00 | 2014-01-12 17:00 |  | 2013-12-16 08:00 | 2013-12-22 17:00 | 2013-12-16 08:00 | 2013-12-22 17:00 | 2013-12-16 08:00 | 2013-12-22 17:00 | 2014-01-07 08:00 | 2014-01-12 17:00 |  | PT_Normal |  |  |  |  | P7L2hbqkQp6EGdVVhQGL2A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29940 | N | N | 10 | MISCELLANEOUS |  | 125476 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 14 | LABOR- SUBCONTRACTOR
%R | 504522 | 6359 | 125477 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKMSEX5015 | Construction of grease Trap | 8178 | 72 | 0 | 56 | 0 | 14 | 14 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-22 08:00 | 2013-12-29 17:00 |  | 2013-12-10 08:00 | 2013-12-17 17:00 | 2013-12-10 08:00 | 2013-12-17 17:00 | 2013-12-10 08:00 | 2013-12-17 17:00 | 2013-12-22 08:00 | 2013-12-29 17:00 |  | PT_Normal |  |  |  |  | onJbIQKtS5yYC68UD5xciA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29940 | N | N | 10 | MISCELLANEOUS |  | 125476 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 14 | LABOR- SUBCONTRACTOR
%R | 504523 | 6359 | 125477 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKMSEX5000 | Construction of Manholes | 8172 | 72 | 0 | 56 | 0 | 66 | 66 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-04 08:00 | 2013-12-11 17:00 |  | 2013-11-24 08:00 | 2013-12-01 17:00 | 2013-11-24 08:00 | 2013-12-01 17:00 | 2013-11-24 08:00 | 2013-12-01 17:00 | 2013-12-04 08:00 | 2013-12-11 17:00 |  | PT_Normal |  |  |  |  | 0Oos3dGIS0Gm40gUD2+9SQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29940 | N | N | 10 | MISCELLANEOUS |  | 125476 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 66 | MANHOLES SK
%R | 504524 | 6359 | 125477 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKMSEX5005 | Construction of Soak pit, Chambers | 8172 | 72 | 0 | 56 | 0 | 22 | 22 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-12 08:00 | 2013-12-21 17:00 |  | 2013-12-02 08:00 | 2013-12-09 17:00 | 2013-12-02 08:00 | 2013-12-09 17:00 | 2013-12-02 08:00 | 2013-12-09 17:00 | 2013-12-12 08:00 | 2013-12-21 17:00 |  | PT_Normal |  |  |  |  | iyIUY1TKQ/G3zXjHdOkgsQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29940 | N | N | 10 | MISCELLANEOUS |  | 125476 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 22 | MANHOLES SK
%R | 504525 | 6359 | 125478 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKWEEX5030 | Excavation | 8177 | 72 | 0 | 32 | 0 | 14 | 14 | 32 | 8 | 0 | 8 |  |  |  | 2013-12-30 08:00 | 2014-01-02 17:00 |  | 2013-12-19 08:00 | 2013-12-23 17:00 | 2013-12-19 08:00 | 2013-12-23 17:00 | 2013-12-19 08:00 | 2013-12-23 17:00 | 2013-12-30 08:00 | 2014-01-02 17:00 |  | PT_Normal |  |  |  |  | qvAWBaklSDSUUg8DTQxjTg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29950 | N | N | 15 | WATER TANK ENCLOSURE |  | 125476 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 14 | LABOR - CIVIL
%R | 504526 | 6359 | 125478 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKWEEX5035 | Construction of Raft | 8165 | 72 | 0 | 56 | 0 | 112 | 112 | 56 | 0 | 0 | 0 |  |  |  | 2014-01-04 08:00 | 2014-01-11 17:00 |  | 2013-12-24 08:00 | 2013-12-31 17:00 | 2013-12-24 08:00 | 2013-12-31 17:00 | 2013-12-24 08:00 | 2013-12-31 17:00 | 2014-01-04 08:00 | 2014-01-11 17:00 |  | PT_Normal |  |  |  |  | 9rIstxRGQvy0BClEUyaEHA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29950 | N | N | 15 | WATER TANK ENCLOSURE |  | 125476 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 112 | STEEL FIXERS SK
%R | 504527 | 6359 | 125478 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKWEEX5040 | Block works & Plastering | 8168 | 72 | 0 | 56 | 0 | 64 | 64 | 56 | 0 | 0 | 0 |  |  |  | 2014-01-12 08:00 | 2014-01-19 17:00 |  | 2014-01-01 08:00 | 2014-01-08 17:00 | 2014-01-01 08:00 | 2014-01-08 17:00 | 2014-01-01 08:00 | 2014-01-08 17:00 | 2014-01-12 08:00 | 2014-01-19 17:00 |  | PT_Normal |  |  |  |  | LsjpqSPmR2OjIco8wg9dIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29950 | N | N | 15 | WATER TANK ENCLOSURE |  | 125476 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 64 | BLOCK MASON SK
%R | 504528 | 6359 | 125478 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKWEEX5045 | Flooring & Painting | 8178 | 72 | 0 | 56 | 0 | 36 | 36 | 56 | 0 | 0 | 0 |  |  |  | 2014-01-20 08:00 | 2014-01-27 17:00 |  | 2014-01-09 08:00 | 2014-01-16 17:00 | 2014-01-09 08:00 | 2014-01-16 17:00 | 2014-01-09 08:00 | 2014-01-16 17:00 | 2014-01-20 08:00 | 2014-01-27 17:00 |  | PT_Normal |  |  |  |  | JMMGP/boSiefaVEQD8Vn+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29950 | N | N | 15 | WATER TANK ENCLOSURE |  | 125476 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 36 | LABOR- SUBCONTRACTOR
%R | 504529 | 6359 | 125478 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKWEEX5050 | Installation of Steel Gate | 8178 | 72 | 0 | 40 | 0 | 14 | 14 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-28 08:00 | 2014-02-02 17:00 |  | 2014-01-18 08:00 | 2014-01-22 17:00 | 2014-01-18 08:00 | 2014-01-22 17:00 | 2014-01-18 08:00 | 2014-01-22 17:00 | 2014-01-28 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | 9Yy158YUT36DxV77mxHKoA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29950 | N | N | 15 | WATER TANK ENCLOSURE |  | 125476 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 14 | LABOR- SUBCONTRACTOR
%R | 504530 | 6359 | 125478 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKWEEX5060 | Structural steel & SS Shed cover installation | 8178 | 72 | 0 | 56 | 0 | 42 | 42 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-03 08:00 | 2014-02-10 17:00 |  | 2014-01-23 08:00 | 2014-01-30 17:00 | 2014-01-23 08:00 | 2014-01-30 17:00 | 2014-01-23 08:00 | 2014-01-30 17:00 | 2014-02-03 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | fv3GHAunROaQNggmZ3oLPw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29950 | N | N | 15 | WATER TANK ENCLOSURE |  | 125476 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 42 | LABOR- SUBCONTRACTOR
%R | 504531 | 6359 | 125478 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKWEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 72 | 0 | 56 | 0 | 34 | 34 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-02-19 17:00 |  | 2014-02-01 08:00 | 2014-02-08 17:00 | 2014-02-01 08:00 | 2014-02-08 17:00 | 2014-02-01 08:00 | 2014-02-08 17:00 | 2014-02-12 08:00 | 2014-02-19 17:00 |  | PT_Normal |  |  |  |  | znEpHbZET2yDx0sdWwV7Gw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29950 | N | N | 15 | WATER TANK ENCLOSURE |  | 125476 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 34 | LABOR- SUBCONTRACTOR
%R | 504532 | 6359 | 125479 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKSLEX5105 | Laying of Grass/ green area | 8178 | 168 | 0 | 56 | 0 | 350 | 350 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-03 08:00 | 2014-02-10 17:00 |  | 2014-01-09 08:00 | 2014-01-16 17:00 | 2014-01-09 08:00 | 2014-01-16 17:00 | 2014-01-09 08:00 | 2014-01-16 17:00 | 2014-02-03 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | C28+US7lSpu5yGj3IAlC6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29970 | N | N | 25 | SOFT LANDSCAPING |  | 125476 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 350 | LABOR- SUBCONTRACTOR
%R | 504533 | 6359 | 125479 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKSLEX5110 | Laying of Palm tree | 8178 | 168 | 40 | 56 | 0 | 28 | 28 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-02-19 17:00 |  | 2014-01-18 08:00 | 2014-01-25 17:00 | 2014-01-18 08:00 | 2014-01-25 17:00 | 2014-01-18 08:00 | 2014-01-25 17:00 | 2014-02-12 08:00 | 2014-02-19 17:00 |  | PT_Normal |  |  |  |  | V9cSCtiCQ4Kz5D2oByX5iA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29970 | N | N | 25 | SOFT LANDSCAPING |  | 125476 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 28 | LABOR- SUBCONTRACTOR
%R | 504534 | 6359 | 125480 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKHDEX5090 | kerb works | 8173 | 144 | 0 | 40 | 0 | 50 | 50 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-01-18 17:00 |  | 2013-12-23 08:00 | 2013-12-28 17:00 | 2013-12-23 08:00 | 2013-12-28 17:00 | 2013-12-23 08:00 | 2013-12-28 17:00 | 2014-01-13 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | 8XY6nw9rR/6XLaf931ghlg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29960 | N | N | 20 | HARD LANDSCAPING |  | 125476 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 50 | KERBSTONE MASON SK
%R | 504535 | 6359 | 125480 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKHDEX5095 | Cobble Stone Works | 8170 | 168 | 0 | 40 | 0 | 28 | 28 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-01-27 17:00 |  | 2013-12-29 08:00 | 2014-01-02 17:00 | 2013-12-29 08:00 | 2014-01-02 17:00 | 2013-12-29 08:00 | 2014-01-02 17:00 | 2014-01-22 08:00 | 2014-01-27 17:00 |  | PT_Normal |  |  |  |  | f2cHt3+ZRwqm8iv8A5ofTw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29960 | N | N | 20 | HARD LANDSCAPING |  | 125476 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 28 | TILE MASON SK
%R | 504536 | 6359 | 125480 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKHDEX5100 | Interlock works | 8174 | 168 | 0 | 40 | 0 | 36 | 36 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-28 08:00 | 2014-02-02 17:00 |  | 2014-01-04 08:00 | 2014-01-08 17:00 | 2014-01-04 08:00 | 2014-01-08 17:00 | 2014-01-04 08:00 | 2014-01-08 17:00 | 2014-01-28 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | rK/fHPG9T1OAA+TZRAFjjg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29960 | N | N | 20 | HARD LANDSCAPING |  | 125476 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 36 | INTERLOCK MASON SK
%R | 504537 | 6359 | 125483 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKAREL3665 | External Plastering | 8169 | 128 | 0 | 80 | 0 | 1784.75 | 1784.75 | 80 | 0 | 0 | 0 |  |  |  | 2013-12-07 08:00 | 2013-12-17 17:00 |  | 2013-11-18 08:00 | 2013-11-28 17:00 | 2013-11-18 08:00 | 2013-11-28 17:00 | 2013-11-18 08:00 | 2013-11-28 17:00 | 2013-12-07 08:00 | 2013-12-17 17:00 |  | PT_Normal |  |  |  |  | 0mST/9CzQ9efFJBAh26spg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29790 | N | N | 15 | ELEVATION |  | 125482 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1784.75 | PLASTER MASON SK
%R | 504538 | 6359 | 125483 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKAREL3670 | External stone cladding works | 8170 | 128 | 0 | 56 | 0 | 123.75 | 123.75 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-19 08:00 | 2013-12-26 17:00 |  | 2013-11-30 08:00 | 2013-12-07 17:00 | 2013-11-30 08:00 | 2013-12-07 17:00 | 2013-11-30 08:00 | 2013-12-07 17:00 | 2013-12-19 08:00 | 2013-12-26 17:00 |  | PT_Normal |  |  |  |  | EQZaGybYSvKNgBwuINA+rQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29790 | N | N | 15 | ELEVATION |  | 125482 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 123.75 | TILE MASON SK
%R | 504539 | 6359 | 125483 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKAREL3680 | External Painting | 8178 | 480 | 88 | 56 | 0 | 476 | 476 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-02-25 17:00 |  | 2013-12-08 08:00 | 2013-12-15 17:00 | 2013-12-08 08:00 | 2013-12-15 17:00 | 2013-12-08 08:00 | 2013-12-15 17:00 | 2014-02-18 08:00 | 2014-02-25 17:00 |  | PT_Normal |  |  |  |  | xX0UoP4zS2GBVnhtM0/2PQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29790 | N | N | 15 | ELEVATION |  | 125482 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 476 | LABOR- SUBCONTRACTOR
%R | 504540 | 6359 | 125484 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 440 | 0 | 40 | 0 | 131.25 | 131.25 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-01-27 17:00 |  | 2013-11-18 08:00 | 2013-11-23 17:00 | 2013-11-18 08:00 | 2013-11-23 17:00 | 2013-11-18 08:00 | 2013-11-23 17:00 | 2014-01-22 08:00 | 2014-01-27 17:00 |  | PT_Normal |  |  |  |  | z+UBtUvySuOlCF01ai1t1w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29780 | N | N | 10 | ROOF |  | 125482 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 131.25 | LABOR- SUBCONTRACTOR
%R | 504541 | 6359 | 125484 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARRF3660 | Installation of Access Ladder | 8178 | 584 | 376 | 48 | 0 | 22 | 22 | 48 | 0 | 0 | 0 |  |  |  | 2014-02-25 08:00 | 2014-03-03 17:00 |  | 2013-11-30 08:00 | 2013-12-05 17:00 | 2013-11-30 08:00 | 2013-12-05 17:00 | 2013-11-30 08:00 | 2013-12-05 17:00 | 2014-02-25 08:00 | 2014-03-03 17:00 |  | PT_Normal |  |  |  |  | yZOU5qqVQfW8BXDc/Rlnag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29780 | N | N | 10 | ROOF |  | 125482 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 22 | LABOR- SUBCONTRACTOR
%R | 504542 | 6359 | 125484 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARRF3630 | Leveling Screed for Waterproofing | 8164 | 72 | 0 | 16 | 0 | 100 | 100 | 16 | 0 | 0 | 0 |  |  |  | 2013-11-14 08:00 | 2013-11-16 17:00 |  | 2013-11-04 08:00 | 2013-11-05 17:00 | 2013-11-04 08:00 | 2013-11-05 17:00 | 2013-11-04 08:00 | 2013-11-05 17:00 | 2013-11-14 08:00 | 2013-11-16 17:00 |  | PT_Normal |  |  |  |  | /u0iTJE3TvKkXaeJttvzZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29780 | N | N | 10 | ROOF |  | 125482 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 100 | SCREED MASON SK
%R | 504543 | 6359 | 125484 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARRF3635 | Laying of Waterproofing Membrane | 8178 | 72 | 0 | 32 | 0 | 143 | 143 | 32 | 0 | 0 | 0 |  |  |  | 2013-11-17 08:00 | 2013-11-20 17:00 |  | 2013-11-06 08:00 | 2013-11-10 17:00 | 2013-11-06 08:00 | 2013-11-10 17:00 | 2013-11-06 08:00 | 2013-11-10 17:00 | 2013-11-17 08:00 | 2013-11-20 17:00 |  | PT_Normal |  |  |  |  | x6OrzkXqT+OqE+mp7p5CZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29780 | N | N | 10 | ROOF |  | 125482 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 143 | LABOR- SUBCONTRACTOR
%R | 504544 | 6359 | 125484 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARRF3640 | Installation of Insulation & Protection | 8178 | 72 | 0 | 32 | 0 | 176 | 176 | 32 | 0 | 0 | 0 |  |  |  | 2013-11-21 08:00 | 2013-11-25 17:00 |  | 2013-11-11 08:00 | 2013-11-14 17:00 | 2013-11-11 08:00 | 2013-11-14 17:00 | 2013-11-11 08:00 | 2013-11-14 17:00 | 2013-11-21 08:00 | 2013-11-25 17:00 |  | PT_Normal |  |  |  |  | Q6Hm4SdNQ8CV53N0mnpwfg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29780 | N | N | 10 | ROOF |  | 125482 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 176 | LABOR- SUBCONTRACTOR
%R | 504545 | 6359 | 125484 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 72 | 0 | 16 | 0 | 87 | 87 | 16 | 0 | 0 | 0 |  |  |  | 2013-11-26 08:00 | 2013-11-27 17:00 |  | 2013-11-16 08:00 | 2013-11-17 17:00 | 2013-11-16 08:00 | 2013-11-17 17:00 | 2013-11-16 08:00 | 2013-11-17 17:00 | 2013-11-26 08:00 | 2013-11-27 17:00 |  | PT_Normal |  |  |  |  | oKNo3ZqyQq2M8KGAcGUO6w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29780 | N | N | 10 | ROOF |  | 125482 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 87 | TILE MASON SK
%R | 504546 | 6359 | 125484 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARRF3655 | Installation of Pumps Protection cabinets | 8178 | 440 | 0 | 40 | 0 | 77 | 77 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-28 08:00 | 2014-02-02 17:00 |  | 2013-11-24 08:00 | 2013-11-28 17:00 | 2013-11-24 08:00 | 2013-11-28 17:00 | 2013-11-24 08:00 | 2013-11-28 17:00 | 2014-01-28 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | kl3YhVJ6SNK88A4k38cOdg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29780 | N | N | 10 | ROOF |  | 125482 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 77 | LABOR- SUBCONTRACTOR
%R | 504547 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3060 | Gypsum board false ceiling | 8178 | 360 | 0 | 56 | 0 | 163.13 | 163.13 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-15 08:00 | 2013-12-23 17:00 |  | 2013-10-23 08:00 | 2013-10-30 17:00 | 2013-10-23 08:00 | 2013-10-30 17:00 | 2013-10-23 08:00 | 2013-10-30 17:00 | 2013-12-15 08:00 | 2013-12-23 17:00 |  | PT_Normal |  |  |  |  | IxSEDTZuTlqsFfhpylFvmA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 163.13 | LABOR- SUBCONTRACTOR
%R | 504548 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3065 | Wooden door & PVC Door | 8178 | 440 | 0 | 40 | 0 | 38.5 | 38.5 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-05 08:00 | 2014-01-09 17:00 |  | 2013-10-31 08:00 | 2013-11-05 17:00 | 2013-10-31 08:00 | 2013-11-05 17:00 | 2013-10-31 08:00 | 2013-11-05 17:00 | 2014-01-05 08:00 | 2014-01-09 17:00 |  | PT_Normal |  |  |  |  | /iYPhz2hSQKZeDNupCL4Rw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 38.5 | LABOR- SUBCONTRACTOR
%R | 504549 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3070 | Aluminum doors | 8178 | 440 | 0 | 40 | 0 | 22 | 22 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-11 08:00 | 2014-01-15 17:00 |  | 2013-11-06 08:00 | 2013-11-11 17:00 | 2013-11-06 08:00 | 2013-11-11 17:00 | 2013-11-06 08:00 | 2013-11-11 17:00 | 2014-01-11 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | CsmtroWfQ6WmgM2p0r7zsA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 22 | LABOR- SUBCONTRACTOR
%R | 504550 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3080 | Aluminum windows | 8178 | 568 | 96 | 40 | 0 | 19.25 | 19.25 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-04 08:00 | 2014-02-09 17:00 |  | 2013-11-12 08:00 | 2013-11-17 17:00 | 2013-11-12 08:00 | 2013-11-17 17:00 | 2013-11-12 08:00 | 2013-11-17 17:00 | 2014-02-04 08:00 | 2014-02-09 17:00 |  | PT_Normal |  |  |  |  | Wf1vibCvSqedQERDqbZKhg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 19.25 | LABOR- SUBCONTRACTOR
%R | 504551 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3075 | Carpentry & Joinery Works | 8178 | 440 | 0 | 80 | 0 | 71.5 | 71.5 | 80 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-01-27 17:00 |  | 2013-11-12 08:00 | 2013-11-23 17:00 | 2013-11-12 08:00 | 2013-11-23 17:00 | 2013-11-12 08:00 | 2013-11-23 17:00 | 2014-01-16 08:00 | 2014-01-27 17:00 |  | PT_Normal |  |  |  |  | 3bawH5vAS+m4MrRF3W4OaA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 71.5 | LABOR- SUBCONTRACTOR
%R | 504552 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3090 | Installation of Granite Counter Top | 8171 | 472 | 0 | 56 | 0 | 22 | 22 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-02 08:00 | 2014-02-09 17:00 |  | 2013-11-24 08:00 | 2013-12-01 17:00 | 2013-11-24 08:00 | 2013-12-01 17:00 | 2013-11-24 08:00 | 2013-12-01 17:00 | 2014-02-02 08:00 | 2014-02-09 17:00 |  | PT_Normal |  |  |  |  | RZAjdS+gRXS6rIkZ/V41GA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 22 | GRANITE MASON SK
%R | 504553 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3085 | S.S.Handrails & Balustrade | 8178 | 480 | 0 | 56 | 0 | 34.75 | 34.75 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-03 08:00 | 2014-02-10 17:00 |  | 2013-11-24 08:00 | 2013-12-01 17:00 | 2013-11-24 08:00 | 2013-12-01 17:00 | 2013-11-24 08:00 | 2013-12-01 17:00 | 2014-02-03 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | 77GI2ZC+QW6XJ2wO+eru2Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 34.75 | LABOR- SUBCONTRACTOR
%R | 504554 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3095 | Final Painting | 8178 | 480 | 312 | 56 | 0 | 679.25 | 679.25 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-02-19 17:00 |  | 2013-12-02 08:00 | 2013-12-09 17:00 | 2013-12-02 08:00 | 2013-12-09 17:00 | 2013-12-02 08:00 | 2013-12-09 17:00 | 2014-02-12 08:00 | 2014-02-19 17:00 |  | PT_Normal |  |  |  |  | plnl8YU0T7aCY5xEfzeumA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 679.25 | LABOR- SUBCONTRACTOR
%R | 504555 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3035 | Slate Tile Flooring & Skirting | 8170 | 368 | 184 | 40 | 0 | 95.5 | 95.5 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-14 08:00 | 2013-12-19 17:00 |  | 2013-10-21 08:00 | 2013-10-26 17:00 | 2013-10-21 08:00 | 2013-10-26 17:00 | 2013-10-21 08:00 | 2013-10-26 17:00 | 2013-12-14 08:00 | 2013-12-19 17:00 |  | PT_Normal |  |  |  |  | fkXty1mNQL26HKZkLnRtYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 95.5 | TILE MASON SK
%R | 504556 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3000 | Block work | 8168 | 144 | 0 | 48 | 0 | 1218.75 | 1218.75 | 48 | 0 | 0 | 0 |  |  |  | 2013-09-24 08:00 | 2013-09-30 17:00 |  | 2013-09-03 08:00 | 2013-09-09 17:00 | 2013-09-03 08:00 | 2013-09-09 17:00 | 2013-09-03 08:00 | 2013-09-09 17:00 | 2013-09-24 08:00 | 2013-09-30 17:00 |  | PT_Normal |  |  |  |  | 3eteeumYQEa/GvbMkT+IMQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1218.75 | BLOCK MASON SK
%R | 504557 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3005 | Plastering work | 8169 | 200 | 0 | 56 | 0 | 1706.25 | 1706.25 | 56 | 0 | 0 | 0 |  |  |  | 2013-10-15 08:00 | 2013-10-24 17:00 |  | 2013-09-16 08:00 | 2013-09-23 17:00 | 2013-09-16 08:00 | 2013-09-23 17:00 | 2013-09-16 08:00 | 2013-09-23 17:00 | 2013-10-15 08:00 | 2013-10-24 17:00 |  | PT_Normal |  |  |  |  | LbW43manQpKavcLv1KsPfw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1706.25 | PLASTER MASON SK
%R | 504558 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3010 | Flooring screed | 8164 | 272 | 0 | 56 | 0 | 198 | 198 | 56 | 0 | 0 | 0 |  |  |  | 2013-10-31 08:00 | 2013-11-07 17:00 |  | 2013-09-19 08:00 | 2013-09-26 17:00 | 2013-09-19 08:00 | 2013-09-26 17:00 | 2013-09-19 08:00 | 2013-09-26 17:00 | 2013-10-31 08:00 | 2013-11-07 17:00 |  | PT_Normal |  |  |  |  | VtsvpOHSRPyoVSuZizXOwg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 198 | SCREED MASON SK
%R | 504559 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 272 | 0 | 40 | 0 | 32 | 32 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-04 08:00 | 2013-11-09 17:00 |  | 2013-09-23 08:00 | 2013-09-28 17:00 | 2013-09-23 08:00 | 2013-09-28 17:00 | 2013-09-23 08:00 | 2013-09-28 17:00 | 2013-11-04 08:00 | 2013-11-09 17:00 |  | PT_Normal |  |  |  |  | ASjkITy4RxWP27izk37nSA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 32 | LABOR- SUBCONTRACTOR
%R | 504560 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3030 | Paint First coat | 8178 | 328 | 32 | 40 | 0 | 679.25 | 679.25 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-21 08:00 | 2013-11-26 17:00 |  | 2013-10-02 08:00 | 2013-10-07 17:00 | 2013-10-02 08:00 | 2013-10-07 17:00 | 2013-10-02 08:00 | 2013-10-07 17:00 | 2013-11-21 08:00 | 2013-11-26 17:00 |  | PT_Normal |  |  |  |  | Ll60+wGrQZef/LZltZnJRQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 679.25 | LABOR- SUBCONTRACTOR
%R | 504561 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3020 | Ceramic Wall Tiling | 8170 | 272 | 0 | 48 | 0 | 553.5 | 553.5 | 48 | 0 | 0 | 0 |  |  |  | 2013-11-10 08:00 | 2013-11-16 17:00 |  | 2013-09-29 08:00 | 2013-10-05 17:00 | 2013-09-29 08:00 | 2013-10-05 17:00 | 2013-09-29 08:00 | 2013-10-05 17:00 | 2013-11-10 08:00 | 2013-11-16 17:00 |  | PT_Normal |  |  |  |  | SEjuaZG7Tom02t+LYRWxrA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 553.5 | TILE MASON SK
%R | 504562 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3025 | Porcelain Tile flooring | 8170 | 272 | 0 | 48 | 0 | 218.75 | 218.75 | 48 | 0 | 0 | 0 |  |  |  | 2013-11-17 08:00 | 2013-11-23 17:00 |  | 2013-10-06 08:00 | 2013-10-12 17:00 | 2013-10-06 08:00 | 2013-10-12 17:00 | 2013-10-06 08:00 | 2013-10-12 17:00 | 2013-11-17 08:00 | 2013-11-23 17:00 |  | PT_Normal |  |  |  |  | IbgQzSSzS3+oJ/6UOxfNdA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 218.75 | TILE MASON SK
%R | 504563 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3040 | Cobble Tile flooring | 8170 | 368 | 0 | 40 | 0 | 93.75 | 93.75 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-08 08:00 | 2013-12-12 17:00 |  | 2013-10-13 08:00 | 2013-10-20 17:00 | 2013-10-13 08:00 | 2013-10-20 17:00 | 2013-10-13 08:00 | 2013-10-20 17:00 | 2013-12-08 08:00 | 2013-12-12 17:00 |  | PT_Normal |  |  |  |  | 8S94KK9uRHuyGV5bGKjSLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 93.75 | TILE MASON SK
%R | 504564 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 440 | 16 | 56 | 0 | 106.25 | 106.25 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-25 08:00 | 2014-01-01 17:00 |  | 2013-10-21 08:00 | 2013-10-28 17:00 | 2013-10-21 08:00 | 2013-10-28 17:00 | 2013-10-21 08:00 | 2013-10-28 17:00 | 2013-12-25 08:00 | 2014-01-01 17:00 |  | PT_Normal |  |  |  |  | Yo8rlcObTHOIPw8hb+zX2Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 106.25 | GRANITE MASON SK
%R | 504565 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3045 | Fixing of Suspension systems | 8178 | 336 | 0 | 56 | 0 | 181.88 | 181.88 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-03 08:00 | 2013-12-10 17:00 |  | 2013-10-13 08:00 | 2013-10-22 17:00 | 2013-10-13 08:00 | 2013-10-22 17:00 | 2013-10-13 08:00 | 2013-10-22 17:00 | 2013-12-03 08:00 | 2013-12-10 17:00 |  | PT_Normal |  |  |  |  | N99pMvdJQDaVsDa7gmNPkQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 181.88 | LABOR- SUBCONTRACTOR
%R | 504566 | 6359 | 125486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARGF3055 | Aluminum tile false ceiling | 8178 | 360 | 0 | 56 | 0 | 18.75 | 18.75 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-15 08:00 | 2013-12-23 17:00 |  | 2013-10-23 08:00 | 2013-10-30 17:00 | 2013-10-23 08:00 | 2013-10-30 17:00 | 2013-10-23 08:00 | 2013-10-30 17:00 | 2013-12-15 08:00 | 2013-12-23 17:00 |  | PT_Normal |  |  |  |  | deWWwT4GSZq5Eq5F6adhCA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29740 | N | N | 10 | GROUND FLOOR |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 18.75 | LABOR- SUBCONTRACTOR
%R | 504567 | 6359 | 125487 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARRF3600 | Block work | 8168 | 288 | 0 | 48 | 0 | 87.5 | 87.5 | 48 | 0 | 0 | 0 |  |  |  | 2013-11-04 08:00 | 2013-11-10 17:00 |  | 2013-09-21 08:00 | 2013-09-26 17:00 | 2013-09-21 08:00 | 2013-09-26 17:00 | 2013-09-21 08:00 | 2013-09-26 17:00 | 2013-11-04 08:00 | 2013-11-10 17:00 |  | PT_Normal |  |  |  |  | dpNK4EX7TtSNJyhMS6o5gg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29760 | N | N | 20 | ROOF |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 87.5 | BLOCK MASON SK
%R | 504568 | 6359 | 125487 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARRF3605 | Plastering work | 8169 | 288 | 0 | 48 | 0 | 224 | 224 | 48 | 0 | 0 | 0 |  |  |  | 2013-11-07 08:00 | 2013-11-13 17:00 |  | 2013-09-24 08:00 | 2013-09-30 17:00 | 2013-09-24 08:00 | 2013-09-30 17:00 | 2013-09-24 08:00 | 2013-09-30 17:00 | 2013-11-07 08:00 | 2013-11-13 17:00 |  | PT_Normal |  |  |  |  | 41ex1LQmSEKn+paiFWfe7Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29760 | N | N | 20 | ROOF |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 224 | PLASTER MASON SK
%R | 504569 | 6359 | 125487 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARRF3610 | Flooring screed | 8164 | 736 | 376 | 48 | 0 | 16.5 | 16.5 | 48 | 0 | 0 | 0 |  |  |  | 2014-01-20 08:00 | 2014-01-26 17:00 |  | 2013-10-01 08:00 | 2013-10-07 17:00 | 2013-10-01 08:00 | 2013-10-07 17:00 | 2013-10-01 08:00 | 2013-10-07 17:00 | 2014-01-20 08:00 | 2014-01-26 17:00 |  | PT_Normal |  |  |  |  | C2/bY3e5St6uSOM/07osjw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29760 | N | N | 20 | ROOF |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 16.5 | SCREED MASON SK
%R | 504570 | 6359 | 125487 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARRF3695 | Painting -Storage area | 8178 | 728 | 0 | 48 | 0 | 212 | 212 | 48 | 0 | 0 | 0 |  |  |  | 2014-01-27 08:00 | 2014-02-02 17:00 |  | 2013-10-09 08:00 | 2013-10-15 17:00 | 2013-10-09 08:00 | 2013-10-15 17:00 | 2013-10-09 08:00 | 2013-10-15 17:00 | 2014-01-27 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | ak6JFbseTP+LZoMZY44Knw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29760 | N | N | 20 | ROOF |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 212 | LABOR- SUBCONTRACTOR
%R | 504571 | 6359 | 125487 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARRF3620 | Epoxy Painting -Storage area | 8178 | 728 | 240 | 48 | 0 | 7.25 | 7.25 | 48 | 0 | 0 | 0 |  |  |  | 2014-02-03 08:00 | 2014-02-09 17:00 |  | 2013-10-16 08:00 | 2013-10-24 17:00 | 2013-10-16 08:00 | 2013-10-24 17:00 | 2013-10-16 08:00 | 2013-10-24 17:00 | 2014-02-03 08:00 | 2014-02-09 17:00 |  | PT_Normal |  |  |  |  | WgW5GjMfS/uJ/OSf6RLzFQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29760 | N | N | 20 | ROOF |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 7.25 | LABOR- SUBCONTRACTOR
%R | 504572 | 6359 | 125488 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARFF3320 | Ceramic Wall Tiling | 8170 | 168 | 0 | 48 | 0 | 475 | 475 | 48 | 0 | 0 | 0 |  |  |  | 2013-12-07 08:00 | 2013-12-12 17:00 |  | 2013-11-12 08:00 | 2013-11-18 17:00 | 2013-11-12 08:00 | 2013-11-18 17:00 | 2013-11-12 08:00 | 2013-11-18 17:00 | 2013-12-07 08:00 | 2013-12-12 17:00 |  | PT_Normal |  |  |  |  | D0BSnignTBKJX+86EcueGA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29750 | N | N | 15 | FIRST FLOORS |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 475 | TILE MASON SK
%R | 504573 | 6359 | 125488 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARFF3325 | Porcelain Tile flooring | 8170 | 168 | 0 | 48 | 0 | 218.75 | 218.75 | 48 | 0 | 0 | 0 |  |  |  | 2013-12-14 08:00 | 2013-12-21 17:00 |  | 2013-11-19 08:00 | 2013-11-25 17:00 | 2013-11-19 08:00 | 2013-11-25 17:00 | 2013-11-19 08:00 | 2013-11-25 17:00 | 2013-12-14 08:00 | 2013-12-21 17:00 |  | PT_Normal |  |  |  |  | YVyd3h0LR+yF60bAMVN8aA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29750 | N | N | 15 | FIRST FLOORS |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 218.75 | TILE MASON SK
%R | 504574 | 6359 | 125488 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARFF3335 | Slate Tile Flooring & Skirting | 8170 | 312 | 248 | 40 | 0 | 33 | 33 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-12 08:00 | 2014-01-16 17:00 |  | 2013-11-26 08:00 | 2013-12-01 17:00 | 2013-11-26 08:00 | 2013-12-01 17:00 | 2013-11-26 08:00 | 2013-12-01 17:00 | 2014-01-12 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | 4a0yvu63QG2bV6AEJSomhg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29750 | N | N | 15 | FIRST FLOORS |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 33 | TILE MASON SK
%R | 504575 | 6359 | 125488 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARFF3350 | Granite - Stair case flooring & Skirting | 8171 | 232 | 56 | 56 | 0 | 112.5 | 112.5 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-31 08:00 | 2014-01-07 17:00 |  | 2013-11-26 08:00 | 2013-12-03 17:00 | 2013-11-26 08:00 | 2013-12-03 17:00 | 2013-11-26 08:00 | 2013-12-03 17:00 | 2013-12-31 08:00 | 2014-01-07 17:00 |  | PT_Normal |  |  |  |  | wF7+AvMAQ1udz8xEPi9/ug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29750 | N | N | 15 | FIRST FLOORS |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 112.5 | GRANITE MASON SK
%R | 504576 | 6359 | 125488 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARFF3345 | Fixing of Suspension systems | 8178 | 176 | 0 | 56 | 0 | 163.13 | 163.13 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-23 08:00 | 2013-12-30 17:00 |  | 2013-11-26 08:00 | 2013-12-03 17:00 | 2013-11-26 08:00 | 2013-12-03 17:00 | 2013-11-26 08:00 | 2013-12-03 17:00 | 2013-12-23 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | xw7IfXVLQLGbCjv9PugEMg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29750 | N | N | 15 | FIRST FLOORS |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 163.13 | LABOR- SUBCONTRACTOR
%R | 504577 | 6359 | 125488 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARFF3360 | Gypsum board false ceiling | 8178 | 176 | 0 | 56 | 0 | 163.13 | 163.13 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-31 08:00 | 2014-01-07 17:00 |  | 2013-12-04 08:00 | 2013-12-11 17:00 | 2013-12-04 08:00 | 2013-12-11 17:00 | 2013-12-04 08:00 | 2013-12-11 17:00 | 2013-12-31 08:00 | 2014-01-07 17:00 |  | PT_Normal |  |  |  |  | S/vzVKbiQnaHdy0ULtl0BA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29750 | N | N | 15 | FIRST FLOORS |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 163.13 | LABOR- SUBCONTRACTOR
%R | 504578 | 6359 | 125488 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARFF3365 | Wooden door | 8178 | 176 | 0 | 40 | 0 | 38.5 | 38.5 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-08 08:00 | 2014-01-13 17:00 |  | 2013-12-12 08:00 | 2013-12-17 17:00 | 2013-12-12 08:00 | 2013-12-17 17:00 | 2013-12-12 08:00 | 2013-12-17 17:00 | 2014-01-08 08:00 | 2014-01-13 17:00 |  | PT_Normal |  |  |  |  | 017tmGqISGKylyzhK63fFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29750 | N | N | 15 | FIRST FLOORS |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 38.5 | LABOR- SUBCONTRACTOR
%R | 504579 | 6359 | 125488 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARFF3370 | Aluminum doors | 8178 | 176 | 0 | 40 | 0 | 27.5 | 27.5 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-01-19 17:00 |  | 2013-12-19 08:00 | 2013-12-24 17:00 | 2013-12-19 08:00 | 2013-12-24 17:00 | 2013-12-19 08:00 | 2013-12-24 17:00 | 2014-01-14 08:00 | 2014-01-19 17:00 |  | PT_Normal |  |  |  |  | KXkQICW2TxyVY+PKwwMu3g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29750 | N | N | 15 | FIRST FLOORS |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 27.5 | LABOR- SUBCONTRACTOR
%R | 504580 | 6359 | 125488 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARFF3380 | Aluminum windows | 8178 | 264 | 96 | 40 | 0 | 22 | 22 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-02 08:00 | 2014-02-06 17:00 |  | 2013-12-25 08:00 | 2013-12-30 17:00 | 2013-12-25 08:00 | 2013-12-30 17:00 | 2013-12-25 08:00 | 2013-12-30 17:00 | 2014-02-02 08:00 | 2014-02-06 17:00 |  | PT_Normal |  |  |  |  | SmqgrDj0TyeYJ+C2vpUzaw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29750 | N | N | 15 | FIRST FLOORS |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 22 | LABOR- SUBCONTRACTOR
%R | 504581 | 6359 | 125488 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARFF3375 | Carpentry & Joinery Works | 8178 | 176 | 0 | 80 | 0 | 137.5 | 137.5 | 80 | 0 | 0 | 0 |  |  |  | 2014-01-20 08:00 | 2014-01-30 17:00 |  | 2013-12-25 08:00 | 2014-01-05 17:00 | 2013-12-25 08:00 | 2014-01-05 17:00 | 2013-12-25 08:00 | 2014-01-05 17:00 | 2014-01-20 08:00 | 2014-01-30 17:00 |  | PT_Normal |  |  |  |  | AZhErGRKSSWwaAZ+0UeJow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29750 | N | N | 15 | FIRST FLOORS |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 137.5 | LABOR- SUBCONTRACTOR
%R | 504582 | 6359 | 125488 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARFF3390 | Installation of Granite Counter Top | 8171 | 192 | 0 | 56 | 0 | 11 | 11 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-03 08:00 | 2014-02-10 17:00 |  | 2014-01-06 08:00 | 2014-01-13 17:00 | 2014-01-06 08:00 | 2014-01-13 17:00 | 2014-01-06 08:00 | 2014-01-13 17:00 | 2014-02-03 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | ORi5pS/ySpi3m9VbUgIlZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29750 | N | N | 15 | FIRST FLOORS |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 11 | GRANITE MASON SK
%R | 504583 | 6359 | 125488 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARFF3385 | S.S.Handrails & Balustrade | 8178 | 192 | 0 | 56 | 0 | 100 | 100 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-03 08:00 | 2014-02-10 17:00 |  | 2014-01-06 08:00 | 2014-01-13 17:00 | 2014-01-06 08:00 | 2014-01-13 17:00 | 2014-01-06 08:00 | 2014-01-13 17:00 | 2014-02-03 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | TTHOhYtEReaVNUJyL6EsHA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29750 | N | N | 15 | FIRST FLOORS |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 100 | LABOR- SUBCONTRACTOR
%R | 504584 | 6359 | 125488 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARFF3395 | Final Painting | 8178 | 192 | 192 | 56 | 0 | 594 | 594 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-02-19 17:00 |  | 2014-01-14 08:00 | 2014-01-21 17:00 | 2014-01-14 08:00 | 2014-01-21 17:00 | 2014-01-14 08:00 | 2014-01-21 17:00 | 2014-02-12 08:00 | 2014-02-19 17:00 |  | PT_Normal |  |  |  |  | h60Ukw5iRzumCglVrOL9rw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29750 | N | N | 15 | FIRST FLOORS |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 594 | LABOR- SUBCONTRACTOR
%R | 504585 | 6359 | 125488 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARFF3300 | Block work | 8168 | 0 | 0 | 48 | 0 | 800 | 800 | 48 | 0 | 0 | 0 |  |  |  | 2013-10-15 08:00 | 2013-10-23 17:00 |  | 2013-10-15 08:00 | 2013-10-23 17:00 | 2013-10-15 08:00 | 2013-10-23 17:00 | 2013-10-15 08:00 | 2013-10-23 17:00 | 2013-10-15 08:00 | 2013-10-23 17:00 |  | PT_Normal |  |  |  |  | iT3zmVC8TCOQDRJxthVVMw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29750 | N | N | 15 | FIRST FLOORS |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 800 | BLOCK MASON SK
%R | 504586 | 6359 | 125488 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARFF3305 | Plastering work | 8169 | 64 | 0 | 56 | 0 | 1112.5 | 1112.5 | 56 | 0 | 0 | 0 |  |  |  | 2013-11-09 08:00 | 2013-11-16 17:00 |  | 2013-10-30 08:00 | 2013-11-06 17:00 | 2013-10-30 08:00 | 2013-11-06 17:00 | 2013-10-30 08:00 | 2013-11-06 17:00 | 2013-11-09 08:00 | 2013-11-16 17:00 |  | PT_Normal |  |  |  |  | zTa3PF+wT1iMQExiIA7bOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29750 | N | N | 15 | FIRST FLOORS |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1112.5 | PLASTER MASON SK
%R | 504587 | 6359 | 125488 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARFF3310 | Flooring screed | 8164 | 168 | 0 | 56 | 0 | 153 | 153 | 56 | 0 | 0 | 0 |  |  |  | 2013-11-27 08:00 | 2013-12-04 17:00 |  | 2013-11-03 08:00 | 2013-11-10 17:00 | 2013-11-03 08:00 | 2013-11-10 17:00 | 2013-11-03 08:00 | 2013-11-10 17:00 | 2013-11-27 08:00 | 2013-12-04 17:00 |  | PT_Normal |  |  |  |  | uIwyD5XYS6yu7XRTFN9sHA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29750 | N | N | 15 | FIRST FLOORS |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 153 | SCREED MASON SK
%R | 504588 | 6359 | 125488 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARFF3315 | Wet area waterproofing & Protection Screed | 8178 | 168 | 0 | 40 | 0 | 153 | 153 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-01 08:00 | 2013-12-05 17:00 |  | 2013-11-06 08:00 | 2013-11-11 17:00 | 2013-11-06 08:00 | 2013-11-11 17:00 | 2013-11-06 08:00 | 2013-11-11 17:00 | 2013-12-01 08:00 | 2013-12-05 17:00 |  | PT_Normal |  |  |  |  | Ru+MmWyQTA+DbdZwgrdv5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29750 | N | N | 15 | FIRST FLOORS |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 153 | LABOR- SUBCONTRACTOR
%R | 504589 | 6359 | 125488 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKARFF3330 | Paint First coat | 8178 | 192 | 32 | 40 | 0 | 594 | 594 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-14 08:00 | 2013-12-19 17:00 |  | 2013-11-16 08:00 | 2013-11-20 17:00 | 2013-11-16 08:00 | 2013-11-20 17:00 | 2013-11-16 08:00 | 2013-11-20 17:00 | 2013-12-14 08:00 | 2013-12-19 17:00 |  | PT_Normal |  |  |  |  | xgX7nUGGRHaaaOjXOx2JEw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29750 | N | N | 15 | FIRST FLOORS |  | 125485 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 594 | LABOR- SUBCONTRACTOR
%R | 504590 | 6359 | 125491 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKPLGF4320 | Installation of Water Heater | 8178 | 632 | 272 | 40 | 0 | 16.8 | 16.8 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-26 08:00 | 2014-03-03 17:00 |  | 2013-11-24 08:00 | 2013-11-28 17:00 | 2013-11-24 08:00 | 2013-11-28 17:00 | 2013-11-24 08:00 | 2013-11-28 17:00 | 2014-02-26 08:00 | 2014-03-03 17:00 |  | PT_Normal |  |  |  |  | Ey2MwlAaQj64duiAVpMsRw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29860 | N | N | 10 | GROUND FLOOR |  | 125490 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 16.8 | LABOR- SUBCONTRACTOR
%R | 504591 | 6359 | 125491 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKPLGF4305 | Installation of Plumbing pipes & testing | 8178 | 216 | 0 | 40 | 0 | 55.2 | 55.2 | 40 | 0 | 0 | 0 |  |  |  | 2013-10-12 08:00 | 2013-10-16 17:00 |  | 2013-09-10 08:00 | 2013-09-15 17:00 | 2013-09-10 08:00 | 2013-09-15 17:00 | 2013-09-10 08:00 | 2013-09-15 17:00 | 2013-10-12 08:00 | 2013-10-16 17:00 |  | PT_Normal |  |  |  |  | FGvkiDBwTJyK22+6vApSsw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29860 | N | N | 10 | GROUND FLOOR |  | 125490 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 55.2 | LABOR- SUBCONTRACTOR
%R | 504592 | 6359 | 125491 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKPLGF4310 | Installation of Drainage pipes &testing | 8178 | 360 | 72 | 40 | 0 | 27.6 | 27.6 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-04 08:00 | 2013-11-09 17:00 |  | 2013-09-10 08:00 | 2013-09-15 17:00 | 2013-09-10 08:00 | 2013-09-15 17:00 | 2013-09-10 08:00 | 2013-09-15 17:00 | 2013-11-04 08:00 | 2013-11-09 17:00 |  | PT_Normal |  |  |  |  | iZaD52GaQRWUyjWPOvwmOw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29860 | N | N | 10 | GROUND FLOOR |  | 125490 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 27.6 | LABOR- SUBCONTRACTOR
%R | 504593 | 6359 | 125491 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKPLGF4315 | Sanitary Fittings & Accessories | 8178 | 384 | 0 | 56 | 0 | 16.8 | 16.8 | 56 | 0 | 0 | 0 |  |  |  | 2014-01-12 08:00 | 2014-01-19 17:00 |  | 2013-11-16 08:00 | 2013-11-23 17:00 | 2013-11-16 08:00 | 2013-11-23 17:00 | 2013-11-16 08:00 | 2013-11-23 17:00 | 2014-01-12 08:00 | 2014-01-19 17:00 |  | PT_Normal |  |  |  |  | A0iOdkCESHGLazdDpgA5Uw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29860 | N | N | 10 | GROUND FLOOR |  | 125490 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 16.8 | LABOR- SUBCONTRACTOR
%R | 504594 | 6359 | 125492 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKPLFF4325 | Installation of Plumbing pipes & testing | 8178 | 72 | 0 | 40 | 0 | 55.2 | 55.2 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-04 08:00 | 2013-11-09 17:00 |  | 2013-10-24 08:00 | 2013-10-29 17:00 | 2013-10-24 08:00 | 2013-10-29 17:00 | 2013-10-24 08:00 | 2013-10-29 17:00 | 2013-11-04 08:00 | 2013-11-09 17:00 |  | PT_Normal |  |  |  |  | 3+UTr9WLSxGVk86V6bdpLg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29870 | N | N | 15 | FIRST FLOORS |  | 125490 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 55.2 | LABOR- SUBCONTRACTOR
%R | 504595 | 6359 | 125492 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKPLFF4330 | Installation of Drainage pipes & testing | 8178 | 240 | 72 | 40 | 0 | 27.6 | 27.6 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-28 08:00 | 2013-12-03 17:00 |  | 2013-10-24 08:00 | 2013-10-29 17:00 | 2013-10-24 08:00 | 2013-10-29 17:00 | 2013-10-24 08:00 | 2013-10-29 17:00 | 2013-11-28 08:00 | 2013-12-03 17:00 |  | PT_Normal |  |  |  |  | WZUfpjWITf27JtoVtjY5yg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29870 | N | N | 15 | FIRST FLOORS |  | 125490 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 27.6 | LABOR- SUBCONTRACTOR
%R | 504596 | 6359 | 125492 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKPLFF4335 | Sanitary Fittings & Accessories | 8178 | 216 | 0 | 56 | 0 | 16.8 | 16.8 | 56 | 0 | 0 | 0 |  |  |  | 2014-01-20 08:00 | 2014-01-27 17:00 |  | 2013-12-19 08:00 | 2013-12-26 17:00 | 2013-12-19 08:00 | 2013-12-26 17:00 | 2013-12-19 08:00 | 2013-12-26 17:00 | 2014-01-20 08:00 | 2014-01-27 17:00 |  | PT_Normal |  |  |  |  | AGiC3EtlTKeJhzIUTZiUsw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29870 | N | N | 15 | FIRST FLOORS |  | 125490 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 16.8 | LABOR- SUBCONTRACTOR
%R | 504597 | 6359 | 125492 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKPLFF4340 | Installation of Water Heater | 8178 | 216 | 0 | 40 | 0 | 16.8 | 16.8 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-28 08:00 | 2014-02-02 17:00 |  | 2013-12-28 08:00 | 2014-01-01 17:00 | 2013-12-28 08:00 | 2014-01-01 17:00 | 2013-12-28 08:00 | 2014-01-01 17:00 | 2014-01-28 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | Ras0eh5KQUaWnzfn/5pFNA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29870 | N | N | 15 | FIRST FLOORS |  | 125490 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 16.8 | LABOR- SUBCONTRACTOR
%R | 504598 | 6359 | 125493 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKPLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 72 | 0 | 40 | 0 | 16.8 | 16.8 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-28 08:00 | 2013-12-03 17:00 |  | 2013-11-18 08:00 | 2013-11-23 17:00 | 2013-11-18 08:00 | 2013-11-23 17:00 | 2013-11-18 08:00 | 2013-11-23 17:00 | 2013-11-28 08:00 | 2013-12-03 17:00 |  | PT_Normal |  |  |  |  | UGF5yl8aTeqTf3XbHFVVIQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29880 | N | N | 20 | ROOF |  | 125490 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 16.8 | LABOR- SUBCONTRACTOR
%R | 504599 | 6359 | 125493 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKPLRF4350 | Installation of Rain water Pipes | 8178 | 440 | 224 | 40 | 0 | 16.8 | 16.8 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-28 08:00 | 2014-02-02 17:00 |  | 2013-11-24 08:00 | 2013-11-28 17:00 | 2013-11-24 08:00 | 2013-11-28 17:00 | 2013-11-24 08:00 | 2013-11-28 17:00 | 2014-01-28 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | P8rAVSpyTPSHZt/710ze1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29880 | N | N | 20 | ROOF |  | 125490 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 16.8 | LABOR- SUBCONTRACTOR
%R | 504600 | 6359 | 125493 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKPLRF4355 | Roof Water Tank Installation & Connections | 8178 | 216 | 144 | 56 | 0 | 50.4 | 50.4 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-03 08:00 | 2014-02-10 17:00 |  | 2014-01-02 08:00 | 2014-01-09 17:00 | 2014-01-02 08:00 | 2014-01-09 17:00 | 2014-01-02 08:00 | 2014-01-09 17:00 | 2014-02-03 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | zXBwaMRyREWx+GU8JgEC1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29880 | N | N | 20 | ROOF |  | 125490 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 504601 | 6359 | 125495 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKACFF4615 | Installation AC Pipes | 8178 | 320 | 32 | 40 | 0 | 130.8 | 130.8 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-25 08:00 | 2013-12-30 17:00 |  | 2013-11-07 08:00 | 2013-11-12 17:00 | 2013-11-07 08:00 | 2013-11-12 17:00 | 2013-11-07 08:00 | 2013-11-12 17:00 | 2013-12-25 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | xM47RUv9T2abr81lgz5fzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29910 | N | N | 15 | FIRST FLOORS |  | 125494 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 130.8 | LABOR- SUBCONTRACTOR
%R | 504602 | 6359 | 125495 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKACFF4620 | Fixing of Ventilation Equipments | 8178 | 232 | 0 | 40 | 0 | 17.2 | 17.2 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-01-21 17:00 |  | 2013-12-12 08:00 | 2013-12-17 17:00 | 2013-12-12 08:00 | 2013-12-17 17:00 | 2013-12-12 08:00 | 2013-12-17 17:00 | 2014-01-16 08:00 | 2014-01-21 17:00 |  | PT_Normal |  |  |  |  | i7YS5gAdT4u8sJvgKif6tQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29910 | N | N | 15 | FIRST FLOORS |  | 125494 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 17.2 | LABOR- SUBCONTRACTOR
%R | 504603 | 6359 | 125495 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKACFF4625 | Fixing of Split AC | 8178 | 336 | 0 | 40 | 0 | 45.6 | 45.6 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-02-12 17:00 |  | 2013-12-19 08:00 | 2013-12-24 17:00 | 2013-12-19 08:00 | 2013-12-24 17:00 | 2013-12-19 08:00 | 2013-12-24 17:00 | 2014-02-06 08:00 | 2014-02-12 17:00 |  | PT_Normal |  |  |  |  | NnKcEfjIQd+9mb7NrFCahA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29910 | N | N | 15 | FIRST FLOORS |  | 125494 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 45.6 | LABOR- SUBCONTRACTOR
%R | 504604 | 6359 | 125496 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKACGF4600 | Installation AC Pipes | 8178 | 504 | 112 | 40 | 0 | 130.8 | 130.8 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-09 08:00 | 2013-12-14 17:00 |  | 2013-09-24 08:00 | 2013-09-29 17:00 | 2013-09-24 08:00 | 2013-09-29 17:00 | 2013-09-24 08:00 | 2013-09-29 17:00 | 2013-12-09 08:00 | 2013-12-14 17:00 |  | PT_Normal |  |  |  |  | /dBKSjvXSrafA4oJSF8yjw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29900 | N | N | 10 | GROUND FLOOR |  | 125494 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 130.8 | LABOR- SUBCONTRACTOR
%R | 504605 | 6359 | 125496 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKACGF4605 | Fixing of Ventilation Equipments | 8178 | 480 | 0 | 40 | 0 | 28.4 | 28.4 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-11 08:00 | 2014-01-15 17:00 |  | 2013-10-31 08:00 | 2013-11-05 17:00 | 2013-10-31 08:00 | 2013-11-05 17:00 | 2013-10-31 08:00 | 2013-11-05 17:00 | 2014-01-11 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | I+K9nMX8T125i++ObdeQdw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29900 | N | N | 10 | GROUND FLOOR |  | 125494 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 28.4 | LABOR- SUBCONTRACTOR
%R | 504606 | 6359 | 125496 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKACGF4610 | Fixing of Split AC | 8178 | 584 | 248 | 40 | 0 | 45.6 | 45.6 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-01 08:00 | 2014-02-05 17:00 |  | 2013-11-06 08:00 | 2013-11-11 17:00 | 2013-11-06 08:00 | 2013-11-11 17:00 | 2013-11-06 08:00 | 2013-11-11 17:00 | 2014-02-01 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | tbSEcRz4SyOdg7yer8CjFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29900 | N | N | 10 | GROUND FLOOR |  | 125494 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 45.6 | LABOR- SUBCONTRACTOR
%R | 504607 | 6359 | 125497 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKACRF4630 | Installation of Refrigerant Pipes | 8178 | 552 | 208 | 40 | 0 | 56.8 | 56.8 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-08 08:00 | 2014-02-13 17:00 |  | 2013-11-18 08:00 | 2013-11-23 17:00 | 2013-11-18 08:00 | 2013-11-23 17:00 | 2013-11-18 08:00 | 2013-11-23 17:00 | 2014-02-08 08:00 | 2014-02-13 17:00 |  | PT_Normal |  |  |  |  | eY6M7iheS6CcuoyGu9I6dQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29920 | N | N | 20 | ROOF |  | 125494 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 56.8 | LABOR- SUBCONTRACTOR
%R | 504608 | 6359 | 125497 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKACRF4635 | Installation of Condensing Unit | 8178 | 344 | 312 | 40 | 0 | 74 | 74 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-15 08:00 | 2014-02-19 17:00 |  | 2013-12-25 08:00 | 2013-12-30 17:00 | 2013-12-25 08:00 | 2013-12-30 17:00 | 2013-12-25 08:00 | 2013-12-30 17:00 | 2014-02-15 08:00 | 2014-02-19 17:00 |  | PT_Normal |  |  |  |  | FAYywaBvS9mRcQOPVDsdcg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29920 | N | N | 20 | ROOF |  | 125494 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 74 | LABOR- SUBCONTRACTOR
%R | 504609 | 6359 | 125499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 64 | 0 | 40 | 0 | 158.4 | 158.4 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-03 08:00 | 2013-11-07 17:00 |  | 2013-10-24 08:00 | 2013-10-29 17:00 | 2013-10-24 08:00 | 2013-10-29 17:00 | 2013-10-24 08:00 | 2013-10-29 17:00 | 2013-11-03 08:00 | 2013-11-07 17:00 |  | PT_Normal |  |  |  |  | wv14AyW5TjiuD+fjgjlRxQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29830 | N | N | 15 | FIRST FLOORS |  | 125498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 158.4 | LABOR- SUBCONTRACTOR
%R | 504610 | 6359 | 125499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKELFF4040 | Cable tray & trunking installation | 8178 | 208 | 0 | 40 | 0 | 170.4 | 170.4 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-08 08:00 | 2013-12-12 17:00 |  | 2013-11-07 08:00 | 2013-11-12 17:00 | 2013-11-07 08:00 | 2013-11-12 17:00 | 2013-11-07 08:00 | 2013-11-12 17:00 | 2013-12-08 08:00 | 2013-12-12 17:00 |  | PT_Normal |  |  |  |  | weCLgi1pQGikFaYDp6/gAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29830 | N | N | 15 | FIRST FLOORS |  | 125498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 170.4 | LABOR- SUBCONTRACTOR
%R | 504611 | 6359 | 125499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKELFF4045 | Installation of wiring & Main Cabling | 8178 | 224 | 16 | 40 | 0 | 45.6 | 45.6 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-16 08:00 | 2013-12-22 17:00 |  | 2013-11-13 08:00 | 2013-11-18 17:00 | 2013-11-13 08:00 | 2013-11-18 17:00 | 2013-11-13 08:00 | 2013-11-18 17:00 | 2013-12-16 08:00 | 2013-12-22 17:00 |  | PT_Normal |  |  |  |  | DXR75hqeRlyuICad2bqiQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29830 | N | N | 15 | FIRST FLOORS |  | 125498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 45.6 | LABOR- SUBCONTRACTOR
%R | 504612 | 6359 | 125499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 248 | 0 | 40 | 0 | 28.4 | 28.4 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-19 08:00 | 2014-01-23 17:00 |  | 2013-12-12 08:00 | 2013-12-17 17:00 | 2013-12-12 08:00 | 2013-12-17 17:00 | 2013-12-12 08:00 | 2013-12-17 17:00 | 2014-01-19 08:00 | 2014-01-23 17:00 |  | PT_Normal |  |  |  |  | gESe88FSSamOE+/5Th2Hvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29830 | N | N | 15 | FIRST FLOORS |  | 125498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 28.4 | LABOR- SUBCONTRACTOR
%R | 504613 | 6359 | 125499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 264 | 0 | 40 | 0 | 206.4 | 206.4 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-27 08:00 | 2014-02-01 17:00 |  | 2013-12-19 08:00 | 2013-12-24 17:00 | 2013-12-19 08:00 | 2013-12-24 17:00 | 2013-12-19 08:00 | 2013-12-24 17:00 | 2014-01-27 08:00 | 2014-02-01 17:00 |  | PT_Normal |  |  |  |  | TcGK9FRySzeXRlvvlTua7g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29830 | N | N | 15 | FIRST FLOORS |  | 125498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 206.4 | LABOR- SUBCONTRACTOR
%R | 504614 | 6359 | 125499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 208 | 192 | 56 | 0 | 134.4 | 134.4 | 56 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-01-20 17:00 |  | 2013-12-12 08:00 | 2013-12-21 17:00 | 2013-12-12 08:00 | 2013-12-21 17:00 | 2013-12-12 08:00 | 2013-12-21 17:00 | 2014-01-13 08:00 | 2014-01-20 17:00 |  | PT_Normal |  |  |  |  | ejnIPXbeTHu4Jm+81Ft+rA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29830 | N | N | 15 | FIRST FLOORS |  | 125498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 504615 | 6359 | 125499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKELFF4050 | Installation of Telephone System | 8178 | 248 | 0 | 40 | 0 | 62 | 62 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-25 08:00 | 2014-01-29 17:00 |  | 2013-12-19 08:00 | 2013-12-24 17:00 | 2013-12-19 08:00 | 2013-12-24 17:00 | 2013-12-19 08:00 | 2013-12-24 17:00 | 2014-01-25 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | U344Is1JSGCYXTNAXt0vuQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29830 | N | N | 15 | FIRST FLOORS |  | 125498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 62 | LABOR- SUBCONTRACTOR
%R | 504616 | 6359 | 125500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 200 | 0 | 40 | 0 | 158.4 | 158.4 | 40 | 0 | 0 | 0 |  |  |  | 2013-10-09 08:00 | 2013-10-14 17:00 |  | 2013-09-10 08:00 | 2013-09-15 17:00 | 2013-09-10 08:00 | 2013-09-15 17:00 | 2013-09-10 08:00 | 2013-09-15 17:00 | 2013-10-09 08:00 | 2013-10-14 17:00 |  | PT_Normal |  |  |  |  | 4ohYQ0CISyu807SaljfpFg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29820 | N | N | 10 | GROUND FLOOR |  | 125498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 158.4 | LABOR- SUBCONTRACTOR
%R | 504617 | 6359 | 125500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKELGF4005 | Cable tray & trunking installation | 8178 | 344 | 0 | 40 | 0 | 170.4 | 170.4 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-16 08:00 | 2013-11-20 17:00 |  | 2013-09-24 08:00 | 2013-09-29 17:00 | 2013-09-24 08:00 | 2013-09-29 17:00 | 2013-09-24 08:00 | 2013-09-29 17:00 | 2013-11-16 08:00 | 2013-11-20 17:00 |  | PT_Normal |  |  |  |  | Il27HdSaRaG3lm0NQqXQRQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29820 | N | N | 10 | GROUND FLOOR |  | 125498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 170.4 | LABOR- SUBCONTRACTOR
%R | 504618 | 6359 | 125500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKELGF4010 | Installation of wiring & Main Cabling | 8178 | 360 | 16 | 40 | 0 | 45.6 | 45.6 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-24 08:00 | 2013-11-28 17:00 |  | 2013-09-30 08:00 | 2013-10-05 17:00 | 2013-09-30 08:00 | 2013-10-05 17:00 | 2013-09-30 08:00 | 2013-10-05 17:00 | 2013-11-24 08:00 | 2013-11-28 17:00 |  | PT_Normal |  |  |  |  | gKA7LKWvS6WxP9gtPKOA+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29820 | N | N | 10 | GROUND FLOOR |  | 125498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 45.6 | LABOR- SUBCONTRACTOR
%R | 504619 | 6359 | 125500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 416 | 0 | 40 | 0 | 28.4 | 28.4 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-01 08:00 | 2014-01-06 17:00 |  | 2013-10-31 08:00 | 2013-11-05 17:00 | 2013-10-31 08:00 | 2013-11-05 17:00 | 2013-10-31 08:00 | 2013-11-05 17:00 | 2014-01-01 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | sbpGpoinRn2eNnowX35uJQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29820 | N | N | 10 | GROUND FLOOR |  | 125498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 28.4 | LABOR- SUBCONTRACTOR
%R | 504620 | 6359 | 125500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 512 | 248 | 40 | 0 | 206.4 | 206.4 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-21 08:00 | 2014-01-26 17:00 |  | 2013-11-06 08:00 | 2013-11-11 17:00 | 2013-11-06 08:00 | 2013-11-11 17:00 | 2013-11-06 08:00 | 2013-11-11 17:00 | 2014-01-21 08:00 | 2014-01-26 17:00 |  | PT_Normal |  |  |  |  | lXzOvx8SQ8OO2mjzk2Ofgw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29820 | N | N | 10 | GROUND FLOOR |  | 125498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 206.4 | LABOR- SUBCONTRACTOR
%R | 504621 | 6359 | 125500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 432 | 208 | 56 | 0 | 134.4 | 134.4 | 56 | 0 | 0 | 0 |  |  |  | 2014-01-05 08:00 | 2014-01-12 17:00 |  | 2013-11-02 08:00 | 2013-11-09 17:00 | 2013-11-02 08:00 | 2013-11-09 17:00 | 2013-11-02 08:00 | 2013-11-09 17:00 | 2014-01-05 08:00 | 2014-01-12 17:00 |  | PT_Normal |  |  |  |  | jsIandXWQTSht7wcoaPlCg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29820 | N | N | 10 | GROUND FLOOR |  | 125498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 504622 | 6359 | 125500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKELGF4030 | Installation of Telephone System | 8178 | 456 | 248 | 40 | 0 | 68 | 68 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-01-18 17:00 |  | 2013-11-06 08:00 | 2013-11-11 17:00 | 2013-11-06 08:00 | 2013-11-11 17:00 | 2013-11-06 08:00 | 2013-11-11 17:00 | 2014-01-13 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | KqhtFLs7QtupKpcPwCAiFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29820 | N | N | 10 | GROUND FLOOR |  | 125498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 68 | LABOR- SUBCONTRACTOR
%R | 504623 | 6359 | 125501 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKELRF4070 | Installation of Isolator | 8178 | 304 | 0 | 40 | 0 | 51.6 | 51.6 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-08 08:00 | 2014-02-13 17:00 |  | 2013-12-25 08:00 | 2013-12-30 17:00 | 2013-12-25 08:00 | 2013-12-30 17:00 | 2013-12-25 08:00 | 2013-12-30 17:00 | 2014-02-08 08:00 | 2014-02-13 17:00 |  | PT_Normal |  |  |  |  | X0RUHrihSYCR9MF3PNyQiA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29840 | N | N | 20 | ROOF |  | 125498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 51.6 | LABOR- SUBCONTRACTOR
%R | 504624 | 6359 | 125501 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AMKELRF4075 | Installation of TV Dish Antenna | 8178 | 304 | 296 | 56 | 0 | 97.2 | 97.2 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-15 08:00 | 2014-02-22 17:00 |  | 2013-12-31 08:00 | 2014-01-07 17:00 | 2013-12-31 08:00 | 2014-01-07 17:00 | 2013-12-31 08:00 | 2014-01-07 17:00 | 2014-02-15 08:00 | 2014-02-22 17:00 |  | PT_Normal |  |  |  |  | 582WTAg8R0uZP3bjxtmRRw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29840 | N | N | 20 | ROOF |  | 125498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 97.2 | LABOR- SUBCONTRACTOR
%R | 504625 | 6359 | 125505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARFF3300 | Block work | 8168 | 0 | 0 | 200 | 0 | 5591 | 5591 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-24 08:00 | 2013-11-21 17:00 |  | 2013-10-24 08:00 | 2013-11-21 17:00 | 2013-10-24 08:00 | 2013-11-21 17:00 | 2013-10-24 08:00 | 2013-11-21 17:00 | 2013-10-24 08:00 | 2013-11-21 17:00 |  | PT_Normal |  |  |  |  | /4rk1cUcRxu3UkQBMdO70A |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30100 | N | N | 15 | FIRST FLOORS |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 5591 | BLOCK MASON SK
%R | 504626 | 6359 | 125505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARFF3305 | Plastering work | 8169 | 0 | 0 | 200 | 0 | 7786.5 | 7786.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-17 08:00 | 2013-12-15 17:00 |  | 2013-11-17 08:00 | 2013-12-15 17:00 | 2013-11-17 08:00 | 2013-12-15 17:00 | 2013-11-17 08:00 | 2013-12-15 17:00 | 2013-11-17 08:00 | 2013-12-15 17:00 |  | PT_Normal |  |  |  |  | 5Q1l/wvdQgKN6taLyad7pw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30100 | N | N | 15 | FIRST FLOORS |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 7786.5 | PLASTER MASON SK
%R | 504627 | 6359 | 125505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARFF3310 | Flooring screed | 8164 | 96 | 96 | 168 | 0 | 1064.25 | 1064.25 | 168 | 0 | 0 | 0 |  |  |  | 2013-12-09 08:00 | 2014-01-02 17:00 |  | 2013-11-25 08:00 | 2013-12-19 17:00 | 2013-11-25 08:00 | 2013-12-19 17:00 | 2013-11-25 08:00 | 2013-12-19 17:00 | 2013-12-09 08:00 | 2014-01-02 17:00 |  | PT_Normal |  |  |  |  | IyIZyUeRSSaTR0Jo9OXzVQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30100 | N | N | 15 | FIRST FLOORS |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1064.25 | SCREED MASON SK
%R | 504628 | 6359 | 125505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARFF3315 | Wet area waterproofing | 8178 | 0 | 0 | 120 | 0 | 1063.25 | 1063.25 | 120 | 0 | 0 | 0 |  |  |  | 2013-12-07 08:00 | 2013-12-24 17:00 |  | 2013-12-07 08:00 | 2013-12-24 17:00 | 2013-12-07 08:00 | 2013-12-24 17:00 | 2013-12-07 08:00 | 2013-12-24 17:00 | 2013-12-07 08:00 | 2013-12-24 17:00 |  | PT_Normal |  |  |  |  | 5OqEmVXkRiO4VgRzCT+TNA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30100 | N | N | 15 | FIRST FLOORS |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1063.25 | LABOR- SUBCONTRACTOR
%R | 504629 | 6359 | 125505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARFF3330 | Paint First coat | 8178 | 112 | 112 | 200 | 0 | 4149.75 | 4149.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-21 08:00 | 2014-01-18 17:00 |  | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | ZmZGNjX4SDquK+L1vIvJ5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30100 | N | N | 15 | FIRST FLOORS |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 4149.75 | LABOR- SUBCONTRACTOR
%R | 504630 | 6359 | 125505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARFF3320 | Ceramic Wall Tiling | 8170 | 0 | 0 | 200 | 0 | 1659.75 | 1659.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-14 08:00 | 2014-01-12 17:00 |  | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 |  | PT_Normal |  |  |  |  | njjYck0BRdCkr1JROn71wA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30100 | N | N | 15 | FIRST FLOORS |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1659.75 | TILE MASON SK
%R | 504631 | 6359 | 125505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARFF3325 | Porcelain Tile flooring | 8170 | 0 | 0 | 200 | 0 | 1525 | 1525 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-22 08:00 | 2014-01-19 17:00 |  | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 |  | PT_Normal |  |  |  |  | Dc9RK7vOS0mph4gCMeprRg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30100 | N | N | 15 | FIRST FLOORS |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1525 | TILE MASON SK
%R | 504632 | 6359 | 125505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARFF3335 | Slate Tile Flooring & Skirting | 8170 | 64 | 64 | 120 | 0 | 228.5 | 228.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-18 08:00 | 2014-02-03 17:00 |  | 2014-01-08 08:00 | 2014-01-25 17:00 | 2014-01-08 08:00 | 2014-01-25 17:00 | 2014-01-08 08:00 | 2014-01-25 17:00 | 2014-01-18 08:00 | 2014-02-03 17:00 |  | PT_Normal |  |  |  |  | jnp+Q9R4T1+tv1SljVJl7Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30100 | N | N | 15 | FIRST FLOORS |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 228.5 | TILE MASON SK
%R | 504633 | 6359 | 125505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARFF3350 | Granite - Stair case flooring & Skirting | 8171 | 16 | 16 | 160 | 0 | 768.75 | 768.75 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-02-05 17:00 |  | 2014-01-12 08:00 | 2014-02-03 17:00 | 2014-01-12 08:00 | 2014-02-03 17:00 | 2014-01-12 08:00 | 2014-02-03 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | G4jAopC1R+6LOr1kIvCCCg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30100 | N | N | 15 | FIRST FLOORS |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 768.75 | GRANITE MASON SK
%R | 504634 | 6359 | 125505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARFF3345 | Fixing of Suspension systems | 8178 | 0 | 0 | 160 | 0 | 1142.23 | 1142.23 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-04 08:00 | 2014-01-26 17:00 |  | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-01-04 08:00 | 2014-01-26 17:00 |  | PT_Normal |  |  |  |  | 3ts9Kn/bR0y1L0ZfPfzGLQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30100 | N | N | 15 | FIRST FLOORS |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1142.23 | LABOR- SUBCONTRACTOR
%R | 504635 | 6359 | 125505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARFF3360 | Gypsum board false ceiling | 8178 | 0 | 0 | 200 | 0 | 1142 | 1142 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-11 08:00 | 2014-02-08 17:00 |  | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 |  | PT_Normal |  |  |  |  | t7z0VWV5QSyTfZGHIRAmUQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30100 | N | N | 15 | FIRST FLOORS |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1142 | LABOR- SUBCONTRACTOR
%R | 504636 | 6359 | 125505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARFF3365 | Wooden door | 8178 | 0 | 0 | 120 | 0 | 269.5 | 269.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-26 08:00 | 2014-02-12 17:00 |  | 2014-01-26 08:00 | 2014-02-12 17:00 | 2014-01-26 08:00 | 2014-02-12 17:00 | 2014-01-26 08:00 | 2014-02-12 17:00 | 2014-01-26 08:00 | 2014-02-12 17:00 |  | PT_Normal |  |  |  |  | jibozNweTDeFxtwEv3ROvQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30100 | N | N | 15 | FIRST FLOORS |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 269.5 | LABOR- SUBCONTRACTOR
%R | 504637 | 6359 | 125505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARFF3370 | Aluminum Door | 8178 | 0 | 0 | 160 | 0 | 192.5 | 192.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-26 08:00 | 2014-02-18 17:00 |  | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-01-26 08:00 | 2014-02-18 17:00 |  | PT_Normal |  |  |  |  | h2iKIAKATc6dZ+wMu+uvhg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30100 | N | N | 15 | FIRST FLOORS |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 192.5 | LABOR- SUBCONTRACTOR
%R | 504638 | 6359 | 125505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARFF3380 | Aluminum windows | 8178 | 40 | 40 | 160 | 0 | 143 | 143 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-08 08:00 | 2014-03-03 17:00 |  | 2014-02-02 08:00 | 2014-02-25 17:00 | 2014-02-02 08:00 | 2014-02-25 17:00 | 2014-02-02 08:00 | 2014-02-25 17:00 | 2014-02-08 08:00 | 2014-03-03 17:00 |  | PT_Normal |  |  |  |  | 3WZsIxsJQRibZ55DHIlUwA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30100 | N | N | 15 | FIRST FLOORS |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 143 | LABOR- SUBCONTRACTOR
%R | 504639 | 6359 | 125505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARFF3375 | Carpentry & Joinery Works | 8178 | 0 | 0 | 200 | 0 | 962.5 | 962.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-01 08:00 | 2014-03-02 17:00 |  | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 |  | PT_Normal |  |  |  |  | gYzm1pdvSHiDFasvSkWlEw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30100 | N | N | 15 | FIRST FLOORS |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 481.25 | LABOR- SUBCONTRACTOR
%R | 504640 | 6359 | 125505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARFF3390 | Installation of Granite Counter Top | 8171 | 8 | 8 | 160 | 0 | 77 | 77 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-10 17:00 |  | 2014-02-15 08:00 | 2014-03-09 17:00 | 2014-02-15 08:00 | 2014-03-09 17:00 | 2014-02-15 08:00 | 2014-03-09 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | K0OHBorYSMit3A0u/THuOw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30100 | N | N | 15 | FIRST FLOORS |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 77 | GRANITE MASON SK
%R | 504641 | 6359 | 125505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARFF3385 | Handrail & S.S.Balustrade | 8178 | 0 | 0 | 160 | 0 | 691 | 691 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-15 08:00 | 2014-03-09 17:00 |  | 2014-02-15 08:00 | 2014-03-09 17:00 | 2014-02-15 08:00 | 2014-03-09 17:00 | 2014-02-15 08:00 | 2014-03-09 17:00 | 2014-02-15 08:00 | 2014-03-09 17:00 |  | PT_Normal |  |  |  |  | xQE01IexRrStWFYj8aPYyA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30100 | N | N | 15 | FIRST FLOORS |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 691 | LABOR- SUBCONTRACTOR
%R | 504642 | 6359 | 125505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARFF3395 | Final Painting | 8178 | 0 | 0 | 200 | 0 | 4149.75 | 4149.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-20 08:00 | 2014-03-20 17:00 |  | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | DFAdwBa/QVOfeWoVPPHrzQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30100 | N | N | 15 | FIRST FLOORS |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 2074.875 | LABOR- SUBCONTRACTOR
%R | 504643 | 6359 | 125506 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARRF3600 | Block work | 8168 | 168 | 0 | 160 | 0 | 612.5 | 612.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-07 08:00 | 2013-12-30 17:00 |  | 2013-11-12 08:00 | 2013-12-04 17:00 | 2013-11-12 08:00 | 2013-12-04 17:00 | 2013-11-12 08:00 | 2013-12-04 17:00 | 2013-12-07 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | RMs3CaO3RPSu1XVfjHdxJQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30110 | N | N | 20 | ROOF |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 612.5 | BLOCK MASON SK
%R | 504644 | 6359 | 125506 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARRF3605 | Plastering work | 8169 | 168 | 0 | 160 | 0 | 1561.5 | 1561.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-15 08:00 | 2014-01-07 17:00 |  | 2013-11-20 08:00 | 2013-12-12 17:00 | 2013-11-20 08:00 | 2013-12-12 17:00 | 2013-11-20 08:00 | 2013-12-12 17:00 | 2013-12-15 08:00 | 2014-01-07 17:00 |  | PT_Normal |  |  |  |  | SM6p343rTBKi7vYUjC6k5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30110 | N | N | 20 | ROOF |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1561.5 | PLASTER MASON SK
%R | 504645 | 6359 | 125506 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARRF3610 | Flooring screed | 8164 | 360 | 0 | 120 | 0 | 120 | 120 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-27 08:00 | 2014-02-13 17:00 |  | 2013-12-04 08:00 | 2013-12-22 17:00 | 2013-12-04 08:00 | 2013-12-22 17:00 | 2013-12-04 08:00 | 2013-12-22 17:00 | 2014-01-27 08:00 | 2014-02-13 17:00 |  | PT_Normal |  |  |  |  | L4pt2Nx8Qhe36GzPRyGYfQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30110 | N | N | 20 | ROOF |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 120 | SCREED MASON SK
%R | 504646 | 6359 | 125506 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARRF3695 | Painting -Storage area | 8178 | 360 | 0 | 160 | 0 | 1442 | 1442 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-04 08:00 | 2014-02-27 17:00 |  | 2013-12-12 08:00 | 2014-01-05 17:00 | 2013-12-12 08:00 | 2014-01-05 17:00 | 2013-12-12 08:00 | 2014-01-05 17:00 | 2014-02-04 08:00 | 2014-02-27 17:00 |  | PT_Normal |  |  |  |  | twlhfNaxQ4O5f9NpSs/wdQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30110 | N | N | 20 | ROOF |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1442 | LABOR- SUBCONTRACTOR
%R | 504647 | 6359 | 125506 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARRF3620 | Epoxy Painting -Storage area | 8178 | 360 | 360 | 120 | 0 | 41.25 | 41.25 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-23 08:00 | 2014-03-11 17:00 |  | 2013-12-31 08:00 | 2014-01-16 17:00 | 2013-12-31 08:00 | 2014-01-16 17:00 | 2013-12-31 08:00 | 2014-01-16 17:00 | 2014-02-23 08:00 | 2014-03-11 17:00 |  | PT_Normal |  |  |  |  | +jXmV+IfTm+2i+HFt1xM7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30110 | N | N | 20 | ROOF |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 41.25 | LABOR- SUBCONTRACTOR
%R | 504648 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3000 | Block work | 8168 | 144 | 0 | 200 | 0 | 8522.25 | 8522.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-01 08:00 | 2013-10-31 17:00 |  | 2013-09-10 08:00 | 2013-10-08 17:00 | 2013-09-10 08:00 | 2013-10-08 17:00 | 2013-09-10 08:00 | 2013-10-08 17:00 | 2013-10-01 08:00 | 2013-10-31 17:00 |  | PT_Normal |  |  |  |  | s8SyqUB2TwOSP5p+45Ifyg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 8522.25 | BLOCK MASON SK
%R | 504649 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3005 | Plastering work | 8169 | 144 | 0 | 200 | 0 | 11933 | 11933 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-26 08:00 | 2013-11-23 17:00 |  | 2013-10-02 08:00 | 2013-11-02 17:00 | 2013-10-02 08:00 | 2013-11-02 17:00 | 2013-10-02 08:00 | 2013-11-02 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 |  | PT_Normal |  |  |  |  | hQLpymOaSK+2R3VlwDR6sg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 5966.5 | PLASTER MASON SK
%R | 504650 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3010 | Flooring screed | 8164 | 208 | 64 | 168 | 0 | 1382.25 | 1382.25 | 168 | 0 | 0 | 0 |  |  |  | 2013-11-12 08:00 | 2013-12-05 17:00 |  | 2013-10-10 08:00 | 2013-11-05 17:00 | 2013-10-10 08:00 | 2013-11-05 17:00 | 2013-10-10 08:00 | 2013-11-05 17:00 | 2013-11-12 08:00 | 2013-12-05 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1382.25 | SCREED MASON SK
%R | 504651 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 144 | 0 | 120 | 0 | 216.25 | 216.25 | 120 | 0 | 0 | 0 |  |  |  | 2013-11-12 08:00 | 2013-11-28 17:00 |  | 2013-10-22 08:00 | 2013-11-07 17:00 | 2013-10-22 08:00 | 2013-11-07 17:00 | 2013-10-22 08:00 | 2013-11-07 17:00 | 2013-11-12 08:00 | 2013-11-28 17:00 |  | PT_Normal |  |  |  |  | JSl0Tb5KTZC2i8dCU+dp2A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 216.25 | LABOR- SUBCONTRACTOR
%R | 504652 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3030 | Paint First coat | 8178 | 256 | 0 | 200 | 0 | 4752 | 4752 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-27 08:00 | 2013-12-26 17:00 |  | 2013-10-21 08:00 | 2013-11-18 17:00 | 2013-10-21 08:00 | 2013-11-18 17:00 | 2013-10-21 08:00 | 2013-11-18 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 |  | PT_Normal |  |  |  |  | rV/CKiWsTIe6dOso7TmFvg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 4752 | LABOR- SUBCONTRACTOR
%R | 504653 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3020 | Ceramic Wall Tiling | 8170 | 144 | 0 | 200 | 0 | 3875 | 3875 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-18 08:00 | 2013-12-16 17:00 |  | 2013-10-28 08:00 | 2013-11-25 17:00 | 2013-10-28 08:00 | 2013-11-25 17:00 | 2013-10-28 08:00 | 2013-11-25 17:00 | 2013-11-18 08:00 | 2013-12-16 17:00 |  | PT_Normal |  |  |  |  | 6sAbHTh8S8i8FgU/6BIQVw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 3875 | TILE MASON SK
%R | 504654 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3025 | Porcelain Tile flooring | 8170 | 144 | 0 | 200 | 0 | 1525 | 1525 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-24 08:00 | 2013-12-23 17:00 |  | 2013-11-03 08:00 | 2013-12-01 17:00 | 2013-11-03 08:00 | 2013-12-01 17:00 | 2013-11-03 08:00 | 2013-12-01 17:00 | 2013-11-24 08:00 | 2013-12-23 17:00 |  | PT_Normal |  |  |  |  | z1p6+lTbSre3eMTNa5oEfA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1525 | TILE MASON SK
%R | 504655 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3040 | Cobble Tile flooring | 8170 | 168 | 0 | 120 | 0 | 649 | 649 | 120 | 0 | 0 | 0 |  |  |  | 2013-12-25 08:00 | 2014-01-11 17:00 |  | 2013-11-30 08:00 | 2013-12-16 17:00 | 2013-11-30 08:00 | 2013-12-16 17:00 | 2013-11-30 08:00 | 2013-12-16 17:00 | 2013-12-25 08:00 | 2014-01-11 17:00 |  | PT_Normal |  |  |  |  | sbfQahpHQlqlQN5NshscYw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 649 | TILE MASON SK
%R | 504656 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 184 | 16 | 120 | 0 | 666 | 666 | 120 | 0 | 0 | 0 |  |  |  | 2013-12-21 08:00 | 2014-01-06 17:00 |  | 2013-11-23 08:00 | 2013-12-09 17:00 | 2013-11-23 08:00 | 2013-12-09 17:00 | 2013-11-23 08:00 | 2013-12-09 17:00 | 2013-12-21 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | w22Md4deT6aAeEbJKi2cjg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 666 | TILE MASON SK
%R | 504657 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 168 | 0 | 160 | 0 | 762.5 | 762.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-02 08:00 | 2014-01-25 17:00 |  | 2013-12-08 08:00 | 2013-12-31 17:00 | 2013-12-08 08:00 | 2013-12-31 17:00 | 2013-12-08 08:00 | 2013-12-31 17:00 | 2014-01-02 08:00 | 2014-01-25 17:00 |  | PT_Normal |  |  |  |  | 2YfNDd00QM2eKPKfseyuuw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 762.5 | GRANITE MASON SK
%R | 504658 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3045 | Fixing of Suspension systems | 8178 | 144 | 0 | 160 | 0 | 1273.48 | 1273.48 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-11 08:00 | 2014-01-04 17:00 |  | 2013-11-20 08:00 | 2013-12-12 17:00 | 2013-11-20 08:00 | 2013-12-12 17:00 | 2013-11-20 08:00 | 2013-12-12 17:00 | 2013-12-11 08:00 | 2014-01-04 17:00 |  | PT_Normal |  |  |  |  | SZjMsea0TOiguE9j7g+UfQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1273.48 | LABOR- SUBCONTRACTOR
%R | 504659 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3055 | Aluminum tile false ceiling | 8178 | 168 | 24 | 200 | 0 | 131.25 | 131.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-24 08:00 | 2014-01-21 17:00 |  | 2013-11-28 08:00 | 2013-12-28 17:00 | 2013-11-28 08:00 | 2013-12-28 17:00 | 2013-11-28 08:00 | 2013-12-28 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 |  | PT_Normal |  |  |  |  | qtmQheobQCaYzp0xufvN1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11; period 2: 2013-AP12 |  | 65.625 | LABOR- SUBCONTRACTOR
%R | 504660 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3060 | Gypsum board false ceiling | 8178 | 144 | 0 | 200 | 0 | 1168.75 | 1168.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-24 08:00 | 2014-01-21 17:00 |  | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 |  | PT_Normal |  |  |  |  | ILxXkSawSciIQUa0S3uMeg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1168.75 | LABOR- SUBCONTRACTOR
%R | 504661 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3065 | Wooden door & PVC Door | 8178 | 168 | 0 | 120 | 0 | 269.5 | 269.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-02-02 17:00 |  | 2013-12-23 08:00 | 2014-01-08 17:00 | 2013-12-23 08:00 | 2014-01-08 17:00 | 2013-12-23 08:00 | 2014-01-08 17:00 | 2014-01-16 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | Alir+HHZQW68EinmvbDa2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 269.5 | LABOR- SUBCONTRACTOR
%R | 504662 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3070 | Aluminum doors | 8178 | 168 | 0 | 120 | 0 | 154 | 154 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-08 17:00 |  | 2013-12-29 08:00 | 2014-01-14 17:00 | 2013-12-29 08:00 | 2014-01-14 17:00 | 2013-12-29 08:00 | 2014-01-14 17:00 | 2014-01-22 08:00 | 2014-02-08 17:00 |  | PT_Normal |  |  |  |  | irLx2+9aT9Czcj2nFyGTEA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 154 | LABOR- SUBCONTRACTOR
%R | 504663 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3080 | Aluminum windows | 8178 | 248 | 40 | 160 | 0 | 140.25 | 140.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-10 08:00 | 2014-03-05 17:00 |  | 2014-01-05 08:00 | 2014-01-27 17:00 | 2014-01-05 08:00 | 2014-01-27 17:00 | 2014-01-05 08:00 | 2014-01-27 17:00 | 2014-02-10 08:00 | 2014-03-05 17:00 |  | PT_Normal |  |  |  |  | pyFpDDb1Se+bc5RsyxJI8w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 140.25 | LABOR- SUBCONTRACTOR
%R | 504664 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3075 | Carpentry & Joinery Works | 8178 | 168 | 0 | 160 | 0 | 500.5 | 500.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-28 08:00 | 2014-02-20 17:00 |  | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-01-28 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | S4twa4MmR7iJVxxXoVNnfA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 500.5 | LABOR- SUBCONTRACTOR
%R | 504665 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3090 | Installation of Granite Counter Top | 8171 | 168 | 0 | 120 | 0 | 154 | 154 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-10 08:00 | 2014-02-27 17:00 |  | 2014-01-16 08:00 | 2014-02-02 17:00 | 2014-01-16 08:00 | 2014-02-02 17:00 | 2014-01-16 08:00 | 2014-02-02 17:00 | 2014-02-10 08:00 | 2014-02-27 17:00 |  | PT_Normal |  |  |  |  | g+v8WEy3Ssiy3DtGk65ieQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 154 | GRANITE MASON SK
%R | 504666 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3085 | S.S.Balustrade | 8178 | 208 | 40 | 160 | 0 | 231.25 | 231.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-06 17:00 |  | 2014-01-12 08:00 | 2014-02-03 17:00 | 2014-01-12 08:00 | 2014-02-03 17:00 | 2014-01-12 08:00 | 2014-02-03 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | /MqKPNKKSQK2WaFXpLRQcg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 231.25 | LABOR- SUBCONTRACTOR
%R | 504667 | 6359 | 125507 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARGF3095 | Final Painting | 8178 | 168 | 0 | 200 | 0 | 4752 | 4752 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-20 08:00 | 2014-03-20 17:00 |  | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | bYtZXk/CQVeCgycm4VExrQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30090 | N | N | 10 | GROUND FLOOR |  | 125504 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 4752 | LABOR- SUBCONTRACTOR
%R | 504668 | 6359 | 125509 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1AREL3665 | External Plastering | 8169 | 376 | 0 | 200 | 0 | 12491 | 12491 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-25 08:00 | 2014-02-23 17:00 |  | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | qonqCkaHTFawGxI0Ie8IwQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30140 | N | N | 15 | ELEVATION |  | 125508 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 12491 | PLASTER MASON SK
%R | 504669 | 6359 | 125509 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1AREL3670 | External stone cladding works | 8170 | 392 | 0 | 160 | 0 | 866.25 | 866.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-15 08:00 | 2014-03-09 17:00 |  | 2013-12-17 08:00 | 2014-01-09 17:00 | 2013-12-17 08:00 | 2014-01-09 17:00 | 2013-12-17 08:00 | 2014-01-09 17:00 | 2014-02-15 08:00 | 2014-03-09 17:00 |  | PT_Normal |  |  |  |  | /HZzhsm2Teyo1xDAnnuyCg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30140 | N | N | 15 | ELEVATION |  | 125508 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 866.25 | TILE MASON SK
%R | 504670 | 6359 | 125509 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1AREL3680 | External Painting | 8178 | 392 | 40 | 160 | 0 | 3314 | 3314 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-26 08:00 | 2014-03-20 17:00 |  | 2013-12-30 08:00 | 2014-01-21 17:00 | 2013-12-30 08:00 | 2014-01-21 17:00 | 2013-12-30 08:00 | 2014-01-21 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | 1SsS/zMwTdukAm2pk314WA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30140 | N | N | 15 | ELEVATION |  | 125508 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 3314 | LABOR- SUBCONTRACTOR
%R | 504671 | 6359 | 125510 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARRF3630 | Leveling Screed for Waterproofing | 8164 | 168 | 0 | 200 | 0 | 700 | 700 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-08 08:00 | 2014-02-05 17:00 |  | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | oCQTptSYRKWdZpZLBIIylg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30130 | N | N | 10 | ROOF |  | 125508 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 700 | SCREED MASON SK
%R | 504672 | 6359 | 125510 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARRF3635 | Laying of Waterproofing Membrane | 8178 | 168 | 0 | 200 | 0 | 997.25 | 997.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-12 08:00 | 2014-02-09 17:00 |  | 2013-12-17 08:00 | 2014-01-15 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 | 2014-01-12 08:00 | 2014-02-09 17:00 |  | PT_Normal |  |  |  |  | WIRAXGrqRKKc9wex4sfDVQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30130 | N | N | 10 | ROOF |  | 125508 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 997.25 | LABOR- SUBCONTRACTOR
%R | 504673 | 6359 | 125510 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARRF3640 | Installation of Insulation & Protection | 8178 | 168 | 0 | 200 | 0 | 1232 | 1232 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-02-15 17:00 |  | 2013-12-23 08:00 | 2014-01-20 17:00 | 2013-12-23 08:00 | 2014-01-20 17:00 | 2013-12-23 08:00 | 2014-01-20 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 |  | PT_Normal |  |  |  |  | QMFtPjXySGmVVyPZYRA5vQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30130 | N | N | 10 | ROOF |  | 125508 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1232 | LABOR- SUBCONTRACTOR
%R | 504674 | 6359 | 125510 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 168 | 0 | 200 | 0 | 602.25 | 602.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-21 08:00 | 2014-02-19 17:00 |  | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 |  | PT_Normal |  |  |  |  | SBYE8kkQQdmYuAjzrKmxdQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30130 | N | N | 10 | ROOF |  | 125508 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 602.25 | TILE MASON SK
%R | 504675 | 6359 | 125510 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 168 | 0 | 160 | 0 | 539 | 539 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-15 08:00 | 2014-03-09 17:00 |  | 2014-01-20 08:00 | 2014-02-12 17:00 | 2014-01-20 08:00 | 2014-02-12 17:00 | 2014-01-20 08:00 | 2014-02-12 17:00 | 2014-02-15 08:00 | 2014-03-09 17:00 |  | PT_Normal |  |  |  |  | hC+nH2hzRoK75G60weW/KQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30130 | N | N | 10 | ROOF |  | 125508 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 539 | LABOR- SUBCONTRACTOR
%R | 504676 | 6359 | 125510 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 168 | 0 | 200 | 0 | 915.25 | 915.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-29 08:00 | 2014-02-27 17:00 |  | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 |  | PT_Normal |  |  |  |  | v+XTmHR4S/qhlvEkr2SO2Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30130 | N | N | 10 | ROOF |  | 125508 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 915.25 | LABOR- SUBCONTRACTOR
%R | 504677 | 6359 | 125510 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ARRF3660 | Installation of Access Ladder | 8178 | 208 | 208 | 120 | 0 | 154 | 154 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-04 08:00 | 2014-03-20 17:00 |  | 2014-02-01 08:00 | 2014-02-18 17:00 | 2014-02-01 08:00 | 2014-02-18 17:00 | 2014-02-01 08:00 | 2014-02-18 17:00 | 2014-03-04 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | vQAGgm3LRoyiDfaFhQ2VBA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30130 | N | N | 10 | ROOF |  | 125508 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 154 | LABOR- SUBCONTRACTOR
%R | 504678 | 6359 | 125513 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ACFF4615 | Installation AC Pipes | 8178 | 216 | 48 | 160 | 0 | 864 | 864 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-02 08:00 | 2014-01-25 17:00 |  | 2013-12-01 08:00 | 2013-12-24 17:00 | 2013-12-01 08:00 | 2013-12-24 17:00 | 2013-12-01 08:00 | 2013-12-24 17:00 | 2014-01-02 08:00 | 2014-01-25 17:00 |  | PT_Normal |  |  |  |  | J1s4RxY/SJi8kdzUX2CzgA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30260 | N | N | 15 | FIRST FLOORS |  | 125512 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 864 | LABOR- SUBCONTRACTOR
%R | 504679 | 6359 | 125513 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ACFF4620 | Fixing of Ventilation Equipments | 8178 | 24 | 0 | 200 | 0 | 102.4 | 102.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-20 17:00 |  | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | ASajaRKzSriXFzb5ZT93hA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30260 | N | N | 15 | FIRST FLOORS |  | 125512 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 102.4 | LABOR- SUBCONTRACTOR
%R | 504680 | 6359 | 125513 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ACFF4625 | Fixing of Split AC | 8178 | 24 | 0 | 160 | 0 | 267.6 | 267.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-03-08 17:00 |  | 2014-02-09 08:00 | 2014-03-04 17:00 | 2014-02-09 08:00 | 2014-03-04 17:00 | 2014-02-09 08:00 | 2014-03-04 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | B/mHSsqZRq+hnQh2uIomnQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30260 | N | N | 15 | FIRST FLOORS |  | 125512 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 267.6 | LABOR- SUBCONTRACTOR
%R | 504681 | 6359 | 125514 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ACGF4600 | Installation AC Pipes | 8178 | 392 | 40 | 160 | 0 | 864 | 864 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-15 08:00 | 2014-01-07 17:00 |  | 2013-10-16 08:00 | 2013-11-10 17:00 | 2013-10-16 08:00 | 2013-11-10 17:00 | 2013-10-16 08:00 | 2013-11-10 17:00 | 2013-12-15 08:00 | 2014-01-07 17:00 |  | PT_Normal |  |  |  |  | jD20VL3ES9CXq1PNXHkFKQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30250 | N | N | 10 | GROUND FLOOR |  | 125512 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 864 | LABOR- SUBCONTRACTOR
%R | 504682 | 6359 | 125514 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ACGF4605 | Fixing of Ventilation Equipments | 8178 | 256 | 0 | 200 | 0 | 165.2 | 165.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-18 08:00 | 2014-02-16 17:00 |  | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2014-01-18 08:00 | 2014-02-16 17:00 |  | PT_Normal |  |  |  |  | 20E6zrJBT+WD9hS/9yS5kw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30250 | N | N | 10 | GROUND FLOOR |  | 125512 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 165.2 | LABOR- SUBCONTRACTOR
%R | 504683 | 6359 | 125514 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ACGF4610 | Fixing of Split AC | 8178 | 256 | 40 | 160 | 0 | 267.6 | 267.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-08 08:00 | 2014-03-03 17:00 |  | 2014-01-01 08:00 | 2014-01-23 17:00 | 2014-01-01 08:00 | 2014-01-23 17:00 | 2014-01-01 08:00 | 2014-01-23 17:00 | 2014-02-08 08:00 | 2014-03-03 17:00 |  | PT_Normal |  |  |  |  | JI5iMXEWQhyBdW2zBfUUFg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30250 | N | N | 10 | GROUND FLOOR |  | 125512 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 267.6 | LABOR- SUBCONTRACTOR
%R | 504684 | 6359 | 125515 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ACRF4630 | Installation of Refrigerant Pipes | 8178 | 272 | 0 | 200 | 0 | 364 | 364 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-15 08:00 | 2014-03-15 17:00 |  | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 |  | PT_Normal |  |  |  |  | fC5iiThaSv25pw5mQEZMEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30270 | N | N | 20 | ROOF |  | 125512 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 364 | LABOR- SUBCONTRACTOR
%R | 504685 | 6359 | 125515 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ACRF4635 | Installation of Condensing Unit | 8178 | 32 | 8 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-20 08:00 | 2014-03-20 17:00 |  | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | UMkzzGySRmi4NiHrSyo0Fw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30270 | N | N | 20 | ROOF |  | 125512 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 250 | LABOR- SUBCONTRACTOR
%R | 504686 | 6359 | 125517 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 0 | 0 | 144 | 0 | 386.4 | 386.4 | 144 | 0 | 0 | 0 |  |  |  | 2013-11-10 08:00 | 2013-11-30 17:00 |  | 2013-11-10 08:00 | 2013-11-30 17:00 | 2013-11-10 08:00 | 2013-11-30 17:00 | 2013-11-10 08:00 | 2013-11-30 17:00 | 2013-11-10 08:00 | 2013-11-30 17:00 |  | PT_Normal |  |  |  |  | 0tW5KFFQQC6HkPx8sUaHWw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30220 | N | N | 15 | FIRST FLOORS |  | 125516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 386.4 | LABOR- SUBCONTRACTOR
%R | 504687 | 6359 | 125517 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1PLFF4330 | Installation of Drainage pipes & testing | 8178 | 176 | 64 | 144 | 0 | 160.8 | 160.8 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-05 08:00 | 2013-12-26 17:00 |  | 2013-11-10 08:00 | 2013-11-30 17:00 | 2013-11-10 08:00 | 2013-11-30 17:00 | 2013-11-10 08:00 | 2013-11-30 17:00 | 2013-12-05 08:00 | 2013-12-26 17:00 |  | PT_Normal |  |  |  |  | bWUlJnMGSdamwBGve9UmuA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30220 | N | N | 15 | FIRST FLOORS |  | 125516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 160.8 | LABOR- SUBCONTRACTOR
%R | 504688 | 6359 | 125517 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1PLFF4335 | Sanitary Fittings & Accessories | 8178 | 8 | 0 | 160 | 0 | 67.2 | 67.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-02 08:00 | 2014-02-25 17:00 |  | 2014-02-01 08:00 | 2014-02-24 17:00 | 2014-02-01 08:00 | 2014-02-24 17:00 | 2014-02-01 08:00 | 2014-02-24 17:00 | 2014-02-02 08:00 | 2014-02-25 17:00 |  | PT_Normal |  |  |  |  | eS0W/tXXSnmD30AcFnjQGw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30220 | N | N | 15 | FIRST FLOORS |  | 125516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504689 | 6359 | 125517 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1PLFF4340 | Installation of Water Heater | 8178 | 8 | 0 | 120 | 0 | 67.2 | 67.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-15 08:00 | 2014-03-03 17:00 |  | 2014-02-13 08:00 | 2014-03-02 17:00 | 2014-02-13 08:00 | 2014-03-02 17:00 | 2014-02-13 08:00 | 2014-03-02 17:00 | 2014-02-15 08:00 | 2014-03-03 17:00 |  | PT_Normal |  |  |  |  | 83AqL6wHTWancoLwBWGVjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30220 | N | N | 15 | FIRST FLOORS |  | 125516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504690 | 6359 | 125518 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 416 | 208 | 120 | 0 | 99.6 | 99.6 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-04 08:00 | 2014-02-22 17:00 |  | 2013-12-04 08:00 | 2013-12-22 17:00 | 2013-12-04 08:00 | 2013-12-22 17:00 | 2013-12-04 08:00 | 2013-12-22 17:00 | 2014-02-04 08:00 | 2014-02-22 17:00 |  | PT_Normal |  |  |  |  | Pgpx8Q4oS9etjirv8N08Iw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30230 | N | N | 20 | ROOF |  | 125516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 99.6 | LABOR- SUBCONTRACTOR
%R | 504691 | 6359 | 125518 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1PLRF4350 | Installation of Rain water Pipes | 8178 | 208 | 80 | 120 | 0 | 67.2 | 67.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-15 08:00 | 2014-03-03 17:00 |  | 2014-01-14 08:00 | 2014-01-30 17:00 | 2014-01-14 08:00 | 2014-01-30 17:00 | 2014-01-14 08:00 | 2014-01-30 17:00 | 2014-02-15 08:00 | 2014-03-03 17:00 |  | PT_Normal |  |  |  |  | FWLNrgJRQo+mSbZpuMI0Ag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30230 | N | N | 20 | ROOF |  | 125516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504692 | 6359 | 125518 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 8 | 0 | 200 | 0 | 302.4 | 302.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-20 08:00 | 2014-03-20 17:00 |  | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | HyRvm6hUSSe3P9gVgJNNPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30230 | N | N | 20 | ROOF |  | 125516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 151.2 | LABOR- SUBCONTRACTOR
%R | 504693 | 6359 | 125519 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 0 | 0 | 128 | 0 | 67.2 | 67.2 | 128 | 0 | 0 | 0 |  |  |  | 2013-06-03 08:00 | 2013-06-20 17:00 |  | 2013-06-03 08:00 | 2013-06-20 17:00 | 2013-06-03 08:00 | 2013-06-20 17:00 | 2013-06-03 08:00 | 2013-06-20 17:00 | 2013-06-03 08:00 | 2013-06-20 17:00 |  | PT_Normal |  |  |  |  | gFd00ODtRluyvvsho/VXaQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30210 | N | N | 10 | GROUND FLOOR |  | 125516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504694 | 6359 | 125519 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 144 | 0 | 144 | 0 | 386.4 | 386.4 | 144 | 0 | 0 | 0 |  |  |  | 2013-10-20 08:00 | 2013-11-09 17:00 |  | 2013-09-26 08:00 | 2013-10-16 17:00 | 2013-09-26 08:00 | 2013-10-16 17:00 | 2013-09-26 08:00 | 2013-10-16 17:00 | 2013-10-20 08:00 | 2013-11-09 17:00 |  | PT_Normal |  |  |  |  | tl4teKs1RTWsz7DKZANoXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30210 | N | N | 10 | GROUND FLOOR |  | 125516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 386.4 | LABOR- SUBCONTRACTOR
%R | 504695 | 6359 | 125519 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1PLGF4310 | Installation of Drainage pipes &testing | 8178 | 312 | 168 | 144 | 0 | 160.8 | 160.8 | 144 | 0 | 0 | 0 |  |  |  | 2013-11-13 08:00 | 2013-12-03 17:00 |  | 2013-09-26 08:00 | 2013-10-16 17:00 | 2013-09-26 08:00 | 2013-10-16 17:00 | 2013-09-26 08:00 | 2013-10-16 17:00 | 2013-11-13 08:00 | 2013-12-03 17:00 |  | PT_Normal |  |  |  |  | 9AQ3m6YOSCycsw6r72eRhw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30210 | N | N | 10 | GROUND FLOOR |  | 125516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 160.8 | LABOR- SUBCONTRACTOR
%R | 504696 | 6359 | 125519 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1PLGF4315 | Sanitary Fittings & Accessories | 8178 | 360 | 0 | 160 | 0 | 117.6 | 117.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-20 08:00 | 2014-03-15 17:00 |  | 2013-12-29 08:00 | 2014-01-20 17:00 | 2013-12-29 08:00 | 2014-01-20 17:00 | 2013-12-29 08:00 | 2014-01-20 17:00 | 2014-02-20 08:00 | 2014-03-15 17:00 |  | PT_Normal |  |  |  |  | vxR3HPGmRiWiOnWb9PosrA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30210 | N | N | 10 | GROUND FLOOR |  | 125516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 117.6 | LABOR- SUBCONTRACTOR
%R | 504697 | 6359 | 125519 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1PLGF4320 | Installation of Water Heater | 8178 | 360 | 80 | 120 | 0 | 117.6 | 117.6 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-04 08:00 | 2014-03-20 17:00 |  | 2014-01-09 08:00 | 2014-01-26 17:00 | 2014-01-09 08:00 | 2014-01-26 17:00 | 2014-01-09 08:00 | 2014-01-26 17:00 | 2014-03-04 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | 5Do/WZY3T8i8SSo62enRYw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30210 | N | N | 10 | GROUND FLOOR |  | 125516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 117.6 | LABOR- SUBCONTRACTOR
%R | 504698 | 6359 | 125521 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 216 | 16 | 200 | 0 | 1075.2 | 1075.2 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-20 08:00 | 2013-11-17 17:00 |  | 2013-09-16 08:00 | 2013-10-14 17:00 | 2013-09-16 08:00 | 2013-10-14 17:00 | 2013-09-16 08:00 | 2013-10-14 17:00 | 2013-10-20 08:00 | 2013-11-17 17:00 |  | PT_Normal |  |  |  |  | UjrFcLLKTY+QGvU0zgSZEQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30170 | N | N | 10 | GROUND FLOOR |  | 125520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1075.2 | LABOR- SUBCONTRACTOR
%R | 504699 | 6359 | 125521 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ELGF4005 | Cable tray & trunking installation | 8178 | 344 | 0 | 160 | 0 | 1159.2 | 1159.2 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-21 08:00 | 2013-12-14 17:00 |  | 2013-09-30 08:00 | 2013-10-24 17:00 | 2013-09-30 08:00 | 2013-10-24 17:00 | 2013-09-30 08:00 | 2013-10-24 17:00 | 2013-11-21 08:00 | 2013-12-14 17:00 |  | PT_Normal |  |  |  |  | T4K8jQn/TLq0ySwsjlvmPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30170 | N | N | 10 | GROUND FLOOR |  | 125520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1159.2 | LABOR- SUBCONTRACTOR
%R | 504700 | 6359 | 125521 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ELGF4010 | Installation of wiring & Main Cabling | 8178 | 344 | 200 | 200 | 0 | 267.6 | 267.6 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-30 08:00 | 2013-12-29 17:00 |  | 2013-10-08 08:00 | 2013-11-07 17:00 | 2013-10-08 08:00 | 2013-11-07 17:00 | 2013-10-08 08:00 | 2013-11-07 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 |  | PT_Normal |  |  |  |  | fsWoKT1UTVOhSjK0/nDtrA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30170 | N | N | 10 | GROUND FLOOR |  | 125520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 267.6 | LABOR- SUBCONTRACTOR
%R | 504701 | 6359 | 125521 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 144 | 0 | 160 | 0 | 198.8 | 198.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-07 08:00 | 2014-01-29 17:00 |  | 2013-12-16 08:00 | 2014-01-08 17:00 | 2013-12-16 08:00 | 2014-01-08 17:00 | 2013-12-16 08:00 | 2014-01-08 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | 5ItYebZoQhaVVDNALVhjAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30170 | N | N | 10 | GROUND FLOOR |  | 125520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 198.8 | LABOR- SUBCONTRACTOR
%R | 504702 | 6359 | 125521 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 200 | 0 | 200 | 0 | 1444.8 | 1444.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-27 08:00 | 2014-02-25 17:00 |  | 2013-12-29 08:00 | 2014-01-26 17:00 | 2013-12-29 08:00 | 2014-01-26 17:00 | 2013-12-29 08:00 | 2014-01-26 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 |  | PT_Normal |  |  |  |  | rICt95e7QT+ebLkVI3tBvA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30170 | N | N | 10 | GROUND FLOOR |  | 125520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1444.8 | LABOR- SUBCONTRACTOR
%R | 504703 | 6359 | 125521 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 240 | 0 | 200 | 0 | 940.8 | 940.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-15 08:00 | 2014-02-13 17:00 |  | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 |  | PT_Normal |  |  |  |  | 3HH681nST9+bo7SbqrCjMQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30170 | N | N | 10 | GROUND FLOOR |  | 125520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 940.8 | LABOR- SUBCONTRACTOR
%R | 504704 | 6359 | 125521 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ELGF4030 | Installation of Telephone System | 8178 | 144 | 40 | 160 | 0 | 458 | 458 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-19 08:00 | 2014-02-10 17:00 |  | 2013-12-29 08:00 | 2014-01-20 17:00 | 2013-12-29 08:00 | 2014-01-20 17:00 | 2013-12-29 08:00 | 2014-01-20 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | bvFdpAxLQzaEghBvlbn45Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30170 | N | N | 10 | GROUND FLOOR |  | 125520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 458 | LABOR- SUBCONTRACTOR
%R | 504705 | 6359 | 125522 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ELRF4070 | Installation of Isolator | 8178 | 8 | 0 | 144 | 0 | 361.2 | 361.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-17 08:00 | 2014-03-09 17:00 |  | 2014-02-16 08:00 | 2014-03-08 17:00 | 2014-02-16 08:00 | 2014-03-08 17:00 | 2014-02-16 08:00 | 2014-03-08 17:00 | 2014-02-17 08:00 | 2014-03-09 17:00 |  | PT_Normal |  |  |  |  | 14CdpvISRl6GOgiv1z2xUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30190 | N | N | 20 | ROOF |  | 125520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 361.2 | LABOR- SUBCONTRACTOR
%R | 504706 | 6359 | 125522 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ELRF4075 | Installation of TV Dish Antenna | 8178 | 8 | 8 | 184 | 0 | 646.8 | 646.8 | 184 | 0 | 0 | 0 |  |  |  | 2014-02-23 08:00 | 2014-03-20 17:00 |  | 2014-02-22 08:00 | 2014-03-19 17:00 | 2014-02-22 08:00 | 2014-03-19 17:00 | 2014-02-22 08:00 | 2014-03-19 17:00 | 2014-02-23 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | Acua2w6DR2iatEQqPRe0Hw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30190 | N | N | 20 | ROOF |  | 125520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 646.8 | LABOR- SUBCONTRACTOR
%R | 504707 | 6359 | 125523 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 80 | 16 | 200 | 0 | 1075.2 | 1075.2 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-11 08:00 | 2013-12-09 17:00 |  | 2013-10-30 08:00 | 2013-11-27 17:00 | 2013-10-30 08:00 | 2013-11-27 17:00 | 2013-10-30 08:00 | 2013-11-27 17:00 | 2013-11-11 08:00 | 2013-12-09 17:00 |  | PT_Normal |  |  |  |  | aV8E5Og3QA+OaKDzeFCbtA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30180 | N | N | 15 | FIRST FLOORS |  | 125520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1075.2 | LABOR- SUBCONTRACTOR
%R | 504708 | 6359 | 125523 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ELFF4040 | Cable tray & trunking installation | 8178 | 208 | 0 | 160 | 0 | 1159.2 | 1159.2 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-14 08:00 | 2014-01-06 17:00 |  | 2013-11-13 08:00 | 2013-12-05 17:00 | 2013-11-13 08:00 | 2013-12-05 17:00 | 2013-11-13 08:00 | 2013-12-05 17:00 | 2013-12-14 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | ZaXCwWBETVyQk+eQZhjCZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30180 | N | N | 15 | FIRST FLOORS |  | 125520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1159.2 | LABOR- SUBCONTRACTOR
%R | 504709 | 6359 | 125523 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 8 | 0 | 160 | 0 | 198.8 | 198.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-27 08:00 | 2014-02-19 17:00 |  | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-01-27 08:00 | 2014-02-19 17:00 |  | PT_Normal |  |  |  |  | UatJHqx4RUaN3og7y9g3yA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30180 | N | N | 15 | FIRST FLOORS |  | 125520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 198.8 | LABOR- SUBCONTRACTOR
%R | 504710 | 6359 | 125523 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 8 | 0 | 200 | 0 | 1444.8 | 1444.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-02 08:00 | 2014-03-03 17:00 |  | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-02 08:00 | 2014-03-03 17:00 |  | PT_Normal |  |  |  |  | AvpVwuSkS6+KatcAq6FTmw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30180 | N | N | 15 | FIRST FLOORS |  | 125520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 722.4 | LABOR- SUBCONTRACTOR
%R | 504711 | 6359 | 125523 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 16 | 8 | 200 | 0 | 890.4 | 890.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-21 08:00 | 2014-02-19 17:00 |  | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 |  | PT_Normal |  |  |  |  | u/dACz+/RXCPs23KqDzDBw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30180 | N | N | 15 | FIRST FLOORS |  | 125520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 890.4 | LABOR- SUBCONTRACTOR
%R | 504712 | 6359 | 125523 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ELFF4050 | Installation of Telephone System | 8178 | 96 | 88 | 200 | 0 | 400.4 | 400.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-03-01 17:00 |  | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | S58bmkeGTQmQUno1jUNgtg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30180 | N | N | 15 | FIRST FLOORS |  | 125520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 400.4 | LABOR- SUBCONTRACTOR
%R | 504713 | 6359 | 125523 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ELFF4045 | Installation of wiring & Main Cabling | 8178 | 208 | 0 | 200 | 0 | 267.6 | 267.6 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-23 08:00 | 2014-01-20 17:00 |  | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-12-23 08:00 | 2014-01-20 17:00 |  | PT_Normal |  |  |  |  | JUa5TWhgSnGPIGr2D996Ow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30180 | N | N | 15 | FIRST FLOORS |  | 125520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11; period 2: 2013-AP12 |  | 133.8 | LABOR- SUBCONTRACTOR
%R | 504714 | 6359 | 125526 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STGF2000 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 4046 | 4046 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-07-27 17:00 |  | 2013-06-29 08:00 | 2013-07-27 17:00 | 2013-06-29 08:00 | 2013-07-27 17:00 | 2013-06-29 08:00 | 2013-07-27 17:00 | 2013-06-29 08:00 | 2013-07-27 17:00 |  | PT_Normal |  |  |  |  | xoOcbqq3QBehoyYfi9iGcw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30040 | N | N | 10 | GROUND FLOOR |  | 125525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 4046 | STEEL FIXERS SK
%R | 504715 | 6359 | 125526 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STGF2005 | Column-Concrete | 8167 | 0 | 0 | 192 | 0 | 255.5 | 255.5 | 192 | 0 | 0 | 0 |  |  |  | 2013-07-07 08:00 | 2013-08-03 17:00 |  | 2013-07-07 08:00 | 2013-08-03 17:00 | 2013-07-07 08:00 | 2013-08-03 17:00 | 2013-07-07 08:00 | 2013-08-03 17:00 | 2013-07-07 08:00 | 2013-08-03 17:00 |  | PT_Normal |  |  |  |  | 4bYuaR89SPu0ChRZr33cHA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30040 | N | N | 10 | GROUND FLOOR |  | 125525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 255.5 | CONCRETE MASON SK
%R | 504716 | 6359 | 125526 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 17116.75 | 17116.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-22 08:00 | 2013-08-22 17:00 |  | 2013-07-22 08:00 | 2013-08-22 17:00 | 2013-07-22 08:00 | 2013-08-22 17:00 | 2013-07-22 08:00 | 2013-08-22 17:00 | 2013-07-22 08:00 | 2013-08-22 17:00 |  | PT_Normal |  |  |  |  | xGBWgHUYRJqYUlBq2p4qNw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30040 | N | N | 10 | GROUND FLOOR |  | 125525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 8558.375 | STEEL FIXERS SK
%R | 504717 | 6359 | 125526 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 0 | 0 | 120 | 0 | 1295 | 1295 | 120 | 0 | 0 | 0 |  |  |  | 2013-08-06 08:00 | 2013-08-26 17:00 |  | 2013-08-06 08:00 | 2013-08-26 17:00 | 2013-08-06 08:00 | 2013-08-26 17:00 | 2013-08-06 08:00 | 2013-08-26 17:00 | 2013-08-06 08:00 | 2013-08-26 17:00 |  | PT_Normal |  |  |  |  | Kwajoa9aRjyARq9N5SWyOw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30040 | N | N | 10 | GROUND FLOOR |  | 125525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 1295 | CONCRETE MASON SK
%R | 504718 | 6359 | 125527 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STRF2040 | Column-Rebar & Formwork | 8165 | 72 | 0 | 144 | 0 | 1205.75 | 1205.75 | 144 | 0 | 0 | 0 |  |  |  | 2013-10-05 08:00 | 2013-10-27 17:00 |  | 2013-09-24 08:00 | 2013-10-14 17:00 | 2013-09-24 08:00 | 2013-10-14 17:00 | 2013-09-24 08:00 | 2013-10-14 17:00 | 2013-10-05 08:00 | 2013-10-27 17:00 |  | PT_Normal |  |  |  |  | cy1OhnSwSgmpLFtshDfyfw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30060 | N | N | 20 | ROOF |  | 125525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1205.75 | STEEL FIXERS SK
%R | 504719 | 6359 | 125527 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STRF2045 | Column-Concrete | 8167 | 72 | 0 | 136 | 0 | 52.5 | 52.5 | 136 | 0 | 0 | 0 |  |  |  | 2013-10-09 08:00 | 2013-10-30 17:00 |  | 2013-09-29 08:00 | 2013-10-20 17:00 | 2013-09-29 08:00 | 2013-10-20 17:00 | 2013-09-29 08:00 | 2013-10-20 17:00 | 2013-10-09 08:00 | 2013-10-30 17:00 |  | PT_Normal |  |  |  |  | IstUCqxlTcyPT5741W2aKg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30060 | N | N | 20 | ROOF |  | 125525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 52.5 | CONCRETE MASON SK
%R | 504720 | 6359 | 125527 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STRF2050 | Slab-Rebar & Formwork - Head Room | 8165 | 72 | 0 | 160 | 0 | 2735.25 | 2735.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-10-13 08:00 | 2013-11-06 17:00 |  | 2013-10-02 08:00 | 2013-10-27 17:00 | 2013-10-02 08:00 | 2013-10-27 17:00 | 2013-10-02 08:00 | 2013-10-27 17:00 | 2013-10-13 08:00 | 2013-11-06 17:00 |  | PT_Normal |  |  |  |  | 6NXFHS8/TBSQQOzY5pJu6g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30060 | N | N | 20 | ROOF |  | 125525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 2735.25 | STEEL FIXERS SK
%R | 504721 | 6359 | 125527 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STRF2055 | Slab-Concrete-Head room | 8167 | 72 | 0 | 80 | 0 | 252 | 252 | 80 | 0 | 0 | 0 |  |  |  | 2013-10-29 08:00 | 2013-11-09 17:00 |  | 2013-10-16 08:00 | 2013-10-29 17:00 | 2013-10-16 08:00 | 2013-10-29 17:00 | 2013-10-16 08:00 | 2013-10-29 17:00 | 2013-10-29 08:00 | 2013-11-09 17:00 |  | PT_Normal |  |  |  |  | FaXkfzZAS1qjOY291Q3aMw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30060 | N | N | 20 | ROOF |  | 125525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 252 | CONCRETE MASON SK
%R | 504722 | 6359 | 125527 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STRF2060 | Construction of Parapets | 8168 | 72 | 0 | 200 | 0 | 2200 | 2200 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-31 08:00 | 2013-11-28 17:00 |  | 2013-10-21 08:00 | 2013-11-18 17:00 | 2013-10-21 08:00 | 2013-11-18 17:00 | 2013-10-21 08:00 | 2013-11-18 17:00 | 2013-10-31 08:00 | 2013-11-28 17:00 |  | PT_Normal |  |  |  |  | AQak22aVTd6GF78W9xXp9A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30060 | N | N | 20 | ROOF |  | 125525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 2200 | BLOCK MASON SK
%R | 504723 | 6359 | 125527 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STRF2065 | Construction of up stands/Plinth | 8165 | 72 | 0 | 200 | 0 | 554.75 | 554.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-06 08:00 | 2013-12-04 17:00 |  | 2013-10-27 08:00 | 2013-11-24 17:00 | 2013-10-27 08:00 | 2013-11-24 17:00 | 2013-10-27 08:00 | 2013-11-24 17:00 | 2013-11-06 08:00 | 2013-12-04 17:00 |  | PT_Normal |  |  |  |  | ZuPDaSJ8T42IbY/ZoXBsYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30060 | N | N | 20 | ROOF |  | 125525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 554.75 | STEEL FIXERS SK
%R | 504724 | 6359 | 125528 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STFF2020 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 3580.5 | 3580.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-08 08:00 | 2013-09-09 17:00 |  | 2013-08-08 08:00 | 2013-09-09 17:00 | 2013-08-08 08:00 | 2013-09-09 17:00 | 2013-08-08 08:00 | 2013-09-09 17:00 | 2013-08-08 08:00 | 2013-09-09 17:00 |  | PT_Normal |  |  |  |  | x/ICCsBzTsG5qjjEbXnTDQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30050 | N | N | 15 | FIRST FLOORS |  | 125525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 1790.25 | STEEL FIXERS SK
%R | 504725 | 6359 | 125528 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STFF2025 | Column-Concrete | 8167 | 0 | 0 | 192 | 0 | 224 | 224 | 192 | 0 | 0 | 0 |  |  |  | 2013-08-21 08:00 | 2013-09-17 17:00 |  | 2013-08-21 08:00 | 2013-09-17 17:00 | 2013-08-21 08:00 | 2013-09-17 17:00 | 2013-08-21 08:00 | 2013-09-17 17:00 | 2013-08-21 08:00 | 2013-09-17 17:00 |  | PT_Normal |  |  |  |  | PGGttB/3SEminum+PpkFVA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30050 | N | N | 15 | FIRST FLOORS |  | 125525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 224 | CONCRETE MASON SK
%R | 504726 | 6359 | 125528 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 16119.25 | 16119.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-05 08:00 | 2013-10-03 17:00 |  | 2013-09-05 08:00 | 2013-10-03 17:00 | 2013-09-05 08:00 | 2013-10-03 17:00 | 2013-09-05 08:00 | 2013-10-03 17:00 | 2013-09-05 08:00 | 2013-10-03 17:00 |  | PT_Normal |  |  |  |  | vVHNz2oURoe+qIUoXTv2IQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30050 | N | N | 15 | FIRST FLOORS |  | 125525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 16119.25 | STEEL FIXERS SK
%R | 504727 | 6359 | 125528 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 0 | 0 | 120 | 0 | 1141 | 1141 | 120 | 0 | 0 | 0 |  |  |  | 2013-09-21 08:00 | 2013-10-07 17:00 |  | 2013-09-21 08:00 | 2013-10-07 17:00 | 2013-09-21 08:00 | 2013-10-07 17:00 | 2013-09-21 08:00 | 2013-10-07 17:00 | 2013-09-21 08:00 | 2013-10-07 17:00 |  | PT_Normal |  |  |  |  | ojfwdBfwRRSq1wZdgM7brg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30050 | N | N | 15 | FIRST FLOORS |  | 125525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1141 | CONCRETE MASON SK
%R | 504728 | 6359 | 125530 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STUG1000 | Footing Excavation | 8177 | 0 | 0 | 200 | 0 | 1114 | 1114 | 200 | 524 | 0 | 524 |  |  |  | 2013-02-14 08:00 | 2013-03-14 17:00 |  | 2013-02-14 08:00 | 2013-03-14 17:00 | 2013-02-14 08:00 | 2013-03-14 17:00 | 2013-02-14 08:00 | 2013-03-14 17:00 | 2013-02-14 08:00 | 2013-03-14 17:00 |  | PT_Normal |  |  |  |  | 0PdlGWOaR++FNjfK8KMlvA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30020 | N | N | 10 | UPTO GRADE SLAB |  | 125529 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 557 | LABOR - CIVIL
%R | 504729 | 6359 | 125530 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STUG1005 | Footing Antitermite | 8178 | 0 | 0 | 184 | 0 | 1584 | 1584 | 184 | 0 | 0 | 0 |  |  |  | 2013-02-26 08:00 | 2013-03-24 17:00 |  | 2013-02-26 08:00 | 2013-03-24 17:00 | 2013-02-26 08:00 | 2013-03-24 17:00 | 2013-02-26 08:00 | 2013-03-24 17:00 | 2013-02-26 08:00 | 2013-03-24 17:00 |  | PT_Normal |  |  |  |  | FVPT7lCWTGGFmYST8on6Yw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30020 | N | N | 10 | UPTO GRADE SLAB |  | 125529 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 1584 | LABOR- SUBCONTRACTOR
%R | 504730 | 6359 | 125530 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STUG1010 | Footing Blinding | 8163 | 0 | 0 | 184 | 0 | 794.5 | 794.5 | 184 | 0 | 0 | 0 |  |  |  | 2013-03-02 08:00 | 2013-03-27 17:00 |  | 2013-03-02 08:00 | 2013-03-27 17:00 | 2013-03-02 08:00 | 2013-03-27 17:00 | 2013-03-02 08:00 | 2013-03-27 17:00 | 2013-03-02 08:00 | 2013-03-27 17:00 |  | PT_Normal |  |  |  |  | zHrycdArRWOpEeMHqd9xBw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30020 | N | N | 10 | UPTO GRADE SLAB |  | 125529 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 794.5 | BLINDING MASON SK
%R | 504731 | 6359 | 125530 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STUG1015 | Footing Waterproofing & Screed | 8164 | 0 | 0 | 200 | 0 | 574.75 | 574.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-03-07 08:00 | 2013-04-04 17:00 |  | 2013-03-07 08:00 | 2013-04-04 17:00 | 2013-03-07 08:00 | 2013-04-04 17:00 | 2013-03-07 08:00 | 2013-04-04 17:00 | 2013-03-07 08:00 | 2013-04-04 17:00 |  | PT_Normal |  |  |  |  | OFxaBZSxSAa6lKqV8X8bsw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30020 | N | N | 10 | UPTO GRADE SLAB |  | 125529 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 574.75 | SCREED MASON SK
%R | 504732 | 6359 | 125530 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STUG1020 | Construction of foundations | 8165 | 0 | 0 | 160 | 0 | 7778.75 | 7778.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-03-23 08:00 | 2013-04-14 17:00 |  | 2013-03-23 08:00 | 2013-04-14 17:00 | 2013-03-23 08:00 | 2013-04-14 17:00 | 2013-03-23 08:00 | 2013-04-14 17:00 | 2013-03-23 08:00 | 2013-04-14 17:00 |  | PT_Normal |  |  |  |  | TKLmua6yT/eI/kq+1Os2IQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30020 | N | N | 10 | UPTO GRADE SLAB |  | 125529 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 7778.75 | STEEL FIXERS SK
%R | 504733 | 6359 | 125530 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STUG1025 | Construction of neck of columns | 8165 | 0 | 0 | 200 | 0 | 1606.5 | 1606.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-04-01 08:00 | 2013-04-29 17:00 |  | 2013-04-01 08:00 | 2013-04-29 17:00 | 2013-04-01 08:00 | 2013-04-29 17:00 | 2013-04-01 08:00 | 2013-04-29 17:00 | 2013-04-01 08:00 | 2013-04-29 17:00 |  | PT_Normal |  |  |  |  | qgE37Y+4QV6lUjOhyezMSw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30020 | N | N | 10 | UPTO GRADE SLAB |  | 125529 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 1606.5 | STEEL FIXERS SK
%R | 504734 | 6359 | 125530 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STUG1030 | Waterproofing Footing & Neck Column | 8178 | 0 | 0 | 200 | 0 | 516 | 516 | 200 | 0 | 0 | 0 |  |  |  | 2013-04-10 08:00 | 2013-05-08 17:00 |  | 2013-04-10 08:00 | 2013-05-08 17:00 | 2013-04-10 08:00 | 2013-05-08 17:00 | 2013-04-10 08:00 | 2013-05-08 17:00 | 2013-04-10 08:00 | 2013-05-08 17:00 |  | PT_Normal |  |  |  |  | dUgTN0MASTW6gYbaKTw0cQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30020 | N | N | 10 | UPTO GRADE SLAB |  | 125529 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 516 | LABOR- SUBCONTRACTOR
%R | 504735 | 6359 | 125530 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 0 | 0 | 200 | 0 | 1041 | 1041 | 200 | 825 | 0 | 825 |  |  |  | 2013-04-24 08:00 | 2013-05-22 17:00 |  | 2013-04-24 08:00 | 2013-05-22 17:00 | 2013-04-24 08:00 | 2013-05-22 17:00 | 2013-04-24 08:00 | 2013-05-22 17:00 | 2013-04-24 08:00 | 2013-05-22 17:00 |  | PT_Normal |  |  |  |  | m+o+6kH/Tn+nUIM4E7qWrw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30020 | N | N | 10 | UPTO GRADE SLAB |  | 125529 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 1041 | LABOR - CIVIL
%R | 504736 | 6359 | 125530 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STUG1040 | Construction of Grade Beams | 8163 | 0 | 0 | 208 | 0 | 7568.75 | 7568.75 | 208 | 0 | 0 | 0 |  |  |  | 2013-05-11 08:00 | 2013-06-09 17:00 |  | 2013-05-11 08:00 | 2013-06-09 17:00 | 2013-05-11 08:00 | 2013-06-09 17:00 | 2013-05-11 08:00 | 2013-06-09 17:00 | 2013-05-11 08:00 | 2013-06-09 17:00 |  | PT_Normal |  |  |  |  | aGLlkalgT3SjZkYucnfyyA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30020 | N | N | 10 | UPTO GRADE SLAB |  | 125529 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 7568.75 | BLINDING MASON SK
%R | 504737 | 6359 | 125530 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1STUG1045 | Construction of slab on grade | 8163 | 0 | 0 | 200 | 0 | 4422 | 4422 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-12 08:00 | 2013-07-10 17:00 |  | 2013-06-12 08:00 | 2013-07-10 17:00 | 2013-06-12 08:00 | 2013-07-10 17:00 | 2013-06-12 08:00 | 2013-07-10 17:00 | 2013-06-12 08:00 | 2013-07-10 17:00 |  | PT_Normal |  |  |  |  | mLvj0VZoSa2jPqHqsQu/Jg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30020 | N | N | 10 | UPTO GRADE SLAB |  | 125529 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 4422 | BLINDING MASON SK
%R | 504738 | 6359 | 125532 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1HDEX5090 | kerb works | 8173 | 128 | 0 | 160 | 0 | 308 | 308 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-19 08:00 | 2014-02-10 17:00 |  | 2013-12-31 08:00 | 2014-01-22 17:00 | 2013-12-31 08:00 | 2014-01-22 17:00 | 2013-12-31 08:00 | 2014-01-22 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | qa71Lo6KQOKgT8kJyNh5IQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30320 | N | N | 20 | HARD LANDSCAPING |  | 125531 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 308 | KERBSTONE MASON SK
%R | 504739 | 6359 | 125532 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1HDEX5095 | Cobble Stone Works | 8170 | 128 | 0 | 160 | 0 | 178 | 178 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-02-23 17:00 |  | 2014-01-12 08:00 | 2014-02-03 17:00 | 2014-01-12 08:00 | 2014-02-03 17:00 | 2014-01-12 08:00 | 2014-02-03 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | U7xvXi6aQ46wL1DLfzeJSA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30320 | N | N | 20 | HARD LANDSCAPING |  | 125531 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 178 | TILE MASON SK
%R | 504740 | 6359 | 125532 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1HDEX5100 | Interlock works | 8174 | 128 | 0 | 160 | 0 | 210 | 210 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-03-02 17:00 |  | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-02-06 08:00 | 2014-03-02 17:00 |  | PT_Normal |  |  |  |  | d0WUS5fuTc2QBxSCY4jAOQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30320 | N | N | 20 | HARD LANDSCAPING |  | 125531 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 210 | INTERLOCK MASON SK
%R | 504741 | 6359 | 125533 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1MSEX5025 | SS.Handrails and Balustrades | 8178 | 176 | 88 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-01 08:00 | 2014-02-24 17:00 |  | 2014-01-06 08:00 | 2014-01-28 17:00 | 2014-01-06 08:00 | 2014-01-28 17:00 | 2014-01-06 08:00 | 2014-01-28 17:00 | 2014-02-01 08:00 | 2014-02-24 17:00 |  | PT_Normal |  |  |  |  | kV8VJRuVQ7Cenkog++M/Og |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30300 | N | N | 10 | MISCELLANEOUS |  | 125531 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 56 | LABOR- SUBCONTRACTOR
%R | 504742 | 6359 | 125533 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1MSEX5015 | Construction of grease Trap | 8178 | 264 | 192 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-15 08:00 | 2014-03-09 17:00 |  | 2014-01-06 08:00 | 2014-01-28 17:00 | 2014-01-06 08:00 | 2014-01-28 17:00 | 2014-01-06 08:00 | 2014-01-28 17:00 | 2014-02-15 08:00 | 2014-03-09 17:00 |  | PT_Normal |  |  |  |  | 6dpmr3g8TLS9zJ+qzELIvg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30300 | N | N | 10 | MISCELLANEOUS |  | 125531 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 56 | LABOR- SUBCONTRACTOR
%R | 504743 | 6359 | 125533 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1MSEX5000 | Construction of Manholes | 8172 | 104 | 0 | 200 | 0 | 462 | 462 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-17 08:00 | 2014-01-15 17:00 |  | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | 8FAKGNMKRA2POYR9lcE/MQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30300 | N | N | 10 | MISCELLANEOUS |  | 125531 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 462 | MANHOLES SK
%R | 504744 | 6359 | 125533 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1MSEX5005 | Construction of Soak pit, Chambers | 8172 | 104 | 0 | 200 | 0 | 154 | 154 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-01 08:00 | 2014-01-29 17:00 |  | 2013-12-16 08:00 | 2014-01-14 17:00 | 2013-12-16 08:00 | 2014-01-14 17:00 | 2013-12-16 08:00 | 2014-01-14 17:00 | 2014-01-01 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | fBVGet5lRGW2ofxAv1YBOg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30300 | N | N | 10 | MISCELLANEOUS |  | 125531 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 154 | MANHOLES SK
%R | 504745 | 6359 | 125533 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1MSEX5010 | Telephone cable laying | 8177 | 104 | 8 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-03-01 17:00 |  | 2014-01-15 08:00 | 2014-02-13 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | nwrsj6ZXRPWn7mnp5OvyQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30300 | N | N | 10 | MISCELLANEOUS |  | 125531 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 500 | LABOR - CIVIL
%R | 504746 | 6359 | 125533 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 824 | 0 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-05 08:00 | 2014-08-05 17:00 |  | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-07-05 08:00 | 2014-08-05 17:00 |  | PT_Normal |  |  |  |  | 1hyC2d9uQ664aXTT41FYmg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 16:44 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30300 | N | N | 10 | MISCELLANEOUS |  | 125531 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 400 | LABOR- SUBCONTRACTOR
%R | 504747 | 6359 | 125533 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1MSEX5020 | Construction Entrance Ramp | 8164 | 128 | 0 | 200 | 0 | 578 | 578 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-05 08:00 | 2014-02-02 17:00 |  | 2013-12-16 08:00 | 2014-01-14 17:00 | 2013-12-16 08:00 | 2014-01-14 17:00 | 2013-12-16 08:00 | 2014-01-14 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | 2yphswiESCW0O/FaKWH5rg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30300 | N | N | 10 | MISCELLANEOUS |  | 125531 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 578 | SCREED MASON SK
%R | 504748 | 6359 | 125534 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1SLEX5105 | Laying of Grass/ green area | 8178 | 128 | 0 | 200 | 0 | 2408 | 2408 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-03-13 17:00 |  | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 |  | PT_Normal |  |  |  |  | p1kXAWZoSeeWA66u9PEqcw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30330 | N | N | 25 | SOFT LANDSCAPING |  | 125531 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 2408 | LABOR- SUBCONTRACTOR
%R | 504749 | 6359 | 125534 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1SLEX5110 | Laying of Palm tree | 8178 | 128 | 128 | 200 | 0 | 154 | 154 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-20 08:00 | 2014-03-20 17:00 |  | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | eTobxUZ/ROC4fecQW/vD9w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30330 | N | N | 25 | SOFT LANDSCAPING |  | 125531 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 77 | LABOR- SUBCONTRACTOR
%R | 504750 | 6359 | 125535 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1WEEX5030 | Excavation | 8177 | 104 | 0 | 160 | 0 | 64 | 64 | 160 | 40 | 0 | 40 |  |  |  | 2014-01-08 08:00 | 2014-01-30 17:00 |  | 2013-12-24 08:00 | 2014-01-15 17:00 | 2013-12-24 08:00 | 2014-01-15 17:00 | 2013-12-24 08:00 | 2014-01-15 17:00 | 2014-01-08 08:00 | 2014-01-30 17:00 |  | PT_Normal |  |  |  |  | sulrMOH6TL+ULcgxaTe09g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30310 | N | N | 15 | WATER TANK ENCLOSURE |  | 125531 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 64 | LABOR - CIVIL
%R | 504751 | 6359 | 125535 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1WEEX5035 | Construction of Raft | 8165 | 88 | 0 | 200 | 0 | 742 | 742 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-02-12 17:00 |  | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 |  | PT_Normal |  |  |  |  | hidqALO7Re6u+erRKDZ03w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30310 | N | N | 15 | WATER TANK ENCLOSURE |  | 125531 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 742 | STEEL FIXERS SK
%R | 504752 | 6359 | 125535 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1WEEX5040 | Block works & Plastering | 8168 | 88 | 0 | 200 | 0 | 448 | 448 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-23 08:00 | 2014-02-22 17:00 |  | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-23 08:00 | 2014-02-22 17:00 |  | PT_Normal |  |  |  |  | VwtCqPdSRECPyDrEnqTfmQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30310 | N | N | 15 | WATER TANK ENCLOSURE |  | 125531 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 448 | BLOCK MASON SK
%R | 504753 | 6359 | 125535 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1WEEX5045 | Flooring & Painting | 8178 | 88 | 0 | 200 | 0 | 210 | 210 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-03-01 17:00 |  | 2014-01-18 08:00 | 2014-02-16 17:00 | 2014-01-18 08:00 | 2014-02-16 17:00 | 2014-01-18 08:00 | 2014-02-16 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | wGeanKiESgWpJ/e8RfQu4g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30310 | N | N | 15 | WATER TANK ENCLOSURE |  | 125531 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 210 | LABOR- SUBCONTRACTOR
%R | 504754 | 6359 | 125535 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1WEEX5050 | Installation of Steel Gate | 8178 | 88 | 8 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-03-08 17:00 |  | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | hvrVFP71Tia0FKgj2FgCCA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30310 | N | N | 15 | WATER TANK ENCLOSURE |  | 125531 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 56 | LABOR- SUBCONTRACTOR
%R | 504755 | 6359 | 125535 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 80 | 0 | 200 | 0 | 294 | 294 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-03-13 17:00 |  | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 |  | PT_Normal |  |  |  |  | 5hnO9nFXRj6oPuTTvDW1dA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30310 | N | N | 15 | WATER TANK ENCLOSURE |  | 125531 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 147 | LABOR- SUBCONTRACTOR
%R | 504756 | 6359 | 125535 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 72 | 0 | 200 | 0 | 186.4 | 186.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-20 08:00 | 2014-03-20 17:00 |  | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | 1hV7c7pGQe+Hx6p36rPNtg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30310 | N | N | 15 | WATER TANK ENCLOSURE |  | 125531 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 93.2 | LABOR- SUBCONTRACTOR
%R | 504757 | 6359 | 125536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8177 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-19 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | BHNnG86/T5y+Be912ZXndg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30340 | N | N | 30 | TESTING AND COMMISSIONING |  | 125502 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 3000 | LABOR - CIVIL
%R | 504758 | 6359 | 125536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ACTC8000 | Pre-Commissioning & Testing of AC Works | 8177 | 0 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-19 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | oc9w1Uj/RZiAAqfpsLuzVQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30340 | N | N | 30 | TESTING AND COMMISSIONING |  | 125502 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1500 | LABOR - CIVIL
%R | 504759 | 6359 | 125536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ1ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8177 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-19 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | /UbbgNRWT2Wmr4/ut7AKgg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30340 | N | N | 30 | TESTING AND COMMISSIONING |  | 125502 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 3000 | LABOR - CIVIL
%R | 504760 | 6359 | 125538 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | HvosgCaQT7as277S3jPgKQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31420 | N | N | 30 | TESTING AND COMMISSIONING |  | 125537 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 504761 | 6359 | 125538 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | oZfyFDPnSV2UJ3AYvakA0A |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31420 | N | N | 30 | TESTING AND COMMISSIONING |  | 125537 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 504762 | 6359 | 125538 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 0 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | yvsvEeKwRnCDrsAHcSVkyw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31420 | N | N | 30 | TESTING AND COMMISSIONING |  | 125537 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 504763 | 6359 | 125540 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4SLEX5105 | Laying of Grass/ green area | 8178 | 128 | 0 | 200 | 0 | 2744 | 2744 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-12 08:00 | 2014-06-09 17:00 |  | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 |  | PT_Normal |  |  |  |  | ceJ3bxhnTiOBGYyfT8gyzw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31410 | N | N | 25 | SOFT LANDSCAPING |  | 125539 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 2744 | LABOR- SUBCONTRACTOR
%R | 504764 | 6359 | 125540 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4SLEX5110 | Laying of Palm tree | 8178 | 128 | 128 | 200 | 0 | 168 | 168 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | Tw/2+3+ZTE+3ayauxQZlGg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31410 | N | N | 25 | SOFT LANDSCAPING |  | 125539 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 168 | LABOR- SUBCONTRACTOR
%R | 504765 | 6359 | 125541 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 760 | 24 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-13 08:00 | 2014-10-13 17:00 |  | 2014-05-21 08:00 | 2014-06-18 17:00 | 2014-05-21 08:00 | 2014-06-18 17:00 | 2014-05-21 08:00 | 2014-06-18 17:00 | 2014-09-13 08:00 | 2014-10-13 17:00 |  | PT_Normal |  |  |  |  | wTsTPbs+TMewyPORuI5iGw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 16:44 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31380 | N | N | 10 | MISCELLANEOUS |  | 125539 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 400 | LABOR- SUBCONTRACTOR
%R | 504766 | 6359 | 125541 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4MSEX5020 | Construction Entrance Ramp | 8164 | 128 | 0 | 200 | 0 | 656 | 656 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-03 08:00 | 2014-05-01 17:00 |  | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | nmUvLVbFRxq9GJFOjEeVMw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31380 | N | N | 10 | MISCELLANEOUS |  | 125539 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 656 | SCREED MASON SK
%R | 504767 | 6359 | 125541 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4MSEX5025 | SS.Handrails and Balustrades | 8178 | 152 | 0 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-24 08:00 | 2014-05-17 17:00 |  | 2014-04-02 08:00 | 2014-04-24 17:00 | 2014-04-02 08:00 | 2014-04-24 17:00 | 2014-04-02 08:00 | 2014-04-24 17:00 | 2014-04-24 08:00 | 2014-05-17 17:00 |  | PT_Normal |  |  |  |  | H9TA4N0qTpaTkZzOqTFIHA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31380 | N | N | 10 | MISCELLANEOUS |  | 125539 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 56 | LABOR- SUBCONTRACTOR
%R | 504768 | 6359 | 125541 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4MSEX5015 | Construction of grease Trap | 8178 | 64 | 0 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-30 17:00 |  | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | OS8okHxjRoyJ3sgPMIxM3g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31380 | N | N | 10 | MISCELLANEOUS |  | 125539 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 56 | LABOR- SUBCONTRACTOR
%R | 504769 | 6359 | 125541 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4MSEX5000 | Construction of Manholes | 8172 | 64 | 0 | 200 | 0 | 528 | 528 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-01 08:00 | 2014-03-02 17:00 |  | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 |  | PT_Normal |  |  |  |  | TE25ctYKTt6NOczGX/BprQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31380 | N | N | 10 | MISCELLANEOUS |  | 125539 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 528 | MANHOLES SK
%R | 504770 | 6359 | 125541 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4MSEX5005 | Construction of Soak pit, Chambers | 8172 | 64 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-16 17:00 |  | 2014-02-05 08:00 | 2014-03-06 17:00 | 2014-02-05 08:00 | 2014-03-06 17:00 | 2014-02-05 08:00 | 2014-03-06 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | 1UUYcsKHRb+09XMvC64zQA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31380 | N | N | 10 | MISCELLANEOUS |  | 125539 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 88 | MANHOLES SK
%R | 504771 | 6359 | 125541 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4MSEX5010 | Telephone cable laying | 8177 | 64 | 0 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-28 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | S67YtHjMStim7FBKg2lTkg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31380 | N | N | 10 | MISCELLANEOUS |  | 125539 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 500 | LABOR - CIVIL
%R | 504772 | 6359 | 125542 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4WEEX5030 | Excavation | 8177 | 184 | 0 | 160 | 0 | 64 | 64 | 160 | 40 | 0 | 40 |  |  |  | 2014-04-01 08:00 | 2014-04-23 17:00 |  | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-04-01 08:00 | 2014-04-23 17:00 |  | PT_Normal |  |  |  |  | PcwBzFCeQN2QNFdAScnf+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31390 | N | N | 15 | WATER TANK ENCLOSURE |  | 125539 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 64 | LABOR - CIVIL
%R | 504773 | 6359 | 125542 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4WEEX5035 | Construction of Raft | 8165 | 184 | 0 | 200 | 0 | 840 | 840 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-07 08:00 | 2014-05-05 17:00 |  | 2014-03-11 08:00 | 2014-04-08 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | KE7InL30SJu7a3xq/VkFWg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31390 | N | N | 15 | WATER TANK ENCLOSURE |  | 125539 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 840 | STEEL FIXERS SK
%R | 504774 | 6359 | 125542 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4WEEX5040 | Block works & Plastering | 8168 | 184 | 0 | 200 | 0 | 512 | 512 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-16 08:00 | 2014-05-14 17:00 |  | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 |  | PT_Normal |  |  |  |  | FUm56mv8SayFMxC3UMQdbw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31390 | N | N | 15 | WATER TANK ENCLOSURE |  | 125539 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 512 | BLOCK MASON SK
%R | 504775 | 6359 | 125542 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4WEEX5045 | Flooring & Painting | 8178 | 184 | 32 | 200 | 0 | 232 | 232 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-05-21 17:00 |  | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | wUZNQVA3RQGTiRAONZZpNw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31390 | N | N | 15 | WATER TANK ENCLOSURE |  | 125539 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 232 | LABOR- SUBCONTRACTOR
%R | 504776 | 6359 | 125542 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4WEEX5050 | Installation of Steel Gate | 8178 | 152 | 72 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-06 08:00 | 2014-05-28 17:00 |  | 2014-04-14 08:00 | 2014-05-06 17:00 | 2014-04-14 08:00 | 2014-05-06 17:00 | 2014-04-14 08:00 | 2014-05-06 17:00 | 2014-05-06 08:00 | 2014-05-28 17:00 |  | PT_Normal |  |  |  |  | rsnqdwkmRMebp8pc/3oy+Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31390 | N | N | 15 | WATER TANK ENCLOSURE |  | 125539 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 56 | LABOR- SUBCONTRACTOR
%R | 504777 | 6359 | 125542 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 80 | 0 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-12 08:00 | 2014-06-09 17:00 |  | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 |  | PT_Normal |  |  |  |  | xRjG2MrhSYSXlVQ8eN2VZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31390 | N | N | 15 | WATER TANK ENCLOSURE |  | 125539 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 336 | LABOR- SUBCONTRACTOR
%R | 504778 | 6359 | 125542 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 72 | 0 | 200 | 0 | 203.2 | 203.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-05-08 08:00 | 2014-06-05 17:00 | 2014-05-08 08:00 | 2014-06-05 17:00 | 2014-05-08 08:00 | 2014-06-05 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | TsulcQYFTDOkteDN0akdcA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31390 | N | N | 15 | WATER TANK ENCLOSURE |  | 125539 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 203.2 | LABOR- SUBCONTRACTOR
%R | 504779 | 6359 | 125543 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4HDEX5090 | kerb works | 8173 | 128 | 0 | 160 | 0 | 344 | 344 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-10 17:00 |  | 2014-03-30 08:00 | 2014-04-21 17:00 | 2014-03-30 08:00 | 2014-04-21 17:00 | 2014-03-30 08:00 | 2014-04-21 17:00 | 2014-04-17 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | 2dxD9vPRS22XSYbBKR1ETQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31400 | N | N | 20 | HARD LANDSCAPING |  | 125539 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 344 | KERBSTONE MASON SK
%R | 504780 | 6359 | 125543 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4HDEX5095 | Cobble Stone Works | 8170 | 128 | 0 | 160 | 0 | 200 | 200 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-21 17:00 |  | 2014-04-10 08:00 | 2014-05-03 17:00 | 2014-04-10 08:00 | 2014-05-03 17:00 | 2014-04-10 08:00 | 2014-05-03 17:00 | 2014-04-29 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | Q79wyYp7RzGTGHn8ZYsuOw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31400 | N | N | 20 | HARD LANDSCAPING |  | 125539 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 200 | TILE MASON SK
%R | 504781 | 6359 | 125543 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4HDEX5100 | Interlock works | 8174 | 128 | 0 | 160 | 0 | 232 | 232 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-06 08:00 | 2014-05-28 17:00 |  | 2014-04-17 08:00 | 2014-05-10 17:00 | 2014-04-17 08:00 | 2014-05-10 17:00 | 2014-04-17 08:00 | 2014-05-10 17:00 | 2014-05-06 08:00 | 2014-05-28 17:00 |  | PT_Normal |  |  |  |  | hRKB2q13S9mBl5F9RgBmRA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31400 | N | N | 20 | HARD LANDSCAPING |  | 125539 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 232 | INTERLOCK MASON SK
%R | 504782 | 6359 | 125546 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ACGF4600 | Installation AC Pipes | 8178 | 392 | 40 | 160 | 0 | 977.6 | 977.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-06 17:00 |  | 2014-01-15 08:00 | 2014-02-06 17:00 | 2014-01-15 08:00 | 2014-02-06 17:00 | 2014-01-15 08:00 | 2014-02-06 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | VluWQi0pQOuvenxbSmSOfQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31330 | N | N | 10 | GROUND FLOOR |  | 125545 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 977.6 | LABOR- SUBCONTRACTOR
%R | 504783 | 6359 | 125546 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ACGF4605 | Fixing of Ventilation Equipments | 8178 | 256 | 0 | 200 | 0 | 182.4 | 182.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-16 08:00 | 2014-05-14 17:00 |  | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 |  | PT_Normal |  |  |  |  | zfigNSquSTicD7VpIcPTUw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31330 | N | N | 10 | GROUND FLOOR |  | 125545 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 182.4 | LABOR- SUBCONTRACTOR
%R | 504784 | 6359 | 125546 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ACGF4610 | Fixing of Split AC | 8178 | 256 | 40 | 160 | 0 | 296 | 296 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-07 08:00 | 2014-05-29 17:00 |  | 2014-03-31 08:00 | 2014-04-22 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 | 2014-05-07 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | QtKx8rqBSRq+52M4UzNisA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31330 | N | N | 10 | GROUND FLOOR |  | 125545 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 296 | LABOR- SUBCONTRACTOR
%R | 504785 | 6359 | 125547 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ACRF4630 | Installation of Refrigerant Pipes | 8178 | 272 | 0 | 200 | 0 | 409.6 | 409.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-06-10 17:00 |  | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-05-13 08:00 | 2014-06-10 17:00 |  | PT_Normal |  |  |  |  | 0LOqOm7LT+qLLccs0iWo1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31350 | N | N | 20 | ROOF |  | 125545 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 409.6 | LABOR- SUBCONTRACTOR
%R | 504786 | 6359 | 125547 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ACRF4635 | Installation of Condensing Unit | 8178 | 24 | 0 | 200 | 0 | 568 | 568 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | Li8U3ynSRqKmuMe/AsbTPQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31350 | N | N | 20 | ROOF |  | 125545 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 568 | LABOR- SUBCONTRACTOR
%R | 504787 | 6359 | 125548 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ACFF4615 | Installation AC Pipes | 8178 | 216 | 40 | 160 | 0 | 977.6 | 977.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-02 08:00 | 2014-04-24 17:00 |  | 2014-03-02 08:00 | 2014-03-24 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 | 2014-04-02 08:00 | 2014-04-24 17:00 |  | PT_Normal |  |  |  |  | jDS+/bqfRe+62p5bUYuujg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31340 | N | N | 15 | FIRST FLOORS |  | 125545 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 977.6 | LABOR- SUBCONTRACTOR
%R | 504788 | 6359 | 125548 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ACFF4620 | Fixing of Ventilation Equipments | 8178 | 16 | 0 | 200 | 0 | 113.6 | 113.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-21 08:00 | 2014-05-19 17:00 |  | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | 218cXu4VSbmYRYVQLG2zTg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31340 | N | N | 15 | FIRST FLOORS |  | 125545 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 113.6 | LABOR- SUBCONTRACTOR
%R | 504789 | 6359 | 125548 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ACFF4625 | Fixing of Split AC | 8178 | 16 | 0 | 160 | 0 | 296 | 296 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-12 08:00 | 2014-06-03 17:00 |  | 2014-05-10 08:00 | 2014-06-01 17:00 | 2014-05-10 08:00 | 2014-06-01 17:00 | 2014-05-10 08:00 | 2014-06-01 17:00 | 2014-05-12 08:00 | 2014-06-03 17:00 |  | PT_Normal |  |  |  |  | Zd/Po/uEQRWSGu9p0UVCHw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31340 | N | N | 15 | FIRST FLOORS |  | 125545 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 296 | LABOR- SUBCONTRACTOR
%R | 504790 | 6359 | 125550 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 144 | 0 | 144 | 0 | 441.6 | 441.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-02-05 17:00 |  | 2013-12-26 08:00 | 2014-01-15 17:00 | 2013-12-26 08:00 | 2014-01-15 17:00 | 2013-12-26 08:00 | 2014-01-15 17:00 | 2014-01-16 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | OSlXr2eDSFOmY15iMcm4/w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31290 | N | N | 10 | GROUND FLOOR |  | 125549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 441.6 | LABOR- SUBCONTRACTOR
%R | 504791 | 6359 | 125550 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4PLGF4310 | Installation of Drainage pipes &testing | 8178 | 168 | 104 | 144 | 0 | 177.6 | 177.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-20 08:00 | 2014-02-09 17:00 |  | 2013-12-26 08:00 | 2014-01-15 17:00 | 2013-12-26 08:00 | 2014-01-15 17:00 | 2013-12-26 08:00 | 2014-01-15 17:00 | 2014-01-20 08:00 | 2014-02-09 17:00 |  | PT_Normal |  |  |  |  | gHaOr+A/SNuUodA8c8hdhQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31290 | N | N | 10 | GROUND FLOOR |  | 125549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 177.6 | LABOR- SUBCONTRACTOR
%R | 504792 | 6359 | 125550 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4PLGF4315 | Sanitary Fittings & Accessories | 8178 | 360 | 0 | 160 | 0 | 134.4 | 134.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-10 17:00 |  | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-05-19 08:00 | 2014-06-10 17:00 |  | PT_Normal |  |  |  |  | kf9mIWxMScuwxjY8+Zc24A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31290 | N | N | 10 | GROUND FLOOR |  | 125549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 504793 | 6359 | 125550 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4PLGF4320 | Installation of Water Heater | 8178 | 360 | 80 | 120 | 0 | 134.4 | 134.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-31 08:00 | 2014-06-16 17:00 |  | 2014-04-08 08:00 | 2014-04-24 17:00 | 2014-04-08 08:00 | 2014-04-24 17:00 | 2014-04-08 08:00 | 2014-04-24 17:00 | 2014-05-31 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | X4wI8I9VSyeyQMDINkKTPA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31290 | N | N | 10 | GROUND FLOOR |  | 125549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 504794 | 6359 | 125550 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 0 | 0 | 128 | 0 | 67.2 | 67.2 | 128 | 0 | 0 | 0 |  |  |  | 2013-09-02 08:00 | 2013-09-19 17:00 |  | 2013-09-02 08:00 | 2013-09-19 17:00 | 2013-09-02 08:00 | 2013-09-19 17:00 | 2013-09-02 08:00 | 2013-09-19 17:00 | 2013-09-02 08:00 | 2013-09-19 17:00 |  | PT_Normal |  |  |  |  | KGocslmqT0OPXFNxzOt88w |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31290 | N | N | 10 | GROUND FLOOR |  | 125549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504795 | 6359 | 125551 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 8 | 0 | 144 | 0 | 441.6 | 441.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-08 08:00 | 2014-03-01 17:00 |  | 2014-02-06 08:00 | 2014-02-27 17:00 | 2014-02-06 08:00 | 2014-02-27 17:00 | 2014-02-06 08:00 | 2014-02-27 17:00 | 2014-02-08 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | WlWs8rxHQpmYZ52pa2lCMQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31300 | N | N | 15 | FIRST FLOORS |  | 125549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 441.6 | LABOR- SUBCONTRACTOR
%R | 504796 | 6359 | 125551 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4PLFF4330 | Installation of Drainage pipes & testing | 8178 | 184 | 64 | 144 | 0 | 177.6 | 177.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-06 08:00 | 2014-03-26 17:00 |  | 2014-02-06 08:00 | 2014-02-27 17:00 | 2014-02-06 08:00 | 2014-02-27 17:00 | 2014-02-06 08:00 | 2014-02-27 17:00 | 2014-03-06 08:00 | 2014-03-26 17:00 |  | PT_Normal |  |  |  |  | xdT1Vr/7TWW+ca4ILrnpVA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31300 | N | N | 15 | FIRST FLOORS |  | 125549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 177.6 | LABOR- SUBCONTRACTOR
%R | 504797 | 6359 | 125551 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4PLFF4335 | Sanitary Fittings & Accessories | 8178 | 40 | 0 | 160 | 0 | 67.2 | 67.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-01 08:00 | 2014-05-24 17:00 |  | 2014-04-26 08:00 | 2014-05-18 17:00 | 2014-04-26 08:00 | 2014-05-18 17:00 | 2014-04-26 08:00 | 2014-05-18 17:00 | 2014-05-01 08:00 | 2014-05-24 17:00 |  | PT_Normal |  |  |  |  | WJCrq9p0QUSgLHUcsiAu4g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31300 | N | N | 15 | FIRST FLOORS |  | 125549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504798 | 6359 | 125551 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4PLFF4340 | Installation of Water Heater | 8178 | 40 | 32 | 120 | 0 | 67.2 | 67.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-05-29 17:00 |  | 2014-05-07 08:00 | 2014-05-24 17:00 | 2014-05-07 08:00 | 2014-05-24 17:00 | 2014-05-07 08:00 | 2014-05-24 17:00 | 2014-05-13 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | xl+dxHBTS6KpwxuOQDvMfw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31300 | N | N | 15 | FIRST FLOORS |  | 125549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504799 | 6359 | 125552 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 448 | 240 | 120 | 0 | 110.4 | 110.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-04 08:00 | 2014-05-20 17:00 |  | 2014-02-27 08:00 | 2014-03-16 17:00 | 2014-02-27 08:00 | 2014-03-16 17:00 | 2014-02-27 08:00 | 2014-03-16 17:00 | 2014-05-04 08:00 | 2014-05-20 17:00 |  | PT_Normal |  |  |  |  | ePnVWfK1TBSyiHpxU2xi0A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31310 | N | N | 20 | ROOF |  | 125549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 110.4 | LABOR- SUBCONTRACTOR
%R | 504800 | 6359 | 125552 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4PLRF4350 | Installation of Rain water Pipes | 8178 | 208 | 80 | 120 | 0 | 67.2 | 67.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-05-29 17:00 |  | 2014-04-13 08:00 | 2014-04-29 17:00 | 2014-04-13 08:00 | 2014-04-29 17:00 | 2014-04-13 08:00 | 2014-04-29 17:00 | 2014-05-13 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | 4CDpcuPNSM6uoB+8vmEyLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31310 | N | N | 20 | ROOF |  | 125549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 504801 | 6359 | 125552 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 8 | 0 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-05-18 08:00 | 2014-06-15 17:00 | 2014-05-18 08:00 | 2014-06-15 17:00 | 2014-05-18 08:00 | 2014-06-15 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | c39vlzuERxiG2SW8U3xHEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31310 | N | N | 20 | ROOF |  | 125549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 336 | LABOR- SUBCONTRACTOR
%R | 504802 | 6359 | 125554 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 216 | 0 | 200 | 0 | 1222.4 | 1222.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-02-15 17:00 |  | 2013-12-15 08:00 | 2014-01-13 17:00 | 2013-12-15 08:00 | 2014-01-13 17:00 | 2013-12-15 08:00 | 2014-01-13 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 |  | PT_Normal |  |  |  |  | NNTsSi0GR7OXjmw5suYaoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31250 | N | N | 10 | GROUND FLOOR |  | 125553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1222.4 | LABOR- SUBCONTRACTOR
%R | 504803 | 6359 | 125554 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ELGF4005 | Cable tray & trunking installation | 8178 | 360 | 0 | 160 | 0 | 1318.4 | 1318.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-19 08:00 | 2014-03-13 17:00 |  | 2013-12-28 08:00 | 2014-01-19 17:00 | 2013-12-28 08:00 | 2014-01-19 17:00 | 2013-12-28 08:00 | 2014-01-19 17:00 | 2014-02-19 08:00 | 2014-03-13 17:00 |  | PT_Normal |  |  |  |  | ctstqlxqT4OjYelSH3mtrg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31250 | N | N | 10 | GROUND FLOOR |  | 125553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1318.4 | LABOR- SUBCONTRACTOR
%R | 504804 | 6359 | 125554 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ELGF4010 | Installation of wiring & Main Cabling | 8178 | 360 | 216 | 200 | 0 | 296 | 296 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-27 08:00 | 2014-03-27 17:00 |  | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 |  | PT_Normal |  |  |  |  | XXyBWcA2Stq58/Y+GXm7+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31250 | N | N | 10 | GROUND FLOOR |  | 125553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 296 | LABOR- SUBCONTRACTOR
%R | 504805 | 6359 | 125554 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 144 | 0 | 160 | 0 | 227.2 | 227.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-04-28 17:00 |  | 2014-03-16 08:00 | 2014-04-07 17:00 | 2014-03-16 08:00 | 2014-04-07 17:00 | 2014-03-16 08:00 | 2014-04-07 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | cDKZvsUzQ/K/I8szQRNFcg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31250 | N | N | 10 | GROUND FLOOR |  | 125553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 227.2 | LABOR- SUBCONTRACTOR
%R | 504806 | 6359 | 125554 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 200 | 0 | 200 | 0 | 1651.2 | 1651.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-26 08:00 | 2014-05-24 17:00 |  | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 |  | PT_Normal |  |  |  |  | sxO27q4MSgOfTEN5rtqZeQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31250 | N | N | 10 | GROUND FLOOR |  | 125553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1651.2 | LABOR- SUBCONTRACTOR
%R | 504807 | 6359 | 125554 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 240 | 0 | 200 | 0 | 1075.2 | 1075.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-14 08:00 | 2014-05-12 17:00 |  | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 |  | PT_Normal |  |  |  |  | LbbTxpfeSVCBAsfx1HLrjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31250 | N | N | 10 | GROUND FLOOR |  | 125553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1075.2 | LABOR- SUBCONTRACTOR
%R | 504808 | 6359 | 125554 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ELGF4030 | Installation of Telephone System | 8178 | 144 | 40 | 160 | 0 | 520 | 520 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-10 17:00 |  | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-04-17 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | X3wyIPoTTOa6JXdkHu49mQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31250 | N | N | 10 | GROUND FLOOR |  | 125553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 520 | LABOR- SUBCONTRACTOR
%R | 504809 | 6359 | 125555 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 88 | 0 | 200 | 0 | 1222.4 | 1222.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-03-10 17:00 |  | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | sg1pDadWRXyzfM3Qv/y2rQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31260 | N | N | 15 | FIRST FLOORS |  | 125553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1222.4 | LABOR- SUBCONTRACTOR
%R | 504810 | 6359 | 125555 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ELFF4040 | Cable tray & trunking installation | 8178 | 232 | 16 | 160 | 0 | 1318.4 | 1318.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-06 17:00 |  | 2014-02-08 08:00 | 2014-03-03 17:00 | 2014-02-08 08:00 | 2014-03-03 17:00 | 2014-02-08 08:00 | 2014-03-03 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | F56MGRPQQAyDJQV/MpKFfw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31260 | N | N | 15 | FIRST FLOORS |  | 125553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1318.4 | LABOR- SUBCONTRACTOR
%R | 504811 | 6359 | 125555 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ELFF4045 | Installation of wiring & Main Cabling | 8178 | 216 | 0 | 200 | 0 | 296 | 296 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-23 08:00 | 2014-04-20 17:00 |  | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | 1hXkHWdzTQGbyI/fj2bcCw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31260 | N | N | 15 | FIRST FLOORS |  | 125553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 148 | LABOR- SUBCONTRACTOR
%R | 504812 | 6359 | 125555 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 24 | 16 | 160 | 0 | 227.2 | 227.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-26 08:00 | 2014-05-18 17:00 |  | 2014-04-22 08:00 | 2014-05-14 17:00 | 2014-04-22 08:00 | 2014-05-14 17:00 | 2014-04-22 08:00 | 2014-05-14 17:00 | 2014-04-26 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | /Yy4bX6OQ4OxOg9E8mD1GA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31260 | N | N | 15 | FIRST FLOORS |  | 125553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 227.2 | LABOR- SUBCONTRACTOR
%R | 504813 | 6359 | 125555 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 8 | 0 | 200 | 0 | 1651.2 | 1651.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-01 08:00 | 2014-05-29 17:00 |  | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | j8r11BXwQTeNjr6Pyv9Gyw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31260 | N | N | 15 | FIRST FLOORS |  | 125553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1651.2 | LABOR- SUBCONTRACTOR
%R | 504814 | 6359 | 125555 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 8 | 0 | 200 | 0 | 1008 | 1008 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | 687DQyKkQJWbw8qJmkcAYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31260 | N | N | 15 | FIRST FLOORS |  | 125553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1008 | LABOR- SUBCONTRACTOR
%R | 504815 | 6359 | 125555 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ELFF4050 | Installation of Telephone System | 8178 | 64 | 56 | 200 | 0 | 451.2 | 451.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-27 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | 9UeQfnUrS7680oqcRcuhug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31260 | N | N | 15 | FIRST FLOORS |  | 125553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 451.2 | LABOR- SUBCONTRACTOR
%R | 504816 | 6359 | 125556 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ELRF4070 | Installation of Isolator | 8178 | 8 | 0 | 144 | 0 | 412.8 | 412.8 | 144 | 0 | 0 | 0 |  |  |  | 2014-05-15 08:00 | 2014-06-04 17:00 |  | 2014-05-14 08:00 | 2014-06-03 17:00 | 2014-05-14 08:00 | 2014-06-03 17:00 | 2014-05-14 08:00 | 2014-06-03 17:00 | 2014-05-15 08:00 | 2014-06-04 17:00 |  | PT_Normal |  |  |  |  | 1qNgoX1hTcWVw3Olvcqwmw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31270 | N | N | 20 | ROOF |  | 125553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 412.8 | LABOR- SUBCONTRACTOR
%R | 504817 | 6359 | 125556 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ELRF4075 | Installation of TV Dish Antenna | 8178 | 8 | 8 | 184 | 0 | 732.8 | 732.8 | 184 | 0 | 0 | 0 |  |  |  | 2014-05-21 08:00 | 2014-06-16 17:00 |  | 2014-05-20 08:00 | 2014-06-15 17:00 | 2014-05-20 08:00 | 2014-06-15 17:00 | 2014-05-20 08:00 | 2014-06-15 17:00 | 2014-05-21 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | IQhkovilRkC3+X2gzyFfhw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31270 | N | N | 20 | ROOF |  | 125553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 732.8 | LABOR- SUBCONTRACTOR
%R | 504818 | 6359 | 125559 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STRF2040 | Column-Rebar & Formwork | 8165 | 64 | 0 | 144 | 0 | 1205.75 | 1205.75 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-04 08:00 | 2014-01-23 17:00 |  | 2013-12-25 08:00 | 2014-01-14 17:00 | 2013-12-25 08:00 | 2014-01-14 17:00 | 2013-12-25 08:00 | 2014-01-14 17:00 | 2014-01-04 08:00 | 2014-01-23 17:00 |  | PT_Normal |  |  |  |  | LluXCma1TzyaL2WW7SDKyw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31140 | N | N | 20 | ROOF |  | 125558 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1205.75 | STEEL FIXERS SK
%R | 504819 | 6359 | 125559 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STRF2045 | Column-Concrete | 8167 | 64 | 0 | 136 | 0 | 52.5 | 52.5 | 136 | 0 | 0 | 0 |  |  |  | 2014-01-07 08:00 | 2014-01-26 17:00 |  | 2013-12-29 08:00 | 2014-01-16 17:00 | 2013-12-29 08:00 | 2014-01-16 17:00 | 2013-12-29 08:00 | 2014-01-16 17:00 | 2014-01-07 08:00 | 2014-01-26 17:00 |  | PT_Normal |  |  |  |  | ItxahXiIRk2mPnCqUM0N9Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31140 | N | N | 20 | ROOF |  | 125558 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 52.5 | CONCRETE MASON SK
%R | 504820 | 6359 | 125559 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STRF2050 | Slab-Rebar & Formwork - Head Room | 8165 | 64 | 0 | 160 | 0 | 2735.25 | 2735.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-09 08:00 | 2014-02-01 17:00 |  | 2013-12-31 08:00 | 2014-01-22 17:00 | 2013-12-31 08:00 | 2014-01-22 17:00 | 2013-12-31 08:00 | 2014-01-22 17:00 | 2014-01-09 08:00 | 2014-02-01 17:00 |  | PT_Normal |  |  |  |  | 7VMwB7IZRJekHLXB0QiAmQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31140 | N | N | 20 | ROOF |  | 125558 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 2735.25 | STEEL FIXERS SK
%R | 504821 | 6359 | 125559 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STRF2055 | Slab-Concrete-Head room | 8167 | 64 | 0 | 104 | 0 | 252 | 252 | 104 | 0 | 0 | 0 |  |  |  | 2014-01-20 08:00 | 2014-02-03 17:00 |  | 2014-01-11 08:00 | 2014-01-25 17:00 | 2014-01-11 08:00 | 2014-01-25 17:00 | 2014-01-11 08:00 | 2014-01-25 17:00 | 2014-01-20 08:00 | 2014-02-03 17:00 |  | PT_Normal |  |  |  |  | 0CQNBM5DRFiz3iO6P7JZRA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31140 | N | N | 20 | ROOF |  | 125558 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 252 | CONCRETE MASON SK
%R | 504822 | 6359 | 125559 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STRF2060 | Construction of Parapets | 8168 | 448 | 32 | 200 | 0 | 2200 | 2200 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-20 08:00 | 2014-04-17 17:00 |  | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 |  | PT_Normal |  |  |  |  | FJl2WbbtRh2/qfx3G8NFtg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31140 | N | N | 20 | ROOF |  | 125558 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 2200 | BLOCK MASON SK
%R | 504823 | 6359 | 125559 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STRF2065 | Construction of up stands/Plinth | 8165 | 416 | 0 | 200 | 0 | 554.75 | 554.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-26 08:00 | 2014-04-23 17:00 |  | 2014-01-23 08:00 | 2014-02-22 17:00 | 2014-01-23 08:00 | 2014-02-22 17:00 | 2014-01-23 08:00 | 2014-02-22 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 |  | PT_Normal |  |  |  |  | Y4U1LNHXQu+NTJZar0jM/A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31140 | N | N | 20 | ROOF |  | 125558 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 554.75 | STEEL FIXERS SK
%R | 504824 | 6359 | 125560 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STFF2020 | Column-Rebar & Formwork | 8165 | 16 | 0 | 200 | 0 | 3580.5 | 3580.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-13 08:00 | 2013-12-11 17:00 |  | 2013-11-11 08:00 | 2013-12-09 17:00 | 2013-11-11 08:00 | 2013-12-09 17:00 | 2013-11-11 08:00 | 2013-12-09 17:00 | 2013-11-13 08:00 | 2013-12-11 17:00 |  | PT_Normal |  |  |  |  | U5TUfHzzSx6pANAp3O3msQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31130 | N | N | 15 | FIRST FLOORS |  | 125558 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 3580.5 | STEEL FIXERS SK
%R | 504825 | 6359 | 125560 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STFF2025 | Column-Concrete | 8167 | 32 | 0 | 192 | 0 | 224 | 224 | 192 | 0 | 0 | 0 |  |  |  | 2013-11-25 08:00 | 2013-12-23 17:00 |  | 2013-11-20 08:00 | 2013-12-17 17:00 | 2013-11-20 08:00 | 2013-12-17 17:00 | 2013-11-20 08:00 | 2013-12-17 17:00 | 2013-11-25 08:00 | 2013-12-23 17:00 |  | PT_Normal |  |  |  |  | 9z1P5zPGRkikuHaSYX7UJg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31130 | N | N | 15 | FIRST FLOORS |  | 125558 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 224 | CONCRETE MASON SK
%R | 504826 | 6359 | 125560 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 32 | 0 | 200 | 0 | 16119.25 | 16119.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-10 08:00 | 2014-01-08 17:00 |  | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 |  | PT_Normal |  |  |  |  | qoLsGjDBQFGb2fKmDSaDsA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31130 | N | N | 15 | FIRST FLOORS |  | 125558 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 16119.25 | STEEL FIXERS SK
%R | 504827 | 6359 | 125560 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 32 | 0 | 112 | 0 | 1141 | 1141 | 112 | 0 | 0 | 0 |  |  |  | 2013-12-28 08:00 | 2014-01-12 17:00 |  | 2013-12-23 08:00 | 2014-01-07 17:00 | 2013-12-23 08:00 | 2014-01-07 17:00 | 2013-12-23 08:00 | 2014-01-07 17:00 | 2013-12-28 08:00 | 2014-01-12 17:00 |  | PT_Normal |  |  |  |  | ZxtggsVRSTiHcJuqm7EN7g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31130 | N | N | 15 | FIRST FLOORS |  | 125558 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1141 | CONCRETE MASON SK
%R | 504828 | 6359 | 125561 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STGF2000 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 4046 | 4046 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-28 08:00 | 2013-10-28 17:00 |  | 2013-09-28 08:00 | 2013-10-28 17:00 | 2013-09-28 08:00 | 2013-10-28 17:00 | 2013-09-28 08:00 | 2013-10-28 17:00 | 2013-09-28 08:00 | 2013-10-28 17:00 |  | PT_Normal |  |  |  |  | 5fyW9rW5QoGoJg+TwQqYrg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31120 | N | N | 10 | GROUND FLOOR |  | 125558 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 2023 | STEEL FIXERS SK
%R | 504829 | 6359 | 125561 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STGF2005 | Column-Concrete | 8167 | 16 | 0 | 192 | 0 | 255.5 | 255.5 | 192 | 0 | 0 | 0 |  |  |  | 2013-10-08 08:00 | 2013-11-06 17:00 |  | 2013-10-06 08:00 | 2013-11-04 17:00 | 2013-10-06 08:00 | 2013-11-04 17:00 | 2013-10-06 08:00 | 2013-11-04 17:00 | 2013-10-08 08:00 | 2013-11-06 17:00 |  | PT_Normal |  |  |  |  | jEqac4hCTUe0oKPcIeeVCQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31120 | N | N | 10 | GROUND FLOOR |  | 125558 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 255.5 | CONCRETE MASON SK
%R | 504830 | 6359 | 125561 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 16 | 0 | 200 | 0 | 16829.75 | 16829.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-26 08:00 | 2013-11-23 17:00 |  | 2013-10-23 08:00 | 2013-11-20 17:00 | 2013-10-23 08:00 | 2013-11-20 17:00 | 2013-10-23 08:00 | 2013-11-20 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 |  | PT_Normal |  |  |  |  | XhiRwuBaTk64pfrh9r8l+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31120 | N | N | 10 | GROUND FLOOR |  | 125558 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 16829.75 | STEEL FIXERS SK
%R | 504831 | 6359 | 125561 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 16 | 0 | 112 | 0 | 1295 | 1295 | 112 | 0 | 0 | 0 |  |  |  | 2013-11-11 08:00 | 2013-11-26 17:00 |  | 2013-11-09 08:00 | 2013-11-24 17:00 | 2013-11-09 08:00 | 2013-11-24 17:00 | 2013-11-09 08:00 | 2013-11-24 17:00 | 2013-11-11 08:00 | 2013-11-26 17:00 |  | PT_Normal |  |  |  |  | k1LoNUwSRKSYfpLS2192lA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31120 | N | N | 10 | GROUND FLOOR |  | 125558 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1295 | CONCRETE MASON SK
%R | 504832 | 6359 | 125563 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STUG1000 | Footing Excavation | 8177 | 0 | 0 | 200 | 0 | 1114 | 1114 | 200 | 524 | 0 | 524 |  |  |  | 2013-05-13 08:00 | 2013-06-10 17:00 |  | 2013-05-13 08:00 | 2013-06-10 17:00 | 2013-05-13 08:00 | 2013-06-10 17:00 | 2013-05-13 08:00 | 2013-06-10 17:00 | 2013-05-13 08:00 | 2013-06-10 17:00 |  | PT_Normal |  |  |  |  | RHe1Qh3cQKG5FtJPGtIaoQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31100 | N | N | 10 | UPTO GRADE SLAB |  | 125562 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 1114 | LABOR - CIVIL
%R | 504833 | 6359 | 125563 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STUG1005 | Footing Antitermite | 8178 | 0 | 0 | 184 | 0 | 1584 | 1584 | 184 | 0 | 0 | 0 |  |  |  | 2013-05-25 08:00 | 2013-06-19 17:00 |  | 2013-05-25 08:00 | 2013-06-19 17:00 | 2013-05-25 08:00 | 2013-06-19 17:00 | 2013-05-25 08:00 | 2013-06-19 17:00 | 2013-05-25 08:00 | 2013-06-19 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31100 | N | N | 10 | UPTO GRADE SLAB |  | 125562 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 1584 | LABOR- SUBCONTRACTOR
%R | 504834 | 6359 | 125563 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STUG1010 | Footing Blinding | 8163 | 0 | 0 | 184 | 0 | 794.5 | 794.5 | 184 | 0 | 0 | 0 |  |  |  | 2013-05-28 08:00 | 2013-06-23 17:00 |  | 2013-05-28 08:00 | 2013-06-23 17:00 | 2013-05-28 08:00 | 2013-06-23 17:00 | 2013-05-28 08:00 | 2013-06-23 17:00 | 2013-05-28 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31100 | N | N | 10 | UPTO GRADE SLAB |  | 125562 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 794.5 | BLINDING MASON SK
%R | 504835 | 6359 | 125563 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STUG1015 | Footing Waterproofing & Screed | 8164 | 0 | 0 | 200 | 0 | 574.75 | 574.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-03 08:00 | 2013-07-01 17:00 |  | 2013-06-03 08:00 | 2013-07-01 17:00 | 2013-06-03 08:00 | 2013-07-01 17:00 | 2013-06-03 08:00 | 2013-07-01 17:00 | 2013-06-03 08:00 | 2013-07-01 17:00 |  | PT_Normal |  |  |  |  | TuJKZPj2TwKHi2UQzZKKPg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31100 | N | N | 10 | UPTO GRADE SLAB |  | 125562 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 574.75 | SCREED MASON SK
%R | 504836 | 6359 | 125563 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STUG1020 | Construction of foundations | 8165 | 0 | 0 | 160 | 0 | 7778.75 | 7778.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-06-18 08:00 | 2013-07-10 17:00 |  | 2013-06-18 08:00 | 2013-07-10 17:00 | 2013-06-18 08:00 | 2013-07-10 17:00 | 2013-06-18 08:00 | 2013-07-10 17:00 | 2013-06-18 08:00 | 2013-07-10 17:00 |  | PT_Normal |  |  |  |  | dBriWKmtTg6LcbyE3lRRJg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31100 | N | N | 10 | UPTO GRADE SLAB |  | 125562 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 7778.75 | STEEL FIXERS SK
%R | 504837 | 6359 | 125563 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STUG1025 | Construction of neck of columns | 8165 | 0 | 0 | 200 | 0 | 1606.5 | 1606.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-27 08:00 | 2013-07-25 17:00 |  | 2013-06-27 08:00 | 2013-07-25 17:00 | 2013-06-27 08:00 | 2013-07-25 17:00 | 2013-06-27 08:00 | 2013-07-25 17:00 | 2013-06-27 08:00 | 2013-07-25 17:00 |  | PT_Normal |  |  |  |  | mEMYwCnqSFOGwGQXX1xCCw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31100 | N | N | 10 | UPTO GRADE SLAB |  | 125562 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 1606.5 | STEEL FIXERS SK
%R | 504838 | 6359 | 125563 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STUG1030 | Waterproofing Footing & Neck Column | 8178 | 0 | 0 | 200 | 0 | 516 | 516 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-07 08:00 | 2013-08-04 17:00 |  | 2013-07-07 08:00 | 2013-08-04 17:00 | 2013-07-07 08:00 | 2013-08-04 17:00 | 2013-07-07 08:00 | 2013-08-04 17:00 | 2013-07-07 08:00 | 2013-08-04 17:00 |  | PT_Normal |  |  |  |  | VNXI00AvTMqbE0X1UVi6vw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31100 | N | N | 10 | UPTO GRADE SLAB |  | 125562 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 516 | LABOR- SUBCONTRACTOR
%R | 504839 | 6359 | 125563 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 0 | 0 | 200 | 0 | 1041 | 1041 | 200 | 825 | 0 | 825 |  |  |  | 2013-07-21 08:00 | 2013-08-21 17:00 |  | 2013-07-21 08:00 | 2013-08-21 17:00 | 2013-07-21 08:00 | 2013-08-21 17:00 | 2013-07-21 08:00 | 2013-08-21 17:00 | 2013-07-21 08:00 | 2013-08-21 17:00 |  | PT_Normal |  |  |  |  | FGaC07YFQLCMDmXMZliZ3A |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31100 | N | N | 10 | UPTO GRADE SLAB |  | 125562 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 520.5 | LABOR - CIVIL
%R | 504840 | 6359 | 125563 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STUG1040 | Construction of Grade Beams | 8163 | 0 | 0 | 200 | 0 | 7568.75 | 7568.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-06 08:00 | 2013-09-07 17:00 |  | 2013-08-06 08:00 | 2013-09-07 17:00 | 2013-08-06 08:00 | 2013-09-07 17:00 | 2013-08-06 08:00 | 2013-09-07 17:00 | 2013-08-06 08:00 | 2013-09-07 17:00 |  | PT_Normal |  |  |  |  | q/yFOvYNQFeLyihBKQgRSg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31100 | N | N | 10 | UPTO GRADE SLAB |  | 125562 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 3784.375 | BLINDING MASON SK
%R | 504841 | 6359 | 125563 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4STUG1045 | Construction of slab on grade | 8163 | 0 | 0 | 200 | 0 | 4422 | 4422 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-11 08:00 | 2013-10-09 17:00 |  | 2013-09-11 08:00 | 2013-10-09 17:00 | 2013-09-11 08:00 | 2013-10-09 17:00 | 2013-09-11 08:00 | 2013-10-09 17:00 | 2013-09-11 08:00 | 2013-10-09 17:00 |  | PT_Normal |  |  |  |  | ZyYp8cSiRZeKb8nePajKYw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31100 | N | N | 10 | UPTO GRADE SLAB |  | 125562 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 4422 | BLINDING MASON SK
%R | 504842 | 6359 | 125566 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4AREL3665 | External Plastering | 8169 | 376 | 0 | 200 | 0 | 14275 | 14275 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-05-21 17:00 |  | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | n+J4fUV5Rwub9ThuofsIzA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31220 | N | N | 15 | ELEVATION |  | 125565 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 7137.5 | PLASTER MASON SK
%R | 504843 | 6359 | 125566 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4AREL3670 | External stone cladding works | 8170 | 392 | 0 | 160 | 0 | 990 | 990 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-06-04 17:00 |  | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-05-13 08:00 | 2014-06-04 17:00 |  | PT_Normal |  |  |  |  | O7Ont6FXT9Oggth5jIgo5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31220 | N | N | 15 | ELEVATION |  | 125565 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 990 | TILE MASON SK
%R | 504844 | 6359 | 125566 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4AREL3680 | External Painting | 8178 | 392 | 40 | 160 | 0 | 3784 | 3784 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-25 08:00 | 2014-06-16 17:00 |  | 2014-03-29 08:00 | 2014-04-20 17:00 | 2014-03-29 08:00 | 2014-04-20 17:00 | 2014-03-29 08:00 | 2014-04-20 17:00 | 2014-05-25 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | LkYp7IYtSgWxspX/1bDGpQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31220 | N | N | 15 | ELEVATION |  | 125565 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 3784 | LABOR- SUBCONTRACTOR
%R | 504845 | 6359 | 125567 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARRF3630 | Leveling Screed for Waterproofing | 8164 | 168 | 0 | 200 | 0 | 800 | 800 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-07 08:00 | 2014-05-05 17:00 |  | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | /Gh20dnsSee3f2489svosw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31210 | N | N | 10 | ROOF |  | 125565 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 800 | SCREED MASON SK
%R | 504846 | 6359 | 125567 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARRF3635 | Laying of Waterproofing Membrane | 8178 | 168 | 0 | 200 | 0 | 1138.5 | 1138.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-10 08:00 | 2014-05-08 17:00 |  | 2014-03-17 08:00 | 2014-04-14 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 | 2014-04-10 08:00 | 2014-05-08 17:00 |  | PT_Normal |  |  |  |  | RF/8xps4RCydCXjpRzUJPA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31210 | N | N | 10 | ROOF |  | 125565 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1138.5 | LABOR- SUBCONTRACTOR
%R | 504847 | 6359 | 125567 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARRF3640 | Installation of Insulation & Protection | 8178 | 168 | 0 | 200 | 0 | 1408 | 1408 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-13 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 |  | PT_Normal |  |  |  |  | 9uAj15TsQGKlSRJXO5ZlLg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31210 | N | N | 10 | ROOF |  | 125565 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1408 | LABOR- SUBCONTRACTOR
%R | 504848 | 6359 | 125567 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 168 | 0 | 200 | 0 | 688.25 | 688.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | JiKA3QFOROKQwO1jtQv0zQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31210 | N | N | 10 | ROOF |  | 125565 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 688.25 | TILE MASON SK
%R | 504849 | 6359 | 125567 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 168 | 0 | 160 | 0 | 616 | 616 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-06-04 17:00 |  | 2014-04-19 08:00 | 2014-05-11 17:00 | 2014-04-19 08:00 | 2014-05-11 17:00 | 2014-04-19 08:00 | 2014-05-11 17:00 | 2014-05-13 08:00 | 2014-06-04 17:00 |  | PT_Normal |  |  |  |  | WnWmaE3mRo6fRdzm1BMFXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31210 | N | N | 10 | ROOF |  | 125565 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 616 | LABOR- SUBCONTRACTOR
%R | 504850 | 6359 | 125567 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 168 | 0 | 200 | 0 | 1046.5 | 1046.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-28 08:00 | 2014-05-26 17:00 |  | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-28 08:00 | 2014-05-26 17:00 |  | PT_Normal |  |  |  |  | /Wz1+Y12TYyfxKd26S9FCQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31210 | N | N | 10 | ROOF |  | 125565 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1046.5 | LABOR- SUBCONTRACTOR
%R | 504851 | 6359 | 125567 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARRF3660 | Installation of Access Ladder | 8178 | 208 | 208 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-31 08:00 | 2014-06-16 17:00 |  | 2014-04-30 08:00 | 2014-05-17 17:00 | 2014-04-30 08:00 | 2014-05-17 17:00 | 2014-04-30 08:00 | 2014-05-17 17:00 | 2014-05-31 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | esBmLSXCRYCPuXJNkC2MRA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31210 | N | N | 10 | ROOF |  | 125565 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 176 | LABOR- SUBCONTRACTOR
%R | 504852 | 6359 | 125569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARFF3300 | Block work | 8168 | 0 | 0 | 200 | 0 | 6387.5 | 6387.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-21 08:00 | 2014-02-19 17:00 |  | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 |  | PT_Normal |  |  |  |  | r/v/jYukQPKdUj2/yIGyqw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31180 | N | N | 15 | FIRST FLOORS |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 6387.5 | BLOCK MASON SK
%R | 504853 | 6359 | 125569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARFF3305 | Plastering work | 8169 | 0 | 0 | 200 | 0 | 8899 | 8899 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-16 17:00 |  | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | /vc8IlmkRM+jw9PSsjbIDA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31180 | N | N | 15 | FIRST FLOORS |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 4449.5 | PLASTER MASON SK
%R | 504854 | 6359 | 125569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARFF3310 | Flooring screed | 8164 | 96 | 96 | 168 | 0 | 1215.5 | 1215.5 | 168 | 0 | 0 | 0 |  |  |  | 2014-03-10 08:00 | 2014-04-02 17:00 |  | 2014-02-24 08:00 | 2014-03-19 17:00 | 2014-02-24 08:00 | 2014-03-19 17:00 | 2014-02-24 08:00 | 2014-03-19 17:00 | 2014-03-10 08:00 | 2014-04-02 17:00 |  | PT_Normal |  |  |  |  | 4n4O46hiQzu/+Lwpo47Q6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31180 | N | N | 15 | FIRST FLOORS |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1215.5 | SCREED MASON SK
%R | 504855 | 6359 | 125569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARFF3315 | Wet area waterproofing | 8178 | 0 | 0 | 120 | 0 | 1215.5 | 1215.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-24 17:00 |  | 2014-03-08 08:00 | 2014-03-24 17:00 | 2014-03-08 08:00 | 2014-03-24 17:00 | 2014-03-08 08:00 | 2014-03-24 17:00 | 2014-03-08 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | DLaHb22GQAeARZIgF4kKFQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31180 | N | N | 15 | FIRST FLOORS |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1215.5 | LABOR- SUBCONTRACTOR
%R | 504856 | 6359 | 125569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARFF3330 | Paint First coat | 8178 | 112 | 112 | 200 | 0 | 4742.75 | 4742.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-20 08:00 | 2014-04-17 17:00 |  | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 |  | PT_Normal |  |  |  |  | U8jwtV61RWWXhcuJfGczcw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31180 | N | N | 15 | FIRST FLOORS |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 4742.75 | LABOR- SUBCONTRACTOR
%R | 504857 | 6359 | 125569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARFF3320 | Ceramic Wall Tiling | 8170 | 0 | 0 | 200 | 0 | 1897.25 | 1897.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-12 17:00 |  | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 |  | PT_Normal |  |  |  |  | /lU18S4MTk2KDZqOz+qi4g |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31180 | N | N | 15 | FIRST FLOORS |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1897.25 | TILE MASON SK
%R | 504858 | 6359 | 125569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARFF3325 | Porcelain Tile flooring | 8170 | 0 | 0 | 200 | 0 | 1743.75 | 1743.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-19 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | iUGvQawqS0+kCtEE0/FFow |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31180 | N | N | 15 | FIRST FLOORS |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1743.75 | TILE MASON SK
%R | 504859 | 6359 | 125569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARFF3335 | Slate Tile Flooring & Skirting | 8170 | 64 | 64 | 120 | 0 | 261.5 | 261.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-04 17:00 |  | 2014-04-08 08:00 | 2014-04-24 17:00 | 2014-04-08 08:00 | 2014-04-24 17:00 | 2014-04-08 08:00 | 2014-04-24 17:00 | 2014-04-17 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | Ka+L1hK/Skq9Eyq3Ifgw9g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31180 | N | N | 15 | FIRST FLOORS |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 261.5 | TILE MASON SK
%R | 504860 | 6359 | 125569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARFF3350 | Granite - Stair case flooring & Skirting | 8171 | 16 | 16 | 160 | 0 | 875 | 875 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-14 08:00 | 2014-05-06 17:00 |  | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-04-14 08:00 | 2014-05-06 17:00 |  | PT_Normal |  |  |  |  | Zog7h7trTrWi5L7PxfJCpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31180 | N | N | 15 | FIRST FLOORS |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 875 | GRANITE MASON SK
%R | 504861 | 6359 | 125569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARFF3345 | Fixing of Suspension systems | 8178 | 0 | 0 | 160 | 0 | 1305 | 1305 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-03 08:00 | 2014-04-26 17:00 |  | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-04-03 08:00 | 2014-04-26 17:00 |  | PT_Normal |  |  |  |  | 3s/1LFECRb+dAs12QSsPnA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31180 | N | N | 15 | FIRST FLOORS |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1305 | LABOR- SUBCONTRACTOR
%R | 504862 | 6359 | 125569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARFF3360 | Gypsum board false ceiling | 8178 | 0 | 0 | 200 | 0 | 1305 | 1305 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-10 08:00 | 2014-05-08 17:00 |  | 2014-04-10 08:00 | 2014-05-08 17:00 | 2014-04-10 08:00 | 2014-05-08 17:00 | 2014-04-10 08:00 | 2014-05-08 17:00 | 2014-04-10 08:00 | 2014-05-08 17:00 |  | PT_Normal |  |  |  |  | TFkJFTJyTvCdDwsiOX3/Bw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31180 | N | N | 15 | FIRST FLOORS |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1305 | LABOR- SUBCONTRACTOR
%R | 504863 | 6359 | 125569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARFF3365 | Wooden door | 8178 | 0 | 0 | 120 | 0 | 308 | 308 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-26 08:00 | 2014-05-12 17:00 |  | 2014-04-26 08:00 | 2014-05-12 17:00 | 2014-04-26 08:00 | 2014-05-12 17:00 | 2014-04-26 08:00 | 2014-05-12 17:00 | 2014-04-26 08:00 | 2014-05-12 17:00 |  | PT_Normal |  |  |  |  | 1Zu7pl48TSG1F6ImWUJTbQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31180 | N | N | 15 | FIRST FLOORS |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 308 | LABOR- SUBCONTRACTOR
%R | 504864 | 6359 | 125569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARFF3370 | Aluminum Door | 8178 | 0 | 0 | 160 | 0 | 220 | 220 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-26 08:00 | 2014-05-18 17:00 |  | 2014-04-26 08:00 | 2014-05-18 17:00 | 2014-04-26 08:00 | 2014-05-18 17:00 | 2014-04-26 08:00 | 2014-05-18 17:00 | 2014-04-26 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | F5Frq+0wSzGIZh5Wm4c6AA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31180 | N | N | 15 | FIRST FLOORS |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 220 | LABOR- SUBCONTRACTOR
%R | 504865 | 6359 | 125569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARFF3380 | Aluminum windows | 8178 | 32 | 32 | 160 | 0 | 162.25 | 162.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-07 08:00 | 2014-05-29 17:00 |  | 2014-05-03 08:00 | 2014-05-25 17:00 | 2014-05-03 08:00 | 2014-05-25 17:00 | 2014-05-03 08:00 | 2014-05-25 17:00 | 2014-05-07 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | 0NK96bRmQ3+cbQiqO+HC0w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31180 | N | N | 15 | FIRST FLOORS |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 162.25 | LABOR- SUBCONTRACTOR
%R | 504866 | 6359 | 125569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARFF3375 | Carpentry & Joinery Works | 8178 | 0 | 0 | 200 | 0 | 1100 | 1100 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-01 08:00 | 2014-05-29 17:00 |  | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | 90V9C0oKQQ2pag8jA+hkfg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31180 | N | N | 15 | FIRST FLOORS |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1100 | LABOR- SUBCONTRACTOR
%R | 504867 | 6359 | 125569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARFF3390 | Installation of Granite Counter Top | 8171 | 8 | 8 | 160 | 0 | 88 | 88 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-14 08:00 | 2014-06-05 17:00 |  | 2014-05-13 08:00 | 2014-06-04 17:00 | 2014-05-13 08:00 | 2014-06-04 17:00 | 2014-05-13 08:00 | 2014-06-04 17:00 | 2014-05-14 08:00 | 2014-06-05 17:00 |  | PT_Normal |  |  |  |  | 04qiTkNaTBq+Zaq73vuPlA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31180 | N | N | 15 | FIRST FLOORS |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 88 | GRANITE MASON SK
%R | 504868 | 6359 | 125569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARFF3385 | Handrail & Balustrade | 8178 | 0 | 0 | 160 | 0 | 787.5 | 787.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-06-04 17:00 |  | 2014-05-13 08:00 | 2014-06-04 17:00 | 2014-05-13 08:00 | 2014-06-04 17:00 | 2014-05-13 08:00 | 2014-06-04 17:00 | 2014-05-13 08:00 | 2014-06-04 17:00 |  | PT_Normal |  |  |  |  | Xu5rvP8bTquG09Ymrk/CFg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31180 | N | N | 15 | FIRST FLOORS |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 787.5 | LABOR- SUBCONTRACTOR
%R | 504869 | 6359 | 125569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARFF3395 | Final Painting | 8178 | 0 | 0 | 200 | 0 | 4742.75 | 4742.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | WdqPw8oURDK92kKIk1gpaw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31180 | N | N | 15 | FIRST FLOORS |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 4742.75 | LABOR- SUBCONTRACTOR
%R | 504870 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3000 | Block work | 8168 | 144 | 0 | 200 | 0 | 9737.5 | 9737.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-31 08:00 | 2014-01-28 17:00 |  | 2013-12-09 08:00 | 2014-01-07 17:00 | 2013-12-09 08:00 | 2014-01-07 17:00 | 2013-12-09 08:00 | 2014-01-07 17:00 | 2013-12-31 08:00 | 2014-01-28 17:00 |  | PT_Normal |  |  |  |  | KmV7fDyzSzWPOPoxd6lb6g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 9737.5 | BLOCK MASON SK
%R | 504871 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3005 | Plastering work | 8169 | 144 | 0 | 200 | 0 | 13637.5 | 13637.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-20 17:00 |  | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | ZK14TmHkRwOYiG4suoJ48A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 13637.5 | PLASTER MASON SK
%R | 504872 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3010 | Flooring screed | 8164 | 208 | 64 | 168 | 0 | 1580.25 | 1580.25 | 168 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-03-05 17:00 |  | 2014-01-09 08:00 | 2014-02-02 17:00 | 2014-01-09 08:00 | 2014-02-02 17:00 | 2014-01-09 08:00 | 2014-02-02 17:00 | 2014-02-09 08:00 | 2014-03-05 17:00 |  | PT_Normal |  |  |  |  | 8YBwcMq5TBqq1JGlt6IDhA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1580.25 | SCREED MASON SK
%R | 504873 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 144 | 0 | 120 | 0 | 247.5 | 247.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-02-26 17:00 |  | 2014-01-19 08:00 | 2014-02-04 17:00 | 2014-01-19 08:00 | 2014-02-04 17:00 | 2014-01-19 08:00 | 2014-02-04 17:00 | 2014-02-09 08:00 | 2014-02-26 17:00 |  | PT_Normal |  |  |  |  | 1OwEdq04R2m/IDy2dvFItg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 247.5 | LABOR- SUBCONTRACTOR
%R | 504874 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3030 | Paint First coat | 8178 | 256 | 0 | 200 | 0 | 5425.75 | 5425.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-25 08:00 | 2014-03-25 17:00 |  | 2014-01-18 08:00 | 2014-02-16 17:00 | 2014-01-18 08:00 | 2014-02-16 17:00 | 2014-01-18 08:00 | 2014-02-16 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 |  | PT_Normal |  |  |  |  | 53XiOUzUQsimnHKBXj2Zlg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 5425.75 | LABOR- SUBCONTRACTOR
%R | 504875 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3020 | Ceramic Wall Tiling | 8170 | 144 | 0 | 200 | 0 | 4428.5 | 4428.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-16 17:00 |  | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | 3nqKtna6RyqEd5KD5zOA+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 4428.5 | TILE MASON SK
%R | 504876 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3025 | Porcelain Tile flooring | 8170 | 144 | 0 | 200 | 0 | 1743.75 | 1743.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-22 17:00 |  | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01; period 2: 2014-AP03 |  | 871.875 | TILE MASON SK
%R | 504877 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3040 | Cobble Tile flooring | 8170 | 168 | 0 | 120 | 0 | 741 | 741 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-24 08:00 | 2014-04-09 17:00 |  | 2014-02-27 08:00 | 2014-03-16 17:00 | 2014-02-27 08:00 | 2014-03-16 17:00 | 2014-02-27 08:00 | 2014-03-16 17:00 | 2014-03-24 08:00 | 2014-04-09 17:00 |  | PT_Normal |  |  |  |  | CZxVHX9DQ46LTurM+8Kl1Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 741 | TILE MASON SK
%R | 504878 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 184 | 16 | 120 | 0 | 761.5 | 761.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-05 17:00 |  | 2014-02-20 08:00 | 2014-03-09 17:00 | 2014-02-20 08:00 | 2014-03-09 17:00 | 2014-02-20 08:00 | 2014-03-09 17:00 | 2014-03-19 08:00 | 2014-04-05 17:00 |  | PT_Normal |  |  |  |  | RcT7TAknTJCFu+J7uNsj2w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 761.5 | TILE MASON SK
%R | 504879 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 168 | 0 | 160 | 0 | 875 | 875 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-01 08:00 | 2014-04-23 17:00 |  | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-04-01 08:00 | 2014-04-23 17:00 |  | PT_Normal |  |  |  |  | VIJnvLvRQAOFIrTgXBXUDA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 875 | GRANITE MASON SK
%R | 504880 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3045 | Fixing of Suspension systems | 8178 | 144 | 0 | 160 | 0 | 1455.05 | 1455.05 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-04-02 17:00 |  | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-03-11 08:00 | 2014-04-02 17:00 |  | PT_Normal |  |  |  |  | sZZ4HlT0T/a+3jY3MuO7qw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1455.05 | LABOR- SUBCONTRACTOR
%R | 504881 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3055 | Aluminum tile false ceiling | 8178 | 168 | 24 | 200 | 0 | 150 | 150 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-23 08:00 | 2014-04-20 17:00 |  | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | cQcux511RUeH4ePPDaJtdQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 75 | LABOR- SUBCONTRACTOR
%R | 504882 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3060 | Gypsum board false ceiling | 8178 | 144 | 0 | 200 | 0 | 1335.15 | 1335.15 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-23 08:00 | 2014-04-20 17:00 |  | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | ZYBzMBNDRhWSPrh8puu6Pw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1335.15 | LABOR- SUBCONTRACTOR
%R | 504883 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3065 | Wooden door & PVC Door | 8178 | 168 | 0 | 120 | 0 | 308 | 308 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-01 17:00 |  | 2014-03-22 08:00 | 2014-04-07 17:00 | 2014-03-22 08:00 | 2014-04-07 17:00 | 2014-03-22 08:00 | 2014-04-07 17:00 | 2014-04-15 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | VoQZoQDrSNOk7nOhb1AcaA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 308 | LABOR- SUBCONTRACTOR
%R | 504884 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3070 | Aluminum doors | 8178 | 168 | 0 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-21 08:00 | 2014-05-07 17:00 |  | 2014-03-27 08:00 | 2014-04-13 17:00 | 2014-03-27 08:00 | 2014-04-13 17:00 | 2014-03-27 08:00 | 2014-04-13 17:00 | 2014-04-21 08:00 | 2014-05-07 17:00 |  | PT_Normal |  |  |  |  | 8CWft2q/QpmuEwuF3ufeyQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 176 | LABOR- SUBCONTRACTOR
%R | 504885 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3080 | Aluminum windows | 8178 | 248 | 40 | 160 | 0 | 162.25 | 162.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-10 08:00 | 2014-06-01 17:00 |  | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-05-10 08:00 | 2014-06-01 17:00 |  | PT_Normal |  |  |  |  | uD4EligxRjKp5UxGcsFM3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 162.25 | LABOR- SUBCONTRACTOR
%R | 504886 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3075 | Carpentry & Joinery Works | 8178 | 168 | 0 | 160 | 0 | 572 | 572 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-27 08:00 | 2014-05-19 17:00 |  | 2014-04-02 08:00 | 2014-04-24 17:00 | 2014-04-02 08:00 | 2014-04-24 17:00 | 2014-04-02 08:00 | 2014-04-24 17:00 | 2014-04-27 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | F+MYiG2qSwqlFUnoLaKAEw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 572 | LABOR- SUBCONTRACTOR
%R | 504887 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3090 | Installation of Granite Counter Top | 8171 | 168 | 0 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-10 08:00 | 2014-05-26 17:00 |  | 2014-04-15 08:00 | 2014-05-01 17:00 | 2014-04-15 08:00 | 2014-05-01 17:00 | 2014-04-15 08:00 | 2014-05-01 17:00 | 2014-05-10 08:00 | 2014-05-26 17:00 |  | PT_Normal |  |  |  |  | fM4F9JwESa6CnoGzF8nppQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 176 | GRANITE MASON SK
%R | 504888 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3085 | S.S.Balustrade | 8178 | 208 | 40 | 160 | 0 | 262.5 | 262.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-06-02 17:00 |  | 2014-04-10 08:00 | 2014-05-03 17:00 | 2014-04-10 08:00 | 2014-05-03 17:00 | 2014-04-10 08:00 | 2014-05-03 17:00 | 2014-05-11 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | dRAnKdgHRbuzUUjrkqf+Fg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 262.5 | LABOR- SUBCONTRACTOR
%R | 504889 | 6359 | 125570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARGF3095 | Final Painting | 8178 | 168 | 0 | 200 | 0 | 5425.75 | 5425.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | lFICMluwTWWtqqnxZX0vNQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31170 | N | N | 10 | GROUND FLOOR |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 5425.75 | LABOR- SUBCONTRACTOR
%R | 504890 | 6359 | 125571 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARRF3600 | Block work | 8168 | 416 | 0 | 160 | 0 | 700 | 700 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-07 08:00 | 2014-04-29 17:00 |  | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-04-07 08:00 | 2014-04-29 17:00 |  | PT_Normal |  |  |  |  | 9w1yOHhUSH2dGkCWayPjtw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31190 | N | N | 20 | ROOF |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 700 | BLOCK MASON SK
%R | 504891 | 6359 | 125571 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARRF3605 | Plastering work | 8169 | 416 | 0 | 160 | 0 | 1786.5 | 1786.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-07 17:00 |  | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-04-15 08:00 | 2014-05-07 17:00 |  | PT_Normal |  |  |  |  | JUM5uufKQo+7tjEBVHom8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31190 | N | N | 20 | ROOF |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1786.5 | PLASTER MASON SK
%R | 504892 | 6359 | 125571 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARRF3610 | Flooring screed | 8164 | 456 | 0 | 120 | 0 | 136.5 | 136.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-05 08:00 | 2014-05-21 17:00 |  | 2014-02-27 08:00 | 2014-03-16 17:00 | 2014-02-27 08:00 | 2014-03-16 17:00 | 2014-02-27 08:00 | 2014-03-16 17:00 | 2014-05-05 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | YkJ8651NRQy9BF7WUKCb1Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31190 | N | N | 20 | ROOF |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 136.5 | SCREED MASON SK
%R | 504893 | 6359 | 125571 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARRF3695 | Painting -Storage area | 8178 | 456 | 0 | 160 | 0 | 1640 | 1640 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-06-04 17:00 |  | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-05-13 08:00 | 2014-06-04 17:00 |  | PT_Normal |  |  |  |  | RefP4vVpQyi1lc3Qb9BJKQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31190 | N | N | 20 | ROOF |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1640 | LABOR- SUBCONTRACTOR
%R | 504894 | 6359 | 125571 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ4ARRF3620 | Epoxy Painting -Storage area | 8178 | 456 | 456 | 120 | 0 | 48.5 | 48.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-31 08:00 | 2014-06-16 17:00 |  | 2014-03-25 08:00 | 2014-04-10 17:00 | 2014-03-25 08:00 | 2014-04-10 17:00 | 2014-03-25 08:00 | 2014-04-10 17:00 | 2014-05-31 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | FJb4iTEaQryvlRv2gBVCJw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:55 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31190 | N | N | 20 | ROOF |  | 125568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 48.5 | LABOR- SUBCONTRACTOR

## Sheet1
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.