## joined_TASK_RSRC_WBS
%F | task_id | proj_id | wbs_id | clndr_id | phys_complete_pct | rev_fdbk_flag | lock_plan_flag | auto_compute_act_flag | complete_pct_type | task_type | duration_type | status_code | task_code | task_name | rsrc_id | total_float_hr_cnt | free_float_hr_cnt | remain_drtn_hr_cnt | act_work_qty | remain_work_qty | target_work_qty | target_drtn_hr_cnt | target_equip_qty | act_equip_qty | remain_equip_qty | cstr_date | act_start_date | act_end_date | late_start_date | late_end_date | expect_end_date | early_start_date | early_end_date | restart_date | reend_date | target_start_date | target_end_date | rem_late_start_date | rem_late_end_date | cstr_type | priority_type | suspend_date | resume_date | float_path | float_path_order | guid | tmpl_guid | cstr_date2 | cstr_type2 | driving_path_flag | act_this_per_work_qty | act_this_per_equip_qty | external_early_start_date | external_late_end_date | create_date | update_date | create_user | update_user | parent_rsrc_id | role_id | shift_id | user_id | pobs_id | rsrc_seq_num | email_addr | employee_code | office_phone | other_phone | rsrc_name | rsrc_short_name | rsrc_title_name | def_qty_per_hr | cost_qty_type | ot_factor | active_flag | def_cost_qty_link_flag | ot_flag | curr_id | unit_id | rsrc_type | rsrc_notes | load_tasks_flag | level_flag | last_checksum | obs_id | seq_num | proj_node_flag | sum_data_flag | wbs_short_name | wbs_name | phase_id | parent_wbs_id | ev_user_pct | ev_etc_user_value | orig_cost | indep_remain_total_cost | ann_dscnt_rate_pct | dscnt_period_type | indep_remain_work_qty | anticip_start_date | anticip_end_date | ev_compute_type | ev_etc_compute_type | plan_open_state | Column1 | period 1 | period 2 | period 3 | period 4 | period 5 | period 6 | period 7 | period 8 | period 9 | period 10 | labour | resource name
%R | 499287 | 6359 | 124256 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP03GNACTC9000 | Submission & Clearance of Punch list,Final Testing & Commissioning of AC Works | 8178 | 0 | 0 | 240 | 0 | 1800 | 1800 | 240 | 0 | 0 | 0 |  |  |  | 2014-08-16 08:00 | 2014-09-18 17:00 |  | 2014-08-16 08:00 | 2014-09-18 17:00 | 2014-08-16 08:00 | 2014-09-18 17:00 | 2014-08-16 08:00 | 2014-09-18 17:00 | 2014-08-16 08:00 | 2014-09-18 17:00 |  | PT_Normal |  |  |  |  | 2u4XDsnBS+KqRni2Wvb/vg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 12:04 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43370 | N | N | L45 | PACKAGE-3 |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08; period 2: 2014-AP09 |  | 900 | LABOR- SUBCONTRACTOR
%R | 499288 | 6359 | 124256 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP03GNELTC9010 | Submission & Clearance Punch list,Final Testing & Commissioning of Electrical Works | 8178 | 0 | 0 | 240 | 0 | 3600 | 3600 | 240 | 0 | 0 | 0 |  |  |  | 2014-08-16 08:00 | 2014-09-18 17:00 |  | 2014-08-16 08:00 | 2014-09-18 17:00 | 2014-08-16 08:00 | 2014-09-18 17:00 | 2014-08-16 08:00 | 2014-09-18 17:00 | 2014-08-16 08:00 | 2014-09-18 17:00 |  | PT_Normal |  |  |  |  | s2ElMOAyTjifQRHGgVQpAg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 12:07 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43370 | N | N | L45 | PACKAGE-3 |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08; period 2: 2014-AP09 |  | 1800 | LABOR- SUBCONTRACTOR
%R | 499289 | 6359 | 124256 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP03GNAB009015 | Submission & Approval of As-Built Drawings & O&M Manuals | 8176 | 0 | 0 | 160 | 0 | 320 | 320 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-08 08:00 | 2014-09-30 17:00 |  | 2014-09-08 08:00 | 2014-09-30 17:00 | 2014-09-08 08:00 | 2014-09-30 17:00 | 2014-09-08 08:00 | 2014-09-30 17:00 | 2014-09-08 08:00 | 2014-09-30 17:00 |  | PT_Normal |  |  |  |  | QNW26tBXSIO/L+hOEoFDoA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 12:11 | admin | admin | 8149 |  |  |  |  | 43530 |  |  |  |  | DRAFTMAN SK | J320 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43370 | N | N | L45 | PACKAGE-3 |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 320 | DRAFTMAN SK
%R | 499290 | 6359 | 124256 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP03GNDM009020 | Demobilization & Handing Over | 8178 | 0 | 0 | 480 | 0 | 19440 | 19440 | 480 | 0 | 0 | 0 |  |  |  | 2014-09-20 08:00 | 2014-11-30 17:00 |  | 2014-09-20 08:00 | 2014-11-30 17:00 | 2014-09-20 08:00 | 2014-11-30 17:00 | 2014-09-20 08:00 | 2014-11-30 17:00 | 2014-09-20 08:00 | 2014-11-30 17:00 |  | PT_Normal |  |  |  |  | jV3cA4nYTAGA2eek61O7pw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43370 | N | N | L45 | PACKAGE-3 |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10; period 3: 2014-AP11 |  | 6480 | LABOR- SUBCONTRACTOR
%R | 499291 | 6359 | 124256 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP03GNPLTC9005 | Submission & Clearance of Punch list, Final Testing &Commissioning of Plumbing/Drainage | 8178 | 0 | 0 | 240 | 0 | 3600 | 3600 | 240 | 0 | 0 | 0 |  |  |  | 2014-08-16 08:00 | 2014-09-18 17:00 |  | 2014-08-16 08:00 | 2014-09-18 17:00 | 2014-08-16 08:00 | 2014-09-18 17:00 | 2014-08-16 08:00 | 2014-09-18 17:00 | 2014-08-16 08:00 | 2014-09-18 17:00 |  | PT_Normal |  |  |  |  | qIt0gbX0RWyrzriWK/md4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 11:49 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43370 | N | N | L45 | PACKAGE-3 |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08; period 2: 2014-AP09 |  | 1800 | LABOR- SUBCONTRACTOR
%R | 499292 | 6359 | 124257 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP1BGNACTC9000 | Submission & Clearance of Punch list,Final Testing & Commissioning of AC Works | 8178 | 0 | 0 | 240 | 0 | 1800 | 1800 | 240 | 0 | 0 | 0 |  |  |  | 2014-12-15 08:00 | 2015-01-19 17:00 |  | 2014-12-15 08:00 | 2015-01-19 17:00 | 2014-12-15 08:00 | 2015-01-19 17:00 | 2014-12-15 08:00 | 2015-01-19 17:00 | 2014-12-15 08:00 | 2015-01-19 17:00 |  | PT_Normal |  |  |  |  | 7bPrvPGVTCibzP7lL+j3pg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 12:04 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43340 | N | N | L25 | PACKAGE-1B |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP12; period 2: 2015-AP01 |  | 900 | LABOR- SUBCONTRACTOR
%R | 499293 | 6359 | 124257 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP1BGNELTC9010 | Submission & Clearance Punch list,Final Testing & Commissioning of Electrical Works | 8178 | 0 | 0 | 240 | 0 | 3600 | 3600 | 240 | 0 | 0 | 0 |  |  |  | 2014-12-15 08:00 | 2015-01-19 17:00 |  | 2014-12-15 08:00 | 2015-01-19 17:00 | 2014-12-15 08:00 | 2015-01-19 17:00 | 2014-12-15 08:00 | 2015-01-19 17:00 | 2014-12-15 08:00 | 2015-01-19 17:00 |  | PT_Normal |  |  |  |  | VCnnZyfTRaqdeN+WTKpyBw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 12:07 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43340 | N | N | L25 | PACKAGE-1B |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP12; period 2: 2015-AP01 |  | 1800 | LABOR- SUBCONTRACTOR
%R | 499294 | 6359 | 124257 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP1BGNPLTC9005 | Submission & Clearance of Punch list, Final Testing &Commissioning of Plumbing/Drainage | 8178 | 0 | 0 | 240 | 0 | 3600 | 3600 | 240 | 0 | 0 | 0 |  |  |  | 2014-12-15 08:00 | 2015-01-19 17:00 |  | 2014-12-15 08:00 | 2015-01-19 17:00 | 2014-12-15 08:00 | 2015-01-19 17:00 | 2014-12-15 08:00 | 2015-01-19 17:00 | 2014-12-15 08:00 | 2015-01-19 17:00 |  | PT_Normal |  |  |  |  | h+hE9gIDTGa0SPWgvDMMBw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 11:49 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43340 | N | N | L25 | PACKAGE-1B |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP12; period 2: 2015-AP01 |  | 1800 | LABOR- SUBCONTRACTOR
%R | 499295 | 6359 | 124257 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP1BGNAB009015 | Submission & Approval of As-Built Drawings & O&M Manuals | 8176 | 0 | 0 | 160 | 0 | 320 | 320 | 160 | 0 | 0 | 0 |  |  |  | 2015-01-08 08:00 | 2015-01-31 17:00 |  | 2015-01-08 08:00 | 2015-01-31 17:00 | 2015-01-08 08:00 | 2015-01-31 17:00 | 2015-01-08 08:00 | 2015-01-31 17:00 | 2015-01-08 08:00 | 2015-01-31 17:00 |  | PT_Normal |  |  |  |  | XZkGXLwaQKqRnJk31JZr5Q |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 12:11 | admin | admin | 8149 |  |  |  |  | 43530 |  |  |  |  | DRAFTMAN SK | J320 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43340 | N | N | L25 | PACKAGE-1B |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2015-AP01 |  | 320 | DRAFTMAN SK
%R | 499296 | 6359 | 124257 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP1BGNDM009020 | Demobilization & Handing Over | 8178 | 0 | 0 | 480 | 0 | 18500 | 18500 | 480 | 0 | 0 | 0 |  |  |  | 2015-01-20 08:00 | 2015-03-31 17:00 |  | 2015-01-20 08:00 | 2015-03-31 17:00 | 2015-01-20 08:00 | 2015-03-31 17:00 | 2015-01-20 08:00 | 2015-03-31 17:00 | 2015-01-20 08:00 | 2015-03-31 17:00 |  | PT_Normal |  |  |  |  | TeJ8LnOnSkyqJtUhHLBasA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43340 | N | N | L25 | PACKAGE-1B |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2015-AP01; period 2: 2015-AP02; period 3: 2015-AP03 |  | 6166.6667 | LABOR- SUBCONTRACTOR
%R | 499297 | 6359 | 124258 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP2AGNAB009015 | Submission & Approval of As-Built Drawings & O&M Manuals | 8176 | 0 | 0 | 160 | 0 | 320 | 320 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-08 08:00 | 2014-07-30 17:00 |  | 2014-07-08 08:00 | 2014-07-30 17:00 | 2014-07-08 08:00 | 2014-07-30 17:00 | 2014-07-08 08:00 | 2014-07-30 17:00 | 2014-07-08 08:00 | 2014-07-30 17:00 |  | PT_Normal |  |  |  |  | R/e3eIg5QjeZwO0G6j1N9Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 12:11 | admin | admin | 8149 |  |  |  |  | 43530 |  |  |  |  | DRAFTMAN SK | J320 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43350 | N | N | L35 | PACKAGE-2A |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 320 | DRAFTMAN SK
%R | 499298 | 6359 | 124258 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP2AGNDM009020 | Demobilization & Handing Over | 8178 | 0 | 0 | 480 | 0 | 23280 | 23280 | 480 | 0 | 0 | 0 |  |  |  | 2014-07-20 08:00 | 2014-09-30 17:00 |  | 2014-07-20 08:00 | 2014-09-30 17:00 | 2014-07-20 08:00 | 2014-09-30 17:00 | 2014-07-20 08:00 | 2014-09-30 17:00 | 2014-07-20 08:00 | 2014-09-30 17:00 |  | PT_Normal |  |  |  |  | lKIW5RA9TlCCYEm9T+6VgA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43350 | N | N | L35 | PACKAGE-2A |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08; period 3: 2014-AP09 |  | 7760 | LABOR- SUBCONTRACTOR
%R | 499299 | 6359 | 124258 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP2AGNACTC9000 | Submission & Clearance of Punch list,Final Testing & Commissioning of AC Works | 8178 | 0 | 0 | 240 | 0 | 1800 | 1800 | 240 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-19 17:00 |  | 2014-06-15 08:00 | 2014-07-19 17:00 | 2014-06-15 08:00 | 2014-07-19 17:00 | 2014-06-15 08:00 | 2014-07-19 17:00 | 2014-06-15 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | MD7u8W8mSmaq1z6UxhELEA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 12:04 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43350 | N | N | L35 | PACKAGE-2A |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06; period 2: 2014-AP07 |  | 900 | LABOR- SUBCONTRACTOR
%R | 499300 | 6359 | 124258 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP2AGNELTC9010 | Submission & Clearance Punch list,Final Testing & Commissioning of Electrical Works | 8178 | 0 | 0 | 240 | 0 | 3600 | 3600 | 240 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-19 17:00 |  | 2014-06-15 08:00 | 2014-07-19 17:00 | 2014-06-15 08:00 | 2014-07-19 17:00 | 2014-06-15 08:00 | 2014-07-19 17:00 | 2014-06-15 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | bSWKsWpZQCuZoe16ELCVQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 12:07 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43350 | N | N | L35 | PACKAGE-2A |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06; period 2: 2014-AP07 |  | 1800 | LABOR- SUBCONTRACTOR
%R | 499301 | 6359 | 124258 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP2AGNPLTC9005 | Submission & Clearance of Punch list, Final Testing &Commissioning of Plumbing/Drainage | 8178 | 0 | 0 | 240 | 0 | 3600 | 3600 | 240 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-19 17:00 |  | 2014-06-15 08:00 | 2014-07-19 17:00 | 2014-06-15 08:00 | 2014-07-19 17:00 | 2014-06-15 08:00 | 2014-07-19 17:00 | 2014-06-15 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | ArGoIniNSD+oOHOSP/rMZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 11:49 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43350 | N | N | L35 | PACKAGE-2A |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06; period 2: 2014-AP07 |  | 1800 | LABOR- SUBCONTRACTOR
%R | 499302 | 6359 | 124259 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP1AGNPLTC9005 | Submission & Clearance of Punch list, Final Testing &Commissioning of Plumbing/Drainage | 8178 | 0 | 0 | 240 | 0 | 3600 | 3600 | 240 | 0 | 0 | 0 |  |  |  | 2014-12-15 08:00 | 2015-01-19 17:00 |  | 2014-12-15 08:00 | 2015-01-19 17:00 | 2014-12-15 08:00 | 2015-01-19 17:00 | 2014-12-15 08:00 | 2015-01-19 17:00 | 2014-12-15 08:00 | 2015-01-19 17:00 |  | PT_Normal |  |  |  |  | hxCSlnp9QQ6h8ifN9VHI0A |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 11:49 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43330 | N | N | L20 | PACKAGE-1A |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP12; period 2: 2015-AP01 |  | 1800 | LABOR- SUBCONTRACTOR
%R | 499303 | 6359 | 124259 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP1AGNACTC9000 | Submission & Clearance of Punch list,Final Testing & Commissioning of AC Works | 8178 | 0 | 0 | 240 | 0 | 1800 | 1800 | 240 | 0 | 0 | 0 |  |  |  | 2014-12-15 08:00 | 2015-01-19 17:00 |  | 2014-12-15 08:00 | 2015-01-19 17:00 | 2014-12-15 08:00 | 2015-01-19 17:00 | 2014-12-15 08:00 | 2015-01-19 17:00 | 2014-12-15 08:00 | 2015-01-19 17:00 |  | PT_Normal |  |  |  |  | hv3xza5ORUqOutXJrN075g |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 12:04 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43330 | N | N | L20 | PACKAGE-1A |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP12; period 2: 2015-AP01 |  | 900 | LABOR- SUBCONTRACTOR
%R | 499304 | 6359 | 124259 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP1AGNELTC9010 | Submission & Clearance Punch list,Final Testing & Commissioning of Electrical Works | 8178 | 0 | 0 | 240 | 0 | 3600 | 3600 | 240 | 0 | 0 | 0 |  |  |  | 2014-12-15 08:00 | 2015-01-19 17:00 |  | 2014-12-15 08:00 | 2015-01-19 17:00 | 2014-12-15 08:00 | 2015-01-19 17:00 | 2014-12-15 08:00 | 2015-01-19 17:00 | 2014-12-15 08:00 | 2015-01-19 17:00 |  | PT_Normal |  |  |  |  | m8FaUSU9T9+53nwXD5sIJQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 12:07 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43330 | N | N | L20 | PACKAGE-1A |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP12; period 2: 2015-AP01 |  | 1800 | LABOR- SUBCONTRACTOR
%R | 499305 | 6359 | 124259 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP1AGNAB009015 | Submission & Approval of As-Built Drawings & O&M Manuals | 8176 | 0 | 0 | 160 | 0 | 320 | 320 | 160 | 0 | 0 | 0 |  |  |  | 2015-01-08 08:00 | 2015-01-31 17:00 |  | 2015-01-08 08:00 | 2015-01-31 17:00 | 2015-01-08 08:00 | 2015-01-31 17:00 | 2015-01-08 08:00 | 2015-01-31 17:00 | 2015-01-08 08:00 | 2015-01-31 17:00 |  | PT_Normal |  |  |  |  | I0RR+ALxQF6LAHTFoyND4A |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 12:11 | admin | admin | 8149 |  |  |  |  | 43530 |  |  |  |  | DRAFTMAN SK | J320 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43330 | N | N | L20 | PACKAGE-1A |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2015-AP01 |  | 320 | DRAFTMAN SK
%R | 499306 | 6359 | 124259 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP1AGNDM009020 | Demobilization & Handing Over | 8178 | 0 | 0 | 480 | 0 | 18500 | 18500 | 480 | 0 | 0 | 0 |  |  |  | 2015-01-20 08:00 | 2015-03-31 17:00 |  | 2015-01-20 08:00 | 2015-03-31 17:00 | 2015-01-20 08:00 | 2015-03-31 17:00 | 2015-01-20 08:00 | 2015-03-31 17:00 | 2015-01-20 08:00 | 2015-03-31 17:00 |  | PT_Normal |  |  |  |  | BzefXAONQY2NXNSOAVUWlw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43330 | N | N | L20 | PACKAGE-1A |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2015-AP01; period 2: 2015-AP02; period 3: 2015-AP03 |  | 6166.6667 | LABOR- SUBCONTRACTOR
%R | 499307 | 6359 | 124260 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP2BGNAB009015 | Submission & Approval of As-Built Drawings & O&M Manuals | 8176 | 0 | 0 | 160 | 0 | 320 | 320 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-08 08:00 | 2014-07-30 17:00 |  | 2014-07-08 08:00 | 2014-07-30 17:00 | 2014-07-08 08:00 | 2014-07-30 17:00 | 2014-07-08 08:00 | 2014-07-30 17:00 | 2014-07-08 08:00 | 2014-07-30 17:00 |  | PT_Normal |  |  |  |  | JT+8+t0jSxqlre4nigGngg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 12:11 | admin | admin | 8149 |  |  |  |  | 43530 |  |  |  |  | DRAFTMAN SK | J320 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43360 | N | N | L40 | PACKAGE-2B |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 320 | DRAFTMAN SK
%R | 499308 | 6359 | 124260 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP2BGNDM009020 | Demobilization & Handing Over | 8178 | 0 | 0 | 480 | 0 | 23280 | 23280 | 480 | 0 | 0 | 0 |  |  |  | 2014-07-20 08:00 | 2014-09-30 17:00 |  | 2014-07-20 08:00 | 2014-09-30 17:00 | 2014-07-20 08:00 | 2014-09-30 17:00 | 2014-07-20 08:00 | 2014-09-30 17:00 | 2014-07-20 08:00 | 2014-09-30 17:00 |  | PT_Normal |  |  |  |  | ptLyWXX7RbKun7I0RXCJRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43360 | N | N | L40 | PACKAGE-2B |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08; period 3: 2014-AP09 |  | 7760 | LABOR- SUBCONTRACTOR
%R | 499309 | 6359 | 124260 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP2BGNELTC9010 | Submission & Clearance Punch list,Final Testing & Commissioning of Electrical Works | 8178 | 0 | 0 | 240 | 0 | 3600 | 3600 | 240 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-19 17:00 |  | 2014-06-15 08:00 | 2014-07-19 17:00 | 2014-06-15 08:00 | 2014-07-19 17:00 | 2014-06-15 08:00 | 2014-07-19 17:00 | 2014-06-15 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | oowqqIYxT26L4iAql9maXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 12:07 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43360 | N | N | L40 | PACKAGE-2B |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06; period 2: 2014-AP07 |  | 1800 | LABOR- SUBCONTRACTOR
%R | 499310 | 6359 | 124260 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP2BGNPLTC9005 | Submission & Clearance of Punch list, Final Testing &Commissioning of Plumbing/Drainage | 8178 | 0 | 0 | 240 | 0 | 3600 | 3600 | 240 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-19 17:00 |  | 2014-06-15 08:00 | 2014-07-19 17:00 | 2014-06-15 08:00 | 2014-07-19 17:00 | 2014-06-15 08:00 | 2014-07-19 17:00 | 2014-06-15 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | xpYVx3SKShuIQCVdtHhqCw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 11:49 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43360 | N | N | L40 | PACKAGE-2B |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06; period 2: 2014-AP07 |  | 1800 | LABOR- SUBCONTRACTOR
%R | 499311 | 6359 | 124260 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHHANP2BGNACTC9000 | Submission & Clearance of Punch list,Final Testing & Commissioning of AC Works | 8178 | 0 | 0 | 240 | 0 | 1800 | 1800 | 240 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-19 17:00 |  | 2014-06-15 08:00 | 2014-07-19 17:00 | 2014-06-15 08:00 | 2014-07-19 17:00 | 2014-06-15 08:00 | 2014-07-19 17:00 | 2014-06-15 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | A9JhNNqCSOedvl0yvB0LVg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-21 12:04 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43360 | N | N | L40 | PACKAGE-2B |  | 124255 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06; period 2: 2014-AP07 |  | 900 | LABOR- SUBCONTRACTOR
%R | 499312 | 6359 | 124262 | 13662 | 0 | N | N | N | CP_Drtn | TT_FinMile | DT_FixedDUR2 | TK_NotStart | DUKHKYDP020000002000 | Package -2 (Milestone-2) -23 Months |  | 0 | 1216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2014-09-30 17:00 |  |  | 2014-09-30 17:00 | 2014-09-30 17:00 |  | 2014-09-30 17:00 | 2014-09-30 17:00 | 2014-09-30 17:00 | 2014-09-30 17:00 | 2014-09-30 17:00 | 2014-09-30 17:00 | 2014-09-30 17:00 | 2014-09-30 17:00 | CS_MEOB | PT_Normal |  |  |  |  | ZC6cvhjDQySEKXDWj7wGCA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 28320 | N | N | L30 | PACKAGE-2 |  | 124261 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 0 | 0
%R | 499313 | 6359 | 124263 | 13662 | 0 | N | N | N | CP_Drtn | TT_FinMile | DT_FixedDUR2 | TK_NotStart | DUKHKYDP030000003000 | Package -3 (Milestone -3) -25 Months |  | 0 | 816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2014-11-30 17:00 |  |  | 2014-11-30 17:00 | 2014-11-30 17:00 |  | 2014-11-30 17:00 | 2014-11-30 17:00 | 2014-11-30 17:00 | 2014-11-30 17:00 | 2014-11-30 17:00 | 2014-11-30 17:00 | 2014-11-30 17:00 | 2014-11-30 17:00 | CS_MEOB | PT_Normal |  |  |  |  | IP4iNwGeTe2p2ShTaJvdiA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 28350 | N | N | L45 | PACKAGE-3 |  | 124261 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 0 | 0
%R | 499314 | 6359 | 124264 | 13663 | 0 | N | N | N | CP_Drtn | TT_Mile | DT_FixedDUR2 | TK_NotStart | DUKHKYDGEN0000001000 | Project Commencement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2012-11-01 08:00 | 2012-11-01 08:00 |  | 2012-11-01 08:00 | 2012-11-01 08:00 | 2012-11-01 08:00 | 2012-11-01 08:00 | 2012-11-01 08:00 | 2012-11-01 08:00 | 2012-11-01 08:00 | 2012-11-01 08:00 |  | PT_Normal |  |  |  |  | K2sEZS8NTwW7Vg58GTYpfw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 28280 | N | N | L10 | GENERAL |  | 124261 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499315 | 6359 | 124264 | 13662 | 0 | N | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | DUKHKYDGEN0000002000 | Project Completion Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2015-03-31 17:00 | 2015-03-31 17:00 |  | 2015-03-31 17:00 | 2015-03-31 17:00 | 2015-03-31 17:00 | 2015-03-31 17:00 | 2015-03-31 17:00 | 2015-03-31 17:00 | 2015-03-31 17:00 | 2015-03-31 17:00 |  | PT_Normal |  |  |  |  | Dtu5DUBzSbirUCdANWIQOQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28280 | N | N | L10 | GENERAL |  | 124261 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2015-AP03 |  | 0 | 0
%R | 499316 | 6359 | 124265 | 13662 | 0 | N | N | N | CP_Drtn | TT_FinMile | DT_FixedDUR2 | TK_NotStart | DUKHKYDP010000001000 | Package -1 (Milestone -1) -29 Months |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2015-03-31 17:00 | 2015-03-31 17:00 |  | 2015-03-31 17:00 | 2015-03-31 17:00 | 2015-03-31 17:00 | 2015-03-31 17:00 | 2015-03-31 17:00 | 2015-03-31 17:00 | 2015-03-31 17:00 | 2015-03-31 17:00 |  | PT_Normal |  |  |  |  | A/hPO32DTTirjRb3NJAMew |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28290 | N | N | L15 | PACKAGE-1 |  | 124261 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2015-AP03 |  | 0 | 0
%R | 499317 | 6359 | 124270 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWARAP4930 | Doors & Window Drawings-App |  | 488 | 280 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-17 08:00 | 2013-07-21 17:00 |  | 2013-04-07 08:00 | 2013-05-11 17:00 | 2013-04-07 08:00 | 2013-05-11 17:00 | 2013-04-07 08:00 | 2013-05-11 17:00 | 2013-06-17 08:00 | 2013-07-21 17:00 |  | PT_Normal |  |  |  |  | or2k3ktZRb+UMSNQQ7uXcw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29110 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499318 | 6359 | 124270 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWARAP4940 | Carpentry & Joinery Drawings-App |  | 664 | 320 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-30 08:00 | 2013-09-05 17:00 |  | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-07-30 08:00 | 2013-09-05 17:00 |  | PT_Normal |  |  |  |  | zi14dbEBTJG8D9sbutAyyA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29110 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499319 | 6359 | 124270 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWARAP4850 | Ground Floor Plan-App |  | 888 | 232 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-04 08:00 | 2013-07-08 17:00 |  | 2013-01-24 08:00 | 2013-02-28 17:00 | 2013-01-24 08:00 | 2013-02-28 17:00 | 2013-01-24 08:00 | 2013-02-28 17:00 | 2013-06-04 08:00 | 2013-07-08 17:00 |  | PT_Normal |  |  |  |  | sBtue8ZnSW2p/d8OfRNldw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29110 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499320 | 6359 | 124270 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWARAP4870 | Roof Floor Plan-App |  | 680 | 192 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-13 08:00 | 2013-06-16 17:00 |  | 2013-02-02 08:00 | 2013-03-09 17:00 | 2013-02-02 08:00 | 2013-03-09 17:00 | 2013-02-02 08:00 | 2013-03-09 17:00 | 2013-05-13 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | eZ1mnA39QD2chha4W+wz5Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29110 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499321 | 6359 | 124270 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWARAP4880 | Ceramic Flooring & Wall Drawings-App |  | 624 | 288 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-14 08:00 | 2013-06-17 17:00 |  | 2013-02-11 08:00 | 2013-03-18 17:00 | 2013-02-11 08:00 | 2013-03-18 17:00 | 2013-02-11 08:00 | 2013-03-18 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 |  | PT_Normal |  |  |  |  | 2Kzj8xfZQF+MeFpgKpPQqg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29110 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499322 | 6359 | 124270 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWARAP4890 | Porcelain Floor Drawings-App |  | 696 | 288 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-25 08:00 | 2013-06-27 17:00 |  | 2013-02-11 08:00 | 2013-03-18 17:00 | 2013-02-11 08:00 | 2013-03-18 17:00 | 2013-02-11 08:00 | 2013-03-18 17:00 | 2013-05-25 08:00 | 2013-06-27 17:00 |  | PT_Normal |  |  |  |  | 4jwa14WERrW/qhvwYh94pw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29110 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499323 | 6359 | 124270 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWARAP4900 | Cobble & Slate Flooring Drawings-App |  | 944 | 288 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-30 08:00 | 2013-08-03 17:00 |  | 2013-02-11 08:00 | 2013-03-18 17:00 | 2013-02-11 08:00 | 2013-03-18 17:00 | 2013-02-11 08:00 | 2013-03-18 17:00 | 2013-06-30 08:00 | 2013-08-03 17:00 |  | PT_Normal |  |  |  |  | 3A1+CjrtStuBND5GcV5s7Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29110 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499324 | 6359 | 124270 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWARAP4910 | Gypsum False Ceiling Drawings-App |  | 536 | 280 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-18 08:00 | 2013-07-22 17:00 |  | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-06-18 08:00 | 2013-07-22 17:00 |  | PT_Normal |  |  |  |  | qdp9JQkiQ7WhabKhV+/Yiw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29110 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499325 | 6359 | 124271 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWARSM4850 | Ground Floor Plan-Sub |  | 624 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-09 08:00 | 2013-04-25 17:00 |  | 2013-01-07 08:00 | 2013-01-23 17:00 | 2013-01-07 08:00 | 2013-01-23 17:00 | 2013-01-07 08:00 | 2013-01-23 17:00 | 2013-04-09 08:00 | 2013-04-25 17:00 |  | PT_Normal |  |  |  |  | e1yLr1UZQiGnQYwbvCo3ZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29100 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499326 | 6359 | 124271 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWARSM4870 | Roof Floor Plan-Sub |  | 664 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-23 08:00 | 2013-05-09 17:00 |  | 2013-01-15 08:00 | 2013-01-31 17:00 | 2013-01-15 08:00 | 2013-01-31 17:00 | 2013-01-15 08:00 | 2013-01-31 17:00 | 2013-04-23 08:00 | 2013-05-09 17:00 |  | PT_Normal |  |  |  |  | YugQjbaaSPefIIocDLtWXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29100 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499327 | 6359 | 124271 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWARSM4880 | Ceramic Flooring & Wall Drawings-Sub |  | 624 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-27 08:00 | 2013-05-13 17:00 |  | 2013-01-24 08:00 | 2013-02-10 17:00 | 2013-01-24 08:00 | 2013-02-10 17:00 | 2013-01-24 08:00 | 2013-02-10 17:00 | 2013-04-27 08:00 | 2013-05-13 17:00 |  | PT_Normal |  |  |  |  | hUVRbipMRTC1jpVWUHHHZg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29100 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499328 | 6359 | 124271 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWARSM4890 | Porcelain Floor Drawings-Sub |  | 696 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-07 08:00 | 2013-05-23 17:00 |  | 2013-01-24 08:00 | 2013-02-10 17:00 | 2013-01-24 08:00 | 2013-02-10 17:00 | 2013-01-24 08:00 | 2013-02-10 17:00 | 2013-05-07 08:00 | 2013-05-23 17:00 |  | PT_Normal |  |  |  |  | kcd/psEKTKuaJC2vATMy0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29100 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499329 | 6359 | 124271 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWARSM4900 | Cobble & Slate Flooring Drawings-Sub |  | 944 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-12 08:00 | 2013-06-29 17:00 |  | 2013-01-24 08:00 | 2013-02-10 17:00 | 2013-01-24 08:00 | 2013-02-10 17:00 | 2013-01-24 08:00 | 2013-02-10 17:00 | 2013-06-12 08:00 | 2013-06-29 17:00 |  | PT_Normal |  |  |  |  | b3im1nf0SEOGZilWM2h+ew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29100 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499330 | 6359 | 124271 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWARSM4910 | Gypsum False Ceiling Drawings-Sub |  | 536 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-01 08:00 | 2013-06-17 17:00 |  | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-06-01 08:00 | 2013-06-17 17:00 |  | PT_Normal |  |  |  |  | PcEAbJJLTPWlpTcwrfpmXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29100 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499331 | 6359 | 124271 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWARSM4930 | Doors & window Drawings-Sub |  | 488 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-30 08:00 | 2013-06-16 17:00 |  | 2013-03-20 08:00 | 2013-04-06 17:00 | 2013-03-20 08:00 | 2013-04-06 17:00 | 2013-03-20 08:00 | 2013-04-06 17:00 | 2013-05-30 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | 0caG/hnMTl+iQATB4nni6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29100 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499332 | 6359 | 124271 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWARSM4940 | Carpentry & Joinery Drawings-Sub |  | 664 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-13 08:00 | 2013-07-29 17:00 |  | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-07-13 08:00 | 2013-07-29 17:00 |  | PT_Normal |  |  |  |  | lJLX+UdCToGVUSJq7ovIjA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29100 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499333 | 6359 | 124273 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWMESM5010 | Plumbing Layout & Details Drawings-Sub |  | 424 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-24 08:00 | 2013-05-11 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-04-24 08:00 | 2013-05-11 17:00 |  | PT_Normal |  |  |  |  | GSwww5lpR3i5fX4eo6hKFQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29160 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124272 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499334 | 6359 | 124273 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWMESM5020 | Drainage Layout & Details Drawings-Sub |  | 360 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-15 08:00 | 2013-05-01 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 |  | PT_Normal |  |  |  |  | iOWpKr3pT2GaI/F69d1icg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29160 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124272 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499335 | 6359 | 124273 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWMESM5030 | Fire Fighting Layout & Details Drawings-Sub |  | 360 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-02 08:00 | 2013-05-19 17:00 |  | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 |  | PT_Normal |  |  |  |  | ZwOvqOf3TkSlAIfYD/iTMA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29160 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124272 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499336 | 6359 | 124273 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWMESM5040 | AC Layout & Details Drawings-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-20 08:00 | 2013-06-05 17:00 |  | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 |  | PT_Normal |  |  |  |  | EwjV9dXkS8uuNl8U6kvEYw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29160 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124272 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 499337 | 6359 | 124274 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWMEAP5010 | Plumbing Layout & Details Drawings-App |  | 424 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-12 08:00 | 2013-06-15 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-05-12 08:00 | 2013-06-15 17:00 |  | PT_Normal |  |  |  |  | H4/MvUOXSAqjaVtA896VbA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29170 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124272 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499338 | 6359 | 124274 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWMEAP5020 | Drainage Layout & Details Drawings-App |  | 424 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-12 08:00 | 2013-06-15 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-05-12 08:00 | 2013-06-15 17:00 |  | PT_Normal |  |  |  |  | sVnxP+QIQFKd/Q6rACTLQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29170 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124272 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499339 | 6359 | 124274 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWMEAP5030 | Fire Fighting Layout & Details Drawings-App |  | 1160 | 440 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-17 08:00 | 2013-10-23 17:00 |  | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-09-17 08:00 | 2013-10-23 17:00 |  | PT_Normal |  |  |  |  | mJY/le8TSAamQ0rjpqBiog |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29170 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124272 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499340 | 6359 | 124274 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWMEAP5040 | AC Layout & Details Drawings-App |  | 512 | 80 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-08-01 17:00 |  | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | p0tmacThQialiW0MfVRhIQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29170 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124272 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499341 | 6359 | 124276 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWSTAP4800 | Footing Drawings-App |  | 432 | 432 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 |  |  |  | 2013-02-10 08:00 | 2013-03-11 17:00 |  | 2012-12-08 08:00 | 2013-01-06 17:00 | 2012-12-08 08:00 | 2013-01-06 17:00 | 2012-12-08 08:00 | 2013-01-06 17:00 | 2013-02-10 08:00 | 2013-03-11 17:00 |  | PT_Normal |  |  |  |  | 5AEXPyk1TVaVtMxCbyO7Fg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29080 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124275 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499342 | 6359 | 124276 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWSTAP4810 | Grade Beam & Slab Drawings-App |  | 680 | 680 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-03-31 08:00 | 2013-05-04 17:00 |  | 2012-12-20 08:00 | 2013-01-23 17:00 | 2012-12-20 08:00 | 2013-01-23 17:00 | 2012-12-20 08:00 | 2013-01-23 17:00 | 2013-03-31 08:00 | 2013-05-04 17:00 |  | PT_Normal |  |  |  |  | 6nsqNayET/KsWOAmXWZVcg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29080 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124275 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499343 | 6359 | 124276 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWSTAP4820 | Column Drawings-App |  | 952 | 952 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-15 08:00 | 2013-06-18 17:00 |  | 2012-12-26 08:00 | 2013-01-29 17:00 | 2012-12-26 08:00 | 2013-01-29 17:00 | 2012-12-26 08:00 | 2013-01-29 17:00 | 2013-05-15 08:00 | 2013-06-18 17:00 |  | PT_Normal |  |  |  |  | MTr9g7SBT1u6zlznS0uOQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29080 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124275 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499344 | 6359 | 124276 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWSTAP4830 | GF Beams & Slabs Drawings-App |  | 1000 | 1000 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-03 08:00 | 2013-07-07 17:00 |  | 2013-01-07 08:00 | 2013-02-10 17:00 | 2013-01-07 08:00 | 2013-02-10 17:00 | 2013-01-07 08:00 | 2013-02-10 17:00 | 2013-06-03 08:00 | 2013-07-07 17:00 |  | PT_Normal |  |  |  |  | fFeYAii9QuagLrHBPl0y9g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29080 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124275 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499345 | 6359 | 124277 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWSTSM4800 | Footing Drawings-Sub |  | 432 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-01-29 08:00 | 2013-02-09 17:00 |  | 2012-11-26 08:00 | 2012-12-06 17:00 | 2012-11-26 08:00 | 2012-12-06 17:00 | 2012-11-26 08:00 | 2012-12-06 17:00 | 2013-01-29 08:00 | 2013-02-09 17:00 |  | PT_Normal |  |  |  |  | wVHSjPZbRHOQ/cbi7e/yjA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29070 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124275 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 20 | 0
%R | 499346 | 6359 | 124277 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWSTSM4810 | Grade Beam & Slab Drawings-Sub |  | 624 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-03-05 08:00 | 2013-03-21 17:00 |  | 2012-12-02 08:00 | 2012-12-19 17:00 | 2012-12-02 08:00 | 2012-12-19 17:00 | 2012-12-02 08:00 | 2012-12-19 17:00 | 2013-03-05 08:00 | 2013-03-21 17:00 |  | PT_Normal |  |  |  |  | U1QMSn0lQ42dTipngdILyQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29070 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124275 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499347 | 6359 | 124277 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWSTSM4820 | Column Drawings-Sub |  | 624 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-03-11 08:00 | 2013-03-27 17:00 |  | 2012-12-08 08:00 | 2012-12-25 17:00 | 2012-12-08 08:00 | 2012-12-25 17:00 | 2012-12-08 08:00 | 2012-12-25 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 |  | PT_Normal |  |  |  |  | JvuWqu/nQLyijTB2Tv7Pjg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29070 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124275 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499348 | 6359 | 124277 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWSTSM4830 | GF Beams & Slabs Drawings-Sub |  | 624 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-03-23 08:00 | 2013-04-08 17:00 |  | 2012-12-20 08:00 | 2013-01-06 17:00 | 2012-12-20 08:00 | 2013-01-06 17:00 | 2012-12-20 08:00 | 2013-01-06 17:00 | 2013-03-23 08:00 | 2013-04-08 17:00 |  | PT_Normal |  |  |  |  | 0SBwHn3ZR9+FwCsEe0rkiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29070 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124275 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499349 | 6359 | 124279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWELAP5000 | Telephone & TV System Drawings-App |  | 600 | 48 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-04 08:00 | 2013-09-10 17:00 |  | 2013-05-08 08:00 | 2013-06-11 17:00 | 2013-05-08 08:00 | 2013-06-11 17:00 | 2013-05-08 08:00 | 2013-06-11 17:00 | 2013-08-04 08:00 | 2013-09-10 17:00 |  | PT_Normal |  |  |  |  | n3PdlMyOT1u3HLhW8JjVfg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29140 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124278 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499350 | 6359 | 124279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWELAP4950 | Single Line Diagram-App |  | 920 | 320 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-23 08:00 | 2013-08-29 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-07-23 08:00 | 2013-08-29 17:00 |  | PT_Normal |  |  |  |  | d7VIRyRCQyu0jpQPIFTppQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29140 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124278 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499351 | 6359 | 124279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWELAP4960 | Lighting Layout Drawings-App |  | 472 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-25 08:00 | 2013-06-27 17:00 |  | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-05-25 08:00 | 2013-06-27 17:00 |  | PT_Normal |  |  |  |  | bqswCp3NR3uPj6EWT/INrw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29140 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124278 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499352 | 6359 | 124279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWELAP4970 | Power Layout Drawings-App |  | 880 | 280 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-23 08:00 | 2013-08-29 17:00 |  | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-07-23 08:00 | 2013-08-29 17:00 |  | PT_Normal |  |  |  |  | QwCb7WjLRaebGnCNL4Mvbg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29140 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124278 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499353 | 6359 | 124279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWELAP4980 | Central Alarm Monitoring System Drawings-App |  | 792 | 160 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-28 08:00 | 2013-09-03 17:00 |  | 2013-04-03 08:00 | 2013-05-07 17:00 | 2013-04-03 08:00 | 2013-05-07 17:00 | 2013-04-03 08:00 | 2013-05-07 17:00 | 2013-07-28 08:00 | 2013-09-03 17:00 |  | PT_Normal |  |  |  |  | 46JSVg9QQ0yDjOfRuweryg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29140 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124278 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499354 | 6359 | 124279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWELAP4990 | Audio Video Intercom System Drawings-App |  | 720 | 160 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-04 08:00 | 2013-09-10 17:00 |  | 2013-04-21 08:00 | 2013-05-25 17:00 | 2013-04-21 08:00 | 2013-05-25 17:00 | 2013-04-21 08:00 | 2013-05-25 17:00 | 2013-08-04 08:00 | 2013-09-10 17:00 |  | PT_Normal |  |  |  |  | H0kIM6ViSQqgzmT1SgYDXw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29140 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124278 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499355 | 6359 | 124280 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWELSM4950 | Single Line Diagram-Sub |  | 472 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-01 08:00 | 2013-05-18 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-05-01 08:00 | 2013-05-18 17:00 |  | PT_Normal |  |  |  |  | jGJ4ZE5ZRgSmG/Ar6nJhww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29130 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124278 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499356 | 6359 | 124280 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWELSM4960 | Lighting Layout Drawings-Sub |  | 472 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-07 08:00 | 2013-05-23 17:00 |  | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-05-07 08:00 | 2013-05-23 17:00 |  | PT_Normal |  |  |  |  | KugGQO43TWeuBcbAtc1FIQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29130 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124278 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499357 | 6359 | 124280 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWELSM4970 | Power Layout Drawings-Sub |  | 600 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-26 08:00 | 2013-06-11 17:00 |  | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-05-26 08:00 | 2013-06-11 17:00 |  | PT_Normal |  |  |  |  | SQn+XHkzTTy0EPkjC4anTg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29130 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124278 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499358 | 6359 | 124280 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWELSM4980 | Central Alarm Monitoring System Drawings-Sub |  | 600 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-12 08:00 | 2013-06-29 17:00 |  | 2013-03-17 08:00 | 2013-04-02 17:00 | 2013-03-17 08:00 | 2013-04-02 17:00 | 2013-03-17 08:00 | 2013-04-02 17:00 | 2013-06-12 08:00 | 2013-06-29 17:00 |  | PT_Normal |  |  |  |  | tktwkdZVTZ+Kxph9DFK2sw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29130 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124278 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499359 | 6359 | 124280 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWELSM4990 | Audio Video Intercom System Drawings-Sub |  | 600 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-30 08:00 | 2013-07-16 17:00 |  | 2013-04-03 08:00 | 2013-04-20 17:00 | 2013-04-03 08:00 | 2013-04-20 17:00 | 2013-04-03 08:00 | 2013-04-20 17:00 | 2013-06-30 08:00 | 2013-07-16 17:00 |  | PT_Normal |  |  |  |  | 2xJL/6exQHiEaZGlOuRoaw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29130 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124278 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499360 | 6359 | 124280 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2ADWELSM5000 | Telephone & TV System Drawings-Sub |  | 600 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-17 08:00 | 2013-08-03 17:00 |  | 2013-04-21 08:00 | 2013-05-07 17:00 | 2013-04-21 08:00 | 2013-05-07 17:00 | 2013-04-21 08:00 | 2013-05-07 17:00 | 2013-07-17 08:00 | 2013-08-03 17:00 |  | PT_Normal |  |  |  |  | YwSs02/rTcy2/ML4G6gFxA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29130 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124278 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499361 | 6359 | 124282 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWELSM5080 | Electrical Line Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-07-15 17:00 |  | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-07-15 17:00 |  | PT_Normal |  |  |  |  | F3nOQlCAQLC70oleRcP+pA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29190 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499362 | 6359 | 124282 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWSTSM5090 | Street Lighting Layout & details -Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-07-15 17:00 |  | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-07-15 17:00 |  | PT_Normal |  |  |  |  | gsOUjjwMSaqucjMhbfaxVg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29190 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499363 | 6359 | 124282 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWDRSM5050 | Drainage Line Layout & Details-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-23 17:00 |  | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-06-06 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | r29oD1IDSzqTBMfDosFDdw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29190 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499364 | 6359 | 124282 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWFFSM5060 | Fire Fighting Line Layout & Details-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-23 17:00 |  | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-06-06 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | WVNZGeiTTh+DUkaXvltPJg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29190 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499365 | 6359 | 124282 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWWSSM5070 | Water Supply Line Layout & Details-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-23 17:00 |  | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-06-06 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | 0NhJtWCNRDSoib8qDoy5rg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29190 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499366 | 6359 | 124282 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWIRSM5110 | Irrigation Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-16 08:00 | 2013-08-01 17:00 |  | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-07-16 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | VkIicYQQQ/y3ce/sf5z17w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29190 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499367 | 6359 | 124282 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWTCSM5100 | Telecommunication Line Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-07-15 17:00 |  | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-07-15 17:00 |  | PT_Normal |  |  |  |  | wZzZSl4FQbmnbSR+WrEOvQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29190 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499368 | 6359 | 124282 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWPSSM5140 | Parking Shed Layout & Details Drawings-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-24 08:00 | 2013-08-13 17:00 |  | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-07-24 08:00 | 2013-08-13 17:00 |  | PT_Normal |  |  |  |  | P+iu5plwSYiS3HKb0PL3TA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29190 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499369 | 6359 | 124282 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWSLSM5120 | Soft & HardLandscaping Layout & Detail-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-16 08:00 | 2013-08-01 17:00 |  | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-07-16 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | rAvU3Vv+TQ+QoC8mdvXyDA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29190 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499370 | 6359 | 124282 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWBWSM5130 | Boundary Wall Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-16 08:00 | 2013-08-01 17:00 |  | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-07-16 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | Ouc53IwzSzOr5M+IWsUyzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29190 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499371 | 6359 | 124282 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWRWSM5150 | Road Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-24 08:00 | 2013-08-13 17:00 |  | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-07-24 08:00 | 2013-08-13 17:00 |  | PT_Normal |  |  |  |  | /zFkS7AKTdmIZ+0CTdiIvg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29190 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499372 | 6359 | 124282 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWIWSM5160 | Irrigation Water Tank & Pump Room Details- Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-24 08:00 | 2013-08-13 17:00 |  | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-07-24 08:00 | 2013-08-13 17:00 |  | PT_Normal |  |  |  |  | gpUFxlkZTQCpC296b3O5zQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29190 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499373 | 6359 | 124282 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWGZSM5170 | Gazebo Plan & Details-Sub |  | 720 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-10-01 08:00 | 2013-10-20 17:00 |  | 2013-06-15 08:00 | 2013-07-01 17:00 | 2013-06-15 08:00 | 2013-07-01 17:00 | 2013-06-15 08:00 | 2013-07-01 17:00 | 2013-10-01 08:00 | 2013-10-20 17:00 |  | PT_Normal |  |  |  |  | sCM1d49fRk2lRK7tFP11dg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29190 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 30 | 0
%R | 499374 | 6359 | 124283 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWELAP5080 | Electrical Line Layout & Details-App |  | 960 | 240 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2013-11-16 17:00 |  | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-10-10 08:00 | 2013-11-16 17:00 |  | PT_Normal |  |  |  |  | i3ElXCarTfSC295Km6/L4A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29200 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499375 | 6359 | 124283 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWSTAP5090 | Street Lighting Layout & details -App |  | 960 | 240 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2013-11-16 17:00 |  | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-10-10 08:00 | 2013-11-16 17:00 |  | PT_Normal |  |  |  |  | ng9jRKTJQtOCM9RHmRR8Dg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29200 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499376 | 6359 | 124283 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWDRAP5050 | Drainage Line Layout & Details-App |  | 544 | 296 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-21 08:00 | 2013-08-27 17:00 |  | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-07-21 08:00 | 2013-08-27 17:00 |  | PT_Normal |  |  |  |  | CEMjgFWyRzetNVgOOP6voA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29200 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499377 | 6359 | 124283 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWFFAP5060 | Fire Fighting Line Layout & Details-App |  | 360 | 320 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-24 08:00 | 2013-07-28 17:00 |  | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-06-24 08:00 | 2013-07-28 17:00 |  | PT_Normal |  |  |  |  | Ds5qSVnbSYWmX9AHYn9RGg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29200 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499378 | 6359 | 124283 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWWSAP5070 | Water Supply Line Layout & Details-App |  | 688 | 296 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-14 08:00 | 2013-09-17 17:00 |  | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-08-14 08:00 | 2013-09-17 17:00 |  | PT_Normal |  |  |  |  | akgVJshbQxi1m6lYZ/ZHWw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29200 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499379 | 6359 | 124283 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWIRAP5110 | Irrigation Layout & Details-App |  | 728 | 120 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-24 08:00 | 2013-10-30 17:00 |  | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-09-24 08:00 | 2013-10-30 17:00 |  | PT_Normal |  |  |  |  | Ns0Tr11mR/6U1LlVG3PjGA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29200 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499380 | 6359 | 124283 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWTCAP5100 | Telecommunication Line Layout & Details-App |  | 960 | 480 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2013-11-16 17:00 |  | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-10-10 08:00 | 2013-11-16 17:00 |  | PT_Normal |  |  |  |  | tHJckZhfQACzdXOA56nlug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29200 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499381 | 6359 | 124283 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWPSAP5140 | Parking Shed Layout & Details Drawings-App |  | 1200 | 184 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-12-12 08:00 | 2014-01-16 17:00 |  | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-12-12 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | zgqgYEZ1SSu8Md2QTcGtPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29200 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499382 | 6359 | 124283 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWSLAP5120 | Soft & HardLandscaping Layout & Detail-App |  | 536 | 360 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-27 08:00 | 2013-09-30 17:00 |  | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-08-27 08:00 | 2013-09-30 17:00 |  | PT_Normal |  |  |  |  | CMkQ4qB/QQag/5iGIWqsXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29200 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499383 | 6359 | 124283 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWBWAP5130 | Boundary Wall Layout & Details-App |  | 680 | 360 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-17 08:00 | 2013-10-23 17:00 |  | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-09-17 08:00 | 2013-10-23 17:00 |  | PT_Normal |  |  |  |  | 66PQkafjSDeN1051nuAbQA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29200 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499384 | 6359 | 124283 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWRWAP5150 | Road Layout & Details-App |  | 1192 | 184 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-12-11 08:00 | 2014-01-15 17:00 |  | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-12-11 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | YVtJansNTMOT2Qh3NbkYbQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29200 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499385 | 6359 | 124283 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWIWAP5160 | Irrigation Water Tank & Pump Room Details-App |  | 392 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-14 08:00 | 2013-09-17 17:00 |  | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-08-14 08:00 | 2013-09-17 17:00 |  | PT_Normal |  |  |  |  | uKNY6kvlTfmsIK4x1kS8Fg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29200 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499386 | 6359 | 124283 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2ADWGZAP5170 | Gazebo Plan & Details-App |  | 720 | 240 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-21 08:00 | 2013-11-24 17:00 |  | 2013-07-02 08:00 | 2013-08-05 17:00 | 2013-07-02 08:00 | 2013-08-05 17:00 | 2013-07-02 08:00 | 2013-08-05 17:00 | 2013-10-21 08:00 | 2013-11-24 17:00 |  | PT_Normal |  |  |  |  | yMcbfOIqQ6+ME2y99Nhc/A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29200 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124281 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 499387 | 6359 | 124287 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWMESM4210 | Plumbing Layout & Details Drawings-Sub |  | 424 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-24 08:00 | 2013-05-11 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-04-24 08:00 | 2013-05-11 17:00 |  | PT_Normal |  |  |  |  | OTyjmycQRkKCDV72atC+1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28820 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124286 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499388 | 6359 | 124287 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWMESM4220 | Drainage Layout & Details Drawings-Sub |  | 360 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-15 08:00 | 2013-05-01 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 |  | PT_Normal |  |  |  |  | eaErJ+3USbCxK9/x+ysWOg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 28820 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124286 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499389 | 6359 | 124287 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWMESM4230 | Fire Fighting Layout & Details Drawings-Sub |  | 360 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-02 08:00 | 2013-05-19 17:00 |  | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 |  | PT_Normal |  |  |  |  | NjjXSuWERXWmE+VVJanmAg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 28820 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124286 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499390 | 6359 | 124287 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWMESM4240 | AC Layout & Details Drawings-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-20 08:00 | 2013-06-05 17:00 |  | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 |  | PT_Normal |  |  |  |  | P9OO+UrzSVGW7n7A3ZASxg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 28820 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124286 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 499391 | 6359 | 124288 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWMEAP4210 | Plumbing Layout & Details Drawings-App |  | 424 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-12 08:00 | 2013-06-15 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-05-12 08:00 | 2013-06-15 17:00 |  | PT_Normal |  |  |  |  | fO9EXrMEQS+58YTFWUmqvA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28830 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124286 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499392 | 6359 | 124288 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWMEAP4220 | Drainage Layout & Details Drawings-App |  | 424 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-12 08:00 | 2013-06-15 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-05-12 08:00 | 2013-06-15 17:00 |  | PT_Normal |  |  |  |  | 8BNlv34GTRGNA1gLJq7WYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28830 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124286 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499393 | 6359 | 124288 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWMEAP4230 | Fire Fighting Layout & Details Drawings-App |  | 1160 | 440 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-17 08:00 | 2013-10-23 17:00 |  | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-09-17 08:00 | 2013-10-23 17:00 |  | PT_Normal |  |  |  |  | DJ4hindFTVmN1p1Xy4yh2A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28830 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124286 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499394 | 6359 | 124288 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWMEAP4240 | AC Layout & Details Drawings-App |  | 512 | 80 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-08-01 17:00 |  | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | 6OTUla9dTO6esDhc/94S5w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28830 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124286 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499395 | 6359 | 124290 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWELSM4150 | Single Line Diagram-Sub |  | 512 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-07 08:00 | 2013-05-23 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-05-07 08:00 | 2013-05-23 17:00 |  | PT_Normal |  |  |  |  | 8JnF1hSJR6iRrYwjO34yVg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28790 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124289 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499396 | 6359 | 124290 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWELSM4160 | Lighting Layout Drawings-Sub |  | 512 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-07 08:00 | 2013-05-23 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-05-07 08:00 | 2013-05-23 17:00 |  | PT_Normal |  |  |  |  | kxOjQgVURxyxrBO+SUv6Ag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28790 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124289 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499397 | 6359 | 124290 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWELSM4170 | Power Layout Drawings-Sub |  | 560 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-26 08:00 | 2013-06-11 17:00 |  | 2013-03-05 08:00 | 2013-03-21 17:00 | 2013-03-05 08:00 | 2013-03-21 17:00 | 2013-03-05 08:00 | 2013-03-21 17:00 | 2013-05-26 08:00 | 2013-06-11 17:00 |  | PT_Normal |  |  |  |  | Cap+JeZrSM+FwubAmuLzog |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28790 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124289 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499398 | 6359 | 124290 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWELSM4180 | Central Alarm Monitoring System Drawings-Sub |  | 560 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-12 08:00 | 2013-06-29 17:00 |  | 2013-03-23 08:00 | 2013-04-08 17:00 | 2013-03-23 08:00 | 2013-04-08 17:00 | 2013-03-23 08:00 | 2013-04-08 17:00 | 2013-06-12 08:00 | 2013-06-29 17:00 |  | PT_Normal |  |  |  |  | m6lxHSriRsuoO7m4fchSzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28790 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124289 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499399 | 6359 | 124290 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWELSM4190 | Audio Video Intercom System Drawings-Sub |  | 560 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-30 08:00 | 2013-07-16 17:00 |  | 2013-04-09 08:00 | 2013-04-25 17:00 | 2013-04-09 08:00 | 2013-04-25 17:00 | 2013-04-09 08:00 | 2013-04-25 17:00 | 2013-06-30 08:00 | 2013-07-16 17:00 |  | PT_Normal |  |  |  |  | S+Fcg+WDRBWPm/wkzqGBgA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28790 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124289 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499400 | 6359 | 124290 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWELSM4200 | Telephone & TV System Drawings-Sub |  | 560 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-17 08:00 | 2013-08-03 17:00 |  | 2013-04-27 08:00 | 2013-05-13 17:00 | 2013-04-27 08:00 | 2013-05-13 17:00 | 2013-04-27 08:00 | 2013-05-13 17:00 | 2013-07-17 08:00 | 2013-08-03 17:00 |  | PT_Normal |  |  |  |  | YlBzXEjBRUuHmpuHZG5X0w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28790 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124289 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499401 | 6359 | 124291 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWELAP4150 | Single Line Diagram-App |  | 920 | 320 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-23 08:00 | 2013-08-29 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-07-23 08:00 | 2013-08-29 17:00 |  | PT_Normal |  |  |  |  | VjegkJLdSRadUczSdwZ7vw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28800 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124289 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499402 | 6359 | 124291 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWELAP4160 | Lighting Layout Drawings-App |  | 512 | 40 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-25 08:00 | 2013-06-27 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-05-25 08:00 | 2013-06-27 17:00 |  | PT_Normal |  |  |  |  | 6/PdXu4zRVykukyliBRgpA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28800 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124289 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499403 | 6359 | 124291 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWELAP4170 | Power Layout Drawings-App |  | 840 | 240 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-23 08:00 | 2013-08-29 17:00 |  | 2013-03-23 08:00 | 2013-04-25 17:00 | 2013-03-23 08:00 | 2013-04-25 17:00 | 2013-03-23 08:00 | 2013-04-25 17:00 | 2013-07-23 08:00 | 2013-08-29 17:00 |  | PT_Normal |  |  |  |  | VfjYk7NCQY2MvG2hFHjWUQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28800 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124289 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499404 | 6359 | 124291 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWELAP4180 | Central Alarm Monitoring System Drawings-App |  | 752 | 120 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-28 08:00 | 2013-09-03 17:00 |  | 2013-04-09 08:00 | 2013-05-13 17:00 | 2013-04-09 08:00 | 2013-05-13 17:00 | 2013-04-09 08:00 | 2013-05-13 17:00 | 2013-07-28 08:00 | 2013-09-03 17:00 |  | PT_Normal |  |  |  |  | jWKBY99QTKaOrMC/HeiziA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28800 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124289 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499405 | 6359 | 124291 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWELAP4190 | Audio Video Intercom System Drawings-App |  | 680 | 120 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-04 08:00 | 2013-09-10 17:00 |  | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-08-04 08:00 | 2013-09-10 17:00 |  | PT_Normal |  |  |  |  | SubG2mCKTquV0Dp4x8s5xQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28800 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124289 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499406 | 6359 | 124291 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWELAP4200 | Telephone & TV System Drawings-App |  | 560 | 8 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-04 08:00 | 2013-09-10 17:00 |  | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-08-04 08:00 | 2013-09-10 17:00 |  | PT_Normal |  |  |  |  | ameOUpBZR1e3A4+00SPiDg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28800 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124289 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499407 | 6359 | 124293 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWPSAP4340 | Parking Shed Layout & Details Drawings-App |  | 1200 | 184 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-12-12 08:00 | 2014-01-16 17:00 |  | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-12-12 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | CFCGP4nETjuOcFid35gZpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28860 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499408 | 6359 | 124293 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWSLAP4320 | Soft & HardLandscaping Layout & Detail-App |  | 536 | 360 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-27 08:00 | 2013-09-30 17:00 |  | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-08-27 08:00 | 2013-09-30 17:00 |  | PT_Normal |  |  |  |  | 4d9Lzxm4TDG5whiyMnSLVg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28860 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499409 | 6359 | 124293 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWBWAP4330 | Boundary Wall Layout & Details-App |  | 680 | 360 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-17 08:00 | 2013-10-23 17:00 |  | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-09-17 08:00 | 2013-10-23 17:00 |  | PT_Normal |  |  |  |  | Fe7gZQy3RiKsJZiehcidAA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 28860 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499410 | 6359 | 124293 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWRWAP4350 | Road Layout & Details-App |  | 1192 | 184 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-12-11 08:00 | 2014-01-15 17:00 |  | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-12-11 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | 3L8OVy5NTBG8EBogLdDcYQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28860 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499411 | 6359 | 124293 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWIWAP4360 | Irrigation Water Tank & Pump Room Details-App |  | 392 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-14 08:00 | 2013-09-17 17:00 |  | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-08-14 08:00 | 2013-09-17 17:00 |  | PT_Normal |  |  |  |  | VjKBBduSRyuX8AdlPR8N0A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28860 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499412 | 6359 | 124293 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWTRAP4370 | Telephone Room Details-App |  | 480 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-14 08:00 | 2013-10-20 17:00 |  | 2013-07-02 08:00 | 2013-08-05 17:00 | 2013-07-02 08:00 | 2013-08-05 17:00 | 2013-07-02 08:00 | 2013-08-05 17:00 | 2013-09-14 08:00 | 2013-10-20 17:00 |  | PT_Normal |  |  |  |  | aUte4TU7RQe/pI9miuc5sg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28860 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 499413 | 6359 | 124293 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWGZAP4380 | Gazebo Plan & Details-App |  | 480 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-21 08:00 | 2013-11-24 17:00 |  | 2013-08-06 08:00 | 2013-09-12 17:00 | 2013-08-06 08:00 | 2013-09-12 17:00 | 2013-08-06 08:00 | 2013-09-12 17:00 | 2013-10-21 08:00 | 2013-11-24 17:00 |  | PT_Normal |  |  |  |  | N9c/VfAvTE6qH4I600vlWg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28860 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 0 | 0
%R | 499414 | 6359 | 124293 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWGHAP4390 | Guard House Plan & Details-App |  | 2176 | 1936 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2014-06-28 08:00 | 2014-07-31 17:00 |  | 2013-08-06 08:00 | 2013-09-12 17:00 | 2013-08-06 08:00 | 2013-09-12 17:00 | 2013-08-06 08:00 | 2013-09-12 17:00 | 2014-06-28 08:00 | 2014-07-31 17:00 |  | PT_Normal |  |  |  |  | GOH2/z7kSF+1IzXtiDXXFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28860 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 0 | 0
%R | 499415 | 6359 | 124293 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWELAP4280 | Electrical Line Layout & Details-App |  | 480 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-29 08:00 | 2013-09-04 17:00 |  | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 |  | PT_Normal |  |  |  |  | xEhE39gGTJGKVSMKnh5eFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28860 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499416 | 6359 | 124293 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWSTAP4290 | Street Lighting Layout & details -App |  | 480 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-05 08:00 | 2013-10-09 17:00 |  | 2013-06-24 08:00 | 2013-07-28 17:00 | 2013-06-24 08:00 | 2013-07-28 17:00 | 2013-06-24 08:00 | 2013-07-28 17:00 | 2013-09-05 08:00 | 2013-10-09 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28860 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499417 | 6359 | 124293 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWDRAP4250 | Drainage Line Layout & Details-App |  | 672 | 296 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-08 08:00 | 2013-09-15 17:00 |  | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-08-08 08:00 | 2013-09-15 17:00 |  | PT_Normal |  |  |  |  | PBt8L0OTQgiQ/4txK/lJUg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28860 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499418 | 6359 | 124293 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWFFAP4260 | Fire Fighting Line Layout & Details-App |  | 360 | 320 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-24 08:00 | 2013-07-28 17:00 |  | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-06-24 08:00 | 2013-07-28 17:00 |  | PT_Normal |  |  |  |  | ZWhpHbUZR3a2jJD33VZ9QA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 28860 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499419 | 6359 | 124293 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWWSAP4270 | Water Supply Line Layout & Details-App |  | 688 | 296 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-14 08:00 | 2013-09-17 17:00 |  | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-08-14 08:00 | 2013-09-17 17:00 |  | PT_Normal |  |  |  |  | BVsvX21UT6mIaWkjB8+ibA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28860 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499420 | 6359 | 124293 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWIRAP4310 | Irrigation Layout & Details-App |  | 728 | 120 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-24 08:00 | 2013-10-30 17:00 |  | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-09-24 08:00 | 2013-10-30 17:00 |  | PT_Normal |  |  |  |  | MNfqcwpBSpCe5qeQU+vbog |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28860 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499421 | 6359 | 124293 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWTCAP4300 | Telecommunication Line Layout & Details-App |  | 480 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2013-11-16 17:00 |  | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-10-10 08:00 | 2013-11-16 17:00 |  | PT_Normal |  |  |  |  | mxM53e3QSNK+yWdEKKYUyQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28860 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 499422 | 6359 | 124294 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWDRSM4250 | Drainage Line Layout & Details-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-23 17:00 |  | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-06-06 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | idvBQanWQcacZxpc5tHk3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 28850 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499423 | 6359 | 124294 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWFFSM4260 | Fire Fighting Line Layout & Details-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-23 17:00 |  | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-06-06 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | FlIpyt14T2qHTLICyFkGHA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 28850 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499424 | 6359 | 124294 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWWSSM4270 | Water Supply Line Layout & Details-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-23 17:00 |  | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-06-06 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | F8u/P5fpRAahf0xCkVJ/EQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 28850 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499425 | 6359 | 124294 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWIRSM4310 | Irrigation Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-16 08:00 | 2013-08-01 17:00 |  | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-07-16 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | z9XfydjAT3mhVajqR/TY5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28850 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499426 | 6359 | 124294 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWTCSM4300 | Telecommunication Line Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-07-15 17:00 |  | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-07-15 17:00 |  | PT_Normal |  |  |  |  | o2uoOKQhSyGIju41iQwZOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28850 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499427 | 6359 | 124294 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWPSSM4340 | Parking Shed Layout & Details Drawings-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-24 08:00 | 2013-08-13 17:00 |  | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-07-24 08:00 | 2013-08-13 17:00 |  | PT_Normal |  |  |  |  | O/zBSPlkTAK8y1QWk9EBZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28850 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499428 | 6359 | 124294 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWSLSM4320 | Soft & HardLandscaping Layout & Detail-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-16 08:00 | 2013-08-01 17:00 |  | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-07-16 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | tx/FWdFYQ5O/wGKCX7mq3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28850 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499429 | 6359 | 124294 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWBWSM4330 | Boundary Wall Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-16 08:00 | 2013-08-01 17:00 |  | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-07-16 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | F0awJ0g2TPmfaMPVnF+vNg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28850 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499430 | 6359 | 124294 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWRWSM4350 | Road Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-24 08:00 | 2013-08-13 17:00 |  | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-07-24 08:00 | 2013-08-13 17:00 |  | PT_Normal |  |  |  |  | TC6rYf6mSmOauuJK4Oe3tQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28850 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499431 | 6359 | 124294 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWIWSM4360 | Irrigation Water Tank & Pump Room Details- Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-24 08:00 | 2013-08-13 17:00 |  | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-07-24 08:00 | 2013-08-13 17:00 |  | PT_Normal |  |  |  |  | sT/5Yr8ES3GzAomCXtKWDg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28850 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499432 | 6359 | 124294 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWTRSM4370 | Telephone Room Details-Sub |  | 480 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-08-27 08:00 | 2013-09-12 17:00 |  | 2013-06-15 08:00 | 2013-07-01 17:00 | 2013-06-15 08:00 | 2013-07-01 17:00 | 2013-06-15 08:00 | 2013-07-01 17:00 | 2013-08-27 08:00 | 2013-09-12 17:00 |  | PT_Normal |  |  |  |  | iuRLrifWR1+mvX2W+x3+CQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28850 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 30 | 0
%R | 499433 | 6359 | 124294 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWGZSM4380 | Gazebo Plan & Details-Sub |  | 600 | 120 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-10-01 08:00 | 2013-10-20 17:00 |  | 2013-07-02 08:00 | 2013-07-18 17:00 | 2013-07-02 08:00 | 2013-07-18 17:00 | 2013-07-02 08:00 | 2013-07-18 17:00 | 2013-10-01 08:00 | 2013-10-20 17:00 |  | PT_Normal |  |  |  |  | Plr+2qpGQgmz4x771JlHhQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28850 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 30 | 0
%R | 499434 | 6359 | 124294 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWGHSM4390 | Guard House Plan & Details-Sub |  | 2296 | 120 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-10 08:00 | 2014-06-26 17:00 |  | 2013-07-02 08:00 | 2013-07-18 17:00 | 2013-07-02 08:00 | 2013-07-18 17:00 | 2013-07-02 08:00 | 2013-07-18 17:00 | 2014-06-10 08:00 | 2014-06-26 17:00 |  | PT_Normal |  |  |  |  | WtCvQ+5IRampTtCgTQwJrg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28850 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 30 | 0
%R | 499435 | 6359 | 124294 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWELSM4280 | Electrical Line Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-07-15 17:00 |  | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-07-15 17:00 |  | PT_Normal |  |  |  |  | tKAf/pLDSEW15ztHarnj5Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28850 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499436 | 6359 | 124294 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1ADWSTSM4290 | Street Lighting Layout & details -Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-07-15 17:00 |  | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-07-15 17:00 |  | PT_Normal |  |  |  |  | 8zSG4Z3OTOCZK75QCu3s7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28850 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499437 | 6359 | 124296 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARAP4050 | Ground Floor Plan-App |  | 736 | 80 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-04 08:00 | 2013-07-08 17:00 |  | 2013-02-17 08:00 | 2013-03-23 17:00 | 2013-02-17 08:00 | 2013-03-23 17:00 | 2013-02-17 08:00 | 2013-03-23 17:00 | 2013-06-04 08:00 | 2013-07-08 17:00 |  | PT_Normal |  |  |  |  | WFib3bb8TUmQNm1swZKyEQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28770 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499438 | 6359 | 124296 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARAP4060 | First Floor Plan-App |  | 496 | 48 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-13 08:00 | 2013-06-16 17:00 |  | 2013-03-02 08:00 | 2013-04-04 17:00 | 2013-03-02 08:00 | 2013-04-04 17:00 | 2013-03-02 08:00 | 2013-04-04 17:00 | 2013-05-13 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | S002S4lBQSSkEng0YltlCA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28770 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499439 | 6359 | 124296 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARAP4070 | Roof Floor Plan-App |  | 440 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-13 08:00 | 2013-06-16 17:00 |  | 2013-03-10 08:00 | 2013-04-13 17:00 | 2013-03-10 08:00 | 2013-04-13 17:00 | 2013-03-10 08:00 | 2013-04-13 17:00 | 2013-05-13 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | w4d6abiGTcmgpaLgz9rNlw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28770 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499440 | 6359 | 124296 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARAP4080 | Ceramic Flooring & Wall Drawings-App |  | 384 | 48 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-14 08:00 | 2013-06-17 17:00 |  | 2013-03-19 08:00 | 2013-04-22 17:00 | 2013-03-19 08:00 | 2013-04-22 17:00 | 2013-03-19 08:00 | 2013-04-22 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 |  | PT_Normal |  |  |  |  | HXu6JoysTzmr3eiJpVWffA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28770 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499441 | 6359 | 124296 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARAP4090 | Porcelain Floor Drawings-App |  | 456 | 48 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-25 08:00 | 2013-06-27 17:00 |  | 2013-03-19 08:00 | 2013-04-22 17:00 | 2013-03-19 08:00 | 2013-04-22 17:00 | 2013-03-19 08:00 | 2013-04-22 17:00 | 2013-05-25 08:00 | 2013-06-27 17:00 |  | PT_Normal |  |  |  |  | PyAmCQeiR7aKIY/VLSRRLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28770 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499442 | 6359 | 124296 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARAP4100 | Cobble & Slate Flooring Drawings-App |  | 704 | 48 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-30 08:00 | 2013-08-03 17:00 |  | 2013-03-19 08:00 | 2013-04-22 17:00 | 2013-03-19 08:00 | 2013-04-22 17:00 | 2013-03-19 08:00 | 2013-04-22 17:00 | 2013-06-30 08:00 | 2013-08-03 17:00 |  | PT_Normal |  |  |  |  | pTHpRuSyRjeotQNbTIGmsw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28770 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499443 | 6359 | 124296 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARAP4110 | Gypsum False Ceiling Drawings-App |  | 536 | 280 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-18 08:00 | 2013-07-22 17:00 |  | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-06-18 08:00 | 2013-07-22 17:00 |  | PT_Normal |  |  |  |  | KAldFzA6SyGzA/dpLWtjVQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28770 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499444 | 6359 | 124296 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARAP4120 | Aluminum False Ceiling Drawings-App |  | 656 | 320 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-06 08:00 | 2013-08-08 17:00 |  | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-07-06 08:00 | 2013-08-08 17:00 |  | PT_Normal |  |  |  |  | FB6pRg0zRkmULcRdq+I9XA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28770 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499445 | 6359 | 124296 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARAP4130 | Doors & Window Drawings-App |  | 440 | 232 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-17 08:00 | 2013-07-21 17:00 |  | 2013-04-14 08:00 | 2013-05-18 17:00 | 2013-04-14 08:00 | 2013-05-18 17:00 | 2013-04-14 08:00 | 2013-05-18 17:00 | 2013-06-17 08:00 | 2013-07-21 17:00 |  | PT_Normal |  |  |  |  | 2uclEJFgSuqcgRTJBGZidg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28770 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499446 | 6359 | 124296 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARAP4140 | Carpentry & Joinery Drawings-App |  | 664 | 320 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-30 08:00 | 2013-09-05 17:00 |  | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-07-30 08:00 | 2013-09-05 17:00 |  | PT_Normal |  |  |  |  | ikPnFo6gTD+SM7e+KkF3xw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28770 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499447 | 6359 | 124297 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARSM4050 | Ground Floor Plan-Sub |  | 384 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-03-27 08:00 | 2013-04-13 17:00 |  | 2013-01-29 08:00 | 2013-02-16 17:00 | 2013-01-29 08:00 | 2013-02-16 17:00 | 2013-01-29 08:00 | 2013-02-16 17:00 | 2013-03-27 08:00 | 2013-04-13 17:00 |  | PT_Normal |  |  |  |  | nPnTgx3RRXuJsVSkcUrnmg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28760 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499448 | 6359 | 124297 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARSM4060 | First Floor Plan-Sub |  | 384 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-09 08:00 | 2013-04-25 17:00 |  | 2013-02-11 08:00 | 2013-02-28 17:00 | 2013-02-11 08:00 | 2013-02-28 17:00 | 2013-02-11 08:00 | 2013-02-28 17:00 | 2013-04-09 08:00 | 2013-04-25 17:00 |  | PT_Normal |  |  |  |  | s1e9rX4iRYS/wpnXjIUGxA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28760 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 30 | 0
%R | 499449 | 6359 | 124297 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARSM4070 | Roof Floor Plan-Sub |  | 424 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-23 08:00 | 2013-05-09 17:00 |  | 2013-02-20 08:00 | 2013-03-09 17:00 | 2013-02-20 08:00 | 2013-03-09 17:00 | 2013-02-20 08:00 | 2013-03-09 17:00 | 2013-04-23 08:00 | 2013-05-09 17:00 |  | PT_Normal |  |  |  |  | lqeULUNCQUe0sj6m7i8jGA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28760 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 30 | 0
%R | 499450 | 6359 | 124297 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARSM4080 | Ceramic Flooring & Wall Drawings-Sub |  | 384 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-27 08:00 | 2013-05-13 17:00 |  | 2013-03-02 08:00 | 2013-03-18 17:00 | 2013-03-02 08:00 | 2013-03-18 17:00 | 2013-03-02 08:00 | 2013-03-18 17:00 | 2013-04-27 08:00 | 2013-05-13 17:00 |  | PT_Normal |  |  |  |  | n538m5/hRqyONYwgVD0tuA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28760 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499451 | 6359 | 124297 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARSM4090 | Porcelain Floor Drawings-Sub |  | 456 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-07 08:00 | 2013-05-23 17:00 |  | 2013-03-02 08:00 | 2013-03-18 17:00 | 2013-03-02 08:00 | 2013-03-18 17:00 | 2013-03-02 08:00 | 2013-03-18 17:00 | 2013-05-07 08:00 | 2013-05-23 17:00 |  | PT_Normal |  |  |  |  | 4Bz6hjLzRxy5vi3PLA8SVQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28760 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499452 | 6359 | 124297 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARSM4100 | Cobble & Slate Flooring Drawings-Sub |  | 704 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-12 08:00 | 2013-06-29 17:00 |  | 2013-03-02 08:00 | 2013-03-18 17:00 | 2013-03-02 08:00 | 2013-03-18 17:00 | 2013-03-02 08:00 | 2013-03-18 17:00 | 2013-06-12 08:00 | 2013-06-29 17:00 |  | PT_Normal |  |  |  |  | oCx3Os3rSy66UURms9TKAA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28760 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499453 | 6359 | 124297 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARSM4110 | Gypsum False Ceiling Drawings-Sub |  | 536 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-01 08:00 | 2013-06-17 17:00 |  | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-06-01 08:00 | 2013-06-17 17:00 |  | PT_Normal |  |  |  |  | P/lwCJpzTSGny3wozbO6Yg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28760 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499454 | 6359 | 124297 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARSM4120 | Aluminum False Ceiling Drawings-Sub |  | 656 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-18 08:00 | 2013-07-04 17:00 |  | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-06-18 08:00 | 2013-07-04 17:00 |  | PT_Normal |  |  |  |  | i3u5oHOSSruD11Bvf/V33w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28760 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499455 | 6359 | 124297 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARSM4130 | Doors & window Drawings-Sub |  | 488 | 48 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-30 08:00 | 2013-06-16 17:00 |  | 2013-03-20 08:00 | 2013-04-06 17:00 | 2013-03-20 08:00 | 2013-04-06 17:00 | 2013-03-20 08:00 | 2013-04-06 17:00 | 2013-05-30 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | qoyEbUwXQTaA94E7QxqgQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28760 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499456 | 6359 | 124297 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWARSM4140 | Carpentry & Joinery Drawings-Sub |  | 664 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-13 08:00 | 2013-07-29 17:00 |  | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-07-13 08:00 | 2013-07-29 17:00 |  | PT_Normal |  |  |  |  | 8HDPnAJjTKGYjMxRf2r2Lg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28760 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124295 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499457 | 6359 | 124299 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWSTAP4020 | Column Drawings-App |  | 984 | 984 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-25 08:00 | 2013-06-27 17:00 |  | 2012-12-31 08:00 | 2013-02-03 17:00 | 2012-12-31 08:00 | 2013-02-03 17:00 | 2012-12-31 08:00 | 2013-02-03 17:00 | 2013-05-25 08:00 | 2013-06-27 17:00 |  | PT_Normal |  |  |  |  | eJxz10zKRtmIfm5F7hKh/w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28740 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124298 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499458 | 6359 | 124299 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWSTAP4030 | GF Beams & Slabs Drawings-App |  | 1064 | 1064 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-17 08:00 | 2013-07-21 17:00 |  | 2013-01-12 08:00 | 2013-02-16 17:00 | 2013-01-12 08:00 | 2013-02-16 17:00 | 2013-01-12 08:00 | 2013-02-16 17:00 | 2013-06-17 08:00 | 2013-07-21 17:00 |  | PT_Normal |  |  |  |  | T7kYDJwQRVybjbxJivF2YQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28740 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124298 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499459 | 6359 | 124299 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWSTAP4040 | FF Beams & Slabs Drawings-App |  | 1064 | 1064 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-04 08:00 | 2013-08-07 17:00 |  | 2013-01-29 08:00 | 2013-03-05 17:00 | 2013-01-29 08:00 | 2013-03-05 17:00 | 2013-01-29 08:00 | 2013-03-05 17:00 | 2013-07-04 08:00 | 2013-08-07 17:00 |  | PT_Normal |  |  |  |  | oh5viV47Q1W7ktz4jJx+eA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28740 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124298 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499460 | 6359 | 124299 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWSTAP4000 | Footing Drawings-App |  | 368 | 368 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 |  |  |  | 2013-02-05 08:00 | 2013-03-06 17:00 |  | 2012-12-12 08:00 | 2013-01-10 17:00 | 2012-12-12 08:00 | 2013-01-10 17:00 | 2012-12-12 08:00 | 2013-01-10 17:00 | 2013-02-05 08:00 | 2013-03-06 17:00 |  | PT_Normal |  |  |  |  | gVeR5oyySK6BM36MZMiqsA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28740 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124298 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499461 | 6359 | 124299 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWSTAP4010 | Grade Beam & Slab Drawings-App |  | 688 | 688 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-06 08:00 | 2013-05-09 17:00 |  | 2012-12-25 08:00 | 2013-01-28 17:00 | 2012-12-25 08:00 | 2013-01-28 17:00 | 2012-12-25 08:00 | 2013-01-28 17:00 | 2013-04-06 08:00 | 2013-05-09 17:00 |  | PT_Normal |  |  |  |  | DYA9m7TCQwWScnJYABotRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28740 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124298 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499462 | 6359 | 124300 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWSTSM4000 | Footing Drawings-Sub | 8176 | 368 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-01-24 08:00 | 2013-02-04 17:00 |  | 2012-12-01 08:00 | 2012-12-11 17:00 | 2012-12-01 08:00 | 2012-12-11 17:00 | 2012-12-01 08:00 | 2012-12-11 17:00 | 2013-01-24 08:00 | 2013-02-04 17:00 |  | PT_Normal |  |  |  |  | gaayB1yhSzqw71AioC0y9g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43530 |  |  |  |  | DRAFTMAN SK | J320 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28730 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124298 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 20 | DRAFTMAN SK
%R | 499463 | 6359 | 124300 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWSTSM4010 | Grade Beam & Slab Drawings-Sub |  | 384 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-02-02 08:00 | 2013-02-19 17:00 |  | 2012-12-06 08:00 | 2012-12-24 17:00 | 2012-12-06 08:00 | 2012-12-24 17:00 | 2012-12-06 08:00 | 2012-12-24 17:00 | 2013-02-02 08:00 | 2013-02-19 17:00 |  | PT_Normal |  |  |  |  | Crs60XobS5K37bo+e3m3bw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28730 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124298 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499464 | 6359 | 124300 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWSTSM4020 | Column Drawings-Sub |  | 384 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-02-07 08:00 | 2013-02-25 17:00 |  | 2012-12-12 08:00 | 2012-12-30 17:00 | 2012-12-12 08:00 | 2012-12-30 17:00 | 2012-12-12 08:00 | 2012-12-30 17:00 | 2013-02-07 08:00 | 2013-02-25 17:00 |  | PT_Normal |  |  |  |  | 12iznbS2QwGcy694z/Ujnw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28730 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124298 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499465 | 6359 | 124300 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWSTSM4030 | GF Beams & Slabs Drawings-Sub |  | 384 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-02-20 08:00 | 2013-03-09 17:00 |  | 2012-12-25 08:00 | 2013-01-10 17:00 | 2012-12-25 08:00 | 2013-01-10 17:00 | 2012-12-25 08:00 | 2013-01-10 17:00 | 2013-02-20 08:00 | 2013-03-09 17:00 |  | PT_Normal |  |  |  |  | vfBfpB7bTZmJMXDJWQmwpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28730 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124298 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499466 | 6359 | 124300 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1ADWSTSM4040 | FF Beams & Slabs Drawings-Sub |  | 384 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-03-10 08:00 | 2013-03-26 17:00 |  | 2013-01-12 08:00 | 2013-01-28 17:00 | 2013-01-12 08:00 | 2013-01-28 17:00 | 2013-01-12 08:00 | 2013-01-28 17:00 | 2013-03-10 08:00 | 2013-03-26 17:00 |  | PT_Normal |  |  |  |  | i4GT2Oz+Q2SfAGhoXOD/yg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28730 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124298 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499467 | 6359 | 124304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWGHSM4790 | Guard House Plan & Details-Sub |  | 2416 | 120 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-10 08:00 | 2014-06-26 17:00 |  | 2013-06-15 08:00 | 2013-07-01 17:00 | 2013-06-15 08:00 | 2013-07-01 17:00 | 2013-06-15 08:00 | 2013-07-01 17:00 | 2014-06-10 08:00 | 2014-06-26 17:00 |  | PT_Normal |  |  |  |  | 5QWfoiq0RUuVoAabKbsV/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29020 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 30 | 0
%R | 499468 | 6359 | 124304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWGZSM4780 | Gazebo Plan & Details-Sub |  | 720 | 120 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-10-01 08:00 | 2013-10-20 17:00 |  | 2013-06-15 08:00 | 2013-07-01 17:00 | 2013-06-15 08:00 | 2013-07-01 17:00 | 2013-06-15 08:00 | 2013-07-01 17:00 | 2013-10-01 08:00 | 2013-10-20 17:00 |  | PT_Normal |  |  |  |  | sHpNxFbDQ6GeyxUuc10CXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29020 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 30 | 0
%R | 499469 | 6359 | 124304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWELSM4680 | Electrical Line Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-07-15 17:00 |  | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-07-15 17:00 |  | PT_Normal |  |  |  |  | g/qhCi7BSFij6sE3gVrjQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29020 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499470 | 6359 | 124304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWSTSM4690 | Street Lighting Layout & details -Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-07-15 17:00 |  | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-07-15 17:00 |  | PT_Normal |  |  |  |  | HwImXB84RHG5zQweEbxLtg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29020 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499471 | 6359 | 124304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWDRSM4650 | Drainage Line Layout & Details-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-23 17:00 |  | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-06-06 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | IhHnlBiWT+qEe62S+LjqjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29020 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499472 | 6359 | 124304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWFFSM4660 | Fire Fighting Line Layout & Details-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-23 17:00 |  | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-06-06 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | pgjYZYbuR/C95kznqjZV4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29020 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499473 | 6359 | 124304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWWSSM4670 | Water Supply Line Layout & Details-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-23 17:00 |  | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-06-06 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | a2jQcZRvQxG1rd3THXDzvA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29020 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499474 | 6359 | 124304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWIRSM4710 | Irrigation Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-16 08:00 | 2013-08-01 17:00 |  | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-07-16 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | 6gcqk4FrT0KpzbzqiQ742A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29020 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499475 | 6359 | 124304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWTCSM4700 | Telecommunication Line Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-07-15 17:00 |  | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-07-15 17:00 |  | PT_Normal |  |  |  |  | qi/eJAUoSOyaEKP1PNI/MQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29020 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499476 | 6359 | 124304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWPSSM4740 | Parking Shed Layout & Details Drawings-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-24 08:00 | 2013-08-13 17:00 |  | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-07-24 08:00 | 2013-08-13 17:00 |  | PT_Normal |  |  |  |  | +qCIphsIRHWBcDf/2FWRpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29020 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499477 | 6359 | 124304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWSLSM4720 | Soft & HardLandscaping Layout & Detail-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-16 08:00 | 2013-08-01 17:00 |  | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-07-16 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | ROGcu7ydRpeWsZyoiigUOQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29020 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499478 | 6359 | 124304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWBWSM4730 | Boundary Wall Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-16 08:00 | 2013-08-01 17:00 |  | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-07-16 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | jIjlRSQdTw6pp+ODcQkD3g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29020 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499479 | 6359 | 124304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWRWSM4750 | Road Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-24 08:00 | 2013-08-13 17:00 |  | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-07-24 08:00 | 2013-08-13 17:00 |  | PT_Normal |  |  |  |  | IRuo3Pi2QP2czqv9X3ZoTQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29020 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499480 | 6359 | 124304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWIWSM4760 | Irrigation Water Tank & Pump Room Details- Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-24 08:00 | 2013-08-13 17:00 |  | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-07-24 08:00 | 2013-08-13 17:00 |  | PT_Normal |  |  |  |  | XuJ4zCLKRqarQDC7R8RU8A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29020 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499481 | 6359 | 124304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWTRSM4770 | Telephone Room Details-Sub |  | 600 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-08-27 08:00 | 2013-09-12 17:00 |  | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-08-27 08:00 | 2013-09-12 17:00 |  | PT_Normal |  |  |  |  | WtGeh2puTKqLx+RQUAjcpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29020 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499482 | 6359 | 124305 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWELAP4680 | Electrical Line Layout & Details-App |  | 480 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-29 08:00 | 2013-09-04 17:00 |  | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 |  | PT_Normal |  |  |  |  | 6NmBclYJSmCuwBEhsJXCug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29030 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499483 | 6359 | 124305 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWSTAP4690 | Street Lighting Layout & details -App |  | 480 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-05 08:00 | 2013-10-09 17:00 |  | 2013-06-24 08:00 | 2013-07-28 17:00 | 2013-06-24 08:00 | 2013-07-28 17:00 | 2013-06-24 08:00 | 2013-07-28 17:00 | 2013-09-05 08:00 | 2013-10-09 17:00 |  | PT_Normal |  |  |  |  | 3R5CTp6SSeCLlbHGPRmzBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29030 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499484 | 6359 | 124305 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWDRAP4650 | Drainage Line Layout & Details-App |  | 688 | 296 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-14 08:00 | 2013-09-17 17:00 |  | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-08-14 08:00 | 2013-09-17 17:00 |  | PT_Normal |  |  |  |  | 01uIUj+iTQGBVQCZ0x0+rQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29030 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499485 | 6359 | 124305 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWFFAP4660 | Fire Fighting Line Layout & Details-App |  | 360 | 320 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-24 08:00 | 2013-07-28 17:00 |  | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-06-24 08:00 | 2013-07-28 17:00 |  | PT_Normal |  |  |  |  | jx3SwcYZRl2GolnLA/NsYQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29030 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499486 | 6359 | 124305 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWWSAP4670 | Water Supply Line Layout & Details-App |  | 688 | 296 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-14 08:00 | 2013-09-17 17:00 |  | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-08-14 08:00 | 2013-09-17 17:00 |  | PT_Normal |  |  |  |  | 3WLkd33kTNCWiis1cUSyug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29030 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499487 | 6359 | 124305 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWIRAP4710 | Irrigation Layout & Details-App |  | 728 | 120 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-24 08:00 | 2013-10-30 17:00 |  | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-09-24 08:00 | 2013-10-30 17:00 |  | PT_Normal |  |  |  |  | iwsOVo+ASv6DgTDJLZs/9w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29030 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499488 | 6359 | 124305 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWTCAP4700 | Telecommunication Line Layout & Details-App |  | 480 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2013-11-16 17:00 |  | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-10-10 08:00 | 2013-11-16 17:00 |  | PT_Normal |  |  |  |  | ShijvBAqQiaMKwnuGOKcGg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29030 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 499489 | 6359 | 124305 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWPSAP4740 | Parking Shed Layout & Details Drawings-App |  | 1200 | 184 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-12-12 08:00 | 2014-01-16 17:00 |  | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-12-12 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | 4cWUOOo1RGK4ZCvsu9aasg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29030 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499490 | 6359 | 124305 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWSLAP4720 | Soft & HardLandscaping Layout & Detail-App |  | 536 | 360 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-27 08:00 | 2013-09-30 17:00 |  | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-08-27 08:00 | 2013-09-30 17:00 |  | PT_Normal |  |  |  |  | 4nYrZLP9QHak5QDc73FyBw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29030 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499491 | 6359 | 124305 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWBWAP4730 | Boundary Wall Layout & Details-App |  | 680 | 360 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-17 08:00 | 2013-10-23 17:00 |  | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-09-17 08:00 | 2013-10-23 17:00 |  | PT_Normal |  |  |  |  | Vx0hd4S6R/ioylMm566BCg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29030 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499492 | 6359 | 124305 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWRWAP4750 | Road Layout & Details-App |  | 1192 | 184 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-12-11 08:00 | 2014-01-15 17:00 |  | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-12-11 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | 1iZD0c6qRzGxH9QnPBLK6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29030 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499493 | 6359 | 124305 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWIWAP4760 | Irrigation Water Tank & Pump Room Details-App |  | 392 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-14 08:00 | 2013-09-17 17:00 |  | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-08-14 08:00 | 2013-09-17 17:00 |  | PT_Normal |  |  |  |  | kzy5CsqBQDmXlC9kSEelhQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29030 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499494 | 6359 | 124305 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWTRAP4770 | Telephone Room Details-App |  | 600 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-14 08:00 | 2013-10-20 17:00 |  | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-09-14 08:00 | 2013-10-20 17:00 |  | PT_Normal |  |  |  |  | fcKCgnlqQeKO9ido5PoYrQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29030 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499495 | 6359 | 124305 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWGZAP4780 | Gazebo Plan & Details-App |  | 600 | 120 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-21 08:00 | 2013-11-24 17:00 |  | 2013-07-20 08:00 | 2013-08-26 17:00 | 2013-07-20 08:00 | 2013-08-26 17:00 | 2013-07-20 08:00 | 2013-08-26 17:00 | 2013-10-21 08:00 | 2013-11-24 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29030 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 499496 | 6359 | 124305 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI1BDWGHAP4790 | Guard House Plan & Details-App |  | 2296 | 2192 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2014-06-28 08:00 | 2014-07-31 17:00 |  | 2013-07-20 08:00 | 2013-08-26 17:00 | 2013-07-20 08:00 | 2013-08-26 17:00 | 2013-07-20 08:00 | 2013-08-26 17:00 | 2014-06-28 08:00 | 2014-07-31 17:00 |  | PT_Normal |  |  |  |  | mVZk+AsYRUG200NjhmO7Vw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29030 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124303 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 499497 | 6359 | 124307 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWELAP4550 | Single Line Diagram-App |  | 920 | 320 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-23 08:00 | 2013-08-29 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-07-23 08:00 | 2013-08-29 17:00 |  | PT_Normal |  |  |  |  | xA6se/DnQ7mXtRlLvqfo9g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28970 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124306 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499498 | 6359 | 124307 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWELAP4560 | Lighting Layout Drawings-App |  | 1176 | 720 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-19 08:00 | 2013-10-26 17:00 |  | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-09-19 08:00 | 2013-10-26 17:00 |  | PT_Normal |  |  |  |  | 8CkAfgUsTTaSRwX2Z5zjfw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28970 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124306 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499499 | 6359 | 124307 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWELAP4570 | Power Layout Drawings-App |  | 768 | 168 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-23 08:00 | 2013-08-29 17:00 |  | 2013-04-02 08:00 | 2013-05-06 17:00 | 2013-04-02 08:00 | 2013-05-06 17:00 | 2013-04-02 08:00 | 2013-05-06 17:00 | 2013-07-23 08:00 | 2013-08-29 17:00 |  | PT_Normal |  |  |  |  | ceWRgZ2gRXGC6i01Mh2ucg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28970 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124306 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499500 | 6359 | 124307 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWELAP4580 | Central Alarm Monitoring System Drawings-App |  | 1544 | 704 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-11-27 08:00 | 2014-01-01 17:00 |  | 2013-04-10 08:00 | 2013-05-14 17:00 | 2013-04-10 08:00 | 2013-05-14 17:00 | 2013-04-10 08:00 | 2013-05-14 17:00 | 2013-11-27 08:00 | 2014-01-01 17:00 |  | PT_Normal |  |  |  |  | sQGTlWmET3GBD8NT52r4zw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28970 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124306 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499501 | 6359 | 124307 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWELAP4590 | Audio Video Intercom System Drawings-App |  | 672 | 112 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-04 08:00 | 2013-09-10 17:00 |  | 2013-04-28 08:00 | 2013-06-01 17:00 | 2013-04-28 08:00 | 2013-06-01 17:00 | 2013-04-28 08:00 | 2013-06-01 17:00 | 2013-08-04 08:00 | 2013-09-10 17:00 |  | PT_Normal |  |  |  |  | lKwkWXk6QCa5H8Sh3Ju6QQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28970 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124306 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499502 | 6359 | 124307 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWELAP4600 | Telephone & TV System Drawings-App |  | 552 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-04 08:00 | 2013-09-10 17:00 |  | 2013-05-15 08:00 | 2013-06-18 17:00 | 2013-05-15 08:00 | 2013-06-18 17:00 | 2013-05-15 08:00 | 2013-06-18 17:00 | 2013-08-04 08:00 | 2013-09-10 17:00 |  | PT_Normal |  |  |  |  | o8fb8XV5SU6LKNoDxy44Yw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28970 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124306 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499503 | 6359 | 124308 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWELSM4550 | Single Line Diagram-Sub |  | 552 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-13 08:00 | 2013-05-29 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-05-13 08:00 | 2013-05-29 17:00 |  | PT_Normal |  |  |  |  | hZ5S6xn7RvaKsmvs5cZDWQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28960 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124306 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499504 | 6359 | 124308 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWELSM4560 | Lighting Layout Drawings-Sub |  | 552 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-30 08:00 | 2013-06-16 17:00 |  | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-05-30 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | 0fxYQCMDR2CpJxM1O0SqMw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28960 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124306 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499505 | 6359 | 124308 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWELSM4570 | Power Layout Drawings-Sub |  | 552 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-04 08:00 | 2013-06-20 17:00 |  | 2013-03-16 08:00 | 2013-04-01 17:00 | 2013-03-16 08:00 | 2013-04-01 17:00 | 2013-03-16 08:00 | 2013-04-01 17:00 | 2013-06-04 08:00 | 2013-06-20 17:00 |  | PT_Normal |  |  |  |  | NFnyFyWxSs+9GhkWQJ2ExA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28960 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124306 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499506 | 6359 | 124308 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWELSM4580 | Central Alarm Monitoring System Drawings-Sub |  | 552 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-12 08:00 | 2013-06-29 17:00 |  | 2013-03-24 08:00 | 2013-04-09 17:00 | 2013-03-24 08:00 | 2013-04-09 17:00 | 2013-03-24 08:00 | 2013-04-09 17:00 | 2013-06-12 08:00 | 2013-06-29 17:00 |  | PT_Normal |  |  |  |  | 41kT3BH6TWmNZ3Kf1V0img |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28960 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124306 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499507 | 6359 | 124308 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWELSM4590 | Audio Video Intercom System Drawings-Sub |  | 552 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-30 08:00 | 2013-07-16 17:00 |  | 2013-04-10 08:00 | 2013-04-27 17:00 | 2013-04-10 08:00 | 2013-04-27 17:00 | 2013-04-10 08:00 | 2013-04-27 17:00 | 2013-06-30 08:00 | 2013-07-16 17:00 |  | PT_Normal |  |  |  |  | XBYk3msXQaKIHOvLGB8TYQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28960 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124306 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499508 | 6359 | 124308 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWELSM4600 | Telephone & TV System Drawings-Sub |  | 552 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-17 08:00 | 2013-08-03 17:00 |  | 2013-04-28 08:00 | 2013-05-14 17:00 | 2013-04-28 08:00 | 2013-05-14 17:00 | 2013-04-28 08:00 | 2013-05-14 17:00 | 2013-07-17 08:00 | 2013-08-03 17:00 |  | PT_Normal |  |  |  |  | W0ylOBqKQsiXaoPk/0vmYw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28960 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124306 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499509 | 6359 | 124310 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWMEAP4610 | Plumbing Layout & Details Drawings-App |  | 424 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-12 08:00 | 2013-06-15 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-05-12 08:00 | 2013-06-15 17:00 |  | PT_Normal |  |  |  |  | WkMMx+ZfSm+elHPj90eY/Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29000 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124309 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499510 | 6359 | 124310 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWMEAP4620 | Drainage Layout & Details Drawings-App |  | 424 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-12 08:00 | 2013-06-15 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-05-12 08:00 | 2013-06-15 17:00 |  | PT_Normal |  |  |  |  | Qg6/Yu3KSVCI1eHG35ny/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29000 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124309 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499511 | 6359 | 124310 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWMEAP4630 | Fire Fighting Layout & Details Drawings-App |  | 1160 | 440 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-17 08:00 | 2013-10-23 17:00 |  | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-09-17 08:00 | 2013-10-23 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29000 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124309 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499512 | 6359 | 124310 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWMEAP4640 | AC Layout & Details Drawings-App |  | 512 | 80 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-08-01 17:00 |  | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | /C62U+14QSGEgPDQS7eRTg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29000 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124309 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499513 | 6359 | 124311 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWMESM4610 | Plumbing Layout & Details Drawings-Sub |  | 424 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-24 08:00 | 2013-05-11 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-04-24 08:00 | 2013-05-11 17:00 |  | PT_Normal |  |  |  |  | dt79AqwuT365e77xgO+avA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28990 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124309 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499514 | 6359 | 124311 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWMESM4620 | Drainage Layout & Details Drawings-Sub |  | 360 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-15 08:00 | 2013-05-01 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 |  | PT_Normal |  |  |  |  | gKvJ7AQBQlCzPLoWfKzWZQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 28990 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124309 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499515 | 6359 | 124311 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWMESM4630 | Fire Fighting Layout & Details Drawings-Sub |  | 360 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-02 08:00 | 2013-05-19 17:00 |  | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 |  | PT_Normal |  |  |  |  | +Xei0c2jQPKn+3WHBTIvBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 28990 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124309 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499516 | 6359 | 124311 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWMESM4640 | AC Layout & Details Drawings-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-20 08:00 | 2013-06-05 17:00 |  | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 |  | PT_Normal |  |  |  |  | K9gM07YBTsKTjYCq+chehg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 28990 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124309 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 499517 | 6359 | 124313 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWSTAP4400 | Footing Drawings-App |  | 464 | 464 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-03-10 08:00 | 2013-04-13 17:00 |  | 2012-12-31 08:00 | 2013-02-03 17:00 | 2012-12-31 08:00 | 2013-02-03 17:00 | 2012-12-31 08:00 | 2013-02-03 17:00 | 2013-03-10 08:00 | 2013-04-13 17:00 |  | PT_Normal |  |  |  |  | 0nprnVQ8TLy3pUtIHYFjZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28910 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499518 | 6359 | 124313 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWSTAP4410 | Grade Beam & Slab Drawings-App |  | 992 | 992 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-01 08:00 | 2013-07-04 17:00 |  | 2013-01-06 08:00 | 2013-02-09 17:00 | 2013-01-06 08:00 | 2013-02-09 17:00 | 2013-01-06 08:00 | 2013-02-09 17:00 | 2013-06-01 08:00 | 2013-07-04 17:00 |  | PT_Normal |  |  |  |  | f2gWDmNsRn+0zzOhBqoh1Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28910 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499519 | 6359 | 124313 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWSTAP4420 | Column Drawings-App |  | 1248 | 1248 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-14 08:00 | 2013-08-20 17:00 |  | 2013-01-12 08:00 | 2013-02-16 17:00 | 2013-01-12 08:00 | 2013-02-16 17:00 | 2013-01-12 08:00 | 2013-02-16 17:00 | 2013-07-14 08:00 | 2013-08-20 17:00 |  | PT_Normal |  |  |  |  | OQNEjdsFQVWUC0tDKEHPmA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28910 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499520 | 6359 | 124313 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWSTAP4430 | GF Beams & Slabs Drawings-App |  | 1328 | 1328 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-06 08:00 | 2013-09-12 17:00 |  | 2013-01-23 08:00 | 2013-02-27 17:00 | 2013-01-23 08:00 | 2013-02-27 17:00 | 2013-01-23 08:00 | 2013-02-27 17:00 | 2013-08-06 08:00 | 2013-09-12 17:00 |  | PT_Normal |  |  |  |  | D0XNeGZjRuW7ngZ5dRpjgg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28910 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499521 | 6359 | 124313 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWSTAP4440 | FF Beams & Slabs Drawings-App |  | 1336 | 1336 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-28 08:00 | 2013-10-01 17:00 |  | 2013-02-10 08:00 | 2013-03-17 17:00 | 2013-02-10 08:00 | 2013-03-17 17:00 | 2013-02-10 08:00 | 2013-03-17 17:00 | 2013-08-28 08:00 | 2013-10-01 17:00 |  | PT_Normal |  |  |  |  | tNhJ1fmzT2CIOXo801k/EA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28910 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499522 | 6359 | 124314 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWSTSM4400 | Footing Drawings-Sub |  | 336 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-01-31 08:00 | 2013-02-18 17:00 |  | 2012-12-12 08:00 | 2012-12-30 17:00 | 2012-12-12 08:00 | 2012-12-30 17:00 | 2012-12-12 08:00 | 2012-12-30 17:00 | 2013-01-31 08:00 | 2013-02-18 17:00 |  | PT_Normal |  |  |  |  | qockfVEHSPiHUXGwxrywuw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28900 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499523 | 6359 | 124314 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWSTSM4410 | Grade Beam & Slab Drawings-Sub |  | 336 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-02-06 08:00 | 2013-02-24 17:00 |  | 2012-12-19 08:00 | 2013-01-05 17:00 | 2012-12-19 08:00 | 2013-01-05 17:00 | 2012-12-19 08:00 | 2013-01-05 17:00 | 2013-02-06 08:00 | 2013-02-24 17:00 |  | PT_Normal |  |  |  |  | 4w2daZ28SW6ktsaUHn11iA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28900 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499524 | 6359 | 124314 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWSTSM4420 | Column Drawings-Sub |  | 336 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-02-13 08:00 | 2013-03-02 17:00 |  | 2012-12-25 08:00 | 2013-01-10 17:00 | 2012-12-25 08:00 | 2013-01-10 17:00 | 2012-12-25 08:00 | 2013-01-10 17:00 | 2013-02-13 08:00 | 2013-03-02 17:00 |  | PT_Normal |  |  |  |  | YGbzGXA8RIiaIbe7SIcjHw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28900 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499525 | 6359 | 124314 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWSTSM4430 | GF Beams & Slabs Drawings-Sub |  | 336 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-02-25 08:00 | 2013-03-13 17:00 |  | 2013-01-06 08:00 | 2013-01-22 17:00 | 2013-01-06 08:00 | 2013-01-22 17:00 | 2013-01-06 08:00 | 2013-01-22 17:00 | 2013-02-25 08:00 | 2013-03-13 17:00 |  | PT_Normal |  |  |  |  | w7upkBRxTsi1cVzEidmcLQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28900 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499526 | 6359 | 124314 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWSTSM4440 | FF Beams & Slabs Drawings-Sub |  | 336 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-03-14 08:00 | 2013-03-31 17:00 |  | 2013-01-23 08:00 | 2013-02-09 17:00 | 2013-01-23 08:00 | 2013-02-09 17:00 | 2013-01-23 08:00 | 2013-02-09 17:00 | 2013-03-14 08:00 | 2013-03-31 17:00 |  | PT_Normal |  |  |  |  | xC+DVwL5Q4aEokislLkDUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28900 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499527 | 6359 | 124316 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARAP4450 | Ground Floor Plan-App |  | 656 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-04 08:00 | 2013-07-08 17:00 |  | 2013-02-28 08:00 | 2013-04-03 17:00 | 2013-02-28 08:00 | 2013-04-03 17:00 | 2013-02-28 08:00 | 2013-04-03 17:00 | 2013-06-04 08:00 | 2013-07-08 17:00 |  | PT_Normal |  |  |  |  | YI0kQzVWQxaDdmGd+9GD3g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28940 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499528 | 6359 | 124316 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARAP4460 | First Floor Plan-App |  | 448 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-13 08:00 | 2013-06-16 17:00 |  | 2013-03-09 08:00 | 2013-04-11 17:00 | 2013-03-09 08:00 | 2013-04-11 17:00 | 2013-03-09 08:00 | 2013-04-11 17:00 | 2013-05-13 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | dcx9rNTySnST9GQsGyqOnQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28940 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499529 | 6359 | 124316 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARAP4470 | Roof Floor Plan-App |  | 392 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-13 08:00 | 2013-06-16 17:00 |  | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-05-13 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | fcl+FesTSmmxanbZyYQrUw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28940 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499530 | 6359 | 124316 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARAP4500 | Ceramic Flooring & Wall Drawings-App |  | 336 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-14 08:00 | 2013-06-17 17:00 |  | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 |  | PT_Normal |  |  |  |  | IWpFw1FuQh6asWwxQuWm2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28940 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499531 | 6359 | 124316 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARAP4510 | Porcelain Floor Drawings-App |  | 408 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-25 08:00 | 2013-06-27 17:00 |  | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-05-25 08:00 | 2013-06-27 17:00 |  | PT_Normal |  |  |  |  | vv7vXs3QS7qEvivkAQlIww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28940 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499532 | 6359 | 124316 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARAP4520 | Cobble & Slate Flooring Drawings-App |  | 656 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-30 08:00 | 2013-08-03 17:00 |  | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-06-30 08:00 | 2013-08-03 17:00 |  | PT_Normal |  |  |  |  | LsCP8ATiSPC0ZsUaT1+gSQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28940 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499533 | 6359 | 124316 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARAP4490 | Aluminum False Ceiling Drawings-App |  | 656 | 320 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-06 08:00 | 2013-08-08 17:00 |  | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-07-06 08:00 | 2013-08-08 17:00 |  | PT_Normal |  |  |  |  | 444KF4zoR4GyaQd54cTAUQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28940 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499534 | 6359 | 124316 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARAP4530 | Doors & Window Drawings-App |  | 392 | 184 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-17 08:00 | 2013-07-21 17:00 |  | 2013-04-21 08:00 | 2013-05-25 17:00 | 2013-04-21 08:00 | 2013-05-25 17:00 | 2013-04-21 08:00 | 2013-05-25 17:00 | 2013-06-17 08:00 | 2013-07-21 17:00 |  | PT_Normal |  |  |  |  | FYsoknPATVaZYaK56dxL6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28940 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499535 | 6359 | 124316 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARAP4540 | Carpentry & Joinery Drawings-App |  | 664 | 320 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-30 08:00 | 2013-09-05 17:00 |  | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-07-30 08:00 | 2013-09-05 17:00 |  | PT_Normal |  |  |  |  | P6O8Mft6QCm+qDW7b+9gwg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28940 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499536 | 6359 | 124316 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARAP4480 | Gypsum False Ceiling Drawings-App |  | 536 | 280 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-18 08:00 | 2013-07-22 17:00 |  | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-06-18 08:00 | 2013-07-22 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28940 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499537 | 6359 | 124317 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARSM4450 | Ground Floor Plan-Sub |  | 336 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-01 08:00 | 2013-04-17 17:00 |  | 2013-02-10 08:00 | 2013-02-27 17:00 | 2013-02-10 08:00 | 2013-02-27 17:00 | 2013-02-10 08:00 | 2013-02-27 17:00 | 2013-04-01 08:00 | 2013-04-17 17:00 |  | PT_Normal |  |  |  |  | JK4yPrnDRAS7kqAtvN3B1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28930 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 30 | 0
%R | 499538 | 6359 | 124317 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARSM4460 | First Floor Plan-Sub |  | 336 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-09 08:00 | 2013-04-25 17:00 |  | 2013-02-19 08:00 | 2013-03-07 17:00 | 2013-02-19 08:00 | 2013-03-07 17:00 | 2013-02-19 08:00 | 2013-03-07 17:00 | 2013-04-09 08:00 | 2013-04-25 17:00 |  | PT_Normal |  |  |  |  | Nt5Ybjr7Qq6Jp3xB9EQIdw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28930 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 30 | 0
%R | 499539 | 6359 | 124317 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARSM4470 | Roof Floor Plan-Sub |  | 376 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-23 08:00 | 2013-05-09 17:00 |  | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-04-23 08:00 | 2013-05-09 17:00 |  | PT_Normal |  |  |  |  | dbW4JIqTQSmacs8j496UdA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28930 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499540 | 6359 | 124317 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARSM4500 | Ceramic Flooring & Wall Drawings-Sub |  | 336 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-27 08:00 | 2013-05-13 17:00 |  | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-04-27 08:00 | 2013-05-13 17:00 |  | PT_Normal |  |  |  |  | U+24XX15TSGII6gL46x00g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28930 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499541 | 6359 | 124317 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARSM4510 | Porcelain Floor Drawings-Sub |  | 408 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-07 08:00 | 2013-05-23 17:00 |  | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-05-07 08:00 | 2013-05-23 17:00 |  | PT_Normal |  |  |  |  | rbk2pjXgQZ2wj859lM4LaQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28930 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499542 | 6359 | 124317 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARSM4520 | Cobble & Slate Flooring Drawings-Sub |  | 656 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-12 08:00 | 2013-06-29 17:00 |  | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-06-12 08:00 | 2013-06-29 17:00 |  | PT_Normal |  |  |  |  | G4HQ+2+5RGG3DzKPkJkhDQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28930 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499543 | 6359 | 124317 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARSM4480 | Gypsum False Ceiling Drawings-Sub |  | 536 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-01 08:00 | 2013-06-17 17:00 |  | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-06-01 08:00 | 2013-06-17 17:00 |  | PT_Normal |  |  |  |  | dCmmZST/R2WTPLEQgPMdvg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28930 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499544 | 6359 | 124317 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARSM4490 | Aluminum False Ceiling Drawings-Sub |  | 656 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-18 08:00 | 2013-07-04 17:00 |  | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-06-18 08:00 | 2013-07-04 17:00 |  | PT_Normal |  |  |  |  | I0kf8/ygRS2DISZkoLA4rA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28930 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499545 | 6359 | 124317 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARSM4530 | Doors & window Drawings-Sub |  | 488 | 96 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-30 08:00 | 2013-06-16 17:00 |  | 2013-03-20 08:00 | 2013-04-06 17:00 | 2013-03-20 08:00 | 2013-04-06 17:00 | 2013-03-20 08:00 | 2013-04-06 17:00 | 2013-05-30 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | 4DW04uT0QYCpIJIJyl7doQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28930 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499546 | 6359 | 124317 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP1BDWARSM4540 | Carpentry & Joinery Drawings-Sub |  | 664 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-13 08:00 | 2013-07-29 17:00 |  | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-07-13 08:00 | 2013-07-29 17:00 |  | PT_Normal |  |  |  |  | i7S6Ki4bRUa0jFCebnzwqQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28930 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124315 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499547 | 6359 | 124321 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWSTAP5180 | Footing Drawings-App |  | 560 | 560 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 |  |  |  | 2013-03-02 08:00 | 2013-03-30 17:00 |  | 2012-12-08 08:00 | 2013-01-06 17:00 | 2012-12-08 08:00 | 2013-01-06 17:00 | 2012-12-08 08:00 | 2013-01-06 17:00 | 2013-03-02 08:00 | 2013-03-30 17:00 |  | PT_Normal |  |  |  |  | XKbgn82hQHqWrP9GOqxTeg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29250 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124320 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499548 | 6359 | 124321 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWSTAP5190 | Grade Beam & Slab Drawings-App |  | 792 | 792 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-16 08:00 | 2013-05-20 17:00 |  | 2012-12-20 08:00 | 2013-01-23 17:00 | 2012-12-20 08:00 | 2013-01-23 17:00 | 2012-12-20 08:00 | 2013-01-23 17:00 | 2013-04-16 08:00 | 2013-05-20 17:00 |  | PT_Normal |  |  |  |  | asTRZTftQRCSTOR4Rdctxw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29250 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124320 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499549 | 6359 | 124321 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWSTAP5200 | Column Drawings-App |  | 1040 | 1024 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-28 08:00 | 2013-07-01 17:00 |  | 2012-12-26 08:00 | 2013-01-29 17:00 | 2012-12-26 08:00 | 2013-01-29 17:00 | 2012-12-26 08:00 | 2013-01-29 17:00 | 2013-05-28 08:00 | 2013-07-01 17:00 |  | PT_Normal |  |  |  |  | AjqLhrWzRPeXRWD2rprIPA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29250 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124320 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499550 | 6359 | 124321 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWSTAP5210 | GF Beams & Slabs Drawings-App |  | 1088 | 1072 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-16 08:00 | 2013-07-20 17:00 |  | 2013-01-07 08:00 | 2013-02-10 17:00 | 2013-01-07 08:00 | 2013-02-10 17:00 | 2013-01-07 08:00 | 2013-02-10 17:00 | 2013-06-16 08:00 | 2013-07-20 17:00 |  | PT_Normal |  |  |  |  | RBjX3J2hQga4gUTm97Pm1w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29250 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124320 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499551 | 6359 | 124322 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWSTSM5180 | Footing Drawings-Sub |  | 560 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-02-18 08:00 | 2013-02-28 17:00 |  | 2012-11-26 08:00 | 2012-12-06 17:00 | 2012-11-26 08:00 | 2012-12-06 17:00 | 2012-11-26 08:00 | 2012-12-06 17:00 | 2013-02-18 08:00 | 2013-02-28 17:00 |  | PT_Normal |  |  |  |  | O4KXvRTdSOylWNRjzQmMqQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29240 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124320 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 20 | 0
%R | 499552 | 6359 | 124322 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWSTSM5190 | Grade Beam & Slab Drawings-Sub |  | 600 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-03-02 08:00 | 2013-03-18 17:00 |  | 2012-12-02 08:00 | 2012-12-19 17:00 | 2012-12-02 08:00 | 2012-12-19 17:00 | 2012-12-02 08:00 | 2012-12-19 17:00 | 2013-03-02 08:00 | 2013-03-18 17:00 |  | PT_Normal |  |  |  |  | YUrqjKtrSMemQ01ebZGmlA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29240 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124320 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499553 | 6359 | 124322 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWSTSM5200 | Column Drawings-Sub |  | 600 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-03-07 08:00 | 2013-03-24 17:00 |  | 2012-12-08 08:00 | 2012-12-25 17:00 | 2012-12-08 08:00 | 2012-12-25 17:00 | 2012-12-08 08:00 | 2012-12-25 17:00 | 2013-03-07 08:00 | 2013-03-24 17:00 |  | PT_Normal |  |  |  |  | UkgJGdMPSjqigEBbmv8BUQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29240 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124320 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499554 | 6359 | 124322 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWSTSM5210 | GF Beams & Slabs Drawings-Sub |  | 600 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-03-19 08:00 | 2013-04-04 17:00 |  | 2012-12-20 08:00 | 2013-01-06 17:00 | 2012-12-20 08:00 | 2013-01-06 17:00 | 2012-12-20 08:00 | 2013-01-06 17:00 | 2013-03-19 08:00 | 2013-04-04 17:00 |  | PT_Normal |  |  |  |  | a84KaenBR3W0StOUmukI8A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29240 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124320 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499555 | 6359 | 124324 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWELAP5460 | Electrical Line Layout & Details-App |  | 960 | 240 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2013-11-16 17:00 |  | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-10-10 08:00 | 2013-11-16 17:00 |  | PT_Normal |  |  |  |  | 70jj3V5CQCKbNPiVScNlSw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29370 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499556 | 6359 | 124324 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWSTAP5470 | Street Lighting Layout & details -App |  | 960 | 240 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2013-11-16 17:00 |  | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-10-10 08:00 | 2013-11-16 17:00 |  | PT_Normal |  |  |  |  | nJ590dRUTR6BoM0qBTVDWw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29370 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499557 | 6359 | 124324 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWDRAP5430 | Drainage Line Layout & Details-App |  | 512 | 296 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-16 08:00 | 2013-08-22 17:00 |  | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-07-16 08:00 | 2013-08-22 17:00 |  | PT_Normal |  |  |  |  | Lqvx07zoTVOHw/yM34uluw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29370 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499558 | 6359 | 124324 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWFFAP5440 | Fire Fighting Line Layout & Details-App |  | 360 | 320 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-24 08:00 | 2013-07-28 17:00 |  | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-06-24 08:00 | 2013-07-28 17:00 |  | PT_Normal |  |  |  |  | cg8t62/vQ0+CnXnshy7ggw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29370 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499559 | 6359 | 124324 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWWSAP5450 | Water Supply Line Layout & Details-App |  | 688 | 296 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-14 08:00 | 2013-09-17 17:00 |  | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-08-14 08:00 | 2013-09-17 17:00 |  | PT_Normal |  |  |  |  | CmvIEwGeRt23bfolfm3nYQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29370 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499560 | 6359 | 124324 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWIRAP5490 | Irrigation Layout & Details-App |  | 728 | 120 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-24 08:00 | 2013-10-30 17:00 |  | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-09-24 08:00 | 2013-10-30 17:00 |  | PT_Normal |  |  |  |  | KIaRLhLBSa68uaTcXCap0w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29370 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499561 | 6359 | 124324 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWTCAP5480 | Telecommunication Line Layout & Details-App |  | 960 | 480 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2013-11-16 17:00 |  | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-10-10 08:00 | 2013-11-16 17:00 |  | PT_Normal |  |  |  |  | f/W3tQKoQ627k9qHxN1m5Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29370 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499562 | 6359 | 124324 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWPSAP5520 | Parking Shed Layout & Details Drawings-App |  | 1200 | 184 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-12-12 08:00 | 2014-01-16 17:00 |  | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-12-12 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | TlhOYPDPQgiCY7LjhAvT8w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29370 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499563 | 6359 | 124324 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWSLAP5500 | Soft & HardLandscaping Layout & Detail-App |  | 536 | 360 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-27 08:00 | 2013-09-30 17:00 |  | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-08-27 08:00 | 2013-09-30 17:00 |  | PT_Normal |  |  |  |  | T+LiIV8sRGyYBPlrmhxqAA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29370 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499564 | 6359 | 124324 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWBWAP5510 | Boundary Wall Layout & Details-App |  | 680 | 360 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-17 08:00 | 2013-10-23 17:00 |  | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-09-17 08:00 | 2013-10-23 17:00 |  | PT_Normal |  |  |  |  | hqGlQcVoSOakUIvFT2De5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29370 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499565 | 6359 | 124324 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWRWAP5530 | Road Layout & Details-App |  | 1192 | 184 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-12-11 08:00 | 2014-01-15 17:00 |  | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-12-11 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | 6HHC0SoVTECwqsy4ZGUdVA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29370 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499566 | 6359 | 124324 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWIWAP5540 | Irrigation Water Tank & Pump Room Details-App |  | 392 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-14 08:00 | 2013-09-17 17:00 |  | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-08-14 08:00 | 2013-09-17 17:00 |  | PT_Normal |  |  |  |  | 0EC4VczaSQu2TpuY+vce3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29370 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499567 | 6359 | 124324 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWGZAP5550 | Gazebo Plan & Details-App |  | 720 | 240 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-21 08:00 | 2013-11-24 17:00 |  | 2013-07-02 08:00 | 2013-08-05 17:00 | 2013-07-02 08:00 | 2013-08-05 17:00 | 2013-07-02 08:00 | 2013-08-05 17:00 | 2013-10-21 08:00 | 2013-11-24 17:00 |  | PT_Normal |  |  |  |  | HRWBZk2cR9CGiOa3mUGTHA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29370 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 499568 | 6359 | 124325 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWELSM5460 | Electrical Line Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-07-15 17:00 |  | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-07-15 17:00 |  | PT_Normal |  |  |  |  | yqlmeltWRLK0fZyzn5r3ng |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29360 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499569 | 6359 | 124325 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWSTSM5470 | Street Lighting Layout & details -Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-07-15 17:00 |  | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-07-15 17:00 |  | PT_Normal |  |  |  |  | aJZNU4NrRdeBCwd6zMeuQA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29360 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499570 | 6359 | 124325 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWDRSM5430 | Drainage Line Layout & Details-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-23 17:00 |  | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-06-06 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | 1nK9+NlrS1OYOvBa7Lmakw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29360 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499571 | 6359 | 124325 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWFFSM5440 | Fire Fighting Line Layout & Details-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-23 17:00 |  | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-06-06 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | 9Zh5FlbqS1upu+trbTqPlA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29360 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499572 | 6359 | 124325 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWWSSM5450 | Water Supply Line Layout & Details-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-23 17:00 |  | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-06-06 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | BS0bcahNSkqZdAbHKnuJEA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29360 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499573 | 6359 | 124325 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWIRSM5490 | Irrigation Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-16 08:00 | 2013-08-01 17:00 |  | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-07-16 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | 1u7UmYtoR0iN4yxjQxZ7Fw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29360 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499574 | 6359 | 124325 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWTCSM5480 | Telecommunication Line Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-07-15 17:00 |  | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-07-15 17:00 |  | PT_Normal |  |  |  |  | P0ivcQZLRWOd+WgrUBzBPQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29360 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499575 | 6359 | 124325 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWPSSM5520 | Parking Shed Layout & Details Drawings-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-24 08:00 | 2013-08-13 17:00 |  | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-07-24 08:00 | 2013-08-13 17:00 |  | PT_Normal |  |  |  |  | AIv+WjTFQ3KOIHyFZ6KjBQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29360 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499576 | 6359 | 124325 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWSLSM5500 | Soft & HardLandscaping Layout & Detail-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-16 08:00 | 2013-08-01 17:00 |  | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-07-16 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | DCox8G4KRIinpNuTnsrJhw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29360 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499577 | 6359 | 124325 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWBWSM5510 | Boundary Wall Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-16 08:00 | 2013-08-01 17:00 |  | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-07-16 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | yyQFbfcfS7+TSFY/iKFgkA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29360 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499578 | 6359 | 124325 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWRWSM5530 | Road Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-24 08:00 | 2013-08-13 17:00 |  | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-07-24 08:00 | 2013-08-13 17:00 |  | PT_Normal |  |  |  |  | p1PtBv+RRFaBtEvX/cynag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29360 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499579 | 6359 | 124325 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWIWSM5540 | Irrigation Water Tank & Pump Room Details- Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-24 08:00 | 2013-08-13 17:00 |  | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-07-24 08:00 | 2013-08-13 17:00 |  | PT_Normal |  |  |  |  | 4yIrfW3wRZSMCmmpy7xf/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29360 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499580 | 6359 | 124325 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI2BDWGZSM5550 | Gazebo Plan & Details-Sub |  | 720 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-10-01 08:00 | 2013-10-20 17:00 |  | 2013-06-15 08:00 | 2013-07-01 17:00 | 2013-06-15 08:00 | 2013-07-01 17:00 | 2013-06-15 08:00 | 2013-07-01 17:00 | 2013-10-01 08:00 | 2013-10-20 17:00 |  | PT_Normal |  |  |  |  | IvzlKFQTRq6zGYaNRS1uyQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29360 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124323 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 30 | 0
%R | 499581 | 6359 | 124327 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWMEAP5390 | Plumbing Layout & Details Drawings-App |  | 424 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-12 08:00 | 2013-06-15 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-05-12 08:00 | 2013-06-15 17:00 |  | PT_Normal |  |  |  |  | opw0b67ARtue6iX5nlriGg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29340 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124326 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499582 | 6359 | 124327 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWMEAP5400 | Drainage Layout & Details Drawings-App |  | 424 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-12 08:00 | 2013-06-15 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-05-12 08:00 | 2013-06-15 17:00 |  | PT_Normal |  |  |  |  | HVa8RzG3SqOC9rxcHObyqA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29340 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124326 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499583 | 6359 | 124327 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWMEAP5410 | Fire Fighting Layout & Details Drawings-App |  | 1160 | 440 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-17 08:00 | 2013-10-23 17:00 |  | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-09-17 08:00 | 2013-10-23 17:00 |  | PT_Normal |  |  |  |  | 9fiBitq9SbqtHNpO/dorVg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29340 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124326 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499584 | 6359 | 124327 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWMEAP5420 | AC Layout & Details Drawings-App |  | 512 | 80 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-08-01 17:00 |  | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | 7a67ZEUTQiCvSQTZeJH+VQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29340 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124326 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499585 | 6359 | 124328 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWMESM5390 | Plumbing Layout & Details Drawings-Sub |  | 424 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-24 08:00 | 2013-05-11 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-04-24 08:00 | 2013-05-11 17:00 |  | PT_Normal |  |  |  |  | SS25S7ERRqO/PR1jPu3nIw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29330 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124326 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499586 | 6359 | 124328 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWMESM5400 | Drainage Layout & Details Drawings-Sub |  | 360 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-15 08:00 | 2013-05-01 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 |  | PT_Normal |  |  |  |  | XSxloOOGSIOkR4esKnkwQw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29330 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124326 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499587 | 6359 | 124328 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWMESM5410 | Fire Fighting Layout & Details Drawings-Sub |  | 360 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-02 08:00 | 2013-05-19 17:00 |  | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 |  | PT_Normal |  |  |  |  | 0rXWLa53R82k41SnByOIEw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29330 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124326 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499588 | 6359 | 124328 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWMESM5420 | AC Layout & Details Drawings-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-20 08:00 | 2013-06-05 17:00 |  | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 |  | PT_Normal |  |  |  |  | KsmRFEBJSBSMYMyUzoOQfQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29330 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124326 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 499589 | 6359 | 124330 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWELSM5330 | Single Line Diagram-Sub |  | 472 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-01 08:00 | 2013-05-18 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-05-01 08:00 | 2013-05-18 17:00 |  | PT_Normal |  |  |  |  | ahaS1RBkRHyUEsCACa8e4A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29300 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124329 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499590 | 6359 | 124330 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWELSM5340 | Lighting Layout Drawings-Sub |  | 472 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-07 08:00 | 2013-05-23 17:00 |  | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-05-07 08:00 | 2013-05-23 17:00 |  | PT_Normal |  |  |  |  | /4P8dCNJSfGL+Y/VJu7zZQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29300 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124329 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499591 | 6359 | 124330 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWELSM5350 | Power Layout Drawings-Sub |  | 600 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-26 08:00 | 2013-06-11 17:00 |  | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-05-26 08:00 | 2013-06-11 17:00 |  | PT_Normal |  |  |  |  | bFh+VyXtR0a+QBEFEKkpJw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29300 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124329 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499592 | 6359 | 124330 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWELSM5360 | Central Alarm Monitoring System Drawings-Sub |  | 600 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-12 08:00 | 2013-06-29 17:00 |  | 2013-03-17 08:00 | 2013-04-02 17:00 | 2013-03-17 08:00 | 2013-04-02 17:00 | 2013-03-17 08:00 | 2013-04-02 17:00 | 2013-06-12 08:00 | 2013-06-29 17:00 |  | PT_Normal |  |  |  |  | VwGdNAa0RPOxmr+Sv0rUaw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29300 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124329 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499593 | 6359 | 124330 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWELSM5370 | Audio Video Intercom System Drawings-Sub |  | 600 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-30 08:00 | 2013-07-16 17:00 |  | 2013-04-03 08:00 | 2013-04-20 17:00 | 2013-04-03 08:00 | 2013-04-20 17:00 | 2013-04-03 08:00 | 2013-04-20 17:00 | 2013-06-30 08:00 | 2013-07-16 17:00 |  | PT_Normal |  |  |  |  | UGZe2Bd6SbCRSvlqY8pEeg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29300 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124329 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499594 | 6359 | 124330 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWELSM5380 | Telephone & TV System Drawings-Sub |  | 600 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-17 08:00 | 2013-08-03 17:00 |  | 2013-04-21 08:00 | 2013-05-07 17:00 | 2013-04-21 08:00 | 2013-05-07 17:00 | 2013-04-21 08:00 | 2013-05-07 17:00 | 2013-07-17 08:00 | 2013-08-03 17:00 |  | PT_Normal |  |  |  |  | XCYYaiN8Qy+qTDW7UIziQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29300 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124329 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499595 | 6359 | 124331 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWELAP5330 | Single Line Diagram-App |  | 920 | 320 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-23 08:00 | 2013-08-29 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-07-23 08:00 | 2013-08-29 17:00 |  | PT_Normal |  |  |  |  | M/t9f4W3TIWjdrXyIa5k7g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29310 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124329 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499596 | 6359 | 124331 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWELAP5340 | Lighting Layout Drawings-App |  | 472 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-25 08:00 | 2013-06-27 17:00 |  | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-05-25 08:00 | 2013-06-27 17:00 |  | PT_Normal |  |  |  |  | q6s3tuTITBKsuFsDwp4h2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29310 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124329 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499597 | 6359 | 124331 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWELAP5350 | Power Layout Drawings-App |  | 880 | 280 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-23 08:00 | 2013-08-29 17:00 |  | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-07-23 08:00 | 2013-08-29 17:00 |  | PT_Normal |  |  |  |  | Sqh/JDFSQK6uwseWXmUe6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29310 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124329 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499598 | 6359 | 124331 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWELAP5360 | Central Alarm Monitoring System Drawings-App |  | 792 | 160 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-28 08:00 | 2013-09-03 17:00 |  | 2013-04-03 08:00 | 2013-05-07 17:00 | 2013-04-03 08:00 | 2013-05-07 17:00 | 2013-04-03 08:00 | 2013-05-07 17:00 | 2013-07-28 08:00 | 2013-09-03 17:00 |  | PT_Normal |  |  |  |  | PxrSlTNMRT+la+iP09Uw2w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29310 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124329 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499599 | 6359 | 124331 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWELAP5370 | Audio Video Intercom System Drawings-App |  | 720 | 160 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-04 08:00 | 2013-09-10 17:00 |  | 2013-04-21 08:00 | 2013-05-25 17:00 | 2013-04-21 08:00 | 2013-05-25 17:00 | 2013-04-21 08:00 | 2013-05-25 17:00 | 2013-08-04 08:00 | 2013-09-10 17:00 |  | PT_Normal |  |  |  |  | h7GNq7DyTne4FH9BS7oqog |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29310 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124329 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499600 | 6359 | 124331 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWELAP5380 | Telephone & TV System Drawings-App |  | 600 | 48 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-04 08:00 | 2013-09-10 17:00 |  | 2013-05-08 08:00 | 2013-06-11 17:00 | 2013-05-08 08:00 | 2013-06-11 17:00 | 2013-05-08 08:00 | 2013-06-11 17:00 | 2013-08-04 08:00 | 2013-09-10 17:00 |  | PT_Normal |  |  |  |  | hSxFEBf+RP6Ca/OgqOEOEQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29310 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124329 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499601 | 6359 | 124333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWARAP5230 | Ground Floor Plan-App |  | 888 | 232 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-04 08:00 | 2013-07-08 17:00 |  | 2013-01-24 08:00 | 2013-02-28 17:00 | 2013-01-24 08:00 | 2013-02-28 17:00 | 2013-01-24 08:00 | 2013-02-28 17:00 | 2013-06-04 08:00 | 2013-07-08 17:00 |  | PT_Normal |  |  |  |  | vDLG5auhSMOU7ZYNfV906A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29280 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124332 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499602 | 6359 | 124333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWARAP5250 | Roof Floor Plan-App |  | 616 | 128 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-13 08:00 | 2013-06-16 17:00 |  | 2013-02-11 08:00 | 2013-03-18 17:00 | 2013-02-11 08:00 | 2013-03-18 17:00 | 2013-02-11 08:00 | 2013-03-18 17:00 | 2013-05-13 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | D2PZZKTlQ9OzRKERbMJcig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29280 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124332 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499603 | 6359 | 124333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWARAP5260 | Ceramic Flooring & Wall Drawings-App |  | 600 | 264 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-14 08:00 | 2013-06-17 17:00 |  | 2013-02-16 08:00 | 2013-03-21 17:00 | 2013-02-16 08:00 | 2013-03-21 17:00 | 2013-02-16 08:00 | 2013-03-21 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 |  | PT_Normal |  |  |  |  | L77b2ZzfTj2KRcRKF3R7mQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29280 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124332 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499604 | 6359 | 124333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWARAP5270 | Porcelain Floor Drawings-App |  | 672 | 264 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-25 08:00 | 2013-06-27 17:00 |  | 2013-02-16 08:00 | 2013-03-21 17:00 | 2013-02-16 08:00 | 2013-03-21 17:00 | 2013-02-16 08:00 | 2013-03-21 17:00 | 2013-05-25 08:00 | 2013-06-27 17:00 |  | PT_Normal |  |  |  |  | XQ+XkwvCTUS7Wp+EB31xOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29280 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124332 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499605 | 6359 | 124333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWARAP5280 | Cobble & Slate Flooring Drawings-App |  | 920 | 264 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-30 08:00 | 2013-08-03 17:00 |  | 2013-02-16 08:00 | 2013-03-21 17:00 | 2013-02-16 08:00 | 2013-03-21 17:00 | 2013-02-16 08:00 | 2013-03-21 17:00 | 2013-06-30 08:00 | 2013-08-03 17:00 |  | PT_Normal |  |  |  |  | fW5c1ygFSTGWzAPlF+KBFg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29280 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124332 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499606 | 6359 | 124333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWARAP5290 | Gypsum False Ceiling Drawings-App |  | 536 | 280 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-18 08:00 | 2013-07-22 17:00 |  | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-06-18 08:00 | 2013-07-22 17:00 |  | PT_Normal |  |  |  |  | prpXs9vUR4Guwf98eeBvmA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29280 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124332 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499607 | 6359 | 124333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWARAP5310 | Doors & Window Drawings-App |  | 488 | 280 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-17 08:00 | 2013-07-21 17:00 |  | 2013-04-07 08:00 | 2013-05-11 17:00 | 2013-04-07 08:00 | 2013-05-11 17:00 | 2013-04-07 08:00 | 2013-05-11 17:00 | 2013-06-17 08:00 | 2013-07-21 17:00 |  | PT_Normal |  |  |  |  | efeQrSKjRKaw50wDVesxsQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29280 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124332 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499608 | 6359 | 124333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWARAP5320 | Carpentry & Joinery Drawings-App |  | 664 | 320 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-30 08:00 | 2013-09-05 17:00 |  | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-07-30 08:00 | 2013-09-05 17:00 |  | PT_Normal |  |  |  |  | t7r1Zzf2QmaOUOj++ShB3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29280 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124332 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499609 | 6359 | 124334 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWARSM5230 | Ground Floor Plan-Sub |  | 600 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-06 08:00 | 2013-04-22 17:00 |  | 2013-01-07 08:00 | 2013-01-23 17:00 | 2013-01-07 08:00 | 2013-01-23 17:00 | 2013-01-07 08:00 | 2013-01-23 17:00 | 2013-04-06 08:00 | 2013-04-22 17:00 |  | PT_Normal |  |  |  |  | VuO2VS9AQK67RBs7NrpdJQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29270 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124332 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499610 | 6359 | 124334 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWARSM5250 | Roof Floor Plan-Sub |  | 600 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-23 08:00 | 2013-05-09 17:00 |  | 2013-01-24 08:00 | 2013-02-10 17:00 | 2013-01-24 08:00 | 2013-02-10 17:00 | 2013-01-24 08:00 | 2013-02-10 17:00 | 2013-04-23 08:00 | 2013-05-09 17:00 |  | PT_Normal |  |  |  |  | q1UYEaxbSsyKTEXvVdyR8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29270 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124332 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499611 | 6359 | 124334 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWARSM5260 | Ceramic Flooring & Wall Drawings-Sub |  | 600 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-27 08:00 | 2013-05-13 17:00 |  | 2013-01-28 08:00 | 2013-02-14 17:00 | 2013-01-28 08:00 | 2013-02-14 17:00 | 2013-01-28 08:00 | 2013-02-14 17:00 | 2013-04-27 08:00 | 2013-05-13 17:00 |  | PT_Normal |  |  |  |  | QPCUPhoAROKIWoH683Be4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29270 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124332 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499612 | 6359 | 124334 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWARSM5270 | Porcelain Floor Drawings-Sub |  | 672 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-07 08:00 | 2013-05-23 17:00 |  | 2013-01-28 08:00 | 2013-02-14 17:00 | 2013-01-28 08:00 | 2013-02-14 17:00 | 2013-01-28 08:00 | 2013-02-14 17:00 | 2013-05-07 08:00 | 2013-05-23 17:00 |  | PT_Normal |  |  |  |  | PRcC1QtsTua6gumsU19DjA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29270 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124332 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499613 | 6359 | 124334 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWARSM5280 | Cobble & Slate Flooring Drawings-Sub |  | 920 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-12 08:00 | 2013-06-29 17:00 |  | 2013-01-28 08:00 | 2013-02-14 17:00 | 2013-01-28 08:00 | 2013-02-14 17:00 | 2013-01-28 08:00 | 2013-02-14 17:00 | 2013-06-12 08:00 | 2013-06-29 17:00 |  | PT_Normal |  |  |  |  | S9cIukAhRyuEQ03k6r1n0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29270 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124332 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499614 | 6359 | 124334 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWARSM5290 | Gypsum False Ceiling Drawings-Sub |  | 536 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-01 08:00 | 2013-06-17 17:00 |  | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-06-01 08:00 | 2013-06-17 17:00 |  | PT_Normal |  |  |  |  | 0fuM63gDS52lpo2ImLsyoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29270 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124332 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499615 | 6359 | 124334 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWARSM5310 | Doors & window Drawings-Sub |  | 488 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-30 08:00 | 2013-06-16 17:00 |  | 2013-03-20 08:00 | 2013-04-06 17:00 | 2013-03-20 08:00 | 2013-04-06 17:00 | 2013-03-20 08:00 | 2013-04-06 17:00 | 2013-05-30 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | DBfEkCueSiOkPh+Np5lDNg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29270 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124332 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499616 | 6359 | 124334 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP2BDWARSM5320 | Carpentry & Joinery Drawings-Sub |  | 664 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-13 08:00 | 2013-07-29 17:00 |  | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-07-13 08:00 | 2013-07-29 17:00 |  | PT_Normal |  |  |  |  | WPryOFzLSASRHm8XpfZS+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29270 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124332 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499617 | 6359 | 124338 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWELSM5710 | Single Line Diagram-Sub |  | 472 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-01 08:00 | 2013-05-18 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-05-01 08:00 | 2013-05-18 17:00 |  | PT_Normal |  |  |  |  | FI0IRYJjQLuci6DT4FX/0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29470 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124337 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499618 | 6359 | 124338 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWELSM5720 | Lighting Layout Drawings-Sub |  | 472 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-07 08:00 | 2013-05-23 17:00 |  | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-05-07 08:00 | 2013-05-23 17:00 |  | PT_Normal |  |  |  |  | fP4ggIxNTomUoGgkECedZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29470 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124337 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499619 | 6359 | 124338 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWELSM5730 | Power Layout Drawings-Sub |  | 600 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-26 08:00 | 2013-06-11 17:00 |  | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-02-27 08:00 | 2013-03-16 17:00 | 2013-05-26 08:00 | 2013-06-11 17:00 |  | PT_Normal |  |  |  |  | pfZ4oV88Qf2Nz2q+ZBHx0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29470 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124337 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499620 | 6359 | 124338 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWELSM5740 | Central Alarm Monitoring System Drawings-Sub |  | 600 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-12 08:00 | 2013-06-29 17:00 |  | 2013-03-17 08:00 | 2013-04-02 17:00 | 2013-03-17 08:00 | 2013-04-02 17:00 | 2013-03-17 08:00 | 2013-04-02 17:00 | 2013-06-12 08:00 | 2013-06-29 17:00 |  | PT_Normal |  |  |  |  | QO+cWnxmTBezpJ2L6GomJA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29470 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124337 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499621 | 6359 | 124338 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWELSM5750 | Audio Video Intercom System Drawings-Sub |  | 600 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-30 08:00 | 2013-07-16 17:00 |  | 2013-04-03 08:00 | 2013-04-20 17:00 | 2013-04-03 08:00 | 2013-04-20 17:00 | 2013-04-03 08:00 | 2013-04-20 17:00 | 2013-06-30 08:00 | 2013-07-16 17:00 |  | PT_Normal |  |  |  |  | C535w4SXR4qDEFsr5JSzUw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29470 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124337 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499622 | 6359 | 124338 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWELSM5760 | Telephone & TV System Drawings-Sub |  | 600 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-17 08:00 | 2013-08-03 17:00 |  | 2013-04-21 08:00 | 2013-05-07 17:00 | 2013-04-21 08:00 | 2013-05-07 17:00 | 2013-04-21 08:00 | 2013-05-07 17:00 | 2013-07-17 08:00 | 2013-08-03 17:00 |  | PT_Normal |  |  |  |  | Bl30H9x9TxyPuQH5NBQ0lA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29470 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124337 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499623 | 6359 | 124339 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWELAP5740 | Central Alarm Monitoring System Drawings-App |  | 792 | 160 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-28 08:00 | 2013-09-03 17:00 |  | 2013-04-03 08:00 | 2013-05-07 17:00 | 2013-04-03 08:00 | 2013-05-07 17:00 | 2013-04-03 08:00 | 2013-05-07 17:00 | 2013-07-28 08:00 | 2013-09-03 17:00 |  | PT_Normal |  |  |  |  | 4PCfl7WhT3qtgHvxkYqOZg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29480 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124337 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499624 | 6359 | 124339 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWELAP5750 | Audio Video Intercom System Drawings-App |  | 720 | 160 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-04 08:00 | 2013-09-10 17:00 |  | 2013-04-21 08:00 | 2013-05-25 17:00 | 2013-04-21 08:00 | 2013-05-25 17:00 | 2013-04-21 08:00 | 2013-05-25 17:00 | 2013-08-04 08:00 | 2013-09-10 17:00 |  | PT_Normal |  |  |  |  | 7L2R+i41T8i7u0dxIVVwvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29480 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124337 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499625 | 6359 | 124339 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWELAP5760 | Telephone & TV System Drawings-App |  | 600 | 48 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-04 08:00 | 2013-09-10 17:00 |  | 2013-05-08 08:00 | 2013-06-11 17:00 | 2013-05-08 08:00 | 2013-06-11 17:00 | 2013-05-08 08:00 | 2013-06-11 17:00 | 2013-08-04 08:00 | 2013-09-10 17:00 |  | PT_Normal |  |  |  |  | wZ0f6D5BSdG4B+IkZzGwYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29480 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124337 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499626 | 6359 | 124339 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWELAP5710 | Single Line Diagram-App |  | 920 | 320 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-23 08:00 | 2013-08-29 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-07-23 08:00 | 2013-08-29 17:00 |  | PT_Normal |  |  |  |  | UAlfL8EeSSihpzbspRsVdA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29480 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124337 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499627 | 6359 | 124339 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWELAP5720 | Lighting Layout Drawings-App |  | 472 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-25 08:00 | 2013-06-27 17:00 |  | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-05-25 08:00 | 2013-06-27 17:00 |  | PT_Normal |  |  |  |  | m7emT1cfRIeX+XmwVzBWyA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29480 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124337 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499628 | 6359 | 124339 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWELAP5730 | Power Layout Drawings-App |  | 880 | 280 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-23 08:00 | 2013-08-29 17:00 |  | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-07-23 08:00 | 2013-08-29 17:00 |  | PT_Normal |  |  |  |  | HnBHdcS3Txeu1zb9+8IgBw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29480 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124337 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499629 | 6359 | 124341 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWELAP5840 | Electrical Line Layout & Details-App |  | 480 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-29 08:00 | 2013-09-04 17:00 |  | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 |  | PT_Normal |  |  |  |  | REmcl/anTxKGftlMvSRVkA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29540 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499630 | 6359 | 124341 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWSTAP5850 | Street Lighting Layout & details -App |  | 480 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-05 08:00 | 2013-10-09 17:00 |  | 2013-06-24 08:00 | 2013-07-28 17:00 | 2013-06-24 08:00 | 2013-07-28 17:00 | 2013-06-24 08:00 | 2013-07-28 17:00 | 2013-09-05 08:00 | 2013-10-09 17:00 |  | PT_Normal |  |  |  |  | SjZshSd0SWO4z5PiqO3ZlQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29540 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499631 | 6359 | 124341 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWDRAP5810 | Drainage Line Layout & Details-App |  | 504 | 296 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-15 08:00 | 2013-08-21 17:00 |  | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-07-15 08:00 | 2013-08-21 17:00 |  | PT_Normal |  |  |  |  | kScWj79tQHCIkZn7GeTS+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29540 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499632 | 6359 | 124341 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWFFAP5820 | Fire Fighting Line Layout & Details-App |  | 360 | 320 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-24 08:00 | 2013-07-28 17:00 |  | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-06-24 08:00 | 2013-07-28 17:00 |  | PT_Normal |  |  |  |  | aAVyqiJRTB6Nr6L/8pV0Ig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29540 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499633 | 6359 | 124341 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWWSAP5830 | Water Supply Line Layout & Details-App |  | 688 | 296 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-14 08:00 | 2013-09-17 17:00 |  | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-08-14 08:00 | 2013-09-17 17:00 |  | PT_Normal |  |  |  |  | 1XCAWB/EQaCiQfxFLciypg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29540 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 499634 | 6359 | 124341 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWIRAP5870 | Irrigation Layout & Details-App |  | 728 | 120 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-24 08:00 | 2013-10-30 17:00 |  | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-09-24 08:00 | 2013-10-30 17:00 |  | PT_Normal |  |  |  |  | dn730uDUQDCQNKZ/FJzyBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29540 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499635 | 6359 | 124341 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWTCAP5860 | Telecommunication Line Layout & Details-App |  | 480 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2013-11-16 17:00 |  | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-10-10 08:00 | 2013-11-16 17:00 |  | PT_Normal |  |  |  |  | PChvhmtaRVKlCUu8hO4huw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29540 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 499636 | 6359 | 124341 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWPSAP5900 | Parking Shed Layout & Details Drawings-App |  | 1200 | 184 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-12-12 08:00 | 2014-01-16 17:00 |  | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-12-12 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | 0I8ArSFURxGaVwBu9A44fA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29540 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499637 | 6359 | 124341 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWSLAP5880 | Soft & HardLandscaping Layout & Detail-App |  | 536 | 360 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-27 08:00 | 2013-09-30 17:00 |  | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-08-27 08:00 | 2013-09-30 17:00 |  | PT_Normal |  |  |  |  | ggWO+fZDRvG/guazruCeFA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29540 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499638 | 6359 | 124341 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWBWAP5890 | Boundary Wall Layout & Details-App |  | 680 | 360 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-17 08:00 | 2013-10-23 17:00 |  | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-09-17 08:00 | 2013-10-23 17:00 |  | PT_Normal |  |  |  |  | N1VbFithTOqR6i6EPuV0CA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29540 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499639 | 6359 | 124341 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWRWAP5910 | Road Layout & Details-App |  | 1192 | 184 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-12-11 08:00 | 2014-01-15 17:00 |  | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-12-11 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | 8HJNrYAoTBCNkJWuKGd4ZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29540 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499640 | 6359 | 124341 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWIWAP5920 | Irrigation Water Tank & Pump Room Details-App |  | 392 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-14 08:00 | 2013-09-17 17:00 |  | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 | 2013-08-14 08:00 | 2013-09-17 17:00 |  | PT_Normal |  |  |  |  | QnuJ6JGWSDK3KYmz5XDk6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29540 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 499641 | 6359 | 124341 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWTRAP5930 | Telephone Room Details-App |  | 480 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-14 08:00 | 2013-10-20 17:00 |  | 2013-07-02 08:00 | 2013-08-05 17:00 | 2013-07-02 08:00 | 2013-08-05 17:00 | 2013-07-02 08:00 | 2013-08-05 17:00 | 2013-09-14 08:00 | 2013-10-20 17:00 |  | PT_Normal |  |  |  |  | gOPpTVc3Ti2G2QO4zBhOUQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29540 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 499642 | 6359 | 124341 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWGZAP5940 | Gazebo Plan & Details-App |  | 480 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-21 08:00 | 2013-11-24 17:00 |  | 2013-08-06 08:00 | 2013-09-12 17:00 | 2013-08-06 08:00 | 2013-09-12 17:00 | 2013-08-06 08:00 | 2013-09-12 17:00 | 2013-10-21 08:00 | 2013-11-24 17:00 |  | PT_Normal |  |  |  |  | rIhpyPqeRgqHHcvlAyxZAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29540 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 0 | 0
%R | 499643 | 6359 | 124341 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWGHAP5950 | Guard House Plan & Details-App |  | 1360 | 1160 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2014-03-01 08:00 | 2014-04-03 17:00 |  | 2013-08-06 08:00 | 2013-09-12 17:00 | 2013-08-06 08:00 | 2013-09-12 17:00 | 2013-08-06 08:00 | 2013-09-12 17:00 | 2014-03-01 08:00 | 2014-04-03 17:00 |  | PT_Normal |  |  |  |  | 5a5TonUiRCShU8OAhfA/wA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29540 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 0 | 0
%R | 499644 | 6359 | 124342 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWELSM5840 | Electrical Line Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-07-15 17:00 |  | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-07-15 17:00 |  | PT_Normal |  |  |  |  | Yd5RWnGRRiabiTj+LVehBw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29530 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499645 | 6359 | 124342 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWSTSM5850 | Street Lighting Layout & details -Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-07-15 17:00 |  | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-07-15 17:00 |  | PT_Normal |  |  |  |  | doTP6PYVRGKZbpgf/K5DEQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29530 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499646 | 6359 | 124342 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWDRSM5810 | Drainage Line Layout & Details-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-23 17:00 |  | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-06-06 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | t/82UcnvRLqZDs44up2wSw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29530 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499647 | 6359 | 124342 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWFFSM5820 | Fire Fighting Line Layout & Details-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-23 17:00 |  | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-06-06 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | 7sEhs5ZxQfuCu1RW2VnddQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29530 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499648 | 6359 | 124342 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWWSSM5830 | Water Supply Line Layout & Details-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-23 17:00 |  | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-06-06 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | JVauB5JHT5SPVGJ/HN6fMg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29530 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499649 | 6359 | 124342 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWIRSM5870 | Irrigation Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-16 08:00 | 2013-08-01 17:00 |  | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-07-16 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | EjmgPTNTSmKCQ7mjDmF/KA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29530 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499650 | 6359 | 124342 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWTCSM5860 | Telecommunication Line Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-07-15 17:00 |  | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-07-15 17:00 |  | PT_Normal |  |  |  |  | Dgi4Z55wSyGSJ0l0q57zvA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29530 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499651 | 6359 | 124342 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWPSSM5900 | Parking Shed Layout & Details Drawings-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-24 08:00 | 2013-08-13 17:00 |  | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-07-24 08:00 | 2013-08-13 17:00 |  | PT_Normal |  |  |  |  | M8sjJVM2QzGSJccr2cuizQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29530 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499652 | 6359 | 124342 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWSLSM5880 | Soft & HardLandscaping Layout & Detail-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-16 08:00 | 2013-08-01 17:00 |  | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-07-16 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | j4sPh7DDSzuwDpRHh0qRxg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29530 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499653 | 6359 | 124342 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWBWSM5890 | Boundary Wall Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-16 08:00 | 2013-08-01 17:00 |  | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-07-16 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | ilfHnjJtQjGtFWtWPYN1Rg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29530 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499654 | 6359 | 124342 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWRWSM5910 | Road Layout & Details-Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-24 08:00 | 2013-08-13 17:00 |  | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-07-24 08:00 | 2013-08-13 17:00 |  | PT_Normal |  |  |  |  | jxkW+fCzSsaAH1Sf3hky5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29530 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499655 | 6359 | 124342 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWIWSM5920 | Irrigation Water Tank & Pump Room Details- Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-24 08:00 | 2013-08-13 17:00 |  | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-05-28 08:00 | 2013-06-13 17:00 | 2013-07-24 08:00 | 2013-08-13 17:00 |  | PT_Normal |  |  |  |  | HczDrW2mTEmmKEJE5hvt4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29530 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 499656 | 6359 | 124342 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWTRSM5930 | Telephone Room Details-Sub |  | 480 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-08-27 08:00 | 2013-09-12 17:00 |  | 2013-06-15 08:00 | 2013-07-01 17:00 | 2013-06-15 08:00 | 2013-07-01 17:00 | 2013-06-15 08:00 | 2013-07-01 17:00 | 2013-08-27 08:00 | 2013-09-12 17:00 |  | PT_Normal |  |  |  |  | hjyXM46ySvqmCL11nAr+mg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29530 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 30 | 0
%R | 499657 | 6359 | 124342 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWGZSM5940 | Gazebo Plan & Details-Sub |  | 600 | 120 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-10-01 08:00 | 2013-10-20 17:00 |  | 2013-07-02 08:00 | 2013-07-18 17:00 | 2013-07-02 08:00 | 2013-07-18 17:00 | 2013-07-02 08:00 | 2013-07-18 17:00 | 2013-10-01 08:00 | 2013-10-20 17:00 |  | PT_Normal |  |  |  |  | DjY9JrphTNaQd3+/bKLJVw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29530 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 30 | 0
%R | 499658 | 6359 | 124342 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGI03DWGHSM5950 | Guard House Plan & Details-Sub |  | 1480 | 120 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-10 08:00 | 2014-02-27 17:00 |  | 2013-07-02 08:00 | 2013-07-18 17:00 | 2013-07-02 08:00 | 2013-07-18 17:00 | 2013-07-02 08:00 | 2013-07-18 17:00 | 2014-02-10 08:00 | 2014-02-27 17:00 |  | PT_Normal |  |  |  |  | X4h3P389RRit4tvQ2nHndA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29530 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124340 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 30 | 0
%R | 499659 | 6359 | 124344 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWMEAP5770 | Plumbing Layout & Details Drawings-App |  | 424 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-12 08:00 | 2013-06-15 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-05-12 08:00 | 2013-06-15 17:00 |  | PT_Normal |  |  |  |  | /aJiALenTC2uSo2ykCbxsg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29510 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499660 | 6359 | 124344 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWMEAP5780 | Drainage Layout & Details Drawings-App |  | 424 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-12 08:00 | 2013-06-15 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-05-12 08:00 | 2013-06-15 17:00 |  | PT_Normal |  |  |  |  | hCEfeAEcSgmBMwcL36aS4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29510 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499661 | 6359 | 124344 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWMEAP5790 | Fire Fighting Layout & Details Drawings-App |  | 1160 | 440 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-17 08:00 | 2013-10-23 17:00 |  | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-09-17 08:00 | 2013-10-23 17:00 |  | PT_Normal |  |  |  |  | 8LPQxdUaQOSINyUM2PJNkw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29510 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499662 | 6359 | 124344 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWMEAP5800 | AC Layout & Details Drawings-App |  | 512 | 80 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-08-01 17:00 |  | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-06-29 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | dW/mLzjESGOlJgaafRv66Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29510 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499663 | 6359 | 124345 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWMESM5770 | Plumbing Layout & Details Drawings-Sub |  | 424 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-24 08:00 | 2013-05-11 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-04-24 08:00 | 2013-05-11 17:00 |  | PT_Normal |  |  |  |  | h6R0imndQemwWDOSn2UbOw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29500 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499664 | 6359 | 124345 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWMESM5780 | Drainage Layout & Details Drawings-Sub |  | 360 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-15 08:00 | 2013-05-01 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 |  | PT_Normal |  |  |  |  | talGRau0SVWZQ+4v8m25ig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29500 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 20 | 0
%R | 499665 | 6359 | 124345 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWMESM5790 | Fire Fighting Layout & Details Drawings-Sub |  | 360 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-02 08:00 | 2013-05-19 17:00 |  | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 |  | PT_Normal |  |  |  |  | YPOw/lASSu2Tz5AVvvXq4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29500 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499666 | 6359 | 124345 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWMESM5800 | AC Layout & Details Drawings-Sub |  | 360 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-20 08:00 | 2013-06-05 17:00 |  | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 |  | PT_Normal |  |  |  |  | rckJtdQzRsSykMTTp1YuwQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29500 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 499667 | 6359 | 124347 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARAP5610 | Ground Floor Plan-App |  | 720 | 64 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-04 08:00 | 2013-07-08 17:00 |  | 2013-02-19 08:00 | 2013-03-25 17:00 | 2013-02-19 08:00 | 2013-03-25 17:00 | 2013-02-19 08:00 | 2013-03-25 17:00 | 2013-06-04 08:00 | 2013-07-08 17:00 |  | PT_Normal |  |  |  |  | PCw6PIaSSI6lbpG21vAGHQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29450 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499668 | 6359 | 124347 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARAP5620 | First Floor Plan-App |  | 496 | 48 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-13 08:00 | 2013-06-16 17:00 |  | 2013-03-02 08:00 | 2013-04-04 17:00 | 2013-03-02 08:00 | 2013-04-04 17:00 | 2013-03-02 08:00 | 2013-04-04 17:00 | 2013-05-13 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | ZHoTaE13TU6G7xzIT5RxPA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29450 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499669 | 6359 | 124347 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARAP5630 | Roof Floor Plan-App |  | 440 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-13 08:00 | 2013-06-16 17:00 |  | 2013-03-10 08:00 | 2013-04-13 17:00 | 2013-03-10 08:00 | 2013-04-13 17:00 | 2013-03-10 08:00 | 2013-04-13 17:00 | 2013-05-13 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | zI5zl9P0Q2W59AddXXUWzA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29450 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499670 | 6359 | 124347 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARAP5640 | Ceramic Flooring & Wall Drawings-App |  | 384 | 48 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-14 08:00 | 2013-06-17 17:00 |  | 2013-03-19 08:00 | 2013-04-22 17:00 | 2013-03-19 08:00 | 2013-04-22 17:00 | 2013-03-19 08:00 | 2013-04-22 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 |  | PT_Normal |  |  |  |  | o4gqkeQSThCq0ZYw+0n2tA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29450 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499671 | 6359 | 124347 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARAP5650 | Porcelain Floor Drawings-App |  | 456 | 48 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-25 08:00 | 2013-06-27 17:00 |  | 2013-03-19 08:00 | 2013-04-22 17:00 | 2013-03-19 08:00 | 2013-04-22 17:00 | 2013-03-19 08:00 | 2013-04-22 17:00 | 2013-05-25 08:00 | 2013-06-27 17:00 |  | PT_Normal |  |  |  |  | hKTGhKx2RGOtjw4MBWQ7JA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29450 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499672 | 6359 | 124347 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARAP5660 | Cobble & Slate Flooring Drawings-App |  | 704 | 48 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-30 08:00 | 2013-08-03 17:00 |  | 2013-03-19 08:00 | 2013-04-22 17:00 | 2013-03-19 08:00 | 2013-04-22 17:00 | 2013-03-19 08:00 | 2013-04-22 17:00 | 2013-06-30 08:00 | 2013-08-03 17:00 |  | PT_Normal |  |  |  |  | M40nBK6VTDyw8UgTVQFU7g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29450 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499673 | 6359 | 124347 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARAP5670 | Gypsum False Ceiling Drawings-App |  | 536 | 280 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-18 08:00 | 2013-07-22 17:00 |  | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-06-18 08:00 | 2013-07-22 17:00 |  | PT_Normal |  |  |  |  | jxOSRDlZTFCU1CJ2P245SQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29450 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499674 | 6359 | 124347 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARAP5680 | Aluminum False Ceiling Drawings-App |  | 656 | 320 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-06 08:00 | 2013-08-08 17:00 |  | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-07-06 08:00 | 2013-08-08 17:00 |  | PT_Normal |  |  |  |  | 4hTqMOMwQY+cSG9/0av2Cw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29450 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499675 | 6359 | 124347 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARAP5690 | Doors & Window Drawings-App |  | 440 | 232 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-17 08:00 | 2013-07-21 17:00 |  | 2013-04-14 08:00 | 2013-05-18 17:00 | 2013-04-14 08:00 | 2013-05-18 17:00 | 2013-04-14 08:00 | 2013-05-18 17:00 | 2013-06-17 08:00 | 2013-07-21 17:00 |  | PT_Normal |  |  |  |  | zTdvq/PgRSG4qWqVY/RzmA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29450 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499676 | 6359 | 124347 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARAP5700 | Carpentry & Joinery Drawings-App |  | 664 | 320 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-30 08:00 | 2013-09-05 17:00 |  | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-07-30 08:00 | 2013-09-05 17:00 |  | PT_Normal |  |  |  |  | Dpbiuh45TtO2WwGSK4R/RA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29450 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499677 | 6359 | 124348 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARSM5610 | Ground Floor Plan-Sub |  | 384 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-03-30 08:00 | 2013-04-15 17:00 |  | 2013-01-31 08:00 | 2013-02-18 17:00 | 2013-01-31 08:00 | 2013-02-18 17:00 | 2013-01-31 08:00 | 2013-02-18 17:00 | 2013-03-30 08:00 | 2013-04-15 17:00 |  | PT_Normal |  |  |  |  | TexPCWFUSGmNWgVQ42O0Cw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29440 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499678 | 6359 | 124348 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARSM5620 | First Floor Plan-Sub |  | 384 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-09 08:00 | 2013-04-25 17:00 |  | 2013-02-11 08:00 | 2013-02-28 17:00 | 2013-02-11 08:00 | 2013-02-28 17:00 | 2013-02-11 08:00 | 2013-02-28 17:00 | 2013-04-09 08:00 | 2013-04-25 17:00 |  | PT_Normal |  |  |  |  | FBnCtwzTSsODeVEwJMAnQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29440 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 30 | 0
%R | 499679 | 6359 | 124348 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARSM5630 | Roof Floor Plan-Sub |  | 424 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-23 08:00 | 2013-05-09 17:00 |  | 2013-02-20 08:00 | 2013-03-09 17:00 | 2013-02-20 08:00 | 2013-03-09 17:00 | 2013-02-20 08:00 | 2013-03-09 17:00 | 2013-04-23 08:00 | 2013-05-09 17:00 |  | PT_Normal |  |  |  |  | U+8mNnk/T8WuZrqmw6+UIw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29440 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 30 | 0
%R | 499680 | 6359 | 124348 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARSM5640 | Ceramic Flooring & Wall Drawings-Sub |  | 384 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-27 08:00 | 2013-05-13 17:00 |  | 2013-03-02 08:00 | 2013-03-18 17:00 | 2013-03-02 08:00 | 2013-03-18 17:00 | 2013-03-02 08:00 | 2013-03-18 17:00 | 2013-04-27 08:00 | 2013-05-13 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29440 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499681 | 6359 | 124348 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARSM5650 | Porcelain Floor Drawings-Sub |  | 456 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-07 08:00 | 2013-05-23 17:00 |  | 2013-03-02 08:00 | 2013-03-18 17:00 | 2013-03-02 08:00 | 2013-03-18 17:00 | 2013-03-02 08:00 | 2013-03-18 17:00 | 2013-05-07 08:00 | 2013-05-23 17:00 |  | PT_Normal |  |  |  |  | zAErE6zESA2TglDh9HqS9Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29440 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499682 | 6359 | 124348 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARSM5660 | Cobble & Slate Flooring Drawings-Sub |  | 704 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-12 08:00 | 2013-06-29 17:00 |  | 2013-03-02 08:00 | 2013-03-18 17:00 | 2013-03-02 08:00 | 2013-03-18 17:00 | 2013-03-02 08:00 | 2013-03-18 17:00 | 2013-06-12 08:00 | 2013-06-29 17:00 |  | PT_Normal |  |  |  |  | 9gRXSGWzQpSoNZ2ZKiadnw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29440 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499683 | 6359 | 124348 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARSM5670 | Gypsum False Ceiling Drawings-Sub |  | 536 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-01 08:00 | 2013-06-17 17:00 |  | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-06-01 08:00 | 2013-06-17 17:00 |  | PT_Normal |  |  |  |  | taSVXtkiSlyzTyRpSA1kpA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29440 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499684 | 6359 | 124348 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARSM5680 | Aluminum False Ceiling Drawings-Sub |  | 656 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-18 08:00 | 2013-07-04 17:00 |  | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-06-18 08:00 | 2013-07-04 17:00 |  | PT_Normal |  |  |  |  | aBCpHTZ2T1ae6Qw5lZXmkA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29440 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499685 | 6359 | 124348 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARSM5690 | Doors & window Drawings-Sub |  | 488 | 48 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-30 08:00 | 2013-06-16 17:00 |  | 2013-03-20 08:00 | 2013-04-06 17:00 | 2013-03-20 08:00 | 2013-04-06 17:00 | 2013-03-20 08:00 | 2013-04-06 17:00 | 2013-05-30 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | S0BEYEuTQy2nPG0r5IllvQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29440 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 499686 | 6359 | 124348 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWARSM5700 | Carpentry & Joinery Drawings-Sub |  | 664 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-13 08:00 | 2013-07-29 17:00 |  | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-07-13 08:00 | 2013-07-29 17:00 |  | PT_Normal |  |  |  |  | kJAmMPeJR/Cetsv1ar3mLQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29440 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124346 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499687 | 6359 | 124350 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWSTAP5560 | Footing Drawings-App |  | 256 | 256 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 |  |  |  | 2013-01-20 08:00 | 2013-02-18 17:00 |  | 2012-12-12 08:00 | 2013-01-10 17:00 | 2012-12-12 08:00 | 2013-01-10 17:00 | 2012-12-12 08:00 | 2013-01-10 17:00 | 2013-01-20 08:00 | 2013-02-18 17:00 |  | PT_Normal |  |  |  |  | bBwiuEhgR0Gmbl1ZtFu91A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29420 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124349 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499688 | 6359 | 124350 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWSTAP5570 | Grade Beam & Slab Drawings-App |  | 544 | 544 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-03-17 08:00 | 2013-04-20 17:00 |  | 2012-12-26 08:00 | 2013-01-29 17:00 | 2012-12-26 08:00 | 2013-01-29 17:00 | 2012-12-26 08:00 | 2013-01-29 17:00 | 2013-03-17 08:00 | 2013-04-20 17:00 |  | PT_Normal |  |  |  |  | jrYb+hS+SQS0LaK+7eBAeA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29420 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124349 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499689 | 6359 | 124350 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWSTAP5580 | Column Drawings-App |  | 792 | 792 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-29 08:00 | 2013-06-02 17:00 |  | 2013-01-02 08:00 | 2013-02-05 17:00 | 2013-01-02 08:00 | 2013-02-05 17:00 | 2013-01-02 08:00 | 2013-02-05 17:00 | 2013-04-29 08:00 | 2013-06-02 17:00 |  | PT_Normal |  |  |  |  | fLlZdKyOTRi+SMUoQc+36g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29420 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124349 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499690 | 6359 | 124350 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWSTAP5590 | GF Beams & Slabs Drawings-App |  | 880 | 880 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-23 08:00 | 2013-06-26 17:00 |  | 2013-01-14 08:00 | 2013-02-18 17:00 | 2013-01-14 08:00 | 2013-02-18 17:00 | 2013-01-14 08:00 | 2013-02-18 17:00 | 2013-05-23 08:00 | 2013-06-26 17:00 |  | PT_Normal |  |  |  |  | re8tJnjdTryfJM2zZcFMIA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29420 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124349 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499691 | 6359 | 124350 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWSTAP5600 | FF Beams & Slabs Drawings-App |  | 880 | 880 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-10 08:00 | 2013-07-14 17:00 |  | 2013-01-31 08:00 | 2013-03-07 17:00 | 2013-01-31 08:00 | 2013-03-07 17:00 | 2013-01-31 08:00 | 2013-03-07 17:00 | 2013-06-10 08:00 | 2013-07-14 17:00 |  | PT_Normal |  |  |  |  | CuW+VTnORIuSkR1CaqGQ5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29420 | N | N | G20 | APPROVAL OF DRAWINGS |  | 124349 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP03 |  | 0 | 0
%R | 499692 | 6359 | 124351 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWSTSM5600 | FF Beams & Slabs Drawings-Sub |  | 384 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-03-12 08:00 | 2013-03-28 17:00 |  | 2013-01-14 08:00 | 2013-01-30 17:00 | 2013-01-14 08:00 | 2013-01-30 17:00 | 2013-01-14 08:00 | 2013-01-30 17:00 | 2013-03-12 08:00 | 2013-03-28 17:00 |  | PT_Normal |  |  |  |  | mYMtuSYaSw2gftektTgjCw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29410 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124349 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499693 | 6359 | 124351 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWSTSM5560 | Footing Drawings-Sub |  | 256 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-01-08 08:00 | 2013-01-19 17:00 |  | 2012-12-01 08:00 | 2012-12-11 17:00 | 2012-12-01 08:00 | 2012-12-11 17:00 | 2012-12-01 08:00 | 2012-12-11 17:00 | 2013-01-08 08:00 | 2013-01-19 17:00 |  | PT_Normal |  |  |  |  | retbBcIQTTqwhOxXyoij3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29410 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124349 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 20 | 0
%R | 499694 | 6359 | 124351 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWSTSM5570 | Grade Beam & Slab Drawings-Sub |  | 384 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-02-03 08:00 | 2013-02-20 17:00 |  | 2012-12-08 08:00 | 2012-12-25 17:00 | 2012-12-08 08:00 | 2012-12-25 17:00 | 2012-12-08 08:00 | 2012-12-25 17:00 | 2013-02-03 08:00 | 2013-02-20 17:00 |  | PT_Normal |  |  |  |  | ONGt3kCPSvOA6XVldi9fMw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29410 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124349 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499695 | 6359 | 124351 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWSTSM5580 | Column Drawings-Sub |  | 384 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-02-10 08:00 | 2013-02-27 17:00 |  | 2012-12-15 08:00 | 2013-01-01 17:00 | 2012-12-15 08:00 | 2013-01-01 17:00 | 2012-12-15 08:00 | 2013-01-01 17:00 | 2013-02-10 08:00 | 2013-02-27 17:00 |  | PT_Normal |  |  |  |  | mqbV0OO8QUOp1xPf2a5rmw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29410 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124349 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499696 | 6359 | 124351 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHENGP03DWSTSM5590 | GF Beams & Slabs Drawings-Sub |  | 384 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-02-23 08:00 | 2013-03-11 17:00 |  | 2012-12-27 08:00 | 2013-01-13 17:00 | 2012-12-27 08:00 | 2013-01-13 17:00 | 2012-12-27 08:00 | 2013-01-13 17:00 | 2013-02-23 08:00 | 2013-03-11 17:00 |  | PT_Normal |  |  |  |  | XkBH0MsGQgesYX6Dn6KM4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29410 | N | N | G10 | SUBMISSION OF DRAWINGS |  | 124349 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499697 | 6359 | 124354 | 13662 | 0 | N | N | N | CP_Drtn | TT_Mile | DT_FixedDUR2 | TK_NotStart | DUKHMOBP2APS00002140 | Receiving of Site Instruction |  | 704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-03-11 08:00 | 2013-03-11 08:00 |  | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2013-03-11 08:00 | 2013-03-11 08:00 |  | PT_Normal |  |  |  |  | Tn3q5BGORyiDLQBRdDBQsQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28420 | N | N | 25 | PACKAGE 2A - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499698 | 6359 | 124354 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP2APS00002145 | Finalization of Subcontractor |  | 944 | 0 | 168 | 0 | 0 | 0 | 168 | 0 | 0 | 0 |  |  |  | 2013-04-15 08:00 | 2013-05-08 17:00 |  | 2012-11-26 08:00 | 2012-12-20 17:00 | 2012-11-26 08:00 | 2012-12-20 17:00 | 2012-11-26 08:00 | 2012-12-20 17:00 | 2013-04-15 08:00 | 2013-05-08 17:00 |  | PT_Normal |  |  |  |  | DCjNjJcZQBSN4sCv7z5RNQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28420 | N | N | 25 | PACKAGE 2A - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499699 | 6359 | 124354 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP2APS00002150 | Submission of Cost Proposal |  | 944 | 0 | 56 | 0 | 0 | 0 | 56 | 0 | 0 | 0 |  |  |  | 2013-05-09 08:00 | 2013-05-16 17:00 |  | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 | 2013-05-09 08:00 | 2013-05-16 17:00 |  | PT_Normal |  |  |  |  | L/dlAWyYQBK4OJBUOqBYxg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28420 | N | N | 25 | PACKAGE 2A - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499700 | 6359 | 124354 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP2APS00002155 | Approval of Cost Proposal |  | 944 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-18 08:00 | 2013-06-20 17:00 |  | 2012-12-30 08:00 | 2013-02-02 17:00 | 2012-12-30 08:00 | 2013-02-02 17:00 | 2012-12-30 08:00 | 2013-02-02 17:00 | 2013-05-18 08:00 | 2013-06-20 17:00 |  | PT_Normal |  |  |  |  | zLhiqYAiSjuJaxyEaSeyrQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28420 | N | N | 25 | PACKAGE 2A - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499701 | 6359 | 124354 | 13662 | 0 | N | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | DUKHMOBP2APS00002160 | Receiving of Variation Order |  | 944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-06-20 17:00 | 2013-06-20 17:00 |  | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-06-20 17:00 | 2013-06-20 17:00 |  | PT_Normal |  |  |  |  | NCz/r29HThKoMhqALHYInA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28420 | N | N | 25 | PACKAGE 2A - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 0 | 0
%R | 499702 | 6359 | 124354 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP2APS00002165 | Engineering & Procurement |  | 944 | 584 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-06-22 08:00 | 2013-11-13 17:00 |  | 2013-02-03 08:00 | 2013-06-23 17:00 | 2013-02-03 08:00 | 2013-06-23 17:00 | 2013-02-03 08:00 | 2013-06-23 17:00 | 2013-06-22 08:00 | 2013-11-13 17:00 |  | PT_Normal |  |  |  |  | KJr7VMb5R5SAApUkFQiLig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28420 | N | N | 25 | PACKAGE 2A - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03; period 3: 2013-AP04; period 4: 2013-AP05; period 5: 2013-AP06 |  | 0 | 0
%R | 499703 | 6359 | 124354 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP2APS00002170 | Commencement of Construction Work |  | 360 | 88 | 1440 | 0 | 0 | 0 | 1440 | 0 | 0 | 0 |  |  |  | 2013-11-14 08:00 | 2014-06-14 17:00 |  | 2013-09-21 08:00 | 2014-04-22 17:00 | 2013-09-21 08:00 | 2014-04-22 17:00 | 2013-09-21 08:00 | 2014-04-22 17:00 | 2013-11-14 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | 7YG5VdG4RJix0Lg5vbTrFg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28420 | N | N | 25 | PACKAGE 2A - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | 2013-AP09 | 2013-AP10 | 2013-AP11 | 2013-AP12 | 2014-AP01 | 2014-AP02 | 2014-AP03 | 2014-AP04 |  |  | 0 | 0
%R | 499704 | 6359 | 124355 | 13662 | 0 | N | N | N | CP_Drtn | TT_Mile | DT_FixedDUR2 | TK_NotStart | DUKHMOBP1BPS00002070 | Receiving of Site Instruction |  | 584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-02-21 08:00 | 2013-02-21 08:00 |  | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2013-02-21 08:00 | 2013-02-21 08:00 |  | PT_Normal |  |  |  |  | SkmogfopTdSUeyVA4vXsAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28400 | N | N | 15 | PACKAGE 1B - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499705 | 6359 | 124355 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP1BPS00002075 | Finalization of Subcontractor |  | 640 | 0 | 168 | 0 | 0 | 0 | 168 | 0 | 0 | 0 |  |  |  | 2013-03-02 08:00 | 2013-03-25 17:00 |  | 2012-11-26 08:00 | 2012-12-20 17:00 | 2012-11-26 08:00 | 2012-12-20 17:00 | 2012-11-26 08:00 | 2012-12-20 17:00 | 2013-03-02 08:00 | 2013-03-25 17:00 |  | PT_Normal |  |  |  |  | Cr0b5UeHQTew8OvXplNLYw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28400 | N | N | 15 | PACKAGE 1B - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499706 | 6359 | 124355 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP1BPS00002080 | Submission of Cost Proposal |  | 640 | 0 | 56 | 0 | 0 | 0 | 56 | 0 | 0 | 0 |  |  |  | 2013-03-26 08:00 | 2013-04-02 17:00 |  | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 | 2013-03-26 08:00 | 2013-04-02 17:00 |  | PT_Normal |  |  |  |  | MDCk3v7qQYmsG3GSm2BGEw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28400 | N | N | 15 | PACKAGE 1B - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499707 | 6359 | 124355 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP1BPS00002085 | Approval of Cost Proposal |  | 640 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-03 08:00 | 2013-05-07 17:00 |  | 2012-12-30 08:00 | 2013-02-02 17:00 | 2012-12-30 08:00 | 2013-02-02 17:00 | 2012-12-30 08:00 | 2013-02-02 17:00 | 2013-04-03 08:00 | 2013-05-07 17:00 |  | PT_Normal |  |  |  |  | 0QUyTZ9XT4+vulAqxuUcyQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28400 | N | N | 15 | PACKAGE 1B - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499708 | 6359 | 124355 | 13662 | 0 | N | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | DUKHMOBP1BPS00002090 | Receiving of Variation Order |  | 640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-05-07 17:00 | 2013-05-07 17:00 |  | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-05-07 17:00 | 2013-05-07 17:00 |  | PT_Normal |  |  |  |  | RgYwbcyKSfqC/LM5JCMRnw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28400 | N | N | 15 | PACKAGE 1B - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 0 | 0
%R | 499709 | 6359 | 124355 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP1BPS00002095 | Engineering & Procurement |  | 640 | 472 | 1680 | 0 | 0 | 0 | 1680 | 0 | 0 | 0 |  |  |  | 2013-05-08 08:00 | 2014-01-14 17:00 |  | 2013-02-03 08:00 | 2013-10-09 17:00 | 2013-02-03 08:00 | 2013-10-09 17:00 | 2013-02-03 08:00 | 2013-10-09 17:00 | 2013-05-08 08:00 | 2014-01-14 17:00 |  | PT_Normal |  |  |  |  | eUDuAMD+SlaK/D0LP2FqJw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28400 | N | N | 15 | PACKAGE 1B - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | 2013-AP02 | 2013-AP03 | 2013-AP04 | 2013-AP05 | 2013-AP06 | 2013-AP07 | 2013-AP08 | 2013-AP09 | 2013-AP10 |  | 0 | 0
%R | 499710 | 6359 | 124355 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP1BPS00002100 | Commencement of Construction Work |  | 168 | 144 | 2240 | 0 | 0 | 0 | 2240 | 0 | 0 | 0 |  |  |  | 2014-01-15 08:00 | 2014-12-14 17:00 |  | 2013-12-22 08:00 | 2014-11-19 17:00 | 2013-12-22 08:00 | 2014-11-19 17:00 | 2013-12-22 08:00 | 2014-11-19 17:00 | 2014-01-15 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | QLwMscttQbuZgVGHEYhKbA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28400 | N | N | 15 | PACKAGE 1B - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: #VALUE! |  | 0 | 0
%R | 499711 | 6359 | 124356 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP03PS00002295 | Approval of Cost Proposal |  | 784 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-24 08:00 | 2013-05-28 17:00 |  | 2012-12-30 08:00 | 2013-02-02 17:00 | 2012-12-30 08:00 | 2013-02-02 17:00 | 2012-12-30 08:00 | 2013-02-02 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 |  | PT_Normal |  |  |  |  | WfsoKsroQROLi7S6OO/25Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28460 | N | N | 45 | PACKAGE 3 - APARTMENT |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499712 | 6359 | 124356 | 13662 | 0 | N | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | DUKHMOBP03PS00002300 | Receiving of Variation Order |  | 784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-05-28 17:00 | 2013-05-28 17:00 |  | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-05-28 17:00 | 2013-05-28 17:00 |  | PT_Normal |  |  |  |  | y/KScyISRyeRWSwNPMPC0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28460 | N | N | 45 | PACKAGE 3 - APARTMENT |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 0 | 0
%R | 499713 | 6359 | 124356 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP03PS00002305 | Engineering & Procurement |  | 784 | 760 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 |  |  |  | 2013-05-29 08:00 | 2013-11-25 17:00 |  | 2013-02-03 08:00 | 2013-07-28 17:00 | 2013-02-03 08:00 | 2013-07-28 17:00 | 2013-02-03 08:00 | 2013-07-28 17:00 | 2013-05-29 08:00 | 2013-11-25 17:00 |  | PT_Normal |  |  |  |  | ZdaFAZzUQRGnjUiHen8LTw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28460 | N | N | 45 | PACKAGE 3 - APARTMENT |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | 2013-AP02 | 2013-AP03 | 2013-AP04 | 2013-AP05 | 2013-AP06 | 2013-AP07 |  |  |  |  | 0 | 0
%R | 499714 | 6359 | 124356 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP03PS00002310 | Commencement of Construction Work |  | 24 | 24 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-11-26 08:00 | 2014-04-16 17:00 |  | 2013-11-23 08:00 | 2014-04-13 17:00 | 2013-11-23 08:00 | 2014-04-13 17:00 | 2013-11-23 08:00 | 2014-04-13 17:00 | 2013-11-26 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | DN9YTHH4SZ+94aXkK9+HIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28460 | N | N | 45 | PACKAGE 3 - APARTMENT |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11; period 2: 2013-AP12; period 3: 2014-AP01; period 4: 2014-AP02; period 5: 2014-AP03 |  | 0 | 0
%R | 499715 | 6359 | 124356 | 13662 | 0 | N | N | N | CP_Drtn | TT_Mile | DT_FixedDUR2 | TK_NotStart | DUKHMOBP03PS00002280 | Receiving of Site Instruction |  | 312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-01-12 08:00 | 2013-01-12 08:00 |  | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2013-01-12 08:00 | 2013-01-12 08:00 |  | PT_Normal |  |  |  |  | 5W/3LfFhSr2ZQmFa6wcU2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28460 | N | N | 45 | PACKAGE 3 - APARTMENT |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499716 | 6359 | 124356 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP03PS00002285 | Finalization of Subcontractor |  | 784 | 0 | 168 | 0 | 0 | 0 | 168 | 0 | 0 | 0 |  |  |  | 2013-03-23 08:00 | 2013-04-15 17:00 |  | 2012-11-26 08:00 | 2012-12-20 17:00 | 2012-11-26 08:00 | 2012-12-20 17:00 | 2012-11-26 08:00 | 2012-12-20 17:00 | 2013-03-23 08:00 | 2013-04-15 17:00 |  | PT_Normal |  |  |  |  | ePsrU9DVSMiIM7DjzTzETQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28460 | N | N | 45 | PACKAGE 3 - APARTMENT |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499717 | 6359 | 124356 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP03PS00002290 | Submission of Cost Proposal |  | 784 | 0 | 56 | 0 | 0 | 0 | 56 | 0 | 0 | 0 |  |  |  | 2013-04-16 08:00 | 2013-04-23 17:00 |  | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 | 2013-04-16 08:00 | 2013-04-23 17:00 |  | PT_Normal |  |  |  |  | Z2Yr++meR/GgayYojTYqmA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28460 | N | N | 45 | PACKAGE 3 - APARTMENT |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499718 | 6359 | 124357 | 13662 | 0 | N | N | N | CP_Drtn | TT_Mile | DT_FixedDUR2 | TK_NotStart | DUKHMOBI2BPS00002245 | Receiving of Site Instruction |  | 384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-01-22 08:00 | 2013-01-22 08:00 |  | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2013-01-22 08:00 | 2013-01-22 08:00 |  | PT_Normal |  |  |  |  | f4hggcWTRvuPmF4PXkqg5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28450 | N | N | 40 | PACKAGE 2B - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499719 | 6359 | 124357 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI2BPS00002250 | Finalization of Subcontractor |  | 384 | 0 | 168 | 0 | 0 | 0 | 168 | 0 | 0 | 0 |  |  |  | 2013-01-22 08:00 | 2013-02-16 17:00 |  | 2012-11-26 08:00 | 2012-12-20 17:00 | 2012-11-26 08:00 | 2012-12-20 17:00 | 2012-11-26 08:00 | 2012-12-20 17:00 | 2013-01-22 08:00 | 2013-02-16 17:00 |  | PT_Normal |  |  |  |  | 4bCKBxYuTjaazy8aiU8GXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28450 | N | N | 40 | PACKAGE 2B - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499720 | 6359 | 124357 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI2BPS00002255 | Submission of Cost Proposal |  | 384 | 0 | 56 | 0 | 0 | 0 | 56 | 0 | 0 | 0 |  |  |  | 2013-02-17 08:00 | 2013-02-24 17:00 |  | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 | 2013-02-17 08:00 | 2013-02-24 17:00 |  | PT_Normal |  |  |  |  | JUsJu/i1SWCmZzhtYON5KQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28450 | N | N | 40 | PACKAGE 2B - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499721 | 6359 | 124357 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI2BPS00002260 | Approval of Cost Proposal |  | 384 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-02-25 08:00 | 2013-03-31 17:00 |  | 2012-12-30 08:00 | 2013-02-02 17:00 | 2012-12-30 08:00 | 2013-02-02 17:00 | 2012-12-30 08:00 | 2013-02-02 17:00 | 2013-02-25 08:00 | 2013-03-31 17:00 |  | PT_Normal |  |  |  |  | q/WwNJOcSHia+BbgcsAXRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28450 | N | N | 40 | PACKAGE 2B - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499722 | 6359 | 124357 | 13662 | 0 | N | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | DUKHMOBI2BPS00002265 | Receiving of Variation Order |  | 384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-03-31 17:00 | 2013-03-31 17:00 |  | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-03-31 17:00 | 2013-03-31 17:00 |  | PT_Normal |  |  |  |  | XHDGe1GMQjmiYI8sj6nNbQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28450 | N | N | 40 | PACKAGE 2B - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 0 | 0
%R | 499723 | 6359 | 124357 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI2BPS00002270 | Engineering & Procurement |  | 384 | 96 | 1120 | 0 | 0 | 0 | 1120 | 0 | 0 | 0 |  |  |  | 2013-04-01 08:00 | 2013-09-14 17:00 |  | 2013-02-03 08:00 | 2013-07-16 17:00 | 2013-02-03 08:00 | 2013-07-16 17:00 | 2013-02-03 08:00 | 2013-07-16 17:00 | 2013-04-01 08:00 | 2013-09-14 17:00 |  | PT_Normal |  |  |  |  | XOQGjwr+SdyNNmaJRZkKLQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28450 | N | N | 40 | PACKAGE 2B - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | 2013-AP02 | 2013-AP03 | 2013-AP04 | 2013-AP05 | 2013-AP06 | 2013-AP07 |  |  |  |  | 0 | 0
%R | 499724 | 6359 | 124357 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI2BPS00002275 | Commencement of Construction Work |  | 288 | 288 | 1840 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 |  |  |  | 2013-09-15 08:00 | 2014-06-14 17:00 |  | 2013-07-31 08:00 | 2014-05-03 17:00 | 2013-07-31 08:00 | 2014-05-03 17:00 | 2013-07-31 08:00 | 2014-05-03 17:00 | 2013-09-15 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | La9VGSNoQ2q0c2oX6R3YVQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28450 | N | N | 40 | PACKAGE 2B - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | 2013-AP07 | 2013-AP08 | 2013-AP09 | 2013-AP10 | 2013-AP11 | 2013-AP12 | 2014-AP01 | 2014-AP02 | 2014-AP03 | 2014-AP04 | 0 | 0
%R | 499725 | 6359 | 124358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Mile | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1APS00002035 | Receiving of Site Instruction |  | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-01-20 08:00 | 2013-01-20 08:00 |  | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2013-01-20 08:00 | 2013-01-20 08:00 |  | PT_Normal |  |  |  |  | 2Sfu9a6vTKeK4sxIMJmYXw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28390 | N | N | 10 | PACKAGE 1A - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499726 | 6359 | 124358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1APS00002040 | Finalization of Subcontractor |  | 368 | 0 | 168 | 0 | 0 | 0 | 168 | 0 | 0 | 0 |  |  |  | 2013-01-20 08:00 | 2013-02-13 17:00 |  | 2012-11-26 08:00 | 2012-12-20 17:00 | 2012-11-26 08:00 | 2012-12-20 17:00 | 2012-11-26 08:00 | 2012-12-20 17:00 | 2013-01-20 08:00 | 2013-02-13 17:00 |  | PT_Normal |  |  |  |  | 8aCCZL6RSWSLLSQbUpeg/A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28390 | N | N | 10 | PACKAGE 1A - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499727 | 6359 | 124358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1APS00002045 | Submission of Cost Proposal |  | 504 | 0 | 56 | 0 | 0 | 0 | 56 | 0 | 0 | 0 |  |  |  | 2013-03-14 08:00 | 2013-03-21 17:00 |  | 2012-12-30 08:00 | 2013-01-06 17:00 | 2012-12-30 08:00 | 2013-01-06 17:00 | 2012-12-30 08:00 | 2013-01-06 17:00 | 2013-03-14 08:00 | 2013-03-21 17:00 |  | PT_Normal |  |  |  |  | r0s5Jr+sSuqj4LXPGg3YBA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28390 | N | N | 10 | PACKAGE 1A - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499728 | 6359 | 124358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1APS00002050 | Approval of Cost Proposal |  | 504 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-03-23 08:00 | 2013-04-25 17:00 |  | 2013-01-07 08:00 | 2013-02-10 17:00 | 2013-01-07 08:00 | 2013-02-10 17:00 | 2013-01-07 08:00 | 2013-02-10 17:00 | 2013-03-23 08:00 | 2013-04-25 17:00 |  | PT_Normal |  |  |  |  | j9b+DeeeQtqjkTVX8TApUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28390 | N | N | 10 | PACKAGE 1A - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499729 | 6359 | 124358 | 13662 | 0 | N | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | DUKHMOBI1APS00002055 | Receiving of Variation Order |  | 504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-04-25 17:00 | 2013-04-25 17:00 |  | 2013-02-10 17:00 | 2013-02-10 17:00 | 2013-02-10 17:00 | 2013-02-10 17:00 | 2013-02-10 17:00 | 2013-02-10 17:00 | 2013-04-25 17:00 | 2013-04-25 17:00 |  | PT_Normal |  |  |  |  | qITXsBWhSNSSliX7ihThGw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28390 | N | N | 10 | PACKAGE 1A - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 0 | 0
%R | 499730 | 6359 | 124358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1APS00002060 | Engineering & Procurement |  | 504 | 0 | 1440 | 0 | 0 | 0 | 1440 | 0 | 0 | 0 |  |  |  | 2013-04-27 08:00 | 2013-11-27 17:00 |  | 2013-02-11 08:00 | 2013-09-12 17:00 | 2013-02-11 08:00 | 2013-09-12 17:00 | 2013-02-11 08:00 | 2013-09-12 17:00 | 2013-04-27 08:00 | 2013-11-27 17:00 |  | PT_Normal |  |  |  |  | oUH4NJwbSauqgFsK4fKRdA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28390 | N | N | 10 | PACKAGE 1A - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | 2013-AP02 | 2013-AP03 | 2013-AP04 | 2013-AP05 | 2013-AP06 | 2013-AP07 | 2013-AP08 | 2013-AP09 |  |  | 0 | 0
%R | 499731 | 6359 | 124358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1APS00002065 | Commencement of Construction Work |  | 504 | 504 | 2560 | 0 | 0 | 0 | 2560 | 0 | 0 | 0 |  |  |  | 2013-11-28 08:00 | 2014-12-14 17:00 |  | 2013-09-14 08:00 | 2014-09-29 17:00 | 2013-09-14 08:00 | 2014-09-29 17:00 | 2013-09-14 08:00 | 2014-09-29 17:00 | 2013-11-28 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | NZiFFVsPRKaI/oyN3XKz3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28390 | N | N | 10 | PACKAGE 1A - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: #VALUE! |  | 0 | 0
%R | 499732 | 6359 | 124358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1APS00002043 | Submission & Approval of General Site Layout |  | 368 | 0 | 168 | 0 | 0 | 0 | 168 | 0 | 0 | 0 |  |  |  | 2013-01-28 08:00 | 2013-02-21 17:00 |  | 2012-12-04 08:00 | 2012-12-29 17:00 | 2012-12-04 08:00 | 2012-12-29 17:00 | 2012-12-04 08:00 | 2012-12-29 17:00 | 2013-01-28 08:00 | 2013-02-21 17:00 |  | PT_Normal |  |  |  |  | G1EiYiwiQF2CNOjjA8OdBw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28390 | N | N | 10 | PACKAGE 1A - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499733 | 6359 | 124358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1APS00001000 | Submission of New Site Design Layout |  | 0 | 0 | 112 | 0 | 0 | 0 | 112 | 0 | 0 | 0 |  |  |  | 2012-12-01 08:00 | 2012-12-16 17:00 |  | 2012-12-01 08:00 | 2012-12-16 17:00 | 2012-12-01 08:00 | 2012-12-16 17:00 | 2012-12-01 08:00 | 2012-12-16 17:00 | 2012-12-01 08:00 | 2012-12-16 17:00 |  | PT_Normal |  |  |  |  | 44aQbJEYQ1CQ91RcBmOh3w | bRhhc9wzTlCfDlhtCkRJTg |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28390 | N | N | 10 | PACKAGE 1A - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499734 | 6359 | 124358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1APS00001200 | Approval of New Site Design Layout |  | 0 | 0 | 168 | 0 | 0 | 0 | 168 | 0 | 0 | 0 |  |  |  | 2012-12-17 08:00 | 2013-01-10 17:00 |  | 2012-12-17 08:00 | 2013-01-10 17:00 | 2012-12-17 08:00 | 2013-01-10 17:00 | 2012-12-17 08:00 | 2013-01-10 17:00 | 2012-12-17 08:00 | 2013-01-10 17:00 |  | PT_Normal |  |  |  |  | rygNNHOHQLmQwbMuHuGLUw | mUa/mwVkL06WZ2VwS6c03g |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28390 | N | N | 10 | PACKAGE 1A - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499735 | 6359 | 124358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1APS00001225 | Submission of Finished Floor Level |  | 0 | 0 | 56 | 0 | 0 | 0 | 56 | 0 | 0 | 0 |  |  |  | 2013-01-12 08:00 | 2013-01-19 17:00 |  | 2013-01-12 08:00 | 2013-01-19 17:00 | 2013-01-12 08:00 | 2013-01-19 17:00 | 2013-01-12 08:00 | 2013-01-19 17:00 | 2013-01-12 08:00 | 2013-01-19 17:00 |  | PT_Normal |  |  |  |  | fOov3uk5QImF8vTG2PRVIA | mUa/mwVkL06WZ2VwS6c03g |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28390 | N | N | 10 | PACKAGE 1A - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 0 | 0
%R | 499736 | 6359 | 124358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1APS00001250 | Approval of Finished Floor Level |  | 0 | 0 | 168 | 0 | 0 | 0 | 168 | 0 | 0 | 0 |  |  |  | 2013-01-20 08:00 | 2013-02-13 17:00 |  | 2013-01-20 08:00 | 2013-02-13 17:00 | 2013-01-20 08:00 | 2013-02-13 17:00 | 2013-01-20 08:00 | 2013-02-13 17:00 | 2013-01-20 08:00 | 2013-02-13 17:00 |  | PT_Normal |  |  |  |  | Vk40iV5YRyaUjAGAEaxmhQ | 1bxI7mBXcUGHOwncrhw4Ig |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28390 | N | N | 10 | PACKAGE 1A - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 0 | 0
%R | 499737 | 6359 | 124358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1APS00001300 | Submission of New Site Design MEP Services Layout |  | 712 | 0 | 112 | 0 | 0 | 0 | 112 | 0 | 0 | 0 |  |  |  | 2013-04-27 08:00 | 2013-05-12 17:00 |  | 2013-01-12 08:00 | 2013-01-27 17:00 | 2013-01-12 08:00 | 2013-01-27 17:00 | 2013-01-12 08:00 | 2013-01-27 17:00 | 2013-04-27 08:00 | 2013-05-12 17:00 |  | PT_Normal |  |  |  |  | Uma2XfeLQ8SITVfsO1wy/A | mUa/mwVkL06WZ2VwS6c03g |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 28390 | N | N | 10 | PACKAGE 1A - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 0 | 0
%R | 499738 | 6359 | 124358 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1APS00001400 | Approval of New Site Design MEP Services Layout |  | 712 | 352 | 168 | 0 | 0 | 0 | 168 | 0 | 0 | 0 |  |  |  | 2013-05-13 08:00 | 2013-06-05 17:00 |  | 2013-01-28 08:00 | 2013-02-21 17:00 | 2013-01-28 08:00 | 2013-02-21 17:00 | 2013-01-28 08:00 | 2013-02-21 17:00 | 2013-05-13 08:00 | 2013-06-05 17:00 |  | PT_Normal |  |  |  |  | jAAXMisNTE+d1sFIiD6fyA | 1bxI7mBXcUGHOwncrhw4Ig |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 28390 | N | N | 10 | PACKAGE 1A - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 0 | 0
%R | 499739 | 6359 | 124359 | 13662 | 0 | N | N | N | CP_Drtn | TT_Mile | DT_FixedDUR2 | TK_NotStart | DUKHMOBP2BPS00002210 | Receiving of Site Instruction |  | 384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-01-22 08:00 | 2013-01-22 08:00 |  | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2013-01-22 08:00 | 2013-01-22 08:00 |  | PT_Normal |  |  |  |  | CHG1xONoRt6Ig3vbsUBNOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28440 | N | N | 35 | PACKAGE 2B - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499740 | 6359 | 124359 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP2BPS00002215 | Finalization of Subcontractor |  | 704 | 0 | 168 | 0 | 0 | 0 | 168 | 0 | 0 | 0 |  |  |  | 2013-03-11 08:00 | 2013-04-03 17:00 |  | 2012-11-26 08:00 | 2012-12-20 17:00 | 2012-11-26 08:00 | 2012-12-20 17:00 | 2012-11-26 08:00 | 2012-12-20 17:00 | 2013-03-11 08:00 | 2013-04-03 17:00 |  | PT_Normal |  |  |  |  | 38onYNPrTDKobKm6NBTy0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28440 | N | N | 35 | PACKAGE 2B - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499741 | 6359 | 124359 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP2BPS00002220 | Submission of Cost Proposal |  | 704 | 0 | 56 | 0 | 0 | 0 | 56 | 0 | 0 | 0 |  |  |  | 2013-04-04 08:00 | 2013-04-11 17:00 |  | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 | 2013-04-04 08:00 | 2013-04-11 17:00 |  | PT_Normal |  |  |  |  | 0tW0UkZwTUmAbVhXAkHJMQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28440 | N | N | 35 | PACKAGE 2B - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499742 | 6359 | 124359 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP2BPS00002225 | Approval of Cost Proposal |  | 704 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-13 08:00 | 2013-05-16 17:00 |  | 2012-12-30 08:00 | 2013-02-02 17:00 | 2012-12-30 08:00 | 2013-02-02 17:00 | 2012-12-30 08:00 | 2013-02-02 17:00 | 2013-04-13 08:00 | 2013-05-16 17:00 |  | PT_Normal |  |  |  |  | fmVAn88HSu++I1Ywl9x6bw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28440 | N | N | 35 | PACKAGE 2B - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499743 | 6359 | 124359 | 13662 | 0 | N | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | DUKHMOBP2BPS00002230 | Receiving of Variation Order |  | 704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-05-16 17:00 | 2013-05-16 17:00 |  | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-05-16 17:00 | 2013-05-16 17:00 |  | PT_Normal |  |  |  |  | iOoAO/oRQ7aenGvZyBfcfQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28440 | N | N | 35 | PACKAGE 2B - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 0 | 0
%R | 499744 | 6359 | 124359 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP2BPS00002235 | Engineering & Procurement |  | 704 | 432 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 |  |  |  | 2013-05-18 08:00 | 2013-11-13 17:00 |  | 2013-02-03 08:00 | 2013-07-28 17:00 | 2013-02-03 08:00 | 2013-07-28 17:00 | 2013-02-03 08:00 | 2013-07-28 17:00 | 2013-05-18 08:00 | 2013-11-13 17:00 |  | PT_Normal |  |  |  |  | 5ZX9SOYQTSesDrDB5qSVQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28440 | N | N | 35 | PACKAGE 2B - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | 2013-AP02 | 2013-AP03 | 2013-AP04 | 2013-AP05 | 2013-AP06 | 2013-AP07 |  |  |  |  | 0 | 0
%R | 499745 | 6359 | 124359 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP2BPS00002240 | Commencement of Construction Work |  | 272 | 272 | 1440 | 0 | 0 | 0 | 1440 | 0 | 0 | 0 |  |  |  | 2013-11-14 08:00 | 2014-06-14 17:00 |  | 2013-10-03 08:00 | 2014-05-05 17:00 | 2013-10-03 08:00 | 2014-05-05 17:00 | 2013-10-03 08:00 | 2014-05-05 17:00 | 2013-11-14 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | 53hKxg8nTTujPCo7qpx3Dw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28440 | N | N | 35 | PACKAGE 2B - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | 2013-AP10 | 2013-AP11 | 2013-AP12 | 2014-AP01 | 2014-AP01 | 2014-AP03 | 2014-AP04 | 2014-AP05 |  |  | 0 | 0
%R | 499746 | 6359 | 124360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Mile | DT_FixedDUR2 | TK_NotStart | DUKHMOBI2APS00002175 | Receiving of Site Instruction |  | 704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-03-11 08:00 | 2013-03-11 08:00 |  | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2013-03-11 08:00 | 2013-03-11 08:00 |  | PT_Normal |  |  |  |  | YYBlsMOQSZ+xXZQF1PmWWg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28430 | N | N | 30 | PACKAGE 2A- INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499747 | 6359 | 124360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI2APS00002180 | Finalization of Subcontractor |  | 704 | 0 | 168 | 0 | 0 | 0 | 168 | 0 | 0 | 0 |  |  |  | 2013-03-11 08:00 | 2013-04-03 17:00 |  | 2012-11-26 08:00 | 2012-12-20 17:00 | 2012-11-26 08:00 | 2012-12-20 17:00 | 2012-11-26 08:00 | 2012-12-20 17:00 | 2013-03-11 08:00 | 2013-04-03 17:00 |  | PT_Normal |  |  |  |  | yH9TM9RBSseAbV3LEaPdfA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28430 | N | N | 30 | PACKAGE 2A- INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499748 | 6359 | 124360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI2APS00002185 | Submission of Cost Proposal |  | 704 | 0 | 56 | 0 | 0 | 0 | 56 | 0 | 0 | 0 |  |  |  | 2013-04-04 08:00 | 2013-04-11 17:00 |  | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 | 2013-04-04 08:00 | 2013-04-11 17:00 |  | PT_Normal |  |  |  |  | bRof1KunRh6dwpoAUOedzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28430 | N | N | 30 | PACKAGE 2A- INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499749 | 6359 | 124360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI2APS00002190 | Approval of Cost Proposal |  | 704 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-13 08:00 | 2013-05-16 17:00 |  | 2012-12-30 08:00 | 2013-02-02 17:00 | 2012-12-30 08:00 | 2013-02-02 17:00 | 2012-12-30 08:00 | 2013-02-02 17:00 | 2013-04-13 08:00 | 2013-05-16 17:00 |  | PT_Normal |  |  |  |  | lgeLu48hRiOuHKea1CB/7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28430 | N | N | 30 | PACKAGE 2A- INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499750 | 6359 | 124360 | 13662 | 0 | N | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | DUKHMOBI2APS00002195 | Receiving of Variation Order |  | 704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-05-16 17:00 | 2013-05-16 17:00 |  | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-05-16 17:00 | 2013-05-16 17:00 |  | PT_Normal |  |  |  |  | cFX/7ZCXTWOisRUgGcEX/Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28430 | N | N | 30 | PACKAGE 2A- INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 0 | 0
%R | 499751 | 6359 | 124360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI2APS00002200 | Engineering & Procurement |  | 704 | 424 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-05-18 08:00 | 2013-10-07 17:00 |  | 2013-02-03 08:00 | 2013-06-23 17:00 | 2013-02-03 08:00 | 2013-06-23 17:00 | 2013-02-03 08:00 | 2013-06-23 17:00 | 2013-05-18 08:00 | 2013-10-07 17:00 |  | PT_Normal |  |  |  |  | Dx3q3P3HQBu+lOOHS99ubA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28430 | N | N | 30 | PACKAGE 2A- INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03; period 3: 2013-AP04; period 4: 2013-AP05; period 5: 2013-AP06 |  | 0 | 0
%R | 499752 | 6359 | 124360 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI2APS00002205 | Commencement of Construction Work |  | 280 | 8 | 1680 | 0 | 0 | 0 | 1680 | 0 | 0 | 0 |  |  |  | 2013-10-08 08:00 | 2014-06-14 17:00 |  | 2013-08-28 08:00 | 2014-05-04 17:00 | 2013-08-28 08:00 | 2014-05-04 17:00 | 2013-08-28 08:00 | 2014-05-04 17:00 | 2013-10-08 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | 2W7EY6FzQQadjliLnpv3WA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28430 | N | N | 30 | PACKAGE 2A- INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | 2013-AP08 | 2013-AP09 | 2013-AP10 | 2013-AP11 | 2013-AP12 | 2014-AP01 | 2014-AP02 | 2014-AP03 | 2014-AP04 |  | 0 | 0
%R | 499753 | 6359 | 124361 | 13662 | 0 | N | N | N | CP_Drtn | TT_Mile | DT_FixedDUR2 | TK_NotStart | DUKHMOBI03PS00002315 | Receiving of Site Instruction |  | 312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-01-12 08:00 | 2013-01-12 08:00 |  | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2013-01-12 08:00 | 2013-01-12 08:00 |  | PT_Normal |  |  |  |  | 36vfoOGySRuKAuHh31+HYA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28470 | N | N | 50 | PACKAGE 3 - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499754 | 6359 | 124361 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI03PS00002320 | Finalization of Subcontractor |  | 312 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-01-12 08:00 | 2013-02-16 17:00 |  | 2012-11-26 08:00 | 2012-12-31 17:00 | 2012-11-26 08:00 | 2012-12-31 17:00 | 2012-11-26 08:00 | 2012-12-31 17:00 | 2013-01-12 08:00 | 2013-02-16 17:00 |  | PT_Normal |  |  |  |  | Lmk6VuY4TeiW3fhcZ/uH7g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28470 | N | N | 50 | PACKAGE 3 - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11; period 2: 2012-AP12 |  | 0 | 0
%R | 499755 | 6359 | 124361 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI03PS00002325 | Submission of Cost Proposal |  | 312 | 0 | 56 | 0 | 0 | 0 | 56 | 0 | 0 | 0 |  |  |  | 2013-02-17 08:00 | 2013-02-24 17:00 |  | 2013-01-01 08:00 | 2013-01-08 17:00 | 2013-01-01 08:00 | 2013-01-08 17:00 | 2013-01-01 08:00 | 2013-01-08 17:00 | 2013-02-17 08:00 | 2013-02-24 17:00 |  | PT_Normal |  |  |  |  | 5IwxHMLBTYG9LNhLbmjw0A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28470 | N | N | 50 | PACKAGE 3 - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 0 | 0
%R | 499756 | 6359 | 124361 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI03PS00002330 | Approval of Cost Proposal |  | 312 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-02-25 08:00 | 2013-03-31 17:00 |  | 2013-01-09 08:00 | 2013-02-13 17:00 | 2013-01-09 08:00 | 2013-02-13 17:00 | 2013-01-09 08:00 | 2013-02-13 17:00 | 2013-02-25 08:00 | 2013-03-31 17:00 |  | PT_Normal |  |  |  |  | FV5XH/fcRuCIYOK0kUxGog |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28470 | N | N | 50 | PACKAGE 3 - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499757 | 6359 | 124361 | 13662 | 0 | N | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | DUKHMOBI03PS00002335 | Receiving of Variation Order |  | 312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-03-31 17:00 | 2013-03-31 17:00 |  | 2013-02-13 17:00 | 2013-02-13 17:00 | 2013-02-13 17:00 | 2013-02-13 17:00 | 2013-02-13 17:00 | 2013-02-13 17:00 | 2013-03-31 17:00 | 2013-03-31 17:00 |  | PT_Normal |  |  |  |  | 2U2Dq1C2R+GzMYGO2yfQ4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28470 | N | N | 50 | PACKAGE 3 - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 0 | 0
%R | 499758 | 6359 | 124361 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI03PS00002340 | Engineering & Procurement |  | 312 | 272 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-04-01 08:00 | 2013-08-21 17:00 |  | 2013-02-14 08:00 | 2013-07-03 17:00 | 2013-02-14 08:00 | 2013-07-03 17:00 | 2013-02-14 08:00 | 2013-07-03 17:00 | 2013-04-01 08:00 | 2013-08-21 17:00 |  | PT_Normal |  |  |  |  | zuDPSbdnQQiKvwAbpVa+Vg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28470 | N | N | 50 | PACKAGE 3 - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03; period 3: 2013-AP04; period 4: 2013-AP05; period 5: 2013-AP06 |  | 0 | 0
%R | 499759 | 6359 | 124361 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI03PS00002345 | Commencement of Construction Work |  | 40 | 40 | 1600 | 0 | 0 | 0 | 1600 | 0 | 0 | 0 |  |  |  | 2013-08-22 08:00 | 2014-04-16 17:00 |  | 2013-08-17 08:00 | 2014-04-10 17:00 | 2013-08-17 08:00 | 2014-04-10 17:00 | 2013-08-17 08:00 | 2014-04-10 17:00 | 2013-08-22 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | uzR0DGRGRHSQrZ12oFDUVw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28470 | N | N | 50 | PACKAGE 3 - INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | 2013-AP08 | 2013-AP09 | 2013-AP10 | 2013-AP11 | 2013-AP12 | 2014-AP01 | 2014-AP02 | 2014-AP03 |  |  | 0 | 0
%R | 499760 | 6359 | 124362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Mile | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1BPS00002105 | Receiving of Site Instruction |  | 584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-02-21 08:00 | 2013-02-21 08:00 |  | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2013-02-21 08:00 | 2013-02-21 08:00 |  | PT_Normal |  |  |  |  | 2rmjb++tSEqCzSuJW6dnQw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28410 | N | N | 20 | PACKAGE 1B -INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499761 | 6359 | 124362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1BPS00002110 | Finalization of Subcontractor |  | 584 | 0 | 168 | 0 | 0 | 0 | 168 | 0 | 0 | 0 |  |  |  | 2013-02-21 08:00 | 2013-03-17 17:00 |  | 2012-11-26 08:00 | 2012-12-20 17:00 | 2012-11-26 08:00 | 2012-12-20 17:00 | 2012-11-26 08:00 | 2012-12-20 17:00 | 2013-02-21 08:00 | 2013-03-17 17:00 |  | PT_Normal |  |  |  |  | 2EIuBOaqRR6EnkJr+sDF5w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28410 | N | N | 20 | PACKAGE 1B -INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499762 | 6359 | 124362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1BPS00002115 | Submission of Cost Proposal |  | 584 | 0 | 56 | 0 | 0 | 0 | 56 | 0 | 0 | 0 |  |  |  | 2013-03-26 08:00 | 2013-04-02 17:00 |  | 2012-12-30 08:00 | 2013-01-06 17:00 | 2012-12-30 08:00 | 2013-01-06 17:00 | 2012-12-30 08:00 | 2013-01-06 17:00 | 2013-03-26 08:00 | 2013-04-02 17:00 |  | PT_Normal |  |  |  |  | 5oGl6ZHpSxCVgkQVojlPQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28410 | N | N | 20 | PACKAGE 1B -INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499763 | 6359 | 124362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1BPS00002120 | Approval of Cost Proposal |  | 584 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-03 08:00 | 2013-05-07 17:00 |  | 2013-01-07 08:00 | 2013-02-10 17:00 | 2013-01-07 08:00 | 2013-02-10 17:00 | 2013-01-07 08:00 | 2013-02-10 17:00 | 2013-04-03 08:00 | 2013-05-07 17:00 |  | PT_Normal |  |  |  |  | czWUVQkcR6yOzU6POXlTRQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28410 | N | N | 20 | PACKAGE 1B -INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499764 | 6359 | 124362 | 13662 | 0 | N | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | DUKHMOBI1BPS00002125 | Receiving of Variation Order |  | 584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-05-07 17:00 | 2013-05-07 17:00 |  | 2013-02-10 17:00 | 2013-02-10 17:00 | 2013-02-10 17:00 | 2013-02-10 17:00 | 2013-02-10 17:00 | 2013-02-10 17:00 | 2013-05-07 17:00 | 2013-05-07 17:00 |  | PT_Normal |  |  |  |  | ju5zYPWZS0C5yhBs8mcP+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28410 | N | N | 20 | PACKAGE 1B -INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 0 | 0
%R | 499765 | 6359 | 124362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1BPS00002130 | Engineering & Procurement |  | 584 | 240 | 1680 | 0 | 0 | 0 | 1680 | 0 | 0 | 0 |  |  |  | 2013-05-08 08:00 | 2014-01-14 17:00 |  | 2013-02-11 08:00 | 2013-10-20 17:00 | 2013-02-11 08:00 | 2013-10-20 17:00 | 2013-02-11 08:00 | 2013-10-20 17:00 | 2013-05-08 08:00 | 2014-01-14 17:00 |  | PT_Normal |  |  |  |  | 4DV+WIf0SBOiDB8uVm14Cg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28410 | N | N | 20 | PACKAGE 1B -INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | 2013-AP02 | 2013-AP03 | 2013-AP04 | 2013-AP05 | 2013-AP06 | 2013-AP07 | 2013-AP08 | 2013-AP09 | 2013-AP10 |  | 0 | 0
%R | 499766 | 6359 | 124362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1BPS00002135 | Commencement of Construction Work |  | 344 | 320 | 2240 | 0 | 0 | 0 | 2240 | 0 | 0 | 0 |  |  |  | 2014-01-15 08:00 | 2014-12-14 17:00 |  | 2013-11-25 08:00 | 2014-10-25 17:00 | 2013-11-25 08:00 | 2014-10-25 17:00 | 2013-11-25 08:00 | 2014-10-25 17:00 | 2014-01-15 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | 5Txk8g09QqGEPrCmlbCy1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28410 | N | N | 20 | PACKAGE 1B -INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: #VALUE! |  | 0 | 0
%R | 499767 | 6359 | 124362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1BPS00002113 | Submission & Approval of General Site Layout |  | 584 | 0 | 168 | 0 | 0 | 0 | 168 | 0 | 0 | 0 |  |  |  | 2013-03-02 08:00 | 2013-03-25 17:00 |  | 2012-12-04 08:00 | 2012-12-29 17:00 | 2012-12-04 08:00 | 2012-12-29 17:00 | 2012-12-04 08:00 | 2012-12-29 17:00 | 2013-03-02 08:00 | 2013-03-25 17:00 |  | PT_Normal |  |  |  |  | 6wwXSlMtRByGUHIRe1BEvQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28410 | N | N | 20 | PACKAGE 1B -INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499768 | 6359 | 124362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1BPS00001000 | Submission of New Site Design Layout |  | 400 | 0 | 112 | 0 | 0 | 0 | 112 | 0 | 0 | 0 |  |  |  | 2013-01-29 08:00 | 2013-02-14 17:00 |  | 2012-12-01 08:00 | 2012-12-16 17:00 | 2012-12-01 08:00 | 2012-12-16 17:00 | 2012-12-01 08:00 | 2012-12-16 17:00 | 2013-01-29 08:00 | 2013-02-14 17:00 |  | PT_Normal |  |  |  |  | ifoUgD8UQaeWWtar7X5GUg | IT27RBTeT4GTef+9l/xLjQ |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28410 | N | N | 20 | PACKAGE 1B -INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499769 | 6359 | 124362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1BPS00001200 | Approval of New Site Design Layout |  | 400 | 0 | 168 | 0 | 0 | 0 | 168 | 0 | 0 | 0 |  |  |  | 2013-02-16 08:00 | 2013-03-11 17:00 |  | 2012-12-17 08:00 | 2013-01-10 17:00 | 2012-12-17 08:00 | 2013-01-10 17:00 | 2012-12-17 08:00 | 2013-01-10 17:00 | 2013-02-16 08:00 | 2013-03-11 17:00 |  | PT_Normal |  |  |  |  | 8kmLG1TJQcqqOp/QFJ9yjg | TkQuAhd13UORiC85wxansA |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28410 | N | N | 20 | PACKAGE 1B -INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499770 | 6359 | 124362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1BPS00001225 | Submission of Finished Floor Level |  | 400 | 0 | 56 | 0 | 0 | 0 | 56 | 0 | 0 | 0 |  |  |  | 2013-03-12 08:00 | 2013-03-19 17:00 |  | 2013-01-12 08:00 | 2013-01-19 17:00 | 2013-01-12 08:00 | 2013-01-19 17:00 | 2013-01-12 08:00 | 2013-01-19 17:00 | 2013-03-12 08:00 | 2013-03-19 17:00 |  | PT_Normal |  |  |  |  | dNc0R2OzT6GHWWdU94rcgQ | TkQuAhd13UORiC85wxansA |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28410 | N | N | 20 | PACKAGE 1B -INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 0 | 0
%R | 499771 | 6359 | 124362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1BPS00001250 | Approval of Finished Floor Level |  | 400 | 400 | 168 | 0 | 0 | 0 | 168 | 0 | 0 | 0 |  |  |  | 2013-03-20 08:00 | 2013-04-13 17:00 |  | 2013-01-20 08:00 | 2013-02-13 17:00 | 2013-01-20 08:00 | 2013-02-13 17:00 | 2013-01-20 08:00 | 2013-02-13 17:00 | 2013-03-20 08:00 | 2013-04-13 17:00 |  | PT_Normal |  |  |  |  | o4pjqeNcSFOMbcan1041Ew | LkoIGHT/jkujbzY48akh+w |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28410 | N | N | 20 | PACKAGE 1B -INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 0 | 0
%R | 499772 | 6359 | 124362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1BPS00001300 | Submission of New Site Design MEP Services Layout |  | 712 | 0 | 112 | 0 | 0 | 0 | 112 | 0 | 0 | 0 |  |  |  | 2013-04-27 08:00 | 2013-05-12 17:00 |  | 2013-01-12 08:00 | 2013-01-27 17:00 | 2013-01-12 08:00 | 2013-01-27 17:00 | 2013-01-12 08:00 | 2013-01-27 17:00 | 2013-04-27 08:00 | 2013-05-12 17:00 |  | PT_Normal |  |  |  |  | F/SRSB0oSGq7f9ALdloEzA | TkQuAhd13UORiC85wxansA |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 28410 | N | N | 20 | PACKAGE 1B -INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 0 | 0
%R | 499773 | 6359 | 124362 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBI1BPS00001400 | Approval of New Site Design MEP Services Layout |  | 712 | 352 | 168 | 0 | 0 | 0 | 168 | 0 | 0 | 0 |  |  |  | 2013-05-13 08:00 | 2013-06-05 17:00 |  | 2013-01-28 08:00 | 2013-02-21 17:00 | 2013-01-28 08:00 | 2013-02-21 17:00 | 2013-01-28 08:00 | 2013-02-21 17:00 | 2013-05-13 08:00 | 2013-06-05 17:00 |  | PT_Normal |  |  |  |  | wvHZopVLQ2KPkeZ2Wc9hZw | LkoIGHT/jkujbzY48akh+w |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 28410 | N | N | 20 | PACKAGE 1B -INFRASTRUCTURE |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 0 | 0
%R | 499774 | 6359 | 124363 | 13662 | 0 | N | N | N | CP_Drtn | TT_Mile | DT_FixedDUR2 | TK_NotStart | DUKHMOBP1APS00002000 | Receiving of Site Instruction |  | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-01-20 08:00 | 2013-01-20 08:00 |  | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2012-11-26 08:00 | 2013-01-20 08:00 | 2013-01-20 08:00 |  | PT_Normal |  |  |  |  | Pc0+cFSYRJeFqC7co+taHg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28380 | N | N | 05 | PACKAGE 1A - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499775 | 6359 | 124363 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP1APS00002005 | Finalization of Subcontractor |  | 720 | 0 | 168 | 0 | 0 | 0 | 168 | 0 | 0 | 0 |  |  |  | 2013-03-13 08:00 | 2013-04-06 17:00 |  | 2012-11-26 08:00 | 2012-12-20 17:00 | 2012-11-26 08:00 | 2012-12-20 17:00 | 2012-11-26 08:00 | 2012-12-20 17:00 | 2013-03-13 08:00 | 2013-04-06 17:00 |  | PT_Normal |  |  |  |  | 5WFlcGB+Sse9mc72cU7ppw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28380 | N | N | 05 | PACKAGE 1A - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499776 | 6359 | 124363 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP1APS00002010 | Submission of Cost Proposal |  | 720 | 0 | 56 | 0 | 0 | 0 | 56 | 0 | 0 | 0 |  |  |  | 2013-04-07 08:00 | 2013-04-14 17:00 |  | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 | 2013-04-07 08:00 | 2013-04-14 17:00 |  | PT_Normal |  |  |  |  | m+vKgNgeS0exMA2wt69trQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28380 | N | N | 05 | PACKAGE 1A - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499777 | 6359 | 124363 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP1APS00002015 | Approval of Cost Proposal |  | 720 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-15 08:00 | 2013-05-19 17:00 |  | 2012-12-30 08:00 | 2013-02-02 17:00 | 2012-12-30 08:00 | 2013-02-02 17:00 | 2012-12-30 08:00 | 2013-02-02 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 |  | PT_Normal |  |  |  |  | ANuX8edjSPyYzSxearALPA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28380 | N | N | 05 | PACKAGE 1A - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499778 | 6359 | 124363 | 13662 | 0 | N | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | DUKHMOBP1APS00002020 | Receiving of Variation Order |  | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-05-19 17:00 | 2013-05-19 17:00 |  | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-02-02 17:00 | 2013-05-19 17:00 | 2013-05-19 17:00 |  | PT_Normal |  |  |  |  | al1uDbt0SlGBA4Vx8x7Xmw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28380 | N | N | 05 | PACKAGE 1A - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 0 | 0
%R | 499779 | 6359 | 124363 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP1APS00002025 | Engineering & Procurement |  | 720 | 504 | 1520 | 0 | 0 | 0 | 1520 | 0 | 0 | 0 |  |  |  | 2013-05-20 08:00 | 2014-01-02 17:00 |  | 2013-02-03 08:00 | 2013-09-16 17:00 | 2013-02-03 08:00 | 2013-09-16 17:00 | 2013-02-03 08:00 | 2013-09-16 17:00 | 2013-05-20 08:00 | 2014-01-02 17:00 |  | PT_Normal |  |  |  |  | g9Yu21x1RiWAXvS//z9mYA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28380 | N | N | 05 | PACKAGE 1A - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | 2013-AP02 | 2013-AP03 | 2013-AP04 | 2013-AP05 | 2013-AP06 | 2013-AP07 | 2013-AP08 | 2013-AP09 |  |  | 0 | 0
%R | 499780 | 6359 | 124363 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP1APS00002030 | Commencement of Construction Work |  | 216 | 216 | 2320 | 0 | 0 | 0 | 2320 | 0 | 0 | 0 |  |  |  | 2014-01-04 08:00 | 2014-12-14 17:00 |  | 2013-12-02 08:00 | 2014-11-12 17:00 | 2013-12-02 08:00 | 2014-11-12 17:00 | 2013-12-02 08:00 | 2014-11-12 17:00 | 2014-01-04 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | 9bMz2bMISZOdyMusdLeIKg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28380 | N | N | 05 | PACKAGE 1A - VILLA |  | 124353 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: #VALUE! |  | 0 | 0
%R | 499781 | 6359 | 124364 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBGEN0000003030 | Sub & App -Key Personnel CVs | 12515 | 712 | 0 | 480 | 0 | 200 | 200 | 480 | 0 | 0 | 0 |  |  |  | 2013-02-20 08:00 | 2013-04-30 17:00 |  | 2012-11-06 08:00 | 2013-01-15 17:00 | 2012-11-06 08:00 | 2013-01-15 17:00 | 2012-11-06 08:00 | 2013-01-15 17:00 | 2013-02-20 08:00 | 2013-04-30 17:00 |  | PT_Normal |  |  |  |  | fSf4rNJeSOaYQ4HdJqkOKA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [5 empty] | 45403 |  |  |  |  | QUANTITY SURVEYOUR | M305 |  | 1 | QT_Hour |  | Y | Y | N | 1 |  | RT_Labor |  |  |  |  | 540 | 28480 | N | N | L10 | GENERAL |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11; period 2: 2012-AP12; period 3: 2013-AP01 |  | 66.6667 | QUANTITY SURVEYOUR
%R | 499782 | 6359 | 124364 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBGEN0000003035 | Sub & App -HSE plan | 12516 | 712 | 0 | 480 | 0 | 200 | 200 | 480 | 0 | 0 | 0 |  |  |  | 2013-02-26 08:00 | 2013-05-06 17:00 |  | 2012-11-12 08:00 | 2013-01-21 17:00 | 2012-11-12 08:00 | 2013-01-21 17:00 | 2012-11-12 08:00 | 2013-01-21 17:00 | 2013-02-26 08:00 | 2013-05-06 17:00 |  | PT_Normal |  |  |  |  | uwxvoquyRceFh83MXuhfxQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [5 empty] | 45402 |  |  |  |  | SAFETY OFFICER | M306 |  | 1 | QT_Hour |  | Y | Y | N | 1 |  | RT_Labor |  |  |  |  | 540 | 28480 | N | N | L10 | GENERAL |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11; period 2: 2012-AP12; period 3: 2013-AP01 |  | 66.6667 | SAFETY OFFICER
%R | 499783 | 6359 | 124364 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBGEN0000003040 | Sub & App -Quality plan | 12515 | 712 | 224 | 480 | 0 | 200 | 200 | 480 | 0 | 0 | 0 |  |  |  | 2013-03-04 08:00 | 2013-05-12 17:00 |  | 2012-11-18 08:00 | 2013-01-27 17:00 | 2012-11-18 08:00 | 2013-01-27 17:00 | 2012-11-18 08:00 | 2013-01-27 17:00 | 2013-03-04 08:00 | 2013-05-12 17:00 |  | PT_Normal |  |  |  |  | UfJiJrDvSJapeI7xwj9L2w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [5 empty] | 45403 |  |  |  |  | QUANTITY SURVEYOUR | M305 |  | 1 | QT_Hour |  | Y | Y | N | 1 |  | RT_Labor |  |  |  |  | 540 | 28480 | N | N | L10 | GENERAL |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11; period 2: 2012-AP12; period 3: 2013-AP01 |  | 66.6667 | QUANTITY SURVEYOUR
%R | 499784 | 6359 | 124364 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBGEN0000003000 | Performance Bond (Clause 10) |  | 576 | 240 | 240 | 0 | 240 | 240 | 240 | 0 | 0 | 0 |  |  |  | 2013-01-26 08:00 | 2013-03-02 17:00 |  | 2012-11-01 08:00 | 2012-12-05 17:00 | 2012-11-01 08:00 | 2012-12-05 17:00 | 2012-11-01 08:00 | 2012-12-05 17:00 | 2013-01-26 08:00 | 2013-03-02 17:00 |  | PT_Normal |  |  |  |  | csX3aL49S3i5HC2sXqMzZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28480 | N | N | L10 | GENERAL |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11; period 2: 2012-AP12 |  | 120 | 0
%R | 499785 | 6359 | 124364 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBGEN0000003005 | Setting Out (Clause 17) |  | 576 | 240 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-01-26 08:00 | 2013-03-02 17:00 |  | 2012-11-01 08:00 | 2012-12-05 17:00 | 2012-11-01 08:00 | 2012-12-05 17:00 | 2012-11-01 08:00 | 2012-12-05 17:00 | 2013-01-26 08:00 | 2013-03-02 17:00 |  | PT_Normal |  |  |  |  | IiaD440ZRG2fZlFOFFGHRw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28480 | N | N | L10 | GENERAL |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11; period 2: 2012-AP12 |  | 0 | 0
%R | 499786 | 6359 | 124364 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBGEN0000003010 | Insurance of works (Clause 21-23) |  | 576 | 240 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-01-26 08:00 | 2013-03-02 17:00 |  | 2012-11-01 08:00 | 2012-12-05 17:00 | 2012-11-01 08:00 | 2012-12-05 17:00 | 2012-11-01 08:00 | 2012-12-05 17:00 | 2013-01-26 08:00 | 2013-03-02 17:00 |  | PT_Normal |  |  |  |  | BfuIFZ3DSb+Gjzl5ZgZ2KQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28480 | N | N | L10 | GENERAL |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11; period 2: 2012-AP12 |  | 0 | 0
%R | 499787 | 6359 | 124364 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBGEN0000003015 | Commencement of works (Clause 41) |  | 456 | 40 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-01-08 08:00 | 2013-02-11 17:00 |  | 2012-11-01 08:00 | 2012-12-05 17:00 | 2012-11-01 08:00 | 2012-12-05 17:00 | 2012-11-01 08:00 | 2012-12-05 17:00 | 2013-01-08 08:00 | 2013-02-11 17:00 |  | PT_Normal |  |  |  |  | WgC1QOsCQ+WlQETmtiLnRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28480 | N | N | L10 | GENERAL |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11; period 2: 2012-AP12 |  | 0 | 0
%R | 499788 | 6359 | 124364 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBGEN0000003020 | Construction of plant,Temporary works & material |  | 336 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2012-12-22 08:00 | 2013-01-24 17:00 |  | 2012-11-01 08:00 | 2012-12-05 17:00 | 2012-11-01 08:00 | 2012-12-05 17:00 | 2012-11-01 08:00 | 2012-12-05 17:00 | 2012-12-22 08:00 | 2013-01-24 17:00 |  | PT_Normal |  |  |  |  | B7Kmw0G4TH+w02ntJZAmiA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28480 | N | N | L10 | GENERAL |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11; period 2: 2012-AP12 |  | 0 | 0
%R | 499789 | 6359 | 124364 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBGEN0000003025 | Construction Running Cost |  | 0 | 0 | 7048 | 0 | 0 | 0 | 7048 | 0 | 0 | 0 |  |  |  | 2012-11-01 08:00 | 2015-03-31 17:00 |  | 2012-11-01 08:00 | 2015-03-31 17:00 | 2012-11-01 08:00 | 2015-03-31 17:00 | 2012-11-01 08:00 | 2015-03-31 17:00 | 2012-11-01 08:00 | 2015-03-31 17:00 |  | PT_Normal |  |  |  |  | riSc+UhpQ+66TxmDJSu31Q |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 28480 | N | N | L10 | GENERAL |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: #VALUE! |  | 0 | 0
%R | 499790 | 6359 | 124365 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP020000004000 | Securing Gate Passes/Access Permit & Courses | 12516 | 0 | 0 | 200 | 0 | 100 | 100 | 200 | 0 | 0 | 0 |  |  |  | 2012-11-01 08:00 | 2012-11-29 17:00 |  | 2012-11-01 08:00 | 2012-11-29 17:00 | 2012-11-01 08:00 | 2012-11-29 17:00 | 2012-11-01 08:00 | 2012-11-29 17:00 | 2012-11-01 08:00 | 2012-11-29 17:00 |  | PT_Normal |  |  |  |  | wjXXbMT1Sxec4aqJZU58TQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [5 empty] | 45402 |  |  |  |  | SAFETY OFFICER | M306 |  | 1 | QT_Hour |  | Y | Y | N | 1 |  | RT_Labor |  |  |  |  | 540 | 28630 | N | N | L30 | PACKAGE-2 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 100 | SAFETY OFFICER
%R | 499791 | 6359 | 124365 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP020000004010 | Sub & Approval of Site Logistic Plan | 8176 | 312 | 0 | 240 | 0 | 100 | 100 | 240 | 0 | 0 | 0 |  |  |  | 2012-12-31 08:00 | 2013-02-03 17:00 |  | 2012-11-14 08:00 | 2012-12-19 17:00 | 2012-11-14 08:00 | 2012-12-19 17:00 | 2012-11-14 08:00 | 2012-12-19 17:00 | 2012-12-31 08:00 | 2013-02-03 17:00 |  | PT_Normal |  |  |  |  | VqlnjOJyTQK4TAPybK9UXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43530 |  |  |  |  | DRAFTMAN SK | J320 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28630 | N | N | L30 | PACKAGE-2 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11; period 2: 2012-AP12 |  | 50 | DRAFTMAN SK
%R | 499792 | 6359 | 124365 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP020000004020 | Sub & App of Method Statement-Temporary Struct. | 8176 | 352 | 0 | 240 | 0 | 100 | 100 | 240 | 0 | 0 | 0 |  |  |  | 2013-01-12 08:00 | 2013-02-16 17:00 |  | 2012-11-20 08:00 | 2012-12-25 17:00 | 2012-11-20 08:00 | 2012-12-25 17:00 | 2012-11-20 08:00 | 2012-12-25 17:00 | 2013-01-12 08:00 | 2013-02-16 17:00 |  | PT_Normal |  |  |  |  | nHXFMgGZRcyJIuptQa3QYA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43530 |  |  |  |  | DRAFTMAN SK | J320 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28630 | N | N | L30 | PACKAGE-2 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11; period 2: 2012-AP12 |  | 50 | DRAFTMAN SK
%R | 499793 | 6359 | 124365 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP020000004030 | Sub & App of Layout Drawings-Temporary Struct. | 8176 | 352 | 0 | 240 | 0 | 100 | 100 | 240 | 0 | 0 | 0 |  |  |  | 2013-02-17 08:00 | 2013-03-23 17:00 |  | 2012-12-26 08:00 | 2013-01-29 17:00 | 2012-12-26 08:00 | 2013-01-29 17:00 | 2012-12-26 08:00 | 2013-01-29 17:00 | 2013-02-17 08:00 | 2013-03-23 17:00 |  | PT_Normal |  |  |  |  | Fk7csKwBTk6UphrXPBPh3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43530 |  |  |  |  | DRAFTMAN SK | J320 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28630 | N | N | L30 | PACKAGE-2 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 50 | DRAFTMAN SK
%R | 499794 | 6359 | 124365 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP020000004040 | Securing Permit To Work | 12516 | 312 | 0 | 160 | 0 | 100 | 100 | 160 | 0 | 0 | 0 |  |  |  | 2013-01-12 08:00 | 2013-02-03 17:00 |  | 2012-11-26 08:00 | 2012-12-19 17:00 | 2012-11-26 08:00 | 2012-12-19 17:00 | 2012-11-26 08:00 | 2012-12-19 17:00 | 2013-01-12 08:00 | 2013-02-03 17:00 |  | PT_Normal |  |  |  |  | iHZsk7XzRqabQrXiG/djOg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [5 empty] | 45402 |  |  |  |  | SAFETY OFFICER | M306 |  | 1 | QT_Hour |  | Y | Y | N | 1 |  | RT_Labor |  |  |  |  | 540 | 28630 | N | N | L30 | PACKAGE-2 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 100 | SAFETY OFFICER
%R | 499795 | 6359 | 124365 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP020000004060 | Establishment of Security Fences & Gates | 8177 | 352 | 352 | 160 | 0 | 300 | 300 | 160 | 0 | 0 | 0 |  |  |  | 2013-03-24 08:00 | 2013-04-15 17:00 |  | 2013-01-30 08:00 | 2013-02-23 17:00 | 2013-01-30 08:00 | 2013-02-23 17:00 | 2013-01-30 08:00 | 2013-02-23 17:00 | 2013-03-24 08:00 | 2013-04-15 17:00 |  | PT_Normal |  |  |  |  | M4wbD0HRSHO5KzAvlu1E4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28630 | N | N | L30 | PACKAGE-2 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 300 | LABOR - CIVIL
%R | 499796 | 6359 | 124365 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP020000004070 | Establishment of Site offices | 8166 | 472 | 472 | 160 | 0 | 700 | 700 | 160 | 0 | 0 | 0 |  |  |  | 2013-02-28 08:00 | 2013-03-23 17:00 |  | 2012-12-20 08:00 | 2013-01-12 17:00 | 2012-12-20 08:00 | 2013-01-12 17:00 | 2012-12-20 08:00 | 2013-01-12 17:00 | 2013-02-28 08:00 | 2013-03-23 17:00 |  | PT_Normal |  |  |  |  | OXe0kD3oTC+Be3SAKur7DQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28630 | N | N | L30 | PACKAGE-2 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 700 | CARPENTERS SK
%R | 499797 | 6359 | 124365 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP020000004080 | Establishment of Labour Mess & Toilets | 8168 | 472 | 472 | 160 | 0 | 371.25 | 371.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-02-28 08:00 | 2013-03-23 17:00 |  | 2012-12-20 08:00 | 2013-01-12 17:00 | 2012-12-20 08:00 | 2013-01-12 17:00 | 2012-12-20 08:00 | 2013-01-12 17:00 | 2013-02-28 08:00 | 2013-03-23 17:00 |  | PT_Normal |  |  |  |  | EeFb7D8uQx+dPexUFqqdcw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28630 | N | N | L30 | PACKAGE-2 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 371.25 | BLOCK MASON SK
%R | 499798 | 6359 | 124365 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP020000004090 | Establishment of Stores & Workshops | 8166 | 472 | 472 | 160 | 0 | 406.25 | 406.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-02-28 08:00 | 2013-03-23 17:00 |  | 2012-12-20 08:00 | 2013-01-12 17:00 | 2012-12-20 08:00 | 2013-01-12 17:00 | 2012-12-20 08:00 | 2013-01-12 17:00 | 2013-02-28 08:00 | 2013-03-23 17:00 |  | PT_Normal |  |  |  |  | 6Qw0WY69RO+TcoGS5UqkJQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28630 | N | N | L30 | PACKAGE-2 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 406.25 | CARPENTERS SK
%R | 499799 | 6359 | 124365 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP020000004050 | Site Cleaning & Leveling Works | 8177 | 312 | 312 | 200 | 0 | 148.69 | 148.69 | 200 | 31.5 | 0 | 31.5 |  |  |  | 2013-01-23 08:00 | 2013-02-21 17:00 |  | 2012-12-08 08:00 | 2013-01-06 17:00 | 2012-12-08 08:00 | 2013-01-06 17:00 | 2012-12-08 08:00 | 2013-01-06 17:00 | 2013-01-23 08:00 | 2013-02-21 17:00 |  | PT_Normal |  |  |  |  | c4t8zjpXQfCrR/+AlOeAhA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28630 | N | N | L30 | PACKAGE-2 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 148.69 | LABOR - CIVIL
%R | 499800 | 6359 | 124366 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP010000004060 | Establishment of Security Fences & Gates | 8177 | 488 | 488 | 160 | 0 | 300 | 300 | 160 | 0 | 0 | 0 |  |  |  | 2013-03-20 08:00 | 2013-04-11 17:00 |  | 2013-01-07 08:00 | 2013-01-29 17:00 | 2013-01-07 08:00 | 2013-01-29 17:00 | 2013-01-07 08:00 | 2013-01-29 17:00 | 2013-03-20 08:00 | 2013-04-11 17:00 |  | PT_Normal |  |  |  |  | TPW8Fre0RWiNyH9+0JlUZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28600 | N | N | L15 | PACKAGE-1 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 300 | LABOR - CIVIL
%R | 499801 | 6359 | 124366 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP010000004070 | Establishment of Site offices | 8166 | 416 | 416 | 160 | 0 | 700 | 700 | 160 | 0 | 0 | 0 |  |  |  | 2013-03-20 08:00 | 2013-04-11 17:00 |  | 2013-01-17 08:00 | 2013-02-09 17:00 | 2013-01-17 08:00 | 2013-02-09 17:00 | 2013-01-17 08:00 | 2013-02-09 17:00 | 2013-03-20 08:00 | 2013-04-11 17:00 |  | PT_Normal |  |  |  |  | Lm0dEQ3JS+qrr1ABpI7TlA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28600 | N | N | L15 | PACKAGE-1 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 700 | CARPENTERS SK
%R | 499802 | 6359 | 124366 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP010000004080 | Establishment of Labour Mess & Toilets | 8168 | 488 | 488 | 160 | 0 | 371.25 | 371.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-03-20 08:00 | 2013-04-11 17:00 |  | 2013-01-07 08:00 | 2013-01-29 17:00 | 2013-01-07 08:00 | 2013-01-29 17:00 | 2013-01-07 08:00 | 2013-01-29 17:00 | 2013-03-20 08:00 | 2013-04-11 17:00 |  | PT_Normal |  |  |  |  | A0QOdTNyRHOX8Y/gJ8yaUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28600 | N | N | L15 | PACKAGE-1 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 371.25 | BLOCK MASON SK
%R | 499803 | 6359 | 124366 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP010000004090 | Establishment of Stores & Workshops | 8166 | 488 | 488 | 160 | 0 | 406.25 | 406.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-03-20 08:00 | 2013-04-11 17:00 |  | 2013-01-07 08:00 | 2013-01-29 17:00 | 2013-01-07 08:00 | 2013-01-29 17:00 | 2013-01-07 08:00 | 2013-01-29 17:00 | 2013-03-20 08:00 | 2013-04-11 17:00 |  | PT_Normal |  |  |  |  | TQZTzGkVTLu2fcQRwoPVwQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28600 | N | N | L15 | PACKAGE-1 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 406.25 | CARPENTERS SK
%R | 499804 | 6359 | 124366 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP010000004050 | Site Cleaning & Leveling Works | 8177 | 296 | 296 | 200 | 0 | 148.69 | 148.69 | 200 | 31.5 | 0 | 31.5 |  |  |  | 2013-02-07 08:00 | 2013-03-09 17:00 |  | 2012-12-26 08:00 | 2013-01-23 17:00 | 2012-12-26 08:00 | 2013-01-23 17:00 | 2012-12-26 08:00 | 2013-01-23 17:00 | 2013-02-07 08:00 | 2013-03-09 17:00 |  | PT_Normal |  |  |  |  | J/fH5xrcR2WwdTKGBDtzZg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28600 | N | N | L15 | PACKAGE-1 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 148.69 | LABOR - CIVIL
%R | 499805 | 6359 | 124366 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP010000004000 | Securing Gate Passes/Access Permit & Courses | 12516 | 0 | 0 | 200 | 0 | 100 | 100 | 200 | 0 | 0 | 0 |  |  |  | 2012-11-01 08:00 | 2012-11-29 17:00 |  | 2012-11-01 08:00 | 2012-11-29 17:00 | 2012-11-01 08:00 | 2012-11-29 17:00 | 2012-11-01 08:00 | 2012-11-29 17:00 | 2012-11-01 08:00 | 2012-11-29 17:00 |  | PT_Normal |  |  |  |  | wARin3HnSUGHtzD4ROCUTw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [5 empty] | 45402 |  |  |  |  | SAFETY OFFICER | M306 |  | 1 | QT_Hour |  | Y | Y | N | 1 |  | RT_Labor |  |  |  |  | 540 | 28600 | N | N | L15 | PACKAGE-1 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 100 | SAFETY OFFICER
%R | 499806 | 6359 | 124366 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP010000004010 | Sub & Approval of Site Logistic Plan | 8176 | 296 | 0 | 240 | 0 | 100 | 100 | 240 | 0 | 0 | 0 |  |  |  | 2012-12-23 08:00 | 2013-01-26 17:00 |  | 2012-11-08 08:00 | 2012-12-12 17:00 | 2012-11-08 08:00 | 2012-12-12 17:00 | 2012-11-08 08:00 | 2012-12-12 17:00 | 2012-12-23 08:00 | 2013-01-26 17:00 |  | PT_Normal |  |  |  |  | Gy3Fr2/gSja7wlUM8+7rVw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43530 |  |  |  |  | DRAFTMAN SK | J320 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28600 | N | N | L15 | PACKAGE-1 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11; period 2: 2012-AP12 |  | 50 | DRAFTMAN SK
%R | 499807 | 6359 | 124366 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP010000004020 | Sub & App of Method Statement-Temporary Struct. | 12515 | 336 | 0 | 240 | 0 | 100 | 100 | 240 | 0 | 0 | 0 |  |  |  | 2013-01-26 08:00 | 2013-03-02 17:00 |  | 2012-12-06 08:00 | 2013-01-10 17:00 | 2012-12-06 08:00 | 2013-01-10 17:00 | 2012-12-06 08:00 | 2013-01-10 17:00 | 2013-01-26 08:00 | 2013-03-02 17:00 |  | PT_Normal |  |  |  |  | AdXrhxeaQCWCyuxA0kmVJw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [5 empty] | 45403 |  |  |  |  | QUANTITY SURVEYOUR | M305 |  | 1 | QT_Hour |  | Y | Y | N | 1 |  | RT_Labor |  |  |  |  | 540 | 28600 | N | N | L15 | PACKAGE-1 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 50 | QUANTITY SURVEYOUR
%R | 499808 | 6359 | 124366 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP010000004030 | Sub & App of Layout Drawings-Temporary Struct. | 8176 | 416 | 0 | 240 | 0 | 100 | 100 | 240 | 0 | 0 | 0 |  |  |  | 2013-02-13 08:00 | 2013-03-19 17:00 |  | 2012-12-12 08:00 | 2013-01-16 17:00 | 2012-12-12 08:00 | 2013-01-16 17:00 | 2012-12-12 08:00 | 2013-01-16 17:00 | 2013-02-13 08:00 | 2013-03-19 17:00 |  | PT_Normal |  |  |  |  | bbgzm3mSQBGt6ohvnU39cg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43530 |  |  |  |  | DRAFTMAN SK | J320 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28600 | N | N | L15 | PACKAGE-1 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 50 | DRAFTMAN SK
%R | 499809 | 6359 | 124366 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP010000004040 | Securing Permit To Work | 12516 | 296 | 0 | 160 | 0 | 100 | 100 | 160 | 0 | 0 | 0 |  |  |  | 2013-01-27 08:00 | 2013-02-19 17:00 |  | 2012-12-13 08:00 | 2013-01-06 17:00 | 2012-12-13 08:00 | 2013-01-06 17:00 | 2012-12-13 08:00 | 2013-01-06 17:00 | 2013-01-27 08:00 | 2013-02-19 17:00 |  | PT_Normal |  |  |  |  | w+mEqGIIRyWNyjdQYRTdeA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [5 empty] | 45402 |  |  |  |  | SAFETY OFFICER | M306 |  | 1 | QT_Hour |  | Y | Y | N | 1 |  | RT_Labor |  |  |  |  | 540 | 28600 | N | N | L15 | PACKAGE-1 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 100 | SAFETY OFFICER
%R | 499810 | 6359 | 124367 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP030000004010 | Sub & Approval of Site Logistic Plan | 8176 | 192 | 0 | 240 | 0 | 100 | 100 | 240 | 0 | 0 | 0 |  |  |  | 2012-12-08 08:00 | 2013-01-12 17:00 |  | 2012-11-10 08:00 | 2012-12-13 17:00 | 2012-11-10 08:00 | 2012-12-13 17:00 | 2012-11-10 08:00 | 2012-12-13 17:00 | 2012-12-08 08:00 | 2013-01-12 17:00 |  | PT_Normal |  |  |  |  | R/tQfH0SQhK9ssH1ykvfEQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43530 |  |  |  |  | DRAFTMAN SK | J320 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28660 | N | N | L45 | PACKAGE-3 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11; period 2: 2012-AP12 |  | 50 | DRAFTMAN SK
%R | 499811 | 6359 | 124367 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP030000004020 | Sub & App of Method Statement-Temporary Struct. | 8176 | 496 | 0 | 240 | 0 | 100 | 100 | 240 | 0 | 0 | 0 |  |  |  | 2013-01-29 08:00 | 2013-03-05 17:00 |  | 2012-11-17 08:00 | 2012-12-22 17:00 | 2012-11-17 08:00 | 2012-12-22 17:00 | 2012-11-17 08:00 | 2012-12-22 17:00 | 2013-01-29 08:00 | 2013-03-05 17:00 |  | PT_Normal |  |  |  |  | CBOYGxNST+2+4MWz6b6IBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43530 |  |  |  |  | DRAFTMAN SK | J320 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28660 | N | N | L45 | PACKAGE-3 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11; period 2: 2012-AP12 |  | 50 | DRAFTMAN SK
%R | 499812 | 6359 | 124367 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP030000004030 | Sub & App of Layout Drawings-Temporary Struct. | 8176 | 496 | 112 | 240 | 0 | 100 | 100 | 240 | 0 | 0 | 0 |  |  |  | 2013-01-29 08:00 | 2013-03-05 17:00 |  | 2012-11-17 08:00 | 2012-12-22 17:00 | 2012-11-17 08:00 | 2012-12-22 17:00 | 2012-11-17 08:00 | 2012-12-22 17:00 | 2013-01-29 08:00 | 2013-03-05 17:00 |  | PT_Normal |  |  |  |  | Z0uC7CjhQ6m/PUG1TawSNw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43530 |  |  |  |  | DRAFTMAN SK | J320 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28660 | N | N | L45 | PACKAGE-3 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11; period 2: 2012-AP12 |  | 50 | DRAFTMAN SK
%R | 499813 | 6359 | 124367 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP030000004040 | Securing Permit To Work | 12516 | 192 | 0 | 160 | 0 | 100 | 100 | 160 | 0 | 0 | 0 |  |  |  | 2013-01-13 08:00 | 2013-02-04 17:00 |  | 2012-12-15 08:00 | 2013-01-07 17:00 | 2012-12-15 08:00 | 2013-01-07 17:00 | 2012-12-15 08:00 | 2013-01-07 17:00 | 2013-01-13 08:00 | 2013-02-04 17:00 |  | PT_Normal |  |  |  |  | zfwuuPD3QZWywWaLm4JW1w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [5 empty] | 45402 |  |  |  |  | SAFETY OFFICER | M306 |  | 1 | QT_Hour |  | Y | Y | N | 1 |  | RT_Labor |  |  |  |  | 540 | 28660 | N | N | L45 | PACKAGE-3 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 100 | SAFETY OFFICER
%R | 499814 | 6359 | 124367 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP030000004060 | Establishment of Security Fences & Gates | 8177 | 384 | 384 | 160 | 0 | 300 | 300 | 160 | 0 | 0 | 0 |  |  |  | 2013-03-06 08:00 | 2013-03-28 17:00 |  | 2013-01-08 08:00 | 2013-01-30 17:00 | 2013-01-08 08:00 | 2013-01-30 17:00 | 2013-01-08 08:00 | 2013-01-30 17:00 | 2013-03-06 08:00 | 2013-03-28 17:00 |  | PT_Normal |  |  |  |  | uwiUCQPzR3yErMJoGrID9Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28660 | N | N | L45 | PACKAGE-3 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 300 | LABOR - CIVIL
%R | 499815 | 6359 | 124367 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP030000004070 | Establishment of Site offices | 8166 | 384 | 384 | 160 | 0 | 700 | 700 | 160 | 0 | 0 | 0 |  |  |  | 2013-03-06 08:00 | 2013-03-28 17:00 |  | 2013-01-08 08:00 | 2013-01-30 17:00 | 2013-01-08 08:00 | 2013-01-30 17:00 | 2013-01-08 08:00 | 2013-01-30 17:00 | 2013-03-06 08:00 | 2013-03-28 17:00 |  | PT_Normal |  |  |  |  | prBMPP/FTx+6UHO6LC2IAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28660 | N | N | L45 | PACKAGE-3 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 700 | CARPENTERS SK
%R | 499816 | 6359 | 124367 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP030000004090 | Establishment of Stores & Workshops | 8166 | 224 | 224 | 160 | 0 | 406.25 | 406.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-02-10 08:00 | 2013-03-05 17:00 |  | 2013-01-08 08:00 | 2013-01-30 17:00 | 2013-01-08 08:00 | 2013-01-30 17:00 | 2013-01-08 08:00 | 2013-01-30 17:00 | 2013-02-10 08:00 | 2013-03-05 17:00 |  | PT_Normal |  |  |  |  | /+hp9TcFSL2TisNvH6jkVQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28660 | N | N | L45 | PACKAGE-3 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 406.25 | CARPENTERS SK
%R | 499817 | 6359 | 124367 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP030000004050 | Site Cleaning & Leveling Works | 8177 | 192 | 192 | 200 | 0 | 148.69 | 148.69 | 200 | 31.5 | 0 | 31.5 |  |  |  | 2013-01-17 08:00 | 2013-02-16 17:00 |  | 2012-12-20 08:00 | 2013-01-17 17:00 | 2012-12-20 08:00 | 2013-01-17 17:00 | 2012-12-20 08:00 | 2013-01-17 17:00 | 2013-01-17 08:00 | 2013-02-16 17:00 |  | PT_Normal |  |  |  |  | vY4RdM4iQFKpT1sUAaTbbQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28660 | N | N | L45 | PACKAGE-3 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 148.69 | LABOR - CIVIL
%R | 499818 | 6359 | 124367 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP030000004080 | Establishment of Labour Mess & Toilets | 8168 | 384 | 384 | 160 | 0 | 371.25 | 371.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-03-06 08:00 | 2013-03-28 17:00 |  | 2013-01-08 08:00 | 2013-01-30 17:00 | 2013-01-08 08:00 | 2013-01-30 17:00 | 2013-01-08 08:00 | 2013-01-30 17:00 | 2013-03-06 08:00 | 2013-03-28 17:00 |  | PT_Normal |  |  |  |  | eJV2+nZnRHKFzobAR1FvaA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 28660 | N | N | L45 | PACKAGE-3 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 371.25 | BLOCK MASON SK
%R | 499819 | 6359 | 124367 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHMOBP030000004000 | Securing Gate Passes/Access Permit & Courses | 12516 | 0 | 0 | 200 | 0 | 100 | 100 | 200 | 0 | 0 | 0 |  |  |  | 2012-11-01 08:00 | 2012-11-29 17:00 |  | 2012-11-01 08:00 | 2012-11-29 17:00 | 2012-11-01 08:00 | 2012-11-29 17:00 | 2012-11-01 08:00 | 2012-11-29 17:00 | 2012-11-01 08:00 | 2012-11-29 17:00 |  | PT_Normal |  |  |  |  | 6ZSF96fXQvOv0rdxKjuCPw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [5 empty] | 45402 |  |  |  |  | SAFETY OFFICER | M306 |  | 1 | QT_Hour |  | Y | Y | N | 1 |  | RT_Labor |  |  |  |  | 540 | 28660 | N | N | L45 | PACKAGE-3 |  | 124352 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 100 | SAFETY OFFICER
%R | 499820 | 6359 | 124370 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP1040 | MEPD_Prequa. 1st App. |  | 32 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2012-12-02 08:00 | 2013-01-06 17:00 |  | 2012-11-27 08:00 | 2013-01-01 17:00 | 2012-11-27 08:00 | 2013-01-01 17:00 | 2012-11-27 08:00 | 2013-01-01 17:00 | 2012-12-02 08:00 | 2013-01-06 17:00 |  | PT_Normal |  |  |  |  | cBK61wD7TF+VAjuytiCdFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29590 | N | N | 15 | 1ST APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11; period 2: 2012-AP12 |  | 0 | 0
%R | 499821 | 6359 | 124370 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP1000 | Anti Termite Treatment_Prequa. 1st App. |  | 360 | 0 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 |  |  |  | 2013-01-02 08:00 | 2013-01-19 17:00 |  | 2012-11-10 08:00 | 2012-11-26 17:00 | 2012-11-10 08:00 | 2012-11-26 17:00 | 2012-11-10 08:00 | 2012-11-26 17:00 | 2013-01-02 08:00 | 2013-01-19 17:00 |  | PT_Normal |  |  |  |  | qHpZpgQ0QCe2xjNFAhLE+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29590 | N | N | 15 | 1ST APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499822 | 6359 | 124370 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP1010 | Concrete_Prequa. 1st App. |  | 312 | 0 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 |  |  |  | 2012-12-27 08:00 | 2013-01-13 17:00 |  | 2012-11-11 08:00 | 2012-11-27 17:00 | 2012-11-11 08:00 | 2012-11-27 17:00 | 2012-11-11 08:00 | 2012-11-27 17:00 | 2012-12-27 08:00 | 2013-01-13 17:00 |  | PT_Normal |  |  |  |  | c5o8SpVjQlis5yesYuFJVQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29590 | N | N | 15 | 1ST APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499823 | 6359 | 124370 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP1020 | Waterproofing -Wet Area _Prequa. 1st App. |  | 304 | 0 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 |  |  |  | 2013-01-12 08:00 | 2013-01-28 17:00 |  | 2012-11-27 08:00 | 2012-12-13 17:00 | 2012-11-27 08:00 | 2012-12-13 17:00 | 2012-11-27 08:00 | 2012-12-13 17:00 | 2013-01-12 08:00 | 2013-01-28 17:00 |  | PT_Normal |  |  |  |  | hygnP707TMi8oK6BZREWIA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29590 | N | N | 15 | 1ST APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499824 | 6359 | 124370 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP1030 | Waterproofing -Roof_Prequa. 1st App. |  | 304 | 0 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 |  |  |  | 2013-01-12 08:00 | 2013-01-28 17:00 |  | 2012-11-27 08:00 | 2012-12-13 17:00 | 2012-11-27 08:00 | 2012-12-13 17:00 | 2012-11-27 08:00 | 2012-12-13 17:00 | 2013-01-12 08:00 | 2013-01-28 17:00 |  | PT_Normal |  |  |  |  | iW+NByfHSdqXlybvA7Uk2A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29590 | N | N | 15 | 1ST APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 0 | 0
%R | 499825 | 6359 | 124370 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP1070 | Wooden Doors_Prequa. 1st App. |  | 208 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-01-27 08:00 | 2013-03-03 17:00 |  | 2012-12-27 08:00 | 2013-01-30 17:00 | 2012-12-27 08:00 | 2013-01-30 17:00 | 2012-12-27 08:00 | 2013-01-30 17:00 | 2013-01-27 08:00 | 2013-03-03 17:00 |  | PT_Normal |  |  |  |  | TiQnNwDuQ+S2kNnNehljjA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29590 | N | N | 15 | 1ST APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499826 | 6359 | 124370 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP1150 | Carpentry & Joinery Works_Prequa. 1st App. |  | 344 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-03-06 08:00 | 2013-04-09 17:00 |  | 2013-01-14 08:00 | 2013-02-18 17:00 | 2013-01-14 08:00 | 2013-02-18 17:00 | 2013-01-14 08:00 | 2013-02-18 17:00 | 2013-03-06 08:00 | 2013-04-09 17:00 |  | PT_Normal |  |  |  |  | GsS892mORSGRvCTOVInXhQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29590 | N | N | 15 | 1ST APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499827 | 6359 | 124370 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP1080 | Aluminum Doors & Windows_Prequa. 1st App. |  | 208 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-01-27 08:00 | 2013-03-03 17:00 |  | 2012-12-27 08:00 | 2013-01-30 17:00 | 2012-12-27 08:00 | 2013-01-30 17:00 | 2012-12-27 08:00 | 2013-01-30 17:00 | 2013-01-27 08:00 | 2013-03-03 17:00 |  | PT_Normal |  |  |  |  | tNRqvh56RsqOezmRGLOatA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29590 | N | N | 15 | 1ST APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499828 | 6359 | 124370 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP1090 | Granite_Prequa. 1st App. |  | 368 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-02-20 08:00 | 2013-03-26 17:00 |  | 2012-12-27 08:00 | 2013-01-30 17:00 | 2012-12-27 08:00 | 2013-01-30 17:00 | 2012-12-27 08:00 | 2013-01-30 17:00 | 2013-02-20 08:00 | 2013-03-26 17:00 |  | PT_Normal |  |  |  |  | Ri0+BgcZTmydtEkiMtjOgg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29590 | N | N | 15 | 1ST APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499829 | 6359 | 124370 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP1050 | Ceiling Works_Prequa. 1st App. |  | 80 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2012-12-29 08:00 | 2013-01-31 17:00 |  | 2012-12-16 08:00 | 2013-01-20 17:00 | 2012-12-16 08:00 | 2013-01-20 17:00 | 2012-12-16 08:00 | 2013-01-20 17:00 | 2012-12-29 08:00 | 2013-01-31 17:00 |  | PT_Normal |  |  |  |  | fMfyjUHPSv6pyIoOM/Rv/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29590 | N | N | 15 | 1ST APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499830 | 6359 | 124370 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP1060 | GRC Panels_Prequa. 1st App. |  | 504 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-02-28 08:00 | 2013-04-03 17:00 |  | 2012-12-15 08:00 | 2013-01-19 17:00 | 2012-12-15 08:00 | 2013-01-19 17:00 | 2012-12-15 08:00 | 2013-01-19 17:00 | 2013-02-28 08:00 | 2013-04-03 17:00 |  | PT_Normal |  |  |  |  | rB5fgeUKSn6CBTf4xg9tIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29590 | N | N | 15 | 1ST APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499831 | 6359 | 124370 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP1100 | Roller Shutter_Prequa. 1st App. |  | 232 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-01-27 08:00 | 2013-03-03 17:00 |  | 2012-12-24 08:00 | 2013-01-27 17:00 | 2012-12-24 08:00 | 2013-01-27 17:00 | 2012-12-24 08:00 | 2013-01-27 17:00 | 2013-01-27 08:00 | 2013-03-03 17:00 |  | PT_Normal |  |  |  |  | b0RffBJ9SQidTYhQ98xKMw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29590 | N | N | 15 | 1ST APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 499832 | 6359 | 124370 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP1180 | Road Works _Prequa. 1st App. |  | 176 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-03-13 08:00 | 2013-04-16 17:00 |  | 2013-02-16 08:00 | 2013-03-21 17:00 | 2013-02-16 08:00 | 2013-03-21 17:00 | 2013-02-16 08:00 | 2013-03-21 17:00 | 2013-03-13 08:00 | 2013-04-16 17:00 |  | PT_Normal |  |  |  |  | dXkmhGCsQNmUtQEXArRVkQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29590 | N | N | 15 | 1ST APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499833 | 6359 | 124370 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP1110 | Structural Steel works_Prequa. 1st App. |  | 320 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-02-27 08:00 | 2013-04-02 17:00 |  | 2013-01-10 08:00 | 2013-02-14 17:00 | 2013-01-10 08:00 | 2013-02-14 17:00 | 2013-01-10 08:00 | 2013-02-14 17:00 | 2013-02-27 08:00 | 2013-04-02 17:00 |  | PT_Normal |  |  |  |  | 1Nx4n0jmQsifUnMSYmQ4Ag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29590 | N | N | 15 | 1ST APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499834 | 6359 | 124370 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP1120 | Car Parking Shed_Prequa. 1st App. |  | 560 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-03 08:00 | 2013-05-07 17:00 |  | 2013-01-10 08:00 | 2013-02-14 17:00 | 2013-01-10 08:00 | 2013-02-14 17:00 | 2013-01-10 08:00 | 2013-02-14 17:00 | 2013-04-03 08:00 | 2013-05-07 17:00 |  | PT_Normal |  |  |  |  | tl1znwdORgW5SEvhh31Ubw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29590 | N | N | 15 | 1ST APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499835 | 6359 | 124370 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP1160 | Soft landscaping /Irrigation _Prequa. 1st App. |  | 296 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-03-13 08:00 | 2013-04-16 17:00 |  | 2013-01-28 08:00 | 2013-03-04 17:00 | 2013-01-28 08:00 | 2013-03-04 17:00 | 2013-01-28 08:00 | 2013-03-04 17:00 | 2013-03-13 08:00 | 2013-04-16 17:00 |  | PT_Normal |  |  |  |  | QKs/fqsIRZCOnqqIF5OZCA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29590 | N | N | 15 | 1ST APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499836 | 6359 | 124370 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP1170 | Pre-cast Boundary Wall _Prequa. 1st App. |  | 560 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-21 08:00 | 2013-05-25 17:00 |  | 2013-01-28 08:00 | 2013-03-04 17:00 | 2013-01-28 08:00 | 2013-03-04 17:00 | 2013-01-28 08:00 | 2013-03-04 17:00 | 2013-04-21 08:00 | 2013-05-25 17:00 |  | PT_Normal |  |  |  |  | pjyNaT55QN+euZczgzXY5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29590 | N | N | 15 | 1ST APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499837 | 6359 | 124370 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP1130 | Steel Door_Prequa. 1st App. |  | 680 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-21 08:00 | 2013-05-25 17:00 |  | 2013-01-10 08:00 | 2013-02-14 17:00 | 2013-01-10 08:00 | 2013-02-14 17:00 | 2013-01-10 08:00 | 2013-02-14 17:00 | 2013-04-21 08:00 | 2013-05-25 17:00 |  | PT_Normal |  |  |  |  | oLOJYPQkSfmef4V04W7EVg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29590 | N | N | 15 | 1ST APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499838 | 6359 | 124370 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP1140 | PVC Tent_Prequa. 1st App. |  | 224 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-02-13 08:00 | 2013-03-19 17:00 |  | 2013-01-10 08:00 | 2013-02-14 17:00 | 2013-01-10 08:00 | 2013-02-14 17:00 | 2013-01-10 08:00 | 2013-02-14 17:00 | 2013-02-13 08:00 | 2013-03-19 17:00 |  | PT_Normal |  |  |  |  | B193jFb9RS2Rjc7bieYjKg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29590 | N | N | 15 | 1ST APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499839 | 6359 | 124371 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP2070 | Wooden Doors_Prequa. 2nd App. |  | 208 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-03-16 08:00 | 2013-04-18 17:00 |  | 2013-02-13 08:00 | 2013-03-19 17:00 | 2013-02-13 08:00 | 2013-03-19 17:00 | 2013-02-13 08:00 | 2013-03-19 17:00 | 2013-03-16 08:00 | 2013-04-18 17:00 |  | PT_Normal |  |  |  |  | 1zCrdXdnRmioH7vCiqHouA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29610 | N | N | 25 | 2ND APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499840 | 6359 | 124371 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP2150 | Carpentry & Joinery Works_Prequa. 2nd App. |  | 344 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-22 08:00 | 2013-05-26 17:00 |  | 2013-03-03 08:00 | 2013-04-06 17:00 | 2013-03-03 08:00 | 2013-04-06 17:00 | 2013-03-03 08:00 | 2013-04-06 17:00 | 2013-04-22 08:00 | 2013-05-26 17:00 |  | PT_Normal |  |  |  |  | V5DPXN15SoKUu1P5C+jjpA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29610 | N | N | 25 | 2ND APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499841 | 6359 | 124371 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP2080 | Aluminum Doors & Windows_Prequa. 2nd App. |  | 208 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-03-16 08:00 | 2013-04-18 17:00 |  | 2013-02-13 08:00 | 2013-03-19 17:00 | 2013-02-13 08:00 | 2013-03-19 17:00 | 2013-02-13 08:00 | 2013-03-19 17:00 | 2013-03-16 08:00 | 2013-04-18 17:00 |  | PT_Normal |  |  |  |  | dhNbusm+SMKcwtlDCoElsQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29610 | N | N | 25 | 2ND APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499842 | 6359 | 124371 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP2090 | Granite_Prequa. 2nd App. |  | 368 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-08 08:00 | 2013-05-12 17:00 |  | 2013-02-13 08:00 | 2013-03-19 17:00 | 2013-02-13 08:00 | 2013-03-19 17:00 | 2013-02-13 08:00 | 2013-03-19 17:00 | 2013-04-08 08:00 | 2013-05-12 17:00 |  | PT_Normal |  |  |  |  | 4gBzssxrQNeK2aQ6ZRUkcA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29610 | N | N | 25 | 2ND APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499843 | 6359 | 124371 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP2050 | Ceiling Works_Prequa. 2nd App. |  | 80 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-02-19 08:00 | 2013-03-25 17:00 |  | 2013-02-06 08:00 | 2013-03-13 17:00 | 2013-02-06 08:00 | 2013-03-13 17:00 | 2013-02-06 08:00 | 2013-03-13 17:00 | 2013-02-19 08:00 | 2013-03-25 17:00 |  | PT_Normal |  |  |  |  | sc/AfN15TfKVqjaE2pzsJQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29610 | N | N | 25 | 2ND APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499844 | 6359 | 124371 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP2060 | GRC Panels_Prequa. 2nd App. |  | 504 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-16 08:00 | 2013-05-20 17:00 |  | 2013-01-31 08:00 | 2013-03-07 17:00 | 2013-01-31 08:00 | 2013-03-07 17:00 | 2013-01-31 08:00 | 2013-03-07 17:00 | 2013-04-16 08:00 | 2013-05-20 17:00 |  | PT_Normal |  |  |  |  | a25T1+4oSmiAGBqix7Na8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29610 | N | N | 25 | 2ND APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP03 |  | 0 | 0
%R | 499845 | 6359 | 124371 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP2100 | Roller Shutter_Prequa. 2nd App. |  | 232 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-03-16 08:00 | 2013-04-18 17:00 |  | 2013-02-09 08:00 | 2013-03-16 17:00 | 2013-02-09 08:00 | 2013-03-16 17:00 | 2013-02-09 08:00 | 2013-03-16 17:00 | 2013-03-16 08:00 | 2013-04-18 17:00 |  | PT_Normal |  |  |  |  | ctid1VCtQkCgB0YnbRkolA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29610 | N | N | 25 | 2ND APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499846 | 6359 | 124371 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP2180 | Road Works _Prequa. 2nd App. |  | 176 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-29 08:00 | 2013-06-02 17:00 |  | 2013-04-03 08:00 | 2013-05-07 17:00 | 2013-04-03 08:00 | 2013-05-07 17:00 | 2013-04-03 08:00 | 2013-05-07 17:00 | 2013-04-29 08:00 | 2013-06-02 17:00 |  | PT_Normal |  |  |  |  | XVZqivyASZqrgLirS2d6Ig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29610 | N | N | 25 | 2ND APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499847 | 6359 | 124371 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP2110 | Structural Steel works_Prequa. 2nd App. |  | 320 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-15 08:00 | 2013-05-19 17:00 |  | 2013-02-27 08:00 | 2013-04-02 17:00 | 2013-02-27 08:00 | 2013-04-02 17:00 | 2013-02-27 08:00 | 2013-04-02 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 |  | PT_Normal |  |  |  |  | 0qZrMYeZSWydm6P1BjcmNw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29610 | N | N | 25 | 2ND APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499848 | 6359 | 124371 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP2120 | Car Parking Shed_Prequa. 2nd App. |  | 560 | 240 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-20 08:00 | 2013-06-23 17:00 |  | 2013-02-27 08:00 | 2013-04-02 17:00 | 2013-02-27 08:00 | 2013-04-02 17:00 | 2013-02-27 08:00 | 2013-04-02 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | CBUkRDYjRFSyqaja3CSASw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29610 | N | N | 25 | 2ND APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499849 | 6359 | 124371 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP2160 | Soft landscaping /Irrigation _Prequa. 2nd App. |  | 296 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-29 08:00 | 2013-06-02 17:00 |  | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-04-29 08:00 | 2013-06-02 17:00 |  | PT_Normal |  |  |  |  | o74M114SRrqt60nZ9skthw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29610 | N | N | 25 | 2ND APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499850 | 6359 | 124371 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP2170 | Pre-cast Boundary Wall _Prequa. 2nd App. |  | 560 | 240 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-07-10 17:00 |  | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-03-17 08:00 | 2013-04-20 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 |  | PT_Normal |  |  |  |  | FYAKtstCReyedaMKeIvvOw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29610 | N | N | 25 | 2ND APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 499851 | 6359 | 124371 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP2130 | Steel Door_Prequa. 2nd App. |  | 680 | 360 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-07-10 17:00 |  | 2013-02-27 08:00 | 2013-04-02 17:00 | 2013-02-27 08:00 | 2013-04-02 17:00 | 2013-02-27 08:00 | 2013-04-02 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 |  | PT_Normal |  |  |  |  | xIXyO10BQdmXVrgdmx8jTw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29610 | N | N | 25 | 2ND APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499852 | 6359 | 124371 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP2140 | PVC Tent_Prequa. 2nd App. |  | 224 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-01 08:00 | 2013-05-05 17:00 |  | 2013-02-27 08:00 | 2013-04-02 17:00 | 2013-02-27 08:00 | 2013-04-02 17:00 | 2013-02-27 08:00 | 2013-04-02 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 |  | PT_Normal |  |  |  |  | 85ZO41dQTR6D27reQX09Ig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29610 | N | N | 25 | 2ND APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499853 | 6359 | 124371 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQAP2040 | MEPD_Prequa. 2nd App. |  | 32 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-01-21 08:00 | 2013-02-25 17:00 |  | 2013-01-16 08:00 | 2013-02-20 17:00 | 2013-01-16 08:00 | 2013-02-20 17:00 | 2013-01-16 08:00 | 2013-02-20 17:00 | 2013-01-21 08:00 | 2013-02-25 17:00 |  | PT_Normal |  |  |  |  | 5m3dpAJkQKqvXDws1iWFyQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29610 | N | N | 25 | 2ND APPROVAL OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 499854 | 6359 | 124372 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM1000 | Anti Termite Treatment_Prequa. 1st Sub. | 11918 | 32 | 0 | 56 | 0 | 14 | 14 | 56 | 0 | 0 | 0 |  |  |  | 2012-11-06 08:00 | 2012-11-13 17:00 |  | 2012-11-01 08:00 | 2012-11-08 17:00 | 2012-11-01 08:00 | 2012-11-08 17:00 | 2012-11-01 08:00 | 2012-11-08 17:00 | 2012-11-06 08:00 | 2012-11-13 17:00 |  | PT_Normal |  |  |  |  | 0pecTXKuThCysn6J4pcnOw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:35 | admin | admin | [5 empty] | 45404 |  |  |  |  | MATERIAL ENGG | M304 |  | 1 | QT_Hour |  | Y | Y | N | 1 |  | RT_Labor |  |  |  |  | 540 | 29580 | N | N | 10 | 1ST SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 14 | MATERIAL ENGG
%R | 499855 | 6359 | 124372 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM1010 | Concrete_Prequa. 1st Sub. | 11918 | 32 | 0 | 64 | 0 | 16 | 16 | 64 | 0 | 0 | 0 |  |  |  | 2012-11-06 08:00 | 2012-11-14 17:00 |  | 2012-11-01 08:00 | 2012-11-10 17:00 | 2012-11-01 08:00 | 2012-11-10 17:00 | 2012-11-01 08:00 | 2012-11-10 17:00 | 2012-11-06 08:00 | 2012-11-14 17:00 |  | PT_Normal |  |  |  |  | GiQc8FCeTM6nKUAL3QQJvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:35 | admin | admin | [5 empty] | 45404 |  |  |  |  | MATERIAL ENGG | M304 |  | 1 | QT_Hour |  | Y | Y | N | 1 |  | RT_Labor |  |  |  |  | 540 | 29580 | N | N | 10 | 1ST SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 16 | MATERIAL ENGG
%R | 499856 | 6359 | 124372 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM1020 | Waterproofing -Wet Area _Prequa. 1st Sub. | 11918 | 80 | 0 | 112 | 0 | 28 | 28 | 112 | 0 | 0 | 0 |  |  |  | 2012-11-22 08:00 | 2012-12-08 17:00 |  | 2012-11-11 08:00 | 2012-11-26 17:00 | 2012-11-11 08:00 | 2012-11-26 17:00 | 2012-11-11 08:00 | 2012-11-26 17:00 | 2012-11-22 08:00 | 2012-12-08 17:00 |  | PT_Normal |  |  |  |  | e8i4ZaTEQNaPwJaZejSeqA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [5 empty] | 45404 |  |  |  |  | MATERIAL ENGG | M304 |  | 1 | QT_Hour |  | Y | Y | N | 1 |  | RT_Labor |  |  |  |  | 540 | 29580 | N | N | 10 | 1ST SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 28 | MATERIAL ENGG
%R | 499857 | 6359 | 124372 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM1030 | Waterproofing -Roof_Prequa. 1st Sub. |  | 80 | 0 | 112 | 0 | 28 | 28 | 112 | 0 | 0 | 0 |  |  |  | 2012-11-22 08:00 | 2012-12-08 17:00 |  | 2012-11-11 08:00 | 2012-11-26 17:00 | 2012-11-11 08:00 | 2012-11-26 17:00 | 2012-11-11 08:00 | 2012-11-26 17:00 | 2012-11-22 08:00 | 2012-12-08 17:00 |  | PT_Normal |  |  |  |  | xaNo8x/YQeeTebKLWG+nLQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29580 | N | N | 10 | 1ST SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 28 | 0
%R | 499858 | 6359 | 124372 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM1070 | Wooden Doors_Prequa. 1st Sub. |  | 208 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-01-09 08:00 | 2013-01-26 17:00 |  | 2012-12-09 08:00 | 2012-12-26 17:00 | 2012-12-09 08:00 | 2012-12-26 17:00 | 2012-12-09 08:00 | 2012-12-26 17:00 | 2013-01-09 08:00 | 2013-01-26 17:00 |  | PT_Normal |  |  |  |  | 9i0SXUvKSGqxEFST1hEzOw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29580 | N | N | 10 | 1ST SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499859 | 6359 | 124372 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM1150 | Carpentry & Joinery Works_Prequa. 1st Sub. |  | 344 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-02-17 08:00 | 2013-03-05 17:00 |  | 2012-12-27 08:00 | 2013-01-13 17:00 | 2012-12-27 08:00 | 2013-01-13 17:00 | 2012-12-27 08:00 | 2013-01-13 17:00 | 2013-02-17 08:00 | 2013-03-05 17:00 |  | PT_Normal |  |  |  |  | wUYBPUO+T82KevHz/mugHg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29580 | N | N | 10 | 1ST SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499860 | 6359 | 124372 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM1080 | Aluminum Doors & Windows_Prequa. 1st Sub. |  | 208 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-01-09 08:00 | 2013-01-26 17:00 |  | 2012-12-09 08:00 | 2012-12-26 17:00 | 2012-12-09 08:00 | 2012-12-26 17:00 | 2012-12-09 08:00 | 2012-12-26 17:00 | 2013-01-09 08:00 | 2013-01-26 17:00 |  | PT_Normal |  |  |  |  | D9lvn6i/QW2QzO+b5WQ7gA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29580 | N | N | 10 | 1ST SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499861 | 6359 | 124372 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM1090 | Granite_Prequa. 1st Sub. |  | 368 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-02-02 08:00 | 2013-02-19 17:00 |  | 2012-12-09 08:00 | 2012-12-26 17:00 | 2012-12-09 08:00 | 2012-12-26 17:00 | 2012-12-09 08:00 | 2012-12-26 17:00 | 2013-02-02 08:00 | 2013-02-19 17:00 |  | PT_Normal |  |  |  |  | txApPcAGQ7em3mOukfW9Bw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29580 | N | N | 10 | 1ST SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499862 | 6359 | 124372 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM1050 | Ceiling Works_Prequa. 1st Sub. |  | 80 | 0 | 128 | 0 | 32 | 32 | 128 | 0 | 0 | 0 |  |  |  | 2012-12-09 08:00 | 2012-12-27 17:00 |  | 2012-11-27 08:00 | 2012-12-15 17:00 | 2012-11-27 08:00 | 2012-12-15 17:00 | 2012-11-27 08:00 | 2012-12-15 17:00 | 2012-12-09 08:00 | 2012-12-27 17:00 |  | PT_Normal |  |  |  |  | 5jo+j4sNR0a9D0BB9sr2Bg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29580 | N | N | 10 | 1ST SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 32 | 0
%R | 499863 | 6359 | 124372 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM1060 | GRC Panels_Prequa. 1st Sub. |  | 176 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2012-12-24 08:00 | 2013-01-09 17:00 |  | 2012-11-27 08:00 | 2012-12-13 17:00 | 2012-11-27 08:00 | 2012-12-13 17:00 | 2012-11-27 08:00 | 2012-12-13 17:00 | 2012-12-24 08:00 | 2013-01-09 17:00 |  | PT_Normal |  |  |  |  | I9EWoGbjS/CZ4mydhW3EWQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29580 | N | N | 10 | 1ST SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 30 | 0
%R | 499864 | 6359 | 124372 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM1100 | Roller Shutter_Prequa. 1st Sub. |  | 176 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-01-01 08:00 | 2013-01-17 17:00 |  | 2012-12-05 08:00 | 2012-12-23 17:00 | 2012-12-05 08:00 | 2012-12-23 17:00 | 2012-12-05 08:00 | 2012-12-23 17:00 | 2013-01-01 08:00 | 2013-01-17 17:00 |  | PT_Normal |  |  |  |  | l1D7v2QbQU6e+PlSDvtq3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29580 | N | N | 10 | 1ST SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499865 | 6359 | 124372 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM1180 | Road Works _Prequa. 1st Sub. |  | 176 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-02-24 08:00 | 2013-03-12 17:00 |  | 2013-01-28 08:00 | 2013-02-14 17:00 | 2013-01-28 08:00 | 2013-02-14 17:00 | 2013-01-28 08:00 | 2013-02-14 17:00 | 2013-02-24 08:00 | 2013-03-12 17:00 |  | PT_Normal |  |  |  |  | 4tuM0s6/RJGVaNA2YHRtJg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29580 | N | N | 10 | 1ST SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499866 | 6359 | 124372 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM1110 | Structural Steel works_Prequa. 1st Sub. |  | 176 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-01-19 08:00 | 2013-02-04 17:00 |  | 2012-12-24 08:00 | 2013-01-09 17:00 | 2012-12-24 08:00 | 2013-01-09 17:00 | 2012-12-24 08:00 | 2013-01-09 17:00 | 2013-01-19 08:00 | 2013-02-04 17:00 |  | PT_Normal |  |  |  |  | Qf0bo65zQrGD7vIKfKsVpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29580 | N | N | 10 | 1ST SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499867 | 6359 | 124372 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM1120 | Car Parking Shed_Prequa. 1st Sub. |  | 176 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-01-19 08:00 | 2013-02-04 17:00 |  | 2012-12-24 08:00 | 2013-01-09 17:00 | 2012-12-24 08:00 | 2013-01-09 17:00 | 2012-12-24 08:00 | 2013-01-09 17:00 | 2013-01-19 08:00 | 2013-02-04 17:00 |  | PT_Normal |  |  |  |  | ilnjxFq6QO2gGM0bQ6nG0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29580 | N | N | 10 | 1ST SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499868 | 6359 | 124372 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM1160 | Soft landscaping /Irrigation _Prequa. 1st Sub. |  | 176 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-02-05 08:00 | 2013-02-23 17:00 |  | 2013-01-10 08:00 | 2013-01-27 17:00 | 2013-01-10 08:00 | 2013-01-27 17:00 | 2013-01-10 08:00 | 2013-01-27 17:00 | 2013-02-05 08:00 | 2013-02-23 17:00 |  | PT_Normal |  |  |  |  | kkOy/lcRQOGEb5xZiNFWNg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29580 | N | N | 10 | 1ST SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499869 | 6359 | 124372 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM1170 | Pre-cast Boundary Wall _Prequa. 1st Sub. |  | 560 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-03 08:00 | 2013-04-20 17:00 |  | 2013-01-10 08:00 | 2013-01-27 17:00 | 2013-01-10 08:00 | 2013-01-27 17:00 | 2013-01-10 08:00 | 2013-01-27 17:00 | 2013-04-03 08:00 | 2013-04-20 17:00 |  | PT_Normal |  |  |  |  | QJBDZA6CRwKZVtVenir1gQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29580 | N | N | 10 | 1ST SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499870 | 6359 | 124372 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM1130 | Steel Door_Prequa. 1st Sub. |  | 680 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-03 08:00 | 2013-04-20 17:00 |  | 2012-12-24 08:00 | 2013-01-09 17:00 | 2012-12-24 08:00 | 2013-01-09 17:00 | 2012-12-24 08:00 | 2013-01-09 17:00 | 2013-04-03 08:00 | 2013-04-20 17:00 |  | PT_Normal |  |  |  |  | 5cXkRsZKR1+eOHhkPHpWqA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29580 | N | N | 10 | 1ST SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499871 | 6359 | 124372 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM1140 | PVC Tent_Prequa. 1st Sub. |  | 224 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-01-26 08:00 | 2013-02-11 17:00 |  | 2012-12-24 08:00 | 2013-01-09 17:00 | 2012-12-24 08:00 | 2013-01-09 17:00 | 2012-12-24 08:00 | 2013-01-09 17:00 | 2013-01-26 08:00 | 2013-02-11 17:00 |  | PT_Normal |  |  |  |  | GY7IXbPLTTK/eEzDxc9ruw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29580 | N | N | 10 | 1ST SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 499872 | 6359 | 124372 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM1040 | MEPD_Prequa. 1st Sub. |  | 32 | 0 | 112 | 0 | 28 | 28 | 112 | 0 | 0 | 0 |  |  |  | 2012-11-15 08:00 | 2012-12-01 17:00 |  | 2012-11-11 08:00 | 2012-11-26 17:00 | 2012-11-11 08:00 | 2012-11-26 17:00 | 2012-11-11 08:00 | 2012-11-26 17:00 | 2012-11-15 08:00 | 2012-12-01 17:00 |  | PT_Normal |  |  |  |  | 4tXW3AuBTnWwHi6JgJ/KBQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29580 | N | N | 10 | 1ST SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 28 | 0
%R | 499873 | 6359 | 124373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM2070 | Wooden Doors_Prequa. 2nd Sub. |  | 208 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-03-04 08:00 | 2013-03-14 17:00 |  | 2013-01-31 08:00 | 2013-02-11 17:00 | 2013-01-31 08:00 | 2013-02-11 17:00 | 2013-01-31 08:00 | 2013-02-11 17:00 | 2013-03-04 08:00 | 2013-03-14 17:00 |  | PT_Normal |  |  |  |  | CbVZW7DiR6qNOUk8ibiAeg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29600 | N | N | 20 | 2ND SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 15 | 0
%R | 499874 | 6359 | 124373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM2150 | Carpentry & Joinery Works_Prequa. 2nd Sub. |  | 344 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-04-10 08:00 | 2013-04-21 17:00 |  | 2013-02-19 08:00 | 2013-03-02 17:00 | 2013-02-19 08:00 | 2013-03-02 17:00 | 2013-02-19 08:00 | 2013-03-02 17:00 | 2013-04-10 08:00 | 2013-04-21 17:00 |  | PT_Normal |  |  |  |  | dIjlcmGdQKyc0+IZS1Y+9A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29600 | N | N | 20 | 2ND SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 15 | 0
%R | 499875 | 6359 | 124373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM2080 | Aluminum Doors & Windows_Prequa. 2nd Sub. |  | 208 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-03-04 08:00 | 2013-03-14 17:00 |  | 2013-01-31 08:00 | 2013-02-11 17:00 | 2013-01-31 08:00 | 2013-02-11 17:00 | 2013-01-31 08:00 | 2013-02-11 17:00 | 2013-03-04 08:00 | 2013-03-14 17:00 |  | PT_Normal |  |  |  |  | W7jWMjQ8TxqKNBFaA7LOYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29600 | N | N | 20 | 2ND SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 15 | 0
%R | 499876 | 6359 | 124373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM2090 | Granite_Prequa. 2nd Sub. |  | 368 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-03-27 08:00 | 2013-04-07 17:00 |  | 2013-01-31 08:00 | 2013-02-11 17:00 | 2013-01-31 08:00 | 2013-02-11 17:00 | 2013-01-31 08:00 | 2013-02-11 17:00 | 2013-03-27 08:00 | 2013-04-07 17:00 |  | PT_Normal |  |  |  |  | uY6svZ/ATIes22INlSgUlQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29600 | N | N | 20 | 2ND SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 15 | 0
%R | 499877 | 6359 | 124373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM2050 | Ceiling Works_Prequa. 2nd Sub. |  | 80 | 0 | 112 | 0 | 21 | 21 | 112 | 0 | 0 | 0 |  |  |  | 2013-02-02 08:00 | 2013-02-18 17:00 |  | 2013-01-21 08:00 | 2013-02-05 17:00 | 2013-01-21 08:00 | 2013-02-05 17:00 | 2013-01-21 08:00 | 2013-02-05 17:00 | 2013-02-02 08:00 | 2013-02-18 17:00 |  | PT_Normal |  |  |  |  | 321Xi0rbR3u/GYc0He3R6g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29600 | N | N | 20 | 2ND SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 21 | 0
%R | 499878 | 6359 | 124373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM2060 | GRC Panels_Prequa. 2nd Sub. |  | 504 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-04-04 08:00 | 2013-04-15 17:00 |  | 2013-01-20 08:00 | 2013-01-30 17:00 | 2013-01-20 08:00 | 2013-01-30 17:00 | 2013-01-20 08:00 | 2013-01-30 17:00 | 2013-04-04 08:00 | 2013-04-15 17:00 |  | PT_Normal |  |  |  |  | MIbNMv6tRpeAfgUNUb5EUQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29600 | N | N | 20 | 2ND SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 15 | 0
%R | 499879 | 6359 | 124373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM2100 | Roller Shutter_Prequa. 2nd Sub. |  | 232 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-03-04 08:00 | 2013-03-14 17:00 |  | 2013-01-28 08:00 | 2013-02-07 17:00 | 2013-01-28 08:00 | 2013-02-07 17:00 | 2013-01-28 08:00 | 2013-02-07 17:00 | 2013-03-04 08:00 | 2013-03-14 17:00 |  | PT_Normal |  |  |  |  | 0Ga+V4cvTLi8qZmBT78XbA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29600 | N | N | 20 | 2ND SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 15 | 0
%R | 499880 | 6359 | 124373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM2180 | Road Works _Prequa. 2nd Sub. |  | 176 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-04-17 08:00 | 2013-04-28 17:00 |  | 2013-03-23 08:00 | 2013-04-02 17:00 | 2013-03-23 08:00 | 2013-04-02 17:00 | 2013-03-23 08:00 | 2013-04-02 17:00 | 2013-04-17 08:00 | 2013-04-28 17:00 |  | PT_Normal |  |  |  |  | dmVo6cq8TMupnS2/mkc/HQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29600 | N | N | 20 | 2ND SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 15 | 0
%R | 499881 | 6359 | 124373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM2110 | Structural Steel works_Prequa. 2nd Sub. |  | 320 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-04-03 08:00 | 2013-04-14 17:00 |  | 2013-02-16 08:00 | 2013-02-26 17:00 | 2013-02-16 08:00 | 2013-02-26 17:00 | 2013-02-16 08:00 | 2013-02-26 17:00 | 2013-04-03 08:00 | 2013-04-14 17:00 |  | PT_Normal |  |  |  |  | zV//qnVWT+6FI7Gl5UDoyQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29600 | N | N | 20 | 2ND SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 15 | 0
%R | 499882 | 6359 | 124373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM2120 | Car Parking Shed_Prequa. 2nd Sub. |  | 560 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-05-08 08:00 | 2013-05-19 17:00 |  | 2013-02-16 08:00 | 2013-02-26 17:00 | 2013-02-16 08:00 | 2013-02-26 17:00 | 2013-02-16 08:00 | 2013-02-26 17:00 | 2013-05-08 08:00 | 2013-05-19 17:00 |  | PT_Normal |  |  |  |  | 8zEvZm41TpS/LRqTBC+prA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29600 | N | N | 20 | 2ND SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 15 | 0
%R | 499883 | 6359 | 124373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM2160 | Soft landscaping /Irrigation _Prequa. 2nd Sub. |  | 296 | 0 | 80 | 0 | 12 | 12 | 80 | 0 | 0 | 0 |  |  |  | 2013-04-17 08:00 | 2013-04-28 17:00 |  | 2013-03-05 08:00 | 2013-03-16 17:00 | 2013-03-05 08:00 | 2013-03-16 17:00 | 2013-03-05 08:00 | 2013-03-16 17:00 | 2013-04-17 08:00 | 2013-04-28 17:00 |  | PT_Normal |  |  |  |  | r4LYV/qeQWGMjGy4DXKsag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29600 | N | N | 20 | 2ND SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 12 | 0
%R | 499884 | 6359 | 124373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM2170 | Pre-cast Boundary Wall _Prequa. 2nd Sub. |  | 560 | 0 | 80 | 0 | 12 | 12 | 80 | 0 | 0 | 0 |  |  |  | 2013-05-26 08:00 | 2013-06-05 17:00 |  | 2013-03-05 08:00 | 2013-03-16 17:00 | 2013-03-05 08:00 | 2013-03-16 17:00 | 2013-03-05 08:00 | 2013-03-16 17:00 | 2013-05-26 08:00 | 2013-06-05 17:00 |  | PT_Normal |  |  |  |  | j6nipW33R2+HwclLGV4Djg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29600 | N | N | 20 | 2ND SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 12 | 0
%R | 499885 | 6359 | 124373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM2130 | Steel Door_Prequa. 2nd Sub. |  | 680 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-05-26 08:00 | 2013-06-05 17:00 |  | 2013-02-16 08:00 | 2013-02-26 17:00 | 2013-02-16 08:00 | 2013-02-26 17:00 | 2013-02-16 08:00 | 2013-02-26 17:00 | 2013-05-26 08:00 | 2013-06-05 17:00 |  | PT_Normal |  |  |  |  | AjC2gIkgRTSunNE53YqzxQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29600 | N | N | 20 | 2ND SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 15 | 0
%R | 499886 | 6359 | 124373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM2140 | PVC Tent_Prequa. 2nd Sub. |  | 224 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-03-20 08:00 | 2013-03-31 17:00 |  | 2013-02-16 08:00 | 2013-02-26 17:00 | 2013-02-16 08:00 | 2013-02-26 17:00 | 2013-02-16 08:00 | 2013-02-26 17:00 | 2013-03-20 08:00 | 2013-03-31 17:00 |  | PT_Normal |  |  |  |  | b9bcPOiITCaCbKbLCmksnw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29600 | N | N | 20 | 2ND SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 15 | 0
%R | 499887 | 6359 | 124373 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PQSM2040 | MEPD_Prequa. 2nd Sub. |  | 32 | 0 | 96 | 0 | 18 | 18 | 96 | 0 | 0 | 0 |  |  |  | 2013-01-07 08:00 | 2013-01-20 17:00 |  | 2013-01-02 08:00 | 2013-01-15 17:00 | 2013-01-02 08:00 | 2013-01-15 17:00 | 2013-01-02 08:00 | 2013-01-15 17:00 | 2013-01-07 08:00 | 2013-01-20 17:00 |  | PT_Normal |  |  |  |  | VoBuPQDARf+TAbobqVjqDw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29600 | N | N | 20 | 2ND SUBMISSION OF PREQUALIFICATION |  | 124369 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 18 | 0
%R | 499888 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3000 | Proc & Del Anti Termite |  | 432 | 432 | 56 | 0 | 0 | 0 | 56 | 0 | 0 | 0 |  |  |  | 2013-02-19 08:00 | 2013-02-25 17:00 |  | 2012-12-27 08:00 | 2013-01-02 17:00 | 2012-12-27 08:00 | 2013-01-02 17:00 | 2012-12-27 08:00 | 2013-01-02 17:00 | 2013-02-19 08:00 | 2013-02-25 17:00 |  | PT_Normal |  |  |  |  | 8Wb7S9GTTV+6+/TstzWrFg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499889 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3020 | Proc & Del Concrete |  | 368 | 368 | 56 | 0 | 0 | 0 | 56 | 0 | 0 | 0 |  |  |  | 2013-02-12 08:00 | 2013-02-18 17:00 |  | 2012-12-28 08:00 | 2013-01-03 17:00 | 2012-12-28 08:00 | 2013-01-03 17:00 | 2012-12-28 08:00 | 2013-01-03 17:00 | 2013-02-12 08:00 | 2013-02-18 17:00 |  | PT_Normal |  |  |  |  | Xt7xHu/7Sum0+Z1YhLGa3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 499890 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3030 | Proc & Del Waterproofing |  | 360 | 360 | 56 | 0 | 0 | 0 | 56 | 0 | 0 | 0 |  |  |  | 2013-02-28 08:00 | 2013-03-06 17:00 |  | 2013-01-14 08:00 | 2013-01-20 17:00 | 2013-01-14 08:00 | 2013-01-20 17:00 | 2013-01-14 08:00 | 2013-01-20 17:00 | 2013-02-28 08:00 | 2013-03-06 17:00 |  | PT_Normal |  |  |  |  | 4uWAzpkSSBW2cvnA0O1nqw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 0 | 0
%R | 499891 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3010 | Proc & Del Block Work |  | 560 | 560 | 80 | 0 | 0 | 0 | 80 | 0 | 0 | 0 |  |  |  | 2013-03-13 08:00 | 2013-03-22 17:00 |  | 2013-01-02 08:00 | 2013-01-11 17:00 | 2013-01-02 08:00 | 2013-01-11 17:00 | 2013-01-02 08:00 | 2013-01-11 17:00 | 2013-03-13 08:00 | 2013-03-22 17:00 |  | PT_Normal |  |  |  |  | fXsxZGT8QEqOUtRWh67eiw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 0 | 0
%R | 499892 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3040 | Proc & Del Plastering & Accessories |  | 784 | 576 | 480 | 0 | 0 | 0 | 480 | 0 | 0 | 0 |  |  |  | 2013-07-19 08:00 | 2013-09-16 17:00 |  | 2013-04-12 08:00 | 2013-06-10 17:00 | 2013-04-12 08:00 | 2013-06-10 17:00 | 2013-04-12 08:00 | 2013-06-10 17:00 | 2013-07-19 08:00 | 2013-09-16 17:00 |  | PT_Normal |  |  |  |  | /LnHX4KXQY6ZoOfPD45ldw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499893 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3050 | Proc & Del Thermal Insulation |  | 1040 | 696 | 480 | 0 | 0 | 0 | 480 | 0 | 0 | 0 |  |  |  | 2013-08-29 08:00 | 2013-10-27 17:00 |  | 2013-04-21 08:00 | 2013-06-19 17:00 | 2013-04-21 08:00 | 2013-06-19 17:00 | 2013-04-21 08:00 | 2013-06-19 17:00 | 2013-08-29 08:00 | 2013-10-27 17:00 |  | PT_Normal |  |  |  |  | FLXiaGN9Qt2t0NtPrPZjXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499894 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3140 | Proc & Del Pitch roofing |  | 840 | 560 | 320 | 0 | 0 | 0 | 320 | 0 | 0 | 0 |  |  |  | 2013-08-13 08:00 | 2013-09-21 17:00 |  | 2013-04-30 08:00 | 2013-06-08 17:00 | 2013-04-30 08:00 | 2013-06-08 17:00 | 2013-04-30 08:00 | 2013-06-08 17:00 | 2013-08-13 08:00 | 2013-09-21 17:00 |  | PT_Normal |  |  |  |  | L0SSzgrYRoey+9qpbcsJuQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 499895 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3490 | Proc & Del Wooden Doors |  | 248 | 16 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-07-22 08:00 | 2013-11-18 17:00 |  | 2013-06-21 08:00 | 2013-10-18 17:00 | 2013-06-21 08:00 | 2013-10-18 17:00 | 2013-06-21 08:00 | 2013-10-18 17:00 | 2013-07-22 08:00 | 2013-11-18 17:00 |  | PT_Normal |  |  |  |  | 0XGijsp8RzGuktC6GD9jhA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08; period 4: 2013-AP09 |  | 0 | 0
%R | 499896 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3440 | Proc & Del PVC Doors |  | 888 | 360 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2014-01-07 17:00 |  | 2013-06-21 08:00 | 2013-09-18 17:00 | 2013-06-21 08:00 | 2013-09-18 17:00 | 2013-06-21 08:00 | 2013-09-18 17:00 | 2013-10-10 08:00 | 2014-01-07 17:00 |  | PT_Normal |  |  |  |  | umqCD0GXTBmoihKz5x/XmQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08 |  | 0 | 0
%R | 499897 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3550 | Proc & Del Closets /wardrobe& Pelmets |  | 432 | 0 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-09-07 08:00 | 2014-01-04 17:00 |  | 2013-07-15 08:00 | 2013-11-11 17:00 | 2013-07-15 08:00 | 2013-11-11 17:00 | 2013-07-15 08:00 | 2013-11-11 17:00 | 2013-09-07 08:00 | 2014-01-04 17:00 |  | PT_Normal |  |  |  |  | cB/Luw1xTCeOmX+AzA6mZg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08; period 3: 2013-AP09; period 4: 2013-AP10 |  | 0 | 0
%R | 499898 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3560 | Proc & Del Counters, Cabinets & Shelves |  | 432 | 0 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-09-07 08:00 | 2014-01-04 17:00 |  | 2013-07-15 08:00 | 2013-11-11 17:00 | 2013-07-15 08:00 | 2013-11-11 17:00 | 2013-07-15 08:00 | 2013-11-11 17:00 | 2013-09-07 08:00 | 2014-01-04 17:00 |  | PT_Normal |  |  |  |  | 2r+YEmVcRP+vFO9+BnjDvg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08; period 3: 2013-AP09; period 4: 2013-AP10 |  | 0 | 0
%R | 499899 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3570 | Proc & Del Wooden Hand Rails |  | 592 | 160 | 800 | 0 | 0 | 0 | 800 | 0 | 0 | 0 |  |  |  | 2013-09-27 08:00 | 2014-01-04 17:00 |  | 2013-07-15 08:00 | 2013-10-22 17:00 | 2013-07-15 08:00 | 2013-10-22 17:00 | 2013-07-15 08:00 | 2013-10-22 17:00 | 2013-09-27 08:00 | 2014-01-04 17:00 |  | PT_Normal |  |  |  |  | n1sGUYCtRvS7lfuyY7qQyg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08; period 3: 2013-AP09; period 4: 2013-AP10 |  | 0 | 0
%R | 499900 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3780 | Proc & Del Gazebo Structure |  | 584 | 368 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-11-25 08:00 | 2014-03-24 17:00 |  | 2013-09-13 08:00 | 2014-01-10 17:00 | 2013-09-13 08:00 | 2014-01-10 17:00 | 2013-09-13 08:00 | 2014-01-10 17:00 | 2013-11-25 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | OuSZO8pJTAqbK6RuPiCQow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10; period 3: 2013-AP11; period 4: 2013-AP12 |  | 0 | 0
%R | 499901 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3450 | Proc & Del Ironmogeries |  | 248 | 16 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-07-22 08:00 | 2013-11-18 17:00 |  | 2013-06-21 08:00 | 2013-10-18 17:00 | 2013-06-21 08:00 | 2013-10-18 17:00 | 2013-06-21 08:00 | 2013-10-18 17:00 | 2013-07-22 08:00 | 2013-11-18 17:00 |  | PT_Normal |  |  |  |  | I+neYZmXR7WiaTP6t55Sww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08; period 4: 2013-AP09 |  | 0 | 0
%R | 499902 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3460 | Proc & Del Aluminum Doors |  | 640 | 120 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-09-09 08:00 | 2014-01-06 17:00 |  | 2013-06-21 08:00 | 2013-10-18 17:00 | 2013-06-21 08:00 | 2013-10-18 17:00 | 2013-06-21 08:00 | 2013-10-18 17:00 | 2013-09-09 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | tC7fTznKQQCMh8H60Iu6oA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08; period 4: 2013-AP09 |  | 0 | 0
%R | 499903 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3470 | Proc & Del Aluminum Windows |  | 696 | 80 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-09-16 08:00 | 2014-01-13 17:00 |  | 2013-06-21 08:00 | 2013-10-18 17:00 | 2013-06-21 08:00 | 2013-10-18 17:00 | 2013-06-21 08:00 | 2013-10-18 17:00 | 2013-09-16 08:00 | 2014-01-13 17:00 |  | PT_Normal |  |  |  |  | L4WQG3tlRLqt+iP6GEAgHA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08; period 4: 2013-AP09 |  | 0 | 0
%R | 499904 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3480 | Proc & Del Granite |  | 464 | 8 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-08-18 08:00 | 2013-12-15 17:00 |  | 2013-06-21 08:00 | 2013-10-18 17:00 | 2013-06-21 08:00 | 2013-10-18 17:00 | 2013-06-21 08:00 | 2013-10-18 17:00 | 2013-08-18 08:00 | 2013-12-15 17:00 |  | PT_Normal |  |  |  |  | ACQS0Rk1Tlq0KoH9pJWlxg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08; period 4: 2013-AP09 |  | 0 | 0
%R | 499905 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3090 | Proc & Del Cobble stone finish |  | 768 | 168 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-08-04 08:00 | 2013-12-01 17:00 |  | 2013-04-30 08:00 | 2013-08-27 17:00 | 2013-04-30 08:00 | 2013-08-27 17:00 | 2013-04-30 08:00 | 2013-08-27 17:00 | 2013-08-04 08:00 | 2013-12-01 17:00 |  | PT_Normal |  |  |  |  | o4II+gWaTC2gE8Q25VGbXQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05; period 3: 2013-AP06; period 4: 2013-AP07 |  | 0 | 0
%R | 499906 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3100 | Proc & Del Slate Tile |  | 816 | 216 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-08-10 08:00 | 2013-12-07 17:00 |  | 2013-04-30 08:00 | 2013-08-27 17:00 | 2013-04-30 08:00 | 2013-08-27 17:00 | 2013-04-30 08:00 | 2013-08-27 17:00 | 2013-08-10 08:00 | 2013-12-07 17:00 |  | PT_Normal |  |  |  |  | OXzv6ylZQZePPHfwsq4dNg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05; period 3: 2013-AP06; period 4: 2013-AP07 |  | 0 | 0
%R | 499907 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3110 | Proc & Del Stone Cladding |  | 1112 | 960 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-08-21 08:00 | 2013-12-18 17:00 |  | 2013-04-04 08:00 | 2013-08-01 17:00 | 2013-04-04 08:00 | 2013-08-01 17:00 | 2013-04-04 08:00 | 2013-08-01 17:00 | 2013-08-21 08:00 | 2013-12-18 17:00 |  | PT_Normal |  |  |  |  | rAQaS7+NTSSn01vVtH9KLw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05; period 3: 2013-AP06; period 4: 2013-AP07 |  | 0 | 0
%R | 499908 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3300 | Proc & Del Gypsum Board false ceiling |  | 296 | 40 | 880 | 0 | 0 | 0 | 880 | 0 | 0 | 0 |  |  |  | 2013-07-23 08:00 | 2013-11-09 17:00 |  | 2013-06-16 08:00 | 2013-10-03 17:00 | 2013-06-16 08:00 | 2013-10-03 17:00 | 2013-06-16 08:00 | 2013-10-03 17:00 | 2013-07-23 08:00 | 2013-11-09 17:00 |  | PT_Normal |  |  |  |  | 89844HFbR0Gl62E9Ydo8TQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08; period 4: 2013-AP09 |  | 0 | 0
%R | 499909 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3310 | Proc & Del Aluminum Tile false ceiling |  | 424 | 8 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-08-13 08:00 | 2013-12-10 17:00 |  | 2013-06-21 08:00 | 2013-10-18 17:00 | 2013-06-21 08:00 | 2013-10-18 17:00 | 2013-06-21 08:00 | 2013-10-18 17:00 | 2013-08-13 08:00 | 2013-12-10 17:00 |  | PT_Normal |  |  |  |  | Jc9yw7wqRWa0t9t1psW2ng |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08; period 4: 2013-AP09 |  | 0 | 0
%R | 499910 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3390 | Proc & Del GRC Panels |  | 712 | 536 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-09-13 08:00 | 2013-12-11 17:00 |  | 2013-06-16 08:00 | 2013-09-13 17:00 | 2013-06-16 08:00 | 2013-09-13 17:00 | 2013-06-16 08:00 | 2013-09-13 17:00 | 2013-09-13 08:00 | 2013-12-11 17:00 |  | PT_Normal |  |  |  |  | 4XVCDMk6Qa+ALeCbfzLTFQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08 |  | 0 | 0
%R | 499911 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3320 | Proc & Del Paints |  | 96 | 0 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-07-09 08:00 | 2013-10-06 17:00 |  | 2013-06-27 08:00 | 2013-09-24 17:00 | 2013-06-27 08:00 | 2013-09-24 17:00 | 2013-06-27 08:00 | 2013-09-24 17:00 | 2013-07-09 08:00 | 2013-10-06 17:00 |  | PT_Normal |  |  |  |  | BLoVsv/mT9qUdiL4+vyIwQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08 |  | 0 | 0
%R | 499912 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3420 | Proc & Del Epoxy |  | 1304 | 424 | 320 | 0 | 0 | 0 | 320 | 0 | 0 | 0 |  |  |  | 2013-12-25 08:00 | 2014-02-02 17:00 |  | 2013-07-15 08:00 | 2013-08-23 17:00 | 2013-07-15 08:00 | 2013-08-23 17:00 | 2013-07-15 08:00 | 2013-08-23 17:00 | 2013-12-25 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | RJY+MBFoSty8i2PsbtCcpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 499913 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3430 | Proc & Del Roller Shutter |  | 2096 | 1128 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2014-03-07 08:00 | 2014-07-04 17:00 |  | 2013-06-18 08:00 | 2013-10-15 17:00 | 2013-06-18 08:00 | 2013-10-15 17:00 | 2013-06-18 08:00 | 2013-10-15 17:00 | 2014-03-07 08:00 | 2014-07-04 17:00 |  | PT_Normal |  |  |  |  | hpIU0T1RRuS49jdNGeW1ug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:44 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08; period 4: 2013-AP09 |  | 0 | 0
%R | 499914 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3700 | Proc & Del Road Works Materials |  | 1800 | 1456 | 320 | 0 | 0 | 0 | 320 | 0 | 0 | 0 |  |  |  | 2014-04-01 08:00 | 2014-05-10 17:00 |  | 2013-08-19 08:00 | 2013-09-27 17:00 | 2013-08-19 08:00 | 2013-09-27 17:00 | 2013-08-19 08:00 | 2013-09-27 17:00 | 2014-04-01 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | UKFxiTjgQuiheyA5s+0Fig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 0 | 0
%R | 499915 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3710 | Proc & Del External signage |  | 1640 | 1296 | 480 | 0 | 0 | 0 | 480 | 0 | 0 | 0 |  |  |  | 2014-03-12 08:00 | 2014-05-10 17:00 |  | 2013-08-19 08:00 | 2013-10-17 17:00 | 2013-08-19 08:00 | 2013-10-17 17:00 | 2013-08-19 08:00 | 2013-10-17 17:00 | 2014-03-12 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | PepPMZjNT1qDndm8V++59A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 0 | 0
%R | 499916 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3720 | Proc & Del Road Marking |  | 1640 | 1296 | 480 | 0 | 0 | 0 | 480 | 0 | 0 | 0 |  |  |  | 2014-03-12 08:00 | 2014-05-10 17:00 |  | 2013-08-19 08:00 | 2013-10-17 17:00 | 2013-08-19 08:00 | 2013-10-17 17:00 | 2013-08-19 08:00 | 2013-10-17 17:00 | 2014-03-12 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | LzCWd8cyS9qtmJq86MoGgQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 0 | 0
%R | 499917 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3600 | Proc & Del kerb works |  | 760 | 368 | 320 | 0 | 0 | 0 | 320 | 0 | 0 | 0 |  |  |  | 2013-10-14 08:00 | 2013-11-22 17:00 |  | 2013-07-11 08:00 | 2013-08-19 17:00 | 2013-07-11 08:00 | 2013-08-19 17:00 | 2013-07-11 08:00 | 2013-08-19 17:00 | 2013-10-14 08:00 | 2013-11-22 17:00 |  | PT_Normal |  |  |  |  | o2/Aa23sQaikl0gkooYP5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 499918 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3660 | Proc & Del Interlock works |  | 840 | 312 | 320 | 0 | 0 | 0 | 320 | 0 | 0 | 0 |  |  |  | 2013-11-11 08:00 | 2013-12-20 17:00 |  | 2013-07-29 08:00 | 2013-09-06 17:00 | 2013-07-29 08:00 | 2013-09-06 17:00 | 2013-07-29 08:00 | 2013-09-06 17:00 | 2013-11-11 08:00 | 2013-12-20 17:00 |  | PT_Normal |  |  |  |  | jXIRrFPfTp27vW6/hNVovg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 499919 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3730 | Proc & Del Car Parking Shed |  | 1208 | 1008 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2014-01-17 08:00 | 2014-04-16 17:00 |  | 2013-08-19 08:00 | 2013-11-16 17:00 | 2013-08-19 08:00 | 2013-11-16 17:00 | 2013-08-19 08:00 | 2013-11-16 17:00 | 2014-01-17 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | UhTsZsbfSvavPiQNxBfrBQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09; period 3: 2013-AP10 |  | 0 | 0
%R | 499920 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3740 | Proc & Del Stone Boulders |  | 1216 | 912 | 480 | 0 | 0 | 0 | 480 | 0 | 0 | 0 |  |  |  | 2014-01-18 08:00 | 2014-03-18 17:00 |  | 2013-08-19 08:00 | 2013-10-17 17:00 | 2013-08-19 08:00 | 2013-10-17 17:00 | 2013-08-19 08:00 | 2013-10-17 17:00 | 2014-01-18 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | Zq0wagwVTjWJ7lqrOPN9Dw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 0 | 0
%R | 499921 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3750 | Proc & Del Speed Humps |  | 1200 | 936 | 480 | 0 | 0 | 0 | 480 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-03-16 17:00 |  | 2013-08-19 08:00 | 2013-10-17 17:00 | 2013-08-19 08:00 | 2013-10-17 17:00 | 2013-08-19 08:00 | 2013-10-17 17:00 | 2014-01-16 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | hn4C5f1QTGmhepZ4uWNEWw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 0 | 0
%R | 499922 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3790 | Proc & Del Plantation(Grass,Trees) |  | 208 | 0 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-10-01 08:00 | 2013-12-29 17:00 |  | 2013-09-05 08:00 | 2013-12-03 17:00 | 2013-09-05 08:00 | 2013-12-03 17:00 | 2013-09-05 08:00 | 2013-12-03 17:00 | 2013-10-01 08:00 | 2013-12-29 17:00 |  | PT_Normal |  |  |  |  | MI3VswreSXiwISVdHNGJmQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10; period 3: 2013-AP11 |  | 0 | 0
%R | 499923 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3820 | Proc & Del Pre-cast Boundry Wall |  | 392 | 80 | 800 | 0 | 0 | 0 | 800 | 0 | 0 | 0 |  |  |  | 2013-10-24 08:00 | 2014-01-31 17:00 |  | 2013-09-05 08:00 | 2013-12-13 17:00 | 2013-09-05 08:00 | 2013-12-13 17:00 | 2013-09-05 08:00 | 2013-12-13 17:00 | 2013-10-24 08:00 | 2014-01-31 17:00 |  | PT_Normal |  |  |  |  | JXNlIgkgTdmt0zzi9uSg6g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10; period 3: 2013-AP11; period 4: 2013-AP12 |  | 0 | 0
%R | 499924 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3800 | Proc & Del Steel Gate & Barrier gates |  | 608 | 288 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-11-20 08:00 | 2014-02-17 17:00 |  | 2013-09-05 08:00 | 2013-12-03 17:00 | 2013-09-05 08:00 | 2013-12-03 17:00 | 2013-09-05 08:00 | 2013-12-03 17:00 | 2013-11-20 08:00 | 2014-02-17 17:00 |  | PT_Normal |  |  |  |  | AsPksYx5ROGFF85qspuzlA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10; period 3: 2013-AP11 |  | 0 | 0
%R | 499925 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3630 | Proc & Del Steel Ladder |  | 360 | 104 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-09-06 08:00 | 2013-12-04 17:00 |  | 2013-07-23 08:00 | 2013-10-20 17:00 | 2013-07-23 08:00 | 2013-10-20 17:00 | 2013-07-23 08:00 | 2013-10-20 17:00 | 2013-09-06 08:00 | 2013-12-04 17:00 |  | PT_Normal |  |  |  |  | FVLra+tbRB6XA1v57Eo5Rw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08; period 3: 2013-AP09 |  | 0 | 0
%R | 499926 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3590 | Proc & Del Manhole Covers and Frames |  | 488 | 368 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-09-18 08:00 | 2013-12-16 17:00 |  | 2013-07-19 08:00 | 2013-10-16 17:00 | 2013-07-19 08:00 | 2013-10-16 17:00 | 2013-07-19 08:00 | 2013-10-16 17:00 | 2013-09-18 08:00 | 2013-12-16 17:00 |  | PT_Normal |  |  |  |  | zCVQbx4MTKu94lzZKUA8jA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08; period 3: 2013-AP09 |  | 0 | 0
%R | 499927 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3400 | Proc & Del Access Ladder |  | 872 | 0 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-10-03 08:00 | 2013-12-31 17:00 |  | 2013-06-16 08:00 | 2013-09-13 17:00 | 2013-06-16 08:00 | 2013-09-13 17:00 | 2013-06-16 08:00 | 2013-09-13 17:00 | 2013-10-03 08:00 | 2013-12-31 17:00 |  | PT_Normal |  |  |  |  | uNiah1TWRdqVio6t3mc/Fg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08 |  | 0 | 0
%R | 499928 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3500 | Proc & Del Steel Door |  | 264 | 0 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-08-02 08:00 | 2013-11-29 17:00 |  | 2013-06-30 08:00 | 2013-10-27 17:00 | 2013-06-30 08:00 | 2013-10-27 17:00 | 2013-06-30 08:00 | 2013-10-27 17:00 | 2013-08-02 08:00 | 2013-11-29 17:00 |  | PT_Normal |  |  |  |  | ohRtti9xTIKHVPSzrPdLSw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08; period 4: 2013-AP09 |  | 0 | 0
%R | 499929 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3580 | Proc & Del Stainless Steel Handrail |  | 600 | 240 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-09-28 08:00 | 2014-01-25 17:00 |  | 2013-07-15 08:00 | 2013-11-11 17:00 | 2013-07-15 08:00 | 2013-11-11 17:00 | 2013-07-15 08:00 | 2013-11-11 17:00 | 2013-09-28 08:00 | 2014-01-25 17:00 |  | PT_Normal |  |  |  |  | /26/VQbFTbigXIBVdoglDQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08; period 3: 2013-AP09; period 4: 2013-AP10 |  | 0 | 0
%R | 499930 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3120 | Proc & Del Ceramic Tile |  | 392 | 56 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-06-18 08:00 | 2013-10-15 17:00 |  | 2013-04-30 08:00 | 2013-08-27 17:00 | 2013-04-30 08:00 | 2013-08-27 17:00 | 2013-04-30 08:00 | 2013-08-27 17:00 | 2013-06-18 08:00 | 2013-10-15 17:00 |  | PT_Normal |  |  |  |  | IlxyE6oVQKSxOOkP/1WHDg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05; period 3: 2013-AP06; period 4: 2013-AP07 |  | 0 | 0
%R | 499931 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3130 | Proc & Del Porcelain Tile |  | 472 | 112 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-06-28 08:00 | 2013-10-25 17:00 |  | 2013-04-30 08:00 | 2013-08-27 17:00 | 2013-04-30 08:00 | 2013-08-27 17:00 | 2013-04-30 08:00 | 2013-08-27 17:00 | 2013-06-28 08:00 | 2013-10-25 17:00 |  | PT_Normal |  |  |  |  | isDC3dehR9GFKjnSxNvyJg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05; period 3: 2013-AP06; period 4: 2013-AP07 |  | 0 | 0
%R | 499932 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3410 | Proc & Del Aluminium Slat Screen |  | 784 | 208 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-09-22 08:00 | 2014-01-19 17:00 |  | 2013-06-16 08:00 | 2013-10-13 17:00 | 2013-06-16 08:00 | 2013-10-13 17:00 | 2013-06-16 08:00 | 2013-10-13 17:00 | 2013-09-22 08:00 | 2014-01-19 17:00 |  | PT_Normal |  |  |  |  | D01LvmOHTz24FfWoXI7mKw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08; period 4: 2013-AP09 |  | 0 | 0
%R | 499933 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3510 | Proc & Del Stainless Steel Cover |  | 264 | 0 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-08-02 08:00 | 2013-11-29 17:00 |  | 2013-06-30 08:00 | 2013-10-27 17:00 | 2013-06-30 08:00 | 2013-10-27 17:00 | 2013-06-30 08:00 | 2013-10-27 17:00 | 2013-08-02 08:00 | 2013-11-29 17:00 |  | PT_Normal |  |  |  |  | sOqAZf7VQW+lXb2EhlIWEQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08; period 4: 2013-AP09 |  | 0 | 0
%R | 499934 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3610 | Proc & Del PVC Tent |  | 304 | 40 | 880 | 0 | 0 | 0 | 880 | 0 | 0 | 0 |  |  |  | 2013-08-12 08:00 | 2013-11-29 17:00 |  | 2013-07-05 08:00 | 2013-10-22 17:00 | 2013-07-05 08:00 | 2013-10-22 17:00 | 2013-07-05 08:00 | 2013-10-22 17:00 | 2013-08-12 08:00 | 2013-11-29 17:00 |  | PT_Normal |  |  |  |  | e1ljy9pVQXeXZghDXtN1Qg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08; period 3: 2013-AP09; period 4: 2013-AP10 |  | 0 | 0
%R | 499935 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3620 | Proc & Del Strutural Steel |  | 264 | 8 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-08-07 08:00 | 2013-12-04 17:00 |  | 2013-07-05 08:00 | 2013-11-01 17:00 | 2013-07-05 08:00 | 2013-11-01 17:00 | 2013-07-05 08:00 | 2013-11-01 17:00 | 2013-08-07 08:00 | 2013-12-04 17:00 |  | PT_Normal |  |  |  |  | uCFLOOBUT+aDO1z4NqmyAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08; period 3: 2013-AP09; period 4: 2013-AP10 |  | 0 | 0
%R | 499936 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3220 | Proc & Del Water Chiller |  | 496 | 400 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-08-19 08:00 | 2013-12-16 17:00 |  | 2013-06-18 08:00 | 2013-10-15 17:00 | 2013-06-18 08:00 | 2013-10-15 17:00 | 2013-06-18 08:00 | 2013-10-15 17:00 | 2013-08-19 08:00 | 2013-12-16 17:00 |  | PT_Normal |  |  |  |  | aohwlh0GSHq3riFviIJ8Gw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08; period 4: 2013-AP09 |  | 0 | 0
%R | 499937 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3330 | Proc & Del Booster Pump |  | 360 | 264 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-08-19 08:00 | 2013-12-16 17:00 |  | 2013-07-05 08:00 | 2013-11-01 17:00 | 2013-07-05 08:00 | 2013-11-01 17:00 | 2013-07-05 08:00 | 2013-11-01 17:00 | 2013-08-19 08:00 | 2013-12-16 17:00 |  | PT_Normal |  |  |  |  | sqfp6MChRi+NhhHu4X+TNg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08; period 3: 2013-AP09; period 4: 2013-AP10 |  | 0 | 0
%R | 499938 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3520 | Proc & Del Lift Pump |  | 216 | 120 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-08-19 08:00 | 2013-12-16 17:00 |  | 2013-07-23 08:00 | 2013-11-19 17:00 | 2013-07-23 08:00 | 2013-11-19 17:00 | 2013-07-23 08:00 | 2013-11-19 17:00 | 2013-08-19 08:00 | 2013-12-16 17:00 |  | PT_Normal |  |  |  |  | Q9brF3R/TtOkMer6RrFQUw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08; period 3: 2013-AP09; period 4: 2013-AP10 |  | 0 | 0
%R | 499939 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3640 | Proc & Del Water meter |  | 560 | 464 | 480 | 0 | 0 | 0 | 480 | 0 | 0 | 0 |  |  |  | 2013-10-18 08:00 | 2013-12-16 17:00 |  | 2013-08-09 08:00 | 2013-10-07 17:00 | 2013-08-09 08:00 | 2013-10-07 17:00 | 2013-08-09 08:00 | 2013-10-07 17:00 | 2013-10-18 08:00 | 2013-12-16 17:00 |  | PT_Normal |  |  |  |  | F5JBfXk9R+KM3JjV+urL4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 0 | 0
%R | 499940 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3680 | Proc & Del Water Tank |  | 392 | 296 | 480 | 0 | 0 | 0 | 480 | 0 | 0 | 0 |  |  |  | 2013-10-18 08:00 | 2013-12-16 17:00 |  | 2013-08-30 08:00 | 2013-10-28 17:00 | 2013-08-30 08:00 | 2013-10-28 17:00 | 2013-08-30 08:00 | 2013-10-28 17:00 | 2013-10-18 08:00 | 2013-12-16 17:00 |  | PT_Normal |  |  |  |  | U0Le3K4QRcmqm4r8aFLKNA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 0 | 0
%R | 499941 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3770 | Proc & Del Kitchen Water Filter |  | 88 | 0 | 480 | 0 | 0 | 0 | 480 | 0 | 0 | 0 |  |  |  | 2013-09-28 08:00 | 2013-11-26 17:00 |  | 2013-09-17 08:00 | 2013-11-15 17:00 | 2013-09-17 08:00 | 2013-11-15 17:00 | 2013-09-17 08:00 | 2013-11-15 17:00 | 2013-09-28 08:00 | 2013-11-26 17:00 |  | PT_Normal |  |  |  |  | mIfA6HWNTp6jDccD1dvPXw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 0 | 0
%R | 499942 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3060 | Proc & Del UPVC Pipes |  | 256 | 256 | 320 | 0 | 0 | 0 | 320 | 0 | 0 | 0 |  |  |  | 2013-03-29 08:00 | 2013-05-07 17:00 |  | 2013-02-25 08:00 | 2013-04-05 17:00 | 2013-02-25 08:00 | 2013-04-05 17:00 | 2013-02-25 08:00 | 2013-04-05 17:00 | 2013-03-29 08:00 | 2013-05-07 17:00 |  | PT_Normal |  |  |  |  | zITfWHlXTWGgQZErkcKpoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499943 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3070 | Proc & Del Floor drains & Cleanouts |  | 256 | 256 | 320 | 0 | 0 | 0 | 320 | 0 | 0 | 0 |  |  |  | 2013-03-29 08:00 | 2013-05-07 17:00 |  | 2013-02-25 08:00 | 2013-04-05 17:00 | 2013-02-25 08:00 | 2013-04-05 17:00 | 2013-02-25 08:00 | 2013-04-05 17:00 | 2013-03-29 08:00 | 2013-05-07 17:00 |  | PT_Normal |  |  |  |  | e/2j6+LpSKegPWpjeiyklA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 499944 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3150 | Proc & Del Sanitary Fittings |  | 480 | 392 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-07-30 08:00 | 2013-11-26 17:00 |  | 2013-05-31 08:00 | 2013-09-27 17:00 | 2013-05-31 08:00 | 2013-09-27 17:00 | 2013-05-31 08:00 | 2013-09-27 17:00 | 2013-07-30 08:00 | 2013-11-26 17:00 |  | PT_Normal |  |  |  |  | etirqcXURn+rR0q1mKfTJw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06; period 3: 2013-AP07; period 4: 2013-AP08 |  | 0 | 0
%R | 499945 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3230 | Proc & Del Water Heater |  | 576 | 488 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-08-29 08:00 | 2013-11-26 17:00 |  | 2013-06-18 08:00 | 2013-09-15 17:00 | 2013-06-18 08:00 | 2013-09-15 17:00 | 2013-06-18 08:00 | 2013-09-15 17:00 | 2013-08-29 08:00 | 2013-11-26 17:00 |  | PT_Normal |  |  |  |  | ElX2xa7xQpakMSjJbEAjaA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08 |  | 0 | 0
%R | 499946 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3080 | Proc & Del Polyethylene Pipes |  | 496 | 360 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-06-16 08:00 | 2013-09-13 17:00 |  | 2013-04-15 08:00 | 2013-07-13 17:00 | 2013-04-15 08:00 | 2013-07-13 17:00 | 2013-04-15 08:00 | 2013-07-13 17:00 | 2013-06-16 08:00 | 2013-09-13 17:00 |  | PT_Normal |  |  |  |  | y1Xtf3nXSmOsOW/sNby8ZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05; period 3: 2013-AP06 |  | 0 | 0
%R | 499947 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3160 | Proc & Del Copper Pipes |  | 504 | 16 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-08-02 08:00 | 2013-10-30 17:00 |  | 2013-05-31 08:00 | 2013-08-28 17:00 | 2013-05-31 08:00 | 2013-08-28 17:00 | 2013-05-31 08:00 | 2013-08-28 17:00 | 2013-08-02 08:00 | 2013-10-30 17:00 |  | PT_Normal |  |  |  |  | 9xko36ofScyZ3rxX4Fyoww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06; period 3: 2013-AP07 |  | 0 | 0
%R | 499948 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3240 | Proc & Del Split AC |  | 808 | 88 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-09-27 08:00 | 2014-01-24 17:00 |  | 2013-06-18 08:00 | 2013-10-15 17:00 | 2013-06-18 08:00 | 2013-10-15 17:00 | 2013-06-18 08:00 | 2013-10-15 17:00 | 2013-09-27 08:00 | 2014-01-24 17:00 |  | PT_Normal |  |  |  |  | fESIShToQiewIU2FUvogQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08; period 4: 2013-AP09 |  | 0 | 0
%R | 499949 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3340 | Proc & Del Exhaust Air louver |  | 744 | 144 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-10-06 08:00 | 2014-01-03 17:00 |  | 2013-07-05 08:00 | 2013-10-02 17:00 | 2013-07-05 08:00 | 2013-10-02 17:00 | 2013-07-05 08:00 | 2013-10-02 17:00 | 2013-10-06 08:00 | 2014-01-03 17:00 |  | PT_Normal |  |  |  |  | vScc18xWSy2YsevwwCdopQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08; period 3: 2013-AP09 |  | 0 | 0
%R | 499950 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3530 | Proc & Del Exhaust Fan |  | 600 | 0 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-10-06 08:00 | 2014-01-03 17:00 |  | 2013-07-23 08:00 | 2013-10-20 17:00 | 2013-07-23 08:00 | 2013-10-20 17:00 | 2013-07-23 08:00 | 2013-10-20 17:00 | 2013-10-06 08:00 | 2014-01-03 17:00 |  | PT_Normal |  |  |  |  | Q1op94UkTzKzZbwqaeH5Ow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08; period 3: 2013-AP09 |  | 0 | 0
%R | 499951 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3170 | Proc & Del SMDB |  | 736 | 184 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-08-31 08:00 | 2013-12-28 17:00 |  | 2013-05-31 08:00 | 2013-09-27 17:00 | 2013-05-31 08:00 | 2013-09-27 17:00 | 2013-05-31 08:00 | 2013-09-27 17:00 | 2013-08-31 08:00 | 2013-12-28 17:00 |  | PT_Normal |  |  |  |  | KhmibntlT8qpreD47AXt7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06; period 3: 2013-AP07; period 4: 2013-AP08 |  | 0 | 0
%R | 499952 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3180 | Proc & Del Cables & Wires |  | 552 | 136 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-10-26 17:00 |  | 2013-04-21 08:00 | 2013-08-18 17:00 | 2013-04-21 08:00 | 2013-08-18 17:00 | 2013-04-21 08:00 | 2013-08-18 17:00 | 2013-06-29 08:00 | 2013-10-26 17:00 |  | PT_Normal |  |  |  |  | EdF2+9X5RsOs1sh6dlt5xA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:51 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05; period 3: 2013-AP06; period 4: 2013-AP07 |  | 0 | 0
%R | 499953 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3190 | Proc & Del Lights & Fixtures |  | 840 | 232 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-09-13 08:00 | 2014-01-10 17:00 |  | 2013-05-31 08:00 | 2013-09-27 17:00 | 2013-05-31 08:00 | 2013-09-27 17:00 | 2013-05-31 08:00 | 2013-09-27 17:00 | 2013-09-13 08:00 | 2014-01-10 17:00 |  | PT_Normal |  |  |  |  | QoITUMzVQouGOOMOIQxwjA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06; period 3: 2013-AP07; period 4: 2013-AP08 |  | 0 | 0
%R | 499954 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3200 | Proc & Del Isolators |  | 1040 | 280 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-10-08 08:00 | 2014-02-04 17:00 |  | 2013-05-31 08:00 | 2013-09-27 17:00 | 2013-05-31 08:00 | 2013-09-27 17:00 | 2013-05-31 08:00 | 2013-09-27 17:00 | 2013-10-08 08:00 | 2014-02-04 17:00 |  | PT_Normal |  |  |  |  | 2kUFuJggRoWBGaWEl67lbw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06; period 3: 2013-AP07; period 4: 2013-AP08 |  | 0 | 0
%R | 499955 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3250 | Proc & Del Street Light Post Set |  | 584 | 8 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-11-17 08:00 | 2014-03-16 17:00 |  | 2013-09-05 08:00 | 2014-01-02 17:00 | 2013-09-05 08:00 | 2014-01-02 17:00 | 2013-09-05 08:00 | 2014-01-02 17:00 | 2013-11-17 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | FcdCPNHTRDCpAhS22EEqGQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:40 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10; period 3: 2013-AP11; period 4: 2013-AP12 |  | 0 | 0
%R | 499956 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3350 | Proc & Del Bollard Lamp |  | 888 | 312 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-11-17 08:00 | 2014-03-16 17:00 |  | 2013-07-29 08:00 | 2013-11-25 17:00 | 2013-07-29 08:00 | 2013-11-25 17:00 | 2013-07-29 08:00 | 2013-11-25 17:00 | 2013-11-17 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | x9gh1c7uTEekorMEz2V/zA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:40 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08; period 3: 2013-AP09; period 4: 2013-AP10 |  | 0 | 0
%R | 499957 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3210 | Proc & Del Fire Resistant Cables |  | 1008 | 520 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-10-04 08:00 | 2014-01-01 17:00 |  | 2013-05-31 08:00 | 2013-08-28 17:00 | 2013-05-31 08:00 | 2013-08-28 17:00 | 2013-05-31 08:00 | 2013-08-28 17:00 | 2013-10-04 08:00 | 2014-01-01 17:00 |  | PT_Normal |  |  |  |  | JgsaH4/TT2CTIKLoYgi4SQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06; period 3: 2013-AP07 |  | 0 | 0
%R | 499958 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3260 | Proc & Del Smoke Detector |  | 864 | 376 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-10-04 08:00 | 2014-01-01 17:00 |  | 2013-06-18 08:00 | 2013-09-15 17:00 | 2013-06-18 08:00 | 2013-09-15 17:00 | 2013-06-18 08:00 | 2013-09-15 17:00 | 2013-10-04 08:00 | 2014-01-01 17:00 |  | PT_Normal |  |  |  |  | IwLry5U7TCy7lw7NDUUNAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08 |  | 0 | 0
%R | 499959 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3360 | Proc & Del Digital Alarm Communicator Panel |  | 488 | 0 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-09-04 08:00 | 2014-01-01 17:00 |  | 2013-07-05 08:00 | 2013-11-01 17:00 | 2013-07-05 08:00 | 2013-11-01 17:00 | 2013-07-05 08:00 | 2013-11-01 17:00 | 2013-09-04 08:00 | 2014-01-01 17:00 |  | PT_Normal |  |  |  |  | 78PC1t7eRQyb2sk0w0eCrg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08; period 3: 2013-AP09; period 4: 2013-AP10 |  | 0 | 0
%R | 499960 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3370 | Proc & Del Fire Blanket |  | 968 | 480 | 480 | 0 | 0 | 0 | 480 | 0 | 0 | 0 |  |  |  | 2013-11-03 08:00 | 2014-01-01 17:00 |  | 2013-07-05 08:00 | 2013-09-02 17:00 | 2013-07-05 08:00 | 2013-09-02 17:00 | 2013-07-05 08:00 | 2013-09-02 17:00 | 2013-11-03 08:00 | 2014-01-01 17:00 |  | PT_Normal |  |  |  |  | kmxIvSh+SkuSDSRazdiKtw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 499961 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3380 | Proc & Del Fire Extinguisher |  | 888 | 400 | 560 | 0 | 0 | 0 | 560 | 0 | 0 | 0 |  |  |  | 2013-10-24 08:00 | 2014-01-01 17:00 |  | 2013-07-05 08:00 | 2013-09-12 17:00 | 2013-07-05 08:00 | 2013-09-12 17:00 | 2013-07-05 08:00 | 2013-09-12 17:00 | 2013-10-24 08:00 | 2014-01-01 17:00 |  | PT_Normal |  |  |  |  | gfM0g5BaSPymUXn3j6GobQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08; period 3: 2013-AP09 |  | 0 | 0
%R | 499962 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3540 | Proc & Del Ductile Iron Pipes |  | 48 | 0 | 880 | 0 | 0 | 0 | 880 | 0 | 0 | 0 |  |  |  | 2013-07-29 08:00 | 2013-11-15 17:00 |  | 2013-07-23 08:00 | 2013-11-09 17:00 | 2013-07-23 08:00 | 2013-11-09 17:00 | 2013-07-23 08:00 | 2013-11-09 17:00 | 2013-07-29 08:00 | 2013-11-15 17:00 |  | PT_Normal |  |  |  |  | IrQQ31TtRHKsTceNP7v7Wg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08; period 3: 2013-AP09; period 4: 2013-AP10 |  | 0 | 0
%R | 499963 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3650 | Proc & Del Isolating Values |  | 72 | 24 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-08-18 08:00 | 2013-11-15 17:00 |  | 2013-08-09 08:00 | 2013-11-06 17:00 | 2013-08-09 08:00 | 2013-11-06 17:00 | 2013-08-09 08:00 | 2013-11-06 17:00 | 2013-08-18 08:00 | 2013-11-15 17:00 |  | PT_Normal |  |  |  |  | BqIqLteOR1aIxLhmo726iQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09; period 3: 2013-AP10 |  | 0 | 0
%R | 499964 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3690 | Proc & Del Fire Hydrant |  | 144 | 0 | 800 | 0 | 0 | 0 | 800 | 0 | 0 | 0 |  |  |  | 2013-09-17 08:00 | 2013-12-25 17:00 |  | 2013-08-30 08:00 | 2013-12-07 17:00 | 2013-08-30 08:00 | 2013-12-07 17:00 | 2013-08-30 08:00 | 2013-12-07 17:00 | 2013-09-17 08:00 | 2013-12-25 17:00 |  | PT_Normal |  |  |  |  | 9CLMAthDS9eeEbYPZVUn7w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09; period 3: 2013-AP10; period 4: 2013-AP11 |  | 0 | 0
%R | 499965 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3270 | Proc & Del Video Com System |  | 680 | 88 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-09-11 08:00 | 2014-01-08 17:00 |  | 2013-06-18 08:00 | 2013-10-15 17:00 | 2013-06-18 08:00 | 2013-10-15 17:00 | 2013-06-18 08:00 | 2013-10-15 17:00 | 2013-09-11 08:00 | 2014-01-08 17:00 |  | PT_Normal |  |  |  |  | USmZJE+dT+mEFA/BCKjSJA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08; period 4: 2013-AP09 |  | 0 | 0
%R | 499966 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3280 | Proc & Del Telephone Fittings & Accessories |  | 672 | 80 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-09-11 08:00 | 2014-01-08 17:00 |  | 2013-06-19 08:00 | 2013-10-16 17:00 | 2013-06-19 08:00 | 2013-10-16 17:00 | 2013-06-19 08:00 | 2013-10-16 17:00 | 2013-09-11 08:00 | 2014-01-08 17:00 |  | PT_Normal |  |  |  |  | Q3Cy1qrbR7SH+oWHTYs3gQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08; period 4: 2013-AP09 |  | 0 | 0
%R | 499967 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3290 | Proc & Del Television devices,Fit. & Access. |  | 944 | 168 | 960 | 0 | 0 | 0 | 960 | 0 | 0 | 0 |  |  |  | 2013-10-15 08:00 | 2014-02-11 17:00 |  | 2013-06-19 08:00 | 2013-10-16 17:00 | 2013-06-19 08:00 | 2013-10-16 17:00 | 2013-06-19 08:00 | 2013-10-16 17:00 | 2013-10-15 08:00 | 2014-02-11 17:00 |  | PT_Normal |  |  |  |  | YtPgJNnGSFKVDva7RLB3Ww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07; period 3: 2013-AP08; period 4: 2013-AP09 |  | 0 | 0
%R | 499968 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3670 | Proc & Del Irrigation Pipes |  | 752 | 544 | 480 | 0 | 0 | 0 | 480 | 0 | 0 | 0 |  |  |  | 2013-10-31 08:00 | 2013-12-29 17:00 |  | 2013-07-29 08:00 | 2013-09-26 17:00 | 2013-07-29 08:00 | 2013-09-26 17:00 | 2013-07-29 08:00 | 2013-09-26 17:00 | 2013-10-31 08:00 | 2013-12-29 17:00 |  | PT_Normal |  |  |  |  | m2OiZKGNSTuYDWHf/pPuiw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 499969 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3760 | Proc & Del Sprinklers |  | 1312 | 1024 | 480 | 0 | 0 | 0 | 480 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-03-30 17:00 |  | 2013-08-19 08:00 | 2013-10-17 17:00 | 2013-08-19 08:00 | 2013-10-17 17:00 | 2013-08-19 08:00 | 2013-10-17 17:00 | 2014-01-30 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | HW6Rb+TLS7eQBdYc4IZvpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 0 | 0
%R | 499970 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3810 | Proc & Del Nozzle Jet |  | 936 | 648 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-12-31 08:00 | 2014-03-30 17:00 |  | 2013-09-05 08:00 | 2013-12-03 17:00 | 2013-09-05 08:00 | 2013-12-03 17:00 | 2013-09-05 08:00 | 2013-12-03 17:00 | 2013-12-31 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | zhb2uA6QQqCyjO4twxEKPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10; period 3: 2013-AP11 |  | 0 | 0
%R | 499971 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3830 | Proc & Del Solenoid Values |  | 792 | 504 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-12-31 08:00 | 2014-03-30 17:00 |  | 2013-09-23 08:00 | 2013-12-21 17:00 | 2013-09-23 08:00 | 2013-12-21 17:00 | 2013-09-23 08:00 | 2013-12-21 17:00 | 2013-12-31 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | ULEHDSTdTLKBFPG3riW6kw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10; period 3: 2013-AP11 |  | 0 | 0
%R | 499972 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3840 | Proc & Del Gate Values |  | 656 | 368 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-12-31 08:00 | 2014-03-30 17:00 |  | 2013-10-10 08:00 | 2014-01-07 17:00 | 2013-10-10 08:00 | 2014-01-07 17:00 | 2013-10-10 08:00 | 2014-01-07 17:00 | 2013-12-31 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | OmM5vicdSwC+Bcc22Nt1SQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11; period 3: 2013-AP12 |  | 0 | 0
%R | 499973 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3860 | Proc & Del Remote Control Value |  | 496 | 208 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-12-31 08:00 | 2014-03-30 17:00 |  | 2013-10-30 08:00 | 2014-01-27 17:00 | 2013-10-30 08:00 | 2014-01-27 17:00 | 2013-10-30 08:00 | 2014-01-27 17:00 | 2013-12-31 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | UN2cCFVERpC2SB3cRqBXDw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11; period 3: 2013-AP12 |  | 0 | 0
%R | 499974 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3870 | Proc & Del Irrigation Controller |  | 352 | 64 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2013-12-31 08:00 | 2014-03-30 17:00 |  | 2013-11-17 08:00 | 2014-02-14 17:00 | 2013-11-17 08:00 | 2014-02-14 17:00 | 2013-11-17 08:00 | 2014-02-14 17:00 | 2013-12-31 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | e2/ASqgRR92AQw6zlEJ1ZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11; period 2: 2013-AP12; period 3: 2014-AP01 |  | 0 | 0
%R | 499975 | 6359 | 124374 | 13663 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00PRDV3850 | Proc & Del Fences |  | 1208 | 680 | 720 | 0 | 0 | 0 | 720 | 0 | 0 | 0 |  |  |  | 2014-02-21 08:00 | 2014-05-21 17:00 |  | 2013-09-23 08:00 | 2013-12-21 17:00 | 2013-09-23 08:00 | 2013-12-21 17:00 | 2013-09-23 08:00 | 2013-12-21 17:00 | 2014-02-21 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | bPjAiBIYSfO2cwhf0w4OZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:47 | admin | admin | [26 empty] | 540 | 29670 | N | N | L25 | MANUFACTURING, PROCUREMENT & DELIVERY |  | 124368 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10; period 3: 2013-AP11 |  | 0 | 0
%R | 499976 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1770 | Kitchen Water Filter_1st_Sub |  | 72 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-17 08:00 | 2013-07-03 17:00 |  | 2013-06-06 08:00 | 2013-06-23 17:00 | 2013-06-06 08:00 | 2013-06-23 17:00 | 2013-06-06 08:00 | 2013-06-23 17:00 | 2013-06-17 08:00 | 2013-07-03 17:00 |  | PT_Normal |  |  |  |  | rBNbPTi9QEe+KL0NbVEbiw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 30 | 0
%R | 499977 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1060 | UPVC Pipes_1st_Sub |  | 224 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-02-04 08:00 | 2013-02-21 17:00 |  | 2013-01-02 08:00 | 2013-01-19 17:00 | 2013-01-02 08:00 | 2013-01-19 17:00 | 2013-01-02 08:00 | 2013-01-19 17:00 | 2013-02-04 08:00 | 2013-02-21 17:00 |  | PT_Normal |  |  |  |  | NEIhDbUXRjOdGoG7xR9tPA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499978 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1070 | Floor drains & Cleanouts_1st_Sub |  | 224 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-02-04 08:00 | 2013-02-21 17:00 |  | 2013-01-02 08:00 | 2013-01-19 17:00 | 2013-01-02 08:00 | 2013-01-19 17:00 | 2013-01-02 08:00 | 2013-01-19 17:00 | 2013-02-04 08:00 | 2013-02-21 17:00 |  | PT_Normal |  |  |  |  | gizdsa8aTJ+glIc+oNTjUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499979 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1150 | Sanitary Fittings_1st_Sub |  | 32 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-02-26 08:00 | 2013-03-14 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-26 08:00 | 2013-03-14 17:00 |  | PT_Normal |  |  |  |  | vSJjUntOQHiBFi3yjDd8mg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 30 | 0
%R | 499980 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1230 | Water Heater_1st_Sub |  | 32 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-03-16 08:00 | 2013-04-01 17:00 |  | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-16 08:00 | 2013-04-01 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 499981 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1080 | Polyethylene Pipes_1st_Sub |  | 440 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-03-09 08:00 | 2013-03-25 17:00 |  | 2013-01-02 08:00 | 2013-01-19 17:00 | 2013-01-02 08:00 | 2013-01-19 17:00 | 2013-01-02 08:00 | 2013-01-19 17:00 | 2013-03-09 08:00 | 2013-03-25 17:00 |  | PT_Normal |  |  |  |  | ra8fEGGaRmanjp4FC8Ceeg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 499982 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1160 | Copper Pipes_1st_Sub |  | 432 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-25 08:00 | 2013-05-12 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-04-25 08:00 | 2013-05-12 17:00 |  | PT_Normal |  |  |  |  | OoV9WKL+QyOwMI3bTjl7Yw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 30 | 0
%R | 499983 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1240 | Split AC_1st_Sub |  | 488 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-21 08:00 | 2013-06-06 17:00 |  | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-05-21 08:00 | 2013-06-06 17:00 |  | PT_Normal |  |  |  |  | g3ciCJr3Sw+Bnm/ZW3ae8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 499984 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1340 | Exhaust Air louver_1st_Sub |  | 488 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-08 08:00 | 2013-06-24 17:00 |  | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-06-08 08:00 | 2013-06-24 17:00 |  | PT_Normal |  |  |  |  | SZq3mc/2RjSrB+1ik4jY3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 499985 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1530 | Exhaust Fan_1st_Sub |  | 488 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-25 08:00 | 2013-07-11 17:00 |  | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-06-25 08:00 | 2013-07-11 17:00 |  | PT_Normal |  |  |  |  | MUPF4u3tQZO0KUUjkZIT2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499986 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1170 | SMDB_1st_Sub |  | 600 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-20 08:00 | 2013-06-05 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 |  | PT_Normal |  |  |  |  | Q6cMZ9D3SrCq+TU/op3u5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 30 | 0
%R | 499987 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1180 | Cables & Wires_1st_Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-20 08:00 | 2013-05-06 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-04-20 08:00 | 2013-05-06 17:00 |  | PT_Normal |  |  |  |  | lFNBUELYRE67Rlgy0V8n6g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 30 | 0
%R | 499988 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1190 | Lights & Fixtures_1st_Sub |  | 696 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-03 08:00 | 2013-06-19 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-06-03 08:00 | 2013-06-19 17:00 |  | PT_Normal |  |  |  |  | 6SnECwHqTfG1cggW2fJ6nA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 30 | 0
%R | 499989 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1200 | Isolators_1st_Sub |  | 864 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-27 08:00 | 2013-07-14 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-06-27 08:00 | 2013-07-14 17:00 |  | PT_Normal |  |  |  |  | 6JieAoFqRN2V/WFczR+D3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 30 | 0
%R | 499990 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1250 | Street Light Post Set_1st_Sub |  | 880 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-17 08:00 | 2013-08-03 17:00 |  | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-07-17 08:00 | 2013-08-03 17:00 |  | PT_Normal |  |  |  |  | NBuH9ITNQHqqW86t086C4g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 499991 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1350 | Bollard Lamp_1st_Sub |  | 880 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-08-04 08:00 | 2013-08-24 17:00 |  | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-08-04 08:00 | 2013-08-24 17:00 |  | PT_Normal |  |  |  |  | 3TmXbWSqSOirm5jxG3dJVg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 499992 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1210 | Fire Resistant Cables_1st_Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-20 08:00 | 2013-05-06 17:00 |  | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-02-21 08:00 | 2013-03-10 17:00 | 2013-04-20 08:00 | 2013-05-06 17:00 |  | PT_Normal |  |  |  |  | 4g28TsejSiCviMy/VW+Cvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 30 | 0
%R | 499993 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1260 | Smoke Detector_1st_Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-07 08:00 | 2013-05-23 17:00 |  | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-05-07 08:00 | 2013-05-23 17:00 |  | PT_Normal |  |  |  |  | hQ1hA2rvQkWZmerJDpO8Xw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 499994 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1360 | Digital Alarm Communicator Panel_1st_Sub |  | 392 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-25 08:00 | 2013-06-10 17:00 |  | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-05-25 08:00 | 2013-06-10 17:00 |  | PT_Normal |  |  |  |  | xvVaVQxTQJK5y0hhdkOtwg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 499995 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1370 | Fire Blanket_1st_Sub |  | 32 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-02 08:00 | 2013-04-18 17:00 |  | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-04-02 08:00 | 2013-04-18 17:00 |  | PT_Normal |  |  |  |  | KkOXOC9zSB+F8aEIhft3AA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 499996 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1380 | Fire Extinguisher_1st_Sub |  | 32 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-02 08:00 | 2013-04-18 17:00 |  | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-04-02 08:00 | 2013-04-18 17:00 |  | PT_Normal |  |  |  |  | 8/pjydewQjeKeLcsZpn6bQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 499997 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1540 | Ductile Iron Pipes_1st_Sub |  | 32 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-20 08:00 | 2013-05-06 17:00 |  | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-20 08:00 | 2013-05-06 17:00 |  | PT_Normal |  |  |  |  | Q31knEOvRPi90E4zH5LlhA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 499998 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1650 | Isolating Values_1st_Sub |  | 32 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-07 08:00 | 2013-05-23 17:00 |  | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-07 08:00 | 2013-05-23 17:00 |  | PT_Normal |  |  |  |  | ZSsmeZVGSTyxfSwNRM9CHg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 20 | 0
%R | 499999 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1690 | Fire Hydrant_1st_Sub |  | 120 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-23 17:00 |  | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-06-06 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | e6eMt+VSRY6gLvAm6HdnWw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 500000 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1270 | Video Com System_1st_Sub |  | 560 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-01 08:00 | 2013-06-17 17:00 |  | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-06-01 08:00 | 2013-06-17 17:00 |  | PT_Normal |  |  |  |  | p2jKDuy1Sx+WJarOiyYyuQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 500001 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1280 | Telephone Fittings & Accessories_1st_Sub |  | 560 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-01 08:00 | 2013-06-17 17:00 |  | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-06-01 08:00 | 2013-06-17 17:00 |  | PT_Normal |  |  |  |  | pYoxM+kOSKaqhj2X8xnR8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 500002 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1290 | Television devices,Fittings & Access._1st_Sub |  | 792 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-04 08:00 | 2013-07-21 17:00 |  | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-07-04 08:00 | 2013-07-21 17:00 |  | PT_Normal |  |  |  |  | QKvb/2vKRU2d9p2On95QYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 500003 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1670 | Irrigation Pipes_1st_Sub |  | 296 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-03 08:00 | 2013-06-19 17:00 |  | 2013-04-21 08:00 | 2013-05-07 17:00 | 2013-04-21 08:00 | 2013-05-07 17:00 | 2013-04-21 08:00 | 2013-05-07 17:00 | 2013-06-03 08:00 | 2013-06-19 17:00 |  | PT_Normal |  |  |  |  | CmzOYHXWSVC4zgZ3LEOSwg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 500004 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1760 | Sprinklers_1st_Sub |  | 296 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-20 08:00 | 2013-07-07 17:00 |  | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-06-20 08:00 | 2013-07-07 17:00 |  | PT_Normal |  |  |  |  | pJIIDO1+TxKeSbA/eaMZCA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 20 | 0
%R | 500005 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1810 | Nozzle Jet_1st_Sub |  | 296 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-08 08:00 | 2013-07-24 17:00 |  | 2013-05-26 08:00 | 2013-06-11 17:00 | 2013-05-26 08:00 | 2013-06-11 17:00 | 2013-05-26 08:00 | 2013-06-11 17:00 | 2013-07-08 08:00 | 2013-07-24 17:00 |  | PT_Normal |  |  |  |  | 5aSsgTmDQQG6yFGPV6AhJQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 500006 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1830 | Solenoid Values_1st_Sub |  | 296 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-25 08:00 | 2013-08-14 17:00 |  | 2013-06-12 08:00 | 2013-06-29 17:00 | 2013-06-12 08:00 | 2013-06-29 17:00 | 2013-06-12 08:00 | 2013-06-29 17:00 | 2013-07-25 08:00 | 2013-08-14 17:00 |  | PT_Normal |  |  |  |  | 6LOmAWmuR1KyONCN+jaR0w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 30 | 0
%R | 500007 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1840 | Gate Values_1st_Sub |  | 296 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-08-15 08:00 | 2013-09-01 17:00 |  | 2013-06-30 08:00 | 2013-07-16 17:00 | 2013-06-30 08:00 | 2013-07-16 17:00 | 2013-06-30 08:00 | 2013-07-16 17:00 | 2013-08-15 08:00 | 2013-09-01 17:00 |  | PT_Normal |  |  |  |  | RJPtyZrQSAaE9/ziJLcOAQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 30 | 0
%R | 500008 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1860 | Remote Control Value_1st_Sub |  | 296 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-09-02 08:00 | 2013-09-18 17:00 |  | 2013-07-17 08:00 | 2013-08-03 17:00 | 2013-07-17 08:00 | 2013-08-03 17:00 | 2013-07-17 08:00 | 2013-08-03 17:00 | 2013-09-02 08:00 | 2013-09-18 17:00 |  | PT_Normal |  |  |  |  | egVjoAQ1Tyau5WDYvIhCtQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 30 | 0
%R | 500009 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1870 | Irrigation Controller_1st_Sub |  | 296 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-09-19 08:00 | 2013-10-06 17:00 |  | 2013-08-04 08:00 | 2013-08-24 17:00 | 2013-08-04 08:00 | 2013-08-24 17:00 | 2013-08-04 08:00 | 2013-08-24 17:00 | 2013-09-19 08:00 | 2013-10-06 17:00 |  | PT_Normal |  |  |  |  | UV/XMsURThyCzP3MuxtzWg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 30 | 0
%R | 500010 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1850 | Fences_1st_Sub |  | 1008 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-11-12 08:00 | 2013-11-28 17:00 |  | 2013-06-12 08:00 | 2013-06-29 17:00 | 2013-06-12 08:00 | 2013-06-29 17:00 | 2013-06-12 08:00 | 2013-06-29 17:00 | 2013-11-12 08:00 | 2013-11-28 17:00 |  | PT_Normal |  |  |  |  | HPi9gU+oRX+mBHEL3tlzFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:47 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 30 | 0
%R | 500011 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1000 | Anti Termite _1st_Sub |  | 360 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-01-20 08:00 | 2013-01-30 17:00 |  | 2012-11-27 08:00 | 2012-12-08 17:00 | 2012-11-27 08:00 | 2012-12-08 17:00 | 2012-11-27 08:00 | 2012-12-08 17:00 | 2013-01-20 08:00 | 2013-01-30 17:00 |  | PT_Normal |  |  |  |  | HKBperbgRf6aJvd6cMhqoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 20 | 0
%R | 500012 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1020 | Concrete_1st_Sub |  | 312 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-01-14 08:00 | 2013-01-24 17:00 |  | 2012-11-28 08:00 | 2012-12-09 17:00 | 2012-11-28 08:00 | 2012-12-09 17:00 | 2012-11-28 08:00 | 2012-12-09 17:00 | 2013-01-14 08:00 | 2013-01-24 17:00 |  | PT_Normal |  |  |  |  | tBhUPahbRPKnJ7EFFT3vSw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 20 | 0
%R | 500013 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1030 | Waterproofing_1st_Sub |  | 304 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-01-29 08:00 | 2013-02-09 17:00 |  | 2012-12-15 08:00 | 2012-12-26 17:00 | 2012-12-15 08:00 | 2012-12-26 17:00 | 2012-12-15 08:00 | 2012-12-26 17:00 | 2013-01-29 08:00 | 2013-02-09 17:00 |  | PT_Normal |  |  |  |  | 8HSmcqb8SWS0OLnj23/HZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 20 | 0
%R | 500014 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1010 | Block Work_1st_Sub |  | 472 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-02-05 08:00 | 2013-02-17 17:00 |  | 2012-11-27 08:00 | 2012-12-08 17:00 | 2012-11-27 08:00 | 2012-12-08 17:00 | 2012-11-27 08:00 | 2012-12-08 17:00 | 2013-02-05 08:00 | 2013-02-17 17:00 |  | PT_Normal |  |  |  |  | aWiOrVNRQ9CZ+S67LK23/A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 20 | 0
%R | 500015 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1040 | Plastering & Accessories_1st_Sub |  | 584 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-02-27 08:00 | 2013-03-10 17:00 |  | 2012-12-02 08:00 | 2012-12-12 17:00 | 2012-12-02 08:00 | 2012-12-12 17:00 | 2012-12-02 08:00 | 2012-12-12 17:00 | 2013-02-27 08:00 | 2013-03-10 17:00 |  | PT_Normal |  |  |  |  | MgMhw1aQTg2Zn8GJfKfFIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 20 | 0
%R | 500016 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1050 | Thermal Insulation_1st_Sub |  | 696 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-09 08:00 | 2013-04-25 17:00 |  | 2012-12-27 08:00 | 2013-01-13 17:00 | 2012-12-27 08:00 | 2013-01-13 17:00 | 2012-12-27 08:00 | 2013-01-13 17:00 | 2013-04-09 08:00 | 2013-04-25 17:00 |  | PT_Normal |  |  |  |  | 8l9Xz7moRwaAQMdlM7b71Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 500017 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1140 | Pitch roofing_1st_Sub |  | 696 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-27 08:00 | 2013-05-13 17:00 |  | 2013-01-14 08:00 | 2013-01-30 17:00 | 2013-01-14 08:00 | 2013-01-30 17:00 | 2013-01-14 08:00 | 2013-01-30 17:00 | 2013-04-27 08:00 | 2013-05-13 17:00 |  | PT_Normal |  |  |  |  | lAQP8WCOS/OHKEsKuOfuvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 30 | 0
%R | 500018 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1490 | Wooden Doors_1st_Sub |  | 208 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-04-20 08:00 | 2013-04-30 17:00 |  | 2013-03-20 08:00 | 2013-03-31 17:00 | 2013-03-20 08:00 | 2013-03-31 17:00 | 2013-03-20 08:00 | 2013-03-31 17:00 | 2013-04-20 08:00 | 2013-04-30 17:00 |  | PT_Normal |  |  |  |  | NyVJGkG8TgWltDTdqPisnw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 500019 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1440 | PVC Doors_1st_Sub |  | 736 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-07-06 08:00 | 2013-07-16 17:00 |  | 2013-03-20 08:00 | 2013-03-31 17:00 | 2013-03-20 08:00 | 2013-03-31 17:00 | 2013-03-20 08:00 | 2013-03-31 17:00 | 2013-07-06 08:00 | 2013-07-16 17:00 |  | PT_Normal |  |  |  |  | 76H76br2SZq3IAEdBU+w8A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 500020 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1550 | Closets /wardrobe& Pelmets_1st_Sub |  | 344 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-27 08:00 | 2013-06-12 17:00 |  | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-05-27 08:00 | 2013-06-12 17:00 |  | PT_Normal |  |  |  |  | hhIDIEjwQGGCjjwf4LOwTA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 500021 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1560 | Counters, Cabinets & Shelves_1st_Sub |  | 344 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-27 08:00 | 2013-06-12 17:00 |  | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-05-27 08:00 | 2013-06-12 17:00 |  | PT_Normal |  |  |  |  | jPJxVLWxSMC1fTt0mXdVuQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 500022 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1570 | Wooden Hand Rails _1st_Sub |  | 488 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-17 08:00 | 2013-07-03 17:00 |  | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-06-17 08:00 | 2013-07-03 17:00 |  | PT_Normal |  |  |  |  | uBW4M3qRQeuN9LBdN5dyKw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 500023 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1780 | Gazebo Structure_1st_Sub |  | 536 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-08-15 08:00 | 2013-09-01 17:00 |  | 2013-05-26 08:00 | 2013-06-11 17:00 | 2013-05-26 08:00 | 2013-06-11 17:00 | 2013-05-26 08:00 | 2013-06-11 17:00 | 2013-08-15 08:00 | 2013-09-01 17:00 |  | PT_Normal |  |  |  |  | NOKaWfcGRKyMiLDJo38uQw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 500024 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1450 | Ironmongeries_1st_Sub |  | 208 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-04-20 08:00 | 2013-04-30 17:00 |  | 2013-03-20 08:00 | 2013-03-31 17:00 | 2013-03-20 08:00 | 2013-03-31 17:00 | 2013-03-20 08:00 | 2013-03-31 17:00 | 2013-04-20 08:00 | 2013-04-30 17:00 |  | PT_Normal |  |  |  |  | FlTQePuwQGuAxr4yru3Osw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 500025 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1460 | Aluminum Doors _1st_Sub |  | 520 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-04 08:00 | 2013-06-15 17:00 |  | 2013-03-20 08:00 | 2013-03-31 17:00 | 2013-03-20 08:00 | 2013-03-31 17:00 | 2013-03-20 08:00 | 2013-03-31 17:00 | 2013-06-04 08:00 | 2013-06-15 17:00 |  | PT_Normal |  |  |  |  | 0vjwiLKfRB6sSO0DIVkq1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 500026 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1470 | Aluminum Windows_1st_Sub |  | 568 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-11 08:00 | 2013-06-22 17:00 |  | 2013-03-20 08:00 | 2013-03-31 17:00 | 2013-03-20 08:00 | 2013-03-31 17:00 | 2013-03-20 08:00 | 2013-03-31 17:00 | 2013-06-11 08:00 | 2013-06-22 17:00 |  | PT_Normal |  |  |  |  | r+yd50qXSmCmN3KxjJ/10Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 500027 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1480 | Granite_1st_Sub |  | 368 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-05-13 08:00 | 2013-05-23 17:00 |  | 2013-03-20 08:00 | 2013-03-31 17:00 | 2013-03-20 08:00 | 2013-03-31 17:00 | 2013-03-20 08:00 | 2013-03-31 17:00 | 2013-05-13 08:00 | 2013-05-23 17:00 |  | PT_Normal |  |  |  |  | oSWCdZ66RbakNE7mFhE7eA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 500028 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1090 | Cobble stone finish _1st_Sub |  | 584 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-03-11 08:00 | 2013-03-27 17:00 |  | 2012-12-13 08:00 | 2012-12-31 17:00 | 2012-12-13 08:00 | 2012-12-31 17:00 | 2012-12-13 08:00 | 2012-12-31 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 |  | PT_Normal |  |  |  |  | /okdHIO5TA2rBjWrZd24eg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 500029 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1100 | Slate Tile_1st_Sub |  | 584 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-03-11 08:00 | 2013-03-27 17:00 |  | 2012-12-13 08:00 | 2012-12-31 17:00 | 2012-12-13 08:00 | 2012-12-31 17:00 | 2012-12-13 08:00 | 2012-12-31 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 |  | PT_Normal |  |  |  |  | FMj5DRmVQAWaUVOaTTQfCg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 500030 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1110 | Stone Cladding_1st_Sub |  | 584 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-03-11 08:00 | 2013-03-27 17:00 |  | 2012-12-13 08:00 | 2012-12-31 17:00 | 2012-12-13 08:00 | 2012-12-31 17:00 | 2012-12-13 08:00 | 2012-12-31 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 |  | PT_Normal |  |  |  |  | nFmhk7+MTb6UPlmIDJwgQw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 500031 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1300 | Gypsum Board false ceiling_1st_Sub |  | 80 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-03-26 08:00 | 2013-04-06 17:00 |  | 2013-03-14 08:00 | 2013-03-25 17:00 | 2013-03-14 08:00 | 2013-03-25 17:00 | 2013-03-14 08:00 | 2013-03-25 17:00 | 2013-03-26 08:00 | 2013-04-06 17:00 |  | PT_Normal |  |  |  |  | ZMaWTQ0wTqSU8Cy46WyFtg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 500032 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1310 | Aluminum Tile false ceiling_1st_Sub |  | 336 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-02 08:00 | 2013-05-19 17:00 |  | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-03-14 08:00 | 2013-03-31 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 500033 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1390 | GRC Panels_1st_Sub |  | 504 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-21 08:00 | 2013-06-06 17:00 |  | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-05-21 08:00 | 2013-06-06 17:00 |  | PT_Normal |  |  |  |  | 7mRp3/JTQDmfnXeM/hg8Qg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 500034 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1320 | Paints_1st_Sub |  | 80 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-01 08:00 | 2013-04-17 17:00 |  | 2013-03-20 08:00 | 2013-04-06 17:00 | 2013-03-20 08:00 | 2013-04-06 17:00 | 2013-03-20 08:00 | 2013-04-06 17:00 | 2013-04-01 08:00 | 2013-04-17 17:00 |  | PT_Normal |  |  |  |  | 1cRMQ+JdQbysrEyi3hxZYA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 500035 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1420 | Epoxy_1st_Sub |  | 1072 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-09-14 08:00 | 2013-09-30 17:00 |  | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-09-14 08:00 | 2013-09-30 17:00 |  | PT_Normal |  |  |  |  | Zl+sOJ2qTeKzeyIrpWyqVA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 500036 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1430 | Roller Shutter_1st_Sub |  | 232 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-04-20 08:00 | 2013-04-30 17:00 |  | 2013-03-17 08:00 | 2013-03-27 17:00 | 2013-03-17 08:00 | 2013-03-27 17:00 | 2013-03-17 08:00 | 2013-03-27 17:00 | 2013-04-20 08:00 | 2013-04-30 17:00 |  | PT_Normal |  |  |  |  | WEGs/hcUQjWLyj6Srl0qDA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 500037 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1700 | Road Works Materials _1st_Sub |  | 176 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-03 08:00 | 2013-06-19 17:00 |  | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-06-03 08:00 | 2013-06-19 17:00 |  | PT_Normal |  |  |  |  | CgIeeifxQVS6NMLhSHSJEQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 20 | 0
%R | 500038 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1710 | External signage _1st_Sub |  | 1376 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-12-01 08:00 | 2013-12-17 17:00 |  | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-12-01 08:00 | 2013-12-17 17:00 |  | PT_Normal |  |  |  |  | 291Cdw7PRkOFYASDzZSqgQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 20 | 0
%R | 500039 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1720 | Road Marking_1st_Sub |  | 1376 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-12-01 08:00 | 2013-12-17 17:00 |  | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-12-01 08:00 | 2013-12-17 17:00 |  | PT_Normal |  |  |  |  | FIThM7j7SLCi0E0elpDcEA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 20 | 0
%R | 500040 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1600 | kerb works_1st_Sub |  | 320 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-20 08:00 | 2013-06-05 17:00 |  | 2013-04-03 08:00 | 2013-04-20 17:00 | 2013-04-03 08:00 | 2013-04-20 17:00 | 2013-04-03 08:00 | 2013-04-20 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 |  | PT_Normal |  |  |  |  | d7m9wXgsS06+ymofUaApbA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 500041 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1660 | Interlock works_1st_Sub |  | 320 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-23 17:00 |  | 2013-04-21 08:00 | 2013-05-07 17:00 | 2013-04-21 08:00 | 2013-05-07 17:00 | 2013-04-21 08:00 | 2013-05-07 17:00 | 2013-06-06 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | ht0UpetwTH6/FFwj27cCqw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 500042 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1730 | Car Parking Shed_1st_Sub |  | 320 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-24 08:00 | 2013-07-10 17:00 |  | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-06-24 08:00 | 2013-07-10 17:00 |  | PT_Normal |  |  |  |  | Nky5hvFyTTGHMgq0JVM6Cg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 20 | 0
%R | 500043 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1740 | Stone Boulders_1st_Sub |  | 176 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-03 08:00 | 2013-06-19 17:00 |  | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-06-03 08:00 | 2013-06-19 17:00 |  | PT_Normal |  |  |  |  | ejbo+ymqQEmGpBPkWRAP7w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 20 | 0
%R | 500044 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1750 | Speed Humps _1st_Sub |  | 176 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-03 08:00 | 2013-06-19 17:00 |  | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-05-08 08:00 | 2013-05-25 17:00 | 2013-06-03 08:00 | 2013-06-19 17:00 |  | PT_Normal |  |  |  |  | EVThxlyRRjWKmpP4R9iLKQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 20 | 0
%R | 500045 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1790 | Plantation(Grass,Trees)_1st_Sub |  | 176 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-20 08:00 | 2013-07-07 17:00 |  | 2013-05-26 08:00 | 2013-06-11 17:00 | 2013-05-26 08:00 | 2013-06-11 17:00 | 2013-05-26 08:00 | 2013-06-11 17:00 | 2013-06-20 08:00 | 2013-07-07 17:00 |  | PT_Normal |  |  |  |  | Ihg8ysbwRW2Xt/HUPKaBOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 500046 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1820 | Pre-cast Boundary Wall _1st_Sub |  | 320 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-11 08:00 | 2013-07-28 17:00 |  | 2013-05-26 08:00 | 2013-06-11 17:00 | 2013-05-26 08:00 | 2013-06-11 17:00 | 2013-05-26 08:00 | 2013-06-11 17:00 | 2013-07-11 08:00 | 2013-07-28 17:00 |  | PT_Normal |  |  |  |  | GTd+JgkqRBmN50pxbrl7wA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 500047 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1800 | Steel Gate & Barrier gates_1st_Sub |  | 320 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-11 08:00 | 2013-07-28 17:00 |  | 2013-05-26 08:00 | 2013-06-11 17:00 | 2013-05-26 08:00 | 2013-06-11 17:00 | 2013-05-26 08:00 | 2013-06-11 17:00 | 2013-07-11 08:00 | 2013-07-28 17:00 |  | PT_Normal |  |  |  |  | myzyxuXxRzypl3T7ccalew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 500048 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1630 | Steel Ladder_1st_Sub |  | 288 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-27 08:00 | 2013-06-12 17:00 |  | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-05-27 08:00 | 2013-06-12 17:00 |  | PT_Normal |  |  |  |  | VMhjfJ9wT+K6xrhP/zkMFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 500049 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1590 | Manhole Covers and Frames_1st_Sub |  | 504 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-08 08:00 | 2013-06-24 17:00 |  | 2013-03-26 08:00 | 2013-04-11 17:00 | 2013-03-26 08:00 | 2013-04-11 17:00 | 2013-03-26 08:00 | 2013-04-11 17:00 | 2013-06-08 08:00 | 2013-06-24 17:00 |  | PT_Normal |  |  |  |  | hTEssUAWTHGC/P95KYJetw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 500050 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1400 | Access Ladder_1st_Sub |  | 504 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-21 08:00 | 2013-06-06 17:00 |  | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-05-21 08:00 | 2013-06-06 17:00 |  | PT_Normal |  |  |  |  | 81e/gAwnQBu1dlSLASytgQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 500051 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1500 | Steel Door_1st_Sub |  | 232 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-05-01 08:00 | 2013-05-12 17:00 |  | 2013-03-28 08:00 | 2013-04-08 17:00 | 2013-03-28 08:00 | 2013-04-08 17:00 | 2013-03-28 08:00 | 2013-04-08 17:00 | 2013-05-01 08:00 | 2013-05-12 17:00 |  | PT_Normal |  |  |  |  | k59ZIJIsS5emqpA8hBAbtQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 500052 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1580 | Stainless Steel Handrail_1st_Sub |  | 488 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-17 08:00 | 2013-07-03 17:00 |  | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-04-07 08:00 | 2013-04-23 17:00 | 2013-06-17 08:00 | 2013-07-03 17:00 |  | PT_Normal |  |  |  |  | 8vMki393TJW0wVx2IJZTiA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 500053 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1120 | Ceramic Tile_1st_Sub |  | 584 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-03-11 08:00 | 2013-03-27 17:00 |  | 2012-12-13 08:00 | 2012-12-31 17:00 | 2012-12-13 08:00 | 2012-12-31 17:00 | 2012-12-13 08:00 | 2012-12-31 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 |  | PT_Normal |  |  |  |  | yfjw2M78RjWFJ1bnJ0BuTw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 500054 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1130 | Porcelain Tile_1st_Sub |  | 656 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-03-21 08:00 | 2013-04-07 17:00 |  | 2012-12-13 08:00 | 2012-12-31 17:00 | 2012-12-13 08:00 | 2012-12-31 17:00 | 2012-12-13 08:00 | 2012-12-31 17:00 | 2013-03-21 08:00 | 2013-04-07 17:00 |  | PT_Normal |  |  |  |  | kW3n69z0S66wt9xczsrjvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 30 | 0
%R | 500055 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1410 | Aluminum Slat Screen_1st_Sub |  | 648 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-11 08:00 | 2013-06-27 17:00 |  | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-06-11 08:00 | 2013-06-27 17:00 |  | PT_Normal |  |  |  |  | zNQ/IfcpQaGdcRRU/57K4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 500056 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1510 | Stainless Steel Cover_1st_Sub |  | 232 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-05-01 08:00 | 2013-05-12 17:00 |  | 2013-03-28 08:00 | 2013-04-08 17:00 | 2013-03-28 08:00 | 2013-04-08 17:00 | 2013-03-28 08:00 | 2013-04-08 17:00 | 2013-05-01 08:00 | 2013-05-12 17:00 |  | PT_Normal |  |  |  |  | jzrU9lEES+my5akjC0T+xA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 20 | 0
%R | 500057 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1610 | PVC Tent_1st_Sub |  | 224 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-05-06 08:00 | 2013-05-16 17:00 |  | 2013-04-03 08:00 | 2013-04-14 17:00 | 2013-04-03 08:00 | 2013-04-14 17:00 | 2013-04-03 08:00 | 2013-04-14 17:00 | 2013-05-06 08:00 | 2013-05-16 17:00 |  | PT_Normal |  |  |  |  | 9sO0bggyQLOGMg4h9JuQgw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 20 | 0
%R | 500058 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1620 | Structural Steel_1st_Sub |  | 224 | 0 | 80 | 0 | 20 | 20 | 80 | 0 | 0 | 0 |  |  |  | 2013-05-06 08:00 | 2013-05-16 17:00 |  | 2013-04-03 08:00 | 2013-04-14 17:00 | 2013-04-03 08:00 | 2013-04-14 17:00 | 2013-04-03 08:00 | 2013-04-14 17:00 | 2013-05-06 08:00 | 2013-05-16 17:00 |  | PT_Normal |  |  |  |  | Vu5j6ponSpe/1fe+RJEA4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 20 | 0
%R | 500059 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1220 | Water Chiller_1st_Sub |  | 72 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-03-21 08:00 | 2013-04-07 17:00 |  | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-11 08:00 | 2013-03-27 17:00 | 2013-03-21 08:00 | 2013-04-07 17:00 |  | PT_Normal |  |  |  |  | XWkQsZ8QQeCKDEqK+qKR+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 500060 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1330 | Booster Pump_1st_Sub |  | 72 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-08 08:00 | 2013-04-24 17:00 |  | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-03-28 08:00 | 2013-04-14 17:00 | 2013-04-08 08:00 | 2013-04-24 17:00 |  | PT_Normal |  |  |  |  | 4ywkfXpRR4SfdlzJXkQDpA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 30 | 0
%R | 500061 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1520 | Lift Pump_1st_Sub |  | 72 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-04-25 08:00 | 2013-05-12 17:00 |  | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-15 08:00 | 2013-05-01 17:00 | 2013-04-25 08:00 | 2013-05-12 17:00 |  | PT_Normal |  |  |  |  | fMgpQsw+SiWX1b0jXdRyig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 30 | 0
%R | 500062 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1640 | Water meter_1st_Sub |  | 72 | 0 | 120 | 0 | 20 | 20 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-13 08:00 | 2013-05-29 17:00 |  | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-02 08:00 | 2013-05-19 17:00 | 2013-05-13 08:00 | 2013-05-29 17:00 |  | PT_Normal |  |  |  |  | ph9++lC7THqLbeoDtZmNjw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 20 | 0
%R | 500063 | 6359 | 124376 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM1680 | Water Tank_1st_Sub |  | 72 | 0 | 120 | 0 | 30 | 30 | 120 | 0 | 0 | 0 |  |  |  | 2013-05-30 08:00 | 2013-06-16 17:00 |  | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-20 08:00 | 2013-06-05 17:00 | 2013-05-30 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | 5/bvnojRRFC6id1GftfH4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29630 | N | N | 10 | 1ST SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 30 | 0
%R | 500064 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2160 | Copper Pipes_2nd_Sub |  | 432 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-17 08:00 | 2013-06-27 17:00 |  | 2013-04-15 08:00 | 2013-04-25 17:00 | 2013-04-15 08:00 | 2013-04-25 17:00 | 2013-04-15 08:00 | 2013-04-25 17:00 | 2013-06-17 08:00 | 2013-06-27 17:00 |  | PT_Normal |  |  |  |  | uAOGQYLDQ+mGzC4ZfQb+JQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 15 | 0
%R | 500065 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2240 | Split AC_2nd_Sub |  | 672 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-08-08 08:00 | 2013-08-22 17:00 |  | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-08-08 08:00 | 2013-08-22 17:00 |  | PT_Normal |  |  |  |  | ci+SMUOGSE+CJQY9xGUPqg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500066 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2340 | Exhaust Air louver_2nd_Sub |  | 608 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-08-20 08:00 | 2013-08-31 17:00 |  | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-08-20 08:00 | 2013-08-31 17:00 |  | PT_Normal |  |  |  |  | 1lvBHxeoSkKWu8hbNfVggg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500067 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2530 | Exhaust Fan_2nd_Sub |  | 488 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-08-20 08:00 | 2013-08-31 17:00 |  | 2013-06-06 08:00 | 2013-06-17 17:00 | 2013-06-06 08:00 | 2013-06-17 17:00 | 2013-06-06 08:00 | 2013-06-17 17:00 | 2013-08-20 08:00 | 2013-08-31 17:00 |  | PT_Normal |  |  |  |  | YcL4oI0ERNeT7PmPQ4rWUw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 15 | 0
%R | 500068 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2170 | SMDB_2nd_Sub |  | 600 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-07-11 08:00 | 2013-07-22 17:00 |  | 2013-04-15 08:00 | 2013-04-25 17:00 | 2013-04-15 08:00 | 2013-04-25 17:00 | 2013-04-15 08:00 | 2013-04-25 17:00 | 2013-07-11 08:00 | 2013-07-22 17:00 |  | PT_Normal |  |  |  |  | Pekute/pSSqb/zgJVLIwRA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 15 | 0
%R | 500069 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2190 | Lights & Fixtures_2nd_Sub |  | 696 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-07-25 08:00 | 2013-08-05 17:00 |  | 2013-04-15 08:00 | 2013-04-25 17:00 | 2013-04-15 08:00 | 2013-04-25 17:00 | 2013-04-15 08:00 | 2013-04-25 17:00 | 2013-07-25 08:00 | 2013-08-05 17:00 |  | PT_Normal |  |  |  |  | iMMIlg9zRGylNFCxiJU3mg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 15 | 0
%R | 500070 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2200 | Isolators_2nd_Sub |  | 864 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-08-22 08:00 | 2013-09-02 17:00 |  | 2013-04-15 08:00 | 2013-04-25 17:00 | 2013-04-15 08:00 | 2013-04-25 17:00 | 2013-04-15 08:00 | 2013-04-25 17:00 | 2013-08-22 08:00 | 2013-09-02 17:00 |  | PT_Normal |  |  |  |  | 2vZ5u/AwTau58uSUCNA9+A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 15 | 0
%R | 500071 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2250 | Street Light Post Set_2nd_Sub |  | 1000 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-09-29 08:00 | 2013-10-09 17:00 |  | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-09-29 08:00 | 2013-10-09 17:00 |  | PT_Normal |  |  |  |  | vJfJALVCRJumifBWnzjZTg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500072 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2350 | Bollard Lamp_2nd_Sub |  | 880 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-09-29 08:00 | 2013-10-09 17:00 |  | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-09-29 08:00 | 2013-10-09 17:00 |  | PT_Normal |  |  |  |  | CP1NyKeZR4OpqgLSU6Xs2w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500073 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2210 | Fire Resistant Cables_2nd_Sub |  | 840 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-08-19 08:00 | 2013-08-29 17:00 |  | 2013-04-15 08:00 | 2013-04-25 17:00 | 2013-04-15 08:00 | 2013-04-25 17:00 | 2013-04-15 08:00 | 2013-04-25 17:00 | 2013-08-19 08:00 | 2013-08-29 17:00 |  | PT_Normal |  |  |  |  | GODjD1dTQPicsjIKbk/uyg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 15 | 0
%R | 500074 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2260 | Smoke Detector_2nd_Sub |  | 720 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-08-19 08:00 | 2013-08-29 17:00 |  | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-08-19 08:00 | 2013-08-29 17:00 |  | PT_Normal |  |  |  |  | uO1OYItOTwWh4jOJxbbJXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500075 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2360 | Digital Alarm Communicator Panel_2nd_Sub |  | 392 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-07-16 08:00 | 2013-07-27 17:00 |  | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-07-16 08:00 | 2013-07-27 17:00 |  | PT_Normal |  |  |  |  | fI2xeKbsRLGNMSnJnINB6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500076 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2370 | Fire Blanket_2nd_Sub |  | 784 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-09-15 08:00 | 2013-09-25 17:00 |  | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-09-15 08:00 | 2013-09-25 17:00 |  | PT_Normal |  |  |  |  | NDQislaMRsWlxdGHMehFBA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500077 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2380 | Fire Extinguisher_2nd_Sub |  | 720 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-09-05 08:00 | 2013-09-16 17:00 |  | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-09-05 08:00 | 2013-09-16 17:00 |  | PT_Normal |  |  |  |  | hNeBc7x+SMu3wxD5OAeyXQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500078 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2540 | Ductile Iron Pipes_2nd_Sub |  | 40 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-12 08:00 | 2013-06-23 17:00 |  | 2013-06-06 08:00 | 2013-06-17 17:00 | 2013-06-06 08:00 | 2013-06-17 17:00 | 2013-06-06 08:00 | 2013-06-17 17:00 | 2013-06-12 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | 4p+0oHn0Q86/4J/XZLLu/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 15 | 0
%R | 500079 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2650 | Isolating Values_2nd_Sub |  | 32 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-07-09 17:00 |  | 2013-06-24 08:00 | 2013-07-04 17:00 | 2013-06-24 08:00 | 2013-07-04 17:00 | 2013-06-24 08:00 | 2013-07-04 17:00 | 2013-06-29 08:00 | 2013-07-09 17:00 |  | PT_Normal |  |  |  |  | M1ByVVpIQTW9SSrhCaNuIA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:22 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 15 | 0
%R | 500080 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2690 | Fire Hydrant_2nd_Sub |  | 120 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-07-29 08:00 | 2013-08-08 17:00 |  | 2013-07-11 08:00 | 2013-07-22 17:00 | 2013-07-11 08:00 | 2013-07-22 17:00 | 2013-07-11 08:00 | 2013-07-22 17:00 | 2013-07-29 08:00 | 2013-08-08 17:00 |  | PT_Normal |  |  |  |  | Cg3wtHwhQ9q2kiN2Sve3RA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 15 | 0
%R | 500081 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2270 | Video Com System_2nd_Sub |  | 560 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-07-23 08:00 | 2013-08-03 17:00 |  | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-07-23 08:00 | 2013-08-03 17:00 |  | PT_Normal |  |  |  |  | peZJdBmrSV+uHfYyTYYRsw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500082 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2280 | Telephone Fittings & Accessories_2nd_Sub |  | 560 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-07-23 08:00 | 2013-08-03 17:00 |  | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-07-23 08:00 | 2013-08-03 17:00 |  | PT_Normal |  |  |  |  | 4+nVT+haTdKlC8KEzoM0gQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500083 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2290 | Television devices,Fittings & Access._2nd_Sub |  | 792 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-08-29 08:00 | 2013-09-09 17:00 |  | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-08-29 08:00 | 2013-09-09 17:00 |  | PT_Normal |  |  |  |  | iwhLh5B6TyumdT2CDP40Kw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500084 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2670 | Irrigation Pipes_2nd_Sub |  | 608 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-09-12 08:00 | 2013-09-23 17:00 |  | 2013-06-12 08:00 | 2013-06-23 17:00 | 2013-06-12 08:00 | 2013-06-23 17:00 | 2013-06-12 08:00 | 2013-06-23 17:00 | 2013-09-12 08:00 | 2013-09-23 17:00 |  | PT_Normal |  |  |  |  | TNYKhNUGR4i/a9KKA839/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 15 | 0
%R | 500085 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2760 | Sprinklers_2nd_Sub |  | 1104 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-12-14 08:00 | 2013-12-25 17:00 |  | 2013-06-30 08:00 | 2013-07-10 17:00 | 2013-06-30 08:00 | 2013-07-10 17:00 | 2013-06-30 08:00 | 2013-07-10 17:00 | 2013-12-14 08:00 | 2013-12-25 17:00 |  | PT_Normal |  |  |  |  | daS/v5WTRpy0/alX3daZmw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 15 | 0
%R | 500086 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2810 | Nozzle Jet_2nd_Sub |  | 776 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-11-13 08:00 | 2013-11-24 17:00 |  | 2013-07-17 08:00 | 2013-07-28 17:00 | 2013-07-17 08:00 | 2013-07-28 17:00 | 2013-07-17 08:00 | 2013-07-28 17:00 | 2013-11-13 08:00 | 2013-11-24 17:00 |  | PT_Normal |  |  |  |  | 5bf6ijy3TtiE9v1Mn9jQIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 15 | 0
%R | 500087 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2830 | Solenoid Values_2nd_Sub |  | 656 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-11-13 08:00 | 2013-11-24 17:00 |  | 2013-08-04 08:00 | 2013-08-18 17:00 | 2013-08-04 08:00 | 2013-08-18 17:00 | 2013-08-04 08:00 | 2013-08-18 17:00 | 2013-11-13 08:00 | 2013-11-24 17:00 |  | PT_Normal |  |  |  |  | qfU0Pdt2QUq53/jsx3KwPw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 15 | 0
%R | 500088 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2840 | Gate Values_2nd_Sub |  | 536 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-11-13 08:00 | 2013-11-24 17:00 |  | 2013-08-25 08:00 | 2013-09-04 17:00 | 2013-08-25 08:00 | 2013-09-04 17:00 | 2013-08-25 08:00 | 2013-09-04 17:00 | 2013-11-13 08:00 | 2013-11-24 17:00 |  | PT_Normal |  |  |  |  | uX+JPsXpRDixtgGVxDaUew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 15 | 0
%R | 500089 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2860 | Remote Control Value_2nd_Sub |  | 416 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-11-13 08:00 | 2013-11-24 17:00 |  | 2013-09-11 08:00 | 2013-09-22 17:00 | 2013-09-11 08:00 | 2013-09-22 17:00 | 2013-09-11 08:00 | 2013-09-22 17:00 | 2013-11-13 08:00 | 2013-11-24 17:00 |  | PT_Normal |  |  |  |  | CHznwBy4SZWK8G7bJWKhMQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 15 | 0
%R | 500090 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2870 | Irrigation Controller_2nd_Sub |  | 296 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-11-13 08:00 | 2013-11-24 17:00 |  | 2013-09-29 08:00 | 2013-10-09 17:00 | 2013-09-29 08:00 | 2013-10-09 17:00 | 2013-09-29 08:00 | 2013-10-09 17:00 | 2013-11-13 08:00 | 2013-11-24 17:00 |  | PT_Normal |  |  |  |  | 1tk4veiGTvm6+ZcSnsKYlg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 15 | 0
%R | 500091 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2850 | Fences_2nd_Sub |  | 1008 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2014-01-05 08:00 | 2014-01-15 17:00 |  | 2013-08-04 08:00 | 2013-08-18 17:00 | 2013-08-04 08:00 | 2013-08-18 17:00 | 2013-08-04 08:00 | 2013-08-18 17:00 | 2014-01-05 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | wUfa15V/TTKijpl/c+X4gw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:47 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 15 | 0
%R | 500092 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2040 | Plastering & Accessories_2nd_Sub |  | 920 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-03 08:00 | 2013-06-13 17:00 |  | 2013-01-19 08:00 | 2013-01-29 17:00 | 2013-01-19 08:00 | 2013-01-29 17:00 | 2013-01-19 08:00 | 2013-01-29 17:00 | 2013-06-03 08:00 | 2013-06-13 17:00 |  | PT_Normal |  |  |  |  | /hPp7g7qQlizW09VztGUzw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 15 | 0
%R | 500093 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2050 | Thermal Insulation_2nd_Sub |  | 928 | 0 | 120 | 0 | 22.5 | 22.5 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-04 08:00 | 2013-07-21 17:00 |  | 2013-02-19 08:00 | 2013-03-07 17:00 | 2013-02-19 08:00 | 2013-03-07 17:00 | 2013-02-19 08:00 | 2013-03-07 17:00 | 2013-07-04 08:00 | 2013-07-21 17:00 |  | PT_Normal |  |  |  |  | AP0iD93RTwuUx6EkAoCpfg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 22.5 | 0
%R | 500094 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2140 | Pitch roofing_2nd_Sub |  | 696 | 0 | 120 | 0 | 22.5 | 22.5 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-18 08:00 | 2013-07-04 17:00 |  | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-03-09 08:00 | 2013-03-25 17:00 | 2013-06-18 08:00 | 2013-07-04 17:00 |  | PT_Normal |  |  |  |  | WB6ZV8JNR9+srsFwIFlJOg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 22.5 | 0
%R | 500095 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2490 | Wooden Doors_2nd_Sub |  | 208 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-05 08:00 | 2013-06-16 17:00 |  | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-06-05 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | 1NmZDjazRI6pJ/khn0K8Pw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500096 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2440 | PVC Doors_2nd_Sub |  | 736 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-08-25 08:00 | 2013-09-04 17:00 |  | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-08-25 08:00 | 2013-09-04 17:00 |  | PT_Normal |  |  |  |  | kg8uXcE2TMe6/Y7zQWSvWw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500097 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2550 | Closets /wardrobe& Pelmets_2nd_Sub |  | 344 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-07-18 08:00 | 2013-07-29 17:00 |  | 2013-05-29 08:00 | 2013-06-09 17:00 | 2013-05-29 08:00 | 2013-06-09 17:00 | 2013-05-29 08:00 | 2013-06-09 17:00 | 2013-07-18 08:00 | 2013-07-29 17:00 |  | PT_Normal |  |  |  |  | htkvZirGRCO2Z6V2nhvbTg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500098 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2560 | Counters, Cabinets & Shelves_2nd_Sub |  | 344 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-07-18 08:00 | 2013-07-29 17:00 |  | 2013-05-29 08:00 | 2013-06-09 17:00 | 2013-05-29 08:00 | 2013-06-09 17:00 | 2013-05-29 08:00 | 2013-06-09 17:00 | 2013-07-18 08:00 | 2013-07-29 17:00 |  | PT_Normal |  |  |  |  | pQtDkr3EQUGbGlpfy7HlyA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500099 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2570 | Wooden Hand Rails _2nd_Sub |  | 488 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-08-08 08:00 | 2013-08-22 17:00 |  | 2013-05-29 08:00 | 2013-06-09 17:00 | 2013-05-29 08:00 | 2013-06-09 17:00 | 2013-05-29 08:00 | 2013-06-09 17:00 | 2013-08-08 08:00 | 2013-08-22 17:00 |  | PT_Normal |  |  |  |  | RwGfwcWBT6aMb9gr8dUCmA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500100 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2780 | Gazebo Structure_2nd_Sub |  | 536 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-10-07 08:00 | 2013-10-20 17:00 |  | 2013-07-17 08:00 | 2013-07-28 17:00 | 2013-07-17 08:00 | 2013-07-28 17:00 | 2013-07-17 08:00 | 2013-07-28 17:00 | 2013-10-07 08:00 | 2013-10-20 17:00 |  | PT_Normal |  |  |  |  | SToAaYsgSamepC+Ej0wkWw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 15 | 0
%R | 500101 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2450 | Ironmongeries_2nd_Sub |  | 208 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-05 08:00 | 2013-06-16 17:00 |  | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-06-05 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | fRTdVDUbQruecw5B974U7g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500102 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2460 | Aluminum Doors_2nd_Sub |  | 520 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-07-21 08:00 | 2013-07-31 17:00 |  | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-07-21 08:00 | 2013-07-31 17:00 |  | PT_Normal |  |  |  |  | lRhjVPLQTCSCufN/SiUbcw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500103 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2470 | Aluminum Windows_2nd_Sub |  | 568 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-07-28 08:00 | 2013-08-07 17:00 |  | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-07-28 08:00 | 2013-08-07 17:00 |  | PT_Normal |  |  |  |  | GmZLPUAkT62TTgB0FOkDnA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500104 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2480 | Granite_2nd_Sub |  | 368 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-07-09 17:00 |  | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-06-29 08:00 | 2013-07-09 17:00 |  | PT_Normal |  |  |  |  | yryjH7RsQ4mKFhduCaFq2Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500105 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2090 | Cobble stone finish _2nd_Sub |  | 904 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-18 08:00 | 2013-06-29 17:00 |  | 2013-02-05 08:00 | 2013-02-17 17:00 | 2013-02-05 08:00 | 2013-02-17 17:00 | 2013-02-05 08:00 | 2013-02-17 17:00 | 2013-06-18 08:00 | 2013-06-29 17:00 |  | PT_Normal |  |  |  |  | xTKJAoRlSTmiJ079oRuS5w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 15 | 0
%R | 500106 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2100 | Slate Tile_2nd_Sub |  | 944 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-24 08:00 | 2013-07-04 17:00 |  | 2013-02-05 08:00 | 2013-02-17 17:00 | 2013-02-05 08:00 | 2013-02-17 17:00 | 2013-02-05 08:00 | 2013-02-17 17:00 | 2013-06-24 08:00 | 2013-07-04 17:00 |  | PT_Normal |  |  |  |  | FrOsMcmaS8SkE5R1XUlIcA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 15 | 0
%R | 500107 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2110 | Stone Cladding_2nd_Sub |  | 1000 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-07-02 08:00 | 2013-07-13 17:00 |  | 2013-02-05 08:00 | 2013-02-17 17:00 | 2013-02-05 08:00 | 2013-02-17 17:00 | 2013-02-05 08:00 | 2013-02-17 17:00 | 2013-07-02 08:00 | 2013-07-13 17:00 |  | PT_Normal |  |  |  |  | DZpM3iQnSPuwn8WYFGsEWA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 15 | 0
%R | 500108 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2300 | Gypsum Board false ceiling_2nd_Sub |  | 256 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-17 17:00 |  | 2013-04-30 08:00 | 2013-05-11 17:00 | 2013-04-30 08:00 | 2013-05-11 17:00 | 2013-04-30 08:00 | 2013-05-11 17:00 | 2013-06-06 08:00 | 2013-06-17 17:00 |  | PT_Normal |  |  |  |  | sVAyAWOnSEediC5lU7PWWw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 15 | 0
%R | 500109 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2310 | Aluminum Tile false ceiling_2nd_Sub |  | 336 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-24 08:00 | 2013-07-04 17:00 |  | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-05-06 08:00 | 2013-05-16 17:00 | 2013-06-24 08:00 | 2013-07-04 17:00 |  | PT_Normal |  |  |  |  | uLwX5OboSIarUyTe3I67kA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500110 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2390 | GRC Panels_2nd_Sub |  | 592 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-07-25 08:00 | 2013-08-05 17:00 |  | 2013-04-30 08:00 | 2013-05-11 17:00 | 2013-04-30 08:00 | 2013-05-11 17:00 | 2013-04-30 08:00 | 2013-05-11 17:00 | 2013-07-25 08:00 | 2013-08-05 17:00 |  | PT_Normal |  |  |  |  | unIVVFClSWWifIWJPe/PIA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 15 | 0
%R | 500111 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2320 | Paints_2nd_Sub |  | 80 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-05-23 08:00 | 2013-06-03 17:00 |  | 2013-05-12 08:00 | 2013-05-22 17:00 | 2013-05-12 08:00 | 2013-05-22 17:00 | 2013-05-12 08:00 | 2013-05-22 17:00 | 2013-05-23 08:00 | 2013-06-03 17:00 |  | PT_Normal |  |  |  |  | n2g4sYEHQKSJUXINYby+og |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500112 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2420 | Epoxy_2nd_Sub |  | 1072 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-11-07 08:00 | 2013-11-18 17:00 |  | 2013-05-29 08:00 | 2013-06-09 17:00 | 2013-05-29 08:00 | 2013-06-09 17:00 | 2013-05-29 08:00 | 2013-06-09 17:00 | 2013-11-07 08:00 | 2013-11-18 17:00 |  | PT_Normal |  |  |  |  | W6cxKXbtQ/qlopG1MnbSDQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500113 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2430 | Roller Shutter_2nd_Sub |  | 1744 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2014-01-19 08:00 | 2014-01-29 17:00 |  | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-05-02 08:00 | 2013-05-13 17:00 | 2014-01-19 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | eAJib3DRS0ajlLofe+HcWg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500114 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2700 | Road Works Materials _2nd_Sub |  | 1512 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-02-24 17:00 |  | 2013-06-30 08:00 | 2013-07-10 17:00 | 2013-06-30 08:00 | 2013-07-10 17:00 | 2013-06-30 08:00 | 2013-07-10 17:00 | 2014-02-13 08:00 | 2014-02-24 17:00 |  | PT_Normal |  |  |  |  | XpOZj/T9QnmroIo8Y8khvg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 15 | 0
%R | 500115 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2710 | External signage _2nd_Sub |  | 1376 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2014-01-23 08:00 | 2014-02-03 17:00 |  | 2013-06-30 08:00 | 2013-07-10 17:00 | 2013-06-30 08:00 | 2013-07-10 17:00 | 2013-06-30 08:00 | 2013-07-10 17:00 | 2014-01-23 08:00 | 2014-02-03 17:00 |  | PT_Normal |  |  |  |  | yUKzoV13TM6NFGmOH69Eaw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 15 | 0
%R | 500116 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2720 | Road Marking_2nd_Sub |  | 1376 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2014-01-23 08:00 | 2014-02-03 17:00 |  | 2013-06-30 08:00 | 2013-07-10 17:00 | 2013-06-30 08:00 | 2013-07-10 17:00 | 2013-06-30 08:00 | 2013-07-10 17:00 | 2014-01-23 08:00 | 2014-02-03 17:00 |  | PT_Normal |  |  |  |  | U5LWA4LyRYyt/uCAKsoWkw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 15 | 0
%R | 500117 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2600 | kerb works_2nd_Sub |  | 624 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-08-28 08:00 | 2013-09-08 17:00 |  | 2013-05-26 08:00 | 2013-06-05 17:00 | 2013-05-26 08:00 | 2013-06-05 17:00 | 2013-05-26 08:00 | 2013-06-05 17:00 | 2013-08-28 08:00 | 2013-09-08 17:00 |  | PT_Normal |  |  |  |  | eIAf8qW3SQ6EsdK3EBn9Zw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500118 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2660 | Interlock works_2nd_Sub |  | 680 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-09-23 08:00 | 2013-10-03 17:00 |  | 2013-06-12 08:00 | 2013-06-23 17:00 | 2013-06-12 08:00 | 2013-06-23 17:00 | 2013-06-12 08:00 | 2013-06-23 17:00 | 2013-09-23 08:00 | 2013-10-03 17:00 |  | PT_Normal |  |  |  |  | 65bBuUWxSKGUt3o1sMFksQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 15 | 0
%R | 500119 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2730 | Car Parking Shed_2nd_Sub |  | 1016 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-12-01 08:00 | 2013-12-11 17:00 |  | 2013-06-30 08:00 | 2013-07-10 17:00 | 2013-06-30 08:00 | 2013-07-10 17:00 | 2013-06-30 08:00 | 2013-07-10 17:00 | 2013-12-01 08:00 | 2013-12-11 17:00 |  | PT_Normal |  |  |  |  | KJxFwO5ETPikNZ5TMHaDgw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 15 | 0
%R | 500120 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2740 | Stone Boulders_2nd_Sub |  | 1016 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-12-01 08:00 | 2013-12-11 17:00 |  | 2013-06-30 08:00 | 2013-07-10 17:00 | 2013-06-30 08:00 | 2013-07-10 17:00 | 2013-06-30 08:00 | 2013-07-10 17:00 | 2013-12-01 08:00 | 2013-12-11 17:00 |  | PT_Normal |  |  |  |  | oThMtqtHQWKCFWubZAvnZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 15 | 0
%R | 500121 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2750 | Speed Humps _2nd_Sub |  | 1008 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-11-30 08:00 | 2013-12-10 17:00 |  | 2013-06-30 08:00 | 2013-07-10 17:00 | 2013-06-30 08:00 | 2013-07-10 17:00 | 2013-06-30 08:00 | 2013-07-10 17:00 | 2013-11-30 08:00 | 2013-12-10 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 15 | 0
%R | 500122 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2790 | Plantation(Grass,Trees)_2nd_Sub |  | 176 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-08-15 08:00 | 2013-08-26 17:00 |  | 2013-07-17 08:00 | 2013-07-28 17:00 | 2013-07-17 08:00 | 2013-07-28 17:00 | 2013-07-17 08:00 | 2013-07-28 17:00 | 2013-08-15 08:00 | 2013-08-26 17:00 |  | PT_Normal |  |  |  |  | aNRpfXLSStS9rVRvkGnsjw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 15 | 0
%R | 500123 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2820 | Pre-cast Boundary Wall _2nd_Sub |  | 320 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-09-05 08:00 | 2013-09-16 17:00 |  | 2013-07-17 08:00 | 2013-07-28 17:00 | 2013-07-17 08:00 | 2013-07-28 17:00 | 2013-07-17 08:00 | 2013-07-28 17:00 | 2013-09-05 08:00 | 2013-09-16 17:00 |  | PT_Normal |  |  |  |  | 5YEorxACR2+OG3NE8+xsnQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 15 | 0
%R | 500124 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2800 | Steel Gate & Barrier gates_2nd_Sub |  | 504 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-10-02 08:00 | 2013-10-13 17:00 |  | 2013-07-17 08:00 | 2013-07-28 17:00 | 2013-07-17 08:00 | 2013-07-28 17:00 | 2013-07-17 08:00 | 2013-07-28 17:00 | 2013-10-02 08:00 | 2013-10-13 17:00 |  | PT_Normal |  |  |  |  | g4I57hoTRz6ZPjAkLBfLyQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 15 | 0
%R | 500125 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2630 | Steel Ladder_2nd_Sub |  | 288 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-07-18 08:00 | 2013-07-29 17:00 |  | 2013-06-06 08:00 | 2013-06-17 17:00 | 2013-06-06 08:00 | 2013-06-17 17:00 | 2013-06-06 08:00 | 2013-06-17 17:00 | 2013-07-18 08:00 | 2013-07-29 17:00 |  | PT_Normal |  |  |  |  | 2wFJCz/aQyaTY8QbaYm8KA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 15 | 0
%R | 500126 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2590 | Manhole Covers and Frames_2nd_Sub |  | 504 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-07-30 08:00 | 2013-08-13 17:00 |  | 2013-05-18 08:00 | 2013-05-28 17:00 | 2013-05-18 08:00 | 2013-05-28 17:00 | 2013-05-18 08:00 | 2013-05-28 17:00 | 2013-07-30 08:00 | 2013-08-13 17:00 |  | PT_Normal |  |  |  |  | Rvo1T3RcRr+eVl6UojpdEw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500127 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2400 | Access Ladder_2nd_Sub |  | 728 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-08-18 08:00 | 2013-08-28 17:00 |  | 2013-04-30 08:00 | 2013-05-11 17:00 | 2013-04-30 08:00 | 2013-05-11 17:00 | 2013-04-30 08:00 | 2013-05-11 17:00 | 2013-08-18 08:00 | 2013-08-28 17:00 |  | PT_Normal |  |  |  |  | UVv1cyqQTUi6NLZZUd2Wrw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 15 | 0
%R | 500128 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2500 | Steel Door_2nd_Sub |  | 232 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-17 08:00 | 2013-06-27 17:00 |  | 2013-05-14 08:00 | 2013-05-25 17:00 | 2013-05-14 08:00 | 2013-05-25 17:00 | 2013-05-14 08:00 | 2013-05-25 17:00 | 2013-06-17 08:00 | 2013-06-27 17:00 |  | PT_Normal |  |  |  |  | jwxJZbM3TMiIMbxf9hBjUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500129 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2580 | Stainless Steel Handrail_2nd_Sub |  | 488 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-08-08 08:00 | 2013-08-22 17:00 |  | 2013-05-29 08:00 | 2013-06-09 17:00 | 2013-05-29 08:00 | 2013-06-09 17:00 | 2013-05-29 08:00 | 2013-06-09 17:00 | 2013-08-08 08:00 | 2013-08-22 17:00 |  | PT_Normal |  |  |  |  | ijE0EZUGSiOunFFKA8Lw2A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500130 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2120 | Ceramic Tile_2nd_Sub |  | 584 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-05-02 08:00 | 2013-05-13 17:00 |  | 2013-02-05 08:00 | 2013-02-17 17:00 | 2013-02-05 08:00 | 2013-02-17 17:00 | 2013-02-05 08:00 | 2013-02-17 17:00 | 2013-05-02 08:00 | 2013-05-13 17:00 |  | PT_Normal |  |  |  |  | KujlUx6cSQ6PmyOJZMshKw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 15 | 0
%R | 500131 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2130 | Porcelain Tile_2nd_Sub |  | 656 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-05-13 08:00 | 2013-05-23 17:00 |  | 2013-02-05 08:00 | 2013-02-17 17:00 | 2013-02-05 08:00 | 2013-02-17 17:00 | 2013-02-05 08:00 | 2013-02-17 17:00 | 2013-05-13 08:00 | 2013-05-23 17:00 |  | PT_Normal |  |  |  |  | sHV1NvSnSQWGlG2bXEUS7Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 15 | 0
%R | 500132 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2410 | Aluminum Slat Screen_2nd_Sub |  | 648 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-08-03 08:00 | 2013-08-17 17:00 |  | 2013-04-30 08:00 | 2013-05-11 17:00 | 2013-04-30 08:00 | 2013-05-11 17:00 | 2013-04-30 08:00 | 2013-05-11 17:00 | 2013-08-03 08:00 | 2013-08-17 17:00 |  | PT_Normal |  |  |  |  | vxZhp5jSQRSbG9rWMhH32g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 15 | 0
%R | 500133 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2510 | Stainless Steel Cover_2nd_Sub |  | 232 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-17 08:00 | 2013-06-27 17:00 |  | 2013-05-14 08:00 | 2013-05-25 17:00 | 2013-05-14 08:00 | 2013-05-25 17:00 | 2013-05-14 08:00 | 2013-05-25 17:00 | 2013-06-17 08:00 | 2013-06-27 17:00 |  | PT_Normal |  |  |  |  | h+ryDR/bTQqpP0XXqSf1Xg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500134 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2610 | PVC Tent_2nd_Sub |  | 240 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-24 08:00 | 2013-07-04 17:00 |  | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-06-24 08:00 | 2013-07-04 17:00 |  | PT_Normal |  |  |  |  | 4cqp27B/RC+E7a1ttW9TPA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500135 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2620 | Structural Steel_2nd_Sub |  | 224 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-22 08:00 | 2013-07-02 17:00 |  | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-06-22 08:00 | 2013-07-02 17:00 |  | PT_Normal |  |  |  |  | uwY85T+5RGayDA5VzQ6tag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500136 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2220 | Water Chiller_2nd_Sub |  | 400 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-30 08:00 | 2013-07-10 17:00 |  | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-06-30 08:00 | 2013-07-10 17:00 |  | PT_Normal |  |  |  |  | nBRwf1kHQTGZnITAadpalQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500137 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2330 | Booster Pump_2nd_Sub |  | 280 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-30 08:00 | 2013-07-10 17:00 |  | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-05-20 08:00 | 2013-05-30 17:00 | 2013-06-30 08:00 | 2013-07-10 17:00 |  | PT_Normal |  |  |  |  | EsoK58SVQIKHxqUas7vfUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500138 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2520 | Lift Pump_2nd_Sub |  | 160 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-30 08:00 | 2013-07-10 17:00 |  | 2013-06-06 08:00 | 2013-06-17 17:00 | 2013-06-06 08:00 | 2013-06-17 17:00 | 2013-06-06 08:00 | 2013-06-17 17:00 | 2013-06-30 08:00 | 2013-07-10 17:00 |  | PT_Normal |  |  |  |  | WNGIBPILTNOM6lUvj6vfUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 15 | 0
%R | 500139 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2640 | Water meter_2nd_Sub |  | 448 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-09-01 08:00 | 2013-09-11 17:00 |  | 2013-06-24 08:00 | 2013-07-04 17:00 | 2013-06-24 08:00 | 2013-07-04 17:00 | 2013-06-24 08:00 | 2013-07-04 17:00 | 2013-09-01 08:00 | 2013-09-11 17:00 |  | PT_Normal |  |  |  |  | oHymLTmfQOe0QX6CWrcoxg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 15 | 0
%R | 500140 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2680 | Water Tank_2nd_Sub |  | 328 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-09-01 08:00 | 2013-09-11 17:00 |  | 2013-07-11 08:00 | 2013-07-22 17:00 | 2013-07-11 08:00 | 2013-07-22 17:00 | 2013-07-11 08:00 | 2013-07-22 17:00 | 2013-09-01 08:00 | 2013-09-11 17:00 |  | PT_Normal |  |  |  |  | Ao8rgSR7QfyHe7Z1ae8jFQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 15 | 0
%R | 500141 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2770 | Kitchen Water Filter_2nd_Sub |  | 72 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-08-08 08:00 | 2013-08-22 17:00 |  | 2013-07-29 08:00 | 2013-08-08 17:00 | 2013-07-29 08:00 | 2013-08-08 17:00 | 2013-07-29 08:00 | 2013-08-08 17:00 | 2013-08-08 08:00 | 2013-08-22 17:00 |  | PT_Normal |  |  |  |  | QtyHNMdGT6ye1jzFjXcqTQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 15 | 0
%R | 500142 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2150 | Sanitary Fittings_2nd_Sub |  | 408 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-06-13 08:00 | 2013-06-24 17:00 |  | 2013-04-15 08:00 | 2013-04-25 17:00 | 2013-04-15 08:00 | 2013-04-25 17:00 | 2013-04-15 08:00 | 2013-04-25 17:00 | 2013-06-13 08:00 | 2013-06-24 17:00 |  | PT_Normal |  |  |  |  | JNRiA0qJRMaC3EyA0a0/QQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 15 | 0
%R | 500143 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2230 | Water Heater_2nd_Sub |  | 472 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-07-10 08:00 | 2013-07-21 17:00 |  | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-05-02 08:00 | 2013-05-13 17:00 | 2013-07-10 08:00 | 2013-07-21 17:00 |  | PT_Normal |  |  |  |  | iFtnVIgVQ4C4khGhFkR/FA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 15 | 0
%R | 500144 | 6359 | 124377 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTSM2080 | Polyethylene Pipes_2nd_Sub |  | 440 | 0 | 80 | 0 | 15 | 15 | 80 | 0 | 0 | 0 |  |  |  | 2013-04-30 08:00 | 2013-05-11 17:00 |  | 2013-02-25 08:00 | 2013-03-07 17:00 | 2013-02-25 08:00 | 2013-03-07 17:00 | 2013-02-25 08:00 | 2013-03-07 17:00 | 2013-04-30 08:00 | 2013-05-11 17:00 |  | PT_Normal |  |  |  |  | ZVa9QX63Tgum8wKaxtwJow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29650 | N | N | 20 | 2ND SUBMISSION OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 15 | 0
%R | 500145 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2120 | Ceramic Tile_2nd_App |  | 584 | 248 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-14 08:00 | 2013-06-17 17:00 |  | 2013-02-18 08:00 | 2013-03-24 17:00 | 2013-02-18 08:00 | 2013-03-24 17:00 | 2013-02-18 08:00 | 2013-03-24 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 |  | PT_Normal |  |  |  |  | ZWbMK02sSCevHA3YqwLtfQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 500146 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2130 | Porcelain Tile_2nd_App |  | 656 | 248 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-25 08:00 | 2013-06-27 17:00 |  | 2013-02-18 08:00 | 2013-03-24 17:00 | 2013-02-18 08:00 | 2013-03-24 17:00 | 2013-02-18 08:00 | 2013-03-24 17:00 | 2013-05-25 08:00 | 2013-06-27 17:00 |  | PT_Normal |  |  |  |  | WX9YmS4ATfiWPR8RORhmTg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 500147 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2410 | Aluminum Slat Screen_2nd_App |  | 648 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-18 08:00 | 2013-09-21 17:00 |  | 2013-05-12 08:00 | 2013-06-15 17:00 | 2013-05-12 08:00 | 2013-06-15 17:00 | 2013-05-12 08:00 | 2013-06-15 17:00 | 2013-08-18 08:00 | 2013-09-21 17:00 |  | PT_Normal |  |  |  |  | qiZjluVHQx2BHya1AbFAsw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500148 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2510 | Stainless Steel Cover_2nd_App |  | 232 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-08-01 17:00 |  | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-06-29 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | PnBitO/bQ0uF3nOxwIvCZg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500149 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2610 | PVC Tent_2nd_App |  | 240 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-06 08:00 | 2013-08-08 17:00 |  | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-07-06 08:00 | 2013-08-08 17:00 |  | PT_Normal |  |  |  |  | TxinutySRUaQPSkGp/56vA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500150 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2620 | Structural Steel_2nd_App |  | 224 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-03 08:00 | 2013-08-06 17:00 |  | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-07-03 08:00 | 2013-08-06 17:00 |  | PT_Normal |  |  |  |  | hETOEiaRR6GNgCjodPMkeQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500151 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2220 | Water Chiller_2nd_App |  | 400 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-11 08:00 | 2013-08-18 17:00 |  | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-07-11 08:00 | 2013-08-18 17:00 |  | PT_Normal |  |  |  |  | tdfU+Vi5RCWw6WTLFWoIlw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500152 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2330 | Booster Pump_2nd_App |  | 280 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-11 08:00 | 2013-08-18 17:00 |  | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-07-11 08:00 | 2013-08-18 17:00 |  | PT_Normal |  |  |  |  | l3DjWR14Th+JZilh7/b5ZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500153 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2520 | Lift Pump_2nd_App |  | 160 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-11 08:00 | 2013-08-18 17:00 |  | 2013-06-18 08:00 | 2013-07-22 17:00 | 2013-06-18 08:00 | 2013-07-22 17:00 | 2013-06-18 08:00 | 2013-07-22 17:00 | 2013-07-11 08:00 | 2013-08-18 17:00 |  | PT_Normal |  |  |  |  | t04jGlEuQ4u0HRGX+OAD+Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500154 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2640 | Water meter_2nd_App |  | 448 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-12 08:00 | 2013-10-16 17:00 |  | 2013-07-06 08:00 | 2013-08-08 17:00 | 2013-07-06 08:00 | 2013-08-08 17:00 | 2013-07-06 08:00 | 2013-08-08 17:00 | 2013-09-12 08:00 | 2013-10-16 17:00 |  | PT_Normal |  |  |  |  | G6WgscAXSjiDSlvGI5rKCg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 500155 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2680 | Water Tank_2nd_App |  | 328 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-12 08:00 | 2013-10-16 17:00 |  | 2013-07-23 08:00 | 2013-08-29 17:00 | 2013-07-23 08:00 | 2013-08-29 17:00 | 2013-07-23 08:00 | 2013-08-29 17:00 | 2013-09-12 08:00 | 2013-10-16 17:00 |  | PT_Normal |  |  |  |  | WU9ucWLZQBmLdMoIZyPPzA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 500156 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2770 | Kitchen Water Filter_2nd_App |  | 72 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-24 08:00 | 2013-09-26 17:00 |  | 2013-08-13 08:00 | 2013-09-16 17:00 | 2013-08-13 08:00 | 2013-09-16 17:00 | 2013-08-13 08:00 | 2013-09-16 17:00 | 2013-08-24 08:00 | 2013-09-26 17:00 |  | PT_Normal |  |  |  |  | IK4XHHjaSEOT47kRk1awRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 0 | 0
%R | 500157 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2150 | Sanitary Fittings_2nd_App |  | 408 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-25 08:00 | 2013-07-29 17:00 |  | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-06-25 08:00 | 2013-07-29 17:00 |  | PT_Normal |  |  |  |  | fuUfs7NfQ0GEmqd9WLOGSQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500158 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2230 | Water Heater_2nd_App |  | 472 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-22 08:00 | 2013-08-28 17:00 |  | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-07-22 08:00 | 2013-08-28 17:00 |  | PT_Normal |  |  |  |  | ofCKk+s5SK6SgAL20+gdQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500159 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2080 | Polyethylene Pipes_2nd_App |  | 440 | 16 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-12 08:00 | 2013-06-15 17:00 |  | 2013-03-09 08:00 | 2013-04-11 17:00 | 2013-03-09 08:00 | 2013-04-11 17:00 | 2013-03-09 08:00 | 2013-04-11 17:00 | 2013-05-12 08:00 | 2013-06-15 17:00 |  | PT_Normal |  |  |  |  | GyS4RQCDTsCvNrlqvNyKXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500160 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2160 | Copper Pipes_2nd_App |  | 432 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-08-01 17:00 |  | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-06-29 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | 70nGHixcScuuNkKkIR5Y/A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500161 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2240 | Split AC_2nd_App |  | 672 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-24 08:00 | 2013-09-26 17:00 |  | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-08-24 08:00 | 2013-09-26 17:00 |  | PT_Normal |  |  |  |  | bAMnCvq5TD6YpzotheDXQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500162 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2340 | Exhaust Air louver_2nd_App |  | 608 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-01 08:00 | 2013-10-05 17:00 |  | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-09-01 08:00 | 2013-10-05 17:00 |  | PT_Normal |  |  |  |  | ZZFrMzLKTEK8Ed+cy0p33Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500163 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2530 | Exhaust Fan_2nd_App |  | 488 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-01 08:00 | 2013-10-05 17:00 |  | 2013-06-18 08:00 | 2013-07-22 17:00 | 2013-06-18 08:00 | 2013-07-22 17:00 | 2013-06-18 08:00 | 2013-07-22 17:00 | 2013-09-01 08:00 | 2013-10-05 17:00 |  | PT_Normal |  |  |  |  | QccfJ6sPReCACxK8SPRyBA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500164 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2170 | SMDB_2nd_App |  | 600 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-23 08:00 | 2013-08-29 17:00 |  | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-07-23 08:00 | 2013-08-29 17:00 |  | PT_Normal |  |  |  |  | aPhCAjDHSh6CKjuwFpdlEQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500165 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2190 | Lights & Fixtures_2nd_App |  | 696 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-06 08:00 | 2013-09-12 17:00 |  | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-08-06 08:00 | 2013-09-12 17:00 |  | PT_Normal |  |  |  |  | sgxBjf9iSve04rtgVDr/Lw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500166 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2200 | Isolators_2nd_App |  | 864 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-03 08:00 | 2013-10-07 17:00 |  | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-09-03 08:00 | 2013-10-07 17:00 |  | PT_Normal |  |  |  |  | R5b9ErBdTk+bunRTV7ROxA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500167 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2250 | Street Light Post Set_2nd_App |  | 1000 | 520 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2013-11-16 17:00 |  | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-10-10 08:00 | 2013-11-16 17:00 |  | PT_Normal |  |  |  |  | rUHHVDZBSRW7C2cDnxGnMA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500168 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2350 | Bollard Lamp_2nd_App |  | 880 | 160 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2013-11-16 17:00 |  | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-10-10 08:00 | 2013-11-16 17:00 |  | PT_Normal |  |  |  |  | UuR+TXGYRXW9Gw1zQL2KcA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500169 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2210 | Fire Resistant Cables_2nd_App |  | 840 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-31 08:00 | 2013-10-03 17:00 |  | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-04-27 08:00 | 2013-05-30 17:00 | 2013-08-31 08:00 | 2013-10-03 17:00 |  | PT_Normal |  |  |  |  | 2R4GlMVCTlG0jedqcJj/NQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500170 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2260 | Smoke Detector_2nd_App |  | 720 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-31 08:00 | 2013-10-03 17:00 |  | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-08-31 08:00 | 2013-10-03 17:00 |  | PT_Normal |  |  |  |  | 9tKos1DUSK+r+S6f7Ko19Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500171 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2360 | Digital Alarm Communicator Panel_2nd_App |  | 392 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-28 08:00 | 2013-09-03 17:00 |  | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-07-28 08:00 | 2013-09-03 17:00 |  | PT_Normal |  |  |  |  | R83IdQZ5SKujTDdoZlU5FQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500172 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2370 | Fire Blanket_2nd_App |  | 784 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-26 08:00 | 2013-11-02 17:00 |  | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-09-26 08:00 | 2013-11-02 17:00 |  | PT_Normal |  |  |  |  | I2Q6Frd/R26BBJxtEuBpEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500173 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2380 | Fire Extinguisher_2nd_App |  | 720 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-17 08:00 | 2013-10-23 17:00 |  | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-06-01 08:00 | 2013-07-04 17:00 | 2013-09-17 08:00 | 2013-10-23 17:00 |  | PT_Normal |  |  |  |  | BmLgSW/dTaG7ELRY+bkqhw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500174 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2540 | Ductile Iron Pipes_2nd_App |  | 40 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-24 08:00 | 2013-07-28 17:00 |  | 2013-06-18 08:00 | 2013-07-22 17:00 | 2013-06-18 08:00 | 2013-07-22 17:00 | 2013-06-18 08:00 | 2013-07-22 17:00 | 2013-06-24 08:00 | 2013-07-28 17:00 |  | PT_Normal |  |  |  |  | IvWFRQLdRxy5wvocWUMSxg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500175 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2650 | Isolating Values_2nd_App |  | 32 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-10 08:00 | 2013-08-17 17:00 |  | 2013-07-06 08:00 | 2013-08-08 17:00 | 2013-07-06 08:00 | 2013-08-08 17:00 | 2013-07-06 08:00 | 2013-08-08 17:00 | 2013-07-10 08:00 | 2013-08-17 17:00 |  | PT_Normal |  |  |  |  | EK1viainTBuQABGQxCENdQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:22 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 500176 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2690 | Fire Hydrant_2nd_App |  | 120 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-13 08:00 | 2013-09-16 17:00 |  | 2013-07-23 08:00 | 2013-08-29 17:00 | 2013-07-23 08:00 | 2013-08-29 17:00 | 2013-07-23 08:00 | 2013-08-29 17:00 | 2013-08-13 08:00 | 2013-09-16 17:00 |  | PT_Normal |  |  |  |  | lWJ21gnATv6H7bbAIVdqHw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 500177 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2270 | Video Com System_2nd_App |  | 560 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-04 08:00 | 2013-09-10 17:00 |  | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-08-04 08:00 | 2013-09-10 17:00 |  | PT_Normal |  |  |  |  | CPdkg0pxT3mMIdB1vXMK6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500178 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2280 | Telephone Fittings & Accessories_2nd_App |  | 560 | 8 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-04 08:00 | 2013-09-10 17:00 |  | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-08-04 08:00 | 2013-09-10 17:00 |  | PT_Normal |  |  |  |  | EoXXU4kjQ3+E4gW7gHkhTQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500179 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2290 | Television devices,Fittings & Access._2nd_App |  | 792 | 8 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-10 08:00 | 2013-10-14 17:00 |  | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-09-10 08:00 | 2013-10-14 17:00 |  | PT_Normal |  |  |  |  | cHXO1TnTRCO9nibc2VVdwg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500180 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2670 | Irrigation Pipes_2nd_App |  | 608 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-24 08:00 | 2013-10-30 17:00 |  | 2013-06-24 08:00 | 2013-07-28 17:00 | 2013-06-24 08:00 | 2013-07-28 17:00 | 2013-06-24 08:00 | 2013-07-28 17:00 | 2013-09-24 08:00 | 2013-10-30 17:00 |  | PT_Normal |  |  |  |  | cLB6HM9DSVS0zGESeK04gQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500181 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2760 | Sprinklers_2nd_App |  | 1104 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-12-26 08:00 | 2014-01-29 17:00 |  | 2013-07-11 08:00 | 2013-08-18 17:00 | 2013-07-11 08:00 | 2013-08-18 17:00 | 2013-07-11 08:00 | 2013-08-18 17:00 | 2013-12-26 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | rkhthhIdQPORgsKXZ7qfcg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 500182 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2810 | Nozzle Jet_2nd_App |  | 776 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-11-25 08:00 | 2013-12-30 17:00 |  | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-11-25 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | oipesOMoSSef65JG6YUfUQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 500183 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2830 | Solenoid Values_2nd_App |  | 656 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-11-25 08:00 | 2013-12-30 17:00 |  | 2013-08-19 08:00 | 2013-09-22 17:00 | 2013-08-19 08:00 | 2013-09-22 17:00 | 2013-08-19 08:00 | 2013-09-22 17:00 | 2013-11-25 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | t6rpaC9BTJuQPS16Ez4Vdw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 0 | 0
%R | 500184 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2840 | Gate Values_2nd_App |  | 536 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-11-25 08:00 | 2013-12-30 17:00 |  | 2013-09-05 08:00 | 2013-10-09 17:00 | 2013-09-05 08:00 | 2013-10-09 17:00 | 2013-09-05 08:00 | 2013-10-09 17:00 | 2013-11-25 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | yYorHzJsT1CD+gWzlft6bw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 0 | 0
%R | 500185 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2860 | Remote Control Value_2nd_App |  | 416 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-11-25 08:00 | 2013-12-30 17:00 |  | 2013-09-23 08:00 | 2013-10-29 17:00 | 2013-09-23 08:00 | 2013-10-29 17:00 | 2013-09-23 08:00 | 2013-10-29 17:00 | 2013-11-25 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | Ta/xqEnXQ7OuSBygpKmAww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 0 | 0
%R | 500186 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2870 | Irrigation Controller_2nd_App |  | 296 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-11-25 08:00 | 2013-12-30 17:00 |  | 2013-10-10 08:00 | 2013-11-16 17:00 | 2013-10-10 08:00 | 2013-11-16 17:00 | 2013-10-10 08:00 | 2013-11-16 17:00 | 2013-11-25 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | C+tA+rOTRKiEGKlWe85eCA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 0 | 0
%R | 500187 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2850 | Fences_2nd_App |  | 1008 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-02-20 17:00 |  | 2013-08-19 08:00 | 2013-09-22 17:00 | 2013-08-19 08:00 | 2013-09-22 17:00 | 2013-08-19 08:00 | 2013-09-22 17:00 | 2014-01-16 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | 6U0yXXFzTZaxFWePU06CzA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:47 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 0 | 0
%R | 500188 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2040 | Plastering & Accessories_2nd_App |  | 920 | 248 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-15 08:00 | 2013-07-18 17:00 |  | 2013-01-30 08:00 | 2013-03-06 17:00 | 2013-01-30 08:00 | 2013-03-06 17:00 | 2013-01-30 08:00 | 2013-03-06 17:00 | 2013-06-15 08:00 | 2013-07-18 17:00 |  | PT_Normal |  |  |  |  | 414q0rViT+2S+09VgzDD2w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP03 |  | 0 | 0
%R | 500189 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2050 | Thermal Insulation_2nd_App |  | 928 | 56 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-22 08:00 | 2013-08-28 17:00 |  | 2013-03-09 08:00 | 2013-04-11 17:00 | 2013-03-09 08:00 | 2013-04-11 17:00 | 2013-03-09 08:00 | 2013-04-11 17:00 | 2013-07-22 08:00 | 2013-08-28 17:00 |  | PT_Normal |  |  |  |  | BGVsirkCRd+5Eu/t4gkCpQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500190 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2140 | Pitch roofing_2nd_App |  | 696 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-06 08:00 | 2013-08-08 17:00 |  | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-07-06 08:00 | 2013-08-08 17:00 |  | PT_Normal |  |  |  |  | fXtrdwnnRrWVzFqCPT+Dww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500191 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2490 | Wooden Doors_2nd_App |  | 208 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-17 08:00 | 2013-07-21 17:00 |  | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-06-17 08:00 | 2013-07-21 17:00 |  | PT_Normal |  |  |  |  | v6y6eoJkSv21vBPP7snIQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500192 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2440 | PVC Doors_2nd_App |  | 736 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-05 08:00 | 2013-10-09 17:00 |  | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-09-05 08:00 | 2013-10-09 17:00 |  | PT_Normal |  |  |  |  | /Dcpy6igS2WDev0C4OyS5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500193 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2550 | Closets /wardrobe& Pelmets_2nd_App |  | 344 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-30 08:00 | 2013-09-05 17:00 |  | 2013-06-10 08:00 | 2013-07-14 17:00 | 2013-06-10 08:00 | 2013-07-14 17:00 | 2013-06-10 08:00 | 2013-07-14 17:00 | 2013-07-30 08:00 | 2013-09-05 17:00 |  | PT_Normal |  |  |  |  | 7XPaMuIcQR6gTGXnTp4kcA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500194 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2560 | Counters, Cabinets & Shelves_2nd_App |  | 344 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-30 08:00 | 2013-09-05 17:00 |  | 2013-06-10 08:00 | 2013-07-14 17:00 | 2013-06-10 08:00 | 2013-07-14 17:00 | 2013-06-10 08:00 | 2013-07-14 17:00 | 2013-07-30 08:00 | 2013-09-05 17:00 |  | PT_Normal |  |  |  |  | wbJWJi1mTduyWCaTgex8cQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500195 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2570 | Wooden Hand Rails _2nd_App |  | 488 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-24 08:00 | 2013-09-26 17:00 |  | 2013-06-10 08:00 | 2013-07-14 17:00 | 2013-06-10 08:00 | 2013-07-14 17:00 | 2013-06-10 08:00 | 2013-07-14 17:00 | 2013-08-24 08:00 | 2013-09-26 17:00 |  | PT_Normal |  |  |  |  | PDO9yURSSVCyefbPtT6/BA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500196 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2780 | Gazebo Structure_2nd_App |  | 536 | 56 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-21 08:00 | 2013-11-24 17:00 |  | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-10-21 08:00 | 2013-11-24 17:00 |  | PT_Normal |  |  |  |  | 8d6Q1CI7R8i/ItewYbvXRA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 500197 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2450 | Ironmongeries_2nd_App |  | 208 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-17 08:00 | 2013-07-21 17:00 |  | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-06-17 08:00 | 2013-07-21 17:00 |  | PT_Normal |  |  |  |  | jF+d3f3TRXSvMVF6AEPyBQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500198 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2460 | Aluminum Doors_2nd_App |  | 520 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-01 08:00 | 2013-09-08 17:00 |  | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-08-01 08:00 | 2013-09-08 17:00 |  | PT_Normal |  |  |  |  | OJqAkjcCQwCG2J3vng1T7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500199 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2470 | Aluminum Windows_2nd_App |  | 568 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-08 08:00 | 2013-09-15 17:00 |  | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-08-08 08:00 | 2013-09-15 17:00 |  | PT_Normal |  |  |  |  | uhXTqvHlQsiOg6Sd4PFNbA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500200 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2480 | Granite_2nd_App |  | 368 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-10 08:00 | 2013-08-17 17:00 |  | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-07-10 08:00 | 2013-08-17 17:00 |  | PT_Normal |  |  |  |  | n7qpvLRFSKiRV/d1o/4zkg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500201 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2090 | Cobble stone finish _2nd_App |  | 904 | 248 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-30 08:00 | 2013-08-03 17:00 |  | 2013-02-18 08:00 | 2013-03-24 17:00 | 2013-02-18 08:00 | 2013-03-24 17:00 | 2013-02-18 08:00 | 2013-03-24 17:00 | 2013-06-30 08:00 | 2013-08-03 17:00 |  | PT_Normal |  |  |  |  | lxR70aF3TFCjJfK4Z73niw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 500202 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2100 | Slate Tile_2nd_App |  | 944 | 248 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-06 08:00 | 2013-08-08 17:00 |  | 2013-02-18 08:00 | 2013-03-24 17:00 | 2013-02-18 08:00 | 2013-03-24 17:00 | 2013-02-18 08:00 | 2013-03-24 17:00 | 2013-07-06 08:00 | 2013-08-08 17:00 |  | PT_Normal |  |  |  |  | RIVRkkorRg+UHie2Sf0rtQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 500203 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2110 | Stone Cladding_2nd_App |  | 1000 | 72 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-14 08:00 | 2013-08-20 17:00 |  | 2013-02-18 08:00 | 2013-03-24 17:00 | 2013-02-18 08:00 | 2013-03-24 17:00 | 2013-02-18 08:00 | 2013-03-24 17:00 | 2013-07-14 08:00 | 2013-08-20 17:00 |  | PT_Normal |  |  |  |  | 6CwcV4A9TueDY6ZV1cxQAA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 0 | 0
%R | 500204 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2300 | Gypsum Board false ceiling_2nd_App |  | 256 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-18 08:00 | 2013-07-22 17:00 |  | 2013-05-12 08:00 | 2013-06-15 17:00 | 2013-05-12 08:00 | 2013-06-15 17:00 | 2013-05-12 08:00 | 2013-06-15 17:00 | 2013-06-18 08:00 | 2013-07-22 17:00 |  | PT_Normal |  |  |  |  | rF/9RSRKSs2cD76Pq9MlFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500205 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2310 | Aluminum Tile false ceiling_2nd_App |  | 336 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-06 08:00 | 2013-08-08 17:00 |  | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-05-18 08:00 | 2013-06-20 17:00 | 2013-07-06 08:00 | 2013-08-08 17:00 |  | PT_Normal |  |  |  |  | lT3EPEvgTXOL6prV7sIWvA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500206 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2390 | GRC Panels_2nd_App |  | 592 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-06 08:00 | 2013-09-12 17:00 |  | 2013-05-12 08:00 | 2013-06-15 17:00 | 2013-05-12 08:00 | 2013-06-15 17:00 | 2013-05-12 08:00 | 2013-06-15 17:00 | 2013-08-06 08:00 | 2013-09-12 17:00 |  | PT_Normal |  |  |  |  | 9LPSaM38SJCtZ/b4gWtvMQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500207 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2320 | Paints_2nd_App |  | 80 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-04 08:00 | 2013-07-08 17:00 |  | 2013-05-23 08:00 | 2013-06-26 17:00 | 2013-05-23 08:00 | 2013-06-26 17:00 | 2013-05-23 08:00 | 2013-06-26 17:00 | 2013-06-04 08:00 | 2013-07-08 17:00 |  | PT_Normal |  |  |  |  | Zwk/qSBrTm+T2Qghqf4iVg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500208 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2420 | Epoxy_2nd_App |  | 1072 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-11-19 08:00 | 2013-12-24 17:00 |  | 2013-06-10 08:00 | 2013-07-14 17:00 | 2013-06-10 08:00 | 2013-07-14 17:00 | 2013-06-10 08:00 | 2013-07-14 17:00 | 2013-11-19 08:00 | 2013-12-24 17:00 |  | PT_Normal |  |  |  |  | EnxhFaoJQZmZWAwrd00BjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500209 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2430 | Roller Shutter_2nd_App |  | 1744 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-03-06 17:00 |  | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 | 2014-01-30 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | pZDgRZEzTIuRw5BdyBjLOQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500210 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2700 | Road Works Materials_2nd_App |  | 1512 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2014-02-25 08:00 | 2014-03-31 17:00 |  | 2013-07-11 08:00 | 2013-08-18 17:00 | 2013-07-11 08:00 | 2013-08-18 17:00 | 2013-07-11 08:00 | 2013-08-18 17:00 | 2014-02-25 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | iFf+BvPSQ+ex9GUf+r14wQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 500211 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2710 | External signage _2nd_App |  | 1376 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2014-02-04 08:00 | 2014-03-11 17:00 |  | 2013-07-11 08:00 | 2013-08-18 17:00 | 2013-07-11 08:00 | 2013-08-18 17:00 | 2013-07-11 08:00 | 2013-08-18 17:00 | 2014-02-04 08:00 | 2014-03-11 17:00 |  | PT_Normal |  |  |  |  | wpK999nTSGm+BESUt812BA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 500212 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2720 | Road Marking_2nd_App |  | 1376 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2014-02-04 08:00 | 2014-03-11 17:00 |  | 2013-07-11 08:00 | 2013-08-18 17:00 | 2013-07-11 08:00 | 2013-08-18 17:00 | 2013-07-11 08:00 | 2013-08-18 17:00 | 2014-02-04 08:00 | 2014-03-11 17:00 |  | PT_Normal |  |  |  |  | nJ3FX5IFTkmxwXSlJcgObA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 500213 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2600 | kerb works_2nd_App |  | 624 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-09 08:00 | 2013-10-13 17:00 |  | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-09-09 08:00 | 2013-10-13 17:00 |  | PT_Normal |  |  |  |  | HBiGnNkVSAGTjqZ4CGgajQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500214 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2660 | Interlock works_2nd_App |  | 680 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-05 08:00 | 2013-11-10 17:00 |  | 2013-06-24 08:00 | 2013-07-28 17:00 | 2013-06-24 08:00 | 2013-07-28 17:00 | 2013-06-24 08:00 | 2013-07-28 17:00 | 2013-10-05 08:00 | 2013-11-10 17:00 |  | PT_Normal |  |  |  |  | 7TsKFbd+S/m9Duto2GRP3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500215 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2730 | Car Parking Shed_2nd_App |  | 1016 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-12-12 08:00 | 2014-01-16 17:00 |  | 2013-07-11 08:00 | 2013-08-18 17:00 | 2013-07-11 08:00 | 2013-08-18 17:00 | 2013-07-11 08:00 | 2013-08-18 17:00 | 2013-12-12 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | siHQXrnFSjqCgA7dN24T5Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 500216 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2740 | Stone Boulders_2nd_App |  | 1016 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-12-12 08:00 | 2014-01-16 17:00 |  | 2013-07-11 08:00 | 2013-08-18 17:00 | 2013-07-11 08:00 | 2013-08-18 17:00 | 2013-07-11 08:00 | 2013-08-18 17:00 | 2013-12-12 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | /0mayk3lQMmisW64+CaUag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 500217 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2750 | Speed Humps _2nd_App |  | 1008 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-12-11 08:00 | 2014-01-15 17:00 |  | 2013-07-11 08:00 | 2013-08-18 17:00 | 2013-07-11 08:00 | 2013-08-18 17:00 | 2013-07-11 08:00 | 2013-08-18 17:00 | 2013-12-11 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | beHZu5nkSTm/Lr3AUCmleg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 500218 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2790 | Plantation(Grass,Trees)_2nd_App |  | 176 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-27 08:00 | 2013-09-30 17:00 |  | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-08-27 08:00 | 2013-09-30 17:00 |  | PT_Normal |  |  |  |  | Cw6P2ER5QvmM2r0LJe/R0w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 500219 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2820 | Pre-cast Boundary Wall _2nd_App |  | 320 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-17 08:00 | 2013-10-23 17:00 |  | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-09-17 08:00 | 2013-10-23 17:00 |  | PT_Normal |  |  |  |  | hqDO0hCNSZaIvLg8C9lX7Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 500220 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2800 | Steel Gate & Barrier gates_2nd_App |  | 504 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-14 08:00 | 2013-11-19 17:00 |  | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 | 2013-10-14 08:00 | 2013-11-19 17:00 |  | PT_Normal |  |  |  |  | nw+PCnT9RIaslju/pUWR0A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 500221 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2630 | Steel Ladder_2nd_App |  | 288 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-30 08:00 | 2013-09-05 17:00 |  | 2013-06-18 08:00 | 2013-07-22 17:00 | 2013-06-18 08:00 | 2013-07-22 17:00 | 2013-06-18 08:00 | 2013-07-22 17:00 | 2013-07-30 08:00 | 2013-09-05 17:00 |  | PT_Normal |  |  |  |  | QZX1NzXVRnqDmzkwD/76cg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500222 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2590 | Manhole Covers and Frames_2nd_App |  | 504 | 112 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-14 08:00 | 2013-09-17 17:00 |  | 2013-05-29 08:00 | 2013-07-02 17:00 | 2013-05-29 08:00 | 2013-07-02 17:00 | 2013-05-29 08:00 | 2013-07-02 17:00 | 2013-08-14 08:00 | 2013-09-17 17:00 |  | PT_Normal |  |  |  |  | npBhwQhfTai+10v9/lb42w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500223 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2400 | Access Ladder_2nd_App |  | 728 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-29 08:00 | 2013-10-02 17:00 |  | 2013-05-12 08:00 | 2013-06-15 17:00 | 2013-05-12 08:00 | 2013-06-15 17:00 | 2013-05-12 08:00 | 2013-06-15 17:00 | 2013-08-29 08:00 | 2013-10-02 17:00 |  | PT_Normal |  |  |  |  | WF/R++AiToqscXXGy4ppWw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500224 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2500 | Steel Door_2nd_App |  | 232 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-08-01 17:00 |  | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-06-29 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | pfvsdkO4Rl6R5hQ9M3AobA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500225 | 6359 | 124378 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP2580 | Stainless Steel Handrail_2nd_App |  | 488 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-24 08:00 | 2013-09-26 17:00 |  | 2013-06-10 08:00 | 2013-07-14 17:00 | 2013-06-10 08:00 | 2013-07-14 17:00 | 2013-06-10 08:00 | 2013-07-14 17:00 | 2013-08-24 08:00 | 2013-09-26 17:00 |  | PT_Normal |  |  |  |  | iYnRv5UuR6SncNoluC6Tbw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29660 | N | N | 25 | 2ND APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500226 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1150 | Sanitary Fittings_1st_App |  | 408 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-09 08:00 | 2013-06-12 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-05-09 08:00 | 2013-06-12 17:00 |  | PT_Normal |  |  |  |  | 1hbRc7eWQSWZWM42uRv4iA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500227 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1230 | Water Heater_1st_App |  | 472 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-05 08:00 | 2013-07-09 17:00 |  | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-06-05 08:00 | 2013-07-09 17:00 |  | PT_Normal |  |  |  |  | +G1ywzN4SAKK8E/D/18qYw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500228 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1080 | Polyethylene Pipes_1st_App |  | 440 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-03-26 08:00 | 2013-04-29 17:00 |  | 2013-01-20 08:00 | 2013-02-24 17:00 | 2013-01-20 08:00 | 2013-02-24 17:00 | 2013-01-20 08:00 | 2013-02-24 17:00 | 2013-03-26 08:00 | 2013-04-29 17:00 |  | PT_Normal |  |  |  |  | +79Fi16oT9GDoJ463R3lfA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 500229 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1160 | Copper Pipes_1st_App |  | 432 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-13 08:00 | 2013-06-16 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-05-13 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | LmW4JqiIR72c00vCjYR5vg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500230 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1240 | Split AC_1st_App |  | 672 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-04 08:00 | 2013-08-07 17:00 |  | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-07-04 08:00 | 2013-08-07 17:00 |  | PT_Normal |  |  |  |  | liQ3RHz3Qg+xTxZVU9mHpA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500231 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1340 | Exhaust Air louver_1st_App |  | 608 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-13 08:00 | 2013-08-19 17:00 |  | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-07-13 08:00 | 2013-08-19 17:00 |  | PT_Normal |  |  |  |  | yR5Fivu5Qq6fbcg6LrfsHg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500232 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1530 | Exhaust Fan_1st_App |  | 488 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-13 08:00 | 2013-08-19 17:00 |  | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-07-13 08:00 | 2013-08-19 17:00 |  | PT_Normal |  |  |  |  | fTdnY9H1RqyQTqap6I9hXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500233 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1170 | SMDB_1st_App |  | 600 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-07-10 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 |  | PT_Normal |  |  |  |  | ZHvna+w9TsCAo9lplLoWlw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500234 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1180 | Cables & Wires_1st_App |  | 512 | 40 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-25 08:00 | 2013-06-27 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-05-25 08:00 | 2013-06-27 17:00 |  | PT_Normal |  |  |  |  | A1Mx8hTKS+64sbADmO0wXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500235 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1190 | Lights & Fixtures_1st_App |  | 696 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-20 08:00 | 2013-07-24 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-06-20 08:00 | 2013-07-24 17:00 |  | PT_Normal |  |  |  |  | mIcQBx51RFO69kGtgypBUg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500236 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1200 | Isolators_1st_App |  | 864 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-15 08:00 | 2013-08-21 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-07-15 08:00 | 2013-08-21 17:00 |  | PT_Normal |  |  |  |  | MhJLWD7bSyK0GCtznWXgcQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500237 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1250 | Street Light Post Set_1st_App |  | 1000 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-25 08:00 | 2013-09-28 17:00 |  | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-08-25 08:00 | 2013-09-28 17:00 |  | PT_Normal |  |  |  |  | nY/yCUi5TVKKigIU8ICCJA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500238 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1350 | Bollard Lamp_1st_App |  | 880 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-25 08:00 | 2013-09-28 17:00 |  | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-08-25 08:00 | 2013-09-28 17:00 |  | PT_Normal |  |  |  |  | FXe9fnVVQNqEb1bkngdYYw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500239 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1210 | Fire Resistant Cables_1st_App |  | 840 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-11 08:00 | 2013-08-18 17:00 |  | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-03-11 08:00 | 2013-04-14 17:00 | 2013-07-11 08:00 | 2013-08-18 17:00 |  | PT_Normal |  |  |  |  | GtYfDRTwTsyZBEjN1Ne+Xw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500240 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1260 | Smoke Detector_1st_App |  | 720 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-11 08:00 | 2013-08-18 17:00 |  | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-07-11 08:00 | 2013-08-18 17:00 |  | PT_Normal |  |  |  |  | frr3CB7iSuWa2rp4lzIwcA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500241 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1360 | Digital Alarm Communicator Panel_1st_App |  | 392 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-11 08:00 | 2013-07-15 17:00 |  | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-06-11 08:00 | 2013-07-15 17:00 |  | PT_Normal |  |  |  |  | TbCj3u2lSbSipVqBBZkN5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500242 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1370 | Fire Blanket_1st_App |  | 784 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-07 08:00 | 2013-09-14 17:00 |  | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-08-07 08:00 | 2013-09-14 17:00 |  | PT_Normal |  |  |  |  | uejjuo9eSn+C79d+jLawvQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500243 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1380 | Fire Extinguisher_1st_App |  | 720 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-29 08:00 | 2013-09-04 17:00 |  | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 |  | PT_Normal |  |  |  |  | E1ACDW13TvqnV5y1SI2BYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500244 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1540 | Ductile Iron Pipes_1st_App |  | 40 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-08 08:00 | 2013-06-11 17:00 |  | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-08 08:00 | 2013-06-11 17:00 |  | PT_Normal |  |  |  |  | 1XK20PqLQzC+rgUvOb3CLg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:17 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500245 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1650 | Isolating Values_1st_App |  | 32 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-25 08:00 | 2013-06-27 17:00 |  | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-25 08:00 | 2013-06-27 17:00 |  | PT_Normal |  |  |  |  | iL7FhCTsSf6JQqB+jSIa4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:22 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500246 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1690 | Fire Hydrant_1st_App |  | 120 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-24 08:00 | 2013-07-28 17:00 |  | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-24 08:00 | 2013-07-28 17:00 |  | PT_Normal |  |  |  |  | IJBiJ7cnRha1WuMnzZP7mw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500247 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1270 | Video Com System_1st_App |  | 560 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-18 08:00 | 2013-07-22 17:00 |  | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-06-18 08:00 | 2013-07-22 17:00 |  | PT_Normal |  |  |  |  | tHL13z+kTnCScPUwAIE1Kg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500248 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1280 | Telephone Fittings & Accessories_1st_App |  | 560 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-18 08:00 | 2013-07-22 17:00 |  | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-06-18 08:00 | 2013-07-22 17:00 |  | PT_Normal |  |  |  |  | K8Mgq9EvTKGK4b3YQKupdA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500249 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1290 | Television devices,Fittings & Access._1st_App |  | 792 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-22 08:00 | 2013-08-28 17:00 |  | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-07-22 08:00 | 2013-08-28 17:00 |  | PT_Normal |  |  |  |  | tZSHDNzZTmeTBUEWnodOGw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500250 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1670 | Irrigation Pipes_1st_App |  | 608 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-05 08:00 | 2013-09-11 17:00 |  | 2013-05-08 08:00 | 2013-06-11 17:00 | 2013-05-08 08:00 | 2013-06-11 17:00 | 2013-05-08 08:00 | 2013-06-11 17:00 | 2013-08-05 08:00 | 2013-09-11 17:00 |  | PT_Normal |  |  |  |  | XjSAgrihRLSmoG4wDOXzQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500251 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1760 | Sprinklers_1st_App |  | 1104 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-11-09 08:00 | 2013-12-12 17:00 |  | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-11-09 08:00 | 2013-12-12 17:00 |  | PT_Normal |  |  |  |  | wzsUduygQJC32t9E/Z1TBA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500252 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1810 | Nozzle Jet_1st_App |  | 776 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-07 08:00 | 2013-11-12 17:00 |  | 2013-06-12 08:00 | 2013-07-16 17:00 | 2013-06-12 08:00 | 2013-07-16 17:00 | 2013-06-12 08:00 | 2013-07-16 17:00 | 2013-10-07 08:00 | 2013-11-12 17:00 |  | PT_Normal |  |  |  |  | Pw88qm66TFWMGZvuWDBwcQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500253 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1830 | Solenoid Values_1st_App |  | 656 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-07 08:00 | 2013-11-12 17:00 |  | 2013-06-30 08:00 | 2013-08-03 17:00 | 2013-06-30 08:00 | 2013-08-03 17:00 | 2013-06-30 08:00 | 2013-08-03 17:00 | 2013-10-07 08:00 | 2013-11-12 17:00 |  | PT_Normal |  |  |  |  | FT3BwrssRCeYW5j3wAamvA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500254 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1840 | Gate Values_1st_App |  | 536 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-07 08:00 | 2013-11-12 17:00 |  | 2013-07-17 08:00 | 2013-08-24 17:00 | 2013-07-17 08:00 | 2013-08-24 17:00 | 2013-07-17 08:00 | 2013-08-24 17:00 | 2013-10-07 08:00 | 2013-11-12 17:00 |  | PT_Normal |  |  |  |  | lz6vdASRTOmrU5liaWYU/Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 0 | 0
%R | 500255 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1860 | Remote Control Value_1st_App |  | 416 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-07 08:00 | 2013-11-12 17:00 |  | 2013-08-04 08:00 | 2013-09-10 17:00 | 2013-08-04 08:00 | 2013-09-10 17:00 | 2013-08-04 08:00 | 2013-09-10 17:00 | 2013-10-07 08:00 | 2013-11-12 17:00 |  | PT_Normal |  |  |  |  | s0/2Ugv5RQCFovzS6LRjzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 0 | 0
%R | 500256 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1870 | Irrigation Controller_1st_App |  | 296 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-07 08:00 | 2013-11-12 17:00 |  | 2013-08-25 08:00 | 2013-09-28 17:00 | 2013-08-25 08:00 | 2013-09-28 17:00 | 2013-08-25 08:00 | 2013-09-28 17:00 | 2013-10-07 08:00 | 2013-11-12 17:00 |  | PT_Normal |  |  |  |  | GvEJn70HSB66JL0ataLz+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 0 | 0
%R | 500257 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1850 | Fences_1st_App |  | 1008 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-11-30 08:00 | 2014-01-04 17:00 |  | 2013-06-30 08:00 | 2013-08-03 17:00 | 2013-06-30 08:00 | 2013-08-03 17:00 | 2013-06-30 08:00 | 2013-08-03 17:00 | 2013-11-30 08:00 | 2014-01-04 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:47 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500258 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1000 | Anti Termite _1st_App |  | 360 | 0 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 |  |  |  | 2013-01-31 08:00 | 2013-02-18 17:00 |  | 2012-12-09 08:00 | 2012-12-26 17:00 | 2012-12-09 08:00 | 2012-12-26 17:00 | 2012-12-09 08:00 | 2012-12-26 17:00 | 2013-01-31 08:00 | 2013-02-18 17:00 |  | PT_Normal |  |  |  |  | cYpzNU/kTPSm9Y6boNf+Gg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 500259 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1020 | Concrete_1st_App |  | 312 | 0 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 |  |  |  | 2013-01-26 08:00 | 2013-02-11 17:00 |  | 2012-12-10 08:00 | 2012-12-27 17:00 | 2012-12-10 08:00 | 2012-12-27 17:00 | 2012-12-10 08:00 | 2012-12-27 17:00 | 2013-01-26 08:00 | 2013-02-11 17:00 |  | PT_Normal |  |  |  |  | 15O9KZRETpSuLTsLXvwPpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 500260 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1030 | Waterproofing_1st_App |  | 304 | 0 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 |  |  |  | 2013-02-10 08:00 | 2013-02-27 17:00 |  | 2012-12-27 08:00 | 2013-01-13 17:00 | 2012-12-27 08:00 | 2013-01-13 17:00 | 2012-12-27 08:00 | 2013-01-13 17:00 | 2013-02-10 08:00 | 2013-02-27 17:00 |  | PT_Normal |  |  |  |  | JQS1Gm/VS/iyuppTGLSnag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 500261 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1010 | Block Work_1st_App |  | 472 | 0 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 |  |  |  | 2013-02-11 08:00 | 2013-03-12 17:00 |  | 2012-12-03 08:00 | 2013-01-01 17:00 | 2012-12-03 08:00 | 2013-01-01 17:00 | 2012-12-03 08:00 | 2013-01-01 17:00 | 2013-02-11 08:00 | 2013-03-12 17:00 |  | PT_Normal |  |  |  |  | FU+LDhTQTNqtePpCrM2Hog |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 500262 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1040 | Plastering & Accessories_1st_App |  | 920 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-29 08:00 | 2013-06-02 17:00 |  | 2012-12-13 08:00 | 2013-01-17 17:00 | 2012-12-13 08:00 | 2013-01-17 17:00 | 2012-12-13 08:00 | 2013-01-17 17:00 | 2013-04-29 08:00 | 2013-06-02 17:00 |  | PT_Normal |  |  |  |  | L9s9p5ozQPW9yxxSFOkaOw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12; period 2: 2013-AP01 |  | 0 | 0
%R | 500263 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1050 | Thermal Insulation_1st_App |  | 928 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-30 08:00 | 2013-07-03 17:00 |  | 2013-01-14 08:00 | 2013-02-18 17:00 | 2013-01-14 08:00 | 2013-02-18 17:00 | 2013-01-14 08:00 | 2013-02-18 17:00 | 2013-05-30 08:00 | 2013-07-03 17:00 |  | PT_Normal |  |  |  |  | sRrOTOWeRQO6nDXncgWaRA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 500264 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1140 | Pitch roofing_1st_App |  | 696 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-14 08:00 | 2013-06-17 17:00 |  | 2013-01-31 08:00 | 2013-03-07 17:00 | 2013-01-31 08:00 | 2013-03-07 17:00 | 2013-01-31 08:00 | 2013-03-07 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 |  | PT_Normal |  |  |  |  | jorN5OFSR6epsOPn99bb0w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP03 |  | 0 | 0
%R | 500265 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1490 | Wooden Doors_1st_App |  | 208 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-01 08:00 | 2013-06-04 17:00 |  | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-05-01 08:00 | 2013-06-04 17:00 |  | PT_Normal |  |  |  |  | uylFb0eXSHCi5sLJc4fj5Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500266 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1440 | PVC Doors_1st_App |  | 736 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-17 08:00 | 2013-08-24 17:00 |  | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-07-17 08:00 | 2013-08-24 17:00 |  | PT_Normal |  |  |  |  | HFBw77i6QbKlm8zW2YRMyA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500267 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1550 | Closets /wardrobe& Pelmets_1st_App |  | 344 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-13 08:00 | 2013-07-17 17:00 |  | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-06-13 08:00 | 2013-07-17 17:00 |  | PT_Normal |  |  |  |  | uL+JbQZXSbuBCndxEufBug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500268 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1560 | Counters, Cabinets & Shelves_1st_App |  | 344 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-13 08:00 | 2013-07-17 17:00 |  | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-06-13 08:00 | 2013-07-17 17:00 |  | PT_Normal |  |  |  |  | JXQIhkHuS5myn/z4sRYAXw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500269 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1570 | Wooden Hand Rails _1st_App |  | 488 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-04 08:00 | 2013-08-07 17:00 |  | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-07-04 08:00 | 2013-08-07 17:00 |  | PT_Normal |  |  |  |  | 5NP181ttQjiUGdPwNpiWoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500270 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1780 | Gazebo Structure_1st_App |  | 536 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-09-02 08:00 | 2013-10-06 17:00 |  | 2013-06-12 08:00 | 2013-07-16 17:00 | 2013-06-12 08:00 | 2013-07-16 17:00 | 2013-06-12 08:00 | 2013-07-16 17:00 | 2013-09-02 08:00 | 2013-10-06 17:00 |  | PT_Normal |  |  |  |  | jik5fqMcRbmii0VQjElcGA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500271 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1450 | Ironmongeries_1st_App |  | 208 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-01 08:00 | 2013-06-04 17:00 |  | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-05-01 08:00 | 2013-06-04 17:00 |  | PT_Normal |  |  |  |  | GXdXEFPtT8SLEtufga67rw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500272 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1460 | Aluminum Doors_1st_App |  | 520 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-16 08:00 | 2013-07-20 17:00 |  | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-06-16 08:00 | 2013-07-20 17:00 |  | PT_Normal |  |  |  |  | Aa4BWtTaT0aVbw0VhYu6rw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500273 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1470 | Aluminum Windows_1st_App |  | 568 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-23 08:00 | 2013-07-27 17:00 |  | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-06-23 08:00 | 2013-07-27 17:00 |  | PT_Normal |  |  |  |  | yso1x3m1QWyftH9WHUmreg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500274 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1480 | Granite_1st_App |  | 368 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-25 08:00 | 2013-06-27 17:00 |  | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-05-25 08:00 | 2013-06-27 17:00 |  | PT_Normal |  |  |  |  | s4JFi8BzQMy/HwDTJrB3TA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500275 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1090 | Cobble stone finish _1st_App |  | 904 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-14 08:00 | 2013-06-17 17:00 |  | 2013-01-01 08:00 | 2013-02-04 17:00 | 2013-01-01 08:00 | 2013-02-04 17:00 | 2013-01-01 08:00 | 2013-02-04 17:00 | 2013-05-14 08:00 | 2013-06-17 17:00 |  | PT_Normal |  |  |  |  | JIyXWrqKT0apo7n7E+m6XA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP01 |  | 0 | 0
%R | 500276 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1100 | Slate Tile_1st_App |  | 944 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-20 08:00 | 2013-06-23 17:00 |  | 2013-01-01 08:00 | 2013-02-04 17:00 | 2013-01-01 08:00 | 2013-02-04 17:00 | 2013-01-01 08:00 | 2013-02-04 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | fmSx2mFWThen0NcrMPqB0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP01 |  | 0 | 0
%R | 500277 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1110 | Stone Cladding_1st_App |  | 1000 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-28 08:00 | 2013-07-01 17:00 |  | 2013-01-01 08:00 | 2013-02-04 17:00 | 2013-01-01 08:00 | 2013-02-04 17:00 | 2013-01-01 08:00 | 2013-02-04 17:00 | 2013-05-28 08:00 | 2013-07-01 17:00 |  | PT_Normal |  |  |  |  | sA2lehVPROmAQagYBoD47A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP01 |  | 0 | 0
%R | 500278 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1300 | Gypsum Board false ceiling_1st_App |  | 256 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-02 08:00 | 2013-06-05 17:00 |  | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 |  | PT_Normal |  |  |  |  | eS9dYdgtRHuj1WKsFkgMBA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500279 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1310 | Aluminum Tile false ceiling_1st_App |  | 336 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-20 08:00 | 2013-06-23 17:00 |  | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-04-01 08:00 | 2013-05-05 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | PbaSAxrUT3SkfsdRoLiaGw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500280 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1390 | GRC Panels_1st_App |  | 592 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-20 08:00 | 2013-07-24 17:00 |  | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-06-20 08:00 | 2013-07-24 17:00 |  | PT_Normal |  |  |  |  | gD68u/98RBOJoB26sHZWHQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500281 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1320 | Paints_1st_App |  | 80 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-18 08:00 | 2013-05-22 17:00 |  | 2013-04-07 08:00 | 2013-05-11 17:00 | 2013-04-07 08:00 | 2013-05-11 17:00 | 2013-04-07 08:00 | 2013-05-11 17:00 | 2013-04-18 08:00 | 2013-05-22 17:00 |  | PT_Normal |  |  |  |  | IiSb053EQtGRGjOpkHd9WQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500282 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1420 | Epoxy_1st_App |  | 1072 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-01 08:00 | 2013-11-06 17:00 |  | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-10-01 08:00 | 2013-11-06 17:00 |  | PT_Normal |  |  |  |  | dFqvhtjlR7a31FUFLSyOKA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500283 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1430 | Roller Shutter_1st_App |  | 1744 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-12-14 08:00 | 2014-01-18 17:00 |  | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-12-14 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | BezmeZhVTSmtCaqa90G0Jw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500284 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1700 | Road Works Materials _1st_App |  | 1512 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2014-01-08 08:00 | 2014-02-12 17:00 |  | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 | 2014-01-08 08:00 | 2014-02-12 17:00 |  | PT_Normal |  |  |  |  | 2T1rGqU9S5yqTkpRnE7mXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500285 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1710 | External signage _1st_App |  | 1376 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-12-19 08:00 | 2014-01-22 17:00 |  | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-12-19 08:00 | 2014-01-22 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500286 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1720 | Road Marking_1st_App |  | 1376 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-12-19 08:00 | 2014-01-22 17:00 |  | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-12-19 08:00 | 2014-01-22 17:00 |  | PT_Normal |  |  |  |  | RCJlbrhMRtKeb3TauYF7aQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500287 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1600 | kerb works_1st_App |  | 624 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-21 08:00 | 2013-08-27 17:00 |  | 2013-04-21 08:00 | 2013-05-25 17:00 | 2013-04-21 08:00 | 2013-05-25 17:00 | 2013-04-21 08:00 | 2013-05-25 17:00 | 2013-07-21 08:00 | 2013-08-27 17:00 |  | PT_Normal |  |  |  |  | 0NEYRbXDTICQkmzVxgmtpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500288 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1660 | Interlock works_1st_App |  | 680 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-19 08:00 | 2013-09-22 17:00 |  | 2013-05-08 08:00 | 2013-06-11 17:00 | 2013-05-08 08:00 | 2013-06-11 17:00 | 2013-05-08 08:00 | 2013-06-11 17:00 | 2013-08-19 08:00 | 2013-09-22 17:00 |  | PT_Normal |  |  |  |  | rhgD1kr/Sj2vEa7NXX+jlw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500289 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1730 | Car Parking Shed_1st_App |  | 1016 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-27 08:00 | 2013-11-30 17:00 |  | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-10-27 08:00 | 2013-11-30 17:00 |  | PT_Normal |  |  |  |  | Gs1iNxOfRwm4+lUHWjTZ+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500290 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1740 | Stone Boulders_1st_App |  | 1016 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-27 08:00 | 2013-11-30 17:00 |  | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-10-27 08:00 | 2013-11-30 17:00 |  | PT_Normal |  |  |  |  | WIL5WrKOQ7KEDc2RI64rUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500291 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1750 | Speed Humps _1st_App |  | 1008 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-10-26 08:00 | 2013-11-28 17:00 |  | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 | 2013-10-26 08:00 | 2013-11-28 17:00 |  | PT_Normal |  |  |  |  | evBPpckpTOOBT+ZH/XEtOw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500292 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1790 | Plantation(Grass,Trees)_1st_App |  | 176 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-08 08:00 | 2013-08-14 17:00 |  | 2013-06-12 08:00 | 2013-07-16 17:00 | 2013-06-12 08:00 | 2013-07-16 17:00 | 2013-06-12 08:00 | 2013-07-16 17:00 | 2013-07-08 08:00 | 2013-08-14 17:00 |  | PT_Normal |  |  |  |  | 7Qjum07gRzOligimvo8Zew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500293 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1820 | Pre-cast Boundary Wall _1st_App |  | 320 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-29 08:00 | 2013-09-04 17:00 |  | 2013-06-12 08:00 | 2013-07-16 17:00 | 2013-06-12 08:00 | 2013-07-16 17:00 | 2013-06-12 08:00 | 2013-07-16 17:00 | 2013-07-29 08:00 | 2013-09-04 17:00 |  | PT_Normal |  |  |  |  | 9dsj+33xQVuIQNYCqu67Mw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:45 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500294 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1800 | Steel Gate & Barrier gates_1st_App |  | 504 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-08-28 08:00 | 2013-10-01 17:00 |  | 2013-06-12 08:00 | 2013-07-16 17:00 | 2013-06-12 08:00 | 2013-07-16 17:00 | 2013-06-12 08:00 | 2013-07-16 17:00 | 2013-08-28 08:00 | 2013-10-01 17:00 |  | PT_Normal |  |  |  |  | 1/l6f9wkQDOLtsHjvoI6Nw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500295 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1630 | Steel Ladder_1st_App |  | 288 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-13 08:00 | 2013-07-17 17:00 |  | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-06-13 08:00 | 2013-07-17 17:00 |  | PT_Normal |  |  |  |  | F7l6A9exR7yEpvhmgYPTRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500296 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1590 | Manhole Covers and Frames_1st_App |  | 504 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-25 08:00 | 2013-07-29 17:00 |  | 2013-04-13 08:00 | 2013-05-16 17:00 | 2013-04-13 08:00 | 2013-05-16 17:00 | 2013-04-13 08:00 | 2013-05-16 17:00 | 2013-06-25 08:00 | 2013-07-29 17:00 |  | PT_Normal |  |  |  |  | daa3IH/8R+aq2yaEro+t8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500297 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1400 | Access Ladder_1st_App |  | 728 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-10 08:00 | 2013-08-17 17:00 |  | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-07-10 08:00 | 2013-08-17 17:00 |  | PT_Normal |  |  |  |  | 5jr7xix3RS2Ymmy1cH0+yw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500298 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1500 | Steel Door_1st_App |  | 232 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-13 08:00 | 2013-06-16 17:00 |  | 2013-04-09 08:00 | 2013-05-13 17:00 | 2013-04-09 08:00 | 2013-05-13 17:00 | 2013-04-09 08:00 | 2013-05-13 17:00 | 2013-05-13 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | vPpV6dx2Sg6k7fvQZepZAQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500299 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1580 | Stainless Steel Handrail_1st_App |  | 488 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-04 08:00 | 2013-08-07 17:00 |  | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-04-24 08:00 | 2013-05-28 17:00 | 2013-07-04 08:00 | 2013-08-07 17:00 |  | PT_Normal |  |  |  |  | dlnWQ3jHSKGN1f89af2ojw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500300 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1120 | Ceramic Tile_1st_App |  | 584 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-03-28 08:00 | 2013-05-01 17:00 |  | 2013-01-01 08:00 | 2013-02-04 17:00 | 2013-01-01 08:00 | 2013-02-04 17:00 | 2013-01-01 08:00 | 2013-02-04 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 |  | PT_Normal |  |  |  |  | mHS6yjx+QrOB0B5oTYdeAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP01 |  | 0 | 0
%R | 500301 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1130 | Porcelain Tile_1st_App |  | 656 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-04-08 08:00 | 2013-05-12 17:00 |  | 2013-01-01 08:00 | 2013-02-04 17:00 | 2013-01-01 08:00 | 2013-02-04 17:00 | 2013-01-01 08:00 | 2013-02-04 17:00 | 2013-04-08 08:00 | 2013-05-12 17:00 |  | PT_Normal |  |  |  |  | odSub0RDQpmp+Rx4KL7Evw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP01 |  | 0 | 0
%R | 500302 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1410 | Aluminum Slat Screen_1st_App |  | 648 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-06-29 08:00 | 2013-08-01 17:00 |  | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-03-26 08:00 | 2013-04-29 17:00 | 2013-06-29 08:00 | 2013-08-01 17:00 |  | PT_Normal |  |  |  |  | LFIlOOp0R6GXkFaROHOV0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500303 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1510 | Stainless Steel Cover_1st_App |  | 232 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-13 08:00 | 2013-06-16 17:00 |  | 2013-04-09 08:00 | 2013-05-13 17:00 | 2013-04-09 08:00 | 2013-05-13 17:00 | 2013-04-09 08:00 | 2013-05-13 17:00 | 2013-05-13 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | u0WFLRYVSVC48//XKmzSeg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500304 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1610 | PVC Tent_1st_App |  | 240 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-20 08:00 | 2013-06-23 17:00 |  | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | HZJwfjyUTe29RJhJD44Afg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500305 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1620 | Structural Steel_1st_App |  | 224 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-18 08:00 | 2013-06-20 17:00 |  | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-05-18 08:00 | 2013-06-20 17:00 |  | PT_Normal |  |  |  |  | eAuRS+tGSeef/PZz3//swQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500306 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1220 | Water Chiller_1st_App |  | 400 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-26 08:00 | 2013-06-29 17:00 |  | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-03-28 08:00 | 2013-05-01 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 |  | PT_Normal |  |  |  |  | icxwO0noRgijCTGFDFakiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03; period 2: 2013-AP04 |  | 0 | 0
%R | 500307 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1330 | Booster Pump_1st_App |  | 280 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-26 08:00 | 2013-06-29 17:00 |  | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-04-15 08:00 | 2013-05-19 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 |  | PT_Normal |  |  |  |  | I3quOoDITeCQXdjAx7J45A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04; period 2: 2013-AP05 |  | 0 | 0
%R | 500308 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1520 | Lift Pump_1st_App |  | 160 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-05-26 08:00 | 2013-06-29 17:00 |  | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-02 08:00 | 2013-06-05 17:00 | 2013-05-26 08:00 | 2013-06-29 17:00 |  | PT_Normal |  |  |  |  | KWLsJE9oQA+hp19w+YvjNw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500309 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1640 | Water meter_1st_App |  | 448 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-24 08:00 | 2013-08-31 17:00 |  | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-05-20 08:00 | 2013-06-23 17:00 | 2013-07-24 08:00 | 2013-08-31 17:00 |  | PT_Normal |  |  |  |  | w/y2jXbDQ/qRqeNw848nfQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05; period 2: 2013-AP06 |  | 0 | 0
%R | 500310 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1680 | Water Tank_1st_App |  | 328 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-24 08:00 | 2013-08-31 17:00 |  | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-06-06 08:00 | 2013-07-10 17:00 | 2013-07-24 08:00 | 2013-08-31 17:00 |  | PT_Normal |  |  |  |  | Aq7gunLTTdq/HVXRN2V+IQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500311 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1770 | Kitchen Water Filter_1st_App |  | 72 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-07-04 08:00 | 2013-08-07 17:00 |  | 2013-06-24 08:00 | 2013-07-28 17:00 | 2013-06-24 08:00 | 2013-07-28 17:00 | 2013-06-24 08:00 | 2013-07-28 17:00 | 2013-07-04 08:00 | 2013-08-07 17:00 |  | PT_Normal |  |  |  |  | V0fFK02sRZO11Q0gksB8oA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06; period 2: 2013-AP07 |  | 0 | 0
%R | 500312 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1060 | UPVC Pipes_1st_App |  | 224 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-02-23 08:00 | 2013-03-28 17:00 |  | 2013-01-20 08:00 | 2013-02-24 17:00 | 2013-01-20 08:00 | 2013-02-24 17:00 | 2013-01-20 08:00 | 2013-02-24 17:00 | 2013-02-23 08:00 | 2013-03-28 17:00 |  | PT_Normal |  |  |  |  | vUO6E/+BQRm98HfoDCReaw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 500313 | 6359 | 124379 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHPROGEN00MTAP1070 | Floor drains & Cleanouts_1st_App |  | 224 | 0 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  |  |  | 2013-02-23 08:00 | 2013-03-28 17:00 |  | 2013-01-20 08:00 | 2013-02-24 17:00 | 2013-01-20 08:00 | 2013-02-24 17:00 | 2013-01-20 08:00 | 2013-02-24 17:00 | 2013-02-23 08:00 | 2013-03-28 17:00 |  | PT_Normal |  |  |  |  | ApAQi1xIRG2DsuwWR5mg7g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29640 | N | N | 15 | 1ST APPROVAL OF MATERIAL |  | 124375 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01; period 2: 2013-AP02 |  | 0 | 0
%R | 500314 | 6359 | 124385 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2AREL3665 | External Plastering | 8169 | 600 | 0 | 200 | 0 | 12200 | 12200 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-18 08:00 | 2014-06-15 17:00 |  | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-05-18 08:00 | 2014-06-15 17:00 |  | PT_Normal |  |  |  |  | Ix7uNJoFQ8aWxvYzEa/llA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35150 | N | N | 15 | ELEVATION |  | 124384 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 6100 | PLASTER MASON SK
%R | 500315 | 6359 | 124385 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2AREL3670 | External stone cladding works | 8170 | 608 | 0 | 160 | 0 | 936 | 936 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-06-28 17:00 |  | 2014-03-09 08:00 | 2014-03-31 17:00 | 2014-03-09 08:00 | 2014-03-31 17:00 | 2014-03-09 08:00 | 2014-03-31 17:00 | 2014-06-05 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | dNGlV3TrRdSSJj/IeJ9gyg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35150 | N | N | 15 | ELEVATION |  | 124384 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 936 | TILE MASON SK
%R | 500316 | 6359 | 124385 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2AREL3675 | GRC works | 8178 | 608 | 0 | 160 | 0 | 550 | 550 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-07-03 17:00 |  | 2014-03-15 08:00 | 2014-04-06 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 |  | PT_Normal |  |  |  |  | BbsU1diOSXqcLeYqFtlePw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35150 | N | N | 15 | ELEVATION |  | 124384 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 550 | LABOR- SUBCONTRACTOR
%R | 500317 | 6359 | 124385 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2AREL3680 | External Painting | 8178 | 608 | 40 | 160 | 0 | 4224 | 4224 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-23 08:00 | 2014-07-15 17:00 |  | 2014-03-26 08:00 | 2014-04-17 17:00 | 2014-03-26 08:00 | 2014-04-17 17:00 | 2014-03-26 08:00 | 2014-04-17 17:00 | 2014-06-23 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | 86PXAQ23QtaZMFgVh+D38g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35150 | N | N | 15 | ELEVATION |  | 124384 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 4224 | LABOR- SUBCONTRACTOR
%R | 500318 | 6359 | 124386 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARRF3630 | Leveling Screed for Waterproofing | 8164 | 624 | 0 | 200 | 0 | 711.5 | 711.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-06 08:00 | 2014-06-03 17:00 |  | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-05-06 08:00 | 2014-06-03 17:00 |  | PT_Normal |  |  |  |  | DfTkKs84TmGXhK4iKOHvzg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35140 | N | N | 10 | ROOF |  | 124384 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 355.75 | SCREED MASON SK
%R | 500319 | 6359 | 124386 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARRF3635 | Laying of Waterproofing Membrane | 8178 | 624 | 0 | 200 | 0 | 986.25 | 986.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-10 08:00 | 2014-06-07 17:00 |  | 2014-02-06 08:00 | 2014-03-08 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 | 2014-05-10 08:00 | 2014-06-07 17:00 |  | PT_Normal |  |  |  |  | z0uzmhh0SdSdXLYejfgIZQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35140 | N | N | 10 | ROOF |  | 124384 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 493.125 | LABOR- SUBCONTRACTOR
%R | 500320 | 6359 | 124386 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARRF3640 | Installation of Insulation & Protection | 8178 | 624 | 0 | 200 | 0 | 1250.25 | 1250.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-14 08:00 | 2014-06-11 17:00 |  | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 |  | PT_Normal |  |  |  |  | KKKG2b4mSVm/lVYVtqOBBQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35140 | N | N | 10 | ROOF |  | 124384 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 625.125 | LABOR- SUBCONTRACTOR
%R | 500321 | 6359 | 124386 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 624 | 0 | 200 | 0 | 626 | 626 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | GzgQmBdOQ/KX3h7bfszs0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35140 | N | N | 10 | ROOF |  | 124384 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 313 | TILE MASON SK
%R | 500322 | 6359 | 124386 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 624 | 0 | 160 | 0 | 616 | 616 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-07-03 17:00 |  | 2014-03-12 08:00 | 2014-04-03 17:00 | 2014-03-12 08:00 | 2014-04-03 17:00 | 2014-03-12 08:00 | 2014-04-03 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 |  | PT_Normal |  |  |  |  | sF3KtWfHSdefqR7c/e6RUg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35140 | N | N | 10 | ROOF |  | 124384 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 616 | LABOR- SUBCONTRACTOR
%R | 500323 | 6359 | 124386 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 624 | 0 | 200 | 0 | 859.25 | 859.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-27 08:00 | 2014-06-24 17:00 |  | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-05-27 08:00 | 2014-06-24 17:00 |  | PT_Normal |  |  |  |  | Lyp7fURxTH+2fZq0jMTwMA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35140 | N | N | 10 | ROOF |  | 124384 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 429.625 | LABOR- SUBCONTRACTOR
%R | 500324 | 6359 | 124386 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARRF3660 | Installation of Access Ladder | 8178 | 648 | 624 | 120 | 0 | 352 | 352 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-15 17:00 |  | 2014-03-26 08:00 | 2014-04-12 17:00 | 2014-03-26 08:00 | 2014-04-12 17:00 | 2014-03-26 08:00 | 2014-04-12 17:00 | 2014-06-29 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | yd301RMSRBykLcTcVo7k9A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35140 | N | N | 10 | ROOF |  | 124384 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 352 | LABOR- SUBCONTRACTOR
%R | 500325 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3075 | Carpentry & Joinery Works | 8178 | 464 | 0 | 160 | 0 | 528 | 528 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-26 08:00 | 2014-06-17 17:00 |  | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-05-26 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | 6COMGC9QTY+CaDzXA1M3qg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 528 | LABOR- SUBCONTRACTOR
%R | 500326 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3090 | Installation of Granite Counter Top | 8171 | 464 | 0 | 120 | 0 | 242 | 242 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-08 08:00 | 2014-06-24 17:00 |  | 2014-04-01 08:00 | 2014-04-17 17:00 | 2014-04-01 08:00 | 2014-04-17 17:00 | 2014-04-01 08:00 | 2014-04-17 17:00 | 2014-06-08 08:00 | 2014-06-24 17:00 |  | PT_Normal |  |  |  |  | WAMoYK+HREWsuSuAyQL4UQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 242 | GRANITE MASON SK
%R | 500327 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3085 | S.S.Balustrade | 8178 | 504 | 40 | 160 | 0 | 175 | 175 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-07-01 17:00 |  | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-06-09 08:00 | 2014-07-01 17:00 |  | PT_Normal |  |  |  |  | Zeh3yLVGQ32Uqz68G72/vg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 175 | LABOR- SUBCONTRACTOR
%R | 500328 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3095 | Final Painting | 8178 | 464 | 8 | 200 | 0 | 5936.25 | 5936.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-04-10 08:00 | 2014-05-08 17:00 | 2014-04-10 08:00 | 2014-05-08 17:00 | 2014-04-10 08:00 | 2014-05-08 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | JpiYGHr+TBmT3aHKxs5++g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 5936.25 | LABOR- SUBCONTRACTOR
%R | 500329 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3070 | Aluminum doors | 8178 | 464 | 0 | 120 | 0 | 88 | 88 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-20 08:00 | 2014-06-05 17:00 |  | 2014-03-13 08:00 | 2014-03-30 17:00 | 2014-03-13 08:00 | 2014-03-30 17:00 | 2014-03-13 08:00 | 2014-03-30 17:00 | 2014-05-20 08:00 | 2014-06-05 17:00 |  | PT_Normal |  |  |  |  | hYkJvpfdQJee+gWehJyNOQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 88 | LABOR- SUBCONTRACTOR
%R | 500330 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3000 | Block work | 8168 | 400 | 0 | 200 | 0 | 9262.5 | 9262.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-23 08:00 | 2014-02-22 17:00 |  | 2013-11-25 08:00 | 2013-12-24 17:00 | 2013-11-25 08:00 | 2013-12-24 17:00 | 2013-11-25 08:00 | 2013-12-24 17:00 | 2014-01-23 08:00 | 2014-02-22 17:00 |  | PT_Normal |  |  |  |  | 3C8il6vZSmCHzBQDCTKm+A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 9262.5 | BLOCK MASON SK
%R | 500331 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3005 | Plastering work | 8169 | 400 | 0 | 200 | 0 | 11350 | 11350 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-16 17:00 |  | 2013-12-17 08:00 | 2014-01-15 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | riwYtON0QPOAbpiDdWKS6w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 11350 | PLASTER MASON SK
%R | 500332 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3010 | Flooring screed | 8164 | 464 | 64 | 168 | 0 | 2171.5 | 2171.5 | 168 | 0 | 0 | 0 |  |  |  | 2014-03-05 08:00 | 2014-03-29 17:00 |  | 2013-12-26 08:00 | 2014-01-19 17:00 | 2013-12-26 08:00 | 2014-01-19 17:00 | 2013-12-26 08:00 | 2014-01-19 17:00 | 2014-03-05 08:00 | 2014-03-29 17:00 |  | PT_Normal |  |  |  |  | EuEScuY1Q4S76rb9yu7aZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 2171.5 | SCREED MASON SK
%R | 500333 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 400 | 0 | 120 | 0 | 423.5 | 423.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-05 08:00 | 2014-03-22 17:00 |  | 2014-01-05 08:00 | 2014-01-21 17:00 | 2014-01-05 08:00 | 2014-01-21 17:00 | 2014-01-05 08:00 | 2014-01-21 17:00 | 2014-03-05 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | jc4pez+6RTWsiwCMkZd8JQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 423.5 | LABOR- SUBCONTRACTOR
%R | 500334 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3030 | Paint First coat | 8178 | 512 | 8 | 200 | 0 | 5936.25 | 5936.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-20 08:00 | 2014-04-17 17:00 |  | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 |  | PT_Normal |  |  |  |  | caRKOwozQ1CiUZX2w+hw0A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 5936.25 | LABOR- SUBCONTRACTOR
%R | 500335 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3020 | Ceramic Wall Tiling | 8170 | 400 | 0 | 200 | 0 | 3534.75 | 3534.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-04-08 17:00 |  | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | JUt2q+nhRZuQ5JR0WVRWiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 3534.75 | TILE MASON SK
%R | 500336 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3025 | Porcelain Tile flooring | 8170 | 400 | 0 | 200 | 0 | 1918.75 | 1918.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-14 17:00 |  | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 |  | PT_Normal |  |  |  |  | DMgERKChQn6VZsMYt31Flw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1918.75 | TILE MASON SK
%R | 500337 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3040 | Cobble Tile flooring | 8170 | 464 | 0 | 120 | 0 | 700 | 700 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-22 08:00 | 2014-05-08 17:00 |  | 2014-02-13 08:00 | 2014-03-02 17:00 | 2014-02-13 08:00 | 2014-03-02 17:00 | 2014-02-13 08:00 | 2014-03-02 17:00 | 2014-04-22 08:00 | 2014-05-08 17:00 |  | PT_Normal |  |  |  |  | P1Tr/6yQQheXOdFwlTtqVw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 700 | TILE MASON SK
%R | 500338 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 480 | 16 | 120 | 0 | 931.25 | 931.25 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-04 17:00 |  | 2014-02-05 08:00 | 2014-02-23 17:00 | 2014-02-05 08:00 | 2014-02-23 17:00 | 2014-02-05 08:00 | 2014-02-23 17:00 | 2014-04-17 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | Aa312uBOSlqLrDwPNFBd5w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 931.25 | TILE MASON SK
%R | 500339 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 464 | 0 | 160 | 0 | 850 | 850 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-30 08:00 | 2014-05-22 17:00 |  | 2014-02-22 08:00 | 2014-03-16 17:00 | 2014-02-22 08:00 | 2014-03-16 17:00 | 2014-02-22 08:00 | 2014-03-16 17:00 | 2014-04-30 08:00 | 2014-05-22 17:00 |  | PT_Normal |  |  |  |  | MTe8BGxMQzyFj4+v+8tuCQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 850 | GRANITE MASON SK
%R | 500340 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3045 | Fixing of Suspension systems | 8178 | 400 | 0 | 160 | 0 | 1320.5 | 1320.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-03 08:00 | 2014-04-26 17:00 |  | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-04-03 08:00 | 2014-04-26 17:00 |  | PT_Normal |  |  |  |  | JrRiwpjSSE6NB2tT9WkmwA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1320.5 | LABOR- SUBCONTRACTOR
%R | 500341 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3055 | Aluminum tile false ceiling | 8178 | 424 | 24 | 200 | 0 | 130 | 130 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-13 17:00 |  | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 |  | PT_Normal |  |  |  |  | 5kG7XdUMSquB4lrbxQ7atg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 65 | LABOR- SUBCONTRACTOR
%R | 500342 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3060 | Gypsum board false ceiling | 8178 | 400 | 0 | 200 | 0 | 1216.3 | 1216.3 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-13 17:00 |  | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 |  | PT_Normal |  |  |  |  | 2UFDUysySzekibEcpP2cPw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 608.15 | LABOR- SUBCONTRACTOR
%R | 500343 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3065 | Wooden door & PVC Door | 8178 | 464 | 0 | 120 | 0 | 660 | 660 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-14 08:00 | 2014-05-31 17:00 |  | 2014-03-08 08:00 | 2014-03-24 17:00 | 2014-03-08 08:00 | 2014-03-24 17:00 | 2014-03-08 08:00 | 2014-03-24 17:00 | 2014-05-14 08:00 | 2014-05-31 17:00 |  | PT_Normal |  |  |  |  | twS5nov0QKeBF4556M+13Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 660 | LABOR- SUBCONTRACTOR
%R | 500344 | 6359 | 124388 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARGF3080 | Aluminum windows | 8178 | 544 | 48 | 160 | 0 | 257.5 | 257.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-08 08:00 | 2014-06-30 17:00 |  | 2014-03-20 08:00 | 2014-04-12 17:00 | 2014-03-20 08:00 | 2014-04-12 17:00 | 2014-03-20 08:00 | 2014-04-12 17:00 | 2014-06-08 08:00 | 2014-06-30 17:00 |  | PT_Normal |  |  |  |  | rcrPDOtVTPW1dX6qRwiUyg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35100 | N | N | 10 | GROUND FLOOR |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 257.5 | LABOR- SUBCONTRACTOR
%R | 500345 | 6359 | 124389 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARRF3600 | Block work | 8168 | 640 | 0 | 160 | 0 | 697.25 | 697.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-01 08:00 | 2014-05-24 17:00 |  | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-05-01 08:00 | 2014-05-24 17:00 |  | PT_Normal |  |  |  |  | s7KmfUlIR+y4y1Yjgu7ktQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35120 | N | N | 20 | ROOF |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 697.25 | BLOCK MASON SK
%R | 500346 | 6359 | 124389 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARRF3605 | Plastering work | 8169 | 640 | 0 | 160 | 0 | 3833 | 3833 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-10 08:00 | 2014-06-01 17:00 |  | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-05-10 08:00 | 2014-06-01 17:00 |  | PT_Normal |  |  |  |  | czL5PPjTStCwHPrrtCPI7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35120 | N | N | 20 | ROOF |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 3833 | PLASTER MASON SK
%R | 500347 | 6359 | 124389 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARRF3610 | Flooring screed | 8164 | 648 | 0 | 120 | 0 | 154 | 154 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-29 08:00 | 2014-06-15 17:00 |  | 2014-02-24 08:00 | 2014-03-12 17:00 | 2014-02-24 08:00 | 2014-03-12 17:00 | 2014-02-24 08:00 | 2014-03-12 17:00 | 2014-05-29 08:00 | 2014-06-15 17:00 |  | PT_Normal |  |  |  |  | qskJ/r+8RQ+Cy8zq3CWbyA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35120 | N | N | 20 | ROOF |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 154 | SCREED MASON SK
%R | 500348 | 6359 | 124389 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARRF3695 | Painting -Storage area | 8178 | 648 | 0 | 160 | 0 | 1640 | 1640 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-07-03 17:00 |  | 2014-03-09 08:00 | 2014-03-31 17:00 | 2014-03-09 08:00 | 2014-03-31 17:00 | 2014-03-09 08:00 | 2014-03-31 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 |  | PT_Normal |  |  |  |  | cGqH764hRyaQBtG7SgARkg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35120 | N | N | 20 | ROOF |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1640 | LABOR- SUBCONTRACTOR
%R | 500349 | 6359 | 124389 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARRF3620 | Epoxy Painting -Storage area | 8178 | 648 | 624 | 120 | 0 | 48.5 | 48.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-15 17:00 |  | 2014-03-26 08:00 | 2014-04-12 17:00 | 2014-03-26 08:00 | 2014-04-12 17:00 | 2014-03-26 08:00 | 2014-04-12 17:00 | 2014-06-29 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | t8qxa4F9TI2Kb7vN4Iz1AA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35120 | N | N | 20 | ROOF |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 48.5 | LABOR- SUBCONTRACTOR
%R | 500350 | 6359 | 124390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARFF3300 | Block work | 8168 | 24 | 0 | 200 | 0 | 7341 | 7341 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-11 08:00 | 2014-02-08 17:00 |  | 2014-01-07 08:00 | 2014-02-04 17:00 | 2014-01-07 08:00 | 2014-02-04 17:00 | 2014-01-07 08:00 | 2014-02-04 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 |  | PT_Normal |  |  |  |  | pbMElWq1QQiGa430PhvvTQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35110 | N | N | 15 | FIRST FLOORS |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 7341 | BLOCK MASON SK
%R | 500351 | 6359 | 124390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARFF3305 | Plastering work | 8169 | 24 | 0 | 200 | 0 | 7518.75 | 7518.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-03-08 17:00 |  | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | qqU+o9g5QDCVrHCSPP1IWg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35110 | N | N | 15 | FIRST FLOORS |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 3759.375 | PLASTER MASON SK
%R | 500352 | 6359 | 124390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARFF3310 | Flooring screed | 8164 | 160 | 136 | 168 | 0 | 1082.5 | 1082.5 | 168 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-31 17:00 |  | 2014-02-12 08:00 | 2014-03-08 17:00 | 2014-02-12 08:00 | 2014-03-08 17:00 | 2014-02-12 08:00 | 2014-03-08 17:00 | 2014-03-08 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | 33rUDvj5Qgqgxb/8D+WDEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35110 | N | N | 15 | FIRST FLOORS |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1082.5 | SCREED MASON SK
%R | 500353 | 6359 | 124390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARFF3315 | Wet area waterproofing | 8178 | 24 | 0 | 120 | 0 | 1374 | 1374 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-01 08:00 | 2014-03-17 17:00 |  | 2014-02-25 08:00 | 2014-03-13 17:00 | 2014-02-25 08:00 | 2014-03-13 17:00 | 2014-02-25 08:00 | 2014-03-13 17:00 | 2014-03-01 08:00 | 2014-03-17 17:00 |  | PT_Normal |  |  |  |  | Gnec1da6SVOt3zwG6LA/SQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35110 | N | N | 15 | FIRST FLOORS |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1374 | LABOR- SUBCONTRACTOR
%R | 500354 | 6359 | 124390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARFF3330 | Paint First coat | 8178 | 232 | 208 | 200 | 0 | 5256.25 | 5256.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-26 08:00 | 2014-04-23 17:00 |  | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 |  | PT_Normal |  |  |  |  | VtF8GgBCToa5Ji0uhl6jDw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35110 | N | N | 15 | FIRST FLOORS |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 2628.125 | LABOR- SUBCONTRACTOR
%R | 500355 | 6359 | 124390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARFF3320 | Ceramic Wall Tiling | 8170 | 24 | 0 | 200 | 0 | 1516 | 1516 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-10 08:00 | 2014-04-07 17:00 |  | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 |  | PT_Normal |  |  |  |  | 2tlRdRLWTT+7RA73ljRbxw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35110 | N | N | 15 | FIRST FLOORS |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1516 | TILE MASON SK
%R | 500356 | 6359 | 124390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARFF3325 | Porcelain Tile flooring | 8170 | 24 | 0 | 200 | 0 | 1341 | 1341 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | JI6OHA3RQAmz/qs1Den2gA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35110 | N | N | 15 | FIRST FLOORS |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1341 | TILE MASON SK
%R | 500357 | 6359 | 124390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARFF3335 | Slate Tile Flooring & Skirting | 8170 | 176 | 152 | 120 | 0 | 931.25 | 931.25 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-28 08:00 | 2014-05-14 17:00 |  | 2014-04-02 08:00 | 2014-04-19 17:00 | 2014-04-02 08:00 | 2014-04-19 17:00 | 2014-04-02 08:00 | 2014-04-19 17:00 | 2014-04-28 08:00 | 2014-05-14 17:00 |  | PT_Normal |  |  |  |  | xJzJfdu4TcqOjDSypVWLrQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35110 | N | N | 15 | FIRST FLOORS |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 931.25 | TILE MASON SK
%R | 500358 | 6359 | 124390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARFF3350 | Granite - Stair case flooring & Skirting | 8171 | 112 | 88 | 160 | 0 | 850 | 850 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-22 08:00 | 2014-05-14 17:00 |  | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-04-22 08:00 | 2014-05-14 17:00 |  | PT_Normal |  |  |  |  | niuouaAIRpCtmhQO/YGvDw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35110 | N | N | 15 | FIRST FLOORS |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 850 | GRANITE MASON SK
%R | 500359 | 6359 | 124390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARFF3345 | Fixing of Suspension systems | 8178 | 24 | 0 | 160 | 0 | 1191 | 1191 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-09 08:00 | 2014-05-01 17:00 |  | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-04-09 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | 989iypIsRGOVlIgC7E6vQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35110 | N | N | 15 | FIRST FLOORS |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1191 | LABOR- SUBCONTRACTOR
%R | 500360 | 6359 | 124390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARFF3360 | Gypsum board false ceiling | 8178 | 24 | 0 | 200 | 0 | 1191 | 1191 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-21 08:00 | 2014-05-19 17:00 |  | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | EaFT5ou/QTSdRWsTxKTaaA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35110 | N | N | 15 | FIRST FLOORS |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1191 | LABOR- SUBCONTRACTOR
%R | 500361 | 6359 | 124390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARFF3365 | Wooden door | 8178 | 24 | 0 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-06 08:00 | 2014-05-22 17:00 |  | 2014-05-03 08:00 | 2014-05-19 17:00 | 2014-05-03 08:00 | 2014-05-19 17:00 | 2014-05-03 08:00 | 2014-05-19 17:00 | 2014-05-06 08:00 | 2014-05-22 17:00 |  | PT_Normal |  |  |  |  | AgboszbMR5mHqw0h9n8cEQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35110 | N | N | 15 | FIRST FLOORS |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 176 | LABOR- SUBCONTRACTOR
%R | 500362 | 6359 | 124390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARFF3370 | Aluminum Door | 8178 | 24 | 0 | 160 | 0 | 132 | 132 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-14 08:00 | 2014-06-05 17:00 |  | 2014-05-11 08:00 | 2014-06-02 17:00 | 2014-05-11 08:00 | 2014-06-02 17:00 | 2014-05-11 08:00 | 2014-06-02 17:00 | 2014-05-14 08:00 | 2014-06-05 17:00 |  | PT_Normal |  |  |  |  | DXo89LDaSIGXbjzWwZXwtg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35110 | N | N | 15 | FIRST FLOORS |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 132 | LABOR- SUBCONTRACTOR
%R | 500363 | 6359 | 124390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARFF3380 | Aluminum windows | 8178 | 128 | 104 | 160 | 0 | 272.25 | 272.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-06-28 17:00 |  | 2014-05-18 08:00 | 2014-06-09 17:00 | 2014-05-18 08:00 | 2014-06-09 17:00 | 2014-05-18 08:00 | 2014-06-09 17:00 | 2014-06-05 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | IIqfkr6QTVK9dEGszVXHBA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35110 | N | N | 15 | FIRST FLOORS |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 272.25 | LABOR- SUBCONTRACTOR
%R | 500364 | 6359 | 124390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARFF3375 | Carpentry & Joinery Works | 8178 | 24 | 0 | 200 | 0 | 704 | 704 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-22 08:00 | 2014-06-19 17:00 |  | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 |  | PT_Normal |  |  |  |  | MJsmfN2tQ4W4Pc0jqwDkiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35110 | N | N | 15 | FIRST FLOORS |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 704 | LABOR- SUBCONTRACTOR
%R | 500365 | 6359 | 124390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARFF3390 | Installation of Granite Counter Top | 8171 | 40 | 16 | 160 | 0 | 110 | 110 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-08 08:00 | 2014-06-30 17:00 |  | 2014-06-02 08:00 | 2014-06-24 17:00 | 2014-06-02 08:00 | 2014-06-24 17:00 | 2014-06-02 08:00 | 2014-06-24 17:00 | 2014-06-08 08:00 | 2014-06-30 17:00 |  | PT_Normal |  |  |  |  | 7rcLzK5uQuqHdQ9DagbVTg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35110 | N | N | 15 | FIRST FLOORS |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 110 | GRANITE MASON SK
%R | 500366 | 6359 | 124390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARFF3385 | Handrail & Balustrade | 8178 | 24 | 0 | 160 | 0 | 175 | 175 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-06-28 17:00 |  | 2014-06-02 08:00 | 2014-06-24 17:00 | 2014-06-02 08:00 | 2014-06-24 17:00 | 2014-06-02 08:00 | 2014-06-24 17:00 | 2014-06-05 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | IktJ2/UuSt2Ha/lb5A5A3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35110 | N | N | 15 | FIRST FLOORS |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 175 | LABOR- SUBCONTRACTOR
%R | 500367 | 6359 | 124390 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ARFF3395 | Final Painting | 8178 | 24 | 0 | 200 | 0 | 5256.25 | 5256.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35110 | N | N | 15 | FIRST FLOORS |  | 124387 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 5256.25 | LABOR- SUBCONTRACTOR
%R | 500368 | 6359 | 124393 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 128 | 0 | 200 | 0 | 2579.2 | 2579.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-01 08:00 | 2014-03-02 17:00 |  | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 |  | PT_Normal |  |  |  |  | ozoIjuD3SCSiogIEsQiIRQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35190 | N | N | 15 | FIRST FLOORS |  | 124392 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 2579.2 | LABOR- SUBCONTRACTOR
%R | 500369 | 6359 | 124393 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ELFF4040 | Cable tray & trunking installation | 8178 | 368 | 0 | 160 | 0 | 3180.8 | 3180.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-20 08:00 | 2014-04-12 17:00 |  | 2014-01-25 08:00 | 2014-02-17 17:00 | 2014-01-25 08:00 | 2014-02-17 17:00 | 2014-01-25 08:00 | 2014-02-17 17:00 | 2014-03-20 08:00 | 2014-04-12 17:00 |  | PT_Normal |  |  |  |  | qgRe/a8eQIqAzHOUmxrFHA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35190 | N | N | 15 | FIRST FLOORS |  | 124392 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 3180.8 | LABOR- SUBCONTRACTOR
%R | 500370 | 6359 | 124393 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ELFF4045 | Installation of wiring & Main Cabling | 8178 | 368 | 0 | 200 | 0 | 636.8 | 636.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-29 08:00 | 2014-04-26 17:00 |  | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-03-29 08:00 | 2014-04-26 17:00 |  | PT_Normal |  |  |  |  | wWz/q/GHRbWHwJZQV9SRiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35190 | N | N | 15 | FIRST FLOORS |  | 124392 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 318.4 | LABOR- SUBCONTRACTOR
%R | 500371 | 6359 | 124393 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 24 | 0 | 160 | 0 | 454.4 | 454.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-06 08:00 | 2014-05-28 17:00 |  | 2014-05-03 08:00 | 2014-05-25 17:00 | 2014-05-03 08:00 | 2014-05-25 17:00 | 2014-05-03 08:00 | 2014-05-25 17:00 | 2014-05-06 08:00 | 2014-05-28 17:00 |  | PT_Normal |  |  |  |  | XQ+DSftAS6aQKgU0yuzDZQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35190 | N | N | 15 | FIRST FLOORS |  | 124392 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 454.4 | LABOR- SUBCONTRACTOR
%R | 500372 | 6359 | 124393 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 24 | 0 | 200 | 0 | 3302.4 | 3302.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | msIjlEimRjKB9SI+HzWtAg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35190 | N | N | 15 | FIRST FLOORS |  | 124392 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 3302.4 | LABOR- SUBCONTRACTOR
%R | 500373 | 6359 | 124393 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 360 | 0 | 200 | 0 | 4569.6 | 4569.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | nkQZr5yQQDuOnsB+E0ejUg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35190 | N | N | 15 | FIRST FLOORS |  | 124392 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 4569.6 | LABOR- SUBCONTRACTOR
%R | 500374 | 6359 | 124393 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ELFF4050 | Installation of Telephone System | 8178 | 200 | 176 | 200 | 0 | 1422.4 | 1422.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-22 08:00 | 2014-06-19 17:00 |  | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 |  | PT_Normal |  |  |  |  | eggNDnWrT+ePaSp2cLDb/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35190 | N | N | 15 | FIRST FLOORS |  | 124392 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1422.4 | LABOR- SUBCONTRACTOR
%R | 500375 | 6359 | 124394 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ELRF4070 | Installation of Isolator | 8178 | 24 | 0 | 144 | 0 | 825.6 | 825.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-06-08 08:00 | 2014-06-28 17:00 |  | 2014-06-04 08:00 | 2014-06-24 17:00 | 2014-06-04 08:00 | 2014-06-24 17:00 | 2014-06-04 08:00 | 2014-06-24 17:00 | 2014-06-08 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | QZEpc7uzQoS2SgkAqpIJBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35200 | N | N | 20 | ROOF |  | 124392 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 825.6 | LABOR- SUBCONTRACTOR
%R | 500376 | 6359 | 124394 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ELRF4075 | Installation of TV Dish Antenna | 8178 | 24 | 0 | 184 | 0 | 1830.4 | 1830.4 | 184 | 0 | 0 | 0 |  |  |  | 2014-06-19 08:00 | 2014-07-15 17:00 |  | 2014-06-16 08:00 | 2014-07-12 17:00 | 2014-06-16 08:00 | 2014-07-12 17:00 | 2014-06-16 08:00 | 2014-07-12 17:00 | 2014-06-19 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | IpO8AF1NSCy/EecxZclwlA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35200 | N | N | 20 | ROOF |  | 124392 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1830.4 | LABOR- SUBCONTRACTOR
%R | 500377 | 6359 | 124395 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 472 | 0 | 200 | 0 | 2579.2 | 2579.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-03-10 17:00 |  | 2013-12-01 08:00 | 2013-12-30 17:00 | 2013-12-01 08:00 | 2013-12-30 17:00 | 2013-12-01 08:00 | 2013-12-30 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | x9GDgInmQnyGPG/pQg3mdA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35180 | N | N | 10 | GROUND FLOOR |  | 124392 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 2579.2 | LABOR- SUBCONTRACTOR
%R | 500378 | 6359 | 124395 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ELGF4005 | Cable tray & trunking installation | 8178 | 616 | 0 | 160 | 0 | 3180.8 | 3180.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-06 17:00 |  | 2013-12-12 08:00 | 2014-01-05 17:00 | 2013-12-12 08:00 | 2014-01-05 17:00 | 2013-12-12 08:00 | 2014-01-05 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | REhagBxIRXurnaSmDupshg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35180 | N | N | 10 | GROUND FLOOR |  | 124392 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 3180.8 | LABOR- SUBCONTRACTOR
%R | 500379 | 6359 | 124395 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ELGF4010 | Installation of wiring & Main Cabling | 8178 | 616 | 216 | 200 | 0 | 636.8 | 636.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-23 08:00 | 2014-04-20 17:00 |  | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | qu+SKHBwSpmByr6XUYmR9A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35180 | N | N | 10 | GROUND FLOOR |  | 124392 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 636.8 | LABOR- SUBCONTRACTOR
%R | 500380 | 6359 | 124395 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 400 | 0 | 160 | 0 | 454.4 | 454.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-21 17:00 |  | 2014-03-02 08:00 | 2014-03-24 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 | 2014-04-29 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | QEqN78iZRkWP65jJQnuEWg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35180 | N | N | 10 | GROUND FLOOR |  | 124392 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 454.4 | LABOR- SUBCONTRACTOR
%R | 500381 | 6359 | 124395 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 416 | 8 | 200 | 0 | 3302.4 | 3302.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-06-10 17:00 |  | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-05-13 08:00 | 2014-06-10 17:00 |  | PT_Normal |  |  |  |  | Wv5DNA95SrqRFODdnjHdwA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35180 | N | N | 10 | GROUND FLOOR |  | 124392 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 3302.4 | LABOR- SUBCONTRACTOR
%R | 500382 | 6359 | 124395 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 576 | 8 | 200 | 0 | 4569.6 | 4569.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | gpoNLW5ZTXar/NIMnPpNXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35180 | N | N | 10 | GROUND FLOOR |  | 124392 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 2284.8 | LABOR- SUBCONTRACTOR
%R | 500383 | 6359 | 124395 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ELGF4030 | Installation of Telephone System | 8178 | 400 | 48 | 160 | 0 | 1422.4 | 1422.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-06-02 17:00 |  | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-05-11 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | FJcR+hOjSQaBFpSfFmBU5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35180 | N | N | 10 | GROUND FLOOR |  | 124392 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1422.4 | LABOR- SUBCONTRACTOR
%R | 500384 | 6359 | 124397 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ACRF4630 | Installation of Refrigerant Pipes | 8178 | 696 | 0 | 200 | 0 | 795.2 | 795.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-07-09 17:00 |  | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-06-11 08:00 | 2014-07-09 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35280 | N | N | 20 | ROOF |  | 124396 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 795.2 | LABOR- SUBCONTRACTOR
%R | 500385 | 6359 | 124397 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ACRF4635 | Installation of Condensing Unit | 8178 | 176 | 0 | 200 | 0 | 1136 | 1136 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | a5swIpA/T7eo7I1vvHvPLg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35280 | N | N | 20 | ROOF |  | 124396 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1136 | LABOR- SUBCONTRACTOR
%R | 500386 | 6359 | 124398 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ACGF4600 | Installation AC Pipes | 8178 | 648 | 48 | 160 | 0 | 1886.4 | 1886.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-07 08:00 | 2014-04-29 17:00 |  | 2014-01-01 08:00 | 2014-01-23 17:00 | 2014-01-01 08:00 | 2014-01-23 17:00 | 2014-01-01 08:00 | 2014-01-23 17:00 | 2014-04-07 08:00 | 2014-04-29 17:00 |  | PT_Normal |  |  |  |  | VO2cOoy3SOWTkrq0O0dMEA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35260 | N | N | 10 | GROUND FLOOR |  | 124396 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1886.4 | LABOR- SUBCONTRACTOR
%R | 500387 | 6359 | 124398 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ACGF4605 | Fixing of Ventilation Equipments | 8178 | 552 | 0 | 200 | 0 | 296 | 296 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-15 08:00 | 2014-06-12 17:00 |  | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 |  | PT_Normal |  |  |  |  | e/lREGRrTlW33XtfRPLcxg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35260 | N | N | 10 | GROUND FLOOR |  | 124396 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 148 | LABOR- SUBCONTRACTOR
%R | 500388 | 6359 | 124398 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ACGF4610 | Fixing of Split AC | 8178 | 552 | 48 | 160 | 0 | 568 | 568 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-06-28 17:00 |  | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-06-05 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | EYjC1g+zQUy8tOoEt38OYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35260 | N | N | 10 | GROUND FLOOR |  | 124396 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 568 | LABOR- SUBCONTRACTOR
%R | 500389 | 6359 | 124399 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ACFF4615 | Installation AC Pipes | 8178 | 368 | 24 | 160 | 0 | 1886.4 | 1886.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-13 08:00 | 2014-05-05 17:00 |  | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | AN/4lmFQTkGFXC0gnB7snQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35270 | N | N | 15 | FIRST FLOORS |  | 124396 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1886.4 | LABOR- SUBCONTRACTOR
%R | 500390 | 6359 | 124399 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ACFF4620 | Fixing of Ventilation Equipments | 8178 | 136 | 0 | 200 | 0 | 182.4 | 182.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-15 08:00 | 2014-06-12 17:00 |  | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 |  | PT_Normal |  |  |  |  | nLCbpP9aTAmhwMdKXOKSNw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35270 | N | N | 15 | FIRST FLOORS |  | 124396 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 182.4 | LABOR- SUBCONTRACTOR
%R | 500391 | 6359 | 124399 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ACFF4625 | Fixing of Split AC | 8178 | 136 | 0 | 160 | 0 | 568 | 568 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-06-28 17:00 |  | 2014-05-17 08:00 | 2014-06-08 17:00 | 2014-05-17 08:00 | 2014-06-08 17:00 | 2014-05-17 08:00 | 2014-06-08 17:00 | 2014-06-05 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | kMeEx5xNTduKGERnu6hBCg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35270 | N | N | 15 | FIRST FLOORS |  | 124396 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 568 | LABOR- SUBCONTRACTOR
%R | 500392 | 6359 | 124401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 400 | 0 | 144 | 0 | 883.2 | 883.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-03-02 17:00 |  | 2013-12-11 08:00 | 2014-01-01 17:00 | 2013-12-11 08:00 | 2014-01-01 17:00 | 2013-12-11 08:00 | 2014-01-01 17:00 | 2014-02-09 08:00 | 2014-03-02 17:00 |  | PT_Normal |  |  |  |  | 6KXjEl57TDmg0M0tMzJ6qA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35220 | N | N | 10 | GROUND FLOOR |  | 124400 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 883.2 | LABOR- SUBCONTRACTOR
%R | 500393 | 6359 | 124401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2PLGF4310 | Installation of Drainage pipes &testing | 8178 | 424 | 128 | 144 | 0 | 331.2 | 331.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-03-05 17:00 |  | 2013-12-11 08:00 | 2014-01-01 17:00 | 2013-12-11 08:00 | 2014-01-01 17:00 | 2013-12-11 08:00 | 2014-01-01 17:00 | 2014-02-13 08:00 | 2014-03-05 17:00 |  | PT_Normal |  |  |  |  | H47O9oTzTcaar3lIFa/qEw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35220 | N | N | 10 | GROUND FLOOR |  | 124400 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 331.2 | LABOR- SUBCONTRACTOR
%R | 500394 | 6359 | 124401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2PLGF4315 | Sanitary Fittings & Accessories | 8178 | 656 | 0 | 160 | 0 | 201.6 | 201.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-09 17:00 |  | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-06-17 08:00 | 2014-07-09 17:00 |  | PT_Normal |  |  |  |  | WBYR+1aNR6qA1eR2MqGuoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35220 | N | N | 10 | GROUND FLOOR |  | 124400 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 201.6 | LABOR- SUBCONTRACTOR
%R | 500395 | 6359 | 124401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2PLGF4320 | Installation of Water Heater | 8178 | 656 | 88 | 120 | 0 | 201.6 | 201.6 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-15 17:00 |  | 2014-03-25 08:00 | 2014-04-10 17:00 | 2014-03-25 08:00 | 2014-04-10 17:00 | 2014-03-25 08:00 | 2014-04-10 17:00 | 2014-06-29 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | IwsMHap/TqeH4/5CD08leg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35220 | N | N | 10 | GROUND FLOOR |  | 124400 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 201.6 | LABOR- SUBCONTRACTOR
%R | 500396 | 6359 | 124401 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 0 | 0 | 160 | 0 | 110.4 | 110.4 | 160 | 0 | 0 | 0 |  |  |  | 2013-08-25 08:00 | 2013-09-16 17:00 |  | 2013-08-25 08:00 | 2013-09-16 17:00 | 2013-08-25 08:00 | 2013-09-16 17:00 | 2013-08-25 08:00 | 2013-09-16 17:00 | 2013-08-25 08:00 | 2013-09-16 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35220 | N | N | 10 | GROUND FLOOR |  | 124400 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 110.4 | LABOR- SUBCONTRACTOR
%R | 500397 | 6359 | 124402 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2PLFF4340 | Installation of Water Heater | 8178 | 152 | 0 | 120 | 0 | 134.4 | 134.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-06-28 17:00 |  | 2014-05-20 08:00 | 2014-06-05 17:00 | 2014-05-20 08:00 | 2014-06-05 17:00 | 2014-05-20 08:00 | 2014-06-05 17:00 | 2014-06-11 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | MBVJC5WARlypB8ignkxcvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35230 | N | N | 15 | FIRST FLOORS |  | 124400 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 500398 | 6359 | 124402 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 24 | 0 | 144 | 0 | 883.2 | 883.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-28 08:00 | 2014-02-18 17:00 |  | 2014-01-25 08:00 | 2014-02-15 17:00 | 2014-01-25 08:00 | 2014-02-15 17:00 | 2014-01-25 08:00 | 2014-02-15 17:00 | 2014-01-28 08:00 | 2014-02-18 17:00 |  | PT_Normal |  |  |  |  | OLY83K8hQUahIzScXWoWOQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35230 | N | N | 15 | FIRST FLOORS |  | 124400 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 883.2 | LABOR- SUBCONTRACTOR
%R | 500399 | 6359 | 124402 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2PLFF4330 | Installation of Drainage pipes & testing | 8178 | 240 | 56 | 144 | 0 | 331.2 | 331.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-22 17:00 |  | 2014-01-25 08:00 | 2014-02-15 17:00 | 2014-01-25 08:00 | 2014-02-15 17:00 | 2014-01-25 08:00 | 2014-02-15 17:00 | 2014-03-02 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | xfGOc0yuRxOf3N7neWnR7w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35230 | N | N | 15 | FIRST FLOORS |  | 124400 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 331.2 | LABOR- SUBCONTRACTOR
%R | 500400 | 6359 | 124402 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2PLFF4335 | Sanitary Fittings & Accessories | 8178 | 152 | 0 | 160 | 0 | 201.6 | 201.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-31 08:00 | 2014-06-22 17:00 |  | 2014-05-08 08:00 | 2014-05-31 17:00 | 2014-05-08 08:00 | 2014-05-31 17:00 | 2014-05-08 08:00 | 2014-05-31 17:00 | 2014-05-31 08:00 | 2014-06-22 17:00 |  | PT_Normal |  |  |  |  | Mc/QHEyqQM2ZOa/fXKk0Rw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35230 | N | N | 15 | FIRST FLOORS |  | 124400 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 201.6 | LABOR- SUBCONTRACTOR
%R | 500401 | 6359 | 124403 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 672 | 72 | 112 | 0 | 288 | 288 | 112 | 0 | 0 | 0 |  |  |  | 2014-05-31 08:00 | 2014-06-15 17:00 |  | 2014-02-22 08:00 | 2014-03-09 17:00 | 2014-02-22 08:00 | 2014-03-09 17:00 | 2014-02-22 08:00 | 2014-03-09 17:00 | 2014-05-31 08:00 | 2014-06-15 17:00 |  | PT_Normal |  |  |  |  | VjEtgyr6SYqy6Cxr1smOBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35240 | N | N | 20 | ROOF |  | 124400 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 288 | LABOR- SUBCONTRACTOR
%R | 500402 | 6359 | 124403 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2PLRF4350 | Installation of Rain water Pipes |  | 600 | 32 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-06-28 17:00 |  | 2014-03-16 08:00 | 2014-04-01 17:00 | 2014-03-16 08:00 | 2014-04-01 17:00 | 2014-03-16 08:00 | 2014-04-01 17:00 | 2014-06-11 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | LIZ2ssDWQIC0dyliTm9UMg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 35240 | N | N | 20 | ROOF |  | 124400 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 0 | 0
%R | 500403 | 6359 | 124403 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 152 | 0 | 200 | 0 | 672 | 672 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-05-26 08:00 | 2014-06-23 17:00 | 2014-05-26 08:00 | 2014-06-23 17:00 | 2014-05-26 08:00 | 2014-06-23 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | xFtUpkeLRyurVTm8SScyGQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35240 | N | N | 20 | ROOF |  | 124400 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 672 | LABOR- SUBCONTRACTOR
%R | 500404 | 6359 | 124404 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 24 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | rhn4dgQrSZim+IglX9U7eQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35350 | N | N | 30 | TESTING AND COMMISSIONING |  | 124382 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 500405 | 6359 | 124404 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 24 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | k83pbsmBR8y+j3b94MoDKg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35350 | N | N | 30 | TESTING AND COMMISSIONING |  | 124382 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 750 | LABOR- SUBCONTRACTOR
%R | 500406 | 6359 | 124404 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 24 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | 9VW/ZU2BQ5Gj33nMTsdRzw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35350 | N | N | 30 | TESTING AND COMMISSIONING |  | 124382 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 500407 | 6359 | 124407 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STUG1000 | Footing Excavation | 8177 | 0 | 0 | 200 | 0 | 1433 | 1433 | 200 | 675 | 0 | 675 |  |  |  | 2013-05-13 08:00 | 2013-06-10 17:00 |  | 2013-05-13 08:00 | 2013-06-10 17:00 | 2013-05-13 08:00 | 2013-06-10 17:00 | 2013-05-13 08:00 | 2013-06-10 17:00 | 2013-05-13 08:00 | 2013-06-10 17:00 |  | PT_Normal |  |  |  |  | m0yx60U0Q3KF5XTNxGGdHw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35030 | N | N | 10 | UPTO GRADE SLAB |  | 124406 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 1433 | LABOR - CIVIL
%R | 500408 | 6359 | 124407 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STUG1005 | Footing Antitermite | 8178 | 0 | 0 | 184 | 0 | 1861.75 | 1861.75 | 184 | 0 | 0 | 0 |  |  |  | 2013-05-25 08:00 | 2013-06-19 17:00 |  | 2013-05-25 08:00 | 2013-06-19 17:00 | 2013-05-25 08:00 | 2013-06-19 17:00 | 2013-05-25 08:00 | 2013-06-19 17:00 | 2013-05-25 08:00 | 2013-06-19 17:00 |  | PT_Normal |  |  |  |  | LEdC1ReBR4Cuu/xJOUUgQw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35030 | N | N | 10 | UPTO GRADE SLAB |  | 124406 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 1861.75 | LABOR- SUBCONTRACTOR
%R | 500409 | 6359 | 124407 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STUG1010 | Footing Blinding | 8163 | 0 | 0 | 184 | 0 | 1048.25 | 1048.25 | 184 | 0 | 0 | 0 |  |  |  | 2013-05-28 08:00 | 2013-06-23 17:00 |  | 2013-05-28 08:00 | 2013-06-23 17:00 | 2013-05-28 08:00 | 2013-06-23 17:00 | 2013-05-28 08:00 | 2013-06-23 17:00 | 2013-05-28 08:00 | 2013-06-23 17:00 |  | PT_Normal |  |  |  |  | C4X8Mjo0Qjmw30JXmI1LPQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35030 | N | N | 10 | UPTO GRADE SLAB |  | 124406 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 1048.25 | BLINDING MASON SK
%R | 500410 | 6359 | 124407 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STUG1015 | Footing Waterproofing & Screed | 8164 | 0 | 0 | 200 | 0 | 825 | 825 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-03 08:00 | 2013-07-01 17:00 |  | 2013-06-03 08:00 | 2013-07-01 17:00 | 2013-06-03 08:00 | 2013-07-01 17:00 | 2013-06-03 08:00 | 2013-07-01 17:00 | 2013-06-03 08:00 | 2013-07-01 17:00 |  | PT_Normal |  |  |  |  | qhJb+lqWTK2119QJhPCpdg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35030 | N | N | 10 | UPTO GRADE SLAB |  | 124406 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 825 | SCREED MASON SK
%R | 500411 | 6359 | 124407 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STUG1020 | Construction of foundations | 8165 | 0 | 0 | 160 | 0 | 7969.5 | 7969.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-06-18 08:00 | 2013-07-10 17:00 |  | 2013-06-18 08:00 | 2013-07-10 17:00 | 2013-06-18 08:00 | 2013-07-10 17:00 | 2013-06-18 08:00 | 2013-07-10 17:00 | 2013-06-18 08:00 | 2013-07-10 17:00 |  | PT_Normal |  |  |  |  | Bqo+yGeNT1KQmHfn54r9uw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35030 | N | N | 10 | UPTO GRADE SLAB |  | 124406 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 7969.5 | STEEL FIXERS SK
%R | 500412 | 6359 | 124407 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STUG1030 | Waterproofing Footing & Neck Column | 8178 | 0 | 0 | 200 | 0 | 535.25 | 535.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-07 08:00 | 2013-08-04 17:00 |  | 2013-07-07 08:00 | 2013-08-04 17:00 | 2013-07-07 08:00 | 2013-08-04 17:00 | 2013-07-07 08:00 | 2013-08-04 17:00 | 2013-07-07 08:00 | 2013-08-04 17:00 |  | PT_Normal |  |  |  |  | 5XcFbc7qTJKiPLGJMdtW3A |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35030 | N | N | 10 | UPTO GRADE SLAB |  | 124406 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 535.25 | LABOR- SUBCONTRACTOR
%R | 500413 | 6359 | 124407 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 0 | 0 | 200 | 0 | 1436 | 1436 | 200 | 1100 | 0 | 1100 |  |  |  | 2013-07-18 08:00 | 2013-08-19 17:00 |  | 2013-07-18 08:00 | 2013-08-19 17:00 | 2013-07-18 08:00 | 2013-08-19 17:00 | 2013-07-18 08:00 | 2013-08-19 17:00 | 2013-07-18 08:00 | 2013-08-19 17:00 |  | PT_Normal |  |  |  |  | pkUfrKknQRWb/tJJ7HG2jw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35030 | N | N | 10 | UPTO GRADE SLAB |  | 124406 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 718 | LABOR - CIVIL
%R | 500414 | 6359 | 124407 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STUG1040 | Construction of Grade Beams | 8163 | 0 | 0 | 200 | 0 | 8096.25 | 8096.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-04 08:00 | 2013-09-04 17:00 |  | 2013-08-04 08:00 | 2013-09-04 17:00 | 2013-08-04 08:00 | 2013-09-04 17:00 | 2013-08-04 08:00 | 2013-09-04 17:00 | 2013-08-04 08:00 | 2013-09-04 17:00 |  | PT_Normal |  |  |  |  | jgsiV4KlT569E9enl6aY0A |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35030 | N | N | 10 | UPTO GRADE SLAB |  | 124406 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 4048.125 | BLINDING MASON SK
%R | 500415 | 6359 | 124407 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STUG1045 | Construction of slab on grade | 8163 | 0 | 0 | 200 | 0 | 5538.75 | 5538.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-03 08:00 | 2013-10-01 17:00 |  | 2013-09-03 08:00 | 2013-10-01 17:00 | 2013-09-03 08:00 | 2013-10-01 17:00 | 2013-09-03 08:00 | 2013-10-01 17:00 | 2013-09-03 08:00 | 2013-10-01 17:00 |  | PT_Normal |  |  |  |  | 6KAY7i1nRuiJkVn+jU1EfA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35030 | N | N | 10 | UPTO GRADE SLAB |  | 124406 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 5538.75 | BLINDING MASON SK
%R | 500416 | 6359 | 124407 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STUG1025 | Construction of neck of columns | 8165 | 0 | 0 | 200 | 0 | 1946 | 1946 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-27 08:00 | 2013-07-25 17:00 |  | 2013-06-27 08:00 | 2013-07-25 17:00 | 2013-06-27 08:00 | 2013-07-25 17:00 | 2013-06-27 08:00 | 2013-07-25 17:00 | 2013-06-27 08:00 | 2013-07-25 17:00 |  | PT_Normal |  |  |  |  | aAg5mEvMQtOBCXln0LG6pA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35030 | N | N | 10 | UPTO GRADE SLAB |  | 124406 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 1946 | STEEL FIXERS SK
%R | 500417 | 6359 | 124409 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STRF2040 | Column-Rebar & Formwork | 8166 | 296 | 0 | 144 | 0 | 1176 | 1176 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-23 08:00 | 2014-02-13 17:00 |  | 2013-12-10 08:00 | 2013-12-31 17:00 | 2013-12-10 08:00 | 2013-12-31 17:00 | 2013-12-10 08:00 | 2013-12-31 17:00 | 2014-01-23 08:00 | 2014-02-13 17:00 |  | PT_Normal |  |  |  |  | lhybsTpnSx6Sp67p1uE04w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35070 | N | N | 20 | ROOF |  | 124408 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1176 | CARPENTERS SK
%R | 500418 | 6359 | 124409 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STRF2045 | Column-Concrete | 8167 | 296 | 0 | 136 | 0 | 80.5 | 80.5 | 136 | 0 | 0 | 0 |  |  |  | 2014-01-27 08:00 | 2014-02-16 17:00 |  | 2013-12-14 08:00 | 2014-01-02 17:00 | 2013-12-14 08:00 | 2014-01-02 17:00 | 2013-12-14 08:00 | 2014-01-02 17:00 | 2014-01-27 08:00 | 2014-02-16 17:00 |  | PT_Normal |  |  |  |  | 0frnIIvTTKqpxCJ8YOLHwg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35070 | N | N | 20 | ROOF |  | 124408 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 80.5 | CONCRETE MASON SK
%R | 500419 | 6359 | 124409 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STRF2050 | Slab-Rebar & Formwork - Head Room | 8165 | 296 | 0 | 160 | 0 | 3444 | 3444 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-29 08:00 | 2014-02-22 17:00 |  | 2013-12-16 08:00 | 2014-01-08 17:00 | 2013-12-16 08:00 | 2014-01-08 17:00 | 2013-12-16 08:00 | 2014-01-08 17:00 | 2014-01-29 08:00 | 2014-02-22 17:00 |  | PT_Normal |  |  |  |  | bkEFW8fpTuGk3NJ/zW8LaQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35070 | N | N | 20 | ROOF |  | 124408 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 3444 | STEEL FIXERS SK
%R | 500420 | 6359 | 124409 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STRF2055 | Slab-Concrete-Head room | 8167 | 296 | 0 | 104 | 0 | 280 | 280 | 104 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-02-27 17:00 |  | 2013-12-31 08:00 | 2014-01-14 17:00 | 2013-12-31 08:00 | 2014-01-14 17:00 | 2013-12-31 08:00 | 2014-01-14 17:00 | 2014-02-13 08:00 | 2014-02-27 17:00 |  | PT_Normal |  |  |  |  | 1U8Sp4PvQKqdRELg0akV2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35070 | N | N | 20 | ROOF |  | 124408 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 280 | CONCRETE MASON SK
%R | 500421 | 6359 | 124409 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STRF2060 | Construction of Parapets | 8168 | 488 | 0 | 200 | 0 | 1175 | 1175 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-16 08:00 | 2014-04-13 17:00 |  | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 |  | PT_Normal |  |  |  |  | NWzMSFFJRrqaWDBJ93VHtQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35070 | N | N | 20 | ROOF |  | 124408 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1175 | BLOCK MASON SK
%R | 500422 | 6359 | 124409 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STRF2065 | Construction of up stands/Plinth | 8165 | 624 | 0 | 200 | 0 | 549.5 | 549.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-24 08:00 | 2014-05-22 17:00 |  | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 |  | PT_Normal |  |  |  |  | JngciILPSo65iOgUpeI1Pw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35070 | N | N | 20 | ROOF |  | 124408 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 549.5 | STEEL FIXERS SK
%R | 500423 | 6359 | 124410 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STFF2020 | Column-Rebar & Formwork | 8166 | 0 | 0 | 200 | 0 | 3418 | 3418 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-03 08:00 | 2013-12-01 17:00 |  | 2013-11-03 08:00 | 2013-12-01 17:00 | 2013-11-03 08:00 | 2013-12-01 17:00 | 2013-11-03 08:00 | 2013-12-01 17:00 | 2013-11-03 08:00 | 2013-12-01 17:00 |  | PT_Normal |  |  |  |  | 4aQNymIcSXGGj++nu6adhQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35060 | N | N | 15 | FIRST FLOORS |  | 124408 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 3418 | CARPENTERS SK
%R | 500424 | 6359 | 124410 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STFF2025 | Column-Concrete | 8167 | 0 | 0 | 184 | 0 | 339.5 | 339.5 | 184 | 0 | 0 | 0 |  |  |  | 2013-11-12 08:00 | 2013-12-08 17:00 |  | 2013-11-12 08:00 | 2013-12-08 17:00 | 2013-11-12 08:00 | 2013-12-08 17:00 | 2013-11-12 08:00 | 2013-12-08 17:00 | 2013-11-12 08:00 | 2013-12-08 17:00 |  | PT_Normal |  |  |  |  | AvWSHubUQX6c1odDk2e5zQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35060 | N | N | 15 | FIRST FLOORS |  | 124408 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 339.5 | CONCRETE MASON SK
%R | 500425 | 6359 | 124410 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 96 | 0 | 200 | 0 | 19080.25 | 19080.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-30 08:00 | 2013-12-29 17:00 |  | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 |  | PT_Normal |  |  |  |  | eq/1cijJSlenkWr5jqepxw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35060 | N | N | 15 | FIRST FLOORS |  | 124408 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 19080.25 | STEEL FIXERS SK
%R | 500426 | 6359 | 124410 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 96 | 16 | 112 | 0 | 1288 | 1288 | 112 | 0 | 0 | 0 |  |  |  | 2013-12-16 08:00 | 2014-01-01 17:00 |  | 2013-12-02 08:00 | 2013-12-17 17:00 | 2013-12-02 08:00 | 2013-12-17 17:00 | 2013-12-02 08:00 | 2013-12-17 17:00 | 2013-12-16 08:00 | 2014-01-01 17:00 |  | PT_Normal |  |  |  |  | WvB8cA/5T4W66laQvUvi8g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35060 | N | N | 15 | FIRST FLOORS |  | 124408 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1288 | CONCRETE MASON SK
%R | 500427 | 6359 | 124411 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STGF2000 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 4984 | 4984 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-19 08:00 | 2013-10-20 17:00 |  | 2013-09-19 08:00 | 2013-10-20 17:00 | 2013-09-19 08:00 | 2013-10-20 17:00 | 2013-09-19 08:00 | 2013-10-20 17:00 | 2013-09-19 08:00 | 2013-10-20 17:00 |  | PT_Normal |  |  |  |  | l8V7u8R7QFO+4FgFoD0SYQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35050 | N | N | 10 | GROUND FLOOR |  | 124408 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 2492 | STEEL FIXERS SK
%R | 500428 | 6359 | 124411 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STGF2005 | Column-Concrete | 8167 | 0 | 0 | 184 | 0 | 388.5 | 388.5 | 184 | 0 | 0 | 0 |  |  |  | 2013-09-29 08:00 | 2013-10-27 17:00 |  | 2013-09-29 08:00 | 2013-10-27 17:00 | 2013-09-29 08:00 | 2013-10-27 17:00 | 2013-09-29 08:00 | 2013-10-27 17:00 | 2013-09-29 08:00 | 2013-10-27 17:00 |  | PT_Normal |  |  |  |  | MKFmBnefSzycO0y2Q6k9GQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35050 | N | N | 10 | GROUND FLOOR |  | 124408 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 388.5 | CONCRETE MASON SK
%R | 500429 | 6359 | 124411 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 18721.5 | 18721.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-13 08:00 | 2013-11-12 17:00 |  | 2013-10-13 08:00 | 2013-11-12 17:00 | 2013-10-13 08:00 | 2013-11-12 17:00 | 2013-10-13 08:00 | 2013-11-12 17:00 | 2013-10-13 08:00 | 2013-11-12 17:00 |  | PT_Normal |  |  |  |  | dSWmb4eFSje9ZwpkG7cXdw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35050 | N | N | 10 | GROUND FLOOR |  | 124408 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 18721.5 | STEEL FIXERS SK
%R | 500430 | 6359 | 124411 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 0 | 0 | 112 | 0 | 1456 | 1456 | 112 | 0 | 0 | 0 |  |  |  | 2013-10-31 08:00 | 2013-11-16 17:00 |  | 2013-10-31 08:00 | 2013-11-16 17:00 | 2013-10-31 08:00 | 2013-11-16 17:00 | 2013-10-31 08:00 | 2013-11-16 17:00 | 2013-10-31 08:00 | 2013-11-16 17:00 |  | PT_Normal |  |  |  |  | 3q/MvI9kQEaVrY6m/yU74A |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35050 | N | N | 10 | GROUND FLOOR |  | 124408 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1456 | CONCRETE MASON SK
%R | 500431 | 6359 | 124413 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2SLEX5105 | Laying of Grass/ green area | 8178 | 552 | 0 | 200 | 0 | 5488 | 5488 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-07-03 17:00 |  | 2014-03-17 08:00 | 2014-04-14 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 | 2014-06-05 08:00 | 2014-07-03 17:00 |  | PT_Normal |  |  |  |  | dIOvtSH/SF+OS2OM9RO7og |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35340 | N | N | 25 | SOFT LANDSCAPING |  | 124412 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 5488 | LABOR- SUBCONTRACTOR
%R | 500432 | 6359 | 124413 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2SLEX5110 | Laying of Palm tree | 8178 | 552 | 528 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-03-29 08:00 | 2014-04-26 17:00 | 2014-03-29 08:00 | 2014-04-26 17:00 | 2014-03-29 08:00 | 2014-04-26 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | TAhPToLdSye0sTs1eVnsgQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35340 | N | N | 25 | SOFT LANDSCAPING |  | 124412 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 336 | LABOR- SUBCONTRACTOR
%R | 500433 | 6359 | 124414 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 200 | 0 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | XTspQdqjT/OEvXzZbRX/+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35310 | N | N | 10 | MISCELLANEOUS |  | 124412 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 400 | LABOR- SUBCONTRACTOR
%R | 500434 | 6359 | 124414 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2MSEX5020 | Construction Entrance Ramp | 8164 | 552 | 0 | 200 | 0 | 1288 | 1288 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-28 17:00 |  | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | KwQS8i34QrSHgbPK4q3eUQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35310 | N | N | 10 | MISCELLANEOUS |  | 124412 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1288 | SCREED MASON SK
%R | 500435 | 6359 | 124414 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2MSEX5025 | SS.Handrails and Balustrades | 8178 | 552 | 0 | 160 | 0 | 400 | 400 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-12 17:00 |  | 2014-01-28 08:00 | 2014-02-20 17:00 | 2014-01-28 08:00 | 2014-02-20 17:00 | 2014-01-28 08:00 | 2014-02-20 17:00 | 2014-04-20 08:00 | 2014-05-12 17:00 |  | PT_Normal |  |  |  |  | +9u9AQpXRGm5nlAV7JJXOg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35310 | N | N | 10 | MISCELLANEOUS |  | 124412 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 400 | LABOR- SUBCONTRACTOR
%R | 500436 | 6359 | 124414 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2MSEX5015 | Construction of grease Trap | 8178 | 296 | 0 | 160 | 0 | 88 | 88 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-22 17:00 |  | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | Nnn0cuPkTEOC+ffNt8X3TA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35310 | N | N | 10 | MISCELLANEOUS |  | 124412 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 88 | LABOR- SUBCONTRACTOR
%R | 500437 | 6359 | 124414 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2MSEX5000 | Construction of Manholes | 8172 | 296 | 0 | 200 | 0 | 880 | 880 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-25 08:00 | 2014-03-25 17:00 |  | 2014-01-12 08:00 | 2014-02-09 17:00 | 2014-01-12 08:00 | 2014-02-09 17:00 | 2014-01-12 08:00 | 2014-02-09 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 |  | PT_Normal |  |  |  |  | VVj6vEiMRwqqu3KaWbaarg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35310 | N | N | 10 | MISCELLANEOUS |  | 124412 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 880 | MANHOLES SK
%R | 500438 | 6359 | 124414 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2MSEX5010 | Telephone cable laying | 8177 | 296 | 96 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-05-21 17:00 |  | 2014-03-11 08:00 | 2014-04-08 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | 0vN4B8arQz+5W+OLBMrK6w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35310 | N | N | 10 | MISCELLANEOUS |  | 124412 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 500 | LABOR - CIVIL
%R | 500439 | 6359 | 124414 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2MSEX5005 | Construction of Soak pit, Chambers | 8172 | 296 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-04-08 17:00 |  | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | sn5IsH91To6HIlg6EvO7xw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35310 | N | N | 10 | MISCELLANEOUS |  | 124412 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 176 | MANHOLES SK
%R | 500440 | 6359 | 124415 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2WEEX5030 | Excavation | 8177 | 408 | 0 | 160 | 0 | 128 | 128 | 160 | 80 | 0 | 80 |  |  |  | 2014-03-18 08:00 | 2014-04-09 17:00 |  | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-03-18 08:00 | 2014-04-09 17:00 |  | PT_Normal |  |  |  |  | 96tG1NC2TYeQexTQco0hpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35320 | N | N | 15 | WATER TANK ENCLOSURE |  | 124412 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 128 | LABOR - CIVIL
%R | 500441 | 6359 | 124415 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2WEEX5035 | Construction of Raft | 8165 | 408 | 0 | 200 | 0 | 1624 | 1624 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-24 08:00 | 2014-04-21 17:00 |  | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-03-24 08:00 | 2014-04-21 17:00 |  | PT_Normal |  |  |  |  | 2JSmjWFQSnWlSwobW58Jpw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35320 | N | N | 15 | WATER TANK ENCLOSURE |  | 124412 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1624 | STEEL FIXERS SK
%R | 500442 | 6359 | 124415 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2WEEX5040 | Block works & Plastering | 8168 | 592 | 0 | 200 | 0 | 888 | 888 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-01 08:00 | 2014-05-29 17:00 |  | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | Nh6InJk7T3ib0zOWIb5E3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35320 | N | N | 15 | WATER TANK ENCLOSURE |  | 124412 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 444 | BLOCK MASON SK
%R | 500443 | 6359 | 124415 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2WEEX5045 | Flooring & Painting | 8178 | 592 | 0 | 200 | 0 | 408 | 408 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-06-10 17:00 |  | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-05-13 08:00 | 2014-06-10 17:00 |  | PT_Normal |  |  |  |  | WFTnNFadT8SeuaOtkWVWMA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35320 | N | N | 15 | WATER TANK ENCLOSURE |  | 124412 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 204 | LABOR- SUBCONTRACTOR
%R | 500444 | 6359 | 124415 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2WEEX5050 | Installation of Steel Gate | 8178 | 592 | 24 | 160 | 0 | 112 | 112 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-31 08:00 | 2014-06-22 17:00 |  | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-05-31 08:00 | 2014-06-22 17:00 |  | PT_Normal |  |  |  |  | Y4w3FF1iQH6S5Elh/a1BZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35320 | N | N | 15 | WATER TANK ENCLOSURE |  | 124412 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 112 | LABOR- SUBCONTRACTOR
%R | 500445 | 6359 | 124415 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 568 | 0 | 200 | 0 | 616 | 616 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-07-03 17:00 |  | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-06-05 08:00 | 2014-07-03 17:00 |  | PT_Normal |  |  |  |  | i1f1QLx2QNCCQw/2PhscsQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35320 | N | N | 15 | WATER TANK ENCLOSURE |  | 124412 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 616 | LABOR- SUBCONTRACTOR
%R | 500446 | 6359 | 124415 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 568 | 40 | 200 | 0 | 382.4 | 382.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | 6jGwHW7cQ2mVIjOrk/Auyw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35320 | N | N | 15 | WATER TANK ENCLOSURE |  | 124412 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 382.4 | LABOR- SUBCONTRACTOR
%R | 500447 | 6359 | 124416 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2HDEX5090 | kerb works | 8173 | 552 | 0 | 160 | 0 | 712 | 712 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-28 08:00 | 2014-05-20 17:00 |  | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-04-28 08:00 | 2014-05-20 17:00 |  | PT_Normal |  |  |  |  | 6fjKgGPgQcOF/gdxQ6Q1Dg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35330 | N | N | 20 | HARD LANDSCAPING |  | 124412 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 712 | KERBSTONE MASON SK
%R | 500448 | 6359 | 124416 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2HDEX5095 | Cobble Stone Works | 8170 | 552 | 0 | 160 | 0 | 456 | 456 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-10 08:00 | 2014-06-01 17:00 |  | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-05-10 08:00 | 2014-06-01 17:00 |  | PT_Normal |  |  |  |  | 8T3PriC6Sl6gJ5rm4flWKg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35330 | N | N | 20 | HARD LANDSCAPING |  | 124412 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 456 | TILE MASON SK
%R | 500449 | 6359 | 124416 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ2HDEX5100 | Interlock works | 8174 | 552 | 0 | 160 | 0 | 408 | 408 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-25 08:00 | 2014-06-16 17:00 |  | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-05-25 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | M+fSENB3QJO1H82YwcGB2Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35330 | N | N | 20 | HARD LANDSCAPING |  | 124412 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 408 | INTERLOCK MASON SK
%R | 500450 | 6359 | 124417 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BGNSP001000 | Survey works, | 8175 | 296 | 0 | 160 | 0 | 87.5 | 87.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-01-14 08:00 | 2013-02-05 17:00 |  | 2012-12-01 08:00 | 2012-12-24 17:00 | 2012-12-01 08:00 | 2012-12-24 17:00 | 2012-12-01 08:00 | 2012-12-24 17:00 | 2013-01-14 08:00 | 2013-02-05 17:00 |  | PT_Normal |  |  |  |  | x6xKApHAQSOTzR7gfBU2Ow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43520 |  |  |  |  | SURVEYOR SK | J315 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124381 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 87.5 | SURVEYOR SK
%R | 500451 | 6359 | 124417 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BGNSP002000 | Scanning for Existing Services for rerouting | 8180 | 296 | 0 | 80 | 0 | 325 | 325 | 80 | 0 | 0 | 0 |  |  |  | 2013-01-20 08:00 | 2013-01-30 17:00 |  | 2012-12-06 08:00 | 2012-12-17 17:00 | 2012-12-06 08:00 | 2012-12-17 17:00 | 2012-12-06 08:00 | 2012-12-17 17:00 | 2013-01-20 08:00 | 2013-01-30 17:00 |  | PT_Normal |  |  |  |  | 8ioC8kigRASnvkd8X+Ehfw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43571 |  |  |  |  | ELECTRICIANS SK | M302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124381 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 325 | ELECTRICIANS SK
%R | 500452 | 6359 | 124417 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BGNSP004000 | Demolition of Existing building & landscaping | 8177 | 696 | 0 | 160 | 0 | 2687.5 | 2687.5 | 160 | 1750 | 0 | 1750 |  |  |  | 2013-04-02 08:00 | 2013-04-24 17:00 |  | 2012-12-20 08:00 | 2013-01-12 17:00 | 2012-12-20 08:00 | 2013-01-12 17:00 | 2012-12-20 08:00 | 2013-01-12 17:00 | 2013-04-02 08:00 | 2013-04-24 17:00 |  | PT_Normal |  |  |  |  | s3GZzjTZRbuAVTEGLWEIkQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124381 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 2687.5 | LABOR - CIVIL
%R | 500453 | 6359 | 124417 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BGNSP005000 | Demolition of existing services works | 8177 | 696 | 696 | 160 | 0 | 775 | 775 | 160 | 400 | 0 | 400 |  |  |  | 2013-04-08 08:00 | 2013-04-30 17:00 |  | 2012-12-26 08:00 | 2013-01-17 17:00 | 2012-12-26 08:00 | 2013-01-17 17:00 | 2012-12-26 08:00 | 2013-01-17 17:00 | 2013-04-08 08:00 | 2013-04-30 17:00 |  | PT_Normal |  |  |  |  | injzK6tpRyCsOHmv8LTDRw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124381 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 775 | LABOR - CIVIL
%R | 500454 | 6359 | 124417 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BGNSP003000 | Site stripping | 8177 | 696 | 0 | 160 | 0 | 675 | 675 | 160 | 300 | 0 | 300 |  |  |  | 2013-03-27 08:00 | 2013-04-18 17:00 |  | 2012-12-13 08:00 | 2013-01-06 17:00 | 2012-12-13 08:00 | 2013-01-06 17:00 | 2012-12-13 08:00 | 2013-01-06 17:00 | 2013-03-27 08:00 | 2013-04-18 17:00 |  | PT_Normal |  |  |  |  | 3fgfuo7nSXq0iCUItedqlw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124381 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 675 | LABOR - CIVIL
%R | 500455 | 6359 | 124417 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BGNSP002100 | Submission of Scanning Reports | 12515 | 296 | 0 | 40 | 0 | 40 | 40 | 40 | 0 | 0 | 0 |  |  |  | 2013-01-31 08:00 | 2013-02-05 17:00 |  | 2012-12-19 08:00 | 2012-12-24 17:00 | 2012-12-19 08:00 | 2012-12-24 17:00 | 2012-12-19 08:00 | 2012-12-24 17:00 | 2013-01-31 08:00 | 2013-02-05 17:00 |  | PT_Normal |  |  |  |  | 3cXxqHQWR721YRNCyXe0Tg | JRFiGGBnTCaUtxRsMC9IFg |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [5 empty] | 45403 |  |  |  |  | QUANTITY SURVEYOUR | M305 |  | 1 | QT_Hour |  | Y | Y | N | 1 |  | RT_Labor |  |  |  |  | 540 | 34630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124381 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 40 | QUANTITY SURVEYOUR
%R | 500456 | 6359 | 124417 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BGNSP002200 | Information Required for Rerouting |  | 296 | 0 | 112 | 0 | 0 | 0 | 112 | 0 | 0 | 0 |  |  |  | 2013-02-06 08:00 | 2013-02-23 17:00 |  | 2012-12-25 08:00 | 2013-01-09 17:00 | 2012-12-25 08:00 | 2013-01-09 17:00 | 2012-12-25 08:00 | 2013-01-09 17:00 | 2013-02-06 08:00 | 2013-02-23 17:00 |  | PT_Normal |  |  |  |  | FBR1ZwgcT9Kw4sl4ax7kjA | JRFiGGBnTCaUtxRsMC9IFg |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 34630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124381 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 500457 | 6359 | 124417 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BGNSP002300 | Preparation & Submission for new Layout for rerouting |  | 296 | 0 | 56 | 0 | 40 | 40 | 56 | 0 | 0 | 0 |  |  |  | 2013-02-24 08:00 | 2013-03-03 17:00 |  | 2013-01-10 08:00 | 2013-01-17 17:00 | 2013-01-10 08:00 | 2013-01-17 17:00 | 2013-01-10 08:00 | 2013-01-17 17:00 | 2013-02-24 08:00 | 2013-03-03 17:00 |  | PT_Normal |  |  |  |  | hRwoBKjDQJSDpAQFycC4bA | 1UOtSVyUzUukS/S9jaCffQ |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 34630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124381 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 40 | 0
%R | 500458 | 6359 | 124417 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BGNSP002400 | Approval for new Layout for rerouting |  | 296 | 0 | 80 | 0 | 0 | 0 | 80 | 0 | 0 | 0 |  |  |  | 2013-03-04 08:00 | 2013-03-14 17:00 |  | 2013-01-19 08:00 | 2013-01-29 17:00 | 2013-01-19 08:00 | 2013-01-29 17:00 | 2013-01-19 08:00 | 2013-01-29 17:00 | 2013-03-04 08:00 | 2013-03-14 17:00 |  | PT_Normal |  |  |  |  | d8osTHRqS6q0rHBxUEIYqw | JuGELodzY0efmuSLH0uRig |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 34630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124381 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 0 | 0
%R | 500459 | 6359 | 124417 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BGNSP002500 | Rerouting Works | 8180 | 296 | 296 | 200 | 0 | 325 | 325 | 200 | 0 | 0 | 0 |  |  |  | 2013-03-16 08:00 | 2013-04-13 17:00 |  | 2013-01-30 08:00 | 2013-02-28 17:00 | 2013-01-30 08:00 | 2013-02-28 17:00 | 2013-01-30 08:00 | 2013-02-28 17:00 | 2013-03-16 08:00 | 2013-04-13 17:00 |  | PT_Normal |  |  |  |  | 1ZluaTpFTEOvNLefMBGnxw | vmi+KZyKMUahQKTW6dbRhg |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43571 |  |  |  |  | ELECTRICIANS SK | M302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124381 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 325 | ELECTRICIANS SK
%R | 500460 | 6359 | 124421 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ACFF4615 | Installation AC Pipes | 8178 | 368 | 24 | 160 | 0 | 2358 | 2358 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-09 08:00 | 2014-07-31 17:00 |  | 2014-05-17 08:00 | 2014-06-08 17:00 | 2014-05-17 08:00 | 2014-06-08 17:00 | 2014-05-17 08:00 | 2014-06-08 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 |  | PT_Normal |  |  |  |  | HvvnKNERTaqDlwJx3iox2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36350 | N | N | 15 | FIRST FLOORS |  | 124420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 2358 | LABOR- SUBCONTRACTOR
%R | 500461 | 6359 | 124421 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ACFF4620 | Fixing of Ventilation Equipments | 8178 | 136 | 0 | 200 | 0 | 228 | 228 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-14 08:00 | 2014-09-11 17:00 |  | 2014-07-22 08:00 | 2014-08-23 17:00 | 2014-07-22 08:00 | 2014-08-23 17:00 | 2014-07-22 08:00 | 2014-08-23 17:00 | 2014-08-14 08:00 | 2014-09-11 17:00 |  | PT_Normal |  |  |  |  | fOxOr+GDRUatgrhc1BaMzg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36350 | N | N | 15 | FIRST FLOORS |  | 124420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 114 | LABOR- SUBCONTRACTOR
%R | 500462 | 6359 | 124421 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ACFF4625 | Fixing of Split AC | 8178 | 136 | 0 | 160 | 0 | 710 | 710 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-04 08:00 | 2014-09-27 17:00 |  | 2014-08-16 08:00 | 2014-09-07 17:00 | 2014-08-16 08:00 | 2014-09-07 17:00 | 2014-08-16 08:00 | 2014-09-07 17:00 | 2014-09-04 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | LcQqXfK/RvO7pIM+jcBDZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36350 | N | N | 15 | FIRST FLOORS |  | 124420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 710 | LABOR- SUBCONTRACTOR
%R | 500463 | 6359 | 124422 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ACRF4630 | Installation of Refrigerant Pipes | 8178 | 696 | 0 | 200 | 0 | 994 | 994 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-10-08 17:00 |  | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-09-10 08:00 | 2014-10-08 17:00 |  | PT_Normal |  |  |  |  | IoWLfgk4Tw+YJA6VK1uxdA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36360 | N | N | 20 | ROOF |  | 124420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 994 | LABOR- SUBCONTRACTOR
%R | 500464 | 6359 | 124422 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ACRF4635 | Installation of Condensing Unit | 8178 | 176 | 0 | 200 | 0 | 1420 | 1420 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-08-21 08:00 | 2014-09-18 17:00 | 2014-08-21 08:00 | 2014-09-18 17:00 | 2014-08-21 08:00 | 2014-09-18 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | o/V59/2iRc2AFygEporbxg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36360 | N | N | 20 | ROOF |  | 124420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1420 | LABOR- SUBCONTRACTOR
%R | 500465 | 6359 | 124423 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ACGF4600 | Installation AC Pipes | 8178 | 640 | 40 | 160 | 0 | 2358 | 2358 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-03 08:00 | 2014-07-26 17:00 |  | 2014-04-01 08:00 | 2014-04-23 17:00 | 2014-04-01 08:00 | 2014-04-23 17:00 | 2014-04-01 08:00 | 2014-04-23 17:00 | 2014-07-03 08:00 | 2014-07-26 17:00 |  | PT_Normal |  |  |  |  | 4GYg+uGbSES/xRhE+ONhkQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36340 | N | N | 10 | GROUND FLOOR |  | 124420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 2358 | LABOR- SUBCONTRACTOR
%R | 500466 | 6359 | 124423 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ACGF4605 | Fixing of Ventilation Equipments | 8178 | 544 | 0 | 200 | 0 | 370 | 370 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-14 08:00 | 2014-09-11 17:00 |  | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-08-14 08:00 | 2014-09-11 17:00 |  | PT_Normal |  |  |  |  | BNU3d5fgSGKHewjSf5SqqA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36340 | N | N | 10 | GROUND FLOOR |  | 124420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 370 | LABOR- SUBCONTRACTOR
%R | 500467 | 6359 | 124423 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ACGF4610 | Fixing of Split AC | 8178 | 544 | 40 | 160 | 0 | 710 | 710 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-04 08:00 | 2014-09-27 17:00 |  | 2014-06-14 08:00 | 2014-07-06 17:00 | 2014-06-14 08:00 | 2014-07-06 17:00 | 2014-06-14 08:00 | 2014-07-06 17:00 | 2014-09-04 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | NoMZf4ifR7CAkLD0Jz+3/A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36340 | N | N | 10 | GROUND FLOOR |  | 124420 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 710 | LABOR- SUBCONTRACTOR
%R | 500468 | 6359 | 124425 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ELRF4070 | Installation of Isolator | 8178 | 24 | 0 | 144 | 0 | 1032 | 1032 | 144 | 0 | 0 | 0 |  |  |  | 2014-09-07 08:00 | 2014-09-27 17:00 |  | 2014-09-03 08:00 | 2014-09-23 17:00 | 2014-09-03 08:00 | 2014-09-23 17:00 | 2014-09-03 08:00 | 2014-09-23 17:00 | 2014-09-07 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | gtJcQ/LmTJyHJeJkQVwnQw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36280 | N | N | 20 | ROOF |  | 124424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 1032 | LABOR- SUBCONTRACTOR
%R | 500469 | 6359 | 124425 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ELRF4075 | Installation of TV Dish Antenna | 8178 | 24 | 0 | 184 | 0 | 2288 | 2288 | 184 | 0 | 0 | 0 |  |  |  | 2014-09-18 08:00 | 2014-10-16 17:00 |  | 2014-09-15 08:00 | 2014-10-13 17:00 | 2014-09-15 08:00 | 2014-10-13 17:00 | 2014-09-15 08:00 | 2014-10-13 17:00 | 2014-09-18 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | DwVKC+/YQ9GhE3XKSKAacg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36280 | N | N | 20 | ROOF |  | 124424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 2288 | LABOR- SUBCONTRACTOR
%R | 500470 | 6359 | 124426 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 464 | 0 | 200 | 0 | 3224 | 3224 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-08 08:00 | 2014-06-05 17:00 |  | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-05-08 08:00 | 2014-06-05 17:00 |  | PT_Normal |  |  |  |  | bLEuKto4RbK02aPzKwJjfQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36260 | N | N | 10 | GROUND FLOOR |  | 124424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 3224 | LABOR- SUBCONTRACTOR
%R | 500471 | 6359 | 124426 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ELGF4005 | Cable tray & trunking installation | 8178 | 608 | 0 | 160 | 0 | 3976 | 3976 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-10 08:00 | 2014-07-02 17:00 |  | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-06-10 08:00 | 2014-07-02 17:00 |  | PT_Normal |  |  |  |  | 447Yjrx5Qsu+jyhVcieG3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36260 | N | N | 10 | GROUND FLOOR |  | 124424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 3976 | LABOR- SUBCONTRACTOR
%R | 500472 | 6359 | 124426 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 392 | 0 | 160 | 0 | 568 | 568 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-26 08:00 | 2014-08-20 17:00 |  | 2014-05-29 08:00 | 2014-06-21 17:00 | 2014-05-29 08:00 | 2014-06-21 17:00 | 2014-05-29 08:00 | 2014-06-21 17:00 | 2014-07-26 08:00 | 2014-08-20 17:00 |  | PT_Normal |  |  |  |  | CKUAqAzPQFOjNLeJsyoPxw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36260 | N | N | 10 | GROUND FLOOR |  | 124424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 568 | LABOR- SUBCONTRACTOR
%R | 500473 | 6359 | 124426 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 408 | 0 | 200 | 0 | 4128 | 4128 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-09-09 17:00 |  | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-08-12 08:00 | 2014-09-09 17:00 |  | PT_Normal |  |  |  |  | YAVUebhgQCmaPaKY/ZEB2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36260 | N | N | 10 | GROUND FLOOR |  | 124424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 4128 | LABOR- SUBCONTRACTOR
%R | 500474 | 6359 | 124426 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 568 | 0 | 200 | 0 | 5712 | 5712 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | 0OCJSATjQ3CXf9S0sDGgGA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36260 | N | N | 10 | GROUND FLOOR |  | 124424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 5712 | LABOR- SUBCONTRACTOR
%R | 500475 | 6359 | 124426 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ELGF4030 | Installation of Telephone System | 8178 | 392 | 40 | 160 | 0 | 1778 | 1778 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-10 08:00 | 2014-09-01 17:00 |  | 2014-06-10 08:00 | 2014-07-02 17:00 | 2014-06-10 08:00 | 2014-07-02 17:00 | 2014-06-10 08:00 | 2014-07-02 17:00 | 2014-08-10 08:00 | 2014-09-01 17:00 |  | PT_Normal |  |  |  |  | kuIxR4IWQZyBNsSQKDrLmg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36260 | N | N | 10 | GROUND FLOOR |  | 124424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1778 | LABOR- SUBCONTRACTOR
%R | 500476 | 6359 | 124426 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ELGF4010 | Installation of wiring & Main Cabling | 8178 | 608 | 216 | 200 | 0 | 796 | 796 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-18 08:00 | 2014-07-16 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-06-18 08:00 | 2014-07-16 17:00 |  | PT_Normal |  |  |  |  | 0VjRCH2HSMmMWEn098n+Hw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36260 | N | N | 10 | GROUND FLOOR |  | 124424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 796 | LABOR- SUBCONTRACTOR
%R | 500477 | 6359 | 124427 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 128 | 0 | 200 | 0 | 3224 | 3224 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-30 08:00 | 2014-05-28 17:00 |  | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 |  | PT_Normal |  |  |  |  | hxs+5OfYTNyh+LEmWRv2nA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36270 | N | N | 15 | FIRST FLOORS |  | 124424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 3224 | LABOR- SUBCONTRACTOR
%R | 500478 | 6359 | 124427 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ELFF4040 | Cable tray & trunking installation | 8178 | 368 | 0 | 160 | 0 | 3976 | 3976 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-16 08:00 | 2014-07-08 17:00 |  | 2014-04-23 08:00 | 2014-05-15 17:00 | 2014-04-23 08:00 | 2014-05-15 17:00 | 2014-04-23 08:00 | 2014-05-15 17:00 | 2014-06-16 08:00 | 2014-07-08 17:00 |  | PT_Normal |  |  |  |  | WJ0yraXpTFmzYWXeQtNpBQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36270 | N | N | 15 | FIRST FLOORS |  | 124424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 3976 | LABOR- SUBCONTRACTOR
%R | 500479 | 6359 | 124427 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ELFF4045 | Installation of wiring & Main Cabling | 8178 | 368 | 0 | 200 | 0 | 796 | 796 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-24 08:00 | 2014-07-22 17:00 |  | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-06-24 08:00 | 2014-07-22 17:00 |  | PT_Normal |  |  |  |  | e5O7Sqf2SIum5If8eJAE4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36270 | N | N | 15 | FIRST FLOORS |  | 124424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 796 | LABOR- SUBCONTRACTOR
%R | 500480 | 6359 | 124427 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 24 | 0 | 160 | 0 | 568 | 568 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-05 08:00 | 2014-08-27 17:00 |  | 2014-07-29 08:00 | 2014-08-24 17:00 | 2014-07-29 08:00 | 2014-08-24 17:00 | 2014-07-29 08:00 | 2014-08-24 17:00 | 2014-08-05 08:00 | 2014-08-27 17:00 |  | PT_Normal |  |  |  |  | FS2sLllYQW22ZHeLyPEFIA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36270 | N | N | 15 | FIRST FLOORS |  | 124424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 568 | LABOR- SUBCONTRACTOR
%R | 500481 | 6359 | 124427 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 24 | 0 | 200 | 0 | 4128 | 4128 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-08-14 08:00 | 2014-09-11 17:00 | 2014-08-14 08:00 | 2014-09-11 17:00 | 2014-08-14 08:00 | 2014-09-11 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | BmN7pR+oTniFnOyh8ymdLQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36270 | N | N | 15 | FIRST FLOORS |  | 124424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 4128 | LABOR- SUBCONTRACTOR
%R | 500482 | 6359 | 124427 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 360 | 0 | 200 | 0 | 5712 | 5712 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-07-22 08:00 | 2014-08-23 17:00 | 2014-07-22 08:00 | 2014-08-23 17:00 | 2014-07-22 08:00 | 2014-08-23 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | 1ObXva20Q+KvBSIxcPRaQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36270 | N | N | 15 | FIRST FLOORS |  | 124424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 2856 | LABOR- SUBCONTRACTOR
%R | 500483 | 6359 | 124427 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ELFF4050 | Installation of Telephone System | 8178 | 200 | 176 | 200 | 0 | 1778 | 1778 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-21 08:00 | 2014-09-18 17:00 |  | 2014-07-20 08:00 | 2014-08-20 17:00 | 2014-07-20 08:00 | 2014-08-20 17:00 | 2014-07-20 08:00 | 2014-08-20 17:00 | 2014-08-21 08:00 | 2014-09-18 17:00 |  | PT_Normal |  |  |  |  | GnQ6+VqtQmWrZ2X+PbGn5w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36270 | N | N | 15 | FIRST FLOORS |  | 124424 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 889 | LABOR- SUBCONTRACTOR
%R | 500484 | 6359 | 124429 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 392 | 0 | 144 | 0 | 1104 | 1104 | 144 | 0 | 0 | 0 |  |  |  | 2014-05-08 08:00 | 2014-05-28 17:00 |  | 2014-03-12 08:00 | 2014-04-01 17:00 | 2014-03-12 08:00 | 2014-04-01 17:00 | 2014-03-12 08:00 | 2014-04-01 17:00 | 2014-05-08 08:00 | 2014-05-28 17:00 |  | PT_Normal |  |  |  |  | datvyTzOSb2xWCffoEL5vg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36300 | N | N | 10 | GROUND FLOOR |  | 124428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1104 | LABOR- SUBCONTRACTOR
%R | 500485 | 6359 | 124429 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5PLGF4310 | Installation of Drainage pipes &testing | 8178 | 416 | 72 | 144 | 0 | 414 | 414 | 144 | 0 | 0 | 0 |  |  |  | 2014-05-12 08:00 | 2014-06-01 17:00 |  | 2014-03-12 08:00 | 2014-04-01 17:00 | 2014-03-12 08:00 | 2014-04-01 17:00 | 2014-03-12 08:00 | 2014-04-01 17:00 | 2014-05-12 08:00 | 2014-06-01 17:00 |  | PT_Normal |  |  |  |  | bmuPArNDRgyLTTRwN7SwSw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36300 | N | N | 10 | GROUND FLOOR |  | 124428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 414 | LABOR- SUBCONTRACTOR
%R | 500486 | 6359 | 124429 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5PLGF4315 | Sanitary Fittings & Accessories | 8178 | 648 | 0 | 160 | 0 | 252 | 252 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-08 17:00 |  | 2014-06-10 08:00 | 2014-07-02 17:00 | 2014-06-10 08:00 | 2014-07-02 17:00 | 2014-06-10 08:00 | 2014-07-02 17:00 | 2014-09-16 08:00 | 2014-10-08 17:00 |  | PT_Normal |  |  |  |  | mYBVsy26Qea0Tpst1mYQIw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36300 | N | N | 10 | GROUND FLOOR |  | 124428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 252 | LABOR- SUBCONTRACTOR
%R | 500487 | 6359 | 124429 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5PLGF4320 | Installation of Water Heater | 8178 | 648 | 80 | 120 | 0 | 252 | 252 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-28 08:00 | 2014-10-16 17:00 |  | 2014-06-22 08:00 | 2014-07-08 17:00 | 2014-06-22 08:00 | 2014-07-08 17:00 | 2014-06-22 08:00 | 2014-07-08 17:00 | 2014-09-28 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | LK32xj94QGa4LPJXwnDRQA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36300 | N | N | 10 | GROUND FLOOR |  | 124428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 252 | LABOR- SUBCONTRACTOR
%R | 500488 | 6359 | 124429 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 88 | 0 | 160 | 0 | 138 | 138 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-07 08:00 | 2013-12-30 17:00 |  | 2013-11-24 08:00 | 2013-12-16 17:00 | 2013-11-24 08:00 | 2013-12-16 17:00 | 2013-11-24 08:00 | 2013-12-16 17:00 | 2013-12-07 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | BtHBFkrsSm6be6SWwN2a7w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36300 | N | N | 10 | GROUND FLOOR |  | 124428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 138 | LABOR- SUBCONTRACTOR
%R | 500489 | 6359 | 124430 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 24 | 0 | 144 | 0 | 1104 | 1104 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-27 08:00 | 2014-05-17 17:00 |  | 2014-04-23 08:00 | 2014-05-13 17:00 | 2014-04-23 08:00 | 2014-05-13 17:00 | 2014-04-23 08:00 | 2014-05-13 17:00 | 2014-04-27 08:00 | 2014-05-17 17:00 |  | PT_Normal |  |  |  |  | xg97YbxgQRG+8MV0Zluwig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36310 | N | N | 15 | FIRST FLOORS |  | 124428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1104 | LABOR- SUBCONTRACTOR
%R | 500490 | 6359 | 124430 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5PLFF4330 | Installation of Drainage pipes & testing | 8178 | 240 | 56 | 144 | 0 | 414 | 414 | 144 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-17 17:00 |  | 2014-04-23 08:00 | 2014-05-13 17:00 | 2014-04-23 08:00 | 2014-05-13 17:00 | 2014-04-23 08:00 | 2014-05-13 17:00 | 2014-05-28 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | Hf1H/i6uQ9uaoBCrSL44CA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36310 | N | N | 15 | FIRST FLOORS |  | 124428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 414 | LABOR- SUBCONTRACTOR
%R | 500491 | 6359 | 124430 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5PLFF4335 | Sanitary Fittings & Accessories | 8178 | 152 | 0 | 160 | 0 | 252 | 252 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-21 17:00 |  | 2014-08-07 08:00 | 2014-08-30 17:00 | 2014-08-07 08:00 | 2014-08-30 17:00 | 2014-08-07 08:00 | 2014-08-30 17:00 | 2014-08-30 08:00 | 2014-09-21 17:00 |  | PT_Normal |  |  |  |  | d6BJlXuxSaubhrSSUsR0iQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36310 | N | N | 15 | FIRST FLOORS |  | 124428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 252 | LABOR- SUBCONTRACTOR
%R | 500492 | 6359 | 124430 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5PLFF4340 | Installation of Water Heater | 8178 | 152 | 0 | 120 | 0 | 168 | 168 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-09-27 17:00 |  | 2014-08-19 08:00 | 2014-09-04 17:00 | 2014-08-19 08:00 | 2014-09-04 17:00 | 2014-08-19 08:00 | 2014-09-04 17:00 | 2014-09-10 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | QVscYScGQEik7LlHp1GKsg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36310 | N | N | 15 | FIRST FLOORS |  | 124428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 168 | LABOR- SUBCONTRACTOR
%R | 500493 | 6359 | 124431 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 688 | 56 | 112 | 0 | 360 | 360 | 112 | 0 | 0 | 0 |  |  |  | 2014-09-01 08:00 | 2014-09-16 17:00 |  | 2014-05-20 08:00 | 2014-06-04 17:00 | 2014-05-20 08:00 | 2014-06-04 17:00 | 2014-05-20 08:00 | 2014-06-04 17:00 | 2014-09-01 08:00 | 2014-09-16 17:00 |  | PT_Normal |  |  |  |  | EyeypzCYSMySZtfIYd27FA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36320 | N | N | 20 | ROOF |  | 124428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 360 | LABOR- SUBCONTRACTOR
%R | 500494 | 6359 | 124431 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5PLRF4350 | Installation of Rain water Pipes |  | 632 | 80 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-09-27 17:00 |  | 2014-06-07 08:00 | 2014-06-23 17:00 | 2014-06-07 08:00 | 2014-06-23 17:00 | 2014-06-07 08:00 | 2014-06-23 17:00 | 2014-09-10 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | PCa1r9RsT8GNuhkypaTGgQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 36320 | N | N | 20 | ROOF |  | 124428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 0 | 0
%R | 500495 | 6359 | 124431 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 152 | 0 | 200 | 0 | 840 | 840 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-08-25 08:00 | 2014-09-22 17:00 | 2014-08-25 08:00 | 2014-09-22 17:00 | 2014-08-25 08:00 | 2014-09-22 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | 6GFkKPVdQcyikB6Igd6dzw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36320 | N | N | 20 | ROOF |  | 124428 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 840 | LABOR- SUBCONTRACTOR
%R | 500496 | 6359 | 124433 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 200 | 0 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-09-16 08:00 | 2014-10-16 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | K8UKCMk/SgitpFxdXZ8C6g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36390 | N | N | 10 | MISCELLANEOUS |  | 124432 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 200 | LABOR- SUBCONTRACTOR
%R | 500497 | 6359 | 124433 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5MSEX5020 | Construction Entrance Ramp | 8164 | 552 | 0 | 200 | 0 | 1610 | 1610 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-26 08:00 | 2014-07-24 17:00 |  | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-06-26 08:00 | 2014-07-24 17:00 |  | PT_Normal |  |  |  |  | T440paxnTo2faga40YDu4A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36390 | N | N | 10 | MISCELLANEOUS |  | 124432 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1610 | SCREED MASON SK
%R | 500498 | 6359 | 124433 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5MSEX5025 | SS.Handrails and Balustrades | 8178 | 568 | 0 | 160 | 0 | 500 | 500 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-11 17:00 |  | 2014-04-24 08:00 | 2014-05-17 17:00 | 2014-04-24 08:00 | 2014-05-17 17:00 | 2014-04-24 08:00 | 2014-05-17 17:00 | 2014-07-16 08:00 | 2014-08-11 17:00 |  | PT_Normal |  |  |  |  | UtjayQ9lRU2E2aqg94FptA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36390 | N | N | 10 | MISCELLANEOUS |  | 124432 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 500 | LABOR- SUBCONTRACTOR
%R | 500499 | 6359 | 124433 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5MSEX5015 | Construction of grease Trap | 8178 | 344 | 0 | 160 | 0 | 110 | 110 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-26 08:00 | 2014-07-19 17:00 |  | 2014-05-07 08:00 | 2014-05-29 17:00 | 2014-05-07 08:00 | 2014-05-29 17:00 | 2014-05-07 08:00 | 2014-05-29 17:00 | 2014-06-26 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | M+HpzSTZQTi/oHsfNRGPaw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36390 | N | N | 10 | MISCELLANEOUS |  | 124432 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 110 | LABOR- SUBCONTRACTOR
%R | 500500 | 6359 | 124433 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5MSEX5000 | Construction of Manholes | 8172 | 344 | 0 | 200 | 0 | 1100 | 1100 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-24 08:00 | 2014-06-21 17:00 |  | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 |  | PT_Normal |  |  |  |  | 3Pz1goMGQEiPy3hySsi3eA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36390 | N | N | 10 | MISCELLANEOUS |  | 124432 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1100 | MANHOLES SK
%R | 500501 | 6359 | 124433 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5MSEX5005 | Construction of Soak pit, Chambers | 8172 | 344 | 0 | 200 | 0 | 220 | 220 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-07 08:00 | 2014-07-05 17:00 |  | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-06-07 08:00 | 2014-07-05 17:00 |  | PT_Normal |  |  |  |  | mGlY4wQYSAqWL8nMG8yaSg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36390 | N | N | 10 | MISCELLANEOUS |  | 124432 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 220 | MANHOLES SK
%R | 500502 | 6359 | 124433 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5MSEX5010 | Telephone cable laying | 8177 | 344 | 144 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-20 08:00 | 2014-08-20 17:00 |  | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-07-20 08:00 | 2014-08-20 17:00 |  | PT_Normal |  |  |  |  | DI+AkW7sSq6YRHK2j/tPgA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36390 | N | N | 10 | MISCELLANEOUS |  | 124432 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 500 | LABOR - CIVIL
%R | 500503 | 6359 | 124434 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5SLEX5105 | Laying of Grass/ green area | 8178 | 568 | 0 | 200 | 0 | 6860 | 6860 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-04 08:00 | 2014-10-02 17:00 |  | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-09-04 08:00 | 2014-10-02 17:00 |  | PT_Normal |  |  |  |  | EGbh3b0oQBWTLdJkSVUgTw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36420 | N | N | 25 | SOFT LANDSCAPING |  | 124432 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 6860 | LABOR- SUBCONTRACTOR
%R | 500504 | 6359 | 124434 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5SLEX5110 | Laying of Palm tree | 8178 | 568 | 544 | 200 | 0 | 420 | 420 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | bYfr5jrmSeOTRgZ2h+bvDg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36420 | N | N | 25 | SOFT LANDSCAPING |  | 124432 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 420 | LABOR- SUBCONTRACTOR
%R | 500505 | 6359 | 124435 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5WEEX5030 | Excavation | 8177 | 408 | 0 | 160 | 0 | 140 | 140 | 160 | 80 | 0 | 80 |  |  |  | 2014-06-25 08:00 | 2014-07-17 17:00 |  | 2014-04-27 08:00 | 2014-05-19 17:00 | 2014-04-27 08:00 | 2014-05-19 17:00 | 2014-04-27 08:00 | 2014-05-19 17:00 | 2014-06-25 08:00 | 2014-07-17 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36400 | N | N | 15 | WATER TANK ENCLOSURE |  | 124432 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 140 | LABOR - CIVIL
%R | 500506 | 6359 | 124435 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5WEEX5035 | Construction of Raft | 8165 | 408 | 0 | 200 | 0 | 2030 | 2030 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-07 08:00 | 2014-08-07 17:00 |  | 2014-05-08 08:00 | 2014-06-05 17:00 | 2014-05-08 08:00 | 2014-06-05 17:00 | 2014-05-08 08:00 | 2014-06-05 17:00 | 2014-07-07 08:00 | 2014-08-07 17:00 |  | PT_Normal |  |  |  |  | xxR1l9MvSleoPIkqQbctsA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36400 | N | N | 15 | WATER TANK ENCLOSURE |  | 124432 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 2030 | STEEL FIXERS SK
%R | 500507 | 6359 | 124435 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5WEEX5040 | Block works & Plastering | 8168 | 472 | 0 | 200 | 0 | 1110 | 1110 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-28 08:00 | 2014-08-28 17:00 |  | 2014-05-20 08:00 | 2014-06-17 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 | 2014-07-28 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | L0gsXLDZScmlX30eUTkNPw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36400 | N | N | 15 | WATER TANK ENCLOSURE |  | 124432 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1110 | BLOCK MASON SK
%R | 500508 | 6359 | 124435 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5WEEX5045 | Flooring & Painting | 8178 | 472 | 0 | 200 | 0 | 510 | 510 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-09-09 17:00 |  | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-08-12 08:00 | 2014-09-09 17:00 |  | PT_Normal |  |  |  |  | gpsWh60eT3G0e/G+2060uA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36400 | N | N | 15 | WATER TANK ENCLOSURE |  | 124432 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 510 | LABOR- SUBCONTRACTOR
%R | 500509 | 6359 | 124435 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5WEEX5050 | Installation of Steel Gate | 8178 | 472 | 40 | 160 | 0 | 140 | 140 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-21 17:00 |  | 2014-06-18 08:00 | 2014-07-10 17:00 | 2014-06-18 08:00 | 2014-07-10 17:00 | 2014-06-18 08:00 | 2014-07-10 17:00 | 2014-08-30 08:00 | 2014-09-21 17:00 |  | PT_Normal |  |  |  |  | svytQr+LQ3yuoQdYP8BONQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36400 | N | N | 15 | WATER TANK ENCLOSURE |  | 124432 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 140 | LABOR- SUBCONTRACTOR
%R | 500510 | 6359 | 124435 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 432 | 0 | 200 | 0 | 770 | 770 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-04 08:00 | 2014-10-02 17:00 |  | 2014-06-30 08:00 | 2014-07-28 17:00 | 2014-06-30 08:00 | 2014-07-28 17:00 | 2014-06-30 08:00 | 2014-07-28 17:00 | 2014-09-04 08:00 | 2014-10-02 17:00 |  | PT_Normal |  |  |  |  | uEOYWOnARsKVUzlvZnIgdA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36400 | N | N | 15 | WATER TANK ENCLOSURE |  | 124432 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 770 | LABOR- SUBCONTRACTOR
%R | 500511 | 6359 | 124435 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 432 | 24 | 200 | 0 | 478 | 478 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-07-12 08:00 | 2014-08-12 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | gamxbDTfSHWi4ISQ7P8qPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36400 | N | N | 15 | WATER TANK ENCLOSURE |  | 124432 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 239 | LABOR- SUBCONTRACTOR
%R | 500512 | 6359 | 124436 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5HDEX5090 | kerb works | 8173 | 568 | 0 | 160 | 0 | 890 | 890 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-24 08:00 | 2014-08-19 17:00 |  | 2014-05-03 08:00 | 2014-05-25 17:00 | 2014-05-03 08:00 | 2014-05-25 17:00 | 2014-05-03 08:00 | 2014-05-25 17:00 | 2014-07-24 08:00 | 2014-08-19 17:00 |  | PT_Normal |  |  |  |  | RTz3eq9NSBuYXx7a80xebw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36410 | N | N | 20 | HARD LANDSCAPING |  | 124432 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 890 | KERBSTONE MASON SK
%R | 500513 | 6359 | 124436 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5HDEX5095 | Cobble Stone Works | 8170 | 568 | 0 | 160 | 0 | 570 | 570 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-09 08:00 | 2014-08-31 17:00 |  | 2014-05-14 08:00 | 2014-06-05 17:00 | 2014-05-14 08:00 | 2014-06-05 17:00 | 2014-05-14 08:00 | 2014-06-05 17:00 | 2014-08-09 08:00 | 2014-08-31 17:00 |  | PT_Normal |  |  |  |  | ZYt7xHOvQwKSmF1EypWGtw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36410 | N | N | 20 | HARD LANDSCAPING |  | 124432 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 570 | TILE MASON SK
%R | 500514 | 6359 | 124436 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5HDEX5100 | Interlock works | 8174 | 568 | 0 | 160 | 0 | 510 | 510 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-24 08:00 | 2014-09-15 17:00 |  | 2014-05-29 08:00 | 2014-06-21 17:00 | 2014-05-29 08:00 | 2014-06-21 17:00 | 2014-05-29 08:00 | 2014-06-21 17:00 | 2014-08-24 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | z6RIrxTbRJCIh9ImDymytg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36410 | N | N | 20 | HARD LANDSCAPING |  | 124432 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 510 | INTERLOCK MASON SK
%R | 500515 | 6359 | 124439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARFF3300 | Block work | 8168 | 24 | 0 | 200 | 0 | 9175 | 9175 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-09 08:00 | 2014-05-07 17:00 |  | 2014-04-06 08:00 | 2014-05-04 17:00 | 2014-04-06 08:00 | 2014-05-04 17:00 | 2014-04-06 08:00 | 2014-05-04 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 |  | PT_Normal |  |  |  |  | 177APofTTKCZucwWJCJIoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36190 | N | N | 15 | FIRST FLOORS |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 9175 | BLOCK MASON SK
%R | 500516 | 6359 | 124439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARFF3305 | Plastering work | 8169 | 24 | 0 | 200 | 0 | 9399 | 9399 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-06 08:00 | 2014-06-03 17:00 |  | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-06 08:00 | 2014-06-03 17:00 |  | PT_Normal |  |  |  |  | VGCw+kl3R8+pk3eDU6OgOg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36190 | N | N | 15 | FIRST FLOORS |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 9399 | PLASTER MASON SK
%R | 500517 | 6359 | 124439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARFF3310 | Flooring screed | 8164 | 160 | 136 | 168 | 0 | 1352 | 1352 | 168 | 0 | 0 | 0 |  |  |  | 2014-06-03 08:00 | 2014-06-26 17:00 |  | 2014-05-11 08:00 | 2014-06-03 17:00 | 2014-05-11 08:00 | 2014-06-03 17:00 | 2014-05-11 08:00 | 2014-06-03 17:00 | 2014-06-03 08:00 | 2014-06-26 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36190 | N | N | 15 | FIRST FLOORS |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1352 | SCREED MASON SK
%R | 500518 | 6359 | 124439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARFF3315 | Wet area waterproofing | 8178 | 24 | 0 | 120 | 0 | 1716 | 1716 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-27 08:00 | 2014-06-12 17:00 |  | 2014-05-24 08:00 | 2014-06-09 17:00 | 2014-05-24 08:00 | 2014-06-09 17:00 | 2014-05-24 08:00 | 2014-06-09 17:00 | 2014-05-27 08:00 | 2014-06-12 17:00 |  | PT_Normal |  |  |  |  | KIIHBLbzQgaGV2/79WdSuw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36190 | N | N | 15 | FIRST FLOORS |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1716 | LABOR- SUBCONTRACTOR
%R | 500519 | 6359 | 124439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARFF3330 | Paint First coat | 8178 | 232 | 208 | 200 | 0 | 6570.3 | 6570.3 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-22 08:00 | 2014-07-20 17:00 |  | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 |  | PT_Normal |  |  |  |  | wXEuYgylTFyx6r8QL+SKig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36190 | N | N | 15 | FIRST FLOORS |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 6570.3 | LABOR- SUBCONTRACTOR
%R | 500520 | 6359 | 124439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARFF3320 | Ceramic Wall Tiling | 8170 | 24 | 0 | 200 | 0 | 1893.75 | 1893.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-07-03 17:00 |  | 2014-06-02 08:00 | 2014-06-30 17:00 | 2014-06-02 08:00 | 2014-06-30 17:00 | 2014-06-02 08:00 | 2014-06-30 17:00 | 2014-06-05 08:00 | 2014-07-03 17:00 |  | PT_Normal |  |  |  |  | mCLvfV1uRMmGvitPe45lgQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36190 | N | N | 15 | FIRST FLOORS |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1893.75 | TILE MASON SK
%R | 500521 | 6359 | 124439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARFF3325 | Porcelain Tile flooring | 8170 | 24 | 0 | 200 | 0 | 1675 | 1675 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-13 17:00 |  | 2014-06-11 08:00 | 2014-07-09 17:00 | 2014-06-11 08:00 | 2014-07-09 17:00 | 2014-06-11 08:00 | 2014-07-09 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 |  | PT_Normal |  |  |  |  | iUlItKvoQwCnQPsQo5z2Hg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36190 | N | N | 15 | FIRST FLOORS |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1675 | TILE MASON SK
%R | 500522 | 6359 | 124439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARFF3335 | Slate Tile Flooring & Skirting | 8170 | 176 | 152 | 120 | 0 | 1162.5 | 1162.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-24 08:00 | 2014-08-13 17:00 |  | 2014-06-29 08:00 | 2014-07-15 17:00 | 2014-06-29 08:00 | 2014-07-15 17:00 | 2014-06-29 08:00 | 2014-07-15 17:00 | 2014-07-24 08:00 | 2014-08-13 17:00 |  | PT_Normal |  |  |  |  | 9niuUe1UQI6h6QgJWfl/3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36190 | N | N | 15 | FIRST FLOORS |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1162.5 | TILE MASON SK
%R | 500523 | 6359 | 124439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARFF3350 | Granite - Stair case flooring & Skirting | 8171 | 112 | 88 | 160 | 0 | 1062.5 | 1062.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-19 08:00 | 2014-08-13 17:00 |  | 2014-07-02 08:00 | 2014-07-24 17:00 | 2014-07-02 08:00 | 2014-07-24 17:00 | 2014-07-02 08:00 | 2014-07-24 17:00 | 2014-07-19 08:00 | 2014-08-13 17:00 |  | PT_Normal |  |  |  |  | d5b2hnGkQEiG1m/CGboZBA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36190 | N | N | 15 | FIRST FLOORS |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1062.5 | GRANITE MASON SK
%R | 500524 | 6359 | 124439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARFF3345 | Fixing of Suspension systems | 8178 | 24 | 0 | 160 | 0 | 1487.5 | 1487.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-06 08:00 | 2014-07-28 17:00 |  | 2014-07-02 08:00 | 2014-07-24 17:00 | 2014-07-02 08:00 | 2014-07-24 17:00 | 2014-07-02 08:00 | 2014-07-24 17:00 | 2014-07-06 08:00 | 2014-07-28 17:00 |  | PT_Normal |  |  |  |  | YneQdNU7TkGiEyi7gCuNqQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36190 | N | N | 15 | FIRST FLOORS |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1487.5 | LABOR- SUBCONTRACTOR
%R | 500525 | 6359 | 124439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARFF3360 | Gypsum board false ceiling | 8178 | 24 | 0 | 200 | 0 | 1487.5 | 1487.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-17 08:00 | 2014-08-18 17:00 |  | 2014-07-14 08:00 | 2014-08-14 17:00 | 2014-07-14 08:00 | 2014-08-14 17:00 | 2014-07-14 08:00 | 2014-08-14 17:00 | 2014-07-17 08:00 | 2014-08-18 17:00 |  | PT_Normal |  |  |  |  | z7tYs7raSqqb7aS8cnyZlg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36190 | N | N | 15 | FIRST FLOORS |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 743.75 | LABOR- SUBCONTRACTOR
%R | 500526 | 6359 | 124439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARFF3365 | Wooden door | 8178 | 24 | 0 | 120 | 0 | 220 | 220 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-05 08:00 | 2014-08-21 17:00 |  | 2014-07-29 08:00 | 2014-08-18 17:00 | 2014-07-29 08:00 | 2014-08-18 17:00 | 2014-07-29 08:00 | 2014-08-18 17:00 | 2014-08-05 08:00 | 2014-08-21 17:00 |  | PT_Normal |  |  |  |  | VKiT5qUbRaWHySHPvY7STg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36190 | N | N | 15 | FIRST FLOORS |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 220 | LABOR- SUBCONTRACTOR
%R | 500527 | 6359 | 124439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARFF3370 | Aluminum Door | 8178 | 24 | 0 | 160 | 0 | 165 | 165 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-13 08:00 | 2014-09-04 17:00 |  | 2014-08-10 08:00 | 2014-09-01 17:00 | 2014-08-10 08:00 | 2014-09-01 17:00 | 2014-08-10 08:00 | 2014-09-01 17:00 | 2014-08-13 08:00 | 2014-09-04 17:00 |  | PT_Normal |  |  |  |  | vSAKN8QqRtyjzuJtiE+MEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36190 | N | N | 15 | FIRST FLOORS |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 165 | LABOR- SUBCONTRACTOR
%R | 500528 | 6359 | 124439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARFF3380 | Aluminum windows | 8178 | 128 | 104 | 160 | 0 | 338.25 | 338.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-04 08:00 | 2014-09-27 17:00 |  | 2014-08-17 08:00 | 2014-09-08 17:00 | 2014-08-17 08:00 | 2014-09-08 17:00 | 2014-08-17 08:00 | 2014-09-08 17:00 | 2014-09-04 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | Fgti9eooSUqMoqCbMf9tqg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36190 | N | N | 15 | FIRST FLOORS |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 338.25 | LABOR- SUBCONTRACTOR
%R | 500529 | 6359 | 124439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARFF3375 | Carpentry & Joinery Works | 8178 | 24 | 0 | 200 | 0 | 880 | 880 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-21 08:00 | 2014-09-18 17:00 |  | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-21 08:00 | 2014-09-18 17:00 |  | PT_Normal |  |  |  |  | PC5suabyRH28G2qQwdG89w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36190 | N | N | 15 | FIRST FLOORS |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 880 | LABOR- SUBCONTRACTOR
%R | 500530 | 6359 | 124439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARFF3390 | Installation of Granite Counter Top | 8171 | 40 | 16 | 160 | 0 | 137.5 | 137.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-07 08:00 | 2014-09-29 17:00 |  | 2014-09-01 08:00 | 2014-09-23 17:00 | 2014-09-01 08:00 | 2014-09-23 17:00 | 2014-09-01 08:00 | 2014-09-23 17:00 | 2014-09-07 08:00 | 2014-09-29 17:00 |  | PT_Normal |  |  |  |  | SSKw50f9SO6CaH6fRmSf9g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36190 | N | N | 15 | FIRST FLOORS |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 137.5 | GRANITE MASON SK
%R | 500531 | 6359 | 124439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARFF3385 | Handrail & Balustrade | 8178 | 24 | 0 | 160 | 0 | 218.75 | 218.75 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-04 08:00 | 2014-09-27 17:00 |  | 2014-09-01 08:00 | 2014-09-23 17:00 | 2014-09-01 08:00 | 2014-09-23 17:00 | 2014-09-01 08:00 | 2014-09-23 17:00 | 2014-09-04 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | hAGSSjTgTCiBKpsNWg9yiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36190 | N | N | 15 | FIRST FLOORS |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 218.75 | LABOR- SUBCONTRACTOR
%R | 500532 | 6359 | 124439 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARFF3395 | Final Painting | 8178 | 24 | 0 | 200 | 0 | 6570.3 | 6570.3 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-09-13 08:00 | 2014-10-13 17:00 | 2014-09-13 08:00 | 2014-10-13 17:00 | 2014-09-13 08:00 | 2014-10-13 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | kPp7+SP4S2S94h//yedXug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36190 | N | N | 15 | FIRST FLOORS |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 3285.15 | LABOR- SUBCONTRACTOR
%R | 500533 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3000 | Block work | 8168 | 392 | 0 | 200 | 0 | 11578.5 | 11578.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-22 08:00 | 2014-05-20 17:00 |  | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-04-22 08:00 | 2014-05-20 17:00 |  | PT_Normal |  |  |  |  | qn70zUGGRQ2iwNpTUG1q6g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 5789.25 | BLOCK MASON SK
%R | 500534 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3005 | Plastering work | 8169 | 392 | 0 | 200 | 0 | 14187.5 | 14187.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-14 08:00 | 2014-06-11 17:00 |  | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 |  | PT_Normal |  |  |  |  | 8uj/COaJSlCL20bLkOehTQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 14187.5 | PLASTER MASON SK
%R | 500535 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3010 | Flooring screed | 8164 | 456 | 64 | 168 | 0 | 2713.25 | 2713.25 | 168 | 0 | 0 | 0 |  |  |  | 2014-06-01 08:00 | 2014-06-24 17:00 |  | 2014-03-26 08:00 | 2014-04-19 17:00 | 2014-03-26 08:00 | 2014-04-19 17:00 | 2014-03-26 08:00 | 2014-04-19 17:00 | 2014-06-01 08:00 | 2014-06-24 17:00 |  | PT_Normal |  |  |  |  | Pfwu4nfCTZO9wQaJzUWKFA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 2713.25 | SCREED MASON SK
%R | 500536 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 392 | 0 | 120 | 0 | 528 | 528 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-01 08:00 | 2014-06-17 17:00 |  | 2014-04-05 08:00 | 2014-04-21 17:00 | 2014-04-05 08:00 | 2014-04-21 17:00 | 2014-04-05 08:00 | 2014-04-21 17:00 | 2014-06-01 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | qzKhW/GMT2Or/B3vkhP5og |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 528 | LABOR- SUBCONTRACTOR
%R | 500537 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3030 | Paint First coat | 8178 | 504 | 0 | 200 | 0 | 7419.5 | 7419.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-16 08:00 | 2014-07-14 17:00 |  | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 |  | PT_Normal |  |  |  |  | XyJ3Is2qRp2z/tF1AaQ12A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 7419.5 | LABOR- SUBCONTRACTOR
%R | 500538 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3020 | Ceramic Wall Tiling | 8170 | 392 | 0 | 200 | 0 | 4418.75 | 4418.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-07 08:00 | 2014-07-05 17:00 |  | 2014-04-10 08:00 | 2014-05-08 17:00 | 2014-04-10 08:00 | 2014-05-08 17:00 | 2014-04-10 08:00 | 2014-05-08 17:00 | 2014-06-07 08:00 | 2014-07-05 17:00 |  | PT_Normal |  |  |  |  | DU4l+x4iSy6VE793k60aQw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 4418.75 | TILE MASON SK
%R | 500539 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3025 | Porcelain Tile flooring | 8170 | 392 | 0 | 200 | 0 | 2397.25 | 2397.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-07-10 17:00 |  | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 |  | PT_Normal |  |  |  |  | 1yCgDN4mTCKDPzPrJhK5Ig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 2397.25 | TILE MASON SK
%R | 500540 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3040 | Cobble Tile flooring | 8170 | 456 | 0 | 120 | 0 | 875 | 875 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-19 08:00 | 2014-08-07 17:00 |  | 2014-05-13 08:00 | 2014-05-29 17:00 | 2014-05-13 08:00 | 2014-05-29 17:00 | 2014-05-13 08:00 | 2014-05-29 17:00 | 2014-07-19 08:00 | 2014-08-07 17:00 |  | PT_Normal |  |  |  |  | pJsQIVDHRlW1sEnWNNOEdw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 875 | TILE MASON SK
%R | 500541 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 472 | 16 | 120 | 0 | 1162.5 | 1162.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-14 08:00 | 2014-07-30 17:00 |  | 2014-05-06 08:00 | 2014-05-22 17:00 | 2014-05-06 08:00 | 2014-05-22 17:00 | 2014-05-06 08:00 | 2014-05-22 17:00 | 2014-07-14 08:00 | 2014-07-30 17:00 |  | PT_Normal |  |  |  |  | L8SkyMFWR8SzqLEy1qTvGg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1162.5 | TILE MASON SK
%R | 500542 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 456 | 0 | 160 | 0 | 1062.5 | 1062.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-27 08:00 | 2014-08-21 17:00 |  | 2014-05-21 08:00 | 2014-06-12 17:00 | 2014-05-21 08:00 | 2014-06-12 17:00 | 2014-05-21 08:00 | 2014-06-12 17:00 | 2014-07-27 08:00 | 2014-08-21 17:00 |  | PT_Normal |  |  |  |  | x+UMC6d7Ti2JqyppTeY0Gw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1062.5 | GRANITE MASON SK
%R | 500543 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3045 | Fixing of Suspension systems | 8178 | 392 | 0 | 160 | 0 | 1650 | 1650 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-30 08:00 | 2014-07-22 17:00 |  | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-06-30 08:00 | 2014-07-22 17:00 |  | PT_Normal |  |  |  |  | uJ/idgY/RPOrK6t9qiePEw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1650 | LABOR- SUBCONTRACTOR
%R | 500544 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3055 | Aluminum tile false ceiling | 8178 | 416 | 24 | 200 | 0 | 162.5 | 162.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-12 08:00 | 2014-08-12 17:00 |  | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 |  | PT_Normal |  |  |  |  | nSRRXCoFSpOKl2yq22lo0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 162.5 | LABOR- SUBCONTRACTOR
%R | 500545 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3060 | Gypsum board false ceiling | 8178 | 392 | 0 | 200 | 0 | 1520.5 | 1520.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-12 08:00 | 2014-08-12 17:00 |  | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 |  | PT_Normal |  |  |  |  | N6PXhZqfSTaZ/FrRz3ZTAA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1520.5 | LABOR- SUBCONTRACTOR
%R | 500546 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3065 | Wooden door & PVC Door | 8178 | 456 | 0 | 120 | 0 | 825 | 825 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-13 08:00 | 2014-08-30 17:00 |  | 2014-06-04 08:00 | 2014-06-21 17:00 | 2014-06-04 08:00 | 2014-06-21 17:00 | 2014-06-04 08:00 | 2014-06-21 17:00 | 2014-08-13 08:00 | 2014-08-30 17:00 |  | PT_Normal |  |  |  |  | K80B4MxSRu6I+EOdVgzdLQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 825 | LABOR- SUBCONTRACTOR
%R | 500547 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3070 | Aluminum doors | 8178 | 456 | 0 | 120 | 0 | 110 | 110 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-19 08:00 | 2014-09-04 17:00 |  | 2014-06-10 08:00 | 2014-06-26 17:00 | 2014-06-10 08:00 | 2014-06-26 17:00 | 2014-06-10 08:00 | 2014-06-26 17:00 | 2014-08-19 08:00 | 2014-09-04 17:00 |  | PT_Normal |  |  |  |  | 99Yh6RoURt2sVprY5GBTUQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 110 | LABOR- SUBCONTRACTOR
%R | 500548 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3080 | Aluminum windows | 8178 | 536 | 40 | 160 | 0 | 323.5 | 323.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-07 08:00 | 2014-09-29 17:00 |  | 2014-06-17 08:00 | 2014-07-09 17:00 | 2014-06-17 08:00 | 2014-07-09 17:00 | 2014-06-17 08:00 | 2014-07-09 17:00 | 2014-09-07 08:00 | 2014-09-29 17:00 |  | PT_Normal |  |  |  |  | zNe1gRN9SX+YQCjEtdLg7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 323.5 | LABOR- SUBCONTRACTOR
%R | 500549 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3075 | Carpentry & Joinery Works | 8178 | 456 | 0 | 160 | 0 | 660 | 660 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-25 08:00 | 2014-09-16 17:00 |  | 2014-06-16 08:00 | 2014-07-08 17:00 | 2014-06-16 08:00 | 2014-07-08 17:00 | 2014-06-16 08:00 | 2014-07-08 17:00 | 2014-08-25 08:00 | 2014-09-16 17:00 |  | PT_Normal |  |  |  |  | 1uheY805S2ex7R+Oh9zETw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 660 | LABOR- SUBCONTRACTOR
%R | 500550 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3090 | Installation of Granite Counter Top | 8171 | 456 | 0 | 120 | 0 | 302.5 | 302.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-07 08:00 | 2014-09-23 17:00 |  | 2014-06-29 08:00 | 2014-07-15 17:00 | 2014-06-29 08:00 | 2014-07-15 17:00 | 2014-06-29 08:00 | 2014-07-15 17:00 | 2014-09-07 08:00 | 2014-09-23 17:00 |  | PT_Normal |  |  |  |  | 9L4c+KmaQeG2WfqsW1B5Sw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 302.5 | GRANITE MASON SK
%R | 500551 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3085 | S.S.Balustrade | 8178 | 496 | 40 | 160 | 0 | 218.75 | 218.75 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-08 08:00 | 2014-09-30 17:00 |  | 2014-06-24 08:00 | 2014-07-16 17:00 | 2014-06-24 08:00 | 2014-07-16 17:00 | 2014-06-24 08:00 | 2014-07-16 17:00 | 2014-09-08 08:00 | 2014-09-30 17:00 |  | PT_Normal |  |  |  |  | 7wGpWM7MTWKMJrUFbI7+iw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 218.75 | LABOR- SUBCONTRACTOR
%R | 500552 | 6359 | 124440 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARGF3095 | Final Painting | 8178 | 456 | 0 | 200 | 0 | 7419.5 | 7419.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-07-08 08:00 | 2014-08-09 17:00 | 2014-07-08 08:00 | 2014-08-09 17:00 | 2014-07-08 08:00 | 2014-08-09 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | pwgAfEFcQKSa2LHBqqNK/A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36180 | N | N | 10 | GROUND FLOOR |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 3709.75 | LABOR- SUBCONTRACTOR
%R | 500553 | 6359 | 124441 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARRF3605 | Plastering work | 8169 | 624 | 0 | 160 | 0 | 4791 | 4791 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-06 08:00 | 2014-08-28 17:00 |  | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-08-06 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | NvaMHS7dSCePQVZ2DetGAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36200 | N | N | 20 | ROOF |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 4791 | PLASTER MASON SK
%R | 500554 | 6359 | 124441 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARRF3610 | Flooring screed | 8164 | 624 | 0 | 120 | 0 | 192.5 | 192.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-24 08:00 | 2014-09-09 17:00 |  | 2014-05-21 08:00 | 2014-06-07 17:00 | 2014-05-21 08:00 | 2014-06-07 17:00 | 2014-05-21 08:00 | 2014-06-07 17:00 | 2014-08-24 08:00 | 2014-09-09 17:00 |  | PT_Normal |  |  |  |  | Q5YVmw7+SxOeoNVrexh09Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36200 | N | N | 20 | ROOF |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 192.5 | SCREED MASON SK
%R | 500555 | 6359 | 124441 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARRF3695 | Painting -Storage area | 8178 | 624 | 0 | 160 | 0 | 2050 | 2050 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-04 08:00 | 2014-09-27 17:00 |  | 2014-06-02 08:00 | 2014-06-24 17:00 | 2014-06-02 08:00 | 2014-06-24 17:00 | 2014-06-02 08:00 | 2014-06-24 17:00 | 2014-09-04 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | X4jw2gyDSoCAoBMJEowxQw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36200 | N | N | 20 | ROOF |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 2050 | LABOR- SUBCONTRACTOR
%R | 500556 | 6359 | 124441 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARRF3620 | Epoxy Painting -Storage area | 8178 | 624 | 0 | 120 | 0 | 59.5 | 59.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-22 08:00 | 2014-10-08 17:00 |  | 2014-06-19 08:00 | 2014-07-06 17:00 | 2014-06-19 08:00 | 2014-07-06 17:00 | 2014-06-19 08:00 | 2014-07-06 17:00 | 2014-09-22 08:00 | 2014-10-08 17:00 |  | PT_Normal |  |  |  |  | ulE4ejwvQleYw3MhigdQWA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36200 | N | N | 20 | ROOF |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 59.5 | LABOR- SUBCONTRACTOR
%R | 500557 | 6359 | 124441 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARRF3600 | Block work | 8168 | 624 | 0 | 160 | 0 | 872.25 | 872.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-22 08:00 | 2014-08-17 17:00 |  | 2014-04-22 08:00 | 2014-05-14 17:00 | 2014-04-22 08:00 | 2014-05-14 17:00 | 2014-04-22 08:00 | 2014-05-14 17:00 | 2014-07-22 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | 1kSMH4OVRdWbaUTtL/S2Mw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36200 | N | N | 20 | ROOF |  | 124438 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 872.25 | BLOCK MASON SK
%R | 500558 | 6359 | 124443 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARRF3630 | Leveling Screed for Waterproofing | 8164 | 624 | 0 | 200 | 0 | 887.5 | 887.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-05 08:00 | 2014-09-02 17:00 |  | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-08-05 08:00 | 2014-09-02 17:00 |  | PT_Normal |  |  |  |  | YcpVCHl+SSeZLVlq8EOZ3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36220 | N | N | 10 | ROOF |  | 124442 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 887.5 | SCREED MASON SK
%R | 500559 | 6359 | 124443 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARRF3635 | Laying of Waterproofing Membrane | 8178 | 624 | 0 | 200 | 0 | 1232 | 1232 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-09 08:00 | 2014-09-06 17:00 |  | 2014-05-06 08:00 | 2014-06-03 17:00 | 2014-05-06 08:00 | 2014-06-03 17:00 | 2014-05-06 08:00 | 2014-06-03 17:00 | 2014-08-09 08:00 | 2014-09-06 17:00 |  | PT_Normal |  |  |  |  | M+vR8gXdTcq+ytLOgXG4qA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36220 | N | N | 10 | ROOF |  | 124442 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1232 | LABOR- SUBCONTRACTOR
%R | 500560 | 6359 | 124443 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARRF3640 | Installation of Insulation & Protection | 8178 | 624 | 0 | 200 | 0 | 1562 | 1562 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-13 08:00 | 2014-09-10 17:00 |  | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-08-13 08:00 | 2014-09-10 17:00 |  | PT_Normal |  |  |  |  | HDMUkM0kTD6SyYhYkPxkTQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36220 | N | N | 10 | ROOF |  | 124442 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1562 | LABOR- SUBCONTRACTOR
%R | 500561 | 6359 | 124443 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 624 | 0 | 200 | 0 | 781 | 781 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | m6dttc/BQkaL4T5HgwYGlg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36220 | N | N | 10 | ROOF |  | 124442 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 781 | TILE MASON SK
%R | 500562 | 6359 | 124443 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 624 | 0 | 160 | 0 | 770 | 770 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-10-02 17:00 |  | 2014-06-08 08:00 | 2014-06-30 17:00 | 2014-06-08 08:00 | 2014-06-30 17:00 | 2014-06-08 08:00 | 2014-06-30 17:00 | 2014-09-10 08:00 | 2014-10-02 17:00 |  | PT_Normal |  |  |  |  | Ii5uVblHSletO9kK+NEQng |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36220 | N | N | 10 | ROOF |  | 124442 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 770 | LABOR- SUBCONTRACTOR
%R | 500563 | 6359 | 124443 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 624 | 0 | 200 | 0 | 1074.5 | 1074.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-26 08:00 | 2014-09-23 17:00 |  | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-08-26 08:00 | 2014-09-23 17:00 |  | PT_Normal |  |  |  |  | eoFpC3mkRVC+jJNDyQQEoA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36220 | N | N | 10 | ROOF |  | 124442 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1074.5 | LABOR- SUBCONTRACTOR
%R | 500564 | 6359 | 124443 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ARRF3660 | Installation of Access Ladder | 8178 | 624 | 600 | 120 | 0 | 440 | 440 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-28 08:00 | 2014-10-16 17:00 |  | 2014-06-25 08:00 | 2014-07-12 17:00 | 2014-06-25 08:00 | 2014-07-12 17:00 | 2014-06-25 08:00 | 2014-07-12 17:00 | 2014-09-28 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | XA41wJRkRZiw1yeGCcmSFg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36220 | N | N | 10 | ROOF |  | 124442 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 440 | LABOR- SUBCONTRACTOR
%R | 500565 | 6359 | 124444 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5AREL3665 | External Plastering | 8169 | 608 | 0 | 200 | 0 | 15250 | 15250 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-05-18 08:00 | 2014-06-15 17:00 | 2014-05-18 08:00 | 2014-06-15 17:00 | 2014-05-18 08:00 | 2014-06-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | QscvOd2GS/mzpQIPYRAGRQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36230 | N | N | 15 | ELEVATION |  | 124442 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 15250 | PLASTER MASON SK
%R | 500566 | 6359 | 124444 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5AREL3670 | External stone cladding works | 8170 | 608 | 0 | 160 | 0 | 1170 | 1170 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-04 08:00 | 2014-09-27 17:00 |  | 2014-06-04 08:00 | 2014-06-26 17:00 | 2014-06-04 08:00 | 2014-06-26 17:00 | 2014-06-04 08:00 | 2014-06-26 17:00 | 2014-09-04 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | /YPlRtzUT6CffRsYjfe5tQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36230 | N | N | 15 | ELEVATION |  | 124442 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1170 | TILE MASON SK
%R | 500567 | 6359 | 124444 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5AREL3675 | GRC works | 8178 | 608 | 0 | 160 | 0 | 550 | 550 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-10-02 17:00 |  | 2014-06-10 08:00 | 2014-07-02 17:00 | 2014-06-10 08:00 | 2014-07-02 17:00 | 2014-06-10 08:00 | 2014-07-02 17:00 | 2014-09-10 08:00 | 2014-10-02 17:00 |  | PT_Normal |  |  |  |  | oaOdbfwPSXi8BdEbVx3u0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36230 | N | N | 15 | ELEVATION |  | 124442 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 550 | LABOR- SUBCONTRACTOR
%R | 500568 | 6359 | 124444 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5AREL3680 | External Painting | 8178 | 608 | 40 | 160 | 0 | 5280 | 5280 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-22 08:00 | 2014-10-16 17:00 |  | 2014-06-22 08:00 | 2014-07-14 17:00 | 2014-06-22 08:00 | 2014-07-14 17:00 | 2014-06-22 08:00 | 2014-07-14 17:00 | 2014-09-22 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | kSGUM2XcQQeOedpaI2omCw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36230 | N | N | 15 | ELEVATION |  | 124442 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 5280 | LABOR- SUBCONTRACTOR
%R | 500569 | 6359 | 124445 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 24 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-10-14 08:00 | 2014-11-11 17:00 | 2014-10-14 08:00 | 2014-11-11 17:00 | 2014-10-14 08:00 | 2014-11-11 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | NcPOJWz+RdqHSIY4cntkNQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36430 | N | N | 30 | TESTING AND COMMISSIONING |  | 124418 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 500570 | 6359 | 124445 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 24 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-10-14 08:00 | 2014-11-11 17:00 | 2014-10-14 08:00 | 2014-11-11 17:00 | 2014-10-14 08:00 | 2014-11-11 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | 09XCXSu6QDWrekfvDnHISw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36430 | N | N | 30 | TESTING AND COMMISSIONING |  | 124418 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 500571 | 6359 | 124445 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 24 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-10-14 08:00 | 2014-11-11 17:00 | 2014-10-14 08:00 | 2014-11-11 17:00 | 2014-10-14 08:00 | 2014-11-11 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | 3kvAPnAMSE+jHhThTr+h3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36430 | N | N | 30 | TESTING AND COMMISSIONING |  | 124418 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 500572 | 6359 | 124448 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STFF2020 | Column-Rebar & Formwork | 8166 | 88 | 0 | 200 | 0 | 4272 | 4272 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-15 08:00 | 2014-03-15 17:00 |  | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 |  | PT_Normal |  |  |  |  | tyj9aCI+RX6W0g72K4UQlw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36140 | N | N | 15 | FIRST FLOORS |  | 124447 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 2136 | CARPENTERS SK
%R | 500573 | 6359 | 124448 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STFF2025 | Column-Concrete | 8167 | 88 | 0 | 184 | 0 | 427 | 427 | 184 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-22 17:00 |  | 2014-02-10 08:00 | 2014-03-09 17:00 | 2014-02-10 08:00 | 2014-03-09 17:00 | 2014-02-10 08:00 | 2014-03-09 17:00 | 2014-02-24 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | WNkj5dF7TpuHYaajkbgfkg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36140 | N | N | 15 | FIRST FLOORS |  | 124447 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 427 | CONCRETE MASON SK
%R | 500574 | 6359 | 124448 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 88 | 0 | 200 | 0 | 23850.75 | 23850.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-27 08:00 | 2014-03-27 17:00 |  | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 |  | PT_Normal |  |  |  |  | MZOe6IZyQ3CyO3MbWKVXBw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36140 | N | N | 15 | FIRST FLOORS |  | 124447 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 11925.375 | STEEL FIXERS SK
%R | 500575 | 6359 | 124448 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 88 | 0 | 112 | 0 | 1610 | 1610 | 112 | 0 | 0 | 0 |  |  |  | 2014-03-16 08:00 | 2014-03-31 17:00 |  | 2014-03-03 08:00 | 2014-03-18 17:00 | 2014-03-03 08:00 | 2014-03-18 17:00 | 2014-03-03 08:00 | 2014-03-18 17:00 | 2014-03-16 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | 4EGHcykOQcirkMmWg+4qXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36140 | N | N | 15 | FIRST FLOORS |  | 124447 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1610 | CONCRETE MASON SK
%R | 500576 | 6359 | 124449 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STRF2040 | Column-Rebar & Formwork | 8166 | 160 | 0 | 144 | 0 | 1470 | 1470 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-01 08:00 | 2014-04-21 17:00 |  | 2014-03-09 08:00 | 2014-03-29 17:00 | 2014-03-09 08:00 | 2014-03-29 17:00 | 2014-03-09 08:00 | 2014-03-29 17:00 | 2014-04-01 08:00 | 2014-04-21 17:00 |  | PT_Normal |  |  |  |  | SpXo4BIdSkyxPTefxjR4Rg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36150 | N | N | 20 | ROOF |  | 124447 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1470 | CARPENTERS SK
%R | 500577 | 6359 | 124449 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STRF2045 | Column-Concrete | 8167 | 200 | 0 | 136 | 0 | 101.5 | 101.5 | 136 | 0 | 0 | 0 |  |  |  | 2014-04-10 08:00 | 2014-04-29 17:00 |  | 2014-03-12 08:00 | 2014-03-31 17:00 | 2014-03-12 08:00 | 2014-03-31 17:00 | 2014-03-12 08:00 | 2014-03-31 17:00 | 2014-04-10 08:00 | 2014-04-29 17:00 |  | PT_Normal |  |  |  |  | mNwpx3VIT0u7Rt1zfUCbjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36150 | N | N | 20 | ROOF |  | 124447 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 101.5 | CONCRETE MASON SK
%R | 500578 | 6359 | 124449 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STRF2050 | Slab-Rebar & Formwork - Head Room | 8165 | 200 | 0 | 160 | 0 | 4303.25 | 4303.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-13 08:00 | 2014-05-05 17:00 |  | 2014-03-15 08:00 | 2014-04-06 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | 4QPM5gOBQI6hEMwd5iuzYA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36150 | N | N | 20 | ROOF |  | 124447 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 4303.25 | STEEL FIXERS SK
%R | 500579 | 6359 | 124449 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STRF2055 | Slab-Concrete-Head room | 8167 | 200 | 0 | 104 | 0 | 350 | 350 | 104 | 0 | 0 | 0 |  |  |  | 2014-04-27 08:00 | 2014-05-11 17:00 |  | 2014-03-29 08:00 | 2014-04-12 17:00 | 2014-03-29 08:00 | 2014-04-12 17:00 | 2014-03-29 08:00 | 2014-04-12 17:00 | 2014-04-27 08:00 | 2014-05-11 17:00 |  | PT_Normal |  |  |  |  | 2kEdEXobRliKyzZwO9RRfA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36150 | N | N | 20 | ROOF |  | 124447 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 350 | CONCRETE MASON SK
%R | 500580 | 6359 | 124449 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STRF2060 | Construction of Parapets | 8168 | 584 | 0 | 200 | 0 | 1468.75 | 1468.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-27 17:00 |  | 2014-04-05 08:00 | 2014-05-03 17:00 | 2014-04-05 08:00 | 2014-05-03 17:00 | 2014-04-05 08:00 | 2014-05-03 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | guAWYa9bTSK48aDqJ13oJw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36150 | N | N | 20 | ROOF |  | 124447 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1468.75 | BLOCK MASON SK
%R | 500581 | 6359 | 124449 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STRF2065 | Construction of up stands/Plinth | 8165 | 624 | 0 | 200 | 0 | 687.75 | 687.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-21 08:00 | 2014-08-21 17:00 |  | 2014-04-21 08:00 | 2014-05-19 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 | 2014-07-21 08:00 | 2014-08-21 17:00 |  | PT_Normal |  |  |  |  | Us27K7GER22PC7Yo2PZv/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36150 | N | N | 20 | ROOF |  | 124447 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 687.75 | STEEL FIXERS SK
%R | 500582 | 6359 | 124450 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STGF2000 | Column-Rebar & Formwork | 8165 | 88 | 0 | 200 | 0 | 6230 | 6230 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-02 08:00 | 2014-01-30 17:00 |  | 2013-12-21 08:00 | 2014-01-18 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 |  | PT_Normal |  |  |  |  | CC/eZ0tHTKKE07ic//DHzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36130 | N | N | 10 | GROUND FLOOR |  | 124447 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 6230 | STEEL FIXERS SK
%R | 500583 | 6359 | 124450 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STGF2005 | Column-Concrete | 8167 | 88 | 0 | 184 | 0 | 486.5 | 486.5 | 184 | 0 | 0 | 0 |  |  |  | 2014-01-12 08:00 | 2014-02-06 17:00 |  | 2013-12-30 08:00 | 2014-01-25 17:00 | 2013-12-30 08:00 | 2014-01-25 17:00 | 2013-12-30 08:00 | 2014-01-25 17:00 | 2014-01-12 08:00 | 2014-02-06 17:00 |  | PT_Normal |  |  |  |  | zX7WtsPkSwSUKTZybwNbJw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36130 | N | N | 10 | GROUND FLOOR |  | 124447 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 486.5 | CONCRETE MASON SK
%R | 500584 | 6359 | 124450 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 88 | 0 | 200 | 0 | 23402.75 | 23402.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-26 08:00 | 2014-02-24 17:00 |  | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 |  | PT_Normal |  |  |  |  | FhK7Sa9MQYmOtyDtMFYLVQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36130 | N | N | 10 | GROUND FLOOR |  | 124447 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 23402.75 | STEEL FIXERS SK
%R | 500585 | 6359 | 124450 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 88 | 0 | 112 | 0 | 1820 | 1820 | 112 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-02-27 17:00 |  | 2014-01-29 08:00 | 2014-02-15 17:00 | 2014-01-29 08:00 | 2014-02-15 17:00 | 2014-01-29 08:00 | 2014-02-15 17:00 | 2014-02-12 08:00 | 2014-02-27 17:00 |  | PT_Normal |  |  |  |  | Mawzh5giSR+Vk4khwlNNUg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36130 | N | N | 10 | GROUND FLOOR |  | 124447 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1820 | CONCRETE MASON SK
%R | 500586 | 6359 | 124452 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STUG1000 | Footing Excavation | 8177 | 88 | 0 | 200 | 0 | 1791 | 1791 | 200 | 843 | 0 | 843 |  |  |  | 2013-08-25 08:00 | 2013-09-22 17:00 |  | 2013-08-08 08:00 | 2013-09-09 17:00 | 2013-08-08 08:00 | 2013-09-09 17:00 | 2013-08-08 08:00 | 2013-09-09 17:00 | 2013-08-25 08:00 | 2013-09-22 17:00 |  | PT_Normal |  |  |  |  | h9d6VlBLRE6B3ujlfueSGA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36110 | N | N | 10 | UPTO GRADE SLAB |  | 124451 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 895.5 | LABOR - CIVIL
%R | 500587 | 6359 | 124452 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STUG1005 | Footing Antitermite | 8178 | 88 | 0 | 184 | 0 | 2326.5 | 2326.5 | 184 | 0 | 0 | 0 |  |  |  | 2013-09-05 08:00 | 2013-10-01 17:00 |  | 2013-08-24 08:00 | 2013-09-18 17:00 | 2013-08-24 08:00 | 2013-09-18 17:00 | 2013-08-24 08:00 | 2013-09-18 17:00 | 2013-09-05 08:00 | 2013-10-01 17:00 |  | PT_Normal |  |  |  |  | akNW9QnpRAC1XZF/Xh5aLQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36110 | N | N | 10 | UPTO GRADE SLAB |  | 124451 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 2326.5 | LABOR- SUBCONTRACTOR
%R | 500588 | 6359 | 124452 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STUG1010 | Footing Blinding | 8163 | 88 | 0 | 184 | 0 | 1309 | 1309 | 184 | 0 | 0 | 0 |  |  |  | 2013-09-10 08:00 | 2013-10-06 17:00 |  | 2013-08-28 08:00 | 2013-09-23 17:00 | 2013-08-28 08:00 | 2013-09-23 17:00 | 2013-08-28 08:00 | 2013-09-23 17:00 | 2013-09-10 08:00 | 2013-10-06 17:00 |  | PT_Normal |  |  |  |  | jype2wwCQKKtZjuMNVJHfQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36110 | N | N | 10 | UPTO GRADE SLAB |  | 124451 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 1309 | BLINDING MASON SK
%R | 500589 | 6359 | 124452 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STUG1015 | Footing Waterproofing & Screed | 8164 | 88 | 0 | 200 | 0 | 1030.25 | 1030.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-16 08:00 | 2013-10-14 17:00 |  | 2013-09-03 08:00 | 2013-10-01 17:00 | 2013-09-03 08:00 | 2013-10-01 17:00 | 2013-09-03 08:00 | 2013-10-01 17:00 | 2013-09-16 08:00 | 2013-10-14 17:00 |  | PT_Normal |  |  |  |  | DsB90iJLQyGXot9HDm1S3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36110 | N | N | 10 | UPTO GRADE SLAB |  | 124451 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1030.25 | SCREED MASON SK
%R | 500590 | 6359 | 124452 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STUG1020 | Construction of foundations | 8165 | 88 | 0 | 160 | 0 | 9962.75 | 9962.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-10-01 08:00 | 2013-10-26 17:00 |  | 2013-09-18 08:00 | 2013-10-10 17:00 | 2013-09-18 08:00 | 2013-10-10 17:00 | 2013-09-18 08:00 | 2013-10-10 17:00 | 2013-10-01 08:00 | 2013-10-26 17:00 |  | PT_Normal |  |  |  |  | KuKVV9GTTnqWTd51EnQeiA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36110 | N | N | 10 | UPTO GRADE SLAB |  | 124451 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 9962.75 | STEEL FIXERS SK
%R | 500591 | 6359 | 124452 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STUG1025 | Construction of neck of columns | 8165 | 88 | 0 | 200 | 0 | 2430.75 | 2430.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2013-11-10 17:00 |  | 2013-09-28 08:00 | 2013-10-28 17:00 | 2013-09-28 08:00 | 2013-10-28 17:00 | 2013-09-28 08:00 | 2013-10-28 17:00 | 2013-10-10 08:00 | 2013-11-10 17:00 |  | PT_Normal |  |  |  |  | 6m/N3qOYQMW42+rUTX9zjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36110 | N | N | 10 | UPTO GRADE SLAB |  | 124451 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 1215.375 | STEEL FIXERS SK
%R | 500592 | 6359 | 124452 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STUG1030 | Waterproofing Footing & Neck Column | 8178 | 88 | 0 | 200 | 0 | 670 | 670 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-22 08:00 | 2013-11-19 17:00 |  | 2013-10-07 08:00 | 2013-11-06 17:00 | 2013-10-07 08:00 | 2013-11-06 17:00 | 2013-10-07 08:00 | 2013-11-06 17:00 | 2013-10-22 08:00 | 2013-11-19 17:00 |  | PT_Normal |  |  |  |  | SlzR+IiVTke6AxlGY+TyPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36110 | N | N | 10 | UPTO GRADE SLAB |  | 124451 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 670 | LABOR- SUBCONTRACTOR
%R | 500593 | 6359 | 124452 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 88 | 0 | 200 | 0 | 1520 | 1520 | 200 | 1100 | 0 | 1100 |  |  |  | 2013-11-03 08:00 | 2013-12-01 17:00 |  | 2013-10-21 08:00 | 2013-11-18 17:00 | 2013-10-21 08:00 | 2013-11-18 17:00 | 2013-10-21 08:00 | 2013-11-18 17:00 | 2013-11-03 08:00 | 2013-12-01 17:00 |  | PT_Normal |  |  |  |  | ryGkajWBSj6truRGT4Av4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36110 | N | N | 10 | UPTO GRADE SLAB |  | 124451 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1520 | LABOR - CIVIL
%R | 500594 | 6359 | 124452 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STUG1040 | Construction of Grade Beams | 8163 | 88 | 0 | 200 | 0 | 10120.75 | 10120.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-19 08:00 | 2013-12-17 17:00 |  | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-11-19 08:00 | 2013-12-17 17:00 |  | PT_Normal |  |  |  |  | qW1TNilHQk6mTLT4eMU5Qw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36110 | N | N | 10 | UPTO GRADE SLAB |  | 124451 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 10120.75 | BLINDING MASON SK
%R | 500595 | 6359 | 124452 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ5STUG1045 | Construction of slab on grade | 8163 | 88 | 0 | 200 | 0 | 6924.5 | 6924.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-16 08:00 | 2014-01-14 17:00 |  | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-16 08:00 | 2014-01-14 17:00 |  | PT_Normal |  |  |  |  | VJ8PWD2jS4y50OS2sUHOgQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36110 | N | N | 10 | UPTO GRADE SLAB |  | 124451 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 6924.5 | BLINDING MASON SK
%R | 500596 | 6359 | 124456 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STUG1000 | Footing Excavation | 8177 | 88 | 0 | 200 | 0 | 1433 | 1433 | 200 | 675 | 0 | 675 |  |  |  | 2013-07-23 08:00 | 2013-08-24 17:00 |  | 2013-07-10 08:00 | 2013-08-07 17:00 | 2013-07-10 08:00 | 2013-08-07 17:00 | 2013-07-10 08:00 | 2013-08-07 17:00 | 2013-07-23 08:00 | 2013-08-24 17:00 |  | PT_Normal |  |  |  |  | s47SsjeoSh+NYGLcXUSg1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35750 | N | N | 10 | UPTO GRADE SLAB |  | 124455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 1433 | LABOR - CIVIL
%R | 500597 | 6359 | 124456 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STUG1005 | Footing Antitermite | 8178 | 88 | 0 | 184 | 0 | 1861.75 | 1861.75 | 184 | 0 | 0 | 0 |  |  |  | 2013-08-04 08:00 | 2013-09-02 17:00 |  | 2013-07-22 08:00 | 2013-08-20 17:00 | 2013-07-22 08:00 | 2013-08-20 17:00 | 2013-07-22 08:00 | 2013-08-20 17:00 | 2013-08-04 08:00 | 2013-09-02 17:00 |  | PT_Normal |  |  |  |  | rWoQhsybQTazigKI84c3/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35750 | N | N | 10 | UPTO GRADE SLAB |  | 124455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 1861.75 | LABOR- SUBCONTRACTOR
%R | 500598 | 6359 | 124456 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STUG1010 | Footing Blinding | 8163 | 88 | 0 | 184 | 0 | 1048.25 | 1048.25 | 184 | 0 | 0 | 0 |  |  |  | 2013-08-08 08:00 | 2013-09-07 17:00 |  | 2013-07-27 08:00 | 2013-08-25 17:00 | 2013-07-27 08:00 | 2013-08-25 17:00 | 2013-07-27 08:00 | 2013-08-25 17:00 | 2013-08-08 08:00 | 2013-09-07 17:00 |  | PT_Normal |  |  |  |  | 63em0Km7TxysK3yab/Vyaw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35750 | N | N | 10 | UPTO GRADE SLAB |  | 124455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 1048.25 | BLINDING MASON SK
%R | 500599 | 6359 | 124456 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STUG1015 | Footing Waterproofing & Screed | 8164 | 88 | 0 | 200 | 0 | 825 | 825 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-18 08:00 | 2013-09-15 17:00 |  | 2013-08-01 08:00 | 2013-09-02 17:00 | 2013-08-01 08:00 | 2013-09-02 17:00 | 2013-08-01 08:00 | 2013-09-02 17:00 | 2013-08-18 08:00 | 2013-09-15 17:00 |  | PT_Normal |  |  |  |  | QA/hlKteTlmz6ucKk++vBQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35750 | N | N | 10 | UPTO GRADE SLAB |  | 124455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP08 |  | 412.5 | SCREED MASON SK
%R | 500600 | 6359 | 124456 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STUG1020 | Construction of foundations | 8165 | 88 | 0 | 160 | 0 | 7969.5 | 7969.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-09-02 08:00 | 2013-09-24 17:00 |  | 2013-08-20 08:00 | 2013-09-11 17:00 | 2013-08-20 08:00 | 2013-09-11 17:00 | 2013-08-20 08:00 | 2013-09-11 17:00 | 2013-09-02 08:00 | 2013-09-24 17:00 |  | PT_Normal |  |  |  |  | aa7UevHqSx++LOf0pLJT7w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35750 | N | N | 10 | UPTO GRADE SLAB |  | 124455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 7969.5 | STEEL FIXERS SK
%R | 500601 | 6359 | 124456 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STUG1025 | Construction of neck of columns | 8165 | 88 | 0 | 200 | 0 | 1946 | 1946 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-11 08:00 | 2013-10-09 17:00 |  | 2013-08-29 08:00 | 2013-09-26 17:00 | 2013-08-29 08:00 | 2013-09-26 17:00 | 2013-08-29 08:00 | 2013-09-26 17:00 | 2013-09-11 08:00 | 2013-10-09 17:00 |  | PT_Normal |  |  |  |  | TfOeMTutT7CcyQ3oZJEzPQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35750 | N | N | 10 | UPTO GRADE SLAB |  | 124455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 1946 | STEEL FIXERS SK
%R | 500602 | 6359 | 124456 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STUG1030 | Waterproofing Footing & Neck Column | 8178 | 88 | 0 | 200 | 0 | 535.25 | 535.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-21 08:00 | 2013-10-21 17:00 |  | 2013-09-08 08:00 | 2013-10-06 17:00 | 2013-09-08 08:00 | 2013-10-06 17:00 | 2013-09-08 08:00 | 2013-10-06 17:00 | 2013-09-21 08:00 | 2013-10-21 17:00 |  | PT_Normal |  |  |  |  | ab/RlcksTaCZovyrudDTvg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35750 | N | N | 10 | UPTO GRADE SLAB |  | 124455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 535.25 | LABOR- SUBCONTRACTOR
%R | 500603 | 6359 | 124456 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 88 | 0 | 200 | 0 | 1436 | 1436 | 200 | 1100 | 0 | 1100 |  |  |  | 2013-10-02 08:00 | 2013-11-02 17:00 |  | 2013-09-19 08:00 | 2013-10-20 17:00 | 2013-09-19 08:00 | 2013-10-20 17:00 | 2013-09-19 08:00 | 2013-10-20 17:00 | 2013-10-02 08:00 | 2013-11-02 17:00 |  | PT_Normal |  |  |  |  | 8wKSXxqXTje0rQcPIKOvJw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35750 | N | N | 10 | UPTO GRADE SLAB |  | 124455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 718 | LABOR - CIVIL
%R | 500604 | 6359 | 124456 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STUG1040 | Construction of Grade Beams | 8163 | 88 | 0 | 200 | 0 | 8096.25 | 8096.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-21 08:00 | 2013-11-18 17:00 |  | 2013-10-06 08:00 | 2013-11-05 17:00 | 2013-10-06 08:00 | 2013-11-05 17:00 | 2013-10-06 08:00 | 2013-11-05 17:00 | 2013-10-21 08:00 | 2013-11-18 17:00 |  | PT_Normal |  |  |  |  | nZbkWT+DTTGlX5OFW6NjpQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35750 | N | N | 10 | UPTO GRADE SLAB |  | 124455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 8096.25 | BLINDING MASON SK
%R | 500605 | 6359 | 124456 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STUG1045 | Construction of slab on grade | 8163 | 88 | 0 | 200 | 0 | 5538.75 | 5538.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-17 08:00 | 2013-12-15 17:00 |  | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-17 08:00 | 2013-12-15 17:00 |  | PT_Normal |  |  |  |  | PW+PFsjlRkiG5l1WlKCt4A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35750 | N | N | 10 | UPTO GRADE SLAB |  | 124455 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 5538.75 | BLINDING MASON SK
%R | 500606 | 6359 | 124458 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STFF2020 | Column-Rebar & Formwork | 8166 | 88 | 0 | 200 | 0 | 3418 | 3418 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-15 08:00 | 2014-02-13 17:00 |  | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 |  | PT_Normal |  |  |  |  | Xf3obMd0QUyPvigncC+o1Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35780 | N | N | 15 | FIRST FLOORS |  | 124457 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 3418 | CARPENTERS SK
%R | 500607 | 6359 | 124458 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STFF2025 | Column-Concrete | 8167 | 88 | 0 | 184 | 0 | 339.5 | 339.5 | 184 | 0 | 0 | 0 |  |  |  | 2014-01-25 08:00 | 2014-02-20 17:00 |  | 2014-01-12 08:00 | 2014-02-06 17:00 | 2014-01-12 08:00 | 2014-02-06 17:00 | 2014-01-12 08:00 | 2014-02-06 17:00 | 2014-01-25 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | ujMZqO5uRGeb582HRrxaOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35780 | N | N | 15 | FIRST FLOORS |  | 124457 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 339.5 | CONCRETE MASON SK
%R | 500608 | 6359 | 124458 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 88 | 0 | 200 | 0 | 19080.25 | 19080.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-28 08:00 | 2014-02-26 17:00 |  | 2014-01-15 08:00 | 2014-02-13 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 |  | PT_Normal |  |  |  |  | KgaJ2s2jR8GZMVmvgX3rTA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35780 | N | N | 15 | FIRST FLOORS |  | 124457 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 19080.25 | STEEL FIXERS SK
%R | 500609 | 6359 | 124458 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 88 | 0 | 112 | 0 | 1288 | 1288 | 112 | 0 | 0 | 0 |  |  |  | 2014-02-15 08:00 | 2014-03-02 17:00 |  | 2014-02-01 08:00 | 2014-02-17 17:00 | 2014-02-01 08:00 | 2014-02-17 17:00 | 2014-02-01 08:00 | 2014-02-17 17:00 | 2014-02-15 08:00 | 2014-03-02 17:00 |  | PT_Normal |  |  |  |  | /e5XBcK1TfK42Bd1m0tHyw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35780 | N | N | 15 | FIRST FLOORS |  | 124457 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1288 | CONCRETE MASON SK
%R | 500610 | 6359 | 124459 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STRF2040 | Column-Rebar & Formwork | 8166 | 216 | 0 | 144 | 0 | 1176 | 1176 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-03-31 17:00 |  | 2014-02-06 08:00 | 2014-02-27 17:00 | 2014-02-06 08:00 | 2014-02-27 17:00 | 2014-02-06 08:00 | 2014-02-27 17:00 | 2014-03-11 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | wJvH1wueRo+s7OYgPYzX8g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35790 | N | N | 20 | ROOF |  | 124457 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1176 | CARPENTERS SK
%R | 500611 | 6359 | 124459 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STRF2045 | Column-Concrete | 8167 | 296 | 0 | 136 | 0 | 80.5 | 80.5 | 136 | 0 | 0 | 0 |  |  |  | 2014-03-26 08:00 | 2014-04-14 17:00 |  | 2014-02-10 08:00 | 2014-03-02 17:00 | 2014-02-10 08:00 | 2014-03-02 17:00 | 2014-02-10 08:00 | 2014-03-02 17:00 | 2014-03-26 08:00 | 2014-04-14 17:00 |  | PT_Normal |  |  |  |  | bZH9NkUQQp6EAiG5w0Ms0A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35790 | N | N | 20 | ROOF |  | 124457 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 80.5 | CONCRETE MASON SK
%R | 500612 | 6359 | 124459 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STRF2050 | Slab-Rebar & Formwork - Head Room | 8165 | 296 | 0 | 160 | 0 | 3444 | 3444 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-29 08:00 | 2014-04-20 17:00 |  | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-03-29 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | pyv4b6f5Rc6+YZs54CwHRQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35790 | N | N | 20 | ROOF |  | 124457 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 3444 | STEEL FIXERS SK
%R | 500613 | 6359 | 124459 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STRF2055 | Slab-Concrete-Head room | 8167 | 296 | 0 | 104 | 0 | 280 | 280 | 104 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-04-26 17:00 |  | 2014-02-27 08:00 | 2014-03-13 17:00 | 2014-02-27 08:00 | 2014-03-13 17:00 | 2014-02-27 08:00 | 2014-03-13 17:00 | 2014-04-12 08:00 | 2014-04-26 17:00 |  | PT_Normal |  |  |  |  | 13W7vRYUQ4i545dSGdrE5w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35790 | N | N | 20 | ROOF |  | 124457 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 280 | CONCRETE MASON SK
%R | 500614 | 6359 | 124459 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STRF2060 | Construction of Parapets | 8168 | 584 | 0 | 200 | 0 | 1175 | 1175 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-31 08:00 | 2014-06-28 17:00 |  | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | nQ74XpqBSX66Se4f7E/iyA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35790 | N | N | 20 | ROOF |  | 124457 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1175 | BLOCK MASON SK
%R | 500615 | 6359 | 124459 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STRF2065 | Construction of up stands/Plinth | 8165 | 624 | 0 | 200 | 0 | 549.5 | 549.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-22 08:00 | 2014-07-20 17:00 |  | 2014-03-23 08:00 | 2014-04-20 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 |  | PT_Normal |  |  |  |  | hVmhsF9XQEq9hyLF6GzKrg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35790 | N | N | 20 | ROOF |  | 124457 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 549.5 | STEEL FIXERS SK
%R | 500616 | 6359 | 124460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STGF2000 | Column-Rebar & Formwork | 8165 | 88 | 0 | 200 | 0 | 4984 | 4984 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-03 08:00 | 2014-01-01 17:00 |  | 2013-11-20 08:00 | 2013-12-19 17:00 | 2013-11-20 08:00 | 2013-12-19 17:00 | 2013-11-20 08:00 | 2013-12-19 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 |  | PT_Normal |  |  |  |  | cDx3Bd+vRjuQSQjZJYnb4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35770 | N | N | 10 | GROUND FLOOR |  | 124457 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 4984 | STEEL FIXERS SK
%R | 500617 | 6359 | 124460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STGF2005 | Column-Concrete | 8167 | 88 | 0 | 184 | 0 | 388.5 | 388.5 | 184 | 0 | 0 | 0 |  |  |  | 2013-12-12 08:00 | 2014-01-08 17:00 |  | 2013-11-30 08:00 | 2013-12-26 17:00 | 2013-11-30 08:00 | 2013-12-26 17:00 | 2013-11-30 08:00 | 2013-12-26 17:00 | 2013-12-12 08:00 | 2014-01-08 17:00 |  | PT_Normal |  |  |  |  | GgR/oT48QKS1vLFvpFbp3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35770 | N | N | 10 | GROUND FLOOR |  | 124457 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 388.5 | CONCRETE MASON SK
%R | 500618 | 6359 | 124460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 88 | 0 | 200 | 0 | 18721.5 | 18721.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-28 08:00 | 2014-01-25 17:00 |  | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 |  | PT_Normal |  |  |  |  | D9EEZ9RaSwqwabMbb6LttQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35770 | N | N | 10 | GROUND FLOOR |  | 124457 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 18721.5 | STEEL FIXERS SK
%R | 500619 | 6359 | 124460 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 88 | 0 | 112 | 0 | 1456 | 1456 | 112 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-01-28 17:00 |  | 2013-12-31 08:00 | 2014-01-15 17:00 | 2013-12-31 08:00 | 2014-01-15 17:00 | 2013-12-31 08:00 | 2014-01-15 17:00 | 2014-01-13 08:00 | 2014-01-28 17:00 |  | PT_Normal |  |  |  |  | jiZHpmbyR+yPR1IcIsFypg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35770 | N | N | 10 | GROUND FLOOR |  | 124457 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1456 | CONCRETE MASON SK
%R | 500620 | 6359 | 124462 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4SLEX5105 | Laying of Grass/ green area | 8178 | 576 | 0 | 200 | 0 | 5488 | 5488 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-06 08:00 | 2014-09-03 17:00 |  | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-08-06 08:00 | 2014-09-03 17:00 |  | PT_Normal |  |  |  |  | WdltzlayTxyar0gtBJh1Yw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36060 | N | N | 25 | SOFT LANDSCAPING |  | 124461 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 5488 | LABOR- SUBCONTRACTOR
%R | 500621 | 6359 | 124462 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4SLEX5110 | Laying of Palm tree | 8178 | 576 | 552 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | PLv/UQpoSwSYBNwMQzHjlA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36060 | N | N | 25 | SOFT LANDSCAPING |  | 124461 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 336 | LABOR- SUBCONTRACTOR
%R | 500622 | 6359 | 124463 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4HDEX5090 | kerb works | 8173 | 576 | 0 | 160 | 0 | 712 | 712 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-26 08:00 | 2014-07-19 17:00 |  | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-06-26 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | gNqCje/9TO6E8y5273CJBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36050 | N | N | 20 | HARD LANDSCAPING |  | 124461 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 712 | KERBSTONE MASON SK
%R | 500623 | 6359 | 124463 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4HDEX5095 | Cobble Stone Works | 8170 | 576 | 0 | 160 | 0 | 456 | 456 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-08 08:00 | 2014-07-30 17:00 |  | 2014-04-15 08:00 | 2014-05-07 17:00 | 2014-04-15 08:00 | 2014-05-07 17:00 | 2014-04-15 08:00 | 2014-05-07 17:00 | 2014-07-08 08:00 | 2014-07-30 17:00 |  | PT_Normal |  |  |  |  | Mgm32q3DSEiKgWLi76FnYw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36050 | N | N | 20 | HARD LANDSCAPING |  | 124461 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 456 | TILE MASON SK
%R | 500624 | 6359 | 124463 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4HDEX5100 | Interlock works | 8174 | 576 | 0 | 160 | 0 | 408 | 408 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-22 08:00 | 2014-08-17 17:00 |  | 2014-04-29 08:00 | 2014-05-21 17:00 | 2014-04-29 08:00 | 2014-05-21 17:00 | 2014-04-29 08:00 | 2014-05-21 17:00 | 2014-07-22 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | 2Rj8Pm0BTMO9p/lfmLMtgA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36050 | N | N | 20 | HARD LANDSCAPING |  | 124461 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 408 | INTERLOCK MASON SK
%R | 500625 | 6359 | 124464 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4MSEX5020 | Construction Entrance Ramp | 8164 | 552 | 0 | 200 | 0 | 1288 | 1288 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-25 17:00 |  | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | nF1XbpDHQvKGdMTnta+LOg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36030 | N | N | 10 | MISCELLANEOUS |  | 124461 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1288 | SCREED MASON SK
%R | 500626 | 6359 | 124464 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4MSEX5025 | SS.Handrails and Balustrades | 8178 | 576 | 0 | 160 | 0 | 400 | 400 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-18 08:00 | 2014-07-10 17:00 |  | 2014-03-26 08:00 | 2014-04-17 17:00 | 2014-03-26 08:00 | 2014-04-17 17:00 | 2014-03-26 08:00 | 2014-04-17 17:00 | 2014-06-18 08:00 | 2014-07-10 17:00 |  | PT_Normal |  |  |  |  | UqF04bVKRxmloRO66NipAQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36030 | N | N | 10 | MISCELLANEOUS |  | 124461 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 400 | LABOR- SUBCONTRACTOR
%R | 500627 | 6359 | 124464 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4MSEX5015 | Construction of grease Trap | 8178 | 344 | 0 | 160 | 0 | 88 | 88 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-19 17:00 |  | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-05-28 08:00 | 2014-06-19 17:00 |  | PT_Normal |  |  |  |  | fp1yzCXpRRmiPqGE88Nr1Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36030 | N | N | 10 | MISCELLANEOUS |  | 124461 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 88 | LABOR- SUBCONTRACTOR
%R | 500628 | 6359 | 124464 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4MSEX5000 | Construction of Manholes | 8172 | 344 | 0 | 200 | 0 | 880 | 880 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-24 08:00 | 2014-05-22 17:00 |  | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 |  | PT_Normal |  |  |  |  | 2G0yt2GhQem0NqBk17KJYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36030 | N | N | 10 | MISCELLANEOUS |  | 124461 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 880 | MANHOLES SK
%R | 500629 | 6359 | 124464 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4MSEX5005 | Construction of Soak pit, Chambers | 8172 | 344 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-08 08:00 | 2014-06-05 17:00 |  | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-05-08 08:00 | 2014-06-05 17:00 |  | PT_Normal |  |  |  |  | MwtyIz4zQCSOcS9E2iWV+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36030 | N | N | 10 | MISCELLANEOUS |  | 124461 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 176 | MANHOLES SK
%R | 500630 | 6359 | 124464 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4MSEX5010 | Telephone cable laying | 8177 | 344 | 144 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-21 08:00 | 2014-07-19 17:00 |  | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-06-21 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | /udFeMzQQmmRPjDsNOXihg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36030 | N | N | 10 | MISCELLANEOUS |  | 124461 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 500 | LABOR - CIVIL
%R | 500631 | 6359 | 124464 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 200 | 0 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | FNKVu1LiTmOCXEdWRKPg3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36030 | N | N | 10 | MISCELLANEOUS |  | 124461 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 400 | LABOR- SUBCONTRACTOR
%R | 500632 | 6359 | 124465 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4WEEX5030 | Excavation | 8177 | 408 | 0 | 160 | 0 | 128 | 128 | 160 | 80 | 0 | 80 |  |  |  | 2014-06-02 08:00 | 2014-06-24 17:00 |  | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-06-02 08:00 | 2014-06-24 17:00 |  | PT_Normal |  |  |  |  | csgbr9ZETHKeUWwZTbOQ1Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36040 | N | N | 15 | WATER TANK ENCLOSURE |  | 124461 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 128 | LABOR - CIVIL
%R | 500633 | 6359 | 124465 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4WEEX5035 | Construction of Raft | 8165 | 432 | 0 | 200 | 0 | 1624 | 1624 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-07-09 17:00 |  | 2014-04-09 08:00 | 2014-05-07 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 | 2014-06-11 08:00 | 2014-07-09 17:00 |  | PT_Normal |  |  |  |  | 1oLXyfcsTr292JxpL9mHcw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36040 | N | N | 15 | WATER TANK ENCLOSURE |  | 124461 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1624 | STEEL FIXERS SK
%R | 500634 | 6359 | 124465 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4WEEX5040 | Block works & Plastering | 8168 | 432 | 0 | 200 | 0 | 888 | 888 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-23 08:00 | 2014-07-21 17:00 |  | 2014-04-21 08:00 | 2014-05-19 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 |  | PT_Normal |  |  |  |  | T2ypLfmgR6Kl0d8UZOcc+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36040 | N | N | 15 | WATER TANK ENCLOSURE |  | 124461 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 888 | BLOCK MASON SK
%R | 500635 | 6359 | 124465 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4WEEX5045 | Flooring & Painting | 8178 | 432 | 0 | 200 | 0 | 408 | 408 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-05 08:00 | 2014-08-05 17:00 |  | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-07-05 08:00 | 2014-08-05 17:00 |  | PT_Normal |  |  |  |  | IXnv0RSpSgSeM2F217K4qw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36040 | N | N | 15 | WATER TANK ENCLOSURE |  | 124461 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 408 | LABOR- SUBCONTRACTOR
%R | 500636 | 6359 | 124465 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4WEEX5050 | Installation of Steel Gate | 8178 | 432 | 0 | 160 | 0 | 112 | 112 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-22 08:00 | 2014-08-17 17:00 |  | 2014-05-20 08:00 | 2014-06-11 17:00 | 2014-05-20 08:00 | 2014-06-11 17:00 | 2014-05-20 08:00 | 2014-06-11 17:00 | 2014-07-22 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | q6r+gLHIT7+MS/U2tziczg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36040 | N | N | 15 | WATER TANK ENCLOSURE |  | 124461 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 112 | LABOR- SUBCONTRACTOR
%R | 500637 | 6359 | 124465 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 432 | 0 | 200 | 0 | 616 | 616 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-06 08:00 | 2014-09-03 17:00 |  | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-08-06 08:00 | 2014-09-03 17:00 |  | PT_Normal |  |  |  |  | K35LFHXrQ7qLreLI9WGiBA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36040 | N | N | 15 | WATER TANK ENCLOSURE |  | 124461 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 616 | LABOR- SUBCONTRACTOR
%R | 500638 | 6359 | 124465 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 432 | 0 | 200 | 0 | 382.4 | 382.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | IPYCJ39lQxyVk2ArLozDpw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36040 | N | N | 15 | WATER TANK ENCLOSURE |  | 124461 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 382.4 | LABOR- SUBCONTRACTOR
%R | 500639 | 6359 | 124468 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4AREL3665 | External Plastering | 8169 | 608 | 0 | 200 | 0 | 12200 | 12200 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | gcdXm43vRuuaYce2d+pW9A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35870 | N | N | 15 | ELEVATION |  | 124467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 12200 | PLASTER MASON SK
%R | 500640 | 6359 | 124468 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4AREL3670 | External stone cladding works | 8170 | 608 | 0 | 160 | 0 | 936 | 936 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-06 08:00 | 2014-08-28 17:00 |  | 2014-05-06 08:00 | 2014-05-28 17:00 | 2014-05-06 08:00 | 2014-05-28 17:00 | 2014-05-06 08:00 | 2014-05-28 17:00 | 2014-08-06 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | pewgigPqQ6CBAV3HEaX5lg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35870 | N | N | 15 | ELEVATION |  | 124467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 936 | TILE MASON SK
%R | 500641 | 6359 | 124468 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4AREL3675 | GRC works | 8178 | 608 | 0 | 160 | 0 | 550 | 550 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-09-03 17:00 |  | 2014-05-12 08:00 | 2014-06-03 17:00 | 2014-05-12 08:00 | 2014-06-03 17:00 | 2014-05-12 08:00 | 2014-06-03 17:00 | 2014-08-12 08:00 | 2014-09-03 17:00 |  | PT_Normal |  |  |  |  | HqO/jfMsTES0VhxZq7TmzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35870 | N | N | 15 | ELEVATION |  | 124467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 550 | LABOR- SUBCONTRACTOR
%R | 500642 | 6359 | 124468 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4AREL3680 | External Painting | 8178 | 608 | 40 | 160 | 0 | 4224 | 4224 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-24 08:00 | 2014-09-15 17:00 |  | 2014-05-24 08:00 | 2014-06-15 17:00 | 2014-05-24 08:00 | 2014-06-15 17:00 | 2014-05-24 08:00 | 2014-06-15 17:00 | 2014-08-24 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | JuVqFfOmT++B6mPGga0nJQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35870 | N | N | 15 | ELEVATION |  | 124467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 4224 | LABOR- SUBCONTRACTOR
%R | 500643 | 6359 | 124469 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARRF3630 | Leveling Screed for Waterproofing | 8164 | 624 | 0 | 200 | 0 | 711.5 | 711.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-03 08:00 | 2014-07-31 17:00 |  | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-07-03 08:00 | 2014-07-31 17:00 |  | PT_Normal |  |  |  |  | d+n0eZJVSlKyUtFaD5ym1Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35860 | N | N | 10 | ROOF |  | 124467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 711.5 | SCREED MASON SK
%R | 500644 | 6359 | 124469 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARRF3635 | Laying of Waterproofing Membrane | 8178 | 624 | 0 | 200 | 0 | 986.25 | 986.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-07 08:00 | 2014-08-07 17:00 |  | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-07-07 08:00 | 2014-08-07 17:00 |  | PT_Normal |  |  |  |  | f744MvMDSSO4AmJ5fq516Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35860 | N | N | 10 | ROOF |  | 124467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 986.25 | LABOR- SUBCONTRACTOR
%R | 500645 | 6359 | 124469 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARRF3640 | Installation of Insulation & Protection | 8178 | 624 | 0 | 200 | 0 | 1250.25 | 1250.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-12 08:00 | 2014-08-12 17:00 |  | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 |  | PT_Normal |  |  |  |  | QKBJVfMHR1iLpRuIHa7Kqw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35860 | N | N | 10 | ROOF |  | 124467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1250.25 | LABOR- SUBCONTRACTOR
%R | 500646 | 6359 | 124469 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 624 | 0 | 200 | 0 | 626 | 626 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | HvnEq0nQRciq1o/0jyY69w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35860 | N | N | 10 | ROOF |  | 124467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 626 | TILE MASON SK
%R | 500647 | 6359 | 124469 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 624 | 0 | 160 | 0 | 616 | 616 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-09-03 17:00 |  | 2014-05-10 08:00 | 2014-06-01 17:00 | 2014-05-10 08:00 | 2014-06-01 17:00 | 2014-05-10 08:00 | 2014-06-01 17:00 | 2014-08-12 08:00 | 2014-09-03 17:00 |  | PT_Normal |  |  |  |  | 0fBPPpm8TQanEybATzXxhw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35860 | N | N | 10 | ROOF |  | 124467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 616 | LABOR- SUBCONTRACTOR
%R | 500648 | 6359 | 124469 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 624 | 0 | 200 | 0 | 859.25 | 859.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-24 08:00 | 2014-08-25 17:00 |  | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-07-24 08:00 | 2014-08-25 17:00 |  | PT_Normal |  |  |  |  | LzH6m7oSTZWTkAOojb/xuw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35860 | N | N | 10 | ROOF |  | 124467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 859.25 | LABOR- SUBCONTRACTOR
%R | 500649 | 6359 | 124469 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARRF3660 | Installation of Access Ladder | 8178 | 624 | 600 | 120 | 0 | 352 | 352 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-15 17:00 |  | 2014-05-27 08:00 | 2014-06-12 17:00 | 2014-05-27 08:00 | 2014-06-12 17:00 | 2014-05-27 08:00 | 2014-06-12 17:00 | 2014-08-30 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | JzIhv1iKQyqkM2SI0fowOw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35860 | N | N | 10 | ROOF |  | 124467 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 352 | LABOR- SUBCONTRACTOR
%R | 500650 | 6359 | 124471 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARRF3605 | Plastering work | 8169 | 624 | 0 | 160 | 0 | 3833 | 3833 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-05 08:00 | 2014-07-27 17:00 |  | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-07-05 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | aVWaERVfR1uh0qOcVP5k6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35840 | N | N | 20 | ROOF |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 3833 | PLASTER MASON SK
%R | 500651 | 6359 | 124471 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARRF3610 | Flooring screed | 8164 | 624 | 0 | 120 | 0 | 154 | 154 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-22 08:00 | 2014-08-11 17:00 |  | 2014-04-22 08:00 | 2014-05-08 17:00 | 2014-04-22 08:00 | 2014-05-08 17:00 | 2014-04-22 08:00 | 2014-05-08 17:00 | 2014-07-22 08:00 | 2014-08-11 17:00 |  | PT_Normal |  |  |  |  | 6f8ug92BSVSihnO+rsCnkw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35840 | N | N | 20 | ROOF |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 154 | SCREED MASON SK
%R | 500652 | 6359 | 124471 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARRF3695 | Painting -Storage area | 8178 | 624 | 0 | 160 | 0 | 1640 | 1640 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-06 08:00 | 2014-08-28 17:00 |  | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-08-06 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | A7tm+76wTViAS9cQOdZjRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35840 | N | N | 20 | ROOF |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1640 | LABOR- SUBCONTRACTOR
%R | 500653 | 6359 | 124471 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARRF3620 | Epoxy Painting -Storage area | 8178 | 624 | 0 | 120 | 0 | 48.5 | 48.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-24 08:00 | 2014-09-09 17:00 |  | 2014-05-21 08:00 | 2014-06-07 17:00 | 2014-05-21 08:00 | 2014-06-07 17:00 | 2014-05-21 08:00 | 2014-06-07 17:00 | 2014-08-24 08:00 | 2014-09-09 17:00 |  | PT_Normal |  |  |  |  | OsJ54ZWnSLaE+7Hh1ZKCeg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35840 | N | N | 20 | ROOF |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 48.5 | LABOR- SUBCONTRACTOR
%R | 500654 | 6359 | 124471 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARRF3600 | Block work | 8168 | 624 | 0 | 160 | 0 | 697.25 | 697.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-23 08:00 | 2014-07-15 17:00 |  | 2014-03-24 08:00 | 2014-04-15 17:00 | 2014-03-24 08:00 | 2014-04-15 17:00 | 2014-03-24 08:00 | 2014-04-15 17:00 | 2014-06-23 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | s9GN7SxqQManCv5UDLEQwQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35840 | N | N | 20 | ROOF |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 697.25 | BLOCK MASON SK
%R | 500655 | 6359 | 124472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARFF3385 | Handrail & Balustrade | 8178 | 24 | 0 | 160 | 0 | 175 | 175 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-06 08:00 | 2014-08-28 17:00 |  | 2014-07-30 08:00 | 2014-08-25 17:00 | 2014-07-30 08:00 | 2014-08-25 17:00 | 2014-07-30 08:00 | 2014-08-25 17:00 | 2014-08-06 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | v7wjADstTiCCqmtme1iInQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35830 | N | N | 15 | FIRST FLOORS |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 175 | LABOR- SUBCONTRACTOR
%R | 500656 | 6359 | 124472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARFF3300 | Block work | 8168 | 24 | 0 | 200 | 0 | 7341 | 7341 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-04-08 17:00 |  | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | xZ2MXSVIS3OViBkhFLYB8w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35830 | N | N | 15 | FIRST FLOORS |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 7341 | BLOCK MASON SK
%R | 500657 | 6359 | 124472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARFF3305 | Plastering work | 8169 | 24 | 0 | 200 | 0 | 7518.75 | 7518.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-07 08:00 | 2014-05-05 17:00 |  | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | /qr22ienQFGmFMa9WhLLew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35830 | N | N | 15 | FIRST FLOORS |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 7518.75 | PLASTER MASON SK
%R | 500658 | 6359 | 124472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARFF3310 | Flooring screed | 8164 | 160 | 136 | 168 | 0 | 1082.5 | 1082.5 | 168 | 0 | 0 | 0 |  |  |  | 2014-05-05 08:00 | 2014-05-28 17:00 |  | 2014-04-12 08:00 | 2014-05-05 17:00 | 2014-04-12 08:00 | 2014-05-05 17:00 | 2014-04-12 08:00 | 2014-05-05 17:00 | 2014-05-05 08:00 | 2014-05-28 17:00 |  | PT_Normal |  |  |  |  | TzEibDnkRMKYGnX7GG53ug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35830 | N | N | 15 | FIRST FLOORS |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1082.5 | SCREED MASON SK
%R | 500659 | 6359 | 124472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARFF3315 | Wet area waterproofing | 8178 | 24 | 0 | 120 | 0 | 1374 | 1374 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-28 08:00 | 2014-05-14 17:00 |  | 2014-04-24 08:00 | 2014-05-11 17:00 | 2014-04-24 08:00 | 2014-05-11 17:00 | 2014-04-24 08:00 | 2014-05-11 17:00 | 2014-04-28 08:00 | 2014-05-14 17:00 |  | PT_Normal |  |  |  |  | SKPhOoM/ReqcGYgm8njtvQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35830 | N | N | 15 | FIRST FLOORS |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1374 | LABOR- SUBCONTRACTOR
%R | 500660 | 6359 | 124472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARFF3395 | Final Painting | 8178 | 24 | 0 | 200 | 0 | 5256.25 | 5256.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-08-14 08:00 | 2014-09-11 17:00 | 2014-08-14 08:00 | 2014-09-11 17:00 | 2014-08-14 08:00 | 2014-09-11 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | VCjteXTVSuibo72KpQh5ow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35830 | N | N | 15 | FIRST FLOORS |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 5256.25 | LABOR- SUBCONTRACTOR
%R | 500661 | 6359 | 124472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARFF3330 | Paint First coat | 8178 | 232 | 208 | 200 | 0 | 5256.25 | 5256.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-24 08:00 | 2014-06-21 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 |  | PT_Normal |  |  |  |  | 25Zr9Y8ORJGAOJoCPlpjFg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35830 | N | N | 15 | FIRST FLOORS |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 5256.25 | LABOR- SUBCONTRACTOR
%R | 500662 | 6359 | 124472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARFF3320 | Ceramic Wall Tiling | 8170 | 24 | 0 | 200 | 0 | 1516 | 1516 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-07 08:00 | 2014-06-04 17:00 |  | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 |  | PT_Normal |  |  |  |  | K8558RWUTHq4e3y5uQ0c+A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35830 | N | N | 15 | FIRST FLOORS |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1516 | TILE MASON SK
%R | 500663 | 6359 | 124472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARFF3325 | Porcelain Tile flooring | 8170 | 24 | 0 | 200 | 0 | 1341 | 1341 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-05-13 08:00 | 2014-06-10 17:00 | 2014-05-13 08:00 | 2014-06-10 17:00 | 2014-05-13 08:00 | 2014-06-10 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | jf4Qzh6eSWSEeW1IKJxmuQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35830 | N | N | 15 | FIRST FLOORS |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1341 | TILE MASON SK
%R | 500664 | 6359 | 124472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARFF3335 | Slate Tile Flooring & Skirting | 8170 | 176 | 152 | 120 | 0 | 931.25 | 931.25 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-25 08:00 | 2014-07-12 17:00 |  | 2014-05-31 08:00 | 2014-06-16 17:00 | 2014-05-31 08:00 | 2014-06-16 17:00 | 2014-05-31 08:00 | 2014-06-16 17:00 | 2014-06-25 08:00 | 2014-07-12 17:00 |  | PT_Normal |  |  |  |  | emZWt/rARAemIOxVgzstkw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35830 | N | N | 15 | FIRST FLOORS |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 931.25 | TILE MASON SK
%R | 500665 | 6359 | 124472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARFF3350 | Granite - Stair case flooring & Skirting | 8171 | 112 | 88 | 160 | 0 | 850 | 850 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-19 08:00 | 2014-07-12 17:00 |  | 2014-06-03 08:00 | 2014-06-25 17:00 | 2014-06-03 08:00 | 2014-06-25 17:00 | 2014-06-03 08:00 | 2014-06-25 17:00 | 2014-06-19 08:00 | 2014-07-12 17:00 |  | PT_Normal |  |  |  |  | xRGcCdoiSl+C5e6ynVuUZg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35830 | N | N | 15 | FIRST FLOORS |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 850 | GRANITE MASON SK
%R | 500666 | 6359 | 124472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARFF3345 | Fixing of Suspension systems | 8178 | 24 | 0 | 160 | 0 | 1191 | 1191 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-07 08:00 | 2014-06-29 17:00 |  | 2014-06-03 08:00 | 2014-06-25 17:00 | 2014-06-03 08:00 | 2014-06-25 17:00 | 2014-06-03 08:00 | 2014-06-25 17:00 | 2014-06-07 08:00 | 2014-06-29 17:00 |  | PT_Normal |  |  |  |  | MrQtinOlTiyobRu5hColcQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35830 | N | N | 15 | FIRST FLOORS |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1191 | LABOR- SUBCONTRACTOR
%R | 500667 | 6359 | 124472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARFF3360 | Gypsum board false ceiling | 8178 | 24 | 0 | 200 | 0 | 1191 | 1191 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-18 08:00 | 2014-07-16 17:00 |  | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-18 08:00 | 2014-07-16 17:00 |  | PT_Normal |  |  |  |  | JKlr5knKRaCxRMQCZ/0I0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35830 | N | N | 15 | FIRST FLOORS |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1191 | LABOR- SUBCONTRACTOR
%R | 500668 | 6359 | 124472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARFF3365 | Wooden door | 8178 | 24 | 0 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-03 08:00 | 2014-07-20 17:00 |  | 2014-06-30 08:00 | 2014-07-16 17:00 | 2014-06-30 08:00 | 2014-07-16 17:00 | 2014-06-30 08:00 | 2014-07-16 17:00 | 2014-07-03 08:00 | 2014-07-20 17:00 |  | PT_Normal |  |  |  |  | ssnB/o6STg+Bq+vpcndWzA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35830 | N | N | 15 | FIRST FLOORS |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 176 | LABOR- SUBCONTRACTOR
%R | 500669 | 6359 | 124472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARFF3370 | Aluminum Door | 8178 | 24 | 0 | 160 | 0 | 132 | 132 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-12 08:00 | 2014-08-06 17:00 |  | 2014-07-08 08:00 | 2014-07-30 17:00 | 2014-07-08 08:00 | 2014-07-30 17:00 | 2014-07-08 08:00 | 2014-07-30 17:00 | 2014-07-12 08:00 | 2014-08-06 17:00 |  | PT_Normal |  |  |  |  | 8vR2mbqRTMKKNspgxt3onQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35830 | N | N | 15 | FIRST FLOORS |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 132 | LABOR- SUBCONTRACTOR
%R | 500670 | 6359 | 124472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARFF3380 | Aluminum windows | 8178 | 128 | 104 | 160 | 0 | 272.25 | 272.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-06 08:00 | 2014-08-28 17:00 |  | 2014-07-15 08:00 | 2014-08-10 17:00 | 2014-07-15 08:00 | 2014-08-10 17:00 | 2014-07-15 08:00 | 2014-08-10 17:00 | 2014-08-06 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | 95byHNHVR3GYlDkgilKQLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35830 | N | N | 15 | FIRST FLOORS |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 272.25 | LABOR- SUBCONTRACTOR
%R | 500671 | 6359 | 124472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARFF3375 | Carpentry & Joinery Works | 8178 | 24 | 0 | 200 | 0 | 704 | 704 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-20 08:00 | 2014-08-20 17:00 |  | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-20 08:00 | 2014-08-20 17:00 |  | PT_Normal |  |  |  |  | CwCCJmbMQnqo8SjFViOU+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35830 | N | N | 15 | FIRST FLOORS |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 352 | LABOR- SUBCONTRACTOR
%R | 500672 | 6359 | 124472 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARFF3390 | Installation of Granite Counter Top | 8171 | 40 | 16 | 160 | 0 | 110 | 110 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-09 08:00 | 2014-08-31 17:00 |  | 2014-07-30 08:00 | 2014-08-25 17:00 | 2014-07-30 08:00 | 2014-08-25 17:00 | 2014-07-30 08:00 | 2014-08-25 17:00 | 2014-08-09 08:00 | 2014-08-31 17:00 |  | PT_Normal |  |  |  |  | BoRSPnqTS0u7q50mieMNmA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35830 | N | N | 15 | FIRST FLOORS |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 110 | GRANITE MASON SK
%R | 500673 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3075 | Carpentry & Joinery Works | 8178 | 456 | 0 | 160 | 0 | 528 | 528 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-23 08:00 | 2014-08-18 17:00 |  | 2014-05-18 08:00 | 2014-06-09 17:00 | 2014-05-18 08:00 | 2014-06-09 17:00 | 2014-05-18 08:00 | 2014-06-09 17:00 | 2014-07-23 08:00 | 2014-08-18 17:00 |  | PT_Normal |  |  |  |  | /I6n6QO2T0O+c+Xu14zYRQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 528 | LABOR- SUBCONTRACTOR
%R | 500674 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3090 | Installation of Granite Counter Top | 8171 | 456 | 0 | 120 | 0 | 242 | 242 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-09 08:00 | 2014-08-25 17:00 |  | 2014-05-31 08:00 | 2014-06-16 17:00 | 2014-05-31 08:00 | 2014-06-16 17:00 | 2014-05-31 08:00 | 2014-06-16 17:00 | 2014-08-09 08:00 | 2014-08-25 17:00 |  | PT_Normal |  |  |  |  | 61D5BkQKQPmxbYPWPAqe5w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 242 | GRANITE MASON SK
%R | 500675 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3085 | S.S.Balustrade | 8178 | 496 | 40 | 160 | 0 | 175 | 175 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-10 08:00 | 2014-09-01 17:00 |  | 2014-05-26 08:00 | 2014-06-17 17:00 | 2014-05-26 08:00 | 2014-06-17 17:00 | 2014-05-26 08:00 | 2014-06-17 17:00 | 2014-08-10 08:00 | 2014-09-01 17:00 |  | PT_Normal |  |  |  |  | LDBwSbokQneIWVP50JCmhA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 175 | LABOR- SUBCONTRACTOR
%R | 500676 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3095 | Final Painting | 8178 | 456 | 0 | 200 | 0 | 5936.25 | 5936.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | Rjpvp7y7TtC0xlCzvAGnmQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 5936.25 | LABOR- SUBCONTRACTOR
%R | 500677 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3000 | Block work | 8168 | 392 | 0 | 200 | 0 | 9262.5 | 9262.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-24 08:00 | 2014-04-21 17:00 |  | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-03-24 08:00 | 2014-04-21 17:00 |  | PT_Normal |  |  |  |  | eOtgMhGqQWycy5IGEvfbDw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 9262.5 | BLOCK MASON SK
%R | 500678 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3005 | Plastering work | 8169 | 392 | 0 | 200 | 0 | 11350 | 11350 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-13 17:00 |  | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 |  | PT_Normal |  |  |  |  | U4FN2th2Q1u48N+jIGJb6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 5675 | PLASTER MASON SK
%R | 500679 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3010 | Flooring screed | 8164 | 456 | 64 | 168 | 0 | 2171.5 | 2171.5 | 168 | 0 | 0 | 0 |  |  |  | 2014-05-03 08:00 | 2014-05-26 17:00 |  | 2014-02-25 08:00 | 2014-03-20 17:00 | 2014-02-25 08:00 | 2014-03-20 17:00 | 2014-02-25 08:00 | 2014-03-20 17:00 | 2014-05-03 08:00 | 2014-05-26 17:00 |  | PT_Normal |  |  |  |  | aIgZ5hF4QqOW0qi2PXRnLQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 2171.5 | SCREED MASON SK
%R | 500680 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 392 | 0 | 120 | 0 | 423.5 | 423.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-03 08:00 | 2014-05-19 17:00 |  | 2014-03-06 08:00 | 2014-03-23 17:00 | 2014-03-06 08:00 | 2014-03-23 17:00 | 2014-03-06 08:00 | 2014-03-23 17:00 | 2014-05-03 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | IW4GSKTzTKaR3mHa1FqmZQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 423.5 | LABOR- SUBCONTRACTOR
%R | 500681 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3030 | Paint First coat | 8178 | 504 | 0 | 200 | 0 | 5936.25 | 5936.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-18 08:00 | 2014-06-15 17:00 |  | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-05-18 08:00 | 2014-06-15 17:00 |  | PT_Normal |  |  |  |  | a0iOGXckTKuGynkL6RZFkA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 5936.25 | LABOR- SUBCONTRACTOR
%R | 500682 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3020 | Ceramic Wall Tiling | 8170 | 392 | 0 | 200 | 0 | 3534.75 | 3534.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-08 08:00 | 2014-06-05 17:00 |  | 2014-03-12 08:00 | 2014-04-09 17:00 | 2014-03-12 08:00 | 2014-04-09 17:00 | 2014-03-12 08:00 | 2014-04-09 17:00 | 2014-05-08 08:00 | 2014-06-05 17:00 |  | PT_Normal |  |  |  |  | yJbb6BwBQyqweBmPqntZtA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 3534.75 | TILE MASON SK
%R | 500683 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3025 | Porcelain Tile flooring | 8170 | 392 | 0 | 200 | 0 | 1918.75 | 1918.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-14 08:00 | 2014-06-11 17:00 |  | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1918.75 | TILE MASON SK
%R | 500684 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3040 | Cobble Tile flooring | 8170 | 456 | 0 | 120 | 0 | 700 | 700 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-19 08:00 | 2014-07-06 17:00 |  | 2014-04-14 08:00 | 2014-04-30 17:00 | 2014-04-14 08:00 | 2014-04-30 17:00 | 2014-04-14 08:00 | 2014-04-30 17:00 | 2014-06-19 08:00 | 2014-07-06 17:00 |  | PT_Normal |  |  |  |  | ZmKK/2nPTuOWnJem8c0ZfA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 700 | TILE MASON SK
%R | 500685 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 472 | 16 | 120 | 0 | 931.25 | 931.25 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-01 17:00 |  | 2014-04-07 08:00 | 2014-04-23 17:00 | 2014-04-07 08:00 | 2014-04-23 17:00 | 2014-04-07 08:00 | 2014-04-23 17:00 | 2014-06-15 08:00 | 2014-07-01 17:00 |  | PT_Normal |  |  |  |  | NzMMRMfiQFG49I2EWjdukQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 931.25 | TILE MASON SK
%R | 500686 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 456 | 0 | 160 | 0 | 850 | 850 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-28 08:00 | 2014-07-20 17:00 |  | 2014-04-22 08:00 | 2014-05-14 17:00 | 2014-04-22 08:00 | 2014-05-14 17:00 | 2014-04-22 08:00 | 2014-05-14 17:00 | 2014-06-28 08:00 | 2014-07-20 17:00 |  | PT_Normal |  |  |  |  | Y6um13f3QuenseMz01/7fA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 850 | GRANITE MASON SK
%R | 500687 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3045 | Fixing of Suspension systems | 8178 | 392 | 0 | 160 | 0 | 1320.5 | 1320.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-01 08:00 | 2014-06-23 17:00 |  | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-06-01 08:00 | 2014-06-23 17:00 |  | PT_Normal |  |  |  |  | s0/KmBjyQ6CWQ1G67szWzw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1320.5 | LABOR- SUBCONTRACTOR
%R | 500688 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3055 | Aluminum tile false ceiling | 8178 | 416 | 24 | 200 | 0 | 130 | 130 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-07-10 17:00 |  | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 |  | PT_Normal |  |  |  |  | /kztnDsBSBm4QZU+wS5Ndw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 130 | LABOR- SUBCONTRACTOR
%R | 500689 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3060 | Gypsum board false ceiling | 8178 | 392 | 0 | 200 | 0 | 1216.3 | 1216.3 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-07-10 17:00 |  | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 |  | PT_Normal |  |  |  |  | cJ+csNCWTaa9p40XiGH59g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1216.3 | LABOR- SUBCONTRACTOR
%R | 500690 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3065 | Wooden door & PVC Door | 8178 | 456 | 0 | 120 | 0 | 660 | 660 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-12 08:00 | 2014-07-28 17:00 |  | 2014-05-06 08:00 | 2014-05-22 17:00 | 2014-05-06 08:00 | 2014-05-22 17:00 | 2014-05-06 08:00 | 2014-05-22 17:00 | 2014-07-12 08:00 | 2014-07-28 17:00 |  | PT_Normal |  |  |  |  | KGiBGlyOS1G7A5gbHIvvLg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 660 | LABOR- SUBCONTRACTOR
%R | 500691 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3070 | Aluminum doors | 8178 | 456 | 0 | 120 | 0 | 88 | 88 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-17 08:00 | 2014-08-06 17:00 |  | 2014-05-12 08:00 | 2014-05-28 17:00 | 2014-05-12 08:00 | 2014-05-28 17:00 | 2014-05-12 08:00 | 2014-05-28 17:00 | 2014-07-17 08:00 | 2014-08-06 17:00 |  | PT_Normal |  |  |  |  | p4Zql/+xS1OSE0g+93WZ1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 88 | LABOR- SUBCONTRACTOR
%R | 500692 | 6359 | 124473 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ARGF3080 | Aluminum windows | 8178 | 536 | 40 | 160 | 0 | 257.5 | 257.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-09 08:00 | 2014-08-31 17:00 |  | 2014-05-19 08:00 | 2014-06-10 17:00 | 2014-05-19 08:00 | 2014-06-10 17:00 | 2014-05-19 08:00 | 2014-06-10 17:00 | 2014-08-09 08:00 | 2014-08-31 17:00 |  | PT_Normal |  |  |  |  | YSpst86hT5GMrlvSc90oiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35820 | N | N | 10 | GROUND FLOOR |  | 124470 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 257.5 | LABOR- SUBCONTRACTOR
%R | 500693 | 6359 | 124476 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ELRF4070 | Installation of Isolator | 8178 | 24 | 0 | 144 | 0 | 825.6 | 825.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-08-09 08:00 | 2014-08-28 17:00 |  | 2014-08-05 08:00 | 2014-08-25 17:00 | 2014-08-05 08:00 | 2014-08-25 17:00 | 2014-08-05 08:00 | 2014-08-25 17:00 | 2014-08-09 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | Hqoi1elgRdqEvTiCFP9kGQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35920 | N | N | 20 | ROOF |  | 124475 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 825.6 | LABOR- SUBCONTRACTOR
%R | 500694 | 6359 | 124476 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ELRF4075 | Installation of TV Dish Antenna | 8178 | 24 | 0 | 184 | 0 | 1830.4 | 1830.4 | 184 | 0 | 0 | 0 |  |  |  | 2014-08-20 08:00 | 2014-09-15 17:00 |  | 2014-08-17 08:00 | 2014-09-11 17:00 | 2014-08-17 08:00 | 2014-09-11 17:00 | 2014-08-17 08:00 | 2014-09-11 17:00 | 2014-08-20 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | 8jU4CbwCSveyOdtyrw+DdQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35920 | N | N | 20 | ROOF |  | 124475 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1830.4 | LABOR- SUBCONTRACTOR
%R | 500695 | 6359 | 124477 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 128 | 0 | 200 | 0 | 2579.2 | 2579.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-01 08:00 | 2014-04-29 17:00 |  | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 |  | PT_Normal |  |  |  |  | 0PL+oXYeSKWAfovprQgTEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35910 | N | N | 15 | FIRST FLOORS |  | 124475 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 2579.2 | LABOR- SUBCONTRACTOR
%R | 500696 | 6359 | 124477 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ELFF4040 | Cable tray & trunking installation | 8178 | 368 | 0 | 160 | 0 | 3180.8 | 3180.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-18 08:00 | 2014-06-09 17:00 |  | 2014-03-25 08:00 | 2014-04-16 17:00 | 2014-03-25 08:00 | 2014-04-16 17:00 | 2014-03-25 08:00 | 2014-04-16 17:00 | 2014-05-18 08:00 | 2014-06-09 17:00 |  | PT_Normal |  |  |  |  | IO6nRMLsTIyJOwi8c3wBQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35910 | N | N | 15 | FIRST FLOORS |  | 124475 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 3180.8 | LABOR- SUBCONTRACTOR
%R | 500697 | 6359 | 124477 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ELFF4045 | Installation of wiring & Main Cabling | 8178 | 368 | 0 | 200 | 0 | 636.8 | 636.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-26 08:00 | 2014-06-23 17:00 |  | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-05-26 08:00 | 2014-06-23 17:00 |  | PT_Normal |  |  |  |  | 94n6PeUkQMGiE4uBI0Jv9Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35910 | N | N | 15 | FIRST FLOORS |  | 124475 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 636.8 | LABOR- SUBCONTRACTOR
%R | 500698 | 6359 | 124477 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 24 | 0 | 160 | 0 | 454.4 | 454.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-03 08:00 | 2014-07-26 17:00 |  | 2014-06-30 08:00 | 2014-07-22 17:00 | 2014-06-30 08:00 | 2014-07-22 17:00 | 2014-06-30 08:00 | 2014-07-22 17:00 | 2014-07-03 08:00 | 2014-07-26 17:00 |  | PT_Normal |  |  |  |  | BuRIGYWZRRiA8cb9xDIhYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35910 | N | N | 15 | FIRST FLOORS |  | 124475 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 454.4 | LABOR- SUBCONTRACTOR
%R | 500699 | 6359 | 124477 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 24 | 0 | 200 | 0 | 3302.4 | 3302.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | QzuSoR7IS6KCaUKRnjDP+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35910 | N | N | 15 | FIRST FLOORS |  | 124475 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 1651.2 | LABOR- SUBCONTRACTOR
%R | 500700 | 6359 | 124477 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 360 | 0 | 200 | 0 | 4569.6 | 4569.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | ajc4ZcycR1GrPEYi99H5wA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35910 | N | N | 15 | FIRST FLOORS |  | 124475 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 4569.6 | LABOR- SUBCONTRACTOR
%R | 500701 | 6359 | 124477 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ELFF4050 | Installation of Telephone System | 8178 | 200 | 176 | 200 | 0 | 1422.4 | 1422.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-20 08:00 | 2014-08-20 17:00 |  | 2014-06-21 08:00 | 2014-07-19 17:00 | 2014-06-21 08:00 | 2014-07-19 17:00 | 2014-06-21 08:00 | 2014-07-19 17:00 | 2014-07-20 08:00 | 2014-08-20 17:00 |  | PT_Normal |  |  |  |  | Yd9jdnOuQj6hmNVoVOyG/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35910 | N | N | 15 | FIRST FLOORS |  | 124475 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1422.4 | LABOR- SUBCONTRACTOR
%R | 500702 | 6359 | 124478 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 464 | 0 | 200 | 0 | 2579.2 | 2579.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-09 08:00 | 2014-05-07 17:00 |  | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 |  | PT_Normal |  |  |  |  | VzhmdzpbRaGjak5Z/14f1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35900 | N | N | 10 | GROUND FLOOR |  | 124475 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01; period 2: 2014-AP03 |  | 1289.6 | LABOR- SUBCONTRACTOR
%R | 500703 | 6359 | 124478 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ELGF4005 | Cable tray & trunking installation | 8178 | 608 | 0 | 160 | 0 | 3180.8 | 3180.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-12 08:00 | 2014-06-03 17:00 |  | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-05-12 08:00 | 2014-06-03 17:00 |  | PT_Normal |  |  |  |  | BSJk1sPiSdO+6BBiwgthyQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35900 | N | N | 10 | GROUND FLOOR |  | 124475 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 3180.8 | LABOR- SUBCONTRACTOR
%R | 500704 | 6359 | 124478 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ELGF4010 | Installation of wiring & Main Cabling | 8178 | 608 | 216 | 200 | 0 | 636.8 | 636.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-20 08:00 | 2014-06-17 17:00 |  | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | zZngbUYqSmOre2Ys+iYhnA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35900 | N | N | 10 | GROUND FLOOR |  | 124475 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 318.4 | LABOR- SUBCONTRACTOR
%R | 500705 | 6359 | 124478 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 392 | 0 | 160 | 0 | 454.4 | 454.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-26 08:00 | 2014-07-19 17:00 |  | 2014-04-30 08:00 | 2014-05-22 17:00 | 2014-04-30 08:00 | 2014-05-22 17:00 | 2014-04-30 08:00 | 2014-05-22 17:00 | 2014-06-26 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | ppUCO0p9TCON8Vpffbm15A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35900 | N | N | 10 | GROUND FLOOR |  | 124475 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 454.4 | LABOR- SUBCONTRACTOR
%R | 500706 | 6359 | 124478 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 408 | 0 | 200 | 0 | 3302.4 | 3302.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-10 08:00 | 2014-08-11 17:00 |  | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-07-10 08:00 | 2014-08-11 17:00 |  | PT_Normal |  |  |  |  | kG9TWBuaQx6BUTIVeKSdTw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35900 | N | N | 10 | GROUND FLOOR |  | 124475 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 3302.4 | LABOR- SUBCONTRACTOR
%R | 500707 | 6359 | 124478 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 568 | 0 | 200 | 0 | 4569.6 | 4569.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | F/knkDS3S72rVRgolVwUQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35900 | N | N | 10 | GROUND FLOOR |  | 124475 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 4569.6 | LABOR- SUBCONTRACTOR
%R | 500708 | 6359 | 124478 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ELGF4030 | Installation of Telephone System | 8178 | 392 | 40 | 160 | 0 | 1422.4 | 1422.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-08 08:00 | 2014-07-30 17:00 |  | 2014-05-12 08:00 | 2014-06-03 17:00 | 2014-05-12 08:00 | 2014-06-03 17:00 | 2014-05-12 08:00 | 2014-06-03 17:00 | 2014-07-08 08:00 | 2014-07-30 17:00 |  | PT_Normal |  |  |  |  | DBiPhvZGRVGen8ZZzohFrQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35900 | N | N | 10 | GROUND FLOOR |  | 124475 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1422.4 | LABOR- SUBCONTRACTOR
%R | 500709 | 6359 | 124480 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 392 | 0 | 144 | 0 | 883.2 | 883.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-09 08:00 | 2014-04-29 17:00 |  | 2014-02-10 08:00 | 2014-03-03 17:00 | 2014-02-10 08:00 | 2014-03-03 17:00 | 2014-02-10 08:00 | 2014-03-03 17:00 | 2014-04-09 08:00 | 2014-04-29 17:00 |  | PT_Normal |  |  |  |  | L5FKW+VXR0+tUSvxMhr7eA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35940 | N | N | 10 | GROUND FLOOR |  | 124479 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 883.2 | LABOR- SUBCONTRACTOR
%R | 500710 | 6359 | 124480 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4PLGF4310 | Installation of Drainage pipes &testing | 8178 | 416 | 72 | 144 | 0 | 331.2 | 331.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-13 08:00 | 2014-05-03 17:00 |  | 2014-02-10 08:00 | 2014-03-03 17:00 | 2014-02-10 08:00 | 2014-03-03 17:00 | 2014-02-10 08:00 | 2014-03-03 17:00 | 2014-04-13 08:00 | 2014-05-03 17:00 |  | PT_Normal |  |  |  |  | PYRWbvDyQ7GbJQSfaNDmvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35940 | N | N | 10 | GROUND FLOOR |  | 124479 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 331.2 | LABOR- SUBCONTRACTOR
%R | 500711 | 6359 | 124480 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4PLGF4315 | Sanitary Fittings & Accessories | 8178 | 648 | 0 | 160 | 0 | 201.6 | 201.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-09 17:00 |  | 2014-05-12 08:00 | 2014-06-03 17:00 | 2014-05-12 08:00 | 2014-06-03 17:00 | 2014-05-12 08:00 | 2014-06-03 17:00 | 2014-08-18 08:00 | 2014-09-09 17:00 |  | PT_Normal |  |  |  |  | Fy9uXvGbS2ygD40YzV9h6w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35940 | N | N | 10 | GROUND FLOOR |  | 124479 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 201.6 | LABOR- SUBCONTRACTOR
%R | 500712 | 6359 | 124480 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4PLGF4320 | Installation of Water Heater | 8178 | 648 | 80 | 120 | 0 | 201.6 | 201.6 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-15 17:00 |  | 2014-05-24 08:00 | 2014-06-09 17:00 | 2014-05-24 08:00 | 2014-06-09 17:00 | 2014-05-24 08:00 | 2014-06-09 17:00 | 2014-08-30 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | M6PZASfUS72pHWFzPPoJiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35940 | N | N | 10 | GROUND FLOOR |  | 124479 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 201.6 | LABOR- SUBCONTRACTOR
%R | 500713 | 6359 | 124480 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 88 | 0 | 160 | 0 | 110.4 | 110.4 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-07 08:00 | 2013-11-30 17:00 |  | 2013-10-26 08:00 | 2013-11-17 17:00 | 2013-10-26 08:00 | 2013-11-17 17:00 | 2013-10-26 08:00 | 2013-11-17 17:00 | 2013-11-07 08:00 | 2013-11-30 17:00 |  | PT_Normal |  |  |  |  | rnYYDnC3TcOngOj+uipEUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35940 | N | N | 10 | GROUND FLOOR |  | 124479 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 110.4 | LABOR- SUBCONTRACTOR
%R | 500714 | 6359 | 124481 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 24 | 0 | 144 | 0 | 883.2 | 883.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-29 08:00 | 2014-04-17 17:00 |  | 2014-03-25 08:00 | 2014-04-14 17:00 | 2014-03-25 08:00 | 2014-04-14 17:00 | 2014-03-25 08:00 | 2014-04-14 17:00 | 2014-03-29 08:00 | 2014-04-17 17:00 |  | PT_Normal |  |  |  |  | evo8mg6qQyuJk2APrwT1bQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35950 | N | N | 15 | FIRST FLOORS |  | 124479 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 883.2 | LABOR- SUBCONTRACTOR
%R | 500715 | 6359 | 124481 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4PLFF4330 | Installation of Drainage pipes & testing | 8178 | 240 | 56 | 144 | 0 | 331.2 | 331.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-19 17:00 |  | 2014-03-25 08:00 | 2014-04-14 17:00 | 2014-03-25 08:00 | 2014-04-14 17:00 | 2014-03-25 08:00 | 2014-04-14 17:00 | 2014-04-29 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | 60hE6zL+RdGmDoExwMui5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35950 | N | N | 15 | FIRST FLOORS |  | 124479 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 331.2 | LABOR- SUBCONTRACTOR
%R | 500716 | 6359 | 124481 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4PLFF4335 | Sanitary Fittings & Accessories | 8178 | 152 | 0 | 160 | 0 | 201.6 | 201.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-28 08:00 | 2014-08-23 17:00 |  | 2014-07-06 08:00 | 2014-07-28 17:00 | 2014-07-06 08:00 | 2014-07-28 17:00 | 2014-07-06 08:00 | 2014-07-28 17:00 | 2014-07-28 08:00 | 2014-08-23 17:00 |  | PT_Normal |  |  |  |  | mTK2YmJTS7iveCvOv5Qniw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35950 | N | N | 15 | FIRST FLOORS |  | 124479 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 201.6 | LABOR- SUBCONTRACTOR
%R | 500717 | 6359 | 124481 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4PLFF4340 | Installation of Water Heater | 8178 | 152 | 0 | 120 | 0 | 134.4 | 134.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-08-28 17:00 |  | 2014-07-17 08:00 | 2014-08-06 17:00 | 2014-07-17 08:00 | 2014-08-06 17:00 | 2014-07-17 08:00 | 2014-08-06 17:00 | 2014-08-12 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | RdM7CvCOQr6IduTBd0h4xw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35950 | N | N | 15 | FIRST FLOORS |  | 124479 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 500718 | 6359 | 124482 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 688 | 56 | 112 | 0 | 288 | 288 | 112 | 0 | 0 | 0 |  |  |  | 2014-07-30 08:00 | 2014-08-18 17:00 |  | 2014-04-21 08:00 | 2014-05-06 17:00 | 2014-04-21 08:00 | 2014-05-06 17:00 | 2014-04-21 08:00 | 2014-05-06 17:00 | 2014-07-30 08:00 | 2014-08-18 17:00 |  | PT_Normal |  |  |  |  | yy5PLHYnRsaOvaHfrOZodw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35960 | N | N | 20 | ROOF |  | 124479 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 288 | LABOR- SUBCONTRACTOR
%R | 500719 | 6359 | 124482 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4PLRF4350 | Installation of Rain water Pipes |  | 632 | 80 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-08-28 17:00 |  | 2014-05-08 08:00 | 2014-05-25 17:00 | 2014-05-08 08:00 | 2014-05-25 17:00 | 2014-05-08 08:00 | 2014-05-25 17:00 | 2014-08-12 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | YEnUdpQPSC2p6PQN+oiD0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 35960 | N | N | 20 | ROOF |  | 124479 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 0 | 0
%R | 500720 | 6359 | 124482 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 152 | 0 | 200 | 0 | 672 | 672 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-07-23 08:00 | 2014-08-24 17:00 | 2014-07-23 08:00 | 2014-08-24 17:00 | 2014-07-23 08:00 | 2014-08-24 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | /vnAQKHbRUCp5lcP1L7bvg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35960 | N | N | 20 | ROOF |  | 124479 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 336 | LABOR- SUBCONTRACTOR
%R | 500721 | 6359 | 124484 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ACRF4630 | Installation of Refrigerant Pipes | 8178 | 696 | 0 | 200 | 0 | 795.2 | 795.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-09-09 17:00 |  | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-08-12 08:00 | 2014-09-09 17:00 |  | PT_Normal |  |  |  |  | JpyGDlP4RFadkMCvTZIGOg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36000 | N | N | 20 | ROOF |  | 124483 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 795.2 | LABOR- SUBCONTRACTOR
%R | 500722 | 6359 | 124484 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ACRF4635 | Installation of Condensing Unit | 8178 | 176 | 0 | 200 | 0 | 1136 | 1136 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-07-20 08:00 | 2014-08-20 17:00 | 2014-07-20 08:00 | 2014-08-20 17:00 | 2014-07-20 08:00 | 2014-08-20 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | Ma6ZM8qnQlWfM+/wLzLwSg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36000 | N | N | 20 | ROOF |  | 124483 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 568 | LABOR- SUBCONTRACTOR
%R | 500723 | 6359 | 124485 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ACFF4615 | Installation AC Pipes | 8178 | 368 | 24 | 160 | 0 | 1886.4 | 1886.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-10 08:00 | 2014-07-02 17:00 |  | 2014-04-17 08:00 | 2014-05-10 17:00 | 2014-04-17 08:00 | 2014-05-10 17:00 | 2014-04-17 08:00 | 2014-05-10 17:00 | 2014-06-10 08:00 | 2014-07-02 17:00 |  | PT_Normal |  |  |  |  | JOXoh8fMQueNW+5JNdlvBQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35990 | N | N | 15 | FIRST FLOORS |  | 124483 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1886.4 | LABOR- SUBCONTRACTOR
%R | 500724 | 6359 | 124485 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ACFF4620 | Fixing of Ventilation Equipments | 8178 | 136 | 0 | 200 | 0 | 182.4 | 182.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-13 08:00 | 2014-08-13 17:00 |  | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 |  | PT_Normal |  |  |  |  | CZxKfMiBQWG5K53wfUJsfg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35990 | N | N | 15 | FIRST FLOORS |  | 124483 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 182.4 | LABOR- SUBCONTRACTOR
%R | 500725 | 6359 | 124485 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ACFF4625 | Fixing of Split AC | 8178 | 136 | 0 | 160 | 0 | 568 | 568 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-06 08:00 | 2014-08-28 17:00 |  | 2014-07-14 08:00 | 2014-08-09 17:00 | 2014-07-14 08:00 | 2014-08-09 17:00 | 2014-07-14 08:00 | 2014-08-09 17:00 | 2014-08-06 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | JpNu8irFRxOrZxnILJCzxA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35990 | N | N | 15 | FIRST FLOORS |  | 124483 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 568 | LABOR- SUBCONTRACTOR
%R | 500726 | 6359 | 124486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ACGF4600 | Installation AC Pipes | 8178 | 640 | 40 | 160 | 0 | 1886.4 | 1886.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-04 08:00 | 2014-06-26 17:00 |  | 2014-03-03 08:00 | 2014-03-25 17:00 | 2014-03-03 08:00 | 2014-03-25 17:00 | 2014-03-03 08:00 | 2014-03-25 17:00 | 2014-06-04 08:00 | 2014-06-26 17:00 |  | PT_Normal |  |  |  |  | Fs2u6CobRpm+/SJVlQf/+Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35980 | N | N | 10 | GROUND FLOOR |  | 124483 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1886.4 | LABOR- SUBCONTRACTOR
%R | 500727 | 6359 | 124486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ACGF4605 | Fixing of Ventilation Equipments | 8178 | 544 | 0 | 200 | 0 | 296 | 296 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-13 08:00 | 2014-08-13 17:00 |  | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 |  | PT_Normal |  |  |  |  | EC+MZQ0+TQ2HqYdtrri4VQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35980 | N | N | 10 | GROUND FLOOR |  | 124483 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 296 | LABOR- SUBCONTRACTOR
%R | 500728 | 6359 | 124486 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ACGF4610 | Fixing of Split AC | 8178 | 544 | 40 | 160 | 0 | 568 | 568 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-06 08:00 | 2014-08-28 17:00 |  | 2014-05-15 08:00 | 2014-06-07 17:00 | 2014-05-15 08:00 | 2014-06-07 17:00 | 2014-05-15 08:00 | 2014-06-07 17:00 | 2014-08-06 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | lrCBeZ8yTbqeqU9guHeLLw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35980 | N | N | 10 | GROUND FLOOR |  | 124483 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 568 | LABOR- SUBCONTRACTOR
%R | 500729 | 6359 | 124487 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 24 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-09-13 08:00 | 2014-10-13 17:00 | 2014-09-13 08:00 | 2014-10-13 17:00 | 2014-09-13 08:00 | 2014-10-13 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | KU59Ek27ROmjWBjlQJ1lkw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36070 | N | N | 30 | TESTING AND COMMISSIONING |  | 124453 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 500730 | 6359 | 124487 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 24 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-09-13 08:00 | 2014-10-13 17:00 | 2014-09-13 08:00 | 2014-10-13 17:00 | 2014-09-13 08:00 | 2014-10-13 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | YoSwdpzUQB+hutgD1j0UmA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36070 | N | N | 30 | TESTING AND COMMISSIONING |  | 124453 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 750 | LABOR- SUBCONTRACTOR
%R | 500731 | 6359 | 124487 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ4ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 24 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-09-13 08:00 | 2014-10-13 17:00 | 2014-09-13 08:00 | 2014-10-13 17:00 | 2014-09-13 08:00 | 2014-10-13 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | X3Acw1ynQ7i2vgJ1n3L3Bg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36070 | N | N | 30 | TESTING AND COMMISSIONING |  | 124453 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 500732 | 6359 | 124490 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6SLEX5105 | Laying of Grass/ green area | 8178 | 552 | 0 | 200 | 0 | 6860 | 6860 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-04 08:00 | 2014-11-03 17:00 |  | 2014-07-12 08:00 | 2014-08-12 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 | 2014-10-04 08:00 | 2014-11-03 17:00 |  | PT_Normal |  |  |  |  | 6sycooSoTFeYnCf5due1VA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36780 | N | N | 25 | SOFT LANDSCAPING |  | 124489 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 3430 | LABOR- SUBCONTRACTOR
%R | 500733 | 6359 | 124490 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6SLEX5110 | Laying of Palm tree | 8178 | 552 | 528 | 200 | 0 | 420 | 420 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-07-23 08:00 | 2014-08-24 17:00 | 2014-07-23 08:00 | 2014-08-24 17:00 | 2014-07-23 08:00 | 2014-08-24 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | lASWNER2QgC0MdBimeAnpw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36780 | N | N | 25 | SOFT LANDSCAPING |  | 124489 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 210 | LABOR- SUBCONTRACTOR
%R | 500734 | 6359 | 124491 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6HDEX5090 | kerb works | 8173 | 552 | 0 | 160 | 0 | 890 | 890 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-26 08:00 | 2014-09-17 17:00 |  | 2014-06-03 08:00 | 2014-06-25 17:00 | 2014-06-03 08:00 | 2014-06-25 17:00 | 2014-06-03 08:00 | 2014-06-25 17:00 | 2014-08-26 08:00 | 2014-09-17 17:00 |  | PT_Normal |  |  |  |  | ar7o27/kSNuBU7VvWZJHaA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36770 | N | N | 20 | HARD LANDSCAPING |  | 124489 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 890 | KERBSTONE MASON SK
%R | 500735 | 6359 | 124491 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6HDEX5095 | Cobble Stone Works | 8170 | 552 | 0 | 160 | 0 | 570 | 570 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-07 08:00 | 2014-09-29 17:00 |  | 2014-06-15 08:00 | 2014-07-07 17:00 | 2014-06-15 08:00 | 2014-07-07 17:00 | 2014-06-15 08:00 | 2014-07-07 17:00 | 2014-09-07 08:00 | 2014-09-29 17:00 |  | PT_Normal |  |  |  |  | JxBJc5YIQR2sLLkUWpQ8hg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36770 | N | N | 20 | HARD LANDSCAPING |  | 124489 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 570 | TILE MASON SK
%R | 500736 | 6359 | 124491 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6HDEX5100 | Interlock works | 8174 | 552 | 0 | 160 | 0 | 510 | 510 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-22 08:00 | 2014-10-16 17:00 |  | 2014-06-30 08:00 | 2014-07-22 17:00 | 2014-06-30 08:00 | 2014-07-22 17:00 | 2014-06-30 08:00 | 2014-07-22 17:00 | 2014-09-22 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | L5QiCzAES1S/4cyrzV7r1w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36770 | N | N | 20 | HARD LANDSCAPING |  | 124489 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 510 | INTERLOCK MASON SK
%R | 500737 | 6359 | 124492 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6WEEX5030 | Excavation | 8177 | 408 | 0 | 160 | 0 | 140 | 140 | 160 | 80 | 0 | 80 |  |  |  | 2014-08-09 08:00 | 2014-08-31 17:00 |  | 2014-06-07 08:00 | 2014-06-29 17:00 | 2014-06-07 08:00 | 2014-06-29 17:00 | 2014-06-07 08:00 | 2014-06-29 17:00 | 2014-08-09 08:00 | 2014-08-31 17:00 |  | PT_Normal |  |  |  |  | 3TXF/rjsQJq8mXmdxN+E6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36760 | N | N | 15 | WATER TANK ENCLOSURE |  | 124489 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 140 | LABOR - CIVIL
%R | 500738 | 6359 | 124492 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6WEEX5035 | Construction of Raft | 8165 | 408 | 0 | 200 | 0 | 2030 | 2030 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-20 08:00 | 2014-09-17 17:00 |  | 2014-06-18 08:00 | 2014-07-16 17:00 | 2014-06-18 08:00 | 2014-07-16 17:00 | 2014-06-18 08:00 | 2014-07-16 17:00 | 2014-08-20 08:00 | 2014-09-17 17:00 |  | PT_Normal |  |  |  |  | /BsjLDz8RWatzNDVaJ7I1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36760 | N | N | 15 | WATER TANK ENCLOSURE |  | 124489 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 2030 | STEEL FIXERS SK
%R | 500739 | 6359 | 124492 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6WEEX5040 | Block works & Plastering | 8168 | 408 | 0 | 200 | 0 | 1110 | 1110 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-27 17:00 |  | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-08-30 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | s4JhbAZmTymKvsr4Terqyg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36760 | N | N | 15 | WATER TANK ENCLOSURE |  | 124489 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1110 | BLOCK MASON SK
%R | 500740 | 6359 | 124492 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6WEEX5045 | Flooring & Painting | 8178 | 408 | 0 | 200 | 0 | 510 | 510 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-10-08 17:00 |  | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-09-10 08:00 | 2014-10-08 17:00 |  | PT_Normal |  |  |  |  | 3qzlmTpDSLOIYO4IX/OGVw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36760 | N | N | 15 | WATER TANK ENCLOSURE |  | 124489 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 255 | LABOR- SUBCONTRACTOR
%R | 500741 | 6359 | 124492 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6WEEX5050 | Installation of Steel Gate | 8178 | 408 | 0 | 160 | 0 | 140 | 140 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-28 08:00 | 2014-10-22 17:00 |  | 2014-07-27 08:00 | 2014-08-21 17:00 | 2014-07-27 08:00 | 2014-08-21 17:00 | 2014-07-27 08:00 | 2014-08-21 17:00 | 2014-09-28 08:00 | 2014-10-22 17:00 |  | PT_Normal |  |  |  |  | LEBFu1GmQy2+ESMx+j3ZKw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36760 | N | N | 15 | WATER TANK ENCLOSURE |  | 124489 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 140 | LABOR- SUBCONTRACTOR
%R | 500742 | 6359 | 124492 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 408 | 0 | 200 | 0 | 770 | 770 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-04 08:00 | 2014-11-03 17:00 |  | 2014-08-05 08:00 | 2014-09-02 17:00 | 2014-08-05 08:00 | 2014-09-02 17:00 | 2014-08-05 08:00 | 2014-09-02 17:00 | 2014-10-04 08:00 | 2014-11-03 17:00 |  | PT_Normal |  |  |  |  | q7IoejUhTZ23U/yzzbTE4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36760 | N | N | 15 | WATER TANK ENCLOSURE |  | 124489 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 770 | LABOR- SUBCONTRACTOR
%R | 500743 | 6359 | 124492 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 408 | 256 | 200 | 0 | 478 | 478 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | 20OJY2NVRLeYep0IB1wBcQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36760 | N | N | 15 | WATER TANK ENCLOSURE |  | 124489 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 478 | LABOR- SUBCONTRACTOR
%R | 500744 | 6359 | 124493 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 200 | 200 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-16 08:00 | 2014-12-14 17:00 |  | 2014-10-18 08:00 | 2014-11-15 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 | 2014-11-16 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | twbjeRMdQUOgMwPgegdpVw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36750 | N | N | 10 | MISCELLANEOUS |  | 124489 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 400 | LABOR- SUBCONTRACTOR
%R | 500745 | 6359 | 124493 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6MSEX5020 | Construction Entrance Ramp | 8164 | 552 | 0 | 200 | 0 | 1610 | 1610 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-26 08:00 | 2014-08-26 17:00 |  | 2014-05-06 08:00 | 2014-06-03 17:00 | 2014-05-06 08:00 | 2014-06-03 17:00 | 2014-05-06 08:00 | 2014-06-03 17:00 | 2014-07-26 08:00 | 2014-08-26 17:00 |  | PT_Normal |  |  |  |  | WMYI7WpvTou5CIW9lflY1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36750 | N | N | 10 | MISCELLANEOUS |  | 124489 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1610 | SCREED MASON SK
%R | 500746 | 6359 | 124493 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6MSEX5025 | SS.Handrails and Balustrades | 8178 | 552 | 0 | 160 | 0 | 500 | 500 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-09 17:00 |  | 2014-05-26 08:00 | 2014-06-17 17:00 | 2014-05-26 08:00 | 2014-06-17 17:00 | 2014-05-26 08:00 | 2014-06-17 17:00 | 2014-08-18 08:00 | 2014-09-09 17:00 |  | PT_Normal |  |  |  |  | KRJzbA7dRLi5EkoSmxfYvA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36750 | N | N | 10 | MISCELLANEOUS |  | 124489 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 500 | LABOR- SUBCONTRACTOR
%R | 500747 | 6359 | 124493 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6MSEX5015 | Construction of grease Trap | 8178 | 304 | 0 | 160 | 0 | 110 | 110 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-26 08:00 | 2014-08-20 17:00 |  | 2014-06-11 08:00 | 2014-07-03 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 | 2014-07-26 08:00 | 2014-08-20 17:00 |  | PT_Normal |  |  |  |  | NTWPFb3BSquNmSq2E+Zpxg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36750 | N | N | 10 | MISCELLANEOUS |  | 124489 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 110 | LABOR- SUBCONTRACTOR
%R | 500748 | 6359 | 124493 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6MSEX5000 | Construction of Manholes | 8172 | 304 | 0 | 200 | 0 | 1100 | 1100 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-22 08:00 | 2014-07-20 17:00 |  | 2014-05-08 08:00 | 2014-06-05 17:00 | 2014-05-08 08:00 | 2014-06-05 17:00 | 2014-05-08 08:00 | 2014-06-05 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 |  | PT_Normal |  |  |  |  | v3e1HAlMRsW7K/9YKqYROQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36750 | N | N | 10 | MISCELLANEOUS |  | 124489 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1100 | MANHOLES SK
%R | 500749 | 6359 | 124493 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6MSEX5005 | Construction of Soak pit, Chambers | 8172 | 304 | 0 | 200 | 0 | 220 | 220 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-06 08:00 | 2014-08-06 17:00 |  | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-07-06 08:00 | 2014-08-06 17:00 |  | PT_Normal |  |  |  |  | J2/RbfLoSqSIhDIRtWzSgw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36750 | N | N | 10 | MISCELLANEOUS |  | 124489 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 220 | MANHOLES SK
%R | 500750 | 6359 | 124493 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6MSEX5010 | Telephone cable laying | 8177 | 304 | 104 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-21 08:00 | 2014-09-18 17:00 |  | 2014-07-05 08:00 | 2014-08-05 17:00 | 2014-07-05 08:00 | 2014-08-05 17:00 | 2014-07-05 08:00 | 2014-08-05 17:00 | 2014-08-21 08:00 | 2014-09-18 17:00 |  | PT_Normal |  |  |  |  | xX87zBZOQIu9kajw3Gmp1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36750 | N | N | 10 | MISCELLANEOUS |  | 124489 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 250 | LABOR - CIVIL
%R | 500751 | 6359 | 124496 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6AREL3665 | External Plastering | 8169 | 608 | 0 | 200 | 0 | 15250 | 15250 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | P04040O6S8Oek+HMhkqyog |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36590 | N | N | 15 | ELEVATION |  | 124495 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 15250 | PLASTER MASON SK
%R | 500752 | 6359 | 124496 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6AREL3670 | External stone cladding works | 8170 | 608 | 0 | 160 | 0 | 1170 | 1170 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-04 08:00 | 2014-10-28 17:00 |  | 2014-07-03 08:00 | 2014-07-26 17:00 | 2014-07-03 08:00 | 2014-07-26 17:00 | 2014-07-03 08:00 | 2014-07-26 17:00 | 2014-10-04 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | rgRtSrxfRKWbIyrUVBcbHg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36590 | N | N | 15 | ELEVATION |  | 124495 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1170 | TILE MASON SK
%R | 500753 | 6359 | 124496 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6AREL3680 | External Painting | 8178 | 608 | 584 | 160 | 0 | 5280 | 5280 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-23 08:00 | 2014-11-15 17:00 |  | 2014-07-21 08:00 | 2014-08-16 17:00 | 2014-07-21 08:00 | 2014-08-16 17:00 | 2014-07-21 08:00 | 2014-08-16 17:00 | 2014-10-23 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | P6KUlyDSRtaKWiG3FNHmFg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36590 | N | N | 15 | ELEVATION |  | 124495 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 5280 | LABOR- SUBCONTRACTOR
%R | 500754 | 6359 | 124496 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6AREL3675 | GRC works | 8178 | 608 | 0 | 160 | 0 | 550 | 550 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-12 08:00 | 2014-11-03 17:00 |  | 2014-07-09 08:00 | 2014-07-31 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 | 2014-10-12 08:00 | 2014-11-03 17:00 |  | PT_Normal |  |  |  |  | k2actkP0RISv/O9S79egYA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36590 | N | N | 15 | ELEVATION |  | 124495 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 550 | LABOR- SUBCONTRACTOR
%R | 500755 | 6359 | 124497 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARRF3630 | Leveling Screed for Waterproofing | 8164 | 624 | 0 | 200 | 0 | 887.5 | 887.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-03 08:00 | 2014-10-01 17:00 |  | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-09-03 08:00 | 2014-10-01 17:00 |  | PT_Normal |  |  |  |  | uS4D4bQyQVmgyRz75o87iQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36580 | N | N | 10 | ROOF |  | 124495 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 887.5 | SCREED MASON SK
%R | 500756 | 6359 | 124497 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARRF3635 | Laying of Waterproofing Membrane | 8178 | 624 | 0 | 200 | 0 | 1232 | 1232 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-07 08:00 | 2014-10-05 17:00 |  | 2014-06-04 08:00 | 2014-07-02 17:00 | 2014-06-04 08:00 | 2014-07-02 17:00 | 2014-06-04 08:00 | 2014-07-02 17:00 | 2014-09-07 08:00 | 2014-10-05 17:00 |  | PT_Normal |  |  |  |  | kSygxe99RbC+pMcwVBTcQw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36580 | N | N | 10 | ROOF |  | 124495 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1232 | LABOR- SUBCONTRACTOR
%R | 500757 | 6359 | 124497 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARRF3640 | Installation of Insulation & Protection | 8178 | 624 | 0 | 200 | 0 | 1562 | 1562 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-11 08:00 | 2014-10-12 17:00 |  | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-09-11 08:00 | 2014-10-12 17:00 |  | PT_Normal |  |  |  |  | nI91lr4sQ7OcXdFXulU4CQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36580 | N | N | 10 | ROOF |  | 124495 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1562 | LABOR- SUBCONTRACTOR
%R | 500758 | 6359 | 124497 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 624 | 0 | 200 | 0 | 781 | 781 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | 6TgfLoz2SgarIhB9S6XkkA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36580 | N | N | 10 | ROOF |  | 124495 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 781 | TILE MASON SK
%R | 500759 | 6359 | 124497 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 624 | 0 | 160 | 0 | 770 | 770 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-12 08:00 | 2014-11-03 17:00 |  | 2014-07-07 08:00 | 2014-07-29 17:00 | 2014-07-07 08:00 | 2014-07-29 17:00 | 2014-07-07 08:00 | 2014-07-29 17:00 | 2014-10-12 08:00 | 2014-11-03 17:00 |  | PT_Normal |  |  |  |  | wDMEaQOcSgif1C+O8HvSBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36580 | N | N | 10 | ROOF |  | 124495 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 770 | LABOR- SUBCONTRACTOR
%R | 500760 | 6359 | 124497 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 624 | 0 | 200 | 0 | 1074.5 | 1074.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-24 08:00 | 2014-10-25 17:00 |  | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-09-24 08:00 | 2014-10-25 17:00 |  | PT_Normal |  |  |  |  | VI8ltcoNQHGeldj2VIG9gg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36580 | N | N | 10 | ROOF |  | 124495 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1074.5 | LABOR- SUBCONTRACTOR
%R | 500761 | 6359 | 124497 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARRF3660 | Installation of Access Ladder | 8178 | 624 | 600 | 120 | 0 | 440 | 440 | 120 | 0 | 0 | 0 |  |  |  | 2014-10-29 08:00 | 2014-11-15 17:00 |  | 2014-07-24 08:00 | 2014-08-13 17:00 | 2014-07-24 08:00 | 2014-08-13 17:00 | 2014-07-24 08:00 | 2014-08-13 17:00 | 2014-10-29 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | fsSlF0KqQDi9eA8vE81qpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36580 | N | N | 10 | ROOF |  | 124495 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 440 | LABOR- SUBCONTRACTOR
%R | 500762 | 6359 | 124499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARFF3300 | Block work | 8168 | 24 | 0 | 200 | 0 | 9175 | 9175 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-08 08:00 | 2014-06-05 17:00 |  | 2014-05-05 08:00 | 2014-06-02 17:00 | 2014-05-05 08:00 | 2014-06-02 17:00 | 2014-05-05 08:00 | 2014-06-02 17:00 | 2014-05-08 08:00 | 2014-06-05 17:00 |  | PT_Normal |  |  |  |  | 4oXuaFL/TIen9K7ONEVrBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36550 | N | N | 15 | FIRST FLOORS |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 9175 | BLOCK MASON SK
%R | 500763 | 6359 | 124499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARFF3305 | Plastering work | 8169 | 24 | 0 | 200 | 0 | 9399 | 9399 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-04 08:00 | 2014-07-02 17:00 |  | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-04 08:00 | 2014-07-02 17:00 |  | PT_Normal |  |  |  |  | he5nGnHLQhmNtTugnJvUAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36550 | N | N | 15 | FIRST FLOORS |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 9399 | PLASTER MASON SK
%R | 500764 | 6359 | 124499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARFF3310 | Flooring screed | 8164 | 160 | 136 | 168 | 0 | 1352 | 1352 | 168 | 0 | 0 | 0 |  |  |  | 2014-07-02 08:00 | 2014-07-26 17:00 |  | 2014-06-09 08:00 | 2014-07-02 17:00 | 2014-06-09 08:00 | 2014-07-02 17:00 | 2014-06-09 08:00 | 2014-07-02 17:00 | 2014-07-02 08:00 | 2014-07-26 17:00 |  | PT_Normal |  |  |  |  | YQxCDwc8TRGCI8lAJRF0Aw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36550 | N | N | 15 | FIRST FLOORS |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1352 | SCREED MASON SK
%R | 500765 | 6359 | 124499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARFF3315 | Wet area waterproofing | 8178 | 24 | 0 | 120 | 0 | 1716 | 1716 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-25 08:00 | 2014-07-12 17:00 |  | 2014-06-22 08:00 | 2014-07-08 17:00 | 2014-06-22 08:00 | 2014-07-08 17:00 | 2014-06-22 08:00 | 2014-07-08 17:00 | 2014-06-25 08:00 | 2014-07-12 17:00 |  | PT_Normal |  |  |  |  | 2nHwKrs8RkmYYNBcvhKF/Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36550 | N | N | 15 | FIRST FLOORS |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1716 | LABOR- SUBCONTRACTOR
%R | 500766 | 6359 | 124499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARFF3330 | Paint First coat | 8178 | 232 | 208 | 200 | 0 | 6570.3 | 6570.3 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-21 08:00 | 2014-08-21 17:00 |  | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-07-21 08:00 | 2014-08-21 17:00 |  | PT_Normal |  |  |  |  | JjsGcYa7TKKBPRigf5Gwqw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36550 | N | N | 15 | FIRST FLOORS |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 6570.3 | LABOR- SUBCONTRACTOR
%R | 500767 | 6359 | 124499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARFF3320 | Ceramic Wall Tiling | 8170 | 24 | 0 | 200 | 0 | 1893.75 | 1893.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-05 08:00 | 2014-08-05 17:00 |  | 2014-07-01 08:00 | 2014-07-29 17:00 | 2014-07-01 08:00 | 2014-07-29 17:00 | 2014-07-01 08:00 | 2014-07-29 17:00 | 2014-07-05 08:00 | 2014-08-05 17:00 |  | PT_Normal |  |  |  |  | Kh5lrFRDQQW1xbWv7sTveQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36550 | N | N | 15 | FIRST FLOORS |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1893.75 | TILE MASON SK
%R | 500768 | 6359 | 124499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARFF3325 | Porcelain Tile flooring | 8170 | 24 | 0 | 200 | 0 | 1675 | 1675 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-14 08:00 | 2014-08-14 17:00 |  | 2014-07-10 08:00 | 2014-08-11 17:00 | 2014-07-10 08:00 | 2014-08-11 17:00 | 2014-07-10 08:00 | 2014-08-11 17:00 | 2014-07-14 08:00 | 2014-08-14 17:00 |  | PT_Normal |  |  |  |  | tV/xRh7BTVGhBFq+bBuE0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36550 | N | N | 15 | FIRST FLOORS |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 837.5 | TILE MASON SK
%R | 500769 | 6359 | 124499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARFF3335 | Slate Tile Flooring & Skirting | 8170 | 176 | 152 | 120 | 0 | 1162.5 | 1162.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-26 08:00 | 2014-09-11 17:00 |  | 2014-07-28 08:00 | 2014-08-17 17:00 | 2014-07-28 08:00 | 2014-08-17 17:00 | 2014-07-28 08:00 | 2014-08-17 17:00 | 2014-08-26 08:00 | 2014-09-11 17:00 |  | PT_Normal |  |  |  |  | p9dkFdIZTLuJNo0+jrOa7Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36550 | N | N | 15 | FIRST FLOORS |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1162.5 | TILE MASON SK
%R | 500770 | 6359 | 124499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARFF3350 | Granite - Stair case flooring & Skirting | 8171 | 112 | 88 | 160 | 0 | 1062.5 | 1062.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-20 08:00 | 2014-09-11 17:00 |  | 2014-07-31 08:00 | 2014-08-26 17:00 | 2014-07-31 08:00 | 2014-08-26 17:00 | 2014-07-31 08:00 | 2014-08-26 17:00 | 2014-08-20 08:00 | 2014-09-11 17:00 |  | PT_Normal |  |  |  |  | N36O9JsyQ3y9UHd6QdLzQw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36550 | N | N | 15 | FIRST FLOORS |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1062.5 | GRANITE MASON SK
%R | 500771 | 6359 | 124499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARFF3345 | Fixing of Suspension systems | 8178 | 24 | 0 | 160 | 0 | 1487.5 | 1487.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-07 08:00 | 2014-08-30 17:00 |  | 2014-07-31 08:00 | 2014-08-26 17:00 | 2014-07-31 08:00 | 2014-08-26 17:00 | 2014-07-31 08:00 | 2014-08-26 17:00 | 2014-08-07 08:00 | 2014-08-30 17:00 |  | PT_Normal |  |  |  |  | uTPRuuUvT2yymsL1N+OVKQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36550 | N | N | 15 | FIRST FLOORS |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1487.5 | LABOR- SUBCONTRACTOR
%R | 500772 | 6359 | 124499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARFF3360 | Gypsum board false ceiling | 8178 | 24 | 0 | 200 | 0 | 1487.5 | 1487.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-19 08:00 | 2014-09-16 17:00 |  | 2014-08-16 08:00 | 2014-09-13 17:00 | 2014-08-16 08:00 | 2014-09-13 17:00 | 2014-08-16 08:00 | 2014-09-13 17:00 | 2014-08-19 08:00 | 2014-09-16 17:00 |  | PT_Normal |  |  |  |  | RxztjDUbTyKxmN1EpNvOBA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36550 | N | N | 15 | FIRST FLOORS |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1487.5 | LABOR- SUBCONTRACTOR
%R | 500773 | 6359 | 124499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARFF3365 | Wooden door | 8178 | 24 | 0 | 120 | 0 | 220 | 220 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-03 08:00 | 2014-09-20 17:00 |  | 2014-08-31 08:00 | 2014-09-16 17:00 | 2014-08-31 08:00 | 2014-09-16 17:00 | 2014-08-31 08:00 | 2014-09-16 17:00 | 2014-09-03 08:00 | 2014-09-20 17:00 |  | PT_Normal |  |  |  |  | rJXmVarLTnubDzve6Q53fg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36550 | N | N | 15 | FIRST FLOORS |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 220 | LABOR- SUBCONTRACTOR
%R | 500774 | 6359 | 124499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARFF3370 | Aluminum Door | 8178 | 24 | 0 | 160 | 0 | 165 | 165 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-11 08:00 | 2014-10-04 17:00 |  | 2014-09-08 08:00 | 2014-09-30 17:00 | 2014-09-08 08:00 | 2014-09-30 17:00 | 2014-09-08 08:00 | 2014-09-30 17:00 | 2014-09-11 08:00 | 2014-10-04 17:00 |  | PT_Normal |  |  |  |  | yMqtxNkqRDOT6yxeY6jCrw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36550 | N | N | 15 | FIRST FLOORS |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 165 | LABOR- SUBCONTRACTOR
%R | 500775 | 6359 | 124499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARFF3380 | Aluminum windows | 8178 | 128 | 104 | 160 | 0 | 338.25 | 338.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-04 08:00 | 2014-10-28 17:00 |  | 2014-09-15 08:00 | 2014-10-07 17:00 | 2014-09-15 08:00 | 2014-10-07 17:00 | 2014-09-15 08:00 | 2014-10-07 17:00 | 2014-10-04 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | icalPZLiRUSyVwmkcw8LpA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36550 | N | N | 15 | FIRST FLOORS |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 338.25 | LABOR- SUBCONTRACTOR
%R | 500776 | 6359 | 124499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARFF3375 | Carpentry & Joinery Works | 8178 | 24 | 0 | 200 | 0 | 880 | 880 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-20 08:00 | 2014-10-20 17:00 |  | 2014-09-16 08:00 | 2014-10-16 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 | 2014-09-20 08:00 | 2014-10-20 17:00 |  | PT_Normal |  |  |  |  | QKMdzqUgSbuneQkiwRPqew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36550 | N | N | 15 | FIRST FLOORS |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 440 | LABOR- SUBCONTRACTOR
%R | 500777 | 6359 | 124499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARFF3390 | Installation of Granite Counter Top | 8171 | 40 | 16 | 160 | 0 | 137.5 | 137.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-06 08:00 | 2014-10-30 17:00 |  | 2014-09-30 08:00 | 2014-10-25 17:00 | 2014-09-30 08:00 | 2014-10-25 17:00 | 2014-09-30 08:00 | 2014-10-25 17:00 | 2014-10-06 08:00 | 2014-10-30 17:00 |  | PT_Normal |  |  |  |  | zZsLjZjKS12ix2D6m18nWQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36550 | N | N | 15 | FIRST FLOORS |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 137.5 | GRANITE MASON SK
%R | 500778 | 6359 | 124499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARFF3385 | Handrail & Balustrade | 8178 | 24 | 0 | 160 | 0 | 218.75 | 218.75 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-04 08:00 | 2014-10-28 17:00 |  | 2014-09-30 08:00 | 2014-10-25 17:00 | 2014-09-30 08:00 | 2014-10-25 17:00 | 2014-09-30 08:00 | 2014-10-25 17:00 | 2014-10-04 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | DiqyyWPGTTGO46WXiRvwtA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36550 | N | N | 15 | FIRST FLOORS |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 218.75 | LABOR- SUBCONTRACTOR
%R | 500779 | 6359 | 124499 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARFF3395 | Final Painting | 8178 | 24 | 0 | 200 | 0 | 6570.3 | 6570.3 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-10-14 08:00 | 2014-11-11 17:00 | 2014-10-14 08:00 | 2014-11-11 17:00 | 2014-10-14 08:00 | 2014-11-11 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | 1LGZpfW/QsCueRn1D+gtyg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36550 | N | N | 15 | FIRST FLOORS |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 6570.3 | LABOR- SUBCONTRACTOR
%R | 500780 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3030 | Paint First coat | 8178 | 504 | 112 | 200 | 0 | 7419.5 | 7419.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-15 08:00 | 2014-08-16 17:00 |  | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-07-15 08:00 | 2014-08-16 17:00 |  | PT_Normal |  |  |  |  | i6O4I/l8TeSm6MHz2HL6bA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 7419.5 | LABOR- SUBCONTRACTOR
%R | 500781 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3020 | Ceramic Wall Tiling | 8170 | 392 | 0 | 200 | 0 | 4418.75 | 4418.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-06 08:00 | 2014-08-06 17:00 |  | 2014-05-10 08:00 | 2014-06-07 17:00 | 2014-05-10 08:00 | 2014-06-07 17:00 | 2014-05-10 08:00 | 2014-06-07 17:00 | 2014-07-06 08:00 | 2014-08-06 17:00 |  | PT_Normal |  |  |  |  | w0sXyQSDQqGa8o1g/joD4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 4418.75 | TILE MASON SK
%R | 500782 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3025 | Porcelain Tile flooring | 8170 | 392 | 0 | 200 | 0 | 2397.25 | 2397.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-12 08:00 | 2014-08-12 17:00 |  | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 |  | PT_Normal |  |  |  |  | uSbL09eRQz+QGvhT/jv88A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 2397.25 | TILE MASON SK
%R | 500783 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3040 | Cobble Tile flooring | 8170 | 456 | 0 | 120 | 0 | 875 | 875 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-20 08:00 | 2014-09-06 17:00 |  | 2014-06-11 08:00 | 2014-06-28 17:00 | 2014-06-11 08:00 | 2014-06-28 17:00 | 2014-06-11 08:00 | 2014-06-28 17:00 | 2014-08-20 08:00 | 2014-09-06 17:00 |  | PT_Normal |  |  |  |  | D0VnIe2ZR5yos+k90yViaw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 875 | TILE MASON SK
%R | 500784 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 472 | 16 | 120 | 0 | 1162.5 | 1162.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-16 08:00 | 2014-09-01 17:00 |  | 2014-06-04 08:00 | 2014-06-21 17:00 | 2014-06-04 08:00 | 2014-06-21 17:00 | 2014-06-04 08:00 | 2014-06-21 17:00 | 2014-08-16 08:00 | 2014-09-01 17:00 |  | PT_Normal |  |  |  |  | D0Ah2N6mQPKIecdH0ODh7Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1162.5 | TILE MASON SK
%R | 500785 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 456 | 0 | 160 | 0 | 1062.5 | 1062.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-28 08:00 | 2014-09-20 17:00 |  | 2014-06-19 08:00 | 2014-07-12 17:00 | 2014-06-19 08:00 | 2014-07-12 17:00 | 2014-06-19 08:00 | 2014-07-12 17:00 | 2014-08-28 08:00 | 2014-09-20 17:00 |  | PT_Normal |  |  |  |  | edJlNcskSUaiVy605b+drQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1062.5 | GRANITE MASON SK
%R | 500786 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3045 | Fixing of Suspension systems | 8178 | 392 | 0 | 160 | 0 | 1650 | 1650 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-29 08:00 | 2014-08-24 17:00 |  | 2014-06-02 08:00 | 2014-06-24 17:00 | 2014-06-02 08:00 | 2014-06-24 17:00 | 2014-06-02 08:00 | 2014-06-24 17:00 | 2014-07-29 08:00 | 2014-08-24 17:00 |  | PT_Normal |  |  |  |  | ERnuRDOKQNyaUnPL1eKeXQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1650 | LABOR- SUBCONTRACTOR
%R | 500787 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3055 | Aluminum tile false ceiling | 8178 | 416 | 24 | 200 | 0 | 162.5 | 162.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-13 08:00 | 2014-09-10 17:00 |  | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-08-13 08:00 | 2014-09-10 17:00 |  | PT_Normal |  |  |  |  | GJNhEgMCRzGJuY0f/UoexQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 162.5 | LABOR- SUBCONTRACTOR
%R | 500788 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3060 | Gypsum board false ceiling | 8178 | 392 | 0 | 200 | 0 | 1520.5 | 1520.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-13 08:00 | 2014-09-10 17:00 |  | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-08-13 08:00 | 2014-09-10 17:00 |  | PT_Normal |  |  |  |  | SorMXM31Tz21kFOGC4+HfA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1520.5 | LABOR- SUBCONTRACTOR
%R | 500789 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3065 | Wooden door & PVC Door | 8178 | 456 | 0 | 120 | 0 | 825 | 825 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-11 08:00 | 2014-09-28 17:00 |  | 2014-07-03 08:00 | 2014-07-20 17:00 | 2014-07-03 08:00 | 2014-07-20 17:00 | 2014-07-03 08:00 | 2014-07-20 17:00 | 2014-09-11 08:00 | 2014-09-28 17:00 |  | PT_Normal |  |  |  |  | Ji8s9lMtSrWqTLP0VUb9XQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 825 | LABOR- SUBCONTRACTOR
%R | 500790 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3070 | Aluminum doors | 8178 | 456 | 0 | 120 | 0 | 110 | 110 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-17 08:00 | 2014-10-04 17:00 |  | 2014-07-09 08:00 | 2014-07-26 17:00 | 2014-07-09 08:00 | 2014-07-26 17:00 | 2014-07-09 08:00 | 2014-07-26 17:00 | 2014-09-17 08:00 | 2014-10-04 17:00 |  | PT_Normal |  |  |  |  | Hdl7eDZnTWqNlnmfk5+THQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 110 | LABOR- SUBCONTRACTOR
%R | 500791 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3080 | Aluminum windows | 8178 | 536 | 80 | 160 | 0 | 323.5 | 323.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-06 08:00 | 2014-10-30 17:00 |  | 2014-07-16 08:00 | 2014-08-11 17:00 | 2014-07-16 08:00 | 2014-08-11 17:00 | 2014-07-16 08:00 | 2014-08-11 17:00 | 2014-10-06 08:00 | 2014-10-30 17:00 |  | PT_Normal |  |  |  |  | hN+yvTuxSr68HJvQacNRng |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 323.5 | LABOR- SUBCONTRACTOR
%R | 500792 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3075 | Carpentry & Joinery Works | 8178 | 456 | 0 | 160 | 0 | 660 | 660 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-23 08:00 | 2014-10-18 17:00 |  | 2014-07-15 08:00 | 2014-08-10 17:00 | 2014-07-15 08:00 | 2014-08-10 17:00 | 2014-07-15 08:00 | 2014-08-10 17:00 | 2014-09-23 08:00 | 2014-10-18 17:00 |  | PT_Normal |  |  |  |  | yGxIvPsVTKeSrt2tMk3tZQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 660 | LABOR- SUBCONTRACTOR
%R | 500793 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3090 | Installation of Granite Counter Top | 8171 | 456 | 0 | 120 | 0 | 302.5 | 302.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-10-06 08:00 | 2014-10-25 17:00 |  | 2014-07-28 08:00 | 2014-08-17 17:00 | 2014-07-28 08:00 | 2014-08-17 17:00 | 2014-07-28 08:00 | 2014-08-17 17:00 | 2014-10-06 08:00 | 2014-10-25 17:00 |  | PT_Normal |  |  |  |  | hyNQRaOSSnWN5s8OGAIUyA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 302.5 | GRANITE MASON SK
%R | 500794 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3085 | S.S.Balustrade | 8178 | 496 | 40 | 160 | 0 | 218.75 | 218.75 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-07 08:00 | 2014-11-01 17:00 |  | 2014-07-23 08:00 | 2014-08-18 17:00 | 2014-07-23 08:00 | 2014-08-18 17:00 | 2014-07-23 08:00 | 2014-08-18 17:00 | 2014-10-07 08:00 | 2014-11-01 17:00 |  | PT_Normal |  |  |  |  | r0iKME7ORXaJ028qSM3v9g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 218.75 | LABOR- SUBCONTRACTOR
%R | 500795 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3095 | Final Painting | 8178 | 456 | 432 | 200 | 0 | 7419.5 | 7419.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-08-10 08:00 | 2014-09-07 17:00 | 2014-08-10 08:00 | 2014-09-07 17:00 | 2014-08-10 08:00 | 2014-09-07 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | Xng7lHAmQeCnHYFTqqwAaA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 7419.5 | LABOR- SUBCONTRACTOR
%R | 500796 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3000 | Block work | 8168 | 392 | 0 | 200 | 0 | 11578.5 | 11578.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-21 08:00 | 2014-06-18 17:00 |  | 2014-03-25 08:00 | 2014-04-22 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 | 2014-05-21 08:00 | 2014-06-18 17:00 |  | PT_Normal |  |  |  |  | LDsEC7APSJ6saXDvvlTmCg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 11578.5 | BLOCK MASON SK
%R | 500797 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3005 | Plastering work | 8169 | 392 | 0 | 200 | 0 | 14187.5 | 14187.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-07-10 17:00 |  | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 |  | PT_Normal |  |  |  |  | vPqfqucQSxmLRPeMwMMRgA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 14187.5 | PLASTER MASON SK
%R | 500798 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3010 | Flooring screed | 8164 | 456 | 64 | 168 | 0 | 2713.25 | 2713.25 | 168 | 0 | 0 | 0 |  |  |  | 2014-06-30 08:00 | 2014-07-23 17:00 |  | 2014-04-24 08:00 | 2014-05-18 17:00 | 2014-04-24 08:00 | 2014-05-18 17:00 | 2014-04-24 08:00 | 2014-05-18 17:00 | 2014-06-30 08:00 | 2014-07-23 17:00 |  | PT_Normal |  |  |  |  | 9z8TB+mITD+XsIbJlAUN4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 2713.25 | SCREED MASON SK
%R | 500799 | 6359 | 124500 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 392 | 0 | 120 | 0 | 528 | 528 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-30 08:00 | 2014-07-16 17:00 |  | 2014-05-04 08:00 | 2014-05-20 17:00 | 2014-05-04 08:00 | 2014-05-20 17:00 | 2014-05-04 08:00 | 2014-05-20 17:00 | 2014-06-30 08:00 | 2014-07-16 17:00 |  | PT_Normal |  |  |  |  | HDw+PCsjTIawO3D/vQIkKg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36540 | N | N | 10 | GROUND FLOOR |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 528 | LABOR- SUBCONTRACTOR
%R | 500800 | 6359 | 124501 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARRF3600 | Block work | 8168 | 624 | 0 | 160 | 0 | 872.25 | 872.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-24 08:00 | 2014-09-15 17:00 |  | 2014-05-21 08:00 | 2014-06-12 17:00 | 2014-05-21 08:00 | 2014-06-12 17:00 | 2014-05-21 08:00 | 2014-06-12 17:00 | 2014-08-24 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | tVkkKsBFS4adaJi1Aau70Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36560 | N | N | 20 | ROOF |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 872.25 | BLOCK MASON SK
%R | 500801 | 6359 | 124501 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARRF3605 | Plastering work | 8169 | 624 | 0 | 160 | 0 | 4791 | 4791 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-04 08:00 | 2014-09-27 17:00 |  | 2014-06-02 08:00 | 2014-06-24 17:00 | 2014-06-02 08:00 | 2014-06-24 17:00 | 2014-06-02 08:00 | 2014-06-24 17:00 | 2014-09-04 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | N4XbKqo0RvqgThsoR1ASYA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36560 | N | N | 20 | ROOF |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 4791 | PLASTER MASON SK
%R | 500802 | 6359 | 124501 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARRF3610 | Flooring screed | 8164 | 624 | 0 | 120 | 0 | 192.5 | 192.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-22 08:00 | 2014-10-08 17:00 |  | 2014-06-19 08:00 | 2014-07-06 17:00 | 2014-06-19 08:00 | 2014-07-06 17:00 | 2014-06-19 08:00 | 2014-07-06 17:00 | 2014-09-22 08:00 | 2014-10-08 17:00 |  | PT_Normal |  |  |  |  | +5mjbjIOSniw3YJdPcz31g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36560 | N | N | 20 | ROOF |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 192.5 | SCREED MASON SK
%R | 500803 | 6359 | 124501 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARRF3695 | Painting -Storage area | 8178 | 624 | 0 | 160 | 0 | 2050 | 2050 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-04 08:00 | 2014-10-28 17:00 |  | 2014-07-01 08:00 | 2014-07-23 17:00 | 2014-07-01 08:00 | 2014-07-23 17:00 | 2014-07-01 08:00 | 2014-07-23 17:00 | 2014-10-04 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | I/EQpCaCTyuN3Ky0rF5+6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36560 | N | N | 20 | ROOF |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 2050 | LABOR- SUBCONTRACTOR
%R | 500804 | 6359 | 124501 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ARRF3620 | Epoxy Painting -Storage area | 8178 | 624 | 0 | 120 | 0 | 59.5 | 59.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-10-23 08:00 | 2014-11-09 17:00 |  | 2014-07-19 08:00 | 2014-08-07 17:00 | 2014-07-19 08:00 | 2014-08-07 17:00 | 2014-07-19 08:00 | 2014-08-07 17:00 | 2014-10-23 08:00 | 2014-11-09 17:00 |  | PT_Normal |  |  |  |  | W5qNzR8MR8CBYWnUig0mrw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36560 | N | N | 20 | ROOF |  | 124498 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 59.5 | LABOR- SUBCONTRACTOR
%R | 500805 | 6359 | 124504 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ELRF4070 | Installation of Isolator | 8178 | 24 | 0 | 144 | 0 | 1032 | 1032 | 144 | 0 | 0 | 0 |  |  |  | 2014-10-06 08:00 | 2014-10-28 17:00 |  | 2014-10-02 08:00 | 2014-10-25 17:00 | 2014-10-02 08:00 | 2014-10-25 17:00 | 2014-10-02 08:00 | 2014-10-25 17:00 | 2014-10-06 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | TKqj6kO8RhCaMk7oeNjaDQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36640 | N | N | 20 | ROOF |  | 124503 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 1032 | LABOR- SUBCONTRACTOR
%R | 500806 | 6359 | 124504 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ELRF4075 | Installation of TV Dish Antenna | 8178 | 24 | 0 | 184 | 0 | 2288 | 2288 | 184 | 0 | 0 | 0 |  |  |  | 2014-10-20 08:00 | 2014-11-15 17:00 |  | 2014-10-16 08:00 | 2014-11-11 17:00 | 2014-10-16 08:00 | 2014-11-11 17:00 | 2014-10-16 08:00 | 2014-11-11 17:00 | 2014-10-20 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | yHz01kv9Q8iuiByN/D8kWw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36640 | N | N | 20 | ROOF |  | 124503 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 2288 | LABOR- SUBCONTRACTOR
%R | 500807 | 6359 | 124505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 128 | 0 | 200 | 0 | 3224 | 3224 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-29 08:00 | 2014-06-26 17:00 |  | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 |  | PT_Normal |  |  |  |  | iur3/f+XS7aXuaO6ldBa4A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36630 | N | N | 15 | FIRST FLOORS |  | 124503 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 3224 | LABOR- SUBCONTRACTOR
%R | 500808 | 6359 | 124505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ELFF4040 | Cable tray & trunking installation | 8178 | 368 | 0 | 160 | 0 | 3976 | 3976 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-15 08:00 | 2014-08-10 17:00 |  | 2014-05-22 08:00 | 2014-06-14 17:00 | 2014-05-22 08:00 | 2014-06-14 17:00 | 2014-05-22 08:00 | 2014-06-14 17:00 | 2014-07-15 08:00 | 2014-08-10 17:00 |  | PT_Normal |  |  |  |  | q0lBHMimSgWHdup4s8apFg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36630 | N | N | 15 | FIRST FLOORS |  | 124503 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 3976 | LABOR- SUBCONTRACTOR
%R | 500809 | 6359 | 124505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ELFF4045 | Installation of wiring & Main Cabling | 8178 | 368 | 344 | 200 | 0 | 796 | 796 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-23 08:00 | 2014-08-24 17:00 |  | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-07-23 08:00 | 2014-08-24 17:00 |  | PT_Normal |  |  |  |  | ARL3UhaFQrK1DRJ3omRT4A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36630 | N | N | 15 | FIRST FLOORS |  | 124503 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 796 | LABOR- SUBCONTRACTOR
%R | 500810 | 6359 | 124505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 24 | 0 | 160 | 0 | 568 | 568 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-03 08:00 | 2014-09-25 17:00 |  | 2014-08-31 08:00 | 2014-09-22 17:00 | 2014-08-31 08:00 | 2014-09-22 17:00 | 2014-08-31 08:00 | 2014-09-22 17:00 | 2014-09-03 08:00 | 2014-09-25 17:00 |  | PT_Normal |  |  |  |  | OenzEtt+QbiKTjJMMV/d1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36630 | N | N | 15 | FIRST FLOORS |  | 124503 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 568 | LABOR- SUBCONTRACTOR
%R | 500811 | 6359 | 124505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 24 | 0 | 200 | 0 | 4128 | 4128 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-09-13 08:00 | 2014-10-13 17:00 | 2014-09-13 08:00 | 2014-10-13 17:00 | 2014-09-13 08:00 | 2014-10-13 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | zdLgxf96SvGoxG4ouCAO2Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36630 | N | N | 15 | FIRST FLOORS |  | 124503 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 2064 | LABOR- SUBCONTRACTOR
%R | 500812 | 6359 | 124505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 360 | 336 | 200 | 0 | 5712 | 5712 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-08-24 08:00 | 2014-09-21 17:00 | 2014-08-24 08:00 | 2014-09-21 17:00 | 2014-08-24 08:00 | 2014-09-21 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | ZMqeJDP2Syio6JZxUujtIA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36630 | N | N | 15 | FIRST FLOORS |  | 124503 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 5712 | LABOR- SUBCONTRACTOR
%R | 500813 | 6359 | 124505 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ELFF4050 | Installation of Telephone System | 8178 | 200 | 176 | 200 | 0 | 1778 | 1778 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-20 08:00 | 2014-10-20 17:00 |  | 2014-08-21 08:00 | 2014-09-18 17:00 | 2014-08-21 08:00 | 2014-09-18 17:00 | 2014-08-21 08:00 | 2014-09-18 17:00 | 2014-09-20 08:00 | 2014-10-20 17:00 |  | PT_Normal |  |  |  |  | vR74Oy1qRPmlffWsybgkSQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36630 | N | N | 15 | FIRST FLOORS |  | 124503 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1778 | LABOR- SUBCONTRACTOR
%R | 500814 | 6359 | 124506 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 464 | 0 | 200 | 0 | 3224 | 3224 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-07 08:00 | 2014-07-05 17:00 |  | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-06-07 08:00 | 2014-07-05 17:00 |  | PT_Normal |  |  |  |  | 17QMuQ1LSYmrJ2DeN48gag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36620 | N | N | 10 | GROUND FLOOR |  | 124503 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 3224 | LABOR- SUBCONTRACTOR
%R | 500815 | 6359 | 124506 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ELGF4005 | Cable tray & trunking installation | 8178 | 608 | 0 | 160 | 0 | 3976 | 3976 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-09 08:00 | 2014-07-31 17:00 |  | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 |  | PT_Normal |  |  |  |  | xAVbkwAQRxOL9+VAUukyUw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36620 | N | N | 10 | GROUND FLOOR |  | 124503 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 3976 | LABOR- SUBCONTRACTOR
%R | 500816 | 6359 | 124506 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ELGF4010 | Installation of wiring & Main Cabling | 8178 | 608 | 216 | 200 | 0 | 796 | 796 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-17 08:00 | 2014-08-18 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-07-17 08:00 | 2014-08-18 17:00 |  | PT_Normal |  |  |  |  | fW4r78t8QxWFBCHv5y8OHQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36620 | N | N | 10 | GROUND FLOOR |  | 124503 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 796 | LABOR- SUBCONTRACTOR
%R | 500817 | 6359 | 124506 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 392 | 0 | 160 | 0 | 568 | 568 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-27 08:00 | 2014-09-18 17:00 |  | 2014-06-28 08:00 | 2014-07-20 17:00 | 2014-06-28 08:00 | 2014-07-20 17:00 | 2014-06-28 08:00 | 2014-07-20 17:00 | 2014-08-27 08:00 | 2014-09-18 17:00 |  | PT_Normal |  |  |  |  | qsG1JL2OQTuIQaS5x7JThA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36620 | N | N | 10 | GROUND FLOOR |  | 124503 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 568 | LABOR- SUBCONTRACTOR
%R | 500818 | 6359 | 124506 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 408 | 384 | 200 | 0 | 4128 | 4128 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-10-08 17:00 |  | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-09-10 08:00 | 2014-10-08 17:00 |  | PT_Normal |  |  |  |  | IJNDJePZRfim+V2QIMHH0A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36620 | N | N | 10 | GROUND FLOOR |  | 124503 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 2064 | LABOR- SUBCONTRACTOR
%R | 500819 | 6359 | 124506 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 568 | 208 | 200 | 0 | 5712 | 5712 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | myoSAeCiSyKJwTGkW7Nkeg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36620 | N | N | 10 | GROUND FLOOR |  | 124503 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 5712 | LABOR- SUBCONTRACTOR
%R | 500820 | 6359 | 124506 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ELGF4030 | Installation of Telephone System | 8178 | 392 | 192 | 160 | 0 | 1778 | 1778 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-08 08:00 | 2014-09-30 17:00 |  | 2014-07-09 08:00 | 2014-07-31 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 | 2014-09-08 08:00 | 2014-09-30 17:00 |  | PT_Normal |  |  |  |  | LrLVtLLVQhyeaibXIzahPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36620 | N | N | 10 | GROUND FLOOR |  | 124503 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1778 | LABOR- SUBCONTRACTOR
%R | 500821 | 6359 | 124508 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ACFF4615 | Installation AC Pipes | 8178 | 368 | 24 | 160 | 0 | 2358 | 2358 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-11 08:00 | 2014-09-02 17:00 |  | 2014-06-15 08:00 | 2014-07-07 17:00 | 2014-06-15 08:00 | 2014-07-07 17:00 | 2014-06-15 08:00 | 2014-07-07 17:00 | 2014-08-11 08:00 | 2014-09-02 17:00 |  | PT_Normal |  |  |  |  | XQO1veRGTnqt5q+bDiijkQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36710 | N | N | 15 | FIRST FLOORS |  | 124507 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 2358 | LABOR- SUBCONTRACTOR
%R | 500822 | 6359 | 124508 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ACFF4620 | Fixing of Ventilation Equipments | 8178 | 136 | 0 | 200 | 0 | 228 | 228 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-13 08:00 | 2014-10-13 17:00 |  | 2014-08-24 08:00 | 2014-09-21 17:00 | 2014-08-24 08:00 | 2014-09-21 17:00 | 2014-08-24 08:00 | 2014-09-21 17:00 | 2014-09-13 08:00 | 2014-10-13 17:00 |  | PT_Normal |  |  |  |  | MixWYsXDQ866IzhEHkKfjw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36710 | N | N | 15 | FIRST FLOORS |  | 124507 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 228 | LABOR- SUBCONTRACTOR
%R | 500823 | 6359 | 124508 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ACFF4625 | Fixing of Split AC | 8178 | 136 | 0 | 160 | 0 | 710 | 710 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-04 08:00 | 2014-10-28 17:00 |  | 2014-09-14 08:00 | 2014-10-06 17:00 | 2014-09-14 08:00 | 2014-10-06 17:00 | 2014-09-14 08:00 | 2014-10-06 17:00 | 2014-10-04 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | 0wRJhva3Su6O10dMMPASvA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36710 | N | N | 15 | FIRST FLOORS |  | 124507 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 710 | LABOR- SUBCONTRACTOR
%R | 500824 | 6359 | 124509 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ACRF4630 | Installation of Refrigerant Pipes | 8178 | 696 | 520 | 200 | 0 | 994 | 994 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-12 08:00 | 2014-11-09 17:00 |  | 2014-06-26 08:00 | 2014-07-24 17:00 | 2014-06-26 08:00 | 2014-07-24 17:00 | 2014-06-26 08:00 | 2014-07-24 17:00 | 2014-10-12 08:00 | 2014-11-09 17:00 |  | PT_Normal |  |  |  |  | x3YbNHkETlOY5+b4bxoqSg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36720 | N | N | 20 | ROOF |  | 124507 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 994 | LABOR- SUBCONTRACTOR
%R | 500825 | 6359 | 124509 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ACRF4635 | Installation of Condensing Unit | 8178 | 176 | 152 | 200 | 0 | 1420 | 1420 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-09-20 08:00 | 2014-10-20 17:00 | 2014-09-20 08:00 | 2014-10-20 17:00 | 2014-09-20 08:00 | 2014-10-20 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | 4DMFYhxgQ9uaEUp2qopM7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36720 | N | N | 20 | ROOF |  | 124507 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 710 | LABOR- SUBCONTRACTOR
%R | 500826 | 6359 | 124510 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ACGF4600 | Installation AC Pipes | 8178 | 640 | 224 | 160 | 0 | 2358 | 2358 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-05 08:00 | 2014-08-27 17:00 |  | 2014-04-30 08:00 | 2014-05-22 17:00 | 2014-04-30 08:00 | 2014-05-22 17:00 | 2014-04-30 08:00 | 2014-05-22 17:00 | 2014-08-05 08:00 | 2014-08-27 17:00 |  | PT_Normal |  |  |  |  | 7cvrQfaaRj2oCGnyr8s0bQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36700 | N | N | 10 | GROUND FLOOR |  | 124507 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 2358 | LABOR- SUBCONTRACTOR
%R | 500827 | 6359 | 124510 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ACGF4605 | Fixing of Ventilation Equipments | 8178 | 544 | 0 | 200 | 0 | 370 | 370 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-13 08:00 | 2014-10-13 17:00 |  | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 | 2014-09-13 08:00 | 2014-10-13 17:00 |  | PT_Normal |  |  |  |  | Syrq2Fs4Q32IkvYgqyX89Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36700 | N | N | 10 | GROUND FLOOR |  | 124507 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 370 | LABOR- SUBCONTRACTOR
%R | 500828 | 6359 | 124510 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ACGF4610 | Fixing of Split AC | 8178 | 544 | 88 | 160 | 0 | 710 | 710 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-04 08:00 | 2014-10-28 17:00 |  | 2014-07-13 08:00 | 2014-08-07 17:00 | 2014-07-13 08:00 | 2014-08-07 17:00 | 2014-07-13 08:00 | 2014-08-07 17:00 | 2014-10-04 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | 2LYY+VWkRD6vJQyAesGm0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36700 | N | N | 10 | GROUND FLOOR |  | 124507 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 710 | LABOR- SUBCONTRACTOR
%R | 500829 | 6359 | 124512 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 24 | 0 | 144 | 0 | 1104 | 1104 | 144 | 0 | 0 | 0 |  |  |  | 2014-05-26 08:00 | 2014-06-15 17:00 |  | 2014-05-22 08:00 | 2014-06-11 17:00 | 2014-05-22 08:00 | 2014-06-11 17:00 | 2014-05-22 08:00 | 2014-06-11 17:00 | 2014-05-26 08:00 | 2014-06-15 17:00 |  | PT_Normal |  |  |  |  | 3QjcIe1PSVyBEZqU1DNHoA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36670 | N | N | 15 | FIRST FLOORS |  | 124511 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1104 | LABOR- SUBCONTRACTOR
%R | 500830 | 6359 | 124512 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6PLFF4330 | Installation of Drainage pipes & testing | 8178 | 240 | 216 | 144 | 0 | 414 | 414 | 144 | 0 | 0 | 0 |  |  |  | 2014-06-26 08:00 | 2014-07-16 17:00 |  | 2014-05-22 08:00 | 2014-06-11 17:00 | 2014-05-22 08:00 | 2014-06-11 17:00 | 2014-05-22 08:00 | 2014-06-11 17:00 | 2014-06-26 08:00 | 2014-07-16 17:00 |  | PT_Normal |  |  |  |  | cqV9C81+T7SGBvPs8om6ew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36670 | N | N | 15 | FIRST FLOORS |  | 124511 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 414 | LABOR- SUBCONTRACTOR
%R | 500831 | 6359 | 124512 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6PLFF4335 | Sanitary Fittings & Accessories | 8178 | 152 | 0 | 160 | 0 | 252 | 252 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-28 08:00 | 2014-10-22 17:00 |  | 2014-09-06 08:00 | 2014-09-28 17:00 | 2014-09-06 08:00 | 2014-09-28 17:00 | 2014-09-06 08:00 | 2014-09-28 17:00 | 2014-09-28 08:00 | 2014-10-22 17:00 |  | PT_Normal |  |  |  |  | Ts+h+pfpTHS6kzJW8+YyHw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36670 | N | N | 15 | FIRST FLOORS |  | 124511 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 252 | LABOR- SUBCONTRACTOR
%R | 500832 | 6359 | 124512 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6PLFF4340 | Installation of Water Heater | 8178 | 152 | 0 | 120 | 0 | 168 | 168 | 120 | 0 | 0 | 0 |  |  |  | 2014-10-12 08:00 | 2014-10-28 17:00 |  | 2014-09-17 08:00 | 2014-10-04 17:00 | 2014-09-17 08:00 | 2014-10-04 17:00 | 2014-09-17 08:00 | 2014-10-04 17:00 | 2014-10-12 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | FYMMgXNcStaytkfXW0KvjA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36670 | N | N | 15 | FIRST FLOORS |  | 124511 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 168 | LABOR- SUBCONTRACTOR
%R | 500833 | 6359 | 124513 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 88 | 0 | 160 | 0 | 138 | 138 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-06 08:00 | 2014-01-28 17:00 |  | 2013-12-24 08:00 | 2014-01-15 17:00 | 2013-12-24 08:00 | 2014-01-15 17:00 | 2013-12-24 08:00 | 2014-01-15 17:00 | 2014-01-06 08:00 | 2014-01-28 17:00 |  | PT_Normal |  |  |  |  | 0UhiA83IRXK5EsiwzfnZwA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36660 | N | N | 10 | GROUND FLOOR |  | 124511 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 138 | LABOR- SUBCONTRACTOR
%R | 500834 | 6359 | 124513 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 392 | 0 | 144 | 0 | 1104 | 1104 | 144 | 0 | 0 | 0 |  |  |  | 2014-06-07 08:00 | 2014-06-26 17:00 |  | 2014-04-10 08:00 | 2014-04-30 17:00 | 2014-04-10 08:00 | 2014-04-30 17:00 | 2014-04-10 08:00 | 2014-04-30 17:00 | 2014-06-07 08:00 | 2014-06-26 17:00 |  | PT_Normal |  |  |  |  | Vl6a9cLSSpOAwPUMcDuINQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36660 | N | N | 10 | GROUND FLOOR |  | 124511 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1104 | LABOR- SUBCONTRACTOR
%R | 500835 | 6359 | 124513 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6PLGF4310 | Installation of Drainage pipes &testing | 8178 | 416 | 112 | 144 | 0 | 414 | 414 | 144 | 0 | 0 | 0 |  |  |  | 2014-06-10 08:00 | 2014-06-30 17:00 |  | 2014-04-10 08:00 | 2014-04-30 17:00 | 2014-04-10 08:00 | 2014-04-30 17:00 | 2014-04-10 08:00 | 2014-04-30 17:00 | 2014-06-10 08:00 | 2014-06-30 17:00 |  | PT_Normal |  |  |  |  | heLoycgiR0m8XIAhWF94gg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36660 | N | N | 10 | GROUND FLOOR |  | 124511 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 414 | LABOR- SUBCONTRACTOR
%R | 500836 | 6359 | 124513 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6PLGF4315 | Sanitary Fittings & Accessories | 8178 | 648 | 0 | 160 | 0 | 252 | 252 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-09 17:00 |  | 2014-07-09 08:00 | 2014-07-31 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 | 2014-10-18 08:00 | 2014-11-09 17:00 |  | PT_Normal |  |  |  |  | 1MdvtlsXR3qUI6Yu1pF4fw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36660 | N | N | 10 | GROUND FLOOR |  | 124511 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 252 | LABOR- SUBCONTRACTOR
%R | 500837 | 6359 | 124513 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6PLGF4320 | Installation of Water Heater | 8178 | 648 | 624 | 120 | 0 | 252 | 252 | 120 | 0 | 0 | 0 |  |  |  | 2014-10-29 08:00 | 2014-11-15 17:00 |  | 2014-07-21 08:00 | 2014-08-10 17:00 | 2014-07-21 08:00 | 2014-08-10 17:00 | 2014-07-21 08:00 | 2014-08-10 17:00 | 2014-10-29 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | 8fEEf+szQ4ysJoZiqz6rIw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36660 | N | N | 10 | GROUND FLOOR |  | 124511 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 252 | LABOR- SUBCONTRACTOR
%R | 500838 | 6359 | 124514 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 688 | 56 | 112 | 0 | 360 | 360 | 112 | 0 | 0 | 0 |  |  |  | 2014-09-30 08:00 | 2014-10-18 17:00 |  | 2014-06-18 08:00 | 2014-07-03 17:00 | 2014-06-18 08:00 | 2014-07-03 17:00 | 2014-06-18 08:00 | 2014-07-03 17:00 | 2014-09-30 08:00 | 2014-10-18 17:00 |  | PT_Normal |  |  |  |  | AGsujw3pTNOOfqI795rsOw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36680 | N | N | 20 | ROOF |  | 124511 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 360 | LABOR- SUBCONTRACTOR
%R | 500839 | 6359 | 124514 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6PLRF4350 | Installation of Rain water Pipes |  | 632 | 224 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 |  |  |  | 2014-10-12 08:00 | 2014-10-28 17:00 |  | 2014-07-06 08:00 | 2014-07-22 17:00 | 2014-07-06 08:00 | 2014-07-22 17:00 | 2014-07-06 08:00 | 2014-07-22 17:00 | 2014-10-12 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | 6FLLKtABRiO7LYmRArH0DQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 36680 | N | N | 20 | ROOF |  | 124511 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 0 | 0
%R | 500840 | 6359 | 124514 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 152 | 128 | 200 | 0 | 840 | 840 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-09-23 08:00 | 2014-10-23 17:00 | 2014-09-23 08:00 | 2014-10-23 17:00 | 2014-09-23 08:00 | 2014-10-23 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | BqrzCwFURD2u/BHj6jSzaQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36680 | N | N | 20 | ROOF |  | 124511 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 420 | LABOR- SUBCONTRACTOR
%R | 500841 | 6359 | 124517 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STFF2020 | Column-Rebar & Formwork | 8166 | 88 | 0 | 200 | 0 | 4272 | 4272 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-16 08:00 | 2014-04-13 17:00 |  | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 |  | PT_Normal |  |  |  |  | C7YMzM00TdGPuEMtRwdhvA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36500 | N | N | 15 | FIRST FLOORS |  | 124516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 4272 | CARPENTERS SK
%R | 500842 | 6359 | 124517 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STFF2025 | Column-Concrete | 8167 | 88 | 0 | 184 | 0 | 427 | 427 | 184 | 0 | 0 | 0 |  |  |  | 2014-03-25 08:00 | 2014-04-20 17:00 |  | 2014-03-12 08:00 | 2014-04-07 17:00 | 2014-03-12 08:00 | 2014-04-07 17:00 | 2014-03-12 08:00 | 2014-04-07 17:00 | 2014-03-25 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | 3rypGTTNSuiThg1IyuiQxQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36500 | N | N | 15 | FIRST FLOORS |  | 124516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 427 | CONCRETE MASON SK
%R | 500843 | 6359 | 124517 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 88 | 0 | 200 | 0 | 23850.75 | 23850.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-29 08:00 | 2014-04-26 17:00 |  | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-29 08:00 | 2014-04-26 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36500 | N | N | 15 | FIRST FLOORS |  | 124516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 23850.75 | STEEL FIXERS SK
%R | 500844 | 6359 | 124517 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 88 | 0 | 112 | 0 | 1610 | 1610 | 112 | 0 | 0 | 0 |  |  |  | 2014-04-14 08:00 | 2014-04-29 17:00 |  | 2014-04-01 08:00 | 2014-04-16 17:00 | 2014-04-01 08:00 | 2014-04-16 17:00 | 2014-04-01 08:00 | 2014-04-16 17:00 | 2014-04-14 08:00 | 2014-04-29 17:00 |  | PT_Normal |  |  |  |  | 8TmIx4OrT/K0FaeYzMMaOg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36500 | N | N | 15 | FIRST FLOORS |  | 124516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1610 | CONCRETE MASON SK
%R | 500845 | 6359 | 124518 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STRF2040 | Column-Rebar & Formwork | 8166 | 104 | 0 | 144 | 0 | 1470 | 1470 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-22 08:00 | 2014-05-12 17:00 |  | 2014-04-07 08:00 | 2014-04-27 17:00 | 2014-04-07 08:00 | 2014-04-27 17:00 | 2014-04-07 08:00 | 2014-04-27 17:00 | 2014-04-22 08:00 | 2014-05-12 17:00 |  | PT_Normal |  |  |  |  | qgJIonTZSam+DOwhIn302g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36510 | N | N | 20 | ROOF |  | 124516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1470 | CARPENTERS SK
%R | 500846 | 6359 | 124518 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STRF2045 | Column-Concrete | 8167 | 104 | 0 | 136 | 0 | 101.5 | 101.5 | 136 | 0 | 0 | 0 |  |  |  | 2014-04-26 08:00 | 2014-05-14 17:00 |  | 2014-04-10 08:00 | 2014-04-29 17:00 | 2014-04-10 08:00 | 2014-04-29 17:00 | 2014-04-10 08:00 | 2014-04-29 17:00 | 2014-04-26 08:00 | 2014-05-14 17:00 |  | PT_Normal |  |  |  |  | riiCE0I0SPeGUkYxiAoceQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36510 | N | N | 20 | ROOF |  | 124516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 101.5 | CONCRETE MASON SK
%R | 500847 | 6359 | 124518 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STRF2050 | Slab-Rebar & Formwork - Head Room | 8165 | 104 | 0 | 160 | 0 | 4303.25 | 4303.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-28 08:00 | 2014-05-20 17:00 |  | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-28 08:00 | 2014-05-20 17:00 |  | PT_Normal |  |  |  |  | 14/33/9FScOWQO5M/Kw1Tg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36510 | N | N | 20 | ROOF |  | 124516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 4303.25 | STEEL FIXERS SK
%R | 500848 | 6359 | 124518 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STRF2055 | Slab-Concrete-Head room | 8167 | 104 | 0 | 104 | 0 | 350 | 350 | 104 | 0 | 0 | 0 |  |  |  | 2014-05-12 08:00 | 2014-05-26 17:00 |  | 2014-04-27 08:00 | 2014-05-11 17:00 | 2014-04-27 08:00 | 2014-05-11 17:00 | 2014-04-27 08:00 | 2014-05-11 17:00 | 2014-05-12 08:00 | 2014-05-26 17:00 |  | PT_Normal |  |  |  |  | PqjSbtg1RemAujDivgc1Wg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36510 | N | N | 20 | ROOF |  | 124516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 350 | CONCRETE MASON SK
%R | 500849 | 6359 | 124518 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STRF2060 | Construction of Parapets | 8168 | 584 | 72 | 200 | 0 | 1468.75 | 1468.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-28 08:00 | 2014-08-28 17:00 |  | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-07-28 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | ZlIcUr/xQYSdHdcHDuEqzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36510 | N | N | 20 | ROOF |  | 124516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1468.75 | BLOCK MASON SK
%R | 500850 | 6359 | 124518 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STRF2065 | Construction of up stands/Plinth | 8165 | 624 | 0 | 200 | 0 | 687.75 | 687.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-23 08:00 | 2014-09-20 17:00 |  | 2014-05-20 08:00 | 2014-06-17 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 | 2014-08-23 08:00 | 2014-09-20 17:00 |  | PT_Normal |  |  |  |  | SpqFGp8yRa+S9fWeYFDyiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36510 | N | N | 20 | ROOF |  | 124516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 687.75 | STEEL FIXERS SK
%R | 500851 | 6359 | 124519 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STGF2000 | Column-Rebar & Formwork | 8165 | 88 | 0 | 200 | 0 | 6230 | 6230 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-01 08:00 | 2014-03-02 17:00 |  | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 |  | PT_Normal |  |  |  |  | OOQYAmELTWi2AghH5OTv6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36490 | N | N | 10 | GROUND FLOOR |  | 124516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 6230 | STEEL FIXERS SK
%R | 500852 | 6359 | 124519 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STGF2005 | Column-Concrete | 8167 | 88 | 0 | 184 | 0 | 486.5 | 486.5 | 184 | 0 | 0 | 0 |  |  |  | 2014-02-10 08:00 | 2014-03-09 17:00 |  | 2014-01-28 08:00 | 2014-02-24 17:00 | 2014-01-28 08:00 | 2014-02-24 17:00 | 2014-01-28 08:00 | 2014-02-24 17:00 | 2014-02-10 08:00 | 2014-03-09 17:00 |  | PT_Normal |  |  |  |  | E+Kg7l+kSdyL/RRZmAHR9A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36490 | N | N | 10 | GROUND FLOOR |  | 124516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 486.5 | CONCRETE MASON SK
%R | 500853 | 6359 | 124519 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 88 | 0 | 200 | 0 | 23402.75 | 23402.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-25 08:00 | 2014-03-25 17:00 |  | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 |  | PT_Normal |  |  |  |  | fq6ZK3RmTuKA0q70b3HEzg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36490 | N | N | 10 | GROUND FLOOR |  | 124516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 11701.375 | STEEL FIXERS SK
%R | 500854 | 6359 | 124519 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 88 | 0 | 112 | 0 | 1820 | 1820 | 112 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-03-29 17:00 |  | 2014-03-01 08:00 | 2014-03-16 17:00 | 2014-03-01 08:00 | 2014-03-16 17:00 | 2014-03-01 08:00 | 2014-03-16 17:00 | 2014-03-13 08:00 | 2014-03-29 17:00 |  | PT_Normal |  |  |  |  | SSUrDxsZQBetoCO+GmovtA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36490 | N | N | 10 | GROUND FLOOR |  | 124516 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1820 | CONCRETE MASON SK
%R | 500855 | 6359 | 124521 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STUG1010 | Footing Blinding | 8163 | 88 | 0 | 184 | 0 | 1309 | 1309 | 184 | 0 | 0 | 0 |  |  |  | 2013-10-09 08:00 | 2013-11-06 17:00 |  | 2013-09-26 08:00 | 2013-10-24 17:00 | 2013-09-26 08:00 | 2013-10-24 17:00 | 2013-09-26 08:00 | 2013-10-24 17:00 | 2013-10-09 08:00 | 2013-11-06 17:00 |  | PT_Normal |  |  |  |  | /hpDB+BlT3m6B68Gx76xAg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36470 | N | N | 10 | UPTO GRADE SLAB |  | 124520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1309 | BLINDING MASON SK
%R | 500856 | 6359 | 124521 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STUG1015 | Footing Waterproofing & Screed | 8164 | 88 | 0 | 200 | 0 | 1030.25 | 1030.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-15 08:00 | 2013-11-14 17:00 |  | 2013-10-02 08:00 | 2013-11-02 17:00 | 2013-10-02 08:00 | 2013-11-02 17:00 | 2013-10-02 08:00 | 2013-11-02 17:00 | 2013-10-15 08:00 | 2013-11-14 17:00 |  | PT_Normal |  |  |  |  | URglp9p0SkW/+fNZLIhsrg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36470 | N | N | 10 | UPTO GRADE SLAB |  | 124520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 515.125 | SCREED MASON SK
%R | 500857 | 6359 | 124521 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STUG1020 | Construction of foundations | 8165 | 88 | 0 | 160 | 0 | 9962.75 | 9962.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-02 08:00 | 2013-11-24 17:00 |  | 2013-10-20 08:00 | 2013-11-11 17:00 | 2013-10-20 08:00 | 2013-11-11 17:00 | 2013-10-20 08:00 | 2013-11-11 17:00 | 2013-11-02 08:00 | 2013-11-24 17:00 |  | PT_Normal |  |  |  |  | hBfII0vmT6i+KUgdyY4edA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36470 | N | N | 10 | UPTO GRADE SLAB |  | 124520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 9962.75 | STEEL FIXERS SK
%R | 500858 | 6359 | 124521 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STUG1025 | Construction of neck of columns | 8165 | 88 | 0 | 200 | 0 | 2430.75 | 2430.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-11 08:00 | 2013-12-09 17:00 |  | 2013-10-29 08:00 | 2013-11-26 17:00 | 2013-10-29 08:00 | 2013-11-26 17:00 | 2013-10-29 08:00 | 2013-11-26 17:00 | 2013-11-11 08:00 | 2013-12-09 17:00 |  | PT_Normal |  |  |  |  | fNzvrsJZReC/v8vJxoWInQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36470 | N | N | 10 | UPTO GRADE SLAB |  | 124520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 2430.75 | STEEL FIXERS SK
%R | 500859 | 6359 | 124521 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STUG1030 | Waterproofing Footing & Neck Column | 8178 | 88 | 0 | 200 | 0 | 670 | 670 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-20 08:00 | 2013-12-19 17:00 |  | 2013-11-07 08:00 | 2013-12-05 17:00 | 2013-11-07 08:00 | 2013-12-05 17:00 | 2013-11-07 08:00 | 2013-12-05 17:00 | 2013-11-20 08:00 | 2013-12-19 17:00 |  | PT_Normal |  |  |  |  | gS3sUv35TrOcnb203Y7XDA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36470 | N | N | 10 | UPTO GRADE SLAB |  | 124520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 670 | LABOR- SUBCONTRACTOR
%R | 500860 | 6359 | 124521 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 88 | 0 | 200 | 0 | 1520 | 1520 | 200 | 1100 | 0 | 1100 |  |  |  | 2013-12-02 08:00 | 2013-12-31 17:00 |  | 2013-11-19 08:00 | 2013-12-17 17:00 | 2013-11-19 08:00 | 2013-12-17 17:00 | 2013-11-19 08:00 | 2013-12-17 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 |  | PT_Normal |  |  |  |  | C7B+tfwRR3O2Q/IiXkbnrQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36470 | N | N | 10 | UPTO GRADE SLAB |  | 124520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1520 | LABOR - CIVIL
%R | 500861 | 6359 | 124521 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STUG1040 | Construction of Grade Beams | 8163 | 88 | 0 | 200 | 0 | 10120.75 | 10120.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-19 08:00 | 2014-01-16 17:00 |  | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-19 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | C/uWEzvgQx2G7D5JwRitDg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36470 | N | N | 10 | UPTO GRADE SLAB |  | 124520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 10120.75 | BLINDING MASON SK
%R | 500862 | 6359 | 124521 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STUG1045 | Construction of slab on grade | 8163 | 88 | 0 | 200 | 0 | 6924.5 | 6924.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-15 08:00 | 2014-02-13 17:00 |  | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 |  | PT_Normal |  |  |  |  | V+i5g3ZFT4+LLKHtRUl4bA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36470 | N | N | 10 | UPTO GRADE SLAB |  | 124520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 6924.5 | BLINDING MASON SK
%R | 500863 | 6359 | 124521 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STUG1000 | Footing Excavation | 8177 | 88 | 0 | 200 | 0 | 1791 | 1791 | 200 | 843 | 0 | 843 |  |  |  | 2013-09-23 08:00 | 2013-10-23 17:00 |  | 2013-09-10 08:00 | 2013-10-08 17:00 | 2013-09-10 08:00 | 2013-10-08 17:00 | 2013-09-10 08:00 | 2013-10-08 17:00 | 2013-09-23 08:00 | 2013-10-23 17:00 |  | PT_Normal |  |  |  |  | oBs4rhXwT6Oe8y3m/Jshsg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36470 | N | N | 10 | UPTO GRADE SLAB |  | 124520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1791 | LABOR - CIVIL
%R | 500864 | 6359 | 124521 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6STUG1005 | Footing Antitermite | 8178 | 88 | 0 | 184 | 0 | 2326.5 | 2326.5 | 184 | 0 | 0 | 0 |  |  |  | 2013-10-05 08:00 | 2013-11-02 17:00 |  | 2013-09-22 08:00 | 2013-10-20 17:00 | 2013-09-22 08:00 | 2013-10-20 17:00 | 2013-09-22 08:00 | 2013-10-20 17:00 | 2013-10-05 08:00 | 2013-11-02 17:00 |  | PT_Normal |  |  |  |  | 65KrBYFESH2aP+nYBczfQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36470 | N | N | 10 | UPTO GRADE SLAB |  | 124520 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 2326.5 | LABOR- SUBCONTRACTOR
%R | 500865 | 6359 | 124522 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 24 | 24 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-16 08:00 | 2014-12-14 17:00 |  | 2014-11-12 08:00 | 2014-12-10 17:00 | 2014-11-12 08:00 | 2014-12-10 17:00 | 2014-11-12 08:00 | 2014-12-10 17:00 | 2014-11-16 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | x3iPb845Qs+34bjqv83sNA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36790 | N | N | 30 | TESTING AND COMMISSIONING |  | 124488 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 500866 | 6359 | 124522 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 24 | 24 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-16 08:00 | 2014-12-14 17:00 |  | 2014-11-12 08:00 | 2014-12-10 17:00 | 2014-11-12 08:00 | 2014-12-10 17:00 | 2014-11-12 08:00 | 2014-12-10 17:00 | 2014-11-16 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | zOCM+MY8RoiaSJ6SWlx+UA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36790 | N | N | 30 | TESTING AND COMMISSIONING |  | 124488 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 500867 | 6359 | 124522 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ6PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 24 | 24 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-16 08:00 | 2014-12-14 17:00 |  | 2014-11-12 08:00 | 2014-12-10 17:00 | 2014-11-12 08:00 | 2014-12-10 17:00 | 2014-11-12 08:00 | 2014-12-10 17:00 | 2014-11-16 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | MjsoRrtzR/aoqZlNnZ7X2Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 36790 | N | N | 30 | TESTING AND COMMISSIONING |  | 124488 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 500868 | 6359 | 124526 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STUG1000 | Footing Excavation | 8177 | 88 | 0 | 200 | 0 | 1433 | 1433 | 200 | 675 | 0 | 675 |  |  |  | 2013-06-24 08:00 | 2013-07-22 17:00 |  | 2013-06-11 08:00 | 2013-07-09 17:00 | 2013-06-11 08:00 | 2013-07-09 17:00 | 2013-06-11 08:00 | 2013-07-09 17:00 | 2013-06-24 08:00 | 2013-07-22 17:00 |  | PT_Normal |  |  |  |  | dVPTlL6hQiyKHG+g1olEGQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35390 | N | N | 10 | UPTO GRADE SLAB |  | 124525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 1433 | LABOR - CIVIL
%R | 500869 | 6359 | 124526 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STUG1005 | Footing Antitermite | 8178 | 88 | 0 | 184 | 0 | 1861.75 | 1861.75 | 184 | 0 | 0 | 0 |  |  |  | 2013-07-06 08:00 | 2013-07-31 17:00 |  | 2013-06-23 08:00 | 2013-07-18 17:00 | 2013-06-23 08:00 | 2013-07-18 17:00 | 2013-06-23 08:00 | 2013-07-18 17:00 | 2013-07-06 08:00 | 2013-07-31 17:00 |  | PT_Normal |  |  |  |  | 9P+AZRivSYq8oJhRtZQ7JA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35390 | N | N | 10 | UPTO GRADE SLAB |  | 124525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 1861.75 | LABOR- SUBCONTRACTOR
%R | 500870 | 6359 | 124526 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STUG1010 | Footing Blinding | 8163 | 88 | 0 | 184 | 0 | 1048.25 | 1048.25 | 184 | 0 | 0 | 0 |  |  |  | 2013-07-10 08:00 | 2013-08-05 17:00 |  | 2013-06-27 08:00 | 2013-07-23 17:00 | 2013-06-27 08:00 | 2013-07-23 17:00 | 2013-06-27 08:00 | 2013-07-23 17:00 | 2013-07-10 08:00 | 2013-08-05 17:00 |  | PT_Normal |  |  |  |  | j+hRMrmAS0ySTTtlW1qgsg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35390 | N | N | 10 | UPTO GRADE SLAB |  | 124525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 1048.25 | BLINDING MASON SK
%R | 500871 | 6359 | 124526 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STUG1015 | Footing Waterproofing & Screed | 8164 | 88 | 0 | 200 | 0 | 825 | 825 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-16 08:00 | 2013-08-17 17:00 |  | 2013-07-03 08:00 | 2013-07-31 17:00 | 2013-07-03 08:00 | 2013-07-31 17:00 | 2013-07-03 08:00 | 2013-07-31 17:00 | 2013-07-16 08:00 | 2013-08-17 17:00 |  | PT_Normal |  |  |  |  | RxSxELLoSvyLSG1HoK/wOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35390 | N | N | 10 | UPTO GRADE SLAB |  | 124525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 825 | SCREED MASON SK
%R | 500872 | 6359 | 124526 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STUG1020 | Construction of foundations | 8165 | 88 | 0 | 160 | 0 | 7969.5 | 7969.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-07-31 08:00 | 2013-08-26 17:00 |  | 2013-07-18 08:00 | 2013-08-13 17:00 | 2013-07-18 08:00 | 2013-08-13 17:00 | 2013-07-18 08:00 | 2013-08-13 17:00 | 2013-07-31 08:00 | 2013-08-26 17:00 |  | PT_Normal |  |  |  |  | BROFChE+R/ykercCFl4IYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35390 | N | N | 10 | UPTO GRADE SLAB |  | 124525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 7969.5 | STEEL FIXERS SK
%R | 500873 | 6359 | 124526 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STUG1025 | Construction of neck of columns | 8165 | 88 | 0 | 200 | 0 | 1946 | 1946 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-13 08:00 | 2013-09-10 17:00 |  | 2013-07-28 08:00 | 2013-08-28 17:00 | 2013-07-28 08:00 | 2013-08-28 17:00 | 2013-07-28 08:00 | 2013-08-28 17:00 | 2013-08-13 08:00 | 2013-09-10 17:00 |  | PT_Normal |  |  |  |  | zNC9//0eRFSqiRfpxUdpmQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35390 | N | N | 10 | UPTO GRADE SLAB |  | 124525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 973 | STEEL FIXERS SK
%R | 500874 | 6359 | 124526 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 88 | 0 | 200 | 0 | 1436 | 1436 | 200 | 1100 | 0 | 1100 |  |  |  | 2013-09-03 08:00 | 2013-10-01 17:00 |  | 2013-08-21 08:00 | 2013-09-18 17:00 | 2013-08-21 08:00 | 2013-09-18 17:00 | 2013-08-21 08:00 | 2013-09-18 17:00 | 2013-09-03 08:00 | 2013-10-01 17:00 |  | PT_Normal |  |  |  |  | SwSvpZa5SQy2YPcZx9190w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35390 | N | N | 10 | UPTO GRADE SLAB |  | 124525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 1436 | LABOR - CIVIL
%R | 500875 | 6359 | 124526 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STUG1040 | Construction of Grade Beams | 8163 | 88 | 0 | 200 | 0 | 8096.25 | 8096.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-19 08:00 | 2013-10-20 17:00 |  | 2013-09-07 08:00 | 2013-10-05 17:00 | 2013-09-07 08:00 | 2013-10-05 17:00 | 2013-09-07 08:00 | 2013-10-05 17:00 | 2013-09-19 08:00 | 2013-10-20 17:00 |  | PT_Normal |  |  |  |  | DdgRtbsCTSWC/8tQ0nK9fw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35390 | N | N | 10 | UPTO GRADE SLAB |  | 124525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 8096.25 | BLINDING MASON SK
%R | 500876 | 6359 | 124526 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STUG1045 | Construction of slab on grade | 8163 | 88 | 0 | 200 | 0 | 5538.75 | 5538.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-16 08:00 | 2013-11-16 17:00 |  | 2013-10-03 08:00 | 2013-11-03 17:00 | 2013-10-03 08:00 | 2013-11-03 17:00 | 2013-10-03 08:00 | 2013-11-03 17:00 | 2013-10-16 08:00 | 2013-11-16 17:00 |  | PT_Normal |  |  |  |  | 2bPIrc+jSPKf7Ib8X+RmuA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35390 | N | N | 10 | UPTO GRADE SLAB |  | 124525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 2769.375 | BLINDING MASON SK
%R | 500877 | 6359 | 124526 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STUG1030 | Waterproofing Footing & Neck Column | 8178 | 88 | 0 | 200 | 0 | 535.25 | 535.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-22 08:00 | 2013-09-19 17:00 |  | 2013-08-06 08:00 | 2013-09-07 17:00 | 2013-08-06 08:00 | 2013-09-07 17:00 | 2013-08-06 08:00 | 2013-09-07 17:00 | 2013-08-22 08:00 | 2013-09-19 17:00 |  | PT_Normal |  |  |  |  | WUOT2sJkRcG09nMAU+sn6g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35390 | N | N | 10 | UPTO GRADE SLAB |  | 124525 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 267.625 | LABOR- SUBCONTRACTOR
%R | 500878 | 6359 | 124528 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 88 | 0 | 200 | 0 | 18721.5 | 18721.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-27 08:00 | 2013-12-26 17:00 |  | 2013-11-14 08:00 | 2013-12-12 17:00 | 2013-11-14 08:00 | 2013-12-12 17:00 | 2013-11-14 08:00 | 2013-12-12 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 |  | PT_Normal |  |  |  |  | y2/cilsnRkGukenoIFLXBQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35410 | N | N | 10 | GROUND FLOOR |  | 124527 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 18721.5 | STEEL FIXERS SK
%R | 500879 | 6359 | 124528 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 88 | 0 | 112 | 0 | 1456 | 1456 | 112 | 0 | 0 | 0 |  |  |  | 2013-12-14 08:00 | 2013-12-30 17:00 |  | 2013-12-01 08:00 | 2013-12-16 17:00 | 2013-12-01 08:00 | 2013-12-16 17:00 | 2013-12-01 08:00 | 2013-12-16 17:00 | 2013-12-14 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | JZO5ZFhGRzq6HdvOp/GgCQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35410 | N | N | 10 | GROUND FLOOR |  | 124527 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1456 | CONCRETE MASON SK
%R | 500880 | 6359 | 124528 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STGF2000 | Column-Rebar & Formwork | 8165 | 88 | 0 | 200 | 0 | 4984 | 4984 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-04 08:00 | 2013-12-02 17:00 |  | 2013-10-22 08:00 | 2013-11-19 17:00 | 2013-10-22 08:00 | 2013-11-19 17:00 | 2013-10-22 08:00 | 2013-11-19 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 |  | PT_Normal |  |  |  |  | qlpsNcKnSByGeWUGNMiLHQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35410 | N | N | 10 | GROUND FLOOR |  | 124527 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 4984 | STEEL FIXERS SK
%R | 500881 | 6359 | 124528 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STGF2005 | Column-Concrete | 8167 | 88 | 0 | 184 | 0 | 388.5 | 388.5 | 184 | 0 | 0 | 0 |  |  |  | 2013-11-13 08:00 | 2013-12-09 17:00 |  | 2013-10-31 08:00 | 2013-11-26 17:00 | 2013-10-31 08:00 | 2013-11-26 17:00 | 2013-10-31 08:00 | 2013-11-26 17:00 | 2013-11-13 08:00 | 2013-12-09 17:00 |  | PT_Normal |  |  |  |  | upH2gnZ3Requ1tnjk3AYPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35410 | N | N | 10 | GROUND FLOOR |  | 124527 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 388.5 | CONCRETE MASON SK
%R | 500882 | 6359 | 124529 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STRF2045 | Column-Concrete | 8167 | 304 | 0 | 136 | 0 | 80.5 | 80.5 | 136 | 0 | 0 | 0 |  |  |  | 2014-02-26 08:00 | 2014-03-17 17:00 |  | 2014-01-12 08:00 | 2014-01-30 17:00 | 2014-01-12 08:00 | 2014-01-30 17:00 | 2014-01-12 08:00 | 2014-01-30 17:00 | 2014-02-26 08:00 | 2014-03-17 17:00 |  | PT_Normal |  |  |  |  | feti1IeeTKGxMzYDK0WMuA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35430 | N | N | 20 | ROOF |  | 124527 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 80.5 | CONCRETE MASON SK
%R | 500883 | 6359 | 124529 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STRF2050 | Slab-Rebar & Formwork - Head Room | 8165 | 304 | 0 | 160 | 0 | 3444 | 3444 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-01 08:00 | 2014-03-23 17:00 |  | 2014-01-14 08:00 | 2014-02-05 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 | 2014-03-01 08:00 | 2014-03-23 17:00 |  | PT_Normal |  |  |  |  | v2LmjFRNR36tJvZjFfqJSA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35430 | N | N | 20 | ROOF |  | 124527 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 3444 | STEEL FIXERS SK
%R | 500884 | 6359 | 124529 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STRF2055 | Slab-Concrete-Head room | 8167 | 304 | 0 | 104 | 0 | 280 | 280 | 104 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-03-29 17:00 |  | 2014-01-28 08:00 | 2014-02-12 17:00 | 2014-01-28 08:00 | 2014-02-12 17:00 | 2014-01-28 08:00 | 2014-02-12 17:00 | 2014-03-15 08:00 | 2014-03-29 17:00 |  | PT_Normal |  |  |  |  | jLu50V2FSWe6PaHUXVP3bg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35430 | N | N | 20 | ROOF |  | 124527 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 280 | CONCRETE MASON SK
%R | 500885 | 6359 | 124529 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STRF2060 | Construction of Parapets | 8168 | 488 | 80 | 200 | 0 | 1175 | 1175 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-14 08:00 | 2014-05-12 17:00 |  | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 |  | PT_Normal |  |  |  |  | 8FaQSFIeRY+z+iLFzIW0zA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35430 | N | N | 20 | ROOF |  | 124527 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 587.5 | BLOCK MASON SK
%R | 500886 | 6359 | 124529 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STRF2040 | Column-Rebar & Formwork | 8166 | 272 | 0 | 144 | 0 | 1176 | 1176 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-10 17:00 |  | 2014-01-08 08:00 | 2014-01-28 17:00 | 2014-01-08 08:00 | 2014-01-28 17:00 | 2014-01-08 08:00 | 2014-01-28 17:00 | 2014-02-18 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | 3gj1sFp/QneNP9U9rjVWfg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35430 | N | N | 20 | ROOF |  | 124527 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1176 | CARPENTERS SK
%R | 500887 | 6359 | 124529 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STRF2065 | Construction of up stands/Plinth | 8165 | 624 | 0 | 200 | 0 | 549.5 | 549.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-24 08:00 | 2014-06-21 17:00 |  | 2014-02-22 08:00 | 2014-03-22 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 |  | PT_Normal |  |  |  |  | yXCzAMZOTQGnSfVG49iSkg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35430 | N | N | 20 | ROOF |  | 124527 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 274.75 | STEEL FIXERS SK
%R | 500888 | 6359 | 124530 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STFF2020 | Column-Rebar & Formwork | 8166 | 88 | 0 | 200 | 0 | 3418 | 3418 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-16 08:00 | 2014-01-14 17:00 |  | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-16 08:00 | 2014-01-14 17:00 |  | PT_Normal |  |  |  |  | Qg5mK9Z7QMm8nbAAKb5MTw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35420 | N | N | 15 | FIRST FLOORS |  | 124527 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 3418 | CARPENTERS SK
%R | 500889 | 6359 | 124530 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STFF2025 | Column-Concrete | 8167 | 88 | 0 | 184 | 0 | 339.5 | 339.5 | 184 | 0 | 0 | 0 |  |  |  | 2013-12-26 08:00 | 2014-01-21 17:00 |  | 2013-12-12 08:00 | 2014-01-08 17:00 | 2013-12-12 08:00 | 2014-01-08 17:00 | 2013-12-12 08:00 | 2014-01-08 17:00 | 2013-12-26 08:00 | 2014-01-21 17:00 |  | PT_Normal |  |  |  |  | ZaEK59zhR+WNMLIcWVeaXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35420 | N | N | 15 | FIRST FLOORS |  | 124527 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 339.5 | CONCRETE MASON SK
%R | 500890 | 6359 | 124530 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 88 | 0 | 200 | 0 | 19080.25 | 19080.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-30 08:00 | 2014-01-27 17:00 |  | 2013-12-16 08:00 | 2014-01-14 17:00 | 2013-12-16 08:00 | 2014-01-14 17:00 | 2013-12-16 08:00 | 2014-01-14 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 |  | PT_Normal |  |  |  |  | OQM+4+UxTZiMNeisSkwvEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35420 | N | N | 15 | FIRST FLOORS |  | 124527 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 19080.25 | STEEL FIXERS SK
%R | 500891 | 6359 | 124530 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 88 | 0 | 112 | 0 | 1288 | 1288 | 112 | 0 | 0 | 0 |  |  |  | 2014-01-15 08:00 | 2014-01-30 17:00 |  | 2014-01-02 08:00 | 2014-01-18 17:00 | 2014-01-02 08:00 | 2014-01-18 17:00 | 2014-01-02 08:00 | 2014-01-18 17:00 | 2014-01-15 08:00 | 2014-01-30 17:00 |  | PT_Normal |  |  |  |  | 80hbc9FFTtG4ZtRJgJ7QEw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35420 | N | N | 15 | FIRST FLOORS |  | 124527 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1288 | CONCRETE MASON SK
%R | 500892 | 6359 | 124533 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3AREL3665 | External Plastering | 8169 | 608 | 0 | 200 | 0 | 12200 | 12200 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | wWMrgBD1Shus2liesScm/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35510 | N | N | 15 | ELEVATION |  | 124532 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 12200 | PLASTER MASON SK
%R | 500893 | 6359 | 124533 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3AREL3670 | External stone cladding works | 8170 | 608 | 0 | 160 | 0 | 936 | 936 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-05 08:00 | 2014-07-27 17:00 |  | 2014-04-07 08:00 | 2014-04-29 17:00 | 2014-04-07 08:00 | 2014-04-29 17:00 | 2014-04-07 08:00 | 2014-04-29 17:00 | 2014-07-05 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | 8iFSgmstTrmosUo9tl+EXQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35510 | N | N | 15 | ELEVATION |  | 124532 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 936 | TILE MASON SK
%R | 500894 | 6359 | 124533 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3AREL3675 | GRC works | 8178 | 608 | 0 | 160 | 0 | 550 | 550 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-10 08:00 | 2014-08-05 17:00 |  | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-07-10 08:00 | 2014-08-05 17:00 |  | PT_Normal |  |  |  |  | s3TsmwhmQQq/F8GIH8neQw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35510 | N | N | 15 | ELEVATION |  | 124532 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 550 | LABOR- SUBCONTRACTOR
%R | 500895 | 6359 | 124533 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3AREL3680 | External Painting | 8178 | 608 | 40 | 160 | 0 | 4224 | 4224 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-22 08:00 | 2014-08-17 17:00 |  | 2014-04-24 08:00 | 2014-05-17 17:00 | 2014-04-24 08:00 | 2014-05-17 17:00 | 2014-04-24 08:00 | 2014-05-17 17:00 | 2014-07-22 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | BW+wo0G/QYWTI2SLnsuNwA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35510 | N | N | 15 | ELEVATION |  | 124532 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 4224 | LABOR- SUBCONTRACTOR
%R | 500896 | 6359 | 124534 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARRF3630 | Leveling Screed for Waterproofing | 8164 | 624 | 0 | 200 | 0 | 711.5 | 711.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-04 08:00 | 2014-07-02 17:00 |  | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-06-04 08:00 | 2014-07-02 17:00 |  | PT_Normal |  |  |  |  | CzXlypm5Se2e/wuZx+o/bg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35500 | N | N | 10 | ROOF |  | 124532 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 711.5 | SCREED MASON SK
%R | 500897 | 6359 | 124534 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARRF3635 | Laying of Waterproofing Membrane | 8178 | 624 | 0 | 200 | 0 | 986.25 | 986.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-08 08:00 | 2014-07-06 17:00 |  | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-06-08 08:00 | 2014-07-06 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35500 | N | N | 10 | ROOF |  | 124532 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 986.25 | LABOR- SUBCONTRACTOR
%R | 500898 | 6359 | 124534 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARRF3640 | Installation of Insulation & Protection | 8178 | 624 | 0 | 200 | 0 | 1250.25 | 1250.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-07-10 17:00 |  | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 |  | PT_Normal |  |  |  |  | DDNdcNE/SIS9FlpodGorDQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35500 | N | N | 10 | ROOF |  | 124532 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1250.25 | LABOR- SUBCONTRACTOR
%R | 500899 | 6359 | 124534 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 624 | 0 | 200 | 0 | 626 | 626 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | OTDxQBaZSVC+axJwWmLPSQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35500 | N | N | 10 | ROOF |  | 124532 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 626 | TILE MASON SK
%R | 500900 | 6359 | 124534 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 624 | 40 | 160 | 0 | 616 | 616 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-10 08:00 | 2014-08-05 17:00 |  | 2014-04-10 08:00 | 2014-05-03 17:00 | 2014-04-10 08:00 | 2014-05-03 17:00 | 2014-04-10 08:00 | 2014-05-03 17:00 | 2014-07-10 08:00 | 2014-08-05 17:00 |  | PT_Normal |  |  |  |  | 8p1yzzinSt2LZiqA//WqBw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35500 | N | N | 10 | ROOF |  | 124532 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 616 | LABOR- SUBCONTRACTOR
%R | 500901 | 6359 | 124534 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 624 | 0 | 200 | 0 | 859.25 | 859.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-25 08:00 | 2014-07-23 17:00 |  | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-06-25 08:00 | 2014-07-23 17:00 |  | PT_Normal |  |  |  |  | F+x3cMSzRmu9uy5lZ/aPRQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35500 | N | N | 10 | ROOF |  | 124532 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 859.25 | LABOR- SUBCONTRACTOR
%R | 500902 | 6359 | 124534 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARRF3660 | Installation of Access Ladder | 8178 | 624 | 600 | 120 | 0 | 352 | 352 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-28 08:00 | 2014-08-17 17:00 |  | 2014-04-28 08:00 | 2014-05-14 17:00 | 2014-04-28 08:00 | 2014-05-14 17:00 | 2014-04-28 08:00 | 2014-05-14 17:00 | 2014-07-28 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | 6FGxdsdOQdmTdLJXKtzA1w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35500 | N | N | 10 | ROOF |  | 124532 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 352 | LABOR- SUBCONTRACTOR
%R | 500903 | 6359 | 124536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARFF3300 | Block work | 8168 | 24 | 0 | 200 | 0 | 7341 | 7341 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-03-10 17:00 |  | 2014-02-05 08:00 | 2014-03-06 17:00 | 2014-02-05 08:00 | 2014-03-06 17:00 | 2014-02-05 08:00 | 2014-03-06 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | GUNn72jqQsy2VtJbj1s9IA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35470 | N | N | 15 | FIRST FLOORS |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 3670.5 | BLOCK MASON SK
%R | 500904 | 6359 | 124536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARFF3305 | Plastering work | 8169 | 24 | 0 | 200 | 0 | 7518.75 | 7518.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-04-06 17:00 |  | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | 8GOv7qw0QSitJj6OAlEejg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35470 | N | N | 15 | FIRST FLOORS |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 7518.75 | PLASTER MASON SK
%R | 500905 | 6359 | 124536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARFF3310 | Flooring screed | 8164 | 160 | 136 | 168 | 0 | 1082.5 | 1082.5 | 168 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-04-29 17:00 |  | 2014-03-13 08:00 | 2014-04-06 17:00 | 2014-03-13 08:00 | 2014-04-06 17:00 | 2014-03-13 08:00 | 2014-04-06 17:00 | 2014-04-06 08:00 | 2014-04-29 17:00 |  | PT_Normal |  |  |  |  | 9KXsqlfCT2qxvmMJ4kOQKg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35470 | N | N | 15 | FIRST FLOORS |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1082.5 | SCREED MASON SK
%R | 500906 | 6359 | 124536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARFF3315 | Wet area waterproofing | 8178 | 24 | 0 | 120 | 0 | 1374 | 1374 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-30 08:00 | 2014-04-15 17:00 |  | 2014-03-26 08:00 | 2014-04-12 17:00 | 2014-03-26 08:00 | 2014-04-12 17:00 | 2014-03-26 08:00 | 2014-04-12 17:00 | 2014-03-30 08:00 | 2014-04-15 17:00 |  | PT_Normal |  |  |  |  | 8BI+rmJbTyOb9L65BAIq+A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35470 | N | N | 15 | FIRST FLOORS |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1374 | LABOR- SUBCONTRACTOR
%R | 500907 | 6359 | 124536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARFF3330 | Paint First coat | 8178 | 232 | 208 | 200 | 0 | 5256.25 | 5256.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-24 08:00 | 2014-05-22 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 |  | PT_Normal |  |  |  |  | KPw1qhkRSp6XxUateU0IcQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35470 | N | N | 15 | FIRST FLOORS |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 5256.25 | LABOR- SUBCONTRACTOR
%R | 500908 | 6359 | 124536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARFF3320 | Ceramic Wall Tiling | 8170 | 24 | 0 | 200 | 0 | 1516 | 1516 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-08 08:00 | 2014-05-06 17:00 |  | 2014-04-05 08:00 | 2014-05-03 17:00 | 2014-04-05 08:00 | 2014-05-03 17:00 | 2014-04-05 08:00 | 2014-05-03 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 |  | PT_Normal |  |  |  |  | 6h98J8snRtidOKkjkI9oWg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35470 | N | N | 15 | FIRST FLOORS |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1516 | TILE MASON SK
%R | 500909 | 6359 | 124536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARFF3325 | Porcelain Tile flooring | 8170 | 24 | 0 | 200 | 0 | 1341 | 1341 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | fYwJa64tT3qTESz94ho8ZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35470 | N | N | 15 | FIRST FLOORS |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1341 | TILE MASON SK
%R | 500910 | 6359 | 124536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARFF3335 | Slate Tile Flooring & Skirting | 8170 | 176 | 152 | 120 | 0 | 931.25 | 931.25 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-27 08:00 | 2014-06-12 17:00 |  | 2014-05-01 08:00 | 2014-05-18 17:00 | 2014-05-01 08:00 | 2014-05-18 17:00 | 2014-05-01 08:00 | 2014-05-18 17:00 | 2014-05-27 08:00 | 2014-06-12 17:00 |  | PT_Normal |  |  |  |  | dOa8ke2sRfW4b7+FVl/kVw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35470 | N | N | 15 | FIRST FLOORS |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 931.25 | TILE MASON SK
%R | 500911 | 6359 | 124536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARFF3350 | Granite - Stair case flooring & Skirting | 8171 | 112 | 88 | 160 | 0 | 850 | 850 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-21 08:00 | 2014-06-12 17:00 |  | 2014-05-05 08:00 | 2014-05-27 17:00 | 2014-05-05 08:00 | 2014-05-27 17:00 | 2014-05-05 08:00 | 2014-05-27 17:00 | 2014-05-21 08:00 | 2014-06-12 17:00 |  | PT_Normal |  |  |  |  | fEWgxDmgQByW1PtmYUTTUQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35470 | N | N | 15 | FIRST FLOORS |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 850 | GRANITE MASON SK
%R | 500912 | 6359 | 124536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARFF3345 | Fixing of Suspension systems | 8178 | 24 | 0 | 160 | 0 | 1191 | 1191 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-08 08:00 | 2014-05-31 17:00 |  | 2014-05-05 08:00 | 2014-05-27 17:00 | 2014-05-05 08:00 | 2014-05-27 17:00 | 2014-05-05 08:00 | 2014-05-27 17:00 | 2014-05-08 08:00 | 2014-05-31 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35470 | N | N | 15 | FIRST FLOORS |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1191 | LABOR- SUBCONTRACTOR
%R | 500913 | 6359 | 124536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARFF3360 | Gypsum board false ceiling | 8178 | 24 | 0 | 200 | 0 | 1191 | 1191 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-20 08:00 | 2014-06-17 17:00 |  | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | y7qM1YJZTZSJp1k+K9w7rA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35470 | N | N | 15 | FIRST FLOORS |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1191 | LABOR- SUBCONTRACTOR
%R | 500914 | 6359 | 124536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARFF3365 | Wooden door | 8178 | 24 | 0 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-04 08:00 | 2014-06-21 17:00 |  | 2014-06-01 08:00 | 2014-06-17 17:00 | 2014-06-01 08:00 | 2014-06-17 17:00 | 2014-06-01 08:00 | 2014-06-17 17:00 | 2014-06-04 08:00 | 2014-06-21 17:00 |  | PT_Normal |  |  |  |  | viFWtxlnR8CS/yJJLqEzXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35470 | N | N | 15 | FIRST FLOORS |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 176 | LABOR- SUBCONTRACTOR
%R | 500915 | 6359 | 124536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARFF3370 | Aluminum Door | 8178 | 24 | 0 | 160 | 0 | 132 | 132 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-07-05 17:00 |  | 2014-06-09 08:00 | 2014-07-01 17:00 | 2014-06-09 08:00 | 2014-07-01 17:00 | 2014-06-09 08:00 | 2014-07-01 17:00 | 2014-06-12 08:00 | 2014-07-05 17:00 |  | PT_Normal |  |  |  |  | 0vQXGI3TTVGbiLmMcLMqTA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35470 | N | N | 15 | FIRST FLOORS |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 132 | LABOR- SUBCONTRACTOR
%R | 500916 | 6359 | 124536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARFF3380 | Aluminum windows | 8178 | 128 | 104 | 160 | 0 | 272.25 | 272.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-05 08:00 | 2014-07-27 17:00 |  | 2014-06-16 08:00 | 2014-07-08 17:00 | 2014-06-16 08:00 | 2014-07-08 17:00 | 2014-06-16 08:00 | 2014-07-08 17:00 | 2014-07-05 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | 1VtL8vZoTz6r2AuQMz4GhA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35470 | N | N | 15 | FIRST FLOORS |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 272.25 | LABOR- SUBCONTRACTOR
%R | 500917 | 6359 | 124536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARFF3390 | Installation of Granite Counter Top | 8171 | 40 | 16 | 160 | 0 | 110 | 110 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-07 08:00 | 2014-07-29 17:00 |  | 2014-07-01 08:00 | 2014-07-23 17:00 | 2014-07-01 08:00 | 2014-07-23 17:00 | 2014-07-01 08:00 | 2014-07-23 17:00 | 2014-07-07 08:00 | 2014-07-29 17:00 |  | PT_Normal |  |  |  |  | IjBYyABHQvaxssFt/C43jg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35470 | N | N | 15 | FIRST FLOORS |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 110 | GRANITE MASON SK
%R | 500918 | 6359 | 124536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARFF3385 | Handrail & Balustrade | 8178 | 24 | 0 | 160 | 0 | 175 | 175 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-05 08:00 | 2014-07-27 17:00 |  | 2014-07-01 08:00 | 2014-07-23 17:00 | 2014-07-01 08:00 | 2014-07-23 17:00 | 2014-07-01 08:00 | 2014-07-23 17:00 | 2014-07-05 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | 8XwWzGMARyi6CaJ6bs9j4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35470 | N | N | 15 | FIRST FLOORS |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 175 | LABOR- SUBCONTRACTOR
%R | 500919 | 6359 | 124536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARFF3395 | Final Painting | 8178 | 24 | 0 | 200 | 0 | 5256.25 | 5256.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | /befUOQsTNa4JxOQre+f1Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35470 | N | N | 15 | FIRST FLOORS |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 2628.125 | LABOR- SUBCONTRACTOR
%R | 500920 | 6359 | 124536 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARFF3375 | Carpentry & Joinery Works | 8178 | 24 | 0 | 200 | 0 | 704 | 704 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-21 08:00 | 2014-07-19 17:00 |  | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-21 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | q9Dd77A2Ts6qRx5hFmrwcQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35470 | N | N | 15 | FIRST FLOORS |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 704 | LABOR- SUBCONTRACTOR
%R | 500921 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3000 | Block work | 8168 | 392 | 0 | 200 | 0 | 9262.5 | 9262.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-23 08:00 | 2014-03-23 17:00 |  | 2013-12-26 08:00 | 2014-01-23 17:00 | 2013-12-26 08:00 | 2014-01-23 17:00 | 2013-12-26 08:00 | 2014-01-23 17:00 | 2014-02-23 08:00 | 2014-03-23 17:00 |  | PT_Normal |  |  |  |  | 4Frep068S7SoQD9XVj4Geg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 9262.5 | BLOCK MASON SK
%R | 500922 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3005 | Plastering work | 8169 | 392 | 0 | 200 | 0 | 11350 | 11350 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-14 17:00 |  | 2014-01-18 08:00 | 2014-02-16 17:00 | 2014-01-18 08:00 | 2014-02-16 17:00 | 2014-01-18 08:00 | 2014-02-16 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 |  | PT_Normal |  |  |  |  | opC0CHrmSzWbQmo+Qd/Brw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 11350 | PLASTER MASON SK
%R | 500923 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3010 | Flooring screed | 8164 | 456 | 64 | 168 | 0 | 2171.5 | 2171.5 | 168 | 0 | 0 | 0 |  |  |  | 2014-04-03 08:00 | 2014-04-27 17:00 |  | 2014-01-26 08:00 | 2014-02-19 17:00 | 2014-01-26 08:00 | 2014-02-19 17:00 | 2014-01-26 08:00 | 2014-02-19 17:00 | 2014-04-03 08:00 | 2014-04-27 17:00 |  | PT_Normal |  |  |  |  | wgBs3WaGROW/zUQVJK4qTg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 2171.5 | SCREED MASON SK
%R | 500924 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 392 | 0 | 120 | 0 | 423.5 | 423.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-03 08:00 | 2014-04-20 17:00 |  | 2014-02-04 08:00 | 2014-02-22 17:00 | 2014-02-04 08:00 | 2014-02-22 17:00 | 2014-02-04 08:00 | 2014-02-22 17:00 | 2014-04-03 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | OWhKG/NDSue4egZTO2Ow0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 423.5 | LABOR- SUBCONTRACTOR
%R | 500925 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3030 | Paint First coat | 8178 | 504 | 0 | 200 | 0 | 5936.25 | 5936.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-19 08:00 | 2014-05-17 17:00 |  | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 |  | PT_Normal |  |  |  |  | 55KQrls+SfWfKaNH2xsbOg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 2968.125 | LABOR- SUBCONTRACTOR
%R | 500926 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3020 | Ceramic Wall Tiling | 8170 | 392 | 0 | 200 | 0 | 3534.75 | 3534.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-09 08:00 | 2014-05-07 17:00 |  | 2014-02-10 08:00 | 2014-03-11 17:00 | 2014-02-10 08:00 | 2014-03-11 17:00 | 2014-02-10 08:00 | 2014-03-11 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 |  | PT_Normal |  |  |  |  | 3uKLADNXQ5qDzkzivnQbHQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 1767.375 | TILE MASON SK
%R | 500927 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3025 | Porcelain Tile flooring | 8170 | 392 | 0 | 200 | 0 | 1918.75 | 1918.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-13 17:00 |  | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 |  | PT_Normal |  |  |  |  | 9dc2a9MUTIi1J7BnnIrCTQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 959.375 | TILE MASON SK
%R | 500928 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3040 | Cobble Tile flooring | 8170 | 456 | 0 | 120 | 0 | 700 | 700 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-21 08:00 | 2014-06-07 17:00 |  | 2014-03-16 08:00 | 2014-04-01 17:00 | 2014-03-16 08:00 | 2014-04-01 17:00 | 2014-03-16 08:00 | 2014-04-01 17:00 | 2014-05-21 08:00 | 2014-06-07 17:00 |  | PT_Normal |  |  |  |  | ch5fMYzeRsuwJawfYRJpZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 700 | TILE MASON SK
%R | 500929 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 472 | 16 | 120 | 0 | 931.25 | 931.25 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-02 17:00 |  | 2014-03-09 08:00 | 2014-03-25 17:00 | 2014-03-09 08:00 | 2014-03-25 17:00 | 2014-03-09 08:00 | 2014-03-25 17:00 | 2014-05-17 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | GvImFTiFSTeqWHKQHU3Hnw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 931.25 | TILE MASON SK
%R | 500930 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 456 | 0 | 160 | 0 | 850 | 850 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-29 08:00 | 2014-06-21 17:00 |  | 2014-03-24 08:00 | 2014-04-15 17:00 | 2014-03-24 08:00 | 2014-04-15 17:00 | 2014-03-24 08:00 | 2014-04-15 17:00 | 2014-05-29 08:00 | 2014-06-21 17:00 |  | PT_Normal |  |  |  |  | 5zw7gz1DTJ6n6In+LBClxg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 850 | GRANITE MASON SK
%R | 500931 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3045 | Fixing of Suspension systems | 8178 | 392 | 0 | 160 | 0 | 1320.5 | 1320.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-03 08:00 | 2014-05-25 17:00 |  | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-05-03 08:00 | 2014-05-25 17:00 |  | PT_Normal |  |  |  |  | oBh5U/pCSBqjACivyeH9eA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1320.5 | LABOR- SUBCONTRACTOR
%R | 500932 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3055 | Aluminum tile false ceiling | 8178 | 416 | 24 | 200 | 0 | 130 | 130 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-14 08:00 | 2014-06-11 17:00 |  | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 |  | PT_Normal |  |  |  |  | PspFmQieS1aBMLyIxpjyKQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 130 | LABOR- SUBCONTRACTOR
%R | 500933 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3060 | Gypsum board false ceiling | 8178 | 392 | 0 | 200 | 0 | 1216.3 | 1216.3 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-14 08:00 | 2014-06-11 17:00 |  | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 |  | PT_Normal |  |  |  |  | fP0A2UCUTB2BtDQ7xEVntA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1216.3 | LABOR- SUBCONTRACTOR
%R | 500934 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3065 | Wooden door & PVC Door | 8178 | 456 | 0 | 120 | 0 | 660 | 660 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-06-29 17:00 |  | 2014-04-07 08:00 | 2014-04-23 17:00 | 2014-04-07 08:00 | 2014-04-23 17:00 | 2014-04-07 08:00 | 2014-04-23 17:00 | 2014-06-12 08:00 | 2014-06-29 17:00 |  | PT_Normal |  |  |  |  | 0daKLYiRT+quj36fWUxpXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 660 | LABOR- SUBCONTRACTOR
%R | 500935 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3070 | Aluminum doors | 8178 | 456 | 0 | 120 | 0 | 88 | 88 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-18 08:00 | 2014-07-05 17:00 |  | 2014-04-13 08:00 | 2014-04-29 17:00 | 2014-04-13 08:00 | 2014-04-29 17:00 | 2014-04-13 08:00 | 2014-04-29 17:00 | 2014-06-18 08:00 | 2014-07-05 17:00 |  | PT_Normal |  |  |  |  | 1w4b5uNoQ1WqQXmUDj0MBA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 88 | LABOR- SUBCONTRACTOR
%R | 500936 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3080 | Aluminum windows | 8178 | 536 | 40 | 160 | 0 | 257.5 | 257.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-07 08:00 | 2014-07-29 17:00 |  | 2014-04-20 08:00 | 2014-05-12 17:00 | 2014-04-20 08:00 | 2014-05-12 17:00 | 2014-04-20 08:00 | 2014-05-12 17:00 | 2014-07-07 08:00 | 2014-07-29 17:00 |  | PT_Normal |  |  |  |  | Vrx0d7zcSCuuJY1ZN4+FdQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 257.5 | LABOR- SUBCONTRACTOR
%R | 500937 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3090 | Installation of Granite Counter Top | 8171 | 456 | 0 | 120 | 0 | 242 | 242 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-07 08:00 | 2014-07-23 17:00 |  | 2014-05-01 08:00 | 2014-05-18 17:00 | 2014-05-01 08:00 | 2014-05-18 17:00 | 2014-05-01 08:00 | 2014-05-18 17:00 | 2014-07-07 08:00 | 2014-07-23 17:00 |  | PT_Normal |  |  |  |  | VL0HtX2FSL6rQZGKjU4vWg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 242 | GRANITE MASON SK
%R | 500938 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3085 | S.S.Balustrade | 8178 | 496 | 40 | 160 | 0 | 175 | 175 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-08 08:00 | 2014-07-30 17:00 |  | 2014-04-27 08:00 | 2014-05-19 17:00 | 2014-04-27 08:00 | 2014-05-19 17:00 | 2014-04-27 08:00 | 2014-05-19 17:00 | 2014-07-08 08:00 | 2014-07-30 17:00 |  | PT_Normal |  |  |  |  | ZDSwb+ThSeKArX8ew6ViDQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 175 | LABOR- SUBCONTRACTOR
%R | 500939 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3095 | Final Painting | 8178 | 456 | 0 | 200 | 0 | 5936.25 | 5936.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | flKAUynyRv2u/RdR3XJKEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 5936.25 | LABOR- SUBCONTRACTOR
%R | 500940 | 6359 | 124537 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARGF3075 | Carpentry & Joinery Works | 8178 | 456 | 0 | 160 | 0 | 528 | 528 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-24 08:00 | 2014-07-16 17:00 |  | 2014-04-19 08:00 | 2014-05-11 17:00 | 2014-04-19 08:00 | 2014-05-11 17:00 | 2014-04-19 08:00 | 2014-05-11 17:00 | 2014-06-24 08:00 | 2014-07-16 17:00 |  | PT_Normal |  |  |  |  | PhbzBchfTqmlrv9muuCZWA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35460 | N | N | 10 | GROUND FLOOR |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 528 | LABOR- SUBCONTRACTOR
%R | 500941 | 6359 | 124538 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARRF3600 | Block work | 8168 | 624 | 0 | 160 | 0 | 697.25 | 697.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-25 08:00 | 2014-06-16 17:00 |  | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-05-25 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | 8H1R8lzlQLSR9NHouMk4tA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35480 | N | N | 20 | ROOF |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 697.25 | BLOCK MASON SK
%R | 500942 | 6359 | 124538 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARRF3605 | Plastering work | 8169 | 624 | 0 | 160 | 0 | 3833 | 3833 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-06-28 17:00 |  | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-06-05 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | 5tFIkmbOQ/WiEKqFdaFoaQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35480 | N | N | 20 | ROOF |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 3833 | PLASTER MASON SK
%R | 500943 | 6359 | 124538 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARRF3610 | Flooring screed | 8164 | 624 | 0 | 120 | 0 | 154 | 154 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-23 08:00 | 2014-07-09 17:00 |  | 2014-03-24 08:00 | 2014-04-09 17:00 | 2014-03-24 08:00 | 2014-04-09 17:00 | 2014-03-24 08:00 | 2014-04-09 17:00 | 2014-06-23 08:00 | 2014-07-09 17:00 |  | PT_Normal |  |  |  |  | yravlzr9SpaY6Kjfw0wRBQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35480 | N | N | 20 | ROOF |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 154 | SCREED MASON SK
%R | 500944 | 6359 | 124538 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARRF3695 | Painting -Storage area | 8178 | 624 | 0 | 160 | 0 | 1640 | 1640 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-05 08:00 | 2014-07-27 17:00 |  | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-07-05 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | C1mYJiMuT6eLsGXlm3qsAQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35480 | N | N | 20 | ROOF |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1640 | LABOR- SUBCONTRACTOR
%R | 500945 | 6359 | 124538 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ARRF3620 | Epoxy Painting -Storage area | 8178 | 624 | 0 | 120 | 0 | 48.5 | 48.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-22 08:00 | 2014-08-11 17:00 |  | 2014-04-22 08:00 | 2014-05-08 17:00 | 2014-04-22 08:00 | 2014-05-08 17:00 | 2014-04-22 08:00 | 2014-05-08 17:00 | 2014-07-22 08:00 | 2014-08-11 17:00 |  | PT_Normal |  |  |  |  | o3mcdyLaTqq0WPBWPhL69A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35480 | N | N | 20 | ROOF |  | 124535 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 48.5 | LABOR- SUBCONTRACTOR
%R | 500946 | 6359 | 124539 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 24 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-08-14 08:00 | 2014-09-11 17:00 | 2014-08-14 08:00 | 2014-09-11 17:00 | 2014-08-14 08:00 | 2014-09-11 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | 0S6JgYoNRPC6ULHV5AQRVQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35710 | N | N | 30 | TESTING AND COMMISSIONING |  | 124523 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 500947 | 6359 | 124539 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 24 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-08-14 08:00 | 2014-09-11 17:00 | 2014-08-14 08:00 | 2014-09-11 17:00 | 2014-08-14 08:00 | 2014-09-11 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | JOg2Epd5TZahR1M5Z22j3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35710 | N | N | 30 | TESTING AND COMMISSIONING |  | 124523 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 500948 | 6359 | 124539 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 24 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-08-14 08:00 | 2014-09-11 17:00 | 2014-08-14 08:00 | 2014-09-11 17:00 | 2014-08-14 08:00 | 2014-09-11 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | uoNUk/PtQHWm3VqVTWdm5w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35710 | N | N | 30 | TESTING AND COMMISSIONING |  | 124523 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 500949 | 6359 | 124542 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 128 | 0 | 200 | 0 | 2579.2 | 2579.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-03 08:00 | 2014-03-31 17:00 |  | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | 9anm/Xl5SWuYNuX2ZWpUhw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35550 | N | N | 15 | FIRST FLOORS |  | 124541 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 1289.6 | LABOR- SUBCONTRACTOR
%R | 500950 | 6359 | 124542 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ELFF4040 | Cable tray & trunking installation | 8178 | 368 | 0 | 160 | 0 | 3180.8 | 3180.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-19 08:00 | 2014-05-11 17:00 |  | 2014-02-24 08:00 | 2014-03-18 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 | 2014-04-19 08:00 | 2014-05-11 17:00 |  | PT_Normal |  |  |  |  | kEgThC29S+qzmhNbMBWN/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35550 | N | N | 15 | FIRST FLOORS |  | 124541 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 3180.8 | LABOR- SUBCONTRACTOR
%R | 500951 | 6359 | 124542 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ELFF4045 | Installation of wiring & Main Cabling | 8178 | 368 | 0 | 200 | 0 | 636.8 | 636.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-27 08:00 | 2014-05-25 17:00 |  | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 |  | PT_Normal |  |  |  |  | S7K3p0n5RWyxvKH06lr3/Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35550 | N | N | 15 | FIRST FLOORS |  | 124541 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 636.8 | LABOR- SUBCONTRACTOR
%R | 500952 | 6359 | 124542 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 24 | 0 | 160 | 0 | 454.4 | 454.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-04 08:00 | 2014-06-26 17:00 |  | 2014-06-01 08:00 | 2014-06-23 17:00 | 2014-06-01 08:00 | 2014-06-23 17:00 | 2014-06-01 08:00 | 2014-06-23 17:00 | 2014-06-04 08:00 | 2014-06-26 17:00 |  | PT_Normal |  |  |  |  | MVenBCNrT5+sMbEic6U7RA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35550 | N | N | 15 | FIRST FLOORS |  | 124541 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 454.4 | LABOR- SUBCONTRACTOR
%R | 500953 | 6359 | 124542 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 24 | 0 | 200 | 0 | 3302.4 | 3302.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | HiRaln6zRpiVD5c+mQy6FQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35550 | N | N | 15 | FIRST FLOORS |  | 124541 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 3302.4 | LABOR- SUBCONTRACTOR
%R | 500954 | 6359 | 124542 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 360 | 0 | 200 | 0 | 4569.6 | 4569.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-05-25 08:00 | 2014-06-22 17:00 | 2014-05-25 08:00 | 2014-06-22 17:00 | 2014-05-25 08:00 | 2014-06-22 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | lc9WrvLXQ++p/7qzMQPCgQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35550 | N | N | 15 | FIRST FLOORS |  | 124541 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 4569.6 | LABOR- SUBCONTRACTOR
%R | 500955 | 6359 | 124542 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ELFF4050 | Installation of Telephone System | 8178 | 200 | 176 | 200 | 0 | 1422.4 | 1422.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-21 08:00 | 2014-07-19 17:00 |  | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-06-21 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | TJDUFwsrQlOaOnnmiDC5mA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35550 | N | N | 15 | FIRST FLOORS |  | 124541 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1422.4 | LABOR- SUBCONTRACTOR
%R | 500956 | 6359 | 124543 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 464 | 0 | 200 | 0 | 2579.2 | 2579.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-04-08 17:00 |  | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | u26nUwy2QOunl+FiT97mOg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35540 | N | N | 10 | GROUND FLOOR |  | 124541 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 2579.2 | LABOR- SUBCONTRACTOR
%R | 500957 | 6359 | 124543 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ELGF4005 | Cable tray & trunking installation | 8178 | 608 | 0 | 160 | 0 | 3180.8 | 3180.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-13 08:00 | 2014-05-05 17:00 |  | 2014-01-13 08:00 | 2014-02-04 17:00 | 2014-01-13 08:00 | 2014-02-04 17:00 | 2014-01-13 08:00 | 2014-02-04 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | z7+wDjL1R++s0eeINZ5MnQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35540 | N | N | 10 | GROUND FLOOR |  | 124541 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 3180.8 | LABOR- SUBCONTRACTOR
%R | 500958 | 6359 | 124543 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ELGF4010 | Installation of wiring & Main Cabling | 8178 | 608 | 216 | 200 | 0 | 636.8 | 636.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-21 08:00 | 2014-05-19 17:00 |  | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | Hfoxf67TQOCmW8jxON7tUw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35540 | N | N | 10 | GROUND FLOOR |  | 124541 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 636.8 | LABOR- SUBCONTRACTOR
%R | 500959 | 6359 | 124543 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 392 | 0 | 160 | 0 | 454.4 | 454.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-19 17:00 |  | 2014-04-01 08:00 | 2014-04-23 17:00 | 2014-04-01 08:00 | 2014-04-23 17:00 | 2014-04-01 08:00 | 2014-04-23 17:00 | 2014-05-28 08:00 | 2014-06-19 17:00 |  | PT_Normal |  |  |  |  | Fhx05GBhRSGwrzNK+3do2A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35540 | N | N | 10 | GROUND FLOOR |  | 124541 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 454.4 | LABOR- SUBCONTRACTOR
%R | 500960 | 6359 | 124543 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 568 | 0 | 200 | 0 | 4569.6 | 4569.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | Pin+sHW8TPOmz7c56Xmq6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35540 | N | N | 10 | GROUND FLOOR |  | 124541 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 4569.6 | LABOR- SUBCONTRACTOR
%R | 500961 | 6359 | 124543 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ELGF4030 | Installation of Telephone System | 8178 | 392 | 40 | 160 | 0 | 1422.4 | 1422.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-07-01 17:00 |  | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-06-09 08:00 | 2014-07-01 17:00 |  | PT_Normal |  |  |  |  | /bo8lYQhTqeDd/KzClEM6g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35540 | N | N | 10 | GROUND FLOOR |  | 124541 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1422.4 | LABOR- SUBCONTRACTOR
%R | 500962 | 6359 | 124543 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 408 | 0 | 200 | 0 | 3302.4 | 3302.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-07-09 17:00 |  | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-06-11 08:00 | 2014-07-09 17:00 |  | PT_Normal |  |  |  |  | GK5EnYgeTsy505dKhi+Ayg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35540 | N | N | 10 | GROUND FLOOR |  | 124541 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 3302.4 | LABOR- SUBCONTRACTOR
%R | 500963 | 6359 | 124544 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ELRF4070 | Installation of Isolator | 8178 | 24 | 0 | 144 | 0 | 825.6 | 825.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-07-07 08:00 | 2014-07-27 17:00 |  | 2014-07-03 08:00 | 2014-07-23 17:00 | 2014-07-03 08:00 | 2014-07-23 17:00 | 2014-07-03 08:00 | 2014-07-23 17:00 | 2014-07-07 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | VZjS19f5TeWHuD2iQ+oKYw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35560 | N | N | 20 | ROOF |  | 124541 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 825.6 | LABOR- SUBCONTRACTOR
%R | 500964 | 6359 | 124544 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ELRF4075 | Installation of TV Dish Antenna | 8178 | 24 | 0 | 184 | 0 | 1830.4 | 1830.4 | 184 | 0 | 0 | 0 |  |  |  | 2014-07-19 08:00 | 2014-08-17 17:00 |  | 2014-07-15 08:00 | 2014-08-13 17:00 | 2014-07-15 08:00 | 2014-08-13 17:00 | 2014-07-15 08:00 | 2014-08-13 17:00 | 2014-07-19 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | 1czXAreLRBKuJtqUYh0Sfw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35560 | N | N | 20 | ROOF |  | 124541 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1830.4 | LABOR- SUBCONTRACTOR
%R | 500965 | 6359 | 124546 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ACFF4615 | Installation AC Pipes | 8178 | 368 | 24 | 160 | 0 | 1886.4 | 1886.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-12 08:00 | 2014-06-03 17:00 |  | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-05-12 08:00 | 2014-06-03 17:00 |  | PT_Normal |  |  |  |  | 39SRotC4S1eGexPumMZZQA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35630 | N | N | 15 | FIRST FLOORS |  | 124545 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1886.4 | LABOR- SUBCONTRACTOR
%R | 500966 | 6359 | 124546 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ACFF4620 | Fixing of Ventilation Equipments | 8178 | 136 | 0 | 200 | 0 | 182.4 | 182.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-14 08:00 | 2014-07-12 17:00 |  | 2014-05-25 08:00 | 2014-06-22 17:00 | 2014-05-25 08:00 | 2014-06-22 17:00 | 2014-05-25 08:00 | 2014-06-22 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 |  | PT_Normal |  |  |  |  | V7uperobScmmIBxRNI7Z1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35630 | N | N | 15 | FIRST FLOORS |  | 124545 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 182.4 | LABOR- SUBCONTRACTOR
%R | 500967 | 6359 | 124546 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ACFF4625 | Fixing of Split AC | 8178 | 136 | 0 | 160 | 0 | 568 | 568 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-05 08:00 | 2014-07-27 17:00 |  | 2014-06-15 08:00 | 2014-07-07 17:00 | 2014-06-15 08:00 | 2014-07-07 17:00 | 2014-06-15 08:00 | 2014-07-07 17:00 | 2014-07-05 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | sh5h/3l2TPyJA3s8h6qBwg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35630 | N | N | 15 | FIRST FLOORS |  | 124545 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 568 | LABOR- SUBCONTRACTOR
%R | 500968 | 6359 | 124547 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ACRF4630 | Installation of Refrigerant Pipes | 8178 | 696 | 0 | 200 | 0 | 795.2 | 795.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-10 08:00 | 2014-08-11 17:00 |  | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-07-10 08:00 | 2014-08-11 17:00 |  | PT_Normal |  |  |  |  | eQer5z+oRBq5qt0ygMdMeQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35640 | N | N | 20 | ROOF |  | 124545 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 795.2 | LABOR- SUBCONTRACTOR
%R | 500969 | 6359 | 124547 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ACRF4635 | Installation of Condensing Unit | 8178 | 176 | 0 | 200 | 0 | 1136 | 1136 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-06-21 08:00 | 2014-07-19 17:00 | 2014-06-21 08:00 | 2014-07-19 17:00 | 2014-06-21 08:00 | 2014-07-19 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | VuVsFLgATiG1HpJPN5XXNg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35640 | N | N | 20 | ROOF |  | 124545 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1136 | LABOR- SUBCONTRACTOR
%R | 500970 | 6359 | 124548 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ACGF4600 | Installation AC Pipes | 8178 | 640 | 40 | 160 | 0 | 1886.4 | 1886.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-06 08:00 | 2014-05-28 17:00 |  | 2014-02-01 08:00 | 2014-02-24 17:00 | 2014-02-01 08:00 | 2014-02-24 17:00 | 2014-02-01 08:00 | 2014-02-24 17:00 | 2014-05-06 08:00 | 2014-05-28 17:00 |  | PT_Normal |  |  |  |  | JIVlid/WSgSk8XH9g7RYzw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35620 | N | N | 10 | GROUND FLOOR |  | 124545 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1886.4 | LABOR- SUBCONTRACTOR
%R | 500971 | 6359 | 124548 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ACGF4605 | Fixing of Ventilation Equipments | 8178 | 544 | 0 | 200 | 0 | 296 | 296 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-14 08:00 | 2014-07-12 17:00 |  | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 |  | PT_Normal |  |  |  |  | eoL0106aT3WMcD7xJG4B7w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35620 | N | N | 10 | GROUND FLOOR |  | 124545 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 296 | LABOR- SUBCONTRACTOR
%R | 500972 | 6359 | 124548 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3ACGF4610 | Fixing of Split AC | 8178 | 544 | 40 | 160 | 0 | 568 | 568 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-05 08:00 | 2014-07-27 17:00 |  | 2014-04-16 08:00 | 2014-05-08 17:00 | 2014-04-16 08:00 | 2014-05-08 17:00 | 2014-04-16 08:00 | 2014-05-08 17:00 | 2014-07-05 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | 2OEooebHTWGiIZ59lSXy+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35620 | N | N | 10 | GROUND FLOOR |  | 124545 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 568 | LABOR- SUBCONTRACTOR
%R | 500973 | 6359 | 124550 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3PLFF4335 | Sanitary Fittings & Accessories | 8178 | 152 | 0 | 160 | 0 | 201.6 | 201.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-21 17:00 |  | 2014-06-07 08:00 | 2014-06-29 17:00 | 2014-06-07 08:00 | 2014-06-29 17:00 | 2014-06-07 08:00 | 2014-06-29 17:00 | 2014-06-29 08:00 | 2014-07-21 17:00 |  | PT_Normal |  |  |  |  | rRdEqxQBTASP8eo+9gPrNA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35590 | N | N | 15 | FIRST FLOORS |  | 124549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 201.6 | LABOR- SUBCONTRACTOR
%R | 500974 | 6359 | 124550 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3PLFF4340 | Installation of Water Heater | 8178 | 152 | 0 | 120 | 0 | 134.4 | 134.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-10 08:00 | 2014-07-27 17:00 |  | 2014-06-18 08:00 | 2014-07-05 17:00 | 2014-06-18 08:00 | 2014-07-05 17:00 | 2014-06-18 08:00 | 2014-07-05 17:00 | 2014-07-10 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | uaSXlEz2RsyRXSzR6Bop/Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35590 | N | N | 15 | FIRST FLOORS |  | 124549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 500975 | 6359 | 124550 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3PLFF4330 | Installation of Drainage pipes & testing | 8178 | 240 | 56 | 144 | 0 | 331.2 | 331.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-20 17:00 |  | 2014-02-24 08:00 | 2014-03-16 17:00 | 2014-02-24 08:00 | 2014-03-16 17:00 | 2014-02-24 08:00 | 2014-03-16 17:00 | 2014-03-31 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | b7VKl9zhTmuXrbWc19T77g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35590 | N | N | 15 | FIRST FLOORS |  | 124549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 331.2 | LABOR- SUBCONTRACTOR
%R | 500976 | 6359 | 124550 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 24 | 0 | 144 | 0 | 883.2 | 883.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-27 08:00 | 2014-03-19 17:00 |  | 2014-02-24 08:00 | 2014-03-16 17:00 | 2014-02-24 08:00 | 2014-03-16 17:00 | 2014-02-24 08:00 | 2014-03-16 17:00 | 2014-02-27 08:00 | 2014-03-19 17:00 |  | PT_Normal |  |  |  |  | TibDeaBTRxWJ7+rA5MiW6w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35590 | N | N | 15 | FIRST FLOORS |  | 124549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 883.2 | LABOR- SUBCONTRACTOR
%R | 500977 | 6359 | 124551 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 672 | 40 | 112 | 0 | 288 | 288 | 112 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-14 17:00 |  | 2014-03-23 08:00 | 2014-04-07 17:00 | 2014-03-23 08:00 | 2014-04-07 17:00 | 2014-03-23 08:00 | 2014-04-07 17:00 | 2014-06-29 08:00 | 2014-07-14 17:00 |  | PT_Normal |  |  |  |  | wdYqplbJQx2NyFxLP9vQKg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35600 | N | N | 20 | ROOF |  | 124549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 288 | LABOR- SUBCONTRACTOR
%R | 500978 | 6359 | 124551 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3PLRF4350 | Installation of Rain water Pipes |  | 632 | 80 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-10 08:00 | 2014-07-27 17:00 |  | 2014-04-09 08:00 | 2014-04-26 17:00 | 2014-04-09 08:00 | 2014-04-26 17:00 | 2014-04-09 08:00 | 2014-04-26 17:00 | 2014-07-10 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | kwAK6NnQRCGJoVuWTIOr2w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 35600 | N | N | 20 | ROOF |  | 124549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 0 | 0
%R | 500979 | 6359 | 124551 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 152 | 0 | 200 | 0 | 672 | 672 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-06-24 08:00 | 2014-07-22 17:00 | 2014-06-24 08:00 | 2014-07-22 17:00 | 2014-06-24 08:00 | 2014-07-22 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | 3JdpT3PpQcyzi8zcTJM2/w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35600 | N | N | 20 | ROOF |  | 124549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 672 | LABOR- SUBCONTRACTOR
%R | 500980 | 6359 | 124552 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 392 | 0 | 144 | 0 | 883.2 | 883.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-03-31 17:00 |  | 2014-01-12 08:00 | 2014-02-01 17:00 | 2014-01-12 08:00 | 2014-02-01 17:00 | 2014-01-12 08:00 | 2014-02-01 17:00 | 2014-03-11 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | nhjoN/EXRISy61Omv5AU0w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35580 | N | N | 10 | GROUND FLOOR |  | 124549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 883.2 | LABOR- SUBCONTRACTOR
%R | 500981 | 6359 | 124552 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3PLGF4310 | Installation of Drainage pipes &testing | 8178 | 416 | 112 | 144 | 0 | 331.2 | 331.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-03 17:00 |  | 2014-01-12 08:00 | 2014-02-01 17:00 | 2014-01-12 08:00 | 2014-02-01 17:00 | 2014-01-12 08:00 | 2014-02-01 17:00 | 2014-03-15 08:00 | 2014-04-03 17:00 |  | PT_Normal |  |  |  |  | GT8Ynvi1QiCnRbUV0aPk+A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35580 | N | N | 10 | GROUND FLOOR |  | 124549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 331.2 | LABOR- SUBCONTRACTOR
%R | 500982 | 6359 | 124552 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3PLGF4315 | Sanitary Fittings & Accessories | 8178 | 648 | 0 | 160 | 0 | 201.6 | 201.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-11 17:00 |  | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-07-16 08:00 | 2014-08-11 17:00 |  | PT_Normal |  |  |  |  | WidW4oa1RJm4kQ+HpJspyA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35580 | N | N | 10 | GROUND FLOOR |  | 124549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 201.6 | LABOR- SUBCONTRACTOR
%R | 500983 | 6359 | 124552 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3PLGF4320 | Installation of Water Heater | 8178 | 648 | 80 | 120 | 0 | 201.6 | 201.6 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-28 08:00 | 2014-08-17 17:00 |  | 2014-04-24 08:00 | 2014-05-11 17:00 | 2014-04-24 08:00 | 2014-05-11 17:00 | 2014-04-24 08:00 | 2014-05-11 17:00 | 2014-07-28 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | 9U3BwB+bTo2OQBqMqEsbHA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35580 | N | N | 10 | GROUND FLOOR |  | 124549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 201.6 | LABOR- SUBCONTRACTOR
%R | 500984 | 6359 | 124552 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 88 | 0 | 160 | 0 | 110.4 | 110.4 | 160 | 0 | 0 | 0 |  |  |  | 2013-10-07 08:00 | 2013-10-31 17:00 |  | 2013-09-24 08:00 | 2013-10-16 17:00 | 2013-09-24 08:00 | 2013-10-16 17:00 | 2013-09-24 08:00 | 2013-10-16 17:00 | 2013-10-07 08:00 | 2013-10-31 17:00 |  | PT_Normal |  |  |  |  | PayMLe9AT+CAguOlDZ5MtQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35580 | N | N | 10 | GROUND FLOOR |  | 124549 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 110.4 | LABOR- SUBCONTRACTOR
%R | 500985 | 6359 | 124554 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3HDEX5090 | kerb works | 8173 | 568 | 0 | 160 | 0 | 712 | 712 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-27 08:00 | 2014-06-18 17:00 |  | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-05-27 08:00 | 2014-06-18 17:00 |  | PT_Normal |  |  |  |  | WfsDDK6DR2e5N+8GkTKWnQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35690 | N | N | 20 | HARD LANDSCAPING |  | 124553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 712 | KERBSTONE MASON SK
%R | 500986 | 6359 | 124554 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3HDEX5095 | Cobble Stone Works | 8170 | 568 | 0 | 160 | 0 | 456 | 456 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-08 08:00 | 2014-06-30 17:00 |  | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-06-08 08:00 | 2014-06-30 17:00 |  | PT_Normal |  |  |  |  | OZoFPosvTe+uObc2xp102Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35690 | N | N | 20 | HARD LANDSCAPING |  | 124553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 456 | TILE MASON SK
%R | 500987 | 6359 | 124554 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3HDEX5100 | Interlock works | 8174 | 568 | 0 | 160 | 0 | 408 | 408 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-23 08:00 | 2014-07-15 17:00 |  | 2014-04-01 08:00 | 2014-04-23 17:00 | 2014-04-01 08:00 | 2014-04-23 17:00 | 2014-04-01 08:00 | 2014-04-23 17:00 | 2014-06-23 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | tFjPskNTQUuaqzyDrA+GsQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35690 | N | N | 20 | HARD LANDSCAPING |  | 124553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 408 | INTERLOCK MASON SK
%R | 500988 | 6359 | 124555 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 200 | 0 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | zybxU8PbSr6AjLalqJvjXQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35670 | N | N | 10 | MISCELLANEOUS |  | 124553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 200 | LABOR- SUBCONTRACTOR
%R | 500989 | 6359 | 124555 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3MSEX5020 | Construction Entrance Ramp | 8164 | 552 | 0 | 200 | 0 | 1288 | 1288 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-27 17:00 |  | 2014-02-06 08:00 | 2014-03-08 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | AkQQH1QkQbm/lFQfnKBAEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35670 | N | N | 10 | MISCELLANEOUS |  | 124553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 644 | SCREED MASON SK
%R | 500990 | 6359 | 124555 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3MSEX5025 | SS.Handrails and Balustrades | 8178 | 568 | 0 | 160 | 0 | 400 | 400 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-10 17:00 |  | 2014-02-25 08:00 | 2014-03-19 17:00 | 2014-02-25 08:00 | 2014-03-19 17:00 | 2014-02-25 08:00 | 2014-03-19 17:00 | 2014-05-19 08:00 | 2014-06-10 17:00 |  | PT_Normal |  |  |  |  | 5KyqQ+SxRHWBNx42yIqBqg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35670 | N | N | 10 | MISCELLANEOUS |  | 124553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 400 | LABOR- SUBCONTRACTOR
%R | 500991 | 6359 | 124555 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3MSEX5015 | Construction of grease Trap | 8178 | 304 | 0 | 160 | 0 | 88 | 88 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-21 17:00 |  | 2014-03-16 08:00 | 2014-04-07 17:00 | 2014-03-16 08:00 | 2014-04-07 17:00 | 2014-03-16 08:00 | 2014-04-07 17:00 | 2014-04-29 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | TloaUZzZRGCmu8/cAODR3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35670 | N | N | 10 | MISCELLANEOUS |  | 124553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 88 | LABOR- SUBCONTRACTOR
%R | 500992 | 6359 | 124555 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3MSEX5000 | Construction of Manholes | 8172 | 304 | 0 | 200 | 0 | 880 | 880 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-26 08:00 | 2014-04-23 17:00 |  | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 |  | PT_Normal |  |  |  |  | EsWowOOoRmyPeoDZO5p03w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35670 | N | N | 10 | MISCELLANEOUS |  | 124553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 440 | MANHOLES SK
%R | 500993 | 6359 | 124555 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3MSEX5005 | Construction of Soak pit, Chambers | 8172 | 304 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-09 08:00 | 2014-05-07 17:00 |  | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 |  | PT_Normal |  |  |  |  | vSJt85T3Qz+JBlha9R7oWQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35670 | N | N | 10 | MISCELLANEOUS |  | 124553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 88 | MANHOLES SK
%R | 500994 | 6359 | 124555 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3MSEX5010 | Telephone cable laying | 8177 | 304 | 104 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-22 08:00 | 2014-06-19 17:00 |  | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 |  | PT_Normal |  |  |  |  | VEbF5klkQauA9UimGgqrIQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35670 | N | N | 10 | MISCELLANEOUS |  | 124553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 500 | LABOR - CIVIL
%R | 500995 | 6359 | 124556 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3SLEX5105 | Laying of Grass/ green area | 8178 | 568 | 0 | 200 | 0 | 5488 | 5488 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-05 08:00 | 2014-08-05 17:00 |  | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-07-05 08:00 | 2014-08-05 17:00 |  | PT_Normal |  |  |  |  | nyr3EXNETaC+EjeEMV0JvQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35700 | N | N | 25 | SOFT LANDSCAPING |  | 124553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 5488 | LABOR- SUBCONTRACTOR
%R | 500996 | 6359 | 124556 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3SLEX5110 | Laying of Palm tree | 8178 | 568 | 544 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | pLK9j31jTE2FoPwM6o9WtQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35700 | N | N | 25 | SOFT LANDSCAPING |  | 124553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 336 | LABOR- SUBCONTRACTOR
%R | 500997 | 6359 | 124557 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3WEEX5030 | Excavation | 8177 | 408 | 0 | 160 | 0 | 128 | 128 | 160 | 80 | 0 | 80 |  |  |  | 2014-04-22 08:00 | 2014-05-14 17:00 |  | 2014-02-22 08:00 | 2014-03-16 17:00 | 2014-02-22 08:00 | 2014-03-16 17:00 | 2014-02-22 08:00 | 2014-03-16 17:00 | 2014-04-22 08:00 | 2014-05-14 17:00 |  | PT_Normal |  |  |  |  | vpCghBjxQOWCgcD6/O5s8w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35680 | N | N | 15 | WATER TANK ENCLOSURE |  | 124553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 128 | LABOR - CIVIL
%R | 500998 | 6359 | 124557 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3WEEX5035 | Construction of Raft | 8165 | 408 | 0 | 200 | 0 | 1624 | 1624 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-04 08:00 | 2014-06-01 17:00 |  | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 |  | PT_Normal |  |  |  |  | Ap9yjlAySV6lG34XpEavRQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35680 | N | N | 15 | WATER TANK ENCLOSURE |  | 124553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1624 | STEEL FIXERS SK
%R | 500999 | 6359 | 124557 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3WEEX5040 | Block works & Plastering | 8168 | 528 | 0 | 200 | 0 | 888 | 888 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-31 08:00 | 2014-06-28 17:00 |  | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | FsWZlTSCR1qoiibQ/76g+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35680 | N | N | 15 | WATER TANK ENCLOSURE |  | 124553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 888 | BLOCK MASON SK
%R | 501000 | 6359 | 124557 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3WEEX5045 | Flooring & Painting | 8178 | 528 | 0 | 200 | 0 | 408 | 408 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-07-09 17:00 |  | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-06-11 08:00 | 2014-07-09 17:00 |  | PT_Normal |  |  |  |  | bc3sjxVMRuq4oBxq3l+Tfw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35680 | N | N | 15 | WATER TANK ENCLOSURE |  | 124553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 408 | LABOR- SUBCONTRACTOR
%R | 501001 | 6359 | 124557 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3WEEX5050 | Installation of Steel Gate | 8178 | 528 | 0 | 160 | 0 | 112 | 112 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-21 17:00 |  | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-06-29 08:00 | 2014-07-21 17:00 |  | PT_Normal |  |  |  |  | YKd7TyWrT82tHv3GKmXmag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35680 | N | N | 15 | WATER TANK ENCLOSURE |  | 124553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 112 | LABOR- SUBCONTRACTOR
%R | 501002 | 6359 | 124557 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 528 | 0 | 200 | 0 | 616 | 616 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-05 08:00 | 2014-08-05 17:00 |  | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-07-05 08:00 | 2014-08-05 17:00 |  | PT_Normal |  |  |  |  | ZxER32NQSxmcFwvG4xPuwg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35680 | N | N | 15 | WATER TANK ENCLOSURE |  | 124553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 616 | LABOR- SUBCONTRACTOR
%R | 501003 | 6359 | 124557 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ3WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 528 | 96 | 200 | 0 | 382.4 | 382.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | f0XFR/4EReyXb/ICQ2D0uA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 35680 | N | N | 15 | WATER TANK ENCLOSURE |  | 124553 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 382.4 | LABOR- SUBCONTRACTOR
%R | 501004 | 6359 | 124561 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ACRF4630 | Installation of Refrigerant Pipes | 8178 | 696 | 0 | 200 | 0 | 795.2 | 795.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-06-10 17:00 |  | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-05-13 08:00 | 2014-06-10 17:00 |  | PT_Normal |  |  |  |  | Jd44Ywy+RF2c63P8JTm48Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34920 | N | N | 20 | ROOF |  | 124560 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01; period 2: 2014-AP03 |  | 397.6 | LABOR- SUBCONTRACTOR
%R | 501005 | 6359 | 124561 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ACRF4635 | Installation of Condensing Unit | 8178 | 176 | 0 | 200 | 0 | 1136 | 1136 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | yk8V0UbiTrOJvOCOfRqz0A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34920 | N | N | 20 | ROOF |  | 124560 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1136 | LABOR- SUBCONTRACTOR
%R | 501006 | 6359 | 124562 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ACGF4600 | Installation AC Pipes | 8178 | 648 | 40 | 160 | 0 | 1886.4 | 1886.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-03-31 17:00 |  | 2013-12-02 08:00 | 2013-12-25 17:00 | 2013-12-02 08:00 | 2013-12-25 17:00 | 2013-12-02 08:00 | 2013-12-25 17:00 | 2014-03-09 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | tysEgvc3RvK5ZhUC0YCVmg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34900 | N | N | 10 | GROUND FLOOR |  | 124560 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1886.4 | LABOR- SUBCONTRACTOR
%R | 501007 | 6359 | 124562 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ACGF4605 | Fixing of Ventilation Equipments | 8178 | 552 | 0 | 200 | 0 | 296 | 296 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-16 08:00 | 2014-05-14 17:00 |  | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 |  | PT_Normal |  |  |  |  | Ran59yWYRPiGsLPrX0+nGA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34900 | N | N | 10 | GROUND FLOOR |  | 124560 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 296 | LABOR- SUBCONTRACTOR
%R | 501008 | 6359 | 124562 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ACGF4610 | Fixing of Split AC | 8178 | 552 | 40 | 160 | 0 | 568 | 568 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-07 08:00 | 2014-05-29 17:00 |  | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-05-07 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | QqkE/kBMTP2PDDaktBQUOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34900 | N | N | 10 | GROUND FLOOR |  | 124560 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 568 | LABOR- SUBCONTRACTOR
%R | 501009 | 6359 | 124563 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ACFF4615 | Installation AC Pipes | 8178 | 368 | 0 | 160 | 0 | 1886.4 | 1886.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-06 17:00 |  | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | dMmXTUtAQPeoI6uQpn6ojQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34910 | N | N | 15 | FIRST FLOORS |  | 124560 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1886.4 | LABOR- SUBCONTRACTOR
%R | 501010 | 6359 | 124563 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ACFF4620 | Fixing of Ventilation Equipments | 8178 | 136 | 0 | 200 | 0 | 182.4 | 182.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-16 08:00 | 2014-05-14 17:00 |  | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 |  | PT_Normal |  |  |  |  | hPZzEdH9T4GCTaVaHYgnxw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34910 | N | N | 15 | FIRST FLOORS |  | 124560 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 182.4 | LABOR- SUBCONTRACTOR
%R | 501011 | 6359 | 124563 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ACFF4625 | Fixing of Split AC | 8178 | 136 | 0 | 160 | 0 | 568 | 568 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-07 08:00 | 2014-05-29 17:00 |  | 2014-04-17 08:00 | 2014-05-10 17:00 | 2014-04-17 08:00 | 2014-05-10 17:00 | 2014-04-17 08:00 | 2014-05-10 17:00 | 2014-05-07 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | yiFp6typS1mipR3lGWDF4g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34910 | N | N | 15 | FIRST FLOORS |  | 124560 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 568 | LABOR- SUBCONTRACTOR
%R | 501012 | 6359 | 124565 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 360 | 0 | 200 | 0 | 4569.6 | 4569.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | d34cImv7To6Qh+BlY72dwQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34830 | N | N | 15 | FIRST FLOORS |  | 124564 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 4569.6 | LABOR- SUBCONTRACTOR
%R | 501013 | 6359 | 124565 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ELFF4050 | Installation of Telephone System | 8178 | 200 | 176 | 200 | 0 | 1422.4 | 1422.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-05-21 17:00 |  | 2014-03-25 08:00 | 2014-04-22 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | DLqIR3/bTUe6rO3s9X2r3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34830 | N | N | 15 | FIRST FLOORS |  | 124564 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1422.4 | LABOR- SUBCONTRACTOR
%R | 501014 | 6359 | 124565 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ELFF4040 | Cable tray & trunking installation | 8178 | 368 | 0 | 160 | 0 | 3180.8 | 3180.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-19 08:00 | 2014-03-13 17:00 |  | 2013-12-26 08:00 | 2014-01-18 17:00 | 2013-12-26 08:00 | 2014-01-18 17:00 | 2013-12-26 08:00 | 2014-01-18 17:00 | 2014-02-19 08:00 | 2014-03-13 17:00 |  | PT_Normal |  |  |  |  | JiU2UuAqSI+PfPCraC/kCA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34830 | N | N | 15 | FIRST FLOORS |  | 124564 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 3180.8 | LABOR- SUBCONTRACTOR
%R | 501015 | 6359 | 124565 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 128 | 0 | 200 | 0 | 2579.2 | 2579.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-02 08:00 | 2014-01-30 17:00 |  | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 |  | PT_Normal |  |  |  |  | vuRY54t2T5akX4zI9TMbKg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34830 | N | N | 15 | FIRST FLOORS |  | 124564 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 2579.2 | LABOR- SUBCONTRACTOR
%R | 501016 | 6359 | 124565 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ELFF4045 | Installation of wiring & Main Cabling | 8178 | 368 | 0 | 200 | 0 | 636.8 | 636.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-27 08:00 | 2014-03-27 17:00 |  | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 |  | PT_Normal |  |  |  |  | ggHtC+IQSt2RwGQQdZBQaA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34830 | N | N | 15 | FIRST FLOORS |  | 124564 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 636.8 | LABOR- SUBCONTRACTOR
%R | 501017 | 6359 | 124565 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 24 | 0 | 160 | 0 | 454.4 | 454.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-07 08:00 | 2014-04-29 17:00 |  | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-04-07 08:00 | 2014-04-29 17:00 |  | PT_Normal |  |  |  |  | eml5G6ExRvS9ydGGC0z0mg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34830 | N | N | 15 | FIRST FLOORS |  | 124564 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 454.4 | LABOR- SUBCONTRACTOR
%R | 501018 | 6359 | 124565 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 24 | 0 | 200 | 0 | 3302.4 | 3302.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | 3XwVHPFfSg+mHdUKL8fbEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34830 | N | N | 15 | FIRST FLOORS |  | 124564 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 3302.4 | LABOR- SUBCONTRACTOR
%R | 501019 | 6359 | 124566 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 472 | 0 | 200 | 0 | 2579.2 | 2579.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-11 08:00 | 2014-02-08 17:00 |  | 2013-11-02 08:00 | 2013-11-30 17:00 | 2013-11-02 08:00 | 2013-11-30 17:00 | 2013-11-02 08:00 | 2013-11-30 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 |  | PT_Normal |  |  |  |  | SvGA60CqQTePNOSe4xBLhQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34820 | N | N | 10 | GROUND FLOOR |  | 124564 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 2579.2 | LABOR- SUBCONTRACTOR
%R | 501020 | 6359 | 124566 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ELGF4005 | Cable tray & trunking installation | 8178 | 616 | 0 | 160 | 0 | 3180.8 | 3180.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-03-08 17:00 |  | 2013-11-13 08:00 | 2013-12-05 17:00 | 2013-11-13 08:00 | 2013-12-05 17:00 | 2013-11-13 08:00 | 2013-12-05 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | 3Cd8B/T8TWutk6IxR7if0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34820 | N | N | 10 | GROUND FLOOR |  | 124564 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 3180.8 | LABOR- SUBCONTRACTOR
%R | 501021 | 6359 | 124566 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ELGF4010 | Installation of wiring & Main Cabling | 8178 | 616 | 216 | 200 | 0 | 636.8 | 636.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-22 17:00 |  | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | ubsLOfHGTu6wXaDAa8fGgw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34820 | N | N | 10 | GROUND FLOOR |  | 124564 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11; period 2: 2013-AP12 |  | 318.4 | LABOR- SUBCONTRACTOR
%R | 501022 | 6359 | 124566 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 400 | 0 | 160 | 0 | 454.4 | 454.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-22 17:00 |  | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | IhyOngIsQhuACCYFxIh2Bg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34820 | N | N | 10 | GROUND FLOOR |  | 124564 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 454.4 | LABOR- SUBCONTRACTOR
%R | 501023 | 6359 | 124566 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 416 | 0 | 200 | 0 | 3302.4 | 3302.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-14 08:00 | 2014-05-12 17:00 |  | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 |  | PT_Normal |  |  |  |  | iGzj330bTriIH5osfmQfiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34820 | N | N | 10 | GROUND FLOOR |  | 124564 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 1651.2 | LABOR- SUBCONTRACTOR
%R | 501024 | 6359 | 124566 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 576 | 0 | 200 | 0 | 4569.6 | 4569.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | 9p6jciXiRheCjUE9fYI1dg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34820 | N | N | 10 | GROUND FLOOR |  | 124564 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 4569.6 | LABOR- SUBCONTRACTOR
%R | 501025 | 6359 | 124566 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ELGF4030 | Installation of Telephone System | 8178 | 400 | 40 | 160 | 0 | 1422.4 | 1422.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-04 17:00 |  | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | xx5uPb1YRsGEpgqDM7P1aA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34820 | N | N | 10 | GROUND FLOOR |  | 124564 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1422.4 | LABOR- SUBCONTRACTOR
%R | 501026 | 6359 | 124567 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ELRF4070 | Installation of Isolator | 8178 | 24 | 0 | 144 | 0 | 825.6 | 825.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-05-10 08:00 | 2014-05-29 17:00 |  | 2014-05-06 08:00 | 2014-05-26 17:00 | 2014-05-06 08:00 | 2014-05-26 17:00 | 2014-05-06 08:00 | 2014-05-26 17:00 | 2014-05-10 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | KtwUf71TSOmibJ4/U/k7LQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34840 | N | N | 20 | ROOF |  | 124564 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 825.6 | LABOR- SUBCONTRACTOR
%R | 501027 | 6359 | 124567 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ELRF4075 | Installation of TV Dish Antenna | 8178 | 24 | 0 | 184 | 0 | 1830.4 | 1830.4 | 184 | 0 | 0 | 0 |  |  |  | 2014-05-21 08:00 | 2014-06-16 17:00 |  | 2014-05-18 08:00 | 2014-06-12 17:00 | 2014-05-18 08:00 | 2014-06-12 17:00 | 2014-05-18 08:00 | 2014-06-12 17:00 | 2014-05-21 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | On2PsDFCRem9qO8Ar4NC7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34840 | N | N | 20 | ROOF |  | 124564 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1830.4 | LABOR- SUBCONTRACTOR
%R | 501028 | 6359 | 124569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 352 | 0 | 144 | 0 | 883.2 | 883.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-04 08:00 | 2014-01-23 17:00 |  | 2013-11-12 08:00 | 2013-12-02 17:00 | 2013-11-12 08:00 | 2013-12-02 17:00 | 2013-11-12 08:00 | 2013-12-02 17:00 | 2014-01-04 08:00 | 2014-01-23 17:00 |  | PT_Normal |  |  |  |  | Kt9XeptiSbOykkraN2U6rg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34860 | N | N | 10 | GROUND FLOOR |  | 124568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 883.2 | LABOR- SUBCONTRACTOR
%R | 501029 | 6359 | 124569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1PLGF4310 | Installation of Drainage pipes &testing | 8178 | 352 | 168 | 144 | 0 | 331.2 | 331.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-04 08:00 | 2014-01-23 17:00 |  | 2013-11-12 08:00 | 2013-12-02 17:00 | 2013-11-12 08:00 | 2013-12-02 17:00 | 2013-11-12 08:00 | 2013-12-02 17:00 | 2014-01-04 08:00 | 2014-01-23 17:00 |  | PT_Normal |  |  |  |  | uejgEAMRQKa9y0+7yJ37hw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34860 | N | N | 10 | GROUND FLOOR |  | 124568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 331.2 | LABOR- SUBCONTRACTOR
%R | 501030 | 6359 | 124569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1PLGF4315 | Sanitary Fittings & Accessories | 8178 | 656 | 0 | 160 | 0 | 201.6 | 201.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-10 17:00 |  | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-05-19 08:00 | 2014-06-10 17:00 |  | PT_Normal |  |  |  |  | FV6UvPx8S9aMJWo43iBUgA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34860 | N | N | 10 | GROUND FLOOR |  | 124568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 201.6 | LABOR- SUBCONTRACTOR
%R | 501031 | 6359 | 124569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1PLGF4320 | Installation of Water Heater | 8178 | 656 | 80 | 120 | 0 | 201.6 | 201.6 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-31 08:00 | 2014-06-16 17:00 |  | 2014-02-24 08:00 | 2014-03-12 17:00 | 2014-02-24 08:00 | 2014-03-12 17:00 | 2014-02-24 08:00 | 2014-03-12 17:00 | 2014-05-31 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | YFXi7D8+RPKejEJ2uOQ+kQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34860 | N | N | 10 | GROUND FLOOR |  | 124568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 201.6 | LABOR- SUBCONTRACTOR
%R | 501032 | 6359 | 124569 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 0 | 0 | 160 | 0 | 110.4 | 110.4 | 160 | 0 | 0 | 0 |  |  |  | 2013-07-23 08:00 | 2013-08-18 17:00 |  | 2013-07-23 08:00 | 2013-08-18 17:00 | 2013-07-23 08:00 | 2013-08-18 17:00 | 2013-07-23 08:00 | 2013-08-18 17:00 | 2013-07-23 08:00 | 2013-08-18 17:00 |  | PT_Normal |  |  |  |  | 37cYZmqdRuS5dJK9K3N5OA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34860 | N | N | 10 | GROUND FLOOR |  | 124568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 110.4 | LABOR- SUBCONTRACTOR
%R | 501033 | 6359 | 124570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 24 | 0 | 144 | 0 | 883.2 | 883.2 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-30 08:00 | 2014-01-19 17:00 |  | 2013-12-26 08:00 | 2014-01-15 17:00 | 2013-12-26 08:00 | 2014-01-15 17:00 | 2013-12-26 08:00 | 2014-01-15 17:00 | 2013-12-30 08:00 | 2014-01-19 17:00 |  | PT_Normal |  |  |  |  | 3ndl+h+6QXuLY4687kg+SQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34870 | N | N | 15 | FIRST FLOORS |  | 124568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 883.2 | LABOR- SUBCONTRACTOR
%R | 501034 | 6359 | 124570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1PLFF4330 | Installation of Drainage pipes & testing | 8178 | 240 | 56 | 144 | 0 | 331.2 | 331.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-02-20 17:00 |  | 2013-12-26 08:00 | 2014-01-15 17:00 | 2013-12-26 08:00 | 2014-01-15 17:00 | 2013-12-26 08:00 | 2014-01-15 17:00 | 2014-01-30 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | AT2bwtKwRSGSWZSakb/UFg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34870 | N | N | 15 | FIRST FLOORS |  | 124568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 331.2 | LABOR- SUBCONTRACTOR
%R | 501035 | 6359 | 124570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1PLFF4335 | Sanitary Fittings & Accessories | 8178 | 152 | 0 | 160 | 0 | 201.6 | 201.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-01 08:00 | 2014-05-24 17:00 |  | 2014-04-09 08:00 | 2014-05-01 17:00 | 2014-04-09 08:00 | 2014-05-01 17:00 | 2014-04-09 08:00 | 2014-05-01 17:00 | 2014-05-01 08:00 | 2014-05-24 17:00 |  | PT_Normal |  |  |  |  | kEjBe8aSTom8iMMvBI6img |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34870 | N | N | 15 | FIRST FLOORS |  | 124568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 201.6 | LABOR- SUBCONTRACTOR
%R | 501036 | 6359 | 124570 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1PLFF4340 | Installation of Water Heater | 8178 | 152 | 0 | 120 | 0 | 134.4 | 134.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-05-29 17:00 |  | 2014-04-21 08:00 | 2014-05-07 17:00 | 2014-04-21 08:00 | 2014-05-07 17:00 | 2014-04-21 08:00 | 2014-05-07 17:00 | 2014-05-13 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | 8p33rilgSQulWKraa7I7fA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34870 | N | N | 15 | FIRST FLOORS |  | 124568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 501037 | 6359 | 124571 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 648 | 16 | 112 | 0 | 288 | 288 | 112 | 0 | 0 | 0 |  |  |  | 2014-05-04 08:00 | 2014-05-19 17:00 |  | 2014-01-28 08:00 | 2014-02-13 17:00 | 2014-01-28 08:00 | 2014-02-13 17:00 | 2014-01-28 08:00 | 2014-02-13 17:00 | 2014-05-04 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | yONIIaedTZGlOo5RCC/x9w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34880 | N | N | 20 | ROOF |  | 124568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 288 | LABOR- SUBCONTRACTOR
%R | 501038 | 6359 | 124571 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1PLRF4350 | Installation of Rain water Pipes |  | 632 | 64 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-05-29 17:00 |  | 2014-02-09 08:00 | 2014-02-26 17:00 | 2014-02-09 08:00 | 2014-02-26 17:00 | 2014-02-09 08:00 | 2014-02-26 17:00 | 2014-05-13 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | TKa3mNZpTnOo2hqfp1lJXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 34880 | N | N | 20 | ROOF |  | 124568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 0 | 0
%R | 501039 | 6359 | 124571 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 152 | 0 | 200 | 0 | 672 | 672 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | 3L4RBxagSKy+IPVgK5WSbw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34880 | N | N | 20 | ROOF |  | 124568 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 672 | LABOR- SUBCONTRACTOR
%R | 501040 | 6359 | 124574 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STRF2040 | Column-Rebar & Formwork | 8166 | 168 | 0 | 144 | 0 | 1176 | 1176 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-14 08:00 | 2014-01-04 17:00 |  | 2013-11-19 08:00 | 2013-12-09 17:00 | 2013-11-19 08:00 | 2013-12-09 17:00 | 2013-11-19 08:00 | 2013-12-09 17:00 | 2013-12-14 08:00 | 2014-01-04 17:00 |  | PT_Normal |  |  |  |  | mD5n0PsdSiKqB1WLiiD5Bg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34710 | N | N | 20 | ROOF |  | 124573 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1176 | CARPENTERS SK
%R | 501041 | 6359 | 124574 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STRF2045 | Column-Concrete | 8167 | 168 | 0 | 136 | 0 | 80.5 | 80.5 | 136 | 0 | 0 | 0 |  |  |  | 2013-12-17 08:00 | 2014-01-06 17:00 |  | 2013-11-23 08:00 | 2013-12-11 17:00 | 2013-11-23 08:00 | 2013-12-11 17:00 | 2013-11-23 08:00 | 2013-12-11 17:00 | 2013-12-17 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | UFYYMofyTdCYoTp+9C5DbA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34710 | N | N | 20 | ROOF |  | 124573 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 80.5 | CONCRETE MASON SK
%R | 501042 | 6359 | 124574 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STRF2050 | Slab-Rebar & Formwork - Head Room | 8165 | 168 | 0 | 160 | 0 | 3444 | 3444 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-21 08:00 | 2014-01-12 17:00 |  | 2013-11-25 08:00 | 2013-12-17 17:00 | 2013-11-25 08:00 | 2013-12-17 17:00 | 2013-11-25 08:00 | 2013-12-17 17:00 | 2013-12-21 08:00 | 2014-01-12 17:00 |  | PT_Normal |  |  |  |  | BCZLRORZRhKQ2kQ9uiVUEA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34710 | N | N | 20 | ROOF |  | 124573 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 3444 | STEEL FIXERS SK
%R | 501043 | 6359 | 124574 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STRF2055 | Slab-Concrete-Head room | 8167 | 168 | 0 | 104 | 0 | 280 | 280 | 104 | 0 | 0 | 0 |  |  |  | 2014-01-04 08:00 | 2014-01-18 17:00 |  | 2013-12-09 08:00 | 2013-12-24 17:00 | 2013-12-09 08:00 | 2013-12-24 17:00 | 2013-12-09 08:00 | 2013-12-24 17:00 | 2014-01-04 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | CpEiAQDPQ+u7zLeS5QFvIA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34710 | N | N | 20 | ROOF |  | 124573 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 280 | CONCRETE MASON SK
%R | 501044 | 6359 | 124574 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STRF2060 | Construction of Parapets | 8168 | 408 | 0 | 200 | 0 | 1175 | 1175 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-10 08:00 | 2014-03-11 17:00 |  | 2013-12-11 08:00 | 2014-01-09 17:00 | 2013-12-11 08:00 | 2014-01-09 17:00 | 2013-12-11 08:00 | 2014-01-09 17:00 | 2014-02-10 08:00 | 2014-03-11 17:00 |  | PT_Normal |  |  |  |  | gyQWre50T92qi3OPGoIxSQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34710 | N | N | 20 | ROOF |  | 124573 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1175 | BLOCK MASON SK
%R | 501045 | 6359 | 124574 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STRF2065 | Construction of up stands/Plinth | 8165 | 624 | 0 | 200 | 0 | 549.5 | 549.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-26 08:00 | 2014-04-23 17:00 |  | 2013-12-24 08:00 | 2014-01-21 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 |  | PT_Normal |  |  |  |  | tT/mU4lkT3qXUhfiyBfBNg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34710 | N | N | 20 | ROOF |  | 124573 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 549.5 | STEEL FIXERS SK
%R | 501046 | 6359 | 124575 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STGF2005 | Column-Concrete | 8167 | 0 | 0 | 184 | 0 | 388.5 | 388.5 | 184 | 0 | 0 | 0 |  |  |  | 2013-08-31 08:00 | 2013-09-25 17:00 |  | 2013-08-31 08:00 | 2013-09-25 17:00 | 2013-08-31 08:00 | 2013-09-25 17:00 | 2013-08-31 08:00 | 2013-09-25 17:00 | 2013-08-31 08:00 | 2013-09-25 17:00 |  | PT_Normal |  |  |  |  | bciAdyMKQJWKX0ikGbDriw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34690 | N | N | 10 | GROUND FLOOR |  | 124573 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 388.5 | CONCRETE MASON SK
%R | 501047 | 6359 | 124575 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 18721.5 | 18721.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-14 08:00 | 2013-10-12 17:00 |  | 2013-09-14 08:00 | 2013-10-12 17:00 | 2013-09-14 08:00 | 2013-10-12 17:00 | 2013-09-14 08:00 | 2013-10-12 17:00 | 2013-09-14 08:00 | 2013-10-12 17:00 |  | PT_Normal |  |  |  |  | zWGLjCDSTB+fP93CDCYVhQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34690 | N | N | 10 | GROUND FLOOR |  | 124573 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 18721.5 | STEEL FIXERS SK
%R | 501048 | 6359 | 124575 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 0 | 0 | 112 | 0 | 1456 | 1456 | 112 | 0 | 0 | 0 |  |  |  | 2013-09-30 08:00 | 2013-10-15 17:00 |  | 2013-09-30 08:00 | 2013-10-15 17:00 | 2013-09-30 08:00 | 2013-10-15 17:00 | 2013-09-30 08:00 | 2013-10-15 17:00 | 2013-09-30 08:00 | 2013-10-15 17:00 |  | PT_Normal |  |  |  |  | 9915HLd+R2iEIvrWeCEMmw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34690 | N | N | 10 | GROUND FLOOR |  | 124573 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1456 | CONCRETE MASON SK
%R | 501049 | 6359 | 124575 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STGF2000 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 4984 | 4984 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-21 08:00 | 2013-09-18 17:00 |  | 2013-08-21 08:00 | 2013-09-18 17:00 | 2013-08-21 08:00 | 2013-09-18 17:00 | 2013-08-21 08:00 | 2013-09-18 17:00 | 2013-08-21 08:00 | 2013-09-18 17:00 |  | PT_Normal |  |  |  |  | JutooPc8SqO0i9TzseVhYw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34690 | N | N | 10 | GROUND FLOOR |  | 124573 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 4984 | STEEL FIXERS SK
%R | 501050 | 6359 | 124576 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STFF2020 | Column-Rebar & Formwork | 8166 | 0 | 0 | 200 | 0 | 3418 | 3418 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-02 08:00 | 2013-11-02 17:00 |  | 2013-10-02 08:00 | 2013-11-02 17:00 | 2013-10-02 08:00 | 2013-11-02 17:00 | 2013-10-02 08:00 | 2013-11-02 17:00 | 2013-10-02 08:00 | 2013-11-02 17:00 |  | PT_Normal |  |  |  |  | l7J6ilDdTea4JyG+5+jEmg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34700 | N | N | 15 | FIRST FLOORS |  | 124573 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 1709 | CARPENTERS SK
%R | 501051 | 6359 | 124576 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STFF2025 | Column-Concrete | 8167 | 24 | 0 | 184 | 0 | 339.5 | 339.5 | 184 | 0 | 0 | 0 |  |  |  | 2013-10-15 08:00 | 2013-11-12 17:00 |  | 2013-10-12 08:00 | 2013-11-09 17:00 | 2013-10-12 08:00 | 2013-11-09 17:00 | 2013-10-12 08:00 | 2013-11-09 17:00 | 2013-10-15 08:00 | 2013-11-12 17:00 |  | PT_Normal |  |  |  |  | hJlRbMk7TcqAxlLWIkkGOQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34700 | N | N | 15 | FIRST FLOORS |  | 124573 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 339.5 | CONCRETE MASON SK
%R | 501052 | 6359 | 124576 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 24 | 0 | 200 | 0 | 19080.25 | 19080.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-31 08:00 | 2013-11-28 17:00 |  | 2013-10-28 08:00 | 2013-11-25 17:00 | 2013-10-28 08:00 | 2013-11-25 17:00 | 2013-10-28 08:00 | 2013-11-25 17:00 | 2013-10-31 08:00 | 2013-11-28 17:00 |  | PT_Normal |  |  |  |  | n2JftmjBSgem0pD2D82LKg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34700 | N | N | 15 | FIRST FLOORS |  | 124573 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 19080.25 | STEEL FIXERS SK
%R | 501053 | 6359 | 124576 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 24 | 0 | 112 | 0 | 1288 | 1288 | 112 | 0 | 0 | 0 |  |  |  | 2013-11-17 08:00 | 2013-12-02 17:00 |  | 2013-11-13 08:00 | 2013-11-28 17:00 | 2013-11-13 08:00 | 2013-11-28 17:00 | 2013-11-13 08:00 | 2013-11-28 17:00 | 2013-11-17 08:00 | 2013-12-02 17:00 |  | PT_Normal |  |  |  |  | MmFmsKUtTjG+jEBUQF/RAA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34700 | N | N | 15 | FIRST FLOORS |  | 124573 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1288 | CONCRETE MASON SK
%R | 501054 | 6359 | 124578 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STUG1000 | Footing Excavation | 8177 | 0 | 0 | 200 | 0 | 1433 | 1433 | 200 | 675 | 0 | 675 |  |  |  | 2013-04-14 08:00 | 2013-05-12 17:00 |  | 2013-04-14 08:00 | 2013-05-12 17:00 | 2013-04-14 08:00 | 2013-05-12 17:00 | 2013-04-14 08:00 | 2013-05-12 17:00 | 2013-04-14 08:00 | 2013-05-12 17:00 |  | PT_Normal |  |  |  |  | fvv/CeJaQ9uywqscEJuXUg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34670 | N | N | 10 | UPTO GRADE SLAB |  | 124577 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 1433 | LABOR - CIVIL
%R | 501055 | 6359 | 124578 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STUG1005 | Footing Antitermite | 8178 | 0 | 0 | 184 | 0 | 1861.75 | 1861.75 | 184 | 0 | 0 | 0 |  |  |  | 2013-04-25 08:00 | 2013-05-21 17:00 |  | 2013-04-25 08:00 | 2013-05-21 17:00 | 2013-04-25 08:00 | 2013-05-21 17:00 | 2013-04-25 08:00 | 2013-05-21 17:00 | 2013-04-25 08:00 | 2013-05-21 17:00 |  | PT_Normal |  |  |  |  | XFeRj5B4ToWcox7by6EKKA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34670 | N | N | 10 | UPTO GRADE SLAB |  | 124577 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 1861.75 | LABOR- SUBCONTRACTOR
%R | 501056 | 6359 | 124578 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STUG1010 | Footing Blinding | 8163 | 0 | 0 | 184 | 0 | 1048.25 | 1048.25 | 184 | 0 | 0 | 0 |  |  |  | 2013-04-29 08:00 | 2013-05-25 17:00 |  | 2013-04-29 08:00 | 2013-05-25 17:00 | 2013-04-29 08:00 | 2013-05-25 17:00 | 2013-04-29 08:00 | 2013-05-25 17:00 | 2013-04-29 08:00 | 2013-05-25 17:00 |  | PT_Normal |  |  |  |  | UqqNsU1VTRi0AVNyaq17wA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34670 | N | N | 10 | UPTO GRADE SLAB |  | 124577 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 1048.25 | BLINDING MASON SK
%R | 501057 | 6359 | 124578 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STUG1015 | Footing Waterproofing & Screed | 8164 | 0 | 0 | 200 | 0 | 825 | 825 | 200 | 0 | 0 | 0 |  |  |  | 2013-05-05 08:00 | 2013-06-02 17:00 |  | 2013-05-05 08:00 | 2013-06-02 17:00 | 2013-05-05 08:00 | 2013-06-02 17:00 | 2013-05-05 08:00 | 2013-06-02 17:00 | 2013-05-05 08:00 | 2013-06-02 17:00 |  | PT_Normal |  |  |  |  | LKVr6rBxRUCPJgrjvbdJkg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34670 | N | N | 10 | UPTO GRADE SLAB |  | 124577 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 825 | SCREED MASON SK
%R | 501058 | 6359 | 124578 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STUG1020 | Construction of foundations | 8165 | 0 | 0 | 160 | 0 | 7969.5 | 7969.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-05-20 08:00 | 2013-06-11 17:00 |  | 2013-05-20 08:00 | 2013-06-11 17:00 | 2013-05-20 08:00 | 2013-06-11 17:00 | 2013-05-20 08:00 | 2013-06-11 17:00 | 2013-05-20 08:00 | 2013-06-11 17:00 |  | PT_Normal |  |  |  |  | fuBsiXyzS5mXldfBlYIj6A |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34670 | N | N | 10 | UPTO GRADE SLAB |  | 124577 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 7969.5 | STEEL FIXERS SK
%R | 501059 | 6359 | 124578 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STUG1025 | Construction of neck of columns | 8165 | 0 | 0 | 200 | 0 | 1946 | 1946 | 200 | 0 | 0 | 0 |  |  |  | 2013-05-29 08:00 | 2013-06-26 17:00 |  | 2013-05-29 08:00 | 2013-06-26 17:00 | 2013-05-29 08:00 | 2013-06-26 17:00 | 2013-05-29 08:00 | 2013-06-26 17:00 | 2013-05-29 08:00 | 2013-06-26 17:00 |  | PT_Normal |  |  |  |  | E8qwOehzRNGp3xluhgi6iQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34670 | N | N | 10 | UPTO GRADE SLAB |  | 124577 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 1946 | STEEL FIXERS SK
%R | 501060 | 6359 | 124578 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STUG1030 | Waterproofing Footing & Neck Column | 8178 | 0 | 0 | 200 | 0 | 535.25 | 535.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-08 08:00 | 2013-07-06 17:00 |  | 2013-06-08 08:00 | 2013-07-06 17:00 | 2013-06-08 08:00 | 2013-07-06 17:00 | 2013-06-08 08:00 | 2013-07-06 17:00 | 2013-06-08 08:00 | 2013-07-06 17:00 |  | PT_Normal |  |  |  |  | 6CSnCpfdQ9qu3GmtT7gQiQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34670 | N | N | 10 | UPTO GRADE SLAB |  | 124577 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 535.25 | LABOR- SUBCONTRACTOR
%R | 501061 | 6359 | 124578 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 0 | 0 | 200 | 0 | 1436 | 1436 | 200 | 1100 | 0 | 1100 |  |  |  | 2013-06-19 08:00 | 2013-07-17 17:00 |  | 2013-06-19 08:00 | 2013-07-17 17:00 | 2013-06-19 08:00 | 2013-07-17 17:00 | 2013-06-19 08:00 | 2013-07-17 17:00 | 2013-06-19 08:00 | 2013-07-17 17:00 |  | PT_Normal |  |  |  |  | onqd4RdPQm2yXU9CiNm+Hg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34670 | N | N | 10 | UPTO GRADE SLAB |  | 124577 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 1436 | LABOR - CIVIL
%R | 501062 | 6359 | 124578 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STUG1040 | Construction of Grade Beams | 8163 | 0 | 0 | 200 | 0 | 8096.25 | 8096.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-06 08:00 | 2013-08-03 17:00 |  | 2013-07-06 08:00 | 2013-08-03 17:00 | 2013-07-06 08:00 | 2013-08-03 17:00 | 2013-07-06 08:00 | 2013-08-03 17:00 | 2013-07-06 08:00 | 2013-08-03 17:00 |  | PT_Normal |  |  |  |  | 4oMTAEM9SCShVA0B0o/4Xw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34670 | N | N | 10 | UPTO GRADE SLAB |  | 124577 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 8096.25 | BLINDING MASON SK
%R | 501063 | 6359 | 124578 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1STUG1045 | Construction of slab on grade | 8163 | 0 | 0 | 200 | 0 | 5538.75 | 5538.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-01 08:00 | 2013-09-02 17:00 |  | 2013-08-01 08:00 | 2013-09-02 17:00 | 2013-08-01 08:00 | 2013-09-02 17:00 | 2013-08-01 08:00 | 2013-09-02 17:00 | 2013-08-01 08:00 | 2013-09-02 17:00 |  | PT_Normal |  |  |  |  | nw49WRHhTimhpkxNnBKiHQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34670 | N | N | 10 | UPTO GRADE SLAB |  | 124577 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP08 |  | 2769.375 | BLINDING MASON SK
%R | 501064 | 6359 | 124579 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 24 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | jT324IYqSSWxC7fMLlz8DQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34990 | N | N | 30 | TESTING AND COMMISSIONING |  | 124558 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 501065 | 6359 | 124579 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 24 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | Z6CvXaOATCK/+XEr42Nbpw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34990 | N | N | 30 | TESTING AND COMMISSIONING |  | 124558 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 501066 | 6359 | 124579 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 24 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | wnTdcL31Qe23OjKpaq7FhA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34990 | N | N | 30 | TESTING AND COMMISSIONING |  | 124558 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 501067 | 6359 | 124581 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 200 | 0 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | 4a/Q+SLcQKqIHAmi4xjGMg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34950 | N | N | 10 | MISCELLANEOUS |  | 124580 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 400 | LABOR- SUBCONTRACTOR
%R | 501068 | 6359 | 124581 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1MSEX5020 | Construction Entrance Ramp | 8164 | 552 | 0 | 200 | 0 | 1288 | 1288 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-30 17:00 |  | 2013-12-09 08:00 | 2014-01-07 17:00 | 2013-12-09 08:00 | 2014-01-07 17:00 | 2013-12-09 08:00 | 2014-01-07 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | YgBUJK0rT02a65D0G9NNYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34950 | N | N | 10 | MISCELLANEOUS |  | 124580 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1288 | SCREED MASON SK
%R | 501069 | 6359 | 124581 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1MSEX5025 | SS.Handrails and Balustrades | 8178 | 552 | 0 | 160 | 0 | 400 | 400 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-13 17:00 |  | 2013-12-30 08:00 | 2014-01-21 17:00 | 2013-12-30 08:00 | 2014-01-21 17:00 | 2013-12-30 08:00 | 2014-01-21 17:00 | 2014-03-22 08:00 | 2014-04-13 17:00 |  | PT_Normal |  |  |  |  | KWmxc1DJS06+Qq1nOXAFzA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34950 | N | N | 10 | MISCELLANEOUS |  | 124580 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 400 | LABOR- SUBCONTRACTOR
%R | 501070 | 6359 | 124581 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1MSEX5015 | Construction of grease Trap | 8178 | 240 | 0 | 160 | 0 | 88 | 88 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-24 17:00 |  | 2014-01-25 08:00 | 2014-02-17 17:00 | 2014-01-25 08:00 | 2014-02-17 17:00 | 2014-01-25 08:00 | 2014-02-17 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | orALG+fFTsuDm+6F8Xu20A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34950 | N | N | 10 | MISCELLANEOUS |  | 124580 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 88 | LABOR- SUBCONTRACTOR
%R | 501071 | 6359 | 124581 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1MSEX5000 | Construction of Manholes | 8172 | 168 | 0 | 200 | 0 | 880 | 880 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-15 08:00 | 2014-02-13 17:00 |  | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 |  | PT_Normal |  |  |  |  | LH1J2IFgQXiT1kOvttLyqQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34950 | N | N | 10 | MISCELLANEOUS |  | 124580 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 880 | MANHOLES SK
%R | 501072 | 6359 | 124581 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1MSEX5005 | Construction of Soak pit, Chambers | 8172 | 240 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-03-10 17:00 |  | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34950 | N | N | 10 | MISCELLANEOUS |  | 124580 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 176 | MANHOLES SK
%R | 501073 | 6359 | 124581 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1MSEX5010 | Telephone cable laying | 8177 | 240 | 40 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-25 08:00 | 2014-04-22 17:00 |  | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | MsK0dSOFTkKt0fdeofVW5Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34950 | N | N | 10 | MISCELLANEOUS |  | 124580 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 250 | LABOR - CIVIL
%R | 501074 | 6359 | 124582 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1WEEX5030 | Excavation | 8177 | 408 | 0 | 160 | 0 | 128 | 128 | 160 | 80 | 0 | 80 |  |  |  | 2014-02-23 08:00 | 2014-03-17 17:00 |  | 2013-12-24 08:00 | 2014-01-15 17:00 | 2013-12-24 08:00 | 2014-01-15 17:00 | 2013-12-24 08:00 | 2014-01-15 17:00 | 2014-02-23 08:00 | 2014-03-17 17:00 |  | PT_Normal |  |  |  |  | 2OgdarD+Qi201OSSQXeDwg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34960 | N | N | 15 | WATER TANK ENCLOSURE |  | 124580 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 128 | LABOR - CIVIL
%R | 501075 | 6359 | 124582 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1WEEX5035 | Construction of Raft | 8165 | 568 | 0 | 200 | 0 | 1624 | 1624 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-24 08:00 | 2014-04-21 17:00 |  | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2014-03-24 08:00 | 2014-04-21 17:00 |  | PT_Normal |  |  |  |  | /p/QJIYGToS3sHyZy/5WoA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34960 | N | N | 15 | WATER TANK ENCLOSURE |  | 124580 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1624 | STEEL FIXERS SK
%R | 501076 | 6359 | 124582 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1WEEX5040 | Block works & Plastering | 8168 | 568 | 0 | 200 | 0 | 888 | 888 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-02 08:00 | 2014-04-30 17:00 |  | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 |  | PT_Normal |  |  |  |  | oEvTafqwR2iXGH7GZfy2xA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34960 | N | N | 15 | WATER TANK ENCLOSURE |  | 124580 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 888 | BLOCK MASON SK
%R | 501077 | 6359 | 124582 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1WEEX5045 | Flooring & Painting | 8178 | 568 | 0 | 200 | 0 | 408 | 408 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-14 08:00 | 2014-05-12 17:00 |  | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 |  | PT_Normal |  |  |  |  | ObJ7ds+HT+e+BxAa16IGqA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34960 | N | N | 15 | WATER TANK ENCLOSURE |  | 124580 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 408 | LABOR- SUBCONTRACTOR
%R | 501078 | 6359 | 124582 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1WEEX5050 | Installation of Steel Gate | 8178 | 568 | 0 | 160 | 0 | 112 | 112 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-01 08:00 | 2014-05-24 17:00 |  | 2014-02-06 08:00 | 2014-03-02 17:00 | 2014-02-06 08:00 | 2014-03-02 17:00 | 2014-02-06 08:00 | 2014-03-02 17:00 | 2014-05-01 08:00 | 2014-05-24 17:00 |  | PT_Normal |  |  |  |  | KDjAoReCSE2K7H0KKRM0eA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34960 | N | N | 15 | WATER TANK ENCLOSURE |  | 124580 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 112 | LABOR- SUBCONTRACTOR
%R | 501079 | 6359 | 124582 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 568 | 0 | 200 | 0 | 616 | 616 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-07 08:00 | 2014-06-04 17:00 |  | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 |  | PT_Normal |  |  |  |  | o441l1e8Ts64iANiglcKbA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34960 | N | N | 15 | WATER TANK ENCLOSURE |  | 124580 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 308 | LABOR- SUBCONTRACTOR
%R | 501080 | 6359 | 124582 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 568 | 0 | 200 | 0 | 382.4 | 382.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | qFBxF9mNQ1+c2l41cdhk6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34960 | N | N | 15 | WATER TANK ENCLOSURE |  | 124580 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 191.2 | LABOR- SUBCONTRACTOR
%R | 501081 | 6359 | 124583 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1HDEX5090 | kerb works | 8173 | 552 | 0 | 160 | 0 | 712 | 712 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-30 08:00 | 2014-04-21 17:00 |  | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-03-30 08:00 | 2014-04-21 17:00 |  | PT_Normal |  |  |  |  | QNvUysahSfWeGcCGqu4qew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34970 | N | N | 20 | HARD LANDSCAPING |  | 124580 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 712 | KERBSTONE MASON SK
%R | 501082 | 6359 | 124583 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1HDEX5095 | Cobble Stone Works | 8170 | 552 | 0 | 160 | 0 | 456 | 456 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-10 08:00 | 2014-05-03 17:00 |  | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-04-10 08:00 | 2014-05-03 17:00 |  | PT_Normal |  |  |  |  | wvzqJ3DrTIaSw7mg+qCwXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34970 | N | N | 20 | HARD LANDSCAPING |  | 124580 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 456 | TILE MASON SK
%R | 501083 | 6359 | 124583 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1HDEX5100 | Interlock works | 8174 | 552 | 0 | 160 | 0 | 408 | 408 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-26 08:00 | 2014-05-18 17:00 |  | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-04-26 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | hDopiiYSRtyvYFw75YaBew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34970 | N | N | 20 | HARD LANDSCAPING |  | 124580 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 408 | INTERLOCK MASON SK
%R | 501084 | 6359 | 124584 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1SLEX5105 | Laying of Grass/ green area | 8178 | 552 | 0 | 200 | 0 | 5488 | 5488 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-07 08:00 | 2014-06-04 17:00 |  | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 |  | PT_Normal |  |  |  |  | Ar5tRiA+TSi56ZBBYj+8cA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34980 | N | N | 25 | SOFT LANDSCAPING |  | 124580 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 2744 | LABOR- SUBCONTRACTOR
%R | 501085 | 6359 | 124584 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1SLEX5110 | Laying of Palm tree | 8178 | 552 | 528 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | Z175rg8LTmSJUpuCdkOBKw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34980 | N | N | 25 | SOFT LANDSCAPING |  | 124580 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 168 | LABOR- SUBCONTRACTOR
%R | 501086 | 6359 | 124587 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1AREL3665 | External Plastering | 8169 | 600 | 0 | 200 | 0 | 12200 | 12200 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-19 08:00 | 2014-05-17 17:00 |  | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 |  | PT_Normal |  |  |  |  | cvoAtf7jQdOh7ERUBoa6VA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34790 | N | N | 15 | ELEVATION |  | 124586 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 12200 | PLASTER MASON SK
%R | 501087 | 6359 | 124587 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1AREL3670 | External stone cladding works | 8170 | 608 | 0 | 160 | 0 | 936 | 936 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-07 08:00 | 2014-05-29 17:00 |  | 2014-02-06 08:00 | 2014-03-02 17:00 | 2014-02-06 08:00 | 2014-03-02 17:00 | 2014-02-06 08:00 | 2014-03-02 17:00 | 2014-05-07 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | XnEO2dj9RLWWVyOdhOE5nQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34790 | N | N | 15 | ELEVATION |  | 124586 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 936 | TILE MASON SK
%R | 501088 | 6359 | 124587 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1AREL3675 | GRC works | 8178 | 608 | 0 | 160 | 0 | 550 | 550 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-06-04 17:00 |  | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-05-13 08:00 | 2014-06-04 17:00 |  | PT_Normal |  |  |  |  | x3UL4WfWTVaxhmFKteW8Ug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34790 | N | N | 15 | ELEVATION |  | 124586 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 550 | LABOR- SUBCONTRACTOR
%R | 501089 | 6359 | 124587 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1AREL3680 | External Painting | 8178 | 608 | 40 | 160 | 0 | 4224 | 4224 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-25 08:00 | 2014-06-16 17:00 |  | 2014-02-25 08:00 | 2014-03-19 17:00 | 2014-02-25 08:00 | 2014-03-19 17:00 | 2014-02-25 08:00 | 2014-03-19 17:00 | 2014-05-25 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | NXNhQcPeTseh/3gHDkMHgA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34790 | N | N | 15 | ELEVATION |  | 124586 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 4224 | LABOR- SUBCONTRACTOR
%R | 501090 | 6359 | 124588 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARRF3630 | Leveling Screed for Waterproofing | 8164 | 624 | 0 | 200 | 0 | 711.5 | 711.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-07 08:00 | 2014-05-05 17:00 |  | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | GTIFLi89SxW0DL7UbV5GWA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34780 | N | N | 10 | ROOF |  | 124586 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 711.5 | SCREED MASON SK
%R | 501091 | 6359 | 124588 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARRF3635 | Laying of Waterproofing Membrane | 8178 | 624 | 0 | 200 | 0 | 986.25 | 986.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-10 08:00 | 2014-05-08 17:00 |  | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-04-10 08:00 | 2014-05-08 17:00 |  | PT_Normal |  |  |  |  | flsGml3mSDenllpe06i7Vg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34780 | N | N | 10 | ROOF |  | 124586 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 986.25 | LABOR- SUBCONTRACTOR
%R | 501092 | 6359 | 124588 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARRF3640 | Installation of Insulation & Protection | 8178 | 624 | 0 | 200 | 0 | 1250.25 | 1250.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-13 17:00 |  | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 |  | PT_Normal |  |  |  |  | rtoaDyOmR4ypFZRw7KzWAg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34780 | N | N | 10 | ROOF |  | 124586 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1250.25 | LABOR- SUBCONTRACTOR
%R | 501093 | 6359 | 124588 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 624 | 0 | 200 | 0 | 626 | 626 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-01-18 08:00 | 2014-02-16 17:00 | 2014-01-18 08:00 | 2014-02-16 17:00 | 2014-01-18 08:00 | 2014-02-16 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | 7o0Nk+EkRCqezO9IOLGMOg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34780 | N | N | 10 | ROOF |  | 124586 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 626 | TILE MASON SK
%R | 501094 | 6359 | 124588 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 624 | 0 | 160 | 0 | 616 | 616 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-06-04 17:00 |  | 2014-02-10 08:00 | 2014-03-05 17:00 | 2014-02-10 08:00 | 2014-03-05 17:00 | 2014-02-10 08:00 | 2014-03-05 17:00 | 2014-05-13 08:00 | 2014-06-04 17:00 |  | PT_Normal |  |  |  |  | YzoibMzuS9mTeObmepXXdA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34780 | N | N | 10 | ROOF |  | 124586 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 616 | LABOR- SUBCONTRACTOR
%R | 501095 | 6359 | 124588 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 624 | 0 | 200 | 0 | 859.25 | 859.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-28 08:00 | 2014-05-26 17:00 |  | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-04-28 08:00 | 2014-05-26 17:00 |  | PT_Normal |  |  |  |  | gY6zGG7bQaKUQBCWsIJM9A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34780 | N | N | 10 | ROOF |  | 124586 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 859.25 | LABOR- SUBCONTRACTOR
%R | 501096 | 6359 | 124588 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARRF3660 | Installation of Access Ladder | 8178 | 648 | 624 | 120 | 0 | 352 | 352 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-31 08:00 | 2014-06-16 17:00 |  | 2014-02-25 08:00 | 2014-03-13 17:00 | 2014-02-25 08:00 | 2014-03-13 17:00 | 2014-02-25 08:00 | 2014-03-13 17:00 | 2014-05-31 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | GMqjDMGkTDCsB2QDR9/0tw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34780 | N | N | 10 | ROOF |  | 124586 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 352 | LABOR- SUBCONTRACTOR
%R | 501097 | 6359 | 124590 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARRF3600 | Block work | 8168 | 600 | 0 | 160 | 0 | 697.25 | 697.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-02 08:00 | 2014-04-24 17:00 |  | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-04-02 08:00 | 2014-04-24 17:00 |  | PT_Normal |  |  |  |  | HKGaVqDqRvO9N16Np3IoSA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34760 | N | N | 20 | ROOF |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 697.25 | BLOCK MASON SK
%R | 501098 | 6359 | 124590 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARRF3605 | Plastering work | 8169 | 600 | 0 | 160 | 0 | 3833 | 3833 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-10 08:00 | 2014-05-03 17:00 |  | 2014-01-12 08:00 | 2014-02-03 17:00 | 2014-01-12 08:00 | 2014-02-03 17:00 | 2014-01-12 08:00 | 2014-02-03 17:00 | 2014-04-10 08:00 | 2014-05-03 17:00 |  | PT_Normal |  |  |  |  | C1b0mWYARlyYWLphCQn97A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34760 | N | N | 20 | ROOF |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 3833 | PLASTER MASON SK
%R | 501099 | 6359 | 124590 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARRF3610 | Flooring screed | 8164 | 648 | 0 | 120 | 0 | 154 | 154 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-01 08:00 | 2014-05-18 17:00 |  | 2014-01-26 08:00 | 2014-02-12 17:00 | 2014-01-26 08:00 | 2014-02-12 17:00 | 2014-01-26 08:00 | 2014-02-12 17:00 | 2014-05-01 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | nglKZ6q8RS2oxefYjHlb+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34760 | N | N | 20 | ROOF |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 154 | SCREED MASON SK
%R | 501100 | 6359 | 124590 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARRF3695 | Painting -Storage area | 8178 | 648 | 0 | 160 | 0 | 1640 | 1640 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-06-04 17:00 |  | 2014-02-06 08:00 | 2014-03-02 17:00 | 2014-02-06 08:00 | 2014-03-02 17:00 | 2014-02-06 08:00 | 2014-03-02 17:00 | 2014-05-13 08:00 | 2014-06-04 17:00 |  | PT_Normal |  |  |  |  | IVBhivWBQSuOU8jzn3P/Hg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34760 | N | N | 20 | ROOF |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1640 | LABOR- SUBCONTRACTOR
%R | 501101 | 6359 | 124590 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARRF3620 | Epoxy Painting -Storage area | 8178 | 648 | 624 | 120 | 0 | 48.5 | 48.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-31 08:00 | 2014-06-16 17:00 |  | 2014-02-25 08:00 | 2014-03-13 17:00 | 2014-02-25 08:00 | 2014-03-13 17:00 | 2014-02-25 08:00 | 2014-03-13 17:00 | 2014-05-31 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | 4kElhjU9SB6SMKUXIOACjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34760 | N | N | 20 | ROOF |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 48.5 | LABOR- SUBCONTRACTOR
%R | 501102 | 6359 | 124591 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARFF3300 | Block work | 8168 | 24 | 0 | 200 | 0 | 7341 | 7341 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-11 08:00 | 2014-01-09 17:00 |  | 2013-12-08 08:00 | 2014-01-06 17:00 | 2013-12-08 08:00 | 2014-01-06 17:00 | 2013-12-08 08:00 | 2014-01-06 17:00 | 2013-12-11 08:00 | 2014-01-09 17:00 |  | PT_Normal |  |  |  |  | zhiqqEwEQyG/QQ6nhE25vw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34750 | N | N | 15 | FIRST FLOORS |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 7341 | BLOCK MASON SK
%R | 501103 | 6359 | 124591 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARFF3305 | Plastering work | 8169 | 24 | 0 | 200 | 0 | 7518.75 | 7518.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-08 08:00 | 2014-02-05 17:00 |  | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | 5wkCbbHgSeetSkMhdOgmDA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34750 | N | N | 15 | FIRST FLOORS |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 7518.75 | PLASTER MASON SK
%R | 501104 | 6359 | 124591 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARFF3310 | Flooring screed | 8164 | 160 | 136 | 168 | 0 | 1082.5 | 1082.5 | 168 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-03-02 17:00 |  | 2014-01-13 08:00 | 2014-02-05 17:00 | 2014-01-13 08:00 | 2014-02-05 17:00 | 2014-01-13 08:00 | 2014-02-05 17:00 | 2014-02-05 08:00 | 2014-03-02 17:00 |  | PT_Normal |  |  |  |  | YZyg/aQjROWroyDTtIaR9A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34750 | N | N | 15 | FIRST FLOORS |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1082.5 | SCREED MASON SK
%R | 501105 | 6359 | 124591 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARFF3315 | Wet area waterproofing | 8178 | 24 | 0 | 120 | 0 | 1374 | 1374 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-29 08:00 | 2014-02-16 17:00 |  | 2014-01-26 08:00 | 2014-02-12 17:00 | 2014-01-26 08:00 | 2014-02-12 17:00 | 2014-01-26 08:00 | 2014-02-12 17:00 | 2014-01-29 08:00 | 2014-02-16 17:00 |  | PT_Normal |  |  |  |  | VjAL/21PT2WWUsViTB20WQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34750 | N | N | 15 | FIRST FLOORS |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1374 | LABOR- SUBCONTRACTOR
%R | 501106 | 6359 | 124591 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARFF3330 | Paint First coat | 8178 | 232 | 208 | 200 | 0 | 5256.25 | 5256.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-25 08:00 | 2014-03-25 17:00 |  | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 |  | PT_Normal |  |  |  |  | qRKC2pnwQF+UU+vpxJKX2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34750 | N | N | 15 | FIRST FLOORS |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 5256.25 | LABOR- SUBCONTRACTOR
%R | 501107 | 6359 | 124591 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARFF3320 | Ceramic Wall Tiling | 8170 | 24 | 0 | 200 | 0 | 1516 | 1516 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-08 08:00 | 2014-03-09 17:00 |  | 2014-02-04 08:00 | 2014-03-05 17:00 | 2014-02-04 08:00 | 2014-03-05 17:00 | 2014-02-04 08:00 | 2014-03-05 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 |  | PT_Normal |  |  |  |  | s0IEtEW2RmCLG196rvxWNA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34750 | N | N | 15 | FIRST FLOORS |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 758 | TILE MASON SK
%R | 501108 | 6359 | 124591 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARFF3325 | Porcelain Tile flooring | 8170 | 24 | 0 | 200 | 0 | 1341 | 1341 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-18 17:00 |  | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | brcgwmubTOGzm5vFcfN6VQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34750 | N | N | 15 | FIRST FLOORS |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 670.5 | TILE MASON SK
%R | 501109 | 6359 | 124591 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARFF3335 | Slate Tile Flooring & Skirting | 8170 | 176 | 152 | 120 | 0 | 931.25 | 931.25 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-30 08:00 | 2014-04-15 17:00 |  | 2014-03-04 08:00 | 2014-03-20 17:00 | 2014-03-04 08:00 | 2014-03-20 17:00 | 2014-03-04 08:00 | 2014-03-20 17:00 | 2014-03-30 08:00 | 2014-04-15 17:00 |  | PT_Normal |  |  |  |  | j8LAh99rRJG/iYIQKX/rLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34750 | N | N | 15 | FIRST FLOORS |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 931.25 | TILE MASON SK
%R | 501110 | 6359 | 124591 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARFF3350 | Granite - Stair case flooring & Skirting | 8171 | 112 | 88 | 160 | 0 | 850 | 850 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-24 08:00 | 2014-04-15 17:00 |  | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-24 08:00 | 2014-04-15 17:00 |  | PT_Normal |  |  |  |  | agjqM/q6TjyYyppNOJksOw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34750 | N | N | 15 | FIRST FLOORS |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 850 | GRANITE MASON SK
%R | 501111 | 6359 | 124591 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARFF3345 | Fixing of Suspension systems | 8178 | 24 | 0 | 160 | 0 | 1143.5 | 1143.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-04-02 17:00 |  | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-11 08:00 | 2014-04-02 17:00 |  | PT_Normal |  |  |  |  | xot4oBxASDipy7jGJIrtWA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34750 | N | N | 15 | FIRST FLOORS |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1143.5 | LABOR- SUBCONTRACTOR
%R | 501112 | 6359 | 124591 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARFF3360 | Gypsum board false ceiling | 8178 | 24 | 0 | 200 | 0 | 1191 | 1191 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-23 08:00 | 2014-04-20 17:00 |  | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | iD9m9/G9QYqO72Xnv87nJA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34750 | N | N | 15 | FIRST FLOORS |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1191 | LABOR- SUBCONTRACTOR
%R | 501113 | 6359 | 124591 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARFF3370 | Aluminum Door | 8178 | 24 | 0 | 160 | 0 | 132 | 132 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-07 17:00 |  | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-04-15 08:00 | 2014-05-07 17:00 |  | PT_Normal |  |  |  |  | rUj6MHorTRuT99NSLfKywA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34750 | N | N | 15 | FIRST FLOORS |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 132 | LABOR- SUBCONTRACTOR
%R | 501114 | 6359 | 124591 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARFF3380 | Aluminum windows | 8178 | 128 | 104 | 160 | 0 | 272.25 | 272.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-07 08:00 | 2014-05-29 17:00 |  | 2014-04-19 08:00 | 2014-05-11 17:00 | 2014-04-19 08:00 | 2014-05-11 17:00 | 2014-04-19 08:00 | 2014-05-11 17:00 | 2014-05-07 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | XwnRCx6iRDiUnWYjPZBK8A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34750 | N | N | 15 | FIRST FLOORS |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 272.25 | LABOR- SUBCONTRACTOR
%R | 501115 | 6359 | 124591 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARFF3375 | Carpentry & Joinery Works | 8178 | 24 | 0 | 200 | 0 | 704 | 704 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-05-21 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | MCJz6q6YR3+eGsTwB5dkTA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34750 | N | N | 15 | FIRST FLOORS |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 704 | LABOR- SUBCONTRACTOR
%R | 501116 | 6359 | 124591 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARFF3390 | Installation of Granite Counter Top | 8171 | 40 | 16 | 160 | 0 | 110 | 110 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-10 08:00 | 2014-06-01 17:00 |  | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-05-10 08:00 | 2014-06-01 17:00 |  | PT_Normal |  |  |  |  | IlsxpiOoSdmWhREXOMKeCw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34750 | N | N | 15 | FIRST FLOORS |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 110 | GRANITE MASON SK
%R | 501117 | 6359 | 124591 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARFF3385 | Handrail & Balustrade | 8178 | 24 | 0 | 160 | 0 | 175 | 175 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-07 08:00 | 2014-05-29 17:00 |  | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-05-07 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | zAMCFvfFSLCSxRmlTN0Wig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34750 | N | N | 15 | FIRST FLOORS |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 175 | LABOR- SUBCONTRACTOR
%R | 501118 | 6359 | 124591 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARFF3395 | Final Painting | 8178 | 24 | 0 | 200 | 0 | 5256.25 | 5256.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | UDyyfpfiTOOjF+qm2bkU3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34750 | N | N | 15 | FIRST FLOORS |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 5256.25 | LABOR- SUBCONTRACTOR
%R | 501119 | 6359 | 124591 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARFF3365 | Wooden door | 8178 | 24 | 0 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-07 08:00 | 2014-04-23 17:00 |  | 2014-04-03 08:00 | 2014-04-20 17:00 | 2014-04-03 08:00 | 2014-04-20 17:00 | 2014-04-03 08:00 | 2014-04-20 17:00 | 2014-04-07 08:00 | 2014-04-23 17:00 |  | PT_Normal |  |  |  |  | Sp4fnZ53S82onVfcI8EFzg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34750 | N | N | 15 | FIRST FLOORS |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 176 | LABOR- SUBCONTRACTOR
%R | 501120 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3000 | Block work | 8168 | 352 | 0 | 200 | 0 | 9262.5 | 9262.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-17 08:00 | 2014-01-15 17:00 |  | 2013-10-27 08:00 | 2013-11-24 17:00 | 2013-10-27 08:00 | 2013-11-24 17:00 | 2013-10-27 08:00 | 2013-11-24 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | NHMq5cmUQyG1OLddD5B1ZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 9262.5 | BLOCK MASON SK
%R | 501121 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3005 | Plastering work | 8169 | 400 | 0 | 200 | 0 | 11350 | 11350 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-02-15 17:00 |  | 2013-11-18 08:00 | 2013-12-16 17:00 | 2013-11-18 08:00 | 2013-12-16 17:00 | 2013-11-18 08:00 | 2013-12-16 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 |  | PT_Normal |  |  |  |  | 4+2pI7PgRL2QSR6WDNntPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 11350 | PLASTER MASON SK
%R | 501122 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3010 | Flooring screed | 8164 | 464 | 64 | 168 | 0 | 2171.5 | 2171.5 | 168 | 0 | 0 | 0 |  |  |  | 2014-02-03 08:00 | 2014-02-27 17:00 |  | 2013-11-26 08:00 | 2013-12-21 17:00 | 2013-11-26 08:00 | 2013-12-21 17:00 | 2013-11-26 08:00 | 2013-12-21 17:00 | 2014-02-03 08:00 | 2014-02-27 17:00 |  | PT_Normal |  |  |  |  | QjoTB9jwR5Gl4B1IEagJ6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 2171.5 | SCREED MASON SK
%R | 501123 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 400 | 0 | 120 | 0 | 423.5 | 423.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-03 08:00 | 2014-02-20 17:00 |  | 2013-12-05 08:00 | 2013-12-23 17:00 | 2013-12-05 08:00 | 2013-12-23 17:00 | 2013-12-05 08:00 | 2013-12-23 17:00 | 2014-02-03 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | yG+nBXvhS32lq1/mNKYILg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 423.5 | LABOR- SUBCONTRACTOR
%R | 501124 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3030 | Paint First coat | 8178 | 512 | 0 | 200 | 0 | 5936.25 | 5936.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-19 08:00 | 2014-03-19 17:00 |  | 2013-12-04 08:00 | 2014-01-02 17:00 | 2013-12-04 08:00 | 2014-01-02 17:00 | 2013-12-04 08:00 | 2014-01-02 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 |  | PT_Normal |  |  |  |  | ULdgzAUYQiGn54e0i26Khg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 5936.25 | LABOR- SUBCONTRACTOR
%R | 501125 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3020 | Ceramic Wall Tiling | 8170 | 400 | 0 | 200 | 0 | 3534.75 | 3534.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-03-10 17:00 |  | 2013-12-11 08:00 | 2014-01-09 17:00 | 2013-12-11 08:00 | 2014-01-09 17:00 | 2013-12-11 08:00 | 2014-01-09 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | xGHwp+MVRq24EMZIV9xGhQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 3534.75 | TILE MASON SK
%R | 501126 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3025 | Porcelain Tile flooring | 8170 | 400 | 0 | 200 | 0 | 1918.75 | 1918.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-16 17:00 |  | 2013-12-17 08:00 | 2014-01-15 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | 2Y00M3DaRU+ktfWC1Lya6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1918.75 | TILE MASON SK
%R | 501127 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3040 | Cobble Tile flooring | 8170 | 464 | 0 | 120 | 0 | 700 | 700 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-24 08:00 | 2014-04-09 17:00 |  | 2014-01-14 08:00 | 2014-01-30 17:00 | 2014-01-14 08:00 | 2014-01-30 17:00 | 2014-01-14 08:00 | 2014-01-30 17:00 | 2014-03-24 08:00 | 2014-04-09 17:00 |  | PT_Normal |  |  |  |  | QR6FeOqKSBeuMH8awsFqUg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 700 | TILE MASON SK
%R | 501128 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 480 | 16 | 120 | 0 | 931.25 | 931.25 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-05 17:00 |  | 2014-01-07 08:00 | 2014-01-23 17:00 | 2014-01-07 08:00 | 2014-01-23 17:00 | 2014-01-07 08:00 | 2014-01-23 17:00 | 2014-03-19 08:00 | 2014-04-05 17:00 |  | PT_Normal |  |  |  |  | paKG+NMOTemZhubUBy2l8g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 931.25 | TILE MASON SK
%R | 501129 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 464 | 0 | 160 | 0 | 850 | 850 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-01 08:00 | 2014-04-23 17:00 |  | 2014-01-22 08:00 | 2014-02-15 17:00 | 2014-01-22 08:00 | 2014-02-15 17:00 | 2014-01-22 08:00 | 2014-02-15 17:00 | 2014-04-01 08:00 | 2014-04-23 17:00 |  | PT_Normal |  |  |  |  | oaarRiqRTdKcvYXAe50bSw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 850 | GRANITE MASON SK
%R | 501130 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3045 | Fixing of Suspension systems | 8178 | 400 | 0 | 160 | 0 | 1320.5 | 1320.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-05 08:00 | 2014-03-27 17:00 |  | 2014-01-05 08:00 | 2014-01-27 17:00 | 2014-01-05 08:00 | 2014-01-27 17:00 | 2014-01-05 08:00 | 2014-01-27 17:00 | 2014-03-05 08:00 | 2014-03-27 17:00 |  | PT_Normal |  |  |  |  | Z/BLywBaRU6CU89Syy/JoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1320.5 | LABOR- SUBCONTRACTOR
%R | 501131 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3055 | Aluminum tile false ceiling | 8178 | 424 | 24 | 200 | 0 | 130 | 130 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-14 17:00 |  | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 |  | PT_Normal |  |  |  |  | DQGMCK4dT96gXfMBztLAag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 130 | LABOR- SUBCONTRACTOR
%R | 501132 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3060 | Gypsum board false ceiling | 8178 | 400 | 0 | 200 | 0 | 1216.3 | 1216.3 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-14 17:00 |  | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 |  | PT_Normal |  |  |  |  | NHh0I6dER/CHJrc6hHNDRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1216.3 | LABOR- SUBCONTRACTOR
%R | 501133 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3065 | Wooden door & PVC Door | 8178 | 464 | 0 | 120 | 0 | 660 | 660 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-01 17:00 |  | 2014-02-05 08:00 | 2014-02-23 17:00 | 2014-02-05 08:00 | 2014-02-23 17:00 | 2014-02-05 08:00 | 2014-02-23 17:00 | 2014-04-15 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | JfrNAlUMR0qr6FqUwrdn8g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 660 | LABOR- SUBCONTRACTOR
%R | 501134 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3070 | Aluminum doors | 8178 | 464 | 0 | 120 | 0 | 88 | 88 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-21 08:00 | 2014-05-07 17:00 |  | 2014-02-12 08:00 | 2014-03-01 17:00 | 2014-02-12 08:00 | 2014-03-01 17:00 | 2014-02-12 08:00 | 2014-03-01 17:00 | 2014-04-21 08:00 | 2014-05-07 17:00 |  | PT_Normal |  |  |  |  | zM00yTi1StuTr96JpZ51Bw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 88 | LABOR- SUBCONTRACTOR
%R | 501135 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3080 | Aluminum windows | 8178 | 544 | 40 | 160 | 0 | 257.5 | 257.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-10 08:00 | 2014-06-01 17:00 |  | 2014-02-19 08:00 | 2014-03-13 17:00 | 2014-02-19 08:00 | 2014-03-13 17:00 | 2014-02-19 08:00 | 2014-03-13 17:00 | 2014-05-10 08:00 | 2014-06-01 17:00 |  | PT_Normal |  |  |  |  | 95FoPM8vQvKZs/iQogPeTQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 257.5 | LABOR- SUBCONTRACTOR
%R | 501136 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3075 | Carpentry & Joinery Works | 8178 | 464 | 0 | 160 | 0 | 528 | 528 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-27 08:00 | 2014-05-19 17:00 |  | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-04-27 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | PKLCjScURKi+QAg3bw2wlw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 528 | LABOR- SUBCONTRACTOR
%R | 501137 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3090 | Installation of Granite Counter Top | 8171 | 464 | 0 | 120 | 0 | 242 | 242 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-10 08:00 | 2014-05-26 17:00 |  | 2014-03-03 08:00 | 2014-03-19 17:00 | 2014-03-03 08:00 | 2014-03-19 17:00 | 2014-03-03 08:00 | 2014-03-19 17:00 | 2014-05-10 08:00 | 2014-05-26 17:00 |  | PT_Normal |  |  |  |  | jbeSzfDQQDuVqNnzeBNZgQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 242 | GRANITE MASON SK
%R | 501138 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3085 | S.S.Balustrade | 8178 | 504 | 40 | 160 | 0 | 175 | 175 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-06-02 17:00 |  | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-05-11 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | TTWlHEjdTAG/UFJuJvJOpw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 175 | LABOR- SUBCONTRACTOR
%R | 501139 | 6359 | 124592 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1BZ1ARGF3095 | Final Painting | 8178 | 464 | 0 | 200 | 0 | 5936.25 | 5936.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-03-12 08:00 | 2014-04-09 17:00 | 2014-03-12 08:00 | 2014-04-09 17:00 | 2014-03-12 08:00 | 2014-04-09 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | 4OqIeo4xTiOQfuvM9Dasyw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34740 | N | N | 10 | GROUND FLOOR |  | 124589 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 5936.25 | LABOR- SUBCONTRACTOR
%R | 501140 | 6359 | 124596 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1ELGL5215 | Excavation Cable Trenches & Duct Banks | 8177 | 24 | 0 | 200 | 0 | 2077 | 2077 | 200 | 751 | 0 | 751 |  |  |  | 2013-12-08 08:00 | 2014-01-06 17:00 |  | 2013-12-04 08:00 | 2014-01-02 17:00 | 2013-12-04 08:00 | 2014-01-02 17:00 | 2013-12-04 08:00 | 2014-01-02 17:00 | 2013-12-08 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | hWDk4Bz4R0urMUAAbMVZDQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38830 | N | N | 30 | ELECTRICAL LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 2077 | LABOR - CIVIL
%R | 501141 | 6359 | 124596 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1ELGL5220 | Laying of electrical cables | 8178 | 48 | 0 | 200 | 0 | 3141.2 | 3141.2 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-17 08:00 | 2014-01-15 17:00 |  | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | bV3KMLRORYq9g/VMEjpTEQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38830 | N | N | 30 | ELECTRICAL LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 3141.2 | LABOR- SUBCONTRACTOR
%R | 501142 | 6359 | 124596 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1ELGL5225 | Backfilling Electrical trench | 8177 | 48 | 0 | 200 | 0 | 1359 | 1359 | 200 | 825 | 0 | 825 |  |  |  | 2013-12-26 08:00 | 2014-01-23 17:00 |  | 2013-12-19 08:00 | 2014-01-16 17:00 | 2013-12-19 08:00 | 2014-01-16 17:00 | 2013-12-19 08:00 | 2014-01-16 17:00 | 2013-12-26 08:00 | 2014-01-23 17:00 |  | PT_Normal |  |  |  |  | C49W1+JNTa+Zg7UIa3jWYQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38830 | N | N | 30 | ELECTRICAL LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1359 | LABOR - CIVIL
%R | 501143 | 6359 | 124596 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1ELGL5230 | Construction of Submain Board & Feeder Pillar | 8165 | 408 | 0 | 200 | 0 | 520 | 520 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-30 17:00 |  | 2013-12-31 08:00 | 2014-01-28 17:00 | 2013-12-31 08:00 | 2014-01-28 17:00 | 2013-12-31 08:00 | 2014-01-28 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | oKH3yaPnR1i8/ozZd+SloQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38830 | N | N | 30 | ELECTRICAL LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 520 | STEEL FIXERS SK
%R | 501144 | 6359 | 124597 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1PSGL7000 | Excavation | 8177 | 208 | 40 | 120 | 0 | 37 | 37 | 120 | 31 | 0 | 31 |  |  |  | 2014-04-15 08:00 | 2014-05-01 17:00 |  | 2014-03-16 08:00 | 2014-04-01 17:00 | 2014-03-16 08:00 | 2014-04-01 17:00 | 2014-03-16 08:00 | 2014-04-01 17:00 | 2014-04-15 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | RtZPcY5AQZqLsok5XogBnw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38890 | N | N | 60 | PARKING SHED |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 37 | LABOR - CIVIL
%R | 501145 | 6359 | 124597 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1PSGL7005 | Foundation casting | 8165 | 168 | 0 | 120 | 0 | 938 | 938 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-21 08:00 | 2014-05-07 17:00 |  | 2014-03-27 08:00 | 2014-04-13 17:00 | 2014-03-27 08:00 | 2014-04-13 17:00 | 2014-03-27 08:00 | 2014-04-13 17:00 | 2014-04-21 08:00 | 2014-05-07 17:00 |  | PT_Normal |  |  |  |  | dT+Vx6bnQSi4wlUzcZLY1w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38890 | N | N | 60 | PARKING SHED |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 938 | STEEL FIXERS SK
%R | 501146 | 6359 | 124597 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1PSGL7010 | Column, Frame& Fabrics Erection | 8178 | 168 | 0 | 200 | 0 | 122 | 122 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-03 08:00 | 2014-05-31 17:00 |  | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 |  | PT_Normal |  |  |  |  | blUr58ZESzKZTndc+tQleg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38890 | N | N | 60 | PARKING SHED |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 122 | LABOR- SUBCONTRACTOR
%R | 501147 | 6359 | 124597 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1PSGL7015 | Electrical Works-Parking Shed | 8178 | 168 | 144 | 200 | 0 | 275.2 | 275.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-08 08:00 | 2014-06-05 17:00 |  | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-05-08 08:00 | 2014-06-05 17:00 |  | PT_Normal |  |  |  |  | NuS4yEKFRnOzLnESnX8biw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38890 | N | N | 60 | PARKING SHED |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 275.2 | LABOR- SUBCONTRACTOR
%R | 501148 | 6359 | 124598 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1TCGL5295 | Excavation Telecommunication trenches | 8177 | 24 | 0 | 160 | 0 | 178 | 178 | 160 | 100 | 0 | 100 |  |  |  | 2014-01-01 08:00 | 2014-01-23 17:00 |  | 2013-12-29 08:00 | 2014-01-20 17:00 | 2013-12-29 08:00 | 2014-01-20 17:00 | 2013-12-29 08:00 | 2014-01-20 17:00 | 2014-01-01 08:00 | 2014-01-23 17:00 |  | PT_Normal |  |  |  |  | LjdjZI5lRiOWfZjfTMaCVQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38860 | N | N | 45 | TELECOMMUNICATION LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 178 | LABOR - CIVIL
%R | 501149 | 6359 | 124598 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1TCGL5300 | Laying of cables | 8178 | 24 | 0 | 160 | 0 | 369.2 | 369.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-07 08:00 | 2014-01-29 17:00 |  | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | qg1r0IOcRPa3M8meuPyrxQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38860 | N | N | 45 | TELECOMMUNICATION LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 369.2 | LABOR- SUBCONTRACTOR
%R | 501150 | 6359 | 124598 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1TCGL5305 | Backfilling telecommunication trench | 8177 | 24 | 0 | 160 | 0 | 140 | 140 | 160 | 110 | 0 | 110 |  |  |  | 2014-01-13 08:00 | 2014-02-04 17:00 |  | 2014-01-09 08:00 | 2014-02-01 17:00 | 2014-01-09 08:00 | 2014-02-01 17:00 | 2014-01-09 08:00 | 2014-02-01 17:00 | 2014-01-13 08:00 | 2014-02-04 17:00 |  | PT_Normal |  |  |  |  | 2AQ4bWrpSZqLEJtnTJ6++w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38860 | N | N | 45 | TELECOMMUNICATION LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 140 | LABOR - CIVIL
%R | 501151 | 6359 | 124598 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1TCGL5310 | Connection & Installation | 8178 | 544 | 184 | 160 | 0 | 180.8 | 180.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-04 17:00 |  | 2014-01-21 08:00 | 2014-02-13 17:00 | 2014-01-21 08:00 | 2014-02-13 17:00 | 2014-01-21 08:00 | 2014-02-13 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | oQZGzy2OSpCzqz/m91xFMQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38860 | N | N | 45 | TELECOMMUNICATION LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 180.8 | LABOR- SUBCONTRACTOR
%R | 501152 | 6359 | 124599 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1WSGL5155 | Excavation for water line | 8177 | 8 | 0 | 200 | 0 | 239 | 239 | 200 | 125 | 0 | 125 |  |  |  | 2013-10-13 08:00 | 2013-11-12 17:00 |  | 2013-10-12 08:00 | 2013-11-11 17:00 | 2013-10-12 08:00 | 2013-11-11 17:00 | 2013-10-12 08:00 | 2013-11-11 17:00 | 2013-10-13 08:00 | 2013-11-12 17:00 |  | PT_Normal |  |  |  |  | 0v+oq0LNQQG/Km1LlxAAxA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38810 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 239 | LABOR - CIVIL
%R | 501153 | 6359 | 124599 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1WSGL5160 | Laying of water line | 8178 | 8 | 0 | 200 | 0 | 302.4 | 302.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-21 08:00 | 2013-11-18 17:00 |  | 2013-10-20 08:00 | 2013-11-17 17:00 | 2013-10-20 08:00 | 2013-11-17 17:00 | 2013-10-20 08:00 | 2013-11-17 17:00 | 2013-10-21 08:00 | 2013-11-18 17:00 |  | PT_Normal |  |  |  |  | Jw/Lx009TG2bZ9SfBPiAAA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38810 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 302.4 | LABOR- SUBCONTRACTOR
%R | 501154 | 6359 | 124599 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1WSGL5165 | Testing of potable water line | 8178 | 8 | 0 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-27 08:00 | 2013-11-24 17:00 |  | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-27 08:00 | 2013-11-24 17:00 |  | PT_Normal |  |  |  |  | c+qc+B83T1edt2AlCz5bBQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38810 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 84 | LABOR- SUBCONTRACTOR
%R | 501155 | 6359 | 124599 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1WSGL5170 | Backfilling potable water line | 8177 | 8 | 0 | 200 | 0 | 187 | 187 | 200 | 139 | 0 | 139 |  |  |  | 2013-11-02 08:00 | 2013-11-30 17:00 |  | 2013-10-31 08:00 | 2013-11-28 17:00 | 2013-10-31 08:00 | 2013-11-28 17:00 | 2013-10-31 08:00 | 2013-11-28 17:00 | 2013-11-02 08:00 | 2013-11-30 17:00 |  | PT_Normal |  |  |  |  | 0sRnUxivQOa3FtODUxFeGA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38810 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 187 | LABOR - CIVIL
%R | 501156 | 6359 | 124599 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1WSGL5175 | Construction of valve chambers & Thrust Blocks | 8172 | 256 | 0 | 200 | 0 | 66 | 66 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-14 08:00 | 2014-01-12 17:00 |  | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 |  | PT_Normal |  |  |  |  | 04CkaujSTaGg4chYUxAmEw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38810 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 66 | MANHOLES SK
%R | 501157 | 6359 | 124599 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1WSGL5180 | Installation of meter ,Accessories & Connection | 8178 | 256 | 96 | 160 | 0 | 33.6 | 33.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-02-04 17:00 |  | 2013-12-05 08:00 | 2013-12-29 17:00 | 2013-12-05 08:00 | 2013-12-29 17:00 | 2013-12-05 08:00 | 2013-12-29 17:00 | 2014-01-13 08:00 | 2014-02-04 17:00 |  | PT_Normal |  |  |  |  | SlcD40DXSIOtiZdMOvomuw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38810 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 33.6 | LABOR- SUBCONTRACTOR
%R | 501158 | 6359 | 124600 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1SAGL5135 | Construction of manholes Drainage | 8172 | 496 | 144 | 200 | 0 | 36 | 36 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-14 08:00 | 2014-01-12 17:00 |  | 2013-09-30 08:00 | 2013-10-30 17:00 | 2013-09-30 08:00 | 2013-10-30 17:00 | 2013-09-30 08:00 | 2013-10-30 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 |  | PT_Normal |  |  |  |  | ibZQKPQ7SX6gBXcKmdKHCA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38800 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 18 | MANHOLES SK
%R | 501159 | 6359 | 124600 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1SAGL5140 | Construction of soakaways | 8172 | 8 | 0 | 200 | 0 | 102 | 102 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-01 08:00 | 2013-10-31 17:00 |  | 2013-09-30 08:00 | 2013-10-30 17:00 | 2013-09-30 08:00 | 2013-10-30 17:00 | 2013-09-30 08:00 | 2013-10-30 17:00 | 2013-10-01 08:00 | 2013-10-31 17:00 |  | PT_Normal |  |  |  |  | ed1Yy6NHSvak99jvN3o4ug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38800 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 51 | MANHOLES SK
%R | 501160 | 6359 | 124600 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1SAGL5145 | Construction of Road gullies | 8172 | 8 | 0 | 200 | 0 | 102 | 102 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-02 08:00 | 2013-11-30 17:00 |  | 2013-10-31 08:00 | 2013-11-28 17:00 | 2013-10-31 08:00 | 2013-11-28 17:00 | 2013-10-31 08:00 | 2013-11-28 17:00 | 2013-11-02 08:00 | 2013-11-30 17:00 |  | PT_Normal |  |  |  |  | 68V0VyFUT2q2wQHXL/qvbg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38800 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 102 | MANHOLES SK
%R | 501161 | 6359 | 124600 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1SAGL5150 | Connection with existing sewer manhole | 8172 | 296 | 272 | 160 | 0 | 36 | 36 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-02-04 17:00 |  | 2013-11-30 08:00 | 2013-12-23 17:00 | 2013-11-30 08:00 | 2013-12-23 17:00 | 2013-11-30 08:00 | 2013-12-23 17:00 | 2014-01-13 08:00 | 2014-02-04 17:00 |  | PT_Normal |  |  |  |  | SAS9s1e4TZSrwk7ahgB8sw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38800 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 36 | MANHOLES SK
%R | 501162 | 6359 | 124601 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1STGL5235 | Excavation for Street lighting | 8177 | 24 | 0 | 200 | 0 | 184 | 184 | 200 | 100 | 0 | 100 |  |  |  | 2013-12-08 08:00 | 2014-01-06 17:00 |  | 2013-12-04 08:00 | 2014-01-02 17:00 | 2013-12-04 08:00 | 2014-01-02 17:00 | 2013-12-04 08:00 | 2014-01-02 17:00 | 2013-12-08 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | biKYGY57R4m8u4mR8ZD/0A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38840 | N | N | 35 | STREET LIGHTING |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 184 | LABOR - CIVIL
%R | 501163 | 6359 | 124601 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1STGL5240 | Construction of Duct Banks | 8178 | 24 | 0 | 200 | 0 | 340.8 | 340.8 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-14 08:00 | 2014-01-12 17:00 |  | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 |  | PT_Normal |  |  |  |  | MKkKuowYQsuB7QI5hj681g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38840 | N | N | 35 | STREET LIGHTING |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 340.8 | LABOR- SUBCONTRACTOR
%R | 501164 | 6359 | 124601 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1STGL5245 | Construction of Foundation | 8172 | 24 | 0 | 200 | 0 | 506 | 506 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-14 08:00 | 2014-01-12 17:00 |  | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 |  | PT_Normal |  |  |  |  | AJwqhlbqSVuubevHlhnsLw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38840 | N | N | 35 | STREET LIGHTING |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 506 | MANHOLES SK
%R | 501165 | 6359 | 124601 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1STGL5250 | Backfilling Street Lighting | 8177 | 24 | 0 | 200 | 0 | 146 | 146 | 200 | 110 | 0 | 110 |  |  |  | 2013-12-21 08:00 | 2014-01-18 17:00 |  | 2013-12-16 08:00 | 2014-01-14 17:00 | 2013-12-16 08:00 | 2014-01-14 17:00 | 2013-12-16 08:00 | 2014-01-14 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | Vx8RE0D/Ru6bIyNZK3KzEw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38840 | N | N | 35 | STREET LIGHTING |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 146 | LABOR - CIVIL
%R | 501166 | 6359 | 124601 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1STGL5255 | Installation of light Post | 8178 | 528 | 104 | 200 | 0 | 170.4 | 170.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-23 08:00 | 2014-04-20 17:00 |  | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | 9dr6eplOSnCfCSaZ6dYLLw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:40 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38840 | N | N | 35 | STREET LIGHTING |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 170.4 | LABOR- SUBCONTRACTOR
%R | 501167 | 6359 | 124601 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1STGL5260 | Electrical Works | 8178 | 408 | 144 | 200 | 0 | 142 | 142 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-28 17:00 |  | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | tEMM8LXOThK8gslzdybDAA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38840 | N | N | 35 | STREET LIGHTING |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 142 | LABOR- SUBCONTRACTOR
%R | 501168 | 6359 | 124602 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1IRGL5265 | Excavation for irrigation line | 8177 | 232 | 0 | 200 | 0 | 93 | 93 | 200 | 51 | 0 | 51 |  |  |  | 2014-02-22 08:00 | 2014-03-22 17:00 |  | 2014-01-18 08:00 | 2014-02-16 17:00 | 2014-01-18 08:00 | 2014-02-16 17:00 | 2014-01-18 08:00 | 2014-02-16 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | k//Fxg0QRt2lI/GSO/VDXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38850 | N | N | 40 | IRRIGATION LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 93 | LABOR - CIVIL
%R | 501169 | 6359 | 124602 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1IRGL5270 | Laying of irrigationline | 8178 | 232 | 0 | 200 | 0 | 50.4 | 50.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-27 08:00 | 2014-03-27 17:00 |  | 2014-01-23 08:00 | 2014-02-22 17:00 | 2014-01-23 08:00 | 2014-02-22 17:00 | 2014-01-23 08:00 | 2014-02-22 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 |  | PT_Normal |  |  |  |  | kUiJ7qeHR0e6kE56HHcGBw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38850 | N | N | 40 | IRRIGATION LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 501170 | 6359 | 124602 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1IRGL5275 | Testing of irrigation line | 8178 | 232 | 0 | 200 | 0 | 50.4 | 50.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-05 08:00 | 2014-04-02 17:00 |  | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 |  | PT_Normal |  |  |  |  | ujytmvhRQqmkAzIKET/7Vw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38850 | N | N | 40 | IRRIGATION LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 501171 | 6359 | 124602 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1IRGL5280 | Backfilling irrigation line | 8177 | 232 | 0 | 200 | 0 | 73 | 73 | 200 | 55 | 0 | 55 |  |  |  | 2014-03-11 08:00 | 2014-04-08 17:00 |  | 2014-02-04 08:00 | 2014-03-05 17:00 | 2014-02-04 08:00 | 2014-03-05 17:00 | 2014-02-04 08:00 | 2014-03-05 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | 80acVa4DRlSXQo8MXY2k2Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38850 | N | N | 40 | IRRIGATION LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 36.5 | LABOR - CIVIL
%R | 501172 | 6359 | 124602 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1IRGL5285 | Construction of Thrust Blocks,Pull boxes | 8178 | 272 | 0 | 200 | 0 | 193.6 | 193.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-29 08:00 | 2014-04-26 17:00 |  | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-03-29 08:00 | 2014-04-26 17:00 |  | PT_Normal |  |  |  |  | NH7tjulAT/G/2bnjlhS0QA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38850 | N | N | 40 | IRRIGATION LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 96.8 | LABOR- SUBCONTRACTOR
%R | 501173 | 6359 | 124602 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1IRGL5290 | Irrigation Fittings (Nozzle,Values) | 8178 | 272 | 88 | 200 | 0 | 33.6 | 33.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-05-04 17:00 |  | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-04-06 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | 2enRg8U5RVeFCiH5CFDp9A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38850 | N | N | 40 | IRRIGATION LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 16.8 | LABOR- SUBCONTRACTOR
%R | 501174 | 6359 | 124603 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1SLGL7200 | Excavation | 8177 | 184 | 0 | 200 | 0 | 658 | 658 | 200 | 376 | 0 | 376 |  |  |  | 2014-04-06 08:00 | 2014-05-04 17:00 |  | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-04-06 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | zgKCNapdSKWYiZuUEPj/gQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38910 | N | N | 70 | SOFT LANDSCAPING |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 658 | LABOR - CIVIL
%R | 501175 | 6359 | 124603 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1SLGL7205 | Sweet Soil Laying | 8178 | 184 | 0 | 200 | 0 | 140 | 140 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | hcdqdxPpS1mJ1ao1accU+Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38910 | N | N | 70 | SOFT LANDSCAPING |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 140 | LABOR- SUBCONTRACTOR
%R | 501176 | 6359 | 124603 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1SLGL7210 | Plantation works | 8178 | 264 | 144 | 200 | 0 | 266 | 266 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-06-08 17:00 |  | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | giTDfJkSRbmuJgSNxkqiEA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38910 | N | N | 70 | SOFT LANDSCAPING |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 266 | LABOR- SUBCONTRACTOR
%R | 501177 | 6359 | 124604 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1HDGL7020 | Precast Concrete Kerbs works | 8173 | 184 | 0 | 160 | 0 | 186 | 186 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-24 17:00 |  | 2014-02-02 08:00 | 2014-02-25 17:00 | 2014-02-02 08:00 | 2014-02-25 17:00 | 2014-02-02 08:00 | 2014-02-25 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | sg4fucxUQ1qLGrKFDJeeKA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38900 | N | N | 65 | HARD LANDSCAPING |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 186 | KERBSTONE MASON SK
%R | 501178 | 6359 | 124604 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1HDGL7025 | Interlocking for Walkways | 8174 | 184 | 0 | 200 | 0 | 432 | 432 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-04-10 17:00 |  | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | GO3/a52yTVO2NaOe4vh8NQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38900 | N | N | 65 | HARD LANDSCAPING |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 216 | INTERLOCK MASON SK
%R | 501179 | 6359 | 124604 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1HDGL7030 | Construction of Retaining wall | 8165 | 184 | 0 | 200 | 0 | 376 | 376 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-25 08:00 | 2014-04-22 17:00 |  | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | g7ehXK7RR0C5HbdZtN1ZQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38900 | N | N | 65 | HARD LANDSCAPING |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 188 | STEEL FIXERS SK
%R | 501180 | 6359 | 124604 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1HDGL7035 | Construction of Wash Stone Boulders | 8170 | 184 | 0 | 200 | 0 | 66 | 66 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-25 08:00 | 2014-04-22 17:00 |  | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | kdub3R0fSSmOV1cd1gvl2w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38900 | N | N | 65 | HARD LANDSCAPING |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 33 | TILE MASON SK
%R | 501181 | 6359 | 124604 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1HDGL7040 | Construction of Speed Humps | 8167 | 264 | 264 | 80 | 0 | 14 | 14 | 80 | 0 | 0 | 0 |  |  |  | 2014-05-22 08:00 | 2014-06-02 17:00 |  | 2014-04-14 08:00 | 2014-04-24 17:00 | 2014-04-14 08:00 | 2014-04-24 17:00 | 2014-04-14 08:00 | 2014-04-24 17:00 | 2014-05-22 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | skkA0rkvQOCfNz6YbNmLcg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38900 | N | N | 65 | HARD LANDSCAPING |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 14 | CONCRETE MASON SK
%R | 501182 | 6359 | 124605 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1FFGL5185 | Excavation for firefighting line | 8177 | 8 | 0 | 200 | 0 | 87 | 87 | 200 | 51 | 0 | 51 |  |  |  | 2013-11-07 08:00 | 2013-12-05 17:00 |  | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-11-07 08:00 | 2013-12-05 17:00 |  | PT_Normal |  |  |  |  | G/FkUWUrTcOBtMCc7KYIGg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38820 | N | N | 25 | FIREFIGHTING LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 87 | LABOR - CIVIL
%R | 501183 | 6359 | 124605 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1FFGL5190 | Laying of firefighting line | 8178 | 8 | 0 | 200 | 0 | 82.8 | 82.8 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-16 08:00 | 2013-12-14 17:00 |  | 2013-11-14 08:00 | 2013-12-12 17:00 | 2013-11-14 08:00 | 2013-12-12 17:00 | 2013-11-14 08:00 | 2013-12-12 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 |  | PT_Normal |  |  |  |  | JgqwzYy5ROuMnRmYr4BDQA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38820 | N | N | 25 | FIREFIGHTING LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 82.8 | LABOR- SUBCONTRACTOR
%R | 501184 | 6359 | 124605 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1FFGL5195 | Testing of firefighting line | 8178 | 8 | 0 | 200 | 0 | 44.4 | 44.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-21 08:00 | 2013-12-21 17:00 |  | 2013-11-20 08:00 | 2013-12-19 17:00 | 2013-11-20 08:00 | 2013-12-19 17:00 | 2013-11-20 08:00 | 2013-12-19 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 |  | PT_Normal |  |  |  |  | hFYVkDVPS0ScHD2Fpf8puw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38820 | N | N | 25 | FIREFIGHTING LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 44.4 | LABOR- SUBCONTRACTOR
%R | 501185 | 6359 | 124605 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1FFGL5200 | Backfilling firefighting line | 8177 | 8 | 0 | 200 | 0 | 73 | 73 | 200 | 55 | 0 | 55 |  |  |  | 2013-11-27 08:00 | 2013-12-26 17:00 |  | 2013-11-26 08:00 | 2013-12-25 17:00 | 2013-11-26 08:00 | 2013-12-25 17:00 | 2013-11-26 08:00 | 2013-12-25 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 |  | PT_Normal |  |  |  |  | an4VcviXTxOEmjBcisxUxQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38820 | N | N | 25 | FIREFIGHTING LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 73 | LABOR - CIVIL
%R | 501186 | 6359 | 124605 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1FFGL5205 | Construction of valve chambers & Thrust Blocks | 8165 | 160 | 0 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-01 08:00 | 2014-01-29 17:00 |  | 2013-12-08 08:00 | 2014-01-06 17:00 | 2013-12-08 08:00 | 2014-01-06 17:00 | 2013-12-08 08:00 | 2014-01-06 17:00 | 2014-01-01 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | cFh+c6dOTZeMs8oS5R8DUQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38820 | N | N | 25 | FIREFIGHTING LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 84 | STEEL FIXERS SK
%R | 501187 | 6359 | 124605 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1FFGL5210 | Connection with existing Firewater System | 8165 | 160 | 104 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-07 08:00 | 2014-02-04 17:00 |  | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2014-01-07 08:00 | 2014-02-04 17:00 |  | PT_Normal |  |  |  |  | /u1Bn2EJTl6czH61ykv5xA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38820 | N | N | 25 | FIREFIGHTING LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 84 | STEEL FIXERS SK
%R | 501188 | 6359 | 124606 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1DRGL5115 | Excavation for Drainage line | 8177 | 0 | 0 | 200 | 0 | 172 | 172 | 200 | 100 | 0 | 100 |  |  |  | 2013-08-28 08:00 | 2013-09-25 17:00 |  | 2013-08-28 08:00 | 2013-09-25 17:00 | 2013-08-28 08:00 | 2013-09-25 17:00 | 2013-08-28 08:00 | 2013-09-25 17:00 | 2013-08-28 08:00 | 2013-09-25 17:00 |  | PT_Normal |  |  |  |  | MhnHFgSSQcSOhRNsye5nTA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38790 | N | N | 10 | DRAINAGE LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 172 | LABOR - CIVIL
%R | 501189 | 6359 | 124606 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1DRGL5120 | Laying of Drainage line | 8178 | 0 | 0 | 200 | 0 | 82.8 | 82.8 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-04 08:00 | 2013-10-02 17:00 |  | 2013-09-04 08:00 | 2013-10-02 17:00 | 2013-09-04 08:00 | 2013-10-02 17:00 | 2013-09-04 08:00 | 2013-10-02 17:00 | 2013-09-04 08:00 | 2013-10-02 17:00 |  | PT_Normal |  |  |  |  | GAMQZtBvTcOUovEsFar8qg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38790 | N | N | 10 | DRAINAGE LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 82.8 | LABOR- SUBCONTRACTOR
%R | 501190 | 6359 | 124606 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1DRGL5125 | Testing of Drainage line | 8178 | 0 | 0 | 200 | 0 | 50.4 | 50.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-12 08:00 | 2013-10-10 17:00 |  | 2013-09-12 08:00 | 2013-10-10 17:00 | 2013-09-12 08:00 | 2013-10-10 17:00 | 2013-09-12 08:00 | 2013-10-10 17:00 | 2013-09-12 08:00 | 2013-10-10 17:00 |  | PT_Normal |  |  |  |  | GY3AKzssRj2wA2PN0O2wEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38790 | N | N | 10 | DRAINAGE LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 501191 | 6359 | 124606 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1DRGL5130 | Backfilling Drainage line | 8177 | 0 | 0 | 120 | 0 | 195 | 195 | 120 | 165 | 0 | 165 |  |  |  | 2013-09-30 08:00 | 2013-10-16 17:00 |  | 2013-09-30 08:00 | 2013-10-16 17:00 | 2013-09-30 08:00 | 2013-10-16 17:00 | 2013-09-30 08:00 | 2013-10-16 17:00 | 2013-09-30 08:00 | 2013-10-16 17:00 |  | PT_Normal |  |  |  |  | 3ZHMRnJvQJ6ZjujIqMtl1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38790 | N | N | 10 | DRAINAGE LINES |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 195 | LABOR - CIVIL
%R | 501192 | 6359 | 124607 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1RWGL6000 | Excavation & Earth Filling | 8177 | 24 | 0 | 80 | 0 | 452 | 452 | 80 | 200 | 0 | 200 |  |  |  | 2014-02-05 08:00 | 2014-02-17 17:00 |  | 2014-02-02 08:00 | 2014-02-13 17:00 | 2014-02-02 08:00 | 2014-02-13 17:00 | 2014-02-02 08:00 | 2014-02-13 17:00 | 2014-02-05 08:00 | 2014-02-17 17:00 |  | PT_Normal |  |  |  |  | MIhKUsZBQfqVITQ9AXSa1Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38880 | N | N | 55 | ROAD WORKS |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 452 | LABOR - CIVIL
%R | 501193 | 6359 | 124607 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1RWGL6005 | Laying of Sub Grade | 8178 | 24 | 0 | 200 | 0 | 18 | 18 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-18 17:00 |  | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | DbBiKWHUQaOL2GIvbMsy1w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38880 | N | N | 55 | ROAD WORKS |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 9 | LABOR- SUBCONTRACTOR
%R | 501194 | 6359 | 124607 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1RWGL6010 | Laying of Precast Kerbs | 8178 | 24 | 0 | 200 | 0 | 18 | 18 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-30 17:00 |  | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | +C+UldCHR6KOIVFHt+mo3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38880 | N | N | 55 | ROAD WORKS |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 9 | LABOR- SUBCONTRACTOR
%R | 501195 | 6359 | 124607 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1RWGL6015 | Laying of Granular Sub Base Coarse | 8173 | 24 | 0 | 160 | 0 | 1250 | 1250 | 160 | 600 | 0 | 600 |  |  |  | 2014-03-13 08:00 | 2014-04-05 17:00 |  | 2014-03-10 08:00 | 2014-04-01 17:00 | 2014-03-10 08:00 | 2014-04-01 17:00 | 2014-03-10 08:00 | 2014-04-01 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 |  | PT_Normal |  |  |  |  | 8coRRbEdTOe9NgxjIh1yfA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38880 | N | N | 55 | ROAD WORKS |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1250 | KERBSTONE MASON SK
%R | 501196 | 6359 | 124607 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1RWGL6020 | Laying of Road Base Asphalt Concrete | 8178 | 168 | 0 | 40 | 0 | 168 | 168 | 40 | 150 | 0 | 150 |  |  |  | 2014-04-27 08:00 | 2014-05-01 17:00 |  | 2014-04-02 08:00 | 2014-04-07 17:00 | 2014-04-02 08:00 | 2014-04-07 17:00 | 2014-04-02 08:00 | 2014-04-07 17:00 | 2014-04-27 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | 7a2tM2xMR5idjDC2hVPHYw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38880 | N | N | 55 | ROAD WORKS |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 168 | LABOR- SUBCONTRACTOR
%R | 501197 | 6359 | 124607 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1RWGL6025 | Laying of Asphalt Wearing Coarse | 8178 | 264 | 0 | 40 | 0 | 168 | 168 | 40 | 150 | 0 | 150 |  |  |  | 2014-05-17 08:00 | 2014-05-21 17:00 |  | 2014-04-08 08:00 | 2014-04-13 17:00 | 2014-04-08 08:00 | 2014-04-13 17:00 | 2014-04-08 08:00 | 2014-04-13 17:00 | 2014-05-17 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | 28XIFD8RQhCKZhSpeoiFMw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38880 | N | N | 55 | ROAD WORKS |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 168 | LABOR- SUBCONTRACTOR
%R | 501198 | 6359 | 124607 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1RWGL6030 | Traffic Signage & Road Marking | 8178 | 288 | 120 | 40 | 0 | 472 | 472 | 40 | 0 | 0 | 0 |  |  |  | 2014-05-26 08:00 | 2014-05-31 17:00 |  | 2014-04-14 08:00 | 2014-04-19 17:00 | 2014-04-14 08:00 | 2014-04-19 17:00 | 2014-04-14 08:00 | 2014-04-19 17:00 | 2014-05-26 08:00 | 2014-05-31 17:00 |  | PT_Normal |  |  |  |  | b/Cyxs/CSh6WLTLhDSL1kA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38880 | N | N | 55 | ROAD WORKS |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 472 | LABOR- SUBCONTRACTOR
%R | 501199 | 6359 | 124608 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1BWGL5315 | Construction of Boundary Wall (Ht-3m) | 8165 | 232 | 0 | 200 | 0 | 126 | 126 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-01 08:00 | 2014-03-02 17:00 |  | 2013-12-29 08:00 | 2014-01-26 17:00 | 2013-12-29 08:00 | 2014-01-26 17:00 | 2013-12-29 08:00 | 2014-01-26 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 |  | PT_Normal |  |  |  |  | A4xbXC0pS32twEt11JLJBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:45 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38870 | N | N | 50 | BOUNDARY WALL |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 126 | STEEL FIXERS SK
%R | 501200 | 6359 | 124608 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 8178 | 232 | 0 | 200 | 0 | 28 | 28 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-18 17:00 |  | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | /7p7J/jpRfuqgK5yPe/WQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:45 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38870 | N | N | 50 | BOUNDARY WALL |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 28 | LABOR- SUBCONTRACTOR
%R | 501201 | 6359 | 124608 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 8165 | 232 | 0 | 200 | 0 | 70 | 70 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | 4H7J98eTT6e8EzQzDG1Jog |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:45 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38870 | N | N | 50 | BOUNDARY WALL |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 35 | STEEL FIXERS SK
%R | 501202 | 6359 | 124608 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ1BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 8165 | 456 | 136 | 200 | 0 | 28 | 28 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-03 08:00 | 2014-05-31 17:00 |  | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 |  | PT_Normal |  |  |  |  | EQV5QzYHQ/2YgG2YejrINA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:45 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38870 | N | N | 50 | BOUNDARY WALL |  | 124595 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 14 | STEEL FIXERS SK
%R | 501203 | 6359 | 124611 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2ASBIWGL7400 | Excavation | 8177 | 224 | 0 | 120 | 0 | 295 | 295 | 120 | 150.9999 | 0 | 150.9999 |  |  |  | 2013-12-15 08:00 | 2014-01-01 17:00 |  | 2013-11-12 08:00 | 2013-11-28 17:00 | 2013-11-12 08:00 | 2013-11-28 17:00 | 2013-11-12 08:00 | 2013-11-28 17:00 | 2013-12-15 08:00 | 2014-01-01 17:00 |  | PT_Normal |  |  |  |  | dfMNim42QXejZ/FPfvkFxA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39090 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124610 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 295 | LABOR - CIVIL
%R | 501204 | 6359 | 124611 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2ASBIWGL7405 | Blinding & base waterproofing | 8163 | 224 | 0 | 80 | 0 | 200 | 200 | 80 | 0 | 0 | 0 |  |  |  | 2014-01-02 08:00 | 2014-01-13 17:00 |  | 2013-11-30 08:00 | 2013-12-10 17:00 | 2013-11-30 08:00 | 2013-12-10 17:00 | 2013-11-30 08:00 | 2013-12-10 17:00 | 2014-01-02 08:00 | 2014-01-13 17:00 |  | PT_Normal |  |  |  |  | nNf8e+2HSguyoDvBXdDlAA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39090 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124610 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 200 | BLINDING MASON SK
%R | 501205 | 6359 | 124611 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2ASBIWGL7410 | Construction of Raft slab | 8165 | 224 | 0 | 80 | 0 | 630 | 630 | 80 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-01-25 17:00 |  | 2013-12-11 08:00 | 2013-12-23 17:00 | 2013-12-11 08:00 | 2013-12-23 17:00 | 2013-12-11 08:00 | 2013-12-23 17:00 | 2014-01-14 08:00 | 2014-01-25 17:00 |  | PT_Normal |  |  |  |  | OmUhHYB4RICUE2M/+BHYHQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39090 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124610 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 630 | STEEL FIXERS SK
%R | 501206 | 6359 | 124611 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2ASBIWGL7415 | Construction of RCC Wall | 8165 | 224 | 0 | 200 | 0 | 1708 | 1708 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-26 08:00 | 2014-02-24 17:00 |  | 2013-12-24 08:00 | 2014-01-21 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 |  | PT_Normal |  |  |  |  | AaNdkxEIRIO8CWamR3tFIQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39090 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124610 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1708 | STEEL FIXERS SK
%R | 501207 | 6359 | 124611 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2ASBIWGL7420 | Construction of Roof Slab | 8165 | 224 | 0 | 160 | 0 | 490 | 490 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-25 08:00 | 2014-03-19 17:00 |  | 2014-01-22 08:00 | 2014-02-15 17:00 | 2014-01-22 08:00 | 2014-02-15 17:00 | 2014-01-22 08:00 | 2014-02-15 17:00 | 2014-02-25 08:00 | 2014-03-19 17:00 |  | PT_Normal |  |  |  |  | 7CdQ3RnPTimllf2C+9qhwQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39090 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124610 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 490 | STEEL FIXERS SK
%R | 501208 | 6359 | 124611 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2ASBIWGL7425 | Waterproofing & Backfilling | 8177 | 272 | 0 | 120 | 0 | 192 | 192 | 120 | 84 | 0 | 84 |  |  |  | 2014-03-27 08:00 | 2014-04-13 17:00 |  | 2014-02-16 08:00 | 2014-03-04 17:00 | 2014-02-16 08:00 | 2014-03-04 17:00 | 2014-02-16 08:00 | 2014-03-04 17:00 | 2014-03-27 08:00 | 2014-04-13 17:00 |  | PT_Normal |  |  |  |  | Reb25fhlRceteCkW5ztR6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39090 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124610 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 192 | LABOR - CIVIL
%R | 501209 | 6359 | 124611 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2ASBIWGL7430 | Floor screed | 8164 | 224 | 0 | 40 | 0 | 66 | 66 | 40 | 0 | 0 | 0 |  |  |  | 2014-04-14 08:00 | 2014-04-19 17:00 |  | 2014-03-12 08:00 | 2014-03-17 17:00 | 2014-03-12 08:00 | 2014-03-17 17:00 | 2014-03-12 08:00 | 2014-03-17 17:00 | 2014-04-14 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | eZuNu50URp2FB+isH/prww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39090 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124610 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 66 | SCREED MASON SK
%R | 501210 | 6359 | 124611 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2ASBIWGL7455 | Internal epoxy coating & Painting | 8178 | 224 | 0 | 40 | 0 | 44 | 44 | 40 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-02 17:00 |  | 2014-04-26 08:00 | 2014-04-30 17:00 | 2014-04-26 08:00 | 2014-04-30 17:00 | 2014-04-26 08:00 | 2014-04-30 17:00 | 2014-05-28 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | V7xgi3i4Qwe4MaQSTfcB0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39090 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124610 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 44 | LABOR- SUBCONTRACTOR
%R | 501211 | 6359 | 124611 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2ASBIWGL7460 | Installation of Steel Ladder | 8178 | 224 | 0 | 40 | 0 | 14 | 14 | 40 | 0 | 0 | 0 |  |  |  | 2014-06-03 08:00 | 2014-06-08 17:00 |  | 2014-05-01 08:00 | 2014-05-06 17:00 | 2014-05-01 08:00 | 2014-05-06 17:00 | 2014-05-01 08:00 | 2014-05-06 17:00 | 2014-06-03 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | 6X9U88TGQ2WeRYC38xY3Yw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39090 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124610 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 14 | LABOR- SUBCONTRACTOR
%R | 501212 | 6359 | 124611 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2ASBIWGL7465 | Installation of G.I Handrails | 8178 | 224 | 224 | 40 | 0 | 164 | 164 | 40 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-06-14 17:00 |  | 2014-05-07 08:00 | 2014-05-12 17:00 | 2014-05-07 08:00 | 2014-05-12 17:00 | 2014-05-07 08:00 | 2014-05-12 17:00 | 2014-06-09 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | WorSYGG2TG+fh/gV4Oabkg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39090 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124610 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 164 | LABOR- SUBCONTRACTOR
%R | 501213 | 6359 | 124611 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2ASBIWGL7440 | Plumbing , Drainage & Firefighting works | 8178 | 224 | 0 | 200 | 0 | 50.4 | 50.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | B7gDtFHWQ/eYUi9nc3COSw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39090 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124610 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 501214 | 6359 | 124611 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2ASBIWGL7445 | AC Works | 8178 | 224 | 0 | 200 | 0 | 159.2 | 159.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | j15SsVizTTuOm8YqRbmC1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39090 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124610 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 159.2 | LABOR- SUBCONTRACTOR
%R | 501215 | 6359 | 124611 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2ASBIWGL7450 | Electrical Works | 8178 | 224 | 0 | 200 | 0 | 325.2 | 325.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-27 17:00 |  | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | /exBS/uoSg2ljUg1kliUnQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39090 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124610 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 325.2 | LABOR- SUBCONTRACTOR
%R | 501216 | 6359 | 124611 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2ASBIWGL7950 | Laying of Interlock | 8174 | 456 | 0 | 80 | 0 | 58 | 58 | 80 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-05-21 17:00 |  | 2014-03-05 08:00 | 2014-03-16 17:00 | 2014-03-05 08:00 | 2014-03-16 17:00 | 2014-03-05 08:00 | 2014-03-16 17:00 | 2014-05-11 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | aCqZLaMCRditrCz+/agS0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39090 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124610 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 58 | INTERLOCK MASON SK
%R | 501217 | 6359 | 124611 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2ASBIWGL7435 | Installation of Boundary Fences | 8165 | 456 | 232 | 120 | 0 | 42 | 42 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-22 08:00 | 2014-06-08 17:00 |  | 2014-03-17 08:00 | 2014-04-02 17:00 | 2014-03-17 08:00 | 2014-04-02 17:00 | 2014-03-17 08:00 | 2014-04-02 17:00 | 2014-05-22 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | pCz/qLi2QIaECyLSHDi0Yg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39090 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124610 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 42 | STEEL FIXERS SK
%R | 501218 | 6359 | 124612 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2ASBGZGL7900 | Construction of Concrete structure | 8165 | 184 | 0 | 160 | 0 | 124 | 124 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-25 08:00 | 2014-04-16 17:00 |  | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-03-25 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | 2bybN7eNTymit3cX+JyZMQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39120 | N | N | 25 | GAZEBO |  | 124610 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 124 | STEEL FIXERS SK
%R | 501219 | 6359 | 124612 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2ASBGZGL7905 | Installation of Wooden Works | 8178 | 184 | 0 | 200 | 0 | 300 | 300 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-05-04 17:00 |  | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-04-06 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | CqFCY9OJQmeHtJnuZ+XqUw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39120 | N | N | 25 | GAZEBO |  | 124610 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 300 | LABOR- SUBCONTRACTOR
%R | 501220 | 6359 | 124612 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2ASBGZGL7910 | Electrical Works-Gazebo | 8178 | 184 | 64 | 120 | 0 | 125.6 | 125.6 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-05 08:00 | 2014-05-21 17:00 |  | 2014-04-08 08:00 | 2014-04-24 17:00 | 2014-04-08 08:00 | 2014-04-24 17:00 | 2014-04-08 08:00 | 2014-04-24 17:00 | 2014-05-05 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | xLNkSNR6SuK9W5MzGmjdhQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39120 | N | N | 25 | GAZEBO |  | 124610 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 125.6 | LABOR- SUBCONTRACTOR
%R | 501221 | 6359 | 124612 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2ASBGZGL7915 | Park Benches Installation | 8178 | 264 | 80 | 120 | 0 | 120 | 120 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-04 17:00 |  | 2014-03-10 08:00 | 2014-03-26 17:00 | 2014-03-10 08:00 | 2014-03-26 17:00 | 2014-03-10 08:00 | 2014-03-26 17:00 | 2014-04-17 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | I+O1Aun6QfquRCGrR9Ch8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39120 | N | N | 25 | GAZEBO |  | 124610 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 120 | LABOR- SUBCONTRACTOR
%R | 501222 | 6359 | 124615 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2IRGL5265 | Excavation for irrigation line | 8177 | 208 | 0 | 200 | 0 | 93 | 93 | 200 | 51 | 0 | 51 |  |  |  | 2014-04-09 08:00 | 2014-05-07 17:00 |  | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 |  | PT_Normal |  |  |  |  | Q9EcWXmqQ3mVMI3vzLK0iQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39000 | N | N | 40 | IRRIGATION LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 93 | LABOR - CIVIL
%R | 501223 | 6359 | 124615 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2IRGL5270 | Laying of irrigationline | 8178 | 208 | 0 | 200 | 0 | 50.4 | 50.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-13 17:00 |  | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 |  | PT_Normal |  |  |  |  | 68LcszB8TsOhgRWa2oBaVw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39000 | N | N | 40 | IRRIGATION LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 501224 | 6359 | 124615 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2IRGL5275 | Testing of irrigation line | 8178 | 208 | 0 | 200 | 0 | 50.4 | 50.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-21 08:00 | 2014-05-19 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | AKWfUohWRPCvn/v2u9ih4A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39000 | N | N | 40 | IRRIGATION LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 501225 | 6359 | 124615 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2IRGL5280 | Backfilling irrigation line | 8177 | 208 | 0 | 200 | 0 | 73 | 73 | 200 | 55 | 0 | 55 |  |  |  | 2014-04-27 08:00 | 2014-05-25 17:00 |  | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 |  | PT_Normal |  |  |  |  | dRTLYpDMQRKS8IB8bgIxIA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39000 | N | N | 40 | IRRIGATION LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 73 | LABOR - CIVIL
%R | 501226 | 6359 | 124615 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2IRGL5285 | Construction of Thrust Blocks,Pull boxes | 8178 | 208 | 0 | 200 | 0 | 193.6 | 193.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-08 08:00 | 2014-06-05 17:00 |  | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-05-08 08:00 | 2014-06-05 17:00 |  | PT_Normal |  |  |  |  | D9dkV2UMTomXaYIjDjDGkw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39000 | N | N | 40 | IRRIGATION LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 193.6 | LABOR- SUBCONTRACTOR
%R | 501227 | 6359 | 124615 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2IRGL5290 | Irrigation Fittings (Nozzle,Values) | 8178 | 208 | 88 | 200 | 0 | 33.6 | 33.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | D72w/3vpT/a0ht6uvN80TA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39000 | N | N | 40 | IRRIGATION LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 33.6 | LABOR- SUBCONTRACTOR
%R | 501228 | 6359 | 124616 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2SLGL7200 | Excavation for Landscaping | 8177 | 120 | 0 | 200 | 0 | 658 | 658 | 200 | 376 | 0 | 376 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | gg0xG2JsSEefW7JWDRqLEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39060 | N | N | 70 | SOFT LANDSCAPING |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 658 | LABOR - CIVIL
%R | 501229 | 6359 | 124616 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2SLGL7205 | Sweet Soil Laying | 8178 | 120 | 0 | 200 | 0 | 140 | 140 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-25 17:00 |  | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | xqgMDhchTjysMyLECuu6cQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39060 | N | N | 70 | SOFT LANDSCAPING |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 140 | LABOR- SUBCONTRACTOR
%R | 501230 | 6359 | 124616 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2SLGL7210 | Plantation works | 8178 | 120 | 120 | 200 | 0 | 266 | 266 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-07-07 17:00 |  | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39060 | N | N | 70 | SOFT LANDSCAPING |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 266 | LABOR- SUBCONTRACTOR
%R | 501231 | 6359 | 124617 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2ELGL5215 | Excavation Cable Trenches & Duct Banks | 8177 | 0 | 0 | 200 | 0 | 2077 | 2077 | 200 | 751 | 0 | 751 |  |  |  | 2014-01-25 08:00 | 2014-02-23 17:00 |  | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | 3bHM3JKpSDypiUxprDpl+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38980 | N | N | 30 | ELECTRICAL LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 2077 | LABOR - CIVIL
%R | 501232 | 6359 | 124617 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2ELGL5220 | Laying of electrical cables | 8178 | 104 | 0 | 200 | 0 | 3141.2 | 3141.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-16 17:00 |  | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | QW2yXu+1RgC7iE6S+zV/vg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38980 | N | N | 30 | ELECTRICAL LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01; period 2: 2014-AP03 |  | 1570.6 | LABOR- SUBCONTRACTOR
%R | 501233 | 6359 | 124617 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2ELGL5225 | Backfilling Electrical trench | 8177 | 104 | 0 | 200 | 0 | 1359 | 1359 | 200 | 825 | 0 | 825 |  |  |  | 2014-02-24 08:00 | 2014-03-24 17:00 |  | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | hohMzS4UQR6zgYpDIrZCLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38980 | N | N | 30 | ELECTRICAL LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 679.5 | LABOR - CIVIL
%R | 501234 | 6359 | 124617 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2ELGL5230 | Construction of Submain Board & Feeder Pillar | 8165 | 264 | 0 | 200 | 0 | 520 | 520 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-28 17:00 |  | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | YnKoeVikT7Wt5UFb8xY2fA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38980 | N | N | 30 | ELECTRICAL LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 260 | STEEL FIXERS SK
%R | 501235 | 6359 | 124618 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2WSGL5160 | Laying of water line | 8178 | 8 | 0 | 200 | 0 | 302.4 | 302.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-09 08:00 | 2014-01-07 17:00 |  | 2013-12-08 08:00 | 2014-01-06 17:00 | 2013-12-08 08:00 | 2014-01-06 17:00 | 2013-12-08 08:00 | 2014-01-06 17:00 | 2013-12-09 08:00 | 2014-01-07 17:00 |  | PT_Normal |  |  |  |  | vvdY8O6jTs6C6LRXsuXWSA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38960 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 302.4 | LABOR- SUBCONTRACTOR
%R | 501236 | 6359 | 124618 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2WSGL5165 | Testing of potable water line | 8178 | 8 | 8 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-15 08:00 | 2014-01-13 17:00 |  | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-15 08:00 | 2014-01-13 17:00 |  | PT_Normal |  |  |  |  | fzuWFzQERHCCeVzr1/tEgg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38960 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 84 | LABOR- SUBCONTRACTOR
%R | 501237 | 6359 | 124618 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2WSGL5170 | Backfilling potable water line | 8177 | 0 | 0 | 200 | 0 | 187 | 187 | 200 | 139 | 0 | 139 |  |  |  | 2013-12-22 08:00 | 2014-01-19 17:00 |  | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 |  | PT_Normal |  |  |  |  | u3VMFdEATAGaZycq1cga1Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38960 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 187 | LABOR - CIVIL
%R | 501238 | 6359 | 124618 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2WSGL5175 | Construction of valve chambers & Thrust Blocks | 8172 | 232 | 0 | 200 | 0 | 66 | 66 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-03-01 17:00 |  | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | Azc/8sOJRkeqv8PE+7eLjg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38960 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 66 | MANHOLES SK
%R | 501239 | 6359 | 124618 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2WSGL5180 | Installation of meter ,Accessories & Connection | 8178 | 232 | 56 | 160 | 0 | 33.6 | 33.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-24 17:00 |  | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | tIt8pmT4TQKOtf8WnUHdTQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38960 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 33.6 | LABOR- SUBCONTRACTOR
%R | 501240 | 6359 | 124618 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2WSGL5155 | Excavation for water line | 8177 | 8 | 0 | 200 | 0 | 239 | 239 | 200 | 125 | 0 | 125 |  |  |  | 2013-12-03 08:00 | 2014-01-01 17:00 |  | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 |  | PT_Normal |  |  |  |  | ayOgjFzIS6ui9FEReXFXwA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38960 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 239 | LABOR - CIVIL
%R | 501241 | 6359 | 124619 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2SAGL5135 | Construction of manholes Drainage | 8172 | 472 | 200 | 200 | 0 | 36 | 36 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-03-01 17:00 |  | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | NpS4QgHIQLCbLHi71r5YnA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38950 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11; period 2: 2013-AP12 |  | 18 | MANHOLES SK
%R | 501242 | 6359 | 124619 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2SAGL5140 | Construction of soakaways | 8172 | 0 | 0 | 200 | 0 | 102 | 102 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-21 08:00 | 2013-12-21 17:00 |  | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 |  | PT_Normal |  |  |  |  | 81pXpsQCToigmPOhexfn3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38950 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11; period 2: 2013-AP12 |  | 51 | MANHOLES SK
%R | 501243 | 6359 | 124619 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2SAGL5145 | Construction of Road gullies | 8172 | 0 | 0 | 200 | 0 | 102 | 102 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-22 08:00 | 2014-01-19 17:00 |  | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 |  | PT_Normal |  |  |  |  | PQe89hojT6C5sOT3El0/3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38950 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 102 | MANHOLES SK
%R | 501244 | 6359 | 124619 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2SAGL5150 | Connection with existing sewer manhole | 8172 | 272 | 272 | 160 | 0 | 36 | 36 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-24 17:00 |  | 2014-01-20 08:00 | 2014-02-12 17:00 | 2014-01-20 08:00 | 2014-02-12 17:00 | 2014-01-20 08:00 | 2014-02-12 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | zHVGqoFfTx+zt/WELTsA2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38950 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 36 | MANHOLES SK
%R | 501245 | 6359 | 124620 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2TCGL5295 | Excavation Telecommunication trenches | 8177 | 0 | 0 | 160 | 0 | 178 | 178 | 160 | 100 | 0 | 100 |  |  |  | 2014-02-18 08:00 | 2014-03-12 17:00 |  | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 |  | PT_Normal |  |  |  |  | GMtwk/cvR5eLL6/0dryOSQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39010 | N | N | 45 | TELECOMMUNICATION LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 178 | LABOR - CIVIL
%R | 501246 | 6359 | 124620 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2TCGL5300 | Laying of cables | 8178 | 0 | 0 | 160 | 0 | 369.2 | 369.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-18 17:00 |  | 2014-02-24 08:00 | 2014-03-18 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | eKmaX9ihTNmsmGv0dLTrMg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39010 | N | N | 45 | TELECOMMUNICATION LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 369.2 | LABOR- SUBCONTRACTOR
%R | 501247 | 6359 | 124620 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2TCGL5305 | Backfilling telecommunication trench | 8177 | 0 | 0 | 160 | 0 | 140 | 140 | 160 | 110 | 0 | 110 |  |  |  | 2014-03-02 08:00 | 2014-03-24 17:00 |  | 2014-03-02 08:00 | 2014-03-24 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | fhrWgEMSQmG/yNkEdmxO3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39010 | N | N | 45 | TELECOMMUNICATION LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 140 | LABOR - CIVIL
%R | 501248 | 6359 | 124620 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2TCGL5310 | Connection & Installation | 8178 | 360 | 136 | 160 | 0 | 180.8 | 180.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-05 08:00 | 2014-05-27 17:00 |  | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-05-05 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | 1k3Xtd1sR0S4RYz2jzNzsA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39010 | N | N | 45 | TELECOMMUNICATION LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 180.8 | LABOR- SUBCONTRACTOR
%R | 501249 | 6359 | 124621 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2STGL5235 | Excavation for Street lighting | 8177 | 0 | 0 | 200 | 0 | 184 | 184 | 200 | 100 | 0 | 100 |  |  |  | 2014-01-25 08:00 | 2014-02-23 17:00 |  | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | WxJ8UKm5Q767VvFEY4RbfA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38990 | N | N | 35 | STREET LIGHTING |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 184 | LABOR - CIVIL
%R | 501250 | 6359 | 124621 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2STGL5240 | Construction of Duct Banks | 8178 | 0 | 0 | 200 | 0 | 340.8 | 340.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-03-01 17:00 |  | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | TXXkBmKpQWiQZfexboAL2A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38990 | N | N | 35 | STREET LIGHTING |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01; period 2: 2014-AP03 |  | 170.4 | LABOR- SUBCONTRACTOR
%R | 501251 | 6359 | 124621 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2STGL5245 | Construction of Foundation | 8172 | 0 | 0 | 200 | 0 | 506 | 506 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-03-01 17:00 |  | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | q6cCLjrHSumonlMPmJZ5nw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38990 | N | N | 35 | STREET LIGHTING |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01; period 2: 2014-AP03 |  | 253 | MANHOLES SK
%R | 501252 | 6359 | 124621 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2STGL5250 | Backfilling Street Lighting | 8177 | 0 | 0 | 200 | 0 | 146 | 146 | 200 | 110 | 0 | 110 |  |  |  | 2014-02-05 08:00 | 2014-03-06 17:00 |  | 2014-02-05 08:00 | 2014-03-06 17:00 | 2014-02-05 08:00 | 2014-03-06 17:00 | 2014-02-05 08:00 | 2014-03-06 17:00 | 2014-02-05 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | mzakfoPsR12GAzwoFNdfIA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38990 | N | N | 35 | STREET LIGHTING |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 73 | LABOR - CIVIL
%R | 501253 | 6359 | 124621 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2STGL5255 | Installation of light Post | 8178 | 424 | 160 | 200 | 0 | 170.4 | 170.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-21 08:00 | 2014-05-19 17:00 |  | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | 2O+e3/43T1qZTdN7b16Beg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38990 | N | N | 35 | STREET LIGHTING |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 85.2 | LABOR- SUBCONTRACTOR
%R | 501254 | 6359 | 124621 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2STGL5260 | Electrical Works | 8178 | 264 | 40 | 200 | 0 | 142 | 142 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-27 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | xA0gS9Y3SGeL8mgDsssyTg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38990 | N | N | 35 | STREET LIGHTING |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 142 | LABOR- SUBCONTRACTOR
%R | 501255 | 6359 | 124622 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2RWGL6015 | Laying of Granular Sub Base Coarse | 8173 | 0 | 0 | 160 | 0 | 1250 | 1250 | 160 | 600 | 0 | 600 |  |  |  | 2014-04-29 08:00 | 2014-05-21 17:00 |  | 2014-04-29 08:00 | 2014-05-21 17:00 | 2014-04-29 08:00 | 2014-05-21 17:00 | 2014-04-29 08:00 | 2014-05-21 17:00 | 2014-04-29 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | SdWXJjgMSOKXU32d5+WZDQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39030 | N | N | 55 | ROAD WORKS |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1250 | KERBSTONE MASON SK
%R | 501256 | 6359 | 124622 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2RWGL6020 | Laying of Road Base Asphalt Concrete | 8178 | 0 | 0 | 40 | 0 | 168 | 168 | 40 | 150 | 0 | 150 |  |  |  | 2014-05-22 08:00 | 2014-05-27 17:00 |  | 2014-05-22 08:00 | 2014-05-27 17:00 | 2014-05-22 08:00 | 2014-05-27 17:00 | 2014-05-22 08:00 | 2014-05-27 17:00 | 2014-05-22 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | Zww7mT4ISL2Ri5eqyOJOIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39030 | N | N | 55 | ROAD WORKS |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 168 | LABOR- SUBCONTRACTOR
%R | 501257 | 6359 | 124622 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2RWGL6025 | Laying of Asphalt Wearing Coarse | 8178 | 0 | 0 | 40 | 0 | 168 | 168 | 40 | 150 | 0 | 150 |  |  |  | 2014-05-28 08:00 | 2014-06-02 17:00 |  | 2014-05-28 08:00 | 2014-06-02 17:00 | 2014-05-28 08:00 | 2014-06-02 17:00 | 2014-05-28 08:00 | 2014-06-02 17:00 | 2014-05-28 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | NRHbdcXgQTGGXBZHiaXH+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39030 | N | N | 55 | ROAD WORKS |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 168 | LABOR- SUBCONTRACTOR
%R | 501258 | 6359 | 124622 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2RWGL6030 | Traffic Signage & Road Marking | 8178 | 144 | 120 | 40 | 0 | 472 | 472 | 40 | 0 | 0 | 0 |  |  |  | 2014-06-24 08:00 | 2014-06-29 17:00 |  | 2014-06-03 08:00 | 2014-06-08 17:00 | 2014-06-03 08:00 | 2014-06-08 17:00 | 2014-06-03 08:00 | 2014-06-08 17:00 | 2014-06-24 08:00 | 2014-06-29 17:00 |  | PT_Normal |  |  |  |  | 47qy7DfdTGyC4nrhaGaFvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39030 | N | N | 55 | ROAD WORKS |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 472 | LABOR- SUBCONTRACTOR
%R | 501259 | 6359 | 124622 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2RWGL6000 | Excavation & Earth Filling | 8177 | 0 | 0 | 80 | 0 | 452 | 452 | 80 | 200 | 0 | 200 |  |  |  | 2014-03-25 08:00 | 2014-04-05 17:00 |  | 2014-03-25 08:00 | 2014-04-05 17:00 | 2014-03-25 08:00 | 2014-04-05 17:00 | 2014-03-25 08:00 | 2014-04-05 17:00 | 2014-03-25 08:00 | 2014-04-05 17:00 |  | PT_Normal |  |  |  |  | iKpi/3xIRFK5Hw69YC20Zg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39030 | N | N | 55 | ROAD WORKS |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 452 | LABOR - CIVIL
%R | 501260 | 6359 | 124622 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2RWGL6005 | Laying of Sub Grade | 8178 | 0 | 0 | 200 | 0 | 18 | 18 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-05-04 17:00 |  | 2014-04-06 08:00 | 2014-05-04 17:00 | 2014-04-06 08:00 | 2014-05-04 17:00 | 2014-04-06 08:00 | 2014-05-04 17:00 | 2014-04-06 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | Hl9baNeZTLGQx8MSqNQ7fg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39030 | N | N | 55 | ROAD WORKS |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 18 | LABOR- SUBCONTRACTOR
%R | 501261 | 6359 | 124622 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2RWGL6010 | Laying of Precast Kerbs | 8178 | 0 | 0 | 200 | 0 | 18 | 18 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | +031N2jMT0OO9yHudAsWVA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39030 | N | N | 55 | ROAD WORKS |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 18 | LABOR- SUBCONTRACTOR
%R | 501262 | 6359 | 124623 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2FFGL5185 | Excavation for firefighting line | 8177 | 0 | 0 | 200 | 0 | 87 | 87 | 200 | 51 | 0 | 51 |  |  |  | 2013-12-28 08:00 | 2014-01-25 17:00 |  | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 |  | PT_Normal |  |  |  |  | BFyq7e2MSI+H7GmDZNtIYw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38970 | N | N | 25 | FIREFIGHTING LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 87 | LABOR - CIVIL
%R | 501263 | 6359 | 124623 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2FFGL5190 | Laying of firefighting line | 8178 | 0 | 0 | 200 | 0 | 82.8 | 82.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-05 08:00 | 2014-02-02 17:00 |  | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | uSOM7RpNTNGXkq/DCSPNRQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38970 | N | N | 25 | FIREFIGHTING LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 82.8 | LABOR- SUBCONTRACTOR
%R | 501264 | 6359 | 124623 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2FFGL5195 | Testing of firefighting line | 8178 | 0 | 0 | 200 | 0 | 44.4 | 44.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-11 08:00 | 2014-02-08 17:00 |  | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 |  | PT_Normal |  |  |  |  | xjfV7VTGSQKrhGt6FKFf+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38970 | N | N | 25 | FIREFIGHTING LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 44.4 | LABOR- SUBCONTRACTOR
%R | 501265 | 6359 | 124623 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2FFGL5200 | Backfilling firefighting line | 8177 | 0 | 0 | 200 | 0 | 73 | 73 | 200 | 55 | 0 | 55 |  |  |  | 2014-01-16 08:00 | 2014-02-15 17:00 |  | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 |  | PT_Normal |  |  |  |  | /9OjZ4dATLiKXp65/s//lg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38970 | N | N | 25 | FIREFIGHTING LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 73 | LABOR - CIVIL
%R | 501266 | 6359 | 124623 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2FFGL5205 | Construction of valve chambers & Thrust Blocks | 8165 | 176 | 0 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-18 17:00 |  | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | HS0OSkTHQ6+i4Lekm2e1Ww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38970 | N | N | 25 | FIREFIGHTING LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 84 | STEEL FIXERS SK
%R | 501267 | 6359 | 124623 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2FFGL5210 | Connection with existing Firewater System | 8165 | 176 | 128 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-24 17:00 |  | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | kmSyijiBSS6CsgxhfdBPeQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38970 | N | N | 25 | FIREFIGHTING LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 84 | STEEL FIXERS SK
%R | 501268 | 6359 | 124624 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2HDGL7020 | Precast Concrete Kerbs works | 8173 | 120 | 0 | 160 | 0 | 186 | 186 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-04 17:00 |  | 2014-03-25 08:00 | 2014-04-16 17:00 | 2014-03-25 08:00 | 2014-04-16 17:00 | 2014-03-25 08:00 | 2014-04-16 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | iZ4SOa3RQBK0ckRAly3ymQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39050 | N | N | 65 | HARD LANDSCAPING |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 186 | KERBSTONE MASON SK
%R | 501269 | 6359 | 124624 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2HDGL7025 | Interlocking for Walkways | 8174 | 120 | 0 | 200 | 0 | 432 | 432 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-05-21 17:00 |  | 2014-04-06 08:00 | 2014-05-04 17:00 | 2014-04-06 08:00 | 2014-05-04 17:00 | 2014-04-06 08:00 | 2014-05-04 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | ymz2MzWiSdyyxQV3I8HWCA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39050 | N | N | 65 | HARD LANDSCAPING |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 432 | INTERLOCK MASON SK
%R | 501270 | 6359 | 124624 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2HDGL7030 | Construction of Retaining wall | 8165 | 120 | 0 | 200 | 0 | 376 | 376 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-05 08:00 | 2014-06-02 17:00 |  | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-05-05 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | lZcrd9FCS+Kkg2I3XCNZGw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39050 | N | N | 65 | HARD LANDSCAPING |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 376 | STEEL FIXERS SK
%R | 501271 | 6359 | 124624 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2HDGL7035 | Construction of Wash Stone Boulders | 8170 | 120 | 0 | 200 | 0 | 66 | 66 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-05 08:00 | 2014-06-02 17:00 |  | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-05-05 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | 5BpausUbSh6GvlLq9Faf4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39050 | N | N | 65 | HARD LANDSCAPING |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 66 | TILE MASON SK
%R | 501272 | 6359 | 124624 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2HDGL7040 | Construction of Speed Humps | 8167 | 0 | 0 | 80 | 0 | 14 | 14 | 80 | 0 | 0 | 0 |  |  |  | 2014-06-03 08:00 | 2014-06-14 17:00 |  | 2014-06-03 08:00 | 2014-06-14 17:00 | 2014-06-03 08:00 | 2014-06-14 17:00 | 2014-06-03 08:00 | 2014-06-14 17:00 | 2014-06-03 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | hF9TRfIpTqquGX16Ln0TFg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39050 | N | N | 65 | HARD LANDSCAPING |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 14 | CONCRETE MASON SK
%R | 501273 | 6359 | 124625 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2DRGL5115 | Excavation for Drainage line | 8177 | 0 | 0 | 200 | 0 | 172 | 172 | 200 | 100 | 0 | 100 |  |  |  | 2013-10-20 08:00 | 2013-11-17 17:00 |  | 2013-10-20 08:00 | 2013-11-17 17:00 | 2013-10-20 08:00 | 2013-11-17 17:00 | 2013-10-20 08:00 | 2013-11-17 17:00 | 2013-10-20 08:00 | 2013-11-17 17:00 |  | PT_Normal |  |  |  |  | 8XvP0MzXTpuF6VNK9b+lDw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38940 | N | N | 10 | DRAINAGE LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 172 | LABOR - CIVIL
%R | 501274 | 6359 | 124625 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2DRGL5120 | Laying of Drainage line | 8178 | 0 | 0 | 200 | 0 | 82.8 | 82.8 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-27 08:00 | 2013-11-24 17:00 |  | 2013-10-27 08:00 | 2013-11-24 17:00 | 2013-10-27 08:00 | 2013-11-24 17:00 | 2013-10-27 08:00 | 2013-11-24 17:00 | 2013-10-27 08:00 | 2013-11-24 17:00 |  | PT_Normal |  |  |  |  | NAKkKBDxRoypLaQ3wiYZ4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38940 | N | N | 10 | DRAINAGE LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 82.8 | LABOR- SUBCONTRACTOR
%R | 501275 | 6359 | 124625 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2DRGL5125 | Testing of Drainage line | 8178 | 0 | 0 | 200 | 0 | 50.4 | 50.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-04 08:00 | 2013-12-02 17:00 |  | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 |  | PT_Normal |  |  |  |  | 9z+qEQ7sQIyD1TShE5JJqA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38940 | N | N | 10 | DRAINAGE LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 501276 | 6359 | 124625 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2DRGL5130 | Backfilling Drainage line | 8177 | 0 | 0 | 120 | 0 | 195 | 195 | 120 | 165 | 0 | 165 |  |  |  | 2013-11-21 08:00 | 2013-12-08 17:00 |  | 2013-11-21 08:00 | 2013-12-08 17:00 | 2013-11-21 08:00 | 2013-12-08 17:00 | 2013-11-21 08:00 | 2013-12-08 17:00 | 2013-11-21 08:00 | 2013-12-08 17:00 |  | PT_Normal |  |  |  |  | jW02cG1cRlOadkro5tSfaw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38940 | N | N | 10 | DRAINAGE LINES |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 195 | LABOR - CIVIL
%R | 501277 | 6359 | 124626 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2PSGL7010 | Column, Frame& Fabrics Erection | 8178 | 24 | 0 | 200 | 0 | 122 | 122 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-01 08:00 | 2014-06-29 17:00 |  | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 |  | PT_Normal |  |  |  |  | qPcbCxW6SoicIQMf2gTxeg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39040 | N | N | 60 | PARKING SHED |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 122 | LABOR- SUBCONTRACTOR
%R | 501278 | 6359 | 124626 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2PSGL7015 | Electrical Works-Parking Shed | 8178 | 24 | 24 | 200 | 0 | 275.2 | 275.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-07 08:00 | 2014-07-05 17:00 |  | 2014-06-03 08:00 | 2014-07-01 17:00 | 2014-06-03 08:00 | 2014-07-01 17:00 | 2014-06-03 08:00 | 2014-07-01 17:00 | 2014-06-07 08:00 | 2014-07-05 17:00 |  | PT_Normal |  |  |  |  | EtC/s+HKQoesOQ5zFQhWZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39040 | N | N | 60 | PARKING SHED |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 275.2 | LABOR- SUBCONTRACTOR
%R | 501279 | 6359 | 124626 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2PSGL7000 | Excavation | 8177 | 64 | 40 | 120 | 0 | 37 | 37 | 120 | 31 | 0 | 31 |  |  |  | 2014-05-14 08:00 | 2014-05-31 17:00 |  | 2014-05-05 08:00 | 2014-05-21 17:00 | 2014-05-05 08:00 | 2014-05-21 17:00 | 2014-05-05 08:00 | 2014-05-21 17:00 | 2014-05-14 08:00 | 2014-05-31 17:00 |  | PT_Normal |  |  |  |  | sch37sMySX+srf+MY0x8hw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39040 | N | N | 60 | PARKING SHED |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 37 | LABOR - CIVIL
%R | 501280 | 6359 | 124626 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2PSGL7005 | Foundation casting | 8165 | 24 | 0 | 120 | 0 | 938 | 938 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-20 08:00 | 2014-06-05 17:00 |  | 2014-05-17 08:00 | 2014-06-02 17:00 | 2014-05-17 08:00 | 2014-06-02 17:00 | 2014-05-17 08:00 | 2014-06-02 17:00 | 2014-05-20 08:00 | 2014-06-05 17:00 |  | PT_Normal |  |  |  |  | V9K1g6JQR0KEPStzQfpNOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39040 | N | N | 60 | PARKING SHED |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 938 | STEEL FIXERS SK
%R | 501281 | 6359 | 124627 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2BWGL5315 | Construction of Boundary Wall (Ht-3m) | 8165 | 216 | 0 | 200 | 0 | 126 | 126 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-19 17:00 |  | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | OzRcb8nWQyyJu4xrLizU4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39020 | N | N | 50 | BOUNDARY WALL |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 63 | STEEL FIXERS SK
%R | 501282 | 6359 | 124627 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 8178 | 216 | 0 | 200 | 0 | 28 | 28 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-05-04 17:00 |  | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-04-06 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | o1K/VXerS5OONwRWdaI0LQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39020 | N | N | 50 | BOUNDARY WALL |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 28 | LABOR- SUBCONTRACTOR
%R | 501283 | 6359 | 124627 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 8165 | 216 | 0 | 200 | 0 | 70 | 70 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-05 08:00 | 2014-06-02 17:00 |  | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-05-05 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | AmEk2/E/SgqRL358lIiNPw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39020 | N | N | 50 | BOUNDARY WALL |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 70 | STEEL FIXERS SK
%R | 501284 | 6359 | 124627 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2AZ2BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 8165 | 320 | 296 | 200 | 0 | 28 | 28 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-01 08:00 | 2014-06-29 17:00 |  | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 |  | PT_Normal |  |  |  |  | hwz8WCzSTaKhvazRYJBJvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39020 | N | N | 50 | BOUNDARY WALL |  | 124614 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 28 | STEEL FIXERS SK
%R | 501285 | 6359 | 124631 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBGZGL7900 | Construction of Concrete structure | 8165 | 40 | 0 | 160 | 0 | 124 | 124 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-03 08:00 | 2014-09-25 17:00 |  | 2014-08-28 08:00 | 2014-09-20 17:00 | 2014-08-28 08:00 | 2014-09-20 17:00 | 2014-08-28 08:00 | 2014-09-20 17:00 | 2014-09-03 08:00 | 2014-09-25 17:00 |  | PT_Normal |  |  |  |  | /ih1RIKbQ1W1dcRuCs139w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37660 | N | N | 25 | GAZEBO |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 124 | STEEL FIXERS SK
%R | 501286 | 6359 | 124631 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBGZGL7905 | Installation of Wooden Works | 8178 | 40 | 0 | 200 | 0 | 300 | 300 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-15 08:00 | 2014-10-15 17:00 |  | 2014-09-09 08:00 | 2014-10-07 17:00 | 2014-09-09 08:00 | 2014-10-07 17:00 | 2014-09-09 08:00 | 2014-10-07 17:00 | 2014-09-15 08:00 | 2014-10-15 17:00 |  | PT_Normal |  |  |  |  | c36bGtGhQzyegWwDDDsZuw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37660 | N | N | 25 | GAZEBO |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 300 | LABOR- SUBCONTRACTOR
%R | 501287 | 6359 | 124631 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBGZGL7910 | Electrical Works-Gazebo | 8178 | 40 | 40 | 120 | 0 | 125.6 | 125.6 | 120 | 0 | 0 | 0 |  |  |  | 2014-10-16 08:00 | 2014-11-02 17:00 |  | 2014-10-08 08:00 | 2014-10-27 17:00 | 2014-10-08 08:00 | 2014-10-27 17:00 | 2014-10-08 08:00 | 2014-10-27 17:00 | 2014-10-16 08:00 | 2014-11-02 17:00 |  | PT_Normal |  |  |  |  | B7yQmDnWT1iXBlvGF65oKg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37660 | N | N | 25 | GAZEBO |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 125.6 | LABOR- SUBCONTRACTOR
%R | 501288 | 6359 | 124631 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBGZGL7915 | Park Benches Installation | 8178 | 120 | 80 | 120 | 0 | 120 | 120 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-27 08:00 | 2014-10-15 17:00 |  | 2014-09-09 08:00 | 2014-09-25 17:00 | 2014-09-09 08:00 | 2014-09-25 17:00 | 2014-09-09 08:00 | 2014-09-25 17:00 | 2014-09-27 08:00 | 2014-10-15 17:00 |  | PT_Normal |  |  |  |  | 9HED+UW8RSqqNJmxaOgDCA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37660 | N | N | 25 | GAZEBO |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 120 | LABOR- SUBCONTRACTOR
%R | 501289 | 6359 | 124632 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBIWGL7460 | Installation of Steel Ladder | 8178 | 272 | 0 | 40 | 0 | 14 | 14 | 40 | 0 | 0 | 0 |  |  |  | 2014-12-03 08:00 | 2014-12-08 17:00 |  | 2014-10-25 08:00 | 2014-10-29 17:00 | 2014-10-25 08:00 | 2014-10-29 17:00 | 2014-10-25 08:00 | 2014-10-29 17:00 | 2014-12-03 08:00 | 2014-12-08 17:00 |  | PT_Normal |  |  |  |  | HpetqwXWTFeQZuvHtnKXsw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37630 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 14 | LABOR- SUBCONTRACTOR
%R | 501290 | 6359 | 124632 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBIWGL7465 | Installation of G.I Handrails | 8178 | 272 | 272 | 40 | 0 | 164 | 164 | 40 | 0 | 0 | 0 |  |  |  | 2014-12-09 08:00 | 2014-12-14 17:00 |  | 2014-10-30 08:00 | 2014-11-04 17:00 | 2014-10-30 08:00 | 2014-11-04 17:00 | 2014-10-30 08:00 | 2014-11-04 17:00 | 2014-12-09 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | BPFJjfwgSLS19HK7x8hH5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37630 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 164 | LABOR- SUBCONTRACTOR
%R | 501291 | 6359 | 124632 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBIWGL7440 | Plumbing , Drainage & Firefighting works | 8178 | 424 | 0 | 200 | 0 | 50.4 | 50.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-29 08:00 | 2014-11-26 17:00 |  | 2014-08-26 08:00 | 2014-09-23 17:00 | 2014-08-26 08:00 | 2014-09-23 17:00 | 2014-08-26 08:00 | 2014-09-23 17:00 | 2014-10-29 08:00 | 2014-11-26 17:00 |  | PT_Normal |  |  |  |  | lh7FXqUsSgimfDnzIkIVlw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37630 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 501292 | 6359 | 124632 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBIWGL7445 | AC Works | 8178 | 424 | 152 | 200 | 0 | 159.2 | 159.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-29 08:00 | 2014-11-26 17:00 |  | 2014-08-26 08:00 | 2014-09-23 17:00 | 2014-08-26 08:00 | 2014-09-23 17:00 | 2014-08-26 08:00 | 2014-09-23 17:00 | 2014-10-29 08:00 | 2014-11-26 17:00 |  | PT_Normal |  |  |  |  | w1Dt3oXZRiGO6E1+k42sTA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37630 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 159.2 | LABOR- SUBCONTRACTOR
%R | 501293 | 6359 | 124632 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBIWGL7450 | Electrical Works | 8178 | 272 | 0 | 200 | 0 | 325.2 | 325.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-29 08:00 | 2014-11-26 17:00 |  | 2014-09-17 08:00 | 2014-10-18 17:00 | 2014-09-17 08:00 | 2014-10-18 17:00 | 2014-09-17 08:00 | 2014-10-18 17:00 | 2014-10-29 08:00 | 2014-11-26 17:00 |  | PT_Normal |  |  |  |  | jluD5PzARyqkqmho4gsxCQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37630 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 162.6 | LABOR- SUBCONTRACTOR
%R | 501294 | 6359 | 124632 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBIWGL7950 | Laying of Interlock | 8174 | 552 | 0 | 80 | 0 | 58 | 58 | 80 | 0 | 0 | 0 |  |  |  | 2014-11-10 08:00 | 2014-11-20 17:00 |  | 2014-08-19 08:00 | 2014-08-30 17:00 | 2014-08-19 08:00 | 2014-08-30 17:00 | 2014-08-19 08:00 | 2014-08-30 17:00 | 2014-11-10 08:00 | 2014-11-20 17:00 |  | PT_Normal |  |  |  |  | 5HplT8VZTz2iZY2groRq6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37630 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 58 | INTERLOCK MASON SK
%R | 501295 | 6359 | 124632 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBIWGL7435 | Installation of Boundary Fences | 8165 | 552 | 280 | 120 | 0 | 42 | 42 | 120 | 0 | 0 | 0 |  |  |  | 2014-11-22 08:00 | 2014-12-08 17:00 |  | 2014-08-31 08:00 | 2014-09-16 17:00 | 2014-08-31 08:00 | 2014-09-16 17:00 | 2014-08-31 08:00 | 2014-09-16 17:00 | 2014-11-22 08:00 | 2014-12-08 17:00 |  | PT_Normal |  |  |  |  | RIrR/s4vSAiO1A3Ko9a1yQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37630 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 42 | STEEL FIXERS SK
%R | 501296 | 6359 | 124632 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBIWGL7400 | Excavation | 8162 | 104 | 0 | 120 | 0 | 295 | 295 | 120 | 150.9999 | 0 | 150.9999 |  |  |  | 2014-05-12 08:00 | 2014-05-28 17:00 |  | 2014-04-27 08:00 | 2014-05-13 17:00 | 2014-04-27 08:00 | 2014-05-13 17:00 | 2014-04-27 08:00 | 2014-05-13 17:00 | 2014-05-12 08:00 | 2014-05-28 17:00 |  | PT_Normal |  |  |  |  | FfA/wII/RD2dV2aW1iw9yg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43390 |  |  |  |  | EQUIP OPERATORS | EQOP |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37630 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 295 | EQUIP OPERATORS
%R | 501297 | 6359 | 124632 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBIWGL7405 | Blinding & base waterproofing | 8163 | 104 | 0 | 80 | 0 | 200 | 200 | 80 | 0 | 0 | 0 |  |  |  | 2014-05-29 08:00 | 2014-06-09 17:00 |  | 2014-05-14 08:00 | 2014-05-25 17:00 | 2014-05-14 08:00 | 2014-05-25 17:00 | 2014-05-14 08:00 | 2014-05-25 17:00 | 2014-05-29 08:00 | 2014-06-09 17:00 |  | PT_Normal |  |  |  |  | XOtMTMqNQ9C8iQmknqisAA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37630 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 200 | BLINDING MASON SK
%R | 501298 | 6359 | 124632 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBIWGL7415 | Construction of RCC Wall | 8165 | 104 | 0 | 200 | 0 | 1708 | 1708 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-22 08:00 | 2014-07-20 17:00 |  | 2014-06-07 08:00 | 2014-07-05 17:00 | 2014-06-07 08:00 | 2014-07-05 17:00 | 2014-06-07 08:00 | 2014-07-05 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 |  | PT_Normal |  |  |  |  | /XJHGkBCSNeQ3GE6que8lw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37630 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1708 | STEEL FIXERS SK
%R | 501299 | 6359 | 124632 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBIWGL7420 | Construction of Roof Slab | 8165 | 432 | 0 | 160 | 0 | 490 | 490 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-10-02 17:00 |  | 2014-07-06 08:00 | 2014-07-28 17:00 | 2014-07-06 08:00 | 2014-07-28 17:00 | 2014-07-06 08:00 | 2014-07-28 17:00 | 2014-09-10 08:00 | 2014-10-02 17:00 |  | PT_Normal |  |  |  |  | CBB5BlNsRbeY4X0ocjlWwg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37630 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 490 | STEEL FIXERS SK
%R | 501300 | 6359 | 124632 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBIWGL7425 | Waterproofing & Backfilling | 8162 | 432 | 0 | 120 | 0 | 141 | 141 | 120 | 33 | 0 | 33 |  |  |  | 2014-10-04 08:00 | 2014-10-22 17:00 |  | 2014-07-29 08:00 | 2014-08-18 17:00 | 2014-07-29 08:00 | 2014-08-18 17:00 | 2014-07-29 08:00 | 2014-08-18 17:00 | 2014-10-04 08:00 | 2014-10-22 17:00 |  | PT_Normal |  |  |  |  | Y5O86HO6RMS/jex+WXhyog |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43390 |  |  |  |  | EQUIP OPERATORS | EQOP |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37630 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 141 | EQUIP OPERATORS
%R | 501301 | 6359 | 124632 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBIWGL7430 | Floor screed | 8164 | 432 | 8 | 40 | 0 | 66 | 66 | 40 | 0 | 0 | 0 |  |  |  | 2014-10-23 08:00 | 2014-10-28 17:00 |  | 2014-08-19 08:00 | 2014-08-24 17:00 | 2014-08-19 08:00 | 2014-08-24 17:00 | 2014-08-19 08:00 | 2014-08-24 17:00 | 2014-10-23 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | 3EtBv7NcQ+C6Q6KDqHg+ng |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37630 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 66 | SCREED MASON SK
%R | 501302 | 6359 | 124632 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBIWGL7455 | Internal epoxy coating & Painting | 8178 | 272 | 0 | 40 | 0 | 44 | 44 | 40 | 0 | 0 | 0 |  |  |  | 2014-11-27 08:00 | 2014-12-02 17:00 |  | 2014-10-19 08:00 | 2014-10-23 17:00 | 2014-10-19 08:00 | 2014-10-23 17:00 | 2014-10-19 08:00 | 2014-10-23 17:00 | 2014-11-27 08:00 | 2014-12-02 17:00 |  | PT_Normal |  |  |  |  | Wmt9l9qKSKGEVDF3hh73Mw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37630 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 44 | LABOR- SUBCONTRACTOR
%R | 501303 | 6359 | 124632 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBIWGL7410 | Construction of Raft slab | 8165 | 104 | 0 | 80 | 0 | 630 | 630 | 80 | 0 | 0 | 0 |  |  |  | 2014-06-10 08:00 | 2014-06-21 17:00 |  | 2014-05-26 08:00 | 2014-06-05 17:00 | 2014-05-26 08:00 | 2014-06-05 17:00 | 2014-05-26 08:00 | 2014-06-05 17:00 | 2014-06-10 08:00 | 2014-06-21 17:00 |  | PT_Normal |  |  |  |  | xcEwOKgCStKxPkat93N5Sg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37630 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 630 | STEEL FIXERS SK
%R | 501304 | 6359 | 124633 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBTRGL7600 | Excavation | 8162 | 104 | 0 | 80 | 0 | 32 | 32 | 80 | 20 | 0 | 20 |  |  |  | 2014-07-21 08:00 | 2014-07-31 17:00 |  | 2014-07-06 08:00 | 2014-07-16 17:00 | 2014-07-06 08:00 | 2014-07-16 17:00 | 2014-07-06 08:00 | 2014-07-16 17:00 | 2014-07-21 08:00 | 2014-07-31 17:00 |  | PT_Normal |  |  |  |  | vNL2z7TuQKqOL7AXM1DtWQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43390 |  |  |  |  | EQUIP OPERATORS | EQOP |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37640 | N | N | 15 | TELECOMMUNICATION ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 32 | EQUIP OPERATORS
%R | 501305 | 6359 | 124633 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBTRGL7605 | Construction of foundation & Grade slab | 8165 | 184 | 0 | 160 | 0 | 280 | 280 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-17 08:00 | 2014-09-08 17:00 |  | 2014-07-17 08:00 | 2014-08-12 17:00 | 2014-07-17 08:00 | 2014-08-12 17:00 | 2014-07-17 08:00 | 2014-08-12 17:00 | 2014-08-17 08:00 | 2014-09-08 17:00 |  | PT_Normal |  |  |  |  | puURPDQwQ2GABRvFj43Y/w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37640 | N | N | 15 | TELECOMMUNICATION ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 280 | STEEL FIXERS SK
%R | 501306 | 6359 | 124633 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBTRGL7610 | Construction Column,Beams & Roof Slab | 8165 | 184 | 0 | 160 | 0 | 280 | 280 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-09 08:00 | 2014-10-01 17:00 |  | 2014-08-13 08:00 | 2014-09-04 17:00 | 2014-08-13 08:00 | 2014-09-04 17:00 | 2014-08-13 08:00 | 2014-09-04 17:00 | 2014-09-09 08:00 | 2014-10-01 17:00 |  | PT_Normal |  |  |  |  | n/i58HfqTXGqeQItfTF/2Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37640 | N | N | 15 | TELECOMMUNICATION ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 280 | STEEL FIXERS SK
%R | 501307 | 6359 | 124633 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBTRGL7615 | Finishing Works | 8164 | 184 | 72 | 200 | 0 | 1000 | 1000 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-29 08:00 | 2014-11-26 17:00 |  | 2014-09-30 08:00 | 2014-10-30 17:00 | 2014-09-30 08:00 | 2014-10-30 17:00 | 2014-09-30 08:00 | 2014-10-30 17:00 | 2014-10-29 08:00 | 2014-11-26 17:00 |  | PT_Normal |  |  |  |  | yp74h0ZdQ+CR93HWmY4Gow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37640 | N | N | 15 | TELECOMMUNICATION ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 500 | SCREED MASON SK
%R | 501308 | 6359 | 124633 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBTRGL7620 | Plumbing , Drainage & Firefighting works | 8178 | 112 | 0 | 200 | 0 | 282.8 | 282.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-10 08:00 | 2014-12-08 17:00 |  | 2014-10-25 08:00 | 2014-11-22 17:00 | 2014-10-25 08:00 | 2014-11-22 17:00 | 2014-10-25 08:00 | 2014-11-22 17:00 | 2014-11-10 08:00 | 2014-12-08 17:00 |  | PT_Normal |  |  |  |  | /E2R+j+TQI6kdpgSYepvlQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37640 | N | N | 15 | TELECOMMUNICATION ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 282.8 | LABOR- SUBCONTRACTOR
%R | 501309 | 6359 | 124633 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBTRGL7625 | AC Works | 8178 | 112 | 0 | 200 | 0 | 284 | 284 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-10 08:00 | 2014-12-08 17:00 |  | 2014-10-25 08:00 | 2014-11-22 17:00 | 2014-10-25 08:00 | 2014-11-22 17:00 | 2014-10-25 08:00 | 2014-11-22 17:00 | 2014-11-10 08:00 | 2014-12-08 17:00 |  | PT_Normal |  |  |  |  | EjYVzKr0RByDXw9LuPd8rw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37640 | N | N | 15 | TELECOMMUNICATION ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 284 | LABOR- SUBCONTRACTOR
%R | 501310 | 6359 | 124633 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBTRGL7630 | Electrical Works-Telecom Room | 8178 | 112 | 0 | 200 | 0 | 416 | 416 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-10 08:00 | 2014-12-08 17:00 |  | 2014-10-25 08:00 | 2014-11-22 17:00 | 2014-10-25 08:00 | 2014-11-22 17:00 | 2014-10-25 08:00 | 2014-11-22 17:00 | 2014-11-10 08:00 | 2014-12-08 17:00 |  | PT_Normal |  |  |  |  | h3xGekIcQlmveXkZ85Bt1Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37640 | N | N | 15 | TELECOMMUNICATION ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 416 | LABOR- SUBCONTRACTOR
%R | 501311 | 6359 | 124633 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBTRGL7635 | Final Paintings | 8178 | 112 | 112 | 40 | 0 | 275 | 275 | 40 | 0 | 0 | 0 |  |  |  | 2014-12-09 08:00 | 2014-12-14 17:00 |  | 2014-11-23 08:00 | 2014-11-27 17:00 | 2014-11-23 08:00 | 2014-11-27 17:00 | 2014-11-23 08:00 | 2014-11-27 17:00 | 2014-12-09 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | mLnkK+7LTBSjTDIRxK/iyg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37640 | N | N | 15 | TELECOMMUNICATION ROOM |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 275 | LABOR- SUBCONTRACTOR
%R | 501312 | 6359 | 124634 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBGHGL7800 | Excavation | 8162 | 104 | 0 | 80 | 0 | 32 | 32 | 80 | 20 | 0 | 20 |  |  |  | 2014-08-05 08:00 | 2014-08-16 17:00 |  | 2014-07-17 08:00 | 2014-07-28 17:00 | 2014-07-17 08:00 | 2014-07-28 17:00 | 2014-07-17 08:00 | 2014-07-28 17:00 | 2014-08-05 08:00 | 2014-08-16 17:00 |  | PT_Normal |  |  |  |  | jEDBNYD/Tnqu76nVWv17GQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43390 |  |  |  |  | EQUIP OPERATORS | EQOP |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37650 | N | N | 20 | GUARD HOUSE |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 32 | EQUIP OPERATORS
%R | 501313 | 6359 | 124634 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBGHGL7805 | Construction of foundation & Grade slab | 8165 | 104 | 0 | 160 | 0 | 280 | 280 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-17 08:00 | 2014-09-08 17:00 |  | 2014-07-29 08:00 | 2014-08-24 17:00 | 2014-07-29 08:00 | 2014-08-24 17:00 | 2014-07-29 08:00 | 2014-08-24 17:00 | 2014-08-17 08:00 | 2014-09-08 17:00 |  | PT_Normal |  |  |  |  | 11LGfRQ/S+eW1QvxRd67aA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37650 | N | N | 20 | GUARD HOUSE |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 280 | STEEL FIXERS SK
%R | 501314 | 6359 | 124634 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBGHGL7810 | Construction Column,Beams & Roof Slab | 8165 | 104 | 0 | 160 | 0 | 280 | 280 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-09 08:00 | 2014-10-01 17:00 |  | 2014-08-25 08:00 | 2014-09-16 17:00 | 2014-08-25 08:00 | 2014-09-16 17:00 | 2014-08-25 08:00 | 2014-09-16 17:00 | 2014-09-09 08:00 | 2014-10-01 17:00 |  | PT_Normal |  |  |  |  | K9Uj7qmTT9WD+gR3kBl1Tg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37650 | N | N | 20 | GUARD HOUSE |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 280 | STEEL FIXERS SK
%R | 501315 | 6359 | 124634 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBGHGL7815 | Finishing Works | 8164 | 104 | 0 | 200 | 0 | 1000 | 1000 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-29 08:00 | 2014-11-26 17:00 |  | 2014-10-14 08:00 | 2014-11-11 17:00 | 2014-10-14 08:00 | 2014-11-11 17:00 | 2014-10-14 08:00 | 2014-11-11 17:00 | 2014-10-29 08:00 | 2014-11-26 17:00 |  | PT_Normal |  |  |  |  | nxsaCWy/TSSGYBFgu0cr6g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37650 | N | N | 20 | GUARD HOUSE |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 1000 | SCREED MASON SK
%R | 501316 | 6359 | 124634 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBGHGL7820 | Plumbing , Drainage & Firefighting works | 8181 | 104 | 0 | 200 | 0 | 282.8 | 282.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-10 08:00 | 2014-12-08 17:00 |  | 2014-10-26 08:00 | 2014-11-23 17:00 | 2014-10-26 08:00 | 2014-11-23 17:00 | 2014-10-26 08:00 | 2014-11-23 17:00 | 2014-11-10 08:00 | 2014-12-08 17:00 |  | PT_Normal |  |  |  |  | pTsjwmCKQcaXl6IxUIT4Jg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43581 |  |  |  |  | MECHANICALS SK | M303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37650 | N | N | 20 | GUARD HOUSE |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 282.8 | MECHANICALS SK
%R | 501317 | 6359 | 124634 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBGHGL7825 | AC Works |  | 104 | 0 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-10 08:00 | 2014-12-08 17:00 |  | 2014-10-26 08:00 | 2014-11-23 17:00 | 2014-10-26 08:00 | 2014-11-23 17:00 | 2014-10-26 08:00 | 2014-11-23 17:00 | 2014-11-10 08:00 | 2014-12-08 17:00 |  | PT_Normal |  |  |  |  | W80yHkWjQy2Q7NzbkLUEGg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 37650 | N | N | 20 | GUARD HOUSE |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 0 | 0
%R | 501318 | 6359 | 124634 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBGHGL7830 | Electrical Works-Telecom Room | 8180 | 104 | 0 | 200 | 0 | 416 | 416 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-10 08:00 | 2014-12-08 17:00 |  | 2014-10-26 08:00 | 2014-11-23 17:00 | 2014-10-26 08:00 | 2014-11-23 17:00 | 2014-10-26 08:00 | 2014-11-23 17:00 | 2014-11-10 08:00 | 2014-12-08 17:00 |  | PT_Normal |  |  |  |  | +6HXkG4HTCyDv+aAOLBK0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43571 |  |  |  |  | ELECTRICIANS SK | M302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37650 | N | N | 20 | GUARD HOUSE |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 416 | ELECTRICIANS SK
%R | 501319 | 6359 | 124634 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BSBGHGL7835 | Final Paintings | 8178 | 104 | 104 | 40 | 0 | 275 | 275 | 40 | 0 | 0 | 0 |  |  |  | 2014-12-09 08:00 | 2014-12-14 17:00 |  | 2014-11-24 08:00 | 2014-11-29 17:00 | 2014-11-24 08:00 | 2014-11-29 17:00 | 2014-11-24 08:00 | 2014-11-29 17:00 | 2014-12-09 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | 3Ycule62Quq864jOyfaEJw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37650 | N | N | 20 | GUARD HOUSE |  | 124630 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 275 | LABOR- SUBCONTRACTOR
%R | 501320 | 6359 | 124637 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2SLGL7200 | Excavation | 8177 | 48 | 0 | 200 | 0 | 926 | 926 | 200 | 500 | 0 | 500 |  |  |  | 2014-07-28 08:00 | 2014-08-28 17:00 |  | 2014-07-21 08:00 | 2014-08-21 17:00 | 2014-07-21 08:00 | 2014-08-21 17:00 | 2014-07-21 08:00 | 2014-08-21 17:00 | 2014-07-28 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | eglZcuZnTnOls4N5NqKTUw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37300 | N | N | 70 | SOFT LANDSCAPING |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 463 | LABOR - CIVIL
%R | 501321 | 6359 | 124637 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2SLGL7205 | Sweet Soil Laying | 8178 | 48 | 0 | 200 | 0 | 4102 | 4102 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-09-09 17:00 |  | 2014-08-05 08:00 | 2014-09-02 17:00 | 2014-08-05 08:00 | 2014-09-02 17:00 | 2014-08-05 08:00 | 2014-09-02 17:00 | 2014-08-12 08:00 | 2014-09-09 17:00 |  | PT_Normal |  |  |  |  | WSOzpmQhQSyNVdAvxQsUJA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37300 | N | N | 70 | SOFT LANDSCAPING |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 4102 | LABOR- SUBCONTRACTOR
%R | 501322 | 6359 | 124637 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2SLGL7210 | Plantation works | 8178 | 208 | 120 | 200 | 0 | 728 | 728 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | MGA2MW7pR9+wXnfkp6Rv+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37300 | N | N | 70 | SOFT LANDSCAPING |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 728 | LABOR- SUBCONTRACTOR
%R | 501323 | 6359 | 124638 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2BWGL5315 | Construction of Boundary Wall (Ht-3m) | 8165 | 280 | 0 | 200 | 0 | 196 | 196 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-22 08:00 | 2014-07-20 17:00 |  | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 |  | PT_Normal |  |  |  |  | 0ZQpAwPqQjO0Q5l7oA34nA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37260 | N | N | 50 | BOUNDARY WALL |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 196 | STEEL FIXERS SK
%R | 501324 | 6359 | 124638 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 8178 | 280 | 0 | 200 | 0 | 14 | 14 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-08 08:00 | 2014-08-09 17:00 |  | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-07-08 08:00 | 2014-08-09 17:00 |  | PT_Normal |  |  |  |  | xf3StfXUTkiKhY8I165O6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37260 | N | N | 50 | BOUNDARY WALL |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 14 | LABOR- SUBCONTRACTOR
%R | 501325 | 6359 | 124638 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 8165 | 280 | 0 | 200 | 0 | 140 | 140 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-10 08:00 | 2014-09-07 17:00 |  | 2014-06-26 08:00 | 2014-07-24 17:00 | 2014-06-26 08:00 | 2014-07-24 17:00 | 2014-06-26 08:00 | 2014-07-24 17:00 | 2014-08-10 08:00 | 2014-09-07 17:00 |  | PT_Normal |  |  |  |  | r38lyPcCTsKMMeaH4MslFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37260 | N | N | 50 | BOUNDARY WALL |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 140 | STEEL FIXERS SK
%R | 501326 | 6359 | 124638 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 8165 | 584 | 120 | 200 | 0 | 140 | 140 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-05 08:00 | 2014-11-04 17:00 |  | 2014-07-08 08:00 | 2014-08-09 17:00 | 2014-07-08 08:00 | 2014-08-09 17:00 | 2014-07-08 08:00 | 2014-08-09 17:00 | 2014-10-05 08:00 | 2014-11-04 17:00 |  | PT_Normal |  |  |  |  | pYGcah+VRbu+1TDyhQ9y0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37260 | N | N | 50 | BOUNDARY WALL |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 70 | STEEL FIXERS SK
%R | 501327 | 6359 | 124639 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2FFGL5185 | Excavation for firefighting line | 8177 | 0 | 0 | 200 | 0 | 190 | 190 | 200 | 100 | 0 | 100 |  |  |  | 2014-03-22 08:00 | 2014-04-19 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | 9XuVDA2IReKH1h0aDwbWnA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37210 | N | N | 25 | FIREFIGHTING LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 190 | LABOR - CIVIL
%R | 501328 | 6359 | 124639 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2FFGL5190 | Laying of firefighting line | 8178 | 0 | 0 | 200 | 0 | 210 | 210 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-30 08:00 | 2014-04-27 17:00 |  | 2014-03-30 08:00 | 2014-04-27 17:00 | 2014-03-30 08:00 | 2014-04-27 17:00 | 2014-03-30 08:00 | 2014-04-27 17:00 | 2014-03-30 08:00 | 2014-04-27 17:00 |  | PT_Normal |  |  |  |  | csLAK4K4QQKNUKz3Bi2OtA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37210 | N | N | 25 | FIREFIGHTING LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 210 | LABOR- SUBCONTRACTOR
%R | 501329 | 6359 | 124639 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2FFGL5195 | Testing of firefighting line | 8178 | 0 | 0 | 200 | 0 | 50.4 | 50.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-05 08:00 | 2014-05-03 17:00 |  | 2014-04-05 08:00 | 2014-05-03 17:00 | 2014-04-05 08:00 | 2014-05-03 17:00 | 2014-04-05 08:00 | 2014-05-03 17:00 | 2014-04-05 08:00 | 2014-05-03 17:00 |  | PT_Normal |  |  |  |  | wnnixq/USjSnuOQGxey9dA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37210 | N | N | 25 | FIREFIGHTING LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 501330 | 6359 | 124639 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2FFGL5200 | Backfilling firefighting line | 8177 | 0 | 0 | 200 | 0 | 311 | 311 | 200 | 275 | 0 | 275 |  |  |  | 2014-04-10 08:00 | 2014-05-08 17:00 |  | 2014-04-10 08:00 | 2014-05-08 17:00 | 2014-04-10 08:00 | 2014-05-08 17:00 | 2014-04-10 08:00 | 2014-05-08 17:00 | 2014-04-10 08:00 | 2014-05-08 17:00 |  | PT_Normal |  |  |  |  | GNl4cUZKQvCpi/912bNB5g |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37210 | N | N | 25 | FIREFIGHTING LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 311 | LABOR - CIVIL
%R | 501331 | 6359 | 124639 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2FFGL5205 | Construction of valve chambers & Thrust Blocks | 8165 | 176 | 0 | 200 | 0 | 266 | 266 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-12 08:00 | 2014-06-09 17:00 |  | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 |  | PT_Normal |  |  |  |  | BSTc5DgkR2C4sLC82O2g3g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37210 | N | N | 25 | FIREFIGHTING LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 266 | STEEL FIXERS SK
%R | 501332 | 6359 | 124639 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2FFGL5210 | Connection with existing Firewater System | 8178 | 176 | 120 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-18 08:00 | 2014-06-15 17:00 |  | 2014-04-22 08:00 | 2014-05-20 17:00 | 2014-04-22 08:00 | 2014-05-20 17:00 | 2014-04-22 08:00 | 2014-05-20 17:00 | 2014-05-18 08:00 | 2014-06-15 17:00 |  | PT_Normal |  |  |  |  | kSBZdW8GQjqlPpRYalN9KA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37210 | N | N | 25 | FIREFIGHTING LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 84 | LABOR- SUBCONTRACTOR
%R | 501333 | 6359 | 124640 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2SAGL5135 | Construction of manholes Drainage | 8177 | 512 | 80 | 200 | 0 | 6 | 6 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-24 08:00 | 2014-05-22 17:00 |  | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 |  | PT_Normal |  |  |  |  | rCxhP2EOS2aqzt3xZx/6fA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37190 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 3 | LABOR - CIVIL
%R | 501334 | 6359 | 124640 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2SAGL5145 | Construction of Road gullies | 8172 | 40 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-16 08:00 | 2014-04-13 17:00 |  | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 |  | PT_Normal |  |  |  |  | yfAwG+pOQtWRxTQ18tV9iQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37190 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 176 | MANHOLES SK
%R | 501335 | 6359 | 124640 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2SAGL5150 | Connection with existing sewer manhole | 8177 | 312 | 312 | 160 | 0 | 6 | 6 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-24 08:00 | 2014-06-15 17:00 |  | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-05-24 08:00 | 2014-06-15 17:00 |  | PT_Normal |  |  |  |  | OllRn1jbQP6h7To1br/Bdg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37190 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 6 | LABOR - CIVIL
%R | 501336 | 6359 | 124640 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2SAGL5140 | Construction of soakaways | 8172 | 40 | 0 | 200 | 0 | 190 | 190 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-15 08:00 | 2014-03-15 17:00 |  | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 |  | PT_Normal |  |  |  |  | yrm9bErKRw6ZNccPL0bOXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37190 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 95 | MANHOLES SK
%R | 501337 | 6359 | 124641 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2IRGL5265 | Excavation for irrigation line | 8177 | 56 | 0 | 200 | 0 | 998 | 998 | 200 | 500 | 0 | 500 |  |  |  | 2014-06-09 08:00 | 2014-07-07 17:00 |  | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 |  | PT_Normal |  |  |  |  | 4JHPMxrqSPuF89RFi+ok8g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37240 | N | N | 40 | IRRIGATION LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 998 | LABOR - CIVIL
%R | 501338 | 6359 | 124641 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2IRGL5270 | Laying of irrigationline | 8178 | 56 | 0 | 200 | 0 | 352.8 | 352.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-13 17:00 |  | 2014-06-07 08:00 | 2014-07-05 17:00 | 2014-06-07 08:00 | 2014-07-05 17:00 | 2014-06-07 08:00 | 2014-07-05 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 |  | PT_Normal |  |  |  |  | njrtsPJgSIeCnTmWAuAgXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37240 | N | N | 40 | IRRIGATION LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 352.8 | LABOR- SUBCONTRACTOR
%R | 501339 | 6359 | 124641 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2IRGL5275 | Testing of irrigation line | 8178 | 56 | 0 | 200 | 0 | 285.6 | 285.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-21 08:00 | 2014-07-19 17:00 |  | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-21 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37240 | N | N | 40 | IRRIGATION LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 285.6 | LABOR- SUBCONTRACTOR
%R | 501340 | 6359 | 124641 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2IRGL5280 | Backfilling irrigation line | 8177 | 56 | 0 | 200 | 0 | 706 | 706 | 200 | 550 | 0 | 550 |  |  |  | 2014-06-26 08:00 | 2014-07-24 17:00 |  | 2014-06-18 08:00 | 2014-07-16 17:00 | 2014-06-18 08:00 | 2014-07-16 17:00 | 2014-06-18 08:00 | 2014-07-16 17:00 | 2014-06-26 08:00 | 2014-07-24 17:00 |  | PT_Normal |  |  |  |  | L2HG3TjJSymO71oS93ujzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37240 | N | N | 40 | IRRIGATION LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 706 | LABOR - CIVIL
%R | 501341 | 6359 | 124641 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2IRGL5285 | Construction of Thrust Blocks,Pull boxes | 8178 | 136 | 0 | 200 | 0 | 149.6 | 149.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-20 08:00 | 2014-08-20 17:00 |  | 2014-06-30 08:00 | 2014-07-28 17:00 | 2014-06-30 08:00 | 2014-07-28 17:00 | 2014-06-30 08:00 | 2014-07-28 17:00 | 2014-07-20 08:00 | 2014-08-20 17:00 |  | PT_Normal |  |  |  |  | wI3eALumTkyxqSde7ipvjw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37240 | N | N | 40 | IRRIGATION LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 149.6 | LABOR- SUBCONTRACTOR
%R | 501342 | 6359 | 124641 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2IRGL5290 | Irrigation Fittings (Nozzle,Values) | 8178 | 136 | 88 | 200 | 0 | 352.8 | 352.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-28 08:00 | 2014-08-28 17:00 |  | 2014-07-08 08:00 | 2014-08-09 17:00 | 2014-07-08 08:00 | 2014-08-09 17:00 | 2014-07-08 08:00 | 2014-08-09 17:00 | 2014-07-28 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | t8WA/eCXQL+p36qfP5Bd5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37240 | N | N | 40 | IRRIGATION LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 176.4 | LABOR- SUBCONTRACTOR
%R | 501343 | 6359 | 124642 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2RWGL6020 | Laying of Road Base Asphalt Concrete | 8178 | 296 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-09-29 08:00 | 2014-10-04 17:00 |  | 2014-08-17 08:00 | 2014-08-21 17:00 | 2014-08-17 08:00 | 2014-08-21 17:00 | 2014-08-17 08:00 | 2014-08-21 17:00 | 2014-09-29 08:00 | 2014-10-04 17:00 |  | PT_Normal |  |  |  |  | ZPLePxyrQVG8loQLPKJL0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37270 | N | N | 55 | ROAD WORKS |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 174 | LABOR- SUBCONTRACTOR
%R | 501344 | 6359 | 124642 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2RWGL6025 | Laying of Asphalt Wearing Coarse | 8178 | 416 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-10-25 08:00 | 2014-10-29 17:00 |  | 2014-08-23 08:00 | 2014-08-27 17:00 | 2014-08-23 08:00 | 2014-08-27 17:00 | 2014-08-23 08:00 | 2014-08-27 17:00 | 2014-10-25 08:00 | 2014-10-29 17:00 |  | PT_Normal |  |  |  |  | Lxj6MKcyRuq6Sfjywmt9Tw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37270 | N | N | 55 | ROAD WORKS |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 174 | LABOR- SUBCONTRACTOR
%R | 501345 | 6359 | 124642 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2RWGL6030 | Traffic Signage & Road Marking | 8178 | 416 | 120 | 40 | 0 | 882 | 882 | 40 | 0 | 0 | 0 |  |  |  | 2014-10-30 08:00 | 2014-11-04 17:00 |  | 2014-08-28 08:00 | 2014-09-02 17:00 | 2014-08-28 08:00 | 2014-09-02 17:00 | 2014-08-28 08:00 | 2014-09-02 17:00 | 2014-10-30 08:00 | 2014-11-04 17:00 |  | PT_Normal |  |  |  |  | kyD9y14oQWiXZXNUeYvXKg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37270 | N | N | 55 | ROAD WORKS |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 882 | LABOR- SUBCONTRACTOR
%R | 501346 | 6359 | 124642 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2RWGL6000 | Excavation & Earth Filling | 8177 | 0 | 0 | 80 | 0 | 1150 | 1150 | 80 | 400 | 0 | 400 |  |  |  | 2014-06-16 08:00 | 2014-06-26 17:00 |  | 2014-06-16 08:00 | 2014-06-26 17:00 | 2014-06-16 08:00 | 2014-06-26 17:00 | 2014-06-16 08:00 | 2014-06-26 17:00 | 2014-06-16 08:00 | 2014-06-26 17:00 |  | PT_Normal |  |  |  |  | B7fikzSdQpyX/FH0FXdZyg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37270 | N | N | 55 | ROAD WORKS |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1150 | LABOR - CIVIL
%R | 501347 | 6359 | 124642 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2RWGL6005 | Laying of Sub Grade | 8178 | 0 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-28 08:00 | 2014-07-26 17:00 |  | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 |  | PT_Normal |  |  |  |  | /VMmbkGPRxa0c6wWhxMJFg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37270 | N | N | 55 | ROAD WORKS |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 24 | LABOR- SUBCONTRACTOR
%R | 501348 | 6359 | 124642 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2RWGL6010 | Laying of Precast Kerbs | 8178 | 0 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-09 08:00 | 2014-08-10 17:00 |  | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-07-09 08:00 | 2014-08-10 17:00 |  | PT_Normal |  |  |  |  | j67kTMlIRU+lNiZBnwCqpg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37270 | N | N | 55 | ROAD WORKS |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 12 | LABOR- SUBCONTRACTOR
%R | 501349 | 6359 | 124642 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2RWGL6015 | Laying of Granular Sub Base Coarse | 8173 | 0 | 0 | 160 | 0 | 1828 | 1828 | 160 | 600 | 0 | 600 |  |  |  | 2014-07-21 08:00 | 2014-08-16 17:00 |  | 2014-07-21 08:00 | 2014-08-16 17:00 | 2014-07-21 08:00 | 2014-08-16 17:00 | 2014-07-21 08:00 | 2014-08-16 17:00 | 2014-07-21 08:00 | 2014-08-16 17:00 |  | PT_Normal |  |  |  |  | 6p02o4T+Rf+N9ct1KcaDyw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37270 | N | N | 55 | ROAD WORKS |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1828 | KERBSTONE MASON SK
%R | 501350 | 6359 | 124643 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2TCGL5295 | Excavation Telecommunication trenches | 8177 | 0 | 0 | 160 | 0 | 356 | 356 | 160 | 200 | 0 | 200 |  |  |  | 2014-05-12 08:00 | 2014-06-03 17:00 |  | 2014-05-12 08:00 | 2014-06-03 17:00 | 2014-05-12 08:00 | 2014-06-03 17:00 | 2014-05-12 08:00 | 2014-06-03 17:00 | 2014-05-12 08:00 | 2014-06-03 17:00 |  | PT_Normal |  |  |  |  | DdHdoi/8SSCuOcdYUQE1aw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37250 | N | N | 45 | TELECOMMUNICATION LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 356 | LABOR - CIVIL
%R | 501351 | 6359 | 124643 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2TCGL5300 | Laying of cables | 8178 | 0 | 0 | 160 | 0 | 727.2 | 727.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-18 08:00 | 2014-06-09 17:00 |  | 2014-05-18 08:00 | 2014-06-09 17:00 | 2014-05-18 08:00 | 2014-06-09 17:00 | 2014-05-18 08:00 | 2014-06-09 17:00 | 2014-05-18 08:00 | 2014-06-09 17:00 |  | PT_Normal |  |  |  |  | mDi+QjBCQbKFKEegIY7Ofg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37250 | N | N | 45 | TELECOMMUNICATION LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 727.2 | LABOR- SUBCONTRACTOR
%R | 501352 | 6359 | 124643 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2TCGL5305 | Backfilling telecommunication trench | 8177 | 0 | 0 | 160 | 0 | 286 | 286 | 160 | 220 | 0 | 220 |  |  |  | 2014-05-24 08:00 | 2014-06-15 17:00 |  | 2014-05-24 08:00 | 2014-06-15 17:00 | 2014-05-24 08:00 | 2014-06-15 17:00 | 2014-05-24 08:00 | 2014-06-15 17:00 | 2014-05-24 08:00 | 2014-06-15 17:00 |  | PT_Normal |  |  |  |  | 4vEzMem3TCGKoLkTP3v/6w |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37250 | N | N | 45 | TELECOMMUNICATION LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 286 | LABOR - CIVIL
%R | 501353 | 6359 | 124643 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2TCGL5310 | Connection & Installation | 8178 | 568 | 160 | 160 | 0 | 271.2 | 271.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-21 17:00 |  | 2014-06-04 08:00 | 2014-06-26 17:00 | 2014-06-04 08:00 | 2014-06-26 17:00 | 2014-06-04 08:00 | 2014-06-26 17:00 | 2014-08-30 08:00 | 2014-09-21 17:00 |  | PT_Normal |  |  |  |  | uGXvJGVWRIyTrc7v/0QK6g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37250 | N | N | 45 | TELECOMMUNICATION LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 271.2 | LABOR- SUBCONTRACTOR
%R | 501354 | 6359 | 124644 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2HDGL7020 | Precast Concrete Kerbs works | 8173 | 48 | 0 | 160 | 0 | 800 | 800 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-23 08:00 | 2014-07-15 17:00 |  | 2014-06-16 08:00 | 2014-07-08 17:00 | 2014-06-16 08:00 | 2014-07-08 17:00 | 2014-06-16 08:00 | 2014-07-08 17:00 | 2014-06-23 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | k4r80m1TRGieOR0jalpg5Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37290 | N | N | 65 | HARD LANDSCAPING |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 800 | KERBSTONE MASON SK
%R | 501355 | 6359 | 124644 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2HDGL7025 | Interlocking for Walkways | 8174 | 48 | 0 | 200 | 0 | 814 | 814 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-05 08:00 | 2014-08-05 17:00 |  | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-07-05 08:00 | 2014-08-05 17:00 |  | PT_Normal |  |  |  |  | kSsun+DWRf+P4TUcR12Nqg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37290 | N | N | 65 | HARD LANDSCAPING |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 814 | INTERLOCK MASON SK
%R | 501356 | 6359 | 124644 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2HDGL7030 | Construction of Retaining wall | 8165 | 48 | 0 | 200 | 0 | 3340 | 3340 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | 6RmbkRKBTMu3g0LzlckNSg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37290 | N | N | 65 | HARD LANDSCAPING |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 1670 | STEEL FIXERS SK
%R | 501357 | 6359 | 124644 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2HDGL7035 | Construction of Wash Stone Boulders | 8170 | 48 | 0 | 200 | 0 | 22 | 22 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | xMByJf2RScW3WGSe+X3LCA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37290 | N | N | 65 | HARD LANDSCAPING |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 11 | TILE MASON SK
%R | 501358 | 6359 | 124644 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2HDGL7040 | Construction of Speed Humps | 8167 | 488 | 240 | 80 | 0 | 14 | 14 | 80 | 0 | 0 | 0 |  |  |  | 2014-11-10 08:00 | 2014-11-20 17:00 |  | 2014-08-28 08:00 | 2014-09-08 17:00 | 2014-08-28 08:00 | 2014-09-08 17:00 | 2014-08-28 08:00 | 2014-09-08 17:00 | 2014-11-10 08:00 | 2014-11-20 17:00 |  | PT_Normal |  |  |  |  | oWhh1l7FTbWLXJrZmv/feQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37290 | N | N | 65 | HARD LANDSCAPING |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 14 | CONCRETE MASON SK
%R | 501359 | 6359 | 124645 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2DRGL5115 | Excavation for Drainage line | 8177 | 40 | 0 | 200 | 0 | 419 | 419 | 200 | 251 | 0 | 251 |  |  |  | 2014-01-12 08:00 | 2014-02-09 17:00 |  | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-12 08:00 | 2014-02-09 17:00 |  | PT_Normal |  |  |  |  | LFcaOKUVTe60AQeBYNxHiw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37180 | N | N | 10 | DRAINAGE LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 419 | LABOR - CIVIL
%R | 501360 | 6359 | 124645 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2DRGL5120 | Laying of Drainage line | 8178 | 40 | 0 | 200 | 0 | 265.2 | 265.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-19 08:00 | 2014-02-17 17:00 |  | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 |  | PT_Normal |  |  |  |  | rcH6FP2SS7erkn9FmpknXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37180 | N | N | 10 | DRAINAGE LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 265.2 | LABOR- SUBCONTRACTOR
%R | 501361 | 6359 | 124645 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2DRGL5125 | Testing of Drainage line | 8178 | 40 | 0 | 200 | 0 | 134.4 | 134.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-27 08:00 | 2014-02-25 17:00 |  | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 |  | PT_Normal |  |  |  |  | jPFFvXh9QzyrHkhQA/MejA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37180 | N | N | 10 | DRAINAGE LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 501362 | 6359 | 124645 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2DRGL5130 | Backfilling Drainage line | 8177 | 40 | 0 | 120 | 0 | 315 | 315 | 120 | 248.9997 | 0 | 248.9997 |  |  |  | 2014-02-15 08:00 | 2014-03-03 17:00 |  | 2014-02-08 08:00 | 2014-02-25 17:00 | 2014-02-08 08:00 | 2014-02-25 17:00 | 2014-02-08 08:00 | 2014-02-25 17:00 | 2014-02-15 08:00 | 2014-03-03 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37180 | N | N | 10 | DRAINAGE LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 315 | LABOR - CIVIL
%R | 501363 | 6359 | 124646 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2STGL5235 | Excavation for Street lighting | 8177 | 0 | 0 | 200 | 0 | 69 | 69 | 200 | 51 | 0 | 51 |  |  |  | 2014-04-19 08:00 | 2014-05-17 17:00 |  | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 |  | PT_Normal |  |  |  |  | mdGQh+H4RfeiZ2V94fwtdw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37230 | N | N | 35 | STREET LIGHTING |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 69 | LABOR - CIVIL
%R | 501364 | 6359 | 124646 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2STGL5240 | Construction of Duct Banks | 8178 | 0 | 0 | 200 | 0 | 1494 | 1494 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-24 08:00 | 2014-05-22 17:00 |  | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 |  | PT_Normal |  |  |  |  | 7EKRi0shSEaj2Kbs6fn3ww |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37230 | N | N | 35 | STREET LIGHTING |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1494 | LABOR- SUBCONTRACTOR
%R | 501365 | 6359 | 124646 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2STGL5245 | Construction of Foundation | 8172 | 0 | 0 | 200 | 0 | 630 | 630 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-24 08:00 | 2014-05-22 17:00 |  | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 |  | PT_Normal |  |  |  |  | iKUsqWSkTeypWWUg/D+biw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37230 | N | N | 35 | STREET LIGHTING |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 630 | MANHOLES SK
%R | 501366 | 6359 | 124646 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2STGL5250 | Backfilling Street Lighting | 8177 | 0 | 0 | 200 | 0 | 122 | 122 | 200 | 110 | 0 | 110 |  |  |  | 2014-04-30 08:00 | 2014-05-28 17:00 |  | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 |  | PT_Normal |  |  |  |  | HwAatu9mSDSfG9Zp4Ge49g |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37230 | N | N | 35 | STREET LIGHTING |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 122 | LABOR - CIVIL
%R | 501367 | 6359 | 124646 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2STGL5255 | Installation of light Post | 8178 | 672 | 120 | 200 | 0 | 216 | 216 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-21 08:00 | 2014-09-18 17:00 |  | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-08-21 08:00 | 2014-09-18 17:00 |  | PT_Normal |  |  |  |  | aG6i+k1xS5qKPfCTGlgNvg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37230 | N | N | 35 | STREET LIGHTING |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 216 | LABOR- SUBCONTRACTOR
%R | 501368 | 6359 | 124646 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2STGL5260 | Electrical Works | 8178 | 512 | 120 | 200 | 0 | 1039.6 | 1039.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-27 17:00 |  | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-08-30 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | cfgp1Sx3S7aC2fhmqv5jEw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37230 | N | N | 35 | STREET LIGHTING |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1039.6 | LABOR- SUBCONTRACTOR
%R | 501369 | 6359 | 124647 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2WSGL5155 | Excavation for water line | 8177 | 0 | 0 | 200 | 0 | 425 | 425 | 200 | 251 | 0 | 251 |  |  |  | 2014-02-26 08:00 | 2014-03-26 17:00 |  | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 |  | PT_Normal |  |  |  |  | AAhhTMU9QAyXVN463GGSSg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37200 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 212.5 | LABOR - CIVIL
%R | 501370 | 6359 | 124647 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2WSGL5160 | Laying of water line | 8178 | 0 | 0 | 200 | 0 | 319.2 | 319.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-04 08:00 | 2014-04-01 17:00 |  | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 |  | PT_Normal |  |  |  |  | Qpulw2VcSLy/Xyqyjtx6fw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37200 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 319.2 | LABOR- SUBCONTRACTOR
%R | 501371 | 6359 | 124647 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2WSGL5165 | Testing of potable water line | 8178 | 0 | 0 | 200 | 0 | 100.8 | 100.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-10 08:00 | 2014-04-07 17:00 |  | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 |  | PT_Normal |  |  |  |  | EZUiqFktQhGZ5qz+rIFLFw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37200 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 100.8 | LABOR- SUBCONTRACTOR
%R | 501372 | 6359 | 124647 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2WSGL5170 | Backfilling potable water line | 8177 | 0 | 0 | 200 | 0 | 347 | 347 | 200 | 275 | 0 | 275 |  |  |  | 2014-03-16 08:00 | 2014-04-13 17:00 |  | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 |  | PT_Normal |  |  |  |  | aNdskWD/RoC6M2mYMxlyWQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37200 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 347 | LABOR - CIVIL
%R | 501373 | 6359 | 124647 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2WSGL5175 | Construction of valve chambers & Thrust Blocks | 8172 | 232 | 0 | 200 | 0 | 88 | 88 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-24 08:00 | 2014-05-22 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 |  | PT_Normal |  |  |  |  | hPvwgsgyQSKzJfoLy3j3Bg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37200 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 88 | MANHOLES SK
%R | 501374 | 6359 | 124647 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2WSGL5180 | Installation of meter ,Accessories & Connection | 8178 | 232 | 56 | 160 | 0 | 50.4 | 50.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-24 08:00 | 2014-06-15 17:00 |  | 2014-04-20 08:00 | 2014-05-12 17:00 | 2014-04-20 08:00 | 2014-05-12 17:00 | 2014-04-20 08:00 | 2014-05-12 17:00 | 2014-05-24 08:00 | 2014-06-15 17:00 |  | PT_Normal |  |  |  |  | V7TLqPilSL66O5kdQNB9eQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37200 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 501375 | 6359 | 124648 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2ELGL5215 | Excavation Cable Trenches & Duct Banks | 8177 | 0 | 0 | 200 | 0 | 2772 | 2772 | 200 | 876 | 0 | 876 |  |  |  | 2014-04-19 08:00 | 2014-05-17 17:00 |  | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 |  | PT_Normal |  |  |  |  | v805cGFCRL+z0AJk6u61Gw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37220 | N | N | 30 | ELECTRICAL LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 2772 | LABOR - CIVIL
%R | 501376 | 6359 | 124648 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2ELGL5220 | Laying of electrical cables | 8178 | 24 | 0 | 200 | 0 | 4487.2 | 4487.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-28 08:00 | 2014-05-26 17:00 |  | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-28 08:00 | 2014-05-26 17:00 |  | PT_Normal |  |  |  |  | z8O0Kxk6SfOX9KuBaHvuGg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37220 | N | N | 30 | ELECTRICAL LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 4487.2 | LABOR- SUBCONTRACTOR
%R | 501377 | 6359 | 124648 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2ELGL5225 | Backfilling Electrical trench | 8177 | 24 | 0 | 200 | 0 | 1862 | 1862 | 200 | 1100 | 0 | 1100 |  |  |  | 2014-05-06 08:00 | 2014-06-03 17:00 |  | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-06 08:00 | 2014-06-03 17:00 |  | PT_Normal |  |  |  |  | mnPJBoQISmumwCVxrUcy+A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37220 | N | N | 30 | ELECTRICAL LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1862 | LABOR - CIVIL
%R | 501378 | 6359 | 124648 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2ELGL5230 | Construction of Submain Board & Feeder Pillar | 8165 | 512 | 0 | 200 | 0 | 276 | 276 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-28 08:00 | 2014-08-28 17:00 |  | 2014-05-14 08:00 | 2014-06-11 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 | 2014-07-28 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | hfAnUBTjRiu1N0S8oumAZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37220 | N | N | 30 | ELECTRICAL LINES |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 276 | STEEL FIXERS SK
%R | 501379 | 6359 | 124649 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2PSGL7000 | Excavation | 8177 | 336 | 40 | 120 | 0 | 163 | 163 | 120 | 90.9998 | 0 | 90.9998 |  |  |  | 2014-09-17 08:00 | 2014-10-04 17:00 |  | 2014-07-27 08:00 | 2014-08-16 17:00 | 2014-07-27 08:00 | 2014-08-16 17:00 | 2014-07-27 08:00 | 2014-08-16 17:00 | 2014-09-17 08:00 | 2014-10-04 17:00 |  | PT_Normal |  |  |  |  | uHx95mxeQK2s5+llJHENLg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37280 | N | N | 60 | PARKING SHED |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 163 | LABOR - CIVIL
%R | 501380 | 6359 | 124649 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2PSGL7005 | Foundation casting | 8165 | 296 | 0 | 120 | 0 | 302 | 302 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-23 08:00 | 2014-10-12 17:00 |  | 2014-08-11 08:00 | 2014-08-27 17:00 | 2014-08-11 08:00 | 2014-08-27 17:00 | 2014-08-11 08:00 | 2014-08-27 17:00 | 2014-09-23 08:00 | 2014-10-12 17:00 |  | PT_Normal |  |  |  |  | ZUs0O1R5SEW+Mnkx9A7eYQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37280 | N | N | 60 | PARKING SHED |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 302 | STEEL FIXERS SK
%R | 501381 | 6359 | 124649 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2PSGL7010 | Column, Frame& Fabrics Erection | 8178 | 296 | 0 | 200 | 0 | 314 | 314 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-05 08:00 | 2014-11-04 17:00 |  | 2014-08-23 08:00 | 2014-09-20 17:00 | 2014-08-23 08:00 | 2014-09-20 17:00 | 2014-08-23 08:00 | 2014-09-20 17:00 | 2014-10-05 08:00 | 2014-11-04 17:00 |  | PT_Normal |  |  |  |  | MHKiAsjDQXq3Qcw9CabkWA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37280 | N | N | 60 | PARKING SHED |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 314 | LABOR- SUBCONTRACTOR
%R | 501382 | 6359 | 124649 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ2PSGL7015 | Electrical Works-Parking Shed | 8178 | 296 | 120 | 200 | 0 | 51.6 | 51.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-13 08:00 | 2014-11-10 17:00 |  | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-10-13 08:00 | 2014-11-10 17:00 |  | PT_Normal |  |  |  |  | qzjo1xvXTGStkaCeT8YOiA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37280 | N | N | 60 | PARKING SHED |  | 124636 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 51.6 | LABOR- SUBCONTRACTOR
%R | 501383 | 6359 | 124652 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3DRGL5115 | Excavation for Drainage line | 8177 | 80 | 0 | 200 | 0 | 419 | 419 | 200 | 251 | 0 | 251 |  |  |  | 2014-03-01 08:00 | 2014-03-29 17:00 |  | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-03-01 08:00 | 2014-03-29 17:00 |  | PT_Normal |  |  |  |  | lvvPTQ0ZRNu/eR6q7CbvIQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37330 | N | N | 10 | DRAINAGE LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 209.5 | LABOR - CIVIL
%R | 501384 | 6359 | 124652 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3DRGL5120 | Laying of Drainage line | 8178 | 80 | 0 | 200 | 0 | 265.2 | 265.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-04-05 17:00 |  | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-03-08 08:00 | 2014-04-05 17:00 |  | PT_Normal |  |  |  |  | S9HumtawTrWtAlOfK0W/NQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37330 | N | N | 10 | DRAINAGE LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 132.6 | LABOR- SUBCONTRACTOR
%R | 501385 | 6359 | 124652 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3DRGL5125 | Testing of Drainage line | 8178 | 80 | 0 | 200 | 0 | 134.4 | 134.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-16 08:00 | 2014-04-13 17:00 |  | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 |  | PT_Normal |  |  |  |  | jN3gXtkwRj+MnbcYitMaHw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37330 | N | N | 10 | DRAINAGE LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 501386 | 6359 | 124652 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3DRGL5130 | Backfilling Drainage line | 8177 | 80 | 0 | 120 | 0 | 315 | 315 | 120 | 248.9997 | 0 | 248.9997 |  |  |  | 2014-04-02 08:00 | 2014-04-19 17:00 |  | 2014-03-22 08:00 | 2014-04-07 17:00 | 2014-03-22 08:00 | 2014-04-07 17:00 | 2014-03-22 08:00 | 2014-04-07 17:00 | 2014-04-02 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | clDGzx0MRiCPbVfDyMRwcw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37330 | N | N | 10 | DRAINAGE LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 315 | LABOR - CIVIL
%R | 501387 | 6359 | 124653 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3FFGL5185 | Excavation for firefighting line | 8177 | 0 | 0 | 200 | 0 | 190 | 190 | 200 | 100 | 0 | 100 |  |  |  | 2014-05-07 08:00 | 2014-06-04 17:00 |  | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 |  | PT_Normal |  |  |  |  | h9U1Fc5cSZyGv2Psgh2e8Q |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37360 | N | N | 25 | FIREFIGHTING LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 190 | LABOR - CIVIL
%R | 501388 | 6359 | 124653 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3FFGL5190 | Laying of firefighting line | 8178 | 0 | 0 | 200 | 0 | 210 | 210 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-15 08:00 | 2014-06-12 17:00 |  | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 |  | PT_Normal |  |  |  |  | 9DXoB6P6TpykQzvasMbhNA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37360 | N | N | 25 | FIREFIGHTING LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 210 | LABOR- SUBCONTRACTOR
%R | 501389 | 6359 | 124653 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3FFGL5195 | Testing of firefighting line | 8178 | 0 | 0 | 200 | 0 | 50.4 | 50.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-21 08:00 | 2014-06-18 17:00 |  | 2014-05-21 08:00 | 2014-06-18 17:00 | 2014-05-21 08:00 | 2014-06-18 17:00 | 2014-05-21 08:00 | 2014-06-18 17:00 | 2014-05-21 08:00 | 2014-06-18 17:00 |  | PT_Normal |  |  |  |  | Iiq4Sk4CSv+SDweqlmUcMg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37360 | N | N | 25 | FIREFIGHTING LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 501390 | 6359 | 124653 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3FFGL5200 | Backfilling firefighting line | 8177 | 0 | 0 | 200 | 0 | 311 | 311 | 200 | 275 | 0 | 275 |  |  |  | 2014-05-27 08:00 | 2014-06-24 17:00 |  | 2014-05-27 08:00 | 2014-06-24 17:00 | 2014-05-27 08:00 | 2014-06-24 17:00 | 2014-05-27 08:00 | 2014-06-24 17:00 | 2014-05-27 08:00 | 2014-06-24 17:00 |  | PT_Normal |  |  |  |  | hmyn6TCJS06D5iCBzI+a6Q |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37360 | N | N | 25 | FIREFIGHTING LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 311 | LABOR - CIVIL
%R | 501391 | 6359 | 124653 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3FFGL5205 | Construction of valve chambers & Thrust Blocks | 8165 | 176 | 0 | 200 | 0 | 266 | 266 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-28 08:00 | 2014-07-26 17:00 |  | 2014-06-02 08:00 | 2014-06-30 17:00 | 2014-06-02 08:00 | 2014-06-30 17:00 | 2014-06-02 08:00 | 2014-06-30 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 |  | PT_Normal |  |  |  |  | 0PoErh9kT3iO76VCqCizgg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37360 | N | N | 25 | FIREFIGHTING LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 266 | STEEL FIXERS SK
%R | 501392 | 6359 | 124653 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3FFGL5210 | Connection with existing Firewater System | 8178 | 176 | 120 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-03 08:00 | 2014-07-31 17:00 |  | 2014-06-08 08:00 | 2014-07-06 17:00 | 2014-06-08 08:00 | 2014-07-06 17:00 | 2014-06-08 08:00 | 2014-07-06 17:00 | 2014-07-03 08:00 | 2014-07-31 17:00 |  | PT_Normal |  |  |  |  | mEXPLDwZS1mvrUuk2cdygg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37360 | N | N | 25 | FIREFIGHTING LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 84 | LABOR- SUBCONTRACTOR
%R | 501393 | 6359 | 124654 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3BWGL5315 | Construction of Boundary Wall (Ht-3m) | 8165 | 360 | 0 | 200 | 0 | 196 | 196 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-23 08:00 | 2014-09-20 17:00 |  | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-08-23 08:00 | 2014-09-20 17:00 |  | PT_Normal |  |  |  |  | sLGn0q76RZabE1WFLWqcfA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37410 | N | N | 50 | BOUNDARY WALL |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 196 | STEEL FIXERS SK
%R | 501394 | 6359 | 124654 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 8178 | 360 | 0 | 200 | 0 | 14 | 14 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-08 08:00 | 2014-10-06 17:00 |  | 2014-07-14 08:00 | 2014-08-14 17:00 | 2014-07-14 08:00 | 2014-08-14 17:00 | 2014-07-14 08:00 | 2014-08-14 17:00 | 2014-09-08 08:00 | 2014-10-06 17:00 |  | PT_Normal |  |  |  |  | XSJxXBhrRzGeh0tB745uTg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37410 | N | N | 50 | BOUNDARY WALL |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 7 | LABOR- SUBCONTRACTOR
%R | 501395 | 6359 | 124654 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 8165 | 360 | 0 | 200 | 0 | 140 | 140 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-07 08:00 | 2014-11-06 17:00 |  | 2014-08-16 08:00 | 2014-09-13 17:00 | 2014-08-16 08:00 | 2014-09-13 17:00 | 2014-08-16 08:00 | 2014-09-13 17:00 | 2014-10-07 08:00 | 2014-11-06 17:00 |  | PT_Normal |  |  |  |  | iGq7HMEIQliYjp2yGWaOtQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37410 | N | N | 50 | BOUNDARY WALL |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 140 | STEEL FIXERS SK
%R | 501396 | 6359 | 124654 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 8165 | 464 | 120 | 200 | 0 | 140 | 140 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-05 08:00 | 2014-12-03 17:00 |  | 2014-08-27 08:00 | 2014-09-24 17:00 | 2014-08-27 08:00 | 2014-09-24 17:00 | 2014-08-27 08:00 | 2014-09-24 17:00 | 2014-11-05 08:00 | 2014-12-03 17:00 |  | PT_Normal |  |  |  |  | yJCgv+3SQJmfcDAGNhDT3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37410 | N | N | 50 | BOUNDARY WALL |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 140 | STEEL FIXERS SK
%R | 501397 | 6359 | 124655 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3SLGL7200 | Excavation | 8177 | 8 | 0 | 200 | 0 | 926 | 926 | 200 | 500 | 0 | 500 |  |  |  | 2014-09-10 08:00 | 2014-10-08 17:00 |  | 2014-09-09 08:00 | 2014-10-07 17:00 | 2014-09-09 08:00 | 2014-10-07 17:00 | 2014-09-09 08:00 | 2014-10-07 17:00 | 2014-09-10 08:00 | 2014-10-08 17:00 |  | PT_Normal |  |  |  |  | XJQov+rxTNewGl/zEZaghA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37450 | N | N | 70 | SOFT LANDSCAPING |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 926 | LABOR - CIVIL
%R | 501398 | 6359 | 124655 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3SLGL7205 | Sweet Soil Laying | 8178 | 8 | 0 | 200 | 0 | 4102 | 4102 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-22 08:00 | 2014-10-22 17:00 |  | 2014-09-21 08:00 | 2014-10-21 17:00 | 2014-09-21 08:00 | 2014-10-21 17:00 | 2014-09-21 08:00 | 2014-10-21 17:00 | 2014-09-22 08:00 | 2014-10-22 17:00 |  | PT_Normal |  |  |  |  | /BczF7XqSU+mHu8yfm2+LQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37450 | N | N | 70 | SOFT LANDSCAPING |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 2051 | LABOR- SUBCONTRACTOR
%R | 501399 | 6359 | 124655 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3SLGL7210 | Plantation works | 8178 | 88 | 88 | 200 | 0 | 728 | 728 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-10-02 08:00 | 2014-11-02 17:00 | 2014-10-02 08:00 | 2014-11-02 17:00 | 2014-10-02 08:00 | 2014-11-02 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | 6X27C5iNRDaEffbKC4nEkw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37450 | N | N | 70 | SOFT LANDSCAPING |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10; period 2: 2014-AP11 |  | 364 | LABOR- SUBCONTRACTOR
%R | 501400 | 6359 | 124656 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3TCGL5295 | Excavation Telecommunication trenches | 8177 | 0 | 0 | 160 | 0 | 356 | 356 | 160 | 200 | 0 | 200 |  |  |  | 2014-06-28 08:00 | 2014-07-20 17:00 |  | 2014-06-28 08:00 | 2014-07-20 17:00 | 2014-06-28 08:00 | 2014-07-20 17:00 | 2014-06-28 08:00 | 2014-07-20 17:00 | 2014-06-28 08:00 | 2014-07-20 17:00 |  | PT_Normal |  |  |  |  | Dz8I6abNSs2qgxiruLJr/g |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37400 | N | N | 45 | TELECOMMUNICATION LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 356 | LABOR - CIVIL
%R | 501401 | 6359 | 124656 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3TCGL5300 | Laying of cables | 8178 | 0 | 0 | 160 | 0 | 727.2 | 727.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-03 08:00 | 2014-07-26 17:00 |  | 2014-07-03 08:00 | 2014-07-26 17:00 | 2014-07-03 08:00 | 2014-07-26 17:00 | 2014-07-03 08:00 | 2014-07-26 17:00 | 2014-07-03 08:00 | 2014-07-26 17:00 |  | PT_Normal |  |  |  |  | EBzVE0IrTCKMv+psY2lfRw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37400 | N | N | 45 | TELECOMMUNICATION LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 727.2 | LABOR- SUBCONTRACTOR
%R | 501402 | 6359 | 124656 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3TCGL5305 | Backfilling telecommunication trench | 8177 | 0 | 0 | 160 | 0 | 286 | 286 | 160 | 220 | 0 | 220 |  |  |  | 2014-07-09 08:00 | 2014-07-31 17:00 |  | 2014-07-09 08:00 | 2014-07-31 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 |  | PT_Normal |  |  |  |  | zbHudxKcQPWZYIpD8TxDUQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37400 | N | N | 45 | TELECOMMUNICATION LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 286 | LABOR - CIVIL
%R | 501403 | 6359 | 124656 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3TCGL5310 | Connection & Installation | 8178 | 408 | 160 | 160 | 0 | 271.2 | 271.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-22 08:00 | 2014-10-16 17:00 |  | 2014-07-21 08:00 | 2014-08-16 17:00 | 2014-07-21 08:00 | 2014-08-16 17:00 | 2014-07-21 08:00 | 2014-08-16 17:00 | 2014-09-22 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | EDPyV2JJSGKoJsfwVHi56g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37400 | N | N | 45 | TELECOMMUNICATION LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 271.2 | LABOR- SUBCONTRACTOR
%R | 501404 | 6359 | 124657 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3SAGL5135 | Construction of manholes Drainage | 8177 | 552 | 80 | 200 | 0 | 6 | 6 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-10 08:00 | 2014-07-08 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 |  | PT_Normal |  |  |  |  | MR+UgQYDTKmvFu7B1HVdhA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37340 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 6 | LABOR - CIVIL
%R | 501405 | 6359 | 124657 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3SAGL5140 | Construction of soakaways | 8172 | 80 | 0 | 200 | 0 | 190 | 190 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-02 08:00 | 2014-04-30 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 |  | PT_Normal |  |  |  |  | jong2Tk1Q8GuIkx9fK8iKA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37340 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 190 | MANHOLES SK
%R | 501406 | 6359 | 124657 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3SAGL5145 | Construction of Road gullies | 8172 | 80 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-01 08:00 | 2014-05-29 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | pIEVvOn6QpeTeFcNYqSuSg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37340 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 176 | MANHOLES SK
%R | 501407 | 6359 | 124657 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3SAGL5150 | Connection with existing sewer manhole | 8177 | 352 | 352 | 160 | 0 | 6 | 6 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-09 08:00 | 2014-07-31 17:00 |  | 2014-05-19 08:00 | 2014-06-10 17:00 | 2014-05-19 08:00 | 2014-06-10 17:00 | 2014-05-19 08:00 | 2014-06-10 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 |  | PT_Normal |  |  |  |  | 3Visfvb5RvKgyvns5tNJkw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37340 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 6 | LABOR - CIVIL
%R | 501408 | 6359 | 124658 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3HDGL7035 | Construction of Wash Stone Boulders | 8170 | 8 | 0 | 200 | 0 | 22 | 22 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-27 17:00 |  | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-30 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | XRa7DcBCTnewoK+013aD9Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37440 | N | N | 65 | HARD LANDSCAPING |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 22 | TILE MASON SK
%R | 501409 | 6359 | 124658 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3HDGL7040 | Construction of Speed Humps | 8167 | 248 | 248 | 80 | 0 | 14 | 14 | 80 | 0 | 0 | 0 |  |  |  | 2014-11-22 08:00 | 2014-12-02 17:00 |  | 2014-10-16 08:00 | 2014-10-27 17:00 | 2014-10-16 08:00 | 2014-10-27 17:00 | 2014-10-16 08:00 | 2014-10-27 17:00 | 2014-11-22 08:00 | 2014-12-02 17:00 |  | PT_Normal |  |  |  |  | EoYpFrzrQb6puoVphQrp2w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37440 | N | N | 65 | HARD LANDSCAPING |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 14 | CONCRETE MASON SK
%R | 501410 | 6359 | 124658 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3HDGL7020 | Precast Concrete Kerbs works | 8173 | 8 | 0 | 160 | 0 | 800 | 800 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-06 08:00 | 2014-08-28 17:00 |  | 2014-08-05 08:00 | 2014-08-27 17:00 | 2014-08-05 08:00 | 2014-08-27 17:00 | 2014-08-05 08:00 | 2014-08-27 17:00 | 2014-08-06 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | tqjRtKvaQU+DrbQpL9iS9A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37440 | N | N | 65 | HARD LANDSCAPING |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 800 | KERBSTONE MASON SK
%R | 501411 | 6359 | 124658 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3HDGL7025 | Interlocking for Walkways | 8174 | 8 | 0 | 200 | 0 | 814 | 814 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | ZMBrPJZxQjqhlOsoxFKg3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37440 | N | N | 65 | HARD LANDSCAPING |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 814 | INTERLOCK MASON SK
%R | 501412 | 6359 | 124658 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3HDGL7030 | Construction of Retaining wall | 8165 | 8 | 0 | 200 | 0 | 3340 | 3340 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-27 17:00 |  | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-30 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | aIa+f6BRRoaF1u6m/8y+xA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37440 | N | N | 65 | HARD LANDSCAPING |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 3340 | STEEL FIXERS SK
%R | 501413 | 6359 | 124659 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3PSGL7000 | Excavation | 8177 | 216 | 40 | 120 | 0 | 163 | 163 | 120 | 90.9998 | 0 | 90.9998 |  |  |  | 2014-10-19 08:00 | 2014-11-04 17:00 |  | 2014-09-15 08:00 | 2014-10-01 17:00 | 2014-09-15 08:00 | 2014-10-01 17:00 | 2014-09-15 08:00 | 2014-10-01 17:00 | 2014-10-19 08:00 | 2014-11-04 17:00 |  | PT_Normal |  |  |  |  | KOFZSF53Q9mB7NTQgQsqHA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37430 | N | N | 60 | PARKING SHED |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 163 | LABOR - CIVIL
%R | 501414 | 6359 | 124659 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3PSGL7005 | Foundation casting | 8165 | 176 | 0 | 120 | 0 | 302 | 302 | 120 | 0 | 0 | 0 |  |  |  | 2014-10-25 08:00 | 2014-11-10 17:00 |  | 2014-09-27 08:00 | 2014-10-15 17:00 | 2014-09-27 08:00 | 2014-10-15 17:00 | 2014-09-27 08:00 | 2014-10-15 17:00 | 2014-10-25 08:00 | 2014-11-10 17:00 |  | PT_Normal |  |  |  |  | uWSw/Cm5Q2CLMeDJhWraOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37430 | N | N | 60 | PARKING SHED |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 302 | STEEL FIXERS SK
%R | 501415 | 6359 | 124659 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3PSGL7015 | Electrical Works-Parking Shed | 8178 | 176 | 128 | 200 | 0 | 51.6 | 51.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-11 08:00 | 2014-12-09 17:00 |  | 2014-10-16 08:00 | 2014-11-13 17:00 | 2014-10-16 08:00 | 2014-11-13 17:00 | 2014-10-16 08:00 | 2014-11-13 17:00 | 2014-11-11 08:00 | 2014-12-09 17:00 |  | PT_Normal |  |  |  |  | TbHNb3FmTYWoejocSzNpPw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37430 | N | N | 60 | PARKING SHED |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 51.6 | LABOR- SUBCONTRACTOR
%R | 501416 | 6359 | 124659 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3PSGL7010 | Column, Frame& Fabrics Erection | 8178 | 176 | 0 | 200 | 0 | 314 | 314 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-05 08:00 | 2014-12-03 17:00 |  | 2014-10-08 08:00 | 2014-11-08 17:00 | 2014-10-08 08:00 | 2014-11-08 17:00 | 2014-10-08 08:00 | 2014-11-08 17:00 | 2014-11-05 08:00 | 2014-12-03 17:00 |  | PT_Normal |  |  |  |  | d4UIpTvdTUmtkhebIbKOVA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37430 | N | N | 60 | PARKING SHED |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10; period 2: 2014-AP11 |  | 157 | LABOR- SUBCONTRACTOR
%R | 501417 | 6359 | 124660 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3ELGL5215 | Excavation Cable Trenches & Duct Banks | 8177 | 0 | 0 | 200 | 0 | 2772 | 2772 | 200 | 876 | 0 | 876 |  |  |  | 2014-06-04 08:00 | 2014-07-02 17:00 |  | 2014-06-04 08:00 | 2014-07-02 17:00 | 2014-06-04 08:00 | 2014-07-02 17:00 | 2014-06-04 08:00 | 2014-07-02 17:00 | 2014-06-04 08:00 | 2014-07-02 17:00 |  | PT_Normal |  |  |  |  | R0QTjJtDRviR2t0IFTvMxg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37370 | N | N | 30 | ELECTRICAL LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 2772 | LABOR - CIVIL
%R | 501418 | 6359 | 124660 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3ELGL5220 | Laying of electrical cables | 8178 | 24 | 0 | 200 | 0 | 4487.2 | 4487.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-14 08:00 | 2014-07-12 17:00 |  | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 |  | PT_Normal |  |  |  |  | RW3sIsg3SfWBkI+Rfhn1vw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37370 | N | N | 30 | ELECTRICAL LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 4487.2 | LABOR- SUBCONTRACTOR
%R | 501419 | 6359 | 124660 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3ELGL5225 | Backfilling Electrical trench | 8177 | 24 | 0 | 200 | 0 | 1862 | 1862 | 200 | 1100 | 0 | 1100 |  |  |  | 2014-06-22 08:00 | 2014-07-20 17:00 |  | 2014-06-18 08:00 | 2014-07-16 17:00 | 2014-06-18 08:00 | 2014-07-16 17:00 | 2014-06-18 08:00 | 2014-07-16 17:00 | 2014-06-22 08:00 | 2014-07-20 17:00 |  | PT_Normal |  |  |  |  | raSGV3QZQxqjcey4xxgXyA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:52 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37370 | N | N | 30 | ELECTRICAL LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1862 | LABOR - CIVIL
%R | 501420 | 6359 | 124660 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3ELGL5230 | Construction of Submain Board & Feeder Pillar | 8165 | 392 | 0 | 200 | 0 | 276 | 276 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-27 17:00 |  | 2014-06-30 08:00 | 2014-07-28 17:00 | 2014-06-30 08:00 | 2014-07-28 17:00 | 2014-06-30 08:00 | 2014-07-28 17:00 | 2014-08-30 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | uMuL6/TXSqiSPbya4/o94g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37370 | N | N | 30 | ELECTRICAL LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 276 | STEEL FIXERS SK
%R | 501421 | 6359 | 124661 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3WSGL5155 | Excavation for water line | 8177 | 0 | 0 | 200 | 0 | 425 | 425 | 200 | 251 | 0 | 251 |  |  |  | 2014-04-14 08:00 | 2014-05-12 17:00 |  | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 |  | PT_Normal |  |  |  |  | 4V5IdPdLTbOHnPukpDOR+Q |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37350 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 425 | LABOR - CIVIL
%R | 501422 | 6359 | 124661 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3WSGL5160 | Laying of water line | 8178 | 0 | 0 | 200 | 0 | 319.2 | 319.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | noc+8JKVSU2GfL7n/KuioA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37350 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 319.2 | LABOR- SUBCONTRACTOR
%R | 501423 | 6359 | 124661 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3WSGL5165 | Testing of potable water line | 8178 | 0 | 0 | 200 | 0 | 100.8 | 100.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-26 08:00 | 2014-05-24 17:00 |  | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 |  | PT_Normal |  |  |  |  | lQpxvxpRTR67g6vtmPaHXQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37350 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 100.8 | LABOR- SUBCONTRACTOR
%R | 501424 | 6359 | 124661 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3WSGL5170 | Backfilling potable water line | 8177 | 0 | 0 | 200 | 0 | 347 | 347 | 200 | 275 | 0 | 275 |  |  |  | 2014-05-01 08:00 | 2014-05-29 17:00 |  | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | EiM9Xt8oR7e3k4w1WjnsXg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37350 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 347 | LABOR - CIVIL
%R | 501425 | 6359 | 124661 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3WSGL5175 | Construction of valve chambers & Thrust Blocks | 8172 | 232 | 0 | 200 | 0 | 88 | 88 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-10 08:00 | 2014-07-08 17:00 |  | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 |  | PT_Normal |  |  |  |  | EHo/GB/fQ9qp1HtB6RV0zg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37350 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 88 | MANHOLES SK
%R | 501426 | 6359 | 124661 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3WSGL5180 | Installation of meter ,Accessories & Connection | 8178 | 232 | 56 | 160 | 0 | 50.4 | 50.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-09 08:00 | 2014-07-31 17:00 |  | 2014-06-05 08:00 | 2014-06-28 17:00 | 2014-06-05 08:00 | 2014-06-28 17:00 | 2014-06-05 08:00 | 2014-06-28 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 |  | PT_Normal |  |  |  |  | tzhcWy0ERKumv4cS0vcFVA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37350 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 501427 | 6359 | 124662 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3IRGL5265 | Excavation for irrigation line | 8177 | 56 | 0 | 200 | 0 | 998 | 998 | 200 | 500 | 0 | 500 |  |  |  | 2014-07-26 08:00 | 2014-08-26 17:00 |  | 2014-07-17 08:00 | 2014-08-18 17:00 | 2014-07-17 08:00 | 2014-08-18 17:00 | 2014-07-17 08:00 | 2014-08-18 17:00 | 2014-07-26 08:00 | 2014-08-26 17:00 |  | PT_Normal |  |  |  |  | aJnkjm9cRJ+KvPJhn667cw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37390 | N | N | 40 | IRRIGATION LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 499 | LABOR - CIVIL
%R | 501428 | 6359 | 124662 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3IRGL5270 | Laying of irrigationline | 8178 | 56 | 0 | 200 | 0 | 352.8 | 352.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-31 08:00 | 2014-09-01 17:00 |  | 2014-07-23 08:00 | 2014-08-24 17:00 | 2014-07-23 08:00 | 2014-08-24 17:00 | 2014-07-23 08:00 | 2014-08-24 17:00 | 2014-07-31 08:00 | 2014-09-01 17:00 |  | PT_Normal |  |  |  |  | sdIZFzTSTJ2M3UgmtTrOpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37390 | N | N | 40 | IRRIGATION LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 176.4 | LABOR- SUBCONTRACTOR
%R | 501429 | 6359 | 124662 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3IRGL5275 | Testing of irrigation line | 8178 | 56 | 0 | 200 | 0 | 285.6 | 285.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-10 08:00 | 2014-09-07 17:00 |  | 2014-07-29 08:00 | 2014-08-30 17:00 | 2014-07-29 08:00 | 2014-08-30 17:00 | 2014-07-29 08:00 | 2014-08-30 17:00 | 2014-08-10 08:00 | 2014-09-07 17:00 |  | PT_Normal |  |  |  |  | 3MfELBb4SS6YOJY9Rt8LLg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37390 | N | N | 40 | IRRIGATION LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 142.8 | LABOR- SUBCONTRACTOR
%R | 501430 | 6359 | 124662 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3IRGL5280 | Backfilling irrigation line | 8177 | 56 | 0 | 200 | 0 | 706 | 706 | 200 | 550 | 0 | 550 |  |  |  | 2014-08-16 08:00 | 2014-09-13 17:00 |  | 2014-08-07 08:00 | 2014-09-04 17:00 | 2014-08-07 08:00 | 2014-09-04 17:00 | 2014-08-07 08:00 | 2014-09-04 17:00 | 2014-08-16 08:00 | 2014-09-13 17:00 |  | PT_Normal |  |  |  |  | L0MsyNNzQoi+Va2XqjwVvg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37390 | N | N | 40 | IRRIGATION LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 706 | LABOR - CIVIL
%R | 501431 | 6359 | 124662 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3IRGL5285 | Construction of Thrust Blocks,Pull boxes | 8178 | 96 | 0 | 200 | 0 | 149.6 | 149.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-02 08:00 | 2014-09-30 17:00 |  | 2014-08-19 08:00 | 2014-09-16 17:00 | 2014-08-19 08:00 | 2014-09-16 17:00 | 2014-08-19 08:00 | 2014-09-16 17:00 | 2014-09-02 08:00 | 2014-09-30 17:00 |  | PT_Normal |  |  |  |  | 7Mpd+Eh7TPGHIav79Ox++g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37390 | N | N | 40 | IRRIGATION LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 149.6 | LABOR- SUBCONTRACTOR
%R | 501432 | 6359 | 124662 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3IRGL5290 | Irrigation Fittings (Nozzle,Values) | 8178 | 96 | 88 | 200 | 0 | 352.8 | 352.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-10-08 17:00 |  | 2014-08-27 08:00 | 2014-09-24 17:00 | 2014-08-27 08:00 | 2014-09-24 17:00 | 2014-08-27 08:00 | 2014-09-24 17:00 | 2014-09-10 08:00 | 2014-10-08 17:00 |  | PT_Normal |  |  |  |  | 7pcqCFO+T3G+3yL3genhrw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37390 | N | N | 40 | IRRIGATION LINES |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 352.8 | LABOR- SUBCONTRACTOR
%R | 501433 | 6359 | 124663 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3STGL5235 | Excavation for Street lighting | 8177 | 0 | 0 | 200 | 0 | 69 | 69 | 200 | 51 | 0 | 51 |  |  |  | 2014-06-04 08:00 | 2014-07-02 17:00 |  | 2014-06-04 08:00 | 2014-07-02 17:00 | 2014-06-04 08:00 | 2014-07-02 17:00 | 2014-06-04 08:00 | 2014-07-02 17:00 | 2014-06-04 08:00 | 2014-07-02 17:00 |  | PT_Normal |  |  |  |  | /6klv9b+TJ+ZlvCep/vUmw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37380 | N | N | 35 | STREET LIGHTING |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 69 | LABOR - CIVIL
%R | 501434 | 6359 | 124663 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3STGL5240 | Construction of Duct Banks | 8178 | 0 | 0 | 200 | 0 | 1494 | 1494 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-10 08:00 | 2014-07-08 17:00 |  | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 |  | PT_Normal |  |  |  |  | YwW7cqFzQD60qHvMbj73tQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37380 | N | N | 35 | STREET LIGHTING |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1494 | LABOR- SUBCONTRACTOR
%R | 501435 | 6359 | 124663 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3STGL5245 | Construction of Foundation | 8172 | 0 | 0 | 200 | 0 | 630 | 630 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-10 08:00 | 2014-07-08 17:00 |  | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 |  | PT_Normal |  |  |  |  | ygD/ZkCsRPGfyoYIf9ZA4Q |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37380 | N | N | 35 | STREET LIGHTING |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 630 | MANHOLES SK
%R | 501436 | 6359 | 124663 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3STGL5250 | Backfilling Street Lighting | 8177 | 0 | 0 | 200 | 0 | 122 | 122 | 200 | 110 | 0 | 110 |  |  |  | 2014-06-16 08:00 | 2014-07-14 17:00 |  | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 |  | PT_Normal |  |  |  |  | HacYRWkNR9mmmCx5Ndobwg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37380 | N | N | 35 | STREET LIGHTING |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 122 | LABOR - CIVIL
%R | 501437 | 6359 | 124663 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3STGL5255 | Installation of light Post | 8178 | 552 | 120 | 200 | 0 | 216 | 216 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-20 08:00 | 2014-10-20 17:00 |  | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-09-20 08:00 | 2014-10-20 17:00 |  | PT_Normal |  |  |  |  | gR6TvYAlRM65pfdxUa12xw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37380 | N | N | 35 | STREET LIGHTING |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 216 | LABOR- SUBCONTRACTOR
%R | 501438 | 6359 | 124663 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3STGL5260 | Electrical Works | 8178 | 392 | 120 | 200 | 0 | 1039.6 | 1039.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-28 08:00 | 2014-10-28 17:00 |  | 2014-07-29 08:00 | 2014-08-30 17:00 | 2014-07-29 08:00 | 2014-08-30 17:00 | 2014-07-29 08:00 | 2014-08-30 17:00 | 2014-09-28 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | ThoE0S2jS+GUlrNABkuc0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37380 | N | N | 35 | STREET LIGHTING |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 519.8 | LABOR- SUBCONTRACTOR
%R | 501439 | 6359 | 124664 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3RWGL6000 | Excavation & Earth Filling | 8177 | 0 | 0 | 80 | 0 | 1150 | 1150 | 80 | 400 | 0 | 400 |  |  |  | 2014-08-05 08:00 | 2014-08-16 17:00 |  | 2014-08-05 08:00 | 2014-08-16 17:00 | 2014-08-05 08:00 | 2014-08-16 17:00 | 2014-08-05 08:00 | 2014-08-16 17:00 | 2014-08-05 08:00 | 2014-08-16 17:00 |  | PT_Normal |  |  |  |  | iHM5X2s5RKmei3nj1cw3Gg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37420 | N | N | 55 | ROAD WORKS |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1150 | LABOR - CIVIL
%R | 501440 | 6359 | 124664 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3RWGL6005 | Laying of Sub Grade | 8178 | 0 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-17 08:00 | 2014-09-14 17:00 |  | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 |  | PT_Normal |  |  |  |  | A0bpCPDuTwqohCopIxXHpA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37420 | N | N | 55 | ROAD WORKS |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 24 | LABOR- SUBCONTRACTOR
%R | 501441 | 6359 | 124664 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3RWGL6010 | Laying of Precast Kerbs | 8178 | 0 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-28 08:00 | 2014-09-25 17:00 |  | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 |  | PT_Normal |  |  |  |  | GM/jb1OxTQuTHKqkBX5zQA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37420 | N | N | 55 | ROAD WORKS |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 24 | LABOR- SUBCONTRACTOR
%R | 501442 | 6359 | 124664 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3RWGL6015 | Laying of Granular Sub Base Coarse | 8173 | 0 | 0 | 160 | 0 | 1828 | 1828 | 160 | 600 | 0 | 600 |  |  |  | 2014-09-09 08:00 | 2014-10-01 17:00 |  | 2014-09-09 08:00 | 2014-10-01 17:00 | 2014-09-09 08:00 | 2014-10-01 17:00 | 2014-09-09 08:00 | 2014-10-01 17:00 | 2014-09-09 08:00 | 2014-10-01 17:00 |  | PT_Normal |  |  |  |  | 5+lOcNJaSH2Qtacxa8kokg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37420 | N | N | 55 | ROAD WORKS |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 1828 | KERBSTONE MASON SK
%R | 501443 | 6359 | 124664 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3RWGL6020 | Laying of Road Base Asphalt Concrete | 8178 | 176 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-10-30 08:00 | 2014-11-04 17:00 |  | 2014-10-02 08:00 | 2014-10-07 17:00 | 2014-10-02 08:00 | 2014-10-07 17:00 | 2014-10-02 08:00 | 2014-10-07 17:00 | 2014-10-30 08:00 | 2014-11-04 17:00 |  | PT_Normal |  |  |  |  | naO1tBd2TnGr5yGCJRc3tQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37420 | N | N | 55 | ROAD WORKS |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 174 | LABOR- SUBCONTRACTOR
%R | 501444 | 6359 | 124664 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3RWGL6025 | Laying of Asphalt Wearing Coarse | 8178 | 248 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-11-16 08:00 | 2014-11-20 17:00 |  | 2014-10-08 08:00 | 2014-10-15 17:00 | 2014-10-08 08:00 | 2014-10-15 17:00 | 2014-10-08 08:00 | 2014-10-15 17:00 | 2014-11-16 08:00 | 2014-11-20 17:00 |  | PT_Normal |  |  |  |  | ak6cCh6rS2iJiU07UKTayw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37420 | N | N | 55 | ROAD WORKS |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 174 | LABOR- SUBCONTRACTOR
%R | 501445 | 6359 | 124664 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ3RWGL6030 | Traffic Signage & Road Marking | 8178 | 296 | 120 | 40 | 0 | 882 | 882 | 40 | 0 | 0 | 0 |  |  |  | 2014-11-29 08:00 | 2014-12-03 17:00 |  | 2014-10-16 08:00 | 2014-10-21 17:00 | 2014-10-16 08:00 | 2014-10-21 17:00 | 2014-10-16 08:00 | 2014-10-21 17:00 | 2014-11-29 08:00 | 2014-12-03 17:00 |  | PT_Normal |  |  |  |  | e/eTTzGBQyGbNE9KejY8YA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37420 | N | N | 55 | ROAD WORKS |  | 124651 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 882 | LABOR- SUBCONTRACTOR
%R | 501446 | 6359 | 124667 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4SAGL5135 | Construction of manholes Drainage | 8177 | 592 | 200 | 200 | 0 | 6 | 6 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-27 08:00 | 2014-08-27 17:00 |  | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-07-27 08:00 | 2014-08-27 17:00 |  | PT_Normal |  |  |  |  | lGVHi9uMR5KIsLpczjeq6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37490 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 6 | LABOR - CIVIL
%R | 501447 | 6359 | 124667 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4SAGL5140 | Construction of soakaways | 8172 | 120 | 0 | 200 | 0 | 190 | 190 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | hc8nRGtUS6S9Dzy/G3FpeQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37490 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 190 | MANHOLES SK
%R | 501448 | 6359 | 124667 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4SAGL5145 | Construction of Road gullies | 8172 | 120 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | vOdNn+CLRvyPs3dlK0xLpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37490 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 176 | MANHOLES SK
%R | 501449 | 6359 | 124667 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4SAGL5150 | Connection with existing sewer manhole | 8177 | 392 | 392 | 160 | 0 | 6 | 6 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-28 08:00 | 2014-09-20 17:00 |  | 2014-06-29 08:00 | 2014-07-21 17:00 | 2014-06-29 08:00 | 2014-07-21 17:00 | 2014-06-29 08:00 | 2014-07-21 17:00 | 2014-08-28 08:00 | 2014-09-20 17:00 |  | PT_Normal |  |  |  |  | 5WKHbcAjTymuerf7I8Di/Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37490 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 6 | LABOR - CIVIL
%R | 501450 | 6359 | 124668 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4IRGL5265 | Excavation for irrigation line | 8177 | 56 | 0 | 200 | 0 | 998 | 998 | 200 | 500 | 0 | 500 |  |  |  | 2014-09-14 08:00 | 2014-10-14 17:00 |  | 2014-09-06 08:00 | 2014-10-04 17:00 | 2014-09-06 08:00 | 2014-10-04 17:00 | 2014-09-06 08:00 | 2014-10-04 17:00 | 2014-09-14 08:00 | 2014-10-14 17:00 |  | PT_Normal |  |  |  |  | YoOMG7mcTSug3Kgp+aWMkQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37540 | N | N | 40 | IRRIGATION LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 998 | LABOR - CIVIL
%R | 501451 | 6359 | 124668 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4IRGL5270 | Laying of irrigationline | 8178 | 56 | 0 | 200 | 0 | 352.8 | 352.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-20 08:00 | 2014-10-20 17:00 |  | 2014-09-11 08:00 | 2014-10-12 17:00 | 2014-09-11 08:00 | 2014-10-12 17:00 | 2014-09-11 08:00 | 2014-10-12 17:00 | 2014-09-20 08:00 | 2014-10-20 17:00 |  | PT_Normal |  |  |  |  | ddreiPs0Rq6HhDxUrfw9/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37540 | N | N | 40 | IRRIGATION LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 176.4 | LABOR- SUBCONTRACTOR
%R | 501452 | 6359 | 124668 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4IRGL5275 | Testing of irrigation line | 8178 | 56 | 0 | 200 | 0 | 285.6 | 285.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-25 08:00 | 2014-10-26 17:00 |  | 2014-09-17 08:00 | 2014-10-18 17:00 | 2014-09-17 08:00 | 2014-10-18 17:00 | 2014-09-17 08:00 | 2014-10-18 17:00 | 2014-09-25 08:00 | 2014-10-26 17:00 |  | PT_Normal |  |  |  |  | 02kPtSYoThyKioNHhC1JMQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37540 | N | N | 40 | IRRIGATION LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 142.8 | LABOR- SUBCONTRACTOR
%R | 501453 | 6359 | 124668 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4IRGL5280 | Backfilling irrigation line | 8177 | 56 | 0 | 200 | 0 | 706 | 706 | 200 | 550 | 0 | 550 |  |  |  | 2014-10-01 08:00 | 2014-11-01 17:00 |  | 2014-09-23 08:00 | 2014-10-23 17:00 | 2014-09-23 08:00 | 2014-10-23 17:00 | 2014-09-23 08:00 | 2014-10-23 17:00 | 2014-10-01 08:00 | 2014-11-01 17:00 |  | PT_Normal |  |  |  |  | CvYoVpuCTvOHY0KytznT8w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37540 | N | N | 40 | IRRIGATION LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 353 | LABOR - CIVIL
%R | 501454 | 6359 | 124668 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4IRGL5285 | Construction of Thrust Blocks,Pull boxes | 8178 | 56 | 0 | 200 | 0 | 149.6 | 149.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-15 08:00 | 2014-11-12 17:00 |  | 2014-10-05 08:00 | 2014-11-04 17:00 | 2014-10-05 08:00 | 2014-11-04 17:00 | 2014-10-05 08:00 | 2014-11-04 17:00 | 2014-10-15 08:00 | 2014-11-12 17:00 |  | PT_Normal |  |  |  |  | ON6l+vtmSEGZJ1t1Ak2FKA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37540 | N | N | 40 | IRRIGATION LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 149.6 | LABOR- SUBCONTRACTOR
%R | 501455 | 6359 | 124668 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4IRGL5290 | Irrigation Fittings (Nozzle,Values) | 8178 | 56 | 56 | 200 | 0 | 352.8 | 352.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-23 08:00 | 2014-11-20 17:00 |  | 2014-10-15 08:00 | 2014-11-12 17:00 | 2014-10-15 08:00 | 2014-11-12 17:00 | 2014-10-15 08:00 | 2014-11-12 17:00 | 2014-10-23 08:00 | 2014-11-20 17:00 |  | PT_Normal |  |  |  |  | NxmEuAV0S7yhuguuRN2yBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37540 | N | N | 40 | IRRIGATION LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 352.8 | LABOR- SUBCONTRACTOR
%R | 501456 | 6359 | 124669 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4HDGL7020 | Precast Concrete Kerbs works | 8173 | 0 | 0 | 160 | 0 | 800 | 800 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-21 08:00 | 2014-10-15 17:00 |  | 2014-09-21 08:00 | 2014-10-15 17:00 | 2014-09-21 08:00 | 2014-10-15 17:00 | 2014-09-21 08:00 | 2014-10-15 17:00 | 2014-09-21 08:00 | 2014-10-15 17:00 |  | PT_Normal |  |  |  |  | o/EyLlNzTnig2pk9sQLPPA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37590 | N | N | 65 | HARD LANDSCAPING |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 800 | KERBSTONE MASON SK
%R | 501457 | 6359 | 124669 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4HDGL7025 | Interlocking for Walkways | 8174 | 0 | 0 | 200 | 0 | 814 | 814 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-02 08:00 | 2014-11-02 17:00 |  | 2014-10-02 08:00 | 2014-11-02 17:00 | 2014-10-02 08:00 | 2014-11-02 17:00 | 2014-10-02 08:00 | 2014-11-02 17:00 | 2014-10-02 08:00 | 2014-11-02 17:00 |  | PT_Normal |  |  |  |  | 06ccMBhpT4y4q8O/UfG9iA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37590 | N | N | 65 | HARD LANDSCAPING |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10; period 2: 2014-AP11 |  | 407 | INTERLOCK MASON SK
%R | 501458 | 6359 | 124669 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4HDGL7030 | Construction of Retaining wall | 8165 | 0 | 0 | 200 | 0 | 3340 | 3340 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-16 08:00 | 2014-11-13 17:00 |  | 2014-10-16 08:00 | 2014-11-13 17:00 | 2014-10-16 08:00 | 2014-11-13 17:00 | 2014-10-16 08:00 | 2014-11-13 17:00 | 2014-10-16 08:00 | 2014-11-13 17:00 |  | PT_Normal |  |  |  |  | 8iQzZ08MS8K6ta+MTQn3pQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37590 | N | N | 65 | HARD LANDSCAPING |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 3340 | STEEL FIXERS SK
%R | 501459 | 6359 | 124669 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4HDGL7035 | Construction of Wash Stone Boulders | 8170 | 0 | 0 | 200 | 0 | 22 | 22 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-16 08:00 | 2014-11-13 17:00 |  | 2014-10-16 08:00 | 2014-11-13 17:00 | 2014-10-16 08:00 | 2014-11-13 17:00 | 2014-10-16 08:00 | 2014-11-13 17:00 | 2014-10-16 08:00 | 2014-11-13 17:00 |  | PT_Normal |  |  |  |  | NUGcZsscRZ6zhP2FnLsZrw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37590 | N | N | 65 | HARD LANDSCAPING |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 22 | TILE MASON SK
%R | 501460 | 6359 | 124669 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4HDGL7040 | Construction of Speed Humps | 8167 | 0 | 0 | 80 | 0 | 14 | 14 | 80 | 0 | 0 | 0 |  |  |  | 2014-12-03 08:00 | 2014-12-14 17:00 |  | 2014-12-03 08:00 | 2014-12-14 17:00 | 2014-12-03 08:00 | 2014-12-14 17:00 | 2014-12-03 08:00 | 2014-12-14 17:00 | 2014-12-03 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | rw98JE4qQ2uJUagn4G/lFw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37590 | N | N | 65 | HARD LANDSCAPING |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP12 |  | 14 | CONCRETE MASON SK
%R | 501461 | 6359 | 124670 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4SLGL7210 | Plantation works | 8178 | 0 | 0 | 200 | 0 | 728 | 728 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-16 08:00 | 2014-12-14 17:00 |  | 2014-11-16 08:00 | 2014-12-14 17:00 | 2014-11-16 08:00 | 2014-12-14 17:00 | 2014-11-16 08:00 | 2014-12-14 17:00 | 2014-11-16 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | ZYsnQs6gQ3qfcAGgTmj62A |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37600 | N | N | 70 | SOFT LANDSCAPING |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 728 | LABOR- SUBCONTRACTOR
%R | 501462 | 6359 | 124670 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4SLGL7200 | Excavation for Landscaping | 8177 | 0 | 0 | 200 | 0 | 926 | 926 | 200 | 500 | 0 | 500 |  |  |  | 2014-10-23 08:00 | 2014-11-20 17:00 |  | 2014-10-23 08:00 | 2014-11-20 17:00 | 2014-10-23 08:00 | 2014-11-20 17:00 | 2014-10-23 08:00 | 2014-11-20 17:00 | 2014-10-23 08:00 | 2014-11-20 17:00 |  | PT_Normal |  |  |  |  | Dr9lqMcBQy2zghuteiYE2w |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37600 | N | N | 70 | SOFT LANDSCAPING |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 926 | LABOR - CIVIL
%R | 501463 | 6359 | 124670 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4SLGL7205 | Sweet Soil Laying | 8178 | 0 | 0 | 200 | 0 | 4102 | 4102 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-04 08:00 | 2014-12-02 17:00 |  | 2014-11-04 08:00 | 2014-12-02 17:00 | 2014-11-04 08:00 | 2014-12-02 17:00 | 2014-11-04 08:00 | 2014-12-02 17:00 | 2014-11-04 08:00 | 2014-12-02 17:00 |  | PT_Normal |  |  |  |  | DYfei8gyQjCmyVyxKF4JbQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37600 | N | N | 70 | SOFT LANDSCAPING |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 4102 | LABOR- SUBCONTRACTOR
%R | 501464 | 6359 | 124671 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4FFGL5185 | Excavation for firefighting line | 8177 | 0 | 0 | 200 | 0 | 190 | 190 | 200 | 100 | 0 | 100 |  |  |  | 2014-06-23 08:00 | 2014-07-21 17:00 |  | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 |  | PT_Normal |  |  |  |  | bpPsO8mMQLGiv+IbSoIOSQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37510 | N | N | 25 | FIREFIGHTING LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 190 | LABOR - CIVIL
%R | 501465 | 6359 | 124671 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4FFGL5190 | Laying of firefighting line | 8178 | 0 | 0 | 200 | 0 | 210 | 210 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-01 08:00 | 2014-07-29 17:00 |  | 2014-07-01 08:00 | 2014-07-29 17:00 | 2014-07-01 08:00 | 2014-07-29 17:00 | 2014-07-01 08:00 | 2014-07-29 17:00 | 2014-07-01 08:00 | 2014-07-29 17:00 |  | PT_Normal |  |  |  |  | RPyDG91YTU69lLFZSCxJQg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37510 | N | N | 25 | FIREFIGHTING LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 210 | LABOR- SUBCONTRACTOR
%R | 501466 | 6359 | 124671 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4FFGL5195 | Testing of firefighting line | 8178 | 0 | 0 | 200 | 0 | 50.4 | 50.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-07 08:00 | 2014-08-07 17:00 |  | 2014-07-07 08:00 | 2014-08-07 17:00 | 2014-07-07 08:00 | 2014-08-07 17:00 | 2014-07-07 08:00 | 2014-08-07 17:00 | 2014-07-07 08:00 | 2014-08-07 17:00 |  | PT_Normal |  |  |  |  | kgDz2SutScKCsBV6MXF6vw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37510 | N | N | 25 | FIREFIGHTING LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 25.2 | LABOR- SUBCONTRACTOR
%R | 501467 | 6359 | 124671 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4FFGL5200 | Backfilling firefighting line | 8177 | 0 | 0 | 200 | 0 | 311 | 311 | 200 | 275 | 0 | 275 |  |  |  | 2014-07-13 08:00 | 2014-08-13 17:00 |  | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 |  | PT_Normal |  |  |  |  | jINHCMhjTy2LQ1GmVFieEA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37510 | N | N | 25 | FIREFIGHTING LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 155.5 | LABOR - CIVIL
%R | 501468 | 6359 | 124671 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4FFGL5205 | Construction of valve chambers & Thrust Blocks | 8165 | 176 | 0 | 200 | 0 | 266 | 266 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-17 08:00 | 2014-09-14 17:00 |  | 2014-07-19 08:00 | 2014-08-19 17:00 | 2014-07-19 08:00 | 2014-08-19 17:00 | 2014-07-19 08:00 | 2014-08-19 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 |  | PT_Normal |  |  |  |  | wmY8Fbw0SoCHrMy4KaI06A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37510 | N | N | 25 | FIREFIGHTING LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 133 | STEEL FIXERS SK
%R | 501469 | 6359 | 124671 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4FFGL5210 | Connection with existing Firewater System | 8178 | 176 | 0 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-23 08:00 | 2014-09-20 17:00 |  | 2014-07-24 08:00 | 2014-08-25 17:00 | 2014-07-24 08:00 | 2014-08-25 17:00 | 2014-07-24 08:00 | 2014-08-25 17:00 | 2014-08-23 08:00 | 2014-09-20 17:00 |  | PT_Normal |  |  |  |  | U/dqGpjbSR2x90SM59ARnQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37510 | N | N | 25 | FIREFIGHTING LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 42 | LABOR- SUBCONTRACTOR
%R | 501470 | 6359 | 124672 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4WSGL5180 | Installation of meter ,Accessories & Connection | 8178 | 232 | 56 | 160 | 0 | 50.4 | 50.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-28 08:00 | 2014-09-20 17:00 |  | 2014-07-22 08:00 | 2014-08-17 17:00 | 2014-07-22 08:00 | 2014-08-17 17:00 | 2014-07-22 08:00 | 2014-08-17 17:00 | 2014-08-28 08:00 | 2014-09-20 17:00 |  | PT_Normal |  |  |  |  | l5hyv3DMQMS95hc38uMvzA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37500 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 501471 | 6359 | 124672 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4WSGL5155 | Excavation for water line | 8177 | 0 | 0 | 200 | 0 | 425 | 425 | 200 | 251 | 0 | 251 |  |  |  | 2014-05-31 08:00 | 2014-06-28 17:00 |  | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | oi/zLTdMRUKL0XDA6kHU3g |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37500 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 425 | LABOR - CIVIL
%R | 501472 | 6359 | 124672 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4WSGL5160 | Laying of water line | 8178 | 0 | 0 | 200 | 0 | 319.2 | 319.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-07-03 17:00 |  | 2014-06-05 08:00 | 2014-07-03 17:00 | 2014-06-05 08:00 | 2014-07-03 17:00 | 2014-06-05 08:00 | 2014-07-03 17:00 | 2014-06-05 08:00 | 2014-07-03 17:00 |  | PT_Normal |  |  |  |  | gcWktnH2QTq7Om6fJm22uQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37500 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 319.2 | LABOR- SUBCONTRACTOR
%R | 501473 | 6359 | 124672 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4WSGL5165 | Testing of potable water line | 8178 | 0 | 0 | 200 | 0 | 100.8 | 100.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-07-09 17:00 |  | 2014-06-11 08:00 | 2014-07-09 17:00 | 2014-06-11 08:00 | 2014-07-09 17:00 | 2014-06-11 08:00 | 2014-07-09 17:00 | 2014-06-11 08:00 | 2014-07-09 17:00 |  | PT_Normal |  |  |  |  | o2FKmXcRSVm2D6HmhLYsXg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37500 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 100.8 | LABOR- SUBCONTRACTOR
%R | 501474 | 6359 | 124672 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4WSGL5170 | Backfilling potable water line | 8177 | 0 | 0 | 200 | 0 | 347 | 347 | 200 | 275 | 0 | 275 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | o35O0+50RbG2YRB8NFtCQw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37500 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 347 | LABOR - CIVIL
%R | 501475 | 6359 | 124672 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4WSGL5175 | Construction of valve chambers & Thrust Blocks | 8172 | 232 | 0 | 200 | 0 | 88 | 88 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-27 08:00 | 2014-08-27 17:00 |  | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-07-27 08:00 | 2014-08-27 17:00 |  | PT_Normal |  |  |  |  | o6m6pj3rTs6fc5qHhXvRAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37500 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 88 | MANHOLES SK
%R | 501476 | 6359 | 124673 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4TCGL5295 | Excavation Telecommunication trenches | 8177 | 0 | 0 | 160 | 0 | 356 | 356 | 160 | 200 | 0 | 200 |  |  |  | 2014-08-17 08:00 | 2014-09-08 17:00 |  | 2014-08-17 08:00 | 2014-09-08 17:00 | 2014-08-17 08:00 | 2014-09-08 17:00 | 2014-08-17 08:00 | 2014-09-08 17:00 | 2014-08-17 08:00 | 2014-09-08 17:00 |  | PT_Normal |  |  |  |  | M+n3LPX+TOi2YzyjPuPq+g |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37550 | N | N | 45 | TELECOMMUNICATION LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 356 | LABOR - CIVIL
%R | 501477 | 6359 | 124673 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4TCGL5300 | Laying of cables | 8178 | 0 | 0 | 160 | 0 | 727.2 | 727.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-23 08:00 | 2014-09-14 17:00 |  | 2014-08-23 08:00 | 2014-09-14 17:00 | 2014-08-23 08:00 | 2014-09-14 17:00 | 2014-08-23 08:00 | 2014-09-14 17:00 | 2014-08-23 08:00 | 2014-09-14 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37550 | N | N | 45 | TELECOMMUNICATION LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 727.2 | LABOR- SUBCONTRACTOR
%R | 501478 | 6359 | 124673 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4TCGL5305 | Backfilling telecommunication trench | 8177 | 0 | 0 | 160 | 0 | 286 | 286 | 160 | 220 | 0 | 220 |  |  |  | 2014-08-28 08:00 | 2014-09-20 17:00 |  | 2014-08-28 08:00 | 2014-09-20 17:00 | 2014-08-28 08:00 | 2014-09-20 17:00 | 2014-08-28 08:00 | 2014-09-20 17:00 | 2014-08-28 08:00 | 2014-09-20 17:00 |  | PT_Normal |  |  |  |  | aSZAuiaITvaNgUVSfBuVdQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37550 | N | N | 45 | TELECOMMUNICATION LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 286 | LABOR - CIVIL
%R | 501479 | 6359 | 124673 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4TCGL5310 | Connection & Installation | 8178 | 248 | 136 | 160 | 0 | 271.2 | 271.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-09 17:00 |  | 2014-09-09 08:00 | 2014-10-01 17:00 | 2014-09-09 08:00 | 2014-10-01 17:00 | 2014-09-09 08:00 | 2014-10-01 17:00 | 2014-10-18 08:00 | 2014-11-09 17:00 |  | PT_Normal |  |  |  |  | 0OIHyyUZRkOwf8/Ynyo0Bw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37550 | N | N | 45 | TELECOMMUNICATION LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 271.2 | LABOR- SUBCONTRACTOR
%R | 501480 | 6359 | 124674 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4STGL5235 | Excavation for Street lighting | 8177 | 0 | 0 | 200 | 0 | 69 | 69 | 200 | 51 | 0 | 51 |  |  |  | 2014-07-21 08:00 | 2014-08-21 17:00 |  | 2014-07-21 08:00 | 2014-08-21 17:00 | 2014-07-21 08:00 | 2014-08-21 17:00 | 2014-07-21 08:00 | 2014-08-21 17:00 | 2014-07-21 08:00 | 2014-08-21 17:00 |  | PT_Normal |  |  |  |  | lkx19wDxQ9uk2dDt8DRymw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37530 | N | N | 35 | STREET LIGHTING |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 34.5 | LABOR - CIVIL
%R | 501481 | 6359 | 124674 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4STGL5240 | Construction of Duct Banks | 8178 | 0 | 0 | 200 | 0 | 1494 | 1494 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-27 08:00 | 2014-08-27 17:00 |  | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-07-27 08:00 | 2014-08-27 17:00 |  | PT_Normal |  |  |  |  | uavSjfs8RcCZsSwbqiB4Ug |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37530 | N | N | 35 | STREET LIGHTING |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 747 | LABOR- SUBCONTRACTOR
%R | 501482 | 6359 | 124674 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4STGL5245 | Construction of Foundation | 8172 | 0 | 0 | 200 | 0 | 630 | 630 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-27 08:00 | 2014-08-27 17:00 |  | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-07-27 08:00 | 2014-08-27 17:00 |  | PT_Normal |  |  |  |  | Oun2sd+VSZ6DS01423HknA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37530 | N | N | 35 | STREET LIGHTING |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 315 | MANHOLES SK
%R | 501483 | 6359 | 124674 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4STGL5250 | Backfilling Street Lighting | 8177 | 0 | 0 | 200 | 0 | 122 | 122 | 200 | 110 | 0 | 110 |  |  |  | 2014-08-05 08:00 | 2014-09-02 17:00 |  | 2014-08-05 08:00 | 2014-09-02 17:00 | 2014-08-05 08:00 | 2014-09-02 17:00 | 2014-08-05 08:00 | 2014-09-02 17:00 | 2014-08-05 08:00 | 2014-09-02 17:00 |  | PT_Normal |  |  |  |  | 77NfZhKTRFGII7Eu+omAnQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37530 | N | N | 35 | STREET LIGHTING |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 122 | LABOR - CIVIL
%R | 501484 | 6359 | 124674 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4STGL5255 | Installation of light Post | 8178 | 432 | 160 | 200 | 0 | 216 | 216 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-21 08:00 | 2014-11-18 17:00 |  | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-10-21 08:00 | 2014-11-18 17:00 |  | PT_Normal |  |  |  |  | etX3Ym8DTNGN9/7DAl2UtA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37530 | N | N | 35 | STREET LIGHTING |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 216 | LABOR- SUBCONTRACTOR
%R | 501485 | 6359 | 124674 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4STGL5260 | Electrical Works | 8178 | 272 | 0 | 200 | 0 | 1039.6 | 1039.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-29 08:00 | 2014-11-26 17:00 |  | 2014-09-17 08:00 | 2014-10-18 17:00 | 2014-09-17 08:00 | 2014-10-18 17:00 | 2014-09-17 08:00 | 2014-10-18 17:00 | 2014-10-29 08:00 | 2014-11-26 17:00 |  | PT_Normal |  |  |  |  | jvWdigBPRsOm+OYUG1YTXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37530 | N | N | 35 | STREET LIGHTING |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 519.8 | LABOR- SUBCONTRACTOR
%R | 501486 | 6359 | 124675 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4DRGL5115 | Excavation for Drainage line | 8177 | 120 | 0 | 200 | 0 | 419 | 419 | 200 | 251 | 0 | 251 |  |  |  | 2014-04-16 08:00 | 2014-05-14 17:00 |  | 2014-03-30 08:00 | 2014-04-27 17:00 | 2014-03-30 08:00 | 2014-04-27 17:00 | 2014-03-30 08:00 | 2014-04-27 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 |  | PT_Normal |  |  |  |  | wh1kvTI2QD6nXWJsRMP8zQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37480 | N | N | 10 | DRAINAGE LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 419 | LABOR - CIVIL
%R | 501487 | 6359 | 124675 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4DRGL5120 | Laying of Drainage line | 8178 | 120 | 0 | 200 | 0 | 265.2 | 265.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-05-21 17:00 |  | 2014-04-06 08:00 | 2014-05-04 17:00 | 2014-04-06 08:00 | 2014-05-04 17:00 | 2014-04-06 08:00 | 2014-05-04 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | FeEekZPDTcSyUj3OSE1GYw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37480 | N | N | 10 | DRAINAGE LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 265.2 | LABOR- SUBCONTRACTOR
%R | 501488 | 6359 | 124675 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4DRGL5125 | Testing of Drainage line | 8178 | 120 | 0 | 200 | 0 | 134.4 | 134.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-01 08:00 | 2014-05-29 17:00 |  | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | /iGb0wmvT/mlMjEMpA+b+A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37480 | N | N | 10 | DRAINAGE LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 501489 | 6359 | 124675 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4DRGL5130 | Backfilling Drainage line | 8177 | 120 | 0 | 120 | 0 | 315 | 315 | 120 | 248.9997 | 0 | 248.9997 |  |  |  | 2014-05-19 08:00 | 2014-06-04 17:00 |  | 2014-05-01 08:00 | 2014-05-18 17:00 | 2014-05-01 08:00 | 2014-05-18 17:00 | 2014-05-01 08:00 | 2014-05-18 17:00 | 2014-05-19 08:00 | 2014-06-04 17:00 |  | PT_Normal |  |  |  |  | AcIZEQheQpKIP98yhzeR5Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37480 | N | N | 10 | DRAINAGE LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 315 | LABOR - CIVIL
%R | 501490 | 6359 | 124676 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4PSGL7000 | Excavation | 8177 | 96 | 40 | 120 | 0 | 163 | 163 | 120 | 90.9998 | 0 | 90.9998 |  |  |  | 2014-11-17 08:00 | 2014-12-03 17:00 |  | 2014-11-03 08:00 | 2014-11-19 17:00 | 2014-11-03 08:00 | 2014-11-19 17:00 | 2014-11-03 08:00 | 2014-11-19 17:00 | 2014-11-17 08:00 | 2014-12-03 17:00 |  | PT_Normal |  |  |  |  | KBflIrE1QCuAiML0BaIPuQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37580 | N | N | 60 | PARKING SHED |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 163 | LABOR - CIVIL
%R | 501491 | 6359 | 124676 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4PSGL7005 | Foundation casting | 8165 | 56 | 8 | 120 | 0 | 302 | 302 | 120 | 0 | 0 | 0 |  |  |  | 2014-11-23 08:00 | 2014-12-09 17:00 |  | 2014-11-15 08:00 | 2014-12-01 17:00 | 2014-11-15 08:00 | 2014-12-01 17:00 | 2014-11-15 08:00 | 2014-12-01 17:00 | 2014-11-23 08:00 | 2014-12-09 17:00 |  | PT_Normal |  |  |  |  | 3YjLnnfZSM2SrG3dbb2wNw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37580 | N | N | 60 | PARKING SHED |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 302 | STEEL FIXERS SK
%R | 501492 | 6359 | 124676 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4PSGL7010 | Column, Frame& Fabrics Erection | 8178 | 48 | 0 | 200 | 0 | 314 | 314 | 200 | 0 | 0 | 0 |  |  |  | 2014-12-04 08:00 | 2015-01-03 17:00 |  | 2014-11-27 08:00 | 2014-12-27 17:00 | 2014-11-27 08:00 | 2014-12-27 17:00 | 2014-11-27 08:00 | 2014-12-27 17:00 | 2014-12-04 08:00 | 2015-01-03 17:00 |  | PT_Normal |  |  |  |  | 1khut1XtTUC80UaROknzYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37580 | N | N | 60 | PARKING SHED |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11; period 2: 2014-AP12 |  | 157 | LABOR- SUBCONTRACTOR
%R | 501493 | 6359 | 124676 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4PSGL7015 | Electrical Works-Parking Shed | 8178 | 48 | 48 | 200 | 0 | 51.6 | 51.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-12-10 08:00 | 2015-01-08 17:00 |  | 2014-12-03 08:00 | 2015-01-01 17:00 | 2014-12-03 08:00 | 2015-01-01 17:00 | 2014-12-03 08:00 | 2015-01-01 17:00 | 2014-12-10 08:00 | 2015-01-08 17:00 |  | PT_Normal |  |  |  |  | oIEPFEd0SpGEhoxAGmpoJA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37580 | N | N | 60 | PARKING SHED |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP12 |  | 51.6 | LABOR- SUBCONTRACTOR
%R | 501494 | 6359 | 124677 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4ELGL5215 | Excavation Cable Trenches & Duct Banks | 8177 | 0 | 0 | 200 | 0 | 2772 | 2772 | 200 | 876 | 0 | 876 |  |  |  | 2014-07-21 08:00 | 2014-08-21 17:00 |  | 2014-07-21 08:00 | 2014-08-21 17:00 | 2014-07-21 08:00 | 2014-08-21 17:00 | 2014-07-21 08:00 | 2014-08-21 17:00 | 2014-07-21 08:00 | 2014-08-21 17:00 |  | PT_Normal |  |  |  |  | QwK6h+MyRQSrgDOcblQbXg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37520 | N | N | 30 | ELECTRICAL LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 1386 | LABOR - CIVIL
%R | 501495 | 6359 | 124677 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4ELGL5220 | Laying of electrical cables | 8178 | 56 | 0 | 200 | 0 | 4487.2 | 4487.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-07 08:00 | 2014-09-04 17:00 |  | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-08-07 08:00 | 2014-09-04 17:00 |  | PT_Normal |  |  |  |  | sDAXgxIbRrOm8GQKKyOZ5Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37520 | N | N | 30 | ELECTRICAL LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 2243.6 | LABOR- SUBCONTRACTOR
%R | 501496 | 6359 | 124677 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4ELGL5225 | Backfilling Electrical trench | 8177 | 56 | 0 | 200 | 0 | 1862 | 1862 | 200 | 1100 | 0 | 1100 |  |  |  | 2014-08-16 08:00 | 2014-09-13 17:00 |  | 2014-08-07 08:00 | 2014-09-04 17:00 | 2014-08-07 08:00 | 2014-09-04 17:00 | 2014-08-07 08:00 | 2014-09-04 17:00 | 2014-08-16 08:00 | 2014-09-13 17:00 |  | PT_Normal |  |  |  |  | YVhQsTUdRz6kgymsx06Bjg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37520 | N | N | 30 | ELECTRICAL LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1862 | LABOR - CIVIL
%R | 501497 | 6359 | 124677 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4ELGL5230 | Construction of Submain Board & Feeder Pillar | 8165 | 272 | 0 | 200 | 0 | 276 | 276 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-28 08:00 | 2014-10-28 17:00 |  | 2014-08-19 08:00 | 2014-09-16 17:00 | 2014-08-19 08:00 | 2014-09-16 17:00 | 2014-08-19 08:00 | 2014-09-16 17:00 | 2014-09-28 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | ODSVIdLPTSeWcBukmNIX4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37520 | N | N | 30 | ELECTRICAL LINES |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 276 | STEEL FIXERS SK
%R | 501498 | 6359 | 124678 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4BWGL5315 | Construction of Boundary Wall (Ht-3m) | 8165 | 240 | 0 | 200 | 0 | 196 | 196 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-21 08:00 | 2014-10-21 17:00 |  | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-09-21 08:00 | 2014-10-21 17:00 |  | PT_Normal |  |  |  |  | coYyPsNkRt6ASxd6rHNb5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37560 | N | N | 50 | BOUNDARY WALL |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 196 | STEEL FIXERS SK
%R | 501499 | 6359 | 124678 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 8178 | 240 | 0 | 200 | 0 | 14 | 14 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-07 08:00 | 2014-11-06 17:00 |  | 2014-09-02 08:00 | 2014-09-30 17:00 | 2014-09-02 08:00 | 2014-09-30 17:00 | 2014-09-02 08:00 | 2014-09-30 17:00 | 2014-10-07 08:00 | 2014-11-06 17:00 |  | PT_Normal |  |  |  |  | AzsJYpk9Qie7ZAO57wmYYA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37560 | N | N | 50 | BOUNDARY WALL |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 14 | LABOR- SUBCONTRACTOR
%R | 501500 | 6359 | 124678 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 8165 | 240 | 0 | 200 | 0 | 140 | 140 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-08 08:00 | 2014-12-06 17:00 |  | 2014-10-01 08:00 | 2014-11-01 17:00 | 2014-10-01 08:00 | 2014-11-01 17:00 | 2014-10-01 08:00 | 2014-11-01 17:00 | 2014-11-08 08:00 | 2014-12-06 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37560 | N | N | 50 | BOUNDARY WALL |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10; period 2: 2014-AP10 |  | 70 | STEEL FIXERS SK
%R | 501501 | 6359 | 124678 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 8165 | 344 | 296 | 200 | 0 | 140 | 140 | 200 | 0 | 0 | 0 |  |  |  | 2014-12-04 08:00 | 2015-01-03 17:00 |  | 2014-10-15 08:00 | 2014-11-12 17:00 | 2014-10-15 08:00 | 2014-11-12 17:00 | 2014-10-15 08:00 | 2014-11-12 17:00 | 2014-12-04 08:00 | 2015-01-03 17:00 |  | PT_Normal |  |  |  |  | j71ReuHcQkO8GOop2TNQ/w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37560 | N | N | 50 | BOUNDARY WALL |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 140 | STEEL FIXERS SK
%R | 501502 | 6359 | 124679 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4RWGL6000 | Excavation & Earth Filling | 8177 | 0 | 0 | 80 | 0 | 1150 | 1150 | 80 | 400 | 0 | 400 |  |  |  | 2014-09-21 08:00 | 2014-10-01 17:00 |  | 2014-09-21 08:00 | 2014-10-01 17:00 | 2014-09-21 08:00 | 2014-10-01 17:00 | 2014-09-21 08:00 | 2014-10-01 17:00 | 2014-09-21 08:00 | 2014-10-01 17:00 |  | PT_Normal |  |  |  |  | XblDjYqcQMm1yrfX6sCn3g |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37570 | N | N | 55 | ROAD WORKS |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 1150 | LABOR - CIVIL
%R | 501503 | 6359 | 124679 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4RWGL6005 | Laying of Sub Grade | 8178 | 0 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-02 08:00 | 2014-11-02 17:00 |  | 2014-10-02 08:00 | 2014-11-02 17:00 | 2014-10-02 08:00 | 2014-11-02 17:00 | 2014-10-02 08:00 | 2014-11-02 17:00 | 2014-10-02 08:00 | 2014-11-02 17:00 |  | PT_Normal |  |  |  |  | r5j/zGYTSO+HY3MVq/G4Ag |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37570 | N | N | 55 | ROAD WORKS |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10; period 2: 2014-AP11 |  | 12 | LABOR- SUBCONTRACTOR
%R | 501504 | 6359 | 124679 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4RWGL6010 | Laying of Precast Kerbs | 8178 | 0 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-16 08:00 | 2014-11-13 17:00 |  | 2014-10-16 08:00 | 2014-11-13 17:00 | 2014-10-16 08:00 | 2014-11-13 17:00 | 2014-10-16 08:00 | 2014-11-13 17:00 | 2014-10-16 08:00 | 2014-11-13 17:00 |  | PT_Normal |  |  |  |  | 9iumzNifS3+R73YwUVOR/Q |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37570 | N | N | 55 | ROAD WORKS |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 24 | LABOR- SUBCONTRACTOR
%R | 501505 | 6359 | 124679 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4RWGL6015 | Laying of Granular Sub Base Coarse | 8173 | 0 | 0 | 160 | 0 | 1828 | 1828 | 160 | 600 | 0 | 600 |  |  |  | 2014-10-28 08:00 | 2014-11-19 17:00 |  | 2014-10-28 08:00 | 2014-11-19 17:00 | 2014-10-28 08:00 | 2014-11-19 17:00 | 2014-10-28 08:00 | 2014-11-19 17:00 | 2014-10-28 08:00 | 2014-11-19 17:00 |  | PT_Normal |  |  |  |  | a4JQTMjIQ7uRYmuTHGfcNw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37570 | N | N | 55 | ROAD WORKS |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 1828 | KERBSTONE MASON SK
%R | 501506 | 6359 | 124679 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4RWGL6020 | Laying of Road Base Asphalt Concrete | 8178 | 0 | 0 | 48 | 0 | 174 | 174 | 48 | 149.9989 | 0 | 149.9989 |  |  |  | 2014-11-20 08:00 | 2014-11-26 17:00 |  | 2014-11-20 08:00 | 2014-11-26 17:00 | 2014-11-20 08:00 | 2014-11-26 17:00 | 2014-11-20 08:00 | 2014-11-26 17:00 | 2014-11-20 08:00 | 2014-11-26 17:00 |  | PT_Normal |  |  |  |  | k2sfCHt8Tu+UrxyzRyrojA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37570 | N | N | 55 | ROAD WORKS |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 174 | LABOR- SUBCONTRACTOR
%R | 501507 | 6359 | 124679 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4RWGL6025 | Laying of Asphalt Wearing Coarse | 8178 | 0 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-11-27 08:00 | 2014-12-02 17:00 |  | 2014-11-27 08:00 | 2014-12-02 17:00 | 2014-11-27 08:00 | 2014-12-02 17:00 | 2014-11-27 08:00 | 2014-12-02 17:00 | 2014-11-27 08:00 | 2014-12-02 17:00 |  | PT_Normal |  |  |  |  | yfi0ODRcTH6bOvSi+ViVFw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37570 | N | N | 55 | ROAD WORKS |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 174 | LABOR- SUBCONTRACTOR
%R | 501508 | 6359 | 124679 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ4RWGL6030 | Traffic Signage & Road Marking | 8178 | 168 | 120 | 40 | 0 | 882 | 882 | 40 | 0 | 0 | 0 |  |  |  | 2014-12-29 08:00 | 2015-01-03 17:00 |  | 2014-12-03 08:00 | 2014-12-08 17:00 | 2014-12-03 08:00 | 2014-12-08 17:00 | 2014-12-03 08:00 | 2014-12-08 17:00 | 2014-12-29 08:00 | 2015-01-03 17:00 |  | PT_Normal |  |  |  |  | SK8SsjYfTuiKokPRpCNQPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37570 | N | N | 55 | ROAD WORKS |  | 124666 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP12 |  | 882 | LABOR- SUBCONTRACTOR
%R | 501509 | 6359 | 124682 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1SAGL5135 | Construction of manholes Drainage | 8177 | 472 | 80 | 200 | 0 | 6 | 6 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-04-06 17:00 |  | 2013-12-29 08:00 | 2014-01-26 17:00 | 2013-12-29 08:00 | 2014-01-26 17:00 | 2013-12-29 08:00 | 2014-01-26 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | 6KjaqcDgQFGjqNOqkbFZDw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37040 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 6 | LABOR - CIVIL
%R | 501510 | 6359 | 124682 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1SAGL5140 | Construction of soakaways | 8172 | 0 | 0 | 200 | 0 | 190 | 190 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-29 08:00 | 2014-01-26 17:00 |  | 2013-12-29 08:00 | 2014-01-26 17:00 | 2013-12-29 08:00 | 2014-01-26 17:00 | 2013-12-29 08:00 | 2014-01-26 17:00 | 2013-12-29 08:00 | 2014-01-26 17:00 |  | PT_Normal |  |  |  |  | 30ePbo/wQ4Wt80ki7FFSUA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37040 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 190 | MANHOLES SK
%R | 501511 | 6359 | 124682 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1SAGL5145 | Construction of Road gullies | 8172 | 0 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-27 08:00 | 2014-02-25 17:00 |  | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 |  | PT_Normal |  |  |  |  | YxUDIhA2SJSj54blU+j4Sw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37040 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 176 | MANHOLES SK
%R | 501512 | 6359 | 124682 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1SAGL5150 | Connection with existing sewer manhole | 8177 | 272 | 272 | 160 | 0 | 6 | 6 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-07 08:00 | 2014-04-29 17:00 |  | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-04-07 08:00 | 2014-04-29 17:00 |  | PT_Normal |  |  |  |  | R/DUpmQVQn23L5GWhYo9OQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37040 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 6 | LABOR - CIVIL
%R | 501513 | 6359 | 124683 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1TCGL5295 | Excavation Telecommunication trenches | 8177 | 0 | 0 | 160 | 0 | 356 | 356 | 160 | 200 | 0 | 200 |  |  |  | 2014-03-26 08:00 | 2014-04-17 17:00 |  | 2014-03-26 08:00 | 2014-04-17 17:00 | 2014-03-26 08:00 | 2014-04-17 17:00 | 2014-03-26 08:00 | 2014-04-17 17:00 | 2014-03-26 08:00 | 2014-04-17 17:00 |  | PT_Normal |  |  |  |  | sRJQwtdBQwi9drEMcf+ujg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37100 | N | N | 45 | TELECOMMUNICATION LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 356 | LABOR - CIVIL
%R | 501514 | 6359 | 124683 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1TCGL5300 | Laying of cables | 8178 | 0 | 0 | 160 | 0 | 727.2 | 727.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-01 08:00 | 2014-04-23 17:00 |  | 2014-04-01 08:00 | 2014-04-23 17:00 | 2014-04-01 08:00 | 2014-04-23 17:00 | 2014-04-01 08:00 | 2014-04-23 17:00 | 2014-04-01 08:00 | 2014-04-23 17:00 |  | PT_Normal |  |  |  |  | TYiCSZCNQN2H165x12WR/w |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37100 | N | N | 45 | TELECOMMUNICATION LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 727.2 | LABOR- SUBCONTRACTOR
%R | 501515 | 6359 | 124683 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1TCGL5305 | Backfilling telecommunication trench | 8177 | 0 | 0 | 160 | 0 | 286 | 286 | 160 | 220 | 0 | 220 |  |  |  | 2014-04-07 08:00 | 2014-04-29 17:00 |  | 2014-04-07 08:00 | 2014-04-29 17:00 | 2014-04-07 08:00 | 2014-04-29 17:00 | 2014-04-07 08:00 | 2014-04-29 17:00 | 2014-04-07 08:00 | 2014-04-29 17:00 |  | PT_Normal |  |  |  |  | 1jigVh3TTlmeNbMqxfaD3A |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37100 | N | N | 45 | TELECOMMUNICATION LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 286 | LABOR - CIVIL
%R | 501516 | 6359 | 124683 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1TCGL5310 | Connection & Installation | 8178 | 728 | 160 | 160 | 0 | 271.2 | 271.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-06 08:00 | 2014-08-28 17:00 |  | 2014-04-19 08:00 | 2014-05-11 17:00 | 2014-04-19 08:00 | 2014-05-11 17:00 | 2014-04-19 08:00 | 2014-05-11 17:00 | 2014-08-06 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | APNiQnlrRz60dbzxAqkppQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37100 | N | N | 45 | TELECOMMUNICATION LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 271.2 | LABOR- SUBCONTRACTOR
%R | 501517 | 6359 | 124684 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1DRGL5115 | Excavation for Drainage line | 8177 | 0 | 0 | 200 | 0 | 419 | 419 | 200 | 251 | 0 | 251 |  |  |  | 2013-11-25 08:00 | 2013-12-24 17:00 |  | 2013-11-25 08:00 | 2013-12-24 17:00 | 2013-11-25 08:00 | 2013-12-24 17:00 | 2013-11-25 08:00 | 2013-12-24 17:00 | 2013-11-25 08:00 | 2013-12-24 17:00 |  | PT_Normal |  |  |  |  | P46G2VGhQAi4EYd7i8Y0hA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37030 | N | N | 10 | DRAINAGE LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 419 | LABOR - CIVIL
%R | 501518 | 6359 | 124684 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1DRGL5120 | Laying of Drainage line | 8178 | 0 | 0 | 200 | 0 | 265.2 | 265.2 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-02 08:00 | 2013-12-31 17:00 |  | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 |  | PT_Normal |  |  |  |  | q6JIvoV0SfKBy3N1rqm7MA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37030 | N | N | 10 | DRAINAGE LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 265.2 | LABOR- SUBCONTRACTOR
%R | 501519 | 6359 | 124684 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1DRGL5125 | Testing of Drainage line | 8178 | 0 | 0 | 200 | 0 | 134.4 | 134.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-10 08:00 | 2014-01-08 17:00 |  | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 |  | PT_Normal |  |  |  |  | rjCfM307TAeGLE+7H9vv3Q |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37030 | N | N | 10 | DRAINAGE LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 501520 | 6359 | 124684 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1DRGL5130 | Backfilling Drainage line | 8177 | 0 | 0 | 120 | 0 | 315 | 315 | 120 | 248.9997 | 0 | 248.9997 |  |  |  | 2013-12-29 08:00 | 2014-01-14 17:00 |  | 2013-12-29 08:00 | 2014-01-14 17:00 | 2013-12-29 08:00 | 2014-01-14 17:00 | 2013-12-29 08:00 | 2014-01-14 17:00 | 2013-12-29 08:00 | 2014-01-14 17:00 |  | PT_Normal |  |  |  |  | /nFK/T++S/KaxCyS9JTtBQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37030 | N | N | 10 | DRAINAGE LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 315 | LABOR - CIVIL
%R | 501521 | 6359 | 124685 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1STGL5235 | Excavation for Street lighting | 8177 | 0 | 0 | 200 | 0 | 69 | 69 | 200 | 51 | 0 | 51 |  |  |  | 2014-03-03 08:00 | 2014-03-31 17:00 |  | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | IcAeZQLaQBaChlqhnIUzUQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37080 | N | N | 35 | STREET LIGHTING |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 69 | LABOR - CIVIL
%R | 501522 | 6359 | 124685 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1STGL5240 | Construction of Duct Banks | 8178 | 0 | 0 | 200 | 0 | 1494 | 1494 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-04-06 17:00 |  | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | nOsDm2OvSSGpJRgNNWECoA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37080 | N | N | 35 | STREET LIGHTING |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1494 | LABOR- SUBCONTRACTOR
%R | 501523 | 6359 | 124685 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1STGL5245 | Construction of Foundation | 8172 | 0 | 0 | 200 | 0 | 630 | 630 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-04-06 17:00 |  | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | JPwamGVKQFqKKkP+5gGXdA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37080 | N | N | 35 | STREET LIGHTING |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 630 | MANHOLES SK
%R | 501524 | 6359 | 124685 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1STGL5250 | Backfilling Street Lighting | 8177 | 0 | 0 | 200 | 0 | 122 | 122 | 200 | 110 | 0 | 110 |  |  |  | 2014-03-15 08:00 | 2014-04-12 17:00 |  | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 |  | PT_Normal |  |  |  |  | yUpXarHxT5CMWzhf1/oDsQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37080 | N | N | 35 | STREET LIGHTING |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 122 | LABOR - CIVIL
%R | 501525 | 6359 | 124685 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1STGL5255 | Installation of light Post | 8178 | 792 | 120 | 200 | 0 | 216 | 216 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-20 08:00 | 2014-08-20 17:00 |  | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-07-20 08:00 | 2014-08-20 17:00 |  | PT_Normal |  |  |  |  | Um1H10k+Rauig4Xg1kNzdQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37080 | N | N | 35 | STREET LIGHTING |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 216 | LABOR- SUBCONTRACTOR
%R | 501526 | 6359 | 124685 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1STGL5260 | Electrical Works | 8178 | 632 | 120 | 200 | 0 | 1039.6 | 1039.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-28 08:00 | 2014-08-28 17:00 |  | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-07-28 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | qTwFTjmYQvyRfS3vQcsX7g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37080 | N | N | 35 | STREET LIGHTING |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1039.6 | LABOR- SUBCONTRACTOR
%R | 501527 | 6359 | 124686 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1IRGL5265 | Excavation for irrigation line | 8177 | 56 | 0 | 200 | 0 | 998 | 998 | 200 | 500 | 0 | 500 |  |  |  | 2014-04-23 08:00 | 2014-05-21 17:00 |  | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | xDlE82VlSF+ozROa/ZKIYA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37090 | N | N | 40 | IRRIGATION LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 998 | LABOR - CIVIL
%R | 501528 | 6359 | 124686 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1IRGL5270 | Laying of irrigationline | 8178 | 56 | 0 | 200 | 0 | 352.8 | 352.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-27 17:00 |  | 2014-04-21 08:00 | 2014-05-19 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | AVT1jqRWS8il1KvDILIIzA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37090 | N | N | 40 | IRRIGATION LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 352.8 | LABOR- SUBCONTRACTOR
%R | 501529 | 6359 | 124686 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1IRGL5275 | Testing of irrigation line | 8178 | 56 | 0 | 200 | 0 | 285.6 | 285.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-05 08:00 | 2014-06-02 17:00 |  | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-05-05 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | XbpdVZ9XT8Wbzy9r8Mvy/A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37090 | N | N | 40 | IRRIGATION LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 285.6 | LABOR- SUBCONTRACTOR
%R | 501530 | 6359 | 124686 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1IRGL5280 | Backfilling irrigation line | 8177 | 56 | 0 | 200 | 0 | 706 | 706 | 200 | 550 | 0 | 550 |  |  |  | 2014-05-11 08:00 | 2014-06-08 17:00 |  | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | ntn+Fv6TQvOxthiqHojWIw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37090 | N | N | 40 | IRRIGATION LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 706 | LABOR - CIVIL
%R | 501531 | 6359 | 124686 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1IRGL5285 | Construction of Thrust Blocks,Pull boxes | 8178 | 176 | 0 | 200 | 0 | 149.6 | 149.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-07-07 17:00 |  | 2014-05-14 08:00 | 2014-06-11 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 |  | PT_Normal |  |  |  |  | zCtsq4vRSBuh6eBXcOxDmA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37090 | N | N | 40 | IRRIGATION LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 149.6 | LABOR- SUBCONTRACTOR
%R | 501532 | 6359 | 124686 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1IRGL5290 | Irrigation Fittings (Nozzle,Values) | 8178 | 176 | 88 | 200 | 0 | 352.8 | 352.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | jbxzboy1Tb6ilXauJDER9Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37090 | N | N | 40 | IRRIGATION LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 352.8 | LABOR- SUBCONTRACTOR
%R | 501533 | 6359 | 124687 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1HDGL7020 | Precast Concrete Kerbs works | 8173 | 88 | 0 | 160 | 0 | 800 | 800 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-06-04 17:00 |  | 2014-04-30 08:00 | 2014-05-22 17:00 | 2014-04-30 08:00 | 2014-05-22 17:00 | 2014-04-30 08:00 | 2014-05-22 17:00 | 2014-05-13 08:00 | 2014-06-04 17:00 |  | PT_Normal |  |  |  |  | MDUQtW/sSfK9KDhZLCnS0w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37140 | N | N | 65 | HARD LANDSCAPING |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 800 | KERBSTONE MASON SK
%R | 501534 | 6359 | 124687 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1HDGL7025 | Interlocking for Walkways | 8174 | 88 | 0 | 200 | 0 | 814 | 814 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-25 08:00 | 2014-06-22 17:00 |  | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-25 08:00 | 2014-06-22 17:00 |  | PT_Normal |  |  |  |  | cRJdE/UkTH+Qxax7bTQimA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37140 | N | N | 65 | HARD LANDSCAPING |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 814 | INTERLOCK MASON SK
%R | 501535 | 6359 | 124687 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1HDGL7030 | Construction of Retaining wall | 8165 | 88 | 0 | 200 | 0 | 3340 | 3340 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-07-03 17:00 |  | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-06-05 08:00 | 2014-07-03 17:00 |  | PT_Normal |  |  |  |  | Dj9EmILvQ9+ArqtDvo8JFg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37140 | N | N | 65 | HARD LANDSCAPING |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 3340 | STEEL FIXERS SK
%R | 501536 | 6359 | 124687 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1HDGL7035 | Construction of Wash Stone Boulders | 8170 | 88 | 0 | 200 | 0 | 22 | 22 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-07-03 17:00 |  | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-06-05 08:00 | 2014-07-03 17:00 |  | PT_Normal |  |  |  |  | iq+GO5PKSEu4tvfs2tSb8A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37140 | N | N | 65 | HARD LANDSCAPING |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 22 | TILE MASON SK
%R | 501537 | 6359 | 124687 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1HDGL7040 | Construction of Speed Humps | 8167 | 728 | 240 | 80 | 0 | 14 | 14 | 80 | 0 | 0 | 0 |  |  |  | 2014-10-29 08:00 | 2014-11-09 17:00 |  | 2014-07-09 08:00 | 2014-07-20 17:00 | 2014-07-09 08:00 | 2014-07-20 17:00 | 2014-07-09 08:00 | 2014-07-20 17:00 | 2014-10-29 08:00 | 2014-11-09 17:00 |  | PT_Normal |  |  |  |  | r+fdGXFmQISDLwlf2rC/QQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37140 | N | N | 65 | HARD LANDSCAPING |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 14 | CONCRETE MASON SK
%R | 501538 | 6359 | 124688 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 8165 | 704 | 120 | 200 | 0 | 140 | 140 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-06 08:00 | 2014-10-04 17:00 |  | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-09-06 08:00 | 2014-10-04 17:00 |  | PT_Normal |  |  |  |  | Y3LYxHS8SgG4xrZnW4SDYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37110 | N | N | 50 | BOUNDARY WALL |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 140 | STEEL FIXERS SK
%R | 501539 | 6359 | 124688 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1BWGL5315 | Construction of Boundary Wall (Ht-3m) | 8165 | 200 | 0 | 200 | 0 | 196 | 196 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-24 08:00 | 2014-05-22 17:00 |  | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 |  | PT_Normal |  |  |  |  | T62GPiPgRzq3i5egSmkIbw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37110 | N | N | 50 | BOUNDARY WALL |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 196 | STEEL FIXERS SK
%R | 501540 | 6359 | 124688 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 8178 | 200 | 0 | 200 | 0 | 14 | 14 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-06-08 17:00 |  | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | XozXnqVQQICmzIM+Uhx9AQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37110 | N | N | 50 | BOUNDARY WALL |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 14 | LABOR- SUBCONTRACTOR
%R | 501541 | 6359 | 124688 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 8165 | 200 | 0 | 200 | 0 | 140 | 140 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-07-07 17:00 |  | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 |  | PT_Normal |  |  |  |  | avorwNANRVat/AxWSKEmQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37110 | N | N | 50 | BOUNDARY WALL |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 140 | STEEL FIXERS SK
%R | 501542 | 6359 | 124689 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1PSGL7000 | Excavation | 8177 | 456 | 40 | 120 | 0 | 163 | 163 | 120 | 90.9998 | 0 | 90.9998 |  |  |  | 2014-08-19 08:00 | 2014-09-04 17:00 |  | 2014-06-10 08:00 | 2014-06-26 17:00 | 2014-06-10 08:00 | 2014-06-26 17:00 | 2014-06-10 08:00 | 2014-06-26 17:00 | 2014-08-19 08:00 | 2014-09-04 17:00 |  | PT_Normal |  |  |  |  | spvEqm83RpCIizr22GOq4g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37130 | N | N | 60 | PARKING SHED |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 163 | LABOR - CIVIL
%R | 501543 | 6359 | 124689 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1PSGL7005 | Foundation casting | 8165 | 416 | 0 | 120 | 0 | 302 | 302 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-25 08:00 | 2014-09-10 17:00 |  | 2014-06-22 08:00 | 2014-07-08 17:00 | 2014-06-22 08:00 | 2014-07-08 17:00 | 2014-06-22 08:00 | 2014-07-08 17:00 | 2014-08-25 08:00 | 2014-09-10 17:00 |  | PT_Normal |  |  |  |  | 2YUuWxMRQ1+7nbrV7JriQA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37130 | N | N | 60 | PARKING SHED |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 302 | STEEL FIXERS SK
%R | 501544 | 6359 | 124689 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1PSGL7010 | Column, Frame& Fabrics Erection | 8178 | 416 | 0 | 200 | 0 | 314 | 314 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-06 08:00 | 2014-10-04 17:00 |  | 2014-07-03 08:00 | 2014-07-31 17:00 | 2014-07-03 08:00 | 2014-07-31 17:00 | 2014-07-03 08:00 | 2014-07-31 17:00 | 2014-09-06 08:00 | 2014-10-04 17:00 |  | PT_Normal |  |  |  |  | hrKSMKk9ShuDu2UNn5WtZQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37130 | N | N | 60 | PARKING SHED |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 314 | LABOR- SUBCONTRACTOR
%R | 501545 | 6359 | 124689 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1PSGL7015 | Electrical Works-Parking Shed | 8178 | 416 | 120 | 200 | 0 | 51.6 | 51.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-11 08:00 | 2014-10-12 17:00 |  | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-07-09 08:00 | 2014-08-10 17:00 | 2014-09-11 08:00 | 2014-10-12 17:00 |  | PT_Normal |  |  |  |  | oFHzMGKVTvKRQmS8YzI0pA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37130 | N | N | 60 | PARKING SHED |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 25.8 | LABOR- SUBCONTRACTOR
%R | 501546 | 6359 | 124690 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1FFGL5185 | Excavation for firefighting line | 8177 | 0 | 0 | 200 | 0 | 190 | 190 | 200 | 100 | 0 | 100 |  |  |  | 2014-02-02 08:00 | 2014-03-03 17:00 |  | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-02 08:00 | 2014-03-03 17:00 |  | PT_Normal |  |  |  |  | J6RE0cduTJy30bb49mteww |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37060 | N | N | 25 | FIREFIGHTING LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 95 | LABOR - CIVIL
%R | 501547 | 6359 | 124690 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1FFGL5190 | Laying of firefighting line | 8178 | 0 | 0 | 200 | 0 | 210 | 210 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-10 08:00 | 2014-03-11 17:00 |  | 2014-02-10 08:00 | 2014-03-11 17:00 | 2014-02-10 08:00 | 2014-03-11 17:00 | 2014-02-10 08:00 | 2014-03-11 17:00 | 2014-02-10 08:00 | 2014-03-11 17:00 |  | PT_Normal |  |  |  |  | 8GNjDgRoQbmgP0PCjeVV2w |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37060 | N | N | 25 | FIREFIGHTING LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 105 | LABOR- SUBCONTRACTOR
%R | 501548 | 6359 | 124690 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1FFGL5195 | Testing of firefighting line | 8178 | 0 | 0 | 200 | 0 | 50.4 | 50.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-17 08:00 | 2014-03-17 17:00 |  | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 |  | PT_Normal |  |  |  |  | /HwdGuiSRla4pvzjTPccQg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37060 | N | N | 25 | FIREFIGHTING LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 25.2 | LABOR- SUBCONTRACTOR
%R | 501549 | 6359 | 124690 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1FFGL5200 | Backfilling firefighting line | 8177 | 0 | 0 | 200 | 0 | 311 | 311 | 200 | 275 | 0 | 275 |  |  |  | 2014-02-23 08:00 | 2014-03-23 17:00 |  | 2014-02-23 08:00 | 2014-03-23 17:00 | 2014-02-23 08:00 | 2014-03-23 17:00 | 2014-02-23 08:00 | 2014-03-23 17:00 | 2014-02-23 08:00 | 2014-03-23 17:00 |  | PT_Normal |  |  |  |  | KyG0SbJQQ86U+h8lXsdflA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37060 | N | N | 25 | FIREFIGHTING LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 155.5 | LABOR - CIVIL
%R | 501550 | 6359 | 124690 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1FFGL5205 | Construction of valve chambers & Thrust Blocks | 8165 | 176 | 0 | 200 | 0 | 266 | 266 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-26 08:00 | 2014-04-23 17:00 |  | 2014-03-01 08:00 | 2014-03-29 17:00 | 2014-03-01 08:00 | 2014-03-29 17:00 | 2014-03-01 08:00 | 2014-03-29 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 |  | PT_Normal |  |  |  |  | +0XRH/22QlG5TDeyJyIYdg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37060 | N | N | 25 | FIREFIGHTING LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 266 | STEEL FIXERS SK
%R | 501551 | 6359 | 124690 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1FFGL5210 | Connection with existing Firewater System | 8178 | 176 | 120 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-01 08:00 | 2014-04-29 17:00 |  | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 |  | PT_Normal |  |  |  |  | nQf2bDR3S9WoBgRxAZHZXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37060 | N | N | 25 | FIREFIGHTING LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 84 | LABOR- SUBCONTRACTOR
%R | 501552 | 6359 | 124691 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1SLGL7200 | Excavation | 8177 | 88 | 0 | 200 | 0 | 926 | 926 | 200 | 500 | 0 | 500 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-06-04 08:00 | 2014-07-02 17:00 | 2014-06-04 08:00 | 2014-07-02 17:00 | 2014-06-04 08:00 | 2014-07-02 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | Oz0SD61fRz6Y2/hh5y+IAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37150 | N | N | 70 | SOFT LANDSCAPING |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 926 | LABOR - CIVIL
%R | 501553 | 6359 | 124691 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1SLGL7210 | Plantation works | 8178 | 328 | 120 | 200 | 0 | 728 | 728 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-15 17:00 |  | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 | 2014-08-18 08:00 | 2014-09-15 17:00 |  | PT_Normal |  |  |  |  | Bi7VXeEaSUuuYRu6HPLpRw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37150 | N | N | 70 | SOFT LANDSCAPING |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 728 | LABOR- SUBCONTRACTOR
%R | 501554 | 6359 | 124691 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1SLGL7205 | Sweet Soil Laying | 8178 | 88 | 0 | 200 | 0 | 4102 | 4102 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-27 17:00 |  | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | 4Kc7nxR4RL231Zq5W4hf9g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37150 | N | N | 70 | SOFT LANDSCAPING |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 4102 | LABOR- SUBCONTRACTOR
%R | 501555 | 6359 | 124692 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1WSGL5155 | Excavation for water line | 8177 | 0 | 0 | 200 | 0 | 425 | 425 | 200 | 251 | 0 | 251 |  |  |  | 2014-01-09 08:00 | 2014-02-06 17:00 |  | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-01-09 08:00 | 2014-02-06 17:00 |  | PT_Normal |  |  |  |  | 5f6TkcxnQIuv4/c3R09ZaQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37050 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 425 | LABOR - CIVIL
%R | 501556 | 6359 | 124692 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1WSGL5160 | Laying of water line | 8178 | 0 | 0 | 200 | 0 | 319.2 | 319.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-15 08:00 | 2014-02-13 17:00 |  | 2014-01-15 08:00 | 2014-02-13 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 |  | PT_Normal |  |  |  |  | oaVudmipQSyygoNz69dMOA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37050 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 319.2 | LABOR- SUBCONTRACTOR
%R | 501557 | 6359 | 124692 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1WSGL5165 | Testing of potable water line | 8178 | 0 | 0 | 200 | 0 | 100.8 | 100.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-21 08:00 | 2014-02-19 17:00 |  | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 |  | PT_Normal |  |  |  |  | fHounxWbRSWi1AkkTIH4ig |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37050 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 100.8 | LABOR- SUBCONTRACTOR
%R | 501558 | 6359 | 124692 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1WSGL5170 | Backfilling potable water line | 8177 | 0 | 0 | 200 | 0 | 347 | 347 | 200 | 275 | 0 | 275 |  |  |  | 2014-01-27 08:00 | 2014-02-25 17:00 |  | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 |  | PT_Normal |  |  |  |  | 45K8+gtcQTC0XiZTGh9WDw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37050 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 347 | LABOR - CIVIL
%R | 501559 | 6359 | 124692 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1WSGL5175 | Construction of valve chambers & Thrust Blocks | 8172 | 232 | 0 | 200 | 0 | 88 | 88 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-04-06 17:00 |  | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | xZGTGYczQbuuWYZQo/XD2w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37050 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 44 | MANHOLES SK
%R | 501560 | 6359 | 124692 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1WSGL5180 | Installation of meter ,Accessories & Connection | 8178 | 232 | 56 | 160 | 0 | 50.4 | 50.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-07 08:00 | 2014-04-29 17:00 |  | 2014-03-04 08:00 | 2014-03-26 17:00 | 2014-03-04 08:00 | 2014-03-26 17:00 | 2014-03-04 08:00 | 2014-03-26 17:00 | 2014-04-07 08:00 | 2014-04-29 17:00 |  | PT_Normal |  |  |  |  | w1Ef5mJfTOScUUbd/w23OA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37050 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 501561 | 6359 | 124693 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1ELGL5215 | Excavation Cable Trenches & Duct Banks | 8177 | 0 | 0 | 200 | 0 | 2772 | 2772 | 200 | 876 | 0 | 876 |  |  |  | 2014-03-03 08:00 | 2014-03-31 17:00 |  | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | jU4Hpms1Q1Cf0wZbEO8+jQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37070 | N | N | 30 | ELECTRICAL LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 2772 | LABOR - CIVIL
%R | 501562 | 6359 | 124693 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1ELGL5220 | Laying of electrical cables | 8178 | 24 | 0 | 200 | 0 | 4487.2 | 4487.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-12 08:00 | 2014-04-09 17:00 |  | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-12 08:00 | 2014-04-09 17:00 |  | PT_Normal |  |  |  |  | 9hR6STZUS9qULwVmZSY5cQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37070 | N | N | 30 | ELECTRICAL LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 4487.2 | LABOR- SUBCONTRACTOR
%R | 501563 | 6359 | 124693 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1ELGL5225 | Backfilling Electrical trench | 8177 | 24 | 0 | 200 | 0 | 1862 | 1862 | 200 | 1100 | 0 | 1100 |  |  |  | 2014-03-20 08:00 | 2014-04-17 17:00 |  | 2014-03-17 08:00 | 2014-04-14 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 |  | PT_Normal |  |  |  |  | eIyUoc8oTe+tBFSTCYdM9g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37070 | N | N | 30 | ELECTRICAL LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1862 | LABOR - CIVIL
%R | 501564 | 6359 | 124693 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1ELGL5230 | Construction of Submain Board & Feeder Pillar | 8165 | 632 | 0 | 200 | 0 | 276 | 276 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-27 17:00 |  | 2014-03-29 08:00 | 2014-04-26 17:00 | 2014-03-29 08:00 | 2014-04-26 17:00 | 2014-03-29 08:00 | 2014-04-26 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | GuyqXZuwRFeCOE28o1e2wg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37070 | N | N | 30 | ELECTRICAL LINES |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 276 | STEEL FIXERS SK
%R | 501565 | 6359 | 124694 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1RWGL6000 | Excavation & Earth Filling | 8177 | 0 | 0 | 80 | 0 | 1150 | 1150 | 80 | 400 | 0 | 400 |  |  |  | 2014-04-30 08:00 | 2014-05-11 17:00 |  | 2014-04-30 08:00 | 2014-05-11 17:00 | 2014-04-30 08:00 | 2014-05-11 17:00 | 2014-04-30 08:00 | 2014-05-11 17:00 | 2014-04-30 08:00 | 2014-05-11 17:00 |  | PT_Normal |  |  |  |  | uua9UjNfT/y3TMAZEkZltw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37120 | N | N | 55 | ROAD WORKS |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1150 | LABOR - CIVIL
%R | 501566 | 6359 | 124694 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1RWGL6005 | Laying of Sub Grade | 8178 | 0 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-12 08:00 | 2014-06-09 17:00 |  | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 |  | PT_Normal |  |  |  |  | 4sioHMEqQ6CVlIkq9qt0FA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37120 | N | N | 55 | ROAD WORKS |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 24 | LABOR- SUBCONTRACTOR
%R | 501567 | 6359 | 124694 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1RWGL6010 | Laying of Precast Kerbs | 8178 | 0 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-24 08:00 | 2014-06-21 17:00 |  | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 |  | PT_Normal |  |  |  |  | oClptBrzTy2+fmX/3yeqNg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37120 | N | N | 55 | ROAD WORKS |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 24 | LABOR- SUBCONTRACTOR
%R | 501568 | 6359 | 124694 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1RWGL6015 | Laying of Granular Sub Base Coarse | 8173 | 0 | 0 | 160 | 0 | 1828 | 1828 | 160 | 600 | 0 | 600 |  |  |  | 2014-06-04 08:00 | 2014-06-26 17:00 |  | 2014-06-04 08:00 | 2014-06-26 17:00 | 2014-06-04 08:00 | 2014-06-26 17:00 | 2014-06-04 08:00 | 2014-06-26 17:00 | 2014-06-04 08:00 | 2014-06-26 17:00 |  | PT_Normal |  |  |  |  | dmN58+cfSM2Sv5KMWNHKPA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37120 | N | N | 55 | ROAD WORKS |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1828 | KERBSTONE MASON SK
%R | 501569 | 6359 | 124694 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1RWGL6020 | Laying of Road Base Asphalt Concrete | 8178 | 416 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-08-31 08:00 | 2014-09-04 17:00 |  | 2014-06-28 08:00 | 2014-07-02 17:00 | 2014-06-28 08:00 | 2014-07-02 17:00 | 2014-06-28 08:00 | 2014-07-02 17:00 | 2014-08-31 08:00 | 2014-09-04 17:00 |  | PT_Normal |  |  |  |  | M1OEBTzxQkiKkWU0lpw19Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37120 | N | N | 55 | ROAD WORKS |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 174 | LABOR- SUBCONTRACTOR
%R | 501570 | 6359 | 124694 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1RWGL6025 | Laying of Asphalt Wearing Coarse | 8178 | 536 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-09-23 08:00 | 2014-09-28 17:00 |  | 2014-07-03 08:00 | 2014-07-08 17:00 | 2014-07-03 08:00 | 2014-07-08 17:00 | 2014-07-03 08:00 | 2014-07-08 17:00 | 2014-09-23 08:00 | 2014-09-28 17:00 |  | PT_Normal |  |  |  |  | 0zR9fmeHSrqVPjscvJJtDg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37120 | N | N | 55 | ROAD WORKS |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 174 | LABOR- SUBCONTRACTOR
%R | 501571 | 6359 | 124694 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1BZ1RWGL6030 | Traffic Signage & Road Marking | 8178 | 536 | 120 | 40 | 0 | 882 | 882 | 40 | 0 | 0 | 0 |  |  |  | 2014-09-29 08:00 | 2014-10-04 17:00 |  | 2014-07-09 08:00 | 2014-07-14 17:00 | 2014-07-09 08:00 | 2014-07-14 17:00 | 2014-07-09 08:00 | 2014-07-14 17:00 | 2014-09-29 08:00 | 2014-10-04 17:00 |  | PT_Normal |  |  |  |  | 8fJtfLpsTTWSbt2EdnymQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37120 | N | N | 55 | ROAD WORKS |  | 124681 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 882 | LABOR- SUBCONTRACTOR
%R | 501572 | 6359 | 124697 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 0 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | UmncrCEcSwmmSJLdv+6l/Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41630 | N | N | 30 | TESTING AND COMMISSIONING |  | 124696 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 501573 | 6359 | 124697 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | I4FVBGV/QKCbefmz6Zodwg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41630 | N | N | 30 | TESTING AND COMMISSIONING |  | 124696 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 501574 | 6359 | 124697 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | e8MzXB2rQ3GrK5kr/b3HOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41630 | N | N | 30 | TESTING AND COMMISSIONING |  | 124696 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 501575 | 6359 | 124700 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2AREL3665 | External Plastering | 8169 | 424 | 0 | 200 | 0 | 9159.75 | 9159.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-22 17:00 |  | 2013-12-21 08:00 | 2014-01-18 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | X6XLtPPtQvauF/UsBNhsyg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41430 | N | N | 15 | ELEVATION |  | 124699 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 9159.75 | PLASTER MASON SK
%R | 501576 | 6359 | 124700 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2AREL3675 | GRC Panel Works | 8178 | 440 | 40 | 160 | 0 | 550 | 550 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-04-05 17:00 |  | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 |  | PT_Normal |  |  |  |  | WUQiSca2QRebwIaXFHqdUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41430 | N | N | 15 | ELEVATION |  | 124699 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 550 | LABOR- SUBCONTRACTOR
%R | 501577 | 6359 | 124700 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2AREL3680 | External Painting | 8178 | 384 | 0 | 160 | 0 | 3234 | 3234 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-25 08:00 | 2014-04-16 17:00 |  | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-03-25 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | QcFHNkjzSa6C9dNGB3ysgA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41430 | N | N | 15 | ELEVATION |  | 124699 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 3234 | LABOR- SUBCONTRACTOR
%R | 501578 | 6359 | 124701 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARRF3630 | Leveling Screed for Waterproofing | 8164 | 496 | 0 | 200 | 0 | 734.75 | 734.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-04 08:00 | 2014-03-05 17:00 |  | 2013-11-23 08:00 | 2013-12-22 17:00 | 2013-11-23 08:00 | 2013-12-22 17:00 | 2013-11-23 08:00 | 2013-12-22 17:00 | 2014-02-04 08:00 | 2014-03-05 17:00 |  | PT_Normal |  |  |  |  | FC1mN3shR+Sx3mKKSLhP+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41420 | N | N | 10 | ROOF |  | 124699 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 734.75 | SCREED MASON SK
%R | 501579 | 6359 | 124701 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARRF3635 | Laying of Waterproofing Membrane | 8178 | 496 | 0 | 200 | 0 | 2042.25 | 2042.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-08 08:00 | 2014-03-09 17:00 |  | 2013-11-26 08:00 | 2013-12-25 17:00 | 2013-11-26 08:00 | 2013-12-25 17:00 | 2013-11-26 08:00 | 2013-12-25 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 |  | PT_Normal |  |  |  |  | CMx2Zu2STPekHnByP89JOw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41420 | N | N | 10 | ROOF |  | 124699 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 2042.25 | LABOR- SUBCONTRACTOR
%R | 501580 | 6359 | 124701 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARRF3640 | Installation of Insulation & Protection | 8178 | 496 | 0 | 200 | 0 | 1291.5 | 1291.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-03-13 17:00 |  | 2013-12-01 08:00 | 2013-12-30 17:00 | 2013-12-01 08:00 | 2013-12-30 17:00 | 2013-12-01 08:00 | 2013-12-30 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 |  | PT_Normal |  |  |  |  | yQe7UApTRZO9qh0aJdj1og |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41420 | N | N | 10 | ROOF |  | 124699 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1291.5 | LABOR- SUBCONTRACTOR
%R | 501581 | 6359 | 124701 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 496 | 0 | 200 | 0 | 741.5 | 741.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-18 17:00 |  | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | E+KZLPc1TcaeKacmwL4Q1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41420 | N | N | 10 | ROOF |  | 124699 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 741.5 | TILE MASON SK
%R | 501582 | 6359 | 124701 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 496 | 0 | 160 | 0 | 231 | 231 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-04-05 17:00 |  | 2013-12-30 08:00 | 2014-01-21 17:00 | 2013-12-30 08:00 | 2014-01-21 17:00 | 2013-12-30 08:00 | 2014-01-21 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 |  | PT_Normal |  |  |  |  | WPUKfQM8RDiwAiQSjC911g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41420 | N | N | 10 | ROOF |  | 124699 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 231 | LABOR- SUBCONTRACTOR
%R | 501583 | 6359 | 124701 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 496 | 0 | 200 | 0 | 882 | 882 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-26 08:00 | 2014-03-26 17:00 |  | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 |  | PT_Normal |  |  |  |  | SjmApVhyR3OeRJhRWC76pw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41420 | N | N | 10 | ROOF |  | 124699 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 882 | LABOR- SUBCONTRACTOR
%R | 501584 | 6359 | 124701 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARRF3660 | Installation of Access Ladder | 8178 | 536 | 536 | 120 | 0 | 198 | 198 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-16 17:00 |  | 2014-01-11 08:00 | 2014-01-27 17:00 | 2014-01-11 08:00 | 2014-01-27 17:00 | 2014-01-11 08:00 | 2014-01-27 17:00 | 2014-03-31 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | N/bZKyMUSKmD/rR3lr+r6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41420 | N | N | 10 | ROOF |  | 124699 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 198 | LABOR- SUBCONTRACTOR
%R | 501585 | 6359 | 124703 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARRF3600 | Block work | 8168 | 536 | 0 | 160 | 0 | 487.5 | 487.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-04 08:00 | 2014-02-27 17:00 |  | 2013-11-17 08:00 | 2013-12-09 17:00 | 2013-11-17 08:00 | 2013-12-09 17:00 | 2013-11-17 08:00 | 2013-12-09 17:00 | 2014-02-04 08:00 | 2014-02-27 17:00 |  | PT_Normal |  |  |  |  | sDIICuPETmC0COE4UnLU4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41400 | N | N | 20 | ROOF |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 487.5 | BLOCK MASON SK
%R | 501586 | 6359 | 124703 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARRF3605 | Plastering work | 8169 | 536 | 0 | 160 | 0 | 1950 | 1950 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-03-08 17:00 |  | 2013-11-25 08:00 | 2013-12-17 17:00 | 2013-11-25 08:00 | 2013-12-17 17:00 | 2013-11-25 08:00 | 2013-12-17 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | jLZH2ojzS6O1R/NEp18Y9Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41400 | N | N | 20 | ROOF |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1950 | PLASTER MASON SK
%R | 501587 | 6359 | 124703 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARRF3610 | Flooring screed | 8164 | 576 | 0 | 120 | 0 | 115.5 | 115.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-05 08:00 | 2014-03-22 17:00 |  | 2013-12-09 08:00 | 2013-12-26 17:00 | 2013-12-09 08:00 | 2013-12-26 17:00 | 2013-12-09 08:00 | 2013-12-26 17:00 | 2014-03-05 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | PlLkLVS0SH+o8O6D2MBRog |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41400 | N | N | 20 | ROOF |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 115.5 | SCREED MASON SK
%R | 501588 | 6359 | 124703 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARRF3695 | Painting | 8178 | 576 | 0 | 160 | 0 | 504 | 504 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-04-05 17:00 |  | 2013-12-17 08:00 | 2014-01-09 17:00 | 2013-12-17 08:00 | 2014-01-09 17:00 | 2013-12-17 08:00 | 2014-01-09 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 |  | PT_Normal |  |  |  |  | BuIQQ9QhQ8iSAAR/MOmNSA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41400 | N | N | 20 | ROOF |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 504 | LABOR- SUBCONTRACTOR
%R | 501589 | 6359 | 124703 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARRF3620 | Epoxy Painting | 8178 | 576 | 576 | 120 | 0 | 24.75 | 24.75 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-16 17:00 |  | 2014-01-05 08:00 | 2014-01-21 17:00 | 2014-01-05 08:00 | 2014-01-21 17:00 | 2014-01-05 08:00 | 2014-01-21 17:00 | 2014-03-31 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | kIHwhN6rSCmi4Dr2rYrKBQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41400 | N | N | 20 | ROOF |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 24.75 | LABOR- SUBCONTRACTOR
%R | 501590 | 6359 | 124704 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARFF3300 | Block work | 8168 | 0 | 0 | 200 | 0 | 5553.5 | 5553.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-29 08:00 | 2013-11-26 17:00 |  | 2013-10-29 08:00 | 2013-11-26 17:00 | 2013-10-29 08:00 | 2013-11-26 17:00 | 2013-10-29 08:00 | 2013-11-26 17:00 | 2013-10-29 08:00 | 2013-11-26 17:00 |  | PT_Normal |  |  |  |  | 96O9zINUTRaDU6CqePc4YA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41390 | N | N | 15 | FIRST FLOORS |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 5553.5 | BLOCK MASON SK
%R | 501591 | 6359 | 124704 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARFF3305 | Plastering work | 8169 | 0 | 0 | 200 | 0 | 5516 | 5516 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-23 08:00 | 2013-12-22 17:00 |  | 2013-11-23 08:00 | 2013-12-22 17:00 | 2013-11-23 08:00 | 2013-12-22 17:00 | 2013-11-23 08:00 | 2013-12-22 17:00 | 2013-11-23 08:00 | 2013-12-22 17:00 |  | PT_Normal |  |  |  |  | lRu5k+kAS/2IRmeZhzKD3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41390 | N | N | 15 | FIRST FLOORS |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 5516 | PLASTER MASON SK
%R | 501592 | 6359 | 124704 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARFF3310 | Flooring screed | 8164 | 120 | 120 | 168 | 0 | 1031.25 | 1031.25 | 168 | 0 | 0 | 0 |  |  |  | 2013-12-19 08:00 | 2014-01-12 17:00 |  | 2013-12-01 08:00 | 2013-12-25 17:00 | 2013-12-01 08:00 | 2013-12-25 17:00 | 2013-12-01 08:00 | 2013-12-25 17:00 | 2013-12-19 08:00 | 2014-01-12 17:00 |  | PT_Normal |  |  |  |  | KV2uMyHLQzOctYbDz0jn4g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41390 | N | N | 15 | FIRST FLOORS |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1031.25 | SCREED MASON SK
%R | 501593 | 6359 | 124704 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARFF3315 | Wet area waterproofing | 8178 | 0 | 0 | 120 | 0 | 582 | 582 | 120 | 0 | 0 | 0 |  |  |  | 2013-12-14 08:00 | 2013-12-31 17:00 |  | 2013-12-14 08:00 | 2013-12-31 17:00 | 2013-12-14 08:00 | 2013-12-31 17:00 | 2013-12-14 08:00 | 2013-12-31 17:00 | 2013-12-14 08:00 | 2013-12-31 17:00 |  | PT_Normal |  |  |  |  | lfu1xezyT+aXp/ALntTJGw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41390 | N | N | 15 | FIRST FLOORS |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 582 | LABOR- SUBCONTRACTOR
%R | 501594 | 6359 | 124704 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARFF3330 | Paint First coat | 8178 | 144 | 144 | 200 | 0 | 3644.75 | 3644.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-31 08:00 | 2014-01-28 17:00 |  | 2013-12-09 08:00 | 2014-01-07 17:00 | 2013-12-09 08:00 | 2014-01-07 17:00 | 2013-12-09 08:00 | 2014-01-07 17:00 | 2013-12-31 08:00 | 2014-01-28 17:00 |  | PT_Normal |  |  |  |  | xJboz2VpRSWjKjHoMUAz1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41390 | N | N | 15 | FIRST FLOORS |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 3644.75 | LABOR- SUBCONTRACTOR
%R | 501595 | 6359 | 124704 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARFF3320 | Ceramic Wall Tiling | 8170 | 0 | 0 | 200 | 0 | 2603.5 | 2603.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-24 08:00 | 2014-01-21 17:00 |  | 2013-12-24 08:00 | 2014-01-21 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 |  | PT_Normal |  |  |  |  | WEyvOTqbRxqsdcL5tcWZ0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41390 | N | N | 15 | FIRST FLOORS |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 2603.5 | TILE MASON SK
%R | 501596 | 6359 | 124704 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARFF3325 | Porcelain Tile flooring | 8170 | 0 | 0 | 200 | 0 | 1787.5 | 1787.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-31 08:00 | 2014-01-28 17:00 |  | 2013-12-31 08:00 | 2014-01-28 17:00 | 2013-12-31 08:00 | 2014-01-28 17:00 | 2013-12-31 08:00 | 2014-01-28 17:00 | 2013-12-31 08:00 | 2014-01-28 17:00 |  | PT_Normal |  |  |  |  | MBiK6Az6SVyHNw7+jN9d4A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41390 | N | N | 15 | FIRST FLOORS |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1787.5 | TILE MASON SK
%R | 501597 | 6359 | 124704 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARFF3335 | Slate Tile Flooring & Skirting | 8178 | 80 | 80 | 120 | 0 | 1350 | 1350 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-29 08:00 | 2014-02-16 17:00 |  | 2014-01-18 08:00 | 2014-02-03 17:00 | 2014-01-18 08:00 | 2014-02-03 17:00 | 2014-01-18 08:00 | 2014-02-03 17:00 | 2014-01-29 08:00 | 2014-02-16 17:00 |  | PT_Normal |  |  |  |  | 4nv3jBQgRQaiPjlvi0cOMg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41390 | N | N | 15 | FIRST FLOORS |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1350 | LABOR- SUBCONTRACTOR
%R | 501598 | 6359 | 124704 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARFF3350 | Granite - Stair case flooring & Skirting | 8178 | 16 | 16 | 160 | 0 | 150 | 150 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-23 08:00 | 2014-02-16 17:00 |  | 2014-01-21 08:00 | 2014-02-13 17:00 | 2014-01-21 08:00 | 2014-02-13 17:00 | 2014-01-21 08:00 | 2014-02-13 17:00 | 2014-01-23 08:00 | 2014-02-16 17:00 |  | PT_Normal |  |  |  |  | PnZe7dxkRyuj2qnyhUdl+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41390 | N | N | 15 | FIRST FLOORS |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 150 | LABOR- SUBCONTRACTOR
%R | 501599 | 6359 | 124704 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARFF3345 | Fixing of Suspension systems | 8178 | 0 | 0 | 160 | 0 | 1434.75 | 1434.75 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-02-05 17:00 |  | 2014-01-14 08:00 | 2014-02-05 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | HIorjQziR0SDR7uHYb8nzA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41390 | N | N | 15 | FIRST FLOORS |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1434.75 | LABOR- SUBCONTRACTOR
%R | 501600 | 6359 | 124704 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARFF3355 | Aluminum tile false ceiling | 8178 | 16 | 0 | 160 | 0 | 181.25 | 181.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-28 08:00 | 2014-02-20 17:00 |  | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-01-28 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | ZMDzOXWWSiuB6LllctQQDA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41390 | N | N | 15 | FIRST FLOORS |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 181.25 | LABOR- SUBCONTRACTOR
%R | 501601 | 6359 | 124704 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARFF3360 | Gypsum board false ceiling | 8178 | 0 | 0 | 200 | 0 | 1298.71 | 1298.71 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-20 17:00 |  | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | sFwtpqttSEuRM2WeBBjL8g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41390 | N | N | 15 | FIRST FLOORS |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1298.71 | LABOR- SUBCONTRACTOR
%R | 501602 | 6359 | 124704 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARFF3365 | Wooden door | 8178 | 0 | 0 | 120 | 0 | 330 | 330 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-02-24 17:00 |  | 2014-02-06 08:00 | 2014-02-24 17:00 | 2014-02-06 08:00 | 2014-02-24 17:00 | 2014-02-06 08:00 | 2014-02-24 17:00 | 2014-02-06 08:00 | 2014-02-24 17:00 |  | PT_Normal |  |  |  |  | tsbB8IdsRbKdqqZcsAEKXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41390 | N | N | 15 | FIRST FLOORS |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 330 | LABOR- SUBCONTRACTOR
%R | 501603 | 6359 | 124704 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARFF3370 | Aluminum Door | 8178 | 0 | 0 | 160 | 0 | 99 | 99 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-10 17:00 |  | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | S/vD3Z9ERFmlwHD6Xj6kpw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41390 | N | N | 15 | FIRST FLOORS |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 99 | LABOR- SUBCONTRACTOR
%R | 501604 | 6359 | 124704 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARFF3380 | Aluminum windows | 8178 | 88 | 88 | 160 | 0 | 264 | 264 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-30 17:00 |  | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | DtcnTPm4SWuzZ8wsWPOCuw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41390 | N | N | 15 | FIRST FLOORS |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 264 | LABOR- SUBCONTRACTOR
%R | 501605 | 6359 | 124704 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARFF3375 | Carpentry & Joinery Works | 8178 | 0 | 0 | 200 | 0 | 300 | 300 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-24 17:00 |  | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | GnbF19VOTPWyAbm5UEOVWQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41390 | N | N | 15 | FIRST FLOORS |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 150 | LABOR- SUBCONTRACTOR
%R | 501606 | 6359 | 124704 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARFF3390 | Installation of Granite Counter Top | 8171 | 0 | 0 | 160 | 0 | 132 | 132 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-10 08:00 | 2014-04-01 17:00 |  | 2014-03-10 08:00 | 2014-04-01 17:00 | 2014-03-10 08:00 | 2014-04-01 17:00 | 2014-03-10 08:00 | 2014-04-01 17:00 | 2014-03-10 08:00 | 2014-04-01 17:00 |  | PT_Normal |  |  |  |  | yW7eDwX0SnaRWE3cfqEPmA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41390 | N | N | 15 | FIRST FLOORS |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 132 | GRANITE MASON SK
%R | 501607 | 6359 | 124704 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARFF3385 | Handrail & Balustrade | 8178 | 0 | 0 | 160 | 0 | 275 | 275 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-30 17:00 |  | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | 7mmiObvjSByqRbnAXNzt9w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41390 | N | N | 15 | FIRST FLOORS |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 275 | LABOR- SUBCONTRACTOR
%R | 501608 | 6359 | 124704 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARFF3395 | Final Painting | 8178 | 0 | 0 | 200 | 0 | 3644.75 | 3644.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | 2meuVwm2RaqfNHBbZeLFUg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41390 | N | N | 15 | FIRST FLOORS |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 3644.75 | LABOR- SUBCONTRACTOR
%R | 501609 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3020 | Ceramic Wall Tiling | 8170 | 280 | 0 | 200 | 0 | 2603.5 | 2603.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-12 08:00 | 2014-01-11 17:00 |  | 2013-11-02 08:00 | 2013-11-30 17:00 | 2013-11-02 08:00 | 2013-11-30 17:00 | 2013-11-02 08:00 | 2013-11-30 17:00 | 2013-12-12 08:00 | 2014-01-11 17:00 |  | PT_Normal |  |  |  |  | w0hVq1lxR1WLJkGRUTxxgQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 2603.5 | TILE MASON SK
%R | 501610 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3025 | Porcelain Tile flooring | 8170 | 280 | 0 | 200 | 0 | 1787.5 | 1787.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-19 08:00 | 2014-01-16 17:00 |  | 2013-11-07 08:00 | 2013-12-05 17:00 | 2013-11-07 08:00 | 2013-12-05 17:00 | 2013-11-07 08:00 | 2013-12-05 17:00 | 2013-12-19 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | L0JnqvIbRnqeqX8V96jPHg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1787.5 | TILE MASON SK
%R | 501611 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3040 | Cobble Tile flooring | 8170 | 320 | 0 | 120 | 0 | 68.75 | 68.75 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-21 08:00 | 2014-02-06 17:00 |  | 2013-12-04 08:00 | 2013-12-22 17:00 | 2013-12-04 08:00 | 2013-12-22 17:00 | 2013-12-04 08:00 | 2013-12-22 17:00 | 2014-01-21 08:00 | 2014-02-06 17:00 |  | PT_Normal |  |  |  |  | J+cmMGQ3Rt+isdCI2SPX3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 68.75 | TILE MASON SK
%R | 501612 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 336 | 16 | 120 | 0 | 45.5 | 45.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-02-02 17:00 |  | 2013-11-27 08:00 | 2013-12-14 17:00 | 2013-11-27 08:00 | 2013-12-14 17:00 | 2013-11-27 08:00 | 2013-12-14 17:00 | 2014-01-16 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | 3bVDxWUNQs+gJ5ndEkpffg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 45.5 | TILE MASON SK
%R | 501613 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 320 | 0 | 160 | 0 | 506.25 | 506.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-29 08:00 | 2014-02-22 17:00 |  | 2013-12-12 08:00 | 2014-01-05 17:00 | 2013-12-12 08:00 | 2014-01-05 17:00 | 2013-12-12 08:00 | 2014-01-05 17:00 | 2014-01-29 08:00 | 2014-02-22 17:00 |  | PT_Normal |  |  |  |  | /jP55/PpQRWlVkTU6G3xKw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 506.25 | GRANITE MASON SK
%R | 501614 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3045 | Fixing of Suspension systems | 8178 | 280 | 0 | 160 | 0 | 1434.75 | 1434.75 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-06 08:00 | 2014-01-28 17:00 |  | 2013-11-25 08:00 | 2013-12-17 17:00 | 2013-11-25 08:00 | 2013-12-17 17:00 | 2013-11-25 08:00 | 2013-12-17 17:00 | 2014-01-06 08:00 | 2014-01-28 17:00 |  | PT_Normal |  |  |  |  | h/Vvid5STs+PkmwMDOsjqQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1434.75 | LABOR- SUBCONTRACTOR
%R | 501615 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3055 | Aluminum tile false ceiling | 8178 | 312 | 24 | 200 | 0 | 156.25 | 156.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-19 08:00 | 2014-02-17 17:00 |  | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 |  | PT_Normal |  |  |  |  | wK2O/mj1QTS5NWomTPz+Jg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 156.25 | LABOR- SUBCONTRACTOR
%R | 501616 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3060 | Gypsum board false ceiling | 8178 | 280 | 0 | 200 | 0 | 1298.71 | 1298.71 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-18 08:00 | 2014-02-16 17:00 |  | 2013-12-07 08:00 | 2014-01-05 17:00 | 2013-12-07 08:00 | 2014-01-05 17:00 | 2013-12-07 08:00 | 2014-01-05 17:00 | 2014-01-18 08:00 | 2014-02-16 17:00 |  | PT_Normal |  |  |  |  | rK7RZCajT2KTZQKCWPWmLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1298.71 | LABOR- SUBCONTRACTOR
%R | 501617 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3065 | Wooden door | 8178 | 320 | 0 | 120 | 0 | 412.5 | 412.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-03-02 17:00 |  | 2013-12-28 08:00 | 2014-01-13 17:00 | 2013-12-28 08:00 | 2014-01-13 17:00 | 2013-12-28 08:00 | 2014-01-13 17:00 | 2014-02-13 08:00 | 2014-03-02 17:00 |  | PT_Normal |  |  |  |  | Y6jjndZiQ7K3Ezhb+pflnw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 412.5 | LABOR- SUBCONTRACTOR
%R | 501618 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3070 | Aluminum doors | 8178 | 320 | 0 | 120 | 0 | 99 | 99 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-19 08:00 | 2014-03-08 17:00 |  | 2014-01-02 08:00 | 2014-01-19 17:00 | 2014-01-02 08:00 | 2014-01-19 17:00 | 2014-01-02 08:00 | 2014-01-19 17:00 | 2014-02-19 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | fYJ8ts/iR9OT3eLa9WQ84A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 99 | LABOR- SUBCONTRACTOR
%R | 501619 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3080 | Aluminum windows | 8178 | 400 | 40 | 160 | 0 | 220 | 220 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-10 08:00 | 2014-04-01 17:00 |  | 2014-01-09 08:00 | 2014-02-01 17:00 | 2014-01-09 08:00 | 2014-02-01 17:00 | 2014-01-09 08:00 | 2014-02-01 17:00 | 2014-03-10 08:00 | 2014-04-01 17:00 |  | PT_Normal |  |  |  |  | hn4DKDpWTlinUbTFEd+W4g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 220 | LABOR- SUBCONTRACTOR
%R | 501620 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3075 | Carpentry & Joinery Works | 8178 | 320 | 0 | 160 | 0 | 792 | 792 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-25 08:00 | 2014-03-19 17:00 |  | 2014-01-08 08:00 | 2014-01-30 17:00 | 2014-01-08 08:00 | 2014-01-30 17:00 | 2014-01-08 08:00 | 2014-01-30 17:00 | 2014-02-25 08:00 | 2014-03-19 17:00 |  | PT_Normal |  |  |  |  | Ld8XUHbhR82YkVQGISqxgA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 792 | LABOR- SUBCONTRACTOR
%R | 501621 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3090 | Installation of Granite Counter Top | 8171 | 320 | 0 | 120 | 0 | 132 | 132 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-10 08:00 | 2014-03-26 17:00 |  | 2014-01-21 08:00 | 2014-02-06 17:00 | 2014-01-21 08:00 | 2014-02-06 17:00 | 2014-01-21 08:00 | 2014-02-06 17:00 | 2014-03-10 08:00 | 2014-03-26 17:00 |  | PT_Normal |  |  |  |  | 6j6yXIrqTpej48YnH5mZyw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 132 | GRANITE MASON SK
%R | 501622 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3085 | S.S.Balustrade | 8178 | 360 | 40 | 160 | 0 | 47.25 | 47.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-04-02 17:00 |  | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-03-11 08:00 | 2014-04-02 17:00 |  | PT_Normal |  |  |  |  | at4FmkHZSSqfYT4PmXX21Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 47.25 | LABOR- SUBCONTRACTOR
%R | 501623 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3095 | Final Painting | 8178 | 320 | 0 | 200 | 0 | 4136.55 | 4136.55 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | jMHkMF1oSWarqgVaLu8efA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01; period 2: 2014-AP03 |  | 2068.275 | LABOR- SUBCONTRACTOR
%R | 501624 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3000 | Block work | 8168 | 280 | 0 | 200 | 0 | 7112.5 | 7112.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-28 08:00 | 2013-11-25 17:00 |  | 2013-09-15 08:00 | 2013-10-13 17:00 | 2013-09-15 08:00 | 2013-10-13 17:00 | 2013-09-15 08:00 | 2013-10-13 17:00 | 2013-10-28 08:00 | 2013-11-25 17:00 |  | PT_Normal |  |  |  |  | tvuLjp8+SCSLKlgP2YgpMQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 7112.5 | BLOCK MASON SK
%R | 501625 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3005 | Plastering work | 8169 | 280 | 0 | 200 | 0 | 6268.75 | 6268.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-19 08:00 | 2013-12-17 17:00 |  | 2013-10-07 08:00 | 2013-11-06 17:00 | 2013-10-07 08:00 | 2013-11-06 17:00 | 2013-10-07 08:00 | 2013-11-06 17:00 | 2013-11-19 08:00 | 2013-12-17 17:00 |  | PT_Normal |  |  |  |  | wC0KHwdoTXOM+VlH32f3+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 6268.75 | PLASTER MASON SK
%R | 501626 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3010 | Flooring screed | 8164 | 344 | 64 | 168 | 0 | 1234.75 | 1234.75 | 168 | 0 | 0 | 0 |  |  |  | 2013-12-07 08:00 | 2013-12-31 17:00 |  | 2013-10-15 08:00 | 2013-11-10 17:00 | 2013-10-15 08:00 | 2013-11-10 17:00 | 2013-10-15 08:00 | 2013-11-10 17:00 | 2013-12-07 08:00 | 2013-12-31 17:00 |  | PT_Normal |  |  |  |  | x0d9l4n+TgivUWISAHj2jg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1234.75 | SCREED MASON SK
%R | 501627 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 280 | 0 | 120 | 0 | 582 | 582 | 120 | 0 | 0 | 0 |  |  |  | 2013-12-07 08:00 | 2013-12-24 17:00 |  | 2013-10-27 08:00 | 2013-11-12 17:00 | 2013-10-27 08:00 | 2013-11-12 17:00 | 2013-10-27 08:00 | 2013-11-12 17:00 | 2013-12-07 08:00 | 2013-12-24 17:00 |  | PT_Normal |  |  |  |  | C8n78WqOSe2f/lEozxLDaA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 582 | LABOR- SUBCONTRACTOR
%R | 501628 | 6359 | 124705 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ARGF3030 | Paint First coat | 8178 | 344 | 0 | 200 | 0 | 4136.55 | 4136.55 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-23 08:00 | 2014-01-20 17:00 |  | 2013-11-02 08:00 | 2013-11-30 17:00 | 2013-11-02 08:00 | 2013-11-30 17:00 | 2013-11-02 08:00 | 2013-11-30 17:00 | 2013-12-23 08:00 | 2014-01-20 17:00 |  | PT_Normal |  |  |  |  | G3VOghAVQUyaK9DyJYe8rg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41380 | N | N | 10 | GROUND FLOOR |  | 124702 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 4136.55 | LABOR- SUBCONTRACTOR
%R | 501629 | 6359 | 124707 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2WTEX5030 | Excavation | 8177 | 464 | 0 | 160 | 0 | 116 | 116 | 160 | 80 | 0 | 80 |  |  |  | 2014-01-14 08:00 | 2014-02-05 17:00 |  | 2013-11-06 08:00 | 2013-11-28 17:00 | 2013-11-06 08:00 | 2013-11-28 17:00 | 2013-11-06 08:00 | 2013-11-28 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | 1nnfuHycS7G6FtBwc88/7Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41600 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124706 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 116 | LABOR - CIVIL
%R | 501630 | 6359 | 124707 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2WTEX5035 | Construction of Raft | 8167 | 464 | 0 | 200 | 0 | 210 | 210 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-20 08:00 | 2014-02-18 17:00 |  | 2013-11-12 08:00 | 2013-12-10 17:00 | 2013-11-12 08:00 | 2013-12-10 17:00 | 2013-11-12 08:00 | 2013-12-10 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 |  | PT_Normal |  |  |  |  | PWXyMk3dQsaUtDJaHK/QDg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41600 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124706 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 210 | CONCRETE MASON SK
%R | 501631 | 6359 | 124707 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2WTEX5040 | Block works & Plastering | 8168 | 464 | 0 | 200 | 0 | 2442 | 2442 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-29 08:00 | 2014-02-27 17:00 |  | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 |  | PT_Normal |  |  |  |  | mOBf8tDwSWavErhOwBCmXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41600 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124706 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11; period 2: 2013-AP12 |  | 1221 | BLOCK MASON SK
%R | 501632 | 6359 | 124707 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2WTEX5045 | Flooring & Painting | 8164 | 464 | 296 | 200 | 0 | 900 | 900 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-12 17:00 |  | 2013-12-04 08:00 | 2014-01-02 17:00 | 2013-12-04 08:00 | 2014-01-02 17:00 | 2013-12-04 08:00 | 2014-01-02 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 |  | PT_Normal |  |  |  |  | vxWVRZ5UTG6cMp9beHM6zg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41600 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124706 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 900 | SCREED MASON SK
%R | 501633 | 6359 | 124707 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2WTEX5050 | Installation of Steel Gate | 8178 | 168 | 16 | 160 | 0 | 84 | 84 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-24 17:00 |  | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | zdoqgfGsS668IECTXJA09g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41600 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124706 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 84 | LABOR- SUBCONTRACTOR
%R | 501634 | 6359 | 124707 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2WTEX5060 | Structural steel & SS Shed cover installation | 8178 | 152 | 0 | 200 | 0 | 588 | 588 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-04-05 17:00 |  | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-03-08 08:00 | 2014-04-05 17:00 |  | PT_Normal |  |  |  |  | bkCR/tMGRSC1aXO8PrDY9A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41600 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124706 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 294 | LABOR- SUBCONTRACTOR
%R | 501635 | 6359 | 124707 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2WTEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 152 | 0 | 200 | 0 | 152.4 | 152.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | OnjxNIzETueVxJjoHuuT9g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41600 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124706 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 76.2 | LABOR- SUBCONTRACTOR
%R | 501636 | 6359 | 124707 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2WTEX5080 | Domestic Water Tank Electrical works | 8178 | 464 | 0 | 200 | 0 | 175 | 175 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-03-08 17:00 |  | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | KSHbnN0NQ+qZCk67PrEPig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41600 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124706 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 175 | LABOR- SUBCONTRACTOR
%R | 501637 | 6359 | 124707 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2WTEX5070 | Domestic Water Tank Plumbings works | 8178 | 464 | 0 | 200 | 0 | 200 | 200 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-03-08 17:00 |  | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | G4a9YLzVRlmKrpDIlHjqKQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41600 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124706 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 200 | LABOR- SUBCONTRACTOR
%R | 501638 | 6359 | 124707 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2WTEX5075 | Domestic Water Tank AC works | 8178 | 464 | 0 | 200 | 0 | 175 | 175 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-03-08 17:00 |  | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | 9yQ4cePTTIGL74WbWvT2MA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41600 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124706 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 175 | LABOR- SUBCONTRACTOR
%R | 501639 | 6359 | 124707 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2WTEX5085 | Domestic Water Tank Firefighting works | 8178 | 464 | 0 | 200 | 0 | 118.8 | 118.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-03-08 17:00 |  | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | 3BweqIE1SZCQEI83i+oy8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41600 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124706 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 118.8 | LABOR- SUBCONTRACTOR
%R | 501640 | 6359 | 124708 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2MSEX5020 | Construction Entrance Ramp | 8164 | 168 | 0 | 200 | 0 | 216 | 216 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-03-01 17:00 |  | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | FPEWukrLS7Cf4bn08j2cQA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41590 | N | N | 10 | MISCELLANEOUS |  | 124706 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 216 | SCREED MASON SK
%R | 501641 | 6359 | 124708 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2MSEX5025 | SS.Handrails and Balustrades | 8178 | 168 | 0 | 160 | 0 | 108 | 108 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-12 17:00 |  | 2014-01-23 08:00 | 2014-02-16 17:00 | 2014-01-23 08:00 | 2014-02-16 17:00 | 2014-01-23 08:00 | 2014-02-16 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 |  | PT_Normal |  |  |  |  | ODIJB/T0Q6idBPRAMv56ZQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41590 | N | N | 10 | MISCELLANEOUS |  | 124706 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 108 | LABOR- SUBCONTRACTOR
%R | 501642 | 6359 | 124708 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2MSEX5015 | Construction of grease Trap | 8178 | 416 | 0 | 160 | 0 | 42 | 42 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-02 08:00 | 2014-02-25 17:00 |  | 2013-12-02 08:00 | 2013-12-25 17:00 | 2013-12-02 08:00 | 2013-12-25 17:00 | 2013-12-02 08:00 | 2013-12-25 17:00 | 2014-02-02 08:00 | 2014-02-25 17:00 |  | PT_Normal |  |  |  |  | f/IGSabzRUWdS9XyuZgkdA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41590 | N | N | 10 | MISCELLANEOUS |  | 124706 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 42 | LABOR- SUBCONTRACTOR
%R | 501643 | 6359 | 124708 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2MSEX5000 | Construction of Manholes | 8178 | 416 | 0 | 200 | 0 | 132 | 132 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-30 08:00 | 2014-01-27 17:00 |  | 2013-10-29 08:00 | 2013-11-26 17:00 | 2013-10-29 08:00 | 2013-11-26 17:00 | 2013-10-29 08:00 | 2013-11-26 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 |  | PT_Normal |  |  |  |  | C1bdmfSQQ/iaCn1MuBjxnA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41590 | N | N | 10 | MISCELLANEOUS |  | 124706 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 132 | LABOR- SUBCONTRACTOR
%R | 501644 | 6359 | 124708 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2MSEX5005 | Construction of Soak pit, Chambers | 8177 | 416 | 0 | 200 | 0 | 275 | 275 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-02-10 17:00 |  | 2013-11-12 08:00 | 2013-12-10 17:00 | 2013-11-12 08:00 | 2013-12-10 17:00 | 2013-11-12 08:00 | 2013-12-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | ChK0yiFpTFagduveDLemcg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41590 | N | N | 10 | MISCELLANEOUS |  | 124706 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 275 | LABOR - CIVIL
%R | 501645 | 6359 | 124708 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2MSEX5010 | Telephone cable laying | 8177 | 416 | 248 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-26 08:00 | 2014-03-26 17:00 |  | 2013-12-26 08:00 | 2014-01-23 17:00 | 2013-12-26 08:00 | 2014-01-23 17:00 | 2013-12-26 08:00 | 2014-01-23 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 |  | PT_Normal |  |  |  |  | dSKlUI+fSz+MPj7iw4m0OA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41590 | N | N | 10 | MISCELLANEOUS |  | 124706 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 500 | LABOR - CIVIL
%R | 501646 | 6359 | 124711 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STUG1045 | Construction of slab on grade | 8163 | 0 | 0 | 200 | 0 | 3327.5 | 3327.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-16 08:00 | 2013-07-14 17:00 |  | 2013-06-16 08:00 | 2013-07-14 17:00 | 2013-06-16 08:00 | 2013-07-14 17:00 | 2013-06-16 08:00 | 2013-07-14 17:00 | 2013-06-16 08:00 | 2013-07-14 17:00 |  | PT_Normal |  |  |  |  | h2m1VizHTeeTXG2BgphGjA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41310 | N | N | 10 | UPTO GRADE SLAB |  | 124710 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 3327.5 | BLINDING MASON SK
%R | 501647 | 6359 | 124711 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STUG1000 | Footing Excavation | 8177 | 0 | 0 | 200 | 0 | 1556 | 1556 | 200 | 732 | 0 | 732 |  |  |  | 2013-02-28 08:00 | 2013-03-28 17:00 |  | 2013-02-28 08:00 | 2013-03-28 17:00 | 2013-02-28 08:00 | 2013-03-28 17:00 | 2013-02-28 08:00 | 2013-03-28 17:00 | 2013-02-28 08:00 | 2013-03-28 17:00 |  | PT_Normal |  |  |  |  | dzQ4FUyxSN6/SvOXr/QsrA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41310 | N | N | 10 | UPTO GRADE SLAB |  | 124710 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 778 | LABOR - CIVIL
%R | 501648 | 6359 | 124711 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STUG1005 | Footing Antitermite | 8178 | 0 | 0 | 184 | 0 | 634.25 | 634.25 | 184 | 0 | 0 | 0 |  |  |  | 2013-03-11 08:00 | 2013-04-06 17:00 |  | 2013-03-11 08:00 | 2013-04-06 17:00 | 2013-03-11 08:00 | 2013-04-06 17:00 | 2013-03-11 08:00 | 2013-04-06 17:00 | 2013-03-11 08:00 | 2013-04-06 17:00 |  | PT_Normal |  |  |  |  | y2J9Xv+IT0+5D08BKs0xmQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41310 | N | N | 10 | UPTO GRADE SLAB |  | 124710 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 634.25 | LABOR- SUBCONTRACTOR
%R | 501649 | 6359 | 124711 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STUG1010 | Footing Blinding | 8163 | 0 | 0 | 184 | 0 | 588 | 588 | 184 | 0 | 0 | 0 |  |  |  | 2013-03-14 08:00 | 2013-04-09 17:00 |  | 2013-03-14 08:00 | 2013-04-09 17:00 | 2013-03-14 08:00 | 2013-04-09 17:00 | 2013-03-14 08:00 | 2013-04-09 17:00 | 2013-03-14 08:00 | 2013-04-09 17:00 |  | PT_Normal |  |  |  |  | r0x0sfnJSsmOM1TASTn60g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41310 | N | N | 10 | UPTO GRADE SLAB |  | 124710 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 588 | BLINDING MASON SK
%R | 501650 | 6359 | 124711 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STUG1015 | Footing Waterproofing & Screed | 8164 | 0 | 0 | 200 | 0 | 1368.5 | 1368.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-03-20 08:00 | 2013-04-17 17:00 |  | 2013-03-20 08:00 | 2013-04-17 17:00 | 2013-03-20 08:00 | 2013-04-17 17:00 | 2013-03-20 08:00 | 2013-04-17 17:00 | 2013-03-20 08:00 | 2013-04-17 17:00 |  | PT_Normal |  |  |  |  | cVK7ZCIHQVG5OD7SvuZ6ug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41310 | N | N | 10 | UPTO GRADE SLAB |  | 124710 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 1368.5 | SCREED MASON SK
%R | 501651 | 6359 | 124711 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STUG1020 | Construction of foundations | 8165 | 0 | 0 | 160 | 0 | 4817.75 | 4817.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-04-04 08:00 | 2013-04-27 17:00 |  | 2013-04-04 08:00 | 2013-04-27 17:00 | 2013-04-04 08:00 | 2013-04-27 17:00 | 2013-04-04 08:00 | 2013-04-27 17:00 | 2013-04-04 08:00 | 2013-04-27 17:00 |  | PT_Normal |  |  |  |  | h2Vgcdt1S8Sha8qHM/UD/A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41310 | N | N | 10 | UPTO GRADE SLAB |  | 124710 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 4817.75 | STEEL FIXERS SK
%R | 501652 | 6359 | 124711 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STUG1025 | Construction of neck of columns | 8165 | 0 | 0 | 200 | 0 | 1400 | 1400 | 200 | 0 | 0 | 0 |  |  |  | 2013-04-14 08:00 | 2013-05-12 17:00 |  | 2013-04-14 08:00 | 2013-05-12 17:00 | 2013-04-14 08:00 | 2013-05-12 17:00 | 2013-04-14 08:00 | 2013-05-12 17:00 | 2013-04-14 08:00 | 2013-05-12 17:00 |  | PT_Normal |  |  |  |  | jHGxjmxURDygS5kATnCXZg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41310 | N | N | 10 | UPTO GRADE SLAB |  | 124710 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 1400 | STEEL FIXERS SK
%R | 501653 | 6359 | 124711 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STUG1030 | Waterproofing Footing & Neck Column | 8178 | 0 | 0 | 200 | 0 | 213.5 | 213.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-04-23 08:00 | 2013-05-21 17:00 |  | 2013-04-23 08:00 | 2013-05-21 17:00 | 2013-04-23 08:00 | 2013-05-21 17:00 | 2013-04-23 08:00 | 2013-05-21 17:00 | 2013-04-23 08:00 | 2013-05-21 17:00 |  | PT_Normal |  |  |  |  | XeWGFmdLSjCYc6o+Kux+8A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41310 | N | N | 10 | UPTO GRADE SLAB |  | 124710 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 213.5 | LABOR- SUBCONTRACTOR
%R | 501654 | 6359 | 124711 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 0 | 0 | 200 | 0 | 2560 | 2560 | 200 | 2200 | 0 | 2200 |  |  |  | 2013-05-04 08:00 | 2013-06-01 17:00 |  | 2013-05-04 08:00 | 2013-06-01 17:00 | 2013-05-04 08:00 | 2013-06-01 17:00 | 2013-05-04 08:00 | 2013-06-01 17:00 | 2013-05-04 08:00 | 2013-06-01 17:00 |  | PT_Normal |  |  |  |  | 7DJhwwbNRIK+ADSPH5h32g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41310 | N | N | 10 | UPTO GRADE SLAB |  | 124710 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 2560 | LABOR - CIVIL
%R | 501655 | 6359 | 124711 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STUG1040 | Construction of Grade Beams | 8163 | 0 | 0 | 200 | 0 | 4745 | 4745 | 200 | 0 | 0 | 0 |  |  |  | 2013-05-20 08:00 | 2013-06-17 17:00 |  | 2013-05-20 08:00 | 2013-06-17 17:00 | 2013-05-20 08:00 | 2013-06-17 17:00 | 2013-05-20 08:00 | 2013-06-17 17:00 | 2013-05-20 08:00 | 2013-06-17 17:00 |  | PT_Normal |  |  |  |  | 1SwMi4n+SOWpw0Pd4bABiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41310 | N | N | 10 | UPTO GRADE SLAB |  | 124710 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 4745 | BLINDING MASON SK
%R | 501656 | 6359 | 124713 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STFF2020 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 1615.25 | 1615.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-17 08:00 | 2013-09-14 17:00 |  | 2013-08-17 08:00 | 2013-09-14 17:00 | 2013-08-17 08:00 | 2013-09-14 17:00 | 2013-08-17 08:00 | 2013-09-14 17:00 | 2013-08-17 08:00 | 2013-09-14 17:00 |  | PT_Normal |  |  |  |  | CiebM0+YRcKEzCMrwfr//w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41340 | N | N | 15 | FIRST FLOORS |  | 124712 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 1615.25 | STEEL FIXERS SK
%R | 501657 | 6359 | 124713 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STFF2025 | Column-Concrete | 8167 | 0 | 0 | 192 | 0 | 87.5 | 87.5 | 192 | 0 | 0 | 0 |  |  |  | 2013-08-27 08:00 | 2013-09-23 17:00 |  | 2013-08-27 08:00 | 2013-09-23 17:00 | 2013-08-27 08:00 | 2013-09-23 17:00 | 2013-08-27 08:00 | 2013-09-23 17:00 | 2013-08-27 08:00 | 2013-09-23 17:00 |  | PT_Normal |  |  |  |  | 9NUa/FFGQv6nvBzt6LsD4A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41340 | N | N | 15 | FIRST FLOORS |  | 124712 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 87.5 | CONCRETE MASON SK
%R | 501658 | 6359 | 124713 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 10081.75 | 10081.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-11 08:00 | 2013-10-09 17:00 |  | 2013-09-11 08:00 | 2013-10-09 17:00 | 2013-09-11 08:00 | 2013-10-09 17:00 | 2013-09-11 08:00 | 2013-10-09 17:00 | 2013-09-11 08:00 | 2013-10-09 17:00 |  | PT_Normal |  |  |  |  | Ah+HSY3XTA6cycuQGPIC3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41340 | N | N | 15 | FIRST FLOORS |  | 124712 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 10081.75 | STEEL FIXERS SK
%R | 501659 | 6359 | 124713 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 0 | 0 | 120 | 0 | 731.5 | 731.5 | 120 | 0 | 0 | 0 |  |  |  | 2013-10-02 08:00 | 2013-10-21 17:00 |  | 2013-10-02 08:00 | 2013-10-21 17:00 | 2013-10-02 08:00 | 2013-10-21 17:00 | 2013-10-02 08:00 | 2013-10-21 17:00 | 2013-10-02 08:00 | 2013-10-21 17:00 |  | PT_Normal |  |  |  |  | U4jiQLB6T6WcV1j7XKqlow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41340 | N | N | 15 | FIRST FLOORS |  | 124712 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 731.5 | CONCRETE MASON SK
%R | 501660 | 6359 | 124714 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STRF2040 | Column-Rebar & Formwork | 8165 | 288 | 0 | 144 | 0 | 549.5 | 549.5 | 144 | 0 | 0 | 0 |  |  |  | 2013-11-18 08:00 | 2013-12-08 17:00 |  | 2013-10-05 08:00 | 2013-10-27 17:00 | 2013-10-05 08:00 | 2013-10-27 17:00 | 2013-10-05 08:00 | 2013-10-27 17:00 | 2013-11-18 08:00 | 2013-12-08 17:00 |  | PT_Normal |  |  |  |  | yIKChX2NQ42VLZaG6g9Jsg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41350 | N | N | 20 | ROOF |  | 124712 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 549.5 | STEEL FIXERS SK
%R | 501661 | 6359 | 124714 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STRF2045 | Column-Concrete | 8167 | 408 | 0 | 136 | 0 | 21 | 21 | 136 | 0 | 0 | 0 |  |  |  | 2013-12-09 08:00 | 2013-12-29 17:00 |  | 2013-10-08 08:00 | 2013-10-29 17:00 | 2013-10-08 08:00 | 2013-10-29 17:00 | 2013-10-08 08:00 | 2013-10-29 17:00 | 2013-12-09 08:00 | 2013-12-29 17:00 |  | PT_Normal |  |  |  |  | obOC8z7eQP6g9xAXTol0Cg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41350 | N | N | 20 | ROOF |  | 124712 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 21 | CONCRETE MASON SK
%R | 501662 | 6359 | 124714 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STRF2050 | Slab-Rebar & Formwork | 8165 | 408 | 0 | 160 | 0 | 1576.75 | 1576.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-11 08:00 | 2014-01-04 17:00 |  | 2013-10-10 08:00 | 2013-11-04 17:00 | 2013-10-10 08:00 | 2013-11-04 17:00 | 2013-10-10 08:00 | 2013-11-04 17:00 | 2013-12-11 08:00 | 2014-01-04 17:00 |  | PT_Normal |  |  |  |  | 0cH7TqUHQeSC8TknncVkeA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41350 | N | N | 20 | ROOF |  | 124712 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1576.75 | STEEL FIXERS SK
%R | 501663 | 6359 | 124714 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STRF2055 | Slab-Concrete | 8167 | 408 | 0 | 104 | 0 | 175 | 175 | 104 | 0 | 0 | 0 |  |  |  | 2013-12-23 08:00 | 2014-01-06 17:00 |  | 2013-10-23 08:00 | 2013-11-06 17:00 | 2013-10-23 08:00 | 2013-11-06 17:00 | 2013-10-23 08:00 | 2013-11-06 17:00 | 2013-12-23 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | kD+7Ca3jTgGycMc9DVTiVw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41350 | N | N | 20 | ROOF |  | 124712 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 175 | CONCRETE MASON SK
%R | 501664 | 6359 | 124714 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STRF2060 | Construction of Parapets | 8168 | 464 | 0 | 200 | 0 | 1441 | 1441 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-02 08:00 | 2014-01-30 17:00 |  | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 |  | PT_Normal |  |  |  |  | zCoxaNcPQsym0A0/G/Zgnw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41350 | N | N | 20 | ROOF |  | 124712 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1441 | BLOCK MASON SK
%R | 501665 | 6359 | 124714 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STRF2065 | Construction of up stands/Plinth | 8165 | 464 | 0 | 200 | 0 | 283.5 | 283.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-08 08:00 | 2014-02-05 17:00 |  | 2013-10-31 08:00 | 2013-11-28 17:00 | 2013-10-31 08:00 | 2013-11-28 17:00 | 2013-10-31 08:00 | 2013-11-28 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | 22j26i58RaOrUKuDs0GXgA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41350 | N | N | 20 | ROOF |  | 124712 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 283.5 | STEEL FIXERS SK
%R | 501666 | 6359 | 124715 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STGF2000 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 1688.75 | 1688.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-02 08:00 | 2013-07-30 17:00 |  | 2013-07-02 08:00 | 2013-07-30 17:00 | 2013-07-02 08:00 | 2013-07-30 17:00 | 2013-07-02 08:00 | 2013-07-30 17:00 | 2013-07-02 08:00 | 2013-07-30 17:00 |  | PT_Normal |  |  |  |  | uXnJRFGAQRmA/6hzhHSSwg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41330 | N | N | 10 | GROUND FLOOR |  | 124712 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 1688.75 | STEEL FIXERS SK
%R | 501667 | 6359 | 124715 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STGF2005 | Column-Concrete | 8167 | 0 | 0 | 192 | 0 | 101.5 | 101.5 | 192 | 0 | 0 | 0 |  |  |  | 2013-07-11 08:00 | 2013-08-07 17:00 |  | 2013-07-11 08:00 | 2013-08-07 17:00 | 2013-07-11 08:00 | 2013-08-07 17:00 | 2013-07-11 08:00 | 2013-08-07 17:00 | 2013-07-11 08:00 | 2013-08-07 17:00 |  | PT_Normal |  |  |  |  | rKz/zyKBSoG+AywVrP/0pw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41330 | N | N | 10 | GROUND FLOOR |  | 124712 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 101.5 | CONCRETE MASON SK
%R | 501668 | 6359 | 124715 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 10592.75 | 10592.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-27 08:00 | 2013-08-27 17:00 |  | 2013-07-27 08:00 | 2013-08-27 17:00 | 2013-07-27 08:00 | 2013-08-27 17:00 | 2013-07-27 08:00 | 2013-08-27 17:00 | 2013-07-27 08:00 | 2013-08-27 17:00 |  | PT_Normal |  |  |  |  | d3+eYgIFTaqx6kEod13kbg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41330 | N | N | 10 | GROUND FLOOR |  | 124712 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 5296.375 | STEEL FIXERS SK
%R | 501669 | 6359 | 124715 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 0 | 0 | 120 | 0 | 868 | 868 | 120 | 0 | 0 | 0 |  |  |  | 2013-08-14 08:00 | 2013-08-31 17:00 |  | 2013-08-14 08:00 | 2013-08-31 17:00 | 2013-08-14 08:00 | 2013-08-31 17:00 | 2013-08-14 08:00 | 2013-08-31 17:00 | 2013-08-14 08:00 | 2013-08-31 17:00 |  | PT_Normal |  |  |  |  | 4yyiX9qYSKmSg8gEH4FlCA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41330 | N | N | 10 | GROUND FLOOR |  | 124712 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 868 | CONCRETE MASON SK
%R | 501670 | 6359 | 124718 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ACFF4615 | Installation AC Pipes | 8178 | 256 | 8 | 160 | 0 | 340.8 | 340.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-02-05 17:00 |  | 2013-12-07 08:00 | 2013-12-30 17:00 | 2013-12-07 08:00 | 2013-12-30 17:00 | 2013-12-07 08:00 | 2013-12-30 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | TsC1tXxfReWVYwtmPC0mIQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41550 | N | N | 15 | FIRST FLOORS |  | 124717 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 340.8 | LABOR- SUBCONTRACTOR
%R | 501671 | 6359 | 124718 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ACFF4620 | Fixing of Ventilation Equipments | 8178 | 72 | 0 | 200 | 0 | 136.8 | 136.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-15 08:00 | 2014-03-15 17:00 |  | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 |  | PT_Normal |  |  |  |  | QDI47MZURr2/fPsLhZYc0A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41550 | N | N | 15 | FIRST FLOORS |  | 124717 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 68.4 | LABOR- SUBCONTRACTOR
%R | 501672 | 6359 | 124718 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ACFF4625 | Fixing of Split AC | 8178 | 72 | 0 | 160 | 0 | 361.2 | 361.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-30 17:00 |  | 2014-02-25 08:00 | 2014-03-19 17:00 | 2014-02-25 08:00 | 2014-03-19 17:00 | 2014-02-25 08:00 | 2014-03-19 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | TA80Z6QuRa+53M7y8ZJ0Uw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41550 | N | N | 15 | FIRST FLOORS |  | 124717 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 361.2 | LABOR- SUBCONTRACTOR
%R | 501673 | 6359 | 124719 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ACRF4630 | Installation of Refrigerant Pipes | 8178 | 584 | 0 | 200 | 0 | 170.4 | 170.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-04-10 17:00 |  | 2013-12-16 08:00 | 2014-01-14 17:00 | 2013-12-16 08:00 | 2014-01-14 17:00 | 2013-12-16 08:00 | 2014-01-14 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | 0jTRtrlPTPGG6iJCTWEAzw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41560 | N | N | 20 | ROOF |  | 124717 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 170.4 | LABOR- SUBCONTRACTOR
%R | 501674 | 6359 | 124719 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ACRF4635 | Installation of Condensing Unit | 8178 | 112 | 0 | 200 | 0 | 562.8 | 562.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | bRneuAP/S8e8K1efvkw9/w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41560 | N | N | 20 | ROOF |  | 124717 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 562.8 | LABOR- SUBCONTRACTOR
%R | 501675 | 6359 | 124720 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ACGF4600 | Installation AC Pipes | 8178 | 528 | 40 | 160 | 0 | 340.8 | 340.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-09 08:00 | 2014-02-01 17:00 |  | 2013-10-23 08:00 | 2013-11-14 17:00 | 2013-10-23 08:00 | 2013-11-14 17:00 | 2013-10-23 08:00 | 2013-11-14 17:00 | 2014-01-09 08:00 | 2014-02-01 17:00 |  | PT_Normal |  |  |  |  | XwqjSqyNSqO7JdeSPeeWsQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41540 | N | N | 10 | GROUND FLOOR |  | 124717 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 340.8 | LABOR- SUBCONTRACTOR
%R | 501676 | 6359 | 124720 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ACGF4605 | Fixing of Ventilation Equipments | 8178 | 408 | 0 | 200 | 0 | 136.8 | 136.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-15 08:00 | 2014-03-15 17:00 |  | 2013-12-15 08:00 | 2014-01-13 17:00 | 2013-12-15 08:00 | 2014-01-13 17:00 | 2013-12-15 08:00 | 2014-01-13 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 |  | PT_Normal |  |  |  |  | gd4qiKbBT3+tzePuRnVk8w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41540 | N | N | 10 | GROUND FLOOR |  | 124717 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 136.8 | LABOR- SUBCONTRACTOR
%R | 501677 | 6359 | 124720 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ACGF4610 | Fixing of Split AC | 8178 | 408 | 40 | 160 | 0 | 361.2 | 361.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-30 17:00 |  | 2014-01-06 08:00 | 2014-01-28 17:00 | 2014-01-06 08:00 | 2014-01-28 17:00 | 2014-01-06 08:00 | 2014-01-28 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | vqNg/RrqSs2gAORobJdFnQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41540 | N | N | 10 | GROUND FLOOR |  | 124717 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 361.2 | LABOR- SUBCONTRACTOR
%R | 501678 | 6359 | 124722 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 568 | 144 | 120 | 0 | 1623.6 | 1623.6 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-04 08:00 | 2014-03-20 17:00 |  | 2013-12-09 08:00 | 2013-12-26 17:00 | 2013-12-09 08:00 | 2013-12-26 17:00 | 2013-12-09 08:00 | 2013-12-26 17:00 | 2014-03-04 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | 6GsqsSNfQg2zOBkvf8ms9A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41520 | N | N | 20 | ROOF |  | 124721 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1623.6 | LABOR- SUBCONTRACTOR
%R | 501679 | 6359 | 124722 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2PLRF4350 | Installation of Rain water Pipes | 8178 | 424 | 80 | 120 | 0 | 82.8 | 82.8 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-03-30 17:00 |  | 2014-01-09 08:00 | 2014-01-26 17:00 | 2014-01-09 08:00 | 2014-01-26 17:00 | 2014-01-09 08:00 | 2014-01-26 17:00 | 2014-03-13 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | FULjPn8iQ+eGlwweFcPa0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41520 | N | N | 20 | ROOF |  | 124721 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 82.8 | LABOR- SUBCONTRACTOR
%R | 501680 | 6359 | 124722 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 112 | 0 | 200 | 0 | 100.8 | 100.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | 4eoFiUBoQtOxfFGjJdtJYA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41520 | N | N | 20 | ROOF |  | 124721 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 100.8 | LABOR- SUBCONTRACTOR
%R | 501681 | 6359 | 124723 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 0 | 0 | 144 | 0 | 2732.4 | 2732.4 | 144 | 0 | 0 | 0 |  |  |  | 2013-11-13 08:00 | 2013-12-03 17:00 |  | 2013-11-13 08:00 | 2013-12-03 17:00 | 2013-11-13 08:00 | 2013-12-03 17:00 | 2013-11-13 08:00 | 2013-12-03 17:00 | 2013-11-13 08:00 | 2013-12-03 17:00 |  | PT_Normal |  |  |  |  | 3DqNoRmUS1+cdqpHY6UHug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41510 | N | N | 15 | FIRST FLOORS |  | 124721 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 2732.4 | LABOR- SUBCONTRACTOR
%R | 501682 | 6359 | 124723 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2PLFF4330 | Installation of Drainage pipes & testing | 8178 | 208 | 56 | 144 | 0 | 216 | 216 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-15 08:00 | 2014-01-05 17:00 |  | 2013-11-14 08:00 | 2013-12-04 17:00 | 2013-11-14 08:00 | 2013-12-04 17:00 | 2013-11-14 08:00 | 2013-12-04 17:00 | 2013-12-15 08:00 | 2014-01-05 17:00 |  | PT_Normal |  |  |  |  | AQ9TGWZnQd2eUS4CXBIsuw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41510 | N | N | 15 | FIRST FLOORS |  | 124721 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 216 | LABOR- SUBCONTRACTOR
%R | 501683 | 6359 | 124723 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2PLFF4335 | Sanitary Fittings & Accessories | 8178 | 112 | 0 | 160 | 0 | 352.8 | 352.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-24 17:00 |  | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | 2jcK2yVpSHu/LSu+NuCZiA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41510 | N | N | 15 | FIRST FLOORS |  | 124721 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 352.8 | LABOR- SUBCONTRACTOR
%R | 501684 | 6359 | 124723 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2PLFF4340 | Installation of Water Heater | 8178 | 112 | 0 | 120 | 0 | 50.4 | 50.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-03-30 17:00 |  | 2014-02-25 08:00 | 2014-03-13 17:00 | 2014-02-25 08:00 | 2014-03-13 17:00 | 2014-02-25 08:00 | 2014-03-13 17:00 | 2014-03-13 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | H3em7B/PSD6qxJPe1jliNA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41510 | N | N | 15 | FIRST FLOORS |  | 124721 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 501685 | 6359 | 124724 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 280 | 0 | 144 | 0 | 2732.4 | 2732.4 | 144 | 0 | 0 | 0 |  |  |  | 2013-11-13 08:00 | 2013-12-03 17:00 |  | 2013-10-01 08:00 | 2013-10-23 17:00 | 2013-10-01 08:00 | 2013-10-23 17:00 | 2013-10-01 08:00 | 2013-10-23 17:00 | 2013-11-13 08:00 | 2013-12-03 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41500 | N | N | 10 | GROUND FLOOR |  | 124721 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 2732.4 | LABOR- SUBCONTRACTOR
%R | 501686 | 6359 | 124724 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2PLGF4310 | Installation of Drainage pipes &testing | 8178 | 448 | 96 | 144 | 0 | 216 | 216 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-08 08:00 | 2013-12-29 17:00 |  | 2013-10-01 08:00 | 2013-10-23 17:00 | 2013-10-01 08:00 | 2013-10-23 17:00 | 2013-10-01 08:00 | 2013-10-23 17:00 | 2013-12-08 08:00 | 2013-12-29 17:00 |  | PT_Normal |  |  |  |  | wuIhcbPsSdKzfPEZTru4dw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41500 | N | N | 10 | GROUND FLOOR |  | 124721 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 216 | LABOR- SUBCONTRACTOR
%R | 501687 | 6359 | 124724 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2PLGF4315 | Sanitary Fittings & Accessories | 8178 | 512 | 0 | 160 | 0 | 352.8 | 352.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-10 17:00 |  | 2014-01-02 08:00 | 2014-01-25 17:00 | 2014-01-02 08:00 | 2014-01-25 17:00 | 2014-01-02 08:00 | 2014-01-25 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | 8ThgjcKyRaOV9y2aqjre5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41500 | N | N | 10 | GROUND FLOOR |  | 124721 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 352.8 | LABOR- SUBCONTRACTOR
%R | 501688 | 6359 | 124724 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2PLGF4320 | Installation of Water Heater | 8178 | 512 | 80 | 120 | 0 | 50.4 | 50.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-16 17:00 |  | 2014-01-14 08:00 | 2014-01-30 17:00 | 2014-01-14 08:00 | 2014-01-30 17:00 | 2014-01-14 08:00 | 2014-01-30 17:00 | 2014-03-31 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | JcnAE9e1Rk+6QL4eanfvZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41500 | N | N | 10 | GROUND FLOOR |  | 124721 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 501689 | 6359 | 124724 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 0 | 0 | 160 | 0 | 165.6 | 165.6 | 160 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-29 17:00 |  | 2013-06-06 08:00 | 2013-06-29 17:00 | 2013-06-06 08:00 | 2013-06-29 17:00 | 2013-06-06 08:00 | 2013-06-29 17:00 | 2013-06-06 08:00 | 2013-06-29 17:00 |  | PT_Normal |  |  |  |  | KbrS0HFASxejqUl/gJvpsA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41500 | N | N | 10 | GROUND FLOOR |  | 124721 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 165.6 | LABOR- SUBCONTRACTOR
%R | 501690 | 6359 | 124726 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 88 | 0 | 200 | 0 | 1102.8 | 1102.8 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-17 08:00 | 2013-12-15 17:00 |  | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-17 08:00 | 2013-12-15 17:00 |  | PT_Normal |  |  |  |  | x1jrnD/tQe+JnJhxS0Aq7g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41470 | N | N | 15 | FIRST FLOORS |  | 124725 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1102.8 | LABOR- SUBCONTRACTOR
%R | 501691 | 6359 | 124726 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ELFF4040 | Cable tray & trunking installation | 8178 | 264 | 24 | 160 | 0 | 1840.8 | 1840.8 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-25 08:00 | 2014-01-16 17:00 |  | 2013-11-16 08:00 | 2013-12-08 17:00 | 2013-11-16 08:00 | 2013-12-08 17:00 | 2013-11-16 08:00 | 2013-12-08 17:00 | 2013-12-25 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | kvgWwN8+R5SuBmbKI80ZkA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41470 | N | N | 15 | FIRST FLOORS |  | 124725 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1840.8 | LABOR- SUBCONTRACTOR
%R | 501692 | 6359 | 124726 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ELFF4045 | Installation of wiring & Main Cabling | 8178 | 240 | 0 | 200 | 0 | 648 | 648 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-02 08:00 | 2014-01-30 17:00 |  | 2013-11-27 08:00 | 2013-12-26 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 |  | PT_Normal |  |  |  |  | 2IdmqH/URxOFO2cbhng3sg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41470 | N | N | 15 | FIRST FLOORS |  | 124725 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 648 | LABOR- SUBCONTRACTOR
%R | 501693 | 6359 | 124726 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 8 | 0 | 160 | 0 | 188.4 | 188.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-08 08:00 | 2014-03-03 17:00 |  | 2014-02-06 08:00 | 2014-03-02 17:00 | 2014-02-06 08:00 | 2014-03-02 17:00 | 2014-02-06 08:00 | 2014-03-02 17:00 | 2014-02-08 08:00 | 2014-03-03 17:00 |  | PT_Normal |  |  |  |  | pJjInAchQSWJbJTaJxTaSw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41470 | N | N | 15 | FIRST FLOORS |  | 124725 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 188.4 | LABOR- SUBCONTRACTOR
%R | 501694 | 6359 | 124726 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 8 | 0 | 200 | 0 | 2528.4 | 2528.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-22 17:00 |  | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | gL45HN7qRdKzDSHy71aosA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41470 | N | N | 15 | FIRST FLOORS |  | 124725 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 1264.2 | LABOR- SUBCONTRACTOR
%R | 501695 | 6359 | 124726 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 96 | 0 | 200 | 0 | 1612.8 | 1612.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-18 17:00 |  | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | fcPEcm52SYCFU/Y6Wkvs2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41470 | N | N | 15 | FIRST FLOORS |  | 124725 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 806.4 | LABOR- SUBCONTRACTOR
%R | 501696 | 6359 | 124726 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ELFF4050 | Installation of Telephone System | 8178 | 168 | 152 | 200 | 0 | 542.4 | 542.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-26 08:00 | 2014-03-26 17:00 |  | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 |  | PT_Normal |  |  |  |  | OkTerOsYSNWMy67YAeRdeA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41470 | N | N | 15 | FIRST FLOORS |  | 124725 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 271.2 | LABOR- SUBCONTRACTOR
%R | 501697 | 6359 | 124727 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 296 | 0 | 200 | 0 | 2580 | 2580 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-16 17:00 |  | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | hMnLeZOjRKeVCV0ydg7uRA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41460 | N | N | 10 | GROUND FLOOR |  | 124725 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 2580 | LABOR- SUBCONTRACTOR
%R | 501698 | 6359 | 124727 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 392 | 0 | 200 | 0 | 1461.6 | 1461.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-12 17:00 |  | 2013-12-15 08:00 | 2014-01-13 17:00 | 2013-12-15 08:00 | 2014-01-13 17:00 | 2013-12-15 08:00 | 2014-01-13 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 |  | PT_Normal |  |  |  |  | rw/mv9S1Tv61GDbOkmXcZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41460 | N | N | 10 | GROUND FLOOR |  | 124725 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1461.6 | LABOR- SUBCONTRACTOR
%R | 501699 | 6359 | 124727 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ELGF4030 | Installation of Telephone System | 8178 | 288 | 40 | 160 | 0 | 542.4 | 542.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-15 08:00 | 2014-03-09 17:00 |  | 2014-01-02 08:00 | 2014-01-25 17:00 | 2014-01-02 08:00 | 2014-01-25 17:00 | 2014-01-02 08:00 | 2014-01-25 17:00 | 2014-02-15 08:00 | 2014-03-09 17:00 |  | PT_Normal |  |  |  |  | j71or//sRmOwL/zSjL1ULg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41460 | N | N | 10 | GROUND FLOOR |  | 124725 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 542.4 | LABOR- SUBCONTRACTOR
%R | 501700 | 6359 | 124727 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 352 | 0 | 200 | 0 | 1102.8 | 1102.8 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-13 08:00 | 2013-12-11 17:00 |  | 2013-09-21 08:00 | 2013-10-21 17:00 | 2013-09-21 08:00 | 2013-10-21 17:00 | 2013-09-21 08:00 | 2013-10-21 17:00 | 2013-11-13 08:00 | 2013-12-11 17:00 |  | PT_Normal |  |  |  |  | 5pbyL0U8TcCn8jhAHp/1ag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41460 | N | N | 10 | GROUND FLOOR |  | 124725 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 551.4 | LABOR- SUBCONTRACTOR
%R | 501701 | 6359 | 124727 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ELGF4005 | Cable tray & trunking installation | 8178 | 496 | 0 | 160 | 0 | 1840.8 | 1840.8 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-16 08:00 | 2014-01-08 17:00 |  | 2013-10-02 08:00 | 2013-10-27 17:00 | 2013-10-02 08:00 | 2013-10-27 17:00 | 2013-10-02 08:00 | 2013-10-27 17:00 | 2013-12-16 08:00 | 2014-01-08 17:00 |  | PT_Normal |  |  |  |  | PeA8IYtlQzO7UDBU1yJk8w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41460 | N | N | 10 | GROUND FLOOR |  | 124725 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1840.8 | LABOR- SUBCONTRACTOR
%R | 501702 | 6359 | 124727 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ELGF4010 | Installation of wiring & Main Cabling | 8178 | 496 | 216 | 200 | 0 | 648 | 648 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-25 08:00 | 2014-01-22 17:00 |  | 2013-10-10 08:00 | 2013-11-10 17:00 | 2013-10-10 08:00 | 2013-11-10 17:00 | 2013-10-10 08:00 | 2013-11-10 17:00 | 2013-12-25 08:00 | 2014-01-22 17:00 |  | PT_Normal |  |  |  |  | kPIb2BjvTSC3VAhrC+391Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41460 | N | N | 10 | GROUND FLOOR |  | 124725 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 324 | LABOR- SUBCONTRACTOR
%R | 501703 | 6359 | 124727 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 288 | 0 | 160 | 0 | 222 | 222 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-02 08:00 | 2014-02-25 17:00 |  | 2013-12-22 08:00 | 2014-01-13 17:00 | 2013-12-22 08:00 | 2014-01-13 17:00 | 2013-12-22 08:00 | 2014-01-13 17:00 | 2014-02-02 08:00 | 2014-02-25 17:00 |  | PT_Normal |  |  |  |  | 9vygB8BuSlCjpTrSC9RqJQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41460 | N | N | 10 | GROUND FLOOR |  | 124725 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 222 | LABOR- SUBCONTRACTOR
%R | 501704 | 6359 | 124728 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ELRF4070 | Installation of Isolator | 8178 | 16 | 0 | 144 | 0 | 309.6 | 309.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-03 17:00 |  | 2014-03-12 08:00 | 2014-04-01 17:00 | 2014-03-12 08:00 | 2014-04-01 17:00 | 2014-03-12 08:00 | 2014-04-01 17:00 | 2014-03-15 08:00 | 2014-04-03 17:00 |  | PT_Normal |  |  |  |  | C93oFcE+RomdU3O0JmMleA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41480 | N | N | 20 | ROOF |  | 124725 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 309.6 | LABOR- SUBCONTRACTOR
%R | 501705 | 6359 | 124728 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z2ELRF4075 | Installation of TV Dish Antenna | 8178 | 16 | 16 | 184 | 0 | 4725.6 | 4725.6 | 184 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-16 17:00 |  | 2014-03-19 08:00 | 2014-04-14 17:00 | 2014-03-19 08:00 | 2014-04-14 17:00 | 2014-03-19 08:00 | 2014-04-14 17:00 | 2014-03-22 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | HFV78SjOTZWH5510ao+KOg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41480 | N | N | 20 | ROOF |  | 124725 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 4725.6 | LABOR- SUBCONTRACTOR
%R | 501706 | 6359 | 124731 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5MSEX5020 | Construction Entrance Ramp | 8164 | 168 | 0 | 200 | 0 | 216 | 216 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-27 17:00 |  | 2014-04-05 08:00 | 2014-05-03 17:00 | 2014-04-05 08:00 | 2014-05-03 17:00 | 2014-04-05 08:00 | 2014-05-03 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | 5FWonS4GRAWu4Fp2cCI6iw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42670 | N | N | 10 | MISCELLANEOUS |  | 124730 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 216 | SCREED MASON SK
%R | 501707 | 6359 | 124731 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5MSEX5025 | SS.Handrails and Balustrades | 8178 | 168 | 0 | 160 | 0 | 108 | 108 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-08 17:00 |  | 2014-04-22 08:00 | 2014-05-14 17:00 | 2014-04-22 08:00 | 2014-05-14 17:00 | 2014-04-22 08:00 | 2014-05-14 17:00 | 2014-05-17 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | TGsOHmyUTrm1YiQwn8utuA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42670 | N | N | 10 | MISCELLANEOUS |  | 124730 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 108 | LABOR- SUBCONTRACTOR
%R | 501708 | 6359 | 124731 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5MSEX5015 | Construction of grease Trap | 8178 | 424 | 0 | 160 | 0 | 42 | 42 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-08 08:00 | 2014-05-31 17:00 |  | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-05-08 08:00 | 2014-05-31 17:00 |  | PT_Normal |  |  |  |  | GgZrbfeyRLWGXjs2bsFlXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42670 | N | N | 10 | MISCELLANEOUS |  | 124730 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 42 | LABOR- SUBCONTRACTOR
%R | 501709 | 6359 | 124731 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5MSEX5000 | Construction of Manholes | 8178 | 424 | 0 | 200 | 0 | 132 | 132 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-05 08:00 | 2014-05-03 17:00 |  | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-04-05 08:00 | 2014-05-03 17:00 |  | PT_Normal |  |  |  |  | Yze8L96YSea8uzDZZl3FQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42670 | N | N | 10 | MISCELLANEOUS |  | 124730 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 66 | LABOR- SUBCONTRACTOR
%R | 501710 | 6359 | 124731 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5MSEX5005 | Construction of Soak pit, Chambers | 8177 | 424 | 0 | 200 | 0 | 275 | 275 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-19 08:00 | 2014-05-17 17:00 |  | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 |  | PT_Normal |  |  |  |  | nKYKkXZtRc6qSuWLx9VQaA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42670 | N | N | 10 | MISCELLANEOUS |  | 124730 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 137.5 | LABOR - CIVIL
%R | 501711 | 6359 | 124731 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5MSEX5010 | Telephone cable laying | 8177 | 424 | 208 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-01 08:00 | 2014-06-29 17:00 |  | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 |  | PT_Normal |  |  |  |  | WcXH208SQM28A9nF4bpOog |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42670 | N | N | 10 | MISCELLANEOUS |  | 124730 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 500 | LABOR - CIVIL
%R | 501712 | 6359 | 124732 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5WTEX5040 | Block works & Plastering | 8168 | 464 | 0 | 200 | 0 | 2442 | 2442 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-28 08:00 | 2014-05-26 17:00 |  | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-04-28 08:00 | 2014-05-26 17:00 |  | PT_Normal |  |  |  |  | mRqTkLgtSVuShcIKjF4gSQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42680 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124730 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 1221 | BLOCK MASON SK
%R | 501713 | 6359 | 124732 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5WTEX5045 | Flooring & Painting | 8164 | 464 | 296 | 200 | 0 | 900 | 900 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-06-08 17:00 |  | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | aYZ1yOC2SAK09t3ZsITSEA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42680 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124730 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 900 | SCREED MASON SK
%R | 501714 | 6359 | 124732 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5WTEX5050 | Installation of Steel Gate | 8178 | 168 | 16 | 160 | 0 | 84 | 84 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-19 17:00 |  | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-05-04 08:00 | 2014-05-26 17:00 | 2014-05-28 08:00 | 2014-06-19 17:00 |  | PT_Normal |  |  |  |  | xRaNXm3kQTmEKfDNdotgGQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42680 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124730 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 84 | LABOR- SUBCONTRACTOR
%R | 501715 | 6359 | 124732 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5WTEX5060 | Structural steel & SS Shed cover installation | 8178 | 152 | 0 | 200 | 0 | 588 | 588 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-03 08:00 | 2014-07-01 17:00 |  | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-06-03 08:00 | 2014-07-01 17:00 |  | PT_Normal |  |  |  |  | e/eV9BPqQH2Lfpgs4tYExw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42680 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124730 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 588 | LABOR- SUBCONTRACTOR
%R | 501716 | 6359 | 124732 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5WTEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 152 | 152 | 200 | 0 | 152.4 | 152.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-13 17:00 |  | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 |  | PT_Normal |  |  |  |  | pzWPg3ENQ2+Ep+8FJ2I6gw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42680 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124730 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 152.4 | LABOR- SUBCONTRACTOR
%R | 501717 | 6359 | 124732 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5WTEX5080 | Domestic Water Tank Electrical works | 8178 | 464 | 0 | 200 | 0 | 175 | 175 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-06 08:00 | 2014-06-03 17:00 |  | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-05-06 08:00 | 2014-06-03 17:00 |  | PT_Normal |  |  |  |  | SJ27Uv7NSwC8jk/dx8mnUg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42680 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124730 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 87.5 | LABOR- SUBCONTRACTOR
%R | 501718 | 6359 | 124732 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5WTEX5070 | Domestic Water Tank Plumbings works | 8178 | 464 | 0 | 200 | 0 | 200 | 200 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-06 08:00 | 2014-06-03 17:00 |  | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-05-06 08:00 | 2014-06-03 17:00 |  | PT_Normal |  |  |  |  | frsex3noRBuv8Og7TplpnA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42680 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124730 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 100 | LABOR- SUBCONTRACTOR
%R | 501719 | 6359 | 124732 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5WTEX5075 | Domestic Water Tank AC works | 8178 | 464 | 0 | 200 | 0 | 175 | 175 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-06 08:00 | 2014-06-03 17:00 |  | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-05-06 08:00 | 2014-06-03 17:00 |  | PT_Normal |  |  |  |  | 1D2LnFLUSMWlDsuLEdiGzw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42680 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124730 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 87.5 | LABOR- SUBCONTRACTOR
%R | 501720 | 6359 | 124732 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5WTEX5085 | Domestic Water Tank Firefighting works | 8178 | 464 | 0 | 200 | 0 | 118.8 | 118.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-06 08:00 | 2014-06-03 17:00 |  | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-05-06 08:00 | 2014-06-03 17:00 |  | PT_Normal |  |  |  |  | CbNLzHTAQoG4Uhrp2dTdyw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42680 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124730 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 59.4 | LABOR- SUBCONTRACTOR
%R | 501721 | 6359 | 124732 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5WTEX5030 | Excavation | 8177 | 464 | 0 | 160 | 0 | 116 | 116 | 160 | 80 | 0 | 80 |  |  |  | 2014-04-13 08:00 | 2014-05-05 17:00 |  | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | VS5FxkxaRrusr/iehU/Z7Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42680 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124730 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 116 | LABOR - CIVIL
%R | 501722 | 6359 | 124732 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5WTEX5035 | Construction of Raft | 8167 | 464 | 0 | 200 | 0 | 210 | 210 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-19 08:00 | 2014-05-17 17:00 |  | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 |  | PT_Normal |  |  |  |  | jPSEONjlTae3aD5WlWpI2A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42680 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124730 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 105 | CONCRETE MASON SK
%R | 501723 | 6359 | 124735 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STFF2020 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 1615.25 | 1615.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-14 08:00 | 2013-12-12 17:00 |  | 2013-11-14 08:00 | 2013-12-12 17:00 | 2013-11-14 08:00 | 2013-12-12 17:00 | 2013-11-14 08:00 | 2013-12-12 17:00 | 2013-11-14 08:00 | 2013-12-12 17:00 |  | PT_Normal |  |  |  |  | V34Vs5RwQ6KRg40L9w2O5w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42420 | N | N | 15 | FIRST FLOORS |  | 124734 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1615.25 | STEEL FIXERS SK
%R | 501724 | 6359 | 124735 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STFF2025 | Column-Concrete | 8167 | 0 | 0 | 192 | 0 | 87.5 | 87.5 | 192 | 0 | 0 | 0 |  |  |  | 2013-11-25 08:00 | 2013-12-23 17:00 |  | 2013-11-25 08:00 | 2013-12-23 17:00 | 2013-11-25 08:00 | 2013-12-23 17:00 | 2013-11-25 08:00 | 2013-12-23 17:00 | 2013-11-25 08:00 | 2013-12-23 17:00 |  | PT_Normal |  |  |  |  | Szo+LiacQhq0Hln2FH3+5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42420 | N | N | 15 | FIRST FLOORS |  | 124734 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 87.5 | CONCRETE MASON SK
%R | 501725 | 6359 | 124735 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 10081.75 | 10081.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-10 08:00 | 2014-01-08 17:00 |  | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 |  | PT_Normal |  |  |  |  | lHtkkNQ1TfqRXkx6ydulvA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42420 | N | N | 15 | FIRST FLOORS |  | 124734 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 10081.75 | STEEL FIXERS SK
%R | 501726 | 6359 | 124735 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 0 | 0 | 120 | 0 | 731.5 | 731.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-01 08:00 | 2014-01-18 17:00 |  | 2014-01-01 08:00 | 2014-01-18 17:00 | 2014-01-01 08:00 | 2014-01-18 17:00 | 2014-01-01 08:00 | 2014-01-18 17:00 | 2014-01-01 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | 3xgwWSqlR6+bmImLEPwPfQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42420 | N | N | 15 | FIRST FLOORS |  | 124734 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 731.5 | CONCRETE MASON SK
%R | 501727 | 6359 | 124736 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STRF2040 | Column-Rebar & Formwork | 8165 | 120 | 0 | 144 | 0 | 549.5 | 549.5 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-21 08:00 | 2014-02-10 17:00 |  | 2014-01-04 08:00 | 2014-01-23 17:00 | 2014-01-04 08:00 | 2014-01-23 17:00 | 2014-01-04 08:00 | 2014-01-23 17:00 | 2014-01-21 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | cGZIV3vGS2+Xk3vr11uBcg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42430 | N | N | 20 | ROOF |  | 124734 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 549.5 | STEEL FIXERS SK
%R | 501728 | 6359 | 124736 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STRF2045 | Column-Concrete | 8167 | 120 | 0 | 136 | 0 | 21 | 21 | 136 | 0 | 0 | 0 |  |  |  | 2014-01-25 08:00 | 2014-02-13 17:00 |  | 2014-01-07 08:00 | 2014-01-26 17:00 | 2014-01-07 08:00 | 2014-01-26 17:00 | 2014-01-07 08:00 | 2014-01-26 17:00 | 2014-01-25 08:00 | 2014-02-13 17:00 |  | PT_Normal |  |  |  |  | +3Qcn5VIQZeU8xi2CoCnjg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42430 | N | N | 20 | ROOF |  | 124734 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 21 | CONCRETE MASON SK
%R | 501729 | 6359 | 124736 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STRF2050 | Slab-Rebar & Formwork | 8165 | 120 | 0 | 160 | 0 | 1576.75 | 1576.75 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-27 08:00 | 2014-02-19 17:00 |  | 2014-01-09 08:00 | 2014-02-01 17:00 | 2014-01-09 08:00 | 2014-02-01 17:00 | 2014-01-09 08:00 | 2014-02-01 17:00 | 2014-01-27 08:00 | 2014-02-19 17:00 |  | PT_Normal |  |  |  |  | zV2ayIIlSR2ffAEUxxLLdg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42430 | N | N | 20 | ROOF |  | 124734 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1576.75 | STEEL FIXERS SK
%R | 501730 | 6359 | 124736 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STRF2055 | Slab-Concrete | 8167 | 120 | 0 | 104 | 0 | 175 | 175 | 104 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-02-22 17:00 |  | 2014-01-20 08:00 | 2014-02-03 17:00 | 2014-01-20 08:00 | 2014-02-03 17:00 | 2014-01-20 08:00 | 2014-02-03 17:00 | 2014-02-06 08:00 | 2014-02-22 17:00 |  | PT_Normal |  |  |  |  | Q8X2Pw0ERnWY8/pFu8jTlg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42430 | N | N | 20 | ROOF |  | 124734 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 175 | CONCRETE MASON SK
%R | 501731 | 6359 | 124736 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STRF2060 | Construction of Parapets | 8168 | 464 | 0 | 200 | 0 | 1441 | 1441 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-01 08:00 | 2014-04-29 17:00 |  | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 |  | PT_Normal |  |  |  |  | x4FjFZLeSyChmhJFXSU9Zw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42430 | N | N | 20 | ROOF |  | 124734 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1441 | BLOCK MASON SK
%R | 501732 | 6359 | 124736 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STRF2065 | Construction of up stands/Plinth | 8165 | 464 | 0 | 200 | 0 | 283.5 | 283.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-07 08:00 | 2014-05-05 17:00 |  | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42430 | N | N | 20 | ROOF |  | 124734 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 283.5 | STEEL FIXERS SK
%R | 501733 | 6359 | 124737 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STGF2000 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 1688.75 | 1688.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-01 08:00 | 2013-10-31 17:00 |  | 2013-10-01 08:00 | 2013-10-31 17:00 | 2013-10-01 08:00 | 2013-10-31 17:00 | 2013-10-01 08:00 | 2013-10-31 17:00 | 2013-10-01 08:00 | 2013-10-31 17:00 |  | PT_Normal |  |  |  |  | MTMHGv/VTCC5fzDp6oxUWA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42410 | N | N | 10 | GROUND FLOOR |  | 124734 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1688.75 | STEEL FIXERS SK
%R | 501734 | 6359 | 124737 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STGF2005 | Column-Concrete | 8167 | 0 | 0 | 192 | 0 | 101.5 | 101.5 | 192 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2013-11-09 17:00 |  | 2013-10-10 08:00 | 2013-11-09 17:00 | 2013-10-10 08:00 | 2013-11-09 17:00 | 2013-10-10 08:00 | 2013-11-09 17:00 | 2013-10-10 08:00 | 2013-11-09 17:00 |  | PT_Normal |  |  |  |  | t4KbGDt+QtqEq5RIONaKVA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42410 | N | N | 10 | GROUND FLOOR |  | 124734 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 101.5 | CONCRETE MASON SK
%R | 501735 | 6359 | 124737 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 10592.75 | 10592.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-28 08:00 | 2013-11-25 17:00 |  | 2013-10-28 08:00 | 2013-11-25 17:00 | 2013-10-28 08:00 | 2013-11-25 17:00 | 2013-10-28 08:00 | 2013-11-25 17:00 | 2013-10-28 08:00 | 2013-11-25 17:00 |  | PT_Normal |  |  |  |  | f7+buwZGRC2TxLerxKIASg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42410 | N | N | 10 | GROUND FLOOR |  | 124734 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 10592.75 | STEEL FIXERS SK
%R | 501736 | 6359 | 124737 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 0 | 0 | 120 | 0 | 868 | 868 | 120 | 0 | 0 | 0 |  |  |  | 2013-11-12 08:00 | 2013-11-28 17:00 |  | 2013-11-12 08:00 | 2013-11-28 17:00 | 2013-11-12 08:00 | 2013-11-28 17:00 | 2013-11-12 08:00 | 2013-11-28 17:00 | 2013-11-12 08:00 | 2013-11-28 17:00 |  | PT_Normal |  |  |  |  | HapMw02bSl2ewdQLxE5kVA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42410 | N | N | 10 | GROUND FLOOR |  | 124734 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 868 | CONCRETE MASON SK
%R | 501737 | 6359 | 124739 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STUG1000 | Footing Excavation | 8177 | 0 | 0 | 200 | 0 | 1556 | 1556 | 200 | 732 | 0 | 732 |  |  |  | 2013-05-27 08:00 | 2013-06-24 17:00 |  | 2013-05-27 08:00 | 2013-06-24 17:00 | 2013-05-27 08:00 | 2013-06-24 17:00 | 2013-05-27 08:00 | 2013-06-24 17:00 | 2013-05-27 08:00 | 2013-06-24 17:00 |  | PT_Normal |  |  |  |  | 9rlyifg3SY2dC3GcwohY3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42390 | N | N | 10 | UPTO GRADE SLAB |  | 124738 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 1556 | LABOR - CIVIL
%R | 501738 | 6359 | 124739 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STUG1005 | Footing Antitermite | 8178 | 0 | 0 | 184 | 0 | 634.25 | 634.25 | 184 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-07-02 17:00 |  | 2013-06-06 08:00 | 2013-07-02 17:00 | 2013-06-06 08:00 | 2013-07-02 17:00 | 2013-06-06 08:00 | 2013-07-02 17:00 | 2013-06-06 08:00 | 2013-07-02 17:00 |  | PT_Normal |  |  |  |  | 11Eo+tlYQfunlHuj0ycU6w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42390 | N | N | 10 | UPTO GRADE SLAB |  | 124738 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 634.25 | LABOR- SUBCONTRACTOR
%R | 501739 | 6359 | 124739 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STUG1010 | Footing Blinding | 8163 | 0 | 0 | 184 | 0 | 588 | 588 | 184 | 0 | 0 | 0 |  |  |  | 2013-06-10 08:00 | 2013-07-06 17:00 |  | 2013-06-10 08:00 | 2013-07-06 17:00 | 2013-06-10 08:00 | 2013-07-06 17:00 | 2013-06-10 08:00 | 2013-07-06 17:00 | 2013-06-10 08:00 | 2013-07-06 17:00 |  | PT_Normal |  |  |  |  | buYTZiU/Q3KzuZ4NvkBN6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42390 | N | N | 10 | UPTO GRADE SLAB |  | 124738 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 588 | BLINDING MASON SK
%R | 501740 | 6359 | 124739 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STUG1015 | Footing Waterproofing & Screed | 8164 | 0 | 0 | 200 | 0 | 1368.5 | 1368.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-16 08:00 | 2013-07-14 17:00 |  | 2013-06-16 08:00 | 2013-07-14 17:00 | 2013-06-16 08:00 | 2013-07-14 17:00 | 2013-06-16 08:00 | 2013-07-14 17:00 | 2013-06-16 08:00 | 2013-07-14 17:00 |  | PT_Normal |  |  |  |  | HoZyPlIQR2SAqlw3UxuoVA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42390 | N | N | 10 | UPTO GRADE SLAB |  | 124738 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 1368.5 | SCREED MASON SK
%R | 501741 | 6359 | 124739 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STUG1020 | Construction of foundations | 8165 | 0 | 0 | 160 | 0 | 4817.75 | 4817.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-07-01 08:00 | 2013-07-23 17:00 |  | 2013-07-01 08:00 | 2013-07-23 17:00 | 2013-07-01 08:00 | 2013-07-23 17:00 | 2013-07-01 08:00 | 2013-07-23 17:00 | 2013-07-01 08:00 | 2013-07-23 17:00 |  | PT_Normal |  |  |  |  | 0caX5rXwTn61NVpBPI2YeQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42390 | N | N | 10 | UPTO GRADE SLAB |  | 124738 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 4817.75 | STEEL FIXERS SK
%R | 501742 | 6359 | 124739 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STUG1025 | Construction of neck of columns | 8165 | 0 | 0 | 200 | 0 | 1400 | 1400 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-10 08:00 | 2013-08-07 17:00 |  | 2013-07-10 08:00 | 2013-08-07 17:00 | 2013-07-10 08:00 | 2013-08-07 17:00 | 2013-07-10 08:00 | 2013-08-07 17:00 | 2013-07-10 08:00 | 2013-08-07 17:00 |  | PT_Normal |  |  |  |  | 1943Y5nlTnSXJFXxSKseZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42390 | N | N | 10 | UPTO GRADE SLAB |  | 124738 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 1400 | STEEL FIXERS SK
%R | 501743 | 6359 | 124739 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STUG1030 | Waterproofing Footing & Neck Column | 8178 | 0 | 0 | 200 | 0 | 213.5 | 213.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-20 08:00 | 2013-08-20 17:00 |  | 2013-07-20 08:00 | 2013-08-20 17:00 | 2013-07-20 08:00 | 2013-08-20 17:00 | 2013-07-20 08:00 | 2013-08-20 17:00 | 2013-07-20 08:00 | 2013-08-20 17:00 |  | PT_Normal |  |  |  |  | mXJeiX+hRV+H8oe84UC0UQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42390 | N | N | 10 | UPTO GRADE SLAB |  | 124738 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 106.75 | LABOR- SUBCONTRACTOR
%R | 501744 | 6359 | 124739 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 0 | 0 | 200 | 0 | 2560 | 2560 | 200 | 2200 | 0 | 2200 |  |  |  | 2013-07-30 08:00 | 2013-08-31 17:00 |  | 2013-07-30 08:00 | 2013-08-31 17:00 | 2013-07-30 08:00 | 2013-08-31 17:00 | 2013-07-30 08:00 | 2013-08-31 17:00 | 2013-07-30 08:00 | 2013-08-31 17:00 |  | PT_Normal |  |  |  |  | PmVuwGE8RLC2Y3K/UES6IQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42390 | N | N | 10 | UPTO GRADE SLAB |  | 124738 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 1280 | LABOR - CIVIL
%R | 501745 | 6359 | 124739 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STUG1040 | Construction of Grade Beams | 8163 | 0 | 0 | 200 | 0 | 4745 | 4745 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-19 08:00 | 2013-09-16 17:00 |  | 2013-08-19 08:00 | 2013-09-16 17:00 | 2013-08-19 08:00 | 2013-09-16 17:00 | 2013-08-19 08:00 | 2013-09-16 17:00 | 2013-08-19 08:00 | 2013-09-16 17:00 |  | PT_Normal |  |  |  |  | JFpapZoeRdytdaNLcdfHxA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42390 | N | N | 10 | UPTO GRADE SLAB |  | 124738 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 4745 | BLINDING MASON SK
%R | 501746 | 6359 | 124739 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5STUG1045 | Construction of slab on grade | 8163 | 0 | 0 | 200 | 0 | 3327.5 | 3327.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-15 08:00 | 2013-10-13 17:00 |  | 2013-09-15 08:00 | 2013-10-13 17:00 | 2013-09-15 08:00 | 2013-10-13 17:00 | 2013-09-15 08:00 | 2013-10-13 17:00 | 2013-09-15 08:00 | 2013-10-13 17:00 |  | PT_Normal |  |  |  |  | KpUQWrroSvizLmCKyNnQow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42390 | N | N | 10 | UPTO GRADE SLAB |  | 124738 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 3327.5 | BLINDING MASON SK
%R | 501747 | 6359 | 124740 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 0 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-14 08:00 | 2014-08-14 17:00 |  | 2014-07-14 08:00 | 2014-08-14 17:00 | 2014-07-14 08:00 | 2014-08-14 17:00 | 2014-07-14 08:00 | 2014-08-14 17:00 | 2014-07-14 08:00 | 2014-08-14 17:00 |  | PT_Normal |  |  |  |  | 1HvYXHqFSKmPcFRggEHPhA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42710 | N | N | 30 | TESTING AND COMMISSIONING |  | 124729 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 750 | LABOR- SUBCONTRACTOR
%R | 501748 | 6359 | 124740 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-14 08:00 | 2014-08-14 17:00 |  | 2014-07-14 08:00 | 2014-08-14 17:00 | 2014-07-14 08:00 | 2014-08-14 17:00 | 2014-07-14 08:00 | 2014-08-14 17:00 | 2014-07-14 08:00 | 2014-08-14 17:00 |  | PT_Normal |  |  |  |  | MKjssf29TYONVOxr6zqT8w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42710 | N | N | 30 | TESTING AND COMMISSIONING |  | 124729 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 501749 | 6359 | 124740 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-14 08:00 | 2014-08-14 17:00 |  | 2014-07-14 08:00 | 2014-08-14 17:00 | 2014-07-14 08:00 | 2014-08-14 17:00 | 2014-07-14 08:00 | 2014-08-14 17:00 | 2014-07-14 08:00 | 2014-08-14 17:00 |  | PT_Normal |  |  |  |  | O3LioIObQW6Pv5wfsVqymQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42710 | N | N | 30 | TESTING AND COMMISSIONING |  | 124729 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 501750 | 6359 | 124743 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 0 | 0 | 144 | 0 | 2732.4 | 2732.4 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-10 08:00 | 2014-03-03 17:00 |  | 2014-02-10 08:00 | 2014-03-03 17:00 | 2014-02-10 08:00 | 2014-03-03 17:00 | 2014-02-10 08:00 | 2014-03-03 17:00 | 2014-02-10 08:00 | 2014-03-03 17:00 |  | PT_Normal |  |  |  |  | MrHjYy8CQFmlhVrcKYbjqA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42590 | N | N | 15 | FIRST FLOORS |  | 124742 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 2732.4 | LABOR- SUBCONTRACTOR
%R | 501751 | 6359 | 124743 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5PLFF4330 | Installation of Drainage pipes & testing | 8178 | 208 | 208 | 144 | 0 | 216 | 216 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-03 17:00 |  | 2014-02-12 08:00 | 2014-03-04 17:00 | 2014-02-12 08:00 | 2014-03-04 17:00 | 2014-02-12 08:00 | 2014-03-04 17:00 | 2014-03-15 08:00 | 2014-04-03 17:00 |  | PT_Normal |  |  |  |  | wTn8j64PQEifx9NmllfGjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42590 | N | N | 15 | FIRST FLOORS |  | 124742 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 216 | LABOR- SUBCONTRACTOR
%R | 501752 | 6359 | 124743 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5PLFF4335 | Sanitary Fittings & Accessories | 8178 | 96 | 0 | 160 | 0 | 352.8 | 352.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-19 17:00 |  | 2014-05-14 08:00 | 2014-06-05 17:00 | 2014-05-14 08:00 | 2014-06-05 17:00 | 2014-05-14 08:00 | 2014-06-05 17:00 | 2014-05-28 08:00 | 2014-06-19 17:00 |  | PT_Normal |  |  |  |  | zAvEtbjZQ2eqiV/JhPOTNQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42590 | N | N | 15 | FIRST FLOORS |  | 124742 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 352.8 | LABOR- SUBCONTRACTOR
%R | 501753 | 6359 | 124743 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5PLFF4340 | Installation of Water Heater | 8178 | 96 | 0 | 120 | 0 | 50.4 | 50.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-06-25 17:00 |  | 2014-05-26 08:00 | 2014-06-11 17:00 | 2014-05-26 08:00 | 2014-06-11 17:00 | 2014-05-26 08:00 | 2014-06-11 17:00 | 2014-06-09 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42590 | N | N | 15 | FIRST FLOORS |  | 124742 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 501754 | 6359 | 124744 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 568 | 144 | 120 | 0 | 1623.6 | 1623.6 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-31 08:00 | 2014-06-16 17:00 |  | 2014-03-09 08:00 | 2014-03-25 17:00 | 2014-03-09 08:00 | 2014-03-25 17:00 | 2014-03-09 08:00 | 2014-03-25 17:00 | 2014-05-31 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | lUZUEfBqSVqw2fwBEo7/AQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42600 | N | N | 20 | ROOF |  | 124742 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1623.6 | LABOR- SUBCONTRACTOR
%R | 501755 | 6359 | 124744 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5PLRF4350 | Installation of Rain water Pipes | 8178 | 424 | 272 | 120 | 0 | 82.8 | 82.8 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-06-25 17:00 |  | 2014-04-08 08:00 | 2014-04-24 17:00 | 2014-04-08 08:00 | 2014-04-24 17:00 | 2014-04-08 08:00 | 2014-04-24 17:00 | 2014-06-09 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | hrhA+ZoBQBm998X/KJv/4g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42600 | N | N | 20 | ROOF |  | 124742 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 82.8 | LABOR- SUBCONTRACTOR
%R | 501756 | 6359 | 124744 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 96 | 96 | 200 | 0 | 100.8 | 100.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-13 17:00 |  | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 |  | PT_Normal |  |  |  |  | l3jWUWJ2TCWXLHE+QvbfSg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42600 | N | N | 20 | ROOF |  | 124742 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 100.8 | LABOR- SUBCONTRACTOR
%R | 501757 | 6359 | 124745 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 320 | 0 | 144 | 0 | 2732.4 | 2732.4 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-17 08:00 | 2014-03-09 17:00 |  | 2013-12-31 08:00 | 2014-01-20 17:00 | 2013-12-31 08:00 | 2014-01-20 17:00 | 2013-12-31 08:00 | 2014-01-20 17:00 | 2014-02-17 08:00 | 2014-03-09 17:00 |  | PT_Normal |  |  |  |  | yqo7ksbKS5e4OwiKoNrOLw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42580 | N | N | 10 | GROUND FLOOR |  | 124742 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 2732.4 | LABOR- SUBCONTRACTOR
%R | 501758 | 6359 | 124745 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5PLGF4310 | Installation of Drainage pipes &testing | 8178 | 488 | 136 | 144 | 0 | 216 | 216 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-04-02 17:00 |  | 2013-12-31 08:00 | 2014-01-20 17:00 | 2013-12-31 08:00 | 2014-01-20 17:00 | 2013-12-31 08:00 | 2014-01-20 17:00 | 2014-03-13 08:00 | 2014-04-02 17:00 |  | PT_Normal |  |  |  |  | efDbu/FqQCGI/Mm57BUloA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42580 | N | N | 10 | GROUND FLOOR |  | 124742 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 216 | LABOR- SUBCONTRACTOR
%R | 501759 | 6359 | 124745 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5PLGF4315 | Sanitary Fittings & Accessories | 8178 | 512 | 0 | 160 | 0 | 352.8 | 352.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-07 17:00 |  | 2014-04-01 08:00 | 2014-04-23 17:00 | 2014-04-01 08:00 | 2014-04-23 17:00 | 2014-04-01 08:00 | 2014-04-23 17:00 | 2014-06-15 08:00 | 2014-07-07 17:00 |  | PT_Normal |  |  |  |  | G26FcdAwReOeXe9qeF3hhw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42580 | N | N | 10 | GROUND FLOOR |  | 124742 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 352.8 | LABOR- SUBCONTRACTOR
%R | 501760 | 6359 | 124745 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5PLGF4320 | Installation of Water Heater | 8178 | 512 | 512 | 120 | 0 | 50.4 | 50.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-26 08:00 | 2014-07-13 17:00 |  | 2014-04-13 08:00 | 2014-04-29 17:00 | 2014-04-13 08:00 | 2014-04-29 17:00 | 2014-04-13 08:00 | 2014-04-29 17:00 | 2014-06-26 08:00 | 2014-07-13 17:00 |  | PT_Normal |  |  |  |  | v81FcaahSSezHhKfLVBQUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42580 | N | N | 10 | GROUND FLOOR |  | 124742 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 501761 | 6359 | 124745 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 0 | 0 | 160 | 0 | 165.6 | 165.6 | 160 | 0 | 0 | 0 |  |  |  | 2013-09-05 08:00 | 2013-09-28 17:00 |  | 2013-09-05 08:00 | 2013-09-28 17:00 | 2013-09-05 08:00 | 2013-09-28 17:00 | 2013-09-05 08:00 | 2013-09-28 17:00 | 2013-09-05 08:00 | 2013-09-28 17:00 |  | PT_Normal |  |  |  |  | Ub/VMm//TQ+8BKqRE3bl1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42580 | N | N | 10 | GROUND FLOOR |  | 124742 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 165.6 | LABOR- SUBCONTRACTOR
%R | 501762 | 6359 | 124747 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 88 | 0 | 200 | 0 | 1102.8 | 1102.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-15 08:00 | 2014-03-15 17:00 |  | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 |  | PT_Normal |  |  |  |  | /ezBU9sFTRmCuXagA8eZdQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42550 | N | N | 15 | FIRST FLOORS |  | 124746 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 551.4 | LABOR- SUBCONTRACTOR
%R | 501763 | 6359 | 124747 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ELFF4040 | Cable tray & trunking installation | 8178 | 264 | 24 | 160 | 0 | 1840.8 | 1840.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-24 08:00 | 2014-04-15 17:00 |  | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-03-24 08:00 | 2014-04-15 17:00 |  | PT_Normal |  |  |  |  | e+SeLMBARtu02UL04dTb2w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42550 | N | N | 15 | FIRST FLOORS |  | 124746 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1840.8 | LABOR- SUBCONTRACTOR
%R | 501764 | 6359 | 124747 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ELFF4045 | Installation of wiring & Main Cabling | 8178 | 240 | 240 | 200 | 0 | 648 | 648 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-01 08:00 | 2014-04-29 17:00 |  | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 |  | PT_Normal |  |  |  |  | MDyVsknnRz6kasNHH2y3Qw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42550 | N | N | 15 | FIRST FLOORS |  | 124746 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 324 | LABOR- SUBCONTRACTOR
%R | 501765 | 6359 | 124747 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 64 | 0 | 160 | 0 | 188.4 | 188.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-15 08:00 | 2014-06-07 17:00 |  | 2014-05-06 08:00 | 2014-05-28 17:00 | 2014-05-06 08:00 | 2014-05-28 17:00 | 2014-05-06 08:00 | 2014-05-28 17:00 | 2014-05-15 08:00 | 2014-06-07 17:00 |  | PT_Normal |  |  |  |  | 6xWOaYPNQIClW5bCDFK0FQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42550 | N | N | 15 | FIRST FLOORS |  | 124746 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 188.4 | LABOR- SUBCONTRACTOR
%R | 501766 | 6359 | 124747 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 64 | 0 | 200 | 0 | 2528.4 | 2528.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-25 17:00 |  | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | 9g+TOFnOSaGmtAMf7LKaKw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42550 | N | N | 15 | FIRST FLOORS |  | 124746 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 2528.4 | LABOR- SUBCONTRACTOR
%R | 501767 | 6359 | 124747 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 96 | 96 | 200 | 0 | 1612.8 | 1612.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | 2MgXX/7YRfyR06tuCgcGBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42550 | N | N | 15 | FIRST FLOORS |  | 124746 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1612.8 | LABOR- SUBCONTRACTOR
%R | 501768 | 6359 | 124747 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ELFF4050 | Installation of Telephone System | 8178 | 216 | 152 | 200 | 0 | 542.4 | 542.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-01 08:00 | 2014-06-29 17:00 |  | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 |  | PT_Normal |  |  |  |  | 2cXt7aDPSWiw2jP6Vqhrkw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42550 | N | N | 15 | FIRST FLOORS |  | 124746 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 542.4 | LABOR- SUBCONTRACTOR
%R | 501769 | 6359 | 124748 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 392 | 296 | 200 | 0 | 1461.6 | 1461.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-06-08 17:00 |  | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | 4z4Er2gOQ9Ccj3QMN76xXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42540 | N | N | 10 | GROUND FLOOR |  | 124746 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1461.6 | LABOR- SUBCONTRACTOR
%R | 501770 | 6359 | 124748 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ELGF4030 | Installation of Telephone System | 8178 | 336 | 120 | 160 | 0 | 542.4 | 542.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-20 08:00 | 2014-06-11 17:00 |  | 2014-04-01 08:00 | 2014-04-23 17:00 | 2014-04-01 08:00 | 2014-04-23 17:00 | 2014-04-01 08:00 | 2014-04-23 17:00 | 2014-05-20 08:00 | 2014-06-11 17:00 |  | PT_Normal |  |  |  |  | rrfiJZeNRz6ArLi1dYoTFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42540 | N | N | 10 | GROUND FLOOR |  | 124746 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 542.4 | LABOR- SUBCONTRACTOR
%R | 501771 | 6359 | 124748 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 392 | 0 | 200 | 0 | 1102.8 | 1102.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-17 08:00 | 2014-03-17 17:00 |  | 2013-12-21 08:00 | 2014-01-18 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 |  | PT_Normal |  |  |  |  | H6ELSAjQRg6DgIUWSJLBig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42540 | N | N | 10 | GROUND FLOOR |  | 124746 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1102.8 | LABOR- SUBCONTRACTOR
%R | 501772 | 6359 | 124748 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ELGF4005 | Cable tray & trunking installation | 8178 | 552 | 0 | 160 | 0 | 1840.8 | 1840.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-24 08:00 | 2014-04-15 17:00 |  | 2014-01-01 08:00 | 2014-01-23 17:00 | 2014-01-01 08:00 | 2014-01-23 17:00 | 2014-01-01 08:00 | 2014-01-23 17:00 | 2014-03-24 08:00 | 2014-04-15 17:00 |  | PT_Normal |  |  |  |  | 9QjwjcymRCqnvS4X18Sh4g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42540 | N | N | 10 | GROUND FLOOR |  | 124746 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1840.8 | LABOR- SUBCONTRACTOR
%R | 501773 | 6359 | 124748 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ELGF4010 | Installation of wiring & Main Cabling | 8178 | 552 | 216 | 200 | 0 | 648 | 648 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-01 08:00 | 2014-04-29 17:00 |  | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 |  | PT_Normal |  |  |  |  | fYvl+J9SRlKoWBrr2RKzqg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42540 | N | N | 10 | GROUND FLOOR |  | 124746 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 648 | LABOR- SUBCONTRACTOR
%R | 501774 | 6359 | 124748 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 336 | 0 | 160 | 0 | 222 | 222 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-08 08:00 | 2014-05-31 17:00 |  | 2014-03-20 08:00 | 2014-04-12 17:00 | 2014-03-20 08:00 | 2014-04-12 17:00 | 2014-03-20 08:00 | 2014-04-12 17:00 | 2014-05-08 08:00 | 2014-05-31 17:00 |  | PT_Normal |  |  |  |  | VN/VaUnRSX2iN7yKIoF8Bg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42540 | N | N | 10 | GROUND FLOOR |  | 124746 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 222 | LABOR- SUBCONTRACTOR
%R | 501775 | 6359 | 124748 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 352 | 288 | 200 | 0 | 2580 | 2580 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-22 08:00 | 2014-06-19 17:00 |  | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 |  | PT_Normal |  |  |  |  | E7SpPI1xSSyzjZYFLwAy1Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42540 | N | N | 10 | GROUND FLOOR |  | 124746 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 2580 | LABOR- SUBCONTRACTOR
%R | 501776 | 6359 | 124749 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ELRF4070 | Installation of Isolator | 8178 | 64 | 0 | 144 | 0 | 309.6 | 309.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-07 17:00 |  | 2014-06-08 08:00 | 2014-06-28 17:00 | 2014-06-08 08:00 | 2014-06-28 17:00 | 2014-06-08 08:00 | 2014-06-28 17:00 | 2014-06-17 08:00 | 2014-07-07 17:00 |  | PT_Normal |  |  |  |  | 0/PXy4m9SICQt4nRKZA/UA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42560 | N | N | 20 | ROOF |  | 124746 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 309.6 | LABOR- SUBCONTRACTOR
%R | 501777 | 6359 | 124749 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ELRF4075 | Installation of TV Dish Antenna | 8178 | 64 | 64 | 184 | 0 | 4725.6 | 4725.6 | 184 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-24 17:00 |  | 2014-06-19 08:00 | 2014-07-15 17:00 | 2014-06-19 08:00 | 2014-07-15 17:00 | 2014-06-19 08:00 | 2014-07-15 17:00 | 2014-06-29 08:00 | 2014-07-24 17:00 |  | PT_Normal |  |  |  |  | g+dL2Ky8ThqIHcbO/7Jatw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42560 | N | N | 20 | ROOF |  | 124746 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 4725.6 | LABOR- SUBCONTRACTOR
%R | 501778 | 6359 | 124751 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ACFF4615 | Installation AC Pipes | 8178 | 256 | 8 | 160 | 0 | 340.8 | 340.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-13 08:00 | 2014-05-05 17:00 |  | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | VO0QDkxFSTOdLpiCY0fqrQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42630 | N | N | 15 | FIRST FLOORS |  | 124750 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 340.8 | LABOR- SUBCONTRACTOR
%R | 501779 | 6359 | 124751 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ACFF4620 | Fixing of Ventilation Equipments | 8178 | 72 | 0 | 200 | 0 | 136.8 | 136.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-06-10 17:00 |  | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-13 08:00 | 2014-06-10 17:00 |  | PT_Normal |  |  |  |  | q7npsYm2QnikXJ64Mvxl7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42630 | N | N | 15 | FIRST FLOORS |  | 124750 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 136.8 | LABOR- SUBCONTRACTOR
%R | 501780 | 6359 | 124751 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ACFF4625 | Fixing of Split AC | 8178 | 72 | 0 | 160 | 0 | 361.2 | 361.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-03 08:00 | 2014-06-25 17:00 |  | 2014-05-24 08:00 | 2014-06-15 17:00 | 2014-05-24 08:00 | 2014-06-15 17:00 | 2014-05-24 08:00 | 2014-06-15 17:00 | 2014-06-03 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | 398RN9R9Q/qqLJBz1cm1lQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42630 | N | N | 15 | FIRST FLOORS |  | 124750 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 361.2 | LABOR- SUBCONTRACTOR
%R | 501781 | 6359 | 124752 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ACGF4600 | Installation AC Pipes | 8178 | 584 | 224 | 160 | 0 | 340.8 | 340.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-16 08:00 | 2014-05-08 17:00 |  | 2014-01-20 08:00 | 2014-02-12 17:00 | 2014-01-20 08:00 | 2014-02-12 17:00 | 2014-01-20 08:00 | 2014-02-12 17:00 | 2014-04-16 08:00 | 2014-05-08 17:00 |  | PT_Normal |  |  |  |  | EBVt7xFFTimn4CZUKnRRWQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42620 | N | N | 10 | GROUND FLOOR |  | 124750 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 340.8 | LABOR- SUBCONTRACTOR
%R | 501782 | 6359 | 124752 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ACGF4605 | Fixing of Ventilation Equipments | 8178 | 408 | 0 | 200 | 0 | 136.8 | 136.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-06-10 17:00 |  | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-05-13 08:00 | 2014-06-10 17:00 |  | PT_Normal |  |  |  |  | u2k1+L0/TOq+nYHlhK0DSA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42620 | N | N | 10 | GROUND FLOOR |  | 124750 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 136.8 | LABOR- SUBCONTRACTOR
%R | 501783 | 6359 | 124752 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ACGF4610 | Fixing of Split AC | 8178 | 408 | 88 | 160 | 0 | 361.2 | 361.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-03 08:00 | 2014-06-25 17:00 |  | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-06-03 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | pfrT2TQRTFK+dCixbBIhKg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42620 | N | N | 10 | GROUND FLOOR |  | 124750 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 361.2 | LABOR- SUBCONTRACTOR
%R | 501784 | 6359 | 124753 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ACRF4630 | Installation of Refrigerant Pipes | 8178 | 584 | 472 | 200 | 0 | 170.4 | 170.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-07-07 17:00 |  | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 |  | PT_Normal |  |  |  |  | CLXg5pZFSaioQ/qDJg+Qzg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42640 | N | N | 20 | ROOF |  | 124750 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 170.4 | LABOR- SUBCONTRACTOR
%R | 501785 | 6359 | 124753 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ACRF4635 | Installation of Condensing Unit | 8178 | 112 | 112 | 200 | 0 | 562.8 | 562.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-13 17:00 |  | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 |  | PT_Normal |  |  |  |  | KjTTreVDQayOlENorXAWeA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42640 | N | N | 20 | ROOF |  | 124750 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 562.8 | LABOR- SUBCONTRACTOR
%R | 501786 | 6359 | 124756 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARRF3630 | Leveling Screed for Waterproofing | 8164 | 496 | 0 | 200 | 0 | 734.75 | 734.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-04 08:00 | 2014-06-01 17:00 |  | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 |  | PT_Normal |  |  |  |  | VoMFp6+dSNSFwSzwy4Clkg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42500 | N | N | 10 | ROOF |  | 124755 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 367.375 | SCREED MASON SK
%R | 501787 | 6359 | 124756 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARRF3635 | Laying of Waterproofing Membrane | 8178 | 496 | 0 | 200 | 0 | 2042.25 | 2042.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-07 08:00 | 2014-06-04 17:00 |  | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 |  | PT_Normal |  |  |  |  | 4qmnENTNSQaskoL/98SqsQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42500 | N | N | 10 | ROOF |  | 124755 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 1021.125 | LABOR- SUBCONTRACTOR
%R | 501788 | 6359 | 124756 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARRF3640 | Installation of Insulation & Protection | 8178 | 496 | 0 | 200 | 0 | 1291.5 | 1291.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-12 08:00 | 2014-06-09 17:00 |  | 2014-03-01 08:00 | 2014-03-29 17:00 | 2014-03-01 08:00 | 2014-03-29 17:00 | 2014-03-01 08:00 | 2014-03-29 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 |  | PT_Normal |  |  |  |  | faKIBKecTPGg8yk+WRO5Ww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42500 | N | N | 10 | ROOF |  | 124755 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1291.5 | LABOR- SUBCONTRACTOR
%R | 501789 | 6359 | 124756 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 496 | 0 | 200 | 0 | 741.5 | 741.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | udjv9UUWR3Kgk4PFYR9tqQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42500 | N | N | 10 | ROOF |  | 124755 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 741.5 | TILE MASON SK
%R | 501790 | 6359 | 124756 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 496 | 0 | 160 | 0 | 231 | 231 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-07-01 17:00 |  | 2014-03-29 08:00 | 2014-04-20 17:00 | 2014-03-29 08:00 | 2014-04-20 17:00 | 2014-03-29 08:00 | 2014-04-20 17:00 | 2014-06-09 08:00 | 2014-07-01 17:00 |  | PT_Normal |  |  |  |  | bz8MvYDbTDGgfmRHeM4oCQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42500 | N | N | 10 | ROOF |  | 124755 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 231 | LABOR- SUBCONTRACTOR
%R | 501791 | 6359 | 124756 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 496 | 0 | 200 | 0 | 882 | 882 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-25 08:00 | 2014-06-22 17:00 |  | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-05-25 08:00 | 2014-06-22 17:00 |  | PT_Normal |  |  |  |  | VnO9EPtAQyOCt9m/ioD30w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42500 | N | N | 10 | ROOF |  | 124755 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 882 | LABOR- SUBCONTRACTOR
%R | 501792 | 6359 | 124756 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARRF3660 | Installation of Access Ladder | 8178 | 536 | 536 | 120 | 0 | 198 | 198 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-26 08:00 | 2014-07-13 17:00 |  | 2014-04-09 08:00 | 2014-04-26 17:00 | 2014-04-09 08:00 | 2014-04-26 17:00 | 2014-04-09 08:00 | 2014-04-26 17:00 | 2014-06-26 08:00 | 2014-07-13 17:00 |  | PT_Normal |  |  |  |  | OKQd4jrzTQOuZl9kmnk/Gw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42500 | N | N | 10 | ROOF |  | 124755 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 198 | LABOR- SUBCONTRACTOR
%R | 501793 | 6359 | 124757 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5AREL3665 | External Plastering | 8169 | 424 | 0 | 200 | 0 | 9159.75 | 9159.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-20 08:00 | 2014-06-17 17:00 |  | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | 7S8xImigQ36FxQf893rwLQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42510 | N | N | 15 | ELEVATION |  | 124755 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 9159.75 | PLASTER MASON SK
%R | 501794 | 6359 | 124757 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5AREL3675 | GRC Panel Works | 8178 | 440 | 0 | 160 | 0 | 550 | 550 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-07-01 17:00 |  | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-06-09 08:00 | 2014-07-01 17:00 |  | PT_Normal |  |  |  |  | stvYpJ5WRrSLrh+U4bx02Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42510 | N | N | 15 | ELEVATION |  | 124755 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 550 | LABOR- SUBCONTRACTOR
%R | 501795 | 6359 | 124757 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5AREL3680 | External Painting | 8178 | 440 | 440 | 160 | 0 | 3234 | 3234 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-21 08:00 | 2014-07-13 17:00 |  | 2014-04-17 08:00 | 2014-05-10 17:00 | 2014-04-17 08:00 | 2014-05-10 17:00 | 2014-04-17 08:00 | 2014-05-10 17:00 | 2014-06-21 08:00 | 2014-07-13 17:00 |  | PT_Normal |  |  |  |  | /EcEAES4S4KE1FRyeqLo5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42510 | N | N | 15 | ELEVATION |  | 124755 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 3234 | LABOR- SUBCONTRACTOR
%R | 501796 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3000 | Block work | 8168 | 320 | 0 | 200 | 0 | 7112.5 | 7112.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-03-01 17:00 |  | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | EHJmJkJ+ThqSIJP9QF5O5w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 7112.5 | BLOCK MASON SK
%R | 501797 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3005 | Plastering work | 8169 | 320 | 0 | 200 | 0 | 6268.75 | 6268.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-23 08:00 | 2014-03-23 17:00 |  | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-02-23 08:00 | 2014-03-23 17:00 |  | PT_Normal |  |  |  |  | 76PdZLHLSrmpvTuQHh8X+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 6268.75 | PLASTER MASON SK
%R | 501798 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3010 | Flooring screed | 8164 | 384 | 64 | 168 | 0 | 1234.75 | 1234.75 | 168 | 0 | 0 | 0 |  |  |  | 2014-03-12 08:00 | 2014-04-05 17:00 |  | 2014-01-14 08:00 | 2014-02-06 17:00 | 2014-01-14 08:00 | 2014-02-06 17:00 | 2014-01-14 08:00 | 2014-02-06 17:00 | 2014-03-12 08:00 | 2014-04-05 17:00 |  | PT_Normal |  |  |  |  | amf+brF8RXCRoHX2JIIckw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1234.75 | SCREED MASON SK
%R | 501799 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 320 | 0 | 120 | 0 | 582 | 582 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-12 08:00 | 2014-03-29 17:00 |  | 2014-01-23 08:00 | 2014-02-09 17:00 | 2014-01-23 08:00 | 2014-02-09 17:00 | 2014-01-23 08:00 | 2014-02-09 17:00 | 2014-03-12 08:00 | 2014-03-29 17:00 |  | PT_Normal |  |  |  |  | nC5p9F4VS/G46n1wHAbfSQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 582 | LABOR- SUBCONTRACTOR
%R | 501800 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3030 | Paint First coat | 8178 | 400 | 64 | 200 | 0 | 4136.55 | 4136.55 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-30 08:00 | 2014-04-27 17:00 |  | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-03-30 08:00 | 2014-04-27 17:00 |  | PT_Normal |  |  |  |  | ibii99GNR6i+w7HjV/1PVg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 4136.55 | LABOR- SUBCONTRACTOR
%R | 501801 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3020 | Ceramic Wall Tiling | 8170 | 320 | 0 | 200 | 0 | 2603.5 | 2603.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-18 08:00 | 2014-04-15 17:00 |  | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 |  | PT_Normal |  |  |  |  | DG0dV7WdQPqpuo+jQr3f3g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 2603.5 | TILE MASON SK
%R | 501802 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3025 | Porcelain Tile flooring | 8170 | 320 | 0 | 200 | 0 | 1787.5 | 1787.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-24 08:00 | 2014-04-21 17:00 |  | 2014-02-04 08:00 | 2014-03-05 17:00 | 2014-02-04 08:00 | 2014-03-05 17:00 | 2014-02-04 08:00 | 2014-03-05 17:00 | 2014-03-24 08:00 | 2014-04-21 17:00 |  | PT_Normal |  |  |  |  | yMnxyxT7QiqY/RbVbvoWpQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 893.75 | TILE MASON SK
%R | 501803 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3040 | Cobble Tile flooring | 8170 | 320 | 0 | 120 | 0 | 68.75 | 68.75 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-06 17:00 |  | 2014-03-04 08:00 | 2014-03-20 17:00 | 2014-03-04 08:00 | 2014-03-20 17:00 | 2014-03-04 08:00 | 2014-03-20 17:00 | 2014-04-20 08:00 | 2014-05-06 17:00 |  | PT_Normal |  |  |  |  | 1y6E39uiQHOakMcara+5gw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 68.75 | TILE MASON SK
%R | 501804 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 336 | 16 | 120 | 0 | 45.5 | 45.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-01 17:00 |  | 2014-02-25 08:00 | 2014-03-13 17:00 | 2014-02-25 08:00 | 2014-03-13 17:00 | 2014-02-25 08:00 | 2014-03-13 17:00 | 2014-04-15 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | wJdap42hQIe9hR1OQp4TzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 45.5 | TILE MASON SK
%R | 501805 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 320 | 0 | 160 | 0 | 506.25 | 506.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-28 08:00 | 2014-05-20 17:00 |  | 2014-03-12 08:00 | 2014-04-03 17:00 | 2014-03-12 08:00 | 2014-04-03 17:00 | 2014-03-12 08:00 | 2014-04-03 17:00 | 2014-04-28 08:00 | 2014-05-20 17:00 |  | PT_Normal |  |  |  |  | /DlMHkk0S+Wg/Qjt5/E6sA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 506.25 | GRANITE MASON SK
%R | 501806 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3045 | Fixing of Suspension systems | 8178 | 336 | 0 | 160 | 0 | 1434.75 | 1434.75 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-13 08:00 | 2014-05-05 17:00 |  | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | U7PpbnL8RkeDGz4yHkAhNQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1434.75 | LABOR- SUBCONTRACTOR
%R | 501807 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3055 | Aluminum tile false ceiling | 8178 | 360 | 24 | 200 | 0 | 156.25 | 156.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-24 08:00 | 2014-05-22 17:00 |  | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 |  | PT_Normal |  |  |  |  | T9pm6lTkQpOBF+OAkRn/nw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 156.25 | LABOR- SUBCONTRACTOR
%R | 501808 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3060 | Gypsum board false ceiling | 8178 | 336 | 0 | 200 | 0 | 1298.71 | 1298.71 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-24 08:00 | 2014-05-22 17:00 |  | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 |  | PT_Normal |  |  |  |  | +R5QYav7QWq720xcXU0oGA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1298.71 | LABOR- SUBCONTRACTOR
%R | 501809 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3065 | Wooden door | 8178 | 320 | 0 | 120 | 0 | 412.5 | 412.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-12 08:00 | 2014-05-28 17:00 |  | 2014-03-26 08:00 | 2014-04-12 17:00 | 2014-03-26 08:00 | 2014-04-12 17:00 | 2014-03-26 08:00 | 2014-04-12 17:00 | 2014-05-12 08:00 | 2014-05-28 17:00 |  | PT_Normal |  |  |  |  | QLKqkT5BQAOnp/jC4tY/4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 412.5 | LABOR- SUBCONTRACTOR
%R | 501810 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3070 | Aluminum doors | 8178 | 320 | 0 | 120 | 0 | 99 | 99 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-18 08:00 | 2014-06-03 17:00 |  | 2014-04-01 08:00 | 2014-04-17 17:00 | 2014-04-01 08:00 | 2014-04-17 17:00 | 2014-04-01 08:00 | 2014-04-17 17:00 | 2014-05-18 08:00 | 2014-06-03 17:00 |  | PT_Normal |  |  |  |  | zclpRrmITrGqrD0LUN/5zw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 99 | LABOR- SUBCONTRACTOR
%R | 501811 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3080 | Aluminum windows | 8178 | 400 | 80 | 160 | 0 | 220 | 220 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-06-28 17:00 |  | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-06-05 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | Y/pj1bGtQ0K5N7DHXPgd7g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 220 | LABOR- SUBCONTRACTOR
%R | 501812 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3075 | Carpentry & Joinery Works | 8178 | 320 | 0 | 160 | 0 | 792 | 792 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-24 08:00 | 2014-06-15 17:00 |  | 2014-04-07 08:00 | 2014-04-29 17:00 | 2014-04-07 08:00 | 2014-04-29 17:00 | 2014-04-07 08:00 | 2014-04-29 17:00 | 2014-05-24 08:00 | 2014-06-15 17:00 |  | PT_Normal |  |  |  |  | az1AzxuHRG6kbbkJlDcx2Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 792 | LABOR- SUBCONTRACTOR
%R | 501813 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3090 | Installation of Granite Counter Top | 8171 | 320 | 0 | 120 | 0 | 132 | 132 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-06-22 17:00 |  | 2014-04-20 08:00 | 2014-05-06 17:00 | 2014-04-20 08:00 | 2014-05-06 17:00 | 2014-04-20 08:00 | 2014-05-06 17:00 | 2014-06-05 08:00 | 2014-06-22 17:00 |  | PT_Normal |  |  |  |  | mfAxJDPOTfG2DCQPdicqTg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 132 | GRANITE MASON SK
%R | 501814 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3085 | S.S.Balustrade | 8178 | 360 | 40 | 160 | 0 | 47.25 | 47.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-07 08:00 | 2014-06-29 17:00 |  | 2014-04-15 08:00 | 2014-05-07 17:00 | 2014-04-15 08:00 | 2014-05-07 17:00 | 2014-04-15 08:00 | 2014-05-07 17:00 | 2014-06-07 08:00 | 2014-06-29 17:00 |  | PT_Normal |  |  |  |  | b3PXbdNRQd+4Byjgt68FUQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 47.25 | LABOR- SUBCONTRACTOR
%R | 501815 | 6359 | 124759 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARGF3095 | Final Painting | 8178 | 320 | 320 | 200 | 0 | 4136.55 | 4136.55 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-13 17:00 |  | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 |  | PT_Normal |  |  |  |  | aanvsrA4SB+MFmKwfMklrQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42460 | N | N | 10 | GROUND FLOOR |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 4136.55 | LABOR- SUBCONTRACTOR
%R | 501816 | 6359 | 124760 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARRF3600 | Block work | 8168 | 536 | 0 | 160 | 0 | 487.5 | 487.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-04 08:00 | 2014-05-26 17:00 |  | 2014-02-15 08:00 | 2014-03-09 17:00 | 2014-02-15 08:00 | 2014-03-09 17:00 | 2014-02-15 08:00 | 2014-03-09 17:00 | 2014-05-04 08:00 | 2014-05-26 17:00 |  | PT_Normal |  |  |  |  | 8UA0pTg5QjewHC2JtodrtQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42480 | N | N | 20 | ROOF |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 487.5 | BLOCK MASON SK
%R | 501817 | 6359 | 124760 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARRF3605 | Plastering work | 8169 | 536 | 0 | 160 | 0 | 1950 | 1950 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-12 08:00 | 2014-06-03 17:00 |  | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-05-12 08:00 | 2014-06-03 17:00 |  | PT_Normal |  |  |  |  | aGvPIIm4SMyDag9E7QdLTg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42480 | N | N | 20 | ROOF |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1950 | PLASTER MASON SK
%R | 501818 | 6359 | 124760 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARRF3610 | Flooring screed | 8164 | 576 | 0 | 120 | 0 | 115.5 | 115.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-01 08:00 | 2014-06-17 17:00 |  | 2014-03-09 08:00 | 2014-03-25 17:00 | 2014-03-09 08:00 | 2014-03-25 17:00 | 2014-03-09 08:00 | 2014-03-25 17:00 | 2014-06-01 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | BKFpttaRS8Op13bvowQMMQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42480 | N | N | 20 | ROOF |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 115.5 | SCREED MASON SK
%R | 501819 | 6359 | 124760 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARRF3695 | Painting | 8178 | 576 | 0 | 160 | 0 | 504 | 504 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-07-01 17:00 |  | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-06-09 08:00 | 2014-07-01 17:00 |  | PT_Normal |  |  |  |  | eGWk2u2iQFmF2zILgZHRGA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42480 | N | N | 20 | ROOF |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 504 | LABOR- SUBCONTRACTOR
%R | 501820 | 6359 | 124760 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARRF3620 | Epoxy Painting | 8178 | 576 | 576 | 120 | 0 | 24.75 | 24.75 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-26 08:00 | 2014-07-13 17:00 |  | 2014-04-03 08:00 | 2014-04-20 17:00 | 2014-04-03 08:00 | 2014-04-20 17:00 | 2014-04-03 08:00 | 2014-04-20 17:00 | 2014-06-26 08:00 | 2014-07-13 17:00 |  | PT_Normal |  |  |  |  | wf+dMNXRR0avjI4HM7UWgg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42480 | N | N | 20 | ROOF |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 24.75 | LABOR- SUBCONTRACTOR
%R | 501821 | 6359 | 124761 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARFF3300 | Block work | 8168 | 0 | 0 | 200 | 0 | 5553.5 | 5553.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-26 08:00 | 2014-02-24 17:00 |  | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 |  | PT_Normal |  |  |  |  | 84rWN0yQS6KA8LeHj4y1FQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42470 | N | N | 15 | FIRST FLOORS |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 5553.5 | BLOCK MASON SK
%R | 501822 | 6359 | 124761 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARFF3305 | Plastering work | 8169 | 0 | 0 | 200 | 0 | 5516 | 5516 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-20 08:00 | 2014-03-20 17:00 |  | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | jxHptPMRSLaqGebN+4Yg7w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42470 | N | N | 15 | FIRST FLOORS |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 2758 | PLASTER MASON SK
%R | 501823 | 6359 | 124761 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARFF3310 | Flooring screed | 8164 | 120 | 120 | 168 | 0 | 1031.25 | 1031.25 | 168 | 0 | 0 | 0 |  |  |  | 2014-03-18 08:00 | 2014-04-10 17:00 |  | 2014-03-01 08:00 | 2014-03-24 17:00 | 2014-03-01 08:00 | 2014-03-24 17:00 | 2014-03-01 08:00 | 2014-03-24 17:00 | 2014-03-18 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | 2oRWQO4/SJmdgIWqxRLFLg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42470 | N | N | 15 | FIRST FLOORS |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1031.25 | SCREED MASON SK
%R | 501824 | 6359 | 124761 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARFF3315 | Wet area waterproofing | 8178 | 0 | 0 | 120 | 0 | 582 | 582 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-03-30 17:00 |  | 2014-03-13 08:00 | 2014-03-30 17:00 | 2014-03-13 08:00 | 2014-03-30 17:00 | 2014-03-13 08:00 | 2014-03-30 17:00 | 2014-03-13 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | kr/quIT2Sg+cGDEpoWdhnA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42470 | N | N | 15 | FIRST FLOORS |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 582 | LABOR- SUBCONTRACTOR
%R | 501825 | 6359 | 124761 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARFF3330 | Paint First coat | 8178 | 144 | 144 | 200 | 0 | 3644.75 | 3644.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-30 08:00 | 2014-04-27 17:00 |  | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-30 08:00 | 2014-04-27 17:00 |  | PT_Normal |  |  |  |  | uivthLpyQ2SSZkjTmal+yA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42470 | N | N | 15 | FIRST FLOORS |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 3644.75 | LABOR- SUBCONTRACTOR
%R | 501826 | 6359 | 124761 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARFF3320 | Ceramic Wall Tiling | 8170 | 0 | 0 | 200 | 0 | 2603.5 | 2603.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-23 08:00 | 2014-04-20 17:00 |  | 2014-03-23 08:00 | 2014-04-20 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | ymirQLHGQSKD437Dz7iwWQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42470 | N | N | 15 | FIRST FLOORS |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 2603.5 | TILE MASON SK
%R | 501827 | 6359 | 124761 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARFF3325 | Porcelain Tile flooring | 8170 | 0 | 0 | 200 | 0 | 1787.5 | 1787.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-30 08:00 | 2014-04-27 17:00 |  | 2014-03-30 08:00 | 2014-04-27 17:00 | 2014-03-30 08:00 | 2014-04-27 17:00 | 2014-03-30 08:00 | 2014-04-27 17:00 | 2014-03-30 08:00 | 2014-04-27 17:00 |  | PT_Normal |  |  |  |  | qmUkK2phRm+QWWwlTvYdkw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42470 | N | N | 15 | FIRST FLOORS |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1787.5 | TILE MASON SK
%R | 501828 | 6359 | 124761 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARFF3335 | Slate Tile Flooring & Skirting | 8178 | 96 | 96 | 120 | 0 | 1350 | 1350 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-30 08:00 | 2014-05-17 17:00 |  | 2014-04-16 08:00 | 2014-05-03 17:00 | 2014-04-16 08:00 | 2014-05-03 17:00 | 2014-04-16 08:00 | 2014-05-03 17:00 | 2014-04-30 08:00 | 2014-05-17 17:00 |  | PT_Normal |  |  |  |  | TCW+mzS3TPaPl2QB2GwWhQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42470 | N | N | 15 | FIRST FLOORS |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1350 | LABOR- SUBCONTRACTOR
%R | 501829 | 6359 | 124761 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARFF3350 | Granite - Stair case flooring & Skirting | 8178 | 32 | 32 | 160 | 0 | 150 | 150 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-24 08:00 | 2014-05-17 17:00 |  | 2014-04-20 08:00 | 2014-05-12 17:00 | 2014-04-20 08:00 | 2014-05-12 17:00 | 2014-04-20 08:00 | 2014-05-12 17:00 | 2014-04-24 08:00 | 2014-05-17 17:00 |  | PT_Normal |  |  |  |  | XdYa0mQiTHuNVqVDaRvprw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42470 | N | N | 15 | FIRST FLOORS |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 150 | LABOR- SUBCONTRACTOR
%R | 501830 | 6359 | 124761 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARFF3345 | Fixing of Suspension systems | 8178 | 0 | 0 | 160 | 0 | 1434.75 | 1434.75 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-13 08:00 | 2014-05-05 17:00 |  | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | SSmhglQDQHGfw4o2FqLGjg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42470 | N | N | 15 | FIRST FLOORS |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1434.75 | LABOR- SUBCONTRACTOR
%R | 501831 | 6359 | 124761 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARFF3355 | Aluminum tile false ceiling | 8178 | 32 | 0 | 160 | 0 | 156.25 | 156.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-21 17:00 |  | 2014-04-24 08:00 | 2014-05-17 17:00 | 2014-04-24 08:00 | 2014-05-17 17:00 | 2014-04-24 08:00 | 2014-05-17 17:00 | 2014-04-29 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | pTnzw6LMTnKeeW6pOyCLrg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42470 | N | N | 15 | FIRST FLOORS |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 156.25 | LABOR- SUBCONTRACTOR
%R | 501832 | 6359 | 124761 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARFF3360 | Gypsum board false ceiling | 8178 | 0 | 0 | 200 | 0 | 1298.71 | 1298.71 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-21 08:00 | 2014-05-19 17:00 |  | 2014-04-21 08:00 | 2014-05-19 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42470 | N | N | 15 | FIRST FLOORS |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1298.71 | LABOR- SUBCONTRACTOR
%R | 501833 | 6359 | 124761 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARFF3365 | Wooden door | 8178 | 0 | 0 | 120 | 0 | 330 | 330 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-08 08:00 | 2014-05-25 17:00 |  | 2014-05-08 08:00 | 2014-05-25 17:00 | 2014-05-08 08:00 | 2014-05-25 17:00 | 2014-05-08 08:00 | 2014-05-25 17:00 | 2014-05-08 08:00 | 2014-05-25 17:00 |  | PT_Normal |  |  |  |  | 52aPL8ECROuK09ZQAfrDiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42470 | N | N | 15 | FIRST FLOORS |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 330 | LABOR- SUBCONTRACTOR
%R | 501834 | 6359 | 124761 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARFF3370 | Aluminum Door | 8178 | 0 | 0 | 160 | 0 | 99 | 99 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-14 08:00 | 2014-06-05 17:00 |  | 2014-05-14 08:00 | 2014-06-05 17:00 | 2014-05-14 08:00 | 2014-06-05 17:00 | 2014-05-14 08:00 | 2014-06-05 17:00 | 2014-05-14 08:00 | 2014-06-05 17:00 |  | PT_Normal |  |  |  |  | Nb3OuTuZT4q3/GTxsa5xYA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42470 | N | N | 15 | FIRST FLOORS |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 99 | LABOR- SUBCONTRACTOR
%R | 501835 | 6359 | 124761 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARFF3380 | Aluminum windows | 8178 | 88 | 88 | 160 | 0 | 264 | 264 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-03 08:00 | 2014-06-25 17:00 |  | 2014-05-21 08:00 | 2014-06-12 17:00 | 2014-05-21 08:00 | 2014-06-12 17:00 | 2014-05-21 08:00 | 2014-06-12 17:00 | 2014-06-03 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | xYISNimcS0iDlRpywx9PUQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42470 | N | N | 15 | FIRST FLOORS |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 264 | LABOR- SUBCONTRACTOR
%R | 501836 | 6359 | 124761 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARFF3375 | Carpentry & Joinery Works | 8178 | 0 | 0 | 200 | 0 | 300 | 300 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-22 08:00 | 2014-06-19 17:00 |  | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 |  | PT_Normal |  |  |  |  | L1t6nB2uSHeQCGl28GeoxA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42470 | N | N | 15 | FIRST FLOORS |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 300 | LABOR- SUBCONTRACTOR
%R | 501837 | 6359 | 124761 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARFF3390 | Installation of Granite Counter Top | 8171 | 16 | 16 | 160 | 0 | 132 | 132 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-07-01 17:00 |  | 2014-06-07 08:00 | 2014-06-29 17:00 | 2014-06-07 08:00 | 2014-06-29 17:00 | 2014-06-07 08:00 | 2014-06-29 17:00 | 2014-06-09 08:00 | 2014-07-01 17:00 |  | PT_Normal |  |  |  |  | wj53KBPhQVyCF5dXQD95pw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42470 | N | N | 15 | FIRST FLOORS |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 132 | GRANITE MASON SK
%R | 501838 | 6359 | 124761 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARFF3385 | Handrail & Balustrade | 8178 | 0 | 0 | 160 | 0 | 275 | 275 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-03 08:00 | 2014-06-25 17:00 |  | 2014-06-03 08:00 | 2014-06-25 17:00 | 2014-06-03 08:00 | 2014-06-25 17:00 | 2014-06-03 08:00 | 2014-06-25 17:00 | 2014-06-03 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | MmT9nFW8SHqITnN5S0u1Xw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42470 | N | N | 15 | FIRST FLOORS |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 275 | LABOR- SUBCONTRACTOR
%R | 501839 | 6359 | 124761 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z5ARFF3395 | Final Painting | 8178 | 0 | 0 | 200 | 0 | 3644.75 | 3644.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-13 17:00 |  | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 |  | PT_Normal |  |  |  |  | 27F7913gT1WlWRx82t/CTQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42470 | N | N | 15 | FIRST FLOORS |  | 124758 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 3644.75 | LABOR- SUBCONTRACTOR
%R | 501840 | 6359 | 124765 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STGF2000 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 1688.75 | 1688.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-03 08:00 | 2013-07-01 17:00 |  | 2013-06-03 08:00 | 2013-07-01 17:00 | 2013-06-03 08:00 | 2013-07-01 17:00 | 2013-06-03 08:00 | 2013-07-01 17:00 | 2013-06-03 08:00 | 2013-07-01 17:00 |  | PT_Normal |  |  |  |  | V5GxBs6LRxWUBu5qZ4l+ZQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40970 | N | N | 10 | GROUND FLOOR |  | 124764 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 1688.75 | STEEL FIXERS SK
%R | 501841 | 6359 | 124765 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STGF2005 | Column-Concrete | 8167 | 0 | 0 | 192 | 0 | 101.5 | 101.5 | 192 | 0 | 0 | 0 |  |  |  | 2013-06-12 08:00 | 2013-07-09 17:00 |  | 2013-06-12 08:00 | 2013-07-09 17:00 | 2013-06-12 08:00 | 2013-07-09 17:00 | 2013-06-12 08:00 | 2013-07-09 17:00 | 2013-06-12 08:00 | 2013-07-09 17:00 |  | PT_Normal |  |  |  |  | 7sRsqkFpRX2JMT+S0RpYTQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40970 | N | N | 10 | GROUND FLOOR |  | 124764 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 101.5 | CONCRETE MASON SK
%R | 501842 | 6359 | 124765 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 10592.75 | 10592.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-27 08:00 | 2013-07-25 17:00 |  | 2013-06-27 08:00 | 2013-07-25 17:00 | 2013-06-27 08:00 | 2013-07-25 17:00 | 2013-06-27 08:00 | 2013-07-25 17:00 | 2013-06-27 08:00 | 2013-07-25 17:00 |  | PT_Normal |  |  |  |  | SFTsOo6rRz+8ZwkAxyuVhw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40970 | N | N | 10 | GROUND FLOOR |  | 124764 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 10592.75 | STEEL FIXERS SK
%R | 501843 | 6359 | 124765 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 0 | 0 | 120 | 0 | 868 | 868 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-13 08:00 | 2013-07-29 17:00 |  | 2013-07-13 08:00 | 2013-07-29 17:00 | 2013-07-13 08:00 | 2013-07-29 17:00 | 2013-07-13 08:00 | 2013-07-29 17:00 | 2013-07-13 08:00 | 2013-07-29 17:00 |  | PT_Normal |  |  |  |  | NcMzu9A9Td65GIESkYfCLw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40970 | N | N | 10 | GROUND FLOOR |  | 124764 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 868 | CONCRETE MASON SK
%R | 501844 | 6359 | 124766 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STRF2040 | Column-Rebar & Formwork | 8165 | 24 | 0 | 144 | 0 | 549.5 | 549.5 | 144 | 0 | 0 | 0 |  |  |  | 2013-09-03 08:00 | 2013-09-23 17:00 |  | 2013-08-31 08:00 | 2013-09-19 17:00 | 2013-08-31 08:00 | 2013-09-19 17:00 | 2013-08-31 08:00 | 2013-09-19 17:00 | 2013-09-03 08:00 | 2013-09-23 17:00 |  | PT_Normal |  |  |  |  | l4TcK53WQP6ugZ44a0c6tw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40990 | N | N | 20 | ROOF |  | 124764 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 549.5 | STEEL FIXERS SK
%R | 501845 | 6359 | 124766 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STRF2045 | Column-Concrete | 8167 | 24 | 0 | 136 | 0 | 21 | 21 | 136 | 0 | 0 | 0 |  |  |  | 2013-09-07 08:00 | 2013-09-25 17:00 |  | 2013-09-03 08:00 | 2013-09-22 17:00 | 2013-09-03 08:00 | 2013-09-22 17:00 | 2013-09-03 08:00 | 2013-09-22 17:00 | 2013-09-07 08:00 | 2013-09-25 17:00 |  | PT_Normal |  |  |  |  | x5KMKo42TdS3EeCjXnOXHw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40990 | N | N | 20 | ROOF |  | 124764 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 21 | CONCRETE MASON SK
%R | 501846 | 6359 | 124766 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STRF2050 | Slab-Rebar & Formwork | 8165 | 24 | 0 | 160 | 0 | 1576.75 | 1576.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-09-09 08:00 | 2013-10-01 17:00 |  | 2013-09-05 08:00 | 2013-09-28 17:00 | 2013-09-05 08:00 | 2013-09-28 17:00 | 2013-09-05 08:00 | 2013-09-28 17:00 | 2013-09-09 08:00 | 2013-10-01 17:00 |  | PT_Normal |  |  |  |  | kmd6FvnFSuykO3drjFDbHg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40990 | N | N | 20 | ROOF |  | 124764 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1576.75 | STEEL FIXERS SK
%R | 501847 | 6359 | 124766 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STRF2055 | Slab-Concrete | 8167 | 24 | 0 | 104 | 0 | 175 | 175 | 104 | 0 | 0 | 0 |  |  |  | 2013-09-19 08:00 | 2013-10-03 17:00 |  | 2013-09-16 08:00 | 2013-09-30 17:00 | 2013-09-16 08:00 | 2013-09-30 17:00 | 2013-09-16 08:00 | 2013-09-30 17:00 | 2013-09-19 08:00 | 2013-10-03 17:00 |  | PT_Normal |  |  |  |  | LYEKpQOnR2ao9h2/0WsdMQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40990 | N | N | 20 | ROOF |  | 124764 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 175 | CONCRETE MASON SK
%R | 501848 | 6359 | 124766 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STRF2060 | Construction of Parapets | 8168 | 144 | 0 | 200 | 0 | 1441 | 1441 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-09 08:00 | 2013-11-09 17:00 |  | 2013-09-18 08:00 | 2013-10-16 17:00 | 2013-09-18 08:00 | 2013-10-16 17:00 | 2013-09-18 08:00 | 2013-10-16 17:00 | 2013-10-09 08:00 | 2013-11-09 17:00 |  | PT_Normal |  |  |  |  | O+Ia9HfvQWuP7zypDOeeWA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40990 | N | N | 20 | ROOF |  | 124764 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1441 | BLOCK MASON SK
%R | 501849 | 6359 | 124766 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STRF2065 | Construction of up stands/Plinth | 8165 | 144 | 0 | 200 | 0 | 283.5 | 283.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-15 08:00 | 2013-11-14 17:00 |  | 2013-09-24 08:00 | 2013-10-24 17:00 | 2013-09-24 08:00 | 2013-10-24 17:00 | 2013-09-24 08:00 | 2013-10-24 17:00 | 2013-10-15 08:00 | 2013-11-14 17:00 |  | PT_Normal |  |  |  |  | D+S/6U1xTvKKxCflzHahPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40990 | N | N | 20 | ROOF |  | 124764 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 141.75 | STEEL FIXERS SK
%R | 501850 | 6359 | 124767 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STFF2020 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 1615.25 | 1615.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-15 08:00 | 2013-08-15 17:00 |  | 2013-07-15 08:00 | 2013-08-15 17:00 | 2013-07-15 08:00 | 2013-08-15 17:00 | 2013-07-15 08:00 | 2013-08-15 17:00 | 2013-07-15 08:00 | 2013-08-15 17:00 |  | PT_Normal |  |  |  |  | 2ffKSGXcQJ6seiwpyzerrg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40980 | N | N | 15 | FIRST FLOORS |  | 124764 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 807.625 | STEEL FIXERS SK
%R | 501851 | 6359 | 124767 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STFF2025 | Column-Concrete | 8167 | 0 | 0 | 192 | 0 | 87.5 | 87.5 | 192 | 0 | 0 | 0 |  |  |  | 2013-07-25 08:00 | 2013-08-25 17:00 |  | 2013-07-25 08:00 | 2013-08-25 17:00 | 2013-07-25 08:00 | 2013-08-25 17:00 | 2013-07-25 08:00 | 2013-08-25 17:00 | 2013-07-25 08:00 | 2013-08-25 17:00 |  | PT_Normal |  |  |  |  | PQWAIFASQzSKdmJbdj5dHA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40980 | N | N | 15 | FIRST FLOORS |  | 124764 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 43.75 | CONCRETE MASON SK
%R | 501852 | 6359 | 124767 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 10081.75 | 10081.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-13 08:00 | 2013-09-10 17:00 |  | 2013-08-13 08:00 | 2013-09-10 17:00 | 2013-08-13 08:00 | 2013-09-10 17:00 | 2013-08-13 08:00 | 2013-09-10 17:00 | 2013-08-13 08:00 | 2013-09-10 17:00 |  | PT_Normal |  |  |  |  | RWRtoz1zRnKoAzaNG4pxiw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40980 | N | N | 15 | FIRST FLOORS |  | 124764 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 10081.75 | STEEL FIXERS SK
%R | 501853 | 6359 | 124767 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 0 | 0 | 120 | 0 | 731.5 | 731.5 | 120 | 0 | 0 | 0 |  |  |  | 2013-08-28 08:00 | 2013-09-14 17:00 |  | 2013-08-28 08:00 | 2013-09-14 17:00 | 2013-08-28 08:00 | 2013-09-14 17:00 | 2013-08-28 08:00 | 2013-09-14 17:00 | 2013-08-28 08:00 | 2013-09-14 17:00 |  | PT_Normal |  |  |  |  | YMBYhaBaSMiBJxJ/OqbUQA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40980 | N | N | 15 | FIRST FLOORS |  | 124764 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 731.5 | CONCRETE MASON SK
%R | 501854 | 6359 | 124769 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STUG1000 | Footing Excavation | 8177 | 0 | 0 | 200 | 0 | 1556 | 1556 | 200 | 732 | 0 | 732 |  |  |  | 2013-01-29 08:00 | 2013-02-27 17:00 |  | 2013-01-29 08:00 | 2013-02-27 17:00 | 2013-01-29 08:00 | 2013-02-27 17:00 | 2013-01-29 08:00 | 2013-02-27 17:00 | 2013-01-29 08:00 | 2013-02-27 17:00 |  | PT_Normal |  |  |  |  | 3rZukdjaTz2EyzesuO5tqw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40950 | N | N | 10 | UPTO GRADE SLAB |  | 124768 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 1556 | LABOR - CIVIL
%R | 501855 | 6359 | 124769 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STUG1005 | Footing Antitermite | 8178 | 0 | 0 | 184 | 0 | 634.25 | 634.25 | 184 | 0 | 0 | 0 |  |  |  | 2013-02-09 08:00 | 2013-03-07 17:00 |  | 2013-02-09 08:00 | 2013-03-07 17:00 | 2013-02-09 08:00 | 2013-03-07 17:00 | 2013-02-09 08:00 | 2013-03-07 17:00 | 2013-02-09 08:00 | 2013-03-07 17:00 |  | PT_Normal |  |  |  |  | P4GbFtCSQ9WyHufgwDzAmA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40950 | N | N | 10 | UPTO GRADE SLAB |  | 124768 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 634.25 | LABOR- SUBCONTRACTOR
%R | 501856 | 6359 | 124769 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STUG1010 | Footing Blinding | 8163 | 0 | 0 | 184 | 0 | 588 | 588 | 184 | 0 | 0 | 0 |  |  |  | 2013-02-13 08:00 | 2013-03-11 17:00 |  | 2013-02-13 08:00 | 2013-03-11 17:00 | 2013-02-13 08:00 | 2013-03-11 17:00 | 2013-02-13 08:00 | 2013-03-11 17:00 | 2013-02-13 08:00 | 2013-03-11 17:00 |  | PT_Normal |  |  |  |  | qFurMJhdSOqjo4GC6j+57A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40950 | N | N | 10 | UPTO GRADE SLAB |  | 124768 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02 |  | 588 | BLINDING MASON SK
%R | 501857 | 6359 | 124769 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STUG1015 | Footing Waterproofing & Screed | 8178 | 0 | 0 | 200 | 0 | 906.5 | 906.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-02-19 08:00 | 2013-03-19 17:00 |  | 2013-02-19 08:00 | 2013-03-19 17:00 | 2013-02-19 08:00 | 2013-03-19 17:00 | 2013-02-19 08:00 | 2013-03-19 17:00 | 2013-02-19 08:00 | 2013-03-19 17:00 |  | PT_Normal |  |  |  |  | Paw+SCRbSomBs01GSD4sEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40950 | N | N | 10 | UPTO GRADE SLAB |  | 124768 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 453.25 | LABOR- SUBCONTRACTOR
%R | 501858 | 6359 | 124769 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STUG1020 | Construction of foundations | 8165 | 0 | 0 | 160 | 0 | 4817.75 | 4817.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-03-06 08:00 | 2013-03-28 17:00 |  | 2013-03-06 08:00 | 2013-03-28 17:00 | 2013-03-06 08:00 | 2013-03-28 17:00 | 2013-03-06 08:00 | 2013-03-28 17:00 | 2013-03-06 08:00 | 2013-03-28 17:00 |  | PT_Normal |  |  |  |  | XLY69J+hTBOBIqwrtmFI6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40950 | N | N | 10 | UPTO GRADE SLAB |  | 124768 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 4817.75 | STEEL FIXERS SK
%R | 501859 | 6359 | 124769 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STUG1025 | Construction of neck of columns | 8165 | 0 | 0 | 200 | 0 | 1400 | 1400 | 200 | 0 | 0 | 0 |  |  |  | 2013-03-16 08:00 | 2013-04-13 17:00 |  | 2013-03-16 08:00 | 2013-04-13 17:00 | 2013-03-16 08:00 | 2013-04-13 17:00 | 2013-03-16 08:00 | 2013-04-13 17:00 | 2013-03-16 08:00 | 2013-04-13 17:00 |  | PT_Normal |  |  |  |  | FtYD5p0RQJqMDhOJLEwgWQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40950 | N | N | 10 | UPTO GRADE SLAB |  | 124768 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 1400 | STEEL FIXERS SK
%R | 501860 | 6359 | 124769 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STUG1030 | Waterproofing Footing & Neck Column | 8178 | 0 | 0 | 200 | 0 | 213.5 | 213.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-03-25 08:00 | 2013-04-22 17:00 |  | 2013-03-25 08:00 | 2013-04-22 17:00 | 2013-03-25 08:00 | 2013-04-22 17:00 | 2013-03-25 08:00 | 2013-04-22 17:00 | 2013-03-25 08:00 | 2013-04-22 17:00 |  | PT_Normal |  |  |  |  | y8s46tqoQR6R+JCFPVZZvA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40950 | N | N | 10 | UPTO GRADE SLAB |  | 124768 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 213.5 | LABOR- SUBCONTRACTOR
%R | 501861 | 6359 | 124769 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 0 | 0 | 200 | 0 | 2560 | 2560 | 200 | 2200 | 0 | 2200 |  |  |  | 2013-04-04 08:00 | 2013-05-02 17:00 |  | 2013-04-04 08:00 | 2013-05-02 17:00 | 2013-04-04 08:00 | 2013-05-02 17:00 | 2013-04-04 08:00 | 2013-05-02 17:00 | 2013-04-04 08:00 | 2013-05-02 17:00 |  | PT_Normal |  |  |  |  | 4bStLizbQdKWw9SaGxxWqQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40950 | N | N | 10 | UPTO GRADE SLAB |  | 124768 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 2560 | LABOR - CIVIL
%R | 501862 | 6359 | 124769 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STUG1040 | Construction of Grade Beams | 8163 | 0 | 0 | 200 | 0 | 4745 | 4745 | 200 | 0 | 0 | 0 |  |  |  | 2013-04-21 08:00 | 2013-05-19 17:00 |  | 2013-04-21 08:00 | 2013-05-19 17:00 | 2013-04-21 08:00 | 2013-05-19 17:00 | 2013-04-21 08:00 | 2013-05-19 17:00 | 2013-04-21 08:00 | 2013-05-19 17:00 |  | PT_Normal |  |  |  |  | oMu4eyMXTsWZASA1PYj1+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40950 | N | N | 10 | UPTO GRADE SLAB |  | 124768 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 4745 | BLINDING MASON SK
%R | 501863 | 6359 | 124769 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1STUG1045 | Construction of slab on grade | 8163 | 0 | 0 | 200 | 0 | 3327.5 | 3327.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-05-18 08:00 | 2013-06-15 17:00 |  | 2013-05-18 08:00 | 2013-06-15 17:00 | 2013-05-18 08:00 | 2013-06-15 17:00 | 2013-05-18 08:00 | 2013-06-15 17:00 | 2013-05-18 08:00 | 2013-06-15 17:00 |  | PT_Normal |  |  |  |  | YPnD034VTZ+khSfFkfWhaQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40950 | N | N | 10 | UPTO GRADE SLAB |  | 124768 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 3327.5 | BLINDING MASON SK
%R | 501864 | 6359 | 124771 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1MSEX5020 | Construction Entrance Ramp | 8164 | 152 | 0 | 200 | 0 | 198 | 198 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-30 08:00 | 2014-01-27 17:00 |  | 2013-12-07 08:00 | 2014-01-05 17:00 | 2013-12-07 08:00 | 2014-01-05 17:00 | 2013-12-07 08:00 | 2014-01-05 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 |  | PT_Normal |  |  |  |  | nLN+jUuZQiOfjdHY2RmVIQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41230 | N | N | 10 | MISCELLANEOUS |  | 124770 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 198 | SCREED MASON SK
%R | 501865 | 6359 | 124771 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1MSEX5025 | SS.Handrails and Balustrades | 8178 | 152 | 0 | 160 | 0 | 99 | 99 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-19 08:00 | 2014-02-10 17:00 |  | 2013-12-28 08:00 | 2014-01-19 17:00 | 2013-12-28 08:00 | 2014-01-19 17:00 | 2013-12-28 08:00 | 2014-01-19 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41230 | N | N | 10 | MISCELLANEOUS |  | 124770 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 99 | LABOR- SUBCONTRACTOR
%R | 501866 | 6359 | 124771 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1MSEX5015 | Construction of grease Trap | 8178 | 312 | 160 | 160 | 0 | 38.5 | 38.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-06 17:00 |  | 2013-12-28 08:00 | 2014-01-19 17:00 | 2013-12-28 08:00 | 2014-01-19 17:00 | 2013-12-28 08:00 | 2014-01-19 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | ttB2E3W1R3CIBJ0zeRSP5w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41230 | N | N | 10 | MISCELLANEOUS |  | 124770 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 38.5 | LABOR- SUBCONTRACTOR
%R | 501867 | 6359 | 124771 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1MSEX5000 | Construction of Manholes | 8178 | 24 | 0 | 200 | 0 | 121 | 121 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-26 08:00 | 2013-12-25 17:00 |  | 2013-11-23 08:00 | 2013-12-22 17:00 | 2013-11-23 08:00 | 2013-12-22 17:00 | 2013-11-23 08:00 | 2013-12-22 17:00 | 2013-11-26 08:00 | 2013-12-25 17:00 |  | PT_Normal |  |  |  |  | 6SHw5n0eSEy8lSxrjarOxg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41230 | N | N | 10 | MISCELLANEOUS |  | 124770 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 121 | LABOR- SUBCONTRACTOR
%R | 501868 | 6359 | 124771 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1MSEX5005 | Construction of Soak pit, Chambers | 8177 | 144 | 0 | 200 | 0 | 275 | 275 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-29 08:00 | 2014-01-26 17:00 |  | 2013-12-07 08:00 | 2014-01-05 17:00 | 2013-12-07 08:00 | 2014-01-05 17:00 | 2013-12-07 08:00 | 2014-01-05 17:00 | 2013-12-29 08:00 | 2014-01-26 17:00 |  | PT_Normal |  |  |  |  | tlA20hrJRPa5zeb/D7FZ0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41230 | N | N | 10 | MISCELLANEOUS |  | 124770 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 275 | LABOR - CIVIL
%R | 501869 | 6359 | 124771 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1MSEX5010 | Telephone Cable laying | 8177 | 144 | 0 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-27 08:00 | 2014-02-25 17:00 |  | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 |  | PT_Normal |  |  |  |  | uIXV6dQ7SfKTVuuUc7UfZg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41230 | N | N | 10 | MISCELLANEOUS |  | 124770 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 500 | LABOR - CIVIL
%R | 501870 | 6359 | 124772 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1WTEX5030 | Excavation | 8177 | 504 | 0 | 160 | 0 | 113 | 113 | 160 | 80 | 0 | 80 |  |  |  | 2013-12-15 08:00 | 2014-01-07 17:00 |  | 2013-09-30 08:00 | 2013-10-24 17:00 | 2013-09-30 08:00 | 2013-10-24 17:00 | 2013-09-30 08:00 | 2013-10-24 17:00 | 2013-12-15 08:00 | 2014-01-07 17:00 |  | PT_Normal |  |  |  |  | JTUnAOCjT1CkStLeskZXYA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41240 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124770 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 113 | LABOR - CIVIL
%R | 501871 | 6359 | 124772 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1WTEX5035 | Construction of Raft & slab | 8167 | 504 | 0 | 200 | 0 | 192.5 | 192.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-22 08:00 | 2014-01-19 17:00 |  | 2013-10-06 08:00 | 2013-11-05 17:00 | 2013-10-06 08:00 | 2013-11-05 17:00 | 2013-10-06 08:00 | 2013-11-05 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 |  | PT_Normal |  |  |  |  | 5d5KGhjET7Weo7tg426Q4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41240 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124770 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 192.5 | CONCRETE MASON SK
%R | 501872 | 6359 | 124772 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1WTEX5040 | Block works & Plastering | 8168 | 504 | 0 | 200 | 0 | 2238.5 | 2238.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-31 08:00 | 2014-01-28 17:00 |  | 2013-10-15 08:00 | 2013-11-14 17:00 | 2013-10-15 08:00 | 2013-11-14 17:00 | 2013-10-15 08:00 | 2013-11-14 17:00 | 2013-12-31 08:00 | 2014-01-28 17:00 |  | PT_Normal |  |  |  |  | BbkGdbeEQg2nXPYpqxwhOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41240 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124770 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 2238.5 | BLOCK MASON SK
%R | 501873 | 6359 | 124772 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1WTEX5045 | Flooring & Painting | 8164 | 504 | 352 | 200 | 0 | 825 | 825 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-02-10 17:00 |  | 2013-10-30 08:00 | 2013-11-27 17:00 | 2013-10-30 08:00 | 2013-11-27 17:00 | 2013-10-30 08:00 | 2013-11-27 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | rDng1kPFTkqz+6Uc2AG2aQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41240 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124770 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 825 | SCREED MASON SK
%R | 501874 | 6359 | 124772 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1WTEX5050 | Installation of Steel Gate | 8178 | 152 | 0 | 160 | 0 | 81 | 81 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-02-23 17:00 |  | 2014-01-08 08:00 | 2014-01-30 17:00 | 2014-01-08 08:00 | 2014-01-30 17:00 | 2014-01-08 08:00 | 2014-01-30 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | u1eiEjP2QoWjysb6nxpdPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41240 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124770 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 81 | LABOR- SUBCONTRACTOR
%R | 501875 | 6359 | 124772 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1WTEX5060 | SS Shed cover installation | 8178 | 152 | 0 | 200 | 0 | 546 | 546 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-03-06 17:00 |  | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-02-05 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | UeN0pj0OQyOdOqX4PInKRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41240 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124770 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 546 | LABOR- SUBCONTRACTOR
%R | 501876 | 6359 | 124772 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1WTEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 152 | 0 | 200 | 0 | 146.4 | 146.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-18 17:00 |  | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | vVb0ZuMrQ1inZd8J7dF7qQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41240 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124770 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 146.4 | LABOR- SUBCONTRACTOR
%R | 501877 | 6359 | 124772 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1WTEX5080 | Domestic Water Tank Electrical works | 8178 | 504 | 0 | 200 | 0 | 175 | 175 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-08 08:00 | 2014-02-05 17:00 |  | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | OX7zOw6PR7islf0m7jVMZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41240 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124770 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 175 | LABOR- SUBCONTRACTOR
%R | 501878 | 6359 | 124772 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1WTEX5070 | Domestic Water Tank Plumbings works | 8178 | 504 | 0 | 200 | 0 | 200 | 200 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-08 08:00 | 2014-02-05 17:00 |  | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | MnwuDzNCTZ2q908+UorpNg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41240 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124770 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 200 | LABOR- SUBCONTRACTOR
%R | 501879 | 6359 | 124772 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1WTEX5075 | Domestic Water Tank AC works | 8178 | 504 | 0 | 200 | 0 | 175 | 175 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-08 08:00 | 2014-02-05 17:00 |  | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | l3Ocyea9QXaRpH6EIhLvoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41240 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124770 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 175 | LABOR- SUBCONTRACTOR
%R | 501880 | 6359 | 124772 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1WTEX5085 | Domestic Water Tank Firefighting works | 8178 | 504 | 0 | 200 | 0 | 116.5 | 116.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-08 08:00 | 2014-02-05 17:00 |  | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | BRwsX+5BSbGyOP23ufPTdg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41240 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124770 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 116.5 | LABOR- SUBCONTRACTOR
%R | 501881 | 6359 | 124775 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ACRF4630 | Installation of Refrigerant Pipes | 8178 | 584 | 0 | 200 | 0 | 156.2 | 156.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-12 17:00 |  | 2013-11-17 08:00 | 2013-12-15 17:00 | 2013-11-17 08:00 | 2013-12-15 17:00 | 2013-11-17 08:00 | 2013-12-15 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 |  | PT_Normal |  |  |  |  | kalhAY6nSVWE9uKNNovMYQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41200 | N | N | 20 | ROOF |  | 124774 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 156.2 | LABOR- SUBCONTRACTOR
%R | 501882 | 6359 | 124775 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ACRF4635 | Installation of Condensing Unit | 8178 | 112 | 0 | 200 | 0 | 515.9 | 515.9 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-18 17:00 |  | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | GAPZ++NBRKGGE37o4HGVdQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41200 | N | N | 20 | ROOF |  | 124774 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 257.95 | LABOR- SUBCONTRACTOR
%R | 501883 | 6359 | 124776 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ACGF4600 | Installation AC Pipes | 8178 | 528 | 40 | 160 | 0 | 312.4 | 312.4 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-10 08:00 | 2014-01-02 17:00 |  | 2013-09-22 08:00 | 2013-10-14 17:00 | 2013-09-22 08:00 | 2013-10-14 17:00 | 2013-09-22 08:00 | 2013-10-14 17:00 | 2013-12-10 08:00 | 2014-01-02 17:00 |  | PT_Normal |  |  |  |  | tjKsZufqToWwf922QIwnhQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41180 | N | N | 10 | GROUND FLOOR |  | 124774 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 312.4 | LABOR- SUBCONTRACTOR
%R | 501884 | 6359 | 124776 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ACGF4605 | Fixing of Ventilation Equipments | 8178 | 408 | 0 | 200 | 0 | 125.4 | 125.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-15 08:00 | 2014-02-13 17:00 |  | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 |  | PT_Normal |  |  |  |  | DsVKz5JbTzeqvXL30UDc1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41180 | N | N | 10 | GROUND FLOOR |  | 124774 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 125.4 | LABOR- SUBCONTRACTOR
%R | 501885 | 6359 | 124776 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ACGF4610 | Fixing of Split AC | 8178 | 408 | 40 | 160 | 0 | 331.1 | 331.1 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-03-01 17:00 |  | 2013-12-07 08:00 | 2013-12-30 17:00 | 2013-12-07 08:00 | 2013-12-30 17:00 | 2013-12-07 08:00 | 2013-12-30 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | rjV0EGNgRyGIo3qk9dAbtQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41180 | N | N | 10 | GROUND FLOOR |  | 124774 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 331.1 | LABOR- SUBCONTRACTOR
%R | 501886 | 6359 | 124777 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ACFF4615 | Installation AC Pipes | 8178 | 256 | 8 | 160 | 0 | 312.4 | 312.4 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-15 08:00 | 2014-01-07 17:00 |  | 2013-11-07 08:00 | 2013-11-30 17:00 | 2013-11-07 08:00 | 2013-11-30 17:00 | 2013-11-07 08:00 | 2013-11-30 17:00 | 2013-12-15 08:00 | 2014-01-07 17:00 |  | PT_Normal |  |  |  |  | ALuoNyK/Q/2WiqjeGPhChw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41190 | N | N | 15 | FIRST FLOORS |  | 124774 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 312.4 | LABOR- SUBCONTRACTOR
%R | 501887 | 6359 | 124777 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ACFF4620 | Fixing of Ventilation Equipments | 8178 | 72 | 0 | 200 | 0 | 125.4 | 125.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-15 08:00 | 2014-02-13 17:00 |  | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 |  | PT_Normal |  |  |  |  | AbzNsm3sS16QepKFtLIfng |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41190 | N | N | 15 | FIRST FLOORS |  | 124774 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 125.4 | LABOR- SUBCONTRACTOR
%R | 501888 | 6359 | 124777 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ACFF4625 | Fixing of Split AC | 8178 | 72 | 0 | 160 | 0 | 331.1 | 331.1 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-03-01 17:00 |  | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | XkvR9x/VTRiT8DRv1rKFng |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41190 | N | N | 15 | FIRST FLOORS |  | 124774 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 331.1 | LABOR- SUBCONTRACTOR
%R | 501889 | 6359 | 124779 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 352 | 16 | 200 | 0 | 1012.4 | 1012.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-13 08:00 | 2013-11-12 17:00 |  | 2013-08-22 08:00 | 2013-09-19 17:00 | 2013-08-22 08:00 | 2013-09-19 17:00 | 2013-08-22 08:00 | 2013-09-19 17:00 | 2013-10-13 08:00 | 2013-11-12 17:00 |  | PT_Normal |  |  |  |  | frApJpygRrar/4kFV6iQdw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41100 | N | N | 10 | GROUND FLOOR |  | 124778 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 1012.4 | LABOR- SUBCONTRACTOR
%R | 501890 | 6359 | 124779 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ELGF4005 | Cable tray & trunking installation | 8178 | 480 | 0 | 160 | 0 | 1687.6 | 1687.6 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-17 08:00 | 2013-12-09 17:00 |  | 2013-09-05 08:00 | 2013-09-28 17:00 | 2013-09-05 08:00 | 2013-09-28 17:00 | 2013-09-05 08:00 | 2013-09-28 17:00 | 2013-11-17 08:00 | 2013-12-09 17:00 |  | PT_Normal |  |  |  |  | T3moe+/KScK8LMNRmF/raw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41100 | N | N | 10 | GROUND FLOOR |  | 124778 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1687.6 | LABOR- SUBCONTRACTOR
%R | 501891 | 6359 | 124779 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ELGF4010 | Installation of wiring & Main Cabling | 8178 | 480 | 200 | 200 | 0 | 591.2 | 591.2 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-25 08:00 | 2013-12-24 17:00 |  | 2013-09-14 08:00 | 2013-10-12 17:00 | 2013-09-14 08:00 | 2013-10-12 17:00 | 2013-09-14 08:00 | 2013-10-12 17:00 | 2013-11-25 08:00 | 2013-12-24 17:00 |  | PT_Normal |  |  |  |  | ibF0zCP6To6dLjs9uc+ROg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41100 | N | N | 10 | GROUND FLOOR |  | 124778 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 591.2 | LABOR- SUBCONTRACTOR
%R | 501892 | 6359 | 124779 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 288 | 0 | 160 | 0 | 204.8 | 204.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-04 08:00 | 2014-01-26 17:00 |  | 2013-11-21 08:00 | 2013-12-14 17:00 | 2013-11-21 08:00 | 2013-12-14 17:00 | 2013-11-21 08:00 | 2013-12-14 17:00 | 2014-01-04 08:00 | 2014-01-26 17:00 |  | PT_Normal |  |  |  |  | u6LgKDjHQfWvs6plaEf/Fg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41100 | N | N | 10 | GROUND FLOOR |  | 124778 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 204.8 | LABOR- SUBCONTRACTOR
%R | 501893 | 6359 | 124779 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 296 | 0 | 200 | 0 | 2373.6 | 2373.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-02-15 17:00 |  | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 |  | PT_Normal |  |  |  |  | CxEo7DZ7QmCVehZtTX/ZMw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41100 | N | N | 10 | GROUND FLOOR |  | 124778 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 2373.6 | LABOR- SUBCONTRACTOR
%R | 501894 | 6359 | 124779 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 392 | 0 | 200 | 0 | 1344 | 1344 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-02-10 17:00 |  | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | H7EndVUCQACrQ5LRR3oAZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41100 | N | N | 10 | GROUND FLOOR |  | 124778 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1344 | LABOR- SUBCONTRACTOR
%R | 501895 | 6359 | 124779 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ELGF4030 | Installation of Telephone System | 8178 | 288 | 40 | 160 | 0 | 502.8 | 502.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-15 08:00 | 2014-02-06 17:00 |  | 2013-12-03 08:00 | 2013-12-26 17:00 | 2013-12-03 08:00 | 2013-12-26 17:00 | 2013-12-03 08:00 | 2013-12-26 17:00 | 2014-01-15 08:00 | 2014-02-06 17:00 |  | PT_Normal |  |  |  |  | XF32NHd6QQO+8FlSCI86dw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41100 | N | N | 10 | GROUND FLOOR |  | 124778 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 502.8 | LABOR- SUBCONTRACTOR
%R | 501896 | 6359 | 124780 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 80 | 16 | 200 | 0 | 1012.4 | 1012.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-16 08:00 | 2013-11-16 17:00 |  | 2013-10-05 08:00 | 2013-11-04 17:00 | 2013-10-05 08:00 | 2013-11-04 17:00 | 2013-10-05 08:00 | 2013-11-04 17:00 | 2013-10-16 08:00 | 2013-11-16 17:00 |  | PT_Normal |  |  |  |  | dnO4pSA8S5GyU9JsFna1Vw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41110 | N | N | 15 | FIRST FLOORS |  | 124778 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1012.4 | LABOR- SUBCONTRACTOR
%R | 501897 | 6359 | 124780 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ELFF4040 | Cable tray & trunking installation | 8178 | 240 | 0 | 160 | 0 | 1687.6 | 1687.6 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-25 08:00 | 2013-12-17 17:00 |  | 2013-10-21 08:00 | 2013-11-12 17:00 | 2013-10-21 08:00 | 2013-11-12 17:00 | 2013-10-21 08:00 | 2013-11-12 17:00 | 2013-11-25 08:00 | 2013-12-17 17:00 |  | PT_Normal |  |  |  |  | pxwKasfpT0K1e80L4tczww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41110 | N | N | 15 | FIRST FLOORS |  | 124778 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1687.6 | LABOR- SUBCONTRACTOR
%R | 501898 | 6359 | 124780 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ELFF4045 | Installation of wiring & Main Cabling | 8178 | 240 | 0 | 200 | 0 | 591.2 | 591.2 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-03 08:00 | 2014-01-01 17:00 |  | 2013-10-29 08:00 | 2013-11-26 17:00 | 2013-10-29 08:00 | 2013-11-26 17:00 | 2013-10-29 08:00 | 2013-11-26 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 |  | PT_Normal |  |  |  |  | mXi/fk2iSHO0zxzPJXQ/0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41110 | N | N | 15 | FIRST FLOORS |  | 124778 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 591.2 | LABOR- SUBCONTRACTOR
%R | 501899 | 6359 | 124780 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 8 | 0 | 160 | 0 | 171.2 | 171.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-09 08:00 | 2014-02-01 17:00 |  | 2014-01-08 08:00 | 2014-01-30 17:00 | 2014-01-08 08:00 | 2014-01-30 17:00 | 2014-01-08 08:00 | 2014-01-30 17:00 | 2014-01-09 08:00 | 2014-02-01 17:00 |  | PT_Normal |  |  |  |  | rxQG79OOTGCTLUQ3RLxGAQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41110 | N | N | 15 | FIRST FLOORS |  | 124778 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 171.2 | LABOR- SUBCONTRACTOR
%R | 501900 | 6359 | 124780 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 8 | 0 | 200 | 0 | 2322 | 2322 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-20 17:00 |  | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | QKZ95QNkRzO3DxOhOSS+rw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41110 | N | N | 15 | FIRST FLOORS |  | 124778 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 2322 | LABOR- SUBCONTRACTOR
%R | 501901 | 6359 | 124780 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 96 | 0 | 200 | 0 | 1478.4 | 1478.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-19 08:00 | 2014-02-17 17:00 |  | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 |  | PT_Normal |  |  |  |  | Bx5A+AXTQJiSwUCsEVdzVA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41110 | N | N | 15 | FIRST FLOORS |  | 124778 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1478.4 | LABOR- SUBCONTRACTOR
%R | 501902 | 6359 | 124780 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ELFF4050 | Installation of Telephone System | 8178 | 144 | 128 | 200 | 0 | 497.2 | 497.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-27 08:00 | 2014-02-25 17:00 |  | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 |  | PT_Normal |  |  |  |  | gSKCGtjQTZucDsP+0srWdg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41110 | N | N | 15 | FIRST FLOORS |  | 124778 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 497.2 | LABOR- SUBCONTRACTOR
%R | 501903 | 6359 | 124781 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ELRF4070 | Installation of Isolator | 8178 | 16 | 0 | 144 | 0 | 283.8 | 283.8 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-03-05 17:00 |  | 2014-02-10 08:00 | 2014-03-03 17:00 | 2014-02-10 08:00 | 2014-03-03 17:00 | 2014-02-10 08:00 | 2014-03-03 17:00 | 2014-02-13 08:00 | 2014-03-05 17:00 |  | PT_Normal |  |  |  |  | 6J5xBK5lSlOgFtLzu4bumA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41120 | N | N | 20 | ROOF |  | 124778 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 283.8 | LABOR- SUBCONTRACTOR
%R | 501904 | 6359 | 124781 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ELRF4075 | Installation of TV Dish Antenna | 8178 | 16 | 16 | 184 | 0 | 4331.8 | 4331.8 | 184 | 0 | 0 | 0 |  |  |  | 2014-02-20 08:00 | 2014-03-18 17:00 |  | 2014-02-18 08:00 | 2014-03-16 17:00 | 2014-02-18 08:00 | 2014-03-16 17:00 | 2014-02-18 08:00 | 2014-03-16 17:00 | 2014-02-20 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | L5o75fXXSN2Qk/+wserPmQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41120 | N | N | 20 | ROOF |  | 124778 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 4331.8 | LABOR- SUBCONTRACTOR
%R | 501905 | 6359 | 124783 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1PLFF4340 | Installation of Water Heater | 8178 | 112 | 0 | 120 | 0 | 46.2 | 46.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-01 17:00 |  | 2014-01-26 08:00 | 2014-02-12 17:00 | 2014-01-26 08:00 | 2014-02-12 17:00 | 2014-01-26 08:00 | 2014-02-12 17:00 | 2014-02-12 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | MQ2OrMrpSym8sJElEQ07yw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41150 | N | N | 15 | FIRST FLOORS |  | 124782 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 46.2 | LABOR- SUBCONTRACTOR
%R | 501906 | 6359 | 124783 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 0 | 0 | 144 | 0 | 2504.7 | 2504.7 | 144 | 0 | 0 | 0 |  |  |  | 2013-10-15 08:00 | 2013-11-06 17:00 |  | 2013-10-15 08:00 | 2013-11-06 17:00 | 2013-10-15 08:00 | 2013-11-06 17:00 | 2013-10-15 08:00 | 2013-11-06 17:00 | 2013-10-15 08:00 | 2013-11-06 17:00 |  | PT_Normal |  |  |  |  | iJzXL+9jSreC4L4qNYIdOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41150 | N | N | 15 | FIRST FLOORS |  | 124782 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 2504.7 | LABOR- SUBCONTRACTOR
%R | 501907 | 6359 | 124783 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1PLFF4330 | Installation of Drainage pipes & testing | 8178 | 200 | 48 | 144 | 0 | 198 | 198 | 144 | 0 | 0 | 0 |  |  |  | 2013-11-16 08:00 | 2013-12-05 17:00 |  | 2013-10-15 08:00 | 2013-11-06 17:00 | 2013-10-15 08:00 | 2013-11-06 17:00 | 2013-10-15 08:00 | 2013-11-06 17:00 | 2013-11-16 08:00 | 2013-12-05 17:00 |  | PT_Normal |  |  |  |  | L6Vvuyp5Rj+ELBuygpfQQA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41150 | N | N | 15 | FIRST FLOORS |  | 124782 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 198 | LABOR- SUBCONTRACTOR
%R | 501908 | 6359 | 124783 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1PLFF4335 | Sanitary Fittings & Accessories | 8178 | 112 | 0 | 160 | 0 | 323.4 | 323.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-02-23 17:00 |  | 2014-01-14 08:00 | 2014-02-05 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | pd7wG1M2T1eh6jMC1MTlQw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41150 | N | N | 15 | FIRST FLOORS |  | 124782 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 323.4 | LABOR- SUBCONTRACTOR
%R | 501909 | 6359 | 124784 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 536 | 112 | 120 | 0 | 1488.3 | 1488.3 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-02 08:00 | 2014-02-19 17:00 |  | 2013-11-14 08:00 | 2013-12-01 17:00 | 2013-11-14 08:00 | 2013-12-01 17:00 | 2013-11-14 08:00 | 2013-12-01 17:00 | 2014-02-02 08:00 | 2014-02-19 17:00 |  | PT_Normal |  |  |  |  | P3oYDX8bQeauvUfERjs6ug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41160 | N | N | 20 | ROOF |  | 124782 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1488.3 | LABOR- SUBCONTRACTOR
%R | 501910 | 6359 | 124784 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1PLRF4350 | Installation of Rain water Pipes | 8178 | 424 | 80 | 120 | 0 | 75.9 | 75.9 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-01 17:00 |  | 2013-12-10 08:00 | 2013-12-28 17:00 | 2013-12-10 08:00 | 2013-12-28 17:00 | 2013-12-10 08:00 | 2013-12-28 17:00 | 2014-02-12 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | W+fFAdRjTIyr+0wNpV+hVg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41160 | N | N | 20 | ROOF |  | 124782 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 75.9 | LABOR- SUBCONTRACTOR
%R | 501911 | 6359 | 124784 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 112 | 0 | 200 | 0 | 100.8 | 100.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-18 17:00 |  | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | 3Kz8T1Q1RiOfdgspY7YVJw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41160 | N | N | 20 | ROOF |  | 124782 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 501912 | 6359 | 124785 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 280 | 0 | 144 | 0 | 2504.7 | 2504.7 | 144 | 0 | 0 | 0 |  |  |  | 2013-10-13 08:00 | 2013-11-04 17:00 |  | 2013-09-02 08:00 | 2013-09-22 17:00 | 2013-09-02 08:00 | 2013-09-22 17:00 | 2013-09-02 08:00 | 2013-09-22 17:00 | 2013-10-13 08:00 | 2013-11-04 17:00 |  | PT_Normal |  |  |  |  | FNljR2SkSyqU8r8umpwClw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41140 | N | N | 10 | GROUND FLOOR |  | 124782 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 2504.7 | LABOR- SUBCONTRACTOR
%R | 501913 | 6359 | 124785 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1PLGF4310 | Installation of Drainage pipes &testing | 8178 | 448 | 168 | 144 | 0 | 198 | 198 | 144 | 0 | 0 | 0 |  |  |  | 2013-11-09 08:00 | 2013-11-28 17:00 |  | 2013-09-02 08:00 | 2013-09-22 17:00 | 2013-09-02 08:00 | 2013-09-22 17:00 | 2013-09-02 08:00 | 2013-09-22 17:00 | 2013-11-09 08:00 | 2013-11-28 17:00 |  | PT_Normal |  |  |  |  | rmyRH1ZfS4SDYcmJyOG6vg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41140 | N | N | 10 | GROUND FLOOR |  | 124782 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 198 | LABOR- SUBCONTRACTOR
%R | 501914 | 6359 | 124785 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1PLGF4315 | Sanitary Fittings & Accessories | 8178 | 512 | 0 | 160 | 0 | 323.4 | 323.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-12 17:00 |  | 2013-12-03 08:00 | 2013-12-26 17:00 | 2013-12-03 08:00 | 2013-12-26 17:00 | 2013-12-03 08:00 | 2013-12-26 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 |  | PT_Normal |  |  |  |  | ggahRbk3S1SjGshuJTcB/A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41140 | N | N | 10 | GROUND FLOOR |  | 124782 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 323.4 | LABOR- SUBCONTRACTOR
%R | 501915 | 6359 | 124785 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1PLGF4320 | Installation of Water Heater | 8178 | 512 | 80 | 120 | 0 | 46.2 | 46.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-18 17:00 |  | 2013-12-15 08:00 | 2014-01-01 17:00 | 2013-12-15 08:00 | 2014-01-01 17:00 | 2013-12-15 08:00 | 2014-01-01 17:00 | 2014-03-02 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | IGHFEPH3SCiH6NCrPq1q0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41140 | N | N | 10 | GROUND FLOOR |  | 124782 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 46.2 | LABOR- SUBCONTRACTOR
%R | 501916 | 6359 | 124785 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 0 | 0 | 160 | 0 | 165.6 | 165.6 | 160 | 0 | 0 | 0 |  |  |  | 2013-05-08 08:00 | 2013-05-30 17:00 |  | 2013-05-08 08:00 | 2013-05-30 17:00 | 2013-05-08 08:00 | 2013-05-30 17:00 | 2013-05-08 08:00 | 2013-05-30 17:00 | 2013-05-08 08:00 | 2013-05-30 17:00 |  | PT_Normal |  |  |  |  | mWMPXWUJTSC0ZrFrPijEGQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41140 | N | N | 10 | GROUND FLOOR |  | 124782 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 165.6 | LABOR- SUBCONTRACTOR
%R | 501917 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3000 | Block work | 8168 | 280 | 0 | 200 | 0 | 4741 | 4741 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-26 08:00 | 2013-10-27 17:00 |  | 2013-08-17 08:00 | 2013-09-14 17:00 | 2013-08-17 08:00 | 2013-09-14 17:00 | 2013-08-17 08:00 | 2013-09-14 17:00 | 2013-09-26 08:00 | 2013-10-27 17:00 |  | PT_Normal |  |  |  |  | QO3aSd+UTNaEK2tI0yTSpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 4741 | BLOCK MASON SK
%R | 501918 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3005 | Plastering work | 8169 | 280 | 0 | 200 | 0 | 4178.5 | 4178.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-21 08:00 | 2013-11-18 17:00 |  | 2013-09-08 08:00 | 2013-10-06 17:00 | 2013-09-08 08:00 | 2013-10-06 17:00 | 2013-09-08 08:00 | 2013-10-06 17:00 | 2013-10-21 08:00 | 2013-11-18 17:00 |  | PT_Normal |  |  |  |  | tqblY2azQkWvZ3pCtHoSRw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 4178.5 | PLASTER MASON SK
%R | 501919 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3010 | Flooring screed | 8164 | 344 | 64 | 168 | 0 | 824 | 824 | 168 | 0 | 0 | 0 |  |  |  | 2013-11-07 08:00 | 2013-12-01 17:00 |  | 2013-09-16 08:00 | 2013-10-09 17:00 | 2013-09-16 08:00 | 2013-10-09 17:00 | 2013-09-16 08:00 | 2013-10-09 17:00 | 2013-11-07 08:00 | 2013-12-01 17:00 |  | PT_Normal |  |  |  |  | DyJG8XkTTfOYSbfSrB7oOQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 824 | SCREED MASON SK
%R | 501920 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 280 | 0 | 120 | 0 | 387.75 | 387.75 | 120 | 0 | 0 | 0 |  |  |  | 2013-11-07 08:00 | 2013-11-24 17:00 |  | 2013-09-25 08:00 | 2013-10-12 17:00 | 2013-09-25 08:00 | 2013-10-12 17:00 | 2013-09-25 08:00 | 2013-10-12 17:00 | 2013-11-07 08:00 | 2013-11-24 17:00 |  | PT_Normal |  |  |  |  | ms8d3TKCRG2ImryBiAj9aA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 387.75 | LABOR- SUBCONTRACTOR
%R | 501921 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3030 | Paint First coat | 8178 | 344 | 0 | 200 | 0 | 2758.25 | 2758.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-23 08:00 | 2013-12-22 17:00 |  | 2013-10-01 08:00 | 2013-10-31 17:00 | 2013-10-01 08:00 | 2013-10-31 17:00 | 2013-10-01 08:00 | 2013-10-31 17:00 | 2013-11-23 08:00 | 2013-12-22 17:00 |  | PT_Normal |  |  |  |  | 2IkLcIETQIeRQyz5pKG4HA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 2758.25 | LABOR- SUBCONTRACTOR
%R | 501922 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3020 | Ceramic Wall Tiling | 8170 | 280 | 0 | 200 | 0 | 1734.75 | 1734.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-13 08:00 | 2013-12-11 17:00 |  | 2013-10-01 08:00 | 2013-10-31 17:00 | 2013-10-01 08:00 | 2013-10-31 17:00 | 2013-10-01 08:00 | 2013-10-31 17:00 | 2013-11-13 08:00 | 2013-12-11 17:00 |  | PT_Normal |  |  |  |  | NtPy9j/SQr6H6uu9jpHlJQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1734.75 | TILE MASON SK
%R | 501923 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3025 | Porcelain Tile flooring | 8170 | 280 | 0 | 200 | 0 | 1192.75 | 1192.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-19 08:00 | 2013-12-17 17:00 |  | 2013-10-07 08:00 | 2013-11-06 17:00 | 2013-10-07 08:00 | 2013-11-06 17:00 | 2013-10-07 08:00 | 2013-11-06 17:00 | 2013-11-19 08:00 | 2013-12-17 17:00 |  | PT_Normal |  |  |  |  | LBX/EYStS26FsgSf4Aj4oQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1192.75 | TILE MASON SK
%R | 501924 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3040 | Cobble Tile flooring | 8170 | 320 | 0 | 120 | 0 | 45.5 | 45.5 | 120 | 0 | 0 | 0 |  |  |  | 2013-12-23 08:00 | 2014-01-08 17:00 |  | 2013-11-05 08:00 | 2013-11-21 17:00 | 2013-11-05 08:00 | 2013-11-21 17:00 | 2013-11-05 08:00 | 2013-11-21 17:00 | 2013-12-23 08:00 | 2014-01-08 17:00 |  | PT_Normal |  |  |  |  | zTFPaOXNSKu0JxGs5ZBiXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 45.5 | TILE MASON SK
%R | 501925 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 336 | 16 | 120 | 0 | 31.25 | 31.25 | 120 | 0 | 0 | 0 |  |  |  | 2013-12-17 08:00 | 2014-01-04 17:00 |  | 2013-10-29 08:00 | 2013-11-14 17:00 | 2013-10-29 08:00 | 2013-11-14 17:00 | 2013-10-29 08:00 | 2013-11-14 17:00 | 2013-12-17 08:00 | 2014-01-04 17:00 |  | PT_Normal |  |  |  |  | jZl2aLpDRraVnLKJIrzqZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 31.25 | TILE MASON SK
%R | 501926 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 320 | 0 | 160 | 0 | 337.5 | 337.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-31 08:00 | 2014-01-22 17:00 |  | 2013-11-13 08:00 | 2013-12-05 17:00 | 2013-11-13 08:00 | 2013-12-05 17:00 | 2013-11-13 08:00 | 2013-12-05 17:00 | 2013-12-31 08:00 | 2014-01-22 17:00 |  | PT_Normal |  |  |  |  | nDBv/7zjSRygfS6u9OQEPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 337.5 | GRANITE MASON SK
%R | 501927 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3045 | Fixing of Suspension systems | 8178 | 280 | 0 | 160 | 0 | 956.25 | 956.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-07 08:00 | 2013-12-30 17:00 |  | 2013-10-27 08:00 | 2013-11-18 17:00 | 2013-10-27 08:00 | 2013-11-18 17:00 | 2013-10-27 08:00 | 2013-11-18 17:00 | 2013-12-07 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | y9bHT/A3RZqNHzarYJ5/Kg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 956.25 | LABOR- SUBCONTRACTOR
%R | 501928 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3055 | Aluminum tile false ceiling | 8178 | 312 | 24 | 200 | 0 | 103.9 | 103.9 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-21 08:00 | 2014-01-18 17:00 |  | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | UVgpdv3BRDOY/I7vMkheoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 103.9 | LABOR- SUBCONTRACTOR
%R | 501929 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3060 | Gypsum board false ceiling | 8178 | 280 | 0 | 200 | 0 | 866 | 866 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-19 08:00 | 2014-01-16 17:00 |  | 2013-11-07 08:00 | 2013-12-05 17:00 | 2013-11-07 08:00 | 2013-12-05 17:00 | 2013-11-07 08:00 | 2013-12-05 17:00 | 2013-12-19 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | HqD7oPscTCiLJUqroMKY7g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 866 | LABOR- SUBCONTRACTOR
%R | 501930 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3065 | Wooden door | 8178 | 320 | 0 | 120 | 0 | 275 | 275 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-01-30 17:00 |  | 2013-11-27 08:00 | 2013-12-14 17:00 | 2013-11-27 08:00 | 2013-12-14 17:00 | 2013-11-27 08:00 | 2013-12-14 17:00 | 2014-01-14 08:00 | 2014-01-30 17:00 |  | PT_Normal |  |  |  |  | I/dkUpS0SYafdan4SKQcrg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 275 | LABOR- SUBCONTRACTOR
%R | 501931 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3070 | Aluminum doors | 8178 | 320 | 0 | 120 | 0 | 66 | 66 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-20 08:00 | 2014-02-05 17:00 |  | 2013-12-03 08:00 | 2013-12-21 17:00 | 2013-12-03 08:00 | 2013-12-21 17:00 | 2013-12-03 08:00 | 2013-12-21 17:00 | 2014-01-20 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | Q07YbMbzSDKpb6HkAzVkbg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 66 | LABOR- SUBCONTRACTOR
%R | 501932 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3080 | Aluminum windows | 8178 | 400 | 40 | 160 | 0 | 147.5 | 147.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-08 08:00 | 2014-03-03 17:00 |  | 2013-12-10 08:00 | 2014-01-02 17:00 | 2013-12-10 08:00 | 2014-01-02 17:00 | 2013-12-10 08:00 | 2014-01-02 17:00 | 2014-02-08 08:00 | 2014-03-03 17:00 |  | PT_Normal |  |  |  |  | wHtftFCDQ7e3PaTXS4ptng |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 147.5 | LABOR- SUBCONTRACTOR
%R | 501933 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3075 | Carpentry & Joinery Works | 8178 | 320 | 0 | 160 | 0 | 528 | 528 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-26 08:00 | 2014-02-18 17:00 |  | 2013-12-09 08:00 | 2014-01-01 17:00 | 2013-12-09 08:00 | 2014-01-01 17:00 | 2013-12-09 08:00 | 2014-01-01 17:00 | 2014-01-26 08:00 | 2014-02-18 17:00 |  | PT_Normal |  |  |  |  | sJCUac0OQnmiZmIjnNjuYw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 528 | LABOR- SUBCONTRACTOR
%R | 501934 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3090 | Installation of Granite Counter Top | 8171 | 320 | 0 | 120 | 0 | 88 | 88 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-08 08:00 | 2014-02-25 17:00 |  | 2013-12-23 08:00 | 2014-01-08 17:00 | 2013-12-23 08:00 | 2014-01-08 17:00 | 2013-12-23 08:00 | 2014-01-08 17:00 | 2014-02-08 08:00 | 2014-02-25 17:00 |  | PT_Normal |  |  |  |  | R0OtpuBzTjCt4+HZeBfFMw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 88 | GRANITE MASON SK
%R | 501935 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3085 | S.S.Balustrade | 8178 | 360 | 40 | 160 | 0 | 31.25 | 31.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-03-04 17:00 |  | 2013-12-17 08:00 | 2014-01-09 17:00 | 2013-12-17 08:00 | 2014-01-09 17:00 | 2013-12-17 08:00 | 2014-01-09 17:00 | 2014-02-09 08:00 | 2014-03-04 17:00 |  | PT_Normal |  |  |  |  | s2VxxBbVRc6gH/XrUpaTOQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 31.25 | LABOR- SUBCONTRACTOR
%R | 501936 | 6359 | 124788 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARGF3095 | Final Painting | 8178 | 320 | 0 | 200 | 0 | 2758.25 | 2758.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-18 17:00 |  | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | aWVHBVAqT2+ecjj2wZhV+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41020 | N | N | 10 | GROUND FLOOR |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 2758.25 | LABOR- SUBCONTRACTOR
%R | 501937 | 6359 | 124789 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARFF3320 | Ceramic Wall Tiling | 8170 | 0 | 0 | 200 | 0 | 1734.75 | 1734.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-24 08:00 | 2013-12-23 17:00 |  | 2013-11-24 08:00 | 2013-12-23 17:00 | 2013-11-24 08:00 | 2013-12-23 17:00 | 2013-11-24 08:00 | 2013-12-23 17:00 | 2013-11-24 08:00 | 2013-12-23 17:00 |  | PT_Normal |  |  |  |  | gH0DHpojSc6Yj1Hmo0LtFg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41030 | N | N | 15 | FIRST FLOORS |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1734.75 | TILE MASON SK
%R | 501938 | 6359 | 124789 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARFF3325 | Porcelain Tile flooring | 8170 | 0 | 0 | 200 | 0 | 1192.75 | 1192.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-01 08:00 | 2013-12-30 17:00 |  | 2013-12-01 08:00 | 2013-12-30 17:00 | 2013-12-01 08:00 | 2013-12-30 17:00 | 2013-12-01 08:00 | 2013-12-30 17:00 | 2013-12-01 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | 7f4sEwIJSruyxyMxqVgWwA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41030 | N | N | 15 | FIRST FLOORS |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1192.75 | TILE MASON SK
%R | 501939 | 6359 | 124789 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARFF3335 | Slate Tile Flooring & Skirting | 8178 | 80 | 80 | 120 | 0 | 1350 | 1350 | 120 | 0 | 0 | 0 |  |  |  | 2013-12-31 08:00 | 2014-01-16 17:00 |  | 2013-12-19 08:00 | 2014-01-05 17:00 | 2013-12-19 08:00 | 2014-01-05 17:00 | 2013-12-19 08:00 | 2014-01-05 17:00 | 2013-12-31 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | ab5/HwtvQlGq8s9k+FElWQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41030 | N | N | 15 | FIRST FLOORS |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1350 | LABOR- SUBCONTRACTOR
%R | 501940 | 6359 | 124789 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARFF3350 | Granite - Stair case flooring & Skirting | 8178 | 16 | 16 | 160 | 0 | 150 | 150 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-25 08:00 | 2014-01-16 17:00 |  | 2013-12-23 08:00 | 2014-01-14 17:00 | 2013-12-23 08:00 | 2014-01-14 17:00 | 2013-12-23 08:00 | 2014-01-14 17:00 | 2013-12-25 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | HRj7mB41RZyl0+UcdJ3Lfw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41030 | N | N | 15 | FIRST FLOORS |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 150 | LABOR- SUBCONTRACTOR
%R | 501941 | 6359 | 124789 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARFF3345 | Fixing of Suspension systems | 8178 | 0 | 0 | 160 | 0 | 956.25 | 956.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-15 08:00 | 2014-01-07 17:00 |  | 2013-12-15 08:00 | 2014-01-07 17:00 | 2013-12-15 08:00 | 2014-01-07 17:00 | 2013-12-15 08:00 | 2014-01-07 17:00 | 2013-12-15 08:00 | 2014-01-07 17:00 |  | PT_Normal |  |  |  |  | x3YYTF+/TX6FiiDQy0MajQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41030 | N | N | 15 | FIRST FLOORS |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 956.25 | LABOR- SUBCONTRACTOR
%R | 501942 | 6359 | 124789 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARFF3355 | Aluminum tile false ceiling | 8178 | 16 | 0 | 160 | 0 | 103.9 | 103.9 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-30 08:00 | 2014-01-21 17:00 |  | 2013-12-28 08:00 | 2014-01-19 17:00 | 2013-12-28 08:00 | 2014-01-19 17:00 | 2013-12-28 08:00 | 2014-01-19 17:00 | 2013-12-30 08:00 | 2014-01-21 17:00 |  | PT_Normal |  |  |  |  | z30deSdnQxOVYFfotNCDLg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41030 | N | N | 15 | FIRST FLOORS |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 103.9 | LABOR- SUBCONTRACTOR
%R | 501943 | 6359 | 124789 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARFF3360 | Gypsum board false ceiling | 8178 | 0 | 0 | 200 | 0 | 866 | 866 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-24 08:00 | 2014-01-21 17:00 |  | 2013-12-24 08:00 | 2014-01-21 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 |  | PT_Normal |  |  |  |  | co8sUmvvQpmw1UYKMbS5Xg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41030 | N | N | 15 | FIRST FLOORS |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 866 | LABOR- SUBCONTRACTOR
%R | 501944 | 6359 | 124789 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARFF3365 | Wooden door | 8178 | 0 | 0 | 120 | 0 | 220 | 220 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-08 08:00 | 2014-01-25 17:00 |  | 2014-01-08 08:00 | 2014-01-25 17:00 | 2014-01-08 08:00 | 2014-01-25 17:00 | 2014-01-08 08:00 | 2014-01-25 17:00 | 2014-01-08 08:00 | 2014-01-25 17:00 |  | PT_Normal |  |  |  |  | R6UTwKs1QUaS2MsXWEP24w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41030 | N | N | 15 | FIRST FLOORS |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 220 | LABOR- SUBCONTRACTOR
%R | 501945 | 6359 | 124789 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARFF3370 | Aluminum Door | 8178 | 0 | 0 | 160 | 0 | 66 | 66 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-02-08 17:00 |  | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-01-16 08:00 | 2014-02-08 17:00 |  | PT_Normal |  |  |  |  | mcL72ivxRAGA/gg05vNq4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41030 | N | N | 15 | FIRST FLOORS |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 66 | LABOR- SUBCONTRACTOR
%R | 501946 | 6359 | 124789 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARFF3380 | Aluminum windows | 8178 | 88 | 88 | 160 | 0 | 176 | 176 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-03-01 17:00 |  | 2014-01-23 08:00 | 2014-02-16 17:00 | 2014-01-23 08:00 | 2014-02-16 17:00 | 2014-01-23 08:00 | 2014-02-16 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | NYbk/3F2RvisuTMMEIsUiw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41030 | N | N | 15 | FIRST FLOORS |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 176 | LABOR- SUBCONTRACTOR
%R | 501947 | 6359 | 124789 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARFF3375 | Carpentry & Joinery Works | 8178 | 0 | 0 | 200 | 0 | 278 | 278 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-25 08:00 | 2014-02-23 17:00 |  | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | LdRJzPsMRrWZNcVfwfbpEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41030 | N | N | 15 | FIRST FLOORS |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 278 | LABOR- SUBCONTRACTOR
%R | 501948 | 6359 | 124789 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARFF3390 | Installation of Granite Counter Top | 8171 | 0 | 0 | 160 | 0 | 88 | 88 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-08 08:00 | 2014-03-03 17:00 |  | 2014-02-08 08:00 | 2014-03-03 17:00 | 2014-02-08 08:00 | 2014-03-03 17:00 | 2014-02-08 08:00 | 2014-03-03 17:00 | 2014-02-08 08:00 | 2014-03-03 17:00 |  | PT_Normal |  |  |  |  | FZpVDyZxTqqTV7w1MAu3tA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41030 | N | N | 15 | FIRST FLOORS |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 88 | GRANITE MASON SK
%R | 501949 | 6359 | 124789 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARFF3385 | Handrail & Balustrade | 8301 | 8 | 8 | 160 | 0 | 250 | 250 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-03-02 17:00 |  | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-02-06 08:00 | 2014-03-02 17:00 |  | PT_Normal |  |  |  |  | YODHET1NQ1SzBFN+wPIRLw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 45900 |  |  |  |  | HANDRAIL ERECTOR SKILLED | S308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41030 | N | N | 15 | FIRST FLOORS |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 250 | HANDRAIL ERECTOR SKILLED
%R | 501950 | 6359 | 124789 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARFF3395 | Final Painting | 8178 | 0 | 0 | 200 | 0 | 2872 | 2872 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-18 17:00 |  | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | oqHE0f8ZTUeNVK1S5zwkKw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41030 | N | N | 15 | FIRST FLOORS |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 1436 | LABOR- SUBCONTRACTOR
%R | 501951 | 6359 | 124789 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARFF3300 | Block work | 8168 | 0 | 0 | 192 | 0 | 3703.5 | 3703.5 | 192 | 0 | 0 | 0 |  |  |  | 2013-09-29 08:00 | 2013-10-28 17:00 |  | 2013-09-29 08:00 | 2013-10-28 17:00 | 2013-09-29 08:00 | 2013-10-28 17:00 | 2013-09-29 08:00 | 2013-10-28 17:00 | 2013-09-29 08:00 | 2013-10-28 17:00 |  | PT_Normal |  |  |  |  | 883XaHghQXKjb0qCCdXsiw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41030 | N | N | 15 | FIRST FLOORS |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 3703.5 | BLOCK MASON SK
%R | 501952 | 6359 | 124789 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARFF3305 | Plastering work | 8169 | 0 | 0 | 200 | 0 | 3678.5 | 3678.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-24 08:00 | 2013-11-21 17:00 |  | 2013-10-24 08:00 | 2013-11-21 17:00 | 2013-10-24 08:00 | 2013-11-21 17:00 | 2013-10-24 08:00 | 2013-11-21 17:00 | 2013-10-24 08:00 | 2013-11-21 17:00 |  | PT_Normal |  |  |  |  | GcMs4cstQbKJlSdi5wKsJA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41030 | N | N | 15 | FIRST FLOORS |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 3678.5 | PLASTER MASON SK
%R | 501953 | 6359 | 124789 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARFF3310 | Flooring screed | 8164 | 120 | 120 | 168 | 0 | 687.5 | 687.5 | 168 | 0 | 0 | 0 |  |  |  | 2013-11-19 08:00 | 2013-12-12 17:00 |  | 2013-11-02 08:00 | 2013-11-25 17:00 | 2013-11-02 08:00 | 2013-11-25 17:00 | 2013-11-02 08:00 | 2013-11-25 17:00 | 2013-11-19 08:00 | 2013-12-12 17:00 |  | PT_Normal |  |  |  |  | hWwCtOCBRrWAVudY8E/LBQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41030 | N | N | 15 | FIRST FLOORS |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 687.5 | SCREED MASON SK
%R | 501954 | 6359 | 124789 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARFF3315 | Wet area waterproofing | 8178 | 0 | 0 | 120 | 0 | 387.75 | 387.75 | 120 | 0 | 0 | 0 |  |  |  | 2013-11-14 08:00 | 2013-12-01 17:00 |  | 2013-11-14 08:00 | 2013-12-01 17:00 | 2013-11-14 08:00 | 2013-12-01 17:00 | 2013-11-14 08:00 | 2013-12-01 17:00 | 2013-11-14 08:00 | 2013-12-01 17:00 |  | PT_Normal |  |  |  |  | 1905RnEFQWSyWBx4oDKcQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41030 | N | N | 15 | FIRST FLOORS |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 387.75 | LABOR- SUBCONTRACTOR
%R | 501955 | 6359 | 124789 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARFF3330 | Paint First coat | 8178 | 144 | 144 | 200 | 0 | 2872 | 2872 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-01 08:00 | 2013-12-30 17:00 |  | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-12-01 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | D8DqXOCjRPSliBk7PEFyLg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41030 | N | N | 15 | FIRST FLOORS |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 2872 | LABOR- SUBCONTRACTOR
%R | 501956 | 6359 | 124790 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARRF3600 | Block work | 8168 | 536 | 0 | 160 | 0 | 325 | 325 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-06 08:00 | 2014-01-28 17:00 |  | 2013-10-16 08:00 | 2013-11-10 17:00 | 2013-10-16 08:00 | 2013-11-10 17:00 | 2013-10-16 08:00 | 2013-11-10 17:00 | 2014-01-06 08:00 | 2014-01-28 17:00 |  | PT_Normal |  |  |  |  | CqzrzTRiQ0KMbzjN0fLANQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41040 | N | N | 20 | ROOF |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 325 | BLOCK MASON SK
%R | 501957 | 6359 | 124790 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARRF3605 | Plastering work | 8169 | 536 | 0 | 160 | 0 | 1300 | 1300 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-02-05 17:00 |  | 2013-10-27 08:00 | 2013-11-18 17:00 | 2013-10-27 08:00 | 2013-11-18 17:00 | 2013-10-27 08:00 | 2013-11-18 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | x2YJz17iTqmkOHLL3GTyDg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41040 | N | N | 20 | ROOF |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1300 | PLASTER MASON SK
%R | 501958 | 6359 | 124790 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARRF3610 | Flooring screed | 8164 | 576 | 280 | 120 | 0 | 77 | 77 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-03 08:00 | 2014-02-20 17:00 |  | 2013-11-10 08:00 | 2013-11-26 17:00 | 2013-11-10 08:00 | 2013-11-26 17:00 | 2013-11-10 08:00 | 2013-11-26 17:00 | 2014-02-03 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | SQPQlN2PSSKxIordNTGsAQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41040 | N | N | 20 | ROOF |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 77 | SCREED MASON SK
%R | 501959 | 6359 | 124790 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARRF3695 | Painting | 8178 | 296 | 0 | 160 | 0 | 460 | 460 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-06 17:00 |  | 2013-12-30 08:00 | 2014-01-21 17:00 | 2013-12-30 08:00 | 2014-01-21 17:00 | 2013-12-30 08:00 | 2014-01-21 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | gJ877H9ZQ7qd2zp5sHdscQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41040 | N | N | 20 | ROOF |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 460 | LABOR- SUBCONTRACTOR
%R | 501960 | 6359 | 124790 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARRF3620 | Epoxy Painting | 8178 | 296 | 296 | 120 | 0 | 16.5 | 16.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-18 17:00 |  | 2014-01-16 08:00 | 2014-02-02 17:00 | 2014-01-16 08:00 | 2014-02-02 17:00 | 2014-01-16 08:00 | 2014-02-02 17:00 | 2014-03-02 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | zMlpeygWQhiEq3FCTx2KXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41040 | N | N | 20 | ROOF |  | 124787 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 16.5 | LABOR- SUBCONTRACTOR
%R | 501961 | 6359 | 124792 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARRF3630 | Leveling Screed for Waterproofing | 8164 | 496 | 0 | 200 | 0 | 489.25 | 489.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-06 08:00 | 2014-02-03 17:00 |  | 2013-10-24 08:00 | 2013-11-21 17:00 | 2013-10-24 08:00 | 2013-11-21 17:00 | 2013-10-24 08:00 | 2013-11-21 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 |  | PT_Normal |  |  |  |  | zEZb1eHTQ9S6h0zY/pszaA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41060 | N | N | 10 | ROOF |  | 124791 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 489.25 | SCREED MASON SK
%R | 501962 | 6359 | 124792 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARRF3635 | Laying of Waterproofing Membrane | 8178 | 480 | 0 | 200 | 0 | 1361.25 | 1361.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-09 08:00 | 2014-02-06 17:00 |  | 2013-10-30 08:00 | 2013-11-27 17:00 | 2013-10-30 08:00 | 2013-11-27 17:00 | 2013-10-30 08:00 | 2013-11-27 17:00 | 2014-01-09 08:00 | 2014-02-06 17:00 |  | PT_Normal |  |  |  |  | 2N4SEpLnTUK32Vn1mlRXjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41060 | N | N | 10 | ROOF |  | 124791 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1361.25 | LABOR- SUBCONTRACTOR
%R | 501963 | 6359 | 124792 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARRF3640 | Installation of Insulation & Protection | 8178 | 480 | 0 | 200 | 0 | 860.75 | 860.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-02-12 17:00 |  | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 |  | PT_Normal |  |  |  |  | dNsMmfK+T3iQM0pL4ESIcA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41060 | N | N | 10 | ROOF |  | 124791 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 860.75 | LABOR- SUBCONTRACTOR
%R | 501964 | 6359 | 124792 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 480 | 0 | 200 | 0 | 495 | 495 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-19 08:00 | 2014-02-17 17:00 |  | 2013-11-09 08:00 | 2013-12-07 17:00 | 2013-11-09 08:00 | 2013-12-07 17:00 | 2013-11-09 08:00 | 2013-12-07 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 |  | PT_Normal |  |  |  |  | KoPuMyq/T1SIfhMJ0fsjng |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41060 | N | N | 10 | ROOF |  | 124791 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 495 | TILE MASON SK
%R | 501965 | 6359 | 124792 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 480 | 0 | 160 | 0 | 154 | 154 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-06 17:00 |  | 2013-12-02 08:00 | 2013-12-25 17:00 | 2013-12-02 08:00 | 2013-12-25 17:00 | 2013-12-02 08:00 | 2013-12-25 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | +50cTco7T4CLV9H1i6btGA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41060 | N | N | 10 | ROOF |  | 124791 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 154 | LABOR- SUBCONTRACTOR
%R | 501966 | 6359 | 124792 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 480 | 0 | 200 | 0 | 588 | 588 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-27 08:00 | 2014-02-25 17:00 |  | 2013-11-17 08:00 | 2013-12-15 17:00 | 2013-11-17 08:00 | 2013-12-15 17:00 | 2013-11-17 08:00 | 2013-12-15 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 |  | PT_Normal |  |  |  |  | lr9rya6iT66fCOKrSK+umg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41060 | N | N | 10 | ROOF |  | 124791 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 588 | LABOR- SUBCONTRACTOR
%R | 501967 | 6359 | 124792 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ARRF3660 | Installation of Access Ladder | 8178 | 520 | 520 | 120 | 0 | 132 | 132 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-18 17:00 |  | 2013-12-14 08:00 | 2013-12-31 17:00 | 2013-12-14 08:00 | 2013-12-31 17:00 | 2013-12-14 08:00 | 2013-12-31 17:00 | 2014-03-02 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | 2/h3lrUHTde3fo3VIezJzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41060 | N | N | 10 | ROOF |  | 124791 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 132 | LABOR- SUBCONTRACTOR
%R | 501968 | 6359 | 124793 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1AREL3665 | External Plastering | 8169 | 424 | 0 | 200 | 0 | 6106.25 | 6106.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-20 17:00 |  | 2013-11-20 08:00 | 2013-12-19 17:00 | 2013-11-20 08:00 | 2013-12-19 17:00 | 2013-11-20 08:00 | 2013-12-19 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | AE/jlQ/6R46zjQHgP8xD2Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41070 | N | N | 15 | ELEVATION |  | 124791 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 6106.25 | PLASTER MASON SK
%R | 501969 | 6359 | 124793 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1AREL3675 | GRC Panel Works | 8178 | 440 | 40 | 160 | 0 | 550 | 550 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-06 17:00 |  | 2013-12-08 08:00 | 2013-12-31 17:00 | 2013-12-08 08:00 | 2013-12-31 17:00 | 2013-12-08 08:00 | 2013-12-31 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | VlxJPq+bRNKTbBzsFTIrbg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41070 | N | N | 15 | ELEVATION |  | 124791 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 550 | LABOR- SUBCONTRACTOR
%R | 501970 | 6359 | 124793 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1AREL3680 | External Painting | 8178 | 344 | 0 | 160 | 0 | 2970 | 2970 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-18 17:00 |  | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | VrPOnGoZRGCx6zn3nRmb2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41070 | N | N | 15 | ELEVATION |  | 124791 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 2970 | LABOR- SUBCONTRACTOR
%R | 501971 | 6359 | 124794 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 0 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | s9U8fhxCSLyxRjrgDo/BkQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41270 | N | N | 30 | TESTING AND COMMISSIONING |  | 124762 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 501972 | 6359 | 124794 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | lybv+joLTPC7y8Dm8TAaYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41270 | N | N | 30 | TESTING AND COMMISSIONING |  | 124762 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 501973 | 6359 | 124794 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z1PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | iDZ//3YvSm6W6IKXk4Fi9g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41270 | N | N | 30 | TESTING AND COMMISSIONING |  | 124762 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 501974 | 6359 | 124798 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARRF3600 | Block work | 8168 | 536 | 0 | 160 | 0 | 487.5 | 487.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-06 08:00 | 2014-03-29 17:00 |  | 2013-12-16 08:00 | 2014-01-08 17:00 | 2013-12-16 08:00 | 2014-01-08 17:00 | 2013-12-16 08:00 | 2014-01-08 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 |  | PT_Normal |  |  |  |  | LKZo8cciQL2SmGBWGGIFOQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41760 | N | N | 20 | ROOF |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 487.5 | BLOCK MASON SK
%R | 501975 | 6359 | 124798 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARRF3605 | Plastering work | 8169 | 536 | 0 | 160 | 0 | 1950 | 1950 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-06 17:00 |  | 2013-12-25 08:00 | 2014-01-16 17:00 | 2013-12-25 08:00 | 2014-01-16 17:00 | 2013-12-25 08:00 | 2014-01-16 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | I22UosdXRP2zTUyOXzJxhA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41760 | N | N | 20 | ROOF |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1950 | PLASTER MASON SK
%R | 501976 | 6359 | 124798 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARRF3610 | Flooring screed | 8164 | 576 | 0 | 120 | 0 | 115.5 | 115.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-03 08:00 | 2014-04-20 17:00 |  | 2014-01-08 08:00 | 2014-01-25 17:00 | 2014-01-08 08:00 | 2014-01-25 17:00 | 2014-01-08 08:00 | 2014-01-25 17:00 | 2014-04-03 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | 9SrXVtklTjibHJ1t+EQaxg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41760 | N | N | 20 | ROOF |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 115.5 | SCREED MASON SK
%R | 501977 | 6359 | 124798 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARRF3695 | Painting | 8178 | 576 | 0 | 160 | 0 | 504 | 504 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-04 17:00 |  | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | X4Fo4uaLRrSr84FzPnhbIA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41760 | N | N | 20 | ROOF |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 504 | LABOR- SUBCONTRACTOR
%R | 501978 | 6359 | 124798 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARRF3620 | Epoxy Painting | 8178 | 576 | 576 | 120 | 0 | 24.75 | 24.75 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-15 17:00 |  | 2014-02-03 08:00 | 2014-02-20 17:00 | 2014-02-03 08:00 | 2014-02-20 17:00 | 2014-02-03 08:00 | 2014-02-20 17:00 | 2014-04-29 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | RJ5GOROLSge8tyHRNYlvtg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41760 | N | N | 20 | ROOF |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 24.75 | LABOR- SUBCONTRACTOR
%R | 501979 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3040 | Cobble Tile flooring | 8170 | 320 | 0 | 120 | 0 | 68.75 | 68.75 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-20 08:00 | 2014-03-09 17:00 |  | 2014-01-04 08:00 | 2014-01-20 17:00 | 2014-01-04 08:00 | 2014-01-20 17:00 | 2014-01-04 08:00 | 2014-01-20 17:00 | 2014-02-20 08:00 | 2014-03-09 17:00 |  | PT_Normal |  |  |  |  | jNBGetzKTUatBe8ljgeRZQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 68.75 | TILE MASON SK
%R | 501980 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 336 | 16 | 120 | 0 | 45.5 | 45.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-04 17:00 |  | 2013-12-28 08:00 | 2014-01-13 17:00 | 2013-12-28 08:00 | 2014-01-13 17:00 | 2013-12-28 08:00 | 2014-01-13 17:00 | 2014-02-16 08:00 | 2014-03-04 17:00 |  | PT_Normal |  |  |  |  | jTY7idU6S6KABlnhIHvNhQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 45.5 | TILE MASON SK
%R | 501981 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 320 | 0 | 160 | 0 | 506.25 | 506.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-01 08:00 | 2014-03-23 17:00 |  | 2014-01-12 08:00 | 2014-02-03 17:00 | 2014-01-12 08:00 | 2014-02-03 17:00 | 2014-01-12 08:00 | 2014-02-03 17:00 | 2014-03-01 08:00 | 2014-03-23 17:00 |  | PT_Normal |  |  |  |  | 5Nyj0k0AQMKsMnjmyY4rsg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 506.25 | GRANITE MASON SK
%R | 501982 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3045 | Fixing of Suspension systems | 8178 | 280 | 0 | 160 | 0 | 1434.75 | 1434.75 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-04 08:00 | 2014-02-27 17:00 |  | 2013-12-25 08:00 | 2014-01-16 17:00 | 2013-12-25 08:00 | 2014-01-16 17:00 | 2013-12-25 08:00 | 2014-01-16 17:00 | 2014-02-04 08:00 | 2014-02-27 17:00 |  | PT_Normal |  |  |  |  | X7FeHSyTRziJQgOAgoUQ7w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1434.75 | LABOR- SUBCONTRACTOR
%R | 501983 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3055 | Aluminum tile false ceiling | 8178 | 304 | 24 | 200 | 0 | 136.5 | 136.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-17 08:00 | 2014-03-17 17:00 |  | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 |  | PT_Normal |  |  |  |  | 1Wx7+NQTQFS+8CaWfZujcA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 136.5 | LABOR- SUBCONTRACTOR
%R | 501984 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3060 | Gypsum board false ceiling | 8178 | 280 | 0 | 200 | 0 | 1298.71 | 1298.71 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-17 08:00 | 2014-03-17 17:00 |  | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 |  | PT_Normal |  |  |  |  | Jt6DELR9Tce6cvPvoZsCXw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1298.71 | LABOR- SUBCONTRACTOR
%R | 501985 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3065 | Wooden door | 8178 | 320 | 0 | 120 | 0 | 412.5 | 412.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-03-31 17:00 |  | 2014-01-26 08:00 | 2014-02-12 17:00 | 2014-01-26 08:00 | 2014-02-12 17:00 | 2014-01-26 08:00 | 2014-02-12 17:00 | 2014-03-15 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | 0rI5eT4XSpiM82i/1X0Htw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 412.5 | LABOR- SUBCONTRACTOR
%R | 501986 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3070 | Aluminum doors | 8178 | 320 | 0 | 120 | 0 | 99 | 99 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-20 08:00 | 2014-04-06 17:00 |  | 2014-02-01 08:00 | 2014-02-18 17:00 | 2014-02-01 08:00 | 2014-02-18 17:00 | 2014-02-01 08:00 | 2014-02-18 17:00 | 2014-03-20 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | M/nFXHkXRbycQqliOmLTjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 99 | LABOR- SUBCONTRACTOR
%R | 501987 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3080 | Aluminum windows | 8178 | 400 | 40 | 160 | 0 | 220 | 220 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-08 08:00 | 2014-04-30 17:00 |  | 2014-02-08 08:00 | 2014-03-03 17:00 | 2014-02-08 08:00 | 2014-03-03 17:00 | 2014-02-08 08:00 | 2014-03-03 17:00 | 2014-04-08 08:00 | 2014-04-30 17:00 |  | PT_Normal |  |  |  |  | OOiSCfchTMKX3oCvdp8VjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 220 | LABOR- SUBCONTRACTOR
%R | 501988 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3075 | Carpentry & Joinery Works | 8178 | 320 | 0 | 160 | 0 | 792 | 792 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-26 08:00 | 2014-04-17 17:00 |  | 2014-02-06 08:00 | 2014-03-02 17:00 | 2014-02-06 08:00 | 2014-03-02 17:00 | 2014-02-06 08:00 | 2014-03-02 17:00 | 2014-03-26 08:00 | 2014-04-17 17:00 |  | PT_Normal |  |  |  |  | ltvvBTP3TgaFIJJTOB8tVQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 792 | LABOR- SUBCONTRACTOR
%R | 501989 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3090 | Installation of Granite Counter Top | 8171 | 320 | 0 | 120 | 0 | 132 | 132 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-08 08:00 | 2014-04-24 17:00 |  | 2014-02-20 08:00 | 2014-03-09 17:00 | 2014-02-20 08:00 | 2014-03-09 17:00 | 2014-02-20 08:00 | 2014-03-09 17:00 | 2014-04-08 08:00 | 2014-04-24 17:00 |  | PT_Normal |  |  |  |  | OoMuC3i7QpGVlJLlzx53JQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 132 | GRANITE MASON SK
%R | 501990 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3085 | S.S.Balustrade | 8178 | 360 | 40 | 160 | 0 | 47.25 | 47.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-09 08:00 | 2014-05-01 17:00 |  | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-04-09 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | qq0adifVSSq5MF35HaBCRQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 47.25 | LABOR- SUBCONTRACTOR
%R | 501991 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3095 | Final Painting | 8178 | 320 | 0 | 200 | 0 | 4136.55 | 4136.55 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | q5aL8wKfTgKBB9Ga9phyZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 4136.55 | LABOR- SUBCONTRACTOR
%R | 501992 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3000 | Block work | 8168 | 280 | 0 | 200 | 0 | 7112.5 | 7112.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-26 08:00 | 2013-12-25 17:00 |  | 2013-10-14 08:00 | 2013-11-13 17:00 | 2013-10-14 08:00 | 2013-11-13 17:00 | 2013-10-14 08:00 | 2013-11-13 17:00 | 2013-11-26 08:00 | 2013-12-25 17:00 |  | PT_Normal |  |  |  |  | 3AEUDno5R1mCEWGAQd7wqQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 7112.5 | BLOCK MASON SK
%R | 501993 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3005 | Plastering work | 8169 | 280 | 0 | 200 | 0 | 6268.75 | 6268.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-19 08:00 | 2014-01-16 17:00 |  | 2013-11-07 08:00 | 2013-12-05 17:00 | 2013-11-07 08:00 | 2013-12-05 17:00 | 2013-11-07 08:00 | 2013-12-05 17:00 | 2013-12-19 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | XUleVh1hQUm/t9prdUGKzg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 6268.75 | PLASTER MASON SK
%R | 501994 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3010 | Flooring screed | 8164 | 344 | 64 | 168 | 0 | 1234.75 | 1234.75 | 168 | 0 | 0 | 0 |  |  |  | 2014-01-06 08:00 | 2014-01-29 17:00 |  | 2013-11-16 08:00 | 2013-12-09 17:00 | 2013-11-16 08:00 | 2013-12-09 17:00 | 2013-11-16 08:00 | 2013-12-09 17:00 | 2014-01-06 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | WhA36q/yQNqyv3D41WdCMg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1234.75 | SCREED MASON SK
%R | 501995 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 280 | 0 | 120 | 0 | 582 | 582 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-06 08:00 | 2014-01-22 17:00 |  | 2013-11-25 08:00 | 2013-12-11 17:00 | 2013-11-25 08:00 | 2013-12-11 17:00 | 2013-11-25 08:00 | 2013-12-11 17:00 | 2014-01-06 08:00 | 2014-01-22 17:00 |  | PT_Normal |  |  |  |  | FqC9LPZVTWqA239hVdAsCA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 582 | LABOR- SUBCONTRACTOR
%R | 501996 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3030 | Paint First coat | 8178 | 344 | 0 | 200 | 0 | 4136.55 | 4136.55 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-21 08:00 | 2014-02-19 17:00 |  | 2013-12-01 08:00 | 2013-12-30 17:00 | 2013-12-01 08:00 | 2013-12-30 17:00 | 2013-12-01 08:00 | 2013-12-30 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 |  | PT_Normal |  |  |  |  | TcKRCpepRReQMej61zwVag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 4136.55 | LABOR- SUBCONTRACTOR
%R | 501997 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3020 | Ceramic Wall Tiling | 8170 | 280 | 0 | 200 | 0 | 2603.5 | 2603.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-12 08:00 | 2014-02-09 17:00 |  | 2013-12-01 08:00 | 2013-12-30 17:00 | 2013-12-01 08:00 | 2013-12-30 17:00 | 2013-12-01 08:00 | 2013-12-30 17:00 | 2014-01-12 08:00 | 2014-02-09 17:00 |  | PT_Normal |  |  |  |  | G9lFdQBbSOyn6GDMm5dKhA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 2603.5 | TILE MASON SK
%R | 501998 | 6359 | 124799 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARGF3025 | Porcelain Tile flooring | 8170 | 280 | 0 | 200 | 0 | 1787.5 | 1787.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-18 08:00 | 2014-02-16 17:00 |  | 2013-12-07 08:00 | 2014-01-05 17:00 | 2013-12-07 08:00 | 2014-01-05 17:00 | 2013-12-07 08:00 | 2014-01-05 17:00 | 2014-01-18 08:00 | 2014-02-16 17:00 |  | PT_Normal |  |  |  |  | IYUTXsm9TviSjN1kThskXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41740 | N | N | 10 | GROUND FLOOR |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1787.5 | TILE MASON SK
%R | 501999 | 6359 | 124800 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARFF3390 | Installation of Granite Counter Top | 8171 | 0 | 0 | 160 | 0 | 132 | 132 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-08 08:00 | 2014-04-30 17:00 |  | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-04-08 08:00 | 2014-04-30 17:00 |  | PT_Normal |  |  |  |  | uAGnwv57TQm2dT5i31whjw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41750 | N | N | 15 | FIRST FLOORS |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 132 | GRANITE MASON SK
%R | 502000 | 6359 | 124800 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARFF3385 | Handrail & Balustrade | 8178 | 0 | 0 | 160 | 0 | 275 | 275 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-04-28 17:00 |  | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | JogBFQXWSj+480FwNHJ/Rw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41750 | N | N | 15 | FIRST FLOORS |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 275 | LABOR- SUBCONTRACTOR
%R | 502001 | 6359 | 124800 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARFF3395 | Final Painting | 8178 | 0 | 0 | 200 | 0 | 3644.75 | 3644.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | kOxWJt93Q3CLSSODvABE5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41750 | N | N | 15 | FIRST FLOORS |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 3644.75 | LABOR- SUBCONTRACTOR
%R | 502002 | 6359 | 124800 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARFF3300 | Block work | 8168 | 0 | 0 | 200 | 0 | 5553.5 | 5553.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-27 08:00 | 2013-12-26 17:00 |  | 2013-11-27 08:00 | 2013-12-26 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 |  | PT_Normal |  |  |  |  | VTOAkEYAR8iNPf3sA5aXpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41750 | N | N | 15 | FIRST FLOORS |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 5553.5 | BLOCK MASON SK
%R | 502003 | 6359 | 124800 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARFF3305 | Plastering work | 8169 | 0 | 0 | 200 | 0 | 5516 | 5516 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-23 08:00 | 2014-01-20 17:00 |  | 2013-12-23 08:00 | 2014-01-20 17:00 | 2013-12-23 08:00 | 2014-01-20 17:00 | 2013-12-23 08:00 | 2014-01-20 17:00 | 2013-12-23 08:00 | 2014-01-20 17:00 |  | PT_Normal |  |  |  |  | Q5hNMxWBQn6gtHiwE3FWXw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41750 | N | N | 15 | FIRST FLOORS |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 5516 | PLASTER MASON SK
%R | 502004 | 6359 | 124800 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARFF3310 | Flooring screed | 8164 | 120 | 120 | 168 | 0 | 1031.25 | 1031.25 | 168 | 0 | 0 | 0 |  |  |  | 2014-01-18 08:00 | 2014-02-10 17:00 |  | 2013-12-31 08:00 | 2014-01-23 17:00 | 2013-12-31 08:00 | 2014-01-23 17:00 | 2013-12-31 08:00 | 2014-01-23 17:00 | 2014-01-18 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | qeRKTohCSdmY2dClm9yJpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41750 | N | N | 15 | FIRST FLOORS |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1031.25 | SCREED MASON SK
%R | 502005 | 6359 | 124800 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARFF3315 | Wet area waterproofing | 8178 | 0 | 0 | 120 | 0 | 582 | 582 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-01-29 17:00 |  | 2014-01-13 08:00 | 2014-01-29 17:00 | 2014-01-13 08:00 | 2014-01-29 17:00 | 2014-01-13 08:00 | 2014-01-29 17:00 | 2014-01-13 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | BI2amrQTSTaU4WRm7X8s6w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41750 | N | N | 15 | FIRST FLOORS |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 582 | LABOR- SUBCONTRACTOR
%R | 502006 | 6359 | 124800 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARFF3330 | Paint First coat | 8178 | 144 | 144 | 200 | 0 | 3644.75 | 3644.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-29 08:00 | 2014-02-27 17:00 |  | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 |  | PT_Normal |  |  |  |  | 8PbR2ldSQdG6QR1BflBqjA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41750 | N | N | 15 | FIRST FLOORS |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 3644.75 | LABOR- SUBCONTRACTOR
%R | 502007 | 6359 | 124800 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARFF3320 | Ceramic Wall Tiling | 8170 | 0 | 0 | 200 | 0 | 2603.5 | 2603.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-20 17:00 |  | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | NeuvUSnWSH23N8bj7Cg1GQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41750 | N | N | 15 | FIRST FLOORS |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 2603.5 | TILE MASON SK
%R | 502008 | 6359 | 124800 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARFF3325 | Porcelain Tile flooring | 8170 | 0 | 0 | 200 | 0 | 1787.5 | 1787.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-29 08:00 | 2014-02-27 17:00 |  | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 |  | PT_Normal |  |  |  |  | C4dPY6nISmCTExVvW8alMA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41750 | N | N | 15 | FIRST FLOORS |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1787.5 | TILE MASON SK
%R | 502009 | 6359 | 124800 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARFF3335 | Slate Tile Flooring & Skirting | 8178 | 80 | 80 | 120 | 0 | 1350 | 1350 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-01 08:00 | 2014-03-17 17:00 |  | 2014-02-17 08:00 | 2014-03-05 17:00 | 2014-02-17 08:00 | 2014-03-05 17:00 | 2014-02-17 08:00 | 2014-03-05 17:00 | 2014-03-01 08:00 | 2014-03-17 17:00 |  | PT_Normal |  |  |  |  | arscE7haRtC6KLvWDpwbQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41750 | N | N | 15 | FIRST FLOORS |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1350 | LABOR- SUBCONTRACTOR
%R | 502010 | 6359 | 124800 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARFF3350 | Granite - Stair case flooring & Skirting | 8178 | 16 | 16 | 160 | 0 | 150 | 150 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-23 08:00 | 2014-03-17 17:00 |  | 2014-02-20 08:00 | 2014-03-15 17:00 | 2014-02-20 08:00 | 2014-03-15 17:00 | 2014-02-20 08:00 | 2014-03-15 17:00 | 2014-02-23 08:00 | 2014-03-17 17:00 |  | PT_Normal |  |  |  |  | 7LugnVqGRDCGpjLaUBaB9Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41750 | N | N | 15 | FIRST FLOORS |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 150 | LABOR- SUBCONTRACTOR
%R | 502011 | 6359 | 124800 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARFF3345 | Fixing of Suspension systems | 8178 | 0 | 0 | 160 | 0 | 1434.75 | 1434.75 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-03-08 17:00 |  | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | H2sswN6kRVKFJxvzTsMytw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41750 | N | N | 15 | FIRST FLOORS |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1434.75 | LABOR- SUBCONTRACTOR
%R | 502012 | 6359 | 124800 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARFF3355 | Aluminum tile false ceiling | 8178 | 16 | 0 | 160 | 0 | 256.25 | 256.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-27 08:00 | 2014-03-22 17:00 |  | 2014-02-25 08:00 | 2014-03-19 17:00 | 2014-02-25 08:00 | 2014-03-19 17:00 | 2014-02-25 08:00 | 2014-03-19 17:00 | 2014-02-27 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | 5k5yHFi/QjaFJ0NGFeVkCw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41750 | N | N | 15 | FIRST FLOORS |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 256.25 | LABOR- SUBCONTRACTOR
%R | 502013 | 6359 | 124800 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARFF3360 | Gypsum board false ceiling | 8178 | 0 | 0 | 200 | 0 | 1298.71 | 1298.71 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-22 17:00 |  | 2014-02-22 08:00 | 2014-03-22 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | p31rSGqHSVm6jnTJBc1q0A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41750 | N | N | 15 | FIRST FLOORS |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 649.355 | LABOR- SUBCONTRACTOR
%R | 502014 | 6359 | 124800 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARFF3365 | Wooden door | 8178 | 0 | 0 | 120 | 0 | 330 | 330 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-03-25 17:00 |  | 2014-03-09 08:00 | 2014-03-25 17:00 | 2014-03-09 08:00 | 2014-03-25 17:00 | 2014-03-09 08:00 | 2014-03-25 17:00 | 2014-03-09 08:00 | 2014-03-25 17:00 |  | PT_Normal |  |  |  |  | sube1AfGSjOpp7ml90EQ6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41750 | N | N | 15 | FIRST FLOORS |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 330 | LABOR- SUBCONTRACTOR
%R | 502015 | 6359 | 124800 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARFF3370 | Aluminum Door | 8178 | 0 | 0 | 160 | 0 | 99 | 99 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-08 17:00 |  | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | Cgs6IL7VRSGIZ7PZk42ArQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41750 | N | N | 15 | FIRST FLOORS |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 99 | LABOR- SUBCONTRACTOR
%R | 502016 | 6359 | 124800 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARFF3380 | Aluminum windows | 8178 | 88 | 88 | 160 | 0 | 264 | 264 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-04-28 17:00 |  | 2014-03-24 08:00 | 2014-04-15 17:00 | 2014-03-24 08:00 | 2014-04-15 17:00 | 2014-03-24 08:00 | 2014-04-15 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | an0Kst8nR1KSZXPwYtPLpQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41750 | N | N | 15 | FIRST FLOORS |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 264 | LABOR- SUBCONTRACTOR
%R | 502017 | 6359 | 124800 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARFF3375 | Carpentry & Joinery Works | 8178 | 0 | 0 | 200 | 0 | 300 | 300 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-25 08:00 | 2014-04-22 17:00 |  | 2014-03-25 08:00 | 2014-04-22 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | qhwFmXN4SwytxTZoi6howQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41750 | N | N | 15 | FIRST FLOORS |  | 124797 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 300 | LABOR- SUBCONTRACTOR
%R | 502018 | 6359 | 124802 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3AREL3665 | External Plastering | 8169 | 424 | 0 | 200 | 0 | 9159.75 | 9159.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-23 08:00 | 2014-04-20 17:00 |  | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | FMjr4+MUS9abIpdgv+D+fw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41790 | N | N | 15 | ELEVATION |  | 124801 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 9159.75 | PLASTER MASON SK
%R | 502019 | 6359 | 124802 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3AREL3675 | GRC Panel Works | 8178 | 440 | 16 | 160 | 0 | 550 | 550 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-04 17:00 |  | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | diPj2P7OQ/aqBsz2HJmE5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41790 | N | N | 15 | ELEVATION |  | 124801 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 550 | LABOR- SUBCONTRACTOR
%R | 502020 | 6359 | 124802 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3AREL3680 | External Painting | 8178 | 424 | 24 | 160 | 0 | 3234 | 3234 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-05-15 17:00 |  | 2014-02-20 08:00 | 2014-03-15 17:00 | 2014-02-20 08:00 | 2014-03-15 17:00 | 2014-02-20 08:00 | 2014-03-15 17:00 | 2014-04-23 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | 2cTCVg8ZTgiNOKvS7LytNg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41790 | N | N | 15 | ELEVATION |  | 124801 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 3234 | LABOR- SUBCONTRACTOR
%R | 502021 | 6359 | 124803 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARRF3630 | Leveling Screed for Waterproofing | 8164 | 496 | 0 | 200 | 0 | 734.75 | 734.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-06 08:00 | 2014-04-03 17:00 |  | 2013-12-23 08:00 | 2014-01-20 17:00 | 2013-12-23 08:00 | 2014-01-20 17:00 | 2013-12-23 08:00 | 2014-01-20 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 |  | PT_Normal |  |  |  |  | VWNEb44jTnuN4uACefX1kA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41780 | N | N | 10 | ROOF |  | 124801 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 734.75 | SCREED MASON SK
%R | 502022 | 6359 | 124803 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARRF3635 | Laying of Waterproofing Membrane | 8178 | 496 | 0 | 200 | 0 | 2042.25 | 2042.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-10 08:00 | 2014-04-07 17:00 |  | 2013-12-26 08:00 | 2014-01-23 17:00 | 2013-12-26 08:00 | 2014-01-23 17:00 | 2013-12-26 08:00 | 2014-01-23 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 |  | PT_Normal |  |  |  |  | 1nFz+De5Q+aYnyyVjztOmQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41780 | N | N | 10 | ROOF |  | 124801 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 2042.25 | LABOR- SUBCONTRACTOR
%R | 502023 | 6359 | 124803 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARRF3640 | Installation of Insulation & Protection | 8178 | 496 | 0 | 200 | 0 | 1291.5 | 1291.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-12 17:00 |  | 2013-12-31 08:00 | 2014-01-28 17:00 | 2013-12-31 08:00 | 2014-01-28 17:00 | 2013-12-31 08:00 | 2014-01-28 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 |  | PT_Normal |  |  |  |  | IYR5xDfLTb+bxWOtkFdDNQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41780 | N | N | 10 | ROOF |  | 124801 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1291.5 | LABOR- SUBCONTRACTOR
%R | 502024 | 6359 | 124803 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 496 | 0 | 200 | 0 | 741.5 | 741.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | 0+9/3mT0RYWiGdxcK8RbtA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41780 | N | N | 10 | ROOF |  | 124801 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 741.5 | TILE MASON SK
%R | 502025 | 6359 | 124803 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 496 | 0 | 160 | 0 | 231 | 231 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-04 17:00 |  | 2014-01-28 08:00 | 2014-02-20 17:00 | 2014-01-28 08:00 | 2014-02-20 17:00 | 2014-01-28 08:00 | 2014-02-20 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | w68FUA2pRZC4ymG0YjPt9g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41780 | N | N | 10 | ROOF |  | 124801 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 231 | LABOR- SUBCONTRACTOR
%R | 502026 | 6359 | 124803 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 496 | 0 | 200 | 0 | 882 | 882 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-27 08:00 | 2014-04-24 17:00 |  | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 |  | PT_Normal |  |  |  |  | V02un8gySYu298cXerDDPw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41780 | N | N | 10 | ROOF |  | 124801 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 882 | LABOR- SUBCONTRACTOR
%R | 502027 | 6359 | 124803 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ARRF3660 | Installation of Access Ladder | 8178 | 536 | 536 | 120 | 0 | 198 | 198 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-15 17:00 |  | 2014-02-09 08:00 | 2014-02-26 17:00 | 2014-02-09 08:00 | 2014-02-26 17:00 | 2014-02-09 08:00 | 2014-02-26 17:00 | 2014-04-29 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | StkchXZnRt+F5v/E8T3+zw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41780 | N | N | 10 | ROOF |  | 124801 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 198 | LABOR- SUBCONTRACTOR
%R | 502028 | 6359 | 124804 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 0 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | edOuXHX1SiSsKO82K3NV+A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41990 | N | N | 30 | TESTING AND COMMISSIONING |  | 124795 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 502029 | 6359 | 124804 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | y94rE3qVR3mVXE6Z8MDgYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41990 | N | N | 30 | TESTING AND COMMISSIONING |  | 124795 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 502030 | 6359 | 124804 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | VN94tUdQSwu6OH13nW/52g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41990 | N | N | 30 | TESTING AND COMMISSIONING |  | 124795 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 502031 | 6359 | 124807 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STFF2020 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 1615.25 | 1615.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-15 08:00 | 2013-10-13 17:00 |  | 2013-09-15 08:00 | 2013-10-13 17:00 | 2013-09-15 08:00 | 2013-10-13 17:00 | 2013-09-15 08:00 | 2013-10-13 17:00 | 2013-09-15 08:00 | 2013-10-13 17:00 |  | PT_Normal |  |  |  |  | oMbV5HyJS8qTYOJ8UkjHfg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41700 | N | N | 15 | FIRST FLOORS |  | 124806 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1615.25 | STEEL FIXERS SK
%R | 502032 | 6359 | 124807 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STFF2025 | Column-Concrete | 8167 | 0 | 0 | 192 | 0 | 87.5 | 87.5 | 192 | 0 | 0 | 0 |  |  |  | 2013-09-25 08:00 | 2013-10-24 17:00 |  | 2013-09-25 08:00 | 2013-10-24 17:00 | 2013-09-25 08:00 | 2013-10-24 17:00 | 2013-09-25 08:00 | 2013-10-24 17:00 | 2013-09-25 08:00 | 2013-10-24 17:00 |  | PT_Normal |  |  |  |  | ok5rY/JGRdSYUqKEj4YwUQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41700 | N | N | 15 | FIRST FLOORS |  | 124806 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 87.5 | CONCRETE MASON SK
%R | 502033 | 6359 | 124807 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 10081.75 | 10081.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2013-11-10 17:00 |  | 2013-10-10 08:00 | 2013-11-10 17:00 | 2013-10-10 08:00 | 2013-11-10 17:00 | 2013-10-10 08:00 | 2013-11-10 17:00 | 2013-10-10 08:00 | 2013-11-10 17:00 |  | PT_Normal |  |  |  |  | kOne+9T+TcSOeMc/qSHFPA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41700 | N | N | 15 | FIRST FLOORS |  | 124806 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 5040.875 | STEEL FIXERS SK
%R | 502034 | 6359 | 124807 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 0 | 0 | 120 | 0 | 731.5 | 731.5 | 120 | 0 | 0 | 0 |  |  |  | 2013-11-03 08:00 | 2013-11-19 17:00 |  | 2013-11-03 08:00 | 2013-11-19 17:00 | 2013-11-03 08:00 | 2013-11-19 17:00 | 2013-11-03 08:00 | 2013-11-19 17:00 | 2013-11-03 08:00 | 2013-11-19 17:00 |  | PT_Normal |  |  |  |  | rYCcBjIVTBKgv0X2ZH9ZOQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41700 | N | N | 15 | FIRST FLOORS |  | 124806 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 731.5 | CONCRETE MASON SK
%R | 502035 | 6359 | 124808 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STGF2000 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 1688.75 | 1688.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-31 08:00 | 2013-09-01 17:00 |  | 2013-07-31 08:00 | 2013-09-01 17:00 | 2013-07-31 08:00 | 2013-09-01 17:00 | 2013-07-31 08:00 | 2013-09-01 17:00 | 2013-07-31 08:00 | 2013-09-01 17:00 |  | PT_Normal |  |  |  |  | 9Hek/NY1QNe+rY1QP7FzPA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41690 | N | N | 10 | GROUND FLOOR |  | 124806 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 844.375 | STEEL FIXERS SK
%R | 502036 | 6359 | 124808 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STGF2005 | Column-Concrete | 8167 | 0 | 0 | 192 | 0 | 101.5 | 101.5 | 192 | 0 | 0 | 0 |  |  |  | 2013-08-13 08:00 | 2013-09-09 17:00 |  | 2013-08-13 08:00 | 2013-09-09 17:00 | 2013-08-13 08:00 | 2013-09-09 17:00 | 2013-08-13 08:00 | 2013-09-09 17:00 | 2013-08-13 08:00 | 2013-09-09 17:00 |  | PT_Normal |  |  |  |  | K8M0FcU9SB22gHCs/hJccw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41690 | N | N | 10 | GROUND FLOOR |  | 124806 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 101.5 | CONCRETE MASON SK
%R | 502037 | 6359 | 124808 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 10592.75 | 10592.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-28 08:00 | 2013-09-25 17:00 |  | 2013-08-28 08:00 | 2013-09-25 17:00 | 2013-08-28 08:00 | 2013-09-25 17:00 | 2013-08-28 08:00 | 2013-09-25 17:00 | 2013-08-28 08:00 | 2013-09-25 17:00 |  | PT_Normal |  |  |  |  | fi6bCIiaSQCHbQLj2juYXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41690 | N | N | 10 | GROUND FLOOR |  | 124806 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 10592.75 | STEEL FIXERS SK
%R | 502038 | 6359 | 124808 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 0 | 0 | 120 | 0 | 868 | 868 | 120 | 0 | 0 | 0 |  |  |  | 2013-09-12 08:00 | 2013-09-29 17:00 |  | 2013-09-12 08:00 | 2013-09-29 17:00 | 2013-09-12 08:00 | 2013-09-29 17:00 | 2013-09-12 08:00 | 2013-09-29 17:00 | 2013-09-12 08:00 | 2013-09-29 17:00 |  | PT_Normal |  |  |  |  | fbPR2oBkQlKHU70HK8/g8w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41690 | N | N | 10 | GROUND FLOOR |  | 124806 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 868 | CONCRETE MASON SK
%R | 502039 | 6359 | 124809 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STRF2040 | Column-Rebar & Formwork | 8165 | 232 | 0 | 144 | 0 | 549.5 | 549.5 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-09 08:00 | 2013-12-30 17:00 |  | 2013-11-05 08:00 | 2013-11-25 17:00 | 2013-11-05 08:00 | 2013-11-25 17:00 | 2013-11-05 08:00 | 2013-11-25 17:00 | 2013-12-09 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | vYsMwSpqTru2HQUlUsCeOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41710 | N | N | 20 | ROOF |  | 124806 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 549.5 | STEEL FIXERS SK
%R | 502040 | 6359 | 124809 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STRF2045 | Column-Concrete | 8167 | 312 | 0 | 136 | 0 | 21 | 21 | 136 | 0 | 0 | 0 |  |  |  | 2013-12-25 08:00 | 2014-01-13 17:00 |  | 2013-11-09 08:00 | 2013-11-27 17:00 | 2013-11-09 08:00 | 2013-11-27 17:00 | 2013-11-09 08:00 | 2013-11-27 17:00 | 2013-12-25 08:00 | 2014-01-13 17:00 |  | PT_Normal |  |  |  |  | b6VTIUECQROvgbj7k7n92w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41710 | N | N | 20 | ROOF |  | 124806 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 21 | CONCRETE MASON SK
%R | 502041 | 6359 | 124809 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STRF2050 | Slab-Rebar & Formwork | 8165 | 312 | 0 | 160 | 0 | 1576.75 | 1576.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-28 08:00 | 2014-01-19 17:00 |  | 2013-11-11 08:00 | 2013-12-03 17:00 | 2013-11-11 08:00 | 2013-12-03 17:00 | 2013-11-11 08:00 | 2013-12-03 17:00 | 2013-12-28 08:00 | 2014-01-19 17:00 |  | PT_Normal |  |  |  |  | gxX9PjPMRmumqhUVIVfuUg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41710 | N | N | 20 | ROOF |  | 124806 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1576.75 | STEEL FIXERS SK
%R | 502042 | 6359 | 124809 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STRF2055 | Slab-Concrete | 8167 | 312 | 0 | 104 | 0 | 175 | 175 | 104 | 0 | 0 | 0 |  |  |  | 2014-01-07 08:00 | 2014-01-21 17:00 |  | 2013-11-21 08:00 | 2013-12-05 17:00 | 2013-11-21 08:00 | 2013-12-05 17:00 | 2013-11-21 08:00 | 2013-12-05 17:00 | 2014-01-07 08:00 | 2014-01-21 17:00 |  | PT_Normal |  |  |  |  | G5CZ6WFBQzO/rphidPqB8A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41710 | N | N | 20 | ROOF |  | 124806 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 175 | CONCRETE MASON SK
%R | 502043 | 6359 | 124809 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STRF2060 | Construction of Parapets | 8168 | 464 | 0 | 200 | 0 | 1441 | 1441 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-01 08:00 | 2014-03-02 17:00 |  | 2013-11-24 08:00 | 2013-12-23 17:00 | 2013-11-24 08:00 | 2013-12-23 17:00 | 2013-11-24 08:00 | 2013-12-23 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 |  | PT_Normal |  |  |  |  | TdLX3Oe4Sp2P5eZPxE4XbQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41710 | N | N | 20 | ROOF |  | 124806 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1441 | BLOCK MASON SK
%R | 502044 | 6359 | 124809 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STRF2065 | Construction of up stands/Plinth | 8165 | 464 | 0 | 200 | 0 | 283.5 | 283.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-03-08 17:00 |  | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | zLk4Tja5SYmtOdq04C5z1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41710 | N | N | 20 | ROOF |  | 124806 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 283.5 | STEEL FIXERS SK
%R | 502045 | 6359 | 124811 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STUG1010 | Footing Blinding | 8163 | 0 | 0 | 184 | 0 | 588 | 588 | 184 | 0 | 0 | 0 |  |  |  | 2013-04-13 08:00 | 2013-05-08 17:00 |  | 2013-04-13 08:00 | 2013-05-08 17:00 | 2013-04-13 08:00 | 2013-05-08 17:00 | 2013-04-13 08:00 | 2013-05-08 17:00 | 2013-04-13 08:00 | 2013-05-08 17:00 |  | PT_Normal |  |  |  |  | YyN5yDMwSTmAKhOLWxt3zw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41670 | N | N | 10 | UPTO GRADE SLAB |  | 124810 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 588 | BLINDING MASON SK
%R | 502046 | 6359 | 124811 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STUG1015 | Footing Waterproofing & Screed | 8164 | 0 | 0 | 200 | 0 | 1368.5 | 1368.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-04-18 08:00 | 2013-05-16 17:00 |  | 2013-04-18 08:00 | 2013-05-16 17:00 | 2013-04-18 08:00 | 2013-05-16 17:00 | 2013-04-18 08:00 | 2013-05-16 17:00 | 2013-04-18 08:00 | 2013-05-16 17:00 |  | PT_Normal |  |  |  |  | 0BaBbRLxSf+2kRkhOGfVkQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41670 | N | N | 10 | UPTO GRADE SLAB |  | 124810 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 1368.5 | SCREED MASON SK
%R | 502047 | 6359 | 124811 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STUG1020 | Construction of foundations | 8165 | 0 | 0 | 160 | 0 | 4817.75 | 4817.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-05-04 08:00 | 2013-05-26 17:00 |  | 2013-05-04 08:00 | 2013-05-26 17:00 | 2013-05-04 08:00 | 2013-05-26 17:00 | 2013-05-04 08:00 | 2013-05-26 17:00 | 2013-05-04 08:00 | 2013-05-26 17:00 |  | PT_Normal |  |  |  |  | ExFfV4gBQXuTb8yURXcn1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41670 | N | N | 10 | UPTO GRADE SLAB |  | 124810 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 4817.75 | STEEL FIXERS SK
%R | 502048 | 6359 | 124811 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STUG1025 | Construction of neck of columns | 8165 | 0 | 0 | 200 | 0 | 1400 | 1400 | 200 | 0 | 0 | 0 |  |  |  | 2013-05-13 08:00 | 2013-06-10 17:00 |  | 2013-05-13 08:00 | 2013-06-10 17:00 | 2013-05-13 08:00 | 2013-06-10 17:00 | 2013-05-13 08:00 | 2013-06-10 17:00 | 2013-05-13 08:00 | 2013-06-10 17:00 |  | PT_Normal |  |  |  |  | UaE2fDIWR1ubMmR+JML+Ow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41670 | N | N | 10 | UPTO GRADE SLAB |  | 124810 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 1400 | STEEL FIXERS SK
%R | 502049 | 6359 | 124811 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STUG1030 | Waterproofing Footing & Neck Column | 8178 | 0 | 0 | 200 | 0 | 213.5 | 213.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-05-22 08:00 | 2013-06-19 17:00 |  | 2013-05-22 08:00 | 2013-06-19 17:00 | 2013-05-22 08:00 | 2013-06-19 17:00 | 2013-05-22 08:00 | 2013-06-19 17:00 | 2013-05-22 08:00 | 2013-06-19 17:00 |  | PT_Normal |  |  |  |  | LEV7DHGSQy6xYBxGXeNnhg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41670 | N | N | 10 | UPTO GRADE SLAB |  | 124810 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 213.5 | LABOR- SUBCONTRACTOR
%R | 502050 | 6359 | 124811 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 0 | 0 | 200 | 0 | 2560 | 2560 | 200 | 2200 | 0 | 2200 |  |  |  | 2013-06-02 08:00 | 2013-06-30 17:00 |  | 2013-06-02 08:00 | 2013-06-30 17:00 | 2013-06-02 08:00 | 2013-06-30 17:00 | 2013-06-02 08:00 | 2013-06-30 17:00 | 2013-06-02 08:00 | 2013-06-30 17:00 |  | PT_Normal |  |  |  |  | WqHXbkVjQfir8eRF7ryAMA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41670 | N | N | 10 | UPTO GRADE SLAB |  | 124810 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 2560 | LABOR - CIVIL
%R | 502051 | 6359 | 124811 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STUG1040 | Construction of Grade Beams | 8163 | 0 | 0 | 200 | 0 | 4745 | 4745 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-18 08:00 | 2013-07-16 17:00 |  | 2013-06-18 08:00 | 2013-07-16 17:00 | 2013-06-18 08:00 | 2013-07-16 17:00 | 2013-06-18 08:00 | 2013-07-16 17:00 | 2013-06-18 08:00 | 2013-07-16 17:00 |  | PT_Normal |  |  |  |  | KkV2dw5eRc+sDdrxCJFn4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41670 | N | N | 10 | UPTO GRADE SLAB |  | 124810 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 4745 | BLINDING MASON SK
%R | 502052 | 6359 | 124811 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STUG1045 | Construction of slab on grade | 8163 | 0 | 0 | 200 | 0 | 3327.5 | 3327.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-15 08:00 | 2013-08-15 17:00 |  | 2013-07-15 08:00 | 2013-08-15 17:00 | 2013-07-15 08:00 | 2013-08-15 17:00 | 2013-07-15 08:00 | 2013-08-15 17:00 | 2013-07-15 08:00 | 2013-08-15 17:00 |  | PT_Normal |  |  |  |  | ocC2AVhiSxO0lAmqDnZe2A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41670 | N | N | 10 | UPTO GRADE SLAB |  | 124810 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 1663.75 | BLINDING MASON SK
%R | 502053 | 6359 | 124811 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STUG1000 | Footing Excavation | 8177 | 0 | 0 | 200 | 0 | 1556 | 1556 | 200 | 732 | 0 | 732 |  |  |  | 2013-03-30 08:00 | 2013-04-27 17:00 |  | 2013-03-30 08:00 | 2013-04-27 17:00 | 2013-03-30 08:00 | 2013-04-27 17:00 | 2013-03-30 08:00 | 2013-04-27 17:00 | 2013-03-30 08:00 | 2013-04-27 17:00 |  | PT_Normal |  |  |  |  | NKQNG+q7Sumeu2v7pwrfjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41670 | N | N | 10 | UPTO GRADE SLAB |  | 124810 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 1556 | LABOR - CIVIL
%R | 502054 | 6359 | 124811 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3STUG1005 | Footing Antitermite | 8178 | 0 | 0 | 184 | 0 | 634.25 | 634.25 | 184 | 0 | 0 | 0 |  |  |  | 2013-04-09 08:00 | 2013-05-05 17:00 |  | 2013-04-09 08:00 | 2013-05-05 17:00 | 2013-04-09 08:00 | 2013-05-05 17:00 | 2013-04-09 08:00 | 2013-05-05 17:00 | 2013-04-09 08:00 | 2013-05-05 17:00 |  | PT_Normal |  |  |  |  | bF7XsTaaRVO4zqr8ToINzA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41670 | N | N | 10 | UPTO GRADE SLAB |  | 124810 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 634.25 | LABOR- SUBCONTRACTOR
%R | 502055 | 6359 | 124814 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 280 | 0 | 144 | 0 | 2732.4 | 2732.4 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-12 08:00 | 2014-01-02 17:00 |  | 2013-11-02 08:00 | 2013-11-21 17:00 | 2013-11-02 08:00 | 2013-11-21 17:00 | 2013-11-02 08:00 | 2013-11-21 17:00 | 2013-12-12 08:00 | 2014-01-02 17:00 |  | PT_Normal |  |  |  |  | g1ZUmgTHT12O/uRaD7DgMQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41860 | N | N | 10 | GROUND FLOOR |  | 124813 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 2732.4 | LABOR- SUBCONTRACTOR
%R | 502056 | 6359 | 124814 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3PLGF4310 | Installation of Drainage pipes &testing | 8178 | 448 | 136 | 144 | 0 | 216 | 216 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-07 08:00 | 2014-01-27 17:00 |  | 2013-11-02 08:00 | 2013-11-21 17:00 | 2013-11-02 08:00 | 2013-11-21 17:00 | 2013-11-02 08:00 | 2013-11-21 17:00 | 2014-01-07 08:00 | 2014-01-27 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41860 | N | N | 10 | GROUND FLOOR |  | 124813 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 216 | LABOR- SUBCONTRACTOR
%R | 502057 | 6359 | 124814 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3PLGF4315 | Sanitary Fittings & Accessories | 8178 | 512 | 0 | 160 | 0 | 352.8 | 352.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-10 17:00 |  | 2014-02-01 08:00 | 2014-02-24 17:00 | 2014-02-01 08:00 | 2014-02-24 17:00 | 2014-02-01 08:00 | 2014-02-24 17:00 | 2014-04-17 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | t7lOiFLvSTq7iiJYPJlqlA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41860 | N | N | 10 | GROUND FLOOR |  | 124813 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 352.8 | LABOR- SUBCONTRACTOR
%R | 502058 | 6359 | 124814 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3PLGF4320 | Installation of Water Heater | 8178 | 512 | 80 | 120 | 0 | 50.4 | 50.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-15 17:00 |  | 2014-02-13 08:00 | 2014-03-02 17:00 | 2014-02-13 08:00 | 2014-03-02 17:00 | 2014-02-13 08:00 | 2014-03-02 17:00 | 2014-04-29 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | iFdrPKHwSxaN18rqgCm4mg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41860 | N | N | 10 | GROUND FLOOR |  | 124813 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 502059 | 6359 | 124814 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 0 | 0 | 160 | 0 | 165.6 | 165.6 | 160 | 0 | 0 | 0 |  |  |  | 2013-07-06 08:00 | 2013-07-28 17:00 |  | 2013-07-06 08:00 | 2013-07-28 17:00 | 2013-07-06 08:00 | 2013-07-28 17:00 | 2013-07-06 08:00 | 2013-07-28 17:00 | 2013-07-06 08:00 | 2013-07-28 17:00 |  | PT_Normal |  |  |  |  | Mz607KtDSsmzw+jD0t0IAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41860 | N | N | 10 | GROUND FLOOR |  | 124813 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 165.6 | LABOR- SUBCONTRACTOR
%R | 502060 | 6359 | 124815 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3PLFF4330 | Installation of Drainage pipes & testing | 8178 | 208 | 56 | 144 | 0 | 216 | 216 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-02-03 17:00 |  | 2013-12-14 08:00 | 2014-01-04 17:00 | 2013-12-14 08:00 | 2014-01-04 17:00 | 2013-12-14 08:00 | 2014-01-04 17:00 | 2014-01-14 08:00 | 2014-02-03 17:00 |  | PT_Normal |  |  |  |  | CBsd7tXMS2icpUBIyp4f1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41870 | N | N | 15 | FIRST FLOORS |  | 124813 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 216 | LABOR- SUBCONTRACTOR
%R | 502061 | 6359 | 124815 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3PLFF4335 | Sanitary Fittings & Accessories | 8178 | 112 | 0 | 160 | 0 | 352.8 | 352.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-22 17:00 |  | 2014-03-15 08:00 | 2014-04-06 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | +zV8y/x4RZifs+9Dchh2EA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41870 | N | N | 15 | FIRST FLOORS |  | 124813 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 352.8 | LABOR- SUBCONTRACTOR
%R | 502062 | 6359 | 124815 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3PLFF4340 | Installation of Water Heater | 8178 | 112 | 0 | 120 | 0 | 50.4 | 50.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-04-28 17:00 |  | 2014-03-26 08:00 | 2014-04-12 17:00 | 2014-03-26 08:00 | 2014-04-12 17:00 | 2014-03-26 08:00 | 2014-04-12 17:00 | 2014-04-12 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | nz1wxdooQwydeqdeVZIPwg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41870 | N | N | 15 | FIRST FLOORS |  | 124813 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 502063 | 6359 | 124815 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 0 | 0 | 144 | 0 | 2732.4 | 2732.4 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-12 08:00 | 2014-01-02 17:00 |  | 2013-12-12 08:00 | 2014-01-02 17:00 | 2013-12-12 08:00 | 2014-01-02 17:00 | 2013-12-12 08:00 | 2014-01-02 17:00 | 2013-12-12 08:00 | 2014-01-02 17:00 |  | PT_Normal |  |  |  |  | 2/vzwivpTPWUv1ZI5BndRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41870 | N | N | 15 | FIRST FLOORS |  | 124813 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 2732.4 | LABOR- SUBCONTRACTOR
%R | 502064 | 6359 | 124816 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 568 | 144 | 120 | 0 | 1623.6 | 1623.6 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-02 08:00 | 2014-04-19 17:00 |  | 2014-01-08 08:00 | 2014-01-25 17:00 | 2014-01-08 08:00 | 2014-01-25 17:00 | 2014-01-08 08:00 | 2014-01-25 17:00 | 2014-04-02 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | DyCjZodLTU6smuIDJRe+5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41880 | N | N | 20 | ROOF |  | 124813 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1623.6 | LABOR- SUBCONTRACTOR
%R | 502065 | 6359 | 124816 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3PLRF4350 | Installation of Rain water Pipes | 8178 | 424 | 80 | 120 | 0 | 82.8 | 82.8 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-04-28 17:00 |  | 2014-02-08 08:00 | 2014-02-25 17:00 | 2014-02-08 08:00 | 2014-02-25 17:00 | 2014-02-08 08:00 | 2014-02-25 17:00 | 2014-04-12 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | OZW2fcF/S/GoM8FbUYLJqw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41880 | N | N | 20 | ROOF |  | 124813 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 82.8 | LABOR- SUBCONTRACTOR
%R | 502066 | 6359 | 124816 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 112 | 0 | 200 | 0 | 100.8 | 100.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | KkxvBI0mQ4KARxwqMWZ1xw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41880 | N | N | 20 | ROOF |  | 124813 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 100.8 | LABOR- SUBCONTRACTOR
%R | 502067 | 6359 | 124818 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 88 | 0 | 200 | 0 | 1102.8 | 1102.8 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-16 08:00 | 2014-01-14 17:00 |  | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-16 08:00 | 2014-01-14 17:00 |  | PT_Normal |  |  |  |  | P20e41sMRRyeM8Tg70lTsw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41830 | N | N | 15 | FIRST FLOORS |  | 124817 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1102.8 | LABOR- SUBCONTRACTOR
%R | 502068 | 6359 | 124818 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ELFF4040 | Cable tray & trunking installation | 8178 | 264 | 24 | 160 | 0 | 1840.8 | 1840.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-23 08:00 | 2014-02-16 17:00 |  | 2013-12-15 08:00 | 2014-01-07 17:00 | 2013-12-15 08:00 | 2014-01-07 17:00 | 2013-12-15 08:00 | 2014-01-07 17:00 | 2014-01-23 08:00 | 2014-02-16 17:00 |  | PT_Normal |  |  |  |  | K/AtAhhHR9GLI8alQ9B4Rg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41830 | N | N | 15 | FIRST FLOORS |  | 124817 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1840.8 | LABOR- SUBCONTRACTOR
%R | 502069 | 6359 | 124818 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ELFF4045 | Installation of wiring & Main Cabling | 8178 | 240 | 0 | 200 | 0 | 648 | 648 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-01 08:00 | 2014-03-02 17:00 |  | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 |  | PT_Normal |  |  |  |  | YZuzoXOSQ66Dc0QNYqFaHA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41830 | N | N | 15 | FIRST FLOORS |  | 124817 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 648 | LABOR- SUBCONTRACTOR
%R | 502070 | 6359 | 124818 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 8 | 0 | 160 | 0 | 188.4 | 188.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-10 08:00 | 2014-04-01 17:00 |  | 2014-03-09 08:00 | 2014-03-31 17:00 | 2014-03-09 08:00 | 2014-03-31 17:00 | 2014-03-09 08:00 | 2014-03-31 17:00 | 2014-03-10 08:00 | 2014-04-01 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41830 | N | N | 15 | FIRST FLOORS |  | 124817 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 188.4 | LABOR- SUBCONTRACTOR
%R | 502071 | 6359 | 124818 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 8 | 0 | 200 | 0 | 2528.4 | 2528.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-23 08:00 | 2014-04-20 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | oDp+JSTCROeuBUnLhI3u/w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41830 | N | N | 15 | FIRST FLOORS |  | 124817 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 2528.4 | LABOR- SUBCONTRACTOR
%R | 502072 | 6359 | 124818 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 96 | 0 | 200 | 0 | 1612.8 | 1612.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | 20Bb04CHSs6vxv0NcGFGMg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41830 | N | N | 15 | FIRST FLOORS |  | 124817 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1612.8 | LABOR- SUBCONTRACTOR
%R | 502073 | 6359 | 124818 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ELFF4050 | Installation of Telephone System | 8178 | 160 | 152 | 200 | 0 | 542.4 | 542.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-26 08:00 | 2014-04-23 17:00 |  | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 |  | PT_Normal |  |  |  |  | kDDCs2fTT2e7W/aO0CACew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41830 | N | N | 15 | FIRST FLOORS |  | 124817 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 542.4 | LABOR- SUBCONTRACTOR
%R | 502074 | 6359 | 124819 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ELRF4070 | Installation of Isolator | 8178 | 8 | 0 | 144 | 0 | 309.6 | 309.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-01 17:00 |  | 2014-04-10 08:00 | 2014-04-30 17:00 | 2014-04-10 08:00 | 2014-04-30 17:00 | 2014-04-10 08:00 | 2014-04-30 17:00 | 2014-04-12 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | Kcin0xcZTySDUjRfpHCO5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41840 | N | N | 20 | ROOF |  | 124817 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 309.6 | LABOR- SUBCONTRACTOR
%R | 502075 | 6359 | 124819 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ELRF4075 | Installation of TV Dish Antenna | 8178 | 8 | 8 | 184 | 0 | 4725.6 | 4725.6 | 184 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-15 17:00 |  | 2014-04-19 08:00 | 2014-05-14 17:00 | 2014-04-19 08:00 | 2014-05-14 17:00 | 2014-04-19 08:00 | 2014-05-14 17:00 | 2014-04-20 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | bQxQgnmYStSBV3NfmfasPw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41840 | N | N | 20 | ROOF |  | 124817 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 4725.6 | LABOR- SUBCONTRACTOR
%R | 502076 | 6359 | 124820 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 352 | 0 | 200 | 0 | 1102.8 | 1102.8 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-12 08:00 | 2014-01-11 17:00 |  | 2013-10-22 08:00 | 2013-11-19 17:00 | 2013-10-22 08:00 | 2013-11-19 17:00 | 2013-10-22 08:00 | 2013-11-19 17:00 | 2013-12-12 08:00 | 2014-01-11 17:00 |  | PT_Normal |  |  |  |  | 66+Ny2tnT6mgSeYHdwwcAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41820 | N | N | 10 | GROUND FLOOR |  | 124817 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1102.8 | LABOR- SUBCONTRACTOR
%R | 502077 | 6359 | 124820 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ELGF4005 | Cable tray & trunking installation | 8178 | 496 | 0 | 160 | 0 | 1840.8 | 1840.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-15 08:00 | 2014-02-06 17:00 |  | 2013-11-03 08:00 | 2013-11-25 17:00 | 2013-11-03 08:00 | 2013-11-25 17:00 | 2013-11-03 08:00 | 2013-11-25 17:00 | 2014-01-15 08:00 | 2014-02-06 17:00 |  | PT_Normal |  |  |  |  | gN/kjsqaT42KPH9vJU00nA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41820 | N | N | 10 | GROUND FLOOR |  | 124817 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1840.8 | LABOR- SUBCONTRACTOR
%R | 502078 | 6359 | 124820 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ELGF4010 | Installation of wiring & Main Cabling | 8178 | 496 | 216 | 200 | 0 | 648 | 648 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-23 08:00 | 2014-02-22 17:00 |  | 2013-11-11 08:00 | 2013-12-09 17:00 | 2013-11-11 08:00 | 2013-12-09 17:00 | 2013-11-11 08:00 | 2013-12-09 17:00 | 2014-01-23 08:00 | 2014-02-22 17:00 |  | PT_Normal |  |  |  |  | ZWh6oRTqRriYLzc3V7QU2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41820 | N | N | 10 | GROUND FLOOR |  | 124817 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 648 | LABOR- SUBCONTRACTOR
%R | 502079 | 6359 | 124820 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 280 | 0 | 160 | 0 | 222 | 222 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-03 08:00 | 2014-03-25 17:00 |  | 2014-01-20 08:00 | 2014-02-12 17:00 | 2014-01-20 08:00 | 2014-02-12 17:00 | 2014-01-20 08:00 | 2014-02-12 17:00 | 2014-03-03 08:00 | 2014-03-25 17:00 |  | PT_Normal |  |  |  |  | pTb6ja+tQaGlqB3q3/2PCA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41820 | N | N | 10 | GROUND FLOOR |  | 124817 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 222 | LABOR- SUBCONTRACTOR
%R | 502080 | 6359 | 124820 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 296 | 0 | 200 | 0 | 2580 | 2580 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-14 17:00 |  | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 |  | PT_Normal |  |  |  |  | wFXksu1GQue3fbxcnQ8kcw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41820 | N | N | 10 | GROUND FLOOR |  | 124817 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 1290 | LABOR- SUBCONTRACTOR
%R | 502081 | 6359 | 124820 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 392 | 0 | 200 | 0 | 1461.6 | 1461.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-04-10 17:00 |  | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | boBWB/RhQweaQPrgFB1tvA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41820 | N | N | 10 | GROUND FLOOR |  | 124817 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1461.6 | LABOR- SUBCONTRACTOR
%R | 502082 | 6359 | 124820 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ELGF4030 | Installation of Telephone System | 8178 | 280 | 40 | 160 | 0 | 542.4 | 542.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-06 17:00 |  | 2014-02-01 08:00 | 2014-02-24 17:00 | 2014-02-01 08:00 | 2014-02-24 17:00 | 2014-02-01 08:00 | 2014-02-24 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | ey3rCbLNRdy23eFkkuYiGA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41820 | N | N | 10 | GROUND FLOOR |  | 124817 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 542.4 | LABOR- SUBCONTRACTOR
%R | 502083 | 6359 | 124822 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ACFF4615 | Installation AC Pipes | 8178 | 256 | 8 | 160 | 0 | 340.8 | 340.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-03-08 17:00 |  | 2014-01-06 08:00 | 2014-01-28 17:00 | 2014-01-06 08:00 | 2014-01-28 17:00 | 2014-01-06 08:00 | 2014-01-28 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | 3A+V0tQXRA+w8NYs0byVdQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41910 | N | N | 15 | FIRST FLOORS |  | 124821 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 340.8 | LABOR- SUBCONTRACTOR
%R | 502084 | 6359 | 124822 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ACFF4620 | Fixing of Ventilation Equipments | 8178 | 72 | 0 | 200 | 0 | 136.8 | 136.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-16 08:00 | 2014-04-13 17:00 |  | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 |  | PT_Normal |  |  |  |  | n9n4FJ43Q1WF32UH7/VnLw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41910 | N | N | 15 | FIRST FLOORS |  | 124821 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 136.8 | LABOR- SUBCONTRACTOR
%R | 502085 | 6359 | 124822 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ACFF4625 | Fixing of Split AC | 8178 | 72 | 0 | 160 | 0 | 361.2 | 361.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-04-28 17:00 |  | 2014-03-26 08:00 | 2014-04-17 17:00 | 2014-03-26 08:00 | 2014-04-17 17:00 | 2014-03-26 08:00 | 2014-04-17 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | 9kqsW9YPSKi5BgWSNKPi4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41910 | N | N | 15 | FIRST FLOORS |  | 124821 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 361.2 | LABOR- SUBCONTRACTOR
%R | 502086 | 6359 | 124823 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ACGF4600 | Installation AC Pipes | 8178 | 528 | 40 | 160 | 0 | 340.8 | 340.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-08 08:00 | 2014-03-03 17:00 |  | 2013-11-21 08:00 | 2013-12-14 17:00 | 2013-11-21 08:00 | 2013-12-14 17:00 | 2013-11-21 08:00 | 2013-12-14 17:00 | 2014-02-08 08:00 | 2014-03-03 17:00 |  | PT_Normal |  |  |  |  | nanXSZGFQb+xMloTt+Y7Rw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41900 | N | N | 10 | GROUND FLOOR |  | 124821 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 340.8 | LABOR- SUBCONTRACTOR
%R | 502087 | 6359 | 124823 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ACGF4605 | Fixing of Ventilation Equipments | 8178 | 408 | 0 | 200 | 0 | 136.8 | 136.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-16 08:00 | 2014-04-13 17:00 |  | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 |  | PT_Normal |  |  |  |  | cHRtUxx0SpaUUE/bQQdsmQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41900 | N | N | 10 | GROUND FLOOR |  | 124821 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 136.8 | LABOR- SUBCONTRACTOR
%R | 502088 | 6359 | 124823 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ACGF4610 | Fixing of Split AC | 8178 | 408 | 40 | 160 | 0 | 361.2 | 361.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-04-28 17:00 |  | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | TtTJka7ZTXSNrhdjce/YpQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41900 | N | N | 10 | GROUND FLOOR |  | 124821 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 361.2 | LABOR- SUBCONTRACTOR
%R | 502089 | 6359 | 124824 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ACRF4630 | Installation of Refrigerant Pipes | 8178 | 584 | 0 | 200 | 0 | 170.4 | 170.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-10 17:00 |  | 2014-01-15 08:00 | 2014-02-13 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | Jn4H9ijxRJSuaNunKAt7aw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41920 | N | N | 20 | ROOF |  | 124821 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 170.4 | LABOR- SUBCONTRACTOR
%R | 502090 | 6359 | 124824 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3ACRF4635 | Installation of Condensing Unit | 8178 | 112 | 0 | 200 | 0 | 562.8 | 562.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | QcmEDb8dQ+20pol3nzni9Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41920 | N | N | 20 | ROOF |  | 124821 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 562.8 | LABOR- SUBCONTRACTOR
%R | 502091 | 6359 | 124826 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3MSEX5020 | Construction Entrance Ramp | 8164 | 168 | 0 | 200 | 0 | 216 | 216 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-30 17:00 |  | 2014-02-04 08:00 | 2014-03-05 17:00 | 2014-02-04 08:00 | 2014-03-05 17:00 | 2014-02-04 08:00 | 2014-03-05 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | rAO092xVRMG5kyTBUxCQAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41950 | N | N | 10 | MISCELLANEOUS |  | 124825 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 108 | SCREED MASON SK
%R | 502092 | 6359 | 124826 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3MSEX5025 | SS.Handrails and Balustrades | 8178 | 168 | 0 | 160 | 0 | 108 | 108 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-10 17:00 |  | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | AcqKY9A4QF65p2/f4EWeJg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41950 | N | N | 10 | MISCELLANEOUS |  | 124825 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 108 | LABOR- SUBCONTRACTOR
%R | 502093 | 6359 | 124826 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3MSEX5015 | Construction of grease Trap | 8178 | 368 | 0 | 160 | 0 | 42 | 42 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-03 08:00 | 2014-03-25 17:00 |  | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-03-03 08:00 | 2014-03-25 17:00 |  | PT_Normal |  |  |  |  | wKwyEA0oQTyIodz/W9FulA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41950 | N | N | 10 | MISCELLANEOUS |  | 124825 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 42 | LABOR- SUBCONTRACTOR
%R | 502094 | 6359 | 124826 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3MSEX5000 | Construction of Manholes | 8178 | 368 | 0 | 200 | 0 | 132 | 132 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-27 08:00 | 2014-02-25 17:00 |  | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 |  | PT_Normal |  |  |  |  | 9Fi4VTMuT/WVwZT3tlFQEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41950 | N | N | 10 | MISCELLANEOUS |  | 124825 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 132 | LABOR- SUBCONTRACTOR
%R | 502095 | 6359 | 124826 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3MSEX5005 | Construction of Soak pit, Chambers | 8177 | 368 | 0 | 200 | 0 | 275 | 275 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-10 08:00 | 2014-03-11 17:00 |  | 2013-12-17 08:00 | 2014-01-15 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 | 2014-02-10 08:00 | 2014-03-11 17:00 |  | PT_Normal |  |  |  |  | SzuSEZxbRKiI6jjPOkMZvA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41950 | N | N | 10 | MISCELLANEOUS |  | 124825 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 275 | LABOR - CIVIL
%R | 502096 | 6359 | 124826 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3MSEX5010 | Telephone cable laying | 8177 | 368 | 208 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-26 08:00 | 2014-04-23 17:00 |  | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 |  | PT_Normal |  |  |  |  | 9X+iI1b2TMyAoQkMV4Y7PA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41950 | N | N | 10 | MISCELLANEOUS |  | 124825 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01; period 2: 2014-AP03 |  | 250 | LABOR - CIVIL
%R | 502097 | 6359 | 124827 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3WTEX5030 | Excavation | 8177 | 464 | 0 | 160 | 0 | 116 | 116 | 160 | 80 | 0 | 80 |  |  |  | 2014-02-13 08:00 | 2014-03-08 17:00 |  | 2013-12-05 08:00 | 2013-12-29 17:00 | 2013-12-05 08:00 | 2013-12-29 17:00 | 2013-12-05 08:00 | 2013-12-29 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | /gfGIiDXQSuJtiGN/dQj2w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41960 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124825 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 116 | LABOR - CIVIL
%R | 502098 | 6359 | 124827 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3WTEX5035 | Construction of Raft | 8167 | 464 | 0 | 200 | 0 | 210 | 210 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-19 08:00 | 2014-03-19 17:00 |  | 2013-12-11 08:00 | 2014-01-09 17:00 | 2013-12-11 08:00 | 2014-01-09 17:00 | 2013-12-11 08:00 | 2014-01-09 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 |  | PT_Normal |  |  |  |  | sybhxljpSjCBKm4glTFU8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41960 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124825 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 210 | CONCRETE MASON SK
%R | 502099 | 6359 | 124827 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3WTEX5040 | Block works & Plastering | 8168 | 464 | 0 | 200 | 0 | 2442 | 2442 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-01 08:00 | 2014-03-29 17:00 |  | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2014-03-01 08:00 | 2014-03-29 17:00 |  | PT_Normal |  |  |  |  | MOMxtWRfSl2uuXyHlUTCAg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41960 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124825 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 2442 | BLOCK MASON SK
%R | 502100 | 6359 | 124827 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3WTEX5045 | Flooring & Painting | 8164 | 464 | 296 | 200 | 0 | 900 | 900 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-04-10 17:00 |  | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | mLmk0EOhTjeYwi+3Tyne5Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41960 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124825 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 900 | SCREED MASON SK
%R | 502101 | 6359 | 124827 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3WTEX5050 | Installation of Steel Gate | 8178 | 168 | 16 | 160 | 0 | 84 | 84 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-22 17:00 |  | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | Uf6gkgXGR0eo0QDyqn06RQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41960 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124825 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 84 | LABOR- SUBCONTRACTOR
%R | 502102 | 6359 | 124827 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3WTEX5060 | Structural steel & SS Shed cover installation | 8178 | 152 | 0 | 200 | 0 | 588 | 588 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-05-04 17:00 |  | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-04-06 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | S/ShXbbuQqyJ/gipQ6o3+Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41960 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124825 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 588 | LABOR- SUBCONTRACTOR
%R | 502103 | 6359 | 124827 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3WTEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 152 | 0 | 200 | 0 | 152.4 | 152.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | Y5/B6b+IRmOybfmDmWspLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41960 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124825 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 152.4 | LABOR- SUBCONTRACTOR
%R | 502104 | 6359 | 124827 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3WTEX5080 | Domestic Water Tank Electrical works | 8178 | 464 | 0 | 200 | 0 | 175 | 175 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-04-06 17:00 |  | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | h6d6dBNTRmqrvkj5aROn0A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41960 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124825 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 175 | LABOR- SUBCONTRACTOR
%R | 502105 | 6359 | 124827 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3WTEX5070 | Domestic Water Tank Plumbings works | 8178 | 464 | 0 | 200 | 0 | 200 | 200 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-04-06 17:00 |  | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | lc8ql2fFQCeXkfdbgmeeoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41960 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124825 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 200 | LABOR- SUBCONTRACTOR
%R | 502106 | 6359 | 124827 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3WTEX5075 | Domestic Water Tank AC works | 8178 | 464 | 0 | 200 | 0 | 175 | 175 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-04-06 17:00 |  | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | 2nug6e0ZQ/ytJFD1IoqrIA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41960 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124825 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 175 | LABOR- SUBCONTRACTOR
%R | 502107 | 6359 | 124827 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z3WTEX5085 | Domestic Water Tank Firefighting works | 8178 | 464 | 0 | 200 | 0 | 112.8 | 112.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-04-06 17:00 |  | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | gg20jv0QQNSXY919MeluRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 41960 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124825 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 112.8 | LABOR- SUBCONTRACTOR
%R | 502108 | 6359 | 124828 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03GNSP001000 | Survey works, | 8175 | 0 | 0 | 160 | 0 | 87.5 | 87.5 | 160 | 0 | 0 | 0 |  |  |  | 2012-12-01 08:00 | 2012-12-24 17:00 |  | 2012-12-01 08:00 | 2012-12-24 17:00 | 2012-12-01 08:00 | 2012-12-24 17:00 | 2012-12-01 08:00 | 2012-12-24 17:00 | 2012-12-01 08:00 | 2012-12-24 17:00 |  | PT_Normal |  |  |  |  | oid4w6K0Q6uFwpj/3pp28A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43520 |  |  |  |  | SURVEYOR SK | J315 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124695 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 87.5 | SURVEYOR SK
%R | 502109 | 6359 | 124828 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03GNSP002000 | Scanning for Existing Services for rerouting | 8180 | 0 | 0 | 80 | 0 | 325 | 325 | 80 | 0 | 0 | 0 |  |  |  | 2012-12-01 08:00 | 2012-12-11 17:00 |  | 2012-12-01 08:00 | 2012-12-11 17:00 | 2012-12-01 08:00 | 2012-12-11 17:00 | 2012-12-01 08:00 | 2012-12-11 17:00 | 2012-12-01 08:00 | 2012-12-11 17:00 |  | PT_Normal |  |  |  |  | fKoPKKPSSXietPJUTQpfiA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43571 |  |  |  |  | ELECTRICIANS SK | M302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124695 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 325 | ELECTRICIANS SK
%R | 502110 | 6359 | 124828 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03GNSP003000 | Site stripping | 8177 | 232 | 0 | 160 | 0 | 675 | 675 | 160 | 300 | 0 | 300 |  |  |  | 2013-01-12 08:00 | 2013-02-03 17:00 |  | 2012-12-08 08:00 | 2012-12-31 17:00 | 2012-12-08 08:00 | 2012-12-31 17:00 | 2012-12-08 08:00 | 2012-12-31 17:00 | 2013-01-12 08:00 | 2013-02-03 17:00 |  | PT_Normal |  |  |  |  | 3uBoaI3lTLumWXjAqAmSdg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124695 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 675 | LABOR - CIVIL
%R | 502111 | 6359 | 124828 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03GNSP004000 | Demolition of Existing building & landscaping | 8177 | 232 | 0 | 160 | 0 | 2687.5 | 2687.5 | 160 | 1750 | 0 | 1750 |  |  |  | 2013-01-17 08:00 | 2013-02-09 17:00 |  | 2012-12-13 08:00 | 2013-01-06 17:00 | 2012-12-13 08:00 | 2013-01-06 17:00 | 2012-12-13 08:00 | 2013-01-06 17:00 | 2013-01-17 08:00 | 2013-02-09 17:00 |  | PT_Normal |  |  |  |  | 3P7WO1erQDeW46Bzl9WFOg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124695 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 2687.5 | LABOR - CIVIL
%R | 502112 | 6359 | 124828 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03GNSP005000 | Demolition of existing services works | 8177 | 232 | 232 | 160 | 0 | 775 | 775 | 160 | 400 | 0 | 400 |  |  |  | 2013-01-23 08:00 | 2013-02-16 17:00 |  | 2012-12-20 08:00 | 2013-01-12 17:00 | 2012-12-20 08:00 | 2013-01-12 17:00 | 2012-12-20 08:00 | 2013-01-12 17:00 | 2013-01-23 08:00 | 2013-02-16 17:00 |  | PT_Normal |  |  |  |  | bE527Oa7TEmd7+bllotdeg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124695 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 775 | LABOR - CIVIL
%R | 502113 | 6359 | 124828 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03GNSP002100 | Submission of Scanning Reports |  | 0 | 0 | 40 | 0 | 40 | 40 | 40 | 0 | 0 | 0 |  |  |  | 2012-12-12 08:00 | 2012-12-17 17:00 |  | 2012-12-12 08:00 | 2012-12-17 17:00 | 2012-12-12 08:00 | 2012-12-17 17:00 | 2012-12-12 08:00 | 2012-12-17 17:00 | 2012-12-12 08:00 | 2012-12-17 17:00 |  | PT_Normal |  |  |  |  | 79R5EtdWTm2uKvtIEA67Vg | Y75aF4QgRxWhj47ZJVDqQA |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 40630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124695 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 40 | 0
%R | 502114 | 6359 | 124828 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03GNSP002200 | Information Required for Rerouting |  | 0 | 0 | 112 | 0 | 0 | 0 | 112 | 0 | 0 | 0 |  |  |  | 2012-12-19 08:00 | 2013-01-03 17:00 |  | 2012-12-19 08:00 | 2013-01-03 17:00 | 2012-12-19 08:00 | 2013-01-03 17:00 | 2012-12-19 08:00 | 2013-01-03 17:00 | 2012-12-19 08:00 | 2013-01-03 17:00 |  | PT_Normal |  |  |  |  | vJaG9y8ETK+XwThhQ/vMCg | Y75aF4QgRxWhj47ZJVDqQA |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 40630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124695 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 502115 | 6359 | 124828 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03GNSP002300 | Preparation & Submission for New Layout |  | 0 | 0 | 40 | 0 | 32 | 32 | 40 | 0 | 0 | 0 |  |  |  | 2013-01-05 08:00 | 2013-01-09 17:00 |  | 2013-01-05 08:00 | 2013-01-09 17:00 | 2013-01-05 08:00 | 2013-01-09 17:00 | 2013-01-05 08:00 | 2013-01-09 17:00 | 2013-01-05 08:00 | 2013-01-09 17:00 |  | PT_Normal |  |  |  |  | CMqJTbbkRrq8FZIOGrwl4g | zqt8miC+PE2BOOz6wRLSOw |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 40630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124695 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 32 | 0
%R | 502116 | 6359 | 124828 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03GNSP002400 | Approval for new Layout for rerouting |  | 0 | 0 | 80 | 0 | 0 | 0 | 80 | 0 | 0 | 0 |  |  |  | 2013-01-10 08:00 | 2013-01-21 17:00 |  | 2013-01-10 08:00 | 2013-01-21 17:00 | 2013-01-10 08:00 | 2013-01-21 17:00 | 2013-01-10 08:00 | 2013-01-21 17:00 | 2013-01-10 08:00 | 2013-01-21 17:00 |  | PT_Normal |  |  |  |  | FhZrDM+OTwK7XYjKQDhZ+g | zI1R+4GvEkS6yTXhRIShOw |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 40630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124695 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 0 | 0
%R | 502117 | 6359 | 124828 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03GNSP002500 | Rerouting Works | 8180 | 0 | 0 | 200 | 0 | 325 | 325 | 200 | 0 | 0 | 0 |  |  |  | 2013-01-22 08:00 | 2013-02-20 17:00 |  | 2013-01-22 08:00 | 2013-02-20 17:00 | 2013-01-22 08:00 | 2013-02-20 17:00 | 2013-01-22 08:00 | 2013-02-20 17:00 | 2013-01-22 08:00 | 2013-02-20 17:00 |  | PT_Normal |  |  |  |  | tuA4M7xkRF+0LcU+I6sAiA | oDyiYv8C1EO7EISJj7AOSA |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43571 |  |  |  |  | ELECTRICIANS SK | M302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40630 | N | N | 03 | SITE PREPARATORY WORKS |  | 124695 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 325 | ELECTRICIANS SK
%R | 502118 | 6359 | 124830 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 0 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-13 17:00 |  | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 |  | PT_Normal |  |  |  |  | Kd5agjqsSJKc4PyzZWgqcw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42350 | N | N | 30 | TESTING AND COMMISSIONING |  | 124829 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 502119 | 6359 | 124830 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-13 17:00 |  | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 |  | PT_Normal |  |  |  |  | e7LkPhGdQZaRkyWoyeRsBw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42350 | N | N | 30 | TESTING AND COMMISSIONING |  | 124829 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 502120 | 6359 | 124830 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-13 17:00 |  | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 |  | PT_Normal |  |  |  |  | koRrVajOQiSdH8J8QzQudw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42350 | N | N | 30 | TESTING AND COMMISSIONING |  | 124829 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 502121 | 6359 | 124833 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ELRF4070 | Installation of Isolator | 8178 | 16 | 0 | 144 | 0 | 309.6 | 309.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-05-12 08:00 | 2014-06-01 17:00 |  | 2014-05-10 08:00 | 2014-05-29 17:00 | 2014-05-10 08:00 | 2014-05-29 17:00 | 2014-05-10 08:00 | 2014-05-29 17:00 | 2014-05-12 08:00 | 2014-06-01 17:00 |  | PT_Normal |  |  |  |  | sAXTUj+EQ/OxtoLhETVLeA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42200 | N | N | 20 | ROOF |  | 124832 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 309.6 | LABOR- SUBCONTRACTOR
%R | 502122 | 6359 | 124833 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ELRF4075 | Installation of TV Dish Antenna | 8178 | 16 | 16 | 184 | 0 | 4725.6 | 4725.6 | 184 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-14 17:00 |  | 2014-05-17 08:00 | 2014-06-11 17:00 | 2014-05-17 08:00 | 2014-06-11 17:00 | 2014-05-17 08:00 | 2014-06-11 17:00 | 2014-05-19 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | YzxhK4qBTZuXxhzqVeADRA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42200 | N | N | 20 | ROOF |  | 124832 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 4725.6 | LABOR- SUBCONTRACTOR
%R | 502123 | 6359 | 124834 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 392 | 0 | 200 | 0 | 1461.6 | 1461.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-10 17:00 |  | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | qhgH4zrqRnm2DdqX+Cqc6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42180 | N | N | 10 | GROUND FLOOR |  | 124832 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 730.8 | LABOR- SUBCONTRACTOR
%R | 502124 | 6359 | 124834 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ELGF4030 | Installation of Telephone System | 8178 | 288 | 40 | 160 | 0 | 542.4 | 542.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-14 08:00 | 2014-05-06 17:00 |  | 2014-03-03 08:00 | 2014-03-25 17:00 | 2014-03-03 08:00 | 2014-03-25 17:00 | 2014-03-03 08:00 | 2014-03-25 17:00 | 2014-04-14 08:00 | 2014-05-06 17:00 |  | PT_Normal |  |  |  |  | O2WKBkJ6QuGMMtWxXrL2DQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42180 | N | N | 10 | GROUND FLOOR |  | 124832 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 542.4 | LABOR- SUBCONTRACTOR
%R | 502125 | 6359 | 124834 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 360 | 0 | 200 | 0 | 1102.8 | 1102.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-02-10 17:00 |  | 2013-11-20 08:00 | 2013-12-19 17:00 | 2013-11-20 08:00 | 2013-12-19 17:00 | 2013-11-20 08:00 | 2013-12-19 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | 4GHTnivcTLOUtqM0cFBtqQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42180 | N | N | 10 | GROUND FLOOR |  | 124832 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1102.8 | LABOR- SUBCONTRACTOR
%R | 502126 | 6359 | 124834 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ELGF4005 | Cable tray & trunking installation | 8178 | 504 | 0 | 160 | 0 | 1840.8 | 1840.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-10 17:00 |  | 2013-12-02 08:00 | 2013-12-25 17:00 | 2013-12-02 08:00 | 2013-12-25 17:00 | 2013-12-02 08:00 | 2013-12-25 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | LNOR3i2CRg2nWHfsSGou1w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42180 | N | N | 10 | GROUND FLOOR |  | 124832 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1840.8 | LABOR- SUBCONTRACTOR
%R | 502127 | 6359 | 124834 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ELGF4010 | Installation of wiring & Main Cabling | 8178 | 504 | 216 | 200 | 0 | 648 | 648 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-24 17:00 |  | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | ThPXUHGITo6j0pXXh/Bebw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42180 | N | N | 10 | GROUND FLOOR |  | 124832 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 648 | LABOR- SUBCONTRACTOR
%R | 502128 | 6359 | 124834 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 288 | 0 | 160 | 0 | 222 | 222 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-02 08:00 | 2014-04-24 17:00 |  | 2014-02-19 08:00 | 2014-03-13 17:00 | 2014-02-19 08:00 | 2014-03-13 17:00 | 2014-02-19 08:00 | 2014-03-13 17:00 | 2014-04-02 08:00 | 2014-04-24 17:00 |  | PT_Normal |  |  |  |  | SpmfpNTMRD2MDTI3r3ZjFg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42180 | N | N | 10 | GROUND FLOOR |  | 124832 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 222 | LABOR- SUBCONTRACTOR
%R | 502129 | 6359 | 124834 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 304 | 0 | 200 | 0 | 2580 | 2580 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-16 08:00 | 2014-05-14 17:00 |  | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 |  | PT_Normal |  |  |  |  | qTMynPjBQ16XySLsmt1Y6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42180 | N | N | 10 | GROUND FLOOR |  | 124832 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 2580 | LABOR- SUBCONTRACTOR
%R | 502130 | 6359 | 124835 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 88 | 0 | 200 | 0 | 1102.8 | 1102.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-15 08:00 | 2014-02-13 17:00 |  | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 |  | PT_Normal |  |  |  |  | /w96j/QEQFWR/OIXNhdufA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42190 | N | N | 15 | FIRST FLOORS |  | 124832 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1102.8 | LABOR- SUBCONTRACTOR
%R | 502131 | 6359 | 124835 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ELFF4040 | Cable tray & trunking installation | 8178 | 264 | 24 | 160 | 0 | 1840.8 | 1840.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-23 08:00 | 2014-03-17 17:00 |  | 2014-01-14 08:00 | 2014-02-05 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 | 2014-02-23 08:00 | 2014-03-17 17:00 |  | PT_Normal |  |  |  |  | 7JNe1+C9SgCBNpLdyddJAg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42190 | N | N | 15 | FIRST FLOORS |  | 124832 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1840.8 | LABOR- SUBCONTRACTOR
%R | 502132 | 6359 | 124835 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ELFF4045 | Installation of wiring & Main Cabling | 8178 | 240 | 0 | 200 | 0 | 648 | 648 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-03 08:00 | 2014-03-31 17:00 |  | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | jquJmlgdSSKECDRaKZ8Veg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42190 | N | N | 15 | FIRST FLOORS |  | 124832 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 648 | LABOR- SUBCONTRACTOR
%R | 502133 | 6359 | 124835 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 16 | 0 | 160 | 0 | 188.4 | 188.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-09 08:00 | 2014-05-01 17:00 |  | 2014-04-07 08:00 | 2014-04-29 17:00 | 2014-04-07 08:00 | 2014-04-29 17:00 | 2014-04-07 08:00 | 2014-04-29 17:00 | 2014-04-09 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | eDdiRc+MTzu9MPE6Ic1WNQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42190 | N | N | 15 | FIRST FLOORS |  | 124832 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 188.4 | LABOR- SUBCONTRACTOR
%R | 502134 | 6359 | 124835 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 16 | 0 | 200 | 0 | 2528.4 | 2528.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-22 08:00 | 2014-05-20 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-22 08:00 | 2014-05-20 17:00 |  | PT_Normal |  |  |  |  | Dsp0ADcJRuqHR4odr6hemw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42190 | N | N | 15 | FIRST FLOORS |  | 124832 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 2528.4 | LABOR- SUBCONTRACTOR
%R | 502135 | 6359 | 124835 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 96 | 0 | 200 | 0 | 1612.8 | 1612.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | FCJ0QeOmTzC8zc8p65WEag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42190 | N | N | 15 | FIRST FLOORS |  | 124832 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1612.8 | LABOR- SUBCONTRACTOR
%R | 502136 | 6359 | 124835 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ELFF4050 | Installation of Telephone System | 8178 | 168 | 152 | 200 | 0 | 542.4 | 542.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-26 08:00 | 2014-05-24 17:00 |  | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 |  | PT_Normal |  |  |  |  | IhocrYaPSVS+WruC+s8J+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42190 | N | N | 15 | FIRST FLOORS |  | 124832 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 542.4 | LABOR- SUBCONTRACTOR
%R | 502137 | 6359 | 124837 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 288 | 0 | 144 | 0 | 2732.4 | 2732.4 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-02-02 17:00 |  | 2013-12-01 08:00 | 2013-12-22 17:00 | 2013-12-01 08:00 | 2013-12-22 17:00 | 2013-12-01 08:00 | 2013-12-22 17:00 | 2014-01-13 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | vRa+Q1LkTyO1eC8HT//8UA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42220 | N | N | 10 | GROUND FLOOR |  | 124836 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 2732.4 | LABOR- SUBCONTRACTOR
%R | 502138 | 6359 | 124837 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4PLGF4310 | Installation of Drainage pipes &testing | 8178 | 456 | 136 | 144 | 0 | 216 | 216 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-02-27 17:00 |  | 2013-12-01 08:00 | 2013-12-22 17:00 | 2013-12-01 08:00 | 2013-12-22 17:00 | 2013-12-01 08:00 | 2013-12-22 17:00 | 2014-02-06 08:00 | 2014-02-27 17:00 |  | PT_Normal |  |  |  |  | gfxIiVmdRXiqEO5Hj+/i/w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42220 | N | N | 10 | GROUND FLOOR |  | 124836 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 216 | LABOR- SUBCONTRACTOR
%R | 502139 | 6359 | 124837 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4PLGF4315 | Sanitary Fittings & Accessories | 8178 | 512 | 0 | 160 | 0 | 352.8 | 352.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-08 17:00 |  | 2014-03-03 08:00 | 2014-03-25 17:00 | 2014-03-03 08:00 | 2014-03-25 17:00 | 2014-03-03 08:00 | 2014-03-25 17:00 | 2014-05-17 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | SXquM8zDTJeO14Va58HeuQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42220 | N | N | 10 | GROUND FLOOR |  | 124836 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 352.8 | LABOR- SUBCONTRACTOR
%R | 502140 | 6359 | 124837 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4PLGF4320 | Installation of Water Heater | 8178 | 512 | 80 | 120 | 0 | 50.4 | 50.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-14 17:00 |  | 2014-03-15 08:00 | 2014-03-31 17:00 | 2014-03-15 08:00 | 2014-03-31 17:00 | 2014-03-15 08:00 | 2014-03-31 17:00 | 2014-05-28 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | 0j6vTNf5ShWu3x0k8z0AIQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42220 | N | N | 10 | GROUND FLOOR |  | 124836 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 502141 | 6359 | 124837 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 0 | 0 | 160 | 0 | 165.6 | 165.6 | 160 | 0 | 0 | 0 |  |  |  | 2013-08-04 08:00 | 2013-08-29 17:00 |  | 2013-08-04 08:00 | 2013-08-29 17:00 | 2013-08-04 08:00 | 2013-08-29 17:00 | 2013-08-04 08:00 | 2013-08-29 17:00 | 2013-08-04 08:00 | 2013-08-29 17:00 |  | PT_Normal |  |  |  |  | yjlMn3QSSpapX1XtMF/5LQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42220 | N | N | 10 | GROUND FLOOR |  | 124836 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 165.6 | LABOR- SUBCONTRACTOR
%R | 502142 | 6359 | 124838 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 568 | 144 | 120 | 0 | 1623.6 | 1623.6 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-01 08:00 | 2014-05-18 17:00 |  | 2014-02-06 08:00 | 2014-02-24 17:00 | 2014-02-06 08:00 | 2014-02-24 17:00 | 2014-02-06 08:00 | 2014-02-24 17:00 | 2014-05-01 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | SDsbGvOhSmiTS09wS3rnfA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42240 | N | N | 20 | ROOF |  | 124836 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1623.6 | LABOR- SUBCONTRACTOR
%R | 502143 | 6359 | 124838 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4PLRF4350 | Installation of Rain water Pipes | 8178 | 424 | 80 | 120 | 0 | 82.8 | 82.8 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-05-27 17:00 |  | 2014-03-10 08:00 | 2014-03-26 17:00 | 2014-03-10 08:00 | 2014-03-26 17:00 | 2014-03-10 08:00 | 2014-03-26 17:00 | 2014-05-11 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | HC7G7xi8QsGsSp53toa8iQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42240 | N | N | 20 | ROOF |  | 124836 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 82.8 | LABOR- SUBCONTRACTOR
%R | 502144 | 6359 | 124838 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 112 | 16 | 200 | 0 | 100.8 | 100.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | GVWymM7GTzOpKiVV4INXSw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42240 | N | N | 20 | ROOF |  | 124836 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 100.8 | LABOR- SUBCONTRACTOR
%R | 502145 | 6359 | 124839 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 0 | 0 | 144 | 0 | 2732.4 | 2732.4 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-12 08:00 | 2014-02-01 17:00 |  | 2014-01-12 08:00 | 2014-02-01 17:00 | 2014-01-12 08:00 | 2014-02-01 17:00 | 2014-01-12 08:00 | 2014-02-01 17:00 | 2014-01-12 08:00 | 2014-02-01 17:00 |  | PT_Normal |  |  |  |  | 92mnQrtbRHuuMgIdMvz+XQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42230 | N | N | 15 | FIRST FLOORS |  | 124836 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 2732.4 | LABOR- SUBCONTRACTOR
%R | 502146 | 6359 | 124839 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4PLFF4330 | Installation of Drainage pipes & testing | 8178 | 208 | 56 | 144 | 0 | 216 | 216 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-03-05 17:00 |  | 2014-01-13 08:00 | 2014-02-02 17:00 | 2014-01-13 08:00 | 2014-02-02 17:00 | 2014-01-13 08:00 | 2014-02-02 17:00 | 2014-02-13 08:00 | 2014-03-05 17:00 |  | PT_Normal |  |  |  |  | k/d4og7yQeGnbipM0cE7yQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42230 | N | N | 15 | FIRST FLOORS |  | 124836 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 216 | LABOR- SUBCONTRACTOR
%R | 502147 | 6359 | 124839 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4PLFF4335 | Sanitary Fittings & Accessories | 8178 | 112 | 0 | 160 | 0 | 352.8 | 352.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-21 17:00 |  | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-29 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | h8lMuiiWR1uO/Uax4yr8pA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42230 | N | N | 15 | FIRST FLOORS |  | 124836 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 352.8 | LABOR- SUBCONTRACTOR
%R | 502148 | 6359 | 124839 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4PLFF4340 | Installation of Water Heater | 8178 | 112 | 0 | 120 | 0 | 50.4 | 50.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-05-27 17:00 |  | 2014-04-24 08:00 | 2014-05-11 17:00 | 2014-04-24 08:00 | 2014-05-11 17:00 | 2014-04-24 08:00 | 2014-05-11 17:00 | 2014-05-11 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | ZASIwTpEQeuh+CYpFL7TJw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42230 | N | N | 15 | FIRST FLOORS |  | 124836 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 502149 | 6359 | 124841 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ACFF4615 | Installation AC Pipes | 8178 | 256 | 8 | 160 | 0 | 340.8 | 340.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-06 17:00 |  | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | vI2O+piwRfGl0Z5oMKBFdg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42270 | N | N | 15 | FIRST FLOORS |  | 124840 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 340.8 | LABOR- SUBCONTRACTOR
%R | 502150 | 6359 | 124841 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ACFF4620 | Fixing of Ventilation Equipments | 8178 | 72 | 0 | 200 | 0 | 136.8 | 136.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-14 08:00 | 2014-05-12 17:00 |  | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 |  | PT_Normal |  |  |  |  | 3+RGDfrNSz+8YHPUb12I1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42270 | N | N | 15 | FIRST FLOORS |  | 124840 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 136.8 | LABOR- SUBCONTRACTOR
%R | 502151 | 6359 | 124841 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ACFF4625 | Fixing of Split AC | 8178 | 72 | 0 | 160 | 0 | 361.2 | 361.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-05 08:00 | 2014-05-27 17:00 |  | 2014-04-24 08:00 | 2014-05-17 17:00 | 2014-04-24 08:00 | 2014-05-17 17:00 | 2014-04-24 08:00 | 2014-05-17 17:00 | 2014-05-05 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | YVSgarIjSteJnG2XC+biHg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42270 | N | N | 15 | FIRST FLOORS |  | 124840 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 361.2 | LABOR- SUBCONTRACTOR
%R | 502152 | 6359 | 124842 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ACGF4600 | Installation AC Pipes | 8178 | 536 | 40 | 160 | 0 | 340.8 | 340.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-04-02 17:00 |  | 2013-12-22 08:00 | 2014-01-13 17:00 | 2013-12-22 08:00 | 2014-01-13 17:00 | 2013-12-22 08:00 | 2014-01-13 17:00 | 2014-03-11 08:00 | 2014-04-02 17:00 |  | PT_Normal |  |  |  |  | vYAhVyD1Qgq+rMhOI8wy9g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42260 | N | N | 10 | GROUND FLOOR |  | 124840 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 340.8 | LABOR- SUBCONTRACTOR
%R | 502153 | 6359 | 124842 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ACGF4605 | Fixing of Ventilation Equipments | 8178 | 408 | 0 | 200 | 0 | 136.8 | 136.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-14 08:00 | 2014-05-12 17:00 |  | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 |  | PT_Normal |  |  |  |  | hCto/uzNRPCyCglG8LDi8A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42260 | N | N | 10 | GROUND FLOOR |  | 124840 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 68.4 | LABOR- SUBCONTRACTOR
%R | 502154 | 6359 | 124842 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ACGF4610 | Fixing of Split AC | 8178 | 408 | 40 | 160 | 0 | 361.2 | 361.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-05 08:00 | 2014-05-27 17:00 |  | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-05-05 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | KofZkfmTS1eTe7RVkzj/iA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42260 | N | N | 10 | GROUND FLOOR |  | 124840 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 361.2 | LABOR- SUBCONTRACTOR
%R | 502155 | 6359 | 124843 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ACRF4630 | Installation of Refrigerant Pipes | 8178 | 584 | 0 | 200 | 0 | 170.4 | 170.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-06-08 17:00 |  | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | tYJQTO7RSP20L9D4Ne0fyQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42280 | N | N | 20 | ROOF |  | 124840 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 85.2 | LABOR- SUBCONTRACTOR
%R | 502156 | 6359 | 124843 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ACRF4635 | Installation of Condensing Unit | 8178 | 112 | 0 | 200 | 0 | 562.8 | 562.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | U+DbYRktQ+SLTC2DudJnIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42280 | N | N | 20 | ROOF |  | 124840 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 562.8 | LABOR- SUBCONTRACTOR
%R | 502157 | 6359 | 124846 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARRF3610 | Flooring screed | 8164 | 576 | 0 | 120 | 0 | 115.5 | 115.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-03 08:00 | 2014-05-19 17:00 |  | 2014-02-06 08:00 | 2014-02-24 17:00 | 2014-02-06 08:00 | 2014-02-24 17:00 | 2014-02-06 08:00 | 2014-02-24 17:00 | 2014-05-03 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | fvKiUHUSRZamlYmD6qfyow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42120 | N | N | 20 | ROOF |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 115.5 | SCREED MASON SK
%R | 502158 | 6359 | 124846 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARRF3695 | Painting | 8178 | 576 | 0 | 160 | 0 | 504 | 504 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-06-02 17:00 |  | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-05-11 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | RY5JO+zwQrCcj8eOR18+RQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42120 | N | N | 20 | ROOF |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 504 | LABOR- SUBCONTRACTOR
%R | 502159 | 6359 | 124846 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARRF3620 | Epoxy Painting | 8178 | 576 | 576 | 120 | 0 | 24.75 | 24.75 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-14 17:00 |  | 2014-03-05 08:00 | 2014-03-22 17:00 | 2014-03-05 08:00 | 2014-03-22 17:00 | 2014-03-05 08:00 | 2014-03-22 17:00 | 2014-05-28 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | 7lxHU+zlRUueXvjKnpOMcQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42120 | N | N | 20 | ROOF |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 24.75 | LABOR- SUBCONTRACTOR
%R | 502160 | 6359 | 124846 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARRF3600 | Block work | 8168 | 536 | 0 | 160 | 0 | 487.5 | 487.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-05 08:00 | 2014-04-27 17:00 |  | 2014-01-15 08:00 | 2014-02-06 17:00 | 2014-01-15 08:00 | 2014-02-06 17:00 | 2014-01-15 08:00 | 2014-02-06 17:00 | 2014-04-05 08:00 | 2014-04-27 17:00 |  | PT_Normal |  |  |  |  | Awe2hlWpTomw+Isd8VPqlA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42120 | N | N | 20 | ROOF |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 487.5 | BLOCK MASON SK
%R | 502161 | 6359 | 124846 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARRF3605 | Plastering work | 8169 | 536 | 0 | 160 | 0 | 1950 | 1950 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-13 08:00 | 2014-05-05 17:00 |  | 2014-01-23 08:00 | 2014-02-16 17:00 | 2014-01-23 08:00 | 2014-02-16 17:00 | 2014-01-23 08:00 | 2014-02-16 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | 45yG2Z8fTUaUsCDoWAJZBw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42120 | N | N | 20 | ROOF |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1950 | PLASTER MASON SK
%R | 502162 | 6359 | 124847 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARFF3300 | Block work | 8168 | 0 | 0 | 200 | 0 | 5553.5 | 5553.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-28 08:00 | 2014-01-25 17:00 |  | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 |  | PT_Normal |  |  |  |  | CIkW+oWVQgmPm0aGFZsffQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42110 | N | N | 15 | FIRST FLOORS |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 5553.5 | BLOCK MASON SK
%R | 502163 | 6359 | 124847 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARFF3305 | Plastering work | 8169 | 0 | 0 | 200 | 0 | 5516 | 5516 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-21 08:00 | 2014-02-19 17:00 |  | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 |  | PT_Normal |  |  |  |  | BeyJbLLGTZuHtOnPamkh3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42110 | N | N | 15 | FIRST FLOORS |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 5516 | PLASTER MASON SK
%R | 502164 | 6359 | 124847 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARFF3310 | Flooring screed | 8164 | 120 | 120 | 168 | 0 | 1031.25 | 1031.25 | 168 | 0 | 0 | 0 |  |  |  | 2014-02-17 08:00 | 2014-03-12 17:00 |  | 2014-01-29 08:00 | 2014-02-23 17:00 | 2014-01-29 08:00 | 2014-02-23 17:00 | 2014-01-29 08:00 | 2014-02-23 17:00 | 2014-02-17 08:00 | 2014-03-12 17:00 |  | PT_Normal |  |  |  |  | DtfTacbmTxit3KnLt5IL6g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42110 | N | N | 15 | FIRST FLOORS |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1031.25 | SCREED MASON SK
%R | 502165 | 6359 | 124847 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARFF3315 | Wet area waterproofing | 8178 | 0 | 0 | 120 | 0 | 582 | 582 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-01 17:00 |  | 2014-02-12 08:00 | 2014-03-01 17:00 | 2014-02-12 08:00 | 2014-03-01 17:00 | 2014-02-12 08:00 | 2014-03-01 17:00 | 2014-02-12 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | Ijr1mjYMTd63FfS5KtlZ3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42110 | N | N | 15 | FIRST FLOORS |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 582 | LABOR- SUBCONTRACTOR
%R | 502166 | 6359 | 124847 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARFF3330 | Paint First coat | 8178 | 144 | 144 | 200 | 0 | 3644.75 | 3644.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-01 08:00 | 2014-03-29 17:00 |  | 2014-02-06 08:00 | 2014-03-08 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 | 2014-03-01 08:00 | 2014-03-29 17:00 |  | PT_Normal |  |  |  |  | 0+RHJOwUS1W5PKH1oPh7sA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42110 | N | N | 15 | FIRST FLOORS |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 1822.375 | LABOR- SUBCONTRACTOR
%R | 502167 | 6359 | 124847 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARFF3320 | Ceramic Wall Tiling | 8170 | 0 | 0 | 200 | 0 | 2603.5 | 2603.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-22 17:00 |  | 2014-02-22 08:00 | 2014-03-22 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | jidYp+5kTJedNiul3htxTA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42110 | N | N | 15 | FIRST FLOORS |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 1301.75 | TILE MASON SK
%R | 502168 | 6359 | 124847 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARFF3325 | Porcelain Tile flooring | 8170 | 0 | 0 | 200 | 0 | 1787.5 | 1787.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-01 08:00 | 2014-03-29 17:00 |  | 2014-03-01 08:00 | 2014-03-29 17:00 | 2014-03-01 08:00 | 2014-03-29 17:00 | 2014-03-01 08:00 | 2014-03-29 17:00 | 2014-03-01 08:00 | 2014-03-29 17:00 |  | PT_Normal |  |  |  |  | lKpp4cL0TXa/JRScSHr61Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42110 | N | N | 15 | FIRST FLOORS |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1787.5 | TILE MASON SK
%R | 502169 | 6359 | 124847 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARFF3335 | Slate Tile Flooring & Skirting | 8178 | 80 | 80 | 120 | 0 | 1350 | 1350 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-30 08:00 | 2014-04-15 17:00 |  | 2014-03-18 08:00 | 2014-04-03 17:00 | 2014-03-18 08:00 | 2014-04-03 17:00 | 2014-03-18 08:00 | 2014-04-03 17:00 | 2014-03-30 08:00 | 2014-04-15 17:00 |  | PT_Normal |  |  |  |  | VR3Xrx/vToSU41k4SINSgg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42110 | N | N | 15 | FIRST FLOORS |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1350 | LABOR- SUBCONTRACTOR
%R | 502170 | 6359 | 124847 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARFF3350 | Granite - Stair case flooring & Skirting | 8178 | 16 | 16 | 160 | 0 | 150 | 150 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-24 08:00 | 2014-04-15 17:00 |  | 2014-03-22 08:00 | 2014-04-13 17:00 | 2014-03-22 08:00 | 2014-04-13 17:00 | 2014-03-22 08:00 | 2014-04-13 17:00 | 2014-03-24 08:00 | 2014-04-15 17:00 |  | PT_Normal |  |  |  |  | J3y5u0GAQDeVnSfm4IqQjg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42110 | N | N | 15 | FIRST FLOORS |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 150 | LABOR- SUBCONTRACTOR
%R | 502171 | 6359 | 124847 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARFF3345 | Fixing of Suspension systems | 8178 | 0 | 0 | 160 | 0 | 1434.75 | 1434.75 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-06 17:00 |  | 2014-03-15 08:00 | 2014-04-06 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | ct5jwHmdSueeO+nzp/+IQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42110 | N | N | 15 | FIRST FLOORS |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1434.75 | LABOR- SUBCONTRACTOR
%R | 502172 | 6359 | 124847 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARFF3355 | Aluminum tile false ceiling | 8178 | 16 | 0 | 160 | 0 | 156.25 | 156.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-29 08:00 | 2014-04-20 17:00 |  | 2014-03-26 08:00 | 2014-04-17 17:00 | 2014-03-26 08:00 | 2014-04-17 17:00 | 2014-03-26 08:00 | 2014-04-17 17:00 | 2014-03-29 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | fIlrKg4NTIibJgK1U51W2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42110 | N | N | 15 | FIRST FLOORS |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 156.25 | LABOR- SUBCONTRACTOR
%R | 502173 | 6359 | 124847 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARFF3360 | Gypsum board false ceiling | 8178 | 0 | 0 | 200 | 0 | 1298.71 | 1298.71 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-23 08:00 | 2014-04-20 17:00 |  | 2014-03-23 08:00 | 2014-04-20 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | AoZkDOqITF2oOfOt90GMqg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42110 | N | N | 15 | FIRST FLOORS |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1298.71 | LABOR- SUBCONTRACTOR
%R | 502174 | 6359 | 124847 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARFF3365 | Wooden door | 8178 | 0 | 0 | 120 | 0 | 330 | 330 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-07 08:00 | 2014-04-23 17:00 |  | 2014-04-07 08:00 | 2014-04-23 17:00 | 2014-04-07 08:00 | 2014-04-23 17:00 | 2014-04-07 08:00 | 2014-04-23 17:00 | 2014-04-07 08:00 | 2014-04-23 17:00 |  | PT_Normal |  |  |  |  | rmcQSzR6Qz2/IDdVQch43w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42110 | N | N | 15 | FIRST FLOORS |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 330 | LABOR- SUBCONTRACTOR
%R | 502175 | 6359 | 124847 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARFF3370 | Aluminum Door | 8178 | 0 | 0 | 160 | 0 | 99 | 99 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-07 17:00 |  | 2014-04-15 08:00 | 2014-05-07 17:00 | 2014-04-15 08:00 | 2014-05-07 17:00 | 2014-04-15 08:00 | 2014-05-07 17:00 | 2014-04-15 08:00 | 2014-05-07 17:00 |  | PT_Normal |  |  |  |  | 2an3KR6LStO6DWvRVlPGgA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42110 | N | N | 15 | FIRST FLOORS |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 99 | LABOR- SUBCONTRACTOR
%R | 502176 | 6359 | 124847 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARFF3380 | Aluminum windows | 8178 | 88 | 88 | 160 | 0 | 264 | 264 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-05 08:00 | 2014-05-27 17:00 |  | 2014-04-22 08:00 | 2014-05-14 17:00 | 2014-04-22 08:00 | 2014-05-14 17:00 | 2014-04-22 08:00 | 2014-05-14 17:00 | 2014-05-05 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | oLxDUDPpR9qu/8BEdklVnw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42110 | N | N | 15 | FIRST FLOORS |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 264 | LABOR- SUBCONTRACTOR
%R | 502177 | 6359 | 124847 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARFF3375 | Carpentry & Joinery Works | 8178 | 0 | 0 | 200 | 0 | 300 | 300 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-05-21 17:00 |  | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | LcCC8TyDQrqWR46JcYdWMg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42110 | N | N | 15 | FIRST FLOORS |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 300 | LABOR- SUBCONTRACTOR
%R | 502178 | 6359 | 124847 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARFF3390 | Installation of Granite Counter Top | 8171 | 0 | 0 | 160 | 0 | 132 | 132 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-07 08:00 | 2014-05-29 17:00 |  | 2014-05-07 08:00 | 2014-05-29 17:00 | 2014-05-07 08:00 | 2014-05-29 17:00 | 2014-05-07 08:00 | 2014-05-29 17:00 | 2014-05-07 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | HjWpILOJQsK0hihEJQXYWg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42110 | N | N | 15 | FIRST FLOORS |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 132 | GRANITE MASON SK
%R | 502179 | 6359 | 124847 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARFF3385 | Handrail & Balustrade | 8178 | 0 | 0 | 160 | 0 | 275 | 275 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-05 08:00 | 2014-05-27 17:00 |  | 2014-05-05 08:00 | 2014-05-27 17:00 | 2014-05-05 08:00 | 2014-05-27 17:00 | 2014-05-05 08:00 | 2014-05-27 17:00 | 2014-05-05 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | 5I7aGG07QyWfjKgLnqp1YA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42110 | N | N | 15 | FIRST FLOORS |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 275 | LABOR- SUBCONTRACTOR
%R | 502180 | 6359 | 124847 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARFF3395 | Final Painting | 8178 | 0 | 0 | 200 | 0 | 3644.75 | 3644.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | zlvkLs3ES4GbG4H2YXHKvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42110 | N | N | 15 | FIRST FLOORS |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 3644.75 | LABOR- SUBCONTRACTOR
%R | 502181 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3000 | Block work | 8168 | 288 | 0 | 200 | 0 | 7112.5 | 7112.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-28 08:00 | 2014-01-25 17:00 |  | 2013-11-14 08:00 | 2013-12-12 17:00 | 2013-11-14 08:00 | 2013-12-12 17:00 | 2013-11-14 08:00 | 2013-12-12 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 |  | PT_Normal |  |  |  |  | 8HlBKH6XRDml9OF59P+gqg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 7112.5 | BLOCK MASON SK
%R | 502182 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3005 | Plastering work | 8169 | 288 | 0 | 200 | 0 | 6268.75 | 6268.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-19 08:00 | 2014-02-17 17:00 |  | 2013-12-07 08:00 | 2014-01-05 17:00 | 2013-12-07 08:00 | 2014-01-05 17:00 | 2013-12-07 08:00 | 2014-01-05 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 |  | PT_Normal |  |  |  |  | /WphrVZNTZSeqzq3oNhngw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 6268.75 | PLASTER MASON SK
%R | 502183 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3010 | Flooring screed | 8164 | 352 | 64 | 168 | 0 | 1234.75 | 1234.75 | 168 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-03-02 17:00 |  | 2013-12-15 08:00 | 2014-01-08 17:00 | 2013-12-15 08:00 | 2014-01-08 17:00 | 2013-12-15 08:00 | 2014-01-08 17:00 | 2014-02-05 08:00 | 2014-03-02 17:00 |  | PT_Normal |  |  |  |  | F55HwyOyQ+G5RwJPN1dYFA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1234.75 | SCREED MASON SK
%R | 502184 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 288 | 0 | 120 | 0 | 582 | 582 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-02-23 17:00 |  | 2013-12-25 08:00 | 2014-01-11 17:00 | 2013-12-25 08:00 | 2014-01-11 17:00 | 2013-12-25 08:00 | 2014-01-11 17:00 | 2014-02-05 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | wz00B7taTq6i4f9y9pHuhw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 582 | LABOR- SUBCONTRACTOR
%R | 502185 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3030 | Paint First coat | 8178 | 352 | 0 | 200 | 0 | 4136.55 | 4136.55 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-22 17:00 |  | 2013-12-31 08:00 | 2014-01-28 17:00 | 2013-12-31 08:00 | 2014-01-28 17:00 | 2013-12-31 08:00 | 2014-01-28 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | q9E7KJxzSouh+n8oqLLp9Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 4136.55 | LABOR- SUBCONTRACTOR
%R | 502186 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3020 | Ceramic Wall Tiling | 8170 | 288 | 0 | 200 | 0 | 2603.5 | 2603.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-12 17:00 |  | 2013-12-31 08:00 | 2014-01-28 17:00 | 2013-12-31 08:00 | 2014-01-28 17:00 | 2013-12-31 08:00 | 2014-01-28 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 |  | PT_Normal |  |  |  |  | wPfHN2ZDQ0ieN8iOs4Ey1w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 2603.5 | TILE MASON SK
%R | 502187 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3025 | Porcelain Tile flooring | 8170 | 288 | 0 | 200 | 0 | 1787.5 | 1787.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-18 17:00 |  | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | 9XEOdBAwSfG9VxYXXYq65w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1787.5 | TILE MASON SK
%R | 502188 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3040 | Cobble Tile flooring | 8170 | 320 | 0 | 120 | 0 | 68.75 | 68.75 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-07 17:00 |  | 2014-02-02 08:00 | 2014-02-19 17:00 | 2014-02-02 08:00 | 2014-02-19 17:00 | 2014-02-02 08:00 | 2014-02-19 17:00 | 2014-03-22 08:00 | 2014-04-07 17:00 |  | PT_Normal |  |  |  |  | eDDTTZmvR/afOfG5K6SNCQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 68.75 | TILE MASON SK
%R | 502189 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 336 | 16 | 120 | 0 | 45.5 | 45.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-02 17:00 |  | 2014-01-26 08:00 | 2014-02-12 17:00 | 2014-01-26 08:00 | 2014-02-12 17:00 | 2014-01-26 08:00 | 2014-02-12 17:00 | 2014-03-17 08:00 | 2014-04-02 17:00 |  | PT_Normal |  |  |  |  | DcfegP5eRJKh4guChhgWfw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 45.5 | TILE MASON SK
%R | 502190 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 320 | 0 | 160 | 0 | 506.25 | 506.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-30 08:00 | 2014-04-21 17:00 |  | 2014-02-10 08:00 | 2014-03-05 17:00 | 2014-02-10 08:00 | 2014-03-05 17:00 | 2014-02-10 08:00 | 2014-03-05 17:00 | 2014-03-30 08:00 | 2014-04-21 17:00 |  | PT_Normal |  |  |  |  | H3XcCsWYTfesTnDLgnudiA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 506.25 | GRANITE MASON SK
%R | 502191 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3045 | Fixing of Suspension systems | 8178 | 288 | 0 | 160 | 0 | 1434.75 | 1434.75 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-30 17:00 |  | 2014-01-23 08:00 | 2014-02-16 17:00 | 2014-01-23 08:00 | 2014-02-16 17:00 | 2014-01-23 08:00 | 2014-02-16 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | r4L63an5Qpu65BpWJxbYzw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1434.75 | LABOR- SUBCONTRACTOR
%R | 502192 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3055 | Aluminum tile false ceiling | 8178 | 312 | 24 | 200 | 0 | 156.25 | 156.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | tnUnrkS3Si627/qtasSjhA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 78.125 | LABOR- SUBCONTRACTOR
%R | 502193 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3060 | Gypsum board false ceiling | 8178 | 288 | 0 | 200 | 0 | 1298.71 | 1298.71 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-02-04 08:00 | 2014-03-05 17:00 | 2014-02-04 08:00 | 2014-03-05 17:00 | 2014-02-04 08:00 | 2014-03-05 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | bPi7MpxxRRi0b7HJ9MSNiA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 649.355 | LABOR- SUBCONTRACTOR
%R | 502194 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3065 | Wooden door | 8178 | 320 | 0 | 120 | 0 | 412.5 | 412.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-13 08:00 | 2014-04-29 17:00 |  | 2014-02-25 08:00 | 2014-03-13 17:00 | 2014-02-25 08:00 | 2014-03-13 17:00 | 2014-02-25 08:00 | 2014-03-13 17:00 | 2014-04-13 08:00 | 2014-04-29 17:00 |  | PT_Normal |  |  |  |  | OkRWs58OTce7f1egwaVgVQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 412.5 | LABOR- SUBCONTRACTOR
%R | 502195 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3070 | Aluminum doors | 8178 | 320 | 0 | 120 | 0 | 99 | 99 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-19 08:00 | 2014-05-05 17:00 |  | 2014-03-03 08:00 | 2014-03-19 17:00 | 2014-03-03 08:00 | 2014-03-19 17:00 | 2014-03-03 08:00 | 2014-03-19 17:00 | 2014-04-19 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | 5FbY9hpqR3CoFbwmIv7OTQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 99 | LABOR- SUBCONTRACTOR
%R | 502196 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3080 | Aluminum windows | 8178 | 400 | 40 | 160 | 0 | 220 | 220 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-07 08:00 | 2014-05-29 17:00 |  | 2014-03-10 08:00 | 2014-04-01 17:00 | 2014-03-10 08:00 | 2014-04-01 17:00 | 2014-03-10 08:00 | 2014-04-01 17:00 | 2014-05-07 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | OexWbYSqQMiVDUHUu6Cgmg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 220 | LABOR- SUBCONTRACTOR
%R | 502197 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3075 | Carpentry & Joinery Works | 8178 | 320 | 0 | 160 | 0 | 792 | 792 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-24 08:00 | 2014-05-17 17:00 |  | 2014-03-09 08:00 | 2014-03-31 17:00 | 2014-03-09 08:00 | 2014-03-31 17:00 | 2014-03-09 08:00 | 2014-03-31 17:00 | 2014-04-24 08:00 | 2014-05-17 17:00 |  | PT_Normal |  |  |  |  | rrr6FXzBTuCig9VzKl1n5w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 792 | LABOR- SUBCONTRACTOR
%R | 502198 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3090 | Installation of Granite Counter Top | 8171 | 320 | 0 | 120 | 0 | 132 | 132 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-07 08:00 | 2014-05-24 17:00 |  | 2014-03-22 08:00 | 2014-04-07 17:00 | 2014-03-22 08:00 | 2014-04-07 17:00 | 2014-03-22 08:00 | 2014-04-07 17:00 | 2014-05-07 08:00 | 2014-05-24 17:00 |  | PT_Normal |  |  |  |  | Ls3s6Sa3SHWCz8p/KElH2Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 132 | GRANITE MASON SK
%R | 502199 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3085 | S.S.Balustrade | 8178 | 360 | 40 | 160 | 0 | 47.25 | 47.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-08 08:00 | 2014-05-31 17:00 |  | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-05-08 08:00 | 2014-05-31 17:00 |  | PT_Normal |  |  |  |  | LhGB7GhfSDeGNZ8C2XxIbw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 47.25 | LABOR- SUBCONTRACTOR
%R | 502200 | 6359 | 124848 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARGF3095 | Final Painting | 8178 | 320 | 0 | 200 | 0 | 4136.55 | 4136.55 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | bkUdV4+TQZi5+sn4HyxgcQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42100 | N | N | 10 | GROUND FLOOR |  | 124845 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 4136.55 | LABOR- SUBCONTRACTOR
%R | 502201 | 6359 | 124850 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARRF3630 | Leveling Screed for Waterproofing | 8164 | 496 | 0 | 200 | 0 | 734.75 | 734.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-05 08:00 | 2014-05-03 17:00 |  | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-04-05 08:00 | 2014-05-03 17:00 |  | PT_Normal |  |  |  |  | D62RlF7YQC2dN8QBUyOi4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42140 | N | N | 10 | ROOF |  | 124849 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 734.75 | SCREED MASON SK
%R | 502202 | 6359 | 124850 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARRF3635 | Laying of Waterproofing Membrane | 8178 | 496 | 0 | 200 | 0 | 2042.25 | 2042.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-08 08:00 | 2014-05-06 17:00 |  | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 |  | PT_Normal |  |  |  |  | ltoVXZGBT12gHAf4l8C2zg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42140 | N | N | 10 | ROOF |  | 124849 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 2042.25 | LABOR- SUBCONTRACTOR
%R | 502203 | 6359 | 124850 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARRF3640 | Installation of Insulation & Protection | 8178 | 496 | 0 | 200 | 0 | 1291.5 | 1291.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-13 08:00 | 2014-05-11 17:00 |  | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-04-13 08:00 | 2014-05-11 17:00 |  | PT_Normal |  |  |  |  | TyBFMljQR1at6qBU65ngWA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42140 | N | N | 10 | ROOF |  | 124849 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1291.5 | LABOR- SUBCONTRACTOR
%R | 502204 | 6359 | 124850 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 496 | 0 | 200 | 0 | 741.5 | 741.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | VX3ERW/3TU+p+rnx8IKbKQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42140 | N | N | 10 | ROOF |  | 124849 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 370.75 | TILE MASON SK
%R | 502205 | 6359 | 124850 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 496 | 0 | 160 | 0 | 231 | 231 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-06-02 17:00 |  | 2014-02-27 08:00 | 2014-03-22 17:00 | 2014-02-27 08:00 | 2014-03-22 17:00 | 2014-02-27 08:00 | 2014-03-22 17:00 | 2014-05-11 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | tEI7vwSdTkSIPj3mFgS79A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42140 | N | N | 10 | ROOF |  | 124849 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 231 | LABOR- SUBCONTRACTOR
%R | 502206 | 6359 | 124850 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 496 | 0 | 200 | 0 | 882 | 882 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-26 08:00 | 2014-05-24 17:00 |  | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 |  | PT_Normal |  |  |  |  | KSa0uY3xTIKO3v3iS4ZlYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42140 | N | N | 10 | ROOF |  | 124849 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 441 | LABOR- SUBCONTRACTOR
%R | 502207 | 6359 | 124850 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4ARRF3660 | Installation of Access Ladder | 8178 | 536 | 536 | 120 | 0 | 198 | 198 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-14 17:00 |  | 2014-03-11 08:00 | 2014-03-27 17:00 | 2014-03-11 08:00 | 2014-03-27 17:00 | 2014-03-11 08:00 | 2014-03-27 17:00 | 2014-05-28 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | Jwyd0hxTQdK1FahIkHoSNg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42140 | N | N | 10 | ROOF |  | 124849 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 198 | LABOR- SUBCONTRACTOR
%R | 502208 | 6359 | 124851 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4AREL3665 | External Plastering | 8169 | 424 | 0 | 200 | 0 | 9159.75 | 9159.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-21 08:00 | 2014-05-19 17:00 |  | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42150 | N | N | 15 | ELEVATION |  | 124849 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 4579.875 | PLASTER MASON SK
%R | 502209 | 6359 | 124851 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4AREL3675 | GRC Panel Works | 8178 | 440 | 0 | 160 | 0 | 550 | 550 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-06-02 17:00 |  | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-05-11 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | WnITZUxpRvato+RQMvF2nQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42150 | N | N | 15 | ELEVATION |  | 124849 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 550 | LABOR- SUBCONTRACTOR
%R | 502210 | 6359 | 124851 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4AREL3680 | External Painting | 8178 | 440 | 40 | 160 | 0 | 3234 | 3234 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-22 08:00 | 2014-06-14 17:00 |  | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-05-22 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | YvQY48J7RKq2K2ZeSva3LQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42150 | N | N | 15 | ELEVATION |  | 124849 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 3234 | LABOR- SUBCONTRACTOR
%R | 502211 | 6359 | 124853 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4MSEX5020 | Construction Entrance Ramp | 8164 | 168 | 0 | 200 | 0 | 216 | 216 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-28 17:00 |  | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | hFEcG3dATKCd687yJ24k7Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42310 | N | N | 10 | MISCELLANEOUS |  | 124852 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 216 | SCREED MASON SK
%R | 502212 | 6359 | 124853 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4MSEX5025 | SS.Handrails and Balustrades | 8178 | 168 | 0 | 160 | 0 | 108 | 108 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-10 17:00 |  | 2014-03-24 08:00 | 2014-04-15 17:00 | 2014-03-24 08:00 | 2014-04-15 17:00 | 2014-03-24 08:00 | 2014-04-15 17:00 | 2014-04-17 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42310 | N | N | 10 | MISCELLANEOUS |  | 124852 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 108 | LABOR- SUBCONTRACTOR
%R | 502213 | 6359 | 124853 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4MSEX5015 | Construction of grease Trap | 8178 | 376 | 0 | 160 | 0 | 42 | 42 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-02 08:00 | 2014-04-24 17:00 |  | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-04-02 08:00 | 2014-04-24 17:00 |  | PT_Normal |  |  |  |  | RcvPgMHyQLaX3JG+oXnW6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42310 | N | N | 10 | MISCELLANEOUS |  | 124852 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 42 | LABOR- SUBCONTRACTOR
%R | 502214 | 6359 | 124853 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4MSEX5000 | Construction of Manholes | 8178 | 376 | 0 | 200 | 0 | 132 | 132 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-27 08:00 | 2014-03-27 17:00 |  | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 |  | PT_Normal |  |  |  |  | 5GnsIwA+T5CeRe3dWPhtEA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42310 | N | N | 10 | MISCELLANEOUS |  | 124852 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 132 | LABOR- SUBCONTRACTOR
%R | 502215 | 6359 | 124853 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4MSEX5005 | Construction of Soak pit, Chambers | 8177 | 376 | 0 | 200 | 0 | 275 | 275 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-04-10 17:00 |  | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | xe+LON5ySu+zLCmEK7dpmw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42310 | N | N | 10 | MISCELLANEOUS |  | 124852 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 275 | LABOR - CIVIL
%R | 502216 | 6359 | 124853 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4MSEX5010 | Telephone cable laying | 8177 | 376 | 208 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-26 08:00 | 2014-05-24 17:00 |  | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 |  | PT_Normal |  |  |  |  | oCMYkqjqQRCBy18yncesnA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42310 | N | N | 10 | MISCELLANEOUS |  | 124852 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 500 | LABOR - CIVIL
%R | 502217 | 6359 | 124854 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4WTEX5030 | Excavation | 8177 | 464 | 0 | 160 | 0 | 116 | 116 | 160 | 80 | 0 | 80 |  |  |  | 2014-03-15 08:00 | 2014-04-06 17:00 |  | 2014-01-05 08:00 | 2014-01-27 17:00 | 2014-01-05 08:00 | 2014-01-27 17:00 | 2014-01-05 08:00 | 2014-01-27 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | 2HI2xwP4RY+6wWnVs+89pA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42320 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124852 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 116 | LABOR - CIVIL
%R | 502218 | 6359 | 124854 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4WTEX5035 | Construction of Raft | 8167 | 464 | 0 | 200 | 0 | 210 | 210 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-20 08:00 | 2014-04-17 17:00 |  | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 |  | PT_Normal |  |  |  |  | yuhyyprFRgSVyUBEYzEltA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42320 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124852 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 210 | CONCRETE MASON SK
%R | 502219 | 6359 | 124854 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4WTEX5040 | Block works & Plastering | 8168 | 464 | 0 | 200 | 0 | 2442 | 2442 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-30 08:00 | 2014-04-27 17:00 |  | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-03-30 08:00 | 2014-04-27 17:00 |  | PT_Normal |  |  |  |  | QtP7sGwSRqetYC8cJ5jFuA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42320 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124852 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 2442 | BLOCK MASON SK
%R | 502220 | 6359 | 124854 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4WTEX5045 | Flooring & Painting | 8164 | 464 | 296 | 200 | 0 | 900 | 900 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-10 17:00 |  | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | p5B9A/ZhRJamqV6lpGffeQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42320 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124852 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 450 | SCREED MASON SK
%R | 502221 | 6359 | 124854 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4WTEX5050 | Installation of Steel Gate | 8178 | 168 | 16 | 160 | 0 | 84 | 84 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-21 17:00 |  | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-04-29 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | uAdMM6+FSkqZCy7q+jtJgw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42320 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124852 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 84 | LABOR- SUBCONTRACTOR
%R | 502222 | 6359 | 124854 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4WTEX5060 | Structural steel & SS Shed cover installation | 8178 | 152 | 0 | 200 | 0 | 588 | 588 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-05 08:00 | 2014-06-02 17:00 |  | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-05-05 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | fjsGzH0gTGCTOOHkPVN8jg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42320 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124852 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 588 | LABOR- SUBCONTRACTOR
%R | 502223 | 6359 | 124854 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4WTEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 152 | 0 | 200 | 0 | 152.4 | 152.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | WbUfY7gwRm+o/ELs7zx9Yw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42320 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124852 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 152.4 | LABOR- SUBCONTRACTOR
%R | 502224 | 6359 | 124854 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4WTEX5080 | Domestic Water Tank Electrical works | 8178 | 464 | 0 | 200 | 0 | 175 | 175 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-07 08:00 | 2014-05-05 17:00 |  | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | fWPLSlUbQfmNz01PAvZsgw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42320 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124852 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 175 | LABOR- SUBCONTRACTOR
%R | 502225 | 6359 | 124854 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4WTEX5070 | Domestic Water Tank Plumbings works | 8178 | 464 | 0 | 200 | 0 | 200 | 200 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-07 08:00 | 2014-05-05 17:00 |  | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | wLFvZCtwQmmR+a7vI0CcjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42320 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124852 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 200 | LABOR- SUBCONTRACTOR
%R | 502226 | 6359 | 124854 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4WTEX5075 | Domestic Water Tank AC works | 8178 | 464 | 0 | 200 | 0 | 175 | 175 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-07 08:00 | 2014-05-05 17:00 |  | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | 6xeW+SpZTOaSKWaiDYS5mQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42320 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124852 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 175 | LABOR- SUBCONTRACTOR
%R | 502227 | 6359 | 124854 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4WTEX5085 | Domestic Water Tank Firefighting works | 8178 | 464 | 0 | 200 | 0 | 118.8 | 118.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-07 08:00 | 2014-05-05 17:00 |  | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | AX5U7h8ZTm2NazsyeyQIAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42320 | N | N | 15 | DOMESTIC WATER TANK & PUMP ROOM |  | 124852 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 118.8 | LABOR- SUBCONTRACTOR
%R | 502228 | 6359 | 124857 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STUG1000 | Footing Excavation | 8177 | 0 | 0 | 200 | 0 | 1556 | 1556 | 200 | 732 | 0 | 732 |  |  |  | 2013-04-28 08:00 | 2013-05-26 17:00 |  | 2013-04-28 08:00 | 2013-05-26 17:00 | 2013-04-28 08:00 | 2013-05-26 17:00 | 2013-04-28 08:00 | 2013-05-26 17:00 | 2013-04-28 08:00 | 2013-05-26 17:00 |  | PT_Normal |  |  |  |  | XIwQ4QsDSCGq81Vb/W6ECw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42030 | N | N | 10 | UPTO GRADE SLAB |  | 124856 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 1556 | LABOR - CIVIL
%R | 502229 | 6359 | 124857 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STUG1005 | Footing Antitermite | 8178 | 0 | 0 | 184 | 0 | 634.25 | 634.25 | 184 | 0 | 0 | 0 |  |  |  | 2013-05-08 08:00 | 2013-06-03 17:00 |  | 2013-05-08 08:00 | 2013-06-03 17:00 | 2013-05-08 08:00 | 2013-06-03 17:00 | 2013-05-08 08:00 | 2013-06-03 17:00 | 2013-05-08 08:00 | 2013-06-03 17:00 |  | PT_Normal |  |  |  |  | YPZweAh+ThSDjMlpjZZ9YQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42030 | N | N | 10 | UPTO GRADE SLAB |  | 124856 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 634.25 | LABOR- SUBCONTRACTOR
%R | 502230 | 6359 | 124857 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STUG1010 | Footing Blinding | 8163 | 0 | 0 | 184 | 0 | 588 | 588 | 184 | 0 | 0 | 0 |  |  |  | 2013-05-12 08:00 | 2013-06-06 17:00 |  | 2013-05-12 08:00 | 2013-06-06 17:00 | 2013-05-12 08:00 | 2013-06-06 17:00 | 2013-05-12 08:00 | 2013-06-06 17:00 | 2013-05-12 08:00 | 2013-06-06 17:00 |  | PT_Normal |  |  |  |  | UUz5hjJJReG+EJBQ0STVhg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42030 | N | N | 10 | UPTO GRADE SLAB |  | 124856 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 588 | BLINDING MASON SK
%R | 502231 | 6359 | 124857 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STUG1015 | Footing Waterproofing & Screed | 8164 | 0 | 0 | 200 | 0 | 1368.5 | 1368.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-05-18 08:00 | 2013-06-15 17:00 |  | 2013-05-18 08:00 | 2013-06-15 17:00 | 2013-05-18 08:00 | 2013-06-15 17:00 | 2013-05-18 08:00 | 2013-06-15 17:00 | 2013-05-18 08:00 | 2013-06-15 17:00 |  | PT_Normal |  |  |  |  | Q8Tb0pBxQ/KdcXua813h8g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42030 | N | N | 10 | UPTO GRADE SLAB |  | 124856 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 1368.5 | SCREED MASON SK
%R | 502232 | 6359 | 124857 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STUG1020 | Construction of foundations | 8165 | 0 | 0 | 160 | 0 | 4817.75 | 4817.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-06-02 08:00 | 2013-06-24 17:00 |  | 2013-06-02 08:00 | 2013-06-24 17:00 | 2013-06-02 08:00 | 2013-06-24 17:00 | 2013-06-02 08:00 | 2013-06-24 17:00 | 2013-06-02 08:00 | 2013-06-24 17:00 |  | PT_Normal |  |  |  |  | nRxKNF9RTVasX9RoXmqFQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42030 | N | N | 10 | UPTO GRADE SLAB |  | 124856 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 4817.75 | STEEL FIXERS SK
%R | 502233 | 6359 | 124857 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STUG1025 | Construction of neck of columns | 8165 | 0 | 0 | 200 | 0 | 1400 | 1400 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-11 08:00 | 2013-07-09 17:00 |  | 2013-06-11 08:00 | 2013-07-09 17:00 | 2013-06-11 08:00 | 2013-07-09 17:00 | 2013-06-11 08:00 | 2013-07-09 17:00 | 2013-06-11 08:00 | 2013-07-09 17:00 |  | PT_Normal |  |  |  |  | XRPr2WBtRuCx9ksLtt5KeQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42030 | N | N | 10 | UPTO GRADE SLAB |  | 124856 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 1400 | STEEL FIXERS SK
%R | 502234 | 6359 | 124857 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STUG1030 | Waterproofing Footing & Neck Column | 8178 | 0 | 0 | 200 | 0 | 213.5 | 213.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-20 08:00 | 2013-07-18 17:00 |  | 2013-06-20 08:00 | 2013-07-18 17:00 | 2013-06-20 08:00 | 2013-07-18 17:00 | 2013-06-20 08:00 | 2013-07-18 17:00 | 2013-06-20 08:00 | 2013-07-18 17:00 |  | PT_Normal |  |  |  |  | +imy/8c2TVeYFVxAui1nmQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42030 | N | N | 10 | UPTO GRADE SLAB |  | 124856 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 213.5 | LABOR- SUBCONTRACTOR
%R | 502235 | 6359 | 124857 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 0 | 0 | 200 | 0 | 2560 | 2560 | 200 | 2200 | 0 | 2200 |  |  |  | 2013-07-01 08:00 | 2013-07-29 17:00 |  | 2013-07-01 08:00 | 2013-07-29 17:00 | 2013-07-01 08:00 | 2013-07-29 17:00 | 2013-07-01 08:00 | 2013-07-29 17:00 | 2013-07-01 08:00 | 2013-07-29 17:00 |  | PT_Normal |  |  |  |  | czI/ZhIZTdqwznGeLORjqw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42030 | N | N | 10 | UPTO GRADE SLAB |  | 124856 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 2560 | LABOR - CIVIL
%R | 502236 | 6359 | 124857 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STUG1040 | Construction of Grade Beams | 8163 | 0 | 0 | 200 | 0 | 4745 | 4745 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-17 08:00 | 2013-08-18 17:00 |  | 2013-07-17 08:00 | 2013-08-18 17:00 | 2013-07-17 08:00 | 2013-08-18 17:00 | 2013-07-17 08:00 | 2013-08-18 17:00 | 2013-07-17 08:00 | 2013-08-18 17:00 |  | PT_Normal |  |  |  |  | Bn9peGwNSAG2xB7XJlMSJA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42030 | N | N | 10 | UPTO GRADE SLAB |  | 124856 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 2372.5 | BLINDING MASON SK
%R | 502237 | 6359 | 124857 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STUG1045 | Construction of slab on grade | 8163 | 0 | 0 | 200 | 0 | 3327.5 | 3327.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-17 08:00 | 2013-09-14 17:00 |  | 2013-08-17 08:00 | 2013-09-14 17:00 | 2013-08-17 08:00 | 2013-09-14 17:00 | 2013-08-17 08:00 | 2013-09-14 17:00 | 2013-08-17 08:00 | 2013-09-14 17:00 |  | PT_Normal |  |  |  |  | VzsoV3WETYuZxhrk4N8gzg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42030 | N | N | 10 | UPTO GRADE SLAB |  | 124856 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 3327.5 | BLINDING MASON SK
%R | 502238 | 6359 | 124859 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STFF2020 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 1615.25 | 1615.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-14 08:00 | 2013-11-13 17:00 |  | 2013-10-14 08:00 | 2013-11-13 17:00 | 2013-10-14 08:00 | 2013-11-13 17:00 | 2013-10-14 08:00 | 2013-11-13 17:00 | 2013-10-14 08:00 | 2013-11-13 17:00 |  | PT_Normal |  |  |  |  | kum8pk0mSVWqyIZbsQhKnw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42060 | N | N | 15 | FIRST FLOORS |  | 124858 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1615.25 | STEEL FIXERS SK
%R | 502239 | 6359 | 124859 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STFF2025 | Column-Concrete | 8167 | 0 | 0 | 192 | 0 | 87.5 | 87.5 | 192 | 0 | 0 | 0 |  |  |  | 2013-10-27 08:00 | 2013-11-23 17:00 |  | 2013-10-27 08:00 | 2013-11-23 17:00 | 2013-10-27 08:00 | 2013-11-23 17:00 | 2013-10-27 08:00 | 2013-11-23 17:00 | 2013-10-27 08:00 | 2013-11-23 17:00 |  | PT_Normal |  |  |  |  | njVkx7a8RRmPadMypVW9DA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42060 | N | N | 15 | FIRST FLOORS |  | 124858 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 87.5 | CONCRETE MASON SK
%R | 502240 | 6359 | 124859 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 10081.75 | 10081.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-11 08:00 | 2013-12-09 17:00 |  | 2013-11-11 08:00 | 2013-12-09 17:00 | 2013-11-11 08:00 | 2013-12-09 17:00 | 2013-11-11 08:00 | 2013-12-09 17:00 | 2013-11-11 08:00 | 2013-12-09 17:00 |  | PT_Normal |  |  |  |  | RMfQiI7WSMyR5VY6p3rgLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42060 | N | N | 15 | FIRST FLOORS |  | 124858 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 10081.75 | STEEL FIXERS SK
%R | 502241 | 6359 | 124859 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 0 | 0 | 120 | 0 | 731.5 | 731.5 | 120 | 0 | 0 | 0 |  |  |  | 2013-12-02 08:00 | 2013-12-19 17:00 |  | 2013-12-02 08:00 | 2013-12-19 17:00 | 2013-12-02 08:00 | 2013-12-19 17:00 | 2013-12-02 08:00 | 2013-12-19 17:00 | 2013-12-02 08:00 | 2013-12-19 17:00 |  | PT_Normal |  |  |  |  | 0VmJ/UySTWGvhB2lNqb75g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42060 | N | N | 15 | FIRST FLOORS |  | 124858 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 731.5 | CONCRETE MASON SK
%R | 502242 | 6359 | 124860 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STRF2045 | Column-Concrete | 8167 | 216 | 0 | 136 | 0 | 21 | 21 | 136 | 0 | 0 | 0 |  |  |  | 2014-01-09 08:00 | 2014-01-28 17:00 |  | 2013-12-08 08:00 | 2013-12-28 17:00 | 2013-12-08 08:00 | 2013-12-28 17:00 | 2013-12-08 08:00 | 2013-12-28 17:00 | 2014-01-09 08:00 | 2014-01-28 17:00 |  | PT_Normal |  |  |  |  | o6t+iQnpTImfkPh8tpe1LA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42070 | N | N | 20 | ROOF |  | 124858 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 21 | CONCRETE MASON SK
%R | 502243 | 6359 | 124860 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STRF2050 | Slab-Rebar & Formwork | 8165 | 216 | 0 | 160 | 0 | 1576.75 | 1576.75 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-12 08:00 | 2014-02-03 17:00 |  | 2013-12-10 08:00 | 2014-01-02 17:00 | 2013-12-10 08:00 | 2014-01-02 17:00 | 2013-12-10 08:00 | 2014-01-02 17:00 | 2014-01-12 08:00 | 2014-02-03 17:00 |  | PT_Normal |  |  |  |  | bXFwD6FrTrqF4SQvY61RoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42070 | N | N | 20 | ROOF |  | 124858 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1576.75 | STEEL FIXERS SK
%R | 502244 | 6359 | 124860 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STRF2055 | Slab-Concrete | 8167 | 216 | 0 | 104 | 0 | 175 | 175 | 104 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-05 17:00 |  | 2013-12-22 08:00 | 2014-01-05 17:00 | 2013-12-22 08:00 | 2014-01-05 17:00 | 2013-12-22 08:00 | 2014-01-05 17:00 | 2014-01-22 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | sikTZMWKRj+CzzlUq/SIkQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42070 | N | N | 20 | ROOF |  | 124858 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 175 | CONCRETE MASON SK
%R | 502245 | 6359 | 124860 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STRF2060 | Construction of Parapets | 8168 | 464 | 0 | 200 | 0 | 1441 | 1441 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-03 08:00 | 2014-03-31 17:00 |  | 2013-12-24 08:00 | 2014-01-21 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | uGQUZ8SqR9qCtREhhwh55A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42070 | N | N | 20 | ROOF |  | 124858 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1441 | BLOCK MASON SK
%R | 502246 | 6359 | 124860 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STRF2065 | Construction of up stands/Plinth | 8165 | 464 | 0 | 200 | 0 | 283.5 | 283.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-04-06 17:00 |  | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | JtFq+iGsTt+axBACtuoa+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42070 | N | N | 20 | ROOF |  | 124858 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 283.5 | STEEL FIXERS SK
%R | 502247 | 6359 | 124860 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STRF2040 | Column-Rebar & Formwork | 8165 | 176 | 0 | 144 | 0 | 549.5 | 549.5 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-31 08:00 | 2014-01-20 17:00 |  | 2013-12-04 08:00 | 2013-12-25 17:00 | 2013-12-04 08:00 | 2013-12-25 17:00 | 2013-12-04 08:00 | 2013-12-25 17:00 | 2013-12-31 08:00 | 2014-01-20 17:00 |  | PT_Normal |  |  |  |  | li0MlXZcQK2Yo9RRPlu0vw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42070 | N | N | 20 | ROOF |  | 124858 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 549.5 | STEEL FIXERS SK
%R | 502248 | 6359 | 124861 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STGF2000 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 1688.75 | 1688.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-02 08:00 | 2013-09-30 17:00 |  | 2013-09-02 08:00 | 2013-09-30 17:00 | 2013-09-02 08:00 | 2013-09-30 17:00 | 2013-09-02 08:00 | 2013-09-30 17:00 | 2013-09-02 08:00 | 2013-09-30 17:00 |  | PT_Normal |  |  |  |  | hW1vzVs9Q5ifMgefyO7Ufg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42050 | N | N | 10 | GROUND FLOOR |  | 124858 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1688.75 | STEEL FIXERS SK
%R | 502249 | 6359 | 124861 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STGF2005 | Column-Concrete | 8167 | 0 | 0 | 192 | 0 | 101.5 | 101.5 | 192 | 0 | 0 | 0 |  |  |  | 2013-09-11 08:00 | 2013-10-08 17:00 |  | 2013-09-11 08:00 | 2013-10-08 17:00 | 2013-09-11 08:00 | 2013-10-08 17:00 | 2013-09-11 08:00 | 2013-10-08 17:00 | 2013-09-11 08:00 | 2013-10-08 17:00 |  | PT_Normal |  |  |  |  | gFWsl/lkQteKUX+URHItJw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42050 | N | N | 10 | GROUND FLOOR |  | 124858 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 101.5 | CONCRETE MASON SK
%R | 502250 | 6359 | 124861 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 10592.75 | 10592.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-26 08:00 | 2013-10-27 17:00 |  | 2013-09-26 08:00 | 2013-10-27 17:00 | 2013-09-26 08:00 | 2013-10-27 17:00 | 2013-09-26 08:00 | 2013-10-27 17:00 | 2013-09-26 08:00 | 2013-10-27 17:00 |  | PT_Normal |  |  |  |  | sfVZDJsWQyerUvAoXlxPfg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42050 | N | N | 10 | GROUND FLOOR |  | 124858 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 5296.375 | STEEL FIXERS SK
%R | 502251 | 6359 | 124861 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03Z4STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 0 | 0 | 120 | 0 | 868 | 868 | 120 | 0 | 0 | 0 |  |  |  | 2013-10-12 08:00 | 2013-10-30 17:00 |  | 2013-10-12 08:00 | 2013-10-30 17:00 | 2013-10-12 08:00 | 2013-10-30 17:00 | 2013-10-12 08:00 | 2013-10-30 17:00 | 2013-10-12 08:00 | 2013-10-30 17:00 |  | PT_Normal |  |  |  |  | SgUD/6cfTFagr+eK0mmg8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42050 | N | N | 10 | GROUND FLOOR |  | 124858 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 868 | CONCRETE MASON SK
%R | 502252 | 6359 | 124864 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKMSEX5020 | Construction Entrance Ramp | 8164 | 152 | 0 | 56 | 0 | 30 | 30 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-22 08:00 | 2013-12-29 17:00 |  | 2013-11-28 08:00 | 2013-12-05 17:00 | 2013-11-28 08:00 | 2013-12-05 17:00 | 2013-11-28 08:00 | 2013-12-05 17:00 | 2013-12-22 08:00 | 2013-12-29 17:00 |  | PT_Normal |  |  |  |  | XPQ9wn15T0WcpPzFx7jvDg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40870 | N | N | 10 | MISCELLANEOUS |  | 124863 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 30 | SCREED MASON SK
%R | 502253 | 6359 | 124864 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKMSEX5025 | SS.Handrails and Balustrades | 8178 | 248 | 96 | 40 | 0 | 14 | 14 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-01-18 17:00 |  | 2013-12-07 08:00 | 2013-12-11 17:00 | 2013-12-07 08:00 | 2013-12-11 17:00 | 2013-12-07 08:00 | 2013-12-11 17:00 | 2014-01-13 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | wTS+ksYJT2yI4ulrZ7hOQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40870 | N | N | 10 | MISCELLANEOUS |  | 124863 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 14 | LABOR- SUBCONTRACTOR
%R | 502254 | 6359 | 124864 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKMSEX5015 | Construction of grease Trap |  | 432 | 120 | 56 | 0 | 0 | 0 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-03 08:00 | 2014-02-10 17:00 |  | 2013-12-01 08:00 | 2013-12-08 17:00 | 2013-12-01 08:00 | 2013-12-08 17:00 | 2013-12-01 08:00 | 2013-12-08 17:00 | 2014-02-03 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | xCUTkmB5SqqwfxIao0clZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 40870 | N | N | 10 | MISCELLANEOUS |  | 124863 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 0 | 0
%R | 502255 | 6359 | 124864 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKMSEX5000 | Construction of Manholes | 8178 | 24 | 0 | 56 | 0 | 14 | 14 | 56 | 0 | 0 | 0 |  |  |  | 2013-11-18 08:00 | 2013-11-25 17:00 |  | 2013-11-14 08:00 | 2013-11-21 17:00 | 2013-11-14 08:00 | 2013-11-21 17:00 | 2013-11-14 08:00 | 2013-11-21 17:00 | 2013-11-18 08:00 | 2013-11-25 17:00 |  | PT_Normal |  |  |  |  | gmcyZW1oQzefndyPSS5c7w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40870 | N | N | 10 | MISCELLANEOUS |  | 124863 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 14 | LABOR- SUBCONTRACTOR
%R | 502256 | 6359 | 124864 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKMSEX5005 | Construction of Soak pit, Chambers | 8172 | 184 | 0 | 56 | 0 | 275 | 275 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-21 08:00 | 2013-12-28 17:00 |  | 2013-11-23 08:00 | 2013-11-30 17:00 | 2013-11-23 08:00 | 2013-11-30 17:00 | 2013-11-23 08:00 | 2013-11-30 17:00 | 2013-12-21 08:00 | 2013-12-28 17:00 |  | PT_Normal |  |  |  |  | fODsgiv2THSKuqWjkt80ZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40870 | N | N | 10 | MISCELLANEOUS |  | 124863 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 275 | MANHOLES SK
%R | 502257 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3000 | Block work | 8168 | 280 | 0 | 48 | 0 | 2372.25 | 2372.25 | 48 | 0 | 0 | 0 |  |  |  | 2013-09-19 08:00 | 2013-09-25 17:00 |  | 2013-08-06 08:00 | 2013-08-15 17:00 | 2013-08-06 08:00 | 2013-08-15 17:00 | 2013-08-06 08:00 | 2013-08-15 17:00 | 2013-09-19 08:00 | 2013-09-25 17:00 |  | PT_Normal |  |  |  |  | sLq82hOgRoqIK05jnD6Quw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 2372.25 | BLOCK MASON SK
%R | 502258 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3005 | Plastering work | 8169 | 336 | 0 | 56 | 0 | 2091 | 2091 | 56 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2013-10-20 17:00 |  | 2013-08-22 08:00 | 2013-08-29 17:00 | 2013-08-22 08:00 | 2013-08-29 17:00 | 2013-08-22 08:00 | 2013-08-29 17:00 | 2013-10-10 08:00 | 2013-10-20 17:00 |  | PT_Normal |  |  |  |  | xJa2kUV/QVqKZ4X2cFZxqA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 2091 | PLASTER MASON SK
%R | 502259 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3010 | Flooring screed | 8164 | 408 | 0 | 56 | 0 | 412.5 | 412.5 | 56 | 0 | 0 | 0 |  |  |  | 2013-10-27 08:00 | 2013-11-03 17:00 |  | 2013-08-26 08:00 | 2013-09-02 17:00 | 2013-08-26 08:00 | 2013-09-02 17:00 | 2013-08-26 08:00 | 2013-09-02 17:00 | 2013-10-27 08:00 | 2013-11-03 17:00 |  | PT_Normal |  |  |  |  | D0wZ8pq/RYiRis2rMCbt1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 412.5 | SCREED MASON SK
%R | 502260 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 408 | 0 | 40 | 0 | 194.25 | 194.25 | 40 | 0 | 0 | 0 |  |  |  | 2013-10-30 08:00 | 2013-11-04 17:00 |  | 2013-08-29 08:00 | 2013-09-03 17:00 | 2013-08-29 08:00 | 2013-09-03 17:00 | 2013-08-29 08:00 | 2013-09-03 17:00 | 2013-10-30 08:00 | 2013-11-04 17:00 |  | PT_Normal |  |  |  |  | 2C+X1bNlQUOZz8um+PEZWQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 194.25 | LABOR- SUBCONTRACTOR
%R | 502261 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3030 | Paint First coat | 8178 | 344 | 0 | 40 | 0 | 1378.85 | 1378.85 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-17 08:00 | 2013-11-21 17:00 |  | 2013-09-25 08:00 | 2013-09-30 17:00 | 2013-09-25 08:00 | 2013-09-30 17:00 | 2013-09-25 08:00 | 2013-09-30 17:00 | 2013-11-17 08:00 | 2013-11-21 17:00 |  | PT_Normal |  |  |  |  | vKORmcg5SZuM8SrObnSglw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1378.85 | LABOR- SUBCONTRACTOR
%R | 502262 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3020 | Ceramic Wall Tiling | 8170 | 408 | 0 | 48 | 0 | 868.75 | 868.75 | 48 | 0 | 0 | 0 |  |  |  | 2013-11-05 08:00 | 2013-11-11 17:00 |  | 2013-09-04 08:00 | 2013-09-10 17:00 | 2013-09-04 08:00 | 2013-09-10 17:00 | 2013-09-04 08:00 | 2013-09-10 17:00 | 2013-11-05 08:00 | 2013-11-11 17:00 |  | PT_Normal |  |  |  |  | tWHRKt0BSwWe2uY9PeHD+Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 868.75 | TILE MASON SK
%R | 502263 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3025 | Porcelain Tile flooring | 8170 | 408 | 0 | 48 | 0 | 597.25 | 597.25 | 48 | 0 | 0 | 0 |  |  |  | 2013-11-12 08:00 | 2013-11-18 17:00 |  | 2013-09-11 08:00 | 2013-09-17 17:00 | 2013-09-11 08:00 | 2013-09-17 17:00 | 2013-09-11 08:00 | 2013-09-17 17:00 | 2013-11-12 08:00 | 2013-11-18 17:00 |  | PT_Normal |  |  |  |  | pLc7M2jFRLCsJ6W93dT6rQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 597.25 | TILE MASON SK
%R | 502264 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3040 | Cobble Tile flooring | 8170 | 520 | 0 | 40 | 0 | 24 | 24 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-05 08:00 | 2013-12-10 17:00 |  | 2013-09-18 08:00 | 2013-09-23 17:00 | 2013-09-18 08:00 | 2013-09-23 17:00 | 2013-09-18 08:00 | 2013-09-23 17:00 | 2013-12-05 08:00 | 2013-12-10 17:00 |  | PT_Normal |  |  |  |  | TXOoqFWYSkCwGlQFYIJCcg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 24 | TILE MASON SK
%R | 502265 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3035 | Slate Tile Flooring & Skirting | 8170 | 520 | 184 | 40 | 0 | 16 | 16 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-11 08:00 | 2013-12-16 17:00 |  | 2013-09-24 08:00 | 2013-09-29 17:00 | 2013-09-24 08:00 | 2013-09-29 17:00 | 2013-09-24 08:00 | 2013-09-29 17:00 | 2013-12-11 08:00 | 2013-12-16 17:00 |  | PT_Normal |  |  |  |  | N3W/UaSqRxmBnfurYBwV2Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 16 | TILE MASON SK
%R | 502266 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 432 | 0 | 56 | 0 | 168.75 | 168.75 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-23 08:00 | 2013-12-30 17:00 |  | 2013-10-20 08:00 | 2013-10-27 17:00 | 2013-10-20 08:00 | 2013-10-27 17:00 | 2013-10-20 08:00 | 2013-10-27 17:00 | 2013-12-23 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | ppHc/wAOR2GhzsZpo2ziyQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 168.75 | GRANITE MASON SK
%R | 502267 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3045 | Fixing of Suspension systems | 8178 | 384 | 0 | 56 | 0 | 478.5 | 478.5 | 56 | 0 | 0 | 0 |  |  |  | 2013-11-28 08:00 | 2013-12-05 17:00 |  | 2013-10-01 08:00 | 2013-10-08 17:00 | 2013-10-01 08:00 | 2013-10-08 17:00 | 2013-10-01 08:00 | 2013-10-08 17:00 | 2013-11-28 08:00 | 2013-12-05 17:00 |  | PT_Normal |  |  |  |  | Z3LYDwiiRxa2CJ9KQmjA6w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 478.5 | LABOR- SUBCONTRACTOR
%R | 502268 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3055 | Aluminum tile false ceiling | 8178 | 360 | 0 | 56 | 0 | 51.95 | 51.95 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-11 08:00 | 2013-12-19 17:00 |  | 2013-10-20 08:00 | 2013-10-27 17:00 | 2013-10-20 08:00 | 2013-10-27 17:00 | 2013-10-20 08:00 | 2013-10-27 17:00 | 2013-12-11 08:00 | 2013-12-19 17:00 |  | PT_Normal |  |  |  |  | f7wVPrQORwON45I6HOiZZg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 51.95 | LABOR- SUBCONTRACTOR
%R | 502269 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3060 | Gypsum board false ceiling | 8178 | 408 | 56 | 56 | 0 | 433 | 433 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-10 08:00 | 2013-12-17 17:00 |  | 2013-10-09 08:00 | 2013-10-16 17:00 | 2013-10-09 08:00 | 2013-10-16 17:00 | 2013-10-09 08:00 | 2013-10-16 17:00 | 2013-12-10 08:00 | 2013-12-17 17:00 |  | PT_Normal |  |  |  |  | KOeYi0hgQdC6zk2/ezQkGQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 433 | LABOR- SUBCONTRACTOR
%R | 502270 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3065 | Wooden door | 8178 | 448 | 0 | 40 | 0 | 137.5 | 137.5 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-02 08:00 | 2014-01-07 17:00 |  | 2013-10-28 08:00 | 2013-11-02 17:00 | 2013-10-28 08:00 | 2013-11-02 17:00 | 2013-10-28 08:00 | 2013-11-02 17:00 | 2014-01-02 08:00 | 2014-01-07 17:00 |  | PT_Normal |  |  |  |  | rg/NUgOKTY6NrS3ubLyZ5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 137.5 | LABOR- SUBCONTRACTOR
%R | 502271 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3070 | Aluminum doors | 8178 | 448 | 0 | 40 | 0 | 33 | 33 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-08 08:00 | 2014-01-13 17:00 |  | 2013-11-03 08:00 | 2013-11-07 17:00 | 2013-11-03 08:00 | 2013-11-07 17:00 | 2013-11-03 08:00 | 2013-11-07 17:00 | 2014-01-08 08:00 | 2014-01-13 17:00 |  | PT_Normal |  |  |  |  | cXjwmSkiSjW7zpicjaIrDQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 33 | LABOR- SUBCONTRACTOR
%R | 502272 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3080 | Aluminum windows | 8178 | 576 | 120 | 40 | 0 | 74.25 | 74.25 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-02 08:00 | 2014-02-06 17:00 |  | 2013-11-09 08:00 | 2013-11-13 17:00 | 2013-11-09 08:00 | 2013-11-13 17:00 | 2013-11-09 08:00 | 2013-11-13 17:00 | 2014-02-02 08:00 | 2014-02-06 17:00 |  | PT_Normal |  |  |  |  | eTmNS/ceS8ucsAGPj5DXJw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 74.25 | LABOR- SUBCONTRACTOR
%R | 502273 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3075 | Carpentry & Joinery Works | 8178 | 424 | 0 | 80 | 0 | 264 | 264 | 80 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-01-25 17:00 |  | 2013-11-12 08:00 | 2013-11-23 17:00 | 2013-11-12 08:00 | 2013-11-23 17:00 | 2013-11-12 08:00 | 2013-11-23 17:00 | 2014-01-14 08:00 | 2014-01-25 17:00 |  | PT_Normal |  |  |  |  | t2XYCM1eQQK6+rbswwoVMQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 264 | LABOR- SUBCONTRACTOR
%R | 502274 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3090 | Installation of Granite Counter Top | 8171 | 456 | 0 | 56 | 0 | 44 | 44 | 56 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-02-06 17:00 |  | 2013-11-24 08:00 | 2013-12-01 17:00 | 2013-11-24 08:00 | 2013-12-01 17:00 | 2013-11-24 08:00 | 2013-12-01 17:00 | 2014-01-30 08:00 | 2014-02-06 17:00 |  | PT_Normal |  |  |  |  | UTv0YvibTyu0zD+ncSm44A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 44 | GRANITE MASON SK
%R | 502275 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3085 | S.S.Handrails & Balustrade | 8178 | 464 | 0 | 56 | 0 | 16 | 16 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-01 08:00 | 2014-02-08 17:00 |  | 2013-11-24 08:00 | 2013-12-01 17:00 | 2013-11-24 08:00 | 2013-12-01 17:00 | 2013-11-24 08:00 | 2013-12-01 17:00 | 2014-02-01 08:00 | 2014-02-08 17:00 |  | PT_Normal |  |  |  |  | 46j4fMmGSjGIr+C9rO3u6w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 16 | LABOR- SUBCONTRACTOR
%R | 502276 | 6359 | 124867 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARGF3095 | Final Painting | 8178 | 464 | 144 | 56 | 0 | 1378.85 | 1378.85 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-02-17 17:00 |  | 2013-12-02 08:00 | 2013-12-09 17:00 | 2013-12-02 08:00 | 2013-12-09 17:00 | 2013-12-02 08:00 | 2013-12-09 17:00 | 2014-02-09 08:00 | 2014-02-17 17:00 |  | PT_Normal |  |  |  |  | gB4wNJvDQkapJ7kHVC3cqA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40670 | N | N | 10 | GROUND FLOOR |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1378.85 | LABOR- SUBCONTRACTOR
%R | 502277 | 6359 | 124868 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARFF3300 | Block work | 8168 | 0 | 0 | 48 | 0 | 1850 | 1850 | 48 | 0 | 0 | 0 |  |  |  | 2013-09-22 08:00 | 2013-09-28 17:00 |  | 2013-09-22 08:00 | 2013-09-28 17:00 | 2013-09-22 08:00 | 2013-09-28 17:00 | 2013-09-22 08:00 | 2013-09-28 17:00 | 2013-09-22 08:00 | 2013-09-28 17:00 |  | PT_Normal |  |  |  |  | 423C9x7HRK+TLTPDGHTSUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40680 | N | N | 15 | FIRST FLOORS |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1850 | BLOCK MASON SK
%R | 502278 | 6359 | 124868 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARFF3305 | Plastering work | 8169 | 64 | 0 | 56 | 0 | 1837.5 | 1837.5 | 56 | 0 | 0 | 0 |  |  |  | 2013-10-14 08:00 | 2013-10-23 17:00 |  | 2013-10-05 08:00 | 2013-10-12 17:00 | 2013-10-05 08:00 | 2013-10-12 17:00 | 2013-10-05 08:00 | 2013-10-12 17:00 | 2013-10-14 08:00 | 2013-10-23 17:00 |  | PT_Normal |  |  |  |  | ejm2BGUHSWyuk07X5VGXGA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40680 | N | N | 15 | FIRST FLOORS |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1837.5 | PLASTER MASON SK
%R | 502279 | 6359 | 124868 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARFF3310 | Flooring screed | 8164 | 176 | 0 | 56 | 0 | 343.75 | 343.75 | 56 | 0 | 0 | 0 |  |  |  | 2013-11-05 08:00 | 2013-11-12 17:00 |  | 2013-10-08 08:00 | 2013-10-15 17:00 | 2013-10-08 08:00 | 2013-10-15 17:00 | 2013-10-08 08:00 | 2013-10-15 17:00 | 2013-11-05 08:00 | 2013-11-12 17:00 |  | PT_Normal |  |  |  |  | xrcrZPIJSR2eOmrdBMm9ZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40680 | N | N | 15 | FIRST FLOORS |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 343.75 | SCREED MASON SK
%R | 502280 | 6359 | 124868 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARFF3315 | Wet area waterproofing & Protection Screed | 8178 | 176 | 0 | 40 | 0 | 194.25 | 194.25 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-09 08:00 | 2013-11-13 17:00 |  | 2013-10-12 08:00 | 2013-10-16 17:00 | 2013-10-12 08:00 | 2013-10-16 17:00 | 2013-10-12 08:00 | 2013-10-16 17:00 | 2013-11-09 08:00 | 2013-11-13 17:00 |  | PT_Normal |  |  |  |  | nutWWgmzS4+6E9Fpsgw+vg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40680 | N | N | 15 | FIRST FLOORS |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 194.25 | LABOR- SUBCONTRACTOR
%R | 502281 | 6359 | 124868 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARFF3330 | Paint First coat | 8178 | 224 | 32 | 40 | 0 | 1436 | 1436 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-25 08:00 | 2013-11-30 17:00 |  | 2013-10-23 08:00 | 2013-10-28 17:00 | 2013-10-23 08:00 | 2013-10-28 17:00 | 2013-10-23 08:00 | 2013-10-28 17:00 | 2013-11-25 08:00 | 2013-11-30 17:00 |  | PT_Normal |  |  |  |  | s7v9is3BRuWE6JWJvfTaQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40680 | N | N | 15 | FIRST FLOORS |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1436 | LABOR- SUBCONTRACTOR
%R | 502282 | 6359 | 124868 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARFF3320 | Ceramic Wall Tiling | 8170 | 192 | 0 | 48 | 0 | 868.75 | 868.75 | 48 | 0 | 0 | 0 |  |  |  | 2013-11-17 08:00 | 2013-11-23 17:00 |  | 2013-10-20 08:00 | 2013-10-26 17:00 | 2013-10-20 08:00 | 2013-10-26 17:00 | 2013-10-20 08:00 | 2013-10-26 17:00 | 2013-11-17 08:00 | 2013-11-23 17:00 |  | PT_Normal |  |  |  |  | SUn32wEeQSSvzdkgXn27Cw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40680 | N | N | 15 | FIRST FLOORS |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 868.75 | TILE MASON SK
%R | 502283 | 6359 | 124868 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARFF3325 | Porcelain Tile flooring | 8170 | 192 | 0 | 48 | 0 | 597.25 | 597.25 | 48 | 0 | 0 | 0 |  |  |  | 2013-11-24 08:00 | 2013-11-30 17:00 |  | 2013-10-27 08:00 | 2013-11-02 17:00 | 2013-10-27 08:00 | 2013-11-02 17:00 | 2013-10-27 08:00 | 2013-11-02 17:00 | 2013-11-24 08:00 | 2013-11-30 17:00 |  | PT_Normal |  |  |  |  | mKQPnGusQJGqUDxKNpelsw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40680 | N | N | 15 | FIRST FLOORS |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 597.25 | TILE MASON SK
%R | 502284 | 6359 | 124868 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARFF3335 | Slate Tile Flooring & Skirting | 8177 | 352 | 0 | 40 | 0 | 275 | 275 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-25 08:00 | 2013-12-30 17:00 |  | 2013-11-03 08:00 | 2013-11-07 17:00 | 2013-11-03 08:00 | 2013-11-07 17:00 | 2013-11-03 08:00 | 2013-11-07 17:00 | 2013-12-25 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | 7myWD22jSbC1BXfx0UdIMA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40680 | N | N | 15 | FIRST FLOORS |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 275 | LABOR - CIVIL
%R | 502285 | 6359 | 124868 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARFF3350 | Granite - Stair case flooring & Skirting | 8177 | 296 | 56 | 56 | 0 | 275 | 275 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-16 08:00 | 2013-12-24 17:00 |  | 2013-11-03 08:00 | 2013-11-10 17:00 | 2013-11-03 08:00 | 2013-11-10 17:00 | 2013-11-03 08:00 | 2013-11-10 17:00 | 2013-12-16 08:00 | 2013-12-24 17:00 |  | PT_Normal |  |  |  |  | uHQ+OGYxTsKd4yD5ZlirkA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40680 | N | N | 15 | FIRST FLOORS |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 275 | LABOR - CIVIL
%R | 502286 | 6359 | 124868 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARFF3345 | Fixing of Suspension systems | 8178 | 232 | 0 | 56 | 0 | 478.5 | 478.5 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-07 08:00 | 2013-12-14 17:00 |  | 2013-11-03 08:00 | 2013-11-10 17:00 | 2013-11-03 08:00 | 2013-11-10 17:00 | 2013-11-03 08:00 | 2013-11-10 17:00 | 2013-12-07 08:00 | 2013-12-14 17:00 |  | PT_Normal |  |  |  |  | HSUZrH7OQWGp8HdUiOzDJw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40680 | N | N | 15 | FIRST FLOORS |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 478.5 | LABOR- SUBCONTRACTOR
%R | 502287 | 6359 | 124868 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARFF3360 | Gypsum board false ceiling | 8178 | 232 | 0 | 56 | 0 | 433 | 433 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-15 08:00 | 2013-12-23 17:00 |  | 2013-11-11 08:00 | 2013-11-18 17:00 | 2013-11-11 08:00 | 2013-11-18 17:00 | 2013-11-11 08:00 | 2013-11-18 17:00 | 2013-12-15 08:00 | 2013-12-23 17:00 |  | PT_Normal |  |  |  |  | 8WtUs8WQSl+dgB3l4iKzvA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40680 | N | N | 15 | FIRST FLOORS |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 433 | LABOR- SUBCONTRACTOR
%R | 502288 | 6359 | 124868 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARFF3365 | Wooden door | 8178 | 288 | 0 | 40 | 0 | 110 | 110 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-01 08:00 | 2014-01-06 17:00 |  | 2013-11-19 08:00 | 2013-11-24 17:00 | 2013-11-19 08:00 | 2013-11-24 17:00 | 2013-11-19 08:00 | 2013-11-24 17:00 | 2014-01-01 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | 7UBcHRyLQiKnHmr9ztsqFA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40680 | N | N | 15 | FIRST FLOORS |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 110 | LABOR- SUBCONTRACTOR
%R | 502289 | 6359 | 124868 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARFF3370 | Aluminum doors | 8178 | 288 | 0 | 40 | 0 | 33 | 33 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-07 08:00 | 2014-01-12 17:00 |  | 2013-11-25 08:00 | 2013-11-30 17:00 | 2013-11-25 08:00 | 2013-11-30 17:00 | 2013-11-25 08:00 | 2013-11-30 17:00 | 2014-01-07 08:00 | 2014-01-12 17:00 |  | PT_Normal |  |  |  |  | QK5YbffqRqGhjCWuuKe4sg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40680 | N | N | 15 | FIRST FLOORS |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 33 | LABOR- SUBCONTRACTOR
%R | 502290 | 6359 | 124868 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARFF3380 | Aluminum windows | 8178 | 392 | 96 | 40 | 0 | 88 | 88 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-28 08:00 | 2014-02-02 17:00 |  | 2013-12-01 08:00 | 2013-12-05 17:00 | 2013-12-01 08:00 | 2013-12-05 17:00 | 2013-12-01 08:00 | 2013-12-05 17:00 | 2014-01-28 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | Xq6JnNtaRq6LZzUfkw/+Lw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40680 | N | N | 15 | FIRST FLOORS |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 88 | LABOR- SUBCONTRACTOR
%R | 502291 | 6359 | 124868 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARFF3375 | Carpentry & Joinery Works | 8178 | 288 | 0 | 80 | 0 | 28 | 28 | 80 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-01-23 17:00 |  | 2013-12-01 08:00 | 2013-12-11 17:00 | 2013-12-01 08:00 | 2013-12-11 17:00 | 2013-12-01 08:00 | 2013-12-11 17:00 | 2014-01-13 08:00 | 2014-01-23 17:00 |  | PT_Normal |  |  |  |  | v8QQQKgrQ32RnmdW10dzAg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40680 | N | N | 15 | FIRST FLOORS |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 28 | LABOR- SUBCONTRACTOR
%R | 502292 | 6359 | 124868 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARFF3390 | Installation of Granite Counter Top | 8171 | 296 | 0 | 56 | 0 | 44 | 44 | 56 | 0 | 0 | 0 |  |  |  | 2014-01-26 08:00 | 2014-02-02 17:00 |  | 2013-12-12 08:00 | 2013-12-21 17:00 | 2013-12-12 08:00 | 2013-12-21 17:00 | 2013-12-12 08:00 | 2013-12-21 17:00 | 2014-01-26 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | QEBdTCreS4eeGkPK9A+ZPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40680 | N | N | 15 | FIRST FLOORS |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 44 | GRANITE MASON SK
%R | 502293 | 6359 | 124868 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARFF3385 | S.S.Handrails & Balustrade | 8178 | 296 | 0 | 56 | 0 | 275 | 275 | 56 | 0 | 0 | 0 |  |  |  | 2014-01-26 08:00 | 2014-02-02 17:00 |  | 2013-12-12 08:00 | 2013-12-21 17:00 | 2013-12-12 08:00 | 2013-12-21 17:00 | 2013-12-12 08:00 | 2013-12-21 17:00 | 2014-01-26 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | SDe/kMjwS0+09DoJFgJ39w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40680 | N | N | 15 | FIRST FLOORS |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 275 | LABOR- SUBCONTRACTOR
%R | 502294 | 6359 | 124868 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARFF3395 | Final Painting | 8178 | 296 | 0 | 56 | 0 | 1436 | 1436 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-03 08:00 | 2014-02-10 17:00 |  | 2013-12-22 08:00 | 2013-12-29 17:00 | 2013-12-22 08:00 | 2013-12-29 17:00 | 2013-12-22 08:00 | 2013-12-29 17:00 | 2014-02-03 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | o/ZVAmbHTzGnugZSh0E2wQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40680 | N | N | 15 | FIRST FLOORS |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1436 | LABOR- SUBCONTRACTOR
%R | 502295 | 6359 | 124868 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARFF3355 | Aluminum tile false ceiling | 8178 | 272 | 0 | 56 | 0 | 51.95 | 51.95 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-22 08:00 | 2013-12-29 17:00 |  | 2013-11-11 08:00 | 2013-11-18 17:00 | 2013-11-11 08:00 | 2013-11-18 17:00 | 2013-11-11 08:00 | 2013-11-18 17:00 | 2013-12-22 08:00 | 2013-12-29 17:00 |  | PT_Normal |  |  |  |  | 3sJmurqATH6L16tzEdbQzw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40680 | N | N | 15 | FIRST FLOORS |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 51.95 | LABOR- SUBCONTRACTOR
%R | 502296 | 6359 | 124869 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARRF3600 | Block work | 8168 | 24 | 0 | 40 | 0 | 162.5 | 162.5 | 40 | 0 | 0 | 0 |  |  |  | 2013-10-14 08:00 | 2013-10-21 17:00 |  | 2013-10-10 08:00 | 2013-10-15 17:00 | 2013-10-10 08:00 | 2013-10-15 17:00 | 2013-10-10 08:00 | 2013-10-15 17:00 | 2013-10-14 08:00 | 2013-10-21 17:00 |  | PT_Normal |  |  |  |  | WL1uL59/RRmcwTAUxy8hJQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40690 | N | N | 20 | ROOF |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 162.5 | BLOCK MASON SK
%R | 502297 | 6359 | 124869 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARRF3605 | Plastering work | 8169 | 24 | 0 | 40 | 0 | 650 | 650 | 40 | 0 | 0 | 0 |  |  |  | 2013-10-20 08:00 | 2013-10-24 17:00 |  | 2013-10-14 08:00 | 2013-10-21 17:00 | 2013-10-14 08:00 | 2013-10-21 17:00 | 2013-10-14 08:00 | 2013-10-21 17:00 | 2013-10-20 08:00 | 2013-10-24 17:00 |  | PT_Normal |  |  |  |  | xiy08CdLSkuYbHsJT28Gmg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40690 | N | N | 20 | ROOF |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 650 | PLASTER MASON SK
%R | 502298 | 6359 | 124869 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARRF3610 | Flooring screed | 8164 | 584 | 288 | 48 | 0 | 38.5 | 38.5 | 48 | 0 | 0 | 0 |  |  |  | 2014-01-29 08:00 | 2014-02-04 17:00 |  | 2013-11-04 08:00 | 2013-11-10 17:00 | 2013-11-04 08:00 | 2013-11-10 17:00 | 2013-11-04 08:00 | 2013-11-10 17:00 | 2014-01-29 08:00 | 2014-02-04 17:00 |  | PT_Normal |  |  |  |  | xLO56g9GTBqDlOVjDqK0fg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40690 | N | N | 20 | ROOF |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 38.5 | SCREED MASON SK
%R | 502299 | 6359 | 124869 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARRF3695 | Painting | 8178 | 296 | 0 | 40 | 0 | 44 | 44 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-02-10 17:00 |  | 2013-12-24 08:00 | 2013-12-29 17:00 | 2013-12-24 08:00 | 2013-12-29 17:00 | 2013-12-24 08:00 | 2013-12-29 17:00 | 2014-02-05 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | oSrvCkZsRLWS8kqb9U6X1Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40690 | N | N | 20 | ROOF |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 44 | LABOR- SUBCONTRACTOR
%R | 502300 | 6359 | 124869 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARRF3620 | Epoxy Painting | 8178 | 376 | 80 | 40 | 0 | 8.25 | 8.25 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-01 17:00 |  | 2013-12-30 08:00 | 2014-01-04 17:00 | 2013-12-30 08:00 | 2014-01-04 17:00 | 2013-12-30 08:00 | 2014-01-04 17:00 | 2014-02-24 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | cuIa+gojT+SLAEsixka2Dw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40690 | N | N | 20 | ROOF |  | 124866 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 8.25 | LABOR- SUBCONTRACTOR
%R | 502301 | 6359 | 124871 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKAREL3675 | GRC Panel Works | 8178 | 152 | 0 | 56 | 0 | 550 | 550 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-12 08:00 | 2013-12-21 17:00 |  | 2013-11-20 08:00 | 2013-11-27 17:00 | 2013-11-20 08:00 | 2013-11-27 17:00 | 2013-11-20 08:00 | 2013-11-27 17:00 | 2013-12-12 08:00 | 2013-12-21 17:00 |  | PT_Normal |  |  |  |  | 6i8/tCDqRTiPZQbad3NcnQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40720 | N | N | 15 | ELEVATION |  | 124870 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 550 | LABOR- SUBCONTRACTOR
%R | 502302 | 6359 | 124871 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKAREL3680 | External Painting | 8178 | 528 | 184 | 56 | 0 | 272 | 272 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-02-23 17:00 |  | 2013-11-28 08:00 | 2013-12-05 17:00 | 2013-11-28 08:00 | 2013-12-05 17:00 | 2013-11-28 08:00 | 2013-12-05 17:00 | 2014-02-16 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | i39g1QERQmeDGIfaUOIUdw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40720 | N | N | 15 | ELEVATION |  | 124870 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 272 | LABOR- SUBCONTRACTOR
%R | 502303 | 6359 | 124871 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKAREL3665 | External Plastering | 8169 | 152 | 0 | 80 | 0 | 3053.5 | 3053.5 | 80 | 0 | 0 | 0 |  |  |  | 2013-12-01 08:00 | 2013-12-11 17:00 |  | 2013-11-09 08:00 | 2013-11-19 17:00 | 2013-11-09 08:00 | 2013-11-19 17:00 | 2013-11-09 08:00 | 2013-11-19 17:00 | 2013-12-01 08:00 | 2013-12-11 17:00 |  | PT_Normal |  |  |  |  | JV2hnl3gT06kPdq9J0Nwzg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40720 | N | N | 15 | ELEVATION |  | 124870 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 3053.5 | PLASTER MASON SK
%R | 502304 | 6359 | 124872 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARRF3630 | Leveling Screed for Waterproofing | 8164 | 24 | 0 | 16 | 0 | 245.5 | 245.5 | 16 | 0 | 0 | 0 |  |  |  | 2013-10-26 08:00 | 2013-10-27 17:00 |  | 2013-10-22 08:00 | 2013-10-23 17:00 | 2013-10-22 08:00 | 2013-10-23 17:00 | 2013-10-22 08:00 | 2013-10-23 17:00 | 2013-10-26 08:00 | 2013-10-27 17:00 |  | PT_Normal |  |  |  |  | DqCHpPwgR6OXEkIbFE7fBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40710 | N | N | 10 | ROOF |  | 124870 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 245.5 | SCREED MASON SK
%R | 502305 | 6359 | 124872 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARRF3635 | Laying of Waterproofing Membrane | 8178 | 24 | 0 | 40 | 0 | 681 | 681 | 40 | 0 | 0 | 0 |  |  |  | 2013-10-28 08:00 | 2013-11-02 17:00 |  | 2013-10-24 08:00 | 2013-10-29 17:00 | 2013-10-24 08:00 | 2013-10-29 17:00 | 2013-10-24 08:00 | 2013-10-29 17:00 | 2013-10-28 08:00 | 2013-11-02 17:00 |  | PT_Normal |  |  |  |  | Pn8935pKTeu8Ot+6TlsLiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40710 | N | N | 10 | ROOF |  | 124870 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 681 | LABOR- SUBCONTRACTOR
%R | 502306 | 6359 | 124872 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARRF3640 | Installation of Insulation & Protection | 8178 | 24 | 0 | 32 | 0 | 430.75 | 430.75 | 32 | 0 | 0 | 0 |  |  |  | 2013-11-03 08:00 | 2013-11-06 17:00 |  | 2013-10-30 08:00 | 2013-11-03 17:00 | 2013-10-30 08:00 | 2013-11-03 17:00 | 2013-10-30 08:00 | 2013-11-03 17:00 | 2013-11-03 08:00 | 2013-11-06 17:00 |  | PT_Normal |  |  |  |  | AjnLwfWZSWOd6qi4vDlSEA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40710 | N | N | 10 | ROOF |  | 124870 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 430.75 | LABOR- SUBCONTRACTOR
%R | 502307 | 6359 | 124872 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 24 | 0 | 32 | 0 | 247.5 | 247.5 | 32 | 0 | 0 | 0 |  |  |  | 2013-11-07 08:00 | 2013-11-11 17:00 |  | 2013-11-04 08:00 | 2013-11-07 17:00 | 2013-11-04 08:00 | 2013-11-07 17:00 | 2013-11-04 08:00 | 2013-11-07 17:00 | 2013-11-07 08:00 | 2013-11-11 17:00 |  | PT_Normal |  |  |  |  | MeRiOwtNRhiesq8EZwvUJg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40710 | N | N | 10 | ROOF |  | 124870 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 247.5 | TILE MASON SK
%R | 502308 | 6359 | 124872 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARRF3655 | Installation of Pumps Protection cabinets | 8178 | 528 | 0 | 48 | 0 | 77 | 77 | 48 | 0 | 0 | 0 |  |  |  | 2014-02-02 08:00 | 2014-02-08 17:00 |  | 2013-11-16 08:00 | 2013-11-21 17:00 | 2013-11-16 08:00 | 2013-11-21 17:00 | 2013-11-16 08:00 | 2013-11-21 17:00 | 2014-02-02 08:00 | 2014-02-08 17:00 |  | PT_Normal |  |  |  |  | 7rY/aB2eRwWdrzpP8kcspg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40710 | N | N | 10 | ROOF |  | 124870 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 77 | LABOR- SUBCONTRACTOR
%R | 502309 | 6359 | 124872 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 488 | 0 | 48 | 0 | 294 | 294 | 48 | 0 | 0 | 0 |  |  |  | 2014-01-20 08:00 | 2014-01-26 17:00 |  | 2013-11-09 08:00 | 2013-11-14 17:00 | 2013-11-09 08:00 | 2013-11-14 17:00 | 2013-11-09 08:00 | 2013-11-14 17:00 | 2014-01-20 08:00 | 2014-01-26 17:00 |  | PT_Normal |  |  |  |  | oXsg8ANwQBis1prVrLo0Ug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40710 | N | N | 10 | ROOF |  | 124870 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 294 | LABOR- SUBCONTRACTOR
%R | 502310 | 6359 | 124872 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKARRF3660 | Installation of Access Ladder | 8178 | 624 | 104 | 40 | 0 | 66 | 66 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-01 17:00 |  | 2013-11-23 08:00 | 2013-11-27 17:00 | 2013-11-23 08:00 | 2013-11-27 17:00 | 2013-11-23 08:00 | 2013-11-27 17:00 | 2014-02-24 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | 9hEn3haeTKivWvz01zlGug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40710 | N | N | 10 | ROOF |  | 124870 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 66 | LABOR- SUBCONTRACTOR
%R | 502311 | 6359 | 124875 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 336 | 0 | 40 | 0 | 90.4 | 90.4 | 40 | 0 | 0 | 0 |  |  |  | 2013-10-05 08:00 | 2013-10-09 17:00 |  | 2013-08-17 08:00 | 2013-08-21 17:00 | 2013-08-17 08:00 | 2013-08-21 17:00 | 2013-08-17 08:00 | 2013-08-21 17:00 | 2013-10-05 08:00 | 2013-10-09 17:00 |  | PT_Normal |  |  |  |  | qFx52e7rRiSvMIVPcOfqhA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40750 | N | N | 10 | GROUND FLOOR |  | 124874 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 90.4 | LABOR- SUBCONTRACTOR
%R | 502312 | 6359 | 124875 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKELGF4005 | Cable tray & trunking installation | 8178 | 480 | 0 | 40 | 0 | 159.2 | 159.2 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-11 08:00 | 2013-11-16 17:00 |  | 2013-08-31 08:00 | 2013-09-04 17:00 | 2013-08-31 08:00 | 2013-09-04 17:00 | 2013-08-31 08:00 | 2013-09-04 17:00 | 2013-11-11 08:00 | 2013-11-16 17:00 |  | PT_Normal |  |  |  |  | dDrdeBAWRQ+b4UWeWzOm2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40750 | N | N | 10 | GROUND FLOOR |  | 124874 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 159.2 | LABOR- SUBCONTRACTOR
%R | 502313 | 6359 | 124875 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKELGF4010 | Installation of wiring & Main Cabling | 8178 | 496 | 16 | 40 | 0 | 56.8 | 56.8 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-19 08:00 | 2013-11-24 17:00 |  | 2013-09-05 08:00 | 2013-09-10 17:00 | 2013-09-05 08:00 | 2013-09-10 17:00 | 2013-09-05 08:00 | 2013-09-10 17:00 | 2013-11-19 08:00 | 2013-11-24 17:00 |  | PT_Normal |  |  |  |  | qU3KZwwXS1qWLQB0V1hbEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40750 | N | N | 10 | GROUND FLOOR |  | 124874 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 56.8 | LABOR- SUBCONTRACTOR
%R | 502314 | 6359 | 124875 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 416 | 0 | 40 | 0 | 17.2 | 17.2 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-29 08:00 | 2014-01-02 17:00 |  | 2013-10-28 08:00 | 2013-11-02 17:00 | 2013-10-28 08:00 | 2013-11-02 17:00 | 2013-10-28 08:00 | 2013-11-02 17:00 | 2013-12-29 08:00 | 2014-01-02 17:00 |  | PT_Normal |  |  |  |  | NnSUuU8CSKu34Lz4ADPK+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40750 | N | N | 10 | GROUND FLOOR |  | 124874 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 17.2 | LABOR- SUBCONTRACTOR
%R | 502315 | 6359 | 124875 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 464 | 112 | 40 | 0 | 223.6 | 223.6 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-11 08:00 | 2014-01-15 17:00 |  | 2013-11-03 08:00 | 2013-11-07 17:00 | 2013-11-03 08:00 | 2013-11-07 17:00 | 2013-11-03 08:00 | 2013-11-07 17:00 | 2014-01-11 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | jwPGPUlvT16l5lC7joKltg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40750 | N | N | 10 | GROUND FLOOR |  | 124874 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 223.6 | LABOR- SUBCONTRACTOR
%R | 502316 | 6359 | 124875 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 416 | 40 | 56 | 0 | 117.6 | 117.6 | 56 | 0 | 0 | 0 |  |  |  | 2014-01-02 08:00 | 2014-01-09 17:00 |  | 2013-11-02 08:00 | 2013-11-09 17:00 | 2013-11-02 08:00 | 2013-11-09 17:00 | 2013-11-02 08:00 | 2013-11-09 17:00 | 2014-01-02 08:00 | 2014-01-09 17:00 |  | PT_Normal |  |  |  |  | 0QT8UJswSx+XEy4TDBaCKQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40750 | N | N | 10 | GROUND FLOOR |  | 124874 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 117.6 | LABOR- SUBCONTRACTOR
%R | 502317 | 6359 | 124875 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKELGF4030 | Installation of Telephone System | 8178 | 456 | 112 | 40 | 0 | 50.8 | 50.8 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-09 08:00 | 2014-01-14 17:00 |  | 2013-11-03 08:00 | 2013-11-07 17:00 | 2013-11-03 08:00 | 2013-11-07 17:00 | 2013-11-03 08:00 | 2013-11-07 17:00 | 2014-01-09 08:00 | 2014-01-14 17:00 |  | PT_Normal |  |  |  |  | 8e7c3TIaR5W232XAzUrzMA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40750 | N | N | 10 | GROUND FLOOR |  | 124874 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 50.8 | LABOR- SUBCONTRACTOR
%R | 502318 | 6359 | 124876 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKELRF4070 | Installation of Isolator | 8178 | 448 | 0 | 40 | 0 | 34.4 | 34.4 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-02-10 17:00 |  | 2013-12-01 08:00 | 2013-12-05 17:00 | 2013-12-01 08:00 | 2013-12-05 17:00 | 2013-12-01 08:00 | 2013-12-05 17:00 | 2014-02-05 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | SETd3ExKR/uiZJ+94zVO9w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40770 | N | N | 20 | ROOF |  | 124874 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 34.4 | LABOR- SUBCONTRACTOR
%R | 502319 | 6359 | 124876 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKELRF4075 | Installation of TV Dish Antenna | 8178 | 448 | 432 | 56 | 0 | 394 | 394 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-02-19 17:00 |  | 2013-12-07 08:00 | 2013-12-14 17:00 | 2013-12-07 08:00 | 2013-12-14 17:00 | 2013-12-07 08:00 | 2013-12-14 17:00 | 2014-02-12 08:00 | 2014-02-19 17:00 |  | PT_Normal |  |  |  |  | sxR5zMJnQteisjDKR5OggQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40770 | N | N | 20 | ROOF |  | 124874 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 394 | LABOR- SUBCONTRACTOR
%R | 502320 | 6359 | 124877 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 64 | 0 | 40 | 0 | 90.4 | 90.4 | 40 | 0 | 0 | 0 |  |  |  | 2013-10-08 08:00 | 2013-10-13 17:00 |  | 2013-09-29 08:00 | 2013-10-03 17:00 | 2013-09-29 08:00 | 2013-10-03 17:00 | 2013-09-29 08:00 | 2013-10-03 17:00 | 2013-10-08 08:00 | 2013-10-13 17:00 |  | PT_Normal |  |  |  |  | Lctie4KeRDCJMHEO2sSDOg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40760 | N | N | 15 | FIRST FLOORS |  | 124874 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 90.4 | LABOR- SUBCONTRACTOR
%R | 502321 | 6359 | 124877 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKELFF4040 | Cable tray & trunking installation | 8178 | 240 | 0 | 40 | 0 | 159.2 | 159.2 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-19 08:00 | 2013-11-24 17:00 |  | 2013-10-13 08:00 | 2013-10-20 17:00 | 2013-10-13 08:00 | 2013-10-20 17:00 | 2013-10-13 08:00 | 2013-10-20 17:00 | 2013-11-19 08:00 | 2013-11-24 17:00 |  | PT_Normal |  |  |  |  | VuYPEcgaSXmp0j5UfFxkCw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40760 | N | N | 15 | FIRST FLOORS |  | 124874 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 159.2 | LABOR- SUBCONTRACTOR
%R | 502322 | 6359 | 124877 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKELFF4045 | Installation of wiring & Main Cabling | 8178 | 256 | 16 | 40 | 0 | 56.8 | 56.8 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-27 08:00 | 2013-12-02 17:00 |  | 2013-10-21 08:00 | 2013-10-26 17:00 | 2013-10-21 08:00 | 2013-10-26 17:00 | 2013-10-21 08:00 | 2013-10-26 17:00 | 2013-11-27 08:00 | 2013-12-02 17:00 |  | PT_Normal |  |  |  |  | Mod//ZNKRrSOkNfPtrCr/A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40760 | N | N | 15 | FIRST FLOORS |  | 124874 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 56.8 | LABOR- SUBCONTRACTOR
%R | 502323 | 6359 | 124877 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 304 | 0 | 40 | 0 | 17.2 | 17.2 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-04 08:00 | 2014-01-08 17:00 |  | 2013-11-19 08:00 | 2013-11-24 17:00 | 2013-11-19 08:00 | 2013-11-24 17:00 | 2013-11-19 08:00 | 2013-11-24 17:00 | 2014-01-04 08:00 | 2014-01-08 17:00 |  | PT_Normal |  |  |  |  | 7i3dNftrTtOFOvwV1k3Vqg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40760 | N | N | 15 | FIRST FLOORS |  | 124874 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 17.2 | LABOR- SUBCONTRACTOR
%R | 502324 | 6359 | 124877 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 352 | 0 | 40 | 0 | 206.4 | 206.4 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-01-21 17:00 |  | 2013-11-25 08:00 | 2013-11-30 17:00 | 2013-11-25 08:00 | 2013-11-30 17:00 | 2013-11-25 08:00 | 2013-11-30 17:00 | 2014-01-16 08:00 | 2014-01-21 17:00 |  | PT_Normal |  |  |  |  | s52kGyOhQze4Fwp99wgMKQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40760 | N | N | 15 | FIRST FLOORS |  | 124874 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 206.4 | LABOR- SUBCONTRACTOR
%R | 502325 | 6359 | 124877 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 352 | 256 | 56 | 0 | 134.4 | 134.4 | 56 | 0 | 0 | 0 |  |  |  | 2014-01-11 08:00 | 2014-01-18 17:00 |  | 2013-11-19 08:00 | 2013-11-26 17:00 | 2013-11-19 08:00 | 2013-11-26 17:00 | 2013-11-19 08:00 | 2013-11-26 17:00 | 2014-01-11 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | BSkGG3QZTWCge9PYcLlraA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40760 | N | N | 15 | FIRST FLOORS |  | 124874 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 502326 | 6359 | 124877 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKELFF4050 | Installation of Telephone System | 8178 | 384 | 0 | 40 | 0 | 50.8 | 50.8 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-21 08:00 | 2014-01-26 17:00 |  | 2013-11-25 08:00 | 2013-11-30 17:00 | 2013-11-25 08:00 | 2013-11-30 17:00 | 2013-11-25 08:00 | 2013-11-30 17:00 | 2014-01-21 08:00 | 2014-01-26 17:00 |  | PT_Normal |  |  |  |  | QqCYq5pGR0OhQT59Fqy1ig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40760 | N | N | 15 | FIRST FLOORS |  | 124874 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 50.8 | LABOR- SUBCONTRACTOR
%R | 502327 | 6359 | 124879 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKPLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 24 | 0 | 40 | 0 | 138 | 138 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-12 08:00 | 2013-11-17 17:00 |  | 2013-11-09 08:00 | 2013-11-13 17:00 | 2013-11-09 08:00 | 2013-11-13 17:00 | 2013-11-09 08:00 | 2013-11-13 17:00 | 2013-11-12 08:00 | 2013-11-17 17:00 |  | PT_Normal |  |  |  |  | zPSWbjaYQ3CaupUTIhHaUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40810 | N | N | 20 | ROOF |  | 124878 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 138 | LABOR- SUBCONTRACTOR
%R | 502328 | 6359 | 124879 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKPLRF4350 | Installation of Rain water Pipes | 8181 | 544 | 128 | 40 | 0 | 10.8 | 10.8 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-03 08:00 | 2014-02-08 17:00 |  | 2013-11-14 08:00 | 2013-11-19 17:00 | 2013-11-14 08:00 | 2013-11-19 17:00 | 2013-11-14 08:00 | 2013-11-19 17:00 | 2014-02-03 08:00 | 2014-02-08 17:00 |  | PT_Normal |  |  |  |  | 4UFoWe1/Tmyi6L3gAU6mlA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43581 |  |  |  |  | MECHANICALS SK | M303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40810 | N | N | 20 | ROOF |  | 124878 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 10.8 | MECHANICALS SK
%R | 502329 | 6359 | 124879 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKPLRF4355 | Roof Water Tank Installation & Connections | 8178 | 416 | 304 | 56 | 0 | 16.8 | 16.8 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-02-17 17:00 |  | 2013-12-09 08:00 | 2013-12-16 17:00 | 2013-12-09 08:00 | 2013-12-16 17:00 | 2013-12-09 08:00 | 2013-12-16 17:00 | 2014-02-09 08:00 | 2014-02-17 17:00 |  | PT_Normal |  |  |  |  | 4L9/fSDtTy6Sd4KfCZ0Jvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40810 | N | N | 20 | ROOF |  | 124878 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 16.8 | LABOR- SUBCONTRACTOR
%R | 502330 | 6359 | 124880 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKPLGF4305 | Installation of Plumbing pipes & testing | 8178 | 352 | 0 | 40 | 0 | 231.6 | 231.6 | 40 | 0 | 0 | 0 |  |  |  | 2013-10-07 08:00 | 2013-10-12 17:00 |  | 2013-08-17 08:00 | 2013-08-21 17:00 | 2013-08-17 08:00 | 2013-08-21 17:00 | 2013-08-17 08:00 | 2013-08-21 17:00 | 2013-10-07 08:00 | 2013-10-12 17:00 |  | PT_Normal |  |  |  |  | TnfOH6Y3TxeRWxilM4DjIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40790 | N | N | 10 | GROUND FLOOR |  | 124878 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 231.6 | LABOR- SUBCONTRACTOR
%R | 502331 | 6359 | 124880 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKPLGF4310 | Installation of Drainage pipes &testing | 8178 | 496 | 72 | 40 | 0 | 16.8 | 16.8 | 40 | 0 | 0 | 0 |  |  |  | 2013-10-30 08:00 | 2013-11-04 17:00 |  | 2013-08-17 08:00 | 2013-08-21 17:00 | 2013-08-17 08:00 | 2013-08-21 17:00 | 2013-08-17 08:00 | 2013-08-21 17:00 | 2013-10-30 08:00 | 2013-11-04 17:00 |  | PT_Normal |  |  |  |  | q8ZaoVCWT9e9c6LzjRElYA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40790 | N | N | 10 | GROUND FLOOR |  | 124878 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 16.8 | LABOR- SUBCONTRACTOR
%R | 502332 | 6359 | 124880 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKPLGF4315 | Sanitary Fittings & Accessories | 8178 | 400 | 0 | 56 | 0 | 33.6 | 33.6 | 56 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-01-21 17:00 |  | 2013-11-16 08:00 | 2013-11-23 17:00 | 2013-11-16 08:00 | 2013-11-23 17:00 | 2013-11-16 08:00 | 2013-11-23 17:00 | 2014-01-14 08:00 | 2014-01-21 17:00 |  | PT_Normal |  |  |  |  | M8zZHmeDQ+qcqj93koOAPw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40790 | N | N | 10 | GROUND FLOOR |  | 124878 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 33.6 | LABOR- SUBCONTRACTOR
%R | 502333 | 6359 | 124880 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKPLGF4320 | Installation of Water Heater |  | 616 | 104 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-01 17:00 |  | 2013-11-24 08:00 | 2013-11-28 17:00 | 2013-11-24 08:00 | 2013-11-28 17:00 | 2013-11-24 08:00 | 2013-11-28 17:00 | 2014-02-24 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | Uvml2fxNR9KrmHFPOGwF7w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 40790 | N | N | 10 | GROUND FLOOR |  | 124878 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 0 | 0
%R | 502334 | 6359 | 124881 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKPLFF4325 | Installation of Plumbing pipes & testing | 8178 | 72 | 0 | 40 | 0 | 231.6 | 231.6 | 40 | 0 | 0 | 0 |  |  |  | 2013-10-09 08:00 | 2013-10-14 17:00 |  | 2013-09-29 08:00 | 2013-10-03 17:00 | 2013-09-29 08:00 | 2013-10-03 17:00 | 2013-09-29 08:00 | 2013-10-03 17:00 | 2013-10-09 08:00 | 2013-10-14 17:00 |  | PT_Normal |  |  |  |  | 55raHiLhRUadBu8noaKIVg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40800 | N | N | 15 | FIRST FLOORS |  | 124878 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 231.6 | LABOR- SUBCONTRACTOR
%R | 502335 | 6359 | 124881 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKPLFF4330 | Installation of Drainage pipes & testing | 8178 | 272 | 72 | 40 | 0 | 16.8 | 16.8 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-10 08:00 | 2013-11-14 17:00 |  | 2013-09-29 08:00 | 2013-10-03 17:00 | 2013-09-29 08:00 | 2013-10-03 17:00 | 2013-09-29 08:00 | 2013-10-03 17:00 | 2013-11-10 08:00 | 2013-11-14 17:00 |  | PT_Normal |  |  |  |  | cO0h5j7JSI6wJzim9s1gQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40800 | N | N | 15 | FIRST FLOORS |  | 124878 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 16.8 | LABOR- SUBCONTRACTOR
%R | 502336 | 6359 | 124881 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKPLFF4335 | Sanitary Fittings & Accessories | 8178 | 392 | 0 | 56 | 0 | 33.6 | 33.6 | 56 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-01-29 17:00 |  | 2013-11-25 08:00 | 2013-12-02 17:00 | 2013-11-25 08:00 | 2013-12-02 17:00 | 2013-11-25 08:00 | 2013-12-02 17:00 | 2014-01-22 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | cf45N85OS6ai4+zN04AmYQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40800 | N | N | 15 | FIRST FLOORS |  | 124878 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 33.6 | LABOR- SUBCONTRACTOR
%R | 502337 | 6359 | 124881 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKPLFF4340 | Installation of Water Heater |  | 416 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-03 08:00 | 2014-02-08 17:00 |  | 2013-12-03 08:00 | 2013-12-08 17:00 | 2013-12-03 08:00 | 2013-12-08 17:00 | 2013-12-03 08:00 | 2013-12-08 17:00 | 2014-02-03 08:00 | 2014-02-08 17:00 |  | PT_Normal |  |  |  |  | 6RCdHWMATlK/Zk754HRLWg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 40800 | N | N | 15 | FIRST FLOORS |  | 124878 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 0 | 0
%R | 502338 | 6359 | 124883 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKACGF4600 | Installation AC Pipes | 8178 | 632 | 112 | 40 | 0 | 28.4 | 28.4 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-03 08:00 | 2013-12-08 17:00 |  | 2013-08-31 08:00 | 2013-09-04 17:00 | 2013-08-31 08:00 | 2013-09-04 17:00 | 2013-08-31 08:00 | 2013-09-04 17:00 | 2013-12-03 08:00 | 2013-12-08 17:00 |  | PT_Normal |  |  |  |  | a3bz9e1+QR6HSsrjS6koWQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40830 | N | N | 10 | GROUND FLOOR |  | 124882 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 28.4 | LABOR- SUBCONTRACTOR
%R | 502339 | 6359 | 124883 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKACGF4605 | Fixing of Ventilation Equipments | 8178 | 456 | 0 | 40 | 0 | 17.2 | 17.2 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-04 08:00 | 2014-01-08 17:00 |  | 2013-10-28 08:00 | 2013-11-02 17:00 | 2013-10-28 08:00 | 2013-11-02 17:00 | 2013-10-28 08:00 | 2013-11-02 17:00 | 2014-01-04 08:00 | 2014-01-08 17:00 |  | PT_Normal |  |  |  |  | oL4IJPOHRmaxEEhvJGKHoA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40830 | N | N | 10 | GROUND FLOOR |  | 124882 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 17.2 | LABOR- SUBCONTRACTOR
%R | 502340 | 6359 | 124883 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKACGF4610 | Fixing of Split AC | 8178 | 560 | 112 | 40 | 0 | 34.4 | 34.4 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-25 08:00 | 2014-01-29 17:00 |  | 2013-11-03 08:00 | 2013-11-07 17:00 | 2013-11-03 08:00 | 2013-11-07 17:00 | 2013-11-03 08:00 | 2013-11-07 17:00 | 2014-01-25 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | Tt+QrP4wSeKl8oSXQ3W1jg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40830 | N | N | 10 | GROUND FLOOR |  | 124882 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 34.4 | LABOR- SUBCONTRACTOR
%R | 502341 | 6359 | 124884 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKACRF4630 | Installation of Refrigerant Pipes | 8178 | 584 | 0 | 56 | 0 | 17.2 | 17.2 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-03 08:00 | 2014-02-10 17:00 |  | 2013-11-09 08:00 | 2013-11-16 17:00 | 2013-11-09 08:00 | 2013-11-16 17:00 | 2013-11-09 08:00 | 2013-11-16 17:00 | 2014-02-03 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | h1C7gMDxQG+mqH85TN7zUw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40850 | N | N | 20 | ROOF |  | 124882 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 17.2 | LABOR- SUBCONTRACTOR
%R | 502342 | 6359 | 124884 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKACRF4635 | Installation of Condensing Unit | 8178 | 488 | 376 | 40 | 0 | 45.6 | 45.6 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-02-17 17:00 |  | 2013-12-01 08:00 | 2013-12-05 17:00 | 2013-12-01 08:00 | 2013-12-05 17:00 | 2013-12-01 08:00 | 2013-12-05 17:00 | 2014-02-12 08:00 | 2014-02-17 17:00 |  | PT_Normal |  |  |  |  | zECNBNeLTMWt5WeS0CRA6w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40850 | N | N | 20 | ROOF |  | 124882 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 45.6 | LABOR- SUBCONTRACTOR
%R | 502343 | 6359 | 124885 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKACFF4615 | Installation AC Pipes | 8178 | 376 | 120 | 40 | 0 | 28.4 | 28.4 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-09 08:00 | 2013-12-14 17:00 |  | 2013-10-13 08:00 | 2013-10-20 17:00 | 2013-10-13 08:00 | 2013-10-20 17:00 | 2013-10-13 08:00 | 2013-10-20 17:00 | 2013-12-09 08:00 | 2013-12-14 17:00 |  | PT_Normal |  |  |  |  | rirwpQjOSMG45Eq8OhZgmA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40840 | N | N | 15 | FIRST FLOORS |  | 124882 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 28.4 | LABOR- SUBCONTRACTOR
%R | 502344 | 6359 | 124885 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKACFF4620 | Fixing of Ventilation Equipments | 8178 | 344 | 0 | 40 | 0 | 17.2 | 17.2 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-09 08:00 | 2014-01-14 17:00 |  | 2013-11-19 08:00 | 2013-11-24 17:00 | 2013-11-19 08:00 | 2013-11-24 17:00 | 2013-11-19 08:00 | 2013-11-24 17:00 | 2014-01-09 08:00 | 2014-01-14 17:00 |  | PT_Normal |  |  |  |  | Ps6YhS5/Q6Kp2J6Y45hD3g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40840 | N | N | 15 | FIRST FLOORS |  | 124882 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 17.2 | LABOR- SUBCONTRACTOR
%R | 502345 | 6359 | 124885 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP03MKACFF4625 | Fixing of Split AC | 8178 | 448 | 0 | 40 | 0 | 34.4 | 34.4 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-02-04 17:00 |  | 2013-11-25 08:00 | 2013-11-30 17:00 | 2013-11-25 08:00 | 2013-11-30 17:00 | 2013-11-25 08:00 | 2013-11-30 17:00 | 2014-01-30 08:00 | 2014-02-04 17:00 |  | PT_Normal |  |  |  |  | ptI6B2zjSz6nBiAfHTr/BA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40840 | N | N | 15 | FIRST FLOORS |  | 124882 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 34.4 | LABOR- SUBCONTRACTOR
%R | 502346 | 6359 | 124889 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3PSGL7000 | Excavation | 8177 | 104 | 40 | 120 | 0 | 37 | 37 | 120 | 31 | 0 | 31 |  |  |  | 2014-06-21 08:00 | 2014-07-07 17:00 |  | 2014-06-05 08:00 | 2014-06-22 17:00 | 2014-06-05 08:00 | 2014-06-22 17:00 | 2014-06-05 08:00 | 2014-06-22 17:00 | 2014-06-21 08:00 | 2014-07-07 17:00 |  | PT_Normal |  |  |  |  | R7Bn80MBTFurg5AcZOjCqA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43220 | N | N | 60 | PARKING SHED |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 37 | LABOR - CIVIL
%R | 502347 | 6359 | 124889 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3PSGL7005 | Foundation casting | 8165 | 64 | 0 | 120 | 0 | 1100 | 1100 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-26 08:00 | 2014-07-13 17:00 |  | 2014-06-17 08:00 | 2014-07-03 17:00 | 2014-06-17 08:00 | 2014-07-03 17:00 | 2014-06-17 08:00 | 2014-07-03 17:00 | 2014-06-26 08:00 | 2014-07-13 17:00 |  | PT_Normal |  |  |  |  | CvOZZimcQfq534FCeyciPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43220 | N | N | 60 | PARKING SHED |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1100 | STEEL FIXERS SK
%R | 502348 | 6359 | 124889 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3PSGL7010 | Column, Frame& Fabrics Erection | 8178 | 64 | 0 | 200 | 0 | 364 | 364 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-08 08:00 | 2014-08-09 17:00 |  | 2014-06-29 08:00 | 2014-07-27 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 | 2014-07-08 08:00 | 2014-08-09 17:00 |  | PT_Normal |  |  |  |  | VBe7e0Y2RQume008YYznUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43220 | N | N | 60 | PARKING SHED |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 364 | LABOR- SUBCONTRACTOR
%R | 502349 | 6359 | 124889 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3PSGL7015 | Electrical Works-Parking Shed | 8178 | 64 | 64 | 200 | 0 | 172 | 172 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-14 08:00 | 2014-08-14 17:00 |  | 2014-07-05 08:00 | 2014-08-05 17:00 | 2014-07-05 08:00 | 2014-08-05 17:00 | 2014-07-05 08:00 | 2014-08-05 17:00 | 2014-07-14 08:00 | 2014-08-14 17:00 |  | PT_Normal |  |  |  |  | L28dTET5TpKXUT79LRqp2A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43220 | N | N | 60 | PARKING SHED |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 86 | LABOR- SUBCONTRACTOR
%R | 502350 | 6359 | 124890 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3DRGL5120 | Laying of Drainage line | 8178 | 96 | 0 | 200 | 0 | 662.4 | 662.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-19 08:00 | 2014-01-16 17:00 |  | 2013-12-04 08:00 | 2014-01-02 17:00 | 2013-12-04 08:00 | 2014-01-02 17:00 | 2013-12-04 08:00 | 2014-01-02 17:00 | 2013-12-19 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | 1me0AVgDS1iQv4R+X/mOLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43120 | N | N | 10 | DRAINAGE LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 662.4 | LABOR- SUBCONTRACTOR
%R | 502351 | 6359 | 124890 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3DRGL5125 | Testing of Drainage line | 8178 | 96 | 0 | 200 | 0 | 662.4 | 662.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-28 08:00 | 2014-01-25 17:00 |  | 2013-12-12 08:00 | 2014-01-11 17:00 | 2013-12-12 08:00 | 2014-01-11 17:00 | 2013-12-12 08:00 | 2014-01-11 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 |  | PT_Normal |  |  |  |  | QvsO2e6vTH6jkOEEyq1IGw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43120 | N | N | 10 | DRAINAGE LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 662.4 | LABOR- SUBCONTRACTOR
%R | 502352 | 6359 | 124890 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3DRGL5130 | Backfilling Drainage line | 8177 | 96 | 0 | 120 | 0 | 450 | 450 | 120 | 330 | 0 | 330 |  |  |  | 2014-01-14 08:00 | 2014-01-30 17:00 |  | 2013-12-31 08:00 | 2014-01-16 17:00 | 2013-12-31 08:00 | 2014-01-16 17:00 | 2013-12-31 08:00 | 2014-01-16 17:00 | 2014-01-14 08:00 | 2014-01-30 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43120 | N | N | 10 | DRAINAGE LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 450 | LABOR - CIVIL
%R | 502353 | 6359 | 124890 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3DRGL5115 | Excavation for Drainage line | 8177 | 96 | 0 | 200 | 0 | 688 | 688 | 200 | 400 | 0 | 400 |  |  |  | 2013-12-11 08:00 | 2014-01-09 17:00 |  | 2013-11-27 08:00 | 2013-12-26 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 | 2013-12-11 08:00 | 2014-01-09 17:00 |  | PT_Normal |  |  |  |  | i0FTywpFTWGhEpchycuZ2w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43120 | N | N | 10 | DRAINAGE LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 688 | LABOR - CIVIL
%R | 502354 | 6359 | 124891 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3WSGL5155 | Excavation for water line | 8177 | 96 | 0 | 200 | 0 | 908 | 908 | 200 | 500 | 0 | 500 |  |  |  | 2014-01-26 08:00 | 2014-02-24 17:00 |  | 2014-01-12 08:00 | 2014-02-09 17:00 | 2014-01-12 08:00 | 2014-02-09 17:00 | 2014-01-12 08:00 | 2014-02-09 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 |  | PT_Normal |  |  |  |  | nwVcf6u8S7Ox7NZMGAmzzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43140 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 908 | LABOR - CIVIL
%R | 502355 | 6359 | 124891 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3WSGL5160 | Laying of water line | 8178 | 96 | 0 | 200 | 0 | 938.4 | 938.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-01 08:00 | 2014-03-02 17:00 |  | 2014-01-18 08:00 | 2014-02-16 17:00 | 2014-01-18 08:00 | 2014-02-16 17:00 | 2014-01-18 08:00 | 2014-02-16 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 |  | PT_Normal |  |  |  |  | 0A9FYr03QT64vnBxx3ioBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43140 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 938.4 | LABOR- SUBCONTRACTOR
%R | 502356 | 6359 | 124891 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3WSGL5165 | Testing of potable water line | 8178 | 96 | 0 | 200 | 0 | 469.2 | 469.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-03-08 17:00 |  | 2014-01-23 08:00 | 2014-02-22 17:00 | 2014-01-23 08:00 | 2014-02-22 17:00 | 2014-01-23 08:00 | 2014-02-22 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | Npwdh0wIRQyT1zUxm0Uq7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43140 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 469.2 | LABOR- SUBCONTRACTOR
%R | 502357 | 6359 | 124891 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3WSGL5170 | Backfilling potable water line | 8177 | 96 | 0 | 200 | 0 | 712 | 712 | 200 | 550 | 0 | 550 |  |  |  | 2014-02-13 08:00 | 2014-03-13 17:00 |  | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 |  | PT_Normal |  |  |  |  | 5kNJgLXbRK6SDDMVpFg+Dg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43140 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 712 | LABOR - CIVIL
%R | 502358 | 6359 | 124891 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3WSGL5175 | Construction of valve chambers & Thrust Blocks | 8177 | 248 | 0 | 200 | 0 | 66 | 66 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-04-10 17:00 |  | 2014-02-04 08:00 | 2014-03-05 17:00 | 2014-02-04 08:00 | 2014-03-05 17:00 | 2014-02-04 08:00 | 2014-03-05 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | k7xzHktbTUu/d+jQYApjvQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43140 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 33 | LABOR - CIVIL
%R | 502359 | 6359 | 124891 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3WSGL5180 | Installation of meter ,Accessories & Connection | 8178 | 248 | 88 | 160 | 0 | 33.6 | 33.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-04 17:00 |  | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | xguT3ggPSe6XcWCBrMn/9Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43140 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 33.6 | LABOR- SUBCONTRACTOR
%R | 502360 | 6359 | 124892 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3IRGL5265 | Excavation for irrigation line | 8177 | 152 | 0 | 200 | 0 | 812 | 812 | 200 | 500 | 0 | 500 |  |  |  | 2014-05-14 08:00 | 2014-06-11 17:00 |  | 2014-04-22 08:00 | 2014-05-20 17:00 | 2014-04-22 08:00 | 2014-05-20 17:00 | 2014-04-22 08:00 | 2014-05-20 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 |  | PT_Normal |  |  |  |  | k84g78F3TkSOoXlwdlwENw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43180 | N | N | 40 | IRRIGATION LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 812 | LABOR - CIVIL
%R | 502361 | 6359 | 124892 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3IRGL5270 | Laying of irrigationline | 8178 | 152 | 0 | 200 | 0 | 1159.2 | 1159.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-20 08:00 | 2014-06-17 17:00 |  | 2014-04-28 08:00 | 2014-05-26 17:00 | 2014-04-28 08:00 | 2014-05-26 17:00 | 2014-04-28 08:00 | 2014-05-26 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | rqiN3qzWSe2lAWVNE2VdVA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43180 | N | N | 40 | IRRIGATION LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1159.2 | LABOR- SUBCONTRACTOR
%R | 502362 | 6359 | 124892 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3IRGL5275 | Testing of irrigation line | 8178 | 152 | 0 | 200 | 0 | 1021.2 | 1021.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-26 08:00 | 2014-06-23 17:00 |  | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-05-26 08:00 | 2014-06-23 17:00 |  | PT_Normal |  |  |  |  | M0EfxLzGR1qSSnUgBPXSRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43180 | N | N | 40 | IRRIGATION LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1021.2 | LABOR- SUBCONTRACTOR
%R | 502363 | 6359 | 124892 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3IRGL5280 | Backfilling irrigation line | 8177 | 152 | 0 | 200 | 0 | 676 | 676 | 200 | 550 | 0 | 550 |  |  |  | 2014-06-01 08:00 | 2014-06-29 17:00 |  | 2014-05-10 08:00 | 2014-06-07 17:00 | 2014-05-10 08:00 | 2014-06-07 17:00 | 2014-05-10 08:00 | 2014-06-07 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 |  | PT_Normal |  |  |  |  | pB9qKUBeSC+rJh78moZKkg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43180 | N | N | 40 | IRRIGATION LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 676 | LABOR - CIVIL
%R | 502364 | 6359 | 124892 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3IRGL5285 | Construction of Thrust Blocks,Pull boxes | 8165 | 152 | 0 | 200 | 0 | 528 | 528 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-07-10 17:00 |  | 2014-05-21 08:00 | 2014-06-18 17:00 | 2014-05-21 08:00 | 2014-06-18 17:00 | 2014-05-21 08:00 | 2014-06-18 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 |  | PT_Normal |  |  |  |  | fLutT93ST6KdUy1zgdDeFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43180 | N | N | 40 | IRRIGATION LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 528 | STEEL FIXERS SK
%R | 502365 | 6359 | 124892 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3IRGL5290 | Irrigation Fittings (Nozzle,Values) | 8178 | 152 | 8 | 200 | 0 | 355 | 355 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-21 08:00 | 2014-07-19 17:00 |  | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-06-21 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | r5GaBYEVQ0aqGmN6nBo1tA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43180 | N | N | 40 | IRRIGATION LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 355 | LABOR- SUBCONTRACTOR
%R | 502366 | 6359 | 124893 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3RWGL6000 | Excavation & Earth Filling | 8177 | 64 | 0 | 80 | 0 | 1614 | 1614 | 80 | 600 | 0 | 600 |  |  |  | 2014-05-05 08:00 | 2014-05-15 17:00 |  | 2014-04-26 08:00 | 2014-05-06 17:00 | 2014-04-26 08:00 | 2014-05-06 17:00 | 2014-04-26 08:00 | 2014-05-06 17:00 | 2014-05-05 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | jrxpeeCzQS+DPJzDZ553+Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43210 | N | N | 55 | ROAD WORKS |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1614 | LABOR - CIVIL
%R | 502367 | 6359 | 124893 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3RWGL6005 | Laying of Sub Grade | 8178 | 64 | 0 | 200 | 0 | 30 | 30 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | rpFt9bKRSueymhhh7sL1xQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43210 | N | N | 55 | ROAD WORKS |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 30 | LABOR- SUBCONTRACTOR
%R | 502368 | 6359 | 124893 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3RWGL6010 | Laying of Precast Kerbs | 8178 | 64 | 0 | 200 | 0 | 1014 | 1014 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-25 17:00 |  | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | 8BMkbG8AScqt9drbc65mSQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43210 | N | N | 55 | ROAD WORKS |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1014 | LABOR- SUBCONTRACTOR
%R | 502369 | 6359 | 124893 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3RWGL6015 | Laying of Granular Sub Base Coarse | 8178 | 64 | 0 | 160 | 0 | 630 | 630 | 160 | 600 | 0 | 600 |  |  |  | 2014-06-09 08:00 | 2014-07-01 17:00 |  | 2014-05-31 08:00 | 2014-06-22 17:00 | 2014-05-31 08:00 | 2014-06-22 17:00 | 2014-05-31 08:00 | 2014-06-22 17:00 | 2014-06-09 08:00 | 2014-07-01 17:00 |  | PT_Normal |  |  |  |  | if0D/LbNQayn8kcnP6vcLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43210 | N | N | 55 | ROAD WORKS |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 630 | LABOR- SUBCONTRACTOR
%R | 502370 | 6359 | 124893 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3RWGL6020 | Laying of Road Base Asphalt Concrete | 8178 | 64 | 0 | 40 | 0 | 180 | 180 | 40 | 150 | 0 | 150 |  |  |  | 2014-07-02 08:00 | 2014-07-07 17:00 |  | 2014-06-23 08:00 | 2014-06-28 17:00 | 2014-06-23 08:00 | 2014-06-28 17:00 | 2014-06-23 08:00 | 2014-06-28 17:00 | 2014-07-02 08:00 | 2014-07-07 17:00 |  | PT_Normal |  |  |  |  | mCqaqRUeRhaGvcIYg3qT5w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43210 | N | N | 55 | ROAD WORKS |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 180 | LABOR- SUBCONTRACTOR
%R | 502371 | 6359 | 124893 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3RWGL6025 | Laying of Asphalt Wearing Coarse | 8178 | 184 | 0 | 40 | 0 | 180 | 180 | 40 | 150 | 0 | 150 |  |  |  | 2014-07-26 08:00 | 2014-07-30 17:00 |  | 2014-06-29 08:00 | 2014-07-03 17:00 | 2014-06-29 08:00 | 2014-07-03 17:00 | 2014-06-29 08:00 | 2014-07-03 17:00 | 2014-07-26 08:00 | 2014-07-30 17:00 |  | PT_Normal |  |  |  |  | aiYXUC5eRpiAjwMiF4eKCQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43210 | N | N | 55 | ROAD WORKS |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 180 | LABOR- SUBCONTRACTOR
%R | 502372 | 6359 | 124893 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3RWGL6030 | Traffic Signage & Road Marking | 8178 | 184 | 120 | 40 | 0 | 366 | 366 | 40 | 0 | 0 | 0 |  |  |  | 2014-07-31 08:00 | 2014-08-09 17:00 |  | 2014-07-05 08:00 | 2014-07-09 17:00 | 2014-07-05 08:00 | 2014-07-09 17:00 | 2014-07-05 08:00 | 2014-07-09 17:00 | 2014-07-31 08:00 | 2014-08-09 17:00 |  | PT_Normal |  |  |  |  | al8bCveoRiavOikpovBs5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43210 | N | N | 55 | ROAD WORKS |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 366 | LABOR- SUBCONTRACTOR
%R | 502373 | 6359 | 124894 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3BWGL5315 | Construction of Boundary Wall (Ht-3m) | 8165 | 152 | 0 | 200 | 0 | 182 | 182 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-24 08:00 | 2014-05-22 17:00 |  | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 |  | PT_Normal |  |  |  |  | sE1rvkQtRIuEnOPDXIsW8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43200 | N | N | 50 | BOUNDARY WALL |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 182 | STEEL FIXERS SK
%R | 502374 | 6359 | 124894 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 8306 | 152 | 8 | 200 | 0 | 14 | 14 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-06-08 17:00 |  | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | gnxjBDj8QX63O56D4u07kA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 45950 |  |  |  |  | GATE ERECTOR SK | S313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43200 | N | N | 50 | BOUNDARY WALL |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 14 | GATE ERECTOR SK
%R | 502375 | 6359 | 124895 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3STGL5235 | Excavation for Street lighting | 8177 | 64 | 0 | 200 | 0 | 69 | 69 | 200 | 51 | 0 | 51 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | 0ThlJ3YpTqy57NJrO4Cciw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43170 | N | N | 35 | STREET LIGHTING |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 69 | LABOR - CIVIL
%R | 502376 | 6359 | 124895 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3STGL5240 | Construction of Duct Banks | 8178 | 64 | 0 | 200 | 0 | 1181.6 | 1181.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-25 08:00 | 2014-04-22 17:00 |  | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | X0hZ8YhNTLmErzdCwX+U+A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43170 | N | N | 35 | STREET LIGHTING |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1181.6 | LABOR- SUBCONTRACTOR
%R | 502377 | 6359 | 124895 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3STGL5245 | Construction of Foundation | 8177 | 64 | 0 | 200 | 0 | 594 | 594 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-25 08:00 | 2014-04-22 17:00 |  | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43170 | N | N | 35 | STREET LIGHTING |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 594 | LABOR - CIVIL
%R | 502378 | 6359 | 124895 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3STGL5250 | Backfilling Street Lighting | 8177 | 64 | 0 | 200 | 0 | 61 | 61 | 200 | 55 | 0 | 55 |  |  |  | 2014-03-31 08:00 | 2014-04-28 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | egWD/JgRRk6ITSRzc4p6wg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43170 | N | N | 35 | STREET LIGHTING |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 61 | LABOR - CIVIL
%R | 502379 | 6359 | 124895 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3STGL5255 | Installation of light Post | 8178 | 448 | 160 | 200 | 0 | 198.8 | 198.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-07 08:00 | 2014-07-05 17:00 |  | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-06-07 08:00 | 2014-07-05 17:00 |  | PT_Normal |  |  |  |  | a9h/y7nlQz21juYpGCfU8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43170 | N | N | 35 | STREET LIGHTING |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 198.8 | LABOR- SUBCONTRACTOR
%R | 502380 | 6359 | 124895 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3STGL5260 | Electrical Works | 8178 | 288 | 224 | 200 | 0 | 482.8 | 482.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-13 17:00 |  | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 |  | PT_Normal |  |  |  |  | FAqa6+kKTXa20Npc0/1Slw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43170 | N | N | 35 | STREET LIGHTING |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 482.8 | LABOR- SUBCONTRACTOR
%R | 502381 | 6359 | 124896 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3FFGL5185 | Excavation for firefighting line | 8177 | 64 | 0 | 200 | 0 | 437 | 437 | 200 | 251 | 0 | 251 |  |  |  | 2014-02-19 08:00 | 2014-03-19 17:00 |  | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 |  | PT_Normal |  |  |  |  | z+0P0VSSQ466VitOA455Qw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43150 | N | N | 25 | FIREFIGHTING LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 218.5 | LABOR - CIVIL
%R | 502382 | 6359 | 124896 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3FFGL5190 | Laying of firefighting line | 8178 | 64 | 0 | 200 | 0 | 430.8 | 430.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-27 08:00 | 2014-03-27 17:00 |  | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 |  | PT_Normal |  |  |  |  | W7lzg6gKQXOhEnICPuZD/A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43150 | N | N | 25 | FIREFIGHTING LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 215.4 | LABOR- SUBCONTRACTOR
%R | 502383 | 6359 | 124896 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3FFGL5195 | Testing of firefighting line | 8178 | 64 | 0 | 200 | 0 | 220.8 | 220.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-05 08:00 | 2014-04-02 17:00 |  | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 |  | PT_Normal |  |  |  |  | rMwc0DI9TUSwQqWNFgY+gg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43150 | N | N | 25 | FIREFIGHTING LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 110.4 | LABOR- SUBCONTRACTOR
%R | 502384 | 6359 | 124896 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3FFGL5200 | Backfilling firefighting line | 8177 | 64 | 0 | 200 | 0 | 353 | 353 | 200 | 275 | 0 | 275 |  |  |  | 2014-03-11 08:00 | 2014-04-08 17:00 |  | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | QY48wHRTS/eoynxHVPSFvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43150 | N | N | 25 | FIREFIGHTING LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 353 | LABOR - CIVIL
%R | 502385 | 6359 | 124896 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3FFGL5205 | Construction of valve chambers & Thrust Blocks | 8165 | 160 | 0 | 200 | 0 | 64 | 64 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-28 17:00 |  | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | QnBn66qsQCiVQvFrFeMVyg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43150 | N | N | 25 | FIREFIGHTING LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 64 | STEEL FIXERS SK
%R | 502386 | 6359 | 124896 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3FFGL5210 | Connection with existing Firewater System | 8165 | 160 | 96 | 200 | 0 | 64 | 64 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-05-04 17:00 |  | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-04-06 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | j7WvT2M6QAG9eARxAIIoAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43150 | N | N | 25 | FIREFIGHTING LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 64 | STEEL FIXERS SK
%R | 502387 | 6359 | 124897 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3ELGL5215 | Excavation Cable Trenches & Duct Banks | 8167 | 64 | 0 | 200 | 0 | 3479.2 | 3479.2 | 200 | 1000 | 0 | 1000 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | AEiqdF4SSFWmIhvBU8JcbA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43160 | N | N | 30 | ELECTRICAL LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 3479.2 | CONCRETE MASON SK
%R | 502388 | 6359 | 124897 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3ELGL5220 | Laying of electrical cables | 8178 | 88 | 0 | 200 | 0 | 5566.4 | 5566.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-29 08:00 | 2014-04-26 17:00 |  | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-29 08:00 | 2014-04-26 17:00 |  | PT_Normal |  |  |  |  | p5APN5EDQ32SwHjvOYCAYA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43160 | N | N | 30 | ELECTRICAL LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 5566.4 | LABOR- SUBCONTRACTOR
%R | 502389 | 6359 | 124897 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3ELGL5225 | Backfilling Electrical trench | 8177 | 88 | 0 | 200 | 0 | 1898 | 1898 | 200 | 1100 | 0 | 1100 |  |  |  | 2014-04-06 08:00 | 2014-05-04 17:00 |  | 2014-03-24 08:00 | 2014-04-21 17:00 | 2014-03-24 08:00 | 2014-04-21 17:00 | 2014-03-24 08:00 | 2014-04-21 17:00 | 2014-04-06 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | qKD5lPieRN6vIHS8Bg4tXQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43160 | N | N | 30 | ELECTRICAL LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1898 | LABOR - CIVIL
%R | 502390 | 6359 | 124897 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3ELGL5230 | Construction of Submain Board & Feeder Pillar | 8165 | 288 | 0 | 200 | 0 | 508 | 508 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-04-05 08:00 | 2014-05-03 17:00 | 2014-04-05 08:00 | 2014-05-03 17:00 | 2014-04-05 08:00 | 2014-05-03 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | az9MHOdSTAutt9ZBGEXFMQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43160 | N | N | 30 | ELECTRICAL LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 508 | STEEL FIXERS SK
%R | 502391 | 6359 | 124898 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3SLGL7200 | Excavation for Landscaping | 8177 | 144 | 0 | 200 | 0 | 81 | 81 | 200 | 51 | 0 | 51 |  |  |  | 2014-06-21 08:00 | 2014-07-19 17:00 |  | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-06-21 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | EzyFtg+lQWG7hLKHq528PQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43240 | N | N | 70 | SOFT LANDSCAPING |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 81 | LABOR - CIVIL
%R | 502392 | 6359 | 124898 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3SLGL7205 | Sweet Soil Laying | 8178 | 144 | 0 | 200 | 0 | 1274 | 1274 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-02 08:00 | 2014-07-30 17:00 |  | 2014-06-11 08:00 | 2014-07-09 17:00 | 2014-06-11 08:00 | 2014-07-09 17:00 | 2014-06-11 08:00 | 2014-07-09 17:00 | 2014-07-02 08:00 | 2014-07-30 17:00 |  | PT_Normal |  |  |  |  | Lvhq0Oj1RE+XHE48ZiOPbA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43240 | N | N | 70 | SOFT LANDSCAPING |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1274 | LABOR- SUBCONTRACTOR
%R | 502393 | 6359 | 124898 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3SLGL7210 | Plantation works | 8178 | 144 | 144 | 200 | 0 | 1918 | 1918 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-14 08:00 | 2014-08-14 17:00 |  | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-07-14 08:00 | 2014-08-14 17:00 |  | PT_Normal |  |  |  |  | 3A3JE4PmSYCG3ghQkNoTzw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43240 | N | N | 70 | SOFT LANDSCAPING |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1918 | LABOR- SUBCONTRACTOR
%R | 502394 | 6359 | 124899 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3SAGL5135 | Construction of manholes Drainage | 8177 | 488 | 200 | 200 | 0 | 300 | 300 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-04-10 17:00 |  | 2013-12-31 08:00 | 2014-01-28 17:00 | 2013-12-31 08:00 | 2014-01-28 17:00 | 2013-12-31 08:00 | 2014-01-28 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | D+dtzwhcRFe1HOvoONzVEA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43130 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 300 | LABOR - CIVIL
%R | 502395 | 6359 | 124899 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3SAGL5140 | Construction of soakaways | 8177 | 96 | 0 | 200 | 0 | 212 | 212 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-02-12 17:00 |  | 2013-12-31 08:00 | 2014-01-28 17:00 | 2013-12-31 08:00 | 2014-01-28 17:00 | 2013-12-31 08:00 | 2014-01-28 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 |  | PT_Normal |  |  |  |  | fl9IDva8R9Krz7FlrJcCeg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43130 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 212 | LABOR - CIVIL
%R | 502396 | 6359 | 124899 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3SAGL5145 | Construction of Road gullies | 8177 | 96 | 0 | 200 | 0 | 256 | 256 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-03-13 17:00 |  | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 |  | PT_Normal |  |  |  |  | Bbzi+mJ5Q52wS7NbDoTgzw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43130 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 256 | LABOR - CIVIL
%R | 502397 | 6359 | 124899 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3SAGL5150 | Connection with existing sewer manhole | 8177 | 288 | 224 | 160 | 0 | 300 | 300 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-04 17:00 |  | 2014-03-01 08:00 | 2014-03-23 17:00 | 2014-03-01 08:00 | 2014-03-23 17:00 | 2014-03-01 08:00 | 2014-03-23 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | SHT38IFmTL6EMJEq6QpUxQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43130 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 300 | LABOR - CIVIL
%R | 502398 | 6359 | 124900 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3TCGL5295 | Excavation Telecommunication trenches | 8177 | 64 | 0 | 160 | 0 | 362 | 362 | 160 | 200 | 0 | 200 |  |  |  | 2014-04-12 08:00 | 2014-05-04 17:00 |  | 2014-04-02 08:00 | 2014-04-24 17:00 | 2014-04-02 08:00 | 2014-04-24 17:00 | 2014-04-02 08:00 | 2014-04-24 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | vec2fjxRSLS85J6+8WmelQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43190 | N | N | 45 | TELECOMMUNICATION LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 362 | LABOR - CIVIL
%R | 502399 | 6359 | 124900 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3TCGL5300 | Laying of cables | 8178 | 64 | 0 | 160 | 0 | 556.8 | 556.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-10 17:00 |  | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-04-17 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | RLsxZiJOSXqgvJx1oAQ6uA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43190 | N | N | 45 | TELECOMMUNICATION LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 556.8 | LABOR- SUBCONTRACTOR
%R | 502400 | 6359 | 124900 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3TCGL5305 | Backfilling telecommunication trench | 8177 | 64 | 0 | 160 | 0 | 286 | 286 | 160 | 220 | 0 | 220 |  |  |  | 2014-04-23 08:00 | 2014-05-15 17:00 |  | 2014-04-14 08:00 | 2014-05-06 17:00 | 2014-04-14 08:00 | 2014-05-06 17:00 | 2014-04-14 08:00 | 2014-05-06 17:00 | 2014-04-23 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | 1Ckv/r68TGmheOsc1Vj1Kg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43190 | N | N | 45 | TELECOMMUNICATION LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 286 | LABOR - CIVIL
%R | 502401 | 6359 | 124900 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3TCGL5310 | Connection & Installation | 8178 | 176 | 0 | 160 | 0 | 180.8 | 180.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-07 17:00 |  | 2014-05-20 08:00 | 2014-06-11 17:00 | 2014-05-20 08:00 | 2014-06-11 17:00 | 2014-05-20 08:00 | 2014-06-11 17:00 | 2014-06-15 08:00 | 2014-07-07 17:00 |  | PT_Normal |  |  |  |  | hv+h+9ffT6q8pq+U0eIJNQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43190 | N | N | 45 | TELECOMMUNICATION LINES |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 180.8 | LABOR- SUBCONTRACTOR
%R | 502402 | 6359 | 124901 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3HDGL7020 | Precast Concrete Kerbs works | 8178 | 144 | 0 | 160 | 0 | 1600 | 1600 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-08 17:00 |  | 2014-04-26 08:00 | 2014-05-18 17:00 | 2014-04-26 08:00 | 2014-05-18 17:00 | 2014-04-26 08:00 | 2014-05-18 17:00 | 2014-05-17 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | HTuafNG/RdK3wTWNkqsE5w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43230 | N | N | 65 | HARD LANDSCAPING |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1600 | LABOR- SUBCONTRACTOR
%R | 502403 | 6359 | 124901 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3HDGL7025 | Interlocking for Walkways | 8174 | 144 | 0 | 200 | 0 | 1048 | 1048 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-25 17:00 |  | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43230 | N | N | 65 | HARD LANDSCAPING |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1048 | INTERLOCK MASON SK
%R | 502404 | 6359 | 124901 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3HDGL7030 | Construction of Retaining wall | 8165 | 144 | 0 | 200 | 0 | 252 | 252 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-07-07 17:00 |  | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 |  | PT_Normal |  |  |  |  | CK0tdhQFRBu+OYupCM33Kw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43230 | N | N | 65 | HARD LANDSCAPING |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 252 | STEEL FIXERS SK
%R | 502405 | 6359 | 124901 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3HDGL7035 | Construction of Wash Stone Boulders | 8170 | 144 | 0 | 200 | 0 | 44 | 44 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-07-07 17:00 |  | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 |  | PT_Normal |  |  |  |  | MxvR95lDRfmurm5QOzs7zQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43230 | N | N | 65 | HARD LANDSCAPING |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 44 | TILE MASON SK
%R | 502406 | 6359 | 124901 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z3HDGL7040 | Construction of Speed Humps | 8167 | 184 | 184 | 80 | 0 | 14 | 14 | 80 | 0 | 0 | 0 |  |  |  | 2014-07-31 08:00 | 2014-08-14 17:00 |  | 2014-07-05 08:00 | 2014-07-15 17:00 | 2014-07-05 08:00 | 2014-07-15 17:00 | 2014-07-05 08:00 | 2014-07-15 17:00 | 2014-07-31 08:00 | 2014-08-14 17:00 |  | PT_Normal |  |  |  |  | bqPt+LmVRXCBOtlfrc8+Kg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43230 | N | N | 65 | HARD LANDSCAPING |  | 124888 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 14 | CONCRETE MASON SK
%R | 502407 | 6359 | 124904 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBIWGL7455 | Internal epoxy coating & Painting | 8178 | 120 | 0 | 40 | 0 | 102 | 102 | 40 | 0 | 0 | 0 |  |  |  | 2014-07-26 08:00 | 2014-07-30 17:00 |  | 2014-07-08 08:00 | 2014-07-13 17:00 | 2014-07-08 08:00 | 2014-07-13 17:00 | 2014-07-08 08:00 | 2014-07-13 17:00 | 2014-07-26 08:00 | 2014-07-30 17:00 |  | PT_Normal |  |  |  |  | ftOfeoHeQtGK0E15xV/ApQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43270 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 102 | LABOR- SUBCONTRACTOR
%R | 502408 | 6359 | 124904 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBIWGL7460 | Installation of Steel Ladder | 8178 | 120 | 0 | 40 | 0 | 14 | 14 | 40 | 0 | 0 | 0 |  |  |  | 2014-07-31 08:00 | 2014-08-09 17:00 |  | 2014-07-14 08:00 | 2014-07-19 17:00 | 2014-07-14 08:00 | 2014-07-19 17:00 | 2014-07-14 08:00 | 2014-07-19 17:00 | 2014-07-31 08:00 | 2014-08-09 17:00 |  | PT_Normal |  |  |  |  | Qn0SsdPRT/GVkL1d0VSjuQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43270 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 14 | LABOR- SUBCONTRACTOR
%R | 502409 | 6359 | 124904 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBIWGL7465 | Installation of G.I Handrails | 8178 | 120 | 120 | 40 | 0 | 328 | 328 | 40 | 0 | 0 | 0 |  |  |  | 2014-08-10 08:00 | 2014-08-14 17:00 |  | 2014-07-20 08:00 | 2014-07-24 17:00 | 2014-07-20 08:00 | 2014-07-24 17:00 | 2014-07-20 08:00 | 2014-07-24 17:00 | 2014-08-10 08:00 | 2014-08-14 17:00 |  | PT_Normal |  |  |  |  | xDA5c7ZOQzWSVwpxtqZKOw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43270 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 328 | LABOR- SUBCONTRACTOR
%R | 502410 | 6359 | 124904 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBIWGL7440 | Plumbing , Drainage & Firefighting works | 8178 | 120 | 0 | 200 | 0 | 50.4 | 50.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-26 08:00 | 2014-07-24 17:00 |  | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-26 08:00 | 2014-07-24 17:00 |  | PT_Normal |  |  |  |  | ZA0iS/WNSG+ub2FCzA7gvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43270 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 502411 | 6359 | 124904 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBIWGL7445 | AC Works | 8178 | 120 | 0 | 200 | 0 | 17.2 | 17.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-26 08:00 | 2014-07-24 17:00 |  | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-26 08:00 | 2014-07-24 17:00 |  | PT_Normal |  |  |  |  | Dg10JSCaSAuUkFg5jllU9g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43270 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 17.2 | LABOR- SUBCONTRACTOR
%R | 502412 | 6359 | 124904 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBIWGL7450 | Electrical Works | 8178 | 120 | 0 | 200 | 0 | 325.2 | 325.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-26 08:00 | 2014-07-24 17:00 |  | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-26 08:00 | 2014-07-24 17:00 |  | PT_Normal |  |  |  |  | 8JewE2cBQa2fMNGA/NkYWA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43270 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 325.2 | LABOR- SUBCONTRACTOR
%R | 502413 | 6359 | 124904 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBIWGL7950 | Laying of Interlock | 8174 | 288 | 0 | 80 | 0 | 58 | 58 | 80 | 0 | 0 | 0 |  |  |  | 2014-07-08 08:00 | 2014-07-19 17:00 |  | 2014-05-27 08:00 | 2014-06-07 17:00 | 2014-05-27 08:00 | 2014-06-07 17:00 | 2014-05-27 08:00 | 2014-06-07 17:00 | 2014-07-08 08:00 | 2014-07-19 17:00 |  | PT_Normal |  |  |  |  | YDpIVz7DTby9OWnuXfaqoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43270 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 58 | INTERLOCK MASON SK
%R | 502414 | 6359 | 124904 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBIWGL7435 | Installation of Boundary Fences | 8165 | 288 | 168 | 120 | 0 | 84 | 84 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-20 08:00 | 2014-08-09 17:00 |  | 2014-06-08 08:00 | 2014-06-24 17:00 | 2014-06-08 08:00 | 2014-06-24 17:00 | 2014-06-08 08:00 | 2014-06-24 17:00 | 2014-07-20 08:00 | 2014-08-09 17:00 |  | PT_Normal |  |  |  |  | Gh1cZtPvRiSCYnzGXSPDkw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43270 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 84 | STEEL FIXERS SK
%R | 502415 | 6359 | 124904 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBIWGL7400 | Excavation | 8177 | 120 | 0 | 120 | 0 | 582 | 582 | 120 | 300 | 0 | 300 |  |  |  | 2014-02-23 08:00 | 2014-03-11 17:00 |  | 2014-02-04 08:00 | 2014-02-22 17:00 | 2014-02-04 08:00 | 2014-02-22 17:00 | 2014-02-04 08:00 | 2014-02-22 17:00 | 2014-02-23 08:00 | 2014-03-11 17:00 |  | PT_Normal |  |  |  |  | ajdDHT9QSp25G5VxSACjIw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43270 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 582 | LABOR - CIVIL
%R | 502416 | 6359 | 124904 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBIWGL7405 | Blinding & base waterproofing | 8163 | 120 | 0 | 80 | 0 | 400 | 400 | 80 | 0 | 0 | 0 |  |  |  | 2014-03-12 08:00 | 2014-03-23 17:00 |  | 2014-02-23 08:00 | 2014-03-05 17:00 | 2014-02-23 08:00 | 2014-03-05 17:00 | 2014-02-23 08:00 | 2014-03-05 17:00 | 2014-03-12 08:00 | 2014-03-23 17:00 |  | PT_Normal |  |  |  |  | C+c6DIU4TL6/3ih/mY1H7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43270 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 400 | BLINDING MASON SK
%R | 502417 | 6359 | 124904 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBIWGL7410 | Construction of Raft slab | 8165 | 120 | 0 | 80 | 0 | 1288 | 1288 | 80 | 0 | 0 | 0 |  |  |  | 2014-03-24 08:00 | 2014-04-03 17:00 |  | 2014-03-06 08:00 | 2014-03-17 17:00 | 2014-03-06 08:00 | 2014-03-17 17:00 | 2014-03-06 08:00 | 2014-03-17 17:00 | 2014-03-24 08:00 | 2014-04-03 17:00 |  | PT_Normal |  |  |  |  | MIFyg4w3Sp6c/L37hHn2QQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43270 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1288 | STEEL FIXERS SK
%R | 502418 | 6359 | 124904 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBIWGL7415 | Construction of RCC Wall | 8165 | 120 | 0 | 200 | 0 | 4200 | 4200 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-05 08:00 | 2014-05-03 17:00 |  | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-04-05 08:00 | 2014-05-03 17:00 |  | PT_Normal |  |  |  |  | iQEcomPcRuyVONHEbKxAkw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43270 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 4200 | STEEL FIXERS SK
%R | 502419 | 6359 | 124904 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBIWGL7420 | Construction of Roof Slab | 8165 | 120 | 0 | 160 | 0 | 756 | 756 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-04 08:00 | 2014-05-26 17:00 |  | 2014-04-16 08:00 | 2014-05-08 17:00 | 2014-04-16 08:00 | 2014-05-08 17:00 | 2014-04-16 08:00 | 2014-05-08 17:00 | 2014-05-04 08:00 | 2014-05-26 17:00 |  | PT_Normal |  |  |  |  | BnX7ImbKSleAFGlK/3d80Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43270 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 756 | STEEL FIXERS SK
%R | 502420 | 6359 | 124904 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBIWGL7425 | Waterproofing & Backfilling | 8177 | 168 | 0 | 120 | 0 | 296 | 296 | 120 | 66 | 0 | 66 |  |  |  | 2014-06-03 08:00 | 2014-06-19 17:00 |  | 2014-05-10 08:00 | 2014-05-26 17:00 | 2014-05-10 08:00 | 2014-05-26 17:00 | 2014-05-10 08:00 | 2014-05-26 17:00 | 2014-06-03 08:00 | 2014-06-19 17:00 |  | PT_Normal |  |  |  |  | sW8JNqsuToO0Q4g4kC8fBA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43270 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 296 | LABOR - CIVIL
%R | 502421 | 6359 | 124904 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBIWGL7430 | Floor screed | 8164 | 120 | 0 | 40 | 0 | 146 | 146 | 40 | 0 | 0 | 0 |  |  |  | 2014-06-21 08:00 | 2014-06-25 17:00 |  | 2014-06-03 08:00 | 2014-06-08 17:00 | 2014-06-03 08:00 | 2014-06-08 17:00 | 2014-06-03 08:00 | 2014-06-08 17:00 | 2014-06-21 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | vALLVAQZTlKPITtnMr2S5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43270 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 146 | SCREED MASON SK
%R | 502422 | 6359 | 124905 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBTRGL7600 | Excavation | 8177 | 200 | 0 | 80 | 0 | 32 | 32 | 80 | 20 | 0 | 20 |  |  |  | 2014-03-24 08:00 | 2014-04-03 17:00 |  | 2014-02-23 08:00 | 2014-03-05 17:00 | 2014-02-23 08:00 | 2014-03-05 17:00 | 2014-02-23 08:00 | 2014-03-05 17:00 | 2014-03-24 08:00 | 2014-04-03 17:00 |  | PT_Normal |  |  |  |  | qm1V5ZR/RFqm3I4CThZbZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43280 | N | N | 15 | TELECOMMUNICATION ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 32 | LABOR - CIVIL
%R | 502423 | 6359 | 124905 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBTRGL7605 | Construction of foundation & Grade slab | 8165 | 280 | 0 | 160 | 0 | 280 | 280 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-16 08:00 | 2014-05-08 17:00 |  | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-04-16 08:00 | 2014-05-08 17:00 |  | PT_Normal |  |  |  |  | d89w4jUSR8q6S194ew5yew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43280 | N | N | 15 | TELECOMMUNICATION ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 280 | STEEL FIXERS SK
%R | 502424 | 6359 | 124905 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBTRGL7610 | Construction Column,Beams & Roof Slab | 8165 | 280 | 0 | 160 | 0 | 280 | 280 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-10 08:00 | 2014-06-01 17:00 |  | 2014-03-30 08:00 | 2014-04-21 17:00 | 2014-03-30 08:00 | 2014-04-21 17:00 | 2014-03-30 08:00 | 2014-04-21 17:00 | 2014-05-10 08:00 | 2014-06-01 17:00 |  | PT_Normal |  |  |  |  | Sb4xyRz2TeKwa6RlD63JOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43280 | N | N | 15 | TELECOMMUNICATION ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 280 | STEEL FIXERS SK
%R | 502425 | 6359 | 124905 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBTRGL7615 | Finishing Works | 8164 | 280 | 0 | 200 | 0 | 1000 | 1000 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-26 08:00 | 2014-07-24 17:00 |  | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-06-26 08:00 | 2014-07-24 17:00 |  | PT_Normal |  |  |  |  | mzCpnU0YTdCeUQa6BmRkWg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43280 | N | N | 15 | TELECOMMUNICATION ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1000 | SCREED MASON SK
%R | 502426 | 6359 | 124905 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBTRGL7620 | Plumbing , Drainage & Firefighting works | 8178 | 280 | 0 | 200 | 0 | 282.8 | 282.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-08 08:00 | 2014-08-09 17:00 |  | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-07-08 08:00 | 2014-08-09 17:00 |  | PT_Normal |  |  |  |  | yyiUcmhcRySKAHST6LnC+Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43280 | N | N | 15 | TELECOMMUNICATION ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 282.8 | LABOR- SUBCONTRACTOR
%R | 502427 | 6359 | 124905 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBTRGL7625 | AC Works | 8178 | 280 | 104 | 200 | 0 | 710 | 710 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-08 08:00 | 2014-08-09 17:00 |  | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-07-08 08:00 | 2014-08-09 17:00 |  | PT_Normal |  |  |  |  | K2EZ7xvUTLyeD3kmqtE+4g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43280 | N | N | 15 | TELECOMMUNICATION ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 710 | LABOR- SUBCONTRACTOR
%R | 502428 | 6359 | 124905 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBTRGL7630 | Electrical Works-Telecom Room | 8178 | 176 | 0 | 200 | 0 | 416 | 416 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-08 08:00 | 2014-08-09 17:00 |  | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-07-08 08:00 | 2014-08-09 17:00 |  | PT_Normal |  |  |  |  | FamUPFZJRf2uVphkw8P4HQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43280 | N | N | 15 | TELECOMMUNICATION ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 416 | LABOR- SUBCONTRACTOR
%R | 502429 | 6359 | 124905 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBTRGL7635 | Final Paintings | 8178 | 176 | 176 | 40 | 0 | 275 | 275 | 40 | 0 | 0 | 0 |  |  |  | 2014-08-10 08:00 | 2014-08-14 17:00 |  | 2014-07-12 08:00 | 2014-07-16 17:00 | 2014-07-12 08:00 | 2014-07-16 17:00 | 2014-07-12 08:00 | 2014-07-16 17:00 | 2014-08-10 08:00 | 2014-08-14 17:00 |  | PT_Normal |  |  |  |  | u7LIljwKRmqfnegISdM47A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43280 | N | N | 15 | TELECOMMUNICATION ROOM |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 275 | LABOR- SUBCONTRACTOR
%R | 502430 | 6359 | 124906 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBGHGL7825 | AC Works | 8178 | 200 | 0 | 200 | 0 | 710 | 710 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-08 08:00 | 2014-08-09 17:00 |  | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-07-08 08:00 | 2014-08-09 17:00 |  | PT_Normal |  |  |  |  | Pfsrsd/PT+OWAnR5ne3n7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43290 | N | N | 20 | GUARD HOUSE |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 710 | LABOR- SUBCONTRACTOR
%R | 502431 | 6359 | 124906 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBGHGL7830 | Electrical Works-Telecom Room | 8178 | 200 | 0 | 200 | 0 | 416 | 416 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-08 08:00 | 2014-08-09 17:00 |  | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-07-08 08:00 | 2014-08-09 17:00 |  | PT_Normal |  |  |  |  | ejNlsy1+S4emRWjNry3Mjw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43290 | N | N | 20 | GUARD HOUSE |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 416 | LABOR- SUBCONTRACTOR
%R | 502432 | 6359 | 124906 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBGHGL7835 | Final Paintings | 8178 | 200 | 200 | 40 | 0 | 275 | 275 | 40 | 0 | 0 | 0 |  |  |  | 2014-08-10 08:00 | 2014-08-14 17:00 |  | 2014-07-08 08:00 | 2014-07-13 17:00 | 2014-07-08 08:00 | 2014-07-13 17:00 | 2014-07-08 08:00 | 2014-07-13 17:00 | 2014-08-10 08:00 | 2014-08-14 17:00 |  | PT_Normal |  |  |  |  | V0MCzZfgQlqfZ36Sl+K7Ew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43290 | N | N | 20 | GUARD HOUSE |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 275 | LABOR- SUBCONTRACTOR
%R | 502433 | 6359 | 124906 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBGHGL7800 | Excavation | 8177 | 200 | 0 | 80 | 0 | 32 | 32 | 80 | 20 | 0 | 20 |  |  |  | 2014-04-05 08:00 | 2014-04-15 17:00 |  | 2014-03-06 08:00 | 2014-03-17 17:00 | 2014-03-06 08:00 | 2014-03-17 17:00 | 2014-03-06 08:00 | 2014-03-17 17:00 | 2014-04-05 08:00 | 2014-04-15 17:00 |  | PT_Normal |  |  |  |  | 4Ag0+xQZTZqYSPphRYqETQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43290 | N | N | 20 | GUARD HOUSE |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 32 | LABOR - CIVIL
%R | 502434 | 6359 | 124906 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBGHGL7805 | Construction of foundation & Grade slab | 8165 | 200 | 0 | 160 | 0 | 280 | 280 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-16 08:00 | 2014-05-08 17:00 |  | 2014-03-18 08:00 | 2014-04-09 17:00 | 2014-03-18 08:00 | 2014-04-09 17:00 | 2014-03-18 08:00 | 2014-04-09 17:00 | 2014-04-16 08:00 | 2014-05-08 17:00 |  | PT_Normal |  |  |  |  | SAcqha7dSeyuVxg4V7YNRw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43290 | N | N | 20 | GUARD HOUSE |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 280 | STEEL FIXERS SK
%R | 502435 | 6359 | 124906 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBGHGL7810 | Construction Column,Beams & Roof Slab | 8165 | 200 | 0 | 160 | 0 | 280 | 280 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-10 08:00 | 2014-06-01 17:00 |  | 2014-04-10 08:00 | 2014-05-03 17:00 | 2014-04-10 08:00 | 2014-05-03 17:00 | 2014-04-10 08:00 | 2014-05-03 17:00 | 2014-05-10 08:00 | 2014-06-01 17:00 |  | PT_Normal |  |  |  |  | zLyZhFYrRgqxNBsyQqIENQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43290 | N | N | 20 | GUARD HOUSE |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 280 | STEEL FIXERS SK
%R | 502436 | 6359 | 124906 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBGHGL7815 | Finishing Works | 8164 | 200 | 0 | 200 | 0 | 1000 | 1000 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-26 08:00 | 2014-07-24 17:00 |  | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-06-26 08:00 | 2014-07-24 17:00 |  | PT_Normal |  |  |  |  | k00NaVBUT2yhF/oCWF9Fnw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43290 | N | N | 20 | GUARD HOUSE |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1000 | SCREED MASON SK
%R | 502437 | 6359 | 124906 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBGHGL7820 | Plumbing , Drainage & Firefighting works | 8178 | 200 | 0 | 200 | 0 | 282.8 | 282.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-08 08:00 | 2014-08-09 17:00 |  | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-07-08 08:00 | 2014-08-09 17:00 |  | PT_Normal |  |  |  |  | F4IQJCaQRZ+xtpGMnKZwKQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43290 | N | N | 20 | GUARD HOUSE |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 282.8 | LABOR- SUBCONTRACTOR
%R | 502438 | 6359 | 124907 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBPGGL7940 | Intial Work Play Ground Works | 8178 | 280 | 0 | 240 | 0 | 480 | 480 | 240 | 0 | 0 | 0 |  |  |  | 2014-06-03 08:00 | 2014-07-07 17:00 |  | 2014-04-23 08:00 | 2014-05-27 17:00 | 2014-04-23 08:00 | 2014-05-27 17:00 | 2014-04-23 08:00 | 2014-05-27 17:00 | 2014-06-03 08:00 | 2014-07-07 17:00 |  | PT_Normal |  |  |  |  | FWHhYmJITBCBnE8JxqREeQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43310 | N | N | 30 | PLAY GROUND |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04; period 2: 2014-AP05 |  | 240 | LABOR- SUBCONTRACTOR
%R | 502439 | 6359 | 124907 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBPGGL7945 | Final Work Play Ground Works | 8178 | 280 | 280 | 240 | 0 | 480 | 480 | 240 | 0 | 0 | 0 |  |  |  | 2014-07-08 08:00 | 2014-08-14 17:00 |  | 2014-05-28 08:00 | 2014-07-01 17:00 | 2014-05-28 08:00 | 2014-07-01 17:00 | 2014-05-28 08:00 | 2014-07-01 17:00 | 2014-07-08 08:00 | 2014-08-14 17:00 |  | PT_Normal |  |  |  |  | 6Osov7wFTTqdRgvdPfB28w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43310 | N | N | 30 | PLAY GROUND |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05; period 2: 2014-AP06 |  | 240 | LABOR- SUBCONTRACTOR
%R | 502440 | 6359 | 124908 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBGZGL7900 | Construction of Concrete structure | 8165 | 200 | 0 | 160 | 0 | 124 | 124 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-21 17:00 |  | 2014-03-31 08:00 | 2014-04-22 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 | 2014-04-29 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | N7DQK0HpT26t0bHSqPAmUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43300 | N | N | 25 | GAZEBO |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 124 | STEEL FIXERS SK
%R | 502441 | 6359 | 124908 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBGZGL7905 | Installation of Wooden Works | 8178 | 200 | 0 | 200 | 0 | 300 | 300 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-06-08 17:00 |  | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | XCEO2s9oTaKS7QrycXJLOg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43300 | N | N | 25 | GAZEBO |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 300 | LABOR- SUBCONTRACTOR
%R | 502442 | 6359 | 124908 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBGZGL7910 | Electrical Works-Gazebo | 8178 | 200 | 56 | 120 | 0 | 125.6 | 125.6 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-06-25 17:00 |  | 2014-05-11 08:00 | 2014-05-27 17:00 | 2014-05-11 08:00 | 2014-05-27 17:00 | 2014-05-11 08:00 | 2014-05-27 17:00 | 2014-06-09 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | KZSoOYx7SnGUdilvnK9bvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43300 | N | N | 25 | GAZEBO |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 125.6 | LABOR- SUBCONTRACTOR
%R | 502443 | 6359 | 124908 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03SBGZGL7915 | Park Benches Installation | 8178 | 200 | 0 | 200 | 0 | 200 | 200 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-06-08 17:00 |  | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | /yzCgk+1TBiJiRaShOLTSg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43300 | N | N | 25 | GAZEBO |  | 124903 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 200 | LABOR- SUBCONTRACTOR
%R | 502444 | 6359 | 124911 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2SAGL5135 | Construction of manholes Drainage | 8177 | 512 | 144 | 200 | 0 | 344 | 344 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-25 08:00 | 2014-02-23 17:00 |  | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-11-10 08:00 | 2013-12-08 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | fCV8B5ZtRgW5w9PIOPhrqg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42980 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 344 | LABOR - CIVIL
%R | 502445 | 6359 | 124911 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2SAGL5140 | Construction of soakaways | 8177 | 104 | 0 | 200 | 0 | 242 | 242 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-25 08:00 | 2013-12-24 17:00 |  | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-11-25 08:00 | 2013-12-24 17:00 |  | PT_Normal |  |  |  |  | b13ohVibR2eIQdzPDqNSPA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42980 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 242 | LABOR - CIVIL
%R | 502446 | 6359 | 124911 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2SAGL5145 | Construction of Road gullies | 8177 | 104 | 0 | 200 | 0 | 286 | 286 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-25 08:00 | 2014-01-22 17:00 |  | 2013-12-09 08:00 | 2014-01-07 17:00 | 2013-12-09 08:00 | 2014-01-07 17:00 | 2013-12-09 08:00 | 2014-01-07 17:00 | 2013-12-25 08:00 | 2014-01-22 17:00 |  | PT_Normal |  |  |  |  | P0cyDP9XR+26z1z1urMmsA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42980 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 286 | LABOR - CIVIL
%R | 502447 | 6359 | 124911 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2SAGL5150 | Connection with existing sewer manhole | 8177 | 312 | 232 | 160 | 0 | 344 | 344 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-18 17:00 |  | 2014-01-08 08:00 | 2014-01-30 17:00 | 2014-01-08 08:00 | 2014-01-30 17:00 | 2014-01-08 08:00 | 2014-01-30 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | L8GbhBnoTcCLUuQeySnNtQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42980 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 344 | LABOR - CIVIL
%R | 502448 | 6359 | 124912 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2DRGL5115 | Excavation for Drainage line | 8177 | 96 | 0 | 200 | 0 | 736 | 736 | 200 | 400 | 0 | 400 |  |  |  | 2013-10-22 08:00 | 2013-11-19 17:00 |  | 2013-10-06 08:00 | 2013-11-05 17:00 | 2013-10-06 08:00 | 2013-11-05 17:00 | 2013-10-06 08:00 | 2013-11-05 17:00 | 2013-10-22 08:00 | 2013-11-19 17:00 |  | PT_Normal |  |  |  |  | thLsau3bTT6zh+i+ufZMng |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42970 | N | N | 10 | DRAINAGE LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 736 | LABOR - CIVIL
%R | 502449 | 6359 | 124912 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2DRGL5120 | Laying of Drainage line | 8178 | 96 | 0 | 200 | 0 | 772.8 | 772.8 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-29 08:00 | 2013-11-26 17:00 |  | 2013-10-13 08:00 | 2013-11-12 17:00 | 2013-10-13 08:00 | 2013-11-12 17:00 | 2013-10-13 08:00 | 2013-11-12 17:00 | 2013-10-29 08:00 | 2013-11-26 17:00 |  | PT_Normal |  |  |  |  | IUCmVE41Tx2SZxnDMPfU+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42970 | N | N | 10 | DRAINAGE LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 772.8 | LABOR- SUBCONTRACTOR
%R | 502450 | 6359 | 124912 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2DRGL5125 | Testing of Drainage line | 8178 | 96 | 0 | 200 | 0 | 772.8 | 772.8 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-06 08:00 | 2013-12-04 17:00 |  | 2013-10-23 08:00 | 2013-11-20 17:00 | 2013-10-23 08:00 | 2013-11-20 17:00 | 2013-10-23 08:00 | 2013-11-20 17:00 | 2013-11-06 08:00 | 2013-12-04 17:00 |  | PT_Normal |  |  |  |  | tk5erEq9S/qp3hHeI7QEyA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42970 | N | N | 10 | DRAINAGE LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 772.8 | LABOR- SUBCONTRACTOR
%R | 502451 | 6359 | 124912 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2DRGL5130 | Backfilling Drainage line | 8177 | 96 | 0 | 120 | 0 | 468 | 468 | 120 | 330 | 0 | 330 |  |  |  | 2013-11-24 08:00 | 2013-12-10 17:00 |  | 2013-11-10 08:00 | 2013-11-26 17:00 | 2013-11-10 08:00 | 2013-11-26 17:00 | 2013-11-10 08:00 | 2013-11-26 17:00 | 2013-11-24 08:00 | 2013-12-10 17:00 |  | PT_Normal |  |  |  |  | KbHuorrURh66GImTq5s5Bw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42970 | N | N | 10 | DRAINAGE LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 468 | LABOR - CIVIL
%R | 502452 | 6359 | 124913 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2PSGL7000 | Excavation | 8177 | 240 | 40 | 120 | 0 | 37 | 37 | 120 | 31 | 0 | 31 |  |  |  | 2014-05-22 08:00 | 2014-06-08 17:00 |  | 2014-04-17 08:00 | 2014-05-04 17:00 | 2014-04-17 08:00 | 2014-05-04 17:00 | 2014-04-17 08:00 | 2014-05-04 17:00 | 2014-05-22 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | EahB18KRTTicV1XrhxadHg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43070 | N | N | 60 | PARKING SHED |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 37 | LABOR - CIVIL
%R | 502453 | 6359 | 124913 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2PSGL7005 | Foundation casting | 8165 | 200 | 0 | 120 | 0 | 1276 | 1276 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-14 17:00 |  | 2014-04-29 08:00 | 2014-05-15 17:00 | 2014-04-29 08:00 | 2014-05-15 17:00 | 2014-04-29 08:00 | 2014-05-15 17:00 | 2014-05-28 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | 12g4bgvbQm6E0RHkgLLaKA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43070 | N | N | 60 | PARKING SHED |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1276 | STEEL FIXERS SK
%R | 502454 | 6359 | 124913 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2PSGL7010 | Column, Frame& Fabrics Erection | 8178 | 200 | 0 | 200 | 0 | 428 | 428 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-07-07 17:00 |  | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 |  | PT_Normal |  |  |  |  | lq+/z7aVTHer3MH6ETnmVw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43070 | N | N | 60 | PARKING SHED |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 428 | LABOR- SUBCONTRACTOR
%R | 502455 | 6359 | 124913 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2PSGL7015 | Electrical Works-Parking Shed | 8178 | 200 | 136 | 200 | 0 | 189.2 | 189.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-13 17:00 |  | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 |  | PT_Normal |  |  |  |  | SxQn8taCSoqh41h/4Of4eA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43070 | N | N | 60 | PARKING SHED |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 189.2 | LABOR- SUBCONTRACTOR
%R | 502456 | 6359 | 124914 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2WSGL5155 | Excavation for water line | 8177 | 104 | 0 | 200 | 0 | 974 | 974 | 200 | 500 | 0 | 500 |  |  |  | 2013-12-07 08:00 | 2014-01-05 17:00 |  | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-12-07 08:00 | 2014-01-05 17:00 |  | PT_Normal |  |  |  |  | k/u2WFiHRY+eOM6yPBZ68g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42990 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11; period 2: 2013-AP12 |  | 487 | LABOR - CIVIL
%R | 502457 | 6359 | 124914 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2WSGL5160 | Laying of water line | 8178 | 104 | 0 | 200 | 0 | 1093.2 | 1093.2 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-12 08:00 | 2014-01-11 17:00 |  | 2013-11-27 08:00 | 2013-12-26 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 | 2013-12-12 08:00 | 2014-01-11 17:00 |  | PT_Normal |  |  |  |  | M6Am1KMHRqmHvr1OpmFaXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42990 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1093.2 | LABOR- SUBCONTRACTOR
%R | 502458 | 6359 | 124914 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2WSGL5165 | Testing of potable water line | 8178 | 104 | 0 | 200 | 0 | 552 | 552 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-19 08:00 | 2014-01-16 17:00 |  | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-19 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | A/OkVI36TuiwsZE/DPszZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42990 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 552 | LABOR- SUBCONTRACTOR
%R | 502459 | 6359 | 124914 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2WSGL5170 | Backfilling potable water line | 8177 | 104 | 0 | 200 | 0 | 742 | 742 | 200 | 550 | 0 | 550 |  |  |  | 2013-12-25 08:00 | 2014-01-22 17:00 |  | 2013-12-09 08:00 | 2014-01-07 17:00 | 2013-12-09 08:00 | 2014-01-07 17:00 | 2013-12-09 08:00 | 2014-01-07 17:00 | 2013-12-25 08:00 | 2014-01-22 17:00 |  | PT_Normal |  |  |  |  | 2m5TAaOqTh+2bxmjBTanMA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42990 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 742 | LABOR - CIVIL
%R | 502460 | 6359 | 124914 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2WSGL5175 | Construction of valve chambers & Thrust Blocks | 8177 | 272 | 0 | 200 | 0 | 80 | 80 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-25 08:00 | 2014-02-23 17:00 |  | 2013-12-15 08:00 | 2014-01-13 17:00 | 2013-12-15 08:00 | 2014-01-13 17:00 | 2013-12-15 08:00 | 2014-01-13 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | a9cnWSA8SWqC2YhdvGq35g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42990 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 80 | LABOR - CIVIL
%R | 502461 | 6359 | 124914 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2WSGL5180 | Installation of meter ,Accessories & Connection | 8178 | 272 | 96 | 160 | 0 | 33.6 | 33.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-18 17:00 |  | 2014-01-14 08:00 | 2014-02-05 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | jW6R37PoQiaG0zIzeQAwrQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42990 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 33.6 | LABOR- SUBCONTRACTOR
%R | 502462 | 6359 | 124915 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2HDGL7020 | Precast Concrete Kerbs works | 8178 | 200 | 0 | 160 | 0 | 1872 | 1872 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-04-28 17:00 |  | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | z6qB/OJBQWexHj1oCnTsog |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43080 | N | N | 65 | HARD LANDSCAPING |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1872 | LABOR- SUBCONTRACTOR
%R | 502463 | 6359 | 124915 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2HDGL7025 | Interlocking for Walkways | 8174 | 200 | 0 | 200 | 0 | 1210 | 1210 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | Boy9hBETRHa300t+A9dGwQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43080 | N | N | 65 | HARD LANDSCAPING |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1210 | INTERLOCK MASON SK
%R | 502464 | 6359 | 124915 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2HDGL7030 | Construction of Retaining wall | 8165 | 200 | 0 | 200 | 0 | 294 | 294 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-27 17:00 |  | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | FPF3yCLsTuWaLGozZwDxxQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43080 | N | N | 65 | HARD LANDSCAPING |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 294 | STEEL FIXERS SK
%R | 502465 | 6359 | 124915 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2HDGL7040 | Construction of Speed Humps | 8167 | 440 | 256 | 80 | 0 | 14 | 14 | 80 | 0 | 0 | 0 |  |  |  | 2014-07-20 08:00 | 2014-07-30 17:00 |  | 2014-05-17 08:00 | 2014-05-27 17:00 | 2014-05-17 08:00 | 2014-05-27 17:00 | 2014-05-17 08:00 | 2014-05-27 17:00 | 2014-07-20 08:00 | 2014-07-30 17:00 |  | PT_Normal |  |  |  |  | e3tR/mbOQ/+EWV64YlO4IA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43080 | N | N | 65 | HARD LANDSCAPING |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 14 | CONCRETE MASON SK
%R | 502466 | 6359 | 124915 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2HDGL7035 | Construction of Wash Stone Boulders | 8170 | 200 | 0 | 200 | 0 | 50 | 50 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-27 17:00 |  | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | Chz/hh3DSjOppELB6mOsBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43080 | N | N | 65 | HARD LANDSCAPING |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 50 | TILE MASON SK
%R | 502467 | 6359 | 124916 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2TCGL5295 | Excavation Telecommunication trenches | 8177 | 80 | 0 | 160 | 0 | 386 | 386 | 160 | 200 | 0 | 200 |  |  |  | 2014-02-24 08:00 | 2014-03-18 17:00 |  | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | OopEoUgAS7ihIZY087UW6w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43040 | N | N | 45 | TELECOMMUNICATION LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 386 | LABOR - CIVIL
%R | 502468 | 6359 | 124916 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2TCGL5300 | Laying of cables | 8178 | 80 | 0 | 160 | 0 | 653.2 | 653.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-24 17:00 |  | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43040 | N | N | 45 | TELECOMMUNICATION LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 653.2 | LABOR- SUBCONTRACTOR
%R | 502469 | 6359 | 124916 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2TCGL5305 | Backfilling telecommunication trench | 8177 | 80 | 0 | 160 | 0 | 298 | 298 | 160 | 220 | 0 | 220 |  |  |  | 2014-03-08 08:00 | 2014-03-30 17:00 |  | 2014-02-24 08:00 | 2014-03-18 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | PbVBhaNNQUegc/p1g6hIsg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43040 | N | N | 45 | TELECOMMUNICATION LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 298 | LABOR - CIVIL
%R | 502470 | 6359 | 124916 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2TCGL5310 | Connection & Installation | 8178 | 176 | 0 | 160 | 0 | 203.2 | 203.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-22 08:00 | 2014-06-14 17:00 |  | 2014-04-27 08:00 | 2014-05-19 17:00 | 2014-04-27 08:00 | 2014-05-19 17:00 | 2014-04-27 08:00 | 2014-05-19 17:00 | 2014-05-22 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | 0q8iSm7rQnqbemw8bYJE/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43040 | N | N | 45 | TELECOMMUNICATION LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 203.2 | LABOR- SUBCONTRACTOR
%R | 502471 | 6359 | 124917 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2RWGL6020 | Laying of Road Base Asphalt Concrete | 8178 | 200 | 0 | 40 | 0 | 186 | 186 | 40 | 150 | 0 | 150 |  |  |  | 2014-06-03 08:00 | 2014-06-08 17:00 |  | 2014-05-05 08:00 | 2014-05-10 17:00 | 2014-05-05 08:00 | 2014-05-10 17:00 | 2014-05-05 08:00 | 2014-05-10 17:00 | 2014-06-03 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | +WpK51rRQ/+6RsFdTMLorA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43060 | N | N | 55 | ROAD WORKS |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 186 | LABOR- SUBCONTRACTOR
%R | 502472 | 6359 | 124917 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2RWGL6025 | Laying of Asphalt Wearing Coarse | 8178 | 320 | 0 | 40 | 0 | 186 | 186 | 40 | 150 | 0 | 150 |  |  |  | 2014-06-26 08:00 | 2014-07-01 17:00 |  | 2014-05-11 08:00 | 2014-05-15 17:00 | 2014-05-11 08:00 | 2014-05-15 17:00 | 2014-05-11 08:00 | 2014-05-15 17:00 | 2014-06-26 08:00 | 2014-07-01 17:00 |  | PT_Normal |  |  |  |  | BjeWuqC0RaWRZXHmD4YAbQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43060 | N | N | 55 | ROAD WORKS |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 186 | LABOR- SUBCONTRACTOR
%R | 502473 | 6359 | 124917 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2RWGL6030 | Traffic Signage & Road Marking | 8178 | 320 | 120 | 40 | 0 | 424 | 424 | 40 | 0 | 0 | 0 |  |  |  | 2014-07-02 08:00 | 2014-07-07 17:00 |  | 2014-05-17 08:00 | 2014-05-21 17:00 | 2014-05-17 08:00 | 2014-05-21 17:00 | 2014-05-17 08:00 | 2014-05-21 17:00 | 2014-07-02 08:00 | 2014-07-07 17:00 |  | PT_Normal |  |  |  |  | W2oVfnPZRMajLUGiR4So0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43060 | N | N | 55 | ROAD WORKS |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 424 | LABOR- SUBCONTRACTOR
%R | 502474 | 6359 | 124917 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2RWGL6000 | Excavation & Earth Filling | 8177 | 80 | 0 | 80 | 0 | 1782 | 1782 | 80 | 600 | 0 | 600 |  |  |  | 2014-03-19 08:00 | 2014-03-30 17:00 |  | 2014-03-08 08:00 | 2014-03-18 17:00 | 2014-03-08 08:00 | 2014-03-18 17:00 | 2014-03-08 08:00 | 2014-03-18 17:00 | 2014-03-19 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | sg2/BZ50TNGCuEhxAcXDww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43060 | N | N | 55 | ROAD WORKS |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1782 | LABOR - CIVIL
%R | 502475 | 6359 | 124917 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2RWGL6005 | Laying of Sub Grade | 8178 | 80 | 0 | 200 | 0 | 36 | 36 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-28 17:00 |  | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | dPij54bKSnGfP+mFrNgF6g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43060 | N | N | 55 | ROAD WORKS |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 36 | LABOR- SUBCONTRACTOR
%R | 502476 | 6359 | 124917 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2RWGL6010 | Laying of Precast Kerbs | 8178 | 80 | 0 | 200 | 0 | 1178 | 1178 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-10 17:00 |  | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | igvqy9XmSlO7sKbAl0TkVQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43060 | N | N | 55 | ROAD WORKS |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1178 | LABOR- SUBCONTRACTOR
%R | 502477 | 6359 | 124917 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2RWGL6015 | Laying of Granular Sub Base Coarse | 8178 | 80 | 0 | 160 | 0 | 636 | 636 | 160 | 600 | 0 | 600 |  |  |  | 2014-04-23 08:00 | 2014-05-15 17:00 |  | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-04-23 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | NlRoyFpLRyqD/Yen0Js8fQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43060 | N | N | 55 | ROAD WORKS |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 636 | LABOR- SUBCONTRACTOR
%R | 502478 | 6359 | 124918 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2STGL5235 | Excavation for Street lighting | 8177 | 80 | 0 | 200 | 0 | 69 | 69 | 200 | 51 | 0 | 51 |  |  |  | 2014-01-30 08:00 | 2014-03-01 17:00 |  | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | EHEqCjQeQt+8uRCzurNgEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43020 | N | N | 35 | STREET LIGHTING |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 69 | LABOR - CIVIL
%R | 502479 | 6359 | 124918 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2STGL5240 | Construction of Duct Banks | 8178 | 80 | 0 | 200 | 0 | 1380.4 | 1380.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-03-06 17:00 |  | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-02-05 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | ggFdg3NSRyKR+e8lNWilEQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43020 | N | N | 35 | STREET LIGHTING |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1380.4 | LABOR- SUBCONTRACTOR
%R | 502480 | 6359 | 124918 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2STGL5245 | Construction of Foundation | 8177 | 80 | 0 | 200 | 0 | 696 | 696 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-03-06 17:00 |  | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-02-05 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | HbcLZT9MQc6WYmnWuc/zmA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43020 | N | N | 35 | STREET LIGHTING |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 696 | LABOR - CIVIL
%R | 502481 | 6359 | 124918 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2STGL5250 | Backfilling Street Lighting | 8177 | 80 | 0 | 200 | 0 | 67 | 67 | 200 | 55 | 0 | 55 |  |  |  | 2014-02-12 08:00 | 2014-03-12 17:00 |  | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 |  | PT_Normal |  |  |  |  | IDt+1x76R+Kpg/xT2eNJqw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43020 | N | N | 35 | STREET LIGHTING |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01; period 2: 2014-AP03 |  | 33.5 | LABOR - CIVIL
%R | 502482 | 6359 | 124918 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2STGL5255 | Installation of light Post | 8178 | 584 | 136 | 200 | 0 | 233.2 | 233.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-08 08:00 | 2014-06-05 17:00 |  | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-05-08 08:00 | 2014-06-05 17:00 |  | PT_Normal |  |  |  |  | 6CEyaU2wTKiF7KVGCvEEoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43020 | N | N | 35 | STREET LIGHTING |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 116.6 | LABOR- SUBCONTRACTOR
%R | 502483 | 6359 | 124918 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2STGL5260 | Electrical Works | 8178 | 424 | 136 | 200 | 0 | 556.8 | 556.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | kBxaKh8IReSDWdrx4kb3sg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43020 | N | N | 35 | STREET LIGHTING |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 556.8 | LABOR- SUBCONTRACTOR
%R | 502484 | 6359 | 124919 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2ELGL5215 | Excavation Cable Trenches & Duct Banks | 8167 | 80 | 0 | 200 | 0 | 3883.2 | 3883.2 | 200 | 1000 | 0 | 1000 |  |  |  | 2014-01-30 08:00 | 2014-03-01 17:00 |  | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | z9RZ9csiQVCztZr9O3/sZg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43010 | N | N | 30 | ELECTRICAL LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 3883.2 | CONCRETE MASON SK
%R | 502485 | 6359 | 124919 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2ELGL5220 | Laying of electrical cables | 8178 | 104 | 0 | 200 | 0 | 6492.4 | 6492.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-03-10 17:00 |  | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | Csh9zgdFTB2k5pw03f9jrQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43010 | N | N | 30 | ELECTRICAL LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 6492.4 | LABOR- SUBCONTRACTOR
%R | 502486 | 6359 | 124919 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2ELGL5225 | Backfilling Electrical trench | 8177 | 104 | 0 | 200 | 0 | 2030 | 2030 | 200 | 1100 | 0 | 1100 |  |  |  | 2014-02-18 08:00 | 2014-03-18 17:00 |  | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | iWAJpOUDRm6Ql9zUO9pMHg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43010 | N | N | 30 | ELECTRICAL LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 1015 | LABOR - CIVIL
%R | 502487 | 6359 | 124919 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2ELGL5230 | Construction of Submain Board & Feeder Pillar | 8165 | 424 | 0 | 200 | 0 | 574 | 574 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | /8Vh/HOlThGoer2M5LKY3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43010 | N | N | 30 | ELECTRICAL LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 287 | STEEL FIXERS SK
%R | 502488 | 6359 | 124920 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2SLGL7200 | Excavation | 8177 | 200 | 0 | 200 | 0 | 87 | 87 | 200 | 51 | 0 | 51 |  |  |  | 2014-05-11 08:00 | 2014-06-08 17:00 |  | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | OXh536H/Qz+2db+XZkkdzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43090 | N | N | 70 | SOFT LANDSCAPING |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 87 | LABOR - CIVIL
%R | 502489 | 6359 | 124920 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2SLGL7205 | Sweet Soil Laying | 8178 | 200 | 0 | 200 | 0 | 1498 | 1498 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-22 08:00 | 2014-06-19 17:00 |  | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 |  | PT_Normal |  |  |  |  | vL6OkRHUQ7eohlpcY89mEQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43090 | N | N | 70 | SOFT LANDSCAPING |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1498 | LABOR- SUBCONTRACTOR
%R | 502490 | 6359 | 124920 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2SLGL7210 | Plantation works | 8178 | 280 | 136 | 200 | 0 | 2240 | 2240 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-15 08:00 | 2014-07-13 17:00 |  | 2014-05-05 08:00 | 2014-06-02 17:00 | 2014-05-05 08:00 | 2014-06-02 17:00 | 2014-05-05 08:00 | 2014-06-02 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 |  | PT_Normal |  |  |  |  | Nw9BumXdTcuv48PIT46HDw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43090 | N | N | 70 | SOFT LANDSCAPING |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 2240 | LABOR- SUBCONTRACTOR
%R | 502491 | 6359 | 124921 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2BWGL5315 | Construction of Boundary Wall (Ht-3m) | 8165 | 288 | 0 | 200 | 0 | 182 | 182 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-26 08:00 | 2014-04-23 17:00 |  | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 |  | PT_Normal |  |  |  |  | xIgWuULyTE24IZoJacyrjg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43050 | N | N | 50 | BOUNDARY WALL |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 91 | STEEL FIXERS SK
%R | 502492 | 6359 | 124921 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 8306 | 288 | 136 | 200 | 0 | 14 | 14 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-10 17:00 |  | 2014-03-01 08:00 | 2014-03-29 17:00 | 2014-03-01 08:00 | 2014-03-29 17:00 | 2014-03-01 08:00 | 2014-03-29 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | I8atnK5RQWa1mLBYsS7CXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 45950 |  |  |  |  | GATE ERECTOR SK | S313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43050 | N | N | 50 | BOUNDARY WALL |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 14 | GATE ERECTOR SK
%R | 502493 | 6359 | 124922 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2IRGL5265 | Excavation for irrigation line | 8177 | 168 | 0 | 200 | 0 | 866 | 866 | 200 | 500 | 0 | 500 |  |  |  | 2014-03-29 08:00 | 2014-04-26 17:00 |  | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-29 08:00 | 2014-04-26 17:00 |  | PT_Normal |  |  |  |  | W6FbYw3ER5OJb8yhOTTdYw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43030 | N | N | 40 | IRRIGATION LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 866 | LABOR - CIVIL
%R | 502494 | 6359 | 124922 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2IRGL5270 | Laying of irrigationline | 8178 | 168 | 0 | 200 | 0 | 1360.8 | 1360.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-03 08:00 | 2014-05-01 17:00 |  | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | HTaX52XCSA+tRoV6knM0YA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43030 | N | N | 40 | IRRIGATION LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1360.8 | LABOR- SUBCONTRACTOR
%R | 502495 | 6359 | 124922 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2IRGL5275 | Testing of irrigation line | 8178 | 168 | 0 | 200 | 0 | 1203.6 | 1203.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-09 08:00 | 2014-05-07 17:00 |  | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 |  | PT_Normal |  |  |  |  | RzaFxYRrRdCIjUA7dlJPIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43030 | N | N | 40 | IRRIGATION LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1203.6 | LABOR- SUBCONTRACTOR
%R | 502496 | 6359 | 124922 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2IRGL5280 | Backfilling irrigation line | 8177 | 168 | 0 | 200 | 0 | 700 | 700 | 200 | 550 | 0 | 550 |  |  |  | 2014-04-15 08:00 | 2014-05-13 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 |  | PT_Normal |  |  |  |  | 4gQ3tcbQTaeLWibUXieg3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43030 | N | N | 40 | IRRIGATION LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 700 | LABOR - CIVIL
%R | 502497 | 6359 | 124922 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2IRGL5285 | Construction of Thrust Blocks,Pull boxes | 8165 | 208 | 0 | 200 | 0 | 628 | 628 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-03 08:00 | 2014-05-31 17:00 |  | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 |  | PT_Normal |  |  |  |  | BcneHKkUQF+Wt7vnaBag7Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43030 | N | N | 40 | IRRIGATION LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 628 | STEEL FIXERS SK
%R | 502498 | 6359 | 124922 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2IRGL5290 | Irrigation Fittings (Nozzle,Values) | 8178 | 208 | 8 | 200 | 0 | 355 | 355 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-06-08 17:00 |  | 2014-04-10 08:00 | 2014-05-08 17:00 | 2014-04-10 08:00 | 2014-05-08 17:00 | 2014-04-10 08:00 | 2014-05-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | BCmeuAlYTN6hcPiRTbdU2A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43030 | N | N | 40 | IRRIGATION LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 355 | LABOR- SUBCONTRACTOR
%R | 502499 | 6359 | 124923 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2FFGL5195 | Testing of firefighting line | 8178 | 64 | 0 | 200 | 0 | 265.2 | 265.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-02-12 17:00 |  | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 |  | PT_Normal |  |  |  |  | kSvpwwoGTUOKL6rsOSwh0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43000 | N | N | 25 | FIREFIGHTING LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 265.2 | LABOR- SUBCONTRACTOR
%R | 502500 | 6359 | 124923 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2FFGL5200 | Backfilling firefighting line | 8177 | 64 | 0 | 200 | 0 | 365 | 365 | 200 | 275 | 0 | 275 |  |  |  | 2014-01-20 08:00 | 2014-02-18 17:00 |  | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 |  | PT_Normal |  |  |  |  | w0ie/AR2STuzfmyYi2EJSQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43000 | N | N | 25 | FIREFIGHTING LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 365 | LABOR - CIVIL
%R | 502501 | 6359 | 124923 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2FFGL5205 | Construction of valve chambers & Thrust Blocks | 8165 | 176 | 0 | 200 | 0 | 78 | 78 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-12 17:00 |  | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 |  | PT_Normal |  |  |  |  | jFF2m+wSRSytD1dPMzMCLQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43000 | N | N | 25 | FIREFIGHTING LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 78 | STEEL FIXERS SK
%R | 502502 | 6359 | 124923 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2FFGL5210 | Connection with existing Firewater System | 8165 | 176 | 96 | 200 | 0 | 78 | 78 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-18 17:00 |  | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | dXay9XyUTCqJDGsGcvIv0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43000 | N | N | 25 | FIREFIGHTING LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 78 | STEEL FIXERS SK
%R | 502503 | 6359 | 124923 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2FFGL5185 | Excavation for firefighting line | 8177 | 64 | 0 | 200 | 0 | 473 | 473 | 200 | 251 | 0 | 251 |  |  |  | 2013-12-31 08:00 | 2014-01-28 17:00 |  | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-31 08:00 | 2014-01-28 17:00 |  | PT_Normal |  |  |  |  | UgiGMe2MTEOCFiNj4tTgDQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43000 | N | N | 25 | FIREFIGHTING LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 473 | LABOR - CIVIL
%R | 502504 | 6359 | 124923 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z2FFGL5190 | Laying of firefighting line | 8178 | 64 | 0 | 200 | 0 | 513.6 | 513.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-08 08:00 | 2014-02-05 17:00 |  | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | WQdjGplDQpS2KO022PjZAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 43000 | N | N | 25 | FIREFIGHTING LINES |  | 124910 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 513.6 | LABOR- SUBCONTRACTOR
%R | 502505 | 6359 | 124926 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1DRGL5115 | Excavation for Drainage line | 8177 | 40 | 0 | 200 | 0 | 736 | 736 | 200 | 400 | 0 | 400 |  |  |  | 2013-08-22 08:00 | 2013-09-19 17:00 |  | 2013-08-17 08:00 | 2013-09-14 17:00 | 2013-08-17 08:00 | 2013-09-14 17:00 | 2013-08-17 08:00 | 2013-09-14 17:00 | 2013-08-22 08:00 | 2013-09-19 17:00 |  | PT_Normal |  |  |  |  | 3QvjLyqwSrGwbdbQCoOJGw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42820 | N | N | 10 | DRAINAGE LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 736 | LABOR - CIVIL
%R | 502506 | 6359 | 124926 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1DRGL5120 | Laying of Drainage line | 8178 | 96 | 0 | 200 | 0 | 772.8 | 772.8 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-07 08:00 | 2013-10-05 17:00 |  | 2013-08-24 08:00 | 2013-09-21 17:00 | 2013-08-24 08:00 | 2013-09-21 17:00 | 2013-08-24 08:00 | 2013-09-21 17:00 | 2013-09-07 08:00 | 2013-10-05 17:00 |  | PT_Normal |  |  |  |  | Rwcq3jzmQqKZqmphjtMFzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42820 | N | N | 10 | DRAINAGE LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 772.8 | LABOR- SUBCONTRACTOR
%R | 502507 | 6359 | 124926 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1DRGL5125 | Testing of Drainage line | 8178 | 96 | 0 | 200 | 0 | 772.8 | 772.8 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-15 08:00 | 2013-10-13 17:00 |  | 2013-09-01 08:00 | 2013-09-29 17:00 | 2013-09-01 08:00 | 2013-09-29 17:00 | 2013-09-01 08:00 | 2013-09-29 17:00 | 2013-09-15 08:00 | 2013-10-13 17:00 |  | PT_Normal |  |  |  |  | BhGDvf7GTMWxOKJW4wfQVQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42820 | N | N | 10 | DRAINAGE LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 772.8 | LABOR- SUBCONTRACTOR
%R | 502508 | 6359 | 124926 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1DRGL5130 | Backfilling Drainage line | 8177 | 96 | 0 | 120 | 0 | 468 | 468 | 120 | 330 | 0 | 330 |  |  |  | 2013-10-02 08:00 | 2013-10-21 17:00 |  | 2013-09-18 08:00 | 2013-10-05 17:00 | 2013-09-18 08:00 | 2013-10-05 17:00 | 2013-09-18 08:00 | 2013-10-05 17:00 | 2013-10-02 08:00 | 2013-10-21 17:00 |  | PT_Normal |  |  |  |  | N1YKcZjATSqLU39HvVIEnw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42820 | N | N | 10 | DRAINAGE LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 468 | LABOR - CIVIL
%R | 502509 | 6359 | 124927 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1FFGL5195 | Testing of firefighting line | 8178 | 64 | 0 | 200 | 0 | 265.2 | 265.2 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-25 08:00 | 2013-12-24 17:00 |  | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-25 08:00 | 2013-12-24 17:00 |  | PT_Normal |  |  |  |  | xCaVigKxTUecTLDFgFEA4g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42850 | N | N | 25 | FIREFIGHTING LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 265.2 | LABOR- SUBCONTRACTOR
%R | 502510 | 6359 | 124927 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1FFGL5200 | Backfilling firefighting line | 8177 | 64 | 0 | 200 | 0 | 365 | 365 | 200 | 275 | 0 | 275 |  |  |  | 2013-12-01 08:00 | 2013-12-30 17:00 |  | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-12-01 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | CiAF1O/jSs+OB+/m+ACWfw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42850 | N | N | 25 | FIREFIGHTING LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11; period 2: 2013-AP12 |  | 182.5 | LABOR - CIVIL
%R | 502511 | 6359 | 124927 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1FFGL5205 | Construction of valve chambers & Thrust Blocks | 8165 | 120 | 0 | 200 | 0 | 78 | 78 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-26 08:00 | 2014-01-23 17:00 |  | 2013-12-08 08:00 | 2014-01-06 17:00 | 2013-12-08 08:00 | 2014-01-06 17:00 | 2013-12-08 08:00 | 2014-01-06 17:00 | 2013-12-26 08:00 | 2014-01-23 17:00 |  | PT_Normal |  |  |  |  | lysNLRwpTvWFW5QvHZr6ig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42850 | N | N | 25 | FIREFIGHTING LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 78 | STEEL FIXERS SK
%R | 502512 | 6359 | 124927 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1FFGL5210 | Connection with existing Firewater System | 8165 | 120 | 24 | 200 | 0 | 78 | 78 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-01 08:00 | 2014-01-29 17:00 |  | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2014-01-01 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | AyYPjOumQoWu1nQrHs0FKw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42850 | N | N | 25 | FIREFIGHTING LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 78 | STEEL FIXERS SK
%R | 502513 | 6359 | 124927 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1FFGL5185 | Excavation for firefighting line | 8177 | 112 | 48 | 200 | 0 | 473 | 473 | 200 | 251 | 0 | 251 |  |  |  | 2013-11-11 08:00 | 2013-12-09 17:00 |  | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-11-11 08:00 | 2013-12-09 17:00 |  | PT_Normal |  |  |  |  | WO1aDtMeQcmBssrXVnyL7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42850 | N | N | 25 | FIREFIGHTING LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 473 | LABOR - CIVIL
%R | 502514 | 6359 | 124927 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1FFGL5190 | Laying of firefighting line | 8178 | 64 | 0 | 200 | 0 | 513.6 | 513.6 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-19 08:00 | 2013-12-17 17:00 |  | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-11-19 08:00 | 2013-12-17 17:00 |  | PT_Normal |  |  |  |  | K5l2o86xRded0TlcoyDNeg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42850 | N | N | 25 | FIREFIGHTING LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 513.6 | LABOR- SUBCONTRACTOR
%R | 502515 | 6359 | 124928 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1SLGL7200 | Excavation | 8177 | 248 | 0 | 200 | 0 | 87 | 87 | 200 | 51 | 0 | 51 |  |  |  | 2014-03-31 08:00 | 2014-04-28 17:00 |  | 2014-02-23 08:00 | 2014-03-23 17:00 | 2014-02-23 08:00 | 2014-03-23 17:00 | 2014-02-23 08:00 | 2014-03-23 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | CMiqaYd/TsqhkYtw8Pb7KQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42940 | N | N | 70 | SOFT LANDSCAPING |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 43.5 | LABOR - CIVIL
%R | 502516 | 6359 | 124928 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1SLGL7205 | Sweet Soil Laying | 8178 | 248 | 0 | 200 | 0 | 1498 | 1498 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-10 17:00 |  | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | EyuNI2AeRAyA73Z2W3LM0A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42940 | N | N | 70 | SOFT LANDSCAPING |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1498 | LABOR- SUBCONTRACTOR
%R | 502517 | 6359 | 124928 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1SLGL7210 | Plantation works | 8178 | 408 | 128 | 200 | 0 | 2240 | 2240 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | hMvc0ItURWC6W2s59Ez+yQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42940 | N | N | 70 | SOFT LANDSCAPING |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 2240 | LABOR- SUBCONTRACTOR
%R | 502518 | 6359 | 124929 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1SAGL5135 | Construction of manholes Drainage | 8177 | 536 | 144 | 200 | 0 | 344 | 344 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-08 08:00 | 2014-01-06 17:00 |  | 2013-09-18 08:00 | 2013-10-16 17:00 | 2013-09-18 08:00 | 2013-10-16 17:00 | 2013-09-18 08:00 | 2013-10-16 17:00 | 2013-12-08 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | 9h7eq0rPRliLUmmTw6EhoA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42830 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 344 | LABOR - CIVIL
%R | 502519 | 6359 | 124929 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1SAGL5140 | Construction of soakaways | 8177 | 112 | 0 | 200 | 0 | 242 | 242 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-05 08:00 | 2013-11-04 17:00 |  | 2013-09-18 08:00 | 2013-10-16 17:00 | 2013-09-18 08:00 | 2013-10-16 17:00 | 2013-09-18 08:00 | 2013-10-16 17:00 | 2013-10-05 08:00 | 2013-11-04 17:00 |  | PT_Normal |  |  |  |  | rmRM6qdhRuu7ykuwEBPKrA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42830 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 242 | LABOR - CIVIL
%R | 502520 | 6359 | 124929 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1SAGL5145 | Construction of Road gullies | 8177 | 112 | 0 | 200 | 0 | 286 | 286 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-05 08:00 | 2013-12-03 17:00 |  | 2013-10-20 08:00 | 2013-11-17 17:00 | 2013-10-20 08:00 | 2013-11-17 17:00 | 2013-10-20 08:00 | 2013-11-17 17:00 | 2013-11-05 08:00 | 2013-12-03 17:00 |  | PT_Normal |  |  |  |  | ejLvsyoyR6+NQwCbXB8a0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42830 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 286 | LABOR - CIVIL
%R | 502521 | 6359 | 124929 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1SAGL5150 | Connection with existing sewer manhole | 8177 | 336 | 240 | 160 | 0 | 344 | 344 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-07 08:00 | 2014-01-29 17:00 |  | 2013-11-18 08:00 | 2013-12-10 17:00 | 2013-11-18 08:00 | 2013-12-10 17:00 | 2013-11-18 08:00 | 2013-12-10 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | pLdl9UBHRmyCPCA0CtA3sw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42830 | N | N | 15 | MANHOLES & SOAKAWAY |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 344 | LABOR - CIVIL
%R | 502522 | 6359 | 124930 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1IRGL5265 | Excavation for irrigation line | 8177 | 168 | 0 | 200 | 0 | 866 | 866 | 200 | 500 | 0 | 500 |  |  |  | 2014-02-09 08:00 | 2014-03-10 17:00 |  | 2014-01-15 08:00 | 2014-02-13 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | MEn020ToSoKSqVPT/981Bw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42880 | N | N | 40 | IRRIGATION LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 866 | LABOR - CIVIL
%R | 502523 | 6359 | 124930 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1IRGL5270 | Laying of irrigationline | 8178 | 168 | 0 | 200 | 0 | 1360.8 | 1360.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-16 17:00 |  | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | ldw2vuSgRyObMqrw02ShXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42880 | N | N | 40 | IRRIGATION LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1360.8 | LABOR- SUBCONTRACTOR
%R | 502524 | 6359 | 124930 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1IRGL5275 | Testing of irrigation line | 8178 | 168 | 0 | 200 | 0 | 1203.6 | 1203.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-22 17:00 |  | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | pv45SSIrRuetglpy2W5Kgg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42880 | N | N | 40 | IRRIGATION LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1203.6 | LABOR- SUBCONTRACTOR
%R | 502525 | 6359 | 124930 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1IRGL5280 | Backfilling irrigation line | 8177 | 168 | 0 | 200 | 0 | 700 | 700 | 200 | 550 | 0 | 550 |  |  |  | 2014-02-27 08:00 | 2014-03-27 17:00 |  | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 |  | PT_Normal |  |  |  |  | KQbyoPfyRsy4OUbyLO+Lyw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42880 | N | N | 40 | IRRIGATION LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 350 | LABOR - CIVIL
%R | 502526 | 6359 | 124930 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1IRGL5285 | Construction of Thrust Blocks,Pull boxes | 8165 | 248 | 0 | 200 | 0 | 628 | 628 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-23 08:00 | 2014-04-20 17:00 |  | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | iy2dSsMNR6SQKcKkqlzvLQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42880 | N | N | 40 | IRRIGATION LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 314 | STEEL FIXERS SK
%R | 502527 | 6359 | 124930 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1IRGL5290 | Irrigation Fittings (Nozzle,Values) | 8178 | 248 | 0 | 200 | 0 | 355 | 355 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-28 17:00 |  | 2014-02-23 08:00 | 2014-03-23 17:00 | 2014-02-23 08:00 | 2014-03-23 17:00 | 2014-02-23 08:00 | 2014-03-23 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | vVAH2v2uSQaTe8TGuVfT9g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42880 | N | N | 40 | IRRIGATION LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 177.5 | LABOR- SUBCONTRACTOR
%R | 502528 | 6359 | 124931 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1BWGL5315 | Construction of Boundary Wall (Ht-3m) | 8165 | 424 | 0 | 200 | 0 | 182 | 182 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-25 08:00 | 2014-03-25 17:00 |  | 2013-12-24 08:00 | 2014-01-21 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 |  | PT_Normal |  |  |  |  | FrJrJ1jfR8Krb/fXEMU2fg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:45 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42900 | N | N | 50 | BOUNDARY WALL |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 182 | STEEL FIXERS SK
%R | 502529 | 6359 | 124931 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 8306 | 424 | 136 | 200 | 0 | 14 | 14 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-04-10 17:00 |  | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | PptPZUA9RjSCCiCk87Np5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:45 | admin | admin | 8149 |  |  |  |  | 45950 |  |  |  |  | GATE ERECTOR SK | S313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42900 | N | N | 50 | BOUNDARY WALL |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 14 | GATE ERECTOR SK
%R | 502530 | 6359 | 124932 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1RWGL6000 | Excavation & Earth Filling | 8177 | 96 | 0 | 80 | 0 | 1782 | 1782 | 80 | 600 | 0 | 600 |  |  |  | 2014-01-30 08:00 | 2014-02-10 17:00 |  | 2014-01-16 08:00 | 2014-01-27 17:00 | 2014-01-16 08:00 | 2014-01-27 17:00 | 2014-01-16 08:00 | 2014-01-27 17:00 | 2014-01-30 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | x6h7oYv/S3C8C/ssCoXjNA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42910 | N | N | 55 | ROAD WORKS |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1782 | LABOR - CIVIL
%R | 502531 | 6359 | 124932 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1RWGL6005 | Laying of Sub Grade | 8178 | 96 | 0 | 200 | 0 | 36 | 36 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-12 17:00 |  | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 |  | PT_Normal |  |  |  |  | 2XVso0OTRKmlC6D5/9qN1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42910 | N | N | 55 | ROAD WORKS |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 36 | LABOR- SUBCONTRACTOR
%R | 502532 | 6359 | 124932 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1RWGL6010 | Laying of Precast Kerbs | 8178 | 96 | 0 | 200 | 0 | 1178 | 1178 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-24 17:00 |  | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | 7f6SIPUKTJao+RYzRPT59A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42910 | N | N | 55 | ROAD WORKS |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 589 | LABOR- SUBCONTRACTOR
%R | 502533 | 6359 | 124932 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1RWGL6015 | Laying of Granular Sub Base Coarse | 8178 | 96 | 0 | 160 | 0 | 636 | 636 | 160 | 600 | 0 | 600 |  |  |  | 2014-03-08 08:00 | 2014-03-30 17:00 |  | 2014-02-22 08:00 | 2014-03-16 17:00 | 2014-02-22 08:00 | 2014-03-16 17:00 | 2014-02-22 08:00 | 2014-03-16 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | 2NLI4LjJQmeB9wWX5XVryw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42910 | N | N | 55 | ROAD WORKS |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 636 | LABOR- SUBCONTRACTOR
%R | 502534 | 6359 | 124932 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1RWGL6020 | Laying of Road Base Asphalt Concrete | 8178 | 176 | 0 | 40 | 0 | 186 | 186 | 40 | 150 | 0 | 150 |  |  |  | 2014-04-12 08:00 | 2014-04-16 17:00 |  | 2014-03-17 08:00 | 2014-03-22 17:00 | 2014-03-17 08:00 | 2014-03-22 17:00 | 2014-03-17 08:00 | 2014-03-22 17:00 | 2014-04-12 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | wKPCN9QfQO+w8BGVp9KUXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42910 | N | N | 55 | ROAD WORKS |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 186 | LABOR- SUBCONTRACTOR
%R | 502535 | 6359 | 124932 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1RWGL6025 | Laying of Asphalt Wearing Coarse | 8178 | 296 | 0 | 40 | 0 | 186 | 186 | 40 | 150 | 0 | 150 |  |  |  | 2014-05-05 08:00 | 2014-05-10 17:00 |  | 2014-03-23 08:00 | 2014-03-27 17:00 | 2014-03-23 08:00 | 2014-03-27 17:00 | 2014-03-23 08:00 | 2014-03-27 17:00 | 2014-05-05 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | 7Ylalp8PTGSzM1bfRH59Bg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42910 | N | N | 55 | ROAD WORKS |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 186 | LABOR- SUBCONTRACTOR
%R | 502536 | 6359 | 124932 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1RWGL6030 | Traffic Signage & Road Marking | 8178 | 296 | 120 | 40 | 0 | 424 | 424 | 40 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-05-15 17:00 |  | 2014-03-29 08:00 | 2014-04-02 17:00 | 2014-03-29 08:00 | 2014-04-02 17:00 | 2014-03-29 08:00 | 2014-04-02 17:00 | 2014-05-11 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | /2EVt3RkRPeQTeZuyM65bQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42910 | N | N | 55 | ROAD WORKS |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 424 | LABOR- SUBCONTRACTOR
%R | 502537 | 6359 | 124933 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1WSGL5155 | Excavation for water line | 8177 | 112 | 0 | 200 | 0 | 974 | 974 | 200 | 500 | 0 | 500 |  |  |  | 2013-10-16 08:00 | 2013-11-16 17:00 |  | 2013-09-30 08:00 | 2013-10-30 17:00 | 2013-09-30 08:00 | 2013-10-30 17:00 | 2013-09-30 08:00 | 2013-10-30 17:00 | 2013-10-16 08:00 | 2013-11-16 17:00 |  | PT_Normal |  |  |  |  | k3sE3Ir2S1enANs+2RM+7g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42840 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 487 | LABOR - CIVIL
%R | 502538 | 6359 | 124933 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1WSGL5160 | Laying of water line | 8178 | 112 | 0 | 200 | 0 | 1093.2 | 1093.2 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-24 08:00 | 2013-11-21 17:00 |  | 2013-10-06 08:00 | 2013-11-05 17:00 | 2013-10-06 08:00 | 2013-11-05 17:00 | 2013-10-06 08:00 | 2013-11-05 17:00 | 2013-10-24 08:00 | 2013-11-21 17:00 |  | PT_Normal |  |  |  |  | uEhZHBI0TeyooZ7sOKAv5w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42840 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1093.2 | LABOR- SUBCONTRACTOR
%R | 502539 | 6359 | 124933 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1WSGL5165 | Testing of potable water line | 8178 | 112 | 0 | 200 | 0 | 552 | 552 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-30 08:00 | 2013-11-27 17:00 |  | 2013-10-12 08:00 | 2013-11-11 17:00 | 2013-10-12 08:00 | 2013-11-11 17:00 | 2013-10-12 08:00 | 2013-11-11 17:00 | 2013-10-30 08:00 | 2013-11-27 17:00 |  | PT_Normal |  |  |  |  | FUA+yaQIRyyexGhZiP7hhg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42840 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 552 | LABOR- SUBCONTRACTOR
%R | 502540 | 6359 | 124933 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1WSGL5170 | Backfilling potable water line | 8177 | 112 | 0 | 200 | 0 | 742 | 742 | 200 | 550 | 0 | 550 |  |  |  | 2013-11-05 08:00 | 2013-12-03 17:00 |  | 2013-10-20 08:00 | 2013-11-17 17:00 | 2013-10-20 08:00 | 2013-11-17 17:00 | 2013-10-20 08:00 | 2013-11-17 17:00 | 2013-11-05 08:00 | 2013-12-03 17:00 |  | PT_Normal |  |  |  |  | BXFephrORdq1K6lWqhDILg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42840 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 742 | LABOR - CIVIL
%R | 502541 | 6359 | 124933 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1WSGL5175 | Construction of valve chambers & Thrust Blocks | 8177 | 296 | 0 | 200 | 0 | 80 | 80 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-08 08:00 | 2014-01-06 17:00 |  | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-12-08 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | gfYObYY/QESrRdVQSpy2uA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42840 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 80 | LABOR - CIVIL
%R | 502542 | 6359 | 124933 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1WSGL5180 | Installation of meter ,Accessories & Connection | 8178 | 296 | 176 | 160 | 0 | 33.6 | 33.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-07 08:00 | 2014-01-29 17:00 |  | 2013-11-24 08:00 | 2013-12-16 17:00 | 2013-11-24 08:00 | 2013-12-16 17:00 | 2013-11-24 08:00 | 2013-12-16 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | 6eYvgblATDG88BrcLZmECg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42840 | N | N | 20 | WATER SUPPLY SYSTEM |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 33.6 | LABOR- SUBCONTRACTOR
%R | 502543 | 6359 | 124934 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1TCGL5295 | Excavation Telecommunication trenches | 8177 | 96 | 0 | 160 | 0 | 386 | 386 | 160 | 200 | 0 | 200 |  |  |  | 2014-01-07 08:00 | 2014-01-29 17:00 |  | 2013-12-24 08:00 | 2014-01-15 17:00 | 2013-12-24 08:00 | 2014-01-15 17:00 | 2013-12-24 08:00 | 2014-01-15 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | GaZ7TLUYSYuzqwjGsR8FBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42890 | N | N | 45 | TELECOMMUNICATION LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 386 | LABOR - CIVIL
%R | 502544 | 6359 | 124934 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1TCGL5300 | Laying of cables | 8178 | 96 | 0 | 160 | 0 | 653.2 | 653.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-02-04 17:00 |  | 2013-12-30 08:00 | 2014-01-21 17:00 | 2013-12-30 08:00 | 2014-01-21 17:00 | 2013-12-30 08:00 | 2014-01-21 17:00 | 2014-01-13 08:00 | 2014-02-04 17:00 |  | PT_Normal |  |  |  |  | XGdtfn2MTLe8sieuszcvTQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42890 | N | N | 45 | TELECOMMUNICATION LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 653.2 | LABOR- SUBCONTRACTOR
%R | 502545 | 6359 | 124934 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1TCGL5305 | Backfilling telecommunication trench | 8177 | 96 | 0 | 160 | 0 | 298 | 298 | 160 | 220 | 0 | 220 |  |  |  | 2014-01-19 08:00 | 2014-02-10 17:00 |  | 2014-01-05 08:00 | 2014-01-27 17:00 | 2014-01-05 08:00 | 2014-01-27 17:00 | 2014-01-05 08:00 | 2014-01-27 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | 3t70o+Z3T7mvWI4pnmDQdw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42890 | N | N | 45 | TELECOMMUNICATION LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 298 | LABOR - CIVIL
%R | 502546 | 6359 | 124934 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1TCGL5310 | Connection & Installation | 8178 | 176 | 0 | 160 | 0 | 203.2 | 203.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-21 17:00 |  | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-04-29 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | mEkHP+/USIibEopGVZRVNg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42890 | N | N | 45 | TELECOMMUNICATION LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 203.2 | LABOR- SUBCONTRACTOR
%R | 502547 | 6359 | 124935 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1ELGL5230 | Construction of Submain Board & Feeder Pillar | 8165 | 384 | 0 | 200 | 0 | 574 | 574 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-24 17:00 |  | 2013-12-29 08:00 | 2014-01-26 17:00 | 2013-12-29 08:00 | 2014-01-26 17:00 | 2013-12-29 08:00 | 2014-01-26 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | 9l6UfVg1RVe3xdG45v+pRA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42860 | N | N | 30 | ELECTRICAL LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 574 | STEEL FIXERS SK
%R | 502548 | 6359 | 124935 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1ELGL5215 | Excavation Cable Trenches & Duct Banks | 8167 | 96 | 0 | 200 | 0 | 3883.2 | 3883.2 | 200 | 1000 | 0 | 1000 |  |  |  | 2013-12-14 08:00 | 2014-01-12 17:00 |  | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 |  | PT_Normal |  |  |  |  | 1GPpDsjIQo2wH7k8yVN8GQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42860 | N | N | 30 | ELECTRICAL LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 3883.2 | CONCRETE MASON SK
%R | 502549 | 6359 | 124935 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1ELGL5220 | Laying of electrical cables | 8178 | 104 | 0 | 200 | 0 | 6492.4 | 6492.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-22 08:00 | 2014-01-19 17:00 |  | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 |  | PT_Normal |  |  |  |  | aqv4i9QXTzyS72Lpg818HA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42860 | N | N | 30 | ELECTRICAL LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 6492.4 | LABOR- SUBCONTRACTOR
%R | 502550 | 6359 | 124935 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1ELGL5225 | Backfilling Electrical trench | 8177 | 104 | 0 | 200 | 0 | 2030 | 2030 | 200 | 1100 | 0 | 1100 |  |  |  | 2014-01-01 08:00 | 2014-01-29 17:00 |  | 2013-12-16 08:00 | 2014-01-14 17:00 | 2013-12-16 08:00 | 2014-01-14 17:00 | 2013-12-16 08:00 | 2014-01-14 17:00 | 2014-01-01 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | i1cNVFAMQuWGL2+0kvcDeg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42860 | N | N | 30 | ELECTRICAL LINES |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 2030 | LABOR - CIVIL
%R | 502551 | 6359 | 124936 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1HDGL7020 | Precast Concrete Kerbs works | 8178 | 256 | 0 | 160 | 0 | 1872 | 1872 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-18 17:00 |  | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | 44CTOGysQguAxgF1Oi265w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42930 | N | N | 65 | HARD LANDSCAPING |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1872 | LABOR- SUBCONTRACTOR
%R | 502552 | 6359 | 124936 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1HDGL7025 | Interlocking for Walkways | 8174 | 256 | 0 | 200 | 0 | 1210 | 1210 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-04-05 17:00 |  | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-03-08 08:00 | 2014-04-05 17:00 |  | PT_Normal |  |  |  |  | saKx2X4gQoefpUCO6zR+6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42930 | N | N | 65 | HARD LANDSCAPING |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1210 | INTERLOCK MASON SK
%R | 502553 | 6359 | 124936 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1HDGL7030 | Construction of Retaining wall | 8165 | 256 | 0 | 200 | 0 | 294 | 294 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | 4IDa3P4FSh+60+WtONl0Ig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42930 | N | N | 65 | HARD LANDSCAPING |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 147 | STEEL FIXERS SK
%R | 502554 | 6359 | 124936 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1HDGL7035 | Construction of Wash Stone Boulders | 8170 | 256 | 8 | 200 | 0 | 50 | 50 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | mpBu8sy6R4yOOVZZA1vKgg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42930 | N | N | 65 | HARD LANDSCAPING |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 25 | TILE MASON SK
%R | 502555 | 6359 | 124936 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1HDGL7040 | Construction of Speed Humps | 8167 | 456 | 48 | 80 | 0 | 14 | 14 | 80 | 0 | 0 | 0 |  |  |  | 2014-06-03 08:00 | 2014-06-14 17:00 |  | 2014-03-29 08:00 | 2014-04-08 17:00 | 2014-03-29 08:00 | 2014-04-08 17:00 | 2014-03-29 08:00 | 2014-04-08 17:00 | 2014-06-03 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | ySubaCwUQdmfUfcrD7rDEQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42930 | N | N | 65 | HARD LANDSCAPING |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 14 | CONCRETE MASON SK
%R | 502556 | 6359 | 124937 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1PSGL7000 | Excavation | 8177 | 216 | 40 | 120 | 0 | 37 | 37 | 120 | 31 | 0 | 31 |  |  |  | 2014-03-31 08:00 | 2014-04-16 17:00 |  | 2014-02-27 08:00 | 2014-03-16 17:00 | 2014-02-27 08:00 | 2014-03-16 17:00 | 2014-02-27 08:00 | 2014-03-16 17:00 | 2014-03-31 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | gc+DJlJISkKuSfKi/d37IA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42920 | N | N | 60 | PARKING SHED |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 37 | LABOR - CIVIL
%R | 502557 | 6359 | 124937 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1PSGL7005 | Foundation casting | 8165 | 176 | 0 | 120 | 0 | 1276 | 1276 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-04-22 17:00 |  | 2014-03-11 08:00 | 2014-03-27 17:00 | 2014-03-11 08:00 | 2014-03-27 17:00 | 2014-03-11 08:00 | 2014-03-27 17:00 | 2014-04-06 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | dGgSTmSbTAusXev/sRjqlA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42920 | N | N | 60 | PARKING SHED |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1276 | STEEL FIXERS SK
%R | 502558 | 6359 | 124937 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1PSGL7010 | Column, Frame& Fabrics Erection | 8178 | 176 | 0 | 200 | 0 | 428 | 428 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-03-23 08:00 | 2014-04-20 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | RL/4SrpATEmdcvN8IdI4yA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42920 | N | N | 60 | PARKING SHED |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 428 | LABOR- SUBCONTRACTOR
%R | 502559 | 6359 | 124937 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1PSGL7015 | Electrical Works-Parking Shed | 8178 | 176 | 0 | 200 | 0 | 189.2 | 189.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-05-21 17:00 |  | 2014-03-29 08:00 | 2014-04-26 17:00 | 2014-03-29 08:00 | 2014-04-26 17:00 | 2014-03-29 08:00 | 2014-04-26 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | GcI1H+TZTlObjR2/2ou+Eg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42920 | N | N | 60 | PARKING SHED |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 189.2 | LABOR- SUBCONTRACTOR
%R | 502560 | 6359 | 124938 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1STGL5235 | Excavation for Street lighting | 8177 | 96 | 0 | 200 | 0 | 69 | 69 | 200 | 51 | 0 | 51 |  |  |  | 2013-12-14 08:00 | 2014-01-12 17:00 |  | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 |  | PT_Normal |  |  |  |  | lj6x1LEcT2yaNQesMpD1pA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42870 | N | N | 35 | STREET LIGHTING |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 69 | LABOR - CIVIL
%R | 502561 | 6359 | 124938 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1STGL5240 | Construction of Duct Banks | 8178 | 96 | 0 | 200 | 0 | 1380.4 | 1380.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-21 08:00 | 2014-01-18 17:00 |  | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | r8L/Iu2xScG8QMUj4e6x1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42870 | N | N | 35 | STREET LIGHTING |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1380.4 | LABOR- SUBCONTRACTOR
%R | 502562 | 6359 | 124938 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1STGL5245 | Construction of Foundation | 8177 | 96 | 0 | 200 | 0 | 696 | 696 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-21 08:00 | 2014-01-18 17:00 |  | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | o/yCAyX4R5Sw/7TQ5XcsZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42870 | N | N | 35 | STREET LIGHTING |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 696 | LABOR - CIVIL
%R | 502563 | 6359 | 124938 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1STGL5250 | Backfilling Street Lighting | 8177 | 96 | 0 | 200 | 0 | 67 | 67 | 200 | 55 | 0 | 55 |  |  |  | 2013-12-26 08:00 | 2014-01-23 17:00 |  | 2013-12-11 08:00 | 2014-01-09 17:00 | 2013-12-11 08:00 | 2014-01-09 17:00 | 2013-12-11 08:00 | 2014-01-09 17:00 | 2013-12-26 08:00 | 2014-01-23 17:00 |  | PT_Normal |  |  |  |  | xLuOBOU4QwS5NkX/FYHMew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42870 | N | N | 35 | STREET LIGHTING |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 67 | LABOR - CIVIL
%R | 502564 | 6359 | 124938 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1STGL5255 | Installation of light Post | 8178 | 424 | 0 | 200 | 0 | 233.2 | 233.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-14 17:00 |  | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 |  | PT_Normal |  |  |  |  | gVhDeNJjQhaPL2Ar1epsqQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42870 | N | N | 35 | STREET LIGHTING |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 233.2 | LABOR- SUBCONTRACTOR
%R | 502565 | 6359 | 124938 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI03Z1STGL5260 | Electrical Works | 8178 | 384 | 120 | 200 | 0 | 556.8 | 556.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-25 08:00 | 2014-04-22 17:00 |  | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | yQjVWLMISs+/BVRRL3EEoA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 42870 | N | N | 35 | STREET LIGHTING |  | 124925 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 556.8 | LABOR- SUBCONTRACTOR
%R | 502566 | 6359 | 124941 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 304 | 304 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | iWQ4Cl54SdmwRf1pTh4UQw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39500 | N | N | 30 | TESTING AND COMMISSIONING |  | 124940 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 502567 | 6359 | 124941 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 304 | 304 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | KoHvLHfmTvKnDPwSYkUa/w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39500 | N | N | 30 | TESTING AND COMMISSIONING |  | 124940 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 502568 | 6359 | 124941 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 304 | 304 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | iqBk+OEUT3Kd5BCug/y1AQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39500 | N | N | 30 | TESTING AND COMMISSIONING |  | 124940 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 502569 | 6359 | 124944 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3PLRF4350 | Installation of Rain water Pipes | 8178 | 280 | 40 | 120 | 0 | 265.2 | 265.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-10 17:00 |  | 2014-01-11 08:00 | 2014-01-27 17:00 | 2014-01-11 08:00 | 2014-01-27 17:00 | 2014-01-11 08:00 | 2014-01-27 17:00 | 2014-02-22 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39390 | N | N | 20 | ROOF |  | 124943 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 265.2 | LABOR- SUBCONTRACTOR
%R | 502570 | 6359 | 124945 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 40 | 0 | 160 | 0 | 1435.2 | 1435.2 | 160 | 0 | 0 | 0 |  |  |  | 2013-09-21 08:00 | 2013-10-13 17:00 |  | 2013-09-15 08:00 | 2013-10-07 17:00 | 2013-09-15 08:00 | 2013-10-07 17:00 | 2013-09-15 08:00 | 2013-10-07 17:00 | 2013-09-21 08:00 | 2013-10-13 17:00 |  | PT_Normal |  |  |  |  | k71p+M+VS6y+sxl4WFlWOw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39370 | N | N | 10 | GROUND FLOOR |  | 124943 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1435.2 | LABOR- SUBCONTRACTOR
%R | 502571 | 6359 | 124945 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3PLGF4310 | Installation of Drainage pipes &testing | 8178 | 240 | 32 | 144 | 0 | 72 | 72 | 144 | 0 | 0 | 0 |  |  |  | 2013-10-24 08:00 | 2013-11-13 17:00 |  | 2013-09-17 08:00 | 2013-10-07 17:00 | 2013-09-17 08:00 | 2013-10-07 17:00 | 2013-09-17 08:00 | 2013-10-07 17:00 | 2013-10-24 08:00 | 2013-11-13 17:00 |  | PT_Normal |  |  |  |  | 8YGi1P+sRRyiNqgU1utnmw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39370 | N | N | 10 | GROUND FLOOR |  | 124943 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 72 | LABOR- SUBCONTRACTOR
%R | 502572 | 6359 | 124945 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3PLGF4320 | Installation of Water Heater | 8178 | 376 | 72 | 120 | 0 | 151.2 | 151.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-15 17:00 |  | 2014-03-05 08:00 | 2014-03-22 17:00 | 2014-03-05 08:00 | 2014-03-22 17:00 | 2014-03-05 08:00 | 2014-03-22 17:00 | 2014-04-29 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | UlynoELGQ/S4QsV9UgO3Sg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39370 | N | N | 10 | GROUND FLOOR |  | 124943 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 151.2 | LABOR- SUBCONTRACTOR
%R | 502573 | 6359 | 124945 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 16 | 0 | 160 | 0 | 182.4 | 182.4 | 160 | 0 | 0 | 0 |  |  |  | 2013-06-06 08:00 | 2013-06-29 17:00 |  | 2013-06-04 08:00 | 2013-06-26 17:00 | 2013-06-04 08:00 | 2013-06-26 17:00 | 2013-06-04 08:00 | 2013-06-26 17:00 | 2013-06-06 08:00 | 2013-06-29 17:00 |  | PT_Normal |  |  |  |  | 3PElPEWzRZKuYI1AeTDtQw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39370 | N | N | 10 | GROUND FLOOR |  | 124943 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 182.4 | LABOR- SUBCONTRACTOR
%R | 502574 | 6359 | 124945 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3PLGF4315 | Sanitary Fittings & Accessories | 8178 | 56 | 0 | 160 | 0 | 218.4 | 218.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-24 17:00 |  | 2014-02-22 08:00 | 2014-03-16 17:00 | 2014-02-22 08:00 | 2014-03-16 17:00 | 2014-02-22 08:00 | 2014-03-16 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | tEvPdIlwTSK4+MSkpprg7g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39370 | N | N | 10 | GROUND FLOOR |  | 124943 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 218.4 | LABOR- SUBCONTRACTOR
%R | 502575 | 6359 | 124947 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 40 | 0 | 160 | 0 | 594.8 | 594.8 | 160 | 0 | 0 | 0 |  |  |  | 2013-09-21 08:00 | 2013-10-13 17:00 |  | 2013-09-15 08:00 | 2013-10-07 17:00 | 2013-09-15 08:00 | 2013-10-07 17:00 | 2013-09-15 08:00 | 2013-10-07 17:00 | 2013-09-21 08:00 | 2013-10-13 17:00 |  | PT_Normal |  |  |  |  | zChqxi7ETL2RmeS9R/+gjA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39330 | N | N | 10 | GROUND FLOOR |  | 124946 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 594.8 | LABOR- SUBCONTRACTOR
%R | 502576 | 6359 | 124947 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ELGF4005 | Cable tray & trunking installation | 8178 | 104 | 0 | 160 | 0 | 2044.8 | 2044.8 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-23 08:00 | 2013-12-15 17:00 |  | 2013-11-07 08:00 | 2013-11-30 17:00 | 2013-11-07 08:00 | 2013-11-30 17:00 | 2013-11-07 08:00 | 2013-11-30 17:00 | 2013-11-23 08:00 | 2013-12-15 17:00 |  | PT_Normal |  |  |  |  | Il+ws9wITZye41YtFUOZxQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39330 | N | N | 10 | GROUND FLOOR |  | 124946 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 2044.8 | LABOR- SUBCONTRACTOR
%R | 502577 | 6359 | 124947 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ELGF4010 | Installation of wiring & Main Cabling | 8178 | 104 | 56 | 160 | 0 | 414.8 | 414.8 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-01 08:00 | 2013-12-24 17:00 |  | 2013-11-16 08:00 | 2013-12-08 17:00 | 2013-11-16 08:00 | 2013-12-08 17:00 | 2013-11-16 08:00 | 2013-12-08 17:00 | 2013-12-01 08:00 | 2013-12-24 17:00 |  | PT_Normal |  |  |  |  | AnnSDabySQa/Nrop121Rmw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39330 | N | N | 10 | GROUND FLOOR |  | 124946 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 414.8 | LABOR- SUBCONTRACTOR
%R | 502578 | 6359 | 124947 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 120 | 0 | 160 | 0 | 170.4 | 170.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-28 08:00 | 2014-02-20 17:00 |  | 2014-01-11 08:00 | 2014-02-02 17:00 | 2014-01-11 08:00 | 2014-02-02 17:00 | 2014-01-11 08:00 | 2014-02-02 17:00 | 2014-01-28 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | G2uS28WPQg2fm/bTNHRXbA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39330 | N | N | 10 | GROUND FLOOR |  | 124946 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 170.4 | LABOR- SUBCONTRACTOR
%R | 502579 | 6359 | 124947 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 120 | 0 | 160 | 0 | 395.6 | 395.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-03-04 17:00 |  | 2014-01-22 08:00 | 2014-02-15 17:00 | 2014-01-22 08:00 | 2014-02-15 17:00 | 2014-01-22 08:00 | 2014-02-15 17:00 | 2014-02-09 08:00 | 2014-03-04 17:00 |  | PT_Normal |  |  |  |  | edxNk1GWTJisCzuOnu0f2A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39330 | N | N | 10 | GROUND FLOOR |  | 124946 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 395.6 | LABOR- SUBCONTRACTOR
%R | 502580 | 6359 | 124947 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 104 | 0 | 160 | 0 | 1108.8 | 1108.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-30 17:00 |  | 2014-02-20 08:00 | 2014-03-15 17:00 | 2014-02-20 08:00 | 2014-03-15 17:00 | 2014-02-20 08:00 | 2014-03-15 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | iQYhWdSHRvip1/R20jwyNQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39330 | N | N | 10 | GROUND FLOOR |  | 124946 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1108.8 | LABOR- SUBCONTRACTOR
%R | 502581 | 6359 | 124947 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ELGF4030 | Installation of Telephone System | 8178 | 144 | 8 | 160 | 0 | 152.4 | 152.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-03-08 17:00 |  | 2014-01-22 08:00 | 2014-02-15 17:00 | 2014-01-22 08:00 | 2014-02-15 17:00 | 2014-01-22 08:00 | 2014-02-15 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | tC67DRhzQtCG+4ompC7PyQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39330 | N | N | 10 | GROUND FLOOR |  | 124946 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 152.4 | LABOR- SUBCONTRACTOR
%R | 502582 | 6359 | 124948 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ELRF4070 | Installation of Isolator | 8178 | 120 | 0 | 144 | 0 | 361.2 | 361.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-16 17:00 |  | 2014-02-05 08:00 | 2014-02-26 17:00 | 2014-02-05 08:00 | 2014-02-26 17:00 | 2014-02-05 08:00 | 2014-02-26 17:00 | 2014-02-24 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | gumfPHT6RR+X5be0pC5vPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39350 | N | N | 20 | ROOF |  | 124946 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 361.2 | LABOR- SUBCONTRACTOR
%R | 502583 | 6359 | 124948 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ELRF4075 | Installation of TV Dish Antenna | 8178 | 120 | 8 | 160 | 0 | 188.4 | 188.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-30 17:00 |  | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | iVjxxKfHTzKICxO0LAHiaQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39350 | N | N | 20 | ROOF |  | 124946 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 188.4 | LABOR- SUBCONTRACTOR
%R | 502584 | 6359 | 124950 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ACGF4600 | Installation AC Pipes | 8178 | 224 | 0 | 160 | 0 | 556.8 | 556.8 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-24 08:00 | 2014-01-15 17:00 |  | 2013-11-20 08:00 | 2013-12-12 17:00 | 2013-11-20 08:00 | 2013-12-12 17:00 | 2013-11-20 08:00 | 2013-12-12 17:00 | 2013-12-24 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | GYyKuPWmQjGNSY2Say61Sg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39410 | N | N | 10 | GROUND FLOOR |  | 124949 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 556.8 | LABOR- SUBCONTRACTOR
%R | 502585 | 6359 | 124950 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ACGF4605 | Fixing of Ventilation Equipments | 8178 | 128 | 0 | 200 | 0 | 85.2 | 85.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-03-08 17:00 |  | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | 9pw8gbB4QOueQsgLQpqMjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39410 | N | N | 10 | GROUND FLOOR |  | 124949 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 85.2 | LABOR- SUBCONTRACTOR
%R | 502586 | 6359 | 124950 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ACGF4610 | Fixing of Split AC | 8178 | 128 | 0 | 160 | 0 | 154.8 | 154.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-24 17:00 |  | 2014-02-10 08:00 | 2014-03-05 17:00 | 2014-02-10 08:00 | 2014-03-05 17:00 | 2014-02-10 08:00 | 2014-03-05 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | bEg2w3O2Rpiq8G4vR0tBiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39410 | N | N | 10 | GROUND FLOOR |  | 124949 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 154.8 | LABOR- SUBCONTRACTOR
%R | 502587 | 6359 | 124951 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ACRF4630 | Installation of Refrigerant Pipes | 8178 | 440 | 40 | 160 | 0 | 17.2 | 17.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-18 17:00 |  | 2013-12-21 08:00 | 2014-01-12 17:00 | 2013-12-21 08:00 | 2014-01-12 17:00 | 2013-12-21 08:00 | 2014-01-12 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39430 | N | N | 20 | ROOF |  | 124949 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 17.2 | LABOR- SUBCONTRACTOR
%R | 502588 | 6359 | 124951 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ACRF4635 | Installation of Condensing Unit | 8178 | 128 | 8 | 160 | 0 | 130.8 | 130.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-30 17:00 |  | 2014-02-17 08:00 | 2014-03-11 17:00 | 2014-02-17 08:00 | 2014-03-11 17:00 | 2014-02-17 08:00 | 2014-03-11 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | g8avUjWqTqKzMvGck3/qUw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39430 | N | N | 20 | ROOF |  | 124949 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 130.8 | LABOR- SUBCONTRACTOR
%R | 502589 | 6359 | 124954 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3STGF2000 | Column-Rebar & Formwork | 8165 | 16 | 0 | 160 | 0 | 1524.25 | 1524.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-07-02 08:00 | 2013-07-24 17:00 |  | 2013-06-30 08:00 | 2013-07-22 17:00 | 2013-06-30 08:00 | 2013-07-22 17:00 | 2013-06-30 08:00 | 2013-07-22 17:00 | 2013-07-02 08:00 | 2013-07-24 17:00 |  | PT_Normal |  |  |  |  | E8TIKBSWQhil3W/1DxZohA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39200 | N | N | 10 | GROUND FLOOR |  | 124953 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 1524.25 | STEEL FIXERS SK
%R | 502590 | 6359 | 124954 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3STGF2005 | Column-Concrete | 8167 | 16 | 0 | 120 | 0 | 105 | 105 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-13 08:00 | 2013-07-29 17:00 |  | 2013-07-10 08:00 | 2013-07-27 17:00 | 2013-07-10 08:00 | 2013-07-27 17:00 | 2013-07-10 08:00 | 2013-07-27 17:00 | 2013-07-13 08:00 | 2013-07-29 17:00 |  | PT_Normal |  |  |  |  | 5Zjyfmh6QraZCdpYmUA9FQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39200 | N | N | 10 | GROUND FLOOR |  | 124953 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 105 | CONCRETE MASON SK
%R | 502591 | 6359 | 124954 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 16 | 0 | 200 | 0 | 6076 | 6076 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-21 08:00 | 2013-08-21 17:00 |  | 2013-07-18 08:00 | 2013-08-19 17:00 | 2013-07-18 08:00 | 2013-08-19 17:00 | 2013-07-18 08:00 | 2013-08-19 17:00 | 2013-07-21 08:00 | 2013-08-21 17:00 |  | PT_Normal |  |  |  |  | fOr9mt13RWGPGieaU+hYwA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39200 | N | N | 10 | GROUND FLOOR |  | 124953 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 3038 | STEEL FIXERS SK
%R | 502592 | 6359 | 124954 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 16 | 0 | 120 | 0 | 1302 | 1302 | 120 | 0 | 0 | 0 |  |  |  | 2013-08-06 08:00 | 2013-08-26 17:00 |  | 2013-08-04 08:00 | 2013-08-24 17:00 | 2013-08-04 08:00 | 2013-08-24 17:00 | 2013-08-04 08:00 | 2013-08-24 17:00 | 2013-08-06 08:00 | 2013-08-26 17:00 |  | PT_Normal |  |  |  |  | EQXXQABqTFayClHFJnnG3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39200 | N | N | 10 | GROUND FLOOR |  | 124953 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 1302 | CONCRETE MASON SK
%R | 502593 | 6359 | 124955 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3STRF2060 | Construction of Parapets | 8165 | 152 | 0 | 160 | 0 | 521.5 | 521.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-10-13 08:00 | 2013-11-06 17:00 |  | 2013-09-21 08:00 | 2013-10-13 17:00 | 2013-09-21 08:00 | 2013-10-13 17:00 | 2013-09-21 08:00 | 2013-10-13 17:00 | 2013-10-13 08:00 | 2013-11-06 17:00 |  | PT_Normal |  |  |  |  | EN+IhWHSQk6p8u5UJ5pz5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39220 | N | N | 20 | ROOF |  | 124953 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 521.5 | STEEL FIXERS SK
%R | 502594 | 6359 | 124955 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3STRF2065 | Construction of up stands/Plinth | 8166 | 208 | 0 | 160 | 0 | 84 | 84 | 160 | 0 | 0 | 0 |  |  |  | 2013-10-30 08:00 | 2013-11-21 17:00 |  | 2013-09-28 08:00 | 2013-10-22 17:00 | 2013-09-28 08:00 | 2013-10-22 17:00 | 2013-09-28 08:00 | 2013-10-22 17:00 | 2013-10-30 08:00 | 2013-11-21 17:00 |  | PT_Normal |  |  |  |  | dePhFGe8S16GNAodmslZLg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39220 | N | N | 20 | ROOF |  | 124953 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 84 | CARPENTERS SK
%R | 502595 | 6359 | 124957 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3STUG1005 | Footing Antitermite | 8178 | 0 | 0 | 160 | 0 | 902 | 902 | 160 | 0 | 0 | 0 |  |  |  | 2013-03-23 08:00 | 2013-04-14 17:00 |  | 2013-03-23 08:00 | 2013-04-14 17:00 | 2013-03-23 08:00 | 2013-04-14 17:00 | 2013-03-23 08:00 | 2013-04-14 17:00 | 2013-03-23 08:00 | 2013-04-14 17:00 |  | PT_Normal |  |  |  |  | x8TSqWnQRy6deFjYbCF64g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39180 | N | N | 10 | UPTO GRADE SLAB |  | 124956 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 902 | LABOR- SUBCONTRACTOR
%R | 502596 | 6359 | 124957 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3STUG1010 | Footing Blinding | 8163 | 0 | 0 | 160 | 0 | 29.75 | 29.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-03-25 08:00 | 2013-04-16 17:00 |  | 2013-03-25 08:00 | 2013-04-16 17:00 | 2013-03-25 08:00 | 2013-04-16 17:00 | 2013-03-25 08:00 | 2013-04-16 17:00 | 2013-03-25 08:00 | 2013-04-16 17:00 |  | PT_Normal |  |  |  |  | q6mcD2zcT6iFthAbYvwGog |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39180 | N | N | 10 | UPTO GRADE SLAB |  | 124956 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 29.75 | BLINDING MASON SK
%R | 502597 | 6359 | 124957 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3STUG1015 | Footing Waterproofing & Screed | 8164 | 0 | 0 | 160 | 0 | 483 | 483 | 160 | 0 | 0 | 0 |  |  |  | 2013-03-31 08:00 | 2013-04-22 17:00 |  | 2013-03-31 08:00 | 2013-04-22 17:00 | 2013-03-31 08:00 | 2013-04-22 17:00 | 2013-03-31 08:00 | 2013-04-22 17:00 | 2013-03-31 08:00 | 2013-04-22 17:00 |  | PT_Normal |  |  |  |  | 2/20u5BkSCyCBEskuVaLgQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39180 | N | N | 10 | UPTO GRADE SLAB |  | 124956 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 483 | SCREED MASON SK
%R | 502598 | 6359 | 124957 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3STUG1020 | Construction of foundations | 8165 | 0 | 0 | 160 | 0 | 1335.25 | 1335.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-04-09 08:00 | 2013-05-01 17:00 |  | 2013-04-09 08:00 | 2013-05-01 17:00 | 2013-04-09 08:00 | 2013-05-01 17:00 | 2013-04-09 08:00 | 2013-05-01 17:00 | 2013-04-09 08:00 | 2013-05-01 17:00 |  | PT_Normal |  |  |  |  | n17McgzZTlWVSQVBptjCzw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39180 | N | N | 10 | UPTO GRADE SLAB |  | 124956 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 1335.25 | STEEL FIXERS SK
%R | 502599 | 6359 | 124957 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3STUG1025 | Construction of neck of columns | 8165 | 0 | 0 | 160 | 0 | 1389.5 | 1389.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-04-18 08:00 | 2013-05-11 17:00 |  | 2013-04-18 08:00 | 2013-05-11 17:00 | 2013-04-18 08:00 | 2013-05-11 17:00 | 2013-04-18 08:00 | 2013-05-11 17:00 | 2013-04-18 08:00 | 2013-05-11 17:00 |  | PT_Normal |  |  |  |  | zttn9yXpR2qovnlYr0xUsg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39180 | N | N | 10 | UPTO GRADE SLAB |  | 124956 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 1389.5 | STEEL FIXERS SK
%R | 502600 | 6359 | 124957 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3STUG1030 | Waterproofing Footing & Neck Column | 8178 | 0 | 0 | 160 | 0 | 125.5 | 125.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-04-28 08:00 | 2013-05-20 17:00 |  | 2013-04-28 08:00 | 2013-05-20 17:00 | 2013-04-28 08:00 | 2013-05-20 17:00 | 2013-04-28 08:00 | 2013-05-20 17:00 | 2013-04-28 08:00 | 2013-05-20 17:00 |  | PT_Normal |  |  |  |  | elF0O4yZSAqv01kBlXwQ5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39180 | N | N | 10 | UPTO GRADE SLAB |  | 124956 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 125.5 | LABOR- SUBCONTRACTOR
%R | 502601 | 6359 | 124957 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 0 | 0 | 160 | 0 | 822 | 822 | 160 | 660 | 0 | 660 |  |  |  | 2013-05-09 08:00 | 2013-06-01 17:00 |  | 2013-05-09 08:00 | 2013-06-01 17:00 | 2013-05-09 08:00 | 2013-06-01 17:00 | 2013-05-09 08:00 | 2013-06-01 17:00 | 2013-05-09 08:00 | 2013-06-01 17:00 |  | PT_Normal |  |  |  |  | InCs1/ZCTTWo32DGQ00pMw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39180 | N | N | 10 | UPTO GRADE SLAB |  | 124956 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 822 | LABOR - CIVIL
%R | 502602 | 6359 | 124957 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3STUG1040 | Construction of Grade Beams | 8163 | 0 | 0 | 200 | 0 | 2325.75 | 2325.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-05-21 08:00 | 2013-06-18 17:00 |  | 2013-05-21 08:00 | 2013-06-18 17:00 | 2013-05-21 08:00 | 2013-06-18 17:00 | 2013-05-21 08:00 | 2013-06-18 17:00 | 2013-05-21 08:00 | 2013-06-18 17:00 |  | PT_Normal |  |  |  |  | eifWcIzGTsqP66dTaWqcSQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39180 | N | N | 10 | UPTO GRADE SLAB |  | 124956 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 2325.75 | BLINDING MASON SK
%R | 502603 | 6359 | 124957 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3STUG1045 | Construction of slab on grade | 8163 | 16 | 0 | 200 | 0 | 1541.75 | 1541.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-15 08:00 | 2013-07-13 17:00 |  | 2013-06-12 08:00 | 2013-07-10 17:00 | 2013-06-12 08:00 | 2013-07-10 17:00 | 2013-06-12 08:00 | 2013-07-10 17:00 | 2013-06-15 08:00 | 2013-07-13 17:00 |  | PT_Normal |  |  |  |  | ofYDO67nTQiG/p5NBqNHog |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39180 | N | N | 10 | UPTO GRADE SLAB |  | 124956 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 1541.75 | BLINDING MASON SK
%R | 502604 | 6359 | 124957 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3STUG1000 | Footing Excavation | 8177 | 0 | 0 | 200 | 0 | 476 | 476 | 200 | 224 | 0 | 224 |  |  |  | 2013-03-11 08:00 | 2013-04-08 17:00 |  | 2013-03-11 08:00 | 2013-04-08 17:00 | 2013-03-11 08:00 | 2013-04-08 17:00 | 2013-03-11 08:00 | 2013-04-08 17:00 | 2013-03-11 08:00 | 2013-04-08 17:00 |  | PT_Normal |  |  |  |  | 9y/zk/U3Q8CTh59im4Hs1Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39180 | N | N | 10 | UPTO GRADE SLAB |  | 124956 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 476 | LABOR - CIVIL
%R | 502605 | 6359 | 124960 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARGF3000 | Block work | 8168 | 16 | 0 | 200 | 0 | 5700 | 5700 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-03 08:00 | 2013-10-01 17:00 |  | 2013-09-01 08:00 | 2013-09-29 17:00 | 2013-09-01 08:00 | 2013-09-29 17:00 | 2013-09-01 08:00 | 2013-09-29 17:00 | 2013-09-03 08:00 | 2013-10-01 17:00 |  | PT_Normal |  |  |  |  | BZfE+D+rTsW+YH0VJA3gTw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39250 | N | N | 10 | GROUND FLOOR |  | 124959 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 5700 | BLOCK MASON SK
%R | 502606 | 6359 | 124960 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARGF3005 | Plastering work | 8169 | 40 | 0 | 200 | 0 | 2850 | 2850 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-26 08:00 | 2013-10-27 17:00 |  | 2013-09-21 08:00 | 2013-10-21 17:00 | 2013-09-21 08:00 | 2013-10-21 17:00 | 2013-09-21 08:00 | 2013-10-21 17:00 | 2013-09-26 08:00 | 2013-10-27 17:00 |  | PT_Normal |  |  |  |  | h/wBWZHrR+OZW5dF+j98vg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39250 | N | N | 10 | GROUND FLOOR |  | 124959 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 1425 | PLASTER MASON SK
%R | 502607 | 6359 | 124960 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARGF3010 | Flooring screed | 8164 | 280 | 80 | 160 | 0 | 634.25 | 634.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-14 08:00 | 2013-12-07 17:00 |  | 2013-10-02 08:00 | 2013-10-27 17:00 | 2013-10-02 08:00 | 2013-10-27 17:00 | 2013-10-02 08:00 | 2013-10-27 17:00 | 2013-11-14 08:00 | 2013-12-07 17:00 |  | PT_Normal |  |  |  |  | HZxwAT/vRMOa7RUZJYqaMw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39250 | N | N | 10 | GROUND FLOOR |  | 124959 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 634.25 | SCREED MASON SK
%R | 502608 | 6359 | 124960 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 136 | 0 | 160 | 0 | 87 | 87 | 160 | 0 | 0 | 0 |  |  |  | 2013-10-27 08:00 | 2013-11-18 17:00 |  | 2013-10-05 08:00 | 2013-10-29 17:00 | 2013-10-05 08:00 | 2013-10-29 17:00 | 2013-10-05 08:00 | 2013-10-29 17:00 | 2013-10-27 08:00 | 2013-11-18 17:00 |  | PT_Normal |  |  |  |  | DkfXPFwTSIiniQS3gH4c2w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39250 | N | N | 10 | GROUND FLOOR |  | 124959 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 87 | LABOR- SUBCONTRACTOR
%R | 502609 | 6359 | 124960 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARGF3030 | Paint First coat | 8178 | 48 | 0 | 160 | 0 | 1815 | 1815 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-01 08:00 | 2013-12-24 17:00 |  | 2013-11-24 08:00 | 2013-12-16 17:00 | 2013-11-24 08:00 | 2013-12-16 17:00 | 2013-11-24 08:00 | 2013-12-16 17:00 | 2013-12-01 08:00 | 2013-12-24 17:00 |  | PT_Normal |  |  |  |  | 7zsvn6MfQr+gNM1/fOD8UQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39250 | N | N | 10 | GROUND FLOOR |  | 124959 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1815 | LABOR- SUBCONTRACTOR
%R | 502610 | 6359 | 124960 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARGF3020 | Ceramic Wall Tiling | 8170 | 136 | 0 | 120 | 0 | 1012.5 | 1012.5 | 120 | 0 | 0 | 0 |  |  |  | 2013-11-14 08:00 | 2013-12-01 17:00 |  | 2013-10-26 08:00 | 2013-11-11 17:00 | 2013-10-26 08:00 | 2013-11-11 17:00 | 2013-10-26 08:00 | 2013-11-11 17:00 | 2013-11-14 08:00 | 2013-12-01 17:00 |  | PT_Normal |  |  |  |  | RwkD9PoCT0OhEgf63/+avw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39250 | N | N | 10 | GROUND FLOOR |  | 124959 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1012.5 | TILE MASON SK
%R | 502611 | 6359 | 124960 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARGF3025 | Porcelain Tile flooring | 8170 | 136 | 88 | 160 | 0 | 1030.25 | 1030.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-01 08:00 | 2013-12-24 17:00 |  | 2013-11-11 08:00 | 2013-12-03 17:00 | 2013-11-11 08:00 | 2013-12-03 17:00 | 2013-11-11 08:00 | 2013-12-03 17:00 | 2013-12-01 08:00 | 2013-12-24 17:00 |  | PT_Normal |  |  |  |  | W3bi2qGXRK+8QHe7y5PqsA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39250 | N | N | 10 | GROUND FLOOR |  | 124959 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1030.25 | TILE MASON SK
%R | 502612 | 6359 | 124960 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARGF3040 | Cobble Tile flooring | 8170 | 184 | 24 | 120 | 0 | 300 | 300 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-26 08:00 | 2014-03-15 17:00 |  | 2014-01-29 08:00 | 2014-02-16 17:00 | 2014-01-29 08:00 | 2014-02-16 17:00 | 2014-01-29 08:00 | 2014-02-16 17:00 | 2014-02-26 08:00 | 2014-03-15 17:00 |  | PT_Normal |  |  |  |  | BxViF3JPSouVm3d7WpgX8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39250 | N | N | 10 | GROUND FLOOR |  | 124959 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 300 | TILE MASON SK
%R | 502613 | 6359 | 124960 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARGF3045 | Fixing of Suspension systems | 8178 | 48 | 0 | 120 | 0 | 653.5 | 653.5 | 120 | 0 | 0 | 0 |  |  |  | 2013-12-24 08:00 | 2014-01-09 17:00 |  | 2013-12-16 08:00 | 2014-01-02 17:00 | 2013-12-16 08:00 | 2014-01-02 17:00 | 2013-12-16 08:00 | 2014-01-02 17:00 | 2013-12-24 08:00 | 2014-01-09 17:00 |  | PT_Normal |  |  |  |  | V3O1UZoHTluAd7qQIIohhw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39250 | N | N | 10 | GROUND FLOOR |  | 124959 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 653.5 | LABOR- SUBCONTRACTOR
%R | 502614 | 6359 | 124960 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARGF3060 | Gypsum board false ceiling | 8178 | 48 | 0 | 160 | 0 | 653.5 | 653.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-09 08:00 | 2014-02-01 17:00 |  | 2014-01-02 08:00 | 2014-01-25 17:00 | 2014-01-02 08:00 | 2014-01-25 17:00 | 2014-01-02 08:00 | 2014-01-25 17:00 | 2014-01-09 08:00 | 2014-02-01 17:00 |  | PT_Normal |  |  |  |  | 5pqy/m9RT0CwUoAI6WKP1Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39250 | N | N | 10 | GROUND FLOOR |  | 124959 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 653.5 | LABOR- SUBCONTRACTOR
%R | 502615 | 6359 | 124960 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARGF3065 | Wooden door | 8178 | 136 | 0 | 120 | 0 | 198 | 198 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-01 17:00 |  | 2014-01-22 08:00 | 2014-02-08 17:00 | 2014-01-22 08:00 | 2014-02-08 17:00 | 2014-01-22 08:00 | 2014-02-08 17:00 | 2014-02-12 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | o0lELTOAScSQZwCWmxbevQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39250 | N | N | 10 | GROUND FLOOR |  | 124959 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 198 | LABOR- SUBCONTRACTOR
%R | 502616 | 6359 | 124960 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARGF3080 | Aluminum windows | 8178 | 392 | 88 | 144 | 0 | 132 | 132 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-08 08:00 | 2014-04-28 17:00 |  | 2014-02-09 08:00 | 2014-03-02 17:00 | 2014-02-09 08:00 | 2014-03-02 17:00 | 2014-02-09 08:00 | 2014-03-02 17:00 | 2014-04-08 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | lmY+GWN3SvSZI/REjjlQnw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39250 | N | N | 10 | GROUND FLOOR |  | 124959 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 132 | LABOR- SUBCONTRACTOR
%R | 502617 | 6359 | 124960 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARGF3075 | Carpentry & Joinery Works | 8178 | 136 | 0 | 144 | 0 | 528 | 528 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-10 17:00 |  | 2014-01-28 08:00 | 2014-02-18 17:00 | 2014-01-28 08:00 | 2014-02-18 17:00 | 2014-01-28 08:00 | 2014-02-18 17:00 | 2014-02-18 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | mMbSdzruTbKAXeog7CujyQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39250 | N | N | 10 | GROUND FLOOR |  | 124959 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 528 | LABOR- SUBCONTRACTOR
%R | 502618 | 6359 | 124960 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARGF3090 | Installation of Granite Counter Top | 8171 | 64 | 0 | 120 | 0 | 99 | 99 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-24 17:00 |  | 2014-02-26 08:00 | 2014-03-15 17:00 | 2014-02-26 08:00 | 2014-03-15 17:00 | 2014-02-26 08:00 | 2014-03-15 17:00 | 2014-03-08 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | 9EyGHY/KTHKqItY5XieKYw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39250 | N | N | 10 | GROUND FLOOR |  | 124959 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 99 | GRANITE MASON SK
%R | 502619 | 6359 | 124960 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARGF3095 | Final Painting | 8178 | 304 | 0 | 200 | 0 | 1815 | 1815 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | b0HCqQVmSHOfNSCv8hM+aA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39250 | N | N | 10 | GROUND FLOOR |  | 124959 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1815 | LABOR- SUBCONTRACTOR
%R | 502620 | 6359 | 124960 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 104 | 0 | 144 | 0 | 1575 | 1575 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-26 08:00 | 2014-02-16 17:00 |  | 2014-01-11 08:00 | 2014-01-30 17:00 | 2014-01-11 08:00 | 2014-01-30 17:00 | 2014-01-11 08:00 | 2014-01-30 17:00 | 2014-01-26 08:00 | 2014-02-16 17:00 |  | PT_Normal |  |  |  |  | QiaFEnfnQbCCcTz8xE4kxA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39250 | N | N | 10 | GROUND FLOOR |  | 124959 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1575 | TILE MASON SK
%R | 502621 | 6359 | 124962 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3AREL3665 | External Plastering | 8169 | 240 | 0 | 200 | 0 | 4012.5 | 4012.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-20 08:00 | 2014-02-18 17:00 |  | 2013-12-15 08:00 | 2014-01-13 17:00 | 2013-12-15 08:00 | 2014-01-13 17:00 | 2013-12-15 08:00 | 2014-01-13 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 |  | PT_Normal |  |  |  |  | 6y2rX0EpQ1uld2aSmAJOHQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39300 | N | N | 15 | ELEVATION |  | 124961 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 4012.5 | PLASTER MASON SK
%R | 502622 | 6359 | 124962 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3AREL3680 | External Painting | 8178 | 400 | 40 | 160 | 0 | 1408 | 1408 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-30 17:00 |  | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | RZxtldESQ2GcLWWbDlQc1w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39300 | N | N | 15 | ELEVATION |  | 124961 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1408 | LABOR- SUBCONTRACTOR
%R | 502623 | 6359 | 124963 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARRF3625 | Laying of Pitched Roof | 8174 | 240 | 0 | 200 | 0 | 256 | 256 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-05 08:00 | 2014-01-04 17:00 |  | 2013-10-31 08:00 | 2013-11-28 17:00 | 2013-10-31 08:00 | 2013-11-28 17:00 | 2013-10-31 08:00 | 2013-11-28 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 |  | PT_Normal |  |  |  |  | oDnBsw4cR0u3RbiTMF5Gvg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39290 | N | N | 10 | ROOF |  | 124961 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 256 | INTERLOCK MASON SK
%R | 502624 | 6359 | 124963 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARRF3630 | Leveling Screed for Waterproofing | 8164 | 240 | 0 | 144 | 0 | 195.5 | 195.5 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-21 08:00 | 2014-01-09 17:00 |  | 2013-11-14 08:00 | 2013-12-04 17:00 | 2013-11-14 08:00 | 2013-12-04 17:00 | 2013-11-14 08:00 | 2013-12-04 17:00 | 2013-12-21 08:00 | 2014-01-09 17:00 |  | PT_Normal |  |  |  |  | Tg4cCa3SQ8O74He9yWeloQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39290 | N | N | 10 | ROOF |  | 124961 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 195.5 | SCREED MASON SK
%R | 502625 | 6359 | 124963 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARRF3635 | Laying of Waterproofing Membrane | 8178 | 240 | 0 | 144 | 0 | 722.25 | 722.25 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-26 08:00 | 2014-01-15 17:00 |  | 2013-11-20 08:00 | 2013-12-10 17:00 | 2013-11-20 08:00 | 2013-12-10 17:00 | 2013-11-20 08:00 | 2013-12-10 17:00 | 2013-12-26 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | F9JlNJ2vTi6G5O6Ruv6HxQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39290 | N | N | 10 | ROOF |  | 124961 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 722.25 | LABOR- SUBCONTRACTOR
%R | 502626 | 6359 | 124963 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARRF3640 | Installation of Insulation & Protection | 8178 | 240 | 0 | 144 | 0 | 343.75 | 343.75 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-31 08:00 | 2014-01-20 17:00 |  | 2013-11-25 08:00 | 2013-12-15 17:00 | 2013-11-25 08:00 | 2013-12-15 17:00 | 2013-11-25 08:00 | 2013-12-15 17:00 | 2013-12-31 08:00 | 2014-01-20 17:00 |  | PT_Normal |  |  |  |  | Po1E1lW/Q2679y7+nu5VaQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39290 | N | N | 10 | ROOF |  | 124961 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 343.75 | LABOR- SUBCONTRACTOR
%R | 502627 | 6359 | 124963 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 240 | 0 | 144 | 0 | 344.5 | 344.5 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-08 08:00 | 2014-01-28 17:00 |  | 2013-12-03 08:00 | 2013-12-24 17:00 | 2013-12-03 08:00 | 2013-12-24 17:00 | 2013-12-03 08:00 | 2013-12-24 17:00 | 2014-01-08 08:00 | 2014-01-28 17:00 |  | PT_Normal |  |  |  |  | SmKBrUkXQnqa6lp+qfxGjA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39290 | N | N | 10 | ROOF |  | 124961 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 344.5 | TILE MASON SK
%R | 502628 | 6359 | 124963 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3ARRF3660 | Installation of Access Ladder | 8178 | 512 | 40 | 160 | 0 | 132 | 132 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-18 17:00 |  | 2013-12-09 08:00 | 2014-01-01 17:00 | 2013-12-09 08:00 | 2014-01-01 17:00 | 2013-12-09 08:00 | 2014-01-01 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | YH3MRPweQyy23tRvNRrQrg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39290 | N | N | 10 | ROOF |  | 124961 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 132 | LABOR- SUBCONTRACTOR
%R | 502629 | 6359 | 124965 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3MSEX5020 | Construction Entrance Ramp | 8164 | 240 | 0 | 160 | 0 | 436 | 436 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-14 08:00 | 2014-01-06 17:00 |  | 2013-11-09 08:00 | 2013-12-01 17:00 | 2013-11-09 08:00 | 2013-12-01 17:00 | 2013-11-09 08:00 | 2013-12-01 17:00 | 2013-12-14 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | 5Lq+Xli0RK27PZ7msyqzLQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39460 | N | N | 10 | MISCELLANEOUS |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 436 | SCREED MASON SK
%R | 502630 | 6359 | 124965 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3MSEX5025 | SS.Handrails and Balustrades | 8178 | 240 | 0 | 160 | 0 | 136 | 136 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-07 08:00 | 2014-01-29 17:00 |  | 2013-12-02 08:00 | 2013-12-25 17:00 | 2013-12-02 08:00 | 2013-12-25 17:00 | 2013-12-02 08:00 | 2013-12-25 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | 9+Q0YnDKTNyaNkEVc8RXQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39460 | N | N | 10 | MISCELLANEOUS |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 136 | LABOR- SUBCONTRACTOR
%R | 502631 | 6359 | 124965 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3MSEX5015 | Construction of grease Trap | 8178 | 288 | 0 | 160 | 0 | 168 | 168 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-22 08:00 | 2014-01-13 17:00 |  | 2013-11-09 08:00 | 2013-12-01 17:00 | 2013-11-09 08:00 | 2013-12-01 17:00 | 2013-11-09 08:00 | 2013-12-01 17:00 | 2013-12-22 08:00 | 2014-01-13 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39460 | N | N | 10 | MISCELLANEOUS |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 168 | LABOR- SUBCONTRACTOR
%R | 502632 | 6359 | 124965 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3MSEX5000 | Construction of Manholes | 8172 | 208 | 0 | 200 | 0 | 132 | 132 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-05 08:00 | 2013-12-03 17:00 |  | 2013-10-03 08:00 | 2013-11-03 17:00 | 2013-10-03 08:00 | 2013-11-03 17:00 | 2013-10-03 08:00 | 2013-11-03 17:00 | 2013-11-05 08:00 | 2013-12-03 17:00 |  | PT_Normal |  |  |  |  | SxFkA3TsTLKZgbjekl4gow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39460 | N | N | 10 | MISCELLANEOUS |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 66 | MANHOLES SK
%R | 502633 | 6359 | 124965 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3MSEX5005 | Construction of Soak pit, Chambers | 8172 | 288 | 0 | 200 | 0 | 66 | 66 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-01 08:00 | 2013-12-30 17:00 |  | 2013-10-20 08:00 | 2013-11-17 17:00 | 2013-10-20 08:00 | 2013-11-17 17:00 | 2013-10-20 08:00 | 2013-11-17 17:00 | 2013-12-01 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | vqmH9iwnRZybcLwED9R9ow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39460 | N | N | 10 | MISCELLANEOUS |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 66 | MANHOLES SK
%R | 502634 | 6359 | 124965 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3MSEX5055 | Installation Steel Door | 8178 | 240 | 0 | 160 | 0 | 180 | 180 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-26 08:00 | 2014-01-18 17:00 |  | 2013-11-20 08:00 | 2013-12-12 17:00 | 2013-11-20 08:00 | 2013-12-12 17:00 | 2013-11-20 08:00 | 2013-12-12 17:00 | 2013-12-26 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | h3mfJ5WwTMKRtD3QClMhaA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39460 | N | N | 10 | MISCELLANEOUS |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 180 | LABOR- SUBCONTRACTOR
%R | 502635 | 6359 | 124965 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3MSEX5010 | Telephone cable laying | 8177 | 288 | 144 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-02-12 17:00 |  | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 |  | PT_Normal |  |  |  |  | XCn7Gcf7TGqdsxaHVA7SGQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39460 | N | N | 10 | MISCELLANEOUS |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 500 | LABOR - CIVIL
%R | 502636 | 6359 | 124966 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3WEEX5035 | Construction of Raft | 8167 | 120 | 0 | 200 | 0 | 210 | 210 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-08 08:00 | 2014-01-06 17:00 |  | 2013-11-20 08:00 | 2013-12-19 17:00 | 2013-11-20 08:00 | 2013-12-19 17:00 | 2013-11-20 08:00 | 2013-12-19 17:00 | 2013-12-08 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | R28pt64wQOW5gNcb6aF2AQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39470 | N | N | 15 | WATER TANK ENCLOSURE |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 210 | CONCRETE MASON SK
%R | 502637 | 6359 | 124966 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3WEEX5040 | Block works & Plastering | 8168 | 280 | 0 | 200 | 0 | 692 | 692 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-11 08:00 | 2014-02-08 17:00 |  | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 |  | PT_Normal |  |  |  |  | uF9QUNVIQ921OpaavQV9wQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39470 | N | N | 15 | WATER TANK ENCLOSURE |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 692 | BLOCK MASON SK
%R | 502638 | 6359 | 124966 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3WEEX5045 | Flooring & Painting | 8164 | 280 | 0 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-20 17:00 |  | 2013-12-11 08:00 | 2014-01-09 17:00 | 2013-12-11 08:00 | 2014-01-09 17:00 | 2013-12-11 08:00 | 2014-01-09 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | k8T8rh7qTD27LAglGVjIKw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39470 | N | N | 15 | WATER TANK ENCLOSURE |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 336 | SCREED MASON SK
%R | 502639 | 6359 | 124966 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3WEEX5050 | Installation of Steel Gate | 8178 | 280 | 0 | 160 | 0 | 150 | 150 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-03-04 17:00 |  | 2013-12-30 08:00 | 2014-01-21 17:00 | 2013-12-30 08:00 | 2014-01-21 17:00 | 2013-12-30 08:00 | 2014-01-21 17:00 | 2014-02-09 08:00 | 2014-03-04 17:00 |  | PT_Normal |  |  |  |  | JtKhULNxReCVwOJ2xbJ58Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39470 | N | N | 15 | WATER TANK ENCLOSURE |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 150 | LABOR- SUBCONTRACTOR
%R | 502640 | 6359 | 124966 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 280 | 200 | 200 | 0 | 534 | 534 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-16 17:00 |  | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | 12vjX3ApRyyrBORbVjeGcg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39470 | N | N | 15 | WATER TANK ENCLOSURE |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 534 | LABOR- SUBCONTRACTOR
%R | 502641 | 6359 | 124966 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 80 | 0 | 200 | 0 | 286.8 | 286.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-27 08:00 | 2014-03-27 17:00 |  | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 |  | PT_Normal |  |  |  |  | 0cMq6ZATT1meiML+HWrZEw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39470 | N | N | 15 | WATER TANK ENCLOSURE |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 143.4 | LABOR- SUBCONTRACTOR
%R | 502642 | 6359 | 124966 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3WEEX5070 | Installation ladder for water Tank | 8178 | 80 | 0 | 160 | 0 | 200 | 200 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-30 17:00 |  | 2014-02-24 08:00 | 2014-03-18 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | inoFO/b+TeeAAu7nbEjlzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39470 | N | N | 15 | WATER TANK ENCLOSURE |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 200 | LABOR- SUBCONTRACTOR
%R | 502643 | 6359 | 124966 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 344 | 136 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | THJBkW/MStOP0YhYik64Sw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39470 | N | N | 15 | WATER TANK ENCLOSURE |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 400 | LABOR- SUBCONTRACTOR
%R | 502644 | 6359 | 124966 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3WEEX5030 | Excavation | 8177 | 120 | 0 | 160 | 0 | 116 | 116 | 160 | 80 | 0 | 80 |  |  |  | 2013-11-30 08:00 | 2013-12-23 17:00 |  | 2013-11-12 08:00 | 2013-12-04 17:00 | 2013-11-12 08:00 | 2013-12-04 17:00 | 2013-11-12 08:00 | 2013-12-04 17:00 | 2013-11-30 08:00 | 2013-12-23 17:00 |  | PT_Normal |  |  |  |  | gWl9litJQ5WlRrZBAfDuEQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39470 | N | N | 15 | WATER TANK ENCLOSURE |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 116 | LABOR - CIVIL
%R | 502645 | 6359 | 124967 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3HDEX5090 | kerb works | 8173 | 240 | 0 | 160 | 0 | 236 | 236 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-15 08:00 | 2014-02-06 17:00 |  | 2013-12-10 08:00 | 2014-01-02 17:00 | 2013-12-10 08:00 | 2014-01-02 17:00 | 2013-12-10 08:00 | 2014-01-02 17:00 | 2014-01-15 08:00 | 2014-02-06 17:00 |  | PT_Normal |  |  |  |  | /K3+flVZSwWDjC+l0hHeFA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39480 | N | N | 20 | HARD LANDSCAPING |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 236 | KERBSTONE MASON SK
%R | 502646 | 6359 | 124967 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3HDEX5095 | Cobble Stone Works | 8170 | 240 | 0 | 160 | 0 | 86 | 86 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-27 08:00 | 2014-02-19 17:00 |  | 2013-12-23 08:00 | 2014-01-14 17:00 | 2013-12-23 08:00 | 2014-01-14 17:00 | 2013-12-23 08:00 | 2014-01-14 17:00 | 2014-01-27 08:00 | 2014-02-19 17:00 |  | PT_Normal |  |  |  |  | XSrHfccHQnGmCNyhtAhlEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39480 | N | N | 20 | HARD LANDSCAPING |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 86 | TILE MASON SK
%R | 502647 | 6359 | 124967 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3HDEX5100 | Interlock works | 8174 | 240 | 72 | 160 | 0 | 300 | 300 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-06 17:00 |  | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | VYXsJVaVSIy9AQrMJe3jtg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39480 | N | N | 20 | HARD LANDSCAPING |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 300 | INTERLOCK MASON SK
%R | 502648 | 6359 | 124968 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3SLEX5105 | Laying of Grass/ green area | 8178 | 168 | 0 | 160 | 0 | 2142 | 2142 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-18 17:00 |  | 2014-01-29 08:00 | 2014-02-22 17:00 | 2014-01-29 08:00 | 2014-02-22 17:00 | 2014-01-29 08:00 | 2014-02-22 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | t3GXTObeTWKm/IyWZh5oYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39490 | N | N | 25 | SOFT LANDSCAPING |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 2142 | LABOR- SUBCONTRACTOR
%R | 502649 | 6359 | 124968 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ3SLEX5110 | Laying of Palm tree | 8178 | 488 | 184 | 160 | 0 | 546 | 546 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-05-15 17:00 |  | 2014-02-10 08:00 | 2014-03-05 17:00 | 2014-02-10 08:00 | 2014-03-05 17:00 | 2014-02-10 08:00 | 2014-03-05 17:00 | 2014-04-23 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | Q8XgQu4UQPGNw7uGZv/7uQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39490 | N | N | 25 | SOFT LANDSCAPING |  | 124964 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 546 | LABOR- SUBCONTRACTOR
%R | 502650 | 6359 | 124972 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 0 | 0 | 160 | 0 | 1435.2 | 1435.2 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-17 08:00 | 2013-12-09 17:00 |  | 2013-11-17 08:00 | 2013-12-09 17:00 | 2013-11-17 08:00 | 2013-12-09 17:00 | 2013-11-17 08:00 | 2013-12-09 17:00 | 2013-11-17 08:00 | 2013-12-09 17:00 |  | PT_Normal |  |  |  |  | 30xHAtOURDebmJ/leSpu4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40090 | N | N | 10 | GROUND FLOOR |  | 124971 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1435.2 | LABOR- SUBCONTRACTOR
%R | 502651 | 6359 | 124972 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5PLGF4310 | Installation of Drainage pipes &testing | 8178 | 224 | 16 | 144 | 0 | 72 | 72 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-23 08:00 | 2014-01-12 17:00 |  | 2013-11-19 08:00 | 2013-12-09 17:00 | 2013-11-19 08:00 | 2013-12-09 17:00 | 2013-11-19 08:00 | 2013-12-09 17:00 | 2013-12-23 08:00 | 2014-01-12 17:00 |  | PT_Normal |  |  |  |  | UDFklH54Tlie8a50CRJ9pw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40090 | N | N | 10 | GROUND FLOOR |  | 124971 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 72 | LABOR- SUBCONTRACTOR
%R | 502652 | 6359 | 124972 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5PLGF4315 | Sanitary Fittings & Accessories | 8178 | 56 | 0 | 160 | 0 | 218.4 | 218.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-10 17:00 |  | 2014-04-09 08:00 | 2014-05-01 17:00 | 2014-04-09 08:00 | 2014-05-01 17:00 | 2014-04-09 08:00 | 2014-05-01 17:00 | 2014-04-17 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | v43PmSHZTgmF2fxGu28JbA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40090 | N | N | 10 | GROUND FLOOR |  | 124971 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 218.4 | LABOR- SUBCONTRACTOR
%R | 502653 | 6359 | 124972 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5PLGF4320 | Installation of Water Heater | 8178 | 56 | 56 | 120 | 0 | 151.2 | 151.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-15 17:00 |  | 2014-04-21 08:00 | 2014-05-07 17:00 | 2014-04-21 08:00 | 2014-05-07 17:00 | 2014-04-21 08:00 | 2014-05-07 17:00 | 2014-04-29 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | xynIEVWtSASBz2nDPt2B9w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40090 | N | N | 10 | GROUND FLOOR |  | 124971 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 151.2 | LABOR- SUBCONTRACTOR
%R | 502654 | 6359 | 124972 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 16 | 0 | 160 | 0 | 182.4 | 182.4 | 160 | 0 | 0 | 0 |  |  |  | 2013-08-04 08:00 | 2013-08-29 17:00 |  | 2013-08-01 08:00 | 2013-08-27 17:00 | 2013-08-01 08:00 | 2013-08-27 17:00 | 2013-08-01 08:00 | 2013-08-27 17:00 | 2013-08-04 08:00 | 2013-08-29 17:00 |  | PT_Normal |  |  |  |  | EwkT3t+tQdaDxS0CBM+EFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40090 | N | N | 10 | GROUND FLOOR |  | 124971 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 182.4 | LABOR- SUBCONTRACTOR
%R | 502655 | 6359 | 124973 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5PLRF4350 | Installation of Rain water Pipes | 8178 | 240 | 120 | 120 | 0 | 265.2 | 265.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-09 08:00 | 2014-04-26 17:00 |  | 2014-03-05 08:00 | 2014-03-22 17:00 | 2014-03-05 08:00 | 2014-03-22 17:00 | 2014-03-05 08:00 | 2014-03-22 17:00 | 2014-04-09 08:00 | 2014-04-26 17:00 |  | PT_Normal |  |  |  |  | SdReBSD3QF2Gmxev35fMqQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40110 | N | N | 20 | ROOF |  | 124971 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 265.2 | LABOR- SUBCONTRACTOR
%R | 502656 | 6359 | 124975 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ELRF4070 | Installation of Isolator | 8178 | 72 | 0 | 144 | 0 | 361.2 | 361.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-01 17:00 |  | 2014-04-01 08:00 | 2014-04-21 17:00 | 2014-04-01 08:00 | 2014-04-21 17:00 | 2014-04-01 08:00 | 2014-04-21 17:00 | 2014-04-12 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | l0B3g/20QVyHV0DDUQpegg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40070 | N | N | 20 | ROOF |  | 124974 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 361.2 | LABOR- SUBCONTRACTOR
%R | 502657 | 6359 | 124975 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ELRF4075 | Installation of TV Dish Antenna | 8178 | 72 | 72 | 160 | 0 | 188.4 | 188.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-05-15 17:00 |  | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 | 2014-04-23 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | djAGXEHJTnu+zEQsN3d6Lg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40070 | N | N | 20 | ROOF |  | 124974 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 188.4 | LABOR- SUBCONTRACTOR
%R | 502658 | 6359 | 124976 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 24 | 24 | 160 | 0 | 594.8 | 594.8 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-20 08:00 | 2013-12-12 17:00 |  | 2013-11-17 08:00 | 2013-12-09 17:00 | 2013-11-17 08:00 | 2013-12-09 17:00 | 2013-11-17 08:00 | 2013-12-09 17:00 | 2013-11-20 08:00 | 2013-12-12 17:00 |  | PT_Normal |  |  |  |  | X99q+of/Rt+dDIfXjqxGTQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40050 | N | N | 10 | GROUND FLOOR |  | 124974 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 594.8 | LABOR- SUBCONTRACTOR
%R | 502659 | 6359 | 124976 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ELGF4005 | Cable tray & trunking installation | 8178 | 104 | 0 | 160 | 0 | 2044.8 | 2044.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-09 08:00 | 2014-02-01 17:00 |  | 2013-12-25 08:00 | 2014-01-16 17:00 | 2013-12-25 08:00 | 2014-01-16 17:00 | 2013-12-25 08:00 | 2014-01-16 17:00 | 2014-01-09 08:00 | 2014-02-01 17:00 |  | PT_Normal |  |  |  |  | wmFTheqHStaGVAhcj5jPuQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40050 | N | N | 10 | GROUND FLOOR |  | 124974 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 2044.8 | LABOR- SUBCONTRACTOR
%R | 502660 | 6359 | 124976 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ELGF4010 | Installation of wiring & Main Cabling | 8178 | 104 | 104 | 160 | 0 | 414.8 | 414.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-18 08:00 | 2014-02-09 17:00 |  | 2014-01-02 08:00 | 2014-01-25 17:00 | 2014-01-02 08:00 | 2014-01-25 17:00 | 2014-01-02 08:00 | 2014-01-25 17:00 | 2014-01-18 08:00 | 2014-02-09 17:00 |  | PT_Normal |  |  |  |  | pwC4KAMUQFWFgrZ0PZjUKQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40050 | N | N | 10 | GROUND FLOOR |  | 124974 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 414.8 | LABOR- SUBCONTRACTOR
%R | 502661 | 6359 | 124976 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 72 | 0 | 160 | 0 | 170.4 | 170.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-08 17:00 |  | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | ESN84CBUSjWmZbfaoQ+00A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40050 | N | N | 10 | GROUND FLOOR |  | 124974 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 170.4 | LABOR- SUBCONTRACTOR
%R | 502662 | 6359 | 124976 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 72 | 0 | 160 | 0 | 395.6 | 395.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-29 08:00 | 2014-04-20 17:00 |  | 2014-03-18 08:00 | 2014-04-09 17:00 | 2014-03-18 08:00 | 2014-04-09 17:00 | 2014-03-18 08:00 | 2014-04-09 17:00 | 2014-03-29 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | TO5Oc06VScmzA0qHGWxzaw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40050 | N | N | 10 | GROUND FLOOR |  | 124974 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 395.6 | LABOR- SUBCONTRACTOR
%R | 502663 | 6359 | 124976 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 104 | 104 | 160 | 0 | 1108.8 | 1108.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-05-15 17:00 |  | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-04-08 08:00 | 2014-04-30 17:00 | 2014-04-23 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | EKZTBQBITLuI3IvGMWviug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40050 | N | N | 10 | GROUND FLOOR |  | 124974 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1108.8 | LABOR- SUBCONTRACTOR
%R | 502664 | 6359 | 124976 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ELGF4030 | Installation of Telephone System | 8178 | 96 | 24 | 160 | 0 | 152.4 | 152.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-01 08:00 | 2014-04-23 17:00 |  | 2014-03-18 08:00 | 2014-04-09 17:00 | 2014-03-18 08:00 | 2014-04-09 17:00 | 2014-03-18 08:00 | 2014-04-09 17:00 | 2014-04-01 08:00 | 2014-04-23 17:00 |  | PT_Normal |  |  |  |  | 2wPY7jEpQ1+wCxzRZdoAUg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40050 | N | N | 10 | GROUND FLOOR |  | 124974 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 152.4 | LABOR- SUBCONTRACTOR
%R | 502665 | 6359 | 124978 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ACRF4635 | Installation of Condensing Unit | 8178 | 80 | 80 | 160 | 0 | 130.8 | 130.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-05-15 17:00 |  | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-04-23 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | dwcKmaFXRJatIY78vUHmpA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40150 | N | N | 20 | ROOF |  | 124977 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 130.8 | LABOR- SUBCONTRACTOR
%R | 502666 | 6359 | 124978 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ACRF4630 | Installation of Refrigerant Pipes | 8178 | 360 | 280 | 160 | 0 | 17.2 | 17.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-04 17:00 |  | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | c+xvFVJiRrO4BckMEideDw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40150 | N | N | 20 | ROOF |  | 124977 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 17.2 | LABOR- SUBCONTRACTOR
%R | 502667 | 6359 | 124979 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ACGF4600 | Installation AC Pipes | 8178 | 224 | 168 | 160 | 0 | 556.8 | 556.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-03-04 17:00 |  | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-02-09 08:00 | 2014-03-04 17:00 |  | PT_Normal |  |  |  |  | 3f76fg9jQbOqrn27gNyKxg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40130 | N | N | 10 | GROUND FLOOR |  | 124977 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 556.8 | LABOR- SUBCONTRACTOR
%R | 502668 | 6359 | 124979 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ACGF4605 | Fixing of Ventilation Equipments | 8178 | 0 | 0 | 200 | 0 | 85.2 | 85.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-12 17:00 |  | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 |  | PT_Normal |  |  |  |  | lQKPgaFeSNewOolB9b90Zw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40130 | N | N | 10 | GROUND FLOOR |  | 124977 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 85.2 | LABOR- SUBCONTRACTOR
%R | 502669 | 6359 | 124979 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ACGF4610 | Fixing of Split AC | 8178 | 0 | 0 | 160 | 0 | 154.8 | 154.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-04-28 17:00 |  | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | dx8oIL77QumoQGw90CL4ow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40130 | N | N | 10 | GROUND FLOOR |  | 124977 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 154.8 | LABOR- SUBCONTRACTOR
%R | 502670 | 6359 | 124980 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 0 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | Q8bkwQgBTtCYJSAVvM+I7g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40220 | N | N | 30 | TESTING AND COMMISSIONING |  | 124969 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 502671 | 6359 | 124980 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | DEa4nCVcTxSkN4g1yq6W5w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40220 | N | N | 30 | TESTING AND COMMISSIONING |  | 124969 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 502672 | 6359 | 124980 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | ptzhQ11YQfWgnRyl6NABBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40220 | N | N | 30 | TESTING AND COMMISSIONING |  | 124969 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 502673 | 6359 | 124983 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5AREL3665 | External Plastering | 8169 | 240 | 0 | 200 | 0 | 4012.5 | 4012.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-20 08:00 | 2014-04-17 17:00 |  | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 |  | PT_Normal |  |  |  |  | 53G/Apo6QoyhawgwOcrRow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40020 | N | N | 15 | ELEVATION |  | 124982 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 2006.25 | PLASTER MASON SK
%R | 502674 | 6359 | 124983 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5AREL3680 | External Painting | 8178 | 320 | 320 | 160 | 0 | 1408 | 1408 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-05-15 17:00 |  | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-04-23 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | TPsAUAgQSJqSG4BvScIXqw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40020 | N | N | 15 | ELEVATION |  | 124982 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1408 | LABOR- SUBCONTRACTOR
%R | 502675 | 6359 | 124984 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARRF3660 | Installation of Access Ladder | 8178 | 432 | 112 | 160 | 0 | 132 | 132 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-04 17:00 |  | 2014-02-06 08:00 | 2014-03-02 17:00 | 2014-02-06 08:00 | 2014-03-02 17:00 | 2014-02-06 08:00 | 2014-03-02 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | 8HiAyZJ7TWaQOakP1d0oHg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40010 | N | N | 10 | ROOF |  | 124982 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 132 | LABOR- SUBCONTRACTOR
%R | 502676 | 6359 | 124984 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARRF3625 | Laying of Pitched Roof | 8174 | 240 | 0 | 200 | 0 | 256 | 256 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-03 08:00 | 2014-03-04 17:00 |  | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40010 | N | N | 10 | ROOF |  | 124982 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 256 | INTERLOCK MASON SK
%R | 502677 | 6359 | 124984 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARRF3630 | Leveling Screed for Waterproofing | 8164 | 240 | 0 | 144 | 0 | 195.5 | 195.5 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-10 17:00 |  | 2014-01-13 08:00 | 2014-02-02 17:00 | 2014-01-13 08:00 | 2014-02-02 17:00 | 2014-01-13 08:00 | 2014-02-02 17:00 | 2014-02-18 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | 49LNCnpCSiq5FkjJ6CMHeA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40010 | N | N | 10 | ROOF |  | 124982 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 195.5 | SCREED MASON SK
%R | 502678 | 6359 | 124984 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARRF3635 | Laying of Waterproofing Membrane | 8178 | 240 | 0 | 144 | 0 | 722.25 | 722.25 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-16 17:00 |  | 2014-01-19 08:00 | 2014-02-08 17:00 | 2014-01-19 08:00 | 2014-02-08 17:00 | 2014-01-19 08:00 | 2014-02-08 17:00 | 2014-02-24 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | 9wAWauA4S8aBW7o1I8OL0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40010 | N | N | 10 | ROOF |  | 124982 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 722.25 | LABOR- SUBCONTRACTOR
%R | 502679 | 6359 | 124984 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARRF3640 | Installation of Insulation & Protection | 8178 | 240 | 0 | 144 | 0 | 343.75 | 343.75 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-01 08:00 | 2014-03-20 17:00 |  | 2014-01-23 08:00 | 2014-02-13 17:00 | 2014-01-23 08:00 | 2014-02-13 17:00 | 2014-01-23 08:00 | 2014-02-13 17:00 | 2014-03-01 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | ycVb2qXKSy2ygL+/ecroHQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40010 | N | N | 10 | ROOF |  | 124982 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 343.75 | LABOR- SUBCONTRACTOR
%R | 502680 | 6359 | 124984 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 240 | 0 | 144 | 0 | 344.5 | 344.5 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-03-29 17:00 |  | 2014-02-01 08:00 | 2014-02-22 17:00 | 2014-02-01 08:00 | 2014-02-22 17:00 | 2014-02-01 08:00 | 2014-02-22 17:00 | 2014-03-09 08:00 | 2014-03-29 17:00 |  | PT_Normal |  |  |  |  | FEwY2z64SfqTP6j9fW7l0A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40010 | N | N | 10 | ROOF |  | 124982 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 344.5 | TILE MASON SK
%R | 502681 | 6359 | 124986 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARGF3030 | Paint First coat | 8178 | 48 | 48 | 160 | 0 | 1815 | 1815 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-18 08:00 | 2014-02-09 17:00 |  | 2014-01-11 08:00 | 2014-02-02 17:00 | 2014-01-11 08:00 | 2014-02-02 17:00 | 2014-01-11 08:00 | 2014-02-02 17:00 | 2014-01-18 08:00 | 2014-02-09 17:00 |  | PT_Normal |  |  |  |  | 9ikDtyb6RDu7ahT4S4fc6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39970 | N | N | 10 | GROUND FLOOR |  | 124985 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1815 | LABOR- SUBCONTRACTOR
%R | 502682 | 6359 | 124986 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARGF3020 | Ceramic Wall Tiling | 8170 | 0 | 0 | 120 | 0 | 1012.5 | 1012.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-01 08:00 | 2014-01-18 17:00 |  | 2014-01-01 08:00 | 2014-01-18 17:00 | 2014-01-01 08:00 | 2014-01-18 17:00 | 2014-01-01 08:00 | 2014-01-18 17:00 | 2014-01-01 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | /sWgPF2/Rn+ftZXTrdBmRQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39970 | N | N | 10 | GROUND FLOOR |  | 124985 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1012.5 | TILE MASON SK
%R | 502683 | 6359 | 124986 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARGF3025 | Porcelain Tile flooring | 8170 | 0 | 0 | 160 | 0 | 1030.25 | 1030.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-18 08:00 | 2014-02-09 17:00 |  | 2014-01-18 08:00 | 2014-02-09 17:00 | 2014-01-18 08:00 | 2014-02-09 17:00 | 2014-01-18 08:00 | 2014-02-09 17:00 | 2014-01-18 08:00 | 2014-02-09 17:00 |  | PT_Normal |  |  |  |  | 9Acm0aPxTNCJ70f+FMm/ZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39970 | N | N | 10 | GROUND FLOOR |  | 124985 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1030.25 | TILE MASON SK
%R | 502684 | 6359 | 124986 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARGF3040 | Cobble Tile flooring | 8170 | 136 | 136 | 120 | 0 | 300 | 300 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-02 08:00 | 2014-04-19 17:00 |  | 2014-03-13 08:00 | 2014-03-30 17:00 | 2014-03-13 08:00 | 2014-03-30 17:00 | 2014-03-13 08:00 | 2014-03-30 17:00 | 2014-04-02 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | gAhyXk9JQR2N8vn6qmLePw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39970 | N | N | 10 | GROUND FLOOR |  | 124985 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 300 | TILE MASON SK
%R | 502685 | 6359 | 124986 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 104 | 0 | 144 | 0 | 1575 | 1575 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-10 08:00 | 2014-03-30 17:00 |  | 2014-02-23 08:00 | 2014-03-15 17:00 | 2014-02-23 08:00 | 2014-03-15 17:00 | 2014-02-23 08:00 | 2014-03-15 17:00 | 2014-03-10 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | l1DF+9wlQwinipX1D649nQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39970 | N | N | 10 | GROUND FLOOR |  | 124985 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1575 | TILE MASON SK
%R | 502686 | 6359 | 124986 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARGF3045 | Fixing of Suspension systems | 8178 | 0 | 0 | 120 | 0 | 653.5 | 653.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-02-26 17:00 |  | 2014-02-09 08:00 | 2014-02-26 17:00 | 2014-02-09 08:00 | 2014-02-26 17:00 | 2014-02-09 08:00 | 2014-02-26 17:00 | 2014-02-09 08:00 | 2014-02-26 17:00 |  | PT_Normal |  |  |  |  | 2A1mAvTfQRac5r72+nyVOw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39970 | N | N | 10 | GROUND FLOOR |  | 124985 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 653.5 | LABOR- SUBCONTRACTOR
%R | 502687 | 6359 | 124986 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARGF3060 | Gypsum board false ceiling | 8178 | 0 | 0 | 160 | 0 | 653.5 | 653.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-26 08:00 | 2014-03-20 17:00 |  | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | ZCo2YDC9Q+2y1su0E2UE6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39970 | N | N | 10 | GROUND FLOOR |  | 124985 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 653.5 | LABOR- SUBCONTRACTOR
%R | 502688 | 6359 | 124986 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARGF3065 | Wooden door | 8178 | 80 | 0 | 120 | 0 | 198 | 198 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-07 17:00 |  | 2014-03-10 08:00 | 2014-03-26 17:00 | 2014-03-10 08:00 | 2014-03-26 17:00 | 2014-03-10 08:00 | 2014-03-26 17:00 | 2014-03-22 08:00 | 2014-04-07 17:00 |  | PT_Normal |  |  |  |  | GDRKjXbeRnq+6w4vhXIhvQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39970 | N | N | 10 | GROUND FLOOR |  | 124985 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 198 | LABOR- SUBCONTRACTOR
%R | 502689 | 6359 | 124986 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARGF3080 | Aluminum windows | 8178 | 80 | 80 | 144 | 0 | 132 | 132 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-08 08:00 | 2014-04-28 17:00 |  | 2014-03-27 08:00 | 2014-04-16 17:00 | 2014-03-27 08:00 | 2014-04-16 17:00 | 2014-03-27 08:00 | 2014-04-16 17:00 | 2014-04-08 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39970 | N | N | 10 | GROUND FLOOR |  | 124985 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 132 | LABOR- SUBCONTRACTOR
%R | 502690 | 6359 | 124986 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARGF3075 | Carpentry & Joinery Works | 8178 | 112 | 48 | 144 | 0 | 528 | 528 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-01 08:00 | 2014-04-21 17:00 |  | 2014-03-16 08:00 | 2014-04-05 17:00 | 2014-03-16 08:00 | 2014-04-05 17:00 | 2014-03-16 08:00 | 2014-04-05 17:00 | 2014-04-01 08:00 | 2014-04-21 17:00 |  | PT_Normal |  |  |  |  | O1YTZfXdQUW9IChlr3nFGA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39970 | N | N | 10 | GROUND FLOOR |  | 124985 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 528 | LABOR- SUBCONTRACTOR
%R | 502691 | 6359 | 124986 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARGF3090 | Installation of Granite Counter Top | 8171 | 64 | 64 | 120 | 0 | 99 | 99 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-04-28 17:00 |  | 2014-04-02 08:00 | 2014-04-19 17:00 | 2014-04-02 08:00 | 2014-04-19 17:00 | 2014-04-02 08:00 | 2014-04-19 17:00 | 2014-04-12 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | bufFZHJ1Srmp4oVgfnaspg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39970 | N | N | 10 | GROUND FLOOR |  | 124985 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 99 | GRANITE MASON SK
%R | 502692 | 6359 | 124986 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARGF3095 | Final Painting | 8178 | 0 | 0 | 200 | 0 | 1815 | 1815 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | XIHsQlkuSMmuetuQw6lbcw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39970 | N | N | 10 | GROUND FLOOR |  | 124985 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1815 | LABOR- SUBCONTRACTOR
%R | 502693 | 6359 | 124986 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARGF3000 | Block work | 8168 | 0 | 0 | 200 | 0 | 5700 | 5700 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-03 08:00 | 2013-12-01 17:00 |  | 2013-11-03 08:00 | 2013-12-01 17:00 | 2013-11-03 08:00 | 2013-12-01 17:00 | 2013-11-03 08:00 | 2013-12-01 17:00 | 2013-11-03 08:00 | 2013-12-01 17:00 |  | PT_Normal |  |  |  |  | Yy18cUQeSjOygtIowuWsJw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39970 | N | N | 10 | GROUND FLOOR |  | 124985 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 5700 | BLOCK MASON SK
%R | 502694 | 6359 | 124986 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARGF3005 | Plastering work | 8169 | 0 | 0 | 200 | 0 | 2850 | 2850 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-26 08:00 | 2013-12-25 17:00 |  | 2013-11-26 08:00 | 2013-12-25 17:00 | 2013-11-26 08:00 | 2013-12-25 17:00 | 2013-11-26 08:00 | 2013-12-25 17:00 | 2013-11-26 08:00 | 2013-12-25 17:00 |  | PT_Normal |  |  |  |  | 6puN92NDS7a79VzkWEWRTA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39970 | N | N | 10 | GROUND FLOOR |  | 124985 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 2850 | PLASTER MASON SK
%R | 502695 | 6359 | 124986 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARGF3010 | Flooring screed | 8164 | 160 | 160 | 160 | 0 | 634.25 | 634.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-01 08:00 | 2014-01-23 17:00 |  | 2013-12-08 08:00 | 2013-12-31 17:00 | 2013-12-08 08:00 | 2013-12-31 17:00 | 2013-12-08 08:00 | 2013-12-31 17:00 | 2014-01-01 08:00 | 2014-01-23 17:00 |  | PT_Normal |  |  |  |  | nqpCKPSWQ1SjDhBwLOGwfA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39970 | N | N | 10 | GROUND FLOOR |  | 124985 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 634.25 | SCREED MASON SK
%R | 502696 | 6359 | 124986 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 0 | 0 | 160 | 0 | 87 | 87 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-12 08:00 | 2014-01-05 17:00 |  | 2013-12-12 08:00 | 2014-01-05 17:00 | 2013-12-12 08:00 | 2014-01-05 17:00 | 2013-12-12 08:00 | 2014-01-05 17:00 | 2013-12-12 08:00 | 2014-01-05 17:00 |  | PT_Normal |  |  |  |  | KeT17u8iSe6FIVGUGIrf/w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39970 | N | N | 10 | GROUND FLOOR |  | 124985 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 87 | LABOR- SUBCONTRACTOR
%R | 502697 | 6359 | 124989 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5STUG1000 | Footing Excavation | 8177 | 16 | 0 | 200 | 0 | 476 | 476 | 200 | 224 | 0 | 224 |  |  |  | 2013-05-11 08:00 | 2013-06-08 17:00 |  | 2013-05-08 08:00 | 2013-06-05 17:00 | 2013-05-08 08:00 | 2013-06-05 17:00 | 2013-05-08 08:00 | 2013-06-05 17:00 | 2013-05-11 08:00 | 2013-06-08 17:00 |  | PT_Normal |  |  |  |  | ER8+82h3SuKQWjAULoPOtw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39900 | N | N | 10 | UPTO GRADE SLAB |  | 124988 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 476 | LABOR - CIVIL
%R | 502698 | 6359 | 124989 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5STUG1005 | Footing Antitermite | 8178 | 16 | 0 | 160 | 0 | 902 | 902 | 160 | 0 | 0 | 0 |  |  |  | 2013-05-22 08:00 | 2013-06-13 17:00 |  | 2013-05-20 08:00 | 2013-06-11 17:00 | 2013-05-20 08:00 | 2013-06-11 17:00 | 2013-05-20 08:00 | 2013-06-11 17:00 | 2013-05-22 08:00 | 2013-06-13 17:00 |  | PT_Normal |  |  |  |  | diibYg7OTVCr5Gg+5vMNoA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39900 | N | N | 10 | UPTO GRADE SLAB |  | 124988 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 902 | LABOR- SUBCONTRACTOR
%R | 502699 | 6359 | 124989 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5STUG1010 | Footing Blinding | 8163 | 16 | 0 | 160 | 0 | 29.75 | 29.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-05-25 08:00 | 2013-06-16 17:00 |  | 2013-05-22 08:00 | 2013-06-13 17:00 | 2013-05-22 08:00 | 2013-06-13 17:00 | 2013-05-22 08:00 | 2013-06-13 17:00 | 2013-05-25 08:00 | 2013-06-16 17:00 |  | PT_Normal |  |  |  |  | D2wpngBSQzKJRVYsSrwTRA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39900 | N | N | 10 | UPTO GRADE SLAB |  | 124988 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 29.75 | BLINDING MASON SK
%R | 502700 | 6359 | 124989 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5STUG1015 | Footing Waterproofing & Screed | 8164 | 16 | 0 | 160 | 0 | 483 | 483 | 160 | 0 | 0 | 0 |  |  |  | 2013-05-30 08:00 | 2013-06-22 17:00 |  | 2013-05-28 08:00 | 2013-06-19 17:00 | 2013-05-28 08:00 | 2013-06-19 17:00 | 2013-05-28 08:00 | 2013-06-19 17:00 | 2013-05-30 08:00 | 2013-06-22 17:00 |  | PT_Normal |  |  |  |  | aoUfJWbSQjGv0kTM7HPOJA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39900 | N | N | 10 | UPTO GRADE SLAB |  | 124988 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 483 | SCREED MASON SK
%R | 502701 | 6359 | 124989 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5STUG1020 | Construction of foundations | 8165 | 16 | 0 | 160 | 0 | 1335.25 | 1335.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-06-09 08:00 | 2013-07-01 17:00 |  | 2013-06-06 08:00 | 2013-06-29 17:00 | 2013-06-06 08:00 | 2013-06-29 17:00 | 2013-06-06 08:00 | 2013-06-29 17:00 | 2013-06-09 08:00 | 2013-07-01 17:00 |  | PT_Normal |  |  |  |  | IW95pxGaQiiiCgyMpLCaBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39900 | N | N | 10 | UPTO GRADE SLAB |  | 124988 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 1335.25 | STEEL FIXERS SK
%R | 502702 | 6359 | 124989 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5STUG1025 | Construction of neck of columns | 8165 | 16 | 0 | 160 | 0 | 1389.5 | 1389.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-06-18 08:00 | 2013-07-10 17:00 |  | 2013-06-16 08:00 | 2013-07-08 17:00 | 2013-06-16 08:00 | 2013-07-08 17:00 | 2013-06-16 08:00 | 2013-07-08 17:00 | 2013-06-18 08:00 | 2013-07-10 17:00 |  | PT_Normal |  |  |  |  | b+b+W73PRSWOGD+INfFNIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39900 | N | N | 10 | UPTO GRADE SLAB |  | 124988 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 1389.5 | STEEL FIXERS SK
%R | 502703 | 6359 | 124989 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5STUG1030 | Waterproofing Footing & Neck Column | 8178 | 16 | 0 | 160 | 0 | 125.5 | 125.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-06-27 08:00 | 2013-07-20 17:00 |  | 2013-06-25 08:00 | 2013-07-17 17:00 | 2013-06-25 08:00 | 2013-07-17 17:00 | 2013-06-25 08:00 | 2013-07-17 17:00 | 2013-06-27 08:00 | 2013-07-20 17:00 |  | PT_Normal |  |  |  |  | rgVJYNaKQBC/NFvRVluzFQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39900 | N | N | 10 | UPTO GRADE SLAB |  | 124988 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 125.5 | LABOR- SUBCONTRACTOR
%R | 502704 | 6359 | 124989 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 16 | 0 | 160 | 0 | 822 | 822 | 160 | 660 | 0 | 660 |  |  |  | 2013-07-09 08:00 | 2013-07-31 17:00 |  | 2013-07-07 08:00 | 2013-07-29 17:00 | 2013-07-07 08:00 | 2013-07-29 17:00 | 2013-07-07 08:00 | 2013-07-29 17:00 | 2013-07-09 08:00 | 2013-07-31 17:00 |  | PT_Normal |  |  |  |  | pbRt3bCKSfGk6HTeVPa5Kw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39900 | N | N | 10 | UPTO GRADE SLAB |  | 124988 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 822 | LABOR - CIVIL
%R | 502705 | 6359 | 124989 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5STUG1040 | Construction of Grade Beams | 8163 | 16 | 0 | 200 | 0 | 2325.75 | 2325.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-21 08:00 | 2013-08-21 17:00 |  | 2013-07-18 08:00 | 2013-08-19 17:00 | 2013-07-18 08:00 | 2013-08-19 17:00 | 2013-07-18 08:00 | 2013-08-19 17:00 | 2013-07-21 08:00 | 2013-08-21 17:00 |  | PT_Normal |  |  |  |  | FRTDSwYyS8qrYSSsEROBlQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39900 | N | N | 10 | UPTO GRADE SLAB |  | 124988 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 1162.875 | BLINDING MASON SK
%R | 502706 | 6359 | 124989 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5STUG1045 | Construction of slab on grade | 8163 | 16 | 0 | 200 | 0 | 1541.75 | 1541.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-15 08:00 | 2013-09-12 17:00 |  | 2013-08-13 08:00 | 2013-09-10 17:00 | 2013-08-13 08:00 | 2013-09-10 17:00 | 2013-08-13 08:00 | 2013-09-10 17:00 | 2013-08-15 08:00 | 2013-09-12 17:00 |  | PT_Normal |  |  |  |  | Asvr+8JOTHGBU5uFe6HnFg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39900 | N | N | 10 | UPTO GRADE SLAB |  | 124988 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 1541.75 | BLINDING MASON SK
%R | 502707 | 6359 | 124991 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5STGF2000 | Column-Rebar & Formwork | 8165 | 16 | 0 | 160 | 0 | 1524.25 | 1524.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-09-02 08:00 | 2013-09-24 17:00 |  | 2013-08-31 08:00 | 2013-09-22 17:00 | 2013-08-31 08:00 | 2013-09-22 17:00 | 2013-08-31 08:00 | 2013-09-22 17:00 | 2013-09-02 08:00 | 2013-09-24 17:00 |  | PT_Normal |  |  |  |  | ryR+SKiCS32167f1pAZpdQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39920 | N | N | 10 | GROUND FLOOR |  | 124990 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 1524.25 | STEEL FIXERS SK
%R | 502708 | 6359 | 124991 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5STGF2005 | Column-Concrete | 8167 | 16 | 0 | 120 | 0 | 105 | 105 | 120 | 0 | 0 | 0 |  |  |  | 2013-09-12 08:00 | 2013-09-29 17:00 |  | 2013-09-10 08:00 | 2013-09-26 17:00 | 2013-09-10 08:00 | 2013-09-26 17:00 | 2013-09-10 08:00 | 2013-09-26 17:00 | 2013-09-12 08:00 | 2013-09-29 17:00 |  | PT_Normal |  |  |  |  | udUf8W09Qo6qhy7Krd6WZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39920 | N | N | 10 | GROUND FLOOR |  | 124990 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 105 | CONCRETE MASON SK
%R | 502709 | 6359 | 124991 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 16 | 0 | 200 | 0 | 6076 | 6076 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-21 08:00 | 2013-10-21 17:00 |  | 2013-09-18 08:00 | 2013-10-16 17:00 | 2013-09-18 08:00 | 2013-10-16 17:00 | 2013-09-18 08:00 | 2013-10-16 17:00 | 2013-09-21 08:00 | 2013-10-21 17:00 |  | PT_Normal |  |  |  |  | ewfZeJfbTteNqNto8Pth8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39920 | N | N | 10 | GROUND FLOOR |  | 124990 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 6076 | STEEL FIXERS SK
%R | 502710 | 6359 | 124991 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 16 | 16 | 120 | 0 | 1302 | 1302 | 120 | 0 | 0 | 0 |  |  |  | 2013-10-07 08:00 | 2013-10-26 17:00 |  | 2013-10-05 08:00 | 2013-10-23 17:00 | 2013-10-05 08:00 | 2013-10-23 17:00 | 2013-10-05 08:00 | 2013-10-23 17:00 | 2013-10-07 08:00 | 2013-10-26 17:00 |  | PT_Normal |  |  |  |  | E27BVydvQm+aubiyr++1Pw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39920 | N | N | 10 | GROUND FLOOR |  | 124990 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1302 | CONCRETE MASON SK
%R | 502711 | 6359 | 124992 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5STRF2060 | Construction of Parapets | 8165 | 152 | 0 | 160 | 0 | 521.5 | 521.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-01 08:00 | 2013-12-24 17:00 |  | 2013-11-09 08:00 | 2013-12-01 17:00 | 2013-11-09 08:00 | 2013-12-01 17:00 | 2013-11-09 08:00 | 2013-12-01 17:00 | 2013-12-01 08:00 | 2013-12-24 17:00 |  | PT_Normal |  |  |  |  | yKZ1/s1PRriCkVaQe47iYQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39940 | N | N | 20 | ROOF |  | 124990 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 521.5 | STEEL FIXERS SK
%R | 502712 | 6359 | 124992 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5STRF2065 | Construction of up stands/Plinth | 8166 | 288 | 80 | 160 | 0 | 84 | 84 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-29 08:00 | 2014-01-20 17:00 |  | 2013-11-16 08:00 | 2013-12-08 17:00 | 2013-11-16 08:00 | 2013-12-08 17:00 | 2013-11-16 08:00 | 2013-12-08 17:00 | 2013-12-29 08:00 | 2014-01-20 17:00 |  | PT_Normal |  |  |  |  | XyvTY8WkSqeFfbVOvnJLQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39940 | N | N | 20 | ROOF |  | 124990 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 84 | CARPENTERS SK
%R | 502713 | 6359 | 124994 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5MSEX5020 | Construction Entrance Ramp | 8164 | 240 | 0 | 160 | 0 | 436 | 436 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-02-23 17:00 |  | 2013-12-26 08:00 | 2014-01-18 17:00 | 2013-12-26 08:00 | 2014-01-18 17:00 | 2013-12-26 08:00 | 2014-01-18 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | H0fQkmt/QQKAfw3MLTKLFA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40180 | N | N | 10 | MISCELLANEOUS |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 436 | SCREED MASON SK
%R | 502714 | 6359 | 124994 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5MSEX5025 | SS.Handrails and Balustrades | 8178 | 240 | 0 | 160 | 0 | 136 | 136 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-18 17:00 |  | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | WXAV0rEcS7KWJ2J0Z5Gq5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40180 | N | N | 10 | MISCELLANEOUS |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 136 | LABOR- SUBCONTRACTOR
%R | 502715 | 6359 | 124994 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5MSEX5015 | Construction of grease Trap | 8178 | 208 | 0 | 160 | 0 | 168 | 168 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-03-02 17:00 |  | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-02-06 08:00 | 2014-03-02 17:00 |  | PT_Normal |  |  |  |  | OuKhl4ScQFW6n0NWRDSUew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40180 | N | N | 10 | MISCELLANEOUS |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 168 | LABOR- SUBCONTRACTOR
%R | 502716 | 6359 | 124994 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5MSEX5000 | Construction of Manholes | 8172 | 208 | 0 | 200 | 0 | 132 | 132 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-04 08:00 | 2014-02-01 17:00 |  | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2014-01-04 08:00 | 2014-02-01 17:00 |  | PT_Normal |  |  |  |  | cPgx8RQGRXqbEIdqWfB9Gw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40180 | N | N | 10 | MISCELLANEOUS |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 132 | MANHOLES SK
%R | 502717 | 6359 | 124994 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5MSEX5005 | Construction of Soak pit, Chambers | 8172 | 208 | 0 | 200 | 0 | 66 | 66 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-18 08:00 | 2014-02-16 17:00 |  | 2013-12-17 08:00 | 2014-01-15 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 | 2014-01-18 08:00 | 2014-02-16 17:00 |  | PT_Normal |  |  |  |  | EQmpWa0MTk+w6FgVg9TFvQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40180 | N | N | 10 | MISCELLANEOUS |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 66 | MANHOLES SK
%R | 502718 | 6359 | 124994 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5MSEX5055 | Installation Steel Door | 8178 | 240 | 0 | 160 | 0 | 180 | 180 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-06 17:00 |  | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | V+3WajOnRAW4AmU4obM3uQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40180 | N | N | 10 | MISCELLANEOUS |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 180 | LABOR- SUBCONTRACTOR
%R | 502719 | 6359 | 124994 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5MSEX5010 | Telephone cable laying | 8177 | 208 | 112 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-03 08:00 | 2014-03-31 17:00 |  | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | ynpAsb38QH6geYSytNGFgA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40180 | N | N | 10 | MISCELLANEOUS |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01; period 2: 2014-AP03 |  | 250 | LABOR - CIVIL
%R | 502720 | 6359 | 124995 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5WEEX5030 | Excavation | 8177 | 120 | 0 | 160 | 0 | 116 | 116 | 160 | 80 | 0 | 80 |  |  |  | 2014-02-12 08:00 | 2014-03-06 17:00 |  | 2014-01-25 08:00 | 2014-02-17 17:00 | 2014-01-25 08:00 | 2014-02-17 17:00 | 2014-01-25 08:00 | 2014-02-17 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | bPmluXkQSguXNYrNOELDNQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40190 | N | N | 15 | WATER TANK ENCLOSURE |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 116 | LABOR - CIVIL
%R | 502721 | 6359 | 124995 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5WEEX5035 | Construction of Raft | 8167 | 120 | 0 | 200 | 0 | 210 | 210 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-18 17:00 |  | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | eOcPdWLMTVaLEioTmPwWsg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40190 | N | N | 15 | WATER TANK ENCLOSURE |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01; period 2: 2014-AP03 |  | 105 | CONCRETE MASON SK
%R | 502722 | 6359 | 124995 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5WEEX5040 | Block works & Plastering | 8168 | 120 | 0 | 200 | 0 | 692 | 692 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-27 08:00 | 2014-03-27 17:00 |  | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 |  | PT_Normal |  |  |  |  | z/9efpX9Q26ijyCSuPtjEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40190 | N | N | 15 | WATER TANK ENCLOSURE |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 346 | BLOCK MASON SK
%R | 502723 | 6359 | 124995 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5WEEX5045 | Flooring & Painting | 8164 | 120 | 0 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-04-08 17:00 |  | 2014-02-22 08:00 | 2014-03-22 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | NZrBetMhRXSLovl0mSjprw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40190 | N | N | 15 | WATER TANK ENCLOSURE |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 168 | SCREED MASON SK
%R | 502724 | 6359 | 124995 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5WEEX5050 | Installation of Steel | 8178 | 120 | 0 | 160 | 0 | 150 | 150 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-29 08:00 | 2014-04-20 17:00 |  | 2014-03-11 08:00 | 2014-04-02 17:00 | 2014-03-11 08:00 | 2014-04-02 17:00 | 2014-03-11 08:00 | 2014-04-02 17:00 | 2014-03-29 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | ERCRqfLAScOdG3QzdoQ1QQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40190 | N | N | 15 | WATER TANK ENCLOSURE |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 150 | LABOR- SUBCONTRACTOR
%R | 502725 | 6359 | 124995 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 120 | 0 | 200 | 0 | 534 | 534 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-03 08:00 | 2014-05-01 17:00 |  | 2014-03-17 08:00 | 2014-04-14 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | eJRlpLuoS16qX2gYmiXotA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40190 | N | N | 15 | WATER TANK ENCLOSURE |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 534 | LABOR- SUBCONTRACTOR
%R | 502726 | 6359 | 124995 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 120 | 40 | 200 | 0 | 286.8 | 286.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-13 17:00 |  | 2014-03-29 08:00 | 2014-04-26 17:00 | 2014-03-29 08:00 | 2014-04-26 17:00 | 2014-03-29 08:00 | 2014-04-26 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 |  | PT_Normal |  |  |  |  | M7WnqxpiTwywWpNtiVX1Sg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40190 | N | N | 15 | WATER TANK ENCLOSURE |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 286.8 | LABOR- SUBCONTRACTOR
%R | 502727 | 6359 | 124995 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5WEEX5070 | Installation ladder for water Tank | 8178 | 80 | 80 | 160 | 0 | 200 | 200 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-05-15 17:00 |  | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-04-23 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | JM6WAr5PTTyfvAF7jVZgCQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40190 | N | N | 15 | WATER TANK ENCLOSURE |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 200 | LABOR- SUBCONTRACTOR
%R | 502728 | 6359 | 124995 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 208 | 208 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | We2oIzwAR8u5KNY4SCdFwQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40190 | N | N | 15 | WATER TANK ENCLOSURE |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 400 | LABOR- SUBCONTRACTOR
%R | 502729 | 6359 | 124996 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5HDEX5090 | kerb works | 8173 | 240 | 0 | 160 | 0 | 236 | 236 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-04 08:00 | 2014-03-26 17:00 |  | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-03-04 08:00 | 2014-03-26 17:00 |  | PT_Normal |  |  |  |  | y0eXUY/HSbCWCBKA0iprYQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40200 | N | N | 20 | HARD LANDSCAPING |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 236 | KERBSTONE MASON SK
%R | 502730 | 6359 | 124996 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5HDEX5095 | Cobble Stone Works | 8170 | 240 | 0 | 160 | 0 | 86 | 86 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-16 08:00 | 2014-04-07 17:00 |  | 2014-02-08 08:00 | 2014-03-03 17:00 | 2014-02-08 08:00 | 2014-03-03 17:00 | 2014-02-08 08:00 | 2014-03-03 17:00 | 2014-03-16 08:00 | 2014-04-07 17:00 |  | PT_Normal |  |  |  |  | KDnFiMz6QDSQ1OX7f7mi5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40200 | N | N | 20 | HARD LANDSCAPING |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 86 | TILE MASON SK
%R | 502731 | 6359 | 124996 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5HDEX5100 | Interlock works | 8174 | 240 | 72 | 160 | 0 | 300 | 300 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-22 17:00 |  | 2014-02-24 08:00 | 2014-03-18 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | s7LMcSLxTLqrr30g9aM2xA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40200 | N | N | 20 | HARD LANDSCAPING |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 300 | INTERLOCK MASON SK
%R | 502732 | 6359 | 124997 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5SLEX5105 | Laying of Grass/ green area | 8178 | 168 | 0 | 160 | 0 | 2142 | 2142 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-04 17:00 |  | 2014-03-18 08:00 | 2014-04-09 17:00 | 2014-03-18 08:00 | 2014-04-09 17:00 | 2014-03-18 08:00 | 2014-04-09 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | bcIeG0VNScSJIscyxwSKSQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40210 | N | N | 25 | SOFT LANDSCAPING |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 2142 | LABOR- SUBCONTRACTOR
%R | 502733 | 6359 | 124997 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ5SLEX5110 | Laying of Palm tree | 8178 | 168 | 168 | 160 | 0 | 546 | 546 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-05-15 17:00 |  | 2014-03-30 08:00 | 2014-04-21 17:00 | 2014-03-30 08:00 | 2014-04-21 17:00 | 2014-03-30 08:00 | 2014-04-21 17:00 | 2014-04-23 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | L01gYBmjSoeliiz2ZJ97Iw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40210 | N | N | 25 | SOFT LANDSCAPING |  | 124993 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 546 | LABOR- SUBCONTRACTOR
%R | 502734 | 6359 | 124998 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BGNSP001000 | Survey works, | 8175 | 0 | 0 | 160 | 0 | 87.5 | 87.5 | 160 | 0 | 0 | 0 |  |  |  | 2012-12-01 08:00 | 2012-12-24 17:00 |  | 2012-12-01 08:00 | 2012-12-24 17:00 | 2012-12-01 08:00 | 2012-12-24 17:00 | 2012-12-01 08:00 | 2012-12-24 17:00 | 2012-12-01 08:00 | 2012-12-24 17:00 |  | PT_Normal |  |  |  |  | sf+hygHwTta03pNqmIdXDA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43520 |  |  |  |  | SURVEYOR SK | J315 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39140 | N | N | 18 | SITE PREPARATORY WORKS |  | 124939 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 87.5 | SURVEYOR SK
%R | 502735 | 6359 | 124998 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BGNSP002000 | Scanning for Existing Services for rerouting | 8180 | 0 | 0 | 96 | 0 | 325 | 325 | 96 | 0 | 0 | 0 |  |  |  | 2012-12-06 08:00 | 2012-12-20 17:00 |  | 2012-12-06 08:00 | 2012-12-20 17:00 | 2012-12-06 08:00 | 2012-12-20 17:00 | 2012-12-06 08:00 | 2012-12-20 17:00 | 2012-12-06 08:00 | 2012-12-20 17:00 |  | PT_Normal |  |  |  |  | WYB0cjpCTfuTnTssOhiawQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43571 |  |  |  |  | ELECTRICIANS SK | M302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39140 | N | N | 18 | SITE PREPARATORY WORKS |  | 124939 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 325 | ELECTRICIANS SK
%R | 502736 | 6359 | 124998 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BGNSP003000 | Site stripping | 8177 | 344 | 0 | 160 | 0 | 675 | 675 | 160 | 300 | 0 | 300 |  |  |  | 2013-02-03 08:00 | 2013-02-26 17:00 |  | 2012-12-13 08:00 | 2013-01-06 17:00 | 2012-12-13 08:00 | 2013-01-06 17:00 | 2012-12-13 08:00 | 2013-01-06 17:00 | 2013-02-03 08:00 | 2013-02-26 17:00 |  | PT_Normal |  |  |  |  | okRBS1pfR7K4j8rzzyGizg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39140 | N | N | 18 | SITE PREPARATORY WORKS |  | 124939 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 675 | LABOR - CIVIL
%R | 502737 | 6359 | 124998 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BGNSP004000 | Demolition of Existing building & landscaping | 8177 | 344 | 0 | 160 | 0 | 2687.5 | 2687.5 | 160 | 1750 | 0 | 1750 |  |  |  | 2013-02-09 08:00 | 2013-03-04 17:00 |  | 2012-12-20 08:00 | 2013-01-12 17:00 | 2012-12-20 08:00 | 2013-01-12 17:00 | 2012-12-20 08:00 | 2013-01-12 17:00 | 2013-02-09 08:00 | 2013-03-04 17:00 |  | PT_Normal |  |  |  |  | NiChegq5Q0WEc/bzVm7qjw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39140 | N | N | 18 | SITE PREPARATORY WORKS |  | 124939 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 2687.5 | LABOR - CIVIL
%R | 502738 | 6359 | 124998 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BGNSP005000 | Demolition of existing services works | 8177 | 344 | 344 | 160 | 0 | 775 | 775 | 160 | 400 | 0 | 400 |  |  |  | 2013-02-16 08:00 | 2013-03-10 17:00 |  | 2012-12-26 08:00 | 2013-01-17 17:00 | 2012-12-26 08:00 | 2013-01-17 17:00 | 2012-12-26 08:00 | 2013-01-17 17:00 | 2013-02-16 08:00 | 2013-03-10 17:00 |  | PT_Normal |  |  |  |  | Z7giiagSQm2EQytwieE4WQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39140 | N | N | 18 | SITE PREPARATORY WORKS |  | 124939 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 775 | LABOR - CIVIL
%R | 502739 | 6359 | 124998 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BGNSP002100 | Submission of Scanning Reports |  | 0 | 0 | 56 | 0 | 40 | 40 | 56 | 0 | 0 | 0 |  |  |  | 2012-12-22 08:00 | 2012-12-29 17:00 |  | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 |  | PT_Normal |  |  |  |  | soRUpRNaQ1qNelFupN1iJQ | 4KFvqL/XTj6N1/VzcFih0A |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 39140 | N | N | 18 | SITE PREPARATORY WORKS |  | 124939 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 40 | 0
%R | 502740 | 6359 | 124998 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BGNSP002200 | Information Required for Rerouting |  | 0 | 0 | 112 | 0 | 0 | 0 | 112 | 0 | 0 | 0 |  |  |  | 2012-12-30 08:00 | 2013-01-14 17:00 |  | 2012-12-30 08:00 | 2013-01-14 17:00 | 2012-12-30 08:00 | 2013-01-14 17:00 | 2012-12-30 08:00 | 2013-01-14 17:00 | 2012-12-30 08:00 | 2013-01-14 17:00 |  | PT_Normal |  |  |  |  | 0wkCWkomSuGemx3jYVuQpg | 0umPvUk9bkKXzcQTENb+qA |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 39140 | N | N | 18 | SITE PREPARATORY WORKS |  | 124939 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 502741 | 6359 | 124998 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BGNSP002300 | Preparation & Submission for New Layout |  | 0 | 0 | 56 | 0 | 40 | 40 | 56 | 0 | 0 | 0 |  |  |  | 2013-01-15 08:00 | 2013-01-22 17:00 |  | 2013-01-15 08:00 | 2013-01-22 17:00 | 2013-01-15 08:00 | 2013-01-22 17:00 | 2013-01-15 08:00 | 2013-01-22 17:00 | 2013-01-15 08:00 | 2013-01-22 17:00 |  | PT_Normal |  |  |  |  | kqErGDs9TFyEDqp/dCCdqQ | 4KFvqL/XTj6N1/VzcFih0A |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 39140 | N | N | 18 | SITE PREPARATORY WORKS |  | 124939 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 40 | 0
%R | 502742 | 6359 | 124998 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BGNSP002400 | Approval for new Layout for rerouting |  | 0 | 0 | 112 | 0 | 0 | 0 | 112 | 0 | 0 | 0 |  |  |  | 2013-01-23 08:00 | 2013-02-07 17:00 |  | 2013-01-23 08:00 | 2013-02-07 17:00 | 2013-01-23 08:00 | 2013-02-07 17:00 | 2013-01-23 08:00 | 2013-02-07 17:00 | 2013-01-23 08:00 | 2013-02-07 17:00 |  | PT_Normal |  |  |  |  | 3kUDdorrSCqouhwVoBTWlw | 0umPvUk9bkKXzcQTENb+qA |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 39140 | N | N | 18 | SITE PREPARATORY WORKS |  | 124939 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 0 | 0
%R | 502743 | 6359 | 124998 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BGNSP002500 | Rerouting Works | 8180 | 0 | 0 | 200 | 0 | 325 | 325 | 200 | 0 | 0 | 0 |  |  |  | 2013-02-09 08:00 | 2013-03-10 17:00 |  | 2013-02-09 08:00 | 2013-03-10 17:00 | 2013-02-09 08:00 | 2013-03-10 17:00 | 2013-02-09 08:00 | 2013-03-10 17:00 | 2013-02-09 08:00 | 2013-03-10 17:00 |  | PT_Normal |  |  |  |  | PXs9q0lfSf26oli2y5bcaQ | qfjYHXbObUibzuRpxKOuvw |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43571 |  |  |  |  | ELECTRICIANS SK | M302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39140 | N | N | 18 | SITE PREPARATORY WORKS |  | 124939 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 162.5 | ELECTRICIANS SK
%R | 502744 | 6359 | 125002 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 24 | 24 | 160 | 0 | 594.8 | 594.8 | 160 | 0 | 0 | 0 |  |  |  | 2013-10-22 08:00 | 2013-11-13 17:00 |  | 2013-10-16 08:00 | 2013-11-10 17:00 | 2013-10-16 08:00 | 2013-11-10 17:00 | 2013-10-16 08:00 | 2013-11-10 17:00 | 2013-10-22 08:00 | 2013-11-13 17:00 |  | PT_Normal |  |  |  |  | kSI0+OO7QqKoFClreuounQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39690 | N | N | 10 | GROUND FLOOR |  | 125001 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 594.8 | LABOR- SUBCONTRACTOR
%R | 502745 | 6359 | 125002 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ELGF4005 | Cable tray & trunking installation | 8178 | 104 | 0 | 160 | 0 | 2044.8 | 2044.8 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-16 08:00 | 2014-01-08 17:00 |  | 2013-12-01 08:00 | 2013-12-24 17:00 | 2013-12-01 08:00 | 2013-12-24 17:00 | 2013-12-01 08:00 | 2013-12-24 17:00 | 2013-12-16 08:00 | 2014-01-08 17:00 |  | PT_Normal |  |  |  |  | Q3lfXptOQ5GBwapYEpVn6w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39690 | N | N | 10 | GROUND FLOOR |  | 125001 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 2044.8 | LABOR- SUBCONTRACTOR
%R | 502746 | 6359 | 125002 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ELGF4010 | Installation of wiring & Main Cabling | 8178 | 104 | 64 | 160 | 0 | 414.8 | 414.8 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-25 08:00 | 2014-01-16 17:00 |  | 2013-12-09 08:00 | 2014-01-01 17:00 | 2013-12-09 08:00 | 2014-01-01 17:00 | 2013-12-09 08:00 | 2014-01-01 17:00 | 2013-12-25 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | nTOqbSk8SlCr2KGj58TUAQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39690 | N | N | 10 | GROUND FLOOR |  | 125001 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 414.8 | LABOR- SUBCONTRACTOR
%R | 502747 | 6359 | 125002 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 112 | 0 | 160 | 0 | 170.4 | 170.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-16 17:00 |  | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-02-22 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | pSLw642cQJq0XcvNdbF2Wg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39690 | N | N | 10 | GROUND FLOOR |  | 125001 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 170.4 | LABOR- SUBCONTRACTOR
%R | 502748 | 6359 | 125002 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 112 | 0 | 160 | 0 | 395.6 | 395.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-05 08:00 | 2014-03-27 17:00 |  | 2014-02-17 08:00 | 2014-03-11 17:00 | 2014-02-17 08:00 | 2014-03-11 17:00 | 2014-02-17 08:00 | 2014-03-11 17:00 | 2014-03-05 08:00 | 2014-03-27 17:00 |  | PT_Normal |  |  |  |  | rQdM+1T6Sjai5oaBD6e8Gg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39690 | N | N | 10 | GROUND FLOOR |  | 125001 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 395.6 | LABOR- SUBCONTRACTOR
%R | 502749 | 6359 | 125002 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 104 | 0 | 160 | 0 | 1108.8 | 1108.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-22 17:00 |  | 2014-03-16 08:00 | 2014-04-07 17:00 | 2014-03-16 08:00 | 2014-04-07 17:00 | 2014-03-16 08:00 | 2014-04-07 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | 8g0iY7FSR0ymPodi3i5Aww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39690 | N | N | 10 | GROUND FLOOR |  | 125001 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1108.8 | LABOR- SUBCONTRACTOR
%R | 502750 | 6359 | 125002 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ELGF4030 | Installation of Telephone System | 8178 | 136 | 24 | 160 | 0 | 152.4 | 152.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-03-31 17:00 |  | 2014-02-17 08:00 | 2014-03-11 17:00 | 2014-02-17 08:00 | 2014-03-11 17:00 | 2014-02-17 08:00 | 2014-03-11 17:00 | 2014-03-09 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | QAJJmTyESUasqpjOqXustg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39690 | N | N | 10 | GROUND FLOOR |  | 125001 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 152.4 | LABOR- SUBCONTRACTOR
%R | 502751 | 6359 | 125003 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ELRF4070 | Installation of Isolator | 8178 | 112 | 0 | 144 | 0 | 361.2 | 361.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-08 17:00 |  | 2014-03-03 08:00 | 2014-03-23 17:00 | 2014-03-03 08:00 | 2014-03-23 17:00 | 2014-03-03 08:00 | 2014-03-23 17:00 | 2014-03-19 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | 2Vb5lnUzQQOKqtnldmV+Qg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39710 | N | N | 20 | ROOF |  | 125001 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 361.2 | LABOR- SUBCONTRACTOR
%R | 502752 | 6359 | 125003 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ELRF4075 | Installation of TV Dish Antenna | 8178 | 112 | 40 | 160 | 0 | 188.4 | 188.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-22 17:00 |  | 2014-03-15 08:00 | 2014-04-06 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | G6OSmVXMQ9eFLXdBA9i+Vg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39710 | N | N | 20 | ROOF |  | 125001 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 188.4 | LABOR- SUBCONTRACTOR
%R | 502753 | 6359 | 125005 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ACGF4600 | Installation AC Pipes | 8178 | 224 | 0 | 160 | 0 | 556.8 | 556.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-02-08 17:00 |  | 2013-12-14 08:00 | 2014-01-06 17:00 | 2013-12-14 08:00 | 2014-01-06 17:00 | 2013-12-14 08:00 | 2014-01-06 17:00 | 2014-01-16 08:00 | 2014-02-08 17:00 |  | PT_Normal |  |  |  |  | FvLRIVwhQsaQXpone+lrRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39770 | N | N | 10 | GROUND FLOOR |  | 125004 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 556.8 | LABOR- SUBCONTRACTOR
%R | 502754 | 6359 | 125005 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ACGF4605 | Fixing of Ventilation Equipments | 8178 | 120 | 0 | 200 | 0 | 85.2 | 85.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-03 08:00 | 2014-03-31 17:00 |  | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | mBcjr6IwTDyDRDycEB2yIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39770 | N | N | 10 | GROUND FLOOR |  | 125004 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 42.6 | LABOR- SUBCONTRACTOR
%R | 502755 | 6359 | 125005 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ACGF4610 | Fixing of Split AC | 8178 | 120 | 0 | 160 | 0 | 154.8 | 154.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-25 08:00 | 2014-04-16 17:00 |  | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-25 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | mO0EPCAvQdq15KRL8Hfwug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39770 | N | N | 10 | GROUND FLOOR |  | 125004 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 154.8 | LABOR- SUBCONTRACTOR
%R | 502756 | 6359 | 125006 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ACRF4635 | Installation of Condensing Unit | 8178 | 120 | 40 | 160 | 0 | 130.8 | 130.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-22 17:00 |  | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | ijhbPD6jS/2AYyXPwF6ndA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39790 | N | N | 20 | ROOF |  | 125004 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 130.8 | LABOR- SUBCONTRACTOR
%R | 502757 | 6359 | 125006 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ACRF4630 | Installation of Refrigerant Pipes | 8178 | 400 | 40 | 160 | 0 | 17.2 | 17.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-10 17:00 |  | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | ykHOoQbBRtSSgBtAGQKiSw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39790 | N | N | 20 | ROOF |  | 125004 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 17.2 | LABOR- SUBCONTRACTOR
%R | 502758 | 6359 | 125008 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 0 | 0 | 160 | 0 | 1435.2 | 1435.2 | 160 | 0 | 0 | 0 |  |  |  | 2013-10-16 08:00 | 2013-11-10 17:00 |  | 2013-10-16 08:00 | 2013-11-10 17:00 | 2013-10-16 08:00 | 2013-11-10 17:00 | 2013-10-16 08:00 | 2013-11-10 17:00 | 2013-10-16 08:00 | 2013-11-10 17:00 |  | PT_Normal |  |  |  |  | ZqqGy4cKQMysMHjfhL70KQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39730 | N | N | 10 | GROUND FLOOR |  | 125007 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1435.2 | LABOR- SUBCONTRACTOR
%R | 502759 | 6359 | 125008 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4PLGF4310 | Installation of Drainage pipes &testing | 8178 | 224 | 16 | 144 | 0 | 72 | 72 | 144 | 0 | 0 | 0 |  |  |  | 2013-11-23 08:00 | 2013-12-12 17:00 |  | 2013-10-21 08:00 | 2013-11-10 17:00 | 2013-10-21 08:00 | 2013-11-10 17:00 | 2013-10-21 08:00 | 2013-11-10 17:00 | 2013-11-23 08:00 | 2013-12-12 17:00 |  | PT_Normal |  |  |  |  | dnq9oQCzQmmXDCsjb2iv5Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39730 | N | N | 10 | GROUND FLOOR |  | 125007 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 72 | LABOR- SUBCONTRACTOR
%R | 502760 | 6359 | 125008 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4PLGF4315 | Sanitary Fittings & Accessories | 8178 | 56 | 0 | 160 | 0 | 218.4 | 218.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-25 08:00 | 2014-04-16 17:00 |  | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-03-25 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | 0mSav7SqRraIUureFyj8HQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39730 | N | N | 10 | GROUND FLOOR |  | 125007 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 218.4 | LABOR- SUBCONTRACTOR
%R | 502761 | 6359 | 125008 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4PLGF4320 | Installation of Water Heater | 8178 | 216 | 32 | 120 | 0 | 151.2 | 151.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-15 17:00 |  | 2014-03-29 08:00 | 2014-04-14 17:00 | 2014-03-29 08:00 | 2014-04-14 17:00 | 2014-03-29 08:00 | 2014-04-14 17:00 | 2014-04-29 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | H7WGgy1iQV6aazVoYLwxow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39730 | N | N | 10 | GROUND FLOOR |  | 125007 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 151.2 | LABOR- SUBCONTRACTOR
%R | 502762 | 6359 | 125008 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 0 | 0 | 160 | 0 | 182.4 | 182.4 | 160 | 0 | 0 | 0 |  |  |  | 2013-07-04 08:00 | 2013-07-27 17:00 |  | 2013-07-04 08:00 | 2013-07-27 17:00 | 2013-07-04 08:00 | 2013-07-27 17:00 | 2013-07-04 08:00 | 2013-07-27 17:00 | 2013-07-04 08:00 | 2013-07-27 17:00 |  | PT_Normal |  |  |  |  | wHj1NrrdTO2jrjz4sti0eQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39730 | N | N | 10 | GROUND FLOOR |  | 125007 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 182.4 | LABOR- SUBCONTRACTOR
%R | 502763 | 6359 | 125009 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4PLRF4350 | Installation of Rain water Pipes | 8178 | 240 | 80 | 120 | 0 | 265.2 | 265.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-03-27 17:00 |  | 2014-02-03 08:00 | 2014-02-20 17:00 | 2014-02-03 08:00 | 2014-02-20 17:00 | 2014-02-03 08:00 | 2014-02-20 17:00 | 2014-03-11 08:00 | 2014-03-27 17:00 |  | PT_Normal |  |  |  |  | IN6IPVx5QVyPE2wEHX+/TQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39750 | N | N | 20 | ROOF |  | 125007 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 265.2 | LABOR- SUBCONTRACTOR
%R | 502764 | 6359 | 125011 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4HDEX5090 | kerb works | 8173 | 240 | 0 | 160 | 0 | 236 | 236 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-08 08:00 | 2014-03-03 17:00 |  | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-02-08 08:00 | 2014-03-03 17:00 |  | PT_Normal |  |  |  |  | uB1uBqPmSzyU90yL7NGVLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39840 | N | N | 20 | HARD LANDSCAPING |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 236 | KERBSTONE MASON SK
%R | 502765 | 6359 | 125011 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4HDEX5095 | Cobble Stone Works | 8170 | 240 | 0 | 160 | 0 | 86 | 86 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-20 08:00 | 2014-03-15 17:00 |  | 2014-01-15 08:00 | 2014-02-06 17:00 | 2014-01-15 08:00 | 2014-02-06 17:00 | 2014-01-15 08:00 | 2014-02-06 17:00 | 2014-02-20 08:00 | 2014-03-15 17:00 |  | PT_Normal |  |  |  |  | 6cFyCQDjQhmgDCRQRblgOw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39840 | N | N | 20 | HARD LANDSCAPING |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 86 | TILE MASON SK
%R | 502766 | 6359 | 125011 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4HDEX5100 | Interlock works | 8174 | 240 | 72 | 160 | 0 | 300 | 300 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-30 17:00 |  | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | aAxtA9YLSGG+rb/xS4WgHw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39840 | N | N | 20 | HARD LANDSCAPING |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 300 | INTERLOCK MASON SK
%R | 502767 | 6359 | 125012 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4SLEX5105 | Laying of Grass/ green area | 8178 | 168 | 0 | 160 | 0 | 2142 | 2142 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-10 17:00 |  | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | 0N+0Msy9RfuALe+o80KrgA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39850 | N | N | 25 | SOFT LANDSCAPING |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 2142 | LABOR- SUBCONTRACTOR
%R | 502768 | 6359 | 125012 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4SLEX5110 | Laying of Palm tree | 8178 | 168 | 0 | 160 | 0 | 546 | 546 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-22 17:00 |  | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | NPSh0zrqT06Z5fCFSvdGJg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39850 | N | N | 25 | SOFT LANDSCAPING |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 546 | LABOR- SUBCONTRACTOR
%R | 502769 | 6359 | 125013 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4WEEX5030 | Excavation | 8177 | 120 | 0 | 160 | 0 | 116 | 116 | 160 | 80 | 0 | 80 |  |  |  | 2014-01-07 08:00 | 2014-01-29 17:00 |  | 2013-12-21 08:00 | 2014-01-12 17:00 | 2013-12-21 08:00 | 2014-01-12 17:00 | 2013-12-21 08:00 | 2014-01-12 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | ZPjRslU3Q+SmgS3pFABA8w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39830 | N | N | 15 | WATER TANK ENCLOSURE |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 116 | LABOR - CIVIL
%R | 502770 | 6359 | 125013 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4WEEX5035 | Construction of Raft | 8167 | 120 | 0 | 200 | 0 | 210 | 210 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-02-10 17:00 |  | 2013-12-26 08:00 | 2014-01-23 17:00 | 2013-12-26 08:00 | 2014-01-23 17:00 | 2013-12-26 08:00 | 2014-01-23 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | VAx+H6AEQ8uBI3wZtasCPw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39830 | N | N | 15 | WATER TANK ENCLOSURE |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 210 | CONCRETE MASON SK
%R | 502771 | 6359 | 125013 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4WEEX5040 | Block works & Plastering | 8168 | 160 | 0 | 200 | 0 | 692 | 692 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-28 08:00 | 2014-02-26 17:00 |  | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 |  | PT_Normal |  |  |  |  | TFDEPCoxTq24IpqXJf/KyQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39830 | N | N | 15 | WATER TANK ENCLOSURE |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 692 | BLOCK MASON SK
%R | 502772 | 6359 | 125013 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4WEEX5045 | Flooring & Painting | 8164 | 160 | 0 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-03-10 17:00 |  | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | VQZ4HtlCSaajU+J15OxVfg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39830 | N | N | 15 | WATER TANK ENCLOSURE |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 336 | SCREED MASON SK
%R | 502773 | 6359 | 125013 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4WEEX5050 | Installation of Steel Gate | 8178 | 160 | 0 | 160 | 0 | 150 | 150 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-27 08:00 | 2014-03-22 17:00 |  | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-02-27 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | p+mYqAppTJa/xcyKnY5fSQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39830 | N | N | 15 | WATER TANK ENCLOSURE |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 150 | LABOR- SUBCONTRACTOR
%R | 502774 | 6359 | 125013 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 160 | 0 | 200 | 0 | 534 | 534 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-05 08:00 | 2014-04-02 17:00 |  | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 |  | PT_Normal |  |  |  |  | ToX5Z5AEQx6QQM83Nzh/7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39830 | N | N | 15 | WATER TANK ENCLOSURE |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 267 | LABOR- SUBCONTRACTOR
%R | 502775 | 6359 | 125013 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 160 | 40 | 200 | 0 | 286.8 | 286.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-14 17:00 |  | 2014-02-22 08:00 | 2014-03-22 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 |  | PT_Normal |  |  |  |  | 7NFKMm6NRby4a1Vx4m48ZQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39830 | N | N | 15 | WATER TANK ENCLOSURE |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 143.4 | LABOR- SUBCONTRACTOR
%R | 502776 | 6359 | 125013 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4WEEX5070 | Installation ladder for water Tank | 8178 | 80 | 0 | 160 | 0 | 200 | 200 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-22 17:00 |  | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | hBhC2wkFQQWaRHVhCLf+Vw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39830 | N | N | 15 | WATER TANK ENCLOSURE |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 200 | LABOR- SUBCONTRACTOR
%R | 502777 | 6359 | 125013 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 208 | 0 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | MFFyGesOROSuVp0tI1iSVg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39830 | N | N | 15 | WATER TANK ENCLOSURE |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 400 | LABOR- SUBCONTRACTOR
%R | 502778 | 6359 | 125014 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4MSEX5020 | Construction Entrance Ramp | 8164 | 240 | 0 | 160 | 0 | 436 | 436 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-07 08:00 | 2014-01-29 17:00 |  | 2013-12-02 08:00 | 2013-12-25 17:00 | 2013-12-02 08:00 | 2013-12-25 17:00 | 2013-12-02 08:00 | 2013-12-25 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | mVF6xBsxSu6AIsqrbi7riw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39820 | N | N | 10 | MISCELLANEOUS |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 436 | SCREED MASON SK
%R | 502779 | 6359 | 125014 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4MSEX5025 | SS.Handrails and Balustrades | 8178 | 240 | 0 | 160 | 0 | 136 | 136 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-02-23 17:00 |  | 2013-12-26 08:00 | 2014-01-18 17:00 | 2013-12-26 08:00 | 2014-01-18 17:00 | 2013-12-26 08:00 | 2014-01-18 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | CJHy2721SBqGbiqzPidkqA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39820 | N | N | 10 | MISCELLANEOUS |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 136 | LABOR- SUBCONTRACTOR
%R | 502780 | 6359 | 125014 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4MSEX5015 | Construction of grease Trap | 8178 | 248 | 0 | 160 | 0 | 168 | 168 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-02-05 17:00 |  | 2013-12-08 08:00 | 2013-12-31 17:00 | 2013-12-08 08:00 | 2013-12-31 17:00 | 2013-12-08 08:00 | 2013-12-31 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | btBkECn8RmuUCGfbclNcLw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39820 | N | N | 10 | MISCELLANEOUS |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 168 | LABOR- SUBCONTRACTOR
%R | 502781 | 6359 | 125014 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4MSEX5000 | Construction of Manholes | 8172 | 208 | 0 | 200 | 0 | 132 | 132 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-04 08:00 | 2014-01-02 17:00 |  | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-12-04 08:00 | 2014-01-02 17:00 |  | PT_Normal |  |  |  |  | Pr9G8jYhS+OVkrm4ImhL2A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39820 | N | N | 10 | MISCELLANEOUS |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 132 | MANHOLES SK
%R | 502782 | 6359 | 125014 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4MSEX5005 | Construction of Soak pit, Chambers | 8172 | 248 | 0 | 200 | 0 | 66 | 66 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-25 08:00 | 2014-01-22 17:00 |  | 2013-11-18 08:00 | 2013-12-16 17:00 | 2013-11-18 08:00 | 2013-12-16 17:00 | 2013-11-18 08:00 | 2013-12-16 17:00 | 2013-12-25 08:00 | 2014-01-22 17:00 |  | PT_Normal |  |  |  |  | fyu/ATGQSV+I/oSRfMmAiA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39820 | N | N | 10 | MISCELLANEOUS |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 66 | MANHOLES SK
%R | 502783 | 6359 | 125014 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4MSEX5055 | Installation Steel Door | 8178 | 240 | 0 | 160 | 0 | 180 | 180 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-19 08:00 | 2014-02-10 17:00 |  | 2013-12-14 08:00 | 2014-01-06 17:00 | 2013-12-14 08:00 | 2014-01-06 17:00 | 2013-12-14 08:00 | 2014-01-06 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | HQcmXng3Tw2s3b8pd72uGg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39820 | N | N | 10 | MISCELLANEOUS |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 180 | LABOR- SUBCONTRACTOR
%R | 502784 | 6359 | 125014 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4MSEX5010 | Telephone cable laying | 8177 | 248 | 112 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-03-08 17:00 |  | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | CY/wQTRISFOj8PFgyrjnoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39820 | N | N | 10 | MISCELLANEOUS |  | 125010 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 500 | LABOR - CIVIL
%R | 502785 | 6359 | 125015 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 184 | 184 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | mMQb6PoFQUyyEZBK7myq1Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39860 | N | N | 30 | TESTING AND COMMISSIONING |  | 124999 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 502786 | 6359 | 125015 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 184 | 184 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | jmWlPpElT3C7VEaeeKYfsg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39860 | N | N | 30 | TESTING AND COMMISSIONING |  | 124999 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 502787 | 6359 | 125015 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 184 | 184 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | 1Ii1zJuTT2ugKf5gUGkLcg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39860 | N | N | 30 | TESTING AND COMMISSIONING |  | 124999 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 502788 | 6359 | 125018 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4STRF2060 | Construction of Parapets | 8165 | 152 | 0 | 160 | 0 | 521.5 | 521.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-07 08:00 | 2013-11-30 17:00 |  | 2013-10-14 08:00 | 2013-11-07 17:00 | 2013-10-14 08:00 | 2013-11-07 17:00 | 2013-10-14 08:00 | 2013-11-07 17:00 | 2013-11-07 08:00 | 2013-11-30 17:00 |  | PT_Normal |  |  |  |  | AWrI8+7MR+2y5vGzBlWDaw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39580 | N | N | 20 | ROOF |  | 125017 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 521.5 | STEEL FIXERS SK
%R | 502789 | 6359 | 125018 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4STRF2065 | Construction of up stands/Plinth | 8166 | 248 | 40 | 160 | 0 | 84 | 84 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-28 08:00 | 2013-12-22 17:00 |  | 2013-10-23 08:00 | 2013-11-14 17:00 | 2013-10-23 08:00 | 2013-11-14 17:00 | 2013-10-23 08:00 | 2013-11-14 17:00 | 2013-11-28 08:00 | 2013-12-22 17:00 |  | PT_Normal |  |  |  |  | 7EY2FraVSvGWC+Pv+cUoow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39580 | N | N | 20 | ROOF |  | 125017 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 84 | CARPENTERS SK
%R | 502790 | 6359 | 125019 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4STGF2000 | Column-Rebar & Formwork | 8165 | 0 | 0 | 160 | 0 | 1524.25 | 1524.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-07-31 08:00 | 2013-08-26 17:00 |  | 2013-07-31 08:00 | 2013-08-26 17:00 | 2013-07-31 08:00 | 2013-08-26 17:00 | 2013-07-31 08:00 | 2013-08-26 17:00 | 2013-07-31 08:00 | 2013-08-26 17:00 |  | PT_Normal |  |  |  |  | YSTLPAdJQQuSHEPKrMpfug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39560 | N | N | 10 | GROUND FLOOR |  | 125017 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 1524.25 | STEEL FIXERS SK
%R | 502791 | 6359 | 125019 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4STGF2005 | Column-Concrete | 8167 | 0 | 0 | 120 | 0 | 105 | 105 | 120 | 0 | 0 | 0 |  |  |  | 2013-08-14 08:00 | 2013-08-31 17:00 |  | 2013-08-14 08:00 | 2013-08-31 17:00 | 2013-08-14 08:00 | 2013-08-31 17:00 | 2013-08-14 08:00 | 2013-08-31 17:00 | 2013-08-14 08:00 | 2013-08-31 17:00 |  | PT_Normal |  |  |  |  | SC6xhsZeSayOYbWXj667qA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39560 | N | N | 10 | GROUND FLOOR |  | 125017 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 105 | CONCRETE MASON SK
%R | 502792 | 6359 | 125019 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 6076 | 6076 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-22 08:00 | 2013-09-19 17:00 |  | 2013-08-22 08:00 | 2013-09-19 17:00 | 2013-08-22 08:00 | 2013-09-19 17:00 | 2013-08-22 08:00 | 2013-09-19 17:00 | 2013-08-22 08:00 | 2013-09-19 17:00 |  | PT_Normal |  |  |  |  | 8Rg736s9TIix80mAUHIAPQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39560 | N | N | 10 | GROUND FLOOR |  | 125017 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 6076 | STEEL FIXERS SK
%R | 502793 | 6359 | 125019 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 0 | 0 | 120 | 0 | 1302 | 1302 | 120 | 0 | 0 | 0 |  |  |  | 2013-09-08 08:00 | 2013-09-24 17:00 |  | 2013-09-08 08:00 | 2013-09-24 17:00 | 2013-09-08 08:00 | 2013-09-24 17:00 | 2013-09-08 08:00 | 2013-09-24 17:00 | 2013-09-08 08:00 | 2013-09-24 17:00 |  | PT_Normal |  |  |  |  | jVtn/w+7TYif+0uDUjwKWQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39560 | N | N | 10 | GROUND FLOOR |  | 125017 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1302 | CONCRETE MASON SK
%R | 502794 | 6359 | 125021 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4STUG1000 | Footing Excavation | 8177 | 0 | 0 | 200 | 0 | 476 | 476 | 200 | 224 | 0 | 224 |  |  |  | 2013-04-09 08:00 | 2013-05-07 17:00 |  | 2013-04-09 08:00 | 2013-05-07 17:00 | 2013-04-09 08:00 | 2013-05-07 17:00 | 2013-04-09 08:00 | 2013-05-07 17:00 | 2013-04-09 08:00 | 2013-05-07 17:00 |  | PT_Normal |  |  |  |  | YOZW6QY9Q++lxJ6i/A7V3g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39540 | N | N | 10 | UPTO GRADE SLAB |  | 125020 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 476 | LABOR - CIVIL
%R | 502795 | 6359 | 125021 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4STUG1005 | Footing Antitermite | 8178 | 0 | 0 | 160 | 0 | 902 | 902 | 160 | 0 | 0 | 0 |  |  |  | 2013-04-21 08:00 | 2013-05-13 17:00 |  | 2013-04-21 08:00 | 2013-05-13 17:00 | 2013-04-21 08:00 | 2013-05-13 17:00 | 2013-04-21 08:00 | 2013-05-13 17:00 | 2013-04-21 08:00 | 2013-05-13 17:00 |  | PT_Normal |  |  |  |  | yXIpK50LS3GvQcP68pcNzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39540 | N | N | 10 | UPTO GRADE SLAB |  | 125020 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 902 | LABOR- SUBCONTRACTOR
%R | 502796 | 6359 | 125021 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4STUG1010 | Footing Blinding | 8163 | 0 | 0 | 160 | 0 | 29.75 | 29.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-04-23 08:00 | 2013-05-15 17:00 |  | 2013-04-23 08:00 | 2013-05-15 17:00 | 2013-04-23 08:00 | 2013-05-15 17:00 | 2013-04-23 08:00 | 2013-05-15 17:00 | 2013-04-23 08:00 | 2013-05-15 17:00 |  | PT_Normal |  |  |  |  | vVkhjH4LSWK5sQKs8Iw0dw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39540 | N | N | 10 | UPTO GRADE SLAB |  | 125020 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 29.75 | BLINDING MASON SK
%R | 502797 | 6359 | 125021 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4STUG1020 | Construction of foundations | 8165 | 0 | 0 | 160 | 0 | 1335.25 | 1335.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-05-08 08:00 | 2013-05-30 17:00 |  | 2013-05-08 08:00 | 2013-05-30 17:00 | 2013-05-08 08:00 | 2013-05-30 17:00 | 2013-05-08 08:00 | 2013-05-30 17:00 | 2013-05-08 08:00 | 2013-05-30 17:00 |  | PT_Normal |  |  |  |  | wkLvYKIbQayQhK/zifAU6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39540 | N | N | 10 | UPTO GRADE SLAB |  | 125020 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 1335.25 | STEEL FIXERS SK
%R | 502798 | 6359 | 125021 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4STUG1025 | Construction of neck of columns | 8165 | 0 | 0 | 160 | 0 | 1389.5 | 1389.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-05-18 08:00 | 2013-06-09 17:00 |  | 2013-05-18 08:00 | 2013-06-09 17:00 | 2013-05-18 08:00 | 2013-06-09 17:00 | 2013-05-18 08:00 | 2013-06-09 17:00 | 2013-05-18 08:00 | 2013-06-09 17:00 |  | PT_Normal |  |  |  |  | Cj107n8+SJadLGx+zmL3Kg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39540 | N | N | 10 | UPTO GRADE SLAB |  | 125020 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 1389.5 | STEEL FIXERS SK
%R | 502799 | 6359 | 125021 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4STUG1030 | Waterproofing Footing & Neck Column | 8178 | 0 | 0 | 160 | 0 | 125.5 | 125.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-05-27 08:00 | 2013-06-18 17:00 |  | 2013-05-27 08:00 | 2013-06-18 17:00 | 2013-05-27 08:00 | 2013-06-18 17:00 | 2013-05-27 08:00 | 2013-06-18 17:00 | 2013-05-27 08:00 | 2013-06-18 17:00 |  | PT_Normal |  |  |  |  | 79zxBjJjSpKD5ZcocUF4Zw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39540 | N | N | 10 | UPTO GRADE SLAB |  | 125020 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 125.5 | LABOR- SUBCONTRACTOR
%R | 502800 | 6359 | 125021 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 0 | 0 | 160 | 0 | 822 | 822 | 160 | 660 | 0 | 660 |  |  |  | 2013-06-08 08:00 | 2013-06-30 17:00 |  | 2013-06-08 08:00 | 2013-06-30 17:00 | 2013-06-08 08:00 | 2013-06-30 17:00 | 2013-06-08 08:00 | 2013-06-30 17:00 | 2013-06-08 08:00 | 2013-06-30 17:00 |  | PT_Normal |  |  |  |  | Ys2nHwrrSiaJOg9canO+bg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39540 | N | N | 10 | UPTO GRADE SLAB |  | 125020 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 822 | LABOR - CIVIL
%R | 502801 | 6359 | 125021 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4STUG1040 | Construction of Grade Beams | 8163 | 0 | 0 | 200 | 0 | 2325.75 | 2325.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-19 08:00 | 2013-07-17 17:00 |  | 2013-06-19 08:00 | 2013-07-17 17:00 | 2013-06-19 08:00 | 2013-07-17 17:00 | 2013-06-19 08:00 | 2013-07-17 17:00 | 2013-06-19 08:00 | 2013-07-17 17:00 |  | PT_Normal |  |  |  |  | MSKaw9EbQNWRx8Xngibm9w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39540 | N | N | 10 | UPTO GRADE SLAB |  | 125020 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 2325.75 | BLINDING MASON SK
%R | 502802 | 6359 | 125021 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4STUG1045 | Construction of slab on grade | 8163 | 0 | 0 | 200 | 0 | 1541.75 | 1541.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-14 08:00 | 2013-08-14 17:00 |  | 2013-07-14 08:00 | 2013-08-14 17:00 | 2013-07-14 08:00 | 2013-08-14 17:00 | 2013-07-14 08:00 | 2013-08-14 17:00 | 2013-07-14 08:00 | 2013-08-14 17:00 |  | PT_Normal |  |  |  |  | kY+NK+fRRdaSXq7+TVo5Pg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39540 | N | N | 10 | UPTO GRADE SLAB |  | 125020 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 770.875 | BLINDING MASON SK
%R | 502803 | 6359 | 125021 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4STUG1015 | Footing Waterproofing & Screed | 8164 | 0 | 0 | 160 | 0 | 483 | 483 | 160 | 0 | 0 | 0 |  |  |  | 2013-04-29 08:00 | 2013-05-21 17:00 |  | 2013-04-29 08:00 | 2013-05-21 17:00 | 2013-04-29 08:00 | 2013-05-21 17:00 | 2013-04-29 08:00 | 2013-05-21 17:00 | 2013-04-29 08:00 | 2013-05-21 17:00 |  | PT_Normal |  |  |  |  | dqVmQLTtReWHQHLH7OEEYw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39540 | N | N | 10 | UPTO GRADE SLAB |  | 125020 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 483 | SCREED MASON SK
%R | 502804 | 6359 | 125024 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4AREL3665 | External Plastering | 8169 | 240 | 0 | 200 | 0 | 4012.5 | 4012.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-19 08:00 | 2014-03-19 17:00 |  | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 |  | PT_Normal |  |  |  |  | dBmSOnq7Trat858PtpKq8A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39660 | N | N | 15 | ELEVATION |  | 125023 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 4012.5 | PLASTER MASON SK
%R | 502805 | 6359 | 125024 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4AREL3680 | External Painting | 8178 | 360 | 40 | 160 | 0 | 1408 | 1408 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-22 17:00 |  | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | 0TUr1QCHRUOcTdrGDQ/3Iw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39660 | N | N | 15 | ELEVATION |  | 125023 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1408 | LABOR- SUBCONTRACTOR
%R | 502806 | 6359 | 125025 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARRF3625 | Laying of Pitched Roof | 8174 | 240 | 0 | 200 | 0 | 256 | 256 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-05 08:00 | 2014-02-02 17:00 |  | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | zcWHn6GxSVORFym677lnvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39650 | N | N | 10 | ROOF |  | 125023 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 256 | INTERLOCK MASON SK
%R | 502807 | 6359 | 125025 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARRF3635 | Laying of Waterproofing Membrane | 8178 | 240 | 0 | 144 | 0 | 722.25 | 722.25 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-25 08:00 | 2014-02-15 17:00 |  | 2013-12-21 08:00 | 2014-01-09 17:00 | 2013-12-21 08:00 | 2014-01-09 17:00 | 2013-12-21 08:00 | 2014-01-09 17:00 | 2014-01-25 08:00 | 2014-02-15 17:00 |  | PT_Normal |  |  |  |  | 7GINOmxjSQ67liLQM+n8Lg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39650 | N | N | 10 | ROOF |  | 125023 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 722.25 | LABOR- SUBCONTRACTOR
%R | 502808 | 6359 | 125025 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARRF3640 | Installation of Insulation & Protection | 8178 | 240 | 0 | 144 | 0 | 343.75 | 343.75 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-29 08:00 | 2014-02-19 17:00 |  | 2013-12-25 08:00 | 2014-01-14 17:00 | 2013-12-25 08:00 | 2014-01-14 17:00 | 2013-12-25 08:00 | 2014-01-14 17:00 | 2014-01-29 08:00 | 2014-02-19 17:00 |  | PT_Normal |  |  |  |  | DL5uJUNERvmJ/zJ9UbXPFQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39650 | N | N | 10 | ROOF |  | 125023 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 343.75 | LABOR- SUBCONTRACTOR
%R | 502809 | 6359 | 125025 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 240 | 0 | 144 | 0 | 344.5 | 344.5 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-02-27 17:00 |  | 2014-01-02 08:00 | 2014-01-22 17:00 | 2014-01-02 08:00 | 2014-01-22 17:00 | 2014-01-02 08:00 | 2014-01-22 17:00 | 2014-02-06 08:00 | 2014-02-27 17:00 |  | PT_Normal |  |  |  |  | FdYPpDv7T22ZuGIyVFRoZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39650 | N | N | 10 | ROOF |  | 125023 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 344.5 | TILE MASON SK
%R | 502810 | 6359 | 125025 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARRF3660 | Installation of Access Ladder | 8178 | 472 | 40 | 160 | 0 | 132 | 132 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-10 17:00 |  | 2014-01-08 08:00 | 2014-01-30 17:00 | 2014-01-08 08:00 | 2014-01-30 17:00 | 2014-01-08 08:00 | 2014-01-30 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | io7lzRc6QMKVwwoc/lxvpw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39650 | N | N | 10 | ROOF |  | 125023 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 132 | LABOR- SUBCONTRACTOR
%R | 502811 | 6359 | 125025 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARRF3630 | Leveling Screed for Waterproofing | 8164 | 240 | 0 | 144 | 0 | 195.5 | 195.5 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-19 08:00 | 2014-02-08 17:00 |  | 2013-12-14 08:00 | 2014-01-04 17:00 | 2013-12-14 08:00 | 2014-01-04 17:00 | 2013-12-14 08:00 | 2014-01-04 17:00 | 2014-01-19 08:00 | 2014-02-08 17:00 |  | PT_Normal |  |  |  |  | vMYN8T7UQ92tKaPrp2qJOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39650 | N | N | 10 | ROOF |  | 125023 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 195.5 | SCREED MASON SK
%R | 502812 | 6359 | 125027 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARGF3000 | Block work | 8168 | 0 | 0 | 200 | 0 | 5700 | 5700 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-02 08:00 | 2013-11-02 17:00 |  | 2013-10-02 08:00 | 2013-11-02 17:00 | 2013-10-02 08:00 | 2013-11-02 17:00 | 2013-10-02 08:00 | 2013-11-02 17:00 | 2013-10-02 08:00 | 2013-11-02 17:00 |  | PT_Normal |  |  |  |  | /yRNis4GR/iLUJiFKiKK3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39610 | N | N | 10 | GROUND FLOOR |  | 125026 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 2850 | BLOCK MASON SK
%R | 502813 | 6359 | 125027 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARGF3005 | Plastering work | 8169 | 0 | 0 | 200 | 0 | 2850 | 2850 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-28 08:00 | 2013-11-25 17:00 |  | 2013-10-28 08:00 | 2013-11-25 17:00 | 2013-10-28 08:00 | 2013-11-25 17:00 | 2013-10-28 08:00 | 2013-11-25 17:00 | 2013-10-28 08:00 | 2013-11-25 17:00 |  | PT_Normal |  |  |  |  | /l4mVQBIS1uUk2jyUgS+qA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39610 | N | N | 10 | GROUND FLOOR |  | 125026 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 2850 | PLASTER MASON SK
%R | 502814 | 6359 | 125027 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARGF3010 | Flooring screed | 8164 | 200 | 40 | 160 | 0 | 634.25 | 634.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-08 08:00 | 2013-12-31 17:00 |  | 2013-11-09 08:00 | 2013-12-01 17:00 | 2013-11-09 08:00 | 2013-12-01 17:00 | 2013-11-09 08:00 | 2013-12-01 17:00 | 2013-12-08 08:00 | 2013-12-31 17:00 |  | PT_Normal |  |  |  |  | PXjUynkFRmua6K+BPsegbA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39610 | N | N | 10 | GROUND FLOOR |  | 125026 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 634.25 | SCREED MASON SK
%R | 502815 | 6359 | 125027 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 40 | 0 | 160 | 0 | 87 | 87 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-19 08:00 | 2013-12-11 17:00 |  | 2013-11-13 08:00 | 2013-12-05 17:00 | 2013-11-13 08:00 | 2013-12-05 17:00 | 2013-11-13 08:00 | 2013-12-05 17:00 | 2013-11-19 08:00 | 2013-12-11 17:00 |  | PT_Normal |  |  |  |  | 6gPiC6bbReG4TUC8q7cxhQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39610 | N | N | 10 | GROUND FLOOR |  | 125026 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 87 | LABOR- SUBCONTRACTOR
%R | 502816 | 6359 | 125027 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARGF3030 | Paint First coat | 8178 | 48 | 0 | 160 | 0 | 1815 | 1815 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-25 08:00 | 2014-01-16 17:00 |  | 2013-12-17 08:00 | 2014-01-09 17:00 | 2013-12-17 08:00 | 2014-01-09 17:00 | 2013-12-17 08:00 | 2014-01-09 17:00 | 2013-12-25 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | cUR9ewZqR/WQhX8v+8KDqg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39610 | N | N | 10 | GROUND FLOOR |  | 125026 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1815 | LABOR- SUBCONTRACTOR
%R | 502817 | 6359 | 125027 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARGF3020 | Ceramic Wall Tiling | 8170 | 40 | 0 | 120 | 0 | 1012.5 | 1012.5 | 120 | 0 | 0 | 0 |  |  |  | 2013-12-08 08:00 | 2013-12-25 17:00 |  | 2013-12-02 08:00 | 2013-12-19 17:00 | 2013-12-02 08:00 | 2013-12-19 17:00 | 2013-12-02 08:00 | 2013-12-19 17:00 | 2013-12-08 08:00 | 2013-12-25 17:00 |  | PT_Normal |  |  |  |  | iZPeLx4RQba09Df5fTe52w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39610 | N | N | 10 | GROUND FLOOR |  | 125026 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1012.5 | TILE MASON SK
%R | 502818 | 6359 | 125027 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARGF3025 | Porcelain Tile flooring | 8170 | 40 | 0 | 160 | 0 | 1030.25 | 1030.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-25 08:00 | 2014-01-16 17:00 |  | 2013-12-19 08:00 | 2014-01-11 17:00 | 2013-12-19 08:00 | 2014-01-11 17:00 | 2013-12-19 08:00 | 2014-01-11 17:00 | 2013-12-25 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | QLAhgmVHRJ6p7C0CAXThLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39610 | N | N | 10 | GROUND FLOOR |  | 125026 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1030.25 | TILE MASON SK
%R | 502819 | 6359 | 125027 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARGF3040 | Cobble Tile flooring | 8170 | 160 | 24 | 120 | 0 | 300 | 300 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-16 08:00 | 2014-04-01 17:00 |  | 2014-02-20 08:00 | 2014-03-09 17:00 | 2014-02-20 08:00 | 2014-03-09 17:00 | 2014-02-20 08:00 | 2014-03-09 17:00 | 2014-03-16 08:00 | 2014-04-01 17:00 |  | PT_Normal |  |  |  |  | wRV6vWboSxWB+wBQvkw8yA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39610 | N | N | 10 | GROUND FLOOR |  | 125026 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 300 | TILE MASON SK
%R | 502820 | 6359 | 125027 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 104 | 0 | 144 | 0 | 1575 | 1575 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-17 08:00 | 2014-03-09 17:00 |  | 2014-02-01 08:00 | 2014-02-22 17:00 | 2014-02-01 08:00 | 2014-02-22 17:00 | 2014-02-01 08:00 | 2014-02-22 17:00 | 2014-02-17 08:00 | 2014-03-09 17:00 |  | PT_Normal |  |  |  |  | h4QDkkLYRICkLmRrezQ6EQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39610 | N | N | 10 | GROUND FLOOR |  | 125026 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1575 | TILE MASON SK
%R | 502821 | 6359 | 125027 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARGF3045 | Fixing of Suspension systems | 8178 | 40 | 0 | 120 | 0 | 653.5 | 653.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-02-02 17:00 |  | 2014-01-11 08:00 | 2014-01-27 17:00 | 2014-01-11 08:00 | 2014-01-27 17:00 | 2014-01-11 08:00 | 2014-01-27 17:00 | 2014-01-16 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | ixU8L72BRVyOLtM0fbyjDQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39610 | N | N | 10 | GROUND FLOOR |  | 125026 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 653.5 | LABOR- SUBCONTRACTOR
%R | 502822 | 6359 | 125027 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARGF3060 | Gypsum board false ceiling | 8178 | 40 | 0 | 160 | 0 | 653.5 | 653.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-02 08:00 | 2014-02-25 17:00 |  | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-02-02 08:00 | 2014-02-25 17:00 |  | PT_Normal |  |  |  |  | /basi6FHTLCqS7vkVYJXIw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39610 | N | N | 10 | GROUND FLOOR |  | 125026 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 653.5 | LABOR- SUBCONTRACTOR
%R | 502823 | 6359 | 125027 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARGF3065 | Wooden door | 8178 | 136 | 0 | 120 | 0 | 198 | 198 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-05 08:00 | 2014-03-22 17:00 |  | 2014-02-13 08:00 | 2014-03-02 17:00 | 2014-02-13 08:00 | 2014-03-02 17:00 | 2014-02-13 08:00 | 2014-03-02 17:00 | 2014-03-05 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | 6HXbgSmlRGCgqDvaDkRF1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39610 | N | N | 10 | GROUND FLOOR |  | 125026 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 198 | LABOR- SUBCONTRACTOR
%R | 502824 | 6359 | 125027 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARGF3075 | Carpentry & Joinery Works | 8178 | 136 | 24 | 144 | 0 | 528 | 528 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-03-31 17:00 |  | 2014-02-19 08:00 | 2014-03-11 17:00 | 2014-02-19 08:00 | 2014-03-11 17:00 | 2014-02-19 08:00 | 2014-03-11 17:00 | 2014-03-11 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | oejQzvtTRtuTtuzpIJ9x2Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39610 | N | N | 10 | GROUND FLOOR |  | 125026 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 528 | LABOR- SUBCONTRACTOR
%R | 502825 | 6359 | 125027 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARGF3090 | Installation of Granite Counter Top | 8171 | 64 | 0 | 120 | 0 | 99 | 99 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-25 08:00 | 2014-04-10 17:00 |  | 2014-03-16 08:00 | 2014-04-01 17:00 | 2014-03-16 08:00 | 2014-04-01 17:00 | 2014-03-16 08:00 | 2014-04-01 17:00 | 2014-03-25 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | Dd6BZxPbTvOdBmtmJ34mfw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39610 | N | N | 10 | GROUND FLOOR |  | 125026 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 99 | GRANITE MASON SK
%R | 502826 | 6359 | 125027 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARGF3095 | Final Painting | 8178 | 184 | 0 | 200 | 0 | 1815 | 1815 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | jP9+TZYdRkSxM0pdbGKcsA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39610 | N | N | 10 | GROUND FLOOR |  | 125026 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1815 | LABOR- SUBCONTRACTOR
%R | 502827 | 6359 | 125027 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2BZ4ARGF3080 | Aluminum windows | 8178 | 248 | 64 | 144 | 0 | 132 | 132 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-08 08:00 | 2014-04-28 17:00 |  | 2014-03-03 08:00 | 2014-03-23 17:00 | 2014-03-03 08:00 | 2014-03-23 17:00 | 2014-03-03 08:00 | 2014-03-23 17:00 | 2014-04-08 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | Fz7f5GJTT4WWQZqZrhcntQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 39610 | N | N | 10 | GROUND FLOOR |  | 125026 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 132 | LABOR- SUBCONTRACTOR
%R | 502828 | 6359 | 125031 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1SLGL7200 | Excavation | 8177 | 496 | 0 | 200 | 0 | 497 | 497 | 200 | 251 | 0 | 251 |  |  |  | 2014-05-31 08:00 | 2014-06-28 17:00 |  | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | vyXHMYcmSH+kzYqEYBg/KA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33940 | N | N | 70 | SOFT LANDSCAPING |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 497 | LABOR - CIVIL
%R | 502829 | 6359 | 125031 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1SLGL7205 | Sweet Soil Laying | 8178 | 496 | 40 | 200 | 0 | 2380 | 2380 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-07-09 17:00 |  | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-06-11 08:00 | 2014-07-09 17:00 |  | PT_Normal |  |  |  |  | bjoN6L9VQj26WCSYzfMhUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33940 | N | N | 70 | SOFT LANDSCAPING |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 2380 | LABOR- SUBCONTRACTOR
%R | 502830 | 6359 | 125031 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1SLGL7210 | Plantation works | 8178 | 776 | 160 | 200 | 0 | 588 | 588 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-09-09 17:00 |  | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-08-12 08:00 | 2014-09-09 17:00 |  | PT_Normal |  |  |  |  | uvYi5VmKRVmlWLlm4n2y6g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33940 | N | N | 70 | SOFT LANDSCAPING |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 588 | LABOR- SUBCONTRACTOR
%R | 502831 | 6359 | 125032 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1IRGL5265 | Excavation for irrigation line | 8177 | 424 | 0 | 200 | 0 | 812 | 812 | 200 | 500 | 0 | 500 |  |  |  | 2014-03-31 08:00 | 2014-04-28 17:00 |  | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | XVyYajYtSFeg/CUe+NYbww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33880 | N | N | 40 | IRRIGATION LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 812 | LABOR - CIVIL
%R | 502832 | 6359 | 125032 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1IRGL5270 | Laying of irrigationline | 8178 | 424 | 0 | 200 | 0 | 386.4 | 386.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-05-04 17:00 |  | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-04-06 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | CL1VYx4tTOCgx7agVzqFlQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33880 | N | N | 40 | IRRIGATION LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 193.2 | LABOR- SUBCONTRACTOR
%R | 502833 | 6359 | 125032 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1IRGL5275 | Testing of irrigation line | 8178 | 424 | 0 | 200 | 0 | 319.2 | 319.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-10 17:00 |  | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | oh6y6uRtThWxN2iO/EMt0A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33880 | N | N | 40 | IRRIGATION LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 159.6 | LABOR- SUBCONTRACTOR
%R | 502834 | 6359 | 125032 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1IRGL5280 | Backfilling irrigation line | 8177 | 424 | 0 | 200 | 0 | 676 | 676 | 200 | 550 | 0 | 550 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | Oexnp2BLS1ybDIpTnYaeLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33880 | N | N | 40 | IRRIGATION LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 338 | LABOR - CIVIL
%R | 502835 | 6359 | 125032 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1IRGL5285 | Construction of Thrust Blocks,Pull boxes | 8178 | 584 | 0 | 200 | 0 | 116.4 | 116.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-22 08:00 | 2014-06-19 17:00 |  | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 |  | PT_Normal |  |  |  |  | AeeACneTRr+egKuwW7+JsQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33880 | N | N | 40 | IRRIGATION LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 58.2 | LABOR- SUBCONTRACTOR
%R | 502836 | 6359 | 125032 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1IRGL5290 | Irrigation Fittings (Nozzle,Values) | 8178 | 584 | 88 | 200 | 0 | 285.6 | 285.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-31 08:00 | 2014-06-28 17:00 |  | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | ZmuacpxWTi6TvllsSH04JQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33880 | N | N | 40 | IRRIGATION LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 285.6 | LABOR- SUBCONTRACTOR
%R | 502837 | 6359 | 125033 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1ELGL5215 | Excavation Cable Trenches & Duct Banks | 8177 | 224 | 0 | 200 | 0 | 1374 | 1374 | 200 | 600 | 0 | 600 |  |  |  | 2014-01-16 08:00 | 2014-02-15 17:00 |  | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 |  | PT_Normal |  |  |  |  | wMw5LhQBQZapPcZcFEe4BA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33860 | N | N | 30 | ELECTRICAL LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1374 | LABOR - CIVIL
%R | 502838 | 6359 | 125033 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1ELGL5220 | Laying of electrical cables | 8178 | 248 | 0 | 200 | 0 | 1834.8 | 1834.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-26 08:00 | 2014-02-24 17:00 |  | 2013-12-21 08:00 | 2014-01-18 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 |  | PT_Normal |  |  |  |  | ehGgm8VET/yFLkkIZInofg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33860 | N | N | 30 | ELECTRICAL LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1834.8 | LABOR- SUBCONTRACTOR
%R | 502839 | 6359 | 125033 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1ELGL5225 | Backfilling Electrical trench | 8177 | 248 | 0 | 200 | 0 | 862 | 862 | 200 | 550 | 0 | 550 |  |  |  | 2014-02-03 08:00 | 2014-03-04 17:00 |  | 2013-12-29 08:00 | 2014-01-26 17:00 | 2013-12-29 08:00 | 2014-01-26 17:00 | 2013-12-29 08:00 | 2014-01-26 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 |  | PT_Normal |  |  |  |  | o2ZfdFmJSzC8wjFuky2ZzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33860 | N | N | 30 | ELECTRICAL LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 862 | LABOR - CIVIL
%R | 502840 | 6359 | 125033 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1ELGL5230 | Construction of Submain Board & Feeder Pillar | 8165 | 760 | 0 | 200 | 0 | 224 | 224 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-06 08:00 | 2014-06-03 17:00 |  | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-05-06 08:00 | 2014-06-03 17:00 |  | PT_Normal |  |  |  |  | OKZw3uGQQ+WGftvBmQJD8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33860 | N | N | 30 | ELECTRICAL LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 224 | STEEL FIXERS SK
%R | 502841 | 6359 | 125034 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1PSGL7000 | Excavation | 8177 | 744 | 40 | 120 | 0 | 148 | 148 | 120 | 76 | 0 | 76 |  |  |  | 2014-07-12 08:00 | 2014-07-28 17:00 |  | 2014-03-25 08:00 | 2014-04-10 17:00 | 2014-03-25 08:00 | 2014-04-10 17:00 | 2014-03-25 08:00 | 2014-04-10 17:00 | 2014-07-12 08:00 | 2014-07-28 17:00 |  | PT_Normal |  |  |  |  | e1J1OGXwTge8zxY4WQdtTA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33920 | N | N | 60 | PARKING SHED |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 148 | LABOR - CIVIL
%R | 502842 | 6359 | 125034 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1PSGL7005 | Foundation casting | 8165 | 704 | 0 | 120 | 0 | 252 | 252 | 120 | 0 | 0 | 0 |  |  |  | 2014-07-17 08:00 | 2014-08-06 17:00 |  | 2014-04-06 08:00 | 2014-04-22 17:00 | 2014-04-06 08:00 | 2014-04-22 17:00 | 2014-04-06 08:00 | 2014-04-22 17:00 | 2014-07-17 08:00 | 2014-08-06 17:00 |  | PT_Normal |  |  |  |  | CkRqowtFTCKaBJRSL0KKuQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33920 | N | N | 60 | PARKING SHED |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 252 | STEEL FIXERS SK
%R | 502843 | 6359 | 125034 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1PSGL7010 | Column, Frame& Fabrics Erection | 8178 | 704 | 0 | 200 | 0 | 286 | 286 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-29 08:00 | 2014-08-30 17:00 |  | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-07-29 08:00 | 2014-08-30 17:00 |  | PT_Normal |  |  |  |  | slT3MjSZTiG8XrDcVj5Twg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33920 | N | N | 60 | PARKING SHED |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 286 | LABOR- SUBCONTRACTOR
%R | 502844 | 6359 | 125034 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1PSGL7015 | Electrical Works-Parking Shed | 8178 | 704 | 200 | 200 | 0 | 51.6 | 51.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-07 08:00 | 2014-09-04 17:00 |  | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-08-07 08:00 | 2014-09-04 17:00 |  | PT_Normal |  |  |  |  | IumUONs3SISLI7O30DSJlg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33920 | N | N | 60 | PARKING SHED |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 51.6 | LABOR- SUBCONTRACTOR
%R | 502845 | 6359 | 125035 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1SAGL5135 | Construction of manholes Drainage | 8177 | 736 | 200 | 200 | 0 | 6 | 6 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-20 17:00 |  | 2013-10-03 08:00 | 2013-11-03 17:00 | 2013-10-03 08:00 | 2013-11-03 17:00 | 2013-10-03 08:00 | 2013-11-03 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | HlqKI/EuQxK1lzeMsqFB5Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33830 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 3 | LABOR - CIVIL
%R | 502846 | 6359 | 125035 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1SAGL5140 | Construction of soakaways | 8172 | 160 | 0 | 200 | 0 | 154 | 154 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-29 08:00 | 2013-11-26 17:00 |  | 2013-10-03 08:00 | 2013-11-03 17:00 | 2013-10-03 08:00 | 2013-11-03 17:00 | 2013-10-03 08:00 | 2013-11-03 17:00 | 2013-10-29 08:00 | 2013-11-26 17:00 |  | PT_Normal |  |  |  |  | GKyGNp6ZT7+x2ZHuI3ZLKA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33830 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 77 | MANHOLES SK
%R | 502847 | 6359 | 125035 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1SAGL5145 | Construction of Road gullies | 8172 | 160 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-27 08:00 | 2013-12-26 17:00 |  | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 |  | PT_Normal |  |  |  |  | EAJq6FymR5Skf6qXR3QVVw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33830 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 176 | MANHOLES SK
%R | 502848 | 6359 | 125035 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1SAGL5150 | Connection with existing sewer manhole | 8177 | 536 | 312 | 160 | 0 | 6 | 6 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-16 17:00 |  | 2013-12-03 08:00 | 2013-12-26 17:00 | 2013-12-03 08:00 | 2013-12-26 17:00 | 2013-12-03 08:00 | 2013-12-26 17:00 | 2014-02-22 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | RcyAotOgTpS/dmsv08sTVQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33830 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 6 | LABOR - CIVIL
%R | 502849 | 6359 | 125036 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1HDGL7020 | Precast Concrete Kerbs works | 8173 | 496 | 0 | 160 | 0 | 1178 | 1178 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-26 08:00 | 2014-05-18 17:00 |  | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-04-26 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | qE82p+61TouUVz6KLXyHdA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33930 | N | N | 65 | HARD LANDSCAPING |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1178 | KERBSTONE MASON SK
%R | 502850 | 6359 | 125036 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1HDGL7025 | Interlocking for Walkways | 8174 | 496 | 0 | 200 | 0 | 806 | 806 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-07 08:00 | 2014-06-04 17:00 |  | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 |  | PT_Normal |  |  |  |  | euiaItjsQjqUA+WfraYY7Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33930 | N | N | 65 | HARD LANDSCAPING |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 403 | INTERLOCK MASON SK
%R | 502851 | 6359 | 125036 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1HDGL7030 | Construction of Retaining wall | 8165 | 496 | 0 | 200 | 0 | 756 | 756 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | 8YC4B/I5Rr2cAwxq7XQuVQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33930 | N | N | 65 | HARD LANDSCAPING |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 756 | STEEL FIXERS SK
%R | 502852 | 6359 | 125036 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1HDGL7035 | Construction of Wash Stone Boulders | 8170 | 496 | 0 | 200 | 0 | 88 | 88 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | JT/TsNMAQfiKfeoFEAa3Ng |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33930 | N | N | 65 | HARD LANDSCAPING |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 88 | TILE MASON SK
%R | 502853 | 6359 | 125036 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1HDGL7040 | Construction of Speed Humps | 8167 | 776 | 0 | 160 | 0 | 14 | 14 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-09 17:00 |  | 2014-04-23 08:00 | 2014-05-15 17:00 | 2014-04-23 08:00 | 2014-05-15 17:00 | 2014-04-23 08:00 | 2014-05-15 17:00 | 2014-08-18 08:00 | 2014-09-09 17:00 |  | PT_Normal |  |  |  |  | 7NTj5nkHRZGSG+wUDyQcHQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33930 | N | N | 65 | HARD LANDSCAPING |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 14 | CONCRETE MASON SK
%R | 502854 | 6359 | 125037 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1WSGL5155 | Excavation for water line | 8177 | 160 | 0 | 200 | 0 | 401 | 401 | 200 | 251 | 0 | 251 |  |  |  | 2013-11-10 08:00 | 2013-12-08 17:00 |  | 2013-10-15 08:00 | 2013-11-14 17:00 | 2013-10-15 08:00 | 2013-11-14 17:00 | 2013-10-15 08:00 | 2013-11-14 17:00 | 2013-11-10 08:00 | 2013-12-08 17:00 |  | PT_Normal |  |  |  |  | hFbENg8YSDWd6JYi21LSWQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33840 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 401 | LABOR - CIVIL
%R | 502855 | 6359 | 125037 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1WSGL5160 | Laying of water line | 8178 | 160 | 0 | 200 | 0 | 285.6 | 285.6 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-16 08:00 | 2013-12-14 17:00 |  | 2013-10-23 08:00 | 2013-11-20 17:00 | 2013-10-23 08:00 | 2013-11-20 17:00 | 2013-10-23 08:00 | 2013-11-20 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 |  | PT_Normal |  |  |  |  | Kafl73/GR3GvJPT9uVCpiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33840 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 285.6 | LABOR- SUBCONTRACTOR
%R | 502856 | 6359 | 125037 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1WSGL5165 | Testing of potable water line | 8178 | 160 | 0 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-21 08:00 | 2013-12-21 17:00 |  | 2013-10-29 08:00 | 2013-11-26 17:00 | 2013-10-29 08:00 | 2013-11-26 17:00 | 2013-10-29 08:00 | 2013-11-26 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 |  | PT_Normal |  |  |  |  | Ky66HL0VRxm78y89vHy3/w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33840 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 84 | LABOR- SUBCONTRACTOR
%R | 502857 | 6359 | 125037 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1WSGL5170 | Backfilling potable water line | 8177 | 160 | 0 | 200 | 0 | 335 | 335 | 200 | 275 | 0 | 275 |  |  |  | 2013-11-27 08:00 | 2013-12-26 17:00 |  | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 |  | PT_Normal |  |  |  |  | sWMwgvKgTJyFP7UjRJLdpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33840 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 335 | LABOR - CIVIL
%R | 502858 | 6359 | 125037 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1WSGL5175 | Construction of valve chambers & Thrust Blocks | 8172 | 496 | 0 | 200 | 0 | 132 | 132 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-20 17:00 |  | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-11-10 08:00 | 2013-12-08 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | y6EYNMLsSZmOTMkofB+Bjw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33840 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 132 | MANHOLES SK
%R | 502859 | 6359 | 125037 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1WSGL5180 | Installation of meter ,Accessories & Connection | 8178 | 496 | 96 | 160 | 0 | 50.4 | 50.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-16 17:00 |  | 2013-12-09 08:00 | 2014-01-01 17:00 | 2013-12-09 08:00 | 2014-01-01 17:00 | 2013-12-09 08:00 | 2014-01-01 17:00 | 2014-02-22 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | KrlOBfjDS9itiJjWf51nZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33840 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 502860 | 6359 | 125038 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1RWGL6000 | Excavation & Earth Filling | 8177 | 224 | 0 | 80 | 0 | 1232 | 1232 | 80 | 500 | 0 | 500 |  |  |  | 2014-03-17 08:00 | 2014-03-27 17:00 |  | 2014-02-12 08:00 | 2014-02-23 17:00 | 2014-02-12 08:00 | 2014-02-23 17:00 | 2014-02-12 08:00 | 2014-02-23 17:00 | 2014-03-17 08:00 | 2014-03-27 17:00 |  | PT_Normal |  |  |  |  | 4TiSfNtXS/qmJ4e2ZKyeDg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33910 | N | N | 55 | ROAD WORKS |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1232 | LABOR - CIVIL
%R | 502861 | 6359 | 125038 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1RWGL6005 | Laying of Sub Grade | 8178 | 224 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-29 08:00 | 2014-04-26 17:00 |  | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-03-29 08:00 | 2014-04-26 17:00 |  | PT_Normal |  |  |  |  | z2TEs9KsSCCOXPMP0+6DLw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33910 | N | N | 55 | ROAD WORKS |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 12 | LABOR- SUBCONTRACTOR
%R | 502862 | 6359 | 125038 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1RWGL6010 | Laying of Precast Kerbs | 8178 | 224 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-09 08:00 | 2014-05-07 17:00 |  | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 |  | PT_Normal |  |  |  |  | Au1lLKgXQyKU9Lnwkn6iqA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33910 | N | N | 55 | ROAD WORKS |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 24 | LABOR- SUBCONTRACTOR
%R | 502863 | 6359 | 125038 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1RWGL6015 | Laying of Granular Sub Base Coarse | 8173 | 224 | 0 | 160 | 0 | 1814 | 1814 | 160 | 600 | 0 | 600 |  |  |  | 2014-04-21 08:00 | 2014-05-13 17:00 |  | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-04-21 08:00 | 2014-05-13 17:00 |  | PT_Normal |  |  |  |  | CyPi85akSLeRcqEaQ/QlUg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33910 | N | N | 55 | ROAD WORKS |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1814 | KERBSTONE MASON SK
%R | 502864 | 6359 | 125038 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1RWGL6020 | Laying of Road Base Asphalt Concrete | 8178 | 704 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-07-23 08:00 | 2014-07-28 17:00 |  | 2014-04-12 08:00 | 2014-04-16 17:00 | 2014-04-12 08:00 | 2014-04-16 17:00 | 2014-04-12 08:00 | 2014-04-16 17:00 | 2014-07-23 08:00 | 2014-07-28 17:00 |  | PT_Normal |  |  |  |  | JsAVvzWvTXeQNnx/UucDbQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33910 | N | N | 55 | ROAD WORKS |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 174 | LABOR- SUBCONTRACTOR
%R | 502865 | 6359 | 125038 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1RWGL6025 | Laying of Asphalt Wearing Coarse | 8178 | 776 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-08-12 08:00 | 2014-08-17 17:00 |  | 2014-04-17 08:00 | 2014-04-22 17:00 | 2014-04-17 08:00 | 2014-04-22 17:00 | 2014-04-17 08:00 | 2014-04-22 17:00 | 2014-08-12 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | gbaZ5s25QnOojJI88rdq9w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33910 | N | N | 55 | ROAD WORKS |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 174 | LABOR- SUBCONTRACTOR
%R | 502866 | 6359 | 125038 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1RWGL6030 | Traffic Signage & Road Marking | 8178 | 824 | 120 | 40 | 0 | 974 | 974 | 40 | 0 | 0 | 0 |  |  |  | 2014-08-25 08:00 | 2014-08-30 17:00 |  | 2014-04-23 08:00 | 2014-04-28 17:00 | 2014-04-23 08:00 | 2014-04-28 17:00 | 2014-04-23 08:00 | 2014-04-28 17:00 | 2014-08-25 08:00 | 2014-08-30 17:00 |  | PT_Normal |  |  |  |  | spPCbFurTeqb5Pfq3HX5Fg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33910 | N | N | 55 | ROAD WORKS |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 974 | LABOR- SUBCONTRACTOR
%R | 502867 | 6359 | 125039 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1STGL5235 | Excavation for Street lighting | 8177 | 224 | 0 | 200 | 0 | 69 | 69 | 200 | 51 | 0 | 51 |  |  |  | 2014-01-16 08:00 | 2014-02-15 17:00 |  | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 |  | PT_Normal |  |  |  |  | 8iZxc07ZTKmNI8ZzULou+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33870 | N | N | 35 | STREET LIGHTING |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 69 | LABOR - CIVIL
%R | 502868 | 6359 | 125039 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1STGL5240 | Construction of Duct Banks | 8178 | 224 | 0 | 200 | 0 | 1192.8 | 1192.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-20 17:00 |  | 2013-12-21 08:00 | 2014-01-18 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | 7c3VdRBoRFyIe1wAfWceyw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33870 | N | N | 35 | STREET LIGHTING |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1192.8 | LABOR- SUBCONTRACTOR
%R | 502869 | 6359 | 125039 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1STGL5245 | Construction of Foundation | 8172 | 224 | 0 | 200 | 0 | 638 | 638 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-20 17:00 |  | 2013-12-21 08:00 | 2014-01-18 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | IGaJVtv/RIGdMEHB88oHCQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33870 | N | N | 35 | STREET LIGHTING |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 638 | MANHOLES SK
%R | 502870 | 6359 | 125039 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1STGL5250 | Backfilling Street Lighting | 8177 | 224 | 0 | 200 | 0 | 287 | 287 | 200 | 275 | 0 | 275 |  |  |  | 2014-01-28 08:00 | 2014-02-26 17:00 |  | 2013-12-26 08:00 | 2014-01-23 17:00 | 2013-12-26 08:00 | 2014-01-23 17:00 | 2013-12-26 08:00 | 2014-01-23 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 |  | PT_Normal |  |  |  |  | rRFhjWHmQzuZkRakAGtzZg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33870 | N | N | 35 | STREET LIGHTING |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 287 | LABOR - CIVIL
%R | 502871 | 6359 | 125039 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1STGL5255 | Installation of light Post | 8178 | 760 | 0 | 200 | 0 | 216 | 216 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-22 08:00 | 2014-06-19 17:00 |  | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 |  | PT_Normal |  |  |  |  | EodAdHGbQWeUQzdXHQZgtw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33870 | N | N | 35 | STREET LIGHTING |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01; period 2: 2014-AP03 |  | 108 | LABOR- SUBCONTRACTOR
%R | 502872 | 6359 | 125039 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1STGL5260 | Electrical Works | 8178 | 760 | 0 | 200 | 0 | 823.6 | 823.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-27 17:00 |  | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | sJ/Vjiu1SmCH8EavRTaqvQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33870 | N | N | 35 | STREET LIGHTING |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 823.6 | LABOR- SUBCONTRACTOR
%R | 502873 | 6359 | 125040 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1FFGL5200 | Backfilling firefighting line | 8177 | 160 | 0 | 200 | 0 | 329 | 329 | 200 | 275 | 0 | 275 |  |  |  | 2013-12-30 08:00 | 2014-01-27 17:00 |  | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 |  | PT_Normal |  |  |  |  | amrql4teRpK9Dszwo3K8DQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33850 | N | N | 25 | FIREFIGHTING LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 329 | LABOR - CIVIL
%R | 502874 | 6359 | 125040 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1FFGL5205 | Construction of valve chambers & Thrust Blocks | 8165 | 400 | 0 | 200 | 0 | 202 | 202 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-03-10 17:00 |  | 2013-12-11 08:00 | 2014-01-09 17:00 | 2013-12-11 08:00 | 2014-01-09 17:00 | 2013-12-11 08:00 | 2014-01-09 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | 58NpvMhTQja2u0gypH1cwQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33850 | N | N | 25 | FIREFIGHTING LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 202 | STEEL FIXERS SK
%R | 502875 | 6359 | 125040 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1FFGL5210 | Connection with existing Firewater System | 8178 | 400 | 176 | 200 | 0 | 134.4 | 134.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-16 17:00 |  | 2013-12-17 08:00 | 2014-01-15 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | xtG8RpkwS5W2POQuWYoxkA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33850 | N | N | 25 | FIREFIGHTING LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 502876 | 6359 | 125040 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1FFGL5185 | Excavation for firefighting line | 8177 | 160 | 0 | 200 | 0 | 283 | 283 | 200 | 151 | 0 | 151 |  |  |  | 2013-12-09 08:00 | 2014-01-07 17:00 |  | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-12-09 08:00 | 2014-01-07 17:00 |  | PT_Normal |  |  |  |  | 1/5K8oyXSLmvjVWN+yaQOQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33850 | N | N | 25 | FIREFIGHTING LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 283 | LABOR - CIVIL
%R | 502877 | 6359 | 125040 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1FFGL5190 | Laying of firefighting line | 8178 | 160 | 0 | 200 | 0 | 303.6 | 303.6 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-17 08:00 | 2014-01-15 17:00 |  | 2013-11-24 08:00 | 2013-12-23 17:00 | 2013-11-24 08:00 | 2013-12-23 17:00 | 2013-11-24 08:00 | 2013-12-23 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | r0hLdj9vT868JlJMM8QYlA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33850 | N | N | 25 | FIREFIGHTING LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 303.6 | LABOR- SUBCONTRACTOR
%R | 502878 | 6359 | 125040 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1FFGL5195 | Testing of firefighting line | 8178 | 160 | 0 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-24 08:00 | 2014-01-21 17:00 |  | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-11-30 08:00 | 2013-12-29 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 |  | PT_Normal |  |  |  |  | im6J/3+wRGWpFkeepWhTzA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33850 | N | N | 25 | FIREFIGHTING LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 84 | LABOR- SUBCONTRACTOR
%R | 502879 | 6359 | 125041 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1BWGL5315 | Construction of Boundary Wall (Ht-3m) | 8165 | 792 | 0 | 200 | 0 | 224 | 224 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-04 08:00 | 2014-06-01 17:00 |  | 2014-01-07 08:00 | 2014-02-04 17:00 | 2014-01-07 08:00 | 2014-02-04 17:00 | 2014-01-07 08:00 | 2014-02-04 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 |  | PT_Normal |  |  |  |  | WHPG+jZqQOKRrxo4qlnpvg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:44 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33900 | N | N | 50 | BOUNDARY WALL |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 224 | STEEL FIXERS SK
%R | 502880 | 6359 | 125041 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 8178 | 792 | 0 | 200 | 0 | 28 | 28 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-20 08:00 | 2014-06-17 17:00 |  | 2014-01-23 08:00 | 2014-02-22 17:00 | 2014-01-23 08:00 | 2014-02-22 17:00 | 2014-01-23 08:00 | 2014-02-22 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | Lm8l0cO3S5WyZ20IiyZiNw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:44 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33900 | N | N | 50 | BOUNDARY WALL |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 28 | LABOR- SUBCONTRACTOR
%R | 502881 | 6359 | 125041 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 8165 | 792 | 0 | 200 | 0 | 168 | 168 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-18 08:00 | 2014-07-16 17:00 |  | 2014-02-23 08:00 | 2014-03-23 17:00 | 2014-02-23 08:00 | 2014-03-23 17:00 | 2014-02-23 08:00 | 2014-03-23 17:00 | 2014-06-18 08:00 | 2014-07-16 17:00 |  | PT_Normal |  |  |  |  | ezXOpQeaRKCrf4hqttUErw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:44 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33900 | N | N | 50 | BOUNDARY WALL |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 84 | STEEL FIXERS SK
%R | 502882 | 6359 | 125041 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 8165 | 792 | 200 | 200 | 0 | 154 | 154 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-30 08:00 | 2014-07-28 17:00 |  | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-06-30 08:00 | 2014-07-28 17:00 |  | PT_Normal |  |  |  |  | DLjgzeAWRe2646LNI6Iz9Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:44 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33900 | N | N | 50 | BOUNDARY WALL |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 154 | STEEL FIXERS SK
%R | 502883 | 6359 | 125042 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1DRGL5115 | Excavation for Drainage line | 8177 | 160 | 0 | 200 | 0 | 431 | 431 | 200 | 251 | 0 | 251 |  |  |  | 2013-09-16 08:00 | 2013-10-14 17:00 |  | 2013-08-24 08:00 | 2013-09-21 17:00 | 2013-08-24 08:00 | 2013-09-21 17:00 | 2013-08-24 08:00 | 2013-09-21 17:00 | 2013-09-16 08:00 | 2013-10-14 17:00 |  | PT_Normal |  |  |  |  | gaKTtqAgRCSji/zqtpmYqA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33820 | N | N | 10 | DRAINAGE LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 431 | LABOR - CIVIL
%R | 502884 | 6359 | 125042 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1DRGL5120 | Laying of Drainage line | 8178 | 160 | 0 | 200 | 0 | 276 | 276 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-28 08:00 | 2013-10-28 17:00 |  | 2013-09-04 08:00 | 2013-10-02 17:00 | 2013-09-04 08:00 | 2013-10-02 17:00 | 2013-09-04 08:00 | 2013-10-02 17:00 | 2013-09-28 08:00 | 2013-10-28 17:00 |  | PT_Normal |  |  |  |  | tec3QJ1QTYWlrfp+huTDrw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33820 | N | N | 10 | DRAINAGE LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 276 | LABOR- SUBCONTRACTOR
%R | 502885 | 6359 | 125042 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1DRGL5125 | Testing of Drainage line | 8178 | 160 | 0 | 200 | 0 | 134.4 | 134.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-09 08:00 | 2013-11-09 17:00 |  | 2013-09-16 08:00 | 2013-10-14 17:00 | 2013-09-16 08:00 | 2013-10-14 17:00 | 2013-09-16 08:00 | 2013-10-14 17:00 | 2013-10-09 08:00 | 2013-11-09 17:00 |  | PT_Normal |  |  |  |  | h0ZjTcwCTYWynearqV6b4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33820 | N | N | 10 | DRAINAGE LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 502886 | 6359 | 125042 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1DRGL5130 | Backfilling Drainage line | 8177 | 160 | 0 | 120 | 0 | 402 | 402 | 120 | 330 | 0 | 330 |  |  |  | 2013-10-29 08:00 | 2013-11-14 17:00 |  | 2013-10-03 08:00 | 2013-10-22 17:00 | 2013-10-03 08:00 | 2013-10-22 17:00 | 2013-10-03 08:00 | 2013-10-22 17:00 | 2013-10-29 08:00 | 2013-11-14 17:00 |  | PT_Normal |  |  |  |  | ZWnCvppkS5mIKwDSY2HrFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33820 | N | N | 10 | DRAINAGE LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 402 | LABOR - CIVIL
%R | 502887 | 6359 | 125043 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1TCGL5295 | Excavation Telecommunication trenches | 8177 | 224 | 0 | 160 | 0 | 528 | 528 | 160 | 300 | 0 | 300 |  |  |  | 2014-02-09 08:00 | 2014-03-04 17:00 |  | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-02-09 08:00 | 2014-03-04 17:00 |  | PT_Normal |  |  |  |  | qJIEHQpdQoah5rvNnQPZdA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33890 | N | N | 45 | TELECOMMUNICATION LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 528 | LABOR - CIVIL
%R | 502888 | 6359 | 125043 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1TCGL5300 | Laying of cables | 8178 | 224 | 0 | 160 | 0 | 795.2 | 795.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-10 17:00 |  | 2014-01-13 08:00 | 2014-02-04 17:00 | 2014-01-13 08:00 | 2014-02-04 17:00 | 2014-01-13 08:00 | 2014-02-04 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | iDm+pIEjTUWBQNx53B7mHg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33890 | N | N | 45 | TELECOMMUNICATION LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 795.2 | LABOR- SUBCONTRACTOR
%R | 502889 | 6359 | 125043 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1TCGL5305 | Backfilling telecommunication trench | 8177 | 224 | 0 | 160 | 0 | 530 | 530 | 160 | 440 | 0 | 440 |  |  |  | 2014-02-22 08:00 | 2014-03-16 17:00 |  | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-02-22 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | pgPQ57hLRu2uqRjPWz/BjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33890 | N | N | 45 | TELECOMMUNICATION LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 530 | LABOR - CIVIL
%R | 502890 | 6359 | 125043 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ1TCGL5310 | Connection & Installation | 8178 | 264 | 40 | 160 | 0 | 344.4 | 344.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-04-02 17:00 |  | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-03-11 08:00 | 2014-04-02 17:00 |  | PT_Normal |  |  |  |  | r9YkzuUOS/+yO1Nlw4oLhg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33890 | N | N | 45 | TELECOMMUNICATION LINES |  | 125030 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 344.4 | LABOR- SUBCONTRACTOR
%R | 502891 | 6359 | 125046 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4TCGL5295 | Excavation Telecommunication trenches | 8177 | 96 | 0 | 160 | 0 | 528 | 528 | 160 | 300 | 0 | 300 |  |  |  | 2014-06-30 08:00 | 2014-07-22 17:00 |  | 2014-06-16 08:00 | 2014-07-08 17:00 | 2014-06-16 08:00 | 2014-07-08 17:00 | 2014-06-16 08:00 | 2014-07-08 17:00 | 2014-06-30 08:00 | 2014-07-22 17:00 |  | PT_Normal |  |  |  |  | E3hqcsGEQy2cw0lM2E8mNA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34340 | N | N | 45 | TELECOMMUNICATION LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 528 | LABOR - CIVIL
%R | 502892 | 6359 | 125046 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4TCGL5300 | Laying of cables | 8178 | 96 | 0 | 160 | 0 | 795.2 | 795.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-06 08:00 | 2014-07-28 17:00 |  | 2014-06-22 08:00 | 2014-07-14 17:00 | 2014-06-22 08:00 | 2014-07-14 17:00 | 2014-06-22 08:00 | 2014-07-14 17:00 | 2014-07-06 08:00 | 2014-07-28 17:00 |  | PT_Normal |  |  |  |  | fgDW9PJSTyGpEepZPYzwoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34340 | N | N | 45 | TELECOMMUNICATION LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 795.2 | LABOR- SUBCONTRACTOR
%R | 502893 | 6359 | 125046 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4TCGL5305 | Backfilling telecommunication trench | 8177 | 96 | 0 | 160 | 0 | 530 | 530 | 160 | 440 | 0 | 440 |  |  |  | 2014-07-12 08:00 | 2014-08-06 17:00 |  | 2014-06-28 08:00 | 2014-07-20 17:00 | 2014-06-28 08:00 | 2014-07-20 17:00 | 2014-06-28 08:00 | 2014-07-20 17:00 | 2014-07-12 08:00 | 2014-08-06 17:00 |  | PT_Normal |  |  |  |  | lgSxoUzASu2pdWiuG87x+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34340 | N | N | 45 | TELECOMMUNICATION LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 530 | LABOR - CIVIL
%R | 502894 | 6359 | 125046 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4TCGL5310 | Connection & Installation | 8178 | 408 | 184 | 160 | 0 | 344.4 | 344.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-10-02 17:00 |  | 2014-07-09 08:00 | 2014-07-31 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 | 2014-09-10 08:00 | 2014-10-02 17:00 |  | PT_Normal |  |  |  |  | sFQDio0rRmOVnWmghIQyiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34340 | N | N | 45 | TELECOMMUNICATION LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 344.4 | LABOR- SUBCONTRACTOR
%R | 502895 | 6359 | 125047 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4RWGL6000 | Excavation & Earth Filling | 8177 | 96 | 0 | 80 | 0 | 1232 | 1232 | 80 | 500 | 0 | 500 |  |  |  | 2014-08-07 08:00 | 2014-08-18 17:00 |  | 2014-07-21 08:00 | 2014-07-31 17:00 | 2014-07-21 08:00 | 2014-07-31 17:00 | 2014-07-21 08:00 | 2014-07-31 17:00 | 2014-08-07 08:00 | 2014-08-18 17:00 |  | PT_Normal |  |  |  |  | uNXaxxarRLerah30mfGsAQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34360 | N | N | 55 | ROAD WORKS |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1232 | LABOR - CIVIL
%R | 502896 | 6359 | 125047 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4RWGL6005 | Laying of Sub Grade | 8178 | 96 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-19 08:00 | 2014-09-16 17:00 |  | 2014-08-05 08:00 | 2014-09-02 17:00 | 2014-08-05 08:00 | 2014-09-02 17:00 | 2014-08-05 08:00 | 2014-09-02 17:00 | 2014-08-19 08:00 | 2014-09-16 17:00 |  | PT_Normal |  |  |  |  | MfwEItFlSieR+UfhC4bZhA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34360 | N | N | 55 | ROAD WORKS |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 24 | LABOR- SUBCONTRACTOR
%R | 502897 | 6359 | 125047 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4RWGL6010 | Laying of Precast Kerbs | 8178 | 96 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-31 08:00 | 2014-09-28 17:00 |  | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-31 08:00 | 2014-09-28 17:00 |  | PT_Normal |  |  |  |  | BTzpFXUJQhCWCM5AUsCt5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34360 | N | N | 55 | ROAD WORKS |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 24 | LABOR- SUBCONTRACTOR
%R | 502898 | 6359 | 125047 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4RWGL6015 | Laying of Granular Sub Base Coarse | 8173 | 96 | 0 | 160 | 0 | 1814 | 1814 | 160 | 600 | 0 | 600 |  |  |  | 2014-09-11 08:00 | 2014-10-04 17:00 |  | 2014-08-28 08:00 | 2014-09-20 17:00 | 2014-08-28 08:00 | 2014-09-20 17:00 | 2014-08-28 08:00 | 2014-09-20 17:00 | 2014-09-11 08:00 | 2014-10-04 17:00 |  | PT_Normal |  |  |  |  | DgpRaNQwQFGq8vi7aoC+xA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34360 | N | N | 55 | ROAD WORKS |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1814 | KERBSTONE MASON SK
%R | 502899 | 6359 | 125047 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4RWGL6020 | Laying of Road Base Asphalt Concrete | 8178 | 216 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-10-25 08:00 | 2014-10-29 17:00 |  | 2014-09-21 08:00 | 2014-09-25 17:00 | 2014-09-21 08:00 | 2014-09-25 17:00 | 2014-09-21 08:00 | 2014-09-25 17:00 | 2014-10-25 08:00 | 2014-10-29 17:00 |  | PT_Normal |  |  |  |  | wGZ7YJLKRuyaeOE9DqZbeA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34360 | N | N | 55 | ROAD WORKS |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 174 | LABOR- SUBCONTRACTOR
%R | 502900 | 6359 | 125047 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4RWGL6025 | Laying of Asphalt Wearing Coarse | 8178 | 328 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-11-16 08:00 | 2014-11-20 17:00 |  | 2014-09-27 08:00 | 2014-10-01 17:00 | 2014-09-27 08:00 | 2014-10-01 17:00 | 2014-09-27 08:00 | 2014-10-01 17:00 | 2014-11-16 08:00 | 2014-11-20 17:00 |  | PT_Normal |  |  |  |  | N4JAM0wVTZi3dsgcxt773w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34360 | N | N | 55 | ROAD WORKS |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 174 | LABOR- SUBCONTRACTOR
%R | 502901 | 6359 | 125047 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4RWGL6030 | Traffic Signage & Road Marking | 8178 | 336 | 120 | 40 | 0 | 974 | 974 | 40 | 0 | 0 | 0 |  |  |  | 2014-11-23 08:00 | 2014-11-27 17:00 |  | 2014-10-02 08:00 | 2014-10-07 17:00 | 2014-10-02 08:00 | 2014-10-07 17:00 | 2014-10-02 08:00 | 2014-10-07 17:00 | 2014-11-23 08:00 | 2014-11-27 17:00 |  | PT_Normal |  |  |  |  | ilpOp0neTMezPUCuhQOhPA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34360 | N | N | 55 | ROAD WORKS |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 974 | LABOR- SUBCONTRACTOR
%R | 502902 | 6359 | 125048 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4IRGL5265 | Excavation for irrigation line | 8177 | 296 | 0 | 200 | 0 | 812 | 812 | 200 | 500 | 0 | 500 |  |  |  | 2014-08-21 08:00 | 2014-09-18 17:00 |  | 2014-07-06 08:00 | 2014-08-06 17:00 | 2014-07-06 08:00 | 2014-08-06 17:00 | 2014-07-06 08:00 | 2014-08-06 17:00 | 2014-08-21 08:00 | 2014-09-18 17:00 |  | PT_Normal |  |  |  |  | qxDt4ViER86sSsZNTTsW5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:53 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34330 | N | N | 40 | IRRIGATION LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 406 | LABOR - CIVIL
%R | 502903 | 6359 | 125048 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4IRGL5270 | Laying of irrigationline | 8178 | 296 | 0 | 200 | 0 | 386.4 | 386.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-27 08:00 | 2014-09-24 17:00 |  | 2014-07-12 08:00 | 2014-08-12 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 | 2014-08-27 08:00 | 2014-09-24 17:00 |  | PT_Normal |  |  |  |  | mIdyWZg7SiKer2xK9APsiw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34330 | N | N | 40 | IRRIGATION LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 193.2 | LABOR- SUBCONTRACTOR
%R | 502904 | 6359 | 125048 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4IRGL5275 | Testing of irrigation line | 8178 | 296 | 0 | 200 | 0 | 319.2 | 319.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-02 08:00 | 2014-09-30 17:00 |  | 2014-07-17 08:00 | 2014-08-18 17:00 | 2014-07-17 08:00 | 2014-08-18 17:00 | 2014-07-17 08:00 | 2014-08-18 17:00 | 2014-09-02 08:00 | 2014-09-30 17:00 |  | PT_Normal |  |  |  |  | 4r+0BUS3R1CYUznonlOaYQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34330 | N | N | 40 | IRRIGATION LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 159.6 | LABOR- SUBCONTRACTOR
%R | 502905 | 6359 | 125048 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4IRGL5280 | Backfilling irrigation line | 8177 | 296 | 0 | 200 | 0 | 676 | 676 | 200 | 550 | 0 | 550 |  |  |  | 2014-09-08 08:00 | 2014-10-06 17:00 |  | 2014-07-23 08:00 | 2014-08-24 17:00 | 2014-07-23 08:00 | 2014-08-24 17:00 | 2014-07-23 08:00 | 2014-08-24 17:00 | 2014-09-08 08:00 | 2014-10-06 17:00 |  | PT_Normal |  |  |  |  | 0dvwdiuGT1KVwWCVXu9VIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34330 | N | N | 40 | IRRIGATION LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 338 | LABOR - CIVIL
%R | 502906 | 6359 | 125048 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4IRGL5285 | Construction of Thrust Blocks,Pull boxes | 8178 | 336 | 0 | 200 | 0 | 116.4 | 116.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-25 08:00 | 2014-10-26 17:00 |  | 2014-08-07 08:00 | 2014-09-04 17:00 | 2014-08-07 08:00 | 2014-09-04 17:00 | 2014-08-07 08:00 | 2014-09-04 17:00 | 2014-09-25 08:00 | 2014-10-26 17:00 |  | PT_Normal |  |  |  |  | YIUx8j8iTzaFll5kTxnO3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34330 | N | N | 40 | IRRIGATION LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 116.4 | LABOR- SUBCONTRACTOR
%R | 502907 | 6359 | 125048 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4IRGL5290 | Irrigation Fittings (Nozzle,Values) | 8178 | 336 | 88 | 200 | 0 | 285.6 | 285.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-04 08:00 | 2014-11-03 17:00 |  | 2014-08-16 08:00 | 2014-09-13 17:00 | 2014-08-16 08:00 | 2014-09-13 17:00 | 2014-08-16 08:00 | 2014-09-13 17:00 | 2014-10-04 08:00 | 2014-11-03 17:00 |  | PT_Normal |  |  |  |  | axF9Kn3+QGCtwmwB6CecfA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34330 | N | N | 40 | IRRIGATION LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 285.6 | LABOR- SUBCONTRACTOR
%R | 502908 | 6359 | 125049 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4WSGL5155 | Excavation for water line | 8177 | 80 | 0 | 200 | 0 | 401 | 401 | 200 | 251 | 0 | 251 |  |  |  | 2014-04-14 08:00 | 2014-05-12 17:00 |  | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34290 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 401 | LABOR - CIVIL
%R | 502909 | 6359 | 125049 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4WSGL5160 | Laying of water line | 8178 | 80 | 0 | 200 | 0 | 285.6 | 285.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | 7yOMClcRTK+SbV6SoJpFgw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34290 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 285.6 | LABOR- SUBCONTRACTOR
%R | 502910 | 6359 | 125049 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4WSGL5165 | Testing of potable water line | 8178 | 80 | 0 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-26 08:00 | 2014-05-24 17:00 |  | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 |  | PT_Normal |  |  |  |  | M/MrXzbsR0abLQS0Ue/cIQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34290 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 84 | LABOR- SUBCONTRACTOR
%R | 502911 | 6359 | 125049 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4WSGL5170 | Backfilling potable water line | 8177 | 80 | 0 | 200 | 0 | 335 | 335 | 200 | 275 | 0 | 275 |  |  |  | 2014-05-01 08:00 | 2014-05-29 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | jI6yOZsQSx+mbYBRJ4nLEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34290 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 335 | LABOR - CIVIL
%R | 502912 | 6359 | 125049 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4WSGL5175 | Construction of valve chambers & Thrust Blocks | 8172 | 328 | 0 | 200 | 0 | 132 | 132 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-07-10 17:00 |  | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 |  | PT_Normal |  |  |  |  | FNznftGuROmgmwDVOEBxKQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34290 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 132 | MANHOLES SK
%R | 502913 | 6359 | 125049 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4WSGL5180 | Installation of meter ,Accessories & Connection | 8178 | 328 | 56 | 160 | 0 | 50.4 | 50.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-12 08:00 | 2014-08-06 17:00 |  | 2014-05-25 08:00 | 2014-06-16 17:00 | 2014-05-25 08:00 | 2014-06-16 17:00 | 2014-05-25 08:00 | 2014-06-16 17:00 | 2014-07-12 08:00 | 2014-08-06 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34290 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 502914 | 6359 | 125050 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4FFGL5185 | Excavation for firefighting line | 8177 | 80 | 0 | 200 | 0 | 283 | 283 | 200 | 151 | 0 | 151 |  |  |  | 2014-05-07 08:00 | 2014-06-04 17:00 |  | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-05-07 08:00 | 2014-06-04 17:00 |  | PT_Normal |  |  |  |  | oPYgus/OQaugczFS0EvxLw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34300 | N | N | 25 | FIREFIGHTING LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 283 | LABOR - CIVIL
%R | 502915 | 6359 | 125050 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4FFGL5190 | Laying of firefighting line | 8178 | 80 | 0 | 200 | 0 | 303.6 | 303.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-15 08:00 | 2014-06-12 17:00 |  | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 |  | PT_Normal |  |  |  |  | GOb0Hi8bRrmGPZYawNJ2KQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34300 | N | N | 25 | FIREFIGHTING LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 303.6 | LABOR- SUBCONTRACTOR
%R | 502916 | 6359 | 125050 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4FFGL5195 | Testing of firefighting line | 8178 | 80 | 0 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-21 08:00 | 2014-06-18 17:00 |  | 2014-05-10 08:00 | 2014-06-07 17:00 | 2014-05-10 08:00 | 2014-06-07 17:00 | 2014-05-10 08:00 | 2014-06-07 17:00 | 2014-05-21 08:00 | 2014-06-18 17:00 |  | PT_Normal |  |  |  |  | U0zzJ0TORomnSoYJoJI20A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34300 | N | N | 25 | FIREFIGHTING LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 84 | LABOR- SUBCONTRACTOR
%R | 502917 | 6359 | 125050 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4FFGL5200 | Backfilling firefighting line | 8177 | 80 | 0 | 200 | 0 | 329 | 329 | 200 | 275 | 0 | 275 |  |  |  | 2014-05-27 08:00 | 2014-06-24 17:00 |  | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 | 2014-05-27 08:00 | 2014-06-24 17:00 |  | PT_Normal |  |  |  |  | Hl79HTZgT8SX0qnplTlEMA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34300 | N | N | 25 | FIREFIGHTING LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 329 | LABOR - CIVIL
%R | 502918 | 6359 | 125050 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4FFGL5205 | Construction of valve chambers & Thrust Blocks | 8165 | 272 | 0 | 200 | 0 | 202 | 202 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-30 08:00 | 2014-07-28 17:00 |  | 2014-05-21 08:00 | 2014-06-18 17:00 | 2014-05-21 08:00 | 2014-06-18 17:00 | 2014-05-21 08:00 | 2014-06-18 17:00 | 2014-06-30 08:00 | 2014-07-28 17:00 |  | PT_Normal |  |  |  |  | 8UQasvklSrKEYpaknfC7dg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34300 | N | N | 25 | FIREFIGHTING LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 202 | STEEL FIXERS SK
%R | 502919 | 6359 | 125050 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4FFGL5210 | Connection with existing Firewater System | 8178 | 272 | 144 | 200 | 0 | 134.4 | 134.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-06 08:00 | 2014-08-06 17:00 |  | 2014-05-27 08:00 | 2014-06-24 17:00 | 2014-05-27 08:00 | 2014-06-24 17:00 | 2014-05-27 08:00 | 2014-06-24 17:00 | 2014-07-06 08:00 | 2014-08-06 17:00 |  | PT_Normal |  |  |  |  | h0TB8H0nS3CmXOwi7bcGLw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34300 | N | N | 25 | FIREFIGHTING LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 502920 | 6359 | 125051 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4HDGL7020 | Precast Concrete Kerbs works | 8173 | 248 | 0 | 160 | 0 | 1178 | 1178 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-21 17:00 |  | 2014-07-21 08:00 | 2014-08-16 17:00 | 2014-07-21 08:00 | 2014-08-16 17:00 | 2014-07-21 08:00 | 2014-08-16 17:00 | 2014-08-30 08:00 | 2014-09-21 17:00 |  | PT_Normal |  |  |  |  | tO/HZ1o9TAK8w9XmJrnA3g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34380 | N | N | 65 | HARD LANDSCAPING |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1178 | KERBSTONE MASON SK
%R | 502921 | 6359 | 125051 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4HDGL7025 | Interlocking for Walkways | 8174 | 248 | 0 | 200 | 0 | 806 | 806 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-10-08 17:00 |  | 2014-08-05 08:00 | 2014-09-02 17:00 | 2014-08-05 08:00 | 2014-09-02 17:00 | 2014-08-05 08:00 | 2014-09-02 17:00 | 2014-09-10 08:00 | 2014-10-08 17:00 |  | PT_Normal |  |  |  |  | Vy0OUZtpQmi7f5laiM2XoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34380 | N | N | 65 | HARD LANDSCAPING |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 806 | INTERLOCK MASON SK
%R | 502922 | 6359 | 125051 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4HDGL7030 | Construction of Retaining wall | 8165 | 248 | 0 | 200 | 0 | 756 | 756 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-22 08:00 | 2014-10-22 17:00 |  | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-09-22 08:00 | 2014-10-22 17:00 |  | PT_Normal |  |  |  |  | hSkAWblfTEu8wcWDWBYAlw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34380 | N | N | 65 | HARD LANDSCAPING |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 756 | STEEL FIXERS SK
%R | 502923 | 6359 | 125051 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4HDGL7035 | Construction of Wash Stone Boulders | 8170 | 248 | 0 | 200 | 0 | 88 | 88 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-22 08:00 | 2014-10-22 17:00 |  | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-09-22 08:00 | 2014-10-22 17:00 |  | PT_Normal |  |  |  |  | yt5H+hAMTaOwdh2idMZuQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34380 | N | N | 65 | HARD LANDSCAPING |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 88 | TILE MASON SK
%R | 502924 | 6359 | 125051 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4HDGL7040 | Construction of Speed Humps | 8167 | 328 | 256 | 80 | 0 | 14 | 14 | 80 | 0 | 0 | 0 |  |  |  | 2014-11-22 08:00 | 2014-12-02 17:00 |  | 2014-10-02 08:00 | 2014-10-15 17:00 | 2014-10-02 08:00 | 2014-10-15 17:00 | 2014-10-02 08:00 | 2014-10-15 17:00 | 2014-11-22 08:00 | 2014-12-02 17:00 |  | PT_Normal |  |  |  |  | Xrk60iR4RyGznW6Vi4sM2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34380 | N | N | 65 | HARD LANDSCAPING |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 14 | CONCRETE MASON SK
%R | 502925 | 6359 | 125052 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4PSGL7000 | Excavation | 8177 | 256 | 40 | 120 | 0 | 148 | 148 | 120 | 76 | 0 | 76 |  |  |  | 2014-10-13 08:00 | 2014-10-29 17:00 |  | 2014-09-03 08:00 | 2014-09-20 17:00 | 2014-09-03 08:00 | 2014-09-20 17:00 | 2014-09-03 08:00 | 2014-09-20 17:00 | 2014-10-13 08:00 | 2014-10-29 17:00 |  | PT_Normal |  |  |  |  | fYZfNly9RtKflYCjrHeEdA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34370 | N | N | 60 | PARKING SHED |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 148 | LABOR - CIVIL
%R | 502926 | 6359 | 125052 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4PSGL7005 | Foundation casting | 8165 | 216 | 0 | 120 | 0 | 252 | 252 | 120 | 0 | 0 | 0 |  |  |  | 2014-10-19 08:00 | 2014-11-04 17:00 |  | 2014-09-15 08:00 | 2014-10-01 17:00 | 2014-09-15 08:00 | 2014-10-01 17:00 | 2014-09-15 08:00 | 2014-10-01 17:00 | 2014-10-19 08:00 | 2014-11-04 17:00 |  | PT_Normal |  |  |  |  | nD4PJcEdSKCae3RX15+SoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34370 | N | N | 60 | PARKING SHED |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 252 | STEEL FIXERS SK
%R | 502927 | 6359 | 125052 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4PSGL7010 | Column, Frame& Fabrics Erection | 8178 | 216 | 0 | 200 | 0 | 286 | 286 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-30 08:00 | 2014-11-27 17:00 |  | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-10-30 08:00 | 2014-11-27 17:00 |  | PT_Normal |  |  |  |  | SoD8bzq3QPmIsaqEOA5ymA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34370 | N | N | 60 | PARKING SHED |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 143 | LABOR- SUBCONTRACTOR
%R | 502928 | 6359 | 125052 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4PSGL7015 | Electrical Works-Parking Shed | 8178 | 216 | 136 | 200 | 0 | 51.6 | 51.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-05 08:00 | 2014-12-03 17:00 |  | 2014-10-02 08:00 | 2014-11-02 17:00 | 2014-10-02 08:00 | 2014-11-02 17:00 | 2014-10-02 08:00 | 2014-11-02 17:00 | 2014-11-05 08:00 | 2014-12-03 17:00 |  | PT_Normal |  |  |  |  | y71hnLDxSRy6jytz97KIow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34370 | N | N | 60 | PARKING SHED |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10; period 2: 2014-AP11 |  | 25.8 | LABOR- SUBCONTRACTOR
%R | 502929 | 6359 | 125053 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4SLGL7200 | Excavation | 8177 | 248 | 0 | 200 | 0 | 497 | 497 | 200 | 251 | 0 | 251 |  |  |  | 2014-10-04 08:00 | 2014-11-03 17:00 |  | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-10-04 08:00 | 2014-11-03 17:00 |  | PT_Normal |  |  |  |  | hjoCQp5YSOONZgW0E/zwrQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34390 | N | N | 70 | SOFT LANDSCAPING |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 497 | LABOR - CIVIL
%R | 502930 | 6359 | 125053 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4SLGL7205 | Sweet Soil Laying | 8178 | 248 | 0 | 200 | 0 | 2380 | 2380 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-09-09 08:00 | 2014-10-07 17:00 | 2014-09-09 08:00 | 2014-10-07 17:00 | 2014-09-09 08:00 | 2014-10-07 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | Kl3IsEpBSGSOMYtgMfSW5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34390 | N | N | 70 | SOFT LANDSCAPING |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 2380 | LABOR- SUBCONTRACTOR
%R | 502931 | 6359 | 125053 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4SLGL7210 | Plantation works | 8178 | 328 | 144 | 200 | 0 | 588 | 588 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-10 08:00 | 2014-12-08 17:00 |  | 2014-09-21 08:00 | 2014-10-21 17:00 | 2014-09-21 08:00 | 2014-10-21 17:00 | 2014-09-21 08:00 | 2014-10-21 17:00 | 2014-11-10 08:00 | 2014-12-08 17:00 |  | PT_Normal |  |  |  |  | hvPk2k6xTQaxFA/xBEl0sQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34390 | N | N | 70 | SOFT LANDSCAPING |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 294 | LABOR- SUBCONTRACTOR
%R | 502932 | 6359 | 125054 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4STGL5235 | Excavation for Street lighting | 8177 | 96 | 0 | 200 | 0 | 69 | 69 | 200 | 51 | 0 | 51 |  |  |  | 2014-06-07 08:00 | 2014-07-05 17:00 |  | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-06-07 08:00 | 2014-07-05 17:00 |  | PT_Normal |  |  |  |  | 3F64JCUDQvGmtse8tPp+aQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34320 | N | N | 35 | STREET LIGHTING |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 69 | LABOR - CIVIL
%R | 502933 | 6359 | 125054 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4STGL5240 | Construction of Duct Banks | 8178 | 96 | 0 | 200 | 0 | 1192.8 | 1192.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-07-10 17:00 |  | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 |  | PT_Normal |  |  |  |  | nXbT2AoITcOqhjngjKvkMA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34320 | N | N | 35 | STREET LIGHTING |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1192.8 | LABOR- SUBCONTRACTOR
%R | 502934 | 6359 | 125054 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4STGL5245 | Construction of Foundation | 8172 | 96 | 0 | 200 | 0 | 638 | 638 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-07-10 17:00 |  | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 |  | PT_Normal |  |  |  |  | nyDDJzC+TjmSJNZecNpuLQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34320 | N | N | 35 | STREET LIGHTING |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 638 | MANHOLES SK
%R | 502935 | 6359 | 125054 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4STGL5250 | Backfilling Street Lighting | 8177 | 96 | 0 | 200 | 0 | 287 | 287 | 200 | 275 | 0 | 275 |  |  |  | 2014-06-18 08:00 | 2014-07-16 17:00 |  | 2014-06-04 08:00 | 2014-07-02 17:00 | 2014-06-04 08:00 | 2014-07-02 17:00 | 2014-06-04 08:00 | 2014-07-02 17:00 | 2014-06-18 08:00 | 2014-07-16 17:00 |  | PT_Normal |  |  |  |  | 7WKht0NYSb+W4WFVQteV6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34320 | N | N | 35 | STREET LIGHTING |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 287 | LABOR - CIVIL
%R | 502936 | 6359 | 125054 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4STGL5255 | Installation of light Post | 8178 | 608 | 144 | 200 | 0 | 216 | 216 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | TvCEwGJrTwG7OAC4n+VyDA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34320 | N | N | 35 | STREET LIGHTING |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 216 | LABOR- SUBCONTRACTOR
%R | 502937 | 6359 | 125054 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4STGL5260 | Electrical Works | 8178 | 472 | 144 | 200 | 0 | 823.6 | 823.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-28 08:00 | 2014-10-28 17:00 |  | 2014-07-17 08:00 | 2014-08-18 17:00 | 2014-07-17 08:00 | 2014-08-18 17:00 | 2014-07-17 08:00 | 2014-08-18 17:00 | 2014-09-28 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | DKUfMYCYRLu5ickHS55/kQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34320 | N | N | 35 | STREET LIGHTING |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 411.8 | LABOR- SUBCONTRACTOR
%R | 502938 | 6359 | 125055 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4DRGL5115 | Excavation for Drainage line | 8177 | 72 | 0 | 200 | 0 | 431 | 431 | 200 | 251 | 0 | 251 |  |  |  | 2014-02-27 08:00 | 2014-03-27 17:00 |  | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 |  | PT_Normal |  |  |  |  | aZ7XnMA9TJie6NnW7v6Tkg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34270 | N | N | 10 | DRAINAGE LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 215.5 | LABOR - CIVIL
%R | 502939 | 6359 | 125055 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4DRGL5120 | Laying of Drainage line | 8178 | 72 | 0 | 200 | 0 | 276 | 276 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-06 08:00 | 2014-04-03 17:00 |  | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 |  | PT_Normal |  |  |  |  | ChYp8aiiQb2ZWohiraiK1w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34270 | N | N | 10 | DRAINAGE LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 138 | LABOR- SUBCONTRACTOR
%R | 502940 | 6359 | 125055 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4DRGL5125 | Testing of Drainage line | 8178 | 72 | 0 | 200 | 0 | 134.4 | 134.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-12 17:00 |  | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 |  | PT_Normal |  |  |  |  | XrxofTvIT5GW/bBFJZgr4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34270 | N | N | 10 | DRAINAGE LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 502941 | 6359 | 125055 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4DRGL5130 | Backfilling Drainage line | 8177 | 72 | 0 | 120 | 0 | 402 | 402 | 120 | 330 | 0 | 330 |  |  |  | 2014-04-01 08:00 | 2014-04-17 17:00 |  | 2014-03-22 08:00 | 2014-04-07 17:00 | 2014-03-22 08:00 | 2014-04-07 17:00 | 2014-03-22 08:00 | 2014-04-07 17:00 | 2014-04-01 08:00 | 2014-04-17 17:00 |  | PT_Normal |  |  |  |  | UiQObifaRaq0xVVsuaiBXQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34270 | N | N | 10 | DRAINAGE LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 402 | LABOR - CIVIL
%R | 502942 | 6359 | 125056 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4SAGL5135 | Construction of manholes Drainage | 8177 | 568 | 144 | 200 | 0 | 6 | 6 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-07-10 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 |  | PT_Normal |  |  |  |  | feBvK+q3RJSMx0bSXAskhw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34280 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 6 | LABOR - CIVIL
%R | 502943 | 6359 | 125056 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4SAGL5140 | Construction of soakaways | 8172 | 96 | 0 | 200 | 0 | 154 | 154 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-02 08:00 | 2014-04-30 17:00 |  | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 |  | PT_Normal |  |  |  |  | B6WdBenyTBmCcaOKAg94XQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34280 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 154 | MANHOLES SK
%R | 502944 | 6359 | 125056 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4SAGL5145 | Construction of Road gullies | 8172 | 96 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-01 08:00 | 2014-05-29 17:00 |  | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-05-01 08:00 | 2014-05-29 17:00 |  | PT_Normal |  |  |  |  | pIuO7vOUT0ybthurFwr7iw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34280 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 176 | MANHOLES SK
%R | 502945 | 6359 | 125056 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4SAGL5150 | Connection with existing sewer manhole | 8177 | 384 | 288 | 160 | 0 | 6 | 6 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-12 08:00 | 2014-08-06 17:00 |  | 2014-05-17 08:00 | 2014-06-08 17:00 | 2014-05-17 08:00 | 2014-06-08 17:00 | 2014-05-17 08:00 | 2014-06-08 17:00 | 2014-07-12 08:00 | 2014-08-06 17:00 |  | PT_Normal |  |  |  |  | 3BQ2PdyGQiGgifhs6RJsaw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34280 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 6 | LABOR - CIVIL
%R | 502946 | 6359 | 125057 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4ELGL5215 | Excavation Cable Trenches & Duct Banks | 8177 | 96 | 0 | 200 | 0 | 1374 | 1374 | 200 | 600 | 0 | 600 |  |  |  | 2014-06-07 08:00 | 2014-07-05 17:00 |  | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-06-07 08:00 | 2014-07-05 17:00 |  | PT_Normal |  |  |  |  | h+kMawrHQh64e7yWWDNmmg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34310 | N | N | 30 | ELECTRICAL LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1374 | LABOR - CIVIL
%R | 502947 | 6359 | 125057 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4ELGL5220 | Laying of electrical cables | 8178 | 120 | 0 | 200 | 0 | 1834.8 | 1834.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-16 08:00 | 2014-07-14 17:00 |  | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 |  | PT_Normal |  |  |  |  | kW0iTY/ST8ijR/6xoxrMxw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34310 | N | N | 30 | ELECTRICAL LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1834.8 | LABOR- SUBCONTRACTOR
%R | 502948 | 6359 | 125057 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4ELGL5225 | Backfilling Electrical trench | 8177 | 120 | 0 | 200 | 0 | 862 | 862 | 200 | 550 | 0 | 550 |  |  |  | 2014-06-24 08:00 | 2014-07-22 17:00 |  | 2014-06-07 08:00 | 2014-07-05 17:00 | 2014-06-07 08:00 | 2014-07-05 17:00 | 2014-06-07 08:00 | 2014-07-05 17:00 | 2014-06-24 08:00 | 2014-07-22 17:00 |  | PT_Normal |  |  |  |  | 7FBrtvk2TUSVVGJ5FVQt2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34310 | N | N | 30 | ELECTRICAL LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 862 | LABOR - CIVIL
%R | 502949 | 6359 | 125057 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4ELGL5230 | Construction of Submain Board & Feeder Pillar | 8165 | 472 | 0 | 200 | 0 | 224 | 224 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-27 17:00 |  | 2014-06-18 08:00 | 2014-07-16 17:00 | 2014-06-18 08:00 | 2014-07-16 17:00 | 2014-06-18 08:00 | 2014-07-16 17:00 | 2014-08-30 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | agdDYjG9TSmEQy8Dr2Yr9w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34310 | N | N | 30 | ELECTRICAL LINES |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 224 | STEEL FIXERS SK
%R | 502950 | 6359 | 125058 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4BWGL5315 | Construction of Boundary Wall (Ht-3m) | 8165 | 416 | 0 | 200 | 0 | 224 | 224 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-19 08:00 | 2014-09-16 17:00 |  | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-08-19 08:00 | 2014-09-16 17:00 |  | PT_Normal |  |  |  |  | EKw85zQGRByfeKScV8T1Kg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34350 | N | N | 50 | BOUNDARY WALL |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 224 | STEEL FIXERS SK
%R | 502951 | 6359 | 125058 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 8178 | 416 | 0 | 200 | 0 | 28 | 28 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-04 08:00 | 2014-10-02 17:00 |  | 2014-07-02 08:00 | 2014-07-30 17:00 | 2014-07-02 08:00 | 2014-07-30 17:00 | 2014-07-02 08:00 | 2014-07-30 17:00 | 2014-09-04 08:00 | 2014-10-02 17:00 |  | PT_Normal |  |  |  |  | /xMrOcL+TVCwShd9G4McTw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34350 | N | N | 50 | BOUNDARY WALL |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 28 | LABOR- SUBCONTRACTOR
%R | 502952 | 6359 | 125058 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 8165 | 416 | 0 | 200 | 0 | 168 | 168 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-04 08:00 | 2014-11-03 17:00 |  | 2014-07-31 08:00 | 2014-09-01 17:00 | 2014-07-31 08:00 | 2014-09-01 17:00 | 2014-07-31 08:00 | 2014-09-01 17:00 | 2014-10-04 08:00 | 2014-11-03 17:00 |  | PT_Normal |  |  |  |  | qG1/ziw1SvusS6PoUUk0hw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34350 | N | N | 50 | BOUNDARY WALL |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 84 | STEEL FIXERS SK
%R | 502953 | 6359 | 125058 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ4BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 8165 | 504 | 144 | 200 | 0 | 154 | 154 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-30 08:00 | 2014-11-27 17:00 |  | 2014-08-16 08:00 | 2014-09-13 17:00 | 2014-08-16 08:00 | 2014-09-13 17:00 | 2014-08-16 08:00 | 2014-09-13 17:00 | 2014-10-30 08:00 | 2014-11-27 17:00 |  | PT_Normal |  |  |  |  | H0kif1euRReGZ3RBCCp2ww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34350 | N | N | 50 | BOUNDARY WALL |  | 125045 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 154 | STEEL FIXERS SK
%R | 502954 | 6359 | 125061 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2ELGL5215 | Excavation Cable Trenches & Duct Banks | 8177 | 144 | 0 | 200 | 0 | 1374 | 1374 | 200 | 600 | 0 | 600 |  |  |  | 2014-03-05 08:00 | 2014-04-02 17:00 |  | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 |  | PT_Normal |  |  |  |  | iw3wIiP/RXyM7PnI+CxFpA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34010 | N | N | 30 | ELECTRICAL LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 687 | LABOR - CIVIL
%R | 502955 | 6359 | 125061 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2ELGL5220 | Laying of electrical cables | 8178 | 168 | 0 | 200 | 0 | 1834.8 | 1834.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-12 17:00 |  | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 |  | PT_Normal |  |  |  |  | mPrFHRw8SCyqX306+eXpwg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34010 | N | N | 30 | ELECTRICAL LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 917.4 | LABOR- SUBCONTRACTOR
%R | 502956 | 6359 | 125061 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2ELGL5225 | Backfilling Electrical trench | 8177 | 168 | 0 | 200 | 0 | 862 | 862 | 200 | 550 | 0 | 550 |  |  |  | 2014-03-23 08:00 | 2014-04-20 17:00 |  | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | St30XFU4R0yTOmv04bgfrA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34010 | N | N | 30 | ELECTRICAL LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 431 | LABOR - CIVIL
%R | 502957 | 6359 | 125061 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2ELGL5230 | Construction of Submain Board & Feeder Pillar | 8165 | 760 | 0 | 200 | 0 | 224 | 224 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-27 17:00 |  | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | Au1SctcyQhiIzJWc0TxJbA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34010 | N | N | 30 | ELECTRICAL LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 224 | STEEL FIXERS SK
%R | 502958 | 6359 | 125062 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2SLGL7200 | Excavation | 8177 | 376 | 0 | 200 | 0 | 497 | 497 | 200 | 251 | 0 | 251 |  |  |  | 2014-07-10 08:00 | 2014-08-11 17:00 |  | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-07-10 08:00 | 2014-08-11 17:00 |  | PT_Normal |  |  |  |  | cE7UmIpaSCCGeFAAB97/LA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34090 | N | N | 70 | SOFT LANDSCAPING |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 497 | LABOR - CIVIL
%R | 502959 | 6359 | 125062 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2SLGL7205 | Sweet Soil Laying | 8178 | 376 | 0 | 200 | 0 | 2380 | 2380 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-22 08:00 | 2014-08-23 17:00 |  | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-07-22 08:00 | 2014-08-23 17:00 |  | PT_Normal |  |  |  |  | pwiAa3B9QjajPcWW4lTiuw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34090 | N | N | 70 | SOFT LANDSCAPING |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 2380 | LABOR- SUBCONTRACTOR
%R | 502960 | 6359 | 125062 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2SLGL7210 | Plantation works | 8178 | 616 | 144 | 200 | 0 | 588 | 588 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-10-08 17:00 |  | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-09-10 08:00 | 2014-10-08 17:00 |  | PT_Normal |  |  |  |  | 8R3WuCWNRzKkFcq02XOYYQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34090 | N | N | 70 | SOFT LANDSCAPING |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 588 | LABOR- SUBCONTRACTOR
%R | 502961 | 6359 | 125063 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2TCGL5295 | Excavation Telecommunication trenches | 8177 | 144 | 0 | 160 | 0 | 528 | 528 | 160 | 300 | 0 | 300 |  |  |  | 2014-03-29 08:00 | 2014-04-20 17:00 |  | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 | 2014-03-29 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | I3Pdsn5RSDmuSca/wPzMug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34040 | N | N | 45 | TELECOMMUNICATION LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 528 | LABOR - CIVIL
%R | 502962 | 6359 | 125063 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2TCGL5300 | Laying of cables | 8178 | 144 | 0 | 160 | 0 | 795.2 | 795.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-03 08:00 | 2014-04-26 17:00 |  | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-04-03 08:00 | 2014-04-26 17:00 |  | PT_Normal |  |  |  |  | QDIv35hSQF+qVlf+K+tcuA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34040 | N | N | 45 | TELECOMMUNICATION LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 795.2 | LABOR- SUBCONTRACTOR
%R | 502963 | 6359 | 125063 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2TCGL5305 | Backfilling telecommunication trench | 8177 | 144 | 0 | 160 | 0 | 530 | 530 | 160 | 440 | 0 | 440 |  |  |  | 2014-04-09 08:00 | 2014-05-01 17:00 |  | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-04-09 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | 7SqPqYSrQa65h4DGG+AJmA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34040 | N | N | 45 | TELECOMMUNICATION LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 530 | LABOR - CIVIL
%R | 502964 | 6359 | 125063 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2TCGL5310 | Connection & Installation | 8178 | 776 | 184 | 160 | 0 | 344.4 | 344.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-22 08:00 | 2014-08-17 17:00 |  | 2014-03-31 08:00 | 2014-04-22 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 | 2014-07-22 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | mlAxpPu9QVKPob2tNpcVqg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34040 | N | N | 45 | TELECOMMUNICATION LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 344.4 | LABOR- SUBCONTRACTOR
%R | 502965 | 6359 | 125064 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2IRGL5265 | Excavation for irrigation line | 8177 | 344 | 0 | 200 | 0 | 812 | 812 | 200 | 500 | 0 | 500 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | Y20f/QVvTe+QjfNhNtwsHA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34030 | N | N | 40 | IRRIGATION LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 812 | LABOR - CIVIL
%R | 502966 | 6359 | 125064 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2IRGL5270 | Laying of irrigationline | 8178 | 344 | 0 | 200 | 0 | 386.4 | 386.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-22 08:00 | 2014-06-19 17:00 |  | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 |  | PT_Normal |  |  |  |  | /fyUKBonQDmyOCOWBHRgCw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34030 | N | N | 40 | IRRIGATION LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 386.4 | LABOR- SUBCONTRACTOR
%R | 502967 | 6359 | 125064 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2IRGL5275 | Testing of irrigation line | 8178 | 344 | 0 | 200 | 0 | 319.2 | 319.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-25 17:00 |  | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | y6wativDSgGg2hVl9Pokmw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34030 | N | N | 40 | IRRIGATION LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 319.2 | LABOR- SUBCONTRACTOR
%R | 502968 | 6359 | 125064 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2IRGL5280 | Backfilling irrigation line | 8177 | 344 | 0 | 200 | 0 | 676 | 676 | 200 | 550 | 0 | 550 |  |  |  | 2014-06-03 08:00 | 2014-07-01 17:00 |  | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-06-03 08:00 | 2014-07-01 17:00 |  | PT_Normal |  |  |  |  | ofLYti+JQbOauNtP1QDM3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34030 | N | N | 40 | IRRIGATION LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 676 | LABOR - CIVIL
%R | 502969 | 6359 | 125064 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2IRGL5285 | Construction of Thrust Blocks,Pull boxes | 8178 | 464 | 0 | 200 | 0 | 116.4 | 116.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-02 08:00 | 2014-07-30 17:00 |  | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-07-02 08:00 | 2014-07-30 17:00 |  | PT_Normal |  |  |  |  | qduOCPYPRBaVt3MF3JvhEQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34030 | N | N | 40 | IRRIGATION LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 116.4 | LABOR- SUBCONTRACTOR
%R | 502970 | 6359 | 125064 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2IRGL5290 | Irrigation Fittings (Nozzle,Values) | 8178 | 464 | 88 | 200 | 0 | 285.6 | 285.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-10 08:00 | 2014-08-11 17:00 |  | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-07-10 08:00 | 2014-08-11 17:00 |  | PT_Normal |  |  |  |  | cVthYI0YQv++pwNXEeLMIw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34030 | N | N | 40 | IRRIGATION LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 285.6 | LABOR- SUBCONTRACTOR
%R | 502971 | 6359 | 125065 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2HDGL7020 | Precast Concrete Kerbs works | 8173 | 376 | 0 | 160 | 0 | 1178 | 1178 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-06-28 17:00 |  | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 | 2014-06-05 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | S1UNjrJ6T/66BJRc46mn4g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34080 | N | N | 65 | HARD LANDSCAPING |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1178 | KERBSTONE MASON SK
%R | 502972 | 6359 | 125065 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2HDGL7025 | Interlocking for Walkways | 8174 | 376 | 0 | 200 | 0 | 806 | 806 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | d3/iRwReQk6EygLl+2/Ufw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34080 | N | N | 65 | HARD LANDSCAPING |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 806 | INTERLOCK MASON SK
%R | 502973 | 6359 | 125065 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2HDGL7030 | Construction of Retaining wall | 8165 | 376 | 0 | 200 | 0 | 756 | 756 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-27 17:00 |  | 2014-05-05 08:00 | 2014-06-02 17:00 | 2014-05-05 08:00 | 2014-06-02 17:00 | 2014-05-05 08:00 | 2014-06-02 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | dE/2SWviQqy8uYVZUN+OEQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34080 | N | N | 65 | HARD LANDSCAPING |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 756 | STEEL FIXERS SK
%R | 502974 | 6359 | 125065 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2HDGL7035 | Construction of Wash Stone Boulders | 8170 | 376 | 0 | 200 | 0 | 88 | 88 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-27 17:00 |  | 2014-05-05 08:00 | 2014-06-02 17:00 | 2014-05-05 08:00 | 2014-06-02 17:00 | 2014-05-05 08:00 | 2014-06-02 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | SwQ6K3cbTZGOmHZ7kFlQlg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34080 | N | N | 65 | HARD LANDSCAPING |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 88 | TILE MASON SK
%R | 502975 | 6359 | 125065 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2HDGL7040 | Construction of Speed Humps | 8167 | 776 | 184 | 160 | 0 | 14 | 14 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-09 17:00 |  | 2014-06-21 08:00 | 2014-07-13 17:00 | 2014-06-21 08:00 | 2014-07-13 17:00 | 2014-06-21 08:00 | 2014-07-13 17:00 | 2014-10-18 08:00 | 2014-11-09 17:00 |  | PT_Normal |  |  |  |  | ZKu2KTdvTjmxQRg1A49qrQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34080 | N | N | 65 | HARD LANDSCAPING |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 14 | CONCRETE MASON SK
%R | 502976 | 6359 | 125066 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2RWGL6000 | Excavation & Earth Filling | 8177 | 144 | 0 | 80 | 0 | 1232 | 1232 | 80 | 500 | 0 | 500 |  |  |  | 2014-05-03 08:00 | 2014-05-13 17:00 |  | 2014-04-12 08:00 | 2014-04-22 17:00 | 2014-04-12 08:00 | 2014-04-22 17:00 | 2014-04-12 08:00 | 2014-04-22 17:00 | 2014-05-03 08:00 | 2014-05-13 17:00 |  | PT_Normal |  |  |  |  | hJKB9/cHT0OkpiVRKuafAA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34060 | N | N | 55 | ROAD WORKS |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1232 | LABOR - CIVIL
%R | 502977 | 6359 | 125066 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2RWGL6005 | Laying of Sub Grade | 8178 | 144 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-14 08:00 | 2014-06-11 17:00 |  | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 |  | PT_Normal |  |  |  |  | 8AdM81uqRtOzWGAGsJ1Q7A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34060 | N | N | 55 | ROAD WORKS |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 24 | LABOR- SUBCONTRACTOR
%R | 502978 | 6359 | 125066 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2RWGL6010 | Laying of Precast Kerbs | 8178 | 144 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-26 08:00 | 2014-06-23 17:00 |  | 2014-05-05 08:00 | 2014-06-02 17:00 | 2014-05-05 08:00 | 2014-06-02 17:00 | 2014-05-05 08:00 | 2014-06-02 17:00 | 2014-05-26 08:00 | 2014-06-23 17:00 |  | PT_Normal |  |  |  |  | BVbJYQTmT1SgzxPwrWMO4A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34060 | N | N | 55 | ROAD WORKS |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 24 | LABOR- SUBCONTRACTOR
%R | 502979 | 6359 | 125066 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2RWGL6015 | Laying of Granular Sub Base Coarse | 8173 | 144 | 0 | 160 | 0 | 1814 | 1814 | 160 | 600 | 0 | 600 |  |  |  | 2014-06-07 08:00 | 2014-06-29 17:00 |  | 2014-05-17 08:00 | 2014-06-08 17:00 | 2014-05-17 08:00 | 2014-06-08 17:00 | 2014-05-17 08:00 | 2014-06-08 17:00 | 2014-06-07 08:00 | 2014-06-29 17:00 |  | PT_Normal |  |  |  |  | iGNGEjhvQ7CV2oBAb8ZzAg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34060 | N | N | 55 | ROAD WORKS |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1814 | KERBSTONE MASON SK
%R | 502980 | 6359 | 125066 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2RWGL6020 | Laying of Road Base Asphalt Concrete | 8178 | 504 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-08-25 08:00 | 2014-08-30 17:00 |  | 2014-06-09 08:00 | 2014-06-14 17:00 | 2014-06-09 08:00 | 2014-06-14 17:00 | 2014-06-09 08:00 | 2014-06-14 17:00 | 2014-08-25 08:00 | 2014-08-30 17:00 |  | PT_Normal |  |  |  |  | gawPy8c0TKmy2iWKeDqdWg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34060 | N | N | 55 | ROAD WORKS |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 174 | LABOR- SUBCONTRACTOR
%R | 502981 | 6359 | 125066 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2RWGL6025 | Laying of Asphalt Wearing Coarse | 8178 | 624 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-09-17 08:00 | 2014-09-22 17:00 |  | 2014-06-15 08:00 | 2014-06-19 17:00 | 2014-06-15 08:00 | 2014-06-19 17:00 | 2014-06-15 08:00 | 2014-06-19 17:00 | 2014-09-17 08:00 | 2014-09-22 17:00 |  | PT_Normal |  |  |  |  | 0hwwlv3IQfC28K6jkxSgLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34060 | N | N | 55 | ROAD WORKS |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 174 | LABOR- SUBCONTRACTOR
%R | 502982 | 6359 | 125066 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2RWGL6030 | Traffic Signage & Road Marking | 8178 | 624 | 120 | 40 | 0 | 974 | 974 | 40 | 0 | 0 | 0 |  |  |  | 2014-09-23 08:00 | 2014-09-28 17:00 |  | 2014-06-21 08:00 | 2014-06-25 17:00 | 2014-06-21 08:00 | 2014-06-25 17:00 | 2014-06-21 08:00 | 2014-06-25 17:00 | 2014-09-23 08:00 | 2014-09-28 17:00 |  | PT_Normal |  |  |  |  | ZDJpX9u2RWKoYrUHWA+ZKg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34060 | N | N | 55 | ROAD WORKS |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 974 | LABOR- SUBCONTRACTOR
%R | 502983 | 6359 | 125067 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2FFGL5185 | Excavation for firefighting line | 8177 | 96 | 0 | 200 | 0 | 283 | 283 | 200 | 151 | 0 | 151 |  |  |  | 2014-01-28 08:00 | 2014-02-26 17:00 |  | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 |  | PT_Normal |  |  |  |  | amNM8wyTQH6jYeKPlJ9vrQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34000 | N | N | 25 | FIREFIGHTING LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 283 | LABOR - CIVIL
%R | 502984 | 6359 | 125067 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2FFGL5190 | Laying of firefighting line | 8178 | 96 | 0 | 200 | 0 | 303.6 | 303.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-03-06 17:00 |  | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-02-05 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | lo0wgmA2Sq2nRFKUt2BtXw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34000 | N | N | 25 | FIREFIGHTING LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 303.6 | LABOR- SUBCONTRACTOR
%R | 502985 | 6359 | 125067 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2FFGL5195 | Testing of firefighting line | 8178 | 96 | 0 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-12 17:00 |  | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 |  | PT_Normal |  |  |  |  | Dr5JaBDHSPq3ksZeX16n0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34000 | N | N | 25 | FIREFIGHTING LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 84 | LABOR- SUBCONTRACTOR
%R | 502986 | 6359 | 125067 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2FFGL5200 | Backfilling firefighting line | 8177 | 96 | 0 | 200 | 0 | 329 | 329 | 200 | 275 | 0 | 275 |  |  |  | 2014-02-18 08:00 | 2014-03-18 17:00 |  | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | O53FEvYnTAK4jZcq/T/sNA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34000 | N | N | 25 | FIREFIGHTING LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 164.5 | LABOR - CIVIL
%R | 502987 | 6359 | 125067 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2FFGL5205 | Construction of valve chambers & Thrust Blocks | 8165 | 320 | 0 | 200 | 0 | 202 | 202 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-29 08:00 | 2014-04-26 17:00 |  | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 | 2014-03-29 08:00 | 2014-04-26 17:00 |  | PT_Normal |  |  |  |  | TKUoORnAQLunDvbzueqmZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34000 | N | N | 25 | FIREFIGHTING LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 101 | STEEL FIXERS SK
%R | 502988 | 6359 | 125067 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2FFGL5210 | Connection with existing Firewater System | 8178 | 320 | 144 | 200 | 0 | 134.4 | 134.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-03 08:00 | 2014-05-01 17:00 |  | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | 5J9CS50jTr26RXNQMBh+/Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34000 | N | N | 25 | FIREFIGHTING LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 502989 | 6359 | 125068 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2STGL5235 | Excavation for Street lighting | 8177 | 144 | 0 | 200 | 0 | 69 | 69 | 200 | 51 | 0 | 51 |  |  |  | 2014-03-05 08:00 | 2014-04-02 17:00 |  | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 |  | PT_Normal |  |  |  |  | C3meAyvUQBeVomqp4yKXqg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34020 | N | N | 35 | STREET LIGHTING |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 34.5 | LABOR - CIVIL
%R | 502990 | 6359 | 125068 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2STGL5240 | Construction of Duct Banks | 8178 | 144 | 0 | 200 | 0 | 1192.8 | 1192.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-04-08 17:00 |  | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34020 | N | N | 35 | STREET LIGHTING |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 596.4 | LABOR- SUBCONTRACTOR
%R | 502991 | 6359 | 125068 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2STGL5245 | Construction of Foundation | 8172 | 144 | 0 | 200 | 0 | 638 | 638 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-04-08 17:00 |  | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | BrVbyVyqSGCHyprNcrwITA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34020 | N | N | 35 | STREET LIGHTING |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 319 | MANHOLES SK
%R | 502992 | 6359 | 125068 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2STGL5250 | Backfilling Street Lighting | 8177 | 144 | 0 | 200 | 0 | 287 | 287 | 200 | 275 | 0 | 275 |  |  |  | 2014-03-17 08:00 | 2014-04-14 17:00 |  | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 |  | PT_Normal |  |  |  |  | 8nUqEPNaTbOm0qNQwy6KVw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34020 | N | N | 35 | STREET LIGHTING |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 143.5 | LABOR - CIVIL
%R | 502993 | 6359 | 125068 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2STGL5255 | Installation of light Post | 8178 | 744 | 72 | 200 | 0 | 216 | 216 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-27 17:00 |  | 2014-03-12 08:00 | 2014-04-09 17:00 | 2014-03-12 08:00 | 2014-04-09 17:00 | 2014-03-12 08:00 | 2014-04-09 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 |  | PT_Normal |  |  |  |  | RL2lzP4TTC2YCvm0IUfruQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34020 | N | N | 35 | STREET LIGHTING |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 216 | LABOR- SUBCONTRACTOR
%R | 502994 | 6359 | 125068 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2STGL5260 | Electrical Works | 8178 | 760 | 144 | 200 | 0 | 823.6 | 823.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-28 08:00 | 2014-08-28 17:00 |  | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-07-28 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | Fp2T653gRkCkbkEauIv8Ug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34020 | N | N | 35 | STREET LIGHTING |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 823.6 | LABOR- SUBCONTRACTOR
%R | 502995 | 6359 | 125069 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2BWGL5315 | Construction of Boundary Wall (Ht-3m) | 8165 | 592 | 0 | 200 | 0 | 224 | 224 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-02 08:00 | 2014-06-30 17:00 |  | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-06-02 08:00 | 2014-06-30 17:00 |  | PT_Normal |  |  |  |  | taHw75rgTTepPkfTEYJ1Pg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34050 | N | N | 50 | BOUNDARY WALL |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 224 | STEEL FIXERS SK
%R | 502996 | 6359 | 125069 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 8178 | 592 | 0 | 200 | 0 | 28 | 28 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-18 08:00 | 2014-07-16 17:00 |  | 2014-03-24 08:00 | 2014-04-21 17:00 | 2014-03-24 08:00 | 2014-04-21 17:00 | 2014-03-24 08:00 | 2014-04-21 17:00 | 2014-06-18 08:00 | 2014-07-16 17:00 |  | PT_Normal |  |  |  |  | Wgkb8LdPSPGfdeKPl0KtbQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34050 | N | N | 50 | BOUNDARY WALL |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 28 | LABOR- SUBCONTRACTOR
%R | 502997 | 6359 | 125069 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 8165 | 592 | 0 | 200 | 0 | 168 | 168 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-17 08:00 | 2014-08-18 17:00 |  | 2014-04-22 08:00 | 2014-05-20 17:00 | 2014-04-22 08:00 | 2014-05-20 17:00 | 2014-04-22 08:00 | 2014-05-20 17:00 | 2014-07-17 08:00 | 2014-08-18 17:00 |  | PT_Normal |  |  |  |  | q8jTtcplQTuFusVZFdhDmw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34050 | N | N | 50 | BOUNDARY WALL |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 168 | STEEL FIXERS SK
%R | 502998 | 6359 | 125069 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 8165 | 592 | 88 | 200 | 0 | 154 | 154 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-29 08:00 | 2014-08-30 17:00 |  | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-07-29 08:00 | 2014-08-30 17:00 |  | PT_Normal |  |  |  |  | ebv4YSn0Sp2MyULhb2V/UA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34050 | N | N | 50 | BOUNDARY WALL |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 154 | STEEL FIXERS SK
%R | 502999 | 6359 | 125070 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2WSGL5180 | Installation of meter ,Accessories & Connection | 8178 | 376 | 56 | 160 | 0 | 50.4 | 50.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-09 08:00 | 2014-05-01 17:00 |  | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 | 2014-04-09 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | BEa8C6miSDKpgcB9kzAoXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33990 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 503000 | 6359 | 125070 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2WSGL5160 | Laying of water line | 8178 | 96 | 0 | 200 | 0 | 285.6 | 285.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-11 08:00 | 2014-02-08 17:00 |  | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 |  | PT_Normal |  |  |  |  | z/aNvY42SV+fpu/czUBQyQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33990 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 285.6 | LABOR- SUBCONTRACTOR
%R | 503001 | 6359 | 125070 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2WSGL5155 | Excavation for water line | 8177 | 96 | 0 | 200 | 0 | 401 | 401 | 200 | 251 | 0 | 251 |  |  |  | 2014-01-05 08:00 | 2014-02-02 17:00 |  | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | CpX987nwQGOfoeW6gc2nVw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33990 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 401 | LABOR - CIVIL
%R | 503002 | 6359 | 125070 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2WSGL5165 | Testing of potable water line | 8178 | 96 | 0 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-02-15 17:00 |  | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 |  | PT_Normal |  |  |  |  | DUyPE4GEQbezump8Dzqg2w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33990 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 84 | LABOR- SUBCONTRACTOR
%R | 503003 | 6359 | 125070 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2WSGL5170 | Backfilling potable water line | 8177 | 96 | 0 | 200 | 0 | 335 | 335 | 200 | 275 | 0 | 275 |  |  |  | 2014-01-22 08:00 | 2014-02-20 17:00 |  | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | Z9kGdiDXTKC36hQPwbSuXw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33990 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 335 | LABOR - CIVIL
%R | 503004 | 6359 | 125070 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2WSGL5175 | Construction of valve chambers & Thrust Blocks | 8172 | 376 | 0 | 200 | 0 | 132 | 132 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-04-08 17:00 |  | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | 4chaqxNiS1ydYjM5gyUNMA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33990 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 132 | MANHOLES SK
%R | 503005 | 6359 | 125071 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2DRGL5125 | Testing of Drainage line | 8178 | 72 | 0 | 200 | 0 | 134.4 | 134.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-02 08:00 | 2013-12-31 17:00 |  | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 |  | PT_Normal |  |  |  |  | zB4NTv8/QY6ScgQ8FYR0zw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33970 | N | N | 10 | DRAINAGE LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11; period 2: 2013-AP12 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 503006 | 6359 | 125071 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2DRGL5130 | Backfilling Drainage line | 8177 | 72 | 0 | 120 | 0 | 402 | 402 | 120 | 330 | 0 | 330 |  |  |  | 2013-12-21 08:00 | 2014-01-06 17:00 |  | 2013-12-09 08:00 | 2013-12-26 17:00 | 2013-12-09 08:00 | 2013-12-26 17:00 | 2013-12-09 08:00 | 2013-12-26 17:00 | 2013-12-21 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | NWFXiuupTdCfAXd6uLFoHg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33970 | N | N | 10 | DRAINAGE LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 402 | LABOR - CIVIL
%R | 503007 | 6359 | 125071 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2DRGL5115 | Excavation for Drainage line | 8177 | 72 | 0 | 200 | 0 | 431 | 431 | 200 | 251 | 0 | 251 |  |  |  | 2013-11-17 08:00 | 2013-12-15 17:00 |  | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-11-17 08:00 | 2013-12-15 17:00 |  | PT_Normal |  |  |  |  | zOTr2q1UT7mkUNxmR1IlfA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33970 | N | N | 10 | DRAINAGE LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 431 | LABOR - CIVIL
%R | 503008 | 6359 | 125071 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2DRGL5120 | Laying of Drainage line | 8178 | 72 | 0 | 200 | 0 | 276 | 276 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-24 08:00 | 2013-12-23 17:00 |  | 2013-11-13 08:00 | 2013-12-11 17:00 | 2013-11-13 08:00 | 2013-12-11 17:00 | 2013-11-13 08:00 | 2013-12-11 17:00 | 2013-11-24 08:00 | 2013-12-23 17:00 |  | PT_Normal |  |  |  |  | w/4ymFGwQIu1o3MPwR4urA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33970 | N | N | 10 | DRAINAGE LINES |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 276 | LABOR- SUBCONTRACTOR
%R | 503009 | 6359 | 125072 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2SAGL5135 | Construction of manholes Drainage | 8177 | 616 | 144 | 200 | 0 | 6 | 6 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-04-08 17:00 |  | 2013-12-09 08:00 | 2014-01-07 17:00 | 2013-12-09 08:00 | 2014-01-07 17:00 | 2013-12-09 08:00 | 2014-01-07 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | qukPaSemSBK2wLOXcGi1Rw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33980 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 6 | LABOR - CIVIL
%R | 503010 | 6359 | 125072 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2SAGL5140 | Construction of soakaways | 8172 | 112 | 0 | 200 | 0 | 154 | 154 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-24 08:00 | 2014-01-21 17:00 |  | 2013-12-07 08:00 | 2014-01-05 17:00 | 2013-12-07 08:00 | 2014-01-05 17:00 | 2013-12-07 08:00 | 2014-01-05 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 |  | PT_Normal |  |  |  |  | pG/ByaG9T4SkUCBdEypOBA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33980 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 154 | MANHOLES SK
%R | 503011 | 6359 | 125072 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2SAGL5145 | Construction of Road gullies | 8172 | 112 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-20 17:00 |  | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-06 08:00 | 2014-02-03 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | hJn4Vc7sS4OpPFfYn1FPFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33980 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 176 | MANHOLES SK
%R | 503012 | 6359 | 125072 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2SAGL5150 | Connection with existing sewer manhole | 8177 | 432 | 288 | 160 | 0 | 6 | 6 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-09 08:00 | 2014-05-01 17:00 |  | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-02-04 08:00 | 2014-02-27 17:00 | 2014-04-09 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | gupmH9z1SIedQ+ip7XKgFQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33980 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 6 | LABOR - CIVIL
%R | 503013 | 6359 | 125073 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2PSGL7015 | Electrical Works-Parking Shed | 8178 | 504 | 144 | 200 | 0 | 51.6 | 51.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-06 08:00 | 2014-10-04 17:00 |  | 2014-06-21 08:00 | 2014-07-19 17:00 | 2014-06-21 08:00 | 2014-07-19 17:00 | 2014-06-21 08:00 | 2014-07-19 17:00 | 2014-09-06 08:00 | 2014-10-04 17:00 |  | PT_Normal |  |  |  |  | 6JSYC7HkRdqDEB1blDjOhg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34070 | N | N | 60 | PARKING SHED |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 51.6 | LABOR- SUBCONTRACTOR
%R | 503014 | 6359 | 125073 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2PSGL7000 | Excavation | 8177 | 544 | 40 | 120 | 0 | 148 | 148 | 120 | 76 | 0 | 76 |  |  |  | 2014-08-13 08:00 | 2014-08-30 17:00 |  | 2014-05-22 08:00 | 2014-06-08 17:00 | 2014-05-22 08:00 | 2014-06-08 17:00 | 2014-05-22 08:00 | 2014-06-08 17:00 | 2014-08-13 08:00 | 2014-08-30 17:00 |  | PT_Normal |  |  |  |  | aCQ/kle0TuOKlNdc4MnXzw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34070 | N | N | 60 | PARKING SHED |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 148 | LABOR - CIVIL
%R | 503015 | 6359 | 125073 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2PSGL7005 | Foundation casting | 8165 | 504 | 0 | 120 | 0 | 252 | 252 | 120 | 0 | 0 | 0 |  |  |  | 2014-08-19 08:00 | 2014-09-04 17:00 |  | 2014-06-03 08:00 | 2014-06-19 17:00 | 2014-06-03 08:00 | 2014-06-19 17:00 | 2014-06-03 08:00 | 2014-06-19 17:00 | 2014-08-19 08:00 | 2014-09-04 17:00 |  | PT_Normal |  |  |  |  | YDBQsA2USiucnmbR8hzX4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34070 | N | N | 60 | PARKING SHED |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 252 | STEEL FIXERS SK
%R | 503016 | 6359 | 125073 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ2PSGL7010 | Column, Frame& Fabrics Erection | 8178 | 504 | 0 | 200 | 0 | 286 | 286 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-31 08:00 | 2014-09-28 17:00 |  | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-08-31 08:00 | 2014-09-28 17:00 |  | PT_Normal |  |  |  |  | 992k2qvMR9KvR5p2Hfgr3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34070 | N | N | 60 | PARKING SHED |  | 125060 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 286 | LABOR- SUBCONTRACTOR
%R | 503017 | 6359 | 125076 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5STGL5235 | Excavation for Street lighting | 8177 | 72 | 0 | 200 | 0 | 69 | 69 | 200 | 51 | 0 | 51 |  |  |  | 2014-07-23 08:00 | 2014-08-24 17:00 |  | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-23 08:00 | 2014-08-24 17:00 |  | PT_Normal |  |  |  |  | PXrNauWoTnOFKY9ktpHh8w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34470 | N | N | 35 | STREET LIGHTING |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 34.5 | LABOR - CIVIL
%R | 503018 | 6359 | 125076 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5STGL5240 | Construction of Duct Banks | 8178 | 72 | 0 | 200 | 0 | 1192.8 | 1192.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-29 08:00 | 2014-08-30 17:00 |  | 2014-07-19 08:00 | 2014-08-19 17:00 | 2014-07-19 08:00 | 2014-08-19 17:00 | 2014-07-19 08:00 | 2014-08-19 17:00 | 2014-07-29 08:00 | 2014-08-30 17:00 |  | PT_Normal |  |  |  |  | T6TgmZhhRsGvR+GPAmTg9w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34470 | N | N | 35 | STREET LIGHTING |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 596.4 | LABOR- SUBCONTRACTOR
%R | 503019 | 6359 | 125076 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5STGL5245 | Construction of Foundation | 8172 | 72 | 0 | 200 | 0 | 638 | 638 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-29 08:00 | 2014-08-30 17:00 |  | 2014-07-19 08:00 | 2014-08-19 17:00 | 2014-07-19 08:00 | 2014-08-19 17:00 | 2014-07-19 08:00 | 2014-08-19 17:00 | 2014-07-29 08:00 | 2014-08-30 17:00 |  | PT_Normal |  |  |  |  | AKKICfYvSzqjZ5qsQg8g2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34470 | N | N | 35 | STREET LIGHTING |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 319 | MANHOLES SK
%R | 503020 | 6359 | 125076 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5STGL5250 | Backfilling Street Lighting | 8177 | 72 | 0 | 200 | 0 | 287 | 287 | 200 | 275 | 0 | 275 |  |  |  | 2014-08-07 08:00 | 2014-09-04 17:00 |  | 2014-07-24 08:00 | 2014-08-25 17:00 | 2014-07-24 08:00 | 2014-08-25 17:00 | 2014-07-24 08:00 | 2014-08-25 17:00 | 2014-08-07 08:00 | 2014-09-04 17:00 |  | PT_Normal |  |  |  |  | c0IzOoBrT+CRty0rFR1gUw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34470 | N | N | 35 | STREET LIGHTING |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 143.5 | LABOR - CIVIL
%R | 503021 | 6359 | 125076 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5STGL5255 | Installation of light Post | 8178 | 464 | 136 | 200 | 0 | 216 | 216 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-08-09 08:00 | 2014-09-06 17:00 | 2014-08-09 08:00 | 2014-09-06 17:00 | 2014-08-09 08:00 | 2014-09-06 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | VN6JpKnWRzyZc7wLbnepRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34470 | N | N | 35 | STREET LIGHTING |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 216 | LABOR- SUBCONTRACTOR
%R | 503022 | 6359 | 125076 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5STGL5260 | Electrical Works | 8178 | 328 | 184 | 200 | 0 | 823.6 | 823.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-29 08:00 | 2014-11-26 17:00 |  | 2014-09-09 08:00 | 2014-10-07 17:00 | 2014-09-09 08:00 | 2014-10-07 17:00 | 2014-09-09 08:00 | 2014-10-07 17:00 | 2014-10-29 08:00 | 2014-11-26 17:00 |  | PT_Normal |  |  |  |  | VKaePwCHTcuzsL9MiGeYGg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34470 | N | N | 35 | STREET LIGHTING |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 823.6 | LABOR- SUBCONTRACTOR
%R | 503023 | 6359 | 125077 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5SLGL7205 | Sweet Soil Laying | 8178 | 184 | 0 | 200 | 0 | 2380 | 2380 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-27 08:00 | 2014-12-27 17:00 |  | 2014-11-01 08:00 | 2014-11-29 17:00 | 2014-11-01 08:00 | 2014-11-29 17:00 | 2014-11-01 08:00 | 2014-11-29 17:00 | 2014-11-27 08:00 | 2014-12-27 17:00 |  | PT_Normal |  |  |  |  | 7bLmSeLwTsyt2wD48DfyMg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34540 | N | N | 70 | SOFT LANDSCAPING |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 2380 | LABOR- SUBCONTRACTOR
%R | 503024 | 6359 | 125077 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5SLGL7210 | Plantation works | 8178 | 184 | 184 | 200 | 0 | 588 | 588 | 200 | 0 | 0 | 0 |  |  |  | 2014-12-09 08:00 | 2015-01-07 17:00 |  | 2014-11-12 08:00 | 2014-12-10 17:00 | 2014-11-12 08:00 | 2014-12-10 17:00 | 2014-11-12 08:00 | 2014-12-10 17:00 | 2014-12-09 08:00 | 2015-01-07 17:00 |  | PT_Normal |  |  |  |  | DxGItTZxTuyu9PpyXAzZLw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34540 | N | N | 70 | SOFT LANDSCAPING |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 588 | LABOR- SUBCONTRACTOR
%R | 503025 | 6359 | 125077 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5SLGL7200 | Excavation for Landscaping | 8177 | 184 | 0 | 200 | 0 | 497 | 497 | 200 | 251 | 0 | 251 |  |  |  | 2014-11-16 08:00 | 2014-12-14 17:00 |  | 2014-10-20 08:00 | 2014-11-17 17:00 | 2014-10-20 08:00 | 2014-11-17 17:00 | 2014-10-20 08:00 | 2014-11-17 17:00 | 2014-11-16 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | M3zJMBZ2T7Ku5vOY2AsO5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34540 | N | N | 70 | SOFT LANDSCAPING |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 497 | LABOR - CIVIL
%R | 503026 | 6359 | 125078 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5ELGL5215 | Excavation Cable Trenches & Duct Banks | 8177 | 72 | 0 | 200 | 0 | 1374 | 1374 | 200 | 600 | 0 | 600 |  |  |  | 2014-07-23 08:00 | 2014-08-24 17:00 |  | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-13 08:00 | 2014-08-13 17:00 | 2014-07-23 08:00 | 2014-08-24 17:00 |  | PT_Normal |  |  |  |  | GVS/1lojTWuSduJ3xGgm6g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34460 | N | N | 30 | ELECTRICAL LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 687 | LABOR - CIVIL
%R | 503027 | 6359 | 125078 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5ELGL5220 | Laying of electrical cables | 8178 | 176 | 0 | 200 | 0 | 1834.8 | 1834.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-17 08:00 | 2014-09-14 17:00 |  | 2014-07-19 08:00 | 2014-08-19 17:00 | 2014-07-19 08:00 | 2014-08-19 17:00 | 2014-07-19 08:00 | 2014-08-19 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 |  | PT_Normal |  |  |  |  | QeexUGijR+Wht7BIJZlC9Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34460 | N | N | 30 | ELECTRICAL LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 917.4 | LABOR- SUBCONTRACTOR
%R | 503028 | 6359 | 125078 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5ELGL5225 | Backfilling Electrical trench | 8177 | 176 | 0 | 200 | 0 | 862 | 862 | 200 | 550 | 0 | 550 |  |  |  | 2014-08-25 08:00 | 2014-09-22 17:00 |  | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-07-27 08:00 | 2014-08-27 17:00 | 2014-08-25 08:00 | 2014-09-22 17:00 |  | PT_Normal |  |  |  |  | nDvBtnChQlu0ypS6JVrPow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34460 | N | N | 30 | ELECTRICAL LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 431 | LABOR - CIVIL
%R | 503029 | 6359 | 125078 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5ELGL5230 | Construction of Submain Board & Feeder Pillar | 8165 | 328 | 0 | 200 | 0 | 224 | 224 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-28 08:00 | 2014-10-28 17:00 |  | 2014-08-11 08:00 | 2014-09-08 17:00 | 2014-08-11 08:00 | 2014-09-08 17:00 | 2014-08-11 08:00 | 2014-09-08 17:00 | 2014-09-28 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | b5HXNqcZTIycvKy7rRBX4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34460 | N | N | 30 | ELECTRICAL LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 224 | STEEL FIXERS SK
%R | 503030 | 6359 | 125079 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5BWGL5315 | Construction of Boundary Wall (Ht-3m) | 8165 | 272 | 0 | 200 | 0 | 224 | 224 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-17 08:00 | 2014-10-18 17:00 |  | 2014-08-09 08:00 | 2014-09-06 17:00 | 2014-08-09 08:00 | 2014-09-06 17:00 | 2014-08-09 08:00 | 2014-09-06 17:00 | 2014-09-17 08:00 | 2014-10-18 17:00 |  | PT_Normal |  |  |  |  | s9f4oT5+Sp+Z8Q3ZxizrFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34500 | N | N | 50 | BOUNDARY WALL |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 224 | STEEL FIXERS SK
%R | 503031 | 6359 | 125079 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 8178 | 272 | 0 | 200 | 0 | 28 | 28 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-04 08:00 | 2014-11-03 17:00 |  | 2014-08-25 08:00 | 2014-09-22 17:00 | 2014-08-25 08:00 | 2014-09-22 17:00 | 2014-08-25 08:00 | 2014-09-22 17:00 | 2014-10-04 08:00 | 2014-11-03 17:00 |  | PT_Normal |  |  |  |  | vOjy6duEQnGRCy9g8fykHw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34500 | N | N | 50 | BOUNDARY WALL |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 28 | LABOR- SUBCONTRACTOR
%R | 503032 | 6359 | 125079 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 8165 | 272 | 0 | 200 | 0 | 168 | 168 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-04 08:00 | 2014-12-02 17:00 |  | 2014-09-23 08:00 | 2014-10-23 17:00 | 2014-09-23 08:00 | 2014-10-23 17:00 | 2014-09-23 08:00 | 2014-10-23 17:00 | 2014-11-04 08:00 | 2014-12-02 17:00 |  | PT_Normal |  |  |  |  | pUWaxAJtSIe/Vr07fjQMbg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34500 | N | N | 50 | BOUNDARY WALL |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 84 | STEEL FIXERS SK
%R | 503033 | 6359 | 125079 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 8165 | 360 | 280 | 200 | 0 | 154 | 154 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-29 08:00 | 2014-12-28 17:00 |  | 2014-10-05 08:00 | 2014-11-04 17:00 | 2014-10-05 08:00 | 2014-11-04 17:00 | 2014-10-05 08:00 | 2014-11-04 17:00 | 2014-11-29 08:00 | 2014-12-28 17:00 |  | PT_Normal |  |  |  |  | W4D0pAR+QdybSgmlmsjdMQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34500 | N | N | 50 | BOUNDARY WALL |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 154 | STEEL FIXERS SK
%R | 503034 | 6359 | 125080 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5SAGL5135 | Construction of manholes Drainage | 8177 | 544 | 184 | 200 | 0 | 6 | 6 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-29 08:00 | 2014-08-30 17:00 |  | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 | 2014-07-29 08:00 | 2014-08-30 17:00 |  | PT_Normal |  |  |  |  | s7QC8+fsTka4OGR/Vqt7gg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34430 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 6 | LABOR - CIVIL
%R | 503035 | 6359 | 125080 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5SAGL5140 | Construction of soakaways | 8172 | 88 | 0 | 200 | 0 | 154 | 154 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-21 08:00 | 2014-06-18 17:00 |  | 2014-05-08 08:00 | 2014-06-05 17:00 | 2014-05-08 08:00 | 2014-06-05 17:00 | 2014-05-08 08:00 | 2014-06-05 17:00 | 2014-05-21 08:00 | 2014-06-18 17:00 |  | PT_Normal |  |  |  |  | +381IWZ+R8O9axdEViZ9yg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34430 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 154 | MANHOLES SK
%R | 503036 | 6359 | 125080 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5SAGL5145 | Construction of Road gullies | 8172 | 88 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-19 08:00 | 2014-07-17 17:00 |  | 2014-06-07 08:00 | 2014-07-05 17:00 | 2014-06-07 08:00 | 2014-07-05 17:00 | 2014-06-07 08:00 | 2014-07-05 17:00 | 2014-06-19 08:00 | 2014-07-17 17:00 |  | PT_Normal |  |  |  |  | 4CCX9q8/RCmRl72TMkI3kg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34430 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 176 | MANHOLES SK
%R | 503037 | 6359 | 125080 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5SAGL5150 | Connection with existing sewer manhole | 8177 | 360 | 288 | 160 | 0 | 6 | 6 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-31 08:00 | 2014-09-22 17:00 |  | 2014-07-06 08:00 | 2014-07-28 17:00 | 2014-07-06 08:00 | 2014-07-28 17:00 | 2014-07-06 08:00 | 2014-07-28 17:00 | 2014-08-31 08:00 | 2014-09-22 17:00 |  | PT_Normal |  |  |  |  | LLmG+euBRQSLc1fzI3qpeQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34430 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 6 | LABOR - CIVIL
%R | 503038 | 6359 | 125081 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5RWGL6000 | Excavation & Earth Filling | 8177 | 72 | 0 | 80 | 0 | 1232 | 1232 | 80 | 500 | 0 | 500 |  |  |  | 2014-09-23 08:00 | 2014-10-04 17:00 |  | 2014-09-13 08:00 | 2014-09-23 17:00 | 2014-09-13 08:00 | 2014-09-23 17:00 | 2014-09-13 08:00 | 2014-09-23 17:00 | 2014-09-23 08:00 | 2014-10-04 17:00 |  | PT_Normal |  |  |  |  | q4A+FByFRP2gyl0vlNFo2w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34510 | N | N | 55 | ROAD WORKS |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 1232 | LABOR - CIVIL
%R | 503039 | 6359 | 125081 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5RWGL6005 | Laying of Sub Grade | 8178 | 72 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-05 08:00 | 2014-11-04 17:00 |  | 2014-09-24 08:00 | 2014-10-25 17:00 | 2014-09-24 08:00 | 2014-10-25 17:00 | 2014-09-24 08:00 | 2014-10-25 17:00 | 2014-10-05 08:00 | 2014-11-04 17:00 |  | PT_Normal |  |  |  |  | mvyoG2KuS2y6Xd4mYqFcmw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34510 | N | N | 55 | ROAD WORKS |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 12 | LABOR- SUBCONTRACTOR
%R | 503040 | 6359 | 125081 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5RWGL6015 | Laying of Granular Sub Base Coarse | 8173 | 72 | 0 | 160 | 0 | 1814 | 1814 | 160 | 600 | 0 | 600 |  |  |  | 2014-10-29 08:00 | 2014-11-20 17:00 |  | 2014-10-19 08:00 | 2014-11-10 17:00 | 2014-10-19 08:00 | 2014-11-10 17:00 | 2014-10-19 08:00 | 2014-11-10 17:00 | 2014-10-29 08:00 | 2014-11-20 17:00 |  | PT_Normal |  |  |  |  | 5pQfwkeBTQWLIR5zZYeJvg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34510 | N | N | 55 | ROAD WORKS |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 1814 | KERBSTONE MASON SK
%R | 503041 | 6359 | 125081 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5RWGL6020 | Laying of Road Base Asphalt Concrete | 8178 | 72 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-11-22 08:00 | 2014-11-26 17:00 |  | 2014-11-11 08:00 | 2014-11-16 17:00 | 2014-11-11 08:00 | 2014-11-16 17:00 | 2014-11-11 08:00 | 2014-11-16 17:00 | 2014-11-22 08:00 | 2014-11-26 17:00 |  | PT_Normal |  |  |  |  | WEb4rxVASy2HcJwFzFa9xg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34510 | N | N | 55 | ROAD WORKS |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 174 | LABOR- SUBCONTRACTOR
%R | 503042 | 6359 | 125081 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5RWGL6025 | Laying of Asphalt Wearing Coarse | 8178 | 72 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-11-27 08:00 | 2014-12-02 17:00 |  | 2014-11-17 08:00 | 2014-11-22 17:00 | 2014-11-17 08:00 | 2014-11-22 17:00 | 2014-11-17 08:00 | 2014-11-22 17:00 | 2014-11-27 08:00 | 2014-12-02 17:00 |  | PT_Normal |  |  |  |  | hJJmIb1JSXu8uRtlHPWhJw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34510 | N | N | 55 | ROAD WORKS |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 174 | LABOR- SUBCONTRACTOR
%R | 503043 | 6359 | 125081 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5RWGL6030 | Traffic Signage & Road Marking | 8178 | 200 | 120 | 40 | 0 | 974 | 974 | 40 | 0 | 0 | 0 |  |  |  | 2014-12-23 08:00 | 2014-12-28 17:00 |  | 2014-11-23 08:00 | 2014-11-27 17:00 | 2014-11-23 08:00 | 2014-11-27 17:00 | 2014-11-23 08:00 | 2014-11-27 17:00 | 2014-12-23 08:00 | 2014-12-28 17:00 |  | PT_Normal |  |  |  |  | 3L1q3QMJQAWPtJOUszqJAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34510 | N | N | 55 | ROAD WORKS |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 974 | LABOR- SUBCONTRACTOR
%R | 503044 | 6359 | 125081 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5RWGL6010 | Laying of Precast Kerbs | 8178 | 72 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-19 08:00 | 2014-11-16 17:00 |  | 2014-10-06 08:00 | 2014-11-05 17:00 | 2014-10-06 08:00 | 2014-11-05 17:00 | 2014-10-06 08:00 | 2014-11-05 17:00 | 2014-10-19 08:00 | 2014-11-16 17:00 |  | PT_Normal |  |  |  |  | JLnyzHJRTDOFpttHHtO+vw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34510 | N | N | 55 | ROAD WORKS |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 24 | LABOR- SUBCONTRACTOR
%R | 503045 | 6359 | 125082 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5TCGL5295 | Excavation Telecommunication trenches | 8177 | 72 | 0 | 160 | 0 | 528 | 528 | 160 | 300 | 0 | 300 |  |  |  | 2014-08-19 08:00 | 2014-09-10 17:00 |  | 2014-08-09 08:00 | 2014-08-31 17:00 | 2014-08-09 08:00 | 2014-08-31 17:00 | 2014-08-09 08:00 | 2014-08-31 17:00 | 2014-08-19 08:00 | 2014-09-10 17:00 |  | PT_Normal |  |  |  |  | 3MhNs/pmR7+vZnjpWaqM8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34490 | N | N | 45 | TELECOMMUNICATION LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 528 | LABOR - CIVIL
%R | 503046 | 6359 | 125082 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5TCGL5300 | Laying of cables | 8178 | 72 | 0 | 160 | 0 | 795.2 | 795.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-25 08:00 | 2014-09-16 17:00 |  | 2014-08-14 08:00 | 2014-09-06 17:00 | 2014-08-14 08:00 | 2014-09-06 17:00 | 2014-08-14 08:00 | 2014-09-06 17:00 | 2014-08-25 08:00 | 2014-09-16 17:00 |  | PT_Normal |  |  |  |  | VvUl7W/2Rs2HRVEZREg4zw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34490 | N | N | 45 | TELECOMMUNICATION LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 795.2 | LABOR- SUBCONTRACTOR
%R | 503047 | 6359 | 125082 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5TCGL5305 | Backfilling telecommunication trench | 8177 | 72 | 0 | 160 | 0 | 530 | 530 | 160 | 440 | 0 | 440 |  |  |  | 2014-08-31 08:00 | 2014-09-22 17:00 |  | 2014-08-20 08:00 | 2014-09-11 17:00 | 2014-08-20 08:00 | 2014-09-11 17:00 | 2014-08-20 08:00 | 2014-09-11 17:00 | 2014-08-31 08:00 | 2014-09-22 17:00 |  | PT_Normal |  |  |  |  | Wr91fwCESgqd0ISzyB0x7w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34490 | N | N | 45 | TELECOMMUNICATION LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 530 | LABOR - CIVIL
%R | 503048 | 6359 | 125082 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5TCGL5310 | Connection & Installation | 8178 | 224 | 16 | 160 | 0 | 344.4 | 344.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-04 08:00 | 2014-10-28 17:00 |  | 2014-09-01 08:00 | 2014-09-23 17:00 | 2014-09-01 08:00 | 2014-09-23 17:00 | 2014-09-01 08:00 | 2014-09-23 17:00 | 2014-10-04 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | sCMHCyNPTqCduAX2CE0DUg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34490 | N | N | 45 | TELECOMMUNICATION LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 344.4 | LABOR- SUBCONTRACTOR
%R | 503049 | 6359 | 125083 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5FFGL5185 | Excavation for firefighting line | 8177 | 72 | 0 | 200 | 0 | 283 | 283 | 200 | 151 | 0 | 151 |  |  |  | 2014-06-25 08:00 | 2014-07-23 17:00 |  | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-25 08:00 | 2014-07-23 17:00 |  | PT_Normal |  |  |  |  | K/MQ549YQkG0bv7cEhqzRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34450 | N | N | 25 | FIREFIGHTING LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 283 | LABOR - CIVIL
%R | 503050 | 6359 | 125083 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5FFGL5190 | Laying of firefighting line | 8178 | 72 | 0 | 200 | 0 | 303.6 | 303.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-03 08:00 | 2014-07-31 17:00 |  | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-07-03 08:00 | 2014-07-31 17:00 |  | PT_Normal |  |  |  |  | SvWrNXTFTKywSyDgNdggZQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34450 | N | N | 25 | FIREFIGHTING LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 303.6 | LABOR- SUBCONTRACTOR
%R | 503051 | 6359 | 125083 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5FFGL5195 | Testing of firefighting line | 8178 | 72 | 0 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-09 08:00 | 2014-08-10 17:00 |  | 2014-06-29 08:00 | 2014-07-27 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 | 2014-06-29 08:00 | 2014-07-27 17:00 | 2014-07-09 08:00 | 2014-08-10 17:00 |  | PT_Normal |  |  |  |  | 0YC/nkxVQKyR/p+mznoFog |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34450 | N | N | 25 | FIREFIGHTING LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 84 | LABOR- SUBCONTRACTOR
%R | 503052 | 6359 | 125083 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5FFGL5200 | Backfilling firefighting line | 8177 | 72 | 0 | 200 | 0 | 329 | 329 | 200 | 275 | 0 | 275 |  |  |  | 2014-07-15 08:00 | 2014-08-16 17:00 |  | 2014-07-05 08:00 | 2014-08-05 17:00 | 2014-07-05 08:00 | 2014-08-05 17:00 | 2014-07-05 08:00 | 2014-08-05 17:00 | 2014-07-15 08:00 | 2014-08-16 17:00 |  | PT_Normal |  |  |  |  | xneOKwsbTDyQQwHvGa3crw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34450 | N | N | 25 | FIREFIGHTING LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 164.5 | LABOR - CIVIL
%R | 503053 | 6359 | 125083 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5FFGL5205 | Construction of valve chambers & Thrust Blocks | 8165 | 248 | 0 | 200 | 0 | 202 | 202 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-19 08:00 | 2014-09-16 17:00 |  | 2014-07-10 08:00 | 2014-08-11 17:00 | 2014-07-10 08:00 | 2014-08-11 17:00 | 2014-07-10 08:00 | 2014-08-11 17:00 | 2014-08-19 08:00 | 2014-09-16 17:00 |  | PT_Normal |  |  |  |  | pY+gAh6gRRWR2dkcHbyMgA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34450 | N | N | 25 | FIREFIGHTING LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 101 | STEEL FIXERS SK
%R | 503054 | 6359 | 125083 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5FFGL5210 | Connection with existing Firewater System | 8178 | 248 | 176 | 200 | 0 | 134.4 | 134.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-25 08:00 | 2014-09-22 17:00 |  | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-08-25 08:00 | 2014-09-22 17:00 |  | PT_Normal |  |  |  |  | JzmHhmfqQNyH6kyp7zsqLg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34450 | N | N | 25 | FIREFIGHTING LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 503055 | 6359 | 125084 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5HDGL7020 | Precast Concrete Kerbs works | 8173 | 184 | 0 | 160 | 0 | 1178 | 1178 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-12 08:00 | 2014-11-03 17:00 |  | 2014-09-13 08:00 | 2014-10-05 17:00 | 2014-09-13 08:00 | 2014-10-05 17:00 | 2014-09-13 08:00 | 2014-10-05 17:00 | 2014-10-12 08:00 | 2014-11-03 17:00 |  | PT_Normal |  |  |  |  | SzoqZ8wLQKO2nH74AdOR/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34530 | N | N | 65 | HARD LANDSCAPING |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 1178 | KERBSTONE MASON SK
%R | 503056 | 6359 | 125084 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5HDGL7025 | Interlocking for Walkways | 8174 | 184 | 0 | 200 | 0 | 806 | 806 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-23 08:00 | 2014-11-20 17:00 |  | 2014-09-24 08:00 | 2014-10-25 17:00 | 2014-09-24 08:00 | 2014-10-25 17:00 | 2014-09-24 08:00 | 2014-10-25 17:00 | 2014-10-23 08:00 | 2014-11-20 17:00 |  | PT_Normal |  |  |  |  | TERV3RJnRxmVKajHuAbvrQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34530 | N | N | 65 | HARD LANDSCAPING |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 403 | INTERLOCK MASON SK
%R | 503057 | 6359 | 125084 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5HDGL7030 | Construction of Retaining wall | 8165 | 184 | 0 | 200 | 0 | 756 | 756 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-04 08:00 | 2014-12-02 17:00 |  | 2014-10-06 08:00 | 2014-11-05 17:00 | 2014-10-06 08:00 | 2014-11-05 17:00 | 2014-10-06 08:00 | 2014-11-05 17:00 | 2014-11-04 08:00 | 2014-12-02 17:00 |  | PT_Normal |  |  |  |  | HgUfer1aS2O5QTdGh88Zyg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34530 | N | N | 65 | HARD LANDSCAPING |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 756 | STEEL FIXERS SK
%R | 503058 | 6359 | 125084 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5HDGL7035 | Construction of Wash Stone Boulders | 8170 | 184 | 0 | 200 | 0 | 88 | 88 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-04 08:00 | 2014-12-02 17:00 |  | 2014-10-06 08:00 | 2014-11-05 17:00 | 2014-10-06 08:00 | 2014-11-05 17:00 | 2014-10-06 08:00 | 2014-11-05 17:00 | 2014-11-04 08:00 | 2014-12-02 17:00 |  | PT_Normal |  |  |  |  | 5h2Mzs/UQH+f0e3cOXHrlg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34530 | N | N | 65 | HARD LANDSCAPING |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 88 | TILE MASON SK
%R | 503059 | 6359 | 125084 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5HDGL7040 | Construction of Speed Humps | 8167 | 72 | 72 | 80 | 0 | 14 | 14 | 80 | 0 | 0 | 0 |  |  |  | 2014-12-03 08:00 | 2014-12-14 17:00 |  | 2014-11-23 08:00 | 2014-12-03 17:00 | 2014-11-23 08:00 | 2014-12-03 17:00 | 2014-11-23 08:00 | 2014-12-03 17:00 | 2014-12-03 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | VVGR/nrqRiWhxLKTvAOYKQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34530 | N | N | 65 | HARD LANDSCAPING |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 14 | CONCRETE MASON SK
%R | 503060 | 6359 | 125085 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5DRGL5115 | Excavation for Drainage line | 8177 | 72 | 0 | 200 | 0 | 431 | 431 | 200 | 251 | 0 | 251 |  |  |  | 2014-04-19 08:00 | 2014-05-17 17:00 |  | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 |  | PT_Normal |  |  |  |  | kP10o29wTbiO2egqJW3bDg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34420 | N | N | 10 | DRAINAGE LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 431 | LABOR - CIVIL
%R | 503061 | 6359 | 125085 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5DRGL5120 | Laying of Drainage line | 8178 | 72 | 0 | 200 | 0 | 276 | 276 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-26 08:00 | 2014-05-24 17:00 |  | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 |  | PT_Normal |  |  |  |  | JiHg2Nr9QhCuWe75Ybsfbw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34420 | N | N | 10 | DRAINAGE LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 276 | LABOR- SUBCONTRACTOR
%R | 503062 | 6359 | 125085 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5DRGL5125 | Testing of Drainage line | 8178 | 72 | 0 | 200 | 0 | 134.4 | 134.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-04 08:00 | 2014-06-01 17:00 |  | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 |  | PT_Normal |  |  |  |  | 5ZtliP40RSaBThg30cPN/A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34420 | N | N | 10 | DRAINAGE LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 503063 | 6359 | 125085 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5DRGL5130 | Backfilling Drainage line | 8177 | 72 | 0 | 120 | 0 | 402 | 402 | 120 | 330 | 0 | 330 |  |  |  | 2014-05-21 08:00 | 2014-06-07 17:00 |  | 2014-05-11 08:00 | 2014-05-27 17:00 | 2014-05-11 08:00 | 2014-05-27 17:00 | 2014-05-11 08:00 | 2014-05-27 17:00 | 2014-05-21 08:00 | 2014-06-07 17:00 |  | PT_Normal |  |  |  |  | Lh6mJjRHSy+Hc3znKmBnhg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34420 | N | N | 10 | DRAINAGE LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 402 | LABOR - CIVIL
%R | 503064 | 6359 | 125086 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5PSGL7000 | Excavation | 8177 | 120 | 40 | 120 | 0 | 148 | 148 | 120 | 76 | 0 | 76 |  |  |  | 2014-11-11 08:00 | 2014-11-27 17:00 |  | 2014-10-25 08:00 | 2014-11-10 17:00 | 2014-10-25 08:00 | 2014-11-10 17:00 | 2014-10-25 08:00 | 2014-11-10 17:00 | 2014-11-11 08:00 | 2014-11-27 17:00 |  | PT_Normal |  |  |  |  | EOFApkJhTw+3vtmKMMldZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34520 | N | N | 60 | PARKING SHED |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 148 | LABOR - CIVIL
%R | 503065 | 6359 | 125086 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5PSGL7005 | Foundation casting | 8165 | 80 | 0 | 120 | 0 | 252 | 252 | 120 | 0 | 0 | 0 |  |  |  | 2014-11-17 08:00 | 2014-12-03 17:00 |  | 2014-11-05 08:00 | 2014-11-22 17:00 | 2014-11-05 08:00 | 2014-11-22 17:00 | 2014-11-05 08:00 | 2014-11-22 17:00 | 2014-11-17 08:00 | 2014-12-03 17:00 |  | PT_Normal |  |  |  |  | tAVTmRfdRmuwmJbc0yJMpQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34520 | N | N | 60 | PARKING SHED |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 252 | STEEL FIXERS SK
%R | 503066 | 6359 | 125086 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5PSGL7010 | Column, Frame& Fabrics Erection | 8178 | 80 | 0 | 200 | 0 | 286 | 286 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-29 08:00 | 2014-12-28 17:00 |  | 2014-11-17 08:00 | 2014-12-15 17:00 | 2014-11-17 08:00 | 2014-12-15 17:00 | 2014-11-17 08:00 | 2014-12-15 17:00 | 2014-11-29 08:00 | 2014-12-28 17:00 |  | PT_Normal |  |  |  |  | hnHJWHXaSgqKzLUOemLh5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34520 | N | N | 60 | PARKING SHED |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 286 | LABOR- SUBCONTRACTOR
%R | 503067 | 6359 | 125086 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5PSGL7015 | Electrical Works-Parking Shed | 8178 | 80 | 80 | 200 | 0 | 51.6 | 51.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-12-04 08:00 | 2015-01-03 17:00 |  | 2014-11-23 08:00 | 2014-12-22 17:00 | 2014-11-23 08:00 | 2014-12-22 17:00 | 2014-11-23 08:00 | 2014-12-22 17:00 | 2014-12-04 08:00 | 2015-01-03 17:00 |  | PT_Normal |  |  |  |  | dkLjAPKTSXWbunfs1IkhWQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34520 | N | N | 60 | PARKING SHED |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 51.6 | LABOR- SUBCONTRACTOR
%R | 503068 | 6359 | 125087 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5IRGL5265 | Excavation for irrigation line | 8177 | 272 | 0 | 200 | 0 | 812 | 812 | 200 | 500 | 0 | 500 |  |  |  | 2014-10-07 08:00 | 2014-11-06 17:00 |  | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-10-07 08:00 | 2014-11-06 17:00 |  | PT_Normal |  |  |  |  | SVGh/N8XR0aMmwgtnt12iw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34480 | N | N | 40 | IRRIGATION LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 812 | LABOR - CIVIL
%R | 503069 | 6359 | 125087 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5IRGL5270 | Laying of irrigationline | 8178 | 272 | 0 | 200 | 0 | 386.4 | 386.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-15 08:00 | 2014-11-12 17:00 |  | 2014-09-03 08:00 | 2014-10-01 17:00 | 2014-09-03 08:00 | 2014-10-01 17:00 | 2014-09-03 08:00 | 2014-10-01 17:00 | 2014-10-15 08:00 | 2014-11-12 17:00 |  | PT_Normal |  |  |  |  | NZKN7k+rSt6sPIPWIeC4aA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34480 | N | N | 40 | IRRIGATION LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 386.4 | LABOR- SUBCONTRACTOR
%R | 503070 | 6359 | 125087 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5IRGL5275 | Testing of irrigation line | 8178 | 272 | 0 | 200 | 0 | 319.2 | 319.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-21 08:00 | 2014-11-18 17:00 |  | 2014-09-09 08:00 | 2014-10-07 17:00 | 2014-09-09 08:00 | 2014-10-07 17:00 | 2014-09-09 08:00 | 2014-10-07 17:00 | 2014-10-21 08:00 | 2014-11-18 17:00 |  | PT_Normal |  |  |  |  | itf3Qp9SS+uwWzdu4H//2Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34480 | N | N | 40 | IRRIGATION LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 319.2 | LABOR- SUBCONTRACTOR
%R | 503071 | 6359 | 125087 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5IRGL5280 | Backfilling irrigation line | 8177 | 272 | 0 | 200 | 0 | 676 | 676 | 200 | 550 | 0 | 550 |  |  |  | 2014-10-27 08:00 | 2014-11-24 17:00 |  | 2014-09-15 08:00 | 2014-10-15 17:00 | 2014-09-15 08:00 | 2014-10-15 17:00 | 2014-09-15 08:00 | 2014-10-15 17:00 | 2014-10-27 08:00 | 2014-11-24 17:00 |  | PT_Normal |  |  |  |  | i1q9FlNnRS2OqkHMum/BnQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34480 | N | N | 40 | IRRIGATION LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 338 | LABOR - CIVIL
%R | 503072 | 6359 | 125087 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5IRGL5285 | Construction of Thrust Blocks,Pull boxes | 8178 | 272 | 0 | 200 | 0 | 116.4 | 116.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-08 08:00 | 2014-12-06 17:00 |  | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-11-08 08:00 | 2014-12-06 17:00 |  | PT_Normal |  |  |  |  | vuhJCxqaSiSkOTcaI8StQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34480 | N | N | 40 | IRRIGATION LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 58.2 | LABOR- SUBCONTRACTOR
%R | 503073 | 6359 | 125087 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5IRGL5290 | Irrigation Fittings (Nozzle,Values) | 8178 | 272 | 88 | 200 | 0 | 285.6 | 285.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-16 08:00 | 2014-12-14 17:00 |  | 2014-10-05 08:00 | 2014-11-04 17:00 | 2014-10-05 08:00 | 2014-11-04 17:00 | 2014-10-05 08:00 | 2014-11-04 17:00 | 2014-11-16 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | jyHwc382QgOkxLLQiSo2jw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34480 | N | N | 40 | IRRIGATION LINES |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 285.6 | LABOR- SUBCONTRACTOR
%R | 503074 | 6359 | 125088 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5WSGL5155 | Excavation for water line | 8177 | 72 | 0 | 200 | 0 | 401 | 401 | 200 | 251 | 0 | 251 |  |  |  | 2014-06-02 08:00 | 2014-06-30 17:00 |  | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-06-02 08:00 | 2014-06-30 17:00 |  | PT_Normal |  |  |  |  | /bk017jRRWmVf7z/PoftDw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34440 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 401 | LABOR - CIVIL
%R | 503075 | 6359 | 125088 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5WSGL5160 | Laying of water line | 8178 | 72 | 0 | 200 | 0 | 285.6 | 285.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-08 08:00 | 2014-07-06 17:00 |  | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-06-08 08:00 | 2014-07-06 17:00 |  | PT_Normal |  |  |  |  | 9KF7z4phQI6d7lq2nfSBoA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34440 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 285.6 | LABOR- SUBCONTRACTOR
%R | 503076 | 6359 | 125088 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5WSGL5165 | Testing of potable water line | 8178 | 72 | 0 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-14 08:00 | 2014-07-12 17:00 |  | 2014-06-03 08:00 | 2014-07-01 17:00 | 2014-06-03 08:00 | 2014-07-01 17:00 | 2014-06-03 08:00 | 2014-07-01 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 |  | PT_Normal |  |  |  |  | cNAn67F0QjaojyES0O7KnQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34440 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 84 | LABOR- SUBCONTRACTOR
%R | 503077 | 6359 | 125088 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5WSGL5170 | Backfilling potable water line | 8177 | 72 | 0 | 200 | 0 | 335 | 335 | 200 | 275 | 0 | 275 |  |  |  | 2014-06-19 08:00 | 2014-07-17 17:00 |  | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-09 08:00 | 2014-07-07 17:00 | 2014-06-19 08:00 | 2014-07-17 17:00 |  | PT_Normal |  |  |  |  | E2WfkReWRaq1opc1hRTxZQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34440 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 335 | LABOR - CIVIL
%R | 503078 | 6359 | 125088 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5WSGL5175 | Construction of valve chambers & Thrust Blocks | 8172 | 304 | 0 | 200 | 0 | 132 | 132 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-29 08:00 | 2014-08-30 17:00 |  | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-07-29 08:00 | 2014-08-30 17:00 |  | PT_Normal |  |  |  |  | wJQmNHZzQGKoyrk7tBAZkQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34440 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 132 | MANHOLES SK
%R | 503079 | 6359 | 125088 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ5WSGL5180 | Installation of meter ,Accessories & Connection | 8178 | 304 | 56 | 160 | 0 | 50.4 | 50.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-31 08:00 | 2014-09-22 17:00 |  | 2014-07-14 08:00 | 2014-08-09 17:00 | 2014-07-14 08:00 | 2014-08-09 17:00 | 2014-07-14 08:00 | 2014-08-09 17:00 | 2014-08-31 08:00 | 2014-09-22 17:00 |  | PT_Normal |  |  |  |  | pVsp7C6QTaG7seOiS6hguQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34440 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125075 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 503080 | 6359 | 125091 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBIWGL7400 | Excavation | 8177 | 144 | 0 | 144 | 0 | 324 | 324 | 144 | 180 | 0 | 180 |  |  |  | 2014-06-16 08:00 | 2014-07-06 17:00 |  | 2014-05-26 08:00 | 2014-06-15 17:00 | 2014-05-26 08:00 | 2014-06-15 17:00 | 2014-05-26 08:00 | 2014-06-15 17:00 | 2014-06-16 08:00 | 2014-07-06 17:00 |  | PT_Normal |  |  |  |  | QBD4k8XQRlWtRu+Ku6fmEA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34570 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 324 | LABOR - CIVIL
%R | 503081 | 6359 | 125091 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBIWGL7405 | Blinding & base waterproofing | 8163 | 144 | 0 | 80 | 0 | 200 | 200 | 80 | 0 | 0 | 0 |  |  |  | 2014-07-07 08:00 | 2014-07-17 17:00 |  | 2014-06-16 08:00 | 2014-06-26 17:00 | 2014-06-16 08:00 | 2014-06-26 17:00 | 2014-06-16 08:00 | 2014-06-26 17:00 | 2014-07-07 08:00 | 2014-07-17 17:00 |  | PT_Normal |  |  |  |  | icy9EX3NRF6JcJvDi58MvA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34570 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 200 | BLINDING MASON SK
%R | 503082 | 6359 | 125091 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBIWGL7410 | Construction of Raft slab | 8165 | 144 | 0 | 96 | 0 | 630 | 630 | 96 | 0 | 0 | 0 |  |  |  | 2014-07-19 08:00 | 2014-07-31 17:00 |  | 2014-06-28 08:00 | 2014-07-10 17:00 | 2014-06-28 08:00 | 2014-07-10 17:00 | 2014-06-28 08:00 | 2014-07-10 17:00 | 2014-07-19 08:00 | 2014-07-31 17:00 |  | PT_Normal |  |  |  |  | EGgBLasdTR2mm7boS4G5Fg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34570 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 630 | STEEL FIXERS SK
%R | 503083 | 6359 | 125091 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBIWGL7415 | Construction of RCC Wall | 8165 | 144 | 0 | 200 | 0 | 1708 | 1708 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-05 08:00 | 2014-09-02 17:00 |  | 2014-07-12 08:00 | 2014-08-12 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 | 2014-08-05 08:00 | 2014-09-02 17:00 |  | PT_Normal |  |  |  |  | 65fifWjRQ0OjcwXvaj5nQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34570 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 854 | STEEL FIXERS SK
%R | 503084 | 6359 | 125091 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBIWGL7420 | Construction of Roof Slab | 8165 | 144 | 0 | 160 | 0 | 490 | 490 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-03 08:00 | 2014-09-25 17:00 |  | 2014-08-13 08:00 | 2014-09-04 17:00 | 2014-08-13 08:00 | 2014-09-04 17:00 | 2014-08-13 08:00 | 2014-09-04 17:00 | 2014-09-03 08:00 | 2014-09-25 17:00 |  | PT_Normal |  |  |  |  | BeSOQ3FNTvC+zFNO6WXKRA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34570 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 490 | STEEL FIXERS SK
%R | 503085 | 6359 | 125091 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBIWGL7425 | Waterproofing & Backfilling | 8177 | 192 | 0 | 120 | 0 | 273 | 273 | 120 | 165 | 0 | 165 |  |  |  | 2014-10-04 08:00 | 2014-10-22 17:00 |  | 2014-09-06 08:00 | 2014-09-22 17:00 | 2014-09-06 08:00 | 2014-09-22 17:00 | 2014-09-06 08:00 | 2014-09-22 17:00 | 2014-10-04 08:00 | 2014-10-22 17:00 |  | PT_Normal |  |  |  |  | 5RaH9lVjSgqF0AoV6gYXNA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34570 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 273 | LABOR - CIVIL
%R | 503086 | 6359 | 125091 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBIWGL7430 | Floor screed | 8164 | 144 | 0 | 40 | 0 | 66 | 66 | 40 | 0 | 0 | 0 |  |  |  | 2014-10-23 08:00 | 2014-10-28 17:00 |  | 2014-09-30 08:00 | 2014-10-05 17:00 | 2014-09-30 08:00 | 2014-10-05 17:00 | 2014-09-30 08:00 | 2014-10-05 17:00 | 2014-10-23 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | pTkjC0cdQy6SmpxbNLrRwA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34570 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 66 | SCREED MASON SK
%R | 503087 | 6359 | 125091 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBIWGL7455 | Internal epoxy coating & Painting | 8178 | 144 | 0 | 40 | 0 | 44 | 44 | 40 | 0 | 0 | 0 |  |  |  | 2014-11-27 08:00 | 2014-12-02 17:00 |  | 2014-11-06 08:00 | 2014-11-11 17:00 | 2014-11-06 08:00 | 2014-11-11 17:00 | 2014-11-06 08:00 | 2014-11-11 17:00 | 2014-11-27 08:00 | 2014-12-02 17:00 |  | PT_Normal |  |  |  |  | W63/TiR6QDqamIOtfBMCsQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34570 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 44 | LABOR- SUBCONTRACTOR
%R | 503088 | 6359 | 125091 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBIWGL7460 | Installation of Steel Ladder | 8178 | 144 | 0 | 40 | 0 | 14 | 14 | 40 | 0 | 0 | 0 |  |  |  | 2014-12-03 08:00 | 2014-12-08 17:00 |  | 2014-11-12 08:00 | 2014-11-17 17:00 | 2014-11-12 08:00 | 2014-11-17 17:00 | 2014-11-12 08:00 | 2014-11-17 17:00 | 2014-12-03 08:00 | 2014-12-08 17:00 |  | PT_Normal |  |  |  |  | RO0or04eQI2/PvsvfrB1Vg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34570 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 14 | LABOR- SUBCONTRACTOR
%R | 503089 | 6359 | 125091 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBIWGL7465 | Installation of G.I Handrails | 8178 | 144 | 144 | 40 | 0 | 164 | 164 | 40 | 0 | 0 | 0 |  |  |  | 2014-12-09 08:00 | 2014-12-14 17:00 |  | 2014-11-18 08:00 | 2014-11-23 17:00 | 2014-11-18 08:00 | 2014-11-23 17:00 | 2014-11-18 08:00 | 2014-11-23 17:00 | 2014-12-09 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | ksL7gVbnSBWI+x4usb1jRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34570 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 164 | LABOR- SUBCONTRACTOR
%R | 503090 | 6359 | 125091 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBIWGL7440 | Plumbing , Drainage & Firefighting works | 8178 | 144 | 0 | 200 | 0 | 50.4 | 50.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-29 08:00 | 2014-11-26 17:00 |  | 2014-10-06 08:00 | 2014-11-05 17:00 | 2014-10-06 08:00 | 2014-11-05 17:00 | 2014-10-06 08:00 | 2014-11-05 17:00 | 2014-10-29 08:00 | 2014-11-26 17:00 |  | PT_Normal |  |  |  |  | 6XCP+Fb8RMWrXdNfowim3g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34570 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 503091 | 6359 | 125091 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBIWGL7445 | AC Works | 8178 | 144 | 0 | 200 | 0 | 159.2 | 159.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-29 08:00 | 2014-11-26 17:00 |  | 2014-10-06 08:00 | 2014-11-05 17:00 | 2014-10-06 08:00 | 2014-11-05 17:00 | 2014-10-06 08:00 | 2014-11-05 17:00 | 2014-10-29 08:00 | 2014-11-26 17:00 |  | PT_Normal |  |  |  |  | 3rpCs9YPQBe8ZgqBsxHM+A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34570 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 159.2 | LABOR- SUBCONTRACTOR
%R | 503092 | 6359 | 125091 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBIWGL7450 | Electrical Works | 8178 | 144 | 0 | 200 | 0 | 325.2 | 325.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-29 08:00 | 2014-11-26 17:00 |  | 2014-10-06 08:00 | 2014-11-05 17:00 | 2014-10-06 08:00 | 2014-11-05 17:00 | 2014-10-06 08:00 | 2014-11-05 17:00 | 2014-10-29 08:00 | 2014-11-26 17:00 |  | PT_Normal |  |  |  |  | JlgGV7YLRdCvARg+ABtryg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34570 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 325.2 | LABOR- SUBCONTRACTOR
%R | 503093 | 6359 | 125091 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBIWGL7950 | Laying of Interlock | 8174 | 312 | 0 | 80 | 0 | 58 | 58 | 80 | 0 | 0 | 0 |  |  |  | 2014-11-10 08:00 | 2014-11-20 17:00 |  | 2014-09-23 08:00 | 2014-10-04 17:00 | 2014-09-23 08:00 | 2014-10-04 17:00 | 2014-09-23 08:00 | 2014-10-04 17:00 | 2014-11-10 08:00 | 2014-11-20 17:00 |  | PT_Normal |  |  |  |  | xy9x1cRsQxS+cOh8Ba3vnA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34570 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 58 | INTERLOCK MASON SK
%R | 503094 | 6359 | 125091 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBIWGL7435 | Installation of Boundary Fences | 8165 | 312 | 168 | 120 | 0 | 42 | 42 | 120 | 0 | 0 | 0 |  |  |  | 2014-11-22 08:00 | 2014-12-08 17:00 |  | 2014-10-05 08:00 | 2014-10-23 17:00 | 2014-10-05 08:00 | 2014-10-23 17:00 | 2014-10-05 08:00 | 2014-10-23 17:00 | 2014-11-22 08:00 | 2014-12-08 17:00 |  | PT_Normal |  |  |  |  | WHWa1ObER+yEjHWLPZfs4A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34570 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 42 | STEEL FIXERS SK
%R | 503095 | 6359 | 125092 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBGHGL7800 | Excavation | 8162 | 240 | 0 | 80 | 0 | 32 | 32 | 80 | 20 | 0 | 20 |  |  |  | 2014-08-05 08:00 | 2014-08-16 17:00 |  | 2014-06-28 08:00 | 2014-07-08 17:00 | 2014-06-28 08:00 | 2014-07-08 17:00 | 2014-06-28 08:00 | 2014-07-08 17:00 | 2014-08-05 08:00 | 2014-08-16 17:00 |  | PT_Normal |  |  |  |  | zDGsBQxLSp23KQzeIpAHDg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43390 |  |  |  |  | EQUIP OPERATORS | EQOP |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34590 | N | N | 20 | GUARD HOUSE |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 32 | EQUIP OPERATORS
%R | 503096 | 6359 | 125092 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBGHGL7805 | Construction of foundation & Grade slab | 8165 | 240 | 0 | 160 | 0 | 280 | 280 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-17 08:00 | 2014-09-08 17:00 |  | 2014-07-09 08:00 | 2014-07-31 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 | 2014-07-09 08:00 | 2014-07-31 17:00 | 2014-08-17 08:00 | 2014-09-08 17:00 |  | PT_Normal |  |  |  |  | fCrrGYBgQguk0TXmB92Yrw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34590 | N | N | 20 | GUARD HOUSE |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 280 | STEEL FIXERS SK
%R | 503097 | 6359 | 125092 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBGHGL7810 | Construction Column,Beams & Roof Slab | 8165 | 240 | 0 | 160 | 0 | 280 | 280 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-09 08:00 | 2014-10-01 17:00 |  | 2014-08-05 08:00 | 2014-08-27 17:00 | 2014-08-05 08:00 | 2014-08-27 17:00 | 2014-08-05 08:00 | 2014-08-27 17:00 | 2014-09-09 08:00 | 2014-10-01 17:00 |  | PT_Normal |  |  |  |  | 5A25ZTAORr+05DLmBbhqLQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34590 | N | N | 20 | GUARD HOUSE |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 280 | STEEL FIXERS SK
%R | 503098 | 6359 | 125092 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBGHGL7815 | Finishing Works | 8164 | 240 | 0 | 200 | 0 | 1000 | 1000 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-29 08:00 | 2014-11-26 17:00 |  | 2014-09-22 08:00 | 2014-10-22 17:00 | 2014-09-22 08:00 | 2014-10-22 17:00 | 2014-09-22 08:00 | 2014-10-22 17:00 | 2014-10-29 08:00 | 2014-11-26 17:00 |  | PT_Normal |  |  |  |  | OjCl6xSIRTuulxYLY7Ftng |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34590 | N | N | 20 | GUARD HOUSE |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 500 | SCREED MASON SK
%R | 503099 | 6359 | 125092 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBGHGL7820 | Plumbing , Drainage & Firefighting works | 8181 | 240 | 0 | 200 | 0 | 282.8 | 282.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-10 08:00 | 2014-12-08 17:00 |  | 2014-10-04 08:00 | 2014-11-03 17:00 | 2014-10-04 08:00 | 2014-11-03 17:00 | 2014-10-04 08:00 | 2014-11-03 17:00 | 2014-11-10 08:00 | 2014-12-08 17:00 |  | PT_Normal |  |  |  |  | KULbdTVVQL+jC3ZJ1AiIvg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43581 |  |  |  |  | MECHANICALS SK | M303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34590 | N | N | 20 | GUARD HOUSE |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 282.8 | MECHANICALS SK
%R | 503100 | 6359 | 125092 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBGHGL7825 | AC Works |  | 240 | 0 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-10 08:00 | 2014-12-08 17:00 |  | 2014-10-04 08:00 | 2014-11-03 17:00 | 2014-10-04 08:00 | 2014-11-03 17:00 | 2014-10-04 08:00 | 2014-11-03 17:00 | 2014-11-10 08:00 | 2014-12-08 17:00 |  | PT_Normal |  |  |  |  | D68GdzzrSbGZF/ENky8n9g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 34590 | N | N | 20 | GUARD HOUSE |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 0 | 0
%R | 503101 | 6359 | 125092 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBGHGL7830 | Electrical Works-Telecom Room | 8180 | 240 | 0 | 200 | 0 | 416 | 416 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-10 08:00 | 2014-12-08 17:00 |  | 2014-10-04 08:00 | 2014-11-03 17:00 | 2014-10-04 08:00 | 2014-11-03 17:00 | 2014-10-04 08:00 | 2014-11-03 17:00 | 2014-11-10 08:00 | 2014-12-08 17:00 |  | PT_Normal |  |  |  |  | CYMRHmAySj+jMUU5xpL1tA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43571 |  |  |  |  | ELECTRICIANS SK | M302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34590 | N | N | 20 | GUARD HOUSE |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 416 | ELECTRICIANS SK
%R | 503102 | 6359 | 125092 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBGHGL7835 | Final Paintings | 8178 | 240 | 240 | 40 | 0 | 275 | 275 | 40 | 0 | 0 | 0 |  |  |  | 2014-12-09 08:00 | 2014-12-14 17:00 |  | 2014-11-04 08:00 | 2014-11-09 17:00 | 2014-11-04 08:00 | 2014-11-09 17:00 | 2014-11-04 08:00 | 2014-11-09 17:00 | 2014-12-09 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | EIy96vkDQ+yIlHcMXRQsaQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34590 | N | N | 20 | GUARD HOUSE |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 275 | LABOR- SUBCONTRACTOR
%R | 503103 | 6359 | 125093 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBTRGL7600 | Excavation | 8177 | 240 | 0 | 80 | 0 | 32 | 32 | 80 | 20 | 0 | 20 |  |  |  | 2014-07-21 08:00 | 2014-07-31 17:00 |  | 2014-06-16 08:00 | 2014-06-26 17:00 | 2014-06-16 08:00 | 2014-06-26 17:00 | 2014-06-16 08:00 | 2014-06-26 17:00 | 2014-07-21 08:00 | 2014-07-31 17:00 |  | PT_Normal |  |  |  |  | 3OzdKHLDS4ewMfYka9dV4A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34580 | N | N | 15 | TELECOMMUNICATION ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 32 | LABOR - CIVIL
%R | 503104 | 6359 | 125093 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBTRGL7605 | Construction of foundation & Grade slab | 8165 | 320 | 0 | 160 | 0 | 280 | 280 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-17 08:00 | 2014-09-08 17:00 |  | 2014-06-28 08:00 | 2014-07-20 17:00 | 2014-06-28 08:00 | 2014-07-20 17:00 | 2014-06-28 08:00 | 2014-07-20 17:00 | 2014-08-17 08:00 | 2014-09-08 17:00 |  | PT_Normal |  |  |  |  | e5xfVflFRpG4rVpVPlvZsg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34580 | N | N | 15 | TELECOMMUNICATION ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 280 | STEEL FIXERS SK
%R | 503105 | 6359 | 125093 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBTRGL7610 | Construction Column,Beams & Roof Slab | 8165 | 320 | 0 | 160 | 0 | 280 | 280 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-09 08:00 | 2014-10-01 17:00 |  | 2014-07-21 08:00 | 2014-08-16 17:00 | 2014-07-21 08:00 | 2014-08-16 17:00 | 2014-07-21 08:00 | 2014-08-16 17:00 | 2014-09-09 08:00 | 2014-10-01 17:00 |  | PT_Normal |  |  |  |  | kDxi/wWYQkyXSBiYIVTB1w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34580 | N | N | 15 | TELECOMMUNICATION ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 280 | STEEL FIXERS SK
%R | 503106 | 6359 | 125093 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBTRGL7615 | Finishing Works | 8164 | 320 | 32 | 200 | 0 | 1000 | 1000 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-29 08:00 | 2014-11-26 17:00 |  | 2014-09-10 08:00 | 2014-10-08 17:00 | 2014-09-10 08:00 | 2014-10-08 17:00 | 2014-09-10 08:00 | 2014-10-08 17:00 | 2014-10-29 08:00 | 2014-11-26 17:00 |  | PT_Normal |  |  |  |  | 2stscppyTs2Geaydz8QUNg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34580 | N | N | 15 | TELECOMMUNICATION ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 1000 | SCREED MASON SK
%R | 503107 | 6359 | 125093 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBTRGL7620 | Plumbing , Drainage & Firefighting works | 8178 | 288 | 0 | 200 | 0 | 282.8 | 282.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-10 08:00 | 2014-12-08 17:00 |  | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-11-10 08:00 | 2014-12-08 17:00 |  | PT_Normal |  |  |  |  | Fx8AW660Sdu81+phA4grKw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34580 | N | N | 15 | TELECOMMUNICATION ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 141.4 | LABOR- SUBCONTRACTOR
%R | 503108 | 6359 | 125093 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBTRGL7625 | AC Works | 8178 | 288 | 0 | 200 | 0 | 284 | 284 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-10 08:00 | 2014-12-08 17:00 |  | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-11-10 08:00 | 2014-12-08 17:00 |  | PT_Normal |  |  |  |  | ylu+8DwWT+uci4Wvz1f83g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34580 | N | N | 15 | TELECOMMUNICATION ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 142 | LABOR- SUBCONTRACTOR
%R | 503109 | 6359 | 125093 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBTRGL7630 | Electrical Works-Telecom Room | 8178 | 288 | 0 | 200 | 0 | 416 | 416 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-10 08:00 | 2014-12-08 17:00 |  | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-11-10 08:00 | 2014-12-08 17:00 |  | PT_Normal |  |  |  |  | yTXn1LAuSC6SDUdxbq6wdA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34580 | N | N | 15 | TELECOMMUNICATION ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 208 | LABOR- SUBCONTRACTOR
%R | 503110 | 6359 | 125093 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBTRGL7635 | Final Paintings | 8178 | 288 | 288 | 40 | 0 | 275 | 275 | 40 | 0 | 0 | 0 |  |  |  | 2014-12-09 08:00 | 2014-12-14 17:00 |  | 2014-10-28 08:00 | 2014-11-02 17:00 | 2014-10-28 08:00 | 2014-11-02 17:00 | 2014-10-28 08:00 | 2014-11-02 17:00 | 2014-12-09 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | vYneHOZuQ+aCi4LYTmbiFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34580 | N | N | 15 | TELECOMMUNICATION ROOM |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 275 | LABOR- SUBCONTRACTOR
%R | 503111 | 6359 | 125094 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBSSGL7920 | Hard landscaping around substation | 8178 | 280 | 0 | 240 | 0 | 720 | 720 | 240 | 0 | 0 | 0 |  |  |  | 2014-11-05 08:00 | 2014-12-09 17:00 |  | 2014-09-23 08:00 | 2014-10-29 17:00 | 2014-09-23 08:00 | 2014-10-29 17:00 | 2014-09-23 08:00 | 2014-10-29 17:00 | 2014-11-05 08:00 | 2014-12-09 17:00 |  | PT_Normal |  |  |  |  | 2DVhAXyhRSKmSrSGxVnUOQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34610 | N | N | 30 | SUBSTATION-(LANDSCAPING,FENCES & CHANNEL WORKS) |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 360 | LABOR- SUBCONTRACTOR
%R | 503112 | 6359 | 125094 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBSSGL7925 | Soft landscaping around substation | 8305 | 280 | 0 | 240 | 0 | 480 | 480 | 240 | 0 | 0 | 0 |  |  |  | 2014-11-19 08:00 | 2014-12-24 17:00 |  | 2014-10-07 08:00 | 2014-11-12 17:00 | 2014-10-07 08:00 | 2014-11-12 17:00 | 2014-10-07 08:00 | 2014-11-12 17:00 | 2014-11-19 08:00 | 2014-12-24 17:00 |  | PT_Normal |  |  |  |  | 1Vc5tj8kSAixTDqYyl6DRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 45940 |  |  |  |  | LANDSCAPING SK | S312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34610 | N | N | 30 | SUBSTATION-(LANDSCAPING,FENCES & CHANNEL WORKS) |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10; period 2: 2014-AP11 |  | 240 | LANDSCAPING SK
%R | 503113 | 6359 | 125094 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBSSGL7930 | Construction of Drainage Channel | 8177 | 280 | 0 | 240 | 0 | 720 | 720 | 240 | 0 | 0 | 0 |  |  |  | 2014-10-22 08:00 | 2014-11-25 17:00 |  | 2014-09-09 08:00 | 2014-10-15 17:00 | 2014-09-09 08:00 | 2014-10-15 17:00 | 2014-09-09 08:00 | 2014-10-15 17:00 | 2014-10-22 08:00 | 2014-11-25 17:00 |  | PT_Normal |  |  |  |  | 6kx06Z56QBOfd+A9rtsZ/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34610 | N | N | 30 | SUBSTATION-(LANDSCAPING,FENCES & CHANNEL WORKS) |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 360 | LABOR - CIVIL
%R | 503114 | 6359 | 125094 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBSSGL7935 | Fencing Works | 8177 | 280 | 96 | 240 | 0 | 720 | 720 | 240 | 0 | 0 | 0 |  |  |  | 2014-12-03 08:00 | 2015-01-07 17:00 |  | 2014-10-23 08:00 | 2014-11-26 17:00 | 2014-10-23 08:00 | 2014-11-26 17:00 | 2014-10-23 08:00 | 2014-11-26 17:00 | 2014-12-03 08:00 | 2015-01-07 17:00 |  | PT_Normal |  |  |  |  | 6CBd8ciJRAOK+8Pm5g4osQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34610 | N | N | 30 | SUBSTATION-(LANDSCAPING,FENCES & CHANNEL WORKS) |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10; period 2: 2014-AP11 |  | 360 | LABOR - CIVIL
%R | 503115 | 6359 | 125095 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBGZGL7900 | Construction of Concrete structure | 8165 | 248 | 0 | 160 | 0 | 124 | 124 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-22 08:00 | 2014-10-16 17:00 |  | 2014-08-17 08:00 | 2014-09-08 17:00 | 2014-08-17 08:00 | 2014-09-08 17:00 | 2014-08-17 08:00 | 2014-09-08 17:00 | 2014-09-22 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | zs2FSQJhRqqfxT+02exsGQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34600 | N | N | 25 | GAZEBO |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 124 | STEEL FIXERS SK
%R | 503116 | 6359 | 125095 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBGZGL7905 | Installation of Wooden Works | 8178 | 248 | 0 | 200 | 0 | 300 | 300 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-04 08:00 | 2014-11-03 17:00 |  | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-08-28 08:00 | 2014-09-25 17:00 | 2014-10-04 08:00 | 2014-11-03 17:00 |  | PT_Normal |  |  |  |  | XeFpghYsSyayY/ngvzQ2Nw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34600 | N | N | 25 | GAZEBO |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 300 | LABOR- SUBCONTRACTOR
%R | 503117 | 6359 | 125095 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBGZGL7910 | Electrical Works-Gazebo | 8178 | 248 | 64 | 120 | 0 | 125.6 | 125.6 | 120 | 0 | 0 | 0 |  |  |  | 2014-11-04 08:00 | 2014-11-20 17:00 |  | 2014-09-27 08:00 | 2014-10-15 17:00 | 2014-09-27 08:00 | 2014-10-15 17:00 | 2014-09-27 08:00 | 2014-10-15 17:00 | 2014-11-04 08:00 | 2014-11-20 17:00 |  | PT_Normal |  |  |  |  | xSfcKYtbQ7WczSCjo+PBBw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34600 | N | N | 25 | GAZEBO |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 125.6 | LABOR- SUBCONTRACTOR
%R | 503118 | 6359 | 125095 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1ASBGZGL7915 | Park Benches Installation | 8178 | 328 | 80 | 120 | 0 | 120 | 120 | 120 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-03 17:00 |  | 2014-08-28 08:00 | 2014-09-14 17:00 | 2014-08-28 08:00 | 2014-09-14 17:00 | 2014-08-28 08:00 | 2014-09-14 17:00 | 2014-10-18 08:00 | 2014-11-03 17:00 |  | PT_Normal |  |  |  |  | 4cgzSm2+R/G7/WfHZls45g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34600 | N | N | 25 | GAZEBO |  | 125090 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 120 | LABOR- SUBCONTRACTOR
%R | 503119 | 6359 | 125098 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3DRGL5115 | Excavation for Drainage line | 8177 | 72 | 0 | 200 | 0 | 431 | 431 | 200 | 251 | 0 | 251 |  |  |  | 2014-01-07 08:00 | 2014-02-04 17:00 |  | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2014-01-07 08:00 | 2014-02-04 17:00 |  | PT_Normal |  |  |  |  | nK7JcpV6T2+xkB/uwTdKFA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34120 | N | N | 10 | DRAINAGE LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 431 | LABOR - CIVIL
%R | 503120 | 6359 | 125098 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3DRGL5120 | Laying of Drainage line | 8178 | 72 | 0 | 200 | 0 | 276 | 276 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-02-12 17:00 |  | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 |  | PT_Normal |  |  |  |  | uRFf/iBLR5Ot7w4s76x+7g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34120 | N | N | 10 | DRAINAGE LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 276 | LABOR- SUBCONTRACTOR
%R | 503121 | 6359 | 125098 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3DRGL5125 | Testing of Drainage line | 8178 | 72 | 0 | 200 | 0 | 134.4 | 134.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-20 17:00 |  | 2014-01-12 08:00 | 2014-02-09 17:00 | 2014-01-12 08:00 | 2014-02-09 17:00 | 2014-01-12 08:00 | 2014-02-09 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | 6cvsrlZGT3Cjw2L4JweGIw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34120 | N | N | 10 | DRAINAGE LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 503122 | 6359 | 125098 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3DRGL5130 | Backfilling Drainage line | 8177 | 72 | 0 | 120 | 0 | 402 | 402 | 120 | 330 | 0 | 330 |  |  |  | 2014-02-09 08:00 | 2014-02-26 17:00 |  | 2014-01-29 08:00 | 2014-02-16 17:00 | 2014-01-29 08:00 | 2014-02-16 17:00 | 2014-01-29 08:00 | 2014-02-16 17:00 | 2014-02-09 08:00 | 2014-02-26 17:00 |  | PT_Normal |  |  |  |  | 9BTImtqYQQ2hLko8BZLSuw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34120 | N | N | 10 | DRAINAGE LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 402 | LABOR - CIVIL
%R | 503123 | 6359 | 125099 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3BWGL5315 | Construction of Boundary Wall (Ht-3m) | 8165 | 560 | 0 | 200 | 0 | 224 | 224 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-17 08:00 | 2014-08-18 17:00 |  | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-07-17 08:00 | 2014-08-18 17:00 |  | PT_Normal |  |  |  |  | XT6/6CWLQU+PZ4zb/CKp4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34200 | N | N | 50 | BOUNDARY WALL |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 224 | STEEL FIXERS SK
%R | 503124 | 6359 | 125099 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 8178 | 560 | 0 | 200 | 0 | 28 | 28 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-06 08:00 | 2014-09-03 17:00 |  | 2014-05-13 08:00 | 2014-06-10 17:00 | 2014-05-13 08:00 | 2014-06-10 17:00 | 2014-05-13 08:00 | 2014-06-10 17:00 | 2014-08-06 08:00 | 2014-09-03 17:00 |  | PT_Normal |  |  |  |  | 13j6RWbBQ1yeOAQOT4TKBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34200 | N | N | 50 | BOUNDARY WALL |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 28 | LABOR- SUBCONTRACTOR
%R | 503125 | 6359 | 125099 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 8165 | 560 | 0 | 200 | 0 | 168 | 168 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-04 08:00 | 2014-10-02 17:00 |  | 2014-06-11 08:00 | 2014-07-09 17:00 | 2014-06-11 08:00 | 2014-07-09 17:00 | 2014-06-11 08:00 | 2014-07-09 17:00 | 2014-09-04 08:00 | 2014-10-02 17:00 |  | PT_Normal |  |  |  |  | 4urkWwhORTmv8/KkVt7yRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34200 | N | N | 50 | BOUNDARY WALL |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 168 | STEEL FIXERS SK
%R | 503126 | 6359 | 125099 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 8165 | 648 | 144 | 200 | 0 | 154 | 154 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-29 08:00 | 2014-10-29 17:00 |  | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-09-29 08:00 | 2014-10-29 17:00 |  | PT_Normal |  |  |  |  | dMpb+KDkRvSMY8ZeUQq2Ig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34200 | N | N | 50 | BOUNDARY WALL |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 154 | STEEL FIXERS SK
%R | 503127 | 6359 | 125100 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3SAGL5135 | Construction of manholes Drainage | 8177 | 592 | 144 | 200 | 0 | 6 | 6 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-27 08:00 | 2014-05-25 17:00 |  | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 |  | PT_Normal |  |  |  |  | 5pFFp1o6RmO4x2vJYwYuDg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34130 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 6 | LABOR - CIVIL
%R | 503128 | 6359 | 125100 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3SAGL5140 | Construction of soakaways | 8172 | 104 | 0 | 200 | 0 | 154 | 154 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-12 17:00 |  | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 |  | PT_Normal |  |  |  |  | gps9ivlcSM6nAgtBJOGfLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34130 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 154 | MANHOLES SK
%R | 503129 | 6359 | 125100 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3SAGL5145 | Construction of Road gullies | 8172 | 104 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-04-10 17:00 |  | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | D7BRcx+jT3SrPGQ4ilQ1Uw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34130 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 88 | MANHOLES SK
%R | 503130 | 6359 | 125100 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3SAGL5150 | Connection with existing sewer manhole | 8177 | 408 | 288 | 160 | 0 | 6 | 6 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-26 08:00 | 2014-06-17 17:00 |  | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-05-26 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | XUfVWwwWQGCjCNBwXN68uw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34130 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 6 | LABOR - CIVIL
%R | 503131 | 6359 | 125101 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3FFGL5185 | Excavation for firefighting line | 8177 | 88 | 0 | 200 | 0 | 283 | 283 | 200 | 151 | 0 | 151 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | uTPyv7TjR+GzdUT029XXtg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34150 | N | N | 25 | FIREFIGHTING LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 283 | LABOR - CIVIL
%R | 503132 | 6359 | 125101 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3FFGL5190 | Laying of firefighting line | 8178 | 88 | 0 | 200 | 0 | 303.6 | 303.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-27 08:00 | 2014-04-24 17:00 |  | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 |  | PT_Normal |  |  |  |  | tSkn+nbzR12z6RzSuiVthA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34150 | N | N | 25 | FIREFIGHTING LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 303.6 | LABOR- SUBCONTRACTOR
%R | 503133 | 6359 | 125101 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3FFGL5195 | Testing of firefighting line | 8178 | 88 | 0 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-02 08:00 | 2014-04-30 17:00 |  | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 |  | PT_Normal |  |  |  |  | Wtl7GGRURjmYQUf0EyU/gA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34150 | N | N | 25 | FIREFIGHTING LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 84 | LABOR- SUBCONTRACTOR
%R | 503134 | 6359 | 125101 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3FFGL5200 | Backfilling firefighting line | 8177 | 88 | 0 | 200 | 0 | 329 | 329 | 200 | 275 | 0 | 275 |  |  |  | 2014-04-08 08:00 | 2014-05-06 17:00 |  | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 |  | PT_Normal |  |  |  |  | FK5vHzXsSpGHxj65qfm+GA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34150 | N | N | 25 | FIREFIGHTING LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 329 | LABOR - CIVIL
%R | 503135 | 6359 | 125101 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3FFGL5205 | Construction of valve chambers & Thrust Blocks | 8165 | 296 | 0 | 200 | 0 | 202 | 202 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-14 08:00 | 2014-06-11 17:00 |  | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 |  | PT_Normal |  |  |  |  | 03yRKp1RSH+8oB1pkI1qvQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34150 | N | N | 25 | FIREFIGHTING LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 202 | STEEL FIXERS SK
%R | 503136 | 6359 | 125101 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3FFGL5210 | Connection with existing Firewater System | 8178 | 296 | 144 | 200 | 0 | 134.4 | 134.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-20 08:00 | 2014-06-17 17:00 |  | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34150 | N | N | 25 | FIREFIGHTING LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 503137 | 6359 | 125102 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3ELGL5215 | Excavation Cable Trenches & Duct Banks | 8177 | 120 | 0 | 200 | 0 | 1374 | 1374 | 200 | 600 | 0 | 600 |  |  |  | 2014-04-21 08:00 | 2014-05-19 17:00 |  | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | 45pd52IjTX6YB03PrbyxKw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34160 | N | N | 30 | ELECTRICAL LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1374 | LABOR - CIVIL
%R | 503138 | 6359 | 125102 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3ELGL5220 | Laying of electrical cables | 8178 | 144 | 0 | 200 | 0 | 1834.8 | 1834.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-30 08:00 | 2014-05-28 17:00 |  | 2014-04-09 08:00 | 2014-05-07 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 | 2014-04-30 08:00 | 2014-05-28 17:00 |  | PT_Normal |  |  |  |  | u8+Gch+cTp2Hvog3/53Qkg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34160 | N | N | 30 | ELECTRICAL LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1834.8 | LABOR- SUBCONTRACTOR
%R | 503139 | 6359 | 125102 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3ELGL5225 | Backfilling Electrical trench | 8177 | 144 | 0 | 200 | 0 | 862 | 862 | 200 | 550 | 0 | 550 |  |  |  | 2014-05-08 08:00 | 2014-06-05 17:00 |  | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 | 2014-05-08 08:00 | 2014-06-05 17:00 |  | PT_Normal |  |  |  |  | xLBr4u3SSqGqGHOzGXCodQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34160 | N | N | 30 | ELECTRICAL LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 862 | LABOR - CIVIL
%R | 503140 | 6359 | 125102 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3ELGL5230 | Construction of Submain Board & Feeder Pillar | 8165 | 616 | 0 | 200 | 0 | 224 | 224 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-28 08:00 | 2014-08-28 17:00 |  | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 | 2014-07-28 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | GK6ZesZ/QKCdBU19jY2Hgg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34160 | N | N | 30 | ELECTRICAL LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 224 | STEEL FIXERS SK
%R | 503141 | 6359 | 125103 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3STGL5235 | Excavation for Street lighting | 8177 | 120 | 0 | 200 | 0 | 69 | 69 | 200 | 51 | 0 | 51 |  |  |  | 2014-04-21 08:00 | 2014-05-19 17:00 |  | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34170 | N | N | 35 | STREET LIGHTING |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 69 | LABOR - CIVIL
%R | 503142 | 6359 | 125103 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3STGL5240 | Construction of Duct Banks | 8178 | 120 | 0 | 200 | 0 | 1192.8 | 1192.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-27 08:00 | 2014-05-25 17:00 |  | 2014-04-09 08:00 | 2014-05-07 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 |  | PT_Normal |  |  |  |  | CU6Fmtz/T3a4oKMtfFYK2A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34170 | N | N | 35 | STREET LIGHTING |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1192.8 | LABOR- SUBCONTRACTOR
%R | 503143 | 6359 | 125103 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3STGL5245 | Construction of Foundation | 8172 | 120 | 0 | 200 | 0 | 638 | 638 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-27 08:00 | 2014-05-25 17:00 |  | 2014-04-09 08:00 | 2014-05-07 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 |  | PT_Normal |  |  |  |  | fJSFhOwxS/at7HwpaNFolg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34170 | N | N | 35 | STREET LIGHTING |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 638 | MANHOLES SK
%R | 503144 | 6359 | 125103 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3STGL5250 | Backfilling Street Lighting | 8177 | 120 | 0 | 200 | 0 | 287 | 287 | 200 | 275 | 0 | 275 |  |  |  | 2014-05-03 08:00 | 2014-05-31 17:00 |  | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 |  | PT_Normal |  |  |  |  | n6oJX7UFTA2djj8ttyI36Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34170 | N | N | 35 | STREET LIGHTING |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 287 | LABOR - CIVIL
%R | 503145 | 6359 | 125103 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3STGL5255 | Installation of light Post | 8178 | 632 | 16 | 200 | 0 | 216 | 216 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-28 08:00 | 2014-08-28 17:00 |  | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-07-28 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | uQCFXi4SToaDqh3ZMOcTTA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34170 | N | N | 35 | STREET LIGHTING |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 216 | LABOR- SUBCONTRACTOR
%R | 503146 | 6359 | 125103 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3STGL5260 | Electrical Works | 8178 | 616 | 144 | 200 | 0 | 823.6 | 823.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-30 08:00 | 2014-09-27 17:00 |  | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-08-30 08:00 | 2014-09-27 17:00 |  | PT_Normal |  |  |  |  | oAJGqnU6QROOGbcGUGI0Jw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34170 | N | N | 35 | STREET LIGHTING |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 823.6 | LABOR- SUBCONTRACTOR
%R | 503147 | 6359 | 125104 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3RWGL6000 | Excavation & Earth Filling | 8177 | 120 | 0 | 80 | 0 | 1232 | 1232 | 80 | 500 | 0 | 500 |  |  |  | 2014-06-18 08:00 | 2014-06-29 17:00 |  | 2014-06-01 08:00 | 2014-06-11 17:00 | 2014-06-01 08:00 | 2014-06-11 17:00 | 2014-06-01 08:00 | 2014-06-11 17:00 | 2014-06-18 08:00 | 2014-06-29 17:00 |  | PT_Normal |  |  |  |  | HZxlx+x3R6umezzOe4q9NA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34210 | N | N | 55 | ROAD WORKS |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1232 | LABOR - CIVIL
%R | 503148 | 6359 | 125104 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3RWGL6005 | Laying of Sub Grade | 8178 | 120 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-30 08:00 | 2014-07-28 17:00 |  | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-30 08:00 | 2014-07-28 17:00 |  | PT_Normal |  |  |  |  | J1/dffhhR9OXt+/AHQulgw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34210 | N | N | 55 | ROAD WORKS |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 24 | LABOR- SUBCONTRACTOR
%R | 503149 | 6359 | 125104 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3RWGL6010 | Laying of Precast Kerbs | 8178 | 120 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-12 08:00 | 2014-08-12 17:00 |  | 2014-06-24 08:00 | 2014-07-22 17:00 | 2014-06-24 08:00 | 2014-07-22 17:00 | 2014-06-24 08:00 | 2014-07-22 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 |  | PT_Normal |  |  |  |  | Iabs8xMeR+unzZ1EoM63tQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34210 | N | N | 55 | ROAD WORKS |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 24 | LABOR- SUBCONTRACTOR
%R | 503150 | 6359 | 125104 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3RWGL6015 | Laying of Granular Sub Base Coarse | 8173 | 120 | 0 | 160 | 0 | 1814 | 1814 | 160 | 600 | 0 | 600 |  |  |  | 2014-07-23 08:00 | 2014-08-18 17:00 |  | 2014-07-06 08:00 | 2014-07-28 17:00 | 2014-07-06 08:00 | 2014-07-28 17:00 | 2014-07-06 08:00 | 2014-07-28 17:00 | 2014-07-23 08:00 | 2014-08-18 17:00 |  | PT_Normal |  |  |  |  | eiG7Lv/hTy2Q7vtJhyQbPQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34210 | N | N | 55 | ROAD WORKS |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1814 | KERBSTONE MASON SK
%R | 503151 | 6359 | 125104 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3RWGL6020 | Laying of Road Base Asphalt Concrete | 8178 | 360 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-09-23 08:00 | 2014-09-28 17:00 |  | 2014-07-29 08:00 | 2014-08-06 17:00 | 2014-07-29 08:00 | 2014-08-06 17:00 | 2014-07-29 08:00 | 2014-08-06 17:00 | 2014-09-23 08:00 | 2014-09-28 17:00 |  | PT_Normal |  |  |  |  | 6ciHV9kPSrWiY26YhK++sg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34210 | N | N | 55 | ROAD WORKS |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 174 | LABOR- SUBCONTRACTOR
%R | 503152 | 6359 | 125104 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3RWGL6025 | Laying of Asphalt Wearing Coarse | 8178 | 480 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-10-19 08:00 | 2014-10-23 17:00 |  | 2014-08-07 08:00 | 2014-08-12 17:00 | 2014-08-07 08:00 | 2014-08-12 17:00 | 2014-08-07 08:00 | 2014-08-12 17:00 | 2014-10-19 08:00 | 2014-10-23 17:00 |  | PT_Normal |  |  |  |  | Gr021jE1Q3+MzYyidZ4AnA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34210 | N | N | 55 | ROAD WORKS |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 174 | LABOR- SUBCONTRACTOR
%R | 503153 | 6359 | 125104 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3RWGL6030 | Traffic Signage & Road Marking | 8178 | 480 | 120 | 40 | 0 | 974 | 974 | 40 | 0 | 0 | 0 |  |  |  | 2014-10-25 08:00 | 2014-10-29 17:00 |  | 2014-08-13 08:00 | 2014-08-18 17:00 | 2014-08-13 08:00 | 2014-08-18 17:00 | 2014-08-13 08:00 | 2014-08-18 17:00 | 2014-10-25 08:00 | 2014-10-29 17:00 |  | PT_Normal |  |  |  |  | Bt/KR7vJSaGSz+QsrvsQjw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34210 | N | N | 55 | ROAD WORKS |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 974 | LABOR- SUBCONTRACTOR
%R | 503154 | 6359 | 125105 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3WSGL5155 | Excavation for water line | 8177 | 88 | 0 | 200 | 0 | 401 | 401 | 200 | 251 | 0 | 251 |  |  |  | 2014-02-24 08:00 | 2014-03-24 17:00 |  | 2014-02-10 08:00 | 2014-03-11 17:00 | 2014-02-10 08:00 | 2014-03-11 17:00 | 2014-02-10 08:00 | 2014-03-11 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | 82XIGZFFRcqYXtP9oa6SIQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34140 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 200.5 | LABOR - CIVIL
%R | 503155 | 6359 | 125105 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3WSGL5160 | Laying of water line | 8178 | 88 | 0 | 200 | 0 | 285.6 | 285.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-30 17:00 |  | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | B0YMeryfQ2miCBYHtV4+Qw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34140 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 142.8 | LABOR- SUBCONTRACTOR
%R | 503156 | 6359 | 125105 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3WSGL5165 | Testing of potable water line | 8178 | 88 | 0 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-04-05 17:00 |  | 2014-02-23 08:00 | 2014-03-23 17:00 | 2014-02-23 08:00 | 2014-03-23 17:00 | 2014-02-23 08:00 | 2014-03-23 17:00 | 2014-03-08 08:00 | 2014-04-05 17:00 |  | PT_Normal |  |  |  |  | e+FbSOw/R6i1dtwAKEum5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34140 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 42 | LABOR- SUBCONTRACTOR
%R | 503157 | 6359 | 125105 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3WSGL5170 | Backfilling potable water line | 8177 | 88 | 0 | 200 | 0 | 335 | 335 | 200 | 275 | 0 | 275 |  |  |  | 2014-03-13 08:00 | 2014-04-10 17:00 |  | 2014-03-01 08:00 | 2014-03-29 17:00 | 2014-03-01 08:00 | 2014-03-29 17:00 | 2014-03-01 08:00 | 2014-03-29 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | MWo6N5oFQ7KJe6Apq2Zj9A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34140 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 335 | LABOR - CIVIL
%R | 503158 | 6359 | 125105 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3WSGL5175 | Construction of valve chambers & Thrust Blocks | 8172 | 352 | 0 | 200 | 0 | 132 | 132 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-27 08:00 | 2014-05-25 17:00 |  | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-03-06 08:00 | 2014-04-03 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 |  | PT_Normal |  |  |  |  | p3JI1T+VRXyJtWKeBOyFJg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34140 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 132 | MANHOLES SK
%R | 503159 | 6359 | 125105 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3WSGL5180 | Installation of meter ,Accessories & Connection | 8178 | 352 | 56 | 160 | 0 | 50.4 | 50.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-26 08:00 | 2014-06-17 17:00 |  | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-04-05 08:00 | 2014-04-27 17:00 | 2014-05-26 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | tYfn27tCSpacL+tat8HjCg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34140 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 503160 | 6359 | 125106 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3TCGL5295 | Excavation Telecommunication trenches | 8177 | 120 | 0 | 160 | 0 | 528 | 528 | 160 | 300 | 0 | 300 |  |  |  | 2014-05-14 08:00 | 2014-06-05 17:00 |  | 2014-04-27 08:00 | 2014-05-19 17:00 | 2014-04-27 08:00 | 2014-05-19 17:00 | 2014-04-27 08:00 | 2014-05-19 17:00 | 2014-05-14 08:00 | 2014-06-05 17:00 |  | PT_Normal |  |  |  |  | d1S6MeDyQHObGCFxyD0Q7g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34190 | N | N | 45 | TELECOMMUNICATION LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 528 | LABOR - CIVIL
%R | 503161 | 6359 | 125106 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3TCGL5300 | Laying of cables | 8178 | 120 | 0 | 160 | 0 | 795.2 | 795.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-20 08:00 | 2014-06-11 17:00 |  | 2014-05-03 08:00 | 2014-05-25 17:00 | 2014-05-03 08:00 | 2014-05-25 17:00 | 2014-05-03 08:00 | 2014-05-25 17:00 | 2014-05-20 08:00 | 2014-06-11 17:00 |  | PT_Normal |  |  |  |  | SBeH3bQ/SP+q25gCFkYO6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34190 | N | N | 45 | TELECOMMUNICATION LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 795.2 | LABOR- SUBCONTRACTOR
%R | 503162 | 6359 | 125106 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3TCGL5305 | Backfilling telecommunication trench | 8177 | 120 | 0 | 160 | 0 | 530 | 530 | 160 | 440 | 0 | 440 |  |  |  | 2014-05-26 08:00 | 2014-06-17 17:00 |  | 2014-05-08 08:00 | 2014-05-31 17:00 | 2014-05-08 08:00 | 2014-05-31 17:00 | 2014-05-08 08:00 | 2014-05-31 17:00 | 2014-05-26 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | zPKBj1dDTz+1HC0+4jbWWw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34190 | N | N | 45 | TELECOMMUNICATION LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 530 | LABOR - CIVIL
%R | 503163 | 6359 | 125106 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3TCGL5310 | Connection & Installation | 8178 | 592 | 184 | 160 | 0 | 344.4 | 344.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-18 08:00 | 2014-09-09 17:00 |  | 2014-05-20 08:00 | 2014-06-11 17:00 | 2014-05-20 08:00 | 2014-06-11 17:00 | 2014-05-20 08:00 | 2014-06-11 17:00 | 2014-08-18 08:00 | 2014-09-09 17:00 |  | PT_Normal |  |  |  |  | BXvlQUWwT8+ON2DnEhWTnQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34190 | N | N | 45 | TELECOMMUNICATION LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 344.4 | LABOR- SUBCONTRACTOR
%R | 503164 | 6359 | 125107 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3SLGL7200 | Excavation | 8177 | 312 | 0 | 200 | 0 | 497 | 497 | 200 | 251 | 0 | 251 |  |  |  | 2014-08-24 08:00 | 2014-09-21 17:00 |  | 2014-07-06 08:00 | 2014-08-06 17:00 | 2014-07-06 08:00 | 2014-08-06 17:00 | 2014-07-06 08:00 | 2014-08-06 17:00 | 2014-08-24 08:00 | 2014-09-21 17:00 |  | PT_Normal |  |  |  |  | aHLdiNoBQm+KntDevP3KpA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34240 | N | N | 70 | SOFT LANDSCAPING |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 248.5 | LABOR - CIVIL
%R | 503165 | 6359 | 125107 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3SLGL7205 | Sweet Soil Laying | 8178 | 312 | 0 | 200 | 0 | 2380 | 2380 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-04 08:00 | 2014-10-02 17:00 |  | 2014-07-17 08:00 | 2014-08-18 17:00 | 2014-07-17 08:00 | 2014-08-18 17:00 | 2014-07-17 08:00 | 2014-08-18 17:00 | 2014-09-04 08:00 | 2014-10-02 17:00 |  | PT_Normal |  |  |  |  | F3klrIsBQimg/4V7jQbl2A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34240 | N | N | 70 | SOFT LANDSCAPING |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 1190 | LABOR- SUBCONTRACTOR
%R | 503166 | 6359 | 125107 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3SLGL7210 | Plantation works | 8178 | 472 | 144 | 200 | 0 | 588 | 588 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-12 08:00 | 2014-11-09 17:00 |  | 2014-07-29 08:00 | 2014-08-30 17:00 | 2014-07-29 08:00 | 2014-08-30 17:00 | 2014-07-29 08:00 | 2014-08-30 17:00 | 2014-10-12 08:00 | 2014-11-09 17:00 |  | PT_Normal |  |  |  |  | 4GLI1TjvRIOhdQTrSCBKDw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34240 | N | N | 70 | SOFT LANDSCAPING |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 294 | LABOR- SUBCONTRACTOR
%R | 503167 | 6359 | 125108 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3HDGL7020 | Precast Concrete Kerbs works | 8173 | 312 | 0 | 160 | 0 | 1178 | 1178 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-11 17:00 |  | 2014-06-01 08:00 | 2014-06-23 17:00 | 2014-06-01 08:00 | 2014-06-23 17:00 | 2014-06-01 08:00 | 2014-06-23 17:00 | 2014-07-16 08:00 | 2014-08-11 17:00 |  | PT_Normal |  |  |  |  | 3AWduIgOTT+9TCDoCuqZxA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34230 | N | N | 65 | HARD LANDSCAPING |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1178 | KERBSTONE MASON SK
%R | 503168 | 6359 | 125108 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3HDGL7025 | Interlocking for Walkways | 8174 | 312 | 0 | 200 | 0 | 806 | 806 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-28 08:00 | 2014-08-28 17:00 |  | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 | 2014-07-28 08:00 | 2014-08-28 17:00 |  | PT_Normal |  |  |  |  | qkIPwiOPTcSl9phttx1YCA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34230 | N | N | 65 | HARD LANDSCAPING |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 806 | INTERLOCK MASON SK
%R | 503169 | 6359 | 125108 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3HDGL7030 | Construction of Retaining wall | 8165 | 312 | 0 | 200 | 0 | 756 | 756 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-09-09 17:00 |  | 2014-06-24 08:00 | 2014-07-22 17:00 | 2014-06-24 08:00 | 2014-07-22 17:00 | 2014-06-24 08:00 | 2014-07-22 17:00 | 2014-08-12 08:00 | 2014-09-09 17:00 |  | PT_Normal |  |  |  |  | 4DzirRtZTaqCSQcR2cYsZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34230 | N | N | 65 | HARD LANDSCAPING |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 756 | STEEL FIXERS SK
%R | 503170 | 6359 | 125108 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3HDGL7040 | Construction of Speed Humps | 8167 | 592 | 264 | 80 | 0 | 14 | 14 | 80 | 0 | 0 | 0 |  |  |  | 2014-11-10 08:00 | 2014-11-20 17:00 |  | 2014-08-13 08:00 | 2014-08-24 17:00 | 2014-08-13 08:00 | 2014-08-24 17:00 | 2014-08-13 08:00 | 2014-08-24 17:00 | 2014-11-10 08:00 | 2014-11-20 17:00 |  | PT_Normal |  |  |  |  | VNZkBlPvRsWgYrNs1ArGFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34230 | N | N | 65 | HARD LANDSCAPING |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 14 | CONCRETE MASON SK
%R | 503171 | 6359 | 125108 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3HDGL7035 | Construction of Wash Stone Boulders | 8170 | 312 | 0 | 200 | 0 | 88 | 88 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-12 08:00 | 2014-09-09 17:00 |  | 2014-06-24 08:00 | 2014-07-22 17:00 | 2014-06-24 08:00 | 2014-07-22 17:00 | 2014-06-24 08:00 | 2014-07-22 17:00 | 2014-08-12 08:00 | 2014-09-09 17:00 |  | PT_Normal |  |  |  |  | nKGkk6mhTMy22IHRXii7XA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34230 | N | N | 65 | HARD LANDSCAPING |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 88 | TILE MASON SK
%R | 503172 | 6359 | 125109 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3IRGL5265 | Excavation for irrigation line | 8177 | 320 | 0 | 200 | 0 | 812 | 812 | 200 | 500 | 0 | 500 |  |  |  | 2014-07-02 08:00 | 2014-07-30 17:00 |  | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 | 2014-07-02 08:00 | 2014-07-30 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34180 | N | N | 40 | IRRIGATION LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 812 | LABOR - CIVIL
%R | 503173 | 6359 | 125109 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3IRGL5270 | Laying of irrigationline | 8178 | 320 | 0 | 200 | 0 | 386.4 | 386.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-08 08:00 | 2014-08-09 17:00 |  | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-07-08 08:00 | 2014-08-09 17:00 |  | PT_Normal |  |  |  |  | 2X0kpmBDQH+0vv9UaJWHnQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34180 | N | N | 40 | IRRIGATION LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 386.4 | LABOR- SUBCONTRACTOR
%R | 503174 | 6359 | 125109 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3IRGL5275 | Testing of irrigation line | 8178 | 320 | 0 | 200 | 0 | 319.2 | 319.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-14 08:00 | 2014-08-14 17:00 |  | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 | 2014-07-14 08:00 | 2014-08-14 17:00 |  | PT_Normal |  |  |  |  | JMhRrOoqSpafW9ujvnCf/A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34180 | N | N | 40 | IRRIGATION LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 319.2 | LABOR- SUBCONTRACTOR
%R | 503175 | 6359 | 125109 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3IRGL5280 | Backfilling irrigation line | 8177 | 320 | 0 | 200 | 0 | 676 | 676 | 200 | 550 | 0 | 550 |  |  |  | 2014-07-20 08:00 | 2014-08-20 17:00 |  | 2014-06-03 08:00 | 2014-07-01 17:00 | 2014-06-03 08:00 | 2014-07-01 17:00 | 2014-06-03 08:00 | 2014-07-01 17:00 | 2014-07-20 08:00 | 2014-08-20 17:00 |  | PT_Normal |  |  |  |  | itCYlkLRQNChhi7nSdJNTg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34180 | N | N | 40 | IRRIGATION LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 676 | LABOR - CIVIL
%R | 503176 | 6359 | 125109 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3IRGL5285 | Construction of Thrust Blocks,Pull boxes | 8178 | 400 | 0 | 200 | 0 | 116.4 | 116.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-16 08:00 | 2014-09-13 17:00 |  | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-06-15 08:00 | 2014-07-13 17:00 | 2014-08-16 08:00 | 2014-09-13 17:00 |  | PT_Normal |  |  |  |  | kqKu1QanSyy0FkbLLflF0A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34180 | N | N | 40 | IRRIGATION LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 116.4 | LABOR- SUBCONTRACTOR
%R | 503177 | 6359 | 125109 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3IRGL5290 | Irrigation Fittings (Nozzle,Values) | 8178 | 400 | 88 | 200 | 0 | 285.6 | 285.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-24 08:00 | 2014-09-21 17:00 |  | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-08-24 08:00 | 2014-09-21 17:00 |  | PT_Normal |  |  |  |  | 0oSWNe6UToa3Q2iAAwjLlQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34180 | N | N | 40 | IRRIGATION LINES |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 285.6 | LABOR- SUBCONTRACTOR
%R | 503178 | 6359 | 125110 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3PSGL7010 | Column, Frame& Fabrics Erection | 8178 | 360 | 0 | 200 | 0 | 286 | 286 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-29 08:00 | 2014-10-29 17:00 |  | 2014-08-07 08:00 | 2014-09-04 17:00 | 2014-08-07 08:00 | 2014-09-04 17:00 | 2014-08-07 08:00 | 2014-09-04 17:00 | 2014-09-29 08:00 | 2014-10-29 17:00 |  | PT_Normal |  |  |  |  | cZM56tgAS5ylmcn9YDkTAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34220 | N | N | 60 | PARKING SHED |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 286 | LABOR- SUBCONTRACTOR
%R | 503179 | 6359 | 125110 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3PSGL7015 | Electrical Works-Parking Shed | 8178 | 360 | 144 | 200 | 0 | 51.6 | 51.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-05 08:00 | 2014-11-04 17:00 |  | 2014-08-13 08:00 | 2014-09-10 17:00 | 2014-08-13 08:00 | 2014-09-10 17:00 | 2014-08-13 08:00 | 2014-09-10 17:00 | 2014-10-05 08:00 | 2014-11-04 17:00 |  | PT_Normal |  |  |  |  | ps9c3MzUQ82u82YEIETZkw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34220 | N | N | 60 | PARKING SHED |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 51.6 | LABOR- SUBCONTRACTOR
%R | 503180 | 6359 | 125110 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3PSGL7000 | Excavation | 8177 | 400 | 40 | 120 | 0 | 148 | 148 | 120 | 76 | 0 | 76 |  |  |  | 2014-09-11 08:00 | 2014-09-28 17:00 |  | 2014-07-12 08:00 | 2014-07-28 17:00 | 2014-07-12 08:00 | 2014-07-28 17:00 | 2014-07-12 08:00 | 2014-07-28 17:00 | 2014-09-11 08:00 | 2014-09-28 17:00 |  | PT_Normal |  |  |  |  | 94Td96/ETBWzyGlpWUrOVg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34220 | N | N | 60 | PARKING SHED |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 148 | LABOR - CIVIL
%R | 503181 | 6359 | 125110 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI1AZ3PSGL7005 | Foundation casting | 8165 | 360 | 0 | 120 | 0 | 252 | 252 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-17 08:00 | 2014-10-04 17:00 |  | 2014-07-23 08:00 | 2014-08-12 17:00 | 2014-07-23 08:00 | 2014-08-12 17:00 | 2014-07-23 08:00 | 2014-08-12 17:00 | 2014-09-17 08:00 | 2014-10-04 17:00 |  | PT_Normal |  |  |  |  | bdAyGhJ7T3GNBcesIqVH2A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 34220 | N | N | 60 | PARKING SHED |  | 125097 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 252 | STEEL FIXERS SK
%R | 503182 | 6359 | 125115 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1STUG1000 | Footing Excavation | 8177 | 0 | 0 | 200 | 0 | 476 | 476 | 200 | 224 | 0 | 224 |  |  |  | 2013-02-23 08:00 | 2013-03-23 17:00 |  | 2013-02-23 08:00 | 2013-03-23 17:00 | 2013-02-23 08:00 | 2013-03-23 17:00 | 2013-02-23 08:00 | 2013-03-23 17:00 | 2013-02-23 08:00 | 2013-03-23 17:00 |  | PT_Normal |  |  |  |  | tcbPa7nGRECUyGtIEcd2mg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38010 | N | N | 10 | UPTO GRADE SLAB |  | 125114 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 238 | LABOR - CIVIL
%R | 503183 | 6359 | 125115 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1STUG1005 | Footing Antitermite | 8178 | 0 | 0 | 160 | 0 | 902 | 902 | 160 | 0 | 0 | 0 |  |  |  | 2013-03-06 08:00 | 2013-03-28 17:00 |  | 2013-03-06 08:00 | 2013-03-28 17:00 | 2013-03-06 08:00 | 2013-03-28 17:00 | 2013-03-06 08:00 | 2013-03-28 17:00 | 2013-03-06 08:00 | 2013-03-28 17:00 |  | PT_Normal |  |  |  |  | 6VFfSVciTFevENoUcnk7yQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38010 | N | N | 10 | UPTO GRADE SLAB |  | 125114 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 902 | LABOR- SUBCONTRACTOR
%R | 503184 | 6359 | 125115 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1STUG1010 | Footing Blinding | 8163 | 0 | 0 | 160 | 0 | 29.75 | 29.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-03-09 08:00 | 2013-03-31 17:00 |  | 2013-03-09 08:00 | 2013-03-31 17:00 | 2013-03-09 08:00 | 2013-03-31 17:00 | 2013-03-09 08:00 | 2013-03-31 17:00 | 2013-03-09 08:00 | 2013-03-31 17:00 |  | PT_Normal |  |  |  |  | mPAbhiXYR+CI0pXuXRVr4A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38010 | N | N | 10 | UPTO GRADE SLAB |  | 125114 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 29.75 | BLINDING MASON SK
%R | 503185 | 6359 | 125115 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1STUG1015 | Footing Waterproofing & Screed | 8164 | 0 | 0 | 160 | 0 | 681 | 681 | 160 | 0 | 0 | 0 |  |  |  | 2013-03-12 08:00 | 2013-04-03 17:00 |  | 2013-03-12 08:00 | 2013-04-03 17:00 | 2013-03-12 08:00 | 2013-04-03 17:00 | 2013-03-12 08:00 | 2013-04-03 17:00 | 2013-03-12 08:00 | 2013-04-03 17:00 |  | PT_Normal |  |  |  |  | c+azP95WR6aqECpMfsTcsA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38010 | N | N | 10 | UPTO GRADE SLAB |  | 125114 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 681 | SCREED MASON SK
%R | 503186 | 6359 | 125115 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1STUG1020 | Construction of foundations | 8165 | 0 | 0 | 160 | 0 | 1335.25 | 1335.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-03-24 08:00 | 2013-04-15 17:00 |  | 2013-03-24 08:00 | 2013-04-15 17:00 | 2013-03-24 08:00 | 2013-04-15 17:00 | 2013-03-24 08:00 | 2013-04-15 17:00 | 2013-03-24 08:00 | 2013-04-15 17:00 |  | PT_Normal |  |  |  |  | 5kDqrzvCSf+3dP4lzIOnwQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38010 | N | N | 10 | UPTO GRADE SLAB |  | 125114 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 1335.25 | STEEL FIXERS SK
%R | 503187 | 6359 | 125115 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1STUG1025 | Construction of neck of columns | 8165 | 0 | 0 | 160 | 0 | 1389.5 | 1389.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-04-02 08:00 | 2013-04-24 17:00 |  | 2013-04-02 08:00 | 2013-04-24 17:00 | 2013-04-02 08:00 | 2013-04-24 17:00 | 2013-04-02 08:00 | 2013-04-24 17:00 | 2013-04-02 08:00 | 2013-04-24 17:00 |  | PT_Normal |  |  |  |  | wvTJSOHqRc2obecF4VpDcw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38010 | N | N | 10 | UPTO GRADE SLAB |  | 125114 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 1389.5 | STEEL FIXERS SK
%R | 503188 | 6359 | 125115 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1STUG1030 | Waterproofing Footing & Neck Column | 8178 | 0 | 0 | 160 | 0 | 125.5 | 125.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-04-11 08:00 | 2013-05-04 17:00 |  | 2013-04-11 08:00 | 2013-05-04 17:00 | 2013-04-11 08:00 | 2013-05-04 17:00 | 2013-04-11 08:00 | 2013-05-04 17:00 | 2013-04-11 08:00 | 2013-05-04 17:00 |  | PT_Normal |  |  |  |  | N7IimtouQ/mrDvTEVOWxbA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38010 | N | N | 10 | UPTO GRADE SLAB |  | 125114 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 125.5 | LABOR- SUBCONTRACTOR
%R | 503189 | 6359 | 125115 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 0 | 0 | 160 | 0 | 822 | 822 | 160 | 660 | 0 | 660 |  |  |  | 2013-04-23 08:00 | 2013-05-15 17:00 |  | 2013-04-23 08:00 | 2013-05-15 17:00 | 2013-04-23 08:00 | 2013-05-15 17:00 | 2013-04-23 08:00 | 2013-05-15 17:00 | 2013-04-23 08:00 | 2013-05-15 17:00 |  | PT_Normal |  |  |  |  | 8jRfWeDGT82ErmeZeSbKGQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38010 | N | N | 10 | UPTO GRADE SLAB |  | 125114 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 822 | LABOR - CIVIL
%R | 503190 | 6359 | 125115 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1STUG1040 | Construction of Grade Beams | 8163 | 0 | 0 | 200 | 0 | 2514.75 | 2514.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-05-05 08:00 | 2013-06-02 17:00 |  | 2013-05-05 08:00 | 2013-06-02 17:00 | 2013-05-05 08:00 | 2013-06-02 17:00 | 2013-05-05 08:00 | 2013-06-02 17:00 | 2013-05-05 08:00 | 2013-06-02 17:00 |  | PT_Normal |  |  |  |  | y4K6TIc/RJmgrvHA05YiZQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38010 | N | N | 10 | UPTO GRADE SLAB |  | 125114 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 2514.75 | BLINDING MASON SK
%R | 503191 | 6359 | 125115 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1STUG1045 | Construction of slab on grade | 8163 | 0 | 0 | 200 | 0 | 1541.75 | 1541.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-02 08:00 | 2013-06-30 17:00 |  | 2013-06-02 08:00 | 2013-06-30 17:00 | 2013-06-02 08:00 | 2013-06-30 17:00 | 2013-06-02 08:00 | 2013-06-30 17:00 | 2013-06-02 08:00 | 2013-06-30 17:00 |  | PT_Normal |  |  |  |  | HlsLiUHAR+KIByvve8GmPw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38010 | N | N | 10 | UPTO GRADE SLAB |  | 125114 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 1541.75 | BLINDING MASON SK
%R | 503192 | 6359 | 125117 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1STRF2060 | Construction of Parapets | 8165 | 0 | 0 | 160 | 0 | 521.5 | 521.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-08-01 08:00 | 2013-08-27 17:00 |  | 2013-08-01 08:00 | 2013-08-27 17:00 | 2013-08-01 08:00 | 2013-08-27 17:00 | 2013-08-01 08:00 | 2013-08-27 17:00 | 2013-08-01 08:00 | 2013-08-27 17:00 |  | PT_Normal |  |  |  |  | oOxRZD5BRIqUhkO4wavoBA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38050 | N | N | 20 | ROOF |  | 125116 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 521.5 | STEEL FIXERS SK
%R | 503193 | 6359 | 125117 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1STRF2065 | Construction of up stands/Plinth | 8166 | 240 | 0 | 160 | 0 | 84 | 84 | 160 | 0 | 0 | 0 |  |  |  | 2013-09-16 08:00 | 2013-10-08 17:00 |  | 2013-08-08 08:00 | 2013-09-03 17:00 | 2013-08-08 08:00 | 2013-09-03 17:00 | 2013-08-08 08:00 | 2013-09-03 17:00 | 2013-09-16 08:00 | 2013-10-08 17:00 |  | PT_Normal |  |  |  |  | 6oan1iwcReK3q49UKHLgMw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38050 | N | N | 20 | ROOF |  | 125116 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 84 | CARPENTERS SK
%R | 503194 | 6359 | 125118 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1STGF2000 | Column-Rebar & Formwork | 8165 | 0 | 0 | 160 | 0 | 1524.25 | 1524.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-06-19 08:00 | 2013-07-11 17:00 |  | 2013-06-19 08:00 | 2013-07-11 17:00 | 2013-06-19 08:00 | 2013-07-11 17:00 | 2013-06-19 08:00 | 2013-07-11 17:00 | 2013-06-19 08:00 | 2013-07-11 17:00 |  | PT_Normal |  |  |  |  | 1rqk3qMiR1uI25f3vtB7Lg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38030 | N | N | 10 | GROUND FLOOR |  | 125116 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 1524.25 | STEEL FIXERS SK
%R | 503195 | 6359 | 125118 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1STGF2005 | Column-Concrete | 8167 | 0 | 0 | 120 | 0 | 105 | 105 | 120 | 0 | 0 | 0 |  |  |  | 2013-06-30 08:00 | 2013-07-16 17:00 |  | 2013-06-30 08:00 | 2013-07-16 17:00 | 2013-06-30 08:00 | 2013-07-16 17:00 | 2013-06-30 08:00 | 2013-07-16 17:00 | 2013-06-30 08:00 | 2013-07-16 17:00 |  | PT_Normal |  |  |  |  | vxw5AT+jQaWSy7TI8RtQFA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38030 | N | N | 10 | GROUND FLOOR |  | 125116 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 105 | CONCRETE MASON SK
%R | 503196 | 6359 | 125118 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 6076 | 6076 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-08 08:00 | 2013-08-05 17:00 |  | 2013-07-08 08:00 | 2013-08-05 17:00 | 2013-07-08 08:00 | 2013-08-05 17:00 | 2013-07-08 08:00 | 2013-08-05 17:00 | 2013-07-08 08:00 | 2013-08-05 17:00 |  | PT_Normal |  |  |  |  | Ucq1LKlrSr+opnkGqGuHBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38030 | N | N | 10 | GROUND FLOOR |  | 125116 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 6076 | STEEL FIXERS SK
%R | 503197 | 6359 | 125118 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 0 | 0 | 120 | 0 | 1302 | 1302 | 120 | 0 | 0 | 0 |  |  |  | 2013-07-24 08:00 | 2013-08-13 17:00 |  | 2013-07-24 08:00 | 2013-08-13 17:00 | 2013-07-24 08:00 | 2013-08-13 17:00 | 2013-07-24 08:00 | 2013-08-13 17:00 | 2013-07-24 08:00 | 2013-08-13 17:00 |  | PT_Normal |  |  |  |  | FpDBoRDJRb+RmQDORWe8Fg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38030 | N | N | 10 | GROUND FLOOR |  | 125116 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 1302 | CONCRETE MASON SK
%R | 503198 | 6359 | 125120 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 232 | 16 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | W4j3he9tRY6larcg7TZKsw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:45 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38290 | N | N | 10 | MISCELLANEOUS |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 400 | LABOR- SUBCONTRACTOR
%R | 503199 | 6359 | 125120 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1MSEX5020 | Construction Entrance Ramp | 8164 | 240 | 0 | 160 | 0 | 363.25 | 363.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-10-28 08:00 | 2013-11-19 17:00 |  | 2013-09-21 08:00 | 2013-10-13 17:00 | 2013-09-21 08:00 | 2013-10-13 17:00 | 2013-09-21 08:00 | 2013-10-13 17:00 | 2013-10-28 08:00 | 2013-11-19 17:00 |  | PT_Normal |  |  |  |  | bBMxTBeXTuGX8loJBOBJ3Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38290 | N | N | 10 | MISCELLANEOUS |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 363.25 | SCREED MASON SK
%R | 503200 | 6359 | 125120 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1MSEX5025 | SS.Handrails and Balustrades | 8178 | 280 | 0 | 160 | 0 | 112.75 | 112.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-20 08:00 | 2013-12-12 17:00 |  | 2013-10-08 08:00 | 2013-11-02 17:00 | 2013-10-08 08:00 | 2013-11-02 17:00 | 2013-10-08 08:00 | 2013-11-02 17:00 | 2013-11-20 08:00 | 2013-12-12 17:00 |  | PT_Normal |  |  |  |  | FE84Rl+ISP64I7dCC9fIJg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38290 | N | N | 10 | MISCELLANEOUS |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 112.75 | LABOR- SUBCONTRACTOR
%R | 503201 | 6359 | 125120 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1MSEX5015 | Construction of grease Trap | 8178 | 336 | 0 | 160 | 0 | 139.75 | 139.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-24 08:00 | 2014-01-15 17:00 |  | 2013-11-04 08:00 | 2013-11-26 17:00 | 2013-11-04 08:00 | 2013-11-26 17:00 | 2013-11-04 08:00 | 2013-11-26 17:00 | 2013-12-24 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | kSvPE+qETGmTp/Ben2AJiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38290 | N | N | 10 | MISCELLANEOUS |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 139.75 | LABOR- SUBCONTRACTOR
%R | 503202 | 6359 | 125120 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1MSEX5005 | Construction of Soak pit, Chambers | 8172 | 336 | 0 | 200 | 0 | 55 | 55 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-03 08:00 | 2014-01-01 17:00 |  | 2013-10-13 08:00 | 2013-11-12 17:00 | 2013-10-13 08:00 | 2013-11-12 17:00 | 2013-10-13 08:00 | 2013-11-12 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 |  | PT_Normal |  |  |  |  | NC/vulh/RE+TIRsES+FWzg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38290 | N | N | 10 | MISCELLANEOUS |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 55 | MANHOLES SK
%R | 503203 | 6359 | 125120 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1MSEX5055 | Installation Steel Door | 8178 | 280 | 0 | 160 | 0 | 180 | 180 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-09 08:00 | 2013-12-01 17:00 |  | 2013-09-26 08:00 | 2013-10-21 17:00 | 2013-09-26 08:00 | 2013-10-21 17:00 | 2013-09-26 08:00 | 2013-10-21 17:00 | 2013-11-09 08:00 | 2013-12-01 17:00 |  | PT_Normal |  |  |  |  | AXTOFpFCS1a+OVpYL6L/sA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38290 | N | N | 10 | MISCELLANEOUS |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 180 | LABOR- SUBCONTRACTOR
%R | 503204 | 6359 | 125120 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1MSEX5010 | Telephone cable laying | 8177 | 480 | 72 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-03-08 17:00 |  | 2013-11-27 08:00 | 2013-12-26 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | 1NsWiWwoTYO2sxrjED/B2w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38290 | N | N | 10 | MISCELLANEOUS |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 500 | LABOR - CIVIL
%R | 503205 | 6359 | 125120 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1MSEX5000 | Construction of Manholes | 8172 | 336 | 0 | 200 | 0 | 110 | 110 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-19 08:00 | 2013-12-17 17:00 |  | 2013-09-29 08:00 | 2013-10-29 17:00 | 2013-09-29 08:00 | 2013-10-29 17:00 | 2013-09-29 08:00 | 2013-10-29 17:00 | 2013-11-19 08:00 | 2013-12-17 17:00 |  | PT_Normal |  |  |  |  | woNND/0dSKa85hbw9sV+Fg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38290 | N | N | 10 | MISCELLANEOUS |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 55 | MANHOLES SK
%R | 503206 | 6359 | 125121 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1SLEX5105 | Laying of Grass/ green area | 8178 | 168 | 0 | 160 | 0 | 1785 | 1785 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-07 08:00 | 2014-01-29 17:00 |  | 2013-12-12 08:00 | 2014-01-05 17:00 | 2013-12-12 08:00 | 2014-01-05 17:00 | 2013-12-12 08:00 | 2014-01-05 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | KvML0d+4S66R57PA0cTQaQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38320 | N | N | 25 | SOFT LANDSCAPING |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1785 | LABOR- SUBCONTRACTOR
%R | 503207 | 6359 | 125121 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1SLEX5110 | Laying of Palm tree | 8178 | 488 | 0 | 160 | 0 | 455 | 455 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-30 17:00 |  | 2013-12-25 08:00 | 2014-01-16 17:00 | 2013-12-25 08:00 | 2014-01-16 17:00 | 2013-12-25 08:00 | 2014-01-16 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | ScszIDXSTN2c3PASCKWjBw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38320 | N | N | 25 | SOFT LANDSCAPING |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 455 | LABOR- SUBCONTRACTOR
%R | 503208 | 6359 | 125122 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1WEEX5030 | Excavation | 8177 | 120 | 0 | 160 | 0 | 110 | 110 | 160 | 80 | 0 | 80 |  |  |  | 2013-10-12 08:00 | 2013-11-05 17:00 |  | 2013-09-24 08:00 | 2013-10-16 17:00 | 2013-09-24 08:00 | 2013-10-16 17:00 | 2013-09-24 08:00 | 2013-10-16 17:00 | 2013-10-12 08:00 | 2013-11-05 17:00 |  | PT_Normal |  |  |  |  | 22+oT0Y9RgKq0MFS1byiqw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38300 | N | N | 15 | WATER TANK ENCLOSURE |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 110 | LABOR - CIVIL
%R | 503209 | 6359 | 125122 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1WEEX5035 | Construction of Raft | 8167 | 200 | 0 | 200 | 0 | 175 | 175 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-03 08:00 | 2013-12-01 17:00 |  | 2013-10-02 08:00 | 2013-11-02 17:00 | 2013-10-02 08:00 | 2013-11-02 17:00 | 2013-10-02 08:00 | 2013-11-02 17:00 | 2013-11-03 08:00 | 2013-12-01 17:00 |  | PT_Normal |  |  |  |  | OgDBqtiLSsaRr9jcFaghBQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38300 | N | N | 15 | WATER TANK ENCLOSURE |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 87.5 | CONCRETE MASON SK
%R | 503210 | 6359 | 125122 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1WEEX5040 | Block works & Plastering | 8168 | 200 | 0 | 200 | 0 | 577 | 577 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-12 08:00 | 2013-12-10 17:00 |  | 2013-10-12 08:00 | 2013-11-11 17:00 | 2013-10-12 08:00 | 2013-11-11 17:00 | 2013-10-12 08:00 | 2013-11-11 17:00 | 2013-11-12 08:00 | 2013-12-10 17:00 |  | PT_Normal |  |  |  |  | X5YtncoXQK2G78VXo+lZAg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38300 | N | N | 15 | WATER TANK ENCLOSURE |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 577 | BLOCK MASON SK
%R | 503211 | 6359 | 125122 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1WEEX5050 | Installation of Steel Gate | 8178 | 200 | 0 | 160 | 0 | 125 | 125 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-11 08:00 | 2014-01-04 17:00 |  | 2013-11-12 08:00 | 2013-12-04 17:00 | 2013-11-12 08:00 | 2013-12-04 17:00 | 2013-11-12 08:00 | 2013-12-04 17:00 | 2013-12-11 08:00 | 2014-01-04 17:00 |  | PT_Normal |  |  |  |  | famvELzSQdKzu47+q7CVyw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38300 | N | N | 15 | WATER TANK ENCLOSURE |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 125 | LABOR- SUBCONTRACTOR
%R | 503212 | 6359 | 125122 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 200 | 120 | 200 | 0 | 445.25 | 445.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-17 08:00 | 2014-01-15 17:00 |  | 2013-11-18 08:00 | 2013-12-16 17:00 | 2013-11-18 08:00 | 2013-12-16 17:00 | 2013-11-18 08:00 | 2013-12-16 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | IrI2qCz1RJOLF6RSAwupBw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38300 | N | N | 15 | WATER TANK ENCLOSURE |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 445.25 | LABOR- SUBCONTRACTOR
%R | 503213 | 6359 | 125122 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 80 | 0 | 200 | 0 | 239 | 239 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-30 08:00 | 2014-01-27 17:00 |  | 2013-12-17 08:00 | 2014-01-15 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 |  | PT_Normal |  |  |  |  | XIgGErlHS+6EPwy6o8fVzw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38300 | N | N | 15 | WATER TANK ENCLOSURE |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 239 | LABOR- SUBCONTRACTOR
%R | 503214 | 6359 | 125122 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1WEEX5070 | Installation ladder for water Tank | 8178 | 160 | 40 | 160 | 0 | 200 | 200 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-19 08:00 | 2014-02-10 17:00 |  | 2013-12-26 08:00 | 2014-01-18 17:00 | 2013-12-26 08:00 | 2014-01-18 17:00 | 2013-12-26 08:00 | 2014-01-18 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | usVKajLTSEuyyxdRiOdOPA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38300 | N | N | 15 | WATER TANK ENCLOSURE |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 200 | LABOR- SUBCONTRACTOR
%R | 503215 | 6359 | 125122 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1WEEX5045 | Flooring & Painting | 8164 | 200 | 0 | 200 | 0 | 280.25 | 280.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-24 08:00 | 2013-12-23 17:00 |  | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-11-24 08:00 | 2013-12-23 17:00 |  | PT_Normal |  |  |  |  | 60xPq/h1SZi6ZeqZjnhL/Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38300 | N | N | 15 | WATER TANK ENCLOSURE |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 280.25 | SCREED MASON SK
%R | 503216 | 6359 | 125123 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1HDEX5090 | kerb works | 8173 | 280 | 0 | 160 | 0 | 196.75 | 196.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-28 08:00 | 2013-12-22 17:00 |  | 2013-10-16 08:00 | 2013-11-10 17:00 | 2013-10-16 08:00 | 2013-11-10 17:00 | 2013-10-16 08:00 | 2013-11-10 17:00 | 2013-11-28 08:00 | 2013-12-22 17:00 |  | PT_Normal |  |  |  |  | p4F5DrBBT1ipOqP7nWkkvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38310 | N | N | 20 | HARD LANDSCAPING |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 196.75 | KERBSTONE MASON SK
%R | 503217 | 6359 | 125123 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1HDEX5095 | Cobble Stone Works | 8170 | 280 | 0 | 160 | 0 | 71.75 | 71.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-10 08:00 | 2014-01-02 17:00 |  | 2013-10-30 08:00 | 2013-11-21 17:00 | 2013-10-30 08:00 | 2013-11-21 17:00 | 2013-10-30 08:00 | 2013-11-21 17:00 | 2013-12-10 08:00 | 2014-01-02 17:00 |  | PT_Normal |  |  |  |  | fRLu0NptSo6iS376wUJu3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38310 | N | N | 20 | HARD LANDSCAPING |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 71.75 | TILE MASON SK
%R | 503218 | 6359 | 125123 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1HDEX5100 | Interlock works | 8174 | 280 | 112 | 160 | 0 | 249.75 | 249.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-26 08:00 | 2014-01-18 17:00 |  | 2013-11-14 08:00 | 2013-12-07 17:00 | 2013-11-14 08:00 | 2013-12-07 17:00 | 2013-11-14 08:00 | 2013-12-07 17:00 | 2013-12-26 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | m7a17atASlWBRZurjpNoNQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38310 | N | N | 20 | HARD LANDSCAPING |  | 125119 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 249.75 | INTERLOCK MASON SK
%R | 503219 | 6359 | 125126 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ACGF4600 | Installation AC Pipes | 8178 | 224 | 0 | 160 | 0 | 463.75 | 463.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-06 08:00 | 2013-11-28 17:00 |  | 2013-10-02 08:00 | 2013-10-27 17:00 | 2013-10-02 08:00 | 2013-10-27 17:00 | 2013-10-02 08:00 | 2013-10-27 17:00 | 2013-11-06 08:00 | 2013-11-28 17:00 |  | PT_Normal |  |  |  |  | lFtV+0PSRICqgK3uPsyUsA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38240 | N | N | 10 | GROUND FLOOR |  | 125125 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 463.75 | LABOR- SUBCONTRACTOR
%R | 503220 | 6359 | 125126 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ACGF4605 | Fixing of Ventilation Equipments | 8178 | 272 | 0 | 200 | 0 | 71 | 71 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-03-13 17:00 |  | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 |  | PT_Normal |  |  |  |  | ftbviXZ+SAe35FckroVMuA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38240 | N | N | 10 | GROUND FLOOR |  | 125125 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 71 | LABOR- SUBCONTRACTOR
%R | 503221 | 6359 | 125126 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ACGF4610 | Fixing of Split AC | 8178 | 272 | 0 | 160 | 0 | 129 | 129 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-30 17:00 |  | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | 0uv8jVqcTq+0Lb1Jwc2sjw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38240 | N | N | 10 | GROUND FLOOR |  | 125125 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 129 | LABOR- SUBCONTRACTOR
%R | 503222 | 6359 | 125127 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ACRF4630 | Installation of Refrigerant Pipes | 8178 | 528 | 48 | 160 | 0 | 15.05 | 15.05 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-07 08:00 | 2014-01-29 17:00 |  | 2013-10-21 08:00 | 2013-11-12 17:00 | 2013-10-21 08:00 | 2013-11-12 17:00 | 2013-10-21 08:00 | 2013-11-12 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | Sclw8b9XQ+C3dOIu0RsxPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38260 | N | N | 20 | ROOF |  | 125125 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 15.05 | LABOR- SUBCONTRACTOR
%R | 503223 | 6359 | 125127 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ACRF4635 | Installation of Condensing Unit | 8178 | 312 | 0 | 200 | 0 | 108.75 | 108.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | Ji/j6U7wSFqtJVEAW3yyeg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38260 | N | N | 20 | ROOF |  | 125125 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 54.375 | LABOR- SUBCONTRACTOR
%R | 503224 | 6359 | 125129 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ELRF4070 | Installation of Isolator | 8178 | 384 | 0 | 144 | 0 | 301 | 301 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-08 17:00 |  | 2014-01-21 08:00 | 2014-02-10 17:00 | 2014-01-21 08:00 | 2014-02-10 17:00 | 2014-01-21 08:00 | 2014-02-10 17:00 | 2014-03-19 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | 3Ugs88zXStCLj6K0tvvaRQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38180 | N | N | 20 | ROOF |  | 125128 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 301 | LABOR- SUBCONTRACTOR
%R | 503225 | 6359 | 125129 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ELRF4075 | Installation of TV Dish Antenna | 8178 | 384 | 0 | 160 | 0 | 157 | 157 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-22 17:00 |  | 2014-02-02 08:00 | 2014-02-25 17:00 | 2014-02-02 08:00 | 2014-02-25 17:00 | 2014-02-02 08:00 | 2014-02-25 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | Ke5gB0bUS1G2I5P7l/AbjA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38180 | N | N | 20 | ROOF |  | 125128 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 157 | LABOR- SUBCONTRACTOR
%R | 503226 | 6359 | 125130 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 56 | 0 | 160 | 0 | 494.95 | 494.95 | 160 | 0 | 0 | 0 |  |  |  | 2013-09-19 08:00 | 2013-10-12 17:00 |  | 2013-09-11 08:00 | 2013-10-03 17:00 | 2013-09-11 08:00 | 2013-10-03 17:00 | 2013-09-11 08:00 | 2013-10-03 17:00 | 2013-09-19 08:00 | 2013-10-12 17:00 |  | PT_Normal |  |  |  |  | fUMeuUY/RhqeZF+IxuX8og |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38160 | N | N | 10 | GROUND FLOOR |  | 125128 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 494.95 | LABOR- SUBCONTRACTOR
%R | 503227 | 6359 | 125130 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ELGF4005 | Cable tray & trunking installation | 8178 | 104 | 0 | 160 | 0 | 1704 | 1704 | 160 | 0 | 0 | 0 |  |  |  | 2013-10-05 08:00 | 2013-10-29 17:00 |  | 2013-09-19 08:00 | 2013-10-12 17:00 | 2013-09-19 08:00 | 2013-10-12 17:00 | 2013-09-19 08:00 | 2013-10-12 17:00 | 2013-10-05 08:00 | 2013-10-29 17:00 |  | PT_Normal |  |  |  |  | erAt+7zGSIiJLKRZ/ZW3Yw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38160 | N | N | 10 | GROUND FLOOR |  | 125128 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1704 | LABOR- SUBCONTRACTOR
%R | 503228 | 6359 | 125130 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ELGF4010 | Installation of wiring & Main Cabling | 8178 | 328 | 272 | 160 | 0 | 345.2 | 345.2 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-17 08:00 | 2013-12-09 17:00 |  | 2013-09-28 08:00 | 2013-10-22 17:00 | 2013-09-28 08:00 | 2013-10-22 17:00 | 2013-09-28 08:00 | 2013-10-22 17:00 | 2013-11-17 08:00 | 2013-12-09 17:00 |  | PT_Normal |  |  |  |  | SyNlqynBTIiHWMMYZ2YxHQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38160 | N | N | 10 | GROUND FLOOR |  | 125128 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 345.2 | LABOR- SUBCONTRACTOR
%R | 503229 | 6359 | 125130 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 384 | 0 | 160 | 0 | 142 | 142 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-16 17:00 |  | 2013-12-26 08:00 | 2014-01-18 17:00 | 2013-12-26 08:00 | 2014-01-18 17:00 | 2013-12-26 08:00 | 2014-01-18 17:00 | 2014-02-22 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | /BPRhDvTR5qfZ6vaZ3aPwA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38160 | N | N | 10 | GROUND FLOOR |  | 125128 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 142 | LABOR- SUBCONTRACTOR
%R | 503230 | 6359 | 125130 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 384 | 0 | 160 | 0 | 328.95 | 328.95 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-05 08:00 | 2014-03-27 17:00 |  | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-03-05 08:00 | 2014-03-27 17:00 |  | PT_Normal |  |  |  |  | XqA95MLAS/2eIFtAb5U7fg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38160 | N | N | 10 | GROUND FLOOR |  | 125128 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 328.95 | LABOR- SUBCONTRACTOR
%R | 503231 | 6359 | 125130 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 104 | 0 | 160 | 0 | 924 | 924 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-19 08:00 | 2014-02-10 17:00 |  | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-01-04 08:00 | 2014-01-26 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | ruNjfSJaTzqxCA+Ysu5s5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38160 | N | N | 10 | GROUND FLOOR |  | 125128 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 924 | LABOR- SUBCONTRACTOR
%R | 503232 | 6359 | 125130 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ELGF4030 | Installation of Telephone System | 8178 | 408 | 0 | 160 | 0 | 127 | 127 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-03-31 17:00 |  | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-03-09 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | ZKCAaJLCTYafgP/DNYKODg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38160 | N | N | 10 | GROUND FLOOR |  | 125128 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 127 | LABOR- SUBCONTRACTOR
%R | 503233 | 6359 | 125132 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 48 | 0 | 160 | 0 | 1195.8 | 1195.8 | 160 | 0 | 0 | 0 |  |  |  | 2013-09-19 08:00 | 2013-10-12 17:00 |  | 2013-09-12 08:00 | 2013-10-05 17:00 | 2013-09-12 08:00 | 2013-10-05 17:00 | 2013-09-12 08:00 | 2013-10-05 17:00 | 2013-09-19 08:00 | 2013-10-12 17:00 |  | PT_Normal |  |  |  |  | ljUsuWTNS3mU8bxmm+2xSw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38200 | N | N | 10 | GROUND FLOOR |  | 125131 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1195.8 | LABOR- SUBCONTRACTOR
%R | 503234 | 6359 | 125132 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1PLGF4310 | Installation of Drainage pipes &testing | 8178 | 240 | 0 | 144 | 0 | 59.55 | 59.55 | 144 | 0 | 0 | 0 |  |  |  | 2013-10-22 08:00 | 2013-11-11 17:00 |  | 2013-09-15 08:00 | 2013-10-05 17:00 | 2013-09-15 08:00 | 2013-10-05 17:00 | 2013-09-15 08:00 | 2013-10-05 17:00 | 2013-10-22 08:00 | 2013-11-11 17:00 |  | PT_Normal |  |  |  |  | Pfx9RsAbQka4Owe3DHMr3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38200 | N | N | 10 | GROUND FLOOR |  | 125131 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 59.55 | LABOR- SUBCONTRACTOR
%R | 503235 | 6359 | 125132 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1PLGF4315 | Sanitary Fittings & Accessories | 8178 | 56 | 0 | 160 | 0 | 182.7 | 182.7 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-02-04 17:00 |  | 2014-01-05 08:00 | 2014-01-27 17:00 | 2014-01-05 08:00 | 2014-01-27 17:00 | 2014-01-05 08:00 | 2014-01-27 17:00 | 2014-01-13 08:00 | 2014-02-04 17:00 |  | PT_Normal |  |  |  |  | 8Bsg1Y9GR7SHZBlllvzAyg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38200 | N | N | 10 | GROUND FLOOR |  | 125131 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 182.7 | LABOR- SUBCONTRACTOR
%R | 503236 | 6359 | 125132 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1PLGF4320 | Installation of Water Heater | 8178 | 496 | 0 | 120 | 0 | 126 | 126 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-04-28 17:00 |  | 2014-01-28 08:00 | 2014-02-15 17:00 | 2014-01-28 08:00 | 2014-02-15 17:00 | 2014-01-28 08:00 | 2014-02-15 17:00 | 2014-04-12 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | mEP/UDLvRTOvQZjkE0x+yQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38200 | N | N | 10 | GROUND FLOOR |  | 125131 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 126 | LABOR- SUBCONTRACTOR
%R | 503237 | 6359 | 125132 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 0 | 0 | 160 | 0 | 182.4 | 182.4 | 160 | 0 | 0 | 0 |  |  |  | 2013-05-23 08:00 | 2013-06-15 17:00 |  | 2013-05-23 08:00 | 2013-06-15 17:00 | 2013-05-23 08:00 | 2013-06-15 17:00 | 2013-05-23 08:00 | 2013-06-15 17:00 | 2013-05-23 08:00 | 2013-06-15 17:00 |  | PT_Normal |  |  |  |  | JkQKFW48SkOPoNagRxdr/w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38200 | N | N | 10 | GROUND FLOOR |  | 125131 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 182.4 | LABOR- SUBCONTRACTOR
%R | 503238 | 6359 | 125133 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1PLRF4350 | Installation of Rain water Pipes | 8178 | 120 | 0 | 120 | 0 | 221.7 | 221.7 | 120 | 0 | 0 | 0 |  |  |  | 2013-12-24 08:00 | 2014-01-09 17:00 |  | 2013-12-05 08:00 | 2013-12-23 17:00 | 2013-12-05 08:00 | 2013-12-23 17:00 | 2013-12-05 08:00 | 2013-12-23 17:00 | 2013-12-24 08:00 | 2014-01-09 17:00 |  | PT_Normal |  |  |  |  | hI6hvq2tT861UWIYmMIVVg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38220 | N | N | 20 | ROOF |  | 125131 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 221.7 | LABOR- SUBCONTRACTOR
%R | 503239 | 6359 | 125134 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 472 | 472 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | 0ieLHMBFR4ulBCP7GL6htQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38330 | N | N | 30 | TESTING AND COMMISSIONING |  | 125112 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 503240 | 6359 | 125134 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 472 | 472 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | rlYiK9sZRque0l9er9qAdg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38330 | N | N | 30 | TESTING AND COMMISSIONING |  | 125112 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 503241 | 6359 | 125134 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 472 | 472 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | hxgIh8HdSYC5k6dneaaFpQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38330 | N | N | 30 | TESTING AND COMMISSIONING |  | 125112 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 503242 | 6359 | 125137 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARGF3045 | Fixing of Suspension systems | 8178 | 56 | 0 | 120 | 0 | 543.75 | 543.75 | 120 | 0 | 0 | 0 |  |  |  | 2013-12-09 08:00 | 2013-12-26 17:00 |  | 2013-12-01 08:00 | 2013-12-17 17:00 | 2013-12-01 08:00 | 2013-12-17 17:00 | 2013-12-01 08:00 | 2013-12-17 17:00 | 2013-12-09 08:00 | 2013-12-26 17:00 |  | PT_Normal |  |  |  |  | 4kg43StqSmOFTd2mAc/Log |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38080 | N | N | 10 | GROUND FLOOR |  | 125136 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 543.75 | LABOR- SUBCONTRACTOR
%R | 503243 | 6359 | 125137 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARGF3060 | Gypsum board false ceiling | 8178 | 56 | 0 | 160 | 0 | 543.75 | 543.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-26 08:00 | 2014-01-18 17:00 |  | 2013-12-17 08:00 | 2014-01-09 17:00 | 2013-12-17 08:00 | 2014-01-09 17:00 | 2013-12-17 08:00 | 2014-01-09 17:00 | 2013-12-26 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | rcmVlDH/RZmtdzZTvnLDRw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38080 | N | N | 10 | GROUND FLOOR |  | 125136 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 543.75 | LABOR- SUBCONTRACTOR
%R | 503244 | 6359 | 125137 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARGF3065 | Wooden door | 8178 | 56 | 0 | 120 | 0 | 165 | 165 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-07 08:00 | 2014-01-23 17:00 |  | 2013-12-30 08:00 | 2014-01-15 17:00 | 2013-12-30 08:00 | 2014-01-15 17:00 | 2013-12-30 08:00 | 2014-01-15 17:00 | 2014-01-07 08:00 | 2014-01-23 17:00 |  | PT_Normal |  |  |  |  | ilJC+b8MT5qx+6r/TuJIXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38080 | N | N | 10 | GROUND FLOOR |  | 125136 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 165 | LABOR- SUBCONTRACTOR
%R | 503245 | 6359 | 125137 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARGF3080 | Aluminum windows | 8178 | 352 | 16 | 144 | 0 | 110 | 110 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-10 08:00 | 2014-03-30 17:00 |  | 2014-01-16 08:00 | 2014-02-05 17:00 | 2014-01-16 08:00 | 2014-02-05 17:00 | 2014-01-16 08:00 | 2014-02-05 17:00 | 2014-03-10 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | pBbSBZ1TStaCw0YAP+leTA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38080 | N | N | 10 | GROUND FLOOR |  | 125136 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 110 | LABOR- SUBCONTRACTOR
%R | 503246 | 6359 | 125137 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARGF3075 | Carpentry & Joinery Works | 8178 | 80 | 0 | 144 | 0 | 440 | 440 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-02-05 17:00 |  | 2014-01-05 08:00 | 2014-01-25 17:00 | 2014-01-05 08:00 | 2014-01-25 17:00 | 2014-01-05 08:00 | 2014-01-25 17:00 | 2014-01-16 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | YiCfvQexQSaLpiSqsiXDBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38080 | N | N | 10 | GROUND FLOOR |  | 125136 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 440 | LABOR- SUBCONTRACTOR
%R | 503247 | 6359 | 125137 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARGF3090 | Installation of Granite Counter Top | 8171 | 104 | 40 | 120 | 0 | 82.5 | 82.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-02-17 17:00 |  | 2014-01-15 08:00 | 2014-02-01 17:00 | 2014-01-15 08:00 | 2014-02-01 17:00 | 2014-01-15 08:00 | 2014-02-01 17:00 | 2014-01-30 08:00 | 2014-02-17 17:00 |  | PT_Normal |  |  |  |  | yM/zvpkOTZSX9QPt5neVLQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38080 | N | N | 10 | GROUND FLOOR |  | 125136 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 82.5 | GRANITE MASON SK
%R | 503248 | 6359 | 125137 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARGF3095 | Final Painting | 8178 | 272 | 0 | 200 | 0 | 1501.5 | 1501.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-02-06 08:00 | 2014-03-08 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | poPc71djSkGekzR3vmj/Gg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38080 | N | N | 10 | GROUND FLOOR |  | 125136 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 750.75 | LABOR- SUBCONTRACTOR
%R | 503249 | 6359 | 125137 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARGF3000 | Block work | 8168 | 48 | 0 | 200 | 0 | 4750 | 4750 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-04 08:00 | 2013-10-02 17:00 |  | 2013-08-28 08:00 | 2013-09-25 17:00 | 2013-08-28 08:00 | 2013-09-25 17:00 | 2013-08-28 08:00 | 2013-09-25 17:00 | 2013-09-04 08:00 | 2013-10-02 17:00 |  | PT_Normal |  |  |  |  | wZqifH4qTay8d286EBXJEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38080 | N | N | 10 | GROUND FLOOR |  | 125136 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 4750 | BLOCK MASON SK
%R | 503250 | 6359 | 125137 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARGF3005 | Plastering work | 8169 | 48 | 0 | 200 | 0 | 2375 | 2375 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-25 08:00 | 2013-10-26 17:00 |  | 2013-09-18 08:00 | 2013-10-16 17:00 | 2013-09-18 08:00 | 2013-10-16 17:00 | 2013-09-18 08:00 | 2013-10-16 17:00 | 2013-09-25 08:00 | 2013-10-26 17:00 |  | PT_Normal |  |  |  |  | eJdL+44YTVeCUya320EAwg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38080 | N | N | 10 | GROUND FLOOR |  | 125136 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 2375 | PLASTER MASON SK
%R | 503251 | 6359 | 125137 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARGF3010 | Flooring screed | 8164 | 200 | 0 | 160 | 0 | 528 | 528 | 160 | 0 | 0 | 0 |  |  |  | 2013-10-31 08:00 | 2013-11-23 17:00 |  | 2013-09-30 08:00 | 2013-10-24 17:00 | 2013-09-30 08:00 | 2013-10-24 17:00 | 2013-09-30 08:00 | 2013-10-24 17:00 | 2013-10-31 08:00 | 2013-11-23 17:00 |  | PT_Normal |  |  |  |  | EVpLyObYTeS58sspStRR+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38080 | N | N | 10 | GROUND FLOOR |  | 125136 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 528 | SCREED MASON SK
%R | 503252 | 6359 | 125137 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 56 | 0 | 160 | 0 | 71.5 | 71.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2013-11-04 17:00 |  | 2013-10-02 08:00 | 2013-10-27 17:00 | 2013-10-02 08:00 | 2013-10-27 17:00 | 2013-10-02 08:00 | 2013-10-27 17:00 | 2013-10-10 08:00 | 2013-11-04 17:00 |  | PT_Normal |  |  |  |  | zSfl/1LeRlC2Hv3rdwLKGQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38080 | N | N | 10 | GROUND FLOOR |  | 125136 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 71.5 | LABOR- SUBCONTRACTOR
%R | 503253 | 6359 | 125137 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARGF3030 | Paint First coat | 8178 | 48 | 0 | 160 | 0 | 1501.5 | 1501.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-10-13 08:00 | 2013-11-06 17:00 |  | 2013-10-06 08:00 | 2013-10-30 17:00 | 2013-10-06 08:00 | 2013-10-30 17:00 | 2013-10-06 08:00 | 2013-10-30 17:00 | 2013-10-13 08:00 | 2013-11-06 17:00 |  | PT_Normal |  |  |  |  | 5TAVl4MrQVKnw37HWnyG5Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38080 | N | N | 10 | GROUND FLOOR |  | 125136 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1501.5 | LABOR- SUBCONTRACTOR
%R | 503254 | 6359 | 125137 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARGF3020 | Ceramic Wall Tiling | 8170 | 56 | 0 | 120 | 0 | 843.75 | 843.75 | 120 | 0 | 0 | 0 |  |  |  | 2013-10-31 08:00 | 2013-11-17 17:00 |  | 2013-10-23 08:00 | 2013-11-09 17:00 | 2013-10-23 08:00 | 2013-11-09 17:00 | 2013-10-23 08:00 | 2013-11-09 17:00 | 2013-10-31 08:00 | 2013-11-17 17:00 |  | PT_Normal |  |  |  |  | gfj3t1qpSUS7OVlqqmF+rQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38080 | N | N | 10 | GROUND FLOOR |  | 125136 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 843.75 | TILE MASON SK
%R | 503255 | 6359 | 125137 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARGF3025 | Porcelain Tile flooring | 8170 | 56 | 0 | 160 | 0 | 858 | 858 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-17 08:00 | 2013-12-09 17:00 |  | 2013-11-09 08:00 | 2013-12-01 17:00 | 2013-11-09 08:00 | 2013-12-01 17:00 | 2013-11-09 08:00 | 2013-12-01 17:00 | 2013-11-17 08:00 | 2013-12-09 17:00 |  | PT_Normal |  |  |  |  | 9Hsd+Cn6Ty6eAU5+wZucgg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38080 | N | N | 10 | GROUND FLOOR |  | 125136 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 858 | TILE MASON SK
%R | 503256 | 6359 | 125137 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARGF3040 | Cobble Tile flooring | 8170 | 248 | 40 | 120 | 0 | 250 | 250 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-21 08:00 | 2014-02-06 17:00 |  | 2013-12-15 08:00 | 2014-01-01 17:00 | 2013-12-15 08:00 | 2014-01-01 17:00 | 2013-12-15 08:00 | 2014-01-01 17:00 | 2014-01-21 08:00 | 2014-02-06 17:00 |  | PT_Normal |  |  |  |  | T2K7uMcrSr2zjFwV0Zh8ng |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38080 | N | N | 10 | GROUND FLOOR |  | 125136 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 250 | TILE MASON SK
%R | 503257 | 6359 | 125137 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 120 | 0 | 144 | 0 | 1312.5 | 1312.5 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-14 08:00 | 2014-01-04 17:00 |  | 2013-11-26 08:00 | 2013-12-16 17:00 | 2013-11-26 08:00 | 2013-12-16 17:00 | 2013-11-26 08:00 | 2013-12-16 17:00 | 2013-12-14 08:00 | 2014-01-04 17:00 |  | PT_Normal |  |  |  |  | k/1VT27XQ7qT9v955KGD1w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38080 | N | N | 10 | GROUND FLOOR |  | 125136 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1312.5 | TILE MASON SK
%R | 503258 | 6359 | 125139 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1AREL3665 | External Plastering | 8169 | 280 | 0 | 200 | 0 | 3343.75 | 3343.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-21 08:00 | 2013-12-21 17:00 |  | 2013-10-09 08:00 | 2013-11-09 17:00 | 2013-10-09 08:00 | 2013-11-09 17:00 | 2013-10-09 08:00 | 2013-11-09 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 |  | PT_Normal |  |  |  |  | gmYw3fYnR324Mc+u2F2OIA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38130 | N | N | 15 | ELEVATION |  | 125138 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 1671.875 | PLASTER MASON SK
%R | 503259 | 6359 | 125139 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1AREL3680 | External Painting | 8178 | 520 | 80 | 160 | 0 | 1173.25 | 1173.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-19 08:00 | 2014-02-10 17:00 |  | 2013-11-03 08:00 | 2013-11-25 17:00 | 2013-11-03 08:00 | 2013-11-25 17:00 | 2013-11-03 08:00 | 2013-11-25 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | gW4e2LUiSHCDnC122AQvAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38130 | N | N | 15 | ELEVATION |  | 125138 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1173.25 | LABOR- SUBCONTRACTOR
%R | 503260 | 6359 | 125140 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARRF3625 | Laying of Pitched Roof | 8174 | 240 | 0 | 200 | 0 | 213 | 213 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-30 08:00 | 2013-10-30 17:00 |  | 2013-08-26 08:00 | 2013-09-23 17:00 | 2013-08-26 08:00 | 2013-09-23 17:00 | 2013-08-26 08:00 | 2013-09-23 17:00 | 2013-09-30 08:00 | 2013-10-30 17:00 |  | PT_Normal |  |  |  |  | ZHsSh6WySwuBSKmkc1w2gg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38120 | N | N | 10 | ROOF |  | 125138 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 213 | INTERLOCK MASON SK
%R | 503261 | 6359 | 125140 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARRF3630 | Leveling Screed for Waterproofing | 8164 | 240 | 0 | 144 | 0 | 162.5 | 162.5 | 144 | 0 | 0 | 0 |  |  |  | 2013-10-14 08:00 | 2013-11-05 17:00 |  | 2013-09-09 08:00 | 2013-09-29 17:00 | 2013-09-09 08:00 | 2013-09-29 17:00 | 2013-09-09 08:00 | 2013-09-29 17:00 | 2013-10-14 08:00 | 2013-11-05 17:00 |  | PT_Normal |  |  |  |  | Bskb8SXtRTu2IMgo4oieGA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38120 | N | N | 10 | ROOF |  | 125138 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 162.5 | SCREED MASON SK
%R | 503262 | 6359 | 125140 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARRF3635 | Laying of Waterproofing Membrane | 8178 | 280 | 0 | 144 | 0 | 602.25 | 602.25 | 144 | 0 | 0 | 0 |  |  |  | 2013-10-28 08:00 | 2013-11-17 17:00 |  | 2013-09-15 08:00 | 2013-10-05 17:00 | 2013-09-15 08:00 | 2013-10-05 17:00 | 2013-09-15 08:00 | 2013-10-05 17:00 | 2013-10-28 08:00 | 2013-11-17 17:00 |  | PT_Normal |  |  |  |  | A6HhLCkIRvGW0B0NBmNCZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38120 | N | N | 10 | ROOF |  | 125138 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 602.25 | LABOR- SUBCONTRACTOR
%R | 503263 | 6359 | 125140 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARRF3640 | Installation of Insulation & Protection | 8178 | 280 | 0 | 144 | 0 | 286 | 286 | 144 | 0 | 0 | 0 |  |  |  | 2013-11-02 08:00 | 2013-11-21 17:00 |  | 2013-09-19 08:00 | 2013-10-09 17:00 | 2013-09-19 08:00 | 2013-10-09 17:00 | 2013-09-19 08:00 | 2013-10-09 17:00 | 2013-11-02 08:00 | 2013-11-21 17:00 |  | PT_Normal |  |  |  |  | HoLxOQYNRBGYup9pYlqWhA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38120 | N | N | 10 | ROOF |  | 125138 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 286 | LABOR- SUBCONTRACTOR
%R | 503264 | 6359 | 125140 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 280 | 0 | 144 | 0 | 286 | 286 | 144 | 0 | 0 | 0 |  |  |  | 2013-11-10 08:00 | 2013-11-30 17:00 |  | 2013-09-28 08:00 | 2013-10-20 17:00 | 2013-09-28 08:00 | 2013-10-20 17:00 | 2013-09-28 08:00 | 2013-10-20 17:00 | 2013-11-10 08:00 | 2013-11-30 17:00 |  | PT_Normal |  |  |  |  | FcUkL18aSIuVF8/F1mUiow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38120 | N | N | 10 | ROOF |  | 125138 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 286 | TILE MASON SK
%R | 503265 | 6359 | 125140 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ1ARRF3660 | Installation of Access Ladder | 8178 | 632 | 80 | 160 | 0 | 110 | 110 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-07 08:00 | 2014-01-29 17:00 |  | 2013-10-03 08:00 | 2013-10-28 17:00 | 2013-10-03 08:00 | 2013-10-28 17:00 | 2013-10-03 08:00 | 2013-10-28 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | tGT83NyMSIGTPCjXDGpIfg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38120 | N | N | 10 | ROOF |  | 125138 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 110 | LABOR- SUBCONTRACTOR
%R | 503266 | 6359 | 125141 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AGNSP001000 | Survey works, | 8175 | 0 | 0 | 160 | 0 | 87.5 | 87.5 | 160 | 0 | 0 | 0 |  |  |  | 2012-11-18 08:00 | 2012-12-10 17:00 |  | 2012-11-18 08:00 | 2012-12-10 17:00 | 2012-11-18 08:00 | 2012-12-10 17:00 | 2012-11-18 08:00 | 2012-12-10 17:00 | 2012-11-18 08:00 | 2012-12-10 17:00 |  | PT_Normal |  |  |  |  | BDH0J36fTXW9a/8S19uIew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43520 |  |  |  |  | SURVEYOR SK | J315 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37680 | N | N | 03 | SITE PREPARATORY WORKS |  | 125111 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 87.5 | SURVEYOR SK
%R | 503267 | 6359 | 125141 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AGNSP002000 | Scanning for Existing Services for rerouting | 8180 | 0 | 0 | 80 | 0 | 325 | 325 | 80 | 0 | 0 | 0 |  |  |  | 2012-12-05 08:00 | 2012-12-16 17:00 |  | 2012-12-05 08:00 | 2012-12-16 17:00 | 2012-12-05 08:00 | 2012-12-16 17:00 | 2012-12-05 08:00 | 2012-12-16 17:00 | 2012-12-05 08:00 | 2012-12-16 17:00 |  | PT_Normal |  |  |  |  | ppORvVg9TQa2iVzStsC4GA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43571 |  |  |  |  | ELECTRICIANS SK | M302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37680 | N | N | 03 | SITE PREPARATORY WORKS |  | 125111 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 325 | ELECTRICIANS SK
%R | 503268 | 6359 | 125141 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AGNSP003000 | Site stripping | 8177 | 384 | 0 | 160 | 0 | 675 | 675 | 160 | 300 | 0 | 300 |  |  |  | 2013-01-31 08:00 | 2013-02-24 17:00 |  | 2012-12-05 08:00 | 2012-12-29 17:00 | 2012-12-05 08:00 | 2012-12-29 17:00 | 2012-12-05 08:00 | 2012-12-29 17:00 | 2013-01-31 08:00 | 2013-02-24 17:00 |  | PT_Normal |  |  |  |  | x3vQuk97RSGzyaMP8SKfXQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37680 | N | N | 03 | SITE PREPARATORY WORKS |  | 125111 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 675 | LABOR - CIVIL
%R | 503269 | 6359 | 125141 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AGNSP004000 | Demolition of Existing building & landscaping | 8177 | 384 | 0 | 160 | 0 | 2687.5 | 2687.5 | 160 | 1750 | 0 | 1750 |  |  |  | 2013-02-07 08:00 | 2013-03-03 17:00 |  | 2012-12-12 08:00 | 2013-01-05 17:00 | 2012-12-12 08:00 | 2013-01-05 17:00 | 2012-12-12 08:00 | 2013-01-05 17:00 | 2013-02-07 08:00 | 2013-03-03 17:00 |  | PT_Normal |  |  |  |  | 181qLHsJSj2bKe2EPrq2ew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37680 | N | N | 03 | SITE PREPARATORY WORKS |  | 125111 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 2687.5 | LABOR - CIVIL
%R | 503270 | 6359 | 125141 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AGNSP005000 | Demolition of existing services works | 8177 | 384 | 384 | 160 | 0 | 775 | 775 | 160 | 400 | 0 | 400 |  |  |  | 2013-02-16 08:00 | 2013-03-10 17:00 |  | 2012-12-20 08:00 | 2013-01-12 17:00 | 2012-12-20 08:00 | 2013-01-12 17:00 | 2012-12-20 08:00 | 2013-01-12 17:00 | 2013-02-16 08:00 | 2013-03-10 17:00 |  | PT_Normal |  |  |  |  | ojasJTNFQoGfOrqnRlczMw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37680 | N | N | 03 | SITE PREPARATORY WORKS |  | 125111 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 775 | LABOR - CIVIL
%R | 503271 | 6359 | 125141 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AGNSP002100 | Submission of Scanning Reports |  | 0 | 0 | 56 | 0 | 48 | 48 | 56 | 0 | 0 | 0 |  |  |  | 2012-12-17 08:00 | 2012-12-25 17:00 |  | 2012-12-17 08:00 | 2012-12-25 17:00 | 2012-12-17 08:00 | 2012-12-25 17:00 | 2012-12-17 08:00 | 2012-12-25 17:00 | 2012-12-17 08:00 | 2012-12-25 17:00 |  | PT_Normal |  |  |  |  | FB9ABQxbSSCisHa7VE45aA | X6g8P8xaSruGyGDe80BZow |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 37680 | N | N | 03 | SITE PREPARATORY WORKS |  | 125111 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 48 | 0
%R | 503272 | 6359 | 125141 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AGNSP002200 | Information Required for Rerouting |  | 0 | 0 | 112 | 0 | 0 | 0 | 112 | 0 | 0 | 0 |  |  |  | 2012-12-26 08:00 | 2013-01-10 17:00 |  | 2012-12-26 08:00 | 2013-01-10 17:00 | 2012-12-26 08:00 | 2013-01-10 17:00 | 2012-12-26 08:00 | 2013-01-10 17:00 | 2012-12-26 08:00 | 2013-01-10 17:00 |  | PT_Normal |  |  |  |  | aD3+cfJsQFeyA7JQe9qLFA | G4W1dBGg0UuF/M5dHjAf+Q |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 37680 | N | N | 03 | SITE PREPARATORY WORKS |  | 125111 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 503273 | 6359 | 125141 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AGNSP002300 | Preparation & Submission for New Layout |  | 0 | 0 | 56 | 0 | 40 | 40 | 56 | 0 | 0 | 0 |  |  |  | 2013-01-12 08:00 | 2013-01-19 17:00 |  | 2013-01-12 08:00 | 2013-01-19 17:00 | 2013-01-12 08:00 | 2013-01-19 17:00 | 2013-01-12 08:00 | 2013-01-19 17:00 | 2013-01-12 08:00 | 2013-01-19 17:00 |  | PT_Normal |  |  |  |  | cSNvToNHQbuLL0lLQtpG6g | VsckLxeAp0C9pl0wxj5E/Q |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 37680 | N | N | 03 | SITE PREPARATORY WORKS |  | 125111 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 40 | 0
%R | 503274 | 6359 | 125141 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AGNSP002400 | Approval for new Layout for rerouting |  | 0 | 0 | 112 | 0 | 0 | 0 | 112 | 0 | 0 | 0 |  |  |  | 2013-01-20 08:00 | 2013-02-04 17:00 |  | 2013-01-20 08:00 | 2013-02-04 17:00 | 2013-01-20 08:00 | 2013-02-04 17:00 | 2013-01-20 08:00 | 2013-02-04 17:00 | 2013-01-20 08:00 | 2013-02-04 17:00 |  | PT_Normal |  |  |  |  | a8Rl6vDlQUKgGM89dupXDA | nchmWbR/s0Wr0F//VVLvvg |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 37680 | N | N | 03 | SITE PREPARATORY WORKS |  | 125111 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 0 | 0
%R | 503275 | 6359 | 125141 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AGNSP002500 | Rerouting Works | 8180 | 0 | 0 | 200 | 0 | 325 | 325 | 200 | 0 | 0 | 0 |  |  |  | 2013-02-05 08:00 | 2013-03-06 17:00 |  | 2013-02-05 08:00 | 2013-03-06 17:00 | 2013-02-05 08:00 | 2013-03-06 17:00 | 2013-02-05 08:00 | 2013-03-06 17:00 | 2013-02-05 08:00 | 2013-03-06 17:00 |  | PT_Normal |  |  |  |  | gGmE0FINTBWRrCcVrQjSQQ | F9W9WBvdd0ywqVbvBEXKNQ |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43571 |  |  |  |  | ELECTRICIANS SK | M302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37680 | N | N | 03 | SITE PREPARATORY WORKS |  | 125111 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP02; period 2: 2013-AP03 |  | 162.5 | ELECTRICIANS SK
%R | 503276 | 6359 | 125145 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARGF3000 | Block work | 8168 | 48 | 0 | 48 | 0 | 950 | 950 | 48 | 0 | 0 | 0 |  |  |  | 2013-08-28 08:00 | 2013-09-03 17:00 |  | 2013-08-21 08:00 | 2013-08-27 17:00 | 2013-08-21 08:00 | 2013-08-27 17:00 | 2013-08-21 08:00 | 2013-08-27 17:00 | 2013-08-28 08:00 | 2013-09-03 17:00 |  | PT_Normal |  |  |  |  | Q5C1L4YSQoGL0Fz1lUJFIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37720 | N | N | 10 | GROUND FLOOR |  | 125144 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 950 | BLOCK MASON SK
%R | 503277 | 6359 | 125145 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARGF3005 | Plastering work | 8169 | 96 | 0 | 56 | 0 | 475 | 475 | 56 | 0 | 0 | 0 |  |  |  | 2013-09-17 08:00 | 2013-09-24 17:00 |  | 2013-09-03 08:00 | 2013-09-10 17:00 | 2013-09-03 08:00 | 2013-09-10 17:00 | 2013-09-03 08:00 | 2013-09-10 17:00 | 2013-09-17 08:00 | 2013-09-24 17:00 |  | PT_Normal |  |  |  |  | 25s27gyYTWqxSulWFkhrIA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37720 | N | N | 10 | GROUND FLOOR |  | 125144 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 475 | PLASTER MASON SK
%R | 503278 | 6359 | 125145 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARGF3010 | Flooring screed | 8164 | 168 | 0 | 56 | 0 | 106.25 | 106.25 | 56 | 0 | 0 | 0 |  |  |  | 2013-10-01 08:00 | 2013-10-08 17:00 |  | 2013-09-07 08:00 | 2013-09-14 17:00 | 2013-09-07 08:00 | 2013-09-14 17:00 | 2013-09-07 08:00 | 2013-09-14 17:00 | 2013-10-01 08:00 | 2013-10-08 17:00 |  | PT_Normal |  |  |  |  | i5MwmkXaSLyxOc0z1cuXlw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37720 | N | N | 10 | GROUND FLOOR |  | 125144 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 106.25 | SCREED MASON SK
%R | 503279 | 6359 | 125145 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 168 | 0 | 40 | 0 | 15.5 | 15.5 | 40 | 0 | 0 | 0 |  |  |  | 2013-10-05 08:00 | 2013-10-09 17:00 |  | 2013-09-10 08:00 | 2013-09-15 17:00 | 2013-09-10 08:00 | 2013-09-15 17:00 | 2013-09-10 08:00 | 2013-09-15 17:00 | 2013-10-05 08:00 | 2013-10-09 17:00 |  | PT_Normal |  |  |  |  | inn+mOmvTzijpSpj64ZBPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37720 | N | N | 10 | GROUND FLOOR |  | 125144 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 15.5 | LABOR- SUBCONTRACTOR
%R | 503280 | 6359 | 125145 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARGF3030 | Paint First coat | 8178 | 80 | 0 | 40 | 0 | 300.3 | 300.3 | 40 | 0 | 0 | 0 |  |  |  | 2013-10-07 08:00 | 2013-10-12 17:00 |  | 2013-09-25 08:00 | 2013-09-30 17:00 | 2013-09-25 08:00 | 2013-09-30 17:00 | 2013-09-25 08:00 | 2013-09-30 17:00 | 2013-10-07 08:00 | 2013-10-12 17:00 |  | PT_Normal |  |  |  |  | tYNL4sA7SZyuDlmY1+8+aw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37720 | N | N | 10 | GROUND FLOOR |  | 125144 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 300.3 | LABOR- SUBCONTRACTOR
%R | 503281 | 6359 | 125145 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARGF3020 | Ceramic Wall Tiling | 8170 | 208 | 0 | 48 | 0 | 168.75 | 168.75 | 48 | 0 | 0 | 0 |  |  |  | 2013-10-16 08:00 | 2013-10-24 17:00 |  | 2013-09-16 08:00 | 2013-09-22 17:00 | 2013-09-16 08:00 | 2013-09-22 17:00 | 2013-09-16 08:00 | 2013-09-22 17:00 | 2013-10-16 08:00 | 2013-10-24 17:00 |  | PT_Normal |  |  |  |  | eY7ZK6P+RAyYddsVlfpQcw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37720 | N | N | 10 | GROUND FLOOR |  | 125144 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 168.75 | TILE MASON SK
%R | 503282 | 6359 | 125145 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARGF3025 | Porcelain Tile flooring | 8170 | 208 | 0 | 48 | 0 | 172.25 | 172.25 | 48 | 0 | 0 | 0 |  |  |  | 2013-10-26 08:00 | 2013-10-31 17:00 |  | 2013-09-23 08:00 | 2013-09-29 17:00 | 2013-09-23 08:00 | 2013-09-29 17:00 | 2013-09-23 08:00 | 2013-09-29 17:00 | 2013-10-26 08:00 | 2013-10-31 17:00 |  | PT_Normal |  |  |  |  | /X7qUVW1Tjej8lWKuwWyFg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37720 | N | N | 10 | GROUND FLOOR |  | 125144 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 172.25 | TILE MASON SK
%R | 503283 | 6359 | 125145 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARGF3040 | Cobble Tile flooring | 8170 | 416 | 0 | 40 | 0 | 50 | 50 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-02 08:00 | 2013-12-07 17:00 |  | 2013-09-30 08:00 | 2013-10-05 17:00 | 2013-09-30 08:00 | 2013-10-05 17:00 | 2013-09-30 08:00 | 2013-10-05 17:00 | 2013-12-02 08:00 | 2013-12-07 17:00 |  | PT_Normal |  |  |  |  | RPWvn5ejTFKRwRbiQxAkQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37720 | N | N | 10 | GROUND FLOOR |  | 125144 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 50 | TILE MASON SK
%R | 503284 | 6359 | 125145 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARGF3035 | Slate Tile Flooring & Skirting | 8170 | 416 | 296 | 40 | 0 | 262.5 | 262.5 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-08 08:00 | 2013-12-12 17:00 |  | 2013-10-06 08:00 | 2013-10-10 17:00 | 2013-10-06 08:00 | 2013-10-10 17:00 | 2013-10-06 08:00 | 2013-10-10 17:00 | 2013-12-08 08:00 | 2013-12-12 17:00 |  | PT_Normal |  |  |  |  | 9YT/qbyuTny0hXQ2okpDCQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37720 | N | N | 10 | GROUND FLOOR |  | 125144 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 262.5 | TILE MASON SK
%R | 503285 | 6359 | 125145 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARGF3045 | Fixing of Suspension systems | 8178 | 200 | 0 | 56 | 0 | 109.75 | 109.75 | 56 | 0 | 0 | 0 |  |  |  | 2013-11-02 08:00 | 2013-11-09 17:00 |  | 2013-10-01 08:00 | 2013-10-08 17:00 | 2013-10-01 08:00 | 2013-10-08 17:00 | 2013-10-01 08:00 | 2013-10-08 17:00 | 2013-11-02 08:00 | 2013-11-09 17:00 |  | PT_Normal |  |  |  |  | TQHY4S+gSEG+lHUvl4T2xA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37720 | N | N | 10 | GROUND FLOOR |  | 125144 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 109.75 | LABOR- SUBCONTRACTOR
%R | 503286 | 6359 | 125145 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARGF3060 | Gypsum board false ceiling | 8178 | 200 | 0 | 64 | 0 | 109.75 | 109.75 | 64 | 0 | 0 | 0 |  |  |  | 2013-11-10 08:00 | 2013-11-18 17:00 |  | 2013-10-09 08:00 | 2013-10-20 17:00 | 2013-10-09 08:00 | 2013-10-20 17:00 | 2013-10-09 08:00 | 2013-10-20 17:00 | 2013-11-10 08:00 | 2013-11-18 17:00 |  | PT_Normal |  |  |  |  | 7758lk08QhWZsuC5PW074Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37720 | N | N | 10 | GROUND FLOOR |  | 125144 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 109.75 | LABOR- SUBCONTRACTOR
%R | 503287 | 6359 | 125145 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARGF3065 | Wooden door | 8178 | 200 | 0 | 56 | 0 | 33 | 33 | 56 | 0 | 0 | 0 |  |  |  | 2013-11-19 08:00 | 2013-11-26 17:00 |  | 2013-10-21 08:00 | 2013-10-28 17:00 | 2013-10-21 08:00 | 2013-10-28 17:00 | 2013-10-21 08:00 | 2013-10-28 17:00 | 2013-11-19 08:00 | 2013-11-26 17:00 |  | PT_Normal |  |  |  |  | q41ylKJvT4aBnzq/zDrFtA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37720 | N | N | 10 | GROUND FLOOR |  | 125144 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 33 | LABOR- SUBCONTRACTOR
%R | 503288 | 6359 | 125145 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARGF3080 | Aluminum windows | 8178 | 520 | 120 | 56 | 0 | 22 | 22 | 56 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-01-21 17:00 |  | 2013-10-29 08:00 | 2013-11-05 17:00 | 2013-10-29 08:00 | 2013-11-05 17:00 | 2013-10-29 08:00 | 2013-11-05 17:00 | 2014-01-14 08:00 | 2014-01-21 17:00 |  | PT_Normal |  |  |  |  | lKKThmXBQSCkbaKSTGrYWg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37720 | N | N | 10 | GROUND FLOOR |  | 125144 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 22 | LABOR- SUBCONTRACTOR
%R | 503289 | 6359 | 125145 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARGF3075 | Carpentry & Joinery Works | 8178 | 360 | 0 | 80 | 0 | 88 | 88 | 80 | 0 | 0 | 0 |  |  |  | 2014-01-05 08:00 | 2014-01-15 17:00 |  | 2013-11-12 08:00 | 2013-11-23 17:00 | 2013-11-12 08:00 | 2013-11-23 17:00 | 2013-11-12 08:00 | 2013-11-23 17:00 | 2014-01-05 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | /tfVC51LRF+oQJRzO0cwXw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37720 | N | N | 10 | GROUND FLOOR |  | 125144 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 88 | LABOR- SUBCONTRACTOR
%R | 503290 | 6359 | 125145 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARGF3090 | Installation of Granite Counter Top | 8171 | 400 | 0 | 56 | 0 | 16.5 | 16.5 | 56 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-01-29 17:00 |  | 2013-11-24 08:00 | 2013-12-01 17:00 | 2013-11-24 08:00 | 2013-12-01 17:00 | 2013-11-24 08:00 | 2013-12-01 17:00 | 2014-01-22 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | kcHkhqXVRrGDJE178HQQGw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37720 | N | N | 10 | GROUND FLOOR |  | 125144 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 16.5 | GRANITE MASON SK
%R | 503291 | 6359 | 125145 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARGF3095 | Final Painting | 8178 | 664 | 392 | 56 | 0 | 300.3 | 300.3 | 56 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-03-18 17:00 |  | 2013-12-02 08:00 | 2013-12-09 17:00 | 2013-12-02 08:00 | 2013-12-09 17:00 | 2013-12-02 08:00 | 2013-12-09 17:00 | 2014-03-11 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | xD4oV0bWR/W+RIo0BCaFqQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37720 | N | N | 10 | GROUND FLOOR |  | 125144 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 300.3 | LABOR- SUBCONTRACTOR
%R | 503292 | 6359 | 125147 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKAREL3665 | External Plastering | 8169 | 240 | 0 | 80 | 0 | 668.75 | 668.75 | 80 | 0 | 0 | 0 |  |  |  | 2013-10-14 08:00 | 2013-10-27 17:00 |  | 2013-09-09 08:00 | 2013-09-19 17:00 | 2013-09-09 08:00 | 2013-09-19 17:00 | 2013-09-09 08:00 | 2013-09-19 17:00 | 2013-10-14 08:00 | 2013-10-27 17:00 |  | PT_Normal |  |  |  |  | ZN9JQm3PSeqWZBXOnWlXyg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37770 | N | N | 15 | ELEVATION |  | 125146 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 668.75 | PLASTER MASON SK
%R | 503293 | 6359 | 125147 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKAREL3680 | External Painting | 8178 | 304 | 0 | 56 | 0 | 234.75 | 234.75 | 56 | 0 | 0 | 0 |  |  |  | 2013-11-06 08:00 | 2013-11-13 17:00 |  | 2013-09-21 08:00 | 2013-09-28 17:00 | 2013-09-21 08:00 | 2013-09-28 17:00 | 2013-09-21 08:00 | 2013-09-28 17:00 | 2013-11-06 08:00 | 2013-11-13 17:00 |  | PT_Normal |  |  |  |  | GiEOmsKhRniWBwbD6vqGVA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37770 | N | N | 15 | ELEVATION |  | 125146 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 234.75 | LABOR- SUBCONTRACTOR
%R | 503294 | 6359 | 125148 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARRF3625 | Laying of Pitched Roof | 8174 | 240 | 0 | 56 | 0 | 43 | 43 | 56 | 0 | 0 | 0 |  |  |  | 2013-09-22 08:00 | 2013-09-29 17:00 |  | 2013-08-18 08:00 | 2013-08-25 17:00 | 2013-08-18 08:00 | 2013-08-25 17:00 | 2013-08-18 08:00 | 2013-08-25 17:00 | 2013-09-22 08:00 | 2013-09-29 17:00 |  | PT_Normal |  |  |  |  | kUURgrM5QJeCOH2rUbJwaw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37760 | N | N | 10 | ROOF |  | 125146 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 43 | INTERLOCK MASON SK
%R | 503295 | 6359 | 125148 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARRF3630 | Leveling Screed for Waterproofing | 8164 | 240 | 0 | 16 | 0 | 33 | 33 | 16 | 0 | 0 | 0 |  |  |  | 2013-09-30 08:00 | 2013-10-01 17:00 |  | 2013-08-26 08:00 | 2013-08-27 17:00 | 2013-08-26 08:00 | 2013-08-27 17:00 | 2013-08-26 08:00 | 2013-08-27 17:00 | 2013-09-30 08:00 | 2013-10-01 17:00 |  | PT_Normal |  |  |  |  | rMhSfh4XQD2u11a+zizNbg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37760 | N | N | 10 | ROOF |  | 125146 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 33 | SCREED MASON SK
%R | 503296 | 6359 | 125148 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARRF3635 | Laying of Waterproofing Membrane | 8178 | 240 | 0 | 32 | 0 | 121 | 121 | 32 | 0 | 0 | 0 |  |  |  | 2013-10-02 08:00 | 2013-10-06 17:00 |  | 2013-08-28 08:00 | 2013-09-01 17:00 | 2013-08-28 08:00 | 2013-09-01 17:00 | 2013-08-28 08:00 | 2013-09-01 17:00 | 2013-10-02 08:00 | 2013-10-06 17:00 |  | PT_Normal |  |  |  |  | qK76p+CdTZmi6u2T28mYAQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37760 | N | N | 10 | ROOF |  | 125146 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 121 | LABOR- SUBCONTRACTOR
%R | 503297 | 6359 | 125148 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARRF3640 | Installation of Insulation & Protection | 8178 | 240 | 0 | 32 | 0 | 57.75 | 57.75 | 32 | 0 | 0 | 0 |  |  |  | 2013-10-07 08:00 | 2013-10-10 17:00 |  | 2013-09-02 08:00 | 2013-09-05 17:00 | 2013-09-02 08:00 | 2013-09-05 17:00 | 2013-09-02 08:00 | 2013-09-05 17:00 | 2013-10-07 08:00 | 2013-10-10 17:00 |  | PT_Normal |  |  |  |  | FN+43azISaCRjTHuHGeVnQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37760 | N | N | 10 | ROOF |  | 125146 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 57.75 | LABOR- SUBCONTRACTOR
%R | 503298 | 6359 | 125148 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 240 | 0 | 16 | 0 | 58.5 | 58.5 | 16 | 0 | 0 | 0 |  |  |  | 2013-10-12 08:00 | 2013-10-13 17:00 |  | 2013-09-07 08:00 | 2013-09-08 17:00 | 2013-09-07 08:00 | 2013-09-08 17:00 | 2013-09-07 08:00 | 2013-09-08 17:00 | 2013-10-12 08:00 | 2013-10-13 17:00 |  | PT_Normal |  |  |  |  | TLIf7nwVR+iPz0UwKpnzqg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37760 | N | N | 10 | ROOF |  | 125146 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 58.5 | TILE MASON SK
%R | 503299 | 6359 | 125148 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKARRF3660 | Installation of Access Ladder | 8178 | 728 | 96 | 40 | 0 | 22 | 22 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-01 08:00 | 2014-01-06 17:00 |  | 2013-09-14 08:00 | 2013-09-18 17:00 | 2013-09-14 08:00 | 2013-09-18 17:00 | 2013-09-14 08:00 | 2013-09-18 17:00 | 2014-01-01 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | 1Xm651gRTCuvXyrxHX3Ttw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37760 | N | N | 10 | ROOF |  | 125146 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 22 | LABOR- SUBCONTRACTOR
%R | 503300 | 6359 | 125151 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKACRF4630 | Installation of Refrigerant Pipes | 8178 | 704 | 176 | 40 | 0 | 2.15 | 2.15 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-01 08:00 | 2014-01-06 17:00 |  | 2013-09-17 08:00 | 2013-09-22 17:00 | 2013-09-17 08:00 | 2013-09-22 17:00 | 2013-09-17 08:00 | 2013-09-22 17:00 | 2014-01-01 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | nSY7FtkdSj6namRTQOEkXw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37900 | N | N | 20 | ROOF |  | 125150 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 2.15 | LABOR- SUBCONTRACTOR
%R | 503301 | 6359 | 125151 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKACRF4635 | Installation of Condensing Unit | 8178 | 784 | 120 | 64 | 0 | 22.05 | 22.05 | 64 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-10 17:00 |  | 2013-11-05 08:00 | 2013-11-13 17:00 | 2013-11-05 08:00 | 2013-11-13 17:00 | 2013-11-05 08:00 | 2013-11-13 17:00 | 2014-03-02 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | CatG/u6vRQuJTa3fSxFBYA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37900 | N | N | 20 | ROOF |  | 125150 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 22.05 | LABOR- SUBCONTRACTOR
%R | 503302 | 6359 | 125152 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKACGF4600 | Installation AC Pipes | 8178 | 328 | 0 | 40 | 0 | 93.05 | 93.05 | 40 | 0 | 0 | 0 |  |  |  | 2013-10-31 08:00 | 2013-11-05 17:00 |  | 2013-09-11 08:00 | 2013-09-16 17:00 | 2013-09-11 08:00 | 2013-09-16 17:00 | 2013-09-11 08:00 | 2013-09-16 17:00 | 2013-10-31 08:00 | 2013-11-05 17:00 |  | PT_Normal |  |  |  |  | Qmi9YCl+R4KzxS6dN3PgTQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37880 | N | N | 10 | GROUND FLOOR |  | 125150 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 93.05 | LABOR- SUBCONTRACTOR
%R | 503303 | 6359 | 125152 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKACGF4605 | Fixing of Ventilation Equipments | 8178 | 736 | 0 | 40 | 0 | 14.2 | 14.2 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-02-12 17:00 |  | 2013-10-21 08:00 | 2013-10-26 17:00 | 2013-10-21 08:00 | 2013-10-26 17:00 | 2013-10-21 08:00 | 2013-10-26 17:00 | 2014-02-06 08:00 | 2014-02-12 17:00 |  | PT_Normal |  |  |  |  | /K1ToYZxTHqp9CcEXC7XLg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37880 | N | N | 10 | GROUND FLOOR |  | 125150 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 14.2 | LABOR- SUBCONTRACTOR
%R | 503304 | 6359 | 125152 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKACGF4610 | Fixing of Split AC | 8178 | 784 | 0 | 64 | 0 | 25.8 | 25.8 | 64 | 0 | 0 | 0 |  |  |  | 2014-02-20 08:00 | 2014-03-01 17:00 |  | 2013-10-27 08:00 | 2013-11-04 17:00 | 2013-10-27 08:00 | 2013-11-04 17:00 | 2013-10-27 08:00 | 2013-11-04 17:00 | 2014-02-20 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | lUildzo9RMW7I7T/17TAnA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37880 | N | N | 10 | GROUND FLOOR |  | 125150 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 25.8 | LABOR- SUBCONTRACTOR
%R | 503305 | 6359 | 125154 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKELRF4070 | Installation of Isolator | 8178 | 776 | 0 | 40 | 0 | 60.2 | 60.2 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-25 08:00 | 2014-03-02 17:00 |  | 2013-11-02 08:00 | 2013-11-06 17:00 | 2013-11-02 08:00 | 2013-11-06 17:00 | 2013-11-02 08:00 | 2013-11-06 17:00 | 2014-02-25 08:00 | 2014-03-02 17:00 |  | PT_Normal |  |  |  |  | D7U/WqYvTnO1PGu3xxVxrg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37820 | N | N | 20 | ROOF |  | 125153 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 60.2 | LABOR- SUBCONTRACTOR
%R | 503306 | 6359 | 125154 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKELRF4075 | Installation of TV Dish Antenna | 8178 | 776 | 112 | 56 | 0 | 31.4 | 31.4 | 56 | 0 | 0 | 0 |  |  |  | 2014-03-03 08:00 | 2014-03-10 17:00 |  | 2013-11-07 08:00 | 2013-11-14 17:00 | 2013-11-07 08:00 | 2013-11-14 17:00 | 2013-11-07 08:00 | 2013-11-14 17:00 | 2014-03-03 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | HbKNpqLyRWe6F8SJOHWE4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37820 | N | N | 20 | ROOF |  | 125153 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 31.4 | LABOR- SUBCONTRACTOR
%R | 503307 | 6359 | 125155 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 96 | 0 | 40 | 0 | 99.85 | 99.85 | 40 | 0 | 0 | 0 |  |  |  | 2013-09-11 08:00 | 2013-09-16 17:00 |  | 2013-08-28 08:00 | 2013-09-02 17:00 | 2013-08-28 08:00 | 2013-09-02 17:00 | 2013-08-28 08:00 | 2013-09-02 17:00 | 2013-09-11 08:00 | 2013-09-16 17:00 |  | PT_Normal |  |  |  |  | P8GaviJ3Q8W4058vU4UL0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37800 | N | N | 10 | GROUND FLOOR |  | 125153 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 99.85 | LABOR- SUBCONTRACTOR
%R | 503308 | 6359 | 125155 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKELGF4005 | Cable tray & trunking installation | 8178 | 120 | 0 | 40 | 0 | 340.8 | 340.8 | 40 | 0 | 0 | 0 |  |  |  | 2013-09-29 08:00 | 2013-10-03 17:00 |  | 2013-09-11 08:00 | 2013-09-16 17:00 | 2013-09-11 08:00 | 2013-09-16 17:00 | 2013-09-11 08:00 | 2013-09-16 17:00 | 2013-09-29 08:00 | 2013-10-03 17:00 |  | PT_Normal |  |  |  |  | F5ERn825SfunlRscOMzXtg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37800 | N | N | 10 | GROUND FLOOR |  | 125153 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 340.8 | LABOR- SUBCONTRACTOR
%R | 503309 | 6359 | 125155 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKELGF4010 | Installation of wiring & Main Cabling | 8178 | 256 | 32 | 40 | 0 | 69.6 | 69.6 | 40 | 0 | 0 | 0 |  |  |  | 2013-10-27 08:00 | 2013-10-31 17:00 |  | 2013-09-17 08:00 | 2013-09-22 17:00 | 2013-09-17 08:00 | 2013-09-22 17:00 | 2013-09-17 08:00 | 2013-09-22 17:00 | 2013-10-27 08:00 | 2013-10-31 17:00 |  | PT_Normal |  |  |  |  | P5p2hcqDQHmyY9v287uAHw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37800 | N | N | 10 | GROUND FLOOR |  | 125153 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 69.6 | LABOR- SUBCONTRACTOR
%R | 503310 | 6359 | 125155 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 528 | 0 | 40 | 0 | 28.4 | 28.4 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-07 08:00 | 2014-01-12 17:00 |  | 2013-10-21 08:00 | 2013-10-26 17:00 | 2013-10-21 08:00 | 2013-10-26 17:00 | 2013-10-21 08:00 | 2013-10-26 17:00 | 2014-01-07 08:00 | 2014-01-12 17:00 |  | PT_Normal |  |  |  |  | CdNYlvMkT3GEjpVr+yUpnQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37800 | N | N | 10 | GROUND FLOOR |  | 125153 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 28.4 | LABOR- SUBCONTRACTOR
%R | 503311 | 6359 | 125155 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 528 | 0 | 40 | 0 | 66.65 | 66.65 | 40 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-01-18 17:00 |  | 2013-10-27 08:00 | 2013-10-31 17:00 | 2013-10-27 08:00 | 2013-10-31 17:00 | 2013-10-27 08:00 | 2013-10-31 17:00 | 2014-01-13 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | ylUgWU4zT5G01NkEfmGOQw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37800 | N | N | 10 | GROUND FLOOR |  | 125153 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 66.65 | LABOR- SUBCONTRACTOR
%R | 503312 | 6359 | 125155 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 472 | 368 | 56 | 0 | 184.8 | 184.8 | 56 | 0 | 0 | 0 |  |  |  | 2014-01-11 08:00 | 2014-01-18 17:00 |  | 2013-11-02 08:00 | 2013-11-09 17:00 | 2013-11-02 08:00 | 2013-11-09 17:00 | 2013-11-02 08:00 | 2013-11-09 17:00 | 2014-01-11 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | UHXOkAtnRaeR1Xp/BkwsEw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37800 | N | N | 10 | GROUND FLOOR |  | 125153 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 184.8 | LABOR- SUBCONTRACTOR
%R | 503313 | 6359 | 125155 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKELGF4030 | Installation of Telephone System | 8178 | 776 | 0 | 40 | 0 | 25.4 | 25.4 | 40 | 0 | 0 | 0 |  |  |  | 2014-02-19 08:00 | 2014-02-24 17:00 |  | 2013-10-27 08:00 | 2013-10-31 17:00 | 2013-10-27 08:00 | 2013-10-31 17:00 | 2013-10-27 08:00 | 2013-10-31 17:00 | 2014-02-19 08:00 | 2014-02-24 17:00 |  | PT_Normal |  |  |  |  | Pz2HC7ajShyULtMTjYouCA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37800 | N | N | 10 | GROUND FLOOR |  | 125153 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 25.4 | LABOR- SUBCONTRACTOR
%R | 503314 | 6359 | 125157 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKPLRF4350 | Installation of Rain water Pipes | 8178 | 80 | 0 | 40 | 0 | 43.5 | 43.5 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-11 08:00 | 2013-12-16 17:00 |  | 2013-11-30 08:00 | 2013-12-04 17:00 | 2013-11-30 08:00 | 2013-12-04 17:00 | 2013-11-30 08:00 | 2013-12-04 17:00 | 2013-12-11 08:00 | 2013-12-16 17:00 |  | PT_Normal |  |  |  |  | U+a6iR2ZR92PPo/vuUHCwA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37860 | N | N | 20 | ROOF |  | 125156 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 43.5 | LABOR- SUBCONTRACTOR
%R | 503315 | 6359 | 125158 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKPLGF4305 | Installation of Plumbing pipes & testing | 8178 | 112 | 0 | 40 | 0 | 239.4 | 239.4 | 40 | 0 | 0 | 0 |  |  |  | 2013-09-14 08:00 | 2013-09-18 17:00 |  | 2013-08-28 08:00 | 2013-09-02 17:00 | 2013-08-28 08:00 | 2013-09-02 17:00 | 2013-08-28 08:00 | 2013-09-02 17:00 | 2013-09-14 08:00 | 2013-09-18 17:00 |  | PT_Normal |  |  |  |  | BP/wLYmOTWeuS16Nv+th8w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37840 | N | N | 10 | GROUND FLOOR |  | 125156 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 239.4 | LABOR- SUBCONTRACTOR
%R | 503316 | 6359 | 125158 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKPLGF4310 | Installation of Drainage pipes &testing | 8178 | 120 | 0 | 40 | 0 | 12.45 | 12.45 | 40 | 0 | 0 | 0 |  |  |  | 2013-09-15 08:00 | 2013-09-19 17:00 |  | 2013-08-28 08:00 | 2013-09-02 17:00 | 2013-08-28 08:00 | 2013-09-02 17:00 | 2013-08-28 08:00 | 2013-09-02 17:00 | 2013-09-15 08:00 | 2013-09-19 17:00 |  | PT_Normal |  |  |  |  | NLUVIl/oTa6PNSW6eZeoXw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37840 | N | N | 10 | GROUND FLOOR |  | 125156 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 12.45 | LABOR- SUBCONTRACTOR
%R | 503317 | 6359 | 125158 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKPLGF4315 | Sanitary Fittings & Accessories | 8178 | 80 | 0 | 56 | 0 | 35.7 | 35.7 | 56 | 0 | 0 | 0 |  |  |  | 2013-11-27 08:00 | 2013-12-04 17:00 |  | 2013-11-16 08:00 | 2013-11-23 17:00 | 2013-11-16 08:00 | 2013-11-23 17:00 | 2013-11-16 08:00 | 2013-11-23 17:00 | 2013-11-27 08:00 | 2013-12-04 17:00 |  | PT_Normal |  |  |  |  | M9wTjDmZQXGXClSvYhTk2Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37840 | N | N | 10 | GROUND FLOOR |  | 125156 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 35.7 | LABOR- SUBCONTRACTOR
%R | 503318 | 6359 | 125158 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKPLGF4320 | Installation of Water Heater | 8178 | 80 | 0 | 40 | 0 | 25.2 | 25.2 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-05 08:00 | 2013-12-10 17:00 |  | 2013-11-24 08:00 | 2013-11-28 17:00 | 2013-11-24 08:00 | 2013-11-28 17:00 | 2013-11-24 08:00 | 2013-11-28 17:00 | 2013-12-05 08:00 | 2013-12-10 17:00 |  | PT_Normal |  |  |  |  | buMMamQoTES1fzSIWC7f5g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37840 | N | N | 10 | GROUND FLOOR |  | 125156 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 25.2 | LABOR- SUBCONTRACTOR
%R | 503319 | 6359 | 125160 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKSLEX5105 | Laying of Grass/ green area | 8178 | 168 | 0 | 56 | 0 | 357 | 357 | 56 | 0 | 0 | 0 |  |  |  | 2013-12-30 08:00 | 2014-01-06 17:00 |  | 2013-12-04 08:00 | 2013-12-11 17:00 | 2013-12-04 08:00 | 2013-12-11 17:00 | 2013-12-04 08:00 | 2013-12-11 17:00 | 2013-12-30 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | /jZWqLFzTBGuVxEUx1U4Jw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37960 | N | N | 25 | SOFT LANDSCAPING |  | 125159 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 357 | LABOR- SUBCONTRACTOR
%R | 503320 | 6359 | 125160 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKSLEX5110 | Laying of Palm tree | 8178 | 512 | 24 | 56 | 0 | 91 | 91 | 56 | 0 | 0 | 0 |  |  |  | 2014-02-27 08:00 | 2014-03-06 17:00 |  | 2013-12-12 08:00 | 2013-12-21 17:00 | 2013-12-12 08:00 | 2013-12-21 17:00 | 2013-12-12 08:00 | 2013-12-21 17:00 | 2014-02-27 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | Yk6qoPn1QBOtfdNgJ25gZg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37960 | N | N | 25 | SOFT LANDSCAPING |  | 125159 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 91 | LABOR- SUBCONTRACTOR
%R | 503321 | 6359 | 125161 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKHDEX5100 | Interlock works | 8174 | 424 | 144 | 40 | 0 | 50.25 | 50.25 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-21 08:00 | 2013-12-25 17:00 |  | 2013-10-16 08:00 | 2013-10-23 17:00 | 2013-10-16 08:00 | 2013-10-23 17:00 | 2013-10-16 08:00 | 2013-10-23 17:00 | 2013-12-21 08:00 | 2013-12-25 17:00 |  | PT_Normal |  |  |  |  | qSkwslZDTaWrybjWPOnfwg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37950 | N | N | 20 | HARD LANDSCAPING |  | 125159 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 50.25 | INTERLOCK MASON SK
%R | 503322 | 6359 | 125161 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKHDEX5090 | kerb works | 8173 | 320 | 0 | 40 | 0 | 39.25 | 39.25 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-23 08:00 | 2013-11-27 17:00 |  | 2013-10-05 08:00 | 2013-10-09 17:00 | 2013-10-05 08:00 | 2013-10-09 17:00 | 2013-10-05 08:00 | 2013-10-09 17:00 | 2013-11-23 08:00 | 2013-11-27 17:00 |  | PT_Normal |  |  |  |  | 1t0aKDJVSTKwQV09OmlJJw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37950 | N | N | 20 | HARD LANDSCAPING |  | 125159 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 39.25 | KERBSTONE MASON SK
%R | 503323 | 6359 | 125161 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKHDEX5095 | Cobble Stone Works | 8170 | 360 | 0 | 40 | 0 | 14.25 | 14.25 | 40 | 0 | 0 | 0 |  |  |  | 2013-12-04 08:00 | 2013-12-09 17:00 |  | 2013-10-10 08:00 | 2013-10-15 17:00 | 2013-10-10 08:00 | 2013-10-15 17:00 | 2013-10-10 08:00 | 2013-10-15 17:00 | 2013-12-04 08:00 | 2013-12-09 17:00 |  | PT_Normal |  |  |  |  | ajhOlf3KRK6pPetJktiHSw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37950 | N | N | 20 | HARD LANDSCAPING |  | 125159 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 14.25 | TILE MASON SK
%R | 503324 | 6359 | 125162 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKMSEX5005 | Construction of Soak pit, Chambers | 8172 | 120 | 0 | 56 | 0 | 11 | 11 | 56 | 0 | 0 | 0 |  |  |  | 2013-09-29 08:00 | 2013-10-06 17:00 |  | 2013-09-11 08:00 | 2013-09-18 17:00 | 2013-09-11 08:00 | 2013-09-18 17:00 | 2013-09-11 08:00 | 2013-09-18 17:00 | 2013-09-29 08:00 | 2013-10-06 17:00 |  | PT_Normal |  |  |  |  | xfhcHDuvSGacy/2Z503M3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37930 | N | N | 10 | MISCELLANEOUS |  | 125159 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 11 | MANHOLES SK
%R | 503325 | 6359 | 125162 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKMSEX5020 | Construction Entrance Ramp | 8164 | 240 | 0 | 56 | 0 | 72.75 | 72.75 | 56 | 0 | 0 | 0 |  |  |  | 2013-10-28 08:00 | 2013-11-04 17:00 |  | 2013-09-21 08:00 | 2013-09-28 17:00 | 2013-09-21 08:00 | 2013-09-28 17:00 | 2013-09-21 08:00 | 2013-09-28 17:00 | 2013-10-28 08:00 | 2013-11-04 17:00 |  | PT_Normal |  |  |  |  | gtKeu1VGR/6nu9anjgp0JQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37930 | N | N | 10 | MISCELLANEOUS |  | 125159 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 72.75 | SCREED MASON SK
%R | 503326 | 6359 | 125162 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKMSEX5025 | SS.Handrails and Balustrades | 8178 | 304 | 0 | 40 | 0 | 23.25 | 23.25 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-14 08:00 | 2013-11-19 17:00 |  | 2013-09-29 08:00 | 2013-10-03 17:00 | 2013-09-29 08:00 | 2013-10-03 17:00 | 2013-09-29 08:00 | 2013-10-03 17:00 | 2013-11-14 08:00 | 2013-11-19 17:00 |  | PT_Normal |  |  |  |  | mR2esEVZRDuO7UUr2x8RCQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37930 | N | N | 10 | MISCELLANEOUS |  | 125159 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 23.25 | LABOR- SUBCONTRACTOR
%R | 503327 | 6359 | 125162 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKMSEX5015 | Construction of grease Trap | 8178 | 120 | 0 | 56 | 0 | 28.25 | 28.25 | 56 | 0 | 0 | 0 |  |  |  | 2013-10-07 08:00 | 2013-10-14 17:00 |  | 2013-09-19 08:00 | 2013-09-26 17:00 | 2013-09-19 08:00 | 2013-09-26 17:00 | 2013-09-19 08:00 | 2013-09-26 17:00 | 2013-10-07 08:00 | 2013-10-14 17:00 |  | PT_Normal |  |  |  |  | QRdo97ZeS5O1o4+ggPGwCg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37930 | N | N | 10 | MISCELLANEOUS |  | 125159 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 28.25 | LABOR- SUBCONTRACTOR
%R | 503328 | 6359 | 125162 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKMSEX5000 | Construction of Manholes | 8172 | 120 | 0 | 56 | 0 | 22 | 22 | 56 | 0 | 0 | 0 |  |  |  | 2013-09-21 08:00 | 2013-09-28 17:00 |  | 2013-09-03 08:00 | 2013-09-10 17:00 | 2013-09-03 08:00 | 2013-09-10 17:00 | 2013-09-03 08:00 | 2013-09-10 17:00 | 2013-09-21 08:00 | 2013-09-28 17:00 |  | PT_Normal |  |  |  |  | E2n30t/UR72MLzkjx/nd3g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37930 | N | N | 10 | MISCELLANEOUS |  | 125159 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 22 | MANHOLES SK
%R | 503329 | 6359 | 125163 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKWEEX5030 | Excavation | 8177 | 120 | 0 | 32 | 0 | 78 | 78 | 32 | 72 | 0 | 72 |  |  |  | 2013-10-07 08:00 | 2013-10-10 17:00 |  | 2013-09-19 08:00 | 2013-09-23 17:00 | 2013-09-19 08:00 | 2013-09-23 17:00 | 2013-09-19 08:00 | 2013-09-23 17:00 | 2013-10-07 08:00 | 2013-10-10 17:00 |  | PT_Normal |  |  |  |  | kkDHO3/qSRivD6vWd2VMpw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37940 | N | N | 15 | WATER TANK ENCLOSURE |  | 125159 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 78 | LABOR - CIVIL
%R | 503330 | 6359 | 125163 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKWEEX5035 | Construction of Raft | 8167 | 200 | 0 | 56 | 0 | 35 | 35 | 56 | 0 | 0 | 0 |  |  |  | 2013-10-26 08:00 | 2013-11-02 17:00 |  | 2013-09-24 08:00 | 2013-10-01 17:00 | 2013-09-24 08:00 | 2013-10-01 17:00 | 2013-09-24 08:00 | 2013-10-01 17:00 | 2013-10-26 08:00 | 2013-11-02 17:00 |  | PT_Normal |  |  |  |  | pfYjQk1PSAakLdyHj9SLdg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37940 | N | N | 15 | WATER TANK ENCLOSURE |  | 125159 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 35 | CONCRETE MASON SK
%R | 503331 | 6359 | 125163 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKWEEX5040 | Block works & Plastering | 8168 | 208 | 0 | 56 | 0 | 115 | 115 | 56 | 0 | 0 | 0 |  |  |  | 2013-11-04 08:00 | 2013-11-11 17:00 |  | 2013-10-02 08:00 | 2013-10-09 17:00 | 2013-10-02 08:00 | 2013-10-09 17:00 | 2013-10-02 08:00 | 2013-10-09 17:00 | 2013-11-04 08:00 | 2013-11-11 17:00 |  | PT_Normal |  |  |  |  | ykxVuVAvT7ywHKcQHHE5Lg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37940 | N | N | 15 | WATER TANK ENCLOSURE |  | 125159 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 115 | BLOCK MASON SK
%R | 503332 | 6359 | 125163 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKWEEX5045 | Flooring & Painting | 8164 | 232 | 32 | 56 | 0 | 55.75 | 55.75 | 56 | 0 | 0 | 0 |  |  |  | 2013-11-16 08:00 | 2013-11-23 17:00 |  | 2013-10-10 08:00 | 2013-10-20 17:00 | 2013-10-10 08:00 | 2013-10-20 17:00 | 2013-10-10 08:00 | 2013-10-20 17:00 | 2013-11-16 08:00 | 2013-11-23 17:00 |  | PT_Normal |  |  |  |  | qKLzgK+9R5m4vZ5MnZQz8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37940 | N | N | 15 | WATER TANK ENCLOSURE |  | 125159 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 55.75 | SCREED MASON SK
%R | 503333 | 6359 | 125163 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKWEEX5050 | Installation of Steel Gate | 8178 | 224 | 0 | 40 | 0 | 25 | 25 | 40 | 0 | 0 | 0 |  |  |  | 2013-11-30 08:00 | 2013-12-04 17:00 |  | 2013-10-28 08:00 | 2013-11-02 17:00 | 2013-10-28 08:00 | 2013-11-02 17:00 | 2013-10-28 08:00 | 2013-11-02 17:00 | 2013-11-30 08:00 | 2013-12-04 17:00 |  | PT_Normal |  |  |  |  | F5mN4c+dSpu9MO+kMN/8Iw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37940 | N | N | 15 | WATER TANK ENCLOSURE |  | 125159 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 25 | LABOR- SUBCONTRACTOR
%R | 503334 | 6359 | 125163 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKWEEX5060 | Structural steel & SS Shed cover installation | 8178 | 224 | 24 | 80 | 0 | 88.75 | 88.75 | 80 | 0 | 0 | 0 |  |  |  | 2013-12-05 08:00 | 2013-12-16 17:00 |  | 2013-11-03 08:00 | 2013-11-13 17:00 | 2013-11-03 08:00 | 2013-11-13 17:00 | 2013-11-03 08:00 | 2013-11-13 17:00 | 2013-12-05 08:00 | 2013-12-16 17:00 |  | PT_Normal |  |  |  |  | Y+U4N5alQoGSNrnRAXmRhw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37940 | N | N | 15 | WATER TANK ENCLOSURE |  | 125159 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 88.75 | LABOR- SUBCONTRACTOR
%R | 503335 | 6359 | 125163 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AMKWEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 80 | 0 | 80 | 0 | 47.8 | 47.8 | 80 | 0 | 0 | 0 |  |  |  | 2013-12-17 08:00 | 2013-12-29 17:00 |  | 2013-12-05 08:00 | 2013-12-16 17:00 | 2013-12-05 08:00 | 2013-12-16 17:00 | 2013-12-05 08:00 | 2013-12-16 17:00 | 2013-12-17 08:00 | 2013-12-29 17:00 |  | PT_Normal |  |  |  |  | 3Loh2LkVSWeUMJHfyP+BFQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 37940 | N | N | 15 | WATER TANK ENCLOSURE |  | 125159 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 47.8 | LABOR- SUBCONTRACTOR
%R | 503336 | 6359 | 125167 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 104 | 0 | 160 | 0 | 182.4 | 182.4 | 160 | 0 | 0 | 0 |  |  |  | 2013-07-02 08:00 | 2013-07-24 17:00 |  | 2013-06-17 08:00 | 2013-07-09 17:00 | 2013-06-17 08:00 | 2013-07-09 17:00 | 2013-06-17 08:00 | 2013-07-09 17:00 | 2013-07-02 08:00 | 2013-07-24 17:00 |  | PT_Normal |  |  |  |  | agxS4WYkRjadYvrV3iqZxA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38560 | N | N | 10 | GROUND FLOOR |  | 125166 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 182.4 | LABOR- SUBCONTRACTOR
%R | 503337 | 6359 | 125167 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2PLGF4320 | Installation of Water Heater | 8178 | 496 | 224 | 120 | 0 | 151.2 | 151.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-15 17:00 |  | 2014-02-16 08:00 | 2014-03-04 17:00 | 2014-02-16 08:00 | 2014-03-04 17:00 | 2014-02-16 08:00 | 2014-03-04 17:00 | 2014-04-29 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | /nEb6c7hTc2IsdiLqnP5lg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38560 | N | N | 10 | GROUND FLOOR |  | 125166 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 151.2 | LABOR- SUBCONTRACTOR
%R | 503338 | 6359 | 125167 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 104 | 0 | 160 | 0 | 1435.2 | 1435.2 | 160 | 0 | 0 | 0 |  |  |  | 2013-10-13 08:00 | 2013-11-06 17:00 |  | 2013-09-28 08:00 | 2013-10-22 17:00 | 2013-09-28 08:00 | 2013-10-22 17:00 | 2013-09-28 08:00 | 2013-10-22 17:00 | 2013-10-13 08:00 | 2013-11-06 17:00 |  | PT_Normal |  |  |  |  | d8hmgZAOTuCxZZgY6AfygA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38560 | N | N | 10 | GROUND FLOOR |  | 125166 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1435.2 | LABOR- SUBCONTRACTOR
%R | 503339 | 6359 | 125167 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2PLGF4310 | Installation of Drainage pipes &testing | 8178 | 256 | 72 | 144 | 0 | 72 | 72 | 144 | 0 | 0 | 0 |  |  |  | 2013-11-14 08:00 | 2013-12-04 17:00 |  | 2013-10-06 08:00 | 2013-10-28 17:00 | 2013-10-06 08:00 | 2013-10-28 17:00 | 2013-10-06 08:00 | 2013-10-28 17:00 | 2013-11-14 08:00 | 2013-12-04 17:00 |  | PT_Normal |  |  |  |  | de7lv/BBT8elU3r+FyhfHQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38560 | N | N | 10 | GROUND FLOOR |  | 125166 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 72 | LABOR- SUBCONTRACTOR
%R | 503340 | 6359 | 125167 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2PLGF4315 | Sanitary Fittings & Accessories | 8178 | 56 | 0 | 160 | 0 | 218.4 | 218.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-03-01 17:00 |  | 2014-01-28 08:00 | 2014-02-20 17:00 | 2014-01-28 08:00 | 2014-02-20 17:00 | 2014-01-28 08:00 | 2014-02-20 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | k/UnKE6iRkqq94B3UZAZAQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38560 | N | N | 10 | GROUND FLOOR |  | 125166 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 218.4 | LABOR- SUBCONTRACTOR
%R | 503341 | 6359 | 125168 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2PLRF4350 | Installation of Rain water Pipes | 8178 | 200 | 0 | 120 | 0 | 265.2 | 265.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-08 17:00 |  | 2013-12-24 08:00 | 2014-01-09 17:00 | 2013-12-24 08:00 | 2014-01-09 17:00 | 2013-12-24 08:00 | 2014-01-09 17:00 | 2014-01-22 08:00 | 2014-02-08 17:00 |  | PT_Normal |  |  |  |  | 0BXhYEOSQ02VbYiZqUdnnw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38580 | N | N | 20 | ROOF |  | 125166 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 265.2 | LABOR- SUBCONTRACTOR
%R | 503342 | 6359 | 125170 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 104 | 0 | 160 | 0 | 594.8 | 594.8 | 160 | 0 | 0 | 0 |  |  |  | 2013-10-13 08:00 | 2013-11-06 17:00 |  | 2013-09-28 08:00 | 2013-10-22 17:00 | 2013-09-28 08:00 | 2013-10-22 17:00 | 2013-09-28 08:00 | 2013-10-22 17:00 | 2013-10-13 08:00 | 2013-11-06 17:00 |  | PT_Normal |  |  |  |  | qAmw94RqQSaWDB5OouwREg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38520 | N | N | 10 | GROUND FLOOR |  | 125169 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 594.8 | LABOR- SUBCONTRACTOR
%R | 503343 | 6359 | 125170 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ELGF4005 | Cable tray & trunking installation | 8178 | 104 | 0 | 160 | 0 | 2044.8 | 2044.8 | 160 | 0 | 0 | 0 |  |  |  | 2013-10-30 08:00 | 2013-11-21 17:00 |  | 2013-10-13 08:00 | 2013-11-06 17:00 | 2013-10-13 08:00 | 2013-11-06 17:00 | 2013-10-13 08:00 | 2013-11-06 17:00 | 2013-10-30 08:00 | 2013-11-21 17:00 |  | PT_Normal |  |  |  |  | YHzK4ZjoTTWzm8Up+zO1mQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38520 | N | N | 10 | GROUND FLOOR |  | 125169 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 2044.8 | LABOR- SUBCONTRACTOR
%R | 503344 | 6359 | 125170 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ELGF4010 | Installation of wiring & Main Cabling | 8178 | 328 | 272 | 160 | 0 | 414.8 | 414.8 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-10 08:00 | 2014-01-02 17:00 |  | 2013-10-23 08:00 | 2013-11-14 17:00 | 2013-10-23 08:00 | 2013-11-14 17:00 | 2013-10-23 08:00 | 2013-11-14 17:00 | 2013-12-10 08:00 | 2014-01-02 17:00 |  | PT_Normal |  |  |  |  | tpZ1j9+FRAOIqI4BesvHpw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38520 | N | N | 10 | GROUND FLOOR |  | 125169 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 414.8 | LABOR- SUBCONTRACTOR
%R | 503345 | 6359 | 125170 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 384 | 0 | 160 | 0 | 170.4 | 170.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-08 17:00 |  | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | SimkYRgHQ7+Wp5CDGDQmuQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38520 | N | N | 10 | GROUND FLOOR |  | 125169 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 170.4 | LABOR- SUBCONTRACTOR
%R | 503346 | 6359 | 125170 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 384 | 0 | 160 | 0 | 395.6 | 395.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-29 08:00 | 2014-04-20 17:00 |  | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-03-29 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | T3ckivPJQXazXrf4lOgn1Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38520 | N | N | 10 | GROUND FLOOR |  | 125169 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 395.6 | LABOR- SUBCONTRACTOR
%R | 503347 | 6359 | 125170 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 104 | 0 | 160 | 0 | 1108.8 | 1108.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-06 17:00 |  | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | U7SKlNjERk68gFMttHXJIQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38520 | N | N | 10 | GROUND FLOOR |  | 125169 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1108.8 | LABOR- SUBCONTRACTOR
%R | 503348 | 6359 | 125170 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ELGF4030 | Installation of Telephone System | 8178 | 408 | 24 | 160 | 0 | 152.4 | 152.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-01 08:00 | 2014-04-23 17:00 |  | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-04-01 08:00 | 2014-04-23 17:00 |  | PT_Normal |  |  |  |  | TCVXM6YsTLWTDQ6vFrpbxQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38520 | N | N | 10 | GROUND FLOOR |  | 125169 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 152.4 | LABOR- SUBCONTRACTOR
%R | 503349 | 6359 | 125171 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ELRF4070 | Installation of Isolator | 8178 | 384 | 0 | 144 | 0 | 361.2 | 361.2 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-01 17:00 |  | 2014-02-15 08:00 | 2014-03-06 17:00 | 2014-02-15 08:00 | 2014-03-06 17:00 | 2014-02-15 08:00 | 2014-03-06 17:00 | 2014-04-12 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | qDvi/xblQOeCfqCwq3XE0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38540 | N | N | 20 | ROOF |  | 125169 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 361.2 | LABOR- SUBCONTRACTOR
%R | 503350 | 6359 | 125171 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ELRF4075 | Installation of TV Dish Antenna | 8178 | 384 | 112 | 160 | 0 | 188.4 | 188.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-05-15 17:00 |  | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-04-23 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | tjpEyWH9RLqM91kG7Nf7Ow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38540 | N | N | 20 | ROOF |  | 125169 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 188.4 | LABOR- SUBCONTRACTOR
%R | 503351 | 6359 | 125173 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ACRF4630 | Installation of Refrigerant Pipes | 8178 | 480 | 40 | 160 | 0 | 17.2 | 17.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-02-23 17:00 |  | 2013-11-20 08:00 | 2013-12-12 17:00 | 2013-11-20 08:00 | 2013-12-12 17:00 | 2013-11-20 08:00 | 2013-12-12 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | jtNyJ+9fSqy5Mw68ieykEQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38620 | N | N | 20 | ROOF |  | 125172 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 17.2 | LABOR- SUBCONTRACTOR
%R | 503352 | 6359 | 125173 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ACRF4635 | Installation of Condensing Unit | 8178 | 312 | 40 | 200 | 0 | 130.8 | 130.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | 4cqFykrcRCG+YTt61LLTrA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38620 | N | N | 20 | ROOF |  | 125172 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 130.8 | LABOR- SUBCONTRACTOR
%R | 503353 | 6359 | 125174 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ACGF4600 | Installation AC Pipes | 8178 | 224 | 0 | 160 | 0 | 556.8 | 556.8 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-30 08:00 | 2013-12-23 17:00 |  | 2013-10-28 08:00 | 2013-11-19 17:00 | 2013-10-28 08:00 | 2013-11-19 17:00 | 2013-10-28 08:00 | 2013-11-19 17:00 | 2013-11-30 08:00 | 2013-12-23 17:00 |  | PT_Normal |  |  |  |  | HpcxR2+uRYKuVYSiiDsCBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38600 | N | N | 10 | GROUND FLOOR |  | 125172 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 556.8 | LABOR- SUBCONTRACTOR
%R | 503354 | 6359 | 125174 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ACGF4605 | Fixing of Ventilation Equipments | 8178 | 312 | 0 | 200 | 0 | 85.2 | 85.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-12 17:00 |  | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 |  | PT_Normal |  |  |  |  | YlK0/8sQS5KsiJbCklT/dw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38600 | N | N | 10 | GROUND FLOOR |  | 125172 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 85.2 | LABOR- SUBCONTRACTOR
%R | 503355 | 6359 | 125174 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ACGF4610 | Fixing of Split AC | 8178 | 312 | 40 | 160 | 0 | 154.8 | 154.8 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-04-28 17:00 |  | 2014-02-19 08:00 | 2014-03-13 17:00 | 2014-02-19 08:00 | 2014-03-13 17:00 | 2014-02-19 08:00 | 2014-03-13 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | nYE92YMDSO2QRhpVac7/eg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38600 | N | N | 10 | GROUND FLOOR |  | 125172 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 154.8 | LABOR- SUBCONTRACTOR
%R | 503356 | 6359 | 125177 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 240 | 0 | 144 | 0 | 344.5 | 344.5 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-09 08:00 | 2013-12-30 17:00 |  | 2013-11-04 08:00 | 2013-11-24 17:00 | 2013-11-04 08:00 | 2013-11-24 17:00 | 2013-11-04 08:00 | 2013-11-24 17:00 | 2013-12-09 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | 2x/hPppbRxylGYQUSl8zlw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38480 | N | N | 10 | ROOF |  | 125176 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 344.5 | TILE MASON SK
%R | 503357 | 6359 | 125177 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARRF3660 | Installation of Access Ladder | 8178 | 552 | 40 | 160 | 0 | 132 | 132 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-02-23 17:00 |  | 2013-11-10 08:00 | 2013-12-02 17:00 | 2013-11-10 08:00 | 2013-12-02 17:00 | 2013-11-10 08:00 | 2013-12-02 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | WGAzc6c9QQSDAkWJ9wjl5Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38480 | N | N | 10 | ROOF |  | 125176 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 132 | LABOR- SUBCONTRACTOR
%R | 503358 | 6359 | 125177 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARRF3625 | Laying of Pitched Roof | 8174 | 240 | 0 | 200 | 0 | 256 | 256 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-06 08:00 | 2013-12-04 17:00 |  | 2013-09-30 08:00 | 2013-10-30 17:00 | 2013-09-30 08:00 | 2013-10-30 17:00 | 2013-09-30 08:00 | 2013-10-30 17:00 | 2013-11-06 08:00 | 2013-12-04 17:00 |  | PT_Normal |  |  |  |  | edQqAHg3Q+uqhtVOERxGAA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38480 | N | N | 10 | ROOF |  | 125176 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 128 | INTERLOCK MASON SK
%R | 503359 | 6359 | 125177 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARRF3630 | Leveling Screed for Waterproofing | 8164 | 240 | 0 | 144 | 0 | 195.5 | 195.5 | 144 | 0 | 0 | 0 |  |  |  | 2013-11-20 08:00 | 2013-12-10 17:00 |  | 2013-10-14 08:00 | 2013-11-05 17:00 | 2013-10-14 08:00 | 2013-11-05 17:00 | 2013-10-14 08:00 | 2013-11-05 17:00 | 2013-11-20 08:00 | 2013-12-10 17:00 |  | PT_Normal |  |  |  |  | 3+pAnhooRvCxAqSjeqN0Ug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38480 | N | N | 10 | ROOF |  | 125176 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 195.5 | SCREED MASON SK
%R | 503360 | 6359 | 125177 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARRF3635 | Laying of Waterproofing Membrane | 8178 | 240 | 0 | 144 | 0 | 722.25 | 722.25 | 144 | 0 | 0 | 0 |  |  |  | 2013-11-26 08:00 | 2013-12-16 17:00 |  | 2013-10-22 08:00 | 2013-11-11 17:00 | 2013-10-22 08:00 | 2013-11-11 17:00 | 2013-10-22 08:00 | 2013-11-11 17:00 | 2013-11-26 08:00 | 2013-12-16 17:00 |  | PT_Normal |  |  |  |  | Uxrb0HVyQiuS1qegYrqWnQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38480 | N | N | 10 | ROOF |  | 125176 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 722.25 | LABOR- SUBCONTRACTOR
%R | 503361 | 6359 | 125177 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARRF3640 | Installation of Insulation & Protection | 8178 | 240 | 0 | 144 | 0 | 343.75 | 343.75 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-01 08:00 | 2013-12-22 17:00 |  | 2013-10-27 08:00 | 2013-11-16 17:00 | 2013-10-27 08:00 | 2013-11-16 17:00 | 2013-10-27 08:00 | 2013-11-16 17:00 | 2013-12-01 08:00 | 2013-12-22 17:00 |  | PT_Normal |  |  |  |  | 7KEcl9H8SPWv/frg54C8QQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38480 | N | N | 10 | ROOF |  | 125176 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 343.75 | LABOR- SUBCONTRACTOR
%R | 503362 | 6359 | 125178 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2AREL3665 | External Plastering | 8169 | 240 | 0 | 200 | 0 | 4012.5 | 4012.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-22 08:00 | 2014-01-19 17:00 |  | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 |  | PT_Normal |  |  |  |  | vOgC/iYNS56s52Tehx0aiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38490 | N | N | 15 | ELEVATION |  | 125176 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 4012.5 | PLASTER MASON SK
%R | 503363 | 6359 | 125178 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2AREL3680 | External Painting | 8178 | 440 | 40 | 160 | 0 | 1408 | 1408 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-06 17:00 |  | 2013-12-08 08:00 | 2013-12-31 17:00 | 2013-12-08 08:00 | 2013-12-31 17:00 | 2013-12-08 08:00 | 2013-12-31 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | cBNUIkQNTuKodTaKlk8x1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38490 | N | N | 15 | ELEVATION |  | 125176 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1408 | LABOR- SUBCONTRACTOR
%R | 503364 | 6359 | 125180 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARGF3000 | Block work | 8168 | 104 | 0 | 200 | 0 | 5700 | 5700 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-29 08:00 | 2013-10-29 17:00 |  | 2013-09-14 08:00 | 2013-10-12 17:00 | 2013-09-14 08:00 | 2013-10-12 17:00 | 2013-09-14 08:00 | 2013-10-12 17:00 | 2013-09-29 08:00 | 2013-10-29 17:00 |  | PT_Normal |  |  |  |  | Jg73Wv9CSWeDZY/aMtP+9A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38440 | N | N | 10 | GROUND FLOOR |  | 125179 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 5700 | BLOCK MASON SK
%R | 503365 | 6359 | 125180 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARGF3005 | Plastering work | 8169 | 104 | 0 | 200 | 0 | 2850 | 2850 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-21 08:00 | 2013-11-18 17:00 |  | 2013-10-03 08:00 | 2013-11-03 17:00 | 2013-10-03 08:00 | 2013-11-03 17:00 | 2013-10-03 08:00 | 2013-11-03 17:00 | 2013-10-21 08:00 | 2013-11-18 17:00 |  | PT_Normal |  |  |  |  | gvIex9CuQKaEPSV5N+/kew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38440 | N | N | 10 | GROUND FLOOR |  | 125179 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 1425 | PLASTER MASON SK
%R | 503366 | 6359 | 125180 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARGF3010 | Flooring screed | 8164 | 200 | 144 | 160 | 0 | 634.25 | 634.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-24 08:00 | 2013-12-16 17:00 |  | 2013-10-26 08:00 | 2013-11-17 17:00 | 2013-10-26 08:00 | 2013-11-17 17:00 | 2013-10-26 08:00 | 2013-11-17 17:00 | 2013-11-24 08:00 | 2013-12-16 17:00 |  | PT_Normal |  |  |  |  | 6judCWByQ2aovX+GUkGr3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38440 | N | N | 10 | GROUND FLOOR |  | 125179 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 634.25 | SCREED MASON SK
%R | 503367 | 6359 | 125180 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 112 | 0 | 160 | 0 | 87 | 87 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-05 08:00 | 2013-11-27 17:00 |  | 2013-10-20 08:00 | 2013-11-11 17:00 | 2013-10-20 08:00 | 2013-11-11 17:00 | 2013-10-20 08:00 | 2013-11-11 17:00 | 2013-11-05 08:00 | 2013-11-27 17:00 |  | PT_Normal |  |  |  |  | oIGsQGw4Q4e90PLF8sm08g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38440 | N | N | 10 | GROUND FLOOR |  | 125179 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 87 | LABOR- SUBCONTRACTOR
%R | 503368 | 6359 | 125180 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARGF3030 | Paint First coat | 8178 | 48 | 0 | 160 | 0 | 1801.8 | 1801.8 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-07 08:00 | 2013-11-30 17:00 |  | 2013-10-31 08:00 | 2013-11-23 17:00 | 2013-10-31 08:00 | 2013-11-23 17:00 | 2013-10-31 08:00 | 2013-11-23 17:00 | 2013-11-07 08:00 | 2013-11-30 17:00 |  | PT_Normal |  |  |  |  | PMjOH9fAQqSmydMNELZEPA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38440 | N | N | 10 | GROUND FLOOR |  | 125179 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1801.8 | LABOR- SUBCONTRACTOR
%R | 503369 | 6359 | 125180 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARGF3020 | Ceramic Wall Tiling | 8170 | 112 | 56 | 120 | 0 | 1012.5 | 1012.5 | 120 | 0 | 0 | 0 |  |  |  | 2013-11-24 08:00 | 2013-12-10 17:00 |  | 2013-11-07 08:00 | 2013-11-24 17:00 | 2013-11-07 08:00 | 2013-11-24 17:00 | 2013-11-07 08:00 | 2013-11-24 17:00 | 2013-11-24 08:00 | 2013-12-10 17:00 |  | PT_Normal |  |  |  |  | GxnA6J+sSeGfRtZOdz+10w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38440 | N | N | 10 | GROUND FLOOR |  | 125179 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1012.5 | TILE MASON SK
%R | 503370 | 6359 | 125180 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARGF3025 | Porcelain Tile flooring | 8170 | 56 | 0 | 160 | 0 | 1030.25 | 1030.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-10 08:00 | 2014-01-02 17:00 |  | 2013-12-02 08:00 | 2013-12-25 17:00 | 2013-12-02 08:00 | 2013-12-25 17:00 | 2013-12-02 08:00 | 2013-12-25 17:00 | 2013-12-10 08:00 | 2014-01-02 17:00 |  | PT_Normal |  |  |  |  | 7S3tqbzZSqahK2EfAjolgg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38440 | N | N | 10 | GROUND FLOOR |  | 125179 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1030.25 | TILE MASON SK
%R | 503371 | 6359 | 125180 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARGF3040 | Cobble Tile flooring | 8170 | 208 | 24 | 120 | 0 | 300 | 300 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-08 08:00 | 2014-02-25 17:00 |  | 2014-01-08 08:00 | 2014-01-25 17:00 | 2014-01-08 08:00 | 2014-01-25 17:00 | 2014-01-08 08:00 | 2014-01-25 17:00 | 2014-02-08 08:00 | 2014-02-25 17:00 |  | PT_Normal |  |  |  |  | i5dbrqPjTzufzZ1vnFGaNA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38440 | N | N | 10 | GROUND FLOOR |  | 125179 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 300 | TILE MASON SK
%R | 503372 | 6359 | 125180 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 104 | 0 | 144 | 0 | 1575 | 1575 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-05 08:00 | 2014-01-25 17:00 |  | 2013-12-21 08:00 | 2014-01-09 17:00 | 2013-12-21 08:00 | 2014-01-09 17:00 | 2013-12-21 08:00 | 2014-01-09 17:00 | 2014-01-05 08:00 | 2014-01-25 17:00 |  | PT_Normal |  |  |  |  | /W7XycU4ROuL51Weu641YA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38440 | N | N | 10 | GROUND FLOOR |  | 125179 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1575 | TILE MASON SK
%R | 503373 | 6359 | 125180 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARGF3045 | Fixing of Suspension systems | 8178 | 56 | 0 | 120 | 0 | 653.5 | 653.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-02 08:00 | 2014-01-19 17:00 |  | 2013-12-25 08:00 | 2014-01-11 17:00 | 2013-12-25 08:00 | 2014-01-11 17:00 | 2013-12-25 08:00 | 2014-01-11 17:00 | 2014-01-02 08:00 | 2014-01-19 17:00 |  | PT_Normal |  |  |  |  | UhRGPz/FR1+CZLrdZV7U/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38440 | N | N | 10 | GROUND FLOOR |  | 125179 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 653.5 | LABOR- SUBCONTRACTOR
%R | 503374 | 6359 | 125180 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARGF3060 | Gypsum board false ceiling | 8178 | 56 | 0 | 160 | 0 | 653.5 | 653.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-19 08:00 | 2014-02-10 17:00 |  | 2014-01-11 08:00 | 2014-02-02 17:00 | 2014-01-11 08:00 | 2014-02-02 17:00 | 2014-01-11 08:00 | 2014-02-02 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | wUHa2swSTemRkrp/1lzqxg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38440 | N | N | 10 | GROUND FLOOR |  | 125179 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 653.5 | LABOR- SUBCONTRACTOR
%R | 503375 | 6359 | 125180 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARGF3065 | Wooden door | 8178 | 56 | 0 | 120 | 0 | 198 | 198 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-02-17 17:00 |  | 2014-01-22 08:00 | 2014-02-08 17:00 | 2014-01-22 08:00 | 2014-02-08 17:00 | 2014-01-22 08:00 | 2014-02-08 17:00 | 2014-01-30 08:00 | 2014-02-17 17:00 |  | PT_Normal |  |  |  |  | EPQDZMMoQr2nbzkY+p38/A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38440 | N | N | 10 | GROUND FLOOR |  | 125179 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 198 | LABOR- SUBCONTRACTOR
%R | 503376 | 6359 | 125180 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARGF3080 | Aluminum windows | 8178 | 392 | 120 | 144 | 0 | 132 | 132 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-08 08:00 | 2014-04-28 17:00 |  | 2014-02-09 08:00 | 2014-03-02 17:00 | 2014-02-09 08:00 | 2014-03-02 17:00 | 2014-02-09 08:00 | 2014-03-02 17:00 | 2014-04-08 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | /lAvxsJnTTi016nF2SWmOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38440 | N | N | 10 | GROUND FLOOR |  | 125179 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 132 | LABOR- SUBCONTRACTOR
%R | 503377 | 6359 | 125180 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARGF3075 | Carpentry & Joinery Works | 8178 | 64 | 0 | 144 | 0 | 528 | 528 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-02-27 17:00 |  | 2014-01-28 08:00 | 2014-02-18 17:00 | 2014-01-28 08:00 | 2014-02-18 17:00 | 2014-01-28 08:00 | 2014-02-18 17:00 | 2014-02-06 08:00 | 2014-02-27 17:00 |  | PT_Normal |  |  |  |  | VIG4GOm2SMW2jIipp1KriA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38440 | N | N | 10 | GROUND FLOOR |  | 125179 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 528 | LABOR- SUBCONTRACTOR
%R | 503378 | 6359 | 125180 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARGF3090 | Installation of Granite Counter Top | 8171 | 64 | 0 | 120 | 0 | 99 | 99 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-06 17:00 |  | 2014-02-08 08:00 | 2014-02-25 17:00 | 2014-02-08 08:00 | 2014-02-25 17:00 | 2014-02-08 08:00 | 2014-02-25 17:00 | 2014-02-18 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | dCW4TJvDQ6q9pmGGAlTBMw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38440 | N | N | 10 | GROUND FLOOR |  | 125179 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 99 | GRANITE MASON SK
%R | 503379 | 6359 | 125180 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ARGF3095 | Final Painting | 8178 | 272 | 0 | 200 | 0 | 1801.8 | 1801.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | Pap0qlI7TdW0WL/A5UESzA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38440 | N | N | 10 | GROUND FLOOR |  | 125179 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1801.8 | LABOR- SUBCONTRACTOR
%R | 503380 | 6359 | 125183 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2STRF2060 | Construction of Parapets | 8165 | 152 | 0 | 160 | 0 | 521.5 | 521.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-09-19 08:00 | 2013-10-12 17:00 |  | 2013-08-28 08:00 | 2013-09-19 17:00 | 2013-08-28 08:00 | 2013-09-19 17:00 | 2013-08-28 08:00 | 2013-09-19 17:00 | 2013-09-19 08:00 | 2013-10-12 17:00 |  | PT_Normal |  |  |  |  | T5/wivEtSlyv/ddQHWxs6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38410 | N | N | 20 | ROOF |  | 125182 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 521.5 | STEEL FIXERS SK
%R | 503381 | 6359 | 125183 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2STRF2065 | Construction of up stands/Plinth | 8166 | 336 | 96 | 160 | 0 | 84 | 84 | 160 | 0 | 0 | 0 |  |  |  | 2013-10-26 08:00 | 2013-11-17 17:00 |  | 2013-09-04 08:00 | 2013-09-26 17:00 | 2013-09-04 08:00 | 2013-09-26 17:00 | 2013-09-04 08:00 | 2013-09-26 17:00 | 2013-10-26 08:00 | 2013-11-17 17:00 |  | PT_Normal |  |  |  |  | z5dTGIPiQ5m2HCczfDx41Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43430 |  |  |  |  | CARPENTERS SK | J305 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38410 | N | N | 20 | ROOF |  | 125182 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 84 | CARPENTERS SK
%R | 503382 | 6359 | 125184 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2STGF2000 | Column-Rebar & Formwork | 8165 | 104 | 0 | 160 | 0 | 1524.25 | 1524.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-07-28 08:00 | 2013-08-22 17:00 |  | 2013-07-13 08:00 | 2013-08-04 17:00 | 2013-07-13 08:00 | 2013-08-04 17:00 | 2013-07-13 08:00 | 2013-08-04 17:00 | 2013-07-28 08:00 | 2013-08-22 17:00 |  | PT_Normal |  |  |  |  | x3g22rLpSNWeFkCB9sH36g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38390 | N | N | 10 | GROUND FLOOR |  | 125182 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 1524.25 | STEEL FIXERS SK
%R | 503383 | 6359 | 125184 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2STGF2005 | Column-Concrete | 8167 | 104 | 0 | 120 | 0 | 105 | 105 | 120 | 0 | 0 | 0 |  |  |  | 2013-08-07 08:00 | 2013-08-27 17:00 |  | 2013-07-23 08:00 | 2013-08-08 17:00 | 2013-07-23 08:00 | 2013-08-08 17:00 | 2013-07-23 08:00 | 2013-08-08 17:00 | 2013-08-07 08:00 | 2013-08-27 17:00 |  | PT_Normal |  |  |  |  | 7bZL3ZwyQoy9Edl5VjB7zA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38390 | N | N | 10 | GROUND FLOOR |  | 125182 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 105 | CONCRETE MASON SK
%R | 503384 | 6359 | 125184 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 104 | 0 | 200 | 0 | 6076 | 6076 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-19 08:00 | 2013-09-16 17:00 |  | 2013-07-31 08:00 | 2013-09-01 17:00 | 2013-07-31 08:00 | 2013-09-01 17:00 | 2013-07-31 08:00 | 2013-09-01 17:00 | 2013-08-19 08:00 | 2013-09-16 17:00 |  | PT_Normal |  |  |  |  | nuwZrHipRXihepspeSSewA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38390 | N | N | 10 | GROUND FLOOR |  | 125182 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 3038 | STEEL FIXERS SK
%R | 503385 | 6359 | 125184 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 104 | 0 | 120 | 0 | 1302 | 1302 | 120 | 0 | 0 | 0 |  |  |  | 2013-09-04 08:00 | 2013-09-21 17:00 |  | 2013-08-20 08:00 | 2013-09-05 17:00 | 2013-08-20 08:00 | 2013-09-05 17:00 | 2013-08-20 08:00 | 2013-09-05 17:00 | 2013-09-04 08:00 | 2013-09-21 17:00 |  | PT_Normal |  |  |  |  | kgsD/eV9SMabLPaXby0ImQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38390 | N | N | 10 | GROUND FLOOR |  | 125182 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 1302 | CONCRETE MASON SK
%R | 503386 | 6359 | 125186 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2STUG1000 | Footing Excavation | 8177 | 104 | 0 | 200 | 0 | 476 | 476 | 200 | 224 | 0 | 224 |  |  |  | 2013-04-08 08:00 | 2013-05-06 17:00 |  | 2013-03-24 08:00 | 2013-04-21 17:00 | 2013-03-24 08:00 | 2013-04-21 17:00 | 2013-03-24 08:00 | 2013-04-21 17:00 | 2013-04-08 08:00 | 2013-05-06 17:00 |  | PT_Normal |  |  |  |  | XaFLJZSuQgCOCET8+gWzmg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38370 | N | N | 10 | UPTO GRADE SLAB |  | 125185 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 476 | LABOR - CIVIL
%R | 503387 | 6359 | 125186 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2STUG1005 | Footing Antitermite | 8178 | 104 | 0 | 160 | 0 | 902 | 902 | 160 | 0 | 0 | 0 |  |  |  | 2013-04-20 08:00 | 2013-05-12 17:00 |  | 2013-04-04 08:00 | 2013-04-27 17:00 | 2013-04-04 08:00 | 2013-04-27 17:00 | 2013-04-04 08:00 | 2013-04-27 17:00 | 2013-04-20 08:00 | 2013-05-12 17:00 |  | PT_Normal |  |  |  |  | 2OnDl0hySRmaBFoU4+mCBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38370 | N | N | 10 | UPTO GRADE SLAB |  | 125185 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 902 | LABOR- SUBCONTRACTOR
%R | 503388 | 6359 | 125186 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2STUG1010 | Footing Blinding | 8163 | 104 | 0 | 160 | 0 | 29.75 | 29.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-04-22 08:00 | 2013-05-14 17:00 |  | 2013-04-07 08:00 | 2013-04-29 17:00 | 2013-04-07 08:00 | 2013-04-29 17:00 | 2013-04-07 08:00 | 2013-04-29 17:00 | 2013-04-22 08:00 | 2013-05-14 17:00 |  | PT_Normal |  |  |  |  | Zu6yHkdXTUu93qyQCHZOJA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38370 | N | N | 10 | UPTO GRADE SLAB |  | 125185 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 29.75 | BLINDING MASON SK
%R | 503389 | 6359 | 125186 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2STUG1015 | Footing Waterproofing & Screed | 8164 | 104 | 0 | 160 | 0 | 681 | 681 | 160 | 0 | 0 | 0 |  |  |  | 2013-04-28 08:00 | 2013-05-20 17:00 |  | 2013-04-13 08:00 | 2013-05-05 17:00 | 2013-04-13 08:00 | 2013-05-05 17:00 | 2013-04-13 08:00 | 2013-05-05 17:00 | 2013-04-28 08:00 | 2013-05-20 17:00 |  | PT_Normal |  |  |  |  | YDX11mxaQcWCSXPrvY+7Ww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38370 | N | N | 10 | UPTO GRADE SLAB |  | 125185 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 681 | SCREED MASON SK
%R | 503390 | 6359 | 125186 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2STUG1020 | Construction of foundations | 8165 | 104 | 0 | 160 | 0 | 1335.25 | 1335.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-05-07 08:00 | 2013-05-29 17:00 |  | 2013-04-22 08:00 | 2013-05-14 17:00 | 2013-04-22 08:00 | 2013-05-14 17:00 | 2013-04-22 08:00 | 2013-05-14 17:00 | 2013-05-07 08:00 | 2013-05-29 17:00 |  | PT_Normal |  |  |  |  | Gsak5FH9Rpur5WAM7X00jQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38370 | N | N | 10 | UPTO GRADE SLAB |  | 125185 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 1335.25 | STEEL FIXERS SK
%R | 503391 | 6359 | 125186 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2STUG1025 | Construction of neck of columns | 8165 | 104 | 0 | 160 | 0 | 1389.5 | 1389.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-05-16 08:00 | 2013-06-08 17:00 |  | 2013-05-01 08:00 | 2013-05-23 17:00 | 2013-05-01 08:00 | 2013-05-23 17:00 | 2013-05-01 08:00 | 2013-05-23 17:00 | 2013-05-16 08:00 | 2013-06-08 17:00 |  | PT_Normal |  |  |  |  | b09m8bfjRxaIinEWGKcw1w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38370 | N | N | 10 | UPTO GRADE SLAB |  | 125185 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 1389.5 | STEEL FIXERS SK
%R | 503392 | 6359 | 125186 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2STUG1030 | Waterproofing Footing & Neck Column | 8178 | 104 | 0 | 160 | 0 | 125.5 | 125.5 | 160 | 0 | 0 | 0 |  |  |  | 2013-05-26 08:00 | 2013-06-17 17:00 |  | 2013-05-11 08:00 | 2013-06-02 17:00 | 2013-05-11 08:00 | 2013-06-02 17:00 | 2013-05-11 08:00 | 2013-06-02 17:00 | 2013-05-26 08:00 | 2013-06-17 17:00 |  | PT_Normal |  |  |  |  | qB6uQs6CQE+47eguf/oW+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38370 | N | N | 10 | UPTO GRADE SLAB |  | 125185 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 125.5 | LABOR- SUBCONTRACTOR
%R | 503393 | 6359 | 125186 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 104 | 0 | 160 | 0 | 822 | 822 | 160 | 660 | 0 | 660 |  |  |  | 2013-06-06 08:00 | 2013-06-29 17:00 |  | 2013-05-22 08:00 | 2013-06-13 17:00 | 2013-05-22 08:00 | 2013-06-13 17:00 | 2013-05-22 08:00 | 2013-06-13 17:00 | 2013-06-06 08:00 | 2013-06-29 17:00 |  | PT_Normal |  |  |  |  | PY8gccm8RR6U22LOAoWraQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38370 | N | N | 10 | UPTO GRADE SLAB |  | 125185 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 822 | LABOR - CIVIL
%R | 503394 | 6359 | 125186 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2STUG1040 | Construction of Grade Beams | 8163 | 104 | 0 | 200 | 0 | 2514.75 | 2514.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-18 08:00 | 2013-07-16 17:00 |  | 2013-06-03 08:00 | 2013-07-01 17:00 | 2013-06-03 08:00 | 2013-07-01 17:00 | 2013-06-03 08:00 | 2013-07-01 17:00 | 2013-06-18 08:00 | 2013-07-16 17:00 |  | PT_Normal |  |  |  |  | R2amyerVSyuykGEvSD6vTQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38370 | N | N | 10 | UPTO GRADE SLAB |  | 125185 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 2514.75 | BLINDING MASON SK
%R | 503395 | 6359 | 125186 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2STUG1045 | Construction of slab on grade | 8163 | 104 | 0 | 200 | 0 | 1541.75 | 1541.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-10 08:00 | 2013-08-07 17:00 |  | 2013-06-25 08:00 | 2013-07-23 17:00 | 2013-06-25 08:00 | 2013-07-23 17:00 | 2013-06-25 08:00 | 2013-07-23 17:00 | 2013-07-10 08:00 | 2013-08-07 17:00 |  | PT_Normal |  |  |  |  | g1EZaK4mSaO2JEO3cILa8A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38370 | N | N | 10 | UPTO GRADE SLAB |  | 125185 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 1541.75 | BLINDING MASON SK
%R | 503396 | 6359 | 125188 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2WEEX5030 | Excavation | 8177 | 120 | 0 | 160 | 0 | 116 | 116 | 160 | 80 | 0 | 80 |  |  |  | 2013-11-06 08:00 | 2013-11-28 17:00 |  | 2013-10-20 08:00 | 2013-11-11 17:00 | 2013-10-20 08:00 | 2013-11-11 17:00 | 2013-10-20 08:00 | 2013-11-11 17:00 | 2013-11-06 08:00 | 2013-11-28 17:00 |  | PT_Normal |  |  |  |  | fo+UlYW4RsibkqkxtBJ/2A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38660 | N | N | 15 | WATER TANK ENCLOSURE |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 116 | LABOR - CIVIL
%R | 503397 | 6359 | 125188 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2WEEX5035 | Construction of Raft | 8167 | 256 | 0 | 200 | 0 | 210 | 210 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-02 08:00 | 2013-12-31 17:00 |  | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-10-26 08:00 | 2013-11-23 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 |  | PT_Normal |  |  |  |  | FDBEng5MQtywcFI1sjocAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38660 | N | N | 15 | WATER TANK ENCLOSURE |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 210 | CONCRETE MASON SK
%R | 503398 | 6359 | 125188 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2WEEX5040 | Block works & Plastering | 8168 | 256 | 0 | 200 | 0 | 692 | 692 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-11 08:00 | 2014-01-09 17:00 |  | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-11-04 08:00 | 2013-12-02 17:00 | 2013-12-11 08:00 | 2014-01-09 17:00 |  | PT_Normal |  |  |  |  | WdC+squ/S6qeqxalggSOcQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38660 | N | N | 15 | WATER TANK ENCLOSURE |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 692 | BLOCK MASON SK
%R | 503399 | 6359 | 125188 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2WEEX5045 | Flooring & Painting | 8164 | 256 | 16 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-24 08:00 | 2014-01-21 17:00 |  | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 |  | PT_Normal |  |  |  |  | 1FW3NqlxTa2fcf9pf7+NWA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38660 | N | N | 15 | WATER TANK ENCLOSURE |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 336 | SCREED MASON SK
%R | 503400 | 6359 | 125188 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2WEEX5050 | Installation of Steel Gate | 8178 | 240 | 0 | 160 | 0 | 150 | 150 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-11 08:00 | 2014-02-02 17:00 |  | 2013-12-05 08:00 | 2013-12-29 17:00 | 2013-12-05 08:00 | 2013-12-29 17:00 | 2013-12-05 08:00 | 2013-12-29 17:00 | 2014-01-11 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | SmheBnUCRY2a1xxYIPlx3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38660 | N | N | 15 | WATER TANK ENCLOSURE |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 150 | LABOR- SUBCONTRACTOR
%R | 503401 | 6359 | 125188 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 240 | 160 | 200 | 0 | 534 | 534 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-02-15 17:00 |  | 2013-12-11 08:00 | 2014-01-09 17:00 | 2013-12-11 08:00 | 2014-01-09 17:00 | 2013-12-11 08:00 | 2014-01-09 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 |  | PT_Normal |  |  |  |  | Pg3RyUmCQe+45G1xP8I9mg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38660 | N | N | 15 | WATER TANK ENCLOSURE |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 534 | LABOR- SUBCONTRACTOR
%R | 503402 | 6359 | 125188 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 80 | 0 | 200 | 0 | 286.8 | 286.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-28 08:00 | 2014-02-26 17:00 |  | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 |  | PT_Normal |  |  |  |  | G7HRWTeQR6O7Q+cmrFJfFA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38660 | N | N | 15 | WATER TANK ENCLOSURE |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 286.8 | LABOR- SUBCONTRACTOR
%R | 503403 | 6359 | 125188 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2WEEX5070 | Installation ladder for water Tank | 8178 | 120 | 40 | 160 | 0 | 200 | 200 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-06 17:00 |  | 2014-01-25 08:00 | 2014-02-17 17:00 | 2014-01-25 08:00 | 2014-02-17 17:00 | 2014-01-25 08:00 | 2014-02-17 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | nl6bre5tTlCG96+EUWHEWg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38660 | N | N | 15 | WATER TANK ENCLOSURE |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 200 | LABOR- SUBCONTRACTOR
%R | 503404 | 6359 | 125189 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2SLEX5105 | Laying of Grass/ green area | 8178 | 168 | 0 | 160 | 0 | 2142 | 2142 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-02-23 17:00 |  | 2014-01-06 08:00 | 2014-01-28 17:00 | 2014-01-06 08:00 | 2014-01-28 17:00 | 2014-01-06 08:00 | 2014-01-28 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | W7/3YSXpSm+VZerTvVFmKA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38680 | N | N | 25 | SOFT LANDSCAPING |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 2142 | LABOR- SUBCONTRACTOR
%R | 503405 | 6359 | 125189 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2SLEX5110 | Laying of Palm tree | 8178 | 488 | 0 | 160 | 0 | 546 | 546 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-22 17:00 |  | 2014-01-18 08:00 | 2014-02-09 17:00 | 2014-01-18 08:00 | 2014-02-09 17:00 | 2014-01-18 08:00 | 2014-02-09 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | 4RWAWJraRzKhAJDibpqm4g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38680 | N | N | 25 | SOFT LANDSCAPING |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 546 | LABOR- SUBCONTRACTOR
%R | 503406 | 6359 | 125190 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 216 | 216 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | 20s58K8YQfmZcgF4q/8Cow |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:45 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38650 | N | N | 10 | MISCELLANEOUS |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 400 | LABOR- SUBCONTRACTOR
%R | 503407 | 6359 | 125190 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2MSEX5020 | Construction Entrance Ramp | 8164 | 240 | 0 | 160 | 0 | 436 | 436 | 160 | 0 | 0 | 0 |  |  |  | 2013-11-20 08:00 | 2013-12-12 17:00 |  | 2013-10-14 08:00 | 2013-11-07 17:00 | 2013-10-14 08:00 | 2013-11-07 17:00 | 2013-10-14 08:00 | 2013-11-07 17:00 | 2013-11-20 08:00 | 2013-12-12 17:00 |  | PT_Normal |  |  |  |  | UZ/cSrl4SwWkHfDaMypK7g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38650 | N | N | 10 | MISCELLANEOUS |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 436 | SCREED MASON SK
%R | 503408 | 6359 | 125190 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2MSEX5015 | Construction of grease Trap | 8178 | 336 | 0 | 160 | 0 | 168 | 168 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-15 17:00 |  | 2013-12-03 08:00 | 2013-12-26 17:00 | 2013-12-03 08:00 | 2013-12-26 17:00 | 2013-12-03 08:00 | 2013-12-26 17:00 | 2014-01-22 08:00 | 2014-02-15 17:00 |  | PT_Normal |  |  |  |  | NbNBD5RAT7OVsYpOqCbk5Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38650 | N | N | 10 | MISCELLANEOUS |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 168 | LABOR- SUBCONTRACTOR
%R | 503409 | 6359 | 125190 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2MSEX5000 | Construction of Manholes | 8172 | 336 | 0 | 200 | 0 | 132 | 132 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-19 08:00 | 2014-01-16 17:00 |  | 2013-10-30 08:00 | 2013-11-27 17:00 | 2013-10-30 08:00 | 2013-11-27 17:00 | 2013-10-30 08:00 | 2013-11-27 17:00 | 2013-12-19 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | 5CcB+bTOTvqtQxkuoA2+BQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38650 | N | N | 10 | MISCELLANEOUS |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 132 | MANHOLES SK
%R | 503410 | 6359 | 125190 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2MSEX5005 | Construction of Soak pit, Chambers | 8172 | 336 | 0 | 200 | 0 | 66 | 66 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-02 08:00 | 2014-01-30 17:00 |  | 2013-11-13 08:00 | 2013-12-11 17:00 | 2013-11-13 08:00 | 2013-12-11 17:00 | 2013-11-13 08:00 | 2013-12-11 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38650 | N | N | 10 | MISCELLANEOUS |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 66 | MANHOLES SK
%R | 503411 | 6359 | 125190 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2MSEX5055 | Installation Steel Door | 8178 | 240 | 0 | 160 | 0 | 180 | 180 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-02 08:00 | 2013-12-25 17:00 |  | 2013-10-28 08:00 | 2013-11-19 17:00 | 2013-10-28 08:00 | 2013-11-19 17:00 | 2013-10-28 08:00 | 2013-11-19 17:00 | 2013-12-02 08:00 | 2013-12-25 17:00 |  | PT_Normal |  |  |  |  | fDnrOL9RQm6hIvuz9BvsFA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38650 | N | N | 10 | MISCELLANEOUS |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 180 | LABOR- SUBCONTRACTOR
%R | 503412 | 6359 | 125190 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2MSEX5010 | Telephone cable laying | 8177 | 440 | 32 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-03 08:00 | 2014-03-31 17:00 |  | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | VwvbAqI+QiiEXgXNZ67XTg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38650 | N | N | 10 | MISCELLANEOUS |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 500 | LABOR - CIVIL
%R | 503413 | 6359 | 125190 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2MSEX5025 | SS.Handrails and Balustrades | 8178 | 240 | 0 | 160 | 0 | 136 | 136 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-14 08:00 | 2014-01-06 17:00 |  | 2013-11-09 08:00 | 2013-12-01 17:00 | 2013-11-09 08:00 | 2013-12-01 17:00 | 2013-11-09 08:00 | 2013-12-01 17:00 | 2013-12-14 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | I/GjYq+fRxqxB/6NxwXxdA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38650 | N | N | 10 | MISCELLANEOUS |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 136 | LABOR- SUBCONTRACTOR
%R | 503414 | 6359 | 125191 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2HDEX5090 | kerb works | 8173 | 240 | 0 | 160 | 0 | 236 | 236 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-23 08:00 | 2014-01-14 17:00 |  | 2013-11-17 08:00 | 2013-12-09 17:00 | 2013-11-17 08:00 | 2013-12-09 17:00 | 2013-11-17 08:00 | 2013-12-09 17:00 | 2013-12-23 08:00 | 2014-01-14 17:00 |  | PT_Normal |  |  |  |  | sMQAI/KnQRSxvh/6LHtH3g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38670 | N | N | 20 | HARD LANDSCAPING |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 236 | KERBSTONE MASON SK
%R | 503415 | 6359 | 125191 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2HDEX5095 | Cobble Stone Works | 8170 | 240 | 0 | 160 | 0 | 86 | 86 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-04 08:00 | 2014-01-26 17:00 |  | 2013-11-28 08:00 | 2013-12-22 17:00 | 2013-11-28 08:00 | 2013-12-22 17:00 | 2013-11-28 08:00 | 2013-12-22 17:00 | 2014-01-04 08:00 | 2014-01-26 17:00 |  | PT_Normal |  |  |  |  | jJMecWs9TrC4HyFwz9IE+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38670 | N | N | 20 | HARD LANDSCAPING |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 86 | TILE MASON SK
%R | 503416 | 6359 | 125191 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2HDEX5100 | Interlock works | 8174 | 240 | 72 | 160 | 0 | 300 | 300 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-19 08:00 | 2014-02-10 17:00 |  | 2013-12-14 08:00 | 2014-01-06 17:00 | 2013-12-14 08:00 | 2014-01-06 17:00 | 2013-12-14 08:00 | 2014-01-06 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | c4bwjvNRSYWYNnfdq/rmAQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38670 | N | N | 20 | HARD LANDSCAPING |  | 125187 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 300 | INTERLOCK MASON SK
%R | 503417 | 6359 | 125192 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 272 | 272 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | BJ0NicgmSyikxw4eVWUnUQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38690 | N | N | 30 | TESTING AND COMMISSIONING |  | 125164 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 503418 | 6359 | 125192 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 272 | 272 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | UqVMt6IuQae998T2h8zZ5w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38690 | N | N | 30 | TESTING AND COMMISSIONING |  | 125164 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 503419 | 6359 | 125192 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP2AZ2ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 272 | 272 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | HHnf8gcwTgqgP07aPVGNpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 38690 | N | N | 30 | TESTING AND COMMISSIONING |  | 125164 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 503420 | 6359 | 125196 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2TCGL5295 | Excavation Telecommunication trenches | 8177 | 136 | 0 | 160 | 0 | 362 | 362 | 160 | 200 | 0 | 200 |  |  |  | 2014-02-12 08:00 | 2014-03-06 17:00 |  | 2014-01-22 08:00 | 2014-02-15 17:00 | 2014-01-22 08:00 | 2014-02-15 17:00 | 2014-01-22 08:00 | 2014-02-15 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | 6R1P3TVLRUSTrwksWUjnQA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40500 | N | N | 45 | TELECOMMUNICATION LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 362 | LABOR - CIVIL
%R | 503421 | 6359 | 125196 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2TCGL5300 | Laying of cables | 8178 | 136 | 0 | 160 | 0 | 954.4 | 954.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-12 17:00 |  | 2014-01-28 08:00 | 2014-02-20 17:00 | 2014-01-28 08:00 | 2014-02-20 17:00 | 2014-01-28 08:00 | 2014-02-20 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 |  | PT_Normal |  |  |  |  | pvYBRB+SSoy4sUCohsY9sQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40500 | N | N | 45 | TELECOMMUNICATION LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 954.4 | LABOR- SUBCONTRACTOR
%R | 503422 | 6359 | 125196 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2TCGL5305 | Backfilling telecommunication trench | 8177 | 136 | 0 | 160 | 0 | 286 | 286 | 160 | 220 | 0 | 220 |  |  |  | 2014-02-24 08:00 | 2014-03-18 17:00 |  | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | hiAa1rtJSquWMG/CILB4Mg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40500 | N | N | 45 | TELECOMMUNICATION LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 286 | LABOR - CIVIL
%R | 503423 | 6359 | 125196 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2TCGL5310 | Connection & Installation | 8178 | 336 | 184 | 160 | 0 | 79.2 | 79.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-04-28 17:00 |  | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | u2dDELuZSWyiAt34KWrvZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40500 | N | N | 45 | TELECOMMUNICATION LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 79.2 | LABOR- SUBCONTRACTOR
%R | 503424 | 6359 | 125197 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2HDGL7020 | Precast Concrete Kerbs works | 8173 | 216 | 0 | 160 | 0 | 650 | 650 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-10 17:00 |  | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | lJ1CVWQARBeQYEjzeJehKw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40540 | N | N | 65 | HARD LANDSCAPING |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 650 | KERBSTONE MASON SK
%R | 503425 | 6359 | 125197 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2HDGL7025 | Interlocking for Walkways | 8174 | 216 | 0 | 200 | 0 | 762 | 762 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-28 17:00 |  | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | wLMqUg/ZTmahFcIkAAcidg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40540 | N | N | 65 | HARD LANDSCAPING |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 381 | INTERLOCK MASON SK
%R | 503426 | 6359 | 125197 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2HDGL7030 | Construction of Retaining wall | 8165 | 216 | 0 | 200 | 0 | 216 | 216 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-10 17:00 |  | 2014-03-11 08:00 | 2014-04-08 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | CwD0adMXQ5uttHSnTi3bPQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40540 | N | N | 65 | HARD LANDSCAPING |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 216 | STEEL FIXERS SK
%R | 503427 | 6359 | 125197 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2HDGL7035 | Construction of Wash Stone Boulders | 8170 | 216 | 0 | 200 | 0 | 396 | 396 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-10 17:00 |  | 2014-03-11 08:00 | 2014-04-08 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | 7lv2KikrRWKHkRW4t8jUWQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40540 | N | N | 65 | HARD LANDSCAPING |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 396 | TILE MASON SK
%R | 503428 | 6359 | 125197 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2HDGL7040 | Construction of Speed Humps | 8167 | 256 | 256 | 80 | 0 | 14 | 14 | 80 | 0 | 0 | 0 |  |  |  | 2014-06-03 08:00 | 2014-06-14 17:00 |  | 2014-04-27 08:00 | 2014-05-07 17:00 | 2014-04-27 08:00 | 2014-05-07 17:00 | 2014-04-27 08:00 | 2014-05-07 17:00 | 2014-06-03 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | ok+wt9xhS+io80HztOH82w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40540 | N | N | 65 | HARD LANDSCAPING |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 14 | CONCRETE MASON SK
%R | 503429 | 6359 | 125198 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2PSGL7000 | Excavation | 8177 | 176 | 40 | 120 | 0 | 49 | 49 | 120 | 31 | 0 | 31 |  |  |  | 2014-04-23 08:00 | 2014-05-10 17:00 |  | 2014-03-29 08:00 | 2014-04-14 17:00 | 2014-03-29 08:00 | 2014-04-14 17:00 | 2014-03-29 08:00 | 2014-04-14 17:00 | 2014-04-23 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | di7W3kWKTIWdF0o3TBeCfQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40530 | N | N | 60 | PARKING SHED |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 49 | LABOR - CIVIL
%R | 503430 | 6359 | 125198 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2PSGL7005 | Foundation casting | 8165 | 136 | 0 | 120 | 0 | 1912 | 1912 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-15 17:00 |  | 2014-04-09 08:00 | 2014-04-26 17:00 | 2014-04-09 08:00 | 2014-04-26 17:00 | 2014-04-09 08:00 | 2014-04-26 17:00 | 2014-04-29 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | pzMVP3PuSNSgTtM1xizDrA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40530 | N | N | 60 | PARKING SHED |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1912 | STEEL FIXERS SK
%R | 503431 | 6359 | 125198 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2PSGL7010 | Column, Frame& Fabrics Erection | 8178 | 136 | 0 | 200 | 0 | 286 | 286 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-06-08 17:00 |  | 2014-04-21 08:00 | 2014-05-19 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | nTjt5OkvTOO/e9c+rCP/iw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40530 | N | N | 60 | PARKING SHED |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 286 | LABOR- SUBCONTRACTOR
%R | 503432 | 6359 | 125198 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2PSGL7015 | Electrical Works-Parking Shed | 8178 | 136 | 136 | 200 | 0 | 51.6 | 51.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-04-27 08:00 | 2014-05-25 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | 3xpOzwFITzuEjuhkYatuiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40530 | N | N | 60 | PARKING SHED |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 51.6 | LABOR- SUBCONTRACTOR
%R | 503433 | 6359 | 125199 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2SLGL7210 | Plantation works | 8178 | 216 | 216 | 200 | 0 | 574 | 574 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-14 17:00 |  | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-05-17 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | pl41cuJITDm8NXvTJ9lpdw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40550 | N | N | 70 | SOFT LANDSCAPING |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 574 | LABOR- SUBCONTRACTOR
%R | 503434 | 6359 | 125199 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2SLGL7200 | Excavation for Landscaping | 8177 | 216 | 0 | 200 | 0 | 2844 | 2844 | 200 | 1500 | 0 | 1500 |  |  |  | 2014-04-23 08:00 | 2014-05-21 17:00 |  | 2014-03-23 08:00 | 2014-04-20 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | iVRBPtIFQ5ujz93TQzrfdg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40550 | N | N | 70 | SOFT LANDSCAPING |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 2844 | LABOR - CIVIL
%R | 503435 | 6359 | 125199 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2SLGL7205 | Sweet Soil Laying | 8178 | 216 | 0 | 200 | 0 | 630 | 630 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-05 08:00 | 2014-06-02 17:00 |  | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-05-05 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | 10WpZKSDR3m7BQwzlQyz6w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40550 | N | N | 70 | SOFT LANDSCAPING |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 630 | LABOR- SUBCONTRACTOR
%R | 503436 | 6359 | 125200 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2RWGL6000 | Excavation & Earth Filling | 8177 | 136 | 0 | 80 | 0 | 1190 | 1190 | 80 | 500 | 0 | 500 |  |  |  | 2014-03-08 08:00 | 2014-03-18 17:00 |  | 2014-02-16 08:00 | 2014-02-26 17:00 | 2014-02-16 08:00 | 2014-02-26 17:00 | 2014-02-16 08:00 | 2014-02-26 17:00 | 2014-03-08 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | Fx53YhCcR4uO9qIiXQ02QQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40520 | N | N | 55 | ROAD WORKS |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1190 | LABOR - CIVIL
%R | 503437 | 6359 | 125200 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2RWGL6005 | Laying of Sub Grade | 8178 | 136 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-02-27 08:00 | 2014-03-27 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | hvGepzrdTxykEgbkDyT8sg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40520 | N | N | 55 | ROAD WORKS |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 12 | LABOR- SUBCONTRACTOR
%R | 503438 | 6359 | 125200 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2RWGL6010 | Laying of Precast Kerbs | 8178 | 136 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-28 17:00 |  | 2014-03-11 08:00 | 2014-04-08 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | PVG3XhPTRrOdYL5aW4QKwg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40520 | N | N | 55 | ROAD WORKS |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 24 | LABOR- SUBCONTRACTOR
%R | 503439 | 6359 | 125200 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2RWGL6015 | Laying of Granular Sub Base Coarse | 8173 | 136 | 0 | 160 | 0 | 1536 | 1536 | 160 | 600 | 0 | 600 |  |  |  | 2014-04-12 08:00 | 2014-05-04 17:00 |  | 2014-03-23 08:00 | 2014-04-14 17:00 | 2014-03-23 08:00 | 2014-04-14 17:00 | 2014-03-23 08:00 | 2014-04-14 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | R0LcoV3mQsq0pYvmF89LSA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40520 | N | N | 55 | ROAD WORKS |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1536 | KERBSTONE MASON SK
%R | 503440 | 6359 | 125200 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2RWGL6020 | Laying of Road Base Asphalt Concrete | 8178 | 136 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-05-05 08:00 | 2014-05-10 17:00 |  | 2014-04-15 08:00 | 2014-04-20 17:00 | 2014-04-15 08:00 | 2014-04-20 17:00 | 2014-04-15 08:00 | 2014-04-20 17:00 | 2014-05-05 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | giPLDeM8TrGpdzdZobqV3w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40520 | N | N | 55 | ROAD WORKS |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 174 | LABOR- SUBCONTRACTOR
%R | 503441 | 6359 | 125200 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2RWGL6025 | Laying of Asphalt Wearing Coarse | 8178 | 256 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-05-28 08:00 | 2014-06-02 17:00 |  | 2014-04-21 08:00 | 2014-04-26 17:00 | 2014-04-21 08:00 | 2014-04-26 17:00 | 2014-04-21 08:00 | 2014-04-26 17:00 | 2014-05-28 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | 30K/vdhzQ/+OT8uu9whKDw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40520 | N | N | 55 | ROAD WORKS |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 174 | LABOR- SUBCONTRACTOR
%R | 503442 | 6359 | 125200 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2RWGL6030 | Traffic Signage & Road Marking | 8178 | 256 | 120 | 40 | 0 | 680 | 680 | 40 | 0 | 0 | 0 |  |  |  | 2014-06-03 08:00 | 2014-06-08 17:00 |  | 2014-04-27 08:00 | 2014-05-01 17:00 | 2014-04-27 08:00 | 2014-05-01 17:00 | 2014-04-27 08:00 | 2014-05-01 17:00 | 2014-06-03 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | gS/2q0F6QpevpkJ5tAyclw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40520 | N | N | 55 | ROAD WORKS |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 680 | LABOR- SUBCONTRACTOR
%R | 503443 | 6359 | 125201 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2WSGL5155 | Excavation for water line | 8177 | 152 | 0 | 200 | 0 | 455 | 455 | 200 | 251 | 0 | 251 |  |  |  | 2013-11-27 08:00 | 2013-12-26 17:00 |  | 2013-11-05 08:00 | 2013-12-03 17:00 | 2013-11-05 08:00 | 2013-12-03 17:00 | 2013-11-05 08:00 | 2013-12-03 17:00 | 2013-11-27 08:00 | 2013-12-26 17:00 |  | PT_Normal |  |  |  |  | s7mixdjiSOSoPqlQTYW27Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40450 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 455 | LABOR - CIVIL
%R | 503444 | 6359 | 125201 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2WSGL5160 | Laying of water line | 8178 | 152 | 0 | 200 | 0 | 386.4 | 386.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-03 08:00 | 2014-01-01 17:00 |  | 2013-11-11 08:00 | 2013-12-09 17:00 | 2013-11-11 08:00 | 2013-12-09 17:00 | 2013-11-11 08:00 | 2013-12-09 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 |  | PT_Normal |  |  |  |  | rO/LiZKqS7CormiCZlHIrw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40450 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 386.4 | LABOR- SUBCONTRACTOR
%R | 503445 | 6359 | 125201 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2WSGL5165 | Testing of potable water line | 8178 | 152 | 0 | 200 | 0 | 117.6 | 117.6 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-09 08:00 | 2014-01-07 17:00 |  | 2013-11-17 08:00 | 2013-12-15 17:00 | 2013-11-17 08:00 | 2013-12-15 17:00 | 2013-11-17 08:00 | 2013-12-15 17:00 | 2013-12-09 08:00 | 2014-01-07 17:00 |  | PT_Normal |  |  |  |  | f+DOe3vBRtyFTOBZSGF3LA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40450 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 117.6 | LABOR- SUBCONTRACTOR
%R | 503446 | 6359 | 125201 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2WSGL5170 | Backfilling potable water line | 8177 | 152 | 0 | 200 | 0 | 359 | 359 | 200 | 275 | 0 | 275 |  |  |  | 2013-12-15 08:00 | 2014-01-13 17:00 |  | 2013-11-23 08:00 | 2013-12-22 17:00 | 2013-11-23 08:00 | 2013-12-22 17:00 | 2013-11-23 08:00 | 2013-12-22 17:00 | 2013-12-15 08:00 | 2014-01-13 17:00 |  | PT_Normal |  |  |  |  | dOIhdwR8SB2Q03MrgUcOlA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40450 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 359 | LABOR - CIVIL
%R | 503447 | 6359 | 125201 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2WSGL5175 | Construction of valve chambers & Thrust Blocks | 8172 | 304 | 0 | 200 | 0 | 80 | 80 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-02-10 17:00 |  | 2013-11-28 08:00 | 2013-12-28 17:00 | 2013-11-28 08:00 | 2013-12-28 17:00 | 2013-11-28 08:00 | 2013-12-28 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | jr2PhZC7SDWIS4slh1khWQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40450 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11; period 2: 2013-AP12 |  | 40 | MANHOLES SK
%R | 503448 | 6359 | 125201 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2WSGL5180 | Installation of meter ,Accessories & Connection | 8178 | 304 | 72 | 160 | 0 | 33.6 | 33.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-06 17:00 |  | 2013-12-29 08:00 | 2014-01-20 17:00 | 2013-12-29 08:00 | 2014-01-20 17:00 | 2013-12-29 08:00 | 2014-01-20 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | HOXX8eIBQzelLdaaWPSu0w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40450 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 33.6 | LABOR- SUBCONTRACTOR
%R | 503449 | 6359 | 125202 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2SAGL5135 | Construction of manholes Drainage | 8172 | 584 | 200 | 200 | 0 | 44 | 44 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-13 08:00 | 2014-02-10 17:00 |  | 2013-10-16 08:00 | 2013-11-16 17:00 | 2013-10-16 08:00 | 2013-11-16 17:00 | 2013-10-16 08:00 | 2013-11-16 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | kQtYBGfDRs+r95cLViRrpQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40440 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 22 | MANHOLES SK
%R | 503450 | 6359 | 125202 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2SAGL5140 | Construction of soakaways | 8172 | 192 | 0 | 200 | 0 | 190 | 190 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-16 08:00 | 2013-12-14 17:00 |  | 2013-10-16 08:00 | 2013-11-16 17:00 | 2013-10-16 08:00 | 2013-11-16 17:00 | 2013-10-16 08:00 | 2013-11-16 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 |  | PT_Normal |  |  |  |  | FiR4PZFpRtykP08uwHixWg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40440 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 95 | MANHOLES SK
%R | 503451 | 6359 | 125202 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2SAGL5145 | Construction of Road gullies | 8172 | 192 | 0 | 200 | 0 | 190 | 190 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-15 08:00 | 2014-01-13 17:00 |  | 2013-11-17 08:00 | 2013-12-15 17:00 | 2013-11-17 08:00 | 2013-12-15 17:00 | 2013-11-17 08:00 | 2013-12-15 17:00 | 2013-12-15 08:00 | 2014-01-13 17:00 |  | PT_Normal |  |  |  |  | Gl9gFOV/QsWognIlLcf86A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40440 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 190 | MANHOLES SK
%R | 503452 | 6359 | 125202 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2SAGL5150 | Connection with existing sewer manhole | 8172 | 384 | 248 | 160 | 0 | 44 | 44 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-06 17:00 |  | 2013-12-16 08:00 | 2014-01-08 17:00 | 2013-12-16 08:00 | 2014-01-08 17:00 | 2013-12-16 08:00 | 2014-01-08 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | vmgG6Z/wS/+GdhtuEoutHg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40440 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 44 | MANHOLES SK
%R | 503453 | 6359 | 125203 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2IRGL5265 | Excavation for irrigation line | 8177 | 224 | 0 | 200 | 0 | 178 | 178 | 200 | 100 | 0 | 100 |  |  |  | 2014-03-17 08:00 | 2014-04-14 17:00 |  | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 |  | PT_Normal |  |  |  |  | 2wCeYZCdQFSCj/Aa79tCfg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40490 | N | N | 40 | IRRIGATION LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 89 | LABOR - CIVIL
%R | 503454 | 6359 | 125203 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2IRGL5270 | Laying of irrigationline | 8178 | 224 | 0 | 200 | 0 | 100.8 | 100.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-23 08:00 | 2014-04-20 17:00 |  | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | kF4HrU4lT6CcBCamJTijUw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40490 | N | N | 40 | IRRIGATION LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 503455 | 6359 | 125203 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2IRGL5275 | Testing of irrigation line | 8178 | 224 | 0 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-29 08:00 | 2014-04-26 17:00 |  | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-03-29 08:00 | 2014-04-26 17:00 |  | PT_Normal |  |  |  |  | vdPQUA5qQte33q7iNLW7wQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40490 | N | N | 40 | IRRIGATION LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 42 | LABOR- SUBCONTRACTOR
%R | 503456 | 6359 | 125203 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2IRGL5280 | Backfilling irrigation line | 8177 | 224 | 0 | 200 | 0 | 140 | 140 | 200 | 110 | 0 | 110 |  |  |  | 2014-04-03 08:00 | 2014-05-01 17:00 |  | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | Ws9KrqYXQ5+69DGxLxGkHQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40490 | N | N | 40 | IRRIGATION LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 140 | LABOR - CIVIL
%R | 503457 | 6359 | 125203 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2IRGL5285 | Construction of Thrust Blocks,Pull boxes | 8178 | 224 | 0 | 200 | 0 | 313.6 | 313.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-13 17:00 |  | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 |  | PT_Normal |  |  |  |  | Ey1OZw1SQ5+noL7aSv1ARw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40490 | N | N | 40 | IRRIGATION LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 313.6 | LABOR- SUBCONTRACTOR
%R | 503458 | 6359 | 125203 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2IRGL5290 | Irrigation Fittings (Nozzle,Values) | 8178 | 224 | 8 | 200 | 0 | 100.8 | 100.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-05-21 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-04-23 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | AuRhEXH6SLaspbo2b4VqzA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40490 | N | N | 40 | IRRIGATION LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 100.8 | LABOR- SUBCONTRACTOR
%R | 503459 | 6359 | 125204 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2DRGL5115 | Excavation for Drainage line | 8177 | 192 | 0 | 200 | 0 | 233 | 233 | 200 | 125 | 0 | 125 |  |  |  | 2013-10-12 08:00 | 2013-11-11 17:00 |  | 2013-09-14 08:00 | 2013-10-12 17:00 | 2013-09-14 08:00 | 2013-10-12 17:00 | 2013-09-14 08:00 | 2013-10-12 17:00 | 2013-10-12 08:00 | 2013-11-11 17:00 |  | PT_Normal |  |  |  |  | e50gGnGBREijoRNbpQrTbA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40430 | N | N | 10 | DRAINAGE LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 233 | LABOR - CIVIL
%R | 503460 | 6359 | 125204 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2DRGL5120 | Laying of Drainage line | 8178 | 192 | 0 | 200 | 0 | 127.2 | 127.2 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-21 08:00 | 2013-11-18 17:00 |  | 2013-09-21 08:00 | 2013-10-21 17:00 | 2013-09-21 08:00 | 2013-10-21 17:00 | 2013-09-21 08:00 | 2013-10-21 17:00 | 2013-10-21 08:00 | 2013-11-18 17:00 |  | PT_Normal |  |  |  |  | jR/KUVNdRfqifRQwyZ8otw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40430 | N | N | 10 | DRAINAGE LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 63.6 | LABOR- SUBCONTRACTOR
%R | 503461 | 6359 | 125204 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2DRGL5125 | Testing of Drainage line | 8178 | 192 | 0 | 200 | 0 | 67.2 | 67.2 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-29 08:00 | 2013-11-26 17:00 |  | 2013-09-29 08:00 | 2013-10-29 17:00 | 2013-09-29 08:00 | 2013-10-29 17:00 | 2013-09-29 08:00 | 2013-10-29 17:00 | 2013-10-29 08:00 | 2013-11-26 17:00 |  | PT_Normal |  |  |  |  | w8wb1PVrTxiMbRh6596BKQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40430 | N | N | 10 | DRAINAGE LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 33.6 | LABOR- SUBCONTRACTOR
%R | 503462 | 6359 | 125204 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2DRGL5130 | Backfilling Drainage line | 8177 | 192 | 0 | 120 | 0 | 207 | 207 | 120 | 165 | 0 | 165 |  |  |  | 2013-11-16 08:00 | 2013-12-02 17:00 |  | 2013-10-16 08:00 | 2013-11-04 17:00 | 2013-10-16 08:00 | 2013-11-04 17:00 | 2013-10-16 08:00 | 2013-11-04 17:00 | 2013-11-16 08:00 | 2013-12-02 17:00 |  | PT_Normal |  |  |  |  | /Hauef2HTVWDNEiUXeP6FA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40430 | N | N | 10 | DRAINAGE LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 207 | LABOR - CIVIL
%R | 503463 | 6359 | 125205 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2FFGL5185 | Excavation for firefighting line | 8177 | 136 | 0 | 200 | 0 | 172 | 172 | 200 | 100 | 0 | 100 |  |  |  | 2013-12-22 08:00 | 2014-01-19 17:00 |  | 2013-12-01 08:00 | 2013-12-30 17:00 | 2013-12-01 08:00 | 2013-12-30 17:00 | 2013-12-01 08:00 | 2013-12-30 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 |  | PT_Normal |  |  |  |  | 1RDk6G3/TVC/EhQEPoDHTQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40460 | N | N | 25 | FIREFIGHTING LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 172 | LABOR - CIVIL
%R | 503464 | 6359 | 125205 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2FFGL5190 | Laying of firefighting line | 8178 | 136 | 0 | 200 | 0 | 165.6 | 165.6 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-30 08:00 | 2014-01-27 17:00 |  | 2013-12-09 08:00 | 2014-01-07 17:00 | 2013-12-09 08:00 | 2014-01-07 17:00 | 2013-12-09 08:00 | 2014-01-07 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 |  | PT_Normal |  |  |  |  | x1REMcnOSjq7YwtOhGdX0A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40460 | N | N | 25 | FIREFIGHTING LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 165.6 | LABOR- SUBCONTRACTOR
%R | 503465 | 6359 | 125205 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2FFGL5195 | Testing of firefighting line | 8178 | 136 | 0 | 200 | 0 | 82.8 | 82.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-05 08:00 | 2014-02-02 17:00 |  | 2013-12-15 08:00 | 2014-01-13 17:00 | 2013-12-15 08:00 | 2014-01-13 17:00 | 2013-12-15 08:00 | 2014-01-13 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | ccPZdKHuRtG0tXXn5LqooQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40460 | N | N | 25 | FIREFIGHTING LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 82.8 | LABOR- SUBCONTRACTOR
%R | 503466 | 6359 | 125205 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2FFGL5200 | Backfilling firefighting line | 8177 | 136 | 0 | 200 | 0 | 140 | 140 | 200 | 110 | 0 | 110 |  |  |  | 2014-01-11 08:00 | 2014-02-08 17:00 |  | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 |  | PT_Normal |  |  |  |  | Mj9VTIwTQiueWlgksCx7NQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40460 | N | N | 25 | FIREFIGHTING LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 140 | LABOR - CIVIL
%R | 503467 | 6359 | 125205 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2FFGL5205 | Construction of valve chambers & Thrust Blocks | 8165 | 232 | 0 | 200 | 0 | 174 | 174 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-03-01 17:00 |  | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | ErGFnNzcSb+NvoydQcXMKQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40460 | N | N | 25 | FIREFIGHTING LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 174 | STEEL FIXERS SK
%R | 503468 | 6359 | 125205 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2FFGL5210 | Connection with existing Firewater System | 8165 | 232 | 96 | 200 | 0 | 174 | 174 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-03-06 17:00 |  | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 | 2014-02-05 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | Gx2cGH37Q6WG5T8cPl0K+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40460 | N | N | 25 | FIREFIGHTING LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 174 | STEEL FIXERS SK
%R | 503469 | 6359 | 125206 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2ELGL5215 | Excavation Cable Trenches & Duct Banks | 8177 | 136 | 0 | 200 | 0 | 1593 | 1593 | 200 | 651 | 0 | 651 |  |  |  | 2014-01-19 08:00 | 2014-02-17 17:00 |  | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 |  | PT_Normal |  |  |  |  | Hl6V4Q76Q7GpUwZgNiWvYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40470 | N | N | 30 | ELECTRICAL LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1593 | LABOR - CIVIL
%R | 503470 | 6359 | 125206 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2ELGL5220 | Laying of electrical cables | 8178 | 160 | 0 | 200 | 0 | 2232.4 | 2232.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-28 08:00 | 2014-02-26 17:00 |  | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 |  | PT_Normal |  |  |  |  | Q0O8k1zKQuGadc5wlHok0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40470 | N | N | 30 | ELECTRICAL LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 2232.4 | LABOR- SUBCONTRACTOR
%R | 503471 | 6359 | 125206 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2ELGL5225 | Backfilling Electrical trench | 8177 | 160 | 0 | 200 | 0 | 1203 | 1203 | 200 | 825 | 0 | 825 |  |  |  | 2014-02-05 08:00 | 2014-03-06 17:00 |  | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-02-05 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | fumtTeC1TweeGkOnVGfW4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40470 | N | N | 30 | ELECTRICAL LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1203 | LABOR - CIVIL
%R | 503472 | 6359 | 125206 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2ELGL5230 | Construction of Submain Board & Feeder Pillar | 8165 | 360 | 0 | 200 | 0 | 520 | 520 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | hQs/eDlZSOanE7ESwgiQnA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40470 | N | N | 30 | ELECTRICAL LINES |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 520 | STEEL FIXERS SK
%R | 503473 | 6359 | 125207 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2STGL5235 | Excavation for Street lighting | 8177 | 136 | 0 | 200 | 0 | 247 | 247 | 200 | 151 | 0 | 151 |  |  |  | 2014-01-19 08:00 | 2014-02-17 17:00 |  | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 |  | PT_Normal |  |  |  |  | aRQr2RV3TV6giU+uxZrzog |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40480 | N | N | 35 | STREET LIGHTING |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 247 | LABOR - CIVIL
%R | 503474 | 6359 | 125207 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2STGL5240 | Construction of Duct Banks | 8178 | 136 | 0 | 200 | 0 | 454.4 | 454.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-25 08:00 | 2014-02-23 17:00 |  | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | 2j26iq6MS2i852F6nKGurw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40480 | N | N | 35 | STREET LIGHTING |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 454.4 | LABOR- SUBCONTRACTOR
%R | 503475 | 6359 | 125207 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2STGL5245 | Construction of Foundation | 8172 | 136 | 0 | 200 | 0 | 674 | 674 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-25 08:00 | 2014-02-23 17:00 |  | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-25 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | 9fbpJVDETi25TsiKTiXYQA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40480 | N | N | 35 | STREET LIGHTING |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 674 | MANHOLES SK
%R | 503476 | 6359 | 125207 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2STGL5250 | Backfilling Street Lighting | 8177 | 136 | 0 | 200 | 0 | 152 | 152 | 200 | 110 | 0 | 110 |  |  |  | 2014-01-30 08:00 | 2014-03-01 17:00 |  | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40480 | N | N | 35 | STREET LIGHTING |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 152 | LABOR - CIVIL
%R | 503477 | 6359 | 125207 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2STGL5255 | Installation of light Post | 8178 | 520 | 160 | 200 | 0 | 227.2 | 227.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-09 08:00 | 2014-05-07 17:00 |  | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 |  | PT_Normal |  |  |  |  | uOKC91QQQ6Sj5Wv9KpiUqA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40480 | N | N | 35 | STREET LIGHTING |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 227.2 | LABOR- SUBCONTRACTOR
%R | 503478 | 6359 | 125207 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2STGL5260 | Electrical Works | 8178 | 360 | 224 | 200 | 0 | 170.4 | 170.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | C1NbQUQEQ0q9LbOXA5epkw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40480 | N | N | 35 | STREET LIGHTING |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 85.2 | LABOR- SUBCONTRACTOR
%R | 503479 | 6359 | 125208 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2BWGL5315 | Construction of Boundary Wall (Ht-3m) | 8165 | 208 | 0 | 200 | 0 | 182 | 182 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-23 08:00 | 2014-03-23 17:00 |  | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-02-23 08:00 | 2014-03-23 17:00 |  | PT_Normal |  |  |  |  | x4evw4SGRsqNdDc9b6Nn2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40510 | N | N | 50 | BOUNDARY WALL |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 182 | STEEL FIXERS SK
%R | 503480 | 6359 | 125208 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 8178 | 208 | 0 | 200 | 0 | 14 | 14 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-04-08 17:00 |  | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | eRyqE0/rQeWLzAz+DU5/LA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40510 | N | N | 50 | BOUNDARY WALL |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 7 | LABOR- SUBCONTRACTOR
%R | 503481 | 6359 | 125208 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 8165 | 208 | 0 | 200 | 0 | 112 | 112 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-09 08:00 | 2014-05-07 17:00 |  | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-03-10 08:00 | 2014-04-07 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 |  | PT_Normal |  |  |  |  | p71lBTOvSrGMtVk/NLAx1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40510 | N | N | 50 | BOUNDARY WALL |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 112 | STEEL FIXERS SK
%R | 503482 | 6359 | 125208 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ2BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 8165 | 344 | 208 | 200 | 0 | 42 | 42 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-06-08 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-05-11 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | ZpOst41MRXWXQUeFhbpFAQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40510 | N | N | 50 | BOUNDARY WALL |  | 125195 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 42 | STEEL FIXERS SK
%R | 503483 | 6359 | 125211 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BSBIWGL7400 | Excavation | 8177 | 152 | 0 | 120 | 0 | 444 | 444 | 120 | 300 | 0 | 300 |  |  |  | 2013-12-25 08:00 | 2014-01-11 17:00 |  | 2013-12-02 08:00 | 2013-12-19 17:00 | 2013-12-02 08:00 | 2013-12-19 17:00 | 2013-12-02 08:00 | 2013-12-19 17:00 | 2013-12-25 08:00 | 2014-01-11 17:00 |  | PT_Normal |  |  |  |  | fu7CppynRZSuUk6ha1oFEA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40580 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125210 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 444 | LABOR - CIVIL
%R | 503484 | 6359 | 125211 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BSBIWGL7405 | Blinding & base waterproofing | 8163 | 152 | 0 | 80 | 0 | 200 | 200 | 80 | 0 | 0 | 0 |  |  |  | 2014-01-12 08:00 | 2014-01-22 17:00 |  | 2013-12-21 08:00 | 2013-12-31 17:00 | 2013-12-21 08:00 | 2013-12-31 17:00 | 2013-12-21 08:00 | 2013-12-31 17:00 | 2014-01-12 08:00 | 2014-01-22 17:00 |  | PT_Normal |  |  |  |  | J+pYEjeiTF+Whdr193CtjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40580 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125210 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 200 | BLINDING MASON SK
%R | 503485 | 6359 | 125211 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BSBIWGL7410 | Construction of Raft slab | 8165 | 152 | 0 | 80 | 0 | 630 | 630 | 80 | 0 | 0 | 0 |  |  |  | 2014-01-23 08:00 | 2014-02-03 17:00 |  | 2014-01-01 08:00 | 2014-01-12 17:00 | 2014-01-01 08:00 | 2014-01-12 17:00 | 2014-01-01 08:00 | 2014-01-12 17:00 | 2014-01-23 08:00 | 2014-02-03 17:00 |  | PT_Normal |  |  |  |  | KpdBoDhMT1qAYDwbixfLWA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40580 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125210 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 630 | STEEL FIXERS SK
%R | 503486 | 6359 | 125211 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BSBIWGL7415 | Construction of RCC Wall | 8165 | 152 | 0 | 200 | 0 | 1708 | 1708 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-04 08:00 | 2014-03-05 17:00 |  | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-02-04 08:00 | 2014-03-05 17:00 |  | PT_Normal |  |  |  |  | GqqkENYDQ/SxyXrxAJIUIw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40580 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125210 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1708 | STEEL FIXERS SK
%R | 503487 | 6359 | 125211 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BSBIWGL7420 | Construction of Roof Slab | 8165 | 152 | 0 | 160 | 0 | 490 | 490 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-06 08:00 | 2014-03-29 17:00 |  | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 |  | PT_Normal |  |  |  |  | oDn5Gfa2SJyHl8g7CGUHtg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40580 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125210 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 490 | STEEL FIXERS SK
%R | 503488 | 6359 | 125211 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BSBIWGL7430 | Floor screed | 8164 | 152 | 0 | 40 | 0 | 66 | 66 | 40 | 0 | 0 | 0 |  |  |  | 2014-04-23 08:00 | 2014-04-28 17:00 |  | 2014-04-01 08:00 | 2014-04-06 17:00 | 2014-04-01 08:00 | 2014-04-06 17:00 | 2014-04-01 08:00 | 2014-04-06 17:00 | 2014-04-23 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | N2aOWnBcSMuJDaEPwTIsvQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40580 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125210 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 66 | SCREED MASON SK
%R | 503489 | 6359 | 125211 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BSBIWGL7455 | Internal epoxy coating & Painting | 8178 | 152 | 0 | 40 | 0 | 44 | 44 | 40 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-02 17:00 |  | 2014-05-06 08:00 | 2014-05-11 17:00 | 2014-05-06 08:00 | 2014-05-11 17:00 | 2014-05-06 08:00 | 2014-05-11 17:00 | 2014-05-28 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | jo/SoOIeQ6eUbxQUstHMfw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40580 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125210 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 44 | LABOR- SUBCONTRACTOR
%R | 503490 | 6359 | 125211 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BSBIWGL7460 | Installation of Steel Ladder | 8178 | 152 | 0 | 40 | 0 | 14 | 14 | 40 | 0 | 0 | 0 |  |  |  | 2014-06-03 08:00 | 2014-06-08 17:00 |  | 2014-05-12 08:00 | 2014-05-17 17:00 | 2014-05-12 08:00 | 2014-05-17 17:00 | 2014-05-12 08:00 | 2014-05-17 17:00 | 2014-06-03 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | t4UNRRDvTLWBdRaVC9UkwQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40580 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125210 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 14 | LABOR- SUBCONTRACTOR
%R | 503491 | 6359 | 125211 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BSBIWGL7465 | Installation of G.I Handrails | 8178 | 152 | 152 | 40 | 0 | 164 | 164 | 40 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-06-14 17:00 |  | 2014-05-18 08:00 | 2014-05-22 17:00 | 2014-05-18 08:00 | 2014-05-22 17:00 | 2014-05-18 08:00 | 2014-05-22 17:00 | 2014-06-09 08:00 | 2014-06-14 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40580 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125210 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 164 | LABOR- SUBCONTRACTOR
%R | 503492 | 6359 | 125211 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BSBIWGL7440 | Plumbing , Drainage & Firefighting works | 8178 | 152 | 0 | 200 | 0 | 50.4 | 50.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-27 17:00 |  | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | EVZ8lWGOTOuR2sNqPiqpKg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40580 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125210 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 503493 | 6359 | 125211 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BSBIWGL7445 | AC Works | 8178 | 152 | 0 | 200 | 0 | 159.2 | 159.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-27 17:00 |  | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | AP15KAqrR+aBr+VytIpXZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40580 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125210 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 159.2 | LABOR- SUBCONTRACTOR
%R | 503494 | 6359 | 125211 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BSBIWGL7450 | Electrical Works | 8178 | 152 | 0 | 200 | 0 | 325.2 | 325.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-27 17:00 |  | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-07 08:00 | 2014-05-05 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | SO5/KTFDTMKyICyCajLtcg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40580 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125210 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 325.2 | LABOR- SUBCONTRACTOR
%R | 503495 | 6359 | 125211 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BSBIWGL7950 | Laying of Interlock | 8174 | 320 | 0 | 80 | 0 | 58 | 58 | 80 | 0 | 0 | 0 |  |  |  | 2014-05-11 08:00 | 2014-05-21 17:00 |  | 2014-03-25 08:00 | 2014-04-05 17:00 | 2014-03-25 08:00 | 2014-04-05 17:00 | 2014-03-25 08:00 | 2014-04-05 17:00 | 2014-05-11 08:00 | 2014-05-21 17:00 |  | PT_Normal |  |  |  |  | Hf3ih8gNQb+EE3VbNNHbWA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40580 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125210 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 58 | INTERLOCK MASON SK
%R | 503496 | 6359 | 125211 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BSBIWGL7435 | Installation of Boundary Fences | 8165 | 320 | 168 | 120 | 0 | 42 | 42 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-22 08:00 | 2014-06-08 17:00 |  | 2014-04-06 08:00 | 2014-04-22 17:00 | 2014-04-06 08:00 | 2014-04-22 17:00 | 2014-04-06 08:00 | 2014-04-22 17:00 | 2014-05-22 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | tmYYXF32T0OGvaEWW6tADQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40580 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125210 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 42 | STEEL FIXERS SK
%R | 503497 | 6359 | 125211 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BSBIWGL7425 | Waterproofing & Backfilling | 8177 | 200 | 0 | 120 | 0 | 207 | 207 | 120 | 99 | 0 | 99 |  |  |  | 2014-04-06 08:00 | 2014-04-22 17:00 |  | 2014-03-08 08:00 | 2014-03-24 17:00 | 2014-03-08 08:00 | 2014-03-24 17:00 | 2014-03-08 08:00 | 2014-03-24 17:00 | 2014-04-06 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | BgjlLOjpRnCpI/Pchfd8rg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40580 | N | N | 10 | IRRIGATION WATER TANK & PUMP ROOM |  | 125210 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 207 | LABOR - CIVIL
%R | 503498 | 6359 | 125212 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BSBGZGL7900 | Construction of Concrete structure | 8165 | 272 | 0 | 160 | 0 | 124 | 124 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-24 17:00 |  | 2014-01-20 08:00 | 2014-02-12 17:00 | 2014-01-20 08:00 | 2014-02-12 17:00 | 2014-01-20 08:00 | 2014-02-12 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | iu292lvBTrefUtv3DVmipQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40610 | N | N | 25 | GAZEBO |  | 125210 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 124 | STEEL FIXERS SK
%R | 503499 | 6359 | 125212 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BSBGZGL7905 | Installation of Wooden Works | 8178 | 272 | 0 | 200 | 0 | 300 | 300 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-04-10 17:00 |  | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | 1asmIBN+QVaZXx6TfIaAVA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40610 | N | N | 25 | GAZEBO |  | 125210 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 150 | LABOR- SUBCONTRACTOR
%R | 503500 | 6359 | 125212 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BSBGZGL7910 | Electrical Works-Gazebo | 8178 | 272 | 56 | 120 | 0 | 125.6 | 125.6 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-04-28 17:00 |  | 2014-03-03 08:00 | 2014-03-19 17:00 | 2014-03-03 08:00 | 2014-03-19 17:00 | 2014-03-03 08:00 | 2014-03-19 17:00 | 2014-04-12 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | YakOwZKkQeuBz3pjnp1vag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40610 | N | N | 25 | GAZEBO |  | 125210 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 125.6 | LABOR- SUBCONTRACTOR
%R | 503501 | 6359 | 125212 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BSBGZGL7915 | Park Benches Installation | 8178 | 352 | 80 | 120 | 0 | 120 | 120 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-25 08:00 | 2014-04-10 17:00 |  | 2014-02-01 08:00 | 2014-02-18 17:00 | 2014-02-01 08:00 | 2014-02-18 17:00 | 2014-02-01 08:00 | 2014-02-18 17:00 | 2014-03-25 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | 6NRncb39TbeWvBFJ3LHViQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40610 | N | N | 25 | GAZEBO |  | 125210 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 120 | LABOR- SUBCONTRACTOR
%R | 503502 | 6359 | 125215 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1BWGL5315 | Construction of Boundary Wall (Ht-3m) | 8165 | 344 | 0 | 200 | 0 | 182 | 182 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-23 08:00 | 2014-02-22 17:00 |  | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2014-01-23 08:00 | 2014-02-22 17:00 |  | PT_Normal |  |  |  |  | 7B0pD6ZPTQ+Ewm29Y9NNXw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40360 | N | N | 50 | BOUNDARY WALL |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 182 | STEEL FIXERS SK
%R | 503503 | 6359 | 125215 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 8178 | 344 | 0 | 200 | 0 | 14 | 14 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-03-10 17:00 |  | 2013-12-21 08:00 | 2014-01-18 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | nnmOjyHsRQOSXjgnvM5n9g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40360 | N | N | 50 | BOUNDARY WALL |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 14 | LABOR- SUBCONTRACTOR
%R | 503504 | 6359 | 125215 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 8165 | 344 | 0 | 200 | 0 | 112 | 112 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-04-08 17:00 |  | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-01-19 08:00 | 2014-02-17 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | s5m1WefXSJWdce9Hb3MXxw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40360 | N | N | 50 | BOUNDARY WALL |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 112 | STEEL FIXERS SK
%R | 503505 | 6359 | 125215 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 8165 | 480 | 136 | 200 | 0 | 42 | 42 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-10 17:00 |  | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | FwJ2wNhFTa6Zs2p3OBfZKQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40360 | N | N | 50 | BOUNDARY WALL |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01; period 2: 2014-AP03 |  | 21 | STEEL FIXERS SK
%R | 503506 | 6359 | 125216 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1IRGL5265 | Excavation for irrigation line | 8177 | 240 | 0 | 200 | 0 | 178 | 178 | 200 | 100 | 0 | 100 |  |  |  | 2014-01-28 08:00 | 2014-02-26 17:00 |  | 2013-12-24 08:00 | 2014-01-21 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 |  | PT_Normal |  |  |  |  | B9KtI8NGS6+PRv9jgfHeQQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40340 | N | N | 40 | IRRIGATION LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 178 | LABOR - CIVIL
%R | 503507 | 6359 | 125216 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1IRGL5270 | Laying of irrigationline | 8178 | 240 | 0 | 200 | 0 | 100.8 | 100.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-03 08:00 | 2014-03-04 17:00 |  | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 |  | PT_Normal |  |  |  |  | CuO73shWQ8iPw2+2Lbpwqg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40340 | N | N | 40 | IRRIGATION LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 100.8 | LABOR- SUBCONTRACTOR
%R | 503508 | 6359 | 125216 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1IRGL5275 | Testing of irrigation line | 8178 | 240 | 0 | 200 | 0 | 84 | 84 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-03-10 17:00 |  | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-02-09 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | vFc05PWmQPy8hhb/MTPeJg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40340 | N | N | 40 | IRRIGATION LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 84 | LABOR- SUBCONTRACTOR
%R | 503509 | 6359 | 125216 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1IRGL5280 | Backfilling irrigation line | 8177 | 240 | 0 | 200 | 0 | 140 | 140 | 200 | 110 | 0 | 110 |  |  |  | 2014-02-16 08:00 | 2014-03-16 17:00 |  | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | GpcnMMD8TM6VBMK3QMqEIA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40340 | N | N | 40 | IRRIGATION LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 140 | LABOR - CIVIL
%R | 503510 | 6359 | 125216 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1IRGL5285 | Construction of Thrust Blocks,Pull boxes | 8178 | 280 | 0 | 200 | 0 | 313.6 | 313.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-05 08:00 | 2014-04-02 17:00 |  | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 |  | PT_Normal |  |  |  |  | 0FhrOz8gSTGbpv/j6Wpr6w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40340 | N | N | 40 | IRRIGATION LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 313.6 | LABOR- SUBCONTRACTOR
%R | 503511 | 6359 | 125216 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1IRGL5290 | Irrigation Fittings (Nozzle,Values) | 8178 | 280 | 8 | 200 | 0 | 100.8 | 100.8 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-04-10 17:00 |  | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | a2y8H8r3QbOPJH7NDsLHeg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40340 | N | N | 40 | IRRIGATION LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01; period 2: 2014-AP03 |  | 50.4 | LABOR- SUBCONTRACTOR
%R | 503512 | 6359 | 125217 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1ELGL5215 | Excavation Cable Trenches & Duct Banks | 8177 | 152 | 0 | 200 | 0 | 1593 | 1593 | 200 | 651 | 0 | 651 |  |  |  | 2013-12-02 08:00 | 2013-12-31 17:00 |  | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 |  | PT_Normal |  |  |  |  | SqodzsVxRrWws0Wl3AXmzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40320 | N | N | 30 | ELECTRICAL LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1593 | LABOR - CIVIL
%R | 503513 | 6359 | 125217 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1ELGL5220 | Laying of electrical cables | 8178 | 176 | 0 | 200 | 0 | 2232.4 | 2232.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-11 08:00 | 2014-01-09 17:00 |  | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-12-11 08:00 | 2014-01-09 17:00 |  | PT_Normal |  |  |  |  | bkZZ1fthTvSNeQhlw35ByA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40320 | N | N | 30 | ELECTRICAL LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 2232.4 | LABOR- SUBCONTRACTOR
%R | 503514 | 6359 | 125217 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1ELGL5225 | Backfilling Electrical trench | 8177 | 176 | 0 | 200 | 0 | 1203 | 1203 | 200 | 825 | 0 | 825 |  |  |  | 2013-12-21 08:00 | 2014-01-18 17:00 |  | 2013-11-24 08:00 | 2013-12-23 17:00 | 2013-11-24 08:00 | 2013-12-23 17:00 | 2013-11-24 08:00 | 2013-12-23 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | +8VmMN4qTAavckk74m1qbw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40320 | N | N | 30 | ELECTRICAL LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1203 | LABOR - CIVIL
%R | 503515 | 6359 | 125217 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1ELGL5230 | Construction of Submain Board & Feeder Pillar | 8165 | 496 | 0 | 200 | 0 | 520 | 520 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-18 17:00 |  | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | vZ6yMKMoRe6jutDJHgSHEQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40320 | N | N | 30 | ELECTRICAL LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 520 | STEEL FIXERS SK
%R | 503516 | 6359 | 125218 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1SLGL7200 | Excavation | 8177 | 272 | 0 | 200 | 0 | 2844 | 2844 | 200 | 1500 | 0 | 1500 |  |  |  | 2014-03-13 08:00 | 2014-04-10 17:00 |  | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-03-13 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | U1fMl+YOS8GQKA5v6KAjNw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40400 | N | N | 70 | SOFT LANDSCAPING |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 1422 | LABOR - CIVIL
%R | 503517 | 6359 | 125218 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1SLGL7205 | Sweet Soil Laying | 8178 | 272 | 0 | 200 | 0 | 630 | 630 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-25 08:00 | 2014-04-22 17:00 |  | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | IEKCowa9TWe/l4UIog6gSQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40400 | N | N | 70 | SOFT LANDSCAPING |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 315 | LABOR- SUBCONTRACTOR
%R | 503518 | 6359 | 125218 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1SLGL7210 | Plantation works | 8178 | 352 | 136 | 200 | 0 | 574 | 574 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | /aOdIL9wSUGhPV6moA5iPA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40400 | N | N | 70 | SOFT LANDSCAPING |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 287 | LABOR- SUBCONTRACTOR
%R | 503519 | 6359 | 125219 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1PSGL7000 | Excavation | 8177 | 312 | 40 | 120 | 0 | 49 | 49 | 120 | 31 | 0 | 31 |  |  |  | 2014-03-25 08:00 | 2014-04-10 17:00 |  | 2014-02-06 08:00 | 2014-02-24 17:00 | 2014-02-06 08:00 | 2014-02-24 17:00 | 2014-02-06 08:00 | 2014-02-24 17:00 | 2014-03-25 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | saYYD/WtSpW5abO+eM5sAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40380 | N | N | 60 | PARKING SHED |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 49 | LABOR - CIVIL
%R | 503520 | 6359 | 125219 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1PSGL7005 | Foundation casting | 8165 | 272 | 0 | 120 | 0 | 1912 | 1912 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-16 17:00 |  | 2014-02-19 08:00 | 2014-03-08 17:00 | 2014-02-19 08:00 | 2014-03-08 17:00 | 2014-02-19 08:00 | 2014-03-08 17:00 | 2014-03-31 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | e60U/qc+R8y760zQauNdQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40380 | N | N | 60 | PARKING SHED |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1912 | STEEL FIXERS SK
%R | 503521 | 6359 | 125219 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1PSGL7010 | Column, Frame& Fabrics Erection | 8178 | 272 | 0 | 200 | 0 | 286 | 286 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-10 17:00 |  | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | U5WikzNRSFeLOOPV3YRE4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40380 | N | N | 60 | PARKING SHED |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 286 | LABOR- SUBCONTRACTOR
%R | 503522 | 6359 | 125219 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1PSGL7015 | Electrical Works-Parking Shed | 8178 | 272 | 136 | 200 | 0 | 51.6 | 51.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-15 17:00 |  | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 | 2014-04-17 08:00 | 2014-05-15 17:00 |  | PT_Normal |  |  |  |  | V1VUaVFbRc6SPNccRi63iw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40380 | N | N | 60 | PARKING SHED |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 51.6 | LABOR- SUBCONTRACTOR
%R | 503523 | 6359 | 125220 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1WSGL5180 | Installation of meter ,Accessories & Connection | 8178 | 304 | 56 | 160 | 0 | 33.6 | 33.6 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-26 08:00 | 2014-01-18 17:00 |  | 2013-11-11 08:00 | 2013-12-03 17:00 | 2013-11-11 08:00 | 2013-12-03 17:00 | 2013-11-11 08:00 | 2013-12-03 17:00 | 2013-12-26 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | wIMKkPLiRNOE0wDeLqYdEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40300 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 33.6 | LABOR- SUBCONTRACTOR
%R | 503524 | 6359 | 125220 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1WSGL5155 | Excavation for water line | 8177 | 136 | 0 | 200 | 0 | 455 | 455 | 200 | 251 | 0 | 251 |  |  |  | 2013-10-07 08:00 | 2013-11-06 17:00 |  | 2013-09-17 08:00 | 2013-10-15 17:00 | 2013-09-17 08:00 | 2013-10-15 17:00 | 2013-09-17 08:00 | 2013-10-15 17:00 | 2013-10-07 08:00 | 2013-11-06 17:00 |  | PT_Normal |  |  |  |  | Zwiu4MggS/qP5WHNUVENsw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40300 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 455 | LABOR - CIVIL
%R | 503525 | 6359 | 125220 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1WSGL5160 | Laying of water line | 8178 | 136 | 0 | 200 | 0 | 386.4 | 386.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-13 08:00 | 2013-11-12 17:00 |  | 2013-09-23 08:00 | 2013-10-23 17:00 | 2013-09-23 08:00 | 2013-10-23 17:00 | 2013-09-23 08:00 | 2013-10-23 17:00 | 2013-10-13 08:00 | 2013-11-12 17:00 |  | PT_Normal |  |  |  |  | 3NHDdSeYSbWpF29WcxvHAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40300 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 193.2 | LABOR- SUBCONTRACTOR
%R | 503526 | 6359 | 125220 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1WSGL5165 | Testing of potable water line | 8178 | 136 | 0 | 200 | 0 | 117.6 | 117.6 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-21 08:00 | 2013-11-18 17:00 |  | 2013-09-29 08:00 | 2013-10-29 17:00 | 2013-09-29 08:00 | 2013-10-29 17:00 | 2013-09-29 08:00 | 2013-10-29 17:00 | 2013-10-21 08:00 | 2013-11-18 17:00 |  | PT_Normal |  |  |  |  | NzsjmCVLSt+H5259mpjadw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40300 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 58.8 | LABOR- SUBCONTRACTOR
%R | 503527 | 6359 | 125220 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1WSGL5170 | Backfilling potable water line | 8177 | 136 | 0 | 200 | 0 | 359 | 359 | 200 | 275 | 0 | 275 |  |  |  | 2013-10-27 08:00 | 2013-11-24 17:00 |  | 2013-10-05 08:00 | 2013-11-04 17:00 | 2013-10-05 08:00 | 2013-11-04 17:00 | 2013-10-05 08:00 | 2013-11-04 17:00 | 2013-10-27 08:00 | 2013-11-24 17:00 |  | PT_Normal |  |  |  |  | 050IGi4wQayA8rAn6tW4hg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40300 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 359 | LABOR - CIVIL
%R | 503528 | 6359 | 125220 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1WSGL5175 | Construction of valve chambers & Thrust Blocks | 8172 | 304 | 0 | 200 | 0 | 80 | 80 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-26 08:00 | 2013-12-25 17:00 |  | 2013-10-10 08:00 | 2013-11-10 17:00 | 2013-10-10 08:00 | 2013-11-10 17:00 | 2013-10-10 08:00 | 2013-11-10 17:00 | 2013-11-26 08:00 | 2013-12-25 17:00 |  | PT_Normal |  |  |  |  | 3ktly1/+SBmzKc6OaE1SpA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40300 | N | N | 20 | WATER SUPPLY SYSTEM |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 40 | MANHOLES SK
%R | 503529 | 6359 | 125221 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1RWGL6000 | Excavation & Earth Filling | 8177 | 152 | 0 | 80 | 0 | 1190 | 1190 | 80 | 500 | 0 | 500 |  |  |  | 2014-01-19 08:00 | 2014-01-29 17:00 |  | 2013-12-28 08:00 | 2014-01-07 17:00 | 2013-12-28 08:00 | 2014-01-07 17:00 | 2013-12-28 08:00 | 2014-01-07 17:00 | 2014-01-19 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | VB5d3qMsTpu285Kyu3HX8w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40370 | N | N | 55 | ROAD WORKS |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1190 | LABOR - CIVIL
%R | 503530 | 6359 | 125221 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1RWGL6005 | Laying of Sub Grade | 8178 | 152 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-30 08:00 | 2014-03-01 17:00 |  | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | M9JzWRgpRdW7OAkEPy3NNA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40370 | N | N | 55 | ROAD WORKS |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 24 | LABOR- SUBCONTRACTOR
%R | 503531 | 6359 | 125221 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1RWGL6010 | Laying of Precast Kerbs | 8178 | 152 | 0 | 200 | 0 | 24 | 24 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-12 08:00 | 2014-03-12 17:00 |  | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 |  | PT_Normal |  |  |  |  | eCh7x5IBQlmNi251MMKtSA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40370 | N | N | 55 | ROAD WORKS |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 24 | LABOR- SUBCONTRACTOR
%R | 503532 | 6359 | 125221 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1RWGL6015 | Laying of Granular Sub Base Coarse | 8173 | 152 | 0 | 160 | 0 | 1536 | 1536 | 160 | 600 | 0 | 600 |  |  |  | 2014-02-24 08:00 | 2014-03-18 17:00 |  | 2014-02-01 08:00 | 2014-02-24 17:00 | 2014-02-01 08:00 | 2014-02-24 17:00 | 2014-02-01 08:00 | 2014-02-24 17:00 | 2014-02-24 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | CI2Bf/57RH6iCi/9Cztqzg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40370 | N | N | 55 | ROAD WORKS |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1536 | KERBSTONE MASON SK
%R | 503533 | 6359 | 125221 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1RWGL6020 | Laying of Road Base Asphalt Concrete | 8178 | 272 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-04-06 08:00 | 2014-04-10 17:00 |  | 2014-02-25 08:00 | 2014-03-02 17:00 | 2014-02-25 08:00 | 2014-03-02 17:00 | 2014-02-25 08:00 | 2014-03-02 17:00 | 2014-04-06 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | WR/xKy39R/u9IeiVeZfJ2Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40370 | N | N | 55 | ROAD WORKS |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 174 | LABOR- SUBCONTRACTOR
%R | 503534 | 6359 | 125221 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1RWGL6025 | Laying of Asphalt Wearing Coarse | 8178 | 392 | 0 | 40 | 0 | 174 | 174 | 40 | 150 | 0 | 150 |  |  |  | 2014-04-29 08:00 | 2014-05-04 17:00 |  | 2014-03-03 08:00 | 2014-03-08 17:00 | 2014-03-03 08:00 | 2014-03-08 17:00 | 2014-03-03 08:00 | 2014-03-08 17:00 | 2014-04-29 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | was9fgBxRpuQyshG7u+/6w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40370 | N | N | 55 | ROAD WORKS |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 174 | LABOR- SUBCONTRACTOR
%R | 503535 | 6359 | 125221 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1RWGL6030 | Traffic Signage & Road Marking | 8178 | 392 | 120 | 40 | 0 | 680 | 680 | 40 | 0 | 0 | 0 |  |  |  | 2014-05-05 08:00 | 2014-05-10 17:00 |  | 2014-03-09 08:00 | 2014-03-13 17:00 | 2014-03-09 08:00 | 2014-03-13 17:00 | 2014-03-09 08:00 | 2014-03-13 17:00 | 2014-05-05 08:00 | 2014-05-10 17:00 |  | PT_Normal |  |  |  |  | RpMrWOj9SsGngXC8xiTItg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40370 | N | N | 55 | ROAD WORKS |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 680 | LABOR- SUBCONTRACTOR
%R | 503536 | 6359 | 125222 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1TCGL5295 | Excavation Telecommunication trenches | 8177 | 152 | 0 | 160 | 0 | 362 | 362 | 160 | 200 | 0 | 200 |  |  |  | 2013-12-26 08:00 | 2014-01-18 17:00 |  | 2013-12-03 08:00 | 2013-12-26 17:00 | 2013-12-03 08:00 | 2013-12-26 17:00 | 2013-12-03 08:00 | 2013-12-26 17:00 | 2013-12-26 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | rStTxg1nRSeSy7DlgQ0gYQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40350 | N | N | 45 | TELECOMMUNICATION LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 362 | LABOR - CIVIL
%R | 503537 | 6359 | 125222 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1TCGL5300 | Laying of cables | 8178 | 152 | 0 | 160 | 0 | 954.4 | 954.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-01 08:00 | 2014-01-23 17:00 |  | 2013-12-09 08:00 | 2014-01-01 17:00 | 2013-12-09 08:00 | 2014-01-01 17:00 | 2013-12-09 08:00 | 2014-01-01 17:00 | 2014-01-01 08:00 | 2014-01-23 17:00 |  | PT_Normal |  |  |  |  | /Iy2gO9qQqik526qeGNAMA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40350 | N | N | 45 | TELECOMMUNICATION LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 954.4 | LABOR- SUBCONTRACTOR
%R | 503538 | 6359 | 125222 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1TCGL5305 | Backfilling telecommunication trench | 8177 | 152 | 0 | 160 | 0 | 286 | 286 | 160 | 220 | 0 | 220 |  |  |  | 2014-01-07 08:00 | 2014-01-29 17:00 |  | 2013-12-15 08:00 | 2014-01-07 17:00 | 2013-12-15 08:00 | 2014-01-07 17:00 | 2013-12-15 08:00 | 2014-01-07 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | juKDGhf0T0eRXgDMjkgujA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40350 | N | N | 45 | TELECOMMUNICATION LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 286 | LABOR - CIVIL
%R | 503539 | 6359 | 125222 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1TCGL5310 | Connection & Installation | 8178 | 480 | 144 | 160 | 0 | 79.2 | 79.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-04-05 17:00 |  | 2014-01-01 08:00 | 2014-01-23 17:00 | 2014-01-01 08:00 | 2014-01-23 17:00 | 2014-01-01 08:00 | 2014-01-23 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 |  | PT_Normal |  |  |  |  | OWXys9RPQuywdglGskm02A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40350 | N | N | 45 | TELECOMMUNICATION LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 79.2 | LABOR- SUBCONTRACTOR
%R | 503540 | 6359 | 125223 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1DRGL5115 | Excavation for Drainage line | 8177 | 136 | 0 | 200 | 0 | 233 | 233 | 200 | 125 | 0 | 125 |  |  |  | 2013-08-24 08:00 | 2013-09-21 17:00 |  | 2013-07-31 08:00 | 2013-09-01 17:00 | 2013-07-31 08:00 | 2013-09-01 17:00 | 2013-07-31 08:00 | 2013-09-01 17:00 | 2013-08-24 08:00 | 2013-09-21 17:00 |  | PT_Normal |  |  |  |  | 9pUFaDESRyS7ksQUs/8CNg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40280 | N | N | 10 | DRAINAGE LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 116.5 | LABOR - CIVIL
%R | 503541 | 6359 | 125223 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1DRGL5125 | Testing of Drainage line | 8178 | 136 | 0 | 200 | 0 | 67.2 | 67.2 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-08 08:00 | 2013-10-06 17:00 |  | 2013-08-19 08:00 | 2013-09-16 17:00 | 2013-08-19 08:00 | 2013-09-16 17:00 | 2013-08-19 08:00 | 2013-09-16 17:00 | 2013-09-08 08:00 | 2013-10-06 17:00 |  | PT_Normal |  |  |  |  | pA0dO3mlSNulW52rrn0YtQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40280 | N | N | 10 | DRAINAGE LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 503542 | 6359 | 125223 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1DRGL5130 | Backfilling Drainage line | 8177 | 136 | 0 | 120 | 0 | 207 | 207 | 120 | 165 | 0 | 165 |  |  |  | 2013-09-25 08:00 | 2013-10-12 17:00 |  | 2013-09-05 08:00 | 2013-09-22 17:00 | 2013-09-05 08:00 | 2013-09-22 17:00 | 2013-09-05 08:00 | 2013-09-22 17:00 | 2013-09-25 08:00 | 2013-10-12 17:00 |  | PT_Normal |  |  |  |  | 8rJd7Hh4TPyiIVtHDIXvjg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40280 | N | N | 10 | DRAINAGE LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 207 | LABOR - CIVIL
%R | 503543 | 6359 | 125223 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1DRGL5120 | Laying of Drainage line | 8178 | 136 | 0 | 200 | 0 | 127.2 | 127.2 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-31 08:00 | 2013-09-28 17:00 |  | 2013-08-07 08:00 | 2013-09-08 17:00 | 2013-08-07 08:00 | 2013-09-08 17:00 | 2013-08-07 08:00 | 2013-09-08 17:00 | 2013-08-31 08:00 | 2013-09-28 17:00 |  | PT_Normal |  |  |  |  | 7hVefdf5QeGRYvdv0v6H4g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40280 | N | N | 10 | DRAINAGE LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 63.6 | LABOR- SUBCONTRACTOR
%R | 503544 | 6359 | 125224 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1STGL5235 | Excavation for Street lighting | 8177 | 152 | 0 | 200 | 0 | 247 | 247 | 200 | 151 | 0 | 151 |  |  |  | 2013-12-02 08:00 | 2013-12-31 17:00 |  | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 |  | PT_Normal |  |  |  |  | XBXVF0aGR5ejbKF5x2XyVg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40330 | N | N | 35 | STREET LIGHTING |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 247 | LABOR - CIVIL
%R | 503545 | 6359 | 125224 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1STGL5240 | Construction of Duct Banks | 8178 | 152 | 0 | 200 | 0 | 454.4 | 454.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-08 08:00 | 2014-01-06 17:00 |  | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-12-08 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | Uoq/zUlEQMC4sQ5QRjiopA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40330 | N | N | 35 | STREET LIGHTING |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 454.4 | LABOR- SUBCONTRACTOR
%R | 503546 | 6359 | 125224 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1STGL5245 | Construction of Foundation | 8172 | 152 | 0 | 200 | 0 | 674 | 674 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-08 08:00 | 2014-01-06 17:00 |  | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-12-08 08:00 | 2014-01-06 17:00 |  | PT_Normal |  |  |  |  | TVDTmatkRsyTJ2m44EFd0Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40330 | N | N | 35 | STREET LIGHTING |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 674 | MANHOLES SK
%R | 503547 | 6359 | 125224 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1STGL5250 | Backfilling Street Lighting | 8177 | 152 | 0 | 200 | 0 | 152 | 152 | 200 | 110 | 0 | 110 |  |  |  | 2013-12-14 08:00 | 2014-01-12 17:00 |  | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 |  | PT_Normal |  |  |  |  | mr5/9F5RRDeO3XVAyDwDng |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40330 | N | N | 35 | STREET LIGHTING |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11; period 2: 2013-AP12 |  | 76 | LABOR - CIVIL
%R | 503548 | 6359 | 125224 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1STGL5255 | Installation of light Post | 8178 | 656 | 136 | 200 | 0 | 227.2 | 227.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-04-08 17:00 |  | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2013-12-03 08:00 | 2014-01-01 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | sM5WD/QqSfabVPOAke3Xhw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40330 | N | N | 35 | STREET LIGHTING |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 227.2 | LABOR- SUBCONTRACTOR
%R | 503549 | 6359 | 125224 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1STGL5260 | Electrical Works | 8178 | 496 | 136 | 200 | 0 | 170.4 | 170.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-16 17:00 |  | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-03-19 08:00 | 2014-04-16 17:00 |  | PT_Normal |  |  |  |  | RX97uvoiSparTC4bqTEvIQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40330 | N | N | 35 | STREET LIGHTING |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 170.4 | LABOR- SUBCONTRACTOR
%R | 503550 | 6359 | 125225 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1FFGL5185 | Excavation for firefighting line | 8177 | 136 | 0 | 200 | 0 | 172 | 172 | 200 | 100 | 0 | 100 |  |  |  | 2013-11-02 08:00 | 2013-11-30 17:00 |  | 2013-10-10 08:00 | 2013-11-10 17:00 | 2013-10-10 08:00 | 2013-11-10 17:00 | 2013-10-10 08:00 | 2013-11-10 17:00 | 2013-11-02 08:00 | 2013-11-30 17:00 |  | PT_Normal |  |  |  |  | wWg99JSjT22VSeblgARcuw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40310 | N | N | 25 | FIREFIGHTING LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 86 | LABOR - CIVIL
%R | 503551 | 6359 | 125225 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1FFGL5190 | Laying of firefighting line | 8178 | 136 | 0 | 200 | 0 | 165.6 | 165.6 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-10 08:00 | 2013-12-08 17:00 |  | 2013-10-21 08:00 | 2013-11-18 17:00 | 2013-10-21 08:00 | 2013-11-18 17:00 | 2013-10-21 08:00 | 2013-11-18 17:00 | 2013-11-10 08:00 | 2013-12-08 17:00 |  | PT_Normal |  |  |  |  | axeqYxuBSQ+BwbIcgcSxyQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40310 | N | N | 25 | FIREFIGHTING LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 165.6 | LABOR- SUBCONTRACTOR
%R | 503552 | 6359 | 125225 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1FFGL5195 | Testing of firefighting line | 8178 | 136 | 0 | 200 | 0 | 82.8 | 82.8 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-16 08:00 | 2013-12-14 17:00 |  | 2013-10-27 08:00 | 2013-11-24 17:00 | 2013-10-27 08:00 | 2013-11-24 17:00 | 2013-10-27 08:00 | 2013-11-24 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 |  | PT_Normal |  |  |  |  | zuHd9d/2Q6ivmfXC/Si6mQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40310 | N | N | 25 | FIREFIGHTING LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 82.8 | LABOR- SUBCONTRACTOR
%R | 503553 | 6359 | 125225 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1FFGL5200 | Backfilling firefighting line | 8177 | 136 | 0 | 200 | 0 | 140 | 140 | 200 | 110 | 0 | 110 |  |  |  | 2013-11-21 08:00 | 2013-12-21 17:00 |  | 2013-11-02 08:00 | 2013-11-30 17:00 | 2013-11-02 08:00 | 2013-11-30 17:00 | 2013-11-02 08:00 | 2013-11-30 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 |  | PT_Normal |  |  |  |  | PqMG6K4cTvaHeDFs2FjY5w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40310 | N | N | 25 | FIREFIGHTING LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 140 | LABOR - CIVIL
%R | 503554 | 6359 | 125225 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1FFGL5205 | Construction of valve chambers & Thrust Blocks | 8165 | 248 | 0 | 200 | 0 | 174 | 174 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-14 08:00 | 2014-01-12 17:00 |  | 2013-11-07 08:00 | 2013-12-05 17:00 | 2013-11-07 08:00 | 2013-12-05 17:00 | 2013-11-07 08:00 | 2013-12-05 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 |  | PT_Normal |  |  |  |  | ASzlXPcJRD+8alwkqi+gzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40310 | N | N | 25 | FIREFIGHTING LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 174 | STEEL FIXERS SK
%R | 503555 | 6359 | 125225 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1FFGL5210 | Connection with existing Firewater System | 8165 | 248 | 96 | 200 | 0 | 174 | 174 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-21 08:00 | 2014-01-18 17:00 |  | 2013-11-13 08:00 | 2013-12-11 17:00 | 2013-11-13 08:00 | 2013-12-11 17:00 | 2013-11-13 08:00 | 2013-12-11 17:00 | 2013-12-21 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | grFLW/rtTm261R1+cCQiVg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40310 | N | N | 25 | FIREFIGHTING LINES |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 174 | STEEL FIXERS SK
%R | 503556 | 6359 | 125226 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1SAGL5135 | Construction of manholes Drainage | 8172 | 544 | 80 | 200 | 0 | 44 | 44 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-26 08:00 | 2013-12-25 17:00 |  | 2013-09-05 08:00 | 2013-10-03 17:00 | 2013-09-05 08:00 | 2013-10-03 17:00 | 2013-09-05 08:00 | 2013-10-03 17:00 | 2013-11-26 08:00 | 2013-12-25 17:00 |  | PT_Normal |  |  |  |  | CS31OlImQLqfUujUjBQO7Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40290 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 44 | MANHOLES SK
%R | 503557 | 6359 | 125226 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1SAGL5140 | Construction of soakaways | 8172 | 136 | 0 | 200 | 0 | 190 | 190 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-25 08:00 | 2013-10-26 17:00 |  | 2013-09-05 08:00 | 2013-10-03 17:00 | 2013-09-05 08:00 | 2013-10-03 17:00 | 2013-09-05 08:00 | 2013-10-03 17:00 | 2013-09-25 08:00 | 2013-10-26 17:00 |  | PT_Normal |  |  |  |  | jmSqvxonTT6eWIMt2gz9XQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40290 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 190 | MANHOLES SK
%R | 503558 | 6359 | 125226 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1SAGL5145 | Construction of Road gullies | 8172 | 136 | 0 | 200 | 0 | 190 | 190 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-27 08:00 | 2013-11-24 17:00 |  | 2013-10-05 08:00 | 2013-11-04 17:00 | 2013-10-05 08:00 | 2013-11-04 17:00 | 2013-10-05 08:00 | 2013-11-04 17:00 | 2013-10-27 08:00 | 2013-11-24 17:00 |  | PT_Normal |  |  |  |  | 3P0NQiYXSB6Ev137oBddJg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40290 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 190 | MANHOLES SK
%R | 503559 | 6359 | 125226 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1SAGL5150 | Connection with existing sewer manhole | 8172 | 344 | 192 | 160 | 0 | 44 | 44 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-26 08:00 | 2014-01-18 17:00 |  | 2013-11-05 08:00 | 2013-11-27 17:00 | 2013-11-05 08:00 | 2013-11-27 17:00 | 2013-11-05 08:00 | 2013-11-27 17:00 | 2013-12-26 08:00 | 2014-01-18 17:00 |  | PT_Normal |  |  |  |  | g/+LTrRWSDGGzsfFkI8cLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40290 | N | N | 15 | MANHOLES & SOAKAWAY |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 44 | MANHOLES SK
%R | 503560 | 6359 | 125227 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1HDGL7020 | Precast Concrete Kerbs works | 8173 | 272 | 0 | 160 | 0 | 650 | 650 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-03-01 17:00 |  | 2013-12-28 08:00 | 2014-01-19 17:00 | 2013-12-28 08:00 | 2014-01-19 17:00 | 2013-12-28 08:00 | 2014-01-19 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | u7TYoL60R9uWyFOQ3UVy4g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40390 | N | N | 65 | HARD LANDSCAPING |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 650 | KERBSTONE MASON SK
%R | 503561 | 6359 | 125227 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1HDGL7025 | Interlocking for Walkways | 8174 | 272 | 0 | 200 | 0 | 762 | 762 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-18 17:00 |  | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-02-18 08:00 | 2014-03-18 17:00 |  | PT_Normal |  |  |  |  | E77eIe4/ScicM8DsQS5sKg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40390 | N | N | 65 | HARD LANDSCAPING |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 762 | INTERLOCK MASON SK
%R | 503562 | 6359 | 125227 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1HDGL7030 | Construction of Retaining wall | 8165 | 272 | 0 | 200 | 0 | 216 | 216 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-30 17:00 |  | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | AD2lcptZQVqEJ+i/S/KJyQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40390 | N | N | 65 | HARD LANDSCAPING |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 216 | STEEL FIXERS SK
%R | 503563 | 6359 | 125227 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1HDGL7035 | Construction of Wash Stone Boulders | 8170 | 272 | 0 | 200 | 0 | 396 | 396 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-30 17:00 |  | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | NT0I0uWZR1uJfyYGfi4qBw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40390 | N | N | 65 | HARD LANDSCAPING |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 396 | TILE MASON SK
%R | 503564 | 6359 | 125227 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONI2BZ1HDGL7040 | Construction of Speed Humps | 8167 | 512 | 256 | 80 | 0 | 14 | 14 | 80 | 0 | 0 | 0 |  |  |  | 2014-05-22 08:00 | 2014-06-02 17:00 |  | 2014-03-09 08:00 | 2014-03-19 17:00 | 2014-03-09 08:00 | 2014-03-19 17:00 | 2014-03-09 08:00 | 2014-03-19 17:00 | 2014-05-22 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | Mw2IibyBRuesW5Y1YB0+Xg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 40390 | N | N | 65 | HARD LANDSCAPING |  | 125214 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 14 | CONCRETE MASON SK
%R | 503565 | 6359 | 125229 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AGNSP001000 | Survey works, | 8175 | 0 | 0 | 160 | 0 | 87.5 | 87.5 | 160 | 0 | 0 | 0 |  |  |  | 2012-12-01 08:00 | 2012-12-24 17:00 |  | 2012-12-01 08:00 | 2012-12-24 17:00 | 2012-12-01 08:00 | 2012-12-24 17:00 | 2012-12-01 08:00 | 2012-12-24 17:00 | 2012-12-01 08:00 | 2012-12-24 17:00 |  | PT_Normal |  |  |  |  | 3TLtxQ92SeODIHP2snQwkQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43520 |  |  |  |  | SURVEYOR SK | J315 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29700 | N | N | 03 | SITE PREPARATORY WORKS |  | 125228 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 87.5 | SURVEYOR SK
%R | 503566 | 6359 | 125229 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AGNSP002000 | Scanning for Existing Services for rerouting | 8180 | 0 | 0 | 128 | 0 | 325 | 325 | 128 | 0 | 0 | 0 |  |  |  | 2012-11-10 08:00 | 2012-11-27 17:00 |  | 2012-11-10 08:00 | 2012-11-27 17:00 | 2012-11-10 08:00 | 2012-11-27 17:00 | 2012-11-10 08:00 | 2012-11-27 17:00 | 2012-11-10 08:00 | 2012-11-27 17:00 |  | PT_Normal |  |  |  |  | Go3Ub3jGQviIDTDidsXIPQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43571 |  |  |  |  | ELECTRICIANS SK | M302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29700 | N | N | 03 | SITE PREPARATORY WORKS |  | 125228 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 325 | ELECTRICIANS SK
%R | 503567 | 6359 | 125229 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AGNSP003000 | Site stripping | 8177 | 480 | 0 | 160 | 0 | 675 | 675 | 160 | 300 | 0 | 300 |  |  |  | 2013-01-27 08:00 | 2013-02-19 17:00 |  | 2012-11-17 08:00 | 2012-12-09 17:00 | 2012-11-17 08:00 | 2012-12-09 17:00 | 2012-11-17 08:00 | 2012-12-09 17:00 | 2013-01-27 08:00 | 2013-02-19 17:00 |  | PT_Normal |  |  |  |  | vebATI3uS2m7VHeFxaPp8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29700 | N | N | 03 | SITE PREPARATORY WORKS |  | 125228 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 675 | LABOR - CIVIL
%R | 503568 | 6359 | 125229 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AGNSP004000 | Demolition of Existing building & landscaping | 8177 | 480 | 0 | 160 | 0 | 2687.5 | 2687.5 | 160 | 1750 | 0 | 1750 |  |  |  | 2013-02-02 08:00 | 2013-02-25 17:00 |  | 2012-11-22 08:00 | 2012-12-15 17:00 | 2012-11-22 08:00 | 2012-12-15 17:00 | 2012-11-22 08:00 | 2012-12-15 17:00 | 2013-02-02 08:00 | 2013-02-25 17:00 |  | PT_Normal |  |  |  |  | qRRZI4jRT+C07auqWmBr8w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29700 | N | N | 03 | SITE PREPARATORY WORKS |  | 125228 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 2687.5 | LABOR - CIVIL
%R | 503569 | 6359 | 125229 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AGNSP005000 | Demolition of existing services works | 8177 | 480 | 480 | 160 | 0 | 775 | 775 | 160 | 400 | 0 | 400 |  |  |  | 2013-02-07 08:00 | 2013-03-03 17:00 |  | 2012-11-28 08:00 | 2012-12-22 17:00 | 2012-11-28 08:00 | 2012-12-22 17:00 | 2012-11-28 08:00 | 2012-12-22 17:00 | 2013-02-07 08:00 | 2013-03-03 17:00 |  | PT_Normal |  |  |  |  | 7Jdt7KdMQ9GJgxBKaGNZSg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29700 | N | N | 03 | SITE PREPARATORY WORKS |  | 125228 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 775 | LABOR - CIVIL
%R | 503570 | 6359 | 125229 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AGNSP002100 | Submission of Scanning Reports | 12515 | 0 | 0 | 40 | 0 | 40 | 40 | 40 | 0 | 0 | 0 |  |  |  | 2012-11-28 08:00 | 2012-12-03 17:00 |  | 2012-11-28 08:00 | 2012-12-03 17:00 | 2012-11-28 08:00 | 2012-12-03 17:00 | 2012-11-28 08:00 | 2012-12-03 17:00 | 2012-11-28 08:00 | 2012-12-03 17:00 |  | PT_Normal |  |  |  |  | kXHzANrFSEa8s0EAYaPGaQ | mUa/mwVkL06WZ2VwS6c03g |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | [5 empty] | 45403 |  |  |  |  | QUANTITY SURVEYOUR | M305 |  | 1 | QT_Hour |  | Y | Y | N | 1 |  | RT_Labor |  |  |  |  | 540 | 29700 | N | N | 03 | SITE PREPARATORY WORKS |  | 125228 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP11 |  | 40 | QUANTITY SURVEYOUR
%R | 503571 | 6359 | 125229 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AGNSP002200 | Information Required for Rerouting |  | 0 | 0 | 112 | 0 | 0 | 0 | 112 | 0 | 0 | 0 |  |  |  | 2012-12-04 08:00 | 2012-12-20 17:00 |  | 2012-12-04 08:00 | 2012-12-20 17:00 | 2012-12-04 08:00 | 2012-12-20 17:00 | 2012-12-04 08:00 | 2012-12-20 17:00 | 2012-12-04 08:00 | 2012-12-20 17:00 |  | PT_Normal |  |  |  |  | F9F8dl4gQFOKF8dZutdsMg | 1bxI7mBXcUGHOwncrhw4Ig |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29700 | N | N | 03 | SITE PREPARATORY WORKS |  | 125228 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 503572 | 6359 | 125229 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AGNSP002300 | Preparation & Submission for new Layout for rerouting | 12515 | 0 | 0 | 56 | 0 | 40 | 40 | 56 | 0 | 0 | 0 |  |  |  | 2012-12-22 08:00 | 2012-12-29 17:00 |  | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 | 2012-12-22 08:00 | 2012-12-29 17:00 |  | PT_Normal |  |  |  |  | rFCEaIEeQGqiIu/8FyYXXQ | NdEYf1DMFUuZ6s1akbRJ+A |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | [5 empty] | 45403 |  |  |  |  | QUANTITY SURVEYOUR | M305 |  | 1 | QT_Hour |  | Y | Y | N | 1 |  | RT_Labor |  |  |  |  | 540 | 29700 | N | N | 03 | SITE PREPARATORY WORKS |  | 125228 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 40 | QUANTITY SURVEYOUR
%R | 503573 | 6359 | 125229 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AGNSP002400 | Approval for new Layout for rerouting |  | 0 | 0 | 112 | 0 | 0 | 0 | 112 | 0 | 0 | 0 |  |  |  | 2012-12-30 08:00 | 2013-01-14 17:00 |  | 2012-12-30 08:00 | 2013-01-14 17:00 | 2012-12-30 08:00 | 2013-01-14 17:00 | 2012-12-30 08:00 | 2013-01-14 17:00 | 2012-12-30 08:00 | 2013-01-14 17:00 |  | PT_Normal |  |  |  |  | cPtXmCoETe+jPzkLbQtPcg | CeTNX/h3PkyHhgVT4OipZw |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | [26 empty] | 540 | 29700 | N | N | 03 | SITE PREPARATORY WORKS |  | 125228 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2012-AP12 |  | 0 | 0
%R | 503574 | 6359 | 125229 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AGNSP002500 | Rerouting Works | 8180 | 0 | 0 | 200 | 0 | 326 | 326 | 200 | 0 | 0 | 0 |  |  |  | 2013-01-15 08:00 | 2013-02-13 17:00 |  | 2013-01-15 08:00 | 2013-02-13 17:00 | 2013-01-15 08:00 | 2013-02-13 17:00 | 2013-01-15 08:00 | 2013-02-13 17:00 | 2013-01-15 08:00 | 2013-02-13 17:00 |  | PT_Normal |  |  |  |  | p6WLTUMaRBCgpjtgEEhB1Q | GenXSjxaLke8f4XSY6yRnQ |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43571 |  |  |  |  | ELECTRICIANS SK | M302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 29700 | N | N | 03 | SITE PREPARATORY WORKS |  | 125228 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP01 |  | 326 | ELECTRICIANS SK
%R | 503575 | 6359 | 125232 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2WEEX5040 | Block works & Plastering | 8168 | 104 | 0 | 200 | 0 | 512 | 512 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-17 08:00 | 2014-03-17 17:00 |  | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 |  | PT_Normal |  |  |  |  | H1SOYp2JQc6I+u/0TRfpAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30670 | N | N | 15 | WATER TANK ENCLOSURE |  | 125231 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 256 | BLOCK MASON SK
%R | 503576 | 6359 | 125232 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2WEEX5045 | Flooring & Painting | 8178 | 104 | 0 | 200 | 0 | 232 | 232 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-24 17:00 |  | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | acwSLkwXQEK8uuRpaLyV3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30670 | N | N | 15 | WATER TANK ENCLOSURE |  | 125231 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 116 | LABOR- SUBCONTRACTOR
%R | 503577 | 6359 | 125232 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2WEEX5050 | Installation of Steel Gate | 8178 | 104 | 24 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-03-31 17:00 |  | 2014-02-22 08:00 | 2014-03-16 17:00 | 2014-02-22 08:00 | 2014-03-16 17:00 | 2014-02-22 08:00 | 2014-03-16 17:00 | 2014-03-09 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | 5N+wKHoCTYeLg4eEVprqBA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30670 | N | N | 15 | WATER TANK ENCLOSURE |  | 125231 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 56 | LABOR- SUBCONTRACTOR
%R | 503578 | 6359 | 125232 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 80 | 0 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-12 17:00 |  | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 |  | PT_Normal |  |  |  |  | rBhsyAIwSQO0Z9Ztz1nRFw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30670 | N | N | 15 | WATER TANK ENCLOSURE |  | 125231 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 336 | LABOR- SUBCONTRACTOR
%R | 503579 | 6359 | 125232 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 72 | 0 | 200 | 0 | 203.2 | 203.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-19 17:00 |  | 2014-03-11 08:00 | 2014-04-08 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | tGwa5kuHTW6LsNGovuEb/w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30670 | N | N | 15 | WATER TANK ENCLOSURE |  | 125231 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 203.2 | LABOR- SUBCONTRACTOR
%R | 503580 | 6359 | 125232 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2WEEX5030 | Excavation | 8177 | 104 | 0 | 160 | 0 | 64 | 64 | 160 | 40 | 0 | 40 |  |  |  | 2014-02-01 08:00 | 2014-02-24 17:00 |  | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-02-01 08:00 | 2014-02-24 17:00 |  | PT_Normal |  |  |  |  | oht2MC1kQK6/E2uob3IBtg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30670 | N | N | 15 | WATER TANK ENCLOSURE |  | 125231 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 64 | LABOR - CIVIL
%R | 503581 | 6359 | 125232 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2WEEX5035 | Construction of Raft | 8165 | 104 | 0 | 200 | 0 | 840 | 840 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-03-08 17:00 |  | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | /elU3VzRQW2G3peWiZ2Ivw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30670 | N | N | 15 | WATER TANK ENCLOSURE |  | 125231 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 840 | STEEL FIXERS SK
%R | 503582 | 6359 | 125233 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2HDEX5090 | kerb works | 8173 | 128 | 0 | 160 | 0 | 344 | 344 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-12 17:00 |  | 2014-01-29 08:00 | 2014-02-22 17:00 | 2014-01-29 08:00 | 2014-02-22 17:00 | 2014-01-29 08:00 | 2014-02-22 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 |  | PT_Normal |  |  |  |  | 0e3UdiivRi2N5tOnotrVSQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30680 | N | N | 20 | HARD LANDSCAPING |  | 125231 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 344 | KERBSTONE MASON SK
%R | 503583 | 6359 | 125233 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2HDEX5095 | Cobble Stone Works | 8170 | 128 | 0 | 160 | 0 | 200 | 200 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-24 17:00 |  | 2014-02-10 08:00 | 2014-03-05 17:00 | 2014-02-10 08:00 | 2014-03-05 17:00 | 2014-02-10 08:00 | 2014-03-05 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | SB6tHQVQQf+K2SD4u2TkEA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30680 | N | N | 20 | HARD LANDSCAPING |  | 125231 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 200 | TILE MASON SK
%R | 503584 | 6359 | 125233 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2HDEX5100 | Interlock works | 8174 | 128 | 0 | 160 | 0 | 232 | 232 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-03-31 17:00 |  | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 | 2014-03-09 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | GSIyAxXoRbW3KmT0BbxENw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30680 | N | N | 20 | HARD LANDSCAPING |  | 125231 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 232 | INTERLOCK MASON SK
%R | 503585 | 6359 | 125234 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2SLEX5105 | Laying of Grass/ green area | 8178 | 128 | 0 | 200 | 0 | 2744 | 2744 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-12 17:00 |  | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-03-15 08:00 | 2014-04-12 17:00 |  | PT_Normal |  |  |  |  | Vef9KdX1SDy/kggmxcn8Yg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30690 | N | N | 25 | SOFT LANDSCAPING |  | 125231 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 1372 | LABOR- SUBCONTRACTOR
%R | 503586 | 6359 | 125234 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2SLEX5110 | Laying of Palm tree | 8178 | 128 | 128 | 200 | 0 | 168 | 168 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-19 17:00 |  | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | SGIPnsycRhellwmkCk7RIQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30690 | N | N | 25 | SOFT LANDSCAPING |  | 125231 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 168 | LABOR- SUBCONTRACTOR
%R | 503587 | 6359 | 125235 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2MSEX5015 | Construction of grease Trap | 8178 | 264 | 0 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-03-01 17:00 |  | 2013-12-29 08:00 | 2014-01-20 17:00 | 2013-12-29 08:00 | 2014-01-20 17:00 | 2013-12-29 08:00 | 2014-01-20 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | z8v5T11UQhy+/VEP3WVsjg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30660 | N | N | 10 | MISCELLANEOUS |  | 125231 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 56 | LABOR- SUBCONTRACTOR
%R | 503588 | 6359 | 125235 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2MSEX5000 | Construction of Manholes | 8172 | 264 | 0 | 200 | 0 | 528 | 528 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-02 08:00 | 2014-01-30 17:00 |  | 2013-11-24 08:00 | 2013-12-23 17:00 | 2013-11-24 08:00 | 2013-12-23 17:00 | 2013-11-24 08:00 | 2013-12-23 17:00 | 2014-01-02 08:00 | 2014-01-30 17:00 |  | PT_Normal |  |  |  |  | wEQQtZ+LS4uIkDy6IbmRGw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30660 | N | N | 10 | MISCELLANEOUS |  | 125231 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 528 | MANHOLES SK
%R | 503589 | 6359 | 125235 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2MSEX5005 | Construction of Soak pit, Chambers | 8172 | 264 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-02-15 17:00 |  | 2013-12-08 08:00 | 2014-01-06 17:00 | 2013-12-08 08:00 | 2014-01-06 17:00 | 2013-12-08 08:00 | 2014-01-06 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30660 | N | N | 10 | MISCELLANEOUS |  | 125231 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 176 | MANHOLES SK
%R | 503590 | 6359 | 125235 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2MSEX5010 | Telephone cable laying | 8177 | 264 | 176 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-30 17:00 |  | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | zZNU2q3uT5KPiI8rcn6ajg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30660 | N | N | 10 | MISCELLANEOUS |  | 125231 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 500 | LABOR - CIVIL
%R | 503591 | 6359 | 125235 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 824 | 0 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-06 08:00 | 2014-09-03 17:00 |  | 2014-04-05 08:00 | 2014-05-03 17:00 | 2014-04-05 08:00 | 2014-05-03 17:00 | 2014-04-05 08:00 | 2014-05-03 17:00 | 2014-08-06 08:00 | 2014-09-03 17:00 |  | PT_Normal |  |  |  |  | UvtO1ZuXS/mu8f5pyDPeug |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:44 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30660 | N | N | 10 | MISCELLANEOUS |  | 125231 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 400 | LABOR- SUBCONTRACTOR
%R | 503592 | 6359 | 125235 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2MSEX5020 | Construction Entrance Ramp | 8164 | 128 | 0 | 200 | 0 | 656 | 656 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-03 08:00 | 2014-03-04 17:00 |  | 2014-01-15 08:00 | 2014-02-13 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 | 2014-01-15 08:00 | 2014-02-13 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 |  | PT_Normal |  |  |  |  | pGtVjLEDQFK7z/8OC8/M9A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30660 | N | N | 10 | MISCELLANEOUS |  | 125231 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 656 | SCREED MASON SK
%R | 503593 | 6359 | 125235 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2MSEX5025 | SS.Handrails and Balustrades | 8178 | 152 | 48 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-25 08:00 | 2014-03-19 17:00 |  | 2014-02-02 08:00 | 2014-02-25 17:00 | 2014-02-02 08:00 | 2014-02-25 17:00 | 2014-02-02 08:00 | 2014-02-25 17:00 | 2014-02-25 08:00 | 2014-03-19 17:00 |  | PT_Normal |  |  |  |  | SjU4tqbTTO2ieHR5bg0+bw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30660 | N | N | 10 | MISCELLANEOUS |  | 125231 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 56 | LABOR- SUBCONTRACTOR
%R | 503594 | 6359 | 125238 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARRF3600 | Block work | 8168 | 416 | 0 | 160 | 0 | 700 | 700 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-03-02 17:00 |  | 2013-12-07 08:00 | 2013-12-30 17:00 | 2013-12-07 08:00 | 2013-12-30 17:00 | 2013-12-07 08:00 | 2013-12-30 17:00 | 2014-02-06 08:00 | 2014-03-02 17:00 |  | PT_Normal |  |  |  |  | cLs70s6sSBWj8URE0qVgtw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30470 | N | N | 20 | ROOF |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 700 | BLOCK MASON SK
%R | 503595 | 6359 | 125238 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARRF3605 | Plastering work | 8169 | 416 | 0 | 160 | 0 | 1786.5 | 1786.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-10 17:00 |  | 2013-12-15 08:00 | 2014-01-07 17:00 | 2013-12-15 08:00 | 2014-01-07 17:00 | 2013-12-15 08:00 | 2014-01-07 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | KcqxzGIYS5W6FR1Ata9Jcg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30470 | N | N | 20 | ROOF |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1786.5 | PLASTER MASON SK
%R | 503596 | 6359 | 125238 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARRF3610 | Flooring screed | 8164 | 456 | 0 | 120 | 0 | 136.5 | 136.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-24 17:00 |  | 2013-12-30 08:00 | 2014-01-15 17:00 | 2013-12-30 08:00 | 2014-01-15 17:00 | 2013-12-30 08:00 | 2014-01-15 17:00 | 2014-03-08 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | Po+6rInCTtyB8ovQ3Tn14w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30470 | N | N | 20 | ROOF |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 136.5 | SCREED MASON SK
%R | 503597 | 6359 | 125238 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARRF3695 | Painting -Storage area | 8178 | 456 | 0 | 160 | 0 | 1640 | 1640 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-16 08:00 | 2014-04-07 17:00 |  | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-03-16 08:00 | 2014-04-07 17:00 |  | PT_Normal |  |  |  |  | qPaelL5GTDOPu9JFzcHRaA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30470 | N | N | 20 | ROOF |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1640 | LABOR- SUBCONTRACTOR
%R | 503598 | 6359 | 125238 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARRF3620 | Epoxy Painting -Storage area | 8178 | 456 | 456 | 120 | 0 | 48.5 | 48.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-02 08:00 | 2014-04-19 17:00 |  | 2014-01-25 08:00 | 2014-02-10 17:00 | 2014-01-25 08:00 | 2014-02-10 17:00 | 2014-01-25 08:00 | 2014-02-10 17:00 | 2014-04-02 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | 1AGLDYyRQv2PAIxLKWefAA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30470 | N | N | 20 | ROOF |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 48.5 | LABOR- SUBCONTRACTOR
%R | 503599 | 6359 | 125239 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARFF3380 | Aluminum windows | 8178 | 32 | 32 | 160 | 0 | 162.25 | 162.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-10 08:00 | 2014-04-01 17:00 |  | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-03-10 08:00 | 2014-04-01 17:00 |  | PT_Normal |  |  |  |  | Rsvk7PV8TAWl4auMsk5qdQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30460 | N | N | 15 | FIRST FLOORS |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 162.25 | LABOR- SUBCONTRACTOR
%R | 503600 | 6359 | 125239 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARFF3375 | Carpentry & Joinery Works | 8178 | 0 | 0 | 200 | 0 | 1100 | 1100 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-04 08:00 | 2014-04-01 17:00 |  | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 |  | PT_Normal |  |  |  |  | urDnAFouTFi9fgxOL+09/w |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30460 | N | N | 15 | FIRST FLOORS |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1100 | LABOR- SUBCONTRACTOR
%R | 503601 | 6359 | 125239 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARFF3390 | Installation of Granite Counter Top | 8171 | 8 | 8 | 160 | 0 | 88 | 88 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-08 17:00 |  | 2014-03-16 08:00 | 2014-04-07 17:00 | 2014-03-16 08:00 | 2014-04-07 17:00 | 2014-03-16 08:00 | 2014-04-07 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | eBO+ybJ7Tq+eFRbtDS4lig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30460 | N | N | 15 | FIRST FLOORS |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 88 | GRANITE MASON SK
%R | 503602 | 6359 | 125239 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARFF3385 | Handrail & Balustrade | 8178 | 0 | 0 | 160 | 0 | 787.5 | 787.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-16 08:00 | 2014-04-07 17:00 |  | 2014-03-16 08:00 | 2014-04-07 17:00 | 2014-03-16 08:00 | 2014-04-07 17:00 | 2014-03-16 08:00 | 2014-04-07 17:00 | 2014-03-16 08:00 | 2014-04-07 17:00 |  | PT_Normal |  |  |  |  | 42pfzH0uRkC79rjypJmp+w |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30460 | N | N | 15 | FIRST FLOORS |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 787.5 | LABOR- SUBCONTRACTOR
%R | 503603 | 6359 | 125239 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARFF3395 | Final Painting | 8178 | 0 | 0 | 200 | 0 | 4742.75 | 4742.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-19 17:00 |  | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30460 | N | N | 15 | FIRST FLOORS |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 4742.75 | LABOR- SUBCONTRACTOR
%R | 503604 | 6359 | 125239 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARFF3300 | Block work | 8168 | 0 | 0 | 200 | 0 | 6387.5 | 6387.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-23 08:00 | 2013-12-22 17:00 |  | 2013-11-23 08:00 | 2013-12-22 17:00 | 2013-11-23 08:00 | 2013-12-22 17:00 | 2013-11-23 08:00 | 2013-12-22 17:00 | 2013-11-23 08:00 | 2013-12-22 17:00 |  | PT_Normal |  |  |  |  | 9gqFSYTlQZ2uJPiu+boXsw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30460 | N | N | 15 | FIRST FLOORS |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 6387.5 | BLOCK MASON SK
%R | 503605 | 6359 | 125239 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARFF3305 | Plastering work | 8169 | 0 | 0 | 200 | 0 | 8899 | 8899 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-17 08:00 | 2014-01-15 17:00 |  | 2013-12-17 08:00 | 2014-01-15 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | 2v/Tgy8PTgi5DgLPmFSaPw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30460 | N | N | 15 | FIRST FLOORS |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 8899 | PLASTER MASON SK
%R | 503606 | 6359 | 125239 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARFF3310 | Flooring screed | 8164 | 96 | 96 | 168 | 0 | 1215.5 | 1215.5 | 168 | 0 | 0 | 0 |  |  |  | 2014-01-09 08:00 | 2014-02-02 17:00 |  | 2013-12-26 08:00 | 2014-01-19 17:00 | 2013-12-26 08:00 | 2014-01-19 17:00 | 2013-12-26 08:00 | 2014-01-19 17:00 | 2014-01-09 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | dvj4OLHkR8O2YKVfppyz1w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30460 | N | N | 15 | FIRST FLOORS |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1215.5 | SCREED MASON SK
%R | 503607 | 6359 | 125239 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARFF3315 | Wet area waterproofing | 8178 | 0 | 0 | 120 | 0 | 1215.5 | 1215.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-07 08:00 | 2014-01-23 17:00 |  | 2014-01-07 08:00 | 2014-01-23 17:00 | 2014-01-07 08:00 | 2014-01-23 17:00 | 2014-01-07 08:00 | 2014-01-23 17:00 | 2014-01-07 08:00 | 2014-01-23 17:00 |  | PT_Normal |  |  |  |  | 8xVJuBOiRZGVcrCq5u8hJw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30460 | N | N | 15 | FIRST FLOORS |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1215.5 | LABOR- SUBCONTRACTOR
%R | 503608 | 6359 | 125239 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARFF3330 | Paint First coat | 8178 | 112 | 112 | 200 | 0 | 4742.75 | 4742.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-20 08:00 | 2014-02-18 17:00 |  | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-01-04 08:00 | 2014-02-01 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 |  | PT_Normal |  |  |  |  | J5V0OW4lQy2k8Bz93BDHhA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30460 | N | N | 15 | FIRST FLOORS |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 4742.75 | LABOR- SUBCONTRACTOR
%R | 503609 | 6359 | 125239 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARFF3320 | Ceramic Wall Tiling | 8170 | 0 | 0 | 200 | 0 | 1897.25 | 1897.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-02-12 17:00 |  | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 |  | PT_Normal |  |  |  |  | RNQ2WEUGRaGOjPJXzsMcuw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30460 | N | N | 15 | FIRST FLOORS |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1897.25 | TILE MASON SK
%R | 503610 | 6359 | 125239 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARFF3325 | Porcelain Tile flooring | 8170 | 0 | 0 | 200 | 0 | 1743.75 | 1743.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-21 08:00 | 2014-02-19 17:00 |  | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 |  | PT_Normal |  |  |  |  | 8GjI9lq2QKuWYUE/E7egfQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30460 | N | N | 15 | FIRST FLOORS |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1743.75 | TILE MASON SK
%R | 503611 | 6359 | 125239 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARFF3335 | Slate Tile Flooring & Skirting | 8170 | 64 | 64 | 120 | 0 | 261.5 | 261.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-06 17:00 |  | 2014-02-08 08:00 | 2014-02-25 17:00 | 2014-02-08 08:00 | 2014-02-25 17:00 | 2014-02-08 08:00 | 2014-02-25 17:00 | 2014-02-18 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | 6aYUOz36SmyGZf0jbw3H3g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30460 | N | N | 15 | FIRST FLOORS |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 261.5 | TILE MASON SK
%R | 503612 | 6359 | 125239 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARFF3350 | Granite - Stair case flooring & Skirting | 8171 | 16 | 16 | 160 | 0 | 875 | 875 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-15 08:00 | 2014-03-09 17:00 |  | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-02-12 08:00 | 2014-03-06 17:00 | 2014-02-15 08:00 | 2014-03-09 17:00 |  | PT_Normal |  |  |  |  | zLP+nmqCSqCbIthTn6KNMg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30460 | N | N | 15 | FIRST FLOORS |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 875 | GRANITE MASON SK
%R | 503613 | 6359 | 125239 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARFF3345 | Fixing of Suspension systems | 8178 | 0 | 0 | 160 | 0 | 1305 | 1305 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-03 08:00 | 2014-02-26 17:00 |  | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-02-03 08:00 | 2014-02-26 17:00 |  | PT_Normal |  |  |  |  | 3/y9fiI2Tx6U0tt5dvlPtA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30460 | N | N | 15 | FIRST FLOORS |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1305 | LABOR- SUBCONTRACTOR
%R | 503614 | 6359 | 125239 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARFF3360 | Gypsum board false ceiling | 8178 | 0 | 0 | 200 | 0 | 1305 | 1305 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-10 08:00 | 2014-03-11 17:00 |  | 2014-02-10 08:00 | 2014-03-11 17:00 | 2014-02-10 08:00 | 2014-03-11 17:00 | 2014-02-10 08:00 | 2014-03-11 17:00 | 2014-02-10 08:00 | 2014-03-11 17:00 |  | PT_Normal |  |  |  |  | GzUKK9fPSZW7ai8D6nKS4g |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30460 | N | N | 15 | FIRST FLOORS |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 652.5 | LABOR- SUBCONTRACTOR
%R | 503615 | 6359 | 125239 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARFF3365 | Wooden door | 8178 | 0 | 0 | 120 | 0 | 308 | 308 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-26 08:00 | 2014-03-15 17:00 |  | 2014-02-26 08:00 | 2014-03-15 17:00 | 2014-02-26 08:00 | 2014-03-15 17:00 | 2014-02-26 08:00 | 2014-03-15 17:00 | 2014-02-26 08:00 | 2014-03-15 17:00 |  | PT_Normal |  |  |  |  | 10bYMOb9TLaEiTCvZn7VvQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30460 | N | N | 15 | FIRST FLOORS |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 308 | LABOR- SUBCONTRACTOR
%R | 503616 | 6359 | 125239 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARFF3370 | Aluminum Door | 8178 | 0 | 0 | 160 | 0 | 220 | 220 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-26 08:00 | 2014-03-20 17:00 |  | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | h9v6WdX7SxKxQRuU5OLU7w |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30460 | N | N | 15 | FIRST FLOORS |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 220 | LABOR- SUBCONTRACTOR
%R | 503617 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3090 | Installation of Granite Counter Top | 8171 | 168 | 0 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-12 08:00 | 2014-03-29 17:00 |  | 2014-02-16 08:00 | 2014-03-04 17:00 | 2014-02-16 08:00 | 2014-03-04 17:00 | 2014-02-16 08:00 | 2014-03-04 17:00 | 2014-03-12 08:00 | 2014-03-29 17:00 |  | PT_Normal |  |  |  |  | m9bqGruYThijurFnYPguGA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 176 | GRANITE MASON SK
%R | 503618 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3085 | S.S.Balustrade | 8178 | 208 | 40 | 160 | 0 | 262.5 | 262.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-13 08:00 | 2014-04-05 17:00 |  | 2014-02-10 08:00 | 2014-03-05 17:00 | 2014-02-10 08:00 | 2014-03-05 17:00 | 2014-02-10 08:00 | 2014-03-05 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 |  | PT_Normal |  |  |  |  | 2pDM//H3S9qrDwvdvR87FA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 262.5 | LABOR- SUBCONTRACTOR
%R | 503619 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3095 | Final Painting | 8178 | 168 | 0 | 200 | 0 | 5425.75 | 5425.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-19 17:00 |  | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | TLH7XdPwR3ODSOr+lyPeYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 2712.875 | LABOR- SUBCONTRACTOR
%R | 503620 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3000 | Block work | 8168 | 144 | 0 | 200 | 0 | 9737.5 | 9737.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-02 08:00 | 2013-11-30 17:00 |  | 2013-10-09 08:00 | 2013-11-09 17:00 | 2013-10-09 08:00 | 2013-11-09 17:00 | 2013-10-09 08:00 | 2013-11-09 17:00 | 2013-11-02 08:00 | 2013-11-30 17:00 |  | PT_Normal |  |  |  |  | IKhkuWgUSb60M1S8c5zocQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 4868.75 | BLOCK MASON SK
%R | 503621 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3005 | Plastering work | 8169 | 144 | 0 | 200 | 0 | 13637.5 | 13637.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-24 08:00 | 2013-12-23 17:00 |  | 2013-11-03 08:00 | 2013-12-01 17:00 | 2013-11-03 08:00 | 2013-12-01 17:00 | 2013-11-03 08:00 | 2013-12-01 17:00 | 2013-11-24 08:00 | 2013-12-23 17:00 |  | PT_Normal |  |  |  |  | GSqJRMTATHCZC32TF5ZS8A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 13637.5 | PLASTER MASON SK
%R | 503622 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3010 | Flooring screed | 8164 | 208 | 64 | 168 | 0 | 1580.25 | 1580.25 | 168 | 0 | 0 | 0 |  |  |  | 2013-12-11 08:00 | 2014-01-05 17:00 |  | 2013-11-11 08:00 | 2013-12-04 17:00 | 2013-11-11 08:00 | 2013-12-04 17:00 | 2013-11-11 08:00 | 2013-12-04 17:00 | 2013-12-11 08:00 | 2014-01-05 17:00 |  | PT_Normal |  |  |  |  | BeytolVaRM2wuaMqS0ccTw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1580.25 | SCREED MASON SK
%R | 503623 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 144 | 0 | 120 | 0 | 247.5 | 247.5 | 120 | 0 | 0 | 0 |  |  |  | 2013-12-11 08:00 | 2013-12-29 17:00 |  | 2013-11-20 08:00 | 2013-12-07 17:00 | 2013-11-20 08:00 | 2013-12-07 17:00 | 2013-11-20 08:00 | 2013-12-07 17:00 | 2013-12-11 08:00 | 2013-12-29 17:00 |  | PT_Normal |  |  |  |  | viYclvvfQUCBPAqt3+Ppzw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 247.5 | LABOR- SUBCONTRACTOR
%R | 503624 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3030 | Paint First coat | 8178 | 256 | 0 | 200 | 0 | 5425.75 | 5425.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-28 08:00 | 2014-01-25 17:00 |  | 2013-11-19 08:00 | 2013-12-17 17:00 | 2013-11-19 08:00 | 2013-12-17 17:00 | 2013-11-19 08:00 | 2013-12-17 17:00 | 2013-12-28 08:00 | 2014-01-25 17:00 |  | PT_Normal |  |  |  |  | bTwcJpkuQEqxYs07QQCrnA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 5425.75 | LABOR- SUBCONTRACTOR
%R | 503625 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3020 | Ceramic Wall Tiling | 8170 | 144 | 0 | 200 | 0 | 4428.5 | 4428.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-17 08:00 | 2014-01-15 17:00 |  | 2013-11-26 08:00 | 2013-12-25 17:00 | 2013-11-26 08:00 | 2013-12-25 17:00 | 2013-11-26 08:00 | 2013-12-25 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | vW/wjGCNRl2kj+WCMWRkfw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 4428.5 | TILE MASON SK
%R | 503626 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3025 | Porcelain Tile flooring | 8170 | 144 | 0 | 200 | 0 | 1743.75 | 1743.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-24 08:00 | 2014-01-21 17:00 |  | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 |  | PT_Normal |  |  |  |  | TfsA/5dLRmatoCC9UpyCgg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1743.75 | TILE MASON SK
%R | 503627 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3040 | Cobble Tile flooring | 8170 | 168 | 0 | 120 | 0 | 741 | 741 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-23 08:00 | 2014-02-09 17:00 |  | 2013-12-30 08:00 | 2014-01-15 17:00 | 2013-12-30 08:00 | 2014-01-15 17:00 | 2013-12-30 08:00 | 2014-01-15 17:00 | 2014-01-23 08:00 | 2014-02-09 17:00 |  | PT_Normal |  |  |  |  | DAwayWuaQO6j+kq9acdNyA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 741 | TILE MASON SK
%R | 503628 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 184 | 16 | 120 | 0 | 761.5 | 761.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-19 08:00 | 2014-02-04 17:00 |  | 2013-12-23 08:00 | 2014-01-08 17:00 | 2013-12-23 08:00 | 2014-01-08 17:00 | 2013-12-23 08:00 | 2014-01-08 17:00 | 2014-01-19 08:00 | 2014-02-04 17:00 |  | PT_Normal |  |  |  |  | JZRn+d+yS6yFcvc9kFRJHA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 761.5 | TILE MASON SK
%R | 503629 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 168 | 0 | 160 | 0 | 875 | 875 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-01 08:00 | 2014-02-24 17:00 |  | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-01-07 08:00 | 2014-01-29 17:00 | 2014-02-01 08:00 | 2014-02-24 17:00 |  | PT_Normal |  |  |  |  | OnGzn8n3TIK6c3Wxe/epSA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 875 | GRANITE MASON SK
%R | 503630 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3045 | Fixing of Suspension systems | 8178 | 144 | 0 | 160 | 0 | 1455.05 | 1455.05 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-11 08:00 | 2014-02-02 17:00 |  | 2013-12-21 08:00 | 2014-01-12 17:00 | 2013-12-21 08:00 | 2014-01-12 17:00 | 2013-12-21 08:00 | 2014-01-12 17:00 | 2014-01-11 08:00 | 2014-02-02 17:00 |  | PT_Normal |  |  |  |  | MOa5x9dLTuGEeG237k9qXQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1455.05 | LABOR- SUBCONTRACTOR
%R | 503631 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3055 | Aluminum tile false ceiling | 8178 | 168 | 24 | 200 | 0 | 150 | 150 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-20 17:00 |  | 2013-12-29 08:00 | 2014-01-26 17:00 | 2013-12-29 08:00 | 2014-01-26 17:00 | 2013-12-29 08:00 | 2014-01-26 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | Cbnnqu3aTGaDc18S+xRWZg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 150 | LABOR- SUBCONTRACTOR
%R | 503632 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3060 | Gypsum board false ceiling | 8178 | 144 | 0 | 200 | 0 | 1335.15 | 1335.15 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-20 17:00 |  | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | pB6Kwq8RQKWODqZEk0m6sQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1335.15 | LABOR- SUBCONTRACTOR
%R | 503633 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3065 | Wooden door & PVC Door | 8178 | 168 | 0 | 120 | 0 | 308 | 308 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-04 17:00 |  | 2014-01-21 08:00 | 2014-02-06 17:00 | 2014-01-21 08:00 | 2014-02-06 17:00 | 2014-01-21 08:00 | 2014-02-06 17:00 | 2014-02-16 08:00 | 2014-03-04 17:00 |  | PT_Normal |  |  |  |  | 942ij9h2R1ihdK4Xrm8xBw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 308 | LABOR- SUBCONTRACTOR
%R | 503634 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3070 | Aluminum doors | 8178 | 168 | 0 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-10 17:00 |  | 2014-01-27 08:00 | 2014-02-13 17:00 | 2014-01-27 08:00 | 2014-02-13 17:00 | 2014-01-27 08:00 | 2014-02-13 17:00 | 2014-02-22 08:00 | 2014-03-10 17:00 |  | PT_Normal |  |  |  |  | ST9I8ln6R52yAkceeZcaEA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 176 | LABOR- SUBCONTRACTOR
%R | 503635 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3080 | Aluminum windows | 8178 | 248 | 40 | 160 | 0 | 162.25 | 162.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-12 08:00 | 2014-04-03 17:00 |  | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-02-03 08:00 | 2014-02-26 17:00 | 2014-03-12 08:00 | 2014-04-03 17:00 |  | PT_Normal |  |  |  |  | pxdFkGo9RW+2NcOhe2WAiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 162.25 | LABOR- SUBCONTRACTOR
%R | 503636 | 6359 | 125240 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARGF3075 | Carpentry & Joinery Works | 8178 | 168 | 0 | 160 | 0 | 572 | 572 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-27 08:00 | 2014-03-22 17:00 |  | 2014-02-02 08:00 | 2014-02-25 17:00 | 2014-02-02 08:00 | 2014-02-25 17:00 | 2014-02-02 08:00 | 2014-02-25 17:00 | 2014-02-27 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | AZD7outmQCuULcsxZvaCPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30450 | N | N | 10 | GROUND FLOOR |  | 125237 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 572 | LABOR- SUBCONTRACTOR
%R | 503637 | 6359 | 125242 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2AREL3665 | External Plastering | 8169 | 376 | 0 | 200 | 0 | 14275 | 14275 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-24 08:00 | 2014-03-24 17:00 |  | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 |  | PT_Normal |  |  |  |  | fUPz3flCT2egmIHYcozj0g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30500 | N | N | 15 | ELEVATION |  | 125241 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 14275 | PLASTER MASON SK
%R | 503638 | 6359 | 125242 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2AREL3670 | External stone cladding works | 8170 | 392 | 0 | 160 | 0 | 990 | 990 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-16 08:00 | 2014-04-07 17:00 |  | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-01-16 08:00 | 2014-02-08 17:00 | 2014-03-16 08:00 | 2014-04-07 17:00 |  | PT_Normal |  |  |  |  | vyHtos3BQiWqK85ldAj0Pg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30500 | N | N | 15 | ELEVATION |  | 125241 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 990 | TILE MASON SK
%R | 503639 | 6359 | 125242 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2AREL3680 | External Painting | 8178 | 392 | 40 | 160 | 0 | 3784 | 3784 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-27 08:00 | 2014-04-19 17:00 |  | 2014-01-28 08:00 | 2014-02-20 17:00 | 2014-01-28 08:00 | 2014-02-20 17:00 | 2014-01-28 08:00 | 2014-02-20 17:00 | 2014-03-27 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | VTkX/f/+RMG/zb+Vq68mCA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30500 | N | N | 15 | ELEVATION |  | 125241 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 3784 | LABOR- SUBCONTRACTOR
%R | 503640 | 6359 | 125243 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARRF3630 | Leveling Screed for Waterproofing | 8164 | 168 | 0 | 200 | 0 | 800 | 800 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-06 08:00 | 2014-03-08 17:00 |  | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-01-13 08:00 | 2014-02-10 17:00 | 2014-02-06 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | NB1i5z3RSR+SeBTkC2a1gw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30490 | N | N | 10 | ROOF |  | 125241 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 800 | SCREED MASON SK
%R | 503641 | 6359 | 125243 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARRF3635 | Laying of Waterproofing Membrane | 8178 | 168 | 0 | 200 | 0 | 1138.5 | 1138.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-10 08:00 | 2014-03-11 17:00 |  | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-02-10 08:00 | 2014-03-11 17:00 |  | PT_Normal |  |  |  |  | VNeMy90rRB29NUd4rI8BqQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30490 | N | N | 10 | ROOF |  | 125241 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1138.5 | LABOR- SUBCONTRACTOR
%R | 503642 | 6359 | 125243 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARRF3640 | Installation of Insulation & Protection | 8178 | 168 | 0 | 200 | 0 | 1408 | 1408 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-16 17:00 |  | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-01-21 08:00 | 2014-02-19 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | p57AidToR7GSjwbmX4wewQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30490 | N | N | 10 | ROOF |  | 125241 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1408 | LABOR- SUBCONTRACTOR
%R | 503643 | 6359 | 125243 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 168 | 0 | 200 | 0 | 688.25 | 688.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-20 08:00 | 2014-03-20 17:00 |  | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | TlQRPhasRl6WcGd2j0hD0w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30490 | N | N | 10 | ROOF |  | 125241 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 688.25 | TILE MASON SK
%R | 503644 | 6359 | 125243 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 168 | 0 | 160 | 0 | 616 | 616 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-16 08:00 | 2014-04-07 17:00 |  | 2014-02-19 08:00 | 2014-03-13 17:00 | 2014-02-19 08:00 | 2014-03-13 17:00 | 2014-02-19 08:00 | 2014-03-13 17:00 | 2014-03-16 08:00 | 2014-04-07 17:00 |  | PT_Normal |  |  |  |  | dfcFugLqSrKEZvND4aqTGQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30490 | N | N | 10 | ROOF |  | 125241 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 616 | LABOR- SUBCONTRACTOR
%R | 503645 | 6359 | 125243 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 168 | 0 | 200 | 0 | 1046.5 | 1046.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-01 08:00 | 2014-03-29 17:00 |  | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-03-01 08:00 | 2014-03-29 17:00 |  | PT_Normal |  |  |  |  | VrthGYTxSIOgCbadQT1WGw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30490 | N | N | 10 | ROOF |  | 125241 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 523.25 | LABOR- SUBCONTRACTOR
%R | 503646 | 6359 | 125243 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ARRF3660 | Installation of Access Ladder | 8178 | 208 | 208 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-02 08:00 | 2014-04-19 17:00 |  | 2014-03-03 08:00 | 2014-03-19 17:00 | 2014-03-03 08:00 | 2014-03-19 17:00 | 2014-03-03 08:00 | 2014-03-19 17:00 | 2014-04-02 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | VrI2O60FReCXXg7RZO7LZQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30490 | N | N | 10 | ROOF |  | 125241 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 176 | LABOR- SUBCONTRACTOR
%R | 503647 | 6359 | 125244 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 0 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | nPIZyY+TS3aag8pfT5NUfw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30700 | N | N | 30 | TESTING AND COMMISSIONING |  | 125230 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 503648 | 6359 | 125244 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | r5u4fjV9QOatei0Z0RHUkQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30700 | N | N | 30 | TESTING AND COMMISSIONING |  | 125230 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 503649 | 6359 | 125244 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | oH2dcHNgRKWpJQrZFDORww |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30700 | N | N | 30 | TESTING AND COMMISSIONING |  | 125230 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 503650 | 6359 | 125247 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ELRF4070 | Installation of Isolator | 8178 | 8 | 0 | 144 | 0 | 412.8 | 412.8 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-18 08:00 | 2014-04-07 17:00 |  | 2014-03-17 08:00 | 2014-04-06 17:00 | 2014-03-17 08:00 | 2014-04-06 17:00 | 2014-03-17 08:00 | 2014-04-06 17:00 | 2014-03-18 08:00 | 2014-04-07 17:00 |  | PT_Normal |  |  |  |  | SaW8iPwIQ2Kd0b/ThOUFyw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30550 | N | N | 20 | ROOF |  | 125246 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 412.8 | LABOR- SUBCONTRACTOR
%R | 503651 | 6359 | 125247 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ELRF4075 | Installation of TV Dish Antenna | 8178 | 8 | 8 | 184 | 0 | 732.8 | 732.8 | 184 | 0 | 0 | 0 |  |  |  | 2014-03-24 08:00 | 2014-04-19 17:00 |  | 2014-03-23 08:00 | 2014-04-17 17:00 | 2014-03-23 08:00 | 2014-04-17 17:00 | 2014-03-23 08:00 | 2014-04-17 17:00 | 2014-03-24 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | X1utrzVdSPqFDoZ4S5OdPw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30550 | N | N | 20 | ROOF |  | 125246 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 732.8 | LABOR- SUBCONTRACTOR
%R | 503652 | 6359 | 125248 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 88 | 0 | 200 | 0 | 1222.4 | 1222.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-11 08:00 | 2014-01-09 17:00 |  | 2013-11-28 08:00 | 2013-12-28 17:00 | 2013-11-28 08:00 | 2013-12-28 17:00 | 2013-11-28 08:00 | 2013-12-28 17:00 | 2013-12-11 08:00 | 2014-01-09 17:00 |  | PT_Normal |  |  |  |  | oxiiNPJbQRSa2inTIQwO6g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30540 | N | N | 15 | FIRST FLOORS |  | 125246 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11; period 2: 2013-AP12 |  | 611.2 | LABOR- SUBCONTRACTOR
%R | 503653 | 6359 | 125248 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ELFF4040 | Cable tray & trunking installation | 8178 | 232 | 16 | 160 | 0 | 1318.4 | 1318.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-02-05 17:00 |  | 2013-12-10 08:00 | 2014-01-02 17:00 | 2013-12-10 08:00 | 2014-01-02 17:00 | 2013-12-10 08:00 | 2014-01-02 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | tv6FwpIuQDSbEfJ5A+brVA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30540 | N | N | 15 | FIRST FLOORS |  | 125246 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1318.4 | LABOR- SUBCONTRACTOR
%R | 503654 | 6359 | 125248 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ELFF4045 | Installation of wiring & Main Cabling | 8178 | 216 | 0 | 200 | 0 | 296 | 296 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-20 17:00 |  | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2013-12-22 08:00 | 2014-01-19 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | cgT7XPp/RzS0Me82R8mACQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30540 | N | N | 15 | FIRST FLOORS |  | 125246 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 296 | LABOR- SUBCONTRACTOR
%R | 503655 | 6359 | 125248 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 24 | 16 | 160 | 0 | 227.2 | 227.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-26 08:00 | 2014-03-20 17:00 |  | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-02-23 08:00 | 2014-03-17 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | rF8U28eEQEaxgG/37B8KzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30540 | N | N | 15 | FIRST FLOORS |  | 125246 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 227.2 | LABOR- SUBCONTRACTOR
%R | 503656 | 6359 | 125248 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 8 | 0 | 200 | 0 | 1651.2 | 1651.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-04 08:00 | 2014-04-01 17:00 |  | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 |  | PT_Normal |  |  |  |  | OVnRcxjgSkKtxXALuH37yg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30540 | N | N | 15 | FIRST FLOORS |  | 125246 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1651.2 | LABOR- SUBCONTRACTOR
%R | 503657 | 6359 | 125248 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 8 | 0 | 200 | 0 | 1008 | 1008 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-20 08:00 | 2014-03-20 17:00 |  | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | Ld6zt53XTmWou2jhyy1cMA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30540 | N | N | 15 | FIRST FLOORS |  | 125246 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 504 | LABOR- SUBCONTRACTOR
%R | 503658 | 6359 | 125248 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ELFF4050 | Installation of Telephone System | 8178 | 88 | 80 | 200 | 0 | 451.2 | 451.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-02 08:00 | 2014-03-30 17:00 |  | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | ou2L75v+SfSfylfBQ4gHXg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30540 | N | N | 15 | FIRST FLOORS |  | 125246 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 225.6 | LABOR- SUBCONTRACTOR
%R | 503659 | 6359 | 125249 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 216 | 0 | 200 | 0 | 1222.4 | 1222.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-18 08:00 | 2013-12-16 17:00 |  | 2013-10-15 08:00 | 2013-11-14 17:00 | 2013-10-15 08:00 | 2013-11-14 17:00 | 2013-10-15 08:00 | 2013-11-14 17:00 | 2013-11-18 08:00 | 2013-12-16 17:00 |  | PT_Normal |  |  |  |  | NZOlQmYfSuSH+H7Ss0+2Yg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30530 | N | N | 10 | GROUND FLOOR |  | 125246 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1222.4 | LABOR- SUBCONTRACTOR
%R | 503660 | 6359 | 125249 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ELGF4005 | Cable tray & trunking installation | 8178 | 360 | 0 | 160 | 0 | 1318.4 | 1318.4 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-22 08:00 | 2014-01-13 17:00 |  | 2013-10-29 08:00 | 2013-11-20 17:00 | 2013-10-29 08:00 | 2013-11-20 17:00 | 2013-10-29 08:00 | 2013-11-20 17:00 | 2013-12-22 08:00 | 2014-01-13 17:00 |  | PT_Normal |  |  |  |  | /PRMZINsQzu+99hi9PndHQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30530 | N | N | 10 | GROUND FLOOR |  | 125246 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1318.4 | LABOR- SUBCONTRACTOR
%R | 503661 | 6359 | 125249 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ELGF4010 | Installation of wiring & Main Cabling | 8178 | 360 | 216 | 200 | 0 | 296 | 296 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-30 08:00 | 2014-01-27 17:00 |  | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-12-30 08:00 | 2014-01-27 17:00 |  | PT_Normal |  |  |  |  | 3Ysmt6UdRTWAUbvFJnu++g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30530 | N | N | 10 | GROUND FLOOR |  | 125246 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 296 | LABOR- SUBCONTRACTOR
%R | 503662 | 6359 | 125249 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 144 | 0 | 160 | 0 | 227.2 | 227.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-03-01 17:00 |  | 2014-01-15 08:00 | 2014-02-06 17:00 | 2014-01-15 08:00 | 2014-02-06 17:00 | 2014-01-15 08:00 | 2014-02-06 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 |  | PT_Normal |  |  |  |  | tH7rtiecQRySBcgfKmL9PA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30530 | N | N | 10 | GROUND FLOOR |  | 125246 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 227.2 | LABOR- SUBCONTRACTOR
%R | 503663 | 6359 | 125249 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 200 | 0 | 200 | 0 | 1651.2 | 1651.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-26 08:00 | 2014-03-26 17:00 |  | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 |  | PT_Normal |  |  |  |  | Dpt10zMdRGC1xVoBkMm35w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30530 | N | N | 10 | GROUND FLOOR |  | 125246 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1651.2 | LABOR- SUBCONTRACTOR
%R | 503664 | 6359 | 125249 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 240 | 0 | 200 | 0 | 1075.2 | 1075.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-15 08:00 | 2014-03-15 17:00 |  | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 |  | PT_Normal |  |  |  |  | JCmeigPnRbqDSrJFzxiYmA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30530 | N | N | 10 | GROUND FLOOR |  | 125246 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1075.2 | LABOR- SUBCONTRACTOR
%R | 503665 | 6359 | 125249 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ELGF4030 | Installation of Telephone System | 8178 | 144 | 40 | 160 | 0 | 520 | 520 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-12 17:00 |  | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-02-18 08:00 | 2014-03-12 17:00 |  | PT_Normal |  |  |  |  | FRHf6aTcSEmE8FVzSsm9EQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30530 | N | N | 10 | GROUND FLOOR |  | 125246 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 520 | LABOR- SUBCONTRACTOR
%R | 503666 | 6359 | 125251 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ACRF4630 | Installation of Refrigerant Pipes | 8178 | 272 | 0 | 200 | 0 | 409.6 | 409.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-16 08:00 | 2014-04-13 17:00 |  | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 |  | PT_Normal |  |  |  |  | zZcXvnzLQOOHaCeqtG26gA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30630 | N | N | 20 | ROOF |  | 125250 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 204.8 | LABOR- SUBCONTRACTOR
%R | 503667 | 6359 | 125251 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ACRF4635 | Installation of Condensing Unit | 8178 | 24 | 0 | 200 | 0 | 568 | 568 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-19 17:00 |  | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | XtlR67hEQP+Gsk48o0C+mg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30630 | N | N | 20 | ROOF |  | 125250 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 568 | LABOR- SUBCONTRACTOR
%R | 503668 | 6359 | 125252 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ACGF4600 | Installation AC Pipes | 8178 | 392 | 40 | 160 | 0 | 977.6 | 977.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-14 08:00 | 2014-02-05 17:00 |  | 2013-11-17 08:00 | 2013-12-09 17:00 | 2013-11-17 08:00 | 2013-12-09 17:00 | 2013-11-17 08:00 | 2013-12-09 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 |  | PT_Normal |  |  |  |  | 3NaLkpl9Re+6V6vwyAjVYA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30610 | N | N | 10 | GROUND FLOOR |  | 125250 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 977.6 | LABOR- SUBCONTRACTOR
%R | 503669 | 6359 | 125252 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ACGF4605 | Fixing of Ventilation Equipments | 8178 | 256 | 0 | 200 | 0 | 182.4 | 182.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-17 08:00 | 2014-03-17 17:00 |  | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-01-09 08:00 | 2014-02-06 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 |  | PT_Normal |  |  |  |  | FRRxGbIWQiOZeu8T66os9A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30610 | N | N | 10 | GROUND FLOOR |  | 125250 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 182.4 | LABOR- SUBCONTRACTOR
%R | 503670 | 6359 | 125252 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ACGF4610 | Fixing of Split AC | 8178 | 256 | 40 | 160 | 0 | 296 | 296 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-10 08:00 | 2014-04-01 17:00 |  | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-03-10 08:00 | 2014-04-01 17:00 |  | PT_Normal |  |  |  |  | HqvZUQF6QgOa8lHjoqgOiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30610 | N | N | 10 | GROUND FLOOR |  | 125250 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 296 | LABOR- SUBCONTRACTOR
%R | 503671 | 6359 | 125253 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ACFF4615 | Installation AC Pipes | 8178 | 216 | 40 | 160 | 0 | 977.6 | 977.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-02 08:00 | 2014-02-25 17:00 |  | 2014-01-01 08:00 | 2014-01-23 17:00 | 2014-01-01 08:00 | 2014-01-23 17:00 | 2014-01-01 08:00 | 2014-01-23 17:00 | 2014-02-02 08:00 | 2014-02-25 17:00 |  | PT_Normal |  |  |  |  | NNZbcqFDQk2HPg2PKYWRtQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30620 | N | N | 15 | FIRST FLOORS |  | 125250 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 977.6 | LABOR- SUBCONTRACTOR
%R | 503672 | 6359 | 125253 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ACFF4620 | Fixing of Ventilation Equipments | 8178 | 16 | 0 | 200 | 0 | 113.6 | 113.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-22 17:00 |  | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | 0oTl4muJSXWhei+wnb14rg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30620 | N | N | 15 | FIRST FLOORS |  | 125250 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 56.8 | LABOR- SUBCONTRACTOR
%R | 503673 | 6359 | 125253 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2ACFF4625 | Fixing of Split AC | 8178 | 16 | 0 | 160 | 0 | 296 | 296 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-15 08:00 | 2014-04-06 17:00 |  | 2014-03-12 08:00 | 2014-04-03 17:00 | 2014-03-12 08:00 | 2014-04-03 17:00 | 2014-03-12 08:00 | 2014-04-03 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | igXnBNrlQZKeV730snaQdg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30620 | N | N | 15 | FIRST FLOORS |  | 125250 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 296 | LABOR- SUBCONTRACTOR
%R | 503674 | 6359 | 125255 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 448 | 240 | 120 | 0 | 110.4 | 110.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-06 08:00 | 2014-03-23 17:00 |  | 2013-12-30 08:00 | 2014-01-15 17:00 | 2013-12-30 08:00 | 2014-01-15 17:00 | 2013-12-30 08:00 | 2014-01-15 17:00 | 2014-03-06 08:00 | 2014-03-23 17:00 |  | PT_Normal |  |  |  |  | cUl5dueMS9KmJ0YJhedgWw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30590 | N | N | 20 | ROOF |  | 125254 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 110.4 | LABOR- SUBCONTRACTOR
%R | 503675 | 6359 | 125255 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2PLRF4350 | Installation of Rain water Pipes | 8178 | 208 | 80 | 120 | 0 | 67.2 | 67.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-16 08:00 | 2014-04-01 17:00 |  | 2014-02-13 08:00 | 2014-03-02 17:00 | 2014-02-13 08:00 | 2014-03-02 17:00 | 2014-02-13 08:00 | 2014-03-02 17:00 | 2014-03-16 08:00 | 2014-04-01 17:00 |  | PT_Normal |  |  |  |  | ovVqQAOXRHmog/P1c/2X8Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30590 | N | N | 20 | ROOF |  | 125254 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 503676 | 6359 | 125255 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 8 | 0 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-19 17:00 |  | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | btm3CoM2RFOS8vc4dZgSFA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30590 | N | N | 20 | ROOF |  | 125254 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 336 | LABOR- SUBCONTRACTOR
%R | 503677 | 6359 | 125256 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 0 | 0 | 144 | 0 | 441.6 | 441.6 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-10 08:00 | 2013-12-31 17:00 |  | 2013-12-10 08:00 | 2013-12-31 17:00 | 2013-12-10 08:00 | 2013-12-31 17:00 | 2013-12-10 08:00 | 2013-12-31 17:00 | 2013-12-10 08:00 | 2013-12-31 17:00 |  | PT_Normal |  |  |  |  | qcZkDzVoTXqck0BCkyK1OA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30580 | N | N | 15 | FIRST FLOORS |  | 125254 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 441.6 | LABOR- SUBCONTRACTOR
%R | 503678 | 6359 | 125256 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2PLFF4330 | Installation of Drainage pipes & testing | 8178 | 176 | 56 | 144 | 0 | 177.6 | 177.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-06 08:00 | 2014-01-26 17:00 |  | 2013-12-10 08:00 | 2013-12-31 17:00 | 2013-12-10 08:00 | 2013-12-31 17:00 | 2013-12-10 08:00 | 2013-12-31 17:00 | 2014-01-06 08:00 | 2014-01-26 17:00 |  | PT_Normal |  |  |  |  | A9gz26L7TG2MokYWFT+mqw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30580 | N | N | 15 | FIRST FLOORS |  | 125254 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 177.6 | LABOR- SUBCONTRACTOR
%R | 503679 | 6359 | 125256 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2PLFF4335 | Sanitary Fittings & Accessories | 8178 | 40 | 0 | 160 | 0 | 67.2 | 67.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-04 08:00 | 2014-03-26 17:00 |  | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-03-04 08:00 | 2014-03-26 17:00 |  | PT_Normal |  |  |  |  | uuQw/8PkSQq2ZbSqjMkavQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30580 | N | N | 15 | FIRST FLOORS |  | 125254 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 503680 | 6359 | 125256 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2PLFF4340 | Installation of Water Heater | 8178 | 40 | 32 | 120 | 0 | 67.2 | 67.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-16 08:00 | 2014-04-01 17:00 |  | 2014-03-10 08:00 | 2014-03-26 17:00 | 2014-03-10 08:00 | 2014-03-26 17:00 | 2014-03-10 08:00 | 2014-03-26 17:00 | 2014-03-16 08:00 | 2014-04-01 17:00 |  | PT_Normal |  |  |  |  | iY+6vJ3dT06k8n1OBTvgcw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30580 | N | N | 15 | FIRST FLOORS |  | 125254 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 503681 | 6359 | 125257 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 144 | 0 | 144 | 0 | 441.6 | 441.6 | 144 | 0 | 0 | 0 |  |  |  | 2013-11-18 08:00 | 2013-12-08 17:00 |  | 2013-10-28 08:00 | 2013-11-17 17:00 | 2013-10-28 08:00 | 2013-11-17 17:00 | 2013-10-28 08:00 | 2013-11-17 17:00 | 2013-11-18 08:00 | 2013-12-08 17:00 |  | PT_Normal |  |  |  |  | 2dXBipqES42Zw06srBkxZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30570 | N | N | 10 | GROUND FLOOR |  | 125254 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 441.6 | LABOR- SUBCONTRACTOR
%R | 503682 | 6359 | 125257 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2PLGF4310 | Installation of Drainage pipes &testing | 8178 | 312 | 104 | 144 | 0 | 177.6 | 177.6 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-12 08:00 | 2014-01-02 17:00 |  | 2013-10-28 08:00 | 2013-11-17 17:00 | 2013-10-28 08:00 | 2013-11-17 17:00 | 2013-10-28 08:00 | 2013-11-17 17:00 | 2013-12-12 08:00 | 2014-01-02 17:00 |  | PT_Normal |  |  |  |  | 4NnnGOz2REWQJqIoeJFt6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30570 | N | N | 10 | GROUND FLOOR |  | 125254 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 177.6 | LABOR- SUBCONTRACTOR
%R | 503683 | 6359 | 125257 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2PLGF4315 | Sanitary Fittings & Accessories | 8178 | 360 | 0 | 160 | 0 | 134.4 | 134.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-13 17:00 |  | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-03-22 08:00 | 2014-04-13 17:00 |  | PT_Normal |  |  |  |  | 5BLJgGreTf6HLSSlPZXRyg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30570 | N | N | 10 | GROUND FLOOR |  | 125254 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 503684 | 6359 | 125257 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2PLGF4320 | Installation of Water Heater | 8178 | 360 | 80 | 120 | 0 | 134.4 | 134.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-02 08:00 | 2014-04-19 17:00 |  | 2014-02-08 08:00 | 2014-02-25 17:00 | 2014-02-08 08:00 | 2014-02-25 17:00 | 2014-02-08 08:00 | 2014-02-25 17:00 | 2014-04-02 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | oMXxLn+6QhuuUKnpSbko+w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30570 | N | N | 10 | GROUND FLOOR |  | 125254 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 503685 | 6359 | 125257 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 0 | 0 | 128 | 0 | 67.2 | 67.2 | 128 | 0 | 0 | 0 |  |  |  | 2013-07-02 08:00 | 2013-07-20 17:00 |  | 2013-07-02 08:00 | 2013-07-20 17:00 | 2013-07-02 08:00 | 2013-07-20 17:00 | 2013-07-02 08:00 | 2013-07-20 17:00 | 2013-07-02 08:00 | 2013-07-20 17:00 |  | PT_Normal |  |  |  |  | c8loucv9QIyor15fNLCswg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30570 | N | N | 10 | GROUND FLOOR |  | 125254 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 503686 | 6359 | 125260 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STRF2040 | Column-Rebar & Formwork | 8165 | 176 | 0 | 144 | 0 | 1205.75 | 1205.75 | 144 | 0 | 0 | 0 |  |  |  | 2013-11-21 08:00 | 2013-12-11 17:00 |  | 2013-10-27 08:00 | 2013-11-16 17:00 | 2013-10-27 08:00 | 2013-11-16 17:00 | 2013-10-27 08:00 | 2013-11-16 17:00 | 2013-11-21 08:00 | 2013-12-11 17:00 |  | PT_Normal |  |  |  |  | eAzBLATiRs28TEbM+Jc+0A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30420 | N | N | 20 | ROOF |  | 125259 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1205.75 | STEEL FIXERS SK
%R | 503687 | 6359 | 125260 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STRF2045 | Column-Concrete | 8167 | 256 | 0 | 136 | 0 | 52.5 | 52.5 | 136 | 0 | 0 | 0 |  |  |  | 2013-12-07 08:00 | 2013-12-26 17:00 |  | 2013-10-30 08:00 | 2013-11-18 17:00 | 2013-10-30 08:00 | 2013-11-18 17:00 | 2013-10-30 08:00 | 2013-11-18 17:00 | 2013-12-07 08:00 | 2013-12-26 17:00 |  | PT_Normal |  |  |  |  | ap3J+vtWSoS2G1IS20o2Cw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30420 | N | N | 20 | ROOF |  | 125259 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 52.5 | CONCRETE MASON SK
%R | 503688 | 6359 | 125260 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STRF2050 | Slab-Rebar & Formwork - Head Room | 8165 | 256 | 0 | 160 | 0 | 2735.25 | 2735.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-09 08:00 | 2014-01-01 17:00 |  | 2013-11-02 08:00 | 2013-11-24 17:00 | 2013-11-02 08:00 | 2013-11-24 17:00 | 2013-11-02 08:00 | 2013-11-24 17:00 | 2013-12-09 08:00 | 2014-01-01 17:00 |  | PT_Normal |  |  |  |  | oor9vev+QRymCDpRR5bRfA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30420 | N | N | 20 | ROOF |  | 125259 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 2735.25 | STEEL FIXERS SK
%R | 503689 | 6359 | 125260 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STRF2055 | Slab-Concrete-Head room | 8167 | 256 | 0 | 104 | 0 | 252 | 252 | 104 | 0 | 0 | 0 |  |  |  | 2013-12-21 08:00 | 2014-01-04 17:00 |  | 2013-11-12 08:00 | 2013-11-26 17:00 | 2013-11-12 08:00 | 2013-11-26 17:00 | 2013-11-12 08:00 | 2013-11-26 17:00 | 2013-12-21 08:00 | 2014-01-04 17:00 |  | PT_Normal |  |  |  |  | GQ+7QZmhQV6bl3CnS6YkTA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30420 | N | N | 20 | ROOF |  | 125259 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 252 | CONCRETE MASON SK
%R | 503690 | 6359 | 125260 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STRF2060 | Construction of Parapets | 8168 | 448 | 32 | 200 | 0 | 2200 | 2200 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-20 08:00 | 2014-02-18 17:00 |  | 2013-11-14 08:00 | 2013-12-12 17:00 | 2013-11-14 08:00 | 2013-12-12 17:00 | 2013-11-14 08:00 | 2013-12-12 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 |  | PT_Normal |  |  |  |  | nV30GpiNTau8LRgh73QMBQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30420 | N | N | 20 | ROOF |  | 125259 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 2200 | BLOCK MASON SK
%R | 503691 | 6359 | 125260 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STRF2065 | Construction of up stands/Plinth | 8165 | 416 | 0 | 200 | 0 | 554.75 | 554.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-26 08:00 | 2014-02-24 17:00 |  | 2013-11-25 08:00 | 2013-12-24 17:00 | 2013-11-25 08:00 | 2013-12-24 17:00 | 2013-11-25 08:00 | 2013-12-24 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 |  | PT_Normal |  |  |  |  | MVhyihdWRbWisNKDn5t/rA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30420 | N | N | 20 | ROOF |  | 125259 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 554.75 | STEEL FIXERS SK
%R | 503692 | 6359 | 125261 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STFF2020 | Column-Rebar & Formwork | 8165 | 16 | 0 | 200 | 0 | 3580.5 | 3580.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-14 08:00 | 2013-10-12 17:00 |  | 2013-09-11 08:00 | 2013-10-09 17:00 | 2013-09-11 08:00 | 2013-10-09 17:00 | 2013-09-11 08:00 | 2013-10-09 17:00 | 2013-09-14 08:00 | 2013-10-12 17:00 |  | PT_Normal |  |  |  |  | jLGBmmBuQGOXnMxIxTDISw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30410 | N | N | 15 | FIRST FLOORS |  | 125259 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 3580.5 | STEEL FIXERS SK
%R | 503693 | 6359 | 125261 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STFF2025 | Column-Concrete | 8167 | 32 | 0 | 192 | 0 | 224 | 224 | 192 | 0 | 0 | 0 |  |  |  | 2013-09-25 08:00 | 2013-10-24 17:00 |  | 2013-09-21 08:00 | 2013-10-20 17:00 | 2013-09-21 08:00 | 2013-10-20 17:00 | 2013-09-21 08:00 | 2013-10-20 17:00 | 2013-09-25 08:00 | 2013-10-24 17:00 |  | PT_Normal |  |  |  |  | gbM3x+M/Q5WWC691+1g72A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30410 | N | N | 15 | FIRST FLOORS |  | 125259 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 224 | CONCRETE MASON SK
%R | 503694 | 6359 | 125261 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 32 | 0 | 200 | 0 | 16119.25 | 16119.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2013-11-10 17:00 |  | 2013-10-06 08:00 | 2013-11-05 17:00 | 2013-10-06 08:00 | 2013-11-05 17:00 | 2013-10-06 08:00 | 2013-11-05 17:00 | 2013-10-10 08:00 | 2013-11-10 17:00 |  | PT_Normal |  |  |  |  | q0X3TZBFTYmd0k9j0Z7zqA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30410 | N | N | 15 | FIRST FLOORS |  | 125259 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 16119.25 | STEEL FIXERS SK
%R | 503695 | 6359 | 125261 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 32 | 0 | 112 | 0 | 1141 | 1141 | 112 | 0 | 0 | 0 |  |  |  | 2013-10-29 08:00 | 2013-11-13 17:00 |  | 2013-10-24 08:00 | 2013-11-09 17:00 | 2013-10-24 08:00 | 2013-11-09 17:00 | 2013-10-24 08:00 | 2013-11-09 17:00 | 2013-10-29 08:00 | 2013-11-13 17:00 |  | PT_Normal |  |  |  |  | cZD5uBOyQv26Nx0XewUAYw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30410 | N | N | 15 | FIRST FLOORS |  | 125259 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1141 | CONCRETE MASON SK
%R | 503696 | 6359 | 125262 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STGF2000 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 4046 | 4046 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-28 08:00 | 2013-08-28 17:00 |  | 2013-07-28 08:00 | 2013-08-28 17:00 | 2013-07-28 08:00 | 2013-08-28 17:00 | 2013-07-28 08:00 | 2013-08-28 17:00 | 2013-07-28 08:00 | 2013-08-28 17:00 |  | PT_Normal |  |  |  |  | UZC+nqzDTQaSPHoZ30Db3w |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30400 | N | N | 10 | GROUND FLOOR |  | 125259 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 2023 | STEEL FIXERS SK
%R | 503697 | 6359 | 125262 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STGF2005 | Column-Concrete | 8167 | 16 | 0 | 192 | 0 | 255.5 | 255.5 | 192 | 0 | 0 | 0 |  |  |  | 2013-08-07 08:00 | 2013-09-07 17:00 |  | 2013-08-05 08:00 | 2013-09-04 17:00 | 2013-08-05 08:00 | 2013-09-04 17:00 | 2013-08-05 08:00 | 2013-09-04 17:00 | 2013-08-07 08:00 | 2013-09-07 17:00 |  | PT_Normal |  |  |  |  | THsUvl2mR8KZv/jddwG1UQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30400 | N | N | 10 | GROUND FLOOR |  | 125259 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 255.5 | CONCRETE MASON SK
%R | 503698 | 6359 | 125262 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 16 | 0 | 200 | 0 | 16829.75 | 16829.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-26 08:00 | 2013-09-23 17:00 |  | 2013-08-24 08:00 | 2013-09-21 17:00 | 2013-08-24 08:00 | 2013-09-21 17:00 | 2013-08-24 08:00 | 2013-09-21 17:00 | 2013-08-26 08:00 | 2013-09-23 17:00 |  | PT_Normal |  |  |  |  | 6E7rL7HGS7u3waXqu4KXvg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30400 | N | N | 10 | GROUND FLOOR |  | 125259 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 16829.75 | STEEL FIXERS SK
%R | 503699 | 6359 | 125262 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 16 | 0 | 112 | 0 | 1295 | 1295 | 112 | 0 | 0 | 0 |  |  |  | 2013-09-11 08:00 | 2013-09-26 17:00 |  | 2013-09-09 08:00 | 2013-09-24 17:00 | 2013-09-09 08:00 | 2013-09-24 17:00 | 2013-09-09 08:00 | 2013-09-24 17:00 | 2013-09-11 08:00 | 2013-09-26 17:00 |  | PT_Normal |  |  |  |  | pDK90rPcSJKzyfSwfCHnEw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30400 | N | N | 10 | GROUND FLOOR |  | 125259 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 1295 | CONCRETE MASON SK
%R | 503700 | 6359 | 125264 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STUG1015 | Footing Waterproofing & Screed | 8164 | 0 | 0 | 200 | 0 | 574.75 | 574.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-04-06 08:00 | 2013-05-04 17:00 |  | 2013-04-06 08:00 | 2013-05-04 17:00 | 2013-04-06 08:00 | 2013-05-04 17:00 | 2013-04-06 08:00 | 2013-05-04 17:00 | 2013-04-06 08:00 | 2013-05-04 17:00 |  | PT_Normal |  |  |  |  | vSq2WQ58QEGJDJxDH92axg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30380 | N | N | 10 | UPTO GRADE SLAB |  | 125263 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 574.75 | SCREED MASON SK
%R | 503701 | 6359 | 125264 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STUG1020 | Construction of foundations | 8165 | 0 | 0 | 160 | 0 | 7778.75 | 7778.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-04-21 08:00 | 2013-05-13 17:00 |  | 2013-04-21 08:00 | 2013-05-13 17:00 | 2013-04-21 08:00 | 2013-05-13 17:00 | 2013-04-21 08:00 | 2013-05-13 17:00 | 2013-04-21 08:00 | 2013-05-13 17:00 |  | PT_Normal |  |  |  |  | GbavQCDSTyeDRDJWIRR2lg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30380 | N | N | 10 | UPTO GRADE SLAB |  | 125263 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 7778.75 | STEEL FIXERS SK
%R | 503702 | 6359 | 125264 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STUG1025 | Construction of neck of columns | 8165 | 0 | 0 | 200 | 0 | 1606.5 | 1606.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-04-30 08:00 | 2013-05-28 17:00 |  | 2013-04-30 08:00 | 2013-05-28 17:00 | 2013-04-30 08:00 | 2013-05-28 17:00 | 2013-04-30 08:00 | 2013-05-28 17:00 | 2013-04-30 08:00 | 2013-05-28 17:00 |  | PT_Normal |  |  |  |  | K+ra7NupT3ac/YpUiQKdXA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30380 | N | N | 10 | UPTO GRADE SLAB |  | 125263 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 1606.5 | STEEL FIXERS SK
%R | 503703 | 6359 | 125264 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STUG1030 | Waterproofing Footing & Neck Column | 8178 | 0 | 0 | 200 | 0 | 516 | 516 | 200 | 0 | 0 | 0 |  |  |  | 2013-05-09 08:00 | 2013-06-06 17:00 |  | 2013-05-09 08:00 | 2013-06-06 17:00 | 2013-05-09 08:00 | 2013-06-06 17:00 | 2013-05-09 08:00 | 2013-06-06 17:00 | 2013-05-09 08:00 | 2013-06-06 17:00 |  | PT_Normal |  |  |  |  | BAKRg0w2Toi23lHqAJh/Yg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30380 | N | N | 10 | UPTO GRADE SLAB |  | 125263 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 516 | LABOR- SUBCONTRACTOR
%R | 503704 | 6359 | 125264 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 0 | 0 | 200 | 0 | 1041 | 1041 | 200 | 825 | 0 | 825 |  |  |  | 2013-05-23 08:00 | 2013-06-20 17:00 |  | 2013-05-23 08:00 | 2013-06-20 17:00 | 2013-05-23 08:00 | 2013-06-20 17:00 | 2013-05-23 08:00 | 2013-06-20 17:00 | 2013-05-23 08:00 | 2013-06-20 17:00 |  | PT_Normal |  |  |  |  | jeM5CRGZR2SIRXXlN+Fyug |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30380 | N | N | 10 | UPTO GRADE SLAB |  | 125263 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 1041 | LABOR - CIVIL
%R | 503705 | 6359 | 125264 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STUG1040 | Construction of Grade Beams | 8163 | 0 | 0 | 200 | 0 | 7568.75 | 7568.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-09 08:00 | 2013-07-07 17:00 |  | 2013-06-09 08:00 | 2013-07-07 17:00 | 2013-06-09 08:00 | 2013-07-07 17:00 | 2013-06-09 08:00 | 2013-07-07 17:00 | 2013-06-09 08:00 | 2013-07-07 17:00 |  | PT_Normal |  |  |  |  | vSDBJenRSvOEHEEd+1Kgng |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30380 | N | N | 10 | UPTO GRADE SLAB |  | 125263 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 7568.75 | BLINDING MASON SK
%R | 503706 | 6359 | 125264 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STUG1045 | Construction of slab on grade | 8163 | 0 | 0 | 200 | 0 | 4422 | 4422 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-11 08:00 | 2013-08-08 17:00 |  | 2013-07-11 08:00 | 2013-08-08 17:00 | 2013-07-11 08:00 | 2013-08-08 17:00 | 2013-07-11 08:00 | 2013-08-08 17:00 | 2013-07-11 08:00 | 2013-08-08 17:00 |  | PT_Normal |  |  |  |  | Df2gypEbSPaSGIN+VyvY5g |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30380 | N | N | 10 | UPTO GRADE SLAB |  | 125263 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 4422 | BLINDING MASON SK
%R | 503707 | 6359 | 125264 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STUG1010 | Footing Blinding | 8163 | 0 | 0 | 184 | 0 | 794.5 | 794.5 | 184 | 0 | 0 | 0 |  |  |  | 2013-03-31 08:00 | 2013-04-25 17:00 |  | 2013-03-31 08:00 | 2013-04-25 17:00 | 2013-03-31 08:00 | 2013-04-25 17:00 | 2013-03-31 08:00 | 2013-04-25 17:00 | 2013-03-31 08:00 | 2013-04-25 17:00 |  | PT_Normal |  |  |  |  | 66ynmllSQS2Fr7V1QVeg9A |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30380 | N | N | 10 | UPTO GRADE SLAB |  | 125263 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 794.5 | BLINDING MASON SK
%R | 503708 | 6359 | 125264 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STUG1000 | Footing Excavation | 8177 | 0 | 0 | 200 | 0 | 1114 | 1114 | 200 | 524 | 0 | 524 |  |  |  | 2013-03-16 08:00 | 2013-04-13 17:00 |  | 2013-03-16 08:00 | 2013-04-13 17:00 | 2013-03-16 08:00 | 2013-04-13 17:00 | 2013-03-16 08:00 | 2013-04-13 17:00 | 2013-03-16 08:00 | 2013-04-13 17:00 |  | PT_Normal |  |  |  |  | eYZK1Aa6Ro+aFt3z6Iayeg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30380 | N | N | 10 | UPTO GRADE SLAB |  | 125263 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 1114 | LABOR - CIVIL
%R | 503709 | 6359 | 125264 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ2STUG1005 | Footing Antitermite | 8178 | 0 | 0 | 184 | 0 | 1584 | 1584 | 184 | 0 | 0 | 0 |  |  |  | 2013-03-27 08:00 | 2013-04-22 17:00 |  | 2013-03-27 08:00 | 2013-04-22 17:00 | 2013-03-27 08:00 | 2013-04-22 17:00 | 2013-03-27 08:00 | 2013-04-22 17:00 | 2013-03-27 08:00 | 2013-04-22 17:00 |  | PT_Normal |  |  |  |  | JyX6O4RITMeGXG9QQt7gsg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30380 | N | N | 10 | UPTO GRADE SLAB |  | 125263 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP03 |  | 1584 | LABOR- SUBCONTRACTOR
%R | 503710 | 6359 | 125268 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STUG1000 | Footing Excavation | 8177 | 0 | 0 | 200 | 0 | 1114 | 1114 | 200 | 524 | 0 | 524 |  |  |  | 2013-04-14 08:00 | 2013-05-12 17:00 |  | 2013-04-14 08:00 | 2013-05-12 17:00 | 2013-04-14 08:00 | 2013-05-12 17:00 | 2013-04-14 08:00 | 2013-05-12 17:00 | 2013-04-14 08:00 | 2013-05-12 17:00 |  | PT_Normal |  |  |  |  | f0GndhlhQUmJy3on4ISgjQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30740 | N | N | 10 | UPTO GRADE SLAB |  | 125267 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 1114 | LABOR - CIVIL
%R | 503711 | 6359 | 125268 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STUG1005 | Footing Antitermite | 8178 | 0 | 0 | 184 | 0 | 1584 | 1584 | 184 | 0 | 0 | 0 |  |  |  | 2013-04-25 08:00 | 2013-05-21 17:00 |  | 2013-04-25 08:00 | 2013-05-21 17:00 | 2013-04-25 08:00 | 2013-05-21 17:00 | 2013-04-25 08:00 | 2013-05-21 17:00 | 2013-04-25 08:00 | 2013-05-21 17:00 |  | PT_Normal |  |  |  |  | PSvMdeGvSnCp5A5Y7vN0AQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30740 | N | N | 10 | UPTO GRADE SLAB |  | 125267 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 1584 | LABOR- SUBCONTRACTOR
%R | 503712 | 6359 | 125268 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STUG1010 | Footing Blinding | 8163 | 0 | 0 | 184 | 0 | 794.5 | 794.5 | 184 | 0 | 0 | 0 |  |  |  | 2013-04-29 08:00 | 2013-05-25 17:00 |  | 2013-04-29 08:00 | 2013-05-25 17:00 | 2013-04-29 08:00 | 2013-05-25 17:00 | 2013-04-29 08:00 | 2013-05-25 17:00 | 2013-04-29 08:00 | 2013-05-25 17:00 |  | PT_Normal |  |  |  |  | 3dZ/XnOgRnyJ5w2YppqxtQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30740 | N | N | 10 | UPTO GRADE SLAB |  | 125267 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP04 |  | 794.5 | BLINDING MASON SK
%R | 503713 | 6359 | 125268 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STUG1015 | Footing Waterproofing & Screed | 8164 | 0 | 0 | 200 | 0 | 574.75 | 574.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-05-05 08:00 | 2013-06-02 17:00 |  | 2013-05-05 08:00 | 2013-06-02 17:00 | 2013-05-05 08:00 | 2013-06-02 17:00 | 2013-05-05 08:00 | 2013-06-02 17:00 | 2013-05-05 08:00 | 2013-06-02 17:00 |  | PT_Normal |  |  |  |  | legGpvCWTx6IeN4FKvFJpw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30740 | N | N | 10 | UPTO GRADE SLAB |  | 125267 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 574.75 | SCREED MASON SK
%R | 503714 | 6359 | 125268 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STUG1020 | Construction of foundations | 8165 | 0 | 0 | 160 | 0 | 7778.75 | 7778.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-05-20 08:00 | 2013-06-11 17:00 |  | 2013-05-20 08:00 | 2013-06-11 17:00 | 2013-05-20 08:00 | 2013-06-11 17:00 | 2013-05-20 08:00 | 2013-06-11 17:00 | 2013-05-20 08:00 | 2013-06-11 17:00 |  | PT_Normal |  |  |  |  | jUJz4uehQPaWtK/d0a+z8g |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30740 | N | N | 10 | UPTO GRADE SLAB |  | 125267 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 7778.75 | STEEL FIXERS SK
%R | 503715 | 6359 | 125268 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STUG1025 | Construction of neck of columns | 8165 | 0 | 0 | 200 | 0 | 1606.5 | 1606.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-05-29 08:00 | 2013-06-26 17:00 |  | 2013-05-29 08:00 | 2013-06-26 17:00 | 2013-05-29 08:00 | 2013-06-26 17:00 | 2013-05-29 08:00 | 2013-06-26 17:00 | 2013-05-29 08:00 | 2013-06-26 17:00 |  | PT_Normal |  |  |  |  | P2/1/MmmTqS19Z0RQjTZ8Q |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30740 | N | N | 10 | UPTO GRADE SLAB |  | 125267 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP05 |  | 1606.5 | STEEL FIXERS SK
%R | 503716 | 6359 | 125268 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STUG1030 | Waterproofing Footing & Neck Column | 8178 | 0 | 0 | 200 | 0 | 516 | 516 | 200 | 0 | 0 | 0 |  |  |  | 2013-06-08 08:00 | 2013-07-06 17:00 |  | 2013-06-08 08:00 | 2013-07-06 17:00 | 2013-06-08 08:00 | 2013-07-06 17:00 | 2013-06-08 08:00 | 2013-07-06 17:00 | 2013-06-08 08:00 | 2013-07-06 17:00 |  | PT_Normal |  |  |  |  | fK2HChL4SdeUYbp2JPNqIw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30740 | N | N | 10 | UPTO GRADE SLAB |  | 125267 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 516 | LABOR- SUBCONTRACTOR
%R | 503717 | 6359 | 125268 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 0 | 0 | 200 | 0 | 1041 | 1041 | 200 | 825 | 0 | 825 |  |  |  | 2013-06-22 08:00 | 2013-07-20 17:00 |  | 2013-06-22 08:00 | 2013-07-20 17:00 | 2013-06-22 08:00 | 2013-07-20 17:00 | 2013-06-22 08:00 | 2013-07-20 17:00 | 2013-06-22 08:00 | 2013-07-20 17:00 |  | PT_Normal |  |  |  |  | 4zz7e9/fTyuWv46EpxPf1g |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30740 | N | N | 10 | UPTO GRADE SLAB |  | 125267 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 1041 | LABOR - CIVIL
%R | 503718 | 6359 | 125268 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STUG1040 | Construction of Grade Beams | 8163 | 0 | 0 | 200 | 0 | 7568.75 | 7568.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-08 08:00 | 2013-08-05 17:00 |  | 2013-07-08 08:00 | 2013-08-05 17:00 | 2013-07-08 08:00 | 2013-08-05 17:00 | 2013-07-08 08:00 | 2013-08-05 17:00 | 2013-07-08 08:00 | 2013-08-05 17:00 |  | PT_Normal |  |  |  |  | bVaS04BjRFmgit2DP7S0dA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30740 | N | N | 10 | UPTO GRADE SLAB |  | 125267 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 7568.75 | BLINDING MASON SK
%R | 503719 | 6359 | 125268 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STUG1045 | Construction of slab on grade | 8163 | 0 | 0 | 200 | 0 | 4422 | 4422 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-13 08:00 | 2013-09-10 17:00 |  | 2013-08-13 08:00 | 2013-09-10 17:00 | 2013-08-13 08:00 | 2013-09-10 17:00 | 2013-08-13 08:00 | 2013-09-10 17:00 | 2013-08-13 08:00 | 2013-09-10 17:00 |  | PT_Normal |  |  |  |  | zS8nUAaiQLmrwJ5B3a1kfA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30740 | N | N | 10 | UPTO GRADE SLAB |  | 125267 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 4422 | BLINDING MASON SK
%R | 503720 | 6359 | 125270 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STRF2040 | Column-Rebar & Formwork | 8165 | 120 | 0 | 144 | 0 | 1205.75 | 1205.75 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-12 08:00 | 2014-01-02 17:00 |  | 2013-11-25 08:00 | 2013-12-15 17:00 | 2013-11-25 08:00 | 2013-12-15 17:00 | 2013-11-25 08:00 | 2013-12-15 17:00 | 2013-12-12 08:00 | 2014-01-02 17:00 |  | PT_Normal |  |  |  |  | 7S0qxzI6SRShCBTA8BwG4Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30780 | N | N | 20 | ROOF |  | 125269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1205.75 | STEEL FIXERS SK
%R | 503721 | 6359 | 125270 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STRF2045 | Column-Concrete | 8167 | 160 | 0 | 136 | 0 | 52.5 | 52.5 | 136 | 0 | 0 | 0 |  |  |  | 2013-12-23 08:00 | 2014-01-11 17:00 |  | 2013-11-28 08:00 | 2013-12-17 17:00 | 2013-11-28 08:00 | 2013-12-17 17:00 | 2013-11-28 08:00 | 2013-12-17 17:00 | 2013-12-23 08:00 | 2014-01-11 17:00 |  | PT_Normal |  |  |  |  | WbDdnzxJQP6nSTUVHWwNLQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30780 | N | N | 20 | ROOF |  | 125269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 52.5 | CONCRETE MASON SK
%R | 503722 | 6359 | 125270 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STRF2050 | Slab-Rebar & Formwork - Head Room | 8165 | 160 | 0 | 160 | 0 | 2735.25 | 2735.25 | 160 | 0 | 0 | 0 |  |  |  | 2013-12-25 08:00 | 2014-01-16 17:00 |  | 2013-12-01 08:00 | 2013-12-24 17:00 | 2013-12-01 08:00 | 2013-12-24 17:00 | 2013-12-01 08:00 | 2013-12-24 17:00 | 2013-12-25 08:00 | 2014-01-16 17:00 |  | PT_Normal |  |  |  |  | ibAqghLPSRClBZDfSFIR7Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30780 | N | N | 20 | ROOF |  | 125269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 2735.25 | STEEL FIXERS SK
%R | 503723 | 6359 | 125270 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STRF2055 | Slab-Concrete-Head room | 8167 | 160 | 0 | 104 | 0 | 252 | 252 | 104 | 0 | 0 | 0 |  |  |  | 2014-01-05 08:00 | 2014-01-19 17:00 |  | 2013-12-11 08:00 | 2013-12-26 17:00 | 2013-12-11 08:00 | 2013-12-26 17:00 | 2013-12-11 08:00 | 2013-12-26 17:00 | 2014-01-05 08:00 | 2014-01-19 17:00 |  | PT_Normal |  |  |  |  | CicNjThQSQi6hdP7n04Xag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30780 | N | N | 20 | ROOF |  | 125269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 252 | CONCRETE MASON SK
%R | 503724 | 6359 | 125270 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STRF2060 | Construction of Parapets | 8168 | 448 | 32 | 200 | 0 | 2200 | 2200 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-19 08:00 | 2014-03-19 17:00 |  | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2013-12-14 08:00 | 2014-01-12 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 |  | PT_Normal |  |  |  |  | D3XTaNI+T9KeihM5s4lC1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30780 | N | N | 20 | ROOF |  | 125269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 2200 | BLOCK MASON SK
%R | 503725 | 6359 | 125270 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STRF2065 | Construction of up stands/Plinth | 8165 | 416 | 0 | 200 | 0 | 554.75 | 554.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-25 08:00 | 2014-03-25 17:00 |  | 2013-12-25 08:00 | 2014-01-22 17:00 | 2013-12-25 08:00 | 2014-01-22 17:00 | 2013-12-25 08:00 | 2014-01-22 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 |  | PT_Normal |  |  |  |  | clIKHav5TLaOBiteWgbxjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30780 | N | N | 20 | ROOF |  | 125269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 554.75 | STEEL FIXERS SK
%R | 503726 | 6359 | 125271 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STGF2000 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 4046 | 4046 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-29 08:00 | 2013-09-26 17:00 |  | 2013-08-29 08:00 | 2013-09-26 17:00 | 2013-08-29 08:00 | 2013-09-26 17:00 | 2013-08-29 08:00 | 2013-09-26 17:00 | 2013-08-29 08:00 | 2013-09-26 17:00 |  | PT_Normal |  |  |  |  | MwqncgrZSXGb01zqODyV5w |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30760 | N | N | 10 | GROUND FLOOR |  | 125269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 4046 | STEEL FIXERS SK
%R | 503727 | 6359 | 125271 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STGF2005 | Column-Concrete | 8167 | 16 | 0 | 192 | 0 | 255.5 | 255.5 | 192 | 0 | 0 | 0 |  |  |  | 2013-09-09 08:00 | 2013-10-06 17:00 |  | 2013-09-07 08:00 | 2013-10-03 17:00 | 2013-09-07 08:00 | 2013-10-03 17:00 | 2013-09-07 08:00 | 2013-10-03 17:00 | 2013-09-09 08:00 | 2013-10-06 17:00 |  | PT_Normal |  |  |  |  | HZXVw5YpT4CeogpjBdqj2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30760 | N | N | 10 | GROUND FLOOR |  | 125269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 255.5 | CONCRETE MASON SK
%R | 503728 | 6359 | 125271 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 16 | 0 | 200 | 0 | 16829.75 | 16829.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-24 08:00 | 2013-10-24 17:00 |  | 2013-09-22 08:00 | 2013-10-22 17:00 | 2013-09-22 08:00 | 2013-10-22 17:00 | 2013-09-22 08:00 | 2013-10-22 17:00 | 2013-09-24 08:00 | 2013-10-24 17:00 |  | PT_Normal |  |  |  |  | 6jjumV9NSRqiC+GtZWIhYQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30760 | N | N | 10 | GROUND FLOOR |  | 125269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09; period 2: 2013-AP10 |  | 8414.875 | STEEL FIXERS SK
%R | 503729 | 6359 | 125271 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 16 | 0 | 112 | 0 | 1295 | 1295 | 112 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2013-10-28 17:00 |  | 2013-10-08 08:00 | 2013-10-26 17:00 | 2013-10-08 08:00 | 2013-10-26 17:00 | 2013-10-08 08:00 | 2013-10-26 17:00 | 2013-10-10 08:00 | 2013-10-28 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30760 | N | N | 10 | GROUND FLOOR |  | 125269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 1295 | CONCRETE MASON SK
%R | 503730 | 6359 | 125272 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STFF2020 | Column-Rebar & Formwork | 8165 | 16 | 0 | 200 | 0 | 3580.5 | 3580.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-13 08:00 | 2013-11-12 17:00 |  | 2013-10-10 08:00 | 2013-11-10 17:00 | 2013-10-10 08:00 | 2013-11-10 17:00 | 2013-10-10 08:00 | 2013-11-10 17:00 | 2013-10-13 08:00 | 2013-11-12 17:00 |  | PT_Normal |  |  |  |  | RPkq4U0tRsyQhYZ5aFjtlw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30770 | N | N | 15 | FIRST FLOORS |  | 125269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 1790.25 | STEEL FIXERS SK
%R | 503731 | 6359 | 125272 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STFF2025 | Column-Concrete | 8167 | 32 | 0 | 192 | 0 | 224 | 224 | 192 | 0 | 0 | 0 |  |  |  | 2013-10-27 08:00 | 2013-11-23 17:00 |  | 2013-10-22 08:00 | 2013-11-18 17:00 | 2013-10-22 08:00 | 2013-11-18 17:00 | 2013-10-22 08:00 | 2013-11-18 17:00 | 2013-10-27 08:00 | 2013-11-23 17:00 |  | PT_Normal |  |  |  |  | vo5RZvEqSQaUHXhwht0X5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30770 | N | N | 15 | FIRST FLOORS |  | 125269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 224 | CONCRETE MASON SK
%R | 503732 | 6359 | 125272 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 32 | 0 | 200 | 0 | 16119.25 | 16119.25 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-11 08:00 | 2013-12-09 17:00 |  | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-11-06 08:00 | 2013-12-04 17:00 | 2013-11-11 08:00 | 2013-12-09 17:00 |  | PT_Normal |  |  |  |  | lBjLcWYAR82aQI/o0NUGAw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30770 | N | N | 15 | FIRST FLOORS |  | 125269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 16119.25 | STEEL FIXERS SK
%R | 503733 | 6359 | 125272 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 32 | 0 | 112 | 0 | 1141 | 1141 | 112 | 0 | 0 | 0 |  |  |  | 2013-11-27 08:00 | 2013-12-12 17:00 |  | 2013-11-23 08:00 | 2013-12-08 17:00 | 2013-11-23 08:00 | 2013-12-08 17:00 | 2013-11-23 08:00 | 2013-12-08 17:00 | 2013-11-27 08:00 | 2013-12-12 17:00 |  | PT_Normal |  |  |  |  | LIA/6jECQ1Wc+GMzX+c+2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30770 | N | N | 15 | FIRST FLOORS |  | 125269 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1141 | CONCRETE MASON SK
%R | 503734 | 6359 | 125275 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3AREL3665 | External Plastering | 8169 | 376 | 0 | 200 | 0 | 14275 | 14275 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-25 08:00 | 2014-04-22 17:00 |  | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | t0/46MMQSUOAZDJnXB03Mg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30860 | N | N | 15 | ELEVATION |  | 125274 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 14275 | PLASTER MASON SK
%R | 503735 | 6359 | 125275 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3AREL3670 | External stone cladding works | 8170 | 392 | 0 | 160 | 0 | 990 | 990 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-14 08:00 | 2014-05-06 17:00 |  | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-02-16 08:00 | 2014-03-10 17:00 | 2014-04-14 08:00 | 2014-05-06 17:00 |  | PT_Normal |  |  |  |  | 6A2JbepeRZG8ZWDMDOvJWw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30860 | N | N | 15 | ELEVATION |  | 125274 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 990 | TILE MASON SK
%R | 503736 | 6359 | 125275 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3AREL3680 | External Painting | 8178 | 392 | 40 | 160 | 0 | 3784 | 3784 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-26 08:00 | 2014-05-18 17:00 |  | 2014-02-27 08:00 | 2014-03-22 17:00 | 2014-02-27 08:00 | 2014-03-22 17:00 | 2014-02-27 08:00 | 2014-03-22 17:00 | 2014-04-26 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | cL63jDpMS+yOZ++27nC6mw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30860 | N | N | 15 | ELEVATION |  | 125274 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 3784 | LABOR- SUBCONTRACTOR
%R | 503737 | 6359 | 125276 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARRF3630 | Leveling Screed for Waterproofing | 8164 | 168 | 0 | 200 | 0 | 800 | 800 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-04-06 17:00 |  | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | njWCYo4wRc+wvDE1PgRhnw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30850 | N | N | 10 | ROOF |  | 125274 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 400 | SCREED MASON SK
%R | 503738 | 6359 | 125276 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARRF3635 | Laying of Waterproofing Membrane | 8178 | 168 | 0 | 200 | 0 | 1138.5 | 1138.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-12 08:00 | 2014-04-09 17:00 |  | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-03-12 08:00 | 2014-04-09 17:00 |  | PT_Normal |  |  |  |  | 1kHXv0d7TQqfK9V4an+vLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30850 | N | N | 10 | ROOF |  | 125274 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 569.25 | LABOR- SUBCONTRACTOR
%R | 503739 | 6359 | 125276 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARRF3640 | Installation of Insulation & Protection | 8178 | 168 | 0 | 200 | 0 | 1408 | 1408 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-14 17:00 |  | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 |  | PT_Normal |  |  |  |  | 46rc+s2fQk6a5krJ8V6GuA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30850 | N | N | 10 | ROOF |  | 125274 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 704 | LABOR- SUBCONTRACTOR
%R | 503740 | 6359 | 125276 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 168 | 0 | 200 | 0 | 688.25 | 688.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-19 17:00 |  | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | 9p79RJzLQ0GKcafbYX/t+g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30850 | N | N | 10 | ROOF |  | 125274 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 344.125 | TILE MASON SK
%R | 503741 | 6359 | 125276 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 168 | 0 | 160 | 0 | 616 | 616 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-14 08:00 | 2014-05-06 17:00 |  | 2014-03-20 08:00 | 2014-04-12 17:00 | 2014-03-20 08:00 | 2014-04-12 17:00 | 2014-03-20 08:00 | 2014-04-12 17:00 | 2014-04-14 08:00 | 2014-05-06 17:00 |  | PT_Normal |  |  |  |  | VweBzl+tRceH9f0RTIOyxQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30850 | N | N | 10 | ROOF |  | 125274 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 616 | LABOR- SUBCONTRACTOR
%R | 503742 | 6359 | 125276 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 168 | 0 | 200 | 0 | 1046.5 | 1046.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-30 08:00 | 2014-04-27 17:00 |  | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-30 08:00 | 2014-04-27 17:00 |  | PT_Normal |  |  |  |  | QxzVevPqSD+uxgVBiSvMgw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30850 | N | N | 10 | ROOF |  | 125274 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1046.5 | LABOR- SUBCONTRACTOR
%R | 503743 | 6359 | 125276 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARRF3660 | Installation of Access Ladder | 8178 | 208 | 208 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-01 08:00 | 2014-05-18 17:00 |  | 2014-04-01 08:00 | 2014-04-17 17:00 | 2014-04-01 08:00 | 2014-04-17 17:00 | 2014-04-01 08:00 | 2014-04-17 17:00 | 2014-05-01 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | 7C6RGnuwTb6ML6DM5LgVkQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30850 | N | N | 10 | ROOF |  | 125274 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 176 | LABOR- SUBCONTRACTOR
%R | 503744 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3025 | Porcelain Tile flooring | 8170 | 144 | 0 | 200 | 0 | 1743.75 | 1743.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-22 08:00 | 2014-02-20 17:00 |  | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-01-01 08:00 | 2014-01-29 17:00 | 2014-01-22 08:00 | 2014-02-20 17:00 |  | PT_Normal |  |  |  |  | LSwdlxKeRWS7Aau7cefQPA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1743.75 | TILE MASON SK
%R | 503745 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3040 | Cobble Tile flooring | 8170 | 168 | 0 | 120 | 0 | 741 | 741 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-23 08:00 | 2014-03-11 17:00 |  | 2014-01-28 08:00 | 2014-02-15 17:00 | 2014-01-28 08:00 | 2014-02-15 17:00 | 2014-01-28 08:00 | 2014-02-15 17:00 | 2014-02-23 08:00 | 2014-03-11 17:00 |  | PT_Normal |  |  |  |  | ceL1HmuzRnCVoFJ6tfAkIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 741 | TILE MASON SK
%R | 503746 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 184 | 16 | 120 | 0 | 761.5 | 761.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-18 08:00 | 2014-03-06 17:00 |  | 2014-01-21 08:00 | 2014-02-06 17:00 | 2014-01-21 08:00 | 2014-02-06 17:00 | 2014-01-21 08:00 | 2014-02-06 17:00 | 2014-02-18 08:00 | 2014-03-06 17:00 |  | PT_Normal |  |  |  |  | f27O1Ig9TtCPVEGexGkDhQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 761.5 | TILE MASON SK
%R | 503747 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 168 | 0 | 160 | 0 | 875 | 875 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-03 08:00 | 2014-03-25 17:00 |  | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-03-03 08:00 | 2014-03-25 17:00 |  | PT_Normal |  |  |  |  | Z6ruhnmfQm6Ki1iIPBmafQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 875 | GRANITE MASON SK
%R | 503748 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3045 | Fixing of Suspension systems | 8178 | 144 | 0 | 160 | 0 | 1455.05 | 1455.05 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-09 08:00 | 2014-03-04 17:00 |  | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-01-19 08:00 | 2014-02-10 17:00 | 2014-02-09 08:00 | 2014-03-04 17:00 |  | PT_Normal |  |  |  |  | m9Mbm6oSTiiBl7kCFS5dVQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1455.05 | LABOR- SUBCONTRACTOR
%R | 503749 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3055 | Aluminum tile false ceiling | 8178 | 168 | 24 | 200 | 0 | 150 | 150 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-22 17:00 |  | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-01-27 08:00 | 2014-02-25 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | YPbzuWxjQFCZ0Mvz06QAqQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 150 | LABOR- SUBCONTRACTOR
%R | 503750 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3060 | Gypsum board false ceiling | 8178 | 144 | 0 | 200 | 0 | 1335.15 | 1335.15 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-22 17:00 |  | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | i0Cdh7OGR0ucF1d4zKljaw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01; period 2: 2014-AP03 |  | 667.575 | LABOR- SUBCONTRACTOR
%R | 503751 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3065 | Wooden door & PVC Door | 8178 | 168 | 0 | 120 | 0 | 308 | 308 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-02 17:00 |  | 2014-02-20 08:00 | 2014-03-09 17:00 | 2014-02-20 08:00 | 2014-03-09 17:00 | 2014-02-20 08:00 | 2014-03-09 17:00 | 2014-03-17 08:00 | 2014-04-02 17:00 |  | PT_Normal |  |  |  |  | t8Xgxqu6TTKfVyXOJf82cQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 308 | LABOR- SUBCONTRACTOR
%R | 503752 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3070 | Aluminum doors | 8178 | 168 | 0 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-23 08:00 | 2014-04-08 17:00 |  | 2014-02-26 08:00 | 2014-03-15 17:00 | 2014-02-26 08:00 | 2014-03-15 17:00 | 2014-02-26 08:00 | 2014-03-15 17:00 | 2014-03-23 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | ljGjp+SuTBmAz9JTRT/gVw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 176 | LABOR- SUBCONTRACTOR
%R | 503753 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3080 | Aluminum windows | 8178 | 248 | 40 | 160 | 0 | 162.25 | 162.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-10 08:00 | 2014-05-03 17:00 |  | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-04-10 08:00 | 2014-05-03 17:00 |  | PT_Normal |  |  |  |  | 1rvKAiAyRsi6Y1VjiZ9M3A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 162.25 | LABOR- SUBCONTRACTOR
%R | 503754 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3075 | Carpentry & Joinery Works | 8178 | 168 | 0 | 160 | 0 | 572 | 572 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-29 08:00 | 2014-04-20 17:00 |  | 2014-03-04 08:00 | 2014-03-26 17:00 | 2014-03-04 08:00 | 2014-03-26 17:00 | 2014-03-04 08:00 | 2014-03-26 17:00 | 2014-03-29 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | Lb/FxKVPRQuDgJSqBC9UXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 572 | LABOR- SUBCONTRACTOR
%R | 503755 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3090 | Installation of Granite Counter Top | 8171 | 168 | 0 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-10 08:00 | 2014-04-27 17:00 |  | 2014-03-17 08:00 | 2014-04-02 17:00 | 2014-03-17 08:00 | 2014-04-02 17:00 | 2014-03-17 08:00 | 2014-04-02 17:00 | 2014-04-10 08:00 | 2014-04-27 17:00 |  | PT_Normal |  |  |  |  | pmcfdz52Sk+oHVUIn9DqeQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 176 | GRANITE MASON SK
%R | 503756 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3085 | S.S.Balustrade | 8178 | 208 | 40 | 160 | 0 | 262.5 | 262.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-12 08:00 | 2014-05-04 17:00 |  | 2014-03-12 08:00 | 2014-04-03 17:00 | 2014-03-12 08:00 | 2014-04-03 17:00 | 2014-03-12 08:00 | 2014-04-03 17:00 | 2014-04-12 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | iHipci0vR6uCsSTum8ixfg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 262.5 | LABOR- SUBCONTRACTOR
%R | 503757 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3095 | Final Painting | 8178 | 168 | 0 | 200 | 0 | 5425.75 | 5425.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | lgP+2xXCTF2HNIF6yYNuuQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 5425.75 | LABOR- SUBCONTRACTOR
%R | 503758 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3000 | Block work | 8168 | 144 | 0 | 200 | 0 | 9737.5 | 9737.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-01 08:00 | 2013-12-30 17:00 |  | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-11-10 08:00 | 2013-12-08 17:00 | 2013-12-01 08:00 | 2013-12-30 17:00 |  | PT_Normal |  |  |  |  | h2nFfkEHSfGNbLi3FzDFeg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 9737.5 | BLOCK MASON SK
%R | 503759 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3005 | Plastering work | 8169 | 144 | 0 | 200 | 0 | 13637.5 | 13637.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-24 08:00 | 2014-01-21 17:00 |  | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-02 08:00 | 2013-12-31 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 |  | PT_Normal |  |  |  |  | woqe1MgSSkGD9OoLvztaTw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 13637.5 | PLASTER MASON SK
%R | 503760 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3010 | Flooring screed | 8164 | 208 | 64 | 168 | 0 | 1580.25 | 1580.25 | 168 | 0 | 0 | 0 |  |  |  | 2014-01-11 08:00 | 2014-02-03 17:00 |  | 2013-12-10 08:00 | 2014-01-04 17:00 | 2013-12-10 08:00 | 2014-01-04 17:00 | 2013-12-10 08:00 | 2014-01-04 17:00 | 2014-01-11 08:00 | 2014-02-03 17:00 |  | PT_Normal |  |  |  |  | UcypIqBVTg+YNjS9uN81yQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1580.25 | SCREED MASON SK
%R | 503761 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 144 | 0 | 120 | 0 | 247.5 | 247.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-01-11 08:00 | 2014-01-27 17:00 |  | 2013-12-21 08:00 | 2014-01-06 17:00 | 2013-12-21 08:00 | 2014-01-06 17:00 | 2013-12-21 08:00 | 2014-01-06 17:00 | 2014-01-11 08:00 | 2014-01-27 17:00 |  | PT_Normal |  |  |  |  | HQ9aqwobSqa77otqCdt2Hw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 247.5 | LABOR- SUBCONTRACTOR
%R | 503762 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3030 | Paint First coat | 8178 | 256 | 0 | 200 | 0 | 5425.75 | 5425.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-26 08:00 | 2014-02-24 17:00 |  | 2013-12-19 08:00 | 2014-01-16 17:00 | 2013-12-19 08:00 | 2014-01-16 17:00 | 2013-12-19 08:00 | 2014-01-16 17:00 | 2014-01-26 08:00 | 2014-02-24 17:00 |  | PT_Normal |  |  |  |  | 5iySJ/6bQJe0utRB9mg7Qw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 5425.75 | LABOR- SUBCONTRACTOR
%R | 503763 | 6359 | 125278 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARGF3020 | Ceramic Wall Tiling | 8170 | 144 | 0 | 200 | 0 | 4428.5 | 4428.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-02-15 17:00 |  | 2013-12-26 08:00 | 2014-01-23 17:00 | 2013-12-26 08:00 | 2014-01-23 17:00 | 2013-12-26 08:00 | 2014-01-23 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 |  | PT_Normal |  |  |  |  | 5Hu98b8bS6K/YrS4Doa4yQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30810 | N | N | 10 | GROUND FLOOR |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 4428.5 | TILE MASON SK
%R | 503764 | 6359 | 125279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARFF3300 | Block work | 8168 | 0 | 0 | 200 | 0 | 6387.5 | 6387.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-23 08:00 | 2014-01-20 17:00 |  | 2013-12-23 08:00 | 2014-01-20 17:00 | 2013-12-23 08:00 | 2014-01-20 17:00 | 2013-12-23 08:00 | 2014-01-20 17:00 | 2013-12-23 08:00 | 2014-01-20 17:00 |  | PT_Normal |  |  |  |  | MGLJ8G1MQYmQNbMCpYJXTg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30820 | N | N | 15 | FIRST FLOORS |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 6387.5 | BLOCK MASON SK
%R | 503765 | 6359 | 125279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARFF3305 | Plastering work | 8169 | 0 | 0 | 200 | 0 | 8899 | 8899 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-16 08:00 | 2014-02-15 17:00 |  | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 | 2014-01-16 08:00 | 2014-02-15 17:00 |  | PT_Normal |  |  |  |  | bnCoacqRSQmiPSiiCxXj8Q |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30820 | N | N | 15 | FIRST FLOORS |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 8899 | PLASTER MASON SK
%R | 503766 | 6359 | 125279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARFF3310 | Flooring screed | 8164 | 96 | 96 | 168 | 0 | 1215.5 | 1215.5 | 168 | 0 | 0 | 0 |  |  |  | 2014-02-08 08:00 | 2014-03-04 17:00 |  | 2014-01-25 08:00 | 2014-02-18 17:00 | 2014-01-25 08:00 | 2014-02-18 17:00 | 2014-01-25 08:00 | 2014-02-18 17:00 | 2014-02-08 08:00 | 2014-03-04 17:00 |  | PT_Normal |  |  |  |  | 3O6vLtO6SYSACY9/Na45qw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30820 | N | N | 15 | FIRST FLOORS |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1215.5 | SCREED MASON SK
%R | 503767 | 6359 | 125279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARFF3315 | Wet area waterproofing | 8178 | 0 | 0 | 120 | 0 | 1215.5 | 1215.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-02-23 17:00 |  | 2014-02-05 08:00 | 2014-02-23 17:00 | 2014-02-05 08:00 | 2014-02-23 17:00 | 2014-02-05 08:00 | 2014-02-23 17:00 | 2014-02-05 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | WUO/qhzpTNKgclKCoF6iqg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30820 | N | N | 15 | FIRST FLOORS |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1215.5 | LABOR- SUBCONTRACTOR
%R | 503768 | 6359 | 125279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARFF3330 | Paint First coat | 8178 | 112 | 112 | 200 | 0 | 4742.75 | 4742.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-19 08:00 | 2014-03-19 17:00 |  | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-02 08:00 | 2014-03-03 17:00 | 2014-02-19 08:00 | 2014-03-19 17:00 |  | PT_Normal |  |  |  |  | 7Ap1GIN1SJqPYb1xjb5CHQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30820 | N | N | 15 | FIRST FLOORS |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 2371.375 | LABOR- SUBCONTRACTOR
%R | 503769 | 6359 | 125279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARFF3320 | Ceramic Wall Tiling | 8170 | 0 | 0 | 200 | 0 | 1897.25 | 1897.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-03-13 17:00 |  | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 | 2014-02-13 08:00 | 2014-03-13 17:00 |  | PT_Normal |  |  |  |  | pGyiWFq1TpGYGll2CGUDwQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30820 | N | N | 15 | FIRST FLOORS |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 948.625 | TILE MASON SK
%R | 503770 | 6359 | 125279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARFF3325 | Porcelain Tile flooring | 8170 | 0 | 0 | 200 | 0 | 1743.75 | 1743.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-20 08:00 | 2014-03-20 17:00 |  | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | yOjvNohqT2CHlp2RC3T1Kg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30820 | N | N | 15 | FIRST FLOORS |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 871.875 | TILE MASON SK
%R | 503771 | 6359 | 125279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARFF3335 | Slate Tile Flooring & Skirting | 8170 | 64 | 64 | 120 | 0 | 261.5 | 261.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-05 17:00 |  | 2014-03-10 08:00 | 2014-03-26 17:00 | 2014-03-10 08:00 | 2014-03-26 17:00 | 2014-03-10 08:00 | 2014-03-26 17:00 | 2014-03-19 08:00 | 2014-04-05 17:00 |  | PT_Normal |  |  |  |  | OGKsMg5ZQJO9mp7JBFR1qA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30820 | N | N | 15 | FIRST FLOORS |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 261.5 | TILE MASON SK
%R | 503772 | 6359 | 125279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARFF3350 | Granite - Stair case flooring & Skirting | 8171 | 16 | 16 | 160 | 0 | 875 | 875 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-16 08:00 | 2014-04-07 17:00 |  | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-03-13 08:00 | 2014-04-05 17:00 | 2014-03-16 08:00 | 2014-04-07 17:00 |  | PT_Normal |  |  |  |  | eFEJUjwZSO25gEw9TDcOfQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30820 | N | N | 15 | FIRST FLOORS |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 875 | GRANITE MASON SK
%R | 503773 | 6359 | 125279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARFF3345 | Fixing of Suspension systems | 8178 | 0 | 0 | 160 | 0 | 1305 | 1305 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-05 08:00 | 2014-03-27 17:00 |  | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-03-05 08:00 | 2014-03-27 17:00 | 2014-03-05 08:00 | 2014-03-27 17:00 |  | PT_Normal |  |  |  |  | Uu+Tc88iRVyZTlcxBUGXJA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30820 | N | N | 15 | FIRST FLOORS |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1305 | LABOR- SUBCONTRACTOR
%R | 503774 | 6359 | 125279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARFF3365 | Wooden door | 8178 | 0 | 0 | 120 | 0 | 308 | 308 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-27 08:00 | 2014-04-13 17:00 |  | 2014-03-27 08:00 | 2014-04-13 17:00 | 2014-03-27 08:00 | 2014-04-13 17:00 | 2014-03-27 08:00 | 2014-04-13 17:00 | 2014-03-27 08:00 | 2014-04-13 17:00 |  | PT_Normal |  |  |  |  | 53dHMIFgQaubFtKHbddjQw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30820 | N | N | 15 | FIRST FLOORS |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 308 | LABOR- SUBCONTRACTOR
%R | 503775 | 6359 | 125279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARFF3370 | Aluminum Door | 8178 | 0 | 0 | 160 | 0 | 220 | 220 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-27 08:00 | 2014-04-19 17:00 |  | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-03-27 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | E7LBu9//RH6/SMqsTOiUiw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30820 | N | N | 15 | FIRST FLOORS |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 220 | LABOR- SUBCONTRACTOR
%R | 503776 | 6359 | 125279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARFF3380 | Aluminum windows | 8178 | 32 | 32 | 160 | 0 | 162.25 | 162.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-08 08:00 | 2014-04-30 17:00 |  | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-04-03 08:00 | 2014-04-26 17:00 | 2014-04-08 08:00 | 2014-04-30 17:00 |  | PT_Normal |  |  |  |  | RtBeVJLgS3CHJEvTsf6+AA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30820 | N | N | 15 | FIRST FLOORS |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 162.25 | LABOR- SUBCONTRACTOR
%R | 503777 | 6359 | 125279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARFF3375 | Carpentry & Joinery Works | 8178 | 0 | 0 | 200 | 0 | 1100 | 1100 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-02 08:00 | 2014-04-30 17:00 |  | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 |  | PT_Normal |  |  |  |  | Xp2js+XMTfuI8zuObJ/sWg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30820 | N | N | 15 | FIRST FLOORS |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1100 | LABOR- SUBCONTRACTOR
%R | 503778 | 6359 | 125279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARFF3390 | Installation of Granite Counter Top | 8171 | 8 | 8 | 160 | 0 | 88 | 88 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-15 08:00 | 2014-05-07 17:00 |  | 2014-04-14 08:00 | 2014-05-06 17:00 | 2014-04-14 08:00 | 2014-05-06 17:00 | 2014-04-14 08:00 | 2014-05-06 17:00 | 2014-04-15 08:00 | 2014-05-07 17:00 |  | PT_Normal |  |  |  |  | NG0uVCuHTgyQFMHx0tSicg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30820 | N | N | 15 | FIRST FLOORS |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 88 | GRANITE MASON SK
%R | 503779 | 6359 | 125279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARFF3385 | Handrail & Balustrade | 8178 | 0 | 0 | 160 | 0 | 787.5 | 787.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-14 08:00 | 2014-05-06 17:00 |  | 2014-04-14 08:00 | 2014-05-06 17:00 | 2014-04-14 08:00 | 2014-05-06 17:00 | 2014-04-14 08:00 | 2014-05-06 17:00 | 2014-04-14 08:00 | 2014-05-06 17:00 |  | PT_Normal |  |  |  |  | oH+uY2d0SjuVGceoTyompQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30820 | N | N | 15 | FIRST FLOORS |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 787.5 | LABOR- SUBCONTRACTOR
%R | 503780 | 6359 | 125279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARFF3395 | Final Painting | 8178 | 0 | 0 | 200 | 0 | 4742.75 | 4742.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | RkRQitmNRsSl0JfIMIYBXg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30820 | N | N | 15 | FIRST FLOORS |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 4742.75 | LABOR- SUBCONTRACTOR
%R | 503781 | 6359 | 125279 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARFF3360 | Gypsum board false ceiling | 8178 | 0 | 0 | 200 | 0 | 1305 | 1305 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-12 08:00 | 2014-04-09 17:00 |  | 2014-03-12 08:00 | 2014-04-09 17:00 | 2014-03-12 08:00 | 2014-04-09 17:00 | 2014-03-12 08:00 | 2014-04-09 17:00 | 2014-03-12 08:00 | 2014-04-09 17:00 |  | PT_Normal |  |  |  |  | qzFthlonSb+yesugDJ5viA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30820 | N | N | 15 | FIRST FLOORS |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1305 | LABOR- SUBCONTRACTOR
%R | 503782 | 6359 | 125280 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARRF3600 | Block work | 8168 | 416 | 0 | 160 | 0 | 700 | 700 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-03-31 17:00 |  | 2014-01-06 08:00 | 2014-01-28 17:00 | 2014-01-06 08:00 | 2014-01-28 17:00 | 2014-01-06 08:00 | 2014-01-28 17:00 | 2014-03-09 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | sQv+DtkMTu2UytwQTvF79w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30830 | N | N | 20 | ROOF |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 700 | BLOCK MASON SK
%R | 503783 | 6359 | 125280 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARRF3605 | Plastering work | 8169 | 416 | 0 | 160 | 0 | 1786.5 | 1786.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-08 17:00 |  | 2014-01-14 08:00 | 2014-02-05 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 | 2014-01-14 08:00 | 2014-02-05 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | efUO77kQSLWffrEOl7x2MQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30830 | N | N | 20 | ROOF |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1786.5 | PLASTER MASON SK
%R | 503784 | 6359 | 125280 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARRF3610 | Flooring screed | 8164 | 456 | 0 | 120 | 0 | 136.5 | 136.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-04-22 17:00 |  | 2014-01-28 08:00 | 2014-02-15 17:00 | 2014-01-28 08:00 | 2014-02-15 17:00 | 2014-01-28 08:00 | 2014-02-15 17:00 | 2014-04-06 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | aGZpKQmmQj2sVgmzj69NkA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30830 | N | N | 20 | ROOF |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 136.5 | SCREED MASON SK
%R | 503785 | 6359 | 125280 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARRF3695 | Painting -Storage area | 8178 | 456 | 0 | 160 | 0 | 1640 | 1640 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-14 08:00 | 2014-05-06 17:00 |  | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-02-05 08:00 | 2014-03-01 17:00 | 2014-04-14 08:00 | 2014-05-06 17:00 |  | PT_Normal |  |  |  |  | yBOaFlKdRwSbzlCRkBvNew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30830 | N | N | 20 | ROOF |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1640 | LABOR- SUBCONTRACTOR
%R | 503786 | 6359 | 125280 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ARRF3620 | Epoxy Painting -Storage area | 8178 | 456 | 456 | 120 | 0 | 48.5 | 48.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-01 08:00 | 2014-05-18 17:00 |  | 2014-02-24 08:00 | 2014-03-12 17:00 | 2014-02-24 08:00 | 2014-03-12 17:00 | 2014-02-24 08:00 | 2014-03-12 17:00 | 2014-05-01 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | 5NstjftlS0Gs1SDQOaNKQA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30830 | N | N | 20 | ROOF |  | 125277 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 48.5 | LABOR- SUBCONTRACTOR
%R | 503787 | 6359 | 125281 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | l5+sKqnVS+G5xeWjIsIiiA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31060 | N | N | 30 | TESTING AND COMMISSIONING |  | 125265 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 503788 | 6359 | 125281 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 0 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | s7yRviuOTHWlu+SnCTSdpw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31060 | N | N | 30 | TESTING AND COMMISSIONING |  | 125265 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 503789 | 6359 | 125281 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | MVQWrZ4qQQCgzp3x5s9DMg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31060 | N | N | 30 | TESTING AND COMMISSIONING |  | 125265 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 503790 | 6359 | 125283 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3SLEX5105 | Laying of Grass/ green area | 8178 | 128 | 0 | 200 | 0 | 2744 | 2744 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-13 08:00 | 2014-05-11 17:00 |  | 2014-03-25 08:00 | 2014-04-22 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 | 2014-04-13 08:00 | 2014-05-11 17:00 |  | PT_Normal |  |  |  |  | ogTYJUkTR8yH75F8YvVXoQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31050 | N | N | 25 | SOFT LANDSCAPING |  | 125282 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 2744 | LABOR- SUBCONTRACTOR
%R | 503791 | 6359 | 125283 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3SLEX5110 | Laying of Palm tree | 8178 | 128 | 128 | 200 | 0 | 168 | 168 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | LorwdEcMS5unO01IC6thdA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31050 | N | N | 25 | SOFT LANDSCAPING |  | 125282 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 168 | LABOR- SUBCONTRACTOR
%R | 503792 | 6359 | 125284 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3WEEX5030 | Excavation | 8177 | 144 | 0 | 160 | 0 | 64 | 64 | 160 | 40 | 0 | 40 |  |  |  | 2014-03-03 08:00 | 2014-03-25 17:00 |  | 2014-02-09 08:00 | 2014-03-04 17:00 | 2014-02-09 08:00 | 2014-03-04 17:00 | 2014-02-09 08:00 | 2014-03-04 17:00 | 2014-03-03 08:00 | 2014-03-25 17:00 |  | PT_Normal |  |  |  |  | 1f/DUqUSQ9y3x9Uo1WnpOA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31030 | N | N | 15 | WATER TANK ENCLOSURE |  | 125282 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 64 | LABOR - CIVIL
%R | 503793 | 6359 | 125284 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3WEEX5035 | Construction of Raft | 8165 | 144 | 0 | 200 | 0 | 840 | 840 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-09 08:00 | 2014-04-06 17:00 |  | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 | 2014-03-09 08:00 | 2014-04-06 17:00 |  | PT_Normal |  |  |  |  | oK0jd3sDRuKwhcXawswCAA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31030 | N | N | 15 | WATER TANK ENCLOSURE |  | 125282 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 420 | STEEL FIXERS SK
%R | 503794 | 6359 | 125284 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3WEEX5040 | Block works & Plastering | 8168 | 144 | 0 | 200 | 0 | 512 | 512 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-18 08:00 | 2014-04-15 17:00 |  | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-02-25 08:00 | 2014-03-25 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 |  | PT_Normal |  |  |  |  | dzzVsmnZQPCiGfMEDx7RPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31030 | N | N | 15 | WATER TANK ENCLOSURE |  | 125282 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 256 | BLOCK MASON SK
%R | 503795 | 6359 | 125284 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3WEEX5045 | Flooring & Painting | 8178 | 144 | 0 | 200 | 0 | 232 | 232 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-25 08:00 | 2014-04-22 17:00 |  | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-04 08:00 | 2014-04-01 17:00 | 2014-03-25 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | KxGDgC5eRTO1mVeyKiO0vw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31030 | N | N | 15 | WATER TANK ENCLOSURE |  | 125282 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 232 | LABOR- SUBCONTRACTOR
%R | 503796 | 6359 | 125284 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3WEEX5050 | Installation of Steel Gate | 8178 | 144 | 64 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-07 08:00 | 2014-04-29 17:00 |  | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-03-17 08:00 | 2014-04-08 17:00 | 2014-04-07 08:00 | 2014-04-29 17:00 |  | PT_Normal |  |  |  |  | cKba5tfLQtWokqbPVcfS4g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31030 | N | N | 15 | WATER TANK ENCLOSURE |  | 125282 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 56 | LABOR- SUBCONTRACTOR
%R | 503797 | 6359 | 125284 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 80 | 0 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-13 08:00 | 2014-05-11 17:00 |  | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-13 08:00 | 2014-05-11 17:00 |  | PT_Normal |  |  |  |  | eUynIquCSz6ExsYasJI20g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31030 | N | N | 15 | WATER TANK ENCLOSURE |  | 125282 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 336 | LABOR- SUBCONTRACTOR
%R | 503798 | 6359 | 125284 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 72 | 0 | 200 | 0 | 203.2 | 203.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-04-09 08:00 | 2014-05-07 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 | 2014-04-09 08:00 | 2014-05-07 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | 3fcBlnxwSruAbVIZ9uBByw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31030 | N | N | 15 | WATER TANK ENCLOSURE |  | 125282 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 203.2 | LABOR- SUBCONTRACTOR
%R | 503799 | 6359 | 125285 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3MSEX5020 | Construction Entrance Ramp | 8164 | 128 | 0 | 200 | 0 | 656 | 656 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-05 08:00 | 2014-04-02 17:00 |  | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-02-15 08:00 | 2014-03-15 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 |  | PT_Normal |  |  |  |  | 6OMaTgPvTzCWoOJVsNjaiA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31020 | N | N | 10 | MISCELLANEOUS |  | 125282 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 328 | SCREED MASON SK
%R | 503800 | 6359 | 125285 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3MSEX5025 | SS.Handrails and Balustrades | 8178 | 152 | 8 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-26 08:00 | 2014-04-17 17:00 |  | 2014-03-04 08:00 | 2014-03-26 17:00 | 2014-03-04 08:00 | 2014-03-26 17:00 | 2014-03-04 08:00 | 2014-03-26 17:00 | 2014-03-26 08:00 | 2014-04-17 17:00 |  | PT_Normal |  |  |  |  | FugNNy7tRjKAPssIfwdf8g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31020 | N | N | 10 | MISCELLANEOUS |  | 125282 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 56 | LABOR- SUBCONTRACTOR
%R | 503801 | 6359 | 125285 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3MSEX5015 | Construction of grease Trap | 8178 | 264 | 0 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-30 17:00 |  | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-01-27 08:00 | 2014-02-19 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | ETD+S7lsRiuNMdq/JYGU5Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31020 | N | N | 10 | MISCELLANEOUS |  | 125282 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 56 | LABOR- SUBCONTRACTOR
%R | 503802 | 6359 | 125285 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3MSEX5000 | Construction of Manholes | 8172 | 264 | 0 | 200 | 0 | 528 | 528 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-01 08:00 | 2014-03-02 17:00 |  | 2013-12-24 08:00 | 2014-01-21 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 | 2013-12-24 08:00 | 2014-01-21 17:00 | 2014-02-01 08:00 | 2014-03-02 17:00 |  | PT_Normal |  |  |  |  | ZsCMijFRTtCOywS7/H6FEQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31020 | N | N | 10 | MISCELLANEOUS |  | 125282 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 528 | MANHOLES SK
%R | 503803 | 6359 | 125285 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3MSEX5005 | Construction of Soak pit, Chambers | 8172 | 264 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-16 17:00 |  | 2014-01-07 08:00 | 2014-02-04 17:00 | 2014-01-07 08:00 | 2014-02-04 17:00 | 2014-01-07 08:00 | 2014-02-04 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | nV4/EnvdRpOUwXL/2iZj1A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31020 | N | N | 10 | MISCELLANEOUS |  | 125282 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 176 | MANHOLES SK
%R | 503804 | 6359 | 125285 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3MSEX5010 | Telephone cable laying | 8177 | 264 | 176 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-28 17:00 |  | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | okd075t9TASPK9283Gw/IA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31020 | N | N | 10 | MISCELLANEOUS |  | 125282 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 250 | LABOR - CIVIL
%R | 503805 | 6359 | 125285 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 824 | 64 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-04 08:00 | 2014-10-02 17:00 |  | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-05-04 08:00 | 2014-06-01 17:00 | 2014-09-04 08:00 | 2014-10-02 17:00 |  | PT_Normal |  |  |  |  | b5Cv+Y7JSRy0ZEOrt/viqQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:44 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31020 | N | N | 10 | MISCELLANEOUS |  | 125282 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 400 | LABOR- SUBCONTRACTOR
%R | 503806 | 6359 | 125286 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3HDEX5090 | kerb works | 8173 | 128 | 0 | 160 | 0 | 344 | 344 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-10 17:00 |  | 2014-03-01 08:00 | 2014-03-23 17:00 | 2014-03-01 08:00 | 2014-03-23 17:00 | 2014-03-01 08:00 | 2014-03-23 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | cwX7FAnATn2pcTCpA0PnLg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31040 | N | N | 20 | HARD LANDSCAPING |  | 125282 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 344 | KERBSTONE MASON SK
%R | 503807 | 6359 | 125286 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3HDEX5095 | Cobble Stone Works | 8170 | 128 | 0 | 160 | 0 | 200 | 200 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-22 17:00 |  | 2014-03-12 08:00 | 2014-04-03 17:00 | 2014-03-12 08:00 | 2014-04-03 17:00 | 2014-03-12 08:00 | 2014-04-03 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | K8azIyIVRGyU/PNL7TD8ew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31040 | N | N | 20 | HARD LANDSCAPING |  | 125282 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 200 | TILE MASON SK
%R | 503808 | 6359 | 125286 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3HDEX5100 | Interlock works | 8174 | 128 | 0 | 160 | 0 | 232 | 232 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-07 08:00 | 2014-04-29 17:00 |  | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-04-07 08:00 | 2014-04-29 17:00 |  | PT_Normal |  |  |  |  | V7Z1pmvkQ56Urj5ti3YKvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31040 | N | N | 20 | HARD LANDSCAPING |  | 125282 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 232 | INTERLOCK MASON SK
%R | 503809 | 6359 | 125289 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ELGF4010 | Installation of wiring & Main Cabling | 8178 | 360 | 216 | 200 | 0 | 296 | 296 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-28 08:00 | 2014-02-26 17:00 |  | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2013-12-05 08:00 | 2014-01-04 17:00 | 2014-01-28 08:00 | 2014-02-26 17:00 |  | PT_Normal |  |  |  |  | oyyOkLFORJWj4/LYw7mrjg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30890 | N | N | 10 | GROUND FLOOR |  | 125288 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 296 | LABOR- SUBCONTRACTOR
%R | 503810 | 6359 | 125289 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 144 | 0 | 160 | 0 | 227.2 | 227.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-08 08:00 | 2014-03-30 17:00 |  | 2014-02-15 08:00 | 2014-03-09 17:00 | 2014-02-15 08:00 | 2014-03-09 17:00 | 2014-02-15 08:00 | 2014-03-09 17:00 | 2014-03-08 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | msG97MdyQNWG2+6d4KWmYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30890 | N | N | 10 | GROUND FLOOR |  | 125288 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 227.2 | LABOR- SUBCONTRACTOR
%R | 503811 | 6359 | 125289 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 200 | 0 | 200 | 0 | 1651.2 | 1651.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-27 08:00 | 2014-04-24 17:00 |  | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 |  | PT_Normal |  |  |  |  | 8Tvuece+TdiXy0T42xJIsQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30890 | N | N | 10 | GROUND FLOOR |  | 125288 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 825.6 | LABOR- SUBCONTRACTOR
%R | 503812 | 6359 | 125289 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 240 | 0 | 200 | 0 | 1075.2 | 1075.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-16 08:00 | 2014-04-13 17:00 |  | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-03-16 08:00 | 2014-04-13 17:00 |  | PT_Normal |  |  |  |  | hzKZGuIwQW+4f8xIAU9+YA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30890 | N | N | 10 | GROUND FLOOR |  | 125288 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 537.6 | LABOR- SUBCONTRACTOR
%R | 503813 | 6359 | 125289 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ELGF4030 | Installation of Telephone System | 8178 | 144 | 40 | 160 | 0 | 520 | 520 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-19 08:00 | 2014-04-10 17:00 |  | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 |  | PT_Normal |  |  |  |  | dx9NQ/d2TQeIJqvA0krb1Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30890 | N | N | 10 | GROUND FLOOR |  | 125288 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 520 | LABOR- SUBCONTRACTOR
%R | 503814 | 6359 | 125289 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 216 | 0 | 200 | 0 | 1222.4 | 1222.4 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-17 08:00 | 2014-01-15 17:00 |  | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-11-16 08:00 | 2013-12-14 17:00 | 2013-12-17 08:00 | 2014-01-15 17:00 |  | PT_Normal |  |  |  |  | QxHIJ5esSSyAbimiDVg+yg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30890 | N | N | 10 | GROUND FLOOR |  | 125288 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1222.4 | LABOR- SUBCONTRACTOR
%R | 503815 | 6359 | 125289 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ELGF4005 | Cable tray & trunking installation | 8178 | 360 | 0 | 160 | 0 | 1318.4 | 1318.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-01-20 08:00 | 2014-02-12 17:00 |  | 2013-11-27 08:00 | 2013-12-21 17:00 | 2013-11-27 08:00 | 2013-12-21 17:00 | 2013-11-27 08:00 | 2013-12-21 17:00 | 2014-01-20 08:00 | 2014-02-12 17:00 |  | PT_Normal |  |  |  |  | 9kWcmaUKR5KNMXNFReeyIw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30890 | N | N | 10 | GROUND FLOOR |  | 125288 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 1318.4 | LABOR- SUBCONTRACTOR
%R | 503816 | 6359 | 125290 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ELRF4070 | Installation of Isolator | 8178 | 8 | 0 | 144 | 0 | 412.8 | 412.8 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-16 08:00 | 2014-05-06 17:00 |  | 2014-04-15 08:00 | 2014-05-05 17:00 | 2014-04-15 08:00 | 2014-05-05 17:00 | 2014-04-15 08:00 | 2014-05-05 17:00 | 2014-04-16 08:00 | 2014-05-06 17:00 |  | PT_Normal |  |  |  |  | IlmxXDN3Qv+f/lsi946a4A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30910 | N | N | 20 | ROOF |  | 125288 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 412.8 | LABOR- SUBCONTRACTOR
%R | 503817 | 6359 | 125290 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ELRF4075 | Installation of TV Dish Antenna | 8178 | 8 | 8 | 184 | 0 | 732.8 | 732.8 | 184 | 0 | 0 | 0 |  |  |  | 2014-04-22 08:00 | 2014-05-18 17:00 |  | 2014-04-21 08:00 | 2014-05-17 17:00 | 2014-04-21 08:00 | 2014-05-17 17:00 | 2014-04-21 08:00 | 2014-05-17 17:00 | 2014-04-22 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30910 | N | N | 20 | ROOF |  | 125288 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 732.8 | LABOR- SUBCONTRACTOR
%R | 503818 | 6359 | 125291 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ELFF4040 | Cable tray & trunking installation | 8178 | 232 | 16 | 160 | 0 | 1318.4 | 1318.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-03-08 17:00 |  | 2014-01-09 08:00 | 2014-02-01 17:00 | 2014-01-09 08:00 | 2014-02-01 17:00 | 2014-01-09 08:00 | 2014-02-01 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | Rf3A7PTkQp6NpjiWbqmIig |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30900 | N | N | 15 | FIRST FLOORS |  | 125288 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1318.4 | LABOR- SUBCONTRACTOR
%R | 503819 | 6359 | 125291 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ELFF4045 | Installation of wiring & Main Cabling | 8178 | 216 | 0 | 200 | 0 | 296 | 296 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-22 17:00 |  | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-01-20 08:00 | 2014-02-18 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | IAJVrwVmTyy6W+cQHVBclQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30900 | N | N | 15 | FIRST FLOORS |  | 125288 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 296 | LABOR- SUBCONTRACTOR
%R | 503820 | 6359 | 125291 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 24 | 16 | 160 | 0 | 227.2 | 227.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-27 08:00 | 2014-04-19 17:00 |  | 2014-03-24 08:00 | 2014-04-15 17:00 | 2014-03-24 08:00 | 2014-04-15 17:00 | 2014-03-24 08:00 | 2014-04-15 17:00 | 2014-03-27 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | wxSXO2W4SfWIQqVb/jSqUg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30900 | N | N | 15 | FIRST FLOORS |  | 125288 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 227.2 | LABOR- SUBCONTRACTOR
%R | 503821 | 6359 | 125291 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 8 | 0 | 200 | 0 | 1651.2 | 1651.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-02 08:00 | 2014-04-30 17:00 |  | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-01 08:00 | 2014-04-29 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 |  | PT_Normal |  |  |  |  | 6cKOjNteRGWv4IfPrAMeWg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30900 | N | N | 15 | FIRST FLOORS |  | 125288 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1651.2 | LABOR- SUBCONTRACTOR
%R | 503822 | 6359 | 125291 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 8 | 0 | 200 | 0 | 1008 | 1008 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-22 08:00 | 2014-04-19 17:00 |  | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-03-22 08:00 | 2014-04-19 17:00 |  | PT_Normal |  |  |  |  | fN38jdZaR9utm8ooePe/hA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30900 | N | N | 15 | FIRST FLOORS |  | 125288 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1008 | LABOR- SUBCONTRACTOR
%R | 503823 | 6359 | 125291 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ELFF4050 | Installation of Telephone System | 8178 | 88 | 80 | 200 | 0 | 451.2 | 451.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-31 08:00 | 2014-04-28 17:00 |  | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | Ksba++FARTyem7k77DKFag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30900 | N | N | 15 | FIRST FLOORS |  | 125288 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 451.2 | LABOR- SUBCONTRACTOR
%R | 503824 | 6359 | 125291 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 88 | 0 | 200 | 0 | 1222.4 | 1222.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-11 08:00 | 2014-02-08 17:00 |  | 2013-12-29 08:00 | 2014-01-26 17:00 | 2013-12-29 08:00 | 2014-01-26 17:00 | 2013-12-29 08:00 | 2014-01-26 17:00 | 2014-01-11 08:00 | 2014-02-08 17:00 |  | PT_Normal |  |  |  |  | vcsgK46IRaGsX2cqZkvkRQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30900 | N | N | 15 | FIRST FLOORS |  | 125288 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1222.4 | LABOR- SUBCONTRACTOR
%R | 503825 | 6359 | 125293 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 448 | 240 | 120 | 0 | 110.4 | 110.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-05 08:00 | 2014-04-21 17:00 |  | 2014-01-28 08:00 | 2014-02-15 17:00 | 2014-01-28 08:00 | 2014-02-15 17:00 | 2014-01-28 08:00 | 2014-02-15 17:00 | 2014-04-05 08:00 | 2014-04-21 17:00 |  | PT_Normal |  |  |  |  | 5/MlgPqBSuWjno2sWjrcJA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30950 | N | N | 20 | ROOF |  | 125292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 110.4 | LABOR- SUBCONTRACTOR
%R | 503826 | 6359 | 125293 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3PLRF4350 | Installation of Rain water Pipes | 8178 | 208 | 80 | 120 | 0 | 67.2 | 67.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-14 08:00 | 2014-04-30 17:00 |  | 2014-03-15 08:00 | 2014-03-31 17:00 | 2014-03-15 08:00 | 2014-03-31 17:00 | 2014-03-15 08:00 | 2014-03-31 17:00 | 2014-04-14 08:00 | 2014-04-30 17:00 |  | PT_Normal |  |  |  |  | /Ri15V0pR/iuUsbQB6MWZw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30950 | N | N | 20 | ROOF |  | 125292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 503827 | 6359 | 125293 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 8 | 0 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | 337PuEDjRUePgcoO6JIhNA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30950 | N | N | 20 | ROOF |  | 125292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 336 | LABOR- SUBCONTRACTOR
%R | 503828 | 6359 | 125294 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 0 | 0 | 144 | 0 | 441.6 | 441.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-09 08:00 | 2014-01-29 17:00 |  | 2014-01-09 08:00 | 2014-01-29 17:00 | 2014-01-09 08:00 | 2014-01-29 17:00 | 2014-01-09 08:00 | 2014-01-29 17:00 | 2014-01-09 08:00 | 2014-01-29 17:00 |  | PT_Normal |  |  |  |  | BIkFv0sKQaSxDku6p9B5Ew |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30940 | N | N | 15 | FIRST FLOORS |  | 125292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 441.6 | LABOR- SUBCONTRACTOR
%R | 503829 | 6359 | 125294 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3PLFF4330 | Installation of Drainage pipes & testing | 8178 | 176 | 48 | 144 | 0 | 177.6 | 177.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-04 08:00 | 2014-02-25 17:00 |  | 2014-01-09 08:00 | 2014-01-29 17:00 | 2014-01-09 08:00 | 2014-01-29 17:00 | 2014-01-09 08:00 | 2014-01-29 17:00 | 2014-02-04 08:00 | 2014-02-25 17:00 |  | PT_Normal |  |  |  |  | RzxJkot7SJSEt8rZykIr9w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30940 | N | N | 15 | FIRST FLOORS |  | 125292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 177.6 | LABOR- SUBCONTRACTOR
%R | 503830 | 6359 | 125294 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3PLFF4335 | Sanitary Fittings & Accessories | 8178 | 40 | 0 | 160 | 0 | 67.2 | 67.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-02 08:00 | 2014-04-24 17:00 |  | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-04-02 08:00 | 2014-04-24 17:00 |  | PT_Normal |  |  |  |  | MpJHcsjxQUGmjw3LPf5B2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30940 | N | N | 15 | FIRST FLOORS |  | 125292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 503831 | 6359 | 125294 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3PLFF4340 | Installation of Water Heater | 8178 | 40 | 32 | 120 | 0 | 67.2 | 67.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-14 08:00 | 2014-04-30 17:00 |  | 2014-04-08 08:00 | 2014-04-24 17:00 | 2014-04-08 08:00 | 2014-04-24 17:00 | 2014-04-08 08:00 | 2014-04-24 17:00 | 2014-04-14 08:00 | 2014-04-30 17:00 |  | PT_Normal |  |  |  |  | lLMJYWbITSiFTHJM9PJnOQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30940 | N | N | 15 | FIRST FLOORS |  | 125292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 503832 | 6359 | 125295 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 144 | 0 | 144 | 0 | 441.6 | 441.6 | 144 | 0 | 0 | 0 |  |  |  | 2013-12-17 08:00 | 2014-01-07 17:00 |  | 2013-11-26 08:00 | 2013-12-16 17:00 | 2013-11-26 08:00 | 2013-12-16 17:00 | 2013-11-26 08:00 | 2013-12-16 17:00 | 2013-12-17 08:00 | 2014-01-07 17:00 |  | PT_Normal |  |  |  |  | Z40noL4KTM21HEdG6cmbDQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30930 | N | N | 10 | GROUND FLOOR |  | 125292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 441.6 | LABOR- SUBCONTRACTOR
%R | 503833 | 6359 | 125295 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3PLGF4310 | Installation of Drainage pipes &testing | 8178 | 312 | 104 | 144 | 0 | 177.6 | 177.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-01-12 08:00 | 2014-02-01 17:00 |  | 2013-11-26 08:00 | 2013-12-16 17:00 | 2013-11-26 08:00 | 2013-12-16 17:00 | 2013-11-26 08:00 | 2013-12-16 17:00 | 2014-01-12 08:00 | 2014-02-01 17:00 |  | PT_Normal |  |  |  |  | W7/qFGf/S+2J34zywrXhYw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30930 | N | N | 10 | GROUND FLOOR |  | 125292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 177.6 | LABOR- SUBCONTRACTOR
%R | 503834 | 6359 | 125295 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3PLGF4315 | Sanitary Fittings & Accessories | 8178 | 360 | 0 | 160 | 0 | 134.4 | 134.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-12 17:00 |  | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-02-26 08:00 | 2014-03-20 17:00 | 2014-04-20 08:00 | 2014-05-12 17:00 |  | PT_Normal |  |  |  |  | UkSD2bhASqi71Igj1S2kDQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30930 | N | N | 10 | GROUND FLOOR |  | 125292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 503835 | 6359 | 125295 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3PLGF4320 | Installation of Water Heater | 8178 | 360 | 80 | 120 | 0 | 134.4 | 134.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-01 08:00 | 2014-05-18 17:00 |  | 2014-03-10 08:00 | 2014-03-26 17:00 | 2014-03-10 08:00 | 2014-03-26 17:00 | 2014-03-10 08:00 | 2014-03-26 17:00 | 2014-05-01 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | dXKApJAxSdK6ip++Nk4N3g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30930 | N | N | 10 | GROUND FLOOR |  | 125292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 503836 | 6359 | 125295 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 0 | 0 | 128 | 0 | 67.2 | 67.2 | 128 | 0 | 0 | 0 |  |  |  | 2013-07-31 08:00 | 2013-08-21 17:00 |  | 2013-07-31 08:00 | 2013-08-21 17:00 | 2013-07-31 08:00 | 2013-08-21 17:00 | 2013-07-31 08:00 | 2013-08-21 17:00 | 2013-07-31 08:00 | 2013-08-21 17:00 |  | PT_Normal |  |  |  |  | 8F9AXm9hTAi/3Cusoj3j6w |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30930 | N | N | 10 | GROUND FLOOR |  | 125292 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 503837 | 6359 | 125297 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ACFF4620 | Fixing of Ventilation Equipments | 8178 | 16 | 0 | 200 | 0 | 113.6 | 113.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-23 08:00 | 2014-04-20 17:00 |  | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | kCXPPv9USD+T/I8YepcxmA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30980 | N | N | 15 | FIRST FLOORS |  | 125296 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 113.6 | LABOR- SUBCONTRACTOR
%R | 503838 | 6359 | 125297 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ACFF4625 | Fixing of Split AC | 8178 | 16 | 0 | 160 | 0 | 296 | 296 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-13 08:00 | 2014-05-05 17:00 |  | 2014-04-10 08:00 | 2014-05-03 17:00 | 2014-04-10 08:00 | 2014-05-03 17:00 | 2014-04-10 08:00 | 2014-05-03 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | y234jTZVSRGoGzIZBjjxyQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30980 | N | N | 15 | FIRST FLOORS |  | 125296 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 296 | LABOR- SUBCONTRACTOR
%R | 503839 | 6359 | 125297 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ACFF4615 | Installation AC Pipes | 8178 | 216 | 40 | 160 | 0 | 977.6 | 977.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-04 08:00 | 2014-03-26 17:00 |  | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-01-30 08:00 | 2014-02-23 17:00 | 2014-03-04 08:00 | 2014-03-26 17:00 |  | PT_Normal |  |  |  |  | kbDAFAolSlOnXBHDSABpHw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30980 | N | N | 15 | FIRST FLOORS |  | 125296 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 977.6 | LABOR- SUBCONTRACTOR
%R | 503840 | 6359 | 125298 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ACGF4600 | Installation AC Pipes | 8178 | 392 | 40 | 160 | 0 | 977.6 | 977.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-13 08:00 | 2014-03-08 17:00 |  | 2013-12-16 08:00 | 2014-01-08 17:00 | 2013-12-16 08:00 | 2014-01-08 17:00 | 2013-12-16 08:00 | 2014-01-08 17:00 | 2014-02-13 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | zkXQlwtrTBiSRoyDbk6bsQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30970 | N | N | 10 | GROUND FLOOR |  | 125296 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 977.6 | LABOR- SUBCONTRACTOR
%R | 503841 | 6359 | 125298 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ACGF4605 | Fixing of Ventilation Equipments | 8178 | 256 | 0 | 200 | 0 | 182.4 | 182.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-18 08:00 | 2014-04-15 17:00 |  | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-02-08 08:00 | 2014-03-09 17:00 | 2014-03-18 08:00 | 2014-04-15 17:00 |  | PT_Normal |  |  |  |  | GSldAfMFSlysqzZ+ucIJLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30970 | N | N | 10 | GROUND FLOOR |  | 125296 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 91.2 | LABOR- SUBCONTRACTOR
%R | 503842 | 6359 | 125298 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ACGF4610 | Fixing of Split AC | 8178 | 256 | 40 | 160 | 0 | 296 | 296 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-08 08:00 | 2014-04-30 17:00 |  | 2014-03-02 08:00 | 2014-03-24 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 | 2014-03-02 08:00 | 2014-03-24 17:00 | 2014-04-08 08:00 | 2014-04-30 17:00 |  | PT_Normal |  |  |  |  | veMJtz9XRw+EShgd7Kwmqw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30970 | N | N | 10 | GROUND FLOOR |  | 125296 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 296 | LABOR- SUBCONTRACTOR
%R | 503843 | 6359 | 125299 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ACRF4630 | Installation of Refrigerant Pipes | 8178 | 272 | 0 | 200 | 0 | 409.6 | 409.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-14 08:00 | 2014-05-12 17:00 |  | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-03-05 08:00 | 2014-04-02 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 |  | PT_Normal |  |  |  |  | TmNd697VSHGNwMoC88TEMQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30990 | N | N | 20 | ROOF |  | 125296 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 409.6 | LABOR- SUBCONTRACTOR
%R | 503844 | 6359 | 125299 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ3ACRF4635 | Installation of Condensing Unit | 8178 | 24 | 0 | 200 | 0 | 568 | 568 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-16 08:00 | 2014-05-14 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | g+vnwV8uQayuce1w2DwK5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 30990 | N | N | 20 | ROOF |  | 125296 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 568 | LABOR- SUBCONTRACTOR
%R | 503845 | 6359 | 125302 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5SLEX5105 | Laying of Grass/ green area | 8178 | 128 | 0 | 200 | 0 | 2744 | 2744 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-10 08:00 | 2014-07-08 17:00 |  | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 |  | PT_Normal |  |  |  |  | BaxbPgDtTx+gXGYJovuDKQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31780 | N | N | 25 | SOFT LANDSCAPING |  | 125301 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 2744 | LABOR- SUBCONTRACTOR
%R | 503846 | 6359 | 125302 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5SLEX5110 | Laying of Palm tree | 8178 | 128 | 128 | 200 | 0 | 168 | 168 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | ETlST7MMTQi8wrkJUxAC4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31780 | N | N | 25 | SOFT LANDSCAPING |  | 125301 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 168 | LABOR- SUBCONTRACTOR
%R | 503847 | 6359 | 125303 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5WEEX5030 | Excavation | 8177 | 224 | 0 | 160 | 0 | 64 | 64 | 160 | 40 | 0 | 40 |  |  |  | 2014-04-30 08:00 | 2014-05-22 17:00 |  | 2014-03-29 08:00 | 2014-04-20 17:00 | 2014-03-29 08:00 | 2014-04-20 17:00 | 2014-03-29 08:00 | 2014-04-20 17:00 | 2014-04-30 08:00 | 2014-05-22 17:00 |  | PT_Normal |  |  |  |  | 84vRq5OSRCCP+W+rajcBfA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31760 | N | N | 15 | WATER TANK ENCLOSURE |  | 125301 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 64 | LABOR - CIVIL
%R | 503848 | 6359 | 125303 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5WEEX5035 | Construction of Raft | 8165 | 224 | 0 | 200 | 0 | 840 | 840 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-06 08:00 | 2014-06-03 17:00 |  | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-04-03 08:00 | 2014-05-01 17:00 | 2014-05-06 08:00 | 2014-06-03 17:00 |  | PT_Normal |  |  |  |  | CX7TlEzvQGqnYzx3P0fKYg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31760 | N | N | 15 | WATER TANK ENCLOSURE |  | 125301 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 840 | STEEL FIXERS SK
%R | 503849 | 6359 | 125303 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5WEEX5040 | Block works & Plastering | 8168 | 224 | 0 | 200 | 0 | 512 | 512 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-15 08:00 | 2014-06-12 17:00 |  | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 |  | PT_Normal |  |  |  |  | ab1iSuJSRIO0wFsDoeZN1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31760 | N | N | 15 | WATER TANK ENCLOSURE |  | 125301 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 512 | BLOCK MASON SK
%R | 503850 | 6359 | 125303 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5WEEX5045 | Flooring & Painting | 8178 | 224 | 72 | 200 | 0 | 232 | 232 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-22 08:00 | 2014-06-19 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 |  | PT_Normal |  |  |  |  | rn2CUvVCQmymC31gfKiOgA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31760 | N | N | 15 | WATER TANK ENCLOSURE |  | 125301 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 232 | LABOR- SUBCONTRACTOR
%R | 503851 | 6359 | 125303 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5WEEX5050 | Installation of Steel Gate | 8178 | 152 | 72 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-04 08:00 | 2014-06-26 17:00 |  | 2014-05-13 08:00 | 2014-06-04 17:00 | 2014-05-13 08:00 | 2014-06-04 17:00 | 2014-05-13 08:00 | 2014-06-04 17:00 | 2014-06-04 08:00 | 2014-06-26 17:00 |  | PT_Normal |  |  |  |  | AQ/DJPleSZiBEsmToSTAGQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31760 | N | N | 15 | WATER TANK ENCLOSURE |  | 125301 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 56 | LABOR- SUBCONTRACTOR
%R | 503852 | 6359 | 125303 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 80 | 0 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-10 08:00 | 2014-07-08 17:00 |  | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-06-10 08:00 | 2014-07-08 17:00 |  | PT_Normal |  |  |  |  | LZVEX/sjTKy+R0mUNhB7lw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31760 | N | N | 15 | WATER TANK ENCLOSURE |  | 125301 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 336 | LABOR- SUBCONTRACTOR
%R | 503853 | 6359 | 125303 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 72 | 0 | 200 | 0 | 203.2 | 203.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-06-07 08:00 | 2014-07-05 17:00 | 2014-06-07 08:00 | 2014-07-05 17:00 | 2014-06-07 08:00 | 2014-07-05 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | pu3mJn8mTj2oGnxiGj0eMg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31760 | N | N | 15 | WATER TANK ENCLOSURE |  | 125301 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 203.2 | LABOR- SUBCONTRACTOR
%R | 503854 | 6359 | 125304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5MSEX5020 | Construction Entrance Ramp | 8164 | 128 | 0 | 200 | 0 | 656 | 656 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-03 08:00 | 2014-05-31 17:00 |  | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-04-14 08:00 | 2014-05-12 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 |  | PT_Normal |  |  |  |  | GdTC8aqqTDy9ppiHqxEKpg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31750 | N | N | 10 | MISCELLANEOUS |  | 125301 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 656 | SCREED MASON SK
%R | 503855 | 6359 | 125304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5MSEX5025 | SS.Handrails and Balustrades | 8178 | 152 | 0 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-24 08:00 | 2014-06-15 17:00 |  | 2014-05-01 08:00 | 2014-05-24 17:00 | 2014-05-01 08:00 | 2014-05-24 17:00 | 2014-05-01 08:00 | 2014-05-24 17:00 | 2014-05-24 08:00 | 2014-06-15 17:00 |  | PT_Normal |  |  |  |  | P2OQDPxgQ/6aanZ2BAuLIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31750 | N | N | 10 | MISCELLANEOUS |  | 125301 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 56 | LABOR- SUBCONTRACTOR
%R | 503856 | 6359 | 125304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5MSEX5015 | Construction of grease Trap | 8178 | 64 | 0 | 160 | 0 | 56 | 56 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-04-28 17:00 |  | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-03-27 08:00 | 2014-04-19 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 |  | PT_Normal |  |  |  |  | d43R3spNS9+MmGW6QtkFCQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31750 | N | N | 10 | MISCELLANEOUS |  | 125301 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 56 | LABOR- SUBCONTRACTOR
%R | 503857 | 6359 | 125304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5MSEX5000 | Construction of Manholes | 8172 | 64 | 0 | 200 | 0 | 528 | 528 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-03 08:00 | 2014-03-31 17:00 |  | 2014-02-22 08:00 | 2014-03-22 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 | 2014-03-03 08:00 | 2014-03-31 17:00 |  | PT_Normal |  |  |  |  | O9xqvp7oQg2oJvEZI3ac2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31750 | N | N | 10 | MISCELLANEOUS |  | 125301 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 264 | MANHOLES SK
%R | 503858 | 6359 | 125304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5MSEX5005 | Construction of Soak pit, Chambers | 8172 | 64 | 0 | 200 | 0 | 176 | 176 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-14 17:00 |  | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-03-08 08:00 | 2014-04-05 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 |  | PT_Normal |  |  |  |  | ggWggXKBTIKRZID+izIuWA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31750 | N | N | 10 | MISCELLANEOUS |  | 125301 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 176 | MANHOLES SK
%R | 503859 | 6359 | 125304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5MSEX5010 | Telephone cable laying | 8177 | 64 | 0 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-29 08:00 | 2014-05-27 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-29 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | H4yiK8bqRoGOjYVTwbmlKw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31750 | N | N | 10 | MISCELLANEOUS |  | 125301 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 500 | LABOR - CIVIL
%R | 503860 | 6359 | 125304 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 736 | 64 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-14 08:00 | 2014-11-11 17:00 |  | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-10-14 08:00 | 2014-11-11 17:00 |  | PT_Normal |  |  |  |  | PLtkaqTsTGisiUgCLABIUA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:44 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31750 | N | N | 10 | MISCELLANEOUS |  | 125301 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 400 | LABOR- SUBCONTRACTOR
%R | 503861 | 6359 | 125305 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5HDEX5090 | kerb works | 8173 | 128 | 0 | 160 | 0 | 344 | 344 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-08 17:00 |  | 2014-04-28 08:00 | 2014-05-20 17:00 | 2014-04-28 08:00 | 2014-05-20 17:00 | 2014-04-28 08:00 | 2014-05-20 17:00 | 2014-05-17 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | FO+QQCk1TZqX5u+kIiCyQA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31770 | N | N | 20 | HARD LANDSCAPING |  | 125301 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 344 | KERBSTONE MASON SK
%R | 503862 | 6359 | 125305 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5HDEX5095 | Cobble Stone Works | 8170 | 128 | 0 | 160 | 0 | 200 | 200 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-19 17:00 |  | 2014-05-10 08:00 | 2014-06-01 17:00 | 2014-05-10 08:00 | 2014-06-01 17:00 | 2014-05-10 08:00 | 2014-06-01 17:00 | 2014-05-28 08:00 | 2014-06-19 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31770 | N | N | 20 | HARD LANDSCAPING |  | 125301 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 200 | TILE MASON SK
%R | 503863 | 6359 | 125305 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5HDEX5100 | Interlock works | 8174 | 128 | 0 | 160 | 0 | 232 | 232 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-04 08:00 | 2014-06-26 17:00 |  | 2014-05-17 08:00 | 2014-06-08 17:00 | 2014-05-17 08:00 | 2014-06-08 17:00 | 2014-05-17 08:00 | 2014-06-08 17:00 | 2014-06-04 08:00 | 2014-06-26 17:00 |  | PT_Normal |  |  |  |  | HMynhg7bSJWYzvzJzE+WkA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31770 | N | N | 20 | HARD LANDSCAPING |  | 125301 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 232 | INTERLOCK MASON SK
%R | 503864 | 6359 | 125306 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | dpGcRzphSf6tYhMqCHTmfw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31790 | N | N | 30 | TESTING AND COMMISSIONING |  | 125300 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 503865 | 6359 | 125306 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 0 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | 9GBFuBzuTGKxLQfqlYNj+w |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31790 | N | N | 30 | TESTING AND COMMISSIONING |  | 125300 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 750 | LABOR- SUBCONTRACTOR
%R | 503866 | 6359 | 125306 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-16 08:00 | 2014-08-17 17:00 |  | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 | 2014-07-16 08:00 | 2014-08-17 17:00 |  | PT_Normal |  |  |  |  | r3ZkyYijSvqnrcC1atlm4g |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31790 | N | N | 30 | TESTING AND COMMISSIONING |  | 125300 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 503867 | 6359 | 125309 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ELGF4030 | Installation of Telephone System | 8178 | 144 | 40 | 160 | 0 | 520 | 520 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-08 17:00 |  | 2014-04-26 08:00 | 2014-05-18 17:00 | 2014-04-26 08:00 | 2014-05-18 17:00 | 2014-04-26 08:00 | 2014-05-18 17:00 | 2014-05-17 08:00 | 2014-06-08 17:00 |  | PT_Normal |  |  |  |  | vXI4wPK+S/KMxyUJbzkJuw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31610 | N | N | 10 | GROUND FLOOR |  | 125308 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 520 | LABOR- SUBCONTRACTOR
%R | 503868 | 6359 | 125309 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 216 | 0 | 200 | 0 | 1222.4 | 1222.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-16 17:00 |  | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-01-14 08:00 | 2014-02-12 17:00 | 2014-02-16 08:00 | 2014-03-16 17:00 |  | PT_Normal |  |  |  |  | ZsVnsLCJTsavwR5C6vSLbQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31610 | N | N | 10 | GROUND FLOOR |  | 125308 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1222.4 | LABOR- SUBCONTRACTOR
%R | 503869 | 6359 | 125309 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ELGF4005 | Cable tray & trunking installation | 8178 | 360 | 0 | 160 | 0 | 1318.4 | 1318.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-03-20 08:00 | 2014-04-12 17:00 |  | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-01-26 08:00 | 2014-02-18 17:00 | 2014-03-20 08:00 | 2014-04-12 17:00 |  | PT_Normal |  |  |  |  | PSaMnZgPQZuz0gz7xc1eDA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31610 | N | N | 10 | GROUND FLOOR |  | 125308 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1318.4 | LABOR- SUBCONTRACTOR
%R | 503870 | 6359 | 125309 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ELGF4010 | Installation of wiring & Main Cabling | 8178 | 360 | 216 | 200 | 0 | 296 | 296 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-29 08:00 | 2014-04-26 17:00 |  | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-02-03 08:00 | 2014-03-04 17:00 | 2014-03-29 08:00 | 2014-04-26 17:00 |  | PT_Normal |  |  |  |  | XiKcvGSdSSGEJ+enq6MGFA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31610 | N | N | 10 | GROUND FLOOR |  | 125308 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 148 | LABOR- SUBCONTRACTOR
%R | 503871 | 6359 | 125309 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 144 | 0 | 160 | 0 | 227.2 | 227.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-05 08:00 | 2014-05-27 17:00 |  | 2014-04-14 08:00 | 2014-05-06 17:00 | 2014-04-14 08:00 | 2014-05-06 17:00 | 2014-04-14 08:00 | 2014-05-06 17:00 | 2014-05-05 08:00 | 2014-05-27 17:00 |  | PT_Normal |  |  |  |  | tt8IQu6bQEGfcptT8qH3Ww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31610 | N | N | 10 | GROUND FLOOR |  | 125308 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 227.2 | LABOR- SUBCONTRACTOR
%R | 503872 | 6359 | 125309 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 200 | 0 | 200 | 0 | 1651.2 | 1651.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-25 08:00 | 2014-06-22 17:00 |  | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-04-26 08:00 | 2014-05-24 17:00 | 2014-05-25 08:00 | 2014-06-22 17:00 |  | PT_Normal |  |  |  |  | /DmqOFfiQMibS3EeSMinZA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31610 | N | N | 10 | GROUND FLOOR |  | 125308 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1651.2 | LABOR- SUBCONTRACTOR
%R | 503873 | 6359 | 125309 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 240 | 0 | 200 | 0 | 1075.2 | 1075.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-06-10 17:00 |  | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-05-13 08:00 | 2014-06-10 17:00 |  | PT_Normal |  |  |  |  | ri/Z7+HbSkiUql5Vuxmb6A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31610 | N | N | 10 | GROUND FLOOR |  | 125308 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1075.2 | LABOR- SUBCONTRACTOR
%R | 503874 | 6359 | 125310 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ELRF4070 | Installation of Isolator | 8178 | 8 | 0 | 144 | 0 | 412.8 | 412.8 | 144 | 0 | 0 | 0 |  |  |  | 2014-06-14 08:00 | 2014-07-03 17:00 |  | 2014-06-12 08:00 | 2014-07-02 17:00 | 2014-06-12 08:00 | 2014-07-02 17:00 | 2014-06-12 08:00 | 2014-07-02 17:00 | 2014-06-14 08:00 | 2014-07-03 17:00 |  | PT_Normal |  |  |  |  | fxQXCvqHQqusZqgMpGB1gA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31630 | N | N | 20 | ROOF |  | 125308 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 412.8 | LABOR- SUBCONTRACTOR
%R | 503875 | 6359 | 125310 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ELRF4075 | Installation of TV Dish Antenna | 8178 | 8 | 8 | 184 | 0 | 732.8 | 732.8 | 184 | 0 | 0 | 0 |  |  |  | 2014-06-19 08:00 | 2014-07-15 17:00 |  | 2014-06-18 08:00 | 2014-07-14 17:00 | 2014-06-18 08:00 | 2014-07-14 17:00 | 2014-06-18 08:00 | 2014-07-14 17:00 | 2014-06-19 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | vIQgvQZkQ2alDUXu24tQIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31630 | N | N | 20 | ROOF |  | 125308 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 732.8 | LABOR- SUBCONTRACTOR
%R | 503876 | 6359 | 125311 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 88 | 0 | 200 | 0 | 1222.4 | 1222.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-04-08 17:00 |  | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-02-26 08:00 | 2014-03-26 17:00 | 2014-03-11 08:00 | 2014-04-08 17:00 |  | PT_Normal |  |  |  |  | 1GkQ6ql0QOyiSnji5SGa1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31620 | N | N | 15 | FIRST FLOORS |  | 125308 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 611.2 | LABOR- SUBCONTRACTOR
%R | 503877 | 6359 | 125311 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ELFF4040 | Cable tray & trunking installation | 8178 | 232 | 16 | 160 | 0 | 1318.4 | 1318.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-13 08:00 | 2014-05-05 17:00 |  | 2014-03-10 08:00 | 2014-04-01 17:00 | 2014-03-10 08:00 | 2014-04-01 17:00 | 2014-03-10 08:00 | 2014-04-01 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | aE3hPSQjRfiQ2NbbwZtrqA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31620 | N | N | 15 | FIRST FLOORS |  | 125308 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1318.4 | LABOR- SUBCONTRACTOR
%R | 503878 | 6359 | 125311 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ELFF4045 | Installation of wiring & Main Cabling | 8178 | 216 | 0 | 200 | 0 | 296 | 296 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-21 08:00 | 2014-05-19 17:00 |  | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-03-20 08:00 | 2014-04-17 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | cCVR33lRSDWn1p0lL5trjQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31620 | N | N | 15 | FIRST FLOORS |  | 125308 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 296 | LABOR- SUBCONTRACTOR
%R | 503879 | 6359 | 125311 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 24 | 16 | 160 | 0 | 227.2 | 227.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-25 08:00 | 2014-06-16 17:00 |  | 2014-05-21 08:00 | 2014-06-12 17:00 | 2014-05-21 08:00 | 2014-06-12 17:00 | 2014-05-21 08:00 | 2014-06-12 17:00 | 2014-05-25 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | 1vurQqu8R/e0VkKRRZEDBA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31620 | N | N | 15 | FIRST FLOORS |  | 125308 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 227.2 | LABOR- SUBCONTRACTOR
%R | 503880 | 6359 | 125311 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 8 | 0 | 200 | 0 | 1651.2 | 1651.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-31 08:00 | 2014-06-28 17:00 |  | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-05-29 08:00 | 2014-06-26 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | EWeuwciKQai9CzVNZDPyTg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31620 | N | N | 15 | FIRST FLOORS |  | 125308 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1651.2 | LABOR- SUBCONTRACTOR
%R | 503881 | 6359 | 125311 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 8 | 0 | 200 | 0 | 1008 | 1008 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-05-18 08:00 | 2014-06-15 17:00 | 2014-05-18 08:00 | 2014-06-15 17:00 | 2014-05-18 08:00 | 2014-06-15 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | gTNLhKU/R6Sh6gY0+r0t1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31620 | N | N | 15 | FIRST FLOORS |  | 125308 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1008 | LABOR- SUBCONTRACTOR
%R | 503882 | 6359 | 125311 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ELFF4050 | Installation of Telephone System | 8178 | 64 | 56 | 200 | 0 | 451.2 | 451.2 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-28 08:00 | 2014-06-25 17:00 |  | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 | 2014-05-28 08:00 | 2014-06-25 17:00 |  | PT_Normal |  |  |  |  | a0zZ8tM1SeaLjKcHWCqf0w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31620 | N | N | 15 | FIRST FLOORS |  | 125308 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 451.2 | LABOR- SUBCONTRACTOR
%R | 503883 | 6359 | 125313 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 0 | 0 | 144 | 0 | 441.6 | 441.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-03-10 08:00 | 2014-03-30 17:00 |  | 2014-03-10 08:00 | 2014-03-30 17:00 | 2014-03-10 08:00 | 2014-03-30 17:00 | 2014-03-10 08:00 | 2014-03-30 17:00 | 2014-03-10 08:00 | 2014-03-30 17:00 |  | PT_Normal |  |  |  |  | oZiSLR3JQ6e4x62Mtdn4SQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31660 | N | N | 15 | FIRST FLOORS |  | 125312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 441.6 | LABOR- SUBCONTRACTOR
%R | 503884 | 6359 | 125313 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5PLFF4330 | Installation of Drainage pipes & testing | 8178 | 176 | 56 | 144 | 0 | 177.6 | 177.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-04-05 08:00 | 2014-04-24 17:00 |  | 2014-03-10 08:00 | 2014-03-30 17:00 | 2014-03-10 08:00 | 2014-03-30 17:00 | 2014-03-10 08:00 | 2014-03-30 17:00 | 2014-04-05 08:00 | 2014-04-24 17:00 |  | PT_Normal |  |  |  |  | eBcoWufVSK+tivFMHZ9QRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31660 | N | N | 15 | FIRST FLOORS |  | 125312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 177.6 | LABOR- SUBCONTRACTOR
%R | 503885 | 6359 | 125313 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5PLFF4335 | Sanitary Fittings & Accessories | 8178 | 40 | 0 | 160 | 0 | 67.2 | 67.2 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-31 08:00 | 2014-06-22 17:00 |  | 2014-05-25 08:00 | 2014-06-16 17:00 | 2014-05-25 08:00 | 2014-06-16 17:00 | 2014-05-25 08:00 | 2014-06-16 17:00 | 2014-05-31 08:00 | 2014-06-22 17:00 |  | PT_Normal |  |  |  |  | ZqRxtiX6Q+2xERALHcga6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31660 | N | N | 15 | FIRST FLOORS |  | 125312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 503886 | 6359 | 125313 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5PLFF4340 | Installation of Water Heater | 8178 | 40 | 32 | 120 | 0 | 67.2 | 67.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-06-28 17:00 |  | 2014-06-05 08:00 | 2014-06-22 17:00 | 2014-06-05 08:00 | 2014-06-22 17:00 | 2014-06-05 08:00 | 2014-06-22 17:00 | 2014-06-11 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | tTNZb7FmQ76+v/zCjmXSiQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31660 | N | N | 15 | FIRST FLOORS |  | 125312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 503887 | 6359 | 125314 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 448 | 240 | 120 | 0 | 110.4 | 110.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-02 08:00 | 2014-06-18 17:00 |  | 2014-03-29 08:00 | 2014-04-14 17:00 | 2014-03-29 08:00 | 2014-04-14 17:00 | 2014-03-29 08:00 | 2014-04-14 17:00 | 2014-06-02 08:00 | 2014-06-18 17:00 |  | PT_Normal |  |  |  |  | XqWaPZK3QS6X9RKCS845ew |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31670 | N | N | 20 | ROOF |  | 125312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 110.4 | LABOR- SUBCONTRACTOR
%R | 503888 | 6359 | 125314 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5PLRF4350 | Installation of Rain water Pipes | 8178 | 208 | 80 | 120 | 0 | 67.2 | 67.2 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-06-28 17:00 |  | 2014-05-12 08:00 | 2014-05-28 17:00 | 2014-05-12 08:00 | 2014-05-28 17:00 | 2014-05-12 08:00 | 2014-05-28 17:00 | 2014-06-11 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | xbC2J0AORdeaaSAOZbHaLQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31670 | N | N | 20 | ROOF |  | 125312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 503889 | 6359 | 125314 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 8 | 0 | 200 | 0 | 336 | 336 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-16 08:00 | 2014-07-14 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | fOzzMreURx6WnFimj1Qdtg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31670 | N | N | 20 | ROOF |  | 125312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 336 | LABOR- SUBCONTRACTOR
%R | 503890 | 6359 | 125315 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 144 | 0 | 144 | 0 | 441.6 | 441.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-16 08:00 | 2014-03-08 17:00 |  | 2014-01-25 08:00 | 2014-02-15 17:00 | 2014-01-25 08:00 | 2014-02-15 17:00 | 2014-01-25 08:00 | 2014-02-15 17:00 | 2014-02-16 08:00 | 2014-03-08 17:00 |  | PT_Normal |  |  |  |  | mAgG7YRqTKyA73fjlZA7mg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31650 | N | N | 10 | GROUND FLOOR |  | 125312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 441.6 | LABOR- SUBCONTRACTOR
%R | 503891 | 6359 | 125315 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5PLGF4310 | Installation of Drainage pipes &testing | 8178 | 168 | 104 | 144 | 0 | 177.6 | 177.6 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-19 08:00 | 2014-03-11 17:00 |  | 2014-01-25 08:00 | 2014-02-15 17:00 | 2014-01-25 08:00 | 2014-02-15 17:00 | 2014-01-25 08:00 | 2014-02-15 17:00 | 2014-02-19 08:00 | 2014-03-11 17:00 |  | PT_Normal |  |  |  |  | 2+4kaR1vRBmc5wjyzocmdA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31650 | N | N | 10 | GROUND FLOOR |  | 125312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 177.6 | LABOR- SUBCONTRACTOR
%R | 503892 | 6359 | 125315 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5PLGF4315 | Sanitary Fittings & Accessories | 8178 | 360 | 0 | 160 | 0 | 134.4 | 134.4 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-09 17:00 |  | 2014-04-26 08:00 | 2014-05-18 17:00 | 2014-04-26 08:00 | 2014-05-18 17:00 | 2014-04-26 08:00 | 2014-05-18 17:00 | 2014-06-17 08:00 | 2014-07-09 17:00 |  | PT_Normal |  |  |  |  | z1opUDO4T1mU3BlRgqGq4w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31650 | N | N | 10 | GROUND FLOOR |  | 125312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 503893 | 6359 | 125315 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5PLGF4320 | Installation of Water Heater | 8178 | 360 | 80 | 120 | 0 | 134.4 | 134.4 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-15 17:00 |  | 2014-05-07 08:00 | 2014-05-24 17:00 | 2014-05-07 08:00 | 2014-05-24 17:00 | 2014-05-07 08:00 | 2014-05-24 17:00 | 2014-06-29 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | LjauT7fgQ0a5xmR/K64OSw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31650 | N | N | 10 | GROUND FLOOR |  | 125312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 134.4 | LABOR- SUBCONTRACTOR
%R | 503894 | 6359 | 125315 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 0 | 0 | 128 | 0 | 67.2 | 67.2 | 128 | 0 | 0 | 0 |  |  |  | 2013-10-01 08:00 | 2013-10-21 17:00 |  | 2013-10-01 08:00 | 2013-10-21 17:00 | 2013-10-01 08:00 | 2013-10-21 17:00 | 2013-10-01 08:00 | 2013-10-21 17:00 | 2013-10-01 08:00 | 2013-10-21 17:00 |  | PT_Normal |  |  |  |  | n2RV86MhRXqyQCscWpPHLQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31650 | N | N | 10 | GROUND FLOOR |  | 125312 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 67.2 | LABOR- SUBCONTRACTOR
%R | 503895 | 6359 | 125317 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ACRF4630 | Installation of Refrigerant Pipes | 8178 | 272 | 0 | 200 | 0 | 409.6 | 409.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-07-09 17:00 |  | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-06-11 08:00 | 2014-07-09 17:00 |  | PT_Normal |  |  |  |  | XFeHwb5jSP+cBMWutDfxiw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31710 | N | N | 20 | ROOF |  | 125316 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 409.6 | LABOR- SUBCONTRACTOR
%R | 503896 | 6359 | 125317 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ACRF4635 | Installation of Condensing Unit | 8178 | 24 | 0 | 200 | 0 | 568 | 568 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-14 08:00 | 2014-07-12 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | M4ei5OdHQHSMqnkC4v6EFg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31710 | N | N | 20 | ROOF |  | 125316 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 568 | LABOR- SUBCONTRACTOR
%R | 503897 | 6359 | 125318 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ACFF4615 | Installation AC Pipes | 8178 | 216 | 40 | 160 | 0 | 977.6 | 977.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-01 08:00 | 2014-05-24 17:00 |  | 2014-03-31 08:00 | 2014-04-22 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 | 2014-03-31 08:00 | 2014-04-22 17:00 | 2014-05-01 08:00 | 2014-05-24 17:00 |  | PT_Normal |  |  |  |  | dFqxfMLgQ4G80d31zke3HQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31700 | N | N | 15 | FIRST FLOORS |  | 125316 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 977.6 | LABOR- SUBCONTRACTOR
%R | 503898 | 6359 | 125318 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ACFF4620 | Fixing of Ventilation Equipments | 8178 | 16 | 0 | 200 | 0 | 113.6 | 113.6 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-20 08:00 | 2014-06-17 17:00 |  | 2014-05-18 08:00 | 2014-06-15 17:00 | 2014-05-18 08:00 | 2014-06-15 17:00 | 2014-05-18 08:00 | 2014-06-15 17:00 | 2014-05-20 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | 0MaaR37xRw+qsPXcQgMKEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31700 | N | N | 15 | FIRST FLOORS |  | 125316 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 113.6 | LABOR- SUBCONTRACTOR
%R | 503899 | 6359 | 125318 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ACFF4625 | Fixing of Split AC | 8178 | 16 | 0 | 160 | 0 | 296 | 296 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-10 08:00 | 2014-07-02 17:00 |  | 2014-06-08 08:00 | 2014-06-30 17:00 | 2014-06-08 08:00 | 2014-06-30 17:00 | 2014-06-08 08:00 | 2014-06-30 17:00 | 2014-06-10 08:00 | 2014-07-02 17:00 |  | PT_Normal |  |  |  |  | Y5e4ecBBTLu4zfN8Sub4Tg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31700 | N | N | 15 | FIRST FLOORS |  | 125316 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 296 | LABOR- SUBCONTRACTOR
%R | 503900 | 6359 | 125319 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ACGF4600 | Installation AC Pipes | 8178 | 392 | 40 | 160 | 0 | 977.6 | 977.6 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-13 08:00 | 2014-05-05 17:00 |  | 2014-02-15 08:00 | 2014-03-09 17:00 | 2014-02-15 08:00 | 2014-03-09 17:00 | 2014-02-15 08:00 | 2014-03-09 17:00 | 2014-04-13 08:00 | 2014-05-05 17:00 |  | PT_Normal |  |  |  |  | RlLq8SIWQfq+Mdqah0wwcQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31690 | N | N | 10 | GROUND FLOOR |  | 125316 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 977.6 | LABOR- SUBCONTRACTOR
%R | 503901 | 6359 | 125319 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ACGF4605 | Fixing of Ventilation Equipments | 8178 | 256 | 0 | 200 | 0 | 182.4 | 182.4 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-15 08:00 | 2014-06-12 17:00 |  | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-04-08 08:00 | 2014-05-06 17:00 | 2014-05-15 08:00 | 2014-06-12 17:00 |  | PT_Normal |  |  |  |  | 01f8oBusTnSN5c7PzUWBAQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31690 | N | N | 10 | GROUND FLOOR |  | 125316 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 182.4 | LABOR- SUBCONTRACTOR
%R | 503902 | 6359 | 125319 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ACGF4610 | Fixing of Split AC | 8178 | 256 | 40 | 160 | 0 | 296 | 296 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-06-28 17:00 |  | 2014-04-29 08:00 | 2014-05-21 17:00 | 2014-04-29 08:00 | 2014-05-21 17:00 | 2014-04-29 08:00 | 2014-05-21 17:00 | 2014-06-05 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | jEmyVHAiQSSPzun08vIGXw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31690 | N | N | 10 | GROUND FLOOR |  | 125316 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 296 | LABOR- SUBCONTRACTOR
%R | 503903 | 6359 | 125322 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STFF2020 | Column-Rebar & Formwork | 8165 | 16 | 0 | 200 | 0 | 3580.5 | 3580.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-12-12 08:00 | 2014-01-11 17:00 |  | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-10 08:00 | 2014-01-08 17:00 | 2013-12-12 08:00 | 2014-01-11 17:00 |  | PT_Normal |  |  |  |  | Nhv10ApQTPaWsirXMjNiwA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31490 | N | N | 15 | FIRST FLOORS |  | 125321 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 3580.5 | STEEL FIXERS SK
%R | 503904 | 6359 | 125322 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STFF2025 | Column-Concrete | 8167 | 32 | 0 | 192 | 0 | 224 | 224 | 192 | 0 | 0 | 0 |  |  |  | 2013-12-25 08:00 | 2014-01-21 17:00 |  | 2013-12-21 08:00 | 2014-01-16 17:00 | 2013-12-21 08:00 | 2014-01-16 17:00 | 2013-12-21 08:00 | 2014-01-16 17:00 | 2013-12-25 08:00 | 2014-01-21 17:00 |  | PT_Normal |  |  |  |  | WKae8j2ESWSAcp0+uW9pLA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31490 | N | N | 15 | FIRST FLOORS |  | 125321 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 224 | CONCRETE MASON SK
%R | 503905 | 6359 | 125322 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 32 | 0 | 200 | 0 | 16119.25 | 16119.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-09 08:00 | 2014-02-06 17:00 |  | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-05 08:00 | 2014-02-02 17:00 | 2014-01-09 08:00 | 2014-02-06 17:00 |  | PT_Normal |  |  |  |  | FvdlaGvDT62fifdEsWcf0w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31490 | N | N | 15 | FIRST FLOORS |  | 125321 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 16119.25 | STEEL FIXERS SK
%R | 503906 | 6359 | 125322 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STFF2035 | Beam, Stairs ,Slab-Concrete | 8167 | 32 | 0 | 112 | 0 | 1141 | 1141 | 112 | 0 | 0 | 0 |  |  |  | 2014-01-26 08:00 | 2014-02-10 17:00 |  | 2014-01-21 08:00 | 2014-02-05 17:00 | 2014-01-21 08:00 | 2014-02-05 17:00 | 2014-01-21 08:00 | 2014-02-05 17:00 | 2014-01-26 08:00 | 2014-02-10 17:00 |  | PT_Normal |  |  |  |  | siu9Sd61SbSQ5Gn/rbTXgQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31490 | N | N | 15 | FIRST FLOORS |  | 125321 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1141 | CONCRETE MASON SK
%R | 503907 | 6359 | 125323 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STGF2000 | Column-Rebar & Formwork | 8165 | 0 | 0 | 200 | 0 | 4046 | 4046 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-29 08:00 | 2013-11-26 17:00 |  | 2013-10-29 08:00 | 2013-11-26 17:00 | 2013-10-29 08:00 | 2013-11-26 17:00 | 2013-10-29 08:00 | 2013-11-26 17:00 | 2013-10-29 08:00 | 2013-11-26 17:00 |  | PT_Normal |  |  |  |  | Oa2a3BHWQfC/u5jQgABCvw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31480 | N | N | 10 | GROUND FLOOR |  | 125321 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10 |  | 4046 | STEEL FIXERS SK
%R | 503908 | 6359 | 125323 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STGF2005 | Column-Concrete | 8167 | 16 | 0 | 192 | 0 | 255.5 | 255.5 | 192 | 0 | 0 | 0 |  |  |  | 2013-11-09 08:00 | 2013-12-05 17:00 |  | 2013-11-06 08:00 | 2013-12-03 17:00 | 2013-11-06 08:00 | 2013-12-03 17:00 | 2013-11-06 08:00 | 2013-12-03 17:00 | 2013-11-09 08:00 | 2013-12-05 17:00 |  | PT_Normal |  |  |  |  | DeiiRbxxTe26EYjbIPSpbg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31480 | N | N | 10 | GROUND FLOOR |  | 125321 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11 |  | 255.5 | CONCRETE MASON SK
%R | 503909 | 6359 | 125323 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 8165 | 16 | 0 | 200 | 0 | 16829.75 | 16829.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-11-24 08:00 | 2013-12-23 17:00 |  | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-21 08:00 | 2013-12-21 17:00 | 2013-11-24 08:00 | 2013-12-23 17:00 |  | PT_Normal |  |  |  |  | ukpLHp5BQJaY+/rGdYMkjg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31480 | N | N | 10 | GROUND FLOOR |  | 125321 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP11; period 2: 2013-AP12 |  | 8414.875 | STEEL FIXERS SK
%R | 503910 | 6359 | 125323 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STGF2015 | Beam, Stairs ,Slab-Concrete | 8167 | 16 | 0 | 112 | 0 | 1295 | 1295 | 112 | 0 | 0 | 0 |  |  |  | 2013-12-10 08:00 | 2013-12-26 17:00 |  | 2013-12-08 08:00 | 2013-12-24 17:00 | 2013-12-08 08:00 | 2013-12-24 17:00 | 2013-12-08 08:00 | 2013-12-24 17:00 | 2013-12-10 08:00 | 2013-12-26 17:00 |  | PT_Normal |  |  |  |  | 4oKI9cBESn6Qp0+KFCh4FA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31480 | N | N | 10 | GROUND FLOOR |  | 125321 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP12 |  | 1295 | CONCRETE MASON SK
%R | 503911 | 6359 | 125324 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STRF2040 | Column-Rebar & Formwork | 8165 | 64 | 0 | 144 | 0 | 1205.75 | 1205.75 | 144 | 0 | 0 | 0 |  |  |  | 2014-02-02 08:00 | 2014-02-23 17:00 |  | 2014-01-23 08:00 | 2014-02-13 17:00 | 2014-01-23 08:00 | 2014-02-13 17:00 | 2014-01-23 08:00 | 2014-02-13 17:00 | 2014-02-02 08:00 | 2014-02-23 17:00 |  | PT_Normal |  |  |  |  | VHKmaX+JTDKWpahaOP7jcg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31500 | N | N | 20 | ROOF |  | 125321 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 1205.75 | STEEL FIXERS SK
%R | 503912 | 6359 | 125324 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STRF2045 | Column-Concrete | 8167 | 64 | 0 | 136 | 0 | 52.5 | 52.5 | 136 | 0 | 0 | 0 |  |  |  | 2014-02-05 08:00 | 2014-02-25 17:00 |  | 2014-01-27 08:00 | 2014-02-16 17:00 | 2014-01-27 08:00 | 2014-02-16 17:00 | 2014-01-27 08:00 | 2014-02-16 17:00 | 2014-02-05 08:00 | 2014-02-25 17:00 |  | PT_Normal |  |  |  |  | aUIpbwTZRw+sQ/fCPUX5ng |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31500 | N | N | 20 | ROOF |  | 125321 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 52.5 | CONCRETE MASON SK
%R | 503913 | 6359 | 125324 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STRF2050 | Slab-Rebar & Formwork - Head Room | 8165 | 64 | 0 | 160 | 0 | 2735.25 | 2735.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-02-08 08:00 | 2014-03-03 17:00 |  | 2014-01-29 08:00 | 2014-02-22 17:00 | 2014-01-29 08:00 | 2014-02-22 17:00 | 2014-01-29 08:00 | 2014-02-22 17:00 | 2014-02-08 08:00 | 2014-03-03 17:00 |  | PT_Normal |  |  |  |  | fUXafp9IQaOB3uoBuUXkOQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31500 | N | N | 20 | ROOF |  | 125321 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 2735.25 | STEEL FIXERS SK
%R | 503914 | 6359 | 125324 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STRF2055 | Slab-Concrete-Head room | 8167 | 64 | 0 | 104 | 0 | 252 | 252 | 104 | 0 | 0 | 0 |  |  |  | 2014-02-19 08:00 | 2014-03-05 17:00 |  | 2014-02-09 08:00 | 2014-02-24 17:00 | 2014-02-09 08:00 | 2014-02-24 17:00 | 2014-02-09 08:00 | 2014-02-24 17:00 | 2014-02-19 08:00 | 2014-03-05 17:00 |  | PT_Normal |  |  |  |  | us27c54xSECtzY3r5QGWWA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43440 |  |  |  |  | CONCRETE MASON SK | J306 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31500 | N | N | 20 | ROOF |  | 125321 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 252 | CONCRETE MASON SK
%R | 503915 | 6359 | 125324 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STRF2060 | Construction of Parapets | 8168 | 448 | 32 | 200 | 0 | 2200 | 2200 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-19 08:00 | 2014-05-17 17:00 |  | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-02-12 08:00 | 2014-03-12 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 |  | PT_Normal |  |  |  |  | XX49zBtxSQKoafRpzwvv7Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31500 | N | N | 20 | ROOF |  | 125321 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 1100 | BLOCK MASON SK
%R | 503916 | 6359 | 125324 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STRF2065 | Construction of up stands/Plinth | 8165 | 416 | 0 | 200 | 0 | 554.75 | 554.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-24 08:00 | 2014-05-22 17:00 |  | 2014-02-23 08:00 | 2014-03-23 17:00 | 2014-02-23 08:00 | 2014-03-23 17:00 | 2014-02-23 08:00 | 2014-03-23 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 |  | PT_Normal |  |  |  |  | ywK0dtnLTDyBA4O/0pQVww |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31500 | N | N | 20 | ROOF |  | 125321 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 277.375 | STEEL FIXERS SK
%R | 503917 | 6359 | 125326 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STUG1035 | Backfilling Upto Grade Beam Bottom | 8177 | 0 | 0 | 200 | 0 | 1041 | 1041 | 200 | 825 | 0 | 825 |  |  |  | 2013-08-22 08:00 | 2013-09-19 17:00 |  | 2013-08-22 08:00 | 2013-09-19 17:00 | 2013-08-22 08:00 | 2013-09-19 17:00 | 2013-08-22 08:00 | 2013-09-19 17:00 | 2013-08-22 08:00 | 2013-09-19 17:00 |  | PT_Normal |  |  |  |  | iTohvNiZR9qDscgEBGurdw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31460 | N | N | 10 | UPTO GRADE SLAB |  | 125325 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08 |  | 1041 | LABOR - CIVIL
%R | 503918 | 6359 | 125326 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STUG1040 | Construction of Grade Beams | 8163 | 0 | 0 | 200 | 0 | 7568.75 | 7568.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-09-08 08:00 | 2013-10-06 17:00 |  | 2013-09-08 08:00 | 2013-10-06 17:00 | 2013-09-08 08:00 | 2013-10-06 17:00 | 2013-09-08 08:00 | 2013-10-06 17:00 | 2013-09-08 08:00 | 2013-10-06 17:00 |  | PT_Normal |  |  |  |  | QUb58SxDTBmneCCX/dtiDA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31460 | N | N | 10 | UPTO GRADE SLAB |  | 125325 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP09 |  | 7568.75 | BLINDING MASON SK
%R | 503919 | 6359 | 125326 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STUG1045 | Construction of slab on grade | 8163 | 0 | 0 | 200 | 0 | 4422 | 4422 | 200 | 0 | 0 | 0 |  |  |  | 2013-10-10 08:00 | 2013-11-10 17:00 |  | 2013-10-10 08:00 | 2013-11-10 17:00 | 2013-10-10 08:00 | 2013-11-10 17:00 | 2013-10-10 08:00 | 2013-11-10 17:00 | 2013-10-10 08:00 | 2013-11-10 17:00 |  | PT_Normal |  |  |  |  | vpsApO+uQ3aOYdZt4Rq3DA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31460 | N | N | 10 | UPTO GRADE SLAB |  | 125325 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP10; period 2: 2013-AP11 |  | 2211 | BLINDING MASON SK
%R | 503920 | 6359 | 125326 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STUG1000 | Footing Excavation | 8177 | 0 | 0 | 200 | 0 | 1114 | 1114 | 200 | 524 | 0 | 524 |  |  |  | 2013-06-11 08:00 | 2013-07-09 17:00 |  | 2013-06-11 08:00 | 2013-07-09 17:00 | 2013-06-11 08:00 | 2013-07-09 17:00 | 2013-06-11 08:00 | 2013-07-09 17:00 | 2013-06-11 08:00 | 2013-07-09 17:00 |  | PT_Normal |  |  |  |  | r+m+5W+eRxypUQpNqswjoQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31460 | N | N | 10 | UPTO GRADE SLAB |  | 125325 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 1114 | LABOR - CIVIL
%R | 503921 | 6359 | 125326 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STUG1005 | Footing Antitermite | 8178 | 0 | 0 | 184 | 0 | 1584 | 1584 | 184 | 0 | 0 | 0 |  |  |  | 2013-06-23 08:00 | 2013-07-18 17:00 |  | 2013-06-23 08:00 | 2013-07-18 17:00 | 2013-06-23 08:00 | 2013-07-18 17:00 | 2013-06-23 08:00 | 2013-07-18 17:00 | 2013-06-23 08:00 | 2013-07-18 17:00 |  | PT_Normal |  |  |  |  | aPcRuf+5TqOY7Wcm/IOZ9Q |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31460 | N | N | 10 | UPTO GRADE SLAB |  | 125325 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 1584 | LABOR- SUBCONTRACTOR
%R | 503922 | 6359 | 125326 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STUG1010 | Footing Blinding | 8163 | 0 | 0 | 184 | 0 | 794.5 | 794.5 | 184 | 0 | 0 | 0 |  |  |  | 2013-06-26 08:00 | 2013-07-22 17:00 |  | 2013-06-26 08:00 | 2013-07-22 17:00 | 2013-06-26 08:00 | 2013-07-22 17:00 | 2013-06-26 08:00 | 2013-07-22 17:00 | 2013-06-26 08:00 | 2013-07-22 17:00 |  | PT_Normal |  |  |  |  | oziymU5oRw2AlglK+OWq8g |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43400 |  |  |  |  | BLINDING MASON SK | J302 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31460 | N | N | 10 | UPTO GRADE SLAB |  | 125325 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP06 |  | 794.5 | BLINDING MASON SK
%R | 503923 | 6359 | 125326 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STUG1015 | Footing Waterproofing & Screed | 8164 | 0 | 0 | 200 | 0 | 574.75 | 574.75 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-02 08:00 | 2013-07-30 17:00 |  | 2013-07-02 08:00 | 2013-07-30 17:00 | 2013-07-02 08:00 | 2013-07-30 17:00 | 2013-07-02 08:00 | 2013-07-30 17:00 | 2013-07-02 08:00 | 2013-07-30 17:00 |  | PT_Normal |  |  |  |  | IEgJ7HeCQWiLVwvLaQHXIw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31460 | N | N | 10 | UPTO GRADE SLAB |  | 125325 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 574.75 | SCREED MASON SK
%R | 503924 | 6359 | 125326 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STUG1020 | Construction of foundations | 8165 | 0 | 0 | 160 | 0 | 7778.75 | 7778.75 | 160 | 0 | 0 | 0 |  |  |  | 2013-07-17 08:00 | 2013-08-08 17:00 |  | 2013-07-17 08:00 | 2013-08-08 17:00 | 2013-07-17 08:00 | 2013-08-08 17:00 | 2013-07-17 08:00 | 2013-08-08 17:00 | 2013-07-17 08:00 | 2013-08-08 17:00 |  | PT_Normal |  |  |  |  | oDzRdASFTPKbjL8J9M9xjA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31460 | N | N | 10 | UPTO GRADE SLAB |  | 125325 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07 |  | 7778.75 | STEEL FIXERS SK
%R | 503925 | 6359 | 125326 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STUG1025 | Construction of neck of columns | 8165 | 0 | 0 | 200 | 0 | 1606.5 | 1606.5 | 200 | 0 | 0 | 0 |  |  |  | 2013-07-27 08:00 | 2013-08-27 17:00 |  | 2013-07-27 08:00 | 2013-08-27 17:00 | 2013-07-27 08:00 | 2013-08-27 17:00 | 2013-07-27 08:00 | 2013-08-27 17:00 | 2013-07-27 08:00 | 2013-08-27 17:00 |  | PT_Normal |  |  |  |  | ENDJbHIlTE27Mq2C6+60lA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31460 | N | N | 10 | UPTO GRADE SLAB |  | 125325 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP07; period 2: 2013-AP08 |  | 803.25 | STEEL FIXERS SK
%R | 503926 | 6359 | 125326 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5STUG1030 | Waterproofing Footing & Neck Column | 8178 | 0 | 0 | 200 | 0 | 516 | 516 | 200 | 0 | 0 | 0 |  |  |  | 2013-08-05 08:00 | 2013-09-05 17:00 |  | 2013-08-05 08:00 | 2013-09-05 17:00 | 2013-08-05 08:00 | 2013-09-05 17:00 | 2013-08-05 08:00 | 2013-09-05 17:00 | 2013-08-05 08:00 | 2013-09-05 17:00 |  | PT_Normal |  |  |  |  | C9Nv8D0FTjmxs9bE/uJl7A |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31460 | N | N | 10 | UPTO GRADE SLAB |  | 125325 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2013-AP08; period 2: 2013-AP09 |  | 258 | LABOR- SUBCONTRACTOR
%R | 503927 | 6359 | 125329 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5AREL3665 | External Plastering | 8169 | 376 | 0 | 200 | 0 | 14275 | 14275 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-22 08:00 | 2014-06-19 17:00 |  | 2014-03-29 08:00 | 2014-04-26 17:00 | 2014-03-29 08:00 | 2014-04-26 17:00 | 2014-03-29 08:00 | 2014-04-26 17:00 | 2014-05-22 08:00 | 2014-06-19 17:00 |  | PT_Normal |  |  |  |  | zZbkRXiVTj6a9QH8phlhUQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31580 | N | N | 15 | ELEVATION |  | 125328 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 14275 | PLASTER MASON SK
%R | 503928 | 6359 | 125329 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5AREL3670 | External stone cladding works | 8170 | 392 | 0 | 160 | 0 | 990 | 990 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-07-03 17:00 |  | 2014-04-15 08:00 | 2014-05-07 17:00 | 2014-04-15 08:00 | 2014-05-07 17:00 | 2014-04-15 08:00 | 2014-05-07 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 |  | PT_Normal |  |  |  |  | TornF2ORTwOl513vZ9hf2g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31580 | N | N | 15 | ELEVATION |  | 125328 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 990 | TILE MASON SK
%R | 503929 | 6359 | 125329 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5AREL3680 | External Painting | 8178 | 392 | 40 | 160 | 0 | 3784 | 3784 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-23 08:00 | 2014-07-15 17:00 |  | 2014-04-27 08:00 | 2014-05-19 17:00 | 2014-04-27 08:00 | 2014-05-19 17:00 | 2014-04-27 08:00 | 2014-05-19 17:00 | 2014-06-23 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | 8Ro/5IU1Q9KbLIAptI2LrQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31580 | N | N | 15 | ELEVATION |  | 125328 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 3784 | LABOR- SUBCONTRACTOR
%R | 503930 | 6359 | 125330 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARRF3630 | Leveling Screed for Waterproofing | 8164 | 168 | 0 | 200 | 0 | 800 | 800 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-06 08:00 | 2014-06-03 17:00 |  | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-04-12 08:00 | 2014-05-10 17:00 | 2014-05-06 08:00 | 2014-06-03 17:00 |  | PT_Normal |  |  |  |  | a7dLVe4DQCaC3bMLa9+Lyg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31570 | N | N | 10 | ROOF |  | 125328 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 800 | SCREED MASON SK
%R | 503931 | 6359 | 125330 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARRF3635 | Laying of Waterproofing Membrane | 8178 | 168 | 0 | 200 | 0 | 1138.5 | 1138.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-10 08:00 | 2014-06-07 17:00 |  | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-04-15 08:00 | 2014-05-13 17:00 | 2014-05-10 08:00 | 2014-06-07 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31570 | N | N | 10 | ROOF |  | 125328 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1138.5 | LABOR- SUBCONTRACTOR
%R | 503932 | 6359 | 125330 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARRF3640 | Installation of Insulation & Protection | 8178 | 168 | 0 | 200 | 0 | 1408 | 1408 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-14 08:00 | 2014-06-11 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-05-14 08:00 | 2014-06-11 17:00 |  | PT_Normal |  |  |  |  | vE59bd0+Tkah4ZnWPsovrQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31570 | N | N | 10 | ROOF |  | 125328 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1408 | LABOR- SUBCONTRACTOR
%R | 503933 | 6359 | 125330 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARRF3645 | Lime Stone Chips & Paving slab Installation | 8170 | 168 | 0 | 200 | 0 | 688.25 | 688.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-19 08:00 | 2014-06-16 17:00 |  | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-04-24 08:00 | 2014-05-22 17:00 | 2014-05-19 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | ACjb0seVSNGer+N7MRG11Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31570 | N | N | 10 | ROOF |  | 125328 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 688.25 | TILE MASON SK
%R | 503934 | 6359 | 125330 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARRF3655 | Installation of Pumps Protection cabinets | 8178 | 168 | 0 | 160 | 0 | 616 | 616 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-07-03 17:00 |  | 2014-05-18 08:00 | 2014-06-09 17:00 | 2014-05-18 08:00 | 2014-06-09 17:00 | 2014-05-18 08:00 | 2014-06-09 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 |  | PT_Normal |  |  |  |  | MxxV3qITRWiiTRjIw/OnaQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31570 | N | N | 10 | ROOF |  | 125328 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 616 | LABOR- SUBCONTRACTOR
%R | 503935 | 6359 | 125330 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 8178 | 168 | 0 | 200 | 0 | 1046.5 | 1046.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-27 08:00 | 2014-06-24 17:00 |  | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-03 08:00 | 2014-05-31 17:00 | 2014-05-27 08:00 | 2014-06-24 17:00 |  | PT_Normal |  |  |  |  | fvffPyC/RRCL++kM8ashPA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31570 | N | N | 10 | ROOF |  | 125328 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1046.5 | LABOR- SUBCONTRACTOR
%R | 503936 | 6359 | 125330 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARRF3660 | Installation of Access Ladder | 8178 | 208 | 208 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-15 17:00 |  | 2014-05-29 08:00 | 2014-06-15 17:00 | 2014-05-29 08:00 | 2014-06-15 17:00 | 2014-05-29 08:00 | 2014-06-15 17:00 | 2014-06-29 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | UtcnL+CbQkyRDYMhrCjKUQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31570 | N | N | 10 | ROOF |  | 125328 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 176 | LABOR- SUBCONTRACTOR
%R | 503937 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3000 | Block work | 8168 | 144 | 0 | 200 | 0 | 9737.5 | 9737.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-01-29 08:00 | 2014-02-27 17:00 |  | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-08 08:00 | 2014-02-05 17:00 | 2014-01-29 08:00 | 2014-02-27 17:00 |  | PT_Normal |  |  |  |  | 0B8taPJSR9GVm9hbytTw1g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 9737.5 | BLOCK MASON SK
%R | 503938 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3005 | Plastering work | 8169 | 144 | 0 | 200 | 0 | 13637.5 | 13637.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-22 08:00 | 2014-03-22 17:00 |  | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-01-30 08:00 | 2014-03-01 17:00 | 2014-02-22 08:00 | 2014-03-22 17:00 |  | PT_Normal |  |  |  |  | 7YwDtIIIRLeArgRopPMEhA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01; period 2: 2014-AP03 |  | 6818.75 | PLASTER MASON SK
%R | 503939 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3010 | Flooring screed | 8164 | 208 | 64 | 168 | 0 | 1580.25 | 1580.25 | 168 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-04-03 17:00 |  | 2014-02-08 08:00 | 2014-03-04 17:00 | 2014-02-08 08:00 | 2014-03-04 17:00 | 2014-02-08 08:00 | 2014-03-04 17:00 | 2014-03-11 08:00 | 2014-04-03 17:00 |  | PT_Normal |  |  |  |  | RGp/y6eyQMeRw+ONfND5kw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 1580.25 | SCREED MASON SK
%R | 503940 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3015 | Wet area waterproofing & Protection Screed | 8178 | 144 | 0 | 120 | 0 | 247.5 | 247.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-03-11 08:00 | 2014-03-27 17:00 |  | 2014-02-18 08:00 | 2014-03-06 17:00 | 2014-02-18 08:00 | 2014-03-06 17:00 | 2014-02-18 08:00 | 2014-03-06 17:00 | 2014-03-11 08:00 | 2014-03-27 17:00 |  | PT_Normal |  |  |  |  | SsH9zPy3QQ2wSOA0uD2ITg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02 |  | 247.5 | LABOR- SUBCONTRACTOR
%R | 503941 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3030 | Paint First coat | 8178 | 256 | 0 | 200 | 0 | 5425.75 | 5425.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-26 08:00 | 2014-04-23 17:00 |  | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-02-17 08:00 | 2014-03-17 17:00 | 2014-03-26 08:00 | 2014-04-23 17:00 |  | PT_Normal |  |  |  |  | g4BgEJPTTruEdd3KEu9K/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 2712.875 | LABOR- SUBCONTRACTOR
%R | 503942 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3020 | Ceramic Wall Tiling | 8170 | 144 | 0 | 200 | 0 | 4428.5 | 4428.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-14 17:00 |  | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-02-24 08:00 | 2014-03-24 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 |  | PT_Normal |  |  |  |  | bYCtbzniSVSbmA/sAKiHQg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 2214.25 | TILE MASON SK
%R | 503943 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3025 | Porcelain Tile flooring | 8170 | 144 | 0 | 200 | 0 | 1743.75 | 1743.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-23 08:00 | 2014-04-20 17:00 |  | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-02 08:00 | 2014-03-30 17:00 | 2014-03-23 08:00 | 2014-04-20 17:00 |  | PT_Normal |  |  |  |  | tIdlO45aQWmn3hdjAaI93Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1743.75 | TILE MASON SK
%R | 503944 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3040 | Cobble Tile flooring | 8170 | 168 | 0 | 120 | 0 | 741 | 741 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-22 08:00 | 2014-05-08 17:00 |  | 2014-03-29 08:00 | 2014-04-14 17:00 | 2014-03-29 08:00 | 2014-04-14 17:00 | 2014-03-29 08:00 | 2014-04-14 17:00 | 2014-04-22 08:00 | 2014-05-08 17:00 |  | PT_Normal |  |  |  |  | WGYvpqoHSxGm/Sa3Fl6QMQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 741 | TILE MASON SK
%R | 503945 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3035 | Slate Tile Flooring & Skirting | 8170 | 184 | 16 | 120 | 0 | 761.5 | 761.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-17 08:00 | 2014-05-04 17:00 |  | 2014-03-22 08:00 | 2014-04-07 17:00 | 2014-03-22 08:00 | 2014-04-07 17:00 | 2014-03-22 08:00 | 2014-04-07 17:00 | 2014-04-17 08:00 | 2014-05-04 17:00 |  | PT_Normal |  |  |  |  | c5WmWK/4TuSwWLryYQNstw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 761.5 | TILE MASON SK
%R | 503946 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3050 | Granite - Stair case flooring & Skirting | 8171 | 168 | 0 | 160 | 0 | 875 | 875 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-30 08:00 | 2014-05-22 17:00 |  | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-04-30 08:00 | 2014-05-22 17:00 |  | PT_Normal |  |  |  |  | B2VQB5Z7TLOuj5TfwIS1EQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 875 | GRANITE MASON SK
%R | 503947 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3045 | Fixing of Suspension systems | 8178 | 144 | 0 | 160 | 0 | 1455.05 | 1455.05 | 160 | 0 | 0 | 0 |  |  |  | 2014-04-09 08:00 | 2014-05-01 17:00 |  | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-03-19 08:00 | 2014-04-10 17:00 | 2014-04-09 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | 5w5I0Th1Q7iJzX4YjvWgIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-23 09:03 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1455.05 | LABOR- SUBCONTRACTOR
%R | 503948 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3055 | Aluminum tile false ceiling | 8178 | 168 | 24 | 200 | 0 | 150 | 150 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-21 08:00 | 2014-05-19 17:00 |  | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-03-27 08:00 | 2014-04-24 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | mtB3wUoJTGS17QpoE8KYfw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 150 | LABOR- SUBCONTRACTOR
%R | 503949 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3060 | Gypsum board false ceiling | 8178 | 144 | 0 | 200 | 0 | 1335.15 | 1335.15 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-21 08:00 | 2014-05-19 17:00 |  | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-03-31 08:00 | 2014-04-28 17:00 | 2014-04-21 08:00 | 2014-05-19 17:00 |  | PT_Normal |  |  |  |  | 58KAQuP8SF+zENkAgMjydw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1335.15 | LABOR- SUBCONTRACTOR
%R | 503950 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3065 | Wooden door & PVC Door | 8178 | 168 | 0 | 120 | 0 | 308 | 308 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-14 08:00 | 2014-05-31 17:00 |  | 2014-04-20 08:00 | 2014-05-06 17:00 | 2014-04-20 08:00 | 2014-05-06 17:00 | 2014-04-20 08:00 | 2014-05-06 17:00 | 2014-05-14 08:00 | 2014-05-31 17:00 |  | PT_Normal |  |  |  |  | LX8JcwnNR9GuADzQ4d/CkA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 308 | LABOR- SUBCONTRACTOR
%R | 503951 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3070 | Aluminum doors | 8178 | 168 | 0 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-20 08:00 | 2014-06-05 17:00 |  | 2014-04-26 08:00 | 2014-05-12 17:00 | 2014-04-26 08:00 | 2014-05-12 17:00 | 2014-04-26 08:00 | 2014-05-12 17:00 | 2014-05-20 08:00 | 2014-06-05 17:00 |  | PT_Normal |  |  |  |  | AjshabO6Qtyau+irS6dpnw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 176 | LABOR- SUBCONTRACTOR
%R | 503952 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3080 | Aluminum windows | 8178 | 248 | 40 | 160 | 0 | 162.25 | 162.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-08 08:00 | 2014-06-30 17:00 |  | 2014-05-03 08:00 | 2014-05-25 17:00 | 2014-05-03 08:00 | 2014-05-25 17:00 | 2014-05-03 08:00 | 2014-05-25 17:00 | 2014-06-08 08:00 | 2014-06-30 17:00 |  | PT_Normal |  |  |  |  | oE3x+ghtQnaFJGp61L5T2Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 162.25 | LABOR- SUBCONTRACTOR
%R | 503953 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3075 | Carpentry & Joinery Works | 8178 | 168 | 0 | 160 | 0 | 572 | 572 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-26 08:00 | 2014-06-17 17:00 |  | 2014-05-01 08:00 | 2014-05-24 17:00 | 2014-05-01 08:00 | 2014-05-24 17:00 | 2014-05-01 08:00 | 2014-05-24 17:00 | 2014-05-26 08:00 | 2014-06-17 17:00 |  | PT_Normal |  |  |  |  | iHquyGKWTsurW1SI4UPOIg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 572 | LABOR- SUBCONTRACTOR
%R | 503954 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3090 | Installation of Granite Counter Top | 8171 | 168 | 0 | 120 | 0 | 176 | 176 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-08 08:00 | 2014-06-24 17:00 |  | 2014-05-14 08:00 | 2014-05-31 17:00 | 2014-05-14 08:00 | 2014-05-31 17:00 | 2014-05-14 08:00 | 2014-05-31 17:00 | 2014-06-08 08:00 | 2014-06-24 17:00 |  | PT_Normal |  |  |  |  | 6A4QU7M5SIeYaZUuU5ZUXA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 176 | GRANITE MASON SK
%R | 503955 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3085 | S.S.Balustrade | 8178 | 208 | 40 | 160 | 0 | 262.5 | 262.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-09 08:00 | 2014-07-01 17:00 |  | 2014-05-10 08:00 | 2014-06-01 17:00 | 2014-05-10 08:00 | 2014-06-01 17:00 | 2014-05-10 08:00 | 2014-06-01 17:00 | 2014-06-09 08:00 | 2014-07-01 17:00 |  | PT_Normal |  |  |  |  | FLDWK1C8Quu9KRCDH2R2hA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 262.5 | LABOR- SUBCONTRACTOR
%R | 503956 | 6359 | 125332 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARGF3095 | Final Painting | 8178 | 168 | 0 | 200 | 0 | 5425.75 | 5425.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-05-24 08:00 | 2014-06-21 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | bn53RzkWQL2OQR0lPq+k5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31530 | N | N | 10 | GROUND FLOOR |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 5425.75 | LABOR- SUBCONTRACTOR
%R | 503957 | 6359 | 125333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARFF3300 | Block work | 8168 | 0 | 0 | 200 | 0 | 6387.5 | 6387.5 | 200 | 0 | 0 | 0 |  |  |  | 2014-02-20 08:00 | 2014-03-20 17:00 |  | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 | 2014-02-20 08:00 | 2014-03-20 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31540 | N | N | 15 | FIRST FLOORS |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP02; period 2: 2014-AP03 |  | 3193.75 | BLOCK MASON SK
%R | 503958 | 6359 | 125333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARFF3305 | Plastering work | 8169 | 0 | 0 | 200 | 0 | 8899 | 8899 | 200 | 0 | 0 | 0 |  |  |  | 2014-03-17 08:00 | 2014-04-14 17:00 |  | 2014-03-17 08:00 | 2014-04-14 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 | 2014-03-17 08:00 | 2014-04-14 17:00 |  | PT_Normal |  |  |  |  | et69NYlqS6KMwVGDA7rYqg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31540 | N | N | 15 | FIRST FLOORS |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 8899 | PLASTER MASON SK
%R | 503959 | 6359 | 125333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARFF3310 | Flooring screed | 8164 | 96 | 96 | 168 | 0 | 1215.5 | 1215.5 | 168 | 0 | 0 | 0 |  |  |  | 2014-04-08 08:00 | 2014-05-01 17:00 |  | 2014-03-25 08:00 | 2014-04-17 17:00 | 2014-03-25 08:00 | 2014-04-17 17:00 | 2014-03-25 08:00 | 2014-04-17 17:00 | 2014-04-08 08:00 | 2014-05-01 17:00 |  | PT_Normal |  |  |  |  | 3uuVuXdTT7aiUzCczxuyyQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31540 | N | N | 15 | FIRST FLOORS |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1215.5 | SCREED MASON SK
%R | 503960 | 6359 | 125333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARFF3315 | Wet area waterproofing | 8178 | 0 | 0 | 120 | 0 | 1215.5 | 1215.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-04-06 08:00 | 2014-04-22 17:00 |  | 2014-04-06 08:00 | 2014-04-22 17:00 | 2014-04-06 08:00 | 2014-04-22 17:00 | 2014-04-06 08:00 | 2014-04-22 17:00 | 2014-04-06 08:00 | 2014-04-22 17:00 |  | PT_Normal |  |  |  |  | K3kzNsffQkK/OjfOoPqVLA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31540 | N | N | 15 | FIRST FLOORS |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1215.5 | LABOR- SUBCONTRACTOR
%R | 503961 | 6359 | 125333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARFF3330 | Paint First coat | 8178 | 112 | 112 | 200 | 0 | 4742.75 | 4742.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-19 08:00 | 2014-05-17 17:00 |  | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-02 08:00 | 2014-04-30 17:00 | 2014-04-19 08:00 | 2014-05-17 17:00 |  | PT_Normal |  |  |  |  | NoreR+RuTKa0k4PmiB1TTg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31540 | N | N | 15 | FIRST FLOORS |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 4742.75 | LABOR- SUBCONTRACTOR
%R | 503962 | 6359 | 125333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARFF3320 | Ceramic Wall Tiling | 8170 | 0 | 0 | 200 | 0 | 1897.25 | 1897.25 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-13 08:00 | 2014-05-11 17:00 |  | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-04-13 08:00 | 2014-05-11 17:00 | 2014-04-13 08:00 | 2014-05-11 17:00 |  | PT_Normal |  |  |  |  | Ka37s9RYR6SL4hTPZFqfbQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31540 | N | N | 15 | FIRST FLOORS |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1897.25 | TILE MASON SK
%R | 503963 | 6359 | 125333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARFF3325 | Porcelain Tile flooring | 8170 | 0 | 0 | 200 | 0 | 1743.75 | 1743.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-04-20 08:00 | 2014-05-18 17:00 |  | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 | 2014-04-20 08:00 | 2014-05-18 17:00 |  | PT_Normal |  |  |  |  | yACYLeSlSSSu0XwiSZdyjw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31540 | N | N | 15 | FIRST FLOORS |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1743.75 | TILE MASON SK
%R | 503964 | 6359 | 125333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARFF3335 | Slate Tile Flooring & Skirting | 8170 | 64 | 64 | 120 | 0 | 261.5 | 261.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-17 08:00 | 2014-06-02 17:00 |  | 2014-05-07 08:00 | 2014-05-24 17:00 | 2014-05-07 08:00 | 2014-05-24 17:00 | 2014-05-07 08:00 | 2014-05-24 17:00 | 2014-05-17 08:00 | 2014-06-02 17:00 |  | PT_Normal |  |  |  |  | j9GyVVoLTuuI0D5C/njxng |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31540 | N | N | 15 | FIRST FLOORS |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 261.5 | TILE MASON SK
%R | 503965 | 6359 | 125333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARFF3350 | Granite - Stair case flooring & Skirting | 8171 | 16 | 16 | 160 | 0 | 875 | 875 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-13 08:00 | 2014-06-04 17:00 |  | 2014-05-11 08:00 | 2014-06-02 17:00 | 2014-05-11 08:00 | 2014-06-02 17:00 | 2014-05-11 08:00 | 2014-06-02 17:00 | 2014-05-13 08:00 | 2014-06-04 17:00 |  | PT_Normal |  |  |  |  | G5hAN/aXTdGRMGpe+YJe5A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31540 | N | N | 15 | FIRST FLOORS |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 875 | GRANITE MASON SK
%R | 503966 | 6359 | 125333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARFF3345 | Fixing of Suspension systems | 8178 | 0 | 0 | 160 | 0 | 1305 | 1305 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-03 08:00 | 2014-05-25 17:00 |  | 2014-05-03 08:00 | 2014-05-25 17:00 | 2014-05-03 08:00 | 2014-05-25 17:00 | 2014-05-03 08:00 | 2014-05-25 17:00 | 2014-05-03 08:00 | 2014-05-25 17:00 |  | PT_Normal |  |  |  |  | /hfpUA43Sy6pCR8JBbJAKQ |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31540 | N | N | 15 | FIRST FLOORS |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1305 | LABOR- SUBCONTRACTOR
%R | 503967 | 6359 | 125333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARFF3360 | Gypsum board false ceiling | 8178 | 0 | 0 | 200 | 0 | 1305 | 1305 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-10 08:00 | 2014-06-07 17:00 |  | 2014-05-10 08:00 | 2014-06-07 17:00 | 2014-05-10 08:00 | 2014-06-07 17:00 | 2014-05-10 08:00 | 2014-06-07 17:00 | 2014-05-10 08:00 | 2014-06-07 17:00 |  | PT_Normal |  |  |  |  | 8kiav5NnT0O+NIt2smw27g |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31540 | N | N | 15 | FIRST FLOORS |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1305 | LABOR- SUBCONTRACTOR
%R | 503968 | 6359 | 125333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARFF3365 | Wooden door | 8178 | 0 | 0 | 120 | 0 | 308 | 308 | 120 | 0 | 0 | 0 |  |  |  | 2014-05-25 08:00 | 2014-06-10 17:00 |  | 2014-05-25 08:00 | 2014-06-10 17:00 | 2014-05-25 08:00 | 2014-06-10 17:00 | 2014-05-25 08:00 | 2014-06-10 17:00 | 2014-05-25 08:00 | 2014-06-10 17:00 |  | PT_Normal |  |  |  |  | sjH0kZomS+OA3C9UhXynzw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31540 | N | N | 15 | FIRST FLOORS |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 308 | LABOR- SUBCONTRACTOR
%R | 503969 | 6359 | 125333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARFF3370 | Aluminum Door | 8178 | 0 | 0 | 160 | 0 | 220 | 220 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-25 08:00 | 2014-06-16 17:00 |  | 2014-05-25 08:00 | 2014-06-16 17:00 | 2014-05-25 08:00 | 2014-06-16 17:00 | 2014-05-25 08:00 | 2014-06-16 17:00 | 2014-05-25 08:00 | 2014-06-16 17:00 |  | PT_Normal |  |  |  |  | a9Rt5lP4S4C3/L9UpqEuKA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31540 | N | N | 15 | FIRST FLOORS |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 220 | LABOR- SUBCONTRACTOR
%R | 503970 | 6359 | 125333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARFF3380 | Aluminum windows | 8178 | 32 | 32 | 160 | 0 | 162.25 | 162.25 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-05 08:00 | 2014-06-28 17:00 |  | 2014-06-01 08:00 | 2014-06-23 17:00 | 2014-06-01 08:00 | 2014-06-23 17:00 | 2014-06-01 08:00 | 2014-06-23 17:00 | 2014-06-05 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | JGC4EWcSSJGko24Q/Kr65A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31540 | N | N | 15 | FIRST FLOORS |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 162.25 | LABOR- SUBCONTRACTOR
%R | 503971 | 6359 | 125333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARFF3375 | Carpentry & Joinery Works | 8178 | 0 | 0 | 200 | 0 | 1100 | 1100 | 200 | 0 | 0 | 0 |  |  |  | 2014-05-31 08:00 | 2014-06-28 17:00 |  | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 | 2014-05-31 08:00 | 2014-06-28 17:00 |  | PT_Normal |  |  |  |  | R00pGoEqRjuVCnAgx1htCw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31540 | N | N | 15 | FIRST FLOORS |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1100 | LABOR- SUBCONTRACTOR
%R | 503972 | 6359 | 125333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARFF3390 | Installation of Granite Counter Top | 8171 | 8 | 8 | 160 | 0 | 88 | 88 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-07-05 17:00 |  | 2014-06-11 08:00 | 2014-07-03 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 | 2014-06-12 08:00 | 2014-07-05 17:00 |  | PT_Normal |  |  |  |  | IImk+bJ0S6erOJNw6uPEWQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43480 |  |  |  |  | GRANITE MASON SK | J310 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31540 | N | N | 15 | FIRST FLOORS |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 88 | GRANITE MASON SK
%R | 503973 | 6359 | 125333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARFF3385 | Handrail & Balustrade | 8178 | 0 | 0 | 160 | 0 | 787.5 | 787.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-07-03 17:00 |  | 2014-06-11 08:00 | 2014-07-03 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 |  | PT_Normal |  |  |  |  | uVAyKULASUm0xWyun6L50g |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31540 | N | N | 15 | FIRST FLOORS |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 787.5 | LABOR- SUBCONTRACTOR
%R | 503974 | 6359 | 125333 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARFF3395 | Final Painting | 8178 | 0 | 0 | 200 | 0 | 4742.75 | 4742.75 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-17 08:00 | 2014-07-15 17:00 |  | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | z9E6ppbfRa2a9HqJGCMmAw |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31540 | N | N | 15 | FIRST FLOORS |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 4742.75 | LABOR- SUBCONTRACTOR
%R | 503975 | 6359 | 125334 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARRF3600 | Block work | 8168 | 416 | 0 | 160 | 0 | 700 | 700 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-06 08:00 | 2014-05-28 17:00 |  | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-03-06 08:00 | 2014-03-29 17:00 | 2014-05-06 08:00 | 2014-05-28 17:00 |  | PT_Normal |  |  |  |  | pXcDPJJsT66KLE2xgxjTKg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31550 | N | N | 20 | ROOF |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 700 | BLOCK MASON SK
%R | 503976 | 6359 | 125334 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARRF3605 | Plastering work | 8169 | 416 | 0 | 160 | 0 | 1786.5 | 1786.5 | 160 | 0 | 0 | 0 |  |  |  | 2014-05-14 08:00 | 2014-06-05 17:00 |  | 2014-03-15 08:00 | 2014-04-06 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 | 2014-03-15 08:00 | 2014-04-06 17:00 | 2014-05-14 08:00 | 2014-06-05 17:00 |  | PT_Normal |  |  |  |  | vcCWsuofS5C2gVzcWz2OAA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43460 |  |  |  |  | PLASTER MASON SK | J308 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31550 | N | N | 20 | ROOF |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 1786.5 | PLASTER MASON SK
%R | 503977 | 6359 | 125334 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARRF3610 | Flooring screed | 8164 | 456 | 0 | 120 | 0 | 136.5 | 136.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-03 08:00 | 2014-06-19 17:00 |  | 2014-03-29 08:00 | 2014-04-14 17:00 | 2014-03-29 08:00 | 2014-04-14 17:00 | 2014-03-29 08:00 | 2014-04-14 17:00 | 2014-06-03 08:00 | 2014-06-19 17:00 |  | PT_Normal |  |  |  |  | 8gj35HkTTNOMGegiaz2Gag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31550 | N | N | 20 | ROOF |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP03 |  | 136.5 | SCREED MASON SK
%R | 503978 | 6359 | 125334 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARRF3695 | Painting -Storage area | 8178 | 456 | 0 | 160 | 0 | 1640 | 1640 | 160 | 0 | 0 | 0 |  |  |  | 2014-06-11 08:00 | 2014-07-03 17:00 |  | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-04-06 08:00 | 2014-04-28 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 |  | PT_Normal |  |  |  |  | HvwMFu6lRFqL8Lo8LsWOEg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31550 | N | N | 20 | ROOF |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 1640 | LABOR- SUBCONTRACTOR
%R | 503979 | 6359 | 125334 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ5ARRF3620 | Epoxy Painting -Storage area | 8178 | 456 | 456 | 120 | 0 | 48.5 | 48.5 | 120 | 0 | 0 | 0 |  |  |  | 2014-06-29 08:00 | 2014-07-15 17:00 |  | 2014-04-23 08:00 | 2014-05-10 17:00 | 2014-04-23 08:00 | 2014-05-10 17:00 | 2014-04-23 08:00 | 2014-05-10 17:00 | 2014-06-29 08:00 | 2014-07-15 17:00 |  | PT_Normal |  |  |  |  | R3/7nfkkSj6egnp5jNBCQw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 31550 | N | N | 20 | ROOF |  | 125331 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP04 |  | 48.5 | LABOR- SUBCONTRACTOR
%R | 503980 | 6359 | 125337 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9WEEX5035 | Construction of Raft | 8165 | 384 | 0 | 200 | 0 | 1050 | 1050 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-03 08:00 | 2014-10-01 17:00 |  | 2014-07-06 08:00 | 2014-08-06 17:00 | 2014-07-06 08:00 | 2014-08-06 17:00 | 2014-07-06 08:00 | 2014-08-06 17:00 | 2014-09-03 08:00 | 2014-10-01 17:00 |  | PT_Normal |  |  |  |  | 0Aa03b59QDyx0QmOIQnAOQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43420 |  |  |  |  | STEEL FIXERS SK | J304 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33200 | N | N | 15 | WATER TANK ENCLOSURE |  | 125336 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 525 | STEEL FIXERS SK
%R | 503981 | 6359 | 125337 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9WEEX5040 | Block works & Plastering | 8168 | 384 | 0 | 200 | 0 | 640 | 640 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-13 08:00 | 2014-10-13 17:00 |  | 2014-07-15 08:00 | 2014-08-16 17:00 | 2014-07-15 08:00 | 2014-08-16 17:00 | 2014-07-15 08:00 | 2014-08-16 17:00 | 2014-09-13 08:00 | 2014-10-13 17:00 |  | PT_Normal |  |  |  |  | TCRAmb3ERsWU/wgi6EkLRw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43450 |  |  |  |  | BLOCK MASON SK | J307 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33200 | N | N | 15 | WATER TANK ENCLOSURE |  | 125336 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 320 | BLOCK MASON SK
%R | 503982 | 6359 | 125337 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9WEEX5045 | Flooring & Painting | 8178 | 384 | 232 | 200 | 0 | 290 | 290 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-20 08:00 | 2014-10-20 17:00 |  | 2014-07-22 08:00 | 2014-08-23 17:00 | 2014-07-22 08:00 | 2014-08-23 17:00 | 2014-07-22 08:00 | 2014-08-23 17:00 | 2014-09-20 08:00 | 2014-10-20 17:00 |  | PT_Normal |  |  |  |  | Y0MfhXMRT0GBnoUW02ueGw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33200 | N | N | 15 | WATER TANK ENCLOSURE |  | 125336 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 145 | LABOR- SUBCONTRACTOR
%R | 503983 | 6359 | 125337 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9WEEX5050 | Installation of Steel Gate | 8178 | 152 | 72 | 160 | 0 | 70 | 70 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-02 08:00 | 2014-10-27 17:00 |  | 2014-09-10 08:00 | 2014-10-02 17:00 | 2014-09-10 08:00 | 2014-10-02 17:00 | 2014-09-10 08:00 | 2014-10-02 17:00 | 2014-10-02 08:00 | 2014-10-27 17:00 |  | PT_Normal |  |  |  |  | 3MwAIIkSQy+Rv8FnA55j7Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33200 | N | N | 15 | WATER TANK ENCLOSURE |  | 125336 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 70 | LABOR- SUBCONTRACTOR
%R | 503984 | 6359 | 125337 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9WEEX5060 | Structural steel & SS Shed cover installation | 8178 | 80 | 8 | 200 | 0 | 420 | 420 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-08 08:00 | 2014-11-08 17:00 |  | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-10-08 08:00 | 2014-11-08 17:00 |  | PT_Normal |  |  |  |  | UbaTNGlyRZaWkg11Zfz/qw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33200 | N | N | 15 | WATER TANK ENCLOSURE |  | 125336 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 210 | LABOR- SUBCONTRACTOR
%R | 503985 | 6359 | 125337 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 8178 | 72 | 72 | 200 | 0 | 254 | 254 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-10-05 08:00 | 2014-11-04 17:00 | 2014-10-05 08:00 | 2014-11-04 17:00 | 2014-10-05 08:00 | 2014-11-04 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | 8PrU+U3BTjOGmVaMqbeogg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33200 | N | N | 15 | WATER TANK ENCLOSURE |  | 125336 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 254 | LABOR- SUBCONTRACTOR
%R | 503986 | 6359 | 125337 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9WEEX5030 | Excavation | 8177 | 384 | 0 | 160 | 0 | 70 | 70 | 160 | 40 | 0 | 40 |  |  |  | 2014-08-28 08:00 | 2014-09-20 17:00 |  | 2014-06-30 08:00 | 2014-07-22 17:00 | 2014-06-30 08:00 | 2014-07-22 17:00 | 2014-06-30 08:00 | 2014-07-22 17:00 | 2014-08-28 08:00 | 2014-09-20 17:00 |  | PT_Normal |  |  |  |  | S1t6ffYhS1GeVvdGCInfgQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33200 | N | N | 15 | WATER TANK ENCLOSURE |  | 125336 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 70 | LABOR - CIVIL
%R | 503987 | 6359 | 125338 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9HDEX5090 | kerb works | 8173 | 128 | 0 | 160 | 0 | 430 | 430 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-14 08:00 | 2014-10-06 17:00 |  | 2014-08-26 08:00 | 2014-09-17 17:00 | 2014-08-26 08:00 | 2014-09-17 17:00 | 2014-08-26 08:00 | 2014-09-17 17:00 | 2014-09-14 08:00 | 2014-10-06 17:00 |  | PT_Normal |  |  |  |  | 6xC1tf9GQcGmgpxIFY/Z6w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43500 |  |  |  |  | KERBSTONE MASON SK | J312 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33210 | N | N | 20 | HARD LANDSCAPING |  | 125336 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 430 | KERBSTONE MASON SK
%R | 503988 | 6359 | 125338 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9HDEX5095 | Cobble Stone Works | 8170 | 128 | 0 | 160 | 0 | 250 | 250 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-25 08:00 | 2014-10-20 17:00 |  | 2014-09-07 08:00 | 2014-09-29 17:00 | 2014-09-07 08:00 | 2014-09-29 17:00 | 2014-09-07 08:00 | 2014-09-29 17:00 | 2014-09-25 08:00 | 2014-10-20 17:00 |  | PT_Normal |  |  |  |  | XV0O3MusRjGfwoKWSvEumg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43470 |  |  |  |  | TILE MASON SK | J309 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33210 | N | N | 20 | HARD LANDSCAPING |  | 125336 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 250 | TILE MASON SK
%R | 503989 | 6359 | 125338 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9HDEX5100 | Interlock works | 8174 | 128 | 0 | 160 | 0 | 290 | 290 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-02 08:00 | 2014-10-27 17:00 |  | 2014-09-14 08:00 | 2014-10-06 17:00 | 2014-09-14 08:00 | 2014-10-06 17:00 | 2014-09-14 08:00 | 2014-10-06 17:00 | 2014-10-02 08:00 | 2014-10-27 17:00 |  | PT_Normal |  |  |  |  | 9i5tmjb7SC6tKVIo0iY4Ag |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43510 |  |  |  |  | INTERLOCK MASON SK | J313 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33210 | N | N | 20 | HARD LANDSCAPING |  | 125336 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 290 | INTERLOCK MASON SK
%R | 503990 | 6359 | 125339 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9SLEX5105 | Laying of Grass/ green area | 8178 | 128 | 0 | 200 | 0 | 3430 | 3430 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-08 08:00 | 2014-11-08 17:00 |  | 2014-09-20 08:00 | 2014-10-20 17:00 | 2014-09-20 08:00 | 2014-10-20 17:00 | 2014-09-20 08:00 | 2014-10-20 17:00 | 2014-10-08 08:00 | 2014-11-08 17:00 |  | PT_Normal |  |  |  |  | auOD0ScVROOmmzoIbcmKOQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33220 | N | N | 25 | SOFT LANDSCAPING |  | 125336 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 1715 | LABOR- SUBCONTRACTOR
%R | 503991 | 6359 | 125339 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9SLEX5110 | Laying of Palm tree | 8178 | 128 | 128 | 200 | 0 | 210 | 210 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | CaE/o+xZTwy7EVDFLC5wmA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33220 | N | N | 25 | SOFT LANDSCAPING |  | 125336 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 105 | LABOR- SUBCONTRACTOR
%R | 503992 | 6359 | 125340 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 8178 | 272 | 272 | 200 | 0 | 400 | 400 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-16 08:00 | 2014-12-14 17:00 |  | 2014-10-05 08:00 | 2014-11-04 17:00 | 2014-10-05 08:00 | 2014-11-04 17:00 | 2014-10-05 08:00 | 2014-11-04 17:00 | 2014-11-16 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | dyqQlptaRV29JmLfKGdVDw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 16:35 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33190 | N | N | 10 | MISCELLANEOUS |  | 125336 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 400 | LABOR- SUBCONTRACTOR
%R | 503993 | 6359 | 125340 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9MSEX5020 | Construction Entrance Ramp | 8164 | 128 | 0 | 200 | 0 | 820 | 820 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-31 08:00 | 2014-09-28 17:00 |  | 2014-08-12 08:00 | 2014-09-09 17:00 | 2014-08-12 08:00 | 2014-09-09 17:00 | 2014-08-12 08:00 | 2014-09-09 17:00 | 2014-08-31 08:00 | 2014-09-28 17:00 |  | PT_Normal |  |  |  |  | QMvBqi2gTdCfz9XeusLl/g |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43410 |  |  |  |  | SCREED MASON SK | J303 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33190 | N | N | 10 | MISCELLANEOUS |  | 125336 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 820 | SCREED MASON SK
%R | 503994 | 6359 | 125340 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9MSEX5025 | SS.Handrails and Balustrades | 8178 | 152 | 0 | 160 | 0 | 70 | 70 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-21 08:00 | 2014-10-15 17:00 |  | 2014-08-30 08:00 | 2014-09-21 17:00 | 2014-08-30 08:00 | 2014-09-21 17:00 | 2014-08-30 08:00 | 2014-09-21 17:00 | 2014-09-21 08:00 | 2014-10-15 17:00 |  | PT_Normal |  |  |  |  | 88K2qyWcReqBSuazvfsTZQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33190 | N | N | 10 | MISCELLANEOUS |  | 125336 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 70 | LABOR- SUBCONTRACTOR
%R | 503995 | 6359 | 125340 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9MSEX5015 | Construction of grease Trap | 8178 | 72 | 0 | 160 | 0 | 70 | 70 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-31 08:00 | 2014-08-26 17:00 |  | 2014-07-21 08:00 | 2014-08-16 17:00 | 2014-07-21 08:00 | 2014-08-16 17:00 | 2014-07-21 08:00 | 2014-08-16 17:00 | 2014-07-31 08:00 | 2014-08-26 17:00 |  | PT_Normal |  |  |  |  | uWLWkwQYQAKCgM2PiFYjlQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33190 | N | N | 10 | MISCELLANEOUS |  | 125336 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 70 | LABOR- SUBCONTRACTOR
%R | 503996 | 6359 | 125340 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9MSEX5000 | Construction of Manholes | 8172 | 72 | 0 | 200 | 0 | 660 | 660 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-28 08:00 | 2014-07-26 17:00 |  | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-17 08:00 | 2014-07-15 17:00 | 2014-06-28 08:00 | 2014-07-26 17:00 |  | PT_Normal |  |  |  |  | arC4uHZTR92DK2dH5K+acQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33190 | N | N | 10 | MISCELLANEOUS |  | 125336 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 660 | MANHOLES SK
%R | 503997 | 6359 | 125340 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9MSEX5005 | Construction of Soak pit, Chambers | 8172 | 72 | 0 | 200 | 0 | 220 | 220 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-12 08:00 | 2014-08-12 17:00 |  | 2014-07-01 08:00 | 2014-07-29 17:00 | 2014-07-01 08:00 | 2014-07-29 17:00 | 2014-07-01 08:00 | 2014-07-29 17:00 | 2014-07-12 08:00 | 2014-08-12 17:00 |  | PT_Normal |  |  |  |  | pnm6cnLIRzOXmDGTUx9vkg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43490 |  |  |  |  | MANHOLES SK | J311 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33190 | N | N | 10 | MISCELLANEOUS |  | 125336 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 220 | MANHOLES SK
%R | 503998 | 6359 | 125340 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9MSEX5010 | Telephone cable laying | 8177 | 72 | 0 | 200 | 0 | 500 | 500 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-27 08:00 | 2014-09-24 17:00 |  | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-17 08:00 | 2014-09-14 17:00 | 2014-08-27 08:00 | 2014-09-24 17:00 |  | PT_Normal |  |  |  |  | fTtSliaETlCTqIL/Ic9aCg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43540 |  |  |  |  | LABOR - CIVIL | LC30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33190 | N | N | 10 | MISCELLANEOUS |  | 125336 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 500 | LABOR - CIVIL
%R | 503999 | 6359 | 125341 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ACTC8000 | Pre-Commissioning & Testing of AC Works | 8178 | 0 | 0 | 200 | 0 | 1500 | 1500 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-16 08:00 | 2014-12-14 17:00 |  | 2014-11-16 08:00 | 2014-12-14 17:00 | 2014-11-16 08:00 | 2014-12-14 17:00 | 2014-11-16 08:00 | 2014-12-14 17:00 | 2014-11-16 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | RnO8xAOpS7q9Y5yXsQVlxg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33230 | N | N | 30 | TESTING AND COMMISSIONING |  | 125335 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 1500 | LABOR- SUBCONTRACTOR
%R | 504000 | 6359 | 125341 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-16 08:00 | 2014-12-14 17:00 |  | 2014-11-16 08:00 | 2014-12-14 17:00 | 2014-11-16 08:00 | 2014-12-14 17:00 | 2014-11-16 08:00 | 2014-12-14 17:00 | 2014-11-16 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | 4/akdkDsSVWr1l94w9G7DA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33230 | N | N | 30 | TESTING AND COMMISSIONING |  | 125335 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 504001 | 6359 | 125341 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 8178 | 0 | 0 | 200 | 0 | 3000 | 3000 | 200 | 0 | 0 | 0 |  |  |  | 2014-11-16 08:00 | 2014-12-14 17:00 |  | 2014-11-16 08:00 | 2014-12-14 17:00 | 2014-11-16 08:00 | 2014-12-14 17:00 | 2014-11-16 08:00 | 2014-12-14 17:00 | 2014-11-16 08:00 | 2014-12-14 17:00 |  | PT_Normal |  |  |  |  | afFUzvO9RMOE4+jC+YBDug |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33230 | N | N | 30 | TESTING AND COMMISSIONING |  | 125335 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP11 |  | 3000 | LABOR- SUBCONTRACTOR
%R | 504002 | 6359 | 125344 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9PLFF4325 | Installation of Plumbing pipes & testing | 8178 | 0 | 0 | 144 | 0 | 552 | 552 | 144 | 0 | 0 | 0 |  |  |  | 2014-07-05 08:00 | 2014-07-24 17:00 |  | 2014-07-05 08:00 | 2014-07-24 17:00 | 2014-07-05 08:00 | 2014-07-24 17:00 | 2014-07-05 08:00 | 2014-07-24 17:00 | 2014-07-05 08:00 | 2014-07-24 17:00 |  | PT_Normal |  |  |  |  | Dsdo6y7YT7SL8r6epOejHg |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33110 | N | N | 15 | FIRST FLOORS |  | 125343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 552 | LABOR- SUBCONTRACTOR
%R | 504003 | 6359 | 125344 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9PLFF4330 | Installation of Drainage pipes & testing | 8178 | 176 | 176 | 144 | 0 | 222 | 222 | 144 | 0 | 0 | 0 |  |  |  | 2014-07-30 08:00 | 2014-08-23 17:00 |  | 2014-07-05 08:00 | 2014-07-24 17:00 | 2014-07-05 08:00 | 2014-07-24 17:00 | 2014-07-05 08:00 | 2014-07-24 17:00 | 2014-07-30 08:00 | 2014-08-23 17:00 |  | PT_Normal |  |  |  |  | XQP3yBQFRbSMEvHNehcn4A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33110 | N | N | 15 | FIRST FLOORS |  | 125343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 222 | LABOR- SUBCONTRACTOR
%R | 504004 | 6359 | 125344 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9PLFF4335 | Sanitary Fittings & Accessories | 8178 | 40 | 0 | 160 | 0 | 84 | 84 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-28 08:00 | 2014-10-22 17:00 |  | 2014-09-22 08:00 | 2014-10-16 17:00 | 2014-09-22 08:00 | 2014-10-16 17:00 | 2014-09-22 08:00 | 2014-10-16 17:00 | 2014-09-28 08:00 | 2014-10-22 17:00 |  | PT_Normal |  |  |  |  | fuc63KdiRuO51bdU1B4Z/Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33110 | N | N | 15 | FIRST FLOORS |  | 125343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 84 | LABOR- SUBCONTRACTOR
%R | 504005 | 6359 | 125344 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9PLFF4340 | Installation of Water Heater | 8178 | 40 | 32 | 120 | 0 | 84 | 84 | 120 | 0 | 0 | 0 |  |  |  | 2014-10-12 08:00 | 2014-10-28 17:00 |  | 2014-10-04 08:00 | 2014-10-22 17:00 | 2014-10-04 08:00 | 2014-10-22 17:00 | 2014-10-04 08:00 | 2014-10-22 17:00 | 2014-10-12 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | j366OIuJQpWaszjHjHXOdQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33110 | N | N | 15 | FIRST FLOORS |  | 125343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 84 | LABOR- SUBCONTRACTOR
%R | 504006 | 6359 | 125345 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9PLGF4305 | Installation of Plumbing pipes & testing | 8178 | 144 | 0 | 144 | 0 | 552 | 552 | 144 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-07-02 17:00 |  | 2014-05-22 08:00 | 2014-06-11 17:00 | 2014-05-22 08:00 | 2014-06-11 17:00 | 2014-05-22 08:00 | 2014-06-11 17:00 | 2014-06-12 08:00 | 2014-07-02 17:00 |  | PT_Normal |  |  |  |  | ZPRYgzmzTIG61SlHIKYCsw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33100 | N | N | 10 | GROUND FLOOR |  | 125343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 552 | LABOR- SUBCONTRACTOR
%R | 504007 | 6359 | 125345 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9PLGF4310 | Installation of Drainage pipes &testing | 8178 | 168 | 96 | 144 | 0 | 222 | 222 | 144 | 0 | 0 | 0 |  |  |  | 2014-06-16 08:00 | 2014-07-06 17:00 |  | 2014-05-22 08:00 | 2014-06-11 17:00 | 2014-05-22 08:00 | 2014-06-11 17:00 | 2014-05-22 08:00 | 2014-06-11 17:00 | 2014-06-16 08:00 | 2014-07-06 17:00 |  | PT_Normal |  |  |  |  | /2PExLhbTsqqUf5375RcRg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33100 | N | N | 10 | GROUND FLOOR |  | 125343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 222 | LABOR- SUBCONTRACTOR
%R | 504008 | 6359 | 125345 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9PLGF4315 | Sanitary Fittings & Accessories | 8178 | 360 | 0 | 160 | 0 | 168 | 168 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-09 17:00 |  | 2014-08-24 08:00 | 2014-09-15 17:00 | 2014-08-24 08:00 | 2014-09-15 17:00 | 2014-08-24 08:00 | 2014-09-15 17:00 | 2014-10-18 08:00 | 2014-11-09 17:00 |  | PT_Normal |  |  |  |  | Zi3vH3K/Q4W8u1RC2gwypw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33100 | N | N | 10 | GROUND FLOOR |  | 125343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 168 | LABOR- SUBCONTRACTOR
%R | 504009 | 6359 | 125345 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9PLGF4320 | Installation of Water Heater | 8178 | 360 | 360 | 120 | 0 | 168 | 168 | 120 | 0 | 0 | 0 |  |  |  | 2014-10-29 08:00 | 2014-11-15 17:00 |  | 2014-09-04 08:00 | 2014-09-21 17:00 | 2014-09-04 08:00 | 2014-09-21 17:00 | 2014-09-04 08:00 | 2014-09-21 17:00 | 2014-10-29 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | 43G4NX80Rhy56qSIy7klMw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33100 | N | N | 10 | GROUND FLOOR |  | 125343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 168 | LABOR- SUBCONTRACTOR
%R | 504010 | 6359 | 125345 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9PLUG4300 | Drainage / Storm Pipes in Grade Slab | 8178 | 0 | 0 | 128 | 0 | 84 | 84 | 128 | 0 | 0 | 0 |  |  |  | 2014-01-28 08:00 | 2014-02-16 17:00 |  | 2014-01-28 08:00 | 2014-02-16 17:00 | 2014-01-28 08:00 | 2014-02-16 17:00 | 2014-01-28 08:00 | 2014-02-16 17:00 | 2014-01-28 08:00 | 2014-02-16 17:00 |  | PT_Normal |  |  |  |  | CQ0++FjsR4a0iM5IOEshSA |  |  |  | Y | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33100 | N | N | 10 | GROUND FLOOR |  | 125343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP01 |  | 84 | LABOR- SUBCONTRACTOR
%R | 504011 | 6359 | 125346 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9PLRF4345 | Installation of Plumbing pipes & fittings | 8178 | 416 | 208 | 120 | 0 | 138 | 138 | 120 | 0 | 0 | 0 |  |  |  | 2014-09-30 08:00 | 2014-10-19 17:00 |  | 2014-07-28 08:00 | 2014-08-17 17:00 | 2014-07-28 08:00 | 2014-08-17 17:00 | 2014-07-28 08:00 | 2014-08-17 17:00 | 2014-09-30 08:00 | 2014-10-19 17:00 |  | PT_Normal |  |  |  |  | CGnpblrzSESAZZzPlM0GWQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33120 | N | N | 20 | ROOF |  | 125343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 138 | LABOR- SUBCONTRACTOR
%R | 504012 | 6359 | 125346 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9PLRF4350 | Installation of Rain water Pipes | 8178 | 208 | 136 | 120 | 0 | 84 | 84 | 120 | 0 | 0 | 0 |  |  |  | 2014-10-12 08:00 | 2014-10-28 17:00 |  | 2014-09-09 08:00 | 2014-09-25 17:00 | 2014-09-09 08:00 | 2014-09-25 17:00 | 2014-09-09 08:00 | 2014-09-25 17:00 | 2014-10-12 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | OFSSwShgT4CXt5Gf0pdnKg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33120 | N | N | 20 | ROOF |  | 125343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 84 | LABOR- SUBCONTRACTOR
%R | 504013 | 6359 | 125346 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9PLRF4355 | Roof Water Tank Installation & Connections | 8178 | 8 | 8 | 200 | 0 | 420 | 420 | 200 | 0 | 0 | 0 |  |  |  | 2014-10-18 08:00 | 2014-11-15 17:00 |  | 2014-10-16 08:00 | 2014-11-13 17:00 | 2014-10-16 08:00 | 2014-11-13 17:00 | 2014-10-16 08:00 | 2014-11-13 17:00 | 2014-10-18 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | IvM5I04TSXa69oWVDrIOvw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33120 | N | N | 20 | ROOF |  | 125343 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 420 | LABOR- SUBCONTRACTOR
%R | 504014 | 6359 | 125348 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ELFF4035 | Fixing of wall conduits & switch socket boxes | 8178 | 88 | 0 | 200 | 0 | 1528 | 1528 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-06 08:00 | 2014-08-06 17:00 |  | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-06-23 08:00 | 2014-07-21 17:00 | 2014-07-06 08:00 | 2014-08-06 17:00 |  | PT_Normal |  |  |  |  | xjMaI8JAQ4q5hZopMxHxaQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33070 | N | N | 15 | FIRST FLOORS |  | 125347 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1528 | LABOR- SUBCONTRACTOR
%R | 504015 | 6359 | 125348 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ELFF4040 | Cable tray & trunking installation | 8178 | 232 | 16 | 160 | 0 | 1648 | 1648 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-11 08:00 | 2014-09-02 17:00 |  | 2014-07-05 08:00 | 2014-07-27 17:00 | 2014-07-05 08:00 | 2014-07-27 17:00 | 2014-07-05 08:00 | 2014-07-27 17:00 | 2014-08-11 08:00 | 2014-09-02 17:00 |  | PT_Normal |  |  |  |  | m5iJ+0sbS76gMKKzE8vsPg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33070 | N | N | 15 | FIRST FLOORS |  | 125347 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07 |  | 1648 | LABOR- SUBCONTRACTOR
%R | 504016 | 6359 | 125348 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ELFF4045 | Installation of wiring & Main Cabling | 8178 | 216 | 216 | 200 | 0 | 370 | 370 | 200 | 0 | 0 | 0 |  |  |  | 2014-08-19 08:00 | 2014-09-16 17:00 |  | 2014-07-15 08:00 | 2014-08-16 17:00 | 2014-07-15 08:00 | 2014-08-16 17:00 | 2014-07-15 08:00 | 2014-08-16 17:00 | 2014-08-19 08:00 | 2014-09-16 17:00 |  | PT_Normal |  |  |  |  | /7VxRGWCTOqMbG+3SWp57w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33070 | N | N | 15 | FIRST FLOORS |  | 125347 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP07; period 2: 2014-AP08 |  | 185 | LABOR- SUBCONTRACTOR
%R | 504017 | 6359 | 125348 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ELFF4060 | Installation of DBS,MCCB Accessories. | 8178 | 24 | 16 | 160 | 0 | 284 | 284 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-22 08:00 | 2014-10-16 17:00 |  | 2014-09-18 08:00 | 2014-10-13 17:00 | 2014-09-18 08:00 | 2014-10-13 17:00 | 2014-09-18 08:00 | 2014-10-13 17:00 | 2014-09-22 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | fyZx7ZVXTxmoCgFsxREaUQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33070 | N | N | 15 | FIRST FLOORS |  | 125347 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09 |  | 284 | LABOR- SUBCONTRACTOR
%R | 504018 | 6359 | 125348 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ELFF4065 | Installation of Lighting fixtures & Accessories | 8178 | 8 | 0 | 200 | 0 | 2064 | 2064 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-28 08:00 | 2014-10-28 17:00 |  | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-09-27 08:00 | 2014-10-27 17:00 | 2014-09-28 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | 1mCQb+32QN6V7spyCm1Wpw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33070 | N | N | 15 | FIRST FLOORS |  | 125347 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 1032 | LABOR- SUBCONTRACTOR
%R | 504019 | 6359 | 125348 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 8178 | 8 | 8 | 200 | 0 | 1260 | 1260 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-16 08:00 | 2014-10-16 17:00 |  | 2014-09-15 08:00 | 2014-10-15 17:00 | 2014-09-15 08:00 | 2014-10-15 17:00 | 2014-09-15 08:00 | 2014-10-15 17:00 | 2014-09-16 08:00 | 2014-10-16 17:00 |  | PT_Normal |  |  |  |  | oYpPfpvXQzOZpcC8FhwZ9w |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33070 | N | N | 15 | FIRST FLOORS |  | 125347 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 630 | LABOR- SUBCONTRACTOR
%R | 504020 | 6359 | 125348 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ELFF4050 | Installation of Telephone System | 8178 | 72 | 64 | 200 | 0 | 564 | 564 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-25 08:00 | 2014-10-26 17:00 |  | 2014-09-15 08:00 | 2014-10-15 17:00 | 2014-09-15 08:00 | 2014-10-15 17:00 | 2014-09-15 08:00 | 2014-10-15 17:00 | 2014-09-25 08:00 | 2014-10-26 17:00 |  | PT_Normal |  |  |  |  | S1pu0ke/TyOAsGMO3s01zQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33070 | N | N | 15 | FIRST FLOORS |  | 125347 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP09; period 2: 2014-AP10 |  | 282 | LABOR- SUBCONTRACTOR
%R | 504021 | 6359 | 125349 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ELGF4000 | Fixing of wall conduits & switch socket boxes | 8178 | 216 | 0 | 200 | 0 | 1528 | 1528 | 200 | 0 | 0 | 0 |  |  |  | 2014-06-12 08:00 | 2014-07-10 17:00 |  | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-05-12 08:00 | 2014-06-09 17:00 | 2014-06-12 08:00 | 2014-07-10 17:00 |  | PT_Normal |  |  |  |  | oipdp665SpyRJftGGI4Lqg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33060 | N | N | 10 | GROUND FLOOR |  | 125347 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1528 | LABOR- SUBCONTRACTOR
%R | 504022 | 6359 | 125349 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ELGF4005 | Cable tray & trunking installation | 8178 | 360 | 0 | 160 | 0 | 1648 | 1648 | 160 | 0 | 0 | 0 |  |  |  | 2014-07-15 08:00 | 2014-08-10 17:00 |  | 2014-05-24 08:00 | 2014-06-15 17:00 | 2014-05-24 08:00 | 2014-06-15 17:00 | 2014-05-24 08:00 | 2014-06-15 17:00 | 2014-07-15 08:00 | 2014-08-10 17:00 |  | PT_Normal |  |  |  |  | yerjNK/WTlemNxmn6uKmzQ |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33060 | N | N | 10 | GROUND FLOOR |  | 125347 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP05 |  | 1648 | LABOR- SUBCONTRACTOR
%R | 504023 | 6359 | 125349 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ELGF4010 | Installation of wiring & Main Cabling | 8178 | 360 | 216 | 200 | 0 | 370 | 370 | 200 | 0 | 0 | 0 |  |  |  | 2014-07-23 08:00 | 2014-08-24 17:00 |  | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-06-01 08:00 | 2014-06-29 17:00 | 2014-07-23 08:00 | 2014-08-24 17:00 |  | PT_Normal |  |  |  |  | 359xiebRSyqUiJiZUexWKg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33060 | N | N | 10 | GROUND FLOOR |  | 125347 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 370 | LABOR- SUBCONTRACTOR
%R | 504024 | 6359 | 125349 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ELGF4020 | Installation of DBS,MCCB Accessories. | 8178 | 144 | 0 | 160 | 0 | 284 | 284 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-02 08:00 | 2014-09-24 17:00 |  | 2014-08-12 08:00 | 2014-09-03 17:00 | 2014-08-12 08:00 | 2014-09-03 17:00 | 2014-08-12 08:00 | 2014-09-03 17:00 | 2014-09-02 08:00 | 2014-09-24 17:00 |  | PT_Normal |  |  |  |  | NS4AIIt8Tam2JSoGS7yl+A |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33060 | N | N | 10 | GROUND FLOOR |  | 125347 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 284 | LABOR- SUBCONTRACTOR
%R | 504025 | 6359 | 125349 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ELGF4025 | Installation of Lighting fixtures & Accessories | 8178 | 200 | 192 | 200 | 0 | 2064 | 2064 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-22 08:00 | 2014-10-22 17:00 |  | 2014-08-24 08:00 | 2014-09-21 17:00 | 2014-08-24 08:00 | 2014-09-21 17:00 | 2014-08-24 08:00 | 2014-09-21 17:00 | 2014-09-22 08:00 | 2014-10-22 17:00 |  | PT_Normal |  |  |  |  | 7THxEovvStG/m2krTqXKBg |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33060 | N | N | 10 | GROUND FLOOR |  | 125347 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 2064 | LABOR- SUBCONTRACTOR
%R | 504026 | 6359 | 125349 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 8178 | 240 | 232 | 200 | 0 | 1344 | 1344 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-10 08:00 | 2014-10-08 17:00 |  | 2014-08-06 08:00 | 2014-09-03 17:00 | 2014-08-06 08:00 | 2014-09-03 17:00 | 2014-08-06 08:00 | 2014-09-03 17:00 | 2014-09-10 08:00 | 2014-10-08 17:00 |  | PT_Normal |  |  |  |  | Og1siRPPT1KOntglbZHXWA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33060 | N | N | 10 | GROUND FLOOR |  | 125347 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 1344 | LABOR- SUBCONTRACTOR
%R | 504027 | 6359 | 125349 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ELGF4030 | Installation of Telephone System | 8178 | 144 | 72 | 160 | 0 | 650 | 650 | 160 | 0 | 0 | 0 |  |  |  | 2014-09-14 08:00 | 2014-10-06 17:00 |  | 2014-08-24 08:00 | 2014-09-15 17:00 | 2014-08-24 08:00 | 2014-09-15 17:00 | 2014-08-24 08:00 | 2014-09-15 17:00 | 2014-09-14 08:00 | 2014-10-06 17:00 |  | PT_Normal |  |  |  |  | i1GHa/P9RQ+CPAi9ILjoBw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33060 | N | N | 10 | GROUND FLOOR |  | 125347 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 650 | LABOR- SUBCONTRACTOR
%R | 504028 | 6359 | 125350 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ELRF4070 | Installation of Isolator | 8178 | 8 | 0 | 144 | 0 | 516 | 516 | 144 | 0 | 0 | 0 |  |  |  | 2014-10-14 08:00 | 2014-11-03 17:00 |  | 2014-10-13 08:00 | 2014-11-02 17:00 | 2014-10-13 08:00 | 2014-11-02 17:00 | 2014-10-13 08:00 | 2014-11-02 17:00 | 2014-10-14 08:00 | 2014-11-03 17:00 |  | PT_Normal |  |  |  |  | x/8N+AG3SWO7AlvF1KgdOw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33080 | N | N | 20 | ROOF |  | 125347 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 516 | LABOR- SUBCONTRACTOR
%R | 504029 | 6359 | 125350 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ELRF4075 | Installation of TV Dish Antenna | 8178 | 8 | 8 | 184 | 0 | 916 | 916 | 184 | 0 | 0 | 0 |  |  |  | 2014-10-20 08:00 | 2014-11-15 17:00 |  | 2014-10-19 08:00 | 2014-11-13 17:00 | 2014-10-19 08:00 | 2014-11-13 17:00 | 2014-10-19 08:00 | 2014-11-13 17:00 | 2014-10-20 08:00 | 2014-11-15 17:00 |  | PT_Normal |  |  |  |  | c9xjCQU+Qt+kDdXtSR4LJw |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33080 | N | N | 20 | ROOF |  | 125347 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP10 |  | 916 | LABOR- SUBCONTRACTOR
%R | 504030 | 6359 | 125352 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ACGF4600 | Installation AC Pipes | 8178 | 392 | 224 | 160 | 0 | 1222 | 1222 | 160 | 0 | 0 | 0 |  |  |  | 2014-08-11 08:00 | 2014-09-02 17:00 |  | 2014-06-11 08:00 | 2014-07-03 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 | 2014-06-11 08:00 | 2014-07-03 17:00 | 2014-08-11 08:00 | 2014-09-02 17:00 |  | PT_Normal |  |  |  |  | dYRCZB6OTg64iKz66nV4TA |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33140 | N | N | 10 | GROUND FLOOR |  | 125351 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP06 |  | 1222 | LABOR- SUBCONTRACTOR
%R | 504031 | 6359 | 125352 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ACGF4605 | Fixing of Ventilation Equipments | 8178 | 256 | 0 | 200 | 0 | 228 | 228 | 200 | 0 | 0 | 0 |  |  |  | 2014-09-13 08:00 | 2014-10-13 17:00 |  | 2014-08-06 08:00 | 2014-09-03 17:00 | 2014-08-06 08:00 | 2014-09-03 17:00 | 2014-08-06 08:00 | 2014-09-03 17:00 | 2014-09-13 08:00 | 2014-10-13 17:00 |  | PT_Normal |  |  |  |  | Q+eOCx4aSQay8gc0M4CX5Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33140 | N | N | 10 | GROUND FLOOR |  | 125351 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 228 | LABOR- SUBCONTRACTOR
%R | 504032 | 6359 | 125352 | 13662 | 0 | N | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | DUKHCONP1AZ9ACGF4610 | Fixing of Split AC | 8178 | 256 | 88 | 160 | 0 | 370 | 370 | 160 | 0 | 0 | 0 |  |  |  | 2014-10-04 08:00 | 2014-10-28 17:00 |  | 2014-08-27 08:00 | 2014-09-18 17:00 | 2014-08-27 08:00 | 2014-09-18 17:00 | 2014-08-27 08:00 | 2014-09-18 17:00 | 2014-10-04 08:00 | 2014-10-28 17:00 |  | PT_Normal |  |  |  |  | 6Oy/YhtRR4qpz1WyWvK/6Q |  |  |  | N | 0 | 0 |  |  | 2013-02-16 15:54 | 2013-02-16 15:56 | admin | admin | 8149 |  |  |  |  | 43550 |  |  |  |  | LABOR- SUBCONTRACTOR | LS30 |  | 1 | QT_Hour |  | Y | Y | Y | 1 |  | RT_Labor |  |  |  |  | 540 | 33140 | N | N | 10 | GROUND FLOOR |  | 125351 |  | 0 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_PF_cpi |  |  | period 1: 2014-AP08 |  | 370 | LABOR- SUBCONTRACTOR